## Overview
OWP JOB 2045 — GRE NOTCH APARTMENTS
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$2,110,205 |  | $1,138,172 |  | $972,033 |  | 14,775
Billed to date (Sage AR) |  | 53.9% of revenue |  | 46.1% margin |  | 39 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 595919 | 404811.73 | 191107.27 | 67.93% | 35.57%
Material | 608708 | 497590.37 | 111117.63 | 81.75% | 43.72%
Overhead | 30300 | 25141.3 | 5158.7 | 82.97% | 2.209%
Burden | 314997.06 | 210628.6 | 104368.46 | 66.87% | 18.51%
TOTAL (expense codes) | 1549924.06 | 1138172 | 411752.06 | 73.43% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 615682.1 | 54.09% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 460396.87 | 40.45% | Material + subcontractor spend
GL (General Ledger) | 62093.03 | 5.456% | Misc adjustments + deposits
AR (Billings, credit) | -2110205 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2045
Project identity + metadata enriched from GDrive close-out package (Notch Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2045 | JDR cover page
job_name | GRE Notch Apartments | Notch Apartments project info PDF
job_name_long | GRE Construction Notch Apartments (Newcastle) | Notch Apartments project info PDF
general_contractor | GRE | Signed subcontract 7927 — Shelter Holdings / Newcastle II LLC
owner | Newcastle II LLC | Signed subcontract §A.a — Newcastle II LLC
architect | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) | Contract counterparty: Newcastle II LLC
location | 13800 Newcastle Golf Club Road, Newcastle, WA 98059 | Signed subcontract + permit records
project_type | Mid-rise multi-family apartments (187 residential units: 179 Type B + 8 Type A ADA) with L1 lobby/lounge + L2 leasing office + rooftop deck amenity. Post-tension deck construction with Hydroflame sleeves. | Scope doc + submittal TOC (6-story mixed-use + 2 parking levels)
unit_count | 187 | Plan drawings: 6-story, 187 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 1804 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from GRE Notch job ticket April 24 2019 (final revision): 187 toilets (179 Gerber SE 21-112 + 8 Gerber SE 21-118 ADA) + 187 Lenova PU-01-W lavs + 187 Aquatic 2603 tub/showers (179 std + 8 SMTE ADA) + 187 Pasco diverters + 8 Delta 57011 handheld + 158 Dayton/Elkay kitchen sinks (150 std + 8 ADA) + 158 ISE Badger 1 disposals + 158 DW roughin + 158 icemaker roughin + 158 washer roughin + 158 AO Smith ENT-50 WHs = 1,704 resident. L1 amenity (bike wash/lobby) 12 + L2 leasing 5 + rooftop 4. Building systems (sand/oil basin, pumps, garage drains, 38 L1 deck drains, 3 unit-310 drains, 6 L5 amenity drains, 6 roof drains w/overflow, 8 hose bibs, trash hose bib, booster pump, 3 backflows, backwater, methane vent) = 75. Total ≈ 1,800. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 5 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-09 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2019-12 | Final pay app 12/13/2019
duration_months | 27 | start → end
contract_signed | 2017-10-02 | Signed subcontract — Mike Donelson 10/02/17
permit_jurisdiction | City of Newcastle (via Notch Plumbing Permit Application) | City of Newcastle permit (Notch plumbing + fixture count)
permits_issued | Plumbing permit (with fixture count); Inspection requests log | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2045 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2045
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 1898200 | Code 999 original (negated)
current_contract_budget | 2110205 | Code 999 current (negated)
revenue_ar_billed | 2110205 | Sum of AR line items (abs)
retainage_outstanding | 105510.25 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 1366963.35 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 1549924.06 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 182960.71 | Revised − Original across expense codes
direct_cost | 1138172 | PR + AP + GL totals
net_profit | 972033 | abs(revenue) − direct_cost
gross_margin_pct | 46.06% | net / revenue

## Cost Categories
COST CATEGORIES — 2045
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 9 | 533695 | 595919 | 404811.73 | 191107.27 | 67.93% | PENDING (needs unit_count)
Material | 9 | 520410 | 608708 | 497590.37 | 111117.63 | 81.75% | PENDING (needs unit_count)
Overhead | 4 | 30000 | 30300 | 25141.3 | 5158.7 | 82.97% | PENDING (needs unit_count)
Burden | 2 | 282858.35 | 314997.06 | 210628.6 | 104368.46 | 66.87% | PENDING (needs unit_count)
Revenue | 1 | -1898200 | -2110205 | -2110205 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 12640 | 13040 | -3528.5 | 9511.5 | 0 | 0 | 183.5 | 0 | 0 | 72.94% | UNDER
101 | Takeoff & Purchase Labor | Labor | 19750 | 20150 | -6372 | 13778 | 0 | 0 | 254.5 | 0 | 0 | 68.38% | UNDER
110 | Underground Labor | Labor | 23250 | 44430 | -13114 | 31316 | 0 | 0 | 1053.5 | 44.5 | 0 | 70.48% | UNDER
111 | Garage Labor | Labor | 31020 | 42943 | -18233.75 | 24709.25 | 0 | 0 | 888 | 49.5 | 0 | 57.54% | UNDER
112 | Canout Labor | Labor | 5250 | 6120 | -889 | 5231 | 0 | 0 | 155 | 0 | 0 | 85.47% | UNDER
120 | Roughin Labor | Labor | 342805 | 360476 | -132873.52 | 227602.48 | 0 | 0 | 8287 | 273.5 | 0 | 63.14% | UNDER
130 | Finish Labor | Labor | 70680 | 71030 | -3783 | 67247 | 0 | 0 | 2528.5 | 0 | 0 | 94.67% | ON
141 | Water Main/Insulation Lab | Labor | 23050 | 29480 | -8439.5 | 21040.5 | 0 | 0 | 686.5 | 12 | 0 | 71.37% | UNDER
142 | Mech Room Labor | Labor | 5250 | 8250 | -3874 | 4376 | 0 | 0 | 125 | 0 | 0 | 53.04% | UNDER
210 | Underground Material | Material | 15530 | 29830 | -15294.21 | 14535.79 | 0 | 0 | 0 | 0 | 0 | 48.73% | UNDER
211 | Garage Material | Material | 30440 | 34850 | -18931.59 | 15918.41 | 0 | 0 | 0 | 0 | 0 | 45.68% | UNDER
212 | Canout Material | Material | 4500 | 5718 | -1394.58 | 4323.42 | 0 | 0 | 0 | 0 | 0 | 75.61% | UNDER
220 | Roughin Material | Material | 153390 | 158260 | -61069 | 97191 | 0 | 0 | 0 | 0 | 0 | 61.41% | UNDER
230 | Finish Material | Material | 274850 | 325525 | -32311.59 | 293213.41 | 0 | 0 | 0 | 0 | 0 | 90.07% | ON
240 | Gas Material | Material | 0 | 0 | 63.72 | 63.72 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
241 | Water Main/Insulation Mat | Material | 34700 | 44525 | 20718.62 | 65243.62 | 0 | 0 | 0 | 0 | 0 | 146.5% | OVER
242 | Mech Room Material | Material | 7000 | 10000 | -2899 | 7101 | 0 | 0 | 0 | 0 | 0 | 71.01% | UNDER
243 | Condensation Drains Mat | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
600 | Subcontractor | Overhead | 500 | 500 | 2912 | 3412 | 0 | 0 | 0 | 0 | 0 | 682.4% | CRITICAL
601 | Engineering/Plans | Overhead | 25000 | 25000 | -8921.75 | 16078.25 | 0 | 0 | 0 | 0 | 0 | 64.31% | UNDER
602 | Rental Equipment | Overhead | 3500 | 3800 | 1198.15 | 4998.15 | 0 | 0 | 0 | 0 | 0 | 131.5% | OVER
607 | Other Expenses | Overhead | 1000 | 1000 | -347.1 | 652.9 | 0 | 0 | 0 | 0 | 0 | 65.29% | UNDER
995 | Payroll Burden | Burden | 242030.68 | 269409.24 | -89767.69 | 179641.55 | 0 | 0 | 0 | 0 | 0 | 66.68% | UNDER
998 | Payroll Taxes | Burden | 40827.67 | 45587.82 | -14600.77 | 30987.05 | 0 | 0 | 0 | 0 | 0 | 67.97% | UNDER
999 | Sales | Revenue | -1898200 | -2110205 | 0 | -2110205 | 0 | -105510.25 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2045
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 9511.5 | 88 | 88 | 0 | 0 | 0 | Gerard, Jeffrey S ($9,236) | 01/04/19 | 12/29/17
101 | Takeoff & Purchase Labor | 13778 | 118 | 118 | 0 | 0 | 0 | Gerard, Jeffrey S ($8,203) | 01/04/19 | 12/29/17
110 | Underground Labor | 31316 | 76 | 76 | 0 | 0 | 0 | Quintanilla, Esteban R ($10,868) | 06/22/18 | 12/15/17
111 | Garage Labor | 24709.25 | 52 | 52 | 0 | 0 | 0 | Gerard, Mitchell J ($5,904) | 01/04/19 | 12/14/18
112 | Canout Labor | 5231 | 9 | 9 | 0 | 0 | 0 | Quintanilla, Esteban R ($3,735) | 08/03/18 | 09/21/18
120 | Roughin Labor | 227602.48 | 330 | 329 | 0 | 1 | 0 | Gerard, Mitchell J ($51,604) | 01/04/19 | 12/28/18
130 | Finish Labor | 67247 | 119 | 119 | 0 | 0 | 0 | Draves, Steven W ($12,960) | 05/10/19 | 12/27/19
141 | Water Main/Insulation Lab | 21040.5 | 39 | 39 | 0 | 0 | 0 | Lima Romero, Melvin A ($9,586) | 01/25/19 | 12/21/18
142 | Mech Room Labor | 4376 | 10 | 10 | 0 | 0 | 0 | McCabe, Thomas C ($1,890) | 05/24/19 | 07/26/19
210 | Underground Material | 14535.79 | 29 | 0 | 21 | 8 | 0 | Rosen Supply Kirkland ($8,318) | 06/26/18 | 12/22/17
211 | Garage Material | 15918.41 | 42 | 0 | 15 | 27 | 0 | Rosen Supply Kirkland ($12,614) | 01/11/19 | 12/21/18
212 | Canout Material | 4323.42 | 7 | 0 | 0 | 7 | 0 | Req 4545 ($3,100) | 08/10/18 | 10/22/18
220 | Roughin Material | 97191 | 127 | 0 | 83 | 44 | 0 | Rosen Supply Kirkland ($56,452) | 01/07/19 | 12/21/18
230 | Finish Material | 293213.41 | 123 | 0 | 82 | 41 | 0 | Keller Supply Company ($160,984) | 01/08/19 | 12/21/18
240 | Gas Material | 63.72 | 6 | 0 | 3 | 3 | 0 | Req 6427 ($133) | 05/29/19 | 12/21/18
241 | Water Main/Insulation Mat | 65243.62 | 85 | 0 | 59 | 26 | 0 | Consolidated Supply Co. ($29,674) | 01/07/19 | 11/26/18
242 | Mech Room Material | 7101 | 27 | 0 | 15 | 12 | 0 | Ferguson Enterprises, Inc. #3007 ($7,368) | 02/01/19 | 10/31/18
243 | Condensation Drains Mat | 0 | 3 | 0 | 0 | 3 | 0 | Req 6032 ($5) | 05/30/19 | 10/16/19
600 | Subcontractor | 3412 | 7 | 0 | 7 | 0 | 0 | Scan2Core, Inc. ($3,162) | 02/01/19 | 09/17/19
601 | Engineering/Plans | 16078.25 | 4 | 0 | 4 | 0 | 0 | Franklin Engineering ($16,078) | 01/05/18 | 11/22/17
602 | Rental Equipment | 4998.15 | 12 | 0 | 12 | 0 | 0 | Ahern Rentals ($4,799) | 01/08/19 | 11/28/18
607 | Other Expenses | 652.9 | 3 | 0 | 3 | 0 | 0 | Travelers ($445) | 01/19/18 | 09/13/17
995 | Payroll Burden | 179641.55 | 840 | 840 | 0 | 0 | 0 | Gerard, Mitchell J ($25,598) | 01/04/19 | 12/29/17
998 | Payroll Taxes | 30987.05 | 840 | 840 | 0 | 0 | 0 | Gerard, Mitchell J ($4,415) | 01/04/19 | 12/29/17
999 | Sales | -2110205 | 85 | 0 | 0 | 0 | 85 | GRE Construction, LLC $Notch ($2,552,995) | 01/18/19 | 12/13/19

## Transactions Detail
TRANSACTIONS DETAIL — 3,081 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17515 | 0 | 0
100 | Supervision | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 19577 | 0 | 0
100 | Supervision | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19638 | 0 | 0
100 | Supervision | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 19639 | 0 | 0
100 | Supervision | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 17826 | 0 | 0
100 | Supervision | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17827 | 0 | 0
100 | Supervision | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17892 | 0 | 0
100 | Supervision | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 97956 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98002 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
100 | Supervision | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 2.5 | 0 | 117.5 | 0 | 117.5 | 918605 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99501 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
100 | Supervision | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20163 | 0 | 0
100 | Supervision | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 290233 | 0 | 0
100 | Supervision | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20300 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
100 | Supervision | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 20401 | 0 | 0
100 | Supervision | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 920519 | 0 | 0
100 | Supervision | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20593 | 0 | 0
100 | Supervision | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20665 | 0 | 0
100 | Supervision | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 920737 | 0 | 0
100 | Supervision | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20809 | 0 | 0
100 | Supervision | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 7 | 0 | 350 | 0 | 350 | 20880 | 0 | 0
100 | Supervision | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90962 | 0 | 0
100 | Supervision | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91032 | 0 | 0
100 | Supervision | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21174 | 0 | 0
100 | Supervision | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21245 | 0 | 0
100 | Supervision | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90883 | 0 | 0
100 | Supervision | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 90884 | 0 | 0
100 | Supervision | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91392 | 0 | 0
100 | Supervision | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91392 | 0 | 0
100 | Supervision | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21467 | 0 | 0
100 | Supervision | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91542 | 0 | 0
100 | Supervision | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 175 | 0 | 175 | 21616 | 0 | 0
100 | Supervision | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 21687 | 0 | 0
100 | Supervision | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20892 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21837 | 0 | 0
100 | Supervision | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21912 | 0 | 0
100 | Supervision | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 260 | 0 | 260 | 921984 | 0 | 0
100 | Supervision | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22057 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22198 | 0 | 0
100 | Supervision | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922269 | 0 | 0
100 | Supervision | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22343 | 0 | 0
100 | Supervision | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22301 | 0 | 0
100 | Supervision | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22301 | 0 | 0
100 | Supervision | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922484 | 0 | 0
100 | Supervision | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922558 | 0 | 0
100 | Supervision | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 78 | 0 | 78 | 22769 | 0 | 0
100 | Supervision | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922910 | 0 | 0
100 | Supervision | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 22982 | 0 | 0
100 | Supervision | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 923054 | 0 | 0
100 | Supervision | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 23125 | 0 | 0
100 | Supervision | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 4.5 | 0 | 234 | 0 | 234 | 23273 | 0 | 0
100 | Supervision | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923346 | 0 | 0
100 | Supervision | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 5 | 0 | 260 | 0 | 260 | 23421 | 0 | 0
100 | Supervision | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923497 | 0 | 0
100 | Supervision | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 78 | 0 | 78 | 923497 | 0 | 0
100 | Supervision | PR | 813 | 04/24/19 | 04/26/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 23569 | 0 | 0
100 | Supervision | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 165 | 0 | 165 | 923644 | 0 | 0
100 | Supervision | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 23720 | 0 | 0
100 | Supervision | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 165 | 0 | 165 | 923799 | 0 | 0
100 | Supervision | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 923876 | 0 | 0
100 | Supervision | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 923953 | 0 | 0
100 | Supervision | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924030 | 0 | 0
100 | Supervision | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24104 | 0 | 0
100 | Supervision | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 192.5 | 0 | 192.5 | 24180 | 0 | 0
100 | Supervision | PR | 911 | 06/26/19 | 06/28/19 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 192.5 | 0 | 192.5 | 24255 | 0 | 0
100 | Supervision | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924330 | 0 | 0
100 | Supervision | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924330 | 0 | 0
100 | Supervision | PR | 353 | 07/10/19 | 07/12/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 220 | 0 | 220 | 924405 | 0 | 0
100 | Supervision | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24485 | 0 | 0
100 | Supervision | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24635 | 0 | 0
100 | Supervision | PR | 77 | 07/31/19 | 08/02/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924708 | 0 | 0
100 | Supervision | PR | 329 | 08/07/19 | 08/09/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 924782 | 0 | 0
100 | Supervision | PR | 637 | 08/14/19 | 08/16/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924856 | 0 | 0
100 | Supervision | PR | 874 | 08/21/19 | 08/23/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924932 | 0 | 0
100 | Supervision | PR | 1065 | 08/28/19 | 08/30/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 25009 | 0 | 0
100 | Supervision | PR | 86 | 09/04/19 | 09/06/19 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 192.5 | 0 | 192.5 | 925084 | 0 | 0
100 | Supervision | PR | 309 | 09/11/19 | 09/13/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 25158 | 0 | 0
100 | Supervision | PR | 706 | 09/25/19 | 09/27/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 165 | 0 | 165 | 925311 | 0 | 0
100 | Supervision | PR | 82 | 10/02/19 | 10/04/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 25389 | 0 | 0
100 | Supervision | PR | 335 | 10/09/19 | 10/11/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 925469 | 0 | 0
100 | Supervision | PR | 81 | 10/30/19 | 11/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 116 | 0 | 116 | 925697 | 0 | 0
100 | Supervision | PR | 254 | 11/06/19 | 11/08/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 58 | 0 | 58 | 925773 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 19577 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 19639 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 17701 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 4 | 0 | 200 | 0 | 200 | 17826 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 17827 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 17891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 17892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97955 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 97956 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98147 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 98214 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 918605 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 70.5 | 0 | 70.5 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 99576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 19721 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99793 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 290233 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920374 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920375 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20400 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20401 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 920518 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 920519 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 920519 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 20592 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20593 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20664 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 20665 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 920736 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 920737 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 20808 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 20809 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 20880 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 90961 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 90962 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91032 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21174 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21245 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 90883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 90884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 91391 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91392 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 21467 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91542 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21615 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21616 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21687 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 20892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 21836 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21837 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21912 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 921983 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 921984 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 22057 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922268 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922269 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22343 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22343 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 22301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922483 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922557 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922558 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22700 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 4.5 | 0 | 234 | 0 | 234 | 22700 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22769 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922840 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922909 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922910 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22982 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 923054 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23124 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 23125 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 923197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 923198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23272 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 23273 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923345 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923346 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 23421 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923497 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23568 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 923644 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 23720 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923798 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 110 | 0 | 110 | 923799 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24104 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 24254 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 546 | 09/18/19 | 09/20/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 925232 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 664 | 10/23/19 | 10/25/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 925504 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 80 | 10/30/19 | 11/01/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 925696 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 917 | 11/27/19 | 11/27/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 925998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 104 | 12/04/19 | 12/06/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 26076 | 0 | 0
110 | Underground Labor | PR | 58 | 10/04/17 | 10/06/17 | SA54 | Sanders, Allen O | 1.5 | 0 | 60 | 0 | 60 | 17630 | 0 | 0
110 | Underground Labor | PR | 217 | 10/11/17 | 10/13/17 | SA54 | Sanders, Allen O | 2.5 | 0 | 100 | 0 | 100 | 17693 | 0 | 0
110 | Underground Labor | PR | 33 | 11/01/17 | 11/03/17 | HU04 | Hubbard, Dustin R | 3 | 0 | 63 | 0 | 63 | 17857 | 0 | 0
110 | Underground Labor | PR | 432 | 12/13/17 | 12/15/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18246 | 0 | 0
110 | Underground Labor | PR | 691 | 06/20/18 | 06/22/18 | BE54 | Benites Portillo, Marvin E | 7 | 0 | 154 | 0 | 154 | 20170 | 0 | 0
110 | Underground Labor | PR | 694 | 06/20/18 | 06/22/18 | CO69 | Cornejo Orellana, Carlos E | 11 | 0 | 209 | 0 | 209 | 20173 | 0 | 0
110 | Underground Labor | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 12 | 0 | 540 | 0 | 540 | 20213 | 0 | 0
110 | Underground Labor | PR | 962 | 06/27/18 | 06/29/18 | CO69 | Cornejo Orellana, Carlos E | 20 | 0 | 380 | 0 | 380 | 20243 | 0 | 0
110 | Underground Labor | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 0 | 1.5 | 0 | 54 | 54 | 20271 | 0 | 0
110 | Underground Labor | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 6 | 0 | 144 | 0 | 144 | 20271 | 0 | 0
110 | Underground Labor | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 19.5 | 0 | 877.5 | 0 | 877.5 | 20282 | 0 | 0
110 | Underground Labor | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 15 | 0 | 675 | 0 | 675 | 20300 | 0 | 0
110 | Underground Labor | PR | 15 | 07/04/18 | 07/06/18 | CO69 | Cornejo Orellana, Carlos E | 12 | 0 | 228 | 0 | 228 | 20312 | 0 | 0
110 | Underground Labor | PR | 26 | 07/04/18 | 07/06/18 | ES09 | Escalante Escobar, Boanerge | 12 | 0 | 216 | 0 | 216 | 20322 | 0 | 0
110 | Underground Labor | PR | 46 | 07/04/18 | 07/06/18 | LO87 | Lovo, German G | 6 | 0 | 144 | 0 | 144 | 20342 | 0 | 0
110 | Underground Labor | PR | 306 | 07/11/18 | 07/13/18 | CO69 | Cornejo Orellana, Carlos E | 16 | 0 | 304 | 0 | 304 | 20386 | 0 | 0
110 | Underground Labor | PR | 337 | 07/11/18 | 07/13/18 | LO87 | Lovo, German G | 19 | 0 | 456 | 0 | 456 | 20417 | 0 | 0
110 | Underground Labor | PR | 348 | 07/11/18 | 07/13/18 | QU35 | Quintanilla, Esteban R | 29 | 0 | 1305 | 0 | 1305 | 20428 | 0 | 0
110 | Underground Labor | PR | 446 | 07/18/18 | 07/20/18 | CO69 | Cornejo Orellana, Carlos E | 16 | 0 | 304 | 0 | 304 | 20457 | 0 | 0
110 | Underground Labor | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 144 | 0 | 144 | 20467 | 0 | 0
110 | Underground Labor | PR | 487 | 07/18/18 | 07/20/18 | PO73 | Portillo Soriano, Walter A | 8 | 0 | 144 | 0 | 144 | 20497 | 0 | 0
110 | Underground Labor | PR | 488 | 07/18/18 | 07/20/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 720 | 0 | 720 | 20498 | 0 | 0
110 | Underground Labor | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 360 | 0 | 360 | 20572 | 0 | 0
110 | Underground Labor | PR | 14 | 08/01/18 | 08/03/18 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 320 | 0 | 320 | 20606 | 0 | 0
110 | Underground Labor | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 32 | 0 | 768 | 0 | 768 | 20634 | 0 | 0
110 | Underground Labor | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 720 | 0 | 720 | 20644 | 0 | 0
110 | Underground Labor | PR | 58 | 08/01/18 | 08/03/18 | RI84 | Rivera, Eli P | 32 | 0 | 864 | 0 | 864 | 20649 | 0 | 0
110 | Underground Labor | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 16 | 0 | 352 | 0 | 352 | 20671 | 0 | 0
110 | Underground Labor | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 480 | 0 | 480 | 20677 | 0 | 0
110 | Underground Labor | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 24 | 0 | 576 | 0 | 576 | 20706 | 0 | 0
110 | Underground Labor | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1080 | 0 | 1080 | 20716 | 0 | 0
110 | Underground Labor | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 32 | 0 | 864 | 0 | 864 | 20721 | 0 | 0
110 | Underground Labor | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 2 | 0 | 66 | 66 | 20744 | 0 | 0
110 | Underground Labor | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 704 | 0 | 704 | 20744 | 0 | 0
110 | Underground Labor | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 60 | 60 | 20750 | 0 | 0
110 | Underground Labor | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 160 | 0 | 160 | 20750 | 0 | 0
110 | Underground Labor | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 0 | 2 | 0 | 72 | 72 | 20778 | 0 | 0
110 | Underground Labor | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 40 | 0 | 960 | 0 | 960 | 20778 | 0 | 0
110 | Underground Labor | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 2 | 0 | 135 | 135 | 20788 | 0 | 0
110 | Underground Labor | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 360 | 0 | 360 | 20788 | 0 | 0
110 | Underground Labor | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 2 | 0 | 81 | 81 | 20793 | 0 | 0
110 | Underground Labor | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 32 | 0 | 864 | 0 | 864 | 20793 | 0 | 0
110 | Underground Labor | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 528 | 0 | 528 | 20816 | 0 | 0
110 | Underground Labor | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 3 | 0 | 90 | 90 | 20822 | 0 | 0
110 | Underground Labor | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 480 | 0 | 480 | 20822 | 0 | 0
110 | Underground Labor | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 3 | 0 | 108 | 108 | 20849 | 0 | 0
110 | Underground Labor | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 32 | 0 | 768 | 0 | 768 | 20849 | 0 | 0
110 | Underground Labor | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 2 | 0 | 135 | 135 | 20859 | 0 | 0
110 | Underground Labor | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1080 | 0 | 1080 | 20859 | 0 | 0
110 | Underground Labor | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 0 | 3 | 0 | 121.5 | 121.5 | 20864 | 0 | 0
110 | Underground Labor | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 40 | 0 | 1080 | 0 | 1080 | 20864 | 0 | 0
110 | Underground Labor | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 0 | 4 | 0 | 132 | 132 | 20898 | 0 | 0
110 | Underground Labor | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 20898 | 0 | 0
110 | Underground Labor | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 4 | 0 | 120 | 120 | 20904 | 0 | 0
110 | Underground Labor | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 20904 | 0 | 0
110 | Underground Labor | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 0 | 2 | 0 | 72 | 72 | 20932 | 0 | 0
110 | Underground Labor | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 40 | 0 | 960 | 0 | 960 | 20932 | 0 | 0
110 | Underground Labor | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 0 | 4 | 0 | 270 | 270 | 20941 | 0 | 0
110 | Underground Labor | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1800 | 0 | 1800 | 20941 | 0 | 0
110 | Underground Labor | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 0 | 4 | 0 | 162 | 162 | 20946 | 0 | 0
110 | Underground Labor | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 40 | 0 | 1080 | 0 | 1080 | 20946 | 0 | 0
110 | Underground Labor | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 176 | 0 | 176 | 20968 | 0 | 0
110 | Underground Labor | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 160 | 0 | 160 | 20974 | 0 | 0
110 | Underground Labor | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 23 | 0 | 552 | 0 | 552 | 21002 | 0 | 0
110 | Underground Labor | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 10 | 0 | 450 | 0 | 450 | 21011 | 0 | 0
110 | Underground Labor | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 8 | 0 | 216 | 0 | 216 | 21016 | 0 | 0
110 | Underground Labor | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 160 | 0 | 160 | 21115 | 0 | 0
110 | Underground Labor | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 21142 | 0 | 0
110 | Underground Labor | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 360 | 0 | 360 | 21152 | 0 | 0
110 | Underground Labor | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 21212 | 0 | 0
110 | Underground Labor | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 4 | 0 | 96 | 96 | 21815 | 0 | 0
110 | Underground Labor | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 16 | 0 | 256 | 0 | 256 | 21815 | 0 | 0
110 | Underground Labor | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 256 | 0 | 256 | 22042 | 0 | 0
110 | Underground Labor | PR | 666 | 09/25/19 | 09/27/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 25271 | 0 | 0
110 | Underground Labor | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 4 | 0 | 124 | 0 | 124 | 25274 | 0 | 0
110 | Underground Labor | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 25348 | 0 | 0
111 | Garage Labor | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 14 | 0 | 322 | 0 | 322 | 21263 | 0 | 0
111 | Garage Labor | PR | 692 | 09/26/18 | 09/28/18 | GE71 | Gerard, Mitchell J | 20 | 0 | 700 | 0 | 700 | 21270 | 0 | 0
111 | Garage Labor | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21294 | 0 | 0
111 | Garage Labor | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21337 | 0 | 0
111 | Garage Labor | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 35 | 0 | 1225 | 0 | 1225 | 21344 | 0 | 0
111 | Garage Labor | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 9 | 0 | 405 | 0 | 405 | 21368 | 0 | 0
111 | Garage Labor | PR | 251 | 10/10/18 | 10/12/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21465 | 0 | 0
111 | Garage Labor | PR | 255 | 10/10/18 | 10/12/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21412 | 0 | 0
111 | Garage Labor | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 30 | 0 | 1050 | 0 | 1050 | 21419 | 0 | 0
111 | Garage Labor | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21443 | 0 | 0
111 | Garage Labor | PR | 450 | 10/17/18 | 10/19/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21540 | 0 | 0
111 | Garage Labor | PR | 453 | 10/17/18 | 10/19/18 | EI74 | Eisenhauer, Tommy J | 27.5 | 0 | 632.5 | 0 | 632.5 | 21486 | 0 | 0
111 | Garage Labor | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21517 | 0 | 0
111 | Garage Labor | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 0 | 2 | 0 | 69 | 69 | 21560 | 0 | 0
111 | Garage Labor | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21560 | 0 | 0
111 | Garage Labor | PR | 727 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 6 | 0 | 315 | 315 | 21567 | 0 | 0
111 | Garage Labor | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21613 | 0 | 0
111 | Garage Labor | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 0 | 5 | 0 | 120 | 120 | 21613 | 0 | 0
111 | Garage Labor | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 4 | 0 | 186 | 186 | 21600 | 0 | 0
111 | Garage Labor | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 24 | 0 | 744 | 0 | 744 | 21600 | 0 | 0
111 | Garage Labor | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 12 | 0 | 420 | 0 | 420 | 21614 | 0 | 0
111 | Garage Labor | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 0 | 8 | 0 | 192 | 192 | 21685 | 0 | 0
111 | Garage Labor | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21685 | 0 | 0
111 | Garage Labor | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 5 | 0 | 175 | 0 | 175 | 21640 | 0 | 0
111 | Garage Labor | PR | 63 | 10/31/18 | 11/02/18 | SE64 | Sepulveda Gonzalez, Alfredo | 25 | 0 | 775 | 0 | 775 | 21672 | 0 | 0
111 | Garage Labor | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 4 | 0 | 96 | 96 | 21758 | 0 | 0
111 | Garage Labor | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 24 | 0 | 384 | 0 | 384 | 21758 | 0 | 0
111 | Garage Labor | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 5 | 0 | 175 | 0 | 175 | 21712 | 0 | 0
111 | Garage Labor | PR | 243 | 11/07/18 | 11/09/18 | SE64 | Sepulveda Gonzalez, Alfredo | 28 | 0 | 868 | 0 | 868 | 21746 | 0 | 0
111 | Garage Labor | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 0 | 7 | 0 | 168 | 168 | 21831 | 0 | 0
111 | Garage Labor | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21831 | 0 | 0
111 | Garage Labor | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 5 | 0 | 175 | 0 | 175 | 21785 | 0 | 0
111 | Garage Labor | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 0 | 5 | 0 | 202.5 | 202.5 | 21813 | 0 | 0
111 | Garage Labor | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 40 | 0 | 1080 | 0 | 1080 | 21813 | 0 | 0
111 | Garage Labor | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 5.5 | 0 | 255.75 | 255.75 | 21819 | 0 | 0
111 | Garage Labor | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1240 | 0 | 1240 | 21819 | 0 | 0
111 | Garage Labor | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 20 | 0 | 320 | 0 | 320 | 21908 | 0 | 0
111 | Garage Labor | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 4 | 0 | 140 | 0 | 140 | 21863 | 0 | 0
111 | Garage Labor | PR | 669 | 11/21/18 | 11/21/18 | RI84 | Rivera, Eli P | 38 | 0 | 1026 | 0 | 1026 | 21890 | 0 | 0
111 | Garage Labor | PR | 675 | 11/21/18 | 11/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 38 | 0 | 1178 | 0 | 1178 | 21896 | 0 | 0
111 | Garage Labor | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 4.5 | 0 | 126 | 0 | 126 | 21964 | 0 | 0
111 | Garage Labor | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 2 | 0 | 81 | 81 | 22007 | 0 | 0
111 | Garage Labor | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 4 | 0 | 108 | 0 | 108 | 22007 | 0 | 0
111 | Garage Labor | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 2 | 0 | 74 | 0 | 74 | 22010 | 0 | 0
111 | Garage Labor | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 9 | 0 | 288 | 0 | 288 | 22042 | 0 | 0
111 | Garage Labor | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 1 | 0 | 55.5 | 55.5 | 22151 | 0 | 0
111 | Garage Labor | PR | 39 | 01/02/19 | 01/04/19 | LO87 | Lovo, German G | 28 | 0 | 700 | 0 | 700 | 22380 | 0 | 0
111 | Garage Labor | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 8 | 0 | 248 | 0 | 248 | 24293 | 0 | 0
111 | Garage Labor | PR | 296 | 07/10/19 | 07/12/19 | DR04 | Draves, Steven W | 8 | 0 | 216 | 0 | 216 | 24348 | 0 | 0
111 | Garage Labor | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 8 | 0 | 224 | 0 | 224 | 24349 | 0 | 0
111 | Garage Labor | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24744 | 0 | 0
111 | Garage Labor | PR | 764 | 01/22/20 | 01/24/20 | GE71 | Gerard, Mitchell J | 40 | 0 | 1400 | 0 | 1400 | 926404 | 0 | 0
112 | Canout Labor | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 720 | 0 | 720 | 20644 | 0 | 0
112 | Canout Labor | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 320 | 0 | 320 | 20677 | 0 | 0
112 | Canout Labor | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 720 | 0 | 720 | 20716 | 0 | 0
112 | Canout Labor | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 8 | 0 | 216 | 0 | 216 | 20721 | 0 | 0
112 | Canout Labor | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 640 | 0 | 640 | 20750 | 0 | 0
112 | Canout Labor | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 32 | 0 | 1440 | 0 | 1440 | 20788 | 0 | 0
112 | Canout Labor | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 320 | 0 | 320 | 20822 | 0 | 0
112 | Canout Labor | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 720 | 0 | 720 | 20859 | 0 | 0
112 | Canout Labor | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 3 | 0 | 135 | 0 | 135 | 21222 | 0 | 0
120 | Roughin Labor | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 2.5 | 0 | 100 | 0 | 100 | 17504 | 0 | 0
120 | Roughin Labor | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 16 | 0 | 384 | 0 | 384 | 20706 | 0 | 0
120 | Roughin Labor | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 10 | 0 | 230 | 0 | 230 | 21263 | 0 | 0
120 | Roughin Labor | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21294 | 0 | 0
120 | Roughin Labor | PR | 727 | 09/26/18 | 09/28/18 | SE71 | Serrano, Jeremiah G | 16 | 0 | 256 | 0 | 256 | 21305 | 0 | 0
120 | Roughin Labor | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 24 | 0 | 384 | 0 | 384 | 21390 | 0 | 0
120 | Roughin Labor | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 5 | 0 | 175 | 0 | 175 | 21344 | 0 | 0
120 | Roughin Labor | PR | 91 | 10/03/18 | 10/05/18 | SE71 | Serrano, Jeremiah G | 29 | 0 | 464 | 0 | 464 | 21379 | 0 | 0
120 | Roughin Labor | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 8 | 0 | 280 | 0 | 280 | 21419 | 0 | 0
120 | Roughin Labor | PR | 297 | 10/10/18 | 10/12/18 | SE71 | Serrano, Jeremiah G | 37.5 | 0 | 600 | 0 | 600 | 21454 | 0 | 0
120 | Roughin Labor | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 90 | 0 | 90 | 21517 | 0 | 0
120 | Roughin Labor | PR | 495 | 10/17/18 | 10/19/18 | SE71 | Serrano, Jeremiah G | 23 | 0 | 368 | 0 | 368 | 21528 | 0 | 0
120 | Roughin Labor | PR | 500 | 10/17/18 | 10/19/18 | TH59 | Thompson, Harley J | 24 | 0 | 384 | 0 | 384 | 21533 | 0 | 0
120 | Roughin Labor | PR | 749 | 10/24/18 | 10/26/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 90 | 0 | 90 | 21589 | 0 | 0
120 | Roughin Labor | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 0 | 6 | 0 | 144 | 144 | 21606 | 0 | 0
120 | Roughin Labor | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 40 | 0 | 640 | 0 | 640 | 21606 | 0 | 0
120 | Roughin Labor | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 28 | 0 | 980 | 0 | 980 | 21614 | 0 | 0
120 | Roughin Labor | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 0 | 6 | 0 | 207 | 207 | 21632 | 0 | 0
120 | Roughin Labor | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21632 | 0 | 0
120 | Roughin Labor | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 8 | 0 | 420 | 420 | 21640 | 0 | 0
120 | Roughin Labor | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 35 | 0 | 1225 | 0 | 1225 | 21640 | 0 | 0
120 | Roughin Labor | PR | 69 | 10/31/18 | 11/02/18 | TH59 | Thompson, Harley J | 28 | 0 | 448 | 0 | 448 | 21678 | 0 | 0
120 | Roughin Labor | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 4 | 0 | 96 | 96 | 21758 | 0 | 0
120 | Roughin Labor | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 16 | 0 | 256 | 0 | 256 | 21758 | 0 | 0
120 | Roughin Labor | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 276 | 276 | 21704 | 0 | 0
120 | Roughin Labor | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21704 | 0 | 0
120 | Roughin Labor | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 8 | 0 | 420 | 420 | 21712 | 0 | 0
120 | Roughin Labor | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 34 | 0 | 1190 | 0 | 1190 | 21712 | 0 | 0
120 | Roughin Labor | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 8 | 0 | 324 | 324 | 21740 | 0 | 0
120 | Roughin Labor | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 24 | 0 | 648 | 0 | 648 | 21740 | 0 | 0
120 | Roughin Labor | PR | 239 | 11/07/18 | 11/09/18 | RO06 | Roberts, Lake A | 30 | 0 | 480 | 0 | 480 | 21742 | 0 | 0
120 | Roughin Labor | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 276 | 276 | 21777 | 0 | 0
120 | Roughin Labor | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21777 | 0 | 0
120 | Roughin Labor | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 8 | 0 | 420 | 420 | 21785 | 0 | 0
120 | Roughin Labor | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 35 | 0 | 1225 | 0 | 1225 | 21785 | 0 | 0
120 | Roughin Labor | PR | 480 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 10 | 0 | 450 | 0 | 450 | 21808 | 0 | 0
120 | Roughin Labor | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 4 | 0 | 96 | 96 | 21815 | 0 | 0
120 | Roughin Labor | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 24 | 0 | 384 | 0 | 384 | 21815 | 0 | 0
120 | Roughin Labor | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | -276 | -276 | 21777 | 0 | 0
120 | Roughin Labor | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | -920 | 0 | -920 | 21777 | 0 | 0
120 | Roughin Labor | PR | 506 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 10 | 0 | -450 | 0 | -450 | 21808 | 0 | 0
120 | Roughin Labor | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 276 | 276 | 21832 | 0 | 0
120 | Roughin Labor | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 920 | 0 | 920 | 21832 | 0 | 0
120 | Roughin Labor | PR | 509 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 10 | 0 | 450 | 0 | 450 | 21834 | 0 | 0
120 | Roughin Labor | PR | 625 | 11/21/18 | 11/21/18 | CH20 | Chevez, Herson G | 38 | 0 | 684 | 0 | 684 | 21847 | 0 | 0
120 | Roughin Labor | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 18 | 0 | 288 | 0 | 288 | 21908 | 0 | 0
120 | Roughin Labor | PR | 634 | 11/21/18 | 11/21/18 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 736 | 0 | 736 | 21855 | 0 | 0
120 | Roughin Labor | PR | 639 | 11/21/18 | 11/21/18 | GA46 | Galdamez, Dagoberto A | 38 | 0 | 950 | 0 | 950 | 21860 | 0 | 0
120 | Roughin Labor | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 34 | 0 | 1190 | 0 | 1190 | 21863 | 0 | 0
120 | Roughin Labor | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21885 | 0 | 0
120 | Roughin Labor | PR | 671 | 11/21/18 | 11/21/18 | RO06 | Roberts, Lake A | 38 | 0 | 608 | 0 | 608 | 21892 | 0 | 0
120 | Roughin Labor | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21895 | 0 | 0
120 | Roughin Labor | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | -180 | 0 | -180 | 21885 | 0 | 0
120 | Roughin Labor | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21910 | 0 | 0
120 | Roughin Labor | PR | 837 | 11/28/18 | 11/30/18 | CH20 | Chevez, Herson G | 34.5 | 0 | 690 | 0 | 690 | 21920 | 0 | 0
120 | Roughin Labor | PR | 845 | 11/28/18 | 11/30/18 | DE45 | de la Torre, Kevin A | 34.5 | 0 | 586.5 | 0 | 586.5 | 21982 | 0 | 0
120 | Roughin Labor | PR | 847 | 11/28/18 | 11/30/18 | EI74 | Eisenhauer, Tommy J | 34.5 | 0 | 862.5 | 0 | 862.5 | 21929 | 0 | 0
120 | Roughin Labor | PR | 852 | 11/28/18 | 11/30/18 | GA46 | Galdamez, Dagoberto A | 34.5 | 0 | 931.5 | 0 | 931.5 | 21934 | 0 | 0
120 | Roughin Labor | PR | 855 | 11/28/18 | 11/30/18 | GE71 | Gerard, Mitchell J | 34.5 | 0 | 1276.5 | 0 | 1276.5 | 21937 | 0 | 0
120 | Roughin Labor | PR | 877 | 11/28/18 | 11/30/18 | QU35 | Quintanilla, Esteban R | 16 | 0 | 752 | 0 | 752 | 21959 | 0 | 0
120 | Roughin Labor | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 30 | 0 | 840 | 0 | 840 | 21964 | 0 | 0
120 | Roughin Labor | PR | 884 | 11/28/18 | 11/30/18 | RO06 | Roberts, Lake A | 34.5 | 0 | 586.5 | 0 | 586.5 | 21966 | 0 | 0
120 | Roughin Labor | PR | 888 | 11/28/18 | 11/30/18 | SE64 | Sepulveda Gonzalez, Alfredo | 23.5 | 0 | 752 | 0 | 752 | 21970 | 0 | 0
120 | Roughin Labor | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 0 | 8 | 0 | 240 | 240 | 21994 | 0 | 0
120 | Roughin Labor | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 40 | 0 | 800 | 0 | 800 | 21994 | 0 | 0
120 | Roughin Labor | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 0 | 8 | 0 | 204 | 204 | 22054 | 0 | 0
120 | Roughin Labor | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 680 | 0 | 680 | 22054 | 0 | 0
120 | Roughin Labor | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 300 | 300 | 22002 | 0 | 0
120 | Roughin Labor | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 22002 | 0 | 0
120 | Roughin Labor | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 2 | 0 | 81 | 81 | 22007 | 0 | 0
120 | Roughin Labor | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 648 | 0 | 648 | 22007 | 0 | 0
120 | Roughin Labor | PR | 66 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1440 | 0 | 1440 | 22008 | 0 | 0
120 | Roughin Labor | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 8 | 0 | 444 | 444 | 22010 | 0 | 0
120 | Roughin Labor | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 38 | 0 | 1406 | 0 | 1406 | 22010 | 0 | 0
120 | Roughin Labor | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 4 | 0 | 150 | 150 | 22022 | 0 | 0
120 | Roughin Labor | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 16 | 0 | 400 | 0 | 400 | 22022 | 0 | 0
120 | Roughin Labor | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 0 | 8 | 0 | 240 | 240 | 22030 | 0 | 0
120 | Roughin Labor | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22030 | 0 | 0
120 | Roughin Labor | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 13 | 0 | 611 | 0 | 611 | 22031 | 0 | 0
120 | Roughin Labor | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 0 | 3 | 0 | 211.5 | 211.5 | 22031 | 0 | 0
120 | Roughin Labor | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 2 | 0 | 84 | 84 | 22036 | 0 | 0
120 | Roughin Labor | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 8 | 0 | 224 | 0 | 224 | 22036 | 0 | 0
120 | Roughin Labor | PR | 96 | 12/05/18 | 12/07/18 | RO06 | Roberts, Lake A | 38 | 0 | 646 | 0 | 646 | 22038 | 0 | 0
120 | Roughin Labor | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 20 | 0 | 640 | 0 | 640 | 22042 | 0 | 0
120 | Roughin Labor | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 40 | 0 | -1440 | 0 | -1440 | 22060 | 0 | 0
120 | Roughin Labor | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 0 | 8 | 0 | 240 | 240 | 22134 | 0 | 0
120 | Roughin Labor | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 40 | 0 | 800 | 0 | 800 | 22134 | 0 | 0
120 | Roughin Labor | PR | 282 | 12/12/18 | 12/14/18 | DE45 | de la Torre, Kevin A | 38 | 0 | 646 | 0 | 646 | 22196 | 0 | 0
120 | Roughin Labor | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 22143 | 0 | 0
120 | Roughin Labor | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 300 | 300 | 22143 | 0 | 0
120 | Roughin Labor | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 40 | 0 | 1480 | 0 | 1480 | 22151 | 0 | 0
120 | Roughin Labor | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 7 | 0 | 388.5 | 388.5 | 22151 | 0 | 0
120 | Roughin Labor | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 2 | 0 | 75 | 75 | 22163 | 0 | 0
120 | Roughin Labor | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 8 | 0 | 200 | 0 | 200 | 22163 | 0 | 0
120 | Roughin Labor | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 0 | 8 | 0 | 240 | 240 | 22172 | 0 | 0
120 | Roughin Labor | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22172 | 0 | 0
120 | Roughin Labor | PR | 314 | 12/12/18 | 12/14/18 | QU35 | Quintanilla, Esteban R | 3 | 0 | 141 | 0 | 141 | 22173 | 0 | 0
120 | Roughin Labor | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 4 | 0 | 168 | 168 | 22178 | 0 | 0
120 | Roughin Labor | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 11 | 0 | 308 | 0 | 308 | 22178 | 0 | 0
120 | Roughin Labor | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 0 | 8 | 0 | 204 | 204 | 22180 | 0 | 0
120 | Roughin Labor | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 40 | 0 | 680 | 0 | 680 | 22180 | 0 | 0
120 | Roughin Labor | PR | 325 | 12/12/18 | 12/14/18 | SE64 | Sepulveda Gonzalez, Alfredo | 36 | 0 | 1152 | 0 | 1152 | 22184 | 0 | 0
120 | Roughin Labor | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 10 | 0 | 480 | 0 | 480 | 22202 | 0 | 0
120 | Roughin Labor | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 0 | 4 | 0 | 120 | 120 | 22206 | 0 | 0
120 | Roughin Labor | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 44 | 0 | 880 | 0 | 880 | 22206 | 0 | 0
120 | Roughin Labor | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 0 | 4 | 0 | 102 | 102 | 22267 | 0 | 0
120 | Roughin Labor | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 44 | 0 | 748 | 0 | 748 | 22267 | 0 | 0
120 | Roughin Labor | PR | 525 | 12/19/18 | 12/21/18 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 22215 | 0 | 0
120 | Roughin Labor | PR | 533 | 12/19/18 | 12/21/18 | GE71 | Gerard, Mitchell J | 36.5 | 0 | 1350.5 | 0 | 1350.5 | 22223 | 0 | 0
120 | Roughin Labor | PR | 545 | 12/19/18 | 12/21/18 | LO87 | Lovo, German G | 17.5 | 0 | 437.5 | 0 | 437.5 | 22235 | 0 | 0
120 | Roughin Labor | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 4 | 0 | 120 | 120 | 22243 | 0 | 0
120 | Roughin Labor | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 44 | 0 | 880 | 0 | 880 | 22243 | 0 | 0
120 | Roughin Labor | PR | 554 | 12/19/18 | 12/21/18 | QU35 | Quintanilla, Esteban R | 1 | 0 | 47 | 0 | 47 | 22244 | 0 | 0
120 | Roughin Labor | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 2 | 0 | 84 | 84 | 22249 | 0 | 0
120 | Roughin Labor | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 34 | 0 | 952 | 0 | 952 | 22249 | 0 | 0
120 | Roughin Labor | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 0 | 4 | 0 | 102 | 102 | 22251 | 0 | 0
120 | Roughin Labor | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 44 | 0 | 748 | 0 | 748 | 22251 | 0 | 0
120 | Roughin Labor | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 96 | 96 | 22255 | 0 | 0
120 | Roughin Labor | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 44 | 0 | 1408 | 0 | 1408 | 22255 | 0 | 0
120 | Roughin Labor | PR | 684 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 14 | 0 | 350 | 0 | 350 | 22268 | 0 | 0
120 | Roughin Labor | PR | 706 | 12/26/18 | 12/28/18 | CH20 | Chevez, Herson G | 26 | 0 | 520 | 0 | 520 | 22279 | 0 | 0
120 | Roughin Labor | PR | 715 | 12/26/18 | 12/28/18 | EI74 | Eisenhauer, Tommy J | 26 | 0 | 650 | 0 | 650 | 22288 | 0 | 0
120 | Roughin Labor | PR | 723 | 12/26/18 | 12/28/18 | GE71 | Gerard, Mitchell J | 16 | 0 | 592 | 0 | 592 | 22296 | 0 | 0
120 | Roughin Labor | PR | 726 | 12/26/18 | 12/28/18 | DE45 | de la Torre, Kevin A | 18 | 0 | 306 | 0 | 306 | 22341 | 0 | 0
120 | Roughin Labor | PR | 736 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 8 | 0 | 200 | 0 | 200 | 22309 | 0 | 0
120 | Roughin Labor | PR | 744 | 12/26/18 | 12/28/18 | PO73 | Portillo Soriano, Walter A | 18 | 0 | 360 | 0 | 360 | 22317 | 0 | 0
120 | Roughin Labor | PR | 750 | 12/26/18 | 12/28/18 | RI84 | Rivera, Eli P | 8 | 0 | 224 | 0 | 224 | 22323 | 0 | 0
120 | Roughin Labor | PR | 752 | 12/26/18 | 12/28/18 | RO06 | Roberts, Lake A | 26 | 0 | 442 | 0 | 442 | 22325 | 0 | 0
120 | Roughin Labor | PR | 756 | 12/26/18 | 12/28/18 | SE64 | Sepulveda Gonzalez, Alfredo | 18 | 0 | 576 | 0 | 576 | 22329 | 0 | 0
120 | Roughin Labor | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 10 | 0 | -480 | 0 | -480 | 22346 | 0 | 0
120 | Roughin Labor | PR | 11 | 01/02/19 | 01/04/19 | CH20 | Chevez, Herson G | 28 | 0 | 560 | 0 | 560 | 22351 | 0 | 0
120 | Roughin Labor | PR | 20 | 01/02/19 | 01/04/19 | EI74 | Eisenhauer, Tommy J | 18 | 0 | 450 | 0 | 450 | 22361 | 0 | 0
120 | Roughin Labor | PR | 28 | 01/02/19 | 01/04/19 | GE71 | Gerard, Mitchell J | 10 | 0 | 370 | 0 | 370 | 22369 | 0 | 0
120 | Roughin Labor | PR | 47 | 01/02/19 | 01/04/19 | PO73 | Portillo Soriano, Walter A | 10 | 0 | 200 | 0 | 200 | 22388 | 0 | 0
120 | Roughin Labor | PR | 53 | 01/02/19 | 01/04/19 | RI84 | Rivera, Eli P | 26.5 | 0 | 742 | 0 | 742 | 22394 | 0 | 0
120 | Roughin Labor | PR | 55 | 01/02/19 | 01/04/19 | RO06 | Roberts, Lake A | 28 | 0 | 476 | 0 | 476 | 22396 | 0 | 0
120 | Roughin Labor | PR | 59 | 01/02/19 | 01/04/19 | SE64 | Sepulveda Gonzalez, Alfredo | 18 | 0 | 576 | 0 | 576 | 22400 | 0 | 0
120 | Roughin Labor | PR | 219 | 01/09/19 | 01/11/19 | CH20 | Chevez, Herson G | 40 | 0 | 800 | 0 | 800 | 22421 | 0 | 0
120 | Roughin Labor | PR | 228 | 01/09/19 | 01/11/19 | EI74 | Eisenhauer, Tommy J | 16 | 0 | 400 | 0 | 400 | 22430 | 0 | 0
120 | Roughin Labor | PR | 233 | 01/09/19 | 01/11/19 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 648 | 0 | 648 | 22435 | 0 | 0
120 | Roughin Labor | PR | 236 | 01/09/19 | 01/11/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1480 | 0 | 1480 | 22438 | 0 | 0
120 | Roughin Labor | PR | 243 | 01/09/19 | 01/11/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 22445 | 0 | 0
120 | Roughin Labor | PR | 249 | 01/09/19 | 01/11/19 | LO87 | Lovo, German G | 32 | 0 | 800 | 0 | 800 | 22451 | 0 | 0
120 | Roughin Labor | PR | 257 | 01/09/19 | 01/11/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22459 | 0 | 0
120 | Roughin Labor | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 4 | 0 | 188 | 0 | 188 | 22460 | 0 | 0
120 | Roughin Labor | PR | 263 | 01/09/19 | 01/11/19 | RI84 | Rivera, Eli P | 40 | 0 | 1120 | 0 | 1120 | 22465 | 0 | 0
120 | Roughin Labor | PR | 265 | 01/09/19 | 01/11/19 | RO06 | Roberts, Lake A | 40 | 0 | 680 | 0 | 680 | 22467 | 0 | 0
120 | Roughin Labor | PR | 269 | 01/09/19 | 01/11/19 | SE64 | Sepulveda Gonzalez, Alfredo | 30.5 | 0 | 976 | 0 | 976 | 22471 | 0 | 0
120 | Roughin Labor | PR | 474 | 01/16/19 | 01/18/19 | CH20 | Chevez, Herson G | 40 | 0 | 800 | 0 | 800 | 22495 | 0 | 0
120 | Roughin Labor | PR | 483 | 01/16/19 | 01/18/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 800 | 0 | 800 | 22504 | 0 | 0
120 | Roughin Labor | PR | 488 | 01/16/19 | 01/18/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 22509 | 0 | 0
120 | Roughin Labor | PR | 491 | 01/16/19 | 01/18/19 | GE71 | Gerard, Mitchell J | 37.5 | 0 | 1387.5 | 0 | 1387.5 | 22512 | 0 | 0
120 | Roughin Labor | PR | 498 | 01/16/19 | 01/18/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 22519 | 0 | 0
120 | Roughin Labor | PR | 504 | 01/16/19 | 01/18/19 | LO87 | Lovo, German G | 40 | 0 | 1000 | 0 | 1000 | 22525 | 0 | 0
120 | Roughin Labor | PR | 512 | 01/16/19 | 01/18/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22533 | 0 | 0
120 | Roughin Labor | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 3 | 0 | -211.5 | -211.5 | 22534 | 0 | 0
120 | Roughin Labor | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 8 | 0 | 376 | 0 | 376 | 22534 | 0 | 0
120 | Roughin Labor | PR | 518 | 01/16/19 | 01/18/19 | RI84 | Rivera, Eli P | 32 | 0 | 896 | 0 | 896 | 22539 | 0 | 0
120 | Roughin Labor | PR | 520 | 01/16/19 | 01/18/19 | RO06 | Roberts, Lake A | 40 | 0 | 680 | 0 | 680 | 22541 | 0 | 0
120 | Roughin Labor | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 256 | 0 | 256 | 22545 | 0 | 0
120 | Roughin Labor | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 36 | 0 | 720 | 0 | 720 | 22568 | 0 | 0
120 | Roughin Labor | PR | 732 | 01/23/19 | 01/25/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 800 | 0 | 800 | 22577 | 0 | 0
120 | Roughin Labor | PR | 737 | 01/23/19 | 01/25/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 22582 | 0 | 0
120 | Roughin Labor | PR | 740 | 01/23/19 | 01/25/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1480 | 0 | 1480 | 22585 | 0 | 0
120 | Roughin Labor | PR | 747 | 01/23/19 | 01/25/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 22592 | 0 | 0
120 | Roughin Labor | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 1 | 0 | 49 | 0 | 49 | 22593 | 0 | 0
120 | Roughin Labor | PR | 753 | 01/23/19 | 01/25/19 | LO87 | Lovo, German G | 37.5 | 0 | 937.5 | 0 | 937.5 | 22598 | 0 | 0
120 | Roughin Labor | PR | 761 | 01/23/19 | 01/25/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22606 | 0 | 0
120 | Roughin Labor | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 32 | 0 | 896 | 0 | 896 | 22612 | 0 | 0
120 | Roughin Labor | PR | 769 | 01/23/19 | 01/25/19 | RO06 | Roberts, Lake A | 16 | 0 | 272 | 0 | 272 | 22614 | 0 | 0
120 | Roughin Labor | PR | 11 | 01/30/19 | 02/01/19 | CH20 | Chevez, Herson G | 40 | 0 | 800 | 0 | 800 | 22640 | 0 | 0
120 | Roughin Labor | PR | 20 | 01/30/19 | 02/01/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 22649 | 0 | 0
120 | Roughin Labor | PR | 25 | 01/30/19 | 02/01/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 22654 | 0 | 0
120 | Roughin Labor | PR | 28 | 01/30/19 | 02/01/19 | GE71 | Gerard, Mitchell J | 38.5 | 0 | 1424.5 | 0 | 1424.5 | 22657 | 0 | 0
120 | Roughin Labor | PR | 35 | 01/30/19 | 02/01/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 22664 | 0 | 0
120 | Roughin Labor | PR | 41 | 01/30/19 | 02/01/19 | LO87 | Lovo, German G | 40 | 0 | 1000 | 0 | 1000 | 22670 | 0 | 0
120 | Roughin Labor | PR | 48 | 01/30/19 | 02/01/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 22677 | 0 | 0
120 | Roughin Labor | PR | 53 | 01/30/19 | 02/01/19 | RI84 | Rivera, Eli P | 32 | 0 | 896 | 0 | 896 | 22682 | 0 | 0
120 | Roughin Labor | PR | 166 | 02/06/19 | 02/08/19 | CH20 | Chevez, Herson G | 24 | 0 | 480 | 0 | 480 | 22708 | 0 | 0
120 | Roughin Labor | PR | 175 | 02/06/19 | 02/08/19 | EI74 | Eisenhauer, Tommy J | 24 | 0 | 600 | 0 | 600 | 22717 | 0 | 0
120 | Roughin Labor | PR | 183 | 02/06/19 | 02/08/19 | GE71 | Gerard, Mitchell J | 24 | 0 | 888 | 0 | 888 | 22725 | 0 | 0
120 | Roughin Labor | PR | 190 | 02/06/19 | 02/08/19 | HU05 | Hubbard, Justin A | 24 | 0 | 576 | 0 | 576 | 22732 | 0 | 0
120 | Roughin Labor | PR | 196 | 02/06/19 | 02/08/19 | LO87 | Lovo, German G | 24 | 0 | 600 | 0 | 600 | 22738 | 0 | 0
120 | Roughin Labor | PR | 203 | 02/06/19 | 02/08/19 | PO73 | Portillo Soriano, Walter A | 24 | 0 | 480 | 0 | 480 | 22745 | 0 | 0
120 | Roughin Labor | PR | 208 | 02/06/19 | 02/08/19 | RI84 | Rivera, Eli P | 24 | 0 | 672 | 0 | 672 | 22750 | 0 | 0
120 | Roughin Labor | PR | 210 | 02/06/19 | 02/08/19 | RO06 | Roberts, Lake A | 8 | 0 | 136 | 0 | 136 | 22752 | 0 | 0
120 | Roughin Labor | PR | 328 | 02/13/19 | 02/15/19 | CH20 | Chevez, Herson G | 14 | 0 | 280 | 0 | 280 | 22777 | 0 | 0
120 | Roughin Labor | PR | 337 | 02/13/19 | 02/15/19 | EI74 | Eisenhauer, Tommy J | 24 | 0 | 600 | 0 | 600 | 22786 | 0 | 0
120 | Roughin Labor | PR | 345 | 02/13/19 | 02/15/19 | GE71 | Gerard, Mitchell J | 24 | 0 | 888 | 0 | 888 | 22795 | 0 | 0
120 | Roughin Labor | PR | 352 | 02/13/19 | 02/15/19 | HU05 | Hubbard, Justin A | 24 | 0 | 576 | 0 | 576 | 22803 | 0 | 0
120 | Roughin Labor | PR | 358 | 02/13/19 | 02/15/19 | LO87 | Lovo, German G | 24 | 0 | 600 | 0 | 600 | 22809 | 0 | 0
120 | Roughin Labor | PR | 365 | 02/13/19 | 02/15/19 | PO73 | Portillo Soriano, Walter A | 24 | 0 | 480 | 0 | 480 | 22816 | 0 | 0
120 | Roughin Labor | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 14 | 0 | 392 | 0 | 392 | 22821 | 0 | 0
120 | Roughin Labor | PR | 372 | 02/13/19 | 02/15/19 | RO06 | Roberts, Lake A | 19.5 | 0 | 331.5 | 0 | 331.5 | 22823 | 0 | 0
120 | Roughin Labor | PR | 595 | 02/20/19 | 02/22/19 | EI74 | Eisenhauer, Tommy J | 48 | 0 | 1200 | 0 | 1200 | 22857 | 0 | 0
120 | Roughin Labor | PR | 603 | 02/20/19 | 02/22/19 | GE71 | Gerard, Mitchell J | 46 | 0 | 1702 | 0 | 1702 | 22865 | 0 | 0
120 | Roughin Labor | PR | 610 | 02/20/19 | 02/22/19 | HU05 | Hubbard, Justin A | 56 | 0 | 1344 | 0 | 1344 | 22872 | 0 | 0
120 | Roughin Labor | PR | 616 | 02/20/19 | 02/22/19 | LO87 | Lovo, German G | 56 | 0 | 1400 | 0 | 1400 | 22878 | 0 | 0
120 | Roughin Labor | PR | 622 | 02/20/19 | 02/22/19 | MU70 | Murphy, Darray E | 29.5 | 0 | 531 | 0 | 531 | 22884 | 0 | 0
120 | Roughin Labor | PR | 624 | 02/20/19 | 02/22/19 | PO73 | Portillo Soriano, Walter A | 56 | 0 | 1120 | 0 | 1120 | 22886 | 0 | 0
120 | Roughin Labor | PR | 629 | 02/20/19 | 02/22/19 | RI84 | Rivera, Eli P | 55 | 0 | 1540 | 0 | 1540 | 22891 | 0 | 0
120 | Roughin Labor | PR | 631 | 02/20/19 | 02/22/19 | RO06 | Roberts, Lake A | 35.5 | 0 | 603.5 | 0 | 603.5 | 22893 | 0 | 0
120 | Roughin Labor | PR | 20 | 02/27/19 | 03/01/19 | DR04 | Draves, Steven W | 16 | 0 | 384 | 0 | 384 | 22927 | 0 | 0
120 | Roughin Labor | PR | 21 | 02/27/19 | 03/01/19 | EI74 | Eisenhauer, Tommy J | 50 | 0 | 1250 | 0 | 1250 | 22928 | 0 | 0
120 | Roughin Labor | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 22933 | 0 | 0
120 | Roughin Labor | PR | 30 | 02/27/19 | 03/01/19 | GE71 | Gerard, Mitchell J | 50 | 0 | 1850 | 0 | 1850 | 22937 | 0 | 0
120 | Roughin Labor | PR | 37 | 02/27/19 | 03/01/19 | HU05 | Hubbard, Justin A | 50 | 0 | 1200 | 0 | 1200 | 22944 | 0 | 0
120 | Roughin Labor | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22949 | 0 | 0
120 | Roughin Labor | PR | 43 | 02/27/19 | 03/01/19 | LO87 | Lovo, German G | 31.5 | 0 | 787.5 | 0 | 787.5 | 22950 | 0 | 0
120 | Roughin Labor | PR | 49 | 02/27/19 | 03/01/19 | MU70 | Murphy, Darray E | 33.5 | 0 | 603 | 0 | 603 | 22956 | 0 | 0
120 | Roughin Labor | PR | 51 | 02/27/19 | 03/01/19 | PO73 | Portillo Soriano, Walter A | 50 | 0 | 1000 | 0 | 1000 | 22958 | 0 | 0
120 | Roughin Labor | PR | 56 | 02/27/19 | 03/01/19 | RI84 | Rivera, Eli P | 50 | 0 | 1400 | 0 | 1400 | 22963 | 0 | 0
120 | Roughin Labor | PR | 58 | 02/27/19 | 03/01/19 | RO06 | Roberts, Lake A | 24 | 0 | 408 | 0 | 408 | 22965 | 0 | 0
120 | Roughin Labor | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 0 | 8 | 0 | 288 | 288 | 23001 | 0 | 0
120 | Roughin Labor | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23001 | 0 | 0
120 | Roughin Labor | PR | 263 | 03/06/19 | 03/08/19 | EI74 | Eisenhauer, Tommy J | 48 | 0 | 1200 | 0 | 1200 | 23002 | 0 | 0
120 | Roughin Labor | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 16 | 0 | 432 | 0 | 432 | 23006 | 0 | 0
120 | Roughin Labor | PR | 271 | 03/06/19 | 03/08/19 | GE71 | Gerard, Mitchell J | 48 | 0 | 1776 | 0 | 1776 | 23010 | 0 | 0
120 | Roughin Labor | PR | 277 | 03/06/19 | 03/08/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 23016 | 0 | 0
120 | Roughin Labor | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 23021 | 0 | 0
120 | Roughin Labor | PR | 291 | 03/06/19 | 03/08/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23030 | 0 | 0
120 | Roughin Labor | PR | 295 | 03/06/19 | 03/08/19 | RI84 | Rivera, Eli P | 40 | 0 | 1120 | 0 | 1120 | 23034 | 0 | 0
120 | Roughin Labor | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23071 | 0 | 0
120 | Roughin Labor | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23072 | 0 | 0
120 | Roughin Labor | PR | 518 | 03/13/19 | 03/15/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1480 | 0 | 1480 | 23080 | 0 | 0
120 | Roughin Labor | PR | 524 | 03/13/19 | 03/15/19 | HU05 | Hubbard, Justin A | 32 | 0 | 768 | 0 | 768 | 23086 | 0 | 0
120 | Roughin Labor | PR | 538 | 03/13/19 | 03/15/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23100 | 0 | 0
120 | Roughin Labor | PR | 542 | 03/13/19 | 03/15/19 | RI84 | Rivera, Eli P | 32 | 0 | 896 | 0 | 896 | 23104 | 0 | 0
120 | Roughin Labor | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23144 | 0 | 0
120 | Roughin Labor | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23145 | 0 | 0
120 | Roughin Labor | PR | 732 | 03/20/19 | 03/22/19 | GE71 | Gerard, Mitchell J | 39 | 0 | 1443 | 0 | 1443 | 23153 | 0 | 0
120 | Roughin Labor | PR | 738 | 03/20/19 | 03/22/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 23159 | 0 | 0
120 | Roughin Labor | PR | 751 | 03/20/19 | 03/22/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23172 | 0 | 0
120 | Roughin Labor | PR | 755 | 03/20/19 | 03/22/19 | RI84 | Rivera, Eli P | 40 | 0 | 1120 | 0 | 1120 | 23176 | 0 | 0
120 | Roughin Labor | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 0 | 8 | 0 | 288 | 288 | 23218 | 0 | 0
120 | Roughin Labor | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23218 | 0 | 0
120 | Roughin Labor | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 0 | 8 | 0 | 300 | 300 | 23219 | 0 | 0
120 | Roughin Labor | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23219 | 0 | 0
120 | Roughin Labor | PR | 944 | 03/27/19 | 03/29/19 | GE71 | Gerard, Mitchell J | 48 | 0 | 1776 | 0 | 1776 | 23228 | 0 | 0
120 | Roughin Labor | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 0 | 2 | 0 | 72 | 72 | 23234 | 0 | 0
120 | Roughin Labor | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 46 | 0 | 1104 | 0 | 1104 | 23234 | 0 | 0
120 | Roughin Labor | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 0 | 4 | 0 | 198 | 198 | 23243 | 0 | 0
120 | Roughin Labor | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 8 | 0 | 264 | 0 | 264 | 23243 | 0 | 0
120 | Roughin Labor | PR | 963 | 03/27/19 | 03/29/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23247 | 0 | 0
120 | Roughin Labor | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 0 | 1 | 0 | 42 | 42 | 23251 | 0 | 0
120 | Roughin Labor | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 47 | 0 | 1316 | 0 | 1316 | 23251 | 0 | 0
120 | Roughin Labor | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 0 | 7 | 0 | 252 | 252 | 23290 | 0 | 0
120 | Roughin Labor | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23290 | 0 | 0
120 | Roughin Labor | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0.5 | 0 | 18.75 | 18.75 | 23291 | 0 | 0
120 | Roughin Labor | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23291 | 0 | 0
120 | Roughin Labor | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 8 | 0 | 324 | 324 | 23296 | 0 | 0
120 | Roughin Labor | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 38 | 0 | 1026 | 0 | 1026 | 23296 | 0 | 0
120 | Roughin Labor | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 0 | 14 | 0 | 777 | 777 | 23300 | 0 | 0
120 | Roughin Labor | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1480 | 0 | 1480 | 23300 | 0 | 0
120 | Roughin Labor | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 0 | 6 | 0 | 216 | 216 | 23307 | 0 | 0
120 | Roughin Labor | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 23307 | 0 | 0
120 | Roughin Labor | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 4 | 0 | 198 | 198 | 23312 | 0 | 0
120 | Roughin Labor | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 23312 | 0 | 0
120 | Roughin Labor | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 0 | 8 | 0 | 240 | 240 | 23320 | 0 | 0
120 | Roughin Labor | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 46 | 0 | 920 | 0 | 920 | 23320 | 0 | 0
120 | Roughin Labor | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 0 | 12 | 0 | 504 | 504 | 23324 | 0 | 0
120 | Roughin Labor | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 40 | 0 | 1120 | 0 | 1120 | 23324 | 0 | 0
120 | Roughin Labor | PR | 340 | 04/10/19 | 04/12/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23364 | 0 | 0
120 | Roughin Labor | PR | 341 | 04/10/19 | 04/12/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23365 | 0 | 0
120 | Roughin Labor | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 648 | 0 | 648 | 23370 | 0 | 0
120 | Roughin Labor | PR | 349 | 04/10/19 | 04/12/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 23373 | 0 | 0
120 | Roughin Labor | PR | 356 | 04/10/19 | 04/12/19 | HU05 | Hubbard, Justin A | 40 | 0 | 960 | 0 | 960 | 23380 | 0 | 0
120 | Roughin Labor | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 23385 | 0 | 0
120 | Roughin Labor | PR | 370 | 04/10/19 | 04/12/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23394 | 0 | 0
120 | Roughin Labor | PR | 374 | 04/10/19 | 04/12/19 | RI84 | Rivera, Eli P | 40 | 0 | 1120 | 0 | 1120 | 23398 | 0 | 0
120 | Roughin Labor | PR | 537 | 04/17/19 | 04/19/19 | DR04 | Draves, Steven W | 40 | 0 | 960 | 0 | 960 | 23438 | 0 | 0
120 | Roughin Labor | PR | 538 | 04/17/19 | 04/19/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1000 | 0 | 1000 | 23439 | 0 | 0
120 | Roughin Labor | PR | 543 | 04/17/19 | 04/19/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 23444 | 0 | 0
120 | Roughin Labor | PR | 547 | 04/17/19 | 04/19/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 23448 | 0 | 0
120 | Roughin Labor | PR | 554 | 04/17/19 | 04/19/19 | HU05 | Hubbard, Justin A | 33.5 | 0 | 804 | 0 | 804 | 23455 | 0 | 0
120 | Roughin Labor | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 23460 | 0 | 0
120 | Roughin Labor | PR | 568 | 04/17/19 | 04/19/19 | PO73 | Portillo Soriano, Walter A | 40 | 0 | 800 | 0 | 800 | 23469 | 0 | 0
120 | Roughin Labor | PR | 572 | 04/17/19 | 04/19/19 | RI84 | Rivera, Eli P | 38 | 0 | 1064 | 0 | 1064 | 23473 | 0 | 0
120 | Roughin Labor | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 0 | 1 | 0 | 40.5 | 40.5 | 23514 | 0 | 0
120 | Roughin Labor | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 23514 | 0 | 0
120 | Roughin Labor | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 1 | 0 | 42 | 42 | 23515 | 0 | 0
120 | Roughin Labor | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 23515 | 0 | 0
120 | Roughin Labor | PR | 762 | 04/24/19 | 04/26/19 | GA46 | Galdamez, Dagoberto A | 16 | 0 | 480 | 0 | 480 | 23519 | 0 | 0
120 | Roughin Labor | PR | 766 | 04/24/19 | 04/26/19 | GE71 | Gerard, Mitchell J | 37.5 | 0 | 1500 | 0 | 1500 | 23523 | 0 | 0
120 | Roughin Labor | PR | 773 | 04/24/19 | 04/26/19 | HU05 | Hubbard, Justin A | 37.5 | 0 | 975 | 0 | 975 | 23530 | 0 | 0
120 | Roughin Labor | PR | 787 | 04/24/19 | 04/26/19 | PO73 | Portillo Soriano, Walter A | 16 | 0 | 352 | 0 | 352 | 23544 | 0 | 0
120 | Roughin Labor | PR | 791 | 04/24/19 | 04/26/19 | RI84 | Rivera, Eli P | 16 | 0 | 480 | 0 | 480 | 23548 | 0 | 0
120 | Roughin Labor | PR | 24 | 05/01/19 | 05/03/19 | DR04 | Draves, Steven W | 35.5 | 0 | 958.5 | 0 | 958.5 | 23586 | 0 | 0
120 | Roughin Labor | PR | 25 | 05/01/19 | 05/03/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 23587 | 0 | 0
120 | Roughin Labor | PR | 34 | 05/01/19 | 05/03/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 23596 | 0 | 0
120 | Roughin Labor | PR | 41 | 05/01/19 | 05/03/19 | HU05 | Hubbard, Justin A | 32 | 0 | 832 | 0 | 832 | 23603 | 0 | 0
120 | Roughin Labor | PR | 177 | 05/08/19 | 05/10/19 | DR04 | Draves, Steven W | 32 | 0 | 864 | 0 | 864 | 23661 | 0 | 0
120 | Roughin Labor | PR | 178 | 05/08/19 | 05/10/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 23662 | 0 | 0
120 | Roughin Labor | PR | 187 | 05/08/19 | 05/10/19 | GE71 | Gerard, Mitchell J | 32 | 0 | 1280 | 0 | 1280 | 23671 | 0 | 0
120 | Roughin Labor | PR | 194 | 05/08/19 | 05/10/19 | HU05 | Hubbard, Justin A | 40 | 0 | 1040 | 0 | 1040 | 23678 | 0 | 0
120 | Roughin Labor | PR | 409 | 05/15/19 | 05/17/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 23740 | 0 | 0
120 | Roughin Labor | PR | 410 | 05/15/19 | 05/17/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 23741 | 0 | 0
120 | Roughin Labor | PR | 419 | 05/15/19 | 05/17/19 | GE71 | Gerard, Mitchell J | 32 | 0 | 1280 | 0 | 1280 | 23750 | 0 | 0
120 | Roughin Labor | PR | 426 | 05/15/19 | 05/17/19 | HU05 | Hubbard, Justin A | 37.5 | 0 | 975 | 0 | 975 | 23757 | 0 | 0
120 | Roughin Labor | PR | 621 | 05/22/19 | 05/24/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 23816 | 0 | 0
120 | Roughin Labor | PR | 622 | 05/22/19 | 05/24/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 23817 | 0 | 0
120 | Roughin Labor | PR | 631 | 05/22/19 | 05/24/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 23826 | 0 | 0
120 | Roughin Labor | PR | 638 | 05/22/19 | 05/24/19 | HU05 | Hubbard, Justin A | 40 | 0 | 1040 | 0 | 1040 | 23833 | 0 | 0
120 | Roughin Labor | PR | 895 | 05/29/19 | 05/31/19 | DR04 | Draves, Steven W | 32 | 0 | 864 | 0 | 864 | 23895 | 0 | 0
120 | Roughin Labor | PR | 896 | 05/29/19 | 05/31/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 896 | 0 | 896 | 23896 | 0 | 0
120 | Roughin Labor | PR | 905 | 05/29/19 | 05/31/19 | GE71 | Gerard, Mitchell J | 32 | 0 | 1280 | 0 | 1280 | 23905 | 0 | 0
120 | Roughin Labor | PR | 912 | 05/29/19 | 05/31/19 | HU05 | Hubbard, Justin A | 29.5 | 0 | 767 | 0 | 767 | 23912 | 0 | 0
120 | Roughin Labor | PR | 197 | 06/05/19 | 06/07/19 | DR04 | Draves, Steven W | 32 | 0 | 864 | 0 | 864 | 23972 | 0 | 0
120 | Roughin Labor | PR | 198 | 06/05/19 | 06/07/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 896 | 0 | 896 | 23973 | 0 | 0
120 | Roughin Labor | PR | 207 | 06/05/19 | 06/07/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 23982 | 0 | 0
120 | Roughin Labor | PR | 214 | 06/05/19 | 06/07/19 | HU05 | Hubbard, Justin A | 24 | 0 | 624 | 0 | 624 | 23989 | 0 | 0
120 | Roughin Labor | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 4 | 0 | 108 | 0 | 108 | 24048 | 0 | 0
120 | Roughin Labor | PR | 468 | 06/12/19 | 06/14/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24049 | 0 | 0
120 | Roughin Labor | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 38 | 0 | 1520 | 0 | 1520 | 24056 | 0 | 0
120 | Roughin Labor | PR | 482 | 06/12/19 | 06/14/19 | HU05 | Hubbard, Justin A | 34.5 | 0 | 897 | 0 | 897 | 24063 | 0 | 0
120 | Roughin Labor | PR | 638 | 06/19/19 | 06/21/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 896 | 0 | 896 | 24124 | 0 | 0
120 | Roughin Labor | PR | 646 | 06/19/19 | 06/21/19 | GE71 | Gerard, Mitchell J | 40 | 0 | 1600 | 0 | 1600 | 24132 | 0 | 0
120 | Roughin Labor | PR | 653 | 06/19/19 | 06/21/19 | HU05 | Hubbard, Justin A | 29 | 0 | 754 | 0 | 754 | 24139 | 0 | 0
120 | Roughin Labor | PR | 27 | 07/03/19 | 07/05/19 | DR04 | Draves, Steven W | 35.5 | 0 | 958.5 | 0 | 958.5 | 24274 | 0 | 0
120 | Roughin Labor | PR | 28 | 07/03/19 | 07/05/19 | EI74 | Eisenhauer, Tommy J | 35.5 | 0 | 994 | 0 | 994 | 24275 | 0 | 0
120 | Roughin Labor | PR | 36 | 07/03/19 | 07/05/19 | GE71 | Gerard, Mitchell J | 4 | 0 | 160 | 0 | 160 | 24283 | 0 | 0
120 | Roughin Labor | PR | 43 | 07/03/19 | 07/05/19 | HU05 | Hubbard, Justin A | 4 | 0 | 104 | 0 | 104 | 24290 | 0 | 0
120 | Roughin Labor | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 8 | 0 | 224 | 0 | 224 | 24349 | 0 | 0
120 | Roughin Labor | PR | 526 | 07/17/19 | 07/19/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24425 | 0 | 0
120 | Roughin Labor | PR | 527 | 07/17/19 | 07/19/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24426 | 0 | 0
120 | Roughin Labor | PR | 535 | 07/17/19 | 07/19/19 | GE71 | Gerard, Mitchell J | 8 | 0 | 320 | 0 | 320 | 24434 | 0 | 0
120 | Roughin Labor | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 26 | 0 | 702 | 0 | 702 | 24579 | 0 | 0
120 | Roughin Labor | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 36 | 0 | 1008 | 0 | 1008 | 24580 | 0 | 0
120 | Roughin Labor | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 4 | 0 | 112 | 0 | 112 | 24654 | 0 | 0
120 | Roughin Labor | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -241.77 |  | 0 | 0
130 | Finish Labor | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | -64 | 0 | -64 | 920304 | 0 | 0
130 | Finish Labor | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | 64 | 0 | 64 | 920306 | 0 | 0
130 | Finish Labor | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23704 | 0 | 0
130 | Finish Labor | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 4 | 0 | 196 | 0 | 196 | 23858 | 0 | 0
130 | Finish Labor | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 144 | 0 | 144 | 24021 | 0 | 0
130 | Finish Labor | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 24022 | 0 | 0
130 | Finish Labor | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 36 | 0 | 972 | 0 | 972 | 24048 | 0 | 0
130 | Finish Labor | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 2 | 0 | 80 | 0 | 80 | 24056 | 0 | 0
130 | Finish Labor | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 32 | 0 | 576 | 0 | 576 | 24095 | 0 | 0
130 | Finish Labor | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 32 | 0 | 512 | 0 | 512 | 24096 | 0 | 0
130 | Finish Labor | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24119 | 0 | 0
130 | Finish Labor | PR | 637 | 06/19/19 | 06/21/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24123 | 0 | 0
130 | Finish Labor | PR | 645 | 06/19/19 | 06/21/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1440 | 0 | 1440 | 24131 | 0 | 0
130 | Finish Labor | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 16 | 0 | 272 | 0 | 272 | 24134 | 0 | 0
130 | Finish Labor | PR | 682 | 06/19/19 | 06/21/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 24168 | 0 | 0
130 | Finish Labor | PR | 685 | 06/19/19 | 06/21/19 | TR60 | Trower-Kelly, Fidel D | 40 | 0 | 720 | 0 | 720 | 24171 | 0 | 0
130 | Finish Labor | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 32 | 0 | 512 | 0 | 512 | 24172 | 0 | 0
130 | Finish Labor | PR | 855 | 06/26/19 | 06/28/19 | DR04 | Draves, Steven W | 46 | 0 | 1242 | 0 | 1242 | 24199 | 0 | 0
130 | Finish Labor | PR | 856 | 06/26/19 | 06/28/19 | EI74 | Eisenhauer, Tommy J | 10 | 0 | 280 | 0 | 280 | 24200 | 0 | 0
130 | Finish Labor | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 6 | 0 | 162 | 0 | 162 | 24201 | 0 | 0
130 | Finish Labor | PR | 863 | 06/26/19 | 06/28/19 | GE70 | Gerard, Jordan E | 47 | 0 | 1692 | 0 | 1692 | 24207 | 0 | 0
130 | Finish Labor | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 28 | 0 | 476 | 0 | 476 | 24210 | 0 | 0
130 | Finish Labor | PR | 899 | 06/26/19 | 06/28/19 | ST02 | Stahlschmidt, John P | 39 | 0 | 741 | 0 | 741 | 24243 | 0 | 0
130 | Finish Labor | PR | 902 | 06/26/19 | 06/28/19 | TR60 | Trower-Kelly, Fidel D | 45.5 | 0 | 819 | 0 | 819 | 24246 | 0 | 0
130 | Finish Labor | PR | 903 | 06/26/19 | 06/28/19 | VA98 | Vazquez Popoca, Jose N | 45.5 | 0 | 728 | 0 | 728 | 24247 | 0 | 0
130 | Finish Labor | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 1.5 | 0 | 73.5 | 0 | 73.5 | 24466 | 0 | 0
130 | Finish Labor | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 144 | 0 | 144 | 24473 | 0 | 0
130 | Finish Labor | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 256 | 0 | 256 | 24474 | 0 | 0
130 | Finish Labor | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 14 | 0 | 378 | 0 | 378 | 24579 | 0 | 0
130 | Finish Labor | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 4 | 0 | 112 | 0 | 112 | 24580 | 0 | 0
130 | Finish Labor | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 16 | 0 | 432 | 0 | 432 | 24581 | 0 | 0
130 | Finish Labor | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 24 | 0 | 864 | 0 | 864 | 24586 | 0 | 0
130 | Finish Labor | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 32 | 0 | 544 | 0 | 544 | 24589 | 0 | 0
130 | Finish Labor | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 8.5 | 0 | 416.5 | 0 | 416.5 | 24619 | 0 | 0
130 | Finish Labor | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 24623 | 0 | 0
130 | Finish Labor | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 24626 | 0 | 0
130 | Finish Labor | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 272 | 0 | 272 | 24627 | 0 | 0
130 | Finish Labor | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 15.5 | 0 | 387.5 | 0 | 387.5 | 24649 | 0 | 0
130 | Finish Labor | PR | 22 | 07/31/19 | 08/02/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24653 | 0 | 0
130 | Finish Labor | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 36 | 0 | 1008 | 0 | 1008 | 24654 | 0 | 0
130 | Finish Labor | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 8 | 0 | 288 | 0 | 288 | 24660 | 0 | 0
130 | Finish Labor | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 13 | 0 | 637 | 0 | 637 | 24692 | 0 | 0
130 | Finish Labor | PR | 65 | 07/31/19 | 08/02/19 | ST02 | Stahlschmidt, John P | 24 | 0 | 456 | 0 | 456 | 24696 | 0 | 0
130 | Finish Labor | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 24 | 0 | 408 | 0 | 408 | 24700 | 0 | 0
130 | Finish Labor | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24723 | 0 | 0
130 | Finish Labor | PR | 274 | 08/07/19 | 08/09/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24727 | 0 | 0
130 | Finish Labor | PR | 275 | 08/07/19 | 08/09/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24728 | 0 | 0
130 | Finish Labor | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 8 | 0 | 288 | 0 | 288 | 24735 | 0 | 0
130 | Finish Labor | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 8 | 0 | 136 | 0 | 136 | 24738 | 0 | 0
130 | Finish Labor | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 4.5 | 0 | 220.5 | 0 | 220.5 | 24767 | 0 | 0
130 | Finish Labor | PR | 321 | 08/07/19 | 08/09/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 272 | 0 | 272 | 24774 | 0 | 0
130 | Finish Labor | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24796 | 0 | 0
130 | Finish Labor | PR | 579 | 08/14/19 | 08/16/19 | CR87 | Cruz Reyes, Jose | 32 | 0 | 928 | 0 | 928 | 24798 | 0 | 0
130 | Finish Labor | PR | 581 | 08/14/19 | 08/16/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24800 | 0 | 0
130 | Finish Labor | PR | 582 | 08/14/19 | 08/16/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24801 | 0 | 0
130 | Finish Labor | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 16 | 0 | 576 | 0 | 576 | 24808 | 0 | 0
130 | Finish Labor | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 8 | 0 | 136 | 0 | 136 | 24811 | 0 | 0
130 | Finish Labor | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 10 | 0 | 490 | 0 | 490 | 24840 | 0 | 0
130 | Finish Labor | PR | 625 | 08/14/19 | 08/16/19 | ST02 | Stahlschmidt, John P | 24 | 0 | 456 | 0 | 456 | 24844 | 0 | 0
130 | Finish Labor | PR | 629 | 08/14/19 | 08/16/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 272 | 0 | 272 | 24848 | 0 | 0
130 | Finish Labor | PR | 815 | 08/21/19 | 08/23/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 24873 | 0 | 0
130 | Finish Labor | PR | 817 | 08/21/19 | 08/23/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24875 | 0 | 0
130 | Finish Labor | PR | 818 | 08/21/19 | 08/23/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24876 | 0 | 0
130 | Finish Labor | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 6 | 0 | 216 | 0 | 216 | 24883 | 0 | 0
130 | Finish Labor | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 14.5 | 0 | 710.5 | 0 | 710.5 | 24916 | 0 | 0
130 | Finish Labor | PR | 862 | 08/21/19 | 08/23/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 24920 | 0 | 0
130 | Finish Labor | PR | 1004 | 08/28/19 | 08/30/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24946 | 0 | 0
130 | Finish Labor | PR | 1006 | 08/28/19 | 08/30/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 24948 | 0 | 0
130 | Finish Labor | PR | 1008 | 08/28/19 | 08/30/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 24950 | 0 | 0
130 | Finish Labor | PR | 1009 | 08/28/19 | 08/30/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 24951 | 0 | 0
130 | Finish Labor | PR | 1016 | 08/28/19 | 08/30/19 | GE70 | Gerard, Jordan E | 21 | 0 | 756 | 0 | 756 | 24958 | 0 | 0
130 | Finish Labor | PR | 1019 | 08/28/19 | 08/30/19 | GU17 | Guerrero, Ali A | 16 | 0 | 272 | 0 | 272 | 24961 | 0 | 0
130 | Finish Labor | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 24991 | 0 | 0
130 | Finish Labor | PR | 1053 | 08/28/19 | 08/30/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 24995 | 0 | 0
130 | Finish Labor | PR | 27 | 09/04/19 | 09/06/19 | CR87 | Cruz Reyes, Jose | 32 | 0 | 928 | 0 | 928 | 25025 | 0 | 0
130 | Finish Labor | PR | 29 | 09/04/19 | 09/06/19 | DR04 | Draves, Steven W | 32 | 0 | 864 | 0 | 864 | 25027 | 0 | 0
130 | Finish Labor | PR | 30 | 09/04/19 | 09/06/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 896 | 0 | 896 | 25028 | 0 | 0
130 | Finish Labor | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 25068 | 0 | 0
130 | Finish Labor | PR | 74 | 09/04/19 | 09/06/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 25072 | 0 | 0
130 | Finish Labor | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 8 | 0 | 232 | 0 | 232 | 25100 | 0 | 0
130 | Finish Labor | PR | 253 | 09/11/19 | 09/13/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 25102 | 0 | 0
130 | Finish Labor | PR | 254 | 09/11/19 | 09/13/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 25103 | 0 | 0
130 | Finish Labor | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 25142 | 0 | 0
130 | Finish Labor | PR | 297 | 09/11/19 | 09/13/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 152 | 0 | 152 | 25146 | 0 | 0
130 | Finish Labor | PR | 490 | 09/18/19 | 09/20/19 | DR04 | Draves, Steven W | 40 | 0 | 1080 | 0 | 1080 | 25176 | 0 | 0
130 | Finish Labor | PR | 491 | 09/18/19 | 09/20/19 | EI74 | Eisenhauer, Tommy J | 40 | 0 | 1120 | 0 | 1120 | 25177 | 0 | 0
130 | Finish Labor | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 25217 | 0 | 0
130 | Finish Labor | PR | 535 | 09/18/19 | 09/20/19 | ST02 | Stahlschmidt, John P | 18 | 0 | 342 | 0 | 342 | 25221 | 0 | 0
130 | Finish Labor | PR | 646 | 09/25/19 | 09/27/19 | DR04 | Draves, Steven W | 32 | 0 | 864 | 0 | 864 | 25251 | 0 | 0
130 | Finish Labor | PR | 647 | 09/25/19 | 09/27/19 | EI74 | Eisenhauer, Tommy J | 32 | 0 | 896 | 0 | 896 | 25252 | 0 | 0
130 | Finish Labor | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 4 | 0 | 124 | 0 | 124 | 25274 | 0 | 0
130 | Finish Labor | PR | 690 | 09/25/19 | 09/27/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 25295 | 0 | 0
130 | Finish Labor | PR | 694 | 09/25/19 | 09/27/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 25299 | 0 | 0
130 | Finish Labor | PR | 44 | 10/02/19 | 10/04/19 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1240 | 0 | 1240 | 25351 | 0 | 0
130 | Finish Labor | PR | 66 | 10/02/19 | 10/04/19 | SA54 | Sanders, Allen O | 8 | 0 | 392 | 0 | 392 | 25373 | 0 | 0
130 | Finish Labor | PR | 70 | 10/02/19 | 10/04/19 | ST02 | Stahlschmidt, John P | 32 | 0 | 608 | 0 | 608 | 25377 | 0 | 0
130 | Finish Labor | PR | 273 | 10/09/19 | 10/11/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 25407 | 0 | 0
130 | Finish Labor | PR | 275 | 10/09/19 | 10/11/19 | CR87 | Cruz Reyes, Jose | 8 | 0 | 232 | 0 | 232 | 25409 | 0 | 0
130 | Finish Labor | PR | 279 | 10/09/19 | 10/11/19 | EL33 | Eliassen, Cory H | 8 | 0 | 216 | 0 | 216 | 25413 | 0 | 0
130 | Finish Labor | PR | 284 | 10/09/19 | 10/11/19 | GA83 | Gauthier, Dillon R | 8 | 0 | 136 | 0 | 136 | 25418 | 0 | 0
130 | Finish Labor | PR | 299 | 10/09/19 | 10/11/19 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1240 | 0 | 1240 | 25433 | 0 | 0
130 | Finish Labor | PR | 321 | 10/09/19 | 10/11/19 | SA54 | Sanders, Allen O | 12 | 0 | 588 | 0 | 588 | 25455 | 0 | 0
130 | Finish Labor | PR | 324 | 10/09/19 | 10/11/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 25458 | 0 | 0
130 | Finish Labor | PR | 492 | 10/16/19 | 10/18/19 | KI55 | Kinssies, Jr, John E | 34.5 | 0 | 1069.5 | 0 | 1069.5 | 25509 | 0 | 0
130 | Finish Labor | PR | 514 | 10/16/19 | 10/18/19 | SA54 | Sanders, Allen O | 13 | 0 | 637 | 0 | 637 | 25531 | 0 | 0
130 | Finish Labor | PR | 517 | 10/16/19 | 10/18/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 25534 | 0 | 0
130 | Finish Labor | PR | 627 | 10/23/19 | 10/25/19 | KI55 | Kinssies, Jr, John E | 35 | 0 | 1085 | 0 | 1085 | 25584 | 0 | 0
130 | Finish Labor | PR | 650 | 10/23/19 | 10/25/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 25607 | 0 | 0
130 | Finish Labor | PR | 653 | 10/23/19 | 10/25/19 | ST02 | Stahlschmidt, John P | 5 | 0 | 95 | 0 | 95 | 25610 | 0 | 0
130 | Finish Labor | PR | 43 | 10/30/19 | 11/01/19 | KI55 | Kinssies, Jr, John E | 30 | 0 | 1050 | 0 | 1050 | 25660 | 0 | 0
130 | Finish Labor | PR | 66 | 10/30/19 | 11/01/19 | SA54 | Sanders, Allen O | 8.5 | 0 | 459 | 0 | 459 | 25683 | 0 | 0
130 | Finish Labor | PR | 217 | 11/06/19 | 11/08/19 | KI55 | Kinssies, Jr, John E | 27 | 0 | 945 | 0 | 945 | 25736 | 0 | 0
130 | Finish Labor | PR | 240 | 11/06/19 | 11/08/19 | SA54 | Sanders, Allen O | 6.5 | 0 | 351 | 0 | 351 | 25759 | 0 | 0
130 | Finish Labor | PR | 476 | 11/13/19 | 11/15/19 | KI55 | Kinssies, Jr, John E | 7 | 0 | 245 | 0 | 245 | 25812 | 0 | 0
130 | Finish Labor | PR | 499 | 11/13/19 | 11/15/19 | SA54 | Sanders, Allen O | 11 | 0 | 594 | 0 | 594 | 25835 | 0 | 0
130 | Finish Labor | PR | 670 | 11/20/19 | 11/22/19 | SA54 | Sanders, Allen O | 5.5 | 0 | 297 | 0 | 297 | 25910 | 0 | 0
130 | Finish Labor | PR | 91 | 12/04/19 | 12/06/19 | SA54 | Sanders, Allen O | 2 | 0 | 108 | 0 | 108 | 26063 | 0 | 0
130 | Finish Labor | PR | 452 | 12/11/19 | 12/13/19 | SA54 | Sanders, Allen O | 3 | 0 | 162 | 0 | 162 | 26218 | 0 | 0
130 | Finish Labor | PR | 763 | 12/25/19 | 12/27/19 | SA54 | Sanders, Allen O | 1 | 0 | 54 | 0 | 54 | 26371 | 0 | 0
141 | Water Main/Insulation Lab | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 6 | 0 | 252 | 252 | 22036 | 0 | 0
141 | Water Main/Insulation Lab | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 32 | 0 | 896 | 0 | 896 | 22036 | 0 | 0
141 | Water Main/Insulation Lab | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 4 | 0 | 168 | 168 | 22178 | 0 | 0
141 | Water Main/Insulation Lab | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 29 | 0 | 812 | 0 | 812 | 22178 | 0 | 0
141 | Water Main/Insulation Lab | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 10 | 0 | 280 | 0 | 280 | 22249 | 0 | 0
141 | Water Main/Insulation Lab | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 4 | 0 | 80 | 0 | 80 | 22568 | 0 | 0
141 | Water Main/Insulation Lab | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 8 | 0 | 224 | 0 | 224 | 22612 | 0 | 0
141 | Water Main/Insulation Lab | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 2 | 0 | 36 | 0 | 36 | 22637 | 0 | 0
141 | Water Main/Insulation Lab | PR | 180 | 02/06/19 | 02/08/19 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 648 | 0 | 648 | 22722 | 0 | 0
141 | Water Main/Insulation Lab | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22737 | 0 | 0
141 | Water Main/Insulation Lab | PR | 342 | 02/13/19 | 02/15/19 | GA46 | Galdamez, Dagoberto A | 14 | 0 | 378 | 0 | 378 | 22792 | 0 | 0
141 | Water Main/Insulation Lab | PR | 357 | 02/13/19 | 02/15/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22808 | 0 | 0
141 | Water Main/Insulation Lab | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 10 | 0 | 280 | 0 | 280 | 22821 | 0 | 0
141 | Water Main/Insulation Lab | PR | 600 | 02/20/19 | 02/22/19 | GA46 | Galdamez, Dagoberto A | 56 | 0 | 1512 | 0 | 1512 | 22862 | 0 | 0
141 | Water Main/Insulation Lab | PR | 613 | 02/20/19 | 02/22/19 | KI55 | Kinssies, Jr, John E | 6 | 0 | 162 | 0 | 162 | 22875 | 0 | 0
141 | Water Main/Insulation Lab | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 99 | 99 | 22877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 48 | 0 | 1584 | 0 | 1584 | 22877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 10 | 0 | 270 | 0 | 270 | 22933 | 0 | 0
141 | Water Main/Insulation Lab | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 8 | 0 | 288 | 0 | 288 | 22934 | 0 | 0
141 | Water Main/Insulation Lab | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 10 | 0 | 330 | 0 | 330 | 22949 | 0 | 0
141 | Water Main/Insulation Lab | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 648 | 0 | 648 | 23006 | 0 | 0
141 | Water Main/Insulation Lab | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 23021 | 0 | 0
141 | Water Main/Insulation Lab | PR | 514 | 03/13/19 | 03/15/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 23076 | 0 | 0
141 | Water Main/Insulation Lab | PR | 529 | 03/13/19 | 03/15/19 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1320 | 0 | 1320 | 23091 | 0 | 0
141 | Water Main/Insulation Lab | PR | 728 | 03/20/19 | 03/22/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 23149 | 0 | 0
141 | Water Main/Insulation Lab | PR | 743 | 03/20/19 | 03/22/19 | LI49 | Lima Romero, Melvin A | 29.5 | 0 | 973.5 | 0 | 973.5 | 23164 | 0 | 0
141 | Water Main/Insulation Lab | PR | 940 | 03/27/19 | 03/29/19 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 1080 | 0 | 1080 | 23224 | 0 | 0
141 | Water Main/Insulation Lab | PR | 955 | 03/27/19 | 03/29/19 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1320 | 0 | 1320 | 23239 | 0 | 0
141 | Water Main/Insulation Lab | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 8 | 0 | 216 | 0 | 216 | 23296 | 0 | 0
141 | Water Main/Insulation Lab | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 23312 | 0 | 0
141 | Water Main/Insulation Lab | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 16 | 0 | 432 | 0 | 432 | 23370 | 0 | 0
141 | Water Main/Insulation Lab | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 23385 | 0 | 0
141 | Water Main/Insulation Lab | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 23460 | 0 | 0
141 | Water Main/Insulation Lab | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24119 | 0 | 0
141 | Water Main/Insulation Lab | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24442 | 0 | 0
141 | Water Main/Insulation Lab | PR | 545 | 07/17/19 | 07/19/19 | KI55 | Kinssies, Jr, John E | 4 | 0 | 124 | 0 | 124 | 24444 | 0 | 0
141 | Water Main/Insulation Lab | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24595 | 0 | 0
141 | Water Main/Insulation Lab | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24669 | 0 | 0
141 | Water Main/Insulation Lab | PR | 878 | 11/27/19 | 11/27/19 | HU06 | Hubbard, Robert W | 2 | 0 | 108 | 0 | 108 | 25959 | 0 | 0
142 | Mech Room Labor | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23834 | 0 | 0
142 | Mech Room Labor | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 24140 | 0 | 0
142 | Mech Room Labor | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 6 | 0 | 300 | 0 | 300 | 24216 | 0 | 0
142 | Mech Room Labor | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 32 | 0 | 992 | 0 | 992 | 24218 | 0 | 0
142 | Mech Room Labor | PR | 881 | 06/26/19 | 06/28/19 | MC09 | McCabe, Thomas C | 32 | 0 | 1120 | 0 | 1120 | 24225 | 0 | 0
142 | Mech Room Labor | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 24291 | 0 | 0
142 | Mech Room Labor | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 8 | 0 | 248 | 0 | 248 | 24293 | 0 | 0
142 | Mech Room Labor | PR | 53 | 07/03/19 | 07/05/19 | MC09 | McCabe, Thomas C | 22 | 0 | 770 | 0 | 770 | 24301 | 0 | 0
142 | Mech Room Labor | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 24595 | 0 | 0
142 | Mech Room Labor | PR | 648 | 07/24/19 | 07/26/19 | KI55 | Kinssies, Jr, John E | 16 | 0 | 496 | 0 | 496 | 24597 | 0 | 0
210 | Underground Material | AP | 120 | 10/27/17 | 11/07/17 | 1231KS | Keller Supply Company |  |  |  |  | 373 | S011300894.001 | 0 | 0
210 | Underground Material | AP | 260 | 10/30/17 | 11/13/17 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 55.2 | 4244474-00 | 0 | 0
210 | Underground Material | GL | 499 | 11/21/17 | 11/21/17 | CK#5021 | Richard Anderson |  |  |  |  | 5.82 |  | 0 | 0
210 | Underground Material | GL | 747 | 12/22/17 | 12/22/17 | Mat | Req 3369 |  |  |  |  | 158 |  | 0 | 0
210 | Underground Material | AP | 889 | 06/15/18 | 06/26/18 | 2045RS | Rosen Supply Company, Inc. $Notch |  |  |  |  | 4189.58 | 4248945-00 | 0 | 0
210 | Underground Material | GL | 1053 | 06/30/18 | 06/30/18 | Mat | Req 3765 |  |  |  |  | 249 |  | 0 | 0
210 | Underground Material | AP | 380 | 06/25/18 | 07/13/18 | 2045RS | Rosen Supply Company, Inc. $Notch |  |  |  |  | 223 | 4251483-00 | 0 | 0
210 | Underground Material | GL | 387 | 07/16/18 | 07/16/18 | Mat | Req 4479 |  |  |  |  | 56.96 |  | 0 | 0
210 | Underground Material | GL | 349 | 08/10/18 | 08/10/18 | Mat | Req 4574 |  |  |  |  | 400.77 |  | 0 | 0
210 | Underground Material | AP | 416 | 07/10/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3122 | 4254312-00 | 0 | 0
210 | Underground Material | AP | 459 | 07/17/18 | 08/15/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 325.67 | 4254695-00 | 0 | 0
210 | Underground Material | GL | 661 | 08/22/18 | 08/22/18 | Mat | Req 4628 |  |  |  |  | 283.74 |  | 0 | 0
210 | Underground Material | AP | 715 | 07/27/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 191.84 | 4255192-00 | 0 | 0
210 | Underground Material | AP | 716 | 07/30/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 380 | 4255221-00 | 0 | 0
210 | Underground Material | AP | 833 | 08/03/18 | 08/24/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 52.78 | 6434410 | 0 | 0
210 | Underground Material | AP | 930 | 08/03/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 39.18 | 4255485-00 | 0 | 0
210 | Underground Material | AP | 966 | 08/15/18 | 08/29/18 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 182.8 | J344487 | 0 | 0
210 | Underground Material | AP | 989 | 08/08/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 375.52 | 4255683-00 | 0 | 0
210 | Underground Material | AP | 19 | 08/15/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 181.94 | 4255991-00 | 0 | 0
210 | Underground Material | GL | 191 | 09/10/18 | 09/10/18 | Mat | Req 4683 |  |  |  |  | 225.06 |  | 0 | 0
210 | Underground Material | AP | 263 | 08/20/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2756 | 4256115-00 | 0 | 0
210 | Underground Material | AP | 264 | 08/21/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 14.62 | 4255991-01 | 0 | 0
210 | Underground Material | AP | 378 | 08/22/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 73.05 | 4256304-00 | 0 | 0
210 | Underground Material | AP | 379 | 08/24/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 320 | 4256396-00 | 0 | 0
210 | Underground Material | AP | 433 | 08/27/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 443.46 | 4256487-00 | 0 | 0
210 | Underground Material | AP | 416 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 18.26 | 4260076-00 | 0 | 0
210 | Underground Material | AP | 680 | 11/26/18 | 12/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 28.01 | 6746380 | 0 | 0
210 | Underground Material | GL | 171 | 07/10/19 | 07/10/19 | Mat | Req 6144 |  |  |  |  | -210.69 |  | 0 | 0
210 | Underground Material | AP | 111 | 09/26/19 | 11/01/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 21.22 | 4273291-00 | 0 | 0
211 | Garage Material | GL | 408 | 07/16/18 | 07/16/18 | Mat | Req 5274 |  |  |  |  | 15.5 |  | 0 | 0
211 | Garage Material | GL | 666 | 08/22/18 | 08/22/18 | Mat | Req 4633 |  |  |  |  | 213.5 |  | 0 | 0
211 | Garage Material | AP | 931 | 08/06/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4189.58 | 4248935-00 | 0 | 0
211 | Garage Material | GL | 192 | 09/10/18 | 09/10/18 | Mat | Req 4682 |  |  |  |  | 297.7 |  | 0 | 0
211 | Garage Material | AP | 224 | 08/15/18 | 09/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 100.26 | S012194606.001 | 0 | 0
211 | Garage Material | GL | 365 | 09/14/18 | 09/14/18 | Mat | Req 5333 |  |  |  |  | -118.7 |  | 0 | 0
211 | Garage Material | GL | 773 | 09/30/18 | 09/30/18 | Mat | Req 5420 |  |  |  |  | 920.8 |  | 0 | 0
211 | Garage Material | GL | 370 | 10/16/18 | 10/16/18 | Mat | Req 5466 |  |  |  |  | 109.36 |  | 0 | 0
211 | Garage Material | AP | 595 | 09/25/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4279.81 | 4257611-00 | 0 | 0
211 | Garage Material | GL | 798 | 10/29/18 | 10/29/18 | Mat | Req 5494 |  |  |  |  | 264.43 |  | 0 | 0
211 | Garage Material | GL | 887 | 10/31/18 | 10/31/18 | Mat | Req 5491 |  |  |  |  | 18.9 |  | 0 | 0
211 | Garage Material | AP | 414 | 10/17/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 222.39 | 4258394-00 | 0 | 0
211 | Garage Material | AP | 599 | 10/22/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 732.55 | 4258845-00 | 0 | 0
211 | Garage Material | AP | 701 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 772.96 | 4259105-00 | 0 | 0
211 | Garage Material | GL | 748 | 11/26/18 | 11/26/18 | Mat | Req 5527 |  |  |  |  | 127.8 |  | 0 | 0
211 | Garage Material | AP | 962 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 101.98 | 4258394-01 | 0 | 0
211 | Garage Material | AP | 963 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 281.72 | 4259369-00 | 0 | 0
211 | Garage Material | GL | 993 | 11/30/18 | 11/30/18 | Mat | Req 5594 |  |  |  |  | 65 |  | 0 | 0
211 | Garage Material | AP | 413 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 171.78 | 4259369-01 | 0 | 0
211 | Garage Material | AP | 415 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 189.86 | 4260021-00 | 0 | 0
211 | Garage Material | GL | 632 | 12/21/18 | 12/21/18 | Mat | Req 5605 |  |  |  |  | 242 |  | 0 | 0
211 | Garage Material | GL | 320 | 01/11/19 | 01/11/19 | Mat | Req 4872 |  |  |  |  | 125.97 |  | 0 | 0
211 | Garage Material | AP | 386 | 11/30/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.99 | 4260452-00 | 0 | 0
211 | Garage Material | AP | 390 | 11/29/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1225.4 | 4260266-00 | 0 | 0
211 | Garage Material | GL | 428 | 01/15/19 | 01/15/19 | Mat | Req 4922 |  |  |  |  | 315.16 |  | 0 | 0
211 | Garage Material | GL | 672 | 01/23/19 | 01/23/19 | Mat | Req 4974 |  |  |  |  | 40 |  | 0 | 0
211 | Garage Material | GL | 184 | 03/04/19 | 03/04/19 | Mat | Req 5696 |  |  |  |  | 80.85 |  | 0 | 0
211 | Garage Material | GL | 381 | 03/08/19 | 03/08/19 | Mat | Req 4934 |  |  |  |  | 140.05 |  | 0 | 0
211 | Garage Material | GL | 600 | 03/15/19 | 03/15/19 | Mat | Req 5805 |  |  |  |  | 188.89 |  | 0 | 0
211 | Garage Material | GL | 197 | 04/08/19 | 04/08/19 | Mat | Req 5869 |  |  |  |  | 208.2 |  | 0 | 0
211 | Garage Material | GL | 845 | 05/30/19 | 05/30/19 | Mat | Req 5216 |  |  |  |  | 118.57 |  | 0 | 0
211 | Garage Material | GL | 151 | 06/05/19 | 06/05/19 | Mat | Req 6003 |  |  |  |  | 8.4 |  | 0 | 0
211 | Garage Material | GL | 814 | 06/26/19 | 06/26/19 | Mat | Req 6044 |  |  |  |  | 175.43 |  | 0 | 0
211 | Garage Material | GL | 170 | 07/10/19 | 07/10/19 | Mat | Req 6145 |  |  |  |  | -368.85 |  | 0 | 0
211 | Garage Material | AP | 268 | 06/18/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 128 | 4268985-00 | 0 | 0
211 | Garage Material | AP | 271 | 06/19/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 193.59 | 4269074-00 | 0 | 0
211 | Garage Material | AP | 485 | 07/02/19 | 07/17/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 84.98 | 4269711-00 | 0 | 0
211 | Garage Material | GL | 219 | 08/08/19 | 08/08/19 | Mat | Req 6168 |  |  |  |  | 87.1 |  | 0 | 0
211 | Garage Material | GL | 675 | 08/20/19 | 08/20/19 | Mat | Req 6273 |  |  |  |  | -14.12 |  | 0 | 0
211 | Garage Material | GL | 690 | 10/28/19 | 10/28/19 | Mat | Req 6421 |  |  |  |  | -168.62 |  | 0 | 0
211 | Garage Material | GL | 698 | 10/28/19 | 10/28/19 | Mat | Req 6430 |  |  |  |  | -40.12 |  | 0 | 0
211 | Garage Material | GL | 143 | 11/05/19 | 11/05/19 | Mat | Req 6478 |  |  |  |  | 151.36 |  | 0 | 0
212 | Canout Material | GL | 338 | 08/10/18 | 08/10/18 | Mat | Req 4573 |  |  |  |  | 1361 |  | 0 | 0
212 | Canout Material | GL | 361 | 08/10/18 | 08/10/18 | Mat | Req 4545 |  |  |  |  | 3100.01 |  | 0 | 0
212 | Canout Material | GL | 662 | 08/22/18 | 08/22/18 | Mat | Req 4629 |  |  |  |  | 745.33 |  | 0 | 0
212 | Canout Material | GL | 679 | 08/22/18 | 08/22/18 | Mat | Req 4646 |  |  |  |  | -842.6 |  | 0 | 0
212 | Canout Material | GL | 190 | 09/10/18 | 09/10/18 | Mat | Req 4684 |  |  |  |  | 75.44 |  | 0 | 0
212 | Canout Material | GL | 361 | 09/14/18 | 09/14/18 | Mat | Req 5331 |  |  |  |  | -92.63 |  | 0 | 0
212 | Canout Material | GL | 582 | 10/22/18 | 10/22/18 | Mat | Req 5478 |  |  |  |  | -23.13 |  | 0 | 0
220 | Roughin Material | GL | 690 | 07/25/18 | 07/25/18 | Mat | Req 4507 |  |  |  |  | 10.32 |  | 0 | 0
220 | Roughin Material | GL | 363 | 08/10/18 | 08/10/18 | Mat | Req 4540 |  |  |  |  | 11.44 |  | 0 | 0
220 | Roughin Material | GL | 663 | 08/22/18 | 08/22/18 | Mat | Req 4630 |  |  |  |  | 90.59 |  | 0 | 0
220 | Roughin Material | AP | 834 | 08/16/18 | 08/24/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 862.92 | 6471335 | 0 | 0
220 | Roughin Material | GL | 189 | 09/10/18 | 09/10/18 | Mat | Req 4685 |  |  |  |  | 117.77 |  | 0 | 0
220 | Roughin Material | GL | 364 | 09/14/18 | 09/14/18 | Mat | Req 5332 |  |  |  |  | -932.3 |  | 0 | 0
220 | Roughin Material | AP | 402 | 08/28/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 428.32 | S8899150.001 | 0 | 0
220 | Roughin Material | GL | 637 | 09/25/18 | 09/25/18 | Mat | Req 5353 |  |  |  |  | 50.5 |  | 0 | 0
220 | Roughin Material | GL | 774 | 09/30/18 | 09/30/18 | Mat | Req 5421 |  |  |  |  | 379.65 |  | 0 | 0
220 | Roughin Material | GL | 797 | 10/29/18 | 10/29/18 | Mat | Req 5495 |  |  |  |  | 26.26 |  | 0 | 0
220 | Roughin Material | AP | 840 | 10/09/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 45.83 | 100918A | 0 | 0
220 | Roughin Material | GL | 888 | 10/31/18 | 10/31/18 | Mat | Req 5490 |  |  |  |  | 289.26 |  | 0 | 0
220 | Roughin Material | AP | 115 | 10/05/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 11.33 | 4258194-00 | 0 | 0
220 | Roughin Material | AP | 117 | 10/05/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 23.62 | 4258256-00 | 0 | 0
220 | Roughin Material | AP | 699 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5594.05 | 4259104-00 | 0 | 0
220 | Roughin Material | GL | 747 | 11/26/18 | 11/26/18 | Mat | Req 5528 |  |  |  |  | 195.19 |  | 0 | 0
220 | Roughin Material | GL | 994 | 11/30/18 | 11/30/18 | Mat | Req 5577 |  |  |  |  | 96.28 |  | 0 | 0
220 | Roughin Material | AP | 1029 | 11/09/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 6528.94 | S8678467.001 | 0 | 0
220 | Roughin Material | AP | 1030 | 11/15/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 327.06 | S9019180.001 | 0 | 0
220 | Roughin Material | AP | 381 | 11/07/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 510.66 | 4259674-00 | 0 | 0
220 | Roughin Material | AP | 414 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 11041.67 | 4259538-00 | 0 | 0
220 | Roughin Material | GL | 631 | 12/21/18 | 12/21/18 | Mat | Req 5604 |  |  |  |  | 1038.9 |  | 0 | 0
220 | Roughin Material | AP | 141 | 12/18/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 5178.8 | 6693515 | 0 | 0
220 | Roughin Material | GL | 322 | 01/11/19 | 01/11/19 | Mat | Req 4870 |  |  |  |  | 816.47 |  | 0 | 0
220 | Roughin Material | AP | 385 | 11/29/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5686 | 4260403-00 | 0 | 0
220 | Roughin Material | AP | 387 | 11/30/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 675.99 | 4260583-00 | 0 | 0
220 | Roughin Material | AP | 388 | 12/04/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 131.28 | 4260583-01 | 0 | 0
220 | Roughin Material | AP | 389 | 12/04/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 128.02 | 4260726-00 | 0 | 0
220 | Roughin Material | GL | 429 | 01/15/19 | 01/15/19 | Mat | Req 4921 |  |  |  |  | 5063.5 |  | 0 | 0
220 | Roughin Material | AP | 571 | 12/07/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 175.86 | 4260945-00 | 0 | 0
220 | Roughin Material | AP | 576 | 12/10/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 10333.71 | 4260933-00 | 0 | 0
220 | Roughin Material | AP | 593 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 56.89 | 4260583-02 | 0 | 0
220 | Roughin Material | AP | 594 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 58.75 | 4261038-00 | 0 | 0
220 | Roughin Material | AP | 595 | 12/12/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 28.91 | 4261038-01 | 0 | 0
220 | Roughin Material | AP | 596 | 12/14/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 142.43 | 4261242-00 | 0 | 0
220 | Roughin Material | AP | 626 | 12/17/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 131.36 | 4261301-00 | 0 | 0
220 | Roughin Material | AP | 628 | 12/19/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 316.23 | 4261437-00 | 0 | 0
220 | Roughin Material | AP | 825 | 12/27/18 | 01/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13.13 | 4260583-03 | 0 | 0
220 | Roughin Material | AP | 826 | 12/27/18 | 01/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 41.59 | 4261301-01 | 0 | 0
220 | Roughin Material | AP | 827 | 12/27/18 | 01/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 48.18 | 4261437-01 | 0 | 0
220 | Roughin Material | AP | 854 | 01/03/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 201.72 | 4261817-00 | 0 | 0
220 | Roughin Material | AP | 855 | 01/04/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6479.7 | 4261773-00 | 0 | 0
220 | Roughin Material | GL | 863 | 01/30/19 | 01/30/19 | Mat | Req 5675 |  |  |  |  | 402.75 |  | 0 | 0
220 | Roughin Material | AP | 266 | 01/08/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 352 | 4260933-02 | 0 | 0
220 | Roughin Material | AP | 267 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1083.54 | 4260933-01 | 0 | 0
220 | Roughin Material | AP | 268 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 181.02 | 4262034-00 | 0 | 0
220 | Roughin Material | AP | 470 | 01/11/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 90.4 | 4262154-00 | 0 | 0
220 | Roughin Material | AP | 471 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 50.02 | 4262147-00 | 0 | 0
220 | Roughin Material | AP | 482 | 01/16/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1059.91 | 4262275-00 | 0 | 0
220 | Roughin Material | AP | 483 | 01/17/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 235.6 | 4262417-00 | 0 | 0
220 | Roughin Material | AP | 497 | 01/25/19 | 02/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 292.8 | 4262769-00 | 0 | 0
220 | Roughin Material | AP | 516 | 02/01/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 6528.94 | S9116293.001 | 0 | 0
220 | Roughin Material | AP | 549 | 02/15/19 | 02/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 327.05 | S9134682.001 | 0 | 0
220 | Roughin Material | AP | 670 | 01/31/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.56 | 4262275-01 | 0 | 0
220 | Roughin Material | AP | 671 | 01/31/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 153 | 4263012-00 | 0 | 0
220 | Roughin Material | AP | 706 | 02/06/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 240.84 | 4263229-00 | 0 | 0
220 | Roughin Material | GL | 140 | 03/04/19 | 03/04/19 | Mat | Req 5050 |  |  |  |  | -1400.82 |  | 0 | 0
220 | Roughin Material | GL | 149 | 03/04/19 | 03/04/19 | Mat | Req 5045 |  |  |  |  | -33.94 |  | 0 | 0
220 | Roughin Material | GL | 187 | 03/04/19 | 03/04/19 | Mat | Req 5693 |  |  |  |  | 1449.84 |  | 0 | 0
220 | Roughin Material | AP | 233 | 02/15/19 | 03/06/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19.28 | 4262275-02 | 0 | 0
220 | Roughin Material | GL | 359 | 03/08/19 | 03/08/19 | Mat | Req 5028 |  |  |  |  | 1963.42 |  | 0 | 0
220 | Roughin Material | AP | 397 | 02/15/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.56 | 4263229-01 | 0 | 0
220 | Roughin Material | AP | 427 | 02/22/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1578.17 | 4263730-00 | 0 | 0
220 | Roughin Material | AP | 475 | 02/26/19 | 03/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 340.4 | 4263902-00 | 0 | 0
220 | Roughin Material | GL | 599 | 03/15/19 | 03/15/19 | Mat | Req 5806 |  |  |  |  | 32.78 |  | 0 | 0
220 | Roughin Material | GL | 617 | 03/15/19 | 03/15/19 | Mat | Req 5067 |  |  |  |  | 524.48 |  | 0 | 0
220 | Roughin Material | AP | 654 | 03/01/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 577.34 | 4264042-00 | 0 | 0
220 | Roughin Material | AP | 655 | 03/04/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75.63 | 4264197-00 | 0 | 0
220 | Roughin Material | GL | 828 | 03/25/19 | 03/25/19 | Mat | Req 5088 |  |  |  |  | 153 |  | 0 | 0
220 | Roughin Material | AP | 863 | 03/07/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3809.57 | S8678630.001 | 0 | 0
220 | Roughin Material | AP | 47 | 03/11/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 301.96 | 4264512-00 | 0 | 0
220 | Roughin Material | AP | 58 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 943.12 | 4264660-00 | 0 | 0
220 | Roughin Material | GL | 196 | 04/08/19 | 04/08/19 | Mat | Req 5868 |  |  |  |  | 270.16 |  | 0 | 0
220 | Roughin Material | AP | 245 | 03/19/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 51.5 | 4264910-00 | 0 | 0
220 | Roughin Material | GL | 429 | 04/12/19 | 04/12/19 | Mat | Req 5147 |  |  |  |  | 1622.51 |  | 0 | 0
220 | Roughin Material | AP | 459 | 04/02/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 852.31 | S9194076.001 | 0 | 0
220 | Roughin Material | AP | 504 | 03/26/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 711.52 | 4265248-00 | 0 | 0
220 | Roughin Material | AP | 512 | 03/28/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 864.68 | 4265406-00 | 0 | 0
220 | Roughin Material | AP | 636 | 04/05/19 | 04/22/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2957.37 | S9200451.001 | 0 | 0
220 | Roughin Material | AP | 675 | 04/04/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 136.4 | 4265795-00 | 0 | 0
220 | Roughin Material | GL | 691 | 04/24/19 | 04/24/19 | Mat | Req 5904 |  |  |  |  | 357.55 |  | 0 | 0
220 | Roughin Material | AP | 709 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 126.8 | 4265829-00 | 0 | 0
220 | Roughin Material | AP | 726 | 04/10/19 | 04/24/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 212.96 | S9194076.002 | 0 | 0
220 | Roughin Material | GL | 880 | 04/30/19 | 04/30/19 | Mat | Req 5177 |  |  |  |  | 196 |  | 0 | 0
220 | Roughin Material | GL | 911 | 04/30/19 | 04/30/19 | Mat | Req 5181 |  |  |  |  | -57.41 |  | 0 | 0
220 | Roughin Material | GL | 914 | 04/30/19 | 04/30/19 | Mat | Req 5178 |  |  |  |  | -120 |  | 0 | 0
220 | Roughin Material | AP | 946 | 03/26/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 12.98 | 032619J | 0 | 0
220 | Roughin Material | AP | 133 | 04/11/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 507.77 | 4265966-00 | 0 | 0
220 | Roughin Material | AP | 323 | 04/18/19 | 05/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 332.1 | 4266292-00 | 0 | 0
220 | Roughin Material | AP | 324 | 04/18/19 | 05/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 54.15 | 4266370-00 | 0 | 0
220 | Roughin Material | AP | 325 | 04/18/19 | 05/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 25.55 | 4266380-00 | 0 | 0
220 | Roughin Material | AP | 340 | 04/19/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 180 | 4266414-00 | 0 | 0
220 | Roughin Material | AP | 752 | 05/06/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 43.12 | 4265966-01 | 0 | 0
220 | Roughin Material | AP | 753 | 05/06/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 346.8 | 4267130-00 | 0 | 0
220 | Roughin Material | AP | 756 | 05/07/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 422.74 | 4267186-00 | 0 | 0
220 | Roughin Material | AP | 769 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 85.26 | 4267265-00 | 0 | 0
220 | Roughin Material | GL | 844 | 05/30/19 | 05/30/19 | Mat | Req 5215 |  |  |  |  | 6345.46 |  | 0 | 0
220 | Roughin Material | GL | 150 | 06/05/19 | 06/05/19 | Mat | Req 6002 |  |  |  |  | 170.52 |  | 0 | 0
220 | Roughin Material | GL | 156 | 06/05/19 | 06/05/19 | Mat | Req 6008 |  |  |  |  | -19.8 |  | 0 | 0
220 | Roughin Material | AP | 275 | 05/17/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 818.93 | 4267556-00 | 0 | 0
220 | Roughin Material | AP | 277 | 05/21/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 107.52 | 4267700-00 | 0 | 0
220 | Roughin Material | AP | 278 | 05/22/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 168.28 | 4267811-00 | 0 | 0
220 | Roughin Material | AP | 279 | 05/22/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 50.94 | 4267867-00 | 0 | 0
220 | Roughin Material | AP | 280 | 05/24/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1159.74 | 4267876-00 | 0 | 0
220 | Roughin Material | AP | 281 | 05/24/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 199.56 | 4267885-00 | 0 | 0
220 | Roughin Material | AP | 302 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 83.5 | 4266370-01 | 0 | 0
220 | Roughin Material | AP | 303 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 14.79 | 4268166-00 | 0 | 0
220 | Roughin Material | AP | 737 | 06/14/19 | 06/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 28 | 4268871-00 | 0 | 0
220 | Roughin Material | GL | 808 | 06/26/19 | 06/26/19 | Mat | Req 6046 |  |  |  |  | 478.7 |  | 0 | 0
220 | Roughin Material | GL | 172 | 07/10/19 | 07/10/19 | Mat | Req 6143 |  |  |  |  | -473.21 |  | 0 | 0
220 | Roughin Material | GL | 173 | 07/10/19 | 07/10/19 | Mat | Req 6142 |  |  |  |  | -805.45 |  | 0 | 0
220 | Roughin Material | GL | 174 | 07/10/19 | 07/10/19 | Mat | Req 6141 |  |  |  |  | -5900.35 |  | 0 | 0
220 | Roughin Material | GL | 205 | 07/10/19 | 07/10/19 | Mat | Req 6109 |  |  |  |  | 241.04 |  | 0 | 0
220 | Roughin Material | AP | 148 | 06/14/19 | 07/19/19 | 1978FC | Fastenal Company |  |  |  |  | 87.66 | WARED110912 | 0 | 0
220 | Roughin Material | AP | 704 | 07/03/19 | 07/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 43.15 | 4269762-00 | 0 | 0
220 | Roughin Material | AP | 705 | 07/10/19 | 07/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 272.97 | 4269974-00 | 0 | 0
220 | Roughin Material | GL | 217 | 08/08/19 | 08/08/19 | Mat | Req 6166 |  |  |  |  | 215.86 |  | 0 | 0
220 | Roughin Material | GL | 730 | 08/20/19 | 08/20/19 | Mat | Req 6223 |  |  |  |  | 154.81 |  | 0 | 0
220 | Roughin Material | GL | 322 | 09/16/19 | 09/16/19 | Mat | Req 6327 |  |  |  |  | 147.72 |  | 0 | 0
220 | Roughin Material | AP | 618 | 09/04/19 | 09/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 27.47 | 4272397-00 | 0 | 0
220 | Roughin Material | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | -2.5 |  | 0 | 0
220 | Roughin Material | GL | 701 | 10/28/19 | 10/28/19 | Mat | Req 6425 |  |  |  |  | -394.03 |  | 0 | 0
220 | Roughin Material | GL | 702 | 10/28/19 | 10/28/19 | Mat | Req 6426 |  |  |  |  | -292.46 |  | 0 | 0
220 | Roughin Material | GL | 144 | 11/05/19 | 11/05/19 | Mat | Req 6476 |  |  |  |  | 341.26 |  | 0 | 0
220 | Roughin Material | GL | 342 | 11/12/19 | 11/12/19 | Mat | Req 6522 |  |  |  |  | -243.25 |  | 0 | 0
220 | Roughin Material | AP | 383 | 10/07/19 | 11/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 42.75 | 4273774-00 | 0 | 0
220 | Roughin Material | AP | 704 | 10/15/19 | 11/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 62.6 | 4274108-00 | 0 | 0
230 | Finish Material | AP | 848 | 04/19/18 | 04/30/18 | 7423OC | Old Castle Infrastructure, Inc. |  |  |  |  | 1971 | 10218939 | 0 | 0
230 | Finish Material | AP | 590 | 04/25/18 | 05/22/18 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 3186 | 16478 | 0 | 0
230 | Finish Material | GL | 339 | 08/10/18 | 08/10/18 | Mat | Req 4572 |  |  |  |  | 834.4 |  | 0 | 0
230 | Finish Material | GL | 362 | 08/10/18 | 08/10/18 | Mat | Req 4539 |  |  |  |  | 208.6 |  | 0 | 0
230 | Finish Material | AP | 466 | 07/19/18 | 08/15/18 | 1231KS | Keller Supply Company |  |  |  |  | 690.86 | S012072694.001 | 0 | 0
230 | Finish Material | AP | 467 | 07/19/18 | 08/15/18 | 1231KS | Keller Supply Company |  |  |  |  | 27.06 | S012072694.002 | 0 | 0
230 | Finish Material | GL | 664 | 08/22/18 | 08/22/18 | Mat | Req 4631 |  |  |  |  | 430.62 |  | 0 | 0
230 | Finish Material | GL | 667 | 08/22/18 | 08/22/18 | Mat | Req 4634 |  |  |  |  | 853.2 |  | 0 | 0
230 | Finish Material | GL | 188 | 09/10/18 | 09/10/18 | Mat | Req 4686 |  |  |  |  | 146.24 |  | 0 | 0
230 | Finish Material | GL | 365 | 10/16/18 | 10/16/18 | Mat | Req 5465 |  |  |  |  | 18.44 |  | 0 | 0
230 | Finish Material | AP | 678 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1072.92 | 4257895-00 | 0 | 0
230 | Finish Material | AP | 131 | 10/09/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 29.94 | 4258390-00 | 0 | 0
230 | Finish Material | AP | 132 | 10/09/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 88.73 | 4258398-00 | 0 | 0
230 | Finish Material | AP | 375 | 10/04/18 | 11/13/18 | 1231KS | Keller Supply Company |  |  |  |  | 912 | S011963305.001 | 0 | 0
230 | Finish Material | AP | 384 | 10/25/18 | 11/13/18 | 1231KS | Keller Supply Company |  |  |  |  | 11977.78 | S012346351.001 | 0 | 0
230 | Finish Material | GL | 746 | 11/26/18 | 11/26/18 | Mat | Req 5529 |  |  |  |  | 313.21 |  | 0 | 0
230 | Finish Material | GL | 995 | 11/30/18 | 11/30/18 | Mat | Req 5576 |  |  |  |  | 1109.16 |  | 0 | 0
230 | Finish Material | AP | 19 | 11/27/18 | 12/05/18 | 1231KS | Keller Supply Company |  |  |  |  | 6.42 | S012517060.001 | 0 | 0
230 | Finish Material | AP | 368 | 11/21/18 | 12/14/18 | 1231KS | Keller Supply Company |  |  |  |  | 11977.78 | S012346175.001 | 0 | 0
230 | Finish Material | AP | 412 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4410.53 | 4253136-00 | 0 | 0
230 | Finish Material | GL | 630 | 12/21/18 | 12/21/18 | Mat | Req 5606 |  |  |  |  | 527.76 |  | 0 | 0
230 | Finish Material | AP | 170 | 11/28/18 | 01/08/19 | 1231KS | Keller Supply Company |  |  |  |  | 11977.78 | S012346225.001 | 0 | 0
230 | Finish Material | AP | 190 | 12/05/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 6136.41 | S012331656.001 | 0 | 0
230 | Finish Material | AP | 191 | 12/07/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 331.66 | S012346175.003 | 0 | 0
230 | Finish Material | AP | 192 | 12/07/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 12641.1 | S012346209.001 | 0 | 0
230 | Finish Material | AP | 193 | 12/07/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 663.33 | S012346225.003 | 0 | 0
230 | Finish Material | GL | 321 | 01/11/19 | 01/11/19 | Mat | Req 4871 |  |  |  |  | 586.4 |  | 0 | 0
230 | Finish Material | GL | 427 | 01/15/19 | 01/15/19 | Mat | Req 4923 |  |  |  |  | 903 |  | 0 | 0
230 | Finish Material | AP | 445 | 12/20/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 12754.83 | S012346057.001 | 0 | 0
230 | Finish Material | AP | 627 | 12/17/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -137.4 | 4261324-00 | 0 | 0
230 | Finish Material | GL | 864 | 01/30/19 | 01/30/19 | Mat | Req 5674 |  |  |  |  | 5906.1 |  | 0 | 0
230 | Finish Material | GL | 148 | 03/04/19 | 03/04/19 | Mat | Req 5046 |  |  |  |  | -7.5 |  | 0 | 0
230 | Finish Material | GL | 186 | 03/04/19 | 03/04/19 | Mat | Req 5694 |  |  |  |  | 861 |  | 0 | 0
230 | Finish Material | GL | 360 | 03/08/19 | 03/08/19 | Mat | Req 5023 |  |  |  |  | 1898.2 |  | 0 | 0
230 | Finish Material | GL | 598 | 03/15/19 | 03/15/19 | Mat | Req 5807 |  |  |  |  | 463.34 |  | 0 | 0
230 | Finish Material | GL | 618 | 03/15/19 | 03/15/19 | Mat | Req 5066 |  |  |  |  | -445.76 |  | 0 | 0
230 | Finish Material | GL | 827 | 03/25/19 | 03/25/19 | Mat | Req 5089 |  |  |  |  | 861 |  | 0 | 0
230 | Finish Material | AP | 234 | 04/04/19 | 04/03/19 | 5560CH | California Hydronics Corp |  |  |  |  | 365.56 | SIN013439 | 0 | 0
230 | Finish Material | AP | 181 | 03/28/19 | 04/06/19 | 5560CH | California Hydronics Corp |  |  |  |  | 1685 | SIN012773 | 0 | 0
230 | Finish Material | GL | 194 | 04/08/19 | 04/08/19 | Mat | Req 5866 |  |  |  |  | 1581.09 |  | 0 | 0
230 | Finish Material | AP | 307 | 04/09/19 | 04/10/19 | 5560CH | California Hydronics Corp |  |  |  |  | -55.56 | SCR000544 | 0 | 0
230 | Finish Material | GL | 430 | 04/12/19 | 04/12/19 | Mat | Req 5146 |  |  |  |  | 1521.36 |  | 0 | 0
230 | Finish Material | AP | 877 | 04/19/19 | 04/30/19 | 5560CH | California Hydronics Corp |  |  |  |  | 2685 | SIN014918 | 0 | 0
230 | Finish Material | GL | 881 | 04/30/19 | 04/30/19 | Mat | Req 5176 |  |  |  |  | 420 |  | 0 | 0
230 | Finish Material | AP | 97 | 04/15/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 211.39 | 7122885 | 0 | 0
230 | Finish Material | AP | 564 | 05/14/19 | 05/20/19 | 5560CH | California Hydronics Corp |  |  |  |  | 15456.86 | SIN016965 | 0 | 0
230 | Finish Material | AP | 565 | 05/17/19 | 05/20/19 | 5560CH | California Hydronics Corp |  |  |  |  | -171.86 | SCR00828 | 0 | 0
230 | Finish Material | GL | 709 | 05/23/19 | 05/23/19 | 1380RS | Inv 4265063-00 |  |  |  |  | 1069.5 |  | 0 | 0
230 | Finish Material | GL | 848 | 05/30/19 | 05/30/19 | Mat | Req 5219 |  |  |  |  | 386.75 |  | 0 | 0
230 | Finish Material | GL | 152 | 06/05/19 | 06/05/19 | Mat | Req 6004 |  |  |  |  | 318.41 |  | 0 | 0
230 | Finish Material | GL | 155 | 06/05/19 | 06/05/19 | Mat | Req 6007 |  |  |  |  | -167 |  | 0 | 0
230 | Finish Material | AP | 386 | 05/30/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 308.65 | S012841186.001 | 0 | 0
230 | Finish Material | AP | 421 | 06/04/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 11242.99 | 6496038 | 0 | 0
230 | Finish Material | AP | 439 | 06/03/19 | 06/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 138.12 | 4268220-00 | 0 | 0
230 | Finish Material | AP | 440 | 06/03/19 | 06/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1376.38 | 4268279-00 | 0 | 0
230 | Finish Material | AP | 583 | 06/11/19 | 06/17/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 11605.67 | 6496034 | 0 | 0
230 | Finish Material | AP | 584 | 06/12/19 | 06/17/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 318 | 7288033 | 0 | 0
230 | Finish Material | AP | 588 | 06/12/19 | 06/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 1603.86 | S013107974.001 | 0 | 0
230 | Finish Material | AP | 590 | 06/12/19 | 06/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 3892.06 | S01241186.002 | 0 | 0
230 | Finish Material | AP | 591 | 06/17/19 | 06/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 10979.2 | S012966625.001 | 0 | 0
230 | Finish Material | AP | 710 | 06/13/19 | 06/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 144 | 4268279-01 | 0 | 0
230 | Finish Material | AP | 736 | 06/14/19 | 06/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 277.03 | 4268866-00 | 0 | 0
230 | Finish Material | AP | 738 | 06/17/19 | 06/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 122.64 | 4268927-00 | 0 | 0
230 | Finish Material | AP | 767 | 06/20/19 | 06/24/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 11605.67 | 6496022 | 0 | 0
230 | Finish Material | AP | 768 | 06/21/19 | 06/24/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -318 | CM782784 | 0 | 0
230 | Finish Material | GL | 801 | 06/26/19 | 06/26/19 | Mat | Req 6074 |  |  |  |  | -95.69 |  | 0 | 0
230 | Finish Material | GL | 825 | 06/26/19 | 06/26/19 | Mat | Req 6045 |  |  |  |  | 1482.15 |  | 0 | 0
230 | Finish Material | GL | 143 | 07/09/19 | 07/09/19 | Mat | Req 6107 |  |  |  |  | 1393.6 |  | 0 | 0
230 | Finish Material | GL | 206 | 07/10/19 | 07/10/19 | Mat | Req 6108 |  |  |  |  | 1094.57 |  | 0 | 0
230 | Finish Material | AP | 265 | 06/20/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 193 | 4269150-00 | 0 | 0
230 | Finish Material | AP | 269 | 06/18/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 108.38 | 4268990-00 | 0 | 0
230 | Finish Material | AP | 270 | 06/19/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 77.95 | 4269056-00 | 0 | 0
230 | Finish Material | AP | 395 | 06/21/19 | 07/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 20.8 | 4269224-00 | 0 | 0
230 | Finish Material | AP | 435 | 06/26/19 | 07/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 123.3 | 4269445-00 | 0 | 0
230 | Finish Material | AP | 473 | 07/11/19 | 07/16/19 | 1231KS | Keller Supply Company |  |  |  |  | 3832.37 | S012841186.003 | 0 | 0
230 | Finish Material | AP | 732 | 07/18/19 | 07/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 11273.61 | S012966601.001 | 0 | 0
230 | Finish Material | AP | 161 | 07/17/19 | 08/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 11928.76 | 6496050 | 0 | 0
230 | Finish Material | AP | 163 | 07/25/19 | 08/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 12241.41 | 6496043 | 0 | 0
230 | Finish Material | AP | 195 | 07/18/19 | 08/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 144 | 4268279-03 | 0 | 0
230 | Finish Material | GL | 216 | 08/08/19 | 08/08/19 | Mat | Req 6165 |  |  |  |  | 363.53 |  | 0 | 0
230 | Finish Material | AP | 468 | 07/24/19 | 08/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 90 | 4270536-00 | 0 | 0
230 | Finish Material | AP | 521 | 07/26/19 | 08/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 8.09 | 6496043-1 | 0 | 0
230 | Finish Material | AP | 555 | 07/30/19 | 08/14/19 | 1231KS | Keller Supply Company |  |  |  |  | 3832.37 | S012841186.004 | 0 | 0
230 | Finish Material | AP | 556 | 08/02/19 | 08/14/19 | 1231KS | Keller Supply Company |  |  |  |  | 7779.14 | S012841186.005 | 0 | 0
230 | Finish Material | GL | 682 | 08/20/19 | 08/20/19 | Mat | Req 6262 |  |  |  |  | 108.68 |  | 0 | 0
230 | Finish Material | GL | 699 | 08/20/19 | 08/20/19 | Mat | Req 6265 |  |  |  |  | -442.26 |  | 0 | 0
230 | Finish Material | GL | 729 | 08/20/19 | 08/20/19 | Mat | Req 6222 |  |  |  |  | 1237.72 |  | 0 | 0
230 | Finish Material | AP | 787 | 08/12/19 | 08/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 11351.38 | S012966575.001 | 0 | 0
230 | Finish Material | AP | 955 | 08/01/19 | 08/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 77.8 | 4270918-00 | 0 | 0
230 | Finish Material | AP | 975 | 08/09/19 | 08/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 14.13 | 4271278-00 | 0 | 0
230 | Finish Material | AP | 1129 | 08/15/19 | 08/31/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -511.2 | CM799447 | 0 | 0
230 | Finish Material | AP | 1134 | 08/16/19 | 08/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 868.04 | S013341722.001 | 0 | 0
230 | Finish Material | AP | 1135 | 08/20/19 | 08/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 11342.1 | S012966164.001 | 0 | 0
230 | Finish Material | AP | 123 | 08/23/19 | 09/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 329.16 | 4271898-00 | 0 | 0
230 | Finish Material | GL | 361 | 09/16/19 | 09/16/19 | Mat | Req 6326 |  |  |  |  | 1643.01 |  | 0 | 0
230 | Finish Material | AP | 434 | 08/30/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 14172.7 | S012966086.001 | 0 | 0
230 | Finish Material | AP | 435 | 09/10/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 6632.93 | S012832761.001 | 0 | 0
230 | Finish Material | AP | 721 | 09/09/19 | 09/27/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 76.9 | 4272580-00 | 0 | 0
230 | Finish Material | AP | 133 | 09/17/19 | 10/07/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 66.44 | 4272718-00 | 0 | 0
230 | Finish Material | AP | 386 | 09/24/19 | 10/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 120.45 | S013468130.001 | 0 | 0
230 | Finish Material | GL | 395 | 10/15/19 | 10/15/19 | Mat | Req 6401 |  |  |  |  | -20.7 |  | 0 | 0
230 | Finish Material | AP | 417 | 09/19/19 | 10/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 16.85 | 4272955-00 | 0 | 0
230 | Finish Material | AP | 765 | 10/01/19 | 10/25/19 | 1231KS | Keller Supply Company |  |  |  |  | 80 | S013501825.001 | 0 | 0
230 | Finish Material | AP | 766 | 10/03/19 | 10/25/19 | 1231KS | Keller Supply Company |  |  |  |  | 86.8 | S013501934.001 | 0 | 0
230 | Finish Material | GL | 688 | 10/28/19 | 10/28/19 | Mat | Req 6422 |  |  |  |  | -606.37 |  | 0 | 0
230 | Finish Material | GL | 699 | 10/28/19 | 10/28/19 | Mat | Req 6428 |  |  |  |  | -373.63 |  | 0 | 0
230 | Finish Material | AP | 97 | 10/11/19 | 11/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 749.87 | S013460813.001 | 0 | 0
230 | Finish Material | AP | 101 | 10/03/19 | 11/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 139.37 | S013501825.002 | 0 | 0
230 | Finish Material | AP | 102 | 10/11/19 | 11/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 33.63 | S013536593.001 | 0 | 0
230 | Finish Material | GL | 146 | 11/05/19 | 11/05/19 | Mat | Req 6475 |  |  |  |  | 50.7 |  | 0 | 0
230 | Finish Material | GL | 147 | 11/05/19 | 11/05/19 | Mat | Req 6474 |  |  |  |  | 2049.38 |  | 0 | 0
230 | Finish Material | AP | 167 | 10/16/19 | 11/06/19 | 1231KS | Keller Supply Company |  |  |  |  | 681.58 | S013545637.001 | 0 | 0
230 | Finish Material | GL | 343 | 11/12/19 | 11/12/19 | Mat | Req 6521 |  |  |  |  | -783.15 |  | 0 | 0
230 | Finish Material | AP | 378 | 10/23/19 | 11/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 599.22 | S013568790.001 | 0 | 0
230 | Finish Material | AP | 379 | 10/25/19 | 11/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 191.31 | S013501825.003 | 0 | 0
230 | Finish Material | GL | 418 | 11/13/19 | 11/13/19 | Mat | Req 6538 |  |  |  |  | 659.61 |  | 0 | 0
230 | Finish Material | AP | 774 | 10/17/19 | 11/21/19 | 1234CO | Capital One Credit Card |  |  |  |  | 14.09 | 101719A | 0 | 0
230 | Finish Material | AP | 775 | 10/29/19 | 11/21/19 | 1234CO | Capital One Credit Card |  |  |  |  | 42.15 | 102919A | 0 | 0
230 | Finish Material | AP | 978 | 10/30/19 | 11/30/19 | 1231KS | Keller Supply Company |  |  |  |  | 194.53 | S012966625.002 | 0 | 0
230 | Finish Material | AP | 13 | 10/29/19 | 12/03/19 | 1231KS | Keller Supply Company |  |  |  |  | 105.3 | S013560334.001 | 0 | 0
230 | Finish Material | AP | 535 | 01/09/20 | 01/13/20 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -318 | CM779384 | 0 | 0
230 | Finish Material | AP | 661 | 01/17/20 | 01/20/20 | 5560CH | California Hydronics Corp |  |  |  |  | 11816 | SIN041595 | 0 | 0
230 | Finish Material | AP | 624 | 02/13/20 | 02/26/20 | 1231KS | Keller Supply Company |  |  |  |  | 36.64 | S013460813.002 | 0 | 0
240 | Gas Material | GL | 629 | 12/21/18 | 12/21/18 | Mat | Req 5607 |  |  |  |  | 1.98 |  | 0 | 0
240 | Gas Material | AP | 770 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 110.39 | 4267298-00 | 0 | 0
240 | Gas Material | AP | 91 | 05/16/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 90.22 | 7214740 | 0 | 0
240 | Gas Material | GL | 154 | 06/05/19 | 06/05/19 | Mat | Req 6006 |  |  |  |  | -13.95 |  | 0 | 0
240 | Gas Material | AP | 276 | 05/17/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.42 | 4267640-00 | 0 | 0
240 | Gas Material | GL | 697 | 10/28/19 | 10/28/19 | Mat | Req 6427 |  |  |  |  | -133.34 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 356 | 08/10/18 | 08/10/18 | Mat | Req 4554 |  |  |  |  | 383.26 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 180 | 10/10/18 | 10/10/18 | Mat | Req 5459 |  |  |  |  | -96.5 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 739 | 11/26/18 | 11/26/18 | Mat | Req 4820 |  |  |  |  | 2730.15 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 127 | 12/17/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2256.79 | S9057763.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 128 | 12/18/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 779.08 | S9061023.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 140 | 12/11/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4257.68 | 6789523 | 0 | 0
241 | Water Main/Insulation Mat | GL | 352 | 01/11/19 | 01/11/19 | Mat | Req 4920 |  |  |  |  | 288.1 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 353 | 01/11/19 | 01/11/19 | Mat | Req 4919 |  |  |  |  | 3979.46 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 103 | 01/21/19 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 596.72 | S9102805.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 517 | 02/14/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3978.68 | S9126298.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 526 | 01/26/19 | 02/19/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4310.17 | 6693554 | 0 | 0
241 | Water Main/Insulation Mat | AP | 527 | 02/01/19 | 02/19/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 668.91 | 6924409 | 0 | 0
241 | Water Main/Insulation Mat | AP | 528 | 02/07/19 | 02/19/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 445.94 | 6924409-1 | 0 | 0
241 | Water Main/Insulation Mat | AP | 529 | 02/07/19 | 02/19/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 718.88 | 6941804 | 0 | 0
241 | Water Main/Insulation Mat | AP | 554 | 02/12/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 65.62 | 4924409-2 | 0 | 0
241 | Water Main/Insulation Mat | AP | 555 | 02/12/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1526.88 | 6941804-1 | 0 | 0
241 | Water Main/Insulation Mat | AP | 556 | 02/13/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 262.48 | 6924409-3 | 0 | 0
241 | Water Main/Insulation Mat | GL | 144 | 03/04/19 | 03/04/19 | Mat | Req 5051 |  |  |  |  | 1657.87 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 185 | 03/04/19 | 03/04/19 | Mat | Req 5695 |  |  |  |  | 432.4 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 224 | 02/18/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 287.82 | S9138474.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 225 | 02/19/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2319.85 | S9138474.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 226 | 02/19/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 18.51 | S9139968.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 227 | 02/19/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 127.31 | S9140053.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 232 | 02/14/19 | 03/06/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 23.5 | 4263438-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 236 | 02/20/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 327.99 | 6969388 | 0 | 0
241 | Water Main/Insulation Mat | AP | 237 | 02/25/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1333.58 | 6986311 | 0 | 0
241 | Water Main/Insulation Mat | GL | 358 | 03/08/19 | 03/08/19 | Mat | Req 5029 |  |  |  |  | 831.62 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 404 | 02/18/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 17 | 4263552-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 441 | 02/27/19 | 03/13/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 7408.19 | S9146888.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 442 | 02/27/19 | 03/13/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 600.32 | S9146888.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 448 | 02/26/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1185.5 | 6986317 | 0 | 0
241 | Water Main/Insulation Mat | AP | 449 | 02/28/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -990.7 | CM745607 | 0 | 0
241 | Water Main/Insulation Mat | AP | 450 | 02/28/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 126.55 | 6996563 | 0 | 0
241 | Water Main/Insulation Mat | AP | 457 | 03/01/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 579.56 | 6996563-1 | 0 | 0
241 | Water Main/Insulation Mat | AP | 458 | 03/07/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 842.93 | 7017358 | 0 | 0
241 | Water Main/Insulation Mat | GL | 597 | 03/15/19 | 03/15/19 | Mat | Req 5808 |  |  |  |  | 232 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 658 | 03/05/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 258 | 4264015-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 864 | 03/14/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4226.02 | S9168537.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 865 | 03/18/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 314.86 | S9174515.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 895 | 03/09/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 146.99 | 7017358-1 | 0 | 0
241 | Water Main/Insulation Mat | AP | 896 | 03/11/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -342.88 | CM748998 | 0 | 0
241 | Water Main/Insulation Mat | AP | 897 | 03/19/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 231.28 | 7044031 | 0 | 0
241 | Water Main/Insulation Mat | AP | 898 | 03/20/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 139.36 | 7044031-1 | 0 | 0
241 | Water Main/Insulation Mat | GL | 1060 | 03/28/19 | 03/28/19 | Mat | Req 5836 |  |  |  |  | 1339.7 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 160 | 03/20/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 917.58 | S9175792.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 161 | 03/20/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1042.32 | S9176639.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 162 | 03/20/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1886.56 | S9178712.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 163 | 03/22/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 383.56 | S9179985.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 193 | 04/08/19 | 04/08/19 | Mat | Req 5865 |  |  |  |  | 2918.22 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 246 | 03/22/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 151.7 | 4265135-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 428 | 04/12/19 | 04/12/19 | Mat | Req 5148 |  |  |  |  | 1956.96 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 456 | 03/26/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 119.32 | S9183229.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 457 | 03/28/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 913.12 | S9188026.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 458 | 03/28/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 94.71 | S9188026.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 503 | 03/26/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 838.5 | 4264145-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 635 | 04/04/19 | 04/22/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 306.8 | S9190009.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 643 | 03/29/19 | 04/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1069.5 | 4265063-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 708 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 282.79 | 4265788-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 725 | 04/10/19 | 04/24/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 150.68 | S9168537.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 912 | 04/30/19 | 04/30/19 | Mat | Req 5180 |  |  |  |  | -128.07 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 913 | 04/30/19 | 04/30/19 | Mat | Req 5179 |  |  |  |  | -143.8 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 919 | 04/16/19 | 04/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 231.6 | S9190009.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 934 | 04/09/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -27.95 | CM758112 | 0 | 0
241 | Water Main/Insulation Mat | AP | 126 | 04/15/19 | 05/02/19 | 1231KS | Keller Supply Company |  |  |  |  | 7.85 | S012913809.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 98 | 04/16/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1158.07 | 7125980 | 0 | 0
241 | Water Main/Insulation Mat | AP | 344 | 04/22/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 443.8 | 4266491-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 846 | 05/30/19 | 05/30/19 | Mat | Req 5217 |  |  |  |  | 167.33 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 153 | 06/05/19 | 06/05/19 | Mat | Req 6005 |  |  |  |  | -103 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 403 | 05/31/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 140.81 | S9282523.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 420 | 05/30/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 28.8 | 7251454 | 0 | 0
241 | Water Main/Insulation Mat | AP | 572 | 06/14/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 195.58 | S009306029.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 821 | 06/26/19 | 06/26/19 | Mat | Req 6031 |  |  |  |  | -23.6 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 824 | 06/26/19 | 06/26/19 | Mat | Req 6047 |  |  |  |  | 247.52 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 203 | 07/10/19 | 07/10/19 | Mat | Req 6111 |  |  |  |  | 41.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 149 | 07/18/19 | 08/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 40.48 | S09354529.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 220 | 08/08/19 | 08/08/19 | Mat | Req 6169 |  |  |  |  | 36 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 677 | 08/20/19 | 08/20/19 | Mat | Req 6272 |  |  |  |  | -671.24 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 727 | 08/20/19 | 08/20/19 | Mat | Req 6225 |  |  |  |  | 147.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 462 | 08/30/19 | 09/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 112.2 | S009417397.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 463 | 09/03/19 | 09/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 112.2 | S009417397.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 551 | 09/03/19 | 09/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | -112.2 | S009417397.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 396 | 10/15/19 | 10/15/19 | Mat | Req 6400 |  |  |  |  | -276.38 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 700 | 10/28/19 | 10/28/19 | Mat | Req 6424 |  |  |  |  | -357.79 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 145 | 11/05/19 | 11/05/19 | Mat | Req 6477 |  |  |  |  | 78.07 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 417 | 11/13/19 | 11/13/19 | Mat | Req 6539 |  |  |  |  | 38.55 |  | 0 | 0
242 | Mech Room Material | AP | 396 | 09/16/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 168.02 | 4257280-00 | 0 | 0
242 | Mech Room Material | AP | 121 | 01/22/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 627.24 | 6892617 | 0 | 0
242 | Mech Room Material | AP | 122 | 01/22/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1268.37 | 6892617-1 | 0 | 0
242 | Mech Room Material | GL | 615 | 03/15/19 | 03/15/19 | Mat | Req 5068 |  |  |  |  | 232.71 |  | 0 | 0
242 | Mech Room Material | GL | 829 | 03/25/19 | 03/25/19 | Mat | Req 5087 |  |  |  |  | 559.9 |  | 0 | 0
242 | Mech Room Material | GL | 1064 | 03/28/19 | 03/28/19 | Mat | Req 5853 |  |  |  |  | -2652 |  | 0 | 0
242 | Mech Room Material | GL | 195 | 04/08/19 | 04/08/19 | Mat | Req 5867 |  |  |  |  | 204.28 |  | 0 | 0
242 | Mech Room Material | GL | 692 | 04/24/19 | 04/24/19 | Mat | Req 5903 |  |  |  |  | 19.7 |  | 0 | 0
242 | Mech Room Material | GL | 709 | 05/23/19 | 05/23/19 | 1380RS | Inv 4265063-00 |  |  |  |  | -1069.5 |  | 0 | 0
242 | Mech Room Material | AP | 90 | 05/15/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 84.25 | 72037706 | 0 | 0
242 | Mech Room Material | AP | 92 | 05/24/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 937.41 | 7227919 | 0 | 0
242 | Mech Room Material | GL | 136 | 06/05/19 | 06/05/19 | Mat | Req 6022 |  |  |  |  | -791.24 |  | 0 | 0
242 | Mech Room Material | AP | 368 | 05/24/19 | 06/11/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 3258.91 | 7232936 | 0 | 0
242 | Mech Room Material | AP | 402 | 05/31/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1060.48 | S9279731.001 | 0 | 0
242 | Mech Room Material | AP | 418 | 06/04/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 24.63 | 7263308 | 0 | 0
242 | Mech Room Material | AP | 558 | 06/06/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 58.14 | S9279731.003 | 0 | 0
242 | Mech Room Material | AP | 95 | 06/27/19 | 07/02/19 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 175 | K766603 | 0 | 0
242 | Mech Room Material | GL | 202 | 07/10/19 | 07/10/19 | Mat | Req 6110 |  |  |  |  | 708.13 |  | 0 | 0
242 | Mech Room Material | AP | 385 | 06/24/19 | 07/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1055.1 | 7320852 | 0 | 0
242 | Mech Room Material | AP | 396 | 06/24/19 | 07/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 389.59 | 4269262-00 | 0 | 0
242 | Mech Room Material | AP | 453 | 06/27/19 | 07/16/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 550.45 | S009325453.001 | 0 | 0
242 | Mech Room Material | AP | 101 | 07/09/19 | 08/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 190.9 | S009325453.002 | 0 | 0
242 | Mech Room Material | AP | 162 | 07/24/19 | 08/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 112.05 | 7403926 | 0 | 0
242 | Mech Room Material | GL | 218 | 08/08/19 | 08/08/19 | Mat | Req 6167 |  |  |  |  | 70.68 |  | 0 | 0
242 | Mech Room Material | GL | 676 | 08/20/19 | 08/20/19 | Mat | Req 6274 |  |  |  |  | -45.15 |  | 0 | 0
242 | Mech Room Material | GL | 728 | 08/20/19 | 08/20/19 | Mat | Req 6224 |  |  |  |  | 228.2 |  | 0 | 0
242 | Mech Room Material | GL | 696 | 10/28/19 | 10/28/19 | Mat | Req 6429 |  |  |  |  | -325.25 |  | 0 | 0
243 | Condensation Drains Mat | GL | 847 | 05/30/19 | 05/30/19 | Mat | Req 5218 |  |  |  |  | 2.55 |  | 0 | 0
243 | Condensation Drains Mat | GL | 816 | 06/26/19 | 06/26/19 | Mat | Req 6032 |  |  |  |  | -5.05 |  | 0 | 0
243 | Condensation Drains Mat | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | 2.5 |  | 0 | 0
600 | Subcontractor | AP | 197 | 07/31/18 | 08/08/18 | 3181SC | Scan2Core, Inc. |  |  |  |  | 280 | 71804 | 0 | 0
600 | Subcontractor | AP | 973 | 08/14/18 | 08/29/18 | 3181SC | Scan2Core, Inc. |  |  |  |  | 830 | 71855B | 0 | 0
600 | Subcontractor | AP | 975 | 08/13/18 | 08/29/18 | 3181SC | Scan2Core, Inc. |  |  |  |  | 822 | 71853B | 0 | 0
600 | Subcontractor | AP | 154 | 01/30/19 | 02/01/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 615 | 013019 | 0 | 0
600 | Subcontractor | AP | 738 | 01/30/19 | 02/27/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 615 | 72409 | 0 | 0
600 | Subcontractor | AP | 1124 | 08/26/19 | 08/31/19 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 200 | 19082601 | 0 | 0
600 | Subcontractor | AP | 417 | 09/05/19 | 09/17/19 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 50 | 19090504 | 0 | 0
601 | Engineering/Plans | AP | 541 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 4019.5 | 6737 | 0 | 0
601 | Engineering/Plans | AP | 108 | 12/19/17 | 01/05/18 | 1625FE | Franklin Engineering |  |  |  |  | 5896.25 | 6772 | 0 | 0
601 | Engineering/Plans | AP | 581 | 01/19/18 | 01/24/18 | 1625FE | Franklin Engineering |  |  |  |  | 303 | 6814 | 0 | 0
601 | Engineering/Plans | AP | 745 | 02/20/18 | 02/27/18 | 1625FE | Franklin Engineering |  |  |  |  | 5859.5 | 6840 | 0 | 0
602 | Rental Equipment | AP | 634 | 10/02/18 | 10/16/18 | 2713AR | Ahern Rentals |  |  |  |  | 519.75 | 19574763-1 | 0 | 0
602 | Rental Equipment | AP | 809 | 11/01/18 | 11/28/18 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-2 | 0 | 0
602 | Rental Equipment | AP | 153 | 11/27/18 | 01/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-3 | 0 | 0
602 | Rental Equipment | AP | 158 | 12/25/18 | 01/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-4 | 0 | 0
602 | Rental Equipment | AP | 139 | 01/22/19 | 02/01/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-5 | 0 | 0
602 | Rental Equipment | AP | 205 | 02/19/19 | 03/05/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-006 | 0 | 0
602 | Rental Equipment | AP | 11 | 03/19/19 | 04/02/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-007 | 0 | 0
602 | Rental Equipment | AP | 838 | 04/16/19 | 04/26/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-008 | 0 | 0
602 | Rental Equipment | AP | 787 | 05/14/19 | 05/29/19 | 2713AR | Ahern Rentals |  |  |  |  | 409.75 | 19574763-009 | 0 | 0
602 | Rental Equipment | AP | 364 | 06/05/19 | 06/10/19 | 2713AR | Ahern Rentals |  |  |  |  | 110 | 19574763-010 | 0 | 0
602 | Rental Equipment | AP | 109 | 06/28/19 | 07/30/19 | 2713AR | Ahern Rentals |  |  |  |  | 891.16 | 20668182-001 | 0 | 0
602 | Rental Equipment | AP | 457 | 09/26/19 | 01/10/20 | 1799AW | AllWest Underground, Inc. |  |  |  |  | 199.24 | 87689 | 0 | 0
607 | Other Expenses | AP | 296 | 09/13/17 | 09/13/17 | 1234CO | Capital One Credit Card |  |  |  |  | 99 | 20170913 | 0 | 0
607 | Other Expenses | AP | 482 | 01/08/18 | 01/19/18 | 3018TR | Travelers |  |  |  |  | 445 | 20180108 | 0 | 0
607 | Other Expenses | AP | 1096 | 08/16/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 108.9 | 081618B1 | 0 | 0
995 | Payroll Burden | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 10/04/17 | 10/06/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 10/11/17 | 10/13/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 11/01/17 | 11/03/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 12/13/17 | 12/15/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 691 | 06/20/18 | 06/22/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 68.3 |  | 0 | 0
995 | Payroll Burden | PR | 694 | 06/20/18 | 06/22/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 92.69 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 962 | 06/27/18 | 06/29/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 168.53 |  | 0 | 0
995 | Payroll Burden | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 389.17 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -28.38 |  | 0 | 0
995 | Payroll Burden | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 299.36 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 07/04/18 | 07/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 101.12 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 07/04/18 | 07/06/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 07/04/18 | 07/06/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 306 | 07/11/18 | 07/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 07/11/18 | 07/13/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 348 | 07/11/18 | 07/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 578.77 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 446 | 07/18/18 | 07/20/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 07/18/18 | 07/20/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 07/18/18 | 07/20/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 08/01/18 | 08/03/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 08/01/18 | 08/03/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 53.89 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 798.3 |  | 0 | 0
995 | Payroll Burden | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 692 | 09/26/18 | 09/28/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 727 | 09/26/18 | 09/28/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 543.29 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 179.62 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 10/03/18 | 10/05/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 10/10/18 | 10/12/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 10/10/18 | 10/12/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 465.68 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 10/10/18 | 10/12/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 10/17/18 | 10/19/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 10/17/18 | 10/19/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 280.51 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 10/17/18 | 10/19/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 10/17/18 | 10/19/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 727 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 10/24/18 | 10/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 82.49 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 434.63 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 543.29 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 10/31/18 | 11/02/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 343.71 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 10/31/18 | 11/02/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 527.77 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 11/07/18 | 11/09/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 11/07/18 | 11/09/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 384.96 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 543.29 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 89.81 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.43 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | -122.41 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | -408.02 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -199.58 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 11/21/18 | 11/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 634 | 11/21/18 | 11/21/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 11/21/18 | 11/21/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 421.33 |  | 0 | 0
995 | Payroll Burden | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 527.77 |  | 0 | 0
995 | Payroll Burden | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 11/21/18 | 11/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 455.03 |  | 0 | 0
995 | Payroll Burden | PR | 671 | 11/21/18 | 11/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 675 | 11/21/18 | 11/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 522.44 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -79.83 |  | 0 | 0
995 | Payroll Burden | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 837 | 11/28/18 | 11/30/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 845 | 11/28/18 | 11/30/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 260.11 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 11/28/18 | 11/30/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 382.52 |  | 0 | 0
995 | Payroll Burden | PR | 852 | 11/28/18 | 11/30/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 413.12 |  | 0 | 0
995 | Payroll Burden | PR | 855 | 11/28/18 | 11/30/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 566.13 |  | 0 | 0
995 | Payroll Burden | PR | 877 | 11/28/18 | 11/30/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 333.51 |  | 0 | 0
995 | Payroll Burden | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 884 | 11/28/18 | 11/30/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 260.11 |  | 0 | 0
995 | Payroll Burden | PR | 888 | 11/28/18 | 11/30/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 333.51 |  | 0 | 0
995 | Payroll Burden | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 623.56 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 270.98 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 93.8 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 96 | 12/05/18 | 12/07/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 286.5 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | -638.64 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 12/12/18 | 12/14/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 286.5 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 172.3 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 24.61 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 12/12/18 | 12/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 360.12 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 136.6 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 12/12/18 | 12/14/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 331.74 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 12/19/18 | 12/21/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 12/19/18 | 12/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 598.95 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 12/19/18 | 12/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 194.03 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 554 | 12/19/18 | 12/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 422.21 |  | 0 | 0
995 | Payroll Burden | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 331.74 |  | 0 | 0
995 | Payroll Burden | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 624.45 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 12/26/18 | 12/28/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 230.62 |  | 0 | 0
995 | Payroll Burden | PR | 715 | 12/26/18 | 12/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 288.28 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 12/26/18 | 12/28/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 262.55 |  | 0 | 0
995 | Payroll Burden | PR | 726 | 12/26/18 | 12/28/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 135.71 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 12/26/18 | 12/28/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 12/26/18 | 12/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 752 | 12/26/18 | 12/28/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 196.03 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 12/26/18 | 12/28/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | -212.88 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 01/02/19 | 01/04/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 01/02/19 | 01/04/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 01/02/19 | 01/04/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 164.1 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 01/02/19 | 01/04/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 01/02/19 | 01/04/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 01/02/19 | 01/04/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 329.08 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 01/02/19 | 01/04/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 211.11 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 01/02/19 | 01/04/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 01/09/19 | 01/11/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 228 | 01/09/19 | 01/11/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 233 | 01/09/19 | 01/11/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 01/09/19 | 01/11/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 01/09/19 | 01/11/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 01/09/19 | 01/11/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 01/09/19 | 01/11/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 01/09/19 | 01/11/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 01/09/19 | 01/11/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 01/09/19 | 01/11/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 432.86 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 474 | 01/16/19 | 01/18/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 01/16/19 | 01/18/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 01/16/19 | 01/18/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 01/16/19 | 01/18/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 615.36 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 01/16/19 | 01/18/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 01/16/19 | 01/18/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 01/16/19 | 01/18/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -93.8 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 166.76 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 01/16/19 | 01/18/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 01/16/19 | 01/18/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 01/23/19 | 01/25/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 737 | 01/23/19 | 01/25/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 01/23/19 | 01/25/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 01/23/19 | 01/25/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 01/23/19 | 01/25/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 415.78 |  | 0 | 0
995 | Payroll Burden | PR | 761 | 01/23/19 | 01/25/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 01/23/19 | 01/25/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 15.97 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 01/30/19 | 02/01/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 01/30/19 | 02/01/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 01/30/19 | 02/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 01/30/19 | 02/01/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 631.77 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 01/30/19 | 02/01/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 01/30/19 | 02/01/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 01/30/19 | 02/01/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 01/30/19 | 02/01/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 166 | 02/06/19 | 02/08/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 175 | 02/06/19 | 02/08/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 180 | 02/06/19 | 02/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 02/06/19 | 02/08/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 190 | 02/06/19 | 02/08/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 196 | 02/06/19 | 02/08/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 203 | 02/06/19 | 02/08/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 208 | 02/06/19 | 02/08/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 02/06/19 | 02/08/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 02/13/19 | 02/15/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 02/13/19 | 02/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 342 | 02/13/19 | 02/15/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 345 | 02/13/19 | 02/15/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 352 | 02/13/19 | 02/15/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 357 | 02/13/19 | 02/15/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 358 | 02/13/19 | 02/15/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 365 | 02/13/19 | 02/15/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 173.85 |  | 0 | 0
995 | Payroll Burden | PR | 372 | 02/13/19 | 02/15/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 147.02 |  | 0 | 0
995 | Payroll Burden | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 595 | 02/20/19 | 02/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 600 | 02/20/19 | 02/22/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 670.57 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 02/20/19 | 02/22/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 754.84 |  | 0 | 0
995 | Payroll Burden | PR | 610 | 02/20/19 | 02/22/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 596.06 |  | 0 | 0
995 | Payroll Burden | PR | 613 | 02/20/19 | 02/22/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 702.5 |  | 0 | 0
995 | Payroll Burden | PR | 616 | 02/20/19 | 02/22/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 02/20/19 | 02/22/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 235.5 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 02/20/19 | 02/22/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 629 | 02/20/19 | 02/22/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 682.99 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 02/20/19 | 02/22/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 267.65 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 02/27/19 | 03/01/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 21 | 02/27/19 | 03/01/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 554.38 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 02/27/19 | 03/01/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 820.48 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 02/27/19 | 03/01/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 146.36 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 02/27/19 | 03/01/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 349.26 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 02/27/19 | 03/01/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 267.43 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 02/27/19 | 03/01/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 02/27/19 | 03/01/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 02/27/19 | 03/01/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 03/06/19 | 03/08/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 03/06/19 | 03/08/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 787.66 |  | 0 | 0
995 | Payroll Burden | PR | 277 | 03/06/19 | 03/08/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 291 | 03/06/19 | 03/08/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 03/06/19 | 03/08/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 03/13/19 | 03/15/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 03/13/19 | 03/15/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 03/13/19 | 03/15/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 03/13/19 | 03/15/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 538 | 03/13/19 | 03/15/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 03/13/19 | 03/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 728 | 03/20/19 | 03/22/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 03/20/19 | 03/22/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 639.97 |  | 0 | 0
995 | Payroll Burden | PR | 738 | 03/20/19 | 03/22/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 743 | 03/20/19 | 03/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 431.75 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 03/20/19 | 03/22/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 755 | 03/20/19 | 03/22/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 940 | 03/27/19 | 03/29/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 944 | 03/27/19 | 03/29/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 787.66 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 489.62 |  | 0 | 0
995 | Payroll Burden | PR | 955 | 03/27/19 | 03/29/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 963 | 03/27/19 | 03/29/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 583.65 |  | 0 | 0
995 | Payroll Burden | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 8.32 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 455.03 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 344.6 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 04/10/19 | 04/12/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 04/10/19 | 04/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 349 | 04/10/19 | 04/12/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 356 | 04/10/19 | 04/12/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 370 | 04/10/19 | 04/12/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 374 | 04/10/19 | 04/12/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 04/17/19 | 04/19/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 538 | 04/17/19 | 04/19/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 04/17/19 | 04/19/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 04/17/19 | 04/19/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 554 | 04/17/19 | 04/19/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 356.57 |  | 0 | 0
995 | Payroll Burden | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 568 | 04/17/19 | 04/19/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 572 | 04/17/19 | 04/19/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 471.88 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 17.96 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 04/24/19 | 04/26/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 766 | 04/24/19 | 04/26/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 665.25 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 04/24/19 | 04/26/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 432.41 |  | 0 | 0
995 | Payroll Burden | PR | 787 | 04/24/19 | 04/26/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 791 | 04/24/19 | 04/26/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 813 | 04/24/19 | 04/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 05/01/19 | 05/03/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.09 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 05/01/19 | 05/03/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 05/01/19 | 05/03/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 05/01/19 | 05/03/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 177 | 05/08/19 | 05/10/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 178 | 05/08/19 | 05/10/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 187 | 05/08/19 | 05/10/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 194 | 05/08/19 | 05/10/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 409 | 05/15/19 | 05/17/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 410 | 05/15/19 | 05/17/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 419 | 05/15/19 | 05/17/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 426 | 05/15/19 | 05/17/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 432.41 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 05/22/19 | 05/24/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 05/22/19 | 05/24/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 05/22/19 | 05/24/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 05/22/19 | 05/24/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 895 | 05/29/19 | 05/31/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 896 | 05/29/19 | 05/31/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 905 | 05/29/19 | 05/31/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 912 | 05/29/19 | 05/31/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 340.16 |  | 0 | 0
995 | Payroll Burden | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 06/05/19 | 06/07/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 06/05/19 | 06/07/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 207 | 06/05/19 | 06/07/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 06/05/19 | 06/07/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 431.08 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 06/12/19 | 06/14/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 674.12 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 06/12/19 | 06/14/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 397.82 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 06/19/19 | 06/21/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 06/19/19 | 06/21/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 645 | 06/19/19 | 06/21/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 06/19/19 | 06/21/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 653 | 06/19/19 | 06/21/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 334.4 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 06/19/19 | 06/21/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 06/19/19 | 06/21/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 85.37 |  | 0 | 0
995 | Payroll Burden | PR | 855 | 06/26/19 | 06/28/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 550.83 |  | 0 | 0
995 | Payroll Burden | PR | 856 | 06/26/19 | 06/28/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 863 | 06/26/19 | 06/28/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 750.4 |  | 0 | 0
995 | Payroll Burden | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 211.11 |  | 0 | 0
995 | Payroll Burden | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 06/26/19 | 06/28/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 899 | 06/26/19 | 06/28/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 328.63 |  | 0 | 0
995 | Payroll Burden | PR | 902 | 06/26/19 | 06/28/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 363.23 |  | 0 | 0
995 | Payroll Burden | PR | 903 | 06/26/19 | 06/28/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 322.87 |  | 0 | 0
995 | Payroll Burden | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 911 | 06/26/19 | 06/28/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 85.37 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 07/03/19 | 07/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 425.09 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 07/03/19 | 07/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 440.84 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 07/03/19 | 07/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 07/03/19 | 07/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 07/03/19 | 07/05/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 07/10/19 | 07/12/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 353 | 07/10/19 | 07/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 526 | 07/17/19 | 07/19/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 07/17/19 | 07/19/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 07/17/19 | 07/19/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 07/17/19 | 07/19/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 49.67 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 07/24/19 | 07/26/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 184.72 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 171.86 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 07/31/19 | 08/02/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 49.67 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 282.51 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 07/31/19 | 08/02/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 07/31/19 | 08/02/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 08/07/19 | 08/09/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 08/07/19 | 08/09/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 08/07/19 | 08/09/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 08/07/19 | 08/09/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 579 | 08/14/19 | 08/16/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 581 | 08/14/19 | 08/16/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 582 | 08/14/19 | 08/16/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 217.32 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 08/14/19 | 08/16/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 629 | 08/14/19 | 08/16/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 08/14/19 | 08/16/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 815 | 08/21/19 | 08/23/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 817 | 08/21/19 | 08/23/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 818 | 08/21/19 | 08/23/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 315.11 |  | 0 | 0
995 | Payroll Burden | PR | 862 | 08/21/19 | 08/23/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 874 | 08/21/19 | 08/23/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 1004 | 08/28/19 | 08/30/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 1006 | 08/28/19 | 08/30/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 1008 | 08/28/19 | 08/30/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 1009 | 08/28/19 | 08/30/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 1016 | 08/28/19 | 08/30/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 08/28/19 | 08/30/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 1053 | 08/28/19 | 08/30/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 1065 | 08/28/19 | 08/30/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 09/04/19 | 09/06/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 09/04/19 | 09/06/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 09/04/19 | 09/06/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 09/04/19 | 09/06/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 86 | 09/04/19 | 09/06/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 85.37 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 09/11/19 | 09/13/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 09/11/19 | 09/13/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 297 | 09/11/19 | 09/13/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 309 | 09/11/19 | 09/13/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 09/18/19 | 09/20/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 09/18/19 | 09/20/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 09/18/19 | 09/20/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 151.68 |  | 0 | 0
995 | Payroll Burden | PR | 546 | 09/18/19 | 09/20/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 09/25/19 | 09/27/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 09/25/19 | 09/27/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 666 | 09/25/19 | 09/27/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 09/25/19 | 09/27/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 694 | 09/25/19 | 09/27/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 09/25/19 | 09/27/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 10/02/19 | 10/04/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 10/02/19 | 10/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 173.85 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 10/02/19 | 10/04/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 10/02/19 | 10/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 48.79 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 10/09/19 | 10/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 10/09/19 | 10/11/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 10/09/19 | 10/11/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 10/09/19 | 10/11/19 | GA83 | Gauthier, Dillon R | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 10/09/19 | 10/11/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 10/09/19 | 10/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 260.78 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 10/09/19 | 10/11/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 10/09/19 | 10/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 10/16/19 | 10/18/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 474.32 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 10/16/19 | 10/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 282.51 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 10/16/19 | 10/18/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 627 | 10/23/19 | 10/25/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 481.2 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 10/23/19 | 10/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 653 | 10/23/19 | 10/25/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 42.13 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 10/23/19 | 10/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/30/19 | 11/01/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 465.68 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 10/30/19 | 11/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 203.57 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 10/30/19 | 11/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 10/30/19 | 11/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 51.45 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 11/06/19 | 11/08/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 419.11 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 11/06/19 | 11/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 155.67 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 11/06/19 | 11/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 25.72 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 11/13/19 | 11/15/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 11/13/19 | 11/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 263.44 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 11/20/19 | 11/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 131.72 |  | 0 | 0
995 | Payroll Burden | PR | 878 | 11/27/19 | 11/27/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 917 | 11/27/19 | 11/27/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 12/04/19 | 12/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 104 | 12/04/19 | 12/06/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 12/11/19 | 12/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 763 | 12/25/19 | 12/27/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 764 | 01/22/20 | 01/24/20 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
998 | Payroll Taxes | PR | 534 | 09/20/17 | 09/22/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 09/20/17 | 09/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 09/27/17 | 09/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 10/04/17 | 10/06/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/04/17 | 10/06/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 10/11/17 | 10/13/17 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 10/11/17 | 10/13/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 11/01/17 | 11/03/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 11/29/17 | 12/01/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 12/06/17 | 12/08/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 12/13/17 | 12/15/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 691 | 06/20/18 | 06/22/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 11.78 |  | 0 | 0
998 | Payroll Taxes | PR | 694 | 06/20/18 | 06/22/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 15.99 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 962 | 06/27/18 | 06/29/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 29.07 |  | 0 | 0
998 | Payroll Taxes | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 991 | 06/27/18 | 06/29/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 67.13 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 51.64 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 07/04/18 | 07/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 17.44 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 07/04/18 | 07/06/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 07/04/18 | 07/06/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 306 | 07/11/18 | 07/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 07/11/18 | 07/13/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 348 | 07/11/18 | 07/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 99.83 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 446 | 07/18/18 | 07/20/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 07/18/18 | 07/20/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 07/18/18 | 07/20/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 08/01/18 | 08/03/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 08/01/18 | 08/03/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 08/08/18 | 08/10/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 08/08/18 | 08/10/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 08/08/18 | 08/10/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 08/08/18 | 08/10/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 08/15/18 | 08/17/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 08/15/18 | 08/17/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 08/15/18 | 08/17/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 08/22/18 | 08/24/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 792 | 08/22/18 | 08/24/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 9.29 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 08/22/18 | 08/24/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 1002 | 08/29/18 | 08/31/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 1008 | 08/29/18 | 08/31/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 1037 | 08/29/18 | 08/31/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 1046 | 08/29/18 | 08/31/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 137.7 |  | 0 | 0
998 | Payroll Taxes | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 1051 | 08/29/18 | 08/31/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 1069 | 08/29/18 | 08/31/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 09/26/18 | 09/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 692 | 09/26/18 | 09/28/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 727 | 09/26/18 | 09/28/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 93.71 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 10/03/18 | 10/05/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 30.98 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 10/03/18 | 10/05/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 10/10/18 | 10/12/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 10/10/18 | 10/12/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 80.33 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 10/10/18 | 10/12/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 10/10/18 | 10/12/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 10/17/18 | 10/19/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 10/17/18 | 10/19/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 48.39 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 10/17/18 | 10/19/18 | SE71 | Serrano, Jeremiah G | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 10/17/18 | 10/19/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 10/24/18 | 10/26/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 727 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 10/24/18 | 10/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 10/24/18 | 10/26/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 14.23 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 10/24/18 | 10/26/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 766 | 10/24/18 | 10/26/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 74.97 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 10/24/18 | 10/26/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 10/31/18 | 11/02/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 10/31/18 | 11/02/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 93.71 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/31/18 | 11/02/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 10/31/18 | 11/02/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 59.29 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 10/31/18 | 11/02/18 | TH59 | Thompson, Harley J | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/07/18 | 11/09/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 201 | 11/07/18 | 11/09/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 91.04 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 11/07/18 | 11/09/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 11/07/18 | 11/09/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 11/07/18 | 11/09/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 66.4 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 11/14/18 | 11/16/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 93.71 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 11/14/18 | 11/16/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 15.49 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 11/14/18 | 11/16/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 11/14/18 | 11/16/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.56 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 11/14/18 | 11/16/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | -21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | -70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 11/14/18 | 11/16/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 11/14/18 | 11/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 11/21/18 | 11/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 11/21/18 | 11/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 634 | 11/21/18 | 11/21/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 11/21/18 | 11/21/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 72.68 |  | 0 | 0
998 | Payroll Taxes | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 91.04 |  | 0 | 0
998 | Payroll Taxes | PR | 642 | 11/21/18 | 11/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 11/21/18 | 11/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 78.49 |  | 0 | 0
998 | Payroll Taxes | PR | 671 | 11/21/18 | 11/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 11/21/18 | 11/21/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 675 | 11/21/18 | 11/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 90.12 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 837 | 11/28/18 | 11/30/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 845 | 11/28/18 | 11/30/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 44.87 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 11/28/18 | 11/30/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 65.98 |  | 0 | 0
998 | Payroll Taxes | PR | 852 | 11/28/18 | 11/30/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 71.26 |  | 0 | 0
998 | Payroll Taxes | PR | 855 | 11/28/18 | 11/30/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 97.65 |  | 0 | 0
998 | Payroll Taxes | PR | 877 | 11/28/18 | 11/30/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 57.53 |  | 0 | 0
998 | Payroll Taxes | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 882 | 11/28/18 | 11/30/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 884 | 11/28/18 | 11/30/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 44.87 |  | 0 | 0
998 | Payroll Taxes | PR | 888 | 11/28/18 | 11/30/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 57.53 |  | 0 | 0
998 | Payroll Taxes | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 12/05/18 | 12/07/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 12/05/18 | 12/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 12/05/18 | 12/07/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 12/05/18 | 12/07/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 107.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 12/05/18 | 12/07/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 12/05/18 | 12/07/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 46.74 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 12/05/18 | 12/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 16.18 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 12/05/18 | 12/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 96 | 12/05/18 | 12/07/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 49.42 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 12/05/18 | 12/07/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | -110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 12/12/18 | 12/14/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 12/12/18 | 12/14/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 49.42 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 12/12/18 | 12/14/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 29.72 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 12/12/18 | 12/14/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 4.25 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 12/12/18 | 12/14/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 12/12/18 | 12/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 62.12 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 12/12/18 | 12/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 23.56 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 12/12/18 | 12/14/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 12/12/18 | 12/14/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 12/19/18 | 12/21/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 12/19/18 | 12/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 57.22 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 12/19/18 | 12/21/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 12/19/18 | 12/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 103.31 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 12/19/18 | 12/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 33.47 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 12/19/18 | 12/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 554 | 12/19/18 | 12/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 72.83 |  | 0 | 0
998 | Payroll Taxes | PR | 559 | 12/19/18 | 12/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 561 | 12/19/18 | 12/21/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 57.22 |  | 0 | 0
998 | Payroll Taxes | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 565 | 12/19/18 | 12/21/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 107.71 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 12/26/18 | 12/28/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 39.78 |  | 0 | 0
998 | Payroll Taxes | PR | 715 | 12/26/18 | 12/28/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 49.73 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 12/26/18 | 12/28/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 45.29 |  | 0 | 0
998 | Payroll Taxes | PR | 726 | 12/26/18 | 12/28/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 23.41 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 12/26/18 | 12/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 12/26/18 | 12/28/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 12/26/18 | 12/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 752 | 12/26/18 | 12/28/18 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 33.81 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 12/26/18 | 12/28/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | -36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 01/02/19 | 01/04/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 01/02/19 | 01/04/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 01/02/19 | 01/04/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 28.31 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 01/02/19 | 01/04/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 01/02/19 | 01/04/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 01/02/19 | 01/04/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 56.76 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 01/02/19 | 01/04/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 36.41 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 01/02/19 | 01/04/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 01/09/19 | 01/11/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 228 | 01/09/19 | 01/11/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 233 | 01/09/19 | 01/11/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 01/09/19 | 01/11/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 01/09/19 | 01/11/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 01/09/19 | 01/11/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 01/09/19 | 01/11/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 01/09/19 | 01/11/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 01/09/19 | 01/11/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 01/09/19 | 01/11/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 74.66 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 474 | 01/16/19 | 01/18/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 01/16/19 | 01/18/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 01/16/19 | 01/18/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 01/16/19 | 01/18/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 106.14 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 01/16/19 | 01/18/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 01/16/19 | 01/18/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 01/16/19 | 01/18/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -16.18 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 28.76 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 01/16/19 | 01/18/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 01/16/19 | 01/18/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 01/16/19 | 01/18/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 01/23/19 | 01/25/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 01/23/19 | 01/25/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 737 | 01/23/19 | 01/25/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 01/23/19 | 01/25/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 01/23/19 | 01/25/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 01/23/19 | 01/25/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 01/23/19 | 01/25/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 71.72 |  | 0 | 0
998 | Payroll Taxes | PR | 761 | 01/23/19 | 01/25/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 01/23/19 | 01/25/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 01/23/19 | 01/25/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 2.75 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 01/30/19 | 02/01/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 01/30/19 | 02/01/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 01/30/19 | 02/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 01/30/19 | 02/01/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 108.97 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 01/30/19 | 02/01/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 01/30/19 | 02/01/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 01/30/19 | 02/01/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 01/30/19 | 02/01/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 166 | 02/06/19 | 02/08/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 175 | 02/06/19 | 02/08/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 180 | 02/06/19 | 02/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 02/06/19 | 02/08/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 190 | 02/06/19 | 02/08/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 196 | 02/06/19 | 02/08/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 203 | 02/06/19 | 02/08/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 208 | 02/06/19 | 02/08/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 02/06/19 | 02/08/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 02/13/19 | 02/15/19 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 02/13/19 | 02/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 342 | 02/13/19 | 02/15/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 345 | 02/13/19 | 02/15/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 352 | 02/13/19 | 02/15/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 357 | 02/13/19 | 02/15/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 358 | 02/13/19 | 02/15/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 365 | 02/13/19 | 02/15/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 370 | 02/13/19 | 02/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 29.99 |  | 0 | 0
998 | Payroll Taxes | PR | 372 | 02/13/19 | 02/15/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 25.36 |  | 0 | 0
998 | Payroll Taxes | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 595 | 02/20/19 | 02/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 600 | 02/20/19 | 02/22/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 115.67 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 02/20/19 | 02/22/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 130.2 |  | 0 | 0
998 | Payroll Taxes | PR | 610 | 02/20/19 | 02/22/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 102.82 |  | 0 | 0
998 | Payroll Taxes | PR | 613 | 02/20/19 | 02/22/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 615 | 02/20/19 | 02/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 121.18 |  | 0 | 0
998 | Payroll Taxes | PR | 616 | 02/20/19 | 02/22/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 02/20/19 | 02/22/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 40.62 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 02/20/19 | 02/22/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 629 | 02/20/19 | 02/22/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 117.81 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 02/20/19 | 02/22/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 46.17 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 02/27/19 | 03/01/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 21 | 02/27/19 | 03/01/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 95.63 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 02/27/19 | 03/01/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 02/27/19 | 03/01/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 141.53 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 02/27/19 | 03/01/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 02/27/19 | 03/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 25.25 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 02/27/19 | 03/01/19 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 60.24 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 02/27/19 | 03/01/19 | MU70 | Murphy, Darray E | 0 | 0 | 0 | 0 | 46.13 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 02/27/19 | 03/01/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 02/27/19 | 03/01/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 02/27/19 | 03/01/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 03/06/19 | 03/08/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 03/06/19 | 03/08/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 03/06/19 | 03/08/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 03/06/19 | 03/08/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 135.86 |  | 0 | 0
998 | Payroll Taxes | PR | 277 | 03/06/19 | 03/08/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 03/06/19 | 03/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 291 | 03/06/19 | 03/08/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 03/06/19 | 03/08/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 03/13/19 | 03/15/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 03/13/19 | 03/15/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 03/13/19 | 03/15/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 03/13/19 | 03/15/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 538 | 03/13/19 | 03/15/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 03/13/19 | 03/15/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 728 | 03/20/19 | 03/22/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 03/20/19 | 03/22/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 110.39 |  | 0 | 0
998 | Payroll Taxes | PR | 738 | 03/20/19 | 03/22/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 743 | 03/20/19 | 03/22/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 74.47 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 03/20/19 | 03/22/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 755 | 03/20/19 | 03/22/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 934 | 03/27/19 | 03/29/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 935 | 03/27/19 | 03/29/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 940 | 03/27/19 | 03/29/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 944 | 03/27/19 | 03/29/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 135.86 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 950 | 03/27/19 | 03/29/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 84.46 |  | 0 | 0
998 | Payroll Taxes | PR | 955 | 03/27/19 | 03/29/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 959 | 03/27/19 | 03/29/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 963 | 03/27/19 | 03/29/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 967 | 03/27/19 | 03/29/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 100.67 |  | 0 | 0
998 | Payroll Taxes | PR | 989 | 03/27/19 | 03/29/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 96 | 04/03/19 | 04/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 1.43 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 04/03/19 | 04/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 78.49 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 04/03/19 | 04/05/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 59.44 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 04/03/19 | 04/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 113 | 04/03/19 | 04/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 118 | 04/03/19 | 04/05/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 126 | 04/03/19 | 04/05/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 130 | 04/03/19 | 04/05/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 04/10/19 | 04/12/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 04/10/19 | 04/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 346 | 04/10/19 | 04/12/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 349 | 04/10/19 | 04/12/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 356 | 04/10/19 | 04/12/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 361 | 04/10/19 | 04/12/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 370 | 04/10/19 | 04/12/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 374 | 04/10/19 | 04/12/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 04/17/19 | 04/19/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 538 | 04/17/19 | 04/19/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 04/17/19 | 04/19/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 04/17/19 | 04/19/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 554 | 04/17/19 | 04/19/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 61.51 |  | 0 | 0
998 | Payroll Taxes | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 559 | 04/17/19 | 04/19/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 568 | 04/17/19 | 04/19/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 572 | 04/17/19 | 04/19/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 81.4 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 3.1 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 04/24/19 | 04/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 04/24/19 | 04/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 04/24/19 | 04/26/19 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 766 | 04/24/19 | 04/26/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 114.75 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 04/24/19 | 04/26/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 74.59 |  | 0 | 0
998 | Payroll Taxes | PR | 787 | 04/24/19 | 04/26/19 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 791 | 04/24/19 | 04/26/19 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 813 | 04/24/19 | 04/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 05/01/19 | 05/03/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.33 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 05/01/19 | 05/03/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 05/01/19 | 05/03/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 05/01/19 | 05/03/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 177 | 05/08/19 | 05/10/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 178 | 05/08/19 | 05/10/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 187 | 05/08/19 | 05/10/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 194 | 05/08/19 | 05/10/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 409 | 05/15/19 | 05/17/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 410 | 05/15/19 | 05/17/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 419 | 05/15/19 | 05/17/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 426 | 05/15/19 | 05/17/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 74.59 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 05/22/19 | 05/24/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 05/22/19 | 05/24/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 05/22/19 | 05/24/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 05/22/19 | 05/24/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 895 | 05/29/19 | 05/31/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 896 | 05/29/19 | 05/31/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 905 | 05/29/19 | 05/31/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 912 | 05/29/19 | 05/31/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 58.68 |  | 0 | 0
998 | Payroll Taxes | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 06/05/19 | 06/07/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 06/05/19 | 06/07/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 207 | 06/05/19 | 06/07/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 06/05/19 | 06/07/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 06/05/19 | 06/07/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 06/05/19 | 06/07/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 74.36 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 06/12/19 | 06/14/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 06/12/19 | 06/14/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 116.28 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 06/12/19 | 06/14/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 06/12/19 | 06/14/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 68.62 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 06/12/19 | 06/14/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 06/12/19 | 06/14/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 06/19/19 | 06/21/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 06/19/19 | 06/21/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 645 | 06/19/19 | 06/21/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 06/19/19 | 06/21/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 653 | 06/19/19 | 06/21/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 57.68 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 06/19/19 | 06/21/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 06/19/19 | 06/21/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.73 |  | 0 | 0
998 | Payroll Taxes | PR | 855 | 06/26/19 | 06/28/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 95.01 |  | 0 | 0
998 | Payroll Taxes | PR | 856 | 06/26/19 | 06/28/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 857 | 06/26/19 | 06/28/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 863 | 06/26/19 | 06/28/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 129.44 |  | 0 | 0
998 | Payroll Taxes | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 36.41 |  | 0 | 0
998 | Payroll Taxes | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 06/26/19 | 06/28/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 899 | 06/26/19 | 06/28/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 56.69 |  | 0 | 0
998 | Payroll Taxes | PR | 902 | 06/26/19 | 06/28/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 62.65 |  | 0 | 0
998 | Payroll Taxes | PR | 903 | 06/26/19 | 06/28/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 55.69 |  | 0 | 0
998 | Payroll Taxes | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 911 | 06/26/19 | 06/28/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.73 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 07/03/19 | 07/05/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 73.33 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 07/03/19 | 07/05/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 76.04 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 07/03/19 | 07/05/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 07/03/19 | 07/05/19 | HU05 | Hubbard, Justin A | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 07/03/19 | 07/05/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 07/03/19 | 07/05/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 07/10/19 | 07/12/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 07/10/19 | 07/12/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 353 | 07/10/19 | 07/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 526 | 07/17/19 | 07/19/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 07/17/19 | 07/19/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 07/17/19 | 07/19/19 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 07/17/19 | 07/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 07/17/19 | 07/19/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 586 | 07/17/19 | 07/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 07/24/19 | 07/26/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 07/24/19 | 07/26/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 8.57 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 07/24/19 | 07/26/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 07/24/19 | 07/26/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 31.86 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 686 | 07/24/19 | 07/26/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 29.64 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 07/31/19 | 08/02/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/31/19 | 08/02/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 8.57 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/31/19 | 08/02/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 07/31/19 | 08/02/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 48.73 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 07/31/19 | 08/02/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 07/31/19 | 08/02/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 08/07/19 | 08/09/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 08/07/19 | 08/09/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 291 | 08/07/19 | 08/09/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 08/07/19 | 08/09/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 08/07/19 | 08/09/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 579 | 08/14/19 | 08/16/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 581 | 08/14/19 | 08/16/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 582 | 08/14/19 | 08/16/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.49 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 08/14/19 | 08/16/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 629 | 08/14/19 | 08/16/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 08/14/19 | 08/16/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 815 | 08/21/19 | 08/23/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 817 | 08/21/19 | 08/23/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 818 | 08/21/19 | 08/23/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 54.35 |  | 0 | 0
998 | Payroll Taxes | PR | 862 | 08/21/19 | 08/23/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 874 | 08/21/19 | 08/23/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 1004 | 08/28/19 | 08/30/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 1006 | 08/28/19 | 08/30/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 1008 | 08/28/19 | 08/30/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 1009 | 08/28/19 | 08/30/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1016 | 08/28/19 | 08/30/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 08/28/19 | 08/30/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 1053 | 08/28/19 | 08/30/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 1065 | 08/28/19 | 08/30/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 09/04/19 | 09/06/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 09/04/19 | 09/06/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 09/04/19 | 09/06/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 09/04/19 | 09/06/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 86 | 09/04/19 | 09/06/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.73 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 09/11/19 | 09/13/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 09/11/19 | 09/13/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 297 | 09/11/19 | 09/13/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 309 | 09/11/19 | 09/13/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 09/18/19 | 09/20/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 09/18/19 | 09/20/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 09/18/19 | 09/20/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 26.16 |  | 0 | 0
998 | Payroll Taxes | PR | 546 | 09/18/19 | 09/20/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 09/25/19 | 09/27/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 09/25/19 | 09/27/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 666 | 09/25/19 | 09/27/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 09/25/19 | 09/27/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 09/25/19 | 09/27/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 694 | 09/25/19 | 09/27/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 09/25/19 | 09/27/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 10/02/19 | 10/04/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 10/02/19 | 10/04/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.99 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 10/02/19 | 10/04/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 10/02/19 | 10/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.42 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 10/09/19 | 10/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 10/09/19 | 10/11/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 10/09/19 | 10/11/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 10/09/19 | 10/11/19 | GA83 | Gauthier, Dillon R | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 10/09/19 | 10/11/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 10/09/19 | 10/11/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 44.98 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 10/09/19 | 10/11/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 10/09/19 | 10/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 10/16/19 | 10/18/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 81.82 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 10/16/19 | 10/18/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 48.73 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 10/16/19 | 10/18/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 627 | 10/23/19 | 10/25/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 83 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 10/23/19 | 10/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 653 | 10/23/19 | 10/25/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 7.27 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 10/23/19 | 10/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/30/19 | 11/01/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 80.33 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 10/30/19 | 11/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 35.11 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 10/30/19 | 11/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 10/30/19 | 11/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.87 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 11/06/19 | 11/08/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 72.29 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 11/06/19 | 11/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 26.85 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 11/06/19 | 11/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.44 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 11/13/19 | 11/15/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 11/13/19 | 11/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 45.44 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 11/20/19 | 11/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.72 |  | 0 | 0
998 | Payroll Taxes | PR | 878 | 11/27/19 | 11/27/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 917 | 11/27/19 | 11/27/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 12/04/19 | 12/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 104 | 12/04/19 | 12/06/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 12/11/19 | 12/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 763 | 12/25/19 | 12/27/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 764 | 01/22/20 | 01/24/20 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
999 | Sales | AR | 550 | 04/20/18 | 04/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -14000 | 037071 | 0 | -700
999 | Sales | AR | 675 | 06/20/18 | 06/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -15000 | 037114 | 0 | -750
999 | Sales | AR | 675 | 06/20/18 | 06/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2300 | 037114 | 0 | -115
999 | Sales | AR | 528 | 07/20/18 | 07/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -29000 | 037140 | 0 | -1450
999 | Sales | AR | 528 | 07/20/18 | 07/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -14550 | 037140 | 0 | -727.5
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -29000 | 037164 | 0 | -1450
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -86000 | 037164 | 0 | -4300
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -4850 | 037164 | 0 | -242.5
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -44860 | 037164 | 0 | -2243
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -34640 | 037164 | 0 | -1732
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -250 | 037164 | 0 | -12.5
999 | Sales | AR | 593 | 08/20/18 | 08/20/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -21795 | 037164 | 0 | -1089.75
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 29000 | 037196 | 0 | 1450
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 86000 | 037196 | 0 | 4300
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 4850 | 037196 | 0 | 242.5
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 44860 | 037196 | 0 | 2243
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 34640 | 037196 | 0 | 1732
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 250 | 037196 | 0 | 12.5
999 | Sales | AR | 138 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 21795 | 037196 | 0 | 1089.75
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -86000 | 037197 | 0 | -4300
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -4850 | 037197 | 0 | -242.5
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -44860 | 037197 | 0 | -2243
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -34640 | 037197 | 0 | -1732
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -250 | 037197 | 0 | -12.5
999 | Sales | AR | 139 | 08/20/18 | 10/01/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -21795 | 037197 | 0 | -1089.75
999 | Sales | AR | 531 | 10/19/18 | 10/19/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -96475 | 037217 | 0 | -4823.75
999 | Sales | AR | 531 | 10/19/18 | 10/19/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -29500 | 037217 | 0 | -1475
999 | Sales | AR | 531 | 10/19/18 | 10/19/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17280 | 037217 | 0 | -864
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17025 | 037236 | 0 | -851.25
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -15400 | 037236 | 0 | -770
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -118000 | 037236 | 0 | -5900
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -26230 | 037236 | 0 | -1311.5
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17760 | 037236 | 0 | -888
999 | Sales | AR | 530 | 11/16/18 | 11/16/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -18240 | 037236 | 0 | -912
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -47750 | 037246 | 0 | -2387.5
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -88500 | 037246 | 0 | -4425
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -131150 | 037246 | 0 | -6557.5
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -78700 | 037246 | 0 | -3935
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17500 | 037246 | 0 | -875
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -18240 | 037246 | 0 | -912
999 | Sales | AR | 171 | 12/11/18 | 12/11/18 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17280 | 037246 | 0 | -864
999 | Sales | AR | 549 | 01/18/19 | 01/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -17800 | 037267 | 0 | -890
999 | Sales | AR | 549 | 01/18/19 | 01/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -78680 | 037267 | 0 | -3934
999 | Sales | AR | 549 | 01/18/19 | 01/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -87380 | 037267 | 0 | -4369
999 | Sales | AR | 549 | 01/18/19 | 01/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -58920 | 037267 | 0 | -2946
999 | Sales | AR | 549 | 01/18/19 | 01/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2420 | 037267 | 0 | -121
999 | Sales | AR | 565 | 02/20/19 | 02/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -26230 | 037287 | 0 | -1311.5
999 | Sales | AR | 565 | 02/20/19 | 02/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -26230 | 037287 | 0 | -1311.5
999 | Sales | AR | 565 | 02/20/19 | 02/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -43700 | 037287 | 0 | -2185
999 | Sales | AR | 565 | 02/20/19 | 02/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -39280 | 037287 | 0 | -1964
999 | Sales | AR | 565 | 02/20/19 | 02/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -12310 | 037287 | 0 | -615.5
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -16350 | 037306 | 0 | -817.5
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -26230 | 037306 | 0 | -1311.5
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -78690 | 037306 | 0 | -3934.5
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -26220 | 037306 | 0 | -1311
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -11400 | 037306 | 0 | -570
999 | Sales | AR | 685 | 03/20/19 | 03/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -10800 | 037306 | 0 | -540
999 | Sales | AR | 608 | 04/19/19 | 04/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -59000 | 037324 | 0 | -2950
999 | Sales | AR | 608 | 04/19/19 | 04/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -52460 | 037324 | 0 | -2623
999 | Sales | AR | 608 | 04/19/19 | 04/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -11400 | 037324 | 0 | -570
999 | Sales | AR | 608 | 04/19/19 | 04/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | 0 | 037324 | 0 | 0
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -3000 | 037342 | 0 | -150
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -10800 | 037342 | 0 | -540
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -11100 | 037342 | 0 | -555
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2592 | 037342 | 0 | -129.6
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2640 | 037342 | 0 | -132
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -4320 | 037342 | 0 | -216
999 | Sales | AR | 509 | 05/20/19 | 05/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2760 | 037342 | 0 | -138
999 | Sales | AR | 610 | 06/19/19 | 06/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -3600 | 037366 | 0 | -180
999 | Sales | AR | 610 | 06/19/19 | 06/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -22480 | 037366 | 0 | -1124
999 | Sales | AR | 610 | 06/19/19 | 06/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -44960 | 037366 | 0 | -2248
999 | Sales | AR | 610 | 06/19/19 | 06/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -54500 | 037366 | 0 | -2725
999 | Sales | AR | 600 | 07/19/19 | 07/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -13625 | 037375 | 0 | -681.25
999 | Sales | AR | 600 | 07/19/19 | 07/19/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -11240 | 037375 | 0 | -562
999 | Sales | AR | 748 | 08/20/19 | 08/15/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -39340 | 037385 | 0 | -1967
999 | Sales | AR | 748 | 08/20/19 | 08/15/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -40875 | 037385 | 0 | -2043.75
999 | Sales | AR | 748 | 08/20/19 | 08/15/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -33720 | 037385 | 0 | -1686
999 | Sales | AR | 564 | 09/20/19 | 09/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -16860 | 037408 | 0 | -843
999 | Sales | AR | 564 | 09/20/19 | 09/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -19155 | 037408 | 0 | -957.75
999 | Sales | AR | 564 | 09/20/19 | 09/20/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -288 | 037408 | 0 | -14.4
999 | Sales | AR | 536 | 10/18/19 | 10/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -2900 | 037423 | 0 | -145
999 | Sales | AR | 536 | 10/18/19 | 10/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -1080 | 037423 | 0 | -54
999 | Sales | AR | 536 | 10/18/19 | 10/18/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -285 | 037423 | 0 | -14.25
999 | Sales | AR | 481 | 12/13/19 | 12/13/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -37000 | 037457 | 0 | -1850
999 | Sales | AR | 481 | 12/13/19 | 12/13/19 | 2045GR | GRE Construction, LLC $Notch |  |  |  |  | -23310 | 037457 | 0 | -1165.5

## Crew Roster
CREW ROSTER — 39 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Garcia, Jordan X | 88 | 0 | 0 | 288 | 0 | 3.2727
APPRENTICE/HELPER | Serrano, Jeremiah G | 105.5 | 0 | 0 | 1688 | 0 | 16
APPRENTICE/HELPER | Thompson, Harley J | 92 | 6 | 0 | 1472 | 144 | 16
APPRENTICE/HELPER | Vazquez Popoca, Jose N | 205.5 | 0 | 0 | 3360 | 0 | 16.3504
APPRENTICE/HELPER | de la Torre, Kevin A | 476.5 | 40 | 0 | 7798.5 | 978 | 16.3662
APPRENTICE/HELPER | Roberts, Lake A | 501.5 | 20 | 0 | 8417.5 | 498 | 16.7846
APPRENTICE/HELPER | Guerrero, Ali A | 108 | 0 | 0 | 1836 | 0 | 17
APPRENTICE/HELPER | Gauthier, Dillon R | 8 | 0 | 0 | 136 | 0 | 17
APPRENTICE/HELPER | Escalante Escobar, Boanerge | 20 | 0 | 0 | 360 | 0 | 18
APPRENTICE/HELPER | Murphy, Darray E | 63 | 0 | 0 | 1134 | 0 | 18
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 149.5 | 0 | 0 | 2691 | 0 | 18
APPRENTICE/HELPER | Belcher, Jacob T | 2 | 0 | 0 | 36 | 0 | 18
APPRENTICE/HELPER | Cornejo Orellana, Carlos E | 75 | 0 | 0 | 1425 | 0 | 19
APPRENTICE/HELPER | Stahlschmidt, John P | 398 | 0 | 0 | 7562 | 0 | 19
APPRENTICE/HELPER | Chevez, Herson G | 448.5 | 20 | 0 | 8894 | 600 | 19.8305
APPRENTICE/HELPER | Barnhart, Joseph N | 20 | 0 | 0 | 0 | 0 | 0
JOURNEYMAN | Portillo Soriano, Walter A | 776 | 28 | 0 | 15536 | 840 | 20.0206
JOURNEYMAN | Hubbard, Dustin R | 5 | 0 | 0 | 105 | 0 | 21
JOURNEYMAN | Cruz Gonzalez, Julio C | 287.5 | 9 | 0 | 6227.5 | 270 | 21.6609
JOURNEYMAN | Benites Portillo, Marvin E | 127 | 6 | 0 | 2794 | 198 | 22
JOURNEYMAN | Lovo, German G | 630.5 | 14.5 | 0 | 15508.5 | 531 | 24.5971
JOURNEYMAN | Hubbard, Justin A | 893.5 | 8 | 0 | 22060 | 288 | 24.6894
JOURNEYMAN | Eisenhauer, Tommy J | 1977.5 | 65.5 | 0 | 49255 | 1788.75 | 24.9077
JOURNEYMAN | Draves, Steven W | 1141 | 24 | 0 | 29919 | 868.5 | 26.2217
JOURNEYMAN | Galdamez, Dagoberto A | 690.5 | 12 | 0 | 18615.5 | 486 | 26.9594
JOURNEYMAN | Eliassen, Cory H | 30 | 0 | 0 | 810 | 0 | 27
JOURNEYMAN | Rivera, Eli P | 1077 | 53 | 0 | 29894 | 2193 | 27.7567
JOURNEYMAN | Cruz Reyes, Jose | 160 | 0 | 0 | 4640 | 0 | 29
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 370 | 11.5 | 0 | 11685 | 537.75 | 31.5811
JOURNEYMAN | Kinssies, Jr, John E | 295.5 | 0 | 0 | 9392.5 | 0 | 31.7851
JOURNEYMAN | Lima Romero, Melvin A | 399.5 | 6 | 0 | 13183.5 | 297 | 33
JOURNEYMAN | McCabe, Thomas C | 62 | 4 | 0 | 2154 | 198 | 34.7419
LEAD/SUPERVISOR | Gerard, Jordan E | 170 | 0 | 0 | 6120 | 0 | 36
LEAD/SUPERVISOR | Gerard, Mitchell J | 1456.5 | 60 | 0 | 54349 | 3240 | 37.3148
LEAD/SUPERVISOR | Quintanilla, Esteban R | 428.5 | 14 | 0 | 18112.5 | 540 | 42.2695
LEAD/SUPERVISOR | Sanders, Allen O | 167 | 0 | 0 | 8302 | 0 | 49.7126
LEAD/SUPERVISOR | Hubbard, Robert W | 30 | 0 | 0 | 1507 | 0 | 50.2333
LEAD/SUPERVISOR | Gerard, Jeffrey S | 341 | 0 | 0 | 17439.5 | 0 | 51.1422
LEAD/SUPERVISOR | Donelson, Richard T | 97 | 0 | 0 | 5850 | 0 | 60.3093

## Wage Tiers
WAGE TIERS & PERCENTILES — 2045
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 16 | 2761 | 86 | 49318 | 15.5378
JOURNEYMAN | 16 | 8922.5 | 241.5 | 240275.5 | 26.6826
LEAD/SUPERVISOR | 7 | 2690 | 74 | 115460 | 46.7117
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 16.28
p25 | 18
p50 | 22
p75 | 31.68
p90 | 43.76
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 27.1721 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 41.6705 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 55.9263 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2045
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 14,775.00 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $142.82 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $27.40 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 5.21x | Throughput ÷ unit cost — productivity signal
Units (residential) | 187 | Notch Apartments scope doc: 179 Type B + 8 Type A ADA
Fixtures (estimate) | 1804 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 27 | start_date → end_date from GDrive enrichment
Hours per Unit | 79.01 | total_labor_hours ÷ units
Hours per Fixture | 8.19 | total_labor_hours ÷ fixtures
Revenue per Unit | $11,285 | revenue ÷ units
Profit per Unit | $5,198 | net_profit ÷ units
Hours per Month | 547 | total_labor_hours ÷ duration_months
Revenue per Month | $78,156 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 17 VENDORS ($460,397 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Keller Supply Company | 161465.23 | 40 | 4036.6307 | 35.07% | 0 | 0
2 | Rosen Supply Kirkland | 90006.18 | 133 | 676.7382 | 19.55% | 0 | 0
3 | Ferguson Enterprises, Inc. #3007 | 88591.11 | 46 | 1925.8937 | 19.24% | 0 | 0
4 | Consolidated Supply Co. | 53281.96 | 41 | 1299.56 | 11.57% | 0 | 0
5 | California Hydronics Corp | 31781 | 7 | 4540.1429 | 6.903% | 0 | 0
6 | Franklin Engineering | 16078.25 | 4 | 4019.5625 | 3.492% | 0 | 0
7 | Ahern Rentals | 4798.91 | 11 | 436.2645 | 1.042% | 0 | 0
8 | Rosen Supply Company, Inc. $Notch | 4412.58 | 2 | 2206.29 | 0.9584% | 0 | 0
9 | Quality Concrete Products, Inc. $32 | 3186 | 1 | 3186 | 0.692% | 0 | 0
10 | Scan2Core, Inc. | 3162 | 5 | 632.4 | 0.6868% | 0 | 0
11 | Old Castle Infrastructure, Inc. | 1971 | 1 | 1971 | 0.4281% | 0 | 0
12 | Travelers | 445 | 1 | 445 | 0.09666% | 0 | 0
13 | Core & Main LP $HD Supply Waterworks | 357.8 | 2 | 178.9 | 0.07772% | 0 | 0
14 | Capital One Credit Card | 322.95 | 6 | 53.825 | 0.07015% | 0 | 0
15 | R.A. Brown Backflow Testing | 250 | 2 | 125 | 0.0543% | 0 | 0
16 | AllWest Underground, Inc. | 199.24 | 1 | 199.24 | 0.04328% | 0 | 0
17 | Fastenal Company | 87.66 | 1 | 87.66 | 0.01904% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2045
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 |  | Minor scope rebalance (from CO#01 Budget Transfer) | 2300 | Executed 2017-11-20 | Y
2 |  | Major scope additions — GW/Storm + Garage + Roughin rebalance (OneWay_CO2 + ExecutedCO2) | 76325 | Executed 2017-11-20 | Y
3 |  | Additional GW/Storm + Roughin work | 34640 | Executed 2018-08-22 | Y
4 |  | Supervision + Takeoff + GW + Garage + Roughin + Finish additive scope | 11455 | Executed 2018-08-07 | Y
5 |  | Garage + Canout + Roughin additive scope | 26975 | Executed 2018-08-07 | Y
6 |  | Supervision + Takeoff + Roughin additions | 37000 | Executed 2019-03-27 | Y
7 |  | Closeout scope rebalance (final) | 23310 | Executed 2019-03-27 | Y
Executed subtotal |  |  | 212005
Budget-transfer total (incl. extras) |  |  | 212005
JDR-implied CO (revenue − original contract) |  |  | 212005
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
ASI-004 | Added drains in backflow room
Retaining Wall Weep Sleeves — prefab only | Pre-fab sleeves for retaining wall weeps
Retaining Wall Weep Sleeves | Field-installed retaining wall weep sleeves
Toilet Change (Greenlake) | Toilet swap scope clarification
RFI-012 Added drains | Deck/roof drain additions per RFI-012
WH Pads Post-Backup | Water heater pad replacement after sewer backup
Outstanding CORs log | Summary log of all pending CORs
Victor Cost Log 11/19/17 | Field walk cost log (Victor)

## Project Team
PROJECT TEAM — 2045
Primary contacts extracted from Notch Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Eric Bentler | TBD | 206.972.8145
GC Superintendent | Victor Vo | TBD | 206.883.7468
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP)
Owner | Newcastle II LLC
Inspecting Authority | City of Newcastle (via Notch Plumbing Permit Application)

## Document Pipeline
DOCUMENT PIPELINE — 2045
Quantitative document counts from the Notch Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 7 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 8 | Change Orders/COR_s/
Budget transfer entries | 7 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 14 | ASI-RFI/
Submittals | 12 | Submittals/ (PDF count)
POs — placed | 11 | PO_s/1 Placed/
POs — scheduled | 118 | PO_s/2 Scheduled/
POs — completed | 117 | PO_s/3 Completed/
POs — total | 246 | PO_s/ (all three subfolders)
Vendor invoices | 301 | Invoices/
Lien releases | 0 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 2 | Permits/ (plumbing permit application + inspection requests)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for Notch)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2045
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 615682.1 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 460396.87 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 62093.03 | SUM(line_items where source=GL)
direct_cost | 1138172 | PR + AP + GL
net_profit | 972033 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.29176 | PR / abs(revenue)
ap_pct_of_revenue | 0.21818 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.53937 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 14775 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 41.6705 | PR / labor hours
fully_loaded_wage | 55.9263 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 27.1721 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 39 | COUNT DISTINCT(name) source=PR
burden_total | 210628.6 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $16.28 ¦ $18.00 ¦ $22.00 ¦ $31.68 ¦ $43.76 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 497590.37 | SUM(actual) codes 2xx
material_budget_total | 608708 | SUM(current_budget) codes 2xx
material_codes_tracked | 9 | COUNT material codes
material_codes_over_budget | 2 | COUNT where plus_minus > 0
material_codes_under_budget | 7 | COUNT where plus_minus ≤ 0
largest_material_overrun | 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719) | Material code with largest +plus_minus
largest_material_savings | 220 Roughin Material: $97,191 vs $158,260 budget ($-61,069) | Material code with largest −plus_minus
material_vendor_count | 17 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Keller Supply Company: $161,465 (35% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 4 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 20 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719) | Phase with largest +plus_minus
largest_savings | 120 Roughin Labor: $227,602 vs $360,476 budget ($-132,874) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 1138172 | SUM(actual) expense codes
total_budget | 1549924.06 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7343 | JTD / budget
total_over_under_budget | 411752.06 | budget − JTD
labor_unit_cost_per_hr | 27.3984 | Labor JTD / labor hours
revenue_per_labor_hour | 142.8227 | abs(revenue) / labor hours
material_price_variance | 111117.63 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2045
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 46.1% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | GREEN | 4/24 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $111,118 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $142.82 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $105,510 | Monitor for collection
Top vendor concentration | GREEN | 35.1% (Keller Supply Company) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2045
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $2,110,205, net profit $972,033 at 46.1% margin.
02 | Parsed 3,081 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 39 distinct PR-booked workers over 14,775 labor hours ($41.67/hr PR-src, $55.93/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719).
05 | Largest phase savings: 120 Roughin Labor: $227,602 vs $360,476 budget ($-132,874).
06 | Material spend $497,590 vs budget $608,708 ($111,118 favorable).
07 | Top AP vendor: Keller Supply Company: $161,465 (35% of AP); 17 total AP vendors.
08 | Retainage outstanding: $105,510.
09 | 4 of 24 expense phases over budget ($411,752 net vs budget).
10 | Revenue per labor hour $142.82, labor unit cost $27.40 (ratio 5.21x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 25/25 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 9511.5 | 9511.5 | 0 | ✓
101 | Takeoff & Purchase Labor | 13778 | 13778 | 0 | ✓
110 | Underground Labor | 31316 | 31316 | 0 | ✓
111 | Garage Labor | 24709.25 | 24709.25 | 0 | ✓
112 | Canout Labor | 5231 | 5231 | 0 | ✓
120 | Roughin Labor | 227602.48 | 227602.48 | 0 | ✓
130 | Finish Labor | 67247 | 67247 | 0 | ✓
141 | Water Main/Insulation Lab | 21040.5 | 21040.5 | 0 | ✓
142 | Mech Room Labor | 4376 | 4376 | 0 | ✓
210 | Underground Material | 14535.79 | 14535.79 | 0 | ✓
211 | Garage Material | 15918.41 | 15918.41 | 0 | ✓
212 | Canout Material | 4323.42 | 4323.42 | 0 | ✓
220 | Roughin Material | 97191 | 97191 | 0 | ✓
230 | Finish Material | 293213.41 | 293213.41 | 0 | ✓
240 | Gas Material | 63.72 | 63.72 | 0 | ✓
241 | Water Main/Insulation Mat | 65243.62 | 65243.62 | 0 | ✓
242 | Mech Room Material | 7101 | 7101 | 0 | ✓
243 | Condensation Drains Mat | 0 | 0 | 0 | ✓
600 | Subcontractor | 3412 | 3412 | 0 | ✓
601 | Engineering/Plans | 16078.25 | 16078.25 | 0 | ✓
602 | Rental Equipment | 4998.15 | 4998.15 | 0 | ✓
607 | Other Expenses | 652.9 | 652.9 | 0 | ✓
995 | Payroll Burden | 179641.55 | 179641.55 | 0 | ✓
998 | Payroll Taxes | 30987.05 | 30987.05 | 0 | ✓
999 | Sales | -2110205 | -2110205 | 0 | ✓
RESULT: 25/25 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2045
Worked example of the Reconciliation Protocol running against Job 2045 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $1,549,924; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $41.67/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $615,682.10 ÷ 14,775.00 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$16.28 ¦ p25=$18.00 ¦ p50=$22.00 ¦ p75=$31.68 ¦ p90=$43.76 (39 workers) | straight_time_rate $27.17 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $27.40/hr ¦ revenue $142.82/hr ¦ ratio 5.21x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2045 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 25/25 codes tie to PDF to the cent | PR $615,682.10 + AP $460,396.87 + GL $62,093.03 = $1,138,172.00 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2045
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2045 | JDR cover page
job_name | Job Name | GRE Notch Apartments | JDR cover page
general_contractor | General Contractor | GRE | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 3081 | Length of line_items[]
cost_code_count | Cost Code Count | 25 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -2110205 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 2110205 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 1138172 | Sage job_totals_expenses
job_totals_net | Net | -972033 | Sage job_totals_net
job_totals_retainage | Retainage | -105510.25 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 615682.1 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 460396.87 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 62093.03 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -2110205 | SUM(line_items source=AR)
direct_cost | Direct Cost | 1138172 | PR + AP + GL
net_profit | Net Profit | 972033 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 46.06% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 404811.73 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 497590.37 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 25141.3 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 210628.6 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 14775 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 39 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 27.1721 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 41.6705 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 55.9263 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 210628.6 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 16.28 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 18 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 22 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 31.68 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 43.76 | Percentile across workers
material_spend_total | Material Spend Total | 497590.37 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 608708 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 9 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 2 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 7 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 17 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 111117.63 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719)
largest_material_savings | Largest Material Savings | 220 Roughin Material: $97,191 vs $158,260 budget ($-61,069)
top_vendor_spend | Top Vendor Spend | Keller Supply Company: $161,465 (35% of AP)
phases_over_budget | Phases Over Budget | 4 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 20 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 241 Water Main/Insulation Mat: $65,244 vs $44,525 budget (+$20,719)
largest_savings | Largest Savings | 120 Roughin Labor: $227,602 vs $360,476 budget ($-132,874)
total_jtd_cost | Total JTD Cost | 1138172 | SUM(actual) expense codes
total_budget | Total Current Budget | 1549924.06 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 73.43% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 411752.06 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 27.3984 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 142.8227 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array