## Overview
Job #2045 · GRE Construction Notch Apartments (Newcastle)
Cortex JCR v2 • GRE (customer 2045SH) • 13800 Newcastle Golf Club Road, Newcastle, WA 98059 • Owner: Newcastle II LLC
PROJECT OVERVIEW
Project Job # | 2045 |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | GRE Notch Apartments |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Notch Apartments — 187-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | GRE |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2045SH |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | Newcastle II LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Eric Bentler |  | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
GC Superintendent | Victor Vo |  | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
GC PE | N/A |  | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314) |  | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
Jobsite Location | 13800 Newcastle Golf Club Road, Newcastle, WA 98059 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 1804 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) |  | Notch Apartments project info.pdf
Contract Type | Lump Sum |  | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
Unit Count | 187 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-09 start → 2019-12 (27 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2110205 |  | 972033 | 1138172 | 14775
Original $1,898,200.00 + ($212,005.00) COs (11.17%) |  | 46.1% margin | 53.9% of revenue | 39 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
187-unit mixed-use (102 Type B + 6 Type A/ADA) at 13800 Newcastle Golf Club Road, Newcastle, WA 98059, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: GRE (2045SH); Owner: Newcastle II LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: Eric Bentler (GC PM) · Victor Vo (GC Sup) · TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) (Architect) · Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314) (OWP signatory).
SOURCES
Canonical financial source: 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $2,110,205.00 / Expenses $1,138,172.00 / Net $972,033.00 / Retainage $105,510.25
Source breakdown (derived): PR $615,682.10 · AP $460,396.87 · GL $62,093.03
Contract: Lump Sum $1,898,200.00 → $2,110,205.00
Change Orders (executed): $212,005.00 net across 7 COs (CO log in enriched meta)
Project Team: Eric Bentler (PM) · Victor Vo (Sup) · TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) · Newcastle II LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | GRE
GC PM | Extracted | Eric Bentler
GC Superintendent | Extracted | Victor Vo
GC PE | N/A | N/A
Owner | Extracted | Newcastle II LLC
Architect | Extracted | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP)
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314)

## Budget vs Actual
Budget vs Actual
All 25 cost codes from JDR. Contract $1,898,200 → $2,110,205.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 12640 | 13040 | 9511.5 | -3528.5 | 72.94% | 183.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 19750 | 20150 | 13778 | -6372 | 68.38% | 254.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 23250 | 44430 | 31316 | -13114 | 70.48% | 1098 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 31020 | 42943 | 24709.25 | -18233.75 | 57.54% | 937.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 5250 | 6120 | 5231 | -889 | 85.47% | 155 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 342805 | 360476 | 227602.48 | -132873.52 | 63.14% | 8560.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 70680 | 71030 | 67247 | -3783 | 94.67% | 2528.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 23050 | 29480 | 21040.5 | -8439.5 | 71.37% | 698.5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 5250 | 8250 | 4376 | -3874 | 53.04% | 125 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 15530 | 29830 | 14535.79 | -15294.21 | 48.73% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 30440 | 34850 | 15918.41 | -18931.59 | 45.68% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 4500 | 5718 | 4323.42 | -1394.58 | 75.61% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 153390 | 158260 | 97191 | -61069 | 61.41% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 274850 | 325525 | 293213.41 | -32311.59 | 90.07% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 0 | 0 | 63.72 | 63.72 |  |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 34700 | 44525 | 65243.62 | 20718.62 | 146.5% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 7000 | 10000 | 7101 | -2899 | 71.01% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 |  |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 500 | 3412 | 2912 | 682.4% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 25000 | 25000 | 16078.25 | -8921.75 | 64.31% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 3500 | 3800 | 4998.15 | 1198.15 | 131.5% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 1000 | 1000 | 652.9 | -347.1 | 65.29% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 242030.68 | 269409.24 | 179641.55 | -89767.69 | 66.68% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 40827.67 | 45587.82 | 30987.05 | -14600.77 | 67.97% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1898200 | -2110205 | -2110205 | 0 | 100% |  | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -531236.65 | -560280.94 | -972033 | -411752.06 |  | 14541

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,141,142 | 404811.73 | 35.57% | 19.18% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 497590.37 | 43.72% | 23.58% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,607 | 25141.3 | 2.209% | 1.191% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 179641.55 | 15.78% | 8.513% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 30987.05 | 2.723% | 1.468% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 1138172 | 100% | 53.94%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1231KS | Keller Supply Company | 161465.23 | 40 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 90006.18 | 133 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 88591.11 | 46 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 53281.96 | 41 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 31781 | 7 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 16078.25 | 4 | Engineering (601) | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 4798.91 | 11 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2045RS | Rosen Supply Company, Inc. $Notch | 4412.58 | 2 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 3186 | 1 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 3162 | 5 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7423OC | Old Castle Infrastructure, Inc. | 1971 | 1 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3018TR | Travelers | 445 | 1 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 357.8 | 2 | Plumbing / Supplies | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 322.95 | 6 | Credit Card (mixed) | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 250 | 2 | Testing subcontractor | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 199.24 | 1 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1978FC | Fastenal Company | 87.66 | 1 | Uncategorized | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 460396.87 | 304

## Crew & Labor
Crew & Labor — Worker Roster
All 39 unique payroll workers. OWP signatory: Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
EI74 | Eisenhauer, Tommy J | 2043 | 51043.75 | 24.9847 | 53 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 1516.5 | 57589 | 37.9749 | 42 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DR04 | Draves, Steven W | 1165 | 30787.5 | 26.427 | 31 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI84 | Rivera, Eli P | 1130 | 32087 | 28.3956 | 31 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU05 | Hubbard, Justin A | 901.5 | 22348 | 24.7898 | 25 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PO73 | Portillo Soriano, Walter A | 804 | 16376 | 20.3682 | 22 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA46 | Galdamez, Dagoberto A | 702.5 | 19101.5 | 27.1907 | 19 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO87 | Lovo, German G | 645 | 16039.5 | 24.8674 | 24 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 521.5 | 8915.5 | 17.0959 | 16 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DE45 | de la Torre, Kevin A | 516.5 | 8776.5 | 16.9923 | 13 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CH20 | Chevez, Herson G | 468.5 | 9494 | 20.2647 | 13 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
QU35 | Quintanilla, Esteban R | 442.5 | 18652.5 | 42.1525 | 27 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LI49 | Lima Romero, Melvin A | 405.5 | 13480.5 | 33.2441 | 11 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 398 | 7562 | 19 | 15 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 381.5 | 12222.75 | 32.0387 | 13 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 341 | 17439.5 | 51.1422 | 90 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 296.5 | 6497.5 | 21.914 | 13 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 295.5 | 9392.5 | 31.7851 | 13 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 205.5 | 3360 | 16.3504 | 9 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 170 | 6120 | 36 | 8 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 167 | 8302 | 49.7126 | 28 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 160 | 4640 | 29 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 149.5 | 2691 | 18 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE54 | Benites Portillo, Marvin E | 133 | 2992 | 22.4962 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GU17 | Guerrero, Ali A | 108 | 1836 | 17 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE71 | Serrano, Jeremiah G | 105.5 | 1688 | 16 | 4 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TH59 | Thompson, Harley J | 98 | 1616 | 16.4898 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 97 | 5850 | 60.3093 | 49 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 88 | 288 | 3.2727 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO69 | Cornejo Orellana, Carlos E | 75 | 1425 | 19 | 5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 66 | 2352 | 35.6364 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MU70 | Murphy, Darray E | 63 | 1134 | 18 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 30 | 810 | 27 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 30 | 1507 | 50.2333 | 12 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ES09 | Escalante Escobar, Boanerge | 20 | 360 | 18 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 20 | 0 | 0 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA83 | Gauthier, Dillon R | 8 | 136 | 17 | 1 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 5 | 105 | 21 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 2 | 36 | 18 | 1 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 14775 | 405053.5

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 39 | Unique payroll IDs | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 14775 | Sum of labor codes | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 405053.5 | Sum of labor codes | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 27.4148 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 13.83% | EI74 Eisenhauer, Tommy J (2043 hrs) | Derived
Top 5 Workers Hours Share | 45.73% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 60.3093 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 378.8462 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 16.1795 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 187 units (1804 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 142.8227 | USD/hr
Profit per Labor Hour | 65.789 | USD/hr
Labor Cost per Hour (blended) | 27.3984 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 55.9263 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 8560.5 | hrs
Finish Hours (code 130) | 2528.5 | hrs
Rough-in % of Total Hours | 58.87% | %
Gross Margin | 46.06% | %
Labor % of Revenue | 19.18% | %
Material % of Revenue | 23.58% | %
Direct Cost Ratio | 53.94% | % | All exp/Rev
Revenue per Unit (187) | 11284.5187 | USD | 187 units
Labor Hours per Unit | 79.0107 | hrs
Labor Cost per Unit | 2164.7686 | USD
Material Cost per Unit | 2660.9111 | USD
Direct Cost per Unit | 6086.4813 | USD
Rough-in Hours per Unit | 45.7781 | hrs
Revenue per Fixture | 1169.7367 | USD | 1804 fixtures
Hours per Fixture | 8.1901 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-10-02 | GRE | Lump Sum Subcontract | Closed | Notch Apartments plumbing (187 units, 7 stories) — per Div 22 | 1898200 | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
CO-NET | — | GRE | Change Orders (executed, 7 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 212005 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 2110205

## Billing & SOV
Billing & Schedule of Values
301 invoices to GRE. Retainage $105,510.25.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
549 | 01/18/19 | -245200 | -12260 | 5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
565 | 02/20/19 | -147750 | -7387.5 | 5 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
685 | 03/20/19 | -169690 | -8484.5 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
608 | 04/19/19 | -122860 | -6143 | 4 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
550 | 04/20/18 | -14000 | -700 | 1 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
509 | 05/20/19 | -37212 | -1860.6 | 7 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
610 | 06/19/19 | -125540 | -6277 | 4 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
675 | 06/20/18 | -17300 | -865 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | 07/19/19 | -24865 | -1243.25 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
528 | 07/20/18 | -43550 | -2177.5 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
593 | 08/20/18 | -221395 | -11069.75 | 7 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
138 | 08/20/18 | 221395 | 11069.75 | 7 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
139 | 08/20/18 | -192395 | -9619.75 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
748 | 08/20/19 | -113935 | -5696.75 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
564 | 09/20/19 | -36303 | -1815.15 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
536 | 10/18/19 | -4265 | -213.25 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
531 | 10/19/18 | -143255 | -7162.75 | 3 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
530 | 11/16/18 | -212655 | -10632.75 | 6 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
171 | 12/11/18 | -399120 | -19956 | 7 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
481 | 12/13/19 | -60310 | -3015.5 | 2 | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -2110205 | -105510.25

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $972,033.00 on $2,110,205.00 revenue = 46.1% gross margin. | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,898,200.00 → final $2,110,205.00 = $+212,005.00 net (11.17%) across 7 executed COs. | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $404,811.73 (19.2% of rev) across 14,775 hrs and 39 workers. Blended wage $27.40/hr. | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$425,125.48 (92% of AP). Top vendor: Keller Supply Company ($161,465.23). | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $105,510.25 — outstanding as of report date. | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 8,560 hrs (59% of labor hours). | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $293,213.41 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Eisenhauer, Tommy J = 2,043 hrs (14% of total). | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Notch Apartments — 187-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 13800 Newcastle Golf Club Road, Newcastle, WA 98059. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2045 | Profile | OWP job ID | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | GRE Construction Notch Apartments (Newcastle) | Profile |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | GRE | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | Newcastle II LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) | Profile |  | Verified | Notch Apartments project info.pdf
Location | location | 13800 Newcastle Golf Club Road, Newcastle, WA 98059 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Mid-rise multi-family apartments (187 residential units: 179 Type B + 8 Type A ADA) with L1 lobby/lounge + L2 leasing office + rooftop deck amenity. Post-tension deck construction with Hydroflame sleeves. | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Eric Bentler | Profile |  | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
GC Sup | gc_sup | Victor Vo | Profile |  | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314) | Profile |  | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-10-02 | Profile |  | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
Work Start | start_date | 2017-09 | Profile |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-12 | Profile |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 27 | Profile |  | Verified | Derived
Unit Count | unit_count | 187 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 1804 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 1898200 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 2110205 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 212005 | Financial | 7 executed | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 11.17% | Financial |  | Verified | Derived
Revenue | revenue | 2110205 | Financial | AR total | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 1138172 | Financial | JDR Expenses | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 972033 | Financial | Rev - Exp | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 46.06% | Financial |  | Verified | Derived
Retainage | retainage | 105510.25 | Financial | JDR AR retainage | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 404811.73 | Labor | Codes 100-151 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 497590.37 | Material | Codes 210-245 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 25141.3 | Financial | Codes 600-607 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 179641.55 | Labor | Code 995 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 30987.05 | Labor | Code 998 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 14775 | Labor | Sum labor codes | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 39 | Labor | Unique PR IDs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 27.3984 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 55.9263 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 8560.5 | Labor | Code 120 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 2528.5 | Labor | Code 130 | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 142.8227 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 65.789 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 11284.5187 | Productivity | 187 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 6086.4813 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 79.0107 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 1169.7367 | Productivity | 1804 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 19.18% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 23.58% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 17 | Material |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 20 | Billing |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 13.83% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 45.73% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 25 | Structure |  | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 7 | Documents |  | Verified | CO log
COR Count | cor_count | 8 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 14 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 12 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 246 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1231KS | Keller Supply Company | 161465.23 | 40 | 35.07% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1380RS | Rosen Supply Kirkland | 90006.18 | 133 | 19.55% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1175FE | Ferguson Enterprises, Inc. #3007 | 88591.11 | 46 | 19.24% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1130CS | Consolidated Supply Co. | 53281.96 | 41 | 11.57% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 5560CH | California Hydronics Corp | 31781 | 7 | 6.903% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1625FE | Franklin Engineering | 16078.25 | 4 | 3.492% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 2713AR | Ahern Rentals | 4798.91 | 11 | 1.042% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 2045RS | Rosen Supply Company, Inc. $Notch | 4412.58 | 2 | 0.9584% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1609QC | Quality Concrete Products, Inc. $32 | 3186 | 1 | 0.692% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 3181SC | Scan2Core, Inc. | 3162 | 5 | 0.6868% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 7423OC | Old Castle Infrastructure, Inc. | 1971 | 1 | 0.4281% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 3018TR | Travelers | 445 | 1 | 0.09666% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 5621HD | Core & Main LP $HD Supply Waterworks | 357.8 | 2 | 0.07772% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1234CO | Capital One Credit Card | 322.95 | 6 | 0.07015% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1421RA | R.A. Brown Backflow Testing | 250 | 2 | 0.0543% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1799AW | AllWest Underground, Inc. | 199.24 | 1 | 0.04328% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1978FC | Fastenal Company | 87.66 | 1 | 0.01904% | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 460396.87 | 304

## Change Log
Change Log — Master Register
Contract, 7 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-10-02 | Prime subcontract — Lump Sum $1,898,200.00 | GRE | 1898200 | Executed | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/13/19 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $105,510.25 (outstanding) | GC | 0 | Outstanding | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 212005 | JDR-implied net CO impact | $1,898,200 → $2,110,205 (7 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -191107.27 | Labor variance vs revised budget | 39 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -111117.63 | Material procurement variance | 17 vendors
Overhead | 600,601,602,603,604,607 | -5158.7 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -104368.46 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -199747.06
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 7 | 212005 | Aggregate executed COs
Sub (OWP) labor performance | 9 | -191107.27 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -111117.63 | 17 vendors
OWP burden accrual | 2 | -104368.46 | Payroll burden + tax
OWP overhead | 4 | -5158.7 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 11.17% | ±10% | WATCH | +11.17% net (7 COs)
Labor % of Revenue | 19.18% | <30% | HEALTHY | 19.2%
GL Overhead % of Revenue | 2.943% | <5% | HEALTHY | 2.9%
Vendor Concentration (Top 5) | 92.34% | <95% | HEALTHY | Top 5 = 92% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 46.06% | >30% | HEALTHY | 46.1%
Labor Hrs Total | 14775 | varies | INFO | 14,775 hrs, 39 workers
Worker Concentration (top 1) | 13.83% | <25% | HEALTHY | 13.8% (Eisenhauer, Tommy J)
Rough-in Labor Share | 58.87% | 40-65% | HEALTHY | 59%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $105,510.25
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 46.06% | Actual | Job closed | 46.1%
Retainage collection | $105,510.25 | Outstanding | Legacy | Outstanding
Unit-level economics | $11,285/unit rev, $5,198/unit profit | Verified | 187 units | Mid-rise multi-family apartments (187 residential units: 179 Type B + 8 Type A ADA) with L1 lobby/lounge + L2 leasing office + rooftop deck amenity. Post-tension deck construction with Hydroflame sleeves.

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2045 | id | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | GRE Construction Notch Apartments (Newcastle) | text | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | GRE | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | Newcastle II LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans (Franklin Notch Apartments folder references Franklin Engineering MEP) | text | Benchmark KPIs | Verified | Notch Apartments project info.pdf
6 | location | Location | 13800 Newcastle Golf Club Road, Newcastle, WA 98059 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Mid-rise multi-family apartments (187 residential units: 179 Type B + 8 Type A ADA) with L1 lobby/lounge + L2 leasing office + rooftop deck amenity. Post-tension deck construction with Hydroflame sleeves. | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Eric Bentler | text | Benchmark KPIs | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Victor Vo | text | Benchmark KPIs | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7927, 10/02/2017; miked@owpllc.net / 425.968.8314) | text | Benchmark KPIs | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-10-02 | date | Benchmark KPIs | Verified | 2045-Shelter Holdings subcontract 7927 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-09 | date | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-12 | date | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 27 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 187 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 1804 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 1898200 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 2110205 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 212005 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 11.17% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 2110205 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 1138172 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 972033 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 46.06% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 105510.25 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 404811.73 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 497590.37 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 25141.3 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 179641.55 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 30987.05 | USD | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 14775 | hours | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 39 | count | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 27.3984 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 55.9263 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 8560.5 | hours | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 2528.5 | hours | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 142.8227 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 65.789 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 11284.5187 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 6086.4813 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 79.0107 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 1169.7367 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 19.18% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 23.58% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 17 | count | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 20 | count | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 13.83% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 45.73% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 25 | count | Benchmark KPIs | Verified | 2045 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 7 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 8 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 14 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 12 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 246 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 2110205 | 2110205 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 1138172 | 1138172 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 972033 | 972033 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 2110205 | 2110205 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 14775 | 14775 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 212005 | 212005 | 0 | TIES | 11↔Derived
7 | Worker count | 39 | 39 | 0 | TIES | 5↔1
8 | Cost code count | 25 | 25 | 0 | TIES | 2↔16