## Overview
OWP JOB 2046 — MARPAC 4218 ROOSEVELT
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$1,721,867 |  | $971,411 |  | $750,456 |  | 12,690
Billed to date (Sage AR) |  | 56.4% of revenue |  | 43.6% margin |  | 32 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 439190 | 349617.68 | 89572.32 | 79.61% | 35.99%
Material | 493642 | 378784.06 | 114857.94 | 76.73% | 38.99%
Overhead | 67182 | 60959.29 | 6222.71 | 90.74% | 6.275%
Burden | 228335.71 | 182049.5 | 46286.21 | 79.73% | 18.74%
TOTAL (expense codes) | 1228349.71 | 971410.53 | 256939.18 | 79.08% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 532143.25 | 54.78% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 400106.03 | 41.19% | Material + subcontractor spend
GL (General Ledger) | 39161.25 | 4.031% | Misc adjustments + deposits
AR (Billings, credit) | -1721867 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2046
Project identity + metadata enriched from GDrive close-out package (4218 Roosevelt Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2046 | JDR cover page
job_name | Marpac 4218 Roosevelt | 4218 Roosevelt Apartments project info PDF
job_name_long | Marpac 4218 Roosevelt Apartments (Marpac Job# 17-10) | 4218 Roosevelt Apartments project info PDF
general_contractor | Marpac | Signed subcontract 17-10 — Shelter Holdings / G&K Investment LP
owner | G&K Investment LP | Signed subcontract §A.a — G&K Investment LP
architect | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) | Contract counterparty: G&K Investment LP
location | 4218 Roosevelt Way NE, Seattle, WA 98105 | Signed subcontract + permit records
project_type | Mid-rise mixed-use apartments (residential + ground-level retail + garage podium): 120 residential units (113 Type B + 7 Type A ADA) plus L1 exercise/amenity + L1 retail + L7 roof deck. Post-tension deck construction with Hydroflame/ProSet sleeves. | Scope doc + submittal TOC (7-story mixed-use + 2 parking levels)
unit_count | 120 | Plan drawings: 7-story, 120 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 734 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from Marpac 4218 Roosevelt Job Ticket 02/14/2019 (final revision): 113 Gerber 21-912 std toilets + 7 Gerber 21-918 ADA toilets + 120 Lenova PU-01-W lavs + 94 Aquatic 2603SMTE std tub/showers + 7 Aquatic ADA + 18 Best Bath LSS4038A5T + 7 Moen ADA wall bars + 104 Lenova Aurora kitchen sinks + 6 Elkay ADA kit sinks + 110 DW roughin + 110 washer roughin = 696 resident. Common areas (mop + 2 ADA toilets + 2 Kohler lavs + 1 Elkay sink) = 6. Building systems (8 Woodford hose bibs + 4 Bock WHs + expansion tank + 2 circ pumps + Flowtherm booster + 3 Watts backflows + irrigation POC + NDS trench + 4 Quality Concrete basins + 4 sched-40 drain segments + misc park drains) ≈ 32. Total ≈ 734. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 6 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-09 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2019-12 | Final pay app 12/13/2019
duration_months | 27 | start → end
contract_signed | 2017-09-11 | Signed subcontract — Richard Donelson 9/11/17
permit_jurisdiction | City of Seattle (DCI) | City of Seattle (DCI) permit (Seattle DCI plumbing + gas + backflow)
permits_issued | Plumbing permit; Gas permit (PSE natural gas worksheet on file); Backflow permit; Inspection request log | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2046 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2046
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 1648500 | Code 999 original (negated)
current_contract_budget | 1721867 | Code 999 current (negated)
revenue_ar_billed | 1721867 | Sum of AR line items (abs)
retainage_outstanding | 86093.35 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 1175261 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 1228349.71 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 53088.71 | Revised − Original across expense codes
direct_cost | 971410.53 | PR + AP + GL totals
net_profit | 750456.47 | abs(revenue) − direct_cost
gross_margin_pct | 43.58% | net / revenue

## Cost Categories
COST CATEGORIES — 2046
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 11 | 426875 | 439190 | 349617.68 | 89572.32 | 79.61% | PENDING (needs unit_count)
Material | 8 | 459229 | 493642 | 378784.06 | 114857.94 | 76.73% | PENDING (needs unit_count)
Overhead | 5 | 67182 | 67182 | 60959.29 | 6222.71 | 90.74% | PENDING (needs unit_count)
Burden | 2 | 221975 | 228335.71 | 182049.5 | 46286.21 | 79.73% | PENDING (needs unit_count)
Revenue | 1 | -1648500 | -1721867 | -1721867 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 13750 | 14050 | -10509 | 3541 | 0 | 0 | 69 | 0 | 0 | 25.2% | UNDER
101 | Takeoff & Purchase Labor | Labor | 19250 | 19700 | -9983 | 9717 | 0 | 0 | 172 | 0 | 0 | 49.32% | UNDER
110 | Underground Labor | Labor | 15775 | 16585 | -13670 | 2915 | 0 | 0 | 82.5 | 0 | 0 | 17.58% | UNDER
111 | Garage Labor | Labor | 28850 | 31010 | -10008 | 21002 | 0 | 0 | 745 | 4 | 0 | 67.73% | UNDER
112 | Canout Labor | Labor | 11285 | 11585 | -5396.5 | 6188.5 | 0 | 0 | 159 | 18.5 | 0 | 53.42% | UNDER
120 | Roughin Labor | Labor | 244210 | 248785 | -49558.25 | 199226.75 | 0 | 0 | 7088.5 | 326 | 0 | 80.08% | UNDER
130 | Finish Labor | Labor | 35160 | 35880 | 690 | 36570 | 0 | 0 | 1002.5 | 50 | 0 | 101.9% | ON
140 | Gas Labor | Labor | 11000 | 11000 | -5831.5 | 5168.5 | 0 | 0 | 127 | 9.5 | 0 | 46.99% | UNDER
141 | Water Main/Insulation Lab | Labor | 32855 | 34835 | 19790.61 | 54625.61 | 0 | 0 | 2223 | 110 | 0 | 156.8% | CRITICAL
142 | Mech Room Labor | Labor | 14740 | 15760 | -5819.18 | 9940.82 | 0 | 0 | 270.5 | 2 | 0 | 63.08% | UNDER
143 | Condensation Drains Labor | Labor | 0 | 0 | 722.5 | 722.5 | 0 | 0 | 20.5 | 0 | 0 | 0% | UNDER
210 | Underground Material | Material | 10575 | 10900 | -7499.91 | 3400.09 | 0 | 0 | 0 | 0 | 0 | 31.19% | UNDER
211 | Garage Material | Material | 26950 | 28736 | -18271.34 | 10464.66 | 0 | 0 | 0 | 0 | 0 | 36.42% | UNDER
212 | Canout Material | Material | 9150 | 9450 | -1907.03 | 7542.97 | 0 | 0 | 0 | 0 | 0 | 79.82% | UNDER
220 | Roughin Material | Material | 129520 | 130335 | -38651.29 | 91683.71 | 0 | 0 | 0 | 0 | 0 | 70.34% | UNDER
230 | Finish Material | Material | 226119 | 255231 | -56214.55 | 199016.45 | 0 | 0 | 0 | 0 | 0 | 77.98% | UNDER
240 | Gas Material | Material | 4000 | 4000 | -1329.18 | 2670.82 | 0 | 0 | 0 | 0 | 0 | 66.77% | UNDER
241 | Water Main/Insulation Mat | Material | 39165 | 39740 | 177.5 | 39917.5 | 0 | 0 | 0 | 0 | 0 | 100.4% | ON
242 | Mech Room Material | Material | 13750 | 15250 | 8837.86 | 24087.86 | 0 | 0 | 0 | 0 | 0 | 158% | CRITICAL
600 | Subcontractor | Overhead | 2500 | 2500 | 7909.7 | 10409.7 | 0 | 0 | 0 | 0 | 0 | 416.4% | CRITICAL
601 | Engineering/Plans | Overhead | 42000 | 42000 | -7495.22 | 34504.78 | 0 | 0 | 0 | 0 | 0 | 82.15% | UNDER
602 | Rental Equipment | Overhead | 4500 | 4500 | -4300.75 | 199.25 | 0 | 0 | 0 | 0 | 0 | 4.428% | UNDER
603 | Permits & Licenses | Overhead | 6682 | 6682 | 819 | 7501 | 0 | 0 | 0 | 0 | 0 | 112.3% | OVER
607 | Other Expenses | Overhead | 11500 | 11500 | -3155.44 | 8344.56 | 0 | 0 | 0 | 0 | 0 | 72.56% | UNDER
995 | Payroll Burden | Burden | 189319.06 | 194737.66 | -39470.87 | 155266.79 | 0 | 0 | 0 | 0 | 0 | 79.73% | UNDER
998 | Payroll Taxes | Burden | 32655.94 | 33598.05 | -6815.34 | 26782.71 | 0 | 0 | 0 | 0 | 0 | 79.72% | UNDER
999 | Sales | Revenue | -1648500 | -1721867 | 0 | -1721867 | 0 | -86093.35 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2046
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 3541 | 47 | 47 | 0 | 0 | 0 | Gerard, Jeffrey S ($3,316) | 01/04/19 | 12/28/18
101 | Takeoff & Purchase Labor | 9717 | 106 | 106 | 0 | 0 | 0 | Donelson, Richard T ($6,600) | 01/11/19 | 12/29/17
110 | Underground Labor | 2915 | 11 | 11 | 0 | 0 | 0 | Anderson, Richard P ($1,029) | 02/09/18 | 11/10/17
111 | Garage Labor | 21002 | 48 | 48 | 0 | 0 | 0 | Velasquez Cruz, Denis M ($5,152) | 03/08/19 | 09/14/18
112 | Canout Labor | 6188.5 | 26 | 26 | 0 | 0 | 0 | Waites, Thaddeus Z ($2,575) | 02/15/19 | 08/17/18
120 | Roughin Labor | 199226.75 | 306 | 306 | 0 | 0 | 0 | Garcia, Jordan X ($39,994) | 01/04/19 | 12/28/18
130 | Finish Labor | 36570 | 53 | 53 | 0 | 0 | 0 | Holmes, Anthony R ($18,690) | 03/15/19 | 12/07/18
140 | Gas Labor | 5168.5 | 12 | 12 | 0 | 0 | 0 | Waites, Thaddeus Z ($2,588) | 01/11/19 | 12/07/18
141 | Water Main/Insulation Lab | 54625.61 | 117 | 116 | 0 | 1 | 0 | Montenegro, Carlos E ($18,314) | 01/04/19 | 12/28/18
142 | Mech Room Labor | 9940.82 | 28 | 27 | 0 | 1 | 0 | Hubbard, Robert W ($5,246) | 01/18/19 | 08/12/19
143 | Condensation Drains Labor | 722.5 | 3 | 3 | 0 | 0 | 0 | Garcia, Jordan X ($576) | 03/09/18 | 03/15/19
210 | Underground Material | 3400.09 | 14 | 0 | 13 | 1 | 0 | Rosen Supply Company, Inc. $4218 Rooseve ($9,084) | 02/14/18 | 11/13/17
211 | Garage Material | 10464.66 | 27 | 0 | 7 | 20 | 0 | Rosen Supply Kirkland ($6,083) | 01/22/19 | 12/21/18
212 | Canout Material | 7542.97 | 14 | 0 | 4 | 10 | 0 | Req 4446 ($3,653) | 03/31/18 | 11/26/18
220 | Roughin Material | 91683.71 | 73 | 0 | 42 | 31 | 0 | Rosen Supply Kirkland ($69,130) | 01/07/19 | 12/21/18
230 | Finish Material | 199016.45 | 99 | 0 | 68 | 31 | 0 | Rosen Supply Kirkland ($115,527) | 01/03/19 | 12/14/18
240 | Gas Material | 2670.82 | 23 | 0 | 19 | 4 | 0 | Rosen Supply Kirkland ($2,670) | 01/14/19 | 12/21/18
241 | Water Main/Insulation Mat | 39917.5 | 48 | 0 | 30 | 18 | 0 | Consolidated Supply Co. ($32,533) | 01/11/19 | 12/21/18
242 | Mech Room Material | 24087.86 | 31 | 0 | 17 | 14 | 0 | Ferguson Enterprises, Inc. #3007 ($18,391) | 02/08/19 | 07/10/19
600 | Subcontractor | 10409.7 | 8 | 0 | 8 | 0 | 0 | Mechanical Resource Services, Inc. ($4,688) | 01/30/19 | 10/05/18
601 | Engineering/Plans | 34504.78 | 10 | 0 | 10 | 0 | 0 | Franklin Engineering ($34,285) | 01/05/18 | 11/22/17
602 | Rental Equipment | 199.25 | 1 | 0 | 1 | 0 | 0 | AllWest Underground, Inc. ($199) | 05/29/19 | 05/29/19
603 | Permits & Licenses | 7501 | 7 | 0 | 7 | 0 | 0 | Capital One Credit Card ($7,300) | 03/31/19 | 09/21/17
607 | Other Expenses | 8344.56 | 24 | 0 | 23 | 1 | 0 | Capital One Credit Card ($8,801) | 02/14/19 | 12/31/18
995 | Payroll Burden | 155266.79 | 755 | 755 | 0 | 0 | 0 | Garcia, Jordan X ($19,661) | 01/04/19 | 12/29/17
998 | Payroll Taxes | 26782.71 | 755 | 755 | 0 | 0 | 0 | Garcia, Jordan X ($3,391) | 01/04/19 | 12/29/17
999 | Sales | -1721867 | 124 | 0 | 0 | 0 | 124 | Marpac Construction, LLC $4218 Roosevelt ($2,296,277) | 01/18/19 | 12/14/18

## Transactions Detail
TRANSACTIONS DETAIL — 2,770 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 97762 | 0 | 0
100 | Supervision | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17892 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98002 | 0 | 0
100 | Supervision | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98215 | 0 | 0
100 | Supervision | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 918605 | 0 | 0
100 | Supervision | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98802 | 0 | 0
100 | Supervision | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18868 | 0 | 0
100 | Supervision | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18884 | 0 | 0
100 | Supervision | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
100 | Supervision | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19206 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
100 | Supervision | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20400 | 0 | 0
100 | Supervision | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20665 | 0 | 0
100 | Supervision | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20809 | 0 | 0
100 | Supervision | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21174 | 0 | 0
100 | Supervision | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21245 | 0 | 0
100 | Supervision | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90884 | 0 | 0
100 | Supervision | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91391 | 0 | 0
100 | Supervision | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21467 | 0 | 0
100 | Supervision | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21616 | 0 | 0
100 | Supervision | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21687 | 0 | 0
100 | Supervision | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20892 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21837 | 0 | 0
100 | Supervision | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21912 | 0 | 0
100 | Supervision | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 921984 | 0 | 0
100 | Supervision | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22057 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
100 | Supervision | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922269 | 0 | 0
100 | Supervision | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22343 | 0 | 0
100 | Supervision | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22301 | 0 | 0
100 | Supervision | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 922484 | 0 | 0
100 | Supervision | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922558 | 0 | 0
100 | Supervision | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 922910 | 0 | 0
100 | Supervision | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22982 | 0 | 0
100 | Supervision | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 923054 | 0 | 0
100 | Supervision | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 23125 | 0 | 0
100 | Supervision | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 923198 | 0 | 0
100 | Supervision | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 23273 | 0 | 0
100 | Supervision | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923346 | 0 | 0
100 | Supervision | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 23720 | 0 | 0
100 | Supervision | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923799 | 0 | 0
100 | Supervision | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923876 | 0 | 0
100 | Supervision | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924030 | 0 | 0
100 | Supervision | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24104 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 17514 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 19638 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 17826 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97955 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98001 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 98475 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 918605 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | -187.5 | 0 | -187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18867 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18868 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18954 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99426 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 19721 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99793 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20079 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20162 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 290232 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20300 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 920374 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20401 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 920518 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920519 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 20592 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20593 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20665 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 920737 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20808 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 20809 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20880 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90962 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91031 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91032 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 21173 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21174 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21245 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 90883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21467 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21615 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21616 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21686 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21687 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21836 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21837 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21911 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 921984 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922268 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22342 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22343 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922483 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922558 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922631 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22700 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 22768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922840 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 3 | 0 | 156 | 0 | 156 | 922910 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923053 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23124 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923346 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23420 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923496 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23568 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923798 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923799 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923875 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 924029 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 24103 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 24254 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 924329 | 0 | 0
110 | Underground Labor | PR | 3 | 11/01/17 | 11/03/17 | AN14 | Anderson, Richard P | 1 | 0 | 42 | 0 | 42 | 17827 | 0 | 0
110 | Underground Labor | PR | 150 | 11/08/17 | 11/10/17 | AN14 | Anderson, Richard P | 3.5 | 0 | 147 | 0 | 147 | 17893 | 0 | 0
110 | Underground Labor | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 18806 | 0 | 0
110 | Underground Labor | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 18872 | 0 | 0
110 | Underground Labor | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 17 | 0 | 748 | 0 | 748 | 18940 | 0 | 0
110 | Underground Labor | PR | 638 | 02/21/18 | 02/23/18 | KI55 | Kinssies, Jr, John E | 5 | 0 | 130 | 0 | 130 | 18972 | 0 | 0
110 | Underground Labor | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 18 | 0 | 756 | 0 | 756 | 19139 | 0 | 0
110 | Underground Labor | PR | 352 | 03/14/18 | 03/16/18 | KI55 | Kinssies, Jr, John E | 30 | 0 | 780 | 0 | 780 | 19173 | 0 | 0
110 | Underground Labor | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 2 | 0 | 84 | 0 | 84 | 19207 | 0 | 0
110 | Underground Labor | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 2 | 0 | 52 | 0 | 52 | 19241 | 0 | 0
110 | Underground Labor | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19508 | 0 | 0
111 | Garage Labor | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 19508 | 0 | 0
111 | Garage Labor | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 1 | 0 | 69 | 69 | 20238 | 0 | 0
111 | Garage Labor | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20238 | 0 | 0
111 | Garage Labor | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 1 | 0 | 42 | 0 | 42 | 20514 | 0 | 0
111 | Garage Labor | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20525 | 0 | 0
111 | Garage Labor | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 8 | 0 | 192 | 0 | 192 | 20585 | 0 | 0
111 | Garage Labor | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 9 | 0 | 378 | 0 | 378 | 20588 | 0 | 0
111 | Garage Labor | PR | 268 | 08/08/18 | 08/10/18 | RE96 | Reyes Cruz, Denis A | 16 | 0 | 400 | 0 | 400 | 20720 | 0 | 0
111 | Garage Labor | PR | 278 | 08/08/18 | 08/10/18 | VE42 | Velasquez Cruz, Denis M | 16 | 0 | 448 | 0 | 448 | 20730 | 0 | 0
111 | Garage Labor | PR | 279 | 08/08/18 | 08/10/18 | VE43 | Velasquez Cruz, Osman N | 16 | 0 | 320 | 0 | 320 | 20731 | 0 | 0
111 | Garage Labor | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20742 | 0 | 0
111 | Garage Labor | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 16 | 0 | 512 | 0 | 512 | 20760 | 0 | 0
111 | Garage Labor | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 8 | 0 | 128 | 0 | 128 | 20768 | 0 | 0
111 | Garage Labor | PR | 535 | 08/15/18 | 08/17/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 20792 | 0 | 0
111 | Garage Labor | PR | 545 | 08/15/18 | 08/17/18 | VE42 | Velasquez Cruz, Denis M | 32 | 0 | 896 | 0 | 896 | 20802 | 0 | 0
111 | Garage Labor | PR | 546 | 08/15/18 | 08/17/18 | VE43 | Velasquez Cruz, Osman N | 32 | 0 | 640 | 0 | 640 | 20803 | 0 | 0
111 | Garage Labor | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 18 | 0 | 756 | 0 | 756 | 20804 | 0 | 0
111 | Garage Labor | PR | 796 | 08/22/18 | 08/24/18 | RE96 | Reyes Cruz, Denis A | 32 | 0 | 800 | 0 | 800 | 20863 | 0 | 0
111 | Garage Labor | PR | 806 | 08/22/18 | 08/24/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 20873 | 0 | 0
111 | Garage Labor | PR | 807 | 08/22/18 | 08/24/18 | VE43 | Velasquez Cruz, Osman N | 32 | 0 | 640 | 0 | 640 | 20874 | 0 | 0
111 | Garage Labor | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 4.5 | 0 | 189 | 0 | 189 | 20875 | 0 | 0
111 | Garage Labor | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20896 | 0 | 0
111 | Garage Labor | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 8 | 0 | 256 | 0 | 256 | 20915 | 0 | 0
111 | Garage Labor | PR | 1050 | 08/29/18 | 08/31/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 20945 | 0 | 0
111 | Garage Labor | PR | 1060 | 08/29/18 | 08/31/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 20955 | 0 | 0
111 | Garage Labor | PR | 1061 | 08/29/18 | 08/31/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 20956 | 0 | 0
111 | Garage Labor | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 4.5 | 0 | 189 | 0 | 189 | 20957 | 0 | 0
111 | Garage Labor | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 8 | 0 | 256 | 0 | 256 | 20985 | 0 | 0
111 | Garage Labor | PR | 90 | 09/05/18 | 09/07/18 | RE96 | Reyes Cruz, Denis A | 32 | 0 | 800 | 0 | 800 | 21015 | 0 | 0
111 | Garage Labor | PR | 100 | 09/05/18 | 09/07/18 | VE42 | Velasquez Cruz, Denis M | 32 | 0 | 896 | 0 | 896 | 21025 | 0 | 0
111 | Garage Labor | PR | 101 | 09/05/18 | 09/07/18 | VE43 | Velasquez Cruz, Osman N | 32 | 0 | 640 | 0 | 640 | 21026 | 0 | 0
111 | Garage Labor | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 6 | 0 | 252 | 0 | 252 | 21027 | 0 | 0
111 | Garage Labor | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 24 | 0 | 600 | 0 | 600 | 21156 | 0 | 0
111 | Garage Labor | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 24 | 0 | 672 | 0 | 672 | 21167 | 0 | 0
111 | Garage Labor | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 24 | 0 | 480 | 0 | 480 | 21168 | 0 | 0
111 | Garage Labor | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 6 | 0 | 252 | 0 | 252 | 21169 | 0 | 0
111 | Garage Labor | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22987 | 0 | 0
111 | Garage Labor | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 20 | 0 | 960 | 0 | 960 | 23131 | 0 | 0
111 | Garage Labor | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23648 | 0 | 0
111 | Garage Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 8 | 0 | 264 | 0 | 264 | 23688 | 0 | 0
111 | Garage Labor | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 3 | 0 | 225 | 225 | 23803 | 0 | 0
111 | Garage Labor | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 5 | 0 | 250 | 0 | 250 | 23803 | 0 | 0
111 | Garage Labor | PR | 648 | 05/22/19 | 05/24/19 | MA71 | Martinez Reyes, Juan C | 37 | 0 | 1221 | 0 | 1221 | 23843 | 0 | 0
111 | Garage Labor | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23881 | 0 | 0
111 | Garage Labor | PR | 922 | 05/29/19 | 05/31/19 | MA71 | Martinez Reyes, Juan C | 16 | 0 | 528 | 0 | 528 | 23922 | 0 | 0
111 | Garage Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23958 | 0 | 0
111 | Garage Labor | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 3 | 0 | 99 | 0 | 99 | 23998 | 0 | 0
111 | Garage Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 24035 | 0 | 0
112 | Canout Labor | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19431 | 0 | 0
112 | Canout Labor | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 132 | 0 | 132 | 19582 | 0 | 0
112 | Canout Labor | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19654 | 0 | 0
112 | Canout Labor | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 1 | 0 | 66 | 66 | 19870 | 0 | 0
112 | Canout Labor | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 7 | 0 | 308 | 0 | 308 | 19870 | 0 | 0
112 | Canout Labor | PR | 799 | 05/23/18 | 05/25/18 | TA96 | Taylor, Evan R | 7 | 0 | 154 | 0 | 154 | 19928 | 0 | 0
112 | Canout Labor | PR | 802 | 05/23/18 | 05/25/18 | WA35 | Waites, Thaddeus Z | 10 | 0 | 410 | 0 | 410 | 19931 | 0 | 0
112 | Canout Labor | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 6 | 0 | 264 | 0 | 264 | 19941 | 0 | 0
112 | Canout Labor | PR | 66 | 05/30/18 | 06/01/18 | TA96 | Taylor, Evan R | 19 | 0 | 418 | 0 | 418 | 20000 | 0 | 0
112 | Canout Labor | PR | 69 | 05/30/18 | 06/01/18 | WA35 | Waites, Thaddeus Z | 19 | 0 | 779 | 0 | 779 | 20003 | 0 | 0
112 | Canout Labor | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 0 | 1 | 0 | 33 | 33 | 20071 | 0 | 0
112 | Canout Labor | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 8 | 0 | 176 | 0 | 176 | 20071 | 0 | 0
112 | Canout Labor | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20098 | 0 | 0
112 | Canout Labor | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 4 | 0 | 276 | 276 | 20238 | 0 | 0
112 | Canout Labor | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 0 | 6 | 0 | 216 | 216 | 20293 | 0 | 0
112 | Canout Labor | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 9 | 0 | 216 | 0 | 216 | 20293 | 0 | 0
112 | Canout Labor | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 0 | 6 | 0 | 378 | 378 | 20296 | 0 | 0
112 | Canout Labor | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 9 | 0 | 378 | 0 | 378 | 20296 | 0 | 0
112 | Canout Labor | PR | 10 | 07/04/18 | 07/06/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20307 | 0 | 0
112 | Canout Labor | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 23 | 0 | 552 | 0 | 552 | 20364 | 0 | 0
112 | Canout Labor | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 5 | 0 | 210 | 0 | 210 | 20367 | 0 | 0
112 | Canout Labor | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 10 | 0 | 240 | 0 | 240 | 20440 | 0 | 0
112 | Canout Labor | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 10 | 0 | 420 | 0 | 420 | 20443 | 0 | 0
112 | Canout Labor | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0.5 | 0 | 34.5 | 34.5 | 20742 | 0 | 0
112 | Canout Labor | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20742 | 0 | 0
112 | Canout Labor | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 256 | 0 | 256 | 22827 | 0 | 0
120 | Roughin Labor | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 19114 | 0 | 0
120 | Roughin Labor | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 1 | 0 | 45 | 0 | 45 | 19239 | 0 | 0
120 | Roughin Labor | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 132 | 0 | 132 | 19357 | 0 | 0
120 | Roughin Labor | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 18 | 0 | 756 | 0 | 756 | 20732 | 0 | 0
120 | Roughin Labor | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 138 | 0 | 138 | 20742 | 0 | 0
120 | Roughin Labor | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 16 | 0 | 512 | 0 | 512 | 20760 | 0 | 0
120 | Roughin Labor | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 8 | 0 | 128 | 0 | 128 | 20768 | 0 | 0
120 | Roughin Labor | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 19.5 | 0 | 819 | 0 | 819 | 20804 | 0 | 0
120 | Roughin Labor | PR | 765 | 08/22/18 | 08/24/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1280 | 0 | 1280 | 20832 | 0 | 0
120 | Roughin Labor | PR | 773 | 08/22/18 | 08/24/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 20840 | 0 | 0
120 | Roughin Labor | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 16 | 0 | 272 | 0 | 272 | 20850 | 0 | 0
120 | Roughin Labor | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 28 | 0 | 1176 | 0 | 1176 | 20875 | 0 | 0
120 | Roughin Labor | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20896 | 0 | 0
120 | Roughin Labor | PR | 1001 | 08/29/18 | 08/31/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 20897 | 0 | 0
120 | Roughin Labor | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 32 | 0 | 1024 | 0 | 1024 | 20915 | 0 | 0
120 | Roughin Labor | PR | 1028 | 08/29/18 | 08/31/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 20923 | 0 | 0
120 | Roughin Labor | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 32 | 0 | 1344 | 0 | 1344 | 20957 | 0 | 0
120 | Roughin Labor | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 138 | 0 | 138 | 20966 | 0 | 0
120 | Roughin Labor | PR | 42 | 09/05/18 | 09/07/18 | BE45 | Belcher, Jacob T | 32 | 0 | 544 | 0 | 544 | 20967 | 0 | 0
120 | Roughin Labor | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 24 | 0 | 768 | 0 | 768 | 20985 | 0 | 0
120 | Roughin Labor | PR | 67 | 09/05/18 | 09/07/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 20992 | 0 | 0
120 | Roughin Labor | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 25 | 0 | 1050 | 0 | 1050 | 21027 | 0 | 0
120 | Roughin Labor | PR | 272 | 09/12/18 | 09/14/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21107 | 0 | 0
120 | Roughin Labor | PR | 273 | 09/12/18 | 09/14/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21108 | 0 | 0
120 | Roughin Labor | PR | 292 | 09/12/18 | 09/14/18 | GA70 | Garcia, Jordan X | 32 | 0 | 1024 | 0 | 1024 | 21126 | 0 | 0
120 | Roughin Labor | PR | 299 | 09/12/18 | 09/14/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21133 | 0 | 0
120 | Roughin Labor | PR | 304 | 09/12/18 | 09/14/18 | KI55 | Kinssies, Jr, John E | 24 | 0 | 624 | 0 | 624 | 21138 | 0 | 0
120 | Roughin Labor | PR | 309 | 09/12/18 | 09/14/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21143 | 0 | 0
120 | Roughin Labor | PR | 315 | 09/12/18 | 09/14/18 | OB46 | O'Bleness, Caleb N | 16 | 0 | 464 | 0 | 464 | 21149 | 0 | 0
120 | Roughin Labor | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 16 | 0 | 400 | 0 | 400 | 21156 | 0 | 0
120 | Roughin Labor | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 16 | 0 | 448 | 0 | 448 | 21167 | 0 | 0
120 | Roughin Labor | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 16 | 0 | 320 | 0 | 320 | 21168 | 0 | 0
120 | Roughin Labor | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 32 | 0 | 1344 | 0 | 1344 | 21169 | 0 | 0
120 | Roughin Labor | PR | 487 | 09/19/18 | 09/21/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21179 | 0 | 0
120 | Roughin Labor | PR | 505 | 09/19/18 | 09/21/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1280 | 0 | 1280 | 21196 | 0 | 0
120 | Roughin Labor | PR | 512 | 09/19/18 | 09/21/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21203 | 0 | 0
120 | Roughin Labor | PR | 517 | 09/19/18 | 09/21/18 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1040 | 0 | 1040 | 21208 | 0 | 0
120 | Roughin Labor | PR | 522 | 09/19/18 | 09/21/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21213 | 0 | 0
120 | Roughin Labor | PR | 528 | 09/19/18 | 09/21/18 | OB46 | O'Bleness, Caleb N | 32 | 0 | 928 | 0 | 928 | 21219 | 0 | 0
120 | Roughin Labor | PR | 535 | 09/19/18 | 09/21/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21226 | 0 | 0
120 | Roughin Labor | PR | 546 | 09/19/18 | 09/21/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21237 | 0 | 0
120 | Roughin Labor | PR | 547 | 09/19/18 | 09/21/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21238 | 0 | 0
120 | Roughin Labor | PR | 548 | 09/19/18 | 09/21/18 | WA35 | Waites, Thaddeus Z | 28 | 0 | 1176 | 0 | 1176 | 21239 | 0 | 0
120 | Roughin Labor | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 138 | 0 | 138 | 21249 | 0 | 0
120 | Roughin Labor | PR | 671 | 09/26/18 | 09/28/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21250 | 0 | 0
120 | Roughin Labor | PR | 690 | 09/26/18 | 09/28/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21268 | 0 | 0
120 | Roughin Labor | PR | 697 | 09/26/18 | 09/28/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21275 | 0 | 0
120 | Roughin Labor | PR | 702 | 09/26/18 | 09/28/18 | KI55 | Kinssies, Jr, John E | 38 | 0 | 988 | 0 | 988 | 21280 | 0 | 0
120 | Roughin Labor | PR | 707 | 09/26/18 | 09/28/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21285 | 0 | 0
120 | Roughin Labor | PR | 713 | 09/26/18 | 09/28/18 | OB46 | O'Bleness, Caleb N | 40 | 0 | 1160 | 0 | 1160 | 21291 | 0 | 0
120 | Roughin Labor | PR | 720 | 09/26/18 | 09/28/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21298 | 0 | 0
120 | Roughin Labor | PR | 732 | 09/26/18 | 09/28/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21310 | 0 | 0
120 | Roughin Labor | PR | 733 | 09/26/18 | 09/28/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21311 | 0 | 0
120 | Roughin Labor | PR | 734 | 09/26/18 | 09/28/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21312 | 0 | 0
120 | Roughin Labor | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 5 | 0 | 230 | 0 | 230 | 21323 | 0 | 0
120 | Roughin Labor | PR | 35 | 10/03/18 | 10/05/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21324 | 0 | 0
120 | Roughin Labor | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 368 | 0 | 368 | 21332 | 0 | 0
120 | Roughin Labor | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 16 | 0 | 384 | 0 | 384 | 21333 | 0 | 0
120 | Roughin Labor | PR | 54 | 10/03/18 | 10/05/18 | GA70 | Garcia, Jordan X | 32 | 0 | 1120 | 0 | 1120 | 21342 | 0 | 0
120 | Roughin Labor | PR | 61 | 10/03/18 | 10/05/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 21349 | 0 | 0
120 | Roughin Labor | PR | 66 | 10/03/18 | 10/05/18 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1040 | 0 | 1040 | 21354 | 0 | 0
120 | Roughin Labor | PR | 71 | 10/03/18 | 10/05/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21359 | 0 | 0
120 | Roughin Labor | PR | 77 | 10/03/18 | 10/05/18 | OB46 | O'Bleness, Caleb N | 40 | 0 | 1160 | 0 | 1160 | 21365 | 0 | 0
120 | Roughin Labor | PR | 84 | 10/03/18 | 10/05/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21372 | 0 | 0
120 | Roughin Labor | PR | 96 | 10/03/18 | 10/05/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21384 | 0 | 0
120 | Roughin Labor | PR | 97 | 10/03/18 | 10/05/18 | VE43 | Velasquez Cruz, Osman N | 32 | 0 | 640 | 0 | 640 | 21385 | 0 | 0
120 | Roughin Labor | PR | 98 | 10/03/18 | 10/05/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21386 | 0 | 0
120 | Roughin Labor | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21396 | 0 | 0
120 | Roughin Labor | PR | 240 | 10/10/18 | 10/12/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21397 | 0 | 0
120 | Roughin Labor | PR | 250 | 10/10/18 | 10/12/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21408 | 0 | 0
120 | Roughin Labor | PR | 260 | 10/10/18 | 10/12/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21417 | 0 | 0
120 | Roughin Labor | PR | 267 | 10/10/18 | 10/12/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 21424 | 0 | 0
120 | Roughin Labor | PR | 272 | 10/10/18 | 10/12/18 | KI55 | Kinssies, Jr, John E | 24 | 0 | 624 | 0 | 624 | 21429 | 0 | 0
120 | Roughin Labor | PR | 277 | 10/10/18 | 10/12/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21434 | 0 | 0
120 | Roughin Labor | PR | 283 | 10/10/18 | 10/12/18 | OB46 | O'Bleness, Caleb N | 24 | 0 | 696 | 0 | 696 | 21440 | 0 | 0
120 | Roughin Labor | PR | 290 | 10/10/18 | 10/12/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21447 | 0 | 0
120 | Roughin Labor | PR | 302 | 10/10/18 | 10/12/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21459 | 0 | 0
120 | Roughin Labor | PR | 303 | 10/10/18 | 10/12/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21460 | 0 | 0
120 | Roughin Labor | PR | 304 | 10/10/18 | 10/12/18 | WA35 | Waites, Thaddeus Z | 29.5 | 0 | 1239 | 0 | 1239 | 21461 | 0 | 0
120 | Roughin Labor | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 0 | 6 | 0 | 153 | 153 | 21472 | 0 | 0
120 | Roughin Labor | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 40 | 0 | 680 | 0 | 680 | 21472 | 0 | 0
120 | Roughin Labor | PR | 448 | 10/17/18 | 10/19/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21482 | 0 | 0
120 | Roughin Labor | PR | 449 | 10/17/18 | 10/19/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21483 | 0 | 0
120 | Roughin Labor | PR | 458 | 10/17/18 | 10/19/18 | GA70 | Garcia, Jordan X | 32 | 0 | 1120 | 0 | 1120 | 21491 | 0 | 0
120 | Roughin Labor | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 0 | 6 | 0 | 144 | 144 | 21498 | 0 | 0
120 | Roughin Labor | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21498 | 0 | 0
120 | Roughin Labor | PR | 470 | 10/17/18 | 10/19/18 | KI55 | Kinssies, Jr, John E | 32 | 0 | 832 | 0 | 832 | 21503 | 0 | 0
120 | Roughin Labor | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 6 | 0 | 153 | 153 | 21508 | 0 | 0
120 | Roughin Labor | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21508 | 0 | 0
120 | Roughin Labor | PR | 481 | 10/17/18 | 10/19/18 | OB46 | O'Bleness, Caleb N | 40 | 0 | 1160 | 0 | 1160 | 21514 | 0 | 0
120 | Roughin Labor | PR | 488 | 10/17/18 | 10/19/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21521 | 0 | 0
120 | Roughin Labor | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 0 | 6 | 0 | 252 | 252 | 21534 | 0 | 0
120 | Roughin Labor | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21534 | 0 | 0
120 | Roughin Labor | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 0 | 6 | 0 | 180 | 180 | 21535 | 0 | 0
120 | Roughin Labor | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21535 | 0 | 0
120 | Roughin Labor | PR | 503 | 10/17/18 | 10/19/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21536 | 0 | 0
120 | Roughin Labor | PR | 706 | 10/24/18 | 10/26/18 | BA70 | Barnhart, Joseph N | 0 | 2 | 0 | 138 | 138 | 21546 | 0 | 0
120 | Roughin Labor | PR | 707 | 10/24/18 | 10/26/18 | BE45 | Belcher, Jacob T | 36 | 0 | 612 | 0 | 612 | 21547 | 0 | 0
120 | Roughin Labor | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 0 | 6 | 0 | 207 | 207 | 21556 | 0 | 0
120 | Roughin Labor | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21556 | 0 | 0
120 | Roughin Labor | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 0 | 6 | 0 | 216 | 216 | 21557 | 0 | 0
120 | Roughin Labor | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21557 | 0 | 0
120 | Roughin Labor | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 0 | 6 | 0 | 315 | 315 | 21565 | 0 | 0
120 | Roughin Labor | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21565 | 0 | 0
120 | Roughin Labor | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 0 | 6 | 0 | 144 | 144 | 21572 | 0 | 0
120 | Roughin Labor | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21572 | 0 | 0
120 | Roughin Labor | PR | 736 | 10/24/18 | 10/26/18 | KI55 | Kinssies, Jr, John E | 40 | 0 | 1040 | 0 | 1040 | 21576 | 0 | 0
120 | Roughin Labor | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 6 | 0 | 153 | 153 | 21581 | 0 | 0
120 | Roughin Labor | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21581 | 0 | 0
120 | Roughin Labor | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 0 | 6 | 0 | 225 | 225 | 21593 | 0 | 0
120 | Roughin Labor | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21593 | 0 | 0
120 | Roughin Labor | PR | 767 | 10/24/18 | 10/26/18 | VE42 | Velasquez Cruz, Denis M | 36 | 0 | 1008 | 0 | 1008 | 21607 | 0 | 0
120 | Roughin Labor | PR | 768 | 10/24/18 | 10/26/18 | VE43 | Velasquez Cruz, Osman N | 36 | 0 | 720 | 0 | 720 | 21608 | 0 | 0
120 | Roughin Labor | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 0 | 6 | 0 | 378 | 378 | 21609 | 0 | 0
120 | Roughin Labor | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 39 | 0 | 1638 | 0 | 1638 | 21609 | 0 | 0
120 | Roughin Labor | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 6 | 0 | 153 | 153 | 21620 | 0 | 0
120 | Roughin Labor | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 32 | 0 | 544 | 0 | 544 | 21620 | 0 | 0
120 | Roughin Labor | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 0 | 6 | 0 | 207 | 207 | 21628 | 0 | 0
120 | Roughin Labor | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21628 | 0 | 0
120 | Roughin Labor | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 0 | 6 | 0 | 216 | 216 | 21629 | 0 | 0
120 | Roughin Labor | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21629 | 0 | 0
120 | Roughin Labor | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 0 | 6 | 0 | 315 | 315 | 21638 | 0 | 0
120 | Roughin Labor | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21638 | 0 | 0
120 | Roughin Labor | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 10 | 0 | 160 | 0 | 160 | 21645 | 0 | 0
120 | Roughin Labor | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0.5 | 0 | 19.5 | 19.5 | 21650 | 0 | 0
120 | Roughin Labor | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 17.5 | 0 | 455 | 0 | 455 | 21650 | 0 | 0
120 | Roughin Labor | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 2 | 0 | 51 | 51 | 21655 | 0 | 0
120 | Roughin Labor | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 8 | 0 | 136 | 0 | 136 | 21655 | 0 | 0
120 | Roughin Labor | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 10 | 0 | 280 | 0 | 280 | 21660 | 0 | 0
120 | Roughin Labor | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 0 | 6 | 0 | 225 | 225 | 21666 | 0 | 0
120 | Roughin Labor | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21666 | 0 | 0
120 | Roughin Labor | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 0 | 6 | 0 | 252 | 252 | 21679 | 0 | 0
120 | Roughin Labor | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21679 | 0 | 0
120 | Roughin Labor | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 0 | 6 | 0 | 180 | 180 | 21680 | 0 | 0
120 | Roughin Labor | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21680 | 0 | 0
120 | Roughin Labor | PR | 72 | 10/31/18 | 11/02/18 | WA35 | Waites, Thaddeus Z | 36 | 0 | 1512 | 0 | 1512 | 21681 | 0 | 0
120 | Roughin Labor | PR | 188 | 11/07/18 | 11/09/18 | BE45 | Belcher, Jacob T | 38 | 0 | 646 | 0 | 646 | 21692 | 0 | 0
120 | Roughin Labor | PR | 196 | 11/07/18 | 11/09/18 | CR79 | Cruz Guzman, Joel A | 38 | 0 | 874 | 0 | 874 | 21700 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 0 | 8 | 0 | 288 | 288 | 21701 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21701 | 0 | 0
120 | Roughin Labor | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 0 | 6 | 0 | 315 | 315 | 21710 | 0 | 0
120 | Roughin Labor | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21710 | 0 | 0
120 | Roughin Labor | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 2 | 0 | 48 | 48 | 21717 | 0 | 0
120 | Roughin Labor | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 8 | 0 | 128 | 0 | 128 | 21717 | 0 | 0
120 | Roughin Labor | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 0 | 8 | 0 | 300 | 300 | 21739 | 0 | 0
120 | Roughin Labor | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21739 | 0 | 0
120 | Roughin Labor | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 0 | 8 | 0 | 336 | 336 | 21752 | 0 | 0
120 | Roughin Labor | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21752 | 0 | 0
120 | Roughin Labor | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 0 | 8 | 0 | 240 | 240 | 21753 | 0 | 0
120 | Roughin Labor | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21753 | 0 | 0
120 | Roughin Labor | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 0 | 8 | 0 | 504 | 504 | 21754 | 0 | 0
120 | Roughin Labor | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21754 | 0 | 0
120 | Roughin Labor | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21764 | 0 | 0
120 | Roughin Labor | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 0 | 8 | 0 | 276 | 276 | 21774 | 0 | 0
120 | Roughin Labor | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21774 | 0 | 0
120 | Roughin Labor | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 0 | 15.5 | 0 | 558 | 558 | 21775 | 0 | 0
120 | Roughin Labor | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21775 | 0 | 0
120 | Roughin Labor | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 0 | 15.5 | 0 | 813.75 | 813.75 | 21783 | 0 | 0
120 | Roughin Labor | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21783 | 0 | 0
120 | Roughin Labor | PR | 459 | 11/14/18 | 11/16/18 | GO56 | Gonzalez Hernandez, Josue | 0 | 7.5 | 0 | 326.25 | 326.25 | 21787 | 0 | 0
120 | Roughin Labor | PR | 461 | 11/14/18 | 11/16/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 7.5 | 0 | 225 | 225 | 21789 | 0 | 0
120 | Roughin Labor | PR | 464 | 11/14/18 | 11/16/18 | HU04 | Hubbard, Dustin R | 2 | 0 | 44 | 0 | 44 | 21792 | 0 | 0
120 | Roughin Labor | PR | 467 | 11/14/18 | 11/16/18 | KI55 | Kinssies, Jr, John E | 8 | 0 | 208 | 0 | 208 | 21795 | 0 | 0
120 | Roughin Labor | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 0 | 8 | 0 | 300 | 300 | 21812 | 0 | 0
120 | Roughin Labor | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21812 | 0 | 0
120 | Roughin Labor | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 0 | 8 | 0 | 336 | 336 | 21825 | 0 | 0
120 | Roughin Labor | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21825 | 0 | 0
120 | Roughin Labor | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 0 | 8 | 0 | 240 | 240 | 21826 | 0 | 0
120 | Roughin Labor | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21826 | 0 | 0
120 | Roughin Labor | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 15.5 | 0 | 976.5 | 976.5 | 21827 | 0 | 0
120 | Roughin Labor | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21827 | 0 | 0
120 | Roughin Labor | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 15.5 | 0 | -976.5 | -976.5 | 21827 | 0 | 0
120 | Roughin Labor | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | -1680 | 0 | -1680 | 21827 | 0 | 0
120 | Roughin Labor | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 15.5 | 0 | 976.5 | 976.5 | 21835 | 0 | 0
120 | Roughin Labor | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21835 | 0 | 0
120 | Roughin Labor | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 138 | 0 | 138 | 21843 | 0 | 0
120 | Roughin Labor | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 3.5 | 0 | 120.75 | 120.75 | 21852 | 0 | 0
120 | Roughin Labor | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21852 | 0 | 0
120 | Roughin Labor | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 0 | 3.5 | 0 | 126 | 126 | 21853 | 0 | 0
120 | Roughin Labor | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21853 | 0 | 0
120 | Roughin Labor | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 0 | 3.5 | 0 | 183.75 | 183.75 | 21861 | 0 | 0
120 | Roughin Labor | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1400 | 0 | 1400 | 21861 | 0 | 0
120 | Roughin Labor | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 4 | 0 | 104 | 0 | 104 | 21873 | 0 | 0
120 | Roughin Labor | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 3.5 | 0 | 131.25 | 131.25 | 21889 | 0 | 0
120 | Roughin Labor | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1000 | 0 | 1000 | 21889 | 0 | 0
120 | Roughin Labor | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 3.5 | 0 | 147 | 147 | 21902 | 0 | 0
120 | Roughin Labor | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1120 | 0 | 1120 | 21902 | 0 | 0
120 | Roughin Labor | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 3.5 | 0 | 105 | 105 | 21903 | 0 | 0
120 | Roughin Labor | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 800 | 0 | 800 | 21903 | 0 | 0
120 | Roughin Labor | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 25 | 0 | 625 | 0 | 625 | 21926 | 0 | 0
120 | Roughin Labor | PR | 844 | 11/28/18 | 11/30/18 | CR87 | Cruz Reyes, Jose | 35 | 0 | 910 | 0 | 910 | 21927 | 0 | 0
120 | Roughin Labor | PR | 853 | 11/28/18 | 11/30/18 | GA70 | Garcia, Jordan X | 24 | 0 | 864 | 0 | 864 | 21935 | 0 | 0
120 | Roughin Labor | PR | 881 | 11/28/18 | 11/30/18 | RE96 | Reyes Cruz, Denis A | 35 | 0 | 945 | 0 | 945 | 21963 | 0 | 0
120 | Roughin Labor | PR | 894 | 11/28/18 | 11/30/18 | VE42 | Velasquez Cruz, Denis M | 31 | 0 | 899 | 0 | 899 | 21976 | 0 | 0
120 | Roughin Labor | PR | 895 | 11/28/18 | 11/30/18 | VE43 | Velasquez Cruz, Osman N | 23 | 0 | 506 | 0 | 506 | 21977 | 0 | 0
120 | Roughin Labor | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 21 | 0 | 903 | 0 | 903 | 21978 | 0 | 0
120 | Roughin Labor | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 28 | 0 | 700 | 0 | 700 | 21999 | 0 | 0
120 | Roughin Labor | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 0 | 8 | 0 | 312 | 312 | 22000 | 0 | 0
120 | Roughin Labor | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 22000 | 0 | 0
120 | Roughin Labor | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 8 | 0 | 324 | 324 | 22035 | 0 | 0
120 | Roughin Labor | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 40 | 0 | 1080 | 0 | 1080 | 22035 | 0 | 0
120 | Roughin Labor | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1160 | 0 | 1160 | 22049 | 0 | 0
120 | Roughin Labor | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 2 | 0 | 66 | 66 | 22050 | 0 | 0
120 | Roughin Labor | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 880 | 0 | 880 | 22050 | 0 | 0
120 | Roughin Labor | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 34 | 0 | 1462 | 0 | 1462 | 22051 | 0 | 0
120 | Roughin Labor | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 8 | 0 | 516 | 516 | 22051 | 0 | 0
120 | Roughin Labor | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1440 | 0 | 1440 | 22060 | 0 | 0
120 | Roughin Labor | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 2 | 0 | 87 | 87 | 22063 | 0 | 0
120 | Roughin Labor | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22130 | 0 | 0
120 | Roughin Labor | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 144 | 0 | 144 | 22130 | 0 | 0
120 | Roughin Labor | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22130 | 0 | 0
120 | Roughin Labor | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 2 | 0 | 75 | 75 | 22140 | 0 | 0
120 | Roughin Labor | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22140 | 0 | 0
120 | Roughin Labor | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 0 | 2 | 0 | 78 | 78 | 22141 | 0 | 0
120 | Roughin Labor | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 22141 | 0 | 0
120 | Roughin Labor | PR | 290 | 12/12/18 | 12/14/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1440 | 0 | 1440 | 22149 | 0 | 0
120 | Roughin Labor | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 24 | 0 | 408 | 0 | 408 | 22155 | 0 | 0
120 | Roughin Labor | PR | 332 | 12/12/18 | 12/14/18 | VE42 | Velasquez Cruz, Denis M | 40 | 0 | 1160 | 0 | 1160 | 22191 | 0 | 0
120 | Roughin Labor | PR | 333 | 12/12/18 | 12/14/18 | VE43 | Velasquez Cruz, Osman N | 40 | 0 | 880 | 0 | 880 | 22192 | 0 | 0
120 | Roughin Labor | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 7 | 0 | 301 | 0 | 301 | 22193 | 0 | 0
120 | Roughin Labor | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 2 | 0 | 129 | 129 | 22193 | 0 | 0
120 | Roughin Labor | PR | 522 | 12/19/18 | 12/21/18 | CR87 | Cruz Reyes, Jose | 42 | 0 | 1092 | 0 | 1092 | 22213 | 0 | 0
120 | Roughin Labor | PR | 531 | 12/19/18 | 12/21/18 | GA70 | Garcia, Jordan X | 39 | 0 | 1404 | 0 | 1404 | 22221 | 0 | 0
120 | Roughin Labor | PR | 558 | 12/19/18 | 12/21/18 | RE96 | Reyes Cruz, Denis A | 42 | 0 | 1134 | 0 | 1134 | 22248 | 0 | 0
120 | Roughin Labor | PR | 572 | 12/19/18 | 12/21/18 | VE42 | Velasquez Cruz, Denis M | 42 | 0 | 1218 | 0 | 1218 | 22262 | 0 | 0
120 | Roughin Labor | PR | 713 | 12/26/18 | 12/28/18 | CR87 | Cruz Reyes, Jose | 24 | 0 | 624 | 0 | 624 | 22286 | 0 | 0
120 | Roughin Labor | PR | 721 | 12/26/18 | 12/28/18 | GA70 | Garcia, Jordan X | 24 | 0 | 864 | 0 | 864 | 22294 | 0 | 0
120 | Roughin Labor | PR | 749 | 12/26/18 | 12/28/18 | RE96 | Reyes Cruz, Denis A | 24 | 0 | 648 | 0 | 648 | 22322 | 0 | 0
120 | Roughin Labor | PR | 763 | 12/26/18 | 12/28/18 | VE42 | Velasquez Cruz, Denis M | 16 | 0 | 464 | 0 | 464 | 22336 | 0 | 0
120 | Roughin Labor | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 10 | 0 | 480 | 0 | 480 | 22346 | 0 | 0
120 | Roughin Labor | PR | 8 | 01/02/19 | 01/04/19 | BE45 | Belcher, Jacob T | 26 | 0 | 468 | 0 | 468 | 22348 | 0 | 0
120 | Roughin Labor | PR | 17 | 01/02/19 | 01/04/19 | CR79 | Cruz Guzman, Joel A | 26 | 0 | 650 | 0 | 650 | 22358 | 0 | 0
120 | Roughin Labor | PR | 18 | 01/02/19 | 01/04/19 | CR87 | Cruz Reyes, Jose | 26 | 0 | 676 | 0 | 676 | 22359 | 0 | 0
120 | Roughin Labor | PR | 26 | 01/02/19 | 01/04/19 | GA70 | Garcia, Jordan X | 26 | 0 | 936 | 0 | 936 | 22367 | 0 | 0
120 | Roughin Labor | PR | 32 | 01/02/19 | 01/04/19 | HO18 | Hoeg, Xavier A | 26 | 0 | 442 | 0 | 442 | 22373 | 0 | 0
120 | Roughin Labor | PR | 52 | 01/02/19 | 01/04/19 | RE96 | Reyes Cruz, Denis A | 26 | 0 | 702 | 0 | 702 | 22393 | 0 | 0
120 | Roughin Labor | PR | 66 | 01/02/19 | 01/04/19 | VE42 | Velasquez Cruz, Denis M | 8 | 0 | 232 | 0 | 232 | 22407 | 0 | 0
120 | Roughin Labor | PR | 67 | 01/02/19 | 01/04/19 | VE43 | Velasquez Cruz, Osman N | 24 | 0 | 528 | 0 | 528 | 22408 | 0 | 0
120 | Roughin Labor | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 1 | 0 | 72 | 72 | 22417 | 0 | 0
120 | Roughin Labor | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 3 | 0 | 144 | 0 | 144 | 22417 | 0 | 0
120 | Roughin Labor | PR | 216 | 01/09/19 | 01/11/19 | BE45 | Belcher, Jacob T | 40 | 0 | 720 | 0 | 720 | 22418 | 0 | 0
120 | Roughin Labor | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 600 | 0 | 600 | 22427 | 0 | 0
120 | Roughin Labor | PR | 226 | 01/09/19 | 01/11/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 22428 | 0 | 0
120 | Roughin Labor | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 24 | 0 | 864 | 0 | 864 | 22436 | 0 | 0
120 | Roughin Labor | PR | 240 | 01/09/19 | 01/11/19 | HO18 | Hoeg, Xavier A | 40 | 0 | 680 | 0 | 680 | 22442 | 0 | 0
120 | Roughin Labor | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 24 | 0 | 696 | 0 | 696 | 22457 | 0 | 0
120 | Roughin Labor | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 0 | 1 | 0 | 72 | 72 | 22490 | 0 | 0
120 | Roughin Labor | PR | 470 | 01/16/19 | 01/18/19 | BE45 | Belcher, Jacob T | 40 | 0 | 720 | 0 | 720 | 22491 | 0 | 0
120 | Roughin Labor | PR | 480 | 01/16/19 | 01/18/19 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22501 | 0 | 0
120 | Roughin Labor | PR | 481 | 01/16/19 | 01/18/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 22502 | 0 | 0
120 | Roughin Labor | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 37 | 0 | 1332 | 0 | 1332 | 22510 | 0 | 0
120 | Roughin Labor | PR | 495 | 01/16/19 | 01/18/19 | HO18 | Hoeg, Xavier A | 16 | 0 | 272 | 0 | 272 | 22516 | 0 | 0
120 | Roughin Labor | PR | 510 | 01/16/19 | 01/18/19 | MO56 | Montenegro, Carlos E | 40 | 0 | 1160 | 0 | 1160 | 22531 | 0 | 0
120 | Roughin Labor | PR | 729 | 01/23/19 | 01/25/19 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22574 | 0 | 0
120 | Roughin Labor | PR | 730 | 01/23/19 | 01/25/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 22575 | 0 | 0
120 | Roughin Labor | PR | 738 | 01/23/19 | 01/25/19 | GA70 | Garcia, Jordan X | 40 | 0 | 1440 | 0 | 1440 | 22583 | 0 | 0
120 | Roughin Labor | PR | 744 | 01/23/19 | 01/25/19 | HO18 | Hoeg, Xavier A | 40 | 0 | 680 | 0 | 680 | 22589 | 0 | 0
120 | Roughin Labor | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 2 | 0 | 46 | 0 | 46 | 22591 | 0 | 0
120 | Roughin Labor | PR | 759 | 01/23/19 | 01/25/19 | MO56 | Montenegro, Carlos E | 40 | 0 | 1160 | 0 | 1160 | 22604 | 0 | 0
120 | Roughin Labor | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 38 | 0 | 684 | 0 | 684 | 22637 | 0 | 0
120 | Roughin Labor | PR | 17 | 01/30/19 | 02/01/19 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22646 | 0 | 0
120 | Roughin Labor | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 24 | 0 | 624 | 0 | 624 | 22647 | 0 | 0
120 | Roughin Labor | PR | 26 | 01/30/19 | 02/01/19 | GA70 | Garcia, Jordan X | 32 | 0 | 1152 | 0 | 1152 | 22655 | 0 | 0
120 | Roughin Labor | PR | 32 | 01/30/19 | 02/01/19 | HO18 | Hoeg, Xavier A | 32 | 0 | 544 | 0 | 544 | 22661 | 0 | 0
120 | Roughin Labor | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 24 | 0 | 696 | 0 | 696 | 22675 | 0 | 0
120 | Roughin Labor | PR | 163 | 02/06/19 | 02/08/19 | BE45 | Belcher, Jacob T | 26 | 0 | 468 | 0 | 468 | 22705 | 0 | 0
120 | Roughin Labor | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 22 | 0 | 792 | 0 | 792 | 22723 | 0 | 0
120 | Roughin Labor | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 14 | 0 | 238 | 0 | 238 | 22729 | 0 | 0
120 | Roughin Labor | PR | 325 | 02/13/19 | 02/15/19 | BE45 | Belcher, Jacob T | 24 | 0 | 432 | 0 | 432 | 22774 | 0 | 0
120 | Roughin Labor | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 22 | 0 | 792 | 0 | 792 | 22793 | 0 | 0
120 | Roughin Labor | PR | 349 | 02/13/19 | 02/15/19 | HO18 | Hoeg, Xavier A | 24 | 0 | 408 | 0 | 408 | 22800 | 0 | 0
120 | Roughin Labor | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22844 | 0 | 0
120 | Roughin Labor | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 50 | 0 | 900 | 0 | 900 | 22845 | 0 | 0
120 | Roughin Labor | PR | 585 | 02/20/19 | 02/22/19 | CA77 | Castro Hernandez, Jose A | 8 | 0 | 264 | 0 | 264 | 22847 | 0 | 0
120 | Roughin Labor | PR | 593 | 02/20/19 | 02/22/19 | CR87 | Cruz Reyes, Jose | 56 | 0 | 1456 | 0 | 1456 | 22855 | 0 | 0
120 | Roughin Labor | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 52 | 0 | 1872 | 0 | 1872 | 22863 | 0 | 0
120 | Roughin Labor | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 50 | 0 | 850 | 0 | 850 | 22869 | 0 | 0
120 | Roughin Labor | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 4 | 0 | 192 | 0 | 192 | 22914 | 0 | 0
120 | Roughin Labor | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 41 | 0 | 738 | 0 | 738 | 22915 | 0 | 0
120 | Roughin Labor | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 5 | 0 | 125 | 0 | 125 | 22924 | 0 | 0
120 | Roughin Labor | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 23 | 0 | 598 | 0 | 598 | 22925 | 0 | 0
120 | Roughin Labor | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 38 | 0 | 1368 | 0 | 1368 | 22934 | 0 | 0
120 | Roughin Labor | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 0 | 6 | 0 | 153 | 153 | 22941 | 0 | 0
120 | Roughin Labor | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 40 | 0 | 680 | 0 | 680 | 22941 | 0 | 0
120 | Roughin Labor | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 3 | 0 | 144 | 0 | 144 | 22987 | 0 | 0
120 | Roughin Labor | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 1 | 0 | 27 | 27 | 22988 | 0 | 0
120 | Roughin Labor | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 44 | 0 | 792 | 0 | 792 | 22988 | 0 | 0
120 | Roughin Labor | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 5 | 0 | 130 | 0 | 130 | 22998 | 0 | 0
120 | Roughin Labor | PR | 268 | 03/06/19 | 03/08/19 | GA70 | Garcia, Jordan X | 42 | 0 | 1512 | 0 | 1512 | 23007 | 0 | 0
120 | Roughin Labor | PR | 274 | 03/06/19 | 03/08/19 | HO18 | Hoeg, Xavier A | 36 | 0 | 612 | 0 | 612 | 23013 | 0 | 0
120 | Roughin Labor | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 17 | 0 | 612 | 0 | 612 | 23077 | 0 | 0
120 | Roughin Labor | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 6 | 0 | 150 | 0 | 150 | 23141 | 0 | 0
120 | Roughin Labor | PR | 729 | 03/20/19 | 03/22/19 | GA70 | Garcia, Jordan X | 32 | 0 | 1152 | 0 | 1152 | 23150 | 0 | 0
120 | Roughin Labor | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 6 | 0 | 174 | 0 | 174 | 23170 | 0 | 0
120 | Roughin Labor | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 23205 | 0 | 0
120 | Roughin Labor | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 6 | 0 | 150 | 0 | 150 | 23215 | 0 | 0
120 | Roughin Labor | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 8 | 0 | 288 | 0 | 288 | 23225 | 0 | 0
120 | Roughin Labor | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 6 | 0 | 174 | 0 | 174 | 23245 | 0 | 0
120 | Roughin Labor | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23501 | 0 | 0
120 | Roughin Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 2 | 0 | 99 | 99 | 23688 | 0 | 0
120 | Roughin Labor | PR | 463 | 05/15/19 | 05/17/19 | WA35 | Waites, Thaddeus Z | 5 | 0 | 225 | 0 | 225 | 23794 | 0 | 0
120 | Roughin Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23958 | 0 | 0
120 | Roughin Labor | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 5 | 0 | 145 | 0 | 145 | 23970 | 0 | 0
120 | Roughin Labor | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 5 | 0 | 200 | 0 | 200 | 23987 | 0 | 0
120 | Roughin Labor | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 24334 | 0 | 0
120 | Roughin Labor | PR | 616 | 07/24/19 | 07/26/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24565 | 0 | 0
130 | Finish Labor | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 2 | 0 | 87 | 87 | 22049 | 0 | 0
130 | Finish Labor | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 2 | 0 | -87 | -87 | 22063 | 0 | 0
130 | Finish Labor | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 23058 | 0 | 0
130 | Finish Labor | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 3 | 0 | 75 | 0 | 75 | 23068 | 0 | 0
130 | Finish Labor | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 3 | 0 | 108 | 0 | 108 | 23077 | 0 | 0
130 | Finish Labor | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 3 | 0 | 87 | 0 | 87 | 23097 | 0 | 0
130 | Finish Labor | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 6 | 0 | 288 | 0 | 288 | 23205 | 0 | 0
130 | Finish Labor | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 400 | 0 | 400 | 23215 | 0 | 0
130 | Finish Labor | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 14 | 0 | 504 | 0 | 504 | 23225 | 0 | 0
130 | Finish Labor | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 16 | 0 | 464 | 0 | 464 | 23245 | 0 | 0
130 | Finish Labor | PR | 83 | 04/03/19 | 04/05/19 | BA70 | Barnhart, Joseph N | 10 | 0 | 480 | 0 | 480 | 23277 | 0 | 0
130 | Finish Labor | PR | 93 | 04/03/19 | 04/05/19 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 400 | 0 | 400 | 23287 | 0 | 0
130 | Finish Labor | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 0 | 6 | 0 | 234 | 234 | 23288 | 0 | 0
130 | Finish Labor | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 23288 | 0 | 0
130 | Finish Labor | PR | 103 | 04/03/19 | 04/05/19 | GA70 | Garcia, Jordan X | 10 | 0 | 360 | 0 | 360 | 23297 | 0 | 0
130 | Finish Labor | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 4 | 0 | 222 | 222 | 23305 | 0 | 0
130 | Finish Labor | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 24 | 0 | 888 | 0 | 888 | 23305 | 0 | 0
130 | Finish Labor | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 0 | 6 | 0 | 234 | 234 | 23362 | 0 | 0
130 | Finish Labor | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 23362 | 0 | 0
130 | Finish Labor | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 0 | 6 | 0 | 360 | 360 | 23378 | 0 | 0
130 | Finish Labor | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1600 | 0 | 1600 | 23378 | 0 | 0
130 | Finish Labor | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23425 | 0 | 0
130 | Finish Labor | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 0 | 8 | 0 | 312 | 312 | 23436 | 0 | 0
130 | Finish Labor | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1040 | 0 | 1040 | 23436 | 0 | 0
130 | Finish Labor | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 0 | 6 | 0 | 360 | 360 | 23453 | 0 | 0
130 | Finish Labor | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1600 | 0 | 1600 | 23453 | 0 | 0
130 | Finish Labor | PR | 755 | 04/24/19 | 04/26/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 23512 | 0 | 0
130 | Finish Labor | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 6 | 0 | 360 | 360 | 23528 | 0 | 0
130 | Finish Labor | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 38 | 0 | 1520 | 0 | 1520 | 23528 | 0 | 0
130 | Finish Labor | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 0 | 2.5 | 0 | 108.75 | 108.75 | 23584 | 0 | 0
130 | Finish Labor | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 23584 | 0 | 0
130 | Finish Labor | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 2 | 0 | 120 | 120 | 23601 | 0 | 0
130 | Finish Labor | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 35.5 | 0 | 1420 | 0 | 1420 | 23601 | 0 | 0
130 | Finish Labor | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 0 | 2.5 | 0 | 123.75 | 123.75 | 23613 | 0 | 0
130 | Finish Labor | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 24 | 0 | 792 | 0 | 792 | 23613 | 0 | 0
130 | Finish Labor | PR | 175 | 05/08/19 | 05/10/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 23659 | 0 | 0
130 | Finish Labor | PR | 192 | 05/08/19 | 05/10/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1600 | 0 | 1600 | 23676 | 0 | 0
130 | Finish Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 1 | 0 | 49.5 | 49.5 | 23688 | 0 | 0
130 | Finish Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 16 | 0 | 528 | 0 | 528 | 23688 | 0 | 0
130 | Finish Labor | PR | 407 | 05/15/19 | 05/17/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 23738 | 0 | 0
130 | Finish Labor | PR | 424 | 05/15/19 | 05/17/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1280 | 0 | 1280 | 23755 | 0 | 0
130 | Finish Labor | PR | 619 | 05/22/19 | 05/24/19 | CR87 | Cruz Reyes, Jose | 40 | 0 | 1160 | 0 | 1160 | 23814 | 0 | 0
130 | Finish Labor | PR | 636 | 05/22/19 | 05/24/19 | HO14 | Holmes, Anthony R | 40 | 0 | 1600 | 0 | 1600 | 23831 | 0 | 0
130 | Finish Labor | PR | 893 | 05/29/19 | 05/31/19 | CR87 | Cruz Reyes, Jose | 32 | 0 | 928 | 0 | 928 | 23893 | 0 | 0
130 | Finish Labor | PR | 910 | 05/29/19 | 05/31/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1280 | 0 | 1280 | 23910 | 0 | 0
130 | Finish Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23958 | 0 | 0
130 | Finish Labor | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 35 | 0 | 1015 | 0 | 1015 | 23970 | 0 | 0
130 | Finish Labor | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 35 | 0 | 1400 | 0 | 1400 | 23987 | 0 | 0
130 | Finish Labor | PR | 465 | 06/12/19 | 06/14/19 | CR87 | Cruz Reyes, Jose | 37 | 0 | 1073 | 0 | 1073 | 24046 | 0 | 0
130 | Finish Labor | PR | 480 | 06/12/19 | 06/14/19 | HO14 | Holmes, Anthony R | 37 | 0 | 1480 | 0 | 1480 | 24061 | 0 | 0
130 | Finish Labor | PR | 651 | 06/19/19 | 06/21/19 | HO14 | Holmes, Anthony R | 8 | 0 | 320 | 0 | 320 | 24137 | 0 | 0
130 | Finish Labor | PR | 869 | 06/26/19 | 06/28/19 | HO14 | Holmes, Anthony R | 32 | 0 | 1280 | 0 | 1280 | 24213 | 0 | 0
130 | Finish Labor | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24411 | 0 | 0
140 | Gas Labor | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 0 | 6 | 0 | 252 | 252 | 21586 | 0 | 0
140 | Gas Labor | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21586 | 0 | 0
140 | Gas Labor | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 0 | 3.5 | 0 | 220.5 | 220.5 | 21904 | 0 | 0
140 | Gas Labor | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 40 | 0 | 1680 | 0 | 1680 | 21904 | 0 | 0
140 | Gas Labor | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 10 | 0 | 430 | 0 | 430 | 21978 | 0 | 0
140 | Gas Labor | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 6 | 0 | 258 | 0 | 258 | 22051 | 0 | 0
140 | Gas Labor | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 4 | 0 | 192 | 0 | 192 | 22417 | 0 | 0
140 | Gas Labor | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 16 | 0 | 576 | 0 | 576 | 22436 | 0 | 0
140 | Gas Labor | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 3 | 0 | 108 | 0 | 108 | 22510 | 0 | 0
140 | Gas Labor | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24184 | 0 | 0
140 | Gas Labor | PR | 12 | 07/03/19 | 07/05/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24259 | 0 | 0
140 | Gas Labor | PR | 52 | 07/03/19 | 07/05/19 | MA71 | Martinez Reyes, Juan C | 4 | 0 | 132 | 0 | 132 | 24300 | 0 | 0
141 | Water Main/Insulation Lab | PR | 236 | 08/08/18 | 08/10/18 | GA72 | Gardner, Andrew M | 12 | 0 | 204 | 0 | 204 | 20688 | 0 | 0
141 | Water Main/Insulation Lab | PR | 504 | 08/15/18 | 08/17/18 | GA72 | Gardner, Andrew M | 12 | 0 | 204 | 0 | 204 | 20761 | 0 | 0
141 | Water Main/Insulation Lab | PR | 766 | 08/22/18 | 08/24/18 | GA72 | Gardner, Andrew M | 12 | 0 | 204 | 0 | 204 | 20833 | 0 | 0
141 | Water Main/Insulation Lab | PR | 1021 | 08/29/18 | 08/31/18 | GA72 | Gardner, Andrew M | 11.5 | 0 | 195.5 | 0 | 195.5 | 20916 | 0 | 0
141 | Water Main/Insulation Lab | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 8 | 0 | 184 | 0 | 184 | 21332 | 0 | 0
141 | Water Main/Insulation Lab | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 8 | 0 | 192 | 0 | 192 | 21333 | 0 | 0
141 | Water Main/Insulation Lab | PR | 249 | 10/10/18 | 10/12/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21407 | 0 | 0
141 | Water Main/Insulation Lab | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 8 | 0 | 136 | 0 | 136 | 21620 | 0 | 0
141 | Water Main/Insulation Lab | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 20 | 0 | 320 | 0 | 320 | 21645 | 0 | 0
141 | Water Main/Insulation Lab | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 4 | 0 | 102 | 102 | 21655 | 0 | 0
141 | Water Main/Insulation Lab | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 32 | 0 | 544 | 0 | 544 | 21655 | 0 | 0
141 | Water Main/Insulation Lab | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 28 | 0 | 784 | 0 | 784 | 21660 | 0 | 0
141 | Water Main/Insulation Lab | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 6 | 0 | 144 | 144 | 21717 | 0 | 0
141 | Water Main/Insulation Lab | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 512 | 0 | 512 | 21717 | 0 | 0
141 | Water Main/Insulation Lab | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 8 | 0 | 204 | 204 | 21727 | 0 | 0
141 | Water Main/Insulation Lab | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21727 | 0 | 0
141 | Water Main/Insulation Lab | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 6 | 0 | 252 | 252 | 21732 | 0 | 0
141 | Water Main/Insulation Lab | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 32 | 0 | 896 | 0 | 896 | 21732 | 0 | 0
141 | Water Main/Insulation Lab | PR | 436 | 11/14/18 | 11/16/18 | BE45 | Belcher, Jacob T | 28 | 0 | 476 | 0 | 476 | 21765 | 0 | 0
141 | Water Main/Insulation Lab | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 0 | 5.5 | 0 | 132 | 132 | 21790 | 0 | 0
141 | Water Main/Insulation Lab | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 640 | 0 | 640 | 21790 | 0 | 0
141 | Water Main/Insulation Lab | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 15.5 | 0 | 395.25 | 395.25 | 21800 | 0 | 0
141 | Water Main/Insulation Lab | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21800 | 0 | 0
141 | Water Main/Insulation Lab | PR | 477 | 11/14/18 | 11/16/18 | MO56 | Montenegro, Carlos E | 38 | 0 | 1064 | 0 | 1064 | 21805 | 0 | 0
141 | Water Main/Insulation Lab | PR | 622 | 11/21/18 | 11/21/18 | BE45 | Belcher, Jacob T | 37.5 | 0 | 637.5 | 0 | 637.5 | 21844 | 0 | 0
141 | Water Main/Insulation Lab | PR | 647 | 11/21/18 | 11/21/18 | HO18 | Hoeg, Xavier A | 37.5 | 0 | 600 | 0 | 600 | 21868 | 0 | 0
141 | Water Main/Insulation Lab | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 3.5 | 0 | 89.25 | 89.25 | 21877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 680 | 0 | 680 | 21877 | 0 | 0
141 | Water Main/Insulation Lab | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 0 | 3.5 | 0 | 147 | 147 | 21882 | 0 | 0
141 | Water Main/Insulation Lab | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21882 | 0 | 0
141 | Water Main/Insulation Lab | PR | 834 | 11/28/18 | 11/30/18 | BE45 | Belcher, Jacob T | 35 | 0 | 630 | 0 | 630 | 21917 | 0 | 0
141 | Water Main/Insulation Lab | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 10 | 0 | 250 | 0 | 250 | 21926 | 0 | 0
141 | Water Main/Insulation Lab | PR | 860 | 11/28/18 | 11/30/18 | HO18 | Hoeg, Xavier A | 35 | 0 | 595 | 0 | 595 | 21942 | 0 | 0
141 | Water Main/Insulation Lab | PR | 869 | 11/28/18 | 11/30/18 | LU09 | Lucas Tzintzun, Rafael | 35 | 0 | 630 | 0 | 630 | 21951 | 0 | 0
141 | Water Main/Insulation Lab | PR | 874 | 11/28/18 | 11/30/18 | MO56 | Montenegro, Carlos E | 35 | 0 | 1015 | 0 | 1015 | 21956 | 0 | 0
141 | Water Main/Insulation Lab | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 0 | 8 | 0 | 216 | 216 | 21991 | 0 | 0
141 | Water Main/Insulation Lab | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 40 | 0 | 720 | 0 | 720 | 21991 | 0 | 0
141 | Water Main/Insulation Lab | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 10 | 0 | 250 | 0 | 250 | 21999 | 0 | 0
141 | Water Main/Insulation Lab | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 0 | 8 | 0 | 204 | 204 | 22014 | 0 | 0
141 | Water Main/Insulation Lab | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 680 | 0 | 680 | 22014 | 0 | 0
141 | Water Main/Insulation Lab | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 8 | 0 | 216 | 216 | 22023 | 0 | 0
141 | Water Main/Insulation Lab | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 720 | 0 | 720 | 22023 | 0 | 0
141 | Water Main/Insulation Lab | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 0 | 8 | 0 | 348 | 348 | 22028 | 0 | 0
141 | Water Main/Insulation Lab | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1160 | 0 | 1160 | 22028 | 0 | 0
141 | Water Main/Insulation Lab | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 0 | 2 | 0 | 54 | 54 | 22131 | 0 | 0
141 | Water Main/Insulation Lab | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 40 | 0 | 720 | 0 | 720 | 22131 | 0 | 0
141 | Water Main/Insulation Lab | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 2 | 0 | 51 | 51 | 22155 | 0 | 0
141 | Water Main/Insulation Lab | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 16 | 0 | 272 | 0 | 272 | 22155 | 0 | 0
141 | Water Main/Insulation Lab | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 2 | 0 | 54 | 54 | 22164 | 0 | 0
141 | Water Main/Insulation Lab | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 40 | 0 | 720 | 0 | 720 | 22164 | 0 | 0
141 | Water Main/Insulation Lab | PR | 311 | 12/12/18 | 12/14/18 | MO56 | Montenegro, Carlos E | 34 | 0 | 986 | 0 | 986 | 22170 | 0 | 0
141 | Water Main/Insulation Lab | PR | 318 | 12/12/18 | 12/14/18 | RE96 | Reyes Cruz, Denis A | 34 | 0 | 918 | 0 | 918 | 22177 | 0 | 0
141 | Water Main/Insulation Lab | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 9 | 0 | 387 | 0 | 387 | 22193 | 0 | 0
141 | Water Main/Insulation Lab | PR | 512 | 12/19/18 | 12/21/18 | BE45 | Belcher, Jacob T | 42 | 0 | 756 | 0 | 756 | 22203 | 0 | 0
141 | Water Main/Insulation Lab | PR | 521 | 12/19/18 | 12/21/18 | CR79 | Cruz Guzman, Joel A | 42 | 0 | 1050 | 0 | 1050 | 22212 | 0 | 0
141 | Water Main/Insulation Lab | PR | 537 | 12/19/18 | 12/21/18 | HO18 | Hoeg, Xavier A | 42 | 0 | 714 | 0 | 714 | 22227 | 0 | 0
141 | Water Main/Insulation Lab | PR | 551 | 12/19/18 | 12/21/18 | MO56 | Montenegro, Carlos E | 42 | 0 | 1218 | 0 | 1218 | 22241 | 0 | 0
141 | Water Main/Insulation Lab | PR | 573 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 42 | 0 | 23.1 | 0 | 23.1 | 22263 | 0 | 0
141 | Water Main/Insulation Lab | PR | 693 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 42 | 0 | -23.1 | 0 | -23.1 | 22263 | 0 | 0
141 | Water Main/Insulation Lab | PR | 692 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 42 | 0 | 924 | 0 | 924 | 22269 | 0 | 0
141 | Water Main/Insulation Lab | PR | 703 | 12/26/18 | 12/28/18 | BE45 | Belcher, Jacob T | 16 | 0 | 288 | 0 | 288 | 22276 | 0 | 0
141 | Water Main/Insulation Lab | PR | 711 | 12/26/18 | 12/28/18 | CR77 | Cruz Gonzalez, Julio C | 26 | 0 | 572 | 0 | 572 | 22284 | 0 | 0
141 | Water Main/Insulation Lab | PR | 712 | 12/26/18 | 12/28/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 400 | 0 | 400 | 22285 | 0 | 0
141 | Water Main/Insulation Lab | PR | 728 | 12/26/18 | 12/28/18 | HO18 | Hoeg, Xavier A | 24 | 0 | 408 | 0 | 408 | 22301 | 0 | 0
141 | Water Main/Insulation Lab | PR | 742 | 12/26/18 | 12/28/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 464 | 0 | 464 | 22315 | 0 | 0
141 | Water Main/Insulation Lab | PR | 764 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 24 | 0 | 528 | 0 | 528 | 22337 | 0 | 0
141 | Water Main/Insulation Lab | PR | 45 | 01/02/19 | 01/04/19 | MO56 | Montenegro, Carlos E | 26 | 0 | 754 | 0 | 754 | 22386 | 0 | 0
141 | Water Main/Insulation Lab | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 400 | 0 | 400 | 22427 | 0 | 0
141 | Water Main/Insulation Lab | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 16 | 0 | 464 | 0 | 464 | 22457 | 0 | 0
141 | Water Main/Insulation Lab | PR | 719 | 01/23/19 | 01/25/19 | BE45 | Belcher, Jacob T | 40 | 0 | 720 | 0 | 720 | 22564 | 0 | 0
141 | Water Main/Insulation Lab | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 16 | 0 | 416 | 0 | 416 | 22647 | 0 | 0
141 | Water Main/Insulation Lab | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 22665 | 0 | 0
141 | Water Main/Insulation Lab | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 16 | 0 | 464 | 0 | 464 | 22675 | 0 | 0
141 | Water Main/Insulation Lab | PR | 172 | 02/06/19 | 02/08/19 | CR79 | Cruz Guzman, Joel A | 26 | 0 | 650 | 0 | 650 | 22714 | 0 | 0
141 | Water Main/Insulation Lab | PR | 173 | 02/06/19 | 02/08/19 | CR87 | Cruz Reyes, Jose | 26 | 0 | 676 | 0 | 676 | 22715 | 0 | 0
141 | Water Main/Insulation Lab | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 4 | 0 | 144 | 0 | 144 | 22723 | 0 | 0
141 | Water Main/Insulation Lab | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 2 | 0 | 34 | 0 | 34 | 22729 | 0 | 0
141 | Water Main/Insulation Lab | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 22733 | 0 | 0
141 | Water Main/Insulation Lab | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 6 | 0 | 198 | 0 | 198 | 22741 | 0 | 0
141 | Water Main/Insulation Lab | PR | 201 | 02/06/19 | 02/08/19 | MO56 | Montenegro, Carlos E | 18 | 0 | 522 | 0 | 522 | 22743 | 0 | 0
141 | Water Main/Insulation Lab | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 256 | 0 | 256 | 22756 | 0 | 0
141 | Water Main/Insulation Lab | PR | 334 | 02/13/19 | 02/15/19 | CR79 | Cruz Guzman, Joel A | 24 | 0 | 600 | 0 | 600 | 22783 | 0 | 0
141 | Water Main/Insulation Lab | PR | 335 | 02/13/19 | 02/15/19 | CR87 | Cruz Reyes, Jose | 24 | 0 | 624 | 0 | 624 | 22784 | 0 | 0
141 | Water Main/Insulation Lab | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 2 | 0 | 72 | 0 | 72 | 22793 | 0 | 0
141 | Water Main/Insulation Lab | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 2.5 | 0 | 122.5 | 0 | 122.5 | 22804 | 0 | 0
141 | Water Main/Insulation Lab | PR | 363 | 02/13/19 | 02/15/19 | MO56 | Montenegro, Carlos E | 14 | 0 | 406 | 0 | 406 | 22814 | 0 | 0
141 | Water Main/Insulation Lab | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 6 | 0 | 108 | 0 | 108 | 22845 | 0 | 0
141 | Water Main/Insulation Lab | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 8 | 0 | 300 | 300 | 22854 | 0 | 0
141 | Water Main/Insulation Lab | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22854 | 0 | 0
141 | Water Main/Insulation Lab | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 4 | 0 | 144 | 0 | 144 | 22863 | 0 | 0
141 | Water Main/Insulation Lab | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 6 | 0 | 102 | 0 | 102 | 22869 | 0 | 0
141 | Water Main/Insulation Lab | PR | 621 | 02/20/19 | 02/22/19 | MO56 | Montenegro, Carlos E | 48 | 0 | 1392 | 0 | 1392 | 22883 | 0 | 0
141 | Water Main/Insulation Lab | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 5 | 0 | 90 | 0 | 90 | 22915 | 0 | 0
141 | Water Main/Insulation Lab | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 33 | 0 | 825 | 0 | 825 | 22924 | 0 | 0
141 | Water Main/Insulation Lab | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 15 | 0 | 390 | 0 | 390 | 22925 | 0 | 0
141 | Water Main/Insulation Lab | PR | 48 | 02/27/19 | 03/01/19 | MO56 | Montenegro, Carlos E | 28 | 0 | 812 | 0 | 812 | 22955 | 0 | 0
141 | Water Main/Insulation Lab | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 4 | 0 | 72 | 0 | 72 | 22988 | 0 | 0
141 | Water Main/Insulation Lab | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 9 | 0 | 337.5 | 337.5 | 22997 | 0 | 0
141 | Water Main/Insulation Lab | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 1000 | 0 | 1000 | 22997 | 0 | 0
141 | Water Main/Insulation Lab | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 0 | 3 | 0 | 130.5 | 130.5 | 23027 | 0 | 0
141 | Water Main/Insulation Lab | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 46 | 0 | 1334 | 0 | 1334 | 23027 | 0 | 0
141 | Water Main/Insulation Lab | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 4 | 0 | 144 | 0 | 144 | 23077 | 0 | 0
141 | Water Main/Insulation Lab | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 37 | 0 | 1073 | 0 | 1073 | 23097 | 0 | 0
141 | Water Main/Insulation Lab | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 34 | 0 | 850 | 0 | 850 | 23141 | 0 | 0
141 | Water Main/Insulation Lab | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 34 | 0 | 986 | 0 | 986 | 23170 | 0 | 0
141 | Water Main/Insulation Lab | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 18 | 0 | 450 | 0 | 450 | 23215 | 0 | 0
141 | Water Main/Insulation Lab | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 16 | 0 | 576 | 0 | 576 | 23225 | 0 | 0
141 | Water Main/Insulation Lab | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 18 | 0 | 522 | 0 | 522 | 23245 | 0 | 0
141 | Water Main/Insulation Lab | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 23531 | 0 | 0
141 | Water Main/Insulation Lab | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 23758 | 0 | 0
141 | Water Main/Insulation Lab | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 24 | 0 | 480 | 0 | 480 | 23778 | 0 | 0
141 | Water Main/Insulation Lab | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 5 | 0 | 90 | 0 | 90 | 23789 | 0 | 0
141 | Water Main/Insulation Lab | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 5 | 0 | 80 | 0 | 80 | 23790 | 0 | 0
141 | Water Main/Insulation Lab | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23803 | 0 | 0
141 | Water Main/Insulation Lab | PR | 659 | 05/22/19 | 05/24/19 | RO06 | Roberts, Lake A | 31 | 0 | 620 | 0 | 620 | 23854 | 0 | 0
141 | Water Main/Insulation Lab | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 140 | 0 | 140 | 23859 | 0 | 0
141 | Water Main/Insulation Lab | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | 103.61 |  | 0 | 0
142 | Mech Room Labor | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 5.5 | 0 | 247.5 | 0 | 247.5 | 19037 | 0 | 0
142 | Mech Room Labor | PR | 43 | 02/28/18 | 03/02/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 19045 | 0 | 0
142 | Mech Room Labor | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 112.5 | 0 | 112.5 | 19106 | 0 | 0
142 | Mech Room Labor | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 1 | 0 | 49 | 0 | 49 | 22520 | 0 | 0
142 | Mech Room Labor | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 6 | 0 | 294 | 0 | 294 | 22665 | 0 | 0
142 | Mech Room Labor | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 4 | 0 | 132 | 0 | 132 | 22673 | 0 | 0
142 | Mech Room Labor | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 15 | 0 | 480 | 0 | 480 | 22687 | 0 | 0
142 | Mech Room Labor | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 10 | 0 | 490 | 0 | 490 | 22804 | 0 | 0
142 | Mech Room Labor | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 4 | 0 | 128 | 0 | 128 | 22827 | 0 | 0
142 | Mech Room Labor | PR | 611 | 02/20/19 | 02/22/19 | HU06 | Hubbard, Robert W | 36.5 | 0 | 1788.5 | 0 | 1788.5 | 22873 | 0 | 0
142 | Mech Room Labor | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 29 | 0 | 957 | 0 | 957 | 22881 | 0 | 0
142 | Mech Room Labor | PR | 635 | 02/20/19 | 02/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 30 | 0 | 960 | 0 | 960 | 22897 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 2 | 0 | 147 | 147 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 11 | 0 | 539 | 0 | 539 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 62 | 02/27/19 | 03/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 41 | 0 | 1312 | 0 | 1312 | 22969 | 0 | 0
142 | Mech Room Labor | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 7 | 0 | 343 | 0 | 343 | 23017 | 0 | 0
142 | Mech Room Labor | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1280 | 0 | 1280 | 23040 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 1 | 0 | 32 | 0 | 32 | 23183 | 0 | 0
142 | Mech Room Labor | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 23197 | 0 | 0
142 | Mech Room Labor | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | -147 | 0 | -147 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23235 | 0 | 0
142 | Mech Room Labor | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 2 | 0 | 64 | 0 | 64 | 23258 | 0 | 0
142 | Mech Room Labor | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 23679 | 0 | 0
142 | Mech Room Labor | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 23834 | 0 | 0
142 | Mech Room Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24035 | 0 | 0
142 | Mech Room Labor | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -579.68 |  | 0 | 0
143 | Condensation Drains Labor | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0.5 | 0 | 22.5 | 0 | 22.5 | 19106 | 0 | 0
143 | Condensation Drains Labor | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 19114 | 0 | 0
143 | Condensation Drains Labor | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 16 | 0 | 576 | 0 | 576 | 23077 | 0 | 0
210 | Underground Material | AP | 262 | 11/01/17 | 11/13/17 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 74.96 | 4244591-00 | 0 | 0
210 | Underground Material | AP | 411 | 02/08/18 | 02/14/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 1663.23 | 4247699-00 | 0 | 0
210 | Underground Material | AP | 539 | 02/15/18 | 02/16/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 525.1 | 4247699-01 | 0 | 0
210 | Underground Material | AP | 540 | 02/15/18 | 02/16/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 696.17 | 4247700-00 | 0 | 0
210 | Underground Material | GL | 785 | 02/21/18 | 02/21/18 | Mat | Req 3484 |  |  |  |  | 10.17 |  | 0 | 0
210 | Underground Material | AP | 281 | 02/08/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | -1663.23 | 4247699-00A | 0 | 0
210 | Underground Material | AP | 282 | 02/08/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 1663.23 | 4247699-00B | 0 | 0
210 | Underground Material | AP | 283 | 02/15/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | -525.1 | 4247699-01A | 0 | 0
210 | Underground Material | AP | 284 | 02/15/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 525.1 | 4247699-01B | 0 | 0
210 | Underground Material | AP | 285 | 02/15/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | -696.17 | 4247700-00A | 0 | 0
210 | Underground Material | AP | 286 | 02/15/18 | 03/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 696.17 | 4247700-00B | 0 | 0
210 | Underground Material | AP | 680 | 03/12/18 | 03/26/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 47.3 | 4249261-00 | 0 | 0
210 | Underground Material | AP | 732 | 03/14/18 | 03/28/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 103.16 | 4249351-00 | 0 | 0
210 | Underground Material | AP | 733 | 03/15/18 | 03/28/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 280 | 4249369-00 | 0 | 0
211 | Garage Material | GL | 255 | 03/13/18 | 03/13/18 | Mat | Req 3533 |  |  |  |  | 48.31 |  | 0 | 0
211 | Garage Material | GL | 688 | 07/25/18 | 07/25/18 | Mat | Req 4509 |  |  |  |  | 18 |  | 0 | 0
211 | Garage Material | GL | 675 | 08/22/18 | 08/22/18 | Mat | Req 4642 |  |  |  |  | 858.57 |  | 0 | 0
211 | Garage Material | AP | 990 | 08/07/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5467.75 | 4255504-00 | 0 | 0
211 | Garage Material | AP | 991 | 08/08/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 22.74 | 4255685-00 | 0 | 0
211 | Garage Material | AP | 992 | 08/09/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 29.89 | 4255685-01 | 0 | 0
211 | Garage Material | GL | 119 | 09/07/18 | 09/07/18 | Mat | Req 5320 |  |  |  |  | 761.84 |  | 0 | 0
211 | Garage Material | GL | 616 | 09/25/18 | 09/25/18 | Mat | Req 5380 |  |  |  |  | 1156.44 |  | 0 | 0
211 | Garage Material | AP | 168 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.88 | 4257062-00 | 0 | 0
211 | Garage Material | AP | 169 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 29.89 | 4257062-01 | 0 | 0
211 | Garage Material | GL | 570 | 10/22/18 | 10/22/18 | Mat | Req 4724 |  |  |  |  | 291.56 |  | 0 | 0
211 | Garage Material | AP | 409 | 09/21/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 463.67 | 4257552-00 | 0 | 0
211 | Garage Material | GL | 319 | 11/09/18 | 11/09/18 | Mat | Req 4762 |  |  |  |  | 534 |  | 0 | 0
211 | Garage Material | GL | 783 | 11/26/18 | 11/26/18 | Mat | Req 4848 |  |  |  |  | 289.47 |  | 0 | 0
211 | Garage Material | GL | 1003 | 11/30/18 | 11/30/18 | Mat | Req 5572 |  |  |  |  | 192 |  | 0 | 0
211 | Garage Material | AP | 442 | 11/21/18 | 12/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 60.26 | 4260314-00 | 0 | 0
211 | Garage Material | GL | 602 | 12/21/18 | 12/21/18 | Mat | Req 5628 |  |  |  |  | 65 |  | 0 | 0
211 | Garage Material | GL | 652 | 01/22/19 | 01/22/19 | Mat | Req 4943 |  |  |  |  | 71.2 |  | 0 | 0
211 | Garage Material | GL | 142 | 03/04/19 | 03/04/19 | Mat | Req 5053 |  |  |  |  | -103.66 |  | 0 | 0
211 | Garage Material | GL | 344 | 03/08/19 | 03/08/19 | Mat | Req 5790 |  |  |  |  | -25.8 |  | 0 | 0
211 | Garage Material | GL | 837 | 03/25/19 | 03/25/19 | Mat | Req 5078 |  |  |  |  | 18 |  | 0 | 0
211 | Garage Material | GL | 541 | 05/21/19 | 05/21/19 | Mat | Req 5947 |  |  |  |  | 2314.7 |  | 0 | 0
211 | Garage Material | GL | 542 | 05/21/19 | 05/21/19 | Mat | Req 5948 |  |  |  |  | -1841.05 |  | 0 | 0
211 | Garage Material | GL | 543 | 05/21/19 | 05/21/19 | Mat | Req 5949 |  |  |  |  | -449.5 |  | 0 | 0
211 | Garage Material | GL | 821 | 05/30/19 | 05/30/19 | Mat | Req 5978 |  |  |  |  | 188.8 |  | 0 | 0
211 | Garage Material | GL | 818 | 06/26/19 | 06/26/19 | Mat | Req 6026 |  |  |  |  | -25.14 |  | 0 | 0
211 | Garage Material | GL | 140 | 07/09/19 | 07/09/19 | Mat | Req 6104 |  |  |  |  | 18.84 |  | 0 | 0
212 | Canout Material | GL | 841 | 03/31/18 | 03/31/18 | Mat | Req 4279 |  |  |  |  | 60.74 |  | 0 | 0
212 | Canout Material | GL | 415 | 04/18/18 | 04/18/18 | Mat | Req 3588 |  |  |  |  | 18.86 |  | 0 | 0
212 | Canout Material | GL | 749 | 04/26/18 | 04/26/18 | Mat | Req 3625 |  |  |  |  | 470.37 |  | 0 | 0
212 | Canout Material | GL | 109 | 05/04/18 | 05/04/18 | Mat | Req 3646 |  |  |  |  | 17.9 |  | 0 | 0
212 | Canout Material | GL | 232 | 06/06/18 | 06/06/18 | Mat | Req 3668 |  |  |  |  | 3332.38 |  | 0 | 0
212 | Canout Material | AP | 1038 | 06/25/18 | 06/28/18 | 3820HI | Hilti, Inc. |  |  |  |  | 315 | 4611817875 | 0 | 0
212 | Canout Material | AP | 242 | 06/25/18 | 07/10/18 | 1231KS | Keller Supply Company |  |  |  |  | 300.39 | S012024115.001 | 0 | 0
212 | Canout Material | GL | 401 | 07/16/18 | 07/16/18 | Mat | Req 4446 |  |  |  |  | 3653.46 |  | 0 | 0
212 | Canout Material | AP | 683 | 06/29/18 | 07/16/18 | 2046KS | Keller Supply Co. $4218 Roosevelt |  |  |  |  | 501.4 | S012038886.001 | 0 | 0
212 | Canout Material | AP | 558 | 06/26/18 | 07/20/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 26.29 | 4253816-00 | 0 | 0
212 | Canout Material | GL | 567 | 07/23/18 | 07/23/18 | Mat | Req 5308 |  |  |  |  | 3.39 |  | 0 | 0
212 | Canout Material | GL | 355 | 08/10/18 | 08/10/18 | Mat | Req 4555 |  |  |  |  | -977.43 |  | 0 | 0
212 | Canout Material | GL | 560 | 08/16/18 | 08/16/18 | Mat | Req 4549 |  |  |  |  | -182.24 |  | 0 | 0
212 | Canout Material | GL | 782 | 11/26/18 | 11/26/18 | Mat | Req 4849 |  |  |  |  | 2.46 |  | 0 | 0
220 | Roughin Material | GL | 402 | 07/16/18 | 07/16/18 | Mat | Req 5268 |  |  |  |  | 96.78 |  | 0 | 0
220 | Roughin Material | AP | 559 | 06/29/18 | 07/20/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | -1999.7 | 4254030-00 | 0 | 0
220 | Roughin Material | AP | 578 | 06/29/18 | 08/01/18 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve |  |  |  |  | 1999.7 | 4254030-00A | 0 | 0
220 | Roughin Material | AP | 579 | 06/29/18 | 08/01/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -1999.7 | 4254030-00 | 0 | 0
220 | Roughin Material | GL | 120 | 09/07/18 | 09/07/18 | Mat | Req 5321 |  |  |  |  | 536.96 |  | 0 | 0
220 | Roughin Material | AP | 265 | 08/21/18 | 09/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19063.16 | 4253107-00 | 0 | 0
220 | Roughin Material | AP | 380 | 08/23/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2228.91 | 4256270-00 | 0 | 0
220 | Roughin Material | AP | 434 | 08/31/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 433.2 | 4256719-00 | 0 | 0
220 | Roughin Material | GL | 614 | 09/25/18 | 09/25/18 | Mat | Req 5382 |  |  |  |  | 1269.25 |  | 0 | 0
220 | Roughin Material | GL | 772 | 09/30/18 | 09/30/18 | Mat | Req 5419 |  |  |  |  | 806.16 |  | 0 | 0
220 | Roughin Material | AP | 108 | 09/07/18 | 10/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 9627.6 | 4256857-00 | 0 | 0
220 | Roughin Material | AP | 166 | 09/11/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6198.47 | 4257031-00 | 0 | 0
220 | Roughin Material | AP | 167 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 102.41 | 4256719-01 | 0 | 0
220 | Roughin Material | AP | 170 | 09/13/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 471.15 | 4257205-00 | 0 | 0
220 | Roughin Material | AP | 428 | 09/17/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 452.82 | 4257328-00 | 0 | 0
220 | Roughin Material | GL | 572 | 10/22/18 | 10/22/18 | Mat | Req 4722 |  |  |  |  | 1113.12 |  | 0 | 0
220 | Roughin Material | GL | 587 | 10/22/18 | 10/22/18 | Mat | Req 4754 |  |  |  |  | 108.32 |  | 0 | 0
220 | Roughin Material | AP | 682 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 201.5 | 4257884-00 | 0 | 0
220 | Roughin Material | AP | 133 | 10/06/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 676.12 | 4258253-00 | 0 | 0
220 | Roughin Material | AP | 134 | 10/10/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 7396.53 | 4258389-00 | 0 | 0
220 | Roughin Material | GL | 297 | 11/09/18 | 11/09/18 | Mat | Req 4786 |  |  |  |  | 1031.46 |  | 0 | 0
220 | Roughin Material | GL | 298 | 11/09/18 | 11/09/18 | Mat | Req 4761 |  |  |  |  | 1437.05 |  | 0 | 0
220 | Roughin Material | AP | 334 | 10/23/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4724.86 | S8678465.001 | 0 | 0
220 | Roughin Material | AP | 600 | 10/18/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2077.37 | 4258687-00 | 0 | 0
220 | Roughin Material | AP | 601 | 10/18/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5420.69 | 4258789-00 | 0 | 0
220 | Roughin Material | AP | 602 | 10/18/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 137.97 | 4258837-00 | 0 | 0
220 | Roughin Material | AP | 603 | 10/22/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 850.18 | 4258253-01 | 0 | 0
220 | Roughin Material | AP | 703 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3475.3 | 4259004-00 | 0 | 0
220 | Roughin Material | AP | 964 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4526.55 | 4253115-00 | 0 | 0
220 | Roughin Material | GL | 1002 | 11/30/18 | 11/30/18 | Mat | Req 5573 |  |  |  |  | 574.5 |  | 0 | 0
220 | Roughin Material | AP | 1020 | 11/02/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 195.51 | 4259418-00 | 0 | 0
220 | Roughin Material | AP | 1025 | 11/07/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 457.77 | S9009372.001 | 0 | 0
220 | Roughin Material | AP | 1032 | 11/08/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4724.86 | S8678402.001 | 0 | 0
220 | Roughin Material | AP | 1034 | 11/15/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 490.59 | S9019148.001 | 0 | 0
220 | Roughin Material | GL | 173 | 12/06/18 | 12/06/18 | CK#5634 | Thaddeus Waites |  |  |  |  | 22.39 |  | 0 | 0
220 | Roughin Material | AP | 382 | 11/07/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1862.96 | 4259559-00 | 0 | 0
220 | Roughin Material | AP | 417 | 11/12/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 277.17 | 4259885-00 | 0 | 0
220 | Roughin Material | AP | 418 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 20.73 | 4259418-01 | 0 | 0
220 | Roughin Material | AP | 419 | 11/16/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 175.6 | 4260130-00 | 0 | 0
220 | Roughin Material | AP | 420 | 11/20/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 65.12 | 4259885-01 | 0 | 0
220 | Roughin Material | AP | 424 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 155 | 4260071-00 | 0 | 0
220 | Roughin Material | AP | 440 | 11/20/18 | 12/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 134.03 | 4260149-00 | 0 | 0
220 | Roughin Material | AP | 441 | 11/21/18 | 12/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 335.07 | 4253115-01 | 0 | 0
220 | Roughin Material | GL | 600 | 12/21/18 | 12/21/18 | Mat | Req 5626 |  |  |  |  | 1500.87 |  | 0 | 0
220 | Roughin Material | AP | 129 | 12/20/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 5216.36 | S8678334.001 | 0 | 0
220 | Roughin Material | AP | 142 | 12/17/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 26.25 | 6805988 | 0 | 0
220 | Roughin Material | GL | 306 | 01/10/19 | 01/10/19 | CK#5497 | Joseph Barnhart |  |  |  |  | 59.19 |  | 0 | 0
220 | Roughin Material | GL | 333 | 01/11/19 | 01/11/19 | Mat | Req 4858 |  |  |  |  | 2187.9 |  | 0 | 0
220 | Roughin Material | GL | 411 | 01/15/19 | 01/15/19 | Mat | Req 4904 |  |  |  |  | 1730.75 |  | 0 | 0
220 | Roughin Material | AP | 577 | 12/10/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 101.7 | 4260940-00 | 0 | 0
220 | Roughin Material | GL | 810 | 01/25/19 | 01/25/19 | CK#5655 | Jordan Garcia |  |  |  |  | 31.91 |  | 0 | 0
220 | Roughin Material | AP | 270 | 01/08/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 89.63 | 4261979-00 | 0 | 0
220 | Roughin Material | GL | 285 | 02/08/19 | 02/08/19 | Mat | Req 5688 |  |  |  |  | 359.84 |  | 0 | 0
220 | Roughin Material | GL | 156 | 03/04/19 | 03/04/19 | Mat | Req 5018 |  |  |  |  | 524.82 |  | 0 | 0
220 | Roughin Material | GL | 343 | 03/08/19 | 03/08/19 | Mat | Req 5791 |  |  |  |  | 130.8 |  | 0 | 0
220 | Roughin Material | GL | 345 | 03/08/19 | 03/08/19 | Mat | Req 5789 |  |  |  |  | 81.2 |  | 0 | 0
220 | Roughin Material | GL | 346 | 03/08/19 | 03/08/19 | Mat | Req 5828 |  |  |  |  | -19.36 |  | 0 | 0
220 | Roughin Material | AP | 415 | 02/20/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 62.24 | 4263558-00 | 0 | 0
220 | Roughin Material | AP | 423 | 02/21/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 82.12 | 4263728-00 | 0 | 0
220 | Roughin Material | GL | 596 | 03/15/19 | 03/15/19 | Mat | Req 5809 |  |  |  |  | 122.27 |  | 0 | 0
220 | Roughin Material | GL | 1002 | 03/29/19 | 03/29/19 | CK#5704 | Joseph Barnhart |  |  |  |  | 5.27 |  | 0 | 0
220 | Roughin Material | GL | 271 | 04/08/19 | 04/08/19 | Mat | Req 5155 |  |  |  |  | -1171.38 |  | 0 | 0
220 | Roughin Material | AP | 260 | 03/25/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 48.45 | 4265219-00 | 0 | 0
220 | Roughin Material | AP | 644 | 03/28/19 | 04/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 126.29 | 4265455-00 | 0 | 0
220 | Roughin Material | GL | 906 | 04/30/19 | 04/30/19 | Mat | Req 5921 |  |  |  |  | 32.44 |  | 0 | 0
220 | Roughin Material | GL | 544 | 05/21/19 | 05/21/19 | Mat | Req 5950 |  |  |  |  | -664.57 |  | 0 | 0
220 | Roughin Material | GL | 545 | 05/21/19 | 05/21/19 | Mat | Req 5951 |  |  |  |  | -269.71 |  | 0 | 0
220 | Roughin Material | GL | 546 | 05/21/19 | 05/21/19 | Mat | Req 5952 |  |  |  |  | -659.62 |  | 0 | 0
220 | Roughin Material | GL | 549 | 05/21/19 | 05/21/19 | Mat | Req 5954 |  |  |  |  | -773.1 |  | 0 | 0
220 | Roughin Material | GL | 819 | 05/30/19 | 05/30/19 | Mat | Req 5977 |  |  |  |  | 597.74 |  | 0 | 0
220 | Roughin Material | GL | 145 | 06/05/19 | 06/05/19 | Mat | Req 5262 |  |  |  |  | 19.64 |  | 0 | 0
220 | Roughin Material | AP | 596 | 06/11/19 | 06/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 58.9 | 4268668-00 | 0 | 0
220 | Roughin Material | GL | 141 | 07/09/19 | 07/09/19 | Mat | Req 6105 |  |  |  |  | 89.38 |  | 0 | 0
230 | Finish Material | GL | 784 | 02/21/18 | 02/21/18 | Mat | Req 3485 |  |  |  |  | 83.88 |  | 0 | 0
230 | Finish Material | AP | 751 | 02/21/18 | 02/27/18 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 5197 | 16226 | 0 | 0
230 | Finish Material | GL | 691 | 03/26/18 | 03/26/18 | Mat | Req 4232 |  |  |  |  | 446.46 |  | 0 | 0
230 | Finish Material | GL | 842 | 03/31/18 | 03/31/18 | Mat | Req 4280 |  |  |  |  | 41.94 |  | 0 | 0
230 | Finish Material | GL | 399 | 04/18/18 | 04/18/18 | Mat | Req 3587 |  |  |  |  | 41.94 |  | 0 | 0
230 | Finish Material | GL | 110 | 05/04/18 | 05/04/18 | Mat | Req 3645 |  |  |  |  | 104.3 |  | 0 | 0
230 | Finish Material | GL | 553 | 06/15/18 | 06/15/18 | Mat | Req 3700 |  |  |  |  | 104.3 |  | 0 | 0
230 | Finish Material | GL | 400 | 07/16/18 | 07/16/18 | Mat | Req 4447 |  |  |  |  | 126.77 |  | 0 | 0
230 | Finish Material | AP | 464 | 07/19/18 | 08/15/18 | 1231KS | Keller Supply Company |  |  |  |  | 517.54 | S012072675.001 | 0 | 0
230 | Finish Material | AP | 465 | 07/19/18 | 08/15/18 | 1231KS | Keller Supply Company |  |  |  |  | 10.15 | S012072675.002 | 0 | 0
230 | Finish Material | AP | 20 | 08/14/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4410.53 | 4253138-00 | 0 | 0
230 | Finish Material | GL | 121 | 09/07/18 | 09/07/18 | Mat | Req 5322 |  |  |  |  | 417.2 |  | 0 | 0
230 | Finish Material | AP | 230 | 09/04/18 | 09/11/18 | 7230BB | Best Bath Systems |  |  |  |  | 7140.7 | 192648-IN | 0 | 0
230 | Finish Material | AP | 415 | 08/30/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5431.2 | 4256234-00 | 0 | 0
230 | Finish Material | AP | 571 | 09/19/18 | 09/20/18 | 7230BB | Best Bath Systems |  |  |  |  | 8925.89 | 193307-IN | 0 | 0
230 | Finish Material | GL | 615 | 09/25/18 | 09/25/18 | Mat | Req 5381 |  |  |  |  | 1989.59 |  | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | AP | 429 | 09/25/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1889.49 | 4256080-00 | 0 | 0
230 | Finish Material | AP | 538 | 09/25/18 | 10/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2680.23 | 4256081-00 | 0 | 0
230 | Finish Material | GL | 571 | 10/22/18 | 10/22/18 | Mat | Req 4723 |  |  |  |  | 2790.79 |  | 0 | 0
230 | Finish Material | AP | 604 | 09/26/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3360.35 | 4256080-01 | 0 | 0
230 | Finish Material | AP | 605 | 09/26/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1120.12 | 4256080-02 | 0 | 0
230 | Finish Material | AP | 606 | 09/26/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 746.74 | 4256081-01 | 0 | 0
230 | Finish Material | AP | 607 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4173.72 | 4256082-00 | 0 | 0
230 | Finish Material | AP | 608 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3733.72 | 4256082-01 | 0 | 0
230 | Finish Material | AP | 679 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 746.74 | 4256080-03 | 0 | 0
230 | Finish Material | AP | 680 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3246.98 | 4256083-00 | 0 | 0
230 | Finish Material | AP | 681 | 09/28/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2240.23 | 4256083-01 | 0 | 0
230 | Finish Material | AP | 683 | 10/01/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4173.73 | 4256084-00 | 0 | 0
230 | Finish Material | AP | 684 | 10/01/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3733.72 | 4256084-01 | 0 | 0
230 | Finish Material | AP | 785 | 10/02/18 | 10/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 746.74 | 4256081-02 | 0 | 0
230 | Finish Material | AP | 712 | 09/28/18 | 11/01/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -3246.98 | 4256083-00A | 0 | 0
230 | Finish Material | AP | 713 | 09/28/18 | 11/01/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3426.98 | 4256083-00B | 0 | 0
230 | Finish Material | AP | 108 | 10/02/18 | 11/02/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1493.49 | 4256083-02 | 0 | 0
230 | Finish Material | AP | 109 | 10/02/18 | 11/02/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 834.74 | 4256085-00 | 0 | 0
230 | Finish Material | GL | 312 | 11/09/18 | 11/09/18 | Mat | Req 4777 |  |  |  |  | 200 |  | 0 | 0
230 | Finish Material | GL | 318 | 11/09/18 | 11/09/18 | Mat | Req 4760 |  |  |  |  | 1137.6 |  | 0 | 0
230 | Finish Material | AP | 415 | 10/12/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 746.74 | 4256083-03 | 0 | 0
230 | Finish Material | AP | 416 | 10/12/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3426.98 | 4258192-00 | 0 | 0
230 | Finish Material | AP | 702 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 746.74 | 4258192-01 | 0 | 0
230 | Finish Material | AP | 715 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 373.37 | 4256085-01 | 0 | 0
230 | Finish Material | GL | 781 | 11/26/18 | 11/26/18 | Mat | Req 4850 |  |  |  |  | 998.7 |  | 0 | 0
230 | Finish Material | GL | 1000 | 11/30/18 | 11/30/18 | Mat | Req 5575 |  |  |  |  | 7.69 |  | 0 | 0
230 | Finish Material | AP | 383 | 11/13/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -440 | 4259961-00 | 0 | 0
230 | Finish Material | AP | 82 | 12/05/18 | 01/03/19 | 5560CH | California Hydronics Corp |  |  |  |  | 41191 | 2115523 | 0 | 0
230 | Finish Material | GL | 410 | 01/15/19 | 01/15/19 | Mat | Req 4905 |  |  |  |  | 305.69 |  | 0 | 0
230 | Finish Material | AP | 446 | 12/21/18 | 01/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 469.3 | S012568281.001 | 0 | 0
230 | Finish Material | AP | 598 | 12/14/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 373.37 | 4256085-02 | 0 | 0
230 | Finish Material | GL | 673 | 01/23/19 | 01/23/19 | Mat | Req 4973 |  |  |  |  | 635.73 |  | 0 | 0
230 | Finish Material | AP | 903 | 01/14/19 | 01/30/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 242.15 | 700000 | 0 | 0
230 | Finish Material | GL | 287 | 02/08/19 | 02/08/19 | Mat | Req 5686 |  |  |  |  | 1845.93 |  | 0 | 0
230 | Finish Material | GL | 356 | 03/08/19 | 03/08/19 | Mat | Req 5058 |  |  |  |  | 1675.33 |  | 0 | 0
230 | Finish Material | AP | 398 | 02/15/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 58.84 | 4263493-00 | 0 | 0
230 | Finish Material | GL | 593 | 03/15/19 | 03/15/19 | Mat | Req 5812 |  |  |  |  | 1356.57 |  | 0 | 0
230 | Finish Material | GL | 612 | 03/15/19 | 03/15/19 | Mat | Req 5062 |  |  |  |  | 196.8 |  | 0 | 0
230 | Finish Material | GL | 612 | 03/15/19 | 03/15/19 | Mat | Req 5062 |  |  |  |  | -196.8 |  | 0 | 0
230 | Finish Material | AP | 646 | 02/28/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 246.25 | 4247862-00 | 0 | 0
230 | Finish Material | AP | 659 | 03/05/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -15.66 | 4264266-00 | 0 | 0
230 | Finish Material | AP | 48 | 03/11/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1843 | 4247861-01 | 0 | 0
230 | Finish Material | AP | 49 | 03/11/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -16.68 | 4264594-00 | 0 | 0
230 | Finish Material | AP | 495 | 03/11/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 16.68 | 4264594-00A | 0 | 0
230 | Finish Material | AP | 496 | 03/11/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -16.86 | 4264594-00B | 0 | 0
230 | Finish Material | GL | 223 | 04/08/19 | 04/08/19 | Mat | Req 5116 |  |  |  |  | 1272.57 |  | 0 | 0
230 | Finish Material | AP | 259 | 03/25/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 7693.91 | 4263361-00 | 0 | 0
230 | Finish Material | AP | 494 | 03/15/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 461.37 | 4264379-00 | 0 | 0
230 | Finish Material | AP | 506 | 03/27/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8097.5 | 4263362-00 | 0 | 0
230 | Finish Material | AP | 645 | 03/29/19 | 04/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1901.25 | 4247862-02 | 0 | 0
230 | Finish Material | AP | 656 | 04/02/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 26.5 | 4265670-00 | 0 | 0
230 | Finish Material | AP | 664 | 04/03/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 371 | 4265670-01 | 0 | 0
230 | Finish Material | GL | 701 | 04/24/19 | 04/24/19 | Mat | Req 5152 |  |  |  |  | 1219.63 |  | 0 | 0
230 | Finish Material | AP | 710 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6256.5 | 4247862-03 | 0 | 0
230 | Finish Material | AP | 711 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 218.46 | 4263361-01 | 0 | 0
230 | Finish Material | GL | 907 | 04/30/19 | 04/30/19 | Mat | Req 5920 |  |  |  |  | 241.31 |  | 0 | 0
230 | Finish Material | AP | 280 | 04/16/19 | 05/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -88 | 4266248-00 | 0 | 0
230 | Finish Material | AP | 352 | 04/23/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8097.5 | 4263363-00 | 0 | 0
230 | Finish Material | GL | 547 | 05/21/19 | 05/21/19 | Mat | Req 5953 |  |  |  |  | -974.09 |  | 0 | 0
230 | Finish Material | GL | 711 | 05/23/19 | 05/23/19 | 1380RS | Inv 4266608-00 |  |  |  |  | 16.62 |  | 0 | 0
230 | Finish Material | AP | 740 | 05/01/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8097.5 | 4263364-00 | 0 | 0
230 | Finish Material | AP | 771 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8315.3 | 4263365-00 | 0 | 0
230 | Finish Material | GL | 820 | 05/30/19 | 05/30/19 | Mat | Req 5976 |  |  |  |  | 2927.3 |  | 0 | 0
230 | Finish Material | GL | 823 | 05/30/19 | 05/30/19 | Mat | Req 5980 |  |  |  |  | 42.87 |  | 0 | 0
230 | Finish Material | GL | 850 | 05/30/19 | 05/30/19 | Mat | Req 5222 |  |  |  |  | 97.53 |  | 0 | 0
230 | Finish Material | GL | 143 | 06/05/19 | 06/05/19 | Mat | Req 5259 |  |  |  |  | 544.22 |  | 0 | 0
230 | Finish Material | AP | 282 | 05/17/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 197.25 | 4267610-00 | 0 | 0
230 | Finish Material | AP | 283 | 05/17/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 503.26 | 4267633-00 | 0 | 0
230 | Finish Material | AP | 284 | 05/20/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 196 | 4247862-04 | 0 | 0
230 | Finish Material | AP | 304 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2660.55 | 4263366-00 | 0 | 0
230 | Finish Material | AP | 305 | 06/03/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 12.34 | 4263365-02 | 0 | 0
230 | Finish Material | AP | 380 | 05/23/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 8481.06 | S012800451.001 | 0 | 0
230 | Finish Material | AP | 441 | 06/05/19 | 06/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 37.12 | 4263366-01 | 0 | 0
230 | Finish Material | AP | 442 | 06/05/19 | 06/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 582.98 | 4268174-00 | 0 | 0
230 | Finish Material | AP | 785 | 06/20/19 | 06/13/19 | 1231KS | Keller Supply Company |  |  |  |  | -72.59 | S012800451.002 | 0 | 0
230 | Finish Material | AP | 594 | 06/11/19 | 06/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 200.22 | 4263366-02 | 0 | 0
230 | Finish Material | AP | 595 | 06/11/19 | 06/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 173.02 | 4268174-01 | 0 | 0
230 | Finish Material | AP | 739 | 06/13/19 | 06/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 227.55 | 4268709-00 | 0 | 0
230 | Finish Material | AP | 415 | 06/05/19 | 07/01/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -582.98 | 4268174-00A | 0 | 0
230 | Finish Material | AP | 416 | 06/05/19 | 07/01/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 528.98 | 4268174-00B | 0 | 0
230 | Finish Material | GL | 139 | 07/09/19 | 07/09/19 | Mat | Req 6103 |  |  |  |  | 38.56 |  | 0 | 0
230 | Finish Material | AP | 272 | 06/20/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 242 | 4269129-00 | 0 | 0
240 | Gas Material | AP | 20 | 10/29/18 | 12/05/18 | 1231KS | Keller Supply Company |  |  |  |  | 609 | S012403774.001 | 0 | 0
240 | Gas Material | AP | 505 | 11/16/18 | 12/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1319 | 4258923-00 | 0 | 0
240 | Gas Material | AP | 681 | 11/26/18 | 12/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 71.58 | 6731283 | 0 | 0
240 | Gas Material | AP | 391 | 12/04/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 85.15 | 4260713-00 | 0 | 0
240 | Gas Material | AP | 403 | 12/05/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 89.98 | 4260713-01 | 0 | 0
240 | Gas Material | AP | 597 | 11/28/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 47.56 | 4260484-00 | 0 | 0
240 | Gas Material | GL | 653 | 01/22/19 | 01/22/19 | Mat | Req 4942 |  |  |  |  | 51.8 |  | 0 | 0
240 | Gas Material | AP | 269 | 01/07/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 217.96 | 4261880-00 | 0 | 0
240 | Gas Material | AP | 271 | 01/08/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 81.97 | 4261990-00 | 0 | 0
240 | Gas Material | AP | 272 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 134.8 | 4262042-00 | 0 | 0
240 | Gas Material | AP | 472 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 26.19 | 4262042-01 | 0 | 0
240 | Gas Material | AP | 484 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 80.35 | 4262255-00 | 0 | 0
240 | Gas Material | AP | 672 | 01/28/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6.28 | 4262255-01 | 0 | 0
240 | Gas Material | AP | 707 | 02/06/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 153.65 | 4263223-00 | 0 | 0
240 | Gas Material | AP | 708 | 02/07/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 74.95 | 4263223-01 | 0 | 0
240 | Gas Material | AP | 751 | 02/13/19 | 02/27/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13.54 | 4263342-00 | 0 | 0
240 | Gas Material | AP | 474 | 02/26/19 | 03/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5.15 | 4263854-00 | 0 | 0
240 | Gas Material | GL | 540 | 05/21/19 | 05/21/19 | Mat | Req 5956 |  |  |  |  | -590.72 |  | 0 | 0
240 | Gas Material | GL | 548 | 05/21/19 | 05/21/19 | Mat | Req 5955 |  |  |  |  | -167.3 |  | 0 | 0
240 | Gas Material | AP | 722 | 04/26/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.25 | 4266709-00 | 0 | 0
240 | Gas Material | GL | 142 | 07/09/19 | 07/09/19 | Mat | Req 6106 |  |  |  |  | 4.38 |  | 0 | 0
240 | Gas Material | AP | 436 | 06/28/19 | 07/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 309.1 | 4269520-00 | 0 | 0
240 | Gas Material | AP | 496 | 07/02/19 | 08/13/19 | 1234CO | Capital One Credit Card |  |  |  |  | 22.2 | 070219JB | 0 | 0
241 | Water Main/Insulation Mat | GL | 569 | 10/22/18 | 10/22/18 | Mat | Req 4725 |  |  |  |  | 1011.8 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 174 | 10/04/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 227.2 | S8959563.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 335 | 10/24/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 10564.28 | S8984651.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 336 | 10/24/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 251.92 | S8984651.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 337 | 10/24/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 43.3 | S8984651.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 338 | 10/24/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 342.44 | S8984651.004 | 0 | 0
241 | Water Main/Insulation Mat | AP | 339 | 10/24/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 387.45 | S8984651.005 | 0 | 0
241 | Water Main/Insulation Mat | AP | 372 | 10/23/18 | 11/13/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3616.6 | S8984346.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 421 | 10/23/18 | 11/13/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 377.24 | S8984346.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 1001 | 11/30/18 | 11/30/18 | Mat | Req 5574 |  |  |  |  | 14.74 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 1031 | 11/06/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1105.52 | S8952898.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1033 | 11/09/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1417.58 | S8952898.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 7 | 10/29/18 | 12/04/18 | 1231KS | Keller Supply Company |  |  |  |  | 4179.85 | S012416341.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 8 | 11/01/18 | 12/04/18 | 1231KS | Keller Supply Company |  |  |  |  | 303.46 | S012416341.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 601 | 12/21/18 | 12/21/18 | Mat | Req 5627 |  |  |  |  | 79.29 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 660 | 12/10/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 381.63 | S9049712.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 332 | 01/11/19 | 01/11/19 | Mat | Req 4859 |  |  |  |  | 336 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 412 | 01/15/19 | 01/15/19 | Mat | Req 4903 |  |  |  |  | 18.86 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 923 | 01/04/19 | 01/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1750.86 | 4261314-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 518 | 01/30/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 218 | S9114447.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 520 | 02/13/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 8715.95 | S9126384.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 521 | 02/13/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 62.73 | S9126384.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 550 | 02/15/19 | 02/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1659.97 | S9134495.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 673 | 01/29/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -94.92 | 4262935-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 155 | 03/04/19 | 03/04/19 | Mat | Req 5017 |  |  |  |  | 191 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 342 | 03/08/19 | 03/08/19 | Mat | Req 5829 |  |  |  |  | 319.8 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 357 | 03/08/19 | 03/08/19 | Mat | Req 5032 |  |  |  |  | 1227.15 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 393 | 02/21/19 | 03/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1130.39 | S9140170.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 422 | 02/21/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 213.96 | 4263553-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 595 | 03/15/19 | 03/15/19 | Mat | Req 5810 |  |  |  |  | 399.32 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 866 | 03/08/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 689.54 | S9160548.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 167 | 03/11/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4368.66 | 4264443-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 272 | 04/08/19 | 04/08/19 | Mat | Req 5154 |  |  |  |  | -828.61 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 273 | 04/08/19 | 04/08/19 | Mat | Req 5153 |  |  |  |  | -3572.1 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 460 | 03/27/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 766.11 | S9185809.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 461 | 04/04/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 332.72 | S9185809.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 920 | 04/12/19 | 04/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 89.08 | S9158509.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 134 | 04/11/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -30.6 | 4266113-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 550 | 05/21/19 | 05/21/19 | Mat | Req 5957 |  |  |  |  | -1853.16 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 551 | 05/21/19 | 05/21/19 | Mat | Req 5958 |  |  |  |  | -1144.67 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 824 | 05/30/19 | 05/30/19 | Mat | Req 5981 |  |  |  |  | 93.6 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 849 | 05/30/19 | 05/30/19 | Mat | Req 5221 |  |  |  |  | 684.06 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 13 | 05/21/19 | 06/03/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 153.14 | S9267418.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 144 | 06/05/19 | 06/05/19 | Mat | Req 5260 |  |  |  |  | 179.2 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 260 | 05/15/19 | 06/06/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 167.04 | 4267526-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 369 | 05/24/19 | 06/11/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 145.7 | 7238576 | 0 | 0
241 | Water Main/Insulation Mat | GL | 817 | 06/26/19 | 06/26/19 | Mat | Req 6025 |  |  |  |  | -659.54 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 819 | 06/26/19 | 06/26/19 | Mat | Req 6027 |  |  |  |  | -116.04 |  | 0 | 0
242 | Mech Room Material | GL | 286 | 02/08/19 | 02/08/19 | Mat | Req 5687 |  |  |  |  | 1944.97 |  | 0 | 0
242 | Mech Room Material | AP | 519 | 02/13/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 512.99 | S9124538.002 | 0 | 0
242 | Mech Room Material | AP | 523 | 02/12/19 | 02/19/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 567.45 | S9124538.003 | 0 | 0
242 | Mech Room Material | AP | 530 | 02/07/19 | 02/19/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 9768.71 | 6938603 | 0 | 0
242 | Mech Room Material | AP | 557 | 02/13/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 843.68 | 6945990 | 0 | 0
242 | Mech Room Material | AP | 558 | 02/15/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2453.62 | 6958799 | 0 | 0
242 | Mech Room Material | AP | 559 | 02/18/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4224.05 | 696458 | 0 | 0
242 | Mech Room Material | AP | 727 | 02/21/19 | 02/27/19 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 245.06 | K165727 | 0 | 0
242 | Mech Room Material | AP | 752 | 02/13/19 | 02/27/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 372.97 | 4263382-00 | 0 | 0
242 | Mech Room Material | GL | 197 | 03/01/19 | 03/01/19 | CK#5686 | Robert Hubbard |  |  |  |  | 58.42 |  | 0 | 0
242 | Mech Room Material | GL | 145 | 03/04/19 | 03/04/19 | Mat | Req 5048 |  |  |  |  | 3036.45 |  | 0 | 0
242 | Mech Room Material | GL | 146 | 03/04/19 | 03/04/19 | Mat | Req 5049 |  |  |  |  | 255.2 |  | 0 | 0
242 | Mech Room Material | GL | 157 | 03/04/19 | 03/04/19 | Mat | Req 5019 |  |  |  |  | 630 |  | 0 | 0
242 | Mech Room Material | AP | 223 | 02/18/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 378.92 | S9137696.002 | 0 | 0
242 | Mech Room Material | AP | 228 | 02/18/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 578.98 | S9137696.001 | 0 | 0
242 | Mech Room Material | AP | 229 | 02/20/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 174.74 | S9137696.004 | 0 | 0
242 | Mech Room Material | AP | 238 | 02/20/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 693.43 | 6964589-1 | 0 | 0
242 | Mech Room Material | GL | 348 | 03/08/19 | 03/08/19 | Mat | Req 5059 |  |  |  |  | 1325.92 |  | 0 | 0
242 | Mech Room Material | GL | 594 | 03/15/19 | 03/15/19 | Mat | Req 5811 |  |  |  |  | 132.05 |  | 0 | 0
242 | Mech Room Material | GL | 611 | 03/15/19 | 03/15/19 | Mat | Req 5831 |  |  |  |  | -564.08 |  | 0 | 0
242 | Mech Room Material | GL | 613 | 03/15/19 | 03/15/19 | Mat | Req 5064 |  |  |  |  | -4432.95 |  | 0 | 0
242 | Mech Room Material | AP | 790 | 03/06/19 | 03/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 128.38 | 4264299-00 | 0 | 0
242 | Mech Room Material | AP | 899 | 03/20/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -407.19 | CM749741 | 0 | 0
242 | Mech Room Material | AP | 360 | 04/24/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 16.62 | 4266608-00 | 0 | 0
242 | Mech Room Material | GL | 711 | 05/23/19 | 05/23/19 | 1380RS | Inv 4266608-00 |  |  |  |  | -16.62 |  | 0 | 0
242 | Mech Room Material | GL | 822 | 05/30/19 | 05/30/19 | Mat | Req 5979 |  |  |  |  | 36.31 |  | 0 | 0
242 | Mech Room Material | GL | 851 | 05/30/19 | 05/30/19 | Mat | Req 5223 |  |  |  |  | 74.8 |  | 0 | 0
242 | Mech Room Material | AP | 12 | 05/20/19 | 06/03/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1000.51 | S9265326.001 | 0 | 0
242 | Mech Room Material | GL | 137 | 06/05/19 | 06/05/19 | Mat | Req 5261 |  |  |  |  | 23.81 |  | 0 | 0
242 | Mech Room Material | AP | 249 | 06/06/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 24.07 | 060619JB1 | 0 | 0
242 | Mech Room Material | GL | 369 | 07/10/19 | 07/10/19 | CK#5793 | Robert Hubbard |  |  |  |  | 6.59 |  | 0 | 0
600 | Subcontractor | AP | 129 | 09/18/19 | 10/05/18 | 4320MC | MAD Concrete Cutting & Coring, Inc. |  |  |  |  | 1690 | 8072 | 0 | 0
600 | Subcontractor | AP | 914 | 01/11/19 | 01/30/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 712 | 72063 | 0 | 0
600 | Subcontractor | AP | 912 | 03/11/19 | 03/26/19 | 1504CA | Chip Away Bathtub Repair, Inc. |  |  |  |  | 1515 | 22862 | 0 | 0
600 | Subcontractor | AP | 25 | 03/15/19 | 04/02/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 975.2 | 72564 | 0 | 0
600 | Subcontractor | AP | 864 | 03/07/19 | 04/30/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 615 | 72533 | 0 | 0
600 | Subcontractor | AP | 807 | 05/23/19 | 05/29/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 3515.62 | 16607-5515 | 0 | 0
600 | Subcontractor | AP | 721 | 06/10/19 | 06/24/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 215 | INV01460 | 0 | 0
600 | Subcontractor | AP | 731 | 06/21/19 | 06/24/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 1171.88 | 16622-5514 | 0 | 0
601 | Engineering/Plans | AP | 539 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 2626 | 6735 | 0 | 0
601 | Engineering/Plans | AP | 109 | 12/19/17 | 01/05/18 | 1625FE | Franklin Engineering |  |  |  |  | 5812.5 | 6773 | 0 | 0
601 | Engineering/Plans | AP | 580 | 01/19/18 | 01/24/18 | 1625FE | Franklin Engineering |  |  |  |  | 636 | 6813 | 0 | 0
601 | Engineering/Plans | AP | 747 | 02/20/18 | 02/27/18 | 1625FE | Franklin Engineering |  |  |  |  | 4875 | 6842 | 0 | 0
601 | Engineering/Plans | AP | 647 | 03/21/18 | 03/26/18 | 1625FE | Franklin Engineering |  |  |  |  | 8942 | 6879 | 0 | 0
601 | Engineering/Plans | AP | 828 | 04/20/18 | 04/30/18 | 1625FE | Franklin Engineering |  |  |  |  | 9227.25 | 6916 | 0 | 0
601 | Engineering/Plans | AP | 162 | 04/02/18 | 05/08/18 | 1288DR | DRSi |  |  |  |  | 201.93 | 461436 | 0 | 0
601 | Engineering/Plans | AP | 239 | 05/29/18 | 06/06/18 | 1288DR | DRSi |  |  |  |  | 17.85 | 465418 | 0 | 0
601 | Engineering/Plans | AP | 789 | 06/19/18 | 06/22/18 | 1625FE | Franklin Engineering |  |  |  |  | 648.25 | 6978 | 0 | 0
601 | Engineering/Plans | AP | 610 | 07/18/18 | 07/23/18 | 1625FE | Franklin Engineering |  |  |  |  | 1518 | 7010 | 0 | 0
602 | Rental Equipment | AP | 804 | 05/23/19 | 05/29/19 | 1799AW | AllWest Underground, Inc. |  |  |  |  | 199.25 | 84330 | 0 | 0
603 | Permits & Licenses | AP | 549 | 09/14/17 | 09/21/17 | 1234CO | Capital One Credit Card |  |  |  |  | 210 | 091417A | 0 | 0
603 | Permits & Licenses | AP | 550 | 09/14/17 | 09/21/17 | 1234CO | Capital One Credit Card |  |  |  |  | 210 | 091417B | 0 | 0
603 | Permits & Licenses | AP | 551 | 09/14/17 | 09/21/17 | 1234CO | Capital One Credit Card |  |  |  |  | 6189 | 091417C | 0 | 0
603 | Permits & Licenses | AP | 770 | 04/03/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 201 | 040318 | 0 | 0
603 | Permits & Licenses | AP | 194 | 05/31/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402 | 053118 | 0 | 0
603 | Permits & Licenses | AP | 1019 | 03/19/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 201 | 031919J | 0 | 0
603 | Permits & Licenses | AP | 225 | 06/12/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 88 | 061219J | 0 | 0
607 | Other Expenses | AP | 822 | 02/10/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 021018D | 0 | 0
607 | Other Expenses | AP | 824 | 02/16/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 021618A | 0 | 0
607 | Other Expenses | AP | 948 | 03/15/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 031518E | 0 | 0
607 | Other Expenses | AP | 758 | 04/03/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 4.47 | 040318A | 0 | 0
607 | Other Expenses | AP | 797 | 04/15/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 488.16 | 041516E | 0 | 0
607 | Other Expenses | AP | 826 | 04/26/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 5 | 042618 | 0 | 0
607 | Other Expenses | AP | 865 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 051518F | 0 | 0
607 | Other Expenses | AP | 193 | 05/29/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 7.36 | 052918J | 0 | 0
607 | Other Expenses | AP | 218 | 06/15/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 061518R6 | 0 | 0
607 | Other Expenses | AP | 147 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 061518R5 | 0 | 0
607 | Other Expenses | AP | 1131 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 051818R5 | 0 | 0
607 | Other Expenses | AP | 826 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 091518R5 | 0 | 0
607 | Other Expenses | AP | 834 | 10/15/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 101518R5 | 0 | 0
607 | Other Expenses | AP | 488 | 11/15/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 111518R5 | 0 | 0
607 | Other Expenses | AP | 857 | 12/21/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 122118R2 | 0 | 0
607 | Other Expenses | GL | 406 | 02/14/19 | 02/14/19 | CK#5674 | Robert Hubbard |  |  |  |  | 6.75 |  | 0 | 0
607 | Other Expenses | AP | 454 | 01/15/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 011519R5 | 0 | 0
607 | Other Expenses | AP | 131 | 02/15/19 | 03/04/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 021519R4 | 0 | 0
607 | Other Expenses | AP | 1043 | 03/16/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 031619R4 | 0 | 0
607 | Other Expenses | AP | 978 | 04/16/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 041619R4 | 0 | 0
607 | Other Expenses | AP | 81 | 05/16/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 051619R5 | 0 | 0
607 | Other Expenses | AP | 226 | 06/12/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 12.26 | 061219J2 | 0 | 0
607 | Other Expenses | AP | 244 | 06/16/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 488.16 | 061619R3 | 0 | 0
607 | Other Expenses | AP | 365 | 07/11/19 | 08/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | -478.16 | 071119C1 | 0 | 0
995 | Payroll Burden | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 3 | 11/01/17 | 11/03/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 150 | 11/08/17 | 11/10/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -83.16 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 331.74 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 02/21/18 | 02/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 109.77 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 02/28/18 | 03/02/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 9.98 |  | 0 | 0
995 | Payroll Burden | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 352 | 03/14/18 | 03/16/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 345.93 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.96 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 136.6 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 05/23/18 | 05/25/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 68.3 |  | 0 | 0
995 | Payroll Burden | PR | 802 | 05/23/18 | 05/25/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 181.84 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/30/18 | 06/01/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 185.38 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 05/30/18 | 06/01/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 345.49 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 14.64 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 10 | 07/04/18 | 07/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 08/08/18 | 08/10/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 08/08/18 | 08/10/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 08/08/18 | 08/10/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 08/08/18 | 08/10/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 08/15/18 | 08/17/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 08/15/18 | 08/17/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 08/15/18 | 08/17/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 546 | 08/15/18 | 08/17/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 363.23 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 08/22/18 | 08/24/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 766 | 08/22/18 | 08/24/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 773 | 08/22/18 | 08/24/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 796 | 08/22/18 | 08/24/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 08/22/18 | 08/24/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 08/22/18 | 08/24/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 521.56 |  | 0 | 0
995 | Payroll Burden | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 1001 | 08/29/18 | 08/31/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 1021 | 08/29/18 | 08/31/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 86.7 |  | 0 | 0
995 | Payroll Burden | PR | 1028 | 08/29/18 | 08/31/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 1050 | 08/29/18 | 08/31/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 1060 | 08/29/18 | 08/31/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 1061 | 08/29/18 | 08/31/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 596.06 |  | 0 | 0
995 | Payroll Burden | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 09/05/18 | 09/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 09/05/18 | 09/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 90 | 09/05/18 | 09/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 09/05/18 | 09/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 101 | 09/05/18 | 09/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 465.68 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 09/12/18 | 09/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 09/12/18 | 09/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 09/12/18 | 09/14/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 09/12/18 | 09/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 09/12/18 | 09/14/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 309 | 09/12/18 | 09/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 09/12/18 | 09/14/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 596.06 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 09/19/18 | 09/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 09/19/18 | 09/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 09/19/18 | 09/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 09/19/18 | 09/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 09/19/18 | 09/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 09/19/18 | 09/21/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 09/19/18 | 09/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 546 | 09/19/18 | 09/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 09/19/18 | 09/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 09/19/18 | 09/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 521.56 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 671 | 09/26/18 | 09/28/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 09/26/18 | 09/28/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 697 | 09/26/18 | 09/28/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 702 | 09/26/18 | 09/28/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 438.18 |  | 0 | 0
995 | Payroll Burden | PR | 707 | 09/26/18 | 09/28/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 713 | 09/26/18 | 09/28/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 09/26/18 | 09/28/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 09/26/18 | 09/28/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 733 | 09/26/18 | 09/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 09/26/18 | 09/28/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 10/03/18 | 10/05/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 54 | 10/03/18 | 10/05/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 10/03/18 | 10/05/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 10/03/18 | 10/05/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 10/03/18 | 10/05/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/03/18 | 10/05/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 10/03/18 | 10/05/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 96 | 10/03/18 | 10/05/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 10/03/18 | 10/05/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 98 | 10/03/18 | 10/05/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 10/10/18 | 10/12/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 10/10/18 | 10/12/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 10/10/18 | 10/12/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 10/10/18 | 10/12/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 10/10/18 | 10/12/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 10/10/18 | 10/12/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 277 | 10/10/18 | 10/12/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 10/10/18 | 10/12/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 10/10/18 | 10/12/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 302 | 10/10/18 | 10/12/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 10/10/18 | 10/12/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 10/10/18 | 10/12/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 549.5 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 10/17/18 | 10/19/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 10/17/18 | 10/19/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 10/17/18 | 10/19/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 10/17/18 | 10/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 10/17/18 | 10/19/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 10/17/18 | 10/19/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 10/17/18 | 10/19/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 10/24/18 | 10/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 707 | 10/24/18 | 10/26/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 271.42 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 10/24/18 | 10/26/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 10/24/18 | 10/26/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 10/24/18 | 10/26/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 726.45 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 8.65 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 201.79 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 22.62 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 347.7 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 10/31/18 | 11/02/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 670.57 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 188 | 11/07/18 | 11/09/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 286.5 |  | 0 | 0
995 | Payroll Burden | PR | 196 | 11/07/18 | 11/09/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 387.62 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 11/14/18 | 11/16/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 211.11 |  | 0 | 0
995 | Payroll Burden | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 360.9 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 459 | 11/14/18 | 11/16/18 | GO56 | Gonzalez Hernandez, Josue | 0 | 0 | 0 | 0 | 144.69 |  | 0 | 0
995 | Payroll Burden | PR | 461 | 11/14/18 | 11/16/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 11/14/18 | 11/16/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 11/14/18 | 11/16/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 175.29 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 11/14/18 | 11/16/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 471.88 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 433.08 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -433.08 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -745.08 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 433.08 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 11/21/18 | 11/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 282.73 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 81.49 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 11/21/18 | 11/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 39.58 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 58.21 |  | 0 | 0
995 | Payroll Burden | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 745.08 |  | 0 | 0
995 | Payroll Burden | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 834 | 11/28/18 | 11/30/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 277.19 |  | 0 | 0
995 | Payroll Burden | PR | 844 | 11/28/18 | 11/30/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 403.59 |  | 0 | 0
995 | Payroll Burden | PR | 853 | 11/28/18 | 11/30/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 860 | 11/28/18 | 11/30/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 263.88 |  | 0 | 0
995 | Payroll Burden | PR | 869 | 11/28/18 | 11/30/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 874 | 11/28/18 | 11/30/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 450.15 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 11/28/18 | 11/30/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 419.11 |  | 0 | 0
995 | Payroll Burden | PR | 894 | 11/28/18 | 11/30/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 398.71 |  | 0 | 0
995 | Payroll Burden | PR | 895 | 11/28/18 | 11/30/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 400.48 |  | 0 | 0
995 | Payroll Burden | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 190.71 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 648.4 |  | 0 | 0
995 | Payroll Burden | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 228.85 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | -38.58 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 12/12/18 | 12/14/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 22.62 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 311 | 12/12/18 | 12/14/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 437.29 |  | 0 | 0
995 | Payroll Burden | PR | 318 | 12/12/18 | 12/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 407.13 |  | 0 | 0
995 | Payroll Burden | PR | 332 | 12/12/18 | 12/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 12/12/18 | 12/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 133.49 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 171.63 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 12/19/18 | 12/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 12/19/18 | 12/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 465.68 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 12/19/18 | 12/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 484.3 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 12/19/18 | 12/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 622.67 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 12/19/18 | 12/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 316.66 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 12/19/18 | 12/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 540.18 |  | 0 | 0
995 | Payroll Burden | PR | 558 | 12/19/18 | 12/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 502.93 |  | 0 | 0
995 | Payroll Burden | PR | 572 | 12/19/18 | 12/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 540.18 |  | 0 | 0
995 | Payroll Burden | PR | 573 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 10.24 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 693 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | -10.24 |  | 0 | 0
995 | Payroll Burden | PR | 692 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 409.79 |  | 0 | 0
995 | Payroll Burden | PR | 703 | 12/26/18 | 12/28/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 711 | 12/26/18 | 12/28/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 712 | 12/26/18 | 12/28/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 713 | 12/26/18 | 12/28/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 12/26/18 | 12/28/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 728 | 12/26/18 | 12/28/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 742 | 12/26/18 | 12/28/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 12/26/18 | 12/28/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 763 | 12/26/18 | 12/28/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 764 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/02/19 | 01/04/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 01/02/19 | 01/04/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 288.28 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 01/02/19 | 01/04/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 299.81 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 01/02/19 | 01/04/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 01/02/19 | 01/04/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 196.03 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 01/02/19 | 01/04/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 334.4 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 01/02/19 | 01/04/19 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/02/19 | 01/04/19 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 01/02/19 | 01/04/19 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 01/09/19 | 01/11/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 01/09/19 | 01/11/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 01/09/19 | 01/11/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 01/16/19 | 01/18/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 01/16/19 | 01/18/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 01/16/19 | 01/18/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 590.74 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 01/16/19 | 01/18/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 01/16/19 | 01/18/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 719 | 01/23/19 | 01/25/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 729 | 01/23/19 | 01/25/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 730 | 01/23/19 | 01/25/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 738 | 01/23/19 | 01/25/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 01/23/19 | 01/25/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 01/23/19 | 01/25/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 01/30/19 | 02/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 184.5 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 01/30/19 | 02/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 01/30/19 | 02/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 163 | 02/06/19 | 02/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 172 | 02/06/19 | 02/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 288.28 |  | 0 | 0
995 | Payroll Burden | PR | 173 | 02/06/19 | 02/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 299.81 |  | 0 | 0
995 | Payroll Burden | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 15.08 |  | 0 | 0
995 | Payroll Burden | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 105.55 |  | 0 | 0
995 | Payroll Burden | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 201 | 02/06/19 | 02/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 231.51 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 02/13/19 | 02/15/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 02/13/19 | 02/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 02/13/19 | 02/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 349 | 02/13/19 | 02/15/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 217.32 |  | 0 | 0
995 | Payroll Burden | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 54.33 |  | 0 | 0
995 | Payroll Burden | PR | 363 | 02/13/19 | 02/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 180.06 |  | 0 | 0
995 | Payroll Burden | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 399.15 |  | 0 | 0
995 | Payroll Burden | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 585 | 02/20/19 | 02/22/19 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 593 | 02/20/19 | 02/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 645.74 |  | 0 | 0
995 | Payroll Burden | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 830.23 |  | 0 | 0
995 | Payroll Burden | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 376.98 |  | 0 | 0
995 | Payroll Burden | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 611 | 02/20/19 | 02/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 793.2 |  | 0 | 0
995 | Payroll Burden | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 424.43 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 02/20/19 | 02/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 617.35 |  | 0 | 0
995 | Payroll Burden | PR | 635 | 02/20/19 | 02/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 327.3 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 365.89 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 172.97 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 606.71 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 239.05 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 02/27/19 | 03/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 360.12 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 02/27/19 | 03/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 581.87 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 11.97 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 149.68 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 03/06/19 | 03/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 670.57 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 03/06/19 | 03/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 271.42 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 152.12 |  | 0 | 0
995 | Payroll Burden | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 57.88 |  | 0 | 0
995 | Payroll Burden | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 591.63 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 271.42 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 475.88 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 376.98 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 729 | 03/20/19 | 03/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 437.29 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 77.17 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 14.19 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -65.19 |  | 0 | 0
995 | Payroll Burden | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 231.51 |  | 0 | 0
995 | Payroll Burden | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 77.17 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 83 | 04/03/19 | 04/05/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 93 | 04/03/19 | 04/05/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 04/03/19 | 04/05/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 98.46 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 755 | 04/24/19 | 04/26/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 674.12 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 48.23 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 629.77 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 54.88 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 175 | 05/08/19 | 05/10/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 05/08/19 | 05/10/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 21.95 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 407 | 05/15/19 | 05/17/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 424 | 05/15/19 | 05/17/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 05/15/19 | 05/17/19 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 619 | 05/22/19 | 05/24/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 05/22/19 | 05/24/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 05/22/19 | 05/24/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 541.51 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 05/22/19 | 05/24/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 274.97 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 893 | 05/29/19 | 05/31/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 910 | 05/29/19 | 05/31/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 922 | 05/29/19 | 05/31/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 450.15 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 64.31 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 06/12/19 | 06/14/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 475.88 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 06/12/19 | 06/14/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 06/19/19 | 06/21/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 869 | 06/26/19 | 06/28/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 07/03/19 | 07/05/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 07/03/19 | 07/05/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 616 | 07/24/19 | 07/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 09/20/17 | 09/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 10/04/17 | 10/06/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 10/25/17 | 10/27/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 3 | 11/01/17 | 11/03/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 150 | 11/08/17 | 11/10/17 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 11/08/17 | 11/10/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 11/22/17 | 11/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 01/10/18 | 01/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 165 | 02/07/18 | 02/09/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 419 | 02/14/18 | 02/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 02/21/18 | 02/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 57.22 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 02/21/18 | 02/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 02/28/18 | 03/02/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 18.93 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 02/28/18 | 03/02/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 1.72 |  | 0 | 0
998 | Payroll Taxes | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 157 | 03/07/18 | 03/09/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 318 | 03/14/18 | 03/16/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 352 | 03/14/18 | 03/16/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 59.67 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 03/21/18 | 03/23/18 | AN14 | Anderson, Richard P | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 03/21/18 | 03/23/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 03/21/18 | 03/23/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 23.56 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 05/23/18 | 05/25/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 11.78 |  | 0 | 0
998 | Payroll Taxes | PR | 802 | 05/23/18 | 05/25/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 31.37 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/30/18 | 06/01/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 31.98 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 05/30/18 | 06/01/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 59.59 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 2.52 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 06/06/18 | 06/08/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 1013 | 06/27/18 | 06/29/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 1016 | 06/27/18 | 06/29/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 10 | 07/04/18 | 07/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 07/04/18 | 07/06/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 07/04/18 | 07/06/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 360 | 07/11/18 | 07/13/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 363 | 07/11/18 | 07/13/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 07/18/18 | 07/20/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 828 | 07/25/18 | 07/27/18 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 831 | 07/25/18 | 07/27/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 08/08/18 | 08/10/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 08/08/18 | 08/10/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 08/08/18 | 08/10/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 08/08/18 | 08/10/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 08/08/18 | 08/10/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 08/15/18 | 08/17/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 08/15/18 | 08/17/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 08/15/18 | 08/17/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 08/15/18 | 08/17/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 08/15/18 | 08/17/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 08/15/18 | 08/17/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 546 | 08/15/18 | 08/17/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 62.65 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 08/15/18 | 08/17/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 08/15/18 | 08/17/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 08/22/18 | 08/24/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 766 | 08/22/18 | 08/24/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 773 | 08/22/18 | 08/24/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 08/22/18 | 08/24/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 796 | 08/22/18 | 08/24/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 08/22/18 | 08/24/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 08/22/18 | 08/24/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 89.96 |  | 0 | 0
998 | Payroll Taxes | PR | 808 | 08/22/18 | 08/24/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 1001 | 08/29/18 | 08/31/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 08/29/18 | 08/31/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 1021 | 08/29/18 | 08/31/18 | GA72 | Gardner, Andrew M | 0 | 0 | 0 | 0 | 14.96 |  | 0 | 0
998 | Payroll Taxes | PR | 1028 | 08/29/18 | 08/31/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 1050 | 08/29/18 | 08/31/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 1060 | 08/29/18 | 08/31/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1061 | 08/29/18 | 08/31/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 102.82 |  | 0 | 0
998 | Payroll Taxes | PR | 1062 | 08/29/18 | 08/31/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 09/05/18 | 09/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 09/05/18 | 09/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 09/05/18 | 09/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 09/05/18 | 09/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 90 | 09/05/18 | 09/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 09/05/18 | 09/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 101 | 09/05/18 | 09/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 80.33 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 09/05/18 | 09/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 09/12/18 | 09/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 09/12/18 | 09/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 09/12/18 | 09/14/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 09/12/18 | 09/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 09/12/18 | 09/14/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 309 | 09/12/18 | 09/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 09/12/18 | 09/14/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 09/12/18 | 09/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 09/12/18 | 09/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 09/12/18 | 09/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 09/12/18 | 09/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 102.82 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 09/19/18 | 09/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 09/19/18 | 09/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 09/19/18 | 09/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 09/19/18 | 09/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 09/19/18 | 09/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 09/19/18 | 09/21/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 09/19/18 | 09/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 546 | 09/19/18 | 09/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 09/19/18 | 09/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 09/19/18 | 09/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 89.96 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 09/26/18 | 09/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 671 | 09/26/18 | 09/28/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 09/26/18 | 09/28/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 697 | 09/26/18 | 09/28/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 702 | 09/26/18 | 09/28/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 75.58 |  | 0 | 0
998 | Payroll Taxes | PR | 707 | 09/26/18 | 09/28/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 713 | 09/26/18 | 09/28/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 09/26/18 | 09/28/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 09/26/18 | 09/28/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 733 | 09/26/18 | 09/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 09/26/18 | 09/28/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 10/03/18 | 10/05/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 10/03/18 | 10/05/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 54 | 10/03/18 | 10/05/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 10/03/18 | 10/05/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 10/03/18 | 10/05/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 10/03/18 | 10/05/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/03/18 | 10/05/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 10/03/18 | 10/05/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 96 | 10/03/18 | 10/05/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 10/03/18 | 10/05/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 98 | 10/03/18 | 10/05/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 10/10/18 | 10/12/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 10/10/18 | 10/12/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 10/10/18 | 10/12/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 10/10/18 | 10/12/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 10/10/18 | 10/12/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 10/10/18 | 10/12/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 277 | 10/10/18 | 10/12/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 10/10/18 | 10/12/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 10/10/18 | 10/12/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 302 | 10/10/18 | 10/12/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 10/10/18 | 10/12/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 10/10/18 | 10/12/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 94.78 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 10/17/18 | 10/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 10/17/18 | 10/19/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 10/17/18 | 10/19/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 10/17/18 | 10/19/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 10/17/18 | 10/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 10/17/18 | 10/19/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 10/17/18 | 10/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 10/17/18 | 10/19/18 | OB46 | O'Bleness, Caleb N | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 10/17/18 | 10/19/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 10/17/18 | 10/19/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 502 | 10/17/18 | 10/19/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 10/17/18 | 10/19/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 10/24/18 | 10/26/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 707 | 10/24/18 | 10/26/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 46.82 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 10/24/18 | 10/26/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 10/24/18 | 10/26/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 10/24/18 | 10/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 10/24/18 | 10/26/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 10/24/18 | 10/26/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 10/24/18 | 10/26/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 10/24/18 | 10/26/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 10/24/18 | 10/26/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 10/24/18 | 10/26/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 10/24/18 | 10/26/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 10/24/18 | 10/26/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 125.31 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 10 | 10/31/18 | 11/02/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 10/31/18 | 11/02/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 19 | 10/31/18 | 11/02/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 10/31/18 | 11/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 10/31/18 | 11/02/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 1.49 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 34.81 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 3.9 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 10/31/18 | 11/02/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 10/31/18 | 11/02/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 59.98 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 10/31/18 | 11/02/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 10/31/18 | 11/02/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 10/31/18 | 11/02/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 10/31/18 | 11/02/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 115.67 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 188 | 11/07/18 | 11/09/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 49.42 |  | 0 | 0
998 | Payroll Taxes | PR | 196 | 11/07/18 | 11/09/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 66.86 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/07/18 | 11/09/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 207 | 11/07/18 | 11/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 11/07/18 | 11/09/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 11/07/18 | 11/09/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 11/07/18 | 11/09/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 11/07/18 | 11/09/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 11/07/18 | 11/09/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 11/07/18 | 11/09/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 11/14/18 | 11/16/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 36.41 |  | 0 | 0
998 | Payroll Taxes | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 445 | 11/14/18 | 11/16/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 446 | 11/14/18 | 11/16/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 62.25 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 11/14/18 | 11/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 459 | 11/14/18 | 11/16/18 | GO56 | Gonzalez Hernandez, Josue | 0 | 0 | 0 | 0 | 24.96 |  | 0 | 0
998 | Payroll Taxes | PR | 461 | 11/14/18 | 11/16/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 462 | 11/14/18 | 11/16/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 11/14/18 | 11/16/18 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 11/14/18 | 11/16/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 30.24 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 11/14/18 | 11/16/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 11/14/18 | 11/16/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 81.4 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 11/14/18 | 11/16/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 11/14/18 | 11/16/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 11/14/18 | 11/16/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 74.7 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -74.7 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | -128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 74.7 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 11/14/18 | 11/16/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 11/21/18 | 11/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.77 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 9.24 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 11/21/18 | 11/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 631 | 11/21/18 | 11/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 14.06 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 11/21/18 | 11/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 11/21/18 | 11/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 6.83 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 11/21/18 | 11/21/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 661 | 11/21/18 | 11/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 10.04 |  | 0 | 0
998 | Payroll Taxes | PR | 668 | 11/21/18 | 11/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 11/21/18 | 11/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 11/21/18 | 11/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 683 | 11/21/18 | 11/21/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 128.52 |  | 0 | 0
998 | Payroll Taxes | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 834 | 11/28/18 | 11/30/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 843 | 11/28/18 | 11/30/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 47.81 |  | 0 | 0
998 | Payroll Taxes | PR | 844 | 11/28/18 | 11/30/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 69.62 |  | 0 | 0
998 | Payroll Taxes | PR | 853 | 11/28/18 | 11/30/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 860 | 11/28/18 | 11/30/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 45.52 |  | 0 | 0
998 | Payroll Taxes | PR | 869 | 11/28/18 | 11/30/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 874 | 11/28/18 | 11/30/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 77.65 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 11/28/18 | 11/30/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 72.29 |  | 0 | 0
998 | Payroll Taxes | PR | 894 | 11/28/18 | 11/30/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 68.77 |  | 0 | 0
998 | Payroll Taxes | PR | 895 | 11/28/18 | 11/30/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 69.08 |  | 0 | 0
998 | Payroll Taxes | PR | 896 | 11/28/18 | 11/30/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 32.9 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 12/05/18 | 12/07/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 12/05/18 | 12/07/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 12/05/18 | 12/07/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 12/05/18 | 12/07/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 12/05/18 | 12/07/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 86 | 12/05/18 | 12/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 93 | 12/05/18 | 12/07/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 107 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 108 | 12/05/18 | 12/07/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 111.84 |  | 0 | 0
998 | Payroll Taxes | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 109 | 12/05/18 | 12/07/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 39.47 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 12/05/18 | 12/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 124 | 12/05/18 | 12/07/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 127 | 12/05/18 | 12/07/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | -6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 12/12/18 | 12/14/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 12/12/18 | 12/14/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 12/12/18 | 12/14/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 12/12/18 | 12/14/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 12/12/18 | 12/14/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 3.9 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 12/12/18 | 12/14/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 12/12/18 | 12/14/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 311 | 12/12/18 | 12/14/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 75.43 |  | 0 | 0
998 | Payroll Taxes | PR | 318 | 12/12/18 | 12/14/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 70.23 |  | 0 | 0
998 | Payroll Taxes | PR | 332 | 12/12/18 | 12/14/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 12/12/18 | 12/14/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 23.03 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 29.61 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 12/12/18 | 12/14/18 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 12/19/18 | 12/21/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 12/19/18 | 12/21/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 80.33 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 12/19/18 | 12/21/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 83.54 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 12/19/18 | 12/21/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 107.41 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 12/19/18 | 12/21/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 54.62 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 12/19/18 | 12/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 93.18 |  | 0 | 0
998 | Payroll Taxes | PR | 558 | 12/19/18 | 12/21/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 86.75 |  | 0 | 0
998 | Payroll Taxes | PR | 572 | 12/19/18 | 12/21/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 93.18 |  | 0 | 0
998 | Payroll Taxes | PR | 573 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 1.77 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 693 | 12/19/18 | 12/21/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | -1.77 |  | 0 | 0
998 | Payroll Taxes | PR | 692 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 70.69 |  | 0 | 0
998 | Payroll Taxes | PR | 703 | 12/26/18 | 12/28/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 711 | 12/26/18 | 12/28/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 712 | 12/26/18 | 12/28/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 713 | 12/26/18 | 12/28/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 12/26/18 | 12/28/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 728 | 12/26/18 | 12/28/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 742 | 12/26/18 | 12/28/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 12/26/18 | 12/28/18 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 763 | 12/26/18 | 12/28/18 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 764 | 12/26/18 | 12/28/18 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 12/26/18 | 12/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/02/19 | 01/04/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 01/02/19 | 01/04/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 49.73 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 01/02/19 | 01/04/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 51.71 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 01/02/19 | 01/04/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 01/02/19 | 01/04/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 33.81 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 01/02/19 | 01/04/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 57.68 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 01/02/19 | 01/04/19 | RE96 | Reyes Cruz, Denis A | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/02/19 | 01/04/19 | VE42 | Velasquez Cruz, Denis M | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 01/02/19 | 01/04/19 | VE43 | Velasquez Cruz, Osman N | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 01/02/19 | 01/04/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 01/09/19 | 01/11/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 01/09/19 | 01/11/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 01/09/19 | 01/11/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 01/09/19 | 01/11/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 01/09/19 | 01/11/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 01/09/19 | 01/11/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 01/16/19 | 01/18/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 01/16/19 | 01/18/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 01/16/19 | 01/18/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 101.9 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 01/16/19 | 01/18/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 01/16/19 | 01/18/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 01/16/19 | 01/18/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 01/16/19 | 01/18/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 719 | 01/23/19 | 01/25/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 729 | 01/23/19 | 01/25/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 730 | 01/23/19 | 01/25/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 738 | 01/23/19 | 01/25/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 01/23/19 | 01/25/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 01/23/19 | 01/25/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/30/19 | 02/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 01/30/19 | 02/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 01/30/19 | 02/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 31.82 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 01/30/19 | 02/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 01/30/19 | 02/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/30/19 | 02/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 01/30/19 | 02/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 01/30/19 | 02/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 01/30/19 | 02/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 163 | 02/06/19 | 02/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 172 | 02/06/19 | 02/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 49.73 |  | 0 | 0
998 | Payroll Taxes | PR | 173 | 02/06/19 | 02/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 51.71 |  | 0 | 0
998 | Payroll Taxes | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 181 | 02/06/19 | 02/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 2.6 |  | 0 | 0
998 | Payroll Taxes | PR | 187 | 02/06/19 | 02/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 18.21 |  | 0 | 0
998 | Payroll Taxes | PR | 191 | 02/06/19 | 02/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 201 | 02/06/19 | 02/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 39.93 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 02/13/19 | 02/15/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 02/13/19 | 02/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 02/13/19 | 02/15/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 02/13/19 | 02/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 349 | 02/13/19 | 02/15/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 37.49 |  | 0 | 0
998 | Payroll Taxes | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 9.37 |  | 0 | 0
998 | Payroll Taxes | PR | 363 | 02/13/19 | 02/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 31.06 |  | 0 | 0
998 | Payroll Taxes | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 376 | 02/13/19 | 02/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 68.85 |  | 0 | 0
998 | Payroll Taxes | PR | 583 | 02/20/19 | 02/22/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 585 | 02/20/19 | 02/22/19 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 592 | 02/20/19 | 02/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 593 | 02/20/19 | 02/22/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 111.38 |  | 0 | 0
998 | Payroll Taxes | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 143.21 |  | 0 | 0
998 | Payroll Taxes | PR | 601 | 02/20/19 | 02/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 65.03 |  | 0 | 0
998 | Payroll Taxes | PR | 607 | 02/20/19 | 02/22/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 611 | 02/20/19 | 02/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 136.82 |  | 0 | 0
998 | Payroll Taxes | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 73.21 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 02/20/19 | 02/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 106.49 |  | 0 | 0
998 | Payroll Taxes | PR | 635 | 02/20/19 | 02/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 56.46 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 02/27/19 | 03/01/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 63.11 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 02/27/19 | 03/01/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.84 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 02/27/19 | 03/01/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 02/27/19 | 03/01/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 104.65 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 02/27/19 | 03/01/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.23 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 02/27/19 | 03/01/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 62.12 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 02/27/19 | 03/01/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 100.37 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 2.07 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 03/06/19 | 03/08/19 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 25.82 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 03/06/19 | 03/08/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 03/06/19 | 03/08/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 03/06/19 | 03/08/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 115.67 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 03/06/19 | 03/08/19 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 46.82 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 26.24 |  | 0 | 0
998 | Payroll Taxes | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 9.98 |  | 0 | 0
998 | Payroll Taxes | PR | 288 | 03/06/19 | 03/08/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 102.05 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 46.82 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 03/13/19 | 03/15/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 82.08 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 03/13/19 | 03/15/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 65.03 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 03/20/19 | 03/22/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 729 | 03/20/19 | 03/22/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 75.43 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 03/20/19 | 03/22/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 13.31 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 2.45 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 931 | 03/27/19 | 03/29/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 941 | 03/27/19 | 03/29/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 39.93 |  | 0 | 0
998 | Payroll Taxes | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 961 | 03/27/19 | 03/29/19 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 13.31 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 83 | 04/03/19 | 04/05/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 93 | 04/03/19 | 04/05/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 94 | 04/03/19 | 04/05/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 04/03/19 | 04/05/19 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 16.98 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 04/03/19 | 04/05/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 04/10/19 | 04/12/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 354 | 04/10/19 | 04/12/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 04/17/19 | 04/19/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 04/17/19 | 04/19/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 755 | 04/24/19 | 04/26/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 04/24/19 | 04/26/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 116.28 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 8.32 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 05/01/19 | 05/03/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 05/01/19 | 05/03/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 108.63 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 9.47 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 05/01/19 | 05/03/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 175 | 05/08/19 | 05/10/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 05/08/19 | 05/10/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 3.79 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 05/08/19 | 05/10/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 407 | 05/15/19 | 05/17/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 424 | 05/15/19 | 05/17/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 05/15/19 | 05/17/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 05/15/19 | 05/17/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 459 | 05/15/19 | 05/17/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 05/15/19 | 05/17/19 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 619 | 05/22/19 | 05/24/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 05/22/19 | 05/24/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 05/22/19 | 05/24/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 93.41 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 05/22/19 | 05/24/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 47.43 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 893 | 05/29/19 | 05/31/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 910 | 05/29/19 | 05/31/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 922 | 05/29/19 | 05/31/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 77.65 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 06/05/19 | 06/07/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 11.09 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 06/05/19 | 06/07/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 06/12/19 | 06/14/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 82.08 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 06/12/19 | 06/14/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 06/19/19 | 06/21/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 869 | 06/26/19 | 06/28/19 | HO14 | Holmes, Anthony R | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 910 | 06/26/19 | 06/28/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 07/03/19 | 07/05/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 07/03/19 | 07/05/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 616 | 07/24/19 | 07/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
999 | Sales | AR | 586 | 02/20/18 | 02/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -34000 | 037028 | 0 | -1700
999 | Sales | AR | 586 | 02/20/18 | 02/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -6400 | 037028 | 0 | -320
999 | Sales | AR | 586 | 02/20/18 | 02/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -29250 | 037028 | 0 | -1462.5
999 | Sales | AR | 434 | 03/20/18 | 03/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -12000 | 037039 | 0 | -600
999 | Sales | AR | 434 | 03/20/18 | 03/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -19450 | 037039 | 0 | -972.5
999 | Sales | AR | 546 | 04/20/18 | 04/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -6500 | 037067 | 0 | -325
999 | Sales | AR | 513 | 05/18/18 | 05/18/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16800 | 037091 | 0 | -840
999 | Sales | AR | 666 | 06/20/18 | 06/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16100 | 037105 | 0 | -805
999 | Sales | AR | 516 | 07/20/18 | 07/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16100 | 037128 | 0 | -805
999 | Sales | AR | 535 | 07/20/18 | 07/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 16100 | 037147 | 0 | 805
999 | Sales | AR | 536 | 07/20/18 | 07/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16100 | 037148 | 0 | -805
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -20500 | 037157 | 0 | -1025
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -77210 | 037157 | 0 | -3860.5
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16290 | 037157 | 0 | -814.5
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -9485 | 037157 | 0 | -474.25
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1052 | 037157 | 0 | -52.6
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -923 | 037157 | 0 | -46.15
999 | Sales | AR | 586 | 08/20/18 | 08/20/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -4615 | 037157 | 0 | -230.75
999 | Sales | AR | 468 | 09/19/18 | 09/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16545 | 037184 | 0 | -827.25
999 | Sales | AR | 468 | 09/19/18 | 09/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -38010 | 037184 | 0 | -1900.5
999 | Sales | AR | 468 | 09/19/18 | 09/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -75880 | 037184 | 0 | -3794
999 | Sales | AR | 468 | 09/19/18 | 09/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -47425 | 037184 | 0 | -2371.25
999 | Sales | AR | 468 | 09/19/18 | 09/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -18290 | 037184 | 0 | -914.5
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -5120 | 037202 | 0 | -256
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -4725 | 037202 | 0 | -236.25
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -5100 | 037202 | 0 | -255
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -56910 | 037202 | 0 | -2845.5
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16525 | 037202 | 0 | -826.25
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -75880 | 037202 | 0 | -3794
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -15525 | 037202 | 0 | -776.25
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -100595 | 037202 | 0 | -5029.75
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -15525 | 037202 | 0 | -776.25
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -73160 | 037202 | 0 | -3658
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -15525 | 037202 | 0 | -776.25
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -13500 | 037202 | 0 | -675
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -14175 | 037202 | 0 | -708.75
999 | Sales | AR | 516 | 10/19/18 | 10/19/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -9022 | 037202 | 0 | -451.1
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -23950 | 037234 | 0 | -1197.5
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2580 | 037234 | 0 | -129
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -9800 | 037234 | 0 | -490
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2600 | 037234 | 0 | -130
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -9165 | 037234 | 0 | -458.25
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -91440 | 037234 | 0 | -4572
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -54000 | 037234 | 0 | -2700
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -6222 | 037234 | 0 | -311.1
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -3848 | 037234 | 0 | -192.4
999 | Sales | AR | 528 | 11/16/18 | 11/16/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2875 | 037234 | 0 | -143.75
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -11500 | 037254 | 0 | -575
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -7840 | 037254 | 0 | -392
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -5050 | 037254 | 0 | -252.5
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037254 | 0 | -1422.75
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037254 | 0 | -1422.75
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -54850 | 037254 | 0 | -2742.5
999 | Sales | AR | 351 | 12/14/18 | 12/14/18 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -18300 | 037254 | 0 | -915
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -60600 | 037274 | 0 | -3030
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8670 | 037274 | 0 | -433.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -10250 | 037274 | 0 | -512.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16545 | 037274 | 0 | -827.25
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -4000 | 037274 | 0 | -200
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1960 | 037274 | 0 | -98
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -54300 | 037274 | 0 | -2715
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2590 | 037274 | 0 | -129.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -10200 | 037274 | 0 | -510
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037274 | 0 | -1422.75
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037274 | 0 | -425.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037274 | 0 | -1422.75
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037274 | 0 | -425.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037274 | 0 | -425.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037274 | 0 | -425.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -7770 | 037274 | 0 | -388.5
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1920 | 037274 | 0 | -96
999 | Sales | AR | 556 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1350 | 037274 | 0 | -67.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 60600 | 037281 | 0 | 3030
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 8670 | 037281 | 0 | 433.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 10250 | 037281 | 0 | 512.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 16545 | 037281 | 0 | 827.25
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 4000 | 037281 | 0 | 200
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 1960 | 037281 | 0 | 98
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 54300 | 037281 | 0 | 2715
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 2590 | 037281 | 0 | 129.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 10200 | 037281 | 0 | 510
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 28455 | 037281 | 0 | 1422.75
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 8510 | 037281 | 0 | 425.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 28455 | 037281 | 0 | 1422.75
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 8510 | 037281 | 0 | 425.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 8510 | 037281 | 0 | 425.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 8510 | 037281 | 0 | 425.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 7770 | 037281 | 0 | 388.5
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 1920 | 037281 | 0 | 96
999 | Sales | AR | 790 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | 1350 | 037281 | 0 | 67.5
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -60600 | 037282 | 0 | -3030
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16545 | 037282 | 0 | -827.25
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -4000 | 037282 | 0 | -200
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1960 | 037282 | 0 | -98
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -54300 | 037282 | 0 | -2715
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037282 | 0 | -1422.75
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -28455 | 037282 | 0 | -1422.75
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037282 | 0 | -425.5
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037282 | 0 | -425.5
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037282 | 0 | -425.5
999 | Sales | AR | 791 | 01/18/19 | 01/18/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -7770 | 037282 | 0 | -388.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -21675 | 037286 | 0 | -1083.75
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -10250 | 037286 | 0 | -512.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2400 | 037286 | 0 | -120
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2590 | 037286 | 0 | -129.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -12750 | 037286 | 0 | -637.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -8510 | 037286 | 0 | -425.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -35000 | 037286 | 0 | -1750
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1920 | 037286 | 0 | -96
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1350 | 037286 | 0 | -67.5
999 | Sales | AR | 564 | 02/20/19 | 02/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -3230 | 037286 | 0 | -161.5
999 | Sales | AR | 678 | 03/20/19 | 03/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -7225 | 037299 | 0 | -361.25
999 | Sales | AR | 678 | 03/20/19 | 03/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -3820 | 037299 | 0 | -191
999 | Sales | AR | 678 | 03/20/19 | 03/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -15900 | 037299 | 0 | -795
999 | Sales | AR | 601 | 04/19/19 | 04/19/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -19100 | 037317 | 0 | -955
999 | Sales | AR | 601 | 04/19/19 | 04/19/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -15280 | 037317 | 0 | -764
999 | Sales | AR | 601 | 04/19/19 | 04/19/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -1800 | 037317 | 0 | -90
999 | Sales | AR | 505 | 05/20/19 | 05/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -16200 | 037338 | 0 | -810
999 | Sales | AR | 505 | 05/20/19 | 05/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -6840 | 037338 | 0 | -342
999 | Sales | AR | 505 | 05/20/19 | 05/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -20200 | 037338 | 0 | -1010
999 | Sales | AR | 505 | 05/20/19 | 05/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -19100 | 037338 | 0 | -955
999 | Sales | AR | 505 | 05/20/19 | 05/20/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -2830 | 037338 | 0 | -141.5
999 | Sales | AR | 606 | 06/19/19 | 06/19/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -760 | 037362 | 0 | -38
999 | Sales | AR | 606 | 06/19/19 | 06/19/19 | 2046MP | Marpac Construction, LLC $4218 Roosevelt |  |  |  |  | -480 | 037362 | 0 | -24

## Crew Roster
CREW ROSTER — 32 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Vazquez Popoca, Jose N | 5 | 0 | 0 | 80 | 0 | 16
APPRENTICE/HELPER | Hoeg, Xavier A | 1030.5 | 41.5 | 0 | 16995 | 1020 | 16.492
APPRENTICE/HELPER | Gardner, Andrew M | 47.5 | 0 | 0 | 807.5 | 0 | 17
APPRENTICE/HELPER | Lucas Tzintzun, Rafael | 571 | 55 | 0 | 9822 | 1417.5 | 17.2014
APPRENTICE/HELPER | Belcher, Jacob T | 1048.5 | 23 | 0 | 18381.5 | 603 | 17.5312
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 5 | 0 | 0 | 90 | 0 | 18
APPRENTICE/HELPER | Velasquez Cruz, Osman N | 857 | 33.5 | 0 | 15846 | 1011 | 18.4901
JOURNEYMAN | Roberts, Lake A | 55 | 0 | 0 | 1100 | 0 | 20
JOURNEYMAN | Cruz Gonzalez, Julio C | 26 | 0 | 0 | 572 | 0 | 22
JOURNEYMAN | Hubbard, Dustin R | 4 | 0 | 0 | 90 | 0 | 22.5
JOURNEYMAN | Taylor, Evan R | 84 | 7 | 0 | 1948 | 249 | 23.1905
JOURNEYMAN | Cruz Guzman, Joel A | 926 | 42.5 | 0 | 22546 | 1523.25 | 24.3477
JOURNEYMAN | Reyes Cruz, Denis A | 801 | 39.5 | 0 | 20427 | 1505.25 | 25.5019
JOURNEYMAN | Kinssies, Jr, John E | 304.5 | 0.5 | 0 | 7917 | 19.5 | 26
JOURNEYMAN | Cruz Reyes, Jose | 1249 | 71.5 | 0 | 32793 | 2682.75 | 26.2554
JOURNEYMAN | Velasquez Cruz, Denis M | 773 | 37.5 | 0 | 21821 | 1410 | 28.229
JOURNEYMAN | Montenegro, Carlos E | 815 | 26.5 | 0 | 23447 | 1129.5 | 28.7693
JOURNEYMAN | O'Bleness, Caleb N | 192 | 0 | 0 | 5568 | 0 | 29
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 153 | 0 | 0 | 4908 | 0 | 32.0784
JOURNEYMAN | McCabe, Thomas C | 51 | 0 | 0 | 1659 | 0 | 32.5294
JOURNEYMAN | Martinez Reyes, Juan C | 108 | 5.5 | 0 | 3564 | 272.25 | 33
JOURNEYMAN | Castro Hernandez, Jose A | 8 | 0 | 0 | 264 | 0 | 33
JOURNEYMAN | Garcia, Jordan X | 1211 | 37 | 0 | 42388 | 1942.5 | 35.0025
LEAD/SUPERVISOR | Waites, Thaddeus Z | 801 | 80 | 0 | 30355 | 3102 | 37.8964
LEAD/SUPERVISOR | Holmes, Anthony R | 438.5 | 24 | 0 | 17468 | 1422 | 39.8358
LEAD/SUPERVISOR | Anderson, Richard P | 24.5 | 0 | 0 | 1029 | 0 | 42
LEAD/SUPERVISOR | Hubbard, Robert W | 117.5 | 2 | 0 | 5439.5 | 147 | 46.2936
LEAD/SUPERVISOR | Barnhart, Joseph N | 182 | 13.5 | 0 | 8550 | 952.5 | 46.978
LEAD/SUPERVISOR | Gerard, Jeffrey S | 135 | 0 | 0 | 6808 | 0 | 50.4296
LEAD/SUPERVISOR | Donelson, Richard T | 112 | 0 | 0 | 6450 | 0 | 57.5893
OT-ONLY | Gonzalez Hernandez, Josue | 0 | 7.5 | 0 | 0 | 326.25 | — (no reg hours)
OT-ONLY | Hernandez Gonzalez, Osbaldo | 0 | 7.5 | 0 | 0 | 225 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2046
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 7 | 3564.5 | 153 | 66073.5 | 17.245
JOURNEYMAN | 16 | 6760.5 | 267.5 | 201746 | 27.5878
LEAD/SUPERVISOR | 7 | 1810.5 | 119.5 | 81723 | 45.8604
OT-ONLY | 2 | 0 | 15 | 551.25 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 17.18
p25 | 20.5
p50 | 27.24
p75 | 34.5
p90 | 46.36
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 27.1215 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 41.9324 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 56.2777 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2046
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 12,690.50 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $135.68 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $27.55 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 4.92x | Throughput ÷ unit cost — productivity signal
Units (residential) | 120 | 4218 Roosevelt Apartments scope doc: 113 Type B + 7 Type A ADA
Fixtures (estimate) | 734 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 27 | start_date → end_date from GDrive enrichment
Hours per Unit | 105.75 | total_labor_hours ÷ units
Hours per Fixture | 17.29 | total_labor_hours ÷ fixtures
Revenue per Unit | $14,349 | revenue ÷ units
Profit per Unit | $6,254 | net_profit ÷ units
Hours per Month | 470 | total_labor_hours ÷ duration_months
Revenue per Month | $63,773 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 22 VENDORS ($400,106 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Rosen Supply Kirkland | 187563.96 | 124 | 1512.6126 | 46.88% | 0 | 0
2 | Consolidated Supply Co. | 51360.82 | 32 | 1605.0256 | 12.84% | 0 | 0
3 | California Hydronics Corp | 41656 | 2 | 20828 | 10.41% | 0 | 0
4 | Franklin Engineering | 34285 | 8 | 4285.625 | 8.569% | 0 | 0
5 | Ferguson Enterprises, Inc. #3007 | 17819.83 | 9 | 1979.9811 | 4.454% | 0 | 0
6 | Best Bath Systems | 16066.59 | 2 | 8033.295 | 4.016% | 0 | 0
7 | Capital One Credit Card | 15191.45 | 29 | 523.8431 | 3.797% | 0 | 0
8 | Keller Supply Company | 14798.16 | 9 | 1644.24 | 3.699% | 0 | 0
9 | Quality Concrete Products, Inc. $32 | 5197 | 1 | 5197 | 1.299% | 0 | 0
10 | Mechanical Resource Services, Inc. | 4687.5 | 2 | 2343.75 | 1.172% | 0 | 0
11 | Rosen Supply Company, Inc. $4218 Rooseve | 3341.25 | 15 | 222.75 | 0.8351% | 0 | 0
12 | Scan2Core, Inc. | 2302.2 | 3 | 767.4 | 0.5754% | 0 | 0
13 | MAD Concrete Cutting & Coring, Inc. | 1690 | 1 | 1690 | 0.4224% | 0 | 0
14 | Chip Away Bathtub Repair, Inc. | 1515 | 1 | 1515 | 0.3786% | 0 | 0
15 | Bank of America CC | 693.63 | 3 | 231.21 | 0.1734% | 0 | 0
16 | Keller Supply Co. $4218 Roosevelt | 501.4 | 1 | 501.4 | 0.1253% | 0 | 0
17 | Hilti, Inc. | 315 | 1 | 315 | 0.07873% | 0 | 0
18 | Core & Main LP $HD Supply Waterworks | 245.06 | 1 | 245.06 | 0.06125% | 0 | 0
19 | Mechanical Sales, Inc. | 242.15 | 1 | 242.15 | 0.06052% | 0 | 0
20 | DRSi | 219.78 | 2 | 109.89 | 0.05493% | 0 | 0
21 | A.R. Brown Backflow Testing | 215 | 1 | 215 | 0.05374% | 0 | 0
22 | AllWest Underground, Inc. | 199.25 | 1 | 199.25 | 0.0498% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2046
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 |  | Domestic booster pump (Alt #1 triggered per COP #1) | 35000 | Executed | Y
2 |  | Submod #2 — insulate toilet tanks + misc scope additions | 22192 | Executed | Y
3 |  | Executed CO#03 — additional scope | 6222 | Executed | Y
4 |  | Executed CO#04 | 3848 | Executed | Y
5 |  | Submod #5 — executed CO#05 scope | 2875 | Executed | Y
6 |  | Submod #6 — added drains (complete) | 3230 | Executed | Y
Executed subtotal |  |  | 73367
Budget-transfer total (incl. extras) |  |  | 73367
JDR-implied CO (revenue − original contract) |  |  | 73367
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
COR #01 Temp Water Service | Temporary water service during roughin
COR #02 Garage Entrance Drain | Added drain in new room next to garage entrance
COR #03 Booster Pump | Add booster pump (became CO#01)
Best Bath Shower Stalls | Best Bath stall substitution log
Replace Showers w/ Straight Flanges | ROM estimate to remove and replace showers w/ straight flanges
Underslab Drainage/Basins/Pumps (draft) | Draft scope for underslab drainage/basins/pumps

## Project Team
PROJECT TEAM — 2046
Primary contacts extracted from 4218 Roosevelt Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Pat Nakamura | TBD | 206-329-4992
GC Project Manager | Calvert N (Cal) | calvertn@marpac.net | 206-329-4992
GC Superintendent | Brett (per Brett 4218 Roosevelt folder) | TBD | TBD
OWP Signatory | Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP)
Owner | G&K Investment LP
Inspecting Authority | City of Seattle (DCI)

## Document Pipeline
DOCUMENT PIPELINE — 2046
Quantitative document counts from the 4218 Roosevelt Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 6 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 52 | Change Orders/COR_s/
Budget transfer entries | 6 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 5 | ASI-RFI/
Submittals | 9 | Submittals/ (PDF count)
POs — placed | 13 | PO_s/1 Placed/
POs — scheduled | 41 | PO_s/2 Scheduled/
POs — completed | 83 | PO_s/3 Completed/
POs — total | 137 | PO_s/ (all three subfolders)
Vendor invoices | 195 | Invoices/
Lien releases | 10 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 4 | Permits/ (Seattle DCI plumbing + gas + backflow permits)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for 4218 Roosevelt)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2046
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 532143.25 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 400106.03 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 39161.25 | SUM(line_items where source=GL)
direct_cost | 971410.53 | PR + AP + GL
net_profit | 750456.47 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.30905 | PR / abs(revenue)
ap_pct_of_revenue | 0.23237 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.56416 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 12690.5 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 41.9324 | PR / labor hours
fully_loaded_wage | 56.2777 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 27.1215 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 32 | COUNT DISTINCT(name) source=PR
burden_total | 182049.5 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $17.18 ¦ $20.50 ¦ $27.24 ¦ $34.50 ¦ $46.36 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 378784.06 | SUM(actual) codes 2xx
material_budget_total | 493642 | SUM(current_budget) codes 2xx
material_codes_tracked | 8 | COUNT material codes
material_codes_over_budget | 2 | COUNT where plus_minus > 0
material_codes_under_budget | 6 | COUNT where plus_minus ≤ 0
largest_material_overrun | 242 Mech Room Material: $24,088 vs $15,250 budget (+$8,838) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $199,016 vs $255,231 budget ($-56,215) | Material code with largest −plus_minus
material_vendor_count | 22 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Rosen Supply Kirkland: $187,564 (47% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 7 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 19 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 141 Water Main/Insulation Lab: $54,626 vs $34,835 budget (+$19,791) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $199,016 vs $255,231 budget ($-56,215) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 971410.53 | SUM(actual) expense codes
total_budget | 1228349.71 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7908 | JTD / budget
total_over_under_budget | 256939.18 | budget − JTD
labor_unit_cost_per_hr | 27.5496 | Labor JTD / labor hours
revenue_per_labor_hour | 135.6816 | abs(revenue) / labor hours
material_price_variance | 114857.94 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2046
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 43.6% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | YELLOW | 7/26 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $114,858 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $135.68 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $86,093 | Monitor for collection
Top vendor concentration | GREEN | 46.9% (Rosen Supply Kirkland) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2046
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $1,721,867, net profit $750,456 at 43.6% margin.
02 | Parsed 2,770 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 32 distinct PR-booked workers over 12,690 labor hours ($41.93/hr PR-src, $56.28/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 141 Water Main/Insulation Lab: $54,626 vs $34,835 budget (+$19,791).
05 | Largest phase savings: 230 Finish Material: $199,016 vs $255,231 budget ($-56,215).
06 | Material spend $378,784 vs budget $493,642 ($114,858 favorable).
07 | Top AP vendor: Rosen Supply Kirkland: $187,564 (47% of AP); 22 total AP vendors.
08 | Retainage outstanding: $86,093.
09 | 7 of 26 expense phases over budget ($256,939 net vs budget).
10 | Revenue per labor hour $135.68, labor unit cost $27.55 (ratio 4.92x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 27/27 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 3541 | 3541 | 0 | ✓
101 | Takeoff & Purchase Labor | 9717 | 9717 | 0 | ✓
110 | Underground Labor | 2915 | 2915 | 0 | ✓
111 | Garage Labor | 21002 | 21002 | 0 | ✓
112 | Canout Labor | 6188.5 | 6188.5 | 0 | ✓
120 | Roughin Labor | 199226.75 | 199226.75 | 0 | ✓
130 | Finish Labor | 36570 | 36570 | 0 | ✓
140 | Gas Labor | 5168.5 | 5168.5 | 0 | ✓
141 | Water Main/Insulation Lab | 54625.61 | 54625.61 | 0 | ✓
142 | Mech Room Labor | 9940.82 | 9940.82 | 0 | ✓
143 | Condensation Drains Labor | 722.5 | 722.5 | 0 | ✓
210 | Underground Material | 3400.09 | 3400.09 | 0 | ✓
211 | Garage Material | 10464.66 | 10464.66 | 0 | ✓
212 | Canout Material | 7542.97 | 7542.97 | 0 | ✓
220 | Roughin Material | 91683.71 | 91683.71 | 0 | ✓
230 | Finish Material | 199016.45 | 199016.45 | 0 | ✓
240 | Gas Material | 2670.82 | 2670.82 | 0 | ✓
241 | Water Main/Insulation Mat | 39917.5 | 39917.5 | 0 | ✓
242 | Mech Room Material | 24087.86 | 24087.86 | 0 | ✓
600 | Subcontractor | 10409.7 | 10409.7 | 0 | ✓
601 | Engineering/Plans | 34504.78 | 34504.78 | 0 | ✓
602 | Rental Equipment | 199.25 | 199.25 | 0 | ✓
603 | Permits & Licenses | 7501 | 7501 | 0 | ✓
607 | Other Expenses | 8344.56 | 8344.56 | 0 | ✓
995 | Payroll Burden | 155266.79 | 155266.79 | 0 | ✓
998 | Payroll Taxes | 26782.71 | 26782.71 | 0 | ✓
999 | Sales | -1721867 | -1721867 | 0 | ✓
RESULT: 27/27 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2046
Worked example of the Reconciliation Protocol running against Job 2046 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 141 Water Main/Insulation Lab: $54,626 vs $34,835 budget (+$19,791) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $1,228,350; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $41.93/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $532,143.25 ÷ 12,690.50 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$17.18 ¦ p25=$20.50 ¦ p50=$27.24 ¦ p75=$34.50 ¦ p90=$46.36 (32 workers) | straight_time_rate $27.12 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $27.55/hr ¦ revenue $135.68/hr ¦ ratio 4.92x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2046 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 27/27 codes tie to PDF to the cent | PR $532,143.25 + AP $400,106.03 + GL $39,161.25 = $971,410.53 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2046
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2046 | JDR cover page
job_name | Job Name | Marpac 4218 Roosevelt | JDR cover page
general_contractor | General Contractor | Marpac | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 2770 | Length of line_items[]
cost_code_count | Cost Code Count | 27 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -1721867 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 1721867 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 971410.53 | Sage job_totals_expenses
job_totals_net | Net | -750456.47 | Sage job_totals_net
job_totals_retainage | Retainage | -86093.35 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 532143.25 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 400106.03 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 39161.25 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -1721867 | SUM(line_items source=AR)
direct_cost | Direct Cost | 971410.53 | PR + AP + GL
net_profit | Net Profit | 750456.47 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 43.58% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 349617.68 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 378784.06 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 60959.29 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 182049.5 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 12690.5 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 32 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 27.1215 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 41.9324 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 56.2777 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 182049.5 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 17.18 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 20.5 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 27.24 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 34.5 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 46.36 | Percentile across workers
material_spend_total | Material Spend Total | 378784.06 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 493642 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 8 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 2 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 6 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 22 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 114857.94 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 242 Mech Room Material: $24,088 vs $15,250 budget (+$8,838)
largest_material_savings | Largest Material Savings | 230 Finish Material: $199,016 vs $255,231 budget ($-56,215)
top_vendor_spend | Top Vendor Spend | Rosen Supply Kirkland: $187,564 (47% of AP)
phases_over_budget | Phases Over Budget | 7 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 19 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 141 Water Main/Insulation Lab: $54,626 vs $34,835 budget (+$19,791)
largest_savings | Largest Savings | 230 Finish Material: $199,016 vs $255,231 budget ($-56,215)
total_jtd_cost | Total JTD Cost | 971410.53 | SUM(actual) expense codes
total_budget | Total Current Budget | 1228349.71 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 79.08% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 256939.18 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 27.5496 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 135.6816 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array