## Overview
Job #2046 · Marpac 4218 Roosevelt Apartments (Marpac Job# 17-10)
Cortex JCR v2 • Marpac (customer 2046SH) • 4218 Roosevelt Way NE, Seattle, WA 98105 • Owner: G&K Investment LP
PROJECT OVERVIEW
Project Job # | 2046 |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | Marpac 4218 Roosevelt |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | 4218 Roosevelt Apartments — 120-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Marpac |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2046SH |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | G&K Investment LP |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Pat Nakamura / Calvert N (Cal) |  | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
GC Superintendent | Brett (per Brett 4218 Roosevelt folder) |  | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
GC PE | N/A |  | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
OWP Signatory | Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314) |  | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
Jobsite Location | 4218 Roosevelt Way NE, Seattle, WA 98105 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 734 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) |  | 4218 Roosevelt Apartments project info.pdf
Contract Type | Lump Sum |  | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
Unit Count | 120 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-09 start → 2019-12 (27 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
1721867 |  | 750456.47 | 971410.53 | 12690.5
Original $1,648,500.00 + ($73,367.00) COs (4.45%) |  | 43.6% margin | 56.4% of revenue | 32 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
120-unit mixed-use (102 Type B + 6 Type A/ADA) at 4218 Roosevelt Way NE, Seattle, WA 98105, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: Marpac (2046SH); Owner: G&K Investment LP.
Insurance: Not Wrap (retail-adjacent residential).
Project team: Pat Nakamura / Calvert N (Cal) (GC PM) · Brett (per Brett 4218 Roosevelt folder) (GC Sup) · TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) (Architect) · Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314) (OWP signatory).
SOURCES
Canonical financial source: 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $1,721,867.00 / Expenses $971,410.53 / Net $750,456.47 / Retainage $86,093.35
Source breakdown (derived): PR $532,143.25 · AP $400,106.03 · GL $39,161.25
Contract: Lump Sum $1,648,500.00 → $1,721,867.00
Change Orders (executed): $73,367.00 net across 6 COs (CO log in enriched meta)
Project Team: Pat Nakamura / Calvert N (Cal) (PM) · Brett (per Brett 4218 Roosevelt folder) (Sup) · TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) · G&K Investment LP
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Marpac
GC PM | Extracted | Pat Nakamura / Calvert N (Cal)
GC Superintendent | Extracted | Brett (per Brett 4218 Roosevelt folder)
GC PE | N/A | N/A
Owner | Extracted | G&K Investment LP
Architect | Extracted | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP)
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314)

## Budget vs Actual
Budget vs Actual
All 27 cost codes from JDR. Contract $1,648,500 → $1,721,867.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 13750 | 14050 | 3541 | -10509 | 25.2% | 69 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 19250 | 19700 | 9717 | -9983 | 49.32% | 172 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 15775 | 16585 | 2915 | -13670 | 17.58% | 82.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 28850 | 31010 | 21002 | -10008 | 67.73% | 749 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 11285 | 11585 | 6188.5 | -5396.5 | 53.42% | 177.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 244210 | 248785 | 199226.75 | -49558.25 | 80.08% | 7414.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 35160 | 35880 | 36570 | 690 | 101.9% | 1052.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 11000 | 11000 | 5168.5 | -5831.5 | 46.99% | 136.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 32855 | 34835 | 54625.61 | 19790.61 | 156.8% | 2333 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 14740 | 15760 | 9940.82 | -5819.18 | 63.08% | 272.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 722.5 | 722.5 |  | 20.5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 10575 | 10900 | 3400.09 | -7499.91 | 31.19% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 26950 | 28736 | 10464.66 | -18271.34 | 36.42% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 9150 | 9450 | 7542.97 | -1907.03 | 79.82% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 129520 | 130335 | 91683.71 | -38651.29 | 70.34% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 226119 | 255231 | 199016.45 | -56214.55 | 77.98% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 4000 | 4000 | 2670.82 | -1329.18 | 66.77% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 39165 | 39740 | 39917.5 | 177.5 | 100.4% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 13750 | 15250 | 24087.86 | 8837.86 | 158% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 2500 | 2500 | 10409.7 | 7909.7 | 416.4% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 42000 | 42000 | 34504.78 | -7495.22 | 82.15% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 4500 | 4500 | 199.25 | -4300.75 | 4.428% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 6682 | 6682 | 7501 | 819 | 112.3% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 11500 | 11500 | 8344.56 | -3155.44 | 72.56% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 189319.06 | 194737.66 | 155266.79 | -39470.87 | 79.73% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 32655.94 | 33598.05 | 26782.71 | -6815.34 | 79.72% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -1648500 | -1721867 | -1721867 | 0 | 100% |  | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -473239 | -493517.29 | -750456.47 | -256939.18 |  | 12479.5

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,143 | 349617.68 | 35.99% | 20.3% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242 | 378784.06 | 38.99% | 22% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 60959.29 | 6.275% | 3.54% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 155266.79 | 15.98% | 9.017% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 26782.71 | 2.757% | 1.555% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 971410.53 | 100% | 56.42%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1380RS | Rosen Supply Kirkland | 187563.96 | 124 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 51360.82 | 32 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 41656 | 2 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 34285 | 8 | Engineering (601) | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 17819.83 | 9 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 16066.59 | 2 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 15191.45 | 29 | Credit Card (mixed) | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 14798.16 | 9 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 5197 | 1 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 4687.5 | 2 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 3341.25 | 15 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 2302.2 | 3 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4320MC | MAD Concrete Cutting & Coring, Inc. | 1690 | 1 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1504CA | Chip Away Bathtub Repair, Inc. | 1515 | 1 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 693.63 | 3 | Credit Card (mixed) | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2046KS | Keller Supply Co. $4218 Roosevelt | 501.4 | 1 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3820HI | Hilti, Inc. | 315 | 1 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 245.06 | 1 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 242.15 | 1 | Plumbing / Supplies | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 219.78 | 2 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 215 | 1 | Testing subcontractor | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 199.25 | 1 | Uncategorized | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 400106.03 | 249

## Crew & Labor
Crew & Labor — Worker Roster
All 32 unique payroll workers. OWP signatory: Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CR87 | Cruz Reyes, Jose | 1320.5 | 35475.75 | 26.8654 | 34 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 1248 | 44330.5 | 35.5212 | 34 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 1072 | 18015 | 16.805 | 30 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 1071.5 | 18984.5 | 17.7177 | 28 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 968.5 | 24069.25 | 24.8521 | 27 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE43 | Velasquez Cruz, Osman N | 890.5 | 16857 | 18.9298 | 22 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WA35 | Waites, Thaddeus Z | 881 | 33457 | 37.9762 | 27 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 841.5 | 24576.5 | 29.2056 | 23 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE96 | Reyes Cruz, Denis A | 840.5 | 21932.25 | 26.0943 | 22 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VE42 | Velasquez Cruz, Denis M | 810.5 | 23231 | 28.6626 | 22 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 626 | 11239.5 | 17.9545 | 15 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO14 | Holmes, Anthony R | 462.5 | 18890 | 40.8432 | 13 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 305 | 7936.5 | 26.0213 | 13 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 195.5 | 9502.5 | 48.6061 | 47 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
OB46 | O'Bleness, Caleb N | 192 | 5568 | 29 | 6 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 153 | 4908 | 32.0784 | 9 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 135 | 6808 | 50.4296 | 60 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 119.5 | 5586.5 | 46.749 | 17 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 113.5 | 3836.25 | 33.7996 | 6 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 112 | 6450 | 57.5893 | 61 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 91 | 2197 | 24.1429 | 7 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 55 | 1100 | 20 | 2 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 51 | 1659 | 32.5294 | 5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA72 | Gardner, Andrew M | 47.5 | 807.5 | 17 | 4 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 26 | 572 | 22 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AN14 | Anderson, Richard P | 24.5 | 1029 | 42 | 4 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA77 | Castro Hernandez, Jose A | 8 | 264 | 33 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO56 | Gonzalez Hernandez, Josue | 7.5 | 326.25 | 43.5 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 7.5 | 225 | 30 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 5 | 80 | 16 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 5 | 90 | 18 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 4 | 90 | 22.5 | 2 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 12690.5 | 350093.75

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 32 | Unique payroll IDs | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 12690.5 | Sum of labor codes | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 350093.75 | Sum of labor codes | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 27.5871 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 10.41% | CR87 Cruz Reyes, Jose (1320 hrs) | Derived
Top 5 Workers Hours Share | 44.76% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 57.5893 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 16 | Single-worker blended | Derived
Avg Hours per Worker | 396.5781 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 17.0625 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 120 units (734 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 135.6816 | USD/hr
Profit per Labor Hour | 59.1353 | USD/hr
Labor Cost per Hour (blended) | 27.5496 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 56.2777 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 7414.5 | hrs
Finish Hours (code 130) | 1052.5 | hrs
Rough-in % of Total Hours | 59.41% | %
Gross Margin | 43.58% | %
Labor % of Revenue | 20.3% | %
Material % of Revenue | 22% | %
Direct Cost Ratio | 56.42% | % | All exp/Rev
Revenue per Unit (120) | 14348.8917 | USD | 120 units
Labor Hours per Unit | 105.7542 | hrs
Labor Cost per Unit | 2913.4807 | USD
Material Cost per Unit | 3156.5338 | USD
Direct Cost per Unit | 8095.0877 | USD
Rough-in Hours per Unit | 61.7875 | hrs
Revenue per Fixture | 2345.8678 | USD | 734 fixtures
Hours per Fixture | 17.2895 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-09-11 | Marpac | Lump Sum Subcontract | Closed | 4218 Roosevelt Apartments plumbing (120 units, 7 stories) — per Div 22 | 1648500 | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
CO-NET | — | Marpac | Change Orders (executed, 6 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 73367 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 1721867

## Billing & SOV
Billing & Schedule of Values
195 invoices to Marpac. Retainage $86,093.35.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
556 | 01/18/19 | -271105 | -13555.25 | 18 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
790 | 01/18/19 | 271105 | 13555.25 | 18 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
791 | 01/18/19 | -227615 | -11380.75 | 11 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
586 | 02/20/18 | -199725 | -9986.25 | 10 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
564 | 02/20/19 | -99675 | -4983.75 | 10 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
434 | 03/20/18 | -31450 | -1572.5 | 2 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
678 | 03/20/19 | -26945 | -1347.25 | 3 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | 04/19/19 | -36180 | -1809 | 3 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
546 | 04/20/18 | -6500 | -325 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
513 | 05/18/18 | -16800 | -840 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
505 | 05/20/19 | -65170 | -3258.5 | 5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
606 | 06/19/19 | -1240 | -62 | 2 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
666 | 06/20/18 | -16100 | -805 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
516 | 07/20/18 | -437387 | -21869.35 | 15 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
535 | 07/20/18 | 16100 | 805 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
536 | 07/20/18 | -16100 | -805 | 1 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
468 | 09/19/18 | -196150 | -9807.5 | 5 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
528 | 11/16/18 | -206480 | -10324 | 10 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
351 | 12/14/18 | -154450 | -7722.5 | 7 | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -1721867 | -86093.35

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $750,456.47 on $1,721,867.00 revenue = 43.6% gross margin. | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $1,648,500.00 → final $1,721,867.00 = $+73,367.00 net (4.45%) across 6 executed COs. | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $349,617.68 (20.3% of rev) across 12,690 hrs and 32 workers. Blended wage $27.55/hr. | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$332,685.61 (83% of AP). Top vendor: Rosen Supply Kirkland ($187,563.96). | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $86,093.35 — outstanding as of report date. | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 7,414 hrs (59% of labor hours). | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $199,226.75 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Cruz Reyes, Jose = 1,320 hrs (10% of total). | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | 4218 Roosevelt Apartments — 120-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 4218 Roosevelt Way NE, Seattle, WA 98105. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2046 | Profile | OWP job ID | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Marpac 4218 Roosevelt Apartments (Marpac Job# 17-10) | Profile |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Marpac | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | G&K Investment LP | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) | Profile |  | Verified | 4218 Roosevelt Apartments project info.pdf
Location | location | 4218 Roosevelt Way NE, Seattle, WA 98105 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Mid-rise mixed-use apartments (residential + ground-level retail + garage podium): 120 residential units (113 Type B + 7 Type A ADA) plus L1 exercise/amenity + L1 retail + L7 roof deck. Post-tension deck construction with Hydroflame/ProSet sleeves. | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Pat Nakamura / Calvert N (Cal) | Profile |  | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
GC Sup | gc_sup | Brett (per Brett 4218 Roosevelt folder) | Profile |  | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314) | Profile |  | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-09-11 | Profile |  | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
Work Start | start_date | 2017-09 | Profile |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-12 | Profile |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 27 | Profile |  | Verified | Derived
Unit Count | unit_count | 120 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 734 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 1648500 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 1721867 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 73367 | Financial | 6 executed | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 4.451% | Financial |  | Verified | Derived
Revenue | revenue | 1721867 | Financial | AR total | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 971410.53 | Financial | JDR Expenses | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 750456.47 | Financial | Rev - Exp | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 43.58% | Financial |  | Verified | Derived
Retainage | retainage | 86093.35 | Financial | JDR AR retainage | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 349617.68 | Labor | Codes 100-151 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 378784.06 | Material | Codes 210-245 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 60959.29 | Financial | Codes 600-607 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 155266.79 | Labor | Code 995 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 26782.71 | Labor | Code 998 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 12690.5 | Labor | Sum labor codes | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 32 | Labor | Unique PR IDs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 27.5496 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 56.2777 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 7414.5 | Labor | Code 120 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 1052.5 | Labor | Code 130 | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 135.6816 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 59.1353 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 14348.8917 | Productivity | 120 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 8095.0877 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 105.7542 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 2345.8678 | Productivity | 734 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 20.3% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 22% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 22 | Material |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 19 | Billing |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 10.41% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 44.76% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 27 | Structure |  | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 6 | Documents |  | Verified | CO log
COR Count | cor_count | 52 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 5 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 9 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 137 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1380RS | Rosen Supply Kirkland | 187563.96 | 124 | 46.88% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1130CS | Consolidated Supply Co. | 51360.82 | 32 | 12.84% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 5560CH | California Hydronics Corp | 41656 | 2 | 10.41% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1625FE | Franklin Engineering | 34285 | 8 | 8.569% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1175FE | Ferguson Enterprises, Inc. #3007 | 17819.83 | 9 | 4.454% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 7230BB | Best Bath Systems | 16066.59 | 2 | 4.016% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 1234CO | Capital One Credit Card | 15191.45 | 29 | 3.797% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 1231KS | Keller Supply Company | 14798.16 | 9 | 3.699% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1609QC | Quality Concrete Products, Inc. $32 | 5197 | 1 | 1.299% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 3129MR | Mechanical Resource Services, Inc. | 4687.5 | 2 | 1.172% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 2046RS | Rosen Supply Company, Inc. $4218 Rooseve | 3341.25 | 15 | 0.8351% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 3181SC | Scan2Core, Inc. | 2302.2 | 3 | 0.5754% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 4320MC | MAD Concrete Cutting & Coring, Inc. | 1690 | 1 | 0.4224% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1504CA | Chip Away Bathtub Repair, Inc. | 1515 | 1 | 0.3786% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1234BA | Bank of America CC | 693.63 | 3 | 0.1734% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 2046KS | Keller Supply Co. $4218 Roosevelt | 501.4 | 1 | 0.1253% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 3820HI | Hilti, Inc. | 315 | 1 | 0.07873% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 5621HD | Core & Main LP $HD Supply Waterworks | 245.06 | 1 | 0.06125% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 3612MS | Mechanical Sales, Inc. | 242.15 | 1 | 0.06052% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1288DR | DRSi | 219.78 | 2 | 0.05493% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 1641AR | A.R. Brown Backflow Testing | 215 | 1 | 0.05374% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | 1799AW | AllWest Underground, Inc. | 199.25 | 1 | 0.0498% | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 400106.03 | 249

## Change Log
Change Log — Master Register
Contract, 6 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-09-11 | Prime subcontract — Lump Sum $1,648,500.00 | Marpac | 1648500 | Executed | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $86,093.35 (outstanding) | GC | 0 | Outstanding | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 73367 | JDR-implied net CO impact | $1,648,500 → $1,721,867 (6 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -89572.32 | Labor variance vs revised budget | 32 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -114857.94 | Material procurement variance | 22 vendors
Overhead | 600,601,602,603,604,607 | -6222.71 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -46286.21 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -183572.18
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 6 | 73367 | Aggregate executed COs
Sub (OWP) labor performance | 11 | -89572.32 | Hours + rate vs budget
Sub (OWP) material procurement | 8 | -114857.94 | 22 vendors
OWP burden accrual | 2 | -46286.21 | Payroll burden + tax
OWP overhead | 5 | -6222.71 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 4.45% | ±10% | HEALTHY | +4.45% net (6 COs)
Labor % of Revenue | 20.3% | <30% | HEALTHY | 20.3%
GL Overhead % of Revenue | 2.274% | <5% | HEALTHY | 2.3%
Vendor Concentration (Top 5) | 83.15% | <95% | HEALTHY | Top 5 = 83% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 43.58% | >30% | HEALTHY | 43.6%
Labor Hrs Total | 12690.5 | varies | INFO | 12,690 hrs, 32 workers
Worker Concentration (top 1) | 10.41% | <25% | HEALTHY | 10.4% (Cruz Reyes, Jose)
Rough-in Labor Share | 59.41% | 40-65% | HEALTHY | 59%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $86,093.35
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 43.58% | Actual | Job closed | 43.6%
Retainage collection | $86,093.35 | Outstanding | Legacy | Outstanding
Unit-level economics | $14,349/unit rev, $6,254/unit profit | Verified | 120 units | Mid-rise mixed-use apartments (residential + ground-level retail + garage podium): 120 residential units (113 Type B + 7 Type A ADA) plus L1 exercise/amenity + L1 retail + L7 roof deck. Post-tension deck construction with Hydroflame/ProSet sleeves.

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2046 | id | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Marpac 4218 Roosevelt Apartments (Marpac Job# 17-10) | text | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Marpac | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | G&K Investment LP | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans (Franklin 4218 Roosevelt folder references Franklin Engineering MEP) | text | Benchmark KPIs | Verified | 4218 Roosevelt Apartments project info.pdf
6 | location | Location | 4218 Roosevelt Way NE, Seattle, WA 98105 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Mid-rise mixed-use apartments (residential + ground-level retail + garage podium): 120 residential units (113 Type B + 7 Type A ADA) plus L1 exercise/amenity + L1 retail + L7 roof deck. Post-tension deck construction with Hydroflame/ProSet sleeves. | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Pat Nakamura / Calvert N (Cal) | text | Benchmark KPIs | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Brett (per Brett 4218 Roosevelt folder) | text | Benchmark KPIs | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Richard Donelson (OWP per Construction Transmittal 9/11/2017; 425.968.8314) | text | Benchmark KPIs | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-09-11 | date | Benchmark KPIs | Verified | 2046-Shelter Holdings subcontract 17-10 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-09 | date | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-12 | date | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 27 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 120 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 734 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 1648500 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 1721867 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 73367 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 4.451% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 1721867 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 971410.53 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 750456.47 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 43.58% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 86093.35 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 349617.68 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 378784.06 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 60959.29 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 155266.79 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 26782.71 | USD | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 12690.5 | hours | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 32 | count | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 27.5496 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 56.2777 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 7414.5 | hours | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 1052.5 | hours | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 135.6816 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 59.1353 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 14348.8917 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 8095.0877 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 105.7542 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 2345.8678 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 20.3% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 22% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 22 | count | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 19 | count | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 10.41% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 44.76% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 27 | count | Benchmark KPIs | Verified | 2046 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 6 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 52 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 5 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 9 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 137 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 1721867 | 1721867 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 971410.53 | 971410.53 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 750456.47 | 750456.47 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 1721867 | 1721867 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 12690.5 | 12690.5 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 73367 | 73367 | 0 | TIES | 11↔Derived
7 | Worker count | 32 | 32 | 0 | TIES | 5↔1
8 | Cost code count | 27 | 27 | 0 | TIES | 2↔16