## Overview
OWP JOB 2047 — GRE GREENLAKE
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$553,189 |  | $366,276 |  | $186,913 |  | 5,993
Billed to date (Sage AR) |  | 66.2% of revenue |  | 33.8% margin |  | 33 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 145329 | 150690.75 | -5361.75 | 103.7% | 41.14%
Material | 172896 | 133195.02 | 39700.98 | 77.04% | 36.36%
Overhead | 8468 | 4030.45 | 4437.55 | 47.6% | 1.1%
Burden | 76787.17 | 78359.56 | -1572.39 | 102% | 21.39%
TOTAL (expense codes) | 403480.17 | 366275.78 | 37204.39 | 90.78% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 229050.31 | 62.53% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 117192.21 | 32% | Material + subcontractor spend
GL (General Ledger) | 20033.26 | 5.469% | Misc adjustments + deposits
AR (Billings, credit) | -553189 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2047
Project identity + metadata enriched from GDrive close-out package (GRE Greenlake Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2047 | JDR cover page
job_name | GRE Greenlake | GRE Greenlake Apartments project info PDF
job_name_long | GRE Greenlake Apartments (8228 Green Lake Dr N) — PRIOR SUB TAKEOVER | GRE Greenlake Apartments project info PDF
general_contractor | GRE | Signed subcontract 7926 — Shelter Holdings / GRE Green Lake LLC
owner | GRE Green Lake LLC | Signed subcontract §A.a — GRE Green Lake LLC
architect | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) | Contract counterparty: GRE Green Lake LLC
location | 8228 Green Lake Dr N, Seattle, WA 98103 | Signed subcontract + permit records
project_type | Rescue/takeover project: OWP replaced prior plumbing subcontractor (Peltram) mid-construction. 72 residential units (61 Type B + 11 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves. CCIP (Contractor-Controlled Insurance Program) project. | Scope doc + submittal TOC (7-story mixed-use + 2 parking levels)
unit_count | 72 | Plan drawings: 7-story, 72 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 751 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from GRE Greenlake Job Ticket 03/26/2018 (final revision): 61 Gerber SE 21-112 std toilets + 11 Gerber SE 21-118 ADA toilets + 72 Lenova UB-903W lavs + 14 shower installs + 58 tub installs + 12 Best Bath P3838B5T pans + 6 Aquatic 6032STT (stolen from Issaquah Gateway) + 2 Sterling tubs (units 221, 222) + 72 Niagara/Delta showerheads + 64 Dayton kitchen sinks + 6 Elkay ADA kit sinks + 70 ISE disposals + 70 DW roughin + 70 icemaker roughin + 70 washer roughin + 70 AO Smith 40-gal WHs = 728 resident. L1 amenity + rooftop = 11. Building systems (hose bibs, trash chute backflow, backflow water room, garage drain pumps) ≈ 12. Total ≈ 751. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 5 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-11 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2018-09 | Final pay app 12/13/2019
duration_months | 11 | start → end
contract_signed | 2017-10-25 | Signed subcontract — Mike Donelson 9/11/17
permit_jurisdiction | City of Seattle (DCI) | City of Seattle (DCI) permit (Seattle DCI plumbing + gas + backflow)
permits_issued | Plumbing permit; Backflow permit; Plan review 1/30/2018 | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2047 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2047
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 475800 | Code 999 original (negated)
current_contract_budget | 553189 | Code 999 current (negated)
revenue_ar_billed | 553189 | Sum of AR line items (abs)
retainage_outstanding | 27659.45 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 351653.21 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 403480.17 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 51826.96 | Revised − Original across expense codes
direct_cost | 366275.78 | PR + AP + GL totals
net_profit | 186913.22 | abs(revenue) − direct_cost
gross_margin_pct | 33.79% | net / revenue

## Cost Categories
COST CATEGORIES — 2047
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 8 | 127757 | 145329 | 150690.75 | -5361.75 | 103.7% | PENDING (needs unit_count)
Material | 5 | 149685 | 172896 | 133195.02 | 39700.98 | 77.04% | PENDING (needs unit_count)
Overhead | 5 | 6500 | 8468 | 4030.45 | 4437.55 | 47.6% | PENDING (needs unit_count)
Burden | 2 | 67711.21 | 76787.17 | 78359.56 | -1572.39 | 102% | PENDING (needs unit_count)
Revenue | 1 | -475800 | -553189 | -553189 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 4200 | 4250 | -1848 | 2402 | 0 | 0 | 49.5 | 0 | 0 | 56.52% | UNDER
101 | Takeoff & Purchase Labor | Labor | 8750 | 9000 | -3625 | 5375 | 0 | 0 | 102 | 0 | 0 | 59.72% | UNDER
111 | Garage Labor | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
120 | Roughin Labor | Labor | 88827 | 105859 | 13515 | 119374 | 0 | 0 | 4590.5 | 171.5 | 0 | 112.8% | OVER
130 | Finish Labor | Labor | 25980 | 26220 | -2680.25 | 23539.75 | 0 | 0 | 876 | 47.5 | 0 | 89.78% | UNDER
141 | Water Main/Insulation Lab | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
142 | Mech Room Labor | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
143 | Condensation Drains Labor | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
211 | Garage Material | Material | 0 | 0 | 10.6 | 10.6 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
212 | Canout Material | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
220 | Roughin Material | Material | 59765 | 67358 | -11354.01 | 56003.99 | 0 | 0 | 0 | 0 | 0 | 83.14% | UNDER
230 | Finish Material | Material | 89920 | 105538 | -28357.57 | 77180.43 | 0 | 0 | 0 | 0 | 0 | 73.13% | UNDER
242 | Mech Room Material | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
600 | Subcontractor | Overhead | 500 | 500 | -345 | 155 | 0 | 0 | 0 | 0 | 0 | 31% | UNDER
601 | Engineering/Plans | Overhead | 1000 | 1000 | -227.5 | 772.5 | 0 | 0 | 0 | 0 | 0 | 77.25% | UNDER
602 | Rental Equipment | Overhead | 1000 | 2046 | 63.22 | 2109.22 | 0 | 0 | 0 | 0 | 0 | 103.1% | ON
603 | Permits & Licenses | Overhead | 0 | 922 | 32.5 | 954.5 | 0 | 0 | 0 | 0 | 0 | 103.5% | ON
607 | Other Expenses | Overhead | 4000 | 4000 | -3960.77 | 39.23 | 0 | 0 | 0 | 0 | 0 | 0.9808% | UNDER
995 | Payroll Burden | Burden | 57937.8 | 65669.48 | 1161.99 | 66831.47 | 0 | 0 | 0 | 0 | 0 | 101.8% | ON
998 | Payroll Taxes | Burden | 9773.41 | 11117.69 | 410.4 | 11528.09 | 0 | 0 | 0 | 0 | 0 | 103.7% | ON
999 | Sales | Revenue | -475800 | -553189 | 0 | -553189 | 0 | -27659.45 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2047
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 2402 | 34 | 34 | 0 | 0 | 0 | Gerard, Jeffrey S ($2,190) | 01/05/18 | 12/29/17
101 | Takeoff & Purchase Labor | 5375 | 47 | 47 | 0 | 0 | 0 | Donelson, Richard T ($2,900) | 01/05/18 | 12/29/17
111 | Garage Labor | 0 | 4 | 4 | 0 | 0 | 0 | Hubbard, Robert W ($810) | 05/04/18 | 05/11/18
120 | Roughin Labor | 119374 | 195 | 195 | 0 | 0 | 0 | Reed, Reuben H ($28,170) | 01/05/18 | 12/29/17
130 | Finish Labor | 23539.75 | 80 | 80 | 0 | 0 | 0 | Sanders, Allen O ($7,456) | 03/30/18 | 08/24/18
141 | Water Main/Insulation Lab | 0 | 2 | 2 | 0 | 0 | 0 | Mendoza Morales, Jesus A ($368) | 02/09/18 | 02/16/18
142 | Mech Room Labor | 0 | 5 | 5 | 0 | 0 | 0 | Hubbard, Robert W ($1,530) | 04/20/18 | 05/25/18
143 | Condensation Drains Labor | 0 | 2 | 2 | 0 | 0 | 0 | Hubbard, Robert W ($270) | 03/09/18 | 03/16/18
211 | Garage Material | 10.6 | 4 | 0 | 0 | 4 | 0 | Req ($234) | 08/10/18 | 11/22/17
212 | Canout Material | 0 | 4 | 0 | 3 | 1 | 0 | Consolidated Supply Co. $Green Lake ($2,771) | 01/05/18 | 12/06/17
220 | Roughin Material | 56003.99 | 103 | 0 | 63 | 40 | 0 | Consolidated Supply Co. $Green Lake ($19,553) | 01/02/18 | 12/31/17
230 | Finish Material | 77180.43 | 68 | 0 | 52 | 16 | 0 | Keller Supply Co. $Green Lake ($34,626) | 01/05/18 | 12/31/17
242 | Mech Room Material | 0 | 6 | 0 | 4 | 2 | 0 | Rosen Supply Company, Inc. $Green Lake ($8,826) | 02/25/18 | 05/21/18
600 | Subcontractor | 155 | 1 | 0 | 1 | 0 | 0 | R.A. Brown Backflow Testing ($155) | 05/21/18 | 05/21/18
601 | Engineering/Plans | 772.5 | 1 | 0 | 1 | 0 | 0 | Franklin Engineering ($772) | 11/22/17 | 11/22/17
602 | Rental Equipment | 2109.22 | 4 | 0 | 4 | 0 | 0 | Ahern Rentals ($1,313) | 05/22/18 | 07/06/18
603 | Permits & Licenses | 954.5 | 4 | 0 | 4 | 0 | 0 | Bank of America CC ($502) | 02/21/18 | 12/01/17
607 | Other Expenses | 39.23 | 3 | 0 | 3 | 0 | 0 | Capital One Credit Card ($27) | 02/21/18 | 04/30/18
995 | Payroll Burden | 66831.47 | 369 | 369 | 0 | 0 | 0 | Reed, Reuben H ($12,493) | 01/05/18 | 12/29/17
998 | Payroll Taxes | 11528.09 | 369 | 369 | 0 | 0 | 0 | Reed, Reuben H ($2,155) | 01/05/18 | 12/29/17
999 | Sales | -553189 | 40 | 0 | 0 | 0 | 40 | GRE Construction LLC $Green Lake ($553,189) | 01/19/18 | 12/15/17

## Transactions Detail
TRANSACTIONS DETAIL — 1,345 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 3 | 0 | 150 | 0 | 150 | 97762 | 0 | 0
100 | Supervision | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 97763 | 0 | 0
100 | Supervision | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
100 | Supervision | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 17892 | 0 | 0
100 | Supervision | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 97956 | 0 | 0
100 | Supervision | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18020 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98002 | 0 | 0
100 | Supervision | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98148 | 0 | 0
100 | Supervision | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98215 | 0 | 0
100 | Supervision | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18280 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18410 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
100 | Supervision | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98540 | 0 | 0
100 | Supervision | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 2.5 | 0 | 117.5 | 0 | 117.5 | 98802 | 0 | 0
100 | Supervision | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18868 | 0 | 0
100 | Supervision | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18884 | 0 | 0
100 | Supervision | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
100 | Supervision | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 99998 | 0 | 0
100 | Supervision | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
100 | Supervision | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99351 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99501 | 0 | 0
100 | Supervision | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
100 | Supervision | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99576 | 0 | 0
100 | Supervision | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
100 | Supervision | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19722 | 0 | 0
100 | Supervision | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920008 | 0 | 0
100 | Supervision | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
100 | Supervision | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20163 | 0 | 0
100 | Supervision | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20809 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5.5 | 0 | 258.5 | 0 | 258.5 | 97763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 17892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 97956 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98002 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98148 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 4 | 0 | 200 | 0 | 200 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18410 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 98475 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 98539 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 918604 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | -187.5 | 0 | -187.5 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 18867 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18868 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99501 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20079 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 20162 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 290232 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920518 | 0 | 0
111 | Garage Labor | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 19681 | 0 | 0
111 | Garage Labor | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 4 | 0 | -180 | 0 | -180 | 19579 | 0 | 0
111 | Garage Labor | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 5 | 0 | 225 | 0 | 225 | 19758 | 0 | 0
111 | Garage Labor | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 5 | 0 | -225 | 0 | -225 | 99797 | 0 | 0
120 | Roughin Labor | PR | 295 | 10/18/17 | 10/20/17 | BE45 | Belcher, Jacob T | 16 | 0 | 256 | 0 | 256 | 17707 | 0 | 0
120 | Roughin Labor | PR | 310 | 10/18/17 | 10/20/17 | GA70 | Garcia, Jordan X | 15 | 0 | 465 | 0 | 465 | 17722 | 0 | 0
120 | Roughin Labor | PR | 336 | 10/18/17 | 10/20/17 | RE18 | Reed, Reuben H | 21 | 0 | 840 | 0 | 840 | 17748 | 0 | 0
120 | Roughin Labor | PR | 489 | 10/25/17 | 10/27/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 17768 | 0 | 0
120 | Roughin Labor | PR | 505 | 10/25/17 | 10/27/17 | GA70 | Garcia, Jordan X | 37 | 0 | 1147 | 0 | 1147 | 17784 | 0 | 0
120 | Roughin Labor | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 7 | 0 | 199.5 | 199.5 | 17794 | 0 | 0
120 | Roughin Labor | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 24 | 0 | 456 | 0 | 456 | 17794 | 0 | 0
120 | Roughin Labor | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 0 | 7 | 0 | 210 | 210 | 17802 | 0 | 0
120 | Roughin Labor | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 17802 | 0 | 0
120 | Roughin Labor | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 0 | 7 | 0 | 199.5 | 199.5 | 17808 | 0 | 0
120 | Roughin Labor | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 17808 | 0 | 0
120 | Roughin Labor | PR | 531 | 10/25/17 | 10/27/17 | RE18 | Reed, Reuben H | 39 | 0 | 1560 | 0 | 1560 | 17810 | 0 | 0
120 | Roughin Labor | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 0 | 4 | 0 | 96 | 96 | 17832 | 0 | 0
120 | Roughin Labor | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 17832 | 0 | 0
120 | Roughin Labor | PR | 25 | 11/01/17 | 11/03/17 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 17849 | 0 | 0
120 | Roughin Labor | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 4 | 0 | 114 | 114 | 17859 | 0 | 0
120 | Roughin Labor | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 17859 | 0 | 0
120 | Roughin Labor | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 0 | 4 | 0 | 120 | 120 | 17867 | 0 | 0
120 | Roughin Labor | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 17867 | 0 | 0
120 | Roughin Labor | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 0 | 4 | 0 | 114 | 114 | 17873 | 0 | 0
120 | Roughin Labor | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 17873 | 0 | 0
120 | Roughin Labor | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 0 | 4 | 0 | 240 | 240 | 17875 | 0 | 0
120 | Roughin Labor | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 17875 | 0 | 0
120 | Roughin Labor | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 1 | 0 | 43 | 0 | 43 | 17891 | 0 | 0
120 | Roughin Labor | PR | 155 | 11/08/17 | 11/10/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 17898 | 0 | 0
120 | Roughin Labor | PR | 172 | 11/08/17 | 11/10/17 | GA70 | Garcia, Jordan X | 48 | 0 | 1488 | 0 | 1488 | 17915 | 0 | 0
120 | Roughin Labor | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 228 | 228 | 17925 | 0 | 0
120 | Roughin Labor | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 17925 | 0 | 0
120 | Roughin Labor | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 0 | 7 | 0 | 210 | 210 | 17933 | 0 | 0
120 | Roughin Labor | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 17933 | 0 | 0
120 | Roughin Labor | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 228 | 228 | 17939 | 0 | 0
120 | Roughin Labor | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 17939 | 0 | 0
120 | Roughin Labor | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 0 | 8 | 0 | 480 | 480 | 17941 | 0 | 0
120 | Roughin Labor | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 17941 | 0 | 0
120 | Roughin Labor | PR | 289 | 11/15/17 | 11/17/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 17964 | 0 | 0
120 | Roughin Labor | PR | 305 | 11/15/17 | 11/17/17 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 17980 | 0 | 0
120 | Roughin Labor | PR | 311 | 11/15/17 | 11/17/17 | HO90 | Howey, Shawn M | 40 | 0 | 760 | 0 | 760 | 17986 | 0 | 0
120 | Roughin Labor | PR | 314 | 11/15/17 | 11/17/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 17989 | 0 | 0
120 | Roughin Labor | PR | 321 | 11/15/17 | 11/17/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 17996 | 0 | 0
120 | Roughin Labor | PR | 327 | 11/15/17 | 11/17/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18003 | 0 | 0
120 | Roughin Labor | PR | 329 | 11/15/17 | 11/17/17 | RE18 | Reed, Reuben H | 37 | 0 | 1480 | 0 | 1480 | 18005 | 0 | 0
120 | Roughin Labor | PR | 431 | 11/22/17 | 11/22/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 18025 | 0 | 0
120 | Roughin Labor | PR | 448 | 11/22/17 | 11/22/17 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18042 | 0 | 0
120 | Roughin Labor | PR | 458 | 11/22/17 | 11/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18052 | 0 | 0
120 | Roughin Labor | PR | 466 | 11/22/17 | 11/22/17 | ME52 | Mendoza, Edgar E | 39 | 0 | 780 | 0 | 780 | 18060 | 0 | 0
120 | Roughin Labor | PR | 472 | 11/22/17 | 11/22/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18066 | 0 | 0
120 | Roughin Labor | PR | 474 | 11/22/17 | 11/22/17 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 18068 | 0 | 0
120 | Roughin Labor | PR | 8 | 11/29/17 | 12/01/17 | BE45 | Belcher, Jacob T | 31 | 0 | 496 | 0 | 496 | 18089 | 0 | 0
120 | Roughin Labor | PR | 25 | 11/29/17 | 12/01/17 | GA70 | Garcia, Jordan X | 31 | 0 | 961 | 0 | 961 | 18106 | 0 | 0
120 | Roughin Labor | PR | 31 | 11/29/17 | 12/01/17 | HO18 | Hoeg, Xavier A | 8 | 0 | 120 | 0 | 120 | 18112 | 0 | 0
120 | Roughin Labor | PR | 35 | 11/29/17 | 12/01/17 | JI50 | Jimenez Alvarenga, Gerson M | 31 | 0 | 589 | 0 | 589 | 18116 | 0 | 0
120 | Roughin Labor | PR | 43 | 11/29/17 | 12/01/17 | ME52 | Mendoza, Edgar E | 31 | 0 | 620 | 0 | 620 | 18124 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 3 | 0 | 129 | 0 | 129 | 18129 | 0 | 0
120 | Roughin Labor | PR | 49 | 11/29/17 | 12/01/17 | RA55 | Ramos Herrera, Franklin J | 31 | 0 | 589 | 0 | 589 | 18130 | 0 | 0
120 | Roughin Labor | PR | 51 | 11/29/17 | 12/01/17 | RE18 | Reed, Reuben H | 15 | 0 | 600 | 0 | 600 | 18132 | 0 | 0
120 | Roughin Labor | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 13 | 0 | 559 | 0 | 559 | 18146 | 0 | 0
120 | Roughin Labor | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 0 | 4 | 0 | 96 | 96 | 18154 | 0 | 0
120 | Roughin Labor | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 18154 | 0 | 0
120 | Roughin Labor | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 7 | 0 | 199.5 | 199.5 | 18164 | 0 | 0
120 | Roughin Labor | PR | 227 | 12/06/17 | 12/08/17 | GA70 | Garcia, Jordan X | 44 | 0 | 1364 | 0 | 1364 | 18172 | 0 | 0
120 | Roughin Labor | PR | 230 | 12/06/17 | 12/08/17 | GO51 | Gomez Reyes, Edith N | 0 | 7 | 0 | 189 | 189 | 18175 | 0 | 0
120 | Roughin Labor | PR | 233 | 12/06/17 | 12/08/17 | HO18 | Hoeg, Xavier A | 24 | 0 | 360 | 0 | 360 | 18178 | 0 | 0
120 | Roughin Labor | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 7 | 0 | 199.5 | 199.5 | 18183 | 0 | 0
120 | Roughin Labor | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18183 | 0 | 0
120 | Roughin Labor | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 7 | 0 | 241.5 | 241.5 | 18187 | 0 | 0
120 | Roughin Labor | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 24 | 0 | 552 | 0 | 552 | 18187 | 0 | 0
120 | Roughin Labor | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 0 | 7 | 0 | 210 | 210 | 18191 | 0 | 0
120 | Roughin Labor | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18191 | 0 | 0
120 | Roughin Labor | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 0 | 7 | 0 | 199.5 | 199.5 | 18196 | 0 | 0
120 | Roughin Labor | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18196 | 0 | 0
120 | Roughin Labor | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 18197 | 0 | 0
120 | Roughin Labor | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 24 | 0 | 432 | 0 | 432 | 18197 | 0 | 0
120 | Roughin Labor | PR | 252 | 12/06/17 | 12/08/17 | RE18 | Reed, Reuben H | 18 | 0 | 720 | 0 | 720 | 18198 | 0 | 0
120 | Roughin Labor | PR | 406 | 12/13/17 | 12/15/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 18220 | 0 | 0
120 | Roughin Labor | PR | 424 | 12/13/17 | 12/15/17 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18238 | 0 | 0
120 | Roughin Labor | PR | 430 | 12/13/17 | 12/15/17 | HO18 | Hoeg, Xavier A | 24 | 0 | 360 | 0 | 360 | 18244 | 0 | 0
120 | Roughin Labor | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 21 | 0 | 945 | 0 | 945 | 18247 | 0 | 0
120 | Roughin Labor | PR | 434 | 12/13/17 | 12/15/17 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18248 | 0 | 0
120 | Roughin Labor | PR | 438 | 12/13/17 | 12/15/17 | LO87 | Lovo, German G | 30 | 0 | 690 | 0 | 690 | 18252 | 0 | 0
120 | Roughin Labor | PR | 442 | 12/13/17 | 12/15/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18256 | 0 | 0
120 | Roughin Labor | PR | 448 | 12/13/17 | 12/15/17 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18262 | 0 | 0
120 | Roughin Labor | PR | 449 | 12/13/17 | 12/15/17 | RA57 | Ramos Melendez, Carlos M | 38 | 0 | 684 | 0 | 684 | 18263 | 0 | 0
120 | Roughin Labor | PR | 450 | 12/13/17 | 12/15/17 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 18264 | 0 | 0
120 | Roughin Labor | PR | 596 | 12/20/17 | 12/22/17 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 18350 | 0 | 0
120 | Roughin Labor | PR | 614 | 12/20/17 | 12/22/17 | GA70 | Garcia, Jordan X | 37 | 0 | 1147 | 0 | 1147 | 18368 | 0 | 0
120 | Roughin Labor | PR | 620 | 12/20/17 | 12/22/17 | HO18 | Hoeg, Xavier A | 32 | 0 | 480 | 0 | 480 | 18374 | 0 | 0
120 | Roughin Labor | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 6.5 | 0 | 292.5 | 0 | 292.5 | 18377 | 0 | 0
120 | Roughin Labor | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 7 | 0 | 199.5 | 199.5 | 18378 | 0 | 0
120 | Roughin Labor | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 608 | 0 | 608 | 18378 | 0 | 0
120 | Roughin Labor | PR | 628 | 12/20/17 | 12/22/17 | LO87 | Lovo, German G | 40 | 0 | 920 | 0 | 920 | 18382 | 0 | 0
120 | Roughin Labor | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 0 | 4 | 0 | 120 | 120 | 18386 | 0 | 0
120 | Roughin Labor | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18386 | 0 | 0
120 | Roughin Labor | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 7 | 0 | 199.5 | 199.5 | 18392 | 0 | 0
120 | Roughin Labor | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 32 | 0 | 608 | 0 | 608 | 18392 | 0 | 0
120 | Roughin Labor | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 18393 | 0 | 0
120 | Roughin Labor | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18393 | 0 | 0
120 | Roughin Labor | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 0 | 4 | 0 | 240 | 240 | 18394 | 0 | 0
120 | Roughin Labor | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 18394 | 0 | 0
120 | Roughin Labor | PR | 787 | 12/27/17 | 12/29/17 | BE45 | Belcher, Jacob T | 24 | 0 | 384 | 0 | 384 | 18416 | 0 | 0
120 | Roughin Labor | PR | 805 | 12/27/17 | 12/29/17 | GA70 | Garcia, Jordan X | 24 | 0 | 744 | 0 | 744 | 18434 | 0 | 0
120 | Roughin Labor | PR | 811 | 12/27/17 | 12/29/17 | HO18 | Hoeg, Xavier A | 24 | 0 | 360 | 0 | 360 | 18440 | 0 | 0
120 | Roughin Labor | PR | 815 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 16 | 0 | 304 | 0 | 304 | 18444 | 0 | 0
120 | Roughin Labor | PR | 819 | 12/27/17 | 12/29/17 | LO87 | Lovo, German G | 24 | 0 | 552 | 0 | 552 | 18448 | 0 | 0
120 | Roughin Labor | PR | 823 | 12/27/17 | 12/29/17 | ME52 | Mendoza, Edgar E | 24 | 0 | 480 | 0 | 480 | 18452 | 0 | 0
120 | Roughin Labor | PR | 828 | 12/27/17 | 12/29/17 | RA55 | Ramos Herrera, Franklin J | 24 | 0 | 456 | 0 | 456 | 18457 | 0 | 0
120 | Roughin Labor | PR | 829 | 12/27/17 | 12/29/17 | RA57 | Ramos Melendez, Carlos M | 24 | 0 | 432 | 0 | 432 | 18458 | 0 | 0
120 | Roughin Labor | PR | 830 | 12/27/17 | 12/29/17 | RE18 | Reed, Reuben H | 24 | 0 | 960 | 0 | 960 | 18459 | 0 | 0
120 | Roughin Labor | PR | 845 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 152 | 0 | 152 | 18474 | 0 | 0
120 | Roughin Labor | PR | 7 | 01/03/18 | 01/05/18 | BE45 | Belcher, Jacob T | 32 | 0 | 512 | 0 | 512 | 18480 | 0 | 0
120 | Roughin Labor | PR | 25 | 01/03/18 | 01/05/18 | GA70 | Garcia, Jordan X | 32 | 0 | 992 | 0 | 992 | 18498 | 0 | 0
120 | Roughin Labor | PR | 31 | 01/03/18 | 01/05/18 | HO18 | Hoeg, Xavier A | 32 | 0 | 480 | 0 | 480 | 18505 | 0 | 0
120 | Roughin Labor | PR | 35 | 01/03/18 | 01/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 27 | 0 | 513 | 0 | 513 | 18509 | 0 | 0
120 | Roughin Labor | PR | 39 | 01/03/18 | 01/05/18 | LO87 | Lovo, German G | 29 | 0 | 667 | 0 | 667 | 18513 | 0 | 0
120 | Roughin Labor | PR | 43 | 01/03/18 | 01/05/18 | ME52 | Mendoza, Edgar E | 24 | 0 | 480 | 0 | 480 | 18517 | 0 | 0
120 | Roughin Labor | PR | 49 | 01/03/18 | 01/05/18 | RA55 | Ramos Herrera, Franklin J | 27 | 0 | 513 | 0 | 513 | 18523 | 0 | 0
120 | Roughin Labor | PR | 50 | 01/03/18 | 01/05/18 | RA57 | Ramos Melendez, Carlos M | 31 | 0 | 558 | 0 | 558 | 18524 | 0 | 0
120 | Roughin Labor | PR | 51 | 01/03/18 | 01/05/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 18525 | 0 | 0
120 | Roughin Labor | PR | 230 | 01/10/18 | 01/12/18 | BE45 | Belcher, Jacob T | 40 | 0 | 640 | 0 | 640 | 18545 | 0 | 0
120 | Roughin Labor | PR | 248 | 01/10/18 | 01/12/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18563 | 0 | 0
120 | Roughin Labor | PR | 254 | 01/10/18 | 01/12/18 | HO18 | Hoeg, Xavier A | 40 | 0 | 600 | 0 | 600 | 18569 | 0 | 0
120 | Roughin Labor | PR | 258 | 01/10/18 | 01/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18573 | 0 | 0
120 | Roughin Labor | PR | 262 | 01/10/18 | 01/12/18 | LO87 | Lovo, German G | 24 | 0 | 552 | 0 | 552 | 18577 | 0 | 0
120 | Roughin Labor | PR | 266 | 01/10/18 | 01/12/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18581 | 0 | 0
120 | Roughin Labor | PR | 272 | 01/10/18 | 01/12/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18587 | 0 | 0
120 | Roughin Labor | PR | 273 | 01/10/18 | 01/12/18 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18588 | 0 | 0
120 | Roughin Labor | PR | 274 | 01/10/18 | 01/12/18 | RE18 | Reed, Reuben H | 37 | 0 | 1480 | 0 | 1480 | 18589 | 0 | 0
120 | Roughin Labor | PR | 390 | 01/17/18 | 01/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 208 | 0 | 208 | 18604 | 0 | 0
120 | Roughin Labor | PR | 396 | 01/17/18 | 01/19/18 | BE45 | Belcher, Jacob T | 29.5 | 0 | 472 | 0 | 472 | 18610 | 0 | 0
120 | Roughin Labor | PR | 402 | 01/17/18 | 01/19/18 | CH20 | Chevez, Herson G | 8 | 0 | 120 | 0 | 120 | 18616 | 0 | 0
120 | Roughin Labor | PR | 414 | 01/17/18 | 01/19/18 | GA70 | Garcia, Jordan X | 29.5 | 0 | 914.5 | 0 | 914.5 | 18629 | 0 | 0
120 | Roughin Labor | PR | 420 | 01/17/18 | 01/19/18 | HO18 | Hoeg, Xavier A | 29.5 | 0 | 442.5 | 0 | 442.5 | 18635 | 0 | 0
120 | Roughin Labor | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 4 | 0 | 114 | 114 | 18639 | 0 | 0
120 | Roughin Labor | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18639 | 0 | 0
120 | Roughin Labor | PR | 428 | 01/17/18 | 01/19/18 | LO87 | Lovo, German G | 22 | 0 | 506 | 0 | 506 | 18643 | 0 | 0
120 | Roughin Labor | PR | 429 | 01/17/18 | 01/19/18 | LU09 | Lucas Tzintzun, Rafael | 8 | 0 | 128 | 0 | 128 | 18644 | 0 | 0
120 | Roughin Labor | PR | 432 | 01/17/18 | 01/19/18 | ME52 | Mendoza, Edgar E | 28 | 0 | 560 | 0 | 560 | 18647 | 0 | 0
120 | Roughin Labor | PR | 433 | 01/17/18 | 01/19/18 | ME53 | Mendoza Morales, Jesus A | 8 | 0 | 184 | 0 | 184 | 18648 | 0 | 0
120 | Roughin Labor | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 4 | 0 | 114 | 114 | 18653 | 0 | 0
120 | Roughin Labor | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18653 | 0 | 0
120 | Roughin Labor | PR | 439 | 01/17/18 | 01/19/18 | RA57 | Ramos Melendez, Carlos M | 24 | 0 | 432 | 0 | 432 | 18654 | 0 | 0
120 | Roughin Labor | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 0 | 1.5 | 0 | 90 | 90 | 18655 | 0 | 0
120 | Roughin Labor | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 18655 | 0 | 0
120 | Roughin Labor | PR | 592 | 01/24/18 | 01/26/18 | BE45 | Belcher, Jacob T | 8 | 0 | 128 | 0 | 128 | 18676 | 0 | 0
120 | Roughin Labor | PR | 609 | 01/24/18 | 01/26/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18693 | 0 | 0
120 | Roughin Labor | PR | 619 | 01/24/18 | 01/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 760 | 0 | 760 | 18703 | 0 | 0
120 | Roughin Labor | PR | 627 | 01/24/18 | 01/26/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18711 | 0 | 0
120 | Roughin Labor | PR | 628 | 01/24/18 | 01/26/18 | ME53 | Mendoza Morales, Jesus A | 8 | 0 | 184 | 0 | 184 | 18712 | 0 | 0
120 | Roughin Labor | PR | 633 | 01/24/18 | 01/26/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 760 | 0 | 760 | 18717 | 0 | 0
120 | Roughin Labor | PR | 635 | 01/24/18 | 01/26/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 18719 | 0 | 0
120 | Roughin Labor | PR | 29 | 01/31/18 | 02/02/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18759 | 0 | 0
120 | Roughin Labor | PR | 47 | 01/31/18 | 02/02/18 | ME52 | Mendoza, Edgar E | 40 | 0 | 800 | 0 | 800 | 18777 | 0 | 0
120 | Roughin Labor | PR | 48 | 01/31/18 | 02/02/18 | ME53 | Mendoza Morales, Jesus A | 8 | 0 | 184 | 0 | 184 | 18778 | 0 | 0
120 | Roughin Labor | PR | 56 | 01/31/18 | 02/02/18 | RE18 | Reed, Reuben H | 32 | 0 | 1280 | 0 | 1280 | 18786 | 0 | 0
120 | Roughin Labor | PR | 186 | 02/07/18 | 02/09/18 | GA70 | Garcia, Jordan X | 40 | 0 | 1240 | 0 | 1240 | 18827 | 0 | 0
120 | Roughin Labor | PR | 204 | 02/07/18 | 02/09/18 | ME52 | Mendoza, Edgar E | 32 | 0 | 640 | 0 | 640 | 18845 | 0 | 0
120 | Roughin Labor | PR | 212 | 02/07/18 | 02/09/18 | RE18 | Reed, Reuben H | 40 | 0 | 1600 | 0 | 1600 | 18853 | 0 | 0
120 | Roughin Labor | PR | 440 | 02/14/18 | 02/16/18 | GA70 | Garcia, Jordan X | 24 | 0 | 744 | 0 | 744 | 18894 | 0 | 0
120 | Roughin Labor | PR | 458 | 02/14/18 | 02/16/18 | ME52 | Mendoza, Edgar E | 23 | 0 | 460 | 0 | 460 | 18912 | 0 | 0
120 | Roughin Labor | PR | 467 | 02/14/18 | 02/16/18 | RE18 | Reed, Reuben H | 24 | 0 | 960 | 0 | 960 | 18921 | 0 | 0
120 | Roughin Labor | PR | 627 | 02/21/18 | 02/23/18 | GA70 | Garcia, Jordan X | 24 | 0 | 744 | 0 | 744 | 18961 | 0 | 0
120 | Roughin Labor | PR | 645 | 02/21/18 | 02/23/18 | ME52 | Mendoza, Edgar E | 24 | 0 | 480 | 0 | 480 | 18979 | 0 | 0
120 | Roughin Labor | PR | 654 | 02/21/18 | 02/23/18 | RE18 | Reed, Reuben H | 23 | 0 | 920 | 0 | 920 | 18988 | 0 | 0
120 | Roughin Labor | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 25 | 0 | 775 | 0 | 775 | 19028 | 0 | 0
120 | Roughin Labor | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 33 | 0 | 660 | 0 | 660 | 19046 | 0 | 0
120 | Roughin Labor | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 30 | 0 | 1200 | 0 | 1200 | 19055 | 0 | 0
120 | Roughin Labor | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19171 | 0 | 0
120 | Roughin Labor | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 0 | 8 | 0 | 240 | 240 | 19180 | 0 | 0
120 | Roughin Labor | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 8 | 0 | 320 | 0 | 320 | 19190 | 0 | 0
120 | Roughin Labor | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 4 | 0 | 80 | 0 | 80 | 19249 | 0 | 0
120 | Roughin Labor | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 8 | 0 | 320 | 0 | 320 | 19259 | 0 | 0
120 | Roughin Labor | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 8 | 0 | 248 | 0 | 248 | 19450 | 0 | 0
120 | Roughin Labor | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 8 | 0 | 128 | 0 | 128 | 19469 | 0 | 0
120 | Roughin Labor | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 16 | 0 | 320 | 0 | 320 | 19472 | 0 | 0
120 | Roughin Labor | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 16 | 0 | 640 | 0 | 640 | 19483 | 0 | 0
120 | Roughin Labor | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 8 | 0 | 360 | 0 | 360 | 19609 | 0 | 0
120 | Roughin Labor | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 8 | 0 | 248 | 0 | 248 | 19620 | 0 | 0
120 | Roughin Labor | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 8 | 0 | 320 | 0 | 320 | 19631 | 0 | 0
120 | Roughin Labor | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 6 | 0 | 270 | 0 | 270 | 19681 | 0 | 0
120 | Roughin Labor | PR | 69 | 05/02/18 | 05/04/18 | MC09 | McCabe, Thomas C | 37 | 0 | 1147 | 0 | 1147 | 19692 | 0 | 0
120 | Roughin Labor | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 19579 | 0 | 0
120 | Roughin Labor | PR | 262 | 05/09/18 | 05/11/18 | MC09 | McCabe, Thomas C | 32 | 0 | 992 | 0 | 992 | 19769 | 0 | 0
120 | Roughin Labor | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 5 | 0 | 225 | 0 | 225 | 99797 | 0 | 0
120 | Roughin Labor | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 10 | 0 | 450 | 0 | 450 | 19825 | 0 | 0
120 | Roughin Labor | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 33 | 0 | 1023 | 0 | 1023 | 19836 | 0 | 0
120 | Roughin Labor | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 8 | 0 | -248 | 0 | -248 | 19886 | 0 | 0
120 | Roughin Labor | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 17 | 0 | 765 | 0 | 765 | 19896 | 0 | 0
120 | Roughin Labor | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 19896 | 0 | 0
120 | Roughin Labor | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 8 | 0 | 248 | 0 | 248 | 19907 | 0 | 0
120 | Roughin Labor | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 27 | 0 | 837 | 0 | 837 | 19907 | 0 | 0
120 | Roughin Labor | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 4 | 0 | 180 | 0 | 180 | 19968 | 0 | 0
120 | Roughin Labor | PR | 45 | 05/30/18 | 06/01/18 | MC09 | McCabe, Thomas C | 40 | 0 | 1240 | 0 | 1240 | 19979 | 0 | 0
120 | Roughin Labor | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 2 | 0 | 80 | 0 | 80 | 19990 | 0 | 0
120 | Roughin Labor | PR | 63 | 05/30/18 | 06/01/18 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 248 | 0 | 248 | 19997 | 0 | 0
120 | Roughin Labor | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 5.5 | 0 | 247.5 | 0 | 247.5 | 20039 | 0 | 0
120 | Roughin Labor | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 20050 | 0 | 0
130 | Finish Labor | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 1.5 | 0 | 63 | 0 | 63 | 19339 | 0 | 0
130 | Finish Labor | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 5.5 | 0 | 88 | 0 | 88 | 19360 | 0 | 0
130 | Finish Labor | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 5.5 | 0 | 148.5 | 0 | 148.5 | 19378 | 0 | 0
130 | Finish Labor | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 5.5 | 0 | 99 | 0 | 99 | 19380 | 0 | 0
130 | Finish Labor | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 5.5 | 0 | 88 | 0 | 88 | 19402 | 0 | 0
130 | Finish Labor | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 5.5 | 0 | 88 | 0 | 88 | 19412 | 0 | 0
130 | Finish Labor | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 5.5 | 0 | 88 | 0 | 88 | 19415 | 0 | 0
130 | Finish Labor | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 5.5 | 0 | 231 | 0 | 231 | 19416 | 0 | 0
130 | Finish Labor | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 5.5 | 0 | 99 | 0 | 99 | 19425 | 0 | 0
130 | Finish Labor | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 24 | 0 | 384 | 0 | 384 | 19434 | 0 | 0
130 | Finish Labor | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 24 | 0 | 432 | 0 | 432 | 19453 | 0 | 0
130 | Finish Labor | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 3 | 0 | 48 | 0 | 48 | 19475 | 0 | 0
130 | Finish Labor | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 15.5 | 0 | 651 | 0 | 651 | 19490 | 0 | 0
130 | Finish Labor | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 0 | 2 | 0 | 48 | 48 | 19511 | 0 | 0
130 | Finish Labor | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 40 | 0 | 640 | 0 | 640 | 19511 | 0 | 0
130 | Finish Labor | PR | 470 | 04/18/18 | 04/20/18 | GO51 | Gomez Reyes, Edith N | 34 | 0 | 612 | 0 | 612 | 19528 | 0 | 0
130 | Finish Labor | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 8 | 0 | 128 | 0 | 128 | 19551 | 0 | 0
130 | Finish Labor | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 126 | 126 | 19565 | 0 | 0
130 | Finish Labor | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 31.5 | 0 | 1323 | 0 | 1323 | 19565 | 0 | 0
130 | Finish Labor | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 0 | 2 | 0 | 48 | 48 | 19585 | 0 | 0
130 | Finish Labor | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 16 | 0 | 256 | 0 | 256 | 19585 | 0 | 0
130 | Finish Labor | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 0 | 10 | 0 | 270 | 270 | 19602 | 0 | 0
130 | Finish Labor | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 288 | 0 | 288 | 19602 | 0 | 0
130 | Finish Labor | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 0 | 8 | 0 | 372 | 372 | 19620 | 0 | 0
130 | Finish Labor | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 504 | 504 | 19638 | 0 | 0
130 | Finish Labor | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 11.5 | 0 | 483 | 0 | 483 | 19638 | 0 | 0
130 | Finish Labor | PR | 34 | 05/02/18 | 05/04/18 | CA50 | Caro, Camilo | 8 | 0 | 128 | 0 | 128 | 19657 | 0 | 0
130 | Finish Labor | PR | 51 | 05/02/18 | 05/04/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 144 | 0 | 144 | 19674 | 0 | 0
130 | Finish Labor | PR | 73 | 05/02/18 | 05/04/18 | NE46 | Nelson, Charles E | 8 | 0 | 128 | 0 | 128 | 19696 | 0 | 0
130 | Finish Labor | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 11.5 | 0 | 483 | 0 | 483 | 19711 | 0 | 0
130 | Finish Labor | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 24 | 0 | 648 | 0 | 648 | 19750 | 0 | 0
130 | Finish Labor | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 1 | 0 | 40.5 | 40.5 | 19750 | 0 | 0
130 | Finish Labor | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 24 | 0 | 384 | 0 | 384 | 19774 | 0 | 0
130 | Finish Labor | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 17 | 0 | 272 | 0 | 272 | 19782 | 0 | 0
130 | Finish Labor | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 5 | 0 | 210 | 0 | 210 | 19785 | 0 | 0
130 | Finish Labor | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 24 | 0 | 432 | 0 | 432 | 19792 | 0 | 0
130 | Finish Labor | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 1.5 | 0 | 60.75 | 60.75 | 19816 | 0 | 0
130 | Finish Labor | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 16 | 0 | 432 | 0 | 432 | 19816 | 0 | 0
130 | Finish Labor | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 1 | 0 | 42 | 0 | 42 | 19854 | 0 | 0
130 | Finish Labor | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 24 | 0 | 432 | 0 | 432 | 19863 | 0 | 0
130 | Finish Labor | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 4 | 0 | 162 | 162 | 19887 | 0 | 0
130 | Finish Labor | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 36 | 0 | 972 | 0 | 972 | 19887 | 0 | 0
130 | Finish Labor | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 0 | 2 | 0 | 54 | 54 | 19889 | 0 | 0
130 | Finish Labor | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 144 | 0 | 144 | 19889 | 0 | 0
130 | Finish Labor | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 93 | 93 | 19907 | 0 | 0
130 | Finish Labor | PR | 784 | 05/23/18 | 05/25/18 | OL17 | Olea Galeana, Maricela | 8 | 0 | 128 | 0 | 128 | 19913 | 0 | 0
130 | Finish Labor | PR | 796 | 05/23/18 | 05/25/18 | SA54 | Sanders, Allen O | 10 | 0 | 420 | 0 | 420 | 19925 | 0 | 0
130 | Finish Labor | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 30 | 0 | 540 | 0 | 540 | 19934 | 0 | 0
130 | Finish Labor | PR | 25 | 05/30/18 | 06/01/18 | GE70 | Gerard, Jordan E | 36 | 0 | 972 | 0 | 972 | 19959 | 0 | 0
130 | Finish Labor | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 0 | 3 | 0 | 81 | 81 | 19961 | 0 | 0
130 | Finish Labor | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 4 | 0 | 72 | 0 | 72 | 19961 | 0 | 0
130 | Finish Labor | PR | 62 | 05/30/18 | 06/01/18 | SA54 | Sanders, Allen O | 8.5 | 0 | 357 | 0 | 357 | 19996 | 0 | 0
130 | Finish Labor | PR | 72 | 05/30/18 | 06/01/18 | YO29 | Yohannes Jr., Samson | 39.5 | 0 | 711 | 0 | 711 | 20006 | 0 | 0
130 | Finish Labor | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 28 | 0 | 756 | 0 | 756 | 20030 | 0 | 0
130 | Finish Labor | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 0 | 1 | 0 | 27 | 27 | 20032 | 0 | 0
130 | Finish Labor | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 288 | 0 | 288 | 20032 | 0 | 0
130 | Finish Labor | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 0 | 1 | 0 | 63 | 63 | 20067 | 0 | 0
130 | Finish Labor | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 15 | 0 | 630 | 0 | 630 | 20067 | 0 | 0
130 | Finish Labor | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 20 | 0 | 360 | 0 | 360 | 20078 | 0 | 0
130 | Finish Labor | PR | 476 | 06/13/18 | 06/15/18 | EL33 | Eliassen, Cory H | 8 | 0 | 184 | 0 | 184 | 20111 | 0 | 0
130 | Finish Labor | PR | 480 | 06/13/18 | 06/15/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1200 | 0 | 1200 | 20115 | 0 | 0
130 | Finish Labor | PR | 482 | 06/13/18 | 06/15/18 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 160 | 0 | 160 | 20117 | 0 | 0
130 | Finish Labor | PR | 504 | 06/13/18 | 06/15/18 | NE46 | Nelson, Charles E | 8 | 0 | 128 | 0 | 128 | 20139 | 0 | 0
130 | Finish Labor | PR | 516 | 06/13/18 | 06/15/18 | SA54 | Sanders, Allen O | 17.5 | 0 | 770 | 0 | 770 | 20151 | 0 | 0
130 | Finish Labor | PR | 526 | 06/13/18 | 06/15/18 | YO29 | Yohannes Jr., Samson | 32 | 0 | 576 | 0 | 576 | 20161 | 0 | 0
130 | Finish Labor | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 8 | 0 | 240 | 0 | 240 | 20185 | 0 | 0
130 | Finish Labor | PR | 742 | 06/20/18 | 06/22/18 | SA54 | Sanders, Allen O | 3.5 | 0 | 154 | 0 | 154 | 20221 | 0 | 0
130 | Finish Labor | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 22 | 0 | 660 | 0 | 660 | 20254 | 0 | 0
130 | Finish Labor | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 22 | 0 | 704 | 0 | 704 | 20255 | 0 | 0
130 | Finish Labor | PR | 1009 | 06/27/18 | 06/29/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 20289 | 0 | 0
130 | Finish Labor | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 22 | 0 | -704 | 0 | -704 | 920304 | 0 | 0
130 | Finish Labor | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20325 | 0 | 0
130 | Finish Labor | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 20360 | 0 | 0
130 | Finish Labor | PR | 320 | 07/11/18 | 07/13/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20400 | 0 | 0
130 | Finish Labor | PR | 497 | 07/18/18 | 07/20/18 | SA54 | Sanders, Allen O | 1.5 | 0 | 66 | 0 | 66 | 20507 | 0 | 0
130 | Finish Labor | PR | 824 | 07/25/18 | 07/27/18 | SA54 | Sanders, Allen O | 1 | 0 | 44 | 0 | 44 | 20581 | 0 | 0
130 | Finish Labor | PR | 62 | 08/01/18 | 08/03/18 | SA54 | Sanders, Allen O | 5 | 0 | 220 | 0 | 220 | 20653 | 0 | 0
130 | Finish Labor | PR | 517 | 08/15/18 | 08/17/18 | KI55 | Kinssies, Jr, John E | 5 | 0 | 130 | 0 | 130 | 20774 | 0 | 0
130 | Finish Labor | PR | 540 | 08/15/18 | 08/17/18 | SA54 | Sanders, Allen O | 5 | 0 | 220 | 0 | 220 | 20797 | 0 | 0
130 | Finish Labor | PR | 801 | 08/22/18 | 08/24/18 | SA54 | Sanders, Allen O | 5 | 0 | 220 | 0 | 220 | 20868 | 0 | 0
141 | Water Main/Insulation Lab | PR | 205 | 02/07/18 | 02/09/18 | ME53 | Mendoza Morales, Jesus A | 8 | 0 | 184 | 0 | 184 | 18846 | 0 | 0
141 | Water Main/Insulation Lab | PR | 543 | 02/14/18 | 02/16/18 | ME53 | Mendoza Morales, Jesus A | 8 | 0 | -184 | 0 | -184 | 18887 | 0 | 0
142 | Mech Room Labor | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 11 | 0 | 495 | 0 | 495 | 19535 | 0 | 0
142 | Mech Room Labor | PR | 488 | 04/18/18 | 04/20/18 | MC09 | McCabe, Thomas C | 8 | 0 | 248 | 0 | 248 | 19546 | 0 | 0
142 | Mech Room Labor | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 6 | 0 | 270 | 0 | 270 | 19681 | 0 | 0
142 | Mech Room Labor | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 17 | 0 | -765 | 0 | -765 | 19896 | 0 | 0
142 | Mech Room Labor | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 8 | 0 | -248 | 0 | -248 | 19907 | 0 | 0
143 | Condensation Drains Labor | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 19106 | 0 | 0
143 | Condensation Drains Labor | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 3 | 0 | -135 | 0 | -135 | 19171 | 0 | 0
211 | Garage Material | GL | 358 | 11/17/17 | 11/17/17 | Mat | Req 3270 |  |  |  |  | 78 |  | 0 | 0
211 | Garage Material | GL | 513 | 11/22/17 | 11/22/17 | Mat | Req 3302 |  |  |  |  | 156 |  | 0 | 0
211 | Garage Material | GL | 601 | 11/22/17 | 11/22/17 | Mat | Req |  |  |  |  | -234 |  | 0 | 0
211 | Garage Material | GL | 316 | 08/10/18 | 08/10/18 | Mat | Req 4592 |  |  |  |  | 10.6 |  | 0 | 0
212 | Canout Material | AP | 199 | 11/20/17 | 12/06/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 1385.58 | S8505277.001 | 0 | 0
212 | Canout Material | AP | 349 | 11/20/17 | 12/06/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | -1385.58 | S8505277.001A | 0 | 0
212 | Canout Material | AP | 350 | 11/20/17 | 12/06/17 | 2037CS | Consolidated Supply Co. $University |  |  |  |  | 1385.58 | S8505277.001 | 0 | 0
212 | Canout Material | GL | 88 | 01/05/18 | 01/05/18 | Adj | [5 empty] | -1385.58 |  | 0 | 0
220 | Roughin Material | AP | 470 | 10/19/17 | 10/25/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 7150.58 | S8460702.001 | 0 | 0
220 | Roughin Material | AP | 646 | 10/18/17 | 10/26/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 107.84 | 4244063-00 | 0 | 0
220 | Roughin Material | AP | 647 | 10/18/17 | 10/26/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1754.91 | 7130254-00 | 0 | 0
220 | Roughin Material | AP | 648 | 10/18/17 | 10/26/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 245.1 | 7130255-00 | 0 | 0
220 | Roughin Material | AP | 649 | 10/24/17 | 10/26/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 293.78 | 4244255-00 | 0 | 0
220 | Roughin Material | AP | 650 | 10/25/17 | 10/26/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 345.49 | 7130460-00 | 0 | 0
220 | Roughin Material | GL | 661 | 10/31/17 | 10/31/17 | Mat | Req 3343 |  |  |  |  | 753.39 |  | 0 | 0
220 | Roughin Material | AP | 88 | 10/19/17 | 11/03/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 339.07 | S8460702.002 | 0 | 0
220 | Roughin Material | AP | 272 | 10/30/17 | 11/13/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1376 | 4244429-00 | 0 | 0
220 | Roughin Material | AP | 273 | 10/30/17 | 11/13/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1362.04 | 4244434-00 | 0 | 0
220 | Roughin Material | GL | 367 | 11/17/17 | 11/17/17 | Mat | Req 3278 |  |  |  |  | 502.5 |  | 0 | 0
220 | Roughin Material | AP | 414 | 11/08/17 | 11/20/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1201.9 | 4244648-00 | 0 | 0
220 | Roughin Material | GL | 514 | 11/22/17 | 11/22/17 | Mat | Req 3301 |  |  |  |  | 475.25 |  | 0 | 0
220 | Roughin Material | GL | 601 | 11/22/17 | 11/22/17 | Mat | Req |  |  |  |  | 234 |  | 0 | 0
220 | Roughin Material | AP | 603 | 11/10/17 | 11/22/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 767.92 | 7130944-00 | 0 | 0
220 | Roughin Material | AP | 610 | 11/10/17 | 11/22/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 7318.46 | S8491342.001 | 0 | 0
220 | Roughin Material | AP | 611 | 11/10/17 | 11/22/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 444.99 | S8491342.002 | 0 | 0
220 | Roughin Material | AP | 612 | 11/10/17 | 11/22/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 194.97 | S8495068.001 | 0 | 0
220 | Roughin Material | GL | 72 | 12/01/17 | 12/01/17 | Mat | Req 4037 |  |  |  |  | 176.57 |  | 0 | 0
220 | Roughin Material | GL | 127 | 12/01/17 | 12/01/17 | Mat | Req 4056 |  |  |  |  | 463.45 |  | 0 | 0
220 | Roughin Material | AP | 135 | 11/13/17 | 12/01/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 142.2 | S8495068.002 | 0 | 0
220 | Roughin Material | GL | 563 | 12/07/17 | 12/07/17 | Mat | Req 4074 |  |  |  |  | 2787.3 |  | 0 | 0
220 | Roughin Material | AP | 303 | 11/15/17 | 12/08/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1058.43 | 4245075-00 | 0 | 0
220 | Roughin Material | AP | 352 | 11/21/17 | 12/12/17 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 782.04 | S8509537.001 | 0 | 0
220 | Roughin Material | AP | 395 | 11/28/17 | 12/13/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 519.41 | 7131327-00 | 0 | 0
220 | Roughin Material | GL | 745 | 12/22/17 | 12/22/17 | Mat | Req 3372 |  |  |  |  | 292.06 |  | 0 | 0
220 | Roughin Material | GL | 751 | 12/22/17 | 12/22/17 | Mat | Req 3385 |  |  |  |  | 18.62 |  | 0 | 0
220 | Roughin Material | AP | 765 | 12/05/17 | 12/22/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 15.22 | 7131582-00 | 0 | 0
220 | Roughin Material | GL | 861 | 12/28/17 | 12/28/17 | Mat | Req 3367 |  |  |  |  | 340.04 |  | 0 | 0
220 | Roughin Material | GL | 862 | 12/28/17 | 12/28/17 | Mat | Req 4122 |  |  |  |  | 1814.67 |  | 0 | 0
220 | Roughin Material | AP | 917 | 12/20/17 | 12/31/17 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 114.98 | 5822332 | 0 | 0
220 | Roughin Material | AP | 298 | 12/08/17 | 01/02/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 617.08 | S8531719.001 | 0 | 0
220 | Roughin Material | GL | 74 | 01/05/18 | 01/05/18 | Mat | Req 3398 |  |  |  |  | 212.4 |  | 0 | 0
220 | Roughin Material | GL | 83 | 01/05/18 | 01/05/18 | Mat | Req 4109 |  |  |  |  | 512 |  | 0 | 0
220 | Roughin Material | GL | 88 | 01/05/18 | 01/05/18 | Adj | [5 empty] | 1385.58 |  | 0 | 0
220 | Roughin Material | AP | 126 | 12/20/17 | 01/05/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 780.43 | 4246254-00 | 0 | 0
220 | Roughin Material | AP | 147 | 12/29/17 | 01/08/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 321.82 | 7132209-00 | 0 | 0
220 | Roughin Material | AP | 192 | 12/28/17 | 01/10/18 | 2034CS | Consolidated Supply Co. $Park Lane |  |  |  |  | 339.66 | S8556771.001 | 0 | 0
220 | Roughin Material | AP | 193 | 12/28/17 | 01/10/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 121.6 | S8556771.002 | 0 | 0
220 | Roughin Material | GL | 333 | 01/16/18 | 01/16/18 | Mat | Req 3422 |  |  |  |  | 696.22 |  | 0 | 0
220 | Roughin Material | AP | 356 | 01/04/18 | 01/16/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 118.4 | 4246569-00 | 0 | 0
220 | Roughin Material | AP | 357 | 01/09/18 | 01/16/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 82.69 | 4246747-00 | 0 | 0
220 | Roughin Material | GL | 662 | 01/30/18 | 01/30/18 | Mat | Req 3453 |  |  |  |  | 355 |  | 0 | 0
220 | Roughin Material | AP | 301 | 12/28/17 | 02/01/18 | 2034CS | Consolidated Supply Co. $Park Lane |  |  |  |  | -339.66 | S8556771.001A | 0 | 0
220 | Roughin Material | AP | 302 | 12/28/17 | 02/01/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 339.66 | S8556771.001 | 0 | 0
220 | Roughin Material | GL | 88 | 02/02/18 | 02/02/18 | Mat | Req 4160 |  |  |  |  | 1691.62 |  | 0 | 0
220 | Roughin Material | AP | 120 | 01/16/18 | 02/06/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 902.57 | S8579574.001 | 0 | 0
220 | Roughin Material | GL | 496 | 02/16/18 | 02/16/18 | Mat | Req 4210 |  |  |  |  | 842.58 |  | 0 | 0
220 | Roughin Material | GL | 789 | 02/21/18 | 02/21/18 | Mat | Req 3483 |  |  |  |  | 482.8 |  | 0 | 0
220 | Roughin Material | AP | 727 | 02/19/18 | 02/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 225.8 | 4248396-00 | 0 | 0
220 | Roughin Material | AP | 366 | 02/02/18 | 02/25/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 476.77 | 7133203-00 | 0 | 0
220 | Roughin Material | AP | 545 | 02/06/18 | 02/25/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 4412.83 | 4247316-00B | 0 | 0
220 | Roughin Material | AP | 759 | 02/19/18 | 02/27/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 528.98 | S8625724.001 | 0 | 0
220 | Roughin Material | AP | 760 | 02/19/18 | 02/27/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 42.5 | S8625724.002 | 0 | 0
220 | Roughin Material | AP | 761 | 02/19/18 | 02/27/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 43.2 | S8625724.003 | 0 | 0
220 | Roughin Material | AP | 113 | 02/22/18 | 03/01/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 64.64 | S8628640.001 | 0 | 0
220 | Roughin Material | AP | 316 | 03/07/18 | 03/14/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 376.74 | S8649074.001 | 0 | 0
220 | Roughin Material | GL | 467 | 03/20/18 | 03/20/18 | Mat | Req 3550 |  |  |  |  | 236.85 |  | 0 | 0
220 | Roughin Material | AP | 595 | 03/09/18 | 03/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 125.2 | 4249212-00 | 0 | 0
220 | Roughin Material | AP | 681 | 03/12/18 | 03/26/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 425.26 | 7134281-00 | 0 | 0
220 | Roughin Material | GL | 834 | 03/31/18 | 03/31/18 | Mat | Req 4272 |  |  |  |  | 1195.12 |  | 0 | 0
220 | Roughin Material | GL | 370 | 04/16/18 | 04/16/18 | Mat | Req 3575 |  |  |  |  | -280 |  | 0 | 0
220 | Roughin Material | GL | 421 | 04/18/18 | 04/18/18 | Mat | Req 3577 |  |  |  |  | 1784.12 |  | 0 | 0
220 | Roughin Material | GL | 425 | 04/18/18 | 04/18/18 | Mat | Req 3578 |  |  |  |  | 360 |  | 0 | 0
220 | Roughin Material | GL | 694 | 04/18/18 | 04/18/18 | Mat | Req 3577 |  |  |  |  | -1784.12 |  | 0 | 0
220 | Roughin Material | GL | 699 | 04/18/18 | 04/18/18 | Mat | Req 3575 |  |  |  |  | -280 |  | 0 | 0
220 | Roughin Material | GL | 700 | 04/18/18 | 04/18/18 | Mat | Req 3578 |  |  |  |  | -126 |  | 0 | 0
220 | Roughin Material | GL | 708 | 04/27/18 | 04/27/18 | Mat | Req 3605 |  |  |  |  | 238.64 |  | 0 | 0
220 | Roughin Material | AP | 148 | 04/16/18 | 05/01/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 11.86 | 7135277-00 | 0 | 0
220 | Roughin Material | AP | 149 | 04/17/18 | 05/01/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 61.92 | 4250787-00 | 0 | 0
220 | Roughin Material | GL | 123 | 05/04/18 | 05/04/18 | Mat | Req 3632 |  |  |  |  | 238.22 |  | 0 | 0
220 | Roughin Material | GL | 132 | 05/04/18 | 05/04/18 | Mat | Req 3652 |  |  |  |  | -192.76 |  | 0 | 0
220 | Roughin Material | AP | 181 | 04/20/18 | 05/09/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 14.07 | 4250972-00 | 0 | 0
220 | Roughin Material | AP | 338 | 04/25/18 | 05/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 307.02 | 4251092-00 | 0 | 0
220 | Roughin Material | AP | 400 | 05/09/18 | 05/16/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 94.98 | S011864944.001 | 0 | 0
220 | Roughin Material | GL | 418 | 05/17/18 | 05/17/18 | Mat | Req 4360 |  |  |  |  | 213.84 |  | 0 | 0
220 | Roughin Material | GL | 536 | 05/21/18 | 05/21/18 | 2047KS | Inv S011781969.001 |  |  |  |  | 122.48 |  | 0 | 0
220 | Roughin Material | GL | 537 | 05/21/18 | 05/21/18 | 1231KS | S011804734.001 |  |  |  |  | 189.09 |  | 0 | 0
220 | Roughin Material | AP | 568 | 05/03/18 | 05/21/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 21.8 | 4251092-01 | 0 | 0
220 | Roughin Material | AP | 637 | 05/07/18 | 05/22/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1395.1 | 4251589-00 | 0 | 0
220 | Roughin Material | AP | 726 | 05/10/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 58.91 | 4251734-00 | 0 | 0
220 | Roughin Material | AP | 727 | 05/15/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 26.52 | 4251589-01 | 0 | 0
220 | Roughin Material | AP | 728 | 05/15/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 17.44 | 4251734-01 | 0 | 0
220 | Roughin Material | AP | 729 | 05/15/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 79.32 | 4251956-00 | 0 | 0
220 | Roughin Material | GL | 88 | 06/01/18 | 06/01/18 | Mat | Req 4389 |  |  |  |  | 401.18 |  | 0 | 0
220 | Roughin Material | GL | 89 | 06/01/18 | 06/01/18 | Mat | Req 4392 |  |  |  |  | 95.7 |  | 0 | 0
220 | Roughin Material | GL | 115 | 06/01/18 | 06/01/18 | Mat | Req 4398 |  |  |  |  | -121.99 |  | 0 | 0
220 | Roughin Material | GL | 116 | 06/01/18 | 06/01/18 | Mat | Req 4397 |  |  |  |  | -1003.67 |  | 0 | 0
220 | Roughin Material | AP | 261 | 05/16/18 | 06/01/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 27.96 | 4252092-00 | 0 | 0
220 | Roughin Material | AP | 262 | 05/17/18 | 06/01/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 198.4 | 4252089-00 | 0 | 0
220 | Roughin Material | AP | 203 | 05/21/18 | 06/05/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 1968.6 | S011895511.001 | 0 | 0
220 | Roughin Material | AP | 217 | 05/24/18 | 06/05/18 | 2047CS | Consolidated Supply Co. $Green Lake |  |  |  |  | 143.78 | S8764644.001 | 0 | 0
220 | Roughin Material | AP | 222 | 05/24/18 | 06/05/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 33.27 | 6234303 | 0 | 0
220 | Roughin Material | AP | 408 | 05/24/18 | 06/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 65.4 | 4251956-02 | 0 | 0
220 | Roughin Material | AP | 409 | 05/24/18 | 06/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 84 | 4252424-00 | 0 | 0
220 | Roughin Material | AP | 410 | 05/24/18 | 06/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 292.84 | 4252429-00 | 0 | 0
220 | Roughin Material | AP | 433 | 05/31/18 | 06/12/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 17.44 | 4252429-01 | 0 | 0
220 | Roughin Material | GL | 609 | 06/18/18 | 06/18/18 | Mat | Req 3679 |  |  |  |  | 166.41 |  | 0 | 0
220 | Roughin Material | AP | 626 | 06/12/18 | 06/19/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 49.15 | 6282598 | 0 | 0
220 | Roughin Material | AP | 645 | 05/30/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 5.21 | S011781969.002 | 0 | 0
220 | Roughin Material | GL | 768 | 06/22/18 | 06/22/18 | Mat | Req 3747 |  |  |  |  | -29.85 |  | 0 | 0
220 | Roughin Material | AP | 835 | 08/09/18 | 08/24/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 6.46 | 6450494 | 0 | 0
220 | Roughin Material | GL | 948 | 08/28/18 | 08/28/18 | Mat | Req 4649 |  |  |  |  | 21.73 |  | 0 | 0
230 | Finish Material | AP | 772 | 12/22/17 | 12/27/17 | 7230BB | Best Bath Systems |  |  |  |  | 3141.5 | 182450-IN | 0 | 0
230 | Finish Material | AP | 952 | 12/12/17 | 12/31/17 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 690.6 | 4245846-00 | 0 | 0
230 | Finish Material | GL | 71 | 01/05/18 | 01/05/18 | Mat | Req 3410 |  |  |  |  | 2027.16 |  | 0 | 0
230 | Finish Material | AP | 176 | 01/05/18 | 01/09/18 | 7230BB | Best Bath Systems |  |  |  |  | 1570.75 | 182715-IN | 0 | 0
230 | Finish Material | AP | 380 | 01/08/18 | 01/17/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 1859.88 | S011393322.001 | 0 | 0
230 | Finish Material | AP | 121 | 01/12/18 | 02/06/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 155 | 4246851-00 | 0 | 0
230 | Finish Material | AP | 335 | 02/08/18 | 02/12/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 390.1 | S011564454.001 | 0 | 0
230 | Finish Material | AP | 254 | 02/23/18 | 03/12/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 1738.32 | 4248102-00 | 0 | 0
230 | Finish Material | AP | 428 | 03/16/18 | 03/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 183.22 | S011671009.001 | 0 | 0
230 | Finish Material | AP | 668 | 03/13/18 | 03/26/18 | 5560CH | California Hydronics Corp |  |  |  |  | 1859 | 2089257 | 0 | 0
230 | Finish Material | AP | 3 | 03/23/18 | 04/04/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 1621.62 | S011671009.002 | 0 | 0
230 | Finish Material | AP | 203 | 03/30/18 | 04/10/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 7112.09 | 5966644 | 0 | 0
230 | Finish Material | AP | 220 | 03/30/18 | 04/10/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 3095.82 | S011671009.003 | 0 | 0
230 | Finish Material | AP | 221 | 03/30/18 | 04/10/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 1282.55 | S011671009.004 | 0 | 0
230 | Finish Material | AP | 222 | 04/03/18 | 04/10/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 507.45 | S011671089.002 | 0 | 0
230 | Finish Material | AP | 254 | 04/10/18 | 04/11/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 6980.96 | S011697528.001 | 0 | 0
230 | Finish Material | AP | 442 | 04/09/18 | 04/18/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 2774 | 4249288-00 | 0 | 0
230 | Finish Material | AP | 443 | 04/10/18 | 04/18/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 916.65 | 4250430-00 | 0 | 0
230 | Finish Material | GL | 694 | 04/18/18 | 04/18/18 | Mat | Req 3577 |  |  |  |  | 1784.12 |  | 0 | 0
230 | Finish Material | GL | 699 | 04/18/18 | 04/18/18 | Mat | Req 3575 |  |  |  |  | 280 |  | 0 | 0
230 | Finish Material | GL | 700 | 04/18/18 | 04/18/18 | Mat | Req 3578 |  |  |  |  | 126 |  | 0 | 0
230 | Finish Material | GL | 747 | 04/26/18 | 04/26/18 | Mat | Req 3610 |  |  |  |  | 467.96 |  | 0 | 0
230 | Finish Material | AP | 799 | 04/09/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 19.28 | 040918A | 0 | 0
230 | Finish Material | AP | 809 | 04/11/18 | 04/30/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 408.95 | 4250540-00 | 0 | 0
230 | Finish Material | AP | 810 | 04/13/18 | 04/30/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 134.44 | 4250656-00 | 0 | 0
230 | Finish Material | GL | 124 | 05/04/18 | 05/04/18 | Mat | Req 3631 |  |  |  |  | 110.7 |  | 0 | 0
230 | Finish Material | AP | 180 | 04/20/18 | 05/09/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 7325.42 | S011697447.001 | 0 | 0
230 | Finish Material | GL | 318 | 05/11/18 | 05/11/18 | Mat | Req 4341 |  |  |  |  | 238.04 |  | 0 | 0
230 | Finish Material | AP | 336 | 04/24/18 | 05/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | -19.5 | 4251136-00 | 0 | 0
230 | Finish Material | AP | 337 | 04/25/18 | 05/11/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 445.5 | 4250430-01 | 0 | 0
230 | Finish Material | AP | 377 | 05/08/18 | 05/15/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 7204.51 | S011697470.001 | 0 | 0
230 | Finish Material | AP | 413 | 04/26/18 | 05/16/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 7112.09 | 5966670 | 0 | 0
230 | Finish Material | AP | 535 | 05/08/18 | 05/21/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 7272.69 | 5966681 | 0 | 0
230 | Finish Material | AP | 567 | 04/30/18 | 05/21/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 13.4 | 4251334-00 | 0 | 0
230 | Finish Material | AP | 569 | 05/07/18 | 05/21/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 3.35 | 4251334-01 | 0 | 0
230 | Finish Material | GL | 604 | 04/27/18 | 05/22/18 | Mat | Req 4361 |  |  |  |  | 151 |  | 0 | 0
230 | Finish Material | GL | 622 | 05/22/18 | 05/22/18 | Mat | Req 4362 |  |  |  |  | 264.68 |  | 0 | 0
230 | Finish Material | AP | 361 | 03/30/18 | 05/25/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 29.55 | 4249954-00 | 0 | 0
230 | Finish Material | GL | 87 | 06/01/18 | 06/01/18 | Mat | Req 4390 |  |  |  |  | 534.87 |  | 0 | 0
230 | Finish Material | GL | 114 | 06/01/18 | 06/01/18 | Mat | Req 4399 |  |  |  |  | -181.5 |  | 0 | 0
230 | Finish Material | AP | 204 | 05/21/18 | 06/05/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 108.9 | S011899623.001 | 0 | 0
230 | Finish Material | AP | 434 | 05/31/18 | 06/12/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 540 | 4252631-00 | 0 | 0
230 | Finish Material | AP | 601 | 06/13/18 | 06/18/18 | 7230BB | Best Bath Systems |  |  |  |  | 126.39 | 189271-IN | 0 | 0
230 | Finish Material | GL | 608 | 06/18/18 | 06/18/18 | Mat | Req 3680 |  |  |  |  | 784.48 |  | 0 | 0
230 | Finish Material | AP | 625 | 06/05/18 | 06/19/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 1322.31 | 5966693 | 0 | 0
230 | Finish Material | AP | 646 | 05/30/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 217.29 | S011903109.001 | 0 | 0
230 | Finish Material | AP | 647 | 06/04/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 1618.01 | S011697349.001 | 0 | 0
230 | Finish Material | AP | 648 | 06/06/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 59.33 | S011697528.002 | 0 | 0
230 | Finish Material | AP | 649 | 06/06/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 501.02 | S011939358.001 | 0 | 0
230 | Finish Material | AP | 650 | 06/06/18 | 06/19/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 84.08 | S011960461.001 | 0 | 0
230 | Finish Material | AP | 655 | 06/18/18 | 06/20/18 | 2047FE | Ferguson Enterprises, Inc. $Green Lake |  |  |  |  | 8.78 | 6299107 | 0 | 0
230 | Finish Material | GL | 767 | 06/22/18 | 06/22/18 | Mat | Req 3748 |  |  |  |  | -466.2 |  | 0 | 0
230 | Finish Material | AP | 945 | 06/11/18 | 06/27/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 73.71 | S011953196.001 | 0 | 0
230 | Finish Material | AP | 946 | 06/12/18 | 06/27/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 283.72 | S011974506.001 | 0 | 0
230 | Finish Material | AP | 947 | 06/13/18 | 06/27/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 110.05 | S011972659.001 | 0 | 0
230 | Finish Material | AP | 948 | 06/19/18 | 06/27/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | -129.99 | S011962056.001 | 0 | 0
230 | Finish Material | GL | 88 | 07/06/18 | 07/06/18 | Mat | Req 4442 |  |  |  |  | 13.3 |  | 0 | 0
230 | Finish Material | AP | 234 | 05/30/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 15.04 | 053018 | 0 | 0
230 | Finish Material | AP | 244 | 06/25/18 | 07/10/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 193.22 | S012019676.001 | 0 | 0
230 | Finish Material | AP | 669 | 06/29/18 | 07/16/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | -501.02 | S011939358.002 | 0 | 0
230 | Finish Material | AP | 670 | 06/29/18 | 07/16/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 293.73 | S011939358.003 | 0 | 0
230 | Finish Material | GL | 317 | 08/10/18 | 08/10/18 | Mat | Req 4593 |  |  |  |  | 74 |  | 0 | 0
230 | Finish Material | AP | 911 | 08/14/18 | 08/24/18 | 1231KS | Keller Supply Company |  |  |  |  | 290.43 | S012170364.001 | 0 | 0
230 | Finish Material | GL | 947 | 08/28/18 | 08/28/18 | Mat | Req 4650 |  |  |  |  | 30.16 |  | 0 | 0
230 | Finish Material | AP | 1141 | 07/31/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 7.93 | 073118A2 | 0 | 0
230 | Finish Material | AP | 1086 | 08/08/18 | 08/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 43.4 | 4255643-00 | 0 | 0
230 | Finish Material | AP | 218 | 08/21/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | -183.22 | S012198026.001 | 0 | 0
230 | Finish Material | AP | 366 | 08/22/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 29.36 | 4256332-00 | 0 | 0
242 | Mech Room Material | AP | 367 | 02/06/18 | 02/25/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 4412.83 | 4247316-00 | 0 | 0
242 | Mech Room Material | AP | 544 | 02/06/18 | 02/25/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | -4412.83 | 4247316-00A | 0 | 0
242 | Mech Room Material | AP | 536 | 04/13/18 | 04/20/18 | 2047KS | Keller Supply Co. $Green Lake |  |  |  |  | 122.48 | S011781969.01 | 0 | 0
242 | Mech Room Material | AP | 341 | 04/20/18 | 05/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 189.09 | S011804734.001 | 0 | 0
242 | Mech Room Material | GL | 536 | 05/21/18 | 05/21/18 | 2047KS | Inv S011781969.001 |  |  |  |  | -122.48 |  | 0 | 0
242 | Mech Room Material | GL | 537 | 05/21/18 | 05/21/18 | 1231KS | S011804734.001 |  |  |  |  | -189.09 |  | 0 | 0
600 | Subcontractor | AP | 538 | 05/08/18 | 05/21/18 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 155 | 18050806 | 0 | 0
601 | Engineering/Plans | AP | 543 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 772.5 | 6739 | 0 | 0
602 | Rental Equipment | AP | 581 | 05/09/18 | 05/22/18 | 2713AR | Ahern Rentals |  |  |  |  | 503.72 | 18970751-2 | 0 | 0
602 | Rental Equipment | AP | 582 | 04/30/18 | 05/22/18 | 2713AR | Ahern Rentals |  |  |  |  | 448.67 | 18950268-1 | 0 | 0
602 | Rental Equipment | AP | 149 | 05/23/18 | 06/04/18 | 1799AW | AllWest Underground, Inc. |  |  |  |  | 796.24 | 74411 | 0 | 0
602 | Rental Equipment | AP | 114 | 06/08/18 | 07/06/18 | 2713AR | Ahern Rentals |  |  |  |  | 360.59 | 18970751-3 | 0 | 0
603 | Permits & Licenses | AP | 161 | 11/20/17 | 12/01/17 | 1234CO | Capital One Credit Card |  |  |  |  | 50 | 112017 | 0 | 0
603 | Permits & Licenses | AP | 811 | 01/31/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 201 | 013118A | 0 | 0
603 | Permits & Licenses | AP | 926 | 03/19/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 201 | 031918 | 0 | 0
603 | Permits & Licenses | AP | 779 | 04/18/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 502.5 | 041818A | 0 | 0
607 | Other Expenses | AP | 810 | 01/31/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 14.71 | 013118 | 0 | 0
607 | Other Expenses | AP | 927 | 03/19/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 12.26 | 031918A | 0 | 0
607 | Other Expenses | AP | 781 | 04/18/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 12.26 | 041818C | 0 | 0
995 | Payroll Burden | PR | 295 | 10/18/17 | 10/20/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/18/17 | 10/20/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 206.23 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 10/18/17 | 10/20/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 114.64 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 10/25/17 | 10/27/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 10/25/17 | 10/27/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 508.69 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 10/25/17 | 10/27/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 11/01/17 | 11/03/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 19.07 |  | 0 | 0
995 | Payroll Burden | PR | 155 | 11/08/17 | 11/10/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 172 | 11/08/17 | 11/10/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 659.93 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 101.12 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 101.12 |  | 0 | 0
995 | Payroll Burden | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 11/15/17 | 11/17/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 11/15/17 | 11/17/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 311 | 11/15/17 | 11/17/17 | HO90 | Howey, Shawn M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 11/15/17 | 11/17/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 321 | 11/15/17 | 11/17/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 11/15/17 | 11/17/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 11/15/17 | 11/17/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 431 | 11/22/17 | 11/22/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 11/22/17 | 11/22/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 11/22/17 | 11/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 11/22/17 | 11/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 345.93 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 11/22/17 | 11/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 474 | 11/22/17 | 11/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 11/29/17 | 12/01/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 11/29/17 | 12/01/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 426.2 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 11/29/17 | 12/01/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 11/29/17 | 12/01/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 261.22 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 11/29/17 | 12/01/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 274.97 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 57.21 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 11/29/17 | 12/01/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 261.22 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 11/29/17 | 12/01/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 247.92 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 12/06/17 | 12/08/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 604.93 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 12/06/17 | 12/08/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 233 | 12/06/17 | 12/08/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 107.11 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 12/06/17 | 12/08/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 406 | 12/13/17 | 12/15/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 424 | 12/13/17 | 12/15/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 12/13/17 | 12/15/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 419.11 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 12/13/17 | 12/15/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 12/13/17 | 12/15/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 442 | 12/13/17 | 12/15/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 448 | 12/13/17 | 12/15/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 449 | 12/13/17 | 12/15/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 12/13/17 | 12/15/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 12/20/17 | 12/22/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 614 | 12/20/17 | 12/22/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 508.69 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 12/20/17 | 12/22/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 129.72 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 628 | 12/20/17 | 12/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 787 | 12/27/17 | 12/29/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 12/27/17 | 12/29/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 12/27/17 | 12/29/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 815 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 819 | 12/27/17 | 12/29/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 823 | 12/27/17 | 12/29/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 828 | 12/27/17 | 12/29/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 829 | 12/27/17 | 12/29/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 830 | 12/27/17 | 12/29/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 845 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 01/03/18 | 01/05/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 01/03/18 | 01/05/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 01/03/18 | 01/05/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 01/03/18 | 01/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 227.52 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 01/03/18 | 01/05/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 295.81 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 01/03/18 | 01/05/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 01/03/18 | 01/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 227.52 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 01/03/18 | 01/05/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 01/03/18 | 01/05/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 01/10/18 | 01/12/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 01/10/18 | 01/12/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 01/10/18 | 01/12/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 01/10/18 | 01/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 01/10/18 | 01/12/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 01/10/18 | 01/12/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 01/10/18 | 01/12/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 01/10/18 | 01/12/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 01/10/18 | 01/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 390 | 01/17/18 | 01/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 396 | 01/17/18 | 01/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 209.33 |  | 0 | 0
995 | Payroll Burden | PR | 402 | 01/17/18 | 01/19/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 414 | 01/17/18 | 01/19/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 405.58 |  | 0 | 0
995 | Payroll Burden | PR | 420 | 01/17/18 | 01/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 196.25 |  | 0 | 0
995 | Payroll Burden | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 428 | 01/17/18 | 01/19/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 429 | 01/17/18 | 01/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 01/17/18 | 01/19/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 01/17/18 | 01/19/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 01/17/18 | 01/19/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -83.16 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 592 | 01/24/18 | 01/26/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 609 | 01/24/18 | 01/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 619 | 01/24/18 | 01/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 627 | 01/24/18 | 01/26/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 628 | 01/24/18 | 01/26/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 633 | 01/24/18 | 01/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 635 | 01/24/18 | 01/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 01/31/18 | 02/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 01/31/18 | 02/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 01/31/18 | 02/02/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 01/31/18 | 02/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 02/07/18 | 02/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 02/07/18 | 02/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 02/07/18 | 02/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 02/07/18 | 02/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 709.6 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 02/14/18 | 02/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 02/14/18 | 02/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 204.01 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 02/14/18 | 02/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 02/14/18 | 02/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | -81.6 |  | 0 | 0
995 | Payroll Burden | PR | 627 | 02/21/18 | 02/23/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 329.96 |  | 0 | 0
995 | Payroll Burden | PR | 645 | 02/21/18 | 02/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 02/21/18 | 02/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 343.71 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 292.71 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -59.87 |  | 0 | 0
995 | Payroll Burden | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 65.86 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 102.45 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 288.72 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 04/18/18 | 04/20/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 271.42 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 219.53 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 04/18/18 | 04/20/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 586.75 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 05/02/18 | 05/04/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 05/02/18 | 05/04/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 05/02/18 | 05/04/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 508.69 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 05/02/18 | 05/04/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -79.83 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 17.96 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 05/09/18 | 05/11/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -99.79 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.94 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 453.7 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | -109.99 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 431.08 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 339.28 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -339.28 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | -109.99 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 371.21 |  | 0 | 0
995 | Payroll Burden | PR | 784 | 05/23/18 | 05/25/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 796 | 05/23/18 | 05/25/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 05/30/18 | 06/01/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 431.08 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 05/30/18 | 06/01/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 05/30/18 | 06/01/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 158.33 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 05/30/18 | 06/01/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 05/30/18 | 06/01/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 315.33 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 11.97 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 109.77 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 06/13/18 | 06/15/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 06/13/18 | 06/15/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 532.2 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 06/13/18 | 06/15/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 06/13/18 | 06/15/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 06/13/18 | 06/15/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 526 | 06/13/18 | 06/15/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 742 | 06/20/18 | 06/22/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 68.3 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 292.71 |  | 0 | 0
995 | Payroll Burden | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 1009 | 06/27/18 | 06/29/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -312.22 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 320 | 07/11/18 | 07/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 07/18/18 | 07/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 824 | 07/25/18 | 07/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 08/01/18 | 08/03/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 08/15/18 | 08/17/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 08/15/18 | 08/17/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 801 | 08/22/18 | 08/24/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 10/18/17 | 10/20/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/18/17 | 10/20/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 35.57 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 10/18/17 | 10/20/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.78 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 10/25/17 | 10/27/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 10/25/17 | 10/27/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 87.75 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 10/25/17 | 10/27/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 10/25/17 | 10/27/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 10/25/17 | 10/27/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 10/25/17 | 10/27/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 11/01/17 | 11/03/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 11/01/17 | 11/03/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 11/01/17 | 11/03/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 11/01/17 | 11/03/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 11/01/17 | 11/03/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 11/01/17 | 11/03/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 3.29 |  | 0 | 0
998 | Payroll Taxes | PR | 155 | 11/08/17 | 11/10/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 172 | 11/08/17 | 11/10/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 113.83 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 17.44 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/08/17 | 11/10/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 190 | 11/08/17 | 11/10/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 17.44 |  | 0 | 0
998 | Payroll Taxes | PR | 196 | 11/08/17 | 11/10/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 198 | 11/08/17 | 11/10/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 11/15/17 | 11/17/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 11/15/17 | 11/17/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 311 | 11/15/17 | 11/17/17 | HO90 | Howey, Shawn M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 11/15/17 | 11/17/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 321 | 11/15/17 | 11/17/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 11/15/17 | 11/17/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 11/15/17 | 11/17/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 431 | 11/22/17 | 11/22/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 11/22/17 | 11/22/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 11/22/17 | 11/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 11/22/17 | 11/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 59.67 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 11/22/17 | 11/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 474 | 11/22/17 | 11/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 11/29/17 | 12/01/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 11/29/17 | 12/01/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 73.52 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 11/29/17 | 12/01/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 11/29/17 | 12/01/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 45.06 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 11/29/17 | 12/01/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 47.43 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 9.87 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 11/29/17 | 12/01/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 45.06 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 11/29/17 | 12/01/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 42.76 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 12/06/17 | 12/08/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 12/06/17 | 12/08/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 104.35 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 12/06/17 | 12/08/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 233 | 12/06/17 | 12/08/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 12/06/17 | 12/08/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 18.47 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 12/06/17 | 12/08/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 250 | 12/06/17 | 12/08/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 12/06/17 | 12/08/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 406 | 12/13/17 | 12/15/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 424 | 12/13/17 | 12/15/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 12/13/17 | 12/15/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 72.29 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 12/13/17 | 12/15/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 12/13/17 | 12/15/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 442 | 12/13/17 | 12/15/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 448 | 12/13/17 | 12/15/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 449 | 12/13/17 | 12/15/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 12/13/17 | 12/15/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 12/20/17 | 12/22/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 614 | 12/20/17 | 12/22/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 87.75 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 12/20/17 | 12/22/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.38 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 12/20/17 | 12/22/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 628 | 12/20/17 | 12/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 12/20/17 | 12/22/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 12/20/17 | 12/22/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 12/20/17 | 12/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 12/20/17 | 12/22/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 787 | 12/27/17 | 12/29/17 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 12/27/17 | 12/29/17 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 12/27/17 | 12/29/17 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 815 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 819 | 12/27/17 | 12/29/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 823 | 12/27/17 | 12/29/17 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 828 | 12/27/17 | 12/29/17 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 829 | 12/27/17 | 12/29/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 830 | 12/27/17 | 12/29/17 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 845 | 12/27/17 | 12/29/17 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 846 | 12/27/17 | 12/29/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 01/03/18 | 01/05/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 01/03/18 | 01/05/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 01/03/18 | 01/05/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 01/03/18 | 01/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 39.24 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 01/03/18 | 01/05/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 51.03 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 01/03/18 | 01/05/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 01/03/18 | 01/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 39.24 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 01/03/18 | 01/05/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 01/03/18 | 01/05/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 01/03/18 | 01/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 01/10/18 | 01/12/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 01/10/18 | 01/12/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 01/10/18 | 01/12/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 01/10/18 | 01/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 01/10/18 | 01/12/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 01/10/18 | 01/12/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 01/10/18 | 01/12/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 01/10/18 | 01/12/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 01/10/18 | 01/12/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 01/10/18 | 01/12/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 390 | 01/17/18 | 01/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 396 | 01/17/18 | 01/19/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 36.11 |  | 0 | 0
998 | Payroll Taxes | PR | 402 | 01/17/18 | 01/19/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 414 | 01/17/18 | 01/19/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 69.96 |  | 0 | 0
998 | Payroll Taxes | PR | 420 | 01/17/18 | 01/19/18 | HO18 | Hoeg, Xavier A | 0 | 0 | 0 | 0 | 33.85 |  | 0 | 0
998 | Payroll Taxes | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 424 | 01/17/18 | 01/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 428 | 01/17/18 | 01/19/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 429 | 01/17/18 | 01/19/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 01/17/18 | 01/19/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 01/17/18 | 01/19/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 01/17/18 | 01/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 01/17/18 | 01/19/18 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 01/17/18 | 01/19/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 592 | 01/24/18 | 01/26/18 | BE45 | Belcher, Jacob T | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 609 | 01/24/18 | 01/26/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 619 | 01/24/18 | 01/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 627 | 01/24/18 | 01/26/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 628 | 01/24/18 | 01/26/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 633 | 01/24/18 | 01/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 635 | 01/24/18 | 01/26/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 01/31/18 | 02/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 01/31/18 | 02/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 01/31/18 | 02/02/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 01/31/18 | 02/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 02/07/18 | 02/09/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 02/07/18 | 02/09/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 02/07/18 | 02/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 02/07/18 | 02/09/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 122.4 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/07/18 | 02/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 02/14/18 | 02/16/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 02/14/18 | 02/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 35.19 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 02/14/18 | 02/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 02/14/18 | 02/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | -14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 627 | 02/21/18 | 02/23/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 56.92 |  | 0 | 0
998 | Payroll Taxes | PR | 645 | 02/21/18 | 02/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 02/21/18 | 02/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 02/28/18 | 03/02/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 59.29 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 02/28/18 | 03/02/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 50.49 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 02/28/18 | 03/02/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 149 | 03/07/18 | 03/09/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 03/14/18 | 03/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 359 | 03/14/18 | 03/16/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 369 | 03/14/18 | 03/16/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 558 | 03/21/18 | 03/23/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 568 | 03/21/18 | 03/23/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 11.36 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 17.67 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 04/11/18 | 04/13/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 04/11/18 | 04/13/18 | LU09 | Lucas Tzintzun, Rafael | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 04/11/18 | 04/13/18 | ME52 | Mendoza, Edgar E | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 04/11/18 | 04/13/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 49.8 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 04/18/18 | 04/20/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 04/18/18 | 04/20/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 46.82 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 04/18/18 | 04/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 37.87 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 04/18/18 | 04/20/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 101.21 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 04/25/18 | 04/27/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 04/25/18 | 04/27/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 644 | 04/25/18 | 04/27/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 04/25/18 | 04/27/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 666 | 04/25/18 | 04/27/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 05/02/18 | 05/04/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 05/02/18 | 05/04/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 05/02/18 | 05/04/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 87.75 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 05/02/18 | 05/04/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 05/02/18 | 05/04/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 3.1 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 05/09/18 | 05/11/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 296 | 05/09/18 | 05/11/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.65 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 78.26 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 05/23/18 | 05/25/18 | GA70 | Garcia, Jordan X | 0 | 0 | 0 | 0 | -18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 74.36 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 05/23/18 | 05/25/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 58.52 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -58.52 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | -18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 05/23/18 | 05/25/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 64.03 |  | 0 | 0
998 | Payroll Taxes | PR | 784 | 05/23/18 | 05/25/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 796 | 05/23/18 | 05/25/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 05/30/18 | 06/01/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 74.36 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 05/30/18 | 06/01/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 05/30/18 | 06/01/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 05/30/18 | 06/01/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 05/30/18 | 06/01/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 27.31 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 05/30/18 | 06/01/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 05/30/18 | 06/01/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 54.39 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 2.07 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 06/06/18 | 06/08/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 18.93 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 06/06/18 | 06/08/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 06/13/18 | 06/15/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 06/13/18 | 06/15/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 06/13/18 | 06/15/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 06/13/18 | 06/15/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 06/13/18 | 06/15/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 526 | 06/13/18 | 06/15/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 742 | 06/20/18 | 06/22/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.78 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 50.49 |  | 0 | 0
998 | Payroll Taxes | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 1009 | 06/27/18 | 06/29/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 1023 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 320 | 07/11/18 | 07/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 07/18/18 | 07/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 824 | 07/25/18 | 07/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 08/01/18 | 08/03/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 08/15/18 | 08/17/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 08/15/18 | 08/17/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 801 | 08/22/18 | 08/24/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
999 | Sales | AR | 361 | 10/20/17 | 10/20/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -37950 | 036965 | 0 | -1897.5
999 | Sales | AR | 361 | 10/20/17 | 10/20/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -13775 | 036965 | 0 | -688.75
999 | Sales | AR | 361 | 10/20/17 | 10/20/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -13775 | 036965 | 0 | -688.75
999 | Sales | AR | 361 | 10/20/17 | 10/20/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -38250 | 036965 | 0 | -1912.5
999 | Sales | AR | 376 | 11/17/17 | 11/17/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -60720 | 036982 | 0 | -3036
999 | Sales | AR | 376 | 11/17/17 | 11/17/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -60720 | 036982 | 0 | -3036
999 | Sales | AR | 376 | 11/17/17 | 11/17/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -22770 | 036982 | 0 | -1138.5
999 | Sales | AR | 376 | 11/17/17 | 11/17/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -10200 | 036982 | 0 | -510
999 | Sales | AR | 376 | 11/17/17 | 11/17/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -11050 | 036982 | 0 | -552.5
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -15180 | 036994 | 0 | -759
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -15180 | 036994 | 0 | -759
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -15180 | 036994 | 0 | -759
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -725 | 036994 | 0 | -36.25
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -725 | 036994 | 0 | -36.25
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -2550 | 036994 | 0 | -127.5
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -5950 | 036994 | 0 | -297.5
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -5803 | 036994 | 0 | -290.15
999 | Sales | AR | 538 | 12/15/17 | 12/15/17 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -9168 | 036994 | 0 | -458.4
999 | Sales | AR | 466 | 01/19/18 | 01/19/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -4800 | 037001 | 0 | -240
999 | Sales | AR | 466 | 01/19/18 | 01/19/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -4800 | 037001 | 0 | -240
999 | Sales | AR | 466 | 01/19/18 | 01/19/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -4800 | 037001 | 0 | -240
999 | Sales | AR | 466 | 01/19/18 | 01/19/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -26300 | 037001 | 0 | -1315
999 | Sales | AR | 583 | 02/20/18 | 02/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -6900 | 037025 | 0 | -345
999 | Sales | AR | 583 | 02/20/18 | 02/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -800 | 037025 | 0 | -40
999 | Sales | AR | 583 | 02/20/18 | 02/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -573 | 037025 | 0 | -28.65
999 | Sales | AR | 444 | 03/20/18 | 03/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -24220 | 037049 | 0 | -1211
999 | Sales | AR | 444 | 03/20/18 | 03/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -11461 | 037049 | 0 | -573.05
999 | Sales | AR | 548 | 04/20/18 | 04/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -29500 | 037069 | 0 | -1475
999 | Sales | AR | 548 | 04/20/18 | 04/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -10380 | 037069 | 0 | -519
999 | Sales | AR | 548 | 04/20/18 | 04/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -6500 | 037069 | 0 | -325
999 | Sales | AR | 548 | 04/20/18 | 04/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -1613 | 037069 | 0 | -80.65
999 | Sales | AR | 510 | 05/18/18 | 05/18/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -7900 | 037088 | 0 | -395
999 | Sales | AR | 510 | 05/18/18 | 05/18/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -34600 | 037088 | 0 | -1730
999 | Sales | AR | 510 | 05/18/18 | 05/18/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -5100 | 037088 | 0 | -255
999 | Sales | AR | 510 | 05/18/18 | 05/18/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -1287 | 037088 | 0 | -64.35
999 | Sales | AR | 510 | 05/18/18 | 05/18/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -3175 | 037088 | 0 | -158.75
999 | Sales | AR | 674 | 06/20/18 | 06/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -17300 | 037113 | 0 | -865
999 | Sales | AR | 674 | 06/20/18 | 06/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -9699 | 037113 | 0 | -484.95
999 | Sales | AR | 674 | 06/20/18 | 06/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -1432 | 037113 | 0 | -71.6
999 | Sales | AR | 526 | 07/20/18 | 07/20/18 | 2047GR | GRE Construction LLC $Green Lake |  |  |  |  | -378 | 037138 | 0 | -18.9

## Crew Roster
CREW ROSTER — 33 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Mendoza Morales, Jesus A | 40 | 0 | 0 | 552 | 0 | 13.8
APPRENTICE/HELPER | Hoeg, Xavier A | 213.5 | 0 | 0 | 3202.5 | 0 | 15
APPRENTICE/HELPER | Chevez, Herson G | 8 | 0 | 0 | 120 | 0 | 15
APPRENTICE/HELPER | Belcher, Jacob T | 500.5 | 8 | 0 | 8008 | 192 | 16
APPRENTICE/HELPER | Lucas Tzintzun, Rafael | 16 | 0 | 0 | 256 | 0 | 16
APPRENTICE/HELPER | Caro, Camilo | 93.5 | 4 | 0 | 1496 | 96 | 16
APPRENTICE/HELPER | Olea Galeana, Maricela | 45.5 | 0 | 0 | 728 | 0 | 16
APPRENTICE/HELPER | Rivera Oseguera, Kate Y | 22.5 | 0 | 0 | 360 | 0 | 16
APPRENTICE/HELPER | Sanchez Olea, Itzel G | 5.5 | 0 | 0 | 88 | 0 | 16
APPRENTICE/HELPER | Nelson, Charles E | 19 | 0 | 0 | 304 | 0 | 16
APPRENTICE/HELPER | Ramos Melendez, Carlos M | 221 | 14 | 0 | 3978 | 378 | 18
APPRENTICE/HELPER | Yohannes Jr., Samson | 175 | 0 | 0 | 3150 | 0 | 18
APPRENTICE/HELPER | Gomez Reyes, Edith N | 123.5 | 23 | 0 | 2239 | 621 | 18.1296
APPRENTICE/HELPER | Jimenez Alvarenga, Gerson M | 498 | 37 | 0 | 9462 | 1054.5 | 19
APPRENTICE/HELPER | Ramos Herrera, Franklin J | 514 | 37 | 0 | 9766 | 1054.5 | 19
APPRENTICE/HELPER | Howey, Shawn M | 40 | 0 | 0 | 760 | 0 | 19
APPRENTICE/HELPER | Gerard, Mitchell J | 44 | 0 | 0 | 0 | 0 | 0
JOURNEYMAN | Mendoza, Edgar E | 678 | 37 | 0 | 13560 | 1110 | 20
JOURNEYMAN | Lovo, German G | 193 | 7 | 0 | 4439 | 241.5 | 23
JOURNEYMAN | Eliassen, Cory H | 8 | 0 | 0 | 184 | 0 | 23
JOURNEYMAN | Amaya Gonzalez, Edilberto A | 8 | 0 | 0 | 208 | 0 | 26
JOURNEYMAN | Kinssies, Jr, John E | 5 | 0 | 0 | 130 | 0 | 26
JOURNEYMAN | Hubbard, Robert W | 152 | 0 | 0 | 4230 | 0 | 27.8289
JOURNEYMAN | Gerard, Jordan E | 219.5 | 6.5 | 0 | 6148.5 | 263.25 | 28.0114
JOURNEYMAN | McCabe, Thomas C | 205 | 10 | 0 | 5859 | 465 | 28.5805
JOURNEYMAN | Garcia, Jordan X | 706.5 | 0 | 0 | 21405.5 | 0 | 30.2979
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 8 | 0 | 0 | 248 | 0 | 31
LEAD/SUPERVISOR | Reed, Reuben H | 678 | 17.5 | 0 | 27120 | 1050 | 40
LEAD/SUPERVISOR | Sanders, Allen O | 159 | 11 | 0 | 6763 | 693 | 42.5346
LEAD/SUPERVISOR | Quintanilla, Esteban R | 17 | 0 | 0 | 731 | 0 | 43
LEAD/SUPERVISOR | Gerard, Jeffrey S | 105.5 | 0 | 0 | 5039.5 | 0 | 47.7678
LEAD/SUPERVISOR | Donelson, Richard T | 52 | 0 | 0 | 2737.5 | 0 | 52.6442
OT-ONLY | Cruz Gonzalez, Julio C | 0 | 7 | 0 | 0 | 199.5 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2047
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 17 | 2579.5 | 123 | 47865.5 | 15.7017
JOURNEYMAN | 10 | 2183 | 60.5 | 58491.75 | 26.3719
LEAD/SUPERVISOR | 5 | 1011.5 | 28.5 | 44134 | 45.1893
OT-ONLY | 1 | 0 | 7 | 199.5 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 15.1
p25 | 16
p50 | 19
p75 | 28.15
p90 | 42.28
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 24.8134 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 38.2196 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 51.2948 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2047
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 5,993.00 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $92.31 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $25.14 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 3.67x | Throughput ÷ unit cost — productivity signal
Units (residential) | 72 | GRE Greenlake Apartments scope doc: 61 Type B + 11 Type A ADA
Fixtures (estimate) | 751 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 11 | start_date → end_date from GDrive enrichment
Hours per Unit | 83.24 | total_labor_hours ÷ units
Hours per Fixture | 7.98 | total_labor_hours ÷ fixtures
Revenue per Unit | $7,683 | revenue ÷ units
Profit per Unit | $2,596 | net_profit ÷ units
Hours per Month | 545 | total_labor_hours ÷ duration_months
Revenue per Month | $50,290 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 17 VENDORS ($117,192 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Keller Supply Co. $Green Lake | 35554.85 | 27 | 1316.8463 | 30.34% | 0 | 0
2 | Rosen Supply Company, Inc. $Green Lake | 26527.5 | 52 | 510.1442 | 22.64% | 0 | 0
3 | Ferguson Enterprises, Inc. $Green Lake | 22910.38 | 7 | 3272.9114 | 19.55% | 0 | 0
4 | Consolidated Supply Co. $Green Lake | 19553.06 | 19 | 1029.1084 | 16.68% | 0 | 0
5 | Best Bath Systems | 4838.64 | 3 | 1612.88 | 4.129% | 0 | 0
6 | California Hydronics Corp | 1859 | 1 | 1859 | 1.586% | 0 | 0
7 | Consolidated Supply Co. $University | 1385.58 | 1 | 1385.58 | 1.182% | 0 | 0
8 | Ahern Rentals | 1312.98 | 3 | 437.66 | 1.12% | 0 | 0
9 | AllWest Underground, Inc. | 796.24 | 1 | 796.24 | 0.6794% | 0 | 0
10 | Franklin Engineering | 772.5 | 1 | 772.5 | 0.6592% | 0 | 0
11 | Bank of America CC | 534.04 | 3 | 178.0133 | 0.4557% | 0 | 0
12 | Capital One Credit Card | 501.94 | 7 | 71.7057 | 0.4283% | 0 | 0
13 | Keller Supply Company | 296.3 | 3 | 98.7667 | 0.2528% | 0 | 0
14 | R.A. Brown Backflow Testing | 155 | 1 | 155 | 0.1323% | 0 | 0
15 | Ferguson Enterprises, Inc. #3007 | 121.44 | 2 | 60.72 | 0.1036% | 0 | 0
16 | Rosen Supply Kirkland | 72.76 | 2 | 36.38 | 0.06209% | 0 | 0
17 | Consolidated Supply Co. $Park Lane | 0 | 2 | 0 | 0% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2047
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 |  | Rescue scope adjustment | 5803 | Executed 2017-12-13 | Y
2 |  | Additional scope (pre-existing defects) | 9168 | Executed 2017-12-19 | Y
3 | COR #02 Repipe | Repipe Units 210-410 (prior sub defects) | 26300 | Executed 2018-01-25 | Y
4 |  | Minor scope addition | 1287 | Executed 2018-02-07 | Y
5 |  | Minor scope addition | 573 | Executed | Y
6 |  | Scope additions | 11461 | Executed | Y
7 |  | Additional rescue scope | 9675 | Executed | Y
8 |  | Minor scope addition | 1613 | Executed | Y
9 |  | Scope additions | 9699 | Executed | Y
10 | COR #01 OT Premium | Overtime premium reimbursement | 1432 | Executed 2018-08-08 | Y
11 |  | Closeout scope adjustment | 378 | Executed 2018-08-08 | Y
Executed subtotal |  |  | 77389
Budget-transfer total (incl. extras) |  |  | 77389
JDR-implied CO (revenue − original contract) |  |  | 77389
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
COR #01 Overtime Premium | OT premium for accelerated rescue schedule (became CO#10)
COR #01.1 Overtime Premium | OT premium revised submission
COR #02 Repipe Units 210-410 | Repipe units 210-410 due to prior sub defects (became CO#03)
COR #03 Repipe Units 203-303 | Repipe units 203-303 due to prior sub defects
+~72 additional CORs | 75 total CORs on file (dense rescue-project COR traffic)

## Project Team
PROJECT TEAM — 2047
Primary contacts extracted from GRE Greenlake Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Eric Bentler | TBD | 206.972.8145
GC Superintendent | Victor Vo / Brett (per GRE greenlake Brett folder) | TBD | 206.883.7468
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP)
Owner | GRE Green Lake LLC
Inspecting Authority | City of Seattle (DCI)

## Document Pipeline
DOCUMENT PIPELINE — 2047
Quantitative document counts from the GRE Greenlake Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 11 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 75 | Change Orders/COR_s/
Budget transfer entries | 11 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 7 | ASI-RFI/
Submittals | 26 | Submittals/ (PDF count)
POs — placed | 0 | PO_s/1 Placed/
POs — scheduled | 19 | PO_s/2 Scheduled/
POs — completed | 78 | PO_s/3 Completed/
POs — total | 97 | PO_s/ (all three subfolders)
Vendor invoices | 117 | Invoices/
Lien releases | 0 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 3 | Permits/ (Seattle DCI plumbing + gas + backflow permits)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for GRE Greenlake)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2047
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 229050.31 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 117192.21 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 20033.26 | SUM(line_items where source=GL)
direct_cost | 366275.78 | PR + AP + GL
net_profit | 186913.22 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.41405 | PR / abs(revenue)
ap_pct_of_revenue | 0.21185 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.66212 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 5993 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 38.2196 | PR / labor hours
fully_loaded_wage | 51.2948 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 24.8134 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 33 | COUNT DISTINCT(name) source=PR
burden_total | 78359.56 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $15.10 ¦ $16.00 ¦ $19.00 ¦ $28.15 ¦ $42.28 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 133195.02 | SUM(actual) codes 2xx
material_budget_total | 172896 | SUM(current_budget) codes 2xx
material_codes_tracked | 5 | COUNT material codes
material_codes_over_budget | 1 | COUNT where plus_minus > 0
material_codes_under_budget | 4 | COUNT where plus_minus ≤ 0
largest_material_overrun | 211 Garage Material: $11 vs $0 budget (+$11) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $77,180 vs $105,538 budget ($-28,358) | Material code with largest −plus_minus
material_vendor_count | 17 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Keller Supply Co. $Green Lake: $35,555 (30% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 6 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 14 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 120 Roughin Labor: $119,374 vs $105,859 budget (+$13,515) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $77,180 vs $105,538 budget ($-28,358) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 366275.78 | SUM(actual) expense codes
total_budget | 403480.17 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.9078 | JTD / budget
total_over_under_budget | 37204.39 | budget − JTD
labor_unit_cost_per_hr | 25.1445 | Labor JTD / labor hours
revenue_per_labor_hour | 92.3059 | abs(revenue) / labor hours
material_price_variance | 39700.98 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2047
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 33.8% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | YELLOW | 6/20 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $39,701 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | YELLOW | $92.31 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $27,659 | Monitor for collection
Top vendor concentration | GREEN | 30.3% (Keller Supply Co. $Green Lake) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2047
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $553,189, net profit $186,913 at 33.8% margin.
02 | Parsed 1,345 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 33 distinct PR-booked workers over 5,993 labor hours ($38.22/hr PR-src, $51.29/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 120 Roughin Labor: $119,374 vs $105,859 budget (+$13,515).
05 | Largest phase savings: 230 Finish Material: $77,180 vs $105,538 budget ($-28,358).
06 | Material spend $133,195 vs budget $172,896 ($39,701 favorable).
07 | Top AP vendor: Keller Supply Co. $Green Lake: $35,555 (30% of AP); 17 total AP vendors.
08 | Retainage outstanding: $27,659.
09 | 6 of 20 expense phases over budget ($37,204 net vs budget).
10 | Revenue per labor hour $92.31, labor unit cost $25.14 (ratio 3.67x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 21/21 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 2402 | 2402 | 0 | ✓
101 | Takeoff & Purchase Labor | 5375 | 5375 | 0 | ✓
111 | Garage Labor | 0 | 0 | 0 | ✓
120 | Roughin Labor | 119374 | 119374 | 0 | ✓
130 | Finish Labor | 23539.75 | 23539.75 | 0 | ✓
141 | Water Main/Insulation Lab | 0 | 0 | 0 | ✓
142 | Mech Room Labor | 0 | 0 | 0 | ✓
143 | Condensation Drains Labor | 0 | 0 | 0 | ✓
211 | Garage Material | 10.6 | 10.6 | 0 | ✓
212 | Canout Material | 0 | 0 | 0 | ✓
220 | Roughin Material | 56003.99 | 56003.99 | 0 | ✓
230 | Finish Material | 77180.43 | 77180.43 | 0 | ✓
242 | Mech Room Material | 0 | 0 | 0 | ✓
600 | Subcontractor | 155 | 155 | 0 | ✓
601 | Engineering/Plans | 772.5 | 772.5 | 0 | ✓
602 | Rental Equipment | 2109.22 | 2109.22 | 0 | ✓
603 | Permits & Licenses | 954.5 | 954.5 | 0 | ✓
607 | Other Expenses | 39.23 | 39.23 | 0 | ✓
995 | Payroll Burden | 66831.47 | 66831.47 | 0 | ✓
998 | Payroll Taxes | 11528.09 | 11528.09 | 0 | ✓
999 | Sales | -553189 | -553189 | 0 | ✓
RESULT: 21/21 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2047
Worked example of the Reconciliation Protocol running against Job 2047 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 120 Roughin Labor: $119,374 vs $105,859 budget (+$13,515) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $403,480; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $38.22/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $229,050.31 ÷ 5,993.00 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$15.10 ¦ p25=$16.00 ¦ p50=$19.00 ¦ p75=$28.15 ¦ p90=$42.28 (33 workers) | straight_time_rate $24.81 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $25.14/hr ¦ revenue $92.31/hr ¦ ratio 3.67x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2047 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 21/21 codes tie to PDF to the cent | PR $229,050.31 + AP $117,192.21 + GL $20,033.26 = $366,275.78 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2047
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2047 | JDR cover page
job_name | Job Name | GRE Greenlake | JDR cover page
general_contractor | General Contractor | GRE | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 1345 | Length of line_items[]
cost_code_count | Cost Code Count | 21 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -553189 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 553189 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 366275.78 | Sage job_totals_expenses
job_totals_net | Net | -186913.22 | Sage job_totals_net
job_totals_retainage | Retainage | -27659.45 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 229050.31 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 117192.21 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 20033.26 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -553189 | SUM(line_items source=AR)
direct_cost | Direct Cost | 366275.78 | PR + AP + GL
net_profit | Net Profit | 186913.22 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 33.79% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 150690.75 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 133195.02 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 4030.45 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 78359.56 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 5993 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 33 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 24.8134 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 38.2196 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 51.2948 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 78359.56 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 15.1 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 16 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 19 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 28.15 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 42.28 | Percentile across workers
material_spend_total | Material Spend Total | 133195.02 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 172896 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 5 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 1 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 4 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 17 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 39700.98 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 211 Garage Material: $11 vs $0 budget (+$11)
largest_material_savings | Largest Material Savings | 230 Finish Material: $77,180 vs $105,538 budget ($-28,358)
top_vendor_spend | Top Vendor Spend | Keller Supply Co. $Green Lake: $35,555 (30% of AP)
phases_over_budget | Phases Over Budget | 6 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 14 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 120 Roughin Labor: $119,374 vs $105,859 budget (+$13,515)
largest_savings | Largest Savings | 230 Finish Material: $77,180 vs $105,538 budget ($-28,358)
total_jtd_cost | Total JTD Cost | 366275.78 | SUM(actual) expense codes
total_budget | Total Current Budget | 403480.17 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 90.78% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 37204.39 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 25.1445 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 92.3059 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array