## Overview
Job #2047 · GRE Greenlake Apartments (8228 Green Lake Dr N) — PRIOR SUB TAKEOVER
Cortex JCR v2 • GRE (customer 2047SH) • 8228 Green Lake Dr N, Seattle, WA 98103 • Owner: GRE Green Lake LLC
PROJECT OVERVIEW
Project Job # | 2047 |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | GRE Greenlake |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | GRE Greenlake Apartments — 72-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | GRE |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2047SH |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | GRE Green Lake LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Eric Bentler |  | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
GC Superintendent | Victor Vo / Brett (per GRE greenlake Brett folder) |  | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
GC PE | N/A |  | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314) |  | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
Jobsite Location | 8228 Green Lake Dr N, Seattle, WA 98103 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 751 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) |  | GRE Greenlake Apartments project info.pdf
Contract Type | Lump Sum |  | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
Unit Count | 72 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-11 start → 2018-09 (11 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
553189 |  | 186913.22 | 366275.78 | 5993
Original $475,800.00 + ($77,389.00) COs (16.27%) |  | 33.8% margin | 66.2% of revenue | 33 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
72-unit mixed-use (102 Type B + 6 Type A/ADA) at 8228 Green Lake Dr N, Seattle, WA 98103, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: GRE (2047SH); Owner: GRE Green Lake LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: Eric Bentler (GC PM) · Victor Vo / Brett (per GRE greenlake Brett folder) (GC Sup) · TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) (Architect) · Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314) (OWP signatory).
SOURCES
Canonical financial source: 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $553,189.00 / Expenses $366,275.78 / Net $186,913.22 / Retainage $27,659.45
Source breakdown (derived): PR $229,050.31 · AP $117,192.21 · GL $20,033.26
Contract: Lump Sum $475,800.00 → $553,189.00
Change Orders (executed): $77,389.00 net across 11 COs (CO log in enriched meta)
Project Team: Eric Bentler (PM) · Victor Vo / Brett (per GRE greenlake Brett folder) (Sup) · TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) · GRE Green Lake LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | GRE
GC PM | Extracted | Eric Bentler
GC Superintendent | Extracted | Victor Vo / Brett (per GRE greenlake Brett folder)
GC PE | N/A | N/A
Owner | Extracted | GRE Green Lake LLC
Architect | Extracted | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP)
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314)

## Budget vs Actual
Budget vs Actual
All 21 cost codes from JDR. Contract $475,800 → $553,189.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 4200 | 4250 | 2402 | -1848 | 56.52% | 49.5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 8750 | 9000 | 5375 | -3625 | 59.72% | 102 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 88827 | 105859 | 119374 | 13515 | 112.8% | 4762 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 25980 | 26220 | 23539.75 | -2680.25 | 89.78% | 923.5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 0 | 10.6 | 10.6 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 59765 | 67358 | 56003.99 | -11354.01 | 83.14% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 89920 | 105538 | 77180.43 | -28357.57 | 73.13% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 0 | 0 | 0 | 0 |  |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 500 | 155 | -345 | 31% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 1000 | 1000 | 772.5 | -227.5 | 77.25% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 1000 | 2046 | 2109.22 | 63.22 | 103.1% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 0 | 922 | 954.5 | 32.5 | 103.5% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 4000 | 4000 | 39.23 | -3960.77 | 0.9808% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 57937.8 | 65669.48 | 66831.47 | 1161.99 | 101.8% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 9773.41 | 11117.69 | 11528.09 | 410.4 | 103.7% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -475800 | -553189 | -553189 | 0 | 100% |  | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -124146.79 | -149708.83 | -186913.22 | -37204.39 |  | 5837

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,111,120,130,141,142,143 | 150690.75 | 41.14% | 27.24% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 211,212,220,230,242 | 133195.02 | 36.36% | 24.08% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 4030.45 | 1.1% | 0.7286% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 66831.47 | 18.25% | 12.08% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 11528.09 | 3.147% | 2.084% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 366275.78 | 100% | 66.21%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2047KS | Keller Supply Co. $Green Lake | 35554.85 | 27 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2047RS | Rosen Supply Company, Inc. $Green Lake | 26527.5 | 52 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2047FE | Ferguson Enterprises, Inc. $Green Lake | 22910.38 | 7 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2047CS | Consolidated Supply Co. $Green Lake | 19553.06 | 19 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 4838.64 | 3 | Uncategorized | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 1859 | 1 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2037CS | Consolidated Supply Co. $University | 1385.58 | 1 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 1312.98 | 3 | Uncategorized | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 796.24 | 1 | Uncategorized | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 772.5 | 1 | Engineering (601) | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 534.04 | 3 | Credit Card (mixed) | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 501.94 | 7 | Credit Card (mixed) | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 296.3 | 3 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 155 | 1 | Testing subcontractor | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 121.44 | 2 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 72.76 | 2 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2034CS | Consolidated Supply Co. $Park Lane | 0 | 2 | Plumbing / Supplies | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 117192.21 | 135

## Crew & Labor
Crew & Labor — Worker Roster
All 33 unique payroll workers. OWP signatory: Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
ME52 | Mendoza, Edgar E | 715 | 14670 | 20.5175 | 22 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA70 | Garcia, Jordan X | 706.5 | 21405.5 | 30.2979 | 22 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 695.5 | 28170 | 40.5032 | 25 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RA55 | Ramos Herrera, Franklin J | 551 | 10820.5 | 19.6379 | 14 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
JI50 | Jimenez Alvarenga, Gerson M | 535 | 10516.5 | 19.657 | 14 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE45 | Belcher, Jacob T | 508.5 | 8200 | 16.1259 | 15 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RA57 | Ramos Melendez, Carlos M | 235 | 4356 | 18.5362 | 7 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 226 | 6411.75 | 28.3706 | 11 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 215 | 6324 | 29.414 | 8 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO18 | Hoeg, Xavier A | 213.5 | 3202.5 | 15 | 8 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO87 | Lovo, German G | 200 | 4680.5 | 23.4025 | 7 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 175 | 3150 | 18 | 7 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 170 | 7456 | 43.8588 | 20 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 152 | 4230 | 27.8289 | 12 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 146.5 | 2860 | 19.5222 | 10 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 105.5 | 5039.5 | 47.7678 | 35 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA50 | Caro, Camilo | 97.5 | 1592 | 16.3282 | 5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 52 | 2737.5 | 52.6442 | 22 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
OL17 | Olea Galeana, Maricela | 45.5 | 728 | 16 | 4 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 44 | 0 | 0 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME53 | Mendoza Morales, Jesus A | 40 | 552 | 13.8 | 5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HO90 | Howey, Shawn M | 40 | 760 | 19 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI89 | Rivera Oseguera, Kate Y | 22.5 | 360 | 16 | 2 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
NE46 | Nelson, Charles E | 19 | 304 | 16 | 3 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
QU35 | Quintanilla, Esteban R | 17 | 731 | 43 | 2 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LU09 | Lucas Tzintzun, Rafael | 16 | 256 | 16 | 2 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CH20 | Chevez, Herson G | 8 | 120 | 15 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 8 | 184 | 23 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AM03 | Amaya Gonzalez, Edilberto A | 8 | 208 | 26 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 8 | 248 | 31 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 7 | 199.5 | 28.5 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA53 | Sanchez Olea, Itzel G | 5.5 | 88 | 16 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 5 | 130 | 26 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 5993 | 150690.75

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 33 | Unique payroll IDs | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 5993 | Sum of labor codes | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 150690.75 | Sum of labor codes | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 25.1445 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 11.93% | ME52 Mendoza, Edgar E (715 hrs) | Derived
Top 5 Workers Hours Share | 53.45% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 52.6442 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 181.6061 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 8.8182 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 72 units (751 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 92.3059 | USD/hr
Profit per Labor Hour | 31.1886 | USD/hr
Labor Cost per Hour (blended) | 25.1445 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 51.2948 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 4762 | hrs
Finish Hours (code 130) | 923.5 | hrs
Rough-in % of Total Hours | 81.58% | %
Gross Margin | 33.79% | %
Labor % of Revenue | 27.24% | %
Material % of Revenue | 24.08% | %
Direct Cost Ratio | 66.21% | % | All exp/Rev
Revenue per Unit (72) | 7683.1806 | USD | 72 units
Labor Hours per Unit | 83.2361 | hrs
Labor Cost per Unit | 2092.9271 | USD
Material Cost per Unit | 1849.9308 | USD
Direct Cost per Unit | 5087.1636 | USD
Rough-in Hours per Unit | 66.1389 | hrs
Revenue per Fixture | 736.6032 | USD | 751 fixtures
Hours per Fixture | 7.98 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-10-25 | GRE | Lump Sum Subcontract | Closed | GRE Greenlake Apartments plumbing (72 units, 7 stories) — per Div 22 | 475800 | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
CO-NET | — | GRE | Change Orders (executed, 11 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 77389 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 553189

## Billing & SOV
Billing & Schedule of Values
117 invoices to GRE. Retainage $27,659.45.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
466 | 01/19/18 | -40700 | -2035 | 4 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
583 | 02/20/18 | -8273 | -413.65 | 3 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
444 | 03/20/18 | -35681 | -1784.05 | 2 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
548 | 04/20/18 | -47993 | -2399.65 | 4 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
510 | 05/18/18 | -52062 | -2603.1 | 5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
674 | 06/20/18 | -28431 | -1421.55 | 3 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
526 | 07/20/18 | -378 | -18.9 | 1 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
361 | 10/20/17 | -103750 | -5187.5 | 4 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
376 | 11/17/17 | -165460 | -8273 | 5 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
538 | 12/15/17 | -70461 | -3523.05 | 9 | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -553189 | -27659.45

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $186,913.22 on $553,189.00 revenue = 33.8% gross margin. | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $475,800.00 → final $553,189.00 = $+77,389.00 net (16.27%) across 11 executed COs. | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $150,690.75 (27.2% of rev) across 5,993 hrs and 33 workers. Blended wage $25.14/hr. | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$109,384.43 (93% of AP). Top vendor: Keller Supply Co. $Green Lake ($35,554.85). | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $27,659.45 — outstanding as of report date. | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 4,762 hrs (82% of labor hours). | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $119,374.00 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Mendoza, Edgar E = 715 hrs (12% of total). | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | GRE Greenlake Apartments — 72-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 8228 Green Lake Dr N, Seattle, WA 98103. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2047 | Profile | OWP job ID | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | GRE Greenlake Apartments (8228 Green Lake Dr N) — PRIOR SUB TAKEOVER | Profile |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | GRE | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | GRE Green Lake LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) | Profile |  | Verified | GRE Greenlake Apartments project info.pdf
Location | location | 8228 Green Lake Dr N, Seattle, WA 98103 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Rescue/takeover project: OWP replaced prior plumbing subcontractor (Peltram) mid-construction. 72 residential units (61 Type B + 11 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves. CCIP (Contractor-Controlled Insurance Program) project. | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Eric Bentler | Profile |  | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
GC Sup | gc_sup | Victor Vo / Brett (per GRE greenlake Brett folder) | Profile |  | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314) | Profile |  | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-10-25 | Profile |  | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
Work Start | start_date | 2017-11 | Profile |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018-09 | Profile |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 11 | Profile |  | Verified | Derived
Unit Count | unit_count | 72 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 751 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 475800 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 553189 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 77389 | Financial | 11 executed | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 16.27% | Financial |  | Verified | Derived
Revenue | revenue | 553189 | Financial | AR total | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 366275.78 | Financial | JDR Expenses | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 186913.22 | Financial | Rev - Exp | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 33.79% | Financial |  | Verified | Derived
Retainage | retainage | 27659.45 | Financial | JDR AR retainage | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 150690.75 | Labor | Codes 100-151 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 133195.02 | Material | Codes 210-245 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 4030.45 | Financial | Codes 600-607 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 66831.47 | Labor | Code 995 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 11528.09 | Labor | Code 998 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 5993 | Labor | Sum labor codes | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 33 | Labor | Unique PR IDs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 25.1445 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 51.2948 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 4762 | Labor | Code 120 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 923.5 | Labor | Code 130 | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 92.3059 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 31.1886 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 7683.1806 | Productivity | 72 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 5087.1636 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 83.2361 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 736.6032 | Productivity | 751 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 27.24% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 24.08% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 17 | Material |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 10 | Billing |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 11.93% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 53.45% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 21 | Structure |  | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 11 | Documents |  | Verified | CO log
COR Count | cor_count | 75 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 7 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 26 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 97 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2047KS | Keller Supply Co. $Green Lake | 35554.85 | 27 | 30.34% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 2047RS | Rosen Supply Company, Inc. $Green Lake | 26527.5 | 52 | 22.64% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2047FE | Ferguson Enterprises, Inc. $Green Lake | 22910.38 | 7 | 19.55% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 2047CS | Consolidated Supply Co. $Green Lake | 19553.06 | 19 | 16.68% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 7230BB | Best Bath Systems | 4838.64 | 3 | 4.129% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 5560CH | California Hydronics Corp | 1859 | 1 | 1.586% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 2037CS | Consolidated Supply Co. $University | 1385.58 | 1 | 1.182% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 2713AR | Ahern Rentals | 1312.98 | 3 | 1.12% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1799AW | AllWest Underground, Inc. | 796.24 | 1 | 0.6794% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 1625FE | Franklin Engineering | 772.5 | 1 | 0.6592% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1234BA | Bank of America CC | 534.04 | 3 | 0.4557% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1234CO | Capital One Credit Card | 501.94 | 7 | 0.4283% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1231KS | Keller Supply Company | 296.3 | 3 | 0.2528% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1421RA | R.A. Brown Backflow Testing | 155 | 1 | 0.1323% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1175FE | Ferguson Enterprises, Inc. #3007 | 121.44 | 2 | 0.1036% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1380RS | Rosen Supply Kirkland | 72.76 | 2 | 0.06209% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 2034CS | Consolidated Supply Co. $Park Lane | 0 | 2 | 0% | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 117192.21 | 135

## Change Log
Change Log — Master Register
Contract, 11 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-10-25 | Prime subcontract — Lump Sum $475,800.00 | GRE | 475800 | Executed | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/19/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $27,659.45 (outstanding) | GC | 0 | Outstanding | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 77389 | JDR-implied net CO impact | $475,800 → $553,189 (11 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | 5361.75 | Labor variance vs revised budget | 33 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -39700.98 | Material procurement variance | 17 vendors
Overhead | 600,601,602,603,604,607 | -4437.55 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | 1572.39 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | 40184.61
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 11 | 77389 | Aggregate executed COs
Sub (OWP) labor performance | 8 | 5361.75 | Hours + rate vs budget
Sub (OWP) material procurement | 5 | -39700.98 | 17 vendors
OWP burden accrual | 2 | 1572.39 | Payroll burden + tax
OWP overhead | 5 | -4437.55 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 16.27% | ±10% | WATCH | +16.27% net (11 COs)
Labor % of Revenue | 27.24% | <30% | HEALTHY | 27.2%
GL Overhead % of Revenue | 3.621% | <5% | HEALTHY | 3.6%
Vendor Concentration (Top 5) | 93.34% | <95% | HEALTHY | Top 5 = 93% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 33.79% | >30% | HEALTHY | 33.8%
Labor Hrs Total | 5993 | varies | INFO | 5,993 hrs, 33 workers
Worker Concentration (top 1) | 11.93% | <25% | HEALTHY | 11.9% (Mendoza, Edgar E)
Rough-in Labor Share | 81.58% | 40-65% | WATCH | 82%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $27,659.45
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 33.79% | Actual | Job closed | 33.8%
Retainage collection | $27,659.45 | Outstanding | Legacy | Outstanding
Unit-level economics | $7,683/unit rev, $2,596/unit profit | Verified | 72 units | Rescue/takeover project: OWP replaced prior plumbing subcontractor (Peltram) mid-construction. 72 residential units (61 Type B + 11 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves. CCIP (Contractor-Controlled Insurance Program) project.

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2047 | id | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | GRE Greenlake Apartments (8228 Green Lake Dr N) — PRIOR SUB TAKEOVER | text | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | GRE | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | GRE Green Lake LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans (Franklin GRE water mains folder references Franklin Engineering MEP) | text | Benchmark KPIs | Verified | GRE Greenlake Apartments project info.pdf
6 | location | Location | 8228 Green Lake Dr N, Seattle, WA 98103 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Rescue/takeover project: OWP replaced prior plumbing subcontractor (Peltram) mid-construction. 72 residential units (61 Type B + 11 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves. CCIP (Contractor-Controlled Insurance Program) project. | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Eric Bentler | text | Benchmark KPIs | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Victor Vo / Brett (per GRE greenlake Brett folder) | text | Benchmark KPIs | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7926, 10/23/2017; miked@owpllc.net / 425.968.8314) | text | Benchmark KPIs | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-10-25 | date | Benchmark KPIs | Verified | 2047-Shelter Holdings subcontract 7926 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-11 | date | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018-09 | date | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 11 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 72 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 751 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 475800 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 553189 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 77389 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 16.27% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 553189 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 366275.78 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 186913.22 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 33.79% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 27659.45 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 150690.75 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 133195.02 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 4030.45 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 66831.47 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 11528.09 | USD | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 5993 | hours | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 33 | count | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 25.1445 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 51.2948 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 4762 | hours | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 923.5 | hours | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 92.3059 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 31.1886 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 7683.1806 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 5087.1636 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 83.2361 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 736.6032 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 27.24% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 24.08% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 17 | count | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 10 | count | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 11.93% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 53.45% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 21 | count | Benchmark KPIs | Verified | 2047 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 11 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 75 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 7 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 26 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 97 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 553189 | 553189 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 366275.78 | 366275.78 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 186913.22 | 186913.22 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 553189 | 553189 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 5993 | 5993 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 77389 | 77389 | 0 | TIES | 11↔Derived
7 | Worker count | 33 | 33 | 0 | TIES | 5↔1
8 | Cost code count | 21 | 21 | 0 | TIES | 2↔16