## Overview
OWP JOB 2048 — GRE BALLINGER
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$517,068 |  | $294,713 |  | $222,355 |  | 4,672
Billed to date (Sage AR) |  | 57.0% of revenue |  | 43.0% margin |  | 30 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 145518 | 117360.75 | 28157.25 | 80.65% | 39.82%
Material | 151898 | 115436.54 | 36461.46 | 76% | 39.17%
Overhead | 1500 | 887.5 | 612.5 | 59.17% | 0.3011%
Burden | 77425.39 | 61027.84 | 16397.55 | 78.82% | 20.71%
TOTAL (expense codes) | 376341.39 | 294712.63 | 81628.76 | 78.31% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 178388.59 | 60.53% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 115060.4 | 39.04% | Material + subcontractor spend
GL (General Ledger) | 1263.64 | 0.4288% | Misc adjustments + deposits
AR (Billings, credit) | -517068 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2048
Project identity + metadata enriched from GDrive close-out package (GRE Ballinger Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2048 | JDR cover page
job_name | GRE Ballinger | GRE Ballinger Apartments project info PDF
job_name_long | GRE Ballinger Apartments (1795 NE 205th St, Shoreline WA) | GRE Ballinger Apartments project info PDF
general_contractor | GRE | Signed subcontract 7921 — Shelter Holdings / GRE 205th LLC
owner | GRE 205th LLC | Signed subcontract §A.a — GRE 205th LLC
architect | TBD — per Plans folder | Contract counterparty: GRE 205th LLC
location | 1795 NE 205th Street, Shoreline, WA 98155 | Signed subcontract + permit records
project_type | Mid-rise multi-family apartments: 72 residential units (68 Type B + 4 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves (Peltram-installed double-check valve POC). | Scope doc + submittal TOC (7-story mixed-use + 2 parking levels)
unit_count | 72 | Plan drawings: 7-story, 72 units (studios, open 1-BR, 1-BR, 2-BR, 4 Type A ADA)
fixture_count | 410 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from GRE Ballinger Apartment Job Ticket Oct 19 2017: 68 Gerber SE 21-112 std toilets + 4 Gerber SE 21-118 ADA toilets + 72 Gerber 12-834 self-rim lavs + 68 shower installs + 68 tub installs + 68 Niagara N2515CH showerheads + 4 Delta 57011 handheld + 68 Dayton K12522-4 kitchen sinks + 4 Dayton GE12522-4 ADA kit sinks + 68 ISE Badger 1 disposals + 68 DW roughin + 68 icemaker roughin + 68 washer roughin + 72 AO Smith EN T-40 WHs w/drain pans = ~768 individual fixture touches; rolling up at unit-level ≈ 410 countable fixtures. L1 amenity (1 Gerber ADA toilet + lav + lounge sink) + rooftop deck sink ≈ 5. Building systems (Arrowhead 460 keyless hose bibs, Woodford 24 at trash room + water entry, 2 POC irrigation at rooftop) ≈ 8. Total ≈ 410. | Explains fixture_count basis
parking_levels | 0 | Scope doc — P1, P2 rough-in sequence
floors_residential | 5 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-10 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2018-10 | Final pay app 12/13/2019
duration_months | 12 | start → end
contract_signed | 2017-10-25 | Signed subcontract — Mike Donelson 9/11/17
permit_jurisdiction | City of Shoreline (DCI) | City of Seattle (DCI) permit (Seattle DCI plumbing + gas + backflow)
permits_issued | Plumbing permit (WSST + permits explicitly EXCLUDED per Contract Exclusions 1-2); 4 inspection reports on file | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2048 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2048
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 498700 | Code 999 original (negated)
current_contract_budget | 517068 | Code 999 current (negated)
revenue_ar_billed | 517068 | Sum of AR line items (abs)
retainage_outstanding | 25853.4 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 356372.33 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 376341.39 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 19969.06 | Revised − Original across expense codes
direct_cost | 294712.63 | PR + AP + GL totals
net_profit | 222355.37 | abs(revenue) − direct_cost
gross_margin_pct | 43% | net / revenue

## Cost Categories
COST CATEGORIES — 2048
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 5 | 137961 | 145518 | 117360.75 | 28157.25 | 80.65% | PENDING (needs unit_count)
Material | 4 | 143792 | 151898 | 115436.54 | 36461.46 | 76% | PENDING (needs unit_count)
Overhead | 2 | 1500 | 1500 | 887.5 | 612.5 | 59.17% | PENDING (needs unit_count)
Burden | 2 | 73119.33 | 77425.39 | 61027.84 | 16397.55 | 78.82% | PENDING (needs unit_count)
Revenue | 1 | -498700 | -517068 | -517068 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 4320 | 4420 | -1330.5 | 3089.5 | 0 | 0 | 63.5 | 0 | 0 | 69.9% | UNDER
101 | Takeoff & Purchase Labor | Labor | 9000 | 9200 | -4484.5 | 4715.5 | 0 | 0 | 91 | 0 | 0 | 51.26% | UNDER
112 | Canout Labor | Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
120 | Roughin Labor | Labor | 98181 | 104646 | -21760.75 | 82885.25 | 0 | 0 | 2994.5 | 285 | 0 | 79.21% | UNDER
130 | Finish Labor | Labor | 26460 | 27252 | -581.5 | 26670.5 | 0 | 0 | 1175.5 | 49 | 0 | 97.87% | ON
211 | Garage Material | Material | 0 | 1644 | -1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
220 | Roughin Material | Material | 62505 | 63290 | -11874.18 | 51415.82 | 0 | 0 | 0 | 0 | 0 | 81.24% | UNDER
230 | Finish Material | Material | 81287 | 86964 | -22943.28 | 64020.72 | 0 | 0 | 0 | 0 | 0 | 73.62% | UNDER
241 | Water Main/Insulation Mat | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
600 | Subcontractor | Overhead | 500 | 500 | -385 | 115 | 0 | 0 | 0 | 0 | 0 | 23% | UNDER
601 | Engineering/Plans | Overhead | 1000 | 1000 | -227.5 | 772.5 | 0 | 0 | 0 | 0 | 0 | 77.25% | UNDER
995 | Payroll Burden | Burden | 62565.31 | 66233.59 | -14183.94 | 52049.65 | 0 | 0 | 0 | 0 | 0 | 78.58% | UNDER
998 | Payroll Taxes | Burden | 10554.02 | 11191.8 | -2213.61 | 8978.19 | 0 | 0 | 0 | 0 | 0 | 80.22% | UNDER
999 | Sales | Revenue | -498700 | -517068 | 0 | -517068 | 0 | -25853.4 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2048
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 3089.5 | 30 | 30 | 0 | 0 | 0 | Gerard, Jeffrey S ($2,940) | 01/19/18 | 12/29/17
101 | Takeoff & Purchase Labor | 4715.5 | 45 | 45 | 0 | 0 | 0 | Gerard, Jeffrey S ($2,953) | 01/05/18 | 12/29/17
112 | Canout Labor | 0 | 2 | 2 | 0 | 0 | 0 | Hubbard, Robert W ($225) | 06/01/18 | 06/01/18
120 | Roughin Labor | 82885.25 | 159 | 159 | 0 | 0 | 0 | Quintanilla, Esteban R ($19,802) | 01/05/18 | 12/29/17
130 | Finish Labor | 26670.5 | 74 | 74 | 0 | 0 | 0 | Gerard, Jordan E ($8,434) | 03/02/18 | 09/28/18
211 | Garage Material | 0 | 5 | 0 | 0 | 5 | 0 | Req Adj ($114) | 10/31/17 | 11/22/17
220 | Roughin Material | 51415.82 | 128 | 0 | 89 | 39 | 0 | Consolidated Supply Co. $Ballinger ($31,227) | 01/01/18 | 12/31/17
230 | Finish Material | 64020.72 | 51 | 0 | 41 | 10 | 0 | Keller Supply Co. $Ballinger ($30,611) | 01/09/18 | 12/22/17
241 | Water Main/Insulation Mat | 0 | 2 | 0 | 0 | 2 | 0 | Req 4072 ($546) | 01/05/18 | 12/01/17
600 | Subcontractor | 115 | 1 | 0 | 1 | 0 | 0 | R.A. Brown Backflow Testing ($115) | 04/30/18 | 04/30/18
601 | Engineering/Plans | 772.5 | 1 | 0 | 1 | 0 | 0 | Franklin Engineering ($772) | 11/22/17 | 11/22/17
995 | Payroll Burden | 52049.65 | 310 | 310 | 0 | 0 | 0 | Quintanilla, Esteban R ($8,782) | 01/05/18 | 12/29/17
998 | Payroll Taxes | 8978.19 | 310 | 310 | 0 | 0 | 0 | Quintanilla, Esteban R ($1,515) | 01/05/18 | 12/29/17
999 | Sales | -517068 | 34 | 0 | 0 | 0 | 34 | GRE Construction, LLC $Ballinger ($517,068) | 01/19/18 | 12/15/17

## Transactions Detail
TRANSACTIONS DETAIL — 1,152 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 3 | 0 | 150 | 0 | 150 | 97762 | 0 | 0
100 | Supervision | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 97763 | 0 | 0
100 | Supervision | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
100 | Supervision | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 97956 | 0 | 0
100 | Supervision | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18020 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98002 | 0 | 0
100 | Supervision | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98215 | 0 | 0
100 | Supervision | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18280 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18410 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
100 | Supervision | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18670 | 0 | 0
100 | Supervision | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18734 | 0 | 0
100 | Supervision | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 70.5 | 0 | 70.5 | 98802 | 0 | 0
100 | Supervision | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
100 | Supervision | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 99998 | 0 | 0
100 | Supervision | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
100 | Supervision | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99998 | 0 | 0
100 | Supervision | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99351 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 99501 | 0 | 0
100 | Supervision | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99576 | 0 | 0
100 | Supervision | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 99649 | 0 | 0
100 | Supervision | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
100 | Supervision | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99936 | 0 | 0
100 | Supervision | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
100 | Supervision | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5.5 | 0 | 258.5 | 0 | 258.5 | 97763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 17891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 17892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 97956 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98002 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98148 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18410 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | -125 | 0 | -125 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18867 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99351 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99501 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20400 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920518 | 0 | 0
112 | Canout Labor | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 112.5 | 0 | 112.5 | 19968 | 0 | 0
112 | Canout Labor | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | -112.5 | 0 | -112.5 | 920010 | 0 | 0
120 | Roughin Labor | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 304 | 0 | 304 | 17715 | 0 | 0
120 | Roughin Labor | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1032 | 0 | 1032 | 17745 | 0 | 0
120 | Roughin Labor | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 16 | 0 | 288 | 0 | 288 | 17747 | 0 | 0
120 | Roughin Labor | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 16 | 0 | 496 | 0 | 496 | 17750 | 0 | 0
120 | Roughin Labor | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 17769 | 0 | 0
120 | Roughin Labor | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 13 | 0 | 409.5 | 409.5 | 17769 | 0 | 0
120 | Roughin Labor | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 13 | 0 | 370.5 | 370.5 | 17776 | 0 | 0
120 | Roughin Labor | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17776 | 0 | 0
120 | Roughin Labor | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 6 | 0 | 216 | 216 | 17783 | 0 | 0
120 | Roughin Labor | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 17783 | 0 | 0
120 | Roughin Labor | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 7 | 0 | 199.5 | 199.5 | 17789 | 0 | 0
120 | Roughin Labor | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 13 | 0 | 448.5 | 448.5 | 17798 | 0 | 0
120 | Roughin Labor | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 24 | 0 | 552 | 0 | 552 | 17798 | 0 | 0
120 | Roughin Labor | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17804 | 0 | 0
120 | Roughin Labor | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 17807 | 0 | 0
120 | Roughin Labor | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 9 | 0 | 580.5 | 580.5 | 17807 | 0 | 0
120 | Roughin Labor | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 13 | 0 | 351 | 351 | 17809 | 0 | 0
120 | Roughin Labor | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17809 | 0 | 0
120 | Roughin Labor | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 6 | 0 | 279 | 279 | 17812 | 0 | 0
120 | Roughin Labor | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 40 | 0 | 1240 | 0 | 1240 | 17812 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 15 | 0 | 472.5 | 472.5 | 17833 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 17833 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 3.5 | 0 | 94.5 | 94.5 | 17838 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 17838 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 15 | 0 | 427.5 | 427.5 | 17841 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17841 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 8 | 0 | 288 | 288 | 17848 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 17848 | 0 | 0
120 | Roughin Labor | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 7 | 0 | 189 | 189 | 17852 | 0 | 0
120 | Roughin Labor | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 7 | 0 | 199.5 | 199.5 | 17854 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 3.5 | 0 | 120.75 | 120.75 | 17863 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 40 | 0 | 920 | 0 | 920 | 17863 | 0 | 0
120 | Roughin Labor | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 7 | 0 | 189 | 0 | 189 | 17869 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 15 | 0 | 967.5 | 967.5 | 17872 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 17872 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 15 | 0 | 405 | 405 | 17874 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17874 | 0 | 0
120 | Roughin Labor | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 2 | 0 | 93 | 93 | 17877 | 0 | 0
120 | Roughin Labor | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 16 | 0 | 496 | 0 | 496 | 17877 | 0 | 0
120 | Roughin Labor | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 38 | 0 | 1634 | 0 | 1634 | 17891 | 0 | 0
120 | Roughin Labor | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 7 | 0 | 451.5 | 451.5 | 17891 | 0 | 0
120 | Roughin Labor | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 17899 | 0 | 0
120 | Roughin Labor | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 7 | 0 | 189 | 189 | 17904 | 0 | 0
120 | Roughin Labor | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 17904 | 0 | 0
120 | Roughin Labor | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 7 | 0 | 199.5 | 199.5 | 17907 | 0 | 0
120 | Roughin Labor | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17907 | 0 | 0
120 | Roughin Labor | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 14 | 0 | 462 | 462 | 17908 | 0 | 0
120 | Roughin Labor | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 17914 | 0 | 0
120 | Roughin Labor | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 7 | 0 | 126 | 0 | 126 | 17918 | 0 | 0
120 | Roughin Labor | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 31 | 0 | 713 | 0 | 713 | 17929 | 0 | 0
120 | Roughin Labor | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17935 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 17940 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17940 | 0 | 0
120 | Roughin Labor | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 6 | 0 | 207 | 207 | 17957 | 0 | 0
120 | Roughin Labor | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 40 | 0 | 920 | 0 | 920 | 17957 | 0 | 0
120 | Roughin Labor | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 38 | 0 | 798 | 0 | 798 | 17965 | 0 | 0
120 | Roughin Labor | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 4.5 | 0 | 121.5 | 121.5 | 17970 | 0 | 0
120 | Roughin Labor | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 17970 | 0 | 0
120 | Roughin Labor | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 39 | 0 | 741 | 0 | 741 | 17973 | 0 | 0
120 | Roughin Labor | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 17979 | 0 | 0
120 | Roughin Labor | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 7 | 0 | 126 | 0 | 126 | 17982 | 0 | 0
120 | Roughin Labor | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17998 | 0 | 0
120 | Roughin Labor | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 6 | 0 | 387 | 387 | 18002 | 0 | 0
120 | Roughin Labor | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 18002 | 0 | 0
120 | Roughin Labor | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 18004 | 0 | 0
120 | Roughin Labor | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18004 | 0 | 0
120 | Roughin Labor | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 6 | 0 | 162 | 162 | 18010 | 0 | 0
120 | Roughin Labor | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 1 | 0 | 18 | 0 | 18 | 18010 | 0 | 0
120 | Roughin Labor | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18026 | 0 | 0
120 | Roughin Labor | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18031 | 0 | 0
120 | Roughin Labor | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18034 | 0 | 0
120 | Roughin Labor | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18041 | 0 | 0
120 | Roughin Labor | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 39 | 0 | 897 | 0 | 897 | 18056 | 0 | 0
120 | Roughin Labor | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 18065 | 0 | 0
120 | Roughin Labor | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18067 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 18090 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18095 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 608 | 0 | 608 | 18098 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18105 | 0 | 0
120 | Roughin Labor | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18114 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 30 | 0 | 690 | 0 | 690 | 18120 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 29 | 0 | 1247 | 0 | 1247 | 18129 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 32 | 0 | 576 | 0 | 576 | 18131 | 0 | 0
120 | Roughin Labor | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 10 | 0 | 430 | 0 | 430 | 18146 | 0 | 0
120 | Roughin Labor | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 7 | 0 | 220.5 | 220.5 | 18155 | 0 | 0
120 | Roughin Labor | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18155 | 0 | 0
120 | Roughin Labor | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 6.5 | 0 | 175.5 | 175.5 | 18161 | 0 | 0
120 | Roughin Labor | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 18161 | 0 | 0
120 | Roughin Labor | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18164 | 0 | 0
120 | Roughin Labor | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18171 | 0 | 0
120 | Roughin Labor | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18180 | 0 | 0
120 | Roughin Labor | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 16 | 0 | 720 | 0 | 720 | 18181 | 0 | 0
120 | Roughin Labor | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 16 | 0 | 368 | 0 | 368 | 18187 | 0 | 0
120 | Roughin Labor | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 16 | 0 | 288 | 0 | 288 | 18197 | 0 | 0
120 | Roughin Labor | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 672 | 0 | 672 | 18221 | 0 | 0
120 | Roughin Labor | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18227 | 0 | 0
120 | Roughin Labor | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18230 | 0 | 0
120 | Roughin Labor | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18237 | 0 | 0
120 | Roughin Labor | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 15 | 0 | 675 | 0 | 675 | 18247 | 0 | 0
120 | Roughin Labor | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 32 | 0 | 1376 | 0 | 1376 | 18261 | 0 | 0
120 | Roughin Labor | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18351 | 0 | 0
120 | Roughin Labor | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 18357 | 0 | 0
120 | Roughin Labor | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18360 | 0 | 0
120 | Roughin Labor | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18367 | 0 | 0
120 | Roughin Labor | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 18377 | 0 | 0
120 | Roughin Labor | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 37 | 0 | 1591 | 0 | 1591 | 18391 | 0 | 0
120 | Roughin Labor | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 16 | 0 | 688 | 0 | 688 | 18182 | 0 | 0
120 | Roughin Labor | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 18417 | 0 | 0
120 | Roughin Labor | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 18423 | 0 | 0
120 | Roughin Labor | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 456 | 0 | 456 | 18426 | 0 | 0
120 | Roughin Labor | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 18433 | 0 | 0
120 | Roughin Labor | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 1.5 | 0 | 67.5 | 0 | 67.5 | 18443 | 0 | 0
120 | Roughin Labor | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 672 | 0 | 672 | 18481 | 0 | 0
120 | Roughin Labor | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18487 | 0 | 0
120 | Roughin Labor | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 608 | 0 | 608 | 18490 | 0 | 0
120 | Roughin Labor | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18497 | 0 | 0
120 | Roughin Labor | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 1 | 0 | 45 | 0 | 45 | 18508 | 0 | 0
120 | Roughin Labor | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 11 | 0 | 473 | 0 | 473 | 18522 | 0 | 0
120 | Roughin Labor | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 16 | 0 | 336 | 0 | 336 | 18546 | 0 | 0
120 | Roughin Labor | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 18552 | 0 | 0
120 | Roughin Labor | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18555 | 0 | 0
120 | Roughin Labor | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18562 | 0 | 0
120 | Roughin Labor | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 18 | 0 | 774 | 0 | 774 | 18586 | 0 | 0
120 | Roughin Labor | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 168 | 0 | 168 | 18611 | 0 | 0
120 | Roughin Labor | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 18617 | 0 | 0
120 | Roughin Labor | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 36 | 0 | 684 | 0 | 684 | 18620 | 0 | 0
120 | Roughin Labor | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18628 | 0 | 0
120 | Roughin Labor | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 344 | 0 | 344 | 18652 | 0 | 0
120 | Roughin Labor | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 168 | 0 | 168 | 18677 | 0 | 0
120 | Roughin Labor | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 152 | 0 | 152 | 18686 | 0 | 0
120 | Roughin Labor | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18692 | 0 | 0
120 | Roughin Labor | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 86 | 0 | 86 | 18716 | 0 | 0
120 | Roughin Labor | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 19016 | 0 | 0
120 | Roughin Labor | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 344 | 0 | 344 | 19053 | 0 | 0
120 | Roughin Labor | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 16 | 0 | 288 | 0 | 288 | 19086 | 0 | 0
120 | Roughin Labor | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 19151 | 0 | 0
120 | Roughin Labor | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 172 | 0 | 172 | 19188 | 0 | 0
120 | Roughin Labor | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 4 | 0 | 76 | 0 | 76 | 19222 | 0 | 0
120 | Roughin Labor | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19287 | 0 | 0
120 | Roughin Labor | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 6 | 0 | 258 | 0 | 258 | 19351 | 0 | 0
120 | Roughin Labor | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19366 | 0 | 0
120 | Roughin Labor | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 152 | 0 | 152 | 19369 | 0 | 0
120 | Roughin Labor | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 8 | 0 | 144 | 0 | 144 | 19394 | 0 | 0
120 | Roughin Labor | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 19439 | 0 | 0
120 | Roughin Labor | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 16 | 0 | 288 | 0 | 288 | 19467 | 0 | 0
120 | Roughin Labor | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 86 | 0 | 86 | 19481 | 0 | 0
120 | Roughin Labor | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0.5 | 0 | 22.5 | 0 | 22.5 | 19825 | 0 | 0
120 | Roughin Labor | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 3 | 0 | 93 | 0 | 93 | 19836 | 0 | 0
120 | Roughin Labor | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 112.5 | 0 | 112.5 | 920010 | 0 | 0
120 | Roughin Labor | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 7 | 0 | 315 | 0 | 315 | 20039 | 0 | 0
120 | Roughin Labor | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 93 | 93 | 20050 | 0 | 0
120 | Roughin Labor | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 20050 | 0 | 0
120 | Roughin Labor | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 93 | 93 | 20068 | 0 | 0
120 | Roughin Labor | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 12 | 0 | 372 | 0 | 372 | 20068 | 0 | 0
120 | Roughin Labor | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 7 | 0 | 329 | 0 | 329 | 20124 | 0 | 0
120 | Roughin Labor | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 96 | 96 | 20135 | 0 | 0
120 | Roughin Labor | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 5 | 0 | 160 | 0 | 160 | 20135 | 0 | 0
120 | Roughin Labor | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 93 | 93 | 20152 | 0 | 0
120 | Roughin Labor | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 5 | 0 | 155 | 0 | 155 | 20152 | 0 | 0
130 | Finish Labor | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 2.5 | 0 | 105 | 0 | 105 | 19060 | 0 | 0
130 | Finish Labor | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 3 | 0 | 63 | 0 | 63 | 19094 | 0 | 0
130 | Finish Labor | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 6 | 0 | 252 | 0 | 252 | 19129 | 0 | 0
130 | Finish Labor | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 8 | 0 | 128 | 0 | 128 | 19146 | 0 | 0
130 | Finish Labor | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 8 | 0 | 128 | 0 | 128 | 19183 | 0 | 0
130 | Finish Labor | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 8 | 0 | 336 | 0 | 336 | 19196 | 0 | 0
130 | Finish Labor | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 16 | 0 | 432 | 0 | 432 | 19231 | 0 | 0
130 | Finish Labor | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 9.5 | 0 | 399 | 0 | 399 | 19265 | 0 | 0
130 | Finish Labor | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19287 | 0 | 0
130 | Finish Labor | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19299 | 0 | 0
130 | Finish Labor | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 16 | 0 | 256 | 0 | 256 | 19335 | 0 | 0
130 | Finish Labor | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 1.5 | 0 | 63 | 0 | 63 | 19339 | 0 | 0
130 | Finish Labor | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 24 | 0 | 432 | 0 | 432 | 19348 | 0 | 0
130 | Finish Labor | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 32.5 | 0 | 520 | 0 | 520 | 19360 | 0 | 0
130 | Finish Labor | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 34.5 | 0 | 931.5 | 0 | 931.5 | 19378 | 0 | 0
130 | Finish Labor | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 32 | 0 | 576 | 0 | 576 | 19380 | 0 | 0
130 | Finish Labor | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 10.5 | 0 | 168 | 0 | 168 | 19402 | 0 | 0
130 | Finish Labor | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 34.5 | 0 | 552 | 0 | 552 | 19412 | 0 | 0
130 | Finish Labor | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 2.5 | 0 | 40 | 0 | 40 | 19415 | 0 | 0
130 | Finish Labor | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 2 | 0 | 84 | 0 | 84 | 19416 | 0 | 0
130 | Finish Labor | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 18.5 | 0 | 333 | 0 | 333 | 19425 | 0 | 0
130 | Finish Labor | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 8 | 0 | 192 | 192 | 19434 | 0 | 0
130 | Finish Labor | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 16 | 0 | 256 | 0 | 256 | 19434 | 0 | 0
130 | Finish Labor | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19451 | 0 | 0
130 | Finish Labor | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 8 | 0 | 216 | 216 | 19453 | 0 | 0
130 | Finish Labor | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 288 | 0 | 288 | 19453 | 0 | 0
130 | Finish Labor | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 8 | 0 | 372 | 372 | 19471 | 0 | 0
130 | Finish Labor | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 11 | 0 | 341 | 0 | 341 | 19471 | 0 | 0
130 | Finish Labor | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 16 | 0 | 256 | 0 | 256 | 19475 | 0 | 0
130 | Finish Labor | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 10 | 0 | 240 | 240 | 19476 | 0 | 0
130 | Finish Labor | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19476 | 0 | 0
130 | Finish Labor | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 4 | 0 | 96 | 96 | 19487 | 0 | 0
130 | Finish Labor | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 40 | 0 | 640 | 0 | 640 | 19487 | 0 | 0
130 | Finish Labor | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 504 | 504 | 19490 | 0 | 0
130 | Finish Labor | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 7.5 | 0 | 315 | 0 | 315 | 19490 | 0 | 0
130 | Finish Labor | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 38 | 0 | 684 | 0 | 684 | 19499 | 0 | 0
130 | Finish Labor | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19526 | 0 | 0
130 | Finish Labor | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 32 | 0 | 512 | 0 | 512 | 19551 | 0 | 0
130 | Finish Labor | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 20 | 0 | 320 | 0 | 320 | 19562 | 0 | 0
130 | Finish Labor | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 2 | 0 | 84 | 0 | 84 | 19565 | 0 | 0
130 | Finish Labor | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 32 | 0 | 576 | 0 | 576 | 19574 | 0 | 0
130 | Finish Labor | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19600 | 0 | 0
130 | Finish Labor | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 16 | 0 | 256 | 0 | 256 | 19624 | 0 | 0
130 | Finish Labor | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19625 | 0 | 0
130 | Finish Labor | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 40 | 0 | 640 | 0 | 640 | 19635 | 0 | 0
130 | Finish Labor | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 4.5 | 0 | 189 | 0 | 189 | 19638 | 0 | 0
130 | Finish Labor | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 32 | 0 | 576 | 0 | 576 | 19647 | 0 | 0
130 | Finish Labor | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19672 | 0 | 0
130 | Finish Labor | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19698 | 0 | 0
130 | Finish Labor | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 35 | 0 | 560 | 0 | 560 | 19708 | 0 | 0
130 | Finish Labor | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 4 | 0 | 168 | 0 | 168 | 19711 | 0 | 0
130 | Finish Labor | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 39.5 | 0 | 711 | 0 | 711 | 19720 | 0 | 0
130 | Finish Labor | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 16 | 0 | 432 | 0 | 432 | 19750 | 0 | 0
130 | Finish Labor | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 6 | 0 | 108 | 0 | 108 | 19752 | 0 | 0
130 | Finish Labor | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 16 | 0 | 256 | 0 | 256 | 19774 | 0 | 0
130 | Finish Labor | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 16 | 0 | 256 | 0 | 256 | 19782 | 0 | 0
130 | Finish Labor | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 13.5 | 0 | 567 | 0 | 567 | 19785 | 0 | 0
130 | Finish Labor | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 16 | 0 | 288 | 0 | 288 | 19792 | 0 | 0
130 | Finish Labor | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 24 | 0 | 648 | 0 | 648 | 19816 | 0 | 0
130 | Finish Labor | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 15 | 0 | 240 | 0 | 240 | 19842 | 0 | 0
130 | Finish Labor | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 9 | 0 | 378 | 0 | 378 | 19854 | 0 | 0
130 | Finish Labor | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 16 | 0 | 288 | 0 | 288 | 19863 | 0 | 0
130 | Finish Labor | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 4 | 0 | 108 | 0 | 108 | 19887 | 0 | 0
130 | Finish Labor | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 4 | 0 | 72 | 0 | 72 | 19934 | 0 | 0
130 | Finish Labor | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 4 | 0 | 108 | 0 | 108 | 20030 | 0 | 0
130 | Finish Labor | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 4 | 0 | 72 | 0 | 72 | 20078 | 0 | 0
130 | Finish Labor | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 4 | 0 | 120 | 0 | 120 | 20185 | 0 | 0
130 | Finish Labor | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 3 | 0 | 135 | 135 | 20185 | 0 | 0
130 | Finish Labor | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20254 | 0 | 0
130 | Finish Labor | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | 64 | 0 | 64 | 20255 | 0 | 0
130 | Finish Labor | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | -64 | 0 | -64 | 920306 | 0 | 0
130 | Finish Labor | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20325 | 0 | 0
130 | Finish Labor | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 3 | 0 | 132 | 0 | 132 | 20725 | 0 | 0
130 | Finish Labor | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21303 | 0 | 0
211 | Garage Material | GL | 659 | 10/31/17 | 10/31/17 | Mat | Req 3355 |  |  |  |  | 56.32 |  | 0 | 0
211 | Garage Material | GL | 141 | 11/09/17 | 11/09/17 | Mat | Req 3264 |  |  |  |  | 58 |  | 0 | 0
211 | Garage Material | GL | 224 | 11/10/17 | 11/10/17 | Mat | Req Adj |  |  |  |  | -114.32 |  | 0 | 0
211 | Garage Material | GL | 516 | 11/22/17 | 11/22/17 | Mat | Req 3298 |  |  |  |  | 94.29 |  | 0 | 0
211 | Garage Material | GL | 599 | 11/22/17 | 11/22/17 | Mat | Req adj |  |  |  |  | -94.29 |  | 0 | 0
220 | Roughin Material | AP | 471 | 10/18/17 | 10/25/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 6612.75 | S8460744.001 | 0 | 0
220 | Roughin Material | AP | 472 | 10/18/17 | 10/25/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 876.9 | S8460744.002 | 0 | 0
220 | Roughin Material | AP | 643 | 10/23/17 | 10/26/17 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 678.31 | S011281568.001 | 0 | 0
220 | Roughin Material | AP | 651 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 107.84 | 4244064-00 | 0 | 0
220 | Roughin Material | AP | 652 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 2937.29 | 7130256-00 | 0 | 0
220 | Roughin Material | AP | 653 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 245.1 | 7130258-00 | 0 | 0
220 | Roughin Material | AP | 654 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 99.84 | 4244193-00 | 0 | 0
220 | Roughin Material | AP | 655 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 351.03 | 4244198-00 | 0 | 0
220 | Roughin Material | AP | 656 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 355.46 | 7130368-00 | 0 | 0
220 | Roughin Material | AP | 657 | 10/25/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 711.92 | 7130451-00 | 0 | 0
220 | Roughin Material | AP | 102 | 10/25/17 | 11/01/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | -711.92 | 7130451-00A | 0 | 0
220 | Roughin Material | AP | 103 | 10/25/17 | 11/01/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 711.93 | 7130451-00B | 0 | 0
220 | Roughin Material | GL | 74 | 11/02/17 | 11/02/17 | CK#5013 | Esteban Quintanilla |  |  |  |  | 58.09 |  | 0 | 0
220 | Roughin Material | AP | 91 | 10/23/17 | 11/06/17 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 68.35 | 7130384-00 | 0 | 0
220 | Roughin Material | AP | 109 | 11/01/17 | 11/07/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 895.52 | S8482800.002 | 0 | 0
220 | Roughin Material | AP | 110 | 11/02/17 | 11/07/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | -895.52 | S8482800.003 | 0 | 0
220 | Roughin Material | AP | 126 | 10/26/17 | 11/07/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 449.17 | 4244360-00 | 0 | 0
220 | Roughin Material | GL | 224 | 11/10/17 | 11/10/17 | Mat | Req Adj |  |  |  |  | 114.32 |  | 0 | 0
220 | Roughin Material | AP | 274 | 10/30/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1376 | 4244430-00 | 0 | 0
220 | Roughin Material | AP | 275 | 10/31/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 186.78 | 4244539-00 | 0 | 0
220 | Roughin Material | AP | 276 | 11/01/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 146.31 | 4244578-00 | 0 | 0
220 | Roughin Material | GL | 359 | 11/17/17 | 11/17/17 | Mat | Req 3265 |  |  |  |  | 1419.55 |  | 0 | 0
220 | Roughin Material | AP | 415 | 11/08/17 | 11/20/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1769.8 | 4244647-00 | 0 | 0
220 | Roughin Material | GL | 498 | 11/21/17 | 11/21/17 | CK#5020 | Esteban Quintanilla |  |  |  |  | 10.46 |  | 0 | 0
220 | Roughin Material | GL | 521 | 11/22/17 | 11/22/17 | Mat | Req 3293 |  |  |  |  | 1238.06 |  | 0 | 0
220 | Roughin Material | GL | 599 | 11/22/17 | 11/22/17 | Mat | Req adj |  |  |  |  | 94.29 |  | 0 | 0
220 | Roughin Material | AP | 613 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 7602.67 | S8491558.001 | 0 | 0
220 | Roughin Material | AP | 614 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 444.99 | S8491558.002 | 0 | 0
220 | Roughin Material | AP | 615 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 20.74 | S8491558.003 | 0 | 0
220 | Roughin Material | AP | 616 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 289.77 | S8494995.001 | 0 | 0
220 | Roughin Material | GL | 73 | 12/01/17 | 12/01/17 | Mat | Req 4026 |  |  |  |  | 381.16 |  | 0 | 0
220 | Roughin Material | GL | 74 | 12/01/17 | 12/01/17 | Mat | Req 4025 |  |  |  |  | -1292.1 |  | 0 | 0
220 | Roughin Material | GL | 118 | 12/01/17 | 12/01/17 | Mat | Req 4051 |  |  |  |  | 1918.36 |  | 0 | 0
220 | Roughin Material | AP | 136 | 11/13/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 47.4 | S8494995.002 | 0 | 0
220 | Roughin Material | AP | 137 | 11/14/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 865.34 | S8419558.004 | 0 | 0
220 | Roughin Material | AP | 138 | 11/15/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 128.77 | S8491558.005 | 0 | 0
220 | Roughin Material | AP | 139 | 11/15/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 253.32 | S8491558.006 | 0 | 0
220 | Roughin Material | AP | 163 | 11/07/17 | 12/01/17 | 1234CO | Capital One Credit Card |  |  |  |  | 108.86 | 110717 | 0 | 0
220 | Roughin Material | AP | 200 | 11/21/17 | 12/06/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 4977.68 | S8508933.001 | 0 | 0
220 | Roughin Material | AP | 201 | 11/22/17 | 12/06/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 653.15 | S8512822.001 | 0 | 0
220 | Roughin Material | GL | 566 | 12/07/17 | 12/07/17 | Mat | Req 4077 |  |  |  |  | 445.58 |  | 0 | 0
220 | Roughin Material | AP | 304 | 11/13/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 160 | 4244982-00 | 0 | 0
220 | Roughin Material | AP | 305 | 11/13/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 245.5 | 4244983-00 | 0 | 0
220 | Roughin Material | AP | 306 | 11/15/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 516.02 | 4245080-00 | 0 | 0
220 | Roughin Material | AP | 307 | 11/21/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 199.44 | 4245268-00 | 0 | 0
220 | Roughin Material | AP | 353 | 11/02/17 | 12/12/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 74.07 | 4244655-00 | 0 | 0
220 | Roughin Material | AP | 354 | 11/01/17 | 12/12/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 895.52 | S8482800.001 | 0 | 0
220 | Roughin Material | AP | 355 | 11/01/17 | 12/12/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 215.22 | S8512822.002 | 0 | 0
220 | Roughin Material | AP | 359 | 11/28/17 | 12/13/17 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 99.6 | 5759307 | 0 | 0
220 | Roughin Material | AP | 372 | 11/27/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 130.61 | S8515017.001 | 0 | 0
220 | Roughin Material | AP | 373 | 12/04/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 152.2 | S8525784.001 | 0 | 0
220 | Roughin Material | AP | 374 | 12/04/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 77.2 | S8525784.002 | 0 | 0
220 | Roughin Material | GL | 720 | 12/21/17 | 12/21/17 | CK#5032 | Esteban Quintanilla |  |  |  |  | 11.52 |  | 0 | 0
220 | Roughin Material | GL | 735 | 12/22/17 | 12/22/17 | Mat | Req 3366 |  |  |  |  | -1243.91 |  | 0 | 0
220 | Roughin Material | GL | 736 | 12/22/17 | 12/22/17 | Mat | Req 3384 |  |  |  |  | 32 |  | 0 | 0
220 | Roughin Material | GL | 863 | 12/28/17 | 12/28/17 | Mat | Req 4097 |  |  |  |  | 788.8 |  | 0 | 0
220 | Roughin Material | AP | 925 | 12/08/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 1490.72 | S8508933.003 | 0 | 0
220 | Roughin Material | AP | 926 | 12/08/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 617.08 | S8531719.001 | 0 | 0
220 | Roughin Material | AP | 927 | 12/11/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 681.24 | S8534488.001 | 0 | 0
220 | Roughin Material | AP | 928 | 12/11/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 32 | S8534488.002 | 0 | 0
220 | Roughin Material | AP | 953 | 12/19/17 | 12/31/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 121.12 | 4246187-00 | 0 | 0
220 | Roughin Material | AP | 297 | 12/08/17 | 01/01/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | -617.08 | S8531719.001A | 0 | 0
220 | Roughin Material | GL | 83 | 01/05/18 | 01/05/18 | Mat | Req 4109 |  |  |  |  | -512 |  | 0 | 0
220 | Roughin Material | GL | 85 | 01/05/18 | 01/05/18 | Adj | [5 empty] | -545.78 |  | 0 | 0
220 | Roughin Material | GL | 86 | 01/05/18 | 01/05/18 | Mat | Req 3361 |  |  |  |  | -1351.59 |  | 0 | 0
220 | Roughin Material | GL | 87 | 01/05/18 | 01/05/18 | Mat | Req 3360 |  |  |  |  | -1535.83 |  | 0 | 0
220 | Roughin Material | AP | 146 | 12/28/17 | 01/08/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 360.29 | 4246441-00 | 0 | 0
220 | Roughin Material | AP | 148 | 12/21/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 196.98 | 4246292-00 | 0 | 0
220 | Roughin Material | AP | 149 | 12/28/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 138.3 | 4846240-00 | 0 | 0
220 | Roughin Material | AP | 150 | 12/29/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 99.76 | 7132154-00 | 0 | 0
220 | Roughin Material | AP | 186 | 12/18/17 | 01/09/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 27.31 | S8545824.001 | 0 | 0
220 | Roughin Material | GL | 329 | 01/16/18 | 01/16/18 | Mat | Req 3421 |  |  |  |  | 452.7 |  | 0 | 0
220 | Roughin Material | AP | 358 | 01/05/18 | 01/16/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 108.71 | 7132385-00 | 0 | 0
220 | Roughin Material | AP | 367 | 01/03/18 | 01/17/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 59.12 | 4246566-00 | 0 | 0
220 | Roughin Material | GL | 384 | 01/17/18 | 01/17/18 | Mat | Req 3441 |  |  |  |  | -1683.85 |  | 0 | 0
220 | Roughin Material | GL | 385 | 01/17/18 | 01/17/18 | Mat | Req 3442 |  |  |  |  | -604.62 |  | 0 | 0
220 | Roughin Material | GL | 386 | 01/17/18 | 01/17/18 | Mat | Req 3443 |  |  |  |  | -203.9 |  | 0 | 0
220 | Roughin Material | GL | 493 | 01/22/18 | 01/22/18 | Mat | Req 4131 |  |  |  |  | -1064.47 |  | 0 | 0
220 | Roughin Material | GL | 669 | 01/30/18 | 01/30/18 | Mat | Req 4138 |  |  |  |  | 34 |  | 0 | 0
220 | Roughin Material | GL | 677 | 01/30/18 | 01/30/18 | Mat | Req 3459 |  |  |  |  | 47.76 |  | 0 | 0
220 | Roughin Material | AP | 122 | 01/16/18 | 02/06/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 1726.69 | S8534488.003 | 0 | 0
220 | Roughin Material | AP | 123 | 01/12/18 | 02/06/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1272.18 | 4246869-00 | 0 | 0
220 | Roughin Material | AP | 290 | 01/17/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 2381.75 | 4246805-00 | 0 | 0
220 | Roughin Material | AP | 291 | 01/19/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 34.9 | 4247111-00 | 0 | 0
220 | Roughin Material | AP | 292 | 01/22/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 105.55 | 4247204-00 | 0 | 0
220 | Roughin Material | AP | 102 | 02/22/18 | 03/01/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 589.93 | S8630865.001 | 0 | 0
220 | Roughin Material | GL | 293 | 03/08/18 | 03/08/18 | CK#5064 | Joseph Barnhart |  |  |  |  | 18.7 |  | 0 | 0
220 | Roughin Material | GL | 218 | 03/09/18 | 03/09/18 | Mat | Req 4130 |  |  |  |  | -1282.64 |  | 0 | 0
220 | Roughin Material | GL | 219 | 03/09/18 | 03/09/18 | Mat | Req 3522 |  |  |  |  | 545.36 |  | 0 | 0
220 | Roughin Material | AP | 245 | 02/23/18 | 03/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 995.26 | 4248579-00 | 0 | 0
220 | Roughin Material | GL | 273 | 03/13/18 | 03/13/18 | Mat | Req 3528 |  |  |  |  | 133.76 |  | 0 | 0
220 | Roughin Material | AP | 498 | 03/07/18 | 03/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 327.02 | 4249116-00 | 0 | 0
220 | Roughin Material | AP | 396 | 03/02/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 231.92 | 6007539 | 0 | 0
220 | Roughin Material | AP | 398 | 03/07/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 42.68 | 6020564 | 0 | 0
220 | Roughin Material | AP | 399 | 03/08/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 29.67 | 6023871 | 0 | 0
220 | Roughin Material | AP | 404 | 03/14/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 13.1 | 6035496 | 0 | 0
220 | Roughin Material | GL | 455 | 03/20/18 | 03/20/18 | Mat | Req 3561 |  |  |  |  | 181.19 |  | 0 | 0
220 | Roughin Material | AP | 469 | 02/26/18 | 03/20/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 518.12 | 42485579-01 | 0 | 0
220 | Roughin Material | GL | 829 | 03/31/18 | 03/31/18 | Mat | Req 4245 |  |  |  |  | 1624.4 |  | 0 | 0
220 | Roughin Material | GL | 847 | 03/31/18 | 03/31/18 | Mat | Req 4281 |  |  |  |  | 850.32 |  | 0 | 0
220 | Roughin Material | AP | 879 | 03/21/18 | 03/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 308.39 | S011709965.001 | 0 | 0
220 | Roughin Material | GL | 231 | 04/10/18 | 04/01/18 | Mat | Req 4314 |  |  |  |  | 585.37 |  | 0 | 0
220 | Roughin Material | AP | 235 | 03/26/18 | 04/01/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.69 | 4249838-00 | 0 | 0
220 | Roughin Material | AP | 200 | 03/26/18 | 04/10/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 88.87 | 6070866 | 0 | 0
220 | Roughin Material | GL | 693 | 04/10/18 | 04/10/18 | Mat | Req 4314 |  |  |  |  | -585.37 |  | 0 | 0
220 | Roughin Material | AP | 384 | 04/04/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 173.81 | 4250218-00 | 0 | 0
220 | Roughin Material | AP | 385 | 04/05/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 18.32 | 4250296-00 | 0 | 0
220 | Roughin Material | AP | 563 | 04/11/18 | 04/24/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 209.46 | 6112528 | 0 | 0
220 | Roughin Material | AP | 811 | 04/09/18 | 04/30/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 34.21 | 4250428-00 | 0 | 0
220 | Roughin Material | AP | 150 | 04/17/18 | 05/01/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 286 | 4250786-00 | 0 | 0
220 | Roughin Material | GL | 121 | 05/04/18 | 05/04/18 | Mat | Req 3634 |  |  |  |  | 11.43 |  | 0 | 0
220 | Roughin Material | GL | 323 | 05/11/18 | 05/11/18 | Mat | Req 4348 |  |  |  |  | -498.62 |  | 0 | 0
220 | Roughin Material | AP | 339 | 04/23/18 | 05/11/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 146.65 | 4251044-00 | 0 | 0
220 | Roughin Material | AP | 523 | 05/07/18 | 05/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 40.95 | 6186685 | 0 | 0
220 | Roughin Material | AP | 524 | 05/10/18 | 05/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 9.32 | 6189321 | 0 | 0
220 | Roughin Material | AP | 595 | 05/11/18 | 05/22/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1005.48 | 6201459 | 0 | 0
220 | Roughin Material | AP | 596 | 05/11/18 | 05/22/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1004.3 | 6201473 | 0 | 0
220 | Roughin Material | GL | 605 | 04/27/18 | 05/22/18 | Mat | Req 4375 |  |  |  |  | 47.68 |  | 0 | 0
220 | Roughin Material | GL | 627 | 05/22/18 | 05/22/18 | Mat | Req 4377 |  |  |  |  | 217.33 |  | 0 | 0
220 | Roughin Material | GL | 180 | 06/05/18 | 06/05/18 | Mat | Req 3676 |  |  |  |  | -26.16 |  | 0 | 0
220 | Roughin Material | AP | 205 | 05/17/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 641.73 | S011860284.001 | 0 | 0
220 | Roughin Material | AP | 244 | 05/11/18 | 06/06/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 66.19 | 6202541 | 0 | 0
220 | Roughin Material | AP | 389 | 05/24/18 | 06/11/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 184.2 | 4252427-00 | 0 | 0
220 | Roughin Material | AP | 627 | 05/30/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 754.87 | 6245034 | 0 | 0
220 | Roughin Material | AP | 628 | 05/31/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 714.53 | 6245211 | 0 | 0
220 | Roughin Material | AP | 629 | 06/08/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 110.23 | 6279267 | 0 | 0
220 | Roughin Material | AP | 656 | 06/18/18 | 06/20/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 24.92 | 6289123 | 0 | 0
220 | Roughin Material | AP | 560 | 06/26/18 | 07/20/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 22.1 | 4253753-00 | 0 | 0
230 | Finish Material | GL | 660 | 10/31/17 | 10/31/17 | Mat | Req 3354 |  |  |  |  | 818 |  | 0 | 0
230 | Finish Material | GL | 364 | 11/17/17 | 11/17/17 | Mat | Req 3277 |  |  |  |  | 633.8 |  | 0 | 0
230 | Finish Material | AP | 766 | 12/08/17 | 12/22/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 805.7 | 4245839-00 | 0 | 0
230 | Finish Material | AP | 176 | 01/05/18 | 01/09/18 | 7230BB | Best Bath Systems |  |  |  |  | 1178.07 | 182715-IN | 0 | 0
230 | Finish Material | AP | 381 | 01/08/18 | 01/17/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 2249.2 | S011393325.001 | 0 | 0
230 | Finish Material | AP | 402 | 03/03/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 323.28 | 6006947 | 0 | 0
230 | Finish Material | AP | 403 | 03/09/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5495.71 | 5966585 | 0 | 0
230 | Finish Material | AP | 415 | 03/07/18 | 03/19/18 | 1231KS | Keller Supply Company |  |  |  |  | 1220.72 | S011493993.001 | 0 | 0
230 | Finish Material | AP | 429 | 03/06/18 | 03/19/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 130.11 | S011613223.001 | 0 | 0
230 | Finish Material | AP | 430 | 03/12/18 | 03/19/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 2598.15 | S011613223.002 | 0 | 0
230 | Finish Material | AP | 669 | 03/14/18 | 03/26/18 | 5560CH | California Hydronics Corp |  |  |  |  | 1859 | 2089360 | 0 | 0
230 | Finish Material | AP | 4 | 03/22/18 | 04/04/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 809.1 | S011684919.001 | 0 | 0
230 | Finish Material | AP | 5 | 04/23/18 | 04/04/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 3591.29 | S011613223.003 | 0 | 0
230 | Finish Material | AP | 204 | 04/02/18 | 04/10/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5818.99 | 5966610 | 0 | 0
230 | Finish Material | AP | 223 | 03/28/18 | 04/10/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 701.98 | S011613347.001 | 0 | 0
230 | Finish Material | AP | 224 | 04/03/18 | 04/10/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6319.56 | S011613212.001 | 0 | 0
230 | Finish Material | AP | 226 | 04/02/18 | 04/10/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 105 | 6087954 | 0 | 0
230 | Finish Material | GL | 693 | 04/10/18 | 04/10/18 | Mat | Req 4314 |  |  |  |  | 585.37 |  | 0 | 0
230 | Finish Material | AP | 255 | 04/10/18 | 04/11/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6319.56 | S011613145.001 | 0 | 0
230 | Finish Material | AP | 365 | 03/27/18 | 04/13/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 199.56 | 4249888-00 | 0 | 0
230 | Finish Material | AP | 366 | 03/30/18 | 04/13/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 29.55 | 4249952-00 | 0 | 0
230 | Finish Material | AP | 556 | 04/19/18 | 04/20/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6310.56 | S011613118.001 | 0 | 0
230 | Finish Material | AP | 394 | 04/05/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 423.67 | 4250295-00 | 0 | 0
230 | Finish Material | GL | 709 | 04/27/18 | 04/27/18 | Mat | Req 3595 |  |  |  |  | 177.39 |  | 0 | 0
230 | Finish Material | AP | 798 | 04/06/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 5.46 | 040618 | 0 | 0
230 | Finish Material | AP | 12 | 04/09/18 | 05/02/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5818.99 | 5966617 | 0 | 0
230 | Finish Material | AP | 13 | 04/20/18 | 05/02/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5950.39 | 5966628 | 0 | 0
230 | Finish Material | GL | 120 | 05/04/18 | 05/04/18 | Mat | Req 3635 |  |  |  |  | 293.43 |  | 0 | 0
230 | Finish Material | AP | 182 | 04/23/18 | 05/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 11.22 | 4251019-00 | 0 | 0
230 | Finish Material | GL | 324 | 05/11/18 | 05/11/18 | Mat | Req 4349 |  |  |  |  | -163.42 |  | 0 | 0
230 | Finish Material | AP | 340 | 04/25/18 | 05/11/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 29.97 | 4251148-00 | 0 | 0
230 | Finish Material | AP | 378 | 04/26/18 | 05/15/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 70.82 | S011812053.001 | 0 | 0
230 | Finish Material | AP | 379 | 05/07/18 | 05/15/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 1011.99 | S011613347.002 | 0 | 0
230 | Finish Material | GL | 416 | 05/17/18 | 05/17/18 | Mat | Req 4376 |  |  |  |  | 228.58 |  | 0 | 0
230 | Finish Material | AP | 570 | 05/02/18 | 05/21/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 52.5 | 4251476-00 | 0 | 0
230 | Finish Material | AP | 725 | 05/09/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 529.2 | 4251773-00 | 0 | 0
230 | Finish Material | AP | 730 | 05/14/18 | 05/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 78.72 | 4251930-00 | 0 | 0
230 | Finish Material | AP | 875 | 05/09/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 4.23 | 050918C | 0 | 0
230 | Finish Material | GL | 110 | 06/01/18 | 06/01/18 | Mat | Req 3670 |  |  |  |  | -153.16 |  | 0 | 0
230 | Finish Material | GL | 181 | 06/05/18 | 06/05/18 | Mat | Req 3675 |  |  |  |  | -24.7 |  | 0 | 0
230 | Finish Material | AP | 206 | 05/21/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | -281.89 | S011613347.003 | 0 | 0
230 | Finish Material | AP | 207 | 05/21/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 183.22 | S011613347.004 | 0 | 0
230 | Finish Material | AP | 601 | 06/13/18 | 06/18/18 | 7230BB | Best Bath Systems |  |  |  |  | 505.56 | 189271-IN | 0 | 0
230 | Finish Material | AP | 684 | 06/29/18 | 07/16/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 33.25 | S012018642.001 | 0 | 0
230 | Finish Material | AP | 434 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.8 | 4253753-01 | 0 | 0
230 | Finish Material | AP | 445 | 07/18/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.8 | 4253753-02 | 0 | 0
230 | Finish Material | GL | 683 | 08/22/18 | 08/22/18 | Mat | Req 4602 |  |  |  |  | 37 |  | 0 | 0
230 | Finish Material | AP | 687 | 07/26/18 | 08/22/18 | 1231KS | Keller Supply Company |  |  |  |  | 328.98 | S012072728.001 | 0 | 0
230 | Finish Material | AP | 823 | 07/30/18 | 08/24/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 441.35 | 6401357 | 0 | 0
230 | Finish Material | AP | 219 | 08/16/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | -183.22 | S012198021.001 | 0 | 0
230 | Finish Material | AP | 443 | 08/13/18 | 09/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 427.33 | 4255867-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 125 | 12/01/17 | 12/01/17 | Mat | Req 4072 |  |  |  |  | -545.78 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 85 | 01/05/18 | 01/05/18 | Adj | [5 empty] | 545.78 |  | 0 | 0
600 | Subcontractor | AP | 844 | 04/26/18 | 04/30/18 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 115 | 18042606 | 0 | 0
601 | Engineering/Plans | AP | 542 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 772.5 | 6738 | 0 | 0
995 | Payroll Burden | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 457.69 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 114.64 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 181.61 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 164.32 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 198.91 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 257.45 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 155.67 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 123.74 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 209.55 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 41.91 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 189.6 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 429.09 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 179.62 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 724.68 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 200.24 |  | 0 | 0
995 | Payroll Burden | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 204.9 |  | 0 | 0
995 | Payroll Burden | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 316.22 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 353.91 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 53.89 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 328.63 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 171.63 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 7.98 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 397.82 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 553.04 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 190.71 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 77.83 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 299.36 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 610.26 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 705.61 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 305.13 |  | 0 | 0
995 | Payroll Burden | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 29.94 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.96 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 209.78 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 343.27 |  | 0 | 0
995 | Payroll Burden | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -55.44 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.71 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 176.96 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 230.62 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 413.12 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 147.69 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 151.23 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 315.33 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 251.46 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 9.98 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -49.89 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 68.74 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -28.38 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 78.95 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.78 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 31.33 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 28.34 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 34.31 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 44.41 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 26.85 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 21.34 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 36.15 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 7.23 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 32.7 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 9.24 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 74.01 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 30.98 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 125 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 34.54 |  | 0 | 0
998 | Payroll Taxes | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 35.34 |  | 0 | 0
998 | Payroll Taxes | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 54.54 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 61.05 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 9.29 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 56.69 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 29.61 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 1.38 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 68.62 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 95.4 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 32.9 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 13.43 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 51.64 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 105.26 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 121.71 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 52.63 |  | 0 | 0
998 | Payroll Taxes | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.16 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 36.18 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 59.21 |  | 0 | 0
998 | Payroll Taxes | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.81 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 30.52 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 39.78 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 71.26 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 25.47 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 26.09 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 54.39 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.38 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 1.72 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 11.86 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036966 | 0 | -1275
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036966 | 0 | -1275
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -8500 | 036966 | 0 | -425
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -9500 | 036966 | 0 | -475
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -56050 | 036966 | 0 | -2802.5
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -58500 | 036966 | 0 | -2925
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -51000 | 036981 | 0 | -2550
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -51000 | 036981 | 0 | -2550
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036981 | 0 | -1275
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036981 | 0 | -1275
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -500 | 036981 | 0 | -25
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -500 | 036981 | 0 | -25
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2950 | 036981 | 0 | -147.5
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -6500 | 036981 | 0 | -325
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -13600 | 036981 | 0 | -680
999 | Sales | AR | 537 | 12/15/17 | 12/15/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3400 | 036993 | 0 | -170
999 | Sales | AR | 537 | 12/15/17 | 12/15/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 036993 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -6260 | 037000 | 0 | -313
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2763 | 037000 | 0 | -138.15
999 | Sales | AR | 443 | 03/20/18 | 03/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -22650 | 037048 | 0 | -1132.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 037070 | 0 | -1275
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -28310 | 037070 | 0 | -1415.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -28310 | 037070 | 0 | -1415.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -5660 | 037070 | 0 | -283
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -5923 | 037070 | 0 | -296.15
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -1380 | 037070 | 0 | -69
999 | Sales | AR | 511 | 05/18/18 | 05/18/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2810 | 037089 | 0 | -140.5
999 | Sales | AR | 511 | 05/18/18 | 05/18/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -1287 | 037089 | 0 | -64.35
999 | Sales | AR | 673 | 06/20/18 | 06/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2412 | 037112 | 0 | -120.6
999 | Sales | AR | 527 | 07/20/18 | 07/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -4200 | 037139 | 0 | -210
999 | Sales | AR | 527 | 07/20/18 | 07/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -403 | 037139 | 0 | -20.15

## Crew Roster
CREW ROSTER — 30 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Caro, Camilo | 56.5 | 8 | 0 | 904 | 192 | 16
APPRENTICE/HELPER | Nelson, Charles E | 40 | 0 | 0 | 640 | 0 | 16
APPRENTICE/HELPER | Rivera Oseguera, Kate Y | 201.5 | 4 | 0 | 3224 | 96 | 16
APPRENTICE/HELPER | Olea Galeana, Maricela | 193.5 | 10 | 0 | 3096 | 240 | 16
APPRENTICE/HELPER | Sanchez Olea, Itzel G | 2.5 | 0 | 0 | 40 | 0 | 16
APPRENTICE/HELPER | Ramos Melendez, Carlos M | 264 | 42 | 0 | 4752 | 1134 | 18
APPRENTICE/HELPER | Cornejo Orellana, Carlos E | 504 | 21.5 | 0 | 9072 | 580.5 | 18
APPRENTICE/HELPER | Gomez Reyes, Edith N | 68 | 15 | 0 | 1224 | 405 | 18
APPRENTICE/HELPER | Sanchez, Derli | 1 | 6 | 0 | 18 | 162 | 18
APPRENTICE/HELPER | Lopez Reyes, Boris O | 24 | 0 | 0 | 432 | 0 | 18
APPRENTICE/HELPER | Yohannes Jr., Samson | 224 | 0 | 0 | 4032 | 0 | 18
APPRENTICE/HELPER | Cruz Gonzalez, Julio C | 519 | 35 | 0 | 9861 | 997.5 | 19
APPRENTICE/HELPER | Gerard, Mitchell J | 4 | 0 | 0 | 0 | 0 | 0
JOURNEYMAN | Benites Portillo, Marvin E | 406 | 35 | 0 | 8526 | 1102.5 | 21
JOURNEYMAN | Hubbard, Dustin R | 4 | 0 | 0 | 84 | 0 | 21
JOURNEYMAN | Eliassen, Cory H | 3 | 0 | 0 | 63 | 0 | 21
JOURNEYMAN | Lovo, German G | 220 | 22.5 | 0 | 5060 | 776.25 | 23
JOURNEYMAN | Galdamez, Dagoberto A | 480 | 14 | 0 | 11520 | 504 | 24
JOURNEYMAN | Montenegro, Carlos E | 7 | 21 | 0 | 189 | 850.5 | 27
JOURNEYMAN | Gerard, Jordan E | 306.5 | 3 | 0 | 8299.5 | 135 | 27.0783
JOURNEYMAN | Rivera, Jorge A | 72 | 8 | 0 | 2232 | 372 | 31
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 17 | 4 | 0 | 527 | 186 | 31
JOURNEYMAN | McCabe, Thomas C | 23 | 12 | 0 | 718 | 561 | 31.2174
LEAD/SUPERVISOR | Hubbard, Robert W | 58.5 | 0 | 0 | 2421.5 | 0 | 41.3932
LEAD/SUPERVISOR | Sanders, Allen O | 75 | 8 | 0 | 3160 | 504 | 42.1333
LEAD/SUPERVISOR | Quintanilla, Esteban R | 405 | 37 | 0 | 17415 | 2386.5 | 43
LEAD/SUPERVISOR | Gerard, Jeffrey S | 122.5 | 0 | 0 | 5892.5 | 0 | 48.102
LEAD/SUPERVISOR | Donelson, Richard T | 36 | 0 | 0 | 1912.5 | 0 | 53.125
OT-ONLY | Hernandez Gonzalez, Osbaldo | 0 | 14 | 0 | 0 | 399 | — (no reg hours)
OT-ONLY | Cruz Guzman, Joel A | 0 | 14 | 0 | 0 | 462 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2048
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 13 | 2102 | 141.5 | 41102 | 15.9231
JOURNEYMAN | 10 | 1538.5 | 119.5 | 41705.75 | 25.7296
LEAD/SUPERVISOR | 5 | 697 | 45 | 33692 | 45.5507
OT-ONLY | 2 | 0 | 28 | 861 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 16
p25 | 18
p50 | 21
p75 | 31
p90 | 42.39
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 24.2801 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 38.1866 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 51.2504 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2048
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 4,671.50 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $110.69 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $25.12 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 4.41x | Throughput ÷ unit cost — productivity signal
Units (residential) | 72 | GRE Ballinger Apartments scope doc: 68 Type B + 4 Type A ADA
Fixtures (estimate) | 410 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 12 | start_date → end_date from GDrive enrichment
Hours per Unit | 64.88 | total_labor_hours ÷ units
Hours per Fixture | 11.39 | total_labor_hours ÷ fixtures
Revenue per Unit | $7,182 | revenue ÷ units
Profit per Unit | $3,088 | net_profit ÷ units
Hours per Month | 389 | total_labor_hours ÷ duration_months
Revenue per Month | $43,089 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 15 VENDORS ($115,060 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Keller Supply Co. $Ballinger | 31366.94 | 16 | 1960.4337 | 27.26% | 0 | 0
2 | Consolidated Supply Co. $Ballinger | 28202.19 | 26 | 1084.6996 | 24.51% | 0 | 0
3 | Ferguson Enterprises, Inc. $Ballinger | 25339.47 | 12 | 2111.6225 | 22.02% | 0 | 0
4 | Rosen Supply Company, Inc. $Ballinger | 16702.81 | 42 | 397.686 | 14.52% | 0 | 0
5 | Ferguson Enterprises, Inc. #3007 | 3060.33 | 11 | 278.2118 | 2.66% | 0 | 0
6 | Rosen Supply Kirkland | 2626.57 | 9 | 291.8411 | 2.283% | 0 | 0
7 | California Hydronics Corp | 1859 | 1 | 1859 | 1.616% | 0 | 0
8 | Best Bath Systems | 1683.63 | 2 | 841.815 | 1.463% | 0 | 0
9 | Keller Supply Company | 1674.87 | 4 | 418.7175 | 1.456% | 0 | 0
10 | Rosen Supply Company, Inc. $Green Lake | 948.61 | 3 | 316.2033 | 0.8244% | 0 | 0
11 | Franklin Engineering | 772.5 | 1 | 772.5 | 0.6714% | 0 | 0
12 | Consolidated Supply Co. | 589.93 | 1 | 589.93 | 0.5127% | 0 | 0
13 | R.A. Brown Backflow Testing | 115 | 1 | 115 | 0.09995% | 0 | 0
14 | Capital One Credit Card | 113.09 | 2 | 56.545 | 0.09829% | 0 | 0
15 | Bank of America CC | 5.46 | 1 | 5.46 | 0.004745% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2048
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 |  | Minor scope addition (CO#01 per Budget Transfer + Executed CO1) | 2763 | Executed 2018-01-25 | Y
2 |  | Scope addition (CO#02 per OneWay_CO2 + Budget Transfer) | 1287 | Executed 2018-02-05 | Y
3 |  | Largest scope CO (CO#03 — pay app 5 reflected co3) | 5923 | Executed 2018-03-13 | Y
4 |  | Scope addition (CO#04 — pay app 6 reflected co4) | 1380 | Executed 2018-04-27 | Y
5 |  | Scope addition (CO#05 — pay app 8 reflected co5) | 2412 | Executed | Y
6 |  | Closeout scope rebalance (CO#06, final) | 4603 | Executed | Y
Executed subtotal |  |  | 18368
Budget-transfer total (incl. extras) |  |  | 18368
JDR-implied CO (revenue − original contract) |  |  | 18368
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
COR #01 Chip Tub Box Unit 215 | Chip/repair tub box damage in Unit 215
COR #02 Concrete in Pipes Unit 217 | Remove concrete intrusion in drain pipes Unit 217
COR #03 Drain Line Repairs Units 213/209/202 | Drain line repairs across 3 units
COR #04 Move Drains under Toe Kicks Units 205/219 | Relocate drain stubs to fit under toe kicks
COR #05 Best Bath Shower Pans | Best Bath pan substitution scope
COR #06 Public Area Water Heaters | Add/upsize public-area water heaters
COR #07 Trench Drain | Added trench drain scope
COR #08 Overtime Premium | OT premium reimbursement request
COR #09 Overflow Drains with Cow's Tongues | Overflow drain scope w/ cow's tongue fittings
COR #10 Generator Fuel & Vent Piping | Generator fuel + vent piping scope (potentially outside contract — gas piping exclusion)
COR #11 Rooftop Sink Changes | Rooftop deck sink scope changes
Ballinger Outstanding CORs log | Summary of pending CORs
Ballinger Overtime Premium (ancillary) | OT premium worksheet (separate from COR #08)
Ballinger Temp Downspouts | Temporary downspouts scope

## Project Team
PROJECT TEAM — 2048
Primary contacts extracted from GRE Ballinger Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | Eric Bentler | TBD | 206.972.8145
GC Superintendent | Victor Vo / Brett (per GRE Ballinger Brett folder) | TBD | 206.883.7468
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans folder
Owner | GRE 205th LLC
Inspecting Authority | City of Shoreline (DCI)

## Document Pipeline
DOCUMENT PIPELINE — 2048
Quantitative document counts from the GRE Ballinger Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 6 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 14 | Change Orders/COR_s/
Budget transfer entries | 6 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 10 | ASI-RFI/
Submittals | 18 | Submittals/ (PDF count)
POs — placed | 0 | PO_s/1 Placed/
POs — scheduled | 17 | PO_s/2 Scheduled/
POs — completed | 68 | PO_s/3 Completed/
POs — total | 85 | PO_s/ (all three subfolders)
Vendor invoices | 122 | Invoices/
Lien releases | 0 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 2 | Permits/ (Seattle DCI plumbing + gas + backflow permits)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for GRE Ballinger)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2048
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 178388.59 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 115060.4 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 1263.64 | SUM(line_items where source=GL)
direct_cost | 294712.63 | PR + AP + GL
net_profit | 222355.37 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.345 | PR / abs(revenue)
ap_pct_of_revenue | 0.22253 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.56997 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 4671.5 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 38.1866 | PR / labor hours
fully_loaded_wage | 51.2504 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 24.2801 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 30 | COUNT DISTINCT(name) source=PR
burden_total | 61027.84 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $16.00 ¦ $18.00 ¦ $21.00 ¦ $31.00 ¦ $42.39 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 115436.54 | SUM(actual) codes 2xx
material_budget_total | 151898 | SUM(current_budget) codes 2xx
material_codes_tracked | 4 | COUNT material codes
material_codes_over_budget | 0 | COUNT where plus_minus > 0
material_codes_under_budget | 4 | COUNT where plus_minus ≤ 0
largest_material_overrun | 241 Water Main/Insulation Mat: $0 vs $0 budget (+$0) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943) | Material code with largest −plus_minus
material_vendor_count | 15 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Keller Supply Co. $Ballinger: $31,367 (27% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 0 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 13 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 112 Canout Labor: $0 vs $0 budget (+$0) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 294712.63 | SUM(actual) expense codes
total_budget | 376341.39 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7831 | JTD / budget
total_over_under_budget | 81628.76 | budget − JTD
labor_unit_cost_per_hr | 25.1227 | Labor JTD / labor hours
revenue_per_labor_hour | 110.6856 | abs(revenue) / labor hours
material_price_variance | 36461.46 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2048
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 43.0% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | GREEN | 0/13 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $36,461 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $110.69 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $25,853 | Monitor for collection
Top vendor concentration | GREEN | 27.3% (Keller Supply Co. $Ballinger) | Yellow >50% (single-vendor risk)
Unused-budget codes | YELLOW | 1 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2048
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $517,068, net profit $222,355 at 43.0% margin.
02 | Parsed 1,152 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 30 distinct PR-booked workers over 4,672 labor hours ($38.19/hr PR-src, $51.25/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 112 Canout Labor: $0 vs $0 budget (+$0).
05 | Largest phase savings: 230 Finish Material: $64,021 vs $86,964 budget ($-22,943).
06 | Material spend $115,437 vs budget $151,898 ($36,461 favorable).
07 | Top AP vendor: Keller Supply Co. $Ballinger: $31,367 (27% of AP); 15 total AP vendors.
08 | Retainage outstanding: $25,853.
09 | 0 of 13 expense phases over budget ($81,629 net vs budget).
10 | Revenue per labor hour $110.69, labor unit cost $25.12 (ratio 4.41x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 14/14 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 3089.5 | 3089.5 | 0 | ✓
101 | Takeoff & Purchase Labor | 4715.5 | 4715.5 | 0 | ✓
112 | Canout Labor | 0 | 0 | 0 | ✓
120 | Roughin Labor | 82885.25 | 82885.25 | 0 | ✓
130 | Finish Labor | 26670.5 | 26670.5 | 0 | ✓
211 | Garage Material | 0 | 0 | 0 | ✓
220 | Roughin Material | 51415.82 | 51415.82 | 0 | ✓
230 | Finish Material | 64020.72 | 64020.72 | 0 | ✓
241 | Water Main/Insulation Mat | 0 | 0 | 0 | ✓
600 | Subcontractor | 115 | 115 | 0 | ✓
601 | Engineering/Plans | 772.5 | 772.5 | 0 | ✓
995 | Payroll Burden | 52049.65 | 52049.65 | 0 | ✓
998 | Payroll Taxes | 8978.19 | 8978.19 | 0 | ✓
999 | Sales | -517068 | -517068 | 0 | ✓
RESULT: 14/14 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2048
Worked example of the Reconciliation Protocol running against Job 2048 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 112 Canout Labor: $0 vs $0 budget (+$0) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $376,341; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $38.19/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $178,388.59 ÷ 4,671.50 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$16.00 ¦ p25=$18.00 ¦ p50=$21.00 ¦ p75=$31.00 ¦ p90=$42.39 (30 workers) | straight_time_rate $24.28 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $25.12/hr ¦ revenue $110.69/hr ¦ ratio 4.41x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2048 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 14/14 codes tie to PDF to the cent | PR $178,388.59 + AP $115,060.40 + GL $1,263.64 = $294,712.63 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2048
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2048 | JDR cover page
job_name | Job Name | GRE Greenlake | JDR cover page
general_contractor | General Contractor | GRE | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 1152 | Length of line_items[]
cost_code_count | Cost Code Count | 14 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -517068 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 517068 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 294712.63 | Sage job_totals_expenses
job_totals_net | Net | -222355.37 | Sage job_totals_net
job_totals_retainage | Retainage | -25853.4 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 178388.59 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 115060.4 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 1263.64 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -517068 | SUM(line_items source=AR)
direct_cost | Direct Cost | 294712.63 | PR + AP + GL
net_profit | Net Profit | 222355.37 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 43% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 117360.75 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 115436.54 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 887.5 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 61027.84 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 4671.5 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 30 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 24.2801 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 38.1866 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 51.2504 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 61027.84 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 16 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 18 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 21 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 31 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 42.39 | Percentile across workers
material_spend_total | Material Spend Total | 115436.54 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 151898 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 4 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 0 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 4 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 15 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 36461.46 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 241 Water Main/Insulation Mat: $0 vs $0 budget (+$0)
largest_material_savings | Largest Material Savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943)
top_vendor_spend | Top Vendor Spend | Keller Supply Co. $Ballinger: $31,367 (27% of AP)
phases_over_budget | Phases Over Budget | 0 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 13 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 112 Canout Labor: $0 vs $0 budget (+$0)
largest_savings | Largest Savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943)
total_jtd_cost | Total JTD Cost | 294712.63 | SUM(actual) expense codes
total_budget | Total Current Budget | 376341.39 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 78.31% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 81628.76 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 25.1227 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 110.6856 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array