## Overview
Job #2048 · GRE Ballinger Apartments (1795 NE 205th St, Shoreline WA)
Cortex JCR v2 • GRE (customer 2048SH) • 1795 NE 205th Street, Shoreline, WA 98155 • Owner: GRE 205th LLC
PROJECT OVERVIEW
Project Job # | 2048 |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | GRE Greenlake |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | GRE Ballinger Apartments — 72-unit 7-story midrise multi-family (4 Type A ADA), Seattle |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | GRE |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2048SH |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | GRE 205th LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | Eric Bentler |  | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
GC Superintendent | Victor Vo / Brett (per GRE Ballinger Brett folder) |  | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
GC PE | N/A |  | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314) |  | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
Jobsite Location | 1795 NE 205th Street, Shoreline, WA 98155 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 410 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans folder |  | GRE Ballinger Apartments project info.pdf
Contract Type | Lump Sum |  | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
Unit Count | 72 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-10 start → 2018-10 (12 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
517068 |  | 222355.37 | 294712.63 | 4671.5
Original $498,700.00 + ($18,368.00) COs (3.68%) |  | 43.0% margin | 57.0% of revenue | 30 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
72-unit mixed-use (102 Type B + 6 Type A/ADA) at 1795 NE 205th Street, Shoreline, WA 98155, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: GRE (2048SH); Owner: GRE 205th LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: Eric Bentler (GC PM) · Victor Vo / Brett (per GRE Ballinger Brett folder) (GC Sup) · TBD — per Plans folder (Architect) · Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314) (OWP signatory).
SOURCES
Canonical financial source: 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $517,068.00 / Expenses $294,712.63 / Net $222,355.37 / Retainage $25,853.40
Source breakdown (derived): PR $178,388.59 · AP $115,060.40 · GL $1,263.64
Contract: Lump Sum $498,700.00 → $517,068.00
Change Orders (executed): $18,368.00 net across 6 COs (CO log in enriched meta)
Project Team: Eric Bentler (PM) · Victor Vo / Brett (per GRE Ballinger Brett folder) (Sup) · TBD — per Plans folder · GRE 205th LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | GRE
GC PM | Extracted | Eric Bentler
GC Superintendent | Extracted | Victor Vo / Brett (per GRE Ballinger Brett folder)
GC PE | N/A | N/A
Owner | Extracted | GRE 205th LLC
Architect | Extracted | TBD — per Plans folder
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314)

## Budget vs Actual
Budget vs Actual
All 14 cost codes from JDR. Contract $498,700 → $517,068.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 4320 | 4420 | 3089.5 | -1330.5 | 69.9% | 63.5 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 9000 | 9200 | 4715.5 | -4484.5 | 51.26% | 91 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 0 | 0 | 0 | 0 |  |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 98181 | 104646 | 82885.25 | -21760.75 | 79.21% | 3279.5 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 26460 | 27252 | 26670.5 | -581.5 | 97.87% | 1224.5 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 0 | 1644 | 0 | -1644 | 0% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 62505 | 63290 | 51415.82 | -11874.18 | 81.24% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 81287 | 86964 | 64020.72 | -22943.28 | 73.62% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 |  |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 500 | 500 | 115 | -385 | 23% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 1000 | 1000 | 772.5 | -227.5 | 77.25% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 62565.31 | 66233.59 | 52049.65 | -14183.94 | 78.58% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 10554.02 | 11191.8 | 8978.19 | -2213.61 | 80.22% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -498700 | -517068 | -517068 | 0 | 100% |  | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -142327.67 | -140726.61 | -222355.37 | -81628.76 |  | 4658.5

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,112,120,130 | 117360.75 | 39.82% | 22.7% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 211,220,230,241 | 115436.54 | 39.17% | 22.33% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601 | 887.5 | 0.3011% | 0.1716% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 52049.65 | 17.66% | 10.07% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 8978.19 | 3.046% | 1.736% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 294712.63 | 100% | 57%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
2048KS | Keller Supply Co. $Ballinger | 31366.94 | 16 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2048CS | Consolidated Supply Co. $Ballinger | 28202.19 | 26 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2048FE | Ferguson Enterprises, Inc. $Ballinger | 25339.47 | 12 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2048RS | Rosen Supply Company, Inc. $Ballinger | 16702.81 | 42 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 3060.33 | 11 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 2626.57 | 9 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 1859 | 1 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7230BB | Best Bath Systems | 1683.63 | 2 | Uncategorized | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 1674.87 | 4 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2047RS | Rosen Supply Company, Inc. $Green Lake | 948.61 | 3 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 772.5 | 1 | Engineering (601) | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 589.93 | 1 | Plumbing / Supplies | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 115 | 1 | Testing subcontractor | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 113.09 | 2 | Credit Card (mixed) | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 5.46 | 1 | Credit Card (mixed) | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 115060.4 | 132

## Crew & Labor
Crew & Labor — Worker Roster
All 30 unique payroll workers. OWP signatory: Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
CR77 | Cruz Gonzalez, Julio C | 554 | 10858.5 | 19.6002 | 17 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO69 | Cornejo Orellana, Carlos E | 525.5 | 9652.5 | 18.3682 | 18 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GA46 | Galdamez, Dagoberto A | 494 | 12024 | 24.3401 | 14 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
QU35 | Quintanilla, Esteban R | 442 | 19801.5 | 44.7998 | 17 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE54 | Benites Portillo, Marvin E | 441 | 9628.5 | 21.8333 | 14 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 309.5 | 8434.5 | 27.252 | 14 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RA57 | Ramos Melendez, Carlos M | 306 | 5886 | 19.2353 | 8 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO87 | Lovo, German G | 242.5 | 5836.25 | 24.067 | 7 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
YO29 | Yohannes Jr., Samson | 224 | 4032 | 18 | 10 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI89 | Rivera Oseguera, Kate Y | 205.5 | 3320 | 16.1557 | 7 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
OL17 | Olea Galeana, Maricela | 203.5 | 3336 | 16.3931 | 7 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 122.5 | 5892.5 | 48.102 | 33 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 83 | 1629 | 19.6265 | 6 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 83 | 3664 | 44.1446 | 14 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI87 | Rivera, Jorge A | 80 | 2604 | 32.55 | 3 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA50 | Caro, Camilo | 64.5 | 1096 | 16.9922 | 3 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 58.5 | 2421.5 | 41.3932 | 9 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
NE46 | Nelson, Charles E | 40 | 640 | 16 | 3 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 36 | 1912.5 | 53.125 | 17 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 35 | 1279 | 36.5429 | 4 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 28 | 1039.5 | 37.125 | 4 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO58 | Lopez Reyes, Boris O | 24 | 432 | 18 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 21 | 713 | 33.9524 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 14 | 399 | 28.5 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 14 | 462 | 33 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA51 | Sanchez, Derli | 7 | 180 | 25.7143 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 4 | 0 | 0 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 4 | 84 | 21 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 3 | 63 | 21 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA53 | Sanchez Olea, Itzel G | 2.5 | 40 | 16 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 4671.5 | 117360.75

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 30 | Unique payroll IDs | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 4671.5 | Sum of labor codes | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 117360.75 | Sum of labor codes | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 25.1227 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 11.86% | CR77 Cruz Gonzalez, Julio C (554 hrs) | Derived
Top 5 Workers Hours Share | 52.58% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 53.125 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 0 | Single-worker blended | Derived
Avg Hours per Worker | 155.7167 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 8.0667 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 72 units (410 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 110.6856 | USD/hr
Profit per Labor Hour | 47.5983 | USD/hr
Labor Cost per Hour (blended) | 25.1227 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 51.2504 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 3279.5 | hrs
Finish Hours (code 130) | 1224.5 | hrs
Rough-in % of Total Hours | 70.4% | %
Gross Margin | 43% | %
Labor % of Revenue | 22.7% | %
Material % of Revenue | 22.33% | %
Direct Cost Ratio | 57% | % | All exp/Rev
Revenue per Unit (72) | 7181.5 | USD | 72 units
Labor Hours per Unit | 64.8819 | hrs
Labor Cost per Unit | 1630.0104 | USD
Material Cost per Unit | 1603.2853 | USD
Direct Cost per Unit | 4093.231 | USD
Rough-in Hours per Unit | 45.5486 | hrs
Revenue per Fixture | 1261.1415 | USD | 410 fixtures
Hours per Fixture | 11.3939 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-10-25 | GRE | Lump Sum Subcontract | Closed | GRE Ballinger Apartments plumbing (72 units, 7 stories) — per Div 22 | 498700 | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
CO-NET | — | GRE | Change Orders (executed, 6 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 18368 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 517068

## Billing & SOV
Billing & Schedule of Values
122 invoices to GRE. Retainage $25,853.40.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
465 | 01/19/18 | -20423 | -1021.15 | 5 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
443 | 03/20/18 | -22650 | -1132.5 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
549 | 04/20/18 | -95083 | -4754.15 | 6 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
511 | 05/18/18 | -4097 | -204.85 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
673 | 06/20/18 | -2412 | -120.6 | 1 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
527 | 07/20/18 | -4603 | -230.15 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
362 | 10/20/17 | -183550 | -9177.5 | 6 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
375 | 11/17/17 | -177050 | -8852.5 | 9 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
537 | 12/15/17 | -7200 | -360 | 2 | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -517068 | -25853.4

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $222,355.37 on $517,068.00 revenue = 43.0% gross margin. | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $498,700.00 → final $517,068.00 = $+18,368.00 net (3.68%) across 6 executed COs. | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $117,360.75 (22.7% of rev) across 4,672 hrs and 30 workers. Blended wage $25.12/hr. | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$104,671.74 (91% of AP). Top vendor: Keller Supply Co. $Ballinger ($31,366.94). | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $25,853.40 — outstanding as of report date. | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 3,280 hrs (70% of labor hours). | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $82,885.25 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Cruz Gonzalez, Julio C = 554 hrs (12% of total). | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | GRE Ballinger Apartments — 72-unit 7-story midrise (68 standard + 4 Type A ADA) + P1/P2 parking at 1795 NE 205th Street, Shoreline, WA 98155. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2048 | Profile | OWP job ID | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | GRE Ballinger Apartments (1795 NE 205th St, Shoreline WA) | Profile |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | GRE | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | GRE 205th LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans folder | Profile |  | Verified | GRE Ballinger Apartments project info.pdf
Location | location | 1795 NE 205th Street, Shoreline, WA 98155 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Mid-rise multi-family apartments: 72 residential units (68 Type B + 4 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves (Peltram-installed double-check valve POC). | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | Eric Bentler | Profile |  | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
GC Sup | gc_sup | Victor Vo / Brett (per GRE Ballinger Brett folder) | Profile |  | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314) | Profile |  | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-10-25 | Profile |  | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
Work Start | start_date | 2017-10 | Profile |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2018-10 | Profile |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 12 | Profile |  | Verified | Derived
Unit Count | unit_count | 72 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 410 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 498700 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 517068 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 18368 | Financial | 6 executed | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 3.683% | Financial |  | Verified | Derived
Revenue | revenue | 517068 | Financial | AR total | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 294712.63 | Financial | JDR Expenses | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 222355.37 | Financial | Rev - Exp | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 43% | Financial |  | Verified | Derived
Retainage | retainage | 25853.4 | Financial | JDR AR retainage | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 117360.75 | Labor | Codes 100-151 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 115436.54 | Material | Codes 210-245 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 887.5 | Financial | Codes 600-607 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 52049.65 | Labor | Code 995 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 8978.19 | Labor | Code 998 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 4671.5 | Labor | Sum labor codes | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 30 | Labor | Unique PR IDs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 25.1227 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 51.2504 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 3279.5 | Labor | Code 120 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 1224.5 | Labor | Code 130 | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 110.6856 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 47.5983 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 7181.5 | Productivity | 72 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 4093.231 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 64.8819 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 1261.1415 | Productivity | 410 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 22.7% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 22.33% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 15 | Material |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 9 | Billing |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 11.86% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 52.58% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 14 | Structure |  | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 6 | Documents |  | Verified | CO log
COR Count | cor_count | 14 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 10 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 18 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 85 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 2048KS | Keller Supply Co. $Ballinger | 31366.94 | 16 | 27.26% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 2048CS | Consolidated Supply Co. $Ballinger | 28202.19 | 26 | 24.51% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 2048FE | Ferguson Enterprises, Inc. $Ballinger | 25339.47 | 12 | 22.02% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 2048RS | Rosen Supply Company, Inc. $Ballinger | 16702.81 | 42 | 14.52% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1175FE | Ferguson Enterprises, Inc. #3007 | 3060.33 | 11 | 2.66% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1380RS | Rosen Supply Kirkland | 2626.57 | 9 | 2.283% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 5560CH | California Hydronics Corp | 1859 | 1 | 1.616% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 7230BB | Best Bath Systems | 1683.63 | 2 | 1.463% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 1231KS | Keller Supply Company | 1674.87 | 4 | 1.456% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2047RS | Rosen Supply Company, Inc. $Green Lake | 948.61 | 3 | 0.8244% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 1625FE | Franklin Engineering | 772.5 | 1 | 0.6714% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1130CS | Consolidated Supply Co. | 589.93 | 1 | 0.5127% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1421RA | R.A. Brown Backflow Testing | 115 | 1 | 0.09995% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1234CO | Capital One Credit Card | 113.09 | 2 | 0.09829% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1234BA | Bank of America CC | 5.46 | 1 | 0.004745% | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 115060.4 | 132

## Change Log
Change Log — Master Register
Contract, 6 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-10-25 | Prime subcontract — Lump Sum $498,700.00 | GRE | 498700 | Executed | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/19/18 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/15/17 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $25,853.40 (outstanding) | GC | 0 | Outstanding | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 18368 | JDR-implied net CO impact | $498,700 → $517,068 (6 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -28157.25 | Labor variance vs revised budget | 30 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -36461.46 | Material procurement variance | 15 vendors
Overhead | 600,601,602,603,604,607 | -612.5 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -16397.55 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -63260.76
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 6 | 18368 | Aggregate executed COs
Sub (OWP) labor performance | 5 | -28157.25 | Hours + rate vs budget
Sub (OWP) material procurement | 4 | -36461.46 | 15 vendors
OWP burden accrual | 2 | -16397.55 | Payroll burden + tax
OWP overhead | 2 | -612.5 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 3.68% | ±10% | HEALTHY | +3.68% net (6 COs)
Labor % of Revenue | 22.7% | <30% | HEALTHY | 22.7%
GL Overhead % of Revenue | 0.2444% | <5% | HEALTHY | 0.2%
Vendor Concentration (Top 5) | 90.97% | <95% | HEALTHY | Top 5 = 91% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 43% | >30% | HEALTHY | 43.0%
Labor Hrs Total | 4671.5 | varies | INFO | 4,672 hrs, 30 workers
Worker Concentration (top 1) | 11.86% | <25% | HEALTHY | 11.9% (Cruz Gonzalez, Julio C)
Rough-in Labor Share | 70.4% | 40-65% | WATCH | 70%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $25,853.40
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 43% | Actual | Job closed | 43.0%
Retainage collection | $25,853.40 | Outstanding | Legacy | Outstanding
Unit-level economics | $7,182/unit rev, $3,088/unit profit | Verified | 72 units | Mid-rise multi-family apartments: 72 residential units (68 Type B + 4 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves (Peltram-installed double-check valve POC).

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2048 | id | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | GRE Ballinger Apartments (1795 NE 205th St, Shoreline WA) | text | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | GRE | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | GRE 205th LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans folder | text | Benchmark KPIs | Verified | GRE Ballinger Apartments project info.pdf
6 | location | Location | 1795 NE 205th Street, Shoreline, WA 98155 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Mid-rise multi-family apartments: 72 residential units (68 Type B + 4 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves (Peltram-installed double-check valve POC). | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | Eric Bentler | text | Benchmark KPIs | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Victor Vo / Brett (per GRE Ballinger Brett folder) | text | Benchmark KPIs | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Mike Donelson (OWP per Subcontractor Work Order 7921, 10/23/2017; miked@owpllc.net / 425.968.8314) | text | Benchmark KPIs | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-10-25 | date | Benchmark KPIs | Verified | 2048-Shelter Holdings subcontract 7921 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-10 | date | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2018-10 | date | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 12 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 72 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 410 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 498700 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 517068 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 18368 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 3.683% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 517068 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 294712.63 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 222355.37 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 43% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 25853.4 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 117360.75 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 115436.54 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 887.5 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 52049.65 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 8978.19 | USD | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 4671.5 | hours | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 30 | count | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 25.1227 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 51.2504 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 3279.5 | hours | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 1224.5 | hours | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 110.6856 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 47.5983 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 7181.5 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 4093.231 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 64.8819 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 1261.1415 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 22.7% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 22.33% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 15 | count | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 9 | count | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 11.86% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 52.58% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 14 | count | Benchmark KPIs | Verified | 2048 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 6 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 14 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 10 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 18 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 85 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 517068 | 517068 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 294712.63 | 294712.63 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 222355.37 | 222355.37 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 517068 | 517068 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 4671.5 | 4671.5 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 18368 | 18368 | 0 | TIES | 11↔Derived
7 | Worker count | 30 | 30 | 0 | TIES | 5↔1
8 | Cost code count | 14 | 14 | 0 | TIES | 2↔16