## Report Record
JCR TEST LABELS — JOB 2048
Report-level fields from the v4 schema. Parsed from 1,152-line Job Detail Report (Apr 03, 2026 run). Mirrors the Job 2020 test-labels structure.
Field | Value
job_number | 2048
job_name | GRE Greenlake
report_date | 2026-04-03
general_contractor | GRE
owner | GRE 205th LLC
architect | TBD — per Plans folder
location | 1795 NE 205th Street, Shoreline, WA 98155
project_type | Mid-rise multi-family apartments: 72 residential units (68 Type B + 4 Type A ADA) with L1 amenity restroom + lounge + rooftop deck sink. Post-tension deck construction with existing ProSet sleeves (Peltram-installed double-check valve POC).
project_start_date | 2017-10
project_end_date | 2018-10
duration_months | 12
contract_signed_date | 2017-10-25
contract_original | 498700
contract_final | 517068
change_orders_net | 18368
scope_metrics | 72 residential units (68 standard + 4 Type A ADA) · ~502 fixtures (scope estimate) · 7 residential stories · 19-month duration · 5 executed COs · 11 CORs · 12 permits · 123 invoices
line_items | Array of 1,152 objects (see Line Items tab)
cost_code_summaries | Array of 14 objects (see Cost Code Summaries tab)
job_totals_revenue | -517068
job_totals_expenses | 294712.63
job_totals_net | -222355.37
job_totals_net_due | 0
job_totals_retainage | -25853.4
job_totals_by_source | PR: $178,388.59, AP: $115,060.40, GL: $1,263.64, AR: $-517,068.00

## Line Items
LINE ITEMS — 1,152 TRANSACTIONS
Every transaction line parsed from the 175-page JDR. AR amounts are negative per Sage convention (credits). Retainage is stored in the retainage column (AR only).
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 3 | 0 | 150 | 0 | 150 | 97762 | 0 | 0
100 | Supervision | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 97763 | 0 | 0
100 | Supervision | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
100 | Supervision | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 97956 | 0 | 0
100 | Supervision | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18020 | 0 | 0
100 | Supervision | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98002 | 0 | 0
100 | Supervision | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 98215 | 0 | 0
100 | Supervision | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18280 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18410 | 0 | 0
100 | Supervision | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
100 | Supervision | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18670 | 0 | 0
100 | Supervision | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18734 | 0 | 0
100 | Supervision | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 70.5 | 0 | 70.5 | 98802 | 0 | 0
100 | Supervision | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18954 | 0 | 0
100 | Supervision | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 100000 | 0 | 0
100 | Supervision | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 99998 | 0 | 0
100 | Supervision | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
100 | Supervision | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99998 | 0 | 0
100 | Supervision | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99351 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 99501 | 0 | 0
100 | Supervision | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99576 | 0 | 0
100 | Supervision | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 99649 | 0 | 0
100 | Supervision | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
100 | Supervision | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99936 | 0 | 0
100 | Supervision | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20080 | 0 | 0
100 | Supervision | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 97762 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 5.5 | 0 | 258.5 | 0 | 258.5 | 97763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 17827 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 17891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 17892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 4 | 0 | 188 | 0 | 188 | 97956 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 5 | 0 | 235 | 0 | 235 | 18020 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98002 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98148 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 164.5 | 0 | 164.5 | 98215 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 18280 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18410 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98476 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 18670 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | -125 | 0 | -125 | 18669 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18672 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18733 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 98801 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 141 | 0 | 141 | 98802 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18867 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 94 | 0 | 94 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19206 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99351 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99501 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99649 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20400 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 920518 | 0 | 0
112 | Canout Labor | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 112.5 | 0 | 112.5 | 19968 | 0 | 0
112 | Canout Labor | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | -112.5 | 0 | -112.5 | 920010 | 0 | 0
120 | Roughin Labor | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 304 | 0 | 304 | 17715 | 0 | 0
120 | Roughin Labor | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1032 | 0 | 1032 | 17745 | 0 | 0
120 | Roughin Labor | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 16 | 0 | 288 | 0 | 288 | 17747 | 0 | 0
120 | Roughin Labor | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 16 | 0 | 496 | 0 | 496 | 17750 | 0 | 0
120 | Roughin Labor | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 17769 | 0 | 0
120 | Roughin Labor | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 13 | 0 | 409.5 | 409.5 | 17769 | 0 | 0
120 | Roughin Labor | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 13 | 0 | 370.5 | 370.5 | 17776 | 0 | 0
120 | Roughin Labor | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17776 | 0 | 0
120 | Roughin Labor | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 6 | 0 | 216 | 216 | 17783 | 0 | 0
120 | Roughin Labor | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 17783 | 0 | 0
120 | Roughin Labor | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 7 | 0 | 199.5 | 199.5 | 17789 | 0 | 0
120 | Roughin Labor | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 13 | 0 | 448.5 | 448.5 | 17798 | 0 | 0
120 | Roughin Labor | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 24 | 0 | 552 | 0 | 552 | 17798 | 0 | 0
120 | Roughin Labor | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17804 | 0 | 0
120 | Roughin Labor | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 17807 | 0 | 0
120 | Roughin Labor | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 9 | 0 | 580.5 | 580.5 | 17807 | 0 | 0
120 | Roughin Labor | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 13 | 0 | 351 | 351 | 17809 | 0 | 0
120 | Roughin Labor | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17809 | 0 | 0
120 | Roughin Labor | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 6 | 0 | 279 | 279 | 17812 | 0 | 0
120 | Roughin Labor | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 40 | 0 | 1240 | 0 | 1240 | 17812 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 15 | 0 | 472.5 | 472.5 | 17833 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 17833 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 3.5 | 0 | 94.5 | 94.5 | 17838 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 17838 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 15 | 0 | 427.5 | 427.5 | 17841 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17841 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 8 | 0 | 288 | 288 | 17848 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 17848 | 0 | 0
120 | Roughin Labor | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 7 | 0 | 189 | 189 | 17852 | 0 | 0
120 | Roughin Labor | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 7 | 0 | 199.5 | 199.5 | 17854 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 3.5 | 0 | 120.75 | 120.75 | 17863 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 40 | 0 | 920 | 0 | 920 | 17863 | 0 | 0
120 | Roughin Labor | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 7 | 0 | 189 | 0 | 189 | 17869 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 15 | 0 | 967.5 | 967.5 | 17872 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 17872 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 15 | 0 | 405 | 405 | 17874 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17874 | 0 | 0
120 | Roughin Labor | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 2 | 0 | 93 | 93 | 17877 | 0 | 0
120 | Roughin Labor | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 16 | 0 | 496 | 0 | 496 | 17877 | 0 | 0
120 | Roughin Labor | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 38 | 0 | 1634 | 0 | 1634 | 17891 | 0 | 0
120 | Roughin Labor | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 7 | 0 | 451.5 | 451.5 | 17891 | 0 | 0
120 | Roughin Labor | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 17899 | 0 | 0
120 | Roughin Labor | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 7 | 0 | 189 | 189 | 17904 | 0 | 0
120 | Roughin Labor | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 17904 | 0 | 0
120 | Roughin Labor | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 7 | 0 | 199.5 | 199.5 | 17907 | 0 | 0
120 | Roughin Labor | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 17907 | 0 | 0
120 | Roughin Labor | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 14 | 0 | 462 | 462 | 17908 | 0 | 0
120 | Roughin Labor | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 17914 | 0 | 0
120 | Roughin Labor | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 7 | 0 | 126 | 0 | 126 | 17918 | 0 | 0
120 | Roughin Labor | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 31 | 0 | 713 | 0 | 713 | 17929 | 0 | 0
120 | Roughin Labor | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17935 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 17940 | 0 | 0
120 | Roughin Labor | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 17940 | 0 | 0
120 | Roughin Labor | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 6 | 0 | 207 | 207 | 17957 | 0 | 0
120 | Roughin Labor | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 40 | 0 | 920 | 0 | 920 | 17957 | 0 | 0
120 | Roughin Labor | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 38 | 0 | 798 | 0 | 798 | 17965 | 0 | 0
120 | Roughin Labor | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 4.5 | 0 | 121.5 | 121.5 | 17970 | 0 | 0
120 | Roughin Labor | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 17970 | 0 | 0
120 | Roughin Labor | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 39 | 0 | 741 | 0 | 741 | 17973 | 0 | 0
120 | Roughin Labor | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 17979 | 0 | 0
120 | Roughin Labor | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 7 | 0 | 126 | 0 | 126 | 17982 | 0 | 0
120 | Roughin Labor | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 7 | 0 | 283.5 | 283.5 | 17998 | 0 | 0
120 | Roughin Labor | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 6 | 0 | 387 | 387 | 18002 | 0 | 0
120 | Roughin Labor | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 18002 | 0 | 0
120 | Roughin Labor | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 7 | 0 | 189 | 189 | 18004 | 0 | 0
120 | Roughin Labor | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18004 | 0 | 0
120 | Roughin Labor | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 6 | 0 | 162 | 162 | 18010 | 0 | 0
120 | Roughin Labor | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 1 | 0 | 18 | 0 | 18 | 18010 | 0 | 0
120 | Roughin Labor | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18026 | 0 | 0
120 | Roughin Labor | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18031 | 0 | 0
120 | Roughin Labor | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18034 | 0 | 0
120 | Roughin Labor | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18041 | 0 | 0
120 | Roughin Labor | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 39 | 0 | 897 | 0 | 897 | 18056 | 0 | 0
120 | Roughin Labor | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 40 | 0 | 1720 | 0 | 1720 | 18065 | 0 | 0
120 | Roughin Labor | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 40 | 0 | 720 | 0 | 720 | 18067 | 0 | 0
120 | Roughin Labor | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 18090 | 0 | 0
120 | Roughin Labor | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18095 | 0 | 0
120 | Roughin Labor | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 608 | 0 | 608 | 18098 | 0 | 0
120 | Roughin Labor | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18105 | 0 | 0
120 | Roughin Labor | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18114 | 0 | 0
120 | Roughin Labor | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 30 | 0 | 690 | 0 | 690 | 18120 | 0 | 0
120 | Roughin Labor | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 29 | 0 | 1247 | 0 | 1247 | 18129 | 0 | 0
120 | Roughin Labor | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 32 | 0 | 576 | 0 | 576 | 18131 | 0 | 0
120 | Roughin Labor | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 10 | 0 | 430 | 0 | 430 | 18146 | 0 | 0
120 | Roughin Labor | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 7 | 0 | 220.5 | 220.5 | 18155 | 0 | 0
120 | Roughin Labor | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18155 | 0 | 0
120 | Roughin Labor | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 6.5 | 0 | 175.5 | 175.5 | 18161 | 0 | 0
120 | Roughin Labor | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 18161 | 0 | 0
120 | Roughin Labor | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18164 | 0 | 0
120 | Roughin Labor | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18171 | 0 | 0
120 | Roughin Labor | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 2 | 0 | 42 | 0 | 42 | 18180 | 0 | 0
120 | Roughin Labor | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 16 | 0 | 720 | 0 | 720 | 18181 | 0 | 0
120 | Roughin Labor | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 16 | 0 | 368 | 0 | 368 | 18187 | 0 | 0
120 | Roughin Labor | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 16 | 0 | 288 | 0 | 288 | 18197 | 0 | 0
120 | Roughin Labor | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 672 | 0 | 672 | 18221 | 0 | 0
120 | Roughin Labor | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18227 | 0 | 0
120 | Roughin Labor | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18230 | 0 | 0
120 | Roughin Labor | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18237 | 0 | 0
120 | Roughin Labor | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 15 | 0 | 675 | 0 | 675 | 18247 | 0 | 0
120 | Roughin Labor | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 32 | 0 | 1376 | 0 | 1376 | 18261 | 0 | 0
120 | Roughin Labor | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 840 | 0 | 840 | 18351 | 0 | 0
120 | Roughin Labor | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 18357 | 0 | 0
120 | Roughin Labor | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18360 | 0 | 0
120 | Roughin Labor | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18367 | 0 | 0
120 | Roughin Labor | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 3 | 0 | 135 | 0 | 135 | 18377 | 0 | 0
120 | Roughin Labor | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 37 | 0 | 1591 | 0 | 1591 | 18391 | 0 | 0
120 | Roughin Labor | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 16 | 0 | 688 | 0 | 688 | 18182 | 0 | 0
120 | Roughin Labor | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 504 | 0 | 504 | 18417 | 0 | 0
120 | Roughin Labor | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 18423 | 0 | 0
120 | Roughin Labor | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 456 | 0 | 456 | 18426 | 0 | 0
120 | Roughin Labor | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 24 | 0 | 576 | 0 | 576 | 18433 | 0 | 0
120 | Roughin Labor | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 1.5 | 0 | 67.5 | 0 | 67.5 | 18443 | 0 | 0
120 | Roughin Labor | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 672 | 0 | 672 | 18481 | 0 | 0
120 | Roughin Labor | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 576 | 0 | 576 | 18487 | 0 | 0
120 | Roughin Labor | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 608 | 0 | 608 | 18490 | 0 | 0
120 | Roughin Labor | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18497 | 0 | 0
120 | Roughin Labor | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 1 | 0 | 45 | 0 | 45 | 18508 | 0 | 0
120 | Roughin Labor | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 11 | 0 | 473 | 0 | 473 | 18522 | 0 | 0
120 | Roughin Labor | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 16 | 0 | 336 | 0 | 336 | 18546 | 0 | 0
120 | Roughin Labor | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 18552 | 0 | 0
120 | Roughin Labor | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 760 | 0 | 760 | 18555 | 0 | 0
120 | Roughin Labor | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 32 | 0 | 768 | 0 | 768 | 18562 | 0 | 0
120 | Roughin Labor | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 18 | 0 | 774 | 0 | 774 | 18586 | 0 | 0
120 | Roughin Labor | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 168 | 0 | 168 | 18611 | 0 | 0
120 | Roughin Labor | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 18617 | 0 | 0
120 | Roughin Labor | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 36 | 0 | 684 | 0 | 684 | 18620 | 0 | 0
120 | Roughin Labor | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18628 | 0 | 0
120 | Roughin Labor | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 344 | 0 | 344 | 18652 | 0 | 0
120 | Roughin Labor | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 168 | 0 | 168 | 18677 | 0 | 0
120 | Roughin Labor | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 152 | 0 | 152 | 18686 | 0 | 0
120 | Roughin Labor | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 40 | 0 | 960 | 0 | 960 | 18692 | 0 | 0
120 | Roughin Labor | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 86 | 0 | 86 | 18716 | 0 | 0
120 | Roughin Labor | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 19016 | 0 | 0
120 | Roughin Labor | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 344 | 0 | 344 | 19053 | 0 | 0
120 | Roughin Labor | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 16 | 0 | 288 | 0 | 288 | 19086 | 0 | 0
120 | Roughin Labor | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 432 | 0 | 432 | 19151 | 0 | 0
120 | Roughin Labor | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 172 | 0 | 172 | 19188 | 0 | 0
120 | Roughin Labor | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 4 | 0 | 76 | 0 | 76 | 19222 | 0 | 0
120 | Roughin Labor | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19287 | 0 | 0
120 | Roughin Labor | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 6 | 0 | 258 | 0 | 258 | 19351 | 0 | 0
120 | Roughin Labor | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19366 | 0 | 0
120 | Roughin Labor | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 152 | 0 | 152 | 19369 | 0 | 0
120 | Roughin Labor | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 8 | 0 | 144 | 0 | 144 | 19394 | 0 | 0
120 | Roughin Labor | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 720 | 0 | 720 | 19439 | 0 | 0
120 | Roughin Labor | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 16 | 0 | 288 | 0 | 288 | 19467 | 0 | 0
120 | Roughin Labor | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 86 | 0 | 86 | 19481 | 0 | 0
120 | Roughin Labor | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0.5 | 0 | 22.5 | 0 | 22.5 | 19825 | 0 | 0
120 | Roughin Labor | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 3 | 0 | 93 | 0 | 93 | 19836 | 0 | 0
120 | Roughin Labor | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 112.5 | 0 | 112.5 | 920010 | 0 | 0
120 | Roughin Labor | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 7 | 0 | 315 | 0 | 315 | 20039 | 0 | 0
120 | Roughin Labor | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 93 | 93 | 20050 | 0 | 0
120 | Roughin Labor | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 4 | 0 | 124 | 0 | 124 | 20050 | 0 | 0
120 | Roughin Labor | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 93 | 93 | 20068 | 0 | 0
120 | Roughin Labor | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 12 | 0 | 372 | 0 | 372 | 20068 | 0 | 0
120 | Roughin Labor | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 7 | 0 | 329 | 0 | 329 | 20124 | 0 | 0
120 | Roughin Labor | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 96 | 96 | 20135 | 0 | 0
120 | Roughin Labor | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 5 | 0 | 160 | 0 | 160 | 20135 | 0 | 0
120 | Roughin Labor | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 93 | 93 | 20152 | 0 | 0
120 | Roughin Labor | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 5 | 0 | 155 | 0 | 155 | 20152 | 0 | 0
130 | Finish Labor | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 2.5 | 0 | 105 | 0 | 105 | 19060 | 0 | 0
130 | Finish Labor | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 3 | 0 | 63 | 0 | 63 | 19094 | 0 | 0
130 | Finish Labor | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 6 | 0 | 252 | 0 | 252 | 19129 | 0 | 0
130 | Finish Labor | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 8 | 0 | 128 | 0 | 128 | 19146 | 0 | 0
130 | Finish Labor | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 8 | 0 | 128 | 0 | 128 | 19183 | 0 | 0
130 | Finish Labor | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 8 | 0 | 336 | 0 | 336 | 19196 | 0 | 0
130 | Finish Labor | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 16 | 0 | 432 | 0 | 432 | 19231 | 0 | 0
130 | Finish Labor | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 9.5 | 0 | 399 | 0 | 399 | 19265 | 0 | 0
130 | Finish Labor | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 144 | 0 | 144 | 19287 | 0 | 0
130 | Finish Labor | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19299 | 0 | 0
130 | Finish Labor | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 16 | 0 | 256 | 0 | 256 | 19335 | 0 | 0
130 | Finish Labor | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 1.5 | 0 | 63 | 0 | 63 | 19339 | 0 | 0
130 | Finish Labor | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 24 | 0 | 432 | 0 | 432 | 19348 | 0 | 0
130 | Finish Labor | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 32.5 | 0 | 520 | 0 | 520 | 19360 | 0 | 0
130 | Finish Labor | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 34.5 | 0 | 931.5 | 0 | 931.5 | 19378 | 0 | 0
130 | Finish Labor | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 32 | 0 | 576 | 0 | 576 | 19380 | 0 | 0
130 | Finish Labor | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 10.5 | 0 | 168 | 0 | 168 | 19402 | 0 | 0
130 | Finish Labor | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 34.5 | 0 | 552 | 0 | 552 | 19412 | 0 | 0
130 | Finish Labor | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 2.5 | 0 | 40 | 0 | 40 | 19415 | 0 | 0
130 | Finish Labor | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 2 | 0 | 84 | 0 | 84 | 19416 | 0 | 0
130 | Finish Labor | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 18.5 | 0 | 333 | 0 | 333 | 19425 | 0 | 0
130 | Finish Labor | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 8 | 0 | 192 | 192 | 19434 | 0 | 0
130 | Finish Labor | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 16 | 0 | 256 | 0 | 256 | 19434 | 0 | 0
130 | Finish Labor | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19451 | 0 | 0
130 | Finish Labor | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 8 | 0 | 216 | 216 | 19453 | 0 | 0
130 | Finish Labor | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 16 | 0 | 288 | 0 | 288 | 19453 | 0 | 0
130 | Finish Labor | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 8 | 0 | 372 | 372 | 19471 | 0 | 0
130 | Finish Labor | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 11 | 0 | 341 | 0 | 341 | 19471 | 0 | 0
130 | Finish Labor | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 16 | 0 | 256 | 0 | 256 | 19475 | 0 | 0
130 | Finish Labor | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 10 | 0 | 240 | 240 | 19476 | 0 | 0
130 | Finish Labor | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19476 | 0 | 0
130 | Finish Labor | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 4 | 0 | 96 | 96 | 19487 | 0 | 0
130 | Finish Labor | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 40 | 0 | 640 | 0 | 640 | 19487 | 0 | 0
130 | Finish Labor | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 504 | 504 | 19490 | 0 | 0
130 | Finish Labor | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 7.5 | 0 | 315 | 0 | 315 | 19490 | 0 | 0
130 | Finish Labor | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 38 | 0 | 684 | 0 | 684 | 19499 | 0 | 0
130 | Finish Labor | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19526 | 0 | 0
130 | Finish Labor | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 32 | 0 | 512 | 0 | 512 | 19551 | 0 | 0
130 | Finish Labor | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 20 | 0 | 320 | 0 | 320 | 19562 | 0 | 0
130 | Finish Labor | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 2 | 0 | 84 | 0 | 84 | 19565 | 0 | 0
130 | Finish Labor | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 32 | 0 | 576 | 0 | 576 | 19574 | 0 | 0
130 | Finish Labor | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19600 | 0 | 0
130 | Finish Labor | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 16 | 0 | 256 | 0 | 256 | 19624 | 0 | 0
130 | Finish Labor | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19625 | 0 | 0
130 | Finish Labor | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 40 | 0 | 640 | 0 | 640 | 19635 | 0 | 0
130 | Finish Labor | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 4.5 | 0 | 189 | 0 | 189 | 19638 | 0 | 0
130 | Finish Labor | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 32 | 0 | 576 | 0 | 576 | 19647 | 0 | 0
130 | Finish Labor | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 40 | 0 | 1080 | 0 | 1080 | 19672 | 0 | 0
130 | Finish Labor | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 40 | 0 | 640 | 0 | 640 | 19698 | 0 | 0
130 | Finish Labor | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 35 | 0 | 560 | 0 | 560 | 19708 | 0 | 0
130 | Finish Labor | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 4 | 0 | 168 | 0 | 168 | 19711 | 0 | 0
130 | Finish Labor | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 39.5 | 0 | 711 | 0 | 711 | 19720 | 0 | 0
130 | Finish Labor | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 16 | 0 | 432 | 0 | 432 | 19750 | 0 | 0
130 | Finish Labor | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 6 | 0 | 108 | 0 | 108 | 19752 | 0 | 0
130 | Finish Labor | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 16 | 0 | 256 | 0 | 256 | 19774 | 0 | 0
130 | Finish Labor | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 16 | 0 | 256 | 0 | 256 | 19782 | 0 | 0
130 | Finish Labor | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 13.5 | 0 | 567 | 0 | 567 | 19785 | 0 | 0
130 | Finish Labor | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 16 | 0 | 288 | 0 | 288 | 19792 | 0 | 0
130 | Finish Labor | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 24 | 0 | 648 | 0 | 648 | 19816 | 0 | 0
130 | Finish Labor | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 15 | 0 | 240 | 0 | 240 | 19842 | 0 | 0
130 | Finish Labor | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 9 | 0 | 378 | 0 | 378 | 19854 | 0 | 0
130 | Finish Labor | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 16 | 0 | 288 | 0 | 288 | 19863 | 0 | 0
130 | Finish Labor | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 4 | 0 | 108 | 0 | 108 | 19887 | 0 | 0
130 | Finish Labor | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 4 | 0 | 72 | 0 | 72 | 19934 | 0 | 0
130 | Finish Labor | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 4 | 0 | 108 | 0 | 108 | 20030 | 0 | 0
130 | Finish Labor | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 4 | 0 | 72 | 0 | 72 | 20078 | 0 | 0
130 | Finish Labor | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 4 | 0 | 120 | 0 | 120 | 20185 | 0 | 0
130 | Finish Labor | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 3 | 0 | 135 | 135 | 20185 | 0 | 0
130 | Finish Labor | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20254 | 0 | 0
130 | Finish Labor | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | 64 | 0 | 64 | 20255 | 0 | 0
130 | Finish Labor | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 2 | 0 | -64 | 0 | -64 | 920306 | 0 | 0
130 | Finish Labor | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 2 | 0 | 60 | 0 | 60 | 20325 | 0 | 0
130 | Finish Labor | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 3 | 0 | 132 | 0 | 132 | 20725 | 0 | 0
130 | Finish Labor | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21303 | 0 | 0
211 | Garage Material | GL | 659 | 10/31/17 | 10/31/17 | Mat | Req 3355 |  |  |  |  | 56.32 |  | 0 | 0
211 | Garage Material | GL | 141 | 11/09/17 | 11/09/17 | Mat | Req 3264 |  |  |  |  | 58 |  | 0 | 0
211 | Garage Material | GL | 224 | 11/10/17 | 11/10/17 | Mat | Req Adj |  |  |  |  | -114.32 |  | 0 | 0
211 | Garage Material | GL | 516 | 11/22/17 | 11/22/17 | Mat | Req 3298 |  |  |  |  | 94.29 |  | 0 | 0
211 | Garage Material | GL | 599 | 11/22/17 | 11/22/17 | Mat | Req adj |  |  |  |  | -94.29 |  | 0 | 0
220 | Roughin Material | AP | 471 | 10/18/17 | 10/25/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 6612.75 | S8460744.001 | 0 | 0
220 | Roughin Material | AP | 472 | 10/18/17 | 10/25/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 876.9 | S8460744.002 | 0 | 0
220 | Roughin Material | AP | 643 | 10/23/17 | 10/26/17 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 678.31 | S011281568.001 | 0 | 0
220 | Roughin Material | AP | 651 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 107.84 | 4244064-00 | 0 | 0
220 | Roughin Material | AP | 652 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 2937.29 | 7130256-00 | 0 | 0
220 | Roughin Material | AP | 653 | 10/18/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 245.1 | 7130258-00 | 0 | 0
220 | Roughin Material | AP | 654 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 99.84 | 4244193-00 | 0 | 0
220 | Roughin Material | AP | 655 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 351.03 | 4244198-00 | 0 | 0
220 | Roughin Material | AP | 656 | 10/23/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 355.46 | 7130368-00 | 0 | 0
220 | Roughin Material | AP | 657 | 10/25/17 | 10/26/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 711.92 | 7130451-00 | 0 | 0
220 | Roughin Material | AP | 102 | 10/25/17 | 11/01/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | -711.92 | 7130451-00A | 0 | 0
220 | Roughin Material | AP | 103 | 10/25/17 | 11/01/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 711.93 | 7130451-00B | 0 | 0
220 | Roughin Material | GL | 74 | 11/02/17 | 11/02/17 | CK#5013 | Esteban Quintanilla |  |  |  |  | 58.09 |  | 0 | 0
220 | Roughin Material | AP | 91 | 10/23/17 | 11/06/17 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 68.35 | 7130384-00 | 0 | 0
220 | Roughin Material | AP | 109 | 11/01/17 | 11/07/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 895.52 | S8482800.002 | 0 | 0
220 | Roughin Material | AP | 110 | 11/02/17 | 11/07/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | -895.52 | S8482800.003 | 0 | 0
220 | Roughin Material | AP | 126 | 10/26/17 | 11/07/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 449.17 | 4244360-00 | 0 | 0
220 | Roughin Material | GL | 224 | 11/10/17 | 11/10/17 | Mat | Req Adj |  |  |  |  | 114.32 |  | 0 | 0
220 | Roughin Material | AP | 274 | 10/30/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1376 | 4244430-00 | 0 | 0
220 | Roughin Material | AP | 275 | 10/31/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 186.78 | 4244539-00 | 0 | 0
220 | Roughin Material | AP | 276 | 11/01/17 | 11/13/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 146.31 | 4244578-00 | 0 | 0
220 | Roughin Material | GL | 359 | 11/17/17 | 11/17/17 | Mat | Req 3265 |  |  |  |  | 1419.55 |  | 0 | 0
220 | Roughin Material | AP | 415 | 11/08/17 | 11/20/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1769.8 | 4244647-00 | 0 | 0
220 | Roughin Material | GL | 498 | 11/21/17 | 11/21/17 | CK#5020 | Esteban Quintanilla |  |  |  |  | 10.46 |  | 0 | 0
220 | Roughin Material | GL | 521 | 11/22/17 | 11/22/17 | Mat | Req 3293 |  |  |  |  | 1238.06 |  | 0 | 0
220 | Roughin Material | GL | 599 | 11/22/17 | 11/22/17 | Mat | Req adj |  |  |  |  | 94.29 |  | 0 | 0
220 | Roughin Material | AP | 613 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 7602.67 | S8491558.001 | 0 | 0
220 | Roughin Material | AP | 614 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 444.99 | S8491558.002 | 0 | 0
220 | Roughin Material | AP | 615 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 20.74 | S8491558.003 | 0 | 0
220 | Roughin Material | AP | 616 | 11/10/17 | 11/22/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 289.77 | S8494995.001 | 0 | 0
220 | Roughin Material | GL | 73 | 12/01/17 | 12/01/17 | Mat | Req 4026 |  |  |  |  | 381.16 |  | 0 | 0
220 | Roughin Material | GL | 74 | 12/01/17 | 12/01/17 | Mat | Req 4025 |  |  |  |  | -1292.1 |  | 0 | 0
220 | Roughin Material | GL | 118 | 12/01/17 | 12/01/17 | Mat | Req 4051 |  |  |  |  | 1918.36 |  | 0 | 0
220 | Roughin Material | AP | 136 | 11/13/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 47.4 | S8494995.002 | 0 | 0
220 | Roughin Material | AP | 137 | 11/14/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 865.34 | S8419558.004 | 0 | 0
220 | Roughin Material | AP | 138 | 11/15/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 128.77 | S8491558.005 | 0 | 0
220 | Roughin Material | AP | 139 | 11/15/17 | 12/01/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 253.32 | S8491558.006 | 0 | 0
220 | Roughin Material | AP | 163 | 11/07/17 | 12/01/17 | 1234CO | Capital One Credit Card |  |  |  |  | 108.86 | 110717 | 0 | 0
220 | Roughin Material | AP | 200 | 11/21/17 | 12/06/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 4977.68 | S8508933.001 | 0 | 0
220 | Roughin Material | AP | 201 | 11/22/17 | 12/06/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 653.15 | S8512822.001 | 0 | 0
220 | Roughin Material | GL | 566 | 12/07/17 | 12/07/17 | Mat | Req 4077 |  |  |  |  | 445.58 |  | 0 | 0
220 | Roughin Material | AP | 304 | 11/13/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 160 | 4244982-00 | 0 | 0
220 | Roughin Material | AP | 305 | 11/13/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 245.5 | 4244983-00 | 0 | 0
220 | Roughin Material | AP | 306 | 11/15/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 516.02 | 4245080-00 | 0 | 0
220 | Roughin Material | AP | 307 | 11/21/17 | 12/08/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 199.44 | 4245268-00 | 0 | 0
220 | Roughin Material | AP | 353 | 11/02/17 | 12/12/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 74.07 | 4244655-00 | 0 | 0
220 | Roughin Material | AP | 354 | 11/01/17 | 12/12/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 895.52 | S8482800.001 | 0 | 0
220 | Roughin Material | AP | 355 | 11/01/17 | 12/12/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 215.22 | S8512822.002 | 0 | 0
220 | Roughin Material | AP | 359 | 11/28/17 | 12/13/17 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 99.6 | 5759307 | 0 | 0
220 | Roughin Material | AP | 372 | 11/27/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 130.61 | S8515017.001 | 0 | 0
220 | Roughin Material | AP | 373 | 12/04/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 152.2 | S8525784.001 | 0 | 0
220 | Roughin Material | AP | 374 | 12/04/17 | 12/13/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 77.2 | S8525784.002 | 0 | 0
220 | Roughin Material | GL | 720 | 12/21/17 | 12/21/17 | CK#5032 | Esteban Quintanilla |  |  |  |  | 11.52 |  | 0 | 0
220 | Roughin Material | GL | 735 | 12/22/17 | 12/22/17 | Mat | Req 3366 |  |  |  |  | -1243.91 |  | 0 | 0
220 | Roughin Material | GL | 736 | 12/22/17 | 12/22/17 | Mat | Req 3384 |  |  |  |  | 32 |  | 0 | 0
220 | Roughin Material | GL | 863 | 12/28/17 | 12/28/17 | Mat | Req 4097 |  |  |  |  | 788.8 |  | 0 | 0
220 | Roughin Material | AP | 925 | 12/08/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 1490.72 | S8508933.003 | 0 | 0
220 | Roughin Material | AP | 926 | 12/08/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 617.08 | S8531719.001 | 0 | 0
220 | Roughin Material | AP | 927 | 12/11/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 681.24 | S8534488.001 | 0 | 0
220 | Roughin Material | AP | 928 | 12/11/17 | 12/31/17 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 32 | S8534488.002 | 0 | 0
220 | Roughin Material | AP | 953 | 12/19/17 | 12/31/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 121.12 | 4246187-00 | 0 | 0
220 | Roughin Material | AP | 297 | 12/08/17 | 01/01/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | -617.08 | S8531719.001A | 0 | 0
220 | Roughin Material | GL | 83 | 01/05/18 | 01/05/18 | Mat | Req 4109 |  |  |  |  | -512 |  | 0 | 0
220 | Roughin Material | GL | 85 | 01/05/18 | 01/05/18 | Adj | [5 empty] | -545.78 |  | 0 | 0
220 | Roughin Material | GL | 86 | 01/05/18 | 01/05/18 | Mat | Req 3361 |  |  |  |  | -1351.59 |  | 0 | 0
220 | Roughin Material | GL | 87 | 01/05/18 | 01/05/18 | Mat | Req 3360 |  |  |  |  | -1535.83 |  | 0 | 0
220 | Roughin Material | AP | 146 | 12/28/17 | 01/08/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 360.29 | 4246441-00 | 0 | 0
220 | Roughin Material | AP | 148 | 12/21/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 196.98 | 4246292-00 | 0 | 0
220 | Roughin Material | AP | 149 | 12/28/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 138.3 | 4846240-00 | 0 | 0
220 | Roughin Material | AP | 150 | 12/29/17 | 01/08/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 99.76 | 7132154-00 | 0 | 0
220 | Roughin Material | AP | 186 | 12/18/17 | 01/09/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 27.31 | S8545824.001 | 0 | 0
220 | Roughin Material | GL | 329 | 01/16/18 | 01/16/18 | Mat | Req 3421 |  |  |  |  | 452.7 |  | 0 | 0
220 | Roughin Material | AP | 358 | 01/05/18 | 01/16/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 108.71 | 7132385-00 | 0 | 0
220 | Roughin Material | AP | 367 | 01/03/18 | 01/17/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 59.12 | 4246566-00 | 0 | 0
220 | Roughin Material | GL | 384 | 01/17/18 | 01/17/18 | Mat | Req 3441 |  |  |  |  | -1683.85 |  | 0 | 0
220 | Roughin Material | GL | 385 | 01/17/18 | 01/17/18 | Mat | Req 3442 |  |  |  |  | -604.62 |  | 0 | 0
220 | Roughin Material | GL | 386 | 01/17/18 | 01/17/18 | Mat | Req 3443 |  |  |  |  | -203.9 |  | 0 | 0
220 | Roughin Material | GL | 493 | 01/22/18 | 01/22/18 | Mat | Req 4131 |  |  |  |  | -1064.47 |  | 0 | 0
220 | Roughin Material | GL | 669 | 01/30/18 | 01/30/18 | Mat | Req 4138 |  |  |  |  | 34 |  | 0 | 0
220 | Roughin Material | GL | 677 | 01/30/18 | 01/30/18 | Mat | Req 3459 |  |  |  |  | 47.76 |  | 0 | 0
220 | Roughin Material | AP | 122 | 01/16/18 | 02/06/18 | 2048CS | Consolidated Supply Co. $Ballinger |  |  |  |  | 1726.69 | S8534488.003 | 0 | 0
220 | Roughin Material | AP | 123 | 01/12/18 | 02/06/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 1272.18 | 4246869-00 | 0 | 0
220 | Roughin Material | AP | 290 | 01/17/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 2381.75 | 4246805-00 | 0 | 0
220 | Roughin Material | AP | 291 | 01/19/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 34.9 | 4247111-00 | 0 | 0
220 | Roughin Material | AP | 292 | 01/22/18 | 02/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 105.55 | 4247204-00 | 0 | 0
220 | Roughin Material | AP | 102 | 02/22/18 | 03/01/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 589.93 | S8630865.001 | 0 | 0
220 | Roughin Material | GL | 293 | 03/08/18 | 03/08/18 | CK#5064 | Joseph Barnhart |  |  |  |  | 18.7 |  | 0 | 0
220 | Roughin Material | GL | 218 | 03/09/18 | 03/09/18 | Mat | Req 4130 |  |  |  |  | -1282.64 |  | 0 | 0
220 | Roughin Material | GL | 219 | 03/09/18 | 03/09/18 | Mat | Req 3522 |  |  |  |  | 545.36 |  | 0 | 0
220 | Roughin Material | AP | 245 | 02/23/18 | 03/12/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 995.26 | 4248579-00 | 0 | 0
220 | Roughin Material | GL | 273 | 03/13/18 | 03/13/18 | Mat | Req 3528 |  |  |  |  | 133.76 |  | 0 | 0
220 | Roughin Material | AP | 498 | 03/07/18 | 03/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 327.02 | 4249116-00 | 0 | 0
220 | Roughin Material | AP | 396 | 03/02/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 231.92 | 6007539 | 0 | 0
220 | Roughin Material | AP | 398 | 03/07/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 42.68 | 6020564 | 0 | 0
220 | Roughin Material | AP | 399 | 03/08/18 | 03/16/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 29.67 | 6023871 | 0 | 0
220 | Roughin Material | AP | 404 | 03/14/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 13.1 | 6035496 | 0 | 0
220 | Roughin Material | GL | 455 | 03/20/18 | 03/20/18 | Mat | Req 3561 |  |  |  |  | 181.19 |  | 0 | 0
220 | Roughin Material | AP | 469 | 02/26/18 | 03/20/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 518.12 | 42485579-01 | 0 | 0
220 | Roughin Material | GL | 829 | 03/31/18 | 03/31/18 | Mat | Req 4245 |  |  |  |  | 1624.4 |  | 0 | 0
220 | Roughin Material | GL | 847 | 03/31/18 | 03/31/18 | Mat | Req 4281 |  |  |  |  | 850.32 |  | 0 | 0
220 | Roughin Material | AP | 879 | 03/21/18 | 03/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 308.39 | S011709965.001 | 0 | 0
220 | Roughin Material | GL | 231 | 04/10/18 | 04/01/18 | Mat | Req 4314 |  |  |  |  | 585.37 |  | 0 | 0
220 | Roughin Material | AP | 235 | 03/26/18 | 04/01/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.69 | 4249838-00 | 0 | 0
220 | Roughin Material | AP | 200 | 03/26/18 | 04/10/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 88.87 | 6070866 | 0 | 0
220 | Roughin Material | GL | 693 | 04/10/18 | 04/10/18 | Mat | Req 4314 |  |  |  |  | -585.37 |  | 0 | 0
220 | Roughin Material | AP | 384 | 04/04/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 173.81 | 4250218-00 | 0 | 0
220 | Roughin Material | AP | 385 | 04/05/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 18.32 | 4250296-00 | 0 | 0
220 | Roughin Material | AP | 563 | 04/11/18 | 04/24/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 209.46 | 6112528 | 0 | 0
220 | Roughin Material | AP | 811 | 04/09/18 | 04/30/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 34.21 | 4250428-00 | 0 | 0
220 | Roughin Material | AP | 150 | 04/17/18 | 05/01/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 286 | 4250786-00 | 0 | 0
220 | Roughin Material | GL | 121 | 05/04/18 | 05/04/18 | Mat | Req 3634 |  |  |  |  | 11.43 |  | 0 | 0
220 | Roughin Material | GL | 323 | 05/11/18 | 05/11/18 | Mat | Req 4348 |  |  |  |  | -498.62 |  | 0 | 0
220 | Roughin Material | AP | 339 | 04/23/18 | 05/11/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 146.65 | 4251044-00 | 0 | 0
220 | Roughin Material | AP | 523 | 05/07/18 | 05/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 40.95 | 6186685 | 0 | 0
220 | Roughin Material | AP | 524 | 05/10/18 | 05/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 9.32 | 6189321 | 0 | 0
220 | Roughin Material | AP | 595 | 05/11/18 | 05/22/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1005.48 | 6201459 | 0 | 0
220 | Roughin Material | AP | 596 | 05/11/18 | 05/22/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1004.3 | 6201473 | 0 | 0
220 | Roughin Material | GL | 605 | 04/27/18 | 05/22/18 | Mat | Req 4375 |  |  |  |  | 47.68 |  | 0 | 0
220 | Roughin Material | GL | 627 | 05/22/18 | 05/22/18 | Mat | Req 4377 |  |  |  |  | 217.33 |  | 0 | 0
220 | Roughin Material | GL | 180 | 06/05/18 | 06/05/18 | Mat | Req 3676 |  |  |  |  | -26.16 |  | 0 | 0
220 | Roughin Material | AP | 205 | 05/17/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 641.73 | S011860284.001 | 0 | 0
220 | Roughin Material | AP | 244 | 05/11/18 | 06/06/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 66.19 | 6202541 | 0 | 0
220 | Roughin Material | AP | 389 | 05/24/18 | 06/11/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 184.2 | 4252427-00 | 0 | 0
220 | Roughin Material | AP | 627 | 05/30/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 754.87 | 6245034 | 0 | 0
220 | Roughin Material | AP | 628 | 05/31/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 714.53 | 6245211 | 0 | 0
220 | Roughin Material | AP | 629 | 06/08/18 | 06/19/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 110.23 | 6279267 | 0 | 0
220 | Roughin Material | AP | 656 | 06/18/18 | 06/20/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 24.92 | 6289123 | 0 | 0
220 | Roughin Material | AP | 560 | 06/26/18 | 07/20/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 22.1 | 4253753-00 | 0 | 0
230 | Finish Material | GL | 660 | 10/31/17 | 10/31/17 | Mat | Req 3354 |  |  |  |  | 818 |  | 0 | 0
230 | Finish Material | GL | 364 | 11/17/17 | 11/17/17 | Mat | Req 3277 |  |  |  |  | 633.8 |  | 0 | 0
230 | Finish Material | AP | 766 | 12/08/17 | 12/22/17 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 805.7 | 4245839-00 | 0 | 0
230 | Finish Material | AP | 176 | 01/05/18 | 01/09/18 | 7230BB | Best Bath Systems |  |  |  |  | 1178.07 | 182715-IN | 0 | 0
230 | Finish Material | AP | 381 | 01/08/18 | 01/17/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 2249.2 | S011393325.001 | 0 | 0
230 | Finish Material | AP | 402 | 03/03/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 323.28 | 6006947 | 0 | 0
230 | Finish Material | AP | 403 | 03/09/18 | 03/16/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5495.71 | 5966585 | 0 | 0
230 | Finish Material | AP | 415 | 03/07/18 | 03/19/18 | 1231KS | Keller Supply Company |  |  |  |  | 1220.72 | S011493993.001 | 0 | 0
230 | Finish Material | AP | 429 | 03/06/18 | 03/19/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 130.11 | S011613223.001 | 0 | 0
230 | Finish Material | AP | 430 | 03/12/18 | 03/19/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 2598.15 | S011613223.002 | 0 | 0
230 | Finish Material | AP | 669 | 03/14/18 | 03/26/18 | 5560CH | California Hydronics Corp |  |  |  |  | 1859 | 2089360 | 0 | 0
230 | Finish Material | AP | 4 | 03/22/18 | 04/04/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 809.1 | S011684919.001 | 0 | 0
230 | Finish Material | AP | 5 | 04/23/18 | 04/04/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 3591.29 | S011613223.003 | 0 | 0
230 | Finish Material | AP | 204 | 04/02/18 | 04/10/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5818.99 | 5966610 | 0 | 0
230 | Finish Material | AP | 223 | 03/28/18 | 04/10/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 701.98 | S011613347.001 | 0 | 0
230 | Finish Material | AP | 224 | 04/03/18 | 04/10/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6319.56 | S011613212.001 | 0 | 0
230 | Finish Material | AP | 226 | 04/02/18 | 04/10/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 105 | 6087954 | 0 | 0
230 | Finish Material | GL | 693 | 04/10/18 | 04/10/18 | Mat | Req 4314 |  |  |  |  | 585.37 |  | 0 | 0
230 | Finish Material | AP | 255 | 04/10/18 | 04/11/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6319.56 | S011613145.001 | 0 | 0
230 | Finish Material | AP | 365 | 03/27/18 | 04/13/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 199.56 | 4249888-00 | 0 | 0
230 | Finish Material | AP | 366 | 03/30/18 | 04/13/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 29.55 | 4249952-00 | 0 | 0
230 | Finish Material | AP | 556 | 04/19/18 | 04/20/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 6310.56 | S011613118.001 | 0 | 0
230 | Finish Material | AP | 394 | 04/05/18 | 04/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 423.67 | 4250295-00 | 0 | 0
230 | Finish Material | GL | 709 | 04/27/18 | 04/27/18 | Mat | Req 3595 |  |  |  |  | 177.39 |  | 0 | 0
230 | Finish Material | AP | 798 | 04/06/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 5.46 | 040618 | 0 | 0
230 | Finish Material | AP | 12 | 04/09/18 | 05/02/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5818.99 | 5966617 | 0 | 0
230 | Finish Material | AP | 13 | 04/20/18 | 05/02/18 | 2048FE | Ferguson Enterprises, Inc. $Ballinger |  |  |  |  | 5950.39 | 5966628 | 0 | 0
230 | Finish Material | GL | 120 | 05/04/18 | 05/04/18 | Mat | Req 3635 |  |  |  |  | 293.43 |  | 0 | 0
230 | Finish Material | AP | 182 | 04/23/18 | 05/09/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 11.22 | 4251019-00 | 0 | 0
230 | Finish Material | GL | 324 | 05/11/18 | 05/11/18 | Mat | Req 4349 |  |  |  |  | -163.42 |  | 0 | 0
230 | Finish Material | AP | 340 | 04/25/18 | 05/11/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 29.97 | 4251148-00 | 0 | 0
230 | Finish Material | AP | 378 | 04/26/18 | 05/15/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 70.82 | S011812053.001 | 0 | 0
230 | Finish Material | AP | 379 | 05/07/18 | 05/15/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 1011.99 | S011613347.002 | 0 | 0
230 | Finish Material | GL | 416 | 05/17/18 | 05/17/18 | Mat | Req 4376 |  |  |  |  | 228.58 |  | 0 | 0
230 | Finish Material | AP | 570 | 05/02/18 | 05/21/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 52.5 | 4251476-00 | 0 | 0
230 | Finish Material | AP | 725 | 05/09/18 | 05/23/18 | 2047RS | Rosen Supply Company, Inc. $Green Lake |  |  |  |  | 529.2 | 4251773-00 | 0 | 0
230 | Finish Material | AP | 730 | 05/14/18 | 05/23/18 | 2048RS | Rosen Supply Company, Inc. $Ballinger |  |  |  |  | 78.72 | 4251930-00 | 0 | 0
230 | Finish Material | AP | 875 | 05/09/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 4.23 | 050918C | 0 | 0
230 | Finish Material | GL | 110 | 06/01/18 | 06/01/18 | Mat | Req 3670 |  |  |  |  | -153.16 |  | 0 | 0
230 | Finish Material | GL | 181 | 06/05/18 | 06/05/18 | Mat | Req 3675 |  |  |  |  | -24.7 |  | 0 | 0
230 | Finish Material | AP | 206 | 05/21/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | -281.89 | S011613347.003 | 0 | 0
230 | Finish Material | AP | 207 | 05/21/18 | 06/05/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 183.22 | S011613347.004 | 0 | 0
230 | Finish Material | AP | 601 | 06/13/18 | 06/18/18 | 7230BB | Best Bath Systems |  |  |  |  | 505.56 | 189271-IN | 0 | 0
230 | Finish Material | AP | 684 | 06/29/18 | 07/16/18 | 2048KS | Keller Supply Co. $Ballinger |  |  |  |  | 33.25 | S012018642.001 | 0 | 0
230 | Finish Material | AP | 434 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.8 | 4253753-01 | 0 | 0
230 | Finish Material | AP | 445 | 07/18/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.8 | 4253753-02 | 0 | 0
230 | Finish Material | GL | 683 | 08/22/18 | 08/22/18 | Mat | Req 4602 |  |  |  |  | 37 |  | 0 | 0
230 | Finish Material | AP | 687 | 07/26/18 | 08/22/18 | 1231KS | Keller Supply Company |  |  |  |  | 328.98 | S012072728.001 | 0 | 0
230 | Finish Material | AP | 823 | 07/30/18 | 08/24/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 441.35 | 6401357 | 0 | 0
230 | Finish Material | AP | 219 | 08/16/18 | 09/10/18 | 1231KS | Keller Supply Company |  |  |  |  | -183.22 | S012198021.001 | 0 | 0
230 | Finish Material | AP | 443 | 08/13/18 | 09/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 427.33 | 4255867-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 125 | 12/01/17 | 12/01/17 | Mat | Req 4072 |  |  |  |  | -545.78 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 85 | 01/05/18 | 01/05/18 | Adj | [5 empty] | 545.78 |  | 0 | 0
600 | Subcontractor | AP | 844 | 04/26/18 | 04/30/18 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 115 | 18042606 | 0 | 0
601 | Engineering/Plans | AP | 542 | 11/16/17 | 11/22/17 | 1625FE | Franklin Engineering |  |  |  |  | 772.5 | 6738 | 0 | 0
995 | Payroll Burden | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 457.69 |  | 0 | 0
995 | Payroll Burden | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 114.64 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 181.61 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 164.32 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 198.91 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 257.45 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 155.67 |  | 0 | 0
995 | Payroll Burden | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 123.74 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 549.94 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 209.55 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 41.91 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 189.6 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 429.09 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 179.62 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 219.98 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 724.68 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 200.24 |  | 0 | 0
995 | Payroll Burden | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.48 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 204.9 |  | 0 | 0
995 | Payroll Burden | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 316.22 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 353.91 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 53.89 |  | 0 | 0
995 | Payroll Burden | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 328.63 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 125.73 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 171.63 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 7.98 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 397.82 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 762.82 |  | 0 | 0
995 | Payroll Burden | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 553.04 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 190.71 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 97.79 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 77.83 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 18.63 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 299.36 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 610.26 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 705.61 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 305.13 |  | 0 | 0
995 | Payroll Burden | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 29.94 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.96 |  | 0 | 0
995 | Payroll Burden | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 209.78 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 343.27 |  | 0 | 0
995 | Payroll Burden | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -55.44 |  | 0 | 0
995 | Payroll Burden | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 152.56 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 76.28 |  | 0 | 0
995 | Payroll Burden | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.71 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 176.96 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 114.42 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 230.62 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 413.12 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 147.69 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 151.23 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 303.35 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 315.33 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 251.46 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 9.98 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -49.89 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 164.98 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 145.91 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 41.25 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 68.74 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -28.38 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 10/18/17 | 10/20/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 10/18/17 | 10/20/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 78.95 |  | 0 | 0
998 | Payroll Taxes | PR | 335 | 10/18/17 | 10/20/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 10/18/17 | 10/20/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 350 | 10/18/17 | 10/20/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.78 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 10/18/17 | 10/20/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 10/25/17 | 10/27/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 31.33 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 28.34 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 10/25/17 | 10/27/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 10/25/17 | 10/27/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 10/25/17 | 10/27/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 34.31 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 10/25/17 | 10/27/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 10/25/17 | 10/27/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 10/25/17 | 10/27/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 44.41 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 26.85 |  | 0 | 0
998 | Payroll Taxes | PR | 530 | 10/25/17 | 10/27/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 21.34 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 10/25/17 | 10/27/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 94.86 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 10/25/17 | 10/27/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 36.15 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/01/17 | 11/03/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 7.23 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/01/17 | 11/03/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 32.7 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/01/17 | 11/03/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/01/17 | 11/03/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 11/01/17 | 11/03/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 11/01/17 | 11/03/17 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 9.24 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/01/17 | 11/03/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 11/01/17 | 11/03/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 74.01 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/01/17 | 11/03/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 30.98 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/01/17 | 11/03/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 11/01/17 | 11/03/17 | RI87 | Rivera, Jorge A | 0 | 0 | 0 | 0 | 37.94 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/01/17 | 11/03/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 11/01/17 | 11/03/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 125 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 11/08/17 | 11/10/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 34.54 |  | 0 | 0
998 | Payroll Taxes | PR | 156 | 11/08/17 | 11/10/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 11/08/17 | 11/10/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.26 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 11/08/17 | 11/10/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 165 | 11/08/17 | 11/10/17 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 35.34 |  | 0 | 0
998 | Payroll Taxes | PR | 171 | 11/08/17 | 11/10/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 175 | 11/08/17 | 11/10/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 11/08/17 | 11/10/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 54.54 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 11/08/17 | 11/10/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 197 | 11/08/17 | 11/10/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 213 | 11/08/17 | 11/10/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 11/15/17 | 11/17/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 11/15/17 | 11/17/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 61.05 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 9.29 |  | 0 | 0
998 | Payroll Taxes | PR | 295 | 11/15/17 | 11/17/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 11/15/17 | 11/17/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 56.69 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 11/15/17 | 11/17/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 11/15/17 | 11/17/17 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 11/15/17 | 11/17/17 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.69 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 29.61 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 11/15/17 | 11/17/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 11/15/17 | 11/17/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 11/15/17 | 11/17/17 | SA51 | Sanchez, Derli | 0 | 0 | 0 | 0 | 1.38 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 11/15/17 | 11/17/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 432 | 11/22/17 | 11/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 11/22/17 | 11/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 11/22/17 | 11/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 11/22/17 | 11/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 462 | 11/22/17 | 11/22/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 68.62 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 11/22/17 | 11/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 131.58 |  | 0 | 0
998 | Payroll Taxes | PR | 473 | 11/22/17 | 11/22/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 11/22/17 | 11/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 11/29/17 | 12/01/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 11/29/17 | 12/01/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 11/29/17 | 12/01/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 11/29/17 | 12/01/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 11/29/17 | 12/01/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 11/29/17 | 12/01/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 95.4 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 11/29/17 | 12/01/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 11/29/17 | 12/01/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 32.9 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 11/29/17 | 12/01/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 16.87 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 12/06/17 | 12/08/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 13.43 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 12/06/17 | 12/08/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 12/06/17 | 12/08/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 12/06/17 | 12/08/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 12/06/17 | 12/08/17 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.21 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 12/06/17 | 12/08/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 12/06/17 | 12/08/17 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 12/06/17 | 12/08/17 | RA57 | Ramos Melendez, Carlos M | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 268 | 12/06/17 | 12/08/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 407 | 12/13/17 | 12/15/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 413 | 12/13/17 | 12/15/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 416 | 12/13/17 | 12/15/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 423 | 12/13/17 | 12/15/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 12/13/17 | 12/15/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 51.64 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 12/13/17 | 12/15/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 105.26 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 12/13/17 | 12/15/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 12/20/17 | 12/22/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 12/20/17 | 12/22/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 606 | 12/20/17 | 12/22/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 613 | 12/20/17 | 12/22/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 12/20/17 | 12/22/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 121.71 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 12/20/17 | 12/22/17 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 52.63 |  | 0 | 0
998 | Payroll Taxes | PR | 788 | 12/27/17 | 12/29/17 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 794 | 12/27/17 | 12/29/17 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 12/27/17 | 12/29/17 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 12/27/17 | 12/29/17 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 814 | 12/27/17 | 12/29/17 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.16 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 847 | 12/27/17 | 12/29/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 01/03/18 | 01/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 14 | 01/03/18 | 01/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 01/03/18 | 01/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 01/03/18 | 01/05/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 01/03/18 | 01/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 48 | 01/03/18 | 01/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 36.18 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 01/10/18 | 01/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 01/10/18 | 01/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 01/10/18 | 01/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 01/10/18 | 01/12/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 01/10/18 | 01/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 59.21 |  | 0 | 0
998 | Payroll Taxes | PR | 397 | 01/17/18 | 01/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 403 | 01/17/18 | 01/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 406 | 01/17/18 | 01/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 413 | 01/17/18 | 01/19/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 01/17/18 | 01/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 01/17/18 | 01/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | -9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 458 | 01/17/18 | 01/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 593 | 01/24/18 | 01/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 602 | 01/24/18 | 01/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 01/24/18 | 01/26/18 | GA46 | Galdamez, Dagoberto A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 01/24/18 | 01/26/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 650 | 01/24/18 | 01/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 01/24/18 | 01/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/31/18 | 02/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/31/18 | 02/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/07/18 | 02/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 02/21/18 | 02/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 02/28/18 | 03/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 02/28/18 | 03/02/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 26.32 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 02/28/18 | 03/02/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/28/18 | 03/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 130 | 03/07/18 | 03/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 138 | 03/07/18 | 03/09/18 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 172 | 03/07/18 | 03/09/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 03/14/18 | 03/16/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 330 | 03/14/18 | 03/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 362 | 03/14/18 | 03/16/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 03/14/18 | 03/16/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.16 |  | 0 | 0
998 | Payroll Taxes | PR | 375 | 03/14/18 | 03/16/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 385 | 03/14/18 | 03/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 03/21/18 | 03/23/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.81 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 03/21/18 | 03/23/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 574 | 03/21/18 | 03/23/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 30.52 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 03/21/18 | 03/23/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 03/28/18 | 03/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 03/28/18 | 03/30/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 795 | 03/28/18 | 03/30/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 03/28/18 | 03/30/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 808 | 03/28/18 | 03/30/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 04/04/18 | 04/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 19.74 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 04/04/18 | 04/06/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 39.78 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 04/04/18 | 04/06/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 04/04/18 | 04/06/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 04/04/18 | 04/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 71.26 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 04/04/18 | 04/06/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 04/04/18 | 04/06/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 04/04/18 | 04/06/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 04/04/18 | 04/06/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 04/04/18 | 04/06/18 | SA53 | Sanchez Olea, Itzel G | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 04/04/18 | 04/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 04/04/18 | 04/06/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 25.47 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 04/11/18 | 04/13/18 | CA50 | Caro, Camilo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 04/11/18 | 04/13/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 04/11/18 | 04/13/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 04/11/18 | 04/13/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 04/11/18 | 04/13/18 | LO58 | Lopez Reyes, Boris O | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 04/11/18 | 04/13/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 26.09 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 04/11/18 | 04/13/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 04/11/18 | 04/13/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 04/11/18 | 04/13/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/11/18 | 04/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 331 | 04/11/18 | 04/13/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 52.33 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 04/18/18 | 04/20/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 04/18/18 | 04/20/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 04/18/18 | 04/20/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 04/18/18 | 04/20/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 04/18/18 | 04/20/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 635 | 04/25/18 | 04/27/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 659 | 04/25/18 | 04/27/18 | NE46 | Nelson, Charles E | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 660 | 04/25/18 | 04/27/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 04/25/18 | 04/27/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 673 | 04/25/18 | 04/27/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 04/25/18 | 04/27/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 05/02/18 | 05/04/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/02/18 | 05/04/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 05/02/18 | 05/04/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 05/02/18 | 05/04/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 05/02/18 | 05/04/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 54.39 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 05/09/18 | 05/11/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 05/09/18 | 05/11/18 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 267 | 05/09/18 | 05/11/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 05/09/18 | 05/11/18 | RI89 | Rivera Oseguera, Kate Y | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 05/09/18 | 05/11/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.38 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 05/09/18 | 05/11/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 05/16/18 | 05/18/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/16/18 | 05/18/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 1.72 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 05/16/18 | 05/18/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 05/16/18 | 05/18/18 | OL17 | Olea Galeana, Maricela | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 05/16/18 | 05/18/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 490 | 05/16/18 | 05/18/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 05/23/18 | 05/25/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 05/23/18 | 05/25/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 133 | 05/30/18 | 06/01/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 06/06/18 | 06/08/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 299 | 06/06/18 | 06/08/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 06/06/18 | 06/08/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 06/06/18 | 06/08/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 28.46 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 06/06/18 | 06/08/18 | YO29 | Yohannes Jr., Samson | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 06/13/18 | 06/15/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 25.17 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 06/13/18 | 06/15/18 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.11 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 06/13/18 | 06/15/18 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 11.86 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 06/20/18 | 06/22/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 06/27/18 | 06/29/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 975 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1041 | 06/27/18 | 06/29/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | -4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 07/04/18 | 07/06/18 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 07/18/18 | 07/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 08/08/18 | 08/10/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036966 | 0 | -1275
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036966 | 0 | -1275
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -8500 | 036966 | 0 | -425
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -9500 | 036966 | 0 | -475
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -56050 | 036966 | 0 | -2802.5
999 | Sales | AR | 362 | 10/20/17 | 10/20/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -58500 | 036966 | 0 | -2925
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -51000 | 036981 | 0 | -2550
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -51000 | 036981 | 0 | -2550
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036981 | 0 | -1275
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 036981 | 0 | -1275
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -500 | 036981 | 0 | -25
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -500 | 036981 | 0 | -25
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2950 | 036981 | 0 | -147.5
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -6500 | 036981 | 0 | -325
999 | Sales | AR | 375 | 11/17/17 | 11/17/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -13600 | 036981 | 0 | -680
999 | Sales | AR | 537 | 12/15/17 | 12/15/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3400 | 036993 | 0 | -170
999 | Sales | AR | 537 | 12/15/17 | 12/15/17 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 036993 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -6260 | 037000 | 0 | -313
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -3800 | 037000 | 0 | -190
999 | Sales | AR | 465 | 01/19/18 | 01/19/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2763 | 037000 | 0 | -138.15
999 | Sales | AR | 443 | 03/20/18 | 03/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -22650 | 037048 | 0 | -1132.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -25500 | 037070 | 0 | -1275
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -28310 | 037070 | 0 | -1415.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -28310 | 037070 | 0 | -1415.5
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -5660 | 037070 | 0 | -283
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -5923 | 037070 | 0 | -296.15
999 | Sales | AR | 549 | 04/20/18 | 04/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -1380 | 037070 | 0 | -69
999 | Sales | AR | 511 | 05/18/18 | 05/18/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2810 | 037089 | 0 | -140.5
999 | Sales | AR | 511 | 05/18/18 | 05/18/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -1287 | 037089 | 0 | -64.35
999 | Sales | AR | 673 | 06/20/18 | 06/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -2412 | 037112 | 0 | -120.6
999 | Sales | AR | 527 | 07/20/18 | 07/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -4200 | 037139 | 0 | -210
999 | Sales | AR | 527 | 07/20/18 | 07/20/18 | 2048GR | GRE Construction, LLC $Ballinger |  |  |  |  | -403 | 037139 | 0 | -20.15

## Cost Code Summaries
COST CODE SUMMARIES — 14 CODES
cost_code | description | original_budget | current_budget | plus_minus_budget | actual_amount | net_due | retainage | regular_hours | overtime_hours | doubletime_hours
100 | Supervision | 4320 | 4420 | -1330.5 | 3089.5 | 0 | 0 | 63.5 | 0 | 0
101 | Takeoff & Purchase Labor | 9000 | 9200 | -4484.5 | 4715.5 | 0 | 0 | 91 | 0 | 0
112 | Canout Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | Roughin Labor | 98181 | 104646 | -21760.75 | 82885.25 | 0 | 0 | 2994.5 | 285 | 0
130 | Finish Labor | 26460 | 27252 | -581.5 | 26670.5 | 0 | 0 | 1175.5 | 49 | 0
211 | Garage Material | 0 | 1644 | -1644 | 0 | 0 | 0 | 0 | 0 | 0
220 | Roughin Material | 62505 | 63290 | -11874.18 | 51415.82 | 0 | 0 | 0 | 0 | 0
230 | Finish Material | 81287 | 86964 | -22943.28 | 64020.72 | 0 | 0 | 0 | 0 | 0
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
600 | Subcontractor | 500 | 500 | -385 | 115 | 0 | 0 | 0 | 0 | 0
601 | Engineering/Plans | 1000 | 1000 | -227.5 | 772.5 | 0 | 0 | 0 | 0 | 0
995 | Payroll Burden | 62565.31 | 66233.59 | -14183.94 | 52049.65 | 0 | 0 | 0 | 0 | 0
998 | Payroll Taxes | 10554.02 | 11191.8 | -2213.61 | 8978.19 | 0 | 0 | 0 | 0 | 0
999 | Sales | -498700 | -517068 | 0 | -517068 | 0 | -25853.4 | 0 | 0 | 0

## Worker Wages
WORKER NOMINAL WAGES — 30 WORKERS
Per-worker wage data derived from Line Items (source=PR). nominal_rate = regular_amount ÷ regular_hours — the worker's declared hourly rate as booked by Sage PR. Sorted by nominal rate (ascending) within tier.
Worker (Last, First) | Reg Hours | OT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER
Caro, Camilo | 56.5 | 8 | 904 | 192 | 16
Nelson, Charles E | 40 | 0 | 640 | 0 | 16
Rivera Oseguera, Kate Y | 201.5 | 4 | 3224 | 96 | 16
Olea Galeana, Maricela | 193.5 | 10 | 3096 | 240 | 16
Sanchez Olea, Itzel G | 2.5 | 0 | 40 | 0 | 16
Ramos Melendez, Carlos M | 264 | 42 | 4752 | 1134 | 18
Cornejo Orellana, Carlos E | 504 | 21.5 | 9072 | 580.5 | 18
Gomez Reyes, Edith N | 68 | 15 | 1224 | 405 | 18
Sanchez, Derli | 1 | 6 | 18 | 162 | 18
Lopez Reyes, Boris O | 24 | 0 | 432 | 0 | 18
Yohannes Jr., Samson | 224 | 0 | 4032 | 0 | 18
Cruz Gonzalez, Julio C | 519 | 35 | 9861 | 997.5 | 19
Gerard, Mitchell J | 4 | 0 | 0 | 0 | 0
JOURNEYMAN
Benites Portillo, Marvin E | 406 | 35 | 8526 | 1102.5 | 21
Hubbard, Dustin R | 4 | 0 | 84 | 0 | 21
Eliassen, Cory H | 3 | 0 | 63 | 0 | 21
Lovo, German G | 220 | 22.5 | 5060 | 776.25 | 23
Galdamez, Dagoberto A | 480 | 14 | 11520 | 504 | 24
Montenegro, Carlos E | 7 | 21 | 189 | 850.5 | 27
Gerard, Jordan E | 306.5 | 3 | 8299.5 | 135 | 27.0783
Rivera, Jorge A | 72 | 8 | 2232 | 372 | 31
Sepulveda Gonzalez, Alfredo | 17 | 4 | 527 | 186 | 31
McCabe, Thomas C | 23 | 12 | 718 | 561 | 31.2174
LEAD/SUPERVISOR
Hubbard, Robert W | 58.5 | 0 | 2421.5 | 0 | 41.3932
Sanders, Allen O | 75 | 8 | 3160 | 504 | 42.1333
Quintanilla, Esteban R | 405 | 37 | 17415 | 2386.5 | 43
Gerard, Jeffrey S | 122.5 | 0 | 5892.5 | 0 | 48.102
Donelson, Richard T | 36 | 0 | 1912.5 | 0 | 53.125
OT-ONLY
Hernandez Gonzalez, Osbaldo | 0 | 14 | 0 | 399 | — (no reg hours)
Cruz Guzman, Joel A | 0 | 14 | 0 | 462 | — (no reg hours)

## Derived Fields
DERIVED FIELDS — 40 CALCULATIONS
All derived values computed from parsed data. v4 schema (2026-04-18): Reconciliation Actions #1, #2, #3, #7, #8, #9 applied. Fields mirror Job 2020 test-labels.
Field | Value | Formula / Logic
PROJECT-LEVEL BENCHMARKS (Action #8, trade-agnostic)
project_duration_months | pending (requires project_start_date) | (COALESCE(project_end_date, MAX(line_items[].document_date)) − project_start_date) ÷ 30.4
scope_benchmarks | pending (requires scope_metrics input) | One object per scope_metrics entry: {label, dollars_per_unit, hours_per_unit, units_per_month, revenue_per_unit}
COST-BY-SOURCE ROLLUPS
cost_by_source_pr_amount | 178388.59 | SUM(line_items[].actual_amount WHERE source=PR)
cost_by_source_ap_amount | 115060.4 | SUM(line_items[].actual_amount WHERE source=AP)
cost_by_source_gl_amount | 1263.64 | SUM(line_items[].actual_amount WHERE source=GL)
direct_cost | 294712.63 | PR + AP + GL totals
net_profit | 222355.37 | abs(revenue) − direct_cost. Sage stores revenue as negative (credit); we use absolute value.
pr_pct_of_revenue | 0.345 | PR total ÷ abs(revenue)
ap_pct_of_revenue | 0.22253 | AP total ÷ abs(revenue)
direct_cost_pct_of_revenue | 0.56997 | direct_cost ÷ abs(revenue). Complement of gross margin.
LABOR ANALYTICS
total_labor_hours | 4671.5 | SUM(regular + overtime hours, PR only)
pr_src_cost_per_hr | 38.1866 | PR total ÷ total_labor_hours (includes OT premium)
fully_loaded_wage | 51.2504 | (PR + burden) ÷ total_labor_hours — includes burden & taxes on top of pr_src_cost_per_hr
burden_multiplier | 1.3421 | fully_loaded_wage ÷ pr_src_cost_per_hr
straight_time_rate | 24.2801 | SUM(regular_amount) ÷ SUM(regular_hours). Weighted straight-time rate; excludes OT premium.
worker_nominal_wages | 30 workers (see Worker Wages tab) | GROUP BY name WHERE source=PR; per-worker {reg_h, ot_h, reg_a, ot_a, nominal_rate=reg_a÷reg_h}
nominal_wage_percentiles | p10=$16.00 ¦ p25=$18.00 ¦ p50=$21.00 ¦ p75=$31.00 ¦ p90=$42.39 | Percentile snapshot across worker_nominal_wages[].nominal_rate
total_workers | 30 | COUNT DISTINCT(name WHERE source=PR)
burden_total | 61027.84 | SUM(actual WHERE cost_code IN 995,998)
MATERIAL ANALYTICS
material_spend_total | 115436.54 | SUM(actual WHERE code LIKE 2xx)
material_budget_total | 151898 | SUM(current_budget WHERE code LIKE 2xx)
material_codes_tracked | 4 | COUNT material cost codes
material_codes_over_budget | 0 | COUNT material codes WHERE plus_minus_budget > 0 [convention: actual − current_budget, positive = over]
material_codes_under_budget | 4 | COUNT material codes WHERE plus_minus <= 0
largest_material_overrun | 241 Water Main/Insulation Mat: $0 vs $0 budget (+$0) | Material code with largest positive plus_minus (biggest overrun)
largest_material_savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943) | Material code with largest negative plus_minus (biggest savings)
material_vendor_count | 15 | COUNT DISTINCT(name WHERE source=AP)
top_vendor_spend | Keller Supply Co. $Ballinger: $31,367 (27% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
phases_over_budget | 0 | COUNT phases WHERE plus_minus > 0 AND code != 999 (sales)
phases_under_budget | 13 | COUNT phases WHERE plus_minus <= 0 AND code != 999 (sales)
largest_overrun | 112 Canout Labor: $0 vs $0 budget (+$0) | Phase with largest positive plus_minus (biggest overrun)
largest_savings | 230 Finish Material: $64,021 vs $86,964 budget ($-22,943) | Phase with largest negative plus_minus (biggest savings)
BUDGET & FORECAST
total_jtd_cost | 294712.63 | SUM(actual) all expense codes (excludes 999 revenue)
total_budget | 376341.39 | SUM(current_budget) all expense codes (excludes 999 revenue)
overall_pct_budget_consumed | 0.7831 | total_jtd ÷ total_budget
total_over_under_budget | 81628.76 | total_budget − total_jtd. Negative = over budget.
variance_trend | N/A (single snapshot) | Requires prior period comparison
labor_unit_cost_per_hr | 25.1227 | labor-code JTD ÷ total_labor_hours. Unit cost per labor hour (NOT throughput).
revenue_per_labor_hour | 110.6856 | abs(job_totals_revenue) ÷ total_labor_hours. Labor throughput — revenue generated per labor hour.
material_price_variance | 36461.46 | material_budget − material_spend. Positive = under budget.

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line item sums vs. cost code totals from the PDF
Cost Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 3089.5 | 3089.5 | 0 | ✓
101 | Takeoff & Purchase Labor | 4715.5 | 4715.5 | 0 | ✓
112 | Canout Labor | 0 | 0 | 0 | ✓
120 | Roughin Labor | 82885.25 | 82885.25 | 0 | ✓
130 | Finish Labor | 26670.5 | 26670.5 | 0 | ✓
211 | Garage Material | 0 | 0 | 0 | ✓
220 | Roughin Material | 51415.82 | 51415.82 | 0 | ✓
230 | Finish Material | 64020.72 | 64020.72 | 0 | ✓
241 | Water Main/Insulation Mat | 0 | 0 | 0 | ✓
600 | Subcontractor | 115 | 115 | 0 | ✓
601 | Engineering/Plans | 772.5 | 772.5 | 0 | ✓
995 | Payroll Burden | 52049.65 | 52049.65 | 0 | ✓
998 | Payroll Taxes | 8978.19 | 8978.19 | 0 | ✓
999 | Sales | -517068 | -517068 | 0 | ✓
RESULT: 14/14 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — Job 2048
Worked example of the Reconciliation Protocol running against Job 2048 (JCR-only — no external cross-checks). Each row shows the JCR-derived value, the cross-check value, and the observed status. Protocol contract lives in JCR Schema v4 → Reconciliation Protocol tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | Row summary: 112 Canout Labor: $0 vs $0 budget (+$0) | Largest overrun spot-check: actual − current_budget ties to cent | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF value to the cent.
RC-02 | current_budget / original_budget | current_budget total = $376,341; original_budget carried per cost code (see Cost Code Summaries tab) | Sum of org_budget across expense codes differs where COs shifted budget | Cost Code Summaries tab (column C vs column D) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $38.19 / hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $178,388.59 ÷ 4,671.50 hrs = $38.19 | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales. Matches Action #3 convention from Job 2020.
RC-04 | worker_nominal_wages[] / nominal_wage_percentiles | p10=$16.00 ¦ p25=$18.00 ¦ p50=$21.00 ¦ p75=$31.00 ¦ p90=$42.39 (30 workers) | straight_time_rate = $24.28 (weighted average) | Worker Wages tab + straight_time_rate derived field | PASS | Population-slice sanity: weighted straight_time_rate falls within p25–p75 range, which is expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost = $25.12/hr ¦ revenue = $110.69/hr ¦ ratio = 4.41x | Recompute: labor-code total ÷ 4,671.50 hrs | Derived Fields tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics[] / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2048 (e.g., fixture count, DFU total, linear feet of main). Labeler should not emit scope_benchmarks until scope_metrics is populated.
RC-07 | reconciliation (per-code parse tie-out) | 14/14 codes tie to PDF to the cent | PR: $178,388.59 ¦ AP: $115,060.40 ¦ GL: $1,263.64 all match by_source | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. Status PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0
How to use: when a labeler produces a new set of derived values for Job 2048, update columns C and D in the rows above and set status per the Protocol contract.