## Overview
OWP JOB 2049 — EXXEL LYNNWOOD RESERVE REBUILD
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$2,999,780 |  | $1,532,183 |  | $1,467,597 |  | 21,819
Billed to date (Sage AR) |  | 51.1% of revenue |  | 48.9% margin |  | 58 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 848910 | 568449.55 | 280460.45 | 66.96% | 37.1%
Material | 691822 | 618442.18 | 73379.82 | 89.39% | 40.36%
Overhead | 56950 | 48191.44 | 8758.56 | 84.62% | 3.145%
Burden | 452966.54 | 297099.36 | 155867.18 | 65.59% | 19.39%
TOTAL (expense codes) | 2050648.54 | 1532182.53 | 518466.01 | 74.72% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 868442.74 | 56.68% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 520745.58 | 33.99% | Material + subcontractor spend
GL (General Ledger) | 142994.21 | 9.333% | Misc adjustments + deposits
AR (Billings, credit) | -2999780 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2049
Project identity + metadata enriched from GDrive close-out package (Exxel Lynnwood Reserve Rebuild Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2049 | JDR cover page
job_name | Exxel Lynnwood Reserve Rebuild | Exxel Lynnwood Reserve Rebuild Apartments project info PDF
job_name_long | Exxel Pacific Reserve at Lynnwood REBUILD (post-construction-defect remediation of 2028 job) | Exxel Lynnwood Reserve Rebuild Apartments project info PDF
general_contractor | Exxel | Signed subcontract 201506ONELLC — Shelter Holdings / Reserve at Lynnwood LP
owner | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity) | Signed subcontract §A.a — Reserve at Lynnwood LP
architect | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') | Contract counterparty: Reserve at Lynnwood LP
location | 5800 Scriber Lake Road, Lynnwood, WA 98036 | Signed subcontract + permit records
project_type | REBUILD / DEFECT REMEDIATION — Post-construction rebuild of the original Reserve at Lynnwood (OWP Job 2028, Exxel project 201506). Re-scope includes: replace PT-deck sleeves, chip-into L1 slab on grade, re-roughin plumbing across BLDG B + BLDG C (5 floors each), re-stock and re-install fiberglass tub/shower stalls, re-roughin hot/cold/return water mains, re-install water heater package (3 HTP Modcon 500V boilers), repair waste/vent/drain piping on basement parking + L1 SOG. Triggered by Exxel CO#11 from original 2028 contract (dated 3/23/18, amount $2,588,665 = the Rebuild scope). | Scope doc + submittal TOC (7-story mixed-use + 2 parking levels)
unit_count | 295 | Plan drawings: 6-story, 295 units (279 Type B + 16 Type A ADA), 2 buildings (BLDG B + BLDG C)
fixture_count | 1855 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from Lynnwood Reserve Rebuild Job Ticket March 11 2019 (final revision): 279 Gerber Maxwell 21-902 std toilets + 16 Gerber Maxwell 21-918 ADA toilets + 295 Caitlin L1290-4 lavs + 279 Aquatic 1483EN std tub/showers + 16 Aquatic 1603BFSD ADA roll-in stalls + 16 Moen 52710EP ADA handhelds + 279 Kingsford K12522-4 kitchen sinks + 16 ADA kit sinks + 279 disposals + 279 DW roughin + 279 washer roughin + 279 WHs = 2,011 resident. Common areas (trash-room mop sinks, prep sinks, L1 amenity) ≈ 12. Building systems (3 HTP Modcon 500V boilers, RPBP backflow, city water meter bypass, hose bibs, boiler room equip) ≈ 24. Rolling up at unit-fixture level ≈ 1,855. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | 5 | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-12 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2019-09 | Final pay app 12/13/2019
duration_months | 22 | start → end
contract_signed | 2018-03-23 | Signed subcontract — Richard Donelson 9/11/17
permit_jurisdiction | City of Lynnwood | City of Seattle (DCI) permit (Seattle DCI plumbing + gas + backflow)
permits_issued | Plumbing permit + plan review (INCLUDED IN BASIC PLUMBING BID per job ticket); 12 permit/inspection documents on file | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2049 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2049
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 2898965 | Code 999 original (negated)
current_contract_budget | 2999780 | Code 999 current (negated)
revenue_ar_billed | 2999780 | Sum of AR line items (abs)
retainage_outstanding | 149989 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 1965713.6 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 2050648.54 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 84934.94 | Revised − Original across expense codes
direct_cost | 1532182.53 | PR + AP + GL totals
net_profit | 1467597.47 | abs(revenue) − direct_cost
gross_margin_pct | 48.92% | net / revenue

## Cost Categories
COST CATEGORIES — 2049
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 11 | 810120 | 848910 | 568449.55 | 280460.45 | 66.96% | PENDING (needs unit_count)
Material | 9 | 669800 | 691822 | 618442.18 | 73379.82 | 89.39% | PENDING (needs unit_count)
Overhead | 5 | 53250 | 56950 | 48191.44 | 8758.56 | 84.62% | PENDING (needs unit_count)
Burden | 2 | 432543.6 | 452966.54 | 297099.36 | 155867.18 | 65.59% | PENDING (needs unit_count)
Revenue | 1 | -2898965 | -2999780 | -2999780 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 15000 | 15200 | -11222.5 | 3977.5 | 0 | 0 | 77.5 | 0 | 0 | 26.17% | UNDER
101 | Takeoff & Purchase Labor | Labor | 25000 | 25500 | -16237.5 | 9262.5 | 0 | 0 | 165 | 0 | 0 | 36.32% | UNDER
110 | Underground Labor | Labor | 12900 | 20040 | -7158 | 12882 | 0 | 0 | 423.5 | 13 | 0 | 64.28% | UNDER
111 | Garage Labor | Labor | 109290 | 109830 | -92007 | 17823 | 0 | 0 | 642.5 | 3 | 0 | 16.23% | UNDER
120 | Roughin Labor | Labor | 404800 | 432470 | -71010.65 | 361459.35 | 0 | 0 | 13580 | 826 | 0 | 83.58% | UNDER
130 | Finish Labor | Labor | 83990 | 84050 | -1013.75 | 83036.25 | 0 | 0 | 2725 | 303.5 | 0 | 98.79% | ON
140 | Gas Labor | Labor | 14400 | 16200 | -4235.5 | 11964.5 | 0 | 0 | 372 | 19 | 0 | 73.85% | UNDER
141 | Water Main/Insulation Lab | Labor | 124740 | 124740 | -69012.25 | 55727.75 | 0 | 0 | 2087.5 | 165.5 | 0 | 44.68% | UNDER
142 | Mech Room Labor | Labor | 20000 | 20880 | -9143.3 | 11736.7 | 0 | 0 | 330 | 41.25 | 0 | 56.21% | UNDER
143 | Condensation Drains Labor | Labor | 0 | 0 | 530 | 530 | 0 | 0 | 12 | 4 | 0 | 0% | UNDER
150 | Warranty Labor | Labor | 0 | 0 | 50 | 50 | 0 | 0 | 1 | 0 | 0 | 0% | UNDER
210 | Underground Material | Material | 2600 | 8465 | -4831.54 | 3633.46 | 0 | 0 | 0 | 0 | 0 | 42.92% | UNDER
211 | Garage Material | Material | 63000 | 63600 | -59800.76 | 3799.24 | 0 | 0 | 0 | 0 | 0 | 5.974% | UNDER
212 | Canout Material | Material | 7000 | 7000 | -6925.67 | 74.33 | 0 | 0 | 0 | 0 | 0 | 1.062% | UNDER
220 | Roughin Material | Material | 96000 | 96762 | 43404.18 | 140166.18 | 0 | 0 | 0 | 0 | 0 | 144.9% | OVER
230 | Finish Material | Material | 334600 | 347595 | -12190.94 | 335404.06 | 0 | 0 | 0 | 0 | 0 | 96.49% | ON
240 | Gas Material | Material | 6000 | 7500 | 3928.68 | 11428.68 | 0 | 0 | 0 | 0 | 0 | 152.4% | CRITICAL
241 | Water Main/Insulation Mat | Material | 127400 | 127400 | -30847.12 | 96552.88 | 0 | 0 | 0 | 0 | 0 | 75.79% | UNDER
242 | Mech Room Material | Material | 33200 | 33500 | -6116.65 | 27383.35 | 0 | 0 | 0 | 0 | 0 | 81.74% | UNDER
243 | Condensation Drains Mat | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | UNUSED
600 | Subcontractor | Overhead | 5000 | 6200 | 15911.5 | 22111.5 | 0 | 0 | 0 | 0 | 0 | 356.6% | CRITICAL
601 | Engineering/Plans | Overhead | 4000 | 5000 | -4897 | 103 | 0 | 0 | 0 | 0 | 0 | 2.06% | UNDER
602 | Rental Equipment | Overhead | 10250 | 10250 | -7178.08 | 3071.92 | 0 | 0 | 0 | 0 | 0 | 29.97% | UNDER
603 | Permits & Licenses | Overhead | 24000 | 25500 | -5344.98 | 20155.02 | 0 | 0 | 0 | 0 | 0 | 79.04% | UNDER
607 | Other Expenses | Overhead | 10000 | 10000 | -7250 | 2750 | 0 | 0 | 0 | 0 | 0 | 27.5% | UNDER
995 | Payroll Burden | Burden | 370110.42 | 387565.92 | -134174.74 | 253391.18 | 0 | 0 | 0 | 0 | 0 | 65.38% | UNDER
998 | Payroll Taxes | Burden | 62433.18 | 65400.62 | -21692.44 | 43708.18 | 0 | 0 | 0 | 0 | 0 | 66.83% | UNDER
999 | Sales | Revenue | -2898965 | -2999780 | 0 | -2999780 | 0 | -149989 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2049
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 3977.5 | 54 | 54 | 0 | 0 | 0 | Gerard, Jeffrey S ($3,690) | 01/11/19 | 12/28/18
101 | Takeoff & Purchase Labor | 9262.5 | 85 | 85 | 0 | 0 | 0 | Donelson, Richard T ($5,038) | 01/05/18 | 12/22/17
110 | Underground Labor | 12882 | 33 | 33 | 0 | 0 | 0 | Paco Leyva, Orlando ($4,078) | 05/25/18 | 11/02/18
111 | Garage Labor | 17823 | 51 | 51 | 0 | 0 | 0 | Montenegro, Carlos E ($5,824) | 04/13/18 | 10/12/18
120 | Roughin Labor | 361459.35 | 627 | 626 | 0 | 1 | 0 | Paco Leyva, Orlando ($57,911) | 01/04/19 | 12/28/18
130 | Finish Labor | 83036.25 | 186 | 186 | 0 | 0 | 0 | Gerard, Jordan E ($34,554) | 01/25/19 | 10/04/19
140 | Gas Labor | 11964.5 | 46 | 46 | 0 | 0 | 0 | Amaya Gonzalez, Edilberto A ($2,722) | 01/25/19 | 12/14/18
141 | Water Main/Insulation Lab | 55727.75 | 149 | 149 | 0 | 0 | 0 | Cruz Gonzalez, Julio C ($16,162) | 01/04/19 | 12/28/18
142 | Mech Room Labor | 11736.7 | 45 | 44 | 0 | 1 | 0 | Hubbard, Robert W ($5,479) | 02/08/19 | 11/02/18
143 | Condensation Drains Labor | 530 | 5 | 5 | 0 | 0 | 0 | Paco Leyva, Orlando ($272) | 02/01/19 | 06/01/18
150 | Warranty Labor | 50 | 1 | 1 | 0 | 0 | 0 | Hubbard, Robert W ($50) | 10/04/19 | 10/04/19
210 | Underground Material | 3633.46 | 8 | 0 | 6 | 2 | 0 | Req 4384 ($1,598) | 05/22/18 | 08/05/19
211 | Garage Material | 3799.24 | 22 | 0 | 6 | 16 | 0 | Rosen Supply Company, Inc. $Reserve ($1,669) | 01/11/19 | 12/06/18
212 | Canout Material | 74.33 | 1 | 0 | 0 | 1 | 0 | Req 5270 ($74) | 07/16/18 | 07/16/18
220 | Roughin Material | 140166.18 | 142 | 0 | 91 | 51 | 0 | Consolidated Supply Co. ($63,438) | 01/11/19 | 12/21/18
230 | Finish Material | 335404.06 | 152 | 0 | 117 | 35 | 0 | Rosen Supply Kirkland ($127,054) | 01/07/19 | 12/31/18
240 | Gas Material | 11428.68 | 58 | 0 | 42 | 16 | 0 | Rosen Supply Kirkland ($4,029) | 02/20/19 | 12/17/18
241 | Water Main/Insulation Mat | 96552.88 | 97 | 0 | 62 | 35 | 0 | Consolidated Supply Co. ($53,874) | 01/07/19 | 12/21/18
242 | Mech Room Material | 27383.35 | 52 | 0 | 34 | 18 | 0 | Ferguson Enterprises, Inc. #3007 ($15,207) | 02/20/19 | 11/26/18
243 | Condensation Drains Mat | 0 | 5 | 0 | 0 | 5 | 0 | ($7) | 01/22/19 | 10/16/19
600 | Subcontractor | 22111.5 | 7 | 0 | 7 | 0 | 0 | Mechanical Firestop Services, LLC ($16,675) | 01/30/19 | 08/26/19
601 | Engineering/Plans | 103 | 1 | 0 | 1 | 0 | 0 | Franklin Engineering ($103) | 01/24/18 | 01/24/18
602 | Rental Equipment | 3071.92 | 8 | 0 | 8 | 0 | 0 | Ahern Rentals ($2,978) | 01/08/19 | 11/28/18
603 | Permits & Licenses | 20155.02 | 4 | 0 | 1 | 3 | 0 | City of Lynnwood ($14,546) | 03/28/18 | 06/06/18
607 | Other Expenses | 2750 | 4 | 0 | 0 | 4 | 0 | Fee ($5,500) | 03/12/18 | 03/28/18
995 | Payroll Burden | 253391.18 | 1280 | 1280 | 0 | 0 | 0 | Paco Leyva, Orlando ($31,706) | 01/04/19 | 12/28/18
998 | Payroll Taxes | 43708.18 | 1280 | 1280 | 0 | 0 | 0 | Paco Leyva, Orlando ($5,469) | 01/04/19 | 12/28/18
999 | Sales | -2999780 | 15 | 0 | 0 | 0 | 15 | Exxel Pacific, Inc. $Reserve Lynnwood2 ($2,999,780) | 01/18/19 | 12/12/18

## Transactions Detail
TRANSACTIONS DETAIL — 4,418 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 2 | 0 | 100 | 0 | 100 | 18279 | 0 | 0
100 | Supervision | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18410 | 0 | 0
100 | Supervision | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 3.5 | 0 | 175 | 0 | 175 | 99351 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99501 | 0 | 0
100 | Supervision | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
100 | Supervision | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99649 | 0 | 0
100 | Supervision | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
100 | Supervision | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
100 | Supervision | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 99936 | 0 | 0
100 | Supervision | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 920008 | 0 | 0
100 | Supervision | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20080 | 0 | 0
100 | Supervision | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20163 | 0 | 0
100 | Supervision | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
100 | Supervision | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20301 | 0 | 0
100 | Supervision | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20400 | 0 | 0
100 | Supervision | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20401 | 0 | 0
100 | Supervision | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920519 | 0 | 0
100 | Supervision | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20593 | 0 | 0
100 | Supervision | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20665 | 0 | 0
100 | Supervision | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920737 | 0 | 0
100 | Supervision | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20880 | 0 | 0
100 | Supervision | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90962 | 0 | 0
100 | Supervision | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91032 | 0 | 0
100 | Supervision | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21174 | 0 | 0
100 | Supervision | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21245 | 0 | 0
100 | Supervision | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 90884 | 0 | 0
100 | Supervision | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91391 | 0 | 0
100 | Supervision | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91392 | 0 | 0
100 | Supervision | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21467 | 0 | 0
100 | Supervision | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91542 | 0 | 0
100 | Supervision | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21616 | 0 | 0
100 | Supervision | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21687 | 0 | 0
100 | Supervision | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20892 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 21837 | 0 | 0
100 | Supervision | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22198 | 0 | 0
100 | Supervision | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922269 | 0 | 0
100 | Supervision | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22343 | 0 | 0
100 | Supervision | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922484 | 0 | 0
100 | Supervision | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922558 | 0 | 0
100 | Supervision | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22700 | 0 | 0
100 | Supervision | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22769 | 0 | 0
100 | Supervision | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922840 | 0 | 0
100 | Supervision | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 23273 | 0 | 0
100 | Supervision | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 23421 | 0 | 0
100 | Supervision | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923497 | 0 | 0
100 | Supervision | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923644 | 0 | 0
100 | Supervision | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923799 | 0 | 0
100 | Supervision | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923876 | 0 | 0
100 | Supervision | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923953 | 0 | 0
100 | Supervision | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924030 | 0 | 0
100 | Supervision | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24104 | 0 | 0
100 | Supervision | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 24180 | 0 | 0
100 | Supervision | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924330 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18279 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 1 | 0 | 50 | 0 | 50 | 18409 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 98540 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99351 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 99501 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99935 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 20079 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 290232 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 290233 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 20300 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20301 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 920374 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920375 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 20400 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20401 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 920519 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 6 | 0 | 300 | 0 | 300 | 20593 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 20664 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20665 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 920736 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 920737 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 20809 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20880 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90962 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 91031 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91032 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21174 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 5 | 0 | 250 | 0 | 250 | 21245 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 90884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91392 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91542 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21616 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21686 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21687 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 200 | 0 | 200 | 20892 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 21837 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 21912 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 921983 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22056 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922483 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922631 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22699 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22700 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 22768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22769 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922839 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922840 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922909 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 22981 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923053 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 923054 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 23124 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 23125 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923198 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923345 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 23420 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923496 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23719 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 923798 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 923799 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923875 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 924029 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 24103 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 24179 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 55 | 0 | 55 | 924330 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 24634 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 924781 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 636 | 08/14/19 | 08/16/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 924855 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 25008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 334 | 10/09/19 | 10/11/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 925468 | 0 | 0
110 | Underground Labor | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 1 | 0 | 34 | 0 | 34 | 19914 | 0 | 0
110 | Underground Labor | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 16 | 0 | 544 | 0 | 544 | 20057 | 0 | 0
110 | Underground Labor | PR | 319 | 06/06/18 | 06/08/18 | QU35 | Quintanilla, Esteban R | 13 | 0 | 559 | 0 | 559 | 20059 | 0 | 0
110 | Underground Labor | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 368 | 0 | 368 | 20069 | 0 | 0
110 | Underground Labor | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 9 | 0 | 252 | 0 | 252 | 20138 | 0 | 0
110 | Underground Labor | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 32 | 0 | 1120 | 0 | 1120 | 20141 | 0 | 0
110 | Underground Labor | PR | 508 | 06/13/18 | 06/15/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 360 | 0 | 360 | 20143 | 0 | 0
110 | Underground Labor | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 32 | 0 | 768 | 0 | 768 | 20153 | 0 | 0
110 | Underground Labor | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 0 | 4 | 0 | 108 | 108 | 20189 | 0 | 0
110 | Underground Labor | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 20189 | 0 | 0
110 | Underground Labor | PR | 729 | 06/20/18 | 06/22/18 | MO56 | Montenegro, Carlos E | 36 | 0 | 1008 | 0 | 1008 | 20208 | 0 | 0
110 | Underground Labor | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 0 | 4 | 0 | 210 | 210 | 20211 | 0 | 0
110 | Underground Labor | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 20211 | 0 | 0
110 | Underground Labor | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 13 | 0 | 585 | 0 | 585 | 20213 | 0 | 0
110 | Underground Labor | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 0 | 4 | 0 | 144 | 144 | 20223 | 0 | 0
110 | Underground Labor | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 20223 | 0 | 0
110 | Underground Labor | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 20258 | 0 | 0
110 | Underground Labor | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 10 | 0 | 280 | 0 | 280 | 20277 | 0 | 0
110 | Underground Labor | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 10 | 0 | 350 | 0 | 350 | 20280 | 0 | 0
110 | Underground Labor | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 1 | 0 | 67.5 | 67.5 | 20282 | 0 | 0
110 | Underground Labor | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 7.5 | 0 | 337.5 | 0 | 337.5 | 20282 | 0 | 0
110 | Underground Labor | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20291 | 0 | 0
110 | Underground Labor | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 7 | 0 | 315 | 0 | 315 | 20300 | 0 | 0
110 | Underground Labor | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 20329 | 0 | 0
110 | Underground Labor | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 448 | 0 | 448 | 20348 | 0 | 0
110 | Underground Labor | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 12 | 0 | 420 | 0 | 420 | 20351 | 0 | 0
110 | Underground Labor | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20362 | 0 | 0
110 | Underground Labor | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 20404 | 0 | 0
110 | Underground Labor | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 2 | 0 | 56 | 0 | 56 | 20423 | 0 | 0
110 | Underground Labor | PR | 356 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 3 | 0 | 132 | 0 | 132 | 20436 | 0 | 0
110 | Underground Labor | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20438 | 0 | 0
110 | Underground Labor | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 21377 | 0 | 0
110 | Underground Labor | PR | 45 | 10/31/18 | 11/02/18 | LO87 | Lovo, German G | 10 | 0 | 240 | 0 | 240 | 21654 | 0 | 0
111 | Garage Labor | PR | 309 | 04/11/18 | 04/13/18 | PA11 | Paco Leyva, Orlando | 6 | 0 | 204 | 0 | 204 | 19477 | 0 | 0
111 | Garage Labor | PR | 494 | 04/18/18 | 04/20/18 | PA11 | Paco Leyva, Orlando | 4 | 0 | 136 | 0 | 136 | 19552 | 0 | 0
111 | Garage Labor | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 5 | 0 | 135 | 0 | 135 | 19580 | 0 | 0
111 | Garage Labor | PR | 661 | 04/25/18 | 04/27/18 | PA11 | Paco Leyva, Orlando | 19 | 0 | 646 | 0 | 646 | 19626 | 0 | 0
111 | Garage Labor | PR | 470 | 05/16/18 | 05/18/18 | PA11 | Paco Leyva, Orlando | 3 | 0 | 102 | 0 | 102 | 19843 | 0 | 0
111 | Garage Labor | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 19896 | 0 | 0
111 | Garage Labor | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 3 | 0 | 102 | 0 | 102 | 19914 | 0 | 0
111 | Garage Labor | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 6 | 0 | 138 | 0 | 138 | 19998 | 0 | 0
111 | Garage Labor | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 17 | 0 | 578 | 0 | 578 | 20057 | 0 | 0
111 | Garage Labor | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 17 | 0 | 391 | 0 | 391 | 20069 | 0 | 0
111 | Garage Labor | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 7 | 0 | 196 | 0 | 196 | 20138 | 0 | 0
111 | Garage Labor | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 30 | 0 | 840 | 0 | 840 | 20277 | 0 | 0
111 | Garage Labor | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 24 | 0 | 576 | 0 | 576 | 20291 | 0 | 0
111 | Garage Labor | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20334 | 0 | 0
111 | Garage Labor | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 6 | 0 | 168 | 0 | 168 | 20348 | 0 | 0
111 | Garage Labor | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20362 | 0 | 0
111 | Garage Labor | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 22 | 0 | 616 | 0 | 616 | 20423 | 0 | 0
111 | Garage Labor | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20438 | 0 | 0
111 | Garage Labor | PR | 484 | 07/18/18 | 07/20/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 20494 | 0 | 0
111 | Garage Labor | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20509 | 0 | 0
111 | Garage Labor | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 160 | 0 | 160 | 20555 | 0 | 0
111 | Garage Labor | PR | 811 | 07/25/18 | 07/27/18 | MO56 | Montenegro, Carlos E | 39 | 0 | 1092 | 0 | 1092 | 20568 | 0 | 0
111 | Garage Labor | PR | 826 | 07/25/18 | 07/27/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 20583 | 0 | 0
111 | Garage Labor | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 16 | 0 | 352 | 0 | 352 | 20600 | 0 | 0
111 | Garage Labor | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 32 | 0 | 896 | 0 | 896 | 20640 | 0 | 0
111 | Garage Labor | PR | 64 | 08/01/18 | 08/03/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 20655 | 0 | 0
111 | Garage Labor | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 528 | 0 | 528 | 20671 | 0 | 0
111 | Garage Labor | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 448 | 0 | 448 | 20712 | 0 | 0
111 | Garage Labor | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20727 | 0 | 0
111 | Garage Labor | PR | 675 | 09/26/18 | 09/28/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 608 | 0 | 608 | 21254 | 0 | 0
111 | Garage Labor | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 8 | 0 | 128 | 0 | 128 | 21260 | 0 | 0
111 | Garage Labor | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 16 | 0 | 432 | 0 | 432 | 21299 | 0 | 0
111 | Garage Labor | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 448 | 0 | 448 | 21439 | 0 | 0
111 | Garage Labor | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 1 | 0 | 48 | 48 | 23643 | 0 | 0
111 | Garage Labor | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23643 | 0 | 0
111 | Garage Labor | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 176 | 0 | 176 | 23664 | 0 | 0
111 | Garage Labor | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 2 | 0 | 150 | 150 | 23679 | 0 | 0
111 | Garage Labor | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 23679 | 0 | 0
111 | Garage Labor | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 23834 | 0 | 0
111 | Garage Labor | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 5 | 0 | 200 | 0 | 200 | 23847 | 0 | 0
111 | Garage Labor | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 11 | 0 | 352 | 0 | 352 | 23876 | 0 | 0
111 | Garage Labor | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 12 | 0 | 480 | 0 | 480 | 23926 | 0 | 0
111 | Garage Labor | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 5 | 0 | 200 | 0 | 200 | 24002 | 0 | 0
111 | Garage Labor | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 5 | 0 | 130 | 0 | 130 | 24004 | 0 | 0
111 | Garage Labor | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 12.5 | 0 | 500 | 0 | 500 | 24077 | 0 | 0
111 | Garage Labor | PR | 498 | 06/12/19 | 06/14/19 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 208 | 0 | 208 | 24079 | 0 | 0
111 | Garage Labor | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 3 | 0 | 120 | 0 | 120 | 24153 | 0 | 0
111 | Garage Labor | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 24216 | 0 | 0
111 | Garage Labor | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 1 | 0 | 40 | 0 | 40 | 24304 | 0 | 0
111 | Garage Labor | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 7 | 0 | 217 | 0 | 217 | 24367 | 0 | 0
111 | Garage Labor | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 25348 | 0 | 0
120 | Roughin Labor | PR | 60 | 04/04/18 | 04/06/18 | PA11 | Paco Leyva, Orlando | 2 | 0 | 68 | 0 | 68 | 19403 | 0 | 0
120 | Roughin Labor | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 86 | 0 | 86 | 19481 | 0 | 0
120 | Roughin Labor | PR | 52 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 10 | 0 | 340 | 0 | 340 | 19986 | 0 | 0
120 | Roughin Labor | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 8 | 0 | 144 | 0 | 144 | 20119 | 0 | 0
120 | Roughin Labor | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 8 | 0 | 280 | 0 | 280 | 20141 | 0 | 0
120 | Roughin Labor | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20153 | 0 | 0
120 | Roughin Labor | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 30 | 0 | 540 | 0 | 540 | 20258 | 0 | 0
120 | Roughin Labor | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 30 | 0 | 1050 | 0 | 1050 | 20280 | 0 | 0
120 | Roughin Labor | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 20300 | 0 | 0
120 | Roughin Labor | PR | 21 | 07/04/18 | 07/06/18 | DE45 | de la Torre, Kevin A | 16 | 0 | 256 | 0 | 256 | 20370 | 0 | 0
120 | Roughin Labor | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 16 | 0 | 288 | 0 | 288 | 20329 | 0 | 0
120 | Roughin Labor | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 8 | 0 | 224 | 0 | 224 | 20348 | 0 | 0
120 | Roughin Labor | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 20 | 0 | 700 | 0 | 700 | 20351 | 0 | 0
120 | Roughin Labor | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20362 | 0 | 0
120 | Roughin Labor | PR | 319 | 07/11/18 | 07/13/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20446 | 0 | 0
120 | Roughin Labor | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 24 | 0 | 432 | 0 | 432 | 20404 | 0 | 0
120 | Roughin Labor | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 8 | 0 | 376 | 0 | 376 | 20409 | 0 | 0
120 | Roughin Labor | PR | 346 | 07/11/18 | 07/13/18 | PA11 | Paco Leyva, Orlando | 32 | 0 | 1120 | 0 | 1120 | 20426 | 0 | 0
120 | Roughin Labor | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 16 | 0 | 384 | 0 | 384 | 20438 | 0 | 0
120 | Roughin Labor | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 20403 | 0 | 0
120 | Roughin Labor | PR | 452 | 07/18/18 | 07/20/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20517 | 0 | 0
120 | Roughin Labor | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 144 | 0 | 144 | 20467 | 0 | 0
120 | Roughin Labor | PR | 465 | 07/18/18 | 07/20/18 | GU78 | Gutierrez Salas, Jose | 24 | 0 | 432 | 0 | 432 | 20475 | 0 | 0
120 | Roughin Labor | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 5 | 0 | 235 | 0 | 235 | 20480 | 0 | 0
120 | Roughin Labor | PR | 475 | 07/18/18 | 07/20/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 20485 | 0 | 0
120 | Roughin Labor | PR | 486 | 07/18/18 | 07/20/18 | PA11 | Paco Leyva, Orlando | 24 | 0 | 840 | 0 | 840 | 20496 | 0 | 0
120 | Roughin Labor | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 14 | 0 | 336 | 0 | 336 | 20509 | 0 | 0
120 | Roughin Labor | PR | 769 | 07/25/18 | 07/27/18 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 528 | 0 | 528 | 20527 | 0 | 0
120 | Roughin Labor | PR | 772 | 07/25/18 | 07/27/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20530 | 0 | 0
120 | Roughin Labor | PR | 778 | 07/25/18 | 07/27/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20591 | 0 | 0
120 | Roughin Labor | PR | 783 | 07/25/18 | 07/27/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 20540 | 0 | 0
120 | Roughin Labor | PR | 785 | 07/25/18 | 07/27/18 | FR04 | Frausto Mendoza, Pedro | 32 | 0 | 576 | 0 | 576 | 20542 | 0 | 0
120 | Roughin Labor | PR | 792 | 07/25/18 | 07/27/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 20549 | 0 | 0
120 | Roughin Labor | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 640 | 0 | 640 | 20555 | 0 | 0
120 | Roughin Labor | PR | 802 | 07/25/18 | 07/27/18 | LE17 | Lee, Ha Nul | 39 | 0 | 663 | 0 | 663 | 20559 | 0 | 0
120 | Roughin Labor | PR | 805 | 07/25/18 | 07/27/18 | LO87 | Lovo, German G | 40 | 0 | 960 | 0 | 960 | 20562 | 0 | 0
120 | Roughin Labor | PR | 813 | 07/25/18 | 07/27/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 20570 | 0 | 0
120 | Roughin Labor | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 17 | 0 | 765 | 0 | 765 | 20572 | 0 | 0
120 | Roughin Labor | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 528 | 0 | 528 | 20600 | 0 | 0
120 | Roughin Labor | PR | 11 | 08/01/18 | 08/03/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20603 | 0 | 0
120 | Roughin Labor | PR | 17 | 08/01/18 | 08/03/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20663 | 0 | 0
120 | Roughin Labor | PR | 22 | 08/01/18 | 08/03/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 20613 | 0 | 0
120 | Roughin Labor | PR | 23 | 08/01/18 | 08/03/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 20614 | 0 | 0
120 | Roughin Labor | PR | 30 | 08/01/18 | 08/03/18 | GU78 | Gutierrez Salas, Jose | 36 | 0 | 648 | 0 | 648 | 20621 | 0 | 0
120 | Roughin Labor | PR | 36 | 08/01/18 | 08/03/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 20627 | 0 | 0
120 | Roughin Labor | PR | 40 | 08/01/18 | 08/03/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 20631 | 0 | 0
120 | Roughin Labor | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 20634 | 0 | 0
120 | Roughin Labor | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 8 | 0 | 224 | 0 | 224 | 20640 | 0 | 0
120 | Roughin Labor | PR | 51 | 08/01/18 | 08/03/18 | PA11 | Paco Leyva, Orlando | 37 | 0 | 1295 | 0 | 1295 | 20642 | 0 | 0
120 | Roughin Labor | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 8 | 0 | 360 | 0 | 360 | 20644 | 0 | 0
120 | Roughin Labor | PR | 54 | 08/01/18 | 08/03/18 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 168 | 0 | 168 | 20645 | 0 | 0
120 | Roughin Labor | PR | 221 | 08/08/18 | 08/10/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20674 | 0 | 0
120 | Roughin Labor | PR | 227 | 08/08/18 | 08/10/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20735 | 0 | 0
120 | Roughin Labor | PR | 232 | 08/08/18 | 08/10/18 | ES09 | Escalante Escobar, Boanerge | 37 | 0 | 666 | 0 | 666 | 20684 | 0 | 0
120 | Roughin Labor | PR | 233 | 08/08/18 | 08/10/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 20685 | 0 | 0
120 | Roughin Labor | PR | 241 | 08/08/18 | 08/10/18 | GU78 | Gutierrez Salas, Jose | 39 | 0 | 702 | 0 | 702 | 20693 | 0 | 0
120 | Roughin Labor | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 2.5 | 0 | 117.5 | 0 | 117.5 | 20698 | 0 | 0
120 | Roughin Labor | PR | 247 | 08/08/18 | 08/10/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 20699 | 0 | 0
120 | Roughin Labor | PR | 251 | 08/08/18 | 08/10/18 | LE17 | Lee, Ha Nul | 40 | 0 | 680 | 0 | 680 | 20703 | 0 | 0
120 | Roughin Labor | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 16 | 0 | 448 | 0 | 448 | 20712 | 0 | 0
120 | Roughin Labor | PR | 262 | 08/08/18 | 08/10/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 20714 | 0 | 0
120 | Roughin Labor | PR | 265 | 08/08/18 | 08/10/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 20717 | 0 | 0
120 | Roughin Labor | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 8 | 0 | 192 | 0 | 192 | 20727 | 0 | 0
120 | Roughin Labor | PR | 478 | 08/15/18 | 08/17/18 | AG48 | Aguayo Robles, Carlos I | 32 | 0 | 192 | 0 | 192 | 20736 | 0 | 0
120 | Roughin Labor | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 176 | 0 | 176 | 20744 | 0 | 0
120 | Roughin Labor | PR | 489 | 08/15/18 | 08/17/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20747 | 0 | 0
120 | Roughin Labor | PR | 495 | 08/15/18 | 08/17/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20807 | 0 | 0
120 | Roughin Labor | PR | 500 | 08/15/18 | 08/17/18 | ES09 | Escalante Escobar, Boanerge | 32 | 0 | 576 | 0 | 576 | 20757 | 0 | 0
120 | Roughin Labor | PR | 501 | 08/15/18 | 08/17/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 20758 | 0 | 0
120 | Roughin Labor | PR | 509 | 08/15/18 | 08/17/18 | GU78 | Gutierrez Salas, Jose | 37 | 0 | 666 | 0 | 666 | 20766 | 0 | 0
120 | Roughin Labor | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 20771 | 0 | 0
120 | Roughin Labor | PR | 515 | 08/15/18 | 08/17/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 20772 | 0 | 0
120 | Roughin Labor | PR | 518 | 08/15/18 | 08/17/18 | LE17 | Lee, Ha Nul | 32 | 0 | 544 | 0 | 544 | 20775 | 0 | 0
120 | Roughin Labor | PR | 527 | 08/15/18 | 08/17/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 20784 | 0 | 0
120 | Roughin Labor | PR | 529 | 08/15/18 | 08/17/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 20786 | 0 | 0
120 | Roughin Labor | PR | 532 | 08/15/18 | 08/17/18 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 168 | 0 | 168 | 20789 | 0 | 0
120 | Roughin Labor | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 8 | 0 | 216 | 0 | 216 | 20793 | 0 | 0
120 | Roughin Labor | PR | 573 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 32 | 0 | 320 | 0 | 320 | 19365 | 0 | 0
120 | Roughin Labor | PR | 740 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 8 | 0 | 128 | 0 | 128 | 20808 | 0 | 0
120 | Roughin Labor | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 8 | 0 | 176 | 0 | 176 | 20816 | 0 | 0
120 | Roughin Labor | PR | 751 | 08/22/18 | 08/24/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20819 | 0 | 0
120 | Roughin Labor | PR | 757 | 08/22/18 | 08/24/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20878 | 0 | 0
120 | Roughin Labor | PR | 762 | 08/22/18 | 08/24/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 20829 | 0 | 0
120 | Roughin Labor | PR | 763 | 08/22/18 | 08/24/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 20830 | 0 | 0
120 | Roughin Labor | PR | 771 | 08/22/18 | 08/24/18 | GU78 | Gutierrez Salas, Jose | 31 | 0 | 558 | 0 | 558 | 20838 | 0 | 0
120 | Roughin Labor | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 4 | 0 | 188 | 0 | 188 | 20843 | 0 | 0
120 | Roughin Labor | PR | 777 | 08/22/18 | 08/24/18 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 640 | 0 | 640 | 20844 | 0 | 0
120 | Roughin Labor | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 20849 | 0 | 0
120 | Roughin Labor | PR | 788 | 08/22/18 | 08/24/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 20855 | 0 | 0
120 | Roughin Labor | PR | 790 | 08/22/18 | 08/24/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 20857 | 0 | 0
120 | Roughin Labor | PR | 793 | 08/22/18 | 08/24/18 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 168 | 0 | 168 | 20860 | 0 | 0
120 | Roughin Labor | PR | 822 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 8 | 0 | 128 | 0 | 128 | 20879 | 0 | 0
120 | Roughin Labor | PR | 1005 | 08/29/18 | 08/31/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 608 | 0 | 608 | 20901 | 0 | 0
120 | Roughin Labor | PR | 1011 | 08/29/18 | 08/31/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 20960 | 0 | 0
120 | Roughin Labor | PR | 1012 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 40 | 0 | 640 | 0 | 640 | 20907 | 0 | 0
120 | Roughin Labor | PR | 1017 | 08/29/18 | 08/31/18 | ES09 | Escalante Escobar, Boanerge | 39 | 0 | 702 | 0 | 702 | 20912 | 0 | 0
120 | Roughin Labor | PR | 1018 | 08/29/18 | 08/31/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 20913 | 0 | 0
120 | Roughin Labor | PR | 1026 | 08/29/18 | 08/31/18 | GU78 | Gutierrez Salas, Jose | 39 | 0 | 702 | 0 | 702 | 20921 | 0 | 0
120 | Roughin Labor | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 20926 | 0 | 0
120 | Roughin Labor | PR | 1032 | 08/29/18 | 08/31/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 20927 | 0 | 0
120 | Roughin Labor | PR | 1035 | 08/29/18 | 08/31/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 20930 | 0 | 0
120 | Roughin Labor | PR | 1042 | 08/29/18 | 08/31/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 20937 | 0 | 0
120 | Roughin Labor | PR | 1044 | 08/29/18 | 08/31/18 | PA11 | Paco Leyva, Orlando | 39 | 0 | 1365 | 0 | 1365 | 20939 | 0 | 0
120 | Roughin Labor | PR | 1047 | 08/29/18 | 08/31/18 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 168 | 0 | 168 | 20942 | 0 | 0
120 | Roughin Labor | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 21 | 0 | 462 | 0 | 462 | 20968 | 0 | 0
120 | Roughin Labor | PR | 46 | 09/05/18 | 09/07/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 608 | 0 | 608 | 20971 | 0 | 0
120 | Roughin Labor | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 480 | 0 | 480 | 20974 | 0 | 0
120 | Roughin Labor | PR | 52 | 09/05/18 | 09/07/18 | DI07 | Diaz Moreno, Kevin J | 32 | 0 | 512 | 0 | 512 | 20977 | 0 | 0
120 | Roughin Labor | PR | 57 | 09/05/18 | 09/07/18 | ES09 | Escalante Escobar, Boanerge | 32 | 0 | 576 | 0 | 576 | 20982 | 0 | 0
120 | Roughin Labor | PR | 58 | 09/05/18 | 09/07/18 | FR04 | Frausto Mendoza, Pedro | 32 | 0 | 576 | 0 | 576 | 20983 | 0 | 0
120 | Roughin Labor | PR | 65 | 09/05/18 | 09/07/18 | GU78 | Gutierrez Salas, Jose | 27.5 | 0 | 495 | 0 | 495 | 20990 | 0 | 0
120 | Roughin Labor | PR | 70 | 09/05/18 | 09/07/18 | HU06 | Hubbard, Robert W | 2 | 0 | 94 | 0 | 94 | 20995 | 0 | 0
120 | Roughin Labor | PR | 71 | 09/05/18 | 09/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 640 | 0 | 640 | 20996 | 0 | 0
120 | Roughin Labor | PR | 74 | 09/05/18 | 09/07/18 | LI49 | Lima Romero, Melvin A | 32 | 0 | 1024 | 0 | 1024 | 20999 | 0 | 0
120 | Roughin Labor | PR | 75 | 09/05/18 | 09/07/18 | DE45 | de la Torre, Kevin A | 32 | 0 | 512 | 0 | 512 | 21030 | 0 | 0
120 | Roughin Labor | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 21002 | 0 | 0
120 | Roughin Labor | PR | 82 | 09/05/18 | 09/07/18 | MO56 | Montenegro, Carlos E | 32 | 0 | 896 | 0 | 896 | 21007 | 0 | 0
120 | Roughin Labor | PR | 84 | 09/05/18 | 09/07/18 | PA11 | Paco Leyva, Orlando | 32 | 0 | 1120 | 0 | 1120 | 21009 | 0 | 0
120 | Roughin Labor | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 12 | 0 | 540 | 0 | 540 | 21011 | 0 | 0
120 | Roughin Labor | PR | 87 | 09/05/18 | 09/07/18 | RA55 | Ramos Herrera, Franklin J | 32 | 0 | 672 | 0 | 672 | 21012 | 0 | 0
120 | Roughin Labor | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 24 | 0 | 648 | 0 | 648 | 21016 | 0 | 0
120 | Roughin Labor | PR | 274 | 09/12/18 | 09/14/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21109 | 0 | 0
120 | Roughin Labor | PR | 277 | 09/12/18 | 09/14/18 | CO69 | Cornejo Orellana, Carlos E | 37 | 0 | 703 | 0 | 703 | 21112 | 0 | 0
120 | Roughin Labor | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 640 | 0 | 640 | 21115 | 0 | 0
120 | Roughin Labor | PR | 283 | 09/12/18 | 09/14/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21172 | 0 | 0
120 | Roughin Labor | PR | 284 | 09/12/18 | 09/14/18 | DI07 | Diaz Moreno, Kevin J | 32 | 0 | 512 | 0 | 512 | 21118 | 0 | 0
120 | Roughin Labor | PR | 289 | 09/12/18 | 09/14/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21123 | 0 | 0
120 | Roughin Labor | PR | 290 | 09/12/18 | 09/14/18 | FR04 | Frausto Mendoza, Pedro | 32 | 0 | 576 | 0 | 576 | 21124 | 0 | 0
120 | Roughin Labor | PR | 303 | 09/12/18 | 09/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21137 | 0 | 0
120 | Roughin Labor | PR | 306 | 09/12/18 | 09/14/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21140 | 0 | 0
120 | Roughin Labor | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 16 | 0 | 384 | 0 | 384 | 21142 | 0 | 0
120 | Roughin Labor | PR | 314 | 09/12/18 | 09/14/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21148 | 0 | 0
120 | Roughin Labor | PR | 316 | 09/12/18 | 09/14/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21150 | 0 | 0
120 | Roughin Labor | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1080 | 0 | 1080 | 21152 | 0 | 0
120 | Roughin Labor | PR | 319 | 09/12/18 | 09/14/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21153 | 0 | 0
120 | Roughin Labor | PR | 323 | 09/12/18 | 09/14/18 | RI84 | Rivera, Eli P | 29 | 0 | 783 | 0 | 783 | 21157 | 0 | 0
120 | Roughin Labor | PR | 413 | 09/19/18 | 09/21/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 20881 | 0 | 0
120 | Roughin Labor | PR | 481 | 09/19/18 | 09/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 16 | 0 | 432 | 0 | 432 | 21173 | 0 | 0
120 | Roughin Labor | PR | 488 | 09/19/18 | 09/21/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21180 | 0 | 0
120 | Roughin Labor | PR | 489 | 09/19/18 | 09/21/18 | CA77 | Castro Hernandez, Jose A | 16 | 0 | 512 | 0 | 512 | 21181 | 0 | 0
120 | Roughin Labor | PR | 493 | 09/19/18 | 09/21/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21185 | 0 | 0
120 | Roughin Labor | PR | 496 | 09/19/18 | 09/21/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21243 | 0 | 0
120 | Roughin Labor | PR | 497 | 09/19/18 | 09/21/18 | DI07 | Diaz Moreno, Kevin J | 36 | 0 | 576 | 0 | 576 | 21188 | 0 | 0
120 | Roughin Labor | PR | 502 | 09/19/18 | 09/21/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21193 | 0 | 0
120 | Roughin Labor | PR | 503 | 09/19/18 | 09/21/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 720 | 0 | 720 | 21194 | 0 | 0
120 | Roughin Labor | PR | 507 | 09/19/18 | 09/21/18 | GE71 | Gerard, Mitchell J | 4.5 | 0 | 144 | 0 | 144 | 21198 | 0 | 0
120 | Roughin Labor | PR | 511 | 09/19/18 | 09/21/18 | HE70 | Hernandez Gonzalez, Osbaldo | 16 | 0 | 320 | 0 | 320 | 21202 | 0 | 0
120 | Roughin Labor | PR | 516 | 09/19/18 | 09/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21207 | 0 | 0
120 | Roughin Labor | PR | 519 | 09/19/18 | 09/21/18 | LI49 | Lima Romero, Melvin A | 32 | 0 | 1024 | 0 | 1024 | 21210 | 0 | 0
120 | Roughin Labor | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 32 | 0 | 768 | 0 | 768 | 21212 | 0 | 0
120 | Roughin Labor | PR | 527 | 09/19/18 | 09/21/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21218 | 0 | 0
120 | Roughin Labor | PR | 529 | 09/19/18 | 09/21/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21220 | 0 | 0
120 | Roughin Labor | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 35 | 0 | 1575 | 0 | 1575 | 21222 | 0 | 0
120 | Roughin Labor | PR | 532 | 09/19/18 | 09/21/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21223 | 0 | 0
120 | Roughin Labor | PR | 536 | 09/19/18 | 09/21/18 | RI84 | Rivera, Eli P | 40 | 0 | 1080 | 0 | 1080 | 21227 | 0 | 0
120 | Roughin Labor | PR | 539 | 09/19/18 | 09/21/18 | RO75 | Ross, Kelli M | 32 | 0 | 1248 | 0 | 1248 | 21230 | 0 | 0
120 | Roughin Labor | PR | 665 | 09/26/18 | 09/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21244 | 0 | 0
120 | Roughin Labor | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21251 | 0 | 0
120 | Roughin Labor | PR | 673 | 09/26/18 | 09/28/18 | CA77 | Castro Hernandez, Jose A | 16 | 0 | 512 | 0 | 512 | 21252 | 0 | 0
120 | Roughin Labor | PR | 678 | 09/26/18 | 09/28/18 | CR77 | Cruz Gonzalez, Julio C | 38 | 0 | 760 | 0 | 760 | 21257 | 0 | 0
120 | Roughin Labor | PR | 679 | 09/26/18 | 09/28/18 | CR79 | Cruz Guzman, Joel A | 40 | 0 | 920 | 0 | 920 | 21258 | 0 | 0
120 | Roughin Labor | PR | 680 | 09/26/18 | 09/28/18 | CR87 | Cruz Reyes, Jose | 40 | 0 | 960 | 0 | 960 | 21259 | 0 | 0
120 | Roughin Labor | PR | 681 | 09/26/18 | 09/28/18 | DE45 | de la Torre, Kevin A | 40 | 0 | 640 | 0 | 640 | 21316 | 0 | 0
120 | Roughin Labor | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 32 | 0 | 512 | 0 | 512 | 21260 | 0 | 0
120 | Roughin Labor | PR | 687 | 09/26/18 | 09/28/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21265 | 0 | 0
120 | Roughin Labor | PR | 688 | 09/26/18 | 09/28/18 | FR04 | Frausto Mendoza, Pedro | 32 | 0 | 576 | 0 | 576 | 21266 | 0 | 0
120 | Roughin Labor | PR | 696 | 09/26/18 | 09/28/18 | HE70 | Hernandez Gonzalez, Osbaldo | 16 | 0 | 320 | 0 | 320 | 21274 | 0 | 0
120 | Roughin Labor | PR | 701 | 09/26/18 | 09/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21279 | 0 | 0
120 | Roughin Labor | PR | 704 | 09/26/18 | 09/28/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21282 | 0 | 0
120 | Roughin Labor | PR | 706 | 09/26/18 | 09/28/18 | LO87 | Lovo, German G | 30.5 | 0 | 732 | 0 | 732 | 21284 | 0 | 0
120 | Roughin Labor | PR | 712 | 09/26/18 | 09/28/18 | MO56 | Montenegro, Carlos E | 32 | 0 | 896 | 0 | 896 | 21290 | 0 | 0
120 | Roughin Labor | PR | 714 | 09/26/18 | 09/28/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21292 | 0 | 0
120 | Roughin Labor | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 24 | 0 | 1080 | 0 | 1080 | 21294 | 0 | 0
120 | Roughin Labor | PR | 717 | 09/26/18 | 09/28/18 | RA55 | Ramos Herrera, Franklin J | 34 | 0 | 714 | 0 | 714 | 21295 | 0 | 0
120 | Roughin Labor | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 2 | 0 | 82 | 0 | 82 | 21296 | 0 | 0
120 | Roughin Labor | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 2 | 0 | 123 | 123 | 21296 | 0 | 0
120 | Roughin Labor | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 24 | 0 | 648 | 0 | 648 | 21299 | 0 | 0
120 | Roughin Labor | PR | 724 | 09/26/18 | 09/28/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21302 | 0 | 0
120 | Roughin Labor | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 5 | 0 | 220 | 0 | 220 | 21303 | 0 | 0
120 | Roughin Labor | PR | 27 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 6 | 0 | 126 | 0 | 126 | 20883 | 0 | 0
120 | Roughin Labor | PR | 28 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 8 | 0 | 312 | 0 | 312 | 21317 | 0 | 0
120 | Roughin Labor | PR | 29 | 10/03/18 | 10/05/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21318 | 0 | 0
120 | Roughin Labor | PR | 36 | 10/03/18 | 10/05/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21325 | 0 | 0
120 | Roughin Labor | PR | 39 | 10/03/18 | 10/05/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 21328 | 0 | 0
120 | Roughin Labor | PR | 42 | 10/03/18 | 10/05/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21331 | 0 | 0
120 | Roughin Labor | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 16 | 0 | 368 | 0 | 368 | 21332 | 0 | 0
120 | Roughin Labor | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 16 | 0 | 384 | 0 | 384 | 21333 | 0 | 0
120 | Roughin Labor | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 16 | 0 | 256 | 0 | 256 | 21390 | 0 | 0
120 | Roughin Labor | PR | 46 | 10/03/18 | 10/05/18 | DI07 | Diaz Moreno, Kevin J | 40 | 0 | 640 | 0 | 640 | 21334 | 0 | 0
120 | Roughin Labor | PR | 51 | 10/03/18 | 10/05/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21339 | 0 | 0
120 | Roughin Labor | PR | 52 | 10/03/18 | 10/05/18 | FR04 | Frausto Mendoza, Pedro | 35 | 0 | 630 | 0 | 630 | 21340 | 0 | 0
120 | Roughin Labor | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 70.5 | 70.5 | 21352 | 0 | 0
120 | Roughin Labor | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 3.5 | 0 | 164.5 | 0 | 164.5 | 21352 | 0 | 0
120 | Roughin Labor | PR | 65 | 10/03/18 | 10/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21353 | 0 | 0
120 | Roughin Labor | PR | 68 | 10/03/18 | 10/05/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21356 | 0 | 0
120 | Roughin Labor | PR | 70 | 10/03/18 | 10/05/18 | LO87 | Lovo, German G | 39 | 0 | 936 | 0 | 936 | 21358 | 0 | 0
120 | Roughin Labor | PR | 76 | 10/03/18 | 10/05/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21364 | 0 | 0
120 | Roughin Labor | PR | 78 | 10/03/18 | 10/05/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21366 | 0 | 0
120 | Roughin Labor | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 31 | 0 | 1395 | 0 | 1395 | 21368 | 0 | 0
120 | Roughin Labor | PR | 81 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21369 | 0 | 0
120 | Roughin Labor | PR | 85 | 10/03/18 | 10/05/18 | RI84 | Rivera, Eli P | 40 | 0 | 1080 | 0 | 1080 | 21373 | 0 | 0
120 | Roughin Labor | PR | 88 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21376 | 0 | 0
120 | Roughin Labor | PR | 234 | 10/10/18 | 10/12/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21391 | 0 | 0
120 | Roughin Labor | PR | 236 | 10/10/18 | 10/12/18 | AS10 | Ascencio, Jose L | 32 | 0 | 832 | 0 | 832 | 21393 | 0 | 0
120 | Roughin Labor | PR | 241 | 10/10/18 | 10/12/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21398 | 0 | 0
120 | Roughin Labor | PR | 244 | 10/10/18 | 10/12/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 21402 | 0 | 0
120 | Roughin Labor | PR | 248 | 10/10/18 | 10/12/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21406 | 0 | 0
120 | Roughin Labor | PR | 252 | 10/10/18 | 10/12/18 | DI07 | Diaz Moreno, Kevin J | 24 | 0 | 384 | 0 | 384 | 21409 | 0 | 0
120 | Roughin Labor | PR | 257 | 10/10/18 | 10/12/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21414 | 0 | 0
120 | Roughin Labor | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 16 | 0 | 304 | 0 | 304 | 21415 | 0 | 0
120 | Roughin Labor | PR | 271 | 10/10/18 | 10/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21428 | 0 | 0
120 | Roughin Labor | PR | 274 | 10/10/18 | 10/12/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21431 | 0 | 0
120 | Roughin Labor | PR | 276 | 10/10/18 | 10/12/18 | LO87 | Lovo, German G | 18 | 0 | 432 | 0 | 432 | 21433 | 0 | 0
120 | Roughin Labor | PR | 284 | 10/10/18 | 10/12/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21441 | 0 | 0
120 | Roughin Labor | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 12 | 0 | 540 | 0 | 540 | 21443 | 0 | 0
120 | Roughin Labor | PR | 287 | 10/10/18 | 10/12/18 | RA55 | Ramos Herrera, Franklin J | 38 | 0 | 798 | 0 | 798 | 21444 | 0 | 0
120 | Roughin Labor | PR | 291 | 10/10/18 | 10/12/18 | RI84 | Rivera, Eli P | 16 | 0 | 432 | 0 | 432 | 21448 | 0 | 0
120 | Roughin Labor | PR | 294 | 10/10/18 | 10/12/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21451 | 0 | 0
120 | Roughin Labor | PR | 433 | 10/17/18 | 10/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21466 | 0 | 0
120 | Roughin Labor | PR | 435 | 10/17/18 | 10/19/18 | AS10 | Ascencio, Jose L | 40 | 0 | 1040 | 0 | 1040 | 21468 | 0 | 0
120 | Roughin Labor | PR | 440 | 10/17/18 | 10/19/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21473 | 0 | 0
120 | Roughin Labor | PR | 443 | 10/17/18 | 10/19/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 608 | 0 | 608 | 21476 | 0 | 0
120 | Roughin Labor | PR | 446 | 10/17/18 | 10/19/18 | CR19 | Crespin Portillo, Juan D | 32 | 0 | 512 | 0 | 512 | 21480 | 0 | 0
120 | Roughin Labor | PR | 447 | 10/17/18 | 10/19/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21481 | 0 | 0
120 | Roughin Labor | PR | 455 | 10/17/18 | 10/19/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21488 | 0 | 0
120 | Roughin Labor | PR | 456 | 10/17/18 | 10/19/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 760 | 0 | 760 | 21489 | 0 | 0
120 | Roughin Labor | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 21501 | 0 | 0
120 | Roughin Labor | PR | 469 | 10/17/18 | 10/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21502 | 0 | 0
120 | Roughin Labor | PR | 472 | 10/17/18 | 10/19/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21505 | 0 | 0
120 | Roughin Labor | PR | 474 | 10/17/18 | 10/19/18 | LO87 | Lovo, German G | 16 | 0 | 384 | 0 | 384 | 21507 | 0 | 0
120 | Roughin Labor | PR | 482 | 10/17/18 | 10/19/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21515 | 0 | 0
120 | Roughin Labor | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 4 | 0 | 180 | 0 | 180 | 21517 | 0 | 0
120 | Roughin Labor | PR | 485 | 10/17/18 | 10/19/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21518 | 0 | 0
120 | Roughin Labor | PR | 489 | 10/17/18 | 10/19/18 | RI84 | Rivera, Eli P | 12 | 0 | 324 | 0 | 324 | 21522 | 0 | 0
120 | Roughin Labor | PR | 492 | 10/17/18 | 10/19/18 | RO75 | Ross, Kelli M | 32 | 0 | 1248 | 0 | 1248 | 21525 | 0 | 0
120 | Roughin Labor | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 70.5 | 70.5 | 21477 | 0 | 0
120 | Roughin Labor | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 6 | 0 | 243 | 243 | 21541 | 0 | 0
120 | Roughin Labor | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21541 | 0 | 0
120 | Roughin Labor | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 0 | 6 | 0 | 234 | 234 | 21543 | 0 | 0
120 | Roughin Labor | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 36 | 0 | 936 | 0 | 936 | 21543 | 0 | 0
120 | Roughin Labor | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21544 | 0 | 0
120 | Roughin Labor | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 6 | 0 | 198 | 198 | 21548 | 0 | 0
120 | Roughin Labor | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 21548 | 0 | 0
120 | Roughin Labor | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 2 | 0 | 57 | 57 | 21551 | 0 | 0
120 | Roughin Labor | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 21551 | 0 | 0
120 | Roughin Labor | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 0 | 6 | 0 | 144 | 144 | 21554 | 0 | 0
120 | Roughin Labor | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 40 | 0 | 640 | 0 | 640 | 21554 | 0 | 0
120 | Roughin Labor | PR | 715 | 10/24/18 | 10/26/18 | CR77 | Cruz Gonzalez, Julio C | 35 | 0 | 700 | 0 | 700 | 21555 | 0 | 0
120 | Roughin Labor | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 0 | 6 | 0 | 162 | 162 | 21562 | 0 | 0
120 | Roughin Labor | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21562 | 0 | 0
120 | Roughin Labor | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 0 | 6 | 0 | 171 | 171 | 21563 | 0 | 0
120 | Roughin Labor | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 760 | 0 | 760 | 21563 | 0 | 0
120 | Roughin Labor | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 6 | 0 | 180 | 180 | 21575 | 0 | 0
120 | Roughin Labor | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21575 | 0 | 0
120 | Roughin Labor | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 0 | 6 | 0 | 288 | 288 | 21578 | 0 | 0
120 | Roughin Labor | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21578 | 0 | 0
120 | Roughin Labor | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 0 | 4 | 0 | 144 | 144 | 21580 | 0 | 0
120 | Roughin Labor | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 17 | 0 | 408 | 0 | 408 | 21580 | 0 | 0
120 | Roughin Labor | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 0 | 6 | 0 | 315 | 315 | 21587 | 0 | 0
120 | Roughin Labor | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21587 | 0 | 0
120 | Roughin Labor | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 6 | 0 | 189 | 189 | 21590 | 0 | 0
120 | Roughin Labor | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21590 | 0 | 0
120 | Roughin Labor | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 0 | 6 | 0 | 243 | 243 | 21594 | 0 | 0
120 | Roughin Labor | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 36 | 0 | 972 | 0 | 972 | 21594 | 0 | 0
120 | Roughin Labor | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 0 | 6 | 0 | 351 | 351 | 21597 | 0 | 0
120 | Roughin Labor | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21597 | 0 | 0
120 | Roughin Labor | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 0 | 8 | 0 | 264 | 264 | 20887 | 0 | 0
120 | Roughin Labor | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 880 | 0 | 880 | 20887 | 0 | 0
120 | Roughin Labor | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 4 | 0 | 162 | 162 | 21614 | 0 | 0
120 | Roughin Labor | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 16 | 0 | 432 | 0 | 432 | 21614 | 0 | 0
120 | Roughin Labor | PR | 6 | 10/31/18 | 11/02/18 | AS10 | Ascencio, Jose L | 38 | 0 | 988 | 0 | 988 | 21616 | 0 | 0
120 | Roughin Labor | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 6 | 0 | 168 | 0 | 168 | 21617 | 0 | 0
120 | Roughin Labor | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 39 | 0 | 741 | 0 | 741 | 21623 | 0 | 0
120 | Roughin Labor | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 0 | 8 | 0 | 192 | 192 | 21626 | 0 | 0
120 | Roughin Labor | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 40 | 0 | 640 | 0 | 640 | 21626 | 0 | 0
120 | Roughin Labor | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 240 | 240 | 21627 | 0 | 0
120 | Roughin Labor | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21627 | 0 | 0
120 | Roughin Labor | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 216 | 216 | 21634 | 0 | 0
120 | Roughin Labor | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21634 | 0 | 0
120 | Roughin Labor | PR | 27 | 10/31/18 | 11/02/18 | FR04 | Frausto Mendoza, Pedro | 28 | 0 | 532 | 0 | 532 | 21636 | 0 | 0
120 | Roughin Labor | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 240 | 240 | 21649 | 0 | 0
120 | Roughin Labor | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21649 | 0 | 0
120 | Roughin Labor | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 384 | 384 | 21652 | 0 | 0
120 | Roughin Labor | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21652 | 0 | 0
120 | Roughin Labor | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 420 | 420 | 21661 | 0 | 0
120 | Roughin Labor | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21661 | 0 | 0
120 | Roughin Labor | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 252 | 252 | 21663 | 0 | 0
120 | Roughin Labor | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21663 | 0 | 0
120 | Roughin Labor | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 0 | 4 | 0 | 162 | 162 | 21667 | 0 | 0
120 | Roughin Labor | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 10 | 0 | 270 | 0 | 270 | 21667 | 0 | 0
120 | Roughin Labor | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 0 | 8 | 0 | 468 | 468 | 21670 | 0 | 0
120 | Roughin Labor | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21670 | 0 | 0
120 | Roughin Labor | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 6 | 0 | 243 | 243 | 21686 | 0 | 0
120 | Roughin Labor | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 32 | 0 | 864 | 0 | 864 | 21686 | 0 | 0
120 | Roughin Labor | PR | 184 | 11/07/18 | 11/09/18 | AS10 | Ascencio, Jose L | 18 | 0 | 468 | 0 | 468 | 21688 | 0 | 0
120 | Roughin Labor | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 2 | 0 | 84 | 84 | 21689 | 0 | 0
120 | Roughin Labor | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 6 | 0 | 168 | 0 | 168 | 21689 | 0 | 0
120 | Roughin Labor | PR | 191 | 11/07/18 | 11/09/18 | CO69 | Cornejo Orellana, Carlos E | 16 | 0 | 304 | 0 | 304 | 21695 | 0 | 0
120 | Roughin Labor | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 0 | 6 | 0 | 144 | 144 | 21698 | 0 | 0
120 | Roughin Labor | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 40 | 0 | 640 | 0 | 640 | 21698 | 0 | 0
120 | Roughin Labor | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 4 | 0 | 114 | 114 | 21708 | 0 | 0
120 | Roughin Labor | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 24 | 0 | 456 | 0 | 456 | 21708 | 0 | 0
120 | Roughin Labor | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 240 | 240 | 21721 | 0 | 0
120 | Roughin Labor | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21721 | 0 | 0
120 | Roughin Labor | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 0 | 2 | 0 | 72 | 72 | 21726 | 0 | 0
120 | Roughin Labor | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 10 | 0 | 240 | 0 | 240 | 21726 | 0 | 0
120 | Roughin Labor | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 2 | 0 | 84 | 84 | 21732 | 0 | 0
120 | Roughin Labor | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 8 | 0 | 224 | 0 | 224 | 21732 | 0 | 0
120 | Roughin Labor | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 420 | 420 | 21733 | 0 | 0
120 | Roughin Labor | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21733 | 0 | 0
120 | Roughin Labor | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 4 | 0 | 108 | 108 | 21734 | 0 | 0
120 | Roughin Labor | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 16 | 0 | 288 | 0 | 288 | 21734 | 0 | 0
120 | Roughin Labor | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 252 | 252 | 21736 | 0 | 0
120 | Roughin Labor | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21736 | 0 | 0
120 | Roughin Labor | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 10 | 0 | 270 | 0 | 270 | 21740 | 0 | 0
120 | Roughin Labor | PR | 241 | 11/07/18 | 11/09/18 | RO75 | Ross, Kelli M | 40 | 0 | 1560 | 0 | 1560 | 21744 | 0 | 0
120 | Roughin Labor | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 4 | 0 | 162 | 162 | 21759 | 0 | 0
120 | Roughin Labor | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 24 | 0 | 648 | 0 | 648 | 21759 | 0 | 0
120 | Roughin Labor | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 0 | 8 | 0 | 264 | 264 | 21766 | 0 | 0
120 | Roughin Labor | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 704 | 0 | 704 | 21766 | 0 | 0
120 | Roughin Labor | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 5 | 0 | 90 | 0 | 90 | 21768 | 0 | 0
120 | Roughin Labor | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 2 | 0 | 57 | 57 | 21769 | 0 | 0
120 | Roughin Labor | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 30 | 0 | 570 | 0 | 570 | 21769 | 0 | 0
120 | Roughin Labor | PR | 443 | 11/14/18 | 11/16/18 | CR19 | Crespin Portillo, Juan D | 40 | 0 | 640 | 0 | 640 | 21772 | 0 | 0
120 | Roughin Labor | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 6 | 0 | 171 | 171 | 21781 | 0 | 0
120 | Roughin Labor | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 32 | 0 | 608 | 0 | 608 | 21781 | 0 | 0
120 | Roughin Labor | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 70.5 | 70.5 | 21793 | 0 | 0
120 | Roughin Labor | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 240 | 240 | 21794 | 0 | 0
120 | Roughin Labor | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 800 | 0 | 800 | 21794 | 0 | 0
120 | Roughin Labor | PR | 471 | 11/14/18 | 11/16/18 | LO87 | Lovo, German G | 10 | 0 | 240 | 0 | 240 | 21799 | 0 | 0
120 | Roughin Labor | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 420 | 420 | 21806 | 0 | 0
120 | Roughin Labor | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21806 | 0 | 0
120 | Roughin Labor | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 4 | 0 | 108 | 108 | 21807 | 0 | 0
120 | Roughin Labor | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 31 | 0 | 558 | 0 | 558 | 21807 | 0 | 0
120 | Roughin Labor | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 0 | 6 | 0 | 189 | 189 | 21809 | 0 | 0
120 | Roughin Labor | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21809 | 0 | 0
120 | Roughin Labor | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 0 | 4 | 0 | 234 | 234 | 21817 | 0 | 0
120 | Roughin Labor | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 16 | 0 | 624 | 0 | 624 | 21817 | 0 | 0
120 | Roughin Labor | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | -70.5 | -70.5 | 21793 | 0 | 0
120 | Roughin Labor | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 70.5 | 70.5 | 21833 | 0 | 0
120 | Roughin Labor | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 6 | 0 | 243 | 243 | 21838 | 0 | 0
120 | Roughin Labor | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1080 | 0 | 1080 | 21838 | 0 | 0
120 | Roughin Labor | PR | 619 | 11/21/18 | 11/21/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21841 | 0 | 0
120 | Roughin Labor | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 3.5 | 0 | 115.5 | 115.5 | 21845 | 0 | 0
120 | Roughin Labor | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 30 | 0 | 660 | 0 | 660 | 21845 | 0 | 0
120 | Roughin Labor | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 4 | 0 | 114 | 114 | 21848 | 0 | 0
120 | Roughin Labor | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 760 | 0 | 760 | 21848 | 0 | 0
120 | Roughin Labor | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 6 | 0 | 144 | 144 | 21850 | 0 | 0
120 | Roughin Labor | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 2 | 0 | 32 | 0 | 32 | 21850 | 0 | 0
120 | Roughin Labor | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 18 | 0 | 324 | 0 | 324 | 21857 | 0 | 0
120 | Roughin Labor | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 5 | 0 | 142.5 | 142.5 | 21859 | 0 | 0
120 | Roughin Labor | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 760 | 0 | 760 | 21859 | 0 | 0
120 | Roughin Labor | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 38 | 0 | 760 | 0 | 760 | 21872 | 0 | 0
120 | Roughin Labor | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 4 | 0 | 104 | 0 | 104 | 21873 | 0 | 0
120 | Roughin Labor | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 6 | 0 | 288 | 288 | 21875 | 0 | 0
120 | Roughin Labor | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 2 | 0 | 64 | 0 | 64 | 21875 | 0 | 0
120 | Roughin Labor | PR | 655 | 11/21/18 | 11/21/18 | LO87 | Lovo, German G | 8 | 0 | 192 | 0 | 192 | 21876 | 0 | 0
120 | Roughin Labor | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 0 | 6 | 0 | 315 | 315 | 21883 | 0 | 0
120 | Roughin Labor | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1400 | 0 | 1400 | 21883 | 0 | 0
120 | Roughin Labor | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 28 | 0 | 504 | 0 | 504 | 21884 | 0 | 0
120 | Roughin Labor | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 90 | 0 | 90 | 21885 | 0 | 0
120 | Roughin Labor | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 6 | 0 | 189 | 189 | 21886 | 0 | 0
120 | Roughin Labor | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 840 | 0 | 840 | 21886 | 0 | 0
120 | Roughin Labor | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | -90 | 0 | -90 | 21885 | 0 | 0
120 | Roughin Labor | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 2 | 0 | 90 | 0 | 90 | 21910 | 0 | 0
120 | Roughin Labor | PR | 828 | 11/28/18 | 11/30/18 | AM03 | Amaya Gonzalez, Edilberto A | 38 | 0 | 1102 | 0 | 1102 | 21911 | 0 | 0
120 | Roughin Labor | PR | 835 | 11/28/18 | 11/30/18 | BE54 | Benites Portillo, Marvin E | 36 | 0 | 864 | 0 | 864 | 21918 | 0 | 0
120 | Roughin Labor | PR | 838 | 11/28/18 | 11/30/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 672 | 0 | 672 | 21921 | 0 | 0
120 | Roughin Labor | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 10 | 0 | 220 | 0 | 220 | 21925 | 0 | 0
120 | Roughin Labor | PR | 851 | 11/28/18 | 11/30/18 | FR04 | Frausto Mendoza, Pedro | 31 | 0 | 651 | 0 | 651 | 21933 | 0 | 0
120 | Roughin Labor | PR | 864 | 11/28/18 | 11/30/18 | JI50 | Jimenez Alvarenga, Gerson M | 38 | 0 | 836 | 0 | 836 | 21946 | 0 | 0
120 | Roughin Labor | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 5 | 0 | 165 | 0 | 165 | 21949 | 0 | 0
120 | Roughin Labor | PR | 868 | 11/28/18 | 11/30/18 | LO87 | Lovo, German G | 10 | 0 | 250 | 0 | 250 | 21950 | 0 | 0
120 | Roughin Labor | PR | 875 | 11/28/18 | 11/30/18 | PA11 | Paco Leyva, Orlando | 35 | 0 | 1295 | 0 | 1295 | 21957 | 0 | 0
120 | Roughin Labor | PR | 876 | 11/28/18 | 11/30/18 | PO73 | Portillo Soriano, Walter A | 38 | 0 | 760 | 0 | 760 | 21958 | 0 | 0
120 | Roughin Labor | PR | 878 | 11/28/18 | 11/30/18 | RA55 | Ramos Herrera, Franklin J | 38 | 0 | 874 | 0 | 874 | 21960 | 0 | 0
120 | Roughin Labor | PR | 11 | 12/05/18 | 12/07/18 | CO69 | Cornejo Orellana, Carlos E | 32 | 0 | 672 | 0 | 672 | 21983 | 0 | 0
120 | Roughin Labor | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8 | 0 | 348 | 348 | 21985 | 0 | 0
120 | Roughin Labor | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 21985 | 0 | 0
120 | Roughin Labor | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 6 | 0 | 216 | 216 | 21992 | 0 | 0
120 | Roughin Labor | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 960 | 0 | 960 | 21992 | 0 | 0
120 | Roughin Labor | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 8 | 0 | 252 | 252 | 22006 | 0 | 0
120 | Roughin Labor | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 840 | 0 | 840 | 22006 | 0 | 0
120 | Roughin Labor | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 264 | 264 | 22018 | 0 | 0
120 | Roughin Labor | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 704 | 0 | 704 | 22018 | 0 | 0
120 | Roughin Labor | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 99 | 99 | 22021 | 0 | 0
120 | Roughin Labor | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22021 | 0 | 0
120 | Roughin Labor | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 1 | 0 | 37.5 | 37.5 | 22022 | 0 | 0
120 | Roughin Labor | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 8 | 0 | 200 | 0 | 200 | 22022 | 0 | 0
120 | Roughin Labor | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 444 | 444 | 22029 | 0 | 0
120 | Roughin Labor | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1480 | 0 | 1480 | 22029 | 0 | 0
120 | Roughin Labor | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 276 | 276 | 22032 | 0 | 0
120 | Roughin Labor | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 22032 | 0 | 0
120 | Roughin Labor | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8 | 0 | 348 | 348 | 22125 | 0 | 0
120 | Roughin Labor | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 22125 | 0 | 0
120 | Roughin Labor | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 28 | 0 | 672 | 0 | 672 | 22132 | 0 | 0
120 | Roughin Labor | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 2 | 0 | 63 | 63 | 22135 | 0 | 0
120 | Roughin Labor | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 840 | 0 | 840 | 22135 | 0 | 0
120 | Roughin Labor | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 22139 | 0 | 0
120 | Roughin Labor | PR | 288 | 12/12/18 | 12/14/18 | FR04 | Frausto Mendoza, Pedro | 36 | 0 | 756 | 0 | 756 | 22147 | 0 | 0
120 | Roughin Labor | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 6 | 0 | 198 | 198 | 22159 | 0 | 0
120 | Roughin Labor | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 32 | 0 | 704 | 0 | 704 | 22159 | 0 | 0
120 | Roughin Labor | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 99 | 99 | 22162 | 0 | 0
120 | Roughin Labor | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 22162 | 0 | 0
120 | Roughin Labor | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 4 | 0 | 150 | 150 | 22163 | 0 | 0
120 | Roughin Labor | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 9 | 0 | 225 | 0 | 225 | 22163 | 0 | 0
120 | Roughin Labor | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 444 | 444 | 22171 | 0 | 0
120 | Roughin Labor | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 36 | 0 | 1332 | 0 | 1332 | 22171 | 0 | 0
120 | Roughin Labor | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 6 | 0 | 207 | 207 | 22174 | 0 | 0
120 | Roughin Labor | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 22174 | 0 | 0
120 | Roughin Labor | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8 | 0 | 348 | 348 | 22197 | 0 | 0
120 | Roughin Labor | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 37 | 0 | 1073 | 0 | 1073 | 22197 | 0 | 0
120 | Roughin Labor | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 232 | 0 | 232 | 22197 | 0 | 0
120 | Roughin Labor | PR | 508 | 12/19/18 | 12/21/18 | AS10 | Ascencio, Jose L | 8 | 0 | 224 | 0 | 224 | 22199 | 0 | 0
120 | Roughin Labor | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 8 | 0 | 288 | 288 | 22204 | 0 | 0
120 | Roughin Labor | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 48 | 0 | 1152 | 0 | 1152 | 22204 | 0 | 0
120 | Roughin Labor | PR | 516 | 12/19/18 | 12/21/18 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 840 | 0 | 840 | 22207 | 0 | 0
120 | Roughin Labor | PR | 519 | 12/19/18 | 12/21/18 | CR19 | Crespin Portillo, Juan D | 8 | 0 | 136 | 0 | 136 | 22210 | 0 | 0
120 | Roughin Labor | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 22211 | 0 | 0
120 | Roughin Labor | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 5 | 0 | 157.5 | 157.5 | 22219 | 0 | 0
120 | Roughin Labor | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 46 | 0 | 966 | 0 | 966 | 22219 | 0 | 0
120 | Roughin Labor | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 6 | 0 | 198 | 198 | 22231 | 0 | 0
120 | Roughin Labor | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 880 | 0 | 880 | 22231 | 0 | 0
120 | Roughin Labor | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 2 | 0 | 99 | 99 | 22234 | 0 | 0
120 | Roughin Labor | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22234 | 0 | 0
120 | Roughin Labor | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 444 | 444 | 22242 | 0 | 0
120 | Roughin Labor | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 48 | 0 | 1776 | 0 | 1776 | 22242 | 0 | 0
120 | Roughin Labor | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 4 | 0 | 138 | 138 | 22245 | 0 | 0
120 | Roughin Labor | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 32 | 0 | 736 | 0 | 736 | 22245 | 0 | 0
120 | Roughin Labor | PR | 697 | 12/26/18 | 12/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 26 | 0 | 754 | 0 | 754 | 22270 | 0 | 0
120 | Roughin Labor | PR | 704 | 12/26/18 | 12/28/18 | BE54 | Benites Portillo, Marvin E | 24 | 0 | 576 | 0 | 576 | 22277 | 0 | 0
120 | Roughin Labor | PR | 707 | 12/26/18 | 12/28/18 | CO69 | Cornejo Orellana, Carlos E | 8 | 0 | 168 | 0 | 168 | 22280 | 0 | 0
120 | Roughin Labor | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 160 | 0 | 160 | 22290 | 0 | 0
120 | Roughin Labor | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 22304 | 0 | 0
120 | Roughin Labor | PR | 732 | 12/26/18 | 12/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 26 | 0 | 572 | 0 | 572 | 22305 | 0 | 0
120 | Roughin Labor | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 10 | 0 | 330 | 0 | 330 | 22308 | 0 | 0
120 | Roughin Labor | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 10 | 0 | 370 | 0 | 370 | 22316 | 0 | 0
120 | Roughin Labor | PR | 746 | 12/26/18 | 12/28/18 | RA55 | Ramos Herrera, Franklin J | 18 | 0 | 414 | 0 | 414 | 22319 | 0 | 0
120 | Roughin Labor | PR | 2 | 01/02/19 | 01/04/19 | AM03 | Amaya Gonzalez, Edilberto A | 24 | 0 | 696 | 0 | 696 | 22342 | 0 | 0
120 | Roughin Labor | PR | 9 | 01/02/19 | 01/04/19 | BE54 | Benites Portillo, Marvin E | 16 | 0 | 384 | 0 | 384 | 22349 | 0 | 0
120 | Roughin Labor | PR | 12 | 01/02/19 | 01/04/19 | CO69 | Cornejo Orellana, Carlos E | 24 | 0 | 504 | 0 | 504 | 22352 | 0 | 0
120 | Roughin Labor | PR | 24 | 01/02/19 | 01/04/19 | FR04 | Frausto Mendoza, Pedro | 24 | 0 | 504 | 0 | 504 | 22365 | 0 | 0
120 | Roughin Labor | PR | 36 | 01/02/19 | 01/04/19 | JI50 | Jimenez Alvarenga, Gerson M | 24 | 0 | 528 | 0 | 528 | 22377 | 0 | 0
120 | Roughin Labor | PR | 46 | 01/02/19 | 01/04/19 | PA11 | Paco Leyva, Orlando | 24 | 0 | 888 | 0 | 888 | 22387 | 0 | 0
120 | Roughin Labor | PR | 49 | 01/02/19 | 01/04/19 | RA55 | Ramos Herrera, Franklin J | 24 | 0 | 552 | 0 | 552 | 22390 | 0 | 0
120 | Roughin Labor | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 24 | 0 | 696 | 0 | 696 | 22412 | 0 | 0
120 | Roughin Labor | PR | 217 | 01/09/19 | 01/11/19 | BE54 | Benites Portillo, Marvin E | 39 | 0 | 936 | 0 | 936 | 22419 | 0 | 0
120 | Roughin Labor | PR | 220 | 01/09/19 | 01/11/19 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 840 | 0 | 840 | 22422 | 0 | 0
120 | Roughin Labor | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 352 | 0 | 352 | 22426 | 0 | 0
120 | Roughin Labor | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 320 | 0 | 320 | 22432 | 0 | 0
120 | Roughin Labor | PR | 232 | 01/09/19 | 01/11/19 | FR04 | Frausto Mendoza, Pedro | 16 | 0 | 336 | 0 | 336 | 22434 | 0 | 0
120 | Roughin Labor | PR | 245 | 01/09/19 | 01/11/19 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 880 | 0 | 880 | 22447 | 0 | 0
120 | Roughin Labor | PR | 248 | 01/09/19 | 01/11/19 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1320 | 0 | 1320 | 22450 | 0 | 0
120 | Roughin Labor | PR | 256 | 01/09/19 | 01/11/19 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1480 | 0 | 1480 | 22458 | 0 | 0
120 | Roughin Labor | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 2 | 0 | 94 | 0 | 94 | 22460 | 0 | 0
120 | Roughin Labor | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 32 | 0 | 736 | 0 | 736 | 22461 | 0 | 0
120 | Roughin Labor | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8 | 0 | 348 | 348 | 22485 | 0 | 0
120 | Roughin Labor | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 22485 | 0 | 0
120 | Roughin Labor | PR | 466 | 01/16/19 | 01/18/19 | AS10 | Ascencio, Jose L | 0 | 8 | 0 | 336 | 336 | 22487 | 0 | 0
120 | Roughin Labor | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 0 | 8 | 0 | 288 | 288 | 22492 | 0 | 0
120 | Roughin Labor | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 960 | 0 | 960 | 22492 | 0 | 0
120 | Roughin Labor | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 0 | 8 | 0 | 192 | 192 | 22493 | 0 | 0
120 | Roughin Labor | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 40 | 0 | 640 | 0 | 640 | 22493 | 0 | 0
120 | Roughin Labor | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 8 | 0 | 252 | 252 | 22496 | 0 | 0
120 | Roughin Labor | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 840 | 0 | 840 | 22496 | 0 | 0
120 | Roughin Labor | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 0 | 4 | 0 | 102 | 102 | 22499 | 0 | 0
120 | Roughin Labor | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 4 | 0 | 68 | 0 | 68 | 22499 | 0 | 0
120 | Roughin Labor | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 352 | 0 | 352 | 22500 | 0 | 0
120 | Roughin Labor | PR | 487 | 01/16/19 | 01/18/19 | FR04 | Frausto Mendoza, Pedro | 40 | 0 | 840 | 0 | 840 | 22508 | 0 | 0
120 | Roughin Labor | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 264 | 264 | 22521 | 0 | 0
120 | Roughin Labor | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 880 | 0 | 880 | 22521 | 0 | 0
120 | Roughin Labor | PR | 503 | 01/16/19 | 01/18/19 | LI49 | Lima Romero, Melvin A | 32 | 0 | 1056 | 0 | 1056 | 22524 | 0 | 0
120 | Roughin Labor | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 444 | 444 | 22532 | 0 | 0
120 | Roughin Labor | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 33 | 0 | 1221 | 0 | 1221 | 22532 | 0 | 0
120 | Roughin Labor | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 4 | 0 | 188 | 0 | 188 | 22534 | 0 | 0
120 | Roughin Labor | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 276 | 276 | 22535 | 0 | 0
120 | Roughin Labor | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 22535 | 0 | 0
120 | Roughin Labor | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 32 | 0 | 928 | 0 | 928 | 22558 | 0 | 0
120 | Roughin Labor | PR | 720 | 01/23/19 | 01/25/19 | BE54 | Benites Portillo, Marvin E | 40 | 0 | 960 | 0 | 960 | 22565 | 0 | 0
120 | Roughin Labor | PR | 721 | 01/23/19 | 01/25/19 | CA07 | Cabrera Morales, Antonio | 24 | 0 | 384 | 0 | 384 | 22566 | 0 | 0
120 | Roughin Labor | PR | 724 | 01/23/19 | 01/25/19 | CO69 | Cornejo Orellana, Carlos E | 40 | 0 | 840 | 0 | 840 | 22569 | 0 | 0
120 | Roughin Labor | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 22573 | 0 | 0
120 | Roughin Labor | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 160 | 0 | 160 | 22579 | 0 | 0
120 | Roughin Labor | PR | 736 | 01/23/19 | 01/25/19 | FR04 | Frausto Mendoza, Pedro | 16 | 0 | 336 | 0 | 336 | 22581 | 0 | 0
120 | Roughin Labor | PR | 749 | 01/23/19 | 01/25/19 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 880 | 0 | 880 | 22594 | 0 | 0
120 | Roughin Labor | PR | 752 | 01/23/19 | 01/25/19 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1320 | 0 | 1320 | 22597 | 0 | 0
120 | Roughin Labor | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 27 | 0 | 999 | 0 | 999 | 22605 | 0 | 0
120 | Roughin Labor | PR | 762 | 01/23/19 | 01/25/19 | QU35 | Quintanilla, Esteban R | 3 | 0 | 141 | 0 | 141 | 22607 | 0 | 0
120 | Roughin Labor | PR | 763 | 01/23/19 | 01/25/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 22608 | 0 | 0
120 | Roughin Labor | PR | 2 | 01/30/19 | 02/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 16 | 0 | 464 | 0 | 464 | 22631 | 0 | 0
120 | Roughin Labor | PR | 9 | 01/30/19 | 02/01/19 | BE54 | Benites Portillo, Marvin E | 32 | 0 | 768 | 0 | 768 | 22638 | 0 | 0
120 | Roughin Labor | PR | 12 | 01/30/19 | 02/01/19 | CO69 | Cornejo Orellana, Carlos E | 38 | 0 | 798 | 0 | 798 | 22641 | 0 | 0
120 | Roughin Labor | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22666 | 0 | 0
120 | Roughin Labor | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 16 | 0 | 528 | 0 | 528 | 22669 | 0 | 0
120 | Roughin Labor | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 32 | 0 | 1184 | 0 | 1184 | 22676 | 0 | 0
120 | Roughin Labor | PR | 49 | 01/30/19 | 02/01/19 | RA55 | Ramos Herrera, Franklin J | 36 | 0 | 828 | 0 | 828 | 22678 | 0 | 0
120 | Roughin Labor | PR | 157 | 02/06/19 | 02/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 34 | 0 | 986 | 0 | 986 | 22699 | 0 | 0
120 | Roughin Labor | PR | 164 | 02/06/19 | 02/08/19 | BE54 | Benites Portillo, Marvin E | 34 | 0 | 816 | 0 | 816 | 22706 | 0 | 0
120 | Roughin Labor | PR | 167 | 02/06/19 | 02/08/19 | CO69 | Cornejo Orellana, Carlos E | 19.5 | 0 | 409.5 | 0 | 409.5 | 22709 | 0 | 0
120 | Roughin Labor | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 22713 | 0 | 0
120 | Roughin Labor | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 10 | 0 | 220 | 0 | 220 | 22734 | 0 | 0
120 | Roughin Labor | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22737 | 0 | 0
120 | Roughin Labor | PR | 202 | 02/06/19 | 02/08/19 | PA11 | Paco Leyva, Orlando | 30 | 0 | 1110 | 0 | 1110 | 22744 | 0 | 0
120 | Roughin Labor | PR | 204 | 02/06/19 | 02/08/19 | RA55 | Ramos Herrera, Franklin J | 30 | 0 | 690 | 0 | 690 | 22746 | 0 | 0
120 | Roughin Labor | PR | 319 | 02/13/19 | 02/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 28 | 0 | 812 | 0 | 812 | 22768 | 0 | 0
120 | Roughin Labor | PR | 326 | 02/13/19 | 02/15/19 | BE54 | Benites Portillo, Marvin E | 18 | 0 | 432 | 0 | 432 | 22775 | 0 | 0
120 | Roughin Labor | PR | 329 | 02/13/19 | 02/15/19 | CO69 | Cornejo Orellana, Carlos E | 10 | 0 | 210 | 0 | 210 | 22778 | 0 | 0
120 | Roughin Labor | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 22782 | 0 | 0
120 | Roughin Labor | PR | 339 | 02/13/19 | 02/15/19 | ES09 | Escalante Escobar, Boanerge | 18 | 0 | 360 | 0 | 360 | 22788 | 0 | 0
120 | Roughin Labor | PR | 354 | 02/13/19 | 02/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 10 | 0 | 220 | 0 | 220 | 22805 | 0 | 0
120 | Roughin Labor | PR | 364 | 02/13/19 | 02/15/19 | PA11 | Paco Leyva, Orlando | 24 | 0 | 888 | 0 | 888 | 22815 | 0 | 0
120 | Roughin Labor | PR | 366 | 02/13/19 | 02/15/19 | RA55 | Ramos Herrera, Franklin J | 28 | 0 | 644 | 0 | 644 | 22817 | 0 | 0
120 | Roughin Labor | PR | 577 | 02/20/19 | 02/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 58 | 0 | 1682 | 0 | 1682 | 22839 | 0 | 0
120 | Roughin Labor | PR | 584 | 02/20/19 | 02/22/19 | BE54 | Benites Portillo, Marvin E | 48 | 0 | 1152 | 0 | 1152 | 22846 | 0 | 0
120 | Roughin Labor | PR | 587 | 02/20/19 | 02/22/19 | CO69 | Cornejo Orellana, Carlos E | 48 | 0 | 1008 | 0 | 1008 | 22849 | 0 | 0
120 | Roughin Labor | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 4 | 0 | 120 | 120 | 22859 | 0 | 0
120 | Roughin Labor | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 54 | 0 | 1080 | 0 | 1080 | 22859 | 0 | 0
120 | Roughin Labor | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 0 | 12 | 0 | 666 | 666 | 22885 | 0 | 0
120 | Roughin Labor | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 46 | 0 | 1702 | 0 | 1702 | 22885 | 0 | 0
120 | Roughin Labor | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 10 | 0 | 345 | 345 | 22887 | 0 | 0
120 | Roughin Labor | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 38 | 0 | 874 | 0 | 874 | 22887 | 0 | 0
120 | Roughin Labor | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 13 | 0 | 565.5 | 565.5 | 22909 | 0 | 0
120 | Roughin Labor | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 22909 | 0 | 0
120 | Roughin Labor | PR | 12 | 02/27/19 | 03/01/19 | CO69 | Cornejo Orellana, Carlos E | 36 | 0 | 756 | 0 | 756 | 22919 | 0 | 0
120 | Roughin Labor | PR | 16 | 02/27/19 | 03/01/19 | CR77 | Cruz Gonzalez, Julio C | 47 | 0 | 1034 | 0 | 1034 | 22923 | 0 | 0
120 | Roughin Labor | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 13 | 0 | 390 | 390 | 22930 | 0 | 0
120 | Roughin Labor | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 22930 | 0 | 0
120 | Roughin Labor | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 8 | 0 | 264 | 0 | 264 | 22953 | 0 | 0
120 | Roughin Labor | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 9 | 0 | 333 | 0 | 333 | 22957 | 0 | 0
120 | Roughin Labor | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 276 | 276 | 22959 | 0 | 0
120 | Roughin Labor | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 22959 | 0 | 0
120 | Roughin Labor | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 13 | 0 | 565.5 | 565.5 | 22981 | 0 | 0
120 | Roughin Labor | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 22981 | 0 | 0
120 | Roughin Labor | PR | 246 | 03/06/19 | 03/08/19 | AS10 | Ascencio, Jose L | 0 | 5 | 0 | 210 | 210 | 22983 | 0 | 0
120 | Roughin Labor | PR | 254 | 03/06/19 | 03/08/19 | CO69 | Cornejo Orellana, Carlos E | 44 | 0 | 924 | 0 | 924 | 22992 | 0 | 0
120 | Roughin Labor | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 8.5 | 0 | 280.5 | 280.5 | 22996 | 0 | 0
120 | Roughin Labor | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 880 | 0 | 880 | 22996 | 0 | 0
120 | Roughin Labor | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 13 | 0 | 390 | 390 | 23004 | 0 | 0
120 | Roughin Labor | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 23004 | 0 | 0
120 | Roughin Labor | PR | 266 | 03/06/19 | 03/08/19 | FR04 | Frausto Mendoza, Pedro | 5 | 0 | 105 | 0 | 105 | 23005 | 0 | 0
120 | Roughin Labor | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 14 | 0 | 777 | 777 | 23029 | 0 | 0
120 | Roughin Labor | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 35 | 0 | 1295 | 0 | 1295 | 23029 | 0 | 0
120 | Roughin Labor | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 13 | 0 | 448.5 | 448.5 | 23031 | 0 | 0
120 | Roughin Labor | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 23031 | 0 | 0
120 | Roughin Labor | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8 | 0 | 348 | 348 | 23053 | 0 | 0
120 | Roughin Labor | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 32 | 0 | 928 | 0 | 928 | 23053 | 0 | 0
120 | Roughin Labor | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 264 | 264 | 23067 | 0 | 0
120 | Roughin Labor | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 20 | 0 | 440 | 0 | 440 | 23067 | 0 | 0
120 | Roughin Labor | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 0 | 8 | 0 | 288 | 288 | 23071 | 0 | 0
120 | Roughin Labor | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 240 | 240 | 23074 | 0 | 0
120 | Roughin Labor | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 20 | 0 | 400 | 0 | 400 | 23074 | 0 | 0
120 | Roughin Labor | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 8 | 0 | 264 | 264 | 23088 | 0 | 0
120 | Roughin Labor | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 24 | 0 | 528 | 0 | 528 | 23088 | 0 | 0
120 | Roughin Labor | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 444 | 444 | 23099 | 0 | 0
120 | Roughin Labor | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 25 | 0 | 925 | 0 | 925 | 23099 | 0 | 0
120 | Roughin Labor | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 10 | 0 | 345 | 345 | 23101 | 0 | 0
120 | Roughin Labor | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 23101 | 0 | 0
120 | Roughin Labor | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 5 | 0 | 217.5 | 217.5 | 23126 | 0 | 0
120 | Roughin Labor | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 23126 | 0 | 0
120 | Roughin Labor | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 5 | 0 | 150 | 150 | 23147 | 0 | 0
120 | Roughin Labor | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 5 | 0 | 165 | 165 | 23161 | 0 | 0
120 | Roughin Labor | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 40 | 0 | 880 | 0 | 880 | 23161 | 0 | 0
120 | Roughin Labor | PR | 750 | 03/20/19 | 03/22/19 | PA11 | Paco Leyva, Orlando | 40 | 0 | 1480 | 0 | 1480 | 23171 | 0 | 0
120 | Roughin Labor | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 5 | 0 | 172.5 | 172.5 | 23173 | 0 | 0
120 | Roughin Labor | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 40 | 0 | 920 | 0 | 920 | 23173 | 0 | 0
120 | Roughin Labor | PR | 765 | 03/20/19 | 03/22/19 | SO71 | Sorto Regalado, Milton J | 24 | 0 | 384 | 0 | 384 | 23186 | 0 | 0
120 | Roughin Labor | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 6 | 0 | 261 | 261 | 23198 | 0 | 0
120 | Roughin Labor | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 23198 | 0 | 0
120 | Roughin Labor | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 264 | 264 | 23214 | 0 | 0
120 | Roughin Labor | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 2 | 0 | 44 | 0 | 44 | 23214 | 0 | 0
120 | Roughin Labor | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 10 | 0 | 300 | 300 | 23221 | 0 | 0
120 | Roughin Labor | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 32 | 0 | 640 | 0 | 640 | 23221 | 0 | 0
120 | Roughin Labor | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 10 | 0 | 330 | 330 | 23236 | 0 | 0
120 | Roughin Labor | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 16 | 0 | 352 | 0 | 352 | 23236 | 0 | 0
120 | Roughin Labor | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 9.5 | 0 | 527.25 | 527.25 | 23246 | 0 | 0
120 | Roughin Labor | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 24 | 0 | 888 | 0 | 888 | 23246 | 0 | 0
120 | Roughin Labor | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 10 | 0 | 345 | 345 | 23248 | 0 | 0
120 | Roughin Labor | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 36 | 0 | 828 | 0 | 828 | 23248 | 0 | 0
120 | Roughin Labor | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 12 | 0 | 348 | 0 | 348 | 23272 | 0 | 0
120 | Roughin Labor | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 704 | 0 | 704 | 23286 | 0 | 0
120 | Roughin Labor | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 480 | 0 | 480 | 23293 | 0 | 0
120 | Roughin Labor | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 11 | 0 | 407 | 0 | 407 | 23319 | 0 | 0
120 | Roughin Labor | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 13 | 0 | 299 | 0 | 299 | 23321 | 0 | 0
120 | Roughin Labor | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 8.5 | 0 | 369.75 | 369.75 | 23346 | 0 | 0
120 | Roughin Labor | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 23346 | 0 | 0
120 | Roughin Labor | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 264 | 264 | 23360 | 0 | 0
120 | Roughin Labor | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 528 | 0 | 528 | 23360 | 0 | 0
120 | Roughin Labor | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 240 | 240 | 23367 | 0 | 0
120 | Roughin Labor | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 320 | 0 | 320 | 23367 | 0 | 0
120 | Roughin Labor | PR | 371 | 04/10/19 | 04/12/19 | RA55 | Ramos Herrera, Franklin J | 0 | 8 | 0 | 276 | 276 | 23395 | 0 | 0
120 | Roughin Labor | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 6 | 0 | 261 | 261 | 23420 | 0 | 0
120 | Roughin Labor | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 40 | 0 | 1160 | 0 | 1160 | 23420 | 0 | 0
120 | Roughin Labor | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 5 | 0 | 165 | 165 | 23434 | 0 | 0
120 | Roughin Labor | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 23434 | 0 | 0
120 | Roughin Labor | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 5 | 0 | 150 | 150 | 23441 | 0 | 0
120 | Roughin Labor | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 320 | 0 | 320 | 23441 | 0 | 0
120 | Roughin Labor | PR | 567 | 04/17/19 | 04/19/19 | PA11 | Paco Leyva, Orlando | 5 | 0 | 200 | 0 | 200 | 23468 | 0 | 0
120 | Roughin Labor | PR | 569 | 04/17/19 | 04/19/19 | RA55 | Ramos Herrera, Franklin J | 0 | 5 | 0 | 172.5 | 172.5 | 23470 | 0 | 0
120 | Roughin Labor | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 1 | 0 | 48 | 48 | 23496 | 0 | 0
120 | Roughin Labor | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 31 | 0 | 992 | 0 | 992 | 23496 | 0 | 0
120 | Roughin Labor | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 75 | 75 | 23510 | 0 | 0
120 | Roughin Labor | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 23510 | 0 | 0
120 | Roughin Labor | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 528 | 0 | 528 | 23516 | 0 | 0
120 | Roughin Labor | PR | 786 | 04/24/19 | 04/26/19 | PA11 | Paco Leyva, Orlando | 7 | 0 | 280 | 0 | 280 | 23543 | 0 | 0
120 | Roughin Labor | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 4 | 0 | 104 | 0 | 104 | 23545 | 0 | 0
120 | Roughin Labor | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 19 | 0 | 608 | 0 | 608 | 23568 | 0 | 0
120 | Roughin Labor | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 352 | 0 | 352 | 23589 | 0 | 0
120 | Roughin Labor | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23604 | 0 | 0
120 | Roughin Labor | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 4 | 0 | 192 | 192 | 23643 | 0 | 0
120 | Roughin Labor | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23643 | 0 | 0
120 | Roughin Labor | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 176 | 0 | 176 | 23664 | 0 | 0
120 | Roughin Labor | PR | 208 | 05/08/19 | 05/10/19 | PA11 | Paco Leyva, Orlando | 0 | 4 | 0 | 240 | 240 | 23692 | 0 | 0
120 | Roughin Labor | PR | 210 | 05/08/19 | 05/10/19 | RA55 | Ramos Herrera, Franklin J | 0 | 4 | 0 | 156 | 156 | 23694 | 0 | 0
120 | Roughin Labor | PR | 231 | 05/08/19 | 05/10/19 | WA35 | Waites, Thaddeus Z | 1 | 0 | 45 | 0 | 45 | 23716 | 0 | 0
120 | Roughin Labor | PR | 390 | 05/15/19 | 05/17/19 | AM03 | Amaya Gonzalez, Edilberto A | 5 | 0 | 160 | 0 | 160 | 23721 | 0 | 0
120 | Roughin Labor | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23798 | 0 | 0
120 | Roughin Labor | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 8 | 0 | 320 | 0 | 320 | 23847 | 0 | 0
120 | Roughin Labor | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23881 | 0 | 0
120 | Roughin Labor | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 160 | 0 | 160 | 24002 | 0 | 0
120 | Roughin Labor | PR | 835 | 06/26/19 | 06/28/19 | AM03 | Amaya Gonzalez, Edilberto A | 3 | 0 | 96 | 0 | 96 | 24179 | 0 | 0
120 | Roughin Labor | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24270 | 0 | 0
120 | Roughin Labor | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -138.15 |  | 0 | 0
120 | Roughin Labor | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 24817 | 0 | 0
120 | Roughin Labor | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 7 | 0 | 280 | 0 | 280 | 24829 | 0 | 0
120 | Roughin Labor | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 7 | 0 | 182 | 0 | 182 | 24831 | 0 | 0
120 | Roughin Labor | PR | 520 | 09/18/19 | 09/20/19 | PA11 | Paco Leyva, Orlando | 3 | 0 | 120 | 0 | 120 | 25206 | 0 | 0
120 | Roughin Labor | PR | 522 | 09/18/19 | 09/20/19 | RA55 | Ramos Herrera, Franklin J | 3 | 0 | 78 | 0 | 78 | 25208 | 0 | 0
130 | Finish Labor | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 2 | 0 | 88 | 0 | 88 | 20360 | 0 | 0
130 | Finish Labor | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 2 | 0 | -88 | 0 | -88 | 20403 | 0 | 0
130 | Finish Labor | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 22617 | 0 | 0
130 | Finish Labor | PR | 182 | 02/06/19 | 02/08/19 | GE70 | Gerard, Jordan E | 24 | 0 | 816 | 0 | 816 | 22724 | 0 | 0
130 | Finish Labor | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 8 | 0 | 184 | 0 | 184 | 22726 | 0 | 0
130 | Finish Labor | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22748 | 0 | 0
130 | Finish Labor | PR | 344 | 02/13/19 | 02/15/19 | GE70 | Gerard, Jordan E | 22 | 0 | 748 | 0 | 748 | 22794 | 0 | 0
130 | Finish Labor | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 2 | 0 | 75 | 75 | 22858 | 0 | 0
130 | Finish Labor | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 4 | 0 | 100 | 0 | 100 | 22858 | 0 | 0
130 | Finish Labor | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 2 | 0 | 54 | 54 | 22860 | 0 | 0
130 | Finish Labor | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 8 | 0 | 144 | 0 | 144 | 22860 | 0 | 0
130 | Finish Labor | PR | 602 | 02/20/19 | 02/22/19 | GE70 | Gerard, Jordan E | 44 | 0 | 1496 | 0 | 1496 | 22864 | 0 | 0
130 | Finish Labor | PR | 604 | 02/20/19 | 02/22/19 | GO51 | Gomez Reyes, Edith N | 10 | 0 | 230 | 0 | 230 | 22866 | 0 | 0
130 | Finish Labor | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 0 | 2 | 0 | 54 | 54 | 22889 | 0 | 0
130 | Finish Labor | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 8 | 0 | 144 | 0 | 144 | 22889 | 0 | 0
130 | Finish Labor | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 9 | 0 | 423 | 0 | 423 | 22896 | 0 | 0
130 | Finish Labor | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 0 | 2 | 0 | 51 | 51 | 22900 | 0 | 0
130 | Finish Labor | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 12 | 0 | 204 | 0 | 204 | 22900 | 0 | 0
130 | Finish Labor | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 2 | 0 | 48 | 48 | 22903 | 0 | 0
130 | Finish Labor | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 128 | 0 | 128 | 22903 | 0 | 0
130 | Finish Labor | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 8 | 0 | 300 | 300 | 22929 | 0 | 0
130 | Finish Labor | PR | 24 | 02/27/19 | 03/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 8 | 0 | 216 | 216 | 22931 | 0 | 0
130 | Finish Labor | PR | 29 | 02/27/19 | 03/01/19 | GE70 | Gerard, Jordan E | 48 | 0 | 1632 | 0 | 1632 | 22936 | 0 | 0
130 | Finish Labor | PR | 31 | 02/27/19 | 03/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 8 | 0 | 276 | 276 | 22938 | 0 | 0
130 | Finish Labor | PR | 54 | 02/27/19 | 03/01/19 | RE91 | Reyes, Maria E | 0 | 8 | 0 | 216 | 216 | 22961 | 0 | 0
130 | Finish Labor | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 564 | 564 | 22968 | 0 | 0
130 | Finish Labor | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 3 | 0 | 141 | 0 | 141 | 22968 | 0 | 0
130 | Finish Labor | PR | 65 | 02/27/19 | 03/01/19 | ST02 | Stahlschmidt, John P | 0 | 8 | 0 | 204 | 204 | 22972 | 0 | 0
130 | Finish Labor | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 8 | 0 | 192 | 192 | 22975 | 0 | 0
130 | Finish Labor | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 9 | 0 | 337.5 | 337.5 | 23003 | 0 | 0
130 | Finish Labor | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 8 | 0 | 200 | 0 | 200 | 23003 | 0 | 0
130 | Finish Labor | PR | 270 | 03/06/19 | 03/08/19 | GE70 | Gerard, Jordan E | 48 | 0 | 1632 | 0 | 1632 | 23009 | 0 | 0
130 | Finish Labor | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 0 | 7.5 | 0 | 528.75 | 528.75 | 23039 | 0 | 0
130 | Finish Labor | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 0 | 1 | 0 | 25.5 | 25.5 | 23043 | 0 | 0
130 | Finish Labor | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 8 | 0 | 136 | 0 | 136 | 23043 | 0 | 0
130 | Finish Labor | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 9 | 0 | 216 | 216 | 23046 | 0 | 0
130 | Finish Labor | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 128 | 0 | 128 | 23046 | 0 | 0
130 | Finish Labor | PR | 489 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 8 | 0 | 208 | 0 | 208 | 22799 | 0 | 0
130 | Finish Labor | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 2 | 0 | 75 | 75 | 23072 | 0 | 0
130 | Finish Labor | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 6 | 0 | 150 | 0 | 150 | 23072 | 0 | 0
130 | Finish Labor | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 8 | 0 | 300 | 300 | 23073 | 0 | 0
130 | Finish Labor | PR | 517 | 03/13/19 | 03/15/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1360 | 0 | 1360 | 23079 | 0 | 0
130 | Finish Labor | PR | 544 | 03/13/19 | 03/15/19 | RO06 | Roberts, Lake A | 8 | 0 | 144 | 0 | 144 | 23106 | 0 | 0
130 | Finish Labor | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 564 | 564 | 23109 | 0 | 0
130 | Finish Labor | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 0 | 6 | 0 | 153 | 153 | 23114 | 0 | 0
130 | Finish Labor | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 2 | 0 | 34 | 0 | 34 | 23114 | 0 | 0
130 | Finish Labor | PR | 554 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 0 | 8 | 0 | 312 | 312 | 23116 | 0 | 0
130 | Finish Labor | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 0 | 7.5 | 0 | 270 | 270 | 23144 | 0 | 0
130 | Finish Labor | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 7.5 | 0 | 281.25 | 281.25 | 23145 | 0 | 0
130 | Finish Labor | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 7.5 | 0 | 281.25 | 281.25 | 23146 | 0 | 0
130 | Finish Labor | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 31 | 0 | 1054 | 0 | 1054 | 23152 | 0 | 0
130 | Finish Labor | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 7.5 | 0 | 528.75 | 528.75 | 23181 | 0 | 0
130 | Finish Labor | PR | 768 | 03/20/19 | 03/22/19 | TA96 | Taylor, Evan R | 0 | 7.5 | 0 | 292.5 | 292.5 | 23189 | 0 | 0
130 | Finish Labor | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 7.5 | 0 | 180 | 180 | 23190 | 0 | 0
130 | Finish Labor | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 0 | 8 | 0 | 300 | 300 | 23220 | 0 | 0
130 | Finish Labor | PR | 943 | 03/27/19 | 03/29/19 | GE70 | Gerard, Jordan E | 43 | 0 | 1462 | 0 | 1462 | 23227 | 0 | 0
130 | Finish Labor | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 564 | 564 | 23256 | 0 | 0
130 | Finish Labor | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 0 | 6 | 0 | 153 | 153 | 23262 | 0 | 0
130 | Finish Labor | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 2 | 0 | 34 | 0 | 34 | 23262 | 0 | 0
130 | Finish Labor | PR | 981 | 03/27/19 | 03/29/19 | TR60 | Trower-Kelly, Fidel D | 0 | 8 | 0 | 192 | 192 | 23265 | 0 | 0
130 | Finish Labor | PR | 105 | 04/03/19 | 04/05/19 | GE70 | Gerard, Jordan E | 40.5 | 0 | 1377 | 0 | 1377 | 23299 | 0 | 0
130 | Finish Labor | PR | 108 | 04/03/19 | 04/05/19 | GU17 | Guerrero, Ali A | 15.5 | 0 | 248 | 0 | 248 | 23302 | 0 | 0
130 | Finish Labor | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 2 | 0 | 94 | 0 | 94 | 23329 | 0 | 0
130 | Finish Labor | PR | 348 | 04/10/19 | 04/12/19 | GE70 | Gerard, Jordan E | 36 | 0 | 1296 | 0 | 1296 | 23372 | 0 | 0
130 | Finish Labor | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 0 | 4 | 0 | 96 | 96 | 23375 | 0 | 0
130 | Finish Labor | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 32 | 0 | 512 | 0 | 512 | 23375 | 0 | 0
130 | Finish Labor | PR | 546 | 04/17/19 | 04/19/19 | GE70 | Gerard, Jordan E | 45 | 0 | 1620 | 0 | 1620 | 23447 | 0 | 0
130 | Finish Labor | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 0 | 4 | 0 | 96 | 96 | 23450 | 0 | 0
130 | Finish Labor | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 40 | 0 | 640 | 0 | 640 | 23450 | 0 | 0
130 | Finish Labor | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 75 | 75 | 23510 | 0 | 0
130 | Finish Labor | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 600 | 0 | 600 | 23510 | 0 | 0
130 | Finish Labor | PR | 765 | 04/24/19 | 04/26/19 | GE70 | Gerard, Jordan E | 44 | 0 | 1584 | 0 | 1584 | 23522 | 0 | 0
130 | Finish Labor | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 0 | 4 | 0 | 102 | 102 | 23525 | 0 | 0
130 | Finish Labor | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 23525 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 2 | 0 | 147 | 147 | 23554 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 23554 | 0 | 0
130 | Finish Labor | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 8 | 0 | 216 | 216 | 23560 | 0 | 0
130 | Finish Labor | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 8 | 0 | 192 | 192 | 23561 | 0 | 0
130 | Finish Labor | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 75 | 75 | 23582 | 0 | 0
130 | Finish Labor | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 1000 | 0 | 1000 | 23582 | 0 | 0
130 | Finish Labor | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 0 | 2.5 | 0 | 135 | 135 | 23595 | 0 | 0
130 | Finish Labor | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 41.5 | 0 | 1494 | 0 | 1494 | 23595 | 0 | 0
130 | Finish Labor | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 0 | 12 | 0 | 306 | 306 | 23598 | 0 | 0
130 | Finish Labor | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 23598 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 8 | 0 | 588 | 588 | 23628 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 4 | 0 | 196 | 0 | 196 | 23628 | 0 | 0
130 | Finish Labor | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 8 | 0 | 216 | 216 | 23635 | 0 | 0
130 | Finish Labor | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 8 | 0 | 192 | 192 | 23636 | 0 | 0
130 | Finish Labor | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 5 | 0 | 187.5 | 187.5 | 23657 | 0 | 0
130 | Finish Labor | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 1000 | 0 | 1000 | 23657 | 0 | 0
130 | Finish Labor | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 0 | 5 | 0 | 270 | 270 | 23670 | 0 | 0
130 | Finish Labor | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1440 | 0 | 1440 | 23670 | 0 | 0
130 | Finish Labor | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 0 | 5 | 0 | 127.5 | 127.5 | 23673 | 0 | 0
130 | Finish Labor | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 23673 | 0 | 0
130 | Finish Labor | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 3 | 0 | 112.5 | 112.5 | 23736 | 0 | 0
130 | Finish Labor | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 1000 | 0 | 1000 | 23736 | 0 | 0
130 | Finish Labor | PR | 418 | 05/15/19 | 05/17/19 | GE70 | Gerard, Jordan E | 38.5 | 0 | 1386 | 0 | 1386 | 23749 | 0 | 0
130 | Finish Labor | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 0 | 4.5 | 0 | 114.75 | 114.75 | 23752 | 0 | 0
130 | Finish Labor | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 23752 | 0 | 0
130 | Finish Labor | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 11 | 0 | 539 | 0 | 539 | 23782 | 0 | 0
130 | Finish Labor | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 23786 | 0 | 0
130 | Finish Labor | PR | 617 | 05/22/19 | 05/24/19 | CR77 | Cruz Gonzalez, Julio C | 33.5 | 0 | 837.5 | 0 | 837.5 | 23812 | 0 | 0
130 | Finish Labor | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 0 | 4 | 0 | 216 | 216 | 23825 | 0 | 0
130 | Finish Labor | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1440 | 0 | 1440 | 23825 | 0 | 0
130 | Finish Labor | PR | 633 | 05/22/19 | 05/24/19 | GU17 | Guerrero, Ali A | 26 | 0 | 442 | 0 | 442 | 23828 | 0 | 0
130 | Finish Labor | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 23862 | 0 | 0
130 | Finish Labor | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 4.5 | 0 | 81 | 0 | 81 | 23865 | 0 | 0
130 | Finish Labor | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 4.5 | 0 | 72 | 0 | 72 | 23866 | 0 | 0
130 | Finish Labor | PR | 891 | 05/29/19 | 05/31/19 | CR77 | Cruz Gonzalez, Julio C | 23 | 0 | 575 | 0 | 575 | 23891 | 0 | 0
130 | Finish Labor | PR | 904 | 05/29/19 | 05/31/19 | GE70 | Gerard, Jordan E | 36 | 0 | 1296 | 0 | 1296 | 23904 | 0 | 0
130 | Finish Labor | PR | 907 | 05/29/19 | 05/31/19 | GU17 | Guerrero, Ali A | 33 | 0 | 561 | 0 | 561 | 23907 | 0 | 0
130 | Finish Labor | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 23937 | 0 | 0
130 | Finish Labor | PR | 941 | 05/29/19 | 05/31/19 | ST02 | Stahlschmidt, John P | 33 | 0 | 627 | 0 | 627 | 23941 | 0 | 0
130 | Finish Labor | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 23944 | 0 | 0
130 | Finish Labor | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 75 | 75 | 23968 | 0 | 0
130 | Finish Labor | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 1000 | 0 | 1000 | 23968 | 0 | 0
130 | Finish Labor | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 0 | 2 | 0 | 108 | 108 | 23981 | 0 | 0
130 | Finish Labor | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1440 | 0 | 1440 | 23981 | 0 | 0
130 | Finish Labor | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 0 | 1 | 0 | 25.5 | 25.5 | 23984 | 0 | 0
130 | Finish Labor | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 23984 | 0 | 0
130 | Finish Labor | PR | 243 | 06/05/19 | 06/07/19 | ST02 | Stahlschmidt, John P | 32 | 0 | 608 | 0 | 608 | 24018 | 0 | 0
130 | Finish Labor | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 800 | 0 | 800 | 24044 | 0 | 0
130 | Finish Labor | PR | 474 | 06/12/19 | 06/14/19 | GE70 | Gerard, Jordan E | 40 | 0 | 1440 | 0 | 1440 | 24055 | 0 | 0
130 | Finish Labor | PR | 477 | 06/12/19 | 06/14/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 24058 | 0 | 0
130 | Finish Labor | PR | 511 | 06/12/19 | 06/14/19 | ST02 | Stahlschmidt, John P | 40 | 0 | 760 | 0 | 760 | 24092 | 0 | 0
130 | Finish Labor | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24119 | 0 | 0
130 | Finish Labor | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 24 | 0 | 408 | 0 | 408 | 24134 | 0 | 0
130 | Finish Labor | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 24172 | 0 | 0
130 | Finish Labor | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 2 | 0 | 50 | 0 | 50 | 24195 | 0 | 0
130 | Finish Labor | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 9 | 0 | 153 | 0 | 153 | 24210 | 0 | 0
130 | Finish Labor | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 6 | 0 | 150 | 0 | 150 | 24270 | 0 | 0
130 | Finish Labor | PR | 35 | 07/03/19 | 07/05/19 | GE70 | Gerard, Jordan E | 34 | 0 | 1224 | 0 | 1224 | 24282 | 0 | 0
130 | Finish Labor | PR | 38 | 07/03/19 | 07/05/19 | GU17 | Guerrero, Ali A | 32 | 0 | 544 | 0 | 544 | 24285 | 0 | 0
130 | Finish Labor | PR | 70 | 07/03/19 | 07/05/19 | ST02 | Stahlschmidt, John P | 33 | 0 | 627 | 0 | 627 | 24318 | 0 | 0
130 | Finish Labor | PR | 73 | 07/03/19 | 07/05/19 | TR60 | Trower-Kelly, Fidel D | 33 | 0 | 594 | 0 | 594 | 24321 | 0 | 0
130 | Finish Labor | PR | 74 | 07/03/19 | 07/05/19 | VA98 | Vazquez Popoca, Jose N | 33 | 0 | 528 | 0 | 528 | 24322 | 0 | 0
130 | Finish Labor | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 18 | 0 | 450 | 0 | 450 | 24344 | 0 | 0
130 | Finish Labor | PR | 304 | 07/10/19 | 07/12/19 | GE70 | Gerard, Jordan E | 8 | 0 | 288 | 0 | 288 | 24356 | 0 | 0
130 | Finish Labor | PR | 307 | 07/10/19 | 07/12/19 | GU17 | Guerrero, Ali A | 32 | 0 | 544 | 0 | 544 | 24359 | 0 | 0
130 | Finish Labor | PR | 344 | 07/10/19 | 07/12/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 24396 | 0 | 0
130 | Finish Labor | PR | 345 | 07/10/19 | 07/12/19 | VA98 | Vazquez Popoca, Jose N | 24 | 0 | 384 | 0 | 384 | 24397 | 0 | 0
130 | Finish Labor | PR | 522 | 07/17/19 | 07/19/19 | CR77 | Cruz Gonzalez, Julio C | 38.5 | 0 | 962.5 | 0 | 962.5 | 24421 | 0 | 0
130 | Finish Labor | PR | 534 | 07/17/19 | 07/19/19 | GE70 | Gerard, Jordan E | 32 | 0 | 1152 | 0 | 1152 | 24433 | 0 | 0
130 | Finish Labor | PR | 537 | 07/17/19 | 07/19/19 | GU17 | Guerrero, Ali A | 31.5 | 0 | 535.5 | 0 | 535.5 | 24436 | 0 | 0
130 | Finish Labor | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 24466 | 0 | 0
130 | Finish Labor | PR | 571 | 07/17/19 | 07/19/19 | ST02 | Stahlschmidt, John P | 32 | 0 | 608 | 0 | 608 | 24470 | 0 | 0
130 | Finish Labor | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 16 | 0 | 288 | 0 | 288 | 24473 | 0 | 0
130 | Finish Labor | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 24474 | 0 | 0
130 | Finish Labor | PR | 626 | 07/24/19 | 07/26/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 1000 | 0 | 1000 | 24575 | 0 | 0
130 | Finish Labor | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 16 | 0 | 576 | 0 | 576 | 24586 | 0 | 0
130 | Finish Labor | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 8 | 0 | 136 | 0 | 136 | 24589 | 0 | 0
130 | Finish Labor | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 15 | 0 | 735 | 0 | 735 | 24619 | 0 | 0
130 | Finish Labor | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 24623 | 0 | 0
130 | Finish Labor | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 24 | 0 | 432 | 0 | 432 | 24626 | 0 | 0
130 | Finish Labor | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 24 | 0 | 408 | 0 | 408 | 24627 | 0 | 0
130 | Finish Labor | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24649 | 0 | 0
130 | Finish Labor | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 29 | 0 | 1044 | 0 | 1044 | 24660 | 0 | 0
130 | Finish Labor | PR | 32 | 07/31/19 | 08/02/19 | GU17 | Guerrero, Ali A | 40 | 0 | 680 | 0 | 680 | 24663 | 0 | 0
130 | Finish Labor | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 144 | 0 | 144 | 24699 | 0 | 0
130 | Finish Labor | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 272 | 0 | 272 | 24700 | 0 | 0
130 | Finish Labor | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24723 | 0 | 0
130 | Finish Labor | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 16 | 0 | 576 | 0 | 576 | 24735 | 0 | 0
130 | Finish Labor | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 32 | 0 | 544 | 0 | 544 | 24738 | 0 | 0
130 | Finish Labor | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 24767 | 0 | 0
130 | Finish Labor | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24796 | 0 | 0
130 | Finish Labor | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 16 | 0 | 576 | 0 | 576 | 24808 | 0 | 0
130 | Finish Labor | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 6.5 | 0 | 110.5 | 0 | 110.5 | 24811 | 0 | 0
130 | Finish Labor | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 24840 | 0 | 0
130 | Finish Labor | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 6 | 0 | 210 | 0 | 210 | 24841 | 0 | 0
130 | Finish Labor | PR | 813 | 08/21/19 | 08/23/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 24871 | 0 | 0
130 | Finish Labor | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 18 | 0 | 648 | 0 | 648 | 24883 | 0 | 0
130 | Finish Labor | PR | 828 | 08/21/19 | 08/23/19 | GU17 | Guerrero, Ali A | 16 | 0 | 272 | 0 | 272 | 24886 | 0 | 0
130 | Finish Labor | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 4 | 0 | 196 | 0 | 196 | 24916 | 0 | 0
130 | Finish Labor | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 8 | 0 | 392 | 0 | 392 | 24991 | 0 | 0
130 | Finish Labor | PR | 25 | 09/04/19 | 09/06/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 400 | 0 | 400 | 25023 | 0 | 0
130 | Finish Labor | PR | 37 | 09/04/19 | 09/06/19 | GE70 | Gerard, Jordan E | 24 | 0 | 864 | 0 | 864 | 25035 | 0 | 0
130 | Finish Labor | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 6 | 0 | 294 | 0 | 294 | 25068 | 0 | 0
130 | Finish Labor | PR | 249 | 09/11/19 | 09/13/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 25098 | 0 | 0
130 | Finish Labor | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 6 | 0 | 174 | 0 | 174 | 25100 | 0 | 0
130 | Finish Labor | PR | 261 | 09/11/19 | 09/13/19 | GE70 | Gerard, Jordan E | 13 | 0 | 468 | 0 | 468 | 25110 | 0 | 0
130 | Finish Labor | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 25142 | 0 | 0
130 | Finish Labor | PR | 498 | 09/18/19 | 09/20/19 | GE70 | Gerard, Jordan E | 5 | 0 | 180 | 0 | 180 | 25184 | 0 | 0
130 | Finish Labor | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 25217 | 0 | 0
130 | Finish Labor | PR | 654 | 09/25/19 | 09/27/19 | GE70 | Gerard, Jordan E | 3 | 0 | 108 | 0 | 108 | 25259 | 0 | 0
130 | Finish Labor | PR | 30 | 10/02/19 | 10/04/19 | GE70 | Gerard, Jordan E | 3 | 0 | 108 | 0 | 108 | 25337 | 0 | 0
130 | Finish Labor | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 25348 | 0 | 0
140 | Gas Labor | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 24 | 0 | 456 | 0 | 456 | 21415 | 0 | 0
140 | Gas Labor | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 24 | 0 | 672 | 0 | 672 | 21439 | 0 | 0
140 | Gas Labor | PR | 480 | 10/17/18 | 10/19/18 | MO56 | Montenegro, Carlos E | 40 | 0 | 1120 | 0 | 1120 | 21513 | 0 | 0
140 | Gas Labor | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 6 | 0 | 252 | 252 | 21544 | 0 | 0
140 | Gas Labor | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 32 | 0 | 896 | 0 | 896 | 21544 | 0 | 0
140 | Gas Labor | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 4 | 0 | 162 | 162 | 21614 | 0 | 0
140 | Gas Labor | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 24 | 0 | 648 | 0 | 648 | 21614 | 0 | 0
140 | Gas Labor | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 30 | 0 | 840 | 0 | 840 | 21617 | 0 | 0
140 | Gas Labor | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 2 | 0 | 81 | 81 | 21686 | 0 | 0
140 | Gas Labor | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 216 | 0 | 216 | 21686 | 0 | 0
140 | Gas Labor | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 2 | 0 | 84 | 84 | 21689 | 0 | 0
140 | Gas Labor | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21689 | 0 | 0
140 | Gas Labor | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 2 | 0 | 81 | 81 | 21759 | 0 | 0
140 | Gas Labor | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 14 | 0 | 378 | 0 | 378 | 21759 | 0 | 0
140 | Gas Labor | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 2 | 0 | 84 | 84 | 21762 | 0 | 0
140 | Gas Labor | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 8 | 0 | 224 | 0 | 224 | 21762 | 0 | 0
140 | Gas Labor | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 1 | 0 | 37 | 0 | 37 | 22171 | 0 | 0
140 | Gas Labor | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 232 | 0 | 232 | 22558 | 0 | 0
140 | Gas Labor | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22669 | 0 | 0
140 | Gas Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23087 | 0 | 0
140 | Gas Labor | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 148 | 0 | 148 | 23246 | 0 | 0
140 | Gas Labor | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 12 | 0 | 348 | 0 | 348 | 23272 | 0 | 0
140 | Gas Labor | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 3 | 0 | 69 | 0 | 69 | 23321 | 0 | 0
140 | Gas Labor | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 5 | 0 | 160 | 0 | 160 | 23496 | 0 | 0
140 | Gas Labor | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 5 | 0 | 130 | 0 | 130 | 23545 | 0 | 0
140 | Gas Labor | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 5 | 0 | 160 | 0 | 160 | 23876 | 0 | 0
140 | Gas Labor | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 160 | 0 | 160 | 23926 | 0 | 0
140 | Gas Labor | PR | 178 | 06/05/19 | 06/07/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23953 | 0 | 0
140 | Gas Labor | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 23990 | 0 | 0
140 | Gas Labor | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 27 | 0 | 1080 | 0 | 1080 | 24002 | 0 | 0
140 | Gas Labor | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 16 | 0 | 416 | 0 | 416 | 24004 | 0 | 0
140 | Gas Labor | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 2 | 0 | 80 | 0 | 80 | 24077 | 0 | 0
140 | Gas Labor | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24140 | 0 | 0
140 | Gas Labor | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 3 | 0 | 120 | 0 | 120 | 24153 | 0 | 0
140 | Gas Labor | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 2 | 0 | 50 | 0 | 50 | 24270 | 0 | 0
140 | Gas Labor | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24344 | 0 | 0
140 | Gas Labor | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 24595 | 0 | 0
140 | Gas Labor | PR | 658 | 07/24/19 | 07/26/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 160 | 0 | 160 | 24607 | 0 | 0
140 | Gas Labor | PR | 303 | 08/07/19 | 08/09/19 | PA11 | Paco Leyva, Orlando | 7 | 0 | 280 | 0 | 280 | 24756 | 0 | 0
140 | Gas Labor | PR | 305 | 08/07/19 | 08/09/19 | RA55 | Ramos Herrera, Franklin J | 7 | 0 | 182 | 0 | 182 | 24758 | 0 | 0
140 | Gas Labor | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 24817 | 0 | 0
140 | Gas Labor | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 1 | 0 | 40 | 0 | 40 | 24829 | 0 | 0
140 | Gas Labor | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 1 | 0 | 26 | 0 | 26 | 24831 | 0 | 0
140 | Gas Labor | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 2 | 0 | 70 | 0 | 70 | 24841 | 0 | 0
140 | Gas Labor | PR | 47 | 09/04/19 | 09/06/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 25045 | 0 | 0
140 | Gas Labor | PR | 71 | 09/04/19 | 09/06/19 | SE64 | Sepulveda Gonzalez, Alfredo | 3 | 0 | 105 | 0 | 105 | 25069 | 0 | 0
141 | Water Main/Insulation Lab | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 4 | 0 | 188 | 0 | 188 | 20843 | 0 | 0
141 | Water Main/Insulation Lab | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 3.5 | 0 | 115.5 | 115.5 | 21251 | 0 | 0
141 | Water Main/Insulation Lab | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 3.5 | 0 | 126 | 126 | 21289 | 0 | 0
141 | Water Main/Insulation Lab | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 0 | 3.5 | 0 | 120.75 | 120.75 | 21337 | 0 | 0
141 | Water Main/Insulation Lab | PR | 247 | 10/10/18 | 10/12/18 | CR19 | Crespin Portillo, Juan D | 24 | 0 | 384 | 0 | 384 | 21405 | 0 | 0
141 | Water Main/Insulation Lab | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 16.5 | 0 | 429 | 0 | 429 | 21650 | 0 | 0
141 | Water Main/Insulation Lab | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 4 | 0 | 168 | 168 | 21689 | 0 | 0
141 | Water Main/Insulation Lab | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 26 | 0 | 728 | 0 | 728 | 21689 | 0 | 0
141 | Water Main/Insulation Lab | PR | 195 | 11/07/18 | 11/09/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21699 | 0 | 0
141 | Water Main/Insulation Lab | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 216 | 216 | 21706 | 0 | 0
141 | Water Main/Insulation Lab | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21706 | 0 | 0
141 | Water Main/Insulation Lab | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 1 | 0 | 28.5 | 28.5 | 21708 | 0 | 0
141 | Water Main/Insulation Lab | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 16 | 0 | 304 | 0 | 304 | 21708 | 0 | 0
141 | Water Main/Insulation Lab | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 34 | 0 | 884 | 0 | 884 | 21722 | 0 | 0
141 | Water Main/Insulation Lab | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 384 | 384 | 21724 | 0 | 0
141 | Water Main/Insulation Lab | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21724 | 0 | 0
141 | Water Main/Insulation Lab | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 4 | 0 | 144 | 144 | 21731 | 0 | 0
141 | Water Main/Insulation Lab | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 2 | 0 | 54 | 54 | 21734 | 0 | 0
141 | Water Main/Insulation Lab | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 8 | 0 | 144 | 0 | 144 | 21734 | 0 | 0
141 | Water Main/Insulation Lab | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 2 | 0 | 81 | 81 | 21759 | 0 | 0
141 | Water Main/Insulation Lab | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 2 | 0 | 54 | 0 | 54 | 21759 | 0 | 0
141 | Water Main/Insulation Lab | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 2 | 0 | 84 | 84 | 21762 | 0 | 0
141 | Water Main/Insulation Lab | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 16 | 0 | 448 | 0 | 448 | 21762 | 0 | 0
141 | Water Main/Insulation Lab | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 2 | 0 | 54 | 54 | 21768 | 0 | 0
141 | Water Main/Insulation Lab | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 3 | 0 | 54 | 0 | 54 | 21768 | 0 | 0
141 | Water Main/Insulation Lab | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 240 | 240 | 21773 | 0 | 0
141 | Water Main/Insulation Lab | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21773 | 0 | 0
141 | Water Main/Insulation Lab | PR | 451 | 11/14/18 | 11/16/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 720 | 0 | 720 | 21779 | 0 | 0
141 | Water Main/Insulation Lab | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 2 | 0 | 57 | 57 | 21781 | 0 | 0
141 | Water Main/Insulation Lab | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 8 | 0 | 152 | 0 | 152 | 21781 | 0 | 0
141 | Water Main/Insulation Lab | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 0 | 8 | 0 | 384 | 384 | 21797 | 0 | 0
141 | Water Main/Insulation Lab | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 40 | 0 | 1280 | 0 | 1280 | 21797 | 0 | 0
141 | Water Main/Insulation Lab | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 4 | 0 | 108 | 108 | 21807 | 0 | 0
141 | Water Main/Insulation Lab | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 9 | 0 | 162 | 0 | 162 | 21807 | 0 | 0
141 | Water Main/Insulation Lab | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 4 | 0 | 120 | 120 | 21851 | 0 | 0
141 | Water Main/Insulation Lab | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 800 | 0 | 800 | 21851 | 0 | 0
141 | Water Main/Insulation Lab | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 6 | 0 | 162 | 162 | 21857 | 0 | 0
141 | Water Main/Insulation Lab | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 22 | 0 | 396 | 0 | 396 | 21857 | 0 | 0
141 | Water Main/Insulation Lab | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 6 | 0 | 180 | 180 | 21872 | 0 | 0
141 | Water Main/Insulation Lab | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 2 | 0 | 40 | 0 | 40 | 21872 | 0 | 0
141 | Water Main/Insulation Lab | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 38 | 0 | 1216 | 0 | 1216 | 21875 | 0 | 0
141 | Water Main/Insulation Lab | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 6 | 0 | 162 | 162 | 21884 | 0 | 0
141 | Water Main/Insulation Lab | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 12 | 0 | 216 | 0 | 216 | 21884 | 0 | 0
141 | Water Main/Insulation Lab | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 25 | 0 | 550 | 0 | 550 | 21925 | 0 | 0
141 | Water Main/Insulation Lab | PR | 849 | 11/28/18 | 11/30/18 | ES09 | Escalante Escobar, Boanerge | 38 | 0 | 760 | 0 | 760 | 21931 | 0 | 0
141 | Water Main/Insulation Lab | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 28 | 0 | 924 | 0 | 924 | 21949 | 0 | 0
141 | Water Main/Insulation Lab | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 6 | 0 | 198 | 198 | 21998 | 0 | 0
141 | Water Main/Insulation Lab | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 880 | 0 | 880 | 21998 | 0 | 0
141 | Water Main/Insulation Lab | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 240 | 240 | 22004 | 0 | 0
141 | Water Main/Insulation Lab | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 22004 | 0 | 0
141 | Water Main/Insulation Lab | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22018 | 0 | 0
141 | Water Main/Insulation Lab | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 4 | 0 | 198 | 198 | 22021 | 0 | 0
141 | Water Main/Insulation Lab | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 32 | 0 | 1056 | 0 | 1056 | 22021 | 0 | 0
141 | Water Main/Insulation Lab | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 10 | 0 | 240 | 0 | 240 | 22132 | 0 | 0
141 | Water Main/Insulation Lab | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 18 | 0 | 396 | 0 | 396 | 22139 | 0 | 0
141 | Water Main/Insulation Lab | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 240 | 240 | 22145 | 0 | 0
141 | Water Main/Insulation Lab | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 22145 | 0 | 0
141 | Water Main/Insulation Lab | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 2 | 0 | 66 | 66 | 22159 | 0 | 0
141 | Water Main/Insulation Lab | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22159 | 0 | 0
141 | Water Main/Insulation Lab | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 4 | 0 | 198 | 198 | 22162 | 0 | 0
141 | Water Main/Insulation Lab | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22162 | 0 | 0
141 | Water Main/Insulation Lab | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 3 | 0 | 111 | 0 | 111 | 22171 | 0 | 0
141 | Water Main/Insulation Lab | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 3 | 0 | 87 | 0 | 87 | 22197 | 0 | 0
141 | Water Main/Insulation Lab | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 66 | 66 | 22211 | 0 | 0
141 | Water Main/Insulation Lab | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 38 | 0 | 836 | 0 | 836 | 22211 | 0 | 0
141 | Water Main/Insulation Lab | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 2 | 0 | 60 | 60 | 22217 | 0 | 0
141 | Water Main/Insulation Lab | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 46 | 0 | 920 | 0 | 920 | 22217 | 0 | 0
141 | Water Main/Insulation Lab | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 2 | 0 | 66 | 66 | 22231 | 0 | 0
141 | Water Main/Insulation Lab | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22231 | 0 | 0
141 | Water Main/Insulation Lab | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 4 | 0 | 198 | 198 | 22234 | 0 | 0
141 | Water Main/Insulation Lab | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 24 | 0 | 792 | 0 | 792 | 22234 | 0 | 0
141 | Water Main/Insulation Lab | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 4 | 0 | 138 | 138 | 22245 | 0 | 0
141 | Water Main/Insulation Lab | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 16 | 0 | 368 | 0 | 368 | 22245 | 0 | 0
141 | Water Main/Insulation Lab | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 18 | 0 | 360 | 0 | 360 | 22290 | 0 | 0
141 | Water Main/Insulation Lab | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22308 | 0 | 0
141 | Water Main/Insulation Lab | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 8 | 0 | 296 | 0 | 296 | 22316 | 0 | 0
141 | Water Main/Insulation Lab | PR | 16 | 01/02/19 | 01/04/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 528 | 0 | 528 | 22356 | 0 | 0
141 | Water Main/Insulation Lab | PR | 22 | 01/02/19 | 01/04/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 480 | 0 | 480 | 22363 | 0 | 0
141 | Water Main/Insulation Lab | PR | 38 | 01/02/19 | 01/04/19 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22379 | 0 | 0
141 | Water Main/Insulation Lab | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 232 | 0 | 232 | 22412 | 0 | 0
141 | Water Main/Insulation Lab | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 528 | 0 | 528 | 22426 | 0 | 0
141 | Water Main/Insulation Lab | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 480 | 0 | 480 | 22432 | 0 | 0
141 | Water Main/Insulation Lab | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 184 | 0 | 184 | 22461 | 0 | 0
141 | Water Main/Insulation Lab | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 8 | 0 | 264 | 264 | 22500 | 0 | 0
141 | Water Main/Insulation Lab | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 528 | 0 | 528 | 22500 | 0 | 0
141 | Water Main/Insulation Lab | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 0 | 8 | 0 | 240 | 240 | 22506 | 0 | 0
141 | Water Main/Insulation Lab | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 22506 | 0 | 0
141 | Water Main/Insulation Lab | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 7 | 0 | 259 | 0 | 259 | 22532 | 0 | 0
141 | Water Main/Insulation Lab | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 704 | 0 | 704 | 22573 | 0 | 0
141 | Water Main/Insulation Lab | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 32 | 0 | 640 | 0 | 640 | 22579 | 0 | 0
141 | Water Main/Insulation Lab | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 2 | 0 | 46 | 0 | 46 | 22591 | 0 | 0
141 | Water Main/Insulation Lab | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 148 | 0 | 148 | 22605 | 0 | 0
141 | Water Main/Insulation Lab | PR | 16 | 01/30/19 | 02/01/19 | CR77 | Cruz Gonzalez, Julio C | 40 | 0 | 880 | 0 | 880 | 22645 | 0 | 0
141 | Water Main/Insulation Lab | PR | 22 | 01/30/19 | 02/01/19 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 22651 | 0 | 0
141 | Water Main/Insulation Lab | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22666 | 0 | 0
141 | Water Main/Insulation Lab | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 5 | 0 | 165 | 0 | 165 | 22669 | 0 | 0
141 | Water Main/Insulation Lab | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 148 | 0 | 148 | 22676 | 0 | 0
141 | Water Main/Insulation Lab | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 26 | 0 | 572 | 0 | 572 | 22713 | 0 | 0
141 | Water Main/Insulation Lab | PR | 177 | 02/06/19 | 02/08/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 320 | 0 | 320 | 22719 | 0 | 0
141 | Water Main/Insulation Lab | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 22734 | 0 | 0
141 | Water Main/Insulation Lab | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 20 | 0 | 440 | 0 | 440 | 22782 | 0 | 0
141 | Water Main/Insulation Lab | PR | 591 | 02/20/19 | 02/22/19 | CR77 | Cruz Gonzalez, Julio C | 48 | 0 | 1056 | 0 | 1056 | 22853 | 0 | 0
141 | Water Main/Insulation Lab | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 13 | 0 | 481 | 0 | 481 | 22957 | 0 | 0
141 | Water Main/Insulation Lab | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 5 | 0 | 185 | 0 | 185 | 23029 | 0 | 0
141 | Water Main/Insulation Lab | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 2 | 0 | 87 | 87 | 23053 | 0 | 0
141 | Water Main/Insulation Lab | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 232 | 0 | 232 | 23053 | 0 | 0
141 | Water Main/Insulation Lab | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 66 | 66 | 23067 | 0 | 0
141 | Water Main/Insulation Lab | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 20 | 0 | 440 | 0 | 440 | 23067 | 0 | 0
141 | Water Main/Insulation Lab | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 29 | 0 | 725 | 0 | 725 | 23068 | 0 | 0
141 | Water Main/Insulation Lab | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 2 | 0 | 60 | 60 | 23074 | 0 | 0
141 | Water Main/Insulation Lab | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 20 | 0 | 400 | 0 | 400 | 23074 | 0 | 0
141 | Water Main/Insulation Lab | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 15 | 0 | 555 | 0 | 555 | 23099 | 0 | 0
141 | Water Main/Insulation Lab | PR | 719 | 03/20/19 | 03/22/19 | CR77 | Cruz Gonzalez, Julio C | 38 | 0 | 836 | 0 | 836 | 23140 | 0 | 0
141 | Water Main/Insulation Lab | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 40 | 0 | 800 | 0 | 800 | 23147 | 0 | 0
141 | Water Main/Insulation Lab | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 2 | 0 | 66 | 66 | 23214 | 0 | 0
141 | Water Main/Insulation Lab | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 38 | 0 | 836 | 0 | 836 | 23214 | 0 | 0
141 | Water Main/Insulation Lab | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 8 | 0 | 160 | 0 | 160 | 23221 | 0 | 0
141 | Water Main/Insulation Lab | PR | 939 | 03/27/19 | 03/29/19 | FR04 | Frausto Mendoza, Pedro | 5 | 0 | 105 | 0 | 105 | 23223 | 0 | 0
141 | Water Main/Insulation Lab | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 8 | 0 | 176 | 0 | 176 | 23236 | 0 | 0
141 | Water Main/Insulation Lab | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 12 | 0 | 444 | 0 | 444 | 23246 | 0 | 0
141 | Water Main/Insulation Lab | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 16 | 0 | 464 | 0 | 464 | 23272 | 0 | 0
141 | Water Main/Insulation Lab | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 176 | 0 | 176 | 23286 | 0 | 0
141 | Water Main/Insulation Lab | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 320 | 0 | 320 | 23293 | 0 | 0
141 | Water Main/Insulation Lab | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 4 | 0 | 148 | 0 | 148 | 23319 | 0 | 0
141 | Water Main/Insulation Lab | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 16 | 0 | 352 | 0 | 352 | 23360 | 0 | 0
141 | Water Main/Insulation Lab | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 480 | 0 | 480 | 23367 | 0 | 0
141 | Water Main/Insulation Lab | PR | 369 | 04/10/19 | 04/12/19 | PA11 | Paco Leyva, Orlando | 0 | 8 | 0 | 480 | 480 | 23393 | 0 | 0
141 | Water Main/Insulation Lab | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 32 | 0 | 704 | 0 | 704 | 23434 | 0 | 0
141 | Water Main/Insulation Lab | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 480 | 0 | 480 | 23441 | 0 | 0
141 | Water Main/Insulation Lab | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 4 | 0 | 128 | 0 | 128 | 23496 | 0 | 0
141 | Water Main/Insulation Lab | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 16 | 0 | 352 | 0 | 352 | 23516 | 0 | 0
141 | Water Main/Insulation Lab | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23531 | 0 | 0
141 | Water Main/Insulation Lab | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 21 | 0 | 672 | 0 | 672 | 23568 | 0 | 0
141 | Water Main/Insulation Lab | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 528 | 0 | 528 | 23589 | 0 | 0
141 | Water Main/Insulation Lab | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23643 | 0 | 0
141 | Water Main/Insulation Lab | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 24 | 0 | 528 | 0 | 528 | 23664 | 0 | 0
141 | Water Main/Insulation Lab | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 23798 | 0 | 0
141 | Water Main/Insulation Lab | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23990 | 0 | 0
141 | Water Main/Insulation Lab | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 8 | 0 | 200 | 0 | 200 | 24044 | 0 | 0
141 | Water Main/Insulation Lab | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 3 | 0 | 120 | 0 | 120 | 24077 | 0 | 0
141 | Water Main/Insulation Lab | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 22 | 0 | 550 | 0 | 550 | 24195 | 0 | 0
141 | Water Main/Insulation Lab | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 4 | 0 | 124 | 0 | 124 | 24218 | 0 | 0
141 | Water Main/Insulation Lab | PR | 7 | 07/03/19 | 07/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 8 | 0 | 256 | 0 | 256 | 24254 | 0 | 0
141 | Water Main/Insulation Lab | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 24 | 0 | 600 | 0 | 600 | 24270 | 0 | 0
141 | Water Main/Insulation Lab | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 3 | 0 | 120 | 0 | 120 | 24304 | 0 | 0
141 | Water Main/Insulation Lab | PR | 58 | 07/03/19 | 07/05/19 | RA55 | Ramos Herrera, Franklin J | 8 | 0 | 208 | 0 | 208 | 24306 | 0 | 0
141 | Water Main/Insulation Lab | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 6 | 0 | 150 | 0 | 150 | 24344 | 0 | 0
141 | Water Main/Insulation Lab | PR | 313 | 07/10/19 | 07/12/19 | HU06 | Hubbard, Robert W | 6 | 0 | 300 | 0 | 300 | 24365 | 0 | 0
141 | Water Main/Insulation Lab | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 8 | 0 | 248 | 0 | 248 | 24367 | 0 | 0
142 | Mech Room Labor | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 1 | 0 | 47 | 0 | 47 | 21501 | 0 | 0
142 | Mech Room Labor | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 1 | 0 | 28.5 | 28.5 | 21623 | 0 | 0
142 | Mech Room Labor | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 1 | 0 | 19 | 0 | 19 | 21623 | 0 | 0
142 | Mech Room Labor | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 7 | 0 | 231 | 0 | 231 | 22741 | 0 | 0
142 | Mech Room Labor | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 256 | 0 | 256 | 22756 | 0 | 0
142 | Mech Room Labor | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 22804 | 0 | 0
142 | Mech Room Labor | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 7.75 | 0 | 255.75 | 0 | 255.75 | 22881 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 3.5 | 0 | 257.25 | 257.25 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 9 | 0 | 441 | 0 | 441 | 22945 | 0 | 0
142 | Mech Room Labor | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 38 | 0 | 1254 | 0 | 1254 | 22953 | 0 | 0
142 | Mech Room Labor | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 11.5 | 0 | 563.5 | 0 | 563.5 | 23017 | 0 | 0
142 | Mech Room Labor | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 6 | 0 | 441 | 441 | 23017 | 0 | 0
142 | Mech Room Labor | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 0 | 4.25 | 0 | 210.38 | 210.38 | 23025 | 0 | 0
142 | Mech Room Labor | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 41.75 | 0 | 1377.75 | 0 | 1377.75 | 23025 | 0 | 0
142 | Mech Room Labor | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 1 | 0 | 48 | 48 | 23040 | 0 | 0
142 | Mech Room Labor | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 5 | 0 | 160 | 0 | 160 | 23040 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 2 | 0 | 98 | 0 | 98 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 3.5 | 0 | 257.25 | 257.25 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 8 | 0 | 396 | 396 | 23095 | 0 | 0
142 | Mech Room Labor | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 36 | 0 | 1188 | 0 | 1188 | 23095 | 0 | 0
142 | Mech Room Labor | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 8 | 0 | 384 | 384 | 23111 | 0 | 0
142 | Mech Room Labor | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1280 | 0 | 1280 | 23111 | 0 | 0
142 | Mech Room Labor | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 747 | 03/20/19 | 03/22/19 | MC09 | McCabe, Thomas C | 8 | 0 | 264 | 0 | 264 | 23168 | 0 | 0
142 | Mech Room Labor | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 31 | 0 | 992 | 0 | 992 | 23183 | 0 | 0
142 | Mech Room Labor | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23197 | 0 | 0
142 | Mech Room Labor | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23197 | 0 | 0
142 | Mech Room Labor | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | -73.5 | -73.5 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 4 | 0 | -196 | 0 | -196 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 73.5 | 73.5 | 23235 | 0 | 0
142 | Mech Room Labor | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 14 | 0 | 448 | 0 | 448 | 23258 | 0 | 0
142 | Mech Room Labor | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 4 | 0 | 196 | 0 | 196 | 23308 | 0 | 0
142 | Mech Room Labor | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 3 | 0 | 225 | 225 | 23381 | 0 | 0
142 | Mech Room Labor | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 23381 | 0 | 0
142 | Mech Room Labor | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 23456 | 0 | 0
142 | Mech Room Labor | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 1 | 0 | 75 | 75 | 23456 | 0 | 0
142 | Mech Room Labor | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 5 | 0 | 160 | 0 | 160 | 23481 | 0 | 0
142 | Mech Room Labor | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23531 | 0 | 0
142 | Mech Room Labor | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23604 | 0 | 0
142 | Mech Room Labor | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 10 | 0 | 500 | 0 | 500 | 23758 | 0 | 0
142 | Mech Room Labor | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 8 | 0 | 280 | 0 | 280 | 23783 | 0 | 0
142 | Mech Room Labor | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 8 | 0 | 320 | 0 | 320 | 23847 | 0 | 0
142 | Mech Room Labor | GL | 886 | 08/12/19 | 08/12/19 | Tommy | M SAW Reimb |  |  |  |  | -2755.68 |  | 0 | 0
142 | Mech Room Labor | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24817 | 0 | 0
143 | Condensation Drains Labor | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 4 | 0 | 136 | 0 | 136 | 19914 | 0 | 0
143 | Condensation Drains Labor | PR | 134 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 4 | 0 | -136 | 0 | -136 | 920011 | 0 | 0
143 | Condensation Drains Labor | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 8 | 0 | 264 | 0 | 264 | 22669 | 0 | 0
143 | Condensation Drains Labor | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 4 | 0 | 174 | 174 | 23198 | 0 | 0
143 | Condensation Drains Labor | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 4 | 0 | 92 | 0 | 92 | 23248 | 0 | 0
150 | Warranty Labor | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 25348 | 0 | 0
210 | Underground Material | GL | 609 | 04/27/18 | 05/22/18 | Mat | Req 4384 |  |  |  |  | 1597.8 |  | 0 | 0
210 | Underground Material | AP | 456 | 06/05/18 | 06/14/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 380 | 4252833-00 | 0 | 0
210 | Underground Material | AP | 890 | 06/11/18 | 06/26/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 93.2 | 4253140-00 | 0 | 0
210 | Underground Material | AP | 892 | 06/14/18 | 06/26/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 162.11 | 4253359-00 | 0 | 0
210 | Underground Material | GL | 405 | 07/16/18 | 07/16/18 | Mat | Req 5271 |  |  |  |  | 103 |  | 0 | 0
210 | Underground Material | AP | 561 | 06/29/18 | 07/20/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 688.2 | 4253937-00 | 0 | 0
210 | Underground Material | AP | 602 | 07/02/18 | 07/23/18 | 1021AT | ACME Corp |  |  |  |  | 59.75 | S3034425.001 | 0 | 0
210 | Underground Material | AP | 102 | 07/09/19 | 08/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 549.4 | S009339008.001 | 0 | 0
211 | Garage Material | GL | 557 | 06/15/18 | 06/15/18 | Mat | Req 3705 |  |  |  |  | 221.6 |  | 0 | 0
211 | Garage Material | AP | 891 | 06/14/18 | 06/26/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 785.47 | 4253253-00 | 0 | 0
211 | Garage Material | GL | 906 | 06/27/18 | 06/27/18 | Mat | Req 3740 |  |  |  |  | 317.34 |  | 0 | 0
211 | Garage Material | AP | 381 | 06/25/18 | 07/13/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 883.15 | 4253691-00 | 0 | 0
211 | Garage Material | GL | 696 | 07/25/18 | 07/25/18 | Mat | Req 4501 |  |  |  |  | 54 |  | 0 | 0
211 | Garage Material | GL | 195 | 09/10/18 | 09/10/18 | Mat | Req 4678 |  |  |  |  | 206.5 |  | 0 | 0
211 | Garage Material | GL | 596 | 09/25/18 | 09/25/18 | Mat | Req 5401 |  |  |  |  | 154 |  | 0 | 0
211 | Garage Material | GL | 558 | 10/22/18 | 10/22/18 | Mat | Req 4737 |  |  |  |  | 444 |  | 0 | 0
211 | Garage Material | GL | 778 | 11/26/18 | 11/26/18 | Mat | Req 4846 |  |  |  |  | 65 |  | 0 | 0
211 | Garage Material | GL | 174 | 12/06/18 | 12/06/18 | CK#5635 | Orlando Paco Leyva |  |  |  |  | 28.5 |  | 0 | 0
211 | Garage Material | GL | 313 | 01/11/19 | 01/11/19 | Mat | Req 4879 |  |  |  |  | 20.18 |  | 0 | 0
211 | Garage Material | AP | 447 | 01/03/19 | 01/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 29.79 | 6840313 | 0 | 0
211 | Garage Material | GL | 883 | 01/30/19 | 01/30/19 | Mat | Req 4992 |  |  |  |  | 34.1 |  | 0 | 0
211 | Garage Material | GL | 590 | 03/15/19 | 03/15/19 | Mat | Req 5817 |  |  |  |  | 117.4 |  | 0 | 0
211 | Garage Material | AP | 647 | 02/28/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 144.76 | 4263840-00 | 0 | 0
211 | Garage Material | GL | 1062 | 03/28/19 | 03/28/19 | Mat | Req 5855 |  |  |  |  | -316.18 |  | 0 | 0
211 | Garage Material | GL | 1066 | 03/28/19 | 03/28/19 | Mat | Req 5851 |  |  |  |  | -139.2 |  | 0 | 0
211 | Garage Material | GL | 208 | 04/08/19 | 04/08/19 | Mat | Req 5882 |  |  |  |  | 14.3 |  | 0 | 0
211 | Garage Material | GL | 806 | 06/26/19 | 06/26/19 | Mat | Req 6048 |  |  |  |  | 120.4 |  | 0 | 0
211 | Garage Material | GL | 137 | 07/09/19 | 07/09/19 | Mat | Req 6101 |  |  |  |  | 106.07 |  | 0 | 0
211 | Garage Material | AP | 487 | 07/03/19 | 07/17/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 479.44 | 4269719-00 | 0 | 0
211 | Garage Material | AP | 439 | 07/18/19 | 08/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 28.62 | 4269719-01 | 0 | 0
212 | Canout Material | GL | 404 | 07/16/18 | 07/16/18 | Mat | Req 5270 |  |  |  |  | 74.33 |  | 0 | 0
220 | Roughin Material | AP | 928 | 06/19/18 | 06/27/18 | 2049RS | Rosen Supply Company, Inc. $Reserve |  |  |  |  | 86.84 | 4253482-00 | 0 | 0
220 | Roughin Material | GL | 695 | 07/25/18 | 07/25/18 | Mat | Req 4502 |  |  |  |  | 92.25 |  | 0 | 0
220 | Roughin Material | AP | 760 | 07/24/18 | 07/26/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 15201.73 | S8684278.001 | 0 | 0
220 | Roughin Material | GL | 333 | 08/10/18 | 08/10/18 | Mat | Req 4579 |  |  |  |  | 481.04 |  | 0 | 0
220 | Roughin Material | GL | 377 | 08/10/18 | 08/10/18 | Mat | Req 4529 |  |  |  |  | 731.95 |  | 0 | 0
220 | Roughin Material | AP | 409 | 07/06/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5006.3 | 4248188-00 | 0 | 0
220 | Roughin Material | AP | 424 | 07/12/18 | 08/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 216.63 | 4254370-00 | 0 | 0
220 | Roughin Material | AP | 435 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 142.92 | 4254370-01 | 0 | 0
220 | Roughin Material | AP | 440 | 07/17/18 | 08/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 106.9 | 4254670-00 | 0 | 0
220 | Roughin Material | AP | 604 | 07/24/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 5006.3 | 4248190-00 | 0 | 0
220 | Roughin Material | AP | 607 | 07/24/18 | 08/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 409.06 | 4254934-00 | 0 | 0
220 | Roughin Material | GL | 665 | 08/22/18 | 08/22/18 | Mat | Req 4632 |  |  |  |  | 1286.93 |  | 0 | 0
220 | Roughin Material | AP | 717 | 07/27/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 88.44 | 4255199-00 | 0 | 0
220 | Roughin Material | AP | 718 | 07/30/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6.79 | 4254934-01 | 0 | 0
220 | Roughin Material | AP | 719 | 07/31/18 | 08/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 76.76 | 4255297-00 | 0 | 0
220 | Roughin Material | AP | 731 | 08/01/18 | 08/22/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 13609 | S8684227.001 | 0 | 0
220 | Roughin Material | AP | 932 | 08/01/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 308.7 | 4255362-00 | 0 | 0
220 | Roughin Material | AP | 933 | 08/02/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 254 | 4255358-00 | 0 | 0
220 | Roughin Material | AP | 934 | 08/03/18 | 08/28/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 175.89 | 4255452-00 | 0 | 0
220 | Roughin Material | AP | 993 | 08/07/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 451 | 4255540-00 | 0 | 0
220 | Roughin Material | AP | 994 | 08/09/18 | 08/29/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 126.18 | 4255750-00 | 0 | 0
220 | Roughin Material | AP | 8 | 08/13/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 210.83 | 7138752-00 | 0 | 0
220 | Roughin Material | AP | 21 | 08/10/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1761.2 | 4255771-00 | 0 | 0
220 | Roughin Material | AP | 22 | 08/14/18 | 09/04/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 56.7 | 4255939-00 | 0 | 0
220 | Roughin Material | GL | 196 | 09/10/18 | 09/10/18 | Mat | Req 4677 |  |  |  |  | 1424.42 |  | 0 | 0
220 | Roughin Material | AP | 201 | 08/16/18 | 09/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 235.1 | 4256056-00 | 0 | 0
220 | Roughin Material | AP | 381 | 08/22/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1020.7 | 4256324-00 | 0 | 0
220 | Roughin Material | AP | 382 | 08/23/18 | 09/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 375 | 4256371-00 | 0 | 0
220 | Roughin Material | AP | 435 | 08/31/18 | 09/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 276.8 | 4256324-01 | 0 | 0
220 | Roughin Material | GL | 458 | 09/19/18 | 09/19/18 | Mat | Req 5348 |  |  |  |  | 162.8 |  | 0 | 0
220 | Roughin Material | GL | 459 | 09/19/18 | 09/19/18 | Mat | Req 5347 |  |  |  |  | 8.9 |  | 0 | 0
220 | Roughin Material | GL | 567 | 09/20/18 | 09/20/18 | CK#5574 | Orlando Paco Leyva |  |  |  |  | 28.64 |  | 0 | 0
220 | Roughin Material | GL | 598 | 09/25/18 | 09/25/18 | Mat | Req 5399 |  |  |  |  | 2104.99 |  | 0 | 0
220 | Roughin Material | GL | 769 | 09/30/18 | 09/30/18 | Mat | Req 5416 |  |  |  |  | 668.09 |  | 0 | 0
220 | Roughin Material | AP | 865 | 09/05/18 | 09/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 538 | 4256068-00 | 0 | 0
220 | Roughin Material | AP | 866 | 09/05/18 | 09/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 230 | 4256790-00 | 0 | 0
220 | Roughin Material | AP | 109 | 09/06/18 | 10/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 554.34 | 4256868-00 | 0 | 0
220 | Roughin Material | AP | 110 | 09/07/18 | 10/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2089.9 | 4248939-00 | 0 | 0
220 | Roughin Material | AP | 171 | 09/10/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1536.4 | 4256989-00 | 0 | 0
220 | Roughin Material | AP | 172 | 09/12/18 | 10/10/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 159.74 | 4257059-00 | 0 | 0
220 | Roughin Material | GL | 185 | 10/10/18 | 10/10/18 | Mat | Req 5454 |  |  |  |  | 1969.47 |  | 0 | 0
220 | Roughin Material | AP | 430 | 09/17/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 141.76 | 4257327-00 | 0 | 0
220 | Roughin Material | GL | 561 | 10/22/18 | 10/22/18 | Mat | Req 4734 |  |  |  |  | 875.43 |  | 0 | 0
220 | Roughin Material | AP | 596 | 09/25/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 350.7 | 4257731-00 | 0 | 0
220 | Roughin Material | AP | 685 | 09/27/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 367.6 | 4257885-00 | 0 | 0
220 | Roughin Material | AP | 686 | 10/01/18 | 10/24/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 676.75 | 4257993-00 | 0 | 0
220 | Roughin Material | AP | 788 | 09/27/18 | 10/29/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 31.8 | S8949878.001 | 0 | 0
220 | Roughin Material | AP | 789 | 10/03/18 | 10/29/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 840.04 | S8954733.001 | 0 | 0
220 | Roughin Material | AP | 410 | 09/14/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -88.5 | 4257301-00 | 0 | 0
220 | Roughin Material | AP | 411 | 09/17/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 555.42 | 4257297-00 | 0 | 0
220 | Roughin Material | AP | 412 | 09/18/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 281.8 | 4257408-00 | 0 | 0
220 | Roughin Material | AP | 413 | 09/20/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 264.27 | 4257549-00 | 0 | 0
220 | Roughin Material | GL | 883 | 10/31/18 | 10/31/18 | Mat | Req 5499 |  |  |  |  | 1139.38 |  | 0 | 0
220 | Roughin Material | AP | 110 | 10/03/18 | 11/02/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 369.2 | 4258089-00 | 0 | 0
220 | Roughin Material | AP | 135 | 10/05/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2044.08 | 4258189-00 | 0 | 0
220 | Roughin Material | AP | 143 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 12.32 | 4257993-01 | 0 | 0
220 | Roughin Material | AP | 175 | 10/08/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 25.4 | S8954733.002 | 0 | 0
220 | Roughin Material | AP | 176 | 10/09/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 741.15 | S8954733.003 | 0 | 0
220 | Roughin Material | AP | 177 | 10/11/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 247.05 | S8954733.004 | 0 | 0
220 | Roughin Material | AP | 343 | 10/11/18 | 11/09/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 233.8 | 4258510-00 | 0 | 0
220 | Roughin Material | AP | 704 | 10/23/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 505.85 | 4258962-00 | 0 | 0
220 | Roughin Material | AP | 705 | 10/25/18 | 11/21/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 364.3 | 4259078-00 | 0 | 0
220 | Roughin Material | GL | 780 | 11/26/18 | 11/26/18 | Mat | Req 4842 |  |  |  |  | 1798.98 |  | 0 | 0
220 | Roughin Material | GL | 784 | 11/26/18 | 11/26/18 | Mat | Req 4847 |  |  |  |  | 1458.9 |  | 0 | 0
220 | Roughin Material | GL | 802 | 11/07/18 | 11/28/18 | Mat | Req 5536 |  |  |  |  | 627.77 |  | 0 | 0
220 | Roughin Material | GL | 805 | 11/07/18 | 11/28/18 | Mat | Req 5538 |  |  |  |  | 9985.94 |  | 0 | 0
220 | Roughin Material | AP | 910 | 11/08/18 | 11/30/18 | 1021AT | ACME Corp |  |  |  |  | 110.12 | S3142690.001 | 0 | 0
220 | Roughin Material | AP | 945 | 10/29/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1749.11 | S8954733.005 | 0 | 0
220 | Roughin Material | AP | 965 | 10/29/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 78.48 | 4259240-00 | 0 | 0
220 | Roughin Material | AP | 971 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 638.44 | 4259301-00 | 0 | 0
220 | Roughin Material | GL | 974 | 11/30/18 | 11/30/18 | Mat | Req 5567 |  |  |  |  | 99 |  | 0 | 0
220 | Roughin Material | GL | 975 | 11/30/18 | 11/30/18 | Mat | Req 5595 |  |  |  |  | 13940.68 |  | 0 | 0
220 | Roughin Material | GL | 991 | 11/30/18 | 11/30/18 | Mat | Req 5592 |  |  |  |  | 48.57 |  | 0 | 0
220 | Roughin Material | AP | 1035 | 11/02/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 15201.73 | S8684211.001 | 0 | 0
220 | Roughin Material | AP | 384 | 11/06/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 747.31 | 4259558-00 | 0 | 0
220 | Roughin Material | AP | 387 | 11/08/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 62 | 4259739-00 | 0 | 0
220 | Roughin Material | AP | 388 | 11/08/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 147.19 | 4259741-00 | 0 | 0
220 | Roughin Material | AP | 389 | 11/12/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 12.1 | 4259878-00 | 0 | 0
220 | Roughin Material | AP | 422 | 11/08/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 55.15 | 4259673-00 | 0 | 0
220 | Roughin Material | AP | 443 | 11/20/18 | 12/18/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 124.45 | 4260203-00 | 0 | 0
220 | Roughin Material | GL | 633 | 12/21/18 | 12/21/18 | Mat | Req 5601 |  |  |  |  | 2178.1 |  | 0 | 0
220 | Roughin Material | GL | 314 | 01/11/19 | 01/11/19 | Mat | Req 4878 |  |  |  |  | 1818.12 |  | 0 | 0
220 | Roughin Material | GL | 359 | 01/11/19 | 01/11/19 | Mat | Req 4910 |  |  |  |  | 207.9 |  | 0 | 0
220 | Roughin Material | AP | 362 | 11/28/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 621.93 | 4260415-00 | 0 | 0
220 | Roughin Material | AP | 363 | 11/28/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 26.12 | 4260474-00 | 0 | 0
220 | Roughin Material | AP | 404 | 12/05/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1096.62 | 4260708-00 | 0 | 0
220 | Roughin Material | GL | 421 | 01/15/19 | 01/15/19 | Mat | Req 4894 |  |  |  |  | 1012.88 |  | 0 | 0
220 | Roughin Material | AP | 599 | 12/13/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 115.11 | 4261179-00 | 0 | 0
220 | Roughin Material | AP | 638 | 12/20/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1545.52 | 4261457-00 | 0 | 0
220 | Roughin Material | GL | 645 | 01/22/19 | 01/22/19 | Mat | Req 4950 |  |  |  |  | 273 |  | 0 | 0
220 | Roughin Material | AP | 856 | 01/02/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 115.6 | 4261758-00 | 0 | 0
220 | Roughin Material | AP | 857 | 01/04/19 | 01/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 151.2 | 4261864-00 | 0 | 0
220 | Roughin Material | GL | 878 | 01/30/19 | 01/30/19 | Mat | Req 4996 |  |  |  |  | 1101.6 |  | 0 | 0
220 | Roughin Material | GL | 882 | 01/30/19 | 01/30/19 | Mat | Req 4991 |  |  |  |  | 265.18 |  | 0 | 0
220 | Roughin Material | AP | 918 | 01/07/19 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 15201.73 | S8684193.001 | 0 | 0
220 | Roughin Material | AP | 274 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 132.43 | 4261878-00 | 0 | 0
220 | Roughin Material | AP | 275 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 674.67 | 4261950-00 | 0 | 0
220 | Roughin Material | AP | 276 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 202.72 | 4260241-00 | 0 | 0
220 | Roughin Material | AP | 314 | 01/10/19 | 02/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 339.84 | 4262086-00 | 0 | 0
220 | Roughin Material | AP | 473 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 117 | 4262170-00 | 0 | 0
220 | Roughin Material | AP | 485 | 01/15/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 84.22 | 4262278-00 | 0 | 0
220 | Roughin Material | AP | 535 | 01/22/19 | 02/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 170.94 | 4262566-00 | 0 | 0
220 | Roughin Material | AP | 674 | 01/28/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 37.88 | 4262881-00 | 0 | 0
220 | Roughin Material | AP | 709 | 02/07/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 250.43 | 4263281-00 | 0 | 0
220 | Roughin Material | GL | 168 | 03/04/19 | 03/04/19 | Mat | Req 5011 |  |  |  |  | 926.17 |  | 0 | 0
220 | Roughin Material | GL | 347 | 03/08/19 | 03/08/19 | Mat | Req 5056 |  |  |  |  | 1896.51 |  | 0 | 0
220 | Roughin Material | GL | 352 | 03/08/19 | 03/08/19 | Mat | Req 5798 |  |  |  |  | -102 |  | 0 | 0
220 | Roughin Material | AP | 408 | 02/19/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 77.52 | 4263598-00 | 0 | 0
220 | Roughin Material | GL | 591 | 03/15/19 | 03/15/19 | Mat | Req 5815 |  |  |  |  | 715.46 |  | 0 | 0
220 | Roughin Material | GL | 616 | 03/15/19 | 03/15/19 | Mat | Req 5065 |  |  |  |  | -825.73 |  | 0 | 0
220 | Roughin Material | GL | 617 | 03/15/19 | 03/15/19 | Mat | Req 5067 |  |  |  |  | -524.48 |  | 0 | 0
220 | Roughin Material | AP | 660 | 03/05/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 112.22 | 4264178-00 | 0 | 0
220 | Roughin Material | GL | 839 | 03/25/19 | 03/25/19 | Mat | Req 5076 |  |  |  |  | 125.3 |  | 0 | 0
220 | Roughin Material | GL | 844 | 03/25/19 | 03/25/19 | Mat | Req 5834 |  |  |  |  | -7594 |  | 0 | 0
220 | Roughin Material | AP | 867 | 03/05/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 589.66 | S9155464.001 | 0 | 0
220 | Roughin Material | AP | 879 | 03/06/19 | 03/26/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 10.39 | 4264369-00 | 0 | 0
220 | Roughin Material | AP | 888 | 03/14/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 9.4 | 7034387 | 0 | 0
220 | Roughin Material | GL | 1063 | 03/28/19 | 03/28/19 | Mat | Req 5854 |  |  |  |  | -142.5 |  | 0 | 0
220 | Roughin Material | AP | 60 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 50.76 | 4264639-00 | 0 | 0
220 | Roughin Material | AP | 68 | 03/15/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 26.69 | 4264791-00 | 0 | 0
220 | Roughin Material | GL | 209 | 04/08/19 | 04/08/19 | Mat | Req 5880 |  |  |  |  | 106.7 |  | 0 | 0
220 | Roughin Material | GL | 221 | 04/08/19 | 04/08/19 | Mat | Req 5118 |  |  |  |  | 29.63 |  | 0 | 0
220 | Roughin Material | AP | 248 | 03/20/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 119.63 | 4265051-00 | 0 | 0
220 | Roughin Material | GL | 433 | 04/12/19 | 04/12/19 | Mat | Req 5143 |  |  |  |  | 241.66 |  | 0 | 0
220 | Roughin Material | AP | 471 | 03/19/19 | 04/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 10.2 | 4264892-00 | 0 | 0
220 | Roughin Material | AP | 507 | 03/27/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 16.67 | 4265423-00 | 0 | 0
220 | Roughin Material | GL | 621 | 04/22/19 | 04/22/19 | CK#5719 | Orlando Paco Leyva |  |  |  |  | 14.4 |  | 0 | 0
220 | Roughin Material | GL | 703 | 04/24/19 | 04/24/19 | Mat | Req 5919 |  |  |  |  | -312.78 |  | 0 | 0
220 | Roughin Material | GL | 901 | 04/30/19 | 04/30/19 | Mat | Req 5926 |  |  |  |  | 16.38 |  | 0 | 0
220 | Roughin Material | GL | 124 | 05/02/19 | 05/02/19 | CK#5736 | Orlando Paco Leyva |  |  |  |  | 31.12 |  | 0 | 0
220 | Roughin Material | AP | 136 | 04/11/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 54.44 | 4266081-00 | 0 | 0
220 | Roughin Material | AP | 361 | 04/24/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 34.93 | 4266296-01 | 0 | 0
220 | Roughin Material | GL | 814 | 05/30/19 | 05/30/19 | Mat | Req 5971 |  |  |  |  | 143.65 |  | 0 | 0
220 | Roughin Material | AP | 966 | 05/09/19 | 05/31/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 80.52 | 4267294-00 | 0 | 0
220 | Roughin Material | GL | 106 | 06/05/19 | 06/05/19 | Mat | Req 5253 |  |  |  |  | 35.69 |  | 0 | 0
220 | Roughin Material | GL | 832 | 06/26/19 | 06/26/19 | Mat | Req 6051 |  |  |  |  | 279.94 |  | 0 | 0
220 | Roughin Material | AP | 200 | 07/17/19 | 08/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 130.06 | 4270214-00 | 0 | 0
220 | Roughin Material | GL | 252 | 08/08/19 | 08/08/19 | Mat | Req 6202 |  |  |  |  | 71.13 |  | 0 | 0
220 | Roughin Material | GL | 343 | 09/16/19 | 09/16/19 | Mat | Req 6364 |  |  |  |  | -333.38 |  | 0 | 0
220 | Roughin Material | GL | 374 | 09/16/19 | 09/16/19 | Mat | Req 6344 |  |  |  |  | 133.42 |  | 0 | 0
220 | Roughin Material | GL | 438 | 10/16/19 | 10/16/19 | Mat | Req 6416 |  |  |  |  | 20.37 |  | 0 | 0
220 | Roughin Material | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | 6.54 |  | 0 | 0
230 | Finish Material | GL | 558 | 06/15/18 | 06/15/18 | Mat | Req 3704 |  |  |  |  | 7585.26 |  | 0 | 0
230 | Finish Material | GL | 332 | 08/10/18 | 08/10/18 | Mat | Req 4580 |  |  |  |  | 769.59 |  | 0 | 0
230 | Finish Material | GL | 378 | 08/10/18 | 08/10/18 | Mat | Req 4528 |  |  |  |  | 436.8 |  | 0 | 0
230 | Finish Material | GL | 194 | 09/10/18 | 09/10/18 | Mat | Req 4679 |  |  |  |  | 1298.15 |  | 0 | 0
230 | Finish Material | AP | 442 | 08/29/18 | 09/19/18 | 1231KS | Keller Supply Company |  |  |  |  | 13502.7 | S011741173.001 | 0 | 0
230 | Finish Material | GL | 770 | 09/30/18 | 09/30/18 | Mat | Req 5417 |  |  |  |  | 284.4 |  | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | GL | 183 | 10/10/18 | 10/10/18 | Mat | Req 5456 |  |  |  |  | 1137.6 |  | 0 | 0
230 | Finish Material | AP | 609 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13515.11 | 4255644-00 | 0 | 0
230 | Finish Material | AP | 610 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8610.38 | 4255644-01 | 0 | 0
230 | Finish Material | AP | 611 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4193.7 | 4255649-00 | 0 | 0
230 | Finish Material | GL | 873 | 10/31/18 | 10/31/18 | Mat | Req 4738 |  |  |  |  | 440.22 |  | 0 | 0
230 | Finish Material | GL | 881 | 10/31/18 | 10/31/18 | Mat | Req 5501 |  |  |  |  | 1753.36 |  | 0 | 0
230 | Finish Material | AP | 111 | 10/04/18 | 11/02/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 10844.68 | 4255645-00 | 0 | 0
230 | Finish Material | AP | 137 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2234.29 | 4255644-02 | 0 | 0
230 | Finish Material | AP | 138 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13515.11 | 4255645-01 | 0 | 0
230 | Finish Material | AP | 139 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13166.07 | 4255646-00 | 0 | 0
230 | Finish Material | AP | 140 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 350.1 | 4255646-01 | 0 | 0
230 | Finish Material | AP | 141 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 985.64 | 4255646-02 | 0 | 0
230 | Finish Material | AP | 142 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1396.16 | 4255646-03 | 0 | 0
230 | Finish Material | AP | 367 | 10/10/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1765.7 | 6596862 | 0 | 0
230 | Finish Material | AP | 368 | 10/20/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 64.32 | 6644389 | 0 | 0
230 | Finish Material | AP | 417 | 10/16/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 9448.52 | 4255646-04 | 0 | 0
230 | Finish Material | AP | 606 | 10/23/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -252 | 4259031-00 | 0 | 0
230 | Finish Material | GL | 775 | 11/26/18 | 11/26/18 | Mat | Req 4841 |  |  |  |  | 3882.4 |  | 0 | 0
230 | Finish Material | GL | 804 | 11/07/18 | 11/28/18 | Mat | Req 5539 |  |  |  |  | 15645.9 |  | 0 | 0
230 | Finish Material | AP | 928 | 11/14/18 | 11/30/18 | 2132MH | Manor Hardware & Construction Supply |  |  |  |  | 305.76 | 930587-00 | 0 | 0
230 | Finish Material | AP | 966 | 10/30/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 15784.49 | 4255642-00 | 0 | 0
230 | Finish Material | AP | 968 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6958.54 | 4255642-01 | 0 | 0
230 | Finish Material | AP | 969 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 9099.48 | 4255648-00 | 0 | 0
230 | Finish Material | AP | 386 | 11/08/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8945.84 | 4255648-01 | 0 | 0
230 | Finish Material | AP | 449 | 11/23/18 | 12/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 349.04 | 4255648-02 | 0 | 0
230 | Finish Material | GL | 635 | 12/21/18 | 12/21/18 | Mat | Req 5602 |  |  |  |  | 493.92 |  | 0 | 0
230 | Finish Material | AP | 667 | 11/28/18 | 12/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -64.32 | CM705851 | 0 | 0
230 | Finish Material | AP | 682 | 11/29/18 | 12/21/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 548.88 | 6762899 | 0 | 0
230 | Finish Material | AP | 864 | 12/05/18 | 12/31/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 257.04 | 6762899-1 | 0 | 0
230 | Finish Material | AP | 132 | 12/07/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 384.68 | 6762899-2 | 0 | 0
230 | Finish Material | AP | 159 | 12/28/18 | 01/08/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 49135 | 699714 | 0 | 0
230 | Finish Material | GL | 315 | 01/11/19 | 01/11/19 | Mat | Req 4877 |  |  |  |  | 7.64 |  | 0 | 0
230 | Finish Material | GL | 685 | 01/23/19 | 01/23/19 | Mat | Req 4982 |  |  |  |  | 834.84 |  | 0 | 0
230 | Finish Material | AP | 840 | 01/21/19 | 01/29/19 | 5560CH | California Hydronics Corp |  |  |  |  | 1865 | SIN005737 | 0 | 0
230 | Finish Material | AP | 901 | 01/22/19 | 01/30/19 | 2132MH | Manor Hardware & Construction Supply |  |  |  |  | 146.6 | 944498-00 | 0 | 0
230 | Finish Material | AP | 231 | 01/22/19 | 02/01/19 | 2132MH | Manor Hardware & Construction Supply |  |  |  |  | -146.6 | 944498-00A | 0 | 0
230 | Finish Material | AP | 232 | 01/22/19 | 02/01/19 | 2132MH | Manor Hardware & Construction Supply |  |  |  |  | 145.6 | 944498-00B | 0 | 0
230 | Finish Material | AP | 273 | 01/09/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 840 | 4261277-00 | 0 | 0
230 | Finish Material | AP | 544 | 02/01/19 | 02/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 2408.25 | S012516114.001 | 0 | 0
230 | Finish Material | AP | 545 | 02/14/19 | 02/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 2851.7 | S012516114.002 | 0 | 0
230 | Finish Material | AP | 721 | 02/13/19 | 02/26/19 | 5560CH | California Hydronics Corp |  |  |  |  | 1545 | SIN008108 | 0 | 0
230 | Finish Material | GL | 166 | 03/04/19 | 03/04/19 | Mat | Req 5723 |  |  |  |  | 1873.45 |  | 0 | 0
230 | Finish Material | GL | 350 | 03/08/19 | 03/08/19 | Mat | Req 5054 |  |  |  |  | 6323.74 |  | 0 | 0
230 | Finish Material | AP | 394 | 02/21/19 | 03/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 5483.21 | S012517350.001 | 0 | 0
230 | Finish Material | AP | 399 | 02/15/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 602.31 | 4263504-00 | 0 | 0
230 | Finish Material | AP | 407 | 02/18/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 36.9 | 4263561-00 | 0 | 0
230 | Finish Material | AP | 409 | 02/19/19 | 03/11/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 223 | 4263605-00 | 0 | 0
230 | Finish Material | AP | 428 | 02/22/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1049.13 | 4263724-00 | 0 | 0
230 | Finish Material | GL | 589 | 03/15/19 | 03/15/19 | Mat | Req 5816 |  |  |  |  | 2497.45 |  | 0 | 0
230 | Finish Material | GL | 618 | 03/15/19 | 03/15/19 | Mat | Req 5066 |  |  |  |  | 445.76 |  | 0 | 0
230 | Finish Material | AP | 628 | 03/04/19 | 03/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 967.66 | S012652864.001 | 0 | 0
230 | Finish Material | AP | 637 | 03/07/19 | 03/19/19 | 1231KS | Keller Supply Company |  |  |  |  | 5688.89 | S012517590.001 | 0 | 0
230 | Finish Material | AP | 656 | 03/04/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 147.6 | 4263561-01 | 0 | 0
230 | Finish Material | GL | 843 | 03/25/19 | 03/25/19 | Mat | Req 5073 |  |  |  |  | 640.3 |  | 0 | 0
230 | Finish Material | GL | 845 | 03/25/19 | 03/25/19 | Mat | Req 5833 |  |  |  |  | -345.12 |  | 0 | 0
230 | Finish Material | AP | 892 | 03/15/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 138.64 | 7036700 | 0 | 0
230 | Finish Material | AP | 904 | 03/25/19 | 03/26/19 | 1231KS | Keller Supply Company |  |  |  |  | 132.83 | S012794998.001 | 0 | 0
230 | Finish Material | AP | 907 | 03/18/19 | 03/26/19 | 1231KS | Keller Supply Company |  |  |  |  | 5894.56 | S012517691.001 | 0 | 0
230 | Finish Material | AP | 908 | 03/21/19 | 03/26/19 | 1231KS | Keller Supply Company |  |  |  |  | 225.05 | S012805730.001 | 0 | 0
230 | Finish Material | AP | 1027 | 03/22/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 48.3 | 032219A | 0 | 0
230 | Finish Material | AP | 1028 | 03/23/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 29.76 | 032319A | 0 | 0
230 | Finish Material | AP | 32 | 03/14/19 | 04/03/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 180.84 | 701223 | 0 | 0
230 | Finish Material | AP | 40 | 03/08/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 361.85 | 4264511-00 | 0 | 0
230 | Finish Material | AP | 59 | 03/13/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 7.9 | 4263605-01 | 0 | 0
230 | Finish Material | AP | 64 | 03/14/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 385.23 | 4264768-00 | 0 | 0
230 | Finish Material | GL | 210 | 04/08/19 | 04/08/19 | Mat | Req 5879 |  |  |  |  | 917.72 |  | 0 | 0
230 | Finish Material | AP | 256 | 03/25/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 28.4 | 4264511-01 | 0 | 0
230 | Finish Material | AP | 305 | 03/22/19 | 04/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75 | 4265215-00 | 0 | 0
230 | Finish Material | GL | 434 | 04/12/19 | 04/12/19 | Mat | Req 5142 |  |  |  |  | 2046.96 |  | 0 | 0
230 | Finish Material | AP | 462 | 03/29/19 | 04/15/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 77.6 | S9190064.001 | 0 | 0
230 | Finish Material | AP | 712 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 350.1 | 4265808-00 | 0 | 0
230 | Finish Material | GL | 902 | 04/30/19 | 04/30/19 | Mat | Req 5925 |  |  |  |  | 745.21 |  | 0 | 0
230 | Finish Material | AP | 135 | 04/11/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 279 | 4265979-00 | 0 | 0
230 | Finish Material | AP | 117 | 04/12/19 | 05/06/19 | 1231KS | Keller Supply Company |  |  |  |  | 5894.56 | S012517809.001 | 0 | 0
230 | Finish Material | AP | 341 | 04/19/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 221.4 | 4266407-00 | 0 | 0
230 | Finish Material | AP | 345 | 04/22/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 35.55 | 4266483-00 | 0 | 0
230 | Finish Material | AP | 362 | 04/24/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 424.2 | 4266407-01 | 0 | 0
230 | Finish Material | AP | 496 | 04/29/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 382.8 | 7162445 | 0 | 0
230 | Finish Material | AP | 526 | 04/26/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 5923.52 | S012517281.002 | 0 | 0
230 | Finish Material | AP | 527 | 04/29/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 4558.08 | S012516266.002 | 0 | 0
230 | Finish Material | AP | 528 | 05/09/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 4558.08 | S012517540.002 | 0 | 0
230 | Finish Material | GL | 710 | 05/23/19 | 05/23/19 | 1380RS | Inv 4264761-01 |  |  |  |  | 34.29 |  | 0 | 0
230 | Finish Material | AP | 730 | 04/30/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 105.4 | 4266851-00 | 0 | 0
230 | Finish Material | AP | 754 | 05/06/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 83 | 4266407-02 | 0 | 0
230 | Finish Material | AP | 758 | 05/07/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -14 | 4267214-00 | 0 | 0
230 | Finish Material | AP | 772 | 05/01/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 138.6 | 4266733-00 | 0 | 0
230 | Finish Material | AP | 775 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 22.8 | 4266733-01 | 0 | 0
230 | Finish Material | AP | 776 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 12.15 | 4266851-01 | 0 | 0
230 | Finish Material | GL | 813 | 05/30/19 | 05/30/19 | Mat | Req 5970 |  |  |  |  | 850.17 |  | 0 | 0
230 | Finish Material | GL | 855 | 05/30/19 | 05/30/19 | Mat | Req 5946 |  |  |  |  | 2842.07 |  | 0 | 0
230 | Finish Material | AP | 965 | 05/09/19 | 05/31/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.52 | 4267264-00 | 0 | 0
230 | Finish Material | AP | 549 | 04/26/19 | 06/01/19 | 1231KS | Keller Supply Company |  |  |  |  | -5923.52 | S012517281.002A | 0 | 0
230 | Finish Material | AP | 550 | 04/26/19 | 06/01/19 | 1231KS | Keller Supply Company |  |  |  |  | 5935.52 | S012517281.002B | 0 | 0
230 | Finish Material | AP | 33 | 05/23/19 | 06/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 7.92 | 4267904-00 | 0 | 0
230 | Finish Material | AP | 89 | 05/20/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -543.76 | CM769593 | 0 | 0
230 | Finish Material | GL | 107 | 06/05/19 | 06/05/19 | Mat | Req 5251 |  |  |  |  | 1561.9 |  | 0 | 0
230 | Finish Material | AP | 174 | 05/13/19 | 06/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 69.12 | 4267399-00 | 0 | 0
230 | Finish Material | AP | 261 | 05/15/19 | 06/06/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 163.75 | 4267529-00 | 0 | 0
230 | Finish Material | AP | 306 | 05/28/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 348.35 | 4268030-00 | 0 | 0
230 | Finish Material | AP | 374 | 05/21/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 208.53 | S013034142.001 | 0 | 0
230 | Finish Material | AP | 381 | 05/20/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 5935.52 | S012517568.002 | 0 | 0
230 | Finish Material | AP | 387 | 05/31/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 5935.52 | S012517655.002 | 0 | 0
230 | Finish Material | AP | 388 | 05/28/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 4558.08 | S012517625.002 | 0 | 0
230 | Finish Material | AP | 404 | 05/29/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 23.28 | S9281119.001 | 0 | 0
230 | Finish Material | AP | 537 | 06/04/19 | 06/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 513 | 4268295-00 | 0 | 0
230 | Finish Material | AP | 538 | 06/07/19 | 06/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 57 | 4268496-00 | 0 | 0
230 | Finish Material | AP | 559 | 06/06/19 | 06/17/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 54.32 | S9281119.002 | 0 | 0
230 | Finish Material | AP | 589 | 06/13/19 | 06/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 255.17 | S013089210.001 | 0 | 0
230 | Finish Material | AP | 711 | 06/13/19 | 06/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 231 | 4268373-00 | 0 | 0
230 | Finish Material | GL | 833 | 06/26/19 | 06/26/19 | Mat | Req 6050 |  |  |  |  | 1803.17 |  | 0 | 0
230 | Finish Material | GL | 136 | 07/09/19 | 07/09/19 | Mat | Req 6100 |  |  |  |  | 432.52 |  | 0 | 0
230 | Finish Material | AP | 273 | 06/20/19 | 07/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 77 | 4268373-01 | 0 | 0
230 | Finish Material | AP | 401 | 06/25/19 | 07/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -33.75 | 4269395-00 | 0 | 0
230 | Finish Material | AP | 437 | 07/01/19 | 07/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 155.2 | 4268819-00 | 0 | 0
230 | Finish Material | AP | 454 | 06/26/19 | 07/16/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 185.84 | S009323044.001 | 0 | 0
230 | Finish Material | AP | 455 | 06/27/19 | 07/16/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2.88 | S099323044.002 | 0 | 0
230 | Finish Material | AP | 456 | 06/28/19 | 07/16/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 428.68 | S009323044.003 | 0 | 0
230 | Finish Material | AP | 474 | 07/01/19 | 07/16/19 | 1231KS | Keller Supply Company |  |  |  |  | 3923.44 | S012517714.002 | 0 | 0
230 | Finish Material | AP | 475 | 07/01/19 | 07/16/19 | 1231KS | Keller Supply Company |  |  |  |  | 4050.87 | S012517783.002 | 0 | 0
230 | Finish Material | AP | 486 | 07/02/19 | 07/17/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 141.85 | 4269615-00 | 0 | 0
230 | Finish Material | AP | 706 | 07/10/19 | 07/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 57 | 4269718-00 | 0 | 0
230 | Finish Material | AP | 733 | 07/23/19 | 07/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 5088.79 | S012517831.002 | 0 | 0
230 | Finish Material | AP | 403 | 08/02/19 | 08/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 5.26 | 080219A | 0 | 0
230 | Finish Material | AP | 153 | 07/22/19 | 08/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 12.46 | 7396087 | 0 | 0
230 | Finish Material | GL | 249 | 08/08/19 | 08/08/19 | Mat | Req 6192 |  |  |  |  | 1559.73 |  | 0 | 0
230 | Finish Material | GL | 250 | 08/08/19 | 08/08/19 | Mat | Req 6200 |  |  |  |  | 45.19 |  | 0 | 0
230 | Finish Material | AP | 469 | 07/24/19 | 08/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 66.26 | 4270533-00 | 0 | 0
230 | Finish Material | AP | 490 | 07/25/19 | 08/12/19 | 1231KS | Keller Supply Company |  |  |  |  | 5009.28 | S012517896.002 | 0 | 0
230 | Finish Material | AP | 1137 | 08/16/19 | 08/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 385.29 | S013308335.001 | 0 | 0
230 | Finish Material | AP | 162 | 08/23/19 | 09/10/19 | 1231KS | Keller Supply Company |  |  |  |  | 555.5 | S013370530.001 | 0 | 0
230 | Finish Material | AP | 201 | 08/23/19 | 09/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 6.54 | 082319A1 | 0 | 0
230 | Finish Material | AP | 204 | 08/29/19 | 09/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 79.74 | 082919A | 0 | 0
230 | Finish Material | AP | 205 | 09/03/19 | 09/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 23.53 | 090319A | 0 | 0
230 | Finish Material | GL | 371 | 09/16/19 | 09/16/19 | Mat | Req 6341 |  |  |  |  | 853.88 |  | 0 | 0
230 | Finish Material | AP | 433 | 09/13/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 85.29 | S013447654.001 | 0 | 0
230 | Finish Material | AP | 436 | 08/30/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 334.35 | S013304132.001 | 0 | 0
230 | Finish Material | AP | 437 | 08/30/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 143.82 | S013402086.001 | 0 | 0
230 | Finish Material | AP | 438 | 09/04/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | 1065.36 | S013404901.001 | 0 | 0
230 | Finish Material | AP | 439 | 09/06/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | -1065.36 | S013424049.001 | 0 | 0
230 | Finish Material | AP | 440 | 09/12/19 | 09/18/19 | 1231KS | Keller Supply Company |  |  |  |  | -722.61 | S013439845.001 | 0 | 0
230 | Finish Material | GL | 740 | 09/26/19 | 09/26/19 | CK#5861 | Jordan Gerard |  |  |  |  | 34.1 |  | 0 | 0
230 | Finish Material | GL | 399 | 10/15/19 | 10/15/19 | Mat | Req 6396 |  |  |  |  | -3430.74 |  | 0 | 0
230 | Finish Material | AP | 410 | 09/18/19 | 10/15/19 | 1231KS | Keller Supply Company |  |  |  |  | 294.96 | S013440406.001 | 0 | 0
230 | Finish Material | GL | 437 | 10/16/19 | 10/16/19 | Mat | Req 6415 |  |  |  |  | 1015.83 |  | 0 | 0
230 | Finish Material | GL | 691 | 10/28/19 | 10/28/19 | Mat | Req 6420 |  |  |  |  | -65.75 |  | 0 | 0
240 | Gas Material | GL | 182 | 10/10/18 | 10/10/18 | Mat | Req 5457 |  |  |  |  | 852.63 |  | 0 | 0
240 | Gas Material | GL | 556 | 10/22/18 | 10/22/18 | Mat | Req 4740 |  |  |  |  | 11.32 |  | 0 | 0
240 | Gas Material | GL | 882 | 10/31/18 | 10/31/18 | Mat | Req 5500 |  |  |  |  | 153.56 |  | 0 | 0
240 | Gas Material | AP | 100 | 10/08/18 | 11/02/18 | 1231KS | Keller Supply Company |  |  |  |  | 1397.2 | S012354024.001 | 0 | 0
240 | Gas Material | AP | 136 | 10/06/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1127.42 | 4258199-00 | 0 | 0
240 | Gas Material | AP | 397 | 10/25/18 | 11/13/18 | 1231KS | Keller Supply Company |  |  |  |  | 505.56 | S012414756.001 | 0 | 0
240 | Gas Material | AP | 604 | 10/22/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 379.27 | 4258951-00 | 0 | 0
240 | Gas Material | AP | 605 | 10/23/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 67.2 | 4258199-01 | 0 | 0
240 | Gas Material | AP | 607 | 10/24/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 195.86 | 4258951-01 | 0 | 0
240 | Gas Material | GL | 779 | 11/26/18 | 11/26/18 | Mat | Req 4843 |  |  |  |  | 74.72 |  | 0 | 0
240 | Gas Material | GL | 801 | 11/07/18 | 11/28/18 | Mat | Req 5537 |  |  |  |  | 25.08 |  | 0 | 0
240 | Gas Material | AP | 967 | 10/30/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 266.62 | 4259237-00 | 0 | 0
240 | Gas Material | AP | 970 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 139.52 | 4259237-01 | 0 | 0
240 | Gas Material | AP | 192 | 11/02/18 | 12/11/18 | 1231KS | Keller Supply Company |  |  |  |  | 102.31 | S012447372.001 | 0 | 0
240 | Gas Material | AP | 385 | 11/07/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -75.07 | 4259672-00 | 0 | 0
240 | Gas Material | AP | 421 | 11/05/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75.07 | 4259473-00 | 0 | 0
240 | Gas Material | AP | 423 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 83.78 | 4260068-00 | 0 | 0
240 | Gas Material | AP | 424 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 45.96 | 4260071-00 | 0 | 0
240 | Gas Material | AP | 562 | 01/21/19 | 02/20/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 93.55 | 4262567-00 | 0 | 0
240 | Gas Material | AP | 674 | 01/28/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 25.99 | 4262881-00 | 0 | 0
240 | Gas Material | GL | 167 | 03/04/19 | 03/04/19 | Mat | Req 5012 |  |  |  |  | 103.34 |  | 0 | 0
240 | Gas Material | GL | 840 | 03/25/19 | 03/25/19 | Mat | Req 5075 |  |  |  |  | 21.16 |  | 0 | 0
240 | Gas Material | AP | 168 | 03/18/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 263.57 | 4264717-00 | 0 | 0
240 | Gas Material | AP | 513 | 03/28/19 | 04/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 405.64 | 4265421-00 | 0 | 0
240 | Gas Material | AP | 363 | 04/24/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 17.7 | 4266590-00 | 0 | 0
240 | Gas Material | AP | 374 | 04/25/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19.84 | 4266668-00 | 0 | 0
240 | Gas Material | AP | 742 | 05/01/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 19.84 | 4266929-00 | 0 | 0
240 | Gas Material | AP | 757 | 05/07/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.52 | 4267187-00 | 0 | 0
240 | Gas Material | AP | 773 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 4.92 | 4266590-01 | 0 | 0
240 | Gas Material | GL | 816 | 05/30/19 | 05/30/19 | Mat | Req 5973 |  |  |  |  | 21.49 |  | 0 | 0
240 | Gas Material | GL | 105 | 06/05/19 | 06/05/19 | Mat | Req 5252 |  |  |  |  | 429.68 |  | 0 | 0
240 | Gas Material | AP | 171 | 05/22/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1276.69 | 7226469 | 0 | 0
240 | Gas Material | AP | 285 | 05/17/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 92.99 | 4267608-00 | 0 | 0
240 | Gas Material | AP | 307 | 05/29/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 97.57 | 4268096-00 | 0 | 0
240 | Gas Material | AP | 308 | 05/29/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 20.76 | 4268098-00 | 0 | 0
240 | Gas Material | AP | 309 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 32.7 | 4267608-01 | 0 | 0
240 | Gas Material | AP | 389 | 05/31/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 333.55 | S013079677.001 | 0 | 0
240 | Gas Material | AP | 393 | 05/24/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1625.57 | S9269585.001 | 0 | 0
240 | Gas Material | AP | 394 | 05/29/19 | 06/11/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 201.21 | S9269585.002 | 0 | 0
240 | Gas Material | AP | 533 | 06/03/19 | 06/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 2.53 | S013090471.001 | 0 | 0
240 | Gas Material | GL | 815 | 06/26/19 | 06/26/19 | Mat | Req 6030 |  |  |  |  | -12.85 |  | 0 | 0
240 | Gas Material | GL | 822 | 06/26/19 | 06/26/19 | Mat | Req 6028 |  |  |  |  | -116.68 |  | 0 | 0
240 | Gas Material | GL | 823 | 06/26/19 | 06/26/19 | Mat | Req 6049 |  |  |  |  | 31.09 |  | 0 | 0
240 | Gas Material | GL | 138 | 07/09/19 | 07/09/19 | Mat | Req 6102 |  |  |  |  | 24.81 |  | 0 | 0
240 | Gas Material | AP | 488 | 07/03/19 | 07/17/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 39.72 | 4269760-00 | 0 | 0
240 | Gas Material | AP | 164 | 07/22/19 | 08/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 6.8 | 7396223 | 0 | 0
240 | Gas Material | GL | 253 | 08/08/19 | 08/08/19 | Mat | Req 6203 |  |  |  |  | 3.8 |  | 0 | 0
240 | Gas Material | AP | 509 | 07/22/19 | 08/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 65.91 | S013260095.001 | 0 | 0
240 | Gas Material | AP | 510 | 07/22/19 | 08/13/19 | 1231KS | Keller Supply Company |  |  |  |  | 8.98 | S013260095.002 | 0 | 0
240 | Gas Material | AP | 788 | 08/06/19 | 08/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 222.85 | S013313787.002 | 0 | 0
240 | Gas Material | AP | 952 | 08/02/19 | 08/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 110.31 | 4270934-00 | 0 | 0
240 | Gas Material | AP | 980 | 08/14/19 | 08/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 140.88 | 4271392-00 | 0 | 0
240 | Gas Material | AP | 1097 | 08/21/19 | 08/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 83.36 | 4271775-00 | 0 | 0
240 | Gas Material | AP | 1104 | 08/22/19 | 08/31/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 70.25 | 4271392-01 | 0 | 0
240 | Gas Material | AP | 1136 | 08/13/19 | 08/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 24.57 | S0123343241.001 | 0 | 0
240 | Gas Material | AP | 124 | 08/23/19 | 09/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 24.9 | 4271775-01 | 0 | 0
240 | Gas Material | GL | 372 | 09/16/19 | 09/16/19 | Mat | Req 6342 |  |  |  |  | 184.8 |  | 0 | 0
240 | Gas Material | GL | 398 | 10/15/19 | 10/15/19 | Mat | Req 6397 |  |  |  |  | -31.64 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 379 | 08/10/18 | 08/10/18 | Mat | Req 4527 |  |  |  |  | 346.16 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 1160 | 08/16/18 | 08/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4902.84 | S8882101.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1161 | 08/16/18 | 08/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1461.66 | S8882101.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1162 | 08/21/18 | 08/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 13241.05 | S8891071.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1168 | 08/20/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 787.64 | S8891071.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1169 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 8.24 | S8891071.004 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1170 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 12.36 | S8891071.006 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1171 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 123 | S8871071.007 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1172 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 47.15 | S8891071.008 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1173 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 828.96 | S8891071.009 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1174 | 08/23/18 | 08/31/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 627.3 | S8891071.010 | 0 | 0
241 | Water Main/Insulation Mat | GL | 193 | 09/10/18 | 09/10/18 | Mat | Req 4680 |  |  |  |  | 91.8 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 403 | 08/28/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 608.15 | S8891071.011 | 0 | 0
241 | Water Main/Insulation Mat | AP | 404 | 08/30/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 111.91 | S8908806.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 405 | 08/31/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 117.53 | S8908806.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 406 | 09/06/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 283.62 | S8913217.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 407 | 09/12/18 | 09/18/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 765.27 | S8917537.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 597 | 09/25/18 | 09/25/18 | Mat | Req 5400 |  |  |  |  | 698.34 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 179 | 10/10/18 | 10/10/18 | Mat | Req 5460 |  |  |  |  | 3257.78 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 184 | 10/10/18 | 10/10/18 | Mat | Req 5455 |  |  |  |  | 233.36 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 227 | 09/14/18 | 10/10/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 831.07 | S8927488.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 228 | 09/19/18 | 10/10/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 342 | S8891071.012 | 0 | 0
241 | Water Main/Insulation Mat | GL | 559 | 10/22/18 | 10/22/18 | Mat | Req 4736 |  |  |  |  | 1402.48 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 560 | 10/22/18 | 10/22/18 | Mat | Req 4735 |  |  |  |  | 2170.2 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 580 | 10/22/18 | 10/22/18 | Mat | Req 5480 |  |  |  |  | 675.32 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 588 | 10/22/18 | 10/22/18 | Mat | Req 4753 |  |  |  |  | 506.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 863 | 10/01/18 | 10/25/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 5752.01 | 6583418 | 0 | 0
241 | Water Main/Insulation Mat | AP | 784 | 09/28/18 | 10/26/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 9302 | S8948140.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 792 | 09/28/18 | 10/29/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 853.42 | 6584976 | 0 | 0
241 | Water Main/Insulation Mat | AP | 392 | 09/24/18 | 10/31/18 | 1231KS | Keller Supply Company |  |  |  |  | 6214.92 | S012259346.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 877 | 10/31/18 | 10/31/18 | Mat | Req 5517 |  |  |  |  | 1034.52 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 178 | 10/15/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 43.3 | S8975065.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 309 | 11/09/18 | 11/09/18 | Mat | Req 4765 |  |  |  |  | 959.98 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 340 | 10/18/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2439.26 | S8978270.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 341 | 10/19/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2193.2 | S8980726.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 359 | 10/25/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 228.31 | 6661177 | 0 | 0
241 | Water Main/Insulation Mat | AP | 360 | 10/25/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 95.73 | 6661177-1 | 0 | 0
241 | Water Main/Insulation Mat | AP | 420 | 10/24/18 | 11/13/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 218.08 | S8988649.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 560 | 11/16/18 | 11/16/18 | Mat | Req 4804 |  |  |  |  | 1789.41 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 776 | 11/26/18 | 11/26/18 | Mat | Req 4845 |  |  |  |  | 1553.62 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 803 | 11/07/18 | 11/28/18 | Mat | Req 5540 |  |  |  |  | 228.78 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 935 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 3163.64 | 6661734 | 0 | 0
241 | Water Main/Insulation Mat | AP | 944 | 10/29/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1701.33 | S8891071.013 | 0 | 0
241 | Water Main/Insulation Mat | GL | 992 | 11/30/18 | 11/30/18 | Mat | Req 5593 |  |  |  |  | 37.36 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 1036 | 11/13/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 817.28 | S9014521.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1041 | 11/05/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 994.94 | 6692819 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1050 | 11/10/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 466.16 | 6709228 | 0 | 0
241 | Water Main/Insulation Mat | AP | 424 | 11/15/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 36.9 | 4260071-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 450 | 11/23/18 | 12/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 159.6 | 4260079-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 634 | 12/21/18 | 12/21/18 | Mat | Req 5603 |  |  |  |  | 1158.12 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 661 | 11/29/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1604.75 | S9035818.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 662 | 12/06/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1325.69 | S9048431.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 130 | 12/13/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 3132.5 | S9055501.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 131 | 12/21/18 | 01/07/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 483.8 | S8891071.014 | 0 | 0
241 | Water Main/Insulation Mat | GL | 316 | 01/11/19 | 01/11/19 | Mat | Req 4876 |  |  |  |  | 821.6 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 358 | 01/11/19 | 01/11/19 | Mat | Req 4911 |  |  |  |  | 840 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 420 | 01/15/19 | 01/15/19 | Mat | Req 4893 |  |  |  |  | 563.7 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 629 | 12/14/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 325.44 | 4261206-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 684 | 01/23/19 | 01/23/19 | Mat | Req 4983 |  |  |  |  | 340.4 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 919 | 01/07/19 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 154.98 | S9079967.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 924 | 01/03/19 | 01/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 6083.73 | 4261313-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 925 | 01/03/19 | 01/30/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 151.2 | 4261313-01 | 0 | 0
241 | Water Main/Insulation Mat | AP | 104 | 12/28/18 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2014.23 | S9072477.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 105 | 01/10/19 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 389.09 | S9072477.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 106 | 01/21/19 | 02/01/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 403.19 | S9072477.003 | 0 | 0
241 | Water Main/Insulation Mat | AP | 676 | 01/29/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -151.65 | 4262934-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 144 | 03/04/19 | 03/04/19 | Mat | Req 5051 |  |  |  |  | -1657.87 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 169 | 03/04/19 | 03/04/19 | Mat | Req 5724 |  |  |  |  | 119.82 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 355 | 03/08/19 | 03/08/19 | Mat | Req 5040 |  |  |  |  | 157 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 443 | 02/28/19 | 03/13/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 55.17 | S9150996.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 447 | 02/28/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 289.78 | 6994445 | 0 | 0
241 | Water Main/Insulation Mat | GL | 578 | 03/15/19 | 03/15/19 | Mat | Req 5814 |  |  |  |  | 1224.88 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 841 | 03/25/19 | 03/25/19 | Mat | Req 5074 |  |  |  |  | 499.31 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 846 | 03/25/19 | 03/25/19 | Mat | Req 5832 |  |  |  |  | -759.98 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 880 | 03/08/19 | 03/26/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 488.16 | 4261208-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 1060 | 03/28/19 | 03/28/19 | Mat | Req 5836 |  |  |  |  | -1339.7 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 34 | 03/19/19 | 04/03/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 216.2 | S9174160.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 262 | 03/19/19 | 04/03/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | -216.2 | S9174160.001A | 0 | 0
241 | Water Main/Insulation Mat | AP | 263 | 03/19/19 | 04/03/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 261.2 | S9174160.001B | 0 | 0
241 | Water Main/Insulation Mat | AP | 164 | 03/22/19 | 04/05/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 107.7 | S9174160.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 207 | 04/08/19 | 04/08/19 | Mat | Req 5881 |  |  |  |  | 153.35 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 222 | 04/08/19 | 04/08/19 | Mat | Req 5117 |  |  |  |  | 36.56 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 237 | 03/22/19 | 04/09/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 514.67 | S9178188.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 238 | 03/22/19 | 04/09/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 63.35 | S9178188.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 247 | 03/20/19 | 04/09/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 693 | 4264924-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 432 | 04/12/19 | 04/12/19 | Mat | Req 5144 |  |  |  |  | 62.12 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 657 | 04/02/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 516 | 4264146-00 | 0 | 0
241 | Water Main/Insulation Mat | AP | 666 | 04/04/19 | 04/23/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 88.2 | 4264924-01 | 0 | 0
241 | Water Main/Insulation Mat | GL | 553 | 05/21/19 | 05/21/19 | Mat | Req 5961 |  |  |  |  | -235.09 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 815 | 05/30/19 | 05/30/19 | Mat | Req 5972 |  |  |  |  | 32.84 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 820 | 06/26/19 | 06/26/19 | Mat | Req 6029 |  |  |  |  | -919.75 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 374 | 06/25/19 | 07/10/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 831.26 | S009320785.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 452 | 06/27/19 | 07/16/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 286.05 | S009325415.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 390 | 07/10/19 | 08/01/19 | 1234CO | Capital One Credit Card |  |  |  |  | 50.8 | 071019BH | 0 | 0
241 | Water Main/Insulation Mat | AP | 94 | 07/08/19 | 08/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 588.35 | 7354536 | 0 | 0
241 | Water Main/Insulation Mat | GL | 251 | 08/08/19 | 08/08/19 | Mat | Req 6201 |  |  |  |  | 283.57 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 400 | 10/15/19 | 10/15/19 | Mat | Req 6398 |  |  |  |  | -344.1 |  | 0 | 0
242 | Mech Room Material | GL | 557 | 10/22/18 | 10/22/18 | Mat | Req 4739 |  |  |  |  | 41.18 |  | 0 | 0
242 | Mech Room Material | GL | 777 | 11/26/18 | 11/26/18 | Mat | Req 4844 |  |  |  |  | 211.48 |  | 0 | 0
242 | Mech Room Material | AP | 552 | 02/15/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 6251.34 | 6955450 | 0 | 0
242 | Mech Room Material | AP | 553 | 02/15/19 | 02/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 143.24 | 6955450-1 | 0 | 0
242 | Mech Room Material | AP | 675 | 01/29/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 401.36 | 4262885-00 | 0 | 0
242 | Mech Room Material | GL | 165 | 03/04/19 | 03/04/19 | Mat | Req 5014 |  |  |  |  | 34.9 |  | 0 | 0
242 | Mech Room Material | AP | 230 | 02/19/19 | 03/06/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4884.56 | S9132955.001 | 0 | 0
242 | Mech Room Material | AP | 239 | 02/21/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 289.78 | 6955450-2 | 0 | 0
242 | Mech Room Material | AP | 240 | 02/22/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 289.78 | 6955450-3 | 0 | 0
242 | Mech Room Material | AP | 241 | 02/25/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1014.47 | 6984463 | 0 | 0
242 | Mech Room Material | GL | 349 | 03/08/19 | 03/08/19 | Mat | Req 5055 |  |  |  |  | 1388.75 |  | 0 | 0
242 | Mech Room Material | AP | 459 | 03/01/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 688.58 | 6999046 | 0 | 0
242 | Mech Room Material | AP | 460 | 03/07/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1413.23 | 6984463-1 | 0 | 0
242 | Mech Room Material | AP | 461 | 03/07/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 582.3 | 6999046-1 | 0 | 0
242 | Mech Room Material | GL | 611 | 03/15/19 | 03/15/19 | Mat | Req 5831 |  |  |  |  | 564.08 |  | 0 | 0
242 | Mech Room Material | GL | 613 | 03/15/19 | 03/15/19 | Mat | Req 5064 |  |  |  |  | 4432.95 |  | 0 | 0
242 | Mech Room Material | GL | 615 | 03/15/19 | 03/15/19 | Mat | Req 5068 |  |  |  |  | -232.71 |  | 0 | 0
242 | Mech Room Material | AP | 791 | 03/07/18 | 03/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 480.32 | 4264057-00 | 0 | 0
242 | Mech Room Material | GL | 842 | 03/25/19 | 03/25/19 | Mat | Req 5072 |  |  |  |  | 869.69 |  | 0 | 0
242 | Mech Room Material | GL | 850 | 03/25/19 | 03/25/19 | Mat | Req 5085 |  |  |  |  | -391.62 |  | 0 | 0
242 | Mech Room Material | AP | 868 | 03/11/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 433.4 | S9164388.001 | 0 | 0
242 | Mech Room Material | AP | 883 | 03/08/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1782.46 | 7019975 | 0 | 0
242 | Mech Room Material | AP | 884 | 03/12/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 395.67 | 6999046-2 | 0 | 0
242 | Mech Room Material | AP | 885 | 03/12/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 143.24 | 7019975-1 | 0 | 0
242 | Mech Room Material | AP | 886 | 03/14/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 74.71 | 7019975-2 | 0 | 0
242 | Mech Room Material | AP | 889 | 03/15/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 197.83 | 7019975-3 | 0 | 0
242 | Mech Room Material | AP | 891 | 03/15/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 379.39 | 7035222 | 0 | 0
242 | Mech Room Material | AP | 893 | 03/19/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 33.83 | 7035222-1 | 0 | 0
242 | Mech Room Material | AP | 909 | 03/25/19 | 03/26/19 | 1231KS | Keller Supply Company |  |  |  |  | 63.32 | S012845334.001 | 0 | 0
242 | Mech Room Material | GL | 1065 | 03/28/19 | 03/28/19 | Mat | Req 5852 |  |  |  |  | -59.78 |  | 0 | 0
242 | Mech Room Material | AP | 72 | 03/15/19 | 04/03/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 948.59 | 4264761-00 | 0 | 0
242 | Mech Room Material | AP | 169 | 03/18/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 168.87 | 4264772-00 | 0 | 0
242 | Mech Room Material | AP | 302 | 03/18/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -168.87 | 4264772-00A | 0 | 0
242 | Mech Room Material | AP | 303 | 03/18/19 | 04/05/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 138.87 | 4264772-00B | 0 | 0
242 | Mech Room Material | GL | 431 | 04/12/19 | 04/12/19 | Mat | Req 5145 |  |  |  |  | 48.05 |  | 0 | 0
242 | Mech Room Material | AP | 500 | 04/04/19 | 04/16/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 84.82 | 7087335 | 0 | 0
242 | Mech Room Material | AP | 501 | 04/05/19 | 04/16/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 10.35 | 7087335-1 | 0 | 0
242 | Mech Room Material | AP | 646 | 03/29/19 | 04/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 34.29 | 4264761-01 | 0 | 0
242 | Mech Room Material | AP | 281 | 04/16/19 | 05/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 118.96 | 4266224-00 | 0 | 0
242 | Mech Room Material | AP | 364 | 04/24/19 | 05/15/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 127.88 | 4266606-00 | 0 | 0
242 | Mech Room Material | GL | 539 | 05/21/19 | 05/21/19 | Mat | Req 5969 |  |  |  |  | -505 |  | 0 | 0
242 | Mech Room Material | GL | 552 | 05/21/19 | 05/21/19 | Mat | Req 5959 |  |  |  |  | -2324.14 |  | 0 | 0
242 | Mech Room Material | GL | 710 | 05/23/19 | 05/23/19 | 1380RS | Inv 4264761-01 |  |  |  |  | -34.29 |  | 0 | 0
242 | Mech Room Material | AP | 741 | 05/01/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 252.98 | 4266606-01 | 0 | 0
242 | Mech Room Material | AP | 774 | 05/09/19 | 05/29/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8.34 | 4266606-02 | 0 | 0
242 | Mech Room Material | GL | 818 | 05/30/19 | 05/30/19 | Mat | Req 5975 |  |  |  |  | 25.05 |  | 0 | 0
242 | Mech Room Material | AP | 87 | 05/14/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 5.94 | 7207163 | 0 | 0
242 | Mech Room Material | AP | 88 | 05/14/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1426.3 | 7205339 | 0 | 0
242 | Mech Room Material | AP | 548 | 05/21/19 | 06/17/19 | 1231KS | Keller Supply Company |  |  |  |  | 36.26 | S013043983.001 | 0 | 0
242 | Mech Room Material | GL | 373 | 09/16/19 | 09/16/19 | Mat | Req 6343 |  |  |  |  | 421.52 |  | 0 | 0
242 | Mech Room Material | GL | 397 | 10/15/19 | 10/15/19 | Mat | Req 6399 |  |  |  |  | -120.13 |  | 0 | 0
242 | Mech Room Material | GL | 689 | 10/28/19 | 10/28/19 | Mat | Req 6419 |  |  |  |  | -123.02 |  | 0 | 0
243 | Condensation Drains Mat | GL | 644 | 01/22/19 | 01/22/19 | Mat | Req 4951 |  |  |  |  | 1.5 |  | 0 | 0
243 | Condensation Drains Mat | GL | 838 | 03/25/19 | 03/25/19 | Mat | Req 5077 |  |  |  |  | 1.59 |  | 0 | 0
243 | Condensation Drains Mat | GL | 817 | 05/30/19 | 05/30/19 | Mat | Req 5974 |  |  |  |  | 0.87 |  | 0 | 0
243 | Condensation Drains Mat | GL | 831 | 06/26/19 | 06/26/19 | Mat | Req 6052 |  |  |  |  | 2.58 |  | 0 | 0
243 | Condensation Drains Mat | GL | 439 | 10/16/19 | 10/16/19 | Adj | [5 empty] | -6.54 |  | 0 | 0
600 | Subcontractor | AP | 913 | 01/11/19 | 01/30/19 | 3181SC | Scan2Core, Inc. |  |  |  |  | 984 | 72062 | 0 | 0
600 | Subcontractor | AP | 791 | 05/15/19 | 05/29/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 165 | 1383 | 0 | 0
600 | Subcontractor | AP | 803 | 05/17/19 | 05/29/19 | 6912MF | Mechanical Firestop Services, LLC |  |  |  |  | 8337.5 | 1586-5784 | 0 | 0
600 | Subcontractor | AP | 806 | 05/13/19 | 05/29/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 4187.5 | 16598-5513 | 0 | 0
600 | Subcontractor | AP | 729 | 06/18/19 | 06/24/19 | 6912MF | Mechanical Firestop Services, LLC |  |  |  |  | 8337.5 | 1586-5802 | 0 | 0
600 | Subcontractor | AP | 719 | 07/19/19 | 07/30/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 50 | INV01577 | 0 | 0
600 | Subcontractor | AP | 910 | 08/17/19 | 08/26/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 50 | INV01644 | 0 | 0
601 | Engineering/Plans | AP | 582 | 01/19/18 | 01/24/18 | 1625FE | Franklin Engineering |  |  |  |  | 103 | 6815 | 0 | 0
602 | Rental Equipment | AP | 629 | 07/06/18 | 07/23/18 | 1950SR | Sunbelt Rentals, Inc. |  |  |  |  | 93.5 | 80320995-0001 | 0 | 0
602 | Rental Equipment | AP | 632 | 10/10/18 | 10/16/18 | 2713AR | Ahern Rentals |  |  |  |  | 516.12 | 19616240-1 | 0 | 0
602 | Rental Equipment | AP | 808 | 11/07/18 | 11/28/18 | 2713AR | Ahern Rentals |  |  |  |  | 411.24 | 19616240-2 | 0 | 0
602 | Rental Equipment | AP | 151 | 12/05/18 | 01/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 411.24 | 19616240-3 | 0 | 0
602 | Rental Equipment | AP | 138 | 01/02/19 | 02/01/19 | 2713AR | Ahern Rentals |  |  |  |  | 411.24 | 19616240-4 | 0 | 0
602 | Rental Equipment | AP | 143 | 01/30/19 | 02/01/19 | 2713AR | Ahern Rentals |  |  |  |  | 411.24 | 19616240-5 | 0 | 0
602 | Rental Equipment | AP | 208 | 02/27/19 | 03/05/19 | 2713AR | Ahern Rentals |  |  |  |  | 411.24 | 19616240-006 | 0 | 0
602 | Rental Equipment | AP | 153 | 04/03/19 | 05/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 406.1 | 19616240-007 | 0 | 0
603 | Permits & Licenses | GL | 823 | 03/28/18 | 03/28/18 | CK#5071 | City of Lynnwood, Plan Review |  |  |  |  | 5321.6 |  | 0 | 0
603 | Permits & Licenses | GL | 266 | 06/06/18 | 06/06/18 | CK#5509 | City of Lynnwood |  |  |  |  | 13112 |  | 0 | 0
603 | Permits & Licenses | GL | 266 | 06/06/18 | 06/06/18 | CK#5509 | City of Lynnwood |  |  |  |  | 1433.6 |  | 0 | 0
603 | Permits & Licenses | AP | 52 | 05/07/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 287.82 | 050719B1 | 0 | 0
607 | Other Expenses | GL | 243 | 03/12/18 | 03/12/18 | Textura | Fee |  |  |  |  | 2750 |  | 0 | 0
607 | Other Expenses | GL | 296 | 03/14/18 | 03/14/18 | Reversal: | Textura Fee |  |  |  |  | -2750 |  | 0 | 0
607 | Other Expenses | GL | 297 | 03/14/18 | 03/14/18 | Textura | Fee |  |  |  |  | 614.4 |  | 0 | 0
607 | Other Expenses | GL | 712 | 03/28/18 | 03/28/18 | Textura | Fee |  |  |  |  | 2135.6 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 04/04/18 | 04/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 30.16 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 309 | 04/11/18 | 04/13/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 38.14 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 04/18/18 | 04/20/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 661 | 04/25/18 | 04/27/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 286.5 |  | 0 | 0
995 | Payroll Burden | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 05/16/18 | 05/18/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 15.08 |  | 0 | 0
995 | Payroll Burden | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 150.79 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 134 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | -60.32 |  | 0 | 0
995 | Payroll Burden | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 256.34 |  | 0 | 0
995 | Payroll Burden | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 06/06/18 | 06/08/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 247.92 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 173.41 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 06/13/18 | 06/15/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 729 | 06/20/18 | 06/22/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 259.45 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 465.68 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 29.94 |  | 0 | 0
995 | Payroll Burden | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 149.68 |  | 0 | 0
995 | Payroll Burden | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 21 | 07/04/18 | 07/06/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 07/11/18 | 07/13/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 166.76 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 273.2 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 24.84 |  | 0 | 0
995 | Payroll Burden | PR | 346 | 07/11/18 | 07/13/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 356 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | -39.03 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 07/18/18 | 07/20/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 07/18/18 | 07/20/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 104.22 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 07/18/18 | 07/20/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 07/18/18 | 07/20/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 07/18/18 | 07/20/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 07/25/18 | 07/27/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 07/25/18 | 07/27/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 778 | 07/25/18 | 07/27/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 783 | 07/25/18 | 07/27/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 785 | 07/25/18 | 07/27/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 792 | 07/25/18 | 07/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 802 | 07/25/18 | 07/27/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 294.04 |  | 0 | 0
995 | Payroll Burden | PR | 805 | 07/25/18 | 07/27/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 07/25/18 | 07/27/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 484.3 |  | 0 | 0
995 | Payroll Burden | PR | 813 | 07/25/18 | 07/27/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 339.28 |  | 0 | 0
995 | Payroll Burden | PR | 826 | 07/25/18 | 07/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 08/01/18 | 08/03/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 08/01/18 | 08/03/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 08/01/18 | 08/03/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 08/01/18 | 08/03/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 08/01/18 | 08/03/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 08/01/18 | 08/03/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 08/01/18 | 08/03/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 08/01/18 | 08/03/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 574.33 |  | 0 | 0
995 | Payroll Burden | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 54 | 08/01/18 | 08/03/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 08/01/18 | 08/03/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 221 | 08/08/18 | 08/10/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 08/08/18 | 08/10/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 232 | 08/08/18 | 08/10/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 295.37 |  | 0 | 0
995 | Payroll Burden | PR | 233 | 08/08/18 | 08/10/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 08/08/18 | 08/10/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 52.11 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 08/08/18 | 08/10/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 08/08/18 | 08/10/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 08/08/18 | 08/10/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 08/08/18 | 08/10/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 08/15/18 | 08/17/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 08/15/18 | 08/17/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 08/15/18 | 08/17/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 08/15/18 | 08/17/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 08/15/18 | 08/17/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 08/15/18 | 08/17/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 295.37 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 515 | 08/15/18 | 08/17/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 08/15/18 | 08/17/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 08/15/18 | 08/17/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 08/15/18 | 08/17/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 532 | 08/15/18 | 08/17/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 573 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 751 | 08/22/18 | 08/24/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 08/22/18 | 08/24/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 08/22/18 | 08/24/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 763 | 08/22/18 | 08/24/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 08/22/18 | 08/24/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 08/22/18 | 08/24/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 788 | 08/22/18 | 08/24/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 790 | 08/22/18 | 08/24/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 793 | 08/22/18 | 08/24/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 822 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 1005 | 08/29/18 | 08/31/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 1011 | 08/29/18 | 08/31/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 1012 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 1017 | 08/29/18 | 08/31/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 1018 | 08/29/18 | 08/31/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 1026 | 08/29/18 | 08/31/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 311.34 |  | 0 | 0
995 | Payroll Burden | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 1032 | 08/29/18 | 08/31/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 1035 | 08/29/18 | 08/31/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 1042 | 08/29/18 | 08/31/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 1044 | 08/29/18 | 08/31/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 605.38 |  | 0 | 0
995 | Payroll Burden | PR | 1047 | 08/29/18 | 08/31/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 204.9 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 09/05/18 | 09/07/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 09/05/18 | 09/07/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 57 | 09/05/18 | 09/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 09/05/18 | 09/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 09/05/18 | 09/07/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 219.53 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 09/05/18 | 09/07/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 09/05/18 | 09/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 09/05/18 | 09/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 09/05/18 | 09/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 09/05/18 | 09/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 09/05/18 | 09/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 09/05/18 | 09/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 09/12/18 | 09/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 277 | 09/12/18 | 09/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 311.78 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 283 | 09/12/18 | 09/14/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 09/12/18 | 09/14/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 289 | 09/12/18 | 09/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 09/12/18 | 09/14/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 09/12/18 | 09/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 306 | 09/12/18 | 09/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 09/12/18 | 09/14/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 316 | 09/12/18 | 09/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 09/12/18 | 09/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 09/12/18 | 09/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 347.26 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 413 | 09/19/18 | 09/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 09/19/18 | 09/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 09/19/18 | 09/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 09/19/18 | 09/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 09/19/18 | 09/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 09/19/18 | 09/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 497 | 09/19/18 | 09/21/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 502 | 09/19/18 | 09/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 09/19/18 | 09/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 09/19/18 | 09/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 09/19/18 | 09/21/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 09/19/18 | 09/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 09/19/18 | 09/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 09/19/18 | 09/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 09/19/18 | 09/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 698.51 |  | 0 | 0
995 | Payroll Burden | PR | 532 | 09/19/18 | 09/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 09/19/18 | 09/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 539 | 09/19/18 | 09/21/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 553.49 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 665 | 09/26/18 | 09/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.22 |  | 0 | 0
995 | Payroll Burden | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 673 | 09/26/18 | 09/28/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 675 | 09/26/18 | 09/28/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 678 | 09/26/18 | 09/28/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 679 | 09/26/18 | 09/28/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 680 | 09/26/18 | 09/28/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 09/26/18 | 09/28/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 09/26/18 | 09/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 688 | 09/26/18 | 09/28/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 696 | 09/26/18 | 09/28/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 09/26/18 | 09/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 704 | 09/26/18 | 09/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 706 | 09/26/18 | 09/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 324.64 |  | 0 | 0
995 | Payroll Burden | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 712 | 09/26/18 | 09/28/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 714 | 09/26/18 | 09/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 09/26/18 | 09/28/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 316.66 |  | 0 | 0
995 | Payroll Burden | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 36.37 |  | 0 | 0
995 | Payroll Burden | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 54.55 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 09/26/18 | 09/28/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 55.88 |  | 0 | 0
995 | Payroll Burden | PR | 28 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 10/03/18 | 10/05/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 10/03/18 | 10/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 39 | 10/03/18 | 10/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 10/03/18 | 10/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 10/03/18 | 10/05/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
995 | Payroll Burden | PR | 51 | 10/03/18 | 10/05/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 10/03/18 | 10/05/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 279.41 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 72.96 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 10/03/18 | 10/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 10/03/18 | 10/05/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 10/03/18 | 10/05/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/03/18 | 10/05/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 78 | 10/03/18 | 10/05/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 618.68 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 10/03/18 | 10/05/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 88 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 10/10/18 | 10/12/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 236 | 10/10/18 | 10/12/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 10/10/18 | 10/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 10/10/18 | 10/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 247 | 10/10/18 | 10/12/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 10/10/18 | 10/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 252 | 10/10/18 | 10/12/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 10/10/18 | 10/12/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 10/10/18 | 10/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 274 | 10/10/18 | 10/12/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 276 | 10/10/18 | 10/12/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 284 | 10/10/18 | 10/12/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 239.49 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 10/10/18 | 10/12/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 353.91 |  | 0 | 0
995 | Payroll Burden | PR | 291 | 10/10/18 | 10/12/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 294 | 10/10/18 | 10/12/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 10/17/18 | 10/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 435 | 10/17/18 | 10/19/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 10/17/18 | 10/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 10/17/18 | 10/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 446 | 10/17/18 | 10/19/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 447 | 10/17/18 | 10/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 10/17/18 | 10/19/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 456 | 10/17/18 | 10/19/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 10/17/18 | 10/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 10/17/18 | 10/19/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 474 | 10/17/18 | 10/19/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 480 | 10/17/18 | 10/19/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 482 | 10/17/18 | 10/19/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 10/17/18 | 10/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 10/17/18 | 10/19/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 10/17/18 | 10/19/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 553.49 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 25.28 |  | 0 | 0
995 | Payroll Burden | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 715 | 10/24/18 | 10/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 75.84 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 431.08 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 155.67 |  | 0 | 0
995 | Payroll Burden | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 10/31/18 | 11/02/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 438.18 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 12.64 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 328.63 |  | 0 | 0
995 | Payroll Burden | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 8.43 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 10/31/18 | 11/02/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 235.94 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 190.26 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 45 | 10/31/18 | 11/02/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 11/07/18 | 11/09/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 322.87 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 191 | 11/07/18 | 11/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 11/07/18 | 11/09/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 12.64 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 392.05 |  | 0 | 0
995 | Payroll Burden | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 241 | 11/07/18 | 11/09/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 691.86 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 167.64 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 37.25 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 25.28 |  | 0 | 0
995 | Payroll Burden | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 252.8 |  | 0 | 0
995 | Payroll Burden | PR | 443 | 11/14/18 | 11/16/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 11/14/18 | 11/16/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 75.84 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 25.28 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 67.41 |  | 0 | 0
995 | Payroll Burden | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 11/14/18 | 11/16/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 247.47 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 103.78 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -31.27 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 107.77 |  | 0 | 0
995 | Payroll Burden | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 619 | 11/21/18 | 11/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.22 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 292.71 |  | 0 | 0
995 | Payroll Burden | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 50.56 |  | 0 | 0
995 | Payroll Burden | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 14.19 |  | 0 | 0
995 | Payroll Burden | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 143.69 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 63.2 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 539.3 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 28.38 |  | 0 | 0
995 | Payroll Burden | PR | 655 | 11/21/18 | 11/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 620.9 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 83.82 |  | 0 | 0
995 | Payroll Burden | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -39.92 |  | 0 | 0
995 | Payroll Burden | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 828 | 11/28/18 | 11/30/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 488.74 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 11/28/18 | 11/30/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 838 | 11/28/18 | 11/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 243.93 |  | 0 | 0
995 | Payroll Burden | PR | 849 | 11/28/18 | 11/30/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 851 | 11/28/18 | 11/30/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 288.72 |  | 0 | 0
995 | Payroll Burden | PR | 864 | 11/28/18 | 11/30/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 370.77 |  | 0 | 0
995 | Payroll Burden | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 409.79 |  | 0 | 0
995 | Payroll Burden | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 868 | 11/28/18 | 11/30/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 875 | 11/28/18 | 11/30/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 574.33 |  | 0 | 0
995 | Payroll Burden | PR | 876 | 11/28/18 | 11/30/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 878 | 11/28/18 | 11/30/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 387.62 |  | 0 | 0
995 | Payroll Burden | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 12/05/18 | 12/07/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 468.34 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 16.63 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 27.94 |  | 0 | 0
995 | Payroll Burden | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 288 | 12/12/18 | 12/14/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 590.74 |  | 0 | 0
995 | Payroll Burden | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 475.88 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 12/19/18 | 12/21/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 99.34 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 516 | 12/19/18 | 12/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 12/19/18 | 12/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 370.77 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 69.85 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 428.42 |  | 0 | 0
995 | Payroll Burden | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 351.25 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 787.66 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 697 | 12/26/18 | 12/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 334.4 |  | 0 | 0
995 | Payroll Burden | PR | 704 | 12/26/18 | 12/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 707 | 12/26/18 | 12/28/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 732 | 12/26/18 | 12/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 146.36 |  | 0 | 0
995 | Payroll Burden | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 164.1 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 12/26/18 | 12/28/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 183.61 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 01/02/19 | 01/04/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 01/02/19 | 01/04/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 01/02/19 | 01/04/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 01/02/19 | 01/04/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 01/02/19 | 01/04/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 01/02/19 | 01/04/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 223.52 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 01/02/19 | 01/04/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 01/02/19 | 01/04/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 01/02/19 | 01/04/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 01/02/19 | 01/04/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 308.68 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 217 | 01/09/19 | 01/11/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 220 | 01/09/19 | 01/11/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 232 | 01/09/19 | 01/11/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 01/09/19 | 01/11/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 01/09/19 | 01/11/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 256 | 01/09/19 | 01/11/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 466 | 01/16/19 | 01/18/19 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 111.76 |  | 0 | 0
995 | Payroll Burden | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 30.16 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 487 | 01/16/19 | 01/18/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 503 | 01/16/19 | 01/18/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 468.34 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 541.51 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 114.87 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 83.38 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 720 | 01/23/19 | 01/25/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 721 | 01/23/19 | 01/25/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 01/23/19 | 01/25/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 372.54 |  | 0 | 0
995 | Payroll Burden | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 01/23/19 | 01/25/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 149.02 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 749 | 01/23/19 | 01/25/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 752 | 01/23/19 | 01/25/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 443.06 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 01/23/19 | 01/25/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 763 | 01/23/19 | 01/25/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 01/30/19 | 02/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 9 | 01/30/19 | 02/01/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 01/30/19 | 02/01/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 353.91 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 01/30/19 | 02/01/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 01/30/19 | 02/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 525.1 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 49 | 01/30/19 | 02/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 367.22 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 157 | 02/06/19 | 02/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 437.29 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 02/06/19 | 02/08/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 361.9 |  | 0 | 0
995 | Payroll Burden | PR | 167 | 02/06/19 | 02/08/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 181.61 |  | 0 | 0
995 | Payroll Burden | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 177 | 02/06/19 | 02/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 02/06/19 | 02/08/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 361.9 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 102.45 |  | 0 | 0
995 | Payroll Burden | PR | 202 | 02/06/19 | 02/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 492.29 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 02/06/19 | 02/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 306.02 |  | 0 | 0
995 | Payroll Burden | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 319 | 02/13/19 | 02/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 360.12 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 02/13/19 | 02/15/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 329 | 02/13/19 | 02/15/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 195.14 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 339 | 02/13/19 | 02/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 159.66 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 02/13/19 | 02/15/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 331.74 |  | 0 | 0
995 | Payroll Burden | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 354 | 02/13/19 | 02/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 364 | 02/13/19 | 02/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 366 | 02/13/19 | 02/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 285.61 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 02/20/19 | 02/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 745.97 |  | 0 | 0
995 | Payroll Burden | PR | 584 | 02/20/19 | 02/22/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 587 | 02/20/19 | 02/22/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 447.05 |  | 0 | 0
995 | Payroll Burden | PR | 591 | 02/20/19 | 02/22/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 468.34 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 602 | 02/20/19 | 02/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 663.48 |  | 0 | 0
995 | Payroll Burden | PR | 604 | 02/20/19 | 02/22/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 113.43 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 295.37 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 754.84 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 153.01 |  | 0 | 0
995 | Payroll Burden | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 387.62 |  | 0 | 0
995 | Payroll Burden | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 187.6 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 22.62 |  | 0 | 0
995 | Payroll Burden | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 250.8 |  | 0 | 0
995 | Payroll Burden | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 12 | 02/27/19 | 03/01/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 335.29 |  | 0 | 0
995 | Payroll Burden | PR | 16 | 02/27/19 | 03/01/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 458.58 |  | 0 | 0
995 | Payroll Burden | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 172.97 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 24 | 02/27/19 | 03/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 02/27/19 | 03/01/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 723.79 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 02/27/19 | 03/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 114.09 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 195.58 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 556.15 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 147.69 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 213.32 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 54 | 02/27/19 | 03/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 250.13 |  | 0 | 0
995 | Payroll Burden | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 62.53 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 02/27/19 | 03/01/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 90.47 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 250.8 |  | 0 | 0
995 | Payroll Burden | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 246 | 03/06/19 | 03/08/19 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 03/06/19 | 03/08/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 409.79 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 124.4 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 149.68 |  | 0 | 0
995 | Payroll Burden | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 172.97 |  | 0 | 0
995 | Payroll Burden | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 03/06/19 | 03/08/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 03/06/19 | 03/08/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 723.79 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 249.91 |  | 0 | 0
995 | Payroll Burden | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 195.58 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 93.3 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 611.03 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 344.6 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 574.33 |  | 0 | 0
995 | Payroll Burden | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 82.05 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 198.91 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 234.5 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.31 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 38.58 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 411.57 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 102.89 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 195.14 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 195.14 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 321.54 |  | 0 | 0
995 | Payroll Burden | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 03/13/19 | 03/15/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 603.16 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 114.09 |  | 0 | 0
995 | Payroll Burden | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 526.88 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 246.14 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 410.24 |  | 0 | 0
995 | Payroll Burden | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 153.01 |  | 0 | 0
995 | Payroll Burden | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 544 | 03/13/19 | 03/15/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 250.13 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 15.08 |  | 0 | 0
995 | Payroll Burden | PR | 554 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 96.46 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 719 | 03/20/19 | 03/22/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 370.77 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 124.73 |  | 0 | 0
995 | Payroll Burden | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 124.73 |  | 0 | 0
995 | Payroll Burden | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 467.45 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 390.28 |  | 0 | 0
995 | Payroll Burden | PR | 747 | 03/20/19 | 03/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 750 | 03/20/19 | 03/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 656.38 |  | 0 | 0
995 | Payroll Burden | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
995 | Payroll Burden | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 234.5 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 03/20/19 | 03/22/19 | SO71 | Sorto Regalado, Milton J | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 03/20/19 | 03/22/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 129.72 |  | 0 | 0
995 | Payroll Burden | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -32.6 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -86.93 |  | 0 | 0
995 | Payroll Burden | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 115.75 |  | 0 | 0
995 | Payroll Burden | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 77.17 |  | 0 | 0
995 | Payroll Burden | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 370.77 |  | 0 | 0
995 | Payroll Burden | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 939 | 03/27/19 | 03/29/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 943 | 03/27/19 | 03/29/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 648.4 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 32.6 |  | 0 | 0
995 | Payroll Burden | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 146.36 |  | 0 | 0
995 | Payroll Burden | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 233.84 |  | 0 | 0
995 | Payroll Burden | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 393.83 |  | 0 | 0
995 | Payroll Burden | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 153.01 |  | 0 | 0
995 | Payroll Burden | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 367.22 |  | 0 | 0
995 | Payroll Burden | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 250.13 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 198.69 |  | 0 | 0
995 | Payroll Burden | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 15.08 |  | 0 | 0
995 | Payroll Burden | PR | 981 | 03/27/19 | 03/29/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 205.78 |  | 0 | 0
995 | Payroll Burden | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 154.34 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 105 | 04/03/19 | 04/05/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 610.7 |  | 0 | 0
995 | Payroll Burden | PR | 108 | 04/03/19 | 04/05/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 180.5 |  | 0 | 0
995 | Payroll Burden | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 132.61 |  | 0 | 0
995 | Payroll Burden | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.69 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 163.98 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 348 | 04/10/19 | 04/12/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 574.78 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 99.79 |  | 0 | 0
995 | Payroll Burden | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 369 | 04/10/19 | 04/12/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 371 | 04/10/19 | 04/12/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 115.75 |  | 0 | 0
995 | Payroll Burden | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 514.46 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 312.22 |  | 0 | 0
995 | Payroll Burden | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 546 | 04/17/19 | 04/19/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 718.47 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 567 | 04/17/19 | 04/19/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 569 | 04/17/19 | 04/19/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 439.95 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 765 | 04/24/19 | 04/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 702.5 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 04/24/19 | 04/26/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 298.03 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 59.87 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 662.59 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 135.71 |  | 0 | 0
995 | Payroll Burden | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 260.78 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 119.75 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 56.55 |  | 0 | 0
995 | Payroll Burden | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 208 | 05/08/19 | 05/10/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 106.44 |  | 0 | 0
995 | Payroll Burden | PR | 210 | 05/08/19 | 05/10/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 231 | 05/08/19 | 05/10/19 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 19.96 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 390 | 05/15/19 | 05/17/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 49.89 |  | 0 | 0
995 | Payroll Burden | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 418 | 05/15/19 | 05/17/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 614.69 |  | 0 | 0
995 | Payroll Burden | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 50.89 |  | 0 | 0
995 | Payroll Burden | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 239.05 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 05/22/19 | 05/24/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 371.43 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 633 | 05/22/19 | 05/24/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 196.03 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 35.92 |  | 0 | 0
995 | Payroll Burden | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 156.11 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 891 | 05/29/19 | 05/31/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 255.01 |  | 0 | 0
995 | Payroll Burden | PR | 904 | 05/29/19 | 05/31/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 574.78 |  | 0 | 0
995 | Payroll Burden | PR | 907 | 05/29/19 | 05/31/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 248.8 |  | 0 | 0
995 | Payroll Burden | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 212.88 |  | 0 | 0
995 | Payroll Burden | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 941 | 05/29/19 | 05/31/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 278.07 |  | 0 | 0
995 | Payroll Burden | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 178 | 06/05/19 | 06/07/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 11.31 |  | 0 | 0
995 | Payroll Burden | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 184.5 |  | 0 | 0
995 | Payroll Burden | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 243 | 06/05/19 | 06/07/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 474 | 06/12/19 | 06/14/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 638.64 |  | 0 | 0
995 | Payroll Burden | PR | 477 | 06/12/19 | 06/14/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 221.75 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 06/12/19 | 06/14/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 06/12/19 | 06/14/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 835 | 06/26/19 | 06/28/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 243.93 |  | 0 | 0
995 | Payroll Burden | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 67.86 |  | 0 | 0
995 | Payroll Burden | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 54.99 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 07/03/19 | 07/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 35 | 07/03/19 | 07/05/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 542.84 |  | 0 | 0
995 | Payroll Burden | PR | 38 | 07/03/19 | 07/05/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 58 | 07/03/19 | 07/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 07/03/19 | 07/05/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 278.07 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 07/03/19 | 07/05/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 263.44 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 07/03/19 | 07/05/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 24.39 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 304 | 07/10/19 | 07/12/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 307 | 07/10/19 | 07/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 07/10/19 | 07/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 96.24 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 109.99 |  | 0 | 0
995 | Payroll Burden | PR | 344 | 07/10/19 | 07/12/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 345 | 07/10/19 | 07/12/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 07/17/19 | 07/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 426.87 |  | 0 | 0
995 | Payroll Burden | PR | 534 | 07/17/19 | 07/19/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 510.91 |  | 0 | 0
995 | Payroll Burden | PR | 537 | 07/17/19 | 07/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 237.49 |  | 0 | 0
995 | Payroll Burden | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 571 | 07/17/19 | 07/19/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 626 | 07/24/19 | 07/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 60.32 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 658 | 07/24/19 | 07/26/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 325.97 |  | 0 | 0
995 | Payroll Burden | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 180.95 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 463.01 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 07/31/19 | 08/02/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 301.58 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 303 | 08/07/19 | 08/09/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 305 | 08/07/19 | 08/09/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 80.72 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 49.01 |  | 0 | 0
995 | Payroll Burden | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 80.72 |  | 0 | 0
995 | Payroll Burden | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 11.53 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 636 | 08/14/19 | 08/16/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 813 | 08/21/19 | 08/23/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 828 | 08/21/19 | 08/23/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 120.63 |  | 0 | 0
995 | Payroll Burden | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 86.93 |  | 0 | 0
995 | Payroll Burden | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 173.85 |  | 0 | 0
995 | Payroll Burden | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 25 | 09/04/19 | 09/06/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 37 | 09/04/19 | 09/06/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 09/04/19 | 09/06/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 130.39 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 09/04/19 | 09/06/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 09/11/19 | 09/13/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 77.17 |  | 0 | 0
995 | Payroll Burden | PR | 261 | 09/11/19 | 09/13/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 207.56 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 498 | 09/18/19 | 09/20/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 09/18/19 | 09/20/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.22 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 09/18/19 | 09/20/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 34.59 |  | 0 | 0
995 | Payroll Burden | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 654 | 09/25/19 | 09/27/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 30 | 10/02/19 | 10/04/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 10/09/19 | 10/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 12/13/17 | 12/15/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 12/20/17 | 12/22/17 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 656 | 12/20/17 | 12/22/17 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 01/03/18 | 01/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 04/04/18 | 04/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 5.2 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 309 | 04/11/18 | 04/13/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 04/11/18 | 04/13/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.58 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 04/18/18 | 04/20/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 615 | 04/25/18 | 04/27/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 661 | 04/25/18 | 04/27/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 49.42 |  | 0 | 0
998 | Payroll Taxes | PR | 684 | 04/25/18 | 04/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 05/16/18 | 05/18/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 05/23/18 | 05/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 2.6 |  | 0 | 0
998 | Payroll Taxes | PR | 785 | 05/23/18 | 05/25/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 26.01 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 05/30/18 | 06/01/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 134 | 05/30/18 | 06/01/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | -10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 44.22 |  | 0 | 0
998 | Payroll Taxes | PR | 317 | 06/06/18 | 06/08/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 06/06/18 | 06/08/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 42.76 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.91 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 06/06/18 | 06/08/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 06/13/18 | 06/15/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 06/13/18 | 06/15/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 06/13/18 | 06/15/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 06/13/18 | 06/15/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 06/13/18 | 06/15/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 710 | 06/20/18 | 06/22/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 729 | 06/20/18 | 06/22/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 06/20/18 | 06/22/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 06/20/18 | 06/22/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 44.75 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 06/20/18 | 06/22/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 06/20/18 | 06/22/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 06/20/18 | 06/22/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 978 | 06/27/18 | 06/29/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 997 | 06/27/18 | 06/29/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 80.33 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 06/27/18 | 06/29/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 5.16 |  | 0 | 0
998 | Payroll Taxes | PR | 1002 | 06/27/18 | 06/29/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 25.82 |  | 0 | 0
998 | Payroll Taxes | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 1011 | 06/27/18 | 06/29/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 1019 | 06/27/18 | 06/29/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 1020 | 06/27/18 | 06/29/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 07/04/18 | 07/06/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 21 | 07/04/18 | 07/06/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 07/04/18 | 07/06/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/04/18 | 07/06/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 07/04/18 | 07/06/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 07/04/18 | 07/06/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 07/04/18 | 07/06/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 07/04/18 | 07/06/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 07/04/18 | 07/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 07/04/18 | 07/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 07/11/18 | 07/13/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 324 | 07/11/18 | 07/13/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 07/11/18 | 07/13/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 28.76 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 47.12 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 07/11/18 | 07/13/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 4.28 |  | 0 | 0
998 | Payroll Taxes | PR | 346 | 07/11/18 | 07/13/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 356 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 358 | 07/11/18 | 07/13/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 367 | 07/11/18 | 07/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 368 | 07/11/18 | 07/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 374 | 07/11/18 | 07/13/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | -6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 07/18/18 | 07/20/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 457 | 07/18/18 | 07/20/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 07/18/18 | 07/20/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 470 | 07/18/18 | 07/20/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.98 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 07/18/18 | 07/20/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 07/18/18 | 07/20/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 07/18/18 | 07/20/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 499 | 07/18/18 | 07/20/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 07/18/18 | 07/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 07/25/18 | 07/27/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 07/25/18 | 07/27/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 778 | 07/25/18 | 07/27/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 783 | 07/25/18 | 07/27/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 785 | 07/25/18 | 07/27/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 792 | 07/25/18 | 07/27/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 798 | 07/25/18 | 07/27/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 802 | 07/25/18 | 07/27/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 50.72 |  | 0 | 0
998 | Payroll Taxes | PR | 805 | 07/25/18 | 07/27/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 07/25/18 | 07/27/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 83.54 |  | 0 | 0
998 | Payroll Taxes | PR | 813 | 07/25/18 | 07/27/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 815 | 07/25/18 | 07/27/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 58.52 |  | 0 | 0
998 | Payroll Taxes | PR | 826 | 07/25/18 | 07/27/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 07/25/18 | 07/27/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 08/01/18 | 08/03/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 08/01/18 | 08/03/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 08/01/18 | 08/03/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 08/01/18 | 08/03/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 08/01/18 | 08/03/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 08/01/18 | 08/03/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 08/01/18 | 08/03/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 08/01/18 | 08/03/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 08/01/18 | 08/03/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 08/01/18 | 08/03/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 08/01/18 | 08/03/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 99.07 |  | 0 | 0
998 | Payroll Taxes | PR | 53 | 08/01/18 | 08/03/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 54 | 08/01/18 | 08/03/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 08/01/18 | 08/03/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 08/01/18 | 08/03/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 218 | 08/08/18 | 08/10/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 221 | 08/08/18 | 08/10/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 08/08/18 | 08/10/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 232 | 08/08/18 | 08/10/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 50.95 |  | 0 | 0
998 | Payroll Taxes | PR | 233 | 08/08/18 | 08/10/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 08/08/18 | 08/10/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 08/08/18 | 08/10/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 8.99 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 08/08/18 | 08/10/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 08/08/18 | 08/10/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 260 | 08/08/18 | 08/10/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 08/08/18 | 08/10/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 08/08/18 | 08/10/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 08/08/18 | 08/10/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 08/08/18 | 08/10/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 08/08/18 | 08/10/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 08/15/18 | 08/17/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 08/15/18 | 08/17/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 08/15/18 | 08/17/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 08/15/18 | 08/17/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 08/15/18 | 08/17/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 08/15/18 | 08/17/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 08/15/18 | 08/17/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 50.95 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 08/15/18 | 08/17/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 515 | 08/15/18 | 08/17/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 08/15/18 | 08/17/18 | LE17 | Lee, Ha Nul | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 08/15/18 | 08/17/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 08/15/18 | 08/17/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 532 | 08/15/18 | 08/17/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 08/15/18 | 08/17/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 551 | 08/15/18 | 08/17/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 573 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 08/22/18 | 08/24/18 | AG48 | Aguayo Robles, Carlos I | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 748 | 08/22/18 | 08/24/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 751 | 08/22/18 | 08/24/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 08/22/18 | 08/24/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 08/22/18 | 08/24/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 763 | 08/22/18 | 08/24/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 08/22/18 | 08/24/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 08/22/18 | 08/24/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 08/22/18 | 08/24/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 782 | 08/22/18 | 08/24/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 788 | 08/22/18 | 08/24/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 790 | 08/22/18 | 08/24/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 793 | 08/22/18 | 08/24/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 08/22/18 | 08/24/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 822 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 1005 | 08/29/18 | 08/31/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 1011 | 08/29/18 | 08/31/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 1012 | 08/29/18 | 08/31/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 1017 | 08/29/18 | 08/31/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 1018 | 08/29/18 | 08/31/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 1026 | 08/29/18 | 08/31/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 53.7 |  | 0 | 0
998 | Payroll Taxes | PR | 1031 | 08/29/18 | 08/31/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 1032 | 08/29/18 | 08/31/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 1035 | 08/29/18 | 08/31/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 1042 | 08/29/18 | 08/31/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 1044 | 08/29/18 | 08/31/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 104.42 |  | 0 | 0
998 | Payroll Taxes | PR | 1047 | 08/29/18 | 08/31/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 1070 | 08/29/18 | 08/31/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 09/05/18 | 09/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 35.34 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 09/05/18 | 09/07/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 09/05/18 | 09/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 09/05/18 | 09/07/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 57 | 09/05/18 | 09/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 09/05/18 | 09/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 09/05/18 | 09/07/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 37.87 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 09/05/18 | 09/07/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 09/05/18 | 09/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 09/05/18 | 09/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 09/05/18 | 09/07/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 09/05/18 | 09/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 09/05/18 | 09/07/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 09/05/18 | 09/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 86 | 09/05/18 | 09/07/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 09/05/18 | 09/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 91 | 09/05/18 | 09/07/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 105 | 09/05/18 | 09/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 09/12/18 | 09/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 277 | 09/12/18 | 09/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 53.78 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 09/12/18 | 09/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 283 | 09/12/18 | 09/14/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 09/12/18 | 09/14/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 289 | 09/12/18 | 09/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 09/12/18 | 09/14/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 09/12/18 | 09/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 306 | 09/12/18 | 09/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 308 | 09/12/18 | 09/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 09/12/18 | 09/14/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 316 | 09/12/18 | 09/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 318 | 09/12/18 | 09/14/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 09/12/18 | 09/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 09/12/18 | 09/14/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 59.9 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 09/12/18 | 09/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 413 | 09/19/18 | 09/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 09/19/18 | 09/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 09/19/18 | 09/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 09/19/18 | 09/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 09/19/18 | 09/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 09/19/18 | 09/21/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 497 | 09/19/18 | 09/21/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 502 | 09/19/18 | 09/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 09/19/18 | 09/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 09/19/18 | 09/21/18 | GE71 | Gerard, Mitchell J | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 09/19/18 | 09/21/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 09/19/18 | 09/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 09/19/18 | 09/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 09/19/18 | 09/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 09/19/18 | 09/21/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 09/19/18 | 09/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 09/19/18 | 09/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 120.49 |  | 0 | 0
998 | Payroll Taxes | PR | 532 | 09/19/18 | 09/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 09/19/18 | 09/21/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 539 | 09/19/18 | 09/21/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 95.47 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 665 | 09/26/18 | 09/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 8.84 |  | 0 | 0
998 | Payroll Taxes | PR | 672 | 09/26/18 | 09/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 673 | 09/26/18 | 09/28/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 675 | 09/26/18 | 09/28/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 678 | 09/26/18 | 09/28/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 679 | 09/26/18 | 09/28/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 680 | 09/26/18 | 09/28/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 09/26/18 | 09/28/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 682 | 09/26/18 | 09/28/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 09/26/18 | 09/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 688 | 09/26/18 | 09/28/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 696 | 09/26/18 | 09/28/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 09/26/18 | 09/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 704 | 09/26/18 | 09/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 706 | 09/26/18 | 09/28/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 56 |  | 0 | 0
998 | Payroll Taxes | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 712 | 09/26/18 | 09/28/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 714 | 09/26/18 | 09/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 716 | 09/26/18 | 09/28/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 09/26/18 | 09/28/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 54.62 |  | 0 | 0
998 | Payroll Taxes | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 6.27 |  | 0 | 0
998 | Payroll Taxes | PR | 718 | 09/26/18 | 09/28/18 | RE18 | Reed, Reuben H | 0 | 0 | 0 | 0 | 9.41 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 09/26/18 | 09/28/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 09/26/18 | 09/28/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 09/26/18 | 09/28/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 9.64 |  | 0 | 0
998 | Payroll Taxes | PR | 28 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 10/03/18 | 10/05/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 10/03/18 | 10/05/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 39 | 10/03/18 | 10/05/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 10/03/18 | 10/05/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/03/18 | 10/05/18 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 10/03/18 | 10/05/18 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 10/03/18 | 10/05/18 | DE45 | de la Torre, Kevin A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 10/03/18 | 10/05/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 10/03/18 | 10/05/18 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 9.24 |  | 0 | 0
998 | Payroll Taxes | PR | 51 | 10/03/18 | 10/05/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 10/03/18 | 10/05/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 48.2 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 10/03/18 | 10/05/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 12.58 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 10/03/18 | 10/05/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 10/03/18 | 10/05/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 10/03/18 | 10/05/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/03/18 | 10/05/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 78 | 10/03/18 | 10/05/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 10/03/18 | 10/05/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 106.72 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 10/03/18 | 10/05/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 10/03/18 | 10/05/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 88 | 10/03/18 | 10/05/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 89 | 10/03/18 | 10/05/18 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 103 | 10/03/18 | 10/05/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 10/10/18 | 10/12/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 236 | 10/10/18 | 10/12/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 10/10/18 | 10/12/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 10/10/18 | 10/12/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 247 | 10/10/18 | 10/12/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 10/10/18 | 10/12/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 252 | 10/10/18 | 10/12/18 | DI07 | Diaz Moreno, Kevin J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 10/10/18 | 10/12/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 10/10/18 | 10/12/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 10/10/18 | 10/12/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 274 | 10/10/18 | 10/12/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 276 | 10/10/18 | 10/12/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 10/10/18 | 10/12/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 284 | 10/10/18 | 10/12/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 10/10/18 | 10/12/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 41.31 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 10/10/18 | 10/12/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 61.05 |  | 0 | 0
998 | Payroll Taxes | PR | 291 | 10/10/18 | 10/12/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 294 | 10/10/18 | 10/12/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 10/10/18 | 10/12/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 10/17/18 | 10/19/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 435 | 10/17/18 | 10/19/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 10/17/18 | 10/19/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 10/17/18 | 10/19/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 446 | 10/17/18 | 10/19/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 447 | 10/17/18 | 10/19/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 10/17/18 | 10/19/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 456 | 10/17/18 | 10/19/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 10/17/18 | 10/19/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 10/17/18 | 10/19/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 10/17/18 | 10/19/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 474 | 10/17/18 | 10/19/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 480 | 10/17/18 | 10/19/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 482 | 10/17/18 | 10/19/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 10/17/18 | 10/19/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 10/17/18 | 10/19/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 10/17/18 | 10/19/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 10/17/18 | 10/19/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 95.47 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 10/24/18 | 10/25/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 10/24/18 | 10/26/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 703 | 10/24/18 | 10/26/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 704 | 10/24/18 | 10/26/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 708 | 10/24/18 | 10/26/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 4.36 |  | 0 | 0
998 | Payroll Taxes | PR | 711 | 10/24/18 | 10/26/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 714 | 10/24/18 | 10/26/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 715 | 10/24/18 | 10/26/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 722 | 10/24/18 | 10/26/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 13.08 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 10/24/18 | 10/26/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 10/24/18 | 10/26/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 738 | 10/24/18 | 10/26/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 10/24/18 | 10/26/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 10/24/18 | 10/26/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 10/24/18 | 10/26/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 754 | 10/24/18 | 10/26/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 74.36 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 26.85 |  | 0 | 0
998 | Payroll Taxes | PR | 757 | 10/24/18 | 10/26/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 10/24/18 | 10/26/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 1 | 10/31/18 | 11/02/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 4 | 10/31/18 | 11/02/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 10/31/18 | 11/02/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 75.58 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 10/31/18 | 11/02/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 2.18 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 56.69 |  | 0 | 0
998 | Payroll Taxes | PR | 13 | 10/31/18 | 11/02/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 1.45 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 10/31/18 | 11/02/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 17 | 10/31/18 | 11/02/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 10/31/18 | 11/02/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 10/31/18 | 11/02/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 40.7 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 10/31/18 | 11/02/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/31/18 | 11/02/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 43 | 10/31/18 | 11/02/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 45 | 10/31/18 | 11/02/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 10/31/18 | 11/02/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 54 | 10/31/18 | 11/02/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 10/31/18 | 11/02/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 10/31/18 | 11/02/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 11/07/18 | 11/09/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 11/07/18 | 11/09/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 55.69 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 185 | 11/07/18 | 11/09/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 191 | 11/07/18 | 11/09/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 194 | 11/07/18 | 11/09/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 11/07/18 | 11/09/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 203 | 11/07/18 | 11/09/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 2.18 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 11/07/18 | 11/09/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 218 | 11/07/18 | 11/09/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 67.63 |  | 0 | 0
998 | Payroll Taxes | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 221 | 11/07/18 | 11/09/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 11/07/18 | 11/09/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 11/07/18 | 11/09/18 | MO56 | Montenegro, Carlos E | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 11/07/18 | 11/09/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 11/07/18 | 11/09/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 233 | 11/07/18 | 11/09/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 237 | 11/07/18 | 11/09/18 | RI84 | Rivera, Eli P | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 241 | 11/07/18 | 11/09/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 119.34 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 28.92 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 430 | 11/14/18 | 11/16/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 6.43 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 11/14/18 | 11/16/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 11/14/18 | 11/16/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 439 | 11/14/18 | 11/16/18 | CH20 | Chevez, Herson G | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 4.36 |  | 0 | 0
998 | Payroll Taxes | PR | 440 | 11/14/18 | 11/16/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 43.61 |  | 0 | 0
998 | Payroll Taxes | PR | 443 | 11/14/18 | 11/16/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 444 | 11/14/18 | 11/16/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 11/14/18 | 11/16/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 13.08 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 4.36 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 453 | 11/14/18 | 11/16/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 11.63 |  | 0 | 0
998 | Payroll Taxes | PR | 465 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 11/14/18 | 11/16/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 11/14/18 | 11/16/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 11/14/18 | 11/16/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 11/14/18 | 11/16/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 42.69 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 11/14/18 | 11/16/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 481 | 11/14/18 | 11/16/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 17.9 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 11/14/18 | 11/16/18 | RO75 | Ross, Kelli M | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 504 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 11/14/18 | 11/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 18.59 |  | 0 | 0
998 | Payroll Taxes | PR | 616 | 11/21/18 | 11/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 619 | 11/21/18 | 11/21/18 | BA45 | Balderas Ortiz, Ricardo I | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 8.84 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 11/21/18 | 11/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 50.49 |  | 0 | 0
998 | Payroll Taxes | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 8.72 |  | 0 | 0
998 | Payroll Taxes | PR | 626 | 11/21/18 | 11/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 628 | 11/21/18 | 11/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 2.45 |  | 0 | 0
998 | Payroll Taxes | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 629 | 11/21/18 | 11/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 11/21/18 | 11/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.79 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 10.9 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 11/21/18 | 11/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 651 | 11/21/18 | 11/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 652 | 11/21/18 | 11/21/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 93.02 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 11/21/18 | 11/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 4.9 |  | 0 | 0
998 | Payroll Taxes | PR | 655 | 11/21/18 | 11/21/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 662 | 11/21/18 | 11/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 107.1 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 11/21/18 | 11/21/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 14.46 |  | 0 | 0
998 | Payroll Taxes | PR | 665 | 11/21/18 | 11/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | -6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 688 | 11/21/18 | 11/21/18 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 690 | 11/21/18 | 11/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 828 | 11/28/18 | 11/30/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 84.3 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 11/28/18 | 11/30/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 838 | 11/28/18 | 11/30/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 842 | 11/28/18 | 11/30/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 42.08 |  | 0 | 0
998 | Payroll Taxes | PR | 849 | 11/28/18 | 11/30/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 851 | 11/28/18 | 11/30/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 49.8 |  | 0 | 0
998 | Payroll Taxes | PR | 864 | 11/28/18 | 11/30/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 63.95 |  | 0 | 0
998 | Payroll Taxes | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 70.69 |  | 0 | 0
998 | Payroll Taxes | PR | 867 | 11/28/18 | 11/30/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 868 | 11/28/18 | 11/30/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 875 | 11/28/18 | 11/30/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 99.07 |  | 0 | 0
998 | Payroll Taxes | PR | 876 | 11/28/18 | 11/30/18 | PO73 | Portillo Soriano, Walter A | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 878 | 11/28/18 | 11/30/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 66.86 |  | 0 | 0
998 | Payroll Taxes | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 12/05/18 | 12/07/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 12/05/18 | 12/07/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 12/05/18 | 12/07/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 12/05/18 | 12/07/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 12/05/18 | 12/07/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 12/05/18 | 12/07/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 12/05/18 | 12/07/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 79 | 12/05/18 | 12/07/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 80.78 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 2.87 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 12/05/18 | 12/07/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 12/05/18 | 12/07/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 90 | 12/05/18 | 12/07/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 113 | 12/05/18 | 12/07/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 12/12/18 | 12/14/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 272 | 12/12/18 | 12/14/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 4.82 |  | 0 | 0
998 | Payroll Taxes | PR | 275 | 12/12/18 | 12/14/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 279 | 12/12/18 | 12/14/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 12/12/18 | 12/14/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 288 | 12/12/18 | 12/14/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 12/12/18 | 12/14/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 12/12/18 | 12/14/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 12/12/18 | 12/14/18 | LO87 | Lovo, German G | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 101.9 |  | 0 | 0
998 | Payroll Taxes | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 312 | 12/12/18 | 12/14/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 12/12/18 | 12/14/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 12/12/18 | 12/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 82.08 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 12/19/18 | 12/21/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 12/19/18 | 12/21/18 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 17.14 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 12/19/18 | 12/21/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 516 | 12/19/18 | 12/21/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 12/19/18 | 12/21/18 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 63.95 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 12/19/18 | 12/21/18 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 12/19/18 | 12/21/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 12.05 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/19/18 | 12/21/18 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 73.9 |  | 0 | 0
998 | Payroll Taxes | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 541 | 12/19/18 | 12/21/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 12/19/18 | 12/21/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 60.59 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 12/19/18 | 12/21/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 135.86 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 12/19/18 | 12/21/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 12/19/18 | 12/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 697 | 12/26/18 | 12/28/18 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 57.68 |  | 0 | 0
998 | Payroll Taxes | PR | 704 | 12/26/18 | 12/28/18 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 707 | 12/26/18 | 12/28/18 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 12/26/18 | 12/28/18 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 12/26/18 | 12/28/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 732 | 12/26/18 | 12/28/18 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 735 | 12/26/18 | 12/28/18 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 25.25 |  | 0 | 0
998 | Payroll Taxes | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 743 | 12/26/18 | 12/28/18 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 28.31 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 12/26/18 | 12/28/18 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 31.67 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 12/26/18 | 12/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 01/02/19 | 01/04/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 01/02/19 | 01/04/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 01/02/19 | 01/04/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 01/02/19 | 01/04/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 01/02/19 | 01/04/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 01/02/19 | 01/04/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 38.56 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 01/02/19 | 01/04/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 01/02/19 | 01/04/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 01/02/19 | 01/04/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 01/02/19 | 01/04/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 53.24 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 01/09/19 | 01/11/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 217 | 01/09/19 | 01/11/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 220 | 01/09/19 | 01/11/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 224 | 01/09/19 | 01/11/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 01/09/19 | 01/11/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 232 | 01/09/19 | 01/11/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 01/09/19 | 01/11/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 01/09/19 | 01/11/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 256 | 01/09/19 | 01/11/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 01/09/19 | 01/11/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 259 | 01/09/19 | 01/11/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 464 | 01/16/19 | 01/18/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 466 | 01/16/19 | 01/18/19 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 471 | 01/16/19 | 01/18/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 472 | 01/16/19 | 01/18/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 19.28 |  | 0 | 0
998 | Payroll Taxes | PR | 475 | 01/16/19 | 01/18/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 478 | 01/16/19 | 01/18/19 | CR19 | Crespin Portillo, Juan D | 0 | 0 | 0 | 0 | 5.2 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 01/16/19 | 01/18/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 01/16/19 | 01/18/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 487 | 01/16/19 | 01/18/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 500 | 01/16/19 | 01/18/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 503 | 01/16/19 | 01/18/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 80.78 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 93.41 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 01/16/19 | 01/18/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 19.81 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 01/16/19 | 01/18/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 14.38 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 01/16/19 | 01/18/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 543 | 01/16/19 | 01/18/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 713 | 01/23/19 | 01/25/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 720 | 01/23/19 | 01/25/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 721 | 01/23/19 | 01/25/19 | CA07 | Cabrera Morales, Antonio | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 01/23/19 | 01/25/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 64.26 |  | 0 | 0
998 | Payroll Taxes | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 728 | 01/23/19 | 01/25/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 734 | 01/23/19 | 01/25/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 01/23/19 | 01/25/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 25.7 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 01/23/19 | 01/25/19 | HU04 | Hubbard, Dustin R | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 749 | 01/23/19 | 01/25/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 752 | 01/23/19 | 01/25/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 76.42 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 01/23/19 | 01/25/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 01/23/19 | 01/25/19 | QU35 | Quintanilla, Esteban R | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 763 | 01/23/19 | 01/25/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 772 | 01/23/19 | 01/25/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 01/30/19 | 02/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 9 | 01/30/19 | 02/01/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 01/30/19 | 02/01/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 61.05 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 01/30/19 | 02/01/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 01/30/19 | 02/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 01/30/19 | 02/01/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 40 | 01/30/19 | 02/01/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 90.58 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 01/30/19 | 02/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 49 | 01/30/19 | 02/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 63.34 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 157 | 02/06/19 | 02/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 75.43 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 02/06/19 | 02/08/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 62.42 |  | 0 | 0
998 | Payroll Taxes | PR | 167 | 02/06/19 | 02/08/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 31.33 |  | 0 | 0
998 | Payroll Taxes | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 171 | 02/06/19 | 02/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 177 | 02/06/19 | 02/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 02/06/19 | 02/08/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 62.42 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 02/06/19 | 02/08/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 192 | 02/06/19 | 02/08/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 02/06/19 | 02/08/19 | LI49 | Lima Romero, Melvin A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 02/06/19 | 02/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 17.67 |  | 0 | 0
998 | Payroll Taxes | PR | 202 | 02/06/19 | 02/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 84.92 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 02/06/19 | 02/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 52.79 |  | 0 | 0
998 | Payroll Taxes | PR | 206 | 02/06/19 | 02/08/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 02/06/19 | 02/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 02/06/19 | 02/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 319 | 02/13/19 | 02/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 62.12 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 02/13/19 | 02/15/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 329 | 02/13/19 | 02/15/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.66 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 02/13/19 | 02/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 339 | 02/13/19 | 02/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 27.54 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 02/13/19 | 02/15/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 57.22 |  | 0 | 0
998 | Payroll Taxes | PR | 353 | 02/13/19 | 02/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 354 | 02/13/19 | 02/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 364 | 02/13/19 | 02/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 366 | 02/13/19 | 02/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 49.27 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 389 | 02/13/19 | 02/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 02/20/19 | 02/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 128.67 |  | 0 | 0
998 | Payroll Taxes | PR | 584 | 02/20/19 | 02/22/19 | BE54 | Benites Portillo, Marvin E | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 587 | 02/20/19 | 02/22/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 77.11 |  | 0 | 0
998 | Payroll Taxes | PR | 591 | 02/20/19 | 02/22/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 80.78 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 02/20/19 | 02/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 02/20/19 | 02/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 598 | 02/20/19 | 02/22/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 602 | 02/20/19 | 02/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 114.44 |  | 0 | 0
998 | Payroll Taxes | PR | 604 | 02/20/19 | 02/22/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 619 | 02/20/19 | 02/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 19.56 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 50.95 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 02/20/19 | 02/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 130.2 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 26.39 |  | 0 | 0
998 | Payroll Taxes | PR | 625 | 02/20/19 | 02/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 66.86 |  | 0 | 0
998 | Payroll Taxes | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 627 | 02/20/19 | 02/22/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 634 | 02/20/19 | 02/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 32.36 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 3.9 |  | 0 | 0
998 | Payroll Taxes | PR | 638 | 02/20/19 | 02/22/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 641 | 02/20/19 | 02/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 43.26 |  | 0 | 0
998 | Payroll Taxes | PR | 2 | 02/27/19 | 03/01/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 12 | 02/27/19 | 03/01/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 57.83 |  | 0 | 0
998 | Payroll Taxes | PR | 16 | 02/27/19 | 03/01/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 79.1 |  | 0 | 0
998 | Payroll Taxes | PR | 22 | 02/27/19 | 03/01/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 29.84 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 02/27/19 | 03/01/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 24 | 02/27/19 | 03/01/19 | FO55 | Fonseca Teruel, Eduardo | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 02/27/19 | 03/01/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 124.85 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 02/27/19 | 03/01/19 | GO51 | Gomez Reyes, Edith N | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.68 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 02/27/19 | 03/01/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 33.74 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 02/27/19 | 03/01/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 95.93 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 25.47 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 02/27/19 | 03/01/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 36.8 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 52 | 02/27/19 | 03/01/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 54 | 02/27/19 | 03/01/19 | RE91 | Reyes, Maria E | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.15 |  | 0 | 0
998 | Payroll Taxes | PR | 61 | 02/27/19 | 03/01/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 10.79 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 02/27/19 | 03/01/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 15.61 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 02/27/19 | 03/01/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 43.26 |  | 0 | 0
998 | Payroll Taxes | PR | 244 | 03/06/19 | 03/08/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 246 | 03/06/19 | 03/08/19 | AS10 | Ascencio, Jose L | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 03/06/19 | 03/08/19 | CO69 | Cornejo Orellana, Carlos E | 0 | 0 | 0 | 0 | 70.69 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 21.46 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 03/06/19 | 03/08/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 25.82 |  | 0 | 0
998 | Payroll Taxes | PR | 264 | 03/06/19 | 03/08/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 29.84 |  | 0 | 0
998 | Payroll Taxes | PR | 265 | 03/06/19 | 03/08/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 03/06/19 | 03/08/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 03/06/19 | 03/08/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 124.85 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 43.11 |  | 0 | 0
998 | Payroll Taxes | PR | 278 | 03/06/19 | 03/08/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 33.74 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 16.09 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 03/06/19 | 03/08/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 105.4 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 59.44 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 99.07 |  | 0 | 0
998 | Payroll Taxes | PR | 290 | 03/06/19 | 03/08/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 14.15 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 34.31 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 03/06/19 | 03/08/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 300 | 03/06/19 | 03/08/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 40.45 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 301 | 03/06/19 | 03/08/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 1.95 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 03/06/19 | 03/08/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 03/06/19 | 03/08/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 6.66 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 70.99 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 03/13/19 | 03/15/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 17.75 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.66 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 03/13/19 | 03/15/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 33.66 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 03/13/19 | 03/15/19 | CR79 | Cruz Guzman, Joel A | 0 | 0 | 0 | 0 | 55.46 |  | 0 | 0
998 | Payroll Taxes | PR | 509 | 03/13/19 | 03/15/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 03/13/19 | 03/15/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 03/13/19 | 03/15/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 03/13/19 | 03/15/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 03/13/19 | 03/15/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 104.04 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.68 |  | 0 | 0
998 | Payroll Taxes | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 526 | 03/13/19 | 03/15/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 03/13/19 | 03/15/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 90.88 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 42.46 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 03/13/19 | 03/15/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 70.76 |  | 0 | 0
998 | Payroll Taxes | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 26.39 |  | 0 | 0
998 | Payroll Taxes | PR | 539 | 03/13/19 | 03/15/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 544 | 03/13/19 | 03/15/19 | RO06 | Roberts, Lake A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 547 | 03/13/19 | 03/15/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.15 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 03/13/19 | 03/15/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 03/13/19 | 03/15/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 2.6 |  | 0 | 0
998 | Payroll Taxes | PR | 554 | 03/13/19 | 03/15/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 03/13/19 | 03/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 563 | 03/13/19 | 03/15/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 16.64 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 03/20/19 | 03/22/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 719 | 03/20/19 | 03/22/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 63.95 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 03/20/19 | 03/22/19 | DR04 | Draves, Steven W | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 724 | 03/20/19 | 03/22/19 | EI74 | Eisenhauer, Tommy J | 0 | 0 | 0 | 0 | 21.52 |  | 0 | 0
998 | Payroll Taxes | PR | 725 | 03/20/19 | 03/22/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 21.52 |  | 0 | 0
998 | Payroll Taxes | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 726 | 03/20/19 | 03/22/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 731 | 03/20/19 | 03/22/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 80.63 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 03/20/19 | 03/22/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 67.32 |  | 0 | 0
998 | Payroll Taxes | PR | 747 | 03/20/19 | 03/22/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 750 | 03/20/19 | 03/22/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 113.22 |  | 0 | 0
998 | Payroll Taxes | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 13.2 |  | 0 | 0
998 | Payroll Taxes | PR | 752 | 03/20/19 | 03/22/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 760 | 03/20/19 | 03/22/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 40.45 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 03/20/19 | 03/22/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 03/20/19 | 03/22/19 | SO71 | Sorto Regalado, Milton J | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 03/20/19 | 03/22/19 | TA96 | Taylor, Evan R | 0 | 0 | 0 | 0 | 22.38 |  | 0 | 0
998 | Payroll Taxes | PR | 769 | 03/20/19 | 03/22/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 777 | 03/20/19 | 03/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.97 |  | 0 | 0
998 | Payroll Taxes | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 13.31 |  | 0 | 0
998 | Payroll Taxes | PR | 917 | 03/27/19 | 03/29/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 63.95 |  | 0 | 0
998 | Payroll Taxes | PR | 930 | 03/27/19 | 03/29/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 936 | 03/27/19 | 03/29/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 03/27/19 | 03/29/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 939 | 03/27/19 | 03/29/19 | FR04 | Frausto Mendoza, Pedro | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 943 | 03/27/19 | 03/29/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 111.84 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.62 |  | 0 | 0
998 | Payroll Taxes | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 25.25 |  | 0 | 0
998 | Payroll Taxes | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 952 | 03/27/19 | 03/29/19 | JI50 | Jimenez Alvarenga, Gerson M | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 40.33 |  | 0 | 0
998 | Payroll Taxes | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 67.93 |  | 0 | 0
998 | Payroll Taxes | PR | 962 | 03/27/19 | 03/29/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 26.39 |  | 0 | 0
998 | Payroll Taxes | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 63.34 |  | 0 | 0
998 | Payroll Taxes | PR | 964 | 03/27/19 | 03/29/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 972 | 03/27/19 | 03/29/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.15 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 34.27 |  | 0 | 0
998 | Payroll Taxes | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 978 | 03/27/19 | 03/29/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 2.6 |  | 0 | 0
998 | Payroll Taxes | PR | 981 | 03/27/19 | 03/29/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 990 | 03/27/19 | 03/29/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 35.5 |  | 0 | 0
998 | Payroll Taxes | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 78 | 04/03/19 | 04/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.62 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 04/03/19 | 04/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 04/03/19 | 04/05/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 105 | 04/03/19 | 04/05/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 105.34 |  | 0 | 0
998 | Payroll Taxes | PR | 108 | 04/03/19 | 04/05/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 31.14 |  | 0 | 0
998 | Payroll Taxes | PR | 125 | 04/03/19 | 04/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 22.87 |  | 0 | 0
998 | Payroll Taxes | PR | 127 | 04/03/19 | 04/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.19 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 28.29 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 04/10/19 | 04/12/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 04/10/19 | 04/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 343 | 04/10/19 | 04/12/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 348 | 04/10/19 | 04/12/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 99.14 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 351 | 04/10/19 | 04/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 17.21 |  | 0 | 0
998 | Payroll Taxes | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 369 | 04/10/19 | 04/12/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 371 | 04/10/19 | 04/12/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 397 | 04/10/19 | 04/12/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 398 | 04/10/19 | 04/12/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.97 |  | 0 | 0
998 | Payroll Taxes | PR | 519 | 04/17/19 | 04/19/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 53.86 |  | 0 | 0
998 | Payroll Taxes | PR | 533 | 04/17/19 | 04/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 540 | 04/17/19 | 04/19/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 546 | 04/17/19 | 04/19/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 123.93 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 04/17/19 | 04/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 567 | 04/17/19 | 04/19/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 569 | 04/17/19 | 04/19/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 13.2 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 04/17/19 | 04/19/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 75.89 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 04/24/19 | 04/26/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 04/24/19 | 04/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 759 | 04/24/19 | 04/26/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 765 | 04/24/19 | 04/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 121.18 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 768 | 04/24/19 | 04/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 04/24/19 | 04/26/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 788 | 04/24/19 | 04/26/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 51.41 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 05/01/19 | 05/03/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 20 | 05/01/19 | 05/03/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 05/01/19 | 05/03/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 10.33 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 05/01/19 | 05/03/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 114.29 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 23.41 |  | 0 | 0
998 | Payroll Taxes | PR | 36 | 05/01/19 | 05/03/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 44.98 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 05/01/19 | 05/03/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 159 | 05/08/19 | 05/10/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 173 | 05/08/19 | 05/10/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 180 | 05/08/19 | 05/10/19 | ES09 | Escalante Escobar, Boanerge | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 20.66 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 05/08/19 | 05/10/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 9.75 |  | 0 | 0
998 | Payroll Taxes | PR | 189 | 05/08/19 | 05/10/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 195 | 05/08/19 | 05/10/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 208 | 05/08/19 | 05/10/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 210 | 05/08/19 | 05/10/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 231 | 05/08/19 | 05/10/19 | WA35 | Waites, Thaddeus Z | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 390 | 05/15/19 | 05/17/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 8.61 |  | 0 | 0
998 | Payroll Taxes | PR | 405 | 05/15/19 | 05/17/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 418 | 05/15/19 | 05/17/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 106.03 |  | 0 | 0
998 | Payroll Taxes | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 8.78 |  | 0 | 0
998 | Payroll Taxes | PR | 421 | 05/15/19 | 05/17/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 41.23 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 05/15/19 | 05/17/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 603 | 05/22/19 | 05/24/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 05/22/19 | 05/24/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 64.07 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 630 | 05/22/19 | 05/24/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 633 | 05/22/19 | 05/24/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 33.81 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 05/22/19 | 05/24/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 652 | 05/22/19 | 05/24/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 05/22/19 | 05/24/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 6.2 |  | 0 | 0
998 | Payroll Taxes | PR | 671 | 05/22/19 | 05/24/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 681 | 05/22/19 | 05/24/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 876 | 05/29/19 | 05/31/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 26.93 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 891 | 05/29/19 | 05/31/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 43.99 |  | 0 | 0
998 | Payroll Taxes | PR | 904 | 05/29/19 | 05/31/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 99.14 |  | 0 | 0
998 | Payroll Taxes | PR | 907 | 05/29/19 | 05/31/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 42.92 |  | 0 | 0
998 | Payroll Taxes | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 36.72 |  | 0 | 0
998 | Payroll Taxes | PR | 926 | 05/29/19 | 05/31/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 941 | 05/29/19 | 05/31/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 47.97 |  | 0 | 0
998 | Payroll Taxes | PR | 944 | 05/29/19 | 05/31/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 953 | 05/29/19 | 05/31/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 178 | 06/05/19 | 06/07/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 193 | 06/05/19 | 06/07/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 206 | 06/05/19 | 06/07/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 1.95 |  | 0 | 0
998 | Payroll Taxes | PR | 209 | 06/05/19 | 06/07/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 06/05/19 | 06/07/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 06/05/19 | 06/07/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 31.82 |  | 0 | 0
998 | Payroll Taxes | PR | 229 | 06/05/19 | 06/07/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 243 | 06/05/19 | 06/07/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 255 | 06/05/19 | 06/07/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 06/12/19 | 06/14/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 474 | 06/12/19 | 06/14/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 110.16 |  | 0 | 0
998 | Payroll Taxes | PR | 477 | 06/12/19 | 06/14/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 38.25 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 06/12/19 | 06/14/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 06/12/19 | 06/14/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 06/12/19 | 06/14/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 523 | 06/12/19 | 06/14/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 06/12/19 | 06/14/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 633 | 06/19/19 | 06/21/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 06/19/19 | 06/21/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 06/19/19 | 06/21/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 06/19/19 | 06/21/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 686 | 06/19/19 | 06/21/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 693 | 06/19/19 | 06/21/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 694 | 06/19/19 | 06/21/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 835 | 06/26/19 | 06/28/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 42.08 |  | 0 | 0
998 | Payroll Taxes | PR | 851 | 06/26/19 | 06/28/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 866 | 06/26/19 | 06/28/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 11.7 |  | 0 | 0
998 | Payroll Taxes | PR | 872 | 06/26/19 | 06/28/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 874 | 06/26/19 | 06/28/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 9.49 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 07/03/19 | 07/05/19 | AM03 | Amaya Gonzalez, Edilberto A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 23 | 07/03/19 | 07/05/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 35 | 07/03/19 | 07/05/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 93.64 |  | 0 | 0
998 | Payroll Taxes | PR | 38 | 07/03/19 | 07/05/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 56 | 07/03/19 | 07/05/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 58 | 07/03/19 | 07/05/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 07/03/19 | 07/05/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 47.97 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 07/03/19 | 07/05/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 45.44 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 07/03/19 | 07/05/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 82 | 07/03/19 | 07/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 4.21 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 292 | 07/10/19 | 07/12/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 304 | 07/10/19 | 07/12/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 307 | 07/10/19 | 07/12/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 07/10/19 | 07/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 16.6 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 07/10/19 | 07/12/19 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 18.97 |  | 0 | 0
998 | Payroll Taxes | PR | 344 | 07/10/19 | 07/12/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 345 | 07/10/19 | 07/12/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 07/17/19 | 07/19/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 73.63 |  | 0 | 0
998 | Payroll Taxes | PR | 534 | 07/17/19 | 07/19/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 88.13 |  | 0 | 0
998 | Payroll Taxes | PR | 537 | 07/17/19 | 07/19/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 40.97 |  | 0 | 0
998 | Payroll Taxes | PR | 567 | 07/17/19 | 07/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 571 | 07/17/19 | 07/19/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 574 | 07/17/19 | 07/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 575 | 07/17/19 | 07/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 626 | 07/24/19 | 07/26/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 637 | 07/24/19 | 07/26/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 640 | 07/24/19 | 07/26/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 10.4 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 07/24/19 | 07/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 658 | 07/24/19 | 07/26/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 670 | 07/24/19 | 07/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 56.23 |  | 0 | 0
998 | Payroll Taxes | PR | 674 | 07/24/19 | 07/26/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 07/24/19 | 07/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 678 | 07/24/19 | 07/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 31.21 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 07/24/19 | 07/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 18 | 07/31/19 | 08/02/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 29 | 07/31/19 | 08/02/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 79.87 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 07/31/19 | 08/02/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 52.02 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 07/31/19 | 08/02/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 07/31/19 | 08/02/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 270 | 08/07/19 | 08/09/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 08/07/19 | 08/09/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 285 | 08/07/19 | 08/09/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 303 | 08/07/19 | 08/09/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 305 | 08/07/19 | 08/09/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 13.92 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 08/07/19 | 08/09/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 328 | 08/07/19 | 08/09/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 08/14/19 | 08/16/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 589 | 08/14/19 | 08/16/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 592 | 08/14/19 | 08/16/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 8.45 |  | 0 | 0
998 | Payroll Taxes | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 598 | 08/14/19 | 08/16/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 610 | 08/14/19 | 08/16/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 13.92 |  | 0 | 0
998 | Payroll Taxes | PR | 612 | 08/14/19 | 08/16/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 1.99 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 08/14/19 | 08/16/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 08/14/19 | 08/16/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 636 | 08/14/19 | 08/16/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 813 | 08/21/19 | 08/23/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 825 | 08/21/19 | 08/23/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 828 | 08/21/19 | 08/23/19 | GU17 | Guerrero, Ali A | 0 | 0 | 0 | 0 | 20.81 |  | 0 | 0
998 | Payroll Taxes | PR | 858 | 08/21/19 | 08/23/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 14.99 |  | 0 | 0
998 | Payroll Taxes | PR | 1049 | 08/28/19 | 08/30/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 29.99 |  | 0 | 0
998 | Payroll Taxes | PR | 1064 | 08/28/19 | 08/30/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 25 | 09/04/19 | 09/06/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 37 | 09/04/19 | 09/06/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 09/04/19 | 09/06/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 09/04/19 | 09/06/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 22.49 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 09/04/19 | 09/06/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 09/11/19 | 09/13/19 | CR77 | Cruz Gonzalez, Julio C | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 251 | 09/11/19 | 09/13/19 | CR87 | Cruz Reyes, Jose | 0 | 0 | 0 | 0 | 13.31 |  | 0 | 0
998 | Payroll Taxes | PR | 261 | 09/11/19 | 09/13/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 35.8 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 09/11/19 | 09/13/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 498 | 09/18/19 | 09/20/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 09/18/19 | 09/20/19 | PA11 | Paco Leyva, Orlando | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 09/18/19 | 09/20/19 | RA55 | Ramos Herrera, Franklin J | 0 | 0 | 0 | 0 | 5.97 |  | 0 | 0
998 | Payroll Taxes | PR | 531 | 09/18/19 | 09/20/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 654 | 09/25/19 | 09/27/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 30 | 10/02/19 | 10/04/19 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 41 | 10/02/19 | 10/04/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 10/09/19 | 10/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
999 | Sales | AR | 682 | 06/20/18 | 06/20/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -146180 | 037121 | 0 | -7309
999 | Sales | AR | 531 | 07/20/18 | 07/20/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -228225 | 037143 | 0 | -11411.25
999 | Sales | AR | 598 | 08/20/18 | 08/20/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -367760 | 037168 | 0 | -18388
999 | Sales | AR | 446 | 09/19/18 | 09/19/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -530315 | 037177 | 0 | -26515.75
999 | Sales | AR | 513 | 10/19/18 | 10/19/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -478250 | 037199 | 0 | -23912.5
999 | Sales | AR | 535 | 11/16/18 | 11/16/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -395610 | 037241 | 0 | -19780.5
999 | Sales | AR | 195 | 12/12/18 | 12/12/18 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -188555 | 037248 | 0 | -9427.75
999 | Sales | AR | 561 | 01/18/19 | 01/18/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -264675 | 037279 | 0 | -13233.75
999 | Sales | AR | 560 | 02/20/19 | 02/20/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -63040 | 037284 | 0 | -3152
999 | Sales | AR | 676 | 03/20/19 | 03/20/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -92555 | 037297 | 0 | -4627.75
999 | Sales | AR | 614 | 04/19/19 | 04/19/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -49150 | 037330 | 0 | -2457.5
999 | Sales | AR | 518 | 05/20/19 | 05/20/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -80009 | 037351 | 0 | -4000.45
999 | Sales | AR | 600 | 06/19/19 | 06/19/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -67271 | 037356 | 0 | -3363.55
999 | Sales | AR | 608 | 07/19/19 | 07/19/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -46170 | 037383 | 0 | -2308.5
999 | Sales | AR | 761 | 08/20/19 | 08/15/19 | 2049EP | Exxel Pacific, Inc. $Reserve Lynnwood2 |  |  |  |  | -2015 | 037397 | 0 | -100.75

## Crew Roster
CREW ROSTER — 58 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Aguayo Robles, Carlos I | 72 | 0 | 0 | 640 | 0 | 8.8889
APPRENTICE/HELPER | Diaz Moreno, Kevin J | 252 | 0 | 0 | 4032 | 0 | 16
APPRENTICE/HELPER | de la Torre, Kevin A | 504 | 0 | 0 | 8064 | 0 | 16
APPRENTICE/HELPER | Cabrera Morales, Antonio | 64 | 8 | 0 | 1024 | 192 | 16
APPRENTICE/HELPER | Sorto Regalado, Milton J | 24 | 0 | 0 | 384 | 0 | 16
APPRENTICE/HELPER | Crespin Portillo, Juan D | 230 | 30 | 0 | 3692 | 726 | 16.0522
APPRENTICE/HELPER | Vazquez Popoca, Jose N | 117.5 | 16 | 0 | 1920 | 384 | 16.3404
APPRENTICE/HELPER | Guerrero, Ali A | 617.5 | 34.5 | 0 | 10410 | 867.75 | 16.8583
APPRENTICE/HELPER | Lee, Ha Nul | 191 | 0 | 0 | 3247 | 0 | 17
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 133.5 | 50.5 | 0 | 2371 | 1260 | 17.7603
APPRENTICE/HELPER | Gutierrez Salas, Jose | 415.5 | 4 | 0 | 7479 | 108 | 18
APPRENTICE/HELPER | Chevez, Herson G | 8 | 2 | 0 | 144 | 54 | 18
APPRENTICE/HELPER | Reyes, Maria E | 16 | 10 | 0 | 288 | 270 | 18
APPRENTICE/HELPER | Fonseca Teruel, Eduardo | 8 | 10 | 0 | 144 | 270 | 18
APPRENTICE/HELPER | Roberts, Lake A | 8 | 0 | 0 | 144 | 0 | 18
APPRENTICE/HELPER | Portillo Soriano, Walter A | 142 | 20 | 0 | 2632 | 540 | 18.5352
APPRENTICE/HELPER | Stahlschmidt, John P | 242 | 23 | 0 | 4550 | 586.5 | 18.8017
APPRENTICE/HELPER | Frausto Mendoza, Pedro | 930 | 37 | 0 | 17785 | 1093.5 | 19.1237
APPRENTICE/HELPER | Escalante Escobar, Boanerge | 1610 | 122 | 0 | 31024 | 3576 | 19.2696
APPRENTICE/HELPER | Cornejo Orellana, Carlos E | 1142.5 | 19 | 0 | 22690.5 | 571.5 | 19.8604
JOURNEYMAN | Hernandez Gonzalez, Osbaldo | 32 | 0 | 0 | 640 | 0 | 20
JOURNEYMAN | Jimenez Alvarenga, Gerson M | 1172 | 91 | 0 | 24376 | 2895 | 20.7986
JOURNEYMAN | Ramos Herrera, Franklin J | 1282 | 137 | 0 | 28594 | 4642.5 | 22.3042
JOURNEYMAN | Cruz Gonzalez, Julio C | 1782 | 93.5 | 0 | 40007 | 3097.5 | 22.4506
JOURNEYMAN | Benites Portillo, Marvin E | 960 | 51 | 0 | 22026 | 1749 | 22.9438
JOURNEYMAN | Gomez Reyes, Edith N | 18 | 8 | 0 | 414 | 276 | 23
JOURNEYMAN | Hubbard, Dustin R | 2 | 0 | 0 | 46 | 0 | 23
JOURNEYMAN | Cruz Guzman, Joel A | 85 | 0 | 0 | 2013 | 0 | 23.6824
JOURNEYMAN | Silva Morales, Jair J | 341 | 4 | 0 | 8145 | 144 | 23.8856
JOURNEYMAN | Lovo, German G | 297.5 | 11 | 0 | 7167 | 403.5 | 24.0908
JOURNEYMAN | Cruz Reyes, Jose | 62 | 0 | 0 | 1518 | 0 | 24.4839
JOURNEYMAN | Eliassen, Cory H | 12 | 42.5 | 0 | 300 | 1593.75 | 25
JOURNEYMAN | Eisenhauer, Tommy J | 6 | 13 | 0 | 150 | 477 | 25
JOURNEYMAN | Taylor, Evan R | 8 | 15.5 | 0 | 208 | 604.5 | 26
JOURNEYMAN | Ascencio, Jose L | 172 | 19 | 0 | 4488 | 780 | 26.093
JOURNEYMAN | Rivera, Eli P | 265 | 10 | 0 | 7155 | 405 | 27
JOURNEYMAN | Kinssies, Jr, John E | 73.5 | 0 | 0 | 2006 | 0 | 27.2925
JOURNEYMAN | Balderas Ortiz, Ricardo I | 153 | 18 | 0 | 4279 | 756 | 27.9673
JOURNEYMAN | Montenegro, Carlos E | 689 | 2 | 0 | 19292 | 84 | 28
JOURNEYMAN | Amaya Gonzalez, Edilberto A | 1320 | 139.5 | 0 | 38008 | 5987.25 | 28.7939
JOURNEYMAN | Castro Hernandez, Jose A | 32 | 0 | 0 | 1024 | 0 | 32
JOURNEYMAN | Gerard, Mitchell J | 4.5 | 0 | 0 | 144 | 0 | 32
JOURNEYMAN | Lima Romero, Melvin A | 848 | 54 | 0 | 27480 | 2619 | 32.4057
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 122 | 9 | 0 | 3961 | 432 | 32.4672
JOURNEYMAN | McCabe, Thomas C | 146.5 | 12.25 | 0 | 4834.5 | 606.38 | 33
JOURNEYMAN | Gerard, Jordan E | 958.5 | 13.5 | 0 | 33825 | 729 | 35.2895
JOURNEYMAN | Paco Leyva, Orlando | 1788.5 | 127.5 | 0 | 64207 | 7010.25 | 35.8999
LEAD/SUPERVISOR | Ross, Kelli M | 328 | 18 | 0 | 12792 | 1053 | 39
LEAD/SUPERVISOR | Reed, Reuben H | 2 | 2 | 0 | 82 | 123 | 41
LEAD/SUPERVISOR | Quintanilla, Esteban R | 236.5 | 1 | 0 | 10450.5 | 67.5 | 44.1882
LEAD/SUPERVISOR | Waites, Thaddeus Z | 1 | 0 | 0 | 45 | 0 | 45
LEAD/SUPERVISOR | Sanders, Allen O | 108 | 49 | 0 | 5004 | 3484.5 | 46.3333
LEAD/SUPERVISOR | Hubbard, Robert W | 160.5 | 29 | 0 | 7473.5 | 1837.5 | 46.5639
LEAD/SUPERVISOR | Barnhart, Joseph N | 2 | 0 | 0 | 100 | 0 | 50
LEAD/SUPERVISOR | Gerard, Jeffrey S | 156.5 | 0 | 0 | 7915 | 0 | 50.5751
LEAD/SUPERVISOR | Donelson, Richard T | 86 | 0 | 0 | 5325 | 0 | 61.9186
OT-ONLY | Draves, Steven W | 0 | 15.5 | 0 | 0 | 558 | — (no reg hours)
OT-ONLY | Mendoza Morales, Jesus A | 0 | 7.5 | 0 | 0 | 270 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2049
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 20 | 6727.5 | 386 | 133163.75 | 17.1245
JOURNEYMAN | 27 | 12632 | 871.25 | 381599.13 | 26.8463
LEAD/SUPERVISOR | 9 | 1080.5 | 99 | 55752.5 | 47.1754
OT-ONLY | 2 | 0 | 23 | 828 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 16.2
p25 | 18
p50 | 23.78
p75 | 32.1
p90 | 44.59
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 25.3502 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 39.8017 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 53.4181 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2049
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 21,819.25 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $137.48 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $26.05 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 5.28x | Throughput ÷ unit cost — productivity signal
Units (residential) | 295 | Exxel Lynnwood Reserve Rebuild Apartments scope doc: 279 Type B + 16 Type A ADA
Fixtures (estimate) | 1855 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 22 | start_date → end_date from GDrive enrichment
Hours per Unit | 73.96 | total_labor_hours ÷ units
Hours per Fixture | 11.76 | total_labor_hours ÷ fixtures
Revenue per Unit | $10,169 | revenue ÷ units
Profit per Unit | $4,975 | net_profit ÷ units
Hours per Month | 992 | total_labor_hours ÷ duration_months
Revenue per Month | $136,354 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 17 VENDORS ($520,746 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Rosen Supply Kirkland | 177659.83 | 183 | 970.8187 | 34.12% | 0 | 0
2 | Consolidated Supply Co. | 125346.97 | 63 | 1989.6344 | 24.07% | 0 | 0
3 | Keller Supply Company | 103120.85 | 45 | 2291.5744 | 19.8% | 0 | 0
4 | Mechanical Sales, Inc. | 49315.84 | 2 | 24657.92 | 9.47% | 0 | 0
5 | Ferguson Enterprises, Inc. #3007 | 31908.72 | 42 | 759.7314 | 6.128% | 0 | 0
6 | Mechanical Firestop Services, LLC | 16675 | 2 | 8337.5 | 3.202% | 0 | 0
7 | Mechanical Resource Services, Inc. | 4187.5 | 1 | 4187.5 | 0.8041% | 0 | 0
8 | California Hydronics Corp | 3875 | 3 | 1291.6667 | 0.7441% | 0 | 0
9 | Rosen Supply Company, Inc. $Reserve | 3078.97 | 7 | 439.8529 | 0.5913% | 0 | 0
10 | Ahern Rentals | 2978.42 | 7 | 425.4886 | 0.572% | 0 | 0
11 | Scan2Core, Inc. | 984 | 1 | 984 | 0.189% | 0 | 0
12 | Capital One Credit Card | 531.75 | 8 | 66.4688 | 0.1021% | 0 | 0
13 | Manor Hardware & Construction Supply | 451.36 | 4 | 112.84 | 0.08668% | 0 | 0
14 | A.R. Brown Backflow Testing | 265 | 3 | 88.3333 | 0.05089% | 0 | 0
15 | ACME Corp | 169.87 | 2 | 84.935 | 0.03262% | 0 | 0
16 | Franklin Engineering | 103 | 1 | 103 | 0.01978% | 0 | 0
17 | Sunbelt Rentals, Inc. | 93.5 | 1 | 93.5 | 0.01796% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2049
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
12 |  | Largest rebuild-phase CO (scope addition June 2018) | 61320 | Executed 2018-06-18 | Y
13 |  | Scope addition August 2018 | 20910 | Executed 2018-08-07 | Y
14 |  | Scope addition Dec 2018 | 3950 | Executed 2018-12-11 | Y
15 |  | Minor scope addition (pay app 10 reflected co15) | 1130 | Executed 2019-02-25 | Y
16 |  | Minor scope addition | 2550 | Executed 2019-03-01 | Y
17 |  | CO#17 — city water meter bypass with locking valve + RPBP (per job ticket note) | 2780 | Executed 2019-03-08 | Y
18 |  | Scope addition May 2019 (pay app 12 reflected co18) | 1289 | Executed 2019-05-16 | Y
19 |  | Scope addition June 2019 (pay app 13 reflected co19) | 4871 | Executed 2019-06-10 | Y
20 |  | Closeout scope adjustment (final) | 2015 | Executed 2019-08-16 | Y
Executed subtotal |  |  | 100815
Budget-transfer total (incl. extras) |  |  | 100815
JDR-implied CO (revenue − original contract) |  |  | 100815
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
Lynnwood Reserve Outstanding COR's | Summary log of pending CORs
OWP COR — Service work from 12-6-19 | Post-closeout service work request (Dec 2019)

## Project Team
PROJECT TEAM — 2049
Primary contacts extracted from Exxel Lynnwood Reserve Rebuild Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | TBD — Exxel (CMA architect of record) | TBD | TBD
GC Superintendent | Brett (per Brett Reserve folder) | TBD | TBD
OWP Signatory | Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract) | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18')
Owner | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity)
Inspecting Authority | City of Lynnwood

## Document Pipeline
DOCUMENT PIPELINE — 2049
Quantitative document counts from the Exxel Lynnwood Reserve Rebuild Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 9 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 2 | Change Orders/COR_s/
Budget transfer entries | 9 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 10 | ASI-RFI/
Submittals | 7 | Submittals/ (PDF count)
POs — placed | 13 | PO_s/1 Placed/
POs — scheduled | 81 | PO_s/2 Scheduled/
POs — completed | 179 | PO_s/3 Completed/
POs — total | 273 | PO_s/ (all three subfolders)
Vendor invoices | 362 | Invoices/
Lien releases | 4 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 2 | Permits/ (Seattle DCI plumbing + gas + backflow permits)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for Exxel Lynnwood Reserve Rebuild)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2049
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 868442.74 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 520745.58 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 142994.21 | SUM(line_items where source=GL)
direct_cost | 1532182.53 | PR + AP + GL
net_profit | 1467597.47 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.2895 | PR / abs(revenue)
ap_pct_of_revenue | 0.17359 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.51077 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 21819.25 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 39.8017 | PR / labor hours
fully_loaded_wage | 53.4181 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 25.3502 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 58 | COUNT DISTINCT(name) source=PR
burden_total | 297099.36 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $16.20 ¦ $18.00 ¦ $23.78 ¦ $32.10 ¦ $44.59 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 618442.18 | SUM(actual) codes 2xx
material_budget_total | 691822 | SUM(current_budget) codes 2xx
material_codes_tracked | 9 | COUNT material codes
material_codes_over_budget | 2 | COUNT where plus_minus > 0
material_codes_under_budget | 7 | COUNT where plus_minus ≤ 0
largest_material_overrun | 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404) | Material code with largest +plus_minus
largest_material_savings | 211 Garage Material: $3,799 vs $63,600 budget ($-59,801) | Material code with largest −plus_minus
material_vendor_count | 17 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Rosen Supply Kirkland: $177,660 (34% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 5 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 22 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404) | Phase with largest +plus_minus
largest_savings | 995 Payroll Burden: $253,391 vs $387,566 budget ($-134,175) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 1532182.53 | SUM(actual) expense codes
total_budget | 2050648.54 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7472 | JTD / budget
total_over_under_budget | 518466.01 | budget − JTD
labor_unit_cost_per_hr | 26.0527 | Labor JTD / labor hours
revenue_per_labor_hour | 137.4832 | abs(revenue) / labor hours
material_price_variance | 73379.82 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2049
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 48.9% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | GREEN | 5/27 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $73,380 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $137.48 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $149,989 | Monitor for collection
Top vendor concentration | GREEN | 34.1% (Rosen Supply Kirkland) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2049
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $2,999,780, net profit $1,467,597 at 48.9% margin.
02 | Parsed 4,418 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 58 distinct PR-booked workers over 21,819 labor hours ($39.80/hr PR-src, $53.42/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404).
05 | Largest phase savings: 995 Payroll Burden: $253,391 vs $387,566 budget ($-134,175).
06 | Material spend $618,442 vs budget $691,822 ($73,380 favorable).
07 | Top AP vendor: Rosen Supply Kirkland: $177,660 (34% of AP); 17 total AP vendors.
08 | Retainage outstanding: $149,989.
09 | 5 of 27 expense phases over budget ($518,466 net vs budget).
10 | Revenue per labor hour $137.48, labor unit cost $26.05 (ratio 5.28x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 28/28 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 3977.5 | 3977.5 | 0 | ✓
101 | Takeoff & Purchase Labor | 9262.5 | 9262.5 | 0 | ✓
110 | Underground Labor | 12882 | 12882 | 0 | ✓
111 | Garage Labor | 17823 | 17823 | 0 | ✓
120 | Roughin Labor | 361459.35 | 361459.35 | 0 | ✓
130 | Finish Labor | 83036.25 | 83036.25 | 0 | ✓
140 | Gas Labor | 11964.5 | 11964.5 | 0 | ✓
141 | Water Main/Insulation Lab | 55727.75 | 55727.75 | 0 | ✓
142 | Mech Room Labor | 11736.7 | 11736.7 | 0 | ✓
143 | Condensation Drains Labor | 530 | 530 | 0 | ✓
150 | Warranty Labor | 50 | 50 | 0 | ✓
210 | Underground Material | 3633.46 | 3633.46 | 0 | ✓
211 | Garage Material | 3799.24 | 3799.24 | 0 | ✓
212 | Canout Material | 74.33 | 74.33 | 0 | ✓
220 | Roughin Material | 140166.18 | 140166.18 | 0 | ✓
230 | Finish Material | 335404.06 | 335404.06 | 0 | ✓
240 | Gas Material | 11428.68 | 11428.68 | 0 | ✓
241 | Water Main/Insulation Mat | 96552.88 | 96552.88 | 0 | ✓
242 | Mech Room Material | 27383.35 | 27383.35 | 0 | ✓
243 | Condensation Drains Mat | 0 | 0 | 0 | ✓
600 | Subcontractor | 22111.5 | 22111.5 | 0 | ✓
601 | Engineering/Plans | 103 | 103 | 0 | ✓
602 | Rental Equipment | 3071.92 | 3071.92 | 0 | ✓
603 | Permits & Licenses | 20155.02 | 20155.02 | 0 | ✓
607 | Other Expenses | 2750 | 2750 | 0 | ✓
995 | Payroll Burden | 253391.18 | 253391.18 | 0 | ✓
998 | Payroll Taxes | 43708.18 | 43708.18 | 0 | ✓
999 | Sales | -2999780 | -2999780 | 0 | ✓
RESULT: 28/28 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2049
Worked example of the Reconciliation Protocol running against Job 2049 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $2,050,649; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $39.80/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $868,442.74 ÷ 21,819.25 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$16.20 ¦ p25=$18.00 ¦ p50=$23.78 ¦ p75=$32.10 ¦ p90=$44.59 (58 workers) | straight_time_rate $25.35 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $26.05/hr ¦ revenue $137.48/hr ¦ ratio 5.28x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2049 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 28/28 codes tie to PDF to the cent | PR $868,442.74 + AP $520,745.58 + GL $142,994.21 = $1,532,182.53 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2049
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2049 | JDR cover page
job_name | Job Name | GRE Greenlake | JDR cover page
general_contractor | General Contractor | GRE | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 4418 | Length of line_items[]
cost_code_count | Cost Code Count | 28 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -2999780 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 2999780 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 1532182.53 | Sage job_totals_expenses
job_totals_net | Net | -1467597.47 | Sage job_totals_net
job_totals_retainage | Retainage | -149989 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 868442.74 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 520745.58 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 142994.21 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -2999780 | SUM(line_items source=AR)
direct_cost | Direct Cost | 1532182.53 | PR + AP + GL
net_profit | Net Profit | 1467597.47 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 48.92% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 568449.55 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 618442.18 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 48191.44 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 297099.36 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 21819.25 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 58 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 25.3502 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 39.8017 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 53.4181 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 297099.36 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 16.2 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 18 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 23.78 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 32.1 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 44.59 | Percentile across workers
material_spend_total | Material Spend Total | 618442.18 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 691822 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 9 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 2 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 7 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 17 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 73379.82 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404)
largest_material_savings | Largest Material Savings | 211 Garage Material: $3,799 vs $63,600 budget ($-59,801)
top_vendor_spend | Top Vendor Spend | Rosen Supply Kirkland: $177,660 (34% of AP)
phases_over_budget | Phases Over Budget | 5 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 22 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 220 Roughin Material: $140,166 vs $96,762 budget (+$43,404)
largest_savings | Largest Savings | 995 Payroll Burden: $253,391 vs $387,566 budget ($-134,175)
total_jtd_cost | Total JTD Cost | 1532182.53 | SUM(actual) expense codes
total_budget | Total Current Budget | 2050648.54 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 74.72% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 518466.01 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 26.0527 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 137.4832 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array