## Overview
Job #2049 · Exxel Pacific Reserve at Lynnwood REBUILD (post-construction-defect remediation of 2028 job)
Cortex JCR v2 • Exxel (customer 2049SH) • 5800 Scriber Lake Road, Lynnwood, WA 98036 • Owner: TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity)
PROJECT OVERVIEW
Project Job # | 2049 |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | GRE Greenlake |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Exxel Lynnwood Reserve Rebuild Apartments — 295-unit 7-story midrise multi-family (16 Type A ADA), Lynnwood |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Exxel |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2049SH |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity) |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | TBD — Exxel (CMA architect of record) |  | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
GC Superintendent | Brett (per Brett Reserve folder) |  | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
GC PE | N/A |  | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
OWP Signatory | Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract) |  | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
Jobsite Location | 5800 Scriber Lake Road, Lynnwood, WA 98036 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 1855 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') |  | Exxel Lynnwood Reserve Rebuild Apartments project info.pdf
Contract Type | Lump Sum |  | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
Unit Count | 295 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-12 start → 2019-09 (22 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
2999780 |  | 1467597.47 | 1532182.53 | 21819.25
Original $2,898,965.00 + ($100,815.00) COs (3.48%) |  | 48.9% margin | 51.1% of revenue | 58 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
295-unit mixed-use (102 Type B + 6 Type A/ADA) at 5800 Scriber Lake Road, Lynnwood, WA 98036, 7-story midrise multi-family (Type 1A podium + Type VA above).
GC: Exxel (2049SH); Owner: TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity).
Insurance: Not Wrap (retail-adjacent residential).
Project team: TBD — Exxel (CMA architect of record) (GC PM) · Brett (per Brett Reserve folder) (GC Sup) · TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') (Architect) · Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract) (OWP signatory).
SOURCES
Canonical financial source: 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $2,999,780.00 / Expenses $1,532,182.53 / Net $1,467,597.47 / Retainage $149,989.00
Source breakdown (derived): PR $868,442.74 · AP $520,745.58 · GL $142,994.21
Contract: Lump Sum $2,898,965.00 → $2,999,780.00
Change Orders (executed): $100,815.00 net across 9 COs (CO log in enriched meta)
Project Team: TBD — Exxel (CMA architect of record) (PM) · Brett (per Brett Reserve folder) (Sup) · TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') · TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity)
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Exxel
GC PM | Extracted | TBD — Exxel (CMA architect of record)
GC Superintendent | Extracted | Brett (per Brett Reserve folder)
GC PE | N/A | N/A
Owner | Extracted | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity)
Architect | Extracted | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18')
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract)

## Budget vs Actual
Budget vs Actual
All 28 cost codes from JDR. Contract $2,898,965 → $2,999,780.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 15000 | 15200 | 3977.5 | -11222.5 | 26.17% | 77.5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 25000 | 25500 | 9262.5 | -16237.5 | 36.32% | 165 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 12900 | 20040 | 12882 | -7158 | 64.28% | 436.5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 109290 | 109830 | 17823 | -92007 | 16.23% | 645.5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 404800 | 432470 | 361459.35 | -71010.65 | 83.58% | 14406 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 83990 | 84050 | 83036.25 | -1013.75 | 98.79% | 3028.5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 14400 | 16200 | 11964.5 | -4235.5 | 73.85% | 391 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 124740 | 124740 | 55727.75 | -69012.25 | 44.68% | 2253 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 20000 | 20880 | 11736.7 | -9143.3 | 56.21% | 371.25 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
143 | Condensation Drains Labor | 0 | 0 | 530 | 530 |  | 16 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
150 | Warranty Labor | 0 | 0 | 50 | 50 |  | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 2600 | 8465 | 3633.46 | -4831.54 | 42.92% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 63000 | 63600 | 3799.24 | -59800.76 | 5.974% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 7000 | 7000 | 74.33 | -6925.67 | 1.062% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 96000 | 96762 | 140166.18 | 43404.18 | 144.9% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 334600 | 347595 | 335404.06 | -12190.94 | 96.49% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 6000 | 7500 | 11428.68 | 3928.68 | 152.4% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 127400 | 127400 | 96552.88 | -30847.12 | 75.79% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 33200 | 33500 | 27383.35 | -6116.65 | 81.74% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 |  |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 5000 | 6200 | 22111.5 | 15911.5 | 356.6% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 4000 | 5000 | 103 | -4897 | 2.06% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 10250 | 10250 | 3071.92 | -7178.08 | 29.97% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 24000 | 25500 | 20155.02 | -5344.98 | 79.04% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 10000 | 10000 | 2750 | -7250 | 27.5% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 370110.42 | 387565.92 | 253391.18 | -134174.74 | 65.38% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 62433.18 | 65400.62 | 43708.18 | -21692.44 | 66.83% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -2898965 | -2999780 | -2999780 | 0 | 100% |  | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -933251.4 | -949131.46 | -1467597.47 | -518466.01 |  | 21791.25

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,120,130,140,141,142,143,150 | 568449.55 | 37.1% | 18.95% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 618442.18 | 40.36% | 20.62% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 48191.44 | 3.145% | 1.606% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 253391.18 | 16.54% | 8.447% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 43708.18 | 2.853% | 1.457% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 1532182.53 | 100% | 51.08%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1380RS | Rosen Supply Kirkland | 177659.83 | 183 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 125346.97 | 63 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 103120.85 | 45 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 49315.84 | 2 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1175FE | Ferguson Enterprises, Inc. #3007 | 31908.72 | 42 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6912MF | Mechanical Firestop Services, LLC | 16675 | 2 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 4187.5 | 1 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 3875 | 3 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2049RS | Rosen Supply Company, Inc. $Reserve | 3078.97 | 7 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 2978.42 | 7 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 984 | 1 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 531.75 | 8 | Credit Card (mixed) | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2132MH | Manor Hardware & Construction Supply | 451.36 | 4 | Plumbing / Supplies | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 265 | 3 | Testing subcontractor | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1021AT | ACME Corp | 169.87 | 2 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 103 | 1 | Engineering (601) | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1950SR | Sunbelt Rentals, Inc. | 93.5 | 1 | Uncategorized | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 520745.58 | 375

## Crew & Labor
Crew & Labor — Worker Roster
All 58 unique payroll workers. OWP signatory: Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract).
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
PA11 | Paco Leyva, Orlando | 1916 | 71217.25 | 37.1698 | 65 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR77 | Cruz Gonzalez, Julio C | 1875.5 | 43104.5 | 22.9829 | 52 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ES09 | Escalante Escobar, Boanerge | 1732 | 34600 | 19.9769 | 43 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AM03 | Amaya Gonzalez, Edilberto A | 1459.5 | 43995.25 | 30.1441 | 40 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RA55 | Ramos Herrera, Franklin J | 1419 | 33236.5 | 23.4225 | 46 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
JI50 | Jimenez Alvarenga, Gerson M | 1263 | 27271 | 21.5922 | 33 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CO69 | Cornejo Orellana, Carlos E | 1161.5 | 23262 | 20.0276 | 33 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BE54 | Benites Portillo, Marvin E | 1011 | 23775 | 23.5163 | 29 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE70 | Gerard, Jordan E | 972 | 34554 | 35.5494 | 32 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FR04 | Frausto Mendoza, Pedro | 967 | 18878.5 | 19.5228 | 28 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LI49 | Lima Romero, Melvin A | 902 | 30099 | 33.3692 | 24 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MO56 | Montenegro, Carlos E | 691 | 19376 | 28.0405 | 20 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GU17 | Guerrero, Ali A | 652 | 11277.75 | 17.2972 | 21 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DE45 | de la Torre, Kevin A | 504 | 8064 | 16 | 14 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GU78 | Gutierrez Salas, Jose | 419.5 | 7587 | 18.0858 | 13 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO75 | Ross, Kelli M | 346 | 13845 | 40.0145 | 9 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SI48 | Silva Morales, Jair J | 345 | 8289 | 24.0261 | 11 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LO87 | Lovo, German G | 308.5 | 7570.5 | 24.5397 | 18 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RI84 | Rivera, Eli P | 275 | 7560 | 27.4909 | 11 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 265 | 5136.5 | 19.383 | 13 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR19 | Crespin Portillo, Juan D | 260 | 4418 | 16.9923 | 9 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DI07 | Diaz Moreno, Kevin J | 252 | 4032 | 16 | 7 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
QU35 | Quintanilla, Esteban R | 237.5 | 10518 | 44.2863 | 19 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LE17 | Lee, Ha Nul | 191 | 3247 | 17 | 5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AS10 | Ascencio, Jose L | 191 | 5268 | 27.5812 | 8 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 189.5 | 9311 | 49.1346 | 36 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 184 | 3631 | 19.7337 | 14 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA45 | Balderas Ortiz, Ricardo I | 171 | 5035 | 29.4444 | 6 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
PO73 | Portillo Soriano, Walter A | 162 | 3172 | 19.5802 | 4 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 158.75 | 5440.88 | 34.2733 | 6 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 157 | 8488.5 | 54.0669 | 25 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 156.5 | 7915 | 50.5751 | 59 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 133.5 | 2304 | 17.2584 | 9 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 131 | 4393 | 33.5344 | 9 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 86 | 5325 | 61.9186 | 45 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR79 | Cruz Guzman, Joel A | 85 | 2013 | 23.6824 | 3 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 73.5 | 2006 | 27.2925 | 5 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
AG48 | Aguayo Robles, Carlos I | 72 | 640 | 8.8889 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA07 | Cabrera Morales, Antonio | 72 | 1216 | 16.8889 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CR87 | Cruz Reyes, Jose | 62 | 1518 | 24.4839 | 3 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 54.5 | 1893.75 | 34.7477 | 6 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 32 | 640 | 20 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA77 | Castro Hernandez, Jose A | 32 | 1024 | 32 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE91 | Reyes, Maria E | 26 | 558 | 21.4615 | 3 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GO51 | Gomez Reyes, Edith N | 26 | 690 | 26.5385 | 3 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SO71 | Sorto Regalado, Milton J | 24 | 384 | 16 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TA96 | Taylor, Evan R | 23.5 | 812.5 | 34.5745 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EI74 | Eisenhauer, Tommy J | 19 | 627 | 33 | 3 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
FO55 | Fonseca Teruel, Eduardo | 18 | 414 | 23 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DR04 | Draves, Steven W | 15.5 | 558 | 36 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CH20 | Chevez, Herson G | 10 | 198 | 19.8 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO06 | Roberts, Lake A | 8 | 144 | 18 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME53 | Mendoza Morales, Jesus A | 7.5 | 270 | 36 | 2 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE71 | Gerard, Mitchell J | 4.5 | 144 | 32 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RE18 | Reed, Reuben H | 4 | 205 | 51.25 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU04 | Hubbard, Dustin R | 2 | 46 | 23 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 2 | 100 | 50 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WA35 | Waites, Thaddeus Z | 1 | 45 | 45 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 21819.25 | 571343.38

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 58 | Unique payroll IDs | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 21819.25 | Sum of labor codes | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 571343.38 | Sum of labor codes | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 26.1853 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 8.781% | PA11 Paco Leyva, Orlando (1916 hrs) | Derived
Top 5 Workers Hours Share | 38.51% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 61.9186 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 8.8889 | Single-worker blended | Derived
Avg Hours per Worker | 376.194 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 14.931 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 295 units (1855 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 137.4832 | USD/hr
Profit per Labor Hour | 67.2616 | USD/hr
Labor Cost per Hour (blended) | 26.0527 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 53.4181 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 14406 | hrs
Finish Hours (code 130) | 3028.5 | hrs
Rough-in % of Total Hours | 66.11% | %
Gross Margin | 48.92% | %
Labor % of Revenue | 18.95% | %
Material % of Revenue | 20.62% | %
Direct Cost Ratio | 51.08% | % | All exp/Rev
Revenue per Unit (295) | 10168.7458 | USD | 295 units
Labor Hours per Unit | 73.9636 | hrs
Labor Cost per Unit | 1926.9476 | USD
Material Cost per Unit | 2096.4142 | USD
Direct Cost per Unit | 5193.8391 | USD
Rough-in Hours per Unit | 48.8339 | hrs
Revenue per Fixture | 1617.1321 | USD | 1855 fixtures
Hours per Fixture | 11.7624 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2018-03-23 | Exxel | Lump Sum Subcontract | Closed | Exxel Lynnwood Reserve Rebuild Apartments plumbing (295 units, 7 stories) — per Div 22 | 2898965 | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
CO-NET | — | Exxel | Change Orders (executed, 9 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 100815 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 2999780

## Billing & SOV
Billing & Schedule of Values
362 invoices to Exxel. Retainage $149,989.00.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
561 | 01/18/19 | -264675 | -13233.75 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
560 | 02/20/19 | -63040 | -3152 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
676 | 03/20/19 | -92555 | -4627.75 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
614 | 04/19/19 | -49150 | -2457.5 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
518 | 05/20/19 | -80009 | -4000.45 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | 06/19/19 | -67271 | -3363.55 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
682 | 06/20/18 | -146180 | -7309 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
608 | 07/19/19 | -46170 | -2308.5 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
531 | 07/20/18 | -228225 | -11411.25 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
598 | 08/20/18 | -367760 | -18388 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
761 | 08/20/19 | -2015 | -100.75 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
446 | 09/19/18 | -530315 | -26515.75 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
513 | 10/19/18 | -478250 | -23912.5 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
535 | 11/16/18 | -395610 | -19780.5 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
195 | 12/12/18 | -188555 | -9427.75 | 1 | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -2999780 | -149989

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $1,467,597.47 on $2,999,780.00 revenue = 48.9% gross margin. | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $2,898,965.00 → final $2,999,780.00 = $+100,815.00 net (3.48%) across 9 executed COs. | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $568,449.55 (18.9% of rev) across 21,819 hrs and 58 workers. Blended wage $26.05/hr. | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$487,352.21 (94% of AP). Top vendor: Rosen Supply Kirkland ($177,659.83). | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $149,989.00 — outstanding as of report date. | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 14,406 hrs (66% of labor hours). | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 120 Roughin Labor = $361,459.35 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Paco Leyva, Orlando = 1,916 hrs (9% of total). | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Exxel Lynnwood Reserve Rebuild Apartments — 295-unit 7-story midrise (279 standard + 16 Type A ADA) + P1/P2 parking at 5800 Scriber Lake Road, Lynnwood, WA 98036. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2049 | Profile | OWP job ID | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Exxel Pacific Reserve at Lynnwood REBUILD (post-construction-defect remediation of 2028 job) | Profile |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Exxel | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity) | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') | Profile |  | Verified | Exxel Lynnwood Reserve Rebuild Apartments project info.pdf
Location | location | 5800 Scriber Lake Road, Lynnwood, WA 98036 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | REBUILD / DEFECT REMEDIATION — Post-construction rebuild of the original Reserve at Lynnwood (OWP Job 2028, Exxel project 201506). Re-scope includes: replace PT-deck sleeves, chip-into L1 slab on grade, re-roughin plumbing across BLDG B + BLDG C (5 floors each), re-stock and re-install fiberglass tub/shower stalls, re-roughin hot/cold/return water mains, re-install water heater package (3 HTP Modcon 500V boilers), repair waste/vent/drain piping on basement parking + L1 SOG. Triggered by Exxel CO#11 from original 2028 contract (dated 3/23/18, amount $2,588,665 = the Rebuild scope). | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | TBD — Exxel (CMA architect of record) | Profile |  | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
GC Sup | gc_sup | Brett (per Brett Reserve folder) | Profile |  | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract) | Profile |  | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2018-03-23 | Profile |  | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
Work Start | start_date | 2017-12 | Profile |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-09 | Profile |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 22 | Profile |  | Verified | Derived
Unit Count | unit_count | 295 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 1855 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 2898965 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 2999780 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 100815 | Financial | 9 executed | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 3.478% | Financial |  | Verified | Derived
Revenue | revenue | 2999780 | Financial | AR total | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 1532182.53 | Financial | JDR Expenses | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 1467597.47 | Financial | Rev - Exp | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 48.92% | Financial |  | Verified | Derived
Retainage | retainage | 149989 | Financial | JDR AR retainage | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 568449.55 | Labor | Codes 100-151 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 618442.18 | Material | Codes 210-245 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 48191.44 | Financial | Codes 600-607 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 253391.18 | Labor | Code 995 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 43708.18 | Labor | Code 998 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 21819.25 | Labor | Sum labor codes | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 58 | Labor | Unique PR IDs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 26.0527 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 53.4181 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 14406 | Labor | Code 120 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 3028.5 | Labor | Code 130 | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 137.4832 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 67.2616 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 10168.7458 | Productivity | 295 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 5193.8391 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 73.9636 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 1617.1321 | Productivity | 1855 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 18.95% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 20.62% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 17 | Material |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 15 | Billing |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 8.781% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 38.51% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 28 | Structure |  | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 9 | Documents |  | Verified | CO log
COR Count | cor_count | 2 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 10 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 7 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 273 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1380RS | Rosen Supply Kirkland | 177659.83 | 183 | 34.12% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1130CS | Consolidated Supply Co. | 125346.97 | 63 | 24.07% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 1231KS | Keller Supply Company | 103120.85 | 45 | 19.8% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 3612MS | Mechanical Sales, Inc. | 49315.84 | 2 | 9.47% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1175FE | Ferguson Enterprises, Inc. #3007 | 31908.72 | 42 | 6.128% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 6912MF | Mechanical Firestop Services, LLC | 16675 | 2 | 3.202% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 3129MR | Mechanical Resource Services, Inc. | 4187.5 | 1 | 0.8041% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 5560CH | California Hydronics Corp | 3875 | 3 | 0.7441% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 2049RS | Rosen Supply Company, Inc. $Reserve | 3078.97 | 7 | 0.5913% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 2713AR | Ahern Rentals | 2978.42 | 7 | 0.572% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 3181SC | Scan2Core, Inc. | 984 | 1 | 0.189% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1234CO | Capital One Credit Card | 531.75 | 8 | 0.1021% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 2132MH | Manor Hardware & Construction Supply | 451.36 | 4 | 0.08668% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 1641AR | A.R. Brown Backflow Testing | 265 | 3 | 0.05089% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1021AT | ACME Corp | 169.87 | 2 | 0.03262% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 1625FE | Franklin Engineering | 103 | 1 | 0.01978% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 1950SR | Sunbelt Rentals, Inc. | 93.5 | 1 | 0.01796% | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 520745.58 | 375

## Change Log
Change Log — Master Register
Contract, 9 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2018-03-23 | Prime subcontract — Lump Sum $2,898,965.00 | Exxel | 2898965 | Executed | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/12/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $149,989.00 (outstanding) | GC | 0 | Outstanding | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 100815 | JDR-implied net CO impact | $2,898,965 → $2,999,780 (9 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -280460.45 | Labor variance vs revised budget | 58 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -73379.82 | Material procurement variance | 17 vendors
Overhead | 600,601,602,603,604,607 | -8758.56 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -155867.18 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -417651.01
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 9 | 100815 | Aggregate executed COs
Sub (OWP) labor performance | 11 | -280460.45 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -73379.82 | 17 vendors
OWP burden accrual | 2 | -155867.18 | Payroll burden + tax
OWP overhead | 5 | -8758.56 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 3.48% | ±10% | HEALTHY | +3.48% net (9 COs)
Labor % of Revenue | 18.95% | <30% | HEALTHY | 18.9%
GL Overhead % of Revenue | 4.767% | <5% | HEALTHY | 4.8%
Vendor Concentration (Top 5) | 93.59% | <95% | HEALTHY | Top 5 = 94% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 48.92% | >30% | HEALTHY | 48.9%
Labor Hrs Total | 21819.25 | varies | INFO | 21,819 hrs, 58 workers
Worker Concentration (top 1) | 8.781% | <25% | HEALTHY | 8.8% (Paco Leyva, Orlando)
Rough-in Labor Share | 66.11% | 40-65% | WATCH | 66%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $149,989.00
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 48.92% | Actual | Job closed | 48.9%
Retainage collection | $149,989.00 | Outstanding | Legacy | Outstanding
Unit-level economics | $10,169/unit rev, $4,975/unit profit | Verified | 295 units | REBUILD / DEFECT REMEDIATION — Post-construction rebuild of the original Reserve at Lynnwood (OWP Job 2028, Exxel project 201506). Re-scope includes: replace PT-deck sleeves, chip-into L1 slab on grade, re-roughin plumbing across BLDG B + BLDG C (5 floors each), re-stock and re-install fiberglass tub/shower stalls, re-roughin hot/cold/return water mains, re-install water heater package (3 HTP Modcon 500V boilers), repair waste/vent/drain piping on basement parking + L1 SOG. Triggered by Exxel CO#11 from original 2028 contract (dated 3/23/18, amount $2,588,665 = the Rebuild scope).

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2049 | id | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Exxel Pacific Reserve at Lynnwood REBUILD (post-construction-defect remediation of 2028 job) | text | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Exxel | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | TBD — per 2028 original contract (Reserve at Lynnwood LP or similar Exxel-owned entity) | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — CMA per RFI responses (e.g., 'CMA Response 24 Jan 19', 'CMA Response 30 May 18') | text | Benchmark KPIs | Verified | Exxel Lynnwood Reserve Rebuild Apartments project info.pdf
6 | location | Location | 5800 Scriber Lake Road, Lynnwood, WA 98036 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | REBUILD / DEFECT REMEDIATION — Post-construction rebuild of the original Reserve at Lynnwood (OWP Job 2028, Exxel project 201506). Re-scope includes: replace PT-deck sleeves, chip-into L1 slab on grade, re-roughin plumbing across BLDG B + BLDG C (5 floors each), re-stock and re-install fiberglass tub/shower stalls, re-roughin hot/cold/return water mains, re-install water heater package (3 HTP Modcon 500V boilers), repair waste/vent/drain piping on basement parking + L1 SOG. Triggered by Exxel CO#11 from original 2028 contract (dated 3/23/18, amount $2,588,665 = the Rebuild scope). | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | TBD — Exxel (CMA architect of record) | text | Benchmark KPIs | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Brett (per Brett Reserve folder) | text | Benchmark KPIs | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Richard Donelson (OWP per CO#11 signature authority on 201506ONELLC subcontract) | text | Benchmark KPIs | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2018-03-23 | date | Benchmark KPIs | Verified | 2049-Shelter Holdings subcontract 201506ONELLC + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-12 | date | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-09 | date | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 22 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 295 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 1855 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 2898965 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 2999780 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 100815 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 3.478% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 2999780 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 1532182.53 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 1467597.47 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 48.92% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 149989 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 568449.55 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 618442.18 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 48191.44 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 253391.18 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 43708.18 | USD | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 21819.25 | hours | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 58 | count | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 26.0527 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 53.4181 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 14406 | hours | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 3028.5 | hours | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 137.4832 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 67.2616 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 10168.7458 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 5193.8391 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 73.9636 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 1617.1321 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 18.95% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 20.62% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 17 | count | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 15 | count | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 8.781% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 38.51% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 28 | count | Benchmark KPIs | Verified | 2049 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 9 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 2 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 10 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 7 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 273 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 2999780 | 2999780 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 1532182.53 | 1532182.53 | 0 | TIES | 1↔3
3 | Net Profit = Revenue - Expenses | 1467597.47 | 1467597.47 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 2999780 | 2999780 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 21819.25 | 21819.25 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 100815 | 100815 | 0 | TIES | 11↔Derived
7 | Worker count | 58 | 58 | 0 | TIES | 5↔1
8 | Cost code count | 28 | 28 | 0 | TIES | 2↔16