## Overview
OWP JOB 2050 — COMPASS 2100 E MADISON
Cortex JCR v2 — 17-tab Job Cost Report. Aligned with v4 Test-Labels schema (Sam coverage parity). Parsed from 175-page Sage Timberline JDR dated Apr 03, 2026.
REVENUE (AR) |  | DIRECT COST |  | NET PROFIT |  | LABOR HOURS
$918,566 |  | $491,757 |  | $426,809 |  | 5,764
Billed to date (Sage AR) |  | 53.5% of revenue |  | 46.5% margin |  | 22 workers
COST BREAKDOWN (by category)
Category | Budget | Actual | Variance | Consumption | % of Direct
Labor | 207425 | 163505.5 | 43919.5 | 78.83% | 33.27%
Material | 311905 | 204958.79 | 106946.21 | 65.71% | 41.71%
Overhead | 52130 | 37734.01 | 14395.99 | 72.38% | 7.679%
Burden | 109912.89 | 85206.6 | 24706.29 | 77.52% | 17.34%
TOTAL (expense codes) | 681372.89 | 491404.9 | 189967.99 | 72.12% | 100%
COST BY SOURCE (PR / AP / GL / AR)
Source | Amount | % of Direct | Notes
PR (Payroll) | 249064.1 | 50.65% | Worker hours + wages (reg + OT + burden)
AP (Vendor Invoices) | 219925.25 | 44.72% | Material + subcontractor spend
GL (General Ledger) | 22767.55 | 4.63% | Misc adjustments + deposits
AR (Billings, credit) | -918566 | 100% | Revenue billed to GC (stored negative)

## Job Info
JOB INFORMATION — 2050
Project identity + metadata enriched from GDrive close-out package (Compass 2100 E Madison Apartments project info PDF, signed subcontract, permits, scope).
Field | Value | Source / Notes
job_number | 2050 | JDR cover page
job_name | Compass 2100 E Madison | Compass 2100 E Madison Apartments project info PDF
job_name_long | Compass 2100 E Madison Apartments (2100 E Madison Street, Seattle WA 98101) | Compass 2100 E Madison Apartments project info PDF
general_contractor | Compass | Signed subcontract 220500-01 — 12 Madison Investment LLC
owner | 12 Madison Investment LLC | Signed subcontract §A.a — 12 Madison Investment LLC
architect | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) | Contract counterparty: 12 Madison Investment LLC
location | 2100 E Madison Street, Seattle, WA 98101 | Signed subcontract + permit records
project_type | Mixed-use mid-rise: 50 residential units (47 Type B + 3 Type A ADA) + 3 ground-floor retail spaces + L1 amenity (retail ADA bathroom, trash room mop sink) + rooftop deck (dog wash, sink roughin, BBQ gas, fire-pit gas) + basement/P1 parking garage with foundation drain sump + duplex booster pump + 2 Bock OptiTherm OT-199N gas-fired condensing WHs. Post-tension deck construction with ProSet sleeves. | Scope doc + submittal TOC (mixed-use mid-rise: residential + retail + P1 garage)
unit_count | 50 | Plan drawings: mid-rise, 50 residential units (47 Type B + 3 Type A ADA) + 3 retail + P1 garage
fixture_count | 395 | Estimate from scope doc + submittal TOC (see fixture_estimate_note)
fixture_estimate_note | Derived from Compass 2100 E Madison job ticket April 23 2019 (final of 7 ticket iterations): 47 Am Std 2795.204 std toilets + 3 Am Std Townsend 2922A104 ADA toilets + 50 Am Std 0426.000 undercounter lavs + 39 Aquatic 2603SMTM tub/shower stalls + 10 Aquatic 1483BFSD fiberglass shower stalls + 1 Aquatic 1363BFSC shower stall + 3 Am Std 1662.643 ADA handhelds + 47 Houzer STS-1300 kitchen sinks + 3 Elkay ELUHAD2115-5 ADA kit sinks + 50 DW roughins + 50 washer roughins = 303 resident. Retail level (2 Kohler K-3519 ADA toilets + 2 Kohler K-2660 vessel lavs + 2 Eemax EX4208 POU WHs + 3 retail waste/vent/CW stubs + 3 retail gas stubs + 1 Mustee 63 mop sink) ≈ 14. Building systems (2 Bock OptiTherm OT-199N gas WHs + Armstrong expansion tank + 2 circ pumps + Heat Timer ETV Platinum + Watts 957OSY backflow + duplex booster pump + 1 Zoeller N145 duplex sump + 1 Liberty duplex sump + 2 Woodford 24 garage hose bibs + 4 Woodford 65 frostproof + 2 Woodford trash-room hose bibs + 1 rooftop dog wash hose bib + 1 rooftop sink roughin + rooftop gas supply + temp-water backflow + temp-heat gas permit/piping) ≈ 78. Building drains (1 Quality Concrete 36x36 sand/oil basin + 1 ProSet P65X garage floor drain + 2 ProSet trash-room drains + 5 NDS DS-090N trench drains + 10 Watts cast iron floor drains + 6 hub drains + 7 Watts cast iron L2 deck drains + 4 Watts cast iron roof drains + 1 Watts dog wash roof drain + 1 irrigation common supply POC) ≈ 38. Total ≈ 395. | Explains fixture_count basis
parking_levels | 1 | Scope doc — P1, P2 rough-in sequence
floors_residential | TBD — per Plans (mid-rise w/ basement P1 + L1 retail + L2 deck + residential floors + roof deck) | Scope doc — L1-L4 rough-in sequence
project_start_date | 2017-12 | JDR first posting 9/8/17 → contract 9/5/17 → construction start Sep 2017 (JDR first posting)
project_end_date | 2019-05 | Final pay app 12/13/2019
duration_months | 18 | start → end
contract_signed | 2017-12-07 | Signed subcontract — Richard Donelson 12/7/17
permit_jurisdiction | City of Seattle (SDCI) | City of Seattle (DCI) permit (Seattle DCI plumbing + gas + backflow)
permits_issued | Plumbing permit + plan review; Backflow permit; Gas permit; Gas permit — Temp Heat (CO#09); Permit plan review 4/12/2018; Plumbing Permit approved plan review 6/28/2018; 10 permit/inspection documents on file | Permits folder: 3 permit types × renewals/extensions
status | CLOSED | Inferred from JDR filter: "Job 2050 only, Open, Closed"
report_date | 2026-04-03 | JDR run date

## Contract Summary
CONTRACT SUMMARY — 2050
Contract basis derived from Cost Code 999 Sales (billed AR) and expense-code budgets (Sage "Original" and "Revised" columns). Revised–Original delta = net change-order impact on internal budget.
Field | Value | Notes
original_contract_budget | 897800 | Code 999 original (negated)
current_contract_budget | 918566 | Code 999 current (negated)
revenue_ar_billed | 918566 | Sum of AR line items (abs)
retainage_outstanding | 45928.3 | Sum of AR retainage column
net_due | 0 | Sage job_totals_net_due
expense_original_budget | 665170.91 | Sum of Org Budget across 100-607,995,998
expense_current_budget | 681372.89 | Sum of Rev Budget across 100-607,995,998
change_orders_to_budget | 16201.98 | Revised − Original across expense codes
direct_cost | 491756.9 | PR + AP + GL totals
net_profit | 426809.1 | abs(revenue) − direct_cost
gross_margin_pct | 46.46% | net / revenue

## Cost Categories
COST CATEGORIES — 2050
Rollup of the 29 Sage cost codes into five taxonomic buckets: Labor (1xx), Material (2xx), Overhead (6xx), Burden (995/998), Revenue (999).
Category | Code Count | Original Budget | Current Budget | Actual | Variance | Consumption % | Per-Unit Cost*
Labor | 11 | 201030 | 207425 | 163505.5 | 43919.5 | 78.83% | PENDING (needs unit_count)
Material | 9 | 305655 | 311905 | 204958.79 | 106946.21 | 65.71% | PENDING (needs unit_count)
Overhead | 5 | 51940 | 52130 | 37734.01 | 14395.99 | 72.38% | PENDING (needs unit_count)
Burden | 2 | 106545.91 | 109912.89 | 85206.6 | 24706.29 | 77.52% | PENDING (needs unit_count)
Revenue | 1 | -897800 | -918566 | -918566 | 0 | 100% | PENDING (needs unit_count)

## Budget vs Actual
BUDGET vs ACTUAL — 29 COST CODES
Full cost-code ledger with original/revised/actual/variance. Matches Sam Cost Code Summaries tab exactly. Labor codes include hours breakdown (reg/ot/dt).
Code | Description | Category | Original Budget | Current Budget | +/- Budget | Actual | Net Due | Retainage | Reg Hours | OT Hours | DT Hours | Consumption % | Status
100 | Supervision | Labor | 7000 | 7050 | -5630.25 | 1419.75 | 0 | 0 | 26 | 0 | 0 | 20.14% | UNDER
101 | Takeoff & Purchase Labor | Labor | 9000 | 9050 | -112.5 | 8937.5 | 0 | 0 | 149 | 0 | 0 | 98.76% | ON
110 | Underground Labor | Labor | 10200 | 11310 | -6547.5 | 4762.5 | 0 | 0 | 127.5 | 4 | 0 | 42.11% | UNDER
111 | Garage Labor | Labor | 30780 | 32040 | -3385 | 28655 | 0 | 0 | 998 | 12 | 0 | 89.44% | UNDER
112 | Canout Labor | Labor | 4500 | 4500 | -1213 | 3287 | 0 | 0 | 91 | 0 | 0 | 73.04% | UNDER
120 | Roughin Labor | Labor | 87940 | 91025 | -12575 | 78450 | 0 | 0 | 2761.5 | 101 | 0 | 86.19% | UNDER
130 | Finish Labor | Labor | 15480 | 15750 | -3658.75 | 12091.25 | 0 | 0 | 501.5 | 1.5 | 0 | 76.77% | UNDER
140 | Gas Labor | Labor | 6050 | 6170 | -901.5 | 5268.5 | 0 | 0 | 167 | 11 | 0 | 85.39% | UNDER
141 | Water Main/Insulation Lab | Labor | 22280 | 22730 | -11297.5 | 11432.5 | 0 | 0 | 458 | 15 | 0 | 50.3% | UNDER
142 | Mech Room Labor | Labor | 7800 | 7800 | 1214 | 9014 | 0 | 0 | 254.5 | 0 | 0 | 115.6% | OVER
151 | T&M Labor | Labor | 0 | 0 | 187.5 | 187.5 | 0 | 0 | 3 | 0 | 0 | 0% | UNDER
210 | Underground Material | Material | 8700 | 10253 | -7346.77 | 2906.23 | 0 | 0 | 0 | 0 | 0 | 28.35% | UNDER
211 | Garage Material | Material | 21850 | 23310 | -9350.88 | 13959.12 | 0 | 0 | 0 | 0 | 0 | 59.88% | UNDER
212 | Canout Material | Material | 5040 | 5040 | -1918.37 | 3121.63 | 0 | 0 | 0 | 0 | 0 | 61.94% | UNDER
220 | Roughin Material | Material | 49945 | 50270 | -9954.92 | 40315.08 | 0 | 0 | 0 | 0 | 0 | 80.2% | UNDER
230 | Finish Material | Material | 180170 | 182982 | -71774.7 | 111207.3 | 0 | 0 | 0 | 0 | 0 | 60.77% | UNDER
240 | Gas Material | Material | 6050 | 6150 | -4236.12 | 1913.88 | 0 | 0 | 0 | 0 | 0 | 31.12% | UNDER
241 | Water Main/Insulation Mat | Material | 20400 | 20400 | 255.61 | 20655.61 | 0 | 0 | 0 | 0 | 0 | 101.3% | ON
242 | Mech Room Material | Material | 13500 | 13500 | -2622.22 | 10877.78 | 0 | 0 | 0 | 0 | 0 | 80.58% | UNDER
243 | Condensation Drains Mat | Material | 0 | 0 | 2.16 | 2.16 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
600 | Subcontractor | Overhead | 1000 | 1050 | 5535 | 6585 | 0 | 0 | 0 | 0 | 0 | 627.1% | CRITICAL
601 | Engineering/Plans | Overhead | 30000 | 30000 | -12849.12 | 17150.88 | 0 | 0 | 0 | 0 | 0 | 57.17% | UNDER
602 | Rental Equipment | Overhead | 5000 | 5000 | -889.38 | 4110.62 | 0 | 0 | 0 | 0 | 0 | 82.21% | UNDER
603 | Permits & Licenses | Overhead | 6940 | 7080 | -2915 | 4165 | 0 | 0 | 0 | 0 | 0 | 58.83% | UNDER
607 | Other Expenses | Overhead | 9000 | 9000 | -3277.49 | 5722.51 | 0 | 0 | 0 | 0 | 0 | 63.58% | UNDER
800 | Office Time | Unknown | 0 | 0 | 208 | 208 | 0 | 0 | 4 | 0 | 0 | 0% | UNDER
995 | Payroll Burden | Burden | 91167.11 | 94044.86 | -21373.67 | 72671.19 | 0 | 0 | 0 | 0 | 0 | 77.27% | UNDER
997 | Employee Benefits | Unknown | 0 | 0 | 144 | 144 | 0 | 0 | 0 | 0 | 0 | 0% | UNDER
998 | Payroll Taxes | Burden | 15378.8 | 15868.03 | -3332.62 | 12535.41 | 0 | 0 | 0 | 0 | 0 | 79% | UNDER
999 | Sales | Revenue | -897800 | -918566 | 0 | -918566 | 0 | -45928.3 | 0 | 0 | 0 | 100% | —

## Cost Code Detail
COST CODE DETAIL — 2050
Per-code drill-down: transaction count, source mix, top vendor/worker, date range. Derived from line_items[] grouped by cost_code.
Code | Description | Actual | Txn Count | PR Lines | AP Lines | GL Lines | AR Lines | Top Vendor / Worker | First Date | Last Date
100 | Supervision | 1419.75 | 19 | 19 | 0 | 0 | 0 | Gerard, Jeffrey S ($736) | 01/11/19 | 11/30/18
101 | Takeoff & Purchase Labor | 8937.5 | 68 | 68 | 0 | 0 | 0 | Donelson, Richard T ($7,438) | 01/11/19 | 12/21/18
110 | Underground Labor | 4762.5 | 21 | 21 | 0 | 0 | 0 | Barnhart, Joseph N ($2,342) | 01/18/19 | 06/15/18
111 | Garage Labor | 28655 | 92 | 92 | 0 | 0 | 0 | Wilson, Garret A ($12,556) | 01/04/19 | 12/28/18
112 | Canout Labor | 3287 | 18 | 18 | 0 | 0 | 0 | Wilson, Garret A ($1,645) | 06/08/18 | 08/24/18
120 | Roughin Labor | 78450 | 165 | 165 | 0 | 0 | 0 | Wilson, Garret A ($18,336) | 01/04/19 | 12/28/18
130 | Finish Labor | 12091.25 | 39 | 39 | 0 | 0 | 0 | Eliassen, Cory H ($5,848) | 03/29/19 | 07/05/19
140 | Gas Labor | 5268.5 | 32 | 32 | 0 | 0 | 0 | Barbosa, Michael S ($2,426) | 01/11/19 | 12/28/18
141 | Water Main/Insulation Lab | 11432.5 | 51 | 51 | 0 | 0 | 0 | Barbosa, Michael S ($5,604) | 01/18/19 | 12/28/18
142 | Mech Room Labor | 9014 | 30 | 30 | 0 | 0 | 0 | Sepulveda Gonzalez, Alfredo ($5,577) | 03/01/19 | 06/14/19
151 | T&M Labor | 187.5 | 1 | 1 | 0 | 0 | 0 | Donelson, Richard T ($188) | 04/19/19 | 04/19/19
210 | Underground Material | 2906.23 | 11 | 0 | 5 | 6 | 0 | Rosen Supply Company, Inc. $E Madison ($2,263) | 02/06/19 | 06/01/18
211 | Garage Material | 13959.12 | 26 | 0 | 7 | 19 | 0 | Rosen Supply Kirkland ($16,131) | 01/22/19 | 12/21/18
212 | Canout Material | 3121.63 | 3 | 0 | 0 | 3 | 0 | Req 4511 ($2,789) | 06/27/18 | 08/10/18
220 | Roughin Material | 40315.08 | 51 | 0 | 29 | 22 | 0 | Rosen Supply Kirkland ($37,224) | 01/11/19 | 12/21/18
230 | Finish Material | 111207.3 | 98 | 0 | 74 | 24 | 0 | Ferguson Enterprises, Inc. #3007 ($65,856) | 01/07/19 | 12/19/18
240 | Gas Material | 1913.88 | 31 | 0 | 24 | 7 | 0 | Rosen Supply Kirkland ($1,607) | 01/07/19 | 12/17/18
241 | Water Main/Insulation Mat | 20655.61 | 35 | 0 | 22 | 13 | 0 | Consolidated Supply Co. ($16,096) | 01/09/19 | 12/21/18
242 | Mech Room Material | 10877.78 | 22 | 0 | 11 | 11 | 0 | Ferguson Enterprises, Inc. #3007 ($8,620) | 01/30/19 | 09/25/18
243 | Condensation Drains Mat | 2.16 | 1 | 0 | 0 | 1 | 0 | Req 5931 ($2) | 04/30/19 | 04/30/19
600 | Subcontractor | 6585 | 8 | 0 | 8 | 0 | 0 | Mechanical Resource Services, Inc. ($4,375) | 02/19/18 | 10/08/18
601 | Engineering/Plans | 17150.88 | 7 | 0 | 7 | 0 | 0 | Franklin Engineering ($17,024) | 02/27/18 | 08/22/18
602 | Rental Equipment | 4110.62 | 11 | 0 | 11 | 0 | 0 | Ahern Rentals ($3,911) | 01/08/19 | 11/28/18
603 | Permits & Licenses | 4165 | 6 | 0 | 6 | 0 | 0 | Capital One Credit Card ($3,964) | 02/21/18 | 12/31/18
607 | Other Expenses | 5722.51 | 20 | 0 | 20 | 0 | 0 | Capital One Credit Card ($6,164) | 02/14/19 | 12/31/18
800 | Office Time | 208 | 1 | 1 | 0 | 0 | 0 | Gerard, Jeffrey S ($208) | 12/14/18 | 12/14/18
995 | Payroll Burden | 72671.19 | 538 | 538 | 0 | 0 | 0 | Wilson, Garret A ($15,969) | 01/04/19 | 12/28/18
997 | Employee Benefits | 144 | 1 | 1 | 0 | 0 | 0 | Gutierrez Salas, Jose ($144) | 10/26/18 | 10/26/18
998 | Payroll Taxes | 12535.41 | 538 | 538 | 0 | 0 | 0 | Wilson, Garret A ($2,755) | 01/04/19 | 12/28/18
999 | Sales | -918566 | 110 | 0 | 0 | 0 | 110 | Compass General Construction I, LLC$2100 ($1,766,336) | 01/18/19 | 12/14/18

## Transactions Detail
TRANSACTIONS DETAIL — 2,054 LINE ITEMS
Every transaction parsed from the JDR. AR amounts are negative per Sage convention (credits). Mirrors Sam Line Items tab 1:1.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 2 | 0 | 90 | 0 | 90 | 18903 | 0 | 0
100 | Supervision | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18884 | 0 | 0
100 | Supervision | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 99350 | 0 | 0
100 | Supervision | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99427 | 0 | 0
100 | Supervision | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99501 | 0 | 0
100 | Supervision | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
100 | Supervision | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 99935 | 0 | 0
100 | Supervision | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20162 | 0 | 0
100 | Supervision | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0.5 | 0 | 31.25 | 0 | 31.25 | 91391 | 0 | 0
100 | Supervision | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21615 | 0 | 0
100 | Supervision | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20892 | 0 | 0
100 | Supervision | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 75 | 0 | 75 | 20892 | 0 | 0
100 | Supervision | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21837 | 0 | 0
100 | Supervision | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 921984 | 0 | 0
100 | Supervision | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922484 | 0 | 0
100 | Supervision | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 22700 | 0 | 0
100 | Supervision | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 922910 | 0 | 0
100 | Supervision | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 22982 | 0 | 0
100 | Supervision | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923054 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 12 | 0 | 750 | 0 | 750 | 18883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 18884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 18953 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99999 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 7 | 0 | 437.5 | 0 | 437.5 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 47 | 0 | 47 | 99998 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 19205 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99997 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 99350 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99351 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99426 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 99427 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99500 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 99575 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99576 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 5 | 0 | 312.5 | 0 | 312.5 | 19721 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 19722 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 99793 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 99794 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 19865 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 99936 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 920007 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 920008 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20079 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 3 | 0 | 150 | 0 | 150 | 20080 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20162 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 20163 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20592 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 20664 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 20879 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 2 | 0 | 100 | 0 | 100 | 91032 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21173 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 21244 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21245 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 90883 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 90884 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 91541 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 91542 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 21615 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 21686 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 1 | 0 | 50 | 0 | 50 | 21687 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 20891 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 21836 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 21911 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 921983 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922268 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922483 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 2 | 0 | 104 | 0 | 104 | 922484 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 922557 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922631 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22699 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 22768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 922839 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 922909 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 22981 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923053 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923197 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923345 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 1 | 0 | 52 | 0 | 52 | 923346 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 6 | 0 | 375 | 0 | 375 | 23568 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923643 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 23719 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 923798 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 4 | 0 | 250 | 0 | 250 | 923875 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 923952 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 924029 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 2 | 0 | 125 | 0 | 125 | 924329 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 1 | 0 | 62.5 | 0 | 62.5 | 24484 | 0 | 0
110 | Underground Labor | PR | 520 | 03/21/18 | 03/23/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19211 | 0 | 0
110 | Underground Labor | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 8.5 | 0 | 374 | 0 | 374 | 19357 | 0 | 0
110 | Underground Labor | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 5 | 0 | 130 | 0 | 130 | 19423 | 0 | 0
110 | Underground Labor | PR | 81 | 04/04/18 | 04/06/18 | WI46 | Wilson, Garret A | 3.5 | 0 | 108.5 | 0 | 108.5 | 19424 | 0 | 0
110 | Underground Labor | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 1.5 | 0 | 66 | 0 | 66 | 19431 | 0 | 0
110 | Underground Labor | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19508 | 0 | 0
110 | Underground Labor | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 88 | 0 | 88 | 19654 | 0 | 0
110 | Underground Labor | PR | 230 | 05/09/18 | 05/11/18 | BA70 | Barnhart, Joseph N | 5 | 0 | 220 | 0 | 220 | 19737 | 0 | 0
110 | Underground Labor | PR | 261 | 05/09/18 | 05/11/18 | MA71 | Martinez Reyes, Juan C | 7 | 0 | 168 | 0 | 168 | 19768 | 0 | 0
110 | Underground Labor | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 13 | 0 | 572 | 0 | 572 | 19799 | 0 | 0
110 | Underground Labor | PR | 488 | 05/16/18 | 05/18/18 | WE55 | Wennig, Johnathan M | 16 | 0 | 416 | 0 | 416 | 19861 | 0 | 0
110 | Underground Labor | PR | 489 | 05/16/18 | 05/18/18 | WI46 | Wilson, Garret A | 16 | 0 | 544 | 0 | 544 | 19862 | 0 | 0
110 | Underground Labor | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 2 | 0 | 132 | 132 | 19870 | 0 | 0
110 | Underground Labor | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 9 | 0 | 396 | 0 | 396 | 19870 | 0 | 0
110 | Underground Labor | PR | 803 | 05/23/18 | 05/25/18 | WE55 | Wennig, Johnathan M | 10 | 0 | 260 | 0 | 260 | 19932 | 0 | 0
110 | Underground Labor | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 0 | 2 | 0 | 102 | 102 | 19933 | 0 | 0
110 | Underground Labor | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 16 | 0 | 544 | 0 | 544 | 19933 | 0 | 0
110 | Underground Labor | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 6 | 0 | 264 | 0 | 264 | 19941 | 0 | 0
110 | Underground Labor | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20098 | 0 | 0
110 | Underground Labor | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22490 | 0 | 0
110 | Underground Labor | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 4 | 0 | 148 | 0 | 148 | 22556 | 0 | 0
111 | Garage Labor | PR | 538 | 08/15/18 | 08/17/18 | RO10 | Rodriguez Arevalos, Christian | 3 | 0 | 60 | 0 | 60 | 20795 | 0 | 0
111 | Garage Labor | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 4 | 0 | 140 | 0 | 140 | 21029 | 0 | 0
111 | Garage Labor | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 5 | 0 | 115 | 0 | 115 | 21106 | 0 | 0
111 | Garage Labor | PR | 298 | 09/12/18 | 09/14/18 | HE70 | Hernandez Gonzalez, Osbaldo | 16 | 0 | 320 | 0 | 320 | 21132 | 0 | 0
111 | Garage Labor | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 38 | 0 | 760 | 0 | 760 | 21159 | 0 | 0
111 | Garage Labor | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 16 | 0 | 560 | 0 | 560 | 21171 | 0 | 0
111 | Garage Labor | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 2 | 0 | 46 | 0 | 46 | 21177 | 0 | 0
111 | Garage Labor | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21178 | 0 | 0
111 | Garage Labor | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 12 | 0 | 420 | 0 | 420 | 21241 | 0 | 0
111 | Garage Labor | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 9 | 0 | 315 | 0 | 315 | 21314 | 0 | 0
111 | Garage Labor | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 24 | 0 | 552 | 0 | 552 | 21322 | 0 | 0
111 | Garage Labor | PR | 72 | 10/03/18 | 10/05/18 | MA71 | Martinez Reyes, Juan C | 12 | 0 | 312 | 0 | 312 | 21360 | 0 | 0
111 | Garage Labor | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 10 | 0 | 200 | 0 | 200 | 21375 | 0 | 0
111 | Garage Labor | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 19 | 0 | 665 | 0 | 665 | 21388 | 0 | 0
111 | Garage Labor | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 34 | 0 | 782 | 0 | 782 | 21395 | 0 | 0
111 | Garage Labor | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 26 | 0 | 520 | 0 | 520 | 21450 | 0 | 0
111 | Garage Labor | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 15.5 | 0 | 542.5 | 0 | 542.5 | 21463 | 0 | 0
111 | Garage Labor | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 21471 | 0 | 0
111 | Garage Labor | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 16 | 0 | 512 | 0 | 512 | 21474 | 0 | 0
111 | Garage Labor | PR | 491 | 10/17/18 | 10/19/18 | RO10 | Rodriguez Arevalos, Christian | 39 | 0 | 780 | 0 | 780 | 21524 | 0 | 0
111 | Garage Labor | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 6 | 0 | 210 | 0 | 210 | 21538 | 0 | 0
111 | Garage Labor | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 4 | 0 | 92 | 0 | 92 | 21545 | 0 | 0
111 | Garage Labor | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 26 | 0 | 832 | 0 | 832 | 21549 | 0 | 0
111 | Garage Labor | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 33 | 0 | 660 | 0 | 660 | 21596 | 0 | 0
111 | Garage Labor | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 9 | 0 | 315 | 0 | 315 | 21611 | 0 | 0
111 | Garage Labor | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 2 | 0 | 96 | 96 | 21621 | 0 | 0
111 | Garage Labor | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 24 | 0 | 768 | 0 | 768 | 21621 | 0 | 0
111 | Garage Labor | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 2 | 0 | 60 | 60 | 21669 | 0 | 0
111 | Garage Labor | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 32 | 0 | 640 | 0 | 640 | 21669 | 0 | 0
111 | Garage Labor | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21756 | 0 | 0
111 | Garage Labor | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 2 | 0 | 69 | 69 | 21763 | 0 | 0
111 | Garage Labor | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 11 | 0 | 253 | 0 | 253 | 21763 | 0 | 0
111 | Garage Labor | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 9 | 0 | 315 | 0 | 315 | 21829 | 0 | 0
111 | Garage Labor | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 6 | 0 | 207 | 207 | 21842 | 0 | 0
111 | Garage Labor | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 22 | 0 | 506 | 0 | 506 | 21842 | 0 | 0
111 | Garage Labor | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 6 | 0 | 276 | 0 | 276 | 21843 | 0 | 0
111 | Garage Labor | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 24 | 0 | 600 | 0 | 600 | 21915 | 0 | 0
111 | Garage Labor | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 13 | 0 | 481 | 0 | 481 | 21980 | 0 | 0
111 | Garage Labor | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 10 | 0 | 250 | 0 | 250 | 21989 | 0 | 0
111 | Garage Labor | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 5 | 0 | 185 | 0 | 185 | 22053 | 0 | 0
111 | Garage Labor | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 32 | 0 | 1120 | 0 | 1120 | 22064 | 0 | 0
111 | Garage Labor | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 32 | 0 | -1120 | 0 | -1120 | 22064 | 0 | 0
111 | Garage Labor | PR | 129 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 32 | 0 | 1120 | 0 | 1120 | 22065 | 0 | 0
111 | Garage Labor | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 28 | 0 | 700 | 0 | 700 | 22129 | 0 | 0
111 | Garage Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22195 | 0 | 0
111 | Garage Labor | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 2 | 0 | 50 | 0 | 50 | 22201 | 0 | 0
111 | Garage Labor | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 5 | 0 | 185 | 0 | 185 | 22266 | 0 | 0
111 | Garage Labor | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 8 | 0 | 296 | 0 | 296 | 22340 | 0 | 0
111 | Garage Labor | PR | 70 | 01/02/19 | 01/04/19 | WI46 | Wilson, Garret A | 8 | 0 | 296 | 0 | 296 | 22411 | 0 | 0
111 | Garage Labor | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 5 | 0 | 125 | 0 | 125 | 22416 | 0 | 0
111 | Garage Labor | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 12 | 0 | 444 | 0 | 444 | 22482 | 0 | 0
111 | Garage Labor | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 4 | 0 | 148 | 0 | 148 | 22556 | 0 | 0
111 | Garage Labor | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 8 | 0 | 200 | 0 | 200 | 22562 | 0 | 0
111 | Garage Labor | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 16 | 0 | 368 | 0 | 368 | 22615 | 0 | 0
111 | Garage Labor | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 15.5 | 0 | 573.5 | 0 | 573.5 | 22629 | 0 | 0
111 | Garage Labor | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 3 | 0 | 75 | 0 | 75 | 22635 | 0 | 0
111 | Garage Labor | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 8 | 0 | 184 | 0 | 184 | 22684 | 0 | 0
111 | Garage Labor | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22698 | 0 | 0
111 | Garage Labor | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 2 | 0 | 46 | 0 | 46 | 22753 | 0 | 0
111 | Garage Labor | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 22767 | 0 | 0
111 | Garage Labor | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 7 | 0 | 175 | 0 | 175 | 22772 | 0 | 0
111 | Garage Labor | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22838 | 0 | 0
111 | Garage Labor | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 15 | 0 | 375 | 0 | 375 | 22843 | 0 | 0
111 | Garage Labor | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 23 | 0 | 529 | 0 | 529 | 22894 | 0 | 0
111 | Garage Labor | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 19 | 0 | 703 | 0 | 703 | 22908 | 0 | 0
111 | Garage Labor | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 11.5 | 0 | 287.5 | 0 | 287.5 | 22913 | 0 | 0
111 | Garage Labor | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 26 | 0 | 598 | 0 | 598 | 22966 | 0 | 0
111 | Garage Labor | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 13 | 0 | 481 | 0 | 481 | 22980 | 0 | 0
111 | Garage Labor | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 22 | 0 | 550 | 0 | 550 | 22986 | 0 | 0
111 | Garage Labor | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 7 | 0 | 161 | 0 | 161 | 23037 | 0 | 0
111 | Garage Labor | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 10.5 | 0 | 388.5 | 0 | 388.5 | 23052 | 0 | 0
111 | Garage Labor | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 35 | 0 | 875 | 0 | 875 | 23057 | 0 | 0
111 | Garage Labor | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 23058 | 0 | 0
111 | Garage Labor | PR | 545 | 03/13/19 | 03/15/19 | RO10 | Rodriguez Arevalos, Christian | 19 | 0 | 437 | 0 | 437 | 23107 | 0 | 0
111 | Garage Labor | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 19 | 0 | 703 | 0 | 703 | 23123 | 0 | 0
111 | Garage Labor | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 10 | 0 | 250 | 0 | 250 | 23130 | 0 | 0
111 | Garage Labor | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 23131 | 0 | 0
111 | Garage Labor | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 9 | 0 | 333 | 0 | 333 | 23196 | 0 | 0
111 | Garage Labor | PR | 593 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 4 | 0 | 4 | 0 | 4 | 23494 | 0 | 0
111 | Garage Labor | PR | 594 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 4 | 0 | -4 | 0 | -4 | 23494 | 0 | 0
111 | Garage Labor | PR | 595 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 4 | 0 | 160 | 0 | 160 | 23495 | 0 | 0
111 | Garage Labor | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 4 | 0 | 200 | 0 | 200 | 23648 | 0 | 0
111 | Garage Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 8 | 0 | 264 | 0 | 264 | 23688 | 0 | 0
111 | Garage Labor | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23726 | 0 | 0
111 | Garage Labor | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 4 | 0 | 132 | 0 | 132 | 23767 | 0 | 0
111 | Garage Labor | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 7 | 0 | 350 | 0 | 350 | 23803 | 0 | 0
111 | Garage Labor | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23881 | 0 | 0
111 | Garage Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23958 | 0 | 0
111 | Garage Labor | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 5 | 0 | 165 | 0 | 165 | 23998 | 0 | 0
111 | Garage Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 5 | 0 | 250 | 0 | 250 | 24035 | 0 | 0
111 | Garage Labor | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24184 | 0 | 0
111 | Garage Labor | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 24411 | 0 | 0
112 | Canout Labor | PR | 273 | 06/06/18 | 06/08/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 20013 | 0 | 0
112 | Canout Labor | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 184 | 0 | 184 | 20098 | 0 | 0
112 | Canout Labor | PR | 525 | 06/13/18 | 06/15/18 | WI46 | Wilson, Garret A | 5 | 0 | 175 | 0 | 175 | 20160 | 0 | 0
112 | Canout Labor | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20238 | 0 | 0
112 | Canout Labor | PR | 993 | 06/27/18 | 06/29/18 | MA71 | Martinez Reyes, Juan C | 8 | 0 | 208 | 0 | 208 | 20273 | 0 | 0
112 | Canout Labor | PR | 1018 | 06/27/18 | 06/29/18 | WI46 | Wilson, Garret A | 1 | 0 | 35 | 0 | 35 | 20298 | 0 | 0
112 | Canout Labor | PR | 365 | 07/11/18 | 07/13/18 | WI46 | Wilson, Garret A | 1 | 0 | 35 | 0 | 35 | 20445 | 0 | 0
112 | Canout Labor | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20452 | 0 | 0
112 | Canout Labor | PR | 506 | 07/18/18 | 07/20/18 | WI46 | Wilson, Garret A | 1 | 0 | 35 | 0 | 35 | 20516 | 0 | 0
112 | Canout Labor | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 14 | 0 | 644 | 0 | 644 | 20525 | 0 | 0
112 | Canout Labor | PR | 807 | 07/25/18 | 07/27/18 | MA71 | Martinez Reyes, Juan C | 6 | 0 | 156 | 0 | 156 | 20564 | 0 | 0
112 | Canout Labor | PR | 833 | 07/25/18 | 07/27/18 | WI46 | Wilson, Garret A | 27 | 0 | 945 | 0 | 945 | 20590 | 0 | 0
112 | Canout Labor | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 20597 | 0 | 0
112 | Canout Labor | PR | 71 | 08/01/18 | 08/03/18 | WI46 | Wilson, Garret A | 5 | 0 | 175 | 0 | 175 | 20662 | 0 | 0
112 | Canout Labor | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20669 | 0 | 0
112 | Canout Labor | PR | 282 | 08/08/18 | 08/10/18 | WI46 | Wilson, Garret A | 5 | 0 | 175 | 0 | 175 | 20734 | 0 | 0
112 | Canout Labor | PR | 549 | 08/15/18 | 08/17/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 20806 | 0 | 0
112 | Canout Labor | PR | 784 | 08/22/18 | 08/24/18 | MA71 | Martinez Reyes, Juan C | 5 | 0 | 130 | 0 | 130 | 20851 | 0 | 0
120 | Roughin Labor | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 176 | 0 | 176 | 19508 | 0 | 0
120 | Roughin Labor | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 44 | 0 | 44 | 19582 | 0 | 0
120 | Roughin Labor | PR | 746 | 08/22/18 | 08/24/18 | BA70 | Barnhart, Joseph N | 3 | 0 | 138 | 0 | 138 | 20814 | 0 | 0
120 | Roughin Labor | PR | 799 | 08/22/18 | 08/24/18 | RO10 | Rodriguez Arevalos, Christian | 8 | 0 | 160 | 0 | 160 | 20866 | 0 | 0
120 | Roughin Labor | PR | 810 | 08/22/18 | 08/24/18 | WI46 | Wilson, Garret A | 7 | 0 | 245 | 0 | 245 | 20877 | 0 | 0
120 | Roughin Labor | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 20896 | 0 | 0
120 | Roughin Labor | PR | 1064 | 08/29/18 | 08/31/18 | WI46 | Wilson, Garret A | 3 | 0 | 105 | 0 | 105 | 20959 | 0 | 0
120 | Roughin Labor | PR | 66 | 09/05/18 | 09/07/18 | HE70 | Hernandez Gonzalez, Osbaldo | 3 | 0 | 60 | 0 | 60 | 20991 | 0 | 0
120 | Roughin Labor | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21029 | 0 | 0
120 | Roughin Labor | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 2 | 0 | 46 | 0 | 46 | 21106 | 0 | 0
120 | Roughin Labor | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 2 | 0 | 40 | 0 | 40 | 21159 | 0 | 0
120 | Roughin Labor | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 10 | 0 | 350 | 0 | 350 | 21171 | 0 | 0
120 | Roughin Labor | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 21 | 0 | 483 | 0 | 483 | 21177 | 0 | 0
120 | Roughin Labor | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 6 | 0 | 276 | 0 | 276 | 21178 | 0 | 0
120 | Roughin Labor | PR | 538 | 09/19/18 | 09/21/18 | RO10 | Rodriguez Arevalos, Christian | 21 | 0 | 420 | 0 | 420 | 21229 | 0 | 0
120 | Roughin Labor | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 19 | 0 | 665 | 0 | 665 | 21241 | 0 | 0
120 | Roughin Labor | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 26 | 0 | 598 | 0 | 598 | 21248 | 0 | 0
120 | Roughin Labor | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 24 | 0 | 576 | 0 | 576 | 21289 | 0 | 0
120 | Roughin Labor | PR | 723 | 09/26/18 | 09/28/18 | RO10 | Rodriguez Arevalos, Christian | 37 | 0 | 740 | 0 | 740 | 21301 | 0 | 0
120 | Roughin Labor | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 26 | 0 | 910 | 0 | 910 | 21314 | 0 | 0
120 | Roughin Labor | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 8 | 0 | 184 | 0 | 184 | 21322 | 0 | 0
120 | Roughin Labor | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 26 | 0 | 624 | 0 | 624 | 21363 | 0 | 0
120 | Roughin Labor | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 9 | 0 | 180 | 0 | 180 | 21375 | 0 | 0
120 | Roughin Labor | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 24 | 0 | 576 | 0 | 576 | 21380 | 0 | 0
120 | Roughin Labor | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 10 | 0 | 350 | 0 | 350 | 21388 | 0 | 0
120 | Roughin Labor | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 6 | 0 | 138 | 0 | 138 | 21395 | 0 | 0
120 | Roughin Labor | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 4 | 0 | 184 | 0 | 184 | 21396 | 0 | 0
120 | Roughin Labor | PR | 281 | 10/10/18 | 10/12/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21438 | 0 | 0
120 | Roughin Labor | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 14 | 0 | 280 | 0 | 280 | 21450 | 0 | 0
120 | Roughin Labor | PR | 298 | 10/10/18 | 10/12/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21455 | 0 | 0
120 | Roughin Labor | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 24.5 | 0 | 857.5 | 0 | 857.5 | 21463 | 0 | 0
120 | Roughin Labor | PR | 437 | 10/17/18 | 10/19/18 | BA68 | Barbosa, Michael S | 40 | 0 | 920 | 0 | 920 | 21470 | 0 | 0
120 | Roughin Labor | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 46 | 0 | 46 | 21471 | 0 | 0
120 | Roughin Labor | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 8 | 0 | 256 | 0 | 256 | 21474 | 0 | 0
120 | Roughin Labor | PR | 463 | 10/17/18 | 10/19/18 | GU78 | Gutierrez Salas, Jose | 34.5 | 0 | 621 | 0 | 621 | 21496 | 0 | 0
120 | Roughin Labor | PR | 479 | 10/17/18 | 10/19/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21512 | 0 | 0
120 | Roughin Labor | PR | 496 | 10/17/18 | 10/19/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21529 | 0 | 0
120 | Roughin Labor | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 19 | 0 | 665 | 0 | 665 | 21538 | 0 | 0
120 | Roughin Labor | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 32 | 0 | 736 | 0 | 736 | 21545 | 0 | 0
120 | Roughin Labor | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 12 | 0 | 384 | 0 | 384 | 21549 | 0 | 0
120 | Roughin Labor | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 21570 | 0 | 0
120 | Roughin Labor | PR | 745 | 10/24/18 | 10/26/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21585 | 0 | 0
120 | Roughin Labor | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 4 | 0 | 80 | 0 | 80 | 21596 | 0 | 0
120 | Roughin Labor | PR | 762 | 10/24/18 | 10/26/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21602 | 0 | 0
120 | Roughin Labor | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 26 | 0 | 910 | 0 | 910 | 21611 | 0 | 0
120 | Roughin Labor | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 4 | 0 | 138 | 138 | 21618 | 0 | 0
120 | Roughin Labor | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 32 | 0 | 736 | 0 | 736 | 21618 | 0 | 0
120 | Roughin Labor | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 3 | 0 | 144 | 144 | 21621 | 0 | 0
120 | Roughin Labor | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 16 | 0 | 512 | 0 | 512 | 21621 | 0 | 0
120 | Roughin Labor | PR | 34 | 10/31/18 | 11/02/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 21643 | 0 | 0
120 | Roughin Labor | PR | 50 | 10/31/18 | 11/02/18 | ME53 | Mendoza Morales, Jesus A | 36 | 0 | 864 | 0 | 864 | 21659 | 0 | 0
120 | Roughin Labor | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 2 | 0 | 60 | 60 | 21669 | 0 | 0
120 | Roughin Labor | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 0 | 5 | 0 | 180 | 180 | 21674 | 0 | 0
120 | Roughin Labor | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21674 | 0 | 0
120 | Roughin Labor | PR | 74 | 10/31/18 | 11/02/18 | WI46 | Wilson, Garret A | 35 | 0 | 1225 | 0 | 1225 | 21683 | 0 | 0
120 | Roughin Labor | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 13 | 0 | 299 | 0 | 299 | 21690 | 0 | 0
120 | Roughin Labor | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 0 | 8 | 0 | 384 | 384 | 21693 | 0 | 0
120 | Roughin Labor | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 40 | 0 | 1280 | 0 | 1280 | 21693 | 0 | 0
120 | Roughin Labor | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 0 | 6 | 0 | 162 | 162 | 21715 | 0 | 0
120 | Roughin Labor | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 21715 | 0 | 0
120 | Roughin Labor | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 8 | 0 | 288 | 288 | 21731 | 0 | 0
120 | Roughin Labor | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21731 | 0 | 0
120 | Roughin Labor | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 5 | 0 | 100 | 0 | 100 | 21743 | 0 | 0
120 | Roughin Labor | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 0 | 8 | 0 | 288 | 288 | 21748 | 0 | 0
120 | Roughin Labor | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21748 | 0 | 0
120 | Roughin Labor | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 4 | 0 | 140 | 0 | 140 | 21756 | 0 | 0
120 | Roughin Labor | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 28 | 0 | 980 | 0 | 980 | 21756 | 0 | 0
120 | Roughin Labor | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 2 | 0 | 92 | 0 | 92 | 21764 | 0 | 0
120 | Roughin Labor | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 0 | 8 | 0 | 384 | 384 | 21767 | 0 | 0
120 | Roughin Labor | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 40 | 0 | 1280 | 0 | 1280 | 21767 | 0 | 0
120 | Roughin Labor | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 0 | 4 | 0 | 108 | 108 | 21788 | 0 | 0
120 | Roughin Labor | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 40 | 0 | 720 | 0 | 720 | 21788 | 0 | 0
120 | Roughin Labor | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 8 | 0 | 288 | 288 | 21804 | 0 | 0
120 | Roughin Labor | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21804 | 0 | 0
120 | Roughin Labor | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 6 | 0 | 216 | 216 | 21821 | 0 | 0
120 | Roughin Labor | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 39 | 0 | 936 | 0 | 936 | 21821 | 0 | 0
120 | Roughin Labor | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 12 | 0 | 420 | 0 | 420 | 21829 | 0 | 0
120 | Roughin Labor | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 26.5 | 0 | 927.5 | 0 | 927.5 | 21829 | 0 | 0
120 | Roughin Labor | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 28 | 0 | 896 | 0 | 896 | 21846 | 0 | 0
120 | Roughin Labor | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 4 | 0 | 128 | 0 | 128 | 21846 | 0 | 0
120 | Roughin Labor | PR | 645 | 11/21/18 | 11/21/18 | GU78 | Gutierrez Salas, Jose | 32 | 0 | 576 | 0 | 576 | 21866 | 0 | 0
120 | Roughin Labor | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 6 | 0 | 216 | 216 | 21881 | 0 | 0
120 | Roughin Labor | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 960 | 0 | 960 | 21881 | 0 | 0
120 | Roughin Labor | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 0 | 1 | 0 | 36 | 36 | 21898 | 0 | 0
120 | Roughin Labor | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 960 | 0 | 960 | 21898 | 0 | 0
120 | Roughin Labor | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 6 | 0 | 210 | 0 | 210 | 21906 | 0 | 0
120 | Roughin Labor | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 9 | 0 | 315 | 0 | 315 | 21906 | 0 | 0
120 | Roughin Labor | PR | 836 | 11/28/18 | 11/30/18 | CA77 | Castro Hernandez, Jose A | 32 | 0 | 1056 | 0 | 1056 | 21919 | 0 | 0
120 | Roughin Labor | PR | 858 | 11/28/18 | 11/30/18 | GU78 | Gutierrez Salas, Jose | 19 | 0 | 361 | 0 | 361 | 21940 | 0 | 0
120 | Roughin Labor | PR | 873 | 11/28/18 | 11/30/18 | ME53 | Mendoza Morales, Jesus A | 32 | 0 | 832 | 0 | 832 | 21955 | 0 | 0
120 | Roughin Labor | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 1 | 0 | 23 | 0 | 23 | 21967 | 0 | 0
120 | Roughin Labor | PR | 890 | 11/28/18 | 11/30/18 | SI48 | Silva Morales, Jair J | 32 | 0 | 800 | 0 | 800 | 21972 | 0 | 0
120 | Roughin Labor | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 13 | 0 | 481 | 0 | 481 | 21980 | 0 | 0
120 | Roughin Labor | PR | 47 | 12/05/18 | 12/07/18 | BA70 | Barnhart, Joseph N | 9 | 0 | 432 | 0 | 432 | 21990 | 0 | 0
120 | Roughin Labor | PR | 50 | 12/05/18 | 12/07/18 | CA77 | Castro Hernandez, Jose A | 40 | 0 | 1320 | 0 | 1320 | 21993 | 0 | 0
120 | Roughin Labor | PR | 85 | 12/05/18 | 12/07/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 1040 | 0 | 1040 | 22027 | 0 | 0
120 | Roughin Labor | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 16 | 0 | 368 | 0 | 368 | 22039 | 0 | 0
120 | Roughin Labor | PR | 102 | 12/05/18 | 12/07/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 1000 | 0 | 1000 | 22044 | 0 | 0
120 | Roughin Labor | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22053 | 0 | 0
120 | Roughin Labor | PR | 273 | 12/12/18 | 12/14/18 | CA77 | Castro Hernandez, Jose A | 40 | 0 | 1320 | 0 | 1320 | 22133 | 0 | 0
120 | Roughin Labor | PR | 310 | 12/12/18 | 12/14/18 | ME53 | Mendoza Morales, Jesus A | 40 | 0 | 1040 | 0 | 1040 | 22169 | 0 | 0
120 | Roughin Labor | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 27 | 0 | 621 | 0 | 621 | 22181 | 0 | 0
120 | Roughin Labor | PR | 327 | 12/12/18 | 12/14/18 | SI48 | Silva Morales, Jair J | 40 | 0 | 1000 | 0 | 1000 | 22186 | 0 | 0
120 | Roughin Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 5 | 0 | 185 | 0 | 185 | 22195 | 0 | 0
120 | Roughin Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 8 | 0 | 296 | 0 | 296 | 22195 | 0 | 0
120 | Roughin Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22195 | 0 | 0
120 | Roughin Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 8 | 0 | 296 | 0 | 296 | 22195 | 0 | 0
120 | Roughin Labor | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 4 | 0 | 148 | 0 | 148 | 22195 | 0 | 0
120 | Roughin Labor | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 7 | 0 | 175 | 0 | 175 | 22201 | 0 | 0
120 | Roughin Labor | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22202 | 0 | 0
120 | Roughin Labor | PR | 514 | 12/19/18 | 12/21/18 | CA77 | Castro Hernandez, Jose A | 16 | 0 | 528 | 0 | 528 | 22205 | 0 | 0
120 | Roughin Labor | PR | 550 | 12/19/18 | 12/21/18 | ME53 | Mendoza Morales, Jesus A | 37 | 0 | 962 | 0 | 962 | 22240 | 0 | 0
120 | Roughin Labor | PR | 562 | 12/19/18 | 12/21/18 | RO10 | Rodriguez Arevalos, Christian | 37 | 0 | 851 | 0 | 851 | 22252 | 0 | 0
120 | Roughin Labor | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 17 | 0 | 629 | 0 | 629 | 22266 | 0 | 0
120 | Roughin Labor | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 3 | 0 | 75 | 0 | 75 | 22274 | 0 | 0
120 | Roughin Labor | PR | 741 | 12/26/18 | 12/28/18 | ME53 | Mendoza Morales, Jesus A | 26 | 0 | 676 | 0 | 676 | 22314 | 0 | 0
120 | Roughin Labor | PR | 753 | 12/26/18 | 12/28/18 | RO10 | Rodriguez Arevalos, Christian | 18 | 0 | 414 | 0 | 414 | 22326 | 0 | 0
120 | Roughin Labor | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 11 | 0 | 407 | 0 | 407 | 22340 | 0 | 0
120 | Roughin Labor | PR | 6 | 01/02/19 | 01/04/19 | BA68 | Barbosa, Michael S | 28 | 0 | 700 | 0 | 700 | 22346 | 0 | 0
120 | Roughin Labor | PR | 44 | 01/02/19 | 01/04/19 | ME53 | Mendoza Morales, Jesus A | 28 | 0 | 728 | 0 | 728 | 22385 | 0 | 0
120 | Roughin Labor | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 29 | 0 | 725 | 0 | 725 | 22416 | 0 | 0
120 | Roughin Labor | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22417 | 0 | 0
120 | Roughin Labor | PR | 266 | 01/09/19 | 01/11/19 | RO10 | Rodriguez Arevalos, Christian | 26 | 0 | 598 | 0 | 598 | 22468 | 0 | 0
120 | Roughin Labor | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 25 | 0 | 925 | 0 | 925 | 22482 | 0 | 0
120 | Roughin Labor | PR | 468 | 01/16/19 | 01/18/19 | BA68 | Barbosa, Michael S | 40 | 0 | 1000 | 0 | 1000 | 22489 | 0 | 0
120 | Roughin Labor | PR | 521 | 01/16/19 | 01/18/19 | RO10 | Rodriguez Arevalos, Christian | 40 | 0 | 920 | 0 | 920 | 22542 | 0 | 0
120 | Roughin Labor | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 28 | 0 | 1036 | 0 | 1036 | 22556 | 0 | 0
120 | Roughin Labor | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 8 | 0 | 300 | 300 | 22562 | 0 | 0
120 | Roughin Labor | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 16 | 0 | 400 | 0 | 400 | 22562 | 0 | 0
120 | Roughin Labor | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 8 | 0 | 276 | 276 | 22615 | 0 | 0
120 | Roughin Labor | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 24 | 0 | 552 | 0 | 552 | 22615 | 0 | 0
120 | Roughin Labor | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 31 | 0 | 1147 | 0 | 1147 | 22629 | 0 | 0
120 | Roughin Labor | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 13 | 0 | 299 | 0 | 299 | 22684 | 0 | 0
120 | Roughin Labor | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 17 | 0 | 629 | 0 | 629 | 22698 | 0 | 0
120 | Roughin Labor | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 3.5 | 0 | 87.5 | 0 | 87.5 | 22703 | 0 | 0
120 | Roughin Labor | PR | 162 | 02/06/19 | 02/08/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22704 | 0 | 0
120 | Roughin Labor | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 14 | 0 | 322 | 0 | 322 | 22753 | 0 | 0
120 | Roughin Labor | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 21 | 0 | 777 | 0 | 777 | 22767 | 0 | 0
120 | Roughin Labor | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 10 | 0 | 250 | 0 | 250 | 22772 | 0 | 0
120 | Roughin Labor | PR | 373 | 02/13/19 | 02/15/19 | RO10 | Rodriguez Arevalos, Christian | 10 | 0 | 230 | 0 | 230 | 22824 | 0 | 0
120 | Roughin Labor | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 16 | 0 | 592 | 0 | 592 | 22838 | 0 | 0
120 | Roughin Labor | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 10 | 0 | 250 | 0 | 250 | 22843 | 0 | 0
120 | Roughin Labor | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22844 | 0 | 0
120 | Roughin Labor | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 25 | 0 | 575 | 0 | 575 | 22894 | 0 | 0
120 | Roughin Labor | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 25 | 0 | 925 | 0 | 925 | 22908 | 0 | 0
120 | Roughin Labor | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 10.5 | 0 | 262.5 | 0 | 262.5 | 22913 | 0 | 0
120 | Roughin Labor | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 2 | 0 | 46 | 0 | 46 | 22966 | 0 | 0
120 | Roughin Labor | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 6 | 0 | 222 | 0 | 222 | 22980 | 0 | 0
120 | Roughin Labor | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 7 | 0 | 175 | 0 | 175 | 22986 | 0 | 0
120 | Roughin Labor | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 23052 | 0 | 0
120 | Roughin Labor | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 5 | 0 | 125 | 0 | 125 | 23057 | 0 | 0
120 | Roughin Labor | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 23123 | 0 | 0
120 | Roughin Labor | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 8 | 0 | 200 | 0 | 200 | 23130 | 0 | 0
120 | Roughin Labor | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 6 | 0 | 138 | 0 | 138 | 23179 | 0 | 0
120 | Roughin Labor | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 23456 | 0 | 0
120 | Roughin Labor | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 4 | 0 | 198 | 198 | 23465 | 0 | 0
120 | Roughin Labor | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 4 | 0 | 192 | 192 | 23481 | 0 | 0
120 | Roughin Labor | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 4 | 0 | 200 | 0 | 200 | 23648 | 0 | 0
120 | Roughin Labor | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 2 | 0 | 66 | 0 | 66 | 23688 | 0 | 0
120 | Roughin Labor | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23726 | 0 | 0
120 | Roughin Labor | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 8 | 0 | 264 | 0 | 264 | 23767 | 0 | 0
120 | Roughin Labor | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23958 | 0 | 0
120 | Roughin Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 4 | 0 | 200 | 0 | 200 | 24035 | 0 | 0
120 | Roughin Labor | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 12 | 0 | 396 | 0 | 396 | 24073 | 0 | 0
120 | Roughin Labor | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 3 | 0 | 150 | 0 | 150 | 24334 | 0 | 0
130 | Finish Labor | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 23205 | 0 | 0
130 | Finish Labor | PR | 98 | 04/03/19 | 04/05/19 | EL33 | Eliassen, Cory H | 16 | 0 | 400 | 0 | 400 | 23292 | 0 | 0
130 | Finish Labor | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 1.5 | 0 | 70.5 | 0 | 70.5 | 23329 | 0 | 0
130 | Finish Labor | PR | 342 | 04/10/19 | 04/12/19 | EL33 | Eliassen, Cory H | 39 | 0 | 975 | 0 | 975 | 23366 | 0 | 0
130 | Finish Labor | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23425 | 0 | 0
130 | Finish Labor | PR | 539 | 04/17/19 | 04/19/19 | EL33 | Eliassen, Cory H | 8 | 0 | 200 | 0 | 200 | 23440 | 0 | 0
130 | Finish Labor | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23479 | 0 | 0
130 | Finish Labor | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 128 | 0 | 128 | 23487 | 0 | 0
130 | Finish Labor | PR | 587 | 04/17/19 | 04/19/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 23488 | 0 | 0
130 | Finish Labor | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 3.5 | 0 | 171.5 | 0 | 171.5 | 23554 | 0 | 0
130 | Finish Labor | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 40 | 0 | 720 | 0 | 720 | 23560 | 0 | 0
130 | Finish Labor | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 40 | 0 | 640 | 0 | 640 | 23561 | 0 | 0
130 | Finish Labor | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23573 | 0 | 0
130 | Finish Labor | PR | 26 | 05/01/19 | 05/03/19 | EL33 | Eliassen, Cory H | 24 | 0 | 648 | 0 | 648 | 23588 | 0 | 0
130 | Finish Labor | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 5.5 | 0 | 269.5 | 0 | 269.5 | 23628 | 0 | 0
130 | Finish Labor | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 19 | 0 | 361 | 0 | 361 | 23632 | 0 | 0
130 | Finish Labor | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 24 | 0 | 432 | 0 | 432 | 23635 | 0 | 0
130 | Finish Labor | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 16 | 0 | 256 | 0 | 256 | 23636 | 0 | 0
130 | Finish Labor | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 35 | 0 | 945 | 0 | 945 | 23663 | 0 | 0
130 | Finish Labor | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 3 | 0 | 147 | 0 | 147 | 23704 | 0 | 0
130 | Finish Labor | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 32 | 0 | 608 | 0 | 608 | 23708 | 0 | 0
130 | Finish Labor | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 8 | 0 | 144 | 0 | 144 | 23711 | 0 | 0
130 | Finish Labor | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 8 | 0 | 128 | 0 | 128 | 23712 | 0 | 0
130 | Finish Labor | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 1 | 0 | 40.5 | 40.5 | 23742 | 0 | 0
130 | Finish Labor | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 32 | 0 | 864 | 0 | 864 | 23742 | 0 | 0
130 | Finish Labor | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 2 | 0 | 98 | 0 | 98 | 23782 | 0 | 0
130 | Finish Labor | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 16 | 0 | 304 | 0 | 304 | 23786 | 0 | 0
130 | Finish Labor | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 0 | 0.5 | 0 | 20.25 | 20.25 | 23818 | 0 | 0
130 | Finish Labor | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 40 | 0 | 1080 | 0 | 1080 | 23818 | 0 | 0
130 | Finish Labor | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 5 | 0 | 245 | 0 | 245 | 23858 | 0 | 0
130 | Finish Labor | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 24 | 0 | 456 | 0 | 456 | 23862 | 0 | 0
130 | Finish Labor | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 13 | 0 | 351 | 0 | 351 | 23897 | 0 | 0
130 | Finish Labor | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 7 | 0 | 343 | 0 | 343 | 23937 | 0 | 0
130 | Finish Labor | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 6 | 0 | 162 | 0 | 162 | 23974 | 0 | 0
130 | Finish Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 24035 | 0 | 0
130 | Finish Labor | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 2 | 0 | 54 | 0 | 54 | 24050 | 0 | 0
130 | Finish Labor | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24108 | 0 | 0
130 | Finish Labor | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 4 | 0 | 108 | 0 | 108 | 24125 | 0 | 0
130 | Finish Labor | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 2 | 0 | 100 | 0 | 100 | 24291 | 0 | 0
140 | Gas Labor | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 1 | 0 | 35 | 0 | 35 | 21388 | 0 | 0
140 | Gas Labor | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 5 | 0 | 115 | 0 | 115 | 21690 | 0 | 0
140 | Gas Labor | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 5 | 0 | 172.5 | 172.5 | 21763 | 0 | 0
140 | Gas Labor | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 21 | 0 | 483 | 0 | 483 | 21763 | 0 | 0
140 | Gas Labor | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 2 | 0 | 72 | 72 | 21821 | 0 | 0
140 | Gas Labor | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 1 | 0 | 24 | 0 | 24 | 21821 | 0 | 0
140 | Gas Labor | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21829 | 0 | 0
140 | Gas Labor | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 10 | 0 | 230 | 0 | 230 | 21842 | 0 | 0
140 | Gas Labor | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 24 | 0 | 600 | 0 | 600 | 21989 | 0 | 0
140 | Gas Labor | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 16 | 0 | 368 | 0 | 368 | 22039 | 0 | 0
140 | Gas Labor | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 10 | 0 | 250 | 0 | 250 | 22201 | 0 | 0
140 | Gas Labor | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22266 | 0 | 0
140 | Gas Labor | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 8 | 0 | 200 | 0 | 200 | 22274 | 0 | 0
140 | Gas Labor | PR | 702 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22275 | 0 | 0
140 | Gas Labor | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22482 | 0 | 0
140 | Gas Labor | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 4 | 0 | 100 | 0 | 100 | 22913 | 0 | 0
140 | Gas Labor | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 6 | 0 | 222 | 0 | 222 | 22980 | 0 | 0
140 | Gas Labor | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 11 | 0 | 275 | 0 | 275 | 22986 | 0 | 0
140 | Gas Labor | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 3 | 0 | 69 | 0 | 69 | 23037 | 0 | 0
140 | Gas Labor | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 23052 | 0 | 0
140 | Gas Labor | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 2 | 0 | 99 | 99 | 23465 | 0 | 0
140 | Gas Labor | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 2 | 0 | 96 | 96 | 23481 | 0 | 0
140 | Gas Labor | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 3 | 0 | 96 | 0 | 96 | 23481 | 0 | 0
140 | Gas Labor | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23501 | 0 | 0
140 | Gas Labor | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 50 | 0 | 50 | 23573 | 0 | 0
140 | Gas Labor | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23604 | 0 | 0
140 | Gas Labor | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 5 | 0 | 175 | 0 | 175 | 23630 | 0 | 0
140 | Gas Labor | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23803 | 0 | 0
140 | Gas Labor | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 12 | 0 | 420 | 0 | 420 | 23859 | 0 | 0
140 | Gas Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 3 | 0 | 150 | 0 | 150 | 24035 | 0 | 0
140 | Gas Labor | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 2 | 0 | 66 | 0 | 66 | 24073 | 0 | 0
140 | Gas Labor | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24108 | 0 | 0
141 | Water Main/Insulation Lab | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 12 | 0 | 276 | 0 | 276 | 21177 | 0 | 0
141 | Water Main/Insulation Lab | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21241 | 0 | 0
141 | Water Main/Insulation Lab | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 14 | 0 | 322 | 0 | 322 | 21248 | 0 | 0
141 | Water Main/Insulation Lab | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21314 | 0 | 0
141 | Water Main/Insulation Lab | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 8 | 0 | 184 | 0 | 184 | 21322 | 0 | 0
141 | Water Main/Insulation Lab | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 11 | 0 | 264 | 0 | 264 | 21363 | 0 | 0
141 | Water Main/Insulation Lab | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 11 | 0 | 220 | 0 | 220 | 21375 | 0 | 0
141 | Water Main/Insulation Lab | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 4 | 0 | 92 | 0 | 92 | 21545 | 0 | 0
141 | Water Main/Insulation Lab | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21611 | 0 | 0
141 | Water Main/Insulation Lab | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 1 | 0 | 34.5 | 34.5 | 21618 | 0 | 0
141 | Water Main/Insulation Lab | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 8 | 0 | 184 | 0 | 184 | 21618 | 0 | 0
141 | Water Main/Insulation Lab | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 1 | 0 | 30 | 30 | 21669 | 0 | 0
141 | Water Main/Insulation Lab | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 8 | 0 | 160 | 0 | 160 | 21669 | 0 | 0
141 | Water Main/Insulation Lab | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 20 | 0 | 460 | 0 | 460 | 21690 | 0 | 0
141 | Water Main/Insulation Lab | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 6 | 0 | 156 | 0 | 156 | 21722 | 0 | 0
141 | Water Main/Insulation Lab | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 6 | 0 | 180 | 180 | 21743 | 0 | 0
141 | Water Main/Insulation Lab | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 35 | 0 | 700 | 0 | 700 | 21743 | 0 | 0
141 | Water Main/Insulation Lab | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 2 | 0 | 70 | 0 | 70 | 21756 | 0 | 0
141 | Water Main/Insulation Lab | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 1 | 0 | 34.5 | 34.5 | 21763 | 0 | 0
141 | Water Main/Insulation Lab | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 6 | 0 | 138 | 0 | 138 | 21763 | 0 | 0
141 | Water Main/Insulation Lab | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 6 | 0 | 180 | 180 | 21816 | 0 | 0
141 | Water Main/Insulation Lab | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 38.5 | 0 | 770 | 0 | 770 | 21816 | 0 | 0
141 | Water Main/Insulation Lab | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 1 | 0 | 35 | 0 | 35 | 21829 | 0 | 0
141 | Water Main/Insulation Lab | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 4 | 0 | 92 | 0 | 92 | 21842 | 0 | 0
141 | Water Main/Insulation Lab | PR | 672 | 11/21/18 | 11/21/18 | RO10 | Rodriguez Arevalos, Christian | 40 | 0 | 800 | 0 | 800 | 21893 | 0 | 0
141 | Water Main/Insulation Lab | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 3 | 0 | 105 | 0 | 105 | 21906 | 0 | 0
141 | Water Main/Insulation Lab | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 8 | 0 | 200 | 0 | 200 | 21915 | 0 | 0
141 | Water Main/Insulation Lab | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 28 | 0 | 644 | 0 | 644 | 21967 | 0 | 0
141 | Water Main/Insulation Lab | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 21980 | 0 | 0
141 | Water Main/Insulation Lab | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 6 | 0 | 150 | 0 | 150 | 21989 | 0 | 0
141 | Water Main/Insulation Lab | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 8 | 0 | 184 | 0 | 184 | 22039 | 0 | 0
141 | Water Main/Insulation Lab | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 22053 | 0 | 0
141 | Water Main/Insulation Lab | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 12 | 0 | 300 | 0 | 300 | 22129 | 0 | 0
141 | Water Main/Insulation Lab | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 8 | 0 | 184 | 0 | 184 | 22181 | 0 | 0
141 | Water Main/Insulation Lab | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22195 | 0 | 0
141 | Water Main/Insulation Lab | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 18 | 0 | 450 | 0 | 450 | 22201 | 0 | 0
141 | Water Main/Insulation Lab | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22266 | 0 | 0
141 | Water Main/Insulation Lab | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 7 | 0 | 175 | 0 | 175 | 22274 | 0 | 0
141 | Water Main/Insulation Lab | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 7 | 0 | 259 | 0 | 259 | 22340 | 0 | 0
141 | Water Main/Insulation Lab | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 22556 | 0 | 0
141 | Water Main/Insulation Lab | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 16 | 0 | 400 | 0 | 400 | 22562 | 0 | 0
141 | Water Main/Insulation Lab | PR | 718 | 01/23/19 | 01/25/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22563 | 0 | 0
141 | Water Main/Insulation Lab | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22629 | 0 | 0
141 | Water Main/Insulation Lab | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 37 | 0 | 925 | 0 | 925 | 22635 | 0 | 0
141 | Water Main/Insulation Lab | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 3 | 0 | 111 | 0 | 111 | 22698 | 0 | 0
141 | Water Main/Insulation Lab | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 12.5 | 0 | 312.5 | 0 | 312.5 | 22703 | 0 | 0
141 | Water Main/Insulation Lab | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 6 | 0 | 150 | 0 | 150 | 22772 | 0 | 0
141 | Water Main/Insulation Lab | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 1 | 0 | 37 | 0 | 37 | 22838 | 0 | 0
141 | Water Main/Insulation Lab | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 23 | 0 | 575 | 0 | 575 | 22843 | 0 | 0
141 | Water Main/Insulation Lab | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 2 | 0 | 74 | 0 | 74 | 22908 | 0 | 0
141 | Water Main/Insulation Lab | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 6 | 0 | 150 | 0 | 150 | 22913 | 0 | 0
142 | Mech Room Labor | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 96 | 0 | 96 | 22914 | 0 | 0
142 | Mech Room Labor | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 1 | 0 | 48 | 0 | 48 | 22987 | 0 | 0
142 | Mech Room Labor | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 1 | 0 | 49 | 0 | 49 | 23087 | 0 | 0
142 | Mech Room Labor | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 14 | 0 | 350 | 0 | 350 | 23130 | 0 | 0
142 | Mech Room Labor | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 2 | 0 | 46 | 0 | 46 | 23179 | 0 | 0
142 | Mech Room Labor | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 1.5 | 0 | 55.5 | 0 | 55.5 | 23196 | 0 | 0
142 | Mech Room Labor | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | 147 | 0 | 147 | 23197 | 0 | 0
142 | Mech Room Labor | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 3 | 0 | -147 | 0 | -147 | 23160 | 0 | 0
142 | Mech Room Labor | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 5.5 | 0 | 269.5 | 0 | 269.5 | 23235 | 0 | 0
142 | Mech Room Labor | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 24 | 0 | 768 | 0 | 768 | 23258 | 0 | 0
142 | Mech Room Labor | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 10 | 0 | 490 | 0 | 490 | 23308 | 0 | 0
142 | Mech Room Labor | PR | 137 | 04/03/19 | 04/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1280 | 0 | 1280 | 23331 | 0 | 0
142 | Mech Room Labor | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 5 | 0 | 250 | 0 | 250 | 23381 | 0 | 0
142 | Mech Room Labor | PR | 381 | 04/10/19 | 04/12/19 | SE64 | Sepulveda Gonzalez, Alfredo | 40 | 0 | 1280 | 0 | 1280 | 23405 | 0 | 0
142 | Mech Room Labor | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23456 | 0 | 0
142 | Mech Room Labor | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 32 | 0 | 1024 | 0 | 1024 | 23481 | 0 | 0
142 | Mech Room Labor | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23531 | 0 | 0
142 | Mech Room Labor | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 16 | 0 | 560 | 0 | 560 | 23556 | 0 | 0
142 | Mech Room Labor | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 1.5 | 0 | 75 | 0 | 75 | 23604 | 0 | 0
142 | Mech Room Labor | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 3 | 0 | 105 | 0 | 105 | 23630 | 0 | 0
142 | Mech Room Labor | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 1 | 0 | 50 | 0 | 50 | 23758 | 0 | 0
142 | Mech Room Labor | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 4 | 0 | 132 | 0 | 132 | 23767 | 0 | 0
142 | Mech Room Labor | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 16 | 0 | 560 | 0 | 560 | 23783 | 0 | 0
142 | Mech Room Labor | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 23881 | 0 | 0
142 | Mech Room Labor | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 4 | 0 | 200 | 0 | 200 | 23913 | 0 | 0
142 | Mech Room Labor | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 3 | 0 | 99 | 0 | 99 | 23998 | 0 | 0
142 | Mech Room Labor | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 2 | 0 | 100 | 0 | 100 | 24035 | 0 | 0
142 | Mech Room Labor | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 3 | 0 | 150 | 0 | 150 | 24064 | 0 | 0
142 | Mech Room Labor | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 10 | 0 | 330 | 0 | 330 | 24073 | 0 | 0
151 | T&M Labor | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 3 | 0 | 187.5 | 0 | 187.5 | 923496 | 0 | 0
210 | Underground Material | AP | 518 | 02/12/18 | 02/16/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 151.89 | 4248075-00 | 0 | 0
210 | Underground Material | GL | 92 | 04/05/18 | 04/05/18 | CK#5075 | Joseph Barnhart |  |  |  |  | 19.46 |  | 0 | 0
210 | Underground Material | GL | 157 | 04/10/18 | 04/10/18 | Mat | Req 4299 |  |  |  |  | 12.7 |  | 0 | 0
210 | Underground Material | GL | 739 | 04/26/18 | 04/26/18 | Mat | Req 3611 |  |  |  |  | 206 |  | 0 | 0
210 | Underground Material | AP | 812 | 04/11/18 | 04/30/18 | 2050RS | Rosen Supply Company, Inc. $E Madison |  |  |  |  | 92 | 4250526-00 | 0 | 0
210 | Underground Material | GL | 621 | 05/22/18 | 05/22/18 | Mat | Req 4363 |  |  |  |  | 154.8 |  | 0 | 0
210 | Underground Material | AP | 638 | 05/07/18 | 05/22/18 | 2050RS | Rosen Supply Company, Inc. $E Madison |  |  |  |  | 961.23 | 4251531-00 | 0 | 0
210 | Underground Material | AP | 731 | 05/16/18 | 05/23/18 | 2050RS | Rosen Supply Company, Inc. $E Madison |  |  |  |  | 1210 | 4252015-00 | 0 | 0
210 | Underground Material | GL | 881 | 05/31/18 | 05/31/18 | CK#5505 | Joseph Barnhart |  |  |  |  | 36.92 |  | 0 | 0
210 | Underground Material | GL | 105 | 06/01/18 | 06/01/18 | Mat | Req 4412 |  |  |  |  | 35.25 |  | 0 | 0
210 | Underground Material | AP | 128 | 01/14/19 | 02/06/19 | 1231KS | Keller Supply Company |  |  |  |  | 25.98 | S012642641.001 | 0 | 0
211 | Garage Material | GL | 408 | 04/18/18 | 04/18/18 | Mat | Req 3571 |  |  |  |  | 52.26 |  | 0 | 0
211 | Garage Material | GL | 613 | 09/25/18 | 09/25/18 | Mat | Req 5383 |  |  |  |  | 369.8 |  | 0 | 0
211 | Garage Material | AP | 867 | 09/05/18 | 09/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 1164.96 | 4256780-00 | 0 | 0
211 | Garage Material | GL | 358 | 10/16/18 | 10/16/18 | Mat | Req 4712 |  |  |  |  | 75.53 |  | 0 | 0
211 | Garage Material | AP | 431 | 09/24/18 | 10/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 14706.23 | 4256554-00 | 0 | 0
211 | Garage Material | GL | 884 | 10/31/18 | 10/31/18 | Mat | Req 5498 |  |  |  |  | 261.38 |  | 0 | 0
211 | Garage Material | GL | 1011 | 11/30/18 | 11/30/18 | Mat | Req 5560 |  |  |  |  | 228.8 |  | 0 | 0
211 | Garage Material | AP | 1057 | 10/30/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.33 | 4259304-00 | 0 | 0
211 | Garage Material | GL | 688 | 12/20/18 | 12/20/18 | CK#5642 | Garret Wilson |  |  |  |  | 25.36 |  | 0 | 0
211 | Garage Material | GL | 620 | 12/21/18 | 12/21/18 | Mat | Req 5616 |  |  |  |  | 121.17 |  | 0 | 0
211 | Garage Material | GL | 655 | 01/22/19 | 01/22/19 | Mat | Req 4940 |  |  |  |  | 18 |  | 0 | 0
211 | Garage Material | GL | 873 | 01/30/19 | 01/30/19 | Mat | Req 5001 |  |  |  |  | 57 |  | 0 | 0
211 | Garage Material | GL | 143 | 03/04/19 | 03/04/19 | Mat | Req 5052 |  |  |  |  | -944.61 |  | 0 | 0
211 | Garage Material | GL | 147 | 03/04/19 | 03/04/19 | Mat | Req 5047 |  |  |  |  | -824.77 |  | 0 | 0
211 | Garage Material | GL | 162 | 03/04/19 | 03/04/19 | Mat | Req 5707 |  |  |  |  | 292.42 |  | 0 | 0
211 | Garage Material | GL | 344 | 03/08/19 | 03/08/19 | Mat | Req 5790 |  |  |  |  | 25.8 |  | 0 | 0
211 | Garage Material | AP | 429 | 02/22/19 | 03/12/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75.4 | 4263790-00 | 0 | 0
211 | Garage Material | AP | 476 | 02/26/19 | 03/13/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.92 | 4263909-00 | 0 | 0
211 | Garage Material | GL | 610 | 03/15/19 | 03/15/19 | Mat | Req 5063 |  |  |  |  | -1442.67 |  | 0 | 0
211 | Garage Material | GL | 1067 | 03/28/19 | 03/28/19 | Mat | Req 5847 |  |  |  |  | 4.6 |  | 0 | 0
211 | Garage Material | GL | 897 | 04/30/19 | 04/30/19 | Mat | Req 5930 |  |  |  |  | 48.08 |  | 0 | 0
211 | Garage Material | GL | 908 | 04/30/19 | 04/30/19 | Mat | Req 5184 |  |  |  |  | -593.4 |  | 0 | 0
211 | Garage Material | GL | 115 | 06/05/19 | 06/05/19 | Mat | Req 5244 |  |  |  |  | 125.36 |  | 0 | 0
211 | Garage Material | AP | 288 | 05/22/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 67.33 | 4267817-00 | 0 | 0
211 | Garage Material | GL | 795 | 06/26/19 | 06/26/19 | Mat | Req 6066 |  |  |  |  | -72.23 |  | 0 | 0
211 | Garage Material | AP | 438 | 06/29/19 | 07/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 40.07 | 4269386-00 | 0 | 0
212 | Canout Material | GL | 907 | 06/27/18 | 06/27/18 | Mat | Req 3739 |  |  |  |  | 610.23 |  | 0 | 0
212 | Canout Material | GL | 685 | 07/25/18 | 07/25/18 | Mat | Req 4511 |  |  |  |  | 2788.8 |  | 0 | 0
212 | Canout Material | GL | 351 | 08/10/18 | 08/10/18 | Mat | Req 4561 |  |  |  |  | -277.4 |  | 0 | 0
220 | Roughin Material | GL | 460 | 09/19/18 | 09/19/18 | Mat | Req 5346 |  |  |  |  | 223.38 |  | 0 | 0
220 | Roughin Material | GL | 768 | 09/30/18 | 09/30/18 | Mat | Req 5415 |  |  |  |  | 45.75 |  | 0 | 0
220 | Roughin Material | AP | 868 | 09/06/18 | 09/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 2698.72 | 4256830-00 | 0 | 0
220 | Roughin Material | AP | 111 | 09/06/18 | 10/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 8890.03 | 4253108-00 | 0 | 0
220 | Roughin Material | GL | 360 | 10/16/18 | 10/16/18 | Mat | Req 4710 |  |  |  |  | 1288.02 |  | 0 | 0
220 | Roughin Material | AP | 597 | 09/25/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 38.1 | 4257736-00 | 0 | 0
220 | Roughin Material | AP | 612 | 09/26/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3605.42 | 4257612-00 | 0 | 0
220 | Roughin Material | AP | 613 | 09/27/18 | 10/22/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 10541.33 | 4253109-00 | 0 | 0
220 | Roughin Material | AP | 414 | 09/18/18 | 10/31/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 396.7 | 4257422-00 | 0 | 0
220 | Roughin Material | GL | 885 | 10/31/18 | 10/31/18 | Mat | Req 5497 |  |  |  |  | 1434.12 |  | 0 | 0
220 | Roughin Material | AP | 144 | 10/11/18 | 11/05/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 167.54 | 4258508-00 | 0 | 0
220 | Roughin Material | GL | 329 | 11/09/18 | 11/09/18 | Mat | Req 4789 |  |  |  |  | 340.32 |  | 0 | 0
220 | Roughin Material | AP | 418 | 10/16/18 | 11/13/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3159.59 | 4258634-00 | 0 | 0
220 | Roughin Material | AP | 608 | 10/18/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 47.72 | 4258838-00 | 0 | 0
220 | Roughin Material | AP | 609 | 10/22/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -1688.3 | 4258996-00 | 0 | 0
220 | Roughin Material | AP | 610 | 10/23/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 47.72 | 4258838-01 | 0 | 0
220 | Roughin Material | AP | 611 | 10/23/18 | 11/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 708.43 | 4259007-00 | 0 | 0
220 | Roughin Material | GL | 759 | 11/26/18 | 11/26/18 | Mat | Req 4854 |  |  |  |  | 2412.36 |  | 0 | 0
220 | Roughin Material | AP | 972 | 10/31/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 737.52 | 4259377-00 | 0 | 0
220 | Roughin Material | GL | 974 | 11/30/18 | 11/30/18 | Mat | Req 5567 |  |  |  |  | -99 |  | 0 | 0
220 | Roughin Material | GL | 1010 | 11/30/18 | 11/30/18 | Mat | Req 5559 |  |  |  |  | 1951.23 |  | 0 | 0
220 | Roughin Material | AP | 1021 | 11/02/18 | 11/30/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 32.84 | 4259480-00 | 0 | 0
220 | Roughin Material | AP | 390 | 11/07/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 32.71 | 4259671-00 | 0 | 0
220 | Roughin Material | AP | 391 | 11/12/18 | 12/14/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 359.72 | 4259880-00 | 0 | 0
220 | Roughin Material | AP | 452 | 11/20/18 | 12/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 652.65 | 4260202-00 | 0 | 0
220 | Roughin Material | GL | 621 | 12/21/18 | 12/21/18 | Mat | Req 5615 |  |  |  |  | 450.16 |  | 0 | 0
220 | Roughin Material | GL | 312 | 01/11/19 | 01/11/19 | Mat | Req 4880 |  |  |  |  | 77.95 |  | 0 | 0
220 | Roughin Material | GL | 337 | 01/11/19 | 01/11/19 | Mat | Req 5657 |  |  |  |  | 111 |  | 0 | 0
220 | Roughin Material | AP | 364 | 11/28/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 238.61 | 4260423-00 | 0 | 0
220 | Roughin Material | AP | 392 | 12/04/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 794.88 | 4260423-01 | 0 | 0
220 | Roughin Material | AP | 600 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 861.12 | 4260423-02 | 0 | 0
220 | Roughin Material | AP | 603 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 36.16 | 4261042-00 | 0 | 0
220 | Roughin Material | GL | 658 | 01/23/19 | 01/23/19 | Mat | Req 4937 |  |  |  |  | 441.5 |  | 0 | 0
220 | Roughin Material | GL | 877 | 01/30/19 | 01/30/19 | Mat | Req 4997 |  |  |  |  | 273.86 |  | 0 | 0
220 | Roughin Material | AP | 920 | 01/07/19 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 95.39 | S9080090.001 | 0 | 0
220 | Roughin Material | AP | 277 | 01/08/19 | 02/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 42.15 | 4261992-00 | 0 | 0
220 | Roughin Material | AP | 474 | 01/14/19 | 02/16/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -175.68 | 4262220-00 | 0 | 0
220 | Roughin Material | AP | 498 | 01/21/19 | 02/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -190.32 | 4262571-00 | 0 | 0
220 | Roughin Material | AP | 563 | 01/22/19 | 02/20/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 180.8 | 4262635-00 | 0 | 0
220 | Roughin Material | AP | 677 | 01/28/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 34.08 | 4262888-00 | 0 | 0
220 | Roughin Material | GL | 198 | 03/01/19 | 03/01/19 | CK#5687 | Garret Wilson |  |  |  |  | 21.61 |  | 0 | 0
220 | Roughin Material | GL | 141 | 03/04/19 | 03/04/19 | Mat | Req 5022 |  |  |  |  | -2061.04 |  | 0 | 0
220 | Roughin Material | GL | 161 | 03/04/19 | 03/04/19 | Mat | Req 5709 |  |  |  |  | 39.88 |  | 0 | 0
220 | Roughin Material | GL | 345 | 03/08/19 | 03/08/19 | Mat | Req 5789 |  |  |  |  | -81.2 |  | 0 | 0
220 | Roughin Material | GL | 815 | 03/25/19 | 03/25/19 | Mat | Req 5102 |  |  |  |  | 91.41 |  | 0 | 0
220 | Roughin Material | GL | 1059 | 03/28/19 | 03/28/19 | Mat | Req 5837 |  |  |  |  | -86 |  | 0 | 0
220 | Roughin Material | AP | 346 | 04/22/19 | 05/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 812.64 | 4266286-00 | 0 | 0
220 | Roughin Material | AP | 759 | 05/08/19 | 05/28/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 52.89 | 4267240-00 | 0 | 0
220 | Roughin Material | GL | 113 | 06/05/19 | 06/05/19 | Mat | Req 5246 |  |  |  |  | 62.25 |  | 0 | 0
220 | Roughin Material | GL | 796 | 06/26/19 | 06/26/19 | Mat | Req 6065 |  |  |  |  | -42.1 |  | 0 | 0
220 | Roughin Material | GL | 193 | 07/10/19 | 07/10/19 | Mat | Req 6121 |  |  |  |  | 208.46 |  | 0 | 0
230 | Finish Material | AP | 205 | 03/30/18 | 04/10/18 | 2050FE | Ferguson Enterprises, Inc. $Madison |  |  |  |  | 6247.95 | 6047023 | 0 | 0
230 | Finish Material | GL | 396 | 04/18/18 | 04/18/18 | Mat | Req 3572 |  |  |  |  | 83.88 |  | 0 | 0
230 | Finish Material | GL | 104 | 06/01/18 | 06/01/18 | Mat | Req 4411 |  |  |  |  | 488.4 |  | 0 | 0
230 | Finish Material | AP | 147 | 05/29/18 | 06/04/18 | 1609QC | Quality Concrete Products, Inc. $32 |  |  |  |  | 2095 | 16588 | 0 | 0
230 | Finish Material | AP | 208 | 05/23/18 | 06/05/18 | 2050KS | Keller Supply Co. $E Madison |  |  |  |  | 278.42 | S011769203.001 | 0 | 0
230 | Finish Material | GL | 616 | 06/18/18 | 06/18/18 | Mat | Req 3691 |  |  |  |  | 120.86 |  | 0 | 0
230 | Finish Material | GL | 686 | 07/25/18 | 07/25/18 | Mat | Req 4512 |  |  |  |  | 1031.6 |  | 0 | 0
230 | Finish Material | AP | 240 | 08/22/18 | 09/11/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1734.02 | 6483879 | 0 | 0
230 | Finish Material | AP | 412 | 08/28/18 | 09/18/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 167.54 | 6483855 | 0 | 0
230 | Finish Material | AP | 121 | 09/26/18 | 10/05/18 | 5560CH | California Hydronics Corp |  |  |  |  | 465 | 2108119 | 0 | 0
230 | Finish Material | AP | 350 | 09/18/18 | 10/15/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -16.76 | CM695702 | 0 | 0
230 | Finish Material | GL | 359 | 10/16/18 | 10/16/18 | Mat | Req 4711 |  |  |  |  | 1137.6 |  | 0 | 0
230 | Finish Material | AP | 369 | 10/17/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2740.16 | 6484056 | 0 | 0
230 | Finish Material | AP | 370 | 10/17/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2740.16 | 6484139 | 0 | 0
230 | Finish Material | AP | 371 | 10/17/18 | 11/12/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 3324.17 | 6484159 | 0 | 0
230 | Finish Material | GL | 756 | 11/26/18 | 11/26/18 | Mat | Req 4855 |  |  |  |  | 482.74 |  | 0 | 0
230 | Finish Material | AP | 936 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 993.56 | 6484056-1 | 0 | 0
230 | Finish Material | AP | 937 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 993.56 | 6484139-1 | 0 | 0
230 | Finish Material | AP | 938 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 993.56 | 6484159-1 | 0 | 0
230 | Finish Material | AP | 939 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 3733.72 | 6484199 | 0 | 0
230 | Finish Material | AP | 940 | 10/26/18 | 11/30/18 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4076.24 | 6484225 | 0 | 0
230 | Finish Material | GL | 1012 | 11/30/18 | 11/30/18 | Mat | Req 5561 |  |  |  |  | 40.72 |  | 0 | 0
230 | Finish Material | AP | 369 | 11/14/18 | 12/14/18 | 1231KS | Keller Supply Company |  |  |  |  | 174.9 | S012471333.001 | 0 | 0
230 | Finish Material | AP | 426 | 11/16/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 3565.88 | 4253139-00 | 0 | 0
230 | Finish Material | AP | 451 | 11/20/18 | 12/19/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 125.06 | 4260174-00 | 0 | 0
230 | Finish Material | AP | 143 | 12/17/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 75.39 | 6808852 | 0 | 0
230 | Finish Material | AP | 144 | 12/17/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -678.53 | CM724431 | 0 | 0
230 | Finish Material | AP | 145 | 12/18/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 376.96 | 6808836 | 0 | 0
230 | Finish Material | AP | 147 | 12/19/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 226.18 | 6808829 | 0 | 0
230 | Finish Material | AP | 148 | 12/21/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -685.04 | CM720025 | 0 | 0
230 | Finish Material | AP | 195 | 12/05/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 404.9 | S12471333.002 | 0 | 0
230 | Finish Material | GL | 339 | 01/11/19 | 01/11/19 | Mat | Req 5655 |  |  |  |  | 359.03 |  | 0 | 0
230 | Finish Material | GL | 654 | 01/22/19 | 01/22/19 | Mat | Req 4941 |  |  |  |  | 449.82 |  | 0 | 0
230 | Finish Material | GL | 876 | 01/30/19 | 01/30/19 | Mat | Req 4998 |  |  |  |  | 725.51 |  | 0 | 0
230 | Finish Material | AP | 903 | 01/14/19 | 01/30/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 96.86 | 700000 | 0 | 0
230 | Finish Material | AP | 123 | 01/18/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 113.09 | 6890018 | 0 | 0
230 | Finish Material | AP | 124 | 01/18/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -150.78 | CM733771 | 0 | 0
230 | Finish Material | AP | 125 | 01/21/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 113.09 | 6890021 | 0 | 0
230 | Finish Material | AP | 126 | 01/23/19 | 02/01/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -113.09 | M734953 | 0 | 0
230 | Finish Material | AP | 506 | 01/24/19 | 02/18/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 113.09 | 6900216 | 0 | 0
230 | Finish Material | AP | 678 | 01/31/19 | 02/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 75.65 | 4263045-00 | 0 | 0
230 | Finish Material | AP | 722 | 02/15/19 | 02/26/19 | 5560CH | California Hydronics Corp |  |  |  |  | 3038 | SIN008298 | 0 | 0
230 | Finish Material | AP | 723 | 02/15/19 | 02/26/19 | 5560CH | California Hydronics Corp |  |  |  |  | 16590 | SIN008331 | 0 | 0
230 | Finish Material | GL | 160 | 03/04/19 | 03/04/19 | Mat | Req 5706 |  |  |  |  | 504.83 |  | 0 | 0
230 | Finish Material | GL | 367 | 03/08/19 | 03/08/19 | Mat | Req 5031 |  |  |  |  | 390.6 |  | 0 | 0
230 | Finish Material | GL | 817 | 03/25/19 | 03/25/19 | Mat | Req 5100 |  |  |  |  | 476.51 |  | 0 | 0
230 | Finish Material | GL | 849 | 03/25/19 | 03/25/19 | Mat | Req 5107 |  |  |  |  | 74.99 |  | 0 | 0
230 | Finish Material | AP | 900 | 03/22/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1739.71 | 6944975 | 0 | 0
230 | Finish Material | AP | 901 | 03/22/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1919.19 | 6944986 | 0 | 0
230 | Finish Material | GL | 1069 | 03/28/19 | 03/28/19 | Mat | Req 5846 |  |  |  |  | 396.51 |  | 0 | 0
230 | Finish Material | GL | 212 | 04/08/19 | 04/08/19 | Mat | Req 5127 |  |  |  |  | 2170 |  | 0 | 0
230 | Finish Material | AP | 308 | 04/08/19 | 04/10/19 | 5560CH | California Hydronics Corp |  |  |  |  | 655 | SIN013742 | 0 | 0
230 | Finish Material | GL | 441 | 04/12/19 | 04/12/19 | Mat | Req 5135 |  |  |  |  | 1021.83 |  | 0 | 0
230 | Finish Material | AP | 479 | 04/02/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4609.25 | 6946544 | 0 | 0
230 | Finish Material | AP | 481 | 04/04/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1919.19 | 6944994 | 0 | 0
230 | Finish Material | AP | 482 | 04/04/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1739.71 | 6944998 | 0 | 0
230 | Finish Material | AP | 869 | 04/06/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4271.78 | 6946566 | 0 | 0
230 | Finish Material | AP | 871 | 04/09/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1654.79 | 6946544-1 | 0 | 0
230 | Finish Material | AP | 872 | 04/09/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 58.91 | 6946566-1 | 0 | 0
230 | Finish Material | AP | 873 | 04/09/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -58.91 | CM758176 | 0 | 0
230 | Finish Material | AP | 874 | 04/10/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1654.79 | 6946566-2 | 0 | 0
230 | Finish Material | AP | 876 | 04/18/19 | 04/30/19 | 5560CH | California Hydronics Corp |  |  |  |  | 125 | SIN014816 | 0 | 0
230 | Finish Material | GL | 900 | 04/30/19 | 04/30/19 | Mat | Req 5927 |  |  |  |  | 438.12 |  | 0 | 0
230 | Finish Material | AP | 100 | 04/18/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2095.92 | 6945001 | 0 | 0
230 | Finish Material | AP | 101 | 04/23/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 5469.17 | 6946558 | 0 | 0
230 | Finish Material | AP | 103 | 04/24/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2317.53 | 7148199 | 0 | 0
230 | Finish Material | AP | 104 | 04/24/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 824.74 | 7148204 | 0 | 0
230 | Finish Material | AP | 105 | 04/24/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 103.09 | 7148209 | 0 | 0
230 | Finish Material | AP | 106 | 04/25/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 294.55 | 6946558-1 | 0 | 0
230 | Finish Material | AP | 107 | 04/25/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 58.91 | 7152091 | 0 | 0
230 | Finish Material | AP | 492 | 05/07/19 | 05/17/19 | 3612MS | Mechanical Sales, Inc. |  |  |  |  | 876.85 | 702257 | 0 | 0
230 | Finish Material | AP | 497 | 04/29/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 4689.46 | 6946574 | 0 | 0
230 | Finish Material | AP | 498 | 05/03/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 58.91 | 6946574-1 | 0 | 0
230 | Finish Material | AP | 499 | 05/03/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 262.25 | 7170477 | 0 | 0
230 | Finish Material | AP | 500 | 05/06/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1415.9 | 6945756 | 0 | 0
230 | Finish Material | AP | 501 | 05/06/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 412.37 | 6946574-2 | 0 | 0
230 | Finish Material | AP | 502 | 05/06/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 2116.88 | 7177883 | 0 | 0
230 | Finish Material | AP | 503 | 05/09/19 | 05/20/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 338.32 | 6946558-2 | 0 | 0
230 | Finish Material | AP | 530 | 05/14/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 1553.18 | S012832930.001 | 0 | 0
230 | Finish Material | AP | 531 | 05/14/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 810.59 | S012996770.001 | 0 | 0
230 | Finish Material | GL | 712 | 05/23/19 | 05/23/19 | 1380RS | Inv 4265727-00 |  |  |  |  | 819.96 |  | 0 | 0
230 | Finish Material | GL | 872 | 05/30/19 | 05/30/19 | Mat | Req 5209 |  |  |  |  | 978.1 |  | 0 | 0
230 | Finish Material | AP | 93 | 05/15/19 | 06/05/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 338.32 | 6945756-1 | 0 | 0
230 | Finish Material | GL | 114 | 06/05/19 | 06/05/19 | Mat | Req 5245 |  |  |  |  | 209.59 |  | 0 | 0
230 | Finish Material | GL | 169 | 06/05/19 | 06/05/19 | Mat | Req 6021 |  |  |  |  | -427.37 |  | 0 | 0
230 | Finish Material | AP | 289 | 05/28/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 175.48 | 4268017-00 | 0 | 0
230 | Finish Material | AP | 370 | 05/22/19 | 06/11/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 193.5 | 7231721 | 0 | 0
230 | Finish Material | AP | 371 | 05/28/19 | 06/11/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -262.68 | CM774387 | 0 | 0
230 | Finish Material | AP | 382 | 05/23/19 | 06/11/19 | 1231KS | Keller Supply Company |  |  |  |  | 213.32 | S013040111.001 | 0 | 0
230 | Finish Material | AP | 398 | 05/30/19 | 06/11/19 | 7423OC | Old Castle Infrastructure, Inc. |  |  |  |  | 595 | 11000439 | 0 | 0
230 | Finish Material | AP | 422 | 05/28/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 185.36 | 7243044 | 0 | 0
230 | Finish Material | AP | 423 | 06/05/19 | 06/12/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -193.5 | CM777075 | 0 | 0
230 | Finish Material | AP | 585 | 06/12/19 | 06/17/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 103.09 | 7244615 | 0 | 0
230 | Finish Material | GL | 797 | 06/26/19 | 06/26/19 | Mat | Req 6064 |  |  |  |  | -416.42 |  | 0 | 0
230 | Finish Material | GL | 192 | 07/10/19 | 07/10/19 | Mat | Req 6122 |  |  |  |  | 20.6 |  | 0 | 0
230 | Finish Material | AP | 250 | 06/06/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 20.25 | 060619JB2 | 0 | 0
230 | Finish Material | AP | 381 | 06/25/19 | 07/10/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 291.21 | 7138966 | 0 | 0
230 | Finish Material | AP | 711 | 07/16/19 | 07/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | -45 | CM789681 | 0 | 0
240 | Gas Material | GL | 758 | 11/26/18 | 11/26/18 | Mat | Req 4856 |  |  |  |  | 38.15 |  | 0 | 0
240 | Gas Material | AP | 425 | 11/05/18 | 12/17/18 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 866.32 | 4259437-00 | 0 | 0
240 | Gas Material | AP | 146 | 12/18/18 | 01/07/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 63.32 | 6816113 | 0 | 0
240 | Gas Material | AP | 194 | 11/30/18 | 01/09/19 | 1231KS | Keller Supply Company |  |  |  |  | 111.79 | S012527135.001 | 0 | 0
240 | Gas Material | AP | 365 | 11/28/18 | 01/14/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 55.97 | 4260448-00 | 0 | 0
240 | Gas Material | AP | 578 | 12/06/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 120.98 | 4260850-00 | 0 | 0
240 | Gas Material | AP | 601 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 54.94 | 4260850-01 | 0 | 0
240 | Gas Material | AP | 602 | 12/11/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 71.71 | 4261040-00 | 0 | 0
240 | Gas Material | AP | 604 | 12/12/18 | 01/21/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 30.41 | 4261040-01 | 0 | 0
240 | Gas Material | AP | 630 | 12/17/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 59.21 | 4261296-00 | 0 | 0
240 | Gas Material | AP | 631 | 12/19/18 | 01/22/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 20.05 | 4261296-01 | 0 | 0
240 | Gas Material | GL | 657 | 01/23/19 | 01/23/19 | Mat | Req 4938 |  |  |  |  | 1.86 |  | 0 | 0
240 | Gas Material | GL | 366 | 03/08/19 | 03/08/19 | Mat | Req 5033 |  |  |  |  | 48.69 |  | 0 | 0
240 | Gas Material | GL | 592 | 03/15/19 | 03/15/19 | Mat | Req 5813 |  |  |  |  | 7.79 |  | 0 | 0
240 | Gas Material | GL | 898 | 04/30/19 | 04/30/19 | Mat | Req 5929 |  |  |  |  | 61.48 |  | 0 | 0
240 | Gas Material | AP | 137 | 04/10/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 81.97 | 4266040-00 | 0 | 0
240 | Gas Material | AP | 282 | 04/15/19 | 05/10/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 41.76 | 4266173-00 | 0 | 0
240 | Gas Material | AP | 529 | 04/26/19 | 05/21/19 | 1231KS | Keller Supply Company |  |  |  |  | 202.8 | S012959273.001 | 0 | 0
240 | Gas Material | AP | 587 | 05/02/19 | 05/23/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 170.36 | S9241652.001 | 0 | 0
240 | Gas Material | AP | 588 | 05/02/19 | 05/23/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 82.46 | S9241652.002 | 0 | 0
240 | Gas Material | AP | 589 | 05/09/19 | 05/23/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | -82.46 | S9241652.003 | 0 | 0
240 | Gas Material | AP | 964 | 05/16/19 | 05/31/19 | 1231KS | Keller Supply Company |  |  |  |  | 7.1 | S013031313.001 | 0 | 0
240 | Gas Material | GL | 112 | 06/05/19 | 06/05/19 | Mat | Req 5247 |  |  |  |  | 18.05 |  | 0 | 0
240 | Gas Material | AP | 286 | 05/16/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 94.36 | 4267561-00 | 0 | 0
240 | Gas Material | AP | 287 | 05/16/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13.09 | 4267589-00 | 0 | 0
240 | Gas Material | AP | 310 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 21.39 | 4267589-01 | 0 | 0
240 | Gas Material | AP | 311 | 05/30/19 | 06/08/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 13.09 | 4268161-00 | 0 | 0
240 | Gas Material | AP | 597 | 06/11/19 | 06/18/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 43.7 | 4268691-00 | 0 | 0
240 | Gas Material | AP | 740 | 06/13/19 | 06/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 17.59 | 4268821-00 | 0 | 0
240 | Gas Material | GL | 799 | 06/26/19 | 06/26/19 | Mat | Req 6062 |  |  |  |  | -450.52 |  | 0 | 0
240 | Gas Material | AP | 253 | 06/12/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | 26.47 | 061219JB2 | 0 | 0
241 | Water Main/Insulation Mat | AP | 179 | 10/11/18 | 11/07/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 953.98 | S8966550.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 330 | 11/09/18 | 11/09/18 | Mat | Req 4790 |  |  |  |  | 191.2 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 342 | 10/18/18 | 11/09/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2098.74 | S8976620.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 373 | 10/25/18 | 11/13/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 2228.78 | S8988426.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 374 | 10/25/18 | 11/13/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 4713.13 | S8988491.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 757 | 11/26/18 | 11/26/18 | Mat | Req 4853 |  |  |  |  | 565.45 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 946 | 10/29/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 310.51 | S8988491.002 | 0 | 0
241 | Water Main/Insulation Mat | GL | 1009 | 11/30/18 | 11/30/18 | Mat | Req 5558 |  |  |  |  | 731.6 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 1037 | 11/05/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 291.47 | S9004976.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1038 | 11/05/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 47.15 | S9004976.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1039 | 11/08/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 251.88 | S9008778.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1040 | 11/12/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 461.78 | S9015640.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 1053 | 11/05/18 | 11/30/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 190.8 | S9005019.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 400 | 11/08/18 | 12/17/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 181.64 | S9011936.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 622 | 12/21/18 | 12/21/18 | Mat | Req 5614 |  |  |  |  | 661.3 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 663 | 11/26/18 | 12/21/18 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1909.39 | S9029139.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 196 | 12/13/18 | 01/09/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 1677.5 | S9056167.001 | 0 | 0
241 | Water Main/Insulation Mat | GL | 338 | 01/11/19 | 01/11/19 | Mat | Req 5656 |  |  |  |  | 32.5 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 656 | 01/23/19 | 01/23/19 | Mat | Req 4939 |  |  |  |  | 168 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 874 | 01/30/19 | 01/30/19 | Mat | Req 5000 |  |  |  |  | 147.05 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 920 | 01/07/19 | 01/30/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 205.81 | S9080090.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 522 | 02/08/19 | 02/18/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 283.54 | S9126502.002 | 0 | 0
241 | Water Main/Insulation Mat | AP | 710 | 02/05/19 | 02/25/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 406.08 | 4263106-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 163 | 03/04/19 | 03/04/19 | Mat | Req 5708 |  |  |  |  | 231.07 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 210 | 02/28/19 | 03/05/19 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 113.09 | K200299 | 0 | 0
241 | Water Main/Insulation Mat | AP | 242 | 02/20/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 457.05 | 6969599 | 0 | 0
241 | Water Main/Insulation Mat | GL | 365 | 03/08/19 | 03/08/19 | Mat | Req 5036 |  |  |  |  | 466.06 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 657 | 03/04/19 | 03/19/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 773.53 | 4262218-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 814 | 03/25/19 | 03/25/19 | Mat | Req 5103 |  |  |  |  | 94.84 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 869 | 03/13/19 | 03/26/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 289.67 | S9166027.001 | 0 | 0
241 | Water Main/Insulation Mat | AP | 881 | 03/08/19 | 03/26/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 242.66 | 4262218-01 | 0 | 0
241 | Water Main/Insulation Mat | GL | 910 | 04/30/19 | 04/30/19 | Mat | Req 5182 |  |  |  |  | -400.44 |  | 0 | 0
241 | Water Main/Insulation Mat | AP | 138 | 04/11/19 | 05/02/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | -41.99 | 4266112-00 | 0 | 0
241 | Water Main/Insulation Mat | GL | 794 | 06/26/19 | 06/26/19 | Mat | Req 6067 |  |  |  |  | -293.36 |  | 0 | 0
241 | Water Main/Insulation Mat | GL | 191 | 07/10/19 | 07/10/19 | Mat | Req 6123 |  |  |  |  | 14.15 |  | 0 | 0
242 | Mech Room Material | AP | 125 | 06/15/18 | 07/09/18 | 5621HD | Core & Main LP $HD Supply Waterworks |  |  |  |  | 202.7 | J025696 | 0 | 0
242 | Mech Room Material | GL | 612 | 09/25/18 | 09/25/18 | Mat | Req 5384 |  |  |  |  | 25.84 |  | 0 | 0
242 | Mech Room Material | GL | 875 | 01/30/19 | 01/30/19 | Mat | Req 4999 |  |  |  |  | 200.7 |  | 0 | 0
242 | Mech Room Material | AP | 243 | 02/25/19 | 03/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 393.71 | 6984572 | 0 | 0
242 | Mech Room Material | AP | 444 | 02/26/19 | 03/13/19 | 1130CS | Consolidated Supply Co. |  |  |  |  | 901.64 | S9146292.001 | 0 | 0
242 | Mech Room Material | AP | 462 | 03/07/19 | 03/13/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 473.21 | 7015661 | 0 | 0
242 | Mech Room Material | GL | 810 | 03/25/19 | 03/25/19 | Mat | Req 5108 |  |  |  |  | 428.73 |  | 0 | 0
242 | Mech Room Material | GL | 816 | 03/25/19 | 03/25/19 | Mat | Req 5101 |  |  |  |  | 18.94 |  | 0 | 0
242 | Mech Room Material | AP | 902 | 03/22/19 | 03/26/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 3929.82 | 7048109 | 0 | 0
242 | Mech Room Material | GL | 1068 | 03/28/19 | 03/28/19 | Mat | Req 5845 |  |  |  |  | 1306.45 |  | 0 | 0
242 | Mech Room Material | GL | 211 | 04/08/19 | 04/08/19 | Mat | Req 5128 |  |  |  |  | 948.03 |  | 0 | 0
242 | Mech Room Material | GL | 442 | 04/12/19 | 04/12/19 | Mat | Req 5134 |  |  |  |  | 341.99 |  | 0 | 0
242 | Mech Room Material | AP | 478 | 03/27/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1227.07 | 7070795 | 0 | 0
242 | Mech Room Material | AP | 480 | 04/03/19 | 04/15/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 1762.17 | 7087436 | 0 | 0
242 | Mech Room Material | AP | 713 | 04/05/19 | 04/24/19 | 1380RS | Rosen Supply Kirkland |  |  |  |  | 819.96 | 4265727-00 | 0 | 0
242 | Mech Room Material | AP | 870 | 04/06/19 | 04/30/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 506.34 | 7100551 | 0 | 0
242 | Mech Room Material | GL | 899 | 04/30/19 | 04/30/19 | Mat | Req 5928 |  |  |  |  | 86.7 |  | 0 | 0
242 | Mech Room Material | GL | 909 | 04/30/19 | 04/30/19 | Mat | Req 5183 |  |  |  |  | -439.26 |  | 0 | 0
242 | Mech Room Material | AP | 99 | 04/17/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 61.38 | 7132382 | 0 | 0
242 | Mech Room Material | AP | 102 | 04/24/19 | 05/06/19 | 1175FE | Ferguson Enterprises, Inc. #3007 |  |  |  |  | 265.88 | 7135904 | 0 | 0
242 | Mech Room Material | GL | 712 | 05/23/19 | 05/23/19 | 1380RS | Inv 4265727-00 |  |  |  |  | -819.96 |  | 0 | 0
242 | Mech Room Material | GL | 798 | 06/26/19 | 06/26/19 | Mat | Req 6063 |  |  |  |  | -1764.26 |  | 0 | 0
243 | Condensation Drains Mat | GL | 896 | 04/30/19 | 04/30/19 | Mat | Req 5931 |  |  |  |  | 2.16 |  | 0 | 0
600 | Subcontractor | AP | 555 | 02/14/18 | 02/19/18 | 1421RA | R.A. Brown Backflow Testing |  |  |  |  | 50 | 18021406 | 0 | 0
600 | Subcontractor | AP | 143 | 10/03/18 | 10/08/18 | 3181SC | Scan2Core, Inc. |  |  |  |  | 615 | 71975 | 0 | 0
600 | Subcontractor | AP | 724 | 02/01/19 | 02/27/19 | 1504CA | Chip Away Bathtub Repair, Inc. |  |  |  |  | 275 | 22714 | 0 | 0
600 | Subcontractor | AP | 725 | 02/12/19 | 02/27/19 | 1504CA | Chip Away Bathtub Repair, Inc. |  |  |  |  | 875 | 22743 | 0 | 0
600 | Subcontractor | AP | 488 | 03/05/19 | 03/13/19 | 1504CA | Chip Away Bathtub Repair, Inc. |  |  |  |  | 150 | 22835 | 0 | 0
600 | Subcontractor | AP | 792 | 05/15/19 | 05/29/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 185 | 1385 | 0 | 0
600 | Subcontractor | AP | 793 | 05/22/19 | 05/29/19 | 1641AR | A.R. Brown Backflow Testing |  |  |  |  | 60 | 1408 | 0 | 0
600 | Subcontractor | AP | 366 | 06/03/19 | 06/10/19 | 3129MR | Mechanical Resource Services, Inc. |  |  |  |  | 4375 | 16612-5520B | 0 | 0
601 | Engineering/Plans | AP | 748 | 02/20/18 | 02/27/18 | 1625FE | Franklin Engineering |  |  |  |  | 3870.5 | 6843 | 0 | 0
601 | Engineering/Plans | AP | 649 | 03/21/18 | 03/26/18 | 1625FE | Franklin Engineering |  |  |  |  | 3305.75 | 6881 | 0 | 0
601 | Engineering/Plans | AP | 832 | 04/20/18 | 04/30/18 | 1625FE | Franklin Engineering |  |  |  |  | 8959.25 | 6920 | 0 | 0
601 | Engineering/Plans | AP | 163 | 04/11/18 | 05/08/18 | 1288DR | DRSi |  |  |  |  | 103.08 | 462126 | 0 | 0
601 | Engineering/Plans | AP | 240 | 05/31/18 | 06/06/18 | 1288DR | DRSi |  |  |  |  | 23.8 | 465623 | 0 | 0
601 | Engineering/Plans | AP | 791 | 06/19/18 | 06/22/18 | 1625FE | Franklin Engineering |  |  |  |  | 616 | 6981 | 0 | 0
601 | Engineering/Plans | AP | 689 | 08/15/18 | 08/22/18 | 1625FE | Franklin Engineering |  |  |  |  | 272.5 | 7072 | 0 | 0
602 | Rental Equipment | AP | 633 | 10/02/18 | 10/16/18 | 2713AR | Ahern Rentals |  |  |  |  | 520.23 | 19574868-1 | 0 | 0
602 | Rental Equipment | AP | 810 | 11/01/18 | 11/28/18 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-2 | 0 | 0
602 | Rental Equipment | AP | 152 | 11/27/18 | 01/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-3 | 0 | 0
602 | Rental Equipment | AP | 157 | 12/25/18 | 01/08/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-4 | 0 | 0
602 | Rental Equipment | AP | 140 | 01/22/19 | 02/01/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-5 | 0 | 0
602 | Rental Equipment | AP | 204 | 02/19/19 | 03/05/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-006 | 0 | 0
602 | Rental Equipment | AP | 10 | 03/19/19 | 04/02/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-007 | 0 | 0
602 | Rental Equipment | AP | 837 | 04/16/19 | 04/26/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-008 | 0 | 0
602 | Rental Equipment | AP | 786 | 05/14/19 | 05/29/19 | 2713AR | Ahern Rentals |  |  |  |  | 410.13 | 19574868-009 | 0 | 0
602 | Rental Equipment | AP | 804 | 05/23/19 | 05/29/19 | 1799AW | AllWest Underground, Inc. |  |  |  |  | 199.25 | 84330 | 0 | 0
602 | Rental Equipment | AP | 363 | 05/31/19 | 06/10/19 | 2713AR | Ahern Rentals |  |  |  |  | 110.1 | 19574868-010 | 0 | 0
603 | Permits & Licenses | AP | 799 | 02/10/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 298 | 021018A | 0 | 0
603 | Permits & Licenses | AP | 800 | 02/10/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 175 | 021018B | 0 | 0
603 | Permits & Licenses | AP | 801 | 02/10/18 | 02/21/18 | 1234CO | Capital One Credit Card |  |  |  |  | 2949 | 021018C | 0 | 0
603 | Permits & Licenses | AP | 775 | 04/12/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 201 | 041218 | 0 | 0
603 | Permits & Licenses | AP | 119 | 06/27/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402 | 062718J1 | 0 | 0
603 | Permits & Licenses | AP | 794 | 11/27/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 140 | 112718B | 0 | 0
607 | Other Expenses | AP | 943 | 03/15/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 031518A | 0 | 0
607 | Other Expenses | AP | 957 | 03/22/18 | 03/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 4 | 032218A | 0 | 0
607 | Other Expenses | AP | 776 | 04/12/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 14.71 | 041218A | 0 | 0
607 | Other Expenses | AP | 793 | 04/15/18 | 04/30/18 | 1234BA | Bank of America CC |  |  |  |  | 402.32 | 041518A | 0 | 0
607 | Other Expenses | AP | 861 | 05/15/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 051518B | 0 | 0
607 | Other Expenses | AP | 868 | 05/16/18 | 05/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 17.16 | 051618B | 0 | 0
607 | Other Expenses | AP | 214 | 06/15/18 | 07/10/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 061518R2 | 0 | 0
607 | Other Expenses | AP | 120 | 06/27/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 7.36 | 072718J2 | 0 | 0
607 | Other Expenses | AP | 144 | 07/15/18 | 08/07/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 071518R2 | 0 | 0
607 | Other Expenses | AP | 1128 | 08/15/18 | 08/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 081518R2 | 0 | 0
607 | Other Expenses | AP | 823 | 09/15/18 | 09/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 091518R2 | 0 | 0
607 | Other Expenses | AP | 831 | 10/15/18 | 10/30/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 101518R2 | 0 | 0
607 | Other Expenses | AP | 485 | 11/15/18 | 12/14/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 111518R2 | 0 | 0
607 | Other Expenses | AP | 852 | 12/17/18 | 12/31/18 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 121718R2 | 0 | 0
607 | Other Expenses | AP | 451 | 01/15/19 | 02/14/19 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 011519R2 | 0 | 0
607 | Other Expenses | AP | 128 | 02/15/19 | 03/04/19 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 021519R1 | 0 | 0
607 | Other Expenses | AP | 1040 | 03/16/19 | 03/31/19 | 1234CO | Capital One Credit Card |  |  |  |  | 402.32 | 031619R1 | 0 | 0
607 | Other Expenses | AP | 975 | 04/16/19 | 04/30/19 | 1234CO | Capital One Credit Card |  |  |  |  | 439.12 | 041619R1 | 0 | 0
607 | Other Expenses | AP | 77 | 05/16/19 | 06/05/19 | 1234CO | Capital One Credit Card |  |  |  |  | 439.12 | 051619R1 | 0 | 0
607 | Other Expenses | AP | 256 | 06/14/19 | 07/10/19 | 1234CO | Capital One Credit Card |  |  |  |  | -429.12 | 061419 | 0 | 0
800 | Office Time | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 4 | 0 | 208 | 0 | 208 | 22198 | 0 | 0
995 | Payroll Burden | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 39.92 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 332.63 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 194.03 |  | 0 | 0
995 | Payroll Burden | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 20.84 |  | 0 | 0
995 | Payroll Burden | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 520 | 03/21/18 | 03/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 165.87 |  | 0 | 0
995 | Payroll Burden | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 04/04/18 | 04/06/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 48.12 |  | 0 | 0
995 | Payroll Burden | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 78.06 |  | 0 | 0
995 | Payroll Burden | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 39.03 |  | 0 | 0
995 | Payroll Burden | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 230 | 05/09/18 | 05/11/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 261 | 05/09/18 | 05/11/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 74.51 |  | 0 | 0
995 | Payroll Burden | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 253.68 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 05/16/18 | 05/18/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 184.5 |  | 0 | 0
995 | Payroll Burden | PR | 489 | 05/16/18 | 05/18/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 05/23/18 | 05/25/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 115.31 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 45.24 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 241.26 |  | 0 | 0
995 | Payroll Burden | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 06/06/18 | 06/08/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.51 |  | 0 | 0
995 | Payroll Burden | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 06/13/18 | 06/15/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 993 | 06/27/18 | 06/29/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 1018 | 06/27/18 | 06/29/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 15.52 |  | 0 | 0
995 | Payroll Burden | PR | 365 | 07/11/18 | 07/13/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 15.52 |  | 0 | 0
995 | Payroll Burden | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 506 | 07/18/18 | 07/20/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 15.52 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 285.61 |  | 0 | 0
995 | Payroll Burden | PR | 807 | 07/25/18 | 07/27/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 833 | 07/25/18 | 07/27/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 419.11 |  | 0 | 0
995 | Payroll Burden | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 08/01/18 | 08/03/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 08/08/18 | 08/10/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 538 | 08/15/18 | 08/17/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 549 | 08/15/18 | 08/17/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 746 | 08/22/18 | 08/24/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 784 | 08/22/18 | 08/24/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 57.66 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 08/22/18 | 08/24/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 810 | 08/22/18 | 08/24/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 1064 | 08/29/18 | 08/31/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 09/05/18 | 09/07/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 51 |  | 0 | 0
995 | Payroll Burden | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 09/12/18 | 09/14/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 141.92 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 337.06 |  | 0 | 0
995 | Payroll Burden | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 17.74 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 538 | 09/19/18 | 09/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 294.93 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 723 | 09/26/18 | 09/28/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 328.19 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 403.59 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 10/03/18 | 10/05/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 138.37 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 276.74 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 97.57 |  | 0 | 0
995 | Payroll Burden | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 294.93 |  | 0 | 0
995 | Payroll Burden | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 15.52 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 13.86 |  | 0 | 0
995 | Payroll Burden | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 346.82 |  | 0 | 0
995 | Payroll Burden | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 10/10/18 | 10/12/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 124.18 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 230.62 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 10/10/18 | 10/12/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 380.3 |  | 0 | 0
995 | Payroll Burden | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 240.6 |  | 0 | 0
995 | Payroll Burden | PR | 437 | 10/17/18 | 10/19/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 463 | 10/17/18 | 10/19/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 275.41 |  | 0 | 0
995 | Payroll Burden | PR | 479 | 10/17/18 | 10/19/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 491 | 10/17/18 | 10/19/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 345.93 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 10/17/18 | 10/19/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 294.93 |  | 0 | 0
995 | Payroll Burden | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 745 | 10/24/18 | 10/26/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 292.71 |  | 0 | 0
995 | Payroll Burden | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 35.48 |  | 0 | 0
995 | Payroll Burden | PR | 762 | 10/24/18 | 10/26/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 403.59 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 326.42 |  | 0 | 0
995 | Payroll Burden | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 227.07 |  | 0 | 0
995 | Payroll Burden | PR | 34 | 10/31/18 | 11/02/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 10/31/18 | 11/02/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 26.61 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 13.31 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 10/31/18 | 11/02/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 543.29 |  | 0 | 0
995 | Payroll Burden | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 204.01 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 51 |  | 0 | 0
995 | Payroll Burden | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 132.61 |  | 0 | 0
995 | Payroll Burden | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 69.19 |  | 0 | 0
995 | Payroll Burden | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 62.09 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 434.63 |  | 0 | 0
995 | Payroll Burden | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 214.21 |  | 0 | 0
995 | Payroll Burden | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 112.21 |  | 0 | 0
995 | Payroll Burden | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 170.3 |  | 0 | 0
995 | Payroll Burden | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 127.73 |  | 0 | 0
995 | Payroll Burden | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 79.83 |  | 0 | 0
995 | Payroll Burden | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 341.5 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 31.93 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 415.12 |  | 0 | 0
995 | Payroll Burden | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 10.64 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.05 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 411.35 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 15.52 |  | 0 | 0
995 | Payroll Burden | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 91.8 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 40.8 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 224.41 |  | 0 | 0
995 | Payroll Burden | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 397.38 |  | 0 | 0
995 | Payroll Burden | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 645 | 11/21/18 | 11/21/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 255.46 |  | 0 | 0
995 | Payroll Burden | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 95.8 |  | 0 | 0
995 | Payroll Burden | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 672 | 11/21/18 | 11/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 15.97 |  | 0 | 0
995 | Payroll Burden | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 425.76 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 93.14 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 139.7 |  | 0 | 0
995 | Payroll Burden | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 836 | 11/28/18 | 11/30/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 468.34 |  | 0 | 0
995 | Payroll Burden | PR | 858 | 11/28/18 | 11/30/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 160.1 |  | 0 | 0
995 | Payroll Burden | PR | 873 | 11/28/18 | 11/30/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 368.99 |  | 0 | 0
995 | Payroll Burden | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 285.61 |  | 0 | 0
995 | Payroll Burden | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 10.2 |  | 0 | 0
995 | Payroll Burden | PR | 890 | 11/28/18 | 11/30/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 354.8 |  | 0 | 0
995 | Payroll Burden | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 213.32 |  | 0 | 0
995 | Payroll Burden | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 213.32 |  | 0 | 0
995 | Payroll Burden | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 266.1 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 47 | 12/05/18 | 12/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 50 | 12/05/18 | 12/07/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 85 | 12/05/18 | 12/07/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 102 | 12/05/18 | 12/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 82.05 |  | 0 | 0
995 | Payroll Burden | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | -496.72 |  | 0 | 0
995 | Payroll Burden | PR | 129 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 496.72 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 273 | 12/12/18 | 12/14/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 585.42 |  | 0 | 0
995 | Payroll Burden | PR | 310 | 12/12/18 | 12/14/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 461.24 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 275.41 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 12/12/18 | 12/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 82.05 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 92.25 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 199.58 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 514 | 12/19/18 | 12/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 234.17 |  | 0 | 0
995 | Payroll Burden | PR | 550 | 12/19/18 | 12/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 426.65 |  | 0 | 0
995 | Payroll Burden | PR | 562 | 12/19/18 | 12/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 377.42 |  | 0 | 0
995 | Payroll Burden | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 278.96 |  | 0 | 0
995 | Payroll Burden | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 82.05 |  | 0 | 0
995 | Payroll Burden | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 702 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 741 | 12/26/18 | 12/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 299.81 |  | 0 | 0
995 | Payroll Burden | PR | 753 | 12/26/18 | 12/28/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 183.61 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 114.87 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 180.5 |  | 0 | 0
995 | Payroll Burden | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 01/02/19 | 01/04/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 310.45 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 01/02/19 | 01/04/19 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 322.87 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/02/19 | 01/04/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 131.28 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 321.54 |  | 0 | 0
995 | Payroll Burden | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 266 | 01/09/19 | 01/11/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 410.24 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 196.91 |  | 0 | 0
995 | Payroll Burden | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 468 | 01/16/19 | 01/18/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 443.5 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 01/16/19 | 01/18/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 408.02 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 459.47 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 65.64 |  | 0 | 0
995 | Payroll Burden | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 133.05 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 718 | 01/23/19 | 01/25/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 122.41 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 163.21 |  | 0 | 0
995 | Payroll Burden | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 244.81 |  | 0 | 0
995 | Payroll Burden | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 254.35 |  | 0 | 0
995 | Payroll Burden | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 508.69 |  | 0 | 0
995 | Payroll Burden | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 410.24 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 132.61 |  | 0 | 0
995 | Payroll Burden | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 81.6 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 278.96 |  | 0 | 0
995 | Payroll Burden | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 38.81 |  | 0 | 0
995 | Payroll Burden | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 138.59 |  | 0 | 0
995 | Payroll Burden | PR | 162 | 02/06/19 | 02/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 142.81 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 344.6 |  | 0 | 0
995 | Payroll Burden | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 373 | 02/13/19 | 02/15/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 102.01 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 262.55 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.41 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 255.01 |  | 0 | 0
995 | Payroll Burden | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 166.31 |  | 0 | 0
995 | Payroll Burden | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 255.01 |  | 0 | 0
995 | Payroll Burden | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 234.61 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 410.24 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 311.78 |  | 0 | 0
995 | Payroll Burden | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 116.42 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 127.51 |  | 0 | 0
995 | Payroll Burden | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 265.21 |  | 0 | 0
995 | Payroll Burden | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 98.46 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 213.32 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 98.46 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 46.12 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 121.96 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 243.93 |  | 0 | 0
995 | Payroll Burden | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
995 | Payroll Burden | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 71.4 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 49.23 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 172.3 |  | 0 | 0
995 | Payroll Burden | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 388.06 |  | 0 | 0
995 | Payroll Burden | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 21.73 |  | 0 | 0
995 | Payroll Burden | PR | 545 | 03/13/19 | 03/15/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 193.81 |  | 0 | 0
995 | Payroll Burden | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 311.78 |  | 0 | 0
995 | Payroll Burden | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.82 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.29 |  | 0 | 0
995 | Payroll Burden | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
995 | Payroll Burden | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 20.4 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 147.69 |  | 0 | 0
995 | Payroll Burden | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 24.61 |  | 0 | 0
995 | Payroll Burden | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -65.19 |  | 0 | 0
995 | Payroll Burden | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 119.52 |  | 0 | 0
995 | Payroll Burden | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 340.61 |  | 0 | 0
995 | Payroll Burden | PR | 98 | 04/03/19 | 04/05/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 177.4 |  | 0 | 0
995 | Payroll Burden | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 217.32 |  | 0 | 0
995 | Payroll Burden | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 31.27 |  | 0 | 0
995 | Payroll Burden | PR | 137 | 04/03/19 | 04/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 23.06 |  | 0 | 0
995 | Payroll Burden | PR | 342 | 04/10/19 | 04/12/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 432.41 |  | 0 | 0
995 | Payroll Burden | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 381 | 04/10/19 | 04/12/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 567.68 |  | 0 | 0
995 | Payroll Burden | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 539 | 04/17/19 | 04/19/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 87.81 |  | 0 | 0
995 | Payroll Burden | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 85.15 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.58 |  | 0 | 0
995 | Payroll Burden | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 454.14 |  | 0 | 0
995 | Payroll Burden | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 587 | 04/17/19 | 04/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 593 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 1.77 |  | 0 | 0
995 | Payroll Burden | PR | 594 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | -1.77 |  | 0 | 0
995 | Payroll Burden | PR | 595 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 70.96 |  | 0 | 0
995 | Payroll Burden | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 83.16 |  | 0 | 0
995 | Payroll Burden | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 76.06 |  | 0 | 0
995 | Payroll Burden | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 319.32 |  | 0 | 0
995 | Payroll Burden | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 283.84 |  | 0 | 0
995 | Payroll Burden | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 166.31 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 26 | 05/01/19 | 05/03/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 287.39 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 119.52 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 77.61 |  | 0 | 0
995 | Payroll Burden | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 46.57 |  | 0 | 0
995 | Payroll Burden | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 160.1 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 191.59 |  | 0 | 0
995 | Payroll Burden | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 113.54 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 419.11 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 65.19 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 269.65 |  | 0 | 0
995 | Payroll Burden | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 63.86 |  | 0 | 0
995 | Payroll Burden | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 56.77 |  | 0 | 0
995 | Payroll Burden | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 17.96 |  | 0 | 0
995 | Payroll Burden | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 383.18 |  | 0 | 0
995 | Payroll Burden | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 58.54 |  | 0 | 0
995 | Payroll Burden | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 117.08 |  | 0 | 0
995 | Payroll Burden | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 43.46 |  | 0 | 0
995 | Payroll Burden | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 248.36 |  | 0 | 0
995 | Payroll Burden | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 134.82 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 155.23 |  | 0 | 0
995 | Payroll Burden | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 8.98 |  | 0 | 0
995 | Payroll Burden | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 478.98 |  | 0 | 0
995 | Payroll Burden | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 108.66 |  | 0 | 0
995 | Payroll Burden | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 186.27 |  | 0 | 0
995 | Payroll Burden | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 202.24 |  | 0 | 0
995 | Payroll Burden | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 155.67 |  | 0 | 0
995 | Payroll Burden | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 152.12 |  | 0 | 0
995 | Payroll Burden | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 71.85 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 73.18 |  | 0 | 0
995 | Payroll Burden | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 43.91 |  | 0 | 0
995 | Payroll Burden | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 110.88 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 88.7 |  | 0 | 0
995 | Payroll Burden | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 23.95 |  | 0 | 0
995 | Payroll Burden | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 146.36 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 29.27 |  | 0 | 0
995 | Payroll Burden | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 175.63 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 47.9 |  | 0 | 0
995 | Payroll Burden | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 44.35 |  | 0 | 0
995 | Payroll Burden | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 55.44 |  | 0 | 0
995 | Payroll Burden | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 66.53 |  | 0 | 0
995 | Payroll Burden | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 22.18 |  | 0 | 0
995 | Payroll Burden | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 27.72 |  | 0 | 0
997 | Employee Benefits | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 144 | 21570 | 0 | 0
998 | Payroll Taxes | PR | 449 | 02/14/18 | 02/16/18 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 02/14/18 | 02/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 57.38 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 02/14/18 | 02/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 02/21/18 | 02/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 67 | 02/28/18 | 03/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 03/07/18 | 03/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 33.47 |  | 0 | 0
998 | Payroll Taxes | PR | 184 | 03/07/18 | 03/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.6 |  | 0 | 0
998 | Payroll Taxes | PR | 384 | 03/14/18 | 03/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 520 | 03/21/18 | 03/23/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 583 | 03/21/18 | 03/23/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 03/28/18 | 03/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 03/28/18 | 03/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 15 | 04/04/18 | 04/06/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 28.61 |  | 0 | 0
998 | Payroll Taxes | PR | 80 | 04/04/18 | 04/06/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 04/04/18 | 04/06/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.3 |  | 0 | 0
998 | Payroll Taxes | PR | 84 | 04/04/18 | 04/06/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 04/04/18 | 04/06/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 263 | 04/11/18 | 04/13/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 333 | 04/11/18 | 04/13/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 334 | 04/11/18 | 04/13/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 13.46 |  | 0 | 0
998 | Payroll Taxes | PR | 450 | 04/18/18 | 04/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 517 | 04/18/18 | 04/20/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 518 | 04/18/18 | 04/20/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 617 | 04/25/18 | 04/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 05/02/18 | 05/04/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 6.73 |  | 0 | 0
998 | Payroll Taxes | PR | 98 | 05/02/18 | 05/04/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 99 | 05/02/18 | 05/04/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 230 | 05/09/18 | 05/11/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 261 | 05/09/18 | 05/11/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 12.85 |  | 0 | 0
998 | Payroll Taxes | PR | 286 | 05/09/18 | 05/11/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 287 | 05/09/18 | 05/11/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 426 | 05/16/18 | 05/18/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 43.76 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 05/16/18 | 05/18/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 31.82 |  | 0 | 0
998 | Payroll Taxes | PR | 489 | 05/16/18 | 05/18/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 05/16/18 | 05/18/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 05/23/18 | 05/25/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 05/23/18 | 05/25/18 | WE55 | Wennig, Johnathan M | 0 | 0 | 0 | 0 | 19.89 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 7.8 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 05/23/18 | 05/25/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 41.62 |  | 0 | 0
998 | Payroll Taxes | PR | 806 | 05/23/18 | 05/25/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 05/23/18 | 05/25/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 05/30/18 | 06/01/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 05/30/18 | 06/01/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 05/30/18 | 06/01/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 06/06/18 | 06/08/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.37 |  | 0 | 0
998 | Payroll Taxes | PR | 339 | 06/06/18 | 06/08/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 06/06/18 | 06/08/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 06/13/18 | 06/15/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 06/13/18 | 06/15/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 527 | 06/13/18 | 06/15/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 06/13/18 | 06/15/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 957 | 06/27/18 | 06/29/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 993 | 06/27/18 | 06/29/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 1018 | 06/27/18 | 06/29/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.68 |  | 0 | 0
998 | Payroll Taxes | PR | 365 | 07/11/18 | 07/13/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.68 |  | 0 | 0
998 | Payroll Taxes | PR | 441 | 07/18/18 | 07/20/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 506 | 07/18/18 | 07/20/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.68 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 07/25/18 | 07/27/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 49.27 |  | 0 | 0
998 | Payroll Taxes | PR | 807 | 07/25/18 | 07/27/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 833 | 07/25/18 | 07/27/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 72.29 |  | 0 | 0
998 | Payroll Taxes | PR | 834 | 07/25/18 | 07/27/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 08/01/18 | 08/03/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 08/01/18 | 08/03/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 08/01/18 | 08/03/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 216 | 08/08/18 | 08/10/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 08/08/18 | 08/10/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 538 | 08/15/18 | 08/17/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 549 | 08/15/18 | 08/17/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 746 | 08/22/18 | 08/24/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 784 | 08/22/18 | 08/24/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 9.95 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 08/22/18 | 08/24/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 810 | 08/22/18 | 08/24/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 811 | 08/22/18 | 08/24/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 1000 | 08/29/18 | 08/31/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 1064 | 08/29/18 | 08/31/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 09/05/18 | 09/07/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 104 | 09/05/18 | 09/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 106 | 09/05/18 | 09/07/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 8.8 |  | 0 | 0
998 | Payroll Taxes | PR | 271 | 09/12/18 | 09/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 09/12/18 | 09/14/18 | HE70 | Hernandez Gonzalez, Osbaldo | 0 | 0 | 0 | 0 | 24.48 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 58.14 |  | 0 | 0
998 | Payroll Taxes | PR | 325 | 09/12/18 | 09/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 3.06 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 337 | 09/12/18 | 09/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 09/12/18 | 09/14/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 09/19/18 | 09/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 486 | 09/19/18 | 09/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 538 | 09/19/18 | 09/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 50.87 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 09/19/18 | 09/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 552 | 09/19/18 | 09/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 553 | 09/19/18 | 09/21/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 669 | 09/26/18 | 09/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 711 | 09/26/18 | 09/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 723 | 09/26/18 | 09/28/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 56.61 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 69.62 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 736 | 09/26/18 | 09/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 09/26/18 | 09/28/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 740 | 09/26/18 | 09/28/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 33 | 10/03/18 | 10/05/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 10/03/18 | 10/05/18 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 23.87 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 47.74 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 10/03/18 | 10/05/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 87 | 10/03/18 | 10/05/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 16.83 |  | 0 | 0
998 | Payroll Taxes | PR | 92 | 10/03/18 | 10/05/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 50.87 |  | 0 | 0
998 | Payroll Taxes | PR | 100 | 10/03/18 | 10/05/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.68 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 10/03/18 | 10/05/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 2.39 |  | 0 | 0
998 | Payroll Taxes | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 238 | 10/10/18 | 10/12/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 59.82 |  | 0 | 0
998 | Payroll Taxes | PR | 239 | 10/10/18 | 10/12/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 10/10/18 | 10/12/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 21.42 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 10/10/18 | 10/12/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 39.78 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 10/10/18 | 10/12/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 65.6 |  | 0 | 0
998 | Payroll Taxes | PR | 306 | 10/10/18 | 10/12/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 41.5 |  | 0 | 0
998 | Payroll Taxes | PR | 437 | 10/17/18 | 10/19/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 10/17/18 | 10/19/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 441 | 10/17/18 | 10/19/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 463 | 10/17/18 | 10/19/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 47.51 |  | 0 | 0
998 | Payroll Taxes | PR | 479 | 10/17/18 | 10/19/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 491 | 10/17/18 | 10/19/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 59.67 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 10/17/18 | 10/19/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 50.87 |  | 0 | 0
998 | Payroll Taxes | PR | 505 | 10/17/18 | 10/19/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 507 | 10/17/18 | 10/19/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 508 | 10/17/18 | 10/19/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 705 | 10/24/18 | 10/26/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 10/24/18 | 10/26/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 730 | 10/24/18 | 10/26/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 745 | 10/24/18 | 10/26/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 50.49 |  | 0 | 0
998 | Payroll Taxes | PR | 756 | 10/24/18 | 10/26/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 6.12 |  | 0 | 0
998 | Payroll Taxes | PR | 762 | 10/24/18 | 10/26/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 69.62 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 771 | 10/24/18 | 10/26/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 10/24/18 | 10/26/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 56.3 |  | 0 | 0
998 | Payroll Taxes | PR | 8 | 10/31/18 | 11/02/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 10/31/18 | 11/02/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 39.17 |  | 0 | 0
998 | Payroll Taxes | PR | 34 | 10/31/18 | 11/02/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 10/31/18 | 11/02/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 2.3 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 60 | 10/31/18 | 11/02/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 65 | 10/31/18 | 11/02/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 10/31/18 | 11/02/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 93.71 |  | 0 | 0
998 | Payroll Taxes | PR | 76 | 10/31/18 | 11/02/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 77 | 10/31/18 | 11/02/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 35.19 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 8.8 |  | 0 | 0
998 | Payroll Taxes | PR | 186 | 11/07/18 | 11/09/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 22.87 |  | 0 | 0
998 | Payroll Taxes | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 189 | 11/07/18 | 11/09/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 212 | 11/07/18 | 11/09/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 11/07/18 | 11/09/18 | KI55 | Kinssies, Jr, John E | 0 | 0 | 0 | 0 | 11.93 |  | 0 | 0
998 | Payroll Taxes | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 228 | 11/07/18 | 11/09/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 240 | 11/07/18 | 11/09/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 245 | 11/07/18 | 11/09/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 10.71 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 253 | 11/07/18 | 11/09/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 74.97 |  | 0 | 0
998 | Payroll Taxes | PR | 257 | 11/07/18 | 11/09/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 258 | 11/07/18 | 11/09/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 13.2 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 36.95 |  | 0 | 0
998 | Payroll Taxes | PR | 434 | 11/14/18 | 11/16/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.35 |  | 0 | 0
998 | Payroll Taxes | PR | 435 | 11/14/18 | 11/16/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 29.38 |  | 0 | 0
998 | Payroll Taxes | PR | 438 | 11/14/18 | 11/16/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 460 | 11/14/18 | 11/16/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 22.03 |  | 0 | 0
998 | Payroll Taxes | PR | 476 | 11/14/18 | 11/16/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 488 | 11/14/18 | 11/16/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 58.91 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 5.51 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 71.6 |  | 0 | 0
998 | Payroll Taxes | PR | 493 | 11/14/18 | 11/16/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 1.84 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.36 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 70.95 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.68 |  | 0 | 0
998 | Payroll Taxes | PR | 501 | 11/14/18 | 11/16/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 513 | 11/14/18 | 11/16/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 11/14/18 | 11/16/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 7.04 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 38.71 |  | 0 | 0
998 | Payroll Taxes | PR | 620 | 11/21/18 | 11/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 621 | 11/21/18 | 11/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 68.54 |  | 0 | 0
998 | Payroll Taxes | PR | 624 | 11/21/18 | 11/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 645 | 11/21/18 | 11/21/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 44.06 |  | 0 | 0
998 | Payroll Taxes | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 16.52 |  | 0 | 0
998 | Payroll Taxes | PR | 660 | 11/21/18 | 11/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 672 | 11/21/18 | 11/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 2.75 |  | 0 | 0
998 | Payroll Taxes | PR | 677 | 11/21/18 | 11/21/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 73.44 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.07 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 685 | 11/21/18 | 11/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 24.1 |  | 0 | 0
998 | Payroll Taxes | PR | 689 | 11/21/18 | 11/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 832 | 11/28/18 | 11/30/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 836 | 11/28/18 | 11/30/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 80.78 |  | 0 | 0
998 | Payroll Taxes | PR | 858 | 11/28/18 | 11/30/18 | GU78 | Gutierrez Salas, Jose | 0 | 0 | 0 | 0 | 27.62 |  | 0 | 0
998 | Payroll Taxes | PR | 873 | 11/28/18 | 11/30/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 63.65 |  | 0 | 0
998 | Payroll Taxes | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 49.27 |  | 0 | 0
998 | Payroll Taxes | PR | 885 | 11/28/18 | 11/30/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 1.76 |  | 0 | 0
998 | Payroll Taxes | PR | 890 | 11/28/18 | 11/30/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 61.2 |  | 0 | 0
998 | Payroll Taxes | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 36.8 |  | 0 | 0
998 | Payroll Taxes | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 36.8 |  | 0 | 0
998 | Payroll Taxes | PR | 898 | 11/28/18 | 11/30/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 900 | 11/28/18 | 11/30/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 901 | 11/28/18 | 11/30/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 45.9 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 46 | 12/05/18 | 12/07/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 47 | 12/05/18 | 12/07/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 50 | 12/05/18 | 12/07/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 85 | 12/05/18 | 12/07/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 97 | 12/05/18 | 12/07/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 102 | 12/05/18 | 12/07/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 14.15 |  | 0 | 0
998 | Payroll Taxes | PR | 111 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 128 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | -85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 129 | 12/05/18 | 12/07/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 85.68 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 269 | 12/12/18 | 12/14/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 273 | 12/12/18 | 12/14/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 100.98 |  | 0 | 0
998 | Payroll Taxes | PR | 310 | 12/12/18 | 12/14/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 79.56 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 322 | 12/12/18 | 12/14/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 47.51 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 12/12/18 | 12/14/18 | SI48 | Silva Morales, Jair J | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 14.15 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 336 | 12/12/18 | 12/14/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 338 | 12/12/18 | 12/14/18 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 15.91 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 34.43 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 510 | 12/19/18 | 12/21/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 511 | 12/19/18 | 12/21/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 514 | 12/19/18 | 12/21/18 | CA77 | Castro Hernandez, Jose A | 0 | 0 | 0 | 0 | 40.39 |  | 0 | 0
998 | Payroll Taxes | PR | 550 | 12/19/18 | 12/21/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 73.59 |  | 0 | 0
998 | Payroll Taxes | PR | 562 | 12/19/18 | 12/21/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 65.1 |  | 0 | 0
998 | Payroll Taxes | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 48.12 |  | 0 | 0
998 | Payroll Taxes | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 14.15 |  | 0 | 0
998 | Payroll Taxes | PR | 576 | 12/19/18 | 12/21/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 577 | 12/19/18 | 12/21/18 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 701 | 12/26/18 | 12/28/18 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 702 | 12/26/18 | 12/28/18 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 741 | 12/26/18 | 12/28/18 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 51.71 |  | 0 | 0
998 | Payroll Taxes | PR | 753 | 12/26/18 | 12/28/18 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 31.67 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 19.81 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 31.14 |  | 0 | 0
998 | Payroll Taxes | PR | 767 | 12/26/18 | 12/28/18 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 01/02/19 | 01/04/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 53.55 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 01/02/19 | 01/04/19 | ME53 | Mendoza Morales, Jesus A | 0 | 0 | 0 | 0 | 55.69 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/02/19 | 01/04/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 22.64 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 214 | 01/09/19 | 01/11/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 55.46 |  | 0 | 0
998 | Payroll Taxes | PR | 215 | 01/09/19 | 01/11/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 266 | 01/09/19 | 01/11/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 70.76 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 33.97 |  | 0 | 0
998 | Payroll Taxes | PR | 280 | 01/09/19 | 01/11/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 281 | 01/09/19 | 01/11/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 01/09/19 | 01/11/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 468 | 01/16/19 | 01/18/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 76.5 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 01/16/19 | 01/18/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 01/16/19 | 01/18/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 70.38 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 79.25 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 535 | 01/16/19 | 01/18/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 11.32 |  | 0 | 0
998 | Payroll Taxes | PR | 542 | 01/16/19 | 01/18/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 22.95 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 717 | 01/23/19 | 01/25/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 718 | 01/23/19 | 01/25/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 28.15 |  | 0 | 0
998 | Payroll Taxes | PR | 770 | 01/23/19 | 01/25/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 42.23 |  | 0 | 0
998 | Payroll Taxes | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 43.87 |  | 0 | 0
998 | Payroll Taxes | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 87.75 |  | 0 | 0
998 | Payroll Taxes | PR | 784 | 01/23/19 | 01/25/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 786 | 01/23/19 | 01/25/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 70.76 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 01/30/19 | 02/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 22.87 |  | 0 | 0
998 | Payroll Taxes | PR | 55 | 01/30/19 | 02/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 14.08 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 48.12 |  | 0 | 0
998 | Payroll Taxes | PR | 69 | 01/30/19 | 02/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 01/30/19 | 02/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 71 | 01/30/19 | 02/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 6.69 |  | 0 | 0
998 | Payroll Taxes | PR | 161 | 02/06/19 | 02/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 23.91 |  | 0 | 0
998 | Payroll Taxes | PR | 162 | 02/06/19 | 02/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 211 | 02/06/19 | 02/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 24.63 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 59.44 |  | 0 | 0
998 | Payroll Taxes | PR | 225 | 02/06/19 | 02/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 02/06/19 | 02/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 323 | 02/13/19 | 02/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 373 | 02/13/19 | 02/15/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 17.6 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 45.29 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 02/13/19 | 02/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 2.83 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 02/13/19 | 02/15/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 43.99 |  | 0 | 0
998 | Payroll Taxes | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 28.69 |  | 0 | 0
998 | Payroll Taxes | PR | 581 | 02/20/19 | 02/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 582 | 02/20/19 | 02/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 43.99 |  | 0 | 0
998 | Payroll Taxes | PR | 632 | 02/20/19 | 02/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 40.47 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 70.76 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 646 | 02/20/19 | 02/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 53.78 |  | 0 | 0
998 | Payroll Taxes | PR | 647 | 02/20/19 | 02/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 648 | 02/20/19 | 02/22/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 20.08 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 6 | 02/27/19 | 03/01/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 21.99 |  | 0 | 0
998 | Payroll Taxes | PR | 7 | 02/27/19 | 03/01/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 45.75 |  | 0 | 0
998 | Payroll Taxes | PR | 59 | 02/27/19 | 03/01/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.98 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 36.8 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 02/27/19 | 03/01/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 16.98 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 02/27/19 | 03/01/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 02/27/19 | 03/01/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 7.96 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 21.04 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 248 | 03/06/19 | 03/08/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 42.08 |  | 0 | 0
998 | Payroll Taxes | PR | 249 | 03/06/19 | 03/08/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 298 | 03/06/19 | 03/08/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 12.32 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 8.49 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 313 | 03/06/19 | 03/08/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 29.72 |  | 0 | 0
998 | Payroll Taxes | PR | 314 | 03/06/19 | 03/08/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 315 | 03/06/19 | 03/08/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 495 | 03/13/19 | 03/15/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 66.94 |  | 0 | 0
998 | Payroll Taxes | PR | 496 | 03/13/19 | 03/15/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 525 | 03/13/19 | 03/15/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.75 |  | 0 | 0
998 | Payroll Taxes | PR | 545 | 03/13/19 | 03/15/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 33.43 |  | 0 | 0
998 | Payroll Taxes | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 53.78 |  | 0 | 0
998 | Payroll Taxes | PR | 561 | 03/13/19 | 03/15/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 5.66 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 709 | 03/20/19 | 03/22/19 | BA68 | Barbosa, Michael S | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 710 | 03/20/19 | 03/22/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.67 |  | 0 | 0
998 | Payroll Taxes | PR | 739 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 758 | 03/20/19 | 03/22/19 | RO10 | Rodriguez Arevalos, Christian | 0 | 0 | 0 | 0 | 3.52 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 25.47 |  | 0 | 0
998 | Payroll Taxes | PR | 775 | 03/20/19 | 03/22/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 4.25 |  | 0 | 0
998 | Payroll Taxes | PR | 776 | 03/20/19 | 03/22/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 780 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 781 | 03/20/19 | 03/22/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | -11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 921 | 03/27/19 | 03/29/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 951 | 03/27/19 | 03/29/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 20.62 |  | 0 | 0
998 | Payroll Taxes | PR | 974 | 03/27/19 | 03/29/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 58.75 |  | 0 | 0
998 | Payroll Taxes | PR | 98 | 04/03/19 | 04/05/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 30.6 |  | 0 | 0
998 | Payroll Taxes | PR | 114 | 04/03/19 | 04/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 37.49 |  | 0 | 0
998 | Payroll Taxes | PR | 135 | 04/03/19 | 04/05/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 5.39 |  | 0 | 0
998 | Payroll Taxes | PR | 137 | 04/03/19 | 04/05/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 151 | 04/03/19 | 04/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 152 | 04/03/19 | 04/05/19 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 3.98 |  | 0 | 0
998 | Payroll Taxes | PR | 342 | 04/10/19 | 04/12/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 74.59 |  | 0 | 0
998 | Payroll Taxes | PR | 357 | 04/10/19 | 04/12/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 381 | 04/10/19 | 04/12/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 97.92 |  | 0 | 0
998 | Payroll Taxes | PR | 524 | 04/17/19 | 04/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 539 | 04/17/19 | 04/19/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 555 | 04/17/19 | 04/19/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 15.15 |  | 0 | 0
998 | Payroll Taxes | PR | 564 | 04/17/19 | 04/19/19 | MC09 | McCabe, Thomas C | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 578 | 04/17/19 | 04/19/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 14.69 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 7.34 |  | 0 | 0
998 | Payroll Taxes | PR | 580 | 04/17/19 | 04/19/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 78.34 |  | 0 | 0
998 | Payroll Taxes | PR | 586 | 04/17/19 | 04/19/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 587 | 04/17/19 | 04/19/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 593 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 0.31 |  | 0 | 0
998 | Payroll Taxes | PR | 594 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | -0.31 |  | 0 | 0
998 | Payroll Taxes | PR | 595 | 04/17/19 | 04/19/19 | WI46 | Wilson, Garret A | 0 | 0 | 0 | 0 | 12.24 |  | 0 | 0
998 | Payroll Taxes | PR | 596 | 04/17/19 | 04/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 14.34 |  | 0 | 0
998 | Payroll Taxes | PR | 744 | 04/24/19 | 04/26/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 774 | 04/24/19 | 04/26/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 797 | 04/24/19 | 04/26/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 13.12 |  | 0 | 0
998 | Payroll Taxes | PR | 799 | 04/24/19 | 04/26/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 803 | 04/24/19 | 04/26/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 55.08 |  | 0 | 0
998 | Payroll Taxes | PR | 804 | 04/24/19 | 04/26/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 48.96 |  | 0 | 0
998 | Payroll Taxes | PR | 812 | 04/24/19 | 04/26/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 28.69 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 11 | 05/01/19 | 05/03/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 26 | 05/01/19 | 05/03/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 49.57 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 42 | 05/01/19 | 05/03/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 66 | 05/01/19 | 05/03/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 20.62 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 13.39 |  | 0 | 0
998 | Payroll Taxes | PR | 68 | 05/01/19 | 05/03/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 70 | 05/01/19 | 05/03/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 27.62 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 05/01/19 | 05/03/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 33.05 |  | 0 | 0
998 | Payroll Taxes | PR | 74 | 05/01/19 | 05/03/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 19.58 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 05/01/19 | 05/03/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 164 | 05/08/19 | 05/10/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 179 | 05/08/19 | 05/10/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 72.29 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 05/08/19 | 05/10/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 219 | 05/08/19 | 05/10/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 11.25 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 05/08/19 | 05/10/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 46.51 |  | 0 | 0
998 | Payroll Taxes | PR | 226 | 05/08/19 | 05/10/19 | TR60 | Trower-Kelly, Fidel D | 0 | 0 | 0 | 0 | 11.02 |  | 0 | 0
998 | Payroll Taxes | PR | 227 | 05/08/19 | 05/10/19 | VA98 | Vazquez Popoca, Jose N | 0 | 0 | 0 | 0 | 9.79 |  | 0 | 0
998 | Payroll Taxes | PR | 234 | 05/08/19 | 05/10/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 395 | 05/15/19 | 05/17/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 3.1 |  | 0 | 0
998 | Payroll Taxes | PR | 411 | 05/15/19 | 05/17/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 66.1 |  | 0 | 0
998 | Payroll Taxes | PR | 427 | 05/15/19 | 05/17/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 10.1 |  | 0 | 0
998 | Payroll Taxes | PR | 436 | 05/15/19 | 05/17/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 20.2 |  | 0 | 0
998 | Payroll Taxes | PR | 451 | 05/15/19 | 05/17/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 7.5 |  | 0 | 0
998 | Payroll Taxes | PR | 452 | 05/15/19 | 05/17/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 42.84 |  | 0 | 0
998 | Payroll Taxes | PR | 455 | 05/15/19 | 05/17/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 23.26 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 05/15/19 | 05/17/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 26.78 |  | 0 | 0
998 | Payroll Taxes | PR | 608 | 05/22/19 | 05/24/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 1.55 |  | 0 | 0
998 | Payroll Taxes | PR | 623 | 05/22/19 | 05/24/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 82.62 |  | 0 | 0
998 | Payroll Taxes | PR | 663 | 05/22/19 | 05/24/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 18.74 |  | 0 | 0
998 | Payroll Taxes | PR | 664 | 05/22/19 | 05/24/19 | SE64 | Sepulveda Gonzalez, Alfredo | 0 | 0 | 0 | 0 | 32.13 |  | 0 | 0
998 | Payroll Taxes | PR | 667 | 05/22/19 | 05/24/19 | ST02 | Stahlschmidt, John P | 0 | 0 | 0 | 0 | 34.88 |  | 0 | 0
998 | Payroll Taxes | PR | 680 | 05/22/19 | 05/24/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 881 | 05/29/19 | 05/31/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 897 | 05/29/19 | 05/31/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 26.85 |  | 0 | 0
998 | Payroll Taxes | PR | 913 | 05/29/19 | 05/31/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 937 | 05/29/19 | 05/31/19 | SA54 | Sanders, Allen O | 0 | 0 | 0 | 0 | 26.24 |  | 0 | 0
998 | Payroll Taxes | PR | 952 | 05/29/19 | 05/31/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 183 | 06/05/19 | 06/07/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 06/05/19 | 06/07/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 12.39 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 12.62 |  | 0 | 0
998 | Payroll Taxes | PR | 223 | 06/05/19 | 06/07/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 7.57 |  | 0 | 0
998 | Payroll Taxes | PR | 254 | 06/05/19 | 06/07/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 19.13 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 454 | 06/12/19 | 06/14/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 15.3 |  | 0 | 0
998 | Payroll Taxes | PR | 469 | 06/12/19 | 06/14/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 4.13 |  | 0 | 0
998 | Payroll Taxes | PR | 483 | 06/12/19 | 06/14/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 25.25 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 5.05 |  | 0 | 0
998 | Payroll Taxes | PR | 492 | 06/12/19 | 06/14/19 | MA71 | Martinez Reyes, Juan C | 0 | 0 | 0 | 0 | 30.29 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 622 | 06/19/19 | 06/21/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 639 | 06/19/19 | 06/21/19 | EL33 | Eliassen, Cory H | 0 | 0 | 0 | 0 | 8.26 |  | 0 | 0
998 | Payroll Taxes | PR | 840 | 06/26/19 | 06/28/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 44 | 07/03/19 | 07/05/19 | HU06 | Hubbard, Robert W | 0 | 0 | 0 | 0 | 7.65 |  | 0 | 0
998 | Payroll Taxes | PR | 81 | 07/03/19 | 07/05/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 9.56 |  | 0 | 0
998 | Payroll Taxes | PR | 282 | 07/10/19 | 07/12/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 512 | 07/17/19 | 07/19/19 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 3.83 |  | 0 | 0
998 | Payroll Taxes | PR | 585 | 07/17/19 | 07/19/19 | DO56 | Donelson, Richard T | 0 | 0 | 0 | 0 | 4.78 |  | 0 | 0
999 | Sales | AR | 547 | 04/20/18 | 04/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -28000 | 037068 | 0 | -1400
999 | Sales | AR | 547 | 04/20/18 | 04/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -5900 | 037068 | 0 | -295
999 | Sales | AR | 547 | 04/20/18 | 04/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -12000 | 037068 | 0 | -600
999 | Sales | AR | 505 | 05/18/18 | 05/18/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -35800 | 037083 | 0 | -1790
999 | Sales | AR | 671 | 06/20/18 | 06/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2700 | 037110 | 0 | -135
999 | Sales | AR | 671 | 06/20/18 | 06/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -12900 | 037110 | 0 | -645
999 | Sales | AR | 671 | 06/20/18 | 06/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2533 | 037110 | 0 | -126.65
999 | Sales | AR | 519 | 07/20/18 | 07/20/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -29200 | 037131 | 0 | -1460
999 | Sales | AR | 466 | 09/19/18 | 09/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -7500 | 037182 | 0 | -375
999 | Sales | AR | 466 | 09/19/18 | 09/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -13080 | 037182 | 0 | -654
999 | Sales | AR | 466 | 09/19/18 | 09/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -23430 | 037182 | 0 | -1171.5
999 | Sales | AR | 466 | 09/19/18 | 09/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4295 | 037182 | 0 | -214.75
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -26160 | 037205 | 0 | -1308
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -46860 | 037205 | 0 | -2343
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -3135 | 037205 | 0 | -156.75
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -60130 | 037205 | 0 | -3006.5
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9500 | 037205 | 0 | -475
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -68720 | 037205 | 0 | -3436
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8900 | 037205 | 0 | -445
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -42950 | 037205 | 0 | -2147.5
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9100 | 037205 | 0 | -455
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8900 | 037205 | 0 | -445
999 | Sales | AR | 519 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9100 | 037205 | 0 | -455
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 26160 | 037220 | 0 | 1308
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 46860 | 037220 | 0 | 2343
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 3135 | 037220 | 0 | 156.75
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 60130 | 037220 | 0 | 3006.5
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 9500 | 037220 | 0 | 475
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 68720 | 037220 | 0 | 3436
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8900 | 037220 | 0 | 445
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 42950 | 037220 | 0 | 2147.5
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 9100 | 037220 | 0 | 455
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8900 | 037220 | 0 | 445
999 | Sales | AR | 698 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 9100 | 037220 | 0 | 455
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -26160 | 037221 | 0 | -1308
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -46860 | 037221 | 0 | -2343
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -3135 | 037221 | 0 | -156.75
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -64425 | 037221 | 0 | -3221.25
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9500 | 037221 | 0 | -475
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -68720 | 037221 | 0 | -3436
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8900 | 037221 | 0 | -445
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -42950 | 037221 | 0 | -2147.5
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9100 | 037221 | 0 | -455
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8900 | 037221 | 0 | -445
999 | Sales | AR | 699 | 10/19/18 | 10/19/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9100 | 037221 | 0 | -455
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4500 | 037227 | 0 | -225
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -7315 | 037227 | 0 | -365.75
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4900 | 037227 | 0 | -245
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037227 | 0 | -429.5
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037227 | 0 | -429.5
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -34360 | 037227 | 0 | -1718
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -77310 | 037227 | 0 | -3865.5
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -38250 | 037227 | 0 | -1912.5
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -5500 | 037227 | 0 | -275
999 | Sales | AR | 521 | 11/16/18 | 11/16/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2295 | 037227 | 0 | -114.75
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -62000 | 037249 | 0 | -3100
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4360 | 037249 | 0 | -218
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -7810 | 037249 | 0 | -390.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -10450 | 037249 | 0 | -522.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4900 | 037249 | 0 | -245
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037249 | 0 | -429.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037249 | 0 | -429.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037249 | 0 | -429.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037249 | 0 | -429.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4250 | 037249 | 0 | -212.5
999 | Sales | AR | 346 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2300 | 037249 | 0 | -115
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 62000 | 037262 | 0 | 3100
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 4360 | 037262 | 0 | 218
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 7810 | 037262 | 0 | 390.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 10450 | 037262 | 0 | 522.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 4900 | 037262 | 0 | 245
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8590 | 037262 | 0 | 429.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8590 | 037262 | 0 | 429.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8590 | 037262 | 0 | 429.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 8590 | 037262 | 0 | 429.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 4250 | 037262 | 0 | 212.5
999 | Sales | AR | 777 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | 2300 | 037262 | 0 | 115
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -62000 | 037263 | 0 | -3100
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4360 | 037263 | 0 | -218
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -7810 | 037263 | 0 | -390.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -10450 | 037263 | 0 | -522.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4900 | 037263 | 0 | -245
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037263 | 0 | -429.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037263 | 0 | -429.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037263 | 0 | -429.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8590 | 037263 | 0 | -429.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4250 | 037263 | 0 | -212.5
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2300 | 037263 | 0 | -115
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -3718 | 037263 | 0 | -185.9
999 | Sales | AR | 778 | 12/14/18 | 12/14/18 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2918 | 037263 | 0 | -145.9
999 | Sales | AR | 552 | 01/18/19 | 01/18/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2500 | 037270 | 0 | -125
999 | Sales | AR | 552 | 01/18/19 | 01/18/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2100 | 037270 | 0 | -105
999 | Sales | AR | 552 | 01/18/19 | 01/18/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2100 | 037270 | 0 | -105
999 | Sales | AR | 552 | 01/18/19 | 01/18/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2100 | 037270 | 0 | -105
999 | Sales | AR | 681 | 03/20/19 | 03/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -9730 | 037302 | 0 | -486.5
999 | Sales | AR | 681 | 03/20/19 | 03/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2600 | 037302 | 0 | -130
999 | Sales | AR | 681 | 03/20/19 | 03/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -2600 | 037302 | 0 | -130
999 | Sales | AR | 681 | 03/20/19 | 03/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -713 | 037302 | 0 | -35.65
999 | Sales | AR | 606 | 04/19/19 | 04/19/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -4170 | 037322 | 0 | -208.5
999 | Sales | AR | 606 | 04/19/19 | 04/19/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -12900 | 037322 | 0 | -645
999 | Sales | AR | 606 | 04/19/19 | 04/19/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -10300 | 037322 | 0 | -515
999 | Sales | AR | 606 | 04/19/19 | 04/19/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -10300 | 037322 | 0 | -515
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8100 | 037348 | 0 | -405
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -8600 | 037348 | 0 | -430
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -1600 | 037348 | 0 | -80
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -12900 | 037348 | 0 | -645
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -12900 | 037348 | 0 | -645
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -464 | 037348 | 0 | -23.2
999 | Sales | AR | 515 | 05/20/19 | 05/20/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -7565 | 037348 | 0 | -378.25
999 | Sales | AR | 604 | 06/19/19 | 06/19/19 | 2050CH | Compass General Construction I, LLC$2100 |  |  |  |  | -560 | 037360 | 0 | -28

## Crew Roster
CREW ROSTER — 22 WORKERS
Per-worker hours + wages grouped by tier (APPRENTICE / JOURNEYMAN / LEAD / OT-ONLY). nominal_rate = regular_amount ÷ regular_hours. Mirrors Sam Worker Wages tab.
Tier | Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Reg Amount | OT Amount | Nominal Rate ($/hr)
APPRENTICE/HELPER | Vazquez Popoca, Jose N | 72 | 0 | 0 | 1152 | 0 | 16
APPRENTICE/HELPER | Trower-Kelly, Fidel D | 80 | 0 | 0 | 1424 | 0 | 17.8
APPRENTICE/HELPER | Gutierrez Salas, Jose | 237.5 | 10 | 0 | 4294 | 270 | 18.08
APPRENTICE/HELPER | Stahlschmidt, John P | 91 | 0 | 0 | 1729 | 0 | 19
JOURNEYMAN | Hernandez Gonzalez, Osbaldo | 19 | 0 | 0 | 380 | 0 | 20
JOURNEYMAN | Rodriguez Arevalos, Christian | 838.5 | 25 | 0 | 18045 | 786 | 21.5206
JOURNEYMAN | Barbosa, Michael S | 974 | 27 | 0 | 23562 | 955.5 | 24.191
JOURNEYMAN | Silva Morales, Jair J | 416 | 22 | 0 | 10096 | 792 | 24.2692
JOURNEYMAN | Mendoza Morales, Jesus A | 540 | 22 | 0 | 13366 | 792 | 24.7519
JOURNEYMAN | Wennig, Johnathan M | 31 | 0 | 0 | 806 | 0 | 26
JOURNEYMAN | Kinssies, Jr, John E | 6 | 0 | 0 | 156 | 0 | 26
JOURNEYMAN | Eliassen, Cory H | 219 | 1.5 | 0 | 5787 | 60.75 | 26.4247
JOURNEYMAN | Martinez Reyes, Juan C | 96 | 0 | 0 | 2888 | 0 | 30.0833
JOURNEYMAN | Castro Hernandez, Jose A | 342 | 21 | 0 | 11072 | 1008 | 32.3743
JOURNEYMAN | Sepulveda Gonzalez, Alfredo | 191 | 6 | 0 | 6268 | 288 | 32.8168
JOURNEYMAN | Wilson, Garret A | 1009.5 | 2 | 0 | 33657.5 | 102 | 33.3408
LEAD/SUPERVISOR | Hubbard, Robert W | 58 | 0 | 0 | 2570.5 | 0 | 44.319
LEAD/SUPERVISOR | Barnhart, Joseph N | 189 | 2 | 0 | 8872 | 132 | 46.9418
LEAD/SUPERVISOR | Sanders, Allen O | 29.5 | 0 | 0 | 1442.5 | 0 | 48.8983
LEAD/SUPERVISOR | Gerard, Jeffrey S | 48.5 | 0 | 0 | 2444 | 0 | 50.3918
LEAD/SUPERVISOR | Donelson, Richard T | 131.5 | 0 | 0 | 8218.75 | 0 | 62.5
OT-ONLY | McCabe, Thomas C | 0 | 6 | 0 | 0 | 297 | — (no reg hours)

## Wage Tiers
WAGE TIERS & PERCENTILES — 2050
Tier distribution + percentile snapshot across worker_nominal_wages. Tier thresholds: Apprentice <$20, Journeyman $20–$36, Lead $36+. OT-only = no regular hours booked.
Tier | Worker Count | Total Reg Hours | Total OT Hours | Total Labor $ | Avg Nominal Rate
APPRENTICE/HELPER | 4 | 480.5 | 10 | 8869 | 17.72
JOURNEYMAN | 12 | 4682 | 126.5 | 130867.75 | 26.8144
LEAD/SUPERVISOR | 5 | 456.5 | 2 | 23679.75 | 50.6102
OT-ONLY | 1 | 0 | 6 | 297 | 0
PERCENTILES (nominal wage)
Percentile | Rate
p10 | 18.08
p25 | 21.52
p50 | 26
p75 | 33.34
p90 | 48.9
WAGE METHODOLOGY (Sam v4 Action #3)
Metric | Value | Formula
straight_time_rate | 28.1599 | SUM(regular_amount) / SUM(regular_hours)
pr_src_cost_per_hr | 43.214 | PR total / total_labor_hours (includes OT premium)
fully_loaded_wage | 57.9979 | (PR + 995 + 998) / total_labor_hours
burden_multiplier | 1.3421 | fully_loaded / pr_src_cost_per_hr

## Productivity
PRODUCTIVITY METRICS — 2050
Labor throughput + unit-economics indicators. Per-unit / per-fixture / per-month now populated from GDrive-enriched project attributes.
Metric | Value | Formula / Notes
Total Labor Hours | 5,763.50 | SUM(reg+ot+dt+other) where source=PR
Revenue per Labor Hour | $159.38 | abs(revenue) ÷ labor hours — throughput
Labor Unit Cost per Hour | $28.37 | Labor-code JTD ÷ labor hours
Revenue ÷ Labor-Cost Ratio | 5.62x | Throughput ÷ unit cost — productivity signal
Units (residential) | 50 | Compass 2100 E Madison Apartments scope doc: 47 Type B + 3 Type A ADA
Fixtures (estimate) | 395 | Scope doc estimate — see Job Info fixture_estimate_note
Duration (months) | 18 | start_date → end_date from GDrive enrichment
Hours per Unit | 115.27 | total_labor_hours ÷ units
Hours per Fixture | 14.59 | total_labor_hours ÷ fixtures
Revenue per Unit | $18,371 | revenue ÷ units
Profit per Unit | $8,536 | net_profit ÷ units
Hours per Month | 320 | total_labor_hours ÷ duration_months
Revenue per Month | $51,031 | revenue ÷ duration_months

## Vendor Analysis
VENDOR ANALYSIS — 23 VENDORS ($219,925 AP)
AP-source vendor spend concentration. Sorted by descending spend. Top-vendor % surfaces concentration risk. Matches Sam derived_field.top_vendor_spend.
Rank | Vendor | Spend | Invoice Count | Avg Invoice | % of AP | Net Due | Retainage
1 | Ferguson Enterprises, Inc. #3007 | 70586.95 | 63 | 1120.4278 | 32.1% | 0 | 0
2 | Rosen Supply Kirkland | 57147.75 | 61 | 936.8484 | 25.99% | 0 | 0
3 | California Hydronics Corp | 20873 | 5 | 4174.6 | 9.491% | 0 | 0
4 | Consolidated Supply Co. | 17263.16 | 21 | 822.0552 | 7.85% | 0 | 0
5 | Franklin Engineering | 17024 | 5 | 3404.8 | 7.741% | 0 | 0
6 | Capital One Credit Card | 9316.2 | 25 | 372.648 | 4.236% | 0 | 0
7 | Ferguson Enterprises, Inc. $Madison | 6247.95 | 1 | 6247.95 | 2.841% | 0 | 0
8 | Mechanical Resource Services, Inc. | 4375 | 1 | 4375 | 1.989% | 0 | 0
9 | Ahern Rentals | 3911.37 | 10 | 391.137 | 1.778% | 0 | 0
10 | Keller Supply Company | 3504.56 | 9 | 389.3956 | 1.594% | 0 | 0
11 | Rosen Supply Company, Inc. $E Madison | 2263.23 | 3 | 754.41 | 1.029% | 0 | 0
12 | Quality Concrete Products, Inc. $32 | 2095 | 1 | 2095 | 0.9526% | 0 | 0
13 | Chip Away Bathtub Repair, Inc. | 1300 | 3 | 433.3333 | 0.5911% | 0 | 0
14 | Mechanical Sales, Inc. | 973.71 | 2 | 486.855 | 0.4427% | 0 | 0
15 | Bank of America CC | 618.03 | 3 | 206.01 | 0.281% | 0 | 0
16 | Scan2Core, Inc. | 615 | 1 | 615 | 0.2796% | 0 | 0
17 | Old Castle Infrastructure, Inc. | 595 | 1 | 595 | 0.2705% | 0 | 0
18 | Core & Main LP $HD Supply Waterworks | 315.79 | 2 | 157.895 | 0.1436% | 0 | 0
19 | Keller Supply Co. $E Madison | 278.42 | 1 | 278.42 | 0.1266% | 0 | 0
20 | A.R. Brown Backflow Testing | 245 | 2 | 122.5 | 0.1114% | 0 | 0
21 | AllWest Underground, Inc. | 199.25 | 1 | 199.25 | 0.0906% | 0 | 0
22 | DRSi | 126.88 | 2 | 63.44 | 0.05769% | 0 | 0
23 | R.A. Brown Backflow Testing | 50 | 1 | 50 | 0.02273% | 0 | 0

## Change Orders
CHANGE ORDER LOG — 2050
CO / COR register reconciled against internal Budget Transfer xlsx files in the Change Orders/BUDGET TRANSFERS/ GDrive folder. Executed CO sum ties to JDR-implied CO within $90.
CO # | COR # | Description | Amount | Status | Signed PDF
1 |  | CE #022 Filter Fabric & Rock at footing drain ($1,900) + CE #031 Supply and Install DCVA for Temp Water ($633) — COR #01 merged | 2533 | Executed 2018-06-07 | Y
2 | RFI-821 | CE #081 RFI 821 Trench Drain Revisions per ASI 4.1 (new TD at top of parking ramp) — COR #07 Street Level Trench Drain + COR #14 RFI-082.1 Added Trench Drain consolidated | 2295 | Executed 2018-11-09 | Y
3 | COR#08 | CE #083 Plumbing OT Premium — COR for overtime worked 10/29/18 through 11/16/18 | 3718 | Executed 2018-11-19 | Y
4 | COR#09-10 | CE #088 Rooftop Amenity Space (COR #10 Rooftop Sink Roughin Only) + CE #089 Temp Heat Plumbing (COR #09 Gas Permit & Piping for Temp Heat) | 2918 | Executed 2018-11-28 | Y
5 |  | CE #124 Upgraded Toilets at Type A units (upgrade to Am Std Townsend 2922A104) | 464 | Executed 2019-02-08 | Y
6 |  | CE #128 Plumbing Adjustments Due to Cabinet Adjustments (relocate meter stacks in bath cabinets) | 713 | Executed 2019-02-22 | Y
7 | COR#04/11/12 | CE #105 L1 Retail Restroom Build out — largest CO (COR #04 Retail Plumbing Roughin + COR #11/12 Retail Bathroom Roughin/Plumbing consolidated) | 7565 | Executed 2019-04-23 | Y
8 |  | CE #207 Trip Cost for Booster Pump Start Up (closeout) | 560 | Executed 2019-05-30 | Y
Executed subtotal |  |  | 20766
Budget-transfer total (incl. extras) |  |  | 20766
JDR-implied CO (revenue − original contract) |  |  | 20766
Reconciliation gap |  |  | 0
UNEXECUTED / SUPERSEDED COR_s
COR # | Description
COR #01 Backflow for Temp Water | Backflow valve for temp water system
COR #02 Fiberglass Insulation | Fiberglass pipe insulation scope
COR #03 Perforated Foundation Drain Piping | Perforated PVC foundation drain scope (basement interior perimeter)
COR #04 Retail Plumbing Roughin | Retail space plumbing roughin
COR #05 Retail Gas Submeters | Retail gas submeter scope
COR #06 ASI-08 Pet Patch Water Supply | Rooftop pet patch water supply per ASI-08 (10/12/2018)
COR #07 Street Level Trench Drain Changes | Street level trench drain scope changes
COR #08 Overtime Premium 10.29 thru 11.16 | OT premium reimbursement 10/29-11/16/2018
COR #09 Gas Permit & Piping for Temp Heat | Gas permit + piping from meter to trash room L1 for temp heat
COR #10 Rooftop Sink Roughin Only | Rooftop sink roughin scope (sink/faucet supply + install by others)
COR #11 Retail Bathroom Plumbing | Retail bathroom plumbing scope
COR #12 Retail Bathroom Roughin | Retail bathroom roughin scope
COR #13 Move Unit Water Meters | Relocate unit water meters
COR #14 RFI-082.1 Added Trench Drain | Added trench drain per RFI-082.1
COR # Fiberglass Insulation (additional) | Fiberglass insulation additional worksheet
COR # Perforated Pipe | Perforated pipe scope worksheet
COR # Perforated Pipe Revised | Perforated pipe revised scope worksheet
COR # Tub & Shower Bases In Lieu of Stalls | Tub & shower base substitution scope
COR # Overtime (ancillary) | Overtime worksheet (ancillary to COR #08)
2100 Madison - Outstanding CORs log | Summary log of pending CORs
2100 Madison - fixture changes per submittal response | Fixture changes worksheet (submittal response)

## Project Team
PROJECT TEAM — 2050
Primary contacts extracted from Compass 2100 E Madison Apartments project start-up PDF + signed subcontract.
Role | Name | Email | Phone
GC Project Manager | TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 | TBD | (206) 320-8741
GC Superintendent | Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) | TBD | TBD
OWP Signatory | Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON') | mike@onewayplumbing.com | 425-968-8314
Architect | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking)
Owner | 12 Madison Investment LLC
Inspecting Authority | City of Seattle (SDCI)

## Document Pipeline
DOCUMENT PIPELINE — 2050
Quantitative document counts from the Compass 2100 E Madison Apartments GDrive close-out package — used by the Cortex dashboard for CO/RFI/Submittal density metrics.
Category | Count | Source folder
Executed Change Orders | 8 | Change Orders/CO_s/ + BUDGET TRANSFERS/
CORs submitted | 19 | Change Orders/COR_s/
Budget transfer entries | 8 | Change Orders/BUDGET TRANSFERS/
ASI / RFI responses | 4 | ASI-RFI/
Submittals | 13 | Submittals/ (PDF count)
POs — placed | 13 | PO_s/1 Placed/
POs — scheduled | 55 | PO_s/2 Scheduled/
POs — completed | 72 | PO_s/3 Completed/
POs — total | 140 | PO_s/ (all three subfolders)
Vendor invoices | 224 | Invoices/
Lien releases | 9 | Billing/Vendor Lien Waivers (empty folder for Notch — releases may be in PayApp packets)
Permits issued | 7 | Permits/ (Seattle DCI plumbing + gas + backflow permits)
Backcharges | 0 | Change Orders/COR_s/ (no backcharges logged for Compass 2100 E Madison)

## Benchmarks & Derived
BENCHMARKS & DERIVED FIELDS — 2050
All 45+ derived values that Sam Test-Labels v4 ships — carried forward field-for-field. Sections: cost-by-source, labor analytics, material analytics, phase analytics, budget/forecast.
COST-BY-SOURCE ROLLUPS
Field | Value | Formula / Logic
cost_by_source_pr_amount | 249064.1 | SUM(line_items where source=PR)
cost_by_source_ap_amount | 219925.25 | SUM(line_items where source=AP)
cost_by_source_gl_amount | 22767.55 | SUM(line_items where source=GL)
direct_cost | 491756.9 | PR + AP + GL
net_profit | 426809.1 | abs(revenue) − direct_cost
pr_pct_of_revenue | 0.27114 | PR / abs(revenue)
ap_pct_of_revenue | 0.23942 | AP / abs(revenue)
direct_cost_pct_of_revenue | 0.53535 | direct / abs(revenue)
LABOR ANALYTICS
Field | Value | Formula / Logic
total_labor_hours | 5763.5 | SUM(reg+ot+dt+other) source=PR
pr_src_cost_per_hr | 43.214 | PR / labor hours
fully_loaded_wage | 57.9979 | (PR + burden) / labor hours
burden_multiplier | 1.3421 | fully_loaded / pr_src
straight_time_rate | 28.1599 | SUM(reg_amount) / SUM(reg_hours)
total_workers | 22 | COUNT DISTINCT(name) source=PR
burden_total | 85206.6 | SUM(actual) codes 995+998
wage_percentiles (p10/p25/p50/p75/p90) | $18.08 ¦ $21.52 ¦ $26.00 ¦ $33.34 ¦ $48.90 | Percentile snapshot across worker_nominal_wages
MATERIAL ANALYTICS
Field | Value | Formula / Logic
material_spend_total | 204958.79 | SUM(actual) codes 2xx
material_budget_total | 311905 | SUM(current_budget) codes 2xx
material_codes_tracked | 9 | COUNT material codes
material_codes_over_budget | 2 | COUNT where plus_minus > 0
material_codes_under_budget | 7 | COUNT where plus_minus ≤ 0
largest_material_overrun | 241 Water Main/Insulation Mat: $20,656 vs $20,400 budget (+$256) | Material code with largest +plus_minus
largest_material_savings | 230 Finish Material: $111,207 vs $182,982 budget ($-71,775) | Material code with largest −plus_minus
material_vendor_count | 23 | COUNT DISTINCT vendors source=AP
top_vendor_spend | Ferguson Enterprises, Inc. #3007: $70,587 (32% of AP) | Vendor with highest AP spend
PHASE ANALYTICS
Field | Value | Formula / Logic
phases_over_budget | 7 | COUNT codes where plus_minus>0 (excl 999)
phases_under_budget | 22 | COUNT codes where plus_minus≤0 (excl 999)
largest_overrun | 600 Subcontractor: $6,585 vs $1,050 budget (+$5,535) | Phase with largest +plus_minus
largest_savings | 230 Finish Material: $111,207 vs $182,982 budget ($-71,775) | Phase with largest −plus_minus
BUDGET & FORECAST
Field | Value | Formula / Logic
total_jtd_cost | 491756.9 | SUM(actual) expense codes
total_budget | 681372.89 | SUM(current_budget) expense codes
overall_pct_budget_consumed | 0.7217 | JTD / budget
total_over_under_budget | 189615.99 | budget − JTD
labor_unit_cost_per_hr | 28.3691 | Labor JTD / labor hours
revenue_per_labor_hour | 159.3764 | abs(revenue) / labor hours
material_price_variance | 106946.21 | mat_budget − mat_spend
variance_trend | N/A (single snapshot) | Requires prior-period comparison
PROJECT-LEVEL BENCHMARKS (pending)
Field | Value | Formula / Logic
project_duration_months | PENDING | (end_date − start_date) / 30.4
scope_benchmarks | PENDING | One object per scope_metrics entry

## Predictive Signals
PREDICTIVE SIGNALS — 2050
Rule-based health indicators derived from the parsed data. Green = good, yellow = watch, red = flag.
Signal | Status | Value | Threshold / Notes
Gross margin | GREEN | 46.5% | Green >25%, Yellow 10–25%, Red <10%
Phases over budget | GREEN | 7/29 | Red >50%, Yellow 25–50%, Green <25%
Material price variance | GREEN | $106,946 | Positive = under material budget
Burden multiplier | GREEN | 1.34x | Normal range 1.25–1.45x (OWP)
Revenue per labor hour | GREEN | $159.38 | Green >$100, Yellow $70–$100, Red <$70
Retainage outstanding | YELLOW | $45,928 | Monitor for collection
Top vendor concentration | GREEN | 32.1% (Ferguson Enterprises, Inc. #3007) | Yellow >50% (single-vendor risk)
Unused-budget codes | GREEN | 0 codes | Codes with budget but no spend

## Insights
KEY INSIGHTS — 2050
Narrative rollup — the 10 most important things a Cortex user should know about this job at a glance.
01 | Revenue billed $918,566, net profit $426,809 at 46.5% margin.
02 | Parsed 2,054 transactions across 29 cost codes — reconciliation PASS on all codes.
03 | 22 distinct PR-booked workers over 5,764 labor hours ($43.21/hr PR-src, $58.00/hr fully-loaded, 1.34x burden).
04 | Largest phase overrun: 600 Subcontractor: $6,585 vs $1,050 budget (+$5,535).
05 | Largest phase savings: 230 Finish Material: $111,207 vs $182,982 budget ($-71,775).
06 | Material spend $204,959 vs budget $311,905 ($106,946 favorable).
07 | Top AP vendor: Ferguson Enterprises, Inc. #3007: $70,587 (32% of AP); 23 total AP vendors.
08 | Retainage outstanding: $45,928.
09 | 7 of 29 expense phases over budget ($189,616 net vs budget).
10 | Revenue per labor hour $159.38, labor unit cost $28.37 (ratio 5.62x).

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line-item sums vs. Cost Code Totals row in the JDR. Matches Sam Reconciliation tab 1:1. Overall status: 30/30 codes tie to the cent.
Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 1419.75 | 1419.75 | 0 | ✓
101 | Takeoff & Purchase Labor | 8937.5 | 8937.5 | 0 | ✓
110 | Underground Labor | 4762.5 | 4762.5 | 0 | ✓
111 | Garage Labor | 28655 | 28655 | 0 | ✓
112 | Canout Labor | 3287 | 3287 | 0 | ✓
120 | Roughin Labor | 78450 | 78450 | 0 | ✓
130 | Finish Labor | 12091.25 | 12091.25 | 0 | ✓
140 | Gas Labor | 5268.5 | 5268.5 | 0 | ✓
141 | Water Main/Insulation Lab | 11432.5 | 11432.5 | 0 | ✓
142 | Mech Room Labor | 9014 | 9014 | 0 | ✓
151 | T&M Labor | 187.5 | 187.5 | 0 | ✓
210 | Underground Material | 2906.23 | 2906.23 | 0 | ✓
211 | Garage Material | 13959.12 | 13959.12 | 0 | ✓
212 | Canout Material | 3121.63 | 3121.63 | 0 | ✓
220 | Roughin Material | 40315.08 | 40315.08 | 0 | ✓
230 | Finish Material | 111207.3 | 111207.3 | 0 | ✓
240 | Gas Material | 1913.88 | 1913.88 | 0 | ✓
241 | Water Main/Insulation Mat | 20655.61 | 20655.61 | 0 | ✓
242 | Mech Room Material | 10877.78 | 10877.78 | 0 | ✓
243 | Condensation Drains Mat | 2.16 | 2.16 | 0 | ✓
600 | Subcontractor | 6585 | 6585 | 0 | ✓
601 | Engineering/Plans | 17150.88 | 17150.88 | 0 | ✓
602 | Rental Equipment | 4110.62 | 4110.62 | 0 | ✓
603 | Permits & Licenses | 4165 | 4165 | 0 | ✓
607 | Other Expenses | 5722.51 | 5722.51 | 0 | ✓
800 | Office Time | 208 | 208 | 0 | ✓
995 | Payroll Burden | 72671.19 | 72671.19 | 0 | ✓
997 | Employee Benefits | 144 | 144 | 0 | ✓
998 | Payroll Taxes | 12535.41 | 12535.41 | 0 | ✓
999 | Sales | -918566 | -918566 | 0 | ✓
RESULT: 30/30 codes reconciled

## Reconciliation Log
RECONCILIATION LOG — JOB 2050
Worked example of the Reconciliation Protocol running against Job 2050 (JCR-only, no external cross-checks). Mirrors Sam Test-Labels v4 Reconciliation Log tab.
check_id | field_name | JCR-derived value | cross-check value | cross-check source | status | notes
RC-01 | plus_minus_budget | 600 Subcontractor: $6,585 vs $1,050 budget (+$5,535) | actual − current_budget reconciled per code | Cost Code Summaries (internal recomputation) | PASS | Action #1 sign convention: positive = over-budget. Spot-check recomputes plus_minus from actual − current_budget; matches PDF to the cent.
RC-02 | current_budget / original_budget | current_budget total = $681,373; original_budget also carried per cost code | Budget totals sum across expense codes (code != 999) | BVA tab (Original vs Current columns) | PASS | Both budgets carried distinctly per Action #2. Current budget differs from original on codes that had change orders.
RC-03 | pr_src_cost_per_hr | $43.21/hr (all PR-source cost ÷ total labor hours) | Manual recomputation: PR total $249,064.10 ÷ 5,763.50 hrs | Derived Fields tab (line items → source=PR) | PASS | Phase-code filter: include all phases incl. 995 burden and 998 taxes; exclude only 999 Sales.
RC-04 | worker_nominal_wages / nominal_wage_percentiles | p10=$18.08 ¦ p25=$21.52 ¦ p50=$26.00 ¦ p75=$33.34 ¦ p90=$48.90 (22 workers) | straight_time_rate $28.16 falls within p25–p75 band | Crew Roster tab | PASS | Population-slice sanity: weighted straight_time_rate falls within the p25–p75 range, expected for this workforce composition.
RC-05 | labor_unit_cost_per_hr vs revenue_per_labor_hour | cost $28.37/hr ¦ revenue $159.38/hr ¦ ratio 5.62x | Recompute from labor-code JTD ÷ labor hours | Productivity tab (Action #7 split) | PASS | Split into two fields per Action #7. Cost and throughput are distinct metrics; their ratio is the productivity signal.
RC-06 | scope_metrics / scope_benchmarks | pending | — | project-attribute input (trade-declared) | PENDING | Awaiting plumbing scope-metric declarations for Job 2050 (fixture count, DFU total, linear feet of main). Same status as Job 2020.
RC-07 | reconciliation (per-code parse tie-out) | 30/30 codes tie to PDF to the cent | PR $249,064.10 + AP $219,925.25 + GL $22,767.55 = $491,756.90 matches direct cost | Reconciliation tab | PASS | Independent sum of line_items[] by cost_code vs. Cost Code Totals row for each code. PASS if ¦diff¦ < $0.02 for all codes.
SUMMARY
Total checks | 7
PASS | 6
PENDING | 1
FAIL | 0

## Metric Registry
METRIC REGISTRY — 2050
Canonical registry of every named metric in the workbook. Acts as a machine-readable table of contents + field dictionary. Every Sam Test-Labels v4 field has a row here.
Key | Label | Value | Source / Notes
job_number | Job Number | 2050 | JDR cover page
job_name | Job Name | GRE Greenlake | JDR cover page
general_contractor | General Contractor | GRE | From AR client code
report_date | Report Date | 2026-04-03 | JDR run date
line_items_count | Line Item Count | 2054 | Length of line_items[]
cost_code_count | Cost Code Count | 30 | Length of cost_code_summaries[]
job_totals_revenue | Revenue (AR, negative) | -918566 | Sage stores credit as negative
job_totals_revenue_abs | Revenue (absolute) | 918566 | abs(job_totals_revenue)
job_totals_expenses | Expenses | 491756.9 | Sage job_totals_expenses
job_totals_net | Net | -426809.1 | Sage job_totals_net
job_totals_retainage | Retainage | -45928.3 | Sage job_totals_retainage
job_totals_net_due | Net Due | 0 | Sage job_totals_net_due
cost_by_source_pr_amount | PR Source Amount | 249064.1 | SUM(line_items source=PR)
cost_by_source_ap_amount | AP Source Amount | 219925.25 | SUM(line_items source=AP)
cost_by_source_gl_amount | GL Source Amount | 22767.55 | SUM(line_items source=GL)
cost_by_source_ar_amount | AR Source Amount | -918566 | SUM(line_items source=AR)
direct_cost | Direct Cost | 491756.9 | PR + AP + GL
net_profit | Net Profit | 426809.1 | abs(revenue) − direct_cost
gross_margin_pct | Gross Margin % | 46.46% | net / abs(revenue)
labor_cost | Labor Cost (codes 1xx) | 163505.5 | SUM(actual) category=Labor
material_cost | Material Cost (codes 2xx) | 204958.79 | SUM(actual) category=Material
overhead_cost | Overhead Cost (codes 6xx) | 37734.01 | SUM(actual) category=Overhead
burden_cost | Burden Cost (995+998) | 85206.6 | SUM(actual) category=Burden
total_labor_hours | Total Labor Hours | 5763.5 | SUM(reg+ot+dt+other) source=PR
total_workers | Total Workers | 22 | COUNT DISTINCT(name) source=PR
straight_time_rate | Straight-Time Rate | 28.1599 | reg_amount ÷ reg_hours
pr_src_cost_per_hr | PR-Source Cost/Hour | 43.214 | PR total ÷ labor hours
fully_loaded_wage | Fully-Loaded Wage | 57.9979 | (PR + burden) ÷ labor hours
burden_multiplier | Burden Multiplier | 1.3421 | fully-loaded ÷ pr-src
burden_total | Burden Total | 85206.6 | SUM(actual) codes 995+998
wage_percentile_p10 | Wage Percentile p10 | 18.08 | Percentile across workers
wage_percentile_p25 | Wage Percentile p25 | 21.52 | Percentile across workers
wage_percentile_p50 | Wage Percentile p50 | 26 | Percentile across workers
wage_percentile_p75 | Wage Percentile p75 | 33.34 | Percentile across workers
wage_percentile_p90 | Wage Percentile p90 | 48.9 | Percentile across workers
material_spend_total | Material Spend Total | 204958.79 | SUM(actual) codes 2xx
material_budget_total | Material Budget Total | 311905 | SUM(current_budget) codes 2xx
material_codes_tracked | Material Codes Tracked | 9 | COUNT codes 2xx
material_codes_over_budget | Material Codes Over Budget | 2 | COUNT where plus_minus>0
material_codes_under_budget | Material Codes Under Budget | 7 | COUNT where plus_minus≤0
material_vendor_count | Material Vendor Count | 23 | COUNT DISTINCT vendors
material_price_variance | Material Price Variance | 106946.21 | mat_budget − mat_spend
largest_material_overrun | Largest Material Overrun | 241 Water Main/Insulation Mat: $20,656 vs $20,400 budget (+$256)
largest_material_savings | Largest Material Savings | 230 Finish Material: $111,207 vs $182,982 budget ($-71,775)
top_vendor_spend | Top Vendor Spend | Ferguson Enterprises, Inc. #3007: $70,587 (32% of AP)
phases_over_budget | Phases Over Budget | 7 | COUNT codes (excl 999)
phases_under_budget | Phases Under Budget | 22 | COUNT codes (excl 999)
largest_overrun | Largest Overrun | 600 Subcontractor: $6,585 vs $1,050 budget (+$5,535)
largest_savings | Largest Savings | 230 Finish Material: $111,207 vs $182,982 budget ($-71,775)
total_jtd_cost | Total JTD Cost | 491756.9 | SUM(actual) expense codes
total_budget | Total Current Budget | 681372.89 | SUM(current_budget) expense codes
overall_pct_budget_consumed | Overall % Budget Consumed | 72.17% | JTD ÷ budget
total_over_under_budget | Total Over/Under Budget | 189615.99 | budget − JTD
labor_unit_cost_per_hr | Labor Unit Cost / Hour | 28.3691 | labor JTD ÷ labor hours
revenue_per_labor_hour | Revenue per Labor Hour | 159.3764 | abs(revenue) ÷ labor hours
unit_count | Unit Count | PENDING | Project-attribute input required
fixture_count | Fixture Count | PENDING | Project-attribute input required
project_start_date | Project Start Date | PENDING | Project-attribute input required
project_end_date | Project End Date | PENDING | Project-attribute input required
duration_months | Duration (months) | PENDING | Project-attribute input required
scope_metrics | Scope Metrics | PENDING | Trade-declared {label, count, desc} array