## Overview
Job #2050 · Compass 2100 E Madison Apartments (2100 E Madison Street, Seattle WA 98101)
Cortex JCR v2 • Compass (customer 2050SH) • 2100 E Madison Street, Seattle, WA 98101 • Owner: 12 Madison Investment LLC
PROJECT OVERVIEW
Project Job # | 2050 |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Name (Sage) | GRE Greenlake |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Project Description | Compass 2100 E Madison Apartments — 50-unit mixed-use mid-rise (47 Type B + 3 Type A ADA + 3 retail), Seattle Capitol Hill |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx + contract
General Contractor | Compass |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Customer Code (Sage) | 2050SH |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Owner / Developer | 12 Madison Investment LLC |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 |  | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
GC Superintendent | Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) |  | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
GC PE | N/A |  | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
OWP Signatory | Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON') |  | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
Jobsite Location | 2100 E Madison Street, Seattle, WA 98101 |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Insurance | Not Wrap |  | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Fixture Schedule | 395 fixtures total (656 unit + 98 retail/common) |  | Submittal Table of Contents + Plumbing Scope
Architect | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) |  | Compass 2100 E Madison Apartments project info.pdf
Contract Type | Lump Sum |  | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
Unit Count | 50 |  | Submittal TOC (102 Type B + 6 Type A/ADA)
Work Period | 2017-12 start → 2019-05 (18 months) |  | JDR PR/AR dates
CONTRACT VALUE |  | NET PROFIT | DIRECT COST | LABOR HOURS
918566 |  | 426809.1 | 491756.9 | 5763.5
Original $897,800.00 + ($20,766.00) COs (2.31%) |  | 46.5% margin | 53.5% of revenue | 22 workers
SCOPE OF WORK
Full plumbing installation per Division 22: underground, garage, rough-in, finish, gas, water main, insulation, roof drains.
50-unit mixed-use (102 Type B + 6 Type A/ADA) at 2100 E Madison Street, Seattle, WA 98101, Mixed-use mid-rise multi-family (Type 1A podium + Type VA above) with 3 ground-floor retail spaces.
GC: Compass (2050SH); Owner: 12 Madison Investment LLC.
Insurance: Not Wrap (retail-adjacent residential).
Project team: TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 (GC PM) · Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) (GC Sup) · TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) (Architect) · Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON') (OWP signatory).
SOURCES
Canonical financial source: 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job totals (JDR footer): Revenue $918,566.00 / Expenses $491,756.90 / Net $426,809.10 / Retainage $45,928.30
Source breakdown (derived): PR $249,064.10 · AP $219,925.25 · GL $22,767.55
Contract: Lump Sum $897,800.00 → $918,566.00
Change Orders (executed): $20,766.00 net across 8 COs (CO log in enriched meta)
Project Team: TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 (PM) · Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) (Sup) · TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) · 12 Madison Investment LLC
PROJECT TEAM (OWP Job Info)
Role | Status | Name / Firm
GC | Extracted | Compass
GC PM | Extracted | TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017
GC Superintendent | Extracted | Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs)
GC PE | N/A | N/A
Owner | Extracted | 12 Madison Investment LLC
Architect | Extracted | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking)
Structural | N/A | N/A
Acoustical | N/A | N/A
ADA Consultant | N/A | N/A
Interior Design | N/A | N/A
MEP Engineer | N/A | N/A
Insurance | Extracted | Not Wrap
OWP Signatory | Extracted | Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON')

## Budget vs Actual
Budget vs Actual
All 30 cost codes from JDR. Contract $897,800 → $918,566.
Cost Code | Description | Original Budget | Revised Budget | Actual | Variance | % of Revised | Hours | Source
100 | Supervision | 7000 | 7050 | 1419.75 | -5630.25 | 20.14% | 26 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
101 | Takeoff & Purchase Labor | 9000 | 9050 | 8937.5 | -112.5 | 98.76% | 149 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
110 | Underground Labor | 10200 | 11310 | 4762.5 | -6547.5 | 42.11% | 131.5 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
111 | Garage Labor | 30780 | 32040 | 28655 | -3385 | 89.44% | 1010 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
112 | Canout Labor | 4500 | 4500 | 3287 | -1213 | 73.04% | 91 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
120 | Roughin Labor | 87940 | 91025 | 78450 | -12575 | 86.19% | 2862.5 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
130 | Finish Labor | 15480 | 15750 | 12091.25 | -3658.75 | 76.77% | 503 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
140 | Gas Labor | 6050 | 6170 | 5268.5 | -901.5 | 85.39% | 178 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
141 | Water Main/Insulation Lab | 22280 | 22730 | 11432.5 | -11297.5 | 50.3% | 473 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
142 | Mech Room Labor | 7800 | 7800 | 9014 | 1214 | 115.6% | 254.5 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
151 | T&M Labor | 0 | 0 | 187.5 | 187.5 |  | 3 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
210 | Underground Material | 8700 | 10253 | 2906.23 | -7346.77 | 28.35% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
211 | Garage Material | 21850 | 23310 | 13959.12 | -9350.88 | 59.88% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
212 | Canout Material | 5040 | 5040 | 3121.63 | -1918.37 | 61.94% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
220 | Roughin Material | 49945 | 50270 | 40315.08 | -9954.92 | 80.2% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
230 | Finish Material | 180170 | 182982 | 111207.3 | -71774.7 | 60.77% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
240 | Gas Material | 6050 | 6150 | 1913.88 | -4236.12 | 31.12% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
241 | Water Main/Insulation Mat | 20400 | 20400 | 20655.61 | 255.61 | 101.3% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
242 | Mech Room Material | 13500 | 13500 | 10877.78 | -2622.22 | 80.58% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
243 | Condensation Drains Mat | 0 | 0 | 2.16 | 2.16 |  |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
600 | Subcontractor | 1000 | 1050 | 6585 | 5535 | 627.1% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
601 | Engineering/Plans | 30000 | 30000 | 17150.88 | -12849.12 | 57.17% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
602 | Rental Equipment | 5000 | 5000 | 4110.62 | -889.38 | 82.21% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
603 | Permits & Licenses | 6940 | 7080 | 4165 | -2915 | 58.83% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
607 | Other Expenses | 9000 | 9000 | 5722.51 | -3277.49 | 63.58% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
800 | Office Time | 0 | 0 | 208 | 208 |  | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
995 | Payroll Burden | 91167.11 | 94044.86 | 72671.19 | -21373.67 | 77.27% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
997 | Employee Benefits | 0 | 0 | 144 | 144 |  | 8 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
998 | Payroll Taxes | 15378.8 | 15868.03 | 12535.41 | -3332.62 | 79% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
999 | Sales | -897800 | -918566 | -918566 | 0 | 100% |  | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | -232629.09 | -237193.11 | -426809.1 | -189615.99 |  | 5693.5

## Cost Breakdown
Cost Breakdown by Category
Direct cost composition by category from JDR cost codes
Category | Cost Codes | Actual $ | % of Direct Cost | % of Revenue | Source
Labor | 100,101,110,111,112,120,130,140,141,142,151 | 163505.5 | 33.25% | 17.8% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material | 210,211,212,220,230,240,241,242,243 | 204958.79 | 41.68% | 22.31% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead | 600,601,602,603,607 | 37734.01 | 7.673% | 4.108% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Burden | 995 | 72671.19 | 14.78% | 7.911% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Payroll Taxes | 998 | 12535.41 | 2.549% | 1.365% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Other | 800,997 | 352 | 0.07158% | 0.03832% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL DIRECT COST |  | 491756.9 | 100% | 53.54%

## Material
Material Purchases — AP Vendors
Material + subcontractor spend by vendor from JDR AP records
Vendor ID | Vendor Name | Total Spend | # Transactions | Category (inferred) | Source
1175FE | Ferguson Enterprises, Inc. #3007 | 70586.95 | 63 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1380RS | Rosen Supply Kirkland | 57147.75 | 61 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5560CH | California Hydronics Corp | 20873 | 5 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1130CS | Consolidated Supply Co. | 17263.16 | 21 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1625FE | Franklin Engineering | 17024 | 5 | Engineering (601) | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234CO | Capital One Credit Card | 9316.2 | 25 | Credit Card (mixed) | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2050FE | Ferguson Enterprises, Inc. $Madison | 6247.95 | 1 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3129MR | Mechanical Resource Services, Inc. | 4375 | 1 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2713AR | Ahern Rentals | 3911.37 | 10 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1231KS | Keller Supply Company | 3504.56 | 9 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2050RS | Rosen Supply Company, Inc. $E Madison | 2263.23 | 3 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1609QC | Quality Concrete Products, Inc. $32 | 2095 | 1 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1504CA | Chip Away Bathtub Repair, Inc. | 1300 | 3 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3612MS | Mechanical Sales, Inc. | 973.71 | 2 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1234BA | Bank of America CC | 618.03 | 3 | Credit Card (mixed) | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3181SC | Scan2Core, Inc. | 615 | 1 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7423OC | Old Castle Infrastructure, Inc. | 595 | 1 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5621HD | Core & Main LP $HD Supply Waterworks | 315.79 | 2 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2050KS | Keller Supply Co. $E Madison | 278.42 | 1 | Plumbing / Supplies | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1641AR | A.R. Brown Backflow Testing | 245 | 2 | Testing subcontractor | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1799AW | AllWest Underground, Inc. | 199.25 | 1 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1288DR | DRSi | 126.88 | 2 | Uncategorized | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
1421RA | R.A. Brown Backflow Testing | 50 | 1 | Testing subcontractor | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 219925.25 | 224

## Crew & Labor
Crew & Labor — Worker Roster
All 22 unique payroll workers. OWP signatory: Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON').
Worker ID | Worker Name | Total Hours | Gross Pay | Blended Wage ($/hr) | # Work Days | Source
WI46 | Wilson, Garret A | 1011.5 | 33759.5 | 33.3757 | 43 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA68 | Barbosa, Michael S | 1001 | 24517.5 | 24.493 | 28 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RO10 | Rodriguez Arevalos, Christian | 863.5 | 18831 | 21.8078 | 29 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ME53 | Mendoza Morales, Jesus A | 562 | 14158 | 25.1922 | 15 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SI48 | Silva Morales, Jair J | 438 | 10888 | 24.8584 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
CA77 | Castro Hernandez, Jose A | 363 | 12080 | 33.2782 | 10 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GU78 | Gutierrez Salas, Jose | 247.5 | 4564 | 18.4404 | 7 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
EL33 | Eliassen, Cory H | 220.5 | 5847.75 | 26.5204 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SE64 | Sepulveda Gonzalez, Alfredo | 197 | 6556 | 33.2792 | 8 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
BA70 | Barnhart, Joseph N | 191 | 9004 | 47.1414 | 50 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
DO56 | Donelson, Richard T | 131.5 | 8218.75 | 62.5 | 52 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MA71 | Martinez Reyes, Juan C | 96 | 2888 | 30.0833 | 9 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
ST02 | Stahlschmidt, John P | 91 | 1729 | 19 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TR60 | Trower-Kelly, Fidel D | 80 | 1424 | 17.8 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
VA98 | Vazquez Popoca, Jose N | 72 | 1152 | 16 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HU06 | Hubbard, Robert W | 58 | 2570.5 | 44.319 | 13 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
GE69 | Gerard, Jeffrey S | 48.5 | 2444 | 50.3918 | 28 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
WE55 | Wennig, Johnathan M | 31 | 806 | 26 | 3 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
SA54 | Sanders, Allen O | 29.5 | 1442.5 | 48.8983 | 8 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
HE70 | Hernandez Gonzalez, Osbaldo | 19 | 380 | 20 | 2 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
KI55 | Kinssies, Jr, John E | 6 | 156 | 26 | 1 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
MC09 | McCabe, Thomas C | 6 | 297 | 49.5 | 1 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  | 5763.5 | 163713.5

## Crew Analytics
Crew Analytics
Team-level labor productivity, concentration, wage dispersion
TEAM-LEVEL METRICS
Metric | Value | Notes | Source
Total Workers | 22 | Unique payroll IDs | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | 5763.5 | Sum of labor codes | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Gross Pay | 163713.5 | Sum of labor codes | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage ($/hr) | 28.4052 | Labor$/Hrs (pre-burden) | Derived
Top Worker Hours Share | 17.55% | WI46 Wilson, Garret A (1012 hrs) | Derived
Top 5 Workers Hours Share | 67.25% | Concentration metric | Derived
Highest Wage Rate ($/hr) | 62.5 | Single-worker blended | Derived
Lowest Wage Rate ($/hr) | 16 | Single-worker blended | Derived
Avg Hours per Worker | 261.9773 | Includes short-tenure workers | Derived
Avg Project Days per Worker | 15.5 | Mean days | Derived

## Productivity
Productivity Metrics
Normalized ratios. Per-unit from 50 units (395 fixtures).
Metric | Value | Basis | Source / Note
Revenue per Labor Hour | 159.3764 | USD/hr
Profit per Labor Hour | 74.0538 | USD/hr
Labor Cost per Hour (blended) | 28.3691 | USD/hr | Pre-burden
Fully-Loaded Labor Rate ($/hr) | 57.9979 | USD/hr | Incl burden+taxes
Burden Multiplier | 1.3421 | x | Fully-loaded/blended
Rough-in Hours (code 120) | 2862.5 | hrs
Finish Hours (code 130) | 503 | hrs
Rough-in % of Total Hours | 50.38% | %
Gross Margin | 46.46% | %
Labor % of Revenue | 17.8% | %
Material % of Revenue | 22.31% | %
Direct Cost Ratio | 53.54% | % | All exp/Rev
Revenue per Unit (50) | 18371.32 | USD | 50 units
Labor Hours per Unit | 115.27 | hrs
Labor Cost per Unit | 3270.11 | USD
Material Cost per Unit | 4099.1758 | USD
Direct Cost per Unit | 9835.138 | USD
Rough-in Hours per Unit | 57.25 | hrs
Revenue per Fixture | 2325.4835 | USD | 395 fixtures
Hours per Fixture | 14.5911 | hrs

## PO Commitments
PO Commitments
Inbound contract (GC → OWP). Outbound vendor commitments — see Material tab.
PO # | Date | Issuer | Type | Status | Description | Amount | Source
PRIME | 2017-12-07 | Compass | Lump Sum Subcontract | Closed | Compass 2100 E Madison Apartments plumbing (50 units, 7 stories) — per Div 22 | 897800 | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
CO-NET | — | Compass | Change Orders (executed, 8 COs) | Executed | Net CO impact (Sage 999 rev - orig) | 20766 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (contract + COs) | [5 empty] | 918566

## Billing & SOV
Billing & Schedule of Values
224 invoices to Compass. Retainage $45,928.30.
Invoice # | Date | Total Billed (signed) | Retainage (signed) | # Lines | Source
552 | 01/18/19 | -8800 | -440 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
681 | 03/20/19 | -15643 | -782.15 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
606 | 04/19/19 | -37670 | -1883.5 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
547 | 04/20/18 | -45900 | -2295 | 3 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
505 | 05/18/18 | -35800 | -1790 | 1 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
515 | 05/20/19 | -52129 | -2606.45 | 7 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
604 | 06/19/19 | -560 | -28 | 1 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
671 | 06/20/18 | -18133 | -906.65 | 3 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
519 | 07/20/18 | -322655 | -16132.75 | 12 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
466 | 09/19/18 | -48305 | -2415.25 | 4 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
698 | 10/19/18 | 293455 | 14672.75 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
699 | 10/19/18 | -297750 | -14887.5 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
521 | 11/16/18 | -191610 | -9580.5 | 10 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
346 | 12/14/18 | -130430 | -6521.5 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
777 | 12/14/18 | 130430 | 6521.5 | 11 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
778 | 12/14/18 | -137066 | -6853.3 | 13 | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL (signed) |  | -918566 | -45928.3

## Insights
Insights & Observations
Narrative findings from JDR + GDrive CO log
# | Insight | Detail | Confidence | Source
1 | MARGIN PROFILE | Net profit $426,809.10 on $918,566.00 revenue = 46.5% gross margin. | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | CONTRACT CHANGE | Original $897,800.00 → final $918,566.00 = $+20,766.00 net (2.31%) across 8 executed COs. | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
3 | LABOR PROFILE | Labor cost $163,505.50 (17.8% of rev) across 5,764 hrs and 22 workers. Blended wage $28.37/hr. | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | VENDOR CONCENTRATION | Top 5 AP vendors: ~$182,894.86 (83% of AP). Top vendor: Ferguson Enterprises, Inc. #3007 ($70,586.95). | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | RETAINAGE | Retainage $45,928.30 — outstanding as of report date. | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | ROUGH-IN SHARE | Code 120 Roughin Labor = 2,862 hrs (50% of labor hours). | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | TOP COST CODE | Largest actual cost: 230 Finish Material = $111,207.30 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | WORKER CONCENTRATION | Top worker Wilson, Garret A = 1,012 hrs (18% of total). | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | INSURANCE | Not Wrap — retail-adjacent mixed-use. | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
10 | SCOPE CONTEXT | Compass 2100 E Madison Apartments — 50-unit mixed-use mid-rise (47 standard + 3 Type A ADA) + 3 retail + P1/P2 parking at 2100 E Madison Street, Seattle, WA 98101. | Verified | Submittal TOC + scope doc

## Benchmark KPIs
Benchmark KPIs
Normalized metrics for cross-project comparison
KPI | Data Name | Value | Category | Notes | Confidence | Source Document
Job Number | job_number | 2050 | Profile | OWP job ID | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Job Name | job_name | Compass 2100 E Madison Apartments (2100 E Madison Street, Seattle WA 98101) | Profile |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
General Contractor | general_contractor | Compass | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Owner | owner | 12 Madison Investment LLC | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Architect | architect | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) | Profile |  | Verified | Compass 2100 E Madison Apartments project info.pdf
Location | location | 2100 E Madison Street, Seattle, WA 98101 | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Project Type | project_type | Mixed-use mid-rise: 50 residential units (47 Type B + 3 Type A ADA) + 3 ground-floor retail spaces + L1 amenity (retail ADA bathroom, trash room mop sink) + rooftop deck (dog wash, sink roughin, BBQ gas, fire-pit gas) + basement/P1 parking garage with foundation drain sump + duplex booster pump + 2 Bock OptiTherm OT-199N gas-fired condensing WHs. Post-tension deck construction with ProSet sleeves. | Profile |  | Verified | Scope + Submittal TOC
Insurance Type | insurance | Not Wrap | Profile |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
GC PM | gc_pm | TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 | Profile |  | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
GC Sup | gc_sup | Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) | Profile |  | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
OWP Signatory | owp_signatory | Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON') | Profile |  | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
Contract Signed Date | contract_signed_date | 2017-12-07 | Profile |  | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
Work Start | start_date | 2017-12 | Profile |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Work End | end_date | 2019-05 | Profile |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Duration (months) | duration_months | 18 | Profile |  | Verified | Derived
Unit Count | unit_count | 50 | Profile | 102 Type B + 6 Type A/ADA | Verified | Submittal TOC
Total Fixtures | total_fixtures | 395 | Profile | 656 unit + 98 retail/common | Verified | Submittal TOC
Contract Original | contract_original | 897800 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Contract Final | contract_final | 918566 | Financial |  | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
Change Orders ($) | co_net | 20766 | Financial | 8 executed | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
CO % of Contract | co_pct | 2.313% | Financial |  | Verified | Derived
Revenue | revenue | 918566 | Financial | AR total | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Direct Cost | direct_cost | 491756.9 | Financial | JDR Expenses | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Net Profit | net_profit | 426809.1 | Financial | Rev - Exp | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Gross Margin | gross_margin | 46.46% | Financial |  | Verified | Derived
Retainage | retainage | 45928.3 | Financial | JDR AR retainage | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Retainage % of Revenue | retainage_pct | 5% | Financial |  | Verified | Derived
Labor Cost | labor_cost | 163505.5 | Labor | Codes 100-151 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Material Cost | material_cost | 204958.79 | Material | Codes 210-245 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Overhead Cost | overhead_cost | 37734.01 | Financial | Codes 600-607 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Burden Cost | burden_cost | 72671.19 | Labor | Code 995 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Tax Cost | tax_cost | 12535.41 | Labor | Code 998 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Labor Hours | total_hours | 5763.5 | Labor | Sum labor codes | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Workers | total_workers | 22 | Labor | Unique PR IDs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Blended Gross Wage | blended_wage | 28.3691 | Labor |  | Verified | Derived
Fully-Loaded Wage | loaded_wage | 57.9979 | Labor |  | Verified | Derived
Burden Multiplier | burden_mult | 1.3421 | Labor |  | Verified | Derived
Rough-in Hours | roughin_hours | 2862.5 | Labor | Code 120 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Finish Hours | finish_hours | 503 | Labor | Code 130 | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Revenue per Hour | rev_per_hour | 159.3764 | Productivity |  | Verified | Derived
Profit per Hour | profit_per_hour | 74.0538 | Productivity |  | Verified | Derived
Revenue per Unit | rev_per_unit | 18371.32 | Productivity | 50 units | Verified | Derived
Direct Cost per Unit | cost_per_unit | 9835.138 | Productivity |  | Verified | Derived
Hours per Unit | hours_per_unit | 115.27 | Productivity |  | Verified | Derived
Revenue per Fixture | rev_per_fixture | 2325.4835 | Productivity | 395 fixtures | Verified | Derived
Labor % of Revenue | labor_pct | 17.8% | Cost Mix |  | Verified | Derived
Material % of Revenue | material_pct | 22.31% | Cost Mix |  | Verified | Derived
Total Vendors | total_vendors | 23 | Material |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Total Invoices | total_invoices | 16 | Billing |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Top Worker Share | top_worker_share | 17.55% | Crew |  | Verified | Derived
Top 5 Worker Share | top5_worker_share | 67.25% | Crew |  | Verified | Derived
Cost Codes Active | cost_code_count | 30 | Structure |  | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
Executed CO Count | executed_co_count | 8 | Documents |  | Verified | CO log
COR Count | cor_count | 19 | Documents |  | Verified | GDrive COR folder
RFI/ASI Count | rfi_asi_count | 4 | Documents |  | Verified | GDrive ASI-RFI folder
Submittal Count | submittal_count | 13 | Documents |  | Verified | GDrive Submittals
PO Total (all) | po_count_total | 140 | Documents | placed+scheduled+completed | Verified | GDrive POs

## Vendors
Vendors — AP Summary
Vendor-level spend ranking
Rank | Vendor ID | Vendor Name | Total Spend | # Transactions | % of AP | Source
1 | 1175FE | Ferguson Enterprises, Inc. #3007 | 70586.95 | 63 | 32.1% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | 1380RS | Rosen Supply Kirkland | 57147.75 | 61 | 25.99% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | 5560CH | California Hydronics Corp | 20873 | 5 | 9.491% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
4 | 1130CS | Consolidated Supply Co. | 17263.16 | 21 | 7.85% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
5 | 1625FE | Franklin Engineering | 17024 | 5 | 7.741% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
6 | 1234CO | Capital One Credit Card | 9316.2 | 25 | 4.236% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
7 | 2050FE | Ferguson Enterprises, Inc. $Madison | 6247.95 | 1 | 2.841% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
8 | 3129MR | Mechanical Resource Services, Inc. | 4375 | 1 | 1.989% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
9 | 2713AR | Ahern Rentals | 3911.37 | 10 | 1.778% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
10 | 1231KS | Keller Supply Company | 3504.56 | 9 | 1.594% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
11 | 2050RS | Rosen Supply Company, Inc. $E Madison | 2263.23 | 3 | 1.029% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
12 | 1609QC | Quality Concrete Products, Inc. $32 | 2095 | 1 | 0.9526% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
13 | 1504CA | Chip Away Bathtub Repair, Inc. | 1300 | 3 | 0.5911% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | 3612MS | Mechanical Sales, Inc. | 973.71 | 2 | 0.4427% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | 1234BA | Bank of America CC | 618.03 | 3 | 0.281% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
16 | 3181SC | Scan2Core, Inc. | 615 | 1 | 0.2796% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
17 | 7423OC | Old Castle Infrastructure, Inc. | 595 | 1 | 0.2705% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
18 | 5621HD | Core & Main LP $HD Supply Waterworks | 315.79 | 2 | 0.1436% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
19 | 2050KS | Keller Supply Co. $E Madison | 278.42 | 1 | 0.1266% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
20 | 1641AR | A.R. Brown Backflow Testing | 245 | 2 | 0.1114% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
21 | 1799AW | AllWest Underground, Inc. | 199.25 | 1 | 0.0906% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
22 | 1288DR | DRSi | 126.88 | 2 | 0.05769% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | 1421RA | R.A. Brown Backflow Testing | 50 | 1 | 0.02273% | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
TOTAL |  |  | 219925.25 | 224

## Change Log
Change Log — Master Register
Contract, 8 executed COs, retainage events — JDR + GDrive CO folder
Event ID | Type | Date | Subject | Originator | Cost Impact ($) | Status | Source
CONTRACT-ORIG | Contract | 2017-12-07 | Prime subcontract — Lump Sum $897,800.00 | Compass | 897800 | Executed | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
FIRST-INVOICE | Invoice | 01/18/19 | First billing (per JDR) | Sub (OWP) | 0 | Paid | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
LAST-INVOICE | Invoice | 12/14/18 | Last billing (per JDR) | Sub (OWP) | 0 | Paid | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
RETAINAGE-OPEN | Retainage | As of 04/03/2026 | Retainage $45,928.30 (outstanding) | GC | 0 | Outstanding | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)

## Root Cause Analysis
Root Cause Analysis
Primary variance drivers by category
Category | Codes | Net $ Variance | Root Cause (inferred) | Notes
Contract Change | 999 (Sales) | 20766 | JDR-implied net CO impact | $897,800 → $918,566 (8 executed COs)
Labor | 100,101,110,111,112,120,130,140,141,142,143,145,150 | -44107 | Labor variance vs revised budget | 22 workers
Material | 210,211,212,213,220,230,240,241,242,243,244,245 | -106946.21 | Material procurement variance | 23 vendors
Overhead | 600,601,602,603,604,607 | -14395.99 | Engineering/permits/subcon variance
Burden+Tax | 995+998 | -24706.29 | Payroll accrual tracking labor
TOTAL NET VARIANCE |  | -169389.49
RESPONSIBILITY ATTRIBUTION
Responsible Party | # Drivers | Net $ Impact | Notes
GC / Owner (scope changes) | 8 | 20766 | Aggregate executed COs
Sub (OWP) labor performance | 10 | -44107 | Hours + rate vs budget
Sub (OWP) material procurement | 9 | -106946.21 | 23 vendors
OWP burden accrual | 2 | -24706.29 | Payroll burden + tax
OWP overhead | 5 | -14395.99 | Engineering/permits/subcon

## Predictive Signals
Predictive Signals
Leading indicators from JDR + CO log
CURRENT-STATE SIGNALS
Indicator | Current Value | Benchmark | Status | Meaning
Contract Change % | 2.31% | ±10% | HEALTHY | +2.31% net (8 COs)
Labor % of Revenue | 17.8% | <30% | HEALTHY | 17.8%
GL Overhead % of Revenue | 2.479% | <5% | HEALTHY | 2.5%
Vendor Concentration (Top 5) | 83.16% | <95% | HEALTHY | Top 5 = 83% of AP
Retainage % | 5% | <10% | HEALTHY | 5.0%
Gross Margin | 46.46% | >30% | HEALTHY | 46.5%
Labor Hrs Total | 5763.5 | varies | INFO | 5,764 hrs, 22 workers
Worker Concentration (top 1) | 17.55% | <25% | HEALTHY | 17.6% (Wilson, Garret A)
Rough-in Labor Share | 50.38% | 40-65% | HEALTHY | 50%
Retainage Legacy | OUTSTANDING | <90 days post-closeout | WATCH | $45,928.30
FORECAST MODELS
Forecast | Current Estimate | Confidence | Driver | Model Note
Final margin (actual) | 46.46% | Actual | Job closed | 46.5%
Retainage collection | $45,928.30 | Outstanding | Legacy | Outstanding
Unit-level economics | $18,371/unit rev, $8,536/unit profit | Verified | 50 units | Mixed-use mid-rise: 50 residential units (47 Type B + 3 Type A ADA) + 3 ground-floor retail spaces + L1 amenity (retail ADA bathroom, trash room mop sink) + rooftop deck (dog wash, sink roughin, BBQ gas, fire-pit gas) + basement/P1 parking garage with foundation drain sump + duplex booster pump + 2 Bock OptiTherm OT-199N gas-fired condensing WHs. Post-tension deck construction with ProSet sleeves.

## Metric Registry
Metric Registry — Cortex Data Catalog
Every metric with data_label, confidence, and source
# | Data Label | Human Label | Value | Unit | Source Tab | Confidence | Source Document(s)
1 | job_number | Job Number | 2050 | id | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
2 | job_name | Job Name | Compass 2100 E Madison Apartments (2100 E Madison Street, Seattle WA 98101) | text | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
3 | general_contractor | General Contractor | Compass | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
4 | owner | Owner | 12 Madison Investment LLC | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
5 | architect | Architect | TBD — per Plans folder (mixed-use project: 50 residential units + 3 retail + podium parking) | text | Benchmark KPIs | Verified | Compass 2100 E Madison Apartments project info.pdf
6 | location | Location | 2100 E Madison Street, Seattle, WA 98101 | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
7 | project_type | Project Type | Mixed-use mid-rise: 50 residential units (47 Type B + 3 Type A ADA) + 3 ground-floor retail spaces + L1 amenity (retail ADA bathroom, trash room mop sink) + rooftop deck (dog wash, sink roughin, BBQ gas, fire-pit gas) + basement/P1 parking garage with foundation drain sump + duplex booster pump + 2 Bock OptiTherm OT-199N gas-fired condensing WHs. Post-tension deck construction with ProSet sleeves. | text | Benchmark KPIs | Verified | Scope + Submittal TOC
8 | insurance | Insurance Type | Not Wrap | text | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
9 | gc_pm | GC PM | TBD — Compass (PM per subcontract); Project Executive signatory on 12/7/2017 | text | Benchmark KPIs | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
10 | gc_sup | GC Sup | Brett (per Brett 2100 Madison folder — site super pattern across multiple OWP jobs) | text | Benchmark KPIs | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
11 | owp_signatory | OWP Signatory | Richard Donelson (OWP per Subcontract 220500-01, 12/7/2017 — 'Subcontractor Representative shall be: RICHARD DONELSON') | text | Benchmark KPIs | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
12 | contract_signed_date | Contract Signed Date | 2017-12-07 | date | Benchmark KPIs | Verified | 2050-Shelter Holdings subcontract 220500-01 + Boren & Spruce CO docs
13 | start_date | Work Start | 2017-12 | date | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
14 | end_date | Work End | 2019-05 | date | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
15 | duration_months | Duration (months) | 18 | months | Benchmark KPIs | Verified | Derived
16 | unit_count | Unit Count | 50 | units | Benchmark KPIs | Verified | Submittal TOC
17 | total_fixtures | Total Fixtures | 395 | count | Benchmark KPIs | Verified | Submittal TOC
18 | contract_original | Contract Original | 897800 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
19 | contract_final | Contract Final | 918566 | USD | Benchmark KPIs | Verified | OWP Project List with Schedule - UPDATED 04-01-26.xlsx
20 | co_net | Change Orders ($) | 20766 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026) + CO log
21 | co_pct | CO % of Contract | 2.313% | % | Benchmark KPIs | Verified | Derived
22 | revenue | Revenue | 918566 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
23 | direct_cost | Direct Cost | 491756.9 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
24 | net_profit | Net Profit | 426809.1 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
25 | gross_margin | Gross Margin | 46.46% | % | Benchmark KPIs | Verified | Derived
26 | retainage | Retainage | 45928.3 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
27 | retainage_pct | Retainage % of Revenue | 5% | % | Benchmark KPIs | Verified | Derived
28 | labor_cost | Labor Cost | 163505.5 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
29 | material_cost | Material Cost | 204958.79 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
30 | overhead_cost | Overhead Cost | 37734.01 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
31 | burden_cost | Burden Cost | 72671.19 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
32 | tax_cost | Tax Cost | 12535.41 | USD | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
33 | total_hours | Total Labor Hours | 5763.5 | hours | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
34 | total_workers | Total Workers | 22 | count | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
35 | blended_wage | Blended Gross Wage | 28.3691 | USD/hr | Benchmark KPIs | Verified | Derived
36 | loaded_wage | Fully-Loaded Wage | 57.9979 | USD/hr | Benchmark KPIs | Verified | Derived
37 | burden_mult | Burden Multiplier | 1.3421 | x | Benchmark KPIs | Verified | Derived
38 | roughin_hours | Rough-in Hours | 2862.5 | hours | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
39 | finish_hours | Finish Hours | 503 | hours | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
40 | rev_per_hour | Revenue per Hour | 159.3764 | USD/hr | Benchmark KPIs | Verified | Derived
41 | profit_per_hour | Profit per Hour | 74.0538 | USD/hr | Benchmark KPIs | Verified | Derived
42 | rev_per_unit | Revenue per Unit | 18371.32 | USD | Benchmark KPIs | Verified | Derived
43 | cost_per_unit | Direct Cost per Unit | 9835.138 | USD | Benchmark KPIs | Verified | Derived
44 | hours_per_unit | Hours per Unit | 115.27 | hours | Benchmark KPIs | Verified | Derived
45 | rev_per_fixture | Revenue per Fixture | 2325.4835 | USD | Benchmark KPIs | Verified | Derived
46 | labor_pct | Labor % of Revenue | 17.8% | % | Benchmark KPIs | Verified | Derived
47 | material_pct | Material % of Revenue | 22.31% | % | Benchmark KPIs | Verified | Derived
48 | total_vendors | Total Vendors | 23 | count | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
49 | total_invoices | Total Invoices | 16 | count | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
50 | top_worker_share | Top Worker Share | 17.55% | % | Benchmark KPIs | Verified | Derived
51 | top5_worker_share | Top 5 Worker Share | 67.25% | % | Benchmark KPIs | Verified | Derived
52 | cost_code_count | Cost Codes Active | 30 | count | Benchmark KPIs | Verified | 2050 Job Detail Report.pdf (Sage Timberline, 04/03/2026)
53 | executed_co_count | Executed CO Count | 8 | count | Benchmark KPIs | Verified | CO log
54 | cor_count | COR Count | 19 | count | Benchmark KPIs | Verified | GDrive COR folder
55 | rfi_asi_count | RFI/ASI Count | 4 | count | Benchmark KPIs | Verified | GDrive ASI-RFI folder
56 | submittal_count | Submittal Count | 13 | count | Benchmark KPIs | Verified | GDrive Submittals
57 | po_count_total | PO Total (all) | 140 | count | Benchmark KPIs | Verified | GDrive POs

## Reconciliation
Reconciliation
Cross-sheet formula checks
# | Check | Value A | Value B | Delta | Status | Tabs
1 | Revenue = Contract Final | 918566 | 918566 | 0 | TIES | 1↔8
2 | Expenses = Labor+Mat+OH+Burden+Tax | 491756.9 | 491404.9 | 352 | WITHIN | 1↔3
3 | Net Profit = Revenue - Expenses | 426809.1 | 426809.1 | 0 | TIES | 1↔Derived
4 | Sage 999 actual = -Revenue | 918566 | 918566 | 0 | TIES | 2↔1
5 | Total Hours = Worker hours sum | 5763.5 | 5763.5 | 0 | TIES | 5↔2
6 | Contract Final - Orig = CO implied | 20766 | 20766 | 0 | TIES | 11↔Derived
7 | Worker count | 22 | 22 | 0 | TIES | 5↔1
8 | Cost code count | 30 | 30 | 0 | TIES | 2↔16