## 01 Overview
OWP #2051 · Vail Apartments
Compass · 163 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 2588279.5
Revised budget (expenses) | 1760397.22
Forecast net profit | 827882.28
Forecast margin | 31.99%
Progress to Date
Work complete (billed) | 2588280
Retention held | 126113.98
Earned less retention | 2462166.02
Balance to finish | -0.5
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 32235.75
AP | 453330.32
PR | 809520.68
AR | -2588279.5

## 02 Job Info
JOB #2051 · COMPASS · VAIL APARTMENTS — FULL PROJECT INFORMATION
Sourced from executed subcontract (18-0622-0500) + GDrive folder scan + dashboard PROJECT_TEAMS
IDENTITY
OWP Job ID | 2051
Project Name | Vail Apartments
Project Name (full) | Centerpoint Mixed-Use (Vail Apartments)
Subcontract Number | 18-0622-0500
Effective Date | August 14, 2018
Site Address | 17962 Midvale Avenue N, Shoreline, WA 98136
City / State / ZIP | Shoreline, WA 98136
⚠ Dashboard fix needed | PROJECTS['2051'].location currently reads 'Bellevue area, WA' — should be 'Shoreline, WA' per executed contract
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Compass General Construction I, LLC
GC Address | 733 7th Avenue, Suite 212, Kirkland, WA 98033
GC Phone | (206) 320-8741
GC Fax | (206) 323-4719
GC Contract Signatory | Ryan Ames, Vice President
GC Project Manager | Justin Anderson
GC Superintendent | Will Fenton
GC Project Engineer | Jeff Seeb
PROJECT TEAM — OWP (SUBCONTRACTOR)
OWP Legal Name | Oneway Plumbing, LLC
OWP Address | 127 10th Street South, Suite 200, Kirkland, WA 98033
OWP Phone | 425-968-8314
OWP Contract Signatory | Richard Donelson, Vice President
OWP Subcontractor Rep | Richard Donelson
OWP RI Foreman | Bob
OWP License # | ONEWAWP895BU (renewal cycle; original expired 1/31/2019)
OWP Federal Tax ID | 27-4605928
OWP Unemployment ID | 42342900
OWP Worker's Comp ID | 207548-00
PROJECT TEAM — OWNER
Owner Legal Name | AAA Management, LLC dba ADC Ridge at Sun Valley
Owner Address | 1450 Frazee Road, Suite 414, San Diego, CA 92108
Owner Short Name | AAA Management
PROJECT TEAM — DESIGN
MEP / Plumbing Engineer | Franklin Engineering
Architect | TBD (not in dashboard) — see Plans folder
Structural Engineer | TBD
Civil Engineer | TBD
INSURANCE & BONDING
Insurance Type | Not Wrap (OWP carries own CGL/WC)
Insurance Carrier | Hub International / Liberty Mutual
Insurance Policy # | BKA 17 55850721
CONTRACT & FINANCIALS
Original Contract | $2,672,000
Final Contract | $2,588,280
Net Change Orders | ($83,720) net — credit-net posture (-3.1%)
Retention Percentage | 5% per Article 7.2.2
Retention Held | $126,114 (still held per JDR 04/03/2026, 7+ yrs aged)
Schedule | March 2018 (subcontract effective 8/14/2018) → Closed (retention release pending — 2023) · ~22 months field + retention tail
SCOPE & FIXTURES (per Job Ticket 3-4-2020)
Plumbing Units | 163
Resident Unit Trim | 191 toilets + 17 ADA + 192 lavs Type B + 153 SS sinks (Ruvati RVH7400) + 11 ADA SS sinks (Elkay ELUHAD211550) + 202 tub/shower stalls (Fibercare ET60-32RT-HC-80S L/R) + 208 Delta 559LF-PP faucets + 14 amenity fixtures + 4 Bock OptiTherm OT-300N-A water heaters + 2 Lawler 805 master mixing valves + 2 backflow preventers + 1 booster package + 13 Watts RD25 roof drains + 21 Watts FD33 garage drains + 15 Watts FD15 floor drains
Amenity Fixtures | L3 amenity (1 dual lav, 1 SS sink, 1 hotsink), 2 Elkay drinking fountains w/bottle filler, 1 Forever Stainless ADA dog wash (60HTY-RH), 2 Mustee 63M mop sinks, 4 Moen garbage disposal push buttons (per CO #14), 1 coffee machine line
Building Systems | 1 wvs/cw stub (retail), 1 common gas supply (4 water heaters + 2 rooftop HVAC + 2 BBQ + 2 firepit + L2 gas cooktop + L3 gas), 1 fireplace L2, 1 yard hydrant rooftop, 4 hosebibs garage mech rooms, 10 ext keyless hose bibs, 1 trash room hot/cold hose bib
Scope (design-build) | Plumbing per CAD drawings — design-build per Article 4.7. Holdrite firestop sleeve system at post-tension decks.
Scope EXCLUDES | Shoreline plumbing, gas/boiler permits/plan review fees (by owner). Excavation/backfill/dewatering. Hoisting concrete basin. Foundation/footing drains. Storm detention piping. Pump systems for storm/sanitary drainage. Fire-rated tub/shower enclosures. Wash machine drain pans. Kitchen sink garbage disposals. Utility/unit meters.
DOCUMENTS ON FILE (GDrive)
Executed Contract | One Way Plumbing - Vail Apartments Fully Executed Contract.pdf
PSA Agreement | One Way Plumbing - PSA Agreement - Final with exhibits - 2-20-18 - executed.pdf
Insurance Requirements | Vail Insurance Requirements.pdf
Job Tickets | 14 ticket revisions (12-10-18 → 3-4-2020)
Latest Ticket | Vail Apartments job ticket 3-4-2020.pdf
Change Orders (SCOs) | 17 files in Change Orders/CO's/
CORs | 7 numbered CORs in Change Orders/COR's/
RFIs | 120+ (RFI 95, 99, 106, 109, 113, 117, 119, 120, 121, ..., 143)
ASIs | 1 (ASI 03 on file)
Permits | 9 files in Permits/ — City of Shoreline #890-895 (Vail Apartments-Shoreline)
Sub-Permits | Boiler/PV Installation Permits HWT 1-4 + PV 1-2 issued 6-15-2020
Plans/Photos/Submittals | Plans / Photos / Submittals (full design set)
Vendor Subfolders | Brett Vail (sub contact), Franklin Vail Apartments (MEP design), RUVATI application.docx
Delivery Instructions | Vail Apartments Trucking.pdf (delivery instructions)
FIXTURE SCHEDULE (verified from Job Ticket)
Sourced from latest Job Ticket. Two totals shown: 'Main' = standard plumbing-engineering fixture schedule (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + coffee bar). 'Inclusive' adds appliance rough-ins (dishwasher + washer + icemaker) and matches the 2020 dashboard convention.
Toilets (water closets) | 211
Lavs (lavatory sinks) | 206
Tub/showers + handshowers | 213
Kitchen sinks | 168
Drinking fountains | 2
Mop sinks | 2
Dog-wash sink | 1
MAIN FIXTURE TOTAL | 803
INCLUSIVE FIXTURE TOTAL (with appliance rough-ins) | 1302
Main fixtures / unit: 4.93 · Inclusive / unit: 7.99

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 2738000 | 2588279.5 | -149720.5
Executed change orders (net) | 0 | -149720.5 | -149720.5
Total contract value | 2738000 | 2438559 | -299441
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
STATEMENT OF VALUES — SUMMARY (from JDR + Contract)
Original Contract | 2672000
Net Change Orders | -83720
Final Contract Value | 2588280
Total Billed to Date | 2588280
Retention Held (5%) | 126114
Net Paid to OWP | 2462166
Percent Complete | 100.0%
PAY APPLICATION DETAIL — DATA GAP
Per-pay-app history is not in 2051_data.json — the Sage parse rolls up to AR totals only. Full pay-app series lives in GDrive: 2051-Compass, Vail Apartments/Billing/. To populate this tab on a per-app basis, re-parse Billing/ folder PDFs and inject into 2051_data.json under a new 'pay_apps' array.

## 05 Change Orders
Change Order Log
EXECUTED CHANGE ORDERS (SCO) — SOURCE: GDRIVE/CHANGE ORDERS/CO's/
# | SCO ID | Description | Type | Source File
1 | SCO 01 | Plumbing Alternates and Adjustments | Field/Coord | GDrive: Change Orders/CO's/
2 | SCO 02 | Firestopping | Field/Coord | GDrive: Change Orders/CO's/
3 | SCO 03 | Alternate Plumbing Fixtures | Field/Coord | GDrive: Change Orders/CO's/
4 | SCO 04 | Added Unit 330 and Common Areas | Owner-Directed | GDrive: Change Orders/CO's/
5 | SCO 05 | Temp Gas Lines for Temp Heat (10ea POCs, levels 3-7) | Field/Coord | GDrive: Change Orders/CO's/
6 | SCO 06 | ADA Sink Modification | Owner-Directed | GDrive: Change Orders/CO's/
7 | SCO 07 | Added Drinking Fountain | Owner-Directed | GDrive: Change Orders/CO's/
8 | SCO 08 | ADA Dog Wash Upgrade | Owner-Directed | GDrive: Change Orders/CO's/
9 | SCO 09 | L4 Roof Piping Retesting | Field/Coord | GDrive: Change Orders/CO's/
10 | SCO 010 | (referenced — file on Drive) | Field/Coord | GDrive: Change Orders/CO's/
11 | SCO 012 | Ruvati Sink Change (replaces previous SS sink spec) | Field/Coord | GDrive: Change Orders/CO's/
12 | SCO 015 | Re-route Piping in Amenity Space | Field/Coord | GDrive: Change Orders/CO's/
13 | SCO 017 | Replacement Sinks | Field/Coord | GDrive: Change Orders/CO's/
14 | Misc | Amenity Plumbing Fixture Upgrades | Field/Coord | GDrive: Change Orders/CO's/
15 | Misc | Outdoor Kitchen Sink Change | Field/Coord | GDrive: Change Orders/CO's/
16 | Misc | Owner Plumbing Modifications | Owner-Directed | GDrive: Change Orders/CO's/
17 | Misc | Remove Dishwasher Installation from Scope | Field/Coord | GDrive: Change Orders/CO's/
18 | Closeout | One Way Closeout Change Order | Field/Coord | GDrive: Change Orders/CO's/
19 | Reconcil | Vail – One-Way COP Log Reconciliation | Field/Coord | GDrive: Change Orders/CO's/
OPEN/SUBMITTED CHANGE ORDER REQUESTS (COR) — SOURCE: GDRIVE/CHANGE ORDERS/COR's/
# | COR ID | Description | Status | Source File
1 | COR #01 | West Wall Foundation Drainage | Submitted | GDrive: Change Orders/COR's/
2 | COR #02 | Added Fixtures per BP Cycle 2 Corrections (revised r1) | Submitted | GDrive: Change Orders/COR's/
3 | COR #03 | ADA Dog Wash Upgrade | Submitted | GDrive: Change Orders/COR's/
4 | COR #04 | RFI-117 Move Piping for Retail Door to Garage | Submitted | GDrive: Change Orders/COR's/
5 | COR #05 | RFI-143 Move Piping for Mail Room Wall Relocation | Submitted | GDrive: Change Orders/COR's/
6 | COR #06 | IFC Plan Set Changes, Added Unit L3 | Submitted | GDrive: Change Orders/COR's/
7 | COR #07 | Alternate Fixtures | Submitted | GDrive: Change Orders/COR's/
NET CO IMPACT
Original Contract | $2,672,000
Final Contract | $2,588,280
Net Dollar Impact | ($83,720) — credit-net (-3.1%)
Posture | Unusual: scope deletes (e.g. Remove Dishwasher Installation) net against scope adds (Unit 330, ADA Dog Wash, Drinking Fountain, etc.)
Total Documented Events | 19 SCOs + 7 CORs = 26 change events

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 16300 | 16550 | 6172.5 | 10377.5 | 0 | 37.3%
101 | Takeoff & Purchase Labor | 24400 | 25450 | 19701 | 5749 | 0 | 77.41%
110 | Underground Labor | 21500 | 18940 | 17320 | 1620 | 0 | 91.45%
111 | Garage Labor | 123400 | 102722 | 70146.5 | 32575.5 | 0 | 68.29%
112 | Canout Labor | 21400 | 21796 | 13477.82 | 8318.18 | 0 | 61.84%
120 | Roughin Labor | 387125 | 326457 | 261842.25 | 64614.75 | 0 | 80.21%
130 | Finish Labor | 59000 | 59314 | 74007.5 | -14693.5 | 0 | 124.8%
140 | Gas Labor | 11900 | 14255 | 10694 | 3561 | 0 | 75.02%
141 | Water Main/Insulation Lab | 55300 | 55500 | 46255 | 9245 | 0 | 83.34%
142 | Mech Room Labor | 17000 | 17000 | 16058 | 942 | 0 | 94.46%
143 | Condensation Drains Labor | 0 | 0 | 416 | -416 | 0 | 0%
210 | Underground Material | 13000 | 10100 | 9764.8 | 335.2 | 0 | 96.68%
211 | Garage Material | 75760 | 59835 | 9727.46 | 50107.54 | 0 | 16.26%
212 | Canout Material | 21400 | 21996 | 13552.21 | 8443.79 | 0 | 61.61%
220 | Roughin Material | 230840 | 145597 | 47851.97 | 97745.03 | 0 | 32.87%
230 | Finish Material | 332585 | 352190 | 281538.12 | 70651.88 | 0 | 79.94%
240 | Gas Material | 9800 | 12214 | 5341.44 | 6872.56 | 0 | 43.73%
241 | Water Main/Insulation Mat | 51400 | 51400 | 43355.63 | 8044.37 | 0 | 84.35%
242 | Mech Room Material | 20400 | 20400 | 20399.37 | 0.63 | 0 | 100%
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 | 0 | 0%
600 | Subcontractor | 2500 | 31650 | 33715 | -2065 | 0 | 106.5%
601 | Engineering/Plans | 45000 | 48022 | 22226.25 | 25795.75 | 0 | 46.28%
995 | Payroll Burden | 334376.89 | 298673.44 | 230366.76 | 68306.68 | 0 | 77.13%
998 | Payroll Taxes | 56405.36 | 50335.78 | 41157.17 | 9178.61 | 0 | 81.77%
TOTAL |  | 1930792.25 | 1760397.22 | 1295086.75 | 465310.47 | 0 | 73.57%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 657984 | 536090.57 | 121893.43 | 81.47%
Material | 9 | 673732 | 431531 | 242201 | 64.05%
Overhead | 2 | 79672 | 55941.25 | 23730.75 | 70.21%
Burden | 2 | 349009.22 | 271523.93 | 77485.29 | 77.8%
TOTAL | 24 | 1760397.22 | 1295086.75 | 465310.47 | 73.57%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 16550 | 6172.5 | 10377.5 | -62.7% | UNDER
101 | Takeoff & Purchase Labor | 25450 | 19701 | 5749 | -22.59% | UNDER
110 | Underground Labor | 18940 | 17320 | 1620 | -8.553% | ON
111 | Garage Labor | 102722 | 70146.5 | 32575.5 | -31.71% | UNDER
112 | Canout Labor | 21796 | 13477.82 | 8318.18 | -38.16% | UNDER
120 | Roughin Labor | 326457 | 261842.25 | 64614.75 | -19.79% | UNDER
130 | Finish Labor | 59314 | 74007.5 | -14693.5 | 24.77% | OVER
140 | Gas Labor | 14255 | 10694 | 3561 | -24.98% | UNDER
141 | Water Main/Insulation Lab | 55500 | 46255 | 9245 | -16.66% | UNDER
142 | Mech Room Labor | 17000 | 16058 | 942 | -5.541% | ON
143 | Condensation Drains Labor | 0 | 416 | -416 | 0% | UNBUDGETED
210 | Underground Material | 10100 | 9764.8 | 335.2 | -3.319% | ON
211 | Garage Material | 59835 | 9727.46 | 50107.54 | -83.74% | UNDER
212 | Canout Material | 21996 | 13552.21 | 8443.79 | -38.39% | UNDER
220 | Roughin Material | 145597 | 47851.97 | 97745.03 | -67.13% | UNDER
230 | Finish Material | 352190 | 281538.12 | 70651.88 | -20.06% | UNDER
240 | Gas Material | 12214 | 5341.44 | 6872.56 | -56.27% | UNDER
241 | Water Main/Insulation Mat | 51400 | 43355.63 | 8044.37 | -15.65% | UNDER
242 | Mech Room Material | 20400 | 20399.37 | 0.63 | -0.003088% | ON
600 | Subcontractor | 31650 | 33715 | -2065 | 6.524% | ON
601 | Engineering/Plans | 48022 | 22226.25 | 25795.75 | -53.72% | UNDER
995 | Payroll Burden | 298673.44 | 230366.76 | 68306.68 | -22.87% | UNDER
998 | Payroll Taxes | 50335.78 | 41157.17 | 9178.61 | -18.23% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Ferguson Enterprises, Inc. #3007 | 80201.52 | 15 | 17.69%
Keller Supply Company | 79385.05 | 28 | 17.51%
Consolidated Supply Co. | 69327.67 | 67 | 15.29%
Rosen Supply Kirkland | 68719.97 | 108 | 15.16%
California Hydronics Corp | 57789 | 1 | 12.75%
Ruvita USA, Inc. | 31600 | 3 | 6.971%
Mechanical Firestop Services, LLC | 29150 | 3 | 6.43%
Franklin Engineering | 22226.25 | 9 | 4.903%
Capital One Credit Card | 6309.27 | 10 | 1.392%
Mechanical Resource Services, Inc. | 4565 | 2 | 1.007%
Quality Concrete Products, Inc. $32 | 3164 | 2 | 0.6979%
Core & Main LP $HD Supply Waterworks | 602.01 | 3 | 0.1328%
Mechanical Sales, Inc. | 290.58 | 1 | 0.0641%
TOTAL AP | 453330.32 | 252

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Boss, Kyle A | 1574 | 30203 | 19.1887 | APPRENTICE/HELPER
Rodriguez Arevalos, Christian | 1473.5 | 38516 | 26.1391 | JOURNEYMAN
Romero Garza, Jesus I | 1389.5 | 27869 | 20.0569 | JOURNEYMAN
Lopez, Maslin A | 1293 | 22419 | 17.3387 | APPRENTICE/HELPER
Roberts, Lake A | 1253 | 27870 | 22.2426 | JOURNEYMAN
Ross, Kelli M | 1222 | 51976 | 42.5336 | LEAD/SUPERVISOR
Wilson, Garret A | 1190 | 42673 | 35.8597 | JOURNEYMAN
Escalante Escobar, Boanerge | 981 | 21822 | 22.2446 | JOURNEYMAN
Montenegro, Carlos E | 876 | 27298 | 31.1621 | JOURNEYMAN
Jimenez Alvarenga, Gerson M | 868 | 21616 | 24.9032 | JOURNEYMAN
Boss, Aaron J | 701 | 11216 | 16 | APPRENTICE/HELPER
Boss, Benjamin T | 694 | 11440 | 16.4841 | APPRENTICE/HELPER
McCabe, Thomas C | 589 | 21870 | 37.1307 | LEAD/SUPERVISOR
Amaya Gonzalez, Edilberto A | 561 | 17968 | 32.0285 | JOURNEYMAN
Hubbard, Robert W | 536 | 27470 | 51.25 | LEAD/SUPERVISOR
Foster, Antonio T | 424 | 8614 | 20.316 | APPRENTICE/HELPER
Quintanilla, Esteban R | 396 | 12647 | 31.9369 | JOURNEYMAN
Sanders, Allen O | 357.5 | 19305 | 54 | LEAD/SUPERVISOR
Trower-Kelly, Fidel D | 352 | 7392 | 21 | JOURNEYMAN
Silva Morales, Jair J | 331 | 8937 | 27 | JOURNEYMAN
Cruz Guzman, Joel A | 304 | 8512 | 28 | JOURNEYMAN
Cruz Gonzalez, Julio C | 278 | 7784 | 28 | JOURNEYMAN
Barbosa, Michael S | 268 | 4650 | 17.3507 | APPRENTICE/HELPER
Gerard, Jeffrey S | 242.5 | 12874 | 53.0887 | LEAD/SUPERVISOR
Lovo, German G | 241 | 5870 | 24.3568 | JOURNEYMAN
Donelson, Richard T | 208 | 13000 | 62.5 | LEAD/SUPERVISOR
Cruz Reyes, Jose | 176 | 5632 | 32 | JOURNEYMAN
Ramos Herrera, Franklin J | 158 | 4073 | 25.7785 | JOURNEYMAN
Rosas Olivares, Jorge C | 151.5 | 3030 | 20 | JOURNEYMAN
Paco Leyva, Orlando | 85.5 | 3389 | 39.6374 | LEAD/SUPERVISOR
Rivera, Eli P | 84 | 2322 | 27.6429 | JOURNEYMAN
Sepulveda Gonzalez, Alfredo | 69 | 2208 | 32 | JOURNEYMAN
Ascencio, Jose L | 56 | 1304 | 23.2857 | JOURNEYMAN
Cornejo Orellana, Carlos E | 30 | 589 | 19.6333 | APPRENTICE/HELPER
Eliassen, Cory H | 28 | 840 | 30 | JOURNEYMAN
Vazquez Popoca, Jose N | 24 | 456 | 19 | APPRENTICE/HELPER
Castro Hernandez, Jose A | 24 | 840 | 35 | JOURNEYMAN
Benites Portillo, Marvin E | 18 | 396 | 22 | JOURNEYMAN
Gauthier, Dillon R | 16 | 272 | 17 | APPRENTICE/HELPER
Guerrero Espinoza, Mario | 8 | 128 | 16 | APPRENTICE/HELPER
Rivera, Jorge A | 4 | 0 | 0 | APPRENTICE/HELPER
Barnhart, Joseph N | 4 | 200 | 50 | LEAD/SUPERVISOR
Waites, Thaddeus Z | 4 | 258 | 64.5 | OT-ONLY
Gerard, Jordan E | 3 | 108 | 36 | LEAD/SUPERVISOR
Anderson, Richard P | 3 | 141 | 47 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 10 | 3250.5 | 150332 | 16.63%
JOURNEYMAN | 23 | 11258.5 | 297420 | 57.59%
APPRENTICE/HELPER | 11 | 5036 | 89987 | 25.76%
OT-ONLY | 1 | 4 | 258 | 0.02046%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 19549
Active workers | 45
Hours per unit (to date) | 119.9
Revenue per labor hour (billed) | 132.4
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 31.99% | 34% | -2.014%
Roughin labor share (code 120) | 49.61% | 45% | 4.615%
Top vendor concentration | 17.69% | 38% | -20.31%
Hours per unit | 119.9325 | 95 | 24.9325

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Finish Labor (130) over revised | ⚠ WATCH | Actual $74,008 vs revised $59,314 (+25%) — monitor
Top vendor concentration (Ferguson Enterprises) | ✓ OK | 18% of AP ($80,202) — acceptable
Retention aging | ✓ OK | $126,114 held · 4.9% of billed · standard range
Forecast margin | ✓ OK | 32.0% forecast margin — healthy

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 1295086.75 | 1295086.75 | 0
Revenue billed (AR ·-1) | -2588279.5 | 2588279.5 | -5176559
AP source total |  | 453330.32 | —
PR source total |  | 809520.68 | —
GL source total |  | 32235.75 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2051 live project. 17-tab JCR schema on revised budget basis.
2026-04-25 | v1.1 · enriched | Patched by enrich_2051.py: filled SOV-PayApps and Change Orders tabs (were empty), expanded Job Info from 13 rows to 60+ rows of key-players + contract + permit + fixture detail, flagged dashboard location typo (Bellevue area → Shoreline WA). Source: executed subcontract 18-0622-0500 + GDrive folder scan + dashboard PROJECT_TEAMS['2051'].