## Summary
#2051 · Vail Apartments
Compass · 163 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
2588279.5 | 31.99% | 2588280 | -0.5
Key facts
Original contract |  | 2738000
Revised contract (CO impact) |  | 2588279.5
Executed COs (net) |  | -149720.5
Retention held |  | 126113.98
Revised expense budget |  | 1760397.22
Forecast net profit |  | 827882.28
Percent complete |  | 100%
Live signals
Finish Labor (130) over | ⚠ WATCH | Actual $74,008 vs revised $59,314 (+25%) — monitor
Top vendor (Ferguson Enterprises) | ✓ OK | 18% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 32.0% forecast — healthy
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Ferguson Enterprises, Inc. #3007 | 15 | 80201.52 | 17.69%
Keller Supply Company | 28 | 79385.05 | 17.51%
Consolidated Supply Co. | 67 | 69327.67 | 15.29%
Rosen Supply Kirkland | 108 | 68719.97 | 15.16%
California Hydronics Corp | 1 | 57789 | 12.75%
Ruvita USA, Inc. | 3 | 31600 | 6.971%

## Transactions
Transactions Detail
JDR source transactions for job #2051 · 4258 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 03/23/18 | 584 | Gerard, Jeffrey S | 1 | 50 | 99998
PR | 100 | 07/27/18 | 835 | Gerard, Jeffrey S | 1 | 50 | 20593
PR | 100 | 08/31/18 | 1070 | Gerard, Jeffrey S | 2 | 100 | 90962
PR | 100 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 100 | 09/14/18 | 341 | Gerard, Jeffrey S | 1 | 50 | 21174
PR | 100 | 09/21/18 | 553 | Gerard, Jeffrey S | 1 | 50 | 21245
PR | 100 | 09/28/18 | 740 | Gerard, Jeffrey S | 1 | 50 | 90884
PR | 100 | 10/05/18 | 103 | Gerard, Jeffrey S | 3 | 150 | 91392
PR | 100 | 10/12/18 | 310 | Gerard, Jeffrey S | 2 | 100 | 21467
PR | 100 | 10/19/18 | 508 | Gerard, Jeffrey S | 1 | 50 | 91542
PR | 100 | 10/26/18 | 775 | Gerard, Jeffrey S | 4 | 200 | 21616
PR | 100 | 11/02/18 | 77 | Gerard, Jeffrey S | 3 | 150 | 21687
PR | 100 | 11/09/18 | 258 | Gerard, Jeffrey S | 2 | 100 | 20892
PR | 100 | 11/16/18 | 514 | Gerard, Jeffrey S | 2 | 100 | 21837
PR | 100 | 11/21/18 | 690 | Gerard, Jeffrey S | 2 | 100 | 21912
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 3 | 156 | 22057
PR | 100 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 100 | 12/21/18 | 578 | Gerard, Jeffrey S | 5 | 260 | 922269
PR | 100 | 01/11/19 | 282 | Gerard, Jeffrey S | 1 | 52 | 922484
PR | 100 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 100 | 02/01/19 | 71 | Gerard, Jeffrey S | 1.5 | 78 | 22700
PR | 100 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 100 | 02/15/19 | 389 | Gerard, Jeffrey S | 1.5 | 78 | 922840
PR | 100 | 02/22/19 | 648 | Gerard, Jeffrey S | 2 | 104 | 922910
PR | 100 | 03/08/19 | 315 | Gerard, Jeffrey S | 1 | 52 | 923054
PR | 100 | 03/15/19 | 563 | Gerard, Jeffrey S | 2 | 104 | 23125
PR | 100 | 03/22/19 | 777 | Gerard, Jeffrey S | 1 | 52 | 923198
PR | 100 | 03/29/19 | 990 | Gerard, Jeffrey S | 2 | 104 | 23273
PR | 100 | 03/29/19 | 990 | Gerard, Jeffrey S | 3 | 156 | 23273
PR | 100 | 04/12/19 | 398 | Gerard, Jeffrey S | 2 | 104 | 23421
PR | 100 | 04/19/19 | 597 | Gerard, Jeffrey S | 2 | 104 | 923497
PR | 100 | 04/26/19 | 813 | Gerard, Jeffrey S | 2 | 110 | 23569
PR | 100 | 05/03/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 923644
PR | 100 | 05/10/19 | 235 | Gerard, Jeffrey S | 2 | 110 | 23720
PR | 100 | 05/17/19 | 468 | Gerard, Jeffrey S | 1 | 55 | 923799
PR | 100 | 05/24/19 | 681 | Gerard, Jeffrey S | 3 | 165 | 923876
PR | 100 | 05/31/19 | 953 | Gerard, Jeffrey S | 1 | 55 | 923953
PR | 100 | 06/07/19 | 255 | Gerard, Jeffrey S | 1 | 55 | 924030
PR | 100 | 06/14/19 | 524 | Gerard, Jeffrey S | 3.5 | 192.5 | 24104
PR | 100 | 06/21/19 | 694 | Gerard, Jeffrey S | 1 | 55 | 24180
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 1 | 55 | 24255
PR | 100 | 07/05/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 924330
PR | 100 | 07/19/19 | 586 | Gerard, Jeffrey S | 3 | 165 | 24485
PR | 100 | 08/02/19 | 77 | Gerard, Jeffrey S | 1 | 55 | 924708
PR | 100 | 08/09/19 | 329 | Gerard, Jeffrey S | 2 | 110 | 924782
PR | 100 | 08/16/19 | 637 | Gerard, Jeffrey S | 3 | 165 | 924856
PR | 100 | 08/23/19 | 874 | Gerard, Jeffrey S | 2 | 110 | 924932
PR | 100 | 08/30/19 | 1065 | Gerard, Jeffrey S | 1 | 55 | 25009
PR | 100 | 09/06/19 | 86 | Gerard, Jeffrey S | 2 | 110 | 925084
PR | 100 | 09/13/19 | 309 | Gerard, Jeffrey S | 2 | 110 | 25158
PR | 100 | 10/11/19 | 335 | Gerard, Jeffrey S | 1 | 55 | 925469
PR | 100 | 10/18/19 | 528 | Gerard, Jeffrey S | 5 | 275 | 25545
PR | 100 | 10/25/19 | 665 | Gerard, Jeffrey S | 3 | 165 | 925505
PR | 100 | 11/01/19 | 81 | Gerard, Jeffrey S | 3 | 174 | 925697
PR | 100 | 11/08/19 | 254 | Gerard, Jeffrey S | 2 | 116 | 925773
PR | 100 | 11/15/19 | 513 | Gerard, Jeffrey S | 2 | 116 | 925849
PR | 100 | 11/27/19 | 918 | Gerard, Jeffrey S | 1 | 58 | 925999
PR | 100 | 12/13/19 | 466 | Gerard, Jeffrey S | 1 | 58 | 926232
PR | 100 | 12/20/19 | 619 | Gerard, Jeffrey S | 2 | 116 | 926308
PR | 100 | 12/27/19 | 777 | Gerard, Jeffrey S | 1 | 58 | 26385
PR | 100 | 02/07/20 | 103 | Gerard, Jeffrey S | 1 | 58 | 26851
PR | 100 | 02/28/20 | 758 | Gerard, Jeffrey S | 1 | 58 | 927086
PR | 100 | 03/26/20 | 821 | Gerard, Jeffrey S | 1 | 58 | 927397
PR | 101 | 03/02/18 | 67 | Donelson, Richard T | 1 | 62.5 | 99999
PR | 101 | 03/09/18 | 184 | Gerard, Jeffrey S | 1 | 47 | 99998
PR | 101 | 03/23/18 | 583 | Donelson, Richard T | 1 | 62.5 | 99997
PR | 101 | 03/30/18 | 811 | Donelson, Richard T | 1 | 62.5 | 99350
PR | 101 | 03/30/18 | 812 | Gerard, Jeffrey S | 2 | 100 | 99351
PR | 101 | 04/27/18 | 684 | Gerard, Jeffrey S | 1 | 50 | 99649
PR | 101 | 05/11/18 | 286 | Donelson, Richard T | 1 | 62.5 | 99793
PR | 101 | 06/08/18 | 339 | Donelson, Richard T | 1 | 62.5 | 20079
PR | 101 | 06/15/18 | 527 | Donelson, Richard T | 1 | 62.5 | 20162
PR | 101 | 06/22/18 | 753 | Donelson, Richard T | 2 | 125 | 290232
PR | 101 | 06/29/18 | 1020 | Gerard, Jeffrey S | 1 | 50 | 20301
PR | 101 | 07/06/18 | 77 | Gerard, Jeffrey S | 1 | 50 | 920375
PR | 101 | 07/13/18 | 367 | Donelson, Richard T | 4 | 250 | 20400
PR | 101 | 07/13/18 | 368 | Gerard, Jeffrey S | 1 | 50 | 20401
PR | 101 | 07/20/18 | 507 | Donelson, Richard T | 3 | 187.5 | 920518
PR | 101 | 07/27/18 | 834 | Donelson, Richard T | 7 | 437.5 | 20592
PR | 101 | 07/27/18 | 835 | Gerard, Jeffrey S | 2 | 100 | 20593
PR | 101 | 08/17/18 | 550 | Donelson, Richard T | 2 | 125 | 20808
PR | 101 | 08/31/18 | 1069 | Donelson, Richard T | 1 | 62.5 | 90961
PR | 101 | 08/31/18 | 1070 | Gerard, Jeffrey S | 3 | 150 | 90962
PR | 101 | 09/07/18 | 105 | Donelson, Richard T | 10 | 625 | 91031
PR | 101 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 101 | 09/14/18 | 340 | Donelson, Richard T | 4 | 250 | 21173
PR | 101 | 09/14/18 | 341 | Gerard, Jeffrey S | 4 | 200 | 21174
PR | 101 | 09/21/18 | 552 | Donelson, Richard T | 1 | 62.5 | 21244
PR | 101 | 09/21/18 | 553 | Gerard, Jeffrey S | 4 | 200 | 21245
PR | 101 | 09/28/18 | 739 | Donelson, Richard T | 3 | 187.5 | 90883
PR | 101 | 09/28/18 | 740 | Gerard, Jeffrey S | 2 | 100 | 90884
PR | 101 | 10/05/18 | 102 | Donelson, Richard T | 4 | 250 | 91391
PR | 101 | 10/05/18 | 103 | Gerard, Jeffrey S | 3 | 150 | 91392
PR | 101 | 10/12/18 | 310 | Gerard, Jeffrey S | 5 | 250 | 21467
PR | 101 | 10/19/18 | 507 | Donelson, Richard T | 1 | 62.5 | 91541
PR | 101 | 10/19/18 | 508 | Gerard, Jeffrey S | 1 | 50 | 91542
PR | 101 | 10/26/18 | 775 | Gerard, Jeffrey S | 3 | 150 | 21616
PR | 101 | 11/02/18 | 76 | Donelson, Richard T | 1 | 62.5 | 21686
PR | 101 | 11/02/18 | 77 | Gerard, Jeffrey S | 2 | 100 | 21687
PR | 101 | 11/09/18 | 257 | Donelson, Richard T | 2 | 125 | 20891
PR | 101 | 11/09/18 | 258 | Gerard, Jeffrey S | 2 | 100 | 20892
PR | 101 | 11/16/18 | 513 | Donelson, Richard T | 4 | 250 | 21836
PR | 101 | 11/16/18 | 514 | Gerard, Jeffrey S | 1 | 50 | 21837
PR | 101 | 11/21/18 | 689 | Donelson, Richard T | 5 | 312.5 | 21911
PR | 101 | 11/21/18 | 690 | Gerard, Jeffrey S | 3 | 150 | 21912
PR | 101 | 11/30/18 | 901 | Gerard, Jeffrey S | 2 | 104 | 921984
PR | 101 | 12/07/18 | 113 | Donelson, Richard T | 8 | 500 | 22056
PR | 101 | 12/07/18 | 114 | Gerard, Jeffrey S | 2 | 104 | 22057
PR | 101 | 12/14/18 | 337 | Donelson, Richard T | 4 | 250 | 22197
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/21/18 | 578 | Gerard, Jeffrey S | 2 | 104 | 922269
PR | 101 | 12/28/18 | 768 | Donelson, Richard T | 1 | 62.5 | 22342
PR | 101 | 12/28/18 | 769 | Gerard, Jeffrey S | 2 | 104 | 22343
PR | 101 | 01/04/19 | 72 | Donelson, Richard T | 2 | 125 | 22300
PR | 101 | 01/04/19 | 73 | Gerard, Jeffrey S | 3 | 156 | 22301
PR | 101 | 01/11/19 | 281 | Donelson, Richard T | 3 | 187.5 | 922483
PR | 101 | 01/11/19 | 282 | Gerard, Jeffrey S | 2 | 104 | 922484
PR | 101 | 01/18/19 | 542 | Donelson, Richard T | 3 | 187.5 | 922557
PR | 101 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 101 | 01/25/19 | 786 | Donelson, Richard T | 6 | 375 | 922631
PR | 101 | 02/01/19 | 70 | Donelson, Richard T | 5 | 312.5 | 22699
PR | 101 | 02/01/19 | 71 | Gerard, Jeffrey S | 2 | 104 | 22700
PR | 101 | 02/08/19 | 226 | Donelson, Richard T | 2 | 125 | 22768
PR | 101 | 02/08/19 | 227 | Gerard, Jeffrey S | 2 | 104 | 22769
PR | 101 | 02/15/19 | 389 | Gerard, Jeffrey S | 1 | 52 | 922840
PR | 101 | 02/22/19 | 647 | Donelson, Richard T | 1 | 62.5 | 922909
PR | 101 | 02/22/19 | 648 | Gerard, Jeffrey S | 2 | 104 | 922910
PR | 101 | 03/01/19 | 74 | Donelson, Richard T | 2 | 125 | 22981
PR | 101 | 03/01/19 | 75 | Gerard, Jeffrey S | 2 | 104 | 22982
PR | 101 | 03/08/19 | 314 | Donelson, Richard T | 1 | 62.5 | 923053
PR | 101 | 03/08/19 | 315 | Gerard, Jeffrey S | 1 | 52 | 923054
PR | 101 | 03/15/19 | 562 | Donelson, Richard T | 3 | 187.5 | 23124
PR | 101 | 03/15/19 | 563 | Gerard, Jeffrey S | 1 | 52 | 23125
PR | 101 | 03/22/19 | 776 | Donelson, Richard T | 5 | 312.5 | 923197
PR | 101 | 03/22/19 | 777 | Gerard, Jeffrey S | 2 | 104 | 923198
PR | 101 | 04/05/19 | 152 | Gerard, Jeffrey S | 2 | 104 | 923346
PR | 101 | 04/12/19 | 398 | Gerard, Jeffrey S | 1 | 52 | 23421
PR | 101 | 04/19/19 | 596 | Donelson, Richard T | 1 | 62.5 | 923496
PR | 101 | 04/26/19 | 812 | Donelson, Richard T | 1 | 62.5 | 23568
PR | 101 | 04/26/19 | 813 | Gerard, Jeffrey S | 2 | 110 | 23569
PR | 101 | 05/03/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 923644
PR | 101 | 05/10/19 | 234 | Donelson, Richard T | 1 | 62.5 | 23719
PR | 101 | 05/10/19 | 235 | Gerard, Jeffrey S | 1 | 55 | 23720
PR | 101 | 05/17/19 | 468 | Gerard, Jeffrey S | 1 | 55 | 923799
PR | 101 | 05/24/19 | 680 | Donelson, Richard T | 2 | 125 | 923875
PR | 101 | 05/24/19 | 681 | Gerard, Jeffrey S | 3 | 165 | 923876
PR | 101 | 05/31/19 | 953 | Gerard, Jeffrey S | 2 | 110 | 923953
PR | 101 | 06/07/19 | 254 | Donelson, Richard T | 1 | 62.5 | 924029
PR | 101 | 06/07/19 | 255 | Gerard, Jeffrey S | 4 | 220 | 924030
PR | 101 | 06/14/19 | 523 | Donelson, Richard T | 6 | 375 | 24103
PR | 101 | 06/14/19 | 524 | Gerard, Jeffrey S | 4 | 220 | 24104
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 2 | 110 | 24180
PR | 101 | 06/28/19 | 910 | Donelson, Richard T | 4 | 250 | 24254
PR | 101 | 06/28/19 | 911 | Gerard, Jeffrey S | 3 | 165 | 24255
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 1 | 62.5 | 924329
PR | 101 | 07/05/19 | 82 | Gerard, Jeffrey S | 3 | 165 | 924330
PR | 101 | 07/12/19 | 353 | Gerard, Jeffrey S | 3 | 165 | 924405
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 101 | 07/26/19 | 685 | Donelson, Richard T | 2 | 125 | 24634
PR | 101 | 07/26/19 | 686 | Gerard, Jeffrey S | 2 | 110 | 24635
PR | 101 | 08/02/19 | 76 | Donelson, Richard T | 2 | 125 | 924707
PR | 101 | 08/09/19 | 328 | Donelson, Richard T | 1 | 62.5 | 924781
PR | 101 | 08/09/19 | 329 | Gerard, Jeffrey S | 3 | 165 | 924782
PR | 101 | 08/16/19 | 636 | Donelson, Richard T | 2 | 125 | 924855
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 1 | 62.5 | 25008
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 7 | 437.5 | 25008
PR | 101 | 09/06/19 | 85 | Donelson, Richard T | 2 | 125 | 925083
PR | 101 | 09/13/19 | 308 | Donelson, Richard T | 3 | 187.5 | 25157
PR | 101 | 09/20/19 | 547 | Gerard, Jeffrey S | 3 | 165 | 925233
PR | 101 | 09/27/19 | 705 | Donelson, Richard T | 1 | 62.5 | 925310
PR | 101 | 10/04/19 | 81 | Donelson, Richard T | 1 | 62.5 | 25388
PR | 101 | 10/04/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 25389
PR | 101 | 10/18/19 | 527 | Donelson, Richard T | 1 | 62.5 | 25544
PR | 101 | 10/18/19 | 528 | Gerard, Jeffrey S | 2 | 110 | 25545
PR | 101 | 10/25/19 | 664 | Donelson, Richard T | 2 | 125 | 925504
PR | 101 | 11/01/19 | 80 | Donelson, Richard T | 2 | 125 | 925696
PR | 101 | 11/08/19 | 254 | Gerard, Jeffrey S | 1 | 58 | 925773
PR | 101 | 12/13/19 | 465 | Donelson, Richard T | 5 | 312.5 | 926231
PR | 101 | 12/20/19 | 618 | Donelson, Richard T | 3 | 187.5 | 926307
PR | 101 | 12/27/19 | 776 | Donelson, Richard T | 3 | 187.5 | 26384
PR | 101 | 01/03/20 | 81 | Donelson, Richard T | 2 | 125 | 926462
PR | 101 | 01/10/20 | 352 | Donelson, Richard T | 6 | 375 | 26540
PR | 101 | 01/17/20 | 618 | Donelson, Richard T | 1 | 62.5 | 926617
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 3 | 187.5 | 926400
PR | 101 | 01/31/20 | 911 | Donelson, Richard T | 4 | 250 | 26772
PR | 101 | 02/07/20 | 102 | Donelson, Richard T | 4 | 250 | 26850
PR | 101 | 02/14/20 | 312 | Donelson, Richard T | 1 | 62.5 | 926928
PR | 101 | 02/21/20 | 528 | Donelson, Richard T | 2 | 125 | 27006
PR | 101 | 02/28/20 | 757 | Donelson, Richard T | 3 | 187.5 | 927085
PR | 101 | 03/06/20 | 119 | Donelson, Richard T | 4 | 250 | 927163
PR | 101 | 03/20/20 | 641 | Donelson, Richard T | 3 | 187.5 | 927321
PR | 101 | 04/03/20 | 42 | Donelson, Richard T | 1 | 62.5 | 927434
PR | 101 | 04/17/20 | 288 | Donelson, Richard T | 1 | 62.5 | 927551
PR | 101 | 04/24/20 | 424 | Donelson, Richard T | 1 | 62.5 | 927628
PR | 101 | 05/01/20 | 79 | Gerard, Jeffrey S | 5 | 290 | 927706
PR | 101 | 05/08/20 | 231 | Donelson, Richard T | 2 | 125 | 927784
PR | 101 | 05/08/20 | 232 | Gerard, Jeffrey S | 1 | 58 | 927785
PR | 101 | 05/15/20 | 384 | Donelson, Richard T | 2 | 125 | 927862
PR | 101 | 05/22/20 | 534 | Donelson, Richard T | 2 | 125 | 927933
PR | 101 | 05/22/20 | 535 | Gerard, Jeffrey S | 1 | 58 | 927934
PR | 101 | 05/29/20 | 659 | Donelson, Richard T | 1 | 62.5 | 928002
PR | 101 | 06/05/20 | 66 | Donelson, Richard T | 1 | 62.5 | 928055
PR | 101 | 06/05/20 | 67 | Gerard, Jeffrey S | 1 | 58 | 928056
PR | 101 | 06/19/20 | 423 | Gerard, Jeffrey S | 1 | 58 | 928200
PR | 101 | 07/02/20 | 50 | Donelson, Richard T | 2 | 125 | 928293
PR | 101 | 07/10/20 | 182 | Donelson, Richard T | 1 | 62.5 | 28341
PR | 110 | 10/12/18 | 276 | Lovo, German G | 22 | 528 | 21433
PR | 110 | 10/12/18 | 286 | Quintanilla, Esteban R | 24 | 1080 | 21443
PR | 110 | 10/12/18 | 291 | Rivera, Eli P | 16 | 432 | 21448
PR | 110 | 10/19/18 | 474 | Lovo, German G | 24 | 576 | 21507
PR | 110 | 10/19/18 | 484 | Quintanilla, Esteban R | 30 | 1350 | 21517
PR | 110 | 10/19/18 | 489 | Rivera, Eli P | 24 | 648 | 21522
PR | 110 | 10/26/18 | 703 | Ascencio, Jose L | 4 | 104 | 21543
PR | 110 | 10/26/18 | 740 | Lovo, German G | 23 | 552 | 21580
PR | 110 | 10/26/18 | 749 | Quintanilla, Esteban R | 36 | 1620 | 21589
PR | 110 | 10/26/18 | 754 | Rivera, Eli P | 4 | 108 | 21594
PR | 110 | 11/02/18 | 2 | Quintanilla, Esteban R | 39 | 1755 | 20888
PR | 110 | 11/02/18 | 45 | Lovo, German G | 28 | 672 | 21654
PR | 110 | 11/02/18 | 58 | Rivera, Eli P | 4 | 162 | 21667
PR | 110 | 11/02/18 | 58 | Rivera, Eli P | 30 | 810 | 21667
PR | 110 | 11/09/18 | 191 | Cornejo Orellana, Carlos E | 18 | 342 | 21695
PR | 110 | 11/09/18 | 223 | Lovo, German G | 2 | 72 | 21726
PR | 110 | 11/09/18 | 223 | Lovo, German G | 30 | 720 | 21726
PR | 110 | 11/09/18 | 232 | Quintanilla, Esteban R | 40 | 1800 | 21735
PR | 110 | 11/09/18 | 232 | Quintanilla, Esteban R | 2 | 135 | 21735
PR | 110 | 11/09/18 | 237 | Rivera, Eli P | 6 | 162 | 21740
PR | 110 | 11/16/18 | 437 | Benites Portillo, Marvin E | 8 | 176 | 21766
PR | 110 | 11/16/18 | 440 | Cornejo Orellana, Carlos E | 2 | 57 | 21769
PR | 110 | 11/16/18 | 440 | Cornejo Orellana, Carlos E | 10 | 190 | 21769
PR | 110 | 11/16/18 | 471 | Lovo, German G | 18 | 432 | 21799
PR | 110 | 11/16/18 | 480 | Quintanilla, Esteban R | 2 | 135 | 21808
PR | 110 | 11/16/18 | 480 | Quintanilla, Esteban R | 30 | 1350 | 21808
PR | 110 | 11/16/18 | 506 | Quintanilla, Esteban R | 2 | -135 | 21808
PR | 110 | 11/16/18 | 506 | Quintanilla, Esteban R | 30 | -1350 | 21808
PR | 110 | 11/16/18 | 509 | Quintanilla, Esteban R | 2 | 135 | 21834
PR | 110 | 11/16/18 | 509 | Quintanilla, Esteban R | 30 | 1350 | 21834
PR | 110 | 11/21/18 | 623 | Benites Portillo, Marvin E | 10 | 220 | 21845
PR | 110 | 11/21/18 | 655 | Lovo, German G | 10 | 240 | 21876
PR | 110 | 11/21/18 | 664 | Quintanilla, Esteban R | 12 | 540 | 21885
PR | 110 | 11/21/18 | 687 | Quintanilla, Esteban R | 12 | -540 | 21885
PR | 110 | 11/21/18 | 688 | Quintanilla, Esteban R | 12 | 540 | 21910
PR | 110 | 09/06/19 | 47 | Hubbard, Robert W | 2 | 100 | 25045
PR | 110 | 09/20/19 | 480 | Boss, Kyle A | 8 | 144 | 25166
PR | 110 | 02/07/20 | 61 | Hubbard, Robert W | 2 | 108 | 26809
PR | 111 | 11/02/18 | 74 | Wilson, Garret A | 8 | 280 | 21683
PR | 111 | 11/21/18 | 685 | Wilson, Garret A | 24 | 840 | 21906
PR | 111 | 12/07/18 | 44 | Ascencio, Jose L | 6 | 252 | 21987
PR | 111 | 12/07/18 | 95 | Rivera, Jorge A | 2 | -66 | 22037
PR | 111 | 12/07/18 | 98 | Ross, Kelli M | 2 | -80 | 22040
PR | 111 | 12/07/18 | 123 | Ascencio, Jose L | 6 | -252 | 22059
PR | 111 | 12/07/18 | 125 | Rivera, Jorge A | 2 | 66 | 22061
PR | 111 | 12/07/18 | 126 | Ross, Kelli M | 2 | 80 | 22062
PR | 111 | 12/07/18 | 129 | Wilson, Garret A | 32 | -1120 | 22065
PR | 111 | 03/08/19 | 298 | Rodriguez Arevalos, Christian | 7 | 161 | 23037
PR | 111 | 03/08/19 | 313 | Wilson, Garret A | 7 | 259 | 23052
PR | 111 | 03/15/19 | 561 | Wilson, Garret A | 9 | 333 | 23123
PR | 111 | 03/22/19 | 709 | Barbosa, Michael S | 2 | 75 | 23130
PR | 111 | 03/22/19 | 709 | Barbosa, Michael S | 8 | 200 | 23130
PR | 111 | 03/22/19 | 739 | Hubbard, Robert W | 1 | 49 | 23160
PR | 111 | 03/22/19 | 758 | Rodriguez Arevalos, Christian | 34 | 782 | 23179
PR | 111 | 03/22/19 | 775 | Wilson, Garret A | 25.5 | 943.5 | 23196
PR | 111 | 03/22/19 | 780 | Hubbard, Robert W | 1 | 49 | 23197
PR | 111 | 03/22/19 | 781 | Hubbard, Robert W | 1 | -49 | 23160
PR | 111 | 03/29/19 | 920 | Barbosa, Michael S | 3 | 112.5 | 23204
PR | 111 | 03/29/19 | 920 | Barbosa, Michael S | 14 | 350 | 23204
PR | 111 | 03/29/19 | 938 | Foster, Antonio T | 1 | 19 | 23222
PR | 111 | 03/29/19 | 951 | Hubbard, Robert W | 1 | 49 | 23235
PR | 111 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M | 2 | 66 | 23236
PR | 111 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M | 16 | 352 | 23236
PR | 111 | 03/29/19 | 970 | Rodriguez Arevalos, Christian | 36 | 828 | 23254
PR | 111 | 03/29/19 | 987 | Wilson, Garret A | 19 | 703 | 23271
PR | 111 | 03/29/19 | 992 | Barbosa, Michael S | 3 | -112.5 | 23204
PR | 111 | 03/29/19 | 992 | Barbosa, Michael S | 14 | -350 | 23204
PR | 111 | 03/29/19 | 993 | Barbosa, Michael S | 3 | 112.5 | 23199
PR | 111 | 03/29/19 | 993 | Barbosa, Michael S | 14 | 350 | 23199
PR | 111 | 04/05/19 | 100 | Foster, Antonio T | 2 | 57 | 23294
PR | 111 | 04/05/19 | 100 | Foster, Antonio T | 8 | 152 | 23294
PR | 111 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M | 8 | 264 | 23309
PR | 111 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M | 40 | 880 | 23309
PR | 111 | 04/05/19 | 133 | Rodriguez Arevalos, Christian | 8 | 276 | 23327
PR | 111 | 04/05/19 | 133 | Rodriguez Arevalos, Christian | 40 | 920 | 23327
PR | 111 | 04/05/19 | 134 | Ross, Kelli M | 6 | 360 | 23328
PR | 111 | 04/05/19 | 134 | Ross, Kelli M | 24 | 960 | 23328
PR | 111 | 04/05/19 | 150 | Wilson, Garret A | 3 | 166.5 | 23344
PR | 111 | 04/05/19 | 150 | Wilson, Garret A | 11 | 407 | 23344
PR | 111 | 04/12/19 | 326 | Barbosa, Michael S | 2 | 75 | 23350
PR | 111 | 04/12/19 | 326 | Barbosa, Michael S | 16 | 400 | 23350
PR | 111 | 04/12/19 | 344 | Foster, Antonio T | 2 | 57 | 23368
PR | 111 | 04/12/19 | 344 | Foster, Antonio T | 8 | 152 | 23368
PR | 111 | 04/12/19 | 357 | Hubbard, Robert W | 2 | 100 | 23381
PR | 111 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M | 8 | 264 | 23382
PR | 111 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M | 40 | 880 | 23382
PR | 111 | 04/12/19 | 377 | Rodriguez Arevalos, Christian | 40 | 920 | 23401
PR | 111 | 04/12/19 | 378 | Ross, Kelli M | 8 | 504 | 23402
PR | 111 | 04/12/19 | 378 | Ross, Kelli M | 40 | 1680 | 23402
PR | 111 | 04/12/19 | 395 | Wilson, Garret A | 6 | 240 | 23419
PR | 111 | 04/19/19 | 523 | Barbosa, Michael S | 8 | 200 | 23424
PR | 111 | 04/19/19 | 541 | Foster, Antonio T | 6 | 171 | 23442
PR | 111 | 04/19/19 | 541 | Foster, Antonio T | 32 | 608 | 23442
PR | 111 | 04/19/19 | 555 | Hubbard, Robert W | 6 | 300 | 23456
PR | 111 | 04/19/19 | 555 | Hubbard, Robert W | 1 | 75 | 23456
PR | 111 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M | 8 | 264 | 23457
PR | 111 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M | 40 | 880 | 23457
PR | 111 | 04/19/19 | 575 | Rodriguez Arevalos, Christian | 40 | 920 | 23476
PR | 111 | 04/19/19 | 575 | Rodriguez Arevalos, Christian | 8 | 276 | 23476
PR | 111 | 04/19/19 | 577 | Ross, Kelli M | 8 | 504 | 23478
PR | 111 | 04/19/19 | 577 | Ross, Kelli M | 40 | 1680 | 23478
PR | 111 | 04/19/19 | 593 | Wilson, Garret A | 3 | 3 | 23494
PR | 111 | 04/19/19 | 594 | Wilson, Garret A | 3 | -3 | 23494
PR | 111 | 04/19/19 | 595 | Wilson, Garret A | 3 | 120 | 23495
PR | 111 | 04/26/19 | 760 | Foster, Antonio T | 2 | 60 | 23517
PR | 111 | 04/26/19 | 760 | Foster, Antonio T | 16 | 320 | 23517
PR | 111 | 04/26/19 | 774 | Hubbard, Robert W | 2 | 100 | 23531
PR | 111 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M | 8 | 300 | 23532
PR | 111 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 23532
PR | 111 | 04/26/19 | 794 | Rodriguez Arevalos, Christian | 6 | 234 | 23551
PR | 111 | 04/26/19 | 794 | Rodriguez Arevalos, Christian | 40 | 1040 | 23551
PR | 111 | 04/26/19 | 796 | Ross, Kelli M | 8 | 504 | 23553
PR | 111 | 04/26/19 | 796 | Ross, Kelli M | 40 | 1680 | 23553
PR | 111 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M | 32 | 800 | 23605
PR | 111 | 05/03/19 | 63 | Rodriguez Arevalos, Christian | 40 | 1040 | 23625
PR | 111 | 05/03/19 | 65 | Ross, Kelli M | 40 | 1680 | 23627
PR | 111 | 05/03/19 | 80 | Wilson, Garret A | 5 | 200 | 23642
PR | 111 | 05/10/19 | 216 | Rodriguez Arevalos, Christian | 29 | 754 | 23701
PR | 111 | 05/10/19 | 233 | Wilson, Garret A | 3 | 120 | 23718
PR | 111 | 06/07/19 | 235 | Rodriguez Arevalos, Christian | 16 | 416 | 24010
PR | 111 | 06/14/19 | 470 | Escalante Escobar, Boanerge | 8 | 176 | 24051
PR | 111 | 06/14/19 | 495 | Montenegro, Carlos E | 8 | 248 | 24076
PR | 111 | 06/14/19 | 504 | Rodriguez Arevalos, Christian | 24 | 624 | 24085
PR | 111 | 06/14/19 | 521 | Wilson, Garret A | 21 | 840 | 24102
PR | 111 | 06/21/19 | 675 | Rodriguez Arevalos, Christian | 32 | 832 | 24161
PR | 111 | 06/21/19 | 678 | Ross, Kelli M | 16 | 672 | 24164
PR | 111 | 06/21/19 | 692 | Wilson, Garret A | 5 | 200 | 24178
PR | 111 | 06/28/19 | 844 | Boss, Kyle A | 6 | 102 | 24188
PR | 111 | 06/28/19 | 892 | Rodriguez Arevalos, Christian | 24 | 624 | 24236
PR | 111 | 06/28/19 | 895 | Ross, Kelli M | 24 | 1008 | 24239
PR | 111 | 06/28/19 | 909 | Wilson, Garret A | 9 | 360 | 24253
PR | 111 | 07/05/19 | 15 | Boss, Aaron J | 5 | 80 | 24262
PR | 111 | 07/05/19 | 16 | Boss, Kyle A | 8 | 136 | 24263
PR | 111 | 07/05/19 | 24 | Cruz Guzman, Joel A | 1 | 28 | 24271
PR | 111 | 07/05/19 | 30 | Escalante Escobar, Boanerge | 1 | 22 | 24277
PR | 111 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M | 1 | 25 | 24292
PR | 111 | 07/05/19 | 49 | Lopez, Maslin A | 1 | 17 | 24296
PR | 111 | 07/05/19 | 63 | Roberts, Lake A | 1 | 20 | 24311
PR | 111 | 07/05/19 | 64 | Rodriguez Arevalos, Christian | 32 | 832 | 24312
PR | 111 | 07/05/19 | 65 | Romero Garza, Jesus I | 8 | 144 | 24313
PR | 111 | 07/05/19 | 66 | Ross, Kelli M | 32 | 1344 | 24314
PR | 111 | 07/05/19 | 68 | Silva Morales, Jair J | 1 | 27 | 24316
PR | 111 | 07/05/19 | 80 | Wilson, Garret A | 21 | 840 | 24328
PR | 111 | 07/12/19 | 285 | Boss, Aaron J | 6 | 96 | 24337
PR | 111 | 07/12/19 | 286 | Boss, Kyle A | 1 | 17 | 24338
PR | 111 | 07/12/19 | 333 | Rodriguez Arevalos, Christian | 29 | 754 | 24385
PR | 111 | 07/12/19 | 336 | Ross, Kelli M | 25 | 1050 | 24388
PR | 111 | 07/12/19 | 351 | Wilson, Garret A | 7 | 280 | 24403
PR | 111 | 07/19/19 | 563 | Rodriguez Arevalos, Christian | 7 | 182 | 24462
PR | 111 | 07/19/19 | 564 | Romero Garza, Jesus I | 8 | 144 | 24463
PR | 111 | 07/19/19 | 566 | Ross, Kelli M | 3 | 126 | 24465
PR | 111 | 07/19/19 | 581 | Wilson, Garret A | 8 | 320 | 24480
PR | 111 | 07/26/19 | 666 | Rodriguez Arevalos, Christian | 8 | 208 | 24615
PR | 111 | 07/26/19 | 667 | Romero Garza, Jesus I | 8 | 144 | 24616
PR | 111 | 07/26/19 | 669 | Ross, Kelli M | 10 | 420 | 24618
PR | 111 | 07/26/19 | 684 | Wilson, Garret A | 1 | 40 | 24633
PR | 111 | 08/02/19 | 59 | Romero Garza, Jesus I | 8 | 144 | 24690
PR | 111 | 08/02/19 | 60 | Ross, Kelli M | 16 | 672 | 24691
PR | 111 | 08/09/19 | 312 | Romero Garza, Jesus I | 8 | 144 | 24765
PR | 111 | 08/16/19 | 563 | Anderson, Richard P | 3 | 141 | 24782
PR | 111 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian | 16 | 416 | 24988
PR | 111 | 08/30/19 | 1048 | Ross, Kelli M | 8 | 336 | 24990
PR | 111 | 09/06/19 | 52 | Lopez, Maslin A | 5 | 85 | 25050
PR | 111 | 09/06/19 | 67 | Rodriguez Arevalos, Christian | 19 | 494 | 25065
PR | 111 | 09/06/19 | 69 | Ross, Kelli M | 8 | 336 | 25067
PR | 111 | 09/20/19 | 509 | Hubbard, Robert W | 6 | 300 | 25195
PR | 111 | 09/20/19 | 545 | Wilson, Garret A | 11 | 440 | 25231
PR | 111 | 09/27/19 | 649 | Escalante Escobar, Boanerge | 24 | 528 | 25254
PR | 111 | 09/27/19 | 678 | Montenegro, Carlos E | 24 | 744 | 25283
PR | 111 | 10/11/19 | 267 | Boss, Kyle A | 8 | 144 | 25401
PR | 111 | 10/11/19 | 296 | Hubbard, Robert W | 3 | 150 | 25430
PR | 111 | 10/11/19 | 316 | Roberts, Lake A | 24 | 528 | 25450
PR | 111 | 10/18/19 | 461 | Boss, Kyle A | 14 | 252 | 25477
PR | 111 | 10/18/19 | 489 | Hubbard, Robert W | 5 | 250 | 25506
PR | 111 | 10/18/19 | 500 | McCabe, Thomas C | 5 | 175 | 25517
PR | 111 | 10/18/19 | 509 | Roberts, Lake A | 20 | 440 | 25526
PR | 111 | 10/25/19 | 597 | Boss, Kyle A | 5 | 90 | 25554
PR | 111 | 10/25/19 | 645 | Roberts, Lake A | 5 | 110 | 25602
PR | 111 | 11/01/19 | 11 | Boss, Benjamin T | 40 | 640 | 25628
PR | 111 | 11/01/19 | 12 | Boss, Kyle A | 8 | 168 | 25629
PR | 111 | 11/01/19 | 24 | Escalante Escobar, Boanerge | 16 | 400 | 25641
PR | 111 | 11/01/19 | 40 | Hubbard, Robert W | 3 | 162 | 25657
PR | 111 | 11/01/19 | 61 | Roberts, Lake A | 24 | 600 | 25678
PR | 111 | 11/08/19 | 185 | Boss, Benjamin T | 16 | 256 | 25704
PR | 111 | 11/08/19 | 186 | Boss, Kyle A | 8 | 168 | 25705
PR | 111 | 11/08/19 | 193 | Cruz Reyes, Jose | 24 | 768 | 25712
PR | 111 | 11/08/19 | 198 | Escalante Escobar, Boanerge | 8 | 200 | 25717
PR | 111 | 11/08/19 | 214 | Hubbard, Robert W | 12 | 648 | 25733
PR | 111 | 11/08/19 | 235 | Roberts, Lake A | 16 | 400 | 25754
PR | 111 | 11/08/19 | 237 | Romero Garza, Jesus I | 24 | 552 | 25756
PR | 111 | 11/08/19 | 239 | Ross, Kelli M | 24 | 1032 | 25758
PR | 111 | 11/15/19 | 446 | Boss, Kyle A | 8 | 168 | 25781
PR | 111 | 11/15/19 | 453 | Cruz Reyes, Jose | 16 | 512 | 25788
PR | 111 | 11/15/19 | 473 | Hubbard, Robert W | 14 | 756 | 25809
PR | 111 | 11/22/19 | 616 | Boss, Benjamin T | 16 | 256 | 25856
PR | 111 | 11/22/19 | 617 | Boss, Kyle A | 22 | 462 | 25857
PR | 111 | 11/22/19 | 623 | Cruz Gonzalez, Julio C | 24 | 672 | 25863
PR | 111 | 11/22/19 | 644 | Hubbard, Robert W | 11 | 594 | 25884
PR | 111 | 11/22/19 | 650 | Lopez, Maslin A | 6 | 114 | 25890
PR | 111 | 11/22/19 | 655 | McCabe, Thomas C | 8 | 312 | 25895
PR | 111 | 11/22/19 | 665 | Roberts, Lake A | 14 | 350 | 25905
PR | 111 | 11/22/19 | 666 | Rodriguez Arevalos, Christian | 6 | 180 | 25906
PR | 111 | 11/22/19 | 667 | Romero Garza, Jesus I | 6 | 138 | 25907
PR | 111 | 11/27/19 | 850 | Boss, Benjamin T | 16 | 256 | 25931
PR | 111 | 11/27/19 | 851 | Boss, Kyle A | 8 | 168 | 25932
PR | 111 | 11/27/19 | 878 | Hubbard, Robert W | 20 | 1080 | 25959
PR | 111 | 11/27/19 | 889 | McCabe, Thomas C | 39 | 1521 | 25970
PR | 111 | 11/27/19 | 899 | Roberts, Lake A | 8 | 200 | 25980
PR | 111 | 11/27/19 | 900 | Rodriguez Arevalos, Christian | 8 | 240 | 25981
PR | 111 | 11/27/19 | 901 | Romero Garza, Jesus I | 16 | 368 | 25982
PR | 111 | 12/06/19 | 36 | Boss, Benjamin T | 8 | 128 | 26008
PR | 111 | 12/06/19 | 65 | Hubbard, Robert W | 11 | 594 | 26037
PR | 111 | 12/06/19 | 76 | McCabe, Thomas C | 8 | 312 | 26048
PR | 111 | 12/06/19 | 86 | Roberts, Lake A | 13 | 325 | 26058
PR | 111 | 12/06/19 | 87 | Rodriguez Arevalos, Christian | 5 | 150 | 26059
PR | 111 | 12/06/19 | 88 | Romero Garza, Jesus I | 8 | 184 | 26060
PR | 111 | 12/13/19 | 426 | Hubbard, Robert W | 8 | 432 | 26191
PR | 111 | 12/20/19 | 579 | Hubbard, Robert W | 4 | 216 | 26268
PR | 111 | 01/03/20 | 40 | Hubbard, Robert W | 4 | 216 | 26423
PR | 111 | 01/10/20 | 334 | Roberts, Lake A | 4 | 100 | 26522
PR | 111 | 01/24/20 | 682 | Boss, Benjamin T | 4 | 64 | 26625
PR | 111 | 01/24/20 | 683 | Boss, Kyle A | 7 | 147 | 26626
PR | 111 | 02/28/20 | 716 | Hubbard, Robert W | 2 | 108 | 27044
PR | 111 | 02/28/20 | 725 | McCabe, Thomas C | 4 | 156 | 27053
PR | 111 | 02/28/20 | 737 | Roberts, Lake A | 16 | 400 | 27065
PR | 111 | 03/06/20 | 78 | Hubbard, Robert W | 11 | 594 | 27122
PR | 111 | 03/06/20 | 87 | McCabe, Thomas C | 5 | 195 | 27131
PR | 111 | 03/06/20 | 99 | Roberts, Lake A | 5 | 125 | 27143
PR | 111 | 05/15/20 | 343 | Hubbard, Robert W | 4 | 216 | 27821
PR | 112 | 11/21/18 | 655 | Lovo, German G | 22 | 528 | 21876
PR | 112 | 11/21/18 | 664 | Quintanilla, Esteban R | 16 | 720 | 21885
PR | 112 | 11/21/18 | 687 | Quintanilla, Esteban R | 16 | -720 | 21885
PR | 112 | 11/21/18 | 688 | Quintanilla, Esteban R | 16 | 720 | 21910
PR | 112 | 11/30/18 | 868 | Lovo, German G | 18 | 450 | 21950
PR | 112 | 11/30/18 | 877 | Quintanilla, Esteban R | 13 | 611 | 21959
PR | 112 | 12/07/18 | 80 | Lovo, German G | 16 | 400 | 22022
PR | 112 | 12/07/18 | 89 | Quintanilla, Esteban R | 19 | 893 | 22031
PR | 112 | 12/14/18 | 304 | Lovo, German G | 23 | 575 | 22163
PR | 112 | 12/14/18 | 314 | Quintanilla, Esteban R | 5 | 235 | 22173
PR | 112 | 12/21/18 | 554 | Quintanilla, Esteban R | 2 | 94 | 22244
PR | 112 | 12/28/18 | 684 | Lovo, German G | 5 | 125 | 22268
PR | 112 | 01/18/19 | 513 | Quintanilla, Esteban R | 2 | 141 | 22534
PR | 112 | 01/25/19 | 748 | Hubbard, Robert W | 12 | 588 | 22593
PR | 112 | 01/25/19 | 756 | McCabe, Thomas C | 16 | 528 | 22601
PR | 112 | 01/25/19 | 760 | Paco Leyva, Orlando | 9 | 333 | 22605
PR | 112 | 01/25/19 | 773 | Sepulveda Gonzalez, Alfredo | 16 | 512 | 22618
PR | 112 | 02/01/19 | 36 | Hubbard, Robert W | 17.5 | 857.5 | 22665
PR | 112 | 02/01/19 | 44 | McCabe, Thomas C | 6 | 198 | 22673
PR | 112 | 02/01/19 | 47 | Paco Leyva, Orlando | 4 | 148 | 22676
PR | 112 | 02/01/19 | 49 | Ramos Herrera, Franklin J | 4 | 92 | 22678
PR | 112 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo | 8 | 256 | 22687
PR | 112 | 02/08/19 | 191 | Hubbard, Robert W | 10 | 490 | 22733
PR | 112 | 02/08/19 | 199 | McCabe, Thomas C | 16 | 528 | 22741
PR | 112 | 02/08/19 | 202 | Paco Leyva, Orlando | 4 | 148 | 22744
PR | 112 | 02/08/19 | 204 | Ramos Herrera, Franklin J | 4 | 92 | 22746
PR | 112 | 02/08/19 | 214 | Sepulveda Gonzalez, Alfredo | 16 | 512 | 22756
PR | 112 | 02/15/19 | 353 | Hubbard, Robert W | 6 | 294 | 22804
PR | 112 | 02/15/19 | 361 | McCabe, Thomas C | 23.5 | 775.5 | 22812
PR | 112 | 02/15/19 | 376 | Sepulveda Gonzalez, Alfredo | 9 | 288 | 22827
PR | 112 | 02/22/19 | 611 | Hubbard, Robert W | 11.5 | 563.5 | 22873
PR | 112 | 02/22/19 | 619 | McCabe, Thomas C | 12 | 396 | 22881
PR | 112 | 02/22/19 | 625 | Ramos Herrera, Franklin J | 8 | 184 | 22887
PR | 112 | 02/22/19 | 635 | Sepulveda Gonzalez, Alfredo | 12 | 384 | 22897
PR | 112 | 03/01/19 | 38 | Hubbard, Robert W | 2.5 | 122.5 | 22945
PR | 112 | 03/01/19 | 59 | Rodriguez Arevalos, Christian | 8 | 184 | 22966
PR | 112 | 03/01/19 | 73 | Wilson, Garret A | 14 | 518 | 22980
PR | 112 | 03/08/19 | 298 | Rodriguez Arevalos, Christian | 16 | 368 | 23037
PR | 112 | 03/08/19 | 313 | Wilson, Garret A | 13 | 481 | 23052
PR | 112 | 03/29/19 | 987 | Wilson, Garret A | 2 | 111 | 23271
PR | 120 | 01/25/19 | 762 | Quintanilla, Esteban R | 4 | 188 | 22607
PR | 120 | 03/01/19 | 59 | Rodriguez Arevalos, Christian | 4 | 92 | 22966
PR | 120 | 03/01/19 | 73 | Wilson, Garret A | 1 | 37 | 22980
PR | 120 | 03/08/19 | 278 | Hubbard, Robert W | 2 | 98 | 23017
PR | 120 | 03/08/19 | 298 | Rodriguez Arevalos, Christian | 7 | 161 | 23037
PR | 120 | 03/08/19 | 313 | Wilson, Garret A | 5 | 185 | 23052
PR | 120 | 03/15/19 | 545 | Rodriguez Arevalos, Christian | 21 | 483 | 23107
PR | 120 | 03/15/19 | 561 | Wilson, Garret A | 10 | 370 | 23123
PR | 120 | 03/22/19 | 739 | Hubbard, Robert W | 3 | 147 | 23160
PR | 120 | 03/22/19 | 775 | Wilson, Garret A | 6 | 222 | 23196
PR | 120 | 03/22/19 | 780 | Hubbard, Robert W | 3 | 147 | 23197
PR | 120 | 03/22/19 | 781 | Hubbard, Robert W | 3 | -147 | 23160
PR | 120 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M | 2 | 66 | 23236
PR | 120 | 03/29/19 | 970 | Rodriguez Arevalos, Christian | 2 | 46 | 23254
PR | 120 | 03/29/19 | 987 | Wilson, Garret A | 5 | 277.5 | 23271
PR | 120 | 03/29/19 | 987 | Wilson, Garret A | 17 | 629 | 23271
PR | 120 | 04/05/19 | 150 | Wilson, Garret A | 3.5 | 194.25 | 23344
PR | 120 | 04/05/19 | 150 | Wilson, Garret A | 27 | 999 | 23344
PR | 120 | 04/12/19 | 326 | Barbosa, Michael S | 4 | 150 | 23350
PR | 120 | 04/12/19 | 326 | Barbosa, Michael S | 16 | 400 | 23350
PR | 120 | 04/12/19 | 344 | Foster, Antonio T | 6 | 171 | 23368
PR | 120 | 04/12/19 | 344 | Foster, Antonio T | 24 | 456 | 23368
PR | 120 | 04/12/19 | 357 | Hubbard, Robert W | 7 | 350 | 23381
PR | 120 | 04/12/19 | 362 | Lopez, Maslin A | 30 | 480 | 23386
PR | 120 | 04/12/19 | 395 | Wilson, Garret A | 2 | 80 | 23419
PR | 120 | 04/19/19 | 541 | Foster, Antonio T | 2 | 57 | 23442
PR | 120 | 04/19/19 | 541 | Foster, Antonio T | 8 | 152 | 23442
PR | 120 | 04/19/19 | 560 | Lopez, Maslin A | 8 | 192 | 23461
PR | 120 | 04/19/19 | 560 | Lopez, Maslin A | 40 | 640 | 23461
PR | 120 | 04/19/19 | 593 | Wilson, Garret A | 23 | 23 | 23494
PR | 120 | 04/19/19 | 594 | Wilson, Garret A | 23 | -23 | 23494
PR | 120 | 04/19/19 | 595 | Wilson, Garret A | 23 | 920 | 23495
PR | 120 | 04/26/19 | 760 | Foster, Antonio T | 6 | 180 | 23517
PR | 120 | 04/26/19 | 760 | Foster, Antonio T | 24 | 480 | 23517
PR | 120 | 04/26/19 | 774 | Hubbard, Robert W | 5 | 250 | 23531
PR | 120 | 04/26/19 | 779 | Lopez, Maslin A | 8 | 204 | 23536
PR | 120 | 04/26/19 | 779 | Lopez, Maslin A | 40 | 680 | 23536
PR | 120 | 04/26/19 | 785 | Montenegro, Carlos E | 6 | 279 | 23542
PR | 120 | 04/26/19 | 785 | Montenegro, Carlos E | 19 | 589 | 23542
PR | 120 | 04/26/19 | 786 | Paco Leyva, Orlando | 2 | 80 | 23543
PR | 120 | 04/26/19 | 810 | Wilson, Garret A | 47 | 1880 | 23567
PR | 120 | 05/03/19 | 28 | Foster, Antonio T | 40 | 800 | 23590
PR | 120 | 05/03/19 | 42 | Hubbard, Robert W | 4.5 | 225 | 23604
PR | 120 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M | 8 | 200 | 23605
PR | 120 | 05/03/19 | 48 | Lopez, Maslin A | 40 | 680 | 23610
PR | 120 | 05/03/19 | 80 | Wilson, Garret A | 30 | 1200 | 23642
PR | 120 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A | 1 | 48 | 23643
PR | 120 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A | 16 | 512 | 23643
PR | 120 | 05/10/19 | 181 | Foster, Antonio T | 40 | 800 | 23665
PR | 120 | 05/10/19 | 195 | Hubbard, Robert W | 1 | 75 | 23679
PR | 120 | 05/10/19 | 196 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 23680
PR | 120 | 05/10/19 | 201 | Lopez, Maslin A | 40 | 680 | 23685
PR | 120 | 05/10/19 | 208 | Paco Leyva, Orlando | 1 | 60 | 23692
PR | 120 | 05/10/19 | 210 | Ramos Herrera, Franklin J | 1 | 39 | 23694
PR | 120 | 05/10/19 | 216 | Rodriguez Arevalos, Christian | 11 | 286 | 23701
PR | 120 | 05/10/19 | 217 | Romero Garza, Jesus I | 16 | 288 | 23702
PR | 120 | 05/10/19 | 218 | Ross, Kelli M | 32 | 1344 | 23703
PR | 120 | 05/10/19 | 233 | Wilson, Garret A | 34 | 1360 | 23718
PR | 120 | 05/17/19 | 390 | Amaya Gonzalez, Edilberto A | 35 | 1120 | 23721
PR | 120 | 05/17/19 | 398 | Boss, Kyle A | 24 | 408 | 23729
PR | 120 | 05/17/19 | 413 | Foster, Antonio T | 40 | 800 | 23744
PR | 120 | 05/17/19 | 427 | Hubbard, Robert W | 4 | 200 | 23758
PR | 120 | 05/17/19 | 428 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 23759
PR | 120 | 05/17/19 | 433 | Lopez, Maslin A | 40 | 680 | 23764
PR | 120 | 05/17/19 | 442 | Ramos Herrera, Franklin J | 16 | 416 | 23773
PR | 120 | 05/17/19 | 448 | Rodriguez Arevalos, Christian | 40 | 1040 | 23779
PR | 120 | 05/17/19 | 449 | Romero Garza, Jesus I | 40 | 720 | 23780
PR | 120 | 05/17/19 | 450 | Ross, Kelli M | 40 | 1680 | 23781
PR | 120 | 05/17/19 | 465 | Wilson, Garret A | 35 | 1400 | 23796
PR | 120 | 05/24/19 | 603 | Amaya Gonzalez, Edilberto A | 24 | 768 | 23798
PR | 120 | 05/24/19 | 610 | Boss, Kyle A | 40 | 680 | 23805
PR | 120 | 05/24/19 | 625 | Foster, Antonio T | 39 | 780 | 23820
PR | 120 | 05/24/19 | 640 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 23835
PR | 120 | 05/24/19 | 645 | Lopez, Maslin A | 40 | 680 | 23840
PR | 120 | 05/24/19 | 654 | Ramos Herrera, Franklin J | 40 | 1040 | 23849
PR | 120 | 05/24/19 | 659 | Roberts, Lake A | 8 | 160 | 23854
PR | 120 | 05/24/19 | 660 | Rodriguez Arevalos, Christian | 40 | 1040 | 23855
PR | 120 | 05/24/19 | 661 | Romero Garza, Jesus I | 40 | 720 | 23856
PR | 120 | 05/24/19 | 662 | Ross, Kelli M | 35 | 1470 | 23857
PR | 120 | 05/24/19 | 677 | Wilson, Garret A | 40 | 1600 | 23872
PR | 120 | 05/31/19 | 876 | Amaya Gonzalez, Edilberto A | 16 | 512 | 23876
PR | 120 | 05/31/19 | 881 | Barnhart, Joseph N | 4 | 200 | 23881
PR | 120 | 05/31/19 | 884 | Boss, Kyle A | 32 | 544 | 23884
PR | 120 | 05/31/19 | 899 | Foster, Antonio T | 32 | 640 | 23899
PR | 120 | 05/31/19 | 914 | Jimenez Alvarenga, Gerson M | 32 | 800 | 23914
PR | 120 | 05/31/19 | 919 | Lopez, Maslin A | 32 | 544 | 23919
PR | 120 | 05/31/19 | 926 | Paco Leyva, Orlando | 4 | 160 | 23926
PR | 120 | 05/31/19 | 928 | Ramos Herrera, Franklin J | 32 | 832 | 23928
PR | 120 | 05/31/19 | 933 | Roberts, Lake A | 32 | 640 | 23933
PR | 120 | 05/31/19 | 934 | Rodriguez Arevalos, Christian | 32 | 832 | 23934
PR | 120 | 05/31/19 | 935 | Romero Garza, Jesus I | 32 | 576 | 23935
PR | 120 | 05/31/19 | 936 | Ross, Kelli M | 24 | 1008 | 23936
PR | 120 | 05/31/19 | 951 | Wilson, Garret A | 32 | 1280 | 23951
PR | 120 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A | 24 | 768 | 23953
PR | 120 | 06/07/19 | 186 | Boss, Kyle A | 40 | 680 | 23961
PR | 120 | 06/07/19 | 201 | Foster, Antonio T | 11 | 220 | 23976
PR | 120 | 06/07/19 | 215 | Hubbard, Robert W | 3 | 150 | 23990
PR | 120 | 06/07/19 | 216 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 23991
PR | 120 | 06/07/19 | 220 | Lopez, Maslin A | 40 | 680 | 23995
PR | 120 | 06/07/19 | 229 | Ramos Herrera, Franklin J | 19 | 494 | 24004
PR | 120 | 06/07/19 | 234 | Roberts, Lake A | 32 | 640 | 24009
PR | 120 | 06/07/19 | 235 | Rodriguez Arevalos, Christian | 24 | 624 | 24010
PR | 120 | 06/07/19 | 236 | Romero Garza, Jesus I | 40 | 720 | 24011
PR | 120 | 06/07/19 | 237 | Rosas Olivares, Jorge C | 24 | 480 | 24012
PR | 120 | 06/07/19 | 238 | Ross, Kelli M | 24 | 1008 | 24013
PR | 120 | 06/07/19 | 253 | Wilson, Garret A | 40 | 1600 | 24028
PR | 120 | 06/14/19 | 449 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24030
PR | 120 | 06/14/19 | 457 | Boss, Kyle A | 40 | 680 | 24038
PR | 120 | 06/14/19 | 483 | Hubbard, Robert W | 3 | 150 | 24064
PR | 120 | 06/14/19 | 484 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24065
PR | 120 | 06/14/19 | 489 | Lopez, Maslin A | 40 | 680 | 24070
PR | 120 | 06/14/19 | 498 | Ramos Herrera, Franklin J | 16 | 416 | 24079
PR | 120 | 06/14/19 | 503 | Roberts, Lake A | 40 | 800 | 24084
PR | 120 | 06/14/19 | 504 | Rodriguez Arevalos, Christian | 16 | 416 | 24085
PR | 120 | 06/14/19 | 505 | Romero Garza, Jesus I | 40 | 720 | 24086
PR | 120 | 06/14/19 | 506 | Rosas Olivares, Jorge C | 32 | 640 | 24087
PR | 120 | 06/14/19 | 507 | Ross, Kelli M | 40 | 1680 | 24088
PR | 120 | 06/14/19 | 521 | Wilson, Garret A | 19 | 760 | 24102
PR | 120 | 06/21/19 | 617 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24103
PR | 120 | 06/21/19 | 625 | Boss, Aaron J | 24 | 384 | 24111
PR | 120 | 06/21/19 | 626 | Boss, Kyle A | 40 | 680 | 24112
PR | 120 | 06/21/19 | 634 | Cruz Guzman, Joel A | 8 | 224 | 24120
PR | 120 | 06/21/19 | 654 | Hubbard, Robert W | 1 | 50 | 24140
PR | 120 | 06/21/19 | 655 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24141
PR | 120 | 06/21/19 | 660 | Lopez, Maslin A | 40 | 680 | 24146
PR | 120 | 06/21/19 | 669 | Ramos Herrera, Franklin J | 16 | 416 | 24155
PR | 120 | 06/21/19 | 674 | Roberts, Lake A | 40 | 800 | 24160
PR | 120 | 06/21/19 | 675 | Rodriguez Arevalos, Christian | 8 | 208 | 24161
PR | 120 | 06/21/19 | 676 | Romero Garza, Jesus I | 32 | 576 | 24162
PR | 120 | 06/21/19 | 677 | Rosas Olivares, Jorge C | 16 | 320 | 24163
PR | 120 | 06/21/19 | 678 | Ross, Kelli M | 24 | 1008 | 24164
PR | 120 | 06/21/19 | 680 | Silva Morales, Jair J | 8 | 216 | 24166
PR | 120 | 06/21/19 | 692 | Wilson, Garret A | 35 | 1400 | 24178
PR | 120 | 06/28/19 | 835 | Amaya Gonzalez, Edilberto A | 37 | 1184 | 24179
PR | 120 | 06/28/19 | 843 | Boss, Aaron J | 40 | 640 | 24187
PR | 120 | 06/28/19 | 844 | Boss, Kyle A | 34 | 578 | 24188
PR | 120 | 06/28/19 | 852 | Cruz Guzman, Joel A | 40 | 1120 | 24196
PR | 120 | 06/28/19 | 873 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24217
PR | 120 | 06/28/19 | 877 | Lopez, Maslin A | 40 | 680 | 24221
PR | 120 | 06/28/19 | 891 | Roberts, Lake A | 32 | 640 | 24235
PR | 120 | 06/28/19 | 892 | Rodriguez Arevalos, Christian | 8 | 208 | 24236
PR | 120 | 06/28/19 | 893 | Romero Garza, Jesus I | 32 | 576 | 24237
PR | 120 | 06/28/19 | 894 | Rosas Olivares, Jorge C | 24 | 480 | 24238
PR | 120 | 06/28/19 | 895 | Ross, Kelli M | 16 | 672 | 24239
PR | 120 | 06/28/19 | 897 | Silva Morales, Jair J | 40 | 1080 | 24241
PR | 120 | 06/28/19 | 909 | Wilson, Garret A | 31 | 1240 | 24253
PR | 120 | 07/05/19 | 7 | Amaya Gonzalez, Edilberto A | 32 | 1024 | 24254
PR | 120 | 07/05/19 | 15 | Boss, Aaron J | 35 | 560 | 24262
PR | 120 | 07/05/19 | 16 | Boss, Kyle A | 32 | 544 | 24263
PR | 120 | 07/05/19 | 24 | Cruz Guzman, Joel A | 39 | 1092 | 24271
PR | 120 | 07/05/19 | 30 | Escalante Escobar, Boanerge | 8 | 176 | 24277
PR | 120 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M | 39 | 975 | 24292
PR | 120 | 07/05/19 | 49 | Lopez, Maslin A | 39 | 663 | 24296
PR | 120 | 07/05/19 | 63 | Roberts, Lake A | 15 | 300 | 24311
PR | 120 | 07/05/19 | 64 | Rodriguez Arevalos, Christian | 8 | 208 | 24312
PR | 120 | 07/05/19 | 65 | Romero Garza, Jesus I | 32 | 576 | 24313
PR | 120 | 07/05/19 | 66 | Ross, Kelli M | 8 | 336 | 24314
PR | 120 | 07/05/19 | 68 | Silva Morales, Jair J | 39 | 1053 | 24316
PR | 120 | 07/05/19 | 80 | Wilson, Garret A | 19 | 760 | 24328
PR | 120 | 07/12/19 | 277 | Amaya Gonzalez, Edilberto A | 32 | 1024 | 24329
PR | 120 | 07/12/19 | 285 | Boss, Aaron J | 26 | 416 | 24337
PR | 120 | 07/12/19 | 286 | Boss, Kyle A | 31 | 527 | 24338
PR | 120 | 07/12/19 | 287 | Castro Hernandez, Jose A | 16 | 560 | 24339
PR | 120 | 07/12/19 | 293 | Cruz Guzman, Joel A | 32 | 896 | 24345
PR | 120 | 07/12/19 | 303 | Gauthier, Dillon R | 16 | 272 | 24355
PR | 120 | 07/12/19 | 314 | Jimenez Alvarenga, Gerson M | 32 | 800 | 24366
PR | 120 | 07/12/19 | 318 | Lopez, Maslin A | 32 | 544 | 24370
PR | 120 | 07/12/19 | 332 | Roberts, Lake A | 14.5 | 290 | 24384
PR | 120 | 07/12/19 | 334 | Romero Garza, Jesus I | 32 | 576 | 24386
PR | 120 | 07/12/19 | 335 | Rosas Olivares, Jorge C | 23.5 | 470 | 24387
PR | 120 | 07/12/19 | 336 | Ross, Kelli M | 7 | 294 | 24388
PR | 120 | 07/12/19 | 339 | Silva Morales, Jair J | 24 | 648 | 24391
PR | 120 | 07/12/19 | 351 | Wilson, Garret A | 24.5 | 980 | 24403
PR | 120 | 07/19/19 | 507 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24406
PR | 120 | 07/19/19 | 515 | Boss, Aaron J | 40 | 640 | 24414
PR | 120 | 07/19/19 | 543 | Hubbard, Robert W | 3 | 150 | 24442
PR | 120 | 07/19/19 | 544 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24443
PR | 120 | 07/19/19 | 548 | Lopez, Maslin A | 40 | 680 | 24447
PR | 120 | 07/19/19 | 562 | Roberts, Lake A | 40 | 800 | 24461
PR | 120 | 07/19/19 | 563 | Rodriguez Arevalos, Christian | 33 | 858 | 24462
PR | 120 | 07/19/19 | 564 | Romero Garza, Jesus I | 32 | 576 | 24463
PR | 120 | 07/19/19 | 565 | Rosas Olivares, Jorge C | 24 | 480 | 24464
PR | 120 | 07/19/19 | 566 | Ross, Kelli M | 37 | 1554 | 24465
PR | 120 | 07/19/19 | 569 | Silva Morales, Jair J | 38 | 1026 | 24468
PR | 120 | 07/19/19 | 581 | Wilson, Garret A | 19 | 760 | 24480
PR | 120 | 07/26/19 | 611 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24560
PR | 120 | 07/26/19 | 619 | Boss, Aaron J | 40 | 640 | 24568
PR | 120 | 07/26/19 | 627 | Cruz Guzman, Joel A | 40 | 1120 | 24576
PR | 120 | 07/26/19 | 646 | Hubbard, Robert W | 2 | 100 | 24595
PR | 120 | 07/26/19 | 647 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24596
PR | 120 | 07/26/19 | 651 | Lopez, Maslin A | 40 | 680 | 24600
PR | 120 | 07/26/19 | 665 | Roberts, Lake A | 40 | 800 | 24614
PR | 120 | 07/26/19 | 666 | Rodriguez Arevalos, Christian | 32 | 832 | 24615
PR | 120 | 07/26/19 | 667 | Romero Garza, Jesus I | 32 | 576 | 24616
PR | 120 | 07/26/19 | 668 | Rosas Olivares, Jorge C | 8 | 160 | 24617
PR | 120 | 07/26/19 | 669 | Ross, Kelli M | 30 | 1260 | 24618
PR | 120 | 07/26/19 | 672 | Silva Morales, Jair J | 39 | 1053 | 24621
PR | 120 | 07/26/19 | 684 | Wilson, Garret A | 38 | 1520 | 24633
PR | 120 | 08/02/19 | 3 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24634
PR | 120 | 08/02/19 | 11 | Boss, Aaron J | 40 | 640 | 24642
PR | 120 | 08/02/19 | 12 | Boss, Kyle A | 24 | 432 | 24643
PR | 120 | 08/02/19 | 19 | Cruz Guzman, Joel A | 40 | 1120 | 24650
PR | 120 | 08/02/19 | 39 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24670
PR | 120 | 08/02/19 | 43 | Lopez, Maslin A | 40 | 680 | 24674
PR | 120 | 08/02/19 | 57 | Roberts, Lake A | 32 | 640 | 24688
PR | 120 | 08/02/19 | 58 | Rodriguez Arevalos, Christian | 39.5 | 1027 | 24689
PR | 120 | 08/02/19 | 59 | Romero Garza, Jesus I | 32 | 576 | 24690
PR | 120 | 08/02/19 | 60 | Ross, Kelli M | 24 | 1008 | 24691
PR | 120 | 08/02/19 | 63 | Silva Morales, Jair J | 39.5 | 1066.5 | 24694
PR | 120 | 08/02/19 | 75 | Wilson, Garret A | 40 | 1600 | 24706
PR | 120 | 08/09/19 | 255 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24708
PR | 120 | 08/09/19 | 263 | Boss, Aaron J | 40 | 640 | 24716
PR | 120 | 08/09/19 | 264 | Boss, Kyle A | 27 | 486 | 24717
PR | 120 | 08/09/19 | 271 | Cruz Guzman, Joel A | 40 | 1120 | 24724
PR | 120 | 08/09/19 | 277 | Escalante Escobar, Boanerge | 40 | 880 | 24730
PR | 120 | 08/09/19 | 291 | Hubbard, Robert W | 6 | 300 | 24744
PR | 120 | 08/09/19 | 292 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24745
PR | 120 | 08/09/19 | 296 | Lopez, Maslin A | 40 | 680 | 24749
PR | 120 | 08/09/19 | 302 | Montenegro, Carlos E | 24 | 744 | 24755
PR | 120 | 08/09/19 | 310 | Roberts, Lake A | 40 | 800 | 24763
PR | 120 | 08/09/19 | 311 | Rodriguez Arevalos, Christian | 40 | 1040 | 24764
PR | 120 | 08/09/19 | 312 | Romero Garza, Jesus I | 32 | 576 | 24765
PR | 120 | 08/09/19 | 313 | Ross, Kelli M | 40 | 1680 | 24766
PR | 120 | 08/09/19 | 316 | Silva Morales, Jair J | 40 | 1080 | 24769
PR | 120 | 08/09/19 | 327 | Wilson, Garret A | 24 | 960 | 24780
PR | 120 | 08/16/19 | 562 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 24781
PR | 120 | 08/16/19 | 570 | Boss, Aaron J | 40 | 640 | 24789
PR | 120 | 08/16/19 | 571 | Boss, Kyle A | 19 | 342 | 24790
PR | 120 | 08/16/19 | 578 | Cruz Guzman, Joel A | 40 | 1120 | 24797
PR | 120 | 08/16/19 | 584 | Escalante Escobar, Boanerge | 40 | 880 | 24803
PR | 120 | 08/16/19 | 598 | Hubbard, Robert W | 4 | 200 | 24817
PR | 120 | 08/16/19 | 599 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 24818
PR | 120 | 08/16/19 | 603 | Lopez, Maslin A | 40 | 680 | 24822
PR | 120 | 08/16/19 | 609 | Montenegro, Carlos E | 32 | 992 | 24828
PR | 120 | 08/16/19 | 617 | Roberts, Lake A | 24 | 480 | 24836
PR | 120 | 08/16/19 | 618 | Rodriguez Arevalos, Christian | 40 | 1040 | 24837
PR | 120 | 08/16/19 | 619 | Romero Garza, Jesus I | 40 | 720 | 24838
PR | 120 | 08/16/19 | 620 | Ross, Kelli M | 40 | 1680 | 24839
PR | 120 | 08/16/19 | 623 | Silva Morales, Jair J | 38.5 | 1039.5 | 24842
PR | 120 | 08/16/19 | 635 | Wilson, Garret A | 32 | 1280 | 24854
PR | 120 | 08/23/19 | 798 | Amaya Gonzalez, Edilberto A | 32 | 1024 | 24856
PR | 120 | 08/23/19 | 806 | Boss, Aaron J | 32 | 512 | 24864
PR | 120 | 08/23/19 | 814 | Cruz Guzman, Joel A | 16 | 448 | 24872
PR | 120 | 08/23/19 | 820 | Escalante Escobar, Boanerge | 40 | 880 | 24878
PR | 120 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M | 16 | 400 | 24894
PR | 120 | 08/23/19 | 840 | Lopez, Maslin A | 32 | 544 | 24898
PR | 120 | 08/23/19 | 846 | Montenegro, Carlos E | 40 | 1240 | 24904
PR | 120 | 08/23/19 | 854 | Roberts, Lake A | 29 | 580 | 24912
PR | 120 | 08/23/19 | 855 | Rodriguez Arevalos, Christian | 40 | 1040 | 24913
PR | 120 | 08/23/19 | 856 | Romero Garza, Jesus I | 32 | 576 | 24914
PR | 120 | 08/23/19 | 857 | Ross, Kelli M | 40 | 1680 | 24915
PR | 120 | 08/23/19 | 860 | Silva Morales, Jair J | 16 | 432 | 24918
PR | 120 | 08/23/19 | 872 | Wilson, Garret A | 40 | 1600 | 24930
PR | 120 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A | 24 | 768 | 24931
PR | 120 | 08/30/19 | 997 | Boss, Aaron J | 40 | 640 | 24939
PR | 120 | 08/30/19 | 1011 | Escalante Escobar, Boanerge | 16 | 352 | 24953
PR | 120 | 08/30/19 | 1026 | Hubbard, Robert W | 4 | 200 | 24968
PR | 120 | 08/30/19 | 1031 | Lopez, Maslin A | 32 | 544 | 24973
PR | 120 | 08/30/19 | 1037 | Montenegro, Carlos E | 16 | 496 | 24979
PR | 120 | 08/30/19 | 1045 | Roberts, Lake A | 29 | 580 | 24987
PR | 120 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian | 24 | 624 | 24988
PR | 120 | 08/30/19 | 1047 | Romero Garza, Jesus I | 32 | 576 | 24989
PR | 120 | 08/30/19 | 1048 | Ross, Kelli M | 32 | 1344 | 24990
PR | 120 | 08/30/19 | 1063 | Wilson, Garret A | 40 | 1600 | 25007
PR | 120 | 09/06/19 | 18 | Boss, Aaron J | 32 | 512 | 25016
PR | 120 | 09/06/19 | 32 | Escalante Escobar, Boanerge | 32 | 704 | 25030
PR | 120 | 09/06/19 | 47 | Hubbard, Robert W | 3 | 150 | 25045
PR | 120 | 09/06/19 | 52 | Lopez, Maslin A | 11 | 187 | 25050
PR | 120 | 09/06/19 | 58 | Montenegro, Carlos E | 32 | 992 | 25056
PR | 120 | 09/06/19 | 66 | Roberts, Lake A | 3 | 60 | 25064
PR | 120 | 09/06/19 | 67 | Rodriguez Arevalos, Christian | 13 | 338 | 25065
PR | 120 | 09/06/19 | 68 | Romero Garza, Jesus I | 24 | 432 | 25066
PR | 120 | 09/06/19 | 69 | Ross, Kelli M | 24 | 1008 | 25067
PR | 120 | 09/06/19 | 84 | Wilson, Garret A | 22 | 880 | 25082
PR | 120 | 09/13/19 | 242 | Boss, Aaron J | 40 | 640 | 25091
PR | 120 | 09/13/19 | 243 | Boss, Kyle A | 6 | 108 | 25092
PR | 120 | 09/13/19 | 256 | Escalante Escobar, Boanerge | 40 | 880 | 25105
PR | 120 | 09/13/19 | 271 | Hubbard, Robert W | 6 | 300 | 25120
PR | 120 | 09/13/19 | 275 | Lopez, Maslin A | 8 | 204 | 25124
PR | 120 | 09/13/19 | 275 | Lopez, Maslin A | 40 | 680 | 25124
PR | 120 | 09/13/19 | 281 | Montenegro, Carlos E | 32 | 992 | 25130
PR | 120 | 09/13/19 | 289 | Roberts, Lake A | 2 | 60 | 25138
PR | 120 | 09/13/19 | 289 | Roberts, Lake A | 24 | 480 | 25138
PR | 120 | 09/13/19 | 290 | Rodriguez Arevalos, Christian | 8 | 312 | 25139
PR | 120 | 09/13/19 | 290 | Rodriguez Arevalos, Christian | 40 | 1040 | 25139
PR | 120 | 09/13/19 | 291 | Romero Garza, Jesus I | 8 | 216 | 25140
PR | 120 | 09/13/19 | 291 | Romero Garza, Jesus I | 40 | 720 | 25140
PR | 120 | 09/13/19 | 292 | Ross, Kelli M | 8 | 504 | 25141
PR | 120 | 09/13/19 | 292 | Ross, Kelli M | 40 | 1680 | 25141
PR | 120 | 09/13/19 | 307 | Wilson, Garret A | 6 | 240 | 25156
PR | 120 | 09/20/19 | 479 | Boss, Aaron J | 40 | 640 | 25165
PR | 120 | 09/20/19 | 480 | Boss, Kyle A | 24 | 432 | 25166
PR | 120 | 09/20/19 | 481 | Castro Hernandez, Jose A | 8 | 280 | 25167
PR | 120 | 09/20/19 | 487 | Cruz Guzman, Joel A | 8 | 224 | 25173
PR | 120 | 09/20/19 | 493 | Escalante Escobar, Boanerge | 40 | 880 | 25179
PR | 120 | 09/20/19 | 502 | Guerrero Espinoza, Mario | 8 | 128 | 25188
PR | 120 | 09/20/19 | 509 | Hubbard, Robert W | 4 | 200 | 25195
PR | 120 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M | 8 | 200 | 25196
PR | 120 | 09/20/19 | 513 | Lopez, Maslin A | 40 | 680 | 25199
PR | 120 | 09/20/19 | 519 | Montenegro, Carlos E | 40 | 1240 | 25205
PR | 120 | 09/20/19 | 527 | Roberts, Lake A | 31 | 620 | 25213
PR | 120 | 09/20/19 | 528 | Rodriguez Arevalos, Christian | 40 | 1040 | 25214
PR | 120 | 09/20/19 | 529 | Romero Garza, Jesus I | 32 | 576 | 25215
PR | 120 | 09/20/19 | 530 | Ross, Kelli M | 32 | 1344 | 25216
PR | 120 | 09/20/19 | 533 | Silva Morales, Jair J | 8 | 216 | 25219
PR | 120 | 09/20/19 | 545 | Wilson, Garret A | 9 | 360 | 25231
PR | 120 | 09/27/19 | 635 | Boss, Aaron J | 40 | 640 | 25240
PR | 120 | 09/27/19 | 636 | Boss, Kyle A | 40 | 720 | 25241
PR | 120 | 09/27/19 | 649 | Escalante Escobar, Boanerge | 16 | 352 | 25254
PR | 120 | 09/27/19 | 666 | Hubbard, Robert W | 7 | 350 | 25271
PR | 120 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M | 8 | 200 | 25272
PR | 120 | 09/27/19 | 672 | Lopez, Maslin A | 40 | 680 | 25277
PR | 120 | 09/27/19 | 678 | Montenegro, Carlos E | 8 | 248 | 25283
PR | 120 | 09/27/19 | 686 | Roberts, Lake A | 22 | 484 | 25291
PR | 120 | 09/27/19 | 687 | Rodriguez Arevalos, Christian | 32 | 832 | 25292
PR | 120 | 09/27/19 | 688 | Romero Garza, Jesus I | 32 | 640 | 25293
PR | 120 | 09/27/19 | 689 | Ross, Kelli M | 40 | 1680 | 25294
PR | 120 | 09/27/19 | 704 | Wilson, Garret A | 32 | 1280 | 25309
PR | 120 | 10/04/19 | 11 | Boss, Aaron J | 40 | 640 | 25318
PR | 120 | 10/04/19 | 12 | Boss, Kyle A | 40 | 720 | 25319
PR | 120 | 10/04/19 | 25 | Escalante Escobar, Boanerge | 19 | 418 | 25332
PR | 120 | 10/04/19 | 41 | Hubbard, Robert W | 6 | 300 | 25348
PR | 120 | 10/04/19 | 47 | Lopez, Maslin A | 40 | 680 | 25354
PR | 120 | 10/04/19 | 54 | Montenegro, Carlos E | 40 | 1240 | 25361
PR | 120 | 10/04/19 | 62 | Roberts, Lake A | 40 | 880 | 25369
PR | 120 | 10/04/19 | 63 | Rodriguez Arevalos, Christian | 40 | 1040 | 25370
PR | 120 | 10/04/19 | 64 | Romero Garza, Jesus I | 40 | 800 | 25371
PR | 120 | 10/04/19 | 65 | Ross, Kelli M | 36 | 1512 | 25372
PR | 120 | 10/04/19 | 80 | Wilson, Garret A | 29 | 1160 | 25387
PR | 120 | 10/11/19 | 266 | Boss, Aaron J | 24 | 384 | 25400
PR | 120 | 10/11/19 | 267 | Boss, Kyle A | 16 | 288 | 25401
PR | 120 | 10/11/19 | 280 | Escalante Escobar, Boanerge | 40 | 880 | 25414
PR | 120 | 10/11/19 | 296 | Hubbard, Robert W | 14 | 700 | 25430
PR | 120 | 10/11/19 | 302 | Lopez, Maslin A | 40 | 680 | 25436
PR | 120 | 10/11/19 | 307 | McCabe, Thomas C | 8 | 280 | 25441
PR | 120 | 10/11/19 | 309 | Paco Leyva, Orlando | 2 | 80 | 25443
PR | 120 | 10/11/19 | 311 | Ramos Herrera, Franklin J | 2 | 52 | 25445
PR | 120 | 10/11/19 | 316 | Roberts, Lake A | 10 | 220 | 25450
PR | 120 | 10/11/19 | 317 | Rodriguez Arevalos, Christian | 40 | 1040 | 25451
PR | 120 | 10/11/19 | 318 | Romero Garza, Jesus I | 16 | 320 | 25452
PR | 120 | 10/11/19 | 320 | Ross, Kelli M | 34 | 1428 | 25454
PR | 120 | 10/18/19 | 460 | Boss, Aaron J | 40 | 640 | 25476
PR | 120 | 10/18/19 | 461 | Boss, Kyle A | 10 | 180 | 25477
PR | 120 | 10/18/19 | 473 | Escalante Escobar, Boanerge | 36 | 792 | 25489
PR | 120 | 10/18/19 | 489 | Hubbard, Robert W | 15 | 750 | 25506
PR | 120 | 10/18/19 | 495 | Lopez, Maslin A | 40 | 680 | 25512
PR | 120 | 10/18/19 | 509 | Roberts, Lake A | 4 | 88 | 25526
PR | 120 | 10/18/19 | 510 | Rodriguez Arevalos, Christian | 32 | 832 | 25527
PR | 120 | 10/18/19 | 511 | Romero Garza, Jesus I | 20 | 400 | 25528
PR | 120 | 10/18/19 | 513 | Ross, Kelli M | 32 | 1344 | 25530
PR | 120 | 10/25/19 | 595 | Boss, Aaron J | 37 | 592 | 25552
PR | 120 | 10/25/19 | 596 | Boss, Benjamin T | 24 | 384 | 25553
PR | 120 | 10/25/19 | 608 | Escalante Escobar, Boanerge | 8 | 176 | 25565
PR | 120 | 10/25/19 | 624 | Hubbard, Robert W | 15 | 750 | 25581
PR | 120 | 10/25/19 | 630 | Lopez, Maslin A | 37 | 629 | 25587
PR | 120 | 10/25/19 | 645 | Roberts, Lake A | 4 | 88 | 25602
PR | 120 | 10/25/19 | 646 | Rodriguez Arevalos, Christian | 37 | 962 | 25603
PR | 120 | 10/25/19 | 647 | Romero Garza, Jesus I | 8 | 160 | 25604
PR | 120 | 10/25/19 | 649 | Ross, Kelli M | 34 | 1428 | 25606
PR | 120 | 11/01/19 | 19 | Cruz Reyes, Jose | 8 | 256 | 25636
PR | 120 | 11/01/19 | 40 | Hubbard, Robert W | 11 | 594 | 25657
PR | 120 | 11/01/19 | 46 | Lopez, Maslin A | 40 | 760 | 25663
PR | 120 | 11/01/19 | 61 | Roberts, Lake A | 4 | 100 | 25678
PR | 120 | 11/01/19 | 62 | Rodriguez Arevalos, Christian | 40 | 1200 | 25679
PR | 120 | 11/01/19 | 63 | Romero Garza, Jesus I | 8 | 184 | 25680
PR | 120 | 11/01/19 | 65 | Ross, Kelli M | 32 | 1376 | 25682
PR | 120 | 11/08/19 | 192 | Cruz Gonzalez, Julio C | 24 | 672 | 25711
PR | 120 | 11/08/19 | 198 | Escalante Escobar, Boanerge | 12 | 300 | 25717
PR | 120 | 11/08/19 | 214 | Hubbard, Robert W | 16 | 864 | 25733
PR | 120 | 11/08/19 | 220 | Lopez, Maslin A | 32 | 608 | 25739
PR | 120 | 11/08/19 | 235 | Roberts, Lake A | 4 | 100 | 25754
PR | 120 | 11/08/19 | 236 | Rodriguez Arevalos, Christian | 40 | 1200 | 25755
PR | 120 | 11/08/19 | 239 | Ross, Kelli M | 16 | 688 | 25758
PR | 120 | 11/15/19 | 445 | Boss, Benjamin T | 40 | 640 | 25780
PR | 120 | 11/15/19 | 446 | Boss, Kyle A | 8 | 168 | 25781
PR | 120 | 11/15/19 | 452 | Cruz Gonzalez, Julio C | 32 | 896 | 25787
PR | 120 | 11/15/19 | 473 | Hubbard, Robert W | 6 | 324 | 25809
PR | 120 | 11/15/19 | 479 | Lopez, Maslin A | 32 | 608 | 25815
PR | 120 | 11/15/19 | 495 | Rodriguez Arevalos, Christian | 32 | 960 | 25831
PR | 120 | 11/15/19 | 496 | Romero Garza, Jesus I | 40 | 920 | 25832
PR | 120 | 11/15/19 | 498 | Ross, Kelli M | 16 | 688 | 25834
PR | 120 | 11/22/19 | 616 | Boss, Benjamin T | 8 | 128 | 25856
PR | 120 | 11/22/19 | 617 | Boss, Kyle A | 16 | 336 | 25857
PR | 120 | 11/22/19 | 623 | Cruz Gonzalez, Julio C | 14 | 392 | 25863
PR | 120 | 11/22/19 | 644 | Hubbard, Robert W | 5 | 270 | 25884
PR | 120 | 11/22/19 | 650 | Lopez, Maslin A | 32 | 608 | 25890
PR | 120 | 11/22/19 | 665 | Roberts, Lake A | 2 | 50 | 25905
PR | 120 | 11/22/19 | 666 | Rodriguez Arevalos, Christian | 32 | 960 | 25906
PR | 120 | 11/22/19 | 667 | Romero Garza, Jesus I | 32 | 736 | 25907
PR | 120 | 11/27/19 | 851 | Boss, Kyle A | 8 | 168 | 25932
PR | 120 | 11/27/19 | 878 | Hubbard, Robert W | 10 | 540 | 25959
PR | 120 | 11/27/19 | 899 | Roberts, Lake A | 24 | 600 | 25980
PR | 120 | 12/13/19 | 426 | Hubbard, Robert W | 2 | 108 | 26191
GL | 120 | 12/19/19 | 680 | Escalante Escobar |  | -660
PR | 120 | 12/27/19 | 708 | Boss, Kyle A | 8 | 168 | 26316
PR | 120 | 12/27/19 | 737 | Hubbard, Robert W | 8 | 432 | 26345
PR | 120 | 12/27/19 | 748 | McCabe, Thomas C | 11 | 429 | 26356
PR | 120 | 12/27/19 | 758 | Roberts, Lake A | 12 | 300 | 26366
PR | 120 | 01/03/20 | 51 | McCabe, Thomas C | 16 | 624 | 26434
PR | 120 | 01/10/20 | 313 | Hubbard, Robert W | 4.5 | 243 | 26500
PR | 120 | 02/14/20 | 292 | Roberts, Lake A | 4 | 100 | 26908
PR | 120 | 02/28/20 | 716 | Hubbard, Robert W | 10 | 540 | 27044
PR | 120 | 02/28/20 | 725 | McCabe, Thomas C | 13.5 | 526.5 | 27053
PR | 120 | 02/28/20 | 737 | Roberts, Lake A | 8 | 200 | 27065
PR | 130 | 10/18/19 | 478 | Gerard, Jordan E | 3 | 108 | 25494
PR | 130 | 10/18/19 | 521 | Vazquez Popoca, Jose N | 8 | 136 | 25538
PR | 130 | 11/01/19 | 66 | Sanders, Allen O | 7 | 378 | 25683
PR | 130 | 11/22/19 | 670 | Sanders, Allen O | 4 | 216 | 25910
PR | 130 | 11/27/19 | 850 | Boss, Benjamin T | 16 | 256 | 25931
PR | 130 | 11/27/19 | 851 | Boss, Kyle A | 8 | 168 | 25932
PR | 130 | 11/27/19 | 857 | Cruz Gonzalez, Julio C | 32 | 896 | 25938
PR | 130 | 11/27/19 | 899 | Roberts, Lake A | 8 | 200 | 25980
PR | 130 | 11/27/19 | 901 | Romero Garza, Jesus I | 24 | 552 | 25982
PR | 130 | 11/27/19 | 904 | Sanders, Allen O | 9 | 486 | 25985
PR | 130 | 12/06/19 | 36 | Boss, Benjamin T | 16 | 256 | 26008
PR | 130 | 12/06/19 | 37 | Boss, Kyle A | 24 | 504 | 26009
PR | 130 | 12/06/19 | 43 | Cruz Gonzalez, Julio C | 16 | 448 | 26015
PR | 130 | 12/06/19 | 76 | McCabe, Thomas C | 20 | 780 | 26048
PR | 130 | 12/06/19 | 86 | Roberts, Lake A | 8 | 200 | 26058
PR | 130 | 12/06/19 | 88 | Romero Garza, Jesus I | 24 | 552 | 26060
PR | 130 | 12/06/19 | 91 | Sanders, Allen O | 5.5 | 297 | 26063
PR | 130 | 12/13/19 | 397 | Boss, Benjamin T | 40 | 640 | 26162
PR | 130 | 12/13/19 | 398 | Boss, Kyle A | 40 | 840 | 26163
PR | 130 | 12/13/19 | 404 | Cruz Gonzalez, Julio C | 16 | 448 | 26169
PR | 130 | 12/13/19 | 426 | Hubbard, Robert W | 8 | 432 | 26191
PR | 130 | 12/13/19 | 437 | McCabe, Thomas C | 17 | 663 | 26203
PR | 130 | 12/13/19 | 447 | Roberts, Lake A | 40 | 1000 | 26213
PR | 130 | 12/13/19 | 449 | Romero Garza, Jesus I | 34 | 782 | 26215
PR | 130 | 12/13/19 | 452 | Sanders, Allen O | 2.5 | 135 | 26218
PR | 130 | 12/20/19 | 550 | Boss, Benjamin T | 40 | 640 | 26239
PR | 130 | 12/20/19 | 551 | Boss, Kyle A | 40 | 840 | 26240
PR | 130 | 12/20/19 | 579 | Hubbard, Robert W | 3 | 162 | 26268
PR | 130 | 12/20/19 | 590 | McCabe, Thomas C | 8 | 312 | 26279
PR | 130 | 12/20/19 | 600 | Roberts, Lake A | 16 | 400 | 26289
PR | 130 | 12/20/19 | 602 | Romero Garza, Jesus I | 40 | 920 | 26291
PR | 130 | 12/20/19 | 605 | Sanders, Allen O | 5 | 270 | 26294
PR | 130 | 12/27/19 | 707 | Boss, Benjamin T | 8 | 128 | 26315
PR | 130 | 12/27/19 | 708 | Boss, Kyle A | 16 | 336 | 26316
PR | 130 | 12/27/19 | 760 | Romero Garza, Jesus I | 24 | 552 | 26368
PR | 130 | 12/27/19 | 763 | Sanders, Allen O | 4 | 216 | 26371
PR | 130 | 01/03/20 | 10 | Boss, Benjamin T | 21 | 336 | 26392
PR | 130 | 01/03/20 | 11 | Boss, Kyle A | 21 | 441 | 26393
PR | 130 | 01/03/20 | 40 | Hubbard, Robert W | 6 | 324 | 26423
PR | 130 | 01/03/20 | 61 | Roberts, Lake A | 21 | 525 | 26444
PR | 130 | 01/03/20 | 63 | Romero Garza, Jesus I | 21 | 483 | 26446
PR | 130 | 01/03/20 | 66 | Sanders, Allen O | 4 | 216 | 26449
PR | 130 | 01/10/20 | 283 | Boss, Benjamin T | 40 | 640 | 26470
PR | 130 | 01/10/20 | 284 | Boss, Kyle A | 40 | 840 | 26471
PR | 130 | 01/10/20 | 313 | Hubbard, Robert W | 1.5 | 81 | 26500
PR | 130 | 01/10/20 | 334 | Roberts, Lake A | 23.5 | 587.5 | 26522
PR | 130 | 01/10/20 | 336 | Romero Garza, Jesus I | 40 | 920 | 26524
PR | 130 | 01/10/20 | 339 | Sanders, Allen O | 10 | 540 | 26527
PR | 130 | 01/17/20 | 549 | Boss, Benjamin T | 25 | 400 | 26548
PR | 130 | 01/17/20 | 550 | Boss, Kyle A | 33 | 693 | 26549
PR | 130 | 01/17/20 | 556 | Cruz Gonzalez, Julio C | 8 | 224 | 26555
PR | 130 | 01/17/20 | 600 | Roberts, Lake A | 16 | 400 | 26599
PR | 130 | 01/17/20 | 602 | Romero Garza, Jesus I | 8 | 184 | 26601
PR | 130 | 01/17/20 | 605 | Sanders, Allen O | 10.5 | 567 | 26604
PR | 130 | 01/24/20 | 682 | Boss, Benjamin T | 36 | 576 | 26625
PR | 130 | 01/24/20 | 683 | Boss, Kyle A | 33 | 693 | 26626
PR | 130 | 01/24/20 | 711 | Hubbard, Robert W | 3 | 162 | 26654
PR | 130 | 01/24/20 | 736 | Sanders, Allen O | 9.5 | 513 | 26679
PR | 130 | 01/31/20 | 841 | Boss, Benjamin T | 40 | 640 | 26702
PR | 130 | 01/31/20 | 842 | Boss, Kyle A | 40 | 840 | 26703
PR | 130 | 01/31/20 | 871 | Hubbard, Robert W | 1 | 54 | 26732
PR | 130 | 01/31/20 | 892 | Roberts, Lake A | 16 | 400 | 26753
PR | 130 | 01/31/20 | 897 | Sanders, Allen O | 16.5 | 891 | 26758
PR | 130 | 01/31/20 | 903 | Trower-Kelly, Fidel D | 40 | 840 | 26764
PR | 130 | 02/07/20 | 32 | Boss, Benjamin T | 40 | 640 | 26780
PR | 130 | 02/07/20 | 33 | Boss, Kyle A | 40 | 840 | 26781
PR | 130 | 02/07/20 | 82 | Roberts, Lake A | 36 | 900 | 26830
PR | 130 | 02/07/20 | 88 | Sanders, Allen O | 12 | 648 | 26836
PR | 130 | 02/07/20 | 94 | Trower-Kelly, Fidel D | 24 | 504 | 26842
PR | 130 | 02/14/20 | 242 | Boss, Benjamin T | 32 | 576 | 26858
PR | 130 | 02/14/20 | 243 | Boss, Kyle A | 32 | 672 | 26859
PR | 130 | 02/14/20 | 249 | Cruz Gonzalez, Julio C | 8 | 224 | 26865
PR | 130 | 02/14/20 | 251 | Cruz Reyes, Jose | 8 | 256 | 26867
PR | 130 | 02/14/20 | 292 | Roberts, Lake A | 3 | 75 | 26908
PR | 130 | 02/14/20 | 298 | Sanders, Allen O | 5 | 270 | 26914
PR | 130 | 02/14/20 | 304 | Trower-Kelly, Fidel D | 8 | 168 | 26920
PR | 130 | 02/21/20 | 459 | Boss, Benjamin T | 24 | 432 | 26936
PR | 130 | 02/21/20 | 460 | Boss, Kyle A | 24 | 504 | 26937
PR | 130 | 02/21/20 | 514 | Sanders, Allen O | 14.5 | 783 | 26991
PR | 130 | 02/21/20 | 520 | Trower-Kelly, Fidel D | 24 | 504 | 26997
PR | 130 | 02/28/20 | 687 | Boss, Benjamin T | 24 | 432 | 27015
PR | 130 | 02/28/20 | 688 | Boss, Kyle A | 21 | 441 | 27016
PR | 130 | 02/28/20 | 696 | Cruz Reyes, Jose | 24 | 768 | 27024
PR | 130 | 02/28/20 | 739 | Romero Garza, Jesus I | 8 | 184 | 27067
PR | 130 | 02/28/20 | 743 | Sanders, Allen O | 14 | 756 | 27071
PR | 130 | 02/28/20 | 749 | Trower-Kelly, Fidel D | 24 | 504 | 27077
PR | 130 | 03/06/20 | 50 | Boss, Kyle A | 24 | 504 | 27094
PR | 130 | 03/06/20 | 58 | Cruz Reyes, Jose | 16 | 512 | 27102
PR | 130 | 03/06/20 | 87 | McCabe, Thomas C | 24 | 936 | 27131
PR | 130 | 03/06/20 | 99 | Roberts, Lake A | 24 | 600 | 27143
PR | 130 | 03/06/20 | 101 | Romero Garza, Jesus I | 16 | 368 | 27145
PR | 130 | 03/06/20 | 105 | Sanders, Allen O | 16.5 | 891 | 27149
PR | 130 | 03/13/20 | 351 | McCabe, Thomas C | 24 | 936 | 27212
PR | 130 | 03/13/20 | 363 | Roberts, Lake A | 24 | 600 | 27224
PR | 130 | 03/13/20 | 369 | Sanders, Allen O | 17 | 918 | 27230
PR | 130 | 03/13/20 | 375 | Trower-Kelly, Fidel D | 16 | 336 | 27236
PR | 130 | 03/20/20 | 572 | Boss, Benjamin T | 32 | 576 | 27252
PR | 130 | 03/20/20 | 573 | Boss, Kyle A | 32 | 672 | 27253
PR | 130 | 03/20/20 | 579 | Cruz Gonzalez, Julio C | 32 | 896 | 27259
PR | 130 | 03/20/20 | 581 | Cruz Reyes, Jose | 32 | 1024 | 27261
PR | 130 | 03/20/20 | 585 | Eliassen, Cory H | 4 | 120 | 27265
PR | 130 | 03/20/20 | 623 | Romero Garza, Jesus I | 32 | 736 | 27303
PR | 130 | 03/20/20 | 627 | Sanders, Allen O | 9.5 | 513 | 27307
PR | 130 | 03/20/20 | 633 | Trower-Kelly, Fidel D | 40 | 840 | 27313
PR | 130 | 03/26/20 | 803 | Romero Garza, Jesus I | 8 | 184 | 27379
PR | 130 | 03/26/20 | 806 | Sanders, Allen O | 7.5 | 405 | 27382
PR | 130 | 03/26/20 | 812 | Trower-Kelly, Fidel D | 8 | 168 | 27388
PR | 130 | 05/01/20 | 64 | Sanders, Allen O | 3 | 162 | 27691
PR | 130 | 05/08/20 | 161 | Boss, Kyle A | 40 | 840 | 27716
PR | 130 | 05/08/20 | 167 | Cruz Gonzalez, Julio C | 24 | 672 | 27722
PR | 130 | 05/08/20 | 215 | Sanders, Allen O | 15 | 810 | 27770
PR | 130 | 05/08/20 | 221 | Trower-Kelly, Fidel D | 40 | 840 | 27776
PR | 130 | 05/15/20 | 315 | Boss, Benjamin T | 16 | 288 | 27793
PR | 130 | 05/15/20 | 316 | Boss, Kyle A | 40 | 840 | 27794
PR | 130 | 05/15/20 | 322 | Cruz Gonzalez, Julio C | 40 | 1120 | 27800
PR | 130 | 05/15/20 | 324 | Cruz Reyes, Jose | 24 | 768 | 27802
PR | 130 | 05/15/20 | 328 | Eliassen, Cory H | 16 | 480 | 27806
PR | 130 | 05/15/20 | 343 | Hubbard, Robert W | 3 | 162 | 27821
PR | 130 | 05/15/20 | 366 | Romero Garza, Jesus I | 16 | 368 | 27844
PR | 130 | 05/15/20 | 370 | Sanders, Allen O | 29 | 1566 | 27848
PR | 130 | 05/15/20 | 376 | Trower-Kelly, Fidel D | 40 | 840 | 27854
PR | 130 | 05/22/20 | 470 | Boss, Benjamin T | 24 | 432 | 27870
PR | 130 | 05/22/20 | 477 | Cruz Gonzalez, Julio C | 8 | 224 | 27877
PR | 130 | 05/22/20 | 479 | Cruz Reyes, Jose | 8 | 256 | 27879
PR | 130 | 05/22/20 | 483 | Eliassen, Cory H | 8 | 240 | 27883
PR | 130 | 05/22/20 | 517 | Romero Garza, Jesus I | 8 | 184 | 27917
PR | 130 | 05/22/20 | 520 | Sanders, Allen O | 29.5 | 1593 | 27920
PR | 130 | 05/22/20 | 526 | Trower-Kelly, Fidel D | 40 | 840 | 27926
PR | 130 | 05/29/20 | 598 | Boss, Benjamin T | 8 | 144 | 27941
PR | 130 | 05/29/20 | 646 | Sanders, Allen O | 22 | 1188 | 27989
PR | 130 | 05/29/20 | 652 | Trower-Kelly, Fidel D | 24 | 504 | 27995
PR | 130 | 06/05/20 | 19 | Boss, Benjamin T | 8 | 144 | 28009
PR | 130 | 06/05/20 | 58 | Sanders, Allen O | 25 | 1350 | 28048
PR | 130 | 06/05/20 | 62 | Trower-Kelly, Fidel D | 24 | 504 | 28052
PR | 130 | 06/12/20 | 260 | Sanders, Allen O | 20 | 1080 | 28145
PR | 130 | 06/19/20 | 416 | Sanders, Allen O | 17.5 | 945 | 28193
PR | 130 | 06/26/20 | 541 | Hubbard, Robert W | 2 | 108 | 28223
PR | 130 | 07/02/20 | 44 | Sanders, Allen O | 6 | 324 | 28287
PR | 130 | 07/24/20 | 442 | Sanders, Allen O | 2 | 108 | 28434
PR | 130 | 07/31/20 | 537 | Sanders, Allen O | 2 | 108 | 28483
PR | 140 | 03/15/19 | 525 | Hubbard, Robert W | 2 | 98 | 23087
PR | 140 | 07/12/19 | 351 | Wilson, Garret A | 0.5 | 20 | 24403
PR | 140 | 07/19/19 | 516 | Boss, Kyle A | 40 | 720 | 24415
PR | 140 | 07/19/19 | 543 | Hubbard, Robert W | 1 | 50 | 24442
PR | 140 | 07/19/19 | 581 | Wilson, Garret A | 9 | 360 | 24480
PR | 140 | 07/26/19 | 620 | Boss, Kyle A | 40 | 720 | 24569
PR | 140 | 07/26/19 | 684 | Wilson, Garret A | 1 | 40 | 24633
PR | 140 | 08/02/19 | 12 | Boss, Kyle A | 16 | 288 | 24643
PR | 140 | 08/09/19 | 264 | Boss, Kyle A | 13 | 234 | 24717
PR | 140 | 08/16/19 | 571 | Boss, Kyle A | 21 | 378 | 24790
PR | 140 | 08/23/19 | 807 | Boss, Kyle A | 32 | 576 | 24865
PR | 140 | 08/23/19 | 854 | Roberts, Lake A | 11 | 220 | 24912
PR | 140 | 08/30/19 | 998 | Boss, Kyle A | 40 | 720 | 24940
PR | 140 | 08/30/19 | 1045 | Roberts, Lake A | 8 | 160 | 24987
PR | 140 | 09/06/19 | 19 | Boss, Kyle A | 22 | 396 | 25017
PR | 140 | 09/06/19 | 66 | Roberts, Lake A | 29 | 580 | 25064
PR | 140 | 09/13/19 | 289 | Roberts, Lake A | 6 | 180 | 25138
PR | 140 | 09/13/19 | 289 | Roberts, Lake A | 16 | 320 | 25138
PR | 140 | 09/20/19 | 527 | Roberts, Lake A | 9 | 180 | 25213
PR | 140 | 09/20/19 | 545 | Wilson, Garret A | 9 | 360 | 25231
PR | 140 | 09/27/19 | 686 | Roberts, Lake A | 6 | 132 | 25291
PR | 140 | 09/27/19 | 704 | Wilson, Garret A | 4 | 160 | 25309
PR | 140 | 10/18/19 | 461 | Boss, Kyle A | 16 | 288 | 25477
PR | 140 | 10/18/19 | 489 | Hubbard, Robert W | 1 | 50 | 25506
PR | 140 | 10/18/19 | 500 | McCabe, Thomas C | 5 | 175 | 25517
PR | 140 | 10/18/19 | 509 | Roberts, Lake A | 16 | 352 | 25526
PR | 140 | 10/25/19 | 597 | Boss, Kyle A | 24 | 432 | 25554
PR | 140 | 10/25/19 | 624 | Hubbard, Robert W | 8 | 400 | 25581
PR | 140 | 10/25/19 | 635 | McCabe, Thomas C | 4 | 140 | 25592
PR | 140 | 10/25/19 | 645 | Roberts, Lake A | 4 | 88 | 25602
PR | 140 | 11/01/19 | 40 | Hubbard, Robert W | 1 | 54 | 25657
PR | 140 | 11/01/19 | 61 | Roberts, Lake A | 4 | 100 | 25678
PR | 140 | 11/08/19 | 214 | Hubbard, Robert W | 2 | 108 | 25733
PR | 140 | 11/08/19 | 235 | Roberts, Lake A | 12 | 300 | 25754
PR | 140 | 11/22/19 | 665 | Roberts, Lake A | 3 | 75 | 25905
PR | 140 | 12/27/19 | 737 | Hubbard, Robert W | 2 | 108 | 26345
PR | 140 | 12/27/19 | 748 | McCabe, Thomas C | 2 | 78 | 26356
PR | 140 | 01/24/20 | 711 | Hubbard, Robert W | 2 | 108 | 26654
PR | 140 | 02/14/20 | 281 | McCabe, Thomas C | 5 | 195 | 26897
PR | 140 | 02/14/20 | 292 | Roberts, Lake A | 5 | 125 | 26908
PR | 140 | 02/28/20 | 716 | Hubbard, Robert W | 2 | 108 | 27044
PR | 140 | 02/28/20 | 725 | McCabe, Thomas C | 4 | 156 | 27053
PR | 140 | 02/28/20 | 737 | Roberts, Lake A | 8 | 200 | 27065
PR | 140 | 07/02/20 | 44 | Sanders, Allen O | 3 | 162 | 28287
PR | 141 | 12/14/18 | 334 | Waites, Thaddeus Z | 4 | 258 | 22193
PR | 141 | 03/29/19 | 920 | Barbosa, Michael S | 5 | 187.5 | 23204
PR | 141 | 03/29/19 | 920 | Barbosa, Michael S | 26 | 650 | 23204
PR | 141 | 03/29/19 | 938 | Foster, Antonio T | 29 | 551 | 23222
PR | 141 | 03/29/19 | 987 | Wilson, Garret A | 1 | 55.5 | 23271
PR | 141 | 03/29/19 | 987 | Wilson, Garret A | 4 | 148 | 23271
PR | 141 | 03/29/19 | 992 | Barbosa, Michael S | 5 | -187.5 | 23204
PR | 141 | 03/29/19 | 992 | Barbosa, Michael S | 26 | -650 | 23204
PR | 141 | 03/29/19 | 993 | Barbosa, Michael S | 5 | 187.5 | 23199
PR | 141 | 03/29/19 | 993 | Barbosa, Michael S | 26 | 650 | 23199
PR | 141 | 04/05/19 | 82 | Barbosa, Michael S | 8 | 300 | 23276
PR | 141 | 04/05/19 | 82 | Barbosa, Michael S | 40 | 1000 | 23276
PR | 141 | 04/05/19 | 100 | Foster, Antonio T | 6 | 171 | 23294
PR | 141 | 04/05/19 | 100 | Foster, Antonio T | 32 | 608 | 23294
PR | 141 | 04/05/19 | 150 | Wilson, Garret A | 2 | 74 | 23344
PR | 141 | 04/12/19 | 326 | Barbosa, Michael S | 2 | 75 | 23350
PR | 141 | 04/12/19 | 326 | Barbosa, Michael S | 8 | 200 | 23350
PR | 141 | 04/12/19 | 344 | Foster, Antonio T | 8 | 152 | 23368
PR | 141 | 04/19/19 | 523 | Barbosa, Michael S | 2 | 75 | 23424
PR | 141 | 04/19/19 | 523 | Barbosa, Michael S | 8 | 200 | 23424
PR | 141 | 04/19/19 | 566 | Montenegro, Carlos E | 4 | 174 | 23467
PR | 141 | 04/19/19 | 566 | Montenegro, Carlos E | 16 | 464 | 23467
PR | 141 | 04/26/19 | 785 | Montenegro, Carlos E | 2 | 93 | 23542
PR | 141 | 04/26/19 | 785 | Montenegro, Carlos E | 21 | 651 | 23542
PR | 141 | 04/26/19 | 810 | Wilson, Garret A | 1 | 40 | 23567
PR | 141 | 05/03/19 | 54 | Montenegro, Carlos E | 32 | 992 | 23616
PR | 141 | 05/03/19 | 80 | Wilson, Garret A | 5 | 200 | 23642
PR | 141 | 05/10/19 | 207 | Montenegro, Carlos E | 40 | 1240 | 23691
PR | 141 | 05/10/19 | 233 | Wilson, Garret A | 3 | 120 | 23718
PR | 141 | 05/17/19 | 412 | Escalante Escobar, Boanerge | 40 | 880 | 23743
PR | 141 | 05/17/19 | 439 | Montenegro, Carlos E | 40 | 1240 | 23770
PR | 141 | 05/17/19 | 465 | Wilson, Garret A | 5 | 200 | 23796
PR | 141 | 05/24/19 | 624 | Escalante Escobar, Boanerge | 40 | 880 | 23819
PR | 141 | 05/24/19 | 651 | Montenegro, Carlos E | 40 | 1240 | 23846
PR | 141 | 05/24/19 | 652 | Paco Leyva, Orlando | 19 | 760 | 23847
PR | 141 | 05/31/19 | 898 | Escalante Escobar, Boanerge | 32 | 704 | 23898
PR | 141 | 05/31/19 | 925 | Montenegro, Carlos E | 32 | 992 | 23925
PR | 141 | 05/31/19 | 926 | Paco Leyva, Orlando | 12 | 480 | 23926
PR | 141 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A | 8 | 256 | 23953
PR | 141 | 06/07/19 | 200 | Escalante Escobar, Boanerge | 40 | 880 | 23975
PR | 141 | 06/07/19 | 226 | Montenegro, Carlos E | 40 | 1240 | 24001
PR | 141 | 06/07/19 | 227 | Paco Leyva, Orlando | 4 | 160 | 24002
PR | 141 | 06/14/19 | 470 | Escalante Escobar, Boanerge | 32 | 704 | 24051
PR | 141 | 06/14/19 | 495 | Montenegro, Carlos E | 32 | 992 | 24076
PR | 141 | 06/14/19 | 496 | Paco Leyva, Orlando | 14.5 | 580 | 24077
PR | 141 | 06/21/19 | 640 | Escalante Escobar, Boanerge | 40 | 880 | 24126
PR | 141 | 06/21/19 | 666 | Montenegro, Carlos E | 40 | 1240 | 24152
PR | 141 | 06/21/19 | 667 | Paco Leyva, Orlando | 10 | 400 | 24153
PR | 141 | 06/28/19 | 858 | Escalante Escobar, Boanerge | 40 | 880 | 24202
PR | 141 | 06/28/19 | 883 | Montenegro, Carlos E | 40 | 1240 | 24227
PR | 141 | 07/05/19 | 30 | Escalante Escobar, Boanerge | 31 | 682 | 24277
PR | 141 | 07/05/19 | 55 | Montenegro, Carlos E | 16 | 496 | 24303
PR | 141 | 07/05/19 | 63 | Roberts, Lake A | 16 | 320 | 24311
PR | 141 | 07/12/19 | 299 | Escalante Escobar, Boanerge | 32 | 704 | 24351
PR | 141 | 07/12/19 | 324 | Montenegro, Carlos E | 16 | 496 | 24376
PR | 141 | 07/19/19 | 529 | Escalante Escobar, Boanerge | 40 | 880 | 24428
PR | 141 | 07/19/19 | 554 | Montenegro, Carlos E | 32 | 992 | 24453
PR | 141 | 07/19/19 | 581 | Wilson, Garret A | 4 | 160 | 24480
PR | 141 | 07/26/19 | 613 | Ascencio, Jose L | 40 | 1200 | 24562
PR | 141 | 07/26/19 | 633 | Escalante Escobar, Boanerge | 40 | 880 | 24582
PR | 141 | 07/26/19 | 657 | Montenegro, Carlos E | 32 | 992 | 24606
PR | 141 | 08/02/19 | 25 | Escalante Escobar, Boanerge | 40 | 880 | 24656
PR | 141 | 08/02/19 | 49 | Montenegro, Carlos E | 32 | 992 | 24680
PR | 141 | 08/09/19 | 302 | Montenegro, Carlos E | 16 | 496 | 24755
PR | 141 | 08/16/19 | 609 | Montenegro, Carlos E | 8 | 248 | 24828
PR | 141 | 08/16/19 | 617 | Roberts, Lake A | 8 | 160 | 24836
PR | 141 | 08/23/19 | 840 | Lopez, Maslin A | 4 | 68 | 24898
PR | 141 | 08/23/19 | 856 | Romero Garza, Jesus I | 4 | 72 | 24914
PR | 141 | 08/30/19 | 1011 | Escalante Escobar, Boanerge | 24 | 528 | 24953
PR | 141 | 08/30/19 | 1031 | Lopez, Maslin A | 8 | 136 | 24973
PR | 141 | 08/30/19 | 1037 | Montenegro, Carlos E | 24 | 744 | 24979
PR | 141 | 08/30/19 | 1047 | Romero Garza, Jesus I | 8 | 144 | 24989
PR | 141 | 09/06/19 | 52 | Lopez, Maslin A | 8 | 136 | 25050
PR | 141 | 09/27/19 | 688 | Romero Garza, Jesus I | 8 | 160 | 25293
PR | 141 | 10/11/19 | 318 | Romero Garza, Jesus I | 8 | 160 | 25452
PR | 141 | 10/18/19 | 489 | Hubbard, Robert W | 3 | 150 | 25506
PR | 141 | 10/18/19 | 511 | Romero Garza, Jesus I | 13 | 260 | 25528
PR | 141 | 10/25/19 | 597 | Boss, Kyle A | 8 | 144 | 25554
PR | 141 | 10/25/19 | 608 | Escalante Escobar, Boanerge | 22 | 484 | 25565
PR | 141 | 10/25/19 | 624 | Hubbard, Robert W | 2 | 100 | 25581
PR | 141 | 10/25/19 | 647 | Romero Garza, Jesus I | 21 | 420 | 25604
PR | 141 | 11/01/19 | 12 | Boss, Kyle A | 8 | 168 | 25629
PR | 141 | 11/01/19 | 24 | Escalante Escobar, Boanerge | 24 | 600 | 25641
PR | 141 | 11/01/19 | 40 | Hubbard, Robert W | 3 | 162 | 25657
PR | 141 | 11/01/19 | 61 | Roberts, Lake A | 4 | 100 | 25678
PR | 141 | 11/01/19 | 63 | Romero Garza, Jesus I | 32 | 736 | 25680
PR | 141 | 11/08/19 | 185 | Boss, Benjamin T | 16 | 256 | 25704
PR | 141 | 11/08/19 | 186 | Boss, Kyle A | 8 | 168 | 25705
PR | 141 | 11/08/19 | 193 | Cruz Reyes, Jose | 16 | 512 | 25712
PR | 141 | 11/08/19 | 198 | Escalante Escobar, Boanerge | 20 | 500 | 25717
PR | 141 | 11/08/19 | 214 | Hubbard, Robert W | 1 | 54 | 25733
PR | 141 | 11/08/19 | 220 | Lopez, Maslin A | 8 | 152 | 25739
PR | 141 | 11/08/19 | 237 | Romero Garza, Jesus I | 16 | 368 | 25756
PR | 141 | 11/15/19 | 473 | Hubbard, Robert W | 5 | 270 | 25809
PR | 141 | 11/15/19 | 479 | Lopez, Maslin A | 8 | 152 | 25815
PR | 141 | 11/15/19 | 506 | Vazquez Popoca, Jose N | 16 | 320 | 25842
PR | 141 | 11/22/19 | 665 | Roberts, Lake A | 3 | 75 | 25905
PR | 141 | 11/27/19 | 850 | Boss, Benjamin T | 4 | 64 | 25931
PR | 141 | 11/27/19 | 851 | Boss, Kyle A | 12 | 252 | 25932
PR | 141 | 01/10/20 | 313 | Hubbard, Robert W | 2 | 108 | 26500
PR | 141 | 01/17/20 | 579 | Hubbard, Robert W | 1 | 54 | 26578
PR | 141 | 01/17/20 | 600 | Roberts, Lake A | 2 | 50 | 26599
PR | 141 | 02/14/20 | 271 | Hubbard, Robert W | 4 | 216 | 26887
PR | 141 | 02/28/20 | 725 | McCabe, Thomas C | 16 | 624 | 27053
PR | 141 | 03/06/20 | 78 | Hubbard, Robert W | 2 | 108 | 27122
PR | 141 | 03/06/20 | 87 | McCabe, Thomas C | 5 | 195 | 27131
PR | 141 | 03/06/20 | 99 | Roberts, Lake A | 8 | 200 | 27143
PR | 142 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo | 8 | 256 | 22687
PR | 142 | 05/31/19 | 913 | Hubbard, Robert W | 2 | 100 | 23913
PR | 142 | 09/13/19 | 271 | Hubbard, Robert W | 1 | 50 | 25120
PR | 142 | 09/27/19 | 666 | Hubbard, Robert W | 3 | 150 | 25271
PR | 142 | 09/27/19 | 676 | McCabe, Thomas C | 16 | 560 | 25281
PR | 142 | 10/04/19 | 41 | Hubbard, Robert W | 8 | 400 | 25348
PR | 142 | 10/04/19 | 52 | McCabe, Thomas C | 35 | 1225 | 25359
PR | 142 | 10/04/19 | 65 | Ross, Kelli M | 1 | 42 | 25372
PR | 142 | 10/04/19 | 80 | Wilson, Garret A | 1 | 40 | 25387
PR | 142 | 10/11/19 | 296 | Hubbard, Robert W | 4 | 200 | 25430
PR | 142 | 10/11/19 | 307 | McCabe, Thomas C | 32 | 1120 | 25441
PR | 142 | 10/11/19 | 318 | Romero Garza, Jesus I | 14.5 | 290 | 25452
PR | 142 | 10/18/19 | 489 | Hubbard, Robert W | 6 | 300 | 25506
PR | 142 | 10/18/19 | 500 | McCabe, Thomas C | 27 | 945 | 25517
PR | 142 | 10/25/19 | 624 | Hubbard, Robert W | 4 | 200 | 25581
PR | 142 | 10/25/19 | 635 | McCabe, Thomas C | 33 | 1155 | 25592
PR | 142 | 11/01/19 | 12 | Boss, Kyle A | 24 | 504 | 25629
PR | 142 | 11/01/19 | 40 | Hubbard, Robert W | 8 | 432 | 25657
PR | 142 | 11/01/19 | 51 | McCabe, Thomas C | 32 | 1248 | 25668
PR | 142 | 11/08/19 | 185 | Boss, Benjamin T | 8 | 128 | 25704
PR | 142 | 11/08/19 | 186 | Boss, Kyle A | 8 | 168 | 25705
PR | 142 | 11/08/19 | 214 | Hubbard, Robert W | 3 | 162 | 25733
PR | 142 | 11/08/19 | 225 | McCabe, Thomas C | 32 | 1248 | 25744
PR | 142 | 11/08/19 | 235 | Roberts, Lake A | 8 | 200 | 25754
PR | 142 | 11/15/19 | 446 | Boss, Kyle A | 16 | 336 | 25781
PR | 142 | 11/15/19 | 473 | Hubbard, Robert W | 7 | 378 | 25809
PR | 142 | 11/15/19 | 484 | McCabe, Thomas C | 40 | 1560 | 25820
PR | 142 | 11/15/19 | 494 | Roberts, Lake A | 24 | 600 | 25830
PR | 142 | 11/22/19 | 616 | Boss, Benjamin T | 4 | 64 | 25856
PR | 142 | 11/22/19 | 644 | Hubbard, Robert W | 2 | 108 | 25884
PR | 142 | 11/22/19 | 655 | McCabe, Thomas C | 17 | 663 | 25895
PR | 142 | 12/20/19 | 579 | Hubbard, Robert W | 1 | 54 | 26268
PR | 142 | 01/31/20 | 892 | Roberts, Lake A | 8 | 200 | 26753
PR | 142 | 02/07/20 | 61 | Hubbard, Robert W | 5 | 270 | 26809
PR | 142 | 02/14/20 | 271 | Hubbard, Robert W | 6 | 324 | 26887
PR | 142 | 05/08/20 | 188 | Hubbard, Robert W | 4 | 216 | 27743
PR | 142 | 06/19/20 | 399 | Hubbard, Robert W | 3 | 162 | 28176
PR | 143 | 09/27/19 | 686 | Roberts, Lake A | 4 | 88 | 25291
PR | 143 | 09/27/19 | 704 | Wilson, Garret A | 4 | 160 | 25309
PR | 143 | 11/08/19 | 186 | Boss, Kyle A | 8 | 168 | 25705
GL | 210 | 10/16/18 | 357 | Req 4713 |  | 151.96
GL | 210 | 10/31/18 | 879 | Req 5503 |  | 168.61
AP | 210 | 11/05/18 | 145 | Rosen Supply Kirkland |  | 7219.69 | 4257681-00
AP | 210 | 11/05/18 | 152 | Core & Main LP $HD Supply Waterworks |  | 375.78 | J719321
AP | 210 | 11/13/18 | 419 | Rosen Supply Kirkland |  | 93.05 | 4258692-00
AP | 210 | 11/19/18 | 612 | Rosen Supply Kirkland |  | 40.86 | 4258851-00
AP | 210 | 11/21/18 | 706 | Rosen Supply Kirkland |  | 62.18 | 4259146-00
AP | 210 | 11/30/18 | 911 | Core & Main LP $HD Supply Waterworks |  | 125.26 | J783595
AP | 210 | 11/30/18 | 1022 | Rosen Supply Kirkland |  | 777.31 | 4259382-00
AP | 210 | 11/30/18 | 1058 | Rosen Supply Kirkland |  | 133.71 | 4259416-00
AP | 210 | 12/14/18 | 392 | Rosen Supply Kirkland |  | 336.43 | 4259654-00
AP | 210 | 12/17/18 | 427 | Rosen Supply Kirkland |  | 279.96 | 4259992-00
GL | 211 | 11/30/18 | 978 | Req 5580 |  | 151.75
GL | 211 | 01/23/19 | 678 | Req 4968 |  | 3.7
GL | 211 | 02/08/19 | 280 | Req 5692 |  | 958.45
GL | 211 | 03/08/19 | 375 | Req 5784 |  | 269.82
GL | 211 | 03/25/19 | 812 | Req 5105 |  | 35
AP | 211 | 04/03/19 | 65 | Rosen Supply Kirkland |  | 4790.37 | 4264657-00
GL | 211 | 04/08/19 | 219 | Req 5120 |  | 380
GL | 211 | 04/08/19 | 227 | Req 5848 |  | 471.32
GL | 211 | 04/30/19 | 887 | Req 5170 |  | 33
GL | 211 | 04/30/19 | 908 | Req 5184 |  | 593.4
AP | 211 | 05/02/19 | 139 | Rosen Supply Kirkland |  | 909.88 | 4265892-00
AP | 211 | 05/02/19 | 140 | Rosen Supply Kirkland |  | 423.1 | 4266036-00
AP | 211 | 05/15/19 | 366 | Rosen Supply Kirkland |  | 985.5 | 4266504-00
AP | 211 | 05/28/19 | 728 | Rosen Supply Kirkland |  | 114.43 | 4266806-00
GL | 211 | 05/30/19 | 873 | Req 5208 |  | 204
GL | 211 | 06/05/19 | 110 | Req 5249 |  | 250
AP | 211 | 07/16/19 | 439 | Rosen Supply Kirkland |  | 95.07 | 4269385-00
GL | 211 | 08/01/19 | 126 | Req 6198 |  | 229.5
GL | 211 | 08/08/19 | 234 | Req 6183 |  | 143
GL | 211 | 09/16/19 | 380 | Req 6351 |  | 75.63
AP | 211 | 10/07/19 | 135 | Rosen Supply Kirkland |  | 144.23 | 4272781-00
GL | 211 | 11/11/19 | 302 | Req 6499 |  | 466.28
GL | 211 | 11/12/19 | 355 | Req 6506 |  | -17.3
AP | 211 | 11/12/19 | 385 | Rosen Supply Kirkland |  | 40.67 | 4273787-00
AP | 211 | 11/16/19 | 529 | Rosen Supply Kirkland |  | 15.42 | 4273832-00
GL | 211 | 11/19/19 | 577 | Req 6586 |  | 39.2
GL | 211 | 12/06/19 | 168 | Req 6601 |  | -86.25
GL | 211 | 12/09/19 | 196 | Req 6657 |  | -106.56
AP | 211 | 12/10/19 | 266 | Rosen Supply Kirkland |  | 95.99 | 4275272-00
AP | 211 | 12/13/19 | 524 | Rosen Supply Kirkland |  | 69.6 | 4275688-00
GL | 211 | 12/20/19 | 635 | Req 6707 |  | -72.95
GL | 211 | 12/27/19 | 807 | Req 6726 |  | 26.21
GL | 211 | 01/10/20 | 371 | Req 5732 |  | -371.3
AP | 211 | 01/10/20 | 455 | Rosen Supply Kirkland |  | 102.2 | 4277092-00
GL | 211 | 02/18/20 | 373 | Req 6820 |  | -1116.59
GL | 211 | 02/18/20 | 374 | Req 6821 |  | -561.45
GL | 211 | 02/18/20 | 393 | Req 6793 |  | -41.64
GL | 211 | 02/18/20 | 394 | Req 6792 |  | -34.56
GL | 211 | 05/29/20 | 667 | Req 7059 |  | -213.13
GL | 211 | 05/31/20 | 691 | Req 7046 |  | 12.81
GL | 211 | 05/31/20 | 702 | Req 7064 |  | -55.23
GL | 211 | 06/24/20 | 478 | Req 7121 |  | -67.31
GL | 212 | 11/26/18 | 751 | Req 5523 |  | 3403.91
GL | 212 | 11/30/18 | 976 | Req 5578 |  | 188.6
GL | 212 | 12/21/18 | 636 | Req 5599 |  | 5723.51
AP | 212 | 12/21/18 | 664 | Consolidated Supply Co. |  | 1713.32 | S9039684.001
GL | 212 | 02/08/19 | 282 | Req 5690 |  | 1951.66
GL | 212 | 02/14/19 | 406 | Robert Hubbard |  | 18.15
AP | 212 | 02/19/19 | 546 | Keller Supply Company |  | 82.38 | S012730007.001
GL | 212 | 03/04/19 | 154 | Req 5016 |  | 247.64
GL | 212 | 03/08/19 | 374 | Req 5785 |  | 336.12
GL | 212 | 12/06/19 | 166 | Req 6600 |  | -62.8
GL | 212 | 05/31/20 | 700 | Req 7066 |  | -50.28
GL | 220 | 11/09/18 | 320 | Req 4757 |  | 66.34
GL | 220 | 11/09/18 | 327 | Req 4787 |  | 239.11
GL | 220 | 11/30/18 | 977 | Req 5579 |  | 277.69
GL | 220 | 12/21/18 | 637 | Req 5600 |  | 274.31
GL | 220 | 01/11/19 | 311 | Req 4889 |  | 297
GL | 220 | 01/11/19 | 359 | Req 4910 |  | -207.9
AP | 220 | 01/21/19 | 606 | Rosen Supply Kirkland |  | 14213.67 | 4259547-00
GL | 220 | 01/25/19 | 814 | Orlando Paco Leyva |  | 20.8
GL | 220 | 03/04/19 | 141 | Req 5022 |  | 2061.04
AP | 220 | 03/19/19 | 661 | Rosen Supply Kirkland |  | 3626.72 | 4261933-00
GL | 220 | 03/25/19 | 811 | Req 5106 |  | 161.29
AP | 220 | 03/31/19 | 1039 | Capital One Credit Card |  | 155.97 | 031519R
GL | 220 | 04/08/19 | 218 | Req 5121 |  | 169.99
GL | 220 | 04/12/19 | 418 | Req 5889 |  | 263.35
GL | 220 | 04/30/19 | 888 | Req 5169 |  | 140.25
AP | 220 | 04/30/19 | 923 | Consolidated Supply Co. |  | 4924.64 | S8833339.001
AP | 220 | 05/10/19 | 283 | Rosen Supply Kirkland |  | 235.88 | 4266232-00
GL | 220 | 05/13/19 | 300 | Req 5191 |  | 557.76
AP | 220 | 05/13/19 | 326 | Rosen Supply Kirkland |  | 262.45 | 4266353-00
AP | 220 | 05/15/19 | 365 | Rosen Supply Kirkland |  | 141.53 | 4266232-01
AP | 220 | 05/28/19 | 727 | Rosen Supply Kirkland |  | 1441.44 | 4266727-00
AP | 220 | 05/28/19 | 731 | Rosen Supply Kirkland |  | 311.6 | 4266853-00
AP | 220 | 05/28/19 | 743 | Rosen Supply Kirkland |  | 95.53 | 42667257-01
AP | 220 | 05/29/19 | 777 | Rosen Supply Kirkland |  | 4802.8 | 4267192-00
GL | 220 | 06/05/19 | 109 | Req 5248 |  | 2693.63
AP | 220 | 06/05/19 | 175 | Rosen Supply Kirkland |  | 285.39 | 4267309-00
AP | 220 | 06/08/19 | 290 | Rosen Supply Kirkland |  | 238 | 4267641-00
AP | 220 | 06/08/19 | 312 | Rosen Supply Kirkland |  | 122.31 | 4267309-01
AP | 220 | 06/08/19 | 313 | Rosen Supply Kirkland |  | 451.89 | 4268162-00
AP | 220 | 06/11/19 | 396 | Consolidated Supply Co. |  | 5276.44 | S9277625.001
AP | 220 | 06/12/19 | 443 | Rosen Supply Kirkland |  | 389.5 | 4268391-00
AP | 220 | 06/12/19 | 444 | Rosen Supply Kirkland |  | 3136.8 | 4268428-00
AP | 220 | 06/13/19 | 539 | Rosen Supply Kirkland |  | 346.6 | 4268361-00
AP | 220 | 06/13/19 | 540 | Rosen Supply Kirkland |  | 219 | 4268361-01
AP | 220 | 06/17/19 | 570 | Consolidated Supply Co. |  | 982.77 | S9292979.001
AP | 220 | 06/18/19 | 598 | Rosen Supply Kirkland |  | 1934.1 | 4268642-00
AP | 220 | 06/21/19 | 712 | Rosen Supply Kirkland |  | 74.76 | 4268742-00
AP | 220 | 06/21/19 | 713 | Rosen Supply Kirkland |  | 38.21 | 4268162-01
AP | 220 | 06/24/19 | 758 | Consolidated Supply Co. |  | 2862.01 | S833749.001
GL | 220 | 07/10/19 | 204 | Req 6112 |  | 898.34
AP | 220 | 07/15/19 | 403 | Rosen Supply Kirkland |  | -27.37 | 4269394-00
AP | 220 | 07/16/19 | 440 | Rosen Supply Kirkland |  | 220.36 | 4269582-00
AP | 220 | 07/17/19 | 499 | Rosen Supply Kirkland |  | 687.51 | 4269764-00
AP | 220 | 07/30/19 | 707 | Rosen Supply Kirkland |  | 495 | 4269965-00
GL | 220 | 08/01/19 | 125 | Req 6199 |  | -990
AP | 220 | 08/08/19 | 201 | Rosen Supply Kirkland |  | 319 | 4270279-00
GL | 220 | 08/08/19 | 233 | Req 6182 |  | 665.24
AP | 220 | 08/12/19 | 479 | Consolidated Supply Co. |  | 540.98 | S009364656.001
AP | 220 | 08/12/19 | 494 | Rosen Supply Kirkland |  | 1431.91 | 4270540-00
AP | 220 | 08/13/19 | 508 | Consolidated Supply Co. |  | 1875.83 | S009340794.001
AP | 220 | 08/14/19 | 537 | Rosen Supply Kirkland |  | 69.8 | 4270715-00
AP | 220 | 08/14/19 | 550 | Rosen Supply Kirkland |  | 272.2 | 4270540-01
GL | 220 | 08/20/19 | 708 | Req 6244 |  | 546.1
GL | 220 | 08/20/19 | 709 | Req 6244 |  | 546.1
AP | 220 | 08/28/19 | 962 | Rosen Supply Kirkland |  | 265.23 | 4271055-00
AP | 220 | 08/28/19 | 974 | Rosen Supply Kirkland |  | 151.55 | 4271169-00
GL | 220 | 09/16/19 | 377 | Req 6347 |  | 1212.42
AP | 220 | 09/23/19 | 578 | Consolidated Supply Co. |  | 823.5 | S009426862.001
AP | 220 | 10/07/19 | 127 | Consolidated Supply Co. |  | 49.95 | S009426862.002
GL | 220 | 10/16/19 | 439 |  |  | 22.08
AP | 220 | 11/06/19 | 170 | Rosen Supply Kirkland |  | 175.4 | 4273390-00
GL | 220 | 11/11/19 | 303 | Req 6498 |  | 113.67
GL | 220 | 11/11/19 | 304 | Req 6497 |  | 7823.85
GL | 220 | 11/11/19 | 310 | Req 6494 |  | -396
GL | 220 | 11/12/19 | 356 | Req 6505 |  | -109.23
GL | 220 | 11/12/19 | 357 | Req 6504 |  | -13945.82
AP | 220 | 11/12/19 | 361 | Rosen Supply Kirkland |  | 94.9 | 4273475-00
AP | 220 | 11/12/19 | 381 | Consolidated Supply Co. |  | 119.97 | S009502037.001
GL | 220 | 11/13/19 | 428 | Req 6525 |  | 534.68
AP | 220 | 11/16/19 | 534 | Rosen Supply Kirkland |  | 8.5 | 4273947-00
AP | 220 | 11/20/19 | 589 | Rosen Supply Kirkland |  | 28.35 | 4274245-00
AP | 220 | 11/22/19 | 706 | Rosen Supply Kirkland |  | 29.52 | 4274492-00
AP | 220 | 11/22/19 | 724 | Rosen Supply Kirkland |  | 124.52 | 4274596-00
GL | 220 | 11/30/19 | 943 | Req 6524 |  | -106.3
AP | 220 | 11/30/19 | 965 | Consolidated Supply Co. |  | 56.1 | S009509975.001
GL | 220 | 12/06/19 | 149 | Req 6635 |  | 18.39
GL | 220 | 12/06/19 | 160 | Req 6596 |  | -980.5
GL | 220 | 12/06/19 | 162 | Req 6605 |  | -8.81
GL | 220 | 12/06/19 | 169 | Req 6598 |  | -1984.99
GL | 220 | 12/09/19 | 197 | Req 6658 |  | -889.42
AP | 220 | 12/10/19 | 220 | Rosen Supply Kirkland |  | 159.55 | 4275098-00
AP | 220 | 12/12/19 | 515 | Consolidated Supply Co. |  | 70.89 | S009502037.002
GL | 220 | 12/20/19 | 633 | Req 6668 |  | -10.71
GL | 220 | 12/20/19 | 634 | Req 6706 |  | -278.55
GL | 220 | 01/07/20 | 158 | Req 6731 |  | 41.58
AP | 220 | 01/08/20 | 202 | Capital One Credit Card |  | 32.77 | 110819BH
AP | 220 | 01/08/20 | 269 | Rosen Supply Kirkland |  | 10.08 | 4277146-00
AP | 220 | 01/10/20 | 424 | Capital One Credit Card |  | 8.68 | 010620RH
AP | 220 | 01/13/20 | 502 | Consolidated Supply Co. |  | 33.66 | S009594324.001
GL | 220 | 01/31/20 | 922 | Req 6659 |  | -777.92
GL | 220 | 02/24/20 | 558 | Req 6829 |  | -3229.23
AP | 220 | 02/29/20 | 804 | Rosen Supply Kirkland |  | 34.1 | 4279109-00
GL | 220 | 03/04/20 | 22 | Req 6822 |  | -410.17
GL | 220 | 05/26/20 | 570 | Req 6999 |  | 59.16
GL | 220 | 05/27/20 | 574 | Req 7043 |  | -36.29
GL | 220 | 05/29/20 | 668 | Req 7055 |  | -279.26
GL | 220 | 05/29/20 | 669 | Req 7056 |  | -904.43
GL | 220 | 05/29/20 | 670 | Req 7057 |  | -271.89
GL | 220 | 05/31/20 | 692 | Req 7047 |  | 22.92
GL | 220 | 05/31/20 | 705 | Req 7061 |  | -107.31
GL | 220 | 06/22/20 | 443 | Req 7117 |  | -136.74
GL | 220 | 07/16/20 | 317 | Req 6244 Adj |  | -546.1
AP | 230 | 10/16/18 | 654 | Quality Concrete Products, Inc. $32 |  | 1548 | 56217
GL | 230 | 10/31/18 | 880 | Req 5502 |  | 355.94
AP | 230 | 11/05/18 | 163 | Quality Concrete Products, Inc. $32 |  | 1616 | 56218
GL | 230 | 11/09/18 | 328 | Req 4788 |  | 818.8
GL | 230 | 11/26/18 | 752 | Req 5524 |  | 456.38
AP | 230 | 12/14/18 | 359 | Keller Supply Company |  | 896.91 | S012471316.001
GL | 230 | 12/21/18 | 605 | Req 5631 |  | 125.82
AP | 230 | 01/21/19 | 605 | Rosen Supply Kirkland |  | 4113.75 | 4253946-00
GL | 230 | 01/23/19 | 679 | Req 4967 |  | 83.88
AP | 230 | 01/30/19 | 903 | Mechanical Sales, Inc. |  | 290.58 | 700000
GL | 230 | 02/08/19 | 281 | Req 5691 |  | 677.95
AP | 230 | 02/27/19 | 753 | Rosen Supply Kirkland |  | 296.78 | 4253946-01
GL | 230 | 04/08/19 | 217 | Req 5122 |  | 374.75
GL | 230 | 04/12/19 | 417 | Req 5890 |  | 234.92
AP | 230 | 05/21/19 | 532 | Keller Supply Company |  | 7306.42 | S012923074.001
GL | 230 | 05/30/19 | 875 | Req 5206 |  | 2752.3
AP | 230 | 06/24/19 | 724 | California Hydronics Corp |  | 57789 | SIN020068
AP | 230 | 07/15/19 | 402 | Rosen Supply Kirkland |  | 161.28 | 4269273-00
AP | 230 | 08/06/19 | 166 | Ferguson Enterprises, Inc. #3007 |  | 2027.8 | 7045682
AP | 230 | 08/06/19 | 167 | Ferguson Enterprises, Inc. #3007 |  | 12166.85 | 7045771
AP | 230 | 08/06/19 | 168 | Ferguson Enterprises, Inc. #3007 |  | 2365.78 | 7045786
AP | 230 | 08/06/19 | 169 | Ferguson Enterprises, Inc. #3007 |  | 13518.72 | 7045811
GL | 230 | 08/08/19 | 235 | Req 6184 |  | 1160.96
AP | 230 | 08/15/19 | 768 | Ferguson Enterprises, Inc. #3007 |  | 11152.95 | 7045786-1
AP | 230 | 08/21/19 | 774 | Ferguson Enterprises, Inc. #3007 |  | 12166.84 | 7045830
AP | 230 | 08/21/19 | 775 | Ferguson Enterprises, Inc. #3007 |  | 13518.72 | 7045902
AP | 230 | 09/10/19 | 177 | Ruvita USA, Inc. |  | 3600 | RVM4250-1
GL | 230 | 09/16/19 | 376 | Req 6346 |  | 2079
GL | 230 | 09/16/19 | 379 | Req 6350 |  | 196.05
GL | 230 | 11/11/19 | 306 | Req 6490 |  | 7936.84
GL | 230 | 11/11/19 | 307 | Req 6491 |  | 1367.87
AP | 230 | 11/11/19 | 331 | Ferguson Enterprises, Inc. #3007 |  | 1351.87 | 7045830-1
GL | 230 | 11/12/19 | 353 | Req 6508 |  | -428.96
GL | 230 | 11/13/19 | 427 | Req 6529 |  | 392
AP | 230 | 11/21/19 | 784 | Capital One Credit Card |  | 5990 | 102119R2
AP | 230 | 11/22/19 | 715 | Ruvita USA, Inc. |  | 3600 | RVM4250-2
AP | 230 | 11/30/19 | 971 | Ferguson Enterprises, Inc. #3007 |  | 939.05 | 7712918
GL | 230 | 12/06/19 | 148 | Req 6634 |  | 1525.91
GL | 230 | 12/06/19 | 151 | Req 6624 |  | -15.6
GL | 230 | 12/06/19 | 167 | Req 6599 |  | -286.56
GL | 230 | 12/09/19 | 179 | Req 6641 |  | 117.74
GL | 230 | 12/09/19 | 195 | Req 6663 |  | -3.82
AP | 230 | 12/11/19 | 367 | Consolidated Supply Co. |  | 1140 | S9294947.001
AP | 230 | 12/12/19 | 494 | Keller Supply Company |  | 2777.12 | S013154764.001
AP | 230 | 12/12/19 | 495 | Keller Supply Company |  | 2777.12 | S013155021.001
AP | 230 | 12/12/19 | 496 | Keller Supply Company |  | 2777.12 | S013155042.001
AP | 230 | 12/12/19 | 497 | Keller Supply Company |  | 1023.02 | S013687224.001
GL | 230 | 12/20/19 | 632 | Req 6669 |  | -46.46
GL | 230 | 12/27/19 | 805 | Req 6723 |  | 3227.07
AP | 230 | 12/27/19 | 824 | Keller Supply Company |  | 159.41 | S013154764.002
AP | 230 | 12/27/19 | 825 | Keller Supply Company |  | 9180.81 | S013154764.003
AP | 230 | 01/06/20 | 131 | Consolidated Supply Co. |  | 1140 | S9294947.002
AP | 230 | 01/07/20 | 175 | Keller Supply Company |  | 2499.41 | S013155062.001
AP | 230 | 01/07/20 | 176 | Keller Supply Company |  | 2777.12 | S013155051.001
AP | 230 | 01/07/20 | 177 | Keller Supply Company |  | 416.57 | S013155514.001
AP | 230 | 01/08/20 | 203 | Capital One Credit Card |  | 31.38 | 112319BH
AP | 230 | 01/13/20 | 508 | Keller Supply Company |  | 9340.21 | S013155021.002
AP | 230 | 01/29/20 | 817 | Consolidated Supply Co. |  | 3480 | S9294947.003
AP | 230 | 01/29/20 | 829 | Keller Supply Company |  | 9340.21 | S013155042.002
AP | 230 | 01/31/20 | 917 | Ruvita USA, Inc. |  | 24400 | RV2492259
AP | 230 | 02/10/20 | 137 | Consolidated Supply Co. |  | 210 | S009617842.001
AP | 230 | 02/10/20 | 184 | Keller Supply Company |  | 9340.21 | S013155051.002
AP | 230 | 02/10/20 | 185 | Keller Supply Company |  | 10434.48 | S013155062.002
AP | 230 | 02/11/20 | 214 | Rosen Supply Kirkland |  | 141.95 | 4277773-00
GL | 230 | 02/18/20 | 390 | Req 6773 |  | 2916.77
AP | 230 | 02/26/20 | 664 | Rosen Supply Kirkland |  | 177 | 4278993-00
AP | 230 | 02/29/20 | 805 | Rosen Supply Kirkland |  | 147.48 | 4279351-00
AP | 230 | 03/03/20 | 4 | Keller Supply Company |  | 662 | S013155062.003
GL | 230 | 03/04/20 | 23 | Req 6850 |  | 1564.56
GL | 230 | 03/10/20 | 244 | Req 6883 |  | 147.53
GL | 230 | 03/13/20 | 394 | Req 6897 |  | -24.14
AP | 230 | 03/16/20 | 436 | Keller Supply Company |  | 3105.89 | S013155514.002
AP | 230 | 03/18/20 | 546 | Rosen Supply Kirkland |  | 35.5 | 4278993-01
AP | 230 | 03/18/20 | 547 | Rosen Supply Kirkland |  | 24.14 | 4279351-01
GL | 230 | 03/20/20 | 684 | Req 6709 |  | -308.57
AP | 230 | 03/27/20 | 853 | Rosen Supply Kirkland |  | 5.36 | 4279351-02
AP | 230 | 03/27/20 | 866 | Rosen Supply Kirkland |  | 171.5 | 4280558-00
AP | 230 | 03/27/20 | 889 | Keller Supply Company |  | 1209.24 | S013568838.001
GL | 230 | 03/31/20 | 896 | Ruvati Return |  | -7400
AP | 230 | 04/15/20 | 187 | Capital One Credit Card |  | 10.07 | 031920A
GL | 230 | 05/05/20 | 106 | Req 6958 |  | 444.99
AP | 230 | 05/06/20 | 145 | Consolidated Supply Co. |  | -180 | S009617842.003
AP | 230 | 05/11/20 | 267 | Rosen Supply Kirkland |  | 122 | 4281443-00
AP | 230 | 05/11/20 | 268 | Rosen Supply Kirkland |  | 35.95 | 4281470-00
GL | 230 | 05/13/20 | 298 | Req 6998 |  | 373.48
AP | 230 | 05/19/20 | 416 | Keller Supply Company |  | 945.94 | S013155521.001
AP | 230 | 05/19/20 | 417 | Keller Supply Company |  | 621.78 | S014215832.001
AP | 230 | 05/19/20 | 429 | Rosen Supply Kirkland |  | 33.06 | 4281853-00
AP | 230 | 05/22/20 | 551 | Keller Supply Company |  | 230.61 | S014209601.001
AP | 230 | 05/22/20 | 556 | Rosen Supply Kirkland |  | 21.49 | 4281920-00
GL | 230 | 05/31/20 | 686 | Req 7082 |  | 568.24
GL | 230 | 05/31/20 | 689 | Req 7044 |  | 525.81
GL | 230 | 05/31/20 | 706 | Req 7060 |  | -356.87
AP | 230 | 05/31/20 | 731 | Keller Supply Company |  | 9.33 | S014259883.001
AP | 230 | 05/31/20 | 738 | Rosen Supply Kirkland |  | 166.35 | 4282193-00
AP | 230 | 06/12/20 | 291 | Capital One Credit Card |  | 34.77 | 051820A1
AP | 230 | 06/12/20 | 292 | Capital One Credit Card |  | 15.34 | 051820A2
GL | 230 | 06/16/20 | 339 | Req 7098 |  | 7.48
GL | 230 | 06/24/20 | 477 | Req 7118 |  | -370.2
AP | 230 | 07/09/20 | 186 | Core & Main LP $HD Supply Waterworks |  | 100.97 | M538644
GL | 230 | 07/09/20 | 188 | Req 7166 |  | -173.67
GL | 230 | 07/16/20 | 314 | Inv 7712918 adj |  | -939.05
GL | 230 | 07/16/20 | 316 | Inv S012778828.001 |  | 591.93
AP | 240 | 06/17/19 | 553 | Consolidated Supply Co. |  | 351.6 | S9292988.001
AP | 240 | 08/05/19 | 103 | Consolidated Supply Co. |  | 683.57 | S009333827.002
AP | 240 | 08/05/19 | 104 | Consolidated Supply Co. |  | 536.34 | S009333827.003
AP | 240 | 08/05/19 | 105 | Consolidated Supply Co. |  | 1386.09 | S009333827.001
AP | 240 | 08/12/19 | 479 | Consolidated Supply Co. |  | 425.39 | S009364656.001
AP | 240 | 08/12/19 | 890 | Consolidated Supply Co. |  | 365.01 | S009385244.001
AP | 240 | 08/12/19 | 891 | Consolidated Supply Co. |  | 362.44 | S009385244.002
AP | 240 | 08/12/19 | 892 | Consolidated Supply Co. |  | 62.76 | S009385244.003
AP | 240 | 08/12/19 | 893 | Consolidated Supply Co. |  | 64.74 | S009385244.004
AP | 240 | 08/28/19 | 948 | Consolidated Supply Co. |  | 131.27 | S009396460.001
AP | 240 | 08/28/19 | 949 | Consolidated Supply Co. |  | 75.04 | S009396460.002
AP | 240 | 09/06/19 | 119 | Consolidated Supply Co. |  | 35.52 | S009406261.001
AP | 240 | 09/09/19 | 125 | Rosen Supply Kirkland |  | 26.87 | 4271844-00
AP | 240 | 09/18/19 | 464 | Consolidated Supply Co. |  | 247.17 | S009416705.001
AP | 240 | 09/23/19 | 582 | Rosen Supply Kirkland |  | 121.39 | 4271972-00
AP | 240 | 09/23/19 | 594 | Rosen Supply Kirkland |  | 24.72 | 4271844-02
AP | 240 | 09/23/19 | 595 | Rosen Supply Kirkland |  | 423.62 | 4272126-00
AP | 240 | 09/25/19 | 619 | Rosen Supply Kirkland |  | 129.04 | 4272400-00
AP | 240 | 09/30/19 | 754 | Rosen Supply Kirkland |  | 30.83 | 4272126-01
GL | 240 | 10/07/19 | 102 | Req 6387 |  | 541.86
AP | 240 | 10/07/19 | 134 | Rosen Supply Kirkland |  | 75.22 | 4272763-00
AP | 240 | 10/11/19 | 363 | Ferguson Enterprises, Inc. #3007 |  | 184.67 | 7546878
AP | 240 | 10/16/19 | 441 | Rosen Supply Kirkland |  | 203.02 | 4273192-00
AP | 240 | 11/01/19 | 103 | Keller Supply Company |  | 152.92 | S013545033.001
AP | 240 | 11/06/19 | 168 | Keller Supply Company |  | 11.86 | S013553695.001
GL | 240 | 11/11/19 | 300 | Req 6502 |  | 315.36
GL | 240 | 11/12/19 | 352 | Req 6509 |  | -15.29
AP | 240 | 11/12/19 | 385 | Rosen Supply Kirkland |  | 60.39 | 4273787-00
GL | 240 | 11/13/19 | 422 | Req 6534 |  | 700.48
AP | 240 | 11/16/19 | 536 | Rosen Supply Kirkland |  | 40.89 | 4273992-00
GL | 240 | 11/30/19 | 949 | Req 6501 |  | 839.9
GL | 240 | 11/30/19 | 952 | Req 6526 |  | 173.99
GL | 240 | 12/09/19 | 192 | Req 6666 |  | -125.02
GL | 240 | 12/09/19 | 198 | Req 6660 |  | -1656.78
AP | 240 | 12/13/19 | 520 | Rosen Supply Kirkland |  | 140.97 | 4275752-00
GL | 240 | 12/27/19 | 786 | Req 6667 |  | -109.48
GL | 240 | 12/27/19 | 806 | Req 6724 |  | 3.04
AP | 240 | 12/31/19 | 864 | Rosen Supply Kirkland |  | 7.8 | 4275751-01
GL | 240 | 01/31/20 | 921 | Req 6754 |  | -845.17
AP | 240 | 03/03/20 | 5 | Rosen Supply Kirkland |  | 58.74 | 4279453-00
GL | 240 | 03/13/20 | 395 | Req 6896 |  | -15.26
AP | 240 | 03/18/20 | 548 | Rosen Supply Kirkland |  | 16.5 | 4279453-01
AP | 240 | 05/13/20 | 304 | Rosen Supply Kirkland |  | 199.66 | 4281645-00
AP | 240 | 05/22/20 | 555 | Rosen Supply Kirkland |  | 20.57 | 4281645-01
AP | 240 | 05/22/20 | 557 | Rosen Supply Kirkland |  | 79.41 | 4281944-00
GL | 240 | 05/31/20 | 690 | Req 7045 |  | 9.3
GL | 240 | 05/31/20 | 703 | Req 7063 |  | -88.81
GL | 240 | 05/31/20 | 704 | Req 7062 |  | -178.36
AP | 240 | 05/31/20 | 737 | Rosen Supply Kirkland |  | 81.8 | 4282189-00
AP | 240 | 05/31/20 | 739 | Rosen Supply Kirkland |  | 4.4 | 4282247-00
GL | 240 | 06/18/20 | 367 | Req 7110 |  | -32.72
GL | 240 | 06/24/20 | 476 | Req 7119 |  | -184.22
AP | 240 | 06/24/20 | 493 | Rosen Supply Kirkland |  | 32.72 | 4282189-01
GL | 240 | 07/09/20 | 189 | Req 7165 |  | -140.44
GL | 240 | 07/16/20 | 313 | Req 6660 Adj |  | -1656.78
GL | 240 | 07/16/20 | 314 | Inv 7712918 adj |  | 939.05
GL | 240 | 07/16/20 | 315 | Inv 4282337-00 adj |  | 11.84
GL | 241 | 12/21/18 | 606 | Req 5632 |  | 122.01
GL | 241 | 01/11/19 | 358 | Req 4911 |  | -840
GL | 241 | 04/12/19 | 419 | Req 5888 |  | 442.7
AP | 241 | 04/15/19 | 463 | Consolidated Supply Co. |  | 4501.52 | S9188254.001
AP | 241 | 04/15/19 | 464 | Consolidated Supply Co. |  | 1444.32 | S9188254.002
AP | 241 | 04/23/19 | 653 | Consolidated Supply Co. |  | 1882.8 | S9202472.001
GL | 241 | 04/30/19 | 889 | Req 5168 |  | 430.62
AP | 241 | 04/30/19 | 921 | Consolidated Supply Co. |  | 722.16 | S9188254.003
AP | 241 | 04/30/19 | 922 | Consolidated Supply Co. |  | 541.62 | S9188254.004
AP | 241 | 04/30/19 | 924 | Consolidated Supply Co. |  | 6138.41 | S9225171.001
AP | 241 | 05/22/19 | 572 | Consolidated Supply Co. |  | 553.5 | S9233605.001
AP | 241 | 05/22/19 | 573 | Consolidated Supply Co. |  | 756.88 | S9225171.002
AP | 241 | 05/22/19 | 574 | Consolidated Supply Co. |  | 184.5 | S9233605.002
AP | 241 | 05/23/19 | 590 | Consolidated Supply Co. |  | 2415.57 | S9248676.001
AP | 241 | 05/23/19 | 591 | Consolidated Supply Co. |  | 589.81 | S9252063.001
GL | 241 | 05/30/19 | 874 | Req 5207 |  | 629.27
AP | 241 | 06/03/19 | 14 | Consolidated Supply Co. |  | 2190.3 | S9259280.001
AP | 241 | 06/03/19 | 15 | Consolidated Supply Co. |  | 2015.46 | S9265077.001
AP | 241 | 06/03/19 | 16 | Consolidated Supply Co. |  | 682.43 | S9269536.001
GL | 241 | 06/05/19 | 111 | Req 5250 |  | 291.14
AP | 241 | 06/11/19 | 395 | Consolidated Supply Co. |  | 1263.78 | S9265077.002
AP | 241 | 06/11/19 | 405 | Consolidated Supply Co. |  | 1991.32 | S9282274.001
AP | 241 | 06/18/19 | 586 | Consolidated Supply Co. |  | 734.37 | S009296618.001
AP | 241 | 06/18/19 | 587 | Consolidated Supply Co. |  | 168.3 | S009296618.002
AP | 241 | 06/24/19 | 759 | Consolidated Supply Co. |  | 1163.83 | S009311136.001
GL | 241 | 07/10/19 | 201 | Req 6113 |  | 953.15
AP | 241 | 08/07/19 | 182 | Consolidated Supply Co. |  | 929.1 | S009352822.001
GL | 241 | 08/08/19 | 236 | Req 6185 |  | 26.4
GL | 241 | 08/08/19 | 237 | Req 6185 |  | 26.4
AP | 241 | 08/10/19 | 433 | Consolidated Supply Co. |  | 336.86 | S009356389.001
AP | 241 | 08/26/19 | 931 | Consolidated Supply Co. |  | 225.15 | S009389627.001
AP | 241 | 08/28/19 | 948 | Consolidated Supply Co. |  | 393.11 | S009396460.001
AP | 241 | 09/06/19 | 119 | Consolidated Supply Co. |  | 216.2 | S009406261.001
GL | 241 | 09/16/19 | 378 | Req 6349 |  | 734.77
AP | 241 | 09/18/19 | 465 | Consolidated Supply Co. |  | 387.21 | S009418747.001
AP | 241 | 10/08/19 | 170 | Consolidated Supply Co. |  | 33.66 | S009450469.001
AP | 241 | 10/15/19 | 418 | Rosen Supply Kirkland |  | 1702.56 | 4272956-00
GL | 241 | 11/12/19 | 351 | Req 6510 |  | -1751.44
GL | 241 | 11/12/19 | 354 | Req 6507 |  | -878.8
GL | 241 | 11/13/19 | 420 | Req 6536 |  | 1814.38
GL | 241 | 11/13/19 | 421 | Req 6535 |  | 3783.52
GL | 241 | 11/13/19 | 430 | Req 6528 |  | 335.89
AP | 241 | 11/16/19 | 531 | Rosen Supply Kirkland |  | 1494 | 4272956-01
AP | 241 | 11/16/19 | 533 | Rosen Supply Kirkland |  | 454.26 | 4273940-00
GL | 241 | 11/19/19 | 579 | Req 6584 |  | 165.64
GL | 241 | 12/06/19 | 150 | Req 6625 |  | 361.68
GL | 241 | 12/06/19 | 161 | Req 6606 |  | -5.28
GL | 241 | 12/09/19 | 180 | Req 6642 |  | 189.7
GL | 241 | 12/09/19 | 199 | Req 6661 |  | -3366.2
GL | 241 | 12/09/19 | 200 | Req 6662 |  | -848.36
AP | 241 | 12/09/19 | 208 | Rosen Supply Kirkland |  | 1475.04 | 4274529-00
AP | 241 | 12/09/19 | 209 | Rosen Supply Kirkland |  | 266.22 | 4274898-00
GL | 241 | 12/20/19 | 636 | Req 6705 |  | -2439.61
GL | 241 | 12/27/19 | 811 | Req 6728 |  | -802.6
AP | 241 | 03/03/20 | 14 | Consolidated Supply Co. |  | 224.6 | S009661546.001
AP | 241 | 03/11/20 | 289 | Consolidated Supply Co. |  | 128.34 | S009669887.001
AP | 241 | 03/11/20 | 290 | Consolidated Supply Co. |  | -115.51 | S009669887.002
AP | 241 | 03/11/20 | 291 | Consolidated Supply Co. |  | 121.92 | S009669887.003
GL | 241 | 05/29/20 | 671 | Req 7058 |  | -168.2
AP | 241 | 06/09/20 | 144 | Rosen Supply Kirkland |  | 11.84 | 4282337-00
GL | 241 | 06/26/20 | 575 | Req 7129 |  | 221.19
GL | 241 | 07/16/20 | 313 | Req 6660 Adj |  | 1656.78
GL | 241 | 07/16/20 | 315 | Inv 4282337-00 adj |  | -11.84
GL | 241 | 07/16/20 | 318 | Req 6185 adj |  | -26.4
AP | 242 | 08/31/19 | 1105 | Rosen Supply Kirkland |  | 925.17 | 4271783-00
AP | 242 | 08/31/19 | 1130 | Ferguson Enterprises, Inc. #3007 |  | 6918.28 | 7471227
AP | 242 | 09/27/19 | 722 | Rosen Supply Kirkland |  | 139.2 | 4271783-01
AP | 242 | 10/01/19 | 235 | Capital One Credit Card |  | 14.87 | 100119BH1
AP | 242 | 10/01/19 | 236 | Capital One Credit Card |  | 15.42 | 100119BH2
AP | 242 | 10/08/19 | 157 | Consolidated Supply Co. |  | 717.72 | S00944277.001
AP | 242 | 10/08/19 | 168 | Consolidated Supply Co. |  | 3641.24 | S009379673.001
AP | 242 | 10/08/19 | 169 | Consolidated Supply Co. |  | 1306.2 | S009379673.002
AP | 242 | 10/08/19 | 171 | Consolidated Supply Co. |  | 663.95 | S009440277.002
AP | 242 | 10/25/19 | 759 | Ferguson Enterprises, Inc. #3007 |  | 523.28 | 7610265
AP | 242 | 10/29/19 | 726 | Consolidated Supply Co. |  | 315.71 | S009379673.003
AP | 242 | 10/29/19 | 727 | Consolidated Supply Co. |  | 14.33 | S009379673.004
AP | 242 | 11/06/19 | 164 | Ferguson Enterprises, Inc. #3007 |  | 2043.76 | 7620656
GL | 242 | 11/11/19 | 305 | Req 6492 |  | 393.68
GL | 242 | 11/11/19 | 308 | Req 6496 |  | 1976.59
AP | 242 | 11/11/19 | 332 | Ferguson Enterprises, Inc. #3007 |  | 1193.68 | 7661386
AP | 242 | 11/12/19 | 380 | Keller Supply Company |  | 820.92 | S013586119.001
AP | 242 | 11/12/19 | 384 | Rosen Supply Kirkland |  | 22.19 | 4273686-00
GL | 242 | 11/13/19 | 429 | Req 6527 |  | 655.01
AP | 242 | 11/16/19 | 530 | Rosen Supply Kirkland |  | 154.84 | 4273861-00
AP | 242 | 11/16/19 | 532 | Rosen Supply Kirkland |  | 760.89 | 4273916-00
AP | 242 | 11/16/19 | 535 | Rosen Supply Kirkland |  | 141.55 | 4273950-00
AP | 242 | 11/22/19 | 705 | Rosen Supply Kirkland |  | 22.52 | 4273861-01
AP | 242 | 11/30/19 | 979 | Keller Supply Company |  | 410.46 | S013600613.001
AP | 242 | 11/30/19 | 980 | Keller Supply Company |  | 75.58 | S013609329.001
AP | 242 | 12/05/19 | 17 | Ferguson Enterprises, Inc. #3007 |  | 129.27 | 7689970
GL | 242 | 12/06/19 | 152 | Req 6623 |  | -936.62
GL | 242 | 12/06/19 | 159 | Req 6597 |  | 23.42
GL | 242 | 12/09/19 | 181 | Req 6643 |  | 46.31
AP | 242 | 12/10/19 | 275 | Rosen Supply Kirkland |  | 69.6 | 4275435-00
GL | 242 | 03/04/20 | 18 | Req 6704 |  | -1466.38
GL | 242 | 05/31/20 | 701 | Req 7065 |  | -118.89
GL | 242 | 06/24/20 | 475 | Req 7120 |  | -1214.38
GL | 243 | 03/08/19 | 376 | Req 5786 |  | 22.08
GL | 243 | 10/16/19 | 439 |  |  | -22.08
AP | 600 | 08/19/19 | 654 | Mechanical Firestop Services, LLC |  | 2915 | 1590-5825
AP | 600 | 10/22/19 | 561 | Mechanical Firestop Services, LLC |  | 20405 | 1590-5842
AP | 600 | 11/25/19 | 832 | Mechanical Firestop Services, LLC |  | 5830 | 1590-5853
AP | 600 | 04/21/20 | 320 | Mechanical Resource Services, Inc. |  | 1597.75 | 16823-5601
AP | 600 | 05/22/20 | 561 | Mechanical Resource Services, Inc. |  | 2967.25 | 16839-5601
AP | 601 | 03/26/18 | 648 | Franklin Engineering |  | 4338.25 | 6880
AP | 601 | 04/30/18 | 830 | Franklin Engineering |  | 3935.5 | 6918
AP | 601 | 06/04/18 | 156 | Franklin Engineering |  | 5257.25 | 6942
AP | 601 | 06/22/18 | 787 | Franklin Engineering |  | 1691.25 | 6976
AP | 601 | 07/23/18 | 608 | Franklin Engineering |  | 1743.25 | 7008
AP | 601 | 08/22/18 | 696 | Franklin Engineering |  | 137.5 | 7068
AP | 601 | 11/29/18 | 826 | Franklin Engineering |  | 578.5 | 7168
AP | 601 | 01/03/19 | 90 | Franklin Engineering |  | 1523.25 | 7189
AP | 601 | 02/27/19 | 740 | Franklin Engineering |  | 3021.5 | 7256
PR | 995 | 03/02/18 | 67 | Donelson, Richard T |  | 27.72
PR | 995 | 03/09/18 | 184 | Gerard, Jeffrey S |  | 20.84
PR | 995 | 03/23/18 | 583 | Donelson, Richard T |  | 27.72
PR | 995 | 03/23/18 | 584 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 03/30/18 | 811 | Donelson, Richard T |  | 27.72
PR | 995 | 03/30/18 | 812 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 04/27/18 | 684 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 05/11/18 | 286 | Donelson, Richard T |  | 27.72
PR | 995 | 06/08/18 | 339 | Donelson, Richard T |  | 27.72
PR | 995 | 06/15/18 | 527 | Donelson, Richard T |  | 27.72
PR | 995 | 06/22/18 | 753 | Donelson, Richard T |  | 55.44
PR | 995 | 06/29/18 | 1020 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/13/18 | 367 | Donelson, Richard T |  | 110.88
PR | 995 | 07/13/18 | 368 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/20/18 | 507 | Donelson, Richard T |  | 83.16
PR | 995 | 07/27/18 | 834 | Donelson, Richard T |  | 194.03
PR | 995 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/17/18 | 550 | Donelson, Richard T |  | 55.44
PR | 995 | 08/31/18 | 1069 | Donelson, Richard T |  | 27.72
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 09/07/18 | 105 | Donelson, Richard T |  | 277.19
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/14/18 | 340 | Donelson, Richard T |  | 110.88
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 88.7
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/21/18 | 552 | Donelson, Richard T |  | 27.72
PR | 995 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 88.7
PR | 995 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/28/18 | 739 | Donelson, Richard T |  | 83.16
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 10/05/18 | 102 | Donelson, Richard T |  | 110.88
PR | 995 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 10/12/18 | 276 | Lovo, German G |  | 234.17
PR | 995 | 10/12/18 | 286 | Quintanilla, Esteban R |  | 478.98
PR | 995 | 10/12/18 | 291 | Rivera, Eli P |  | 191.59
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 110.88
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 10/19/18 | 474 | Lovo, German G |  | 255.46
PR | 995 | 10/19/18 | 484 | Quintanilla, Esteban R |  | 598.73
PR | 995 | 10/19/18 | 489 | Rivera, Eli P |  | 287.39
PR | 995 | 10/19/18 | 507 | Donelson, Richard T |  | 27.72
PR | 995 | 10/19/18 | 508 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/19/18 | 508 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/26/18 | 703 | Ascencio, Jose L |  | 46.12
PR | 995 | 10/26/18 | 740 | Lovo, German G |  | 244.81
PR | 995 | 10/26/18 | 749 | Quintanilla, Esteban R |  | 718.47
PR | 995 | 10/26/18 | 754 | Rivera, Eli P |  | 47.9
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 88.7
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 11/02/18 | 2 | Quintanilla, Esteban R |  | 778.34
PR | 995 | 11/02/18 | 45 | Lovo, German G |  | 298.03
PR | 995 | 11/02/18 | 58 | Rivera, Eli P |  | 71.85
PR | 995 | 11/02/18 | 58 | Rivera, Eli P |  | 359.24
PR | 995 | 11/02/18 | 74 | Wilson, Garret A |  | 124.18
PR | 995 | 11/02/18 | 76 | Donelson, Richard T |  | 27.72
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/09/18 | 191 | Cornejo Orellana, Carlos E |  | 151.68
PR | 995 | 11/09/18 | 223 | Lovo, German G |  | 31.93
PR | 995 | 11/09/18 | 223 | Lovo, German G |  | 319.32
PR | 995 | 11/09/18 | 232 | Quintanilla, Esteban R |  | 798.3
PR | 995 | 11/09/18 | 232 | Quintanilla, Esteban R |  | 59.87
PR | 995 | 11/09/18 | 237 | Rivera, Eli P |  | 71.85
PR | 995 | 11/09/18 | 257 | Donelson, Richard T |  | 55.44
PR | 995 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/16/18 | 437 | Benites Portillo, Marvin E |  | 78.06
PR | 995 | 11/16/18 | 440 | Cornejo Orellana, Carlos E |  | 25.28
PR | 995 | 11/16/18 | 440 | Cornejo Orellana, Carlos E |  | 84.27
PR | 995 | 11/16/18 | 471 | Lovo, German G |  | 191.59
PR | 995 | 11/16/18 | 480 | Quintanilla, Esteban R |  | 59.87
PR | 995 | 11/16/18 | 480 | Quintanilla, Esteban R |  | 598.73
PR | 995 | 11/16/18 | 506 | Quintanilla, Esteban R |  | -59.87
PR | 995 | 11/16/18 | 506 | Quintanilla, Esteban R |  | -598.73
PR | 995 | 11/16/18 | 509 | Quintanilla, Esteban R |  | 59.87
PR | 995 | 11/16/18 | 509 | Quintanilla, Esteban R |  | 598.73
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 110.88
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/21/18 | 623 | Benites Portillo, Marvin E |  | 97.57
PR | 995 | 11/21/18 | 655 | Lovo, German G |  | 234.17
PR | 995 | 11/21/18 | 655 | Lovo, German G |  | 106.44
PR | 995 | 11/21/18 | 664 | Quintanilla, Esteban R |  | 319.32
PR | 995 | 11/21/18 | 664 | Quintanilla, Esteban R |  | 239.49
PR | 995 | 11/21/18 | 685 | Wilson, Garret A |  | 372.54
PR | 995 | 11/21/18 | 687 | Quintanilla, Esteban R |  | -319.32
PR | 995 | 11/21/18 | 687 | Quintanilla, Esteban R |  | -239.49
PR | 995 | 11/21/18 | 688 | Quintanilla, Esteban R |  | 319.32
PR | 995 | 11/21/18 | 688 | Quintanilla, Esteban R |  | 239.49
PR | 995 | 11/21/18 | 689 | Donelson, Richard T |  | 138.59
PR | 995 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/30/18 | 868 | Lovo, German G |  | 199.58
PR | 995 | 11/30/18 | 877 | Quintanilla, Esteban R |  | 270.98
PR | 995 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 12/07/18 | 44 | Ascencio, Jose L |  | 111.76
PR | 995 | 12/07/18 | 80 | Lovo, German G |  | 177.4
PR | 995 | 12/07/18 | 89 | Quintanilla, Esteban R |  | 396.05
PR | 995 | 12/07/18 | 95 | Rivera, Jorge A |  | -29.27
PR | 995 | 12/07/18 | 98 | Ross, Kelli M |  | -35.48
PR | 995 | 12/07/18 | 113 | Donelson, Richard T |  | 221.75
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 12/07/18 | 123 | Ascencio, Jose L |  | -111.76
PR | 995 | 12/07/18 | 125 | Rivera, Jorge A |  | 29.27
PR | 995 | 12/07/18 | 126 | Ross, Kelli M |  | 35.48
PR | 995 | 12/07/18 | 129 | Wilson, Garret A |  | -496.72
PR | 995 | 12/14/18 | 304 | Lovo, German G |  | 255.01
PR | 995 | 12/14/18 | 314 | Quintanilla, Esteban R |  | 104.22
PR | 995 | 12/14/18 | 334 | Waites, Thaddeus Z |  | 114.42
PR | 995 | 12/14/18 | 337 | Donelson, Richard T |  | 110.88
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/21/18 | 554 | Quintanilla, Esteban R |  | 41.69
PR | 995 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 115.31
PR | 995 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 12/28/18 | 684 | Lovo, German G |  | 55.44
PR | 995 | 12/28/18 | 768 | Donelson, Richard T |  | 27.72
PR | 995 | 12/28/18 | 769 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 01/04/19 | 72 | Donelson, Richard T |  | 55.44
PR | 995 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 01/11/19 | 281 | Donelson, Richard T |  | 83.16
PR | 995 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/18/19 | 513 | Quintanilla, Esteban R |  | 62.53
PR | 995 | 01/18/19 | 542 | Donelson, Richard T |  | 83.16
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/25/19 | 748 | Hubbard, Robert W |  | 260.78
PR | 995 | 01/25/19 | 756 | McCabe, Thomas C |  | 234.17
PR | 995 | 01/25/19 | 760 | Paco Leyva, Orlando |  | 147.69
PR | 995 | 01/25/19 | 762 | Quintanilla, Esteban R |  | 83.38
PR | 995 | 01/25/19 | 773 | Sepulveda Gonzalez, Alfredo |  | 227.07
PR | 995 | 01/25/19 | 786 | Donelson, Richard T |  | 166.31
PR | 995 | 02/01/19 | 36 | Hubbard, Robert W |  | 380.3
PR | 995 | 02/01/19 | 44 | McCabe, Thomas C |  | 87.81
PR | 995 | 02/01/19 | 47 | Paco Leyva, Orlando |  | 65.64
PR | 995 | 02/01/19 | 49 | Ramos Herrera, Franklin J |  | 40.8
PR | 995 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo |  | 113.54
PR | 995 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo |  | 113.54
PR | 995 | 02/01/19 | 70 | Donelson, Richard T |  | 138.59
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 34.59
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/08/19 | 191 | Hubbard, Robert W |  | 217.32
PR | 995 | 02/08/19 | 199 | McCabe, Thomas C |  | 234.17
PR | 995 | 02/08/19 | 202 | Paco Leyva, Orlando |  | 65.64
PR | 995 | 02/08/19 | 204 | Ramos Herrera, Franklin J |  | 40.8
PR | 995 | 02/08/19 | 214 | Sepulveda Gonzalez, Alfredo |  | 227.07
PR | 995 | 02/08/19 | 226 | Donelson, Richard T |  | 55.44
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/15/19 | 353 | Hubbard, Robert W |  | 130.39
PR | 995 | 02/15/19 | 361 | McCabe, Thomas C |  | 343.93
PR | 995 | 02/15/19 | 376 | Sepulveda Gonzalez, Alfredo |  | 127.73
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 34.59
PR | 995 | 02/22/19 | 611 | Hubbard, Robert W |  | 249.91
PR | 995 | 02/22/19 | 619 | McCabe, Thomas C |  | 175.63
PR | 995 | 02/22/19 | 625 | Ramos Herrera, Franklin J |  | 81.6
PR | 995 | 02/22/19 | 635 | Sepulveda Gonzalez, Alfredo |  | 170.3
PR | 995 | 02/22/19 | 647 | Donelson, Richard T |  | 27.72
PR | 995 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/01/19 | 38 | Hubbard, Robert W |  | 54.33
PR | 995 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 40.8
PR | 995 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 81.6
PR | 995 | 03/01/19 | 73 | Wilson, Garret A |  | 229.73
PR | 995 | 03/01/19 | 73 | Wilson, Garret A |  | 16.41
PR | 995 | 03/01/19 | 74 | Donelson, Richard T |  | 55.44
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/08/19 | 278 | Hubbard, Robert W |  | 43.46
PR | 995 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 71.4
PR | 995 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 163.21
PR | 995 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 71.4
PR | 995 | 03/08/19 | 313 | Wilson, Garret A |  | 82.05
PR | 995 | 03/08/19 | 313 | Wilson, Garret A |  | 213.32
PR | 995 | 03/08/19 | 313 | Wilson, Garret A |  | 114.87
PR | 995 | 03/08/19 | 314 | Donelson, Richard T |  | 27.72
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 525 | Hubbard, Robert W |  | 43.46
PR | 995 | 03/15/19 | 545 | Rodriguez Arevalos, Christian |  | 214.21
PR | 995 | 03/15/19 | 561 | Wilson, Garret A |  | 164.1
PR | 995 | 03/15/19 | 561 | Wilson, Garret A |  | 147.69
PR | 995 | 03/15/19 | 562 | Donelson, Richard T |  | 83.16
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/22/19 | 709 | Barbosa, Michael S |  | 33.26
PR | 995 | 03/22/19 | 709 | Barbosa, Michael S |  | 88.7
PR | 995 | 03/22/19 | 739 | Hubbard, Robert W |  | 21.73
PR | 995 | 03/22/19 | 739 | Hubbard, Robert W |  | 65.19
PR | 995 | 03/22/19 | 758 | Rodriguez Arevalos, Christian |  | 346.82
PR | 995 | 03/22/19 | 775 | Wilson, Garret A |  | 418.44
PR | 995 | 03/22/19 | 775 | Wilson, Garret A |  | 98.46
PR | 995 | 03/22/19 | 776 | Donelson, Richard T |  | 138.59
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/22/19 | 780 | Hubbard, Robert W |  | 21.73
PR | 995 | 03/22/19 | 780 | Hubbard, Robert W |  | 65.19
PR | 995 | 03/22/19 | 781 | Hubbard, Robert W |  | -21.73
PR | 995 | 03/22/19 | 781 | Hubbard, Robert W |  | -65.19
PR | 995 | 03/29/19 | 920 | Barbosa, Michael S |  | 49.89
PR | 995 | 03/29/19 | 920 | Barbosa, Michael S |  | 83.16
PR | 995 | 03/29/19 | 920 | Barbosa, Michael S |  | 288.28
PR | 995 | 03/29/19 | 920 | Barbosa, Michael S |  | 155.23
PR | 995 | 03/29/19 | 938 | Foster, Antonio T |  | 244.37
PR | 995 | 03/29/19 | 938 | Foster, Antonio T |  | 8.43
PR | 995 | 03/29/19 | 951 | Hubbard, Robert W |  | 21.73
PR | 995 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 29.27
PR | 995 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 29.27
PR | 995 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 156.11
PR | 995 | 03/29/19 | 970 | Rodriguez Arevalos, Christian |  | 367.22
PR | 995 | 03/29/19 | 970 | Rodriguez Arevalos, Christian |  | 20.4
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 123.07
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 24.61
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 49.23
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 278.96
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 65.64
PR | 995 | 03/29/19 | 987 | Wilson, Garret A |  | 311.78
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/29/19 | 992 | Barbosa, Michael S |  | -49.89
PR | 995 | 03/29/19 | 992 | Barbosa, Michael S |  | -83.16
PR | 995 | 03/29/19 | 992 | Barbosa, Michael S |  | -288.28
PR | 995 | 03/29/19 | 992 | Barbosa, Michael S |  | -155.23
PR | 995 | 03/29/19 | 993 | Barbosa, Michael S |  | 49.89
PR | 995 | 03/29/19 | 993 | Barbosa, Michael S |  | 83.16
PR | 995 | 03/29/19 | 993 | Barbosa, Michael S |  | 288.28
PR | 995 | 03/29/19 | 993 | Barbosa, Michael S |  | 155.23
PR | 995 | 04/05/19 | 82 | Barbosa, Michael S |  | 133.05
PR | 995 | 04/05/19 | 82 | Barbosa, Michael S |  | 443.5
PR | 995 | 04/05/19 | 100 | Foster, Antonio T |  | 75.84
PR | 995 | 04/05/19 | 100 | Foster, Antonio T |  | 25.28
PR | 995 | 04/05/19 | 100 | Foster, Antonio T |  | 269.65
PR | 995 | 04/05/19 | 100 | Foster, Antonio T |  | 67.41
PR | 995 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M |  | 117.08
PR | 995 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M |  | 390.28
PR | 995 | 04/05/19 | 133 | Rodriguez Arevalos, Christian |  | 122.41
PR | 995 | 04/05/19 | 133 | Rodriguez Arevalos, Christian |  | 408.02
PR | 995 | 04/05/19 | 134 | Ross, Kelli M |  | 159.66
PR | 995 | 04/05/19 | 134 | Ross, Kelli M |  | 425.76
PR | 995 | 04/05/19 | 150 | Wilson, Garret A |  | 86.15
PR | 995 | 04/05/19 | 150 | Wilson, Garret A |  | 73.84
PR | 995 | 04/05/19 | 150 | Wilson, Garret A |  | 180.5
PR | 995 | 04/05/19 | 150 | Wilson, Garret A |  | 32.82
PR | 995 | 04/05/19 | 150 | Wilson, Garret A |  | 443.06
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 33.26
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 66.53
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 33.26
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 177.4
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 177.4
PR | 995 | 04/12/19 | 326 | Barbosa, Michael S |  | 88.7
PR | 995 | 04/12/19 | 344 | Foster, Antonio T |  | 75.84
PR | 995 | 04/12/19 | 344 | Foster, Antonio T |  | 25.28
PR | 995 | 04/12/19 | 344 | Foster, Antonio T |  | 202.24
PR | 995 | 04/12/19 | 344 | Foster, Antonio T |  | 67.41
PR | 995 | 04/12/19 | 344 | Foster, Antonio T |  | 67.41
PR | 995 | 04/12/19 | 357 | Hubbard, Robert W |  | 155.23
PR | 995 | 04/12/19 | 357 | Hubbard, Robert W |  | 44.35
PR | 995 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M |  | 117.08
PR | 995 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M |  | 390.28
PR | 995 | 04/12/19 | 362 | Lopez, Maslin A |  | 212.88
PR | 995 | 04/12/19 | 377 | Rodriguez Arevalos, Christian |  | 408.02
PR | 995 | 04/12/19 | 378 | Ross, Kelli M |  | 223.52
PR | 995 | 04/12/19 | 378 | Ross, Kelli M |  | 745.08
PR | 995 | 04/12/19 | 395 | Wilson, Garret A |  | 106.44
PR | 995 | 04/12/19 | 395 | Wilson, Garret A |  | 35.48
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/19/19 | 523 | Barbosa, Michael S |  | 33.26
PR | 995 | 04/19/19 | 523 | Barbosa, Michael S |  | 88.7
PR | 995 | 04/19/19 | 523 | Barbosa, Michael S |  | 88.7
PR | 995 | 04/19/19 | 541 | Foster, Antonio T |  | 75.84
PR | 995 | 04/19/19 | 541 | Foster, Antonio T |  | 25.28
PR | 995 | 04/19/19 | 541 | Foster, Antonio T |  | 269.65
PR | 995 | 04/19/19 | 541 | Foster, Antonio T |  | 67.41
PR | 995 | 04/19/19 | 555 | Hubbard, Robert W |  | 133.05
PR | 995 | 04/19/19 | 555 | Hubbard, Robert W |  | 33.26
PR | 995 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M |  | 117.08
PR | 995 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M |  | 390.28
PR | 995 | 04/19/19 | 560 | Lopez, Maslin A |  | 85.15
PR | 995 | 04/19/19 | 560 | Lopez, Maslin A |  | 283.84
PR | 995 | 04/19/19 | 566 | Montenegro, Carlos E |  | 77.17
PR | 995 | 04/19/19 | 566 | Montenegro, Carlos E |  | 205.78
PR | 995 | 04/19/19 | 575 | Rodriguez Arevalos, Christian |  | 408.02
PR | 995 | 04/19/19 | 575 | Rodriguez Arevalos, Christian |  | 122.41
PR | 995 | 04/19/19 | 577 | Ross, Kelli M |  | 223.52
PR | 995 | 04/19/19 | 577 | Ross, Kelli M |  | 745.08
PR | 995 | 04/19/19 | 593 | Wilson, Garret A |  | 10.2
PR | 995 | 04/19/19 | 593 | Wilson, Garret A |  | 1.33
PR | 995 | 04/19/19 | 594 | Wilson, Garret A |  | -10.2
PR | 995 | 04/19/19 | 594 | Wilson, Garret A |  | -1.33
PR | 995 | 04/19/19 | 595 | Wilson, Garret A |  | 408.02
PR | 995 | 04/19/19 | 595 | Wilson, Garret A |  | 53.22
PR | 995 | 04/19/19 | 596 | Donelson, Richard T |  | 27.72
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 04/26/19 | 760 | Foster, Antonio T |  | 79.83
PR | 995 | 04/26/19 | 760 | Foster, Antonio T |  | 26.61
PR | 995 | 04/26/19 | 760 | Foster, Antonio T |  | 212.88
PR | 995 | 04/26/19 | 760 | Foster, Antonio T |  | 141.92
PR | 995 | 04/26/19 | 774 | Hubbard, Robert W |  | 110.88
PR | 995 | 04/26/19 | 774 | Hubbard, Robert W |  | 44.35
PR | 995 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M |  | 133.05
PR | 995 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M |  | 443.5
PR | 995 | 04/26/19 | 779 | Lopez, Maslin A |  | 90.47
PR | 995 | 04/26/19 | 779 | Lopez, Maslin A |  | 301.58
PR | 995 | 04/26/19 | 785 | Montenegro, Carlos E |  | 123.74
PR | 995 | 04/26/19 | 785 | Montenegro, Carlos E |  | 41.25
PR | 995 | 04/26/19 | 785 | Montenegro, Carlos E |  | 261.22
PR | 995 | 04/26/19 | 785 | Montenegro, Carlos E |  | 288.72
PR | 995 | 04/26/19 | 786 | Paco Leyva, Orlando |  | 35.48
PR | 995 | 04/26/19 | 794 | Rodriguez Arevalos, Christian |  | 103.78
PR | 995 | 04/26/19 | 794 | Rodriguez Arevalos, Christian |  | 461.24
PR | 995 | 04/26/19 | 796 | Ross, Kelli M |  | 223.52
PR | 995 | 04/26/19 | 796 | Ross, Kelli M |  | 745.08
PR | 995 | 04/26/19 | 810 | Wilson, Garret A |  | 833.78
PR | 995 | 04/26/19 | 810 | Wilson, Garret A |  | 17.74
PR | 995 | 04/26/19 | 812 | Donelson, Richard T |  | 27.72
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/03/19 | 28 | Foster, Antonio T |  | 354.8
PR | 995 | 05/03/19 | 42 | Hubbard, Robert W |  | 99.79
PR | 995 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M |  | 354.8
PR | 995 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M |  | 88.7
PR | 995 | 05/03/19 | 48 | Lopez, Maslin A |  | 301.58
PR | 995 | 05/03/19 | 54 | Montenegro, Carlos E |  | 439.95
PR | 995 | 05/03/19 | 63 | Rodriguez Arevalos, Christian |  | 461.24
PR | 995 | 05/03/19 | 65 | Ross, Kelli M |  | 745.08
PR | 995 | 05/03/19 | 80 | Wilson, Garret A |  | 532.2
PR | 995 | 05/03/19 | 80 | Wilson, Garret A |  | 88.7
PR | 995 | 05/03/19 | 80 | Wilson, Garret A |  | 88.7
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A |  | 21.29
PR | 995 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A |  | 227.07
PR | 995 | 05/10/19 | 181 | Foster, Antonio T |  | 354.8
PR | 995 | 05/10/19 | 195 | Hubbard, Robert W |  | 33.26
PR | 995 | 05/10/19 | 196 | Jimenez Alvarenga, Gerson M |  | 443.5
PR | 995 | 05/10/19 | 201 | Lopez, Maslin A |  | 301.58
PR | 995 | 05/10/19 | 207 | Montenegro, Carlos E |  | 549.94
PR | 995 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 26.61
PR | 995 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 17.3
PR | 995 | 05/10/19 | 216 | Rodriguez Arevalos, Christian |  | 334.4
PR | 995 | 05/10/19 | 216 | Rodriguez Arevalos, Christian |  | 126.84
PR | 995 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 127.73
PR | 995 | 05/10/19 | 218 | Ross, Kelli M |  | 596.06
PR | 995 | 05/10/19 | 233 | Wilson, Garret A |  | 603.16
PR | 995 | 05/10/19 | 233 | Wilson, Garret A |  | 53.22
PR | 995 | 05/10/19 | 233 | Wilson, Garret A |  | 53.22
PR | 995 | 05/10/19 | 234 | Donelson, Richard T |  | 27.72
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/17/19 | 390 | Amaya Gonzalez, Edilberto A |  | 496.72
PR | 995 | 05/17/19 | 398 | Boss, Kyle A |  | 180.95
PR | 995 | 05/17/19 | 412 | Escalante Escobar, Boanerge |  | 390.28
PR | 995 | 05/17/19 | 413 | Foster, Antonio T |  | 354.8
PR | 995 | 05/17/19 | 427 | Hubbard, Robert W |  | 88.7
PR | 995 | 05/17/19 | 428 | Jimenez Alvarenga, Gerson M |  | 443.5
PR | 995 | 05/17/19 | 433 | Lopez, Maslin A |  | 301.58
PR | 995 | 05/17/19 | 439 | Montenegro, Carlos E |  | 549.94
PR | 995 | 05/17/19 | 442 | Ramos Herrera, Franklin J |  | 184.5
PR | 995 | 05/17/19 | 448 | Rodriguez Arevalos, Christian |  | 461.24
PR | 995 | 05/17/19 | 449 | Romero Garza, Jesus I |  | 319.32
PR | 995 | 05/17/19 | 450 | Ross, Kelli M |  | 745.08
PR | 995 | 05/17/19 | 465 | Wilson, Garret A |  | 620.9
PR | 995 | 05/17/19 | 465 | Wilson, Garret A |  | 88.7
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/24/19 | 603 | Amaya Gonzalez, Edilberto A |  | 325.25
PR | 995 | 05/24/19 | 610 | Boss, Kyle A |  | 287.98
PR | 995 | 05/24/19 | 624 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 05/24/19 | 625 | Foster, Antonio T |  | 330.33
PR | 995 | 05/24/19 | 640 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 05/24/19 | 645 | Lopez, Maslin A |  | 287.98
PR | 995 | 05/24/19 | 651 | Montenegro, Carlos E |  | 525.14
PR | 995 | 05/24/19 | 652 | Paco Leyva, Orlando |  | 321.86
PR | 995 | 05/24/19 | 654 | Ramos Herrera, Franklin J |  | 440.44
PR | 995 | 05/24/19 | 659 | Roberts, Lake A |  | 67.76
PR | 995 | 05/24/19 | 660 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 05/24/19 | 661 | Romero Garza, Jesus I |  | 304.92
PR | 995 | 05/24/19 | 662 | Ross, Kelli M |  | 622.55
PR | 995 | 05/24/19 | 677 | Wilson, Garret A |  | 677.6
PR | 995 | 05/24/19 | 680 | Donelson, Richard T |  | 55.44
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 05/31/19 | 876 | Amaya Gonzalez, Edilberto A |  | 216.83
PR | 995 | 05/31/19 | 881 | Barnhart, Joseph N |  | 84.7
PR | 995 | 05/31/19 | 884 | Boss, Kyle A |  | 230.38
PR | 995 | 05/31/19 | 898 | Escalante Escobar, Boanerge |  | 298.14
PR | 995 | 05/31/19 | 899 | Foster, Antonio T |  | 271.04
PR | 995 | 05/31/19 | 913 | Hubbard, Robert W |  | 42.35
PR | 995 | 05/31/19 | 914 | Jimenez Alvarenga, Gerson M |  | 338.8
PR | 995 | 05/31/19 | 919 | Lopez, Maslin A |  | 230.38
PR | 995 | 05/31/19 | 925 | Montenegro, Carlos E |  | 420.11
PR | 995 | 05/31/19 | 926 | Paco Leyva, Orlando |  | 203.28
PR | 995 | 05/31/19 | 926 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 05/31/19 | 928 | Ramos Herrera, Franklin J |  | 352.35
PR | 995 | 05/31/19 | 933 | Roberts, Lake A |  | 271.04
PR | 995 | 05/31/19 | 934 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 05/31/19 | 935 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 05/31/19 | 936 | Ross, Kelli M |  | 426.89
PR | 995 | 05/31/19 | 951 | Wilson, Garret A |  | 542.08
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A |  | 325.25
PR | 995 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A |  | 108.42
PR | 995 | 06/07/19 | 186 | Boss, Kyle A |  | 287.98
PR | 995 | 06/07/19 | 200 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 06/07/19 | 201 | Foster, Antonio T |  | 93.17
PR | 995 | 06/07/19 | 215 | Hubbard, Robert W |  | 63.53
PR | 995 | 06/07/19 | 216 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 06/07/19 | 220 | Lopez, Maslin A |  | 287.98
PR | 995 | 06/07/19 | 226 | Montenegro, Carlos E |  | 525.14
PR | 995 | 06/07/19 | 227 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 06/07/19 | 229 | Ramos Herrera, Franklin J |  | 209.21
PR | 995 | 06/07/19 | 234 | Roberts, Lake A |  | 271.04
PR | 995 | 06/07/19 | 235 | Rodriguez Arevalos, Christian |  | 264.26
PR | 995 | 06/07/19 | 235 | Rodriguez Arevalos, Christian |  | 176.18
PR | 995 | 06/07/19 | 236 | Romero Garza, Jesus I |  | 304.92
PR | 995 | 06/07/19 | 237 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 06/07/19 | 238 | Ross, Kelli M |  | 426.89
PR | 995 | 06/07/19 | 253 | Wilson, Garret A |  | 677.6
PR | 995 | 06/07/19 | 254 | Donelson, Richard T |  | 27.72
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/14/19 | 449 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 06/14/19 | 457 | Boss, Kyle A |  | 287.98
PR | 995 | 06/14/19 | 470 | Escalante Escobar, Boanerge |  | 74.54
PR | 995 | 06/14/19 | 470 | Escalante Escobar, Boanerge |  | 298.14
PR | 995 | 06/14/19 | 483 | Hubbard, Robert W |  | 63.53
PR | 995 | 06/14/19 | 484 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 06/14/19 | 489 | Lopez, Maslin A |  | 287.98
PR | 995 | 06/14/19 | 495 | Montenegro, Carlos E |  | 105.03
PR | 995 | 06/14/19 | 495 | Montenegro, Carlos E |  | 420.11
PR | 995 | 06/14/19 | 496 | Paco Leyva, Orlando |  | 245.63
PR | 995 | 06/14/19 | 498 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 06/14/19 | 503 | Roberts, Lake A |  | 338.8
PR | 995 | 06/14/19 | 504 | Rodriguez Arevalos, Christian |  | 264.26
PR | 995 | 06/14/19 | 504 | Rodriguez Arevalos, Christian |  | 176.18
PR | 995 | 06/14/19 | 505 | Romero Garza, Jesus I |  | 304.92
PR | 995 | 06/14/19 | 506 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 06/14/19 | 507 | Ross, Kelli M |  | 711.48
PR | 995 | 06/14/19 | 521 | Wilson, Garret A |  | 321.86
PR | 995 | 06/14/19 | 521 | Wilson, Garret A |  | 355.74
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 166.31
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 81.52
PR | 995 | 06/21/19 | 617 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 06/21/19 | 625 | Boss, Aaron J |  | 162.62
PR | 995 | 06/21/19 | 626 | Boss, Kyle A |  | 287.98
PR | 995 | 06/21/19 | 634 | Cruz Guzman, Joel A |  | 94.86
PR | 995 | 06/21/19 | 640 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 06/21/19 | 654 | Hubbard, Robert W |  | 21.18
PR | 995 | 06/21/19 | 655 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 06/21/19 | 660 | Lopez, Maslin A |  | 287.98
PR | 995 | 06/21/19 | 666 | Montenegro, Carlos E |  | 525.14
PR | 995 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 169.4
PR | 995 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 06/21/19 | 674 | Roberts, Lake A |  | 338.8
PR | 995 | 06/21/19 | 675 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 06/21/19 | 675 | Rodriguez Arevalos, Christian |  | 88.09
PR | 995 | 06/21/19 | 676 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 06/21/19 | 677 | Rosas Olivares, Jorge C |  | 135.52
PR | 995 | 06/21/19 | 678 | Ross, Kelli M |  | 426.89
PR | 995 | 06/21/19 | 678 | Ross, Kelli M |  | 284.59
PR | 995 | 06/21/19 | 680 | Silva Morales, Jair J |  | 91.48
PR | 995 | 06/21/19 | 692 | Wilson, Garret A |  | 592.9
PR | 995 | 06/21/19 | 692 | Wilson, Garret A |  | 84.7
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/28/19 | 835 | Amaya Gonzalez, Edilberto A |  | 501.42
PR | 995 | 06/28/19 | 843 | Boss, Aaron J |  | 271.04
PR | 995 | 06/28/19 | 844 | Boss, Kyle A |  | 244.78
PR | 995 | 06/28/19 | 844 | Boss, Kyle A |  | 43.2
PR | 995 | 06/28/19 | 852 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 06/28/19 | 858 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 06/28/19 | 873 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 06/28/19 | 877 | Lopez, Maslin A |  | 287.98
PR | 995 | 06/28/19 | 883 | Montenegro, Carlos E |  | 525.14
PR | 995 | 06/28/19 | 891 | Roberts, Lake A |  | 271.04
PR | 995 | 06/28/19 | 892 | Rodriguez Arevalos, Christian |  | 264.26
PR | 995 | 06/28/19 | 892 | Rodriguez Arevalos, Christian |  | 88.09
PR | 995 | 06/28/19 | 893 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 06/28/19 | 894 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 06/28/19 | 895 | Ross, Kelli M |  | 284.59
PR | 995 | 06/28/19 | 895 | Ross, Kelli M |  | 426.89
PR | 995 | 06/28/19 | 897 | Silva Morales, Jair J |  | 457.38
PR | 995 | 06/28/19 | 909 | Wilson, Garret A |  | 525.14
PR | 995 | 06/28/19 | 909 | Wilson, Garret A |  | 152.46
PR | 995 | 06/28/19 | 910 | Donelson, Richard T |  | 110.88
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/05/19 | 7 | Amaya Gonzalez, Edilberto A |  | 433.66
PR | 995 | 07/05/19 | 15 | Boss, Aaron J |  | 237.16
PR | 995 | 07/05/19 | 15 | Boss, Aaron J |  | 33.88
PR | 995 | 07/05/19 | 16 | Boss, Kyle A |  | 230.38
PR | 995 | 07/05/19 | 16 | Boss, Kyle A |  | 57.6
PR | 995 | 07/05/19 | 24 | Cruz Guzman, Joel A |  | 462.46
PR | 995 | 07/05/19 | 24 | Cruz Guzman, Joel A |  | 11.86
PR | 995 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 288.83
PR | 995 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 9.32
PR | 995 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 74.54
PR | 995 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M |  | 412.91
PR | 995 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M |  | 10.59
PR | 995 | 07/05/19 | 49 | Lopez, Maslin A |  | 280.78
PR | 995 | 07/05/19 | 49 | Lopez, Maslin A |  | 7.2
PR | 995 | 07/05/19 | 55 | Montenegro, Carlos E |  | 210.06
PR | 995 | 07/05/19 | 63 | Roberts, Lake A |  | 127.05
PR | 995 | 07/05/19 | 63 | Roberts, Lake A |  | 8.47
PR | 995 | 07/05/19 | 63 | Roberts, Lake A |  | 135.52
PR | 995 | 07/05/19 | 64 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 07/05/19 | 64 | Rodriguez Arevalos, Christian |  | 88.09
PR | 995 | 07/05/19 | 65 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 07/05/19 | 65 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 07/05/19 | 66 | Ross, Kelli M |  | 569.18
PR | 995 | 07/05/19 | 66 | Ross, Kelli M |  | 142.3
PR | 995 | 07/05/19 | 68 | Silva Morales, Jair J |  | 445.95
PR | 995 | 07/05/19 | 68 | Silva Morales, Jair J |  | 11.43
PR | 995 | 07/05/19 | 80 | Wilson, Garret A |  | 355.74
PR | 995 | 07/05/19 | 80 | Wilson, Garret A |  | 321.86
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 27.72
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/12/19 | 277 | Amaya Gonzalez, Edilberto A |  | 433.66
PR | 995 | 07/12/19 | 285 | Boss, Aaron J |  | 176.18
PR | 995 | 07/12/19 | 285 | Boss, Aaron J |  | 40.66
PR | 995 | 07/12/19 | 286 | Boss, Kyle A |  | 223.18
PR | 995 | 07/12/19 | 286 | Boss, Kyle A |  | 7.2
PR | 995 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 237.16
PR | 995 | 07/12/19 | 293 | Cruz Guzman, Joel A |  | 379.46
PR | 995 | 07/12/19 | 299 | Escalante Escobar, Boanerge |  | 298.14
PR | 995 | 07/12/19 | 303 | Gauthier, Dillon R |  | 115.19
PR | 995 | 07/12/19 | 314 | Jimenez Alvarenga, Gerson M |  | 338.8
PR | 995 | 07/12/19 | 318 | Lopez, Maslin A |  | 230.38
PR | 995 | 07/12/19 | 324 | Montenegro, Carlos E |  | 210.06
PR | 995 | 07/12/19 | 332 | Roberts, Lake A |  | 122.82
PR | 995 | 07/12/19 | 333 | Rodriguez Arevalos, Christian |  | 319.32
PR | 995 | 07/12/19 | 334 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 07/12/19 | 335 | Rosas Olivares, Jorge C |  | 199.05
PR | 995 | 07/12/19 | 336 | Ross, Kelli M |  | 444.68
PR | 995 | 07/12/19 | 336 | Ross, Kelli M |  | 124.51
PR | 995 | 07/12/19 | 339 | Silva Morales, Jair J |  | 274.43
PR | 995 | 07/12/19 | 351 | Wilson, Garret A |  | 415.03
PR | 995 | 07/12/19 | 351 | Wilson, Garret A |  | 118.58
PR | 995 | 07/12/19 | 351 | Wilson, Garret A |  | 8.47
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/19/19 | 507 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 07/19/19 | 515 | Boss, Aaron J |  | 271.04
PR | 995 | 07/19/19 | 516 | Boss, Kyle A |  | 304.92
PR | 995 | 07/19/19 | 529 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 07/19/19 | 543 | Hubbard, Robert W |  | 63.53
PR | 995 | 07/19/19 | 543 | Hubbard, Robert W |  | 21.18
PR | 995 | 07/19/19 | 544 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 07/19/19 | 548 | Lopez, Maslin A |  | 287.98
PR | 995 | 07/19/19 | 554 | Montenegro, Carlos E |  | 420.11
PR | 995 | 07/19/19 | 562 | Roberts, Lake A |  | 338.8
PR | 995 | 07/19/19 | 563 | Rodriguez Arevalos, Christian |  | 363.36
PR | 995 | 07/19/19 | 563 | Rodriguez Arevalos, Christian |  | 77.08
PR | 995 | 07/19/19 | 564 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 07/19/19 | 564 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 07/19/19 | 565 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 07/19/19 | 566 | Ross, Kelli M |  | 658.12
PR | 995 | 07/19/19 | 566 | Ross, Kelli M |  | 53.36
PR | 995 | 07/19/19 | 569 | Silva Morales, Jair J |  | 434.51
PR | 995 | 07/19/19 | 581 | Wilson, Garret A |  | 321.86
PR | 995 | 07/19/19 | 581 | Wilson, Garret A |  | 67.76
PR | 995 | 07/19/19 | 581 | Wilson, Garret A |  | 152.46
PR | 995 | 07/19/19 | 581 | Wilson, Garret A |  | 135.52
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/26/19 | 611 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 07/26/19 | 613 | Ascencio, Jose L |  | 508.2
PR | 995 | 07/26/19 | 619 | Boss, Aaron J |  | 271.04
PR | 995 | 07/26/19 | 620 | Boss, Kyle A |  | 304.92
PR | 995 | 07/26/19 | 627 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 07/26/19 | 633 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 07/26/19 | 646 | Hubbard, Robert W |  | 42.35
PR | 995 | 07/26/19 | 647 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 07/26/19 | 651 | Lopez, Maslin A |  | 287.98
PR | 995 | 07/26/19 | 657 | Montenegro, Carlos E |  | 420.11
PR | 995 | 07/26/19 | 665 | Roberts, Lake A |  | 338.8
PR | 995 | 07/26/19 | 666 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 07/26/19 | 666 | Rodriguez Arevalos, Christian |  | 88.09
PR | 995 | 07/26/19 | 667 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 07/26/19 | 667 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 07/26/19 | 668 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 07/26/19 | 669 | Ross, Kelli M |  | 533.61
PR | 995 | 07/26/19 | 669 | Ross, Kelli M |  | 177.87
PR | 995 | 07/26/19 | 672 | Silva Morales, Jair J |  | 445.95
PR | 995 | 07/26/19 | 684 | Wilson, Garret A |  | 643.72
PR | 995 | 07/26/19 | 684 | Wilson, Garret A |  | 16.94
PR | 995 | 07/26/19 | 684 | Wilson, Garret A |  | 16.94
PR | 995 | 07/26/19 | 685 | Donelson, Richard T |  | 55.44
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/02/19 | 3 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 08/02/19 | 11 | Boss, Aaron J |  | 271.04
PR | 995 | 08/02/19 | 12 | Boss, Kyle A |  | 121.97
PR | 995 | 08/02/19 | 12 | Boss, Kyle A |  | 182.95
PR | 995 | 08/02/19 | 19 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 08/02/19 | 25 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 08/02/19 | 39 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 08/02/19 | 43 | Lopez, Maslin A |  | 287.98
PR | 995 | 08/02/19 | 49 | Montenegro, Carlos E |  | 420.11
PR | 995 | 08/02/19 | 57 | Roberts, Lake A |  | 271.04
PR | 995 | 08/02/19 | 58 | Rodriguez Arevalos, Christian |  | 434.93
PR | 995 | 08/02/19 | 59 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 08/02/19 | 59 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 08/02/19 | 60 | Ross, Kelli M |  | 426.89
PR | 995 | 08/02/19 | 60 | Ross, Kelli M |  | 284.59
PR | 995 | 08/02/19 | 63 | Silva Morales, Jair J |  | 451.66
PR | 995 | 08/02/19 | 75 | Wilson, Garret A |  | 677.6
PR | 995 | 08/02/19 | 76 | Donelson, Richard T |  | 55.44
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/09/19 | 255 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 08/09/19 | 263 | Boss, Aaron J |  | 271.04
PR | 995 | 08/09/19 | 264 | Boss, Kyle A |  | 205.82
PR | 995 | 08/09/19 | 264 | Boss, Kyle A |  | 99.1
PR | 995 | 08/09/19 | 271 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 08/09/19 | 277 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 08/09/19 | 291 | Hubbard, Robert W |  | 127.05
PR | 995 | 08/09/19 | 292 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 08/09/19 | 296 | Lopez, Maslin A |  | 287.98
PR | 995 | 08/09/19 | 302 | Montenegro, Carlos E |  | 315.08
PR | 995 | 08/09/19 | 302 | Montenegro, Carlos E |  | 210.06
PR | 995 | 08/09/19 | 310 | Roberts, Lake A |  | 338.8
PR | 995 | 08/09/19 | 311 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 08/09/19 | 312 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 08/09/19 | 312 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 08/09/19 | 313 | Ross, Kelli M |  | 711.48
PR | 995 | 08/09/19 | 316 | Silva Morales, Jair J |  | 457.38
PR | 995 | 08/09/19 | 327 | Wilson, Garret A |  | 406.56
PR | 995 | 08/09/19 | 328 | Donelson, Richard T |  | 27.72
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/16/19 | 562 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 08/16/19 | 563 | Anderson, Richard P |  | 59.71
PR | 995 | 08/16/19 | 570 | Boss, Aaron J |  | 271.04
PR | 995 | 08/16/19 | 571 | Boss, Kyle A |  | 160.08
PR | 995 | 08/16/19 | 571 | Boss, Kyle A |  | 144.84
PR | 995 | 08/16/19 | 578 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 08/16/19 | 584 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 08/16/19 | 598 | Hubbard, Robert W |  | 84.7
PR | 995 | 08/16/19 | 599 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 08/16/19 | 603 | Lopez, Maslin A |  | 287.98
PR | 995 | 08/16/19 | 609 | Montenegro, Carlos E |  | 420.11
PR | 995 | 08/16/19 | 609 | Montenegro, Carlos E |  | 105.03
PR | 995 | 08/16/19 | 617 | Roberts, Lake A |  | 203.28
PR | 995 | 08/16/19 | 617 | Roberts, Lake A |  | 67.76
PR | 995 | 08/16/19 | 618 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 08/16/19 | 619 | Romero Garza, Jesus I |  | 304.92
PR | 995 | 08/16/19 | 620 | Ross, Kelli M |  | 711.48
PR | 995 | 08/16/19 | 623 | Silva Morales, Jair J |  | 440.23
PR | 995 | 08/16/19 | 635 | Wilson, Garret A |  | 542.08
PR | 995 | 08/16/19 | 636 | Donelson, Richard T |  | 55.44
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/23/19 | 798 | Amaya Gonzalez, Edilberto A |  | 433.66
PR | 995 | 08/23/19 | 806 | Boss, Aaron J |  | 216.83
PR | 995 | 08/23/19 | 807 | Boss, Kyle A |  | 243.94
PR | 995 | 08/23/19 | 814 | Cruz Guzman, Joel A |  | 189.73
PR | 995 | 08/23/19 | 820 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M |  | 169.4
PR | 995 | 08/23/19 | 840 | Lopez, Maslin A |  | 230.38
PR | 995 | 08/23/19 | 840 | Lopez, Maslin A |  | 28.8
PR | 995 | 08/23/19 | 846 | Montenegro, Carlos E |  | 525.14
PR | 995 | 08/23/19 | 854 | Roberts, Lake A |  | 245.63
PR | 995 | 08/23/19 | 854 | Roberts, Lake A |  | 93.17
PR | 995 | 08/23/19 | 855 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 30.49
PR | 995 | 08/23/19 | 857 | Ross, Kelli M |  | 711.48
PR | 995 | 08/23/19 | 860 | Silva Morales, Jair J |  | 182.95
PR | 995 | 08/23/19 | 872 | Wilson, Garret A |  | 677.6
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 325.25
PR | 995 | 08/30/19 | 997 | Boss, Aaron J |  | 271.04
PR | 995 | 08/30/19 | 998 | Boss, Kyle A |  | 304.92
PR | 995 | 08/30/19 | 1011 | Escalante Escobar, Boanerge |  | 223.61
PR | 995 | 08/30/19 | 1011 | Escalante Escobar, Boanerge |  | 149.07
PR | 995 | 08/30/19 | 1026 | Hubbard, Robert W |  | 84.7
PR | 995 | 08/30/19 | 1031 | Lopez, Maslin A |  | 230.38
PR | 995 | 08/30/19 | 1031 | Lopez, Maslin A |  | 57.6
PR | 995 | 08/30/19 | 1037 | Montenegro, Carlos E |  | 315.08
PR | 995 | 08/30/19 | 1037 | Montenegro, Carlos E |  | 210.06
PR | 995 | 08/30/19 | 1045 | Roberts, Lake A |  | 245.63
PR | 995 | 08/30/19 | 1045 | Roberts, Lake A |  | 67.76
PR | 995 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian |  | 264.26
PR | 995 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian |  | 176.18
PR | 995 | 08/30/19 | 1047 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 08/30/19 | 1047 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 08/30/19 | 1048 | Ross, Kelli M |  | 569.18
PR | 995 | 08/30/19 | 1048 | Ross, Kelli M |  | 142.3
PR | 995 | 08/30/19 | 1063 | Wilson, Garret A |  | 677.6
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 27.72
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 194.03
PR | 995 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 09/06/19 | 18 | Boss, Aaron J |  | 216.83
PR | 995 | 09/06/19 | 19 | Boss, Kyle A |  | 167.71
PR | 995 | 09/06/19 | 32 | Escalante Escobar, Boanerge |  | 298.14
PR | 995 | 09/06/19 | 47 | Hubbard, Robert W |  | 63.53
PR | 995 | 09/06/19 | 47 | Hubbard, Robert W |  | 42.35
PR | 995 | 09/06/19 | 52 | Lopez, Maslin A |  | 79.19
PR | 995 | 09/06/19 | 52 | Lopez, Maslin A |  | 36
PR | 995 | 09/06/19 | 52 | Lopez, Maslin A |  | 57.6
PR | 995 | 09/06/19 | 58 | Montenegro, Carlos E |  | 420.11
PR | 995 | 09/06/19 | 66 | Roberts, Lake A |  | 245.63
PR | 995 | 09/06/19 | 66 | Roberts, Lake A |  | 25.41
PR | 995 | 09/06/19 | 67 | Rodriguez Arevalos, Christian |  | 143.14
PR | 995 | 09/06/19 | 67 | Rodriguez Arevalos, Christian |  | 209.21
PR | 995 | 09/06/19 | 68 | Romero Garza, Jesus I |  | 182.95
PR | 995 | 09/06/19 | 69 | Ross, Kelli M |  | 142.3
PR | 995 | 09/06/19 | 69 | Ross, Kelli M |  | 426.89
PR | 995 | 09/06/19 | 84 | Wilson, Garret A |  | 372.68
PR | 995 | 09/06/19 | 85 | Donelson, Richard T |  | 55.44
PR | 995 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/13/19 | 242 | Boss, Aaron J |  | 271.04
PR | 995 | 09/13/19 | 243 | Boss, Kyle A |  | 45.74
PR | 995 | 09/13/19 | 256 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 09/13/19 | 271 | Hubbard, Robert W |  | 21.18
PR | 995 | 09/13/19 | 271 | Hubbard, Robert W |  | 127.05
PR | 995 | 09/13/19 | 275 | Lopez, Maslin A |  | 86.39
PR | 995 | 09/13/19 | 275 | Lopez, Maslin A |  | 287.98
PR | 995 | 09/13/19 | 281 | Montenegro, Carlos E |  | 420.11
PR | 995 | 09/13/19 | 289 | Roberts, Lake A |  | 25.41
PR | 995 | 09/13/19 | 289 | Roberts, Lake A |  | 76.23
PR | 995 | 09/13/19 | 289 | Roberts, Lake A |  | 203.28
PR | 995 | 09/13/19 | 289 | Roberts, Lake A |  | 135.52
PR | 995 | 09/13/19 | 290 | Rodriguez Arevalos, Christian |  | 132.13
PR | 995 | 09/13/19 | 290 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 09/13/19 | 291 | Romero Garza, Jesus I |  | 91.48
PR | 995 | 09/13/19 | 291 | Romero Garza, Jesus I |  | 304.92
PR | 995 | 09/13/19 | 292 | Ross, Kelli M |  | 213.44
PR | 995 | 09/13/19 | 292 | Ross, Kelli M |  | 711.48
PR | 995 | 09/13/19 | 307 | Wilson, Garret A |  | 101.64
PR | 995 | 09/13/19 | 308 | Donelson, Richard T |  | 83.16
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/20/19 | 479 | Boss, Aaron J |  | 271.04
PR | 995 | 09/20/19 | 480 | Boss, Kyle A |  | 182.95
PR | 995 | 09/20/19 | 480 | Boss, Kyle A |  | 60.98
PR | 995 | 09/20/19 | 481 | Castro Hernandez, Jose A |  | 118.58
PR | 995 | 09/20/19 | 487 | Cruz Guzman, Joel A |  | 94.86
PR | 995 | 09/20/19 | 493 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 09/20/19 | 502 | Guerrero Espinoza, Mario |  | 54.21
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 127.05
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 84.7
PR | 995 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M |  | 84.7
PR | 995 | 09/20/19 | 513 | Lopez, Maslin A |  | 287.98
PR | 995 | 09/20/19 | 519 | Montenegro, Carlos E |  | 525.14
PR | 995 | 09/20/19 | 527 | Roberts, Lake A |  | 262.57
PR | 995 | 09/20/19 | 527 | Roberts, Lake A |  | 76.23
PR | 995 | 09/20/19 | 528 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 09/20/19 | 529 | Romero Garza, Jesus I |  | 243.94
PR | 995 | 09/20/19 | 530 | Ross, Kelli M |  | 569.18
PR | 995 | 09/20/19 | 533 | Silva Morales, Jair J |  | 91.48
PR | 995 | 09/20/19 | 545 | Wilson, Garret A |  | 152.46
PR | 995 | 09/20/19 | 545 | Wilson, Garret A |  | 186.34
PR | 995 | 09/20/19 | 545 | Wilson, Garret A |  | 152.46
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 09/27/19 | 635 | Boss, Aaron J |  | 271.04
PR | 995 | 09/27/19 | 636 | Boss, Kyle A |  | 304.92
PR | 995 | 09/27/19 | 649 | Escalante Escobar, Boanerge |  | 223.61
PR | 995 | 09/27/19 | 649 | Escalante Escobar, Boanerge |  | 149.07
PR | 995 | 09/27/19 | 666 | Hubbard, Robert W |  | 63.53
PR | 995 | 09/27/19 | 666 | Hubbard, Robert W |  | 148.23
PR | 995 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M |  | 84.7
PR | 995 | 09/27/19 | 672 | Lopez, Maslin A |  | 287.98
PR | 995 | 09/27/19 | 676 | McCabe, Thomas C |  | 237.16
PR | 995 | 09/27/19 | 678 | Montenegro, Carlos E |  | 315.08
PR | 995 | 09/27/19 | 678 | Montenegro, Carlos E |  | 105.03
PR | 995 | 09/27/19 | 686 | Roberts, Lake A |  | 204.97
PR | 995 | 09/27/19 | 686 | Roberts, Lake A |  | 55.9
PR | 995 | 09/27/19 | 686 | Roberts, Lake A |  | 37.27
PR | 995 | 09/27/19 | 687 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 09/27/19 | 688 | Romero Garza, Jesus I |  | 271.04
PR | 995 | 09/27/19 | 688 | Romero Garza, Jesus I |  | 67.76
PR | 995 | 09/27/19 | 689 | Ross, Kelli M |  | 711.48
PR | 995 | 09/27/19 | 704 | Wilson, Garret A |  | 542.08
PR | 995 | 09/27/19 | 704 | Wilson, Garret A |  | 67.76
PR | 995 | 09/27/19 | 704 | Wilson, Garret A |  | 67.76
PR | 995 | 09/27/19 | 705 | Donelson, Richard T |  | 27.72
PR | 995 | 10/04/19 | 11 | Boss, Aaron J |  | 271.04
PR | 995 | 10/04/19 | 12 | Boss, Kyle A |  | 304.92
PR | 995 | 10/04/19 | 25 | Escalante Escobar, Boanerge |  | 177.02
PR | 995 | 10/04/19 | 41 | Hubbard, Robert W |  | 169.4
PR | 995 | 10/04/19 | 41 | Hubbard, Robert W |  | 127.05
PR | 995 | 10/04/19 | 47 | Lopez, Maslin A |  | 287.98
PR | 995 | 10/04/19 | 52 | McCabe, Thomas C |  | 518.79
PR | 995 | 10/04/19 | 54 | Montenegro, Carlos E |  | 525.14
PR | 995 | 10/04/19 | 62 | Roberts, Lake A |  | 372.68
PR | 995 | 10/04/19 | 63 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 10/04/19 | 64 | Romero Garza, Jesus I |  | 338.8
PR | 995 | 10/04/19 | 65 | Ross, Kelli M |  | 640.33
PR | 995 | 10/04/19 | 65 | Ross, Kelli M |  | 17.79
PR | 995 | 10/04/19 | 80 | Wilson, Garret A |  | 491.26
PR | 995 | 10/04/19 | 80 | Wilson, Garret A |  | 16.94
PR | 995 | 10/04/19 | 81 | Donelson, Richard T |  | 27.72
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/11/19 | 266 | Boss, Aaron J |  | 162.62
PR | 995 | 10/11/19 | 267 | Boss, Kyle A |  | 60.98
PR | 995 | 10/11/19 | 267 | Boss, Kyle A |  | 121.97
PR | 995 | 10/11/19 | 280 | Escalante Escobar, Boanerge |  | 372.68
PR | 995 | 10/11/19 | 296 | Hubbard, Robert W |  | 84.7
PR | 995 | 10/11/19 | 296 | Hubbard, Robert W |  | 296.45
PR | 995 | 10/11/19 | 296 | Hubbard, Robert W |  | 63.53
PR | 995 | 10/11/19 | 302 | Lopez, Maslin A |  | 287.98
PR | 995 | 10/11/19 | 307 | McCabe, Thomas C |  | 118.58
PR | 995 | 10/11/19 | 307 | McCabe, Thomas C |  | 474.32
PR | 995 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 33.88
PR | 995 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 22.02
PR | 995 | 10/11/19 | 316 | Roberts, Lake A |  | 93.17
PR | 995 | 10/11/19 | 316 | Roberts, Lake A |  | 223.61
PR | 995 | 10/11/19 | 317 | Rodriguez Arevalos, Christian |  | 440.44
PR | 995 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 135.52
PR | 995 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 122.82
PR | 995 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 67.76
PR | 995 | 10/11/19 | 320 | Ross, Kelli M |  | 604.76
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/18/19 | 460 | Boss, Aaron J |  | 271.04
PR | 995 | 10/18/19 | 461 | Boss, Kyle A |  | 106.72
PR | 995 | 10/18/19 | 461 | Boss, Kyle A |  | 76.23
PR | 995 | 10/18/19 | 461 | Boss, Kyle A |  | 121.97
PR | 995 | 10/18/19 | 473 | Escalante Escobar, Boanerge |  | 335.41
PR | 995 | 10/18/19 | 478 | Gerard, Jordan E |  | 45.74
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 105.88
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 127.05
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 63.53
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 317.63
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 21.18
PR | 995 | 10/18/19 | 495 | Lopez, Maslin A |  | 287.98
PR | 995 | 10/18/19 | 500 | McCabe, Thomas C |  | 74.11
PR | 995 | 10/18/19 | 500 | McCabe, Thomas C |  | 400.21
PR | 995 | 10/18/19 | 500 | McCabe, Thomas C |  | 74.11
PR | 995 | 10/18/19 | 509 | Roberts, Lake A |  | 37.27
PR | 995 | 10/18/19 | 509 | Roberts, Lake A |  | 186.34
PR | 995 | 10/18/19 | 509 | Roberts, Lake A |  | 149.07
PR | 995 | 10/18/19 | 510 | Rodriguez Arevalos, Christian |  | 352.35
PR | 995 | 10/18/19 | 511 | Romero Garza, Jesus I |  | 169.4
PR | 995 | 10/18/19 | 511 | Romero Garza, Jesus I |  | 110.11
PR | 995 | 10/18/19 | 513 | Ross, Kelli M |  | 569.18
PR | 995 | 10/18/19 | 521 | Vazquez Popoca, Jose N |  | 57.6
PR | 995 | 10/18/19 | 527 | Donelson, Richard T |  | 27.72
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/25/19 | 595 | Boss, Aaron J |  | 250.71
PR | 995 | 10/25/19 | 596 | Boss, Benjamin T |  | 162.62
PR | 995 | 10/25/19 | 597 | Boss, Kyle A |  | 182.95
PR | 995 | 10/25/19 | 597 | Boss, Kyle A |  | 38.12
PR | 995 | 10/25/19 | 597 | Boss, Kyle A |  | 60.98
PR | 995 | 10/25/19 | 608 | Escalante Escobar, Boanerge |  | 204.97
PR | 995 | 10/25/19 | 608 | Escalante Escobar, Boanerge |  | 74.54
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 317.63
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 42.35
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 169.4
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 84.7
PR | 995 | 10/25/19 | 630 | Lopez, Maslin A |  | 266.38
PR | 995 | 10/25/19 | 635 | McCabe, Thomas C |  | 489.14
PR | 995 | 10/25/19 | 635 | McCabe, Thomas C |  | 59.29
PR | 995 | 10/25/19 | 645 | Roberts, Lake A |  | 37.27
PR | 995 | 10/25/19 | 645 | Roberts, Lake A |  | 37.27
PR | 995 | 10/25/19 | 645 | Roberts, Lake A |  | 46.59
PR | 995 | 10/25/19 | 646 | Rodriguez Arevalos, Christian |  | 407.41
PR | 995 | 10/25/19 | 647 | Romero Garza, Jesus I |  | 177.87
PR | 995 | 10/25/19 | 647 | Romero Garza, Jesus I |  | 67.76
PR | 995 | 10/25/19 | 649 | Ross, Kelli M |  | 604.76
PR | 995 | 10/25/19 | 664 | Donelson, Richard T |  | 55.44
PR | 995 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 11/01/19 | 11 | Boss, Benjamin T |  | 271.04
PR | 995 | 11/01/19 | 12 | Boss, Kyle A |  | 71.15
PR | 995 | 11/01/19 | 12 | Boss, Kyle A |  | 213.44
PR | 995 | 11/01/19 | 12 | Boss, Kyle A |  | 71.15
PR | 995 | 11/01/19 | 19 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 11/01/19 | 24 | Escalante Escobar, Boanerge |  | 169.4
PR | 995 | 11/01/19 | 24 | Escalante Escobar, Boanerge |  | 254.1
PR | 995 | 11/01/19 | 40 | Hubbard, Robert W |  | 251.56
PR | 995 | 11/01/19 | 40 | Hubbard, Robert W |  | 68.61
PR | 995 | 11/01/19 | 40 | Hubbard, Robert W |  | 182.95
PR | 995 | 11/01/19 | 40 | Hubbard, Robert W |  | 22.87
PR | 995 | 11/01/19 | 40 | Hubbard, Robert W |  | 68.61
PR | 995 | 11/01/19 | 46 | Lopez, Maslin A |  | 321.86
PR | 995 | 11/01/19 | 51 | McCabe, Thomas C |  | 528.53
PR | 995 | 11/01/19 | 61 | Roberts, Lake A |  | 254.1
PR | 995 | 11/01/19 | 61 | Roberts, Lake A |  | 42.35
PR | 995 | 11/01/19 | 61 | Roberts, Lake A |  | 42.35
PR | 995 | 11/01/19 | 61 | Roberts, Lake A |  | 42.35
PR | 995 | 11/01/19 | 62 | Rodriguez Arevalos, Christian |  | 508.2
PR | 995 | 11/01/19 | 63 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 11/01/19 | 63 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 11/01/19 | 65 | Ross, Kelli M |  | 582.74
PR | 995 | 11/01/19 | 66 | Sanders, Allen O |  | 160.08
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 55.44
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 11/08/19 | 185 | Boss, Benjamin T |  | 108.42
PR | 995 | 11/08/19 | 185 | Boss, Benjamin T |  | 108.42
PR | 995 | 11/08/19 | 185 | Boss, Benjamin T |  | 54.21
PR | 995 | 11/08/19 | 186 | Boss, Kyle A |  | 71.15
PR | 995 | 11/08/19 | 186 | Boss, Kyle A |  | 71.15
PR | 995 | 11/08/19 | 186 | Boss, Kyle A |  | 71.15
PR | 995 | 11/08/19 | 186 | Boss, Kyle A |  | 71.15
PR | 995 | 11/08/19 | 192 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 11/08/19 | 193 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 11/08/19 | 193 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 211.75
PR | 995 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 84.7
PR | 995 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 127.05
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 68.61
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 22.87
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 274.43
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 365.9
PR | 995 | 11/08/19 | 220 | Lopez, Maslin A |  | 257.49
PR | 995 | 11/08/19 | 220 | Lopez, Maslin A |  | 64.37
PR | 995 | 11/08/19 | 225 | McCabe, Thomas C |  | 528.53
PR | 995 | 11/08/19 | 235 | Roberts, Lake A |  | 127.05
PR | 995 | 11/08/19 | 235 | Roberts, Lake A |  | 42.35
PR | 995 | 11/08/19 | 235 | Roberts, Lake A |  | 169.4
PR | 995 | 11/08/19 | 235 | Roberts, Lake A |  | 84.7
PR | 995 | 11/08/19 | 236 | Rodriguez Arevalos, Christian |  | 508.2
PR | 995 | 11/08/19 | 237 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 11/08/19 | 237 | Romero Garza, Jesus I |  | 155.85
PR | 995 | 11/08/19 | 239 | Ross, Kelli M |  | 437.05
PR | 995 | 11/08/19 | 239 | Ross, Kelli M |  | 291.37
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/15/19 | 445 | Boss, Benjamin T |  | 271.04
PR | 995 | 11/15/19 | 446 | Boss, Kyle A |  | 71.15
PR | 995 | 11/15/19 | 446 | Boss, Kyle A |  | 142.3
PR | 995 | 11/15/19 | 446 | Boss, Kyle A |  | 71.15
PR | 995 | 11/15/19 | 452 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 11/15/19 | 453 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 11/15/19 | 473 | Hubbard, Robert W |  | 137.21
PR | 995 | 11/15/19 | 473 | Hubbard, Robert W |  | 114.35
PR | 995 | 11/15/19 | 473 | Hubbard, Robert W |  | 320.17
PR | 995 | 11/15/19 | 473 | Hubbard, Robert W |  | 160.08
PR | 995 | 11/15/19 | 479 | Lopez, Maslin A |  | 257.49
PR | 995 | 11/15/19 | 479 | Lopez, Maslin A |  | 64.37
PR | 995 | 11/15/19 | 484 | McCabe, Thomas C |  | 660.66
PR | 995 | 11/15/19 | 494 | Roberts, Lake A |  | 254.1
PR | 995 | 11/15/19 | 495 | Rodriguez Arevalos, Christian |  | 406.56
PR | 995 | 11/15/19 | 496 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 11/15/19 | 498 | Ross, Kelli M |  | 291.37
PR | 995 | 11/15/19 | 506 | Vazquez Popoca, Jose N |  | 135.52
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/22/19 | 616 | Boss, Benjamin T |  | 108.42
PR | 995 | 11/22/19 | 616 | Boss, Benjamin T |  | 27.1
PR | 995 | 11/22/19 | 616 | Boss, Benjamin T |  | 54.21
PR | 995 | 11/22/19 | 617 | Boss, Kyle A |  | 195.66
PR | 995 | 11/22/19 | 617 | Boss, Kyle A |  | 142.3
PR | 995 | 11/22/19 | 623 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 11/22/19 | 623 | Cruz Gonzalez, Julio C |  | 166.01
PR | 995 | 11/22/19 | 644 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/22/19 | 644 | Hubbard, Robert W |  | 114.35
PR | 995 | 11/22/19 | 644 | Hubbard, Robert W |  | 251.56
PR | 995 | 11/22/19 | 650 | Lopez, Maslin A |  | 257.49
PR | 995 | 11/22/19 | 650 | Lopez, Maslin A |  | 48.28
PR | 995 | 11/22/19 | 655 | McCabe, Thomas C |  | 280.78
PR | 995 | 11/22/19 | 655 | McCabe, Thomas C |  | 132.13
PR | 995 | 11/22/19 | 665 | Roberts, Lake A |  | 31.76
PR | 995 | 11/22/19 | 665 | Roberts, Lake A |  | 31.76
PR | 995 | 11/22/19 | 665 | Roberts, Lake A |  | 148.23
PR | 995 | 11/22/19 | 665 | Roberts, Lake A |  | 21.18
PR | 995 | 11/22/19 | 666 | Rodriguez Arevalos, Christian |  | 406.56
PR | 995 | 11/22/19 | 666 | Rodriguez Arevalos, Christian |  | 76.23
PR | 995 | 11/22/19 | 667 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 11/22/19 | 667 | Romero Garza, Jesus I |  | 58.44
PR | 995 | 11/22/19 | 670 | Sanders, Allen O |  | 91.48
PR | 995 | 11/27/19 | 850 | Boss, Benjamin T |  | 27.1
PR | 995 | 11/27/19 | 850 | Boss, Benjamin T |  | 108.42
PR | 995 | 11/27/19 | 850 | Boss, Benjamin T |  | 108.42
PR | 995 | 11/27/19 | 851 | Boss, Kyle A |  | 106.72
PR | 995 | 11/27/19 | 851 | Boss, Kyle A |  | 71.15
PR | 995 | 11/27/19 | 851 | Boss, Kyle A |  | 71.15
PR | 995 | 11/27/19 | 851 | Boss, Kyle A |  | 71.15
PR | 995 | 11/27/19 | 857 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 11/27/19 | 878 | Hubbard, Robert W |  | 457.38
PR | 995 | 11/27/19 | 878 | Hubbard, Robert W |  | 228.69
PR | 995 | 11/27/19 | 889 | McCabe, Thomas C |  | 644.14
PR | 995 | 11/27/19 | 899 | Roberts, Lake A |  | 84.7
PR | 995 | 11/27/19 | 899 | Roberts, Lake A |  | 254.1
PR | 995 | 11/27/19 | 899 | Roberts, Lake A |  | 84.7
PR | 995 | 11/27/19 | 900 | Rodriguez Arevalos, Christian |  | 101.64
PR | 995 | 11/27/19 | 901 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 11/27/19 | 901 | Romero Garza, Jesus I |  | 155.85
PR | 995 | 11/27/19 | 904 | Sanders, Allen O |  | 205.82
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/06/19 | 36 | Boss, Benjamin T |  | 108.42
PR | 995 | 12/06/19 | 36 | Boss, Benjamin T |  | 54.21
PR | 995 | 12/06/19 | 37 | Boss, Kyle A |  | 213.44
PR | 995 | 12/06/19 | 43 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 12/06/19 | 65 | Hubbard, Robert W |  | 251.56
PR | 995 | 12/06/19 | 76 | McCabe, Thomas C |  | 330.33
PR | 995 | 12/06/19 | 76 | McCabe, Thomas C |  | 132.13
PR | 995 | 12/06/19 | 86 | Roberts, Lake A |  | 137.64
PR | 995 | 12/06/19 | 86 | Roberts, Lake A |  | 84.7
PR | 995 | 12/06/19 | 87 | Rodriguez Arevalos, Christian |  | 63.53
PR | 995 | 12/06/19 | 88 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 12/06/19 | 88 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 12/06/19 | 91 | Sanders, Allen O |  | 125.78
PR | 995 | 12/13/19 | 397 | Boss, Benjamin T |  | 271.04
PR | 995 | 12/13/19 | 398 | Boss, Kyle A |  | 355.74
PR | 995 | 12/13/19 | 404 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 182.95
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 182.95
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 45.74
PR | 995 | 12/13/19 | 437 | McCabe, Thomas C |  | 280.78
PR | 995 | 12/13/19 | 447 | Roberts, Lake A |  | 423.5
PR | 995 | 12/13/19 | 449 | Romero Garza, Jesus I |  | 331.18
PR | 995 | 12/13/19 | 452 | Sanders, Allen O |  | 57.17
PR | 995 | 12/13/19 | 465 | Donelson, Richard T |  | 138.59
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/20/19 | 550 | Boss, Benjamin T |  | 271.04
PR | 995 | 12/20/19 | 551 | Boss, Kyle A |  | 355.74
PR | 995 | 12/20/19 | 579 | Hubbard, Robert W |  | 68.61
PR | 995 | 12/20/19 | 579 | Hubbard, Robert W |  | 22.87
PR | 995 | 12/20/19 | 579 | Hubbard, Robert W |  | 91.48
PR | 995 | 12/20/19 | 590 | McCabe, Thomas C |  | 132.13
PR | 995 | 12/20/19 | 600 | Roberts, Lake A |  | 169.4
PR | 995 | 12/20/19 | 602 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 12/20/19 | 605 | Sanders, Allen O |  | 114.35
PR | 995 | 12/20/19 | 618 | Donelson, Richard T |  | 83.16
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/27/19 | 707 | Boss, Benjamin T |  | 54.21
PR | 995 | 12/27/19 | 708 | Boss, Kyle A |  | 142.3
PR | 995 | 12/27/19 | 708 | Boss, Kyle A |  | 71.15
PR | 995 | 12/27/19 | 737 | Hubbard, Robert W |  | 45.74
PR | 995 | 12/27/19 | 737 | Hubbard, Robert W |  | 182.95
PR | 995 | 12/27/19 | 748 | McCabe, Thomas C |  | 181.68
PR | 995 | 12/27/19 | 748 | McCabe, Thomas C |  | 33.03
PR | 995 | 12/27/19 | 758 | Roberts, Lake A |  | 127.05
PR | 995 | 12/27/19 | 760 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 12/27/19 | 763 | Sanders, Allen O |  | 91.48
PR | 995 | 12/27/19 | 776 | Donelson, Richard T |  | 83.16
PR | 995 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/03/20 | 10 | Boss, Benjamin T |  | 142.3
PR | 995 | 01/03/20 | 11 | Boss, Kyle A |  | 186.76
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 137.21
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 91.48
PR | 995 | 01/03/20 | 51 | McCabe, Thomas C |  | 264.26
PR | 995 | 01/03/20 | 61 | Roberts, Lake A |  | 222.34
PR | 995 | 01/03/20 | 63 | Romero Garza, Jesus I |  | 204.55
PR | 995 | 01/03/20 | 66 | Sanders, Allen O |  | 91.48
PR | 995 | 01/03/20 | 81 | Donelson, Richard T |  | 55.44
PR | 995 | 01/10/20 | 283 | Boss, Benjamin T |  | 271.04
PR | 995 | 01/10/20 | 284 | Boss, Kyle A |  | 355.74
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 102.91
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 34.3
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 45.74
PR | 995 | 01/10/20 | 334 | Roberts, Lake A |  | 248.81
PR | 995 | 01/10/20 | 334 | Roberts, Lake A |  | 42.35
PR | 995 | 01/10/20 | 336 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 01/10/20 | 339 | Sanders, Allen O |  | 228.69
PR | 995 | 01/10/20 | 352 | Donelson, Richard T |  | 166.31
PR | 995 | 01/17/20 | 549 | Boss, Benjamin T |  | 169.4
PR | 995 | 01/17/20 | 550 | Boss, Kyle A |  | 293.49
PR | 995 | 01/17/20 | 556 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 01/17/20 | 579 | Hubbard, Robert W |  | 22.87
PR | 995 | 01/17/20 | 600 | Roberts, Lake A |  | 21.18
PR | 995 | 01/17/20 | 600 | Roberts, Lake A |  | 169.4
PR | 995 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 01/17/20 | 605 | Sanders, Allen O |  | 240.12
PR | 995 | 01/17/20 | 618 | Donelson, Richard T |  | 27.72
PR | 995 | 01/24/20 | 682 | Boss, Benjamin T |  | 243.94
PR | 995 | 01/24/20 | 682 | Boss, Benjamin T |  | 27.1
PR | 995 | 01/24/20 | 683 | Boss, Kyle A |  | 293.49
PR | 995 | 01/24/20 | 683 | Boss, Kyle A |  | 62.25
PR | 995 | 01/24/20 | 711 | Hubbard, Robert W |  | 45.74
PR | 995 | 01/24/20 | 711 | Hubbard, Robert W |  | 68.61
PR | 995 | 01/24/20 | 736 | Sanders, Allen O |  | 217.26
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 83.16
PR | 995 | 01/31/20 | 841 | Boss, Benjamin T |  | 271.04
PR | 995 | 01/31/20 | 842 | Boss, Kyle A |  | 355.74
PR | 995 | 01/31/20 | 871 | Hubbard, Robert W |  | 22.87
PR | 995 | 01/31/20 | 892 | Roberts, Lake A |  | 169.4
PR | 995 | 01/31/20 | 892 | Roberts, Lake A |  | 84.7
PR | 995 | 01/31/20 | 897 | Sanders, Allen O |  | 377.34
PR | 995 | 01/31/20 | 903 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 01/31/20 | 911 | Donelson, Richard T |  | 110.88
PR | 995 | 02/07/20 | 32 | Boss, Benjamin T |  | 271.04
PR | 995 | 02/07/20 | 33 | Boss, Kyle A |  | 355.74
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 114.35
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/07/20 | 82 | Roberts, Lake A |  | 381.15
PR | 995 | 02/07/20 | 88 | Sanders, Allen O |  | 274.43
PR | 995 | 02/07/20 | 94 | Trower-Kelly, Fidel D |  | 213.44
PR | 995 | 02/07/20 | 102 | Donelson, Richard T |  | 110.88
PR | 995 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 02/14/20 | 242 | Boss, Benjamin T |  | 243.94
PR | 995 | 02/14/20 | 243 | Boss, Kyle A |  | 284.59
PR | 995 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 137.21
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 91.48
PR | 995 | 02/14/20 | 281 | McCabe, Thomas C |  | 82.58
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 52.94
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 31.76
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 42.35
PR | 995 | 02/14/20 | 298 | Sanders, Allen O |  | 114.35
PR | 995 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 02/14/20 | 312 | Donelson, Richard T |  | 27.72
PR | 995 | 02/21/20 | 459 | Boss, Benjamin T |  | 182.95
PR | 995 | 02/21/20 | 460 | Boss, Kyle A |  | 213.44
PR | 995 | 02/21/20 | 514 | Sanders, Allen O |  | 331.6
PR | 995 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 213.44
PR | 995 | 02/21/20 | 528 | Donelson, Richard T |  | 55.44
PR | 995 | 02/28/20 | 687 | Boss, Benjamin T |  | 182.95
PR | 995 | 02/28/20 | 688 | Boss, Kyle A |  | 186.76
PR | 995 | 02/28/20 | 696 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 02/28/20 | 716 | Hubbard, Robert W |  | 228.69
PR | 995 | 02/28/20 | 716 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/28/20 | 716 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/28/20 | 725 | McCabe, Thomas C |  | 222.97
PR | 995 | 02/28/20 | 725 | McCabe, Thomas C |  | 66.07
PR | 995 | 02/28/20 | 725 | McCabe, Thomas C |  | 66.07
PR | 995 | 02/28/20 | 725 | McCabe, Thomas C |  | 264.26
PR | 995 | 02/28/20 | 737 | Roberts, Lake A |  | 84.7
PR | 995 | 02/28/20 | 737 | Roberts, Lake A |  | 84.7
PR | 995 | 02/28/20 | 737 | Roberts, Lake A |  | 169.4
PR | 995 | 02/28/20 | 739 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 02/28/20 | 743 | Sanders, Allen O |  | 320.17
PR | 995 | 02/28/20 | 749 | Trower-Kelly, Fidel D |  | 213.44
PR | 995 | 02/28/20 | 757 | Donelson, Richard T |  | 83.16
PR | 995 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 03/06/20 | 50 | Boss, Kyle A |  | 213.44
PR | 995 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 03/06/20 | 78 | Hubbard, Robert W |  | 251.56
PR | 995 | 03/06/20 | 78 | Hubbard, Robert W |  | 45.74
PR | 995 | 03/06/20 | 87 | McCabe, Thomas C |  | 396.4
PR | 995 | 03/06/20 | 87 | McCabe, Thomas C |  | 82.58
PR | 995 | 03/06/20 | 87 | McCabe, Thomas C |  | 82.58
PR | 995 | 03/06/20 | 99 | Roberts, Lake A |  | 254.1
PR | 995 | 03/06/20 | 99 | Roberts, Lake A |  | 52.94
PR | 995 | 03/06/20 | 99 | Roberts, Lake A |  | 84.7
PR | 995 | 03/06/20 | 101 | Romero Garza, Jesus I |  | 155.85
PR | 995 | 03/06/20 | 105 | Sanders, Allen O |  | 377.34
PR | 995 | 03/06/20 | 119 | Donelson, Richard T |  | 110.88
PR | 995 | 03/13/20 | 351 | McCabe, Thomas C |  | 396.4
PR | 995 | 03/13/20 | 363 | Roberts, Lake A |  | 254.1
PR | 995 | 03/13/20 | 369 | Sanders, Allen O |  | 388.77
PR | 995 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 142.3
PR | 995 | 03/20/20 | 572 | Boss, Benjamin T |  | 243.94
PR | 995 | 03/20/20 | 573 | Boss, Kyle A |  | 284.59
PR | 995 | 03/20/20 | 579 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 03/20/20 | 581 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 03/20/20 | 585 | Eliassen, Cory H |  | 50.82
PR | 995 | 03/20/20 | 623 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 03/20/20 | 627 | Sanders, Allen O |  | 217.26
PR | 995 | 03/20/20 | 633 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 03/20/20 | 641 | Donelson, Richard T |  | 83.16
PR | 995 | 03/26/20 | 803 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 03/26/20 | 806 | Sanders, Allen O |  | 171.52
PR | 995 | 03/26/20 | 812 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 04/03/20 | 42 | Donelson, Richard T |  | 27.72
PR | 995 | 04/17/20 | 288 | Donelson, Richard T |  | 27.72
PR | 995 | 04/24/20 | 424 | Donelson, Richard T |  | 27.72
PR | 995 | 05/01/20 | 64 | Sanders, Allen O |  | 68.61
PR | 995 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 05/08/20 | 161 | Boss, Kyle A |  | 355.74
PR | 995 | 05/08/20 | 167 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 05/08/20 | 188 | Hubbard, Robert W |  | 91.48
PR | 995 | 05/08/20 | 215 | Sanders, Allen O |  | 343.04
PR | 995 | 05/08/20 | 221 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 05/08/20 | 231 | Donelson, Richard T |  | 55.44
PR | 995 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 05/15/20 | 315 | Boss, Benjamin T |  | 121.97
PR | 995 | 05/15/20 | 316 | Boss, Kyle A |  | 355.74
PR | 995 | 05/15/20 | 322 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 05/15/20 | 324 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 05/15/20 | 328 | Eliassen, Cory H |  | 203.28
PR | 995 | 05/15/20 | 343 | Hubbard, Robert W |  | 91.48
PR | 995 | 05/15/20 | 343 | Hubbard, Robert W |  | 68.61
PR | 995 | 05/15/20 | 366 | Romero Garza, Jesus I |  | 155.85
PR | 995 | 05/15/20 | 370 | Sanders, Allen O |  | 663.2
PR | 995 | 05/15/20 | 376 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 05/15/20 | 384 | Donelson, Richard T |  | 55.44
PR | 995 | 05/22/20 | 470 | Boss, Benjamin T |  | 182.95
PR | 995 | 05/22/20 | 477 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 05/22/20 | 479 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 05/22/20 | 483 | Eliassen, Cory H |  | 101.64
PR | 995 | 05/22/20 | 517 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 05/22/20 | 520 | Sanders, Allen O |  | 674.64
PR | 995 | 05/22/20 | 526 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 05/22/20 | 534 | Donelson, Richard T |  | 55.44
PR | 995 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 05/29/20 | 598 | Boss, Benjamin T |  | 60.98
PR | 995 | 05/29/20 | 646 | Sanders, Allen O |  | 503.12
PR | 995 | 05/29/20 | 652 | Trower-Kelly, Fidel D |  | 213.44
PR | 995 | 05/29/20 | 659 | Donelson, Richard T |  | 27.72
PR | 995 | 06/05/20 | 19 | Boss, Benjamin T |  | 60.98
PR | 995 | 06/05/20 | 58 | Sanders, Allen O |  | 571.73
PR | 995 | 06/05/20 | 62 | Trower-Kelly, Fidel D |  | 213.44
PR | 995 | 06/05/20 | 66 | Donelson, Richard T |  | 27.72
PR | 995 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/12/20 | 260 | Sanders, Allen O |  | 457.38
PR | 995 | 06/19/20 | 399 | Hubbard, Robert W |  | 68.61
PR | 995 | 06/19/20 | 416 | Sanders, Allen O |  | 400.21
PR | 995 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/26/20 | 541 | Hubbard, Robert W |  | 45.74
PR | 995 | 07/02/20 | 44 | Sanders, Allen O |  | 137.21
PR | 995 | 07/02/20 | 44 | Sanders, Allen O |  | 68.61
PR | 995 | 07/02/20 | 50 | Donelson, Richard T |  | 55.44
PR | 995 | 07/10/20 | 182 | Donelson, Richard T |  | 27.72
PR | 995 | 07/24/20 | 442 | Sanders, Allen O |  | 45.74
PR | 995 | 07/31/20 | 537 | Sanders, Allen O |  | 45.74
PR | 998 | 03/02/18 | 67 | Donelson, Richard T |  | 4.78
PR | 998 | 03/09/18 | 184 | Gerard, Jeffrey S |  | 3.6
PR | 998 | 03/23/18 | 583 | Donelson, Richard T |  | 4.78
PR | 998 | 03/23/18 | 584 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 03/30/18 | 811 | Donelson, Richard T |  | 4.78
PR | 998 | 03/30/18 | 812 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 04/27/18 | 684 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 05/11/18 | 286 | Donelson, Richard T |  | 4.78
PR | 998 | 06/08/18 | 339 | Donelson, Richard T |  | 4.78
PR | 998 | 06/15/18 | 527 | Donelson, Richard T |  | 4.78
PR | 998 | 06/22/18 | 753 | Donelson, Richard T |  | 9.56
PR | 998 | 06/29/18 | 1020 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/13/18 | 367 | Donelson, Richard T |  | 19.13
PR | 998 | 07/13/18 | 368 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/20/18 | 507 | Donelson, Richard T |  | 14.34
PR | 998 | 07/27/18 | 834 | Donelson, Richard T |  | 33.47
PR | 998 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/17/18 | 550 | Donelson, Richard T |  | 9.56
PR | 998 | 08/31/18 | 1069 | Donelson, Richard T |  | 4.78
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 09/07/18 | 105 | Donelson, Richard T |  | 47.81
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/14/18 | 340 | Donelson, Richard T |  | 19.13
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 15.3
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/21/18 | 552 | Donelson, Richard T |  | 4.78
PR | 998 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 15.3
PR | 998 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/28/18 | 739 | Donelson, Richard T |  | 14.34
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/05/18 | 102 | Donelson, Richard T |  | 19.13
PR | 998 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 10/12/18 | 276 | Lovo, German G |  | 40.39
PR | 998 | 10/12/18 | 286 | Quintanilla, Esteban R |  | 82.62
PR | 998 | 10/12/18 | 291 | Rivera, Eli P |  | 33.05
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 19.13
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/19/18 | 474 | Lovo, German G |  | 44.06
PR | 998 | 10/19/18 | 484 | Quintanilla, Esteban R |  | 103.28
PR | 998 | 10/19/18 | 489 | Rivera, Eli P |  | 49.57
PR | 998 | 10/19/18 | 507 | Donelson, Richard T |  | 4.78
PR | 998 | 10/19/18 | 508 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/19/18 | 508 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/26/18 | 703 | Ascencio, Jose L |  | 7.96
PR | 998 | 10/26/18 | 740 | Lovo, German G |  | 42.23
PR | 998 | 10/26/18 | 749 | Quintanilla, Esteban R |  | 123.93
PR | 998 | 10/26/18 | 754 | Rivera, Eli P |  | 8.26
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 15.3
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 11/02/18 | 2 | Quintanilla, Esteban R |  | 134.26
PR | 998 | 11/02/18 | 45 | Lovo, German G |  | 51.41
PR | 998 | 11/02/18 | 58 | Rivera, Eli P |  | 12.39
PR | 998 | 11/02/18 | 58 | Rivera, Eli P |  | 61.97
PR | 998 | 11/02/18 | 74 | Wilson, Garret A |  | 21.42
PR | 998 | 11/02/18 | 76 | Donelson, Richard T |  | 4.78
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/09/18 | 191 | Cornejo Orellana, Carlos E |  | 26.16
PR | 998 | 11/09/18 | 223 | Lovo, German G |  | 5.51
PR | 998 | 11/09/18 | 223 | Lovo, German G |  | 55.08
PR | 998 | 11/09/18 | 232 | Quintanilla, Esteban R |  | 137.7
PR | 998 | 11/09/18 | 232 | Quintanilla, Esteban R |  | 10.33
PR | 998 | 11/09/18 | 237 | Rivera, Eli P |  | 12.39
PR | 998 | 11/09/18 | 257 | Donelson, Richard T |  | 9.56
PR | 998 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/16/18 | 437 | Benites Portillo, Marvin E |  | 13.46
PR | 998 | 11/16/18 | 440 | Cornejo Orellana, Carlos E |  | 4.36
PR | 998 | 11/16/18 | 440 | Cornejo Orellana, Carlos E |  | 14.54
PR | 998 | 11/16/18 | 471 | Lovo, German G |  | 33.05
PR | 998 | 11/16/18 | 480 | Quintanilla, Esteban R |  | 10.33
PR | 998 | 11/16/18 | 480 | Quintanilla, Esteban R |  | 103.28
PR | 998 | 11/16/18 | 506 | Quintanilla, Esteban R |  | -10.33
PR | 998 | 11/16/18 | 506 | Quintanilla, Esteban R |  | -103.28
PR | 998 | 11/16/18 | 509 | Quintanilla, Esteban R |  | 10.33
PR | 998 | 11/16/18 | 509 | Quintanilla, Esteban R |  | 103.28
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 19.13
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/21/18 | 623 | Benites Portillo, Marvin E |  | 16.83
PR | 998 | 11/21/18 | 655 | Lovo, German G |  | 40.39
PR | 998 | 11/21/18 | 655 | Lovo, German G |  | 18.36
PR | 998 | 11/21/18 | 664 | Quintanilla, Esteban R |  | 55.08
PR | 998 | 11/21/18 | 664 | Quintanilla, Esteban R |  | 41.31
PR | 998 | 11/21/18 | 685 | Wilson, Garret A |  | 64.26
PR | 998 | 11/21/18 | 687 | Quintanilla, Esteban R |  | -55.08
PR | 998 | 11/21/18 | 687 | Quintanilla, Esteban R |  | -41.31
PR | 998 | 11/21/18 | 688 | Quintanilla, Esteban R |  | 55.08
PR | 998 | 11/21/18 | 688 | Quintanilla, Esteban R |  | 41.31
PR | 998 | 11/21/18 | 689 | Donelson, Richard T |  | 23.91
PR | 998 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/30/18 | 868 | Lovo, German G |  | 34.43
PR | 998 | 11/30/18 | 877 | Quintanilla, Esteban R |  | 46.74
PR | 998 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 12/07/18 | 44 | Ascencio, Jose L |  | 19.28
PR | 998 | 12/07/18 | 80 | Lovo, German G |  | 30.6
PR | 998 | 12/07/18 | 89 | Quintanilla, Esteban R |  | 68.31
PR | 998 | 12/07/18 | 95 | Rivera, Jorge A |  | -5.05
PR | 998 | 12/07/18 | 98 | Ross, Kelli M |  | -6.12
PR | 998 | 12/07/18 | 113 | Donelson, Richard T |  | 38.25
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 12/07/18 | 123 | Ascencio, Jose L |  | -19.28
PR | 998 | 12/07/18 | 125 | Rivera, Jorge A |  | 5.05
PR | 998 | 12/07/18 | 126 | Ross, Kelli M |  | 6.12
PR | 998 | 12/07/18 | 129 | Wilson, Garret A |  | -85.68
PR | 998 | 12/14/18 | 304 | Lovo, German G |  | 43.99
PR | 998 | 12/14/18 | 314 | Quintanilla, Esteban R |  | 17.98
PR | 998 | 12/14/18 | 334 | Waites, Thaddeus Z |  | 19.74
PR | 998 | 12/14/18 | 337 | Donelson, Richard T |  | 19.13
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/21/18 | 554 | Quintanilla, Esteban R |  | 7.19
PR | 998 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 19.89
PR | 998 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 12/28/18 | 684 | Lovo, German G |  | 9.56
PR | 998 | 12/28/18 | 768 | Donelson, Richard T |  | 4.78
PR | 998 | 12/28/18 | 769 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 01/04/19 | 72 | Donelson, Richard T |  | 9.56
PR | 998 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 01/11/19 | 281 | Donelson, Richard T |  | 14.34
PR | 998 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/18/19 | 513 | Quintanilla, Esteban R |  | 10.79
PR | 998 | 01/18/19 | 542 | Donelson, Richard T |  | 14.34
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/25/19 | 748 | Hubbard, Robert W |  | 44.98
PR | 998 | 01/25/19 | 756 | McCabe, Thomas C |  | 40.39
PR | 998 | 01/25/19 | 760 | Paco Leyva, Orlando |  | 25.47
PR | 998 | 01/25/19 | 762 | Quintanilla, Esteban R |  | 14.38
PR | 998 | 01/25/19 | 773 | Sepulveda Gonzalez, Alfredo |  | 39.17
PR | 998 | 01/25/19 | 786 | Donelson, Richard T |  | 28.69
PR | 998 | 02/01/19 | 36 | Hubbard, Robert W |  | 65.6
PR | 998 | 02/01/19 | 44 | McCabe, Thomas C |  | 15.15
PR | 998 | 02/01/19 | 47 | Paco Leyva, Orlando |  | 11.32
PR | 998 | 02/01/19 | 49 | Ramos Herrera, Franklin J |  | 7.04
PR | 998 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo |  | 19.58
PR | 998 | 02/01/19 | 58 | Sepulveda Gonzalez, Alfredo |  | 19.58
PR | 998 | 02/01/19 | 70 | Donelson, Richard T |  | 23.91
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 5.97
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/08/19 | 191 | Hubbard, Robert W |  | 37.49
PR | 998 | 02/08/19 | 199 | McCabe, Thomas C |  | 40.39
PR | 998 | 02/08/19 | 202 | Paco Leyva, Orlando |  | 11.32
PR | 998 | 02/08/19 | 204 | Ramos Herrera, Franklin J |  | 7.04
PR | 998 | 02/08/19 | 214 | Sepulveda Gonzalez, Alfredo |  | 39.17
PR | 998 | 02/08/19 | 226 | Donelson, Richard T |  | 9.56
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/15/19 | 353 | Hubbard, Robert W |  | 22.49
PR | 998 | 02/15/19 | 361 | McCabe, Thomas C |  | 59.33
PR | 998 | 02/15/19 | 376 | Sepulveda Gonzalez, Alfredo |  | 22.03
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 5.97
PR | 998 | 02/22/19 | 611 | Hubbard, Robert W |  | 43.11
PR | 998 | 02/22/19 | 619 | McCabe, Thomas C |  | 30.29
PR | 998 | 02/22/19 | 625 | Ramos Herrera, Franklin J |  | 14.08
PR | 998 | 02/22/19 | 635 | Sepulveda Gonzalez, Alfredo |  | 29.38
PR | 998 | 02/22/19 | 647 | Donelson, Richard T |  | 4.78
PR | 998 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/01/19 | 38 | Hubbard, Robert W |  | 9.37
PR | 998 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 7.04
PR | 998 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 14.08
PR | 998 | 03/01/19 | 73 | Wilson, Garret A |  | 39.63
PR | 998 | 03/01/19 | 73 | Wilson, Garret A |  | 2.83
PR | 998 | 03/01/19 | 74 | Donelson, Richard T |  | 9.56
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/08/19 | 278 | Hubbard, Robert W |  | 7.5
PR | 998 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 12.32
PR | 998 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 28.15
PR | 998 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 12.32
PR | 998 | 03/08/19 | 313 | Wilson, Garret A |  | 14.15
PR | 998 | 03/08/19 | 313 | Wilson, Garret A |  | 36.8
PR | 998 | 03/08/19 | 313 | Wilson, Garret A |  | 19.81
PR | 998 | 03/08/19 | 314 | Donelson, Richard T |  | 4.78
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 525 | Hubbard, Robert W |  | 7.5
PR | 998 | 03/15/19 | 545 | Rodriguez Arevalos, Christian |  | 36.95
PR | 998 | 03/15/19 | 561 | Wilson, Garret A |  | 28.31
PR | 998 | 03/15/19 | 561 | Wilson, Garret A |  | 25.47
PR | 998 | 03/15/19 | 562 | Donelson, Richard T |  | 14.34
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/22/19 | 709 | Barbosa, Michael S |  | 5.74
PR | 998 | 03/22/19 | 709 | Barbosa, Michael S |  | 15.3
PR | 998 | 03/22/19 | 739 | Hubbard, Robert W |  | 3.75
PR | 998 | 03/22/19 | 739 | Hubbard, Robert W |  | 11.25
PR | 998 | 03/22/19 | 758 | Rodriguez Arevalos, Christian |  | 59.82
PR | 998 | 03/22/19 | 775 | Wilson, Garret A |  | 72.18
PR | 998 | 03/22/19 | 775 | Wilson, Garret A |  | 16.98
PR | 998 | 03/22/19 | 776 | Donelson, Richard T |  | 23.91
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/22/19 | 780 | Hubbard, Robert W |  | 3.75
PR | 998 | 03/22/19 | 780 | Hubbard, Robert W |  | 11.25
PR | 998 | 03/22/19 | 781 | Hubbard, Robert W |  | -3.75
PR | 998 | 03/22/19 | 781 | Hubbard, Robert W |  | -11.25
PR | 998 | 03/29/19 | 920 | Barbosa, Michael S |  | 8.61
PR | 998 | 03/29/19 | 920 | Barbosa, Michael S |  | 14.34
PR | 998 | 03/29/19 | 920 | Barbosa, Michael S |  | 49.73
PR | 998 | 03/29/19 | 920 | Barbosa, Michael S |  | 26.78
PR | 998 | 03/29/19 | 938 | Foster, Antonio T |  | 42.15
PR | 998 | 03/29/19 | 938 | Foster, Antonio T |  | 1.45
PR | 998 | 03/29/19 | 951 | Hubbard, Robert W |  | 3.75
PR | 998 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 5.05
PR | 998 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 5.05
PR | 998 | 03/29/19 | 952 | Jimenez Alvarenga, Gerson M |  | 26.93
PR | 998 | 03/29/19 | 970 | Rodriguez Arevalos, Christian |  | 63.34
PR | 998 | 03/29/19 | 970 | Rodriguez Arevalos, Christian |  | 3.52
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 21.23
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 4.25
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 8.49
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 48.12
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 11.32
PR | 998 | 03/29/19 | 987 | Wilson, Garret A |  | 53.78
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/29/19 | 992 | Barbosa, Michael S |  | -8.61
PR | 998 | 03/29/19 | 992 | Barbosa, Michael S |  | -14.34
PR | 998 | 03/29/19 | 992 | Barbosa, Michael S |  | -49.73
PR | 998 | 03/29/19 | 992 | Barbosa, Michael S |  | -26.78
PR | 998 | 03/29/19 | 993 | Barbosa, Michael S |  | 8.61
PR | 998 | 03/29/19 | 993 | Barbosa, Michael S |  | 14.34
PR | 998 | 03/29/19 | 993 | Barbosa, Michael S |  | 49.73
PR | 998 | 03/29/19 | 993 | Barbosa, Michael S |  | 26.78
PR | 998 | 04/05/19 | 82 | Barbosa, Michael S |  | 22.95
PR | 998 | 04/05/19 | 82 | Barbosa, Michael S |  | 76.5
PR | 998 | 04/05/19 | 100 | Foster, Antonio T |  | 13.08
PR | 998 | 04/05/19 | 100 | Foster, Antonio T |  | 4.36
PR | 998 | 04/05/19 | 100 | Foster, Antonio T |  | 46.51
PR | 998 | 04/05/19 | 100 | Foster, Antonio T |  | 11.63
PR | 998 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M |  | 20.2
PR | 998 | 04/05/19 | 115 | Jimenez Alvarenga, Gerson M |  | 67.32
PR | 998 | 04/05/19 | 133 | Rodriguez Arevalos, Christian |  | 21.11
PR | 998 | 04/05/19 | 133 | Rodriguez Arevalos, Christian |  | 70.38
PR | 998 | 04/05/19 | 134 | Ross, Kelli M |  | 27.54
PR | 998 | 04/05/19 | 134 | Ross, Kelli M |  | 73.44
PR | 998 | 04/05/19 | 150 | Wilson, Garret A |  | 14.86
PR | 998 | 04/05/19 | 150 | Wilson, Garret A |  | 12.74
PR | 998 | 04/05/19 | 150 | Wilson, Garret A |  | 31.14
PR | 998 | 04/05/19 | 150 | Wilson, Garret A |  | 5.66
PR | 998 | 04/05/19 | 150 | Wilson, Garret A |  | 76.42
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 5.74
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 11.48
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 5.74
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 30.6
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 30.6
PR | 998 | 04/12/19 | 326 | Barbosa, Michael S |  | 15.3
PR | 998 | 04/12/19 | 344 | Foster, Antonio T |  | 13.08
PR | 998 | 04/12/19 | 344 | Foster, Antonio T |  | 4.36
PR | 998 | 04/12/19 | 344 | Foster, Antonio T |  | 34.88
PR | 998 | 04/12/19 | 344 | Foster, Antonio T |  | 11.63
PR | 998 | 04/12/19 | 344 | Foster, Antonio T |  | 11.63
PR | 998 | 04/12/19 | 357 | Hubbard, Robert W |  | 26.78
PR | 998 | 04/12/19 | 357 | Hubbard, Robert W |  | 7.65
PR | 998 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M |  | 20.2
PR | 998 | 04/12/19 | 358 | Jimenez Alvarenga, Gerson M |  | 67.32
PR | 998 | 04/12/19 | 362 | Lopez, Maslin A |  | 36.72
PR | 998 | 04/12/19 | 377 | Rodriguez Arevalos, Christian |  | 70.38
PR | 998 | 04/12/19 | 378 | Ross, Kelli M |  | 38.56
PR | 998 | 04/12/19 | 378 | Ross, Kelli M |  | 128.52
PR | 998 | 04/12/19 | 395 | Wilson, Garret A |  | 18.36
PR | 998 | 04/12/19 | 395 | Wilson, Garret A |  | 6.12
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/19/19 | 523 | Barbosa, Michael S |  | 5.74
PR | 998 | 04/19/19 | 523 | Barbosa, Michael S |  | 15.3
PR | 998 | 04/19/19 | 523 | Barbosa, Michael S |  | 15.3
PR | 998 | 04/19/19 | 541 | Foster, Antonio T |  | 13.08
PR | 998 | 04/19/19 | 541 | Foster, Antonio T |  | 4.36
PR | 998 | 04/19/19 | 541 | Foster, Antonio T |  | 46.51
PR | 998 | 04/19/19 | 541 | Foster, Antonio T |  | 11.63
PR | 998 | 04/19/19 | 555 | Hubbard, Robert W |  | 22.95
PR | 998 | 04/19/19 | 555 | Hubbard, Robert W |  | 5.74
PR | 998 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M |  | 20.2
PR | 998 | 04/19/19 | 556 | Jimenez Alvarenga, Gerson M |  | 67.32
PR | 998 | 04/19/19 | 560 | Lopez, Maslin A |  | 14.69
PR | 998 | 04/19/19 | 560 | Lopez, Maslin A |  | 48.96
PR | 998 | 04/19/19 | 566 | Montenegro, Carlos E |  | 13.31
PR | 998 | 04/19/19 | 566 | Montenegro, Carlos E |  | 35.5
PR | 998 | 04/19/19 | 575 | Rodriguez Arevalos, Christian |  | 70.38
PR | 998 | 04/19/19 | 575 | Rodriguez Arevalos, Christian |  | 21.11
PR | 998 | 04/19/19 | 577 | Ross, Kelli M |  | 38.56
PR | 998 | 04/19/19 | 577 | Ross, Kelli M |  | 128.52
PR | 998 | 04/19/19 | 593 | Wilson, Garret A |  | 1.76
PR | 998 | 04/19/19 | 593 | Wilson, Garret A |  | 0.23
PR | 998 | 04/19/19 | 594 | Wilson, Garret A |  | -1.76
PR | 998 | 04/19/19 | 594 | Wilson, Garret A |  | -0.23
PR | 998 | 04/19/19 | 595 | Wilson, Garret A |  | 70.38
PR | 998 | 04/19/19 | 595 | Wilson, Garret A |  | 9.18
PR | 998 | 04/19/19 | 596 | Donelson, Richard T |  | 4.78
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 04/26/19 | 760 | Foster, Antonio T |  | 13.77
PR | 998 | 04/26/19 | 760 | Foster, Antonio T |  | 4.59
PR | 998 | 04/26/19 | 760 | Foster, Antonio T |  | 36.72
PR | 998 | 04/26/19 | 760 | Foster, Antonio T |  | 24.48
PR | 998 | 04/26/19 | 774 | Hubbard, Robert W |  | 19.13
PR | 998 | 04/26/19 | 774 | Hubbard, Robert W |  | 7.65
PR | 998 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M |  | 22.95
PR | 998 | 04/26/19 | 775 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 04/26/19 | 779 | Lopez, Maslin A |  | 15.61
PR | 998 | 04/26/19 | 779 | Lopez, Maslin A |  | 52.02
PR | 998 | 04/26/19 | 785 | Montenegro, Carlos E |  | 21.34
PR | 998 | 04/26/19 | 785 | Montenegro, Carlos E |  | 7.11
PR | 998 | 04/26/19 | 785 | Montenegro, Carlos E |  | 45.06
PR | 998 | 04/26/19 | 785 | Montenegro, Carlos E |  | 49.8
PR | 998 | 04/26/19 | 786 | Paco Leyva, Orlando |  | 6.12
PR | 998 | 04/26/19 | 794 | Rodriguez Arevalos, Christian |  | 17.9
PR | 998 | 04/26/19 | 794 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 04/26/19 | 796 | Ross, Kelli M |  | 38.56
PR | 998 | 04/26/19 | 796 | Ross, Kelli M |  | 128.52
PR | 998 | 04/26/19 | 810 | Wilson, Garret A |  | 143.82
PR | 998 | 04/26/19 | 810 | Wilson, Garret A |  | 3.06
PR | 998 | 04/26/19 | 812 | Donelson, Richard T |  | 4.78
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/03/19 | 28 | Foster, Antonio T |  | 61.2
PR | 998 | 05/03/19 | 42 | Hubbard, Robert W |  | 17.21
PR | 998 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 05/03/19 | 43 | Jimenez Alvarenga, Gerson M |  | 15.3
PR | 998 | 05/03/19 | 48 | Lopez, Maslin A |  | 52.02
PR | 998 | 05/03/19 | 54 | Montenegro, Carlos E |  | 75.89
PR | 998 | 05/03/19 | 63 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 05/03/19 | 65 | Ross, Kelli M |  | 128.52
PR | 998 | 05/03/19 | 80 | Wilson, Garret A |  | 91.8
PR | 998 | 05/03/19 | 80 | Wilson, Garret A |  | 15.3
PR | 998 | 05/03/19 | 80 | Wilson, Garret A |  | 15.3
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A |  | 3.67
PR | 998 | 05/10/19 | 159 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 05/10/19 | 181 | Foster, Antonio T |  | 61.2
PR | 998 | 05/10/19 | 195 | Hubbard, Robert W |  | 5.74
PR | 998 | 05/10/19 | 196 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 05/10/19 | 201 | Lopez, Maslin A |  | 52.02
PR | 998 | 05/10/19 | 207 | Montenegro, Carlos E |  | 94.86
PR | 998 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 4.59
PR | 998 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 2.98
PR | 998 | 05/10/19 | 216 | Rodriguez Arevalos, Christian |  | 57.68
PR | 998 | 05/10/19 | 216 | Rodriguez Arevalos, Christian |  | 21.88
PR | 998 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 22.03
PR | 998 | 05/10/19 | 218 | Ross, Kelli M |  | 102.82
PR | 998 | 05/10/19 | 233 | Wilson, Garret A |  | 104.04
PR | 998 | 05/10/19 | 233 | Wilson, Garret A |  | 9.18
PR | 998 | 05/10/19 | 233 | Wilson, Garret A |  | 9.18
PR | 998 | 05/10/19 | 234 | Donelson, Richard T |  | 4.78
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/17/19 | 390 | Amaya Gonzalez, Edilberto A |  | 85.68
PR | 998 | 05/17/19 | 398 | Boss, Kyle A |  | 31.21
PR | 998 | 05/17/19 | 412 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 05/17/19 | 413 | Foster, Antonio T |  | 61.2
PR | 998 | 05/17/19 | 427 | Hubbard, Robert W |  | 15.3
PR | 998 | 05/17/19 | 428 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 05/17/19 | 433 | Lopez, Maslin A |  | 52.02
PR | 998 | 05/17/19 | 439 | Montenegro, Carlos E |  | 94.86
PR | 998 | 05/17/19 | 442 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 05/17/19 | 448 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 05/17/19 | 449 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 05/17/19 | 450 | Ross, Kelli M |  | 128.52
PR | 998 | 05/17/19 | 465 | Wilson, Garret A |  | 107.1
PR | 998 | 05/17/19 | 465 | Wilson, Garret A |  | 15.3
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/24/19 | 603 | Amaya Gonzalez, Edilberto A |  | 58.75
PR | 998 | 05/24/19 | 610 | Boss, Kyle A |  | 52.02
PR | 998 | 05/24/19 | 624 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 05/24/19 | 625 | Foster, Antonio T |  | 59.67
PR | 998 | 05/24/19 | 640 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 05/24/19 | 645 | Lopez, Maslin A |  | 52.02
PR | 998 | 05/24/19 | 651 | Montenegro, Carlos E |  | 94.86
PR | 998 | 05/24/19 | 652 | Paco Leyva, Orlando |  | 58.14
PR | 998 | 05/24/19 | 654 | Ramos Herrera, Franklin J |  | 79.56
PR | 998 | 05/24/19 | 659 | Roberts, Lake A |  | 12.24
PR | 998 | 05/24/19 | 660 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 05/24/19 | 661 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 05/24/19 | 662 | Ross, Kelli M |  | 112.46
PR | 998 | 05/24/19 | 677 | Wilson, Garret A |  | 122.4
PR | 998 | 05/24/19 | 680 | Donelson, Richard T |  | 9.56
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 05/31/19 | 876 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 05/31/19 | 881 | Barnhart, Joseph N |  | 15.3
PR | 998 | 05/31/19 | 884 | Boss, Kyle A |  | 41.62
PR | 998 | 05/31/19 | 898 | Escalante Escobar, Boanerge |  | 53.86
PR | 998 | 05/31/19 | 899 | Foster, Antonio T |  | 48.96
PR | 998 | 05/31/19 | 913 | Hubbard, Robert W |  | 7.65
PR | 998 | 05/31/19 | 914 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 05/31/19 | 919 | Lopez, Maslin A |  | 41.62
PR | 998 | 05/31/19 | 925 | Montenegro, Carlos E |  | 75.89
PR | 998 | 05/31/19 | 926 | Paco Leyva, Orlando |  | 36.72
PR | 998 | 05/31/19 | 926 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 05/31/19 | 928 | Ramos Herrera, Franklin J |  | 63.65
PR | 998 | 05/31/19 | 933 | Roberts, Lake A |  | 48.96
PR | 998 | 05/31/19 | 934 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 05/31/19 | 935 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 05/31/19 | 936 | Ross, Kelli M |  | 77.11
PR | 998 | 05/31/19 | 951 | Wilson, Garret A |  | 97.92
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A |  | 58.75
PR | 998 | 06/07/19 | 178 | Amaya Gonzalez, Edilberto A |  | 19.58
PR | 998 | 06/07/19 | 186 | Boss, Kyle A |  | 52.02
PR | 998 | 06/07/19 | 200 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 06/07/19 | 201 | Foster, Antonio T |  | 16.83
PR | 998 | 06/07/19 | 215 | Hubbard, Robert W |  | 11.48
PR | 998 | 06/07/19 | 216 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 06/07/19 | 220 | Lopez, Maslin A |  | 52.02
PR | 998 | 06/07/19 | 226 | Montenegro, Carlos E |  | 94.86
PR | 998 | 06/07/19 | 227 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 06/07/19 | 229 | Ramos Herrera, Franklin J |  | 37.79
PR | 998 | 06/07/19 | 234 | Roberts, Lake A |  | 48.96
PR | 998 | 06/07/19 | 235 | Rodriguez Arevalos, Christian |  | 47.74
PR | 998 | 06/07/19 | 235 | Rodriguez Arevalos, Christian |  | 31.82
PR | 998 | 06/07/19 | 236 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 06/07/19 | 237 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 06/07/19 | 238 | Ross, Kelli M |  | 77.11
PR | 998 | 06/07/19 | 253 | Wilson, Garret A |  | 122.4
PR | 998 | 06/07/19 | 254 | Donelson, Richard T |  | 4.78
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/14/19 | 449 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 06/14/19 | 457 | Boss, Kyle A |  | 52.02
PR | 998 | 06/14/19 | 470 | Escalante Escobar, Boanerge |  | 13.46
PR | 998 | 06/14/19 | 470 | Escalante Escobar, Boanerge |  | 53.86
PR | 998 | 06/14/19 | 483 | Hubbard, Robert W |  | 11.48
PR | 998 | 06/14/19 | 484 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 06/14/19 | 489 | Lopez, Maslin A |  | 52.02
PR | 998 | 06/14/19 | 495 | Montenegro, Carlos E |  | 18.97
PR | 998 | 06/14/19 | 495 | Montenegro, Carlos E |  | 75.89
PR | 998 | 06/14/19 | 496 | Paco Leyva, Orlando |  | 44.37
PR | 998 | 06/14/19 | 498 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 06/14/19 | 503 | Roberts, Lake A |  | 61.2
PR | 998 | 06/14/19 | 504 | Rodriguez Arevalos, Christian |  | 47.74
PR | 998 | 06/14/19 | 504 | Rodriguez Arevalos, Christian |  | 31.82
PR | 998 | 06/14/19 | 505 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 06/14/19 | 506 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 06/14/19 | 507 | Ross, Kelli M |  | 128.52
PR | 998 | 06/14/19 | 521 | Wilson, Garret A |  | 58.14
PR | 998 | 06/14/19 | 521 | Wilson, Garret A |  | 64.26
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 28.69
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 14.73
PR | 998 | 06/21/19 | 617 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 06/21/19 | 625 | Boss, Aaron J |  | 29.38
PR | 998 | 06/21/19 | 626 | Boss, Kyle A |  | 52.02
PR | 998 | 06/21/19 | 634 | Cruz Guzman, Joel A |  | 17.14
PR | 998 | 06/21/19 | 640 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 06/21/19 | 654 | Hubbard, Robert W |  | 3.83
PR | 998 | 06/21/19 | 655 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 06/21/19 | 660 | Lopez, Maslin A |  | 52.02
PR | 998 | 06/21/19 | 666 | Montenegro, Carlos E |  | 94.86
PR | 998 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 30.6
PR | 998 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 06/21/19 | 674 | Roberts, Lake A |  | 61.2
PR | 998 | 06/21/19 | 675 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 06/21/19 | 675 | Rodriguez Arevalos, Christian |  | 15.91
PR | 998 | 06/21/19 | 676 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 06/21/19 | 677 | Rosas Olivares, Jorge C |  | 24.48
PR | 998 | 06/21/19 | 678 | Ross, Kelli M |  | 77.11
PR | 998 | 06/21/19 | 678 | Ross, Kelli M |  | 51.41
PR | 998 | 06/21/19 | 680 | Silva Morales, Jair J |  | 16.52
PR | 998 | 06/21/19 | 692 | Wilson, Garret A |  | 107.1
PR | 998 | 06/21/19 | 692 | Wilson, Garret A |  | 15.3
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 835 | Amaya Gonzalez, Edilberto A |  | 90.58
PR | 998 | 06/28/19 | 843 | Boss, Aaron J |  | 48.96
PR | 998 | 06/28/19 | 844 | Boss, Kyle A |  | 44.22
PR | 998 | 06/28/19 | 844 | Boss, Kyle A |  | 7.8
PR | 998 | 06/28/19 | 852 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 06/28/19 | 858 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 06/28/19 | 873 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 06/28/19 | 877 | Lopez, Maslin A |  | 52.02
PR | 998 | 06/28/19 | 883 | Montenegro, Carlos E |  | 94.86
PR | 998 | 06/28/19 | 891 | Roberts, Lake A |  | 48.96
PR | 998 | 06/28/19 | 892 | Rodriguez Arevalos, Christian |  | 47.74
PR | 998 | 06/28/19 | 892 | Rodriguez Arevalos, Christian |  | 15.91
PR | 998 | 06/28/19 | 893 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 06/28/19 | 894 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 06/28/19 | 895 | Ross, Kelli M |  | 51.41
PR | 998 | 06/28/19 | 895 | Ross, Kelli M |  | 77.11
PR | 998 | 06/28/19 | 897 | Silva Morales, Jair J |  | 82.62
PR | 998 | 06/28/19 | 909 | Wilson, Garret A |  | 94.86
PR | 998 | 06/28/19 | 909 | Wilson, Garret A |  | 27.54
PR | 998 | 06/28/19 | 910 | Donelson, Richard T |  | 19.13
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/05/19 | 7 | Amaya Gonzalez, Edilberto A |  | 78.34
PR | 998 | 07/05/19 | 15 | Boss, Aaron J |  | 42.84
PR | 998 | 07/05/19 | 15 | Boss, Aaron J |  | 6.12
PR | 998 | 07/05/19 | 16 | Boss, Kyle A |  | 41.62
PR | 998 | 07/05/19 | 16 | Boss, Kyle A |  | 10.4
PR | 998 | 07/05/19 | 24 | Cruz Guzman, Joel A |  | 83.54
PR | 998 | 07/05/19 | 24 | Cruz Guzman, Joel A |  | 2.14
PR | 998 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 52.17
PR | 998 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 1.68
PR | 998 | 07/05/19 | 30 | Escalante Escobar, Boanerge |  | 13.46
PR | 998 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M |  | 74.59
PR | 998 | 07/05/19 | 45 | Jimenez Alvarenga, Gerson M |  | 1.91
PR | 998 | 07/05/19 | 49 | Lopez, Maslin A |  | 50.72
PR | 998 | 07/05/19 | 49 | Lopez, Maslin A |  | 1.3
PR | 998 | 07/05/19 | 55 | Montenegro, Carlos E |  | 37.94
PR | 998 | 07/05/19 | 63 | Roberts, Lake A |  | 22.95
PR | 998 | 07/05/19 | 63 | Roberts, Lake A |  | 1.53
PR | 998 | 07/05/19 | 63 | Roberts, Lake A |  | 24.48
PR | 998 | 07/05/19 | 64 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 07/05/19 | 64 | Rodriguez Arevalos, Christian |  | 15.91
PR | 998 | 07/05/19 | 65 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 07/05/19 | 65 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 07/05/19 | 66 | Ross, Kelli M |  | 102.82
PR | 998 | 07/05/19 | 66 | Ross, Kelli M |  | 25.7
PR | 998 | 07/05/19 | 68 | Silva Morales, Jair J |  | 80.55
PR | 998 | 07/05/19 | 68 | Silva Morales, Jair J |  | 2.07
PR | 998 | 07/05/19 | 80 | Wilson, Garret A |  | 64.26
PR | 998 | 07/05/19 | 80 | Wilson, Garret A |  | 58.14
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 4.78
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/12/19 | 277 | Amaya Gonzalez, Edilberto A |  | 78.34
PR | 998 | 07/12/19 | 285 | Boss, Aaron J |  | 31.82
PR | 998 | 07/12/19 | 285 | Boss, Aaron J |  | 7.34
PR | 998 | 07/12/19 | 286 | Boss, Kyle A |  | 40.32
PR | 998 | 07/12/19 | 286 | Boss, Kyle A |  | 1.3
PR | 998 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 42.84
PR | 998 | 07/12/19 | 293 | Cruz Guzman, Joel A |  | 68.54
PR | 998 | 07/12/19 | 299 | Escalante Escobar, Boanerge |  | 53.86
PR | 998 | 07/12/19 | 303 | Gauthier, Dillon R |  | 20.81
PR | 998 | 07/12/19 | 314 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 07/12/19 | 318 | Lopez, Maslin A |  | 41.62
PR | 998 | 07/12/19 | 324 | Montenegro, Carlos E |  | 37.94
PR | 998 | 07/12/19 | 332 | Roberts, Lake A |  | 22.19
PR | 998 | 07/12/19 | 333 | Rodriguez Arevalos, Christian |  | 57.68
PR | 998 | 07/12/19 | 334 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 07/12/19 | 335 | Rosas Olivares, Jorge C |  | 35.96
PR | 998 | 07/12/19 | 336 | Ross, Kelli M |  | 80.33
PR | 998 | 07/12/19 | 336 | Ross, Kelli M |  | 22.49
PR | 998 | 07/12/19 | 339 | Silva Morales, Jair J |  | 49.57
PR | 998 | 07/12/19 | 351 | Wilson, Garret A |  | 74.97
PR | 998 | 07/12/19 | 351 | Wilson, Garret A |  | 21.42
PR | 998 | 07/12/19 | 351 | Wilson, Garret A |  | 1.53
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/19/19 | 507 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 07/19/19 | 515 | Boss, Aaron J |  | 48.96
PR | 998 | 07/19/19 | 516 | Boss, Kyle A |  | 55.08
PR | 998 | 07/19/19 | 529 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 07/19/19 | 543 | Hubbard, Robert W |  | 11.48
PR | 998 | 07/19/19 | 543 | Hubbard, Robert W |  | 3.83
PR | 998 | 07/19/19 | 544 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 07/19/19 | 548 | Lopez, Maslin A |  | 52.02
PR | 998 | 07/19/19 | 554 | Montenegro, Carlos E |  | 75.89
PR | 998 | 07/19/19 | 562 | Roberts, Lake A |  | 61.2
PR | 998 | 07/19/19 | 563 | Rodriguez Arevalos, Christian |  | 65.64
PR | 998 | 07/19/19 | 563 | Rodriguez Arevalos, Christian |  | 13.92
PR | 998 | 07/19/19 | 564 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 07/19/19 | 564 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 07/19/19 | 565 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 07/19/19 | 566 | Ross, Kelli M |  | 118.88
PR | 998 | 07/19/19 | 566 | Ross, Kelli M |  | 9.64
PR | 998 | 07/19/19 | 569 | Silva Morales, Jair J |  | 78.49
PR | 998 | 07/19/19 | 581 | Wilson, Garret A |  | 58.14
PR | 998 | 07/19/19 | 581 | Wilson, Garret A |  | 12.24
PR | 998 | 07/19/19 | 581 | Wilson, Garret A |  | 27.54
PR | 998 | 07/19/19 | 581 | Wilson, Garret A |  | 24.48
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 611 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 07/26/19 | 613 | Ascencio, Jose L |  | 91.8
PR | 998 | 07/26/19 | 619 | Boss, Aaron J |  | 48.96
PR | 998 | 07/26/19 | 620 | Boss, Kyle A |  | 55.08
PR | 998 | 07/26/19 | 627 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 07/26/19 | 633 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 07/26/19 | 646 | Hubbard, Robert W |  | 7.65
PR | 998 | 07/26/19 | 647 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 07/26/19 | 651 | Lopez, Maslin A |  | 52.02
PR | 998 | 07/26/19 | 657 | Montenegro, Carlos E |  | 75.89
PR | 998 | 07/26/19 | 665 | Roberts, Lake A |  | 61.2
PR | 998 | 07/26/19 | 666 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 07/26/19 | 666 | Rodriguez Arevalos, Christian |  | 15.91
PR | 998 | 07/26/19 | 667 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 07/26/19 | 667 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 07/26/19 | 668 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 07/26/19 | 669 | Ross, Kelli M |  | 96.39
PR | 998 | 07/26/19 | 669 | Ross, Kelli M |  | 32.13
PR | 998 | 07/26/19 | 672 | Silva Morales, Jair J |  | 80.55
PR | 998 | 07/26/19 | 684 | Wilson, Garret A |  | 116.28
PR | 998 | 07/26/19 | 684 | Wilson, Garret A |  | 3.06
PR | 998 | 07/26/19 | 684 | Wilson, Garret A |  | 3.06
PR | 998 | 07/26/19 | 685 | Donelson, Richard T |  | 9.56
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/02/19 | 3 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 08/02/19 | 11 | Boss, Aaron J |  | 48.96
PR | 998 | 08/02/19 | 12 | Boss, Kyle A |  | 22.03
PR | 998 | 08/02/19 | 12 | Boss, Kyle A |  | 33.05
PR | 998 | 08/02/19 | 19 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 08/02/19 | 25 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 08/02/19 | 39 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 08/02/19 | 43 | Lopez, Maslin A |  | 52.02
PR | 998 | 08/02/19 | 49 | Montenegro, Carlos E |  | 75.89
PR | 998 | 08/02/19 | 57 | Roberts, Lake A |  | 48.96
PR | 998 | 08/02/19 | 58 | Rodriguez Arevalos, Christian |  | 78.57
PR | 998 | 08/02/19 | 59 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 08/02/19 | 59 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 08/02/19 | 60 | Ross, Kelli M |  | 77.11
PR | 998 | 08/02/19 | 60 | Ross, Kelli M |  | 51.41
PR | 998 | 08/02/19 | 63 | Silva Morales, Jair J |  | 81.59
PR | 998 | 08/02/19 | 75 | Wilson, Garret A |  | 122.4
PR | 998 | 08/02/19 | 76 | Donelson, Richard T |  | 9.56
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/09/19 | 255 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 08/09/19 | 263 | Boss, Aaron J |  | 48.96
PR | 998 | 08/09/19 | 264 | Boss, Kyle A |  | 37.18
PR | 998 | 08/09/19 | 264 | Boss, Kyle A |  | 17.9
PR | 998 | 08/09/19 | 271 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 08/09/19 | 277 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 08/09/19 | 291 | Hubbard, Robert W |  | 22.95
PR | 998 | 08/09/19 | 292 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 08/09/19 | 296 | Lopez, Maslin A |  | 52.02
PR | 998 | 08/09/19 | 302 | Montenegro, Carlos E |  | 56.92
PR | 998 | 08/09/19 | 302 | Montenegro, Carlos E |  | 37.94
PR | 998 | 08/09/19 | 310 | Roberts, Lake A |  | 61.2
PR | 998 | 08/09/19 | 311 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 08/09/19 | 312 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 08/09/19 | 312 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 08/09/19 | 313 | Ross, Kelli M |  | 128.52
PR | 998 | 08/09/19 | 316 | Silva Morales, Jair J |  | 82.62
PR | 998 | 08/09/19 | 327 | Wilson, Garret A |  | 73.44
PR | 998 | 08/09/19 | 328 | Donelson, Richard T |  | 4.78
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/16/19 | 562 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 08/16/19 | 563 | Anderson, Richard P |  | 10.79
PR | 998 | 08/16/19 | 570 | Boss, Aaron J |  | 48.96
PR | 998 | 08/16/19 | 571 | Boss, Kyle A |  | 28.92
PR | 998 | 08/16/19 | 571 | Boss, Kyle A |  | 26.16
PR | 998 | 08/16/19 | 578 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 08/16/19 | 584 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 08/16/19 | 598 | Hubbard, Robert W |  | 15.3
PR | 998 | 08/16/19 | 599 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 08/16/19 | 603 | Lopez, Maslin A |  | 52.02
PR | 998 | 08/16/19 | 609 | Montenegro, Carlos E |  | 75.89
PR | 998 | 08/16/19 | 609 | Montenegro, Carlos E |  | 18.97
PR | 998 | 08/16/19 | 617 | Roberts, Lake A |  | 36.72
PR | 998 | 08/16/19 | 617 | Roberts, Lake A |  | 12.24
PR | 998 | 08/16/19 | 618 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 08/16/19 | 619 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 08/16/19 | 620 | Ross, Kelli M |  | 128.52
PR | 998 | 08/16/19 | 623 | Silva Morales, Jair J |  | 79.52
PR | 998 | 08/16/19 | 635 | Wilson, Garret A |  | 97.92
PR | 998 | 08/16/19 | 636 | Donelson, Richard T |  | 9.56
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/23/19 | 798 | Amaya Gonzalez, Edilberto A |  | 78.34
PR | 998 | 08/23/19 | 806 | Boss, Aaron J |  | 39.17
PR | 998 | 08/23/19 | 807 | Boss, Kyle A |  | 44.06
PR | 998 | 08/23/19 | 814 | Cruz Guzman, Joel A |  | 34.27
PR | 998 | 08/23/19 | 820 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M |  | 30.6
PR | 998 | 08/23/19 | 840 | Lopez, Maslin A |  | 41.62
PR | 998 | 08/23/19 | 840 | Lopez, Maslin A |  | 5.2
PR | 998 | 08/23/19 | 846 | Montenegro, Carlos E |  | 94.86
PR | 998 | 08/23/19 | 854 | Roberts, Lake A |  | 44.37
PR | 998 | 08/23/19 | 854 | Roberts, Lake A |  | 16.83
PR | 998 | 08/23/19 | 855 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 5.51
PR | 998 | 08/23/19 | 857 | Ross, Kelli M |  | 128.52
PR | 998 | 08/23/19 | 860 | Silva Morales, Jair J |  | 33.05
PR | 998 | 08/23/19 | 872 | Wilson, Garret A |  | 122.4
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 58.75
PR | 998 | 08/30/19 | 997 | Boss, Aaron J |  | 48.96
PR | 998 | 08/30/19 | 998 | Boss, Kyle A |  | 55.08
PR | 998 | 08/30/19 | 1011 | Escalante Escobar, Boanerge |  | 40.39
PR | 998 | 08/30/19 | 1011 | Escalante Escobar, Boanerge |  | 26.93
PR | 998 | 08/30/19 | 1026 | Hubbard, Robert W |  | 15.3
PR | 998 | 08/30/19 | 1031 | Lopez, Maslin A |  | 41.62
PR | 998 | 08/30/19 | 1031 | Lopez, Maslin A |  | 10.4
PR | 998 | 08/30/19 | 1037 | Montenegro, Carlos E |  | 56.92
PR | 998 | 08/30/19 | 1037 | Montenegro, Carlos E |  | 37.94
PR | 998 | 08/30/19 | 1045 | Roberts, Lake A |  | 44.37
PR | 998 | 08/30/19 | 1045 | Roberts, Lake A |  | 12.24
PR | 998 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian |  | 47.74
PR | 998 | 08/30/19 | 1046 | Rodriguez Arevalos, Christian |  | 31.82
PR | 998 | 08/30/19 | 1047 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 08/30/19 | 1047 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 08/30/19 | 1048 | Ross, Kelli M |  | 102.82
PR | 998 | 08/30/19 | 1048 | Ross, Kelli M |  | 25.7
PR | 998 | 08/30/19 | 1063 | Wilson, Garret A |  | 122.4
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 4.78
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 33.47
PR | 998 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/06/19 | 18 | Boss, Aaron J |  | 39.17
PR | 998 | 09/06/19 | 19 | Boss, Kyle A |  | 30.29
PR | 998 | 09/06/19 | 32 | Escalante Escobar, Boanerge |  | 53.86
PR | 998 | 09/06/19 | 47 | Hubbard, Robert W |  | 11.48
PR | 998 | 09/06/19 | 47 | Hubbard, Robert W |  | 7.65
PR | 998 | 09/06/19 | 52 | Lopez, Maslin A |  | 14.31
PR | 998 | 09/06/19 | 52 | Lopez, Maslin A |  | 6.5
PR | 998 | 09/06/19 | 52 | Lopez, Maslin A |  | 10.4
PR | 998 | 09/06/19 | 58 | Montenegro, Carlos E |  | 75.89
PR | 998 | 09/06/19 | 66 | Roberts, Lake A |  | 44.37
PR | 998 | 09/06/19 | 66 | Roberts, Lake A |  | 4.59
PR | 998 | 09/06/19 | 67 | Rodriguez Arevalos, Christian |  | 25.86
PR | 998 | 09/06/19 | 67 | Rodriguez Arevalos, Christian |  | 37.79
PR | 998 | 09/06/19 | 68 | Romero Garza, Jesus I |  | 33.05
PR | 998 | 09/06/19 | 69 | Ross, Kelli M |  | 25.7
PR | 998 | 09/06/19 | 69 | Ross, Kelli M |  | 77.11
PR | 998 | 09/06/19 | 84 | Wilson, Garret A |  | 67.32
PR | 998 | 09/06/19 | 85 | Donelson, Richard T |  | 9.56
PR | 998 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/13/19 | 242 | Boss, Aaron J |  | 48.96
PR | 998 | 09/13/19 | 243 | Boss, Kyle A |  | 8.26
PR | 998 | 09/13/19 | 256 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 09/13/19 | 271 | Hubbard, Robert W |  | 3.83
PR | 998 | 09/13/19 | 271 | Hubbard, Robert W |  | 22.95
PR | 998 | 09/13/19 | 275 | Lopez, Maslin A |  | 15.61
PR | 998 | 09/13/19 | 275 | Lopez, Maslin A |  | 52.02
PR | 998 | 09/13/19 | 281 | Montenegro, Carlos E |  | 75.89
PR | 998 | 09/13/19 | 289 | Roberts, Lake A |  | 4.59
PR | 998 | 09/13/19 | 289 | Roberts, Lake A |  | 13.77
PR | 998 | 09/13/19 | 289 | Roberts, Lake A |  | 36.72
PR | 998 | 09/13/19 | 289 | Roberts, Lake A |  | 24.48
PR | 998 | 09/13/19 | 290 | Rodriguez Arevalos, Christian |  | 23.87
PR | 998 | 09/13/19 | 290 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 09/13/19 | 291 | Romero Garza, Jesus I |  | 16.52
PR | 998 | 09/13/19 | 291 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 09/13/19 | 292 | Ross, Kelli M |  | 38.56
PR | 998 | 09/13/19 | 292 | Ross, Kelli M |  | 128.52
PR | 998 | 09/13/19 | 307 | Wilson, Garret A |  | 18.36
PR | 998 | 09/13/19 | 308 | Donelson, Richard T |  | 14.34
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/20/19 | 479 | Boss, Aaron J |  | 48.96
PR | 998 | 09/20/19 | 480 | Boss, Kyle A |  | 33.05
PR | 998 | 09/20/19 | 480 | Boss, Kyle A |  | 11.02
PR | 998 | 09/20/19 | 481 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 09/20/19 | 487 | Cruz Guzman, Joel A |  | 17.14
PR | 998 | 09/20/19 | 493 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 09/20/19 | 502 | Guerrero Espinoza, Mario |  | 9.79
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 22.95
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 15.3
PR | 998 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M |  | 15.3
PR | 998 | 09/20/19 | 513 | Lopez, Maslin A |  | 52.02
PR | 998 | 09/20/19 | 519 | Montenegro, Carlos E |  | 94.86
PR | 998 | 09/20/19 | 527 | Roberts, Lake A |  | 47.43
PR | 998 | 09/20/19 | 527 | Roberts, Lake A |  | 13.77
PR | 998 | 09/20/19 | 528 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 09/20/19 | 529 | Romero Garza, Jesus I |  | 44.06
PR | 998 | 09/20/19 | 530 | Ross, Kelli M |  | 102.82
PR | 998 | 09/20/19 | 533 | Silva Morales, Jair J |  | 16.52
PR | 998 | 09/20/19 | 545 | Wilson, Garret A |  | 27.54
PR | 998 | 09/20/19 | 545 | Wilson, Garret A |  | 33.66
PR | 998 | 09/20/19 | 545 | Wilson, Garret A |  | 27.54
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 09/27/19 | 635 | Boss, Aaron J |  | 48.96
PR | 998 | 09/27/19 | 636 | Boss, Kyle A |  | 55.08
PR | 998 | 09/27/19 | 649 | Escalante Escobar, Boanerge |  | 40.39
PR | 998 | 09/27/19 | 649 | Escalante Escobar, Boanerge |  | 26.93
PR | 998 | 09/27/19 | 666 | Hubbard, Robert W |  | 11.48
PR | 998 | 09/27/19 | 666 | Hubbard, Robert W |  | 26.78
PR | 998 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M |  | 15.3
PR | 998 | 09/27/19 | 672 | Lopez, Maslin A |  | 52.02
PR | 998 | 09/27/19 | 676 | McCabe, Thomas C |  | 42.84
PR | 998 | 09/27/19 | 678 | Montenegro, Carlos E |  | 56.92
PR | 998 | 09/27/19 | 678 | Montenegro, Carlos E |  | 18.97
PR | 998 | 09/27/19 | 686 | Roberts, Lake A |  | 37.03
PR | 998 | 09/27/19 | 686 | Roberts, Lake A |  | 10.1
PR | 998 | 09/27/19 | 686 | Roberts, Lake A |  | 6.73
PR | 998 | 09/27/19 | 687 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 09/27/19 | 688 | Romero Garza, Jesus I |  | 48.96
PR | 998 | 09/27/19 | 688 | Romero Garza, Jesus I |  | 12.24
PR | 998 | 09/27/19 | 689 | Ross, Kelli M |  | 128.52
PR | 998 | 09/27/19 | 704 | Wilson, Garret A |  | 97.92
PR | 998 | 09/27/19 | 704 | Wilson, Garret A |  | 12.24
PR | 998 | 09/27/19 | 704 | Wilson, Garret A |  | 12.24
PR | 998 | 09/27/19 | 705 | Donelson, Richard T |  | 4.78
PR | 998 | 10/04/19 | 11 | Boss, Aaron J |  | 48.96
PR | 998 | 10/04/19 | 12 | Boss, Kyle A |  | 55.08
PR | 998 | 10/04/19 | 25 | Escalante Escobar, Boanerge |  | 31.98
PR | 998 | 10/04/19 | 41 | Hubbard, Robert W |  | 30.6
PR | 998 | 10/04/19 | 41 | Hubbard, Robert W |  | 22.95
PR | 998 | 10/04/19 | 47 | Lopez, Maslin A |  | 52.02
PR | 998 | 10/04/19 | 52 | McCabe, Thomas C |  | 93.71
PR | 998 | 10/04/19 | 54 | Montenegro, Carlos E |  | 94.86
PR | 998 | 10/04/19 | 62 | Roberts, Lake A |  | 67.32
PR | 998 | 10/04/19 | 63 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 10/04/19 | 64 | Romero Garza, Jesus I |  | 61.2
PR | 998 | 10/04/19 | 65 | Ross, Kelli M |  | 115.67
PR | 998 | 10/04/19 | 65 | Ross, Kelli M |  | 3.21
PR | 998 | 10/04/19 | 80 | Wilson, Garret A |  | 88.74
PR | 998 | 10/04/19 | 80 | Wilson, Garret A |  | 3.06
PR | 998 | 10/04/19 | 81 | Donelson, Richard T |  | 4.78
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/11/19 | 266 | Boss, Aaron J |  | 29.38
PR | 998 | 10/11/19 | 267 | Boss, Kyle A |  | 11.02
PR | 998 | 10/11/19 | 267 | Boss, Kyle A |  | 22.03
PR | 998 | 10/11/19 | 280 | Escalante Escobar, Boanerge |  | 67.32
PR | 998 | 10/11/19 | 296 | Hubbard, Robert W |  | 15.3
PR | 998 | 10/11/19 | 296 | Hubbard, Robert W |  | 53.55
PR | 998 | 10/11/19 | 296 | Hubbard, Robert W |  | 11.48
PR | 998 | 10/11/19 | 302 | Lopez, Maslin A |  | 52.02
PR | 998 | 10/11/19 | 307 | McCabe, Thomas C |  | 21.42
PR | 998 | 10/11/19 | 307 | McCabe, Thomas C |  | 85.68
PR | 998 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 6.12
PR | 998 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 3.98
PR | 998 | 10/11/19 | 316 | Roberts, Lake A |  | 16.83
PR | 998 | 10/11/19 | 316 | Roberts, Lake A |  | 40.39
PR | 998 | 10/11/19 | 317 | Rodriguez Arevalos, Christian |  | 79.56
PR | 998 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 24.48
PR | 998 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 22.19
PR | 998 | 10/11/19 | 318 | Romero Garza, Jesus I |  | 12.24
PR | 998 | 10/11/19 | 320 | Ross, Kelli M |  | 109.24
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/18/19 | 460 | Boss, Aaron J |  | 48.96
PR | 998 | 10/18/19 | 461 | Boss, Kyle A |  | 19.28
PR | 998 | 10/18/19 | 461 | Boss, Kyle A |  | 13.77
PR | 998 | 10/18/19 | 461 | Boss, Kyle A |  | 22.03
PR | 998 | 10/18/19 | 473 | Escalante Escobar, Boanerge |  | 60.59
PR | 998 | 10/18/19 | 478 | Gerard, Jordan E |  | 8.26
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 19.13
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 22.95
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 11.48
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 57.38
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 3.83
PR | 998 | 10/18/19 | 495 | Lopez, Maslin A |  | 52.02
PR | 998 | 10/18/19 | 500 | McCabe, Thomas C |  | 13.39
PR | 998 | 10/18/19 | 500 | McCabe, Thomas C |  | 72.29
PR | 998 | 10/18/19 | 500 | McCabe, Thomas C |  | 13.39
PR | 998 | 10/18/19 | 509 | Roberts, Lake A |  | 6.73
PR | 998 | 10/18/19 | 509 | Roberts, Lake A |  | 33.66
PR | 998 | 10/18/19 | 509 | Roberts, Lake A |  | 26.93
PR | 998 | 10/18/19 | 510 | Rodriguez Arevalos, Christian |  | 63.65
PR | 998 | 10/18/19 | 511 | Romero Garza, Jesus I |  | 30.6
PR | 998 | 10/18/19 | 511 | Romero Garza, Jesus I |  | 19.89
PR | 998 | 10/18/19 | 513 | Ross, Kelli M |  | 102.82
PR | 998 | 10/18/19 | 521 | Vazquez Popoca, Jose N |  | 10.4
PR | 998 | 10/18/19 | 527 | Donelson, Richard T |  | 4.78
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/25/19 | 595 | Boss, Aaron J |  | 45.29
PR | 998 | 10/25/19 | 596 | Boss, Benjamin T |  | 29.38
PR | 998 | 10/25/19 | 597 | Boss, Kyle A |  | 33.05
PR | 998 | 10/25/19 | 597 | Boss, Kyle A |  | 6.89
PR | 998 | 10/25/19 | 597 | Boss, Kyle A |  | 11.02
PR | 998 | 10/25/19 | 608 | Escalante Escobar, Boanerge |  | 37.03
PR | 998 | 10/25/19 | 608 | Escalante Escobar, Boanerge |  | 13.46
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 57.38
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 7.65
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 30.6
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 15.3
PR | 998 | 10/25/19 | 630 | Lopez, Maslin A |  | 48.12
PR | 998 | 10/25/19 | 635 | McCabe, Thomas C |  | 88.36
PR | 998 | 10/25/19 | 635 | McCabe, Thomas C |  | 10.71
PR | 998 | 10/25/19 | 645 | Roberts, Lake A |  | 6.73
PR | 998 | 10/25/19 | 645 | Roberts, Lake A |  | 6.73
PR | 998 | 10/25/19 | 645 | Roberts, Lake A |  | 8.42
PR | 998 | 10/25/19 | 646 | Rodriguez Arevalos, Christian |  | 73.59
PR | 998 | 10/25/19 | 647 | Romero Garza, Jesus I |  | 32.13
PR | 998 | 10/25/19 | 647 | Romero Garza, Jesus I |  | 12.24
PR | 998 | 10/25/19 | 649 | Ross, Kelli M |  | 109.24
PR | 998 | 10/25/19 | 664 | Donelson, Richard T |  | 9.56
PR | 998 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 11/01/19 | 11 | Boss, Benjamin T |  | 48.96
PR | 998 | 11/01/19 | 12 | Boss, Kyle A |  | 12.85
PR | 998 | 11/01/19 | 12 | Boss, Kyle A |  | 38.56
PR | 998 | 11/01/19 | 12 | Boss, Kyle A |  | 12.85
PR | 998 | 11/01/19 | 19 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 11/01/19 | 24 | Escalante Escobar, Boanerge |  | 30.6
PR | 998 | 11/01/19 | 24 | Escalante Escobar, Boanerge |  | 45.9
PR | 998 | 11/01/19 | 40 | Hubbard, Robert W |  | 45.44
PR | 998 | 11/01/19 | 40 | Hubbard, Robert W |  | 12.39
PR | 998 | 11/01/19 | 40 | Hubbard, Robert W |  | 33.05
PR | 998 | 11/01/19 | 40 | Hubbard, Robert W |  | 4.13
PR | 998 | 11/01/19 | 40 | Hubbard, Robert W |  | 12.39
PR | 998 | 11/01/19 | 46 | Lopez, Maslin A |  | 58.14
PR | 998 | 11/01/19 | 51 | McCabe, Thomas C |  | 95.47
PR | 998 | 11/01/19 | 61 | Roberts, Lake A |  | 45.9
PR | 998 | 11/01/19 | 61 | Roberts, Lake A |  | 7.65
PR | 998 | 11/01/19 | 61 | Roberts, Lake A |  | 7.65
PR | 998 | 11/01/19 | 61 | Roberts, Lake A |  | 7.65
PR | 998 | 11/01/19 | 62 | Rodriguez Arevalos, Christian |  | 91.8
PR | 998 | 11/01/19 | 63 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 11/01/19 | 63 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 11/01/19 | 65 | Ross, Kelli M |  | 105.26
PR | 998 | 11/01/19 | 66 | Sanders, Allen O |  | 28.92
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 9.56
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 11/08/19 | 185 | Boss, Benjamin T |  | 19.58
PR | 998 | 11/08/19 | 185 | Boss, Benjamin T |  | 19.58
PR | 998 | 11/08/19 | 185 | Boss, Benjamin T |  | 9.79
PR | 998 | 11/08/19 | 186 | Boss, Kyle A |  | 12.85
PR | 998 | 11/08/19 | 186 | Boss, Kyle A |  | 12.85
PR | 998 | 11/08/19 | 186 | Boss, Kyle A |  | 12.85
PR | 998 | 11/08/19 | 186 | Boss, Kyle A |  | 12.85
PR | 998 | 11/08/19 | 192 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 11/08/19 | 193 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 11/08/19 | 193 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 38.25
PR | 998 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 15.3
PR | 998 | 11/08/19 | 198 | Escalante Escobar, Boanerge |  | 22.95
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 12.39
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 4.13
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 49.57
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 66.1
PR | 998 | 11/08/19 | 220 | Lopez, Maslin A |  | 46.51
PR | 998 | 11/08/19 | 220 | Lopez, Maslin A |  | 11.63
PR | 998 | 11/08/19 | 225 | McCabe, Thomas C |  | 95.47
PR | 998 | 11/08/19 | 235 | Roberts, Lake A |  | 22.95
PR | 998 | 11/08/19 | 235 | Roberts, Lake A |  | 7.65
PR | 998 | 11/08/19 | 235 | Roberts, Lake A |  | 30.6
PR | 998 | 11/08/19 | 235 | Roberts, Lake A |  | 15.3
PR | 998 | 11/08/19 | 236 | Rodriguez Arevalos, Christian |  | 91.8
PR | 998 | 11/08/19 | 237 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 11/08/19 | 237 | Romero Garza, Jesus I |  | 28.15
PR | 998 | 11/08/19 | 239 | Ross, Kelli M |  | 78.95
PR | 998 | 11/08/19 | 239 | Ross, Kelli M |  | 52.63
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/15/19 | 445 | Boss, Benjamin T |  | 48.96
PR | 998 | 11/15/19 | 446 | Boss, Kyle A |  | 12.85
PR | 998 | 11/15/19 | 446 | Boss, Kyle A |  | 25.7
PR | 998 | 11/15/19 | 446 | Boss, Kyle A |  | 12.85
PR | 998 | 11/15/19 | 452 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 11/15/19 | 453 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 11/15/19 | 473 | Hubbard, Robert W |  | 24.79
PR | 998 | 11/15/19 | 473 | Hubbard, Robert W |  | 20.66
PR | 998 | 11/15/19 | 473 | Hubbard, Robert W |  | 57.83
PR | 998 | 11/15/19 | 473 | Hubbard, Robert W |  | 28.92
PR | 998 | 11/15/19 | 479 | Lopez, Maslin A |  | 46.51
PR | 998 | 11/15/19 | 479 | Lopez, Maslin A |  | 11.63
PR | 998 | 11/15/19 | 484 | McCabe, Thomas C |  | 119.34
PR | 998 | 11/15/19 | 494 | Roberts, Lake A |  | 45.9
PR | 998 | 11/15/19 | 495 | Rodriguez Arevalos, Christian |  | 73.44
PR | 998 | 11/15/19 | 496 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 11/15/19 | 498 | Ross, Kelli M |  | 52.63
PR | 998 | 11/15/19 | 506 | Vazquez Popoca, Jose N |  | 24.48
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/22/19 | 616 | Boss, Benjamin T |  | 19.58
PR | 998 | 11/22/19 | 616 | Boss, Benjamin T |  | 4.9
PR | 998 | 11/22/19 | 616 | Boss, Benjamin T |  | 9.79
PR | 998 | 11/22/19 | 617 | Boss, Kyle A |  | 35.34
PR | 998 | 11/22/19 | 617 | Boss, Kyle A |  | 25.7
PR | 998 | 11/22/19 | 623 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 11/22/19 | 623 | Cruz Gonzalez, Julio C |  | 29.99
PR | 998 | 11/22/19 | 644 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/22/19 | 644 | Hubbard, Robert W |  | 20.66
PR | 998 | 11/22/19 | 644 | Hubbard, Robert W |  | 45.44
PR | 998 | 11/22/19 | 650 | Lopez, Maslin A |  | 46.51
PR | 998 | 11/22/19 | 650 | Lopez, Maslin A |  | 8.72
PR | 998 | 11/22/19 | 655 | McCabe, Thomas C |  | 50.72
PR | 998 | 11/22/19 | 655 | McCabe, Thomas C |  | 23.87
PR | 998 | 11/22/19 | 665 | Roberts, Lake A |  | 5.74
PR | 998 | 11/22/19 | 665 | Roberts, Lake A |  | 5.74
PR | 998 | 11/22/19 | 665 | Roberts, Lake A |  | 26.78
PR | 998 | 11/22/19 | 665 | Roberts, Lake A |  | 3.83
PR | 998 | 11/22/19 | 666 | Rodriguez Arevalos, Christian |  | 73.44
PR | 998 | 11/22/19 | 666 | Rodriguez Arevalos, Christian |  | 13.77
PR | 998 | 11/22/19 | 667 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 11/22/19 | 667 | Romero Garza, Jesus I |  | 10.56
PR | 998 | 11/22/19 | 670 | Sanders, Allen O |  | 16.52
PR | 998 | 11/27/19 | 850 | Boss, Benjamin T |  | 4.9
PR | 998 | 11/27/19 | 850 | Boss, Benjamin T |  | 19.58
PR | 998 | 11/27/19 | 850 | Boss, Benjamin T |  | 19.58
PR | 998 | 11/27/19 | 851 | Boss, Kyle A |  | 19.28
PR | 998 | 11/27/19 | 851 | Boss, Kyle A |  | 12.85
PR | 998 | 11/27/19 | 851 | Boss, Kyle A |  | 12.85
PR | 998 | 11/27/19 | 851 | Boss, Kyle A |  | 12.85
PR | 998 | 11/27/19 | 857 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 11/27/19 | 878 | Hubbard, Robert W |  | 82.62
PR | 998 | 11/27/19 | 878 | Hubbard, Robert W |  | 41.31
PR | 998 | 11/27/19 | 889 | McCabe, Thomas C |  | 116.36
PR | 998 | 11/27/19 | 899 | Roberts, Lake A |  | 15.3
PR | 998 | 11/27/19 | 899 | Roberts, Lake A |  | 45.9
PR | 998 | 11/27/19 | 899 | Roberts, Lake A |  | 15.3
PR | 998 | 11/27/19 | 900 | Rodriguez Arevalos, Christian |  | 18.36
PR | 998 | 11/27/19 | 901 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 11/27/19 | 901 | Romero Garza, Jesus I |  | 28.15
PR | 998 | 11/27/19 | 904 | Sanders, Allen O |  | 37.18
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/06/19 | 36 | Boss, Benjamin T |  | 19.58
PR | 998 | 12/06/19 | 36 | Boss, Benjamin T |  | 9.79
PR | 998 | 12/06/19 | 37 | Boss, Kyle A |  | 38.56
PR | 998 | 12/06/19 | 43 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 12/06/19 | 65 | Hubbard, Robert W |  | 45.44
PR | 998 | 12/06/19 | 76 | McCabe, Thomas C |  | 59.67
PR | 998 | 12/06/19 | 76 | McCabe, Thomas C |  | 23.87
PR | 998 | 12/06/19 | 86 | Roberts, Lake A |  | 24.86
PR | 998 | 12/06/19 | 86 | Roberts, Lake A |  | 15.3
PR | 998 | 12/06/19 | 87 | Rodriguez Arevalos, Christian |  | 11.48
PR | 998 | 12/06/19 | 88 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 12/06/19 | 88 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 12/06/19 | 91 | Sanders, Allen O |  | 22.72
PR | 998 | 12/13/19 | 397 | Boss, Benjamin T |  | 48.96
PR | 998 | 12/13/19 | 398 | Boss, Kyle A |  | 64.26
PR | 998 | 12/13/19 | 404 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 33.05
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 33.05
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 8.26
PR | 998 | 12/13/19 | 437 | McCabe, Thomas C |  | 50.72
PR | 998 | 12/13/19 | 447 | Roberts, Lake A |  | 76.5
PR | 998 | 12/13/19 | 449 | Romero Garza, Jesus I |  | 59.82
PR | 998 | 12/13/19 | 452 | Sanders, Allen O |  | 10.33
PR | 998 | 12/13/19 | 465 | Donelson, Richard T |  | 23.91
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/20/19 | 550 | Boss, Benjamin T |  | 48.96
PR | 998 | 12/20/19 | 551 | Boss, Kyle A |  | 64.26
PR | 998 | 12/20/19 | 579 | Hubbard, Robert W |  | 12.39
PR | 998 | 12/20/19 | 579 | Hubbard, Robert W |  | 4.13
PR | 998 | 12/20/19 | 579 | Hubbard, Robert W |  | 16.52
PR | 998 | 12/20/19 | 590 | McCabe, Thomas C |  | 23.87
PR | 998 | 12/20/19 | 600 | Roberts, Lake A |  | 30.6
PR | 998 | 12/20/19 | 602 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 12/20/19 | 605 | Sanders, Allen O |  | 20.66
PR | 998 | 12/20/19 | 618 | Donelson, Richard T |  | 14.34
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/27/19 | 707 | Boss, Benjamin T |  | 9.79
PR | 998 | 12/27/19 | 708 | Boss, Kyle A |  | 25.7
PR | 998 | 12/27/19 | 708 | Boss, Kyle A |  | 12.85
PR | 998 | 12/27/19 | 737 | Hubbard, Robert W |  | 8.26
PR | 998 | 12/27/19 | 737 | Hubbard, Robert W |  | 33.05
PR | 998 | 12/27/19 | 748 | McCabe, Thomas C |  | 32.82
PR | 998 | 12/27/19 | 748 | McCabe, Thomas C |  | 5.97
PR | 998 | 12/27/19 | 758 | Roberts, Lake A |  | 22.95
PR | 998 | 12/27/19 | 760 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 12/27/19 | 763 | Sanders, Allen O |  | 16.52
PR | 998 | 12/27/19 | 776 | Donelson, Richard T |  | 14.34
PR | 998 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/03/20 | 10 | Boss, Benjamin T |  | 25.7
PR | 998 | 01/03/20 | 11 | Boss, Kyle A |  | 33.74
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 24.79
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 16.52
PR | 998 | 01/03/20 | 51 | McCabe, Thomas C |  | 47.74
PR | 998 | 01/03/20 | 61 | Roberts, Lake A |  | 40.16
PR | 998 | 01/03/20 | 63 | Romero Garza, Jesus I |  | 36.95
PR | 998 | 01/03/20 | 66 | Sanders, Allen O |  | 16.52
PR | 998 | 01/03/20 | 81 | Donelson, Richard T |  | 9.56
PR | 998 | 01/10/20 | 283 | Boss, Benjamin T |  | 48.96
PR | 998 | 01/10/20 | 284 | Boss, Kyle A |  | 64.26
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 18.59
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 6.2
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/10/20 | 334 | Roberts, Lake A |  | 44.94
PR | 998 | 01/10/20 | 334 | Roberts, Lake A |  | 7.65
PR | 998 | 01/10/20 | 336 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 01/10/20 | 339 | Sanders, Allen O |  | 41.31
PR | 998 | 01/10/20 | 352 | Donelson, Richard T |  | 28.69
PR | 998 | 01/17/20 | 549 | Boss, Benjamin T |  | 30.6
PR | 998 | 01/17/20 | 550 | Boss, Kyle A |  | 53.01
PR | 998 | 01/17/20 | 556 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 01/17/20 | 579 | Hubbard, Robert W |  | 4.13
PR | 998 | 01/17/20 | 600 | Roberts, Lake A |  | 3.83
PR | 998 | 01/17/20 | 600 | Roberts, Lake A |  | 30.6
PR | 998 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 01/17/20 | 605 | Sanders, Allen O |  | 43.38
PR | 998 | 01/17/20 | 618 | Donelson, Richard T |  | 4.78
PR | 998 | 01/24/20 | 682 | Boss, Benjamin T |  | 44.06
PR | 998 | 01/24/20 | 682 | Boss, Benjamin T |  | 4.9
PR | 998 | 01/24/20 | 683 | Boss, Kyle A |  | 53.01
PR | 998 | 01/24/20 | 683 | Boss, Kyle A |  | 11.25
PR | 998 | 01/24/20 | 711 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/24/20 | 711 | Hubbard, Robert W |  | 12.39
PR | 998 | 01/24/20 | 736 | Sanders, Allen O |  | 39.24
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 14.34
PR | 998 | 01/31/20 | 841 | Boss, Benjamin T |  | 48.96
PR | 998 | 01/31/20 | 842 | Boss, Kyle A |  | 64.26
PR | 998 | 01/31/20 | 871 | Hubbard, Robert W |  | 4.13
PR | 998 | 01/31/20 | 892 | Roberts, Lake A |  | 30.6
PR | 998 | 01/31/20 | 892 | Roberts, Lake A |  | 15.3
PR | 998 | 01/31/20 | 897 | Sanders, Allen O |  | 68.16
PR | 998 | 01/31/20 | 903 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 01/31/20 | 911 | Donelson, Richard T |  | 19.13
PR | 998 | 02/07/20 | 32 | Boss, Benjamin T |  | 48.96
PR | 998 | 02/07/20 | 33 | Boss, Kyle A |  | 64.26
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 20.66
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/07/20 | 82 | Roberts, Lake A |  | 68.85
PR | 998 | 02/07/20 | 88 | Sanders, Allen O |  | 49.57
PR | 998 | 02/07/20 | 94 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 02/07/20 | 102 | Donelson, Richard T |  | 19.13
PR | 998 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/14/20 | 242 | Boss, Benjamin T |  | 44.06
PR | 998 | 02/14/20 | 243 | Boss, Kyle A |  | 51.41
PR | 998 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 24.79
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 16.52
PR | 998 | 02/14/20 | 281 | McCabe, Thomas C |  | 14.92
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 9.56
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 5.74
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 7.65
PR | 998 | 02/14/20 | 298 | Sanders, Allen O |  | 20.66
PR | 998 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 02/14/20 | 312 | Donelson, Richard T |  | 4.78
PR | 998 | 02/21/20 | 459 | Boss, Benjamin T |  | 33.05
PR | 998 | 02/21/20 | 460 | Boss, Kyle A |  | 38.56
PR | 998 | 02/21/20 | 514 | Sanders, Allen O |  | 59.9
PR | 998 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 02/21/20 | 528 | Donelson, Richard T |  | 9.56
PR | 998 | 02/28/20 | 687 | Boss, Benjamin T |  | 33.05
PR | 998 | 02/28/20 | 688 | Boss, Kyle A |  | 33.74
PR | 998 | 02/28/20 | 696 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 02/28/20 | 716 | Hubbard, Robert W |  | 41.31
PR | 998 | 02/28/20 | 716 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/28/20 | 716 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/28/20 | 725 | McCabe, Thomas C |  | 40.28
PR | 998 | 02/28/20 | 725 | McCabe, Thomas C |  | 11.93
PR | 998 | 02/28/20 | 725 | McCabe, Thomas C |  | 11.93
PR | 998 | 02/28/20 | 725 | McCabe, Thomas C |  | 47.74
PR | 998 | 02/28/20 | 737 | Roberts, Lake A |  | 15.3
PR | 998 | 02/28/20 | 737 | Roberts, Lake A |  | 15.3
PR | 998 | 02/28/20 | 737 | Roberts, Lake A |  | 30.6
PR | 998 | 02/28/20 | 739 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 02/28/20 | 743 | Sanders, Allen O |  | 57.83
PR | 998 | 02/28/20 | 749 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 02/28/20 | 757 | Donelson, Richard T |  | 14.34
PR | 998 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/06/20 | 50 | Boss, Kyle A |  | 38.56
PR | 998 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 03/06/20 | 78 | Hubbard, Robert W |  | 45.44
PR | 998 | 03/06/20 | 78 | Hubbard, Robert W |  | 8.26
PR | 998 | 03/06/20 | 87 | McCabe, Thomas C |  | 71.6
PR | 998 | 03/06/20 | 87 | McCabe, Thomas C |  | 14.92
PR | 998 | 03/06/20 | 87 | McCabe, Thomas C |  | 14.92
PR | 998 | 03/06/20 | 99 | Roberts, Lake A |  | 45.9
PR | 998 | 03/06/20 | 99 | Roberts, Lake A |  | 9.56
PR | 998 | 03/06/20 | 99 | Roberts, Lake A |  | 15.3
PR | 998 | 03/06/20 | 101 | Romero Garza, Jesus I |  | 28.15
PR | 998 | 03/06/20 | 105 | Sanders, Allen O |  | 68.16
PR | 998 | 03/06/20 | 119 | Donelson, Richard T |  | 19.13
PR | 998 | 03/13/20 | 351 | McCabe, Thomas C |  | 71.6
PR | 998 | 03/13/20 | 363 | Roberts, Lake A |  | 45.9
PR | 998 | 03/13/20 | 369 | Sanders, Allen O |  | 70.23
PR | 998 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 25.7
PR | 998 | 03/20/20 | 572 | Boss, Benjamin T |  | 44.06
PR | 998 | 03/20/20 | 573 | Boss, Kyle A |  | 51.41
PR | 998 | 03/20/20 | 579 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 03/20/20 | 581 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 03/20/20 | 585 | Eliassen, Cory H |  | 9.18
PR | 998 | 03/20/20 | 623 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 03/20/20 | 627 | Sanders, Allen O |  | 39.24
PR | 998 | 03/20/20 | 633 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 03/20/20 | 641 | Donelson, Richard T |  | 14.34
PR | 998 | 03/26/20 | 803 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 03/26/20 | 806 | Sanders, Allen O |  | 30.98
PR | 998 | 03/26/20 | 812 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 04/03/20 | 42 | Donelson, Richard T |  | 4.78
PR | 998 | 04/17/20 | 288 | Donelson, Richard T |  | 4.78
PR | 998 | 04/24/20 | 424 | Donelson, Richard T |  | 4.78
PR | 998 | 05/01/20 | 64 | Sanders, Allen O |  | 12.39
PR | 998 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 05/08/20 | 161 | Boss, Kyle A |  | 64.26
PR | 998 | 05/08/20 | 167 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 05/08/20 | 188 | Hubbard, Robert W |  | 16.52
PR | 998 | 05/08/20 | 215 | Sanders, Allen O |  | 61.97
PR | 998 | 05/08/20 | 221 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 05/08/20 | 231 | Donelson, Richard T |  | 9.56
PR | 998 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 05/15/20 | 315 | Boss, Benjamin T |  | 22.03
PR | 998 | 05/15/20 | 316 | Boss, Kyle A |  | 64.26
PR | 998 | 05/15/20 | 322 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 05/15/20 | 324 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 05/15/20 | 328 | Eliassen, Cory H |  | 36.72
PR | 998 | 05/15/20 | 343 | Hubbard, Robert W |  | 16.52
PR | 998 | 05/15/20 | 343 | Hubbard, Robert W |  | 12.39
PR | 998 | 05/15/20 | 366 | Romero Garza, Jesus I |  | 28.15
PR | 998 | 05/15/20 | 370 | Sanders, Allen O |  | 119.8
PR | 998 | 05/15/20 | 376 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 05/15/20 | 384 | Donelson, Richard T |  | 9.56
PR | 998 | 05/22/20 | 470 | Boss, Benjamin T |  | 33.05
PR | 998 | 05/22/20 | 477 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 05/22/20 | 479 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 05/22/20 | 483 | Eliassen, Cory H |  | 18.36
PR | 998 | 05/22/20 | 517 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 05/22/20 | 520 | Sanders, Allen O |  | 121.86
PR | 998 | 05/22/20 | 526 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 05/22/20 | 534 | Donelson, Richard T |  | 9.56
PR | 998 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 05/29/20 | 598 | Boss, Benjamin T |  | 11.02
PR | 998 | 05/29/20 | 646 | Sanders, Allen O |  | 90.88
PR | 998 | 05/29/20 | 652 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 05/29/20 | 659 | Donelson, Richard T |  | 4.78
PR | 998 | 06/05/20 | 19 | Boss, Benjamin T |  | 11.02
PR | 998 | 06/05/20 | 58 | Sanders, Allen O |  | 103.28
PR | 998 | 06/05/20 | 62 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 06/05/20 | 66 | Donelson, Richard T |  | 4.78
PR | 998 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/12/20 | 260 | Sanders, Allen O |  | 82.62
PR | 998 | 06/19/20 | 399 | Hubbard, Robert W |  | 12.39
PR | 998 | 06/19/20 | 416 | Sanders, Allen O |  | 72.29
PR | 998 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/26/20 | 541 | Hubbard, Robert W |  | 8.26
PR | 998 | 07/02/20 | 44 | Sanders, Allen O |  | 24.79
PR | 998 | 07/02/20 | 44 | Sanders, Allen O |  | 12.39
PR | 998 | 07/02/20 | 50 | Donelson, Richard T |  | 9.56
PR | 998 | 07/10/20 | 182 | Donelson, Richard T |  | 4.78
PR | 998 | 07/24/20 | 442 | Sanders, Allen O |  | 8.26
PR | 998 | 07/31/20 | 537 | Sanders, Allen O |  | 8.26
AR | 999 | 09/19/18 | 475 | Compass Harbor Construction, LLC $Vail |  | -52800 | 037191
AR | 999 | 10/19/18 | 521 | Compass Harbor Construction, LLC $Vail |  | -107100 | 037207
AR | 999 | 10/19/18 | 533 | Compass Harbor Construction, LLC $Vail |  | -52800 | 037218
AR | 999 | 10/19/18 | 533 | Compass Harbor Construction, LLC $Vail |  | -13200 | 037218
AR | 999 | 10/19/18 | 867 | Compass Harbor Construction, LLC $Vail |  | 52800 | 037222
AR | 999 | 10/19/18 | 867 | Compass Harbor Construction, LLC $Vail |  | 13200 | 037222
AR | 999 | 10/19/18 | 868 | Compass Harbor Construction, LLC $Vail |  | -13200 | 037223
AR | 999 | 11/01/18 | 112 | Compass Harbor Construction, LLC $Vail |  | 13200 | 037224
AR | 999 | 11/16/18 | 519 | Compass Harbor Construction, LLC $Vail |  | -35700 | 037225
AR | 999 | 11/16/18 | 519 | Compass Harbor Construction, LLC $Vail |  | -4800 | 037225
AR | 999 | 11/16/18 | 537 | Compass Harbor Construction, LLC $Vail |  | -13200 | 037242
AR | 999 | 12/14/18 | 349 | Compass Harbor Construction, LLC $Vail |  | -4800 | 037252
AR | 999 | 12/14/18 | 349 | Compass Harbor Construction, LLC $Vail |  | -11200 | 037252
AR | 999 | 12/14/18 | 349 | Compass Harbor Construction, LLC $Vail |  | -4100 | 037252
AR | 999 | 12/14/18 | 349 | Compass Harbor Construction, LLC $Vail |  | -4100 | 037252
AR | 999 | 12/14/18 | 349 | Compass Harbor Construction, LLC $Vail |  | -3086 | 037252
AR | 999 | 01/18/19 | 551 | Compass Harbor Construction, LLC $Vail |  | -17850 | 037269
AR | 999 | 02/20/19 | 573 | Compass Harbor Construction, LLC $Vail |  | -5950 | 037295
AR | 999 | 03/20/19 | 683 | Compass Harbor Construction, LLC $Vail |  | -100260 | 037304
AR | 999 | 03/20/19 | 683 | Compass Harbor Construction, LLC $Vail |  | -8635 | 037304
AR | 999 | 03/20/19 | 683 | Compass Harbor Construction, LLC $Vail |  | 15504 | 037304
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | -11140 | 037321
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | -55800 | 037321
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | -112255 | 037321
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | -94160 | 037321
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | -30193 | 037321
AR | 999 | 04/19/19 | 605 | Compass Harbor Construction, LLC $Vail |  | 20520 | 037321
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -6200 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -25905 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -11770 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -8260 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -241540 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -241540 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | -60250 | 037347
AR | 999 | 05/20/19 | 514 | Compass Harbor Construction, LLC $Vail |  | 77292 | 037347
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -49700 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -70000 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -17270 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -5885 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -15095 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -45290 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -226580 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -150965 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | -9435 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | 61788 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | 5800 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | 47200 | 037359
AR | 999 | 06/19/19 | 603 | Compass Harbor Construction, LLC $Vail |  | 2450 | 037359
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -5800 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -3540 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -19000 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -34100 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -39000 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -39000 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -135864 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -39000 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -132090 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -39000 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | 52896 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -6935 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -1950 | 037381
AR | 999 | 07/19/19 | 606 | Compass Harbor Construction, LLC $Vail |  | -2000 | 037381
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -5900 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -6900 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -8635 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -5885 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -15097 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -15095 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -15095 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -15096 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -47175 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -11000 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -8550 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -8560 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -12760 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -4784 | 037395
AR | 999 | 08/15/19 | 758 | Compass Harbor Construction, LLC $Vail |  | -3837 | 037395
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 5900 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 6900 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 8635 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 5885 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 15097 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 15095 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 15095 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 15096 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 47175 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 11000 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 8550 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 8560 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 12760 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 4784 | 037402
AR | 999 | 09/09/19 | 116 | Compass Harbor Construction, LLC $Vail |  | 3837 | 037402
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -8635 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -5885 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -15097 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -15095 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -15095 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -15096 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -47175 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -2750 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -8550 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -8560 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -12760 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -4784 | 037403
AR | 999 | 09/09/19 | 117 | Compass Harbor Construction, LLC $Vail |  | -3837 | 037403
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -5900 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -6900 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -11000 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -11000 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -8250 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -950 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -29960 | 037415
AR | 999 | 09/20/19 | 571 | Compass Harbor Construction, LLC $Vail |  | -3264 | 037415
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -17700 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -20700 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -11000 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -4000 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -4500 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -4280 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | 739 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | 480 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -8955 | 037427
AR | 999 | 10/18/19 | 540 | Compass Harbor Construction, LLC $Vail |  | -5368 | 037427
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 17700 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 20700 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 11000 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 4000 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 4500 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 4280 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | -739 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | -480 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 8955 | 037430
AR | 999 | 10/18/19 | 585 | Compass Harbor Construction, LLC $Vail |  | 5368 | 037430
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -16900 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -19900 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -11000 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -4000 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -4500 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -4280 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | 739 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | 480 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -8955 | 037431
AR | 999 | 10/18/19 | 586 | Compass Harbor Construction, LLC $Vail |  | -5368 | 037431
AR | 999 | 11/18/19 | 559 | Compass Harbor Construction, LLC $Vail |  | -1600 | 037441
AR | 999 | 11/18/19 | 559 | Compass Harbor Construction, LLC $Vail |  | -9600 | 037441
AR | 999 | 11/18/19 | 559 | Compass Harbor Construction, LLC $Vail |  | -3994 | 037441
AR | 999 | 11/18/19 | 559 | Compass Harbor Construction, LLC $Vail |  | -350 | 037441
AR | 999 | 12/13/19 | 480 | Compass Harbor Construction, LLC $Vail |  | -4000 | 037456
AR | 999 | 12/13/19 | 480 | Compass Harbor Construction, LLC $Vail |  | -4000 | 037456
AR | 999 | 12/13/19 | 480 | Compass Harbor Construction, LLC $Vail |  | -4000 | 037456
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -115 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -240 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -1390 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -1590 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -11900 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -18260 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -23030 | 037471
AR | 999 | 01/20/20 | 656 | Compass Harbor Construction, LLC $Vail |  | -1152 | 037471
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -800 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -800 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -18070 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -20670 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -6360 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -6360 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -770 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -3588 | 037483
AR | 999 | 02/19/20 | 448 | Compass Harbor Construction, LLC $Vail |  | 3853 | 037483
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -6360 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -9540 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -3180 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -530 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -1343 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -4200 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -540 | 037494
AR | 999 | 03/20/20 | 654 | Compass Harbor Construction, LLC $Vail |  | -2472 | 037494
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -2185 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -4560 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -8340 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -3180 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -1125 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -3190 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -1196 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -816 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -773 | 037502
AR | 999 | 05/20/20 | 448 | Compass Harbor Construction, LLC $Vail |  | -4203.5 | 037502
AR | 999 | 06/18/20 | 430 | Compass Harbor Construction, LLC $Vail |  | -331 | 037510
AR | 999 | 06/18/20 | 430 | Compass Harbor Construction, LLC $Vail |  | -559 | 037510