## 01 Overview
OWP #2052 · Fifth & Roy
Farrell-McKenna Construction LLC · 107 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 2231035
Revised budget (expenses) | 1665799.11
Forecast net profit | 565235.89
Forecast margin | 25.34%
Progress to Date
Work complete (billed) | 2231035
Retention held | 111551.75
Earned less retention | 2119483.25
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 58255.93
AP | 485225.95
PR | 673729.1
AR | -2231035

## 02 Job Info
JOB #2052 · FARRELL-McKENNA · FIFTH & ROY — FULL PROJECT INFORMATION
Sourced from executed Master Contract (#22-0000 / Project #17-100) + Job Ticket 7-25-2019 + GDrive folder scan
IDENTITY
OWP Job ID | 2052
Project Name | Fifth & Roy
GC Project Number | 17-100
Subcontract Number | 22-0000
Effective Date | February 9, 2018
Site Address | 701 5th Ave North, Seattle, WA 98109
City | Seattle (Lower Queen Anne)
Ground-Floor Tenant | Blarney Stone Irish pub (retail tenant)
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Farrell-McKenna Construction LLC
GC Address | 17786 Des Moines Memorial Dr, Burien, WA 98148
GC Phone | (206) 241-2600
GC Fax | (206) 243-0654
GC Contract Signatory | Initials "CM" on contract pages (full name on Meeting Minutes — see GDrive)
GC Project Manager | TBD — see Meetings-Schedules folder for sub coordination meeting attendees
GC Superintendent | TBD
GC Project Engineer | Michael McKenna (referenced in 7/24/19 email re Lotus L6 sinks)
GC Field Contact | Joe (referenced in Job Ticket 6/6/19 re irrigation deduct meter)
PROJECT TEAM — OWP (SUBCONTRACTOR)
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S, Suite 200, Kirkland, WA 98003
OWP Phone | (425) 968-8314
OWP Email | miked@owpllc.net
OWP Contract Signatory | Michael Donelson (initials MD on contract)
OWP Contact (per contract) | Michael Donelson
OWP Top-Hours Foremen | TBD — see Daily Reports / PR records (top hours: Frausto Mendoza Pedro 1,413; Wennig Johnathan 1,341; Velasquez Cruz Denis 1,340)
OWP License # | ONEWAWP895BU
OWP State Tax ID | 603 078 218
OWP Savings # | 138101826916
PROJECT TEAM — OWNER
Owner Legal Name | Fifth North & Roy LLC
Owner Address | 17786 Des Moines Memorial Dr, Burien, WA 98148 (same address as GC — sister development entity)
Owner Phone | (206) 241-2600
PROJECT TEAM — DESIGN
Architect | Hewitt Architects
Architect Address | 101 Stewart Street, Suite 200, Seattle, WA 98101
Architect Phone | (206) 834-3821
Civil Engineer | KPFF Consulting Engineers
Civil Address | 1601 Fifth Avenue, Suite 1600, Seattle, WA 98101
Civil Phone | (206) 622-5822
Structural Engineer | Bykonen Carter Quinn
Structural Address | 820 John Street, Suite 201, Seattle, WA 98109
Structural Phone | (206) 264-7784
MEP / Plumbing Engineer | Rushing Engineering
INSURANCE & BONDING
Bond Status | Not Required (per contract Page 1)
Insurance | OWP carries own CGL/WC; Bond Not Required per contract
CONTRACT & FINANCIALS
Original Contract | $2,134,000 (Item 22-0000 Unit Trim, Rough-in, Building Plumbing Systems)
Final Contract | $2,231,035
Net Change Orders | +$97,035 net (+4.5%) — additive growth, healthy posture
Retention Percentage | 5%
Retention Held | $111,551.75 (still held per JDR 04/03/2026 · 6+ yrs aged)
WSST | Item 00-0000 — Washington State Sales Tax (separately invoiced, N/A on contract)
Schedule | February 9, 2018 (contract effective) · first Sage PR Mar 23, 2018 → December 19, 2019 (last AR invoice 037460) · ~22 months
SCOPE & FIXTURES (per Job Ticket 7-25-2019)
Plumbing Units | 107
Resident Unit Trim | 111 Toto CST743E elongated bowl toilets (Bemis 500EC seat) + 6 Toto CST744EL ADA elongated + 1 Toto CST744EFN.10#01 specialty (unit 217); 112 Kohler K2355 undercounter lavs + 6 K2882 ADA (Delta 559LF-PP faucet); 115 Fibercare ET60-32RTHC80S tub/shower stalls w/ Delta R10000MF + T14459 valve; 6 Delta 51549 ADA handheld showers; 1 white Bestbath 38" shower stall (R10000MF + T14259); 93 Blanco 235829 nested SS undercounter sinks (Type B, per approval 10/22/18); 5 Blanco 442079 SS sinks ADA; 8 Lotus 2718-10D L6 sinks Type B + 1 Type A (per Michael McKenna email 7/24/19); 107 Delta 9159-DST chrome kitchen faucets; 107 ISE Badger 1 1/3hp garbage disposals; 107 dishwasher rough-ins; 107 ice-maker box rough-ins; 107 washer rough-ins
Amenity / Lobby Fixtures | ASSE 1070 mixing valves at amenity lavs (scald protection); 4 Watts FD15 floor drains lobby/amenity restrooms; 4 Toto CST454 ADA toilets; 1 Kohler K-2330 lobby lav (Delta 559LF-BL-LPU black faucet w/grid strainer); 2 Kohler K-2210 L1 amenity lavs (Delta 559LF-BLLPU + Brizo RP72412BL grid); 1 K-2330 roof amenity (Delta 559LF-SSLPU + Delta RP6346SS grid); 4 Kohler K3894 SS sinks (media room, north/south rooftops, leasing); 1 lobby coffee bar; 4 ISE Badger 1 disposals at amenities; 4 dishwashers (rough/connect at amenities); refrigerator/icemaker rough-ins; 2 Mustee 63M mop sinks (Rooms 115 + 650, T&S Brass B-0665-BSTR faucet); 1 Ridalco SS dog wash sink with pre-rinse; 1 Fitness Elkay LZSTL8WSSP drinking fountain w/ bottle filler
Building Systems | 1 wvs/cw stub at 2 retail spaces; 1 common gas supply (1 earthquake valve + 3 water heaters + 2 rooftop fire pits + 2 rooftop BBQ + 1 rooftop amenity cooktop area B Room 610 + 1 rooftop amenity fireplace area A Room 611); rooftop HVAC TBD (Rushing shows 4, Mech shows less); 1 gas supply roughin from PSE meter; 4 gas submeters; 2 Woodford 24 keyless hosebibs garage mech rooms; 10 Woodford B65 frostproof keyless hose bibs ext; 2 Woodford yard hydrants rooftop; 1 Woodford hot/cold trash room; 3 Bock 399,000 BTU gas-fired condensing water heaters w/ PVC vent; 1 hot water expansion tank; 2 hot water circulating pumps w/ Tekmar pump control; 2 thermostatic master mixing valves; 2 Watts backflow valves DWS; 1 Watts pressure reducing; 1 duplex booster package (added per CO #2); 1 Watts backflow for irrigation; 1 deduct meter (per Joe conversation 6/6/19 — may be street-mounted, not procured)
Drainage Systems | 1 Quality Concrete 36×36 sand/oil basin garage drainage; 1 type 241 concrete basin foundation drainage silt collection; SP-1 60" basin w/ duplex pumps garage floor drains; SP-2 72" basin w/ duplex pumps storm detention + foundation drains; SP-3 60" basin w/ duplex pumps deck drain + bio-retention storm; 1 foundation drain 4" Master Meter Octave Ultrasonic w/ Itron 100W ERT remote kit (in 60" basin); 1 PVC control structure detention vault; 1 NDS DS-090N trench drain w/ DS-232 grate; 9 Watts FD33/Proset P65X garage floor drains; 11 Watts FD15/ProSet P65X mech/trash/loading-dock drains; 12 deck drains Roy/5th Ave side (overflow check); 9 ballast roof drains units 411-415, 516, 602-605; 42 Watts cast iron drains w/ overflow + bio-retention SLOTTED piping per 12/L3.11; 16 Watts cast iron drains L2-L4 overflow; 7 Watts FD15 upper roof gutters per RFI-210; 26 Watts cast iron drains roof; 1 PVC foundation wall collector pipe per RFI #009 (excludes miradrain adaptors); 4 backwater valves L1 sanitary; 1 grease waste line stub for future TI
Scope EXCLUDES (per ticket) | Shoreline plumbing/gas/boiler permits/plan review (by owner). Excavation/backfill. Hoisting/concrete basin placement. Foundation/footing drains. HVAC condensate. Pump systems for storm/sanitary (gravity assumed). Unit meter jumpers (by others). Fire-rated tub/shower enclosures. Heat trace. Generator. Pipe protection bollards. Water heater housekeeping pad. Unit meters. Wash machine drain pans. Kitchen sink garbage disposals. Sewer hookup. Landscape irrigation. Exterior side sewers/storm sewers. Retentions above 5%. Bonding. WSST. Prevailing wage rates.
Blarney Stone Retail Tenant | Ground-floor retail tenant — separate Blarney Stone floor drain markup PDF/JPG on file (1122 plan revised)
DOCUMENTS ON FILE (GDrive)
Executed Master Contract | One Way & FMC - Master Contract - 5th & Roy FULLY EXECUTED.pdf (20 pages)
Exhibit J&K (SOV + Pay App) | 8 - ONE WAY Exhibit J&K (Schedule of Values and Application for Payment).xls
Exhibit L&M (Release Forms) | 9 - ONE WAY Exhibit L&M (Release on Progress Payment).xls
Job Tickets | 10+ ticket revisions (Oct 2018 → Mar 2019, then 7-25-2019 latest)
Latest Ticket | Fifth and Roy job ticket 07-25-2019.pdf
RFIs | many (RFI #009, RFI #117, RFI #143, RFI #210 referenced in Job Ticket — full inventory in ASI-RFI/)
ASIs | see ASI-RFI/ folder
Permits | see Permits/ folder; Farrell McKenna Reseller Permit 2016-2018.pdf on file
Vendor Subfolders | Franklin 5th & Roy (MEP design subfolder)
GDrive Status | Folder fully accessible at this run. Contract + ticket + change orders + permits all read-through.
FIXTURE SCHEDULE (verified from Job Ticket)
Sourced from latest Job Ticket. Two totals shown: 'Main' = standard plumbing-engineering fixture schedule (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + coffee bar). 'Inclusive' adds appliance rough-ins (dishwasher + washer + icemaker) and matches the 2020 dashboard convention.
Toilets (water closets) | 122
Lavs (lavatory sinks) | 122
Tub/showers + handshowers | 122
Kitchen sinks | 111
Drinking fountains | 1
Mop sinks | 2
Dog-wash sink | 1
Lobby coffee bar | 1
MAIN FIXTURE TOTAL | 482
INCLUSIVE FIXTURE TOTAL (with appliance rough-ins) | 814
Main fixtures / unit: 4.50 · Inclusive / unit: 7.61

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 2134000 | 2231035 | 97035
Executed change orders (net) | 0 | 97035 | 97035
Total contract value | 2134000 | 2328070 | 194070
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
STATEMENT OF VALUES — SUMMARY
Original Contract (Item 22-0000) | 2134000
WSST (Item 00-0000) | N/A — separately invoiced
Net Change Orders | 97035
Final Contract Value | 2231035
Total Billed to Date | 2231035
Retention Held (5%) | 111552
Net Paid to OWP | 2119483
Percent Complete | 100.0%
PAY APPLICATION DETAIL — DATA SOURCE
Per-pay-app history lives in 2052-Farrell, 5th & Roy/Billing/ on GDrive. JDR shows 12 distinct AR invoices Dec 2018 → Dec 2019 (037260, 037266, 037293, 037305, 037325, 037345, 037361, 037378, 037386, 037422, 037460). Contract uses Exhibit J&K (Schedule of Values + App for Payment forms).

## 05 Change Orders
Change Order Log
CHANGE ORDER LOG — SOURCE: GDRIVE/CHANGE ORDERS/
Net JDR delta: original $2,134,000 → final $2,231,035 = +$97,035 (+4.5% additive)
# | CO Reference | Description | Type | Source
1 | CO #2 | Added duplex booster package at water entry room | Owner-Directed | Job Ticket 7-25-2019 line item
2 | RFI #009 | Foundation wall collector PVC pipe (excludes miradrain adaptors) per revised drawings | Field/Coord | Job Ticket 7-25-2019 (drainage section)
3 | RFI #210 | 7 Watts FD15 drains for upper roof gutters | Field/Coord | Job Ticket 7-25-2019 (drainage section)
4 | Email 7/24/19 | Lotus 2718-10D L6 sinks (8 Type B + 1 Type A) per Michael McKenna | Submittal | Job Ticket 7-25-2019 line items
5 | Conv 6/6/19 | Deduct meter for irrigation water supply — meter may be street-mounted (no order) | Field/Coord | Job Ticket 7-25-2019 line item with handwritten note
6 | Approval 10/22/18 | Blanco 235829 nested SS undercounter sinks (replaces 518171 spec) | Submittal | Job Ticket 7-25-2019 line item
GDRIVE CO INVENTORY NOTE
Full CO/COR ledger in 2052-Farrell, 5th & Roy/Change Orders/ folder. JDR-implied net is +$97,035 (+4.5%). The references above are CO/RFI mentions extracted from the Job Ticket; per-CO dollar amounts can be reconciled by reading the SCO/COR PDFs directly. Farrell McKenna Reseller Permit 2016-2018.pdf is also on file at the project root.

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 10700 | 11000 | 5783 | 5217 | 0 | 52.57%
101 | Takeoff & Purchase Labor | 18190 | 20540 | 12636.5 | 7903.5 | 0 | 61.52%
110 | Underground Labor | 25825 | 27925 | 13156 | 14769 | 0 | 47.11%
111 | Garage Labor | 110040 | 113215 | 33231 | 79984 | 0 | 29.35%
112 | Canout Labor | 21300 | 22040 | 9800 | 12240 | 0 | 44.46%
120 | Roughin Labor | 195065 | 211765 | 201052.75 | 10712.25 | 0 | 94.94%
130 | Finish Labor | 35640 | 35780 | 34751 | 1029 | 0 | 97.12%
140 | Gas Labor | 9750 | 10050 | 4126.5 | 5923.5 | 0 | 41.06%
141 | Water Main/Insulation Lab | 49650 | 49650 | 117138.5 | -67488.5 | 0 | 235.9%
142 | Mech Room Labor | 16000 | 19000 | 11567 | 7433 | 0 | 60.88%
210 | Underground Material | 20325 | 20325 | 13998.46 | 6326.54 | 0 | 68.87%
211 | Garage Material | 70875 | 73930 | 30100.97 | 43829.03 | 0 | 40.72%
212 | Canout Material | 21300 | 22040 | 11577.93 | 10462.07 | 0 | 52.53%
220 | Roughin Material | 112170 | 118820 | 87583.59 | 31236.41 | 0 | 73.71%
230 | Finish Material | 404000 | 419844 | 273004.96 | 146839.04 | 0 | 65.03%
240 | Gas Material | 7500 | 8425 | 6559.15 | 1865.85 | 0 | 77.85%
241 | Water Main/Insulation Mat | 69550 | 69550 | 41276.8 | 28273.2 | 0 | 59.35%
242 | Mech Room Material | 20000 | 22000 | 15179.21 | 6820.79 | 0 | 69%
251 | T&M Material | 0 | 0 | 81.68 | -81.68 | 0 | 0%
600 | Subcontractor | 25500 | 25500 | 13352 | 12148 | 0 | 52.36%
601 | Engineering/Plans | 50000 | 51250 | 35026.44 | 16223.56 | 0 | 68.34%
602 | Rental Equipment | 8000 | 8400 | 591.82 | 7808.18 | 0 | 7.045%
603 | Permits & Licenses | 16780 | 16780 | 8631.5 | 8148.5 | 0 | 51.44%
607 | Other Expenses | 12000 | 12000 | 6517.37 | 5482.63 | 0 | 54.31%
995 | Payroll Burden | 223194.56 | 236116.28 | 196578.34 | 39537.94 | 0 | 83.25%
998 | Payroll Taxes | 37650.24 | 39853.83 | 33908.51 | 5945.32 | 0 | 85.08%
TOTAL |  | 1591004.8 | 1665799.11 | 1217210.98 | 448588.13 | 0 | 73.07%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 520965 | 443242.25 | 77722.75 | 85.08%
Material | 9 | 754934 | 479362.75 | 275571.25 | 63.5%
Overhead | 5 | 113930 | 64119.13 | 49810.87 | 56.28%
Burden | 2 | 275970.11 | 230486.85 | 45483.26 | 83.52%
TOTAL | 26 | 1665799.11 | 1217210.98 | 448588.13 | 73.07%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 11000 | 5783 | 5217 | -47.43% | UNDER
101 | Takeoff & Purchase Labor | 20540 | 12636.5 | 7903.5 | -38.48% | UNDER
110 | Underground Labor | 27925 | 13156 | 14769 | -52.89% | UNDER
111 | Garage Labor | 113215 | 33231 | 79984 | -70.65% | UNDER
112 | Canout Labor | 22040 | 9800 | 12240 | -55.54% | UNDER
120 | Roughin Labor | 211765 | 201052.75 | 10712.25 | -5.059% | ON
130 | Finish Labor | 35780 | 34751 | 1029 | -2.876% | ON
140 | Gas Labor | 10050 | 4126.5 | 5923.5 | -58.94% | UNDER
141 | Water Main/Insulation Lab | 49650 | 117138.5 | -67488.5 | 135.9% | CRITICAL
142 | Mech Room Labor | 19000 | 11567 | 7433 | -39.12% | UNDER
210 | Underground Material | 20325 | 13998.46 | 6326.54 | -31.13% | UNDER
211 | Garage Material | 73930 | 30100.97 | 43829.03 | -59.28% | UNDER
212 | Canout Material | 22040 | 11577.93 | 10462.07 | -47.47% | UNDER
220 | Roughin Material | 118820 | 87583.59 | 31236.41 | -26.29% | UNDER
230 | Finish Material | 419844 | 273004.96 | 146839.04 | -34.97% | UNDER
240 | Gas Material | 8425 | 6559.15 | 1865.85 | -22.15% | UNDER
241 | Water Main/Insulation Mat | 69550 | 41276.8 | 28273.2 | -40.65% | UNDER
242 | Mech Room Material | 22000 | 15179.21 | 6820.79 | -31% | UNDER
251 | T&M Material | 0 | 81.68 | -81.68 | 0% | UNBUDGETED
600 | Subcontractor | 25500 | 13352 | 12148 | -47.64% | UNDER
601 | Engineering/Plans | 51250 | 35026.44 | 16223.56 | -31.66% | UNDER
602 | Rental Equipment | 8400 | 591.82 | 7808.18 | -92.95% | UNDER
603 | Permits & Licenses | 16780 | 8631.5 | 8148.5 | -48.56% | UNDER
607 | Other Expenses | 12000 | 6517.37 | 5482.63 | -45.69% | UNDER
995 | Payroll Burden | 236116.28 | 196578.34 | 39537.94 | -16.75% | UNDER
998 | Payroll Taxes | 39853.83 | 33908.51 | 5945.32 | -14.92% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 110029.79 | 89 | 22.68%
Keller Supply Company | 98682.59 | 33 | 20.34%
Consolidated Supply Co. | 76452.43 | 61 | 15.76%
California Hydronics Corp | 54714 | 8 | 11.28%
Ferguson Enterprises, Inc. #3007 | 54268.63 | 49 | 11.18%
Franklin Engineering | 34755.75 | 5 | 7.163%
Capital One Credit Card | 17324.5 | 43 | 3.57%
Quality Concrete Products, Inc. $32 | 11277 | 7 | 2.324%
Patchworks, Inc. | 6630 | 1 | 1.366%
Rosen Supply Company, Inc. $Fifth & Roy | 5742.65 | 4 | 1.184%
Mechanical Resource Services, Inc. | 4000 | 1 | 0.8244%
Scan2Core, Inc. | 2722 | 4 | 0.561%
Consolidated Supply Co. $5th Roy | 2208.55 | 1 | 0.4552%
Citibank Credit Card | 1895 | 7 | 0.3905%
Lotus United, LLC | 1395 | 1 | 0.2875%
Core & Main LP $HD Supply Waterworks | 1280 | 1 | 0.2638%
Best Bath Systems | 985.55 | 1 | 0.2031%
Sunbelt Rentals, Inc. | 591.82 | 2 | 0.122%
DRSi | 270.69 | 2 | 0.05579%
Rosen Supply Company, Inc. $Reserve | 0 | 2 | 0%
TOTAL AP | 485225.95 | 322

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Frausto Mendoza, Pedro | 1413 | 31952 | 22.6129 | JOURNEYMAN
Wennig, Johnathan M | 1341 | 43087 | 32.1305 | JOURNEYMAN
Velasquez Cruz, Denis M | 1340 | 41653 | 31.0843 | JOURNEYMAN
Martinez Reyes, Juan C | 1288 | 36015 | 27.962 | JOURNEYMAN
Velasquez Cruz, Osman N | 1281 | 30554 | 23.8517 | JOURNEYMAN
Waites, Thaddeus Z | 1192.5 | 53703 | 45.034 | LEAD/SUPERVISOR
Crespin Portillo, Juan D | 1190 | 21184 | 17.8017 | APPRENTICE/HELPER
Ascencio, Jose L | 1060 | 30796 | 29.0528 | JOURNEYMAN
Cornejo Orellana, Carlos E | 817 | 18347 | 22.4565 | JOURNEYMAN
Serrano, Jeremiah G | 649 | 10916 | 16.8197 | APPRENTICE/HELPER
Barnhart, Joseph N | 622.5 | 30174 | 48.4723 | LEAD/SUPERVISOR
Garcia Perez, Ervey O | 551 | 8816 | 16 | APPRENTICE/HELPER
Cruz Gonzalez, Julio C | 360 | 9363 | 26.0083 | JOURNEYMAN
McCabe, Thomas C | 280 | 9752 | 34.8286 | JOURNEYMAN
Gerard, Jordan E | 268 | 9888 | 36.8955 | LEAD/SUPERVISOR
Cruz Reyes, Jose | 245 | 7201 | 29.3918 | JOURNEYMAN
Gerard, Jeffrey S | 220.5 | 11394 | 51.6735 | LEAD/SUPERVISOR
Jimenez Alvarenga, Gerson M | 206 | 4796 | 23.2816 | JOURNEYMAN
Jimenez Montiel, Carlos A | 189 | 3024 | 16 | APPRENTICE/HELPER
Donelson, Richard T | 106 | 6625 | 62.5 | LEAD/SUPERVISOR
Sanders, Allen O | 104.5 | 5470 | 52.3445 | LEAD/SUPERVISOR
Kinssies, Jr, John E | 93 | 2799 | 30.0968 | JOURNEYMAN
Villalobos Tejada, Carlos F | 88 | 1500 | 17.0455 | APPRENTICE/HELPER
Mendoza, Edgar E | 82 | 2004 | 24.439 | JOURNEYMAN
Hubbard, Robert W | 80 | 3974 | 49.675 | LEAD/SUPERVISOR
Taylor, Evan R | 69 | 2288 | 33.1594 | JOURNEYMAN
Vazquez Popoca, Jose N | 48 | 816 | 17 | APPRENTICE/HELPER
Guerrero, Ali A | 47.5 | 808 | 17.0105 | APPRENTICE/HELPER
Rodriguez Arevalos, Christian | 38 | 986 | 25.9474 | JOURNEYMAN
Trower-Kelly, Fidel D | 24 | 432 | 18 | APPRENTICE/HELPER
Sepulveda Gonzalez, Alfredo | 23 | 741 | 32.2174 | JOURNEYMAN
Wilson, Garret A | 23 | 851 | 37 | LEAD/SUPERVISOR
Stahlschmidt, John P | 16 | 304 | 19 | APPRENTICE/HELPER
Eliassen, Cory H | 16 | 432 | 27 | JOURNEYMAN
Mendoza Galdamez, Geovanny A | 14 | 224 | 16 | APPRENTICE/HELPER
Gauthier, Dillon R | 5 | 85 | 17 | APPRENTICE/HELPER
Roberts, Lake A | 5 | 135 | 27 | OT-ONLY
Barbosa, Michael S | 3 | 75 | 25 | JOURNEYMAN
Mendoza Morales, Jesus A | 3 | 78 | 26 | JOURNEYMAN

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 8 | 2617 | 122080 | 16.99%
JOURNEYMAN | 19 | 9958 | 272918 | 64.66%
APPRENTICE/HELPER | 11 | 2821.5 | 48109 | 18.32%
OT-ONLY | 1 | 5 | 135 | 0.03246%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 15402
Active workers | 39
Hours per unit (to date) | 143.9
Revenue per labor hour (billed) | 144.86
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 25.34% | 34% | -8.665%
Roughin labor share (code 120) | 40.65% | 45% | -4.351%
Top vendor concentration | 22.68% | 38% | -15.32%
Hours per unit | 143.9393 | 95 | 48.9393

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Water Main/Insulation Lab (141) CRITICAL overrun | ⚠ WATCH | Actual $117,138 vs revised $49,650 (+136%) — needs immediate attention
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 23% of AP ($110,030) — acceptable
Retention aging | ✓ OK | $111,552 held · 5.0% of billed · standard range
Forecast margin | ✓ OK | 25.3% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 1217210.98 | 1217210.98 | 0
Revenue billed (AR ·-1) | -2231035 | 2231035 | -4462070
AP source total |  | 485225.95 | —
PR source total |  | 673729.1 | —
GL source total |  | 58255.93 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2052 live project. 17-tab JCR schema on revised budget basis.
2026-04-25 | v1.1 · enriched | Patched by enrich_2052.py: filled SOV-PayApps and Change Orders tabs (were empty), expanded Job Info from 13 rows to 60+ rows of key-players + contract + permit + fixture detail. Source: executed Master Contract #22-0000 (Project #17-100) + Job Ticket 7-25-2019 + GDrive folder scan + JDR AR invoice ledger.