## 01 Overview
OWP #2053 · Bellevue Parkside
Compass Harbor Construction · 135 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 2332680
Revised budget (expenses) | 1684489.42
Forecast net profit | 648190.58
Forecast margin | 27.79%
Progress to Date
Work complete (billed) | 2332680
Retention held | 113684
Earned less retention | 2218996
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 85030.76
AP | 488543.88
PR | 824969.92
AR | -2332680

## 02 Job Info
JOB #2053 · COMPASS HARBOR CONSTRUCTION · Bellevue Parkside (BLU Apartments) — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract 22-0500 (DocuSign EF1187E8-...).
IDENTITY
OWP Job ID | 2053
Project Name | Bellevue Parkside (BLU Apartments)
Site Address | 75 102nd Ave NE, Bellevue WA 98004
Subcontract Number | 22-0500 (DocuSign EF1187E8-...)
Effective Date | May 23, 2018
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Compass Harbor Construction
GC Address | 11332 NE 122nd Way Ste 350, Kirkland WA 98034 · (206) 320-8741
GC Contract Signatory | Ryan Ames, Vice-President
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson, VP
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Bellevue Parkside, LP
Owner Address | 600 108th Ave NE Suite 1010, Bellevue WA 98004
PROJECT TEAM — DESIGN
Architect | Encore Architects
MEP / Plumbing Engineer | Franklin Engineering
INSURANCE & BONDING
Insurance Type | OCIP / Wrap-up — OCIP enrollment cert + 18-19 COI on file
Retention | 5% per contract
CONTRACT
Contract Value | $2,241,309 (originally $2,240,765, revised to $2,241,309 with initials)
CHANGE-EVENT META
Executed CO Count | 11
COR Count | 10
RFI Count | 50
ASI Count | 3
CO Inventory | CO01 P3 Gridline 7 Drainage · CO02 P1+LB Underslab Drains · CO03 PT Deck Sleeves · CO04 Added FCU 2/3 Bedroom Units · CO05 Unit Sinks · CO06 L3 IDF Dedicated Cooling · CO07 L1 Added Hose Bibs · CO08 Roof Gas L6 Drain Heated/Soft Close Toilets · Compass Directed EWA · Work Room Sink
COR Themes | COR01-02 Added Wall Drainage P1/P2 (RFI-042.1) · COR03 Retail Sleeves Future TI · COR04 Added Condensate Drains · COR05/05r1 Drinking Fountain + Bottle Filler · COR06 Delete Lav+Kitchen Sinks · COR07 Unit Plumbing Fixture Changes · COR08 Gas Piping Roof Heaters · COR09 L3 IDF Condensate · COR10 Unit 117 Tub Drain Core Drill (OLD)
Key RFIs | RFI#012 Water Meter Locations · RFI#014 Patio Drain Overflows · RFI#021 P3 NW Plumbing · RFI#031 P1 Trash Floor Drain · RFI#042.1 P3 Wall Drainage · RFI#054 Underslab Drainage Rock · RFI#084 P3 FD+Mop Sink Relocate · RFI#094.1 GYM Filling Station · RFI#149 Delete 5 Lav Sinks · RFI#163 4in Water Service · RFI#187 L1 Hose Bibs · RFI#203 P3 FS Revisions · RFI#229 X03 Vent Pipe · RFI#246 Unit 408+410 Vent Reroute · RFI#261 Grease Interceptor + Parking
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Compass Parkside job ticket 02-17-2020.pdf (latest of 11 ticket revisions)
GDrive Folder | Job Books - Completed Jobs/2053-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets | 167 | 159 Gerber Viper WS-21-512 + 7 ADA Gerber Viper HE-21-519 + 1 amenity ADA
Heated toilet seats | 167 | Bemis H1900NL — OWP responsible for plug-in + cord wrap
Lavs | 169 | 172 Delta 559LF-PP - 5 deleted per RFI-149 = 167; +1 amenity Lenova PU-01-W; rooftop+amenity sinks
Tubs (Type B) | 150 | Maxx Rubix 6030 + Delta T17459 chrome trim
Tubs (Type A ADA) | 7 | Maxx Rubix 6030 + Delta T17459-LHD + 57011 handheld
Kitchen sinks | 140 | 135 unit sinks + 4 amenity Elkay + 1 work room
Kitchen faucets | 135 | Delta 9113-AR-DST stainless steel
Air gaps | 135 | Delta 72020-SS
Garbage disposals | 135 | ISE Badger 5
Drinking fountain | 1 | Oasis MWSMG8SBF bottle filler outside gym
Mop sink | 1 | Mustee 63M wall-mount
Coffee bar | 1 | lobby
Hose bibs | 17 | 4 Woodford 24 garage + 7 ext + 2 trash + 4 yard hydrants
Water heaters | 5 | HTP Phoenix PH199-119 gallon condensing boilers
Foundation drain | 1 | 4" sched 40 PVC per civil
Garage drains | 15 | ProSet/Watts FD33
Roof drains | 30 | L4 + upper roof + L2 + L6
Condensate stacks | 303 | 167 residential + 136 garage HVAC
VERIFIED MAIN FIXTURE COUNT | 635
Per unit (135): 4.70
AUDIT NOTE (2026-04-25): First-pass count of 1579 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 635 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 2300309 | 2332680 | 32371
Executed change orders (net) | 0 | 32371 | 32371
Total contract value | 2300309 | 2365051 | 64742
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 10800 | 10900 | 1448.5 | 9451.5 | 0 | 13.29%
101 | Takeoff & Purchase Labor | 19575 | 19675 | 16497 | 3178 | 0 | 83.85%
110 | Underground Labor | 13206 | 15488 | 16111.5 | -623.5 | 0 | 104%
111 | Garage Labor | 67077 | 67077 | 63370.5 | 3706.5 | 0 | 94.47%
112 | Canout Labor | 39340 | 39790 | 21073.5 | 18716.5 | 0 | 52.96%
120 | Roughin Labor | 243255 | 247365 | 301988 | -54623 | 0 | 122.1%
130 | Finish Labor | 46860 | 47430 | 58885.5 | -11455.5 | 0 | 124.2%
140 | Gas Labor | 8100 | 8550 | 13994 | -5444 | 0 | 163.7%
141 | Water Main/Insulation Lab | 50660 | 51080 | 46415.5 | 4664.5 | 0 | 90.87%
142 | Mech Room Labor | 18150 | 18150 | 17521.5 | 628.5 | 0 | 96.54%
143 | Condensation Drains Labor | 0 | 0 | 106 | -106 | 0 | 0%
210 | Underground Material | 10664 | 13531 | 8316.84 | 5214.16 | 0 | 61.47%
211 | Garage Material | 97667 | 97667 | 22525.24 | 75141.76 | 0 | 23.06%
212 | Canout Material | 22085 | 22585 | 12046.87 | 10538.13 | 0 | 53.34%
220 | Roughin Material | 163620 | 166602 | 74601.11 | 92000.89 | 0 | 44.78%
230 | Finish Material | 371637 | 366745 | 287966.65 | 78778.35 | 0 | 78.52%
240 | Gas Material | 18450 | 18838 | 6882.96 | 11955.04 | 0 | 36.54%
241 | Water Main/Insulation Mat | 57400 | 57623 | 45462.73 | 12160.27 | 0 | 78.9%
242 | Mech Room Material | 44000 | 44000 | 20788.7 | 23211.3 | 0 | 47.25%
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 | 0 | 0%
600 | Subcontractor | 1000 | 4360 | 9771.2 | -5411.2 | 0 | 224.1%
601 | Engineering/Plans | 70000 | 70000 | 40070.75 | 29929.25 | 0 | 57.24%
602 | Rental Equipment | 9000 | 9000 | 10709.84 | -1709.84 | 0 | 119%
603 | Permits & Licenses | 26800 | 26800 | 21423 | 5377 | 0 | 79.94%
607 | Other Expenses | 11000 | 11000 | 13008.75 | -2008.75 | 0 | 118.3%
995 | Payroll Burden | 206809.13 | 210032.29 | 224915.87 | -14883.58 | 0 | 107.1%
998 | Payroll Taxes | 39552.25 | 40201.13 | 42642.55 | -2441.42 | 0 | 106.1%
TOTAL |  | 1666707.38 | 1684489.42 | 1398544.56 | 285944.86 | 0 | 83.02%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 525505 | 557411.5 | -31906.5 | 106.1%
Material | 9 | 787591 | 478591.1 | 308999.9 | 60.77%
Overhead | 5 | 121160 | 94983.54 | 26176.46 | 78.4%
Burden | 2 | 250233.42 | 267558.42 | -17325 | 106.9%
TOTAL | 27 | 1684489.42 | 1398544.56 | 285944.86 | 83.02%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 10900 | 1448.5 | 9451.5 | -86.71% | UNDER
101 | Takeoff & Purchase Labor | 19675 | 16497 | 3178 | -16.15% | UNDER
110 | Underground Labor | 15488 | 16111.5 | -623.5 | 4.026% | ON
111 | Garage Labor | 67077 | 63370.5 | 3706.5 | -5.526% | ON
112 | Canout Labor | 39790 | 21073.5 | 18716.5 | -47.04% | UNDER
120 | Roughin Labor | 247365 | 301988 | -54623 | 22.08% | OVER
130 | Finish Labor | 47430 | 58885.5 | -11455.5 | 24.15% | OVER
140 | Gas Labor | 8550 | 13994 | -5444 | 63.67% | CRITICAL
141 | Water Main/Insulation Lab | 51080 | 46415.5 | 4664.5 | -9.132% | ON
142 | Mech Room Labor | 18150 | 17521.5 | 628.5 | -3.463% | ON
143 | Condensation Drains Labor | 0 | 106 | -106 | 0% | UNBUDGETED
210 | Underground Material | 13531 | 8316.84 | 5214.16 | -38.53% | UNDER
211 | Garage Material | 97667 | 22525.24 | 75141.76 | -76.94% | UNDER
212 | Canout Material | 22585 | 12046.87 | 10538.13 | -46.66% | UNDER
220 | Roughin Material | 166602 | 74601.11 | 92000.89 | -55.22% | UNDER
230 | Finish Material | 366745 | 287966.65 | 78778.35 | -21.48% | UNDER
240 | Gas Material | 18838 | 6882.96 | 11955.04 | -63.46% | UNDER
241 | Water Main/Insulation Mat | 57623 | 45462.73 | 12160.27 | -21.1% | UNDER
242 | Mech Room Material | 44000 | 20788.7 | 23211.3 | -52.75% | UNDER
600 | Subcontractor | 4360 | 9771.2 | -5411.2 | 124.1% | CRITICAL
601 | Engineering/Plans | 70000 | 40070.75 | 29929.25 | -42.76% | UNDER
602 | Rental Equipment | 9000 | 10709.84 | -1709.84 | 19% | OVER
603 | Permits & Licenses | 26800 | 21423 | 5377 | -20.06% | UNDER
607 | Other Expenses | 11000 | 13008.75 | -2008.75 | 18.26% | OVER
995 | Payroll Burden | 210032.29 | 224915.87 | -14883.58 | 7.086% | ON
998 | Payroll Taxes | 40201.13 | 42642.55 | -2441.42 | 6.073% | ON

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 154840.21 | 111 | 31.69%
Keller Supply Company | 108692.89 | 27 | 22.25%
Consolidated Supply Co. | 70168.11 | 34 | 14.36%
Franklin Engineering | 40070.75 | 7 | 8.202%
Capital One Credit Card | 35790.67 | 36 | 7.326%
Mechanical Sales, Inc. | 24178.58 | 3 | 4.949%
Ferguson Enterprises, Inc. #3007 | 20634.39 | 19 | 4.224%
Ahern Rentals | 10155.75 | 23 | 2.079%
Mechanical Resource Services, Inc. | 5350 | 2 | 1.095%
Old Castle Infrastructure, Inc. | 4866 | 2 | 0.996%
MAD Concrete Cutting & Coring, Inc. | 4421.2 | 4 | 0.905%
Quality Concrete Products, Inc. $32 | 4073 | 1 | 0.8337%
California Hydronics Corp | 3505 | 4 | 0.7174%
Sunbelt Rentals, Inc. | 554.09 | 2 | 0.1134%
Ferguson Enterprises, Inc.$Bell Parkside | 551.04 | 1 | 0.1128%
Manor Hardware & Construction Supply | 392.76 | 2 | 0.08039%
Core & Main LP $HD Supply Waterworks | 226.18 | 1 | 0.0463%
Kele, Inc $ MI Controls | 73.26 | 1 | 0.015%
TOTAL AP | 488543.88 | 280

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Cortes Sepulveda, Jose R | 2528 | 74332 | 29.4035 | JOURNEYMAN
Balderas Ortiz, Ricardo I | 2287 | 74008 | 32.3603 | JOURNEYMAN
Cortes Mendiola, Victor H | 2054 | 92916 | 45.2366 | LEAD/SUPERVISOR
Lucas Tzintzun, Rafael | 1231 | 25719 | 20.8928 | JOURNEYMAN
Chevez, Herson G | 1201 | 27049 | 22.5221 | JOURNEYMAN
Benites Portillo, Marvin E | 1193 | 31435 | 26.3495 | JOURNEYMAN
Lovo, German G | 1026 | 27186 | 26.4971 | JOURNEYMAN
Sorto Regalado, Milton J | 885 | 14392 | 16.2621 | APPRENTICE/HELPER
Rivera, Eli P | 857 | 25965 | 30.2975 | JOURNEYMAN
Portillo Soriano, Walter A | 828 | 18348 | 22.1594 | JOURNEYMAN
Belcher, Jacob T | 765 | 15080 | 19.7124 | APPRENTICE/HELPER
Eliassen, Cory H | 733.5 | 21936 | 29.9059 | JOURNEYMAN
Hoeg, Xavier A | 694.5 | 11832 | 17.0367 | APPRENTICE/HELPER
Galdamez, Dagoberto A | 664 | 19920 | 30 | JOURNEYMAN
Gauthier, Dillon R | 461 | 8290 | 17.9826 | APPRENTICE/HELPER
Trower-Kelly, Fidel D | 433 | 9036 | 20.8684 | JOURNEYMAN
Hubbard, Robert W | 343 | 17170 | 50.0583 | LEAD/SUPERVISOR
Sepulveda Gonzalez, Alfredo | 271 | 9433 | 34.8081 | JOURNEYMAN
Saules Bezanilla, Fernando | 223 | 2936 | 13.1659 | APPRENTICE/HELPER
Donelson, Richard T | 175 | 10938 | 62.5029 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 133 | 7008 | 52.6917 | LEAD/SUPERVISOR
Sanders, Allen O | 96 | 5106 | 53.1875 | LEAD/SUPERVISOR
Vazquez Popoca, Jose N | 85 | 1637 | 19.2588 | APPRENTICE/HELPER
Romero Garza, Jesus I | 48 | 1104 | 23 | JOURNEYMAN
Stahlschmidt, John P | 32 | 608 | 19 | APPRENTICE/HELPER
McCabe, Thomas C | 24 | 768 | 32 | JOURNEYMAN
Amaya Gonzalez, Edilberto A | 17 | 612 | 36 | LEAD/SUPERVISOR
Gutierrez Salas, Jose | 16 | 288 | 18 | APPRENTICE/HELPER
Rodriguez Arevalos, Christian | 16 | 368 | 23 | JOURNEYMAN
Martinez Reyes, Juan C | 10 | 316 | 31.6 | JOURNEYMAN
Barbosa, Michael S | 8 | 200 | 25 | JOURNEYMAN
Crespin Portillo, Juan D | 7 | 128 | 18.2857 | APPRENTICE/HELPER
Serrano, Jeremiah G | 7 | 128 | 18.2857 | APPRENTICE/HELPER
Hubbard, Dustin R | 6 | 150 | 25 | JOURNEYMAN
Hubbard, Justin A | 6 | 156 | 26 | JOURNEYMAN
Eisenhauer, Tommy J | 6 | 252 | 42 | OT-ONLY
Draves, Steven W | 6 | 243 | 40.5 | OT-ONLY
Gerard, Jordan E | 5 | 270 | 54 | OT-ONLY
Roberts, Lake A | 5 | 150 | 30 | OT-ONLY

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 6 | 2818 | 133750 | 14.54%
JOURNEYMAN | 19 | 13370.5 | 367428 | 68.97%
APPRENTICE/HELPER | 10 | 3175.5 | 55318 | 16.38%
OT-ONLY | 4 | 22 | 915 | 0.1135%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 19386
Active workers | 39
Hours per unit (to date) | 143.6
Revenue per labor hour (billed) | 120.33
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 27.79% | 34% | -6.213%
Roughin labor share (code 120) | 47.07% | 45% | 2.072%
Top vendor concentration | 31.69% | 38% | -6.306%
Hours per unit | 143.6 | 95 | 48.6

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Roughin Labor (120) over revised | ⚠ WATCH | Actual $301,988 vs revised $247,365 (+22%) — monitor
Finish Labor (130) over revised | ⚠ WATCH | Actual $58,886 vs revised $47,430 (+24%) — monitor
Gas Labor (140) CRITICAL overrun | ⚠ WATCH | Actual $13,994 vs revised $8,550 (+64%) — needs immediate attention
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $9,771 vs revised $4,360 (+124%) — needs immediate attention
Rental Equipment (602) over revised | ⚠ WATCH | Actual $10,710 vs revised $9,000 (+19%) — monitor
Other Expenses (607) over revised | ⚠ WATCH | Actual $13,009 vs revised $11,000 (+18%) — monitor
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 32% of AP ($154,840) — acceptable
Retention aging | ✓ OK | $113,684 held · 4.9% of billed · standard range
Forecast margin | ✓ OK | 27.8% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 1398544.56 | 1398544.56 | 0
Revenue billed (AR ·-1) | -2332680 | 2332680 | -4665360
AP source total |  | 488543.88 | —
PR source total |  | 824969.92 | —
GL source total |  | 85030.76 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2053 live project. 17-tab JCR schema on revised budget basis.