## Summary
#2053 · Bellevue Parkside
Compass Harbor Constructi · 135 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
2332680 | 27.79% | 2332680 | 0
Key facts
Original contract |  | 2300309
Revised contract (CO impact) |  | 2332680
Executed COs (net) |  | 32371
Retention held |  | 113684
Revised expense budget |  | 1684489.42
Forecast net profit |  | 648190.58
Percent complete |  | 100%
Live signals
Roughin Labor (120) over | ⚠ WATCH | Actual $301,988 vs revised $247,365 (+22%) — monitor
Finish Labor (130) over | ⚠ WATCH | Actual $58,886 vs revised $47,430 (+24%) — monitor
Gas Labor (140) CRITICAL | ⚠ WATCH | Actual $13,994 vs revised $8,550 (+64%) — needs attention
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $9,771 vs revised $4,360 (+124%) — needs attention
Rental Equipment (602) over | ⚠ WATCH | Actual $10,710 vs revised $9,000 (+19%) — monitor
Other Expenses (607) over | ⚠ WATCH | Actual $13,009 vs revised $11,000 (+18%) — monitor
Top vendor (Rosen Supply Kirklan) | ✓ OK | 32% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 27.8% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Rosen Supply Kirkland | 111 | 154840.21 | 31.69%
Keller Supply Company | 27 | 108692.89 | 22.25%
Consolidated Supply Co. | 34 | 70168.11 | 14.36%
Franklin Engineering | 7 | 40070.75 | 8.202%
Capital One Credit Card | 36 | 35790.67 | 7.326%
Mechanical Sales, Inc. | 3 | 24178.58 | 4.949%

## Transactions
Transactions Detail
JDR source transactions for job #2053 · 3824 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 06/08/18 | 340 | Gerard, Jeffrey S | 2 | 100 | 20080
PR | 100 | 07/27/18 | 835 | Gerard, Jeffrey S | 1 | 50 | 20593
PR | 100 | 08/31/18 | 1070 | Gerard, Jeffrey S | 1 | 50 | 90962
PR | 100 | 11/30/18 | 901 | Gerard, Jeffrey S | 1 | 52 | 921984
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 2 | 104 | 22057
PR | 100 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 100 | 01/11/19 | 281 | Donelson, Richard T | 1 | 62.5 | 922483
PR | 100 | 02/15/19 | 389 | Gerard, Jeffrey S | 1 | 52 | 922840
PR | 100 | 03/29/19 | 990 | Gerard, Jeffrey S | 3 | 156 | 23273
PR | 100 | 04/26/19 | 813 | Gerard, Jeffrey S | 1 | 55 | 23569
PR | 100 | 05/10/19 | 235 | Gerard, Jeffrey S | 1 | 55 | 23720
PR | 100 | 05/17/19 | 468 | Gerard, Jeffrey S | 1.5 | 82.5 | 923799
PR | 100 | 05/24/19 | 681 | Gerard, Jeffrey S | 1.5 | 82.5 | 923876
PR | 100 | 06/07/19 | 255 | Gerard, Jeffrey S | 1 | 55 | 924030
PR | 100 | 06/14/19 | 524 | Gerard, Jeffrey S | 1 | 55 | 24104
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 2 | 110 | 24255
PR | 100 | 07/05/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 924330
PR | 100 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 100 | 09/20/19 | 547 | Gerard, Jeffrey S | 1 | 55 | 925233
PR | 100 | 10/11/19 | 335 | Gerard, Jeffrey S | 1 | 55 | 925469
PR | 101 | 03/09/18 | 184 | Gerard, Jeffrey S | 1 | 47 | 99998
PR | 101 | 03/30/18 | 811 | Donelson, Richard T | 2 | 125 | 99350
PR | 101 | 05/25/18 | 806 | Donelson, Richard T | 8 | 500 | 99935
PR | 101 | 06/01/18 | 75 | Donelson, Richard T | 5 | 312.5 | 920007
PR | 101 | 06/08/18 | 339 | Donelson, Richard T | 12 | 750 | 20079
PR | 101 | 06/08/18 | 340 | Gerard, Jeffrey S | 1 | 50 | 20080
PR | 101 | 06/15/18 | 527 | Donelson, Richard T | 6 | 375 | 20162
PR | 101 | 06/15/18 | 528 | Gerard, Jeffrey S | 2 | 100 | 20163
PR | 101 | 06/22/18 | 753 | Donelson, Richard T | 3 | 187.5 | 290232
PR | 101 | 06/22/18 | 754 | Gerard, Jeffrey S | 1 | 50 | 290233
PR | 101 | 06/29/18 | 1019 | Donelson, Richard T | 5 | 312.5 | 20300
PR | 101 | 06/29/18 | 1020 | Gerard, Jeffrey S | 1 | 50 | 20301
PR | 101 | 07/06/18 | 76 | Donelson, Richard T | 1 | 62.5 | 920374
PR | 101 | 07/13/18 | 367 | Donelson, Richard T | 3 | 187.5 | 20400
PR | 101 | 07/13/18 | 368 | Gerard, Jeffrey S | 1 | 50 | 20401
PR | 101 | 07/20/18 | 507 | Donelson, Richard T | 1 | 62.5 | 920518
PR | 101 | 07/20/18 | 508 | Gerard, Jeffrey S | 3 | 150 | 920519
PR | 101 | 07/27/18 | 834 | Donelson, Richard T | 1 | 62.5 | 20592
PR | 101 | 07/27/18 | 835 | Gerard, Jeffrey S | 2 | 100 | 20593
PR | 101 | 08/03/18 | 72 | Donelson, Richard T | 6 | 375 | 20664
PR | 101 | 08/03/18 | 73 | Gerard, Jeffrey S | 1 | 50 | 20665
PR | 101 | 08/10/18 | 283 | Donelson, Richard T | 11 | 687.5 | 920736
PR | 101 | 08/17/18 | 551 | Gerard, Jeffrey S | 1 | 50 | 20809
PR | 101 | 08/24/18 | 811 | Donelson, Richard T | 5 | 312.5 | 20879
PR | 101 | 08/31/18 | 1069 | Donelson, Richard T | 4 | 250 | 90961
PR | 101 | 09/07/18 | 105 | Donelson, Richard T | 3 | 187.5 | 91031
PR | 101 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 101 | 09/14/18 | 340 | Donelson, Richard T | 1 | 62.5 | 21173
PR | 101 | 09/14/18 | 341 | Gerard, Jeffrey S | 1 | 50 | 21174
PR | 101 | 09/21/18 | 552 | Donelson, Richard T | 1 | 62.5 | 21244
PR | 101 | 09/21/18 | 553 | Gerard, Jeffrey S | 3 | 150 | 21245
PR | 101 | 09/28/18 | 739 | Donelson, Richard T | 3 | 187.5 | 90883
PR | 101 | 09/28/18 | 740 | Gerard, Jeffrey S | 2 | 100 | 90884
PR | 101 | 10/05/18 | 102 | Donelson, Richard T | 3 | 187.5 | 91391
PR | 101 | 10/12/18 | 310 | Gerard, Jeffrey S | 2 | 100 | 21467
PR | 101 | 10/19/18 | 507 | Donelson, Richard T | 5 | 312.5 | 91541
PR | 101 | 10/26/18 | 774 | Donelson, Richard T | 2 | 125 | 21615
PR | 101 | 10/26/18 | 774 | Donelson, Richard T | 5 | 312.5 | 21615
PR | 101 | 11/02/18 | 76 | Donelson, Richard T | 2 | 125 | 21686
PR | 101 | 11/02/18 | 77 | Gerard, Jeffrey S | 2 | 100 | 21687
PR | 101 | 11/16/18 | 513 | Donelson, Richard T | 1 | 62.5 | 21836
PR | 101 | 11/16/18 | 514 | Gerard, Jeffrey S | 1 | 50 | 21837
PR | 101 | 11/21/18 | 690 | Gerard, Jeffrey S | 2 | 100 | 21912
PR | 101 | 11/30/18 | 900 | Donelson, Richard T | 2 | 125 | 921983
PR | 101 | 11/30/18 | 901 | Gerard, Jeffrey S | 2 | 104 | 921984
PR | 101 | 12/07/18 | 113 | Donelson, Richard T | 1 | 62.5 | 22056
PR | 101 | 12/07/18 | 114 | Gerard, Jeffrey S | 4 | 208 | 22057
PR | 101 | 12/14/18 | 337 | Donelson, Richard T | 3 | 187.5 | 22197
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/21/18 | 577 | Donelson, Richard T | 1 | 62.5 | 922268
PR | 101 | 12/21/18 | 578 | Gerard, Jeffrey S | 1 | 52 | 922269
PR | 101 | 12/28/18 | 768 | Donelson, Richard T | 1 | 62.5 | 22342
PR | 101 | 01/04/19 | 73 | Gerard, Jeffrey S | 1 | 52 | 22301
PR | 101 | 01/11/19 | 282 | Gerard, Jeffrey S | 1 | 52 | 922484
PR | 101 | 01/18/19 | 542 | Donelson, Richard T | 1 | 62.5 | 922557
PR | 101 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 101 | 01/25/19 | 786 | Donelson, Richard T | 5 | 312.5 | 922631
PR | 101 | 02/01/19 | 70 | Donelson, Richard T | 3 | 187.5 | 22699
PR | 101 | 02/01/19 | 71 | Gerard, Jeffrey S | 3 | 156 | 22700
PR | 101 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 101 | 02/15/19 | 389 | Gerard, Jeffrey S | 2 | 104 | 922840
PR | 101 | 02/22/19 | 647 | Donelson, Richard T | 1 | 62.5 | 922909
PR | 101 | 02/22/19 | 648 | Gerard, Jeffrey S | 2 | 104 | 922910
PR | 101 | 03/01/19 | 74 | Donelson, Richard T | 3 | 187.5 | 22981
PR | 101 | 03/01/19 | 75 | Gerard, Jeffrey S | 4 | 208 | 22982
PR | 101 | 03/08/19 | 314 | Donelson, Richard T | 1 | 62.5 | 923053
PR | 101 | 03/08/19 | 315 | Gerard, Jeffrey S | 4 | 208 | 923054
PR | 101 | 03/15/19 | 562 | Donelson, Richard T | 1 | 62.5 | 23124
PR | 101 | 03/15/19 | 563 | Gerard, Jeffrey S | 3 | 156 | 23125
PR | 101 | 03/22/19 | 776 | Donelson, Richard T | 3 | 187.5 | 923197
PR | 101 | 03/22/19 | 777 | Gerard, Jeffrey S | 3 | 156 | 923198
PR | 101 | 03/29/19 | 989 | Donelson, Richard T | 3 | 187.5 | 23272
PR | 101 | 04/05/19 | 151 | Donelson, Richard T | 1 | 62.5 | 923345
PR | 101 | 04/05/19 | 152 | Gerard, Jeffrey S | 4 | 208 | 923346
PR | 101 | 04/12/19 | 398 | Gerard, Jeffrey S | 1 | 52 | 23421
PR | 101 | 04/19/19 | 596 | Donelson, Richard T | 2 | 125 | 923496
PR | 101 | 04/19/19 | 597 | Gerard, Jeffrey S | 1 | 52 | 923497
PR | 101 | 04/26/19 | 812 | Donelson, Richard T | 2 | 125 | 23568
PR | 101 | 04/26/19 | 813 | Gerard, Jeffrey S | 2 | 110 | 23569
PR | 101 | 05/03/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 923644
PR | 101 | 05/10/19 | 234 | Donelson, Richard T | 2 | 125 | 23719
PR | 101 | 05/10/19 | 235 | Gerard, Jeffrey S | 1 | 55 | 23720
PR | 101 | 05/17/19 | 467 | Donelson, Richard T | 1 | 62.5 | 923798
PR | 101 | 05/17/19 | 468 | Gerard, Jeffrey S | 4 | 220 | 923799
PR | 101 | 05/24/19 | 680 | Donelson, Richard T | 1 | 62.5 | 923875
PR | 101 | 05/24/19 | 681 | Gerard, Jeffrey S | 4 | 220 | 923876
PR | 101 | 05/31/19 | 952 | Donelson, Richard T | 1 | 62.5 | 923952
PR | 101 | 05/31/19 | 953 | Gerard, Jeffrey S | 3 | 165 | 923953
PR | 101 | 06/07/19 | 254 | Donelson, Richard T | 5 | 312.5 | 924029
PR | 101 | 06/07/19 | 255 | Gerard, Jeffrey S | 3 | 165 | 924030
PR | 101 | 06/14/19 | 523 | Donelson, Richard T | 1 | 62.5 | 24103
PR | 101 | 06/14/19 | 524 | Gerard, Jeffrey S | 4 | 220 | 24104
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 1 | 62.5 | 24179
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 2 | 110 | 24180
PR | 101 | 06/28/19 | 910 | Donelson, Richard T | 1 | 62.5 | 24254
PR | 101 | 06/28/19 | 911 | Gerard, Jeffrey S | 1 | 55 | 24255
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 1 | 62.5 | 924329
PR | 101 | 07/05/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 924330
PR | 101 | 07/12/19 | 353 | Gerard, Jeffrey S | 2 | 110 | 924405
PR | 101 | 07/19/19 | 585 | Donelson, Richard T | 1 | 62.5 | 24484
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 101 | 07/26/19 | 686 | Gerard, Jeffrey S | 3 | 165 | 24635
PR | 101 | 08/16/19 | 636 | Donelson, Richard T | 3 | 187.5 | 924855
PR | 101 | 08/16/19 | 637 | Gerard, Jeffrey S | 2 | 110 | 924856
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 1 | 62.5 | 25008
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 2 | 125 | 25008
PR | 101 | 09/20/19 | 547 | Gerard, Jeffrey S | 2 | 110 | 925233
PR | 101 | 10/11/19 | 335 | Gerard, Jeffrey S | 1 | 55 | 925469
PR | 101 | 11/15/19 | 512 | Donelson, Richard T | 1 | 62.5 | 925848
PR | 101 | 11/22/19 | 684 | Donelson, Richard T | 1 | 62.5 | 925923
PR | 101 | 12/13/19 | 465 | Donelson, Richard T | 1 | 62.5 | 926231
PR | 101 | 01/17/20 | 618 | Donelson, Richard T | 1 | 62.5 | 926617
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 1 | 62.5 | 926400
PR | 101 | 02/07/20 | 102 | Donelson, Richard T | 2 | 125 | 26850
PR | 101 | 02/21/20 | 528 | Donelson, Richard T | 1 | 62.5 | 27006
PR | 101 | 02/28/20 | 757 | Donelson, Richard T | 2 | 125 | 927085
PR | 101 | 03/06/20 | 119 | Donelson, Richard T | 1 | 62.5 | 927163
PR | 101 | 03/13/20 | 383 | Donelson, Richard T | 4 | 250 | 927244
PR | 101 | 04/17/20 | 288 | Donelson, Richard T | 1 | 62.5 | 927551
PR | 101 | 04/24/20 | 424 | Donelson, Richard T | 3 | 187.5 | 927628
PR | 101 | 05/01/20 | 78 | Donelson, Richard T | 1 | 62.5 | 927705
PR | 110 | 02/02/18 | 38 | Hubbard, Robert W | 1 | 45 | 18768
PR | 110 | 02/09/18 | 195 | Hubbard, Robert W | 2 | 90 | 18836
PR | 110 | 05/18/18 | 452 | Hubbard, Robert W | 1 | 45 | 19825
PR | 110 | 06/29/18 | 950 | Cortes Sepulveda, Jose R | 12 | 288 | 19949
PR | 110 | 06/29/18 | 963 | Cortes Mendiola, Victor H | 12 | 492 | 20244
PR | 110 | 06/29/18 | 983 | Hubbard, Robert W | 8.5 | 399.5 | 20263
PR | 110 | 07/13/18 | 307 | Cortes Mendiola, Victor H | 16 | 656 | 20387
PR | 110 | 07/13/18 | 308 | Cortes Sepulveda, Jose R | 16 | 384 | 20388
PR | 110 | 07/13/18 | 329 | Hubbard, Robert W | 4 | 188 | 20409
PR | 110 | 07/20/18 | 447 | Cortes Mendiola, Victor H | 8 | 328 | 20458
PR | 110 | 07/20/18 | 448 | Cortes Sepulveda, Jose R | 8 | 192 | 20459
PR | 110 | 07/20/18 | 470 | Hubbard, Robert W | 5 | 235 | 20480
PR | 110 | 07/27/18 | 773 | Cortes Mendiola, Victor H | 24 | 984 | 20531
PR | 110 | 07/27/18 | 774 | Cortes Sepulveda, Jose R | 24 | 576 | 20532
PR | 110 | 07/27/18 | 797 | Hubbard, Robert W | 25 | 1175 | 20554
PR | 110 | 07/27/18 | 808 | McCabe, Thomas C | 16 | 512 | 20565
PR | 110 | 07/27/18 | 825 | Sepulveda Gonzalez, Alfredo | 16 | 496 | 20582
PR | 110 | 08/03/18 | 12 | Cortes Mendiola, Victor H | 24 | 984 | 20604
PR | 110 | 08/03/18 | 13 | Cortes Sepulveda, Jose R | 24 | 576 | 20605
PR | 110 | 08/03/18 | 35 | Hubbard, Robert W | 14 | 658 | 20626
PR | 110 | 08/03/18 | 46 | McCabe, Thomas C | 8 | 256 | 20637
PR | 110 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo | 8 | 248 | 20654
PR | 110 | 08/10/18 | 222 | Cortes Mendiola, Victor H | 16 | 656 | 20675
PR | 110 | 08/10/18 | 223 | Cortes Sepulveda, Jose R | 22 | 528 | 20676
PR | 110 | 08/10/18 | 246 | Hubbard, Robert W | 5 | 235 | 20698
PR | 110 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo | 13 | 403 | 20726
PR | 110 | 08/31/18 | 1038 | Martinez Reyes, Juan C | 2 | 52 | 20933
PR | 110 | 09/21/18 | 515 | Hubbard, Robert W | 2 | 94 | 21206
PR | 110 | 10/05/18 | 40 | Cortes Mendiola, Victor H | 8 | 328 | 21329
PR | 110 | 10/05/18 | 41 | Cortes Sepulveda, Jose R | 8 | 192 | 21330
PR | 110 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I | 8 | 224 | 21394
PR | 110 | 10/12/18 | 245 | Cortes Mendiola, Victor H | 14 | 574 | 21403
PR | 110 | 10/12/18 | 246 | Cortes Sepulveda, Jose R | 14 | 336 | 21404
PR | 110 | 10/12/18 | 265 | Gutierrez Salas, Jose | 8 | 144 | 21422
PR | 110 | 10/12/18 | 270 | Hubbard, Robert W | 2 | 94 | 21427
PR | 110 | 10/19/18 | 444 | Cortes Mendiola, Victor H | 4 | 164 | 21478
PR | 110 | 10/19/18 | 445 | Cortes Sepulveda, Jose R | 4 | 96 | 21479
PR | 110 | 10/26/18 | 712 | Cortes Mendiola, Victor H | 16 | 656 | 21552
PR | 110 | 10/26/18 | 713 | Cortes Sepulveda, Jose R | 16 | 384 | 21553
PR | 110 | 11/02/18 | 14 | Cortes Mendiola, Victor H | 8 | 328 | 21624
PR | 110 | 11/02/18 | 15 | Cortes Sepulveda, Jose R | 8 | 192 | 21625
PR | 110 | 02/21/20 | 515 | Sepulveda Gonzalez, Alfredo | 8 | 312 | 26992
PR | 110 | 02/28/20 | 744 | Sepulveda Gonzalez, Alfredo | 8 | 312 | 27072
PR | 111 | 09/28/18 | 700 | Hubbard, Robert W | 1 | 47 | 21278
PR | 111 | 10/26/18 | 713 | Cortes Sepulveda, Jose R | 7 | 168 | 21553
PR | 111 | 11/16/18 | 433 | Balderas Ortiz, Ricardo I | 16 | 448 | 21762
PR | 111 | 11/16/18 | 441 | Cortes Mendiola, Victor H | 16 | 656 | 21770
PR | 111 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I | 16 | 448 | 21841
PR | 111 | 11/21/18 | 627 | Cortes Mendiola, Victor H | 10 | 410 | 21849
PR | 111 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I | 24 | 696 | 21914
PR | 111 | 11/30/18 | 839 | Cortes Mendiola, Victor H | 8 | 344 | 21922
PR | 111 | 11/30/18 | 840 | Cortes Sepulveda, Jose R | 11 | 286 | 21923
PR | 111 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I | 16 | 464 | 21988
PR | 111 | 12/07/18 | 52 | Cortes Mendiola, Victor H | 16 | 688 | 21995
PR | 111 | 12/07/18 | 53 | Cortes Sepulveda, Jose R | 16 | 416 | 21996
PR | 111 | 01/11/19 | 244 | Hubbard, Robert W | 2 | 98 | 22446
PR | 111 | 01/25/19 | 716 | Balderas Ortiz, Ricardo I | 40 | 1160 | 22561
PR | 111 | 01/25/19 | 725 | Cortes Mendiola, Victor H | 36 | 1548 | 22570
PR | 111 | 01/25/19 | 726 | Cortes Sepulveda, Jose R | 40 | 1040 | 22571
PR | 111 | 01/25/19 | 748 | Hubbard, Robert W | 3 | 147 | 22593
PR | 111 | 02/01/19 | 5 | Balderas Ortiz, Ricardo I | 40 | 1160 | 22634
PR | 111 | 02/01/19 | 13 | Cortes Mendiola, Victor H | 35 | 1505 | 22642
PR | 111 | 02/01/19 | 14 | Cortes Sepulveda, Jose R | 40 | 1040 | 22643
PR | 111 | 02/01/19 | 36 | Hubbard, Robert W | 1 | 49 | 22665
PR | 111 | 02/08/19 | 160 | Balderas Ortiz, Ricardo I | 24 | 696 | 22702
PR | 111 | 02/08/19 | 168 | Cortes Mendiola, Victor H | 21 | 903 | 22710
PR | 111 | 02/08/19 | 169 | Cortes Sepulveda, Jose R | 13 | 338 | 22711
PR | 111 | 02/15/19 | 322 | Balderas Ortiz, Ricardo I | 24 | 696 | 22771
PR | 111 | 02/15/19 | 328 | Chevez, Herson G | 10 | 200 | 22777
PR | 111 | 02/15/19 | 330 | Cortes Mendiola, Victor H | 19 | 817 | 22779
PR | 111 | 02/15/19 | 331 | Cortes Sepulveda, Jose R | 24 | 624 | 22780
PR | 111 | 02/22/19 | 580 | Balderas Ortiz, Ricardo I | 40 | 1160 | 22842
PR | 111 | 02/22/19 | 586 | Chevez, Herson G | 44 | 880 | 22848
PR | 111 | 02/22/19 | 588 | Cortes Mendiola, Victor H | 34 | 1462 | 22850
PR | 111 | 02/22/19 | 589 | Cortes Sepulveda, Jose R | 44 | 1144 | 22851
PR | 111 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I | 33 | 957 | 22912
PR | 111 | 03/01/19 | 9 | Benites Portillo, Marvin E | 16 | 384 | 22916
PR | 111 | 03/01/19 | 11 | Chevez, Herson G | 16 | 320 | 22918
PR | 111 | 03/01/19 | 13 | Cortes Mendiola, Victor H | 5 | 215 | 22920
PR | 111 | 03/01/19 | 14 | Cortes Sepulveda, Jose R | 16 | 416 | 22921
PR | 111 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I | 9 | 391.5 | 22985
PR | 111 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I | 40 | 1160 | 22985
PR | 111 | 03/08/19 | 255 | Cortes Mendiola, Victor H | 4 | 172 | 22993
PR | 111 | 03/08/19 | 256 | Cortes Sepulveda, Jose R | 6 | 234 | 22994
PR | 111 | 03/08/19 | 256 | Cortes Sepulveda, Jose R | 43 | 1118 | 22994
PR | 111 | 03/08/19 | 278 | Hubbard, Robert W | 2 | 98 | 23017
PR | 111 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I | 16 | 464 | 23056
PR | 111 | 03/15/19 | 502 | Cortes Mendiola, Victor H | 4 | 172 | 23064
PR | 111 | 04/05/19 | 114 | Hubbard, Robert W | 2 | 98 | 23308
PR | 111 | 05/03/19 | 42 | Hubbard, Robert W | 3 | 150 | 23604
PR | 111 | 05/24/19 | 639 | Hubbard, Robert W | 6 | 300 | 23834
PR | 111 | 05/31/19 | 888 | Cortes Mendiola, Victor H | 6 | 276 | 23888
PR | 111 | 05/31/19 | 913 | Hubbard, Robert W | 4 | 200 | 23913
PR | 111 | 06/07/19 | 185 | Benites Portillo, Marvin E | 40 | 1080 | 23960
PR | 111 | 06/07/19 | 190 | Cortes Mendiola, Victor H | 10 | 460 | 23965
PR | 111 | 06/07/19 | 203 | Galdamez, Dagoberto A | 40 | 1200 | 23978
PR | 111 | 06/07/19 | 215 | Hubbard, Robert W | 2 | 100 | 23990
PR | 111 | 06/07/19 | 223 | Martinez Reyes, Juan C | 8 | 264 | 23998
PR | 111 | 06/14/19 | 456 | Benites Portillo, Marvin E | 8 | 216 | 24037
PR | 111 | 06/14/19 | 471 | Galdamez, Dagoberto A | 8 | 240 | 24052
PR | 111 | 06/14/19 | 483 | Hubbard, Robert W | 3 | 150 | 24064
PR | 111 | 06/21/19 | 624 | Benites Portillo, Marvin E | 24 | 648 | 24110
PR | 111 | 06/21/19 | 642 | Galdamez, Dagoberto A | 24 | 720 | 24128
PR | 111 | 06/28/19 | 842 | Benites Portillo, Marvin E | 32 | 864 | 24186
PR | 111 | 06/28/19 | 848 | Cortes Mendiola, Victor H | 5 | 230 | 24192
PR | 111 | 07/26/19 | 646 | Hubbard, Robert W | 5 | 250 | 24595
PR | 111 | 08/02/19 | 10 | Benites Portillo, Marvin E | 37 | 999 | 24641
PR | 111 | 08/02/19 | 16 | Cortes Mendiola, Victor H | 12 | 552 | 24647
PR | 111 | 08/23/19 | 835 | Hubbard, Robert W | 2 | 100 | 24893
PR | 111 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I | 24 | 768 | 25086
PR | 111 | 09/13/19 | 241 | Benites Portillo, Marvin E | 16 | 432 | 25090
PR | 111 | 09/13/19 | 247 | Cortes Mendiola, Victor H | 20 | 920 | 25096
PR | 111 | 09/13/19 | 248 | Cortes Sepulveda, Jose R | 21 | 630 | 25097
PR | 111 | 09/13/19 | 271 | Hubbard, Robert W | 4 | 200 | 25120
PR | 111 | 09/13/19 | 287 | Rivera, Eli P | 16 | 480 | 25136
PR | 111 | 09/20/19 | 484 | Cortes Mendiola, Victor H | 2 | 92 | 25170
PR | 111 | 09/27/19 | 634 | Benites Portillo, Marvin E | 40 | 1080 | 25239
PR | 111 | 09/27/19 | 640 | Cortes Mendiola, Victor H | 17 | 782 | 25245
PR | 111 | 09/27/19 | 666 | Hubbard, Robert W | 3 | 150 | 25271
PR | 111 | 09/27/19 | 693 | Sorto Regalado, Milton J | 40 | 640 | 25298
PR | 111 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I | 16 | 512 | 25313
PR | 111 | 10/04/19 | 10 | Benites Portillo, Marvin E | 24 | 648 | 25317
PR | 111 | 10/04/19 | 16 | Cortes Mendiola, Victor H | 14 | 644 | 25323
PR | 111 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I | 20 | 640 | 25394
PR | 111 | 10/11/19 | 265 | Benites Portillo, Marvin E | 7 | 189 | 25398
PR | 111 | 10/11/19 | 271 | Cortes Mendiola, Victor H | 15 | 690 | 25405
PR | 111 | 10/11/19 | 272 | Cortes Sepulveda, Jose R | 8 | 240 | 25406
PR | 111 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I | 13 | 416 | 25471
PR | 111 | 10/18/19 | 465 | Cortes Mendiola, Victor H | 1 | 46 | 25481
PR | 111 | 10/18/19 | 466 | Cortes Sepulveda, Jose R | 8 | 240 | 25482
PR | 111 | 10/18/19 | 497 | Lucas Tzintzun, Rafael | 8 | 168 | 25514
PR | 111 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I | 24 | 768 | 25547
PR | 111 | 10/25/19 | 601 | Cortes Mendiola, Victor H | 20 | 920 | 25558
PR | 111 | 10/25/19 | 602 | Cortes Sepulveda, Jose R | 16 | 480 | 25559
PR | 111 | 10/25/19 | 624 | Hubbard, Robert W | 3 | 150 | 25581
PR | 111 | 10/25/19 | 632 | Lucas Tzintzun, Rafael | 27 | 567 | 25589
PR | 111 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I | 16 | 576 | 25623
PR | 111 | 11/01/19 | 16 | Cortes Mendiola, Victor H | 19 | 950 | 25633
PR | 111 | 11/01/19 | 17 | Cortes Sepulveda, Jose R | 16 | 544 | 25634
PR | 111 | 11/01/19 | 48 | Lucas Tzintzun, Rafael | 16 | 384 | 25665
PR | 111 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I | 24 | 864 | 25699
PR | 111 | 11/08/19 | 190 | Cortes Mendiola, Victor H | 3 | 150 | 25709
PR | 111 | 11/08/19 | 191 | Cortes Sepulveda, Jose R | 24 | 816 | 25710
PR | 111 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I | 16 | 576 | 25775
PR | 111 | 11/15/19 | 451 | Cortes Sepulveda, Jose R | 16 | 544 | 25786
PR | 111 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I | 23 | 828 | 25851
PR | 111 | 11/22/19 | 621 | Cortes Mendiola, Victor H | 9 | 450 | 25861
PR | 111 | 11/22/19 | 622 | Cortes Sepulveda, Jose R | 15 | 510 | 25862
PR | 111 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I | 8 | 288 | 25926
PR | 111 | 11/27/19 | 856 | Cortes Sepulveda, Jose R | 24 | 816 | 25937
PR | 111 | 12/06/19 | 65 | Hubbard, Robert W | 2 | 108 | 26037
PR | 111 | 12/13/19 | 426 | Hubbard, Robert W | 2 | 108 | 26191
PR | 111 | 12/20/19 | 579 | Hubbard, Robert W | 3 | 162 | 26268
PR | 111 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I | 6 | 216 | 26310
PR | 111 | 12/27/19 | 713 | Cortes Sepulveda, Jose R | 6 | 204 | 26321
PR | 111 | 12/27/19 | 737 | Hubbard, Robert W | 2 | 108 | 26345
PR | 111 | 01/03/20 | 40 | Hubbard, Robert W | 5 | 270 | 26423
PR | 111 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I | 14 | 504 | 26543
PR | 111 | 01/17/20 | 555 | Cortes Sepulveda, Jose R | 14 | 476 | 26554
PR | 111 | 01/17/20 | 579 | Hubbard, Robert W | 1 | 54 | 26578
PR | 111 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I | 24 | 864 | 26775
PR | 111 | 02/07/20 | 38 | Cortes Sepulveda, Jose R | 24 | 816 | 26786
PR | 111 | 02/21/20 | 486 | Hubbard, Robert W | 6 | 324 | 26963
PR | 111 | 03/06/20 | 78 | Hubbard, Robert W | 5 | 270 | 27122
PR | 111 | 03/13/20 | 342 | Hubbard, Robert W | 3 | 162 | 27203
PR | 112 | 08/17/18 | 490 | Cortes Mendiola, Victor H | 4 | 164 | 20748
PR | 112 | 08/17/18 | 491 | Cortes Sepulveda, Jose R | 4 | 96 | 20749
PR | 112 | 08/17/18 | 514 | Hubbard, Robert W | 2 | 94 | 20771
PR | 112 | 08/24/18 | 752 | Cortes Mendiola, Victor H | 8 | 328 | 20820
PR | 112 | 08/24/18 | 753 | Cortes Sepulveda, Jose R | 11 | 264 | 20821
PR | 112 | 08/31/18 | 1007 | Cortes Sepulveda, Jose R | 4 | 96 | 20903
PR | 112 | 09/07/18 | 47 | Cortes Mendiola, Victor H | 4 | 164 | 20972
PR | 112 | 09/14/18 | 278 | Cortes Mendiola, Victor H | 8 | 328 | 21113
PR | 112 | 09/14/18 | 279 | Cortes Sepulveda, Jose R | 8 | 192 | 21114
PR | 112 | 09/14/18 | 302 | Hubbard, Robert W | 1 | 47 | 21136
PR | 112 | 09/21/18 | 491 | Cortes Mendiola, Victor H | 2 | 82 | 21183
PR | 112 | 09/21/18 | 492 | Cortes Sepulveda, Jose R | 9 | 216 | 21184
PR | 112 | 09/28/18 | 676 | Cortes Mendiola, Victor H | 11 | 451 | 21255
PR | 112 | 09/28/18 | 677 | Cortes Sepulveda, Jose R | 11 | 264 | 21256
PR | 112 | 09/28/18 | 700 | Hubbard, Robert W | 3 | 141 | 21278
PR | 112 | 10/05/18 | 40 | Cortes Mendiola, Victor H | 4 | 164 | 21329
PR | 112 | 10/05/18 | 41 | Cortes Sepulveda, Jose R | 7 | 168 | 21330
PR | 112 | 10/05/18 | 64 | Hubbard, Robert W | 2 | 94 | 21352
PR | 112 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I | 8 | 224 | 21394
PR | 112 | 10/12/18 | 245 | Cortes Mendiola, Victor H | 18 | 738 | 21403
PR | 112 | 10/12/18 | 246 | Cortes Sepulveda, Jose R | 18 | 432 | 21404
PR | 112 | 10/12/18 | 265 | Gutierrez Salas, Jose | 8 | 144 | 21422
PR | 112 | 10/12/18 | 270 | Hubbard, Robert W | 2 | 94 | 21427
PR | 112 | 10/19/18 | 444 | Cortes Mendiola, Victor H | 16 | 656 | 21478
PR | 112 | 10/19/18 | 445 | Cortes Sepulveda, Jose R | 16 | 384 | 21479
PR | 112 | 10/19/18 | 468 | Hubbard, Robert W | 9.5 | 446.5 | 21501
PR | 112 | 10/25/18 | 687 | Hubbard, Robert W | 10 | 470 | 21477
PR | 112 | 10/26/18 | 712 | Cortes Mendiola, Victor H | 4 | 164 | 21552
PR | 112 | 11/02/18 | 14 | Cortes Mendiola, Victor H | 14 | 574 | 21624
PR | 112 | 11/02/18 | 15 | Cortes Sepulveda, Jose R | 14 | 336 | 21625
PR | 112 | 11/09/18 | 192 | Cortes Mendiola, Victor H | 16 | 656 | 21696
PR | 112 | 11/09/18 | 193 | Cortes Sepulveda, Jose R | 16 | 384 | 21697
PR | 112 | 11/09/18 | 217 | Hubbard, Robert W | 2 | 94 | 21720
PR | 112 | 11/16/18 | 441 | Cortes Mendiola, Victor H | 16 | 656 | 21770
PR | 112 | 11/16/18 | 442 | Cortes Sepulveda, Jose R | 16 | 384 | 21771
PR | 112 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I | 16 | 448 | 21841
PR | 112 | 11/21/18 | 627 | Cortes Mendiola, Victor H | 22 | 902 | 21849
PR | 112 | 11/21/18 | 650 | Hubbard, Robert W | 1 | 47 | 21871
PR | 112 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I | 8 | 232 | 21914
PR | 112 | 11/30/18 | 839 | Cortes Mendiola, Victor H | 21 | 903 | 21922
PR | 112 | 11/30/18 | 840 | Cortes Sepulveda, Jose R | 13 | 338 | 21923
PR | 112 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I | 16 | 464 | 21988
PR | 112 | 12/07/18 | 52 | Cortes Mendiola, Victor H | 24 | 1032 | 21995
PR | 112 | 12/07/18 | 53 | Cortes Sepulveda, Jose R | 24 | 624 | 21996
PR | 112 | 12/14/18 | 268 | Balderas Ortiz, Ricardo I | 28 | 812 | 22128
PR | 112 | 12/14/18 | 276 | Cortes Mendiola, Victor H | 28 | 1204 | 22136
PR | 112 | 12/14/18 | 277 | Cortes Sepulveda, Jose R | 28 | 728 | 22137
PR | 112 | 12/21/18 | 509 | Balderas Ortiz, Ricardo I | 16 | 464 | 22200
PR | 112 | 12/21/18 | 517 | Cortes Mendiola, Victor H | 26 | 1118 | 22208
PR | 112 | 12/21/18 | 518 | Cortes Sepulveda, Jose R | 16 | 416 | 22209
PR | 112 | 12/21/18 | 540 | Hubbard, Robert W | 3 | 147 | 22230
PR | 112 | 12/28/18 | 709 | Cortes Sepulveda, Jose R | 5 | 130 | 22282
PR | 112 | 01/11/19 | 213 | Balderas Ortiz, Ricardo I | 4 | 116 | 22415
PR | 112 | 01/11/19 | 221 | Cortes Mendiola, Victor H | 3 | 129 | 22423
PR | 112 | 01/11/19 | 222 | Cortes Sepulveda, Jose R | 11 | 286 | 22424
PR | 112 | 01/18/19 | 476 | Cortes Mendiola, Victor H | 8 | 344 | 22497
PR | 120 | 07/06/18 | 38 | Hubbard, Robert W | 2 | 94 | 20334
PR | 120 | 01/18/19 | 476 | Cortes Mendiola, Victor H | 5 | 215 | 22497
PR | 120 | 02/01/19 | 13 | Cortes Mendiola, Victor H | 2 | 86 | 22642
PR | 120 | 02/22/19 | 588 | Cortes Mendiola, Victor H | 10 | 430 | 22850
PR | 120 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I | 16 | 464 | 22912
PR | 120 | 03/01/19 | 6 | Barbosa, Michael S | 8 | 200 | 22913
PR | 120 | 03/01/19 | 9 | Benites Portillo, Marvin E | 26 | 624 | 22916
PR | 120 | 03/01/19 | 11 | Chevez, Herson G | 4 | 120 | 22918
PR | 120 | 03/01/19 | 11 | Chevez, Herson G | 29 | 580 | 22918
PR | 120 | 03/01/19 | 13 | Cortes Mendiola, Victor H | 8 | 516 | 22920
PR | 120 | 03/01/19 | 13 | Cortes Mendiola, Victor H | 30 | 1290 | 22920
PR | 120 | 03/01/19 | 14 | Cortes Sepulveda, Jose R | 33 | 858 | 22921
PR | 120 | 03/01/19 | 43 | Lovo, German G | 18 | 450 | 22950
PR | 120 | 03/01/19 | 59 | Rodriguez Arevalos, Christian | 8 | 184 | 22966
PR | 120 | 03/08/19 | 251 | Benites Portillo, Marvin E | 41 | 984 | 22989
PR | 120 | 03/08/19 | 253 | Chevez, Herson G | 9 | 270 | 22991
PR | 120 | 03/08/19 | 253 | Chevez, Herson G | 40 | 800 | 22991
PR | 120 | 03/08/19 | 255 | Cortes Mendiola, Victor H | 10 | 645 | 22993
PR | 120 | 03/08/19 | 255 | Cortes Mendiola, Victor H | 29 | 1247 | 22993
PR | 120 | 03/08/19 | 257 | Crespin Portillo, Juan D | 1 | 25.5 | 22995
PR | 120 | 03/08/19 | 257 | Crespin Portillo, Juan D | 6 | 102 | 22995
PR | 120 | 03/08/19 | 283 | Lovo, German G | 40 | 1000 | 23022
PR | 120 | 03/08/19 | 298 | Rodriguez Arevalos, Christian | 8 | 184 | 23037
PR | 120 | 03/08/19 | 302 | Serrano, Jeremiah G | 1 | 25.5 | 23041
PR | 120 | 03/08/19 | 302 | Serrano, Jeremiah G | 6 | 102 | 23041
PR | 120 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I | 2 | 87 | 23056
PR | 120 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I | 24 | 696 | 23056
PR | 120 | 03/15/19 | 497 | Belcher, Jacob T | 2 | 54 | 23059
PR | 120 | 03/15/19 | 497 | Belcher, Jacob T | 40 | 720 | 23059
PR | 120 | 03/15/19 | 498 | Benites Portillo, Marvin E | 43 | 1032 | 23060
PR | 120 | 03/15/19 | 500 | Chevez, Herson G | 3 | 90 | 23062
PR | 120 | 03/15/19 | 500 | Chevez, Herson G | 40 | 800 | 23062
PR | 120 | 03/15/19 | 502 | Cortes Mendiola, Victor H | 3 | 193.5 | 23064
PR | 120 | 03/15/19 | 502 | Cortes Mendiola, Victor H | 31 | 1333 | 23064
PR | 120 | 03/15/19 | 503 | Cortes Sepulveda, Jose R | 39 | 1014 | 23065
PR | 120 | 03/15/19 | 521 | Hoeg, Xavier A | 2 | 51 | 23083
PR | 120 | 03/15/19 | 521 | Hoeg, Xavier A | 40 | 680 | 23083
PR | 120 | 03/15/19 | 525 | Hubbard, Robert W | 2 | 98 | 23087
PR | 120 | 03/15/19 | 530 | Lovo, German G | 33 | 825 | 23092
PR | 120 | 03/15/19 | 531 | Lucas Tzintzun, Rafael | 17 | 306 | 23093
PR | 120 | 03/22/19 | 708 | Balderas Ortiz, Ricardo I | 36 | 1044 | 23129
PR | 120 | 03/22/19 | 711 | Belcher, Jacob T | 5 | 135 | 23132
PR | 120 | 03/22/19 | 711 | Belcher, Jacob T | 40 | 720 | 23132
PR | 120 | 03/22/19 | 712 | Benites Portillo, Marvin E | 36 | 864 | 23133
PR | 120 | 03/22/19 | 714 | Chevez, Herson G | 5 | 150 | 23135
PR | 120 | 03/22/19 | 714 | Chevez, Herson G | 40 | 800 | 23135
PR | 120 | 03/22/19 | 716 | Cortes Mendiola, Victor H | 5 | 322.5 | 23137
PR | 120 | 03/22/19 | 716 | Cortes Mendiola, Victor H | 40 | 1720 | 23137
PR | 120 | 03/22/19 | 717 | Cortes Sepulveda, Jose R | 3 | 117 | 23138
PR | 120 | 03/22/19 | 717 | Cortes Sepulveda, Jose R | 40 | 1040 | 23138
PR | 120 | 03/22/19 | 735 | Hoeg, Xavier A | 17 | 289 | 23156
PR | 120 | 03/22/19 | 744 | Lovo, German G | 43 | 1075 | 23165
PR | 120 | 03/22/19 | 761 | Saules Bezanilla, Fernando | 5 | 120 | 23182
PR | 120 | 03/22/19 | 761 | Saules Bezanilla, Fernando | 40 | 640 | 23182
PR | 120 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I | 8 | 348 | 23203
PR | 120 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I | 40 | 1160 | 23203
PR | 120 | 03/29/19 | 922 | Belcher, Jacob T | 12 | 324 | 23206
PR | 120 | 03/29/19 | 922 | Belcher, Jacob T | 40 | 720 | 23206
PR | 120 | 03/29/19 | 923 | Benites Portillo, Marvin E | 12 | 432 | 23207
PR | 120 | 03/29/19 | 923 | Benites Portillo, Marvin E | 40 | 960 | 23207
PR | 120 | 03/29/19 | 925 | Chevez, Herson G | 12 | 360 | 23209
PR | 120 | 03/29/19 | 925 | Chevez, Herson G | 40 | 800 | 23209
PR | 120 | 03/29/19 | 927 | Cortes Mendiola, Victor H | 10 | 645 | 23211
PR | 120 | 03/29/19 | 927 | Cortes Mendiola, Victor H | 35 | 1505 | 23211
PR | 120 | 03/29/19 | 928 | Cortes Sepulveda, Jose R | 8 | 312 | 23212
PR | 120 | 03/29/19 | 928 | Cortes Sepulveda, Jose R | 24 | 624 | 23212
PR | 120 | 03/29/19 | 947 | Hoeg, Xavier A | 37 | 629 | 23231
PR | 120 | 03/29/19 | 951 | Hubbard, Robert W | 1.5 | 73.5 | 23235
PR | 120 | 03/29/19 | 956 | Lovo, German G | 3 | 112.5 | 23240
PR | 120 | 03/29/19 | 956 | Lovo, German G | 41 | 1025 | 23240
PR | 120 | 03/29/19 | 957 | Lucas Tzintzun, Rafael | 12 | 324 | 23241
PR | 120 | 03/29/19 | 957 | Lucas Tzintzun, Rafael | 40 | 720 | 23241
PR | 120 | 03/29/19 | 973 | Saules Bezanilla, Fernando | 26 | 416 | 23257
PR | 120 | 03/29/19 | 973 | Saules Bezanilla, Fernando | 12 | 288 | 23257
PR | 120 | 03/29/19 | 973 | Saules Bezanilla, Fernando | 40 | 640 | 23257
PR | 120 | 03/29/19 | 977 | Sorto Regalado, Milton J | 12 | 288 | 23261
PR | 120 | 03/29/19 | 977 | Sorto Regalado, Milton J | 40 | 640 | 23261
PR | 120 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I | 31 | 899 | 23275
PR | 120 | 04/05/19 | 84 | Belcher, Jacob T | 40 | 720 | 23278
PR | 120 | 04/05/19 | 85 | Benites Portillo, Marvin E | 3 | 108 | 23279
PR | 120 | 04/05/19 | 85 | Benites Portillo, Marvin E | 35 | 840 | 23279
PR | 120 | 04/05/19 | 87 | Chevez, Herson G | 10 | 300 | 23281
PR | 120 | 04/05/19 | 87 | Chevez, Herson G | 40 | 800 | 23281
PR | 120 | 04/05/19 | 89 | Cortes Mendiola, Victor H | 8 | 516 | 23283
PR | 120 | 04/05/19 | 89 | Cortes Mendiola, Victor H | 34 | 1462 | 23283
PR | 120 | 04/05/19 | 90 | Cortes Sepulveda, Jose R | 4 | 156 | 23284
PR | 120 | 04/05/19 | 90 | Cortes Sepulveda, Jose R | 40 | 1040 | 23284
PR | 120 | 04/05/19 | 110 | Hoeg, Xavier A | 34 | 578 | 23304
PR | 120 | 04/05/19 | 119 | Lovo, German G | 3 | 112.5 | 23313
PR | 120 | 04/05/19 | 119 | Lovo, German G | 40 | 1000 | 23313
PR | 120 | 04/05/19 | 120 | Lucas Tzintzun, Rafael | 10 | 270 | 23314
PR | 120 | 04/05/19 | 120 | Lucas Tzintzun, Rafael | 40 | 720 | 23314
PR | 120 | 04/05/19 | 136 | Saules Bezanilla, Fernando | 8 | 192 | 23330
PR | 120 | 04/05/19 | 136 | Saules Bezanilla, Fernando | 40 | 640 | 23330
PR | 120 | 04/05/19 | 140 | Sorto Regalado, Milton J | 10 | 240 | 23334
PR | 120 | 04/05/19 | 140 | Sorto Regalado, Milton J | 40 | 640 | 23334
PR | 120 | 04/12/19 | 328 | Belcher, Jacob T | 1 | 27 | 23352
PR | 120 | 04/12/19 | 328 | Belcher, Jacob T | 40 | 720 | 23352
PR | 120 | 04/12/19 | 329 | Benites Portillo, Marvin E | 40 | 960 | 23353
PR | 120 | 04/12/19 | 331 | Chevez, Herson G | 1 | 30 | 23355
PR | 120 | 04/12/19 | 331 | Chevez, Herson G | 40 | 800 | 23355
PR | 120 | 04/12/19 | 333 | Cortes Mendiola, Victor H | 30 | 1380 | 23357
PR | 120 | 04/12/19 | 353 | Hoeg, Xavier A | 1 | 25.5 | 23377
PR | 120 | 04/12/19 | 353 | Hoeg, Xavier A | 40 | 680 | 23377
PR | 120 | 04/12/19 | 357 | Hubbard, Robert W | 2 | 100 | 23381
PR | 120 | 04/12/19 | 363 | Lovo, German G | 1 | 37.5 | 23387
PR | 120 | 04/12/19 | 363 | Lovo, German G | 40 | 1000 | 23387
PR | 120 | 04/12/19 | 364 | Lucas Tzintzun, Rafael | 1 | 27 | 23388
PR | 120 | 04/12/19 | 364 | Lucas Tzintzun, Rafael | 40 | 720 | 23388
PR | 120 | 04/12/19 | 384 | Sorto Regalado, Milton J | 1 | 24 | 23408
PR | 120 | 04/12/19 | 384 | Sorto Regalado, Milton J | 40 | 640 | 23408
PR | 120 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I | 16 | 464 | 23423
PR | 120 | 04/19/19 | 525 | Belcher, Jacob T | 40 | 720 | 23426
PR | 120 | 04/19/19 | 526 | Benites Portillo, Marvin E | 32 | 768 | 23427
PR | 120 | 04/19/19 | 528 | Chevez, Herson G | 24 | 480 | 23429
PR | 120 | 04/19/19 | 530 | Cortes Mendiola, Victor H | 38 | 1748 | 23431
PR | 120 | 04/19/19 | 551 | Hoeg, Xavier A | 32 | 544 | 23452
PR | 120 | 04/19/19 | 561 | Lovo, German G | 32 | 800 | 23462
PR | 120 | 04/19/19 | 562 | Lucas Tzintzun, Rafael | 32 | 576 | 23463
PR | 120 | 04/19/19 | 582 | Sorto Regalado, Milton J | 8 | 128 | 23483
PR | 120 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I | 6 | 288 | 23499
PR | 120 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23499
PR | 120 | 04/26/19 | 745 | Belcher, Jacob T | 6 | 180 | 23502
PR | 120 | 04/26/19 | 745 | Belcher, Jacob T | 40 | 800 | 23502
PR | 120 | 04/26/19 | 746 | Benites Portillo, Marvin E | 38 | 1026 | 23503
PR | 120 | 04/26/19 | 748 | Chevez, Herson G | 6 | 207 | 23505
PR | 120 | 04/26/19 | 748 | Chevez, Herson G | 40 | 920 | 23505
PR | 120 | 04/26/19 | 750 | Cortes Mendiola, Victor H | 6 | 414 | 23507
PR | 120 | 04/26/19 | 750 | Cortes Mendiola, Victor H | 28 | 1288 | 23507
PR | 120 | 04/26/19 | 770 | Hoeg, Xavier A | 32 | 544 | 23527
PR | 120 | 04/26/19 | 780 | Lovo, German G | 32 | 864 | 23537
PR | 120 | 04/26/19 | 781 | Lucas Tzintzun, Rafael | 6 | 189 | 23538
PR | 120 | 04/26/19 | 781 | Lucas Tzintzun, Rafael | 40 | 840 | 23538
PR | 120 | 04/26/19 | 787 | Portillo Soriano, Walter A | 6 | 198 | 23544
PR | 120 | 04/26/19 | 787 | Portillo Soriano, Walter A | 24 | 528 | 23544
PR | 120 | 04/26/19 | 791 | Rivera, Eli P | 6 | 270 | 23548
PR | 120 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I | 6 | 288 | 23571
PR | 120 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23571
PR | 120 | 05/03/19 | 12 | Belcher, Jacob T | 6 | 180 | 23574
PR | 120 | 05/03/19 | 12 | Belcher, Jacob T | 40 | 800 | 23574
PR | 120 | 05/03/19 | 13 | Benites Portillo, Marvin E | 39 | 1053 | 23575
PR | 120 | 05/03/19 | 15 | Chevez, Herson G | 6 | 207 | 23577
PR | 120 | 05/03/19 | 15 | Chevez, Herson G | 40 | 920 | 23577
PR | 120 | 05/03/19 | 17 | Cortes Mendiola, Victor H | 40 | 1840 | 23579
PR | 120 | 05/03/19 | 38 | Hoeg, Xavier A | 40 | 680 | 23600
PR | 120 | 05/03/19 | 42 | Hubbard, Robert W | 6 | 300 | 23604
PR | 120 | 05/03/19 | 50 | Lucas Tzintzun, Rafael | 6 | 189 | 23612
PR | 120 | 05/03/19 | 50 | Lucas Tzintzun, Rafael | 40 | 840 | 23612
PR | 120 | 05/03/19 | 56 | Portillo Soriano, Walter A | 40 | 880 | 23618
PR | 120 | 05/10/19 | 162 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23646
PR | 120 | 05/10/19 | 165 | Belcher, Jacob T | 40 | 800 | 23649
PR | 120 | 05/10/19 | 166 | Benites Portillo, Marvin E | 40 | 1080 | 23650
PR | 120 | 05/10/19 | 168 | Chevez, Herson G | 40 | 920 | 23652
PR | 120 | 05/10/19 | 170 | Cortes Mendiola, Victor H | 21 | 966 | 23654
PR | 120 | 05/10/19 | 171 | Cortes Sepulveda, Jose R | 24 | 720 | 23655
PR | 120 | 05/10/19 | 191 | Hoeg, Xavier A | 40 | 680 | 23675
PR | 120 | 05/10/19 | 195 | Hubbard, Robert W | 6 | 300 | 23679
PR | 120 | 05/10/19 | 202 | Lovo, German G | 40 | 1080 | 23686
PR | 120 | 05/10/19 | 203 | Lucas Tzintzun, Rafael | 40 | 840 | 23687
PR | 120 | 05/10/19 | 209 | Portillo Soriano, Walter A | 40 | 880 | 23693
PR | 120 | 05/17/19 | 393 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23724
PR | 120 | 05/17/19 | 396 | Belcher, Jacob T | 32 | 640 | 23727
PR | 120 | 05/17/19 | 397 | Benites Portillo, Marvin E | 16 | 432 | 23728
PR | 120 | 05/17/19 | 400 | Chevez, Herson G | 40 | 920 | 23731
PR | 120 | 05/17/19 | 402 | Cortes Mendiola, Victor H | 35 | 1610 | 23733
PR | 120 | 05/17/19 | 403 | Cortes Sepulveda, Jose R | 40 | 1200 | 23734
PR | 120 | 05/17/19 | 415 | Galdamez, Dagoberto A | 16 | 480 | 23746
PR | 120 | 05/17/19 | 423 | Hoeg, Xavier A | 40 | 680 | 23754
PR | 120 | 05/17/19 | 434 | Lovo, German G | 37 | 999 | 23765
PR | 120 | 05/17/19 | 435 | Lucas Tzintzun, Rafael | 38 | 798 | 23766
PR | 120 | 05/17/19 | 441 | Portillo Soriano, Walter A | 32 | 704 | 23772
PR | 120 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I | 6 | 288 | 23801
PR | 120 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23801
PR | 120 | 05/24/19 | 609 | Belcher, Jacob T | 37.5 | 750 | 23804
PR | 120 | 05/24/19 | 612 | Chevez, Herson G | 6 | 207 | 23807
PR | 120 | 05/24/19 | 612 | Chevez, Herson G | 40 | 920 | 23807
PR | 120 | 05/24/19 | 614 | Cortes Mendiola, Victor H | 6 | 414 | 23809
PR | 120 | 05/24/19 | 614 | Cortes Mendiola, Victor H | 33 | 1518 | 23809
PR | 120 | 05/24/19 | 627 | Galdamez, Dagoberto A | 32 | 960 | 23822
PR | 120 | 05/24/19 | 635 | Hoeg, Xavier A | 40 | 680 | 23830
PR | 120 | 05/24/19 | 646 | Lovo, German G | 40 | 1080 | 23841
PR | 120 | 05/24/19 | 647 | Lucas Tzintzun, Rafael | 6 | 189 | 23842
PR | 120 | 05/24/19 | 647 | Lucas Tzintzun, Rafael | 40 | 840 | 23842
PR | 120 | 05/24/19 | 666 | Sorto Regalado, Milton J | 6 | 144 | 23861
PR | 120 | 05/24/19 | 666 | Sorto Regalado, Milton J | 40 | 640 | 23861
PR | 120 | 05/31/19 | 879 | Balderas Ortiz, Ricardo I | 32 | 1024 | 23879
PR | 120 | 05/31/19 | 882 | Belcher, Jacob T | 32 | 640 | 23882
PR | 120 | 05/31/19 | 883 | Benites Portillo, Marvin E | 16 | 432 | 23883
PR | 120 | 05/31/19 | 886 | Chevez, Herson G | 32 | 736 | 23886
PR | 120 | 05/31/19 | 888 | Cortes Mendiola, Victor H | 22 | 1012 | 23888
PR | 120 | 05/31/19 | 889 | Cortes Sepulveda, Jose R | 29 | 870 | 23889
PR | 120 | 05/31/19 | 901 | Galdamez, Dagoberto A | 29 | 870 | 23901
PR | 120 | 05/31/19 | 909 | Hoeg, Xavier A | 32 | 544 | 23909
PR | 120 | 05/31/19 | 913 | Hubbard, Robert W | 1 | 50 | 23913
PR | 120 | 05/31/19 | 920 | Lovo, German G | 29 | 783 | 23920
PR | 120 | 05/31/19 | 921 | Lucas Tzintzun, Rafael | 32 | 672 | 23921
PR | 120 | 05/31/19 | 940 | Sorto Regalado, Milton J | 32 | 512 | 23940
PR | 120 | 06/07/19 | 181 | Balderas Ortiz, Ricardo I | 40 | 1280 | 23956
PR | 120 | 06/07/19 | 184 | Belcher, Jacob T | 40 | 800 | 23959
PR | 120 | 06/07/19 | 188 | Chevez, Herson G | 40 | 920 | 23963
PR | 120 | 06/07/19 | 190 | Cortes Mendiola, Victor H | 20 | 920 | 23965
PR | 120 | 06/07/19 | 211 | Hoeg, Xavier A | 40 | 680 | 23986
PR | 120 | 06/07/19 | 221 | Lovo, German G | 32 | 864 | 23996
PR | 120 | 06/07/19 | 222 | Lucas Tzintzun, Rafael | 40 | 840 | 23997
PR | 120 | 06/07/19 | 228 | Portillo Soriano, Walter A | 24 | 528 | 24003
PR | 120 | 06/07/19 | 242 | Sorto Regalado, Milton J | 40 | 640 | 24017
PR | 120 | 06/14/19 | 452 | Balderas Ortiz, Ricardo I | 39 | 1248 | 24033
PR | 120 | 06/14/19 | 455 | Belcher, Jacob T | 31.5 | 630 | 24036
PR | 120 | 06/14/19 | 456 | Benites Portillo, Marvin E | 32 | 864 | 24037
PR | 120 | 06/14/19 | 460 | Cortes Mendiola, Victor H | 40 | 1840 | 24041
PR | 120 | 06/14/19 | 468 | Eisenhauer, Tommy J | 6 | 252 | 24049
PR | 120 | 06/14/19 | 471 | Galdamez, Dagoberto A | 32 | 960 | 24052
PR | 120 | 06/14/19 | 474 | Gerard, Jordan E | 5 | 270 | 24055
PR | 120 | 06/14/19 | 479 | Hoeg, Xavier A | 31.5 | 535.5 | 24060
PR | 120 | 06/14/19 | 490 | Lovo, German G | 16 | 432 | 24071
PR | 120 | 06/14/19 | 491 | Lucas Tzintzun, Rafael | 40 | 840 | 24072
PR | 120 | 06/14/19 | 497 | Portillo Soriano, Walter A | 40 | 880 | 24078
PR | 120 | 06/14/19 | 510 | Sorto Regalado, Milton J | 39 | 624 | 24091
PR | 120 | 06/21/19 | 620 | Balderas Ortiz, Ricardo I | 36 | 1152 | 24106
PR | 120 | 06/21/19 | 623 | Belcher, Jacob T | 32 | 640 | 24109
PR | 120 | 06/21/19 | 624 | Benites Portillo, Marvin E | 8 | 216 | 24110
PR | 120 | 06/21/19 | 628 | Chevez, Herson G | 40 | 920 | 24114
PR | 120 | 06/21/19 | 630 | Cortes Mendiola, Victor H | 30 | 1380 | 24116
PR | 120 | 06/21/19 | 642 | Galdamez, Dagoberto A | 16 | 480 | 24128
PR | 120 | 06/21/19 | 650 | Hoeg, Xavier A | 40 | 680 | 24136
PR | 120 | 06/21/19 | 654 | Hubbard, Robert W | 6 | 300 | 24140
PR | 120 | 06/21/19 | 661 | Lovo, German G | 10 | 270 | 24147
PR | 120 | 06/21/19 | 662 | Lucas Tzintzun, Rafael | 32 | 672 | 24148
PR | 120 | 06/21/19 | 668 | Portillo Soriano, Walter A | 40 | 880 | 24154
PR | 120 | 06/21/19 | 672 | Rivera, Eli P | 8 | 240 | 24158
PR | 120 | 06/21/19 | 681 | Sorto Regalado, Milton J | 36 | 576 | 24167
PR | 120 | 06/28/19 | 838 | Balderas Ortiz, Ricardo I | 32 | 1024 | 24182
PR | 120 | 06/28/19 | 841 | Belcher, Jacob T | 40 | 800 | 24185
PR | 120 | 06/28/19 | 842 | Benites Portillo, Marvin E | 8 | 216 | 24186
PR | 120 | 06/28/19 | 846 | Chevez, Herson G | 40 | 920 | 24190
PR | 120 | 06/28/19 | 848 | Cortes Mendiola, Victor H | 30 | 1380 | 24192
PR | 120 | 06/28/19 | 849 | Cortes Sepulveda, Jose R | 16 | 480 | 24193
PR | 120 | 06/28/19 | 860 | Galdamez, Dagoberto A | 40 | 1200 | 24204
PR | 120 | 06/28/19 | 868 | Hoeg, Xavier A | 32 | 544 | 24212
PR | 120 | 06/28/19 | 878 | Lovo, German G | 40 | 1080 | 24222
PR | 120 | 06/28/19 | 879 | Lucas Tzintzun, Rafael | 36 | 756 | 24223
PR | 120 | 06/28/19 | 885 | Portillo Soriano, Walter A | 40 | 880 | 24229
PR | 120 | 06/28/19 | 898 | Sorto Regalado, Milton J | 32 | 512 | 24242
PR | 120 | 07/05/19 | 10 | Balderas Ortiz, Ricardo I | 40 | 1280 | 24257
PR | 120 | 07/05/19 | 13 | Belcher, Jacob T | 40 | 800 | 24260
PR | 120 | 07/05/19 | 14 | Benites Portillo, Marvin E | 34 | 918 | 24261
PR | 120 | 07/05/19 | 18 | Chevez, Herson G | 40 | 920 | 24265
PR | 120 | 07/05/19 | 20 | Cortes Mendiola, Victor H | 32 | 1472 | 24267
PR | 120 | 07/05/19 | 21 | Cortes Sepulveda, Jose R | 31 | 930 | 24268
PR | 120 | 07/05/19 | 32 | Galdamez, Dagoberto A | 40 | 1200 | 24279
PR | 120 | 07/05/19 | 40 | Hoeg, Xavier A | 36 | 612 | 24287
PR | 120 | 07/05/19 | 42 | Hubbard, Dustin R | 6 | 150 | 24289
PR | 120 | 07/05/19 | 50 | Lovo, German G | 39 | 1053 | 24297
PR | 120 | 07/05/19 | 51 | Lucas Tzintzun, Rafael | 40 | 840 | 24298
PR | 120 | 07/05/19 | 57 | Portillo Soriano, Walter A | 40 | 880 | 24305
PR | 120 | 07/05/19 | 69 | Sorto Regalado, Milton J | 40 | 640 | 24317
PR | 120 | 07/12/19 | 280 | Balderas Ortiz, Ricardo I | 32 | 1024 | 24332
PR | 120 | 07/12/19 | 283 | Belcher, Jacob T | 32 | 640 | 24335
PR | 120 | 07/12/19 | 284 | Benites Portillo, Marvin E | 32 | 864 | 24336
PR | 120 | 07/12/19 | 288 | Chevez, Herson G | 32 | 736 | 24340
PR | 120 | 07/12/19 | 290 | Cortes Mendiola, Victor H | 16 | 736 | 24342
PR | 120 | 07/12/19 | 301 | Galdamez, Dagoberto A | 32 | 960 | 24353
PR | 120 | 07/12/19 | 309 | Hoeg, Xavier A | 32 | 544 | 24361
PR | 120 | 07/12/19 | 313 | Hubbard, Robert W | 5.5 | 275 | 24365
PR | 120 | 07/12/19 | 319 | Lovo, German G | 32 | 864 | 24371
PR | 120 | 07/12/19 | 320 | Lucas Tzintzun, Rafael | 31 | 651 | 24372
PR | 120 | 07/12/19 | 326 | Portillo Soriano, Walter A | 32 | 704 | 24378
PR | 120 | 07/12/19 | 340 | Sorto Regalado, Milton J | 32 | 512 | 24392
PR | 120 | 07/12/19 | 341 | Stahlschmidt, John P | 32 | 608 | 24393
PR | 120 | 07/19/19 | 510 | Balderas Ortiz, Ricardo I | 40 | 1280 | 24409
PR | 120 | 07/19/19 | 513 | Belcher, Jacob T | 40 | 800 | 24412
PR | 120 | 07/19/19 | 514 | Benites Portillo, Marvin E | 32 | 864 | 24413
PR | 120 | 07/19/19 | 518 | Chevez, Herson G | 40 | 920 | 24417
PR | 120 | 07/19/19 | 520 | Cortes Mendiola, Victor H | 24 | 1104 | 24419
PR | 120 | 07/19/19 | 531 | Galdamez, Dagoberto A | 16 | 480 | 24430
PR | 120 | 07/19/19 | 539 | Hoeg, Xavier A | 40 | 680 | 24438
PR | 120 | 07/19/19 | 549 | Lovo, German G | 40 | 1080 | 24448
PR | 120 | 07/19/19 | 550 | Lucas Tzintzun, Rafael | 40 | 840 | 24449
PR | 120 | 07/19/19 | 556 | Portillo Soriano, Walter A | 40 | 880 | 24455
PR | 120 | 07/19/19 | 570 | Sorto Regalado, Milton J | 32 | 512 | 24469
PR | 120 | 07/26/19 | 614 | Balderas Ortiz, Ricardo I | 30 | 960 | 24563
PR | 120 | 07/26/19 | 617 | Belcher, Jacob T | 16 | 320 | 24566
PR | 120 | 07/26/19 | 618 | Benites Portillo, Marvin E | 40 | 1080 | 24567
PR | 120 | 07/26/19 | 622 | Chevez, Herson G | 40 | 920 | 24571
PR | 120 | 07/26/19 | 624 | Cortes Mendiola, Victor H | 40 | 1840 | 24573
PR | 120 | 07/26/19 | 642 | Hoeg, Xavier A | 16 | 272 | 24591
PR | 120 | 07/26/19 | 646 | Hubbard, Robert W | 4 | 200 | 24595
PR | 120 | 07/26/19 | 652 | Lovo, German G | 27 | 729 | 24601
PR | 120 | 07/26/19 | 653 | Lucas Tzintzun, Rafael | 40 | 840 | 24602
PR | 120 | 07/26/19 | 659 | Portillo Soriano, Walter A | 40 | 880 | 24608
PR | 120 | 07/26/19 | 673 | Sorto Regalado, Milton J | 40 | 640 | 24622
PR | 120 | 08/02/19 | 6 | Balderas Ortiz, Ricardo I | 40 | 1280 | 24637
PR | 120 | 08/02/19 | 14 | Chevez, Herson G | 40 | 920 | 24645
PR | 120 | 08/02/19 | 16 | Cortes Mendiola, Victor H | 25 | 1150 | 24647
PR | 120 | 08/02/19 | 17 | Cortes Sepulveda, Jose R | 37 | 1110 | 24648
PR | 120 | 08/02/19 | 38 | Hubbard, Robert W | 4 | 200 | 24669
PR | 120 | 08/02/19 | 44 | Lovo, German G | 40 | 1080 | 24675
PR | 120 | 08/02/19 | 45 | Lucas Tzintzun, Rafael | 36 | 756 | 24676
PR | 120 | 08/02/19 | 51 | Portillo Soriano, Walter A | 40 | 880 | 24682
PR | 120 | 08/02/19 | 55 | Rivera, Eli P | 40 | 1200 | 24686
PR | 120 | 08/02/19 | 64 | Sorto Regalado, Milton J | 40 | 640 | 24695
PR | 120 | 08/09/19 | 258 | Balderas Ortiz, Ricardo I | 40 | 1280 | 24711
PR | 120 | 08/09/19 | 262 | Benites Portillo, Marvin E | 37 | 999 | 24715
PR | 120 | 08/09/19 | 266 | Chevez, Herson G | 32 | 736 | 24719
PR | 120 | 08/09/19 | 268 | Cortes Mendiola, Victor H | 30 | 1380 | 24721
PR | 120 | 08/09/19 | 269 | Cortes Sepulveda, Jose R | 24 | 720 | 24722
PR | 120 | 08/09/19 | 279 | Galdamez, Dagoberto A | 16 | 480 | 24732
PR | 120 | 08/09/19 | 291 | Hubbard, Robert W | 4 | 200 | 24744
PR | 120 | 08/09/19 | 297 | Lovo, German G | 32 | 864 | 24750
PR | 120 | 08/09/19 | 298 | Lucas Tzintzun, Rafael | 32 | 672 | 24751
PR | 120 | 08/09/19 | 304 | Portillo Soriano, Walter A | 32 | 704 | 24757
PR | 120 | 08/09/19 | 308 | Rivera, Eli P | 24 | 720 | 24761
PR | 120 | 08/09/19 | 317 | Sorto Regalado, Milton J | 32 | 512 | 24770
PR | 120 | 08/16/19 | 565 | Balderas Ortiz, Ricardo I | 32 | 1024 | 24784
PR | 120 | 08/16/19 | 569 | Benites Portillo, Marvin E | 40 | 1080 | 24788
PR | 120 | 08/16/19 | 573 | Chevez, Herson G | 40 | 920 | 24792
PR | 120 | 08/16/19 | 575 | Cortes Mendiola, Victor H | 40 | 1840 | 24794
PR | 120 | 08/16/19 | 576 | Cortes Sepulveda, Jose R | 40 | 1200 | 24795
PR | 120 | 08/16/19 | 586 | Galdamez, Dagoberto A | 40 | 1200 | 24805
PR | 120 | 08/16/19 | 604 | Lovo, German G | 24 | 648 | 24823
PR | 120 | 08/16/19 | 605 | Lucas Tzintzun, Rafael | 24 | 504 | 24824
PR | 120 | 08/16/19 | 611 | Portillo Soriano, Walter A | 24 | 528 | 24830
PR | 120 | 08/16/19 | 615 | Rivera, Eli P | 24 | 720 | 24834
PR | 120 | 08/16/19 | 624 | Sorto Regalado, Milton J | 24 | 384 | 24843
PR | 120 | 08/23/19 | 801 | Balderas Ortiz, Ricardo I | 40 | 1280 | 24859
PR | 120 | 08/23/19 | 805 | Benites Portillo, Marvin E | 40 | 1080 | 24863
PR | 120 | 08/23/19 | 809 | Chevez, Herson G | 40 | 920 | 24867
PR | 120 | 08/23/19 | 811 | Cortes Mendiola, Victor H | 40 | 1840 | 24869
PR | 120 | 08/23/19 | 812 | Cortes Sepulveda, Jose R | 32 | 960 | 24870
PR | 120 | 08/23/19 | 822 | Galdamez, Dagoberto A | 40 | 1200 | 24880
PR | 120 | 08/23/19 | 841 | Lovo, German G | 8 | 216 | 24899
PR | 120 | 08/23/19 | 842 | Lucas Tzintzun, Rafael | 32 | 672 | 24900
PR | 120 | 08/23/19 | 848 | Portillo Soriano, Walter A | 40 | 880 | 24906
PR | 120 | 08/23/19 | 852 | Rivera, Eli P | 40 | 1200 | 24910
PR | 120 | 08/23/19 | 861 | Sorto Regalado, Milton J | 32 | 512 | 24919
PR | 120 | 08/30/19 | 992 | Balderas Ortiz, Ricardo I | 32 | 1024 | 24934
PR | 120 | 08/30/19 | 996 | Benites Portillo, Marvin E | 40 | 1080 | 24938
PR | 120 | 08/30/19 | 1000 | Chevez, Herson G | 40 | 920 | 24942
PR | 120 | 08/30/19 | 1002 | Cortes Mendiola, Victor H | 24 | 1104 | 24944
PR | 120 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R | 16 | 480 | 24945
PR | 120 | 08/30/19 | 1013 | Galdamez, Dagoberto A | 40 | 1200 | 24955
PR | 120 | 08/30/19 | 1026 | Hubbard, Robert W | 5 | 250 | 24968
PR | 120 | 08/30/19 | 1032 | Lovo, German G | 8 | 216 | 24974
PR | 120 | 08/30/19 | 1033 | Lucas Tzintzun, Rafael | 32 | 672 | 24975
PR | 120 | 08/30/19 | 1039 | Portillo Soriano, Walter A | 40 | 880 | 24981
PR | 120 | 08/30/19 | 1043 | Rivera, Eli P | 16 | 480 | 24985
PR | 120 | 08/30/19 | 1052 | Sorto Regalado, Milton J | 40 | 640 | 24994
PR | 120 | 09/06/19 | 13 | Balderas Ortiz, Ricardo I | 16 | 512 | 25011
PR | 120 | 09/06/19 | 17 | Benites Portillo, Marvin E | 32 | 864 | 25015
PR | 120 | 09/06/19 | 21 | Chevez, Herson G | 32 | 736 | 25019
PR | 120 | 09/06/19 | 23 | Cortes Mendiola, Victor H | 30 | 1380 | 25021
PR | 120 | 09/06/19 | 24 | Cortes Sepulveda, Jose R | 24 | 720 | 25022
PR | 120 | 09/06/19 | 34 | Galdamez, Dagoberto A | 24 | 720 | 25032
PR | 120 | 09/06/19 | 47 | Hubbard, Robert W | 5 | 250 | 25045
PR | 120 | 09/06/19 | 53 | Lovo, German G | 32 | 864 | 25051
PR | 120 | 09/06/19 | 54 | Lucas Tzintzun, Rafael | 32 | 672 | 25052
PR | 120 | 09/06/19 | 60 | Portillo Soriano, Walter A | 16 | 352 | 25058
PR | 120 | 09/06/19 | 64 | Rivera, Eli P | 24 | 720 | 25062
PR | 120 | 09/06/19 | 73 | Sorto Regalado, Milton J | 16 | 256 | 25071
PR | 120 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I | 16 | 512 | 25086
PR | 120 | 09/13/19 | 241 | Benites Portillo, Marvin E | 16 | 432 | 25090
PR | 120 | 09/13/19 | 245 | Chevez, Herson G | 40 | 920 | 25094
PR | 120 | 09/13/19 | 247 | Cortes Mendiola, Victor H | 20 | 920 | 25096
PR | 120 | 09/13/19 | 248 | Cortes Sepulveda, Jose R | 16 | 480 | 25097
PR | 120 | 09/13/19 | 258 | Galdamez, Dagoberto A | 40 | 1200 | 25107
PR | 120 | 09/13/19 | 276 | Lovo, German G | 40 | 1080 | 25125
PR | 120 | 09/13/19 | 277 | Lucas Tzintzun, Rafael | 16 | 336 | 25126
PR | 120 | 09/13/19 | 283 | Portillo Soriano, Walter A | 40 | 880 | 25132
PR | 120 | 09/13/19 | 287 | Rivera, Eli P | 24 | 720 | 25136
PR | 120 | 09/13/19 | 296 | Sorto Regalado, Milton J | 40 | 640 | 25145
PR | 120 | 09/20/19 | 474 | Balderas Ortiz, Ricardo I | 37 | 1184 | 25160
PR | 120 | 09/20/19 | 478 | Benites Portillo, Marvin E | 40 | 1080 | 25164
PR | 120 | 09/20/19 | 484 | Cortes Mendiola, Victor H | 33 | 1518 | 25170
PR | 120 | 09/20/19 | 485 | Cortes Sepulveda, Jose R | 34 | 1020 | 25171
PR | 120 | 09/20/19 | 521 | Portillo Soriano, Walter A | 40 | 880 | 25207
PR | 120 | 09/20/19 | 525 | Rivera, Eli P | 40 | 1200 | 25211
PR | 120 | 09/20/19 | 534 | Sorto Regalado, Milton J | 37 | 592 | 25220
PR | 120 | 09/27/19 | 630 | Balderas Ortiz, Ricardo I | 40 | 1280 | 25235
PR | 120 | 09/27/19 | 640 | Cortes Mendiola, Victor H | 20 | 920 | 25245
PR | 120 | 09/27/19 | 641 | Cortes Sepulveda, Jose R | 40 | 1200 | 25246
PR | 120 | 09/27/19 | 674 | Lucas Tzintzun, Rafael | 8 | 168 | 25279
PR | 120 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I | 16 | 512 | 25313
PR | 120 | 10/04/19 | 10 | Benites Portillo, Marvin E | 13 | 351 | 25317
PR | 120 | 10/04/19 | 16 | Cortes Mendiola, Victor H | 20 | 920 | 25323
PR | 120 | 10/04/19 | 17 | Cortes Sepulveda, Jose R | 16 | 480 | 25324
PR | 120 | 10/04/19 | 69 | Sorto Regalado, Milton J | 8 | 128 | 25376
PR | 120 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I | 20 | 640 | 25394
PR | 120 | 10/11/19 | 265 | Benites Portillo, Marvin E | 16 | 432 | 25398
PR | 120 | 10/11/19 | 271 | Cortes Mendiola, Victor H | 19 | 874 | 25405
PR | 120 | 10/11/19 | 272 | Cortes Sepulveda, Jose R | 15 | 450 | 25406
PR | 120 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I | 24 | 768 | 25471
PR | 120 | 10/18/19 | 459 | Benites Portillo, Marvin E | 8 | 216 | 25475
PR | 120 | 10/18/19 | 465 | Cortes Mendiola, Victor H | 20 | 920 | 25481
PR | 120 | 10/18/19 | 466 | Cortes Sepulveda, Jose R | 32 | 960 | 25482
PR | 120 | 10/18/19 | 497 | Lucas Tzintzun, Rafael | 8 | 168 | 25514
PR | 120 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I | 13 | 416 | 25547
PR | 120 | 10/25/19 | 594 | Benites Portillo, Marvin E | 8 | 216 | 25551
PR | 120 | 10/25/19 | 602 | Cortes Sepulveda, Jose R | 13 | 390 | 25559
PR | 120 | 10/25/19 | 632 | Lucas Tzintzun, Rafael | 8 | 168 | 25589
PR | 120 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo | 9 | 315 | 25608
PR | 120 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I | 8 | 288 | 25623
PR | 120 | 11/01/19 | 10 | Benites Portillo, Marvin E | 8 | 232 | 25627
PR | 120 | 11/01/19 | 17 | Cortes Sepulveda, Jose R | 8 | 272 | 25634
PR | 120 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I | 16 | 576 | 25699
PR | 120 | 11/08/19 | 190 | Cortes Mendiola, Victor H | 6 | 300 | 25709
PR | 120 | 11/08/19 | 191 | Cortes Sepulveda, Jose R | 8 | 272 | 25710
PR | 120 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I | 24 | 864 | 25775
PR | 120 | 11/15/19 | 450 | Cortes Mendiola, Victor H | 5 | 250 | 25785
PR | 120 | 11/15/19 | 451 | Cortes Sepulveda, Jose R | 24 | 816 | 25786
PR | 120 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I | 14 | 504 | 25851
PR | 120 | 11/22/19 | 621 | Cortes Mendiola, Victor H | 3 | 150 | 25861
PR | 120 | 11/22/19 | 622 | Cortes Sepulveda, Jose R | 14 | 476 | 25862
PR | 120 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I | 16 | 576 | 25926
PR | 120 | 11/27/19 | 855 | Cortes Mendiola, Victor H | 3 | 150 | 25936
PR | 120 | 11/27/19 | 856 | Cortes Sepulveda, Jose R | 8 | 272 | 25937
PR | 120 | 12/06/19 | 31 | Balderas Ortiz, Ricardo I | 32 | 1152 | 26002
PR | 120 | 12/06/19 | 42 | Cortes Sepulveda, Jose R | 32 | 1088 | 26014
PR | 120 | 12/13/19 | 392 | Balderas Ortiz, Ricardo I | 40 | 1440 | 26157
PR | 120 | 12/13/19 | 402 | Cortes Mendiola, Victor H | 17 | 850 | 26167
PR | 120 | 12/13/19 | 403 | Cortes Sepulveda, Jose R | 40 | 1360 | 26168
PR | 120 | 12/20/19 | 545 | Balderas Ortiz, Ricardo I | 40 | 1440 | 26234
PR | 120 | 12/20/19 | 555 | Cortes Mendiola, Victor H | 2 | 100 | 26244
PR | 120 | 12/20/19 | 556 | Cortes Sepulveda, Jose R | 40 | 1360 | 26245
PR | 120 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I | 18 | 648 | 26310
PR | 120 | 12/27/19 | 713 | Cortes Sepulveda, Jose R | 18 | 612 | 26321
PR | 120 | 01/03/20 | 5 | Balderas Ortiz, Ricardo I | 8 | 288 | 26387
PR | 120 | 01/03/20 | 15 | Cortes Mendiola, Victor H | 2 | 100 | 26397
PR | 120 | 01/03/20 | 16 | Cortes Sepulveda, Jose R | 13 | 442 | 26398
PR | 120 | 01/10/20 | 278 | Balderas Ortiz, Ricardo I | 40 | 1440 | 26465
PR | 120 | 01/10/20 | 289 | Cortes Sepulveda, Jose R | 35 | 1190 | 26476
PR | 120 | 01/24/20 | 688 | Cortes Sepulveda, Jose R | 8 | 272 | 26631
PR | 120 | 01/31/20 | 847 | Cortes Sepulveda, Jose R | 8 | 272 | 26708
PR | 120 | 05/22/20 | 483 | Eliassen, Cory H | 2 | 60 | 27883
PR | 130 | 03/15/19 | 548 | Saules Bezanilla, Fernando | 26 | 416 | 23110
PR | 130 | 03/29/19 | 973 | Saules Bezanilla, Fernando | 26 | -416 | 23257
PR | 130 | 06/14/19 | 467 | Draves, Steven W | 6 | 243 | 24048
PR | 130 | 08/16/19 | 621 | Sanders, Allen O | 2 | 98 | 24840
PR | 130 | 08/23/19 | 835 | Hubbard, Robert W | 2 | 100 | 24893
PR | 130 | 09/13/19 | 293 | Sanders, Allen O | 2 | 98 | 25142
PR | 130 | 09/27/19 | 690 | Sanders, Allen O | 2 | 98 | 25295
PR | 130 | 10/04/19 | 66 | Sanders, Allen O | 2 | 98 | 25373
PR | 130 | 10/18/19 | 472 | Eliassen, Cory H | 19 | 513 | 25488
PR | 130 | 10/18/19 | 477 | Gauthier, Dillon R | 8 | 136 | 25493
PR | 130 | 10/18/19 | 514 | Sanders, Allen O | 2.5 | 122.5 | 25531
PR | 130 | 10/25/19 | 607 | Eliassen, Cory H | 25 | 675 | 25564
PR | 130 | 10/25/19 | 650 | Sanders, Allen O | 5 | 245 | 25607
PR | 130 | 10/25/19 | 656 | Trower-Kelly, Fidel D | 19 | 342 | 25613
PR | 130 | 10/25/19 | 657 | Vazquez Popoca, Jose N | 21 | 357 | 25614
PR | 130 | 11/01/19 | 23 | Eliassen, Cory H | 32 | 960 | 25640
PR | 130 | 11/01/19 | 66 | Sanders, Allen O | 2 | 108 | 25683
PR | 130 | 11/01/19 | 72 | Trower-Kelly, Fidel D | 32 | 672 | 25689
PR | 130 | 11/01/19 | 73 | Vazquez Popoca, Jose N | 24 | 480 | 25690
PR | 130 | 11/08/19 | 197 | Eliassen, Cory H | 24 | 720 | 25716
PR | 130 | 11/08/19 | 240 | Sanders, Allen O | 3 | 162 | 25759
PR | 130 | 11/08/19 | 246 | Trower-Kelly, Fidel D | 32 | 672 | 25765
PR | 130 | 11/08/19 | 247 | Vazquez Popoca, Jose N | 32 | 640 | 25766
PR | 130 | 11/15/19 | 457 | Eliassen, Cory H | 32 | 960 | 25792
PR | 130 | 11/15/19 | 462 | Gauthier, Dillon R | 32 | 576 | 25797
PR | 130 | 11/15/19 | 499 | Sanders, Allen O | 7 | 378 | 25835
PR | 130 | 11/15/19 | 505 | Trower-Kelly, Fidel D | 24 | 504 | 25841
PR | 130 | 11/15/19 | 506 | Vazquez Popoca, Jose N | 8 | 160 | 25842
PR | 130 | 11/22/19 | 628 | Eliassen, Cory H | 38 | 1140 | 25868
PR | 130 | 11/22/19 | 633 | Gauthier, Dillon R | 27 | 486 | 25873
PR | 130 | 11/22/19 | 670 | Sanders, Allen O | 7.5 | 405 | 25910
PR | 130 | 11/22/19 | 676 | Trower-Kelly, Fidel D | 38 | 798 | 25916
PR | 130 | 11/27/19 | 862 | Eliassen, Cory H | 32 | 960 | 25943
PR | 130 | 11/27/19 | 867 | Gauthier, Dillon R | 30 | 540 | 25948
PR | 130 | 11/27/19 | 904 | Sanders, Allen O | 7 | 378 | 25985
PR | 130 | 11/27/19 | 910 | Trower-Kelly, Fidel D | 32 | 672 | 25991
PR | 130 | 12/06/19 | 48 | Eliassen, Cory H | 32 | 960 | 26020
PR | 130 | 12/06/19 | 54 | Gauthier, Dillon R | 32 | 576 | 26026
PR | 130 | 12/06/19 | 91 | Sanders, Allen O | 4 | 216 | 26063
PR | 130 | 12/06/19 | 97 | Trower-Kelly, Fidel D | 28.5 | 598.5 | 26069
PR | 130 | 12/13/19 | 409 | Eliassen, Cory H | 32 | 960 | 26174
PR | 130 | 12/13/19 | 415 | Gauthier, Dillon R | 40 | 720 | 26180
PR | 130 | 12/13/19 | 452 | Sanders, Allen O | 6 | 324 | 26218
PR | 130 | 12/13/19 | 458 | Trower-Kelly, Fidel D | 40 | 840 | 26224
PR | 130 | 12/20/19 | 562 | Eliassen, Cory H | 24 | 720 | 26251
PR | 130 | 12/20/19 | 568 | Gauthier, Dillon R | 32 | 576 | 26257
PR | 130 | 12/20/19 | 605 | Sanders, Allen O | 6 | 324 | 26294
PR | 130 | 12/20/19 | 611 | Trower-Kelly, Fidel D | 40 | 840 | 26300
PR | 130 | 12/27/19 | 720 | Eliassen, Cory H | 24 | 720 | 26328
PR | 130 | 12/27/19 | 726 | Gauthier, Dillon R | 24 | 432 | 26334
PR | 130 | 12/27/19 | 763 | Sanders, Allen O | 5 | 270 | 26371
PR | 130 | 12/27/19 | 769 | Trower-Kelly, Fidel D | 22 | 462 | 26377
PR | 130 | 01/03/20 | 23 | Eliassen, Cory H | 32 | 960 | 26406
PR | 130 | 01/03/20 | 29 | Gauthier, Dillon R | 24 | 432 | 26412
PR | 130 | 01/03/20 | 66 | Sanders, Allen O | 4 | 216 | 26449
PR | 130 | 01/03/20 | 72 | Trower-Kelly, Fidel D | 24 | 504 | 26455
PR | 130 | 01/10/20 | 296 | Eliassen, Cory H | 32 | 960 | 26483
PR | 130 | 01/10/20 | 302 | Gauthier, Dillon R | 12 | 216 | 26489
PR | 130 | 01/10/20 | 339 | Sanders, Allen O | 2.5 | 135 | 26527
PR | 130 | 01/17/20 | 562 | Eliassen, Cory H | 32 | 960 | 26561
PR | 130 | 01/17/20 | 568 | Gauthier, Dillon R | 32 | 576 | 26567
PR | 130 | 01/17/20 | 602 | Romero Garza, Jesus I | 8 | 184 | 26601
PR | 130 | 01/17/20 | 605 | Sanders, Allen O | 6 | 324 | 26604
PR | 130 | 01/17/20 | 611 | Trower-Kelly, Fidel D | 32 | 672 | 26610
PR | 130 | 01/24/20 | 677 | Balderas Ortiz, Ricardo I | 40 | 1440 | 26620
PR | 130 | 01/24/20 | 688 | Cortes Sepulveda, Jose R | 24 | 816 | 26631
PR | 130 | 01/24/20 | 695 | Eliassen, Cory H | 40 | 1200 | 26638
PR | 130 | 01/24/20 | 700 | Gauthier, Dillon R | 40 | 720 | 26643
PR | 130 | 01/24/20 | 736 | Sanders, Allen O | 2.5 | 135 | 26679
PR | 130 | 01/24/20 | 742 | Trower-Kelly, Fidel D | 24 | 504 | 26685
PR | 130 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I | 16 | 576 | 26696
PR | 130 | 01/31/20 | 847 | Cortes Sepulveda, Jose R | 8 | 272 | 26708
PR | 130 | 01/31/20 | 854 | Eliassen, Cory H | 40 | 1200 | 26715
PR | 130 | 01/31/20 | 860 | Gauthier, Dillon R | 40 | 720 | 26721
PR | 130 | 01/31/20 | 894 | Romero Garza, Jesus I | 40 | 920 | 26755
PR | 130 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I | 14 | 504 | 26775
PR | 130 | 02/07/20 | 38 | Cortes Sepulveda, Jose R | 14 | 476 | 26786
PR | 130 | 02/07/20 | 45 | Eliassen, Cory H | 40 | 1200 | 26793
PR | 130 | 02/07/20 | 50 | Gauthier, Dillon R | 24 | 432 | 26798
PR | 130 | 02/07/20 | 88 | Sanders, Allen O | 1 | 54 | 26836
PR | 130 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I | 17 | 612 | 26853
PR | 130 | 02/14/20 | 248 | Cortes Sepulveda, Jose R | 15 | 510 | 26864
PR | 130 | 02/14/20 | 255 | Eliassen, Cory H | 40 | 1200 | 26871
PR | 130 | 02/14/20 | 260 | Gauthier, Dillon R | 32 | 576 | 26876
PR | 130 | 02/14/20 | 304 | Trower-Kelly, Fidel D | 8 | 168 | 26920
PR | 130 | 02/21/20 | 454 | Balderas Ortiz, Ricardo I | 24 | 864 | 26931
PR | 130 | 02/21/20 | 465 | Cortes Sepulveda, Jose R | 24 | 816 | 26942
PR | 130 | 02/21/20 | 471 | Eliassen, Cory H | 40 | 1200 | 26948
PR | 130 | 02/21/20 | 476 | Gauthier, Dillon R | 24 | 432 | 26953
PR | 130 | 02/21/20 | 514 | Sanders, Allen O | 1.5 | 81 | 26991
PR | 130 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I | 24 | 864 | 27010
PR | 130 | 02/28/20 | 693 | Cortes Sepulveda, Jose R | 8 | 272 | 27021
PR | 130 | 02/28/20 | 700 | Eliassen, Cory H | 40 | 1200 | 27028
PR | 130 | 02/28/20 | 705 | Gauthier, Dillon R | 8 | 144 | 27033
PR | 130 | 02/28/20 | 743 | Sanders, Allen O | 7.5 | 405 | 27071
PR | 130 | 03/06/20 | 63 | Eliassen, Cory H | 21 | 630 | 27107
PR | 130 | 03/06/20 | 111 | Trower-Kelly, Fidel D | 21.5 | 451.5 | 27155
PR | 130 | 03/13/20 | 306 | Amaya Gonzalez, Edilberto A | 6 | 216 | 27166
PR | 130 | 03/13/20 | 309 | Balderas Ortiz, Ricardo I | 16 | 576 | 27169
PR | 130 | 03/13/20 | 319 | Cortes Mendiola, Victor H | 6 | 300 | 27179
PR | 130 | 03/13/20 | 320 | Cortes Sepulveda, Jose R | 16 | 544 | 27180
PR | 130 | 03/13/20 | 327 | Eliassen, Cory H | 24 | 720 | 27187
PR | 130 | 03/13/20 | 369 | Sanders, Allen O | 1 | 54 | 27230
PR | 130 | 03/13/20 | 375 | Trower-Kelly, Fidel D | 16 | 336 | 27236
PR | 130 | 03/20/20 | 564 | Amaya Gonzalez, Edilberto A | 11 | 396 | 27244
PR | 130 | 03/20/20 | 577 | Cortes Mendiola, Victor H | 11 | 550 | 27257
PR | 130 | 03/20/20 | 578 | Cortes Sepulveda, Jose R | 8 | 272 | 27258
PR | 130 | 03/20/20 | 585 | Eliassen, Cory H | 22 | 660 | 27265
PR | 130 | 03/20/20 | 627 | Sanders, Allen O | 1 | 54 | 27307
PR | 130 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I | 8 | 288 | 27326
PR | 130 | 03/26/20 | 760 | Cortes Mendiola, Victor H | 6 | 300 | 27336
PR | 130 | 03/26/20 | 761 | Cortes Sepulveda, Jose R | 8 | 272 | 27337
PR | 130 | 03/26/20 | 806 | Sanders, Allen O | 1 | 54 | 27382
PR | 130 | 05/01/20 | 64 | Sanders, Allen O | 3 | 162 | 27691
PR | 130 | 05/15/20 | 328 | Eliassen, Cory H | 2.5 | 75 | 27806
PR | 130 | 06/05/20 | 31 | Eliassen, Cory H | 6 | 180 | 28021
PR | 130 | 06/26/20 | 541 | Hubbard, Robert W | 2 | 108 | 28223
PR | 140 | 03/15/19 | 502 | Cortes Mendiola, Victor H | 3 | 129 | 23064
PR | 140 | 07/05/19 | 20 | Cortes Mendiola, Victor H | 2 | 92 | 24267
PR | 140 | 07/12/19 | 290 | Cortes Mendiola, Victor H | 16 | 736 | 24342
PR | 140 | 07/12/19 | 291 | Cortes Sepulveda, Jose R | 32 | 960 | 24343
PR | 140 | 07/12/19 | 330 | Rivera, Eli P | 32 | 960 | 24382
PR | 140 | 07/19/19 | 520 | Cortes Mendiola, Victor H | 12 | 552 | 24419
PR | 140 | 07/19/19 | 521 | Cortes Sepulveda, Jose R | 40 | 1200 | 24420
PR | 140 | 07/19/19 | 560 | Rivera, Eli P | 40 | 1200 | 24459
PR | 140 | 07/26/19 | 625 | Cortes Sepulveda, Jose R | 40 | 1200 | 24574
PR | 140 | 07/26/19 | 663 | Rivera, Eli P | 40 | 1200 | 24612
PR | 140 | 08/02/19 | 38 | Hubbard, Robert W | 3 | 150 | 24669
PR | 140 | 08/23/19 | 812 | Cortes Sepulveda, Jose R | 8 | 240 | 24870
PR | 140 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R | 24 | 720 | 24945
PR | 140 | 08/30/19 | 1026 | Hubbard, Robert W | 1 | 50 | 24968
PR | 140 | 08/30/19 | 1043 | Rivera, Eli P | 24 | 720 | 24985
PR | 140 | 09/06/19 | 23 | Cortes Mendiola, Victor H | 2 | 92 | 25021
PR | 140 | 09/06/19 | 24 | Cortes Sepulveda, Jose R | 8 | 240 | 25022
PR | 140 | 09/06/19 | 64 | Rivera, Eli P | 8 | 240 | 25062
PR | 140 | 09/27/19 | 640 | Cortes Mendiola, Victor H | 1 | 46 | 25245
PR | 140 | 10/04/19 | 16 | Cortes Mendiola, Victor H | 2 | 92 | 25323
PR | 140 | 10/11/19 | 265 | Benites Portillo, Marvin E | 8 | 216 | 25398
PR | 140 | 10/11/19 | 272 | Cortes Sepulveda, Jose R | 8 | 240 | 25406
PR | 140 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I | 8 | 288 | 26543
PR | 140 | 01/17/20 | 555 | Cortes Sepulveda, Jose R | 8 | 272 | 26554
PR | 140 | 01/24/20 | 688 | Cortes Sepulveda, Jose R | 8 | 272 | 26631
PR | 140 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I | 4 | 144 | 26696
PR | 140 | 01/31/20 | 847 | Cortes Sepulveda, Jose R | 4 | 136 | 26708
PR | 140 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I | 2 | 72 | 26775
PR | 140 | 02/07/20 | 38 | Cortes Sepulveda, Jose R | 2 | 68 | 26786
PR | 140 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I | 7 | 252 | 26853
PR | 140 | 02/14/20 | 248 | Cortes Sepulveda, Jose R | 9 | 306 | 26864
PR | 140 | 02/21/20 | 486 | Hubbard, Robert W | 3 | 162 | 26963
PR | 140 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I | 8 | 288 | 27010
PR | 140 | 02/28/20 | 716 | Hubbard, Robert W | 7.5 | 405 | 27044
PR | 140 | 04/24/20 | 410 | Sanders, Allen O | 1 | 54 | 27614
PR | 141 | 03/29/19 | 927 | Cortes Mendiola, Victor H | 2 | 129 | 23211
PR | 141 | 03/29/19 | 927 | Cortes Mendiola, Victor H | 2 | 86 | 23211
PR | 141 | 03/29/19 | 928 | Cortes Sepulveda, Jose R | 4 | 156 | 23212
PR | 141 | 03/29/19 | 928 | Cortes Sepulveda, Jose R | 16 | 416 | 23212
PR | 141 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I | 9 | 261 | 23275
PR | 141 | 04/05/19 | 89 | Cortes Mendiola, Victor H | 1 | 64.5 | 23283
PR | 141 | 04/05/19 | 89 | Cortes Mendiola, Victor H | 1 | 43 | 23283
PR | 141 | 04/12/19 | 325 | Balderas Ortiz, Ricardo I | 40 | 1160 | 23349
PR | 141 | 04/12/19 | 333 | Cortes Mendiola, Victor H | 4 | 184 | 23357
PR | 141 | 04/12/19 | 334 | Cortes Sepulveda, Jose R | 1 | 39 | 23358
PR | 141 | 04/12/19 | 334 | Cortes Sepulveda, Jose R | 40 | 1040 | 23358
PR | 141 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I | 24 | 696 | 23423
PR | 141 | 04/19/19 | 531 | Cortes Sepulveda, Jose R | 40 | 1040 | 23432
PR | 141 | 04/19/19 | 561 | Lovo, German G | 8 | 200 | 23462
PR | 141 | 04/26/19 | 750 | Cortes Mendiola, Victor H | 9 | 414 | 23507
PR | 141 | 04/26/19 | 751 | Cortes Sepulveda, Jose R | 6 | 270 | 23508
PR | 141 | 04/26/19 | 751 | Cortes Sepulveda, Jose R | 40 | 1200 | 23508
PR | 141 | 04/26/19 | 762 | Galdamez, Dagoberto A | 24 | 720 | 23519
PR | 141 | 04/26/19 | 791 | Rivera, Eli P | 24 | 720 | 23548
PR | 141 | 05/03/19 | 18 | Cortes Sepulveda, Jose R | 40 | 1200 | 23580
PR | 141 | 05/03/19 | 30 | Galdamez, Dagoberto A | 40 | 1200 | 23592
PR | 141 | 05/03/19 | 49 | Lovo, German G | 40 | 1080 | 23611
PR | 141 | 05/03/19 | 60 | Rivera, Eli P | 5 | 225 | 23622
PR | 141 | 05/03/19 | 60 | Rivera, Eli P | 40 | 1200 | 23622
PR | 141 | 05/10/19 | 170 | Cortes Mendiola, Victor H | 3 | 138 | 23654
PR | 141 | 05/10/19 | 171 | Cortes Sepulveda, Jose R | 16 | 480 | 23655
PR | 141 | 05/10/19 | 183 | Galdamez, Dagoberto A | 40 | 1200 | 23667
PR | 141 | 05/10/19 | 213 | Rivera, Eli P | 32 | 960 | 23697
PR | 141 | 05/17/19 | 402 | Cortes Mendiola, Victor H | 5 | 230 | 23733
PR | 141 | 05/17/19 | 415 | Galdamez, Dagoberto A | 24 | 720 | 23746
PR | 141 | 05/17/19 | 441 | Portillo Soriano, Walter A | 8 | 176 | 23772
PR | 141 | 05/17/19 | 445 | Rivera, Eli P | 40 | 1200 | 23776
PR | 141 | 05/17/19 | 454 | Sorto Regalado, Milton J | 16 | 256 | 23785
PR | 141 | 05/24/19 | 614 | Cortes Mendiola, Victor H | 7 | 322 | 23809
PR | 141 | 05/24/19 | 615 | Cortes Sepulveda, Jose R | 6 | 270 | 23810
PR | 141 | 05/24/19 | 615 | Cortes Sepulveda, Jose R | 40 | 1200 | 23810
PR | 141 | 05/24/19 | 653 | Portillo Soriano, Walter A | 6 | 198 | 23848
PR | 141 | 05/24/19 | 653 | Portillo Soriano, Walter A | 40 | 880 | 23848
PR | 141 | 05/24/19 | 657 | Rivera, Eli P | 6 | 270 | 23852
PR | 141 | 05/24/19 | 657 | Rivera, Eli P | 40 | 1200 | 23852
PR | 141 | 05/31/19 | 888 | Cortes Mendiola, Victor H | 4 | 184 | 23888
PR | 141 | 05/31/19 | 901 | Galdamez, Dagoberto A | 3 | 90 | 23901
PR | 141 | 05/31/19 | 927 | Portillo Soriano, Walter A | 16 | 352 | 23927
PR | 141 | 05/31/19 | 931 | Rivera, Eli P | 32 | 960 | 23931
PR | 141 | 06/07/19 | 190 | Cortes Mendiola, Victor H | 10 | 460 | 23965
PR | 141 | 06/07/19 | 191 | Cortes Sepulveda, Jose R | 40 | 1200 | 23966
PR | 141 | 06/07/19 | 232 | Rivera, Eli P | 40 | 1200 | 24007
PR | 141 | 06/14/19 | 461 | Cortes Sepulveda, Jose R | 40 | 1200 | 24042
PR | 141 | 06/14/19 | 469 | Eliassen, Cory H | 6 | 243 | 24050
PR | 141 | 06/14/19 | 482 | Hubbard, Justin A | 6 | 156 | 24063
PR | 141 | 06/14/19 | 490 | Lovo, German G | 24 | 648 | 24071
PR | 141 | 06/14/19 | 501 | Rivera, Eli P | 40 | 1200 | 24082
PR | 141 | 06/14/19 | 503 | Roberts, Lake A | 5 | 150 | 24084
PR | 141 | 06/21/19 | 630 | Cortes Mendiola, Victor H | 10 | 460 | 24116
PR | 141 | 06/21/19 | 631 | Cortes Sepulveda, Jose R | 40 | 1200 | 24117
PR | 141 | 06/21/19 | 661 | Lovo, German G | 30 | 810 | 24147
PR | 141 | 06/21/19 | 672 | Rivera, Eli P | 30 | 900 | 24158
PR | 141 | 06/28/19 | 848 | Cortes Mendiola, Victor H | 5 | 230 | 24192
PR | 141 | 06/28/19 | 849 | Cortes Sepulveda, Jose R | 24 | 720 | 24193
PR | 141 | 06/28/19 | 889 | Rivera, Eli P | 40 | 1200 | 24233
PR | 141 | 07/05/19 | 20 | Cortes Mendiola, Victor H | 6 | 276 | 24267
PR | 141 | 07/05/19 | 61 | Rivera, Eli P | 40 | 1200 | 24309
PR | 141 | 07/19/19 | 520 | Cortes Mendiola, Victor H | 4 | 184 | 24419
PR | 141 | 08/09/19 | 266 | Chevez, Herson G | 8 | 184 | 24719
PR | 141 | 08/09/19 | 268 | Cortes Mendiola, Victor H | 10 | 460 | 24721
PR | 141 | 08/09/19 | 269 | Cortes Sepulveda, Jose R | 8 | 240 | 24722
PR | 141 | 08/09/19 | 279 | Galdamez, Dagoberto A | 8 | 240 | 24732
PR | 141 | 08/09/19 | 297 | Lovo, German G | 8 | 216 | 24750
PR | 141 | 08/09/19 | 298 | Lucas Tzintzun, Rafael | 8 | 168 | 24751
PR | 141 | 08/09/19 | 308 | Rivera, Eli P | 8 | 240 | 24761
PR | 141 | 08/09/19 | 317 | Sorto Regalado, Milton J | 8 | 128 | 24770
PR | 141 | 08/16/19 | 604 | Lovo, German G | 16 | 432 | 24823
PR | 141 | 08/16/19 | 605 | Lucas Tzintzun, Rafael | 16 | 336 | 24824
PR | 141 | 08/16/19 | 611 | Portillo Soriano, Walter A | 16 | 352 | 24830
PR | 141 | 08/16/19 | 615 | Rivera, Eli P | 16 | 480 | 24834
PR | 141 | 08/16/19 | 624 | Sorto Regalado, Milton J | 16 | 256 | 24843
PR | 141 | 08/23/19 | 841 | Lovo, German G | 8 | 216 | 24899
PR | 141 | 09/06/19 | 60 | Portillo Soriano, Walter A | 16 | 352 | 25058
PR | 141 | 09/06/19 | 73 | Sorto Regalado, Milton J | 16 | 256 | 25071
PR | 141 | 09/27/19 | 680 | Portillo Soriano, Walter A | 16 | 352 | 25285
PR | 141 | 09/27/19 | 684 | Rivera, Eli P | 16 | 480 | 25289
PR | 141 | 10/04/19 | 17 | Cortes Sepulveda, Jose R | 16 | 480 | 25324
PR | 141 | 10/18/19 | 489 | Hubbard, Robert W | 2 | 100 | 25506
PR | 141 | 11/01/19 | 67 | Sepulveda Gonzalez, Alfredo | 8 | 312 | 25684
PR | 141 | 12/13/19 | 426 | Hubbard, Robert W | 1 | 54 | 26191
PR | 141 | 01/10/20 | 313 | Hubbard, Robert W | 6.5 | 351 | 26500
PR | 141 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I | 16 | 576 | 26543
PR | 141 | 01/17/20 | 555 | Cortes Sepulveda, Jose R | 8 | 272 | 26554
PR | 141 | 02/21/20 | 486 | Hubbard, Robert W | 4 | 216 | 26963
PR | 142 | 01/18/19 | 499 | Hubbard, Robert W | 2 | 98 | 22520
PR | 142 | 03/15/19 | 525 | Hubbard, Robert W | 2 | 98 | 23087
PR | 142 | 04/26/19 | 774 | Hubbard, Robert W | 2 | 100 | 23531
PR | 142 | 05/03/19 | 42 | Hubbard, Robert W | 1.5 | 112.5 | 23604
PR | 142 | 05/10/19 | 195 | Hubbard, Robert W | 6 | 300 | 23679
PR | 142 | 05/17/19 | 427 | Hubbard, Robert W | 2 | 100 | 23758
PR | 142 | 05/24/19 | 639 | Hubbard, Robert W | 2 | 100 | 23834
PR | 142 | 09/06/19 | 47 | Hubbard, Robert W | 6 | 300 | 25045
PR | 142 | 09/06/19 | 71 | Sepulveda Gonzalez, Alfredo | 13 | 455 | 25069
PR | 142 | 09/13/19 | 271 | Hubbard, Robert W | 10 | 500 | 25120
PR | 142 | 09/13/19 | 277 | Lucas Tzintzun, Rafael | 24 | 504 | 25126
PR | 142 | 09/13/19 | 294 | Sepulveda Gonzalez, Alfredo | 25 | 875 | 25143
PR | 142 | 09/20/19 | 484 | Cortes Mendiola, Victor H | 1 | 46 | 25170
PR | 142 | 09/20/19 | 509 | Hubbard, Robert W | 8 | 400 | 25195
PR | 142 | 09/20/19 | 515 | Lucas Tzintzun, Rafael | 40 | 840 | 25201
PR | 142 | 09/20/19 | 532 | Sepulveda Gonzalez, Alfredo | 35 | 1225 | 25218
PR | 142 | 09/27/19 | 640 | Cortes Mendiola, Victor H | 1 | 46 | 25245
PR | 142 | 09/27/19 | 674 | Lucas Tzintzun, Rafael | 32 | 672 | 25279
PR | 142 | 09/27/19 | 691 | Sepulveda Gonzalez, Alfredo | 32 | 1120 | 25296
PR | 142 | 10/04/19 | 16 | Cortes Mendiola, Victor H | 4 | 184 | 25323
PR | 142 | 10/04/19 | 41 | Hubbard, Robert W | 5 | 250 | 25348
PR | 142 | 10/04/19 | 49 | Lucas Tzintzun, Rafael | 40 | 840 | 25356
PR | 142 | 10/04/19 | 67 | Sepulveda Gonzalez, Alfredo | 32 | 1120 | 25374
PR | 142 | 10/11/19 | 271 | Cortes Mendiola, Victor H | 2 | 92 | 25405
PR | 142 | 10/11/19 | 296 | Hubbard, Robert W | 2 | 100 | 25430
PR | 142 | 10/11/19 | 304 | Lucas Tzintzun, Rafael | 40 | 840 | 25438
PR | 142 | 10/11/19 | 322 | Sepulveda Gonzalez, Alfredo | 40 | 1400 | 25456
PR | 142 | 10/18/19 | 465 | Cortes Mendiola, Victor H | 4 | 184 | 25481
PR | 142 | 10/18/19 | 497 | Lucas Tzintzun, Rafael | 13 | 273 | 25514
PR | 142 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo | 24 | 840 | 25532
PR | 142 | 11/01/19 | 16 | Cortes Mendiola, Victor H | 16 | 800 | 25633
PR | 142 | 11/01/19 | 17 | Cortes Sepulveda, Jose R | 16 | 544 | 25634
PR | 142 | 11/08/19 | 190 | Cortes Mendiola, Victor H | 3 | 150 | 25709
PR | 142 | 01/03/20 | 40 | Hubbard, Robert W | 2.5 | 135 | 26423
PR | 142 | 01/10/20 | 313 | Hubbard, Robert W | 2 | 108 | 26500
PR | 142 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I | 2 | 72 | 26543
PR | 142 | 01/17/20 | 555 | Cortes Sepulveda, Jose R | 2 | 68 | 26554
PR | 142 | 01/24/20 | 711 | Hubbard, Robert W | 5 | 270 | 26654
PR | 142 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I | 4 | 144 | 26696
PR | 142 | 01/31/20 | 847 | Cortes Sepulveda, Jose R | 4 | 136 | 26708
PR | 142 | 03/06/20 | 78 | Hubbard, Robert W | 10 | 540 | 27122
PR | 142 | 03/13/20 | 342 | Hubbard, Robert W | 9 | 486 | 27203
PR | 142 | 04/24/20 | 410 | Sanders, Allen O | 1 | 54 | 27614
PR | 143 | 06/21/19 | 672 | Rivera, Eli P | 2 | 60 | 24158
PR | 143 | 09/27/19 | 640 | Cortes Mendiola, Victor H | 1 | 46 | 25245
AP | 210 | 02/25/18 | 350 | Rosen Supply Kirkland |  | 56.28 | 4247736-00
GL | 210 | 07/16/18 | 394 | Req 4472 |  | 143.58
GL | 210 | 07/23/18 | 563 | Req 5312 |  | 51.1
GL | 210 | 08/10/18 | 330 | Req 4582 |  | 30.12
AP | 210 | 08/13/18 | 404 | Rosen Supply Kirkland |  | 1974 | 4253134-00
AP | 210 | 08/13/18 | 405 | Rosen Supply Kirkland |  | 614.5 | 4253436-00
AP | 210 | 08/13/18 | 406 | Rosen Supply Kirkland |  | 421.3 | 4253438-00
AP | 210 | 08/13/18 | 408 | Rosen Supply Kirkland |  | 75 | 4254265-00
AP | 210 | 08/13/18 | 429 | Rosen Supply Kirkland |  | 577.37 | 4253436-01
AP | 210 | 08/14/18 | 431 | Rosen Supply Kirkland |  | 409.1 | 4253438-01
AP | 210 | 08/21/18 | 608 | Rosen Supply Kirkland |  | 698.3 | 4254963-00
AP | 210 | 08/22/18 | 720 | Rosen Supply Kirkland |  | 1692 | 4253134-01
AP | 210 | 08/22/18 | 723 | Rosen Supply Kirkland |  | 254 | 4255092-00
AP | 210 | 08/22/18 | 724 | Rosen Supply Kirkland |  | 20.4 | 4255093-00
AP | 210 | 10/22/18 | 614 | Rosen Supply Kirkland |  | 1297.98 | 4257746-00
AP | 210 | 04/15/19 | 486 | Keller Supply Company |  | 1.81 | S012853701.001
GL | 211 | 07/16/18 | 384 | Req 5280 |  | 617.6
GL | 211 | 08/10/18 | 376 | Req 4530 |  | 189.66
GL | 211 | 10/22/18 | 566 | Req 4728 |  | 162.3
GL | 211 | 11/09/18 | 314 | Req 4779 |  | 141.62
GL | 211 | 11/28/18 | 794 | Req 5551 |  | 512.23
AP | 211 | 12/17/18 | 430 | Rosen Supply Kirkland |  | 1011.56 | 4259888-00
GL | 211 | 12/21/18 | 627 | Req 5609 |  | 303
GL | 211 | 01/30/19 | 872 | Req 5002 |  | 583.84
AP | 211 | 02/16/19 | 489 | Rosen Supply Kirkland |  | 5284.3 | 4262296-00
AP | 211 | 02/22/19 | 680 | Rosen Supply Kirkland |  | 438.68 | 4262838-00
AP | 211 | 02/22/19 | 686 | Rosen Supply Kirkland |  | 4091.39 | 4263009-00
AP | 211 | 02/27/19 | 755 | Rosen Supply Kirkland |  | 173.7 | 4263387-00
GL | 211 | 03/04/19 | 174 | Req 5718 |  | 536.4
GL | 211 | 03/08/19 | 371 | Req 5781 |  | 436.45
AP | 211 | 03/22/19 | 792 | Rosen Supply Kirkland |  | 1165.6 | 4264207-00
GL | 211 | 03/25/19 | 821 | Req 5096 |  | 226.2
AP | 211 | 04/03/19 | 74 | Rosen Supply Kirkland |  | 933.74 | 4264721-00
GL | 211 | 04/12/19 | 424 | Req 5885 |  | 66
GL | 211 | 05/13/19 | 305 | Req 5185 |  | 322
GL | 211 | 05/30/19 | 834 | Req 5991 |  | 279
GL | 211 | 06/05/19 | 157 | Req 6009 |  | 220.7
AP | 211 | 06/13/19 | 541 | Rosen Supply Kirkland |  | 224.39 | 4268259-00
AP | 211 | 06/18/19 | 599 | Rosen Supply Kirkland |  | 1002.59 | 4268569-00
GL | 211 | 06/26/19 | 830 | Req 6053 |  | 471.06
GL | 211 | 07/09/19 | 129 | Req 6093 |  | 268.91
AP | 211 | 07/30/19 | 708 | Rosen Supply Kirkland |  | 62.27 | 4270016-00
GL | 211 | 08/08/19 | 212 | Req 6161 |  | 49.56
AP | 211 | 08/14/19 | 540 | Rosen Supply Kirkland |  | -15.72 | 4270833-00
GL | 211 | 08/20/19 | 722 | Req 6229 |  | 365.69
GL | 211 | 09/16/19 | 364 | Req 6331 |  | 96.15
AP | 211 | 09/25/19 | 620 | Rosen Supply Kirkland |  | 426.94 | 4272249-00
AP | 211 | 09/27/19 | 725 | Rosen Supply Kirkland |  | 947.17 | 4272531-00
AP | 211 | 09/30/19 | 757 | Rosen Supply Kirkland |  | 19.2 | 4272249-02
AP | 211 | 11/06/19 | 171 | Rosen Supply Kirkland |  | 114.71 | 4273391-00
GL | 211 | 11/08/19 | 284 | Req 6489 |  | 462.82
AP | 211 | 11/12/19 | 362 | Rosen Supply Kirkland |  | 107.73 | 4273685-00
AP | 211 | 11/16/19 | 542 | Rosen Supply Kirkland |  | 16.58 | 4273391-01
GL | 211 | 11/19/19 | 565 | Req 6570 |  | 106.03
AP | 211 | 11/22/19 | 725 | Rosen Supply Kirkland |  | 37.59 | 4274624-00
GL | 211 | 12/06/19 | 147 | Req 6633 |  | 2.3
GL | 211 | 12/20/19 | 628 | Req 6673 |  | -9.51
GL | 211 | 12/27/19 | 803 | Req 6721 |  | 63.96
GL | 211 | 01/10/20 | 370 | Req 5733 |  | -35.35
GL | 211 | 04/29/20 | 441 | Req 6945 |  | 57.77
GL | 211 | 05/06/20 | 119 | Req 5987 |  | 13.57
GL | 211 | 05/06/20 | 123 | Req 6987 |  | -13.57
GL | 211 | 05/06/20 | 123 | Req 6987 |  | -13.57
GL | 212 | 08/28/18 | 938 | Req 4663 |  | -201
GL | 212 | 09/10/18 | 177 | Req 4698 |  | 162.5
GL | 212 | 09/25/18 | 632 | Req 5358 |  | 543.93
GL | 212 | 10/22/18 | 567 | Req 4727 |  | 1615.2
GL | 212 | 11/01/18 | 89 | Req 5511 |  | 338.09
GL | 212 | 11/16/18 | 562 | Req 4799 |  | 1750.57
GL | 212 | 11/28/18 | 793 | Req 5549 |  | 1012.41
GL | 212 | 11/30/18 | 983 | Req 5585 |  | 101.1
GL | 212 | 12/21/18 | 638 | Req 5598 |  | 5733.96
GL | 212 | 01/11/19 | 331 | Req 4860 |  | 327.9
GL | 212 | 01/11/19 | 348 | Req 5663 |  | -246
GL | 212 | 01/15/19 | 417 | Req 4891 |  | 121.32
GL | 212 | 03/04/19 | 172 | Req 5720 |  | 49.2
GL | 220 | 10/10/18 | 192 | Req 5446 |  | 71.97
GL | 220 | 12/21/18 | 628 | Req 5608 |  | 391.61
AP | 220 | 12/21/18 | 651 | Consolidated Supply Co. |  | 1713.32 | S9051387.001
GL | 220 | 01/15/19 | 418 | Req 4886 |  | 209.02
GL | 220 | 01/30/19 | 871 | Req 5003 |  | 7.18
GL | 220 | 03/04/19 | 173 | Req 5719 |  | 195.02
GL | 220 | 03/08/19 | 372 | Req 5782 |  | 307.92
AP | 220 | 03/12/19 | 430 | Rosen Supply Kirkland |  | 5533.95 | 4261931-00
AP | 220 | 03/13/19 | 477 | Rosen Supply Kirkland |  | 539.34 | 4263904-00
GL | 220 | 03/15/19 | 580 | Req 5821 |  | 309.58
GL | 220 | 03/25/19 | 819 | Req 5098 |  | 678.43
GL | 220 | 03/28/19 | 1063 | Req 5854 |  | 142.5
GL | 220 | 03/28/19 | 1071 | Req 5843 |  | 299.12
AP | 220 | 04/03/19 | 61 | Rosen Supply Kirkland |  | 25.2 | 4263904-01
AP | 220 | 04/05/19 | 166 | Consolidated Supply Co. |  | 5051.92 | S8833895.001
AP | 220 | 04/09/19 | 249 | Rosen Supply Kirkland |  | 1006.65 | 4265009-00
GL | 220 | 04/12/19 | 421 | Req 5884 |  | 99.16
GL | 220 | 04/12/19 | 423 | Req 5163 |  | 2923.82
AP | 220 | 04/15/19 | 468 | Consolidated Supply Co. |  | 5051.92 | S8834385.001
AP | 220 | 04/16/19 | 508 | Rosen Supply Kirkland |  | 3626.72 | 4253574-00
AP | 220 | 04/22/19 | 647 | Rosen Supply Kirkland |  | 96.21 | 4265476-00
AP | 220 | 04/23/19 | 659 | Rosen Supply Kirkland |  | 172.15 | 4265599-00
AP | 220 | 04/23/19 | 665 | Rosen Supply Kirkland |  | 23.22 | 4265476-01
AP | 220 | 04/23/19 | 676 | Rosen Supply Kirkland |  | 296.7 | 4265803-00
GL | 220 | 04/24/19 | 687 | Req 5908 |  | 695.81
AP | 220 | 04/30/19 | 930 | Consolidated Supply Co. |  | 7286.3 | S9216984.001
AP | 220 | 04/30/19 | 931 | Consolidated Supply Co. |  | 254.5 | S9216984.002
AP | 220 | 05/10/19 | 284 | Rosen Supply Kirkland |  | 948.71 | 4266154-00
GL | 220 | 05/13/19 | 292 | Req 5186 |  | 2604.59
AP | 220 | 05/14/19 | 342 | Rosen Supply Kirkland |  | 150.08 | 4266412-00
AP | 220 | 05/23/19 | 596 | Consolidated Supply Co. |  | 1642.59 | S9235053.001
AP | 220 | 05/28/19 | 723 | Rosen Supply Kirkland |  | 1455.11 | 4266672-00
AP | 220 | 05/28/19 | 745 | Rosen Supply Kirkland |  | 38.77 | 4266412-01
AP | 220 | 05/29/19 | 768 | Rosen Supply Kirkland |  | 218.35 | 4267267-00
GL | 220 | 05/30/19 | 831 | Req 5988 |  | 3145.45
GL | 220 | 05/30/19 | 835 | Req 5992 |  | 232.86
AP | 220 | 06/03/19 | 19 | Consolidated Supply Co. |  | 4426.2 | S9258309.001
GL | 220 | 06/05/19 | 160 | Req 6012 |  | 643.8
AP | 220 | 06/05/19 | 176 | Rosen Supply Kirkland |  | 544.2 | 4267319-00
AP | 220 | 06/06/19 | 263 | Rosen Supply Kirkland |  | 474.27 | 4267466-00
AP | 220 | 06/08/19 | 291 | Rosen Supply Kirkland |  | 495 | 4267553-00
AP | 220 | 06/08/19 | 314 | Rosen Supply Kirkland |  | 1476.89 | 4267966-00
AP | 220 | 06/11/19 | 372 | Rosen Supply Kirkland |  | 117.43 | 4267292-00
AP | 220 | 06/11/19 | 373 | Rosen Supply Kirkland |  | 20.37 | 4267292-001
AP | 220 | 06/21/19 | 715 | Rosen Supply Kirkland |  | 537.53 | 4268697-00
AP | 220 | 06/24/19 | 743 | Rosen Supply Kirkland |  | 507.95 | 4268799-00
GL | 220 | 06/26/19 | 807 | Req 6055 |  | 2325.37
GL | 220 | 07/09/19 | 128 | Req 6092 |  | 1276.34
GL | 220 | 07/09/19 | 132 | Req 6096 |  | 575.21
AP | 220 | 07/10/19 | 274 | Rosen Supply Kirkland |  | 67.72 | 4268697-01
AP | 220 | 07/10/19 | 376 | Consolidated Supply Co. |  | 384.11 | S009320662.001
AP | 220 | 07/15/19 | 388 | Rosen Supply Kirkland |  | 362.2 | 4269153-00
AP | 220 | 07/15/19 | 404 | Rosen Supply Kirkland |  | 887.61 | 4269287-00
AP | 220 | 07/16/19 | 441 | Rosen Supply Kirkland |  | 277.1 | 4269581-00
AP | 220 | 07/16/19 | 442 | Rosen Supply Kirkland |  | 16 | 4268697-03
AP | 220 | 07/17/19 | 489 | Rosen Supply Kirkland |  | 478.51 | 4269699-00
GL | 220 | 08/01/19 | 136 | Req 6154 |  | 940.84
GL | 220 | 08/01/19 | 139 | Req 6153 |  | 1832.77
AP | 220 | 08/06/19 | 153 | Ferguson Enterprises, Inc. #3007 |  | 78.8 | 7396087
AP | 220 | 08/07/19 | 186 | Rosen Supply Kirkland |  | 93.2 | 4269581-01
GL | 220 | 08/08/19 | 210 | Req 6159 |  | 685.3
AP | 220 | 08/10/19 | 440 | Rosen Supply Kirkland |  | 8.64 | 4269699-01
AP | 220 | 08/10/19 | 442 | Rosen Supply Kirkland |  | 408.01 | 4270287-00
AP | 220 | 08/10/19 | 452 | Rosen Supply Kirkland |  | 99.9 | 4270407-00
AP | 220 | 08/12/19 | 471 | Rosen Supply Kirkland |  | 215.87 | 4270541-00
AP | 220 | 08/13/19 | 525 | Ferguson Enterprises, Inc. #3007 |  | 429 | 7420814
AP | 220 | 08/14/19 | 538 | Rosen Supply Kirkland |  | 785.26 | 4270638-00
AP | 220 | 08/14/19 | 541 | Rosen Supply Kirkland |  | 47.16 | 4270837-00
GL | 220 | 08/20/19 | 721 | Req 6231 |  | 232.65
GL | 220 | 08/20/19 | 726 | Req 6226 |  | 1307.18
AP | 220 | 08/28/19 | 966 | Rosen Supply Kirkland |  | 410 | 4270963-00
AP | 220 | 08/28/19 | 983 | Rosen Supply Kirkland |  | 445.2 | 4271455-00
AP | 220 | 08/30/19 | 1098 | Rosen Supply Kirkland |  | 48.88 | 4271779-00
AP | 220 | 08/31/19 | 1107 | Rosen Supply Kirkland |  | 7.57 | 4271455-01
AP | 220 | 09/01/19 | 393 | Rosen Supply Kirkland |  | -47.16 | 4270837-00A
AP | 220 | 09/01/19 | 394 | Rosen Supply Kirkland |  | -47.16 | 4270837-00C
AP | 220 | 09/10/19 | 197 | Capital One Credit Card |  | 46.76 | 082319BH
GL | 220 | 09/16/19 | 362 | Req 6329 |  | 1064.71
AP | 220 | 09/20/19 | 577 | Manor Hardware & Construction Supply |  | 87 | 997028-00
AP | 220 | 10/01/19 | 224 | Capital One Credit Card |  | 92.26 | 092319J
GL | 220 | 10/03/19 | 92 | Victor Cortes Mendiola |  | 55.78
GL | 220 | 10/07/19 | 103 | Req 6332 |  | 160.7
AP | 220 | 10/15/19 | 422 | Rosen Supply Kirkland |  | 9.72 | 4273010-00
GL | 220 | 10/16/19 | 439 |  |  | 80.04
AP | 220 | 10/23/19 | 580 | Consolidated Supply Co. |  | 98.26 | S009460460.001
GL | 220 | 11/08/19 | 286 | Req 6483 |  | 46.53
GL | 220 | 11/08/19 | 289 | Req 6482 |  | 1160.47
AP | 220 | 11/16/19 | 543 | Rosen Supply Kirkland |  | 42 | 4274049-00
GL | 220 | 11/19/19 | 566 | Req 6571 |  | 101.93
AP | 220 | 11/22/19 | 707 | Rosen Supply Kirkland |  | 141.95 | 4274549-00
GL | 220 | 12/20/19 | 629 | Req 6672 |  | -2.95
GL | 220 | 12/27/19 | 802 | Req 6720 |  | 53.41
AP | 220 | 12/31/19 | 861 | Rosen Supply Kirkland |  | 30 | 4276089-00
AP | 220 | 12/31/19 | 870 | Rosen Supply Kirkland |  | 17 | 4276312-00
AP | 220 | 01/03/20 | 93 | Rosen Supply Kirkland |  | 21 | 4276306-00
GL | 220 | 01/10/20 | 369 | Req 5734 |  | -86.58
AP | 220 | 01/29/20 | 819 | Consolidated Supply Co. |  | 33.66 | S009611084.002
GL | 220 | 01/31/20 | 949 | Req 5780 |  | 29.55
GL | 220 | 02/24/20 | 538 | Req 6818 |  | 39.49
GL | 220 | 03/10/20 | 251 | Req 6889 |  | 33.89
GL | 220 | 04/29/20 | 444 | Req 6948 |  | 2.79
GL | 220 | 05/06/20 | 121 | Req 6986 |  | -43.64
GL | 220 | 05/15/20 | 400 | Req 7014 |  | -36.09
AP | 230 | 02/25/18 | 345 | Rosen Supply Kirkland |  | 98.47 | 4247691-00
AP | 230 | 04/30/18 | 813 | Capital One Credit Card |  | 1098.35 | 041018
AP | 230 | 06/19/18 | 630 | Ferguson Enterprises, Inc.$Bell Parkside |  | 551.04 | 6271951
AP | 230 | 07/09/18 | 138 | Old Castle Infrastructure, Inc. |  | 3450 | 10220420
AP | 230 | 07/23/18 | 626 | Quality Concrete Products, Inc. $32 |  | 4073 | 16803
GL | 230 | 08/10/18 | 331 | Req 4581 |  | 1450.32
GL | 230 | 08/10/18 | 375 | Req 4531 |  | 309.22
GL | 230 | 09/10/18 | 176 | Req 4699 |  | 209.7
GL | 230 | 09/25/18 | 631 | Req 5359 |  | 83.88
AP | 230 | 10/05/18 | 121 | California Hydronics Corp |  | 465 | 2108119
GL | 230 | 10/10/18 | 193 | Req 5445 |  | 219.91
GL | 230 | 10/22/18 | 568 | Req 4726 |  | 1132.79
GL | 230 | 11/09/18 | 313 | Req 4778 |  | 336.55
GL | 230 | 11/16/18 | 561 | Req 4800 |  | 52.15
GL | 230 | 11/28/18 | 792 | Req 5550 |  | 85.69
GL | 230 | 12/21/18 | 623 | Req 5613 |  | 316.36
GL | 230 | 12/21/18 | 626 | Req 5610 |  | 312.9
AP | 230 | 01/14/19 | 394 | Rosen Supply Kirkland |  | 85.69 | 4260355-00
AP | 230 | 01/29/19 | 843 | California Hydronics Corp |  | 3040 | SIN005654
AP | 230 | 01/30/19 | 903 | Mechanical Sales, Inc. |  | 290.58 | 700000
AP | 230 | 02/18/19 | 500 | Rosen Supply Kirkland |  | 23275 | 4258270-00
AP | 230 | 02/19/19 | 537 | Keller Supply Company |  | 786.09 | S012595118.001
AP | 230 | 03/19/19 | 663 | Rosen Supply Kirkland |  | 2178.9 | 4260158-00
AP | 230 | 03/19/19 | 664 | Rosen Supply Kirkland |  | 4720.95 | 4261059-00
AP | 230 | 03/22/19 | 793 | Rosen Supply Kirkland |  | 21062.7 | 4260157-00
GL | 230 | 03/25/19 | 820 | Req 5097 |  | 11.58
GL | 230 | 03/28/19 | 1072 | Req 5842 |  | 2265.1
AP | 230 | 04/09/19 | 235 | Old Castle Infrastructure, Inc. |  | 1416 | 11000084
GL | 230 | 04/12/19 | 422 | Req 5883 |  | 1955.34
AP | 230 | 04/15/19 | 485 | Ferguson Enterprises, Inc. #3007 |  | 162.31 | 7066515
AP | 230 | 04/23/19 | 658 | Rosen Supply Kirkland |  | 10531.35 | 4260166-00
GL | 230 | 04/24/19 | 689 | Req 5906 |  | 1134.4
AP | 230 | 04/30/19 | 878 | California Hydronics Corp |  | 3040 | SIN011466
AP | 230 | 05/01/19 | 476 | California Hydronics Corp |  | -3040 | SIN011466A
AP | 230 | 05/06/19 | 118 | Keller Supply Company |  | 3792.36 | S012899115.001
GL | 230 | 05/13/19 | 304 | Req 5187 |  | 819.52
AP | 230 | 05/13/19 | 327 | Rosen Supply Kirkland |  | 10168.2 | 4260155-00
AP | 230 | 05/13/19 | 328 | Rosen Supply Kirkland |  | 9441.9 | 4260161-00
AP | 230 | 05/29/19 | 808 | Mechanical Sales, Inc. |  | 23638 | 702342
GL | 230 | 05/30/19 | 836 | Req 5993 |  | 3138.88
GL | 230 | 06/05/19 | 159 | Req 6011 |  | 2496.2
AP | 230 | 06/08/19 | 292 | Rosen Supply Kirkland |  | 9441.9 | 4260154-00
AP | 230 | 06/17/19 | 563 | Consolidated Supply Co. |  | 2839.66 | S9274138.001
GL | 230 | 06/26/19 | 828 | Req 6056 |  | 3696.12
GL | 230 | 07/09/19 | 130 | Req 6094 |  | 2416.4
AP | 230 | 07/16/19 | 428 | Manor Hardware & Construction Supply |  | 305.76 | 983253-00
GL | 230 | 08/01/19 | 128 | Req 6157 |  | 1447
GL | 230 | 08/08/19 | 209 | Req 6158 |  | 871.9
GL | 230 | 08/20/19 | 723 | Req 6227 |  | 702.75
AP | 230 | 08/21/19 | 782 | Ferguson Enterprises, Inc. #3007 |  | 123.5 | 7451978
AP | 230 | 08/21/19 | 783 | Ferguson Enterprises, Inc. #3007 |  | 19 | 7451988
AP | 230 | 08/21/19 | 784 | Ferguson Enterprises, Inc. #3007 |  | 76 | 7454501
GL | 230 | 09/16/19 | 323 | Req 6328 |  | 947.16
AP | 230 | 09/19/19 | 554 | Consolidated Supply Co. |  | 175.14 | S009427962.001
AP | 230 | 10/07/19 | 145 | Mechanical Sales, Inc. |  | 250 | 704544
AP | 230 | 11/01/19 | 105 | Keller Supply Company |  | 23.03 | S013544954.001
AP | 230 | 11/01/19 | 106 | Keller Supply Company |  | 12679.64 | S013119117.001
AP | 230 | 11/01/19 | 732 | Keller Supply Company |  | -12679.64 | S013119117.001A
AP | 230 | 11/01/19 | 733 | Keller Supply Company |  | 12879.64 | S013119117.001B
GL | 230 | 11/06/19 | 161 | for Keller Inv S013463531.001 |  | 759.88
GL | 230 | 11/08/19 | 290 | Req 6484 |  | 376.67
GL | 230 | 11/08/19 | 293 | Req 6480 |  | 1457.63
GL | 230 | 11/08/19 | 294 | Req 6479 |  | 2528.75
GL | 230 | 11/12/19 | 350 | Req 6511 |  | -164.48
AP | 230 | 11/12/19 | 386 | Rosen Supply Kirkland |  | 15.27 | 4273784-00
AP | 230 | 11/16/19 | 540 | Rosen Supply Kirkland |  | 45.81 | 4273784-01
GL | 230 | 11/19/19 | 563 | Req 6568 |  | 2235.8
AP | 230 | 11/22/19 | 721 | Rosen Supply Kirkland |  | 2228.86 | 4274007-00
AP | 230 | 11/30/19 | 966 | Consolidated Supply Co. |  | 392.97 | S009499745.001
AP | 230 | 11/30/19 | 981 | Keller Supply Company |  | 12556.22 | S013119106.001
GL | 230 | 12/06/19 | 146 | Req 6632 |  | 34.56
GL | 230 | 12/06/19 | 156 | Req 6594 |  | 905.31
AP | 230 | 12/10/19 | 267 | Rosen Supply Kirkland |  | 653.82 | 4275149-00
AP | 230 | 12/12/19 | 500 | Keller Supply Company |  | 18772.41 | S012918866.001
AP | 230 | 12/12/19 | 501 | Keller Supply Company |  | 13128.51 | S013119084.001
AP | 230 | 12/12/19 | 502 | Keller Supply Company |  | 14599.12 | S013118978.001
AP | 230 | 12/12/19 | 503 | Keller Supply Company |  | 14092.61 | S013119015.001
GL | 230 | 12/20/19 | 643 | Req 6678 |  | 2644.55
GL | 230 | 12/27/19 | 800 | Req 6716 |  | 1103.18
GL | 230 | 12/27/19 | 804 | Req 6722 |  | 6.89
AP | 230 | 01/08/20 | 198 | Capital One Credit Card |  | 48.07 | 112019J
GL | 230 | 01/10/20 | 365 | Req 5738 |  | -399.44
AP | 230 | 01/13/20 | 509 | Keller Supply Company |  | 8056.91 | S013118817.001
AP | 230 | 01/29/20 | 818 | Consolidated Supply Co. |  | 686.11 | S9274138.002
GL | 230 | 01/31/20 | 948 | Req 5777 |  | 1808.32
AP | 230 | 02/07/20 | 129 | Keller Supply Company |  | 364.04 | S013590927.001
AP | 230 | 02/10/20 | 138 | Consolidated Supply Co. |  | -163.35 | S9274138.003
AP | 230 | 02/10/20 | 187 | Keller Supply Company |  | 6111.39 | S013118775.001
GL | 230 | 02/24/20 | 536 | Req 6815 |  | 2144.5
AP | 230 | 02/26/20 | 629 | Keller Supply Company |  | 1902.49 | S013887401.001
AP | 230 | 02/26/20 | 630 | Keller Supply Company |  | 42.53 | S013119015.002
AP | 230 | 02/26/20 | 631 | Keller Supply Company |  | 204.33 | S013829928.001
AP | 230 | 02/26/20 | 640 | Ferguson Enterprises, Inc. #3007 |  | 398.78 | 7980549
GL | 230 | 03/10/20 | 250 | Req 6890 |  | 30.21
AP | 230 | 03/11/20 | 300 | Keller Supply Company |  | -65.75 | S013829928.002
AP | 230 | 03/16/20 | 434 | Keller Supply Company |  | 142.14 | S014007336.001
AP | 230 | 03/16/20 | 435 | Keller Supply Company |  | 59 | S013996654.001
AP | 230 | 03/16/20 | 437 | Keller Supply Company |  | 490.13 | S013958105.001
AP | 230 | 03/18/20 | 549 | Rosen Supply Kirkland |  | 100 | 4279942-00
GL | 230 | 03/20/20 | 683 | Req 6932 |  | 344.85
AP | 230 | 03/24/20 | 729 | Keller Supply Company |  | 186.47 | S019358105.002
AP | 230 | 03/24/20 | 732 | Rosen Supply Kirkland |  | 640.98 | 1560701-00
AP | 230 | 03/27/20 | 888 | Keller Supply Company |  | 107.78 | S014044274.001
AP | 230 | 04/15/20 | 184 | Capital One Credit Card |  | 42.01 | 031620A1
GL | 230 | 04/29/20 | 442 | Req 6946 |  | 67.4
GL | 230 | 05/06/20 | 120 | Req 6985 |  | -98.67
GL | 230 | 05/06/20 | 122 | Req 6984 |  | -642.36
AP | 230 | 05/06/20 | 141 | Rosen Supply Kirkland |  | 266.46 | 4281196-00
AP | 230 | 05/06/20 | 149 | Rosen Supply Kirkland |  | 266.46 | 4281329-00
AP | 230 | 05/12/20 | 286 | Kele, Inc $ MI Controls |  | 73.26 | IMIS0807005875
GL | 230 | 05/15/20 | 403 | Req 7010 |  | -898.14
AP | 230 | 05/19/20 | 418 | Keller Supply Company |  | 373.19 | S014012258.001
AP | 230 | 06/08/20 | 110 | Capital One Credit Card |  | 16.88 | 042820A
AP | 240 | 05/28/19 | 732 | Rosen Supply Kirkland |  | 88.49 | 4266803-00
GL | 240 | 06/26/19 | 822 | Req 6028 |  | 116.68
AP | 240 | 07/16/19 | 457 | Consolidated Supply Co. |  | 4047.65 | S009319203.001
AP | 240 | 07/17/19 | 495 | Rosen Supply Kirkland |  | 266.03 | 4269889-00
GL | 240 | 08/01/19 | 138 | Req 6156 |  | 210.77
AP | 240 | 08/05/19 | 108 | Consolidated Supply Co. |  | 610.22 | S009319203.002
AP | 240 | 08/08/19 | 203 | Rosen Supply Kirkland |  | 122.9 | 4269889-01
GL | 240 | 08/08/19 | 213 | Req 6162 |  | 11.35
AP | 240 | 08/10/19 | 441 | Rosen Supply Kirkland |  | 108.17 | 4270185-00
GL | 240 | 09/16/19 | 363 | Req 6330 |  | 53.4
AP | 240 | 10/29/19 | 729 | Consolidated Supply Co. |  | 607.05 | S009468929.001
GL | 240 | 11/08/19 | 285 | Req 6488 |  | 37.65
GL | 240 | 11/11/19 | 309 | Req 6495 |  | -424.32
GL | 240 | 11/19/19 | 568 | Req 6573 |  | 442.43
AP | 240 | 11/20/19 | 590 | Rosen Supply Kirkland |  | 95.61 | 4273854-00
AP | 240 | 11/20/19 | 591 | Rosen Supply Kirkland |  | 4.75 | 4274109-00
GL | 240 | 11/30/19 | 951 | Req 6512 |  | -834.65
GL | 240 | 12/06/19 | 145 | Req 6631 |  | 6.11
AP | 240 | 12/12/19 | 499 | Keller Supply Company |  | 54.87 | S013644235.001
GL | 240 | 12/27/19 | 801 | Req 6719 |  | 105.39
GL | 240 | 01/31/20 | 950 | Req 6753 |  | 140.86
AP | 240 | 02/10/20 | 188 | Keller Supply Company |  | 31.57 | S013869114.001
GL | 240 | 02/24/20 | 537 | Req 6817 |  | 11.32
AP | 240 | 02/25/20 | 600 | Rosen Supply Kirkland |  | 187.45 | 4278622-00
AP | 240 | 02/28/20 | 778 | Ferguson Enterprises, Inc. #3007 |  | 207.9 | 8004167
AP | 240 | 02/28/20 | 779 | Ferguson Enterprises, Inc. #3007 |  | 182.21 | 8004167-1
AP | 240 | 02/29/20 | 806 | Rosen Supply Kirkland |  | 18.9 | 4279320-00
GL | 240 | 03/10/20 | 248 | Req 6888 |  | 36.18
AP | 240 | 03/25/20 | 492 | Capital One Credit Card |  | 14.59 | 022420BH
AP | 240 | 03/27/20 | 854 | Rosen Supply Kirkland |  | 49 | 4280512-00
GL | 240 | 04/29/20 | 445 | Req 6949 |  | 471.94
GL | 240 | 05/15/20 | 395 | Req 7011 |  | -199.51
GL | 241 | 12/21/18 | 624 | Req 5612 |  | 34.8
GL | 241 | 01/23/19 | 686 | Req 4981 |  | 123.6
GL | 241 | 03/25/19 | 818 | Req 5099 |  | 156.1
GL | 241 | 03/25/19 | 822 | Req 5095 |  | 103.48
GL | 241 | 03/28/19 | 1070 | Req 5844 |  | 96.14
AP | 241 | 04/15/19 | 466 | Consolidated Supply Co. |  | 4443.73 | S9186175.001
AP | 241 | 04/15/19 | 467 | Consolidated Supply Co. |  | 1081 | S9186175.002
GL | 241 | 04/24/19 | 688 | Req 5907 |  | 387.61
GL | 241 | 05/13/19 | 303 | Req 5188 |  | 947.57
AP | 241 | 05/17/19 | 473 | Consolidated Supply Co. |  | 8220.64 | S9227144.001
AP | 241 | 05/17/19 | 474 | Consolidated Supply Co. |  | 815.49 | S9227144.002
AP | 241 | 05/17/19 | 475 | Consolidated Supply Co. |  | 1607.22 | S9227144.003
AP | 241 | 05/23/19 | 595 | Consolidated Supply Co. |  | 607.2 | S9234747.001
AP | 241 | 05/23/19 | 597 | Consolidated Supply Co. |  | 406.27 | S9227144.004
AP | 241 | 05/23/19 | 599 | Consolidated Supply Co. |  | 9546.18 | S9252620.001
AP | 241 | 05/23/19 | 600 | Consolidated Supply Co. |  | 509 | S9252620.002
AP | 241 | 05/23/19 | 601 | Consolidated Supply Co. |  | 188.19 | S9252620.003
GL | 241 | 05/30/19 | 833 | Req 5990 |  | 458.84
AP | 241 | 06/03/19 | 18 | Consolidated Supply Co. |  | 1374.42 | S9227144.005
GL | 241 | 06/05/19 | 158 | Req 6010 |  | 135.63
AP | 241 | 06/17/19 | 561 | Consolidated Supply Co. |  | 3484.4 | S9284724.001
AP | 241 | 06/17/19 | 562 | Consolidated Supply Co. |  | 89.2 | S9289135.001
GL | 241 | 06/26/19 | 829 | Req 6054 |  | 1522.98
GL | 241 | 07/09/19 | 131 | Req 6095 |  | 200.8
GL | 241 | 08/01/19 | 137 | Req 6155 |  | 1352.16
AP | 241 | 08/06/19 | 170 | Ferguson Enterprises, Inc. #3007 |  | 429.38 | 7364965
AP | 241 | 08/06/19 | 171 | Ferguson Enterprises, Inc. #3007 |  | 1159.11 | 7364824
GL | 241 | 08/08/19 | 214 | Req 6163 |  | 28.29
AP | 241 | 08/12/19 | 470 | Rosen Supply Kirkland |  | 5152.8 | 4270527-00
AP | 241 | 08/14/19 | 539 | Rosen Supply Kirkland |  | 3280 | 4270530-00
GL | 241 | 08/20/19 | 724 | Req 6230 |  | 150.94
AP | 241 | 08/31/19 | 1106 | Rosen Supply Kirkland |  | 126 | 4270527-01
GL | 241 | 11/08/19 | 292 | Req 6481 |  | 395.81
GL | 241 | 11/19/19 | 567 | Req 6572 |  | 215.54
GL | 241 | 11/19/19 | 581 | Req 6582 |  | -1751.04
GL | 241 | 01/10/20 | 366 | Req 5737 |  | -269.09
GL | 241 | 01/10/20 | 367 | Req 5736 |  | -529.3
GL | 241 | 01/10/20 | 368 | Req 5735 |  | -3490.8
GL | 241 | 01/31/20 | 925 | Req 5776 |  | -221.91
GL | 241 | 02/24/20 | 535 | Req 6816 |  | 140.3
GL | 241 | 03/10/20 | 252 | Req 6891 |  | 37.27
GL | 241 | 04/29/20 | 443 | Req 6947 |  | 124.12
GL | 241 | 05/15/20 | 402 | Req 7012 |  | -24.94
GL | 241 | 05/31/20 | 694 | Req 7049 |  | 38.89
AP | 242 | 05/23/19 | 598 | Consolidated Supply Co. |  | 65.6 | S9243133.001
GL | 242 | 05/30/19 | 837 | Req 5994 |  | 10.07
AP | 242 | 06/12/19 | 424 | Ferguson Enterprises, Inc. #3007 |  | 11795.02 | 7263426
AP | 242 | 06/17/19 | 564 | Consolidated Supply Co. |  | 1553.06 | S927843.001
AP | 242 | 06/21/19 | 714 | Rosen Supply Kirkland |  | 2744.44 | 4267847-00
GL | 242 | 06/26/19 | 827 | Req 6057 |  | 95.18
GL | 242 | 08/08/19 | 211 | Req 6160 |  | 150.15
GL | 242 | 08/20/19 | 680 | Req 6269 |  | 1121.76
GL | 242 | 08/20/19 | 725 | Req 6228 |  | 57.44
GL | 242 | 09/16/19 | 366 | Req 6334 |  | 37.6
AP | 242 | 09/17/19 | 426 | Ferguson Enterprises, Inc. #3007 |  | 223.59 | 7534254
AP | 242 | 09/17/19 | 427 | Ferguson Enterprises, Inc. #3007 |  | 1873.14 | 7539098
AP | 242 | 09/17/19 | 428 | Ferguson Enterprises, Inc. #3007 |  | 1054.75 | 7539098-1
AP | 242 | 09/19/19 | 555 | Consolidated Supply Co. |  | 1038.28 | S009430234.001
AP | 242 | 09/30/19 | 745 | Core & Main LP $HD Supply Waterworks |  | 226.18 | L230551
GL | 242 | 10/07/19 | 99 | Req 6391 |  | 81.49
AP | 242 | 10/10/19 | 378 | Ferguson Enterprises, Inc. #3007 |  | 641.25 | 7554346
AP | 242 | 10/11/19 | 366 | Ferguson Enterprises, Inc. #3007 |  | 557.42 | 7539098-2
AP | 242 | 10/23/19 | 575 | Ferguson Enterprises, Inc. #3007 |  | 927.8 | 7583197
GL | 242 | 11/08/19 | 287 | Req 6487 |  | 96.02
GL | 242 | 11/08/19 | 288 | Req 6486 |  | 1179.63
GL | 242 | 11/08/19 | 291 | Req 6485 |  | 751.5
AP | 242 | 11/16/19 | 541 | Rosen Supply Kirkland |  | 91.5 | 4273857-00
GL | 242 | 11/19/19 | 564 | Req 6569 |  | 32.14
GL | 242 | 12/20/19 | 630 | Req 6671 |  | -478.28
GL | 242 | 12/20/19 | 631 | Req 6670 |  | -2389.33
AP | 242 | 01/08/20 | 265 | Rosen Supply Kirkland |  | 5.11 | 4277114-00
GL | 242 | 01/31/20 | 953 | Req 6752 |  | 34.92
AP | 242 | 02/14/20 | 332 | Rosen Supply Kirkland |  | 12.71 | 4276731-00
AP | 242 | 02/28/20 | 780 | Ferguson Enterprises, Inc. #3007 |  | 295.43 | 8004302
GL | 242 | 03/10/20 | 249 | Req 6887 |  | 670.09
GL | 242 | 05/15/20 | 401 | Req 7013 |  | -8.39
GL | 243 | 07/09/19 | 133 | Req 6097 |  | 45.64
GL | 243 | 09/16/19 | 365 | Req 6333 |  | 34.4
GL | 243 | 10/16/19 | 439 |  |  | -80.04
AP | 600 | 10/08/18 | 130 | MAD Concrete Cutting & Coring, Inc. |  | 900 | 8077
AP | 600 | 11/05/18 | 157 | MAD Concrete Cutting & Coring, Inc. |  | 1321.2 | 8092
AP | 600 | 11/07/18 | 168 | MAD Concrete Cutting & Coring, Inc. |  | -200 | 8092C
AP | 600 | 06/10/19 | 328 | MAD Concrete Cutting & Coring, Inc. |  | 2400 | 8212
AP | 600 | 02/25/20 | 591 | Mechanical Resource Services, Inc. |  | 2675 | 16788-5600
AP | 600 | 03/16/20 | 429 | Mechanical Resource Services, Inc. |  | 2675 | 16803-5600
AP | 601 | 04/30/18 | 831 | Franklin Engineering |  | 2584.75 | 6919
AP | 601 | 06/04/18 | 157 | Franklin Engineering |  | 1612.5 | 6944
AP | 601 | 06/22/18 | 788 | Franklin Engineering |  | 24042.25 | 6977
AP | 601 | 07/23/18 | 611 | Franklin Engineering |  | 3628.75 | 7011
AP | 601 | 08/22/18 | 690 | Franklin Engineering |  | 5892 | 7048
AP | 601 | 10/01/18 | 18 | Franklin Engineering |  | 1002.5 | 7084
AP | 601 | 10/16/18 | 657 | Franklin Engineering |  | 1308 | 7131
AP | 602 | 02/01/19 | 142 | Ahern Rentals |  | 579.98 | 20048404-1
AP | 602 | 03/05/19 | 206 | Ahern Rentals |  | 469.98 | 20048404-002
AP | 602 | 03/05/19 | 207 | Ahern Rentals |  | 983.13 | 20165056-001
AP | 602 | 04/02/19 | 9 | Ahern Rentals |  | 409.75 | 20048404-003
AP | 602 | 04/02/19 | 12 | Ahern Rentals |  | 750.75 | 20165056-002
AP | 602 | 04/22/19 | 623 | Ahern Rentals |  | -111.38 | 20165056-003
AP | 602 | 04/22/19 | 624 | Ahern Rentals |  | -60.23 | 20048404-004
AP | 602 | 04/22/19 | 625 | Ahern Rentals |  | -60.23 | 20048404-005
AP | 602 | 04/26/19 | 840 | Ahern Rentals |  | 409.75 | 20048404-006
AP | 602 | 04/26/19 | 841 | Ahern Rentals |  | 750.75 | 20165056-004
AP | 602 | 05/29/19 | 789 | Ahern Rentals |  | 409.75 | 20048404-007
AP | 602 | 05/29/19 | 790 | Ahern Rentals |  | 750.75 | 20165056-005
AP | 602 | 06/13/19 | 780 | Ahern Rentals |  | 409.75 | 20048404-008
AP | 602 | 06/13/19 | 781 | Ahern Rentals |  | 750.75 | 20165056-006
AP | 602 | 07/30/19 | 716 | Ahern Rentals |  | 409.75 | 20048404-009
AP | 602 | 07/30/19 | 717 | Ahern Rentals |  | 750.75 | 20165056-007
AP | 602 | 08/26/19 | 907 | Ahern Rentals |  | 409.75 | 20048404-010
AP | 602 | 08/26/19 | 908 | Ahern Rentals |  | 750.75 | 20165056-008
AP | 602 | 09/17/19 | 402 | Ahern Rentals |  | 409.75 | 20048404-011
AP | 602 | 09/17/19 | 403 | Ahern Rentals |  | 750.75 | 20165056-009
AP | 602 | 10/29/19 | 710 | Ahern Rentals |  | 110 | 20048404-012
AP | 602 | 11/06/19 | 162 | Ahern Rentals |  | 242 | 20165056-010
AP | 602 | 11/06/19 | 163 | Ahern Rentals |  | -121 | 20165056-011
AP | 602 | 02/25/20 | 595 | Sunbelt Rentals, Inc. |  | 603.68 | 98629431-0001
AP | 602 | 03/10/20 | 258 | Sunbelt Rentals, Inc. |  | -49.59 | 98629431-0002
AP | 603 | 06/12/18 | 411 | Capital One Credit Card |  | 2115 | 061118
AP | 603 | 08/07/18 | 111 | Capital One Credit Card |  | 16908 | 071318B1
AP | 603 | 08/30/18 | 1100 | Capital One Credit Card |  | 787 | 082318B
AP | 603 | 09/30/18 | 789 | Capital One Credit Card |  | 39 | 082718B
AP | 603 | 10/30/18 | 805 | Capital One Credit Card |  | 1574 | 100418B
AP | 607 | 07/10/18 | 203 | Capital One Credit Card |  | 395 | 053118R
AP | 607 | 07/10/18 | 215 | Capital One Credit Card |  | 395 | 061518R3
AP | 607 | 08/07/18 | 145 | Capital One Credit Card |  | 395 | 071518R3
AP | 607 | 08/30/18 | 1129 | Capital One Credit Card |  | 395 | 081518R3
AP | 607 | 09/30/18 | 824 | Capital One Credit Card |  | 395 | 091518R3
AP | 607 | 10/30/18 | 832 | Capital One Credit Card |  | 395 | 101518R3
AP | 607 | 12/14/18 | 486 | Capital One Credit Card |  | 417 | 111518R3
AP | 607 | 12/31/18 | 853 | Capital One Credit Card |  | 417 | 121718R3
AP | 607 | 02/14/19 | 452 | Capital One Credit Card |  | 417 | 011519R3
AP | 607 | 03/04/19 | 129 | Capital One Credit Card |  | 417 | 021519R2
AP | 607 | 03/04/19 | 135 | Capital One Credit Card |  | 417 | 022519R
AP | 607 | 03/31/19 | 1041 | Capital One Credit Card |  | 834 | 031619R2
AP | 607 | 04/30/19 | 976 | Capital One Credit Card |  | 834 | 041619R2
AP | 607 | 06/05/19 | 78 | Capital One Credit Card |  | 834 | 051619R2
AP | 607 | 07/10/19 | 242 | Capital One Credit Card |  | 834 | 061619R1
AP | 607 | 08/01/19 | 412 | Capital One Credit Card |  | 834.04 | 071519R1
AP | 607 | 09/10/19 | 210 | Capital One Credit Card |  | 834.04 | 081619R1
AP | 607 | 10/01/19 | 252 | Capital One Credit Card |  | 834.04 | 091619R1
AP | 607 | 11/21/19 | 780 | Capital One Credit Card |  | 834.04 | 101619R
AP | 607 | 01/08/20 | 216 | Capital One Credit Card |  | 834.04 | 111619R
AP | 607 | 01/10/20 | 433 | Capital One Credit Card |  | 834.04 | 121619R1
AP | 607 | 03/09/20 | 210 | Capital One Credit Card |  | 208.51 | 011620R
AP | 607 | 03/25/20 | 464 | Capital One Credit Card |  | -225.51 | 030520RDC
AP | 607 | 03/25/20 | 497 | Capital One Credit Card |  | 230.51 | 021620R1
PR | 995 | 02/02/18 | 38 | Hubbard, Robert W |  | 18.16
PR | 995 | 02/09/18 | 195 | Hubbard, Robert W |  | 36.32
PR | 995 | 03/09/18 | 184 | Gerard, Jeffrey S |  | 18.96
PR | 995 | 03/30/18 | 811 | Donelson, Richard T |  | 50.44
PR | 995 | 05/18/18 | 452 | Hubbard, Robert W |  | 18.16
PR | 995 | 05/25/18 | 806 | Donelson, Richard T |  | 201.75
PR | 995 | 06/01/18 | 75 | Donelson, Richard T |  | 126.09
PR | 995 | 06/08/18 | 339 | Donelson, Richard T |  | 302.63
PR | 995 | 06/08/18 | 340 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 06/08/18 | 340 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 06/15/18 | 527 | Donelson, Richard T |  | 151.31
PR | 995 | 06/15/18 | 528 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 06/22/18 | 753 | Donelson, Richard T |  | 75.66
PR | 995 | 06/22/18 | 754 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 06/29/18 | 950 | Cortes Sepulveda, Jose R |  | 116.21
PR | 995 | 06/29/18 | 963 | Cortes Mendiola, Victor H |  | 198.52
PR | 995 | 06/29/18 | 983 | Hubbard, Robert W |  | 161.2
PR | 995 | 06/29/18 | 1019 | Donelson, Richard T |  | 126.09
PR | 995 | 06/29/18 | 1020 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 07/06/18 | 38 | Hubbard, Robert W |  | 37.93
PR | 995 | 07/06/18 | 76 | Donelson, Richard T |  | 25.22
PR | 995 | 07/13/18 | 307 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 07/13/18 | 308 | Cortes Sepulveda, Jose R |  | 154.94
PR | 995 | 07/13/18 | 329 | Hubbard, Robert W |  | 75.86
PR | 995 | 07/13/18 | 367 | Donelson, Richard T |  | 75.66
PR | 995 | 07/13/18 | 368 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 07/20/18 | 447 | Cortes Mendiola, Victor H |  | 132.35
PR | 995 | 07/20/18 | 448 | Cortes Sepulveda, Jose R |  | 77.47
PR | 995 | 07/20/18 | 470 | Hubbard, Robert W |  | 94.82
PR | 995 | 07/20/18 | 507 | Donelson, Richard T |  | 25.22
PR | 995 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 60.53
PR | 995 | 07/27/18 | 773 | Cortes Mendiola, Victor H |  | 397.04
PR | 995 | 07/27/18 | 774 | Cortes Sepulveda, Jose R |  | 232.42
PR | 995 | 07/27/18 | 797 | Hubbard, Robert W |  | 474.11
PR | 995 | 07/27/18 | 808 | McCabe, Thomas C |  | 206.59
PR | 995 | 07/27/18 | 825 | Sepulveda Gonzalez, Alfredo |  | 200.14
PR | 995 | 07/27/18 | 834 | Donelson, Richard T |  | 25.22
PR | 995 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 08/03/18 | 12 | Cortes Mendiola, Victor H |  | 397.04
PR | 995 | 08/03/18 | 13 | Cortes Sepulveda, Jose R |  | 232.42
PR | 995 | 08/03/18 | 35 | Hubbard, Robert W |  | 265.5
PR | 995 | 08/03/18 | 46 | McCabe, Thomas C |  | 103.3
PR | 995 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo |  | 100.07
PR | 995 | 08/03/18 | 72 | Donelson, Richard T |  | 151.31
PR | 995 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 08/10/18 | 222 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 08/10/18 | 223 | Cortes Sepulveda, Jose R |  | 213.05
PR | 995 | 08/10/18 | 246 | Hubbard, Robert W |  | 94.82
PR | 995 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo |  | 162.61
PR | 995 | 08/10/18 | 283 | Donelson, Richard T |  | 277.41
PR | 995 | 08/17/18 | 490 | Cortes Mendiola, Victor H |  | 66.17
PR | 995 | 08/17/18 | 491 | Cortes Sepulveda, Jose R |  | 38.74
PR | 995 | 08/17/18 | 514 | Hubbard, Robert W |  | 37.93
PR | 995 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 08/24/18 | 752 | Cortes Mendiola, Victor H |  | 132.35
PR | 995 | 08/24/18 | 753 | Cortes Sepulveda, Jose R |  | 106.52
PR | 995 | 08/24/18 | 811 | Donelson, Richard T |  | 126.09
PR | 995 | 08/31/18 | 1007 | Cortes Sepulveda, Jose R |  | 38.74
PR | 995 | 08/31/18 | 1038 | Martinez Reyes, Juan C |  | 20.98
PR | 995 | 08/31/18 | 1069 | Donelson, Richard T |  | 100.88
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 09/07/18 | 47 | Cortes Mendiola, Victor H |  | 66.17
PR | 995 | 09/07/18 | 105 | Donelson, Richard T |  | 75.66
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 09/14/18 | 278 | Cortes Mendiola, Victor H |  | 132.35
PR | 995 | 09/14/18 | 279 | Cortes Sepulveda, Jose R |  | 77.47
PR | 995 | 09/14/18 | 302 | Hubbard, Robert W |  | 18.96
PR | 995 | 09/14/18 | 340 | Donelson, Richard T |  | 25.22
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 09/21/18 | 491 | Cortes Mendiola, Victor H |  | 33.09
PR | 995 | 09/21/18 | 492 | Cortes Sepulveda, Jose R |  | 87.16
PR | 995 | 09/21/18 | 515 | Hubbard, Robert W |  | 37.93
PR | 995 | 09/21/18 | 552 | Donelson, Richard T |  | 25.22
PR | 995 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 60.53
PR | 995 | 09/28/18 | 676 | Cortes Mendiola, Victor H |  | 181.98
PR | 995 | 09/28/18 | 677 | Cortes Sepulveda, Jose R |  | 106.52
PR | 995 | 09/28/18 | 700 | Hubbard, Robert W |  | 18.96
PR | 995 | 09/28/18 | 700 | Hubbard, Robert W |  | 56.89
PR | 995 | 09/28/18 | 739 | Donelson, Richard T |  | 75.66
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 10/05/18 | 40 | Cortes Mendiola, Victor H |  | 132.35
PR | 995 | 10/05/18 | 40 | Cortes Mendiola, Victor H |  | 66.17
PR | 995 | 10/05/18 | 41 | Cortes Sepulveda, Jose R |  | 77.47
PR | 995 | 10/05/18 | 41 | Cortes Sepulveda, Jose R |  | 67.79
PR | 995 | 10/05/18 | 64 | Hubbard, Robert W |  | 37.93
PR | 995 | 10/05/18 | 102 | Donelson, Richard T |  | 75.66
PR | 995 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I |  | 90.38
PR | 995 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I |  | 90.38
PR | 995 | 10/12/18 | 245 | Cortes Mendiola, Victor H |  | 231.61
PR | 995 | 10/12/18 | 245 | Cortes Mendiola, Victor H |  | 297.78
PR | 995 | 10/12/18 | 246 | Cortes Sepulveda, Jose R |  | 135.58
PR | 995 | 10/12/18 | 246 | Cortes Sepulveda, Jose R |  | 174.31
PR | 995 | 10/12/18 | 265 | Gutierrez Salas, Jose |  | 58.1
PR | 995 | 10/12/18 | 265 | Gutierrez Salas, Jose |  | 58.1
PR | 995 | 10/12/18 | 270 | Hubbard, Robert W |  | 37.93
PR | 995 | 10/12/18 | 270 | Hubbard, Robert W |  | 37.93
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 10/19/18 | 444 | Cortes Mendiola, Victor H |  | 66.17
PR | 995 | 10/19/18 | 444 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 10/19/18 | 445 | Cortes Sepulveda, Jose R |  | 38.74
PR | 995 | 10/19/18 | 445 | Cortes Sepulveda, Jose R |  | 154.94
PR | 995 | 10/19/18 | 468 | Hubbard, Robert W |  | 180.16
PR | 995 | 10/19/18 | 507 | Donelson, Richard T |  | 126.09
PR | 995 | 10/25/18 | 687 | Hubbard, Robert W |  | 189.65
PR | 995 | 10/26/18 | 712 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 10/26/18 | 712 | Cortes Mendiola, Victor H |  | 66.17
PR | 995 | 10/26/18 | 713 | Cortes Sepulveda, Jose R |  | 154.94
PR | 995 | 10/26/18 | 713 | Cortes Sepulveda, Jose R |  | 67.79
PR | 995 | 10/26/18 | 774 | Donelson, Richard T |  | 50.44
PR | 995 | 10/26/18 | 774 | Donelson, Richard T |  | 126.09
PR | 995 | 11/02/18 | 14 | Cortes Mendiola, Victor H |  | 132.35
PR | 995 | 11/02/18 | 14 | Cortes Mendiola, Victor H |  | 231.61
PR | 995 | 11/02/18 | 15 | Cortes Sepulveda, Jose R |  | 77.47
PR | 995 | 11/02/18 | 15 | Cortes Sepulveda, Jose R |  | 135.58
PR | 995 | 11/02/18 | 76 | Donelson, Richard T |  | 50.44
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 11/09/18 | 192 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 11/09/18 | 193 | Cortes Sepulveda, Jose R |  | 154.94
PR | 995 | 11/09/18 | 217 | Hubbard, Robert W |  | 37.93
PR | 995 | 11/16/18 | 433 | Balderas Ortiz, Ricardo I |  | 180.77
PR | 995 | 11/16/18 | 441 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 11/16/18 | 441 | Cortes Mendiola, Victor H |  | 264.7
PR | 995 | 11/16/18 | 442 | Cortes Sepulveda, Jose R |  | 154.94
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 25.22
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 20.18
PR | 995 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I |  | 180.77
PR | 995 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I |  | 180.77
PR | 995 | 11/21/18 | 627 | Cortes Mendiola, Victor H |  | 363.96
PR | 995 | 11/21/18 | 627 | Cortes Mendiola, Victor H |  | 165.44
PR | 995 | 11/21/18 | 650 | Hubbard, Robert W |  | 18.96
PR | 995 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 40.35
PR | 995 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I |  | 280.84
PR | 995 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I |  | 93.61
PR | 995 | 11/30/18 | 839 | Cortes Mendiola, Victor H |  | 138.8
PR | 995 | 11/30/18 | 839 | Cortes Mendiola, Victor H |  | 364.36
PR | 995 | 11/30/18 | 840 | Cortes Sepulveda, Jose R |  | 115.4
PR | 995 | 11/30/18 | 840 | Cortes Sepulveda, Jose R |  | 136.38
PR | 995 | 11/30/18 | 900 | Donelson, Richard T |  | 50.44
PR | 995 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 41.96
PR | 995 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 12/07/18 | 52 | Cortes Mendiola, Victor H |  | 416.41
PR | 995 | 12/07/18 | 52 | Cortes Mendiola, Victor H |  | 277.61
PR | 995 | 12/07/18 | 53 | Cortes Sepulveda, Jose R |  | 251.78
PR | 995 | 12/07/18 | 53 | Cortes Sepulveda, Jose R |  | 167.86
PR | 995 | 12/07/18 | 113 | Donelson, Richard T |  | 25.22
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 83.93
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 41.96
PR | 995 | 12/14/18 | 268 | Balderas Ortiz, Ricardo I |  | 327.64
PR | 995 | 12/14/18 | 276 | Cortes Mendiola, Victor H |  | 485.81
PR | 995 | 12/14/18 | 277 | Cortes Sepulveda, Jose R |  | 293.75
PR | 995 | 12/14/18 | 337 | Donelson, Richard T |  | 75.66
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 12/21/18 | 509 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 12/21/18 | 517 | Cortes Mendiola, Victor H |  | 451.11
PR | 995 | 12/21/18 | 518 | Cortes Sepulveda, Jose R |  | 167.86
PR | 995 | 12/21/18 | 540 | Hubbard, Robert W |  | 59.31
PR | 995 | 12/21/18 | 577 | Donelson, Richard T |  | 25.22
PR | 995 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 12/28/18 | 709 | Cortes Sepulveda, Jose R |  | 52.46
PR | 995 | 12/28/18 | 768 | Donelson, Richard T |  | 25.22
PR | 995 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 01/11/19 | 213 | Balderas Ortiz, Ricardo I |  | 46.81
PR | 995 | 01/11/19 | 221 | Cortes Mendiola, Victor H |  | 52.05
PR | 995 | 01/11/19 | 222 | Cortes Sepulveda, Jose R |  | 115.4
PR | 995 | 01/11/19 | 244 | Hubbard, Robert W |  | 39.54
PR | 995 | 01/11/19 | 281 | Donelson, Richard T |  | 25.22
PR | 995 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 01/18/19 | 476 | Cortes Mendiola, Victor H |  | 86.75
PR | 995 | 01/18/19 | 476 | Cortes Mendiola, Victor H |  | 138.8
PR | 995 | 01/18/19 | 499 | Hubbard, Robert W |  | 39.54
PR | 995 | 01/18/19 | 542 | Donelson, Richard T |  | 25.22
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 01/25/19 | 716 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 01/25/19 | 725 | Cortes Mendiola, Victor H |  | 624.62
PR | 995 | 01/25/19 | 726 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 01/25/19 | 748 | Hubbard, Robert W |  | 59.31
PR | 995 | 01/25/19 | 786 | Donelson, Richard T |  | 126.09
PR | 995 | 02/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 02/01/19 | 13 | Cortes Mendiola, Victor H |  | 607.27
PR | 995 | 02/01/19 | 13 | Cortes Mendiola, Victor H |  | 34.7
PR | 995 | 02/01/19 | 14 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 02/01/19 | 36 | Hubbard, Robert W |  | 19.77
PR | 995 | 02/01/19 | 70 | Donelson, Richard T |  | 75.66
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 62.95
PR | 995 | 02/08/19 | 160 | Balderas Ortiz, Ricardo I |  | 280.84
PR | 995 | 02/08/19 | 168 | Cortes Mendiola, Victor H |  | 364.36
PR | 995 | 02/08/19 | 169 | Cortes Sepulveda, Jose R |  | 136.38
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 02/15/19 | 322 | Balderas Ortiz, Ricardo I |  | 280.84
PR | 995 | 02/15/19 | 328 | Chevez, Herson G |  | 80.7
PR | 995 | 02/15/19 | 330 | Cortes Mendiola, Victor H |  | 329.66
PR | 995 | 02/15/19 | 331 | Cortes Sepulveda, Jose R |  | 251.78
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 41.96
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 02/22/19 | 580 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 02/22/19 | 586 | Chevez, Herson G |  | 355.08
PR | 995 | 02/22/19 | 588 | Cortes Mendiola, Victor H |  | 589.92
PR | 995 | 02/22/19 | 588 | Cortes Mendiola, Victor H |  | 173.51
PR | 995 | 02/22/19 | 589 | Cortes Sepulveda, Jose R |  | 461.6
PR | 995 | 02/22/19 | 647 | Donelson, Richard T |  | 25.22
PR | 995 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 41.96
PR | 995 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 386.15
PR | 995 | 03/01/19 | 6 | Barbosa, Michael S |  | 80.7
PR | 995 | 03/01/19 | 9 | Benites Portillo, Marvin E |  | 251.78
PR | 995 | 03/01/19 | 9 | Benites Portillo, Marvin E |  | 154.94
PR | 995 | 03/01/19 | 11 | Chevez, Herson G |  | 48.42
PR | 995 | 03/01/19 | 11 | Chevez, Herson G |  | 129.12
PR | 995 | 03/01/19 | 11 | Chevez, Herson G |  | 234.03
PR | 995 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 208.21
PR | 995 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 520.52
PR | 995 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 86.75
PR | 995 | 03/01/19 | 14 | Cortes Sepulveda, Jose R |  | 346.2
PR | 995 | 03/01/19 | 14 | Cortes Sepulveda, Jose R |  | 167.86
PR | 995 | 03/01/19 | 43 | Lovo, German G |  | 181.58
PR | 995 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 74.24
PR | 995 | 03/01/19 | 74 | Donelson, Richard T |  | 75.66
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 83.93
PR | 995 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I |  | 157.97
PR | 995 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 03/08/19 | 251 | Benites Portillo, Marvin E |  | 397.04
PR | 995 | 03/08/19 | 253 | Chevez, Herson G |  | 108.95
PR | 995 | 03/08/19 | 253 | Chevez, Herson G |  | 322.8
PR | 995 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 260.26
PR | 995 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 503.16
PR | 995 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 69.4
PR | 995 | 03/08/19 | 256 | Cortes Sepulveda, Jose R |  | 94.42
PR | 995 | 03/08/19 | 256 | Cortes Sepulveda, Jose R |  | 451.11
PR | 995 | 03/08/19 | 257 | Crespin Portillo, Juan D |  | 10.29
PR | 995 | 03/08/19 | 257 | Crespin Portillo, Juan D |  | 41.16
PR | 995 | 03/08/19 | 278 | Hubbard, Robert W |  | 39.54
PR | 995 | 03/08/19 | 283 | Lovo, German G |  | 403.5
PR | 995 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 74.24
PR | 995 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 10.29
PR | 995 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 41.16
PR | 995 | 03/08/19 | 314 | Donelson, Richard T |  | 25.22
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 83.93
PR | 995 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 35.1
PR | 995 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 280.84
PR | 995 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 03/15/19 | 497 | Belcher, Jacob T |  | 21.79
PR | 995 | 03/15/19 | 497 | Belcher, Jacob T |  | 290.52
PR | 995 | 03/15/19 | 498 | Benites Portillo, Marvin E |  | 416.41
PR | 995 | 03/15/19 | 500 | Chevez, Herson G |  | 36.32
PR | 995 | 03/15/19 | 500 | Chevez, Herson G |  | 322.8
PR | 995 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 78.08
PR | 995 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 537.87
PR | 995 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 52.05
PR | 995 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 69.4
PR | 995 | 03/15/19 | 503 | Cortes Sepulveda, Jose R |  | 409.15
PR | 995 | 03/15/19 | 521 | Hoeg, Xavier A |  | 20.58
PR | 995 | 03/15/19 | 521 | Hoeg, Xavier A |  | 274.38
PR | 995 | 03/15/19 | 525 | Hubbard, Robert W |  | 39.54
PR | 995 | 03/15/19 | 525 | Hubbard, Robert W |  | 39.54
PR | 995 | 03/15/19 | 530 | Lovo, German G |  | 332.89
PR | 995 | 03/15/19 | 531 | Lucas Tzintzun, Rafael |  | 123.47
PR | 995 | 03/15/19 | 548 | Saules Bezanilla, Fernando |  | 167.86
PR | 995 | 03/15/19 | 562 | Donelson, Richard T |  | 25.22
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 62.95
PR | 995 | 03/22/19 | 708 | Balderas Ortiz, Ricardo I |  | 421.25
PR | 995 | 03/22/19 | 711 | Belcher, Jacob T |  | 54.47
PR | 995 | 03/22/19 | 711 | Belcher, Jacob T |  | 290.52
PR | 995 | 03/22/19 | 712 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 03/22/19 | 714 | Chevez, Herson G |  | 60.53
PR | 995 | 03/22/19 | 714 | Chevez, Herson G |  | 322.8
PR | 995 | 03/22/19 | 716 | Cortes Mendiola, Victor H |  | 130.13
PR | 995 | 03/22/19 | 716 | Cortes Mendiola, Victor H |  | 694.02
PR | 995 | 03/22/19 | 717 | Cortes Sepulveda, Jose R |  | 47.21
PR | 995 | 03/22/19 | 717 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 03/22/19 | 735 | Hoeg, Xavier A |  | 116.61
PR | 995 | 03/22/19 | 744 | Lovo, German G |  | 433.76
PR | 995 | 03/22/19 | 761 | Saules Bezanilla, Fernando |  | 48.42
PR | 995 | 03/22/19 | 761 | Saules Bezanilla, Fernando |  | 258.24
PR | 995 | 03/22/19 | 776 | Donelson, Richard T |  | 75.66
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 62.95
PR | 995 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I |  | 140.42
PR | 995 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 03/29/19 | 922 | Belcher, Jacob T |  | 130.73
PR | 995 | 03/29/19 | 922 | Belcher, Jacob T |  | 290.52
PR | 995 | 03/29/19 | 923 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 03/29/19 | 923 | Benites Portillo, Marvin E |  | 387.36
PR | 995 | 03/29/19 | 925 | Chevez, Herson G |  | 145.26
PR | 995 | 03/29/19 | 925 | Chevez, Herson G |  | 322.8
PR | 995 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 260.26
PR | 995 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 52.05
PR | 995 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 607.27
PR | 995 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 34.7
PR | 995 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 125.89
PR | 995 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 62.95
PR | 995 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 251.78
PR | 995 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 167.86
PR | 995 | 03/29/19 | 947 | Hoeg, Xavier A |  | 253.8
PR | 995 | 03/29/19 | 951 | Hubbard, Robert W |  | 29.66
PR | 995 | 03/29/19 | 956 | Lovo, German G |  | 45.39
PR | 995 | 03/29/19 | 956 | Lovo, German G |  | 413.59
PR | 995 | 03/29/19 | 957 | Lucas Tzintzun, Rafael |  | 130.73
PR | 995 | 03/29/19 | 957 | Lucas Tzintzun, Rafael |  | 290.52
PR | 995 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 167.86
PR | 995 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | -167.86
PR | 995 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 116.21
PR | 995 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 258.24
PR | 995 | 03/29/19 | 977 | Sorto Regalado, Milton J |  | 116.21
PR | 995 | 03/29/19 | 977 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 03/29/19 | 989 | Donelson, Richard T |  | 75.66
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 62.95
PR | 995 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I |  | 105.31
PR | 995 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I |  | 362.75
PR | 995 | 04/05/19 | 84 | Belcher, Jacob T |  | 290.52
PR | 995 | 04/05/19 | 85 | Benites Portillo, Marvin E |  | 43.58
PR | 995 | 04/05/19 | 85 | Benites Portillo, Marvin E |  | 338.94
PR | 995 | 04/05/19 | 87 | Chevez, Herson G |  | 121.05
PR | 995 | 04/05/19 | 87 | Chevez, Herson G |  | 322.8
PR | 995 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 26.03
PR | 995 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 208.21
PR | 995 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 589.92
PR | 995 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 17.35
PR | 995 | 04/05/19 | 90 | Cortes Sepulveda, Jose R |  | 62.95
PR | 995 | 04/05/19 | 90 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 04/05/19 | 110 | Hoeg, Xavier A |  | 233.22
PR | 995 | 04/05/19 | 114 | Hubbard, Robert W |  | 39.54
PR | 995 | 04/05/19 | 119 | Lovo, German G |  | 45.39
PR | 995 | 04/05/19 | 119 | Lovo, German G |  | 403.5
PR | 995 | 04/05/19 | 120 | Lucas Tzintzun, Rafael |  | 108.95
PR | 995 | 04/05/19 | 120 | Lucas Tzintzun, Rafael |  | 290.52
PR | 995 | 04/05/19 | 136 | Saules Bezanilla, Fernando |  | 77.47
PR | 995 | 04/05/19 | 136 | Saules Bezanilla, Fernando |  | 258.24
PR | 995 | 04/05/19 | 140 | Sorto Regalado, Milton J |  | 96.84
PR | 995 | 04/05/19 | 140 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 04/05/19 | 151 | Donelson, Richard T |  | 25.22
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 83.93
PR | 995 | 04/12/19 | 325 | Balderas Ortiz, Ricardo I |  | 468.06
PR | 995 | 04/12/19 | 328 | Belcher, Jacob T |  | 10.89
PR | 995 | 04/12/19 | 328 | Belcher, Jacob T |  | 290.52
PR | 995 | 04/12/19 | 329 | Benites Portillo, Marvin E |  | 387.36
PR | 995 | 04/12/19 | 331 | Chevez, Herson G |  | 12.11
PR | 995 | 04/12/19 | 331 | Chevez, Herson G |  | 322.8
PR | 995 | 04/12/19 | 333 | Cortes Mendiola, Victor H |  | 556.83
PR | 995 | 04/12/19 | 333 | Cortes Mendiola, Victor H |  | 74.24
PR | 995 | 04/12/19 | 334 | Cortes Sepulveda, Jose R |  | 15.74
PR | 995 | 04/12/19 | 334 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 04/12/19 | 353 | Hoeg, Xavier A |  | 10.29
PR | 995 | 04/12/19 | 353 | Hoeg, Xavier A |  | 274.38
PR | 995 | 04/12/19 | 357 | Hubbard, Robert W |  | 40.35
PR | 995 | 04/12/19 | 363 | Lovo, German G |  | 15.13
PR | 995 | 04/12/19 | 363 | Lovo, German G |  | 403.5
PR | 995 | 04/12/19 | 364 | Lucas Tzintzun, Rafael |  | 10.89
PR | 995 | 04/12/19 | 364 | Lucas Tzintzun, Rafael |  | 290.52
PR | 995 | 04/12/19 | 384 | Sorto Regalado, Milton J |  | 9.68
PR | 995 | 04/12/19 | 384 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I |  | 187.22
PR | 995 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I |  | 280.84
PR | 995 | 04/19/19 | 525 | Belcher, Jacob T |  | 290.52
PR | 995 | 04/19/19 | 526 | Benites Portillo, Marvin E |  | 309.89
PR | 995 | 04/19/19 | 528 | Chevez, Herson G |  | 193.68
PR | 995 | 04/19/19 | 530 | Cortes Mendiola, Victor H |  | 705.32
PR | 995 | 04/19/19 | 531 | Cortes Sepulveda, Jose R |  | 419.64
PR | 995 | 04/19/19 | 551 | Hoeg, Xavier A |  | 219.5
PR | 995 | 04/19/19 | 561 | Lovo, German G |  | 322.8
PR | 995 | 04/19/19 | 561 | Lovo, German G |  | 80.7
PR | 995 | 04/19/19 | 562 | Lucas Tzintzun, Rafael |  | 232.42
PR | 995 | 04/19/19 | 582 | Sorto Regalado, Milton J |  | 51.65
PR | 995 | 04/19/19 | 596 | Donelson, Richard T |  | 50.44
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 20.98
PR | 995 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 04/26/19 | 745 | Belcher, Jacob T |  | 72.63
PR | 995 | 04/26/19 | 745 | Belcher, Jacob T |  | 322.8
PR | 995 | 04/26/19 | 746 | Benites Portillo, Marvin E |  | 413.99
PR | 995 | 04/26/19 | 748 | Chevez, Herson G |  | 83.52
PR | 995 | 04/26/19 | 748 | Chevez, Herson G |  | 371.22
PR | 995 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 167.05
PR | 995 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 519.71
PR | 995 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 167.05
PR | 995 | 04/26/19 | 751 | Cortes Sepulveda, Jose R |  | 108.95
PR | 995 | 04/26/19 | 751 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 04/26/19 | 762 | Galdamez, Dagoberto A |  | 290.52
PR | 995 | 04/26/19 | 770 | Hoeg, Xavier A |  | 219.5
PR | 995 | 04/26/19 | 774 | Hubbard, Robert W |  | 40.35
PR | 995 | 04/26/19 | 780 | Lovo, German G |  | 348.62
PR | 995 | 04/26/19 | 781 | Lucas Tzintzun, Rafael |  | 76.26
PR | 995 | 04/26/19 | 781 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 04/26/19 | 787 | Portillo Soriano, Walter A |  | 79.89
PR | 995 | 04/26/19 | 787 | Portillo Soriano, Walter A |  | 213.05
PR | 995 | 04/26/19 | 791 | Rivera, Eli P |  | 108.95
PR | 995 | 04/26/19 | 791 | Rivera, Eli P |  | 290.52
PR | 995 | 04/26/19 | 812 | Donelson, Richard T |  | 50.44
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 05/03/19 | 12 | Belcher, Jacob T |  | 72.63
PR | 995 | 05/03/19 | 12 | Belcher, Jacob T |  | 322.8
PR | 995 | 05/03/19 | 13 | Benites Portillo, Marvin E |  | 424.89
PR | 995 | 05/03/19 | 15 | Chevez, Herson G |  | 83.52
PR | 995 | 05/03/19 | 15 | Chevez, Herson G |  | 371.22
PR | 995 | 05/03/19 | 17 | Cortes Mendiola, Victor H |  | 742.44
PR | 995 | 05/03/19 | 18 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 05/03/19 | 30 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 05/03/19 | 38 | Hoeg, Xavier A |  | 274.38
PR | 995 | 05/03/19 | 42 | Hubbard, Robert W |  | 45.39
PR | 995 | 05/03/19 | 42 | Hubbard, Robert W |  | 121.05
PR | 995 | 05/03/19 | 42 | Hubbard, Robert W |  | 60.53
PR | 995 | 05/03/19 | 49 | Lovo, German G |  | 435.78
PR | 995 | 05/03/19 | 50 | Lucas Tzintzun, Rafael |  | 76.26
PR | 995 | 05/03/19 | 50 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 05/03/19 | 56 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 05/03/19 | 60 | Rivera, Eli P |  | 90.79
PR | 995 | 05/03/19 | 60 | Rivera, Eli P |  | 484.2
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 05/10/19 | 162 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 05/10/19 | 165 | Belcher, Jacob T |  | 322.8
PR | 995 | 05/10/19 | 166 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 05/10/19 | 168 | Chevez, Herson G |  | 371.22
PR | 995 | 05/10/19 | 170 | Cortes Mendiola, Victor H |  | 389.78
PR | 995 | 05/10/19 | 170 | Cortes Mendiola, Victor H |  | 55.68
PR | 995 | 05/10/19 | 171 | Cortes Sepulveda, Jose R |  | 290.52
PR | 995 | 05/10/19 | 171 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 05/10/19 | 183 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 05/10/19 | 191 | Hoeg, Xavier A |  | 274.38
PR | 995 | 05/10/19 | 195 | Hubbard, Robert W |  | 121.05
PR | 995 | 05/10/19 | 195 | Hubbard, Robert W |  | 121.05
PR | 995 | 05/10/19 | 202 | Lovo, German G |  | 435.78
PR | 995 | 05/10/19 | 203 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 05/10/19 | 209 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 05/10/19 | 213 | Rivera, Eli P |  | 387.36
PR | 995 | 05/10/19 | 234 | Donelson, Richard T |  | 50.44
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 05/17/19 | 393 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 05/17/19 | 396 | Belcher, Jacob T |  | 258.24
PR | 995 | 05/17/19 | 397 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 05/17/19 | 400 | Chevez, Herson G |  | 371.22
PR | 995 | 05/17/19 | 402 | Cortes Mendiola, Victor H |  | 649.64
PR | 995 | 05/17/19 | 402 | Cortes Mendiola, Victor H |  | 92.81
PR | 995 | 05/17/19 | 403 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 05/17/19 | 415 | Galdamez, Dagoberto A |  | 290.52
PR | 995 | 05/17/19 | 415 | Galdamez, Dagoberto A |  | 193.68
PR | 995 | 05/17/19 | 423 | Hoeg, Xavier A |  | 274.38
PR | 995 | 05/17/19 | 427 | Hubbard, Robert W |  | 40.35
PR | 995 | 05/17/19 | 434 | Lovo, German G |  | 403.1
PR | 995 | 05/17/19 | 435 | Lucas Tzintzun, Rafael |  | 321.99
PR | 995 | 05/17/19 | 441 | Portillo Soriano, Walter A |  | 284.06
PR | 995 | 05/17/19 | 441 | Portillo Soriano, Walter A |  | 71.02
PR | 995 | 05/17/19 | 445 | Rivera, Eli P |  | 484.2
PR | 995 | 05/17/19 | 454 | Sorto Regalado, Milton J |  | 103.3
PR | 995 | 05/17/19 | 467 | Donelson, Richard T |  | 25.22
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 88.77
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 33.29
PR | 995 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 05/24/19 | 609 | Belcher, Jacob T |  | 302.63
PR | 995 | 05/24/19 | 612 | Chevez, Herson G |  | 83.52
PR | 995 | 05/24/19 | 612 | Chevez, Herson G |  | 371.22
PR | 995 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 167.05
PR | 995 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 612.51
PR | 995 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 129.93
PR | 995 | 05/24/19 | 615 | Cortes Sepulveda, Jose R |  | 108.95
PR | 995 | 05/24/19 | 615 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 05/24/19 | 627 | Galdamez, Dagoberto A |  | 387.36
PR | 995 | 05/24/19 | 635 | Hoeg, Xavier A |  | 274.38
PR | 995 | 05/24/19 | 639 | Hubbard, Robert W |  | 121.05
PR | 995 | 05/24/19 | 639 | Hubbard, Robert W |  | 40.35
PR | 995 | 05/24/19 | 646 | Lovo, German G |  | 435.78
PR | 995 | 05/24/19 | 647 | Lucas Tzintzun, Rafael |  | 76.26
PR | 995 | 05/24/19 | 647 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 05/24/19 | 653 | Portillo Soriano, Walter A |  | 79.89
PR | 995 | 05/24/19 | 653 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 05/24/19 | 657 | Rivera, Eli P |  | 108.95
PR | 995 | 05/24/19 | 657 | Rivera, Eli P |  | 484.2
PR | 995 | 05/24/19 | 666 | Sorto Regalado, Milton J |  | 58.1
PR | 995 | 05/24/19 | 666 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 05/24/19 | 680 | Donelson, Richard T |  | 25.22
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 88.77
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 33.29
PR | 995 | 05/31/19 | 879 | Balderas Ortiz, Ricardo I |  | 413.18
PR | 995 | 05/31/19 | 882 | Belcher, Jacob T |  | 258.24
PR | 995 | 05/31/19 | 883 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 05/31/19 | 886 | Chevez, Herson G |  | 296.98
PR | 995 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 408.34
PR | 995 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 111.37
PR | 995 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 74.24
PR | 995 | 05/31/19 | 889 | Cortes Sepulveda, Jose R |  | 351.05
PR | 995 | 05/31/19 | 901 | Galdamez, Dagoberto A |  | 351.05
PR | 995 | 05/31/19 | 901 | Galdamez, Dagoberto A |  | 36.32
PR | 995 | 05/31/19 | 909 | Hoeg, Xavier A |  | 219.5
PR | 995 | 05/31/19 | 913 | Hubbard, Robert W |  | 20.18
PR | 995 | 05/31/19 | 913 | Hubbard, Robert W |  | 80.7
PR | 995 | 05/31/19 | 920 | Lovo, German G |  | 315.94
PR | 995 | 05/31/19 | 921 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 05/31/19 | 927 | Portillo Soriano, Walter A |  | 142.03
PR | 995 | 05/31/19 | 931 | Rivera, Eli P |  | 387.36
PR | 995 | 05/31/19 | 940 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 05/31/19 | 952 | Donelson, Richard T |  | 25.22
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 66.58
PR | 995 | 06/07/19 | 181 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 06/07/19 | 184 | Belcher, Jacob T |  | 322.8
PR | 995 | 06/07/19 | 185 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 06/07/19 | 188 | Chevez, Herson G |  | 371.22
PR | 995 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 185.61
PR | 995 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 185.61
PR | 995 | 06/07/19 | 191 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 06/07/19 | 203 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 06/07/19 | 211 | Hoeg, Xavier A |  | 274.38
PR | 995 | 06/07/19 | 215 | Hubbard, Robert W |  | 40.35
PR | 995 | 06/07/19 | 221 | Lovo, German G |  | 348.62
PR | 995 | 06/07/19 | 222 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 06/07/19 | 223 | Martinez Reyes, Juan C |  | 106.52
PR | 995 | 06/07/19 | 228 | Portillo Soriano, Walter A |  | 213.05
PR | 995 | 06/07/19 | 232 | Rivera, Eli P |  | 484.2
PR | 995 | 06/07/19 | 242 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 06/07/19 | 254 | Donelson, Richard T |  | 126.09
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 66.58
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 06/14/19 | 452 | Balderas Ortiz, Ricardo I |  | 503.57
PR | 995 | 06/14/19 | 455 | Belcher, Jacob T |  | 254.21
PR | 995 | 06/14/19 | 456 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 06/14/19 | 456 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 06/14/19 | 460 | Cortes Mendiola, Victor H |  | 742.44
PR | 995 | 06/14/19 | 461 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 06/14/19 | 467 | Draves, Steven W |  | 98.05
PR | 995 | 06/14/19 | 468 | Eisenhauer, Tommy J |  | 101.68
PR | 995 | 06/14/19 | 469 | Eliassen, Cory H |  | 98.05
PR | 995 | 06/14/19 | 471 | Galdamez, Dagoberto A |  | 387.36
PR | 995 | 06/14/19 | 471 | Galdamez, Dagoberto A |  | 96.84
PR | 995 | 06/14/19 | 474 | Gerard, Jordan E |  | 108.95
PR | 995 | 06/14/19 | 479 | Hoeg, Xavier A |  | 216.07
PR | 995 | 06/14/19 | 482 | Hubbard, Justin A |  | 62.95
PR | 995 | 06/14/19 | 483 | Hubbard, Robert W |  | 60.53
PR | 995 | 06/14/19 | 490 | Lovo, German G |  | 174.31
PR | 995 | 06/14/19 | 490 | Lovo, German G |  | 261.47
PR | 995 | 06/14/19 | 491 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 06/14/19 | 497 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 06/14/19 | 501 | Rivera, Eli P |  | 484.2
PR | 995 | 06/14/19 | 503 | Roberts, Lake A |  | 60.53
PR | 995 | 06/14/19 | 510 | Sorto Regalado, Milton J |  | 251.78
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 25.22
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 88.77
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 06/21/19 | 620 | Balderas Ortiz, Ricardo I |  | 464.83
PR | 995 | 06/21/19 | 623 | Belcher, Jacob T |  | 258.24
PR | 995 | 06/21/19 | 624 | Benites Portillo, Marvin E |  | 261.47
PR | 995 | 06/21/19 | 624 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 06/21/19 | 628 | Chevez, Herson G |  | 371.22
PR | 995 | 06/21/19 | 630 | Cortes Mendiola, Victor H |  | 556.83
PR | 995 | 06/21/19 | 630 | Cortes Mendiola, Victor H |  | 185.61
PR | 995 | 06/21/19 | 631 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 06/21/19 | 642 | Galdamez, Dagoberto A |  | 290.52
PR | 995 | 06/21/19 | 642 | Galdamez, Dagoberto A |  | 193.68
PR | 995 | 06/21/19 | 650 | Hoeg, Xavier A |  | 274.38
PR | 995 | 06/21/19 | 654 | Hubbard, Robert W |  | 121.05
PR | 995 | 06/21/19 | 661 | Lovo, German G |  | 326.84
PR | 995 | 06/21/19 | 661 | Lovo, German G |  | 108.95
PR | 995 | 06/21/19 | 662 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 06/21/19 | 668 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 06/21/19 | 672 | Rivera, Eli P |  | 363.15
PR | 995 | 06/21/19 | 672 | Rivera, Eli P |  | 96.84
PR | 995 | 06/21/19 | 672 | Rivera, Eli P |  | 24.21
PR | 995 | 06/21/19 | 681 | Sorto Regalado, Milton J |  | 232.42
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 25.22
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 06/28/19 | 838 | Balderas Ortiz, Ricardo I |  | 413.18
PR | 995 | 06/28/19 | 841 | Belcher, Jacob T |  | 322.8
PR | 995 | 06/28/19 | 842 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 06/28/19 | 842 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 06/28/19 | 846 | Chevez, Herson G |  | 371.22
PR | 995 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 556.83
PR | 995 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 92.81
PR | 995 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 92.81
PR | 995 | 06/28/19 | 849 | Cortes Sepulveda, Jose R |  | 290.52
PR | 995 | 06/28/19 | 849 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 06/28/19 | 860 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 06/28/19 | 868 | Hoeg, Xavier A |  | 219.5
PR | 995 | 06/28/19 | 878 | Lovo, German G |  | 435.78
PR | 995 | 06/28/19 | 879 | Lucas Tzintzun, Rafael |  | 305.05
PR | 995 | 06/28/19 | 885 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 06/28/19 | 889 | Rivera, Eli P |  | 484.2
PR | 995 | 06/28/19 | 898 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 06/28/19 | 910 | Donelson, Richard T |  | 25.22
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 07/05/19 | 10 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 07/05/19 | 13 | Belcher, Jacob T |  | 322.8
PR | 995 | 07/05/19 | 14 | Benites Portillo, Marvin E |  | 370.41
PR | 995 | 07/05/19 | 18 | Chevez, Herson G |  | 371.22
PR | 995 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 111.37
PR | 995 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 593.95
PR | 995 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 37.12
PR | 995 | 07/05/19 | 21 | Cortes Sepulveda, Jose R |  | 375.26
PR | 995 | 07/05/19 | 32 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 07/05/19 | 40 | Hoeg, Xavier A |  | 246.94
PR | 995 | 07/05/19 | 42 | Hubbard, Dustin R |  | 60.53
PR | 995 | 07/05/19 | 50 | Lovo, German G |  | 424.89
PR | 995 | 07/05/19 | 51 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 07/05/19 | 57 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 07/05/19 | 61 | Rivera, Eli P |  | 484.2
PR | 995 | 07/05/19 | 69 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 25.22
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 07/12/19 | 280 | Balderas Ortiz, Ricardo I |  | 413.18
PR | 995 | 07/12/19 | 283 | Belcher, Jacob T |  | 258.24
PR | 995 | 07/12/19 | 284 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 07/12/19 | 288 | Chevez, Herson G |  | 296.98
PR | 995 | 07/12/19 | 290 | Cortes Mendiola, Victor H |  | 296.98
PR | 995 | 07/12/19 | 290 | Cortes Mendiola, Victor H |  | 296.98
PR | 995 | 07/12/19 | 291 | Cortes Sepulveda, Jose R |  | 387.36
PR | 995 | 07/12/19 | 301 | Galdamez, Dagoberto A |  | 387.36
PR | 995 | 07/12/19 | 309 | Hoeg, Xavier A |  | 219.5
PR | 995 | 07/12/19 | 313 | Hubbard, Robert W |  | 110.96
PR | 995 | 07/12/19 | 319 | Lovo, German G |  | 348.62
PR | 995 | 07/12/19 | 320 | Lucas Tzintzun, Rafael |  | 262.68
PR | 995 | 07/12/19 | 326 | Portillo Soriano, Walter A |  | 284.06
PR | 995 | 07/12/19 | 330 | Rivera, Eli P |  | 387.36
PR | 995 | 07/12/19 | 340 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 07/12/19 | 341 | Stahlschmidt, John P |  | 245.33
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 07/19/19 | 510 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 07/19/19 | 513 | Belcher, Jacob T |  | 322.8
PR | 995 | 07/19/19 | 514 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 07/19/19 | 518 | Chevez, Herson G |  | 371.22
PR | 995 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 445.46
PR | 995 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 222.73
PR | 995 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 74.24
PR | 995 | 07/19/19 | 521 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 07/19/19 | 531 | Galdamez, Dagoberto A |  | 193.68
PR | 995 | 07/19/19 | 539 | Hoeg, Xavier A |  | 274.38
PR | 995 | 07/19/19 | 549 | Lovo, German G |  | 435.78
PR | 995 | 07/19/19 | 550 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 07/19/19 | 556 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 07/19/19 | 560 | Rivera, Eli P |  | 484.2
PR | 995 | 07/19/19 | 570 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 07/19/19 | 585 | Donelson, Richard T |  | 25.22
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 07/26/19 | 614 | Balderas Ortiz, Ricardo I |  | 387.36
PR | 995 | 07/26/19 | 617 | Belcher, Jacob T |  | 129.12
PR | 995 | 07/26/19 | 618 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 07/26/19 | 622 | Chevez, Herson G |  | 371.22
PR | 995 | 07/26/19 | 624 | Cortes Mendiola, Victor H |  | 742.44
PR | 995 | 07/26/19 | 625 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 07/26/19 | 642 | Hoeg, Xavier A |  | 109.75
PR | 995 | 07/26/19 | 646 | Hubbard, Robert W |  | 80.7
PR | 995 | 07/26/19 | 646 | Hubbard, Robert W |  | 100.88
PR | 995 | 07/26/19 | 652 | Lovo, German G |  | 294.15
PR | 995 | 07/26/19 | 653 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 07/26/19 | 659 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 07/26/19 | 663 | Rivera, Eli P |  | 484.2
PR | 995 | 07/26/19 | 673 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 66.58
PR | 995 | 08/02/19 | 6 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 08/02/19 | 10 | Benites Portillo, Marvin E |  | 403.1
PR | 995 | 08/02/19 | 14 | Chevez, Herson G |  | 371.22
PR | 995 | 08/02/19 | 16 | Cortes Mendiola, Victor H |  | 464.03
PR | 995 | 08/02/19 | 16 | Cortes Mendiola, Victor H |  | 222.73
PR | 995 | 08/02/19 | 17 | Cortes Sepulveda, Jose R |  | 447.89
PR | 995 | 08/02/19 | 38 | Hubbard, Robert W |  | 60.53
PR | 995 | 08/02/19 | 38 | Hubbard, Robert W |  | 80.7
PR | 995 | 08/02/19 | 44 | Lovo, German G |  | 435.78
PR | 995 | 08/02/19 | 45 | Lucas Tzintzun, Rafael |  | 305.05
PR | 995 | 08/02/19 | 51 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 08/02/19 | 55 | Rivera, Eli P |  | 484.2
PR | 995 | 08/02/19 | 64 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 08/09/19 | 258 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 08/09/19 | 262 | Benites Portillo, Marvin E |  | 403.1
PR | 995 | 08/09/19 | 266 | Chevez, Herson G |  | 296.98
PR | 995 | 08/09/19 | 266 | Chevez, Herson G |  | 74.24
PR | 995 | 08/09/19 | 268 | Cortes Mendiola, Victor H |  | 556.83
PR | 995 | 08/09/19 | 268 | Cortes Mendiola, Victor H |  | 185.61
PR | 995 | 08/09/19 | 269 | Cortes Sepulveda, Jose R |  | 290.52
PR | 995 | 08/09/19 | 269 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 08/09/19 | 279 | Galdamez, Dagoberto A |  | 193.68
PR | 995 | 08/09/19 | 279 | Galdamez, Dagoberto A |  | 96.84
PR | 995 | 08/09/19 | 291 | Hubbard, Robert W |  | 80.7
PR | 995 | 08/09/19 | 297 | Lovo, German G |  | 348.62
PR | 995 | 08/09/19 | 297 | Lovo, German G |  | 87.16
PR | 995 | 08/09/19 | 298 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 08/09/19 | 298 | Lucas Tzintzun, Rafael |  | 67.79
PR | 995 | 08/09/19 | 304 | Portillo Soriano, Walter A |  | 284.06
PR | 995 | 08/09/19 | 308 | Rivera, Eli P |  | 96.84
PR | 995 | 08/09/19 | 308 | Rivera, Eli P |  | 290.52
PR | 995 | 08/09/19 | 317 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 08/09/19 | 317 | Sorto Regalado, Milton J |  | 51.65
PR | 995 | 08/16/19 | 565 | Balderas Ortiz, Ricardo I |  | 413.18
PR | 995 | 08/16/19 | 569 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 08/16/19 | 573 | Chevez, Herson G |  | 371.22
PR | 995 | 08/16/19 | 575 | Cortes Mendiola, Victor H |  | 742.44
PR | 995 | 08/16/19 | 576 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 08/16/19 | 586 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 08/16/19 | 604 | Lovo, German G |  | 174.31
PR | 995 | 08/16/19 | 604 | Lovo, German G |  | 261.47
PR | 995 | 08/16/19 | 605 | Lucas Tzintzun, Rafael |  | 135.58
PR | 995 | 08/16/19 | 605 | Lucas Tzintzun, Rafael |  | 203.36
PR | 995 | 08/16/19 | 611 | Portillo Soriano, Walter A |  | 142.03
PR | 995 | 08/16/19 | 611 | Portillo Soriano, Walter A |  | 213.05
PR | 995 | 08/16/19 | 615 | Rivera, Eli P |  | 193.68
PR | 995 | 08/16/19 | 615 | Rivera, Eli P |  | 290.52
PR | 995 | 08/16/19 | 621 | Sanders, Allen O |  | 39.54
PR | 995 | 08/16/19 | 624 | Sorto Regalado, Milton J |  | 103.3
PR | 995 | 08/16/19 | 624 | Sorto Regalado, Milton J |  | 154.94
PR | 995 | 08/16/19 | 636 | Donelson, Richard T |  | 75.66
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 08/23/19 | 801 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 08/23/19 | 805 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 08/23/19 | 809 | Chevez, Herson G |  | 371.22
PR | 995 | 08/23/19 | 811 | Cortes Mendiola, Victor H |  | 742.44
PR | 995 | 08/23/19 | 812 | Cortes Sepulveda, Jose R |  | 387.36
PR | 995 | 08/23/19 | 812 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 08/23/19 | 822 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 08/23/19 | 835 | Hubbard, Robert W |  | 40.35
PR | 995 | 08/23/19 | 835 | Hubbard, Robert W |  | 40.35
PR | 995 | 08/23/19 | 841 | Lovo, German G |  | 87.16
PR | 995 | 08/23/19 | 841 | Lovo, German G |  | 87.16
PR | 995 | 08/23/19 | 842 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 08/23/19 | 848 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 08/23/19 | 852 | Rivera, Eli P |  | 484.2
PR | 995 | 08/23/19 | 861 | Sorto Regalado, Milton J |  | 206.59
PR | 995 | 08/30/19 | 992 | Balderas Ortiz, Ricardo I |  | 413.18
PR | 995 | 08/30/19 | 996 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 08/30/19 | 1000 | Chevez, Herson G |  | 371.22
PR | 995 | 08/30/19 | 1002 | Cortes Mendiola, Victor H |  | 445.46
PR | 995 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R |  | 290.52
PR | 995 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 08/30/19 | 1013 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 08/30/19 | 1026 | Hubbard, Robert W |  | 100.88
PR | 995 | 08/30/19 | 1026 | Hubbard, Robert W |  | 20.18
PR | 995 | 08/30/19 | 1032 | Lovo, German G |  | 87.16
PR | 995 | 08/30/19 | 1033 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 08/30/19 | 1039 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 08/30/19 | 1043 | Rivera, Eli P |  | 290.52
PR | 995 | 08/30/19 | 1043 | Rivera, Eli P |  | 193.68
PR | 995 | 08/30/19 | 1052 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 25.22
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 50.44
PR | 995 | 09/06/19 | 13 | Balderas Ortiz, Ricardo I |  | 206.59
PR | 995 | 09/06/19 | 17 | Benites Portillo, Marvin E |  | 348.62
PR | 995 | 09/06/19 | 21 | Chevez, Herson G |  | 296.98
PR | 995 | 09/06/19 | 23 | Cortes Mendiola, Victor H |  | 556.83
PR | 995 | 09/06/19 | 23 | Cortes Mendiola, Victor H |  | 37.12
PR | 995 | 09/06/19 | 24 | Cortes Sepulveda, Jose R |  | 290.52
PR | 995 | 09/06/19 | 24 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 09/06/19 | 34 | Galdamez, Dagoberto A |  | 290.52
PR | 995 | 09/06/19 | 47 | Hubbard, Robert W |  | 121.05
PR | 995 | 09/06/19 | 47 | Hubbard, Robert W |  | 100.88
PR | 995 | 09/06/19 | 53 | Lovo, German G |  | 348.62
PR | 995 | 09/06/19 | 54 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 09/06/19 | 60 | Portillo Soriano, Walter A |  | 142.03
PR | 995 | 09/06/19 | 60 | Portillo Soriano, Walter A |  | 142.03
PR | 995 | 09/06/19 | 64 | Rivera, Eli P |  | 290.52
PR | 995 | 09/06/19 | 64 | Rivera, Eli P |  | 96.84
PR | 995 | 09/06/19 | 71 | Sepulveda Gonzalez, Alfredo |  | 183.59
PR | 995 | 09/06/19 | 73 | Sorto Regalado, Milton J |  | 103.3
PR | 995 | 09/06/19 | 73 | Sorto Regalado, Milton J |  | 103.3
PR | 995 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I |  | 309.89
PR | 995 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I |  | 206.59
PR | 995 | 09/13/19 | 241 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 09/13/19 | 241 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 09/13/19 | 245 | Chevez, Herson G |  | 371.22
PR | 995 | 09/13/19 | 247 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 09/13/19 | 247 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 09/13/19 | 248 | Cortes Sepulveda, Jose R |  | 254.21
PR | 995 | 09/13/19 | 248 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 09/13/19 | 258 | Galdamez, Dagoberto A |  | 484.2
PR | 995 | 09/13/19 | 271 | Hubbard, Robert W |  | 201.75
PR | 995 | 09/13/19 | 271 | Hubbard, Robert W |  | 80.7
PR | 995 | 09/13/19 | 276 | Lovo, German G |  | 435.78
PR | 995 | 09/13/19 | 277 | Lucas Tzintzun, Rafael |  | 203.36
PR | 995 | 09/13/19 | 277 | Lucas Tzintzun, Rafael |  | 135.58
PR | 995 | 09/13/19 | 283 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 09/13/19 | 287 | Rivera, Eli P |  | 193.68
PR | 995 | 09/13/19 | 287 | Rivera, Eli P |  | 290.52
PR | 995 | 09/13/19 | 293 | Sanders, Allen O |  | 39.54
PR | 995 | 09/13/19 | 294 | Sepulveda Gonzalez, Alfredo |  | 353.06
PR | 995 | 09/13/19 | 296 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 09/20/19 | 474 | Balderas Ortiz, Ricardo I |  | 477.74
PR | 995 | 09/20/19 | 478 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 612.51
PR | 995 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 18.56
PR | 995 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 37.12
PR | 995 | 09/20/19 | 485 | Cortes Sepulveda, Jose R |  | 411.57
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 161.4
PR | 995 | 09/20/19 | 515 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 09/20/19 | 521 | Portillo Soriano, Walter A |  | 355.08
PR | 995 | 09/20/19 | 525 | Rivera, Eli P |  | 484.2
PR | 995 | 09/20/19 | 532 | Sepulveda Gonzalez, Alfredo |  | 494.29
PR | 995 | 09/20/19 | 534 | Sorto Regalado, Milton J |  | 238.87
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 44.39
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 09/27/19 | 630 | Balderas Ortiz, Ricardo I |  | 516.48
PR | 995 | 09/27/19 | 634 | Benites Portillo, Marvin E |  | 435.78
PR | 995 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 315.54
PR | 995 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 18.56
PR | 995 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 18.56
PR | 995 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 18.56
PR | 995 | 09/27/19 | 641 | Cortes Sepulveda, Jose R |  | 484.2
PR | 995 | 09/27/19 | 666 | Hubbard, Robert W |  | 60.53
PR | 995 | 09/27/19 | 674 | Lucas Tzintzun, Rafael |  | 271.15
PR | 995 | 09/27/19 | 674 | Lucas Tzintzun, Rafael |  | 67.79
PR | 995 | 09/27/19 | 680 | Portillo Soriano, Walter A |  | 142.03
PR | 995 | 09/27/19 | 684 | Rivera, Eli P |  | 193.68
PR | 995 | 09/27/19 | 690 | Sanders, Allen O |  | 39.54
PR | 995 | 09/27/19 | 691 | Sepulveda Gonzalez, Alfredo |  | 451.92
PR | 995 | 09/27/19 | 693 | Sorto Regalado, Milton J |  | 258.24
PR | 995 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I |  | 206.59
PR | 995 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I |  | 206.59
PR | 995 | 10/04/19 | 10 | Benites Portillo, Marvin E |  | 261.47
PR | 995 | 10/04/19 | 10 | Benites Portillo, Marvin E |  | 141.63
PR | 995 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 259.85
PR | 995 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 74.24
PR | 995 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 37.12
PR | 995 | 10/04/19 | 17 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 10/04/19 | 17 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 10/04/19 | 41 | Hubbard, Robert W |  | 100.88
PR | 995 | 10/04/19 | 49 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 10/04/19 | 66 | Sanders, Allen O |  | 39.54
PR | 995 | 10/04/19 | 67 | Sepulveda Gonzalez, Alfredo |  | 451.92
PR | 995 | 10/04/19 | 69 | Sorto Regalado, Milton J |  | 51.65
PR | 995 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I |  | 258.24
PR | 995 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I |  | 258.24
PR | 995 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 76.26
PR | 995 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 174.31
PR | 995 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 278.42
PR | 995 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 352.66
PR | 995 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 37.12
PR | 995 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 181.58
PR | 995 | 10/11/19 | 296 | Hubbard, Robert W |  | 40.35
PR | 995 | 10/11/19 | 304 | Lucas Tzintzun, Rafael |  | 338.94
PR | 995 | 10/11/19 | 322 | Sepulveda Gonzalez, Alfredo |  | 564.9
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 22.19
PR | 995 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I |  | 167.86
PR | 995 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I |  | 309.89
PR | 995 | 10/18/19 | 459 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 18.56
PR | 995 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 74.24
PR | 995 | 10/18/19 | 466 | Cortes Sepulveda, Jose R |  | 387.36
PR | 995 | 10/18/19 | 466 | Cortes Sepulveda, Jose R |  | 96.84
PR | 995 | 10/18/19 | 472 | Eliassen, Cory H |  | 207
PR | 995 | 10/18/19 | 477 | Gauthier, Dillon R |  | 54.88
PR | 995 | 10/18/19 | 489 | Hubbard, Robert W |  | 40.35
PR | 995 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 67.79
PR | 995 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 110.16
PR | 995 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 67.79
PR | 995 | 10/18/19 | 514 | Sanders, Allen O |  | 49.43
PR | 995 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo |  | 338.94
PR | 995 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I |  | 309.89
PR | 995 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I |  | 167.86
PR | 995 | 10/25/19 | 594 | Benites Portillo, Marvin E |  | 87.16
PR | 995 | 10/25/19 | 601 | Cortes Mendiola, Victor H |  | 371.22
PR | 995 | 10/25/19 | 602 | Cortes Sepulveda, Jose R |  | 193.68
PR | 995 | 10/25/19 | 602 | Cortes Sepulveda, Jose R |  | 157.37
PR | 995 | 10/25/19 | 607 | Eliassen, Cory H |  | 272.36
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 60.53
PR | 995 | 10/25/19 | 632 | Lucas Tzintzun, Rafael |  | 228.78
PR | 995 | 10/25/19 | 632 | Lucas Tzintzun, Rafael |  | 67.79
PR | 995 | 10/25/19 | 650 | Sanders, Allen O |  | 98.86
PR | 995 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo |  | 127.1
PR | 995 | 10/25/19 | 656 | Trower-Kelly, Fidel D |  | 138
PR | 995 | 10/25/19 | 657 | Vazquez Popoca, Jose N |  | 144.05
PR | 995 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 11/01/19 | 10 | Benites Portillo, Marvin E |  | 93.61
PR | 995 | 11/01/19 | 16 | Cortes Mendiola, Victor H |  | 322.8
PR | 995 | 11/01/19 | 16 | Cortes Mendiola, Victor H |  | 383.33
PR | 995 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 219.5
PR | 995 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 219.5
PR | 995 | 11/01/19 | 23 | Eliassen, Cory H |  | 387.36
PR | 995 | 11/01/19 | 48 | Lucas Tzintzun, Rafael |  | 154.94
PR | 995 | 11/01/19 | 66 | Sanders, Allen O |  | 43.58
PR | 995 | 11/01/19 | 67 | Sepulveda Gonzalez, Alfredo |  | 125.89
PR | 995 | 11/01/19 | 72 | Trower-Kelly, Fidel D |  | 271.15
PR | 995 | 11/01/19 | 73 | Vazquez Popoca, Jose N |  | 193.68
PR | 995 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I |  | 348.62
PR | 995 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 121.05
PR | 995 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 60.53
PR | 995 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 60.53
PR | 995 | 11/08/19 | 191 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 11/08/19 | 191 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 11/08/19 | 197 | Eliassen, Cory H |  | 290.52
PR | 995 | 11/08/19 | 240 | Sanders, Allen O |  | 65.37
PR | 995 | 11/08/19 | 246 | Trower-Kelly, Fidel D |  | 271.15
PR | 995 | 11/08/19 | 247 | Vazquez Popoca, Jose N |  | 258.24
PR | 995 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I |  | 348.62
PR | 995 | 11/15/19 | 450 | Cortes Mendiola, Victor H |  | 100.88
PR | 995 | 11/15/19 | 451 | Cortes Sepulveda, Jose R |  | 219.5
PR | 995 | 11/15/19 | 451 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 11/15/19 | 457 | Eliassen, Cory H |  | 387.36
PR | 995 | 11/15/19 | 462 | Gauthier, Dillon R |  | 232.42
PR | 995 | 11/15/19 | 499 | Sanders, Allen O |  | 152.52
PR | 995 | 11/15/19 | 505 | Trower-Kelly, Fidel D |  | 203.36
PR | 995 | 11/15/19 | 506 | Vazquez Popoca, Jose N |  | 64.56
PR | 995 | 11/15/19 | 512 | Donelson, Richard T |  | 25.22
PR | 995 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I |  | 334.1
PR | 995 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I |  | 203.36
PR | 995 | 11/22/19 | 621 | Cortes Mendiola, Victor H |  | 181.58
PR | 995 | 11/22/19 | 621 | Cortes Mendiola, Victor H |  | 60.53
PR | 995 | 11/22/19 | 622 | Cortes Sepulveda, Jose R |  | 205.79
PR | 995 | 11/22/19 | 622 | Cortes Sepulveda, Jose R |  | 192.07
PR | 995 | 11/22/19 | 628 | Eliassen, Cory H |  | 459.99
PR | 995 | 11/22/19 | 633 | Gauthier, Dillon R |  | 196.1
PR | 995 | 11/22/19 | 670 | Sanders, Allen O |  | 163.42
PR | 995 | 11/22/19 | 676 | Trower-Kelly, Fidel D |  | 321.99
PR | 995 | 11/22/19 | 684 | Donelson, Richard T |  | 25.22
PR | 995 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 11/27/19 | 855 | Cortes Mendiola, Victor H |  | 60.53
PR | 995 | 11/27/19 | 856 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 11/27/19 | 856 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 11/27/19 | 862 | Eliassen, Cory H |  | 387.36
PR | 995 | 11/27/19 | 867 | Gauthier, Dillon R |  | 217.89
PR | 995 | 11/27/19 | 904 | Sanders, Allen O |  | 152.52
PR | 995 | 11/27/19 | 910 | Trower-Kelly, Fidel D |  | 271.15
PR | 995 | 12/06/19 | 31 | Balderas Ortiz, Ricardo I |  | 464.83
PR | 995 | 12/06/19 | 42 | Cortes Sepulveda, Jose R |  | 439.01
PR | 995 | 12/06/19 | 48 | Eliassen, Cory H |  | 387.36
PR | 995 | 12/06/19 | 54 | Gauthier, Dillon R |  | 232.42
PR | 995 | 12/06/19 | 65 | Hubbard, Robert W |  | 43.58
PR | 995 | 12/06/19 | 91 | Sanders, Allen O |  | 87.16
PR | 995 | 12/06/19 | 97 | Trower-Kelly, Fidel D |  | 241.49
PR | 995 | 12/13/19 | 392 | Balderas Ortiz, Ricardo I |  | 581.04
PR | 995 | 12/13/19 | 402 | Cortes Mendiola, Victor H |  | 342.98
PR | 995 | 12/13/19 | 403 | Cortes Sepulveda, Jose R |  | 548.76
PR | 995 | 12/13/19 | 409 | Eliassen, Cory H |  | 387.36
PR | 995 | 12/13/19 | 415 | Gauthier, Dillon R |  | 290.52
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 43.58
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 21.79
PR | 995 | 12/13/19 | 452 | Sanders, Allen O |  | 130.73
PR | 995 | 12/13/19 | 458 | Trower-Kelly, Fidel D |  | 338.94
PR | 995 | 12/13/19 | 465 | Donelson, Richard T |  | 25.22
PR | 995 | 12/20/19 | 545 | Balderas Ortiz, Ricardo I |  | 581.04
PR | 995 | 12/20/19 | 555 | Cortes Mendiola, Victor H |  | 40.35
PR | 995 | 12/20/19 | 556 | Cortes Sepulveda, Jose R |  | 548.76
PR | 995 | 12/20/19 | 562 | Eliassen, Cory H |  | 290.52
PR | 995 | 12/20/19 | 568 | Gauthier, Dillon R |  | 232.42
PR | 995 | 12/20/19 | 579 | Hubbard, Robert W |  | 65.37
PR | 995 | 12/20/19 | 605 | Sanders, Allen O |  | 130.73
PR | 995 | 12/20/19 | 611 | Trower-Kelly, Fidel D |  | 338.94
PR | 995 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I |  | 261.47
PR | 995 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I |  | 87.16
PR | 995 | 12/27/19 | 713 | Cortes Sepulveda, Jose R |  | 246.94
PR | 995 | 12/27/19 | 713 | Cortes Sepulveda, Jose R |  | 82.31
PR | 995 | 12/27/19 | 720 | Eliassen, Cory H |  | 290.52
PR | 995 | 12/27/19 | 726 | Gauthier, Dillon R |  | 174.31
PR | 995 | 12/27/19 | 737 | Hubbard, Robert W |  | 43.58
PR | 995 | 12/27/19 | 763 | Sanders, Allen O |  | 108.95
PR | 995 | 12/27/19 | 769 | Trower-Kelly, Fidel D |  | 186.42
PR | 995 | 01/03/20 | 5 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 01/03/20 | 15 | Cortes Mendiola, Victor H |  | 40.35
PR | 995 | 01/03/20 | 16 | Cortes Sepulveda, Jose R |  | 178.35
PR | 995 | 01/03/20 | 23 | Eliassen, Cory H |  | 387.36
PR | 995 | 01/03/20 | 29 | Gauthier, Dillon R |  | 174.31
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 108.95
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 54.47
PR | 995 | 01/03/20 | 66 | Sanders, Allen O |  | 87.16
PR | 995 | 01/03/20 | 72 | Trower-Kelly, Fidel D |  | 203.36
PR | 995 | 01/10/20 | 278 | Balderas Ortiz, Ricardo I |  | 581.04
PR | 995 | 01/10/20 | 289 | Cortes Sepulveda, Jose R |  | 480.17
PR | 995 | 01/10/20 | 296 | Eliassen, Cory H |  | 387.36
PR | 995 | 01/10/20 | 302 | Gauthier, Dillon R |  | 87.16
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 141.63
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 43.58
PR | 995 | 01/10/20 | 339 | Sanders, Allen O |  | 54.47
PR | 995 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 203.36
PR | 995 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 29.05
PR | 995 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 192.07
PR | 995 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 27.44
PR | 995 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/17/20 | 562 | Eliassen, Cory H |  | 387.36
PR | 995 | 01/17/20 | 568 | Gauthier, Dillon R |  | 232.42
PR | 995 | 01/17/20 | 579 | Hubbard, Robert W |  | 21.79
PR | 995 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 74.24
PR | 995 | 01/17/20 | 605 | Sanders, Allen O |  | 130.73
PR | 995 | 01/17/20 | 611 | Trower-Kelly, Fidel D |  | 271.15
PR | 995 | 01/17/20 | 618 | Donelson, Richard T |  | 25.22
PR | 995 | 01/24/20 | 677 | Balderas Ortiz, Ricardo I |  | 581.04
PR | 995 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/24/20 | 695 | Eliassen, Cory H |  | 484.2
PR | 995 | 01/24/20 | 700 | Gauthier, Dillon R |  | 290.52
PR | 995 | 01/24/20 | 711 | Hubbard, Robert W |  | 108.95
PR | 995 | 01/24/20 | 736 | Sanders, Allen O |  | 54.47
PR | 995 | 01/24/20 | 742 | Trower-Kelly, Fidel D |  | 203.36
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 25.22
PR | 995 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 58.1
PR | 995 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 58.1
PR | 995 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 54.88
PR | 995 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 54.88
PR | 995 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 01/31/20 | 854 | Eliassen, Cory H |  | 484.2
PR | 995 | 01/31/20 | 860 | Gauthier, Dillon R |  | 290.52
PR | 995 | 01/31/20 | 894 | Romero Garza, Jesus I |  | 371.22
PR | 995 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 348.62
PR | 995 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 203.36
PR | 995 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 29.05
PR | 995 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 192.07
PR | 995 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 27.44
PR | 995 | 02/07/20 | 45 | Eliassen, Cory H |  | 484.2
PR | 995 | 02/07/20 | 50 | Gauthier, Dillon R |  | 174.31
PR | 995 | 02/07/20 | 88 | Sanders, Allen O |  | 21.79
PR | 995 | 02/07/20 | 102 | Donelson, Richard T |  | 50.44
PR | 995 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I |  | 246.94
PR | 995 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I |  | 101.68
PR | 995 | 02/14/20 | 248 | Cortes Sepulveda, Jose R |  | 205.79
PR | 995 | 02/14/20 | 248 | Cortes Sepulveda, Jose R |  | 123.47
PR | 995 | 02/14/20 | 255 | Eliassen, Cory H |  | 484.2
PR | 995 | 02/14/20 | 260 | Gauthier, Dillon R |  | 232.42
PR | 995 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 67.79
PR | 995 | 02/21/20 | 454 | Balderas Ortiz, Ricardo I |  | 348.62
PR | 995 | 02/21/20 | 465 | Cortes Sepulveda, Jose R |  | 329.26
PR | 995 | 02/21/20 | 471 | Eliassen, Cory H |  | 484.2
PR | 995 | 02/21/20 | 476 | Gauthier, Dillon R |  | 174.31
PR | 995 | 02/21/20 | 486 | Hubbard, Robert W |  | 130.73
PR | 995 | 02/21/20 | 486 | Hubbard, Robert W |  | 87.16
PR | 995 | 02/21/20 | 486 | Hubbard, Robert W |  | 65.37
PR | 995 | 02/21/20 | 514 | Sanders, Allen O |  | 32.68
PR | 995 | 02/21/20 | 515 | Sepulveda Gonzalez, Alfredo |  | 125.89
PR | 995 | 02/21/20 | 528 | Donelson, Richard T |  | 25.22
PR | 995 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I |  | 348.62
PR | 995 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 02/28/20 | 693 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 02/28/20 | 700 | Eliassen, Cory H |  | 484.2
PR | 995 | 02/28/20 | 705 | Gauthier, Dillon R |  | 58.1
PR | 995 | 02/28/20 | 716 | Hubbard, Robert W |  | 163.42
PR | 995 | 02/28/20 | 743 | Sanders, Allen O |  | 163.42
PR | 995 | 02/28/20 | 744 | Sepulveda Gonzalez, Alfredo |  | 125.89
PR | 995 | 02/28/20 | 757 | Donelson, Richard T |  | 50.44
PR | 995 | 03/06/20 | 63 | Eliassen, Cory H |  | 254.21
PR | 995 | 03/06/20 | 78 | Hubbard, Robert W |  | 217.89
PR | 995 | 03/06/20 | 78 | Hubbard, Robert W |  | 108.95
PR | 995 | 03/06/20 | 111 | Trower-Kelly, Fidel D |  | 182.18
PR | 995 | 03/06/20 | 119 | Donelson, Richard T |  | 25.22
PR | 995 | 03/13/20 | 306 | Amaya Gonzalez, Edilberto A |  | 87.16
PR | 995 | 03/13/20 | 309 | Balderas Ortiz, Ricardo I |  | 232.42
PR | 995 | 03/13/20 | 319 | Cortes Mendiola, Victor H |  | 121.05
PR | 995 | 03/13/20 | 320 | Cortes Sepulveda, Jose R |  | 219.5
PR | 995 | 03/13/20 | 327 | Eliassen, Cory H |  | 290.52
PR | 995 | 03/13/20 | 342 | Hubbard, Robert W |  | 196.1
PR | 995 | 03/13/20 | 342 | Hubbard, Robert W |  | 65.37
PR | 995 | 03/13/20 | 369 | Sanders, Allen O |  | 21.79
PR | 995 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 135.58
PR | 995 | 03/13/20 | 383 | Donelson, Richard T |  | 100.88
PR | 995 | 03/20/20 | 564 | Amaya Gonzalez, Edilberto A |  | 159.79
PR | 995 | 03/20/20 | 577 | Cortes Mendiola, Victor H |  | 221.93
PR | 995 | 03/20/20 | 578 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 03/20/20 | 585 | Eliassen, Cory H |  | 266.31
PR | 995 | 03/20/20 | 627 | Sanders, Allen O |  | 21.79
PR | 995 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I |  | 116.21
PR | 995 | 03/26/20 | 760 | Cortes Mendiola, Victor H |  | 121.05
PR | 995 | 03/26/20 | 761 | Cortes Sepulveda, Jose R |  | 109.75
PR | 995 | 03/26/20 | 806 | Sanders, Allen O |  | 21.79
PR | 995 | 04/17/20 | 288 | Donelson, Richard T |  | 25.22
PR | 995 | 04/24/20 | 410 | Sanders, Allen O |  | 21.79
PR | 995 | 04/24/20 | 410 | Sanders, Allen O |  | 21.79
PR | 995 | 04/24/20 | 424 | Donelson, Richard T |  | 75.66
PR | 995 | 05/01/20 | 64 | Sanders, Allen O |  | 65.37
PR | 995 | 05/01/20 | 78 | Donelson, Richard T |  | 25.22
PR | 995 | 05/15/20 | 328 | Eliassen, Cory H |  | 30.26
PR | 995 | 05/22/20 | 483 | Eliassen, Cory H |  | 24.21
PR | 995 | 06/05/20 | 31 | Eliassen, Cory H |  | 72.63
PR | 995 | 06/26/20 | 541 | Hubbard, Robert W |  | 43.58
PR | 998 | 02/02/18 | 38 | Hubbard, Robert W |  | 3.44
PR | 998 | 02/09/18 | 195 | Hubbard, Robert W |  | 6.89
PR | 998 | 03/09/18 | 184 | Gerard, Jeffrey S |  | 3.6
PR | 998 | 03/30/18 | 811 | Donelson, Richard T |  | 9.56
PR | 998 | 05/18/18 | 452 | Hubbard, Robert W |  | 3.44
PR | 998 | 05/25/18 | 806 | Donelson, Richard T |  | 38.25
PR | 998 | 06/01/18 | 75 | Donelson, Richard T |  | 23.91
PR | 998 | 06/08/18 | 339 | Donelson, Richard T |  | 57.38
PR | 998 | 06/08/18 | 340 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 06/08/18 | 340 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 06/15/18 | 527 | Donelson, Richard T |  | 28.69
PR | 998 | 06/15/18 | 528 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 06/22/18 | 753 | Donelson, Richard T |  | 14.34
PR | 998 | 06/22/18 | 754 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 06/29/18 | 950 | Cortes Sepulveda, Jose R |  | 22.03
PR | 998 | 06/29/18 | 963 | Cortes Mendiola, Victor H |  | 37.64
PR | 998 | 06/29/18 | 983 | Hubbard, Robert W |  | 30.56
PR | 998 | 06/29/18 | 1019 | Donelson, Richard T |  | 23.91
PR | 998 | 06/29/18 | 1020 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/06/18 | 38 | Hubbard, Robert W |  | 7.19
PR | 998 | 07/06/18 | 76 | Donelson, Richard T |  | 4.78
PR | 998 | 07/13/18 | 307 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 07/13/18 | 308 | Cortes Sepulveda, Jose R |  | 29.38
PR | 998 | 07/13/18 | 329 | Hubbard, Robert W |  | 14.38
PR | 998 | 07/13/18 | 367 | Donelson, Richard T |  | 14.34
PR | 998 | 07/13/18 | 368 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/20/18 | 447 | Cortes Mendiola, Victor H |  | 25.09
PR | 998 | 07/20/18 | 448 | Cortes Sepulveda, Jose R |  | 14.69
PR | 998 | 07/20/18 | 470 | Hubbard, Robert W |  | 17.98
PR | 998 | 07/20/18 | 507 | Donelson, Richard T |  | 4.78
PR | 998 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 07/27/18 | 773 | Cortes Mendiola, Victor H |  | 75.28
PR | 998 | 07/27/18 | 774 | Cortes Sepulveda, Jose R |  | 44.06
PR | 998 | 07/27/18 | 797 | Hubbard, Robert W |  | 89.89
PR | 998 | 07/27/18 | 808 | McCabe, Thomas C |  | 39.17
PR | 998 | 07/27/18 | 825 | Sepulveda Gonzalez, Alfredo |  | 37.94
PR | 998 | 07/27/18 | 834 | Donelson, Richard T |  | 4.78
PR | 998 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/03/18 | 12 | Cortes Mendiola, Victor H |  | 75.28
PR | 998 | 08/03/18 | 13 | Cortes Sepulveda, Jose R |  | 44.06
PR | 998 | 08/03/18 | 35 | Hubbard, Robert W |  | 50.34
PR | 998 | 08/03/18 | 46 | McCabe, Thomas C |  | 19.58
PR | 998 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo |  | 18.97
PR | 998 | 08/03/18 | 72 | Donelson, Richard T |  | 28.69
PR | 998 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/10/18 | 222 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 08/10/18 | 223 | Cortes Sepulveda, Jose R |  | 40.39
PR | 998 | 08/10/18 | 246 | Hubbard, Robert W |  | 17.98
PR | 998 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo |  | 30.83
PR | 998 | 08/10/18 | 283 | Donelson, Richard T |  | 52.59
PR | 998 | 08/17/18 | 490 | Cortes Mendiola, Victor H |  | 12.55
PR | 998 | 08/17/18 | 491 | Cortes Sepulveda, Jose R |  | 7.34
PR | 998 | 08/17/18 | 514 | Hubbard, Robert W |  | 7.19
PR | 998 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/24/18 | 752 | Cortes Mendiola, Victor H |  | 25.09
PR | 998 | 08/24/18 | 753 | Cortes Sepulveda, Jose R |  | 20.2
PR | 998 | 08/24/18 | 811 | Donelson, Richard T |  | 23.91
PR | 998 | 08/31/18 | 1007 | Cortes Sepulveda, Jose R |  | 7.34
PR | 998 | 08/31/18 | 1038 | Martinez Reyes, Juan C |  | 3.98
PR | 998 | 08/31/18 | 1069 | Donelson, Richard T |  | 19.13
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/07/18 | 47 | Cortes Mendiola, Victor H |  | 12.55
PR | 998 | 09/07/18 | 105 | Donelson, Richard T |  | 14.34
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/14/18 | 278 | Cortes Mendiola, Victor H |  | 25.09
PR | 998 | 09/14/18 | 279 | Cortes Sepulveda, Jose R |  | 14.69
PR | 998 | 09/14/18 | 302 | Hubbard, Robert W |  | 3.6
PR | 998 | 09/14/18 | 340 | Donelson, Richard T |  | 4.78
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/21/18 | 491 | Cortes Mendiola, Victor H |  | 6.27
PR | 998 | 09/21/18 | 492 | Cortes Sepulveda, Jose R |  | 16.52
PR | 998 | 09/21/18 | 515 | Hubbard, Robert W |  | 7.19
PR | 998 | 09/21/18 | 552 | Donelson, Richard T |  | 4.78
PR | 998 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 09/28/18 | 676 | Cortes Mendiola, Victor H |  | 34.5
PR | 998 | 09/28/18 | 677 | Cortes Sepulveda, Jose R |  | 20.2
PR | 998 | 09/28/18 | 700 | Hubbard, Robert W |  | 3.6
PR | 998 | 09/28/18 | 700 | Hubbard, Robert W |  | 10.79
PR | 998 | 09/28/18 | 739 | Donelson, Richard T |  | 14.34
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/05/18 | 40 | Cortes Mendiola, Victor H |  | 25.09
PR | 998 | 10/05/18 | 40 | Cortes Mendiola, Victor H |  | 12.55
PR | 998 | 10/05/18 | 41 | Cortes Sepulveda, Jose R |  | 14.69
PR | 998 | 10/05/18 | 41 | Cortes Sepulveda, Jose R |  | 12.85
PR | 998 | 10/05/18 | 64 | Hubbard, Robert W |  | 7.19
PR | 998 | 10/05/18 | 102 | Donelson, Richard T |  | 14.34
PR | 998 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I |  | 17.14
PR | 998 | 10/12/18 | 237 | Balderas Ortiz, Ricardo I |  | 17.14
PR | 998 | 10/12/18 | 245 | Cortes Mendiola, Victor H |  | 43.91
PR | 998 | 10/12/18 | 245 | Cortes Mendiola, Victor H |  | 56.46
PR | 998 | 10/12/18 | 246 | Cortes Sepulveda, Jose R |  | 25.7
PR | 998 | 10/12/18 | 246 | Cortes Sepulveda, Jose R |  | 33.05
PR | 998 | 10/12/18 | 265 | Gutierrez Salas, Jose |  | 11.02
PR | 998 | 10/12/18 | 265 | Gutierrez Salas, Jose |  | 11.02
PR | 998 | 10/12/18 | 270 | Hubbard, Robert W |  | 7.19
PR | 998 | 10/12/18 | 270 | Hubbard, Robert W |  | 7.19
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/19/18 | 444 | Cortes Mendiola, Victor H |  | 12.55
PR | 998 | 10/19/18 | 444 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 10/19/18 | 445 | Cortes Sepulveda, Jose R |  | 7.34
PR | 998 | 10/19/18 | 445 | Cortes Sepulveda, Jose R |  | 29.38
PR | 998 | 10/19/18 | 468 | Hubbard, Robert W |  | 34.16
PR | 998 | 10/19/18 | 507 | Donelson, Richard T |  | 23.91
PR | 998 | 10/25/18 | 687 | Hubbard, Robert W |  | 35.96
PR | 998 | 10/26/18 | 712 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 10/26/18 | 712 | Cortes Mendiola, Victor H |  | 12.55
PR | 998 | 10/26/18 | 713 | Cortes Sepulveda, Jose R |  | 29.38
PR | 998 | 10/26/18 | 713 | Cortes Sepulveda, Jose R |  | 12.85
PR | 998 | 10/26/18 | 774 | Donelson, Richard T |  | 9.56
PR | 998 | 10/26/18 | 774 | Donelson, Richard T |  | 23.91
PR | 998 | 11/02/18 | 14 | Cortes Mendiola, Victor H |  | 25.09
PR | 998 | 11/02/18 | 14 | Cortes Mendiola, Victor H |  | 43.91
PR | 998 | 11/02/18 | 15 | Cortes Sepulveda, Jose R |  | 14.69
PR | 998 | 11/02/18 | 15 | Cortes Sepulveda, Jose R |  | 25.7
PR | 998 | 11/02/18 | 76 | Donelson, Richard T |  | 9.56
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/09/18 | 192 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 11/09/18 | 193 | Cortes Sepulveda, Jose R |  | 29.38
PR | 998 | 11/09/18 | 217 | Hubbard, Robert W |  | 7.19
PR | 998 | 11/16/18 | 433 | Balderas Ortiz, Ricardo I |  | 34.27
PR | 998 | 11/16/18 | 441 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 11/16/18 | 441 | Cortes Mendiola, Victor H |  | 50.18
PR | 998 | 11/16/18 | 442 | Cortes Sepulveda, Jose R |  | 29.38
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 4.78
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I |  | 34.27
PR | 998 | 11/21/18 | 619 | Balderas Ortiz, Ricardo I |  | 34.27
PR | 998 | 11/21/18 | 627 | Cortes Mendiola, Victor H |  | 69
PR | 998 | 11/21/18 | 627 | Cortes Mendiola, Victor H |  | 31.37
PR | 998 | 11/21/18 | 650 | Hubbard, Robert W |  | 3.6
PR | 998 | 11/21/18 | 690 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I |  | 53.24
PR | 998 | 11/30/18 | 831 | Balderas Ortiz, Ricardo I |  | 17.75
PR | 998 | 11/30/18 | 839 | Cortes Mendiola, Victor H |  | 26.32
PR | 998 | 11/30/18 | 839 | Cortes Mendiola, Victor H |  | 69.08
PR | 998 | 11/30/18 | 840 | Cortes Sepulveda, Jose R |  | 21.88
PR | 998 | 11/30/18 | 840 | Cortes Sepulveda, Jose R |  | 25.86
PR | 998 | 11/30/18 | 900 | Donelson, Richard T |  | 9.56
PR | 998 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 12/07/18 | 45 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 12/07/18 | 52 | Cortes Mendiola, Victor H |  | 78.95
PR | 998 | 12/07/18 | 52 | Cortes Mendiola, Victor H |  | 52.63
PR | 998 | 12/07/18 | 53 | Cortes Sepulveda, Jose R |  | 47.74
PR | 998 | 12/07/18 | 53 | Cortes Sepulveda, Jose R |  | 31.82
PR | 998 | 12/07/18 | 113 | Donelson, Richard T |  | 4.78
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 12/14/18 | 268 | Balderas Ortiz, Ricardo I |  | 62.12
PR | 998 | 12/14/18 | 276 | Cortes Mendiola, Victor H |  | 92.11
PR | 998 | 12/14/18 | 277 | Cortes Sepulveda, Jose R |  | 55.69
PR | 998 | 12/14/18 | 337 | Donelson, Richard T |  | 14.34
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/21/18 | 509 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 12/21/18 | 517 | Cortes Mendiola, Victor H |  | 85.53
PR | 998 | 12/21/18 | 518 | Cortes Sepulveda, Jose R |  | 31.82
PR | 998 | 12/21/18 | 540 | Hubbard, Robert W |  | 11.25
PR | 998 | 12/21/18 | 577 | Donelson, Richard T |  | 4.78
PR | 998 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/28/18 | 709 | Cortes Sepulveda, Jose R |  | 9.95
PR | 998 | 12/28/18 | 768 | Donelson, Richard T |  | 4.78
PR | 998 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/11/19 | 213 | Balderas Ortiz, Ricardo I |  | 8.87
PR | 998 | 01/11/19 | 221 | Cortes Mendiola, Victor H |  | 9.87
PR | 998 | 01/11/19 | 222 | Cortes Sepulveda, Jose R |  | 21.88
PR | 998 | 01/11/19 | 244 | Hubbard, Robert W |  | 7.5
PR | 998 | 01/11/19 | 281 | Donelson, Richard T |  | 4.78
PR | 998 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/18/19 | 476 | Cortes Mendiola, Victor H |  | 16.45
PR | 998 | 01/18/19 | 476 | Cortes Mendiola, Victor H |  | 26.32
PR | 998 | 01/18/19 | 499 | Hubbard, Robert W |  | 7.5
PR | 998 | 01/18/19 | 542 | Donelson, Richard T |  | 4.78
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/25/19 | 716 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 01/25/19 | 725 | Cortes Mendiola, Victor H |  | 118.42
PR | 998 | 01/25/19 | 726 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 01/25/19 | 748 | Hubbard, Robert W |  | 11.25
PR | 998 | 01/25/19 | 786 | Donelson, Richard T |  | 23.91
PR | 998 | 02/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 02/01/19 | 13 | Cortes Mendiola, Victor H |  | 115.13
PR | 998 | 02/01/19 | 13 | Cortes Mendiola, Victor H |  | 6.58
PR | 998 | 02/01/19 | 14 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 02/01/19 | 36 | Hubbard, Robert W |  | 3.75
PR | 998 | 02/01/19 | 70 | Donelson, Richard T |  | 14.34
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 02/08/19 | 160 | Balderas Ortiz, Ricardo I |  | 53.24
PR | 998 | 02/08/19 | 168 | Cortes Mendiola, Victor H |  | 69.08
PR | 998 | 02/08/19 | 169 | Cortes Sepulveda, Jose R |  | 25.86
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/15/19 | 322 | Balderas Ortiz, Ricardo I |  | 53.24
PR | 998 | 02/15/19 | 328 | Chevez, Herson G |  | 15.3
PR | 998 | 02/15/19 | 330 | Cortes Mendiola, Victor H |  | 62.5
PR | 998 | 02/15/19 | 331 | Cortes Sepulveda, Jose R |  | 47.74
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/22/19 | 580 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 02/22/19 | 586 | Chevez, Herson G |  | 67.32
PR | 998 | 02/22/19 | 588 | Cortes Mendiola, Victor H |  | 111.84
PR | 998 | 02/22/19 | 588 | Cortes Mendiola, Victor H |  | 32.9
PR | 998 | 02/22/19 | 589 | Cortes Sepulveda, Jose R |  | 87.52
PR | 998 | 02/22/19 | 647 | Donelson, Richard T |  | 4.78
PR | 998 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 03/01/19 | 5 | Balderas Ortiz, Ricardo I |  | 73.21
PR | 998 | 03/01/19 | 6 | Barbosa, Michael S |  | 15.3
PR | 998 | 03/01/19 | 9 | Benites Portillo, Marvin E |  | 47.74
PR | 998 | 03/01/19 | 9 | Benites Portillo, Marvin E |  | 29.38
PR | 998 | 03/01/19 | 11 | Chevez, Herson G |  | 9.18
PR | 998 | 03/01/19 | 11 | Chevez, Herson G |  | 24.48
PR | 998 | 03/01/19 | 11 | Chevez, Herson G |  | 44.37
PR | 998 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 39.47
PR | 998 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 98.69
PR | 998 | 03/01/19 | 13 | Cortes Mendiola, Victor H |  | 16.45
PR | 998 | 03/01/19 | 14 | Cortes Sepulveda, Jose R |  | 65.64
PR | 998 | 03/01/19 | 14 | Cortes Sepulveda, Jose R |  | 31.82
PR | 998 | 03/01/19 | 43 | Lovo, German G |  | 34.43
PR | 998 | 03/01/19 | 59 | Rodriguez Arevalos, Christian |  | 14.08
PR | 998 | 03/01/19 | 74 | Donelson, Richard T |  | 14.34
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I |  | 29.95
PR | 998 | 03/08/19 | 247 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 03/08/19 | 251 | Benites Portillo, Marvin E |  | 75.28
PR | 998 | 03/08/19 | 253 | Chevez, Herson G |  | 20.66
PR | 998 | 03/08/19 | 253 | Chevez, Herson G |  | 61.2
PR | 998 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 49.34
PR | 998 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 95.4
PR | 998 | 03/08/19 | 255 | Cortes Mendiola, Victor H |  | 13.16
PR | 998 | 03/08/19 | 256 | Cortes Sepulveda, Jose R |  | 17.9
PR | 998 | 03/08/19 | 256 | Cortes Sepulveda, Jose R |  | 85.53
PR | 998 | 03/08/19 | 257 | Crespin Portillo, Juan D |  | 1.95
PR | 998 | 03/08/19 | 257 | Crespin Portillo, Juan D |  | 7.8
PR | 998 | 03/08/19 | 278 | Hubbard, Robert W |  | 7.5
PR | 998 | 03/08/19 | 283 | Lovo, German G |  | 76.5
PR | 998 | 03/08/19 | 298 | Rodriguez Arevalos, Christian |  | 14.08
PR | 998 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 1.95
PR | 998 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 7.8
PR | 998 | 03/08/19 | 314 | Donelson, Richard T |  | 4.78
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 6.66
PR | 998 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 53.24
PR | 998 | 03/15/19 | 494 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 03/15/19 | 497 | Belcher, Jacob T |  | 4.13
PR | 998 | 03/15/19 | 497 | Belcher, Jacob T |  | 55.08
PR | 998 | 03/15/19 | 498 | Benites Portillo, Marvin E |  | 78.95
PR | 998 | 03/15/19 | 500 | Chevez, Herson G |  | 6.89
PR | 998 | 03/15/19 | 500 | Chevez, Herson G |  | 61.2
PR | 998 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 14.8
PR | 998 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 101.97
PR | 998 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 9.87
PR | 998 | 03/15/19 | 502 | Cortes Mendiola, Victor H |  | 13.16
PR | 998 | 03/15/19 | 503 | Cortes Sepulveda, Jose R |  | 77.57
PR | 998 | 03/15/19 | 521 | Hoeg, Xavier A |  | 3.9
PR | 998 | 03/15/19 | 521 | Hoeg, Xavier A |  | 52.02
PR | 998 | 03/15/19 | 525 | Hubbard, Robert W |  | 7.5
PR | 998 | 03/15/19 | 525 | Hubbard, Robert W |  | 7.5
PR | 998 | 03/15/19 | 530 | Lovo, German G |  | 63.11
PR | 998 | 03/15/19 | 531 | Lucas Tzintzun, Rafael |  | 23.41
PR | 998 | 03/15/19 | 548 | Saules Bezanilla, Fernando |  | 31.82
PR | 998 | 03/15/19 | 562 | Donelson, Richard T |  | 4.78
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/22/19 | 708 | Balderas Ortiz, Ricardo I |  | 79.87
PR | 998 | 03/22/19 | 711 | Belcher, Jacob T |  | 10.33
PR | 998 | 03/22/19 | 711 | Belcher, Jacob T |  | 55.08
PR | 998 | 03/22/19 | 712 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 03/22/19 | 714 | Chevez, Herson G |  | 11.48
PR | 998 | 03/22/19 | 714 | Chevez, Herson G |  | 61.2
PR | 998 | 03/22/19 | 716 | Cortes Mendiola, Victor H |  | 24.67
PR | 998 | 03/22/19 | 716 | Cortes Mendiola, Victor H |  | 131.58
PR | 998 | 03/22/19 | 717 | Cortes Sepulveda, Jose R |  | 8.95
PR | 998 | 03/22/19 | 717 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 03/22/19 | 735 | Hoeg, Xavier A |  | 22.11
PR | 998 | 03/22/19 | 744 | Lovo, German G |  | 82.24
PR | 998 | 03/22/19 | 761 | Saules Bezanilla, Fernando |  | 9.18
PR | 998 | 03/22/19 | 761 | Saules Bezanilla, Fernando |  | 48.96
PR | 998 | 03/22/19 | 776 | Donelson, Richard T |  | 14.34
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I |  | 26.62
PR | 998 | 03/29/19 | 919 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 03/29/19 | 922 | Belcher, Jacob T |  | 24.79
PR | 998 | 03/29/19 | 922 | Belcher, Jacob T |  | 55.08
PR | 998 | 03/29/19 | 923 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 03/29/19 | 923 | Benites Portillo, Marvin E |  | 73.44
PR | 998 | 03/29/19 | 925 | Chevez, Herson G |  | 27.54
PR | 998 | 03/29/19 | 925 | Chevez, Herson G |  | 61.2
PR | 998 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 49.34
PR | 998 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 9.87
PR | 998 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 115.13
PR | 998 | 03/29/19 | 927 | Cortes Mendiola, Victor H |  | 6.58
PR | 998 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 23.87
PR | 998 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 11.93
PR | 998 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 47.74
PR | 998 | 03/29/19 | 928 | Cortes Sepulveda, Jose R |  | 31.82
PR | 998 | 03/29/19 | 947 | Hoeg, Xavier A |  | 48.12
PR | 998 | 03/29/19 | 951 | Hubbard, Robert W |  | 5.62
PR | 998 | 03/29/19 | 956 | Lovo, German G |  | 8.61
PR | 998 | 03/29/19 | 956 | Lovo, German G |  | 78.41
PR | 998 | 03/29/19 | 957 | Lucas Tzintzun, Rafael |  | 24.79
PR | 998 | 03/29/19 | 957 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 31.82
PR | 998 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | -31.82
PR | 998 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 22.03
PR | 998 | 03/29/19 | 973 | Saules Bezanilla, Fernando |  | 48.96
PR | 998 | 03/29/19 | 977 | Sorto Regalado, Milton J |  | 22.03
PR | 998 | 03/29/19 | 977 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 03/29/19 | 989 | Donelson, Richard T |  | 14.34
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I |  | 19.97
PR | 998 | 04/05/19 | 81 | Balderas Ortiz, Ricardo I |  | 68.77
PR | 998 | 04/05/19 | 84 | Belcher, Jacob T |  | 55.08
PR | 998 | 04/05/19 | 85 | Benites Portillo, Marvin E |  | 8.26
PR | 998 | 04/05/19 | 85 | Benites Portillo, Marvin E |  | 64.26
PR | 998 | 04/05/19 | 87 | Chevez, Herson G |  | 22.95
PR | 998 | 04/05/19 | 87 | Chevez, Herson G |  | 61.2
PR | 998 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 4.93
PR | 998 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 39.47
PR | 998 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 111.84
PR | 998 | 04/05/19 | 89 | Cortes Mendiola, Victor H |  | 3.29
PR | 998 | 04/05/19 | 90 | Cortes Sepulveda, Jose R |  | 11.93
PR | 998 | 04/05/19 | 90 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 04/05/19 | 110 | Hoeg, Xavier A |  | 44.22
PR | 998 | 04/05/19 | 114 | Hubbard, Robert W |  | 7.5
PR | 998 | 04/05/19 | 119 | Lovo, German G |  | 8.61
PR | 998 | 04/05/19 | 119 | Lovo, German G |  | 76.5
PR | 998 | 04/05/19 | 120 | Lucas Tzintzun, Rafael |  | 20.66
PR | 998 | 04/05/19 | 120 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 04/05/19 | 136 | Saules Bezanilla, Fernando |  | 14.69
PR | 998 | 04/05/19 | 136 | Saules Bezanilla, Fernando |  | 48.96
PR | 998 | 04/05/19 | 140 | Sorto Regalado, Milton J |  | 18.36
PR | 998 | 04/05/19 | 140 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 04/05/19 | 151 | Donelson, Richard T |  | 4.78
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 04/12/19 | 325 | Balderas Ortiz, Ricardo I |  | 88.74
PR | 998 | 04/12/19 | 328 | Belcher, Jacob T |  | 2.07
PR | 998 | 04/12/19 | 328 | Belcher, Jacob T |  | 55.08
PR | 998 | 04/12/19 | 329 | Benites Portillo, Marvin E |  | 73.44
PR | 998 | 04/12/19 | 331 | Chevez, Herson G |  | 2.3
PR | 998 | 04/12/19 | 331 | Chevez, Herson G |  | 61.2
PR | 998 | 04/12/19 | 333 | Cortes Mendiola, Victor H |  | 105.57
PR | 998 | 04/12/19 | 333 | Cortes Mendiola, Victor H |  | 14.08
PR | 998 | 04/12/19 | 334 | Cortes Sepulveda, Jose R |  | 2.98
PR | 998 | 04/12/19 | 334 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 04/12/19 | 353 | Hoeg, Xavier A |  | 1.95
PR | 998 | 04/12/19 | 353 | Hoeg, Xavier A |  | 52.02
PR | 998 | 04/12/19 | 357 | Hubbard, Robert W |  | 7.65
PR | 998 | 04/12/19 | 363 | Lovo, German G |  | 2.87
PR | 998 | 04/12/19 | 363 | Lovo, German G |  | 76.5
PR | 998 | 04/12/19 | 364 | Lucas Tzintzun, Rafael |  | 2.07
PR | 998 | 04/12/19 | 364 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 04/12/19 | 384 | Sorto Regalado, Milton J |  | 1.84
PR | 998 | 04/12/19 | 384 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I |  | 35.5
PR | 998 | 04/19/19 | 522 | Balderas Ortiz, Ricardo I |  | 53.24
PR | 998 | 04/19/19 | 525 | Belcher, Jacob T |  | 55.08
PR | 998 | 04/19/19 | 526 | Benites Portillo, Marvin E |  | 58.75
PR | 998 | 04/19/19 | 528 | Chevez, Herson G |  | 36.72
PR | 998 | 04/19/19 | 530 | Cortes Mendiola, Victor H |  | 133.72
PR | 998 | 04/19/19 | 531 | Cortes Sepulveda, Jose R |  | 79.56
PR | 998 | 04/19/19 | 551 | Hoeg, Xavier A |  | 41.62
PR | 998 | 04/19/19 | 561 | Lovo, German G |  | 61.2
PR | 998 | 04/19/19 | 561 | Lovo, German G |  | 15.3
PR | 998 | 04/19/19 | 562 | Lucas Tzintzun, Rafael |  | 44.06
PR | 998 | 04/19/19 | 582 | Sorto Regalado, Milton J |  | 9.79
PR | 998 | 04/19/19 | 596 | Donelson, Richard T |  | 9.56
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 04/26/19 | 742 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 04/26/19 | 745 | Belcher, Jacob T |  | 13.77
PR | 998 | 04/26/19 | 745 | Belcher, Jacob T |  | 61.2
PR | 998 | 04/26/19 | 746 | Benites Portillo, Marvin E |  | 78.49
PR | 998 | 04/26/19 | 748 | Chevez, Herson G |  | 15.84
PR | 998 | 04/26/19 | 748 | Chevez, Herson G |  | 70.38
PR | 998 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 31.67
PR | 998 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 98.53
PR | 998 | 04/26/19 | 750 | Cortes Mendiola, Victor H |  | 31.67
PR | 998 | 04/26/19 | 751 | Cortes Sepulveda, Jose R |  | 20.66
PR | 998 | 04/26/19 | 751 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 04/26/19 | 762 | Galdamez, Dagoberto A |  | 55.08
PR | 998 | 04/26/19 | 770 | Hoeg, Xavier A |  | 41.62
PR | 998 | 04/26/19 | 774 | Hubbard, Robert W |  | 7.65
PR | 998 | 04/26/19 | 780 | Lovo, German G |  | 66.1
PR | 998 | 04/26/19 | 781 | Lucas Tzintzun, Rafael |  | 14.46
PR | 998 | 04/26/19 | 781 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 04/26/19 | 787 | Portillo Soriano, Walter A |  | 15.15
PR | 998 | 04/26/19 | 787 | Portillo Soriano, Walter A |  | 40.39
PR | 998 | 04/26/19 | 791 | Rivera, Eli P |  | 20.66
PR | 998 | 04/26/19 | 791 | Rivera, Eli P |  | 55.08
PR | 998 | 04/26/19 | 812 | Donelson, Richard T |  | 9.56
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 05/03/19 | 9 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 05/03/19 | 12 | Belcher, Jacob T |  | 13.77
PR | 998 | 05/03/19 | 12 | Belcher, Jacob T |  | 61.2
PR | 998 | 05/03/19 | 13 | Benites Portillo, Marvin E |  | 80.55
PR | 998 | 05/03/19 | 15 | Chevez, Herson G |  | 15.84
PR | 998 | 05/03/19 | 15 | Chevez, Herson G |  | 70.38
PR | 998 | 05/03/19 | 17 | Cortes Mendiola, Victor H |  | 140.76
PR | 998 | 05/03/19 | 18 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 05/03/19 | 30 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 05/03/19 | 38 | Hoeg, Xavier A |  | 52.02
PR | 998 | 05/03/19 | 42 | Hubbard, Robert W |  | 8.61
PR | 998 | 05/03/19 | 42 | Hubbard, Robert W |  | 22.95
PR | 998 | 05/03/19 | 42 | Hubbard, Robert W |  | 11.48
PR | 998 | 05/03/19 | 49 | Lovo, German G |  | 82.62
PR | 998 | 05/03/19 | 50 | Lucas Tzintzun, Rafael |  | 14.46
PR | 998 | 05/03/19 | 50 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 05/03/19 | 56 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 05/03/19 | 60 | Rivera, Eli P |  | 17.21
PR | 998 | 05/03/19 | 60 | Rivera, Eli P |  | 91.8
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/10/19 | 162 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 05/10/19 | 165 | Belcher, Jacob T |  | 61.2
PR | 998 | 05/10/19 | 166 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 05/10/19 | 168 | Chevez, Herson G |  | 70.38
PR | 998 | 05/10/19 | 170 | Cortes Mendiola, Victor H |  | 73.9
PR | 998 | 05/10/19 | 170 | Cortes Mendiola, Victor H |  | 10.56
PR | 998 | 05/10/19 | 171 | Cortes Sepulveda, Jose R |  | 55.08
PR | 998 | 05/10/19 | 171 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 05/10/19 | 183 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 05/10/19 | 191 | Hoeg, Xavier A |  | 52.02
PR | 998 | 05/10/19 | 195 | Hubbard, Robert W |  | 22.95
PR | 998 | 05/10/19 | 195 | Hubbard, Robert W |  | 22.95
PR | 998 | 05/10/19 | 202 | Lovo, German G |  | 82.62
PR | 998 | 05/10/19 | 203 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 05/10/19 | 209 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 05/10/19 | 213 | Rivera, Eli P |  | 73.44
PR | 998 | 05/10/19 | 234 | Donelson, Richard T |  | 9.56
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/17/19 | 393 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 05/17/19 | 396 | Belcher, Jacob T |  | 48.96
PR | 998 | 05/17/19 | 397 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 05/17/19 | 400 | Chevez, Herson G |  | 70.38
PR | 998 | 05/17/19 | 402 | Cortes Mendiola, Victor H |  | 123.17
PR | 998 | 05/17/19 | 402 | Cortes Mendiola, Victor H |  | 17.6
PR | 998 | 05/17/19 | 403 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 05/17/19 | 415 | Galdamez, Dagoberto A |  | 55.08
PR | 998 | 05/17/19 | 415 | Galdamez, Dagoberto A |  | 36.72
PR | 998 | 05/17/19 | 423 | Hoeg, Xavier A |  | 52.02
PR | 998 | 05/17/19 | 427 | Hubbard, Robert W |  | 7.65
PR | 998 | 05/17/19 | 434 | Lovo, German G |  | 76.42
PR | 998 | 05/17/19 | 435 | Lucas Tzintzun, Rafael |  | 61.05
PR | 998 | 05/17/19 | 441 | Portillo Soriano, Walter A |  | 53.86
PR | 998 | 05/17/19 | 441 | Portillo Soriano, Walter A |  | 13.46
PR | 998 | 05/17/19 | 445 | Rivera, Eli P |  | 91.8
PR | 998 | 05/17/19 | 454 | Sorto Regalado, Milton J |  | 19.58
PR | 998 | 05/17/19 | 467 | Donelson, Richard T |  | 4.78
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 6.31
PR | 998 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 05/24/19 | 606 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 05/24/19 | 609 | Belcher, Jacob T |  | 57.38
PR | 998 | 05/24/19 | 612 | Chevez, Herson G |  | 15.84
PR | 998 | 05/24/19 | 612 | Chevez, Herson G |  | 70.38
PR | 998 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 31.67
PR | 998 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 116.13
PR | 998 | 05/24/19 | 614 | Cortes Mendiola, Victor H |  | 24.63
PR | 998 | 05/24/19 | 615 | Cortes Sepulveda, Jose R |  | 20.66
PR | 998 | 05/24/19 | 615 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 05/24/19 | 627 | Galdamez, Dagoberto A |  | 73.44
PR | 998 | 05/24/19 | 635 | Hoeg, Xavier A |  | 52.02
PR | 998 | 05/24/19 | 639 | Hubbard, Robert W |  | 22.95
PR | 998 | 05/24/19 | 639 | Hubbard, Robert W |  | 7.65
PR | 998 | 05/24/19 | 646 | Lovo, German G |  | 82.62
PR | 998 | 05/24/19 | 647 | Lucas Tzintzun, Rafael |  | 14.46
PR | 998 | 05/24/19 | 647 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 05/24/19 | 653 | Portillo Soriano, Walter A |  | 15.15
PR | 998 | 05/24/19 | 653 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 05/24/19 | 657 | Rivera, Eli P |  | 20.66
PR | 998 | 05/24/19 | 657 | Rivera, Eli P |  | 91.8
PR | 998 | 05/24/19 | 666 | Sorto Regalado, Milton J |  | 11.02
PR | 998 | 05/24/19 | 666 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 05/24/19 | 680 | Donelson, Richard T |  | 4.78
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 6.31
PR | 998 | 05/31/19 | 879 | Balderas Ortiz, Ricardo I |  | 78.34
PR | 998 | 05/31/19 | 882 | Belcher, Jacob T |  | 48.96
PR | 998 | 05/31/19 | 883 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 05/31/19 | 886 | Chevez, Herson G |  | 56.3
PR | 998 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 77.42
PR | 998 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 21.11
PR | 998 | 05/31/19 | 888 | Cortes Mendiola, Victor H |  | 14.08
PR | 998 | 05/31/19 | 889 | Cortes Sepulveda, Jose R |  | 66.56
PR | 998 | 05/31/19 | 901 | Galdamez, Dagoberto A |  | 66.56
PR | 998 | 05/31/19 | 901 | Galdamez, Dagoberto A |  | 6.89
PR | 998 | 05/31/19 | 909 | Hoeg, Xavier A |  | 41.62
PR | 998 | 05/31/19 | 913 | Hubbard, Robert W |  | 3.83
PR | 998 | 05/31/19 | 913 | Hubbard, Robert W |  | 15.3
PR | 998 | 05/31/19 | 920 | Lovo, German G |  | 59.9
PR | 998 | 05/31/19 | 921 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 05/31/19 | 927 | Portillo Soriano, Walter A |  | 26.93
PR | 998 | 05/31/19 | 931 | Rivera, Eli P |  | 73.44
PR | 998 | 05/31/19 | 940 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 05/31/19 | 952 | Donelson, Richard T |  | 4.78
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 06/07/19 | 181 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 06/07/19 | 184 | Belcher, Jacob T |  | 61.2
PR | 998 | 06/07/19 | 185 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 06/07/19 | 188 | Chevez, Herson G |  | 70.38
PR | 998 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 35.19
PR | 998 | 06/07/19 | 190 | Cortes Mendiola, Victor H |  | 35.19
PR | 998 | 06/07/19 | 191 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 06/07/19 | 203 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 06/07/19 | 211 | Hoeg, Xavier A |  | 52.02
PR | 998 | 06/07/19 | 215 | Hubbard, Robert W |  | 7.65
PR | 998 | 06/07/19 | 221 | Lovo, German G |  | 66.1
PR | 998 | 06/07/19 | 222 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 06/07/19 | 223 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 06/07/19 | 228 | Portillo Soriano, Walter A |  | 40.39
PR | 998 | 06/07/19 | 232 | Rivera, Eli P |  | 91.8
PR | 998 | 06/07/19 | 242 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 06/07/19 | 254 | Donelson, Richard T |  | 23.91
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/14/19 | 452 | Balderas Ortiz, Ricardo I |  | 95.47
PR | 998 | 06/14/19 | 455 | Belcher, Jacob T |  | 48.2
PR | 998 | 06/14/19 | 456 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 06/14/19 | 456 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 06/14/19 | 460 | Cortes Mendiola, Victor H |  | 140.76
PR | 998 | 06/14/19 | 461 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 06/14/19 | 467 | Draves, Steven W |  | 18.59
PR | 998 | 06/14/19 | 468 | Eisenhauer, Tommy J |  | 19.28
PR | 998 | 06/14/19 | 469 | Eliassen, Cory H |  | 18.59
PR | 998 | 06/14/19 | 471 | Galdamez, Dagoberto A |  | 73.44
PR | 998 | 06/14/19 | 471 | Galdamez, Dagoberto A |  | 18.36
PR | 998 | 06/14/19 | 474 | Gerard, Jordan E |  | 20.66
PR | 998 | 06/14/19 | 479 | Hoeg, Xavier A |  | 40.97
PR | 998 | 06/14/19 | 482 | Hubbard, Justin A |  | 11.93
PR | 998 | 06/14/19 | 483 | Hubbard, Robert W |  | 11.48
PR | 998 | 06/14/19 | 490 | Lovo, German G |  | 33.05
PR | 998 | 06/14/19 | 490 | Lovo, German G |  | 49.57
PR | 998 | 06/14/19 | 491 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 06/14/19 | 497 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 06/14/19 | 501 | Rivera, Eli P |  | 91.8
PR | 998 | 06/14/19 | 503 | Roberts, Lake A |  | 11.48
PR | 998 | 06/14/19 | 510 | Sorto Regalado, Milton J |  | 47.74
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 4.78
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/21/19 | 620 | Balderas Ortiz, Ricardo I |  | 88.13
PR | 998 | 06/21/19 | 623 | Belcher, Jacob T |  | 48.96
PR | 998 | 06/21/19 | 624 | Benites Portillo, Marvin E |  | 49.57
PR | 998 | 06/21/19 | 624 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 06/21/19 | 628 | Chevez, Herson G |  | 70.38
PR | 998 | 06/21/19 | 630 | Cortes Mendiola, Victor H |  | 105.57
PR | 998 | 06/21/19 | 630 | Cortes Mendiola, Victor H |  | 35.19
PR | 998 | 06/21/19 | 631 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 06/21/19 | 642 | Galdamez, Dagoberto A |  | 55.08
PR | 998 | 06/21/19 | 642 | Galdamez, Dagoberto A |  | 36.72
PR | 998 | 06/21/19 | 650 | Hoeg, Xavier A |  | 52.02
PR | 998 | 06/21/19 | 654 | Hubbard, Robert W |  | 22.95
PR | 998 | 06/21/19 | 661 | Lovo, German G |  | 61.97
PR | 998 | 06/21/19 | 661 | Lovo, German G |  | 20.66
PR | 998 | 06/21/19 | 662 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 06/21/19 | 668 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 06/21/19 | 672 | Rivera, Eli P |  | 68.85
PR | 998 | 06/21/19 | 672 | Rivera, Eli P |  | 18.36
PR | 998 | 06/21/19 | 672 | Rivera, Eli P |  | 4.59
PR | 998 | 06/21/19 | 681 | Sorto Regalado, Milton J |  | 44.06
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 4.78
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/28/19 | 838 | Balderas Ortiz, Ricardo I |  | 78.34
PR | 998 | 06/28/19 | 841 | Belcher, Jacob T |  | 61.2
PR | 998 | 06/28/19 | 842 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 06/28/19 | 842 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 06/28/19 | 846 | Chevez, Herson G |  | 70.38
PR | 998 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 105.57
PR | 998 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 17.6
PR | 998 | 06/28/19 | 848 | Cortes Mendiola, Victor H |  | 17.6
PR | 998 | 06/28/19 | 849 | Cortes Sepulveda, Jose R |  | 55.08
PR | 998 | 06/28/19 | 849 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 06/28/19 | 860 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 06/28/19 | 868 | Hoeg, Xavier A |  | 41.62
PR | 998 | 06/28/19 | 878 | Lovo, German G |  | 82.62
PR | 998 | 06/28/19 | 879 | Lucas Tzintzun, Rafael |  | 57.83
PR | 998 | 06/28/19 | 885 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 06/28/19 | 889 | Rivera, Eli P |  | 91.8
PR | 998 | 06/28/19 | 898 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 06/28/19 | 910 | Donelson, Richard T |  | 4.78
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/05/19 | 10 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 07/05/19 | 13 | Belcher, Jacob T |  | 61.2
PR | 998 | 07/05/19 | 14 | Benites Portillo, Marvin E |  | 70.23
PR | 998 | 07/05/19 | 18 | Chevez, Herson G |  | 70.38
PR | 998 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 21.11
PR | 998 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 112.61
PR | 998 | 07/05/19 | 20 | Cortes Mendiola, Victor H |  | 7.04
PR | 998 | 07/05/19 | 21 | Cortes Sepulveda, Jose R |  | 71.15
PR | 998 | 07/05/19 | 32 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 07/05/19 | 40 | Hoeg, Xavier A |  | 46.82
PR | 998 | 07/05/19 | 42 | Hubbard, Dustin R |  | 11.48
PR | 998 | 07/05/19 | 50 | Lovo, German G |  | 80.55
PR | 998 | 07/05/19 | 51 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 07/05/19 | 57 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 07/05/19 | 61 | Rivera, Eli P |  | 91.8
PR | 998 | 07/05/19 | 69 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 4.78
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/12/19 | 280 | Balderas Ortiz, Ricardo I |  | 78.34
PR | 998 | 07/12/19 | 283 | Belcher, Jacob T |  | 48.96
PR | 998 | 07/12/19 | 284 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 07/12/19 | 288 | Chevez, Herson G |  | 56.3
PR | 998 | 07/12/19 | 290 | Cortes Mendiola, Victor H |  | 56.3
PR | 998 | 07/12/19 | 290 | Cortes Mendiola, Victor H |  | 56.3
PR | 998 | 07/12/19 | 291 | Cortes Sepulveda, Jose R |  | 73.44
PR | 998 | 07/12/19 | 301 | Galdamez, Dagoberto A |  | 73.44
PR | 998 | 07/12/19 | 309 | Hoeg, Xavier A |  | 41.62
PR | 998 | 07/12/19 | 313 | Hubbard, Robert W |  | 21.04
PR | 998 | 07/12/19 | 319 | Lovo, German G |  | 66.1
PR | 998 | 07/12/19 | 320 | Lucas Tzintzun, Rafael |  | 49.8
PR | 998 | 07/12/19 | 326 | Portillo Soriano, Walter A |  | 53.86
PR | 998 | 07/12/19 | 330 | Rivera, Eli P |  | 73.44
PR | 998 | 07/12/19 | 340 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 07/12/19 | 341 | Stahlschmidt, John P |  | 46.51
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/19/19 | 510 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 07/19/19 | 513 | Belcher, Jacob T |  | 61.2
PR | 998 | 07/19/19 | 514 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 07/19/19 | 518 | Chevez, Herson G |  | 70.38
PR | 998 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 84.46
PR | 998 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 42.23
PR | 998 | 07/19/19 | 520 | Cortes Mendiola, Victor H |  | 14.08
PR | 998 | 07/19/19 | 521 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 07/19/19 | 531 | Galdamez, Dagoberto A |  | 36.72
PR | 998 | 07/19/19 | 539 | Hoeg, Xavier A |  | 52.02
PR | 998 | 07/19/19 | 549 | Lovo, German G |  | 82.62
PR | 998 | 07/19/19 | 550 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 07/19/19 | 556 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 07/19/19 | 560 | Rivera, Eli P |  | 91.8
PR | 998 | 07/19/19 | 570 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 07/19/19 | 585 | Donelson, Richard T |  | 4.78
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 614 | Balderas Ortiz, Ricardo I |  | 73.44
PR | 998 | 07/26/19 | 617 | Belcher, Jacob T |  | 24.48
PR | 998 | 07/26/19 | 618 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 07/26/19 | 622 | Chevez, Herson G |  | 70.38
PR | 998 | 07/26/19 | 624 | Cortes Mendiola, Victor H |  | 140.76
PR | 998 | 07/26/19 | 625 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 07/26/19 | 642 | Hoeg, Xavier A |  | 20.81
PR | 998 | 07/26/19 | 646 | Hubbard, Robert W |  | 15.3
PR | 998 | 07/26/19 | 646 | Hubbard, Robert W |  | 19.13
PR | 998 | 07/26/19 | 652 | Lovo, German G |  | 55.77
PR | 998 | 07/26/19 | 653 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 07/26/19 | 659 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 07/26/19 | 663 | Rivera, Eli P |  | 91.8
PR | 998 | 07/26/19 | 673 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/02/19 | 6 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 08/02/19 | 10 | Benites Portillo, Marvin E |  | 76.42
PR | 998 | 08/02/19 | 14 | Chevez, Herson G |  | 70.38
PR | 998 | 08/02/19 | 16 | Cortes Mendiola, Victor H |  | 87.98
PR | 998 | 08/02/19 | 16 | Cortes Mendiola, Victor H |  | 42.23
PR | 998 | 08/02/19 | 17 | Cortes Sepulveda, Jose R |  | 84.92
PR | 998 | 08/02/19 | 38 | Hubbard, Robert W |  | 11.48
PR | 998 | 08/02/19 | 38 | Hubbard, Robert W |  | 15.3
PR | 998 | 08/02/19 | 44 | Lovo, German G |  | 82.62
PR | 998 | 08/02/19 | 45 | Lucas Tzintzun, Rafael |  | 57.83
PR | 998 | 08/02/19 | 51 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 08/02/19 | 55 | Rivera, Eli P |  | 91.8
PR | 998 | 08/02/19 | 64 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 08/09/19 | 258 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 08/09/19 | 262 | Benites Portillo, Marvin E |  | 76.42
PR | 998 | 08/09/19 | 266 | Chevez, Herson G |  | 56.3
PR | 998 | 08/09/19 | 266 | Chevez, Herson G |  | 14.08
PR | 998 | 08/09/19 | 268 | Cortes Mendiola, Victor H |  | 105.57
PR | 998 | 08/09/19 | 268 | Cortes Mendiola, Victor H |  | 35.19
PR | 998 | 08/09/19 | 269 | Cortes Sepulveda, Jose R |  | 55.08
PR | 998 | 08/09/19 | 269 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 08/09/19 | 279 | Galdamez, Dagoberto A |  | 36.72
PR | 998 | 08/09/19 | 279 | Galdamez, Dagoberto A |  | 18.36
PR | 998 | 08/09/19 | 291 | Hubbard, Robert W |  | 15.3
PR | 998 | 08/09/19 | 297 | Lovo, German G |  | 66.1
PR | 998 | 08/09/19 | 297 | Lovo, German G |  | 16.52
PR | 998 | 08/09/19 | 298 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 08/09/19 | 298 | Lucas Tzintzun, Rafael |  | 12.85
PR | 998 | 08/09/19 | 304 | Portillo Soriano, Walter A |  | 53.86
PR | 998 | 08/09/19 | 308 | Rivera, Eli P |  | 18.36
PR | 998 | 08/09/19 | 308 | Rivera, Eli P |  | 55.08
PR | 998 | 08/09/19 | 317 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 08/09/19 | 317 | Sorto Regalado, Milton J |  | 9.79
PR | 998 | 08/16/19 | 565 | Balderas Ortiz, Ricardo I |  | 78.34
PR | 998 | 08/16/19 | 569 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 08/16/19 | 573 | Chevez, Herson G |  | 70.38
PR | 998 | 08/16/19 | 575 | Cortes Mendiola, Victor H |  | 140.76
PR | 998 | 08/16/19 | 576 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 08/16/19 | 586 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 08/16/19 | 604 | Lovo, German G |  | 33.05
PR | 998 | 08/16/19 | 604 | Lovo, German G |  | 49.57
PR | 998 | 08/16/19 | 605 | Lucas Tzintzun, Rafael |  | 25.7
PR | 998 | 08/16/19 | 605 | Lucas Tzintzun, Rafael |  | 38.56
PR | 998 | 08/16/19 | 611 | Portillo Soriano, Walter A |  | 26.93
PR | 998 | 08/16/19 | 611 | Portillo Soriano, Walter A |  | 40.39
PR | 998 | 08/16/19 | 615 | Rivera, Eli P |  | 36.72
PR | 998 | 08/16/19 | 615 | Rivera, Eli P |  | 55.08
PR | 998 | 08/16/19 | 621 | Sanders, Allen O |  | 7.5
PR | 998 | 08/16/19 | 624 | Sorto Regalado, Milton J |  | 19.58
PR | 998 | 08/16/19 | 624 | Sorto Regalado, Milton J |  | 29.38
PR | 998 | 08/16/19 | 636 | Donelson, Richard T |  | 14.34
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/23/19 | 801 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 08/23/19 | 805 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 08/23/19 | 809 | Chevez, Herson G |  | 70.38
PR | 998 | 08/23/19 | 811 | Cortes Mendiola, Victor H |  | 140.76
PR | 998 | 08/23/19 | 812 | Cortes Sepulveda, Jose R |  | 73.44
PR | 998 | 08/23/19 | 812 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 08/23/19 | 822 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 08/23/19 | 835 | Hubbard, Robert W |  | 7.65
PR | 998 | 08/23/19 | 835 | Hubbard, Robert W |  | 7.65
PR | 998 | 08/23/19 | 841 | Lovo, German G |  | 16.52
PR | 998 | 08/23/19 | 841 | Lovo, German G |  | 16.52
PR | 998 | 08/23/19 | 842 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 08/23/19 | 848 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 08/23/19 | 852 | Rivera, Eli P |  | 91.8
PR | 998 | 08/23/19 | 861 | Sorto Regalado, Milton J |  | 39.17
PR | 998 | 08/30/19 | 992 | Balderas Ortiz, Ricardo I |  | 78.34
PR | 998 | 08/30/19 | 996 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 08/30/19 | 1000 | Chevez, Herson G |  | 70.38
PR | 998 | 08/30/19 | 1002 | Cortes Mendiola, Victor H |  | 84.46
PR | 998 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R |  | 55.08
PR | 998 | 08/30/19 | 1003 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 08/30/19 | 1013 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 08/30/19 | 1026 | Hubbard, Robert W |  | 19.13
PR | 998 | 08/30/19 | 1026 | Hubbard, Robert W |  | 3.83
PR | 998 | 08/30/19 | 1032 | Lovo, German G |  | 16.52
PR | 998 | 08/30/19 | 1033 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 08/30/19 | 1039 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 08/30/19 | 1043 | Rivera, Eli P |  | 55.08
PR | 998 | 08/30/19 | 1043 | Rivera, Eli P |  | 36.72
PR | 998 | 08/30/19 | 1052 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 4.78
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 9.56
PR | 998 | 09/06/19 | 13 | Balderas Ortiz, Ricardo I |  | 39.17
PR | 998 | 09/06/19 | 17 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 09/06/19 | 21 | Chevez, Herson G |  | 56.3
PR | 998 | 09/06/19 | 23 | Cortes Mendiola, Victor H |  | 105.57
PR | 998 | 09/06/19 | 23 | Cortes Mendiola, Victor H |  | 7.04
PR | 998 | 09/06/19 | 24 | Cortes Sepulveda, Jose R |  | 55.08
PR | 998 | 09/06/19 | 24 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 09/06/19 | 34 | Galdamez, Dagoberto A |  | 55.08
PR | 998 | 09/06/19 | 47 | Hubbard, Robert W |  | 22.95
PR | 998 | 09/06/19 | 47 | Hubbard, Robert W |  | 19.13
PR | 998 | 09/06/19 | 53 | Lovo, German G |  | 66.1
PR | 998 | 09/06/19 | 54 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 09/06/19 | 60 | Portillo Soriano, Walter A |  | 26.93
PR | 998 | 09/06/19 | 60 | Portillo Soriano, Walter A |  | 26.93
PR | 998 | 09/06/19 | 64 | Rivera, Eli P |  | 55.08
PR | 998 | 09/06/19 | 64 | Rivera, Eli P |  | 18.36
PR | 998 | 09/06/19 | 71 | Sepulveda Gonzalez, Alfredo |  | 34.81
PR | 998 | 09/06/19 | 73 | Sorto Regalado, Milton J |  | 19.58
PR | 998 | 09/06/19 | 73 | Sorto Regalado, Milton J |  | 19.58
PR | 998 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I |  | 58.75
PR | 998 | 09/13/19 | 237 | Balderas Ortiz, Ricardo I |  | 39.17
PR | 998 | 09/13/19 | 241 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 09/13/19 | 241 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 09/13/19 | 245 | Chevez, Herson G |  | 70.38
PR | 998 | 09/13/19 | 247 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 09/13/19 | 247 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 09/13/19 | 248 | Cortes Sepulveda, Jose R |  | 48.2
PR | 998 | 09/13/19 | 248 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 09/13/19 | 258 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 09/13/19 | 271 | Hubbard, Robert W |  | 38.25
PR | 998 | 09/13/19 | 271 | Hubbard, Robert W |  | 15.3
PR | 998 | 09/13/19 | 276 | Lovo, German G |  | 82.62
PR | 998 | 09/13/19 | 277 | Lucas Tzintzun, Rafael |  | 38.56
PR | 998 | 09/13/19 | 277 | Lucas Tzintzun, Rafael |  | 25.7
PR | 998 | 09/13/19 | 283 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 09/13/19 | 287 | Rivera, Eli P |  | 36.72
PR | 998 | 09/13/19 | 287 | Rivera, Eli P |  | 55.08
PR | 998 | 09/13/19 | 293 | Sanders, Allen O |  | 7.5
PR | 998 | 09/13/19 | 294 | Sepulveda Gonzalez, Alfredo |  | 66.94
PR | 998 | 09/13/19 | 296 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 09/20/19 | 474 | Balderas Ortiz, Ricardo I |  | 90.58
PR | 998 | 09/20/19 | 478 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 116.13
PR | 998 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 3.52
PR | 998 | 09/20/19 | 484 | Cortes Mendiola, Victor H |  | 7.04
PR | 998 | 09/20/19 | 485 | Cortes Sepulveda, Jose R |  | 78.03
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 30.6
PR | 998 | 09/20/19 | 515 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 09/20/19 | 521 | Portillo Soriano, Walter A |  | 67.32
PR | 998 | 09/20/19 | 525 | Rivera, Eli P |  | 91.8
PR | 998 | 09/20/19 | 532 | Sepulveda Gonzalez, Alfredo |  | 93.71
PR | 998 | 09/20/19 | 534 | Sorto Regalado, Milton J |  | 45.29
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/27/19 | 630 | Balderas Ortiz, Ricardo I |  | 97.92
PR | 998 | 09/27/19 | 634 | Benites Portillo, Marvin E |  | 82.62
PR | 998 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 59.82
PR | 998 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 3.52
PR | 998 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 3.52
PR | 998 | 09/27/19 | 640 | Cortes Mendiola, Victor H |  | 3.52
PR | 998 | 09/27/19 | 641 | Cortes Sepulveda, Jose R |  | 91.8
PR | 998 | 09/27/19 | 666 | Hubbard, Robert W |  | 11.48
PR | 998 | 09/27/19 | 674 | Lucas Tzintzun, Rafael |  | 51.41
PR | 998 | 09/27/19 | 674 | Lucas Tzintzun, Rafael |  | 12.85
PR | 998 | 09/27/19 | 680 | Portillo Soriano, Walter A |  | 26.93
PR | 998 | 09/27/19 | 684 | Rivera, Eli P |  | 36.72
PR | 998 | 09/27/19 | 690 | Sanders, Allen O |  | 7.5
PR | 998 | 09/27/19 | 691 | Sepulveda Gonzalez, Alfredo |  | 85.68
PR | 998 | 09/27/19 | 693 | Sorto Regalado, Milton J |  | 48.96
PR | 998 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I |  | 39.17
PR | 998 | 10/04/19 | 6 | Balderas Ortiz, Ricardo I |  | 39.17
PR | 998 | 10/04/19 | 10 | Benites Portillo, Marvin E |  | 49.57
PR | 998 | 10/04/19 | 10 | Benites Portillo, Marvin E |  | 26.85
PR | 998 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 49.27
PR | 998 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 14.08
PR | 998 | 10/04/19 | 16 | Cortes Mendiola, Victor H |  | 7.04
PR | 998 | 10/04/19 | 17 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 10/04/19 | 17 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 10/04/19 | 41 | Hubbard, Robert W |  | 19.13
PR | 998 | 10/04/19 | 49 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 10/04/19 | 66 | Sanders, Allen O |  | 7.5
PR | 998 | 10/04/19 | 67 | Sepulveda Gonzalez, Alfredo |  | 85.68
PR | 998 | 10/04/19 | 69 | Sorto Regalado, Milton J |  | 9.79
PR | 998 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I |  | 48.96
PR | 998 | 10/11/19 | 261 | Balderas Ortiz, Ricardo I |  | 48.96
PR | 998 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 14.46
PR | 998 | 10/11/19 | 265 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 52.79
PR | 998 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 66.86
PR | 998 | 10/11/19 | 271 | Cortes Mendiola, Victor H |  | 7.04
PR | 998 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 10/11/19 | 272 | Cortes Sepulveda, Jose R |  | 34.43
PR | 998 | 10/11/19 | 296 | Hubbard, Robert W |  | 7.65
PR | 998 | 10/11/19 | 304 | Lucas Tzintzun, Rafael |  | 64.26
PR | 998 | 10/11/19 | 322 | Sepulveda Gonzalez, Alfredo |  | 107.1
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I |  | 31.82
PR | 998 | 10/18/19 | 455 | Balderas Ortiz, Ricardo I |  | 58.75
PR | 998 | 10/18/19 | 459 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 3.52
PR | 998 | 10/18/19 | 465 | Cortes Mendiola, Victor H |  | 14.08
PR | 998 | 10/18/19 | 466 | Cortes Sepulveda, Jose R |  | 73.44
PR | 998 | 10/18/19 | 466 | Cortes Sepulveda, Jose R |  | 18.36
PR | 998 | 10/18/19 | 472 | Eliassen, Cory H |  | 39.24
PR | 998 | 10/18/19 | 477 | Gauthier, Dillon R |  | 10.4
PR | 998 | 10/18/19 | 489 | Hubbard, Robert W |  | 7.65
PR | 998 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 12.85
PR | 998 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 20.88
PR | 998 | 10/18/19 | 497 | Lucas Tzintzun, Rafael |  | 12.85
PR | 998 | 10/18/19 | 514 | Sanders, Allen O |  | 9.37
PR | 998 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo |  | 64.26
PR | 998 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I |  | 58.75
PR | 998 | 10/25/19 | 590 | Balderas Ortiz, Ricardo I |  | 31.82
PR | 998 | 10/25/19 | 594 | Benites Portillo, Marvin E |  | 16.52
PR | 998 | 10/25/19 | 601 | Cortes Mendiola, Victor H |  | 70.38
PR | 998 | 10/25/19 | 602 | Cortes Sepulveda, Jose R |  | 36.72
PR | 998 | 10/25/19 | 602 | Cortes Sepulveda, Jose R |  | 29.84
PR | 998 | 10/25/19 | 607 | Eliassen, Cory H |  | 51.64
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 11.48
PR | 998 | 10/25/19 | 632 | Lucas Tzintzun, Rafael |  | 43.38
PR | 998 | 10/25/19 | 632 | Lucas Tzintzun, Rafael |  | 12.85
PR | 998 | 10/25/19 | 650 | Sanders, Allen O |  | 18.74
PR | 998 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo |  | 24.1
PR | 998 | 10/25/19 | 656 | Trower-Kelly, Fidel D |  | 26.16
PR | 998 | 10/25/19 | 657 | Vazquez Popoca, Jose N |  | 27.31
PR | 998 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 11/01/19 | 6 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 11/01/19 | 10 | Benites Portillo, Marvin E |  | 17.75
PR | 998 | 11/01/19 | 16 | Cortes Mendiola, Victor H |  | 61.2
PR | 998 | 11/01/19 | 16 | Cortes Mendiola, Victor H |  | 72.68
PR | 998 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 41.62
PR | 998 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 11/01/19 | 17 | Cortes Sepulveda, Jose R |  | 41.62
PR | 998 | 11/01/19 | 23 | Eliassen, Cory H |  | 73.44
PR | 998 | 11/01/19 | 48 | Lucas Tzintzun, Rafael |  | 29.38
PR | 998 | 11/01/19 | 66 | Sanders, Allen O |  | 8.26
PR | 998 | 11/01/19 | 67 | Sepulveda Gonzalez, Alfredo |  | 23.87
PR | 998 | 11/01/19 | 72 | Trower-Kelly, Fidel D |  | 51.41
PR | 998 | 11/01/19 | 73 | Vazquez Popoca, Jose N |  | 36.72
PR | 998 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I |  | 66.1
PR | 998 | 11/08/19 | 180 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 22.95
PR | 998 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 11.48
PR | 998 | 11/08/19 | 190 | Cortes Mendiola, Victor H |  | 11.48
PR | 998 | 11/08/19 | 191 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 11/08/19 | 191 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 11/08/19 | 197 | Eliassen, Cory H |  | 55.08
PR | 998 | 11/08/19 | 240 | Sanders, Allen O |  | 12.39
PR | 998 | 11/08/19 | 246 | Trower-Kelly, Fidel D |  | 51.41
PR | 998 | 11/08/19 | 247 | Vazquez Popoca, Jose N |  | 48.96
PR | 998 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 11/15/19 | 440 | Balderas Ortiz, Ricardo I |  | 66.1
PR | 998 | 11/15/19 | 450 | Cortes Mendiola, Victor H |  | 19.13
PR | 998 | 11/15/19 | 451 | Cortes Sepulveda, Jose R |  | 41.62
PR | 998 | 11/15/19 | 451 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 11/15/19 | 457 | Eliassen, Cory H |  | 73.44
PR | 998 | 11/15/19 | 462 | Gauthier, Dillon R |  | 44.06
PR | 998 | 11/15/19 | 499 | Sanders, Allen O |  | 28.92
PR | 998 | 11/15/19 | 505 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 11/15/19 | 506 | Vazquez Popoca, Jose N |  | 12.24
PR | 998 | 11/15/19 | 512 | Donelson, Richard T |  | 4.78
PR | 998 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I |  | 63.34
PR | 998 | 11/22/19 | 611 | Balderas Ortiz, Ricardo I |  | 38.56
PR | 998 | 11/22/19 | 621 | Cortes Mendiola, Victor H |  | 34.43
PR | 998 | 11/22/19 | 621 | Cortes Mendiola, Victor H |  | 11.48
PR | 998 | 11/22/19 | 622 | Cortes Sepulveda, Jose R |  | 39.02
PR | 998 | 11/22/19 | 622 | Cortes Sepulveda, Jose R |  | 36.41
PR | 998 | 11/22/19 | 628 | Eliassen, Cory H |  | 87.21
PR | 998 | 11/22/19 | 633 | Gauthier, Dillon R |  | 37.18
PR | 998 | 11/22/19 | 670 | Sanders, Allen O |  | 30.98
PR | 998 | 11/22/19 | 676 | Trower-Kelly, Fidel D |  | 61.05
PR | 998 | 11/22/19 | 684 | Donelson, Richard T |  | 4.78
PR | 998 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 11/27/19 | 845 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 11/27/19 | 855 | Cortes Mendiola, Victor H |  | 11.48
PR | 998 | 11/27/19 | 856 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 11/27/19 | 856 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 11/27/19 | 862 | Eliassen, Cory H |  | 73.44
PR | 998 | 11/27/19 | 867 | Gauthier, Dillon R |  | 41.31
PR | 998 | 11/27/19 | 904 | Sanders, Allen O |  | 28.92
PR | 998 | 11/27/19 | 910 | Trower-Kelly, Fidel D |  | 51.41
PR | 998 | 12/06/19 | 31 | Balderas Ortiz, Ricardo I |  | 88.13
PR | 998 | 12/06/19 | 42 | Cortes Sepulveda, Jose R |  | 83.23
PR | 998 | 12/06/19 | 48 | Eliassen, Cory H |  | 73.44
PR | 998 | 12/06/19 | 54 | Gauthier, Dillon R |  | 44.06
PR | 998 | 12/06/19 | 65 | Hubbard, Robert W |  | 8.26
PR | 998 | 12/06/19 | 91 | Sanders, Allen O |  | 16.52
PR | 998 | 12/06/19 | 97 | Trower-Kelly, Fidel D |  | 45.79
PR | 998 | 12/13/19 | 392 | Balderas Ortiz, Ricardo I |  | 110.16
PR | 998 | 12/13/19 | 402 | Cortes Mendiola, Victor H |  | 65.03
PR | 998 | 12/13/19 | 403 | Cortes Sepulveda, Jose R |  | 104.04
PR | 998 | 12/13/19 | 409 | Eliassen, Cory H |  | 73.44
PR | 998 | 12/13/19 | 415 | Gauthier, Dillon R |  | 55.08
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 8.26
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 4.13
PR | 998 | 12/13/19 | 452 | Sanders, Allen O |  | 24.79
PR | 998 | 12/13/19 | 458 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 12/13/19 | 465 | Donelson, Richard T |  | 4.78
PR | 998 | 12/20/19 | 545 | Balderas Ortiz, Ricardo I |  | 110.16
PR | 998 | 12/20/19 | 555 | Cortes Mendiola, Victor H |  | 7.65
PR | 998 | 12/20/19 | 556 | Cortes Sepulveda, Jose R |  | 104.04
PR | 998 | 12/20/19 | 562 | Eliassen, Cory H |  | 55.08
PR | 998 | 12/20/19 | 568 | Gauthier, Dillon R |  | 44.06
PR | 998 | 12/20/19 | 579 | Hubbard, Robert W |  | 12.39
PR | 998 | 12/20/19 | 605 | Sanders, Allen O |  | 24.79
PR | 998 | 12/20/19 | 611 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I |  | 49.57
PR | 998 | 12/27/19 | 702 | Balderas Ortiz, Ricardo I |  | 16.52
PR | 998 | 12/27/19 | 713 | Cortes Sepulveda, Jose R |  | 46.82
PR | 998 | 12/27/19 | 713 | Cortes Sepulveda, Jose R |  | 15.61
PR | 998 | 12/27/19 | 720 | Eliassen, Cory H |  | 55.08
PR | 998 | 12/27/19 | 726 | Gauthier, Dillon R |  | 33.05
PR | 998 | 12/27/19 | 737 | Hubbard, Robert W |  | 8.26
PR | 998 | 12/27/19 | 763 | Sanders, Allen O |  | 20.66
PR | 998 | 12/27/19 | 769 | Trower-Kelly, Fidel D |  | 35.34
PR | 998 | 01/03/20 | 5 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 01/03/20 | 15 | Cortes Mendiola, Victor H |  | 7.65
PR | 998 | 01/03/20 | 16 | Cortes Sepulveda, Jose R |  | 33.81
PR | 998 | 01/03/20 | 23 | Eliassen, Cory H |  | 73.44
PR | 998 | 01/03/20 | 29 | Gauthier, Dillon R |  | 33.05
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 20.66
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 10.33
PR | 998 | 01/03/20 | 66 | Sanders, Allen O |  | 16.52
PR | 998 | 01/03/20 | 72 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 01/10/20 | 278 | Balderas Ortiz, Ricardo I |  | 110.16
PR | 998 | 01/10/20 | 289 | Cortes Sepulveda, Jose R |  | 91.04
PR | 998 | 01/10/20 | 296 | Eliassen, Cory H |  | 73.44
PR | 998 | 01/10/20 | 302 | Gauthier, Dillon R |  | 16.52
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 26.85
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/10/20 | 339 | Sanders, Allen O |  | 10.33
PR | 998 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 38.56
PR | 998 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 5.51
PR | 998 | 01/17/20 | 544 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 36.41
PR | 998 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 5.2
PR | 998 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/17/20 | 555 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/17/20 | 562 | Eliassen, Cory H |  | 73.44
PR | 998 | 01/17/20 | 568 | Gauthier, Dillon R |  | 44.06
PR | 998 | 01/17/20 | 579 | Hubbard, Robert W |  | 4.13
PR | 998 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 01/17/20 | 605 | Sanders, Allen O |  | 24.79
PR | 998 | 01/17/20 | 611 | Trower-Kelly, Fidel D |  | 51.41
PR | 998 | 01/17/20 | 618 | Donelson, Richard T |  | 4.78
PR | 998 | 01/24/20 | 677 | Balderas Ortiz, Ricardo I |  | 110.16
PR | 998 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 01/24/20 | 688 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/24/20 | 695 | Eliassen, Cory H |  | 91.8
PR | 998 | 01/24/20 | 700 | Gauthier, Dillon R |  | 55.08
PR | 998 | 01/24/20 | 711 | Hubbard, Robert W |  | 20.66
PR | 998 | 01/24/20 | 736 | Sanders, Allen O |  | 10.33
PR | 998 | 01/24/20 | 742 | Trower-Kelly, Fidel D |  | 38.56
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 4.78
PR | 998 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 11.02
PR | 998 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 11.02
PR | 998 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 10.4
PR | 998 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 10.4
PR | 998 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/31/20 | 854 | Eliassen, Cory H |  | 91.8
PR | 998 | 01/31/20 | 860 | Gauthier, Dillon R |  | 55.08
PR | 998 | 01/31/20 | 894 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 66.1
PR | 998 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 38.56
PR | 998 | 02/07/20 | 27 | Balderas Ortiz, Ricardo I |  | 5.51
PR | 998 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 36.41
PR | 998 | 02/07/20 | 38 | Cortes Sepulveda, Jose R |  | 5.2
PR | 998 | 02/07/20 | 45 | Eliassen, Cory H |  | 91.8
PR | 998 | 02/07/20 | 50 | Gauthier, Dillon R |  | 33.05
PR | 998 | 02/07/20 | 88 | Sanders, Allen O |  | 4.13
PR | 998 | 02/07/20 | 102 | Donelson, Richard T |  | 9.56
PR | 998 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I |  | 46.82
PR | 998 | 02/14/20 | 237 | Balderas Ortiz, Ricardo I |  | 19.28
PR | 998 | 02/14/20 | 248 | Cortes Sepulveda, Jose R |  | 39.02
PR | 998 | 02/14/20 | 248 | Cortes Sepulveda, Jose R |  | 23.41
PR | 998 | 02/14/20 | 255 | Eliassen, Cory H |  | 91.8
PR | 998 | 02/14/20 | 260 | Gauthier, Dillon R |  | 44.06
PR | 998 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 02/21/20 | 454 | Balderas Ortiz, Ricardo I |  | 66.1
PR | 998 | 02/21/20 | 465 | Cortes Sepulveda, Jose R |  | 62.42
PR | 998 | 02/21/20 | 471 | Eliassen, Cory H |  | 91.8
PR | 998 | 02/21/20 | 476 | Gauthier, Dillon R |  | 33.05
PR | 998 | 02/21/20 | 486 | Hubbard, Robert W |  | 24.79
PR | 998 | 02/21/20 | 486 | Hubbard, Robert W |  | 16.52
PR | 998 | 02/21/20 | 486 | Hubbard, Robert W |  | 12.39
PR | 998 | 02/21/20 | 514 | Sanders, Allen O |  | 6.2
PR | 998 | 02/21/20 | 515 | Sepulveda Gonzalez, Alfredo |  | 23.87
PR | 998 | 02/21/20 | 528 | Donelson, Richard T |  | 4.78
PR | 998 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I |  | 66.1
PR | 998 | 02/28/20 | 682 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 02/28/20 | 693 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 02/28/20 | 700 | Eliassen, Cory H |  | 91.8
PR | 998 | 02/28/20 | 705 | Gauthier, Dillon R |  | 11.02
PR | 998 | 02/28/20 | 716 | Hubbard, Robert W |  | 30.98
PR | 998 | 02/28/20 | 743 | Sanders, Allen O |  | 30.98
PR | 998 | 02/28/20 | 744 | Sepulveda Gonzalez, Alfredo |  | 23.87
PR | 998 | 02/28/20 | 757 | Donelson, Richard T |  | 9.56
PR | 998 | 03/06/20 | 63 | Eliassen, Cory H |  | 48.2
PR | 998 | 03/06/20 | 78 | Hubbard, Robert W |  | 41.31
PR | 998 | 03/06/20 | 78 | Hubbard, Robert W |  | 20.66
PR | 998 | 03/06/20 | 111 | Trower-Kelly, Fidel D |  | 34.54
PR | 998 | 03/06/20 | 119 | Donelson, Richard T |  | 4.78
PR | 998 | 03/13/20 | 306 | Amaya Gonzalez, Edilberto A |  | 16.52
PR | 998 | 03/13/20 | 309 | Balderas Ortiz, Ricardo I |  | 44.06
PR | 998 | 03/13/20 | 319 | Cortes Mendiola, Victor H |  | 22.95
PR | 998 | 03/13/20 | 320 | Cortes Sepulveda, Jose R |  | 41.62
PR | 998 | 03/13/20 | 327 | Eliassen, Cory H |  | 55.08
PR | 998 | 03/13/20 | 342 | Hubbard, Robert W |  | 37.18
PR | 998 | 03/13/20 | 342 | Hubbard, Robert W |  | 12.39
PR | 998 | 03/13/20 | 369 | Sanders, Allen O |  | 4.13
PR | 998 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 25.7
PR | 998 | 03/13/20 | 383 | Donelson, Richard T |  | 19.13
PR | 998 | 03/20/20 | 564 | Amaya Gonzalez, Edilberto A |  | 30.29
PR | 998 | 03/20/20 | 577 | Cortes Mendiola, Victor H |  | 42.08
PR | 998 | 03/20/20 | 578 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 03/20/20 | 585 | Eliassen, Cory H |  | 50.49
PR | 998 | 03/20/20 | 627 | Sanders, Allen O |  | 4.13
PR | 998 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 03/26/20 | 760 | Cortes Mendiola, Victor H |  | 22.95
PR | 998 | 03/26/20 | 761 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 03/26/20 | 806 | Sanders, Allen O |  | 4.13
PR | 998 | 04/17/20 | 288 | Donelson, Richard T |  | 4.78
PR | 998 | 04/24/20 | 410 | Sanders, Allen O |  | 4.13
PR | 998 | 04/24/20 | 410 | Sanders, Allen O |  | 4.13
PR | 998 | 04/24/20 | 424 | Donelson, Richard T |  | 14.34
PR | 998 | 05/01/20 | 64 | Sanders, Allen O |  | 12.39
PR | 998 | 05/01/20 | 78 | Donelson, Richard T |  | 4.78
PR | 998 | 05/15/20 | 328 | Eliassen, Cory H |  | 5.74
PR | 998 | 05/22/20 | 483 | Eliassen, Cory H |  | 4.59
PR | 998 | 06/05/20 | 31 | Eliassen, Cory H |  | 13.77
PR | 998 | 06/26/20 | 541 | Hubbard, Robert W |  | 8.26
AR | 999 | 06/20/18 | 672 | Compass Harbor Construction, LLC $Parksi |  | -1865 | 037111
AR | 999 | 06/20/18 | 672 | Compass Harbor Construction, LLC $Parksi |  | -544 | 037111
AR | 999 | 06/20/18 | 672 | Compass Harbor Construction, LLC $Parksi |  | -14000 | 037111
AR | 999 | 07/20/18 | 517 | Compass Harbor Construction, LLC $Parksi |  | -42480 | 037129
AR | 999 | 07/20/18 | 518 | Compass Harbor Construction, LLC $Parksi |  | -20300 | 037130
AR | 999 | 07/20/18 | 518 | Compass Harbor Construction, LLC $Parksi |  | -32500 | 037130
AR | 999 | 08/20/18 | 584 | Compass Harbor Construction, LLC $Parksi |  | -46500 | 037155
AR | 999 | 08/20/18 | 584 | Compass Harbor Construction, LLC $Parksi |  | -3750 | 037155
AR | 999 | 10/11/18 | 229 | Compass Harbor Construction, LLC $Parksi |  | -4720 | 037198
AR | 999 | 10/11/18 | 229 | Compass Harbor Construction, LLC $Parksi |  | -11800 | 037198
AR | 999 | 10/19/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -5000 | 037206
AR | 999 | 10/19/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -3750 | 037206
AR | 999 | 10/19/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -8500 | 037206
AR | 999 | 10/19/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -11600 | 037206
AR | 999 | 10/19/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -6950 | 037206
AR | 999 | 11/16/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -26080 | 037226
AR | 999 | 11/16/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -34320 | 037226
AR | 999 | 11/16/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -6950 | 037226
AR | 999 | 11/16/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -2447 | 037226
AR | 999 | 11/16/18 | 520 | Compass Harbor Construction, LLC $Parksi |  | -4436 | 037226
AR | 999 | 12/14/18 | 348 | Compass Harbor Construction, LLC $Parksi |  | -27300 | 037251
AR | 999 | 01/18/19 | 550 | Compass Harbor Construction, LLC $Parksi |  | -6520 | 037268
AR | 999 | 01/18/19 | 550 | Compass Harbor Construction, LLC $Parksi |  | -8580 | 037268
AR | 999 | 01/18/19 | 550 | Compass Harbor Construction, LLC $Parksi |  | -27720 | 037268
AR | 999 | 01/18/19 | 550 | Compass Harbor Construction, LLC $Parksi |  | -846 | 037268
AR | 999 | 02/20/19 | 572 | Compass Harbor Construction, LLC $Parksi |  | -27720 | 037294
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -6930 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -110220 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -7800 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -147240 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -4100 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -132900 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -17100 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -41740 | 037303
AR | 999 | 03/20/19 | 682 | Compass Harbor Construction, LLC $Parksi |  | -17100 | 037303
AR | 999 | 04/19/19 | 604 | Compass Harbor Construction, LLC $Parksi |  | -146090 | 037320
AR | 999 | 04/19/19 | 604 | Compass Harbor Construction, LLC $Parksi |  | -120300 | 037320
AR | 999 | 04/19/19 | 604 | Compass Harbor Construction, LLC $Parksi |  | -16500 | 037320
AR | 999 | 04/19/19 | 604 | Compass Harbor Construction, LLC $Parksi |  | -20320 | 037320
AR | 999 | 04/19/19 | 604 | Compass Harbor Construction, LLC $Parksi |  | -15400 | 037320
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -55110 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -73620 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -58350 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -60150 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -142240 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -16930 | 037346
AR | 999 | 05/20/19 | 513 | Compass Harbor Construction, LLC $Parksi |  | -15400 | 037346
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -6930 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -49700 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -75000 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -6400 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -9500 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -9185 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -12270 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -10625 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -10435 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -10025 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -30480 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -118510 | 037358
AR | 999 | 06/19/19 | 602 | Compass Harbor Construction, LLC $Parksi |  | -1867 | 037358
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -6400 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -9500 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -10160 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -2800 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -33860 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -2800 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -4300 | 037380
AR | 999 | 07/19/19 | 605 | Compass Harbor Construction, LLC $Parksi |  | -12584 | 037380
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -9185 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -1900 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -12270 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -2500 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -10625 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -3200 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -10435 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -10025 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -2800 | 037392
AR | 999 | 08/15/19 | 755 | Compass Harbor Construction, LLC $Parksi |  | -631 | 037392
AR | 999 | 09/20/19 | 570 | Compass Harbor Construction, LLC $Parksi |  | -18880 | 037414
AR | 999 | 09/20/19 | 570 | Compass Harbor Construction, LLC $Parksi |  | -22880 | 037414
AR | 999 | 09/20/19 | 570 | Compass Harbor Construction, LLC $Parksi |  | -3200 | 037414
AR | 999 | 09/20/19 | 570 | Compass Harbor Construction, LLC $Parksi |  | -11426 | 037414
AR | 999 | 09/20/19 | 570 | Compass Harbor Construction, LLC $Parksi |  | -6000 | 037414
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -6560 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -6960 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -4720 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -5720 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -17840 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -22300 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | 8704 | 037426
AR | 999 | 10/18/19 | 539 | Compass Harbor Construction, LLC $Parksi |  | -2800 | 037426
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | -18750 | 037440
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | -18750 | 037440
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | -23600 | 037440
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | -4460 | 037440
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | 8704 | 037440
AR | 999 | 11/18/19 | 558 | Compass Harbor Construction, LLC $Parksi |  | -8800 | 037440
AR | 999 | 12/13/19 | 479 | Compass Harbor Construction, LLC $Parksi |  | -3000 | 037455
AR | 999 | 12/13/19 | 479 | Compass Harbor Construction, LLC $Parksi |  | -6250 | 037455
AR | 999 | 01/20/20 | 655 | Compass Harbor Construction, LLC $Parksi |  | -9700 | 037470
AR | 999 | 01/20/20 | 655 | Compass Harbor Construction, LLC $Parksi |  | -12500 | 037470
AR | 999 | 01/20/20 | 655 | Compass Harbor Construction, LLC $Parksi |  | -3250 | 037470
AR | 999 | 01/20/20 | 655 | Compass Harbor Construction, LLC $Parksi |  | 9792 | 037470
AR | 999 | 01/20/20 | 655 | Compass Harbor Construction, LLC $Parksi |  | -7295 | 037470
AR | 999 | 02/19/20 | 447 | Compass Harbor Construction, LLC $Parksi |  | -1640 | 037482
AR | 999 | 02/19/20 | 447 | Compass Harbor Construction, LLC $Parksi |  | -1740 | 037482
AR | 999 | 02/19/20 | 447 | Compass Harbor Construction, LLC $Parksi |  | -800 | 037482
AR | 999 | 02/19/20 | 447 | Compass Harbor Construction, LLC $Parksi |  | -439 | 037482