## 01 Overview
OWP #2054 · 800 5th Apartments
Blueprint Capital Services, LLC · 68 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 843087
Revised budget (expenses) | 636625.49
Forecast net profit | 206461.51
Forecast margin | 24.49%
Progress to Date
Work complete (billed) | 843087
Retention held | 0
Earned less retention | 843087
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | -43157.19
AP | 262972.37
PR | 425357.25
AR | -767116

## 02 Job Info
JOB #2054 · BLUEPRINT CAPITAL SERVICES LLC · 800 5th Apartments — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract 03-08-6505.
IDENTITY
OWP Job ID | 2054
Project Name | 800 5th Apartments
Site Address | 800 5th Ave N, Seattle WA 98109
Subcontract Number | 03-08-6505
Effective Date | Feb 5, 2018
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Blueprint Capital Services LLC
GC Address | PO Box 16309, Seattle WA 98116 · (206) 282-9270
GC Contract Signatory | TBD (per Blueprint)
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson, VP
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Blueprint 800, LLC
Owner Address | PO Box 16309, Seattle WA 98116
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | Not Wrap (OWP CGL · Hub International / Liberty Mutual)
Retention | 5% per contract
CONTRACT
Contract Value | $785,600
CHANGE-EVENT META
Executed CO Count | TBD — see GDrive Change Orders/CO's/
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | (see GDrive Change Orders folder)
COR Themes | (see GDrive)
Key RFIs | (see GDrive ASI-RFI folder)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Blueprint 800 5th job ticket 12-10-18.pdf
GDrive Folder | Job Books - Completed Jobs/2054-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets | 68 | 59 Gerber Maxwell 21-912 + 9 ADA
Lavs | 68 | Kohler K-2035-1 wall-hung w/ Delta Trinsic 559HA-BL-DST matte black
Showers | 57 | 48 Best Bath P3838 std + 4 LSS6337W75BL Live/Work + 5 Aquatic 2603SMTE Type A tubs
Tubs | 11 | Sterling 71171110 plastic tub bases
Kitchen faucets | 68 | Delta Trinsic 9959-BL-DST matte black bar (sinks by others)
Air gaps | 68 | Delta 72020-BL matte black
Dishwasher rough-ins | 68
Washer rough-ins | 68
Common areas | 6 | 1 Toto CST794EF ADA + 1 Kohler K-2035-1 lav + amenity sink + coffee + retail + trash hosebib
Hose bibs | 5 | 1 trash + 4 ext (3 ground + 1 roof)
VERIFIED MAIN FIXTURE COUNT | 277
Per unit (68): 4.07
AUDIT NOTE (2026-04-25): First-pass count of 487 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 277 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 785600 | 843087 | 57487
Executed change orders (net) | 0 | 57487 | 57487
Total contract value | 785600 | 900574 | 114974
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 6120 | 6220 | 2903.5 | 3316.5 | 0 | 46.68%
101 | Takeoff & Purchase Labor | 9860 | 9960 | 4181.5 | 5778.5 | 0 | 41.98%
110 | Underground Labor | 12885 | 14055 | 7369 | 6686 | 0 | 52.43%
111 | Garage Labor | 7113 | 7113 | 3588 | 3525 | 0 | 50.44%
112 | Canout Labor | 4350 | 4350 | 2258.5 | 2091.5 | 0 | 51.92%
120 | Roughin Labor | 91743 | 94273 | 147001.5 | -52728.5 | 0 | 155.9%
130 | Finish Labor | 20700 | 20700 | 21750 | -1050 | 0 | 105.1%
140 | Gas Labor | 7500 | 7500 | 6735 | 765 | 0 | 89.8%
141 | Water Main/Insulation Lab | 26735 | 26735 | 74881.5 | -48146.5 | 0 | 280.1%
142 | Mech Room Labor | 12000 | 12000 | 12228 | -228 | 0 | 101.9%
210 | Underground Material | 10925 | 11575 | 3063.5 | 8511.5 | 0 | 26.47%
211 | Garage Material | 7500 | 7500 | 26287.7 | -18787.7 | 0 | 350.5%
212 | Canout Material | 5220 | 5220 | 9124.86 | -3904.86 | 0 | 174.8%
220 | Roughin Material | 46890 | 49582 | 34199.43 | 15382.57 | 0 | 68.98%
230 | Finish Material | 129526 | 169700 | 147852.36 | 21847.64 | 0 | 87.13%
240 | Gas Material | 8500 | 8500 | 3477.36 | 5022.64 | 0 | 40.91%
241 | Water Main/Insulation Mat | 26265 | 26265 | 18210.35 | 8054.65 | 0 | 69.33%
242 | Mech Room Material | 12500 | 12500 | 22105.44 | -9605.44 | 0 | 176.8%
600 | Subcontractor | 1000 | 1000 | 6041.25 | -5041.25 | 0 | 604.1%
601 | Engineering/Plans | 18500 | 18900 | 17733.13 | 1166.87 | 0 | 93.83%
602 | Rental Equipment | 600 | 850 | 241.47 | 608.53 | 0 | 28.41%
603 | Permits & Licenses | 8298 | 8298 | 4539.5 | 3758.5 | 0 | 54.71%
607 | Other Expenses | 7000 | 7000 | 2909.83 | 4090.17 | 0 | 41.57%
995 | Payroll Burden | 89552.25 | 91307.25 | 120818.93 | -29511.68 | 0 | 132.3%
998 | Payroll Taxes | 15223.88 | 15522.24 | 21641.82 | -6119.58 | 0 | 139.4%
TOTAL |  | 586506.13 | 636625.49 | 721143.43 | -84517.94 | 0 | 113.3%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 202906 | 282896.5 | -79990.5 | 139.4%
Material | 8 | 290842 | 264321 | 26521 | 90.88%
Overhead | 5 | 36048 | 31465.18 | 4582.82 | 87.29%
Burden | 2 | 106829.49 | 142460.75 | -35631.26 | 133.4%
TOTAL | 25 | 636625.49 | 721143.43 | -84517.94 | 113.3%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 6220 | 2903.5 | 3316.5 | -53.32% | UNDER
101 | Takeoff & Purchase Labor | 9960 | 4181.5 | 5778.5 | -58.02% | UNDER
110 | Underground Labor | 14055 | 7369 | 6686 | -47.57% | UNDER
111 | Garage Labor | 7113 | 3588 | 3525 | -49.56% | UNDER
112 | Canout Labor | 4350 | 2258.5 | 2091.5 | -48.08% | UNDER
120 | Roughin Labor | 94273 | 147001.5 | -52728.5 | 55.93% | CRITICAL
130 | Finish Labor | 20700 | 21750 | -1050 | 5.072% | ON
140 | Gas Labor | 7500 | 6735 | 765 | -10.2% | UNDER
141 | Water Main/Insulation Lab | 26735 | 74881.5 | -48146.5 | 180.1% | CRITICAL
142 | Mech Room Labor | 12000 | 12228 | -228 | 1.9% | ON
210 | Underground Material | 11575 | 3063.5 | 8511.5 | -73.53% | UNDER
211 | Garage Material | 7500 | 26287.7 | -18787.7 | 250.5% | CRITICAL
212 | Canout Material | 5220 | 9124.86 | -3904.86 | 74.81% | CRITICAL
220 | Roughin Material | 49582 | 34199.43 | 15382.57 | -31.02% | UNDER
230 | Finish Material | 169700 | 147852.36 | 21847.64 | -12.87% | UNDER
240 | Gas Material | 8500 | 3477.36 | 5022.64 | -59.09% | UNDER
241 | Water Main/Insulation Mat | 26265 | 18210.35 | 8054.65 | -30.67% | UNDER
242 | Mech Room Material | 12500 | 22105.44 | -9605.44 | 76.84% | CRITICAL
600 | Subcontractor | 1000 | 6041.25 | -5041.25 | 504.1% | CRITICAL
601 | Engineering/Plans | 18900 | 17733.13 | 1166.87 | -6.174% | ON
602 | Rental Equipment | 850 | 241.47 | 608.53 | -71.59% | UNDER
603 | Permits & Licenses | 8298 | 4539.5 | 3758.5 | -45.29% | UNDER
607 | Other Expenses | 7000 | 2909.83 | 4090.17 | -58.43% | UNDER
995 | Payroll Burden | 91307.25 | 120818.93 | -29511.68 | 32.32% | OVER
998 | Payroll Taxes | 15522.24 | 21641.82 | -6119.58 | 39.42% | OVER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 76581.35 | 84 | 29.12%
Keller Supply Company | 74702.97 | 12 | 28.41%
Best Bath Systems | 31203.56 | 3 | 11.87%
Ferguson Enterprises, Inc. #3007 | 21091.91 | 26 | 8.021%
Consolidated Supply Co. | 18923.1 | 27 | 7.196%
Sider + Byers Associates, Inc. | 17445 | 5 | 6.634%
Capital One Credit Card | 7620.35 | 32 | 2.898%
Mechanical Resource Services, Inc. | 4475 | 1 | 1.702%
California Hydronics Corp | 4005 | 5 | 1.523%
Quality Concrete Products, Inc. $32 | 3856 | 1 | 1.466%
Patchworks, Inc. | 826.25 | 2 | 0.3142%
Scan2Core, Inc. | 740 | 1 | 0.2814%
Core & Main LP $HD Supply Waterworks | 565.61 | 2 | 0.2151%
DRSi | 288.13 | 4 | 0.1096%
Kele, Inc $ MI Controls | 276.17 | 1 | 0.105%
Sunbelt Rentals, Inc. | 241.47 | 1 | 0.09182%
Manor Hardware & Construction Supply | 130.5 | 1 | 0.04962%
Citibank Credit Card | 0 | 6 | 0%
TOTAL AP | 262972.37 | 214

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Villalobos Tejada, Carlos F | 1608.5 | 28218 | 17.5431 | APPRENTICE/HELPER
Taylor, Evan R | 1575.5 | 46943 | 29.7956 | JOURNEYMAN
Ascencio, Jose L | 1206.5 | 37750 | 31.2889 | JOURNEYMAN
Waites, Thaddeus Z | 908 | 42770 | 47.1035 | LEAD/SUPERVISOR
Cornejo Orellana, Carlos E | 732 | 17928 | 24.4918 | JOURNEYMAN
Garcia Perez, Ervey O | 521 | 8376 | 16.0768 | APPRENTICE/HELPER
Wennig, Johnathan M | 515 | 17876 | 34.7107 | JOURNEYMAN
Cruz Reyes, Jose | 431 | 12927 | 29.993 | JOURNEYMAN
Cruz Gonzalez, Julio C | 282.5 | 7910 | 28 | JOURNEYMAN
McCabe, Thomas C | 231 | 9009 | 39 | LEAD/SUPERVISOR
Barnhart, Joseph N | 228 | 11190 | 49.0789 | LEAD/SUPERVISOR
Velasquez Cruz, Osman N | 174.5 | 4583 | 26.2636 | JOURNEYMAN
Velasquez Cruz, Denis M | 174.5 | 5956 | 34.1318 | JOURNEYMAN
Serrano, Jeremiah G | 168 | 2856 | 17 | APPRENTICE/HELPER
Roberts, Lake A | 113 | 2825 | 25 | JOURNEYMAN
Sanders, Allen O | 94.5 | 5093 | 53.8942 | LEAD/SUPERVISOR
Trower-Kelly, Fidel D | 88 | 1848 | 21 | JOURNEYMAN
Gerard, Mitchell J | 80 | 0 | 0 | APPRENTICE/HELPER
Gerard, Jeffrey S | 79 | 4148 | 52.5063 | LEAD/SUPERVISOR
Hubbard, Robert W | 78 | 4207 | 53.9359 | LEAD/SUPERVISOR
Gauthier, Dillon R | 56 | 1008 | 18 | APPRENTICE/HELPER
Jimenez Montiel, Carlos A | 50.5 | 824 | 16.3168 | APPRENTICE/HELPER
Gerard, Jordan E | 48 | 0 | 0 | APPRENTICE/HELPER
Romero Garza, Jesus I | 48 | 1104 | 23 | JOURNEYMAN
Donelson, Richard T | 47 | 2938 | 62.5106 | LEAD/SUPERVISOR
Martinez Reyes, Juan C | 44 | 1234 | 28.0455 | JOURNEYMAN
Frausto Mendoza, Pedro | 37 | 835 | 22.5676 | JOURNEYMAN
Boss, Benjamin T | 16 | 272 | 17 | APPRENTICE/HELPER
Crespin Portillo, Juan D | 15 | 380 | 25.3333 | APPRENTICE/HELPER
Eliassen, Cory H | 15 | 429 | 28.6 | JOURNEYMAN
Boss, Kyle A | 8 | 168 | 21 | JOURNEYMAN
Amaya Gonzalez, Edilberto A | 8 | 256 | 32 | JOURNEYMAN
Cortes Sepulveda, Jose R | 8 | 272 | 34 | JOURNEYMAN
Balderas Ortiz, Ricardo I | 8 | 288 | 36 | LEAD/SUPERVISOR
Hubbard, Dustin R | 7 | 175 | 25 | JOURNEYMAN
Cortes Mendiola, Victor H | 6 | 300 | 50 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 9 | 1679.5 | 79942 | 17.3%
JOURNEYMAN | 18 | 5467.5 | 161019 | 56.31%
APPRENTICE/HELPER | 9 | 2563 | 41935 | 26.4%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 9710
Active workers | 36
Hours per unit (to date) | 142.8
Revenue per labor hour (billed) | 86.83
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 24.49% | 34% | -9.511%
Roughin labor share (code 120) | 46.46% | 45% | 1.461%
Top vendor concentration | 29.12% | 38% | -8.879%
Hours per unit | 142.7941 | 95 | 47.7941

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Roughin Labor (120) CRITICAL overrun | ⚠ WATCH | Actual $147,002 vs revised $94,273 (+56%) — needs immediate attention
Water Main/Insulation Lab (141) CRITICAL overrun | ⚠ WATCH | Actual $74,882 vs revised $26,735 (+180%) — needs immediate attention
Garage Material (211) CRITICAL overrun | ⚠ WATCH | Actual $26,288 vs revised $7,500 (+251%) — needs immediate attention
Canout Material (212) CRITICAL overrun | ⚠ WATCH | Actual $9,125 vs revised $5,220 (+75%) — needs immediate attention
Mech Room Material (242) CRITICAL overrun | ⚠ WATCH | Actual $22,105 vs revised $12,500 (+77%) — needs immediate attention
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $6,041 vs revised $1,000 (+504%) — needs immediate attention
Payroll Burden (995) over revised | ⚠ WATCH | Actual $120,819 vs revised $91,307 (+32%) — monitor
Payroll Taxes (998) over revised | ⚠ WATCH | Actual $21,642 vs revised $15,522 (+39%) — monitor
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 29% of AP ($76,581) — acceptable
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 721143.43 | 721143.43 | 0
Revenue billed (AR ·-1) | -843087 | 767116 | -1610203
AP source total |  | 262972.37 | —
PR source total |  | 425357.25 | —
GL source total |  | -43157.19 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2054 live project. 17-tab JCR schema on revised budget basis.