## Summary
#2054 · 800 5th Apartments
Blueprint Capital Service · 68 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
843087 | 24.49% | 843087 | 0
Key facts
Original contract |  | 785600
Revised contract (CO impact) |  | 843087
Executed COs (net) |  | 57487
Retention held |  | 0
Revised expense budget |  | 636625.49
Forecast net profit |  | 206461.51
Percent complete |  | 100%
Live signals
Roughin Labor (120) CRITICAL | ⚠ WATCH | Actual $147,002 vs revised $94,273 (+56%) — needs attention
Water Main/Insulation Lab (141) CRITICAL | ⚠ WATCH | Actual $74,882 vs revised $26,735 (+180%) — needs attention
Garage Material (211) CRITICAL | ⚠ WATCH | Actual $26,288 vs revised $7,500 (+251%) — needs attention
Canout Material (212) CRITICAL | ⚠ WATCH | Actual $9,125 vs revised $5,220 (+75%) — needs attention
Mech Room Material (242) CRITICAL | ⚠ WATCH | Actual $22,105 vs revised $12,500 (+77%) — needs attention
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $6,041 vs revised $1,000 (+504%) — needs attention
Payroll Burden (995) over | ⚠ WATCH | Actual $120,819 vs revised $91,307 (+32%) — monitor
Payroll Taxes (998) over | ⚠ WATCH | Actual $21,642 vs revised $15,522 (+39%) — monitor
Top vendor (Rosen Supply Kirklan) | ✓ OK | 29% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Rosen Supply Kirkland | 84 | 76581.35 | 29.12%
Keller Supply Company | 12 | 74702.97 | 28.41%
Best Bath Systems | 3 | 31203.56 | 11.87%
Ferguson Enterprises, Inc. #3007 | 26 | 21091.91 | 8.021%
Consolidated Supply Co. | 27 | 18923.1 | 7.196%
Sider + Byers Associates, Inc. | 5 | 17445 | 6.634%

## Transactions
Transactions Detail
JDR source transactions for job #2054 · 2344 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 08/24/18 | 812 | Gerard, Jeffrey S | 1 | 50 | 20880
PR | 100 | 08/31/18 | 1070 | Gerard, Jeffrey S | 1 | 50 | 90962
PR | 100 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 100 | 09/14/18 | 341 | Gerard, Jeffrey S | 1 | 50 | 21174
PR | 100 | 09/28/18 | 740 | Gerard, Jeffrey S | 2 | 100 | 90884
PR | 100 | 10/12/18 | 310 | Gerard, Jeffrey S | 1 | 50 | 21467
PR | 100 | 10/26/18 | 775 | Gerard, Jeffrey S | 3.5 | 175 | 21616
PR | 100 | 11/02/18 | 77 | Gerard, Jeffrey S | 1 | 50 | 21687
PR | 100 | 11/02/18 | 77 | Gerard, Jeffrey S | 2 | 100 | 21687
PR | 100 | 11/16/18 | 514 | Gerard, Jeffrey S | 1 | 50 | 21837
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 1 | 52 | 22057
PR | 100 | 12/21/18 | 578 | Gerard, Jeffrey S | 1 | 52 | 922269
PR | 100 | 02/01/19 | 71 | Gerard, Jeffrey S | 1 | 52 | 22700
PR | 100 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 100 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 100 | 03/01/19 | 75 | Gerard, Jeffrey S | 1 | 52 | 22982
PR | 100 | 03/15/19 | 563 | Gerard, Jeffrey S | 1 | 52 | 23125
PR | 100 | 03/29/19 | 989 | Donelson, Richard T | 1 | 62.5 | 23272
PR | 100 | 04/05/19 | 152 | Gerard, Jeffrey S | 1 | 52 | 923346
PR | 100 | 04/12/19 | 398 | Gerard, Jeffrey S | 1 | 52 | 23421
PR | 100 | 04/19/19 | 597 | Gerard, Jeffrey S | 1 | 52 | 923497
PR | 100 | 05/24/19 | 681 | Gerard, Jeffrey S | 1 | 55 | 923876
PR | 100 | 06/07/19 | 255 | Gerard, Jeffrey S | 1.5 | 82.5 | 924030
PR | 100 | 06/14/19 | 524 | Gerard, Jeffrey S | 2 | 110 | 24104
PR | 100 | 06/21/19 | 694 | Gerard, Jeffrey S | 1 | 55 | 24180
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 1 | 55 | 24255
PR | 100 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 100 | 08/02/19 | 77 | Gerard, Jeffrey S | 1 | 55 | 924708
PR | 100 | 08/09/19 | 329 | Gerard, Jeffrey S | 2 | 110 | 924782
PR | 100 | 08/16/19 | 637 | Gerard, Jeffrey S | 1 | 55 | 924856
PR | 100 | 08/23/19 | 874 | Gerard, Jeffrey S | 1 | 55 | 924932
PR | 100 | 08/30/19 | 1065 | Gerard, Jeffrey S | 2 | 110 | 25009
PR | 100 | 09/20/19 | 547 | Gerard, Jeffrey S | 1 | 55 | 925233
PR | 100 | 09/27/19 | 706 | Gerard, Jeffrey S | 2 | 110 | 925311
PR | 100 | 10/04/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 25389
PR | 100 | 10/11/19 | 335 | Gerard, Jeffrey S | 2 | 110 | 925469
PR | 100 | 11/01/19 | 80 | Donelson, Richard T | 1 | 62.5 | 925696
PR | 100 | 11/01/19 | 81 | Gerard, Jeffrey S | 1 | 58 | 925697
PR | 100 | 11/08/19 | 254 | Gerard, Jeffrey S | 1 | 58 | 925773
PR | 100 | 11/27/19 | 918 | Gerard, Jeffrey S | 2 | 116 | 925999
PR | 100 | 12/13/19 | 466 | Gerard, Jeffrey S | 2 | 116 | 926232
PR | 100 | 12/27/19 | 777 | Gerard, Jeffrey S | 1 | 58 | 26385
PR | 101 | 04/06/18 | 84 | Donelson, Richard T | 1 | 62.5 | 99426
PR | 101 | 04/20/18 | 517 | Donelson, Richard T | 1 | 62.5 | 99575
PR | 101 | 06/15/18 | 527 | Donelson, Richard T | 2 | 125 | 20162
PR | 101 | 07/06/18 | 76 | Donelson, Richard T | 3 | 187.5 | 920374
PR | 101 | 07/13/18 | 367 | Donelson, Richard T | 1 | 62.5 | 20400
PR | 101 | 08/17/18 | 550 | Donelson, Richard T | 3 | 187.5 | 20808
PR | 101 | 08/24/18 | 811 | Donelson, Richard T | 1 | 62.5 | 20879
PR | 101 | 08/24/18 | 812 | Gerard, Jeffrey S | 2 | 100 | 20880
PR | 101 | 08/31/18 | 1069 | Donelson, Richard T | 2 | 125 | 90961
PR | 101 | 08/31/18 | 1070 | Gerard, Jeffrey S | 3 | 150 | 90962
PR | 101 | 09/07/18 | 106 | Gerard, Jeffrey S | 3 | 150 | 91032
PR | 101 | 09/14/18 | 340 | Donelson, Richard T | 1 | 62.5 | 21173
PR | 101 | 09/14/18 | 341 | Gerard, Jeffrey S | 2 | 100 | 21174
PR | 101 | 09/21/18 | 552 | Donelson, Richard T | 3 | 187.5 | 21244
PR | 101 | 09/21/18 | 553 | Gerard, Jeffrey S | 1 | 50 | 21245
PR | 101 | 09/28/18 | 739 | Donelson, Richard T | 1 | 62.5 | 90883
PR | 101 | 09/28/18 | 740 | Gerard, Jeffrey S | 1 | 50 | 90884
PR | 101 | 10/05/18 | 103 | Gerard, Jeffrey S | 1 | 50 | 91392
PR | 101 | 10/12/18 | 310 | Gerard, Jeffrey S | 2 | 100 | 21467
PR | 101 | 10/19/18 | 507 | Donelson, Richard T | 3 | 187.5 | 91541
PR | 101 | 10/26/18 | 774 | Donelson, Richard T | 1 | 62.5 | 21615
PR | 101 | 10/26/18 | 775 | Gerard, Jeffrey S | 4 | 200 | 21616
PR | 101 | 11/09/18 | 257 | Donelson, Richard T | 1 | 62.5 | 20891
PR | 101 | 11/16/18 | 513 | Donelson, Richard T | 1 | 62.5 | 21836
PR | 101 | 12/07/18 | 113 | Donelson, Richard T | 3 | 187.5 | 22056
PR | 101 | 12/14/18 | 337 | Donelson, Richard T | 1 | 62.5 | 22197
PR | 101 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 101 | 03/01/19 | 75 | Gerard, Jeffrey S | 1 | 52 | 22982
PR | 101 | 03/08/19 | 315 | Gerard, Jeffrey S | 2 | 104 | 923054
PR | 101 | 03/15/19 | 562 | Donelson, Richard T | 1 | 62.5 | 23124
PR | 101 | 03/15/19 | 563 | Gerard, Jeffrey S | 1 | 52 | 23125
PR | 101 | 04/05/19 | 152 | Gerard, Jeffrey S | 1 | 52 | 923346
PR | 101 | 04/19/19 | 597 | Gerard, Jeffrey S | 1 | 52 | 923497
PR | 101 | 05/17/19 | 467 | Donelson, Richard T | 1 | 62.5 | 923798
PR | 101 | 05/24/19 | 680 | Donelson, Richard T | 2 | 125 | 923875
PR | 101 | 06/14/19 | 523 | Donelson, Richard T | 2 | 125 | 24103
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 1 | 62.5 | 24179
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 1 | 62.5 | 24179
PR | 101 | 06/28/19 | 910 | Donelson, Richard T | 3 | 187.5 | 24254
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 1 | 62.5 | 25008
PR | 101 | 11/01/19 | 80 | Donelson, Richard T | 1 | 62.5 | 925696
PR | 101 | 11/08/19 | 253 | Donelson, Richard T | 1 | 62.5 | 925772
PR | 101 | 12/06/19 | 104 | Donelson, Richard T | 1 | 62.5 | 26076
PR | 101 | 02/14/20 | 312 | Donelson, Richard T | 1 | 62.5 | 926928
PR | 110 | 08/31/18 | 1000 | Barnhart, Joseph N | 4 | 184 | 20896
PR | 110 | 09/07/18 | 41 | Barnhart, Joseph N | 1 | 46 | 20966
PR | 110 | 09/14/18 | 272 | Barnhart, Joseph N | 2 | 92 | 21107
PR | 110 | 09/14/18 | 310 | Martinez Reyes, Juan C | 2 | 52 | 21144
PR | 110 | 09/21/18 | 486 | Barnhart, Joseph N | 4 | 184 | 21178
PR | 110 | 09/28/18 | 670 | Barnhart, Joseph N | 1 | 46 | 21249
PR | 110 | 09/28/18 | 708 | Martinez Reyes, Juan C | 1 | 26 | 21286
PR | 110 | 10/05/18 | 34 | Barnhart, Joseph N | 2 | 92 | 21323
PR | 110 | 10/05/18 | 72 | Martinez Reyes, Juan C | 1 | 26 | 21360
PR | 110 | 10/19/18 | 438 | Barnhart, Joseph N | 3 | 138 | 21471
PR | 110 | 10/19/18 | 476 | Martinez Reyes, Juan C | 2 | 52 | 21509
PR | 110 | 10/26/18 | 706 | Barnhart, Joseph N | 2 | 138 | 21546
PR | 110 | 10/26/18 | 706 | Barnhart, Joseph N | 12 | 552 | 21546
PR | 110 | 10/26/18 | 742 | Martinez Reyes, Juan C | 2 | 78 | 21582
PR | 110 | 10/26/18 | 742 | Martinez Reyes, Juan C | 4 | 104 | 21582
PR | 110 | 10/26/18 | 770 | Wennig, Johnathan M | 16 | 448 | 21610
PR | 110 | 11/02/18 | 9 | Barnhart, Joseph N | 29.5 | 1357 | 21619
PR | 110 | 11/02/18 | 73 | Wennig, Johnathan M | 36 | 1008 | 21682
PR | 110 | 11/09/18 | 187 | Barnhart, Joseph N | 3 | 138 | 21691
PR | 110 | 11/16/18 | 435 | Barnhart, Joseph N | 5 | 230 | 21764
PR | 110 | 11/30/18 | 833 | Barnhart, Joseph N | 2 | 96 | 21916
PR | 110 | 12/07/18 | 47 | Barnhart, Joseph N | 4 | 192 | 21990
PR | 110 | 12/14/18 | 270 | Barnhart, Joseph N | 5 | 240 | 22130
PR | 110 | 12/14/18 | 270 | Barnhart, Joseph N | 3 | 216 | 22130
PR | 110 | 12/14/18 | 270 | Barnhart, Joseph N | 1 | 48 | 22130
PR | 110 | 12/14/18 | 270 | Barnhart, Joseph N | 3 | 144 | 22130
PR | 110 | 12/14/18 | 335 | Wennig, Johnathan M | 8 | 240 | 22194
PR | 110 | 12/21/18 | 511 | Barnhart, Joseph N | 6 | 288 | 22202
PR | 110 | 12/21/18 | 547 | Martinez Reyes, Juan C | 2 | 56 | 22237
PR | 110 | 12/28/18 | 702 | Barnhart, Joseph N | 4 | 192 | 22275
PR | 110 | 01/04/19 | 7 | Barnhart, Joseph N | 2 | 96 | 22347
PR | 110 | 01/11/19 | 215 | Barnhart, Joseph N | 7 | 336 | 22417
PR | 110 | 01/11/19 | 251 | Martinez Reyes, Juan C | 3 | 84 | 22453
PR | 110 | 04/12/19 | 327 | Barnhart, Joseph N | 2 | 100 | 23351
PR | 110 | 06/07/19 | 183 | Barnhart, Joseph N | 1 | 50 | 23958
PR | 111 | 10/19/18 | 460 | Gerard, Mitchell J | 40 | 1400 | 21493
PR | 111 | 02/22/19 | 582 | Barnhart, Joseph N | 6 | 288 | 22844
PR | 111 | 02/22/19 | 636 | Serrano, Jeremiah G | 7 | 119 | 22898
PR | 111 | 03/01/19 | 7 | Barnhart, Joseph N | 12 | 576 | 22914
PR | 111 | 03/01/19 | 63 | Serrano, Jeremiah G | 8 | 136 | 22970
PR | 111 | 03/08/19 | 249 | Barnhart, Joseph N | 3 | 144 | 22987
PR | 111 | 03/08/19 | 302 | Serrano, Jeremiah G | 8 | 136 | 23041
PR | 111 | 03/08/19 | 306 | Taylor, Evan R | 24 | 624 | 23045
PR | 111 | 03/15/19 | 554 | Taylor, Evan R | 2 | 78 | 23116
PR | 111 | 03/15/19 | 554 | Taylor, Evan R | 8 | 208 | 23116
PR | 111 | 03/15/19 | 558 | Villalobos Tejada, Carlos F | 3 | 48 | 23120
PR | 111 | 03/22/19 | 768 | Taylor, Evan R | 2 | 78 | 23189
PR | 111 | 03/22/19 | 768 | Taylor, Evan R | 8 | 208 | 23189
PR | 111 | 03/22/19 | 772 | Villalobos Tejada, Carlos F | 2 | 48 | 23193
PR | 111 | 03/22/19 | 772 | Villalobos Tejada, Carlos F | 8 | 128 | 23193
PR | 111 | 11/15/19 | 510 | Waites, Thaddeus Z | 7 | 343 | 25846
PR | 111 | 01/24/20 | 764 | Gerard, Mitchell J | 40 | -1400 | 926404
PR | 111 | 02/21/20 | 496 | McCabe, Thomas C | 4 | 156 | 26973
PR | 111 | 03/13/20 | 342 | Hubbard, Robert W | 3 | 162 | 27203
PR | 111 | 03/20/20 | 569 | Barnhart, Joseph N | 1 | 54 | 27249
PR | 111 | 03/26/20 | 752 | Barnhart, Joseph N | 1 | 54 | 27328
PR | 112 | 10/19/18 | 438 | Barnhart, Joseph N | 6 | 276 | 21471
PR | 112 | 01/18/19 | 469 | Barnhart, Joseph N | 13 | 624 | 22490
PR | 112 | 01/18/19 | 506 | Martinez Reyes, Juan C | 14 | 392 | 22527
PR | 112 | 01/25/19 | 718 | Barnhart, Joseph N | 9 | 432 | 22563
PR | 112 | 01/25/19 | 755 | Martinez Reyes, Juan C | 6 | 168 | 22600
PR | 112 | 02/01/19 | 7 | Barnhart, Joseph N | 1 | 72 | 22636
PR | 112 | 02/01/19 | 15 | Crespin Portillo, Juan D | 2 | 34 | 22644
PR | 112 | 02/01/19 | 43 | Martinez Reyes, Juan C | 7 | 196 | 22672
PR | 112 | 02/01/19 | 67 | Waites, Thaddeus Z | 1 | 64.5 | 22696
PR | 120 | 03/08/19 | 302 | Serrano, Jeremiah G | 8 | 136 | 23041
PR | 120 | 03/08/19 | 306 | Taylor, Evan R | 8 | 208 | 23045
PR | 120 | 03/08/19 | 310 | Villalobos Tejada, Carlos F | 8 | 128 | 23049
PR | 120 | 03/08/19 | 311 | Waites, Thaddeus Z | 8 | 344 | 23050
PR | 120 | 03/15/19 | 496 | Barnhart, Joseph N | 10 | 480 | 23058
PR | 120 | 03/15/19 | 550 | Serrano, Jeremiah G | 26 | 442 | 23112
PR | 120 | 03/15/19 | 554 | Taylor, Evan R | 1 | 39 | 23116
PR | 120 | 03/15/19 | 554 | Taylor, Evan R | 32 | 832 | 23116
PR | 120 | 03/15/19 | 558 | Villalobos Tejada, Carlos F | 1 | 24 | 23120
PR | 120 | 03/15/19 | 558 | Villalobos Tejada, Carlos F | 5 | 80 | 23120
PR | 120 | 03/22/19 | 710 | Barnhart, Joseph N | 7 | 336 | 23131
PR | 120 | 03/22/19 | 763 | Serrano, Jeremiah G | 40 | 680 | 23184
PR | 120 | 03/22/19 | 768 | Taylor, Evan R | 1 | 39 | 23189
PR | 120 | 03/22/19 | 768 | Taylor, Evan R | 32 | 832 | 23189
PR | 120 | 03/22/19 | 772 | Villalobos Tejada, Carlos F | 1 | 24 | 23193
PR | 120 | 03/22/19 | 772 | Villalobos Tejada, Carlos F | 32 | 512 | 23193
PR | 120 | 03/22/19 | 773 | Waites, Thaddeus Z | 6 | 258 | 23194
PR | 120 | 03/29/19 | 975 | Serrano, Jeremiah G | 29 | 493 | 23259
PR | 120 | 03/29/19 | 980 | Taylor, Evan R | 40 | 1040 | 23264
PR | 120 | 03/29/19 | 984 | Villalobos Tejada, Carlos F | 24 | 384 | 23268
PR | 120 | 03/29/19 | 985 | Waites, Thaddeus Z | 14 | 602 | 23269
PR | 120 | 04/05/19 | 80 | Ascencio, Jose L | 24 | 672 | 23274
PR | 120 | 04/05/19 | 83 | Barnhart, Joseph N | 4 | 192 | 23277
PR | 120 | 04/05/19 | 138 | Serrano, Jeremiah G | 34 | 578 | 23332
PR | 120 | 04/05/19 | 143 | Taylor, Evan R | 40 | 1040 | 23337
PR | 120 | 04/05/19 | 147 | Villalobos Tejada, Carlos F | 40 | 640 | 23341
PR | 120 | 04/05/19 | 148 | Waites, Thaddeus Z | 20 | 860 | 23342
PR | 120 | 04/12/19 | 327 | Barnhart, Joseph N | 2 | 100 | 23351
PR | 120 | 04/12/19 | 382 | Serrano, Jeremiah G | 8 | 136 | 23406
PR | 120 | 04/12/19 | 387 | Taylor, Evan R | 29 | 754 | 23411
PR | 120 | 04/12/19 | 392 | Villalobos Tejada, Carlos F | 40 | 640 | 23416
PR | 120 | 04/12/19 | 393 | Waites, Thaddeus Z | 12 | 540 | 23417
PR | 120 | 04/19/19 | 521 | Ascencio, Jose L | 8 | 336 | 23422
PR | 120 | 04/19/19 | 524 | Barnhart, Joseph N | 1 | 50 | 23425
PR | 120 | 04/19/19 | 529 | Cornejo Orellana, Carlos E | 8 | 252 | 23430
PR | 120 | 04/19/19 | 532 | Crespin Portillo, Juan D | 8 | 204 | 23433
PR | 120 | 04/19/19 | 542 | Frausto Mendoza, Pedro | 8 | 168 | 23443
PR | 120 | 04/19/19 | 544 | Garcia Perez, Ervey O | 24 | 384 | 23445
PR | 120 | 04/19/19 | 585 | Taylor, Evan R | 16 | 416 | 23486
PR | 120 | 04/19/19 | 588 | Velasquez Cruz, Denis M | 8 | 348 | 23489
PR | 120 | 04/19/19 | 589 | Velasquez Cruz, Osman N | 8 | 264 | 23490
PR | 120 | 04/19/19 | 590 | Villalobos Tejada, Carlos F | 9 | 216 | 23491
PR | 120 | 04/19/19 | 590 | Villalobos Tejada, Carlos F | 40 | 640 | 23491
PR | 120 | 04/19/19 | 591 | Waites, Thaddeus Z | 8 | 540 | 23492
PR | 120 | 04/19/19 | 591 | Waites, Thaddeus Z | 19 | 855 | 23492
PR | 120 | 04/19/19 | 592 | Wennig, Johnathan M | 8 | 360 | 23493
PR | 120 | 04/26/19 | 741 | Ascencio, Jose L | 5 | 225 | 23498
PR | 120 | 04/26/19 | 752 | Crespin Portillo, Juan D | 5 | 142.5 | 23509
PR | 120 | 04/26/19 | 761 | Frausto Mendoza, Pedro | 5 | 115 | 23518
PR | 120 | 04/26/19 | 763 | Garcia Perez, Ervey O | 5 | 120 | 23520
PR | 120 | 04/26/19 | 763 | Garcia Perez, Ervey O | 24 | 384 | 23520
PR | 120 | 04/26/19 | 805 | Velasquez Cruz, Denis M | 5 | 240 | 23562
PR | 120 | 04/26/19 | 806 | Velasquez Cruz, Osman N | 5 | 125 | 23563
PR | 120 | 04/26/19 | 807 | Villalobos Tejada, Carlos F | 5 | 127.5 | 23564
PR | 120 | 04/26/19 | 807 | Villalobos Tejada, Carlos F | 24 | 408 | 23564
PR | 120 | 04/26/19 | 808 | Waites, Thaddeus Z | 1 | 67.5 | 23565
PR | 120 | 04/26/19 | 808 | Waites, Thaddeus Z | 20 | 900 | 23565
PR | 120 | 05/03/19 | 11 | Barnhart, Joseph N | 1 | 50 | 23573
PR | 120 | 05/03/19 | 31 | Garcia Perez, Ervey O | 40 | 640 | 23593
PR | 120 | 05/03/19 | 44 | Jimenez Montiel, Carlos A | 8 | 128 | 23606
PR | 120 | 05/03/19 | 72 | Taylor, Evan R | 24 | 696 | 23634
PR | 120 | 05/03/19 | 75 | Velasquez Cruz, Denis M | 6.5 | 312 | 23637
PR | 120 | 05/03/19 | 76 | Velasquez Cruz, Osman N | 6.5 | 243.75 | 23638
PR | 120 | 05/03/19 | 77 | Villalobos Tejada, Carlos F | 40 | 680 | 23639
PR | 120 | 05/03/19 | 78 | Waites, Thaddeus Z | 6.5 | 438.75 | 23640
PR | 120 | 05/03/19 | 78 | Waites, Thaddeus Z | 20 | 900 | 23640
PR | 120 | 05/03/19 | 79 | Wennig, Johnathan M | 6.5 | 214.5 | 23641
PR | 120 | 05/10/19 | 184 | Garcia Perez, Ervey O | 40 | 640 | 23668
PR | 120 | 05/10/19 | 197 | Jimenez Montiel, Carlos A | 3.5 | 56 | 23681
PR | 120 | 05/10/19 | 225 | Taylor, Evan R | 40 | 1160 | 23710
PR | 120 | 05/10/19 | 230 | Villalobos Tejada, Carlos F | 32 | 544 | 23715
PR | 120 | 05/10/19 | 231 | Waites, Thaddeus Z | 8 | 360 | 23716
PR | 120 | 05/17/19 | 457 | Taylor, Evan R | 40 | 1160 | 23788
PR | 120 | 05/17/19 | 462 | Villalobos Tejada, Carlos F | 40 | 680 | 23793
PR | 120 | 05/17/19 | 463 | Waites, Thaddeus Z | 10 | 450 | 23794
PR | 120 | 05/24/19 | 605 | Ascencio, Jose L | 4 | 180 | 23800
PR | 120 | 05/24/19 | 605 | Ascencio, Jose L | 10 | 300 | 23800
PR | 120 | 05/24/19 | 613 | Cornejo Orellana, Carlos E | 4 | 138 | 23808
PR | 120 | 05/24/19 | 613 | Cornejo Orellana, Carlos E | 6 | 138 | 23808
PR | 120 | 05/24/19 | 641 | Jimenez Montiel, Carlos A | 2 | 48 | 23836
PR | 120 | 05/24/19 | 641 | Jimenez Montiel, Carlos A | 14 | 224 | 23836
PR | 120 | 05/24/19 | 669 | Taylor, Evan R | 4 | 174 | 23864
PR | 120 | 05/24/19 | 669 | Taylor, Evan R | 40 | 1160 | 23864
PR | 120 | 05/24/19 | 674 | Villalobos Tejada, Carlos F | 4 | 102 | 23869
PR | 120 | 05/24/19 | 674 | Villalobos Tejada, Carlos F | 40 | 680 | 23869
PR | 120 | 05/24/19 | 675 | Waites, Thaddeus Z | 2 | 135 | 23870
PR | 120 | 05/24/19 | 675 | Waites, Thaddeus Z | 22 | 990 | 23870
PR | 120 | 05/31/19 | 878 | Ascencio, Jose L | 24 | 720 | 23878
PR | 120 | 05/31/19 | 915 | Jimenez Montiel, Carlos A | 23 | 368 | 23915
PR | 120 | 05/31/19 | 943 | Taylor, Evan R | 36 | 1044 | 23943
PR | 120 | 05/31/19 | 948 | Villalobos Tejada, Carlos F | 36 | 612 | 23948
PR | 120 | 06/07/19 | 180 | Ascencio, Jose L | 4 | 180 | 23955
PR | 120 | 06/07/19 | 180 | Ascencio, Jose L | 40 | 1200 | 23955
PR | 120 | 06/07/19 | 183 | Barnhart, Joseph N | 2 | 100 | 23958
PR | 120 | 06/07/19 | 245 | Taylor, Evan R | 4 | 174 | 24020
PR | 120 | 06/07/19 | 245 | Taylor, Evan R | 40 | 1160 | 24020
PR | 120 | 06/07/19 | 250 | Villalobos Tejada, Carlos F | 4 | 102 | 24025
PR | 120 | 06/07/19 | 250 | Villalobos Tejada, Carlos F | 40 | 680 | 24025
PR | 120 | 06/07/19 | 251 | Waites, Thaddeus Z | 20 | 900 | 24026
PR | 120 | 06/14/19 | 451 | Ascencio, Jose L | 6 | 270 | 24032
PR | 120 | 06/14/19 | 451 | Ascencio, Jose L | 40 | 1200 | 24032
PR | 120 | 06/14/19 | 513 | Taylor, Evan R | 13 | 565.5 | 24094
PR | 120 | 06/14/19 | 513 | Taylor, Evan R | 40 | 1160 | 24094
PR | 120 | 06/14/19 | 516 | Velasquez Cruz, Denis M | 6 | 288 | 24097
PR | 120 | 06/14/19 | 517 | Velasquez Cruz, Osman N | 6 | 225 | 24098
PR | 120 | 06/14/19 | 518 | Villalobos Tejada, Carlos F | 9 | 229.5 | 24099
PR | 120 | 06/14/19 | 518 | Villalobos Tejada, Carlos F | 40 | 680 | 24099
PR | 120 | 06/14/19 | 519 | Waites, Thaddeus Z | 5 | 337.5 | 24100
PR | 120 | 06/14/19 | 519 | Waites, Thaddeus Z | 8 | 360 | 24100
PR | 120 | 06/14/19 | 519 | Waites, Thaddeus Z | 20 | 900 | 24100
PR | 120 | 06/14/19 | 520 | Wennig, Johnathan M | 7 | 231 | 24101
PR | 120 | 06/21/19 | 619 | Ascencio, Jose L | 6 | 270 | 24105
PR | 120 | 06/21/19 | 619 | Ascencio, Jose L | 40 | 1200 | 24105
PR | 120 | 06/21/19 | 635 | Cruz Reyes, Jose | 6 | 261 | 24121
PR | 120 | 06/21/19 | 635 | Cruz Reyes, Jose | 40 | 1160 | 24121
PR | 120 | 06/21/19 | 684 | Taylor, Evan R | 6 | 261 | 24170
PR | 120 | 06/21/19 | 684 | Taylor, Evan R | 40 | 1160 | 24170
PR | 120 | 06/21/19 | 689 | Villalobos Tejada, Carlos F | 6 | 153 | 24175
PR | 120 | 06/21/19 | 689 | Villalobos Tejada, Carlos F | 40 | 680 | 24175
PR | 120 | 06/21/19 | 690 | Waites, Thaddeus Z | 3.5 | 236.25 | 24176
PR | 120 | 06/21/19 | 690 | Waites, Thaddeus Z | 23 | 1035 | 24176
PR | 120 | 06/21/19 | 691 | Wennig, Johnathan M | 4 | 132 | 24177
PR | 120 | 06/28/19 | 837 | Ascencio, Jose L | 2 | 90 | 24181
PR | 120 | 06/28/19 | 837 | Ascencio, Jose L | 40 | 1200 | 24181
PR | 120 | 06/28/19 | 853 | Cruz Reyes, Jose | 2 | 87 | 24197
PR | 120 | 06/28/19 | 853 | Cruz Reyes, Jose | 40 | 1160 | 24197
PR | 120 | 06/28/19 | 901 | Taylor, Evan R | 2 | 87 | 24245
PR | 120 | 06/28/19 | 901 | Taylor, Evan R | 40 | 1160 | 24245
PR | 120 | 06/28/19 | 906 | Villalobos Tejada, Carlos F | 2 | 51 | 24250
PR | 120 | 06/28/19 | 906 | Villalobos Tejada, Carlos F | 40 | 680 | 24250
PR | 120 | 06/28/19 | 907 | Waites, Thaddeus Z | 17 | 765 | 24251
PR | 120 | 06/28/19 | 908 | Wennig, Johnathan M | 8 | 264 | 24252
PR | 120 | 07/05/19 | 9 | Ascencio, Jose L | 39 | 1170 | 24256
PR | 120 | 07/05/19 | 12 | Barnhart, Joseph N | 2 | 100 | 24259
PR | 120 | 07/05/19 | 25 | Cruz Reyes, Jose | 39 | 1131 | 24272
PR | 120 | 07/05/19 | 29 | Eliassen, Cory H | 7 | 189 | 24276
PR | 120 | 07/05/19 | 72 | Taylor, Evan R | 39 | 1131 | 24320
PR | 120 | 07/05/19 | 77 | Villalobos Tejada, Carlos F | 39 | 663 | 24325
PR | 120 | 07/05/19 | 78 | Waites, Thaddeus Z | 10.5 | 472.5 | 24326
PR | 120 | 07/12/19 | 279 | Ascencio, Jose L | 32 | 960 | 24331
PR | 120 | 07/12/19 | 294 | Cruz Reyes, Jose | 32 | 928 | 24346
PR | 120 | 07/12/19 | 343 | Taylor, Evan R | 32 | 928 | 24395
PR | 120 | 07/12/19 | 348 | Villalobos Tejada, Carlos F | 32 | 544 | 24400
PR | 120 | 07/12/19 | 349 | Waites, Thaddeus Z | 16 | 720 | 24401
PR | 120 | 07/19/19 | 509 | Ascencio, Jose L | 16 | 480 | 24408
PR | 120 | 07/19/19 | 524 | Cruz Reyes, Jose | 8 | 232 | 24423
PR | 120 | 07/19/19 | 573 | Taylor, Evan R | 16 | 464 | 24472
PR | 120 | 07/19/19 | 578 | Villalobos Tejada, Carlos F | 8 | 136 | 24477
PR | 120 | 07/19/19 | 579 | Waites, Thaddeus Z | 16 | 720 | 24478
PR | 120 | 07/26/19 | 676 | Taylor, Evan R | 40 | 1160 | 24625
PR | 120 | 07/26/19 | 681 | Villalobos Tejada, Carlos F | 8 | 136 | 24630
PR | 120 | 07/26/19 | 682 | Waites, Thaddeus Z | 10 | 450 | 24631
PR | 120 | 08/02/19 | 67 | Taylor, Evan R | 32 | 928 | 24698
PR | 120 | 08/02/19 | 73 | Waites, Thaddeus Z | 9 | 405 | 24704
PR | 120 | 08/09/19 | 257 | Ascencio, Jose L | 8 | 240 | 24710
PR | 120 | 08/09/19 | 260 | Barnhart, Joseph N | 1 | 50 | 24713
PR | 120 | 08/09/19 | 319 | Taylor, Evan R | 39 | 1131 | 24772
PR | 120 | 08/09/19 | 325 | Waites, Thaddeus Z | 9 | 405 | 24778
PR | 120 | 08/16/19 | 579 | Cruz Reyes, Jose | 8 | 232 | 24798
PR | 120 | 08/16/19 | 627 | Taylor, Evan R | 16 | 464 | 24846
PR | 120 | 08/16/19 | 633 | Waites, Thaddeus Z | 3 | 135 | 24852
PR | 120 | 08/23/19 | 864 | Taylor, Evan R | 24 | 696 | 24922
PR | 120 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A | 8 | 256 | 24931
PR | 120 | 08/30/19 | 1055 | Taylor, Evan R | 40 | 1160 | 24997
PR | 120 | 09/06/19 | 76 | Taylor, Evan R | 32 | 928 | 25074
PR | 120 | 09/06/19 | 82 | Waites, Thaddeus Z | 6 | 270 | 25080
PR | 120 | 09/13/19 | 259 | Garcia Perez, Ervey O | 16 | 256 | 25108
PR | 120 | 09/13/19 | 299 | Taylor, Evan R | 40 | 1160 | 25148
PR | 120 | 09/13/19 | 302 | Velasquez Cruz, Denis M | 16 | 512 | 25151
PR | 120 | 09/13/19 | 303 | Velasquez Cruz, Osman N | 16 | 400 | 25152
PR | 120 | 09/13/19 | 305 | Waites, Thaddeus Z | 4 | 180 | 25154
PR | 120 | 09/20/19 | 473 | Ascencio, Jose L | 8 | 240 | 25159
PR | 120 | 09/20/19 | 476 | Barnhart, Joseph N | 2 | 100 | 25162
PR | 120 | 09/20/19 | 509 | Hubbard, Robert W | 3 | 150 | 25195
PR | 120 | 09/20/19 | 537 | Taylor, Evan R | 40 | 1160 | 25223
PR | 120 | 09/20/19 | 540 | Velasquez Cruz, Denis M | 24 | 768 | 25226
PR | 120 | 09/20/19 | 541 | Velasquez Cruz, Osman N | 24 | 600 | 25227
PR | 120 | 09/20/19 | 543 | Waites, Thaddeus Z | 4 | 180 | 25229
PR | 120 | 09/27/19 | 629 | Ascencio, Jose L | 8 | 240 | 25234
PR | 120 | 09/27/19 | 696 | Taylor, Evan R | 40 | 1160 | 25301
PR | 120 | 09/27/19 | 699 | Velasquez Cruz, Denis M | 24 | 768 | 25304
PR | 120 | 09/27/19 | 700 | Velasquez Cruz, Osman N | 24 | 600 | 25305
PR | 120 | 10/04/19 | 5 | Ascencio, Jose L | 40 | 1200 | 25312
PR | 120 | 10/04/19 | 28 | Garcia Perez, Ervey O | 16 | 256 | 25335
PR | 120 | 10/04/19 | 72 | Taylor, Evan R | 40 | 1160 | 25379
PR | 120 | 10/04/19 | 75 | Velasquez Cruz, Denis M | 11 | 352 | 25382
PR | 120 | 10/04/19 | 76 | Velasquez Cruz, Osman N | 11 | 275 | 25383
PR | 120 | 10/04/19 | 78 | Waites, Thaddeus Z | 6 | 270 | 25385
PR | 120 | 10/11/19 | 260 | Ascencio, Jose L | 40 | 1200 | 25393
PR | 120 | 10/11/19 | 326 | Taylor, Evan R | 40 | 1160 | 25460
PR | 120 | 10/11/19 | 333 | Wennig, Johnathan M | 16 | 528 | 25467
PR | 120 | 10/18/19 | 454 | Ascencio, Jose L | 40 | 1200 | 25470
PR | 120 | 10/18/19 | 474 | Frausto Mendoza, Pedro | 16 | 368 | 25490
PR | 120 | 10/18/19 | 519 | Taylor, Evan R | 40 | 1160 | 25536
PR | 120 | 10/18/19 | 525 | Waites, Thaddeus Z | 18 | 810 | 25542
PR | 120 | 10/18/19 | 526 | Wennig, Johnathan M | 40 | 1320 | 25543
PR | 120 | 10/25/19 | 589 | Ascencio, Jose L | 36 | 1080 | 25546
PR | 120 | 10/25/19 | 611 | Garcia Perez, Ervey O | 16 | 256 | 25568
PR | 120 | 10/25/19 | 655 | Taylor, Evan R | 36 | 1044 | 25612
PR | 120 | 10/25/19 | 661 | Waites, Thaddeus Z | 14 | 630 | 25618
PR | 120 | 10/25/19 | 662 | Wennig, Johnathan M | 36 | 1188 | 25619
PR | 120 | 11/01/19 | 5 | Ascencio, Jose L | 4.5 | 222.75 | 25622
PR | 120 | 11/01/19 | 5 | Ascencio, Jose L | 40 | 1320 | 25622
PR | 120 | 11/01/19 | 8 | Barnhart, Joseph N | 6 | 324 | 25625
PR | 120 | 11/01/19 | 15 | Cornejo Orellana, Carlos E | 8 | 208 | 25632
PR | 120 | 11/01/19 | 71 | Taylor, Evan R | 4.5 | 222.75 | 25688
PR | 120 | 11/01/19 | 71 | Taylor, Evan R | 40 | 1320 | 25688
PR | 120 | 11/01/19 | 76 | Villalobos Tejada, Carlos F | 4.5 | 128.25 | 25693
PR | 120 | 11/01/19 | 76 | Villalobos Tejada, Carlos F | 8 | 152 | 25693
PR | 120 | 11/01/19 | 77 | Waites, Thaddeus Z | 16 | 784 | 25694
PR | 120 | 11/01/19 | 78 | Wennig, Johnathan M | 4.5 | 243 | 25695
PR | 120 | 11/01/19 | 78 | Wennig, Johnathan M | 40 | 1440 | 25695
PR | 120 | 11/08/19 | 179 | Ascencio, Jose L | 40 | 1320 | 25698
PR | 120 | 11/08/19 | 214 | Hubbard, Robert W | 2 | 108 | 25733
PR | 120 | 11/08/19 | 245 | Taylor, Evan R | 40 | 1320 | 25764
PR | 120 | 11/08/19 | 251 | Waites, Thaddeus Z | 24 | 1176 | 25770
PR | 120 | 11/08/19 | 252 | Wennig, Johnathan M | 40 | 1440 | 25771
PR | 120 | 11/15/19 | 439 | Ascencio, Jose L | 24 | 792 | 25774
PR | 120 | 11/15/19 | 442 | Barnhart, Joseph N | 2 | 108 | 25777
PR | 120 | 11/15/19 | 504 | Taylor, Evan R | 40 | 1320 | 25840
PR | 120 | 11/15/19 | 509 | Villalobos Tejada, Carlos F | 8 | 152 | 25845
PR | 120 | 11/15/19 | 510 | Waites, Thaddeus Z | 14 | 686 | 25846
PR | 120 | 11/15/19 | 511 | Wennig, Johnathan M | 40 | 1440 | 25847
PR | 120 | 11/22/19 | 610 | Ascencio, Jose L | 24 | 792 | 25850
PR | 120 | 11/22/19 | 613 | Barnhart, Joseph N | 2 | 108 | 25853
PR | 120 | 11/22/19 | 675 | Taylor, Evan R | 38 | 1254 | 25915
PR | 120 | 11/22/19 | 680 | Villalobos Tejada, Carlos F | 8 | 152 | 25920
PR | 120 | 11/22/19 | 681 | Waites, Thaddeus Z | 28 | 1372 | 25921
PR | 120 | 11/22/19 | 682 | Wennig, Johnathan M | 13 | 468 | 25922
PR | 120 | 11/27/19 | 844 | Ascencio, Jose L | 32 | 1056 | 25925
PR | 120 | 11/27/19 | 909 | Taylor, Evan R | 24 | 792 | 25990
PR | 120 | 11/27/19 | 914 | Villalobos Tejada, Carlos F | 16 | 304 | 25995
PR | 120 | 11/27/19 | 915 | Waites, Thaddeus Z | 18 | 882 | 25996
PR | 120 | 11/27/19 | 916 | Wennig, Johnathan M | 40 | 1440 | 25997
PR | 120 | 12/06/19 | 96 | Taylor, Evan R | 24 | 792 | 26068
PR | 120 | 12/06/19 | 102 | Waites, Thaddeus Z | 14 | 686 | 26074
PR | 120 | 12/06/19 | 103 | Wennig, Johnathan M | 32 | 1152 | 26075
PR | 120 | 12/13/19 | 391 | Ascencio, Jose L | 40 | 1320 | 26156
PR | 120 | 12/13/19 | 394 | Barnhart, Joseph N | 5 | 270 | 26159
PR | 120 | 12/13/19 | 457 | Taylor, Evan R | 16 | 528 | 26223
PR | 120 | 12/13/19 | 463 | Waites, Thaddeus Z | 21 | 1029 | 26229
PR | 120 | 12/13/19 | 464 | Wennig, Johnathan M | 40 | 1440 | 26230
PR | 120 | 12/20/19 | 610 | Taylor, Evan R | 16 | 528 | 26299
PR | 120 | 12/20/19 | 616 | Waites, Thaddeus Z | 12 | 588 | 26305
PR | 120 | 12/20/19 | 617 | Wennig, Johnathan M | 16 | 576 | 26306
PR | 120 | 12/27/19 | 701 | Ascencio, Jose L | 16 | 528 | 26309
PR | 120 | 12/27/19 | 727 | Gerard, Jordan E | 24 | 1008 | 26335
PR | 120 | 12/27/19 | 774 | Waites, Thaddeus Z | 10 | 490 | 26382
PR | 120 | 12/27/19 | 775 | Wennig, Johnathan M | 24 | 864 | 26383
PR | 120 | 01/03/20 | 4 | Ascencio, Jose L | 32 | 1056 | 26386
PR | 120 | 01/03/20 | 14 | Cornejo Orellana, Carlos E | 16 | 416 | 26396
PR | 120 | 01/03/20 | 15 | Cortes Mendiola, Victor H | 6 | 300 | 26397
PR | 120 | 01/03/20 | 71 | Taylor, Evan R | 16 | 528 | 26454
PR | 120 | 01/03/20 | 76 | Villalobos Tejada, Carlos F | 16 | 304 | 26459
PR | 120 | 01/03/20 | 77 | Waites, Thaddeus Z | 21 | 1029 | 26460
PR | 120 | 01/10/20 | 344 | Taylor, Evan R | 16 | 528 | 26532
PR | 120 | 01/10/20 | 350 | Waites, Thaddeus Z | 16 | 784 | 26538
PR | 120 | 01/24/20 | 763 | Gerard, Jordan E | 24 | -1008 | 926403
PR | 120 | 01/31/20 | 838 | Barnhart, Joseph N | 1 | 54 | 26698
PR | 120 | 03/26/20 | 811 | Taylor, Evan R | 13 | 429 | 27387
PR | 120 | 03/26/20 | 817 | Waites, Thaddeus Z | 13 | 637 | 27393
PR | 130 | 08/30/19 | 1049 | Sanders, Allen O | 2 | 98 | 24991
PR | 130 | 11/01/19 | 66 | Sanders, Allen O | 2 | 108 | 25683
PR | 130 | 11/22/19 | 670 | Sanders, Allen O | 2.5 | 135 | 25910
PR | 130 | 11/27/19 | 904 | Sanders, Allen O | 2 | 108 | 25985
PR | 130 | 12/20/19 | 557 | Cruz Gonzalez, Julio C | 26 | 728 | 26246
PR | 130 | 12/20/19 | 562 | Eliassen, Cory H | 8 | 240 | 26251
PR | 130 | 12/20/19 | 568 | Gauthier, Dillon R | 8 | 144 | 26257
PR | 130 | 12/20/19 | 605 | Sanders, Allen O | 14.5 | 783 | 26294
PR | 130 | 12/27/19 | 714 | Cruz Gonzalez, Julio C | 17 | 476 | 26322
PR | 130 | 12/27/19 | 763 | Sanders, Allen O | 2 | 108 | 26371
PR | 130 | 01/03/20 | 17 | Cruz Gonzalez, Julio C | 22 | 616 | 26400
PR | 130 | 01/03/20 | 29 | Gauthier, Dillon R | 8 | 144 | 26412
PR | 130 | 01/03/20 | 66 | Sanders, Allen O | 4 | 216 | 26449
PR | 130 | 01/10/20 | 290 | Cruz Gonzalez, Julio C | 36 | 1008 | 26477
PR | 130 | 01/10/20 | 302 | Gauthier, Dillon R | 24 | 432 | 26489
PR | 130 | 01/10/20 | 339 | Sanders, Allen O | 8 | 432 | 26527
PR | 130 | 01/10/20 | 345 | Trower-Kelly, Fidel D | 40 | 840 | 26533
PR | 130 | 01/17/20 | 546 | Barnhart, Joseph N | 1 | 54 | 26545
PR | 130 | 01/17/20 | 549 | Boss, Benjamin T | 8 | 128 | 26548
PR | 130 | 01/17/20 | 556 | Cruz Gonzalez, Julio C | 22 | 616 | 26555
PR | 130 | 01/17/20 | 602 | Romero Garza, Jesus I | 8 | 184 | 26601
PR | 130 | 01/17/20 | 605 | Sanders, Allen O | 8 | 432 | 26604
PR | 130 | 01/17/20 | 611 | Trower-Kelly, Fidel D | 8 | 168 | 26610
PR | 130 | 01/24/20 | 689 | Cruz Gonzalez, Julio C | 37 | 1036 | 26632
PR | 130 | 01/24/20 | 691 | Cruz Reyes, Jose | 16 | 512 | 26634
PR | 130 | 01/24/20 | 733 | Romero Garza, Jesus I | 40 | 920 | 26676
PR | 130 | 01/24/20 | 736 | Sanders, Allen O | 5.5 | 297 | 26679
PR | 130 | 01/24/20 | 742 | Trower-Kelly, Fidel D | 16 | 336 | 26685
PR | 130 | 01/31/20 | 838 | Barnhart, Joseph N | 1 | 54 | 26698
PR | 130 | 01/31/20 | 848 | Cruz Gonzalez, Julio C | 40 | 1120 | 26709
PR | 130 | 01/31/20 | 850 | Cruz Reyes, Jose | 40 | 1280 | 26711
PR | 130 | 01/31/20 | 897 | Sanders, Allen O | 9.5 | 513 | 26758
PR | 130 | 02/07/20 | 39 | Cruz Gonzalez, Julio C | 16 | 448 | 26787
PR | 130 | 02/07/20 | 41 | Cruz Reyes, Jose | 16 | 512 | 26789
PR | 130 | 02/07/20 | 50 | Gauthier, Dillon R | 16 | 288 | 26798
PR | 130 | 02/07/20 | 88 | Sanders, Allen O | 4 | 216 | 26836
PR | 130 | 02/14/20 | 242 | Boss, Benjamin T | 8 | 144 | 26858
PR | 130 | 02/14/20 | 243 | Boss, Kyle A | 8 | 168 | 26859
PR | 130 | 02/14/20 | 249 | Cruz Gonzalez, Julio C | 8 | 224 | 26865
PR | 130 | 02/14/20 | 251 | Cruz Reyes, Jose | 16 | 512 | 26867
PR | 130 | 02/14/20 | 292 | Roberts, Lake A | 2 | 50 | 26908
PR | 130 | 02/14/20 | 298 | Sanders, Allen O | 5 | 270 | 26914
PR | 130 | 02/14/20 | 304 | Trower-Kelly, Fidel D | 16 | 336 | 26920
PR | 130 | 02/21/20 | 466 | Cruz Gonzalez, Julio C | 21 | 588 | 26943
PR | 130 | 02/21/20 | 468 | Cruz Reyes, Jose | 8 | 256 | 26945
PR | 130 | 02/21/20 | 514 | Sanders, Allen O | 10.5 | 567 | 26991
PR | 130 | 02/21/20 | 520 | Trower-Kelly, Fidel D | 8 | 168 | 26997
PR | 130 | 02/28/20 | 684 | Barnhart, Joseph N | 4 | 216 | 27012
PR | 130 | 02/28/20 | 694 | Cruz Gonzalez, Julio C | 21.5 | 602 | 27022
PR | 130 | 02/28/20 | 743 | Sanders, Allen O | 7 | 378 | 27071
PR | 130 | 03/06/20 | 46 | Barnhart, Joseph N | 6.5 | 351 | 27090
PR | 130 | 03/06/20 | 56 | Cruz Gonzalez, Julio C | 16 | 448 | 27100
PR | 130 | 03/06/20 | 58 | Cruz Reyes, Jose | 8 | 256 | 27102
PR | 130 | 03/06/20 | 105 | Sanders, Allen O | 1.5 | 81 | 27149
PR | 130 | 03/13/20 | 311 | Barnhart, Joseph N | 1 | 54 | 27171
PR | 130 | 03/13/20 | 369 | Sanders, Allen O | 1 | 54 | 27230
PR | 130 | 03/20/20 | 627 | Sanders, Allen O | 1.5 | 81 | 27307
PR | 130 | 03/26/20 | 806 | Sanders, Allen O | 2 | 108 | 27382
PR | 130 | 05/08/20 | 215 | Sanders, Allen O | 2 | 108 | 27770
PR | 140 | 08/09/19 | 319 | Taylor, Evan R | 1 | 29 | 24772
PR | 140 | 08/09/19 | 325 | Waites, Thaddeus Z | 2 | 90 | 24778
PR | 140 | 08/30/19 | 1058 | Velasquez Cruz, Denis M | 10 | 320 | 25000
PR | 140 | 08/30/19 | 1059 | Velasquez Cruz, Osman N | 2 | 50 | 25003
PR | 140 | 08/30/19 | 1061 | Waites, Thaddeus Z | 4 | 180 | 25005
PR | 140 | 09/06/19 | 79 | Velasquez Cruz, Denis M | 16 | 512 | 25077
PR | 140 | 09/06/19 | 80 | Velasquez Cruz, Osman N | 16 | 400 | 25078
PR | 140 | 09/06/19 | 82 | Waites, Thaddeus Z | 2 | 90 | 25080
PR | 140 | 09/13/19 | 302 | Velasquez Cruz, Denis M | 16 | 512 | 25151
PR | 140 | 09/13/19 | 303 | Velasquez Cruz, Osman N | 24 | 600 | 25152
PR | 140 | 09/13/19 | 305 | Waites, Thaddeus Z | 6 | 270 | 25154
PR | 140 | 09/20/19 | 540 | Velasquez Cruz, Denis M | 16 | 512 | 25226
PR | 140 | 09/20/19 | 541 | Velasquez Cruz, Osman N | 16 | 400 | 25227
PR | 140 | 09/20/19 | 543 | Waites, Thaddeus Z | 2 | 90 | 25229
PR | 140 | 09/27/19 | 699 | Velasquez Cruz, Denis M | 16 | 512 | 25304
PR | 140 | 09/27/19 | 700 | Velasquez Cruz, Osman N | 16 | 400 | 25305
PR | 140 | 09/27/19 | 702 | Waites, Thaddeus Z | 2 | 90 | 25307
PR | 140 | 12/06/19 | 102 | Waites, Thaddeus Z | 2 | 98 | 26074
PR | 140 | 01/17/20 | 610 | Taylor, Evan R | 8 | 264 | 26609
PR | 140 | 02/14/20 | 271 | Hubbard, Robert W | 5 | 270 | 26887
PR | 140 | 02/14/20 | 281 | McCabe, Thomas C | 8 | 312 | 26897
PR | 140 | 02/14/20 | 292 | Roberts, Lake A | 8 | 200 | 26908
PR | 140 | 02/28/20 | 684 | Barnhart, Joseph N | 2 | 108 | 27012
PR | 140 | 02/28/20 | 748 | Taylor, Evan R | 4 | 132 | 27076
PR | 140 | 02/28/20 | 754 | Waites, Thaddeus Z | 6 | 294 | 27082
PR | 141 | 06/14/19 | 483 | Hubbard, Robert W | 3 | 150 | 24064
PR | 141 | 06/21/19 | 690 | Waites, Thaddeus Z | 1 | 45 | 24176
PR | 141 | 07/05/19 | 44 | Hubbard, Robert W | 2 | 100 | 24291
PR | 141 | 07/19/19 | 509 | Ascencio, Jose L | 16 | 480 | 24408
PR | 141 | 07/19/19 | 524 | Cruz Reyes, Jose | 32 | 928 | 24423
PR | 141 | 07/19/19 | 573 | Taylor, Evan R | 24 | 696 | 24472
PR | 141 | 07/19/19 | 578 | Villalobos Tejada, Carlos F | 24 | 408 | 24477
PR | 141 | 07/19/19 | 579 | Waites, Thaddeus Z | 4 | 180 | 24478
PR | 141 | 07/26/19 | 628 | Cruz Reyes, Jose | 40 | 1160 | 24577
PR | 141 | 07/26/19 | 681 | Villalobos Tejada, Carlos F | 32 | 544 | 24630
PR | 141 | 07/26/19 | 682 | Waites, Thaddeus Z | 10 | 450 | 24631
PR | 141 | 08/02/19 | 5 | Ascencio, Jose L | 40 | 1200 | 24636
PR | 141 | 08/02/19 | 20 | Cruz Reyes, Jose | 40 | 1160 | 24651
PR | 141 | 08/02/19 | 36 | Hubbard, Dustin R | 3 | 75 | 24667
PR | 141 | 08/02/19 | 72 | Villalobos Tejada, Carlos F | 40 | 680 | 24703
PR | 141 | 08/02/19 | 73 | Waites, Thaddeus Z | 9 | 405 | 24704
PR | 141 | 08/09/19 | 257 | Ascencio, Jose L | 32 | 960 | 24710
PR | 141 | 08/09/19 | 272 | Cruz Reyes, Jose | 40 | 1160 | 24725
PR | 141 | 08/09/19 | 289 | Hubbard, Dustin R | 4 | 100 | 24742
PR | 141 | 08/09/19 | 324 | Villalobos Tejada, Carlos F | 40 | 680 | 24777
PR | 141 | 08/09/19 | 325 | Waites, Thaddeus Z | 9 | 405 | 24778
PR | 141 | 08/16/19 | 564 | Ascencio, Jose L | 40 | 1200 | 24783
PR | 141 | 08/16/19 | 632 | Villalobos Tejada, Carlos F | 40 | 680 | 24851
PR | 141 | 08/16/19 | 633 | Waites, Thaddeus Z | 9 | 405 | 24852
PR | 141 | 08/23/19 | 800 | Ascencio, Jose L | 40 | 1200 | 24858
PR | 141 | 08/23/19 | 810 | Cornejo Orellana, Carlos E | 40 | 920 | 24868
PR | 141 | 08/23/19 | 823 | Garcia Perez, Ervey O | 40 | 640 | 24881
PR | 141 | 08/23/19 | 869 | Villalobos Tejada, Carlos F | 40 | 680 | 24927
PR | 141 | 08/23/19 | 870 | Waites, Thaddeus Z | 20 | 900 | 24928
PR | 141 | 08/30/19 | 991 | Ascencio, Jose L | 40 | 1200 | 24933
PR | 141 | 08/30/19 | 1001 | Cornejo Orellana, Carlos E | 40 | 920 | 24943
PR | 141 | 08/30/19 | 1014 | Garcia Perez, Ervey O | 40 | 640 | 24956
PR | 141 | 08/30/19 | 1060 | Villalobos Tejada, Carlos F | 40 | 680 | 25004
PR | 141 | 08/30/19 | 1061 | Waites, Thaddeus Z | 16 | 720 | 25005
PR | 141 | 09/06/19 | 12 | Ascencio, Jose L | 32 | 960 | 25010
PR | 141 | 09/06/19 | 22 | Cornejo Orellana, Carlos E | 32 | 736 | 25020
PR | 141 | 09/06/19 | 35 | Garcia Perez, Ervey O | 32 | 512 | 25033
PR | 141 | 09/06/19 | 81 | Villalobos Tejada, Carlos F | 32 | 544 | 25079
PR | 141 | 09/06/19 | 82 | Waites, Thaddeus Z | 8 | 360 | 25080
PR | 141 | 09/13/19 | 236 | Ascencio, Jose L | 40 | 1200 | 25085
PR | 141 | 09/13/19 | 246 | Cornejo Orellana, Carlos E | 40 | 920 | 25095
PR | 141 | 09/13/19 | 259 | Garcia Perez, Ervey O | 24 | 384 | 25108
PR | 141 | 09/13/19 | 304 | Villalobos Tejada, Carlos F | 40 | 680 | 25153
PR | 141 | 09/13/19 | 305 | Waites, Thaddeus Z | 10 | 450 | 25154
PR | 141 | 09/20/19 | 473 | Ascencio, Jose L | 32 | 960 | 25159
PR | 141 | 09/20/19 | 483 | Cornejo Orellana, Carlos E | 40 | 920 | 25169
PR | 141 | 09/20/19 | 496 | Garcia Perez, Ervey O | 40 | 640 | 25182
PR | 141 | 09/20/19 | 542 | Villalobos Tejada, Carlos F | 40 | 680 | 25228
PR | 141 | 09/20/19 | 543 | Waites, Thaddeus Z | 10 | 450 | 25229
PR | 141 | 09/27/19 | 629 | Ascencio, Jose L | 32 | 960 | 25234
PR | 141 | 09/27/19 | 639 | Cornejo Orellana, Carlos E | 40 | 920 | 25244
PR | 141 | 09/27/19 | 652 | Garcia Perez, Ervey O | 40 | 640 | 25257
PR | 141 | 09/27/19 | 701 | Villalobos Tejada, Carlos F | 40 | 680 | 25306
PR | 141 | 09/27/19 | 702 | Waites, Thaddeus Z | 18 | 810 | 25307
PR | 141 | 10/04/19 | 15 | Cornejo Orellana, Carlos E | 40 | 920 | 25322
PR | 141 | 10/04/19 | 28 | Garcia Perez, Ervey O | 24 | 384 | 25335
PR | 141 | 10/04/19 | 77 | Villalobos Tejada, Carlos F | 40 | 680 | 25384
PR | 141 | 10/04/19 | 78 | Waites, Thaddeus Z | 6 | 270 | 25385
PR | 141 | 10/11/19 | 270 | Cornejo Orellana, Carlos E | 40 | 920 | 25404
PR | 141 | 10/11/19 | 281 | Frausto Mendoza, Pedro | 8 | 184 | 25415
PR | 141 | 10/11/19 | 283 | Garcia Perez, Ervey O | 40 | 640 | 25417
PR | 141 | 10/11/19 | 331 | Villalobos Tejada, Carlos F | 40 | 680 | 25465
PR | 141 | 10/18/19 | 464 | Cornejo Orellana, Carlos E | 40 | 920 | 25480
PR | 141 | 10/18/19 | 476 | Garcia Perez, Ervey O | 40 | 640 | 25492
PR | 141 | 10/18/19 | 524 | Villalobos Tejada, Carlos F | 40 | 680 | 25541
PR | 141 | 10/25/19 | 600 | Cornejo Orellana, Carlos E | 36 | 828 | 25557
PR | 141 | 10/25/19 | 611 | Garcia Perez, Ervey O | 20 | 320 | 25568
PR | 141 | 10/25/19 | 660 | Villalobos Tejada, Carlos F | 36 | 612 | 25617
PR | 141 | 10/25/19 | 661 | Waites, Thaddeus Z | 10 | 450 | 25618
PR | 141 | 11/01/19 | 15 | Cornejo Orellana, Carlos E | 32 | 832 | 25632
PR | 141 | 11/01/19 | 76 | Villalobos Tejada, Carlos F | 32 | 608 | 25693
PR | 141 | 11/01/19 | 77 | Waites, Thaddeus Z | 16.5 | 808.5 | 25694
PR | 141 | 11/08/19 | 189 | Cornejo Orellana, Carlos E | 32 | 832 | 25708
PR | 141 | 11/08/19 | 250 | Villalobos Tejada, Carlos F | 40 | 760 | 25769
PR | 141 | 11/08/19 | 251 | Waites, Thaddeus Z | 4 | 196 | 25770
PR | 141 | 11/15/19 | 439 | Ascencio, Jose L | 16 | 528 | 25774
PR | 141 | 11/15/19 | 449 | Cornejo Orellana, Carlos E | 32 | 832 | 25784
PR | 141 | 11/15/19 | 509 | Villalobos Tejada, Carlos F | 32 | 608 | 25845
PR | 141 | 11/15/19 | 510 | Waites, Thaddeus Z | 14 | 686 | 25846
PR | 141 | 11/22/19 | 610 | Ascencio, Jose L | 6 | 198 | 25850
PR | 141 | 11/22/19 | 620 | Cornejo Orellana, Carlos E | 38 | 988 | 25860
PR | 141 | 11/22/19 | 680 | Villalobos Tejada, Carlos F | 22 | 418 | 25920
PR | 141 | 11/22/19 | 681 | Waites, Thaddeus Z | 5 | 245 | 25921
PR | 141 | 11/22/19 | 682 | Wennig, Johnathan M | 24 | 864 | 25922
PR | 141 | 11/27/19 | 844 | Ascencio, Jose L | 8 | 264 | 25925
PR | 141 | 11/27/19 | 854 | Cornejo Orellana, Carlos E | 40 | 1040 | 25935
PR | 141 | 11/27/19 | 909 | Taylor, Evan R | 16 | 528 | 25990
PR | 141 | 11/27/19 | 914 | Villalobos Tejada, Carlos F | 24 | 456 | 25995
PR | 141 | 11/27/19 | 915 | Waites, Thaddeus Z | 14 | 686 | 25996
PR | 141 | 12/06/19 | 30 | Ascencio, Jose L | 32 | 1056 | 26001
PR | 141 | 12/06/19 | 40 | Cornejo Orellana, Carlos E | 24 | 624 | 26012
PR | 141 | 12/06/19 | 65 | Hubbard, Robert W | 1 | 54 | 26037
PR | 141 | 12/06/19 | 96 | Taylor, Evan R | 8 | 264 | 26068
PR | 141 | 12/06/19 | 101 | Villalobos Tejada, Carlos F | 32 | 608 | 26073
PR | 141 | 12/06/19 | 102 | Waites, Thaddeus Z | 14 | 686 | 26074
PR | 141 | 12/13/19 | 401 | Cornejo Orellana, Carlos E | 32 | 832 | 26166
PR | 141 | 12/13/19 | 462 | Villalobos Tejada, Carlos F | 40 | 760 | 26228
PR | 141 | 12/13/19 | 463 | Waites, Thaddeus Z | 14 | 686 | 26229
PR | 141 | 12/20/19 | 544 | Ascencio, Jose L | 20 | 660 | 26233
PR | 141 | 12/20/19 | 554 | Cornejo Orellana, Carlos E | 32 | 832 | 26243
PR | 141 | 12/20/19 | 615 | Villalobos Tejada, Carlos F | 20 | 380 | 26304
PR | 141 | 12/20/19 | 616 | Waites, Thaddeus Z | 6 | 294 | 26305
PR | 141 | 12/27/19 | 701 | Ascencio, Jose L | 8 | 264 | 26309
PR | 141 | 12/27/19 | 711 | Cornejo Orellana, Carlos E | 24 | 624 | 26319
PR | 141 | 12/27/19 | 773 | Villalobos Tejada, Carlos F | 24 | 456 | 26381
PR | 141 | 12/27/19 | 774 | Waites, Thaddeus Z | 14 | 686 | 26382
PR | 141 | 01/03/20 | 14 | Cornejo Orellana, Carlos E | 16 | 416 | 26396
PR | 141 | 01/03/20 | 71 | Taylor, Evan R | 5 | 165 | 26454
PR | 141 | 01/03/20 | 76 | Villalobos Tejada, Carlos F | 16 | 304 | 26459
PR | 141 | 01/03/20 | 77 | Waites, Thaddeus Z | 8 | 392 | 26460
PR | 141 | 01/03/20 | 78 | Wennig, Johnathan M | 16 | 576 | 26461
PR | 141 | 01/10/20 | 344 | Taylor, Evan R | 16 | 528 | 26532
PR | 141 | 01/10/20 | 350 | Waites, Thaddeus Z | 11 | 539 | 26538
PR | 141 | 01/17/20 | 610 | Taylor, Evan R | 8 | 264 | 26609
PR | 141 | 01/17/20 | 616 | Waites, Thaddeus Z | 8 | 392 | 26615
PR | 141 | 02/07/20 | 61 | Hubbard, Robert W | 1 | 81 | 26809
PR | 141 | 02/07/20 | 61 | Hubbard, Robert W | 5 | 270 | 26809
PR | 141 | 02/07/20 | 71 | McCabe, Thomas C | 8 | 312 | 26819
PR | 141 | 02/21/20 | 486 | Hubbard, Robert W | 5 | 270 | 26963
PR | 141 | 02/21/20 | 496 | McCabe, Thomas C | 24 | 936 | 26973
PR | 141 | 02/21/20 | 508 | Roberts, Lake A | 28 | 700 | 26985
PR | 141 | 02/28/20 | 684 | Barnhart, Joseph N | 2 | 108 | 27012
PR | 141 | 02/28/20 | 737 | Roberts, Lake A | 8 | 200 | 27065
PR | 142 | 11/15/19 | 473 | Hubbard, Robert W | 2 | 108 | 25809
PR | 142 | 11/27/19 | 878 | Hubbard, Robert W | 2 | 108 | 25959
PR | 142 | 01/03/20 | 40 | Hubbard, Robert W | 2 | 108 | 26423
PR | 142 | 01/03/20 | 51 | McCabe, Thomas C | 13 | 507 | 26434
PR | 142 | 01/10/20 | 313 | Hubbard, Robert W | 6 | 324 | 26500
PR | 142 | 01/10/20 | 324 | McCabe, Thomas C | 20 | 780 | 26512
PR | 142 | 01/17/20 | 579 | Hubbard, Robert W | 6 | 324 | 26578
PR | 142 | 01/17/20 | 590 | McCabe, Thomas C | 28 | 1092 | 26589
PR | 142 | 01/17/20 | 600 | Roberts, Lake A | 13 | 325 | 26599
PR | 142 | 01/24/20 | 711 | Hubbard, Robert W | 4 | 216 | 26654
PR | 142 | 01/24/20 | 721 | McCabe, Thomas C | 32 | 1248 | 26664
PR | 142 | 01/24/20 | 731 | Roberts, Lake A | 28 | 700 | 26674
PR | 142 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I | 8 | 288 | 26696
PR | 142 | 01/31/20 | 838 | Barnhart, Joseph N | 1 | 54 | 26698
PR | 142 | 01/31/20 | 847 | Cortes Sepulveda, Jose R | 8 | 272 | 26708
PR | 142 | 01/31/20 | 871 | Hubbard, Robert W | 11 | 594 | 26732
PR | 142 | 01/31/20 | 881 | McCabe, Thomas C | 40 | 1560 | 26742
PR | 142 | 02/07/20 | 61 | Hubbard, Robert W | 3 | 162 | 26809
PR | 142 | 02/07/20 | 71 | McCabe, Thomas C | 28 | 1092 | 26819
PR | 142 | 02/14/20 | 271 | Hubbard, Robert W | 3 | 162 | 26887
PR | 142 | 02/14/20 | 281 | McCabe, Thomas C | 14 | 546 | 26897
PR | 142 | 02/14/20 | 292 | Roberts, Lake A | 14 | 350 | 26908
PR | 142 | 02/21/20 | 486 | Hubbard, Robert W | 2 | 108 | 26963
PR | 142 | 02/21/20 | 496 | McCabe, Thomas C | 12 | 468 | 26973
PR | 142 | 02/21/20 | 508 | Roberts, Lake A | 12 | 300 | 26985
PR | 142 | 02/28/20 | 716 | Hubbard, Robert W | 7 | 378 | 27044
PR | 142 | 03/06/20 | 46 | Barnhart, Joseph N | 1 | 54 | 27090
AP | 210 | 11/19/18 | 614 | Rosen Supply Kirkland |  | 2217.69 | 4258855-00
AP | 210 | 11/21/18 | 707 | Rosen Supply Kirkland |  | 79.64 | 4259026-00
GL | 210 | 11/28/18 | 797 | Req 5544 |  | 12.98
AP | 210 | 11/30/18 | 973 | Rosen Supply Kirkland |  | 187.58 | 4259186-00
AP | 210 | 10/17/19 | 568 | Core & Main LP $HD Supply Waterworks |  | 312.11 | L325428
AP | 210 | 10/22/19 | 551 | Core & Main LP $HD Supply Waterworks |  | 253.5 | L351546
GL | 211 | 11/09/18 | 299 | Req 4758 |  | 104.87
GL | 211 | 03/08/19 | 373 | Req 5783 |  | 704
GL | 211 | 03/15/19 | 586 | Req 5827 |  | 52
AP | 211 | 03/22/19 | 794 | Rosen Supply Kirkland |  | 19275.59 | 4264133-00
AP | 211 | 04/03/19 | 75 | Rosen Supply Kirkland |  | 376.68 | 4264572-00
GL | 211 | 04/12/19 | 416 | Req 5891 |  | 540.26
AP | 211 | 04/22/19 | 641 | Rosen Supply Kirkland |  | 178.6 | 4265532-00
AP | 211 | 04/23/19 | 677 | Rosen Supply Kirkland |  | 89.52 | 4265682-00
AP | 211 | 04/24/19 | 715 | Rosen Supply Kirkland |  | 588.76 | 4265780-00
GL | 211 | 04/30/19 | 885 | Req 5172 |  | 108
GL | 211 | 05/13/19 | 311 | Req 5203 |  | -375.66
AP | 211 | 05/13/19 | 329 | Rosen Supply Kirkland |  | 292.99 | 4265780-01
AP | 211 | 05/28/19 | 749 | Rosen Supply Kirkland |  | 790.4 | 4266997-00
GL | 211 | 05/30/19 | 862 | Req 5939 |  | 815.54
GL | 211 | 06/05/19 | 118 | Req 5237 |  | 350.15
AP | 211 | 06/08/19 | 315 | Rosen Supply Kirkland |  | 309 | 4268097-00
AP | 211 | 06/13/19 | 543 | Rosen Supply Kirkland |  | 1032.1 | 4268487-00
AP | 211 | 06/13/19 | 544 | Rosen Supply Kirkland |  | 794.24 | 4268576-00
AP | 211 | 06/24/19 | 745 | Rosen Supply Kirkland |  | 21.24 | 4268760-00
GL | 211 | 07/09/19 | 121 | Req 6085 |  | 154.85
AP | 211 | 07/17/19 | 490 | Rosen Supply Kirkland |  | 809.9 | 4269414-00
AP | 211 | 07/30/19 | 709 | Rosen Supply Kirkland |  | 19.24 | 4269960-00
AP | 211 | 08/10/19 | 443 | Rosen Supply Kirkland |  | 194 | 4269414-01
GL | 211 | 08/20/19 | 736 | Req 6216 |  | 73.4
GL | 211 | 09/06/19 | 108 | Req 6311 |  | -200.62
GL | 211 | 10/07/19 | 110 | Req 6372 |  | 1791.36
GL | 211 | 10/29/19 | 744 | Req 6439 |  | 514
AP | 211 | 11/06/19 | 169 | Rosen Supply Kirkland |  | 198.22 | 4273394-00
AP | 211 | 11/12/19 | 363 | Rosen Supply Kirkland |  | 264.77 | 4273691-00
GL | 211 | 11/13/19 | 407 | Req 6550 |  | 107
GL | 211 | 11/19/19 | 578 | Req 6585 |  | -282.24
GL | 211 | 11/19/19 | 580 | Req 6583 |  | -639.1
GL | 211 | 12/06/19 | 141 | Req 6627 |  | 37.14
GL | 211 | 12/06/19 | 173 | Req 6587 |  | -1245
AP | 211 | 12/10/19 | 222 | Rosen Supply Kirkland |  | 330 | 4275035-00
GL | 211 | 12/20/19 | 641 | Req 6676 |  | 58.06
GL | 211 | 12/30/19 | 832 | Req 6733 |  | -1198.44
GL | 211 | 12/30/19 | 833 | Req 6734 |  | -21.47
GL | 211 | 01/07/20 | 163 | Req 6741 |  | -242.53
GL | 211 | 01/07/20 | 164 | Req 6740 |  | -563.28
GL | 211 | 01/20/20 | 642 | Req 5727 |  | 13.68
GL | 211 | 01/27/20 | 786 | Req 5754 |  | 14.13
GL | 211 | 01/31/20 | 928 | Req 6759 |  | -97.36
AP | 211 | 02/29/20 | 810 | Rosen Supply Kirkland |  | 62.64 | 4279242-00
AP | 211 | 03/04/20 | 30 | Rosen Supply Kirkland |  | 10.81 | 4279539-00
GL | 211 | 03/10/20 | 247 | Req 6886 |  | 33.42
GL | 211 | 03/13/20 | 408 | Req 6908 |  | -40.83
GL | 211 | 05/05/20 | 104 | Req 6960 |  | 37.16
GL | 212 | 01/23/19 | 682 | Req 4984 |  | 2864.17
GL | 212 | 01/25/19 | 812 | Joseph Barnhart |  | 46.69
GL | 212 | 02/01/19 | 156 | Reversal, Stop payment used on this # from online bill |  | -46.69
AP | 212 | 02/06/19 | 130 | Keller Supply Company |  | 373.52 | S012649603.002
GL | 212 | 02/07/19 | 402 | Joseph Barnhart |  | 46.69
GL | 212 | 03/04/19 | 183 | Req 5697 |  | 49.99
GL | 212 | 05/30/19 | 857 | Req 5944 |  | 6016.83
GL | 212 | 01/31/20 | 927 | Req 6760 |  | -226.34
GL | 220 | 01/11/19 | 341 | Req 5653 |  | 14.8
GL | 220 | 01/15/19 | 423 | Req 4896 |  | 17.09
AP | 220 | 01/21/19 | 579 | Rosen Supply Kirkland |  | 16.64 | 1527088-00
AP | 220 | 02/16/19 | 475 | Rosen Supply Kirkland |  | 3651.78 | 4259551-00
GL | 220 | 03/25/19 | 831 | Req 5084 |  | 23.95
AP | 220 | 04/03/19 | 50 | Rosen Supply Kirkland |  | 367.75 | 4264437-00
AP | 220 | 04/09/19 | 250 | Rosen Supply Kirkland |  | 5002.4 | 4265018-00
GL | 220 | 04/30/19 | 886 | Req 5171 |  | 169.41
AP | 220 | 05/02/19 | 141 | Rosen Supply Kirkland |  | 7090.54 | 4265981-00
AP | 220 | 05/02/19 | 142 | Rosen Supply Kirkland |  | 1762.71 | 4265984-00
AP | 220 | 05/13/19 | 317 | Rosen Supply Kirkland |  | 466.86 | 4266234-00
AP | 220 | 05/13/19 | 318 | Rosen Supply Kirkland |  | 22.92 | 4266300-00
AP | 220 | 05/15/19 | 367 | Rosen Supply Kirkland |  | 55.9 | 4266300-01
GL | 220 | 05/30/19 | 853 | Req 5225 |  | 140.14
GL | 220 | 05/30/19 | 861 | Req 5940 |  | 330.34
AP | 220 | 06/03/19 | 34 | Rosen Supply Kirkland |  | 43.58 | 4267918-00
GL | 220 | 06/05/19 | 121 | Req 5240 |  | 42.18
AP | 220 | 06/08/19 | 294 | Rosen Supply Kirkland |  | 597.36 | 4267557-00
AP | 220 | 06/12/19 | 445 | Rosen Supply Kirkland |  | 68.2 | 4268223-00
AP | 220 | 06/13/19 | 542 | Rosen Supply Kirkland |  | 221.5 | 4268362-00
AP | 220 | 06/24/19 | 744 | Rosen Supply Kirkland |  | 396 | 4268710-00
GL | 220 | 07/09/19 | 118 | Req 6082 |  | 323.62
AP | 220 | 07/15/19 | 389 | Rosen Supply Kirkland |  | 683.16 | 4269123-00
AP | 220 | 07/17/19 | 491 | Rosen Supply Kirkland |  | 289.61 | 4269708-00
GL | 220 | 08/01/19 | 129 | Req 6146 |  | 529.4
AP | 220 | 08/05/19 | 110 | Consolidated Supply Co. |  | 4931.3 | S009341455.001
AP | 220 | 08/08/19 | 204 | Rosen Supply Kirkland |  | 168.22 | 4270052-00
AP | 220 | 08/12/19 | 455 | Consolidated Supply Co. |  | 2948.02 | S009359789.001
AP | 220 | 08/12/19 | 472 | Rosen Supply Kirkland |  | 30.6 | 4270052-01
GL | 220 | 08/20/19 | 700 | Req 6266 |  | 347.95
GL | 220 | 08/20/19 | 702 | Req 6259 |  | -65
GL | 220 | 08/20/19 | 740 | Req 6212 |  | 2510.26
GL | 220 | 09/06/19 | 107 | Req 6310 |  | -972.84
GL | 220 | 09/16/19 | 334 | Req 6299 |  | 454.28
GL | 220 | 10/07/19 | 101 | Req 6389 |  | 29.7
GL | 220 | 10/07/19 | 114 | Req 6375 |  | 387.52
GL | 220 | 10/15/19 | 409 | Req 6045 |  | 20
AP | 220 | 10/16/19 | 443 | Rosen Supply Kirkland |  | 334.34 | 4273098-00
GL | 220 | 10/29/19 | 745 | Req 6438 |  | 1027.2
AP | 220 | 11/01/19 | 115 | Rosen Supply Kirkland |  | 14.63 | 4273098-02
AP | 220 | 11/11/19 | 320 | Consolidated Supply Co. |  | 89.76 | S009498691.001
AP | 220 | 11/11/19 | 321 | Consolidated Supply Co. |  | 89.76 | S009498691.002
GL | 220 | 11/13/19 | 403 | Req 6554 |  | 105.14
AP | 220 | 11/16/19 | 544 | Rosen Supply Kirkland |  | 127 | 4273852-00
AP | 220 | 11/16/19 | 545 | Rosen Supply Kirkland |  | 30.07 | 4273922-00
AP | 220 | 11/20/19 | 592 | Rosen Supply Kirkland |  | 679.45 | 4274062-00
AP | 220 | 11/22/19 | 708 | Rosen Supply Kirkland |  | 95.88 | 4274550-00
AP | 220 | 11/30/19 | 967 | Consolidated Supply Co. |  | -89.76 | S009498691.003
AP | 220 | 12/05/19 | 111 | Rosen Supply Kirkland |  | 61.66 | 4274718-00
GL | 220 | 12/06/19 | 126 | Req 6621 |  | 242.66
AP | 220 | 12/09/19 | 211 | Rosen Supply Kirkland |  | 36.5 | 4274899-00
AP | 220 | 12/10/19 | 223 | Rosen Supply Kirkland |  | 11.22 | 4275102-00
AP | 220 | 12/10/19 | 268 | Rosen Supply Kirkland |  | 9.94 | 4275397-00
AP | 220 | 12/13/19 | 526 | Rosen Supply Kirkland |  | 87.27 | 4275707-00
AP | 220 | 12/13/19 | 527 | Rosen Supply Kirkland |  | 23.94 | 4275902-00
GL | 220 | 12/20/19 | 642 | Req 6677 |  | 208.88
GL | 220 | 12/27/19 | 809 | Req 6730 |  | 19.8
GL | 220 | 01/07/20 | 165 | Req 6739 |  | -519.54
GL | 220 | 01/07/20 | 166 | Req 6738 |  | -264.87
AP | 220 | 01/14/20 | 485 | Consolidated Supply Co. |  | 81.8 | S009599238.001
GL | 220 | 01/15/20 | 497 | Req 5744 |  | -1190.31
GL | 220 | 01/20/20 | 641 | Req 5726 |  | 43.61
GL | 220 | 01/27/20 | 787 | Req 5753 |  | 156.82
GL | 220 | 01/31/20 | 926 | Req 6761 |  | -15.53
GL | 220 | 01/31/20 | 929 | Req 6758 |  | -916.43
GL | 220 | 02/11/20 | 205 | Req 6765 |  | 73.3
AP | 220 | 02/12/20 | 218 | Rosen Supply Kirkland |  | 438.86 | 4277842-00
GL | 220 | 02/24/20 | 546 | Req 6841 |  | 13.88
AP | 220 | 02/26/20 | 650 | Rosen Supply Kirkland |  | 27 | 4278727-00
AP | 220 | 02/28/20 | 772 | Consolidated Supply Co. |  | 18.33 | S009615522.001
AP | 220 | 02/28/20 | 773 | Consolidated Supply Co. |  | -16.36 | S009615522.002
AP | 220 | 02/29/20 | 807 | Rosen Supply Kirkland |  | 66.18 | 4279106-00
GL | 220 | 03/13/20 | 410 | Req 6907 |  | -39.37
GL | 220 | 03/13/20 | 411 | Req 6906 |  | -81.13
AP | 230 | 10/05/18 | 121 | California Hydronics Corp |  | 465 | 2108119
AP | 230 | 10/17/18 | 432 | Rosen Supply Kirkland |  | 2354 | 4257412-00
GL | 230 | 01/15/19 | 422 | Req 4895 |  | 150.11
GL | 230 | 01/23/19 | 683 | Req 4985 |  | 208.6
AP | 230 | 02/27/19 | 737 | Quality Concrete Products, Inc. $32 |  | 3856 | 56399
AP | 230 | 02/27/19 | 756 | Rosen Supply Kirkland |  | 13965 | 4260329-00
GL | 230 | 05/30/19 | 852 | Req 5224 |  | 1134.3
GL | 230 | 05/30/19 | 856 | Req 5945 |  | 507.19
GL | 230 | 06/05/19 | 120 | Req 5239 |  | 861
AP | 230 | 06/10/19 | 365 | Best Bath Systems |  | 10334 | 5203
AP | 230 | 06/11/19 | 383 | Keller Supply Company |  | 1753.74 | S013011654.001
AP | 230 | 06/11/19 | 384 | Keller Supply Company |  | 755.21 | S013011654.003
AP | 230 | 06/13/19 | 786 | Keller Supply Company |  | 4074.29 | S013032505.001
AP | 230 | 06/24/19 | 722 | Best Bath Systems |  | 10334 | 5625
AP | 230 | 06/24/19 | 725 | California Hydronics Corp |  | 1186 | SIN020519
AP | 230 | 07/02/19 | 92 | Best Bath Systems |  | 10535.56 | 5970
AP | 230 | 07/02/19 | 94 | California Hydronics Corp |  | 1685 | SIN020636
GL | 230 | 07/09/19 | 117 | Req 6081 |  | 1693.79
AP | 230 | 07/16/19 | 476 | Keller Supply Company |  | 109.02 | S013032505.002
AP | 230 | 08/01/19 | 141 | California Hydronics Corp |  | 375 | SIN022531
AP | 230 | 08/14/19 | 542 | Rosen Supply Kirkland |  | 111.44 | 4270811-00
GL | 230 | 08/20/19 | 737 | Req 6215 |  | 25.84
AP | 230 | 09/24/19 | 602 | Manor Hardware & Construction Supply |  | 130.5 | 997710-00
GL | 230 | 10/07/19 | 112 | Req 6373 |  | 1312.14
GL | 230 | 10/29/19 | 743 | Req 6440 |  | 464.3
GL | 230 | 11/06/19 | 161 | for Keller Inv S013463531.001 |  | 178.37
GL | 230 | 11/13/19 | 406 | Req 6551 |  | 1048.17
GL | 230 | 12/06/19 | 127 | Req 6620 |  | 287.07
GL | 230 | 12/09/19 | 186 | Req 6654 |  | 52.15
GL | 230 | 12/20/19 | 638 | Req 6680 |  | 534.24
AP | 230 | 01/06/20 | 154 | Keller Supply Company |  | 14963.24 | S013157335.001
AP | 230 | 01/07/20 | 178 | Keller Supply Company |  | 14984.76 | S013157310.001
AP | 230 | 01/10/20 | 425 | Capital One Credit Card |  | 48.02 | 121219A
AP | 230 | 01/10/20 | 429 | Capital One Credit Card |  | 57.47 | 123119A
AP | 230 | 01/13/20 | 527 | Rosen Supply Kirkland |  | 679.03 | 4276722-00
AP | 230 | 01/14/20 | 476 | California Hydronics Corp |  | 294 | SIN040226
GL | 230 | 01/20/20 | 643 | Req 5725 |  | 739.32
GL | 230 | 01/27/20 | 784 | Req 5748 |  | 1518.81
AP | 230 | 02/07/20 | 125 | Keller Supply Company |  | 15384.05 | S013918767.001
AP | 230 | 02/07/20 | 126 | Keller Supply Company |  | 14518.65 | S013157287.001
AP | 230 | 02/10/20 | 189 | Keller Supply Company |  | 7431.13 | S013157095.001
GL | 230 | 02/11/20 | 203 | Req 6762 |  | 1295.19
AP | 230 | 02/17/20 | 354 | Rosen Supply Kirkland |  | 2369.31 | 4278043-00
AP | 230 | 02/17/20 | 355 | Rosen Supply Kirkland |  | 170.46 | 4278043-01
AP | 230 | 02/17/20 | 356 | Rosen Supply Kirkland |  | 2228.86 | 4278043-02
AP | 230 | 02/19/20 | 425 | Consolidated Supply Co. |  | 320.36 | S009638548.001
GL | 230 | 02/24/20 | 549 | Req 6838 |  | 995.11
AP | 230 | 02/25/20 | 601 | Rosen Supply Kirkland |  | 404.51 | 4278368-00
AP | 230 | 02/29/20 | 811 | Rosen Supply Kirkland |  | 346.67 | 4279241-00
AP | 230 | 03/09/20 | 202 | Capital One Credit Card |  | 35.91 | 010920A
AP | 230 | 03/09/20 | 206 | Capital One Credit Card |  | 16.85 | 012420A2
GL | 230 | 03/10/20 | 246 | Req 6885 |  | 33.52
GL | 230 | 03/13/20 | 389 | Req 6903 |  | -1532.08
AP | 230 | 03/25/20 | 493 | Capital One Credit Card |  | 28.74 | 021120A
AP | 230 | 03/25/20 | 494 | Capital One Credit Card |  | 32.44 | 021220A
GL | 230 | 05/05/20 | 103 | Req 6961 |  | 7
GL | 240 | 06/05/19 | 164 | Req 6016 |  | 20.49
AP | 240 | 06/12/19 | 445 | Rosen Supply Kirkland |  | 175.82 | 4268223-00
AP | 240 | 08/13/19 | 517 | Consolidated Supply Co. |  | 406.4 | S009370975.001
AP | 240 | 08/19/19 | 663 | Consolidated Supply Co. |  | 404.19 | S009375515.001
GL | 240 | 08/20/19 | 738 | Req 6214 |  | 114.21
AP | 240 | 09/18/19 | 449 | Keller Supply Company |  | 201.4 | S013399487.001
GL | 240 | 10/07/19 | 113 | Req 6374 |  | 76.8
AP | 240 | 10/08/19 | 162 | Consolidated Supply Co. |  | 273.6 | S009440909.002
AP | 240 | 10/16/19 | 443 | Rosen Supply Kirkland |  | 142.21 | 4273098-00
AP | 240 | 10/16/19 | 444 | Rosen Supply Kirkland |  | 61.45 | 4273098-01
GL | 240 | 11/11/19 | 311 | Req 6493 |  | -46.4
GL | 240 | 11/13/19 | 405 | Req 6553 |  | 11.07
AP | 240 | 12/31/19 | 854 | Kele, Inc $ MI Controls |  | 276.17 | IMIS0807002723
AP | 240 | 01/06/20 | 109 | Rosen Supply Kirkland |  | 150.21 | 4276668-00
AP | 240 | 01/08/20 | 243 | Rosen Supply Kirkland |  | 15.64 | 4276872-00
GL | 240 | 01/10/20 | 358 | Req 6742 |  | -105.83
AP | 240 | 01/17/20 | 635 | Ferguson Enterprises, Inc. #3007 |  | 89.45 | 4276668-01
GL | 240 | 01/31/20 | 951 | Req 5750 |  | 581.52
AP | 240 | 02/01/20 | 112 | Ferguson Enterprises, Inc. #3007 |  | -89.45 | 4276668-01A
AP | 240 | 02/01/20 | 113 | Rosen Supply Kirkland |  | 89.45 | 4276668-011
AP | 240 | 02/10/20 | 144 | Rosen Supply Kirkland |  | 35.72 | 4277666-00
GL | 240 | 02/11/20 | 206 | Req 6766 |  | 14.6
AP | 240 | 02/11/20 | 211 | Rosen Supply Kirkland |  | 178.74 | 4277774-00
AP | 240 | 02/17/20 | 358 | Rosen Supply Kirkland |  | 99.77 | 4278189-00
AP | 240 | 02/18/20 | 401 | Rosen Supply Kirkland |  | 48.51 | 4278285-00
GL | 240 | 02/24/20 | 548 | Req 6839 |  | 202.76
AP | 240 | 02/26/20 | 649 | Rosen Supply Kirkland |  | 100.3 | 4278715-00
AP | 240 | 02/26/20 | 665 | Rosen Supply Kirkland |  | 201.84 | 4278979-00
AP | 240 | 02/29/20 | 808 | Rosen Supply Kirkland |  | 67.4 | 4278715-01
GL | 240 | 03/10/20 | 245 | Req 6884 |  | 132.45
GL | 240 | 03/13/20 | 388 | Req 6904 |  | -411.13
GL | 240 | 03/13/20 | 409 | Req 6909 |  | -60.86
AP | 240 | 03/18/20 | 550 | Rosen Supply Kirkland |  | 18.86 | 4278979-01
GL | 241 | 11/09/18 | 300 | Req 4759 |  | 103
GL | 241 | 11/26/18 | 749 | Req 5526 |  | 65
GL | 241 | 01/11/19 | 340 | Req 5654 |  | 141
GL | 241 | 05/30/19 | 860 | Req 5941 |  | 35.82
GL | 241 | 06/05/19 | 119 | Req 5238 |  | 44.6
GL | 241 | 06/26/19 | 821 | Req 6031 |  | 23.6
GL | 241 | 08/01/19 | 124 | Req 6232 |  | -305.4
AP | 241 | 08/05/19 | 109 | Consolidated Supply Co. |  | 1707.12 | S009341419.001
AP | 241 | 08/05/19 | 111 | Consolidated Supply Co. |  | 26.32 | S009343340.002
AP | 241 | 08/05/19 | 112 | Consolidated Supply Co. |  | 88.56 | S009343340.003
AP | 241 | 08/05/19 | 113 | Consolidated Supply Co. |  | 3220.11 | S009343340.001
AP | 241 | 08/12/19 | 480 | Consolidated Supply Co. |  | 345.92 | S009364722.001
AP | 241 | 08/13/19 | 517 | Consolidated Supply Co. |  | 1179.05 | S009370975.001
GL | 241 | 08/20/19 | 698 | Req 6263 |  | 1016.4
GL | 241 | 08/20/19 | 703 | Req 6258 |  | -66
GL | 241 | 08/20/19 | 739 | Req 6213 |  | 1932.52
AP | 241 | 08/26/19 | 934 | Consolidated Supply Co. |  | 211.44 | S009381745.001
AP | 241 | 08/26/19 | 935 | Consolidated Supply Co. |  | 112.2 | S009385497.001
GL | 241 | 09/06/19 | 103 | Req 6325 |  | 994.52
GL | 241 | 09/16/19 | 333 | Req 6298 |  | 394.22
GL | 241 | 09/16/19 | 342 | Req 6359 |  | 304.92
AP | 241 | 09/18/19 | 467 | Consolidated Supply Co. |  | 509 | S009413109.001
GL | 241 | 10/07/19 | 111 | Req 6371 |  | 2569.94
AP | 241 | 10/07/19 | 137 | Rosen Supply Kirkland |  | 348.67 | 4272836-00
AP | 241 | 10/08/19 | 161 | Consolidated Supply Co. |  | 508.2 | S009440780.001
AP | 241 | 10/29/19 | 730 | Consolidated Supply Co. |  | 600.06 | S009472987.001
GL | 241 | 10/29/19 | 742 | Req 6441 |  | 284.95
GL | 241 | 11/13/19 | 404 | Req 6552 |  | 64.6
AP | 241 | 12/05/19 | 19 | Consolidated Supply Co. |  | 202.4 | S009515783.001
GL | 241 | 12/06/19 | 124 | Req 6655 |  | -175.56
GL | 241 | 12/06/19 | 125 | Req 6622 |  | 2511.9
AP | 241 | 12/11/19 | 369 | Consolidated Supply Co. |  | 432.4 | S009534828.001
GL | 241 | 12/20/19 | 639 | Req 6674 |  | 1280.07
GL | 241 | 12/27/19 | 810 | Req 6729 |  | -615.15
GL | 241 | 12/27/19 | 811 | Req 6728 |  | 802.6
AP | 241 | 12/27/19 | 817 | Consolidated Supply Co. |  | 252.09 | S009548038.001
AP | 241 | 01/08/20 | 242 | Rosen Supply Kirkland |  | 577.65 | 4276794-00
GL | 241 | 01/20/20 | 645 | Req 6750 |  | 503.36
GL | 241 | 01/27/20 | 785 | Req 5749 |  | 201.05
GL | 241 | 01/31/20 | 919 | Req 6756 |  | -3010.86
GL | 241 | 01/31/20 | 924 | Req 5778 |  | -55.2
GL | 241 | 01/31/20 | 930 | Req 6757 |  | -1410.75
AP | 241 | 02/05/20 | 18 | Consolidated Supply Co. |  | 70.83 | S009611126.001
GL | 241 | 02/11/20 | 207 | Req 6767 |  | 40.6
AP | 241 | 02/11/20 | 212 | Rosen Supply Kirkland |  | -19.26 | 4277763-00
AP | 241 | 02/17/20 | 357 | Rosen Supply Kirkland |  | 372.33 | 4278139-00
GL | 241 | 02/24/20 | 550 | Req 6837 |  | 160.09
GL | 241 | 03/20/20 | 682 | Req 6905 |  | -436.04
GL | 242 | 07/09/19 | 119 | Req 6083 |  | 15.66
GL | 242 | 08/01/19 | 130 | Req 6147 |  | 5.01
AP | 242 | 09/17/19 | 429 | Ferguson Enterprises, Inc. #3007 |  | 3840.51 | 7544741
GL | 242 | 10/07/19 | 100 | Req 6390 |  | -289.79
AP | 242 | 10/10/19 | 379 | Ferguson Enterprises, Inc. #3007 |  | 683.15 | 7554950
AP | 242 | 10/10/19 | 380 | Ferguson Enterprises, Inc. #3007 |  | 97.59 | 7554950-1
AP | 242 | 10/11/19 | 367 | Ferguson Enterprises, Inc. #3007 |  | 262.48 | 7544741-1
AP | 242 | 11/11/19 | 333 | Ferguson Enterprises, Inc. #3007 |  | 39.69 | 7674256
AP | 242 | 12/11/19 | 384 | Ferguson Enterprises, Inc. #3007 |  | 347.04 | 7752858
GL | 242 | 12/20/19 | 640 | Req 6675 |  | 25.56
AP | 242 | 01/06/20 | 112 | Rosen Supply Kirkland |  | 145.68 | 4276748-00
AP | 242 | 01/06/20 | 146 | Ferguson Enterprises, Inc. #3007 |  | 2120.06 | 7800311
GL | 242 | 01/10/20 | 359 | Req 6748 |  | 1678.05
AP | 242 | 01/13/20 | 536 | Ferguson Enterprises, Inc. #3007 |  | 169.65 | 7852927-3
AP | 242 | 01/14/20 | 492 | Ferguson Enterprises, Inc. #3007 |  | 1606.98 | 7852927-1
AP | 242 | 01/14/20 | 493 | Ferguson Enterprises, Inc. #3007 |  | 197.83 | 7852927-2
AP | 242 | 01/14/20 | 494 | Ferguson Enterprises, Inc. #3007 |  | 4016.82 | 7852927
AP | 242 | 01/17/20 | 631 | Ferguson Enterprises, Inc. #3007 |  | 1624.84 | 7869862
AP | 242 | 01/17/20 | 632 | Ferguson Enterprises, Inc. #3007 |  | 488.83 | 7869862-1
GL | 242 | 01/20/20 | 646 | Req 6749 |  | 143.36
GL | 242 | 01/27/20 | 788 | Req 5752 |  | 63.95
GL | 242 | 01/27/20 | 789 | Req 5751 |  | 669.04
AP | 242 | 01/29/20 | 822 | Ferguson Enterprises, Inc. #3007 |  | 300.4 | 7900909
AP | 242 | 01/29/20 | 830 | Keller Supply Company |  | 153.96 | S013837515.001
AP | 242 | 02/01/20 | 120 | Ferguson Enterprises, Inc. #3007 |  | -1606.98 | 7852927-1A
AP | 242 | 02/01/20 | 121 | Ferguson Enterprises, Inc. #3007 |  | 1606.08 | 7852927-1B
AP | 242 | 02/07/20 | 118 | Ferguson Enterprises, Inc. #3007 |  | 3750.1 | 7927771
AP | 242 | 02/10/20 | 153 | Ferguson Enterprises, Inc. #3007 |  | 453.09 | 7297771-1
AP | 242 | 02/10/20 | 154 | Ferguson Enterprises, Inc. #3007 |  | 1178.72 | 7945062
AP | 242 | 02/10/20 | 155 | Ferguson Enterprises, Inc. #3007 |  | 115.66 | 7956866
AP | 242 | 02/10/20 | 156 | Ferguson Enterprises, Inc. #3007 |  | -822.19 | CM857275
GL | 242 | 02/11/20 | 204 | Req 6764 |  | 612.2
GL | 242 | 02/24/20 | 547 | Req 6840 |  | 12.05
GL | 242 | 02/24/20 | 551 | Req 6836 |  | 505.17
AP | 242 | 02/26/20 | 641 | Ferguson Enterprises, Inc. #3007 |  | 529.79 | 7975831
AP | 242 | 02/26/20 | 642 | Ferguson Enterprises, Inc. #3007 |  | 18.51 | 797495
AP | 242 | 02/26/20 | 643 | Ferguson Enterprises, Inc. #3007 |  | 73.26 | 7990832
AP | 242 | 02/29/20 | 809 | Rosen Supply Kirkland |  | 37.8 | 4279152-00
GL | 242 | 03/04/20 | 17 | Req 6763 |  | 781.64
GL | 242 | 03/13/20 | 390 | Req 6902 |  | -40.4
GL | 242 | 03/13/20 | 391 | Req 6901 |  | -1099.1
GL | 242 | 03/13/20 | 392 | Req 6898 |  | -2085.95
GL | 242 | 03/13/20 | 393 | Req 6900 |  | -331.81
AP | 242 | 03/25/20 | 491 | Capital One Credit Card |  | 11.45 | 021820RH2
AP | 600 | 10/15/19 | 429 | Scan2Core, Inc. |  | 740 | 73492
AP | 600 | 03/24/20 | 721 | Mechanical Resource Services, Inc. |  | 4475 | 16811-5635
AP | 600 | 04/17/20 | 295 | Patchworks, Inc. |  | 445 | 9286
AP | 600 | 04/17/20 | 296 | Patchworks, Inc. |  | 381.25 | 9291
AP | 601 | 05/08/18 | 165 | Sider + Byers Associates, Inc. |  | 1320 | 12456
AP | 601 | 08/23/18 | 736 | Sider + Byers Associates, Inc. |  | 8860 | 12660
AP | 601 | 09/11/18 | 228 | DRSi |  | 83.56 | 471644
AP | 601 | 09/11/18 | 232 | Sider + Byers Associates, Inc. |  | 4930 | 12671
AP | 601 | 10/01/18 | 17 | Sider + Byers Associates, Inc. |  | 1235 | 12755
AP | 601 | 10/16/18 | 639 | DRSi |  | 87.18 | 473651
AP | 601 | 10/16/18 | 640 | DRSi |  | 9.85 | 473896
AP | 601 | 11/05/18 | 153 | DRSi |  | 107.54 | 474733
AP | 601 | 11/05/18 | 165 | Sider + Byers Associates, Inc. |  | 1100 | 12796
AP | 602 | 03/09/20 | 159 | Sunbelt Rentals, Inc. |  | 241.47 | 98739996-0002
AP | 603 | 03/31/18 | 889 | Citibank Credit Card |  | 298 | 022818D
AP | 603 | 03/31/18 | 890 | Citibank Credit Card |  | 255 | 022818E
AP | 603 | 03/31/18 | 891 | Citibank Credit Card |  | 3133 | 022818F
AP | 603 | 03/31/18 | 902 | Citibank Credit Card |  | -298 | 022818DA
AP | 603 | 03/31/18 | 903 | Capital One Credit Card |  | 298 | 022818D
AP | 603 | 03/31/18 | 904 | Citibank Credit Card |  | -255 | 022818EA
AP | 603 | 03/31/18 | 905 | Capital One Credit Card |  | 255 | 022818E
AP | 603 | 03/31/18 | 906 | Citibank Credit Card |  | -3133 | 022818FA
AP | 603 | 03/31/18 | 907 | Capital One Credit Card |  | 3133 | 022818F
AP | 603 | 09/30/18 | 803 | Capital One Credit Card |  | 201 | 090518J
AP | 603 | 10/30/18 | 822 | Capital One Credit Card |  | 201 | 102218J
AP | 603 | 12/31/18 | 814 | Capital One Credit Card |  | 301.5 | 120418J1
AP | 603 | 09/10/19 | 189 | Capital One Credit Card |  | 150 | 082619J1
AP | 607 | 09/30/18 | 804 | Capital One Credit Card |  | 12.26 | 090518J2
AP | 607 | 10/30/18 | 820 | Capital One Credit Card |  | 14.71 | 100818J
AP | 607 | 10/30/18 | 823 | Capital One Credit Card |  | 14.71 | 102218J2
AP | 607 | 10/30/18 | 824 | Capital One Credit Card |  | 7.36 | 102418J
AP | 607 | 12/31/18 | 815 | Capital One Credit Card |  | 17.16 | 120418J2
GL | 607 | 03/20/19 | 674 | Taylor Parking Infraction. |  | 47.6
GL | 607 | 05/09/19 | 333 | Dustin Hubbard |  | 12.26
AP | 607 | 08/01/19 | 401 | Capital One Credit Card |  | 256.49 | 070119R5
AP | 607 | 08/01/19 | 423 | Capital One Credit Card |  | 427.5 | 080119R2
AP | 607 | 09/10/19 | 190 | Capital One Credit Card |  | 6.13 | 082619J2
AP | 607 | 09/10/19 | 219 | Capital One Credit Card |  | 427.5 | 090119R
AP | 607 | 10/11/19 | 341 | Capital One Credit Card |  | 427.5 | 100119R2
AP | 607 | 11/21/19 | 790 | Capital One Credit Card |  | 512.99 | 110119R2
AP | 607 | 11/21/19 | 801 | Capital One Credit Card |  | 12.26 | 102819JB
AP | 607 | 01/08/20 | 228 | Capital One Credit Card |  | 512.99 | 120119R2
AP | 607 | 01/08/20 | 234 | Capital One Credit Card |  | 8.58 | 120519JB
AP | 607 | 03/09/20 | 160 | Capital One Credit Card |  | -342 | 020420C
AP | 607 | 03/09/20 | 224 | Capital One Credit Card |  | 512.99 | 020120R
AP | 607 | 03/09/20 | 233 | Capital One Credit Card |  | 12.26 | 020520A
AP | 607 | 03/25/20 | 490 | Capital One Credit Card |  | 8.58 | 021820BH
PR | 995 | 04/06/18 | 84 | Donelson, Richard T |  | 27.72
PR | 995 | 04/20/18 | 517 | Donelson, Richard T |  | 27.72
PR | 995 | 06/15/18 | 527 | Donelson, Richard T |  | 55.44
PR | 995 | 07/06/18 | 76 | Donelson, Richard T |  | 83.16
PR | 995 | 07/13/18 | 367 | Donelson, Richard T |  | 27.72
PR | 995 | 08/17/18 | 550 | Donelson, Richard T |  | 83.16
PR | 995 | 08/24/18 | 811 | Donelson, Richard T |  | 27.72
PR | 995 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/31/18 | 1000 | Barnhart, Joseph N |  | 81.6
PR | 995 | 08/31/18 | 1069 | Donelson, Richard T |  | 55.44
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/07/18 | 41 | Barnhart, Joseph N |  | 20.4
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/14/18 | 272 | Barnhart, Joseph N |  | 40.8
PR | 995 | 09/14/18 | 310 | Martinez Reyes, Juan C |  | 23.06
PR | 995 | 09/14/18 | 340 | Donelson, Richard T |  | 27.72
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 09/21/18 | 486 | Barnhart, Joseph N |  | 81.6
PR | 995 | 09/21/18 | 552 | Donelson, Richard T |  | 83.16
PR | 995 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/28/18 | 670 | Barnhart, Joseph N |  | 20.4
PR | 995 | 09/28/18 | 708 | Martinez Reyes, Juan C |  | 11.53
PR | 995 | 09/28/18 | 739 | Donelson, Richard T |  | 27.72
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/05/18 | 34 | Barnhart, Joseph N |  | 40.8
PR | 995 | 10/05/18 | 72 | Martinez Reyes, Juan C |  | 11.53
PR | 995 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/19/18 | 438 | Barnhart, Joseph N |  | 61.2
PR | 995 | 10/19/18 | 438 | Barnhart, Joseph N |  | 122.41
PR | 995 | 10/19/18 | 460 | Gerard, Mitchell J |  | 620.9
PR | 995 | 10/19/18 | 476 | Martinez Reyes, Juan C |  | 23.06
PR | 995 | 10/19/18 | 507 | Donelson, Richard T |  | 83.16
PR | 995 | 10/26/18 | 706 | Barnhart, Joseph N |  | 61.2
PR | 995 | 10/26/18 | 706 | Barnhart, Joseph N |  | 244.81
PR | 995 | 10/26/18 | 742 | Martinez Reyes, Juan C |  | 34.59
PR | 995 | 10/26/18 | 742 | Martinez Reyes, Juan C |  | 46.12
PR | 995 | 10/26/18 | 770 | Wennig, Johnathan M |  | 198.69
PR | 995 | 10/26/18 | 774 | Donelson, Richard T |  | 27.72
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 88.7
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 77.61
PR | 995 | 11/02/18 | 9 | Barnhart, Joseph N |  | 601.83
PR | 995 | 11/02/18 | 73 | Wennig, Johnathan M |  | 447.05
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/09/18 | 187 | Barnhart, Joseph N |  | 61.2
PR | 995 | 11/09/18 | 257 | Donelson, Richard T |  | 27.72
PR | 995 | 11/16/18 | 435 | Barnhart, Joseph N |  | 102.01
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 27.72
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/30/18 | 833 | Barnhart, Joseph N |  | 42.58
PR | 995 | 12/07/18 | 47 | Barnhart, Joseph N |  | 85.15
PR | 995 | 12/07/18 | 113 | Donelson, Richard T |  | 83.16
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 270 | Barnhart, Joseph N |  | 106.44
PR | 995 | 12/14/18 | 270 | Barnhart, Joseph N |  | 95.8
PR | 995 | 12/14/18 | 270 | Barnhart, Joseph N |  | 21.29
PR | 995 | 12/14/18 | 270 | Barnhart, Joseph N |  | 63.86
PR | 995 | 12/14/18 | 335 | Wennig, Johnathan M |  | 106.44
PR | 995 | 12/14/18 | 337 | Donelson, Richard T |  | 27.72
PR | 995 | 12/21/18 | 511 | Barnhart, Joseph N |  | 127.73
PR | 995 | 12/21/18 | 547 | Martinez Reyes, Juan C |  | 24.84
PR | 995 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/28/18 | 702 | Barnhart, Joseph N |  | 85.15
PR | 995 | 01/04/19 | 7 | Barnhart, Joseph N |  | 42.58
PR | 995 | 01/11/19 | 215 | Barnhart, Joseph N |  | 149.02
PR | 995 | 01/11/19 | 251 | Martinez Reyes, Juan C |  | 37.25
PR | 995 | 01/18/19 | 469 | Barnhart, Joseph N |  | 276.74
PR | 995 | 01/18/19 | 506 | Martinez Reyes, Juan C |  | 173.85
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/25/19 | 718 | Barnhart, Joseph N |  | 191.59
PR | 995 | 01/25/19 | 755 | Martinez Reyes, Juan C |  | 74.51
PR | 995 | 02/01/19 | 7 | Barnhart, Joseph N |  | 31.93
PR | 995 | 02/01/19 | 15 | Crespin Portillo, Juan D |  | 15.08
PR | 995 | 02/01/19 | 43 | Martinez Reyes, Juan C |  | 86.93
PR | 995 | 02/01/19 | 67 | Waites, Thaddeus Z |  | 28.61
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/22/19 | 582 | Barnhart, Joseph N |  | 127.73
PR | 995 | 02/22/19 | 636 | Serrano, Jeremiah G |  | 52.78
PR | 995 | 03/01/19 | 7 | Barnhart, Joseph N |  | 255.46
PR | 995 | 03/01/19 | 63 | Serrano, Jeremiah G |  | 60.32
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/08/19 | 249 | Barnhart, Joseph N |  | 63.86
PR | 995 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 60.32
PR | 995 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 60.32
PR | 995 | 03/08/19 | 306 | Taylor, Evan R |  | 276.74
PR | 995 | 03/08/19 | 306 | Taylor, Evan R |  | 92.25
PR | 995 | 03/08/19 | 310 | Villalobos Tejada, Carlos F |  | 56.77
PR | 995 | 03/08/19 | 311 | Waites, Thaddeus Z |  | 152.56
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/15/19 | 496 | Barnhart, Joseph N |  | 212.88
PR | 995 | 03/15/19 | 550 | Serrano, Jeremiah G |  | 196.03
PR | 995 | 03/15/19 | 554 | Taylor, Evan R |  | 17.3
PR | 995 | 03/15/19 | 554 | Taylor, Evan R |  | 34.59
PR | 995 | 03/15/19 | 554 | Taylor, Evan R |  | 368.99
PR | 995 | 03/15/19 | 554 | Taylor, Evan R |  | 92.25
PR | 995 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 10.64
PR | 995 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 21.29
PR | 995 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 35.48
PR | 995 | 03/15/19 | 562 | Donelson, Richard T |  | 27.72
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/22/19 | 710 | Barnhart, Joseph N |  | 149.02
PR | 995 | 03/22/19 | 763 | Serrano, Jeremiah G |  | 301.58
PR | 995 | 03/22/19 | 768 | Taylor, Evan R |  | 17.3
PR | 995 | 03/22/19 | 768 | Taylor, Evan R |  | 34.59
PR | 995 | 03/22/19 | 768 | Taylor, Evan R |  | 368.99
PR | 995 | 03/22/19 | 768 | Taylor, Evan R |  | 92.25
PR | 995 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 10.64
PR | 995 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 21.29
PR | 995 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 227.07
PR | 995 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 56.77
PR | 995 | 03/22/19 | 773 | Waites, Thaddeus Z |  | 114.42
PR | 995 | 03/29/19 | 975 | Serrano, Jeremiah G |  | 218.65
PR | 995 | 03/29/19 | 980 | Taylor, Evan R |  | 461.24
PR | 995 | 03/29/19 | 984 | Villalobos Tejada, Carlos F |  | 170.3
PR | 995 | 03/29/19 | 985 | Waites, Thaddeus Z |  | 266.99
PR | 995 | 03/29/19 | 989 | Donelson, Richard T |  | 27.72
PR | 995 | 04/05/19 | 80 | Ascencio, Jose L |  | 298.03
PR | 995 | 04/05/19 | 83 | Barnhart, Joseph N |  | 85.15
PR | 995 | 04/05/19 | 138 | Serrano, Jeremiah G |  | 256.34
PR | 995 | 04/05/19 | 143 | Taylor, Evan R |  | 461.24
PR | 995 | 04/05/19 | 147 | Villalobos Tejada, Carlos F |  | 283.84
PR | 995 | 04/05/19 | 148 | Waites, Thaddeus Z |  | 381.41
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 44.35
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 44.35
PR | 995 | 04/12/19 | 382 | Serrano, Jeremiah G |  | 60.32
PR | 995 | 04/12/19 | 387 | Taylor, Evan R |  | 334.4
PR | 995 | 04/12/19 | 392 | Villalobos Tejada, Carlos F |  | 283.84
PR | 995 | 04/12/19 | 393 | Waites, Thaddeus Z |  | 239.49
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/19/19 | 521 | Ascencio, Jose L |  | 149.02
PR | 995 | 04/19/19 | 524 | Barnhart, Joseph N |  | 22.18
PR | 995 | 04/19/19 | 529 | Cornejo Orellana, Carlos E |  | 111.76
PR | 995 | 04/19/19 | 532 | Crespin Portillo, Juan D |  | 90.47
PR | 995 | 04/19/19 | 542 | Frausto Mendoza, Pedro |  | 74.51
PR | 995 | 04/19/19 | 544 | Garcia Perez, Ervey O |  | 170.3
PR | 995 | 04/19/19 | 585 | Taylor, Evan R |  | 184.5
PR | 995 | 04/19/19 | 588 | Velasquez Cruz, Denis M |  | 154.34
PR | 995 | 04/19/19 | 589 | Velasquez Cruz, Osman N |  | 117.08
PR | 995 | 04/19/19 | 590 | Villalobos Tejada, Carlos F |  | 95.8
PR | 995 | 04/19/19 | 590 | Villalobos Tejada, Carlos F |  | 283.84
PR | 995 | 04/19/19 | 591 | Waites, Thaddeus Z |  | 239.49
PR | 995 | 04/19/19 | 591 | Waites, Thaddeus Z |  | 379.19
PR | 995 | 04/19/19 | 592 | Wennig, Johnathan M |  | 159.66
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/26/19 | 741 | Ascencio, Jose L |  | 99.79
PR | 995 | 04/26/19 | 752 | Crespin Portillo, Juan D |  | 63.2
PR | 995 | 04/26/19 | 761 | Frausto Mendoza, Pedro |  | 51
PR | 995 | 04/26/19 | 763 | Garcia Perez, Ervey O |  | 53.22
PR | 995 | 04/26/19 | 763 | Garcia Perez, Ervey O |  | 170.3
PR | 995 | 04/26/19 | 805 | Velasquez Cruz, Denis M |  | 106.44
PR | 995 | 04/26/19 | 806 | Velasquez Cruz, Osman N |  | 55.44
PR | 995 | 04/26/19 | 807 | Villalobos Tejada, Carlos F |  | 56.55
PR | 995 | 04/26/19 | 807 | Villalobos Tejada, Carlos F |  | 180.95
PR | 995 | 04/26/19 | 808 | Waites, Thaddeus Z |  | 29.94
PR | 995 | 04/26/19 | 808 | Waites, Thaddeus Z |  | 399.15
PR | 995 | 05/03/19 | 11 | Barnhart, Joseph N |  | 22.18
PR | 995 | 05/03/19 | 31 | Garcia Perez, Ervey O |  | 283.84
PR | 995 | 05/03/19 | 44 | Jimenez Montiel, Carlos A |  | 56.77
PR | 995 | 05/03/19 | 72 | Taylor, Evan R |  | 308.68
PR | 995 | 05/03/19 | 75 | Velasquez Cruz, Denis M |  | 138.37
PR | 995 | 05/03/19 | 76 | Velasquez Cruz, Osman N |  | 108.1
PR | 995 | 05/03/19 | 77 | Villalobos Tejada, Carlos F |  | 301.58
PR | 995 | 05/03/19 | 78 | Waites, Thaddeus Z |  | 194.59
PR | 995 | 05/03/19 | 78 | Waites, Thaddeus Z |  | 399.15
PR | 995 | 05/03/19 | 79 | Wennig, Johnathan M |  | 95.13
PR | 995 | 05/10/19 | 184 | Garcia Perez, Ervey O |  | 283.84
PR | 995 | 05/10/19 | 197 | Jimenez Montiel, Carlos A |  | 24.84
PR | 995 | 05/10/19 | 225 | Taylor, Evan R |  | 514.46
PR | 995 | 05/10/19 | 230 | Villalobos Tejada, Carlos F |  | 241.26
PR | 995 | 05/10/19 | 231 | Waites, Thaddeus Z |  | 159.66
PR | 995 | 05/17/19 | 457 | Taylor, Evan R |  | 514.46
PR | 995 | 05/17/19 | 462 | Villalobos Tejada, Carlos F |  | 301.58
PR | 995 | 05/17/19 | 463 | Waites, Thaddeus Z |  | 199.58
PR | 995 | 05/17/19 | 467 | Donelson, Richard T |  | 27.72
PR | 995 | 05/24/19 | 605 | Ascencio, Jose L |  | 76.23
PR | 995 | 05/24/19 | 605 | Ascencio, Jose L |  | 127.05
PR | 995 | 05/24/19 | 613 | Cornejo Orellana, Carlos E |  | 58.44
PR | 995 | 05/24/19 | 613 | Cornejo Orellana, Carlos E |  | 58.44
PR | 995 | 05/24/19 | 641 | Jimenez Montiel, Carlos A |  | 20.33
PR | 995 | 05/24/19 | 641 | Jimenez Montiel, Carlos A |  | 94.86
PR | 995 | 05/24/19 | 669 | Taylor, Evan R |  | 73.69
PR | 995 | 05/24/19 | 669 | Taylor, Evan R |  | 491.26
PR | 995 | 05/24/19 | 674 | Villalobos Tejada, Carlos F |  | 43.2
PR | 995 | 05/24/19 | 674 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 05/24/19 | 675 | Waites, Thaddeus Z |  | 57.17
PR | 995 | 05/24/19 | 675 | Waites, Thaddeus Z |  | 419.27
PR | 995 | 05/24/19 | 680 | Donelson, Richard T |  | 55.44
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 05/31/19 | 878 | Ascencio, Jose L |  | 304.92
PR | 995 | 05/31/19 | 915 | Jimenez Montiel, Carlos A |  | 155.85
PR | 995 | 05/31/19 | 943 | Taylor, Evan R |  | 442.13
PR | 995 | 05/31/19 | 948 | Villalobos Tejada, Carlos F |  | 259.18
PR | 995 | 06/07/19 | 180 | Ascencio, Jose L |  | 76.23
PR | 995 | 06/07/19 | 180 | Ascencio, Jose L |  | 508.2
PR | 995 | 06/07/19 | 183 | Barnhart, Joseph N |  | 21.18
PR | 995 | 06/07/19 | 183 | Barnhart, Joseph N |  | 42.35
PR | 995 | 06/07/19 | 245 | Taylor, Evan R |  | 73.69
PR | 995 | 06/07/19 | 245 | Taylor, Evan R |  | 491.26
PR | 995 | 06/07/19 | 250 | Villalobos Tejada, Carlos F |  | 43.2
PR | 995 | 06/07/19 | 250 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 06/07/19 | 251 | Waites, Thaddeus Z |  | 381.15
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 34.94
PR | 995 | 06/14/19 | 451 | Ascencio, Jose L |  | 114.35
PR | 995 | 06/14/19 | 451 | Ascencio, Jose L |  | 508.2
PR | 995 | 06/14/19 | 483 | Hubbard, Robert W |  | 63.53
PR | 995 | 06/14/19 | 513 | Taylor, Evan R |  | 239.49
PR | 995 | 06/14/19 | 513 | Taylor, Evan R |  | 491.26
PR | 995 | 06/14/19 | 516 | Velasquez Cruz, Denis M |  | 121.97
PR | 995 | 06/14/19 | 517 | Velasquez Cruz, Osman N |  | 95.29
PR | 995 | 06/14/19 | 518 | Villalobos Tejada, Carlos F |  | 97.19
PR | 995 | 06/14/19 | 518 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 142.93
PR | 995 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 152.46
PR | 995 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 381.15
PR | 995 | 06/14/19 | 520 | Wennig, Johnathan M |  | 97.83
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 55.44
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 06/21/19 | 619 | Ascencio, Jose L |  | 114.35
PR | 995 | 06/21/19 | 619 | Ascencio, Jose L |  | 508.2
PR | 995 | 06/21/19 | 635 | Cruz Reyes, Jose |  | 110.53
PR | 995 | 06/21/19 | 635 | Cruz Reyes, Jose |  | 491.26
PR | 995 | 06/21/19 | 684 | Taylor, Evan R |  | 110.53
PR | 995 | 06/21/19 | 684 | Taylor, Evan R |  | 491.26
PR | 995 | 06/21/19 | 689 | Villalobos Tejada, Carlos F |  | 64.8
PR | 995 | 06/21/19 | 689 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 100.05
PR | 995 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 438.32
PR | 995 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 19.06
PR | 995 | 06/21/19 | 691 | Wennig, Johnathan M |  | 55.9
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 27.72
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 27.72
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/28/19 | 837 | Ascencio, Jose L |  | 38.12
PR | 995 | 06/28/19 | 837 | Ascencio, Jose L |  | 508.2
PR | 995 | 06/28/19 | 853 | Cruz Reyes, Jose |  | 36.84
PR | 995 | 06/28/19 | 853 | Cruz Reyes, Jose |  | 491.26
PR | 995 | 06/28/19 | 901 | Taylor, Evan R |  | 36.84
PR | 995 | 06/28/19 | 901 | Taylor, Evan R |  | 491.26
PR | 995 | 06/28/19 | 906 | Villalobos Tejada, Carlos F |  | 21.6
PR | 995 | 06/28/19 | 906 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 06/28/19 | 907 | Waites, Thaddeus Z |  | 323.98
PR | 995 | 06/28/19 | 908 | Wennig, Johnathan M |  | 111.8
PR | 995 | 06/28/19 | 910 | Donelson, Richard T |  | 83.16
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/05/19 | 9 | Ascencio, Jose L |  | 495.5
PR | 995 | 07/05/19 | 12 | Barnhart, Joseph N |  | 42.35
PR | 995 | 07/05/19 | 25 | Cruz Reyes, Jose |  | 478.98
PR | 995 | 07/05/19 | 29 | Eliassen, Cory H |  | 80.04
PR | 995 | 07/05/19 | 44 | Hubbard, Robert W |  | 42.35
PR | 995 | 07/05/19 | 72 | Taylor, Evan R |  | 478.98
PR | 995 | 07/05/19 | 77 | Villalobos Tejada, Carlos F |  | 280.78
PR | 995 | 07/05/19 | 78 | Waites, Thaddeus Z |  | 200.1
PR | 995 | 07/12/19 | 279 | Ascencio, Jose L |  | 406.56
PR | 995 | 07/12/19 | 294 | Cruz Reyes, Jose |  | 393.01
PR | 995 | 07/12/19 | 343 | Taylor, Evan R |  | 393.01
PR | 995 | 07/12/19 | 348 | Villalobos Tejada, Carlos F |  | 230.38
PR | 995 | 07/12/19 | 349 | Waites, Thaddeus Z |  | 304.92
PR | 995 | 07/19/19 | 509 | Ascencio, Jose L |  | 203.28
PR | 995 | 07/19/19 | 509 | Ascencio, Jose L |  | 203.28
PR | 995 | 07/19/19 | 524 | Cruz Reyes, Jose |  | 393.01
PR | 995 | 07/19/19 | 524 | Cruz Reyes, Jose |  | 98.25
PR | 995 | 07/19/19 | 573 | Taylor, Evan R |  | 294.76
PR | 995 | 07/19/19 | 573 | Taylor, Evan R |  | 196.5
PR | 995 | 07/19/19 | 578 | Villalobos Tejada, Carlos F |  | 172.79
PR | 995 | 07/19/19 | 578 | Villalobos Tejada, Carlos F |  | 57.6
PR | 995 | 07/19/19 | 579 | Waites, Thaddeus Z |  | 304.92
PR | 995 | 07/19/19 | 579 | Waites, Thaddeus Z |  | 76.23
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/26/19 | 628 | Cruz Reyes, Jose |  | 491.26
PR | 995 | 07/26/19 | 676 | Taylor, Evan R |  | 491.26
PR | 995 | 07/26/19 | 681 | Villalobos Tejada, Carlos F |  | 230.38
PR | 995 | 07/26/19 | 681 | Villalobos Tejada, Carlos F |  | 57.6
PR | 995 | 07/26/19 | 682 | Waites, Thaddeus Z |  | 190.58
PR | 995 | 07/26/19 | 682 | Waites, Thaddeus Z |  | 190.58
PR | 995 | 08/02/19 | 5 | Ascencio, Jose L |  | 508.2
PR | 995 | 08/02/19 | 20 | Cruz Reyes, Jose |  | 491.26
PR | 995 | 08/02/19 | 36 | Hubbard, Dustin R |  | 31.76
PR | 995 | 08/02/19 | 67 | Taylor, Evan R |  | 393.01
PR | 995 | 08/02/19 | 72 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 08/02/19 | 73 | Waites, Thaddeus Z |  | 171.52
PR | 995 | 08/02/19 | 73 | Waites, Thaddeus Z |  | 171.52
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/09/19 | 257 | Ascencio, Jose L |  | 406.56
PR | 995 | 08/09/19 | 257 | Ascencio, Jose L |  | 101.64
PR | 995 | 08/09/19 | 260 | Barnhart, Joseph N |  | 21.18
PR | 995 | 08/09/19 | 272 | Cruz Reyes, Jose |  | 491.26
PR | 995 | 08/09/19 | 289 | Hubbard, Dustin R |  | 42.35
PR | 995 | 08/09/19 | 319 | Taylor, Evan R |  | 478.98
PR | 995 | 08/09/19 | 319 | Taylor, Evan R |  | 12.28
PR | 995 | 08/09/19 | 324 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 171.52
PR | 995 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 171.52
PR | 995 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 38.12
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/16/19 | 564 | Ascencio, Jose L |  | 508.2
PR | 995 | 08/16/19 | 579 | Cruz Reyes, Jose |  | 98.25
PR | 995 | 08/16/19 | 627 | Taylor, Evan R |  | 196.5
PR | 995 | 08/16/19 | 632 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 08/16/19 | 633 | Waites, Thaddeus Z |  | 57.17
PR | 995 | 08/16/19 | 633 | Waites, Thaddeus Z |  | 171.52
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/23/19 | 800 | Ascencio, Jose L |  | 508.2
PR | 995 | 08/23/19 | 810 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 08/23/19 | 823 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 08/23/19 | 864 | Taylor, Evan R |  | 294.76
PR | 995 | 08/23/19 | 869 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 08/23/19 | 870 | Waites, Thaddeus Z |  | 381.15
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 108.42
PR | 995 | 08/30/19 | 991 | Ascencio, Jose L |  | 508.2
PR | 995 | 08/30/19 | 1001 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 08/30/19 | 1014 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 08/30/19 | 1049 | Sanders, Allen O |  | 41.5
PR | 995 | 08/30/19 | 1055 | Taylor, Evan R |  | 491.26
PR | 995 | 08/30/19 | 1058 | Velasquez Cruz, Denis M |  | 135.52
PR | 995 | 08/30/19 | 1059 | Velasquez Cruz, Osman N |  | 21.18
PR | 995 | 08/30/19 | 1060 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 08/30/19 | 1061 | Waites, Thaddeus Z |  | 304.92
PR | 995 | 08/30/19 | 1061 | Waites, Thaddeus Z |  | 76.23
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 27.72
PR | 995 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/06/19 | 12 | Ascencio, Jose L |  | 406.56
PR | 995 | 09/06/19 | 22 | Cornejo Orellana, Carlos E |  | 311.7
PR | 995 | 09/06/19 | 35 | Garcia Perez, Ervey O |  | 216.83
PR | 995 | 09/06/19 | 76 | Taylor, Evan R |  | 393.01
PR | 995 | 09/06/19 | 79 | Velasquez Cruz, Denis M |  | 216.83
PR | 995 | 09/06/19 | 80 | Velasquez Cruz, Osman N |  | 169.4
PR | 995 | 09/06/19 | 81 | Villalobos Tejada, Carlos F |  | 230.38
PR | 995 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 152.46
PR | 995 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 38.12
PR | 995 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 114.35
PR | 995 | 09/13/19 | 236 | Ascencio, Jose L |  | 508.2
PR | 995 | 09/13/19 | 246 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 09/13/19 | 259 | Garcia Perez, Ervey O |  | 108.42
PR | 995 | 09/13/19 | 259 | Garcia Perez, Ervey O |  | 162.62
PR | 995 | 09/13/19 | 299 | Taylor, Evan R |  | 491.26
PR | 995 | 09/13/19 | 302 | Velasquez Cruz, Denis M |  | 216.83
PR | 995 | 09/13/19 | 302 | Velasquez Cruz, Denis M |  | 216.83
PR | 995 | 09/13/19 | 303 | Velasquez Cruz, Osman N |  | 169.4
PR | 995 | 09/13/19 | 303 | Velasquez Cruz, Osman N |  | 254.1
PR | 995 | 09/13/19 | 304 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 76.23
PR | 995 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 190.58
PR | 995 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 114.35
PR | 995 | 09/20/19 | 473 | Ascencio, Jose L |  | 406.56
PR | 995 | 09/20/19 | 473 | Ascencio, Jose L |  | 101.64
PR | 995 | 09/20/19 | 476 | Barnhart, Joseph N |  | 42.35
PR | 995 | 09/20/19 | 483 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 09/20/19 | 496 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 63.53
PR | 995 | 09/20/19 | 537 | Taylor, Evan R |  | 491.26
PR | 995 | 09/20/19 | 540 | Velasquez Cruz, Denis M |  | 216.83
PR | 995 | 09/20/19 | 540 | Velasquez Cruz, Denis M |  | 325.25
PR | 995 | 09/20/19 | 541 | Velasquez Cruz, Osman N |  | 169.4
PR | 995 | 09/20/19 | 541 | Velasquez Cruz, Osman N |  | 254.1
PR | 995 | 09/20/19 | 542 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 76.23
PR | 995 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 190.58
PR | 995 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 38.12
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 09/27/19 | 629 | Ascencio, Jose L |  | 406.56
PR | 995 | 09/27/19 | 629 | Ascencio, Jose L |  | 101.64
PR | 995 | 09/27/19 | 639 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 09/27/19 | 652 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 09/27/19 | 696 | Taylor, Evan R |  | 491.26
PR | 995 | 09/27/19 | 699 | Velasquez Cruz, Denis M |  | 216.83
PR | 995 | 09/27/19 | 699 | Velasquez Cruz, Denis M |  | 325.25
PR | 995 | 09/27/19 | 700 | Velasquez Cruz, Osman N |  | 169.4
PR | 995 | 09/27/19 | 700 | Velasquez Cruz, Osman N |  | 254.1
PR | 995 | 09/27/19 | 701 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 09/27/19 | 702 | Waites, Thaddeus Z |  | 343.04
PR | 995 | 09/27/19 | 702 | Waites, Thaddeus Z |  | 38.12
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/04/19 | 5 | Ascencio, Jose L |  | 508.2
PR | 995 | 10/04/19 | 15 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 10/04/19 | 28 | Garcia Perez, Ervey O |  | 108.42
PR | 995 | 10/04/19 | 28 | Garcia Perez, Ervey O |  | 162.62
PR | 995 | 10/04/19 | 72 | Taylor, Evan R |  | 491.26
PR | 995 | 10/04/19 | 75 | Velasquez Cruz, Denis M |  | 149.07
PR | 995 | 10/04/19 | 76 | Velasquez Cruz, Osman N |  | 116.46
PR | 995 | 10/04/19 | 77 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 10/04/19 | 78 | Waites, Thaddeus Z |  | 114.35
PR | 995 | 10/04/19 | 78 | Waites, Thaddeus Z |  | 114.35
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/11/19 | 260 | Ascencio, Jose L |  | 508.2
PR | 995 | 10/11/19 | 270 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 10/11/19 | 281 | Frausto Mendoza, Pedro |  | 77.92
PR | 995 | 10/11/19 | 283 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 10/11/19 | 326 | Taylor, Evan R |  | 491.26
PR | 995 | 10/11/19 | 331 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 10/11/19 | 333 | Wennig, Johnathan M |  | 223.61
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/18/19 | 454 | Ascencio, Jose L |  | 508.2
PR | 995 | 10/18/19 | 464 | Cornejo Orellana, Carlos E |  | 389.62
PR | 995 | 10/18/19 | 474 | Frausto Mendoza, Pedro |  | 155.85
PR | 995 | 10/18/19 | 476 | Garcia Perez, Ervey O |  | 271.04
PR | 995 | 10/18/19 | 519 | Taylor, Evan R |  | 491.26
PR | 995 | 10/18/19 | 524 | Villalobos Tejada, Carlos F |  | 287.98
PR | 995 | 10/18/19 | 525 | Waites, Thaddeus Z |  | 343.04
PR | 995 | 10/18/19 | 526 | Wennig, Johnathan M |  | 559.02
PR | 995 | 10/25/19 | 589 | Ascencio, Jose L |  | 457.38
PR | 995 | 10/25/19 | 600 | Cornejo Orellana, Carlos E |  | 350.66
PR | 995 | 10/25/19 | 611 | Garcia Perez, Ervey O |  | 135.52
PR | 995 | 10/25/19 | 611 | Garcia Perez, Ervey O |  | 108.42
PR | 995 | 10/25/19 | 655 | Taylor, Evan R |  | 442.13
PR | 995 | 10/25/19 | 660 | Villalobos Tejada, Carlos F |  | 259.18
PR | 995 | 10/25/19 | 661 | Waites, Thaddeus Z |  | 266.81
PR | 995 | 10/25/19 | 661 | Waites, Thaddeus Z |  | 190.58
PR | 995 | 10/25/19 | 662 | Wennig, Johnathan M |  | 503.12
PR | 995 | 11/01/19 | 5 | Ascencio, Jose L |  | 94.33
PR | 995 | 11/01/19 | 5 | Ascencio, Jose L |  | 559.02
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 137.21
PR | 995 | 11/01/19 | 15 | Cornejo Orellana, Carlos E |  | 352.35
PR | 995 | 11/01/19 | 15 | Cornejo Orellana, Carlos E |  | 88.09
PR | 995 | 11/01/19 | 66 | Sanders, Allen O |  | 45.74
PR | 995 | 11/01/19 | 71 | Taylor, Evan R |  | 94.33
PR | 995 | 11/01/19 | 71 | Taylor, Evan R |  | 559.02
PR | 995 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 54.31
PR | 995 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 257.49
PR | 995 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 64.37
PR | 995 | 11/01/19 | 77 | Waites, Thaddeus Z |  | 332.02
PR | 995 | 11/01/19 | 77 | Waites, Thaddeus Z |  | 342.4
PR | 995 | 11/01/19 | 78 | Wennig, Johnathan M |  | 102.91
PR | 995 | 11/01/19 | 78 | Wennig, Johnathan M |  | 609.84
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 27.72
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 27.72
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/08/19 | 179 | Ascencio, Jose L |  | 559.02
PR | 995 | 11/08/19 | 189 | Cornejo Orellana, Carlos E |  | 352.35
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/08/19 | 245 | Taylor, Evan R |  | 559.02
PR | 995 | 11/08/19 | 250 | Villalobos Tejada, Carlos F |  | 321.86
PR | 995 | 11/08/19 | 251 | Waites, Thaddeus Z |  | 83.01
PR | 995 | 11/08/19 | 251 | Waites, Thaddeus Z |  | 498.04
PR | 995 | 11/08/19 | 252 | Wennig, Johnathan M |  | 609.84
PR | 995 | 11/08/19 | 253 | Donelson, Richard T |  | 27.72
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/15/19 | 439 | Ascencio, Jose L |  | 335.41
PR | 995 | 11/15/19 | 439 | Ascencio, Jose L |  | 223.61
PR | 995 | 11/15/19 | 442 | Barnhart, Joseph N |  | 45.74
PR | 995 | 11/15/19 | 449 | Cornejo Orellana, Carlos E |  | 352.35
PR | 995 | 11/15/19 | 473 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/15/19 | 504 | Taylor, Evan R |  | 559.02
PR | 995 | 11/15/19 | 509 | Villalobos Tejada, Carlos F |  | 257.49
PR | 995 | 11/15/19 | 509 | Villalobos Tejada, Carlos F |  | 64.37
PR | 995 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 145.26
PR | 995 | 11/15/19 | 511 | Wennig, Johnathan M |  | 609.84
PR | 995 | 11/22/19 | 610 | Ascencio, Jose L |  | 335.41
PR | 995 | 11/22/19 | 610 | Ascencio, Jose L |  | 83.85
PR | 995 | 11/22/19 | 613 | Barnhart, Joseph N |  | 45.74
PR | 995 | 11/22/19 | 620 | Cornejo Orellana, Carlos E |  | 418.42
PR | 995 | 11/22/19 | 670 | Sanders, Allen O |  | 57.17
PR | 995 | 11/22/19 | 675 | Taylor, Evan R |  | 531.07
PR | 995 | 11/22/19 | 680 | Villalobos Tejada, Carlos F |  | 177.02
PR | 995 | 11/22/19 | 680 | Villalobos Tejada, Carlos F |  | 64.37
PR | 995 | 11/22/19 | 681 | Waites, Thaddeus Z |  | 581.04
PR | 995 | 11/22/19 | 681 | Waites, Thaddeus Z |  | 103.76
PR | 995 | 11/22/19 | 682 | Wennig, Johnathan M |  | 365.9
PR | 995 | 11/22/19 | 682 | Wennig, Johnathan M |  | 198.2
PR | 995 | 11/27/19 | 844 | Ascencio, Jose L |  | 447.22
PR | 995 | 11/27/19 | 844 | Ascencio, Jose L |  | 111.8
PR | 995 | 11/27/19 | 854 | Cornejo Orellana, Carlos E |  | 440.44
PR | 995 | 11/27/19 | 878 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/27/19 | 904 | Sanders, Allen O |  | 45.74
PR | 995 | 11/27/19 | 909 | Taylor, Evan R |  | 335.41
PR | 995 | 11/27/19 | 909 | Taylor, Evan R |  | 223.61
PR | 995 | 11/27/19 | 914 | Villalobos Tejada, Carlos F |  | 193.12
PR | 995 | 11/27/19 | 914 | Villalobos Tejada, Carlos F |  | 128.74
PR | 995 | 11/27/19 | 915 | Waites, Thaddeus Z |  | 373.53
PR | 995 | 11/27/19 | 915 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 11/27/19 | 916 | Wennig, Johnathan M |  | 609.84
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/06/19 | 30 | Ascencio, Jose L |  | 447.22
PR | 995 | 12/06/19 | 40 | Cornejo Orellana, Carlos E |  | 264.26
PR | 995 | 12/06/19 | 65 | Hubbard, Robert W |  | 22.87
PR | 995 | 12/06/19 | 96 | Taylor, Evan R |  | 335.41
PR | 995 | 12/06/19 | 96 | Taylor, Evan R |  | 111.8
PR | 995 | 12/06/19 | 101 | Villalobos Tejada, Carlos F |  | 257.49
PR | 995 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 41.5
PR | 995 | 12/06/19 | 103 | Wennig, Johnathan M |  | 487.87
PR | 995 | 12/06/19 | 104 | Donelson, Richard T |  | 27.72
PR | 995 | 12/13/19 | 391 | Ascencio, Jose L |  | 559.02
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 114.35
PR | 995 | 12/13/19 | 401 | Cornejo Orellana, Carlos E |  | 352.35
PR | 995 | 12/13/19 | 457 | Taylor, Evan R |  | 223.61
PR | 995 | 12/13/19 | 462 | Villalobos Tejada, Carlos F |  | 321.86
PR | 995 | 12/13/19 | 463 | Waites, Thaddeus Z |  | 435.78
PR | 995 | 12/13/19 | 463 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 12/13/19 | 464 | Wennig, Johnathan M |  | 609.84
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/20/19 | 544 | Ascencio, Jose L |  | 279.51
PR | 995 | 12/20/19 | 554 | Cornejo Orellana, Carlos E |  | 352.35
PR | 995 | 12/20/19 | 557 | Cruz Gonzalez, Julio C |  | 308.31
PR | 995 | 12/20/19 | 562 | Eliassen, Cory H |  | 101.64
PR | 995 | 12/20/19 | 568 | Gauthier, Dillon R |  | 60.98
PR | 995 | 12/20/19 | 605 | Sanders, Allen O |  | 331.6
PR | 995 | 12/20/19 | 610 | Taylor, Evan R |  | 223.61
PR | 995 | 12/20/19 | 615 | Villalobos Tejada, Carlos F |  | 160.93
PR | 995 | 12/20/19 | 616 | Waites, Thaddeus Z |  | 124.51
PR | 995 | 12/20/19 | 616 | Waites, Thaddeus Z |  | 249.02
PR | 995 | 12/20/19 | 617 | Wennig, Johnathan M |  | 243.94
PR | 995 | 12/27/19 | 701 | Ascencio, Jose L |  | 223.61
PR | 995 | 12/27/19 | 701 | Ascencio, Jose L |  | 111.8
PR | 995 | 12/27/19 | 711 | Cornejo Orellana, Carlos E |  | 264.26
PR | 995 | 12/27/19 | 714 | Cruz Gonzalez, Julio C |  | 201.59
PR | 995 | 12/27/19 | 727 | Gerard, Jordan E |  | 426.89
PR | 995 | 12/27/19 | 763 | Sanders, Allen O |  | 45.74
PR | 995 | 12/27/19 | 773 | Villalobos Tejada, Carlos F |  | 193.12
PR | 995 | 12/27/19 | 774 | Waites, Thaddeus Z |  | 207.52
PR | 995 | 12/27/19 | 774 | Waites, Thaddeus Z |  | 290.52
PR | 995 | 12/27/19 | 775 | Wennig, Johnathan M |  | 365.9
PR | 995 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/03/20 | 4 | Ascencio, Jose L |  | 447.22
PR | 995 | 01/03/20 | 14 | Cornejo Orellana, Carlos E |  | 176.18
PR | 995 | 01/03/20 | 14 | Cornejo Orellana, Carlos E |  | 176.18
PR | 995 | 01/03/20 | 15 | Cortes Mendiola, Victor H |  | 127.05
PR | 995 | 01/03/20 | 17 | Cruz Gonzalez, Julio C |  | 260.88
PR | 995 | 01/03/20 | 29 | Gauthier, Dillon R |  | 60.98
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 45.74
PR | 995 | 01/03/20 | 51 | McCabe, Thomas C |  | 214.71
PR | 995 | 01/03/20 | 66 | Sanders, Allen O |  | 91.48
PR | 995 | 01/03/20 | 71 | Taylor, Evan R |  | 223.61
PR | 995 | 01/03/20 | 71 | Taylor, Evan R |  | 69.88
PR | 995 | 01/03/20 | 76 | Villalobos Tejada, Carlos F |  | 128.74
PR | 995 | 01/03/20 | 76 | Villalobos Tejada, Carlos F |  | 128.74
PR | 995 | 01/03/20 | 77 | Waites, Thaddeus Z |  | 435.78
PR | 995 | 01/03/20 | 77 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 01/03/20 | 78 | Wennig, Johnathan M |  | 243.94
PR | 995 | 01/10/20 | 290 | Cruz Gonzalez, Julio C |  | 426.89
PR | 995 | 01/10/20 | 302 | Gauthier, Dillon R |  | 182.95
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 137.21
PR | 995 | 01/10/20 | 324 | McCabe, Thomas C |  | 330.33
PR | 995 | 01/10/20 | 339 | Sanders, Allen O |  | 182.95
PR | 995 | 01/10/20 | 344 | Taylor, Evan R |  | 223.61
PR | 995 | 01/10/20 | 344 | Taylor, Evan R |  | 223.61
PR | 995 | 01/10/20 | 345 | Trower-Kelly, Fidel D |  | 355.74
PR | 995 | 01/10/20 | 350 | Waites, Thaddeus Z |  | 332.02
PR | 995 | 01/10/20 | 350 | Waites, Thaddeus Z |  | 228.27
PR | 995 | 01/17/20 | 546 | Barnhart, Joseph N |  | 22.87
PR | 995 | 01/17/20 | 549 | Boss, Benjamin T |  | 54.21
PR | 995 | 01/17/20 | 556 | Cruz Gonzalez, Julio C |  | 260.88
PR | 995 | 01/17/20 | 579 | Hubbard, Robert W |  | 137.21
PR | 995 | 01/17/20 | 590 | McCabe, Thomas C |  | 462.46
PR | 995 | 01/17/20 | 600 | Roberts, Lake A |  | 137.64
PR | 995 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 01/17/20 | 605 | Sanders, Allen O |  | 182.95
PR | 995 | 01/17/20 | 610 | Taylor, Evan R |  | 111.8
PR | 995 | 01/17/20 | 610 | Taylor, Evan R |  | 111.8
PR | 995 | 01/17/20 | 611 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 01/17/20 | 616 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 01/24/20 | 689 | Cruz Gonzalez, Julio C |  | 438.75
PR | 995 | 01/24/20 | 691 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 01/24/20 | 711 | Hubbard, Robert W |  | 91.48
PR | 995 | 01/24/20 | 721 | McCabe, Thomas C |  | 528.53
PR | 995 | 01/24/20 | 731 | Roberts, Lake A |  | 296.45
PR | 995 | 01/24/20 | 733 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 01/24/20 | 736 | Sanders, Allen O |  | 125.78
PR | 995 | 01/24/20 | 742 | Trower-Kelly, Fidel D |  | 142.3
PR | 995 | 01/24/20 | 763 | Gerard, Jordan E |  | -426.89
PR | 995 | 01/24/20 | 764 | Gerard, Mitchell J |  | -592.9
PR | 995 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 121.97
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 22.87
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 22.87
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 22.87
PR | 995 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 115.19
PR | 995 | 01/31/20 | 848 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 01/31/20 | 850 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 01/31/20 | 871 | Hubbard, Robert W |  | 251.56
PR | 995 | 01/31/20 | 881 | McCabe, Thomas C |  | 660.66
PR | 995 | 01/31/20 | 897 | Sanders, Allen O |  | 217.26
PR | 995 | 02/07/20 | 39 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 02/07/20 | 41 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 02/07/20 | 50 | Gauthier, Dillon R |  | 121.97
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 34.3
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 68.61
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 114.35
PR | 995 | 02/07/20 | 71 | McCabe, Thomas C |  | 462.46
PR | 995 | 02/07/20 | 71 | McCabe, Thomas C |  | 132.13
PR | 995 | 02/07/20 | 88 | Sanders, Allen O |  | 91.48
PR | 995 | 02/14/20 | 242 | Boss, Benjamin T |  | 60.98
PR | 995 | 02/14/20 | 243 | Boss, Kyle A |  | 71.15
PR | 995 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 114.35
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 68.61
PR | 995 | 02/14/20 | 281 | McCabe, Thomas C |  | 132.13
PR | 995 | 02/14/20 | 281 | McCabe, Thomas C |  | 231.23
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 148.23
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 21.18
PR | 995 | 02/14/20 | 292 | Roberts, Lake A |  | 84.7
PR | 995 | 02/14/20 | 298 | Sanders, Allen O |  | 114.35
PR | 995 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 142.3
PR | 995 | 02/14/20 | 312 | Donelson, Richard T |  | 27.72
PR | 995 | 02/21/20 | 466 | Cruz Gonzalez, Julio C |  | 249.02
PR | 995 | 02/21/20 | 468 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 02/21/20 | 486 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/21/20 | 486 | Hubbard, Robert W |  | 114.35
PR | 995 | 02/21/20 | 496 | McCabe, Thomas C |  | 198.2
PR | 995 | 02/21/20 | 496 | McCabe, Thomas C |  | 396.4
PR | 995 | 02/21/20 | 496 | McCabe, Thomas C |  | 66.07
PR | 995 | 02/21/20 | 508 | Roberts, Lake A |  | 127.05
PR | 995 | 02/21/20 | 508 | Roberts, Lake A |  | 296.45
PR | 995 | 02/21/20 | 514 | Sanders, Allen O |  | 240.12
PR | 995 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 91.48
PR | 995 | 02/28/20 | 694 | Cruz Gonzalez, Julio C |  | 254.95
PR | 995 | 02/28/20 | 716 | Hubbard, Robert W |  | 160.08
PR | 995 | 02/28/20 | 737 | Roberts, Lake A |  | 84.7
PR | 995 | 02/28/20 | 743 | Sanders, Allen O |  | 160.08
PR | 995 | 02/28/20 | 748 | Taylor, Evan R |  | 55.9
PR | 995 | 02/28/20 | 754 | Waites, Thaddeus Z |  | 124.51
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 148.65
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 22.87
PR | 995 | 03/06/20 | 56 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 03/06/20 | 105 | Sanders, Allen O |  | 34.3
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 22.87
PR | 995 | 03/13/20 | 342 | Hubbard, Robert W |  | 68.61
PR | 995 | 03/13/20 | 369 | Sanders, Allen O |  | 22.87
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 22.87
PR | 995 | 03/20/20 | 627 | Sanders, Allen O |  | 34.3
PR | 995 | 03/26/20 | 752 | Barnhart, Joseph N |  | 22.87
PR | 995 | 03/26/20 | 806 | Sanders, Allen O |  | 45.74
PR | 995 | 03/26/20 | 811 | Taylor, Evan R |  | 181.68
PR | 995 | 03/26/20 | 817 | Waites, Thaddeus Z |  | 269.77
PR | 995 | 05/08/20 | 215 | Sanders, Allen O |  | 45.74
PR | 998 | 04/06/18 | 84 | Donelson, Richard T |  | 4.78
PR | 998 | 04/20/18 | 517 | Donelson, Richard T |  | 4.78
PR | 998 | 06/15/18 | 527 | Donelson, Richard T |  | 9.56
PR | 998 | 07/06/18 | 76 | Donelson, Richard T |  | 14.34
PR | 998 | 07/13/18 | 367 | Donelson, Richard T |  | 4.78
PR | 998 | 08/17/18 | 550 | Donelson, Richard T |  | 14.34
PR | 998 | 08/24/18 | 811 | Donelson, Richard T |  | 4.78
PR | 998 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/31/18 | 1000 | Barnhart, Joseph N |  | 14.08
PR | 998 | 08/31/18 | 1069 | Donelson, Richard T |  | 9.56
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/07/18 | 41 | Barnhart, Joseph N |  | 3.52
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/14/18 | 272 | Barnhart, Joseph N |  | 7.04
PR | 998 | 09/14/18 | 310 | Martinez Reyes, Juan C |  | 3.98
PR | 998 | 09/14/18 | 340 | Donelson, Richard T |  | 4.78
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 09/21/18 | 486 | Barnhart, Joseph N |  | 14.08
PR | 998 | 09/21/18 | 552 | Donelson, Richard T |  | 14.34
PR | 998 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/28/18 | 670 | Barnhart, Joseph N |  | 3.52
PR | 998 | 09/28/18 | 708 | Martinez Reyes, Juan C |  | 1.99
PR | 998 | 09/28/18 | 739 | Donelson, Richard T |  | 4.78
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/05/18 | 34 | Barnhart, Joseph N |  | 7.04
PR | 998 | 10/05/18 | 72 | Martinez Reyes, Juan C |  | 1.99
PR | 998 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/19/18 | 438 | Barnhart, Joseph N |  | 10.56
PR | 998 | 10/19/18 | 438 | Barnhart, Joseph N |  | 21.11
PR | 998 | 10/19/18 | 460 | Gerard, Mitchell J |  | 107.1
PR | 998 | 10/19/18 | 476 | Martinez Reyes, Juan C |  | 3.98
PR | 998 | 10/19/18 | 507 | Donelson, Richard T |  | 14.34
PR | 998 | 10/26/18 | 706 | Barnhart, Joseph N |  | 10.56
PR | 998 | 10/26/18 | 706 | Barnhart, Joseph N |  | 42.23
PR | 998 | 10/26/18 | 742 | Martinez Reyes, Juan C |  | 5.97
PR | 998 | 10/26/18 | 742 | Martinez Reyes, Juan C |  | 7.96
PR | 998 | 10/26/18 | 770 | Wennig, Johnathan M |  | 34.27
PR | 998 | 10/26/18 | 774 | Donelson, Richard T |  | 4.78
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 15.3
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 13.39
PR | 998 | 11/02/18 | 9 | Barnhart, Joseph N |  | 103.81
PR | 998 | 11/02/18 | 73 | Wennig, Johnathan M |  | 77.11
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/09/18 | 187 | Barnhart, Joseph N |  | 10.56
PR | 998 | 11/09/18 | 257 | Donelson, Richard T |  | 4.78
PR | 998 | 11/16/18 | 435 | Barnhart, Joseph N |  | 17.6
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 4.78
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/30/18 | 833 | Barnhart, Joseph N |  | 7.34
PR | 998 | 12/07/18 | 47 | Barnhart, Joseph N |  | 14.69
PR | 998 | 12/07/18 | 113 | Donelson, Richard T |  | 14.34
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 270 | Barnhart, Joseph N |  | 18.36
PR | 998 | 12/14/18 | 270 | Barnhart, Joseph N |  | 16.52
PR | 998 | 12/14/18 | 270 | Barnhart, Joseph N |  | 3.67
PR | 998 | 12/14/18 | 270 | Barnhart, Joseph N |  | 11.02
PR | 998 | 12/14/18 | 335 | Wennig, Johnathan M |  | 18.36
PR | 998 | 12/14/18 | 337 | Donelson, Richard T |  | 4.78
PR | 998 | 12/21/18 | 511 | Barnhart, Joseph N |  | 22.03
PR | 998 | 12/21/18 | 547 | Martinez Reyes, Juan C |  | 4.28
PR | 998 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/28/18 | 702 | Barnhart, Joseph N |  | 14.69
PR | 998 | 01/04/19 | 7 | Barnhart, Joseph N |  | 7.34
PR | 998 | 01/11/19 | 215 | Barnhart, Joseph N |  | 25.7
PR | 998 | 01/11/19 | 251 | Martinez Reyes, Juan C |  | 6.43
PR | 998 | 01/18/19 | 469 | Barnhart, Joseph N |  | 47.74
PR | 998 | 01/18/19 | 506 | Martinez Reyes, Juan C |  | 29.99
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/25/19 | 718 | Barnhart, Joseph N |  | 33.05
PR | 998 | 01/25/19 | 755 | Martinez Reyes, Juan C |  | 12.85
PR | 998 | 02/01/19 | 7 | Barnhart, Joseph N |  | 5.51
PR | 998 | 02/01/19 | 15 | Crespin Portillo, Juan D |  | 2.6
PR | 998 | 02/01/19 | 43 | Martinez Reyes, Juan C |  | 14.99
PR | 998 | 02/01/19 | 67 | Waites, Thaddeus Z |  | 4.93
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/22/19 | 582 | Barnhart, Joseph N |  | 22.03
PR | 998 | 02/22/19 | 636 | Serrano, Jeremiah G |  | 9.1
PR | 998 | 03/01/19 | 7 | Barnhart, Joseph N |  | 44.06
PR | 998 | 03/01/19 | 63 | Serrano, Jeremiah G |  | 10.4
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/08/19 | 249 | Barnhart, Joseph N |  | 11.02
PR | 998 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 10.4
PR | 998 | 03/08/19 | 302 | Serrano, Jeremiah G |  | 10.4
PR | 998 | 03/08/19 | 306 | Taylor, Evan R |  | 47.74
PR | 998 | 03/08/19 | 306 | Taylor, Evan R |  | 15.91
PR | 998 | 03/08/19 | 310 | Villalobos Tejada, Carlos F |  | 9.79
PR | 998 | 03/08/19 | 311 | Waites, Thaddeus Z |  | 26.32
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/15/19 | 496 | Barnhart, Joseph N |  | 36.72
PR | 998 | 03/15/19 | 550 | Serrano, Jeremiah G |  | 33.81
PR | 998 | 03/15/19 | 554 | Taylor, Evan R |  | 2.98
PR | 998 | 03/15/19 | 554 | Taylor, Evan R |  | 5.97
PR | 998 | 03/15/19 | 554 | Taylor, Evan R |  | 63.65
PR | 998 | 03/15/19 | 554 | Taylor, Evan R |  | 15.91
PR | 998 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 1.84
PR | 998 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 3.67
PR | 998 | 03/15/19 | 558 | Villalobos Tejada, Carlos F |  | 6.12
PR | 998 | 03/15/19 | 562 | Donelson, Richard T |  | 4.78
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/22/19 | 710 | Barnhart, Joseph N |  | 25.7
PR | 998 | 03/22/19 | 763 | Serrano, Jeremiah G |  | 52.02
PR | 998 | 03/22/19 | 768 | Taylor, Evan R |  | 2.98
PR | 998 | 03/22/19 | 768 | Taylor, Evan R |  | 5.97
PR | 998 | 03/22/19 | 768 | Taylor, Evan R |  | 63.65
PR | 998 | 03/22/19 | 768 | Taylor, Evan R |  | 15.91
PR | 998 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 1.84
PR | 998 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 3.67
PR | 998 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 39.17
PR | 998 | 03/22/19 | 772 | Villalobos Tejada, Carlos F |  | 9.79
PR | 998 | 03/22/19 | 773 | Waites, Thaddeus Z |  | 19.74
PR | 998 | 03/29/19 | 975 | Serrano, Jeremiah G |  | 37.71
PR | 998 | 03/29/19 | 980 | Taylor, Evan R |  | 79.56
PR | 998 | 03/29/19 | 984 | Villalobos Tejada, Carlos F |  | 29.38
PR | 998 | 03/29/19 | 985 | Waites, Thaddeus Z |  | 46.05
PR | 998 | 03/29/19 | 989 | Donelson, Richard T |  | 4.78
PR | 998 | 04/05/19 | 80 | Ascencio, Jose L |  | 51.41
PR | 998 | 04/05/19 | 83 | Barnhart, Joseph N |  | 14.69
PR | 998 | 04/05/19 | 138 | Serrano, Jeremiah G |  | 44.22
PR | 998 | 04/05/19 | 143 | Taylor, Evan R |  | 79.56
PR | 998 | 04/05/19 | 147 | Villalobos Tejada, Carlos F |  | 48.96
PR | 998 | 04/05/19 | 148 | Waites, Thaddeus Z |  | 65.79
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 7.65
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 7.65
PR | 998 | 04/12/19 | 382 | Serrano, Jeremiah G |  | 10.4
PR | 998 | 04/12/19 | 387 | Taylor, Evan R |  | 57.68
PR | 998 | 04/12/19 | 392 | Villalobos Tejada, Carlos F |  | 48.96
PR | 998 | 04/12/19 | 393 | Waites, Thaddeus Z |  | 41.31
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/19/19 | 521 | Ascencio, Jose L |  | 25.7
PR | 998 | 04/19/19 | 524 | Barnhart, Joseph N |  | 3.83
PR | 998 | 04/19/19 | 529 | Cornejo Orellana, Carlos E |  | 19.28
PR | 998 | 04/19/19 | 532 | Crespin Portillo, Juan D |  | 15.61
PR | 998 | 04/19/19 | 542 | Frausto Mendoza, Pedro |  | 12.85
PR | 998 | 04/19/19 | 544 | Garcia Perez, Ervey O |  | 29.38
PR | 998 | 04/19/19 | 585 | Taylor, Evan R |  | 31.82
PR | 998 | 04/19/19 | 588 | Velasquez Cruz, Denis M |  | 26.62
PR | 998 | 04/19/19 | 589 | Velasquez Cruz, Osman N |  | 20.2
PR | 998 | 04/19/19 | 590 | Villalobos Tejada, Carlos F |  | 16.52
PR | 998 | 04/19/19 | 590 | Villalobos Tejada, Carlos F |  | 48.96
PR | 998 | 04/19/19 | 591 | Waites, Thaddeus Z |  | 41.31
PR | 998 | 04/19/19 | 591 | Waites, Thaddeus Z |  | 65.41
PR | 998 | 04/19/19 | 592 | Wennig, Johnathan M |  | 27.54
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/26/19 | 741 | Ascencio, Jose L |  | 17.21
PR | 998 | 04/26/19 | 752 | Crespin Portillo, Juan D |  | 10.9
PR | 998 | 04/26/19 | 761 | Frausto Mendoza, Pedro |  | 8.8
PR | 998 | 04/26/19 | 763 | Garcia Perez, Ervey O |  | 9.18
PR | 998 | 04/26/19 | 763 | Garcia Perez, Ervey O |  | 29.38
PR | 998 | 04/26/19 | 805 | Velasquez Cruz, Denis M |  | 18.36
PR | 998 | 04/26/19 | 806 | Velasquez Cruz, Osman N |  | 9.56
PR | 998 | 04/26/19 | 807 | Villalobos Tejada, Carlos F |  | 9.75
PR | 998 | 04/26/19 | 807 | Villalobos Tejada, Carlos F |  | 31.21
PR | 998 | 04/26/19 | 808 | Waites, Thaddeus Z |  | 5.16
PR | 998 | 04/26/19 | 808 | Waites, Thaddeus Z |  | 68.85
PR | 998 | 05/03/19 | 11 | Barnhart, Joseph N |  | 3.83
PR | 998 | 05/03/19 | 31 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 05/03/19 | 44 | Jimenez Montiel, Carlos A |  | 9.79
PR | 998 | 05/03/19 | 72 | Taylor, Evan R |  | 53.24
PR | 998 | 05/03/19 | 75 | Velasquez Cruz, Denis M |  | 23.87
PR | 998 | 05/03/19 | 76 | Velasquez Cruz, Osman N |  | 18.65
PR | 998 | 05/03/19 | 77 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 05/03/19 | 78 | Waites, Thaddeus Z |  | 33.56
PR | 998 | 05/03/19 | 78 | Waites, Thaddeus Z |  | 68.85
PR | 998 | 05/03/19 | 79 | Wennig, Johnathan M |  | 16.41
PR | 998 | 05/10/19 | 184 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 05/10/19 | 197 | Jimenez Montiel, Carlos A |  | 4.28
PR | 998 | 05/10/19 | 225 | Taylor, Evan R |  | 88.74
PR | 998 | 05/10/19 | 230 | Villalobos Tejada, Carlos F |  | 41.62
PR | 998 | 05/10/19 | 231 | Waites, Thaddeus Z |  | 27.54
PR | 998 | 05/17/19 | 457 | Taylor, Evan R |  | 88.74
PR | 998 | 05/17/19 | 462 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 05/17/19 | 463 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 05/17/19 | 467 | Donelson, Richard T |  | 4.78
PR | 998 | 05/24/19 | 605 | Ascencio, Jose L |  | 13.77
PR | 998 | 05/24/19 | 605 | Ascencio, Jose L |  | 22.95
PR | 998 | 05/24/19 | 613 | Cornejo Orellana, Carlos E |  | 10.56
PR | 998 | 05/24/19 | 613 | Cornejo Orellana, Carlos E |  | 10.56
PR | 998 | 05/24/19 | 641 | Jimenez Montiel, Carlos A |  | 3.67
PR | 998 | 05/24/19 | 641 | Jimenez Montiel, Carlos A |  | 17.14
PR | 998 | 05/24/19 | 669 | Taylor, Evan R |  | 13.31
PR | 998 | 05/24/19 | 669 | Taylor, Evan R |  | 88.74
PR | 998 | 05/24/19 | 674 | Villalobos Tejada, Carlos F |  | 7.8
PR | 998 | 05/24/19 | 674 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 05/24/19 | 675 | Waites, Thaddeus Z |  | 10.33
PR | 998 | 05/24/19 | 675 | Waites, Thaddeus Z |  | 75.74
PR | 998 | 05/24/19 | 680 | Donelson, Richard T |  | 9.56
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/31/19 | 878 | Ascencio, Jose L |  | 55.08
PR | 998 | 05/31/19 | 915 | Jimenez Montiel, Carlos A |  | 28.15
PR | 998 | 05/31/19 | 943 | Taylor, Evan R |  | 79.87
PR | 998 | 05/31/19 | 948 | Villalobos Tejada, Carlos F |  | 46.82
PR | 998 | 06/07/19 | 180 | Ascencio, Jose L |  | 13.77
PR | 998 | 06/07/19 | 180 | Ascencio, Jose L |  | 91.8
PR | 998 | 06/07/19 | 183 | Barnhart, Joseph N |  | 3.83
PR | 998 | 06/07/19 | 183 | Barnhart, Joseph N |  | 7.65
PR | 998 | 06/07/19 | 245 | Taylor, Evan R |  | 13.31
PR | 998 | 06/07/19 | 245 | Taylor, Evan R |  | 88.74
PR | 998 | 06/07/19 | 250 | Villalobos Tejada, Carlos F |  | 7.8
PR | 998 | 06/07/19 | 250 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 06/07/19 | 251 | Waites, Thaddeus Z |  | 68.85
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 6.31
PR | 998 | 06/14/19 | 451 | Ascencio, Jose L |  | 20.66
PR | 998 | 06/14/19 | 451 | Ascencio, Jose L |  | 91.8
PR | 998 | 06/14/19 | 483 | Hubbard, Robert W |  | 11.48
PR | 998 | 06/14/19 | 513 | Taylor, Evan R |  | 43.26
PR | 998 | 06/14/19 | 513 | Taylor, Evan R |  | 88.74
PR | 998 | 06/14/19 | 516 | Velasquez Cruz, Denis M |  | 22.03
PR | 998 | 06/14/19 | 517 | Velasquez Cruz, Osman N |  | 17.21
PR | 998 | 06/14/19 | 518 | Villalobos Tejada, Carlos F |  | 17.56
PR | 998 | 06/14/19 | 518 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 25.82
PR | 998 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 27.54
PR | 998 | 06/14/19 | 519 | Waites, Thaddeus Z |  | 68.85
PR | 998 | 06/14/19 | 520 | Wennig, Johnathan M |  | 17.67
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 9.56
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/21/19 | 619 | Ascencio, Jose L |  | 20.66
PR | 998 | 06/21/19 | 619 | Ascencio, Jose L |  | 91.8
PR | 998 | 06/21/19 | 635 | Cruz Reyes, Jose |  | 19.97
PR | 998 | 06/21/19 | 635 | Cruz Reyes, Jose |  | 88.74
PR | 998 | 06/21/19 | 684 | Taylor, Evan R |  | 19.97
PR | 998 | 06/21/19 | 684 | Taylor, Evan R |  | 88.74
PR | 998 | 06/21/19 | 689 | Villalobos Tejada, Carlos F |  | 11.7
PR | 998 | 06/21/19 | 689 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 18.07
PR | 998 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 79.18
PR | 998 | 06/21/19 | 690 | Waites, Thaddeus Z |  | 3.44
PR | 998 | 06/21/19 | 691 | Wennig, Johnathan M |  | 10.1
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 4.78
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 4.78
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 837 | Ascencio, Jose L |  | 6.89
PR | 998 | 06/28/19 | 837 | Ascencio, Jose L |  | 91.8
PR | 998 | 06/28/19 | 853 | Cruz Reyes, Jose |  | 6.66
PR | 998 | 06/28/19 | 853 | Cruz Reyes, Jose |  | 88.74
PR | 998 | 06/28/19 | 901 | Taylor, Evan R |  | 6.66
PR | 998 | 06/28/19 | 901 | Taylor, Evan R |  | 88.74
PR | 998 | 06/28/19 | 906 | Villalobos Tejada, Carlos F |  | 3.9
PR | 998 | 06/28/19 | 906 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 06/28/19 | 907 | Waites, Thaddeus Z |  | 58.52
PR | 998 | 06/28/19 | 908 | Wennig, Johnathan M |  | 20.2
PR | 998 | 06/28/19 | 910 | Donelson, Richard T |  | 14.34
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/05/19 | 9 | Ascencio, Jose L |  | 89.51
PR | 998 | 07/05/19 | 12 | Barnhart, Joseph N |  | 7.65
PR | 998 | 07/05/19 | 25 | Cruz Reyes, Jose |  | 86.52
PR | 998 | 07/05/19 | 29 | Eliassen, Cory H |  | 14.46
PR | 998 | 07/05/19 | 44 | Hubbard, Robert W |  | 7.65
PR | 998 | 07/05/19 | 72 | Taylor, Evan R |  | 86.52
PR | 998 | 07/05/19 | 77 | Villalobos Tejada, Carlos F |  | 50.72
PR | 998 | 07/05/19 | 78 | Waites, Thaddeus Z |  | 36.15
PR | 998 | 07/12/19 | 279 | Ascencio, Jose L |  | 73.44
PR | 998 | 07/12/19 | 294 | Cruz Reyes, Jose |  | 70.99
PR | 998 | 07/12/19 | 343 | Taylor, Evan R |  | 70.99
PR | 998 | 07/12/19 | 348 | Villalobos Tejada, Carlos F |  | 41.62
PR | 998 | 07/12/19 | 349 | Waites, Thaddeus Z |  | 55.08
PR | 998 | 07/19/19 | 509 | Ascencio, Jose L |  | 36.72
PR | 998 | 07/19/19 | 509 | Ascencio, Jose L |  | 36.72
PR | 998 | 07/19/19 | 524 | Cruz Reyes, Jose |  | 70.99
PR | 998 | 07/19/19 | 524 | Cruz Reyes, Jose |  | 17.75
PR | 998 | 07/19/19 | 573 | Taylor, Evan R |  | 53.24
PR | 998 | 07/19/19 | 573 | Taylor, Evan R |  | 35.5
PR | 998 | 07/19/19 | 578 | Villalobos Tejada, Carlos F |  | 31.21
PR | 998 | 07/19/19 | 578 | Villalobos Tejada, Carlos F |  | 10.4
PR | 998 | 07/19/19 | 579 | Waites, Thaddeus Z |  | 55.08
PR | 998 | 07/19/19 | 579 | Waites, Thaddeus Z |  | 13.77
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 628 | Cruz Reyes, Jose |  | 88.74
PR | 998 | 07/26/19 | 676 | Taylor, Evan R |  | 88.74
PR | 998 | 07/26/19 | 681 | Villalobos Tejada, Carlos F |  | 41.62
PR | 998 | 07/26/19 | 681 | Villalobos Tejada, Carlos F |  | 10.4
PR | 998 | 07/26/19 | 682 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 07/26/19 | 682 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 08/02/19 | 5 | Ascencio, Jose L |  | 91.8
PR | 998 | 08/02/19 | 20 | Cruz Reyes, Jose |  | 88.74
PR | 998 | 08/02/19 | 36 | Hubbard, Dustin R |  | 5.74
PR | 998 | 08/02/19 | 67 | Taylor, Evan R |  | 70.99
PR | 998 | 08/02/19 | 72 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 08/02/19 | 73 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 08/02/19 | 73 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/09/19 | 257 | Ascencio, Jose L |  | 73.44
PR | 998 | 08/09/19 | 257 | Ascencio, Jose L |  | 18.36
PR | 998 | 08/09/19 | 260 | Barnhart, Joseph N |  | 3.83
PR | 998 | 08/09/19 | 272 | Cruz Reyes, Jose |  | 88.74
PR | 998 | 08/09/19 | 289 | Hubbard, Dustin R |  | 7.65
PR | 998 | 08/09/19 | 319 | Taylor, Evan R |  | 86.52
PR | 998 | 08/09/19 | 319 | Taylor, Evan R |  | 2.22
PR | 998 | 08/09/19 | 324 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 08/09/19 | 325 | Waites, Thaddeus Z |  | 6.89
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/16/19 | 564 | Ascencio, Jose L |  | 91.8
PR | 998 | 08/16/19 | 579 | Cruz Reyes, Jose |  | 17.75
PR | 998 | 08/16/19 | 627 | Taylor, Evan R |  | 35.5
PR | 998 | 08/16/19 | 632 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 08/16/19 | 633 | Waites, Thaddeus Z |  | 10.33
PR | 998 | 08/16/19 | 633 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/23/19 | 800 | Ascencio, Jose L |  | 91.8
PR | 998 | 08/23/19 | 810 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 08/23/19 | 823 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 08/23/19 | 864 | Taylor, Evan R |  | 53.24
PR | 998 | 08/23/19 | 869 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 08/23/19 | 870 | Waites, Thaddeus Z |  | 68.85
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 19.58
PR | 998 | 08/30/19 | 991 | Ascencio, Jose L |  | 91.8
PR | 998 | 08/30/19 | 1001 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 08/30/19 | 1014 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 08/30/19 | 1049 | Sanders, Allen O |  | 7.5
PR | 998 | 08/30/19 | 1055 | Taylor, Evan R |  | 88.74
PR | 998 | 08/30/19 | 1058 | Velasquez Cruz, Denis M |  | 24.48
PR | 998 | 08/30/19 | 1059 | Velasquez Cruz, Osman N |  | 3.83
PR | 998 | 08/30/19 | 1060 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 08/30/19 | 1061 | Waites, Thaddeus Z |  | 55.08
PR | 998 | 08/30/19 | 1061 | Waites, Thaddeus Z |  | 13.77
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 4.78
PR | 998 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/06/19 | 12 | Ascencio, Jose L |  | 73.44
PR | 998 | 09/06/19 | 22 | Cornejo Orellana, Carlos E |  | 56.3
PR | 998 | 09/06/19 | 35 | Garcia Perez, Ervey O |  | 39.17
PR | 998 | 09/06/19 | 76 | Taylor, Evan R |  | 70.99
PR | 998 | 09/06/19 | 79 | Velasquez Cruz, Denis M |  | 39.17
PR | 998 | 09/06/19 | 80 | Velasquez Cruz, Osman N |  | 30.6
PR | 998 | 09/06/19 | 81 | Villalobos Tejada, Carlos F |  | 41.62
PR | 998 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 27.54
PR | 998 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 6.89
PR | 998 | 09/06/19 | 82 | Waites, Thaddeus Z |  | 20.66
PR | 998 | 09/13/19 | 236 | Ascencio, Jose L |  | 91.8
PR | 998 | 09/13/19 | 246 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 09/13/19 | 259 | Garcia Perez, Ervey O |  | 19.58
PR | 998 | 09/13/19 | 259 | Garcia Perez, Ervey O |  | 29.38
PR | 998 | 09/13/19 | 299 | Taylor, Evan R |  | 88.74
PR | 998 | 09/13/19 | 302 | Velasquez Cruz, Denis M |  | 39.17
PR | 998 | 09/13/19 | 302 | Velasquez Cruz, Denis M |  | 39.17
PR | 998 | 09/13/19 | 303 | Velasquez Cruz, Osman N |  | 30.6
PR | 998 | 09/13/19 | 303 | Velasquez Cruz, Osman N |  | 45.9
PR | 998 | 09/13/19 | 304 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 13.77
PR | 998 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 09/13/19 | 305 | Waites, Thaddeus Z |  | 20.66
PR | 998 | 09/20/19 | 473 | Ascencio, Jose L |  | 73.44
PR | 998 | 09/20/19 | 473 | Ascencio, Jose L |  | 18.36
PR | 998 | 09/20/19 | 476 | Barnhart, Joseph N |  | 7.65
PR | 998 | 09/20/19 | 483 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 09/20/19 | 496 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 11.48
PR | 998 | 09/20/19 | 537 | Taylor, Evan R |  | 88.74
PR | 998 | 09/20/19 | 540 | Velasquez Cruz, Denis M |  | 39.17
PR | 998 | 09/20/19 | 540 | Velasquez Cruz, Denis M |  | 58.75
PR | 998 | 09/20/19 | 541 | Velasquez Cruz, Osman N |  | 30.6
PR | 998 | 09/20/19 | 541 | Velasquez Cruz, Osman N |  | 45.9
PR | 998 | 09/20/19 | 542 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 13.77
PR | 998 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 09/20/19 | 543 | Waites, Thaddeus Z |  | 6.89
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/27/19 | 629 | Ascencio, Jose L |  | 73.44
PR | 998 | 09/27/19 | 629 | Ascencio, Jose L |  | 18.36
PR | 998 | 09/27/19 | 639 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 09/27/19 | 652 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 09/27/19 | 696 | Taylor, Evan R |  | 88.74
PR | 998 | 09/27/19 | 699 | Velasquez Cruz, Denis M |  | 39.17
PR | 998 | 09/27/19 | 699 | Velasquez Cruz, Denis M |  | 58.75
PR | 998 | 09/27/19 | 700 | Velasquez Cruz, Osman N |  | 30.6
PR | 998 | 09/27/19 | 700 | Velasquez Cruz, Osman N |  | 45.9
PR | 998 | 09/27/19 | 701 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 09/27/19 | 702 | Waites, Thaddeus Z |  | 61.97
PR | 998 | 09/27/19 | 702 | Waites, Thaddeus Z |  | 6.89
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/04/19 | 5 | Ascencio, Jose L |  | 91.8
PR | 998 | 10/04/19 | 15 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 10/04/19 | 28 | Garcia Perez, Ervey O |  | 19.58
PR | 998 | 10/04/19 | 28 | Garcia Perez, Ervey O |  | 29.38
PR | 998 | 10/04/19 | 72 | Taylor, Evan R |  | 88.74
PR | 998 | 10/04/19 | 75 | Velasquez Cruz, Denis M |  | 26.93
PR | 998 | 10/04/19 | 76 | Velasquez Cruz, Osman N |  | 21.04
PR | 998 | 10/04/19 | 77 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 10/04/19 | 78 | Waites, Thaddeus Z |  | 20.66
PR | 998 | 10/04/19 | 78 | Waites, Thaddeus Z |  | 20.66
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/11/19 | 260 | Ascencio, Jose L |  | 91.8
PR | 998 | 10/11/19 | 270 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 10/11/19 | 281 | Frausto Mendoza, Pedro |  | 14.08
PR | 998 | 10/11/19 | 283 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 10/11/19 | 326 | Taylor, Evan R |  | 88.74
PR | 998 | 10/11/19 | 331 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 10/11/19 | 333 | Wennig, Johnathan M |  | 40.39
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/18/19 | 454 | Ascencio, Jose L |  | 91.8
PR | 998 | 10/18/19 | 464 | Cornejo Orellana, Carlos E |  | 70.38
PR | 998 | 10/18/19 | 474 | Frausto Mendoza, Pedro |  | 28.15
PR | 998 | 10/18/19 | 476 | Garcia Perez, Ervey O |  | 48.96
PR | 998 | 10/18/19 | 519 | Taylor, Evan R |  | 88.74
PR | 998 | 10/18/19 | 524 | Villalobos Tejada, Carlos F |  | 52.02
PR | 998 | 10/18/19 | 525 | Waites, Thaddeus Z |  | 61.97
PR | 998 | 10/18/19 | 526 | Wennig, Johnathan M |  | 100.98
PR | 998 | 10/25/19 | 589 | Ascencio, Jose L |  | 82.62
PR | 998 | 10/25/19 | 600 | Cornejo Orellana, Carlos E |  | 63.34
PR | 998 | 10/25/19 | 611 | Garcia Perez, Ervey O |  | 24.48
PR | 998 | 10/25/19 | 611 | Garcia Perez, Ervey O |  | 19.58
PR | 998 | 10/25/19 | 655 | Taylor, Evan R |  | 79.87
PR | 998 | 10/25/19 | 660 | Villalobos Tejada, Carlos F |  | 46.82
PR | 998 | 10/25/19 | 661 | Waites, Thaddeus Z |  | 48.2
PR | 998 | 10/25/19 | 661 | Waites, Thaddeus Z |  | 34.43
PR | 998 | 10/25/19 | 662 | Wennig, Johnathan M |  | 90.88
PR | 998 | 11/01/19 | 5 | Ascencio, Jose L |  | 17.04
PR | 998 | 11/01/19 | 5 | Ascencio, Jose L |  | 100.98
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 24.79
PR | 998 | 11/01/19 | 15 | Cornejo Orellana, Carlos E |  | 63.65
PR | 998 | 11/01/19 | 15 | Cornejo Orellana, Carlos E |  | 15.91
PR | 998 | 11/01/19 | 66 | Sanders, Allen O |  | 8.26
PR | 998 | 11/01/19 | 71 | Taylor, Evan R |  | 17.04
PR | 998 | 11/01/19 | 71 | Taylor, Evan R |  | 100.98
PR | 998 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 9.81
PR | 998 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 46.51
PR | 998 | 11/01/19 | 76 | Villalobos Tejada, Carlos F |  | 11.63
PR | 998 | 11/01/19 | 77 | Waites, Thaddeus Z |  | 59.98
PR | 998 | 11/01/19 | 77 | Waites, Thaddeus Z |  | 61.85
PR | 998 | 11/01/19 | 78 | Wennig, Johnathan M |  | 18.59
PR | 998 | 11/01/19 | 78 | Wennig, Johnathan M |  | 110.16
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 4.78
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 4.78
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/08/19 | 179 | Ascencio, Jose L |  | 100.98
PR | 998 | 11/08/19 | 189 | Cornejo Orellana, Carlos E |  | 63.65
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/08/19 | 245 | Taylor, Evan R |  | 100.98
PR | 998 | 11/08/19 | 250 | Villalobos Tejada, Carlos F |  | 58.14
PR | 998 | 11/08/19 | 251 | Waites, Thaddeus Z |  | 14.99
PR | 998 | 11/08/19 | 251 | Waites, Thaddeus Z |  | 89.96
PR | 998 | 11/08/19 | 252 | Wennig, Johnathan M |  | 110.16
PR | 998 | 11/08/19 | 253 | Donelson, Richard T |  | 4.78
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/15/19 | 439 | Ascencio, Jose L |  | 60.59
PR | 998 | 11/15/19 | 439 | Ascencio, Jose L |  | 40.39
PR | 998 | 11/15/19 | 442 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/15/19 | 449 | Cornejo Orellana, Carlos E |  | 63.65
PR | 998 | 11/15/19 | 473 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/15/19 | 504 | Taylor, Evan R |  | 100.98
PR | 998 | 11/15/19 | 509 | Villalobos Tejada, Carlos F |  | 46.51
PR | 998 | 11/15/19 | 509 | Villalobos Tejada, Carlos F |  | 11.63
PR | 998 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 11/15/19 | 510 | Waites, Thaddeus Z |  | 26.24
PR | 998 | 11/15/19 | 511 | Wennig, Johnathan M |  | 110.16
PR | 998 | 11/22/19 | 610 | Ascencio, Jose L |  | 60.59
PR | 998 | 11/22/19 | 610 | Ascencio, Jose L |  | 15.15
PR | 998 | 11/22/19 | 613 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/22/19 | 620 | Cornejo Orellana, Carlos E |  | 75.58
PR | 998 | 11/22/19 | 670 | Sanders, Allen O |  | 10.33
PR | 998 | 11/22/19 | 675 | Taylor, Evan R |  | 95.93
PR | 998 | 11/22/19 | 680 | Villalobos Tejada, Carlos F |  | 31.98
PR | 998 | 11/22/19 | 680 | Villalobos Tejada, Carlos F |  | 11.63
PR | 998 | 11/22/19 | 681 | Waites, Thaddeus Z |  | 104.96
PR | 998 | 11/22/19 | 681 | Waites, Thaddeus Z |  | 18.74
PR | 998 | 11/22/19 | 682 | Wennig, Johnathan M |  | 66.1
PR | 998 | 11/22/19 | 682 | Wennig, Johnathan M |  | 35.8
PR | 998 | 11/27/19 | 844 | Ascencio, Jose L |  | 80.78
PR | 998 | 11/27/19 | 844 | Ascencio, Jose L |  | 20.2
PR | 998 | 11/27/19 | 854 | Cornejo Orellana, Carlos E |  | 79.56
PR | 998 | 11/27/19 | 878 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/27/19 | 904 | Sanders, Allen O |  | 8.26
PR | 998 | 11/27/19 | 909 | Taylor, Evan R |  | 60.59
PR | 998 | 11/27/19 | 909 | Taylor, Evan R |  | 40.39
PR | 998 | 11/27/19 | 914 | Villalobos Tejada, Carlos F |  | 34.88
PR | 998 | 11/27/19 | 914 | Villalobos Tejada, Carlos F |  | 23.26
PR | 998 | 11/27/19 | 915 | Waites, Thaddeus Z |  | 67.47
PR | 998 | 11/27/19 | 915 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 11/27/19 | 916 | Wennig, Johnathan M |  | 110.16
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/06/19 | 30 | Ascencio, Jose L |  | 80.78
PR | 998 | 12/06/19 | 40 | Cornejo Orellana, Carlos E |  | 47.74
PR | 998 | 12/06/19 | 65 | Hubbard, Robert W |  | 4.13
PR | 998 | 12/06/19 | 96 | Taylor, Evan R |  | 60.59
PR | 998 | 12/06/19 | 96 | Taylor, Evan R |  | 20.2
PR | 998 | 12/06/19 | 101 | Villalobos Tejada, Carlos F |  | 46.51
PR | 998 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 12/06/19 | 102 | Waites, Thaddeus Z |  | 7.5
PR | 998 | 12/06/19 | 103 | Wennig, Johnathan M |  | 88.13
PR | 998 | 12/06/19 | 104 | Donelson, Richard T |  | 4.78
PR | 998 | 12/13/19 | 391 | Ascencio, Jose L |  | 100.98
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 20.66
PR | 998 | 12/13/19 | 401 | Cornejo Orellana, Carlos E |  | 63.65
PR | 998 | 12/13/19 | 457 | Taylor, Evan R |  | 40.39
PR | 998 | 12/13/19 | 462 | Villalobos Tejada, Carlos F |  | 58.14
PR | 998 | 12/13/19 | 463 | Waites, Thaddeus Z |  | 78.72
PR | 998 | 12/13/19 | 463 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 12/13/19 | 464 | Wennig, Johnathan M |  | 110.16
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/20/19 | 544 | Ascencio, Jose L |  | 50.49
PR | 998 | 12/20/19 | 554 | Cornejo Orellana, Carlos E |  | 63.65
PR | 998 | 12/20/19 | 557 | Cruz Gonzalez, Julio C |  | 55.69
PR | 998 | 12/20/19 | 562 | Eliassen, Cory H |  | 18.36
PR | 998 | 12/20/19 | 568 | Gauthier, Dillon R |  | 11.02
PR | 998 | 12/20/19 | 605 | Sanders, Allen O |  | 59.9
PR | 998 | 12/20/19 | 610 | Taylor, Evan R |  | 40.39
PR | 998 | 12/20/19 | 615 | Villalobos Tejada, Carlos F |  | 29.07
PR | 998 | 12/20/19 | 616 | Waites, Thaddeus Z |  | 22.49
PR | 998 | 12/20/19 | 616 | Waites, Thaddeus Z |  | 44.98
PR | 998 | 12/20/19 | 617 | Wennig, Johnathan M |  | 44.06
PR | 998 | 12/27/19 | 701 | Ascencio, Jose L |  | 40.39
PR | 998 | 12/27/19 | 701 | Ascencio, Jose L |  | 20.2
PR | 998 | 12/27/19 | 711 | Cornejo Orellana, Carlos E |  | 47.74
PR | 998 | 12/27/19 | 714 | Cruz Gonzalez, Julio C |  | 36.41
PR | 998 | 12/27/19 | 727 | Gerard, Jordan E |  | 77.11
PR | 998 | 12/27/19 | 763 | Sanders, Allen O |  | 8.26
PR | 998 | 12/27/19 | 773 | Villalobos Tejada, Carlos F |  | 34.88
PR | 998 | 12/27/19 | 774 | Waites, Thaddeus Z |  | 37.49
PR | 998 | 12/27/19 | 774 | Waites, Thaddeus Z |  | 52.48
PR | 998 | 12/27/19 | 775 | Wennig, Johnathan M |  | 66.1
PR | 998 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/03/20 | 4 | Ascencio, Jose L |  | 80.78
PR | 998 | 01/03/20 | 14 | Cornejo Orellana, Carlos E |  | 31.82
PR | 998 | 01/03/20 | 14 | Cornejo Orellana, Carlos E |  | 31.82
PR | 998 | 01/03/20 | 15 | Cortes Mendiola, Victor H |  | 22.95
PR | 998 | 01/03/20 | 17 | Cruz Gonzalez, Julio C |  | 47.12
PR | 998 | 01/03/20 | 29 | Gauthier, Dillon R |  | 11.02
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/03/20 | 51 | McCabe, Thomas C |  | 38.79
PR | 998 | 01/03/20 | 66 | Sanders, Allen O |  | 16.52
PR | 998 | 01/03/20 | 71 | Taylor, Evan R |  | 40.39
PR | 998 | 01/03/20 | 71 | Taylor, Evan R |  | 12.62
PR | 998 | 01/03/20 | 76 | Villalobos Tejada, Carlos F |  | 23.26
PR | 998 | 01/03/20 | 76 | Villalobos Tejada, Carlos F |  | 23.26
PR | 998 | 01/03/20 | 77 | Waites, Thaddeus Z |  | 78.72
PR | 998 | 01/03/20 | 77 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 01/03/20 | 78 | Wennig, Johnathan M |  | 44.06
PR | 998 | 01/10/20 | 290 | Cruz Gonzalez, Julio C |  | 77.11
PR | 998 | 01/10/20 | 302 | Gauthier, Dillon R |  | 33.05
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 24.79
PR | 998 | 01/10/20 | 324 | McCabe, Thomas C |  | 59.67
PR | 998 | 01/10/20 | 339 | Sanders, Allen O |  | 33.05
PR | 998 | 01/10/20 | 344 | Taylor, Evan R |  | 40.39
PR | 998 | 01/10/20 | 344 | Taylor, Evan R |  | 40.39
PR | 998 | 01/10/20 | 345 | Trower-Kelly, Fidel D |  | 64.26
PR | 998 | 01/10/20 | 350 | Waites, Thaddeus Z |  | 59.98
PR | 998 | 01/10/20 | 350 | Waites, Thaddeus Z |  | 41.23
PR | 998 | 01/17/20 | 546 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/17/20 | 549 | Boss, Benjamin T |  | 9.79
PR | 998 | 01/17/20 | 556 | Cruz Gonzalez, Julio C |  | 47.12
PR | 998 | 01/17/20 | 579 | Hubbard, Robert W |  | 24.79
PR | 998 | 01/17/20 | 590 | McCabe, Thomas C |  | 83.54
PR | 998 | 01/17/20 | 600 | Roberts, Lake A |  | 24.86
PR | 998 | 01/17/20 | 602 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 01/17/20 | 605 | Sanders, Allen O |  | 33.05
PR | 998 | 01/17/20 | 610 | Taylor, Evan R |  | 20.2
PR | 998 | 01/17/20 | 610 | Taylor, Evan R |  | 20.2
PR | 998 | 01/17/20 | 611 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 01/17/20 | 616 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 01/24/20 | 689 | Cruz Gonzalez, Julio C |  | 79.25
PR | 998 | 01/24/20 | 691 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 01/24/20 | 711 | Hubbard, Robert W |  | 16.52
PR | 998 | 01/24/20 | 721 | McCabe, Thomas C |  | 95.47
PR | 998 | 01/24/20 | 731 | Roberts, Lake A |  | 53.55
PR | 998 | 01/24/20 | 733 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 01/24/20 | 736 | Sanders, Allen O |  | 22.72
PR | 998 | 01/24/20 | 742 | Trower-Kelly, Fidel D |  | 25.7
PR | 998 | 01/24/20 | 763 | Gerard, Jordan E |  | -77.11
PR | 998 | 01/24/20 | 764 | Gerard, Mitchell J |  | -107.1
PR | 998 | 01/31/20 | 836 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/31/20 | 847 | Cortes Sepulveda, Jose R |  | 20.81
PR | 998 | 01/31/20 | 848 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 01/31/20 | 850 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 01/31/20 | 871 | Hubbard, Robert W |  | 45.44
PR | 998 | 01/31/20 | 881 | McCabe, Thomas C |  | 119.34
PR | 998 | 01/31/20 | 897 | Sanders, Allen O |  | 39.24
PR | 998 | 02/07/20 | 39 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 02/07/20 | 41 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 02/07/20 | 50 | Gauthier, Dillon R |  | 22.03
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 6.2
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 12.39
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 20.66
PR | 998 | 02/07/20 | 71 | McCabe, Thomas C |  | 83.54
PR | 998 | 02/07/20 | 71 | McCabe, Thomas C |  | 23.87
PR | 998 | 02/07/20 | 88 | Sanders, Allen O |  | 16.52
PR | 998 | 02/14/20 | 242 | Boss, Benjamin T |  | 11.02
PR | 998 | 02/14/20 | 243 | Boss, Kyle A |  | 12.85
PR | 998 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 20.66
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 12.39
PR | 998 | 02/14/20 | 281 | McCabe, Thomas C |  | 23.87
PR | 998 | 02/14/20 | 281 | McCabe, Thomas C |  | 41.77
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 26.78
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 3.83
PR | 998 | 02/14/20 | 292 | Roberts, Lake A |  | 15.3
PR | 998 | 02/14/20 | 298 | Sanders, Allen O |  | 20.66
PR | 998 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 25.7
PR | 998 | 02/14/20 | 312 | Donelson, Richard T |  | 4.78
PR | 998 | 02/21/20 | 466 | Cruz Gonzalez, Julio C |  | 44.98
PR | 998 | 02/21/20 | 468 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 02/21/20 | 486 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/21/20 | 486 | Hubbard, Robert W |  | 20.66
PR | 998 | 02/21/20 | 496 | McCabe, Thomas C |  | 35.8
PR | 998 | 02/21/20 | 496 | McCabe, Thomas C |  | 71.6
PR | 998 | 02/21/20 | 496 | McCabe, Thomas C |  | 11.93
PR | 998 | 02/21/20 | 508 | Roberts, Lake A |  | 22.95
PR | 998 | 02/21/20 | 508 | Roberts, Lake A |  | 53.55
PR | 998 | 02/21/20 | 514 | Sanders, Allen O |  | 43.38
PR | 998 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 16.52
PR | 998 | 02/28/20 | 694 | Cruz Gonzalez, Julio C |  | 46.05
PR | 998 | 02/28/20 | 716 | Hubbard, Robert W |  | 28.92
PR | 998 | 02/28/20 | 737 | Roberts, Lake A |  | 15.3
PR | 998 | 02/28/20 | 743 | Sanders, Allen O |  | 28.92
PR | 998 | 02/28/20 | 748 | Taylor, Evan R |  | 10.1
PR | 998 | 02/28/20 | 754 | Waites, Thaddeus Z |  | 22.49
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 26.85
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/06/20 | 56 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 03/06/20 | 105 | Sanders, Allen O |  | 6.2
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/13/20 | 342 | Hubbard, Robert W |  | 12.39
PR | 998 | 03/13/20 | 369 | Sanders, Allen O |  | 4.13
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/20/20 | 627 | Sanders, Allen O |  | 6.2
PR | 998 | 03/26/20 | 752 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/26/20 | 806 | Sanders, Allen O |  | 8.26
PR | 998 | 03/26/20 | 811 | Taylor, Evan R |  | 32.82
PR | 998 | 03/26/20 | 817 | Waites, Thaddeus Z |  | 48.73
PR | 998 | 05/08/20 | 215 | Sanders, Allen O |  | 8.26
AR | 999 | 09/19/18 | 472 | Blueprint Capital Services, LLC$800 5th |  | -33900 | 037188
AR | 999 | 09/19/18 | 472 | Blueprint Capital Services, LLC$800 5th |  | -7400 | 037188
AR | 999 | 09/19/18 | 472 | Blueprint Capital Services, LLC$800 5th |  | -4500 | 037188
AR | 999 | 10/19/18 | 527 | Blueprint Capital Services, LLC$800 5th |  | -45800 | 037213
AR | 999 | 01/18/19 | 558 | Blueprint Capital Services, LLC$800 5th |  | -12130 | 037276
AR | 999 | 01/18/19 | 558 | Blueprint Capital Services, LLC$800 5th |  | -20785 | 037276
AR | 999 | 03/20/19 | 679 | Blueprint Capital Services, LLC$800 5th |  | -71760 | 037300
AR | 999 | 03/20/19 | 679 | Blueprint Capital Services, LLC$800 5th |  | -12130 | 037300
AR | 999 | 04/19/19 | 611 | Blueprint Capital Services, LLC$800 5th |  | -35880 | 037327
AR | 999 | 04/19/19 | 611 | Blueprint Capital Services, LLC$800 5th |  | -60650 | 037327
AR | 999 | 04/19/19 | 611 | Blueprint Capital Services, LLC$800 5th |  | -24260 | 037327
AR | 999 | 05/20/19 | 506 | Blueprint Capital Services, LLC$800 5th |  | -60650 | 037339
AR | 999 | 05/20/19 | 506 | Blueprint Capital Services, LLC$800 5th |  | -21350 | 037339
AR | 999 | 05/20/19 | 506 | Blueprint Capital Services, LLC$800 5th |  | -2615 | 037339
AR | 999 | 06/19/19 | 612 | Blueprint Capital Services, LLC$800 5th |  | -38430 | 037368
AR | 999 | 06/19/19 | 612 | Blueprint Capital Services, LLC$800 5th |  | -8434 | 037368
AR | 999 | 06/19/19 | 612 | Blueprint Capital Services, LLC$800 5th |  | -2285 | 037368
AR | 999 | 06/19/19 | 612 | Blueprint Capital Services, LLC$800 5th |  | 1300 | 037368
AR | 999 | 07/19/19 | 601 | Blueprint Capital Services, LLC$800 5th |  | -38900 | 037376
AR | 999 | 07/19/19 | 601 | Blueprint Capital Services, LLC$800 5th |  | -18195 | 037376
AR | 999 | 07/19/19 | 601 | Blueprint Capital Services, LLC$800 5th |  | -12810 | 037376
AR | 999 | 07/19/19 | 601 | Blueprint Capital Services, LLC$800 5th |  | -754 | 037376
AR | 999 | 08/15/19 | 752 | Blueprint Capital Services, LLC$800 5th |  | -38900 | 037389
AR | 999 | 08/15/19 | 752 | Blueprint Capital Services, LLC$800 5th |  | -24260 | 037389
AR | 999 | 08/15/19 | 752 | Blueprint Capital Services, LLC$800 5th |  | -6065 | 037389
AR | 999 | 08/15/19 | 752 | Blueprint Capital Services, LLC$800 5th |  | -12810 | 037389
AR | 999 | 09/20/19 | 568 | Blueprint Capital Services, LLC$800 5th |  | -9700 | 037412
AR | 999 | 09/20/19 | 568 | Blueprint Capital Services, LLC$800 5th |  | -23900 | 037412
AR | 999 | 09/20/19 | 568 | Blueprint Capital Services, LLC$800 5th |  | -12130 | 037412
AR | 999 | 09/20/19 | 568 | Blueprint Capital Services, LLC$800 5th |  | -12130 | 037412
AR | 999 | 10/18/19 | 532 | Blueprint Capital Services, LLC$800 5th |  | -11960 | 037419
AR | 999 | 10/18/19 | 532 | Blueprint Capital Services, LLC$800 5th |  | -1023 | 037419
AR | 999 | 11/18/19 | 554 | Blueprint Capital Services, LLC$800 5th |  | -5000 | 037436
AR | 999 | 12/13/19 | 476 | Blueprint Capital Services, LLC$800 5th |  | -38000 | 037452
AR | 999 | 12/13/19 | 476 | Blueprint Capital Services, LLC$800 5th |  | -24900 | 037452
AR | 999 | 12/13/19 | 476 | Blueprint Capital Services, LLC$800 5th |  | -3500 | 037452
AR | 999 | 02/19/20 | 444 | Blueprint Capital Services, LLC$800 5th |  | -9950 | 037479
AR | 999 | 02/19/20 | 444 | Blueprint Capital Services, LLC$800 5th |  | -570 | 037479
GL | 999 | 05/20/20 | 443 | Billing Adj |  | -75971