## 01 Overview
OWP #2055 · Dockside Apartments
Blueprint Capital Services, LLC · 98 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 1315429
Revised budget (expenses) | 972283.38
Forecast net profit | 343145.62
Forecast margin | 26.09%
Progress to Date
Work complete (billed) | 1315429
Retention held | 0
Earned less retention | 1315429
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 53135.72
AP | 424189.14
PR | 499296.62
AR | -1315429

## 02 Job Info
JOB #2055 · BLUEPRINT CAPITAL SERVICES LLC · Dockside Apartments — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract Dockside SC 6505 (Blueprint format).
IDENTITY
OWP Job ID | 2055
Project Name | Dockside Apartments
Site Address | 6860 E Green Lake Way N, Seattle WA 98115
Subcontract Number | Dockside SC 6505 (Blueprint format)
Effective Date | 2018-2019
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Blueprint Capital Services LLC
GC Address | PO Box 16309, Seattle WA 98116
GC Contract Signatory | Blueprint
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Blueprint
Owner Address | PO Box 16309, Seattle WA 98116
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | Not Wrap
Retention | 5% per contract
CONTRACT
Contract Value | $1,142,340 original
CHANGE-EVENT META
Executed CO Count | TBD — see GDrive Change Orders/CO's/
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | (see GDrive)
COR Themes | (see GDrive)
Key RFIs | (see GDrive)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Dockside job ticket 7-21-2020.pdf
GDrive Folder | Job Books - Completed Jobs/2055-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets | 99 | 92 Gerber Maxwell 21-912 + 6 ADA + 1 amenity Toto CST454CEFG
Lavs | 99 | 98 Kohler K-2035-1 + 1 amenity K-5150
Showers | 104 | 92 Best Bath P3838 std + 6 LSS3838B5T Type A
Tubs | 0 | (no tubs in this project — pan-only showers)
Kitchen faucets | 98 | Delta Trinsic 9959-BL-DST matte black
Air gaps | 98 | Delta 72020-BL
Common areas | 4 | 1 ADA toilet + lav + amenity + coffee
Retail bathrooms | 2 | Roughin only
Grease interceptor | 1 | Schier GB250 retail
Water heaters | 4 | Bock OptiTherm OT-199N 99-gallon
Booster pump | 1 | Flowtherm duplex
Hose bibs | 5 | 1 trash + 4 ext (3 ground + 1 upper roof)
VERIFIED MAIN FIXTURE COUNT | 398
Per unit (98): 4.06
AUDIT NOTE (2026-04-25): First-pass count of 515 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 398 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 1142340 | 1315429 | 173089
Executed change orders (net) | 0 | 173089 | 173089
Total contract value | 1142340 | 1488518 | 346178
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 7920 | 8920 | 1582 | 7338 | 0 | 17.74%
101 | Takeoff & Purchase Labor | 13200 | 14700 | 6150.5 | 8549.5 | 0 | 41.84%
110 | Underground Labor | 9150 | 9150 | 11833.5 | -2683.5 | 0 | 129.3%
111 | Garage Labor | 18890 | 21890 | 22091 | -201 | 0 | 100.9%
112 | Canout Labor | 8370 | 9170 | 4742 | 4428 | 0 | 51.71%
120 | Roughin Labor | 143615 | 178365 | 182281.5 | -3916.5 | 0 | 102.2%
130 | Finish Labor | 29055 | 32055 | 32494.5 | -439.5 | 0 | 101.4%
140 | Gas Labor | 9600 | 9600 | 7800 | 1800 | 0 | 81.25%
141 | Water Main/Insulation Lab | 36080 | 39780 | 37064.5 | 2715.5 | 0 | 93.17%
142 | Mech Room Labor | 15600 | 15600 | 28376 | -12776 | 0 | 181.9%
210 | Underground Material | 6825 | 6825 | 5959.91 | 865.09 | 0 | 87.32%
211 | Garage Material | 5175 | 6675 | 28292.22 | -21617.22 | 0 | 423.9%
212 | Canout Material | 7254 | 7654 | 4336.58 | 3317.42 | 0 | 56.66%
220 | Roughin Material | 63421 | 70041 | 84940.23 | -14899.23 | 0 | 121.3%
230 | Finish Material | 238986 | 255066 | 216460.37 | 38605.63 | 0 | 84.86%
240 | Gas Material | 6000 | 6000 | 4654.15 | 1345.85 | 0 | 77.57%
241 | Water Main/Insulation Mat | 33530 | 37230 | 32273.25 | 4956.75 | 0 | 86.69%
242 | Mech Room Material | 16250 | 16250 | 29539.9 | -13289.9 | 0 | 181.8%
600 | Subcontractor | 1000 | 1000 | 9865 | -8865 | 0 | 986.5%
601 | Engineering/Plans | 32000 | 53044 | 43959.25 | 9084.75 | 0 | 82.87%
602 | Rental Equipment | 600 | 600 | 4238 | -3638 | 0 | 706.3%
603 | Permits & Licenses | 9362 | 9362 | 6505 | 2857 | 0 | 69.48%
607 | Other Expenses | 7000 | 7000 | 6301 | 699 | 0 | 90.01%
995 | Payroll Burden | 108867.78 | 130355.28 | 139298.13 | -8942.85 | 0 | 106.9%
997 | Employee Benefits | 0 | 0 | 0 | 0 | 0 | 0%
998 | Payroll Taxes | 22298.22 | 25951.1 | 25582.99 | 368.11 | 0 | 98.58%
TOTAL |  | 850049 | 972283.38 | 976621.48 | -4338.1 | 0 | 100.4%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 339230 | 334415.5 | 4814.5 | 98.58%
Material | 8 | 405741 | 406456.61 | -715.61 | 100.2%
Overhead | 5 | 71006 | 70868.25 | 137.75 | 99.81%
Burden | 2 | 156306.38 | 164881.12 | -8574.74 | 105.5%
TOTAL | 25 | 972283.38 | 976621.48 | -4338.1 | 100.4%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 8920 | 1582 | 7338 | -82.26% | UNDER
101 | Takeoff & Purchase Labor | 14700 | 6150.5 | 8549.5 | -58.16% | UNDER
110 | Underground Labor | 9150 | 11833.5 | -2683.5 | 29.33% | OVER
111 | Garage Labor | 21890 | 22091 | -201 | 0.9182% | ON
112 | Canout Labor | 9170 | 4742 | 4428 | -48.29% | UNDER
120 | Roughin Labor | 178365 | 182281.5 | -3916.5 | 2.196% | ON
130 | Finish Labor | 32055 | 32494.5 | -439.5 | 1.371% | ON
140 | Gas Labor | 9600 | 7800 | 1800 | -18.75% | UNDER
141 | Water Main/Insulation Lab | 39780 | 37064.5 | 2715.5 | -6.826% | ON
142 | Mech Room Labor | 15600 | 28376 | -12776 | 81.9% | CRITICAL
210 | Underground Material | 6825 | 5959.91 | 865.09 | -12.68% | UNDER
211 | Garage Material | 6675 | 28292.22 | -21617.22 | 323.9% | CRITICAL
212 | Canout Material | 7654 | 4336.58 | 3317.42 | -43.34% | UNDER
220 | Roughin Material | 70041 | 84940.23 | -14899.23 | 21.27% | OVER
230 | Finish Material | 255066 | 216460.37 | 38605.63 | -15.14% | UNDER
240 | Gas Material | 6000 | 4654.15 | 1345.85 | -22.43% | UNDER
241 | Water Main/Insulation Mat | 37230 | 32273.25 | 4956.75 | -13.31% | UNDER
242 | Mech Room Material | 16250 | 29539.9 | -13289.9 | 81.78% | CRITICAL
600 | Subcontractor | 1000 | 9865 | -8865 | 886.5% | CRITICAL
601 | Engineering/Plans | 53044 | 43959.25 | 9084.75 | -17.13% | UNDER
602 | Rental Equipment | 600 | 4238 | -3638 | 606.3% | CRITICAL
603 | Permits & Licenses | 9362 | 6505 | 2857 | -30.52% | UNDER
607 | Other Expenses | 7000 | 6301 | 699 | -9.986% | ON
995 | Payroll Burden | 130355.28 | 139298.13 | -8942.85 | 6.86% | ON
998 | Payroll Taxes | 25951.1 | 25582.99 | 368.11 | -1.418% | ON

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 111727.79 | 103 | 26.35%
Keller Supply Company | 77740.41 | 24 | 18.33%
Best Bath Systems | 70452.14 | 4 | 16.62%
California Hydronics Corp | 45310 | 5 | 10.69%
Franklin Engineering | 43959.25 | 17 | 10.37%
Consolidated Supply Co. | 28866.92 | 23 | 6.808%
Ferguson Enterprises, Inc. #3007 | 18312.93 | 15 | 4.319%
Capital One Credit Card | 11123.25 | 47 | 2.623%
Mechanical Resource Services, Inc. | 6500 | 1 | 1.533%
H&E Equipment Services, Inc. | 4238 | 10 | 0.9995%
Chemical Products Company | 3150 | 1 | 0.7429%
Bank of America CC | 2278 | 12 | 0.5373%
A.R. Brown Backflow Testing | 215 | 1 | 0.05071%
ACME Corp | 135 | 1 | 0.03184%
TOTAL AP | 424008.69 | 264

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Trower-Kelly, Fidel D | 1167 | 29404 | 25.1962 | JOURNEYMAN
Cruz Guzman, Joel A | 1122.5 | 39650 | 35.3229 | JOURNEYMAN
Cruz Gonzalez, Julio C | 1117.5 | 34864 | 31.1982 | JOURNEYMAN
Guerrero Espinoza, Mario | 834.5 | 19072 | 22.8544 | JOURNEYMAN
Ascencio, Jose L | 822.5 | 29085 | 35.3617 | JOURNEYMAN
Paco Leyva, Orlando | 735 | 36306 | 49.3959 | LEAD/SUPERVISOR
Balderas Ortiz, Ricardo I | 507 | 20312 | 40.0631 | LEAD/SUPERVISOR
Romero Garza, Jesus I | 387 | 9967 | 25.7545 | JOURNEYMAN
Gonzalez Hernandez, Josue | 312.5 | 12316 | 39.4112 | LEAD/SUPERVISOR
Lopez, Maslin A | 312 | 8106 | 25.9808 | JOURNEYMAN
Cruz Reyes, Jose | 302.5 | 10285 | 34 | JOURNEYMAN
Eliassen, Cory H | 200 | 6888 | 34.44 | JOURNEYMAN
Galdamez, Dagoberto A | 187 | 6699 | 35.8235 | JOURNEYMAN
Herrera Hernandez, Manuel L | 168 | 3192 | 19 | APPRENTICE/HELPER
Mendoza Morales, Jesus A | 168 | 5728 | 34.0952 | JOURNEYMAN
Barnhart, Joseph N | 155.5 | 8734 | 56.1672 | LEAD/SUPERVISOR
Robles Arroyo, Alonso | 152 | 3276 | 21.5526 | JOURNEYMAN
Anderson, Richard P | 137.5 | 6824 | 49.6291 | LEAD/SUPERVISOR
Sanders, Allen O | 132.5 | 7700 | 58.1132 | LEAD/SUPERVISOR
Hubbard, Robert W | 127 | 7066 | 55.6378 | LEAD/SUPERVISOR
Lucas Tzintzun, Rafael | 126.5 | 3289 | 26 | JOURNEYMAN
Martinez Reyes, Juan C | 125 | 4681 | 37.448 | LEAD/SUPERVISOR
Ramos Herrera, Franklin J | 100 | 3468 | 34.68 | JOURNEYMAN
Young, Joshua S | 96 | 1952 | 20.3333 | JOURNEYMAN
Ross, Kelli M | 83 | 3601 | 43.3855 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 76.5 | 4495 | 58.7582 | LEAD/SUPERVISOR
Hawkins, Conor L | 56 | 952 | 17 | APPRENTICE/HELPER
Donelson, Richard T | 47 | 2938 | 62.5106 | LEAD/SUPERVISOR
McCabe, Thomas C | 20 | 840 | 42 | LEAD/SUPERVISOR
Castro Hernandez, Jose A | 16 | 704 | 44 | LEAD/SUPERVISOR
Cortes Sepulveda, Jose R | 14 | 504 | 36 | LEAD/SUPERVISOR
Chevez, Herson G | 13 | 364 | 28 | JOURNEYMAN
Boss, Kyle A | 12 | 46 | 3.8333 | JOURNEYMAN
Barnhart, Thomas L | 8 | 304 | 38 | LEAD/SUPERVISOR
Boss, Benjamin T | 7 | 232 | 33.1429 | JOURNEYMAN
Johnson, Jake E | 6 | 300 | 50 | LEAD/SUPERVISOR
Taylor, Evan R | 5 | 185 | 37 | LEAD/SUPERVISOR
Eisenhauer, Tommy J | 2 | 88 | 44 | LEAD/SUPERVISOR
Reed, Reuben H | 0 | 0 | 0 | OT-ONLY

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 18 | 2509.5 | 117897 | 25.45%
JOURNEYMAN | 18 | 7127 | 212374 | 72.28%
APPRENTICE/HELPER | 2 | 224 | 4144 | 2.272%
OT-ONLY | 1 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 9860
Active workers | 39
Hours per unit (to date) | 100.6
Revenue per labor hour (billed) | 133.4
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 26.09% | 34% | -7.914%
Roughin labor share (code 120) | 52.58% | 45% | 7.579%
Top vendor concentration | 26.35% | 38% | -11.65%
Hours per unit | 100.6173 | 95 | 5.6173

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Underground Labor (110) over revised | ⚠ WATCH | Actual $11,834 vs revised $9,150 (+29%) — monitor
Mech Room Labor (142) CRITICAL overrun | ⚠ WATCH | Actual $28,376 vs revised $15,600 (+82%) — needs immediate attention
Garage Material (211) CRITICAL overrun | ⚠ WATCH | Actual $28,292 vs revised $6,675 (+324%) — needs immediate attention
Roughin Material (220) over revised | ⚠ WATCH | Actual $84,940 vs revised $70,041 (+21%) — monitor
Mech Room Material (242) CRITICAL overrun | ⚠ WATCH | Actual $29,540 vs revised $16,250 (+82%) — needs immediate attention
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $9,865 vs revised $1,000 (+886%) — needs immediate attention
Rental Equipment (602) CRITICAL overrun | ⚠ WATCH | Actual $4,238 vs revised $600 (+606%) — needs immediate attention
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 26% of AP ($111,728) — acceptable
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range
Forecast margin | ✓ OK | 26.1% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 976621.48 | 976621.48 | 0
Revenue billed (AR ·-1) | -1315429 | 1315429 | -2630858
AP source total |  | 424189.14 | —
PR source total |  | 499296.62 | —
GL source total |  | 53135.72 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2055 live project. 17-tab JCR schema on revised budget basis.