## Summary
#2055 · Dockside Apartments
Blueprint Capital Service · 98 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
1315429 | 26.09% | 1315429 | 0
Key facts
Original contract |  | 1142340
Revised contract (CO impact) |  | 1315429
Executed COs (net) |  | 173089
Retention held |  | 0
Revised expense budget |  | 972283.38
Forecast net profit |  | 343145.62
Percent complete |  | 100%
Live signals
Underground Labor (110) over | ⚠ WATCH | Actual $11,834 vs revised $9,150 (+29%) — monitor
Mech Room Labor (142) CRITICAL | ⚠ WATCH | Actual $28,376 vs revised $15,600 (+82%) — needs attention
Garage Material (211) CRITICAL | ⚠ WATCH | Actual $28,292 vs revised $6,675 (+324%) — needs attention
Roughin Material (220) over | ⚠ WATCH | Actual $84,940 vs revised $70,041 (+21%) — monitor
Mech Room Material (242) CRITICAL | ⚠ WATCH | Actual $29,540 vs revised $16,250 (+82%) — needs attention
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $9,865 vs revised $1,000 (+886%) — needs attention
Rental Equipment (602) CRITICAL | ⚠ WATCH | Actual $4,238 vs revised $600 (+606%) — needs attention
Top vendor (Rosen Supply Kirklan) | ✓ OK | 26% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 26.1% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Rosen Supply Kirkland | 103 | 111727.79 | 26.35%
Keller Supply Company | 24 | 77740.41 | 18.33%
Best Bath Systems | 4 | 70452.14 | 16.62%
California Hydronics Corp | 5 | 45310 | 10.69%
Franklin Engineering | 17 | 43959.25 | 10.37%
Consolidated Supply Co. | 23 | 28866.92 | 6.808%

## Transactions
Transactions Detail
JDR source transactions for job #2055 · 2525 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 10/23/20 | 482 | Gerard, Jeffrey S | 1 | 58 | 929042
PR | 100 | 11/06/20 | 59 | Gerard, Jeffrey S | 1 | 58 | 929136
PR | 100 | 12/11/20 | 225 | Gerard, Jeffrey S | 1 | 58 | 929366
PR | 100 | 01/08/21 | 53 | Gerard, Jeffrey S | 1 | 58 | 929604
PR | 100 | 01/29/21 | 433 | Gerard, Jeffrey S | 1 | 58 | 929758
PR | 100 | 02/12/21 | 308 | Gerard, Jeffrey S | 1 | 58 | 929869
PR | 100 | 02/19/21 | 474 | Gerard, Jeffrey S | 1 | 58 | 929927
PR | 100 | 03/05/21 | 108 | Gerard, Jeffrey S | 1 | 58 | 930043
PR | 100 | 03/12/21 | 233 | Gerard, Jeffrey S | 1 | 58 | 930099
PR | 100 | 04/09/21 | 168 | Gerard, Jeffrey S | 1 | 60 | 930346
PR | 100 | 04/23/21 | 467 | Gerard, Jeffrey S | 1 | 60 | 930480
PR | 100 | 04/30/21 | 638 | Gerard, Jeffrey S | 1 | 60 | 930548
PR | 100 | 05/07/21 | 107 | Gerard, Jeffrey S | 1 | 60 | 930620
PR | 100 | 05/14/21 | 311 | Gerard, Jeffrey S | 2 | 120 | 930689
PR | 100 | 05/28/21 | 701 | Gerard, Jeffrey S | 2 | 120 | 930830
PR | 100 | 06/04/21 | 100 | Gerard, Jeffrey S | 1 | 60 | 930905
PR | 100 | 06/18/21 | 476 | Gerard, Jeffrey S | 1 | 60 | 931054
PR | 100 | 06/25/21 | 673 | Gerard, Jeffrey S | 1 | 60 | 931132
PR | 100 | 07/30/21 | 758 | Gerard, Jeffrey S | 1 | 60 | 931514
PR | 100 | 08/20/21 | 662 | Gerard, Jeffrey S | 1 | 60 | 931755
PR | 100 | 09/03/21 | 87 | Gerard, Jeffrey S | 1 | 60 | 931919
PR | 100 | 11/24/21 | 660 | Gerard, Jeffrey S | 1 | 60 | 932997
PR | 100 | 04/01/22 | 109 | Gerard, Jeffrey S | 1 | 60 | 934836
PR | 100 | 04/29/22 | 1111 | Johnson, Jake E | 2 | 100 | 35167
PR | 101 | 10/25/19 | 664 | Donelson, Richard T | 4 | 250 | 925504
PR | 101 | 11/01/19 | 80 | Donelson, Richard T | 1 | 62.5 | 925696
PR | 101 | 11/08/19 | 253 | Donelson, Richard T | 1 | 62.5 | 925772
PR | 101 | 11/15/19 | 512 | Donelson, Richard T | 1 | 62.5 | 925848
PR | 101 | 04/24/20 | 424 | Donelson, Richard T | 2 | 125 | 927628
PR | 101 | 07/24/20 | 449 | Gerard, Jeffrey S | 1 | 58 | 928441
PR | 101 | 07/31/20 | 544 | Gerard, Jeffrey S | 1 | 58 | 928490
PR | 101 | 08/14/20 | 332 | Donelson, Richard T | 3 | 187.5 | 928572
PR | 101 | 08/14/20 | 333 | Gerard, Jeffrey S | 2 | 116 | 928573
PR | 101 | 08/21/20 | 460 | Gerard, Jeffrey S | 1 | 58 | 928614
PR | 101 | 08/28/20 | 604 | Donelson, Richard T | 1 | 62.5 | 928657
PR | 101 | 09/11/20 | 120 | Gerard, Jeffrey S | 1 | 58 | 28754
PR | 101 | 09/18/20 | 331 | Gerard, Jeffrey S | 2 | 116 | 928802
PR | 101 | 09/25/20 | 479 | Gerard, Jeffrey S | 4 | 232 | 928850
PR | 101 | 10/02/20 | 52 | Gerard, Jeffrey S | 2 | 116 | 28601
PR | 101 | 10/09/20 | 199 | Gerard, Jeffrey S | 2 | 116 | 928948
PR | 101 | 10/16/20 | 339 | Donelson, Richard T | 1 | 62.5 | 928993
PR | 101 | 10/16/20 | 340 | Gerard, Jeffrey S | 2 | 116 | 928994
PR | 101 | 10/30/20 | 637 | Gerard, Jeffrey S | 3 | 174 | 929088
PR | 101 | 11/06/20 | 59 | Gerard, Jeffrey S | 2 | 116 | 929136
PR | 101 | 11/13/20 | 231 | Gerard, Jeffrey S | 3 | 174 | 29182
PR | 101 | 11/20/20 | 388 | Donelson, Richard T | 2 | 125 | 26225
PR | 101 | 11/20/20 | 389 | Gerard, Jeffrey S | 2 | 116 | 26226
PR | 101 | 12/04/20 | 51 | Gerard, Jeffrey S | 2 | 116 | 929320
PR | 101 | 12/04/20 | 51 | Gerard, Jeffrey S | 1.5 | 87 | 929320
PR | 101 | 12/11/20 | 224 | Donelson, Richard T | 1 | 62.5 | 929365
PR | 101 | 12/11/20 | 225 | Gerard, Jeffrey S | 1 | 58 | 929366
PR | 101 | 12/18/20 | 387 | Gerard, Jeffrey S | 1 | 58 | 929413
PR | 101 | 12/23/20 | 529 | Gerard, Jeffrey S | 1 | 58 | 929508
PR | 101 | 12/31/20 | 627 | Donelson, Richard T | 1 | 62.5 | 929555
PR | 101 | 12/31/20 | 628 | Gerard, Jeffrey S | 1 | 58 | 929556
PR | 101 | 01/08/21 | 52 | Donelson, Richard T | 1 | 62.5 | 929603
PR | 101 | 01/08/21 | 53 | Gerard, Jeffrey S | 1 | 58 | 929604
PR | 101 | 01/15/21 | 171 | Donelson, Richard T | 2 | 125 | 929656
PR | 101 | 02/05/21 | 122 | Gerard, Jeffrey S | 1 | 58 | 929813
PR | 101 | 03/05/21 | 107 | Donelson, Richard T | 1 | 62.5 | 930042
PR | 101 | 03/12/21 | 233 | Gerard, Jeffrey S | 1 | 58 | 930099
PR | 101 | 04/02/21 | 64 | Donelson, Richard T | 1 | 62.5 | 930283
PR | 101 | 04/16/21 | 315 | Gerard, Jeffrey S | 1 | 60 | 930413
PR | 101 | 04/23/21 | 466 | Donelson, Richard T | 1 | 62.5 | 930479
PR | 101 | 04/23/21 | 467 | Gerard, Jeffrey S | 1 | 60 | 930480
PR | 101 | 05/07/21 | 106 | Donelson, Richard T | 1 | 62.5 | 930619
PR | 101 | 05/07/21 | 107 | Gerard, Jeffrey S | 1 | 60 | 930620
PR | 101 | 05/14/21 | 311 | Gerard, Jeffrey S | 2 | 120 | 930689
PR | 101 | 05/21/21 | 457 | Gerard, Jeffrey S | 3 | 180 | 930758
PR | 101 | 06/04/21 | 99 | Donelson, Richard T | 2 | 125 | 930904
PR | 101 | 07/02/21 | 78 | Donelson, Richard T | 1 | 62.5 | 931201
PR | 101 | 07/09/21 | 176 | Gerard, Jeffrey S | 1 | 60 | 931279
PR | 101 | 07/30/21 | 758 | Gerard, Jeffrey S | 1 | 60 | 931514
PR | 101 | 08/13/21 | 379 | Gerard, Jeffrey S | 1 | 60 | 931673
PR | 101 | 08/20/21 | 662 | Gerard, Jeffrey S | 1 | 60 | 931755
PR | 101 | 08/27/21 | 883 | Gerard, Jeffrey S | 1 | 60 | 931835
PR | 101 | 09/10/21 | 254 | Donelson, Richard T | 1 | 62.5 | 932002
PR | 101 | 10/01/21 | 88 | Donelson, Richard T | 1 | 62.5 | 932258
PR | 101 | 12/17/21 | 603 | Donelson, Richard T | 1 | 62.5 | 933415
PR | 101 | 01/28/22 | 705 | Donelson, Richard T | 1 | 62.5 | 933981
PR | 101 | 02/04/22 | 99 | Donelson, Richard T | 1 | 62.5 | 934078
PR | 101 | 02/18/22 | 577 | Donelson, Richard T | 1 | 62.5 | 934269
PR | 101 | 03/25/22 | 962 | Donelson, Richard T | 1 | 62.5 | 934741
PR | 101 | 04/01/22 | 108 | Donelson, Richard T | 3 | 187.5 | 934835
PR | 101 | 04/08/22 | 276 | Johnson, Jake E | 1 | 50 | 34890
PR | 101 | 04/08/22 | 314 | Donelson, Richard T | 1 | 62.5 | 934928
PR | 101 | 04/15/22 | 561 | Donelson, Richard T | 1 | 62.5 | 935022
PR | 101 | 04/22/22 | 851 | Johnson, Jake E | 1 | 50 | 35075
PR | 101 | 04/22/22 | 889 | Donelson, Richard T | 1 | 62.5 | 935113
PR | 101 | 05/13/22 | 370 | Johnson, Jake E | 1 | 50 | 35344
PR | 101 | 05/20/22 | 681 | Donelson, Richard T | 1 | 62.5 | 935472
PR | 101 | 06/03/22 | 56 | Johnson, Jake E | 1 | 50 | 35615
PR | 101 | 06/03/22 | 93 | Donelson, Richard T | 1 | 62.5 | 935652
PR | 101 | 06/10/22 | 301 | Donelson, Richard T | 4 | 250 | 935740
PR | 110 | 11/06/20 | 15 | Barnhart, Joseph N | 2 | 108 | 29093
PR | 110 | 11/25/20 | 456 | Barnhart, Joseph N | 3 | 162 | 29231
PR | 110 | 12/04/20 | 7 | Barnhart, Joseph N | 19 | 1026 | 29278
PR | 110 | 12/04/20 | 31 | Martinez Reyes, Juan C | 14 | 518 | 29302
PR | 110 | 12/11/20 | 183 | Barnhart, Joseph N | 14 | 756 | 29324
PR | 110 | 12/18/20 | 344 | Barnhart, Joseph N | 2 | 108 | 29370
PR | 110 | 12/23/20 | 485 | Barnhart, Joseph N | 4 | 216 | 29465
PR | 110 | 12/31/20 | 581 | Anderson, Richard P | 16 | 784 | 29509
PR | 110 | 12/31/20 | 585 | Barnhart, Joseph N | 2 | 108 | 29513
PR | 110 | 12/31/20 | 609 | Martinez Reyes, Juan C | 16 | 592 | 29537
PR | 110 | 01/08/21 | 4 | Anderson, Richard P | 28 | 1372 | 29556
PR | 110 | 01/08/21 | 32 | Martinez Reyes, Juan C | 28 | 1036 | 29584
PR | 110 | 01/15/21 | 117 | Anderson, Richard P | 2 | 98 | 29604
PR | 110 | 01/15/21 | 146 | Martinez Reyes, Juan C | 2 | 74 | 29633
PR | 110 | 01/29/21 | 386 | Barnhart, Joseph N | 1 | 54 | 29711
PR | 110 | 02/05/21 | 67 | Anderson, Richard P | 8 | 392 | 29758
PR | 110 | 02/05/21 | 99 | Martinez Reyes, Juan C | 8 | 296 | 29790
PR | 110 | 02/12/21 | 252 | Anderson, Richard P | 15 | 735 | 29813
PR | 110 | 02/12/21 | 285 | Martinez Reyes, Juan C | 4 | 148 | 29846
PR | 110 | 02/19/21 | 416 | Anderson, Richard P | 1.5 | 73.5 | 29869
PR | 110 | 02/26/21 | 593 | Anderson, Richard P | 24 | 1176 | 29929
PR | 110 | 02/26/21 | 597 | Barnhart, Joseph N | 1 | 54 | 29933
PR | 110 | 02/26/21 | 629 | Martinez Reyes, Juan C | 21 | 777 | 29965
PR | 110 | 03/05/21 | 52 | Anderson, Richard P | 14 | 686 | 29987
PR | 110 | 03/05/21 | 87 | Martinez Reyes, Juan C | 4 | 148 | 30022
PR | 110 | 04/16/21 | 253 | Barnhart, Joseph N | 1 | 56 | 30351
PR | 110 | 04/16/21 | 272 | Galdamez, Dagoberto A | 8 | 280 | 30370
PR | 111 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I | 20 | 760 | 30349
PR | 111 | 04/16/21 | 272 | Galdamez, Dagoberto A | 12 | 420 | 30370
PR | 111 | 04/16/21 | 296 | Paco Leyva, Orlando | 15 | 705 | 30394
PR | 111 | 04/23/21 | 402 | Balderas Ortiz, Ricardo I | 16 | 608 | 30415
PR | 111 | 04/23/21 | 415 | Cruz Guzman, Joel A | 36 | 1224 | 30428
PR | 111 | 04/23/21 | 423 | Galdamez, Dagoberto A | 24 | 840 | 30436
PR | 111 | 04/23/21 | 431 | Guerrero Espinoza, Mario | 8 | 176 | 30444
PR | 111 | 04/23/21 | 440 | Lopez, Maslin A | 20 | 480 | 30453
PR | 111 | 04/23/21 | 447 | Paco Leyva, Orlando | 12 | 564 | 30460
PR | 111 | 04/23/21 | 451 | Ramos Herrera, Franklin J | 16 | 528 | 30464
PR | 111 | 04/30/21 | 572 | Balderas Ortiz, Ricardo I | 16 | 608 | 30482
PR | 111 | 04/30/21 | 585 | Cruz Guzman, Joel A | 40 | 1360 | 30495
PR | 111 | 04/30/21 | 593 | Galdamez, Dagoberto A | 40 | 1400 | 30503
PR | 111 | 04/30/21 | 601 | Guerrero Espinoza, Mario | 34 | 748 | 30511
PR | 111 | 04/30/21 | 610 | Lopez, Maslin A | 21 | 504 | 30520
PR | 111 | 04/30/21 | 618 | Paco Leyva, Orlando | 26 | 1222 | 30528
PR | 111 | 05/07/21 | 41 | Barnhart, Joseph N | 2 | 112 | 30554
PR | 111 | 05/07/21 | 51 | Cruz Gonzalez, Julio C | 32 | 960 | 30564
PR | 111 | 05/07/21 | 52 | Cruz Guzman, Joel A | 40 | 1360 | 30565
PR | 111 | 05/07/21 | 60 | Galdamez, Dagoberto A | 4 | 140 | 30573
PR | 111 | 05/07/21 | 68 | Guerrero Espinoza, Mario | 20 | 440 | 30581
PR | 111 | 05/07/21 | 78 | Lopez, Maslin A | 20 | 480 | 30591
PR | 111 | 05/07/21 | 86 | Paco Leyva, Orlando | 12 | 564 | 30599
PR | 111 | 05/07/21 | 90 | Ramos Herrera, Franklin J | 8 | 264 | 30603
PR | 111 | 05/14/21 | 256 | Cruz Guzman, Joel A | 25 | 850 | 30635
PR | 111 | 05/14/21 | 272 | Guerrero Espinoza, Mario | 30 | 660 | 30651
PR | 111 | 05/14/21 | 290 | Paco Leyva, Orlando | 10 | 470 | 30669
PR | 111 | 05/21/21 | 400 | Cruz Gonzalez, Julio C | 4 | 120 | 30702
PR | 111 | 05/21/21 | 401 | Cruz Guzman, Joel A | 32 | 1088 | 30703
PR | 111 | 05/21/21 | 417 | Guerrero Espinoza, Mario | 24 | 528 | 30719
PR | 111 | 05/21/21 | 436 | Paco Leyva, Orlando | 10 | 470 | 30738
PR | 111 | 05/28/21 | 642 | Cruz Guzman, Joel A | 24 | 816 | 30772
PR | 111 | 05/28/21 | 658 | Guerrero Espinoza, Mario | 24 | 528 | 30788
PR | 111 | 05/28/21 | 678 | Paco Leyva, Orlando | 2 | 94 | 30808
PR | 112 | 03/05/21 | 56 | Barnhart, Joseph N | 1 | 54 | 29991
PR | 112 | 03/19/21 | 287 | Anderson, Richard P | 22 | 1122 | 30100
PR | 112 | 03/19/21 | 300 | Cortes Sepulveda, Jose R | 14 | 504 | 30113
PR | 112 | 03/19/21 | 327 | Martinez Reyes, Juan C | 22 | 858 | 30140
PR | 112 | 03/26/21 | 518 | Anderson, Richard P | 6 | 306 | 30161
PR | 112 | 03/26/21 | 522 | Barnhart, Joseph N | 2 | 112 | 30165
PR | 112 | 03/26/21 | 528 | Chevez, Herson G | 8 | 224 | 30171
PR | 112 | 03/26/21 | 558 | Martinez Reyes, Juan C | 6 | 234 | 30201
PR | 112 | 03/26/21 | 562 | Paco Leyva, Orlando | 5 | 235 | 30205
PR | 112 | 04/02/21 | 13 | Chevez, Herson G | 5 | 140 | 30232
PR | 112 | 04/02/21 | 25 | Galdamez, Dagoberto A | 6 | 210 | 30244
PR | 112 | 04/02/21 | 47 | Paco Leyva, Orlando | 13 | 611 | 30266
PR | 112 | 04/02/21 | 50 | Ramos Herrera, Franklin J | 4 | 132 | 30269
PR | 120 | 12/18/20 | 344 | Barnhart, Joseph N | 1 | 54 | 29370
PR | 120 | 01/29/21 | 386 | Barnhart, Joseph N | 1 | 54 | 29711
PR | 120 | 04/02/21 | 7 | Barnhart, Joseph N | 1 | 56 | 30226
PR | 120 | 04/09/21 | 110 | Barnhart, Joseph N | 2 | 112 | 30288
PR | 120 | 04/09/21 | 128 | Galdamez, Dagoberto A | 8 | 280 | 30306
PR | 120 | 04/09/21 | 151 | Paco Leyva, Orlando | 4 | 188 | 30329
PR | 120 | 04/16/21 | 253 | Barnhart, Joseph N | 2 | 112 | 30351
PR | 120 | 04/23/21 | 404 | Barnhart, Joseph N | 4.5 | 252 | 30417
PR | 120 | 04/23/21 | 431 | Guerrero Espinoza, Mario | 16 | 352 | 30444
PR | 120 | 04/23/21 | 440 | Lopez, Maslin A | 14 | 336 | 30453
PR | 120 | 04/23/21 | 447 | Paco Leyva, Orlando | 4 | 188 | 30460
PR | 120 | 04/30/21 | 574 | Barnhart, Joseph N | 2 | 112 | 30484
PR | 120 | 04/30/21 | 601 | Guerrero Espinoza, Mario | 6 | 132 | 30511
PR | 120 | 04/30/21 | 610 | Lopez, Maslin A | 3 | 72 | 30520
PR | 120 | 04/30/21 | 618 | Paco Leyva, Orlando | 6 | 282 | 30528
PR | 120 | 05/07/21 | 41 | Barnhart, Joseph N | 1 | 56 | 30554
PR | 120 | 05/07/21 | 60 | Galdamez, Dagoberto A | 4 | 140 | 30573
PR | 120 | 05/07/21 | 68 | Guerrero Espinoza, Mario | 16 | 352 | 30581
PR | 120 | 05/07/21 | 78 | Lopez, Maslin A | 16 | 384 | 30591
PR | 120 | 05/07/21 | 86 | Paco Leyva, Orlando | 9 | 423 | 30599
PR | 120 | 05/14/21 | 246 | Barnhart, Joseph N | 2 | 112 | 30625
PR | 120 | 05/14/21 | 272 | Guerrero Espinoza, Mario | 6 | 132 | 30651
PR | 120 | 05/14/21 | 290 | Paco Leyva, Orlando | 6 | 282 | 30669
PR | 120 | 05/21/21 | 391 | Barnhart, Joseph N | 1 | 56 | 30693
PR | 120 | 05/21/21 | 394 | Boss, Benjamin T | 2 | 44 | 30696
PR | 120 | 05/21/21 | 395 | Boss, Kyle A | 2 | 46 | 30697
PR | 120 | 05/21/21 | 405 | Eisenhauer, Tommy J | 2 | 88 | 30707
PR | 120 | 05/21/21 | 436 | Paco Leyva, Orlando | 5 | 235 | 30738
PR | 120 | 05/21/21 | 444 | Romero Garza, Jesus I | 40 | 960 | 30746
PR | 120 | 05/21/21 | 451 | Trower-Kelly, Fidel D | 40 | 960 | 30753
PR | 120 | 05/28/21 | 632 | Barnhart, Joseph N | 2 | 112 | 30762
PR | 120 | 05/28/21 | 641 | Cruz Gonzalez, Julio C | 2 | 60 | 30771
PR | 120 | 05/28/21 | 642 | Cruz Guzman, Joel A | 16 | 544 | 30772
PR | 120 | 05/28/21 | 643 | Cruz Reyes, Jose | 32 | 1088 | 30773
PR | 120 | 05/28/21 | 658 | Guerrero Espinoza, Mario | 16 | 352 | 30788
PR | 120 | 05/28/21 | 665 | Hubbard, Robert W | 3 | 165 | 30795
PR | 120 | 05/28/21 | 675 | Mendoza Morales, Jesus A | 40 | 1360 | 30805
PR | 120 | 05/28/21 | 678 | Paco Leyva, Orlando | 4 | 188 | 30808
PR | 120 | 05/28/21 | 687 | Romero Garza, Jesus I | 40 | 960 | 30817
PR | 120 | 05/28/21 | 694 | Trower-Kelly, Fidel D | 40 | 960 | 30824
PR | 120 | 06/04/21 | 26 | Ascencio, Jose L | 32 | 1088 | 30831
PR | 120 | 06/04/21 | 29 | Barnhart, Joseph N | 2 | 112 | 30834
PR | 120 | 06/04/21 | 40 | Cruz Gonzalez, Julio C | 16 | 480 | 30845
PR | 120 | 06/04/21 | 41 | Cruz Guzman, Joel A | 32 | 1088 | 30846
PR | 120 | 06/04/21 | 43 | Cruz Reyes, Jose | 16 | 544 | 30848
PR | 120 | 06/04/21 | 58 | Guerrero Espinoza, Mario | 8 | 176 | 30863
PR | 120 | 06/04/21 | 65 | Hubbard, Robert W | 2 | 110 | 30870
PR | 120 | 06/04/21 | 79 | Paco Leyva, Orlando | 7 | 329 | 30884
PR | 120 | 06/04/21 | 89 | Sanders, Allen O | 1 | 55 | 30894
PR | 120 | 06/04/21 | 94 | Trower-Kelly, Fidel D | 32 | 768 | 30899
PR | 120 | 06/11/21 | 200 | Ascencio, Jose L | 40 | 1360 | 30906
PR | 120 | 06/11/21 | 214 | Cruz Gonzalez, Julio C | 16 | 480 | 30920
PR | 120 | 06/11/21 | 215 | Cruz Guzman, Joel A | 40 | 1360 | 30921
PR | 120 | 06/11/21 | 216 | Cruz Reyes, Jose | 40 | 1360 | 30922
PR | 120 | 06/11/21 | 231 | Guerrero Espinoza, Mario | 32 | 704 | 30937
PR | 120 | 06/11/21 | 251 | Paco Leyva, Orlando | 10 | 470 | 30957
PR | 120 | 06/11/21 | 266 | Trower-Kelly, Fidel D | 40 | 960 | 30972
PR | 120 | 06/18/21 | 402 | Ascencio, Jose L | 24 | 816 | 30980
PR | 120 | 06/18/21 | 405 | Barnhart, Joseph N | 1 | 56 | 30983
PR | 120 | 06/18/21 | 417 | Cruz Guzman, Joel A | 32 | 1088 | 30995
PR | 120 | 06/18/21 | 418 | Cruz Reyes, Jose | 24 | 816 | 30996
PR | 120 | 06/18/21 | 433 | Guerrero Espinoza, Mario | 40 | 880 | 31011
PR | 120 | 06/18/21 | 446 | Lucas Tzintzun, Rafael | 16 | 416 | 31024
PR | 120 | 06/18/21 | 453 | Paco Leyva, Orlando | 18 | 846 | 31031
PR | 120 | 06/18/21 | 463 | Ross, Kelli M | 3 | 129 | 31041
PR | 120 | 06/18/21 | 469 | Trower-Kelly, Fidel D | 40 | 960 | 31047
PR | 120 | 06/25/21 | 597 | Ascencio, Jose L | 40 | 1360 | 31055
PR | 120 | 06/25/21 | 600 | Barnhart, Joseph N | 1 | 56 | 31058
PR | 120 | 06/25/21 | 612 | Cruz Guzman, Joel A | 40 | 1360 | 31070
PR | 120 | 06/25/21 | 613 | Cruz Reyes, Jose | 40 | 1360 | 31071
PR | 120 | 06/25/21 | 628 | Guerrero Espinoza, Mario | 37 | 814 | 31086
PR | 120 | 06/25/21 | 631 | Hawkins, Conor L | 32 | 544 | 31089
PR | 120 | 06/25/21 | 641 | Lucas Tzintzun, Rafael | 32 | 832 | 31099
PR | 120 | 06/25/21 | 648 | Paco Leyva, Orlando | 14 | 658 | 31106
PR | 120 | 06/25/21 | 664 | Trower-Kelly, Fidel D | 40 | 960 | 31122
PR | 120 | 07/02/21 | 6 | Ascencio, Jose L | 38.5 | 1309 | 31129
PR | 120 | 07/02/21 | 9 | Barnhart, Joseph N | 1 | 56 | 31132
PR | 120 | 07/02/21 | 21 | Cruz Guzman, Joel A | 38.5 | 1309 | 31144
PR | 120 | 07/02/21 | 22 | Cruz Reyes, Jose | 38.5 | 1309 | 31145
PR | 120 | 07/02/21 | 37 | Guerrero Espinoza, Mario | 22.5 | 495 | 31160
PR | 120 | 07/02/21 | 38 | Hawkins, Conor L | 24 | 408 | 31161
PR | 120 | 07/02/21 | 48 | Lucas Tzintzun, Rafael | 30.5 | 793 | 31171
PR | 120 | 07/02/21 | 56 | Paco Leyva, Orlando | 15 | 705 | 31179
PR | 120 | 07/02/21 | 72 | Trower-Kelly, Fidel D | 37 | 888 | 31195
PR | 120 | 07/09/21 | 101 | Ascencio, Jose L | 32 | 1088 | 31204
PR | 120 | 07/09/21 | 116 | Cruz Guzman, Joel A | 32 | 1088 | 31219
PR | 120 | 07/09/21 | 117 | Cruz Reyes, Jose | 32 | 1088 | 31220
PR | 120 | 07/09/21 | 132 | Guerrero Espinoza, Mario | 32 | 704 | 31235
PR | 120 | 07/09/21 | 143 | Lucas Tzintzun, Rafael | 32 | 832 | 31246
PR | 120 | 07/09/21 | 151 | Paco Leyva, Orlando | 12 | 564 | 31254
PR | 120 | 07/09/21 | 169 | Trower-Kelly, Fidel D | 16 | 384 | 31272
PR | 120 | 07/16/21 | 319 | Ascencio, Jose L | 40 | 1360 | 31280
PR | 120 | 07/16/21 | 333 | Cruz Gonzalez, Julio C | 4 | 120 | 31294
PR | 120 | 07/16/21 | 334 | Cruz Guzman, Joel A | 40 | 1360 | 31295
PR | 120 | 07/16/21 | 335 | Cruz Reyes, Jose | 40 | 1360 | 31296
PR | 120 | 07/16/21 | 350 | Guerrero Espinoza, Mario | 32 | 704 | 31311
PR | 120 | 07/16/21 | 361 | Lucas Tzintzun, Rafael | 16 | 416 | 31322
PR | 120 | 07/16/21 | 369 | Paco Leyva, Orlando | 15 | 705 | 31330
PR | 120 | 07/16/21 | 387 | Trower-Kelly, Fidel D | 40 | 960 | 31348
PR | 120 | 07/23/21 | 489 | Ascencio, Jose L | 32 | 1088 | 31357
PR | 120 | 07/23/21 | 504 | Cruz Gonzalez, Julio C | 10 | 300 | 31372
PR | 120 | 07/23/21 | 505 | Cruz Guzman, Joel A | 40 | 1360 | 31373
PR | 120 | 07/23/21 | 506 | Cruz Reyes, Jose | 16 | 544 | 31374
PR | 120 | 07/23/21 | 521 | Guerrero Espinoza, Mario | 32 | 704 | 31389
PR | 120 | 07/23/21 | 541 | Paco Leyva, Orlando | 14 | 658 | 31409
PR | 120 | 07/23/21 | 559 | Trower-Kelly, Fidel D | 40 | 960 | 31427
PR | 120 | 07/30/21 | 680 | Ascencio, Jose L | 40 | 1360 | 31436
PR | 120 | 07/30/21 | 696 | Cruz Gonzalez, Julio C | 8 | 240 | 31452
PR | 120 | 07/30/21 | 697 | Cruz Guzman, Joel A | 40 | 1360 | 31453
PR | 120 | 07/30/21 | 698 | Cruz Reyes, Jose | 24 | 816 | 31454
PR | 120 | 07/30/21 | 713 | Guerrero Espinoza, Mario | 40 | 880 | 31469
PR | 120 | 07/30/21 | 734 | Paco Leyva, Orlando | 5 | 235 | 31490
PR | 120 | 07/30/21 | 751 | Trower-Kelly, Fidel D | 32 | 768 | 31507
PR | 120 | 08/06/21 | 40 | Ascencio, Jose L | 40 | 1360 | 31518
PR | 120 | 08/06/21 | 57 | Cruz Guzman, Joel A | 40 | 1360 | 31535
PR | 120 | 08/06/21 | 70 | Gonzalez Hernandez, Josue | 8 | 304 | 31548
PR | 120 | 08/06/21 | 72 | Guerrero Espinoza, Mario | 32 | 704 | 31550
PR | 120 | 08/06/21 | 93 | Paco Leyva, Orlando | 5 | 235 | 31571
PR | 120 | 08/06/21 | 110 | Trower-Kelly, Fidel D | 40 | 960 | 31588
PR | 120 | 08/13/21 | 302 | Ascencio, Jose L | 16 | 544 | 31597
PR | 120 | 08/13/21 | 306 | Barnhart, Joseph N | 5 | 280 | 31601
PR | 120 | 08/13/21 | 319 | Cruz Guzman, Joel A | 16 | 544 | 31614
PR | 120 | 08/13/21 | 334 | Guerrero Espinoza, Mario | 40 | 920 | 31629
PR | 120 | 08/13/21 | 355 | Paco Leyva, Orlando | 11 | 517 | 31650
PR | 120 | 08/13/21 | 371 | Trower-Kelly, Fidel D | 40 | 960 | 31666
PR | 120 | 08/20/21 | 583 | Ascencio, Jose L | 24 | 816 | 31676
PR | 120 | 08/20/21 | 600 | Cruz Guzman, Joel A | 40 | 1360 | 31693
PR | 120 | 08/20/21 | 616 | Guerrero Espinoza, Mario | 40 | 920 | 31709
PR | 120 | 08/20/21 | 638 | Paco Leyva, Orlando | 9 | 423 | 31731
PR | 120 | 08/20/21 | 654 | Trower-Kelly, Fidel D | 24 | 576 | 31747
PR | 120 | 08/27/21 | 804 | Ascencio, Jose L | 40 | 1360 | 31756
PR | 120 | 08/27/21 | 807 | Barnhart, Joseph N | 3 | 168 | 31759
PR | 120 | 08/27/21 | 820 | Cruz Gonzalez, Julio C | 8 | 240 | 31772
PR | 120 | 08/27/21 | 821 | Cruz Guzman, Joel A | 40 | 1360 | 31773
PR | 120 | 08/27/21 | 837 | Guerrero Espinoza, Mario | 40 | 920 | 31789
PR | 120 | 08/27/21 | 844 | Hubbard, Robert W | 2 | 110 | 31796
PR | 120 | 08/27/21 | 858 | Paco Leyva, Orlando | 6 | 282 | 31810
PR | 120 | 08/27/21 | 869 | Ross, Kelli M | 40 | 1720 | 31821
PR | 120 | 08/27/21 | 875 | Trower-Kelly, Fidel D | 40 | 960 | 31827
PR | 120 | 08/27/21 | 881 | Young, Joshua S | 32 | 608 | 31833
PR | 120 | 09/03/21 | 5 | Ascencio, Jose L | 40 | 1360 | 31837
PR | 120 | 09/03/21 | 8 | Barnhart, Joseph N | 5 | 280 | 31840
PR | 120 | 09/03/21 | 22 | Cruz Guzman, Joel A | 32 | 1088 | 31854
PR | 120 | 09/03/21 | 39 | Guerrero Espinoza, Mario | 40 | 920 | 31871
PR | 120 | 09/03/21 | 46 | Hubbard, Robert W | 2 | 110 | 31878
PR | 120 | 09/03/21 | 60 | Paco Leyva, Orlando | 11 | 517 | 31892
PR | 120 | 09/03/21 | 72 | Ross, Kelli M | 24 | 1032 | 31904
PR | 120 | 09/03/21 | 78 | Trower-Kelly, Fidel D | 32 | 768 | 31910
PR | 120 | 09/10/21 | 173 | Ascencio, Jose L | 32 | 1152 | 31921
PR | 120 | 09/10/21 | 176 | Barnhart, Joseph N | 5 | 290 | 31924
PR | 120 | 09/10/21 | 190 | Cruz Guzman, Joel A | 24 | 888 | 31938
PR | 120 | 09/10/21 | 207 | Guerrero Espinoza, Mario | 23 | 575 | 31955
PR | 120 | 09/10/21 | 214 | Hubbard, Robert W | 2 | 112 | 31962
PR | 120 | 09/10/21 | 228 | Paco Leyva, Orlando | 16 | 800 | 31976
PR | 120 | 09/10/21 | 241 | Ross, Kelli M | 16 | 720 | 31989
PR | 120 | 09/10/21 | 247 | Trower-Kelly, Fidel D | 8 | 208 | 31995
PR | 120 | 09/17/21 | 335 | Ascencio, Jose L | 40 | 1440 | 32005
PR | 120 | 09/17/21 | 338 | Barnhart, Joseph N | 6 | 348 | 32008
PR | 120 | 09/17/21 | 351 | Cruz Gonzalez, Julio C | 8 | 256 | 32021
PR | 120 | 09/17/21 | 352 | Cruz Guzman, Joel A | 40 | 1480 | 32022
PR | 120 | 09/17/21 | 367 | Gonzalez Hernandez, Josue | 16 | 640 | 32037
PR | 120 | 09/17/21 | 369 | Guerrero Espinoza, Mario | 40 | 1000 | 32039
PR | 120 | 09/17/21 | 390 | Paco Leyva, Orlando | 8 | 400 | 32060
PR | 120 | 09/17/21 | 409 | Trower-Kelly, Fidel D | 32 | 832 | 32079
PR | 120 | 09/24/21 | 489 | Ascencio, Jose L | 32 | 1152 | 32089
PR | 120 | 09/24/21 | 490 | Balderas Ortiz, Ricardo I | 8 | 320 | 32090
PR | 120 | 09/24/21 | 492 | Barnhart, Joseph N | 9 | 522 | 32092
PR | 120 | 09/24/21 | 505 | Cruz Gonzalez, Julio C | 8 | 256 | 32105
PR | 120 | 09/24/21 | 506 | Cruz Guzman, Joel A | 32 | 1184 | 32106
PR | 120 | 09/24/21 | 516 | Galdamez, Dagoberto A | 8 | 296 | 32116
PR | 120 | 09/24/21 | 521 | Gonzalez Hernandez, Josue | 5.5 | 220 | 32121
PR | 120 | 09/24/21 | 523 | Guerrero Espinoza, Mario | 40 | 1000 | 32123
PR | 120 | 09/24/21 | 534 | Lopez, Maslin A | 8 | 216 | 32134
PR | 120 | 09/24/21 | 540 | Mendoza Morales, Jesus A | 8 | 288 | 32140
PR | 120 | 09/24/21 | 544 | Paco Leyva, Orlando | 19 | 950 | 32144
PR | 120 | 09/24/21 | 551 | Ramos Herrera, Franklin J | 8 | 288 | 32151
PR | 120 | 09/24/21 | 564 | Trower-Kelly, Fidel D | 32 | 832 | 32164
PR | 120 | 09/24/21 | 570 | Young, Joshua S | 8 | 168 | 32170
PR | 120 | 10/01/21 | 6 | Ascencio, Jose L | 8 | 432 | 32176
PR | 120 | 10/01/21 | 6 | Ascencio, Jose L | 32 | 1152 | 32176
PR | 120 | 10/01/21 | 9 | Barnhart, Joseph N | 5 | 290 | 32179
PR | 120 | 10/01/21 | 22 | Cruz Gonzalez, Julio C | 7.5 | 360 | 32192
PR | 120 | 10/01/21 | 22 | Cruz Gonzalez, Julio C | 27 | 864 | 32192
PR | 120 | 10/01/21 | 23 | Cruz Guzman, Joel A | 10 | 555 | 32193
PR | 120 | 10/01/21 | 23 | Cruz Guzman, Joel A | 40 | 1480 | 32193
PR | 120 | 10/01/21 | 40 | Guerrero Espinoza, Mario | 8 | 300 | 32210
PR | 120 | 10/01/21 | 40 | Guerrero Espinoza, Mario | 40 | 1000 | 32210
PR | 120 | 10/01/21 | 61 | Paco Leyva, Orlando | 6 | 450 | 32231
PR | 120 | 10/01/21 | 61 | Paco Leyva, Orlando | 18 | 900 | 32231
PR | 120 | 10/01/21 | 81 | Trower-Kelly, Fidel D | 12 | 468 | 32251
PR | 120 | 10/01/21 | 81 | Trower-Kelly, Fidel D | 40 | 1040 | 32251
PR | 120 | 10/08/21 | 294 | Ascencio, Jose L | 8 | 432 | 32265
PR | 120 | 10/08/21 | 294 | Ascencio, Jose L | 40 | 1440 | 32265
PR | 120 | 10/08/21 | 297 | Barnhart, Joseph N | 7 | 406 | 32268
PR | 120 | 10/08/21 | 311 | Cruz Gonzalez, Julio C | 32 | 1024 | 32282
PR | 120 | 10/08/21 | 312 | Cruz Guzman, Joel A | 38 | 1406 | 32283
PR | 120 | 10/08/21 | 354 | Paco Leyva, Orlando | 24 | 1200 | 32325
PR | 120 | 10/08/21 | 374 | Trower-Kelly, Fidel D | 38 | 988 | 32345
PR | 120 | 10/15/21 | 558 | Ascencio, Jose L | 8 | 432 | 32355
PR | 120 | 10/15/21 | 558 | Ascencio, Jose L | 40 | 1440 | 32355
PR | 120 | 10/15/21 | 561 | Barnhart, Joseph N | 1 | 58 | 32358
PR | 120 | 10/15/21 | 575 | Cruz Gonzalez, Julio C | 30 | 960 | 32372
PR | 120 | 10/15/21 | 576 | Cruz Guzman, Joel A | 8 | 444 | 32373
PR | 120 | 10/15/21 | 576 | Cruz Guzman, Joel A | 40 | 1480 | 32373
PR | 120 | 10/15/21 | 618 | Paco Leyva, Orlando | 4 | 300 | 32415
PR | 120 | 10/15/21 | 618 | Paco Leyva, Orlando | 19 | 950 | 32415
PR | 120 | 10/15/21 | 628 | Robles Arroyo, Alonso | 8 | 252 | 32425
PR | 120 | 10/15/21 | 628 | Robles Arroyo, Alonso | 40 | 840 | 32425
PR | 120 | 10/22/21 | 744 | Ascencio, Jose L | 40 | 1440 | 32448
PR | 120 | 10/22/21 | 748 | Barnhart, Joseph N | 3 | 174 | 32452
PR | 120 | 10/22/21 | 764 | Cruz Guzman, Joel A | 30 | 1110 | 32468
PR | 120 | 10/22/21 | 790 | Herrera Hernandez, Manuel L | 16 | 304 | 32494
PR | 120 | 10/22/21 | 798 | Lopez, Maslin A | 8 | 216 | 32502
PR | 120 | 10/22/21 | 808 | Paco Leyva, Orlando | 17 | 850 | 32512
PR | 120 | 10/22/21 | 815 | Ramos Herrera, Franklin J | 8 | 288 | 32519
PR | 120 | 10/22/21 | 818 | Robles Arroyo, Alonso | 36 | 756 | 32522
PR | 120 | 10/22/21 | 828 | Trower-Kelly, Fidel D | 24 | 624 | 32532
PR | 120 | 10/29/21 | 1002 | Anderson, Richard P | 1 | 79.5 | 32539
PR | 120 | 10/29/21 | 1004 | Ascencio, Jose L | 32 | 1152 | 32541
PR | 120 | 10/29/21 | 1008 | Barnhart, Joseph N | 4 | 232 | 32545
PR | 120 | 10/29/21 | 1024 | Cruz Guzman, Joel A | 40 | 1480 | 32561
PR | 120 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L | 29 | 551 | 32587
PR | 120 | 10/29/21 | 1058 | Lopez, Maslin A | 26 | 702 | 32595
PR | 120 | 10/29/21 | 1067 | Paco Leyva, Orlando | 16 | 800 | 32604
PR | 120 | 10/29/21 | 1077 | Robles Arroyo, Alonso | 32 | 672 | 32614
PR | 120 | 10/29/21 | 1086 | Trower-Kelly, Fidel D | 24 | 624 | 32623
PR | 120 | 11/05/21 | 54 | Barnhart, Joseph N | 2 | 116 | 32636
PR | 120 | 11/05/21 | 69 | Cruz Gonzalez, Julio C | 8 | 256 | 32651
PR | 120 | 11/05/21 | 70 | Cruz Guzman, Joel A | 40 | 1480 | 32652
PR | 120 | 11/05/21 | 83 | Galdamez, Dagoberto A | 8 | 296 | 32665
PR | 120 | 11/05/21 | 97 | Herrera Hernandez, Manuel L | 12 | 228 | 32679
PR | 120 | 11/05/21 | 106 | Lopez, Maslin A | 40 | 1080 | 32688
PR | 120 | 11/05/21 | 115 | Paco Leyva, Orlando | 16 | 800 | 32697
PR | 120 | 11/05/21 | 122 | Ramos Herrera, Franklin J | 16 | 576 | 32704
PR | 120 | 11/05/21 | 125 | Robles Arroyo, Alonso | 8 | 168 | 32707
PR | 120 | 11/12/21 | 266 | Ascencio, Jose L | 16 | 576 | 32728
PR | 120 | 11/12/21 | 269 | Barnhart, Joseph N | 3 | 174 | 32731
PR | 120 | 11/12/21 | 284 | Cruz Gonzalez, Julio C | 14 | 448 | 32746
PR | 120 | 11/12/21 | 285 | Cruz Guzman, Joel A | 16 | 592 | 32747
PR | 120 | 11/12/21 | 297 | Galdamez, Dagoberto A | 24 | 888 | 32759
PR | 120 | 11/12/21 | 311 | Herrera Hernandez, Manuel L | 24 | 456 | 32773
PR | 120 | 11/12/21 | 320 | Lopez, Maslin A | 32 | 864 | 32782
PR | 120 | 11/12/21 | 329 | Paco Leyva, Orlando | 19 | 950 | 32791
PR | 120 | 11/12/21 | 336 | Ramos Herrera, Franklin J | 16 | 576 | 32798
PR | 120 | 11/19/21 | 434 | Ascencio, Jose L | 16 | 576 | 32820
PR | 120 | 11/19/21 | 437 | Barnhart, Joseph N | 1 | 58 | 32823
PR | 120 | 11/19/21 | 452 | Cruz Gonzalez, Julio C | 36 | 1152 | 32838
PR | 120 | 11/19/21 | 453 | Cruz Guzman, Joel A | 16 | 592 | 32839
PR | 120 | 11/19/21 | 465 | Galdamez, Dagoberto A | 16 | 592 | 32851
PR | 120 | 11/19/21 | 479 | Herrera Hernandez, Manuel L | 16 | 304 | 32865
PR | 120 | 11/19/21 | 488 | Lopez, Maslin A | 40 | 1080 | 32874
PR | 120 | 11/19/21 | 497 | Paco Leyva, Orlando | 17 | 850 | 32883
PR | 120 | 11/24/21 | 592 | Cruz Gonzalez, Julio C | 38 | 1216 | 32929
PR | 120 | 11/24/21 | 626 | Lopez, Maslin A | 38 | 1026 | 32963
PR | 120 | 11/24/21 | 635 | Paco Leyva, Orlando | 16 | 800 | 32972
PR | 120 | 11/24/21 | 658 | Young, Joshua S | 16 | 336 | 32995
PR | 120 | 12/03/21 | 29 | Cruz Gonzalez, Julio C | 32 | 1024 | 33019
PR | 120 | 12/03/21 | 64 | Lopez, Maslin A | 8 | 216 | 33054
PR | 120 | 12/03/21 | 73 | Paco Leyva, Orlando | 14 | 700 | 33063
PR | 120 | 12/10/21 | 210 | Cruz Gonzalez, Julio C | 16 | 512 | 33109
PR | 120 | 12/10/21 | 256 | Paco Leyva, Orlando | 17 | 850 | 33155
PR | 120 | 12/17/21 | 532 | Cruz Gonzalez, Julio C | 6 | 192 | 33344
PR | 120 | 12/17/21 | 545 | Galdamez, Dagoberto A | 5 | 185 | 33357
PR | 120 | 12/17/21 | 578 | Paco Leyva, Orlando | 8 | 400 | 33390
PR | 120 | 12/23/21 | 741 | Barnhart, Joseph N | 1 | 58 | 33423
PR | 120 | 12/23/21 | 757 | Cruz Gonzalez, Julio C | 16 | 512 | 33439
PR | 120 | 12/23/21 | 803 | Paco Leyva, Orlando | 24 | 1200 | 33485
PR | 120 | 12/30/21 | 998 | Paco Leyva, Orlando | 5 | 250 | 33578
PR | 120 | 01/07/22 | 30 | Barnhart, Joseph N | 1 | 58 | 33610
PR | 120 | 01/07/22 | 73 | Herrera Hernandez, Manuel L | 16 | 304 | 33653
PR | 120 | 01/07/22 | 92 | Paco Leyva, Orlando | 15 | 750 | 33672
PR | 120 | 01/14/22 | 274 | Herrera Hernandez, Manuel L | 16 | 304 | 33746
PR | 120 | 01/14/22 | 292 | Paco Leyva, Orlando | 9 | 450 | 33764
PR | 120 | 01/21/22 | 476 | Paco Leyva, Orlando | 3 | 150 | 33858
PR | 120 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I | 12 | 480 | 33890
PR | 120 | 01/28/22 | 643 | Galdamez, Dagoberto A | 4 | 148 | 33920
PR | 120 | 01/28/22 | 677 | Paco Leyva, Orlando | 9 | 450 | 33954
PR | 120 | 01/28/22 | 684 | Ramos Herrera, Franklin J | 4 | 144 | 33961
PR | 120 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I | 8 | 320 | 33988
PR | 120 | 02/11/22 | 215 | Balderas Ortiz, Ricardo I | 4 | 160 | 34083
PR | 120 | 02/11/22 | 217 | Barnhart, Joseph N | 2 | 116 | 34085
PR | 120 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I | 4 | 160 | 34180
PR | 120 | 02/18/22 | 488 | Barnhart, Joseph N | 2 | 116 | 34181
PR | 120 | 02/18/22 | 549 | Paco Leyva, Orlando | 1 | 50 | 34242
PR | 120 | 02/25/22 | 709 | Barnhart, Joseph N | 1 | 58 | 34274
PR | 120 | 02/25/22 | 769 | Paco Leyva, Orlando | 3 | 150 | 34334
PR | 120 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I | 5 | 200 | 34367
PR | 120 | 03/11/22 | 404 | Paco Leyva, Orlando | 3 | 150 | 34526
PR | 120 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I | 6 | 240 | 34558
PR | 120 | 03/18/22 | 689 | Paco Leyva, Orlando | 8 | 400 | 34622
PR | 120 | 04/01/22 | 66 | Hubbard, Robert W | 1 | 56 | 34793
PR | 120 | 04/01/22 | 82 | Paco Leyva, Orlando | 1 | 50 | 34809
PR | 120 | 04/15/22 | 535 | Paco Leyva, Orlando | 2 | 100 | 34996
PR | 120 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I | 4 | 160 | 35026
PR | 120 | 04/22/22 | 834 | Gonzalez Hernandez, Josue | 4 | 160 | 35058
PR | 120 | 04/22/22 | 847 | Hubbard, Robert W | 2 | 112 | 35071
PR | 120 | 04/22/22 | 863 | Paco Leyva, Orlando | 2 | 100 | 35087
PR | 120 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I | 4 | 160 | 35118
PR | 120 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue | 6 | 240 | 35150
PR | 120 | 04/29/22 | 1107 | Hubbard, Robert W | 2 | 112 | 35163
PR | 120 | 04/29/22 | 1124 | Paco Leyva, Orlando | 1 | 50 | 35180
PR | 120 | 05/06/22 | 118 | Gonzalez Hernandez, Josue | 3 | 120 | 35239
PR | 120 | 05/06/22 | 131 | Hubbard, Robert W | 3 | 168 | 35252
PR | 130 | 11/24/21 | 650 | Sanders, Allen O | 2 | 114 | 32987
PR | 130 | 12/03/21 | 88 | Sanders, Allen O | 6.5 | 370.5 | 33078
PR | 130 | 02/18/22 | 564 | Sanders, Allen O | 1 | 57 | 34257
PR | 130 | 02/25/22 | 763 | McCabe, Thomas C | 18 | 756 | 34328
PR | 130 | 02/25/22 | 780 | Romero Garza, Jesus I | 22 | 572 | 34345
PR | 130 | 02/25/22 | 784 | Sanders, Allen O | 5 | 285 | 34349
PR | 130 | 02/25/22 | 789 | Trower-Kelly, Fidel D | 24 | 624 | 34354
PR | 130 | 03/04/22 | 101 | McCabe, Thomas C | 2 | 84 | 34425
PR | 130 | 03/04/22 | 118 | Romero Garza, Jesus I | 40 | 1040 | 34442
PR | 130 | 03/04/22 | 122 | Sanders, Allen O | 2 | 114 | 34446
PR | 130 | 03/04/22 | 127 | Trower-Kelly, Fidel D | 40 | 1040 | 34451
PR | 130 | 03/11/22 | 415 | Romero Garza, Jesus I | 40 | 1040 | 34537
PR | 130 | 03/11/22 | 419 | Sanders, Allen O | 7 | 399 | 34541
PR | 130 | 03/11/22 | 424 | Trower-Kelly, Fidel D | 40 | 1040 | 34546
PR | 130 | 03/18/22 | 700 | Romero Garza, Jesus I | 24 | 624 | 34633
PR | 130 | 03/18/22 | 704 | Sanders, Allen O | 5.5 | 313.5 | 34637
PR | 130 | 03/18/22 | 709 | Trower-Kelly, Fidel D | 32 | 832 | 34642
PR | 130 | 03/25/22 | 946 | Romero Garza, Jesus I | 40 | 1040 | 34725
PR | 130 | 03/25/22 | 950 | Sanders, Allen O | 7 | 399 | 34729
PR | 130 | 03/25/22 | 954 | Trower-Kelly, Fidel D | 39 | 1014 | 34733
PR | 130 | 04/01/22 | 92 | Romero Garza, Jesus I | 40 | 1040 | 34819
PR | 130 | 04/01/22 | 96 | Sanders, Allen O | 3 | 171 | 34823
PR | 130 | 04/01/22 | 100 | Trower-Kelly, Fidel D | 32 | 832 | 34827
PR | 130 | 04/08/22 | 247 | Eliassen, Cory H | 24 | 816 | 34861
PR | 130 | 04/08/22 | 298 | Romero Garza, Jesus I | 24 | 624 | 34912
PR | 130 | 04/08/22 | 302 | Sanders, Allen O | 4.5 | 256.5 | 34916
PR | 130 | 04/08/22 | 306 | Trower-Kelly, Fidel D | 32 | 832 | 34920
PR | 130 | 04/15/22 | 476 | Barnhart, Thomas L | 8 | 304 | 34937
PR | 130 | 04/15/22 | 494 | Eliassen, Cory H | 20 | 680 | 34955
PR | 130 | 04/15/22 | 506 | Gonzalez Hernandez, Josue | 2 | 80 | 34967
PR | 130 | 04/15/22 | 519 | Hubbard, Robert W | 2 | 112 | 34980
PR | 130 | 04/15/22 | 549 | Sanders, Allen O | 12 | 684 | 35010
PR | 130 | 04/15/22 | 553 | Trower-Kelly, Fidel D | 24 | 624 | 35014
PR | 130 | 04/22/22 | 822 | Eliassen, Cory H | 32 | 1088 | 35046
PR | 130 | 04/22/22 | 873 | Romero Garza, Jesus I | 16 | 416 | 35097
PR | 130 | 04/22/22 | 877 | Sanders, Allen O | 14 | 798 | 35101
PR | 130 | 04/22/22 | 881 | Trower-Kelly, Fidel D | 32 | 832 | 35105
PR | 130 | 04/29/22 | 1082 | Eliassen, Cory H | 36 | 1224 | 35138
PR | 130 | 04/29/22 | 1134 | Romero Garza, Jesus I | 40 | 1040 | 35190
PR | 130 | 04/29/22 | 1137 | Sanders, Allen O | 8.5 | 484.5 | 35193
PR | 130 | 04/29/22 | 1141 | Trower-Kelly, Fidel D | 40 | 1040 | 35197
PR | 130 | 05/06/22 | 107 | Eliassen, Cory H | 40 | 1360 | 35228
PR | 130 | 05/06/22 | 158 | Romero Garza, Jesus I | 16 | 416 | 35279
PR | 130 | 05/06/22 | 160 | Sanders, Allen O | 13 | 741 | 35281
PR | 130 | 05/06/22 | 164 | Trower-Kelly, Fidel D | 32 | 832 | 35285
PR | 130 | 05/13/22 | 342 | Eliassen, Cory H | 40 | 1360 | 35316
PR | 130 | 05/13/22 | 396 | Sanders, Allen O | 16 | 912 | 35370
PR | 130 | 05/20/22 | 616 | Eliassen, Cory H | 1 | 35 | 35407
PR | 130 | 05/20/22 | 669 | Sanders, Allen O | 6.5 | 383.5 | 35460
PR | 130 | 05/27/22 | 937 | Sanders, Allen O | 5 | 295 | 35547
PR | 130 | 06/10/22 | 289 | Sanders, Allen O | 4 | 236 | 35728
PR | 130 | 06/17/22 | 537 | Sanders, Allen O | 2 | 118 | 35817
PR | 130 | 07/01/22 | 31 | Eliassen, Cory H | 2 | 70 | 35941
PR | 140 | 05/07/21 | 51 | Cruz Gonzalez, Julio C | 8 | 240 | 30564
PR | 140 | 05/14/21 | 255 | Cruz Gonzalez, Julio C | 24 | 720 | 30634
PR | 140 | 05/14/21 | 256 | Cruz Guzman, Joel A | 15 | 510 | 30635
PR | 140 | 05/14/21 | 272 | Guerrero Espinoza, Mario | 4 | 88 | 30651
PR | 140 | 05/14/21 | 288 | Mendoza Morales, Jesus A | 8 | 272 | 30667
PR | 140 | 05/14/21 | 290 | Paco Leyva, Orlando | 4 | 188 | 30669
PR | 140 | 05/21/21 | 401 | Cruz Guzman, Joel A | 8 | 272 | 30703
PR | 140 | 05/21/21 | 436 | Paco Leyva, Orlando | 2 | 94 | 30738
PR | 140 | 06/11/21 | 201 | Balderas Ortiz, Ricardo I | 8 | 304 | 30907
PR | 140 | 06/11/21 | 256 | Ramos Herrera, Franklin J | 8 | 264 | 30962
PR | 140 | 08/13/21 | 318 | Cruz Gonzalez, Julio C | 8 | 240 | 31613
PR | 140 | 08/13/21 | 332 | Gonzalez Hernandez, Josue | 4 | 152 | 31627
PR | 140 | 10/22/21 | 764 | Cruz Guzman, Joel A | 2 | 74 | 32468
PR | 140 | 10/22/21 | 808 | Paco Leyva, Orlando | 2 | 100 | 32512
PR | 140 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C | 8 | 256 | 32560
PR | 140 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L | 8 | 152 | 32587
PR | 140 | 10/29/21 | 1058 | Lopez, Maslin A | 4 | 108 | 32595
PR | 140 | 10/29/21 | 1067 | Paco Leyva, Orlando | 7 | 350 | 32604
PR | 140 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I | 4 | 160 | 34367
PR | 140 | 03/04/22 | 107 | Paco Leyva, Orlando | 4 | 200 | 34431
PR | 140 | 03/25/22 | 936 | Paco Leyva, Orlando | 2 | 100 | 34715
PR | 140 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I | 4 | 160 | 35026
PR | 140 | 04/22/22 | 834 | Gonzalez Hernandez, Josue | 9 | 360 | 35058
PR | 140 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I | 22 | 880 | 35118
PR | 140 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue | 4 | 160 | 35150
PR | 140 | 04/29/22 | 1107 | Hubbard, Robert W | 6.5 | 364 | 35163
PR | 140 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I | 12 | 480 | 35210
PR | 140 | 05/06/22 | 118 | Gonzalez Hernandez, Josue | 4 | 160 | 35239
PR | 140 | 05/06/22 | 131 | Hubbard, Robert W | 7 | 392 | 35252
PR | 141 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I | 4 | 152 | 30349
PR | 141 | 04/16/21 | 272 | Galdamez, Dagoberto A | 4 | 140 | 30370
PR | 141 | 04/30/21 | 610 | Lopez, Maslin A | 8 | 192 | 30520
PR | 141 | 04/30/21 | 618 | Paco Leyva, Orlando | 2 | 94 | 30528
PR | 141 | 04/30/21 | 622 | Ramos Herrera, Franklin J | 8 | 264 | 30532
PR | 141 | 05/07/21 | 68 | Guerrero Espinoza, Mario | 4 | 88 | 30581
PR | 141 | 05/07/21 | 78 | Lopez, Maslin A | 4 | 96 | 30591
PR | 141 | 05/14/21 | 255 | Cruz Gonzalez, Julio C | 16 | 480 | 30634
PR | 141 | 05/14/21 | 288 | Mendoza Morales, Jesus A | 32 | 1088 | 30667
PR | 141 | 05/21/21 | 400 | Cruz Gonzalez, Julio C | 36 | 1080 | 30702
PR | 141 | 05/21/21 | 417 | Guerrero Espinoza, Mario | 8 | 176 | 30719
PR | 141 | 05/21/21 | 434 | Mendoza Morales, Jesus A | 40 | 1360 | 30736
PR | 141 | 05/28/21 | 641 | Cruz Gonzalez, Julio C | 38 | 1140 | 30771
PR | 141 | 06/11/21 | 214 | Cruz Gonzalez, Julio C | 16 | 480 | 30920
PR | 141 | 06/11/21 | 247 | Mendoza Morales, Jesus A | 24 | 816 | 30953
PR | 141 | 06/18/21 | 410 | Castro Hernandez, Jose A | 16 | 704 | 30988
PR | 141 | 06/18/21 | 416 | Cruz Gonzalez, Julio C | 24 | 720 | 30994
PR | 141 | 06/18/21 | 449 | Mendoza Morales, Jesus A | 16 | 544 | 31027
PR | 141 | 06/18/21 | 453 | Paco Leyva, Orlando | 2 | 94 | 31031
PR | 141 | 06/25/21 | 611 | Cruz Gonzalez, Julio C | 40 | 1200 | 31069
PR | 141 | 06/25/21 | 648 | Paco Leyva, Orlando | 3 | 141 | 31106
PR | 141 | 07/02/21 | 20 | Cruz Gonzalez, Julio C | 30.5 | 915 | 31143
PR | 141 | 07/02/21 | 56 | Paco Leyva, Orlando | 1 | 47 | 31179
PR | 141 | 07/09/21 | 115 | Cruz Gonzalez, Julio C | 32 | 960 | 31218
PR | 141 | 07/09/21 | 151 | Paco Leyva, Orlando | 1 | 47 | 31254
PR | 141 | 07/16/21 | 333 | Cruz Gonzalez, Julio C | 12 | 360 | 31294
PR | 141 | 07/16/21 | 369 | Paco Leyva, Orlando | 4 | 188 | 31330
PR | 141 | 07/23/21 | 504 | Cruz Gonzalez, Julio C | 27.5 | 825 | 31372
PR | 141 | 07/23/21 | 541 | Paco Leyva, Orlando | 1 | 47 | 31409
PR | 141 | 07/30/21 | 696 | Cruz Gonzalez, Julio C | 24 | 720 | 31452
PR | 141 | 07/30/21 | 734 | Paco Leyva, Orlando | 8 | 376 | 31490
PR | 141 | 08/06/21 | 56 | Cruz Gonzalez, Julio C | 32 | 960 | 31534
PR | 141 | 08/06/21 | 70 | Gonzalez Hernandez, Josue | 16 | 608 | 31548
PR | 141 | 08/13/21 | 318 | Cruz Gonzalez, Julio C | 8 | 240 | 31613
PR | 141 | 08/13/21 | 332 | Gonzalez Hernandez, Josue | 4 | 152 | 31627
PR | 141 | 08/13/21 | 341 | Hubbard, Robert W | 3 | 165 | 31636
PR | 141 | 08/20/21 | 599 | Cruz Gonzalez, Julio C | 40 | 1200 | 31692
PR | 141 | 08/27/21 | 820 | Cruz Gonzalez, Julio C | 24 | 720 | 31772
PR | 141 | 09/03/21 | 21 | Cruz Gonzalez, Julio C | 16 | 480 | 31853
PR | 141 | 09/03/21 | 37 | Gonzalez Hernandez, Josue | 4 | 152 | 31869
PR | 141 | 09/10/21 | 189 | Cruz Gonzalez, Julio C | 32 | 1024 | 31937
PR | 141 | 09/10/21 | 247 | Trower-Kelly, Fidel D | 8 | 208 | 31995
PR | 141 | 09/17/21 | 351 | Cruz Gonzalez, Julio C | 24 | 768 | 32021
PR | 141 | 09/24/21 | 505 | Cruz Gonzalez, Julio C | 32 | 1024 | 32105
PR | 141 | 09/24/21 | 506 | Cruz Guzman, Joel A | 8 | 296 | 32106
PR | 141 | 09/24/21 | 544 | Paco Leyva, Orlando | 2 | 100 | 32144
PR | 141 | 10/01/21 | 22 | Cruz Gonzalez, Julio C | 6 | 288 | 32192
PR | 141 | 10/01/21 | 22 | Cruz Gonzalez, Julio C | 13 | 416 | 32192
PR | 141 | 10/01/21 | 61 | Paco Leyva, Orlando | 3 | 225 | 32231
PR | 141 | 10/01/21 | 81 | Trower-Kelly, Fidel D | 4 | 156 | 32251
PR | 141 | 10/22/21 | 763 | Cruz Gonzalez, Julio C | 32 | 1024 | 32467
PR | 141 | 10/22/21 | 808 | Paco Leyva, Orlando | 1 | 50 | 32512
PR | 141 | 10/22/21 | 818 | Robles Arroyo, Alonso | 4 | 84 | 32522
PR | 141 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C | 32 | 1024 | 32560
PR | 141 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L | 3 | 57 | 32587
PR | 141 | 10/29/21 | 1058 | Lopez, Maslin A | 2 | 54 | 32595
PR | 141 | 10/29/21 | 1067 | Paco Leyva, Orlando | 2 | 100 | 32604
PR | 141 | 11/05/21 | 69 | Cruz Gonzalez, Julio C | 32 | 1024 | 32651
PR | 141 | 11/05/21 | 97 | Herrera Hernandez, Manuel L | 12 | 228 | 32679
PR | 141 | 11/05/21 | 115 | Paco Leyva, Orlando | 6 | 300 | 32697
PR | 141 | 11/05/21 | 125 | Robles Arroyo, Alonso | 24 | 504 | 32707
PR | 141 | 11/05/21 | 140 | Young, Joshua S | 24 | 504 | 32722
PR | 141 | 11/12/21 | 284 | Cruz Gonzalez, Julio C | 24 | 768 | 32746
PR | 141 | 11/12/21 | 311 | Herrera Hernandez, Manuel L | 8 | 152 | 32773
PR | 141 | 11/12/21 | 329 | Paco Leyva, Orlando | 2 | 100 | 32791
PR | 141 | 11/19/21 | 520 | Young, Joshua S | 16 | 336 | 32906
PR | 141 | 12/03/21 | 73 | Paco Leyva, Orlando | 2 | 100 | 33063
PR | 141 | 12/10/21 | 210 | Cruz Gonzalez, Julio C | 24 | 768 | 33109
PR | 141 | 12/17/21 | 532 | Cruz Gonzalez, Julio C | 24 | 768 | 33344
PR | 141 | 12/17/21 | 545 | Galdamez, Dagoberto A | 8 | 296 | 33357
PR | 141 | 12/17/21 | 578 | Paco Leyva, Orlando | 11 | 550 | 33390
PR | 141 | 12/30/21 | 998 | Paco Leyva, Orlando | 3 | 150 | 33578
PR | 141 | 01/28/22 | 643 | Galdamez, Dagoberto A | 4 | 148 | 33920
PR | 141 | 01/28/22 | 677 | Paco Leyva, Orlando | 4 | 200 | 33954
PR | 141 | 01/28/22 | 684 | Ramos Herrera, Franklin J | 4 | 144 | 33961
PR | 141 | 02/18/22 | 549 | Paco Leyva, Orlando | 1 | 50 | 34242
PR | 141 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I | 2 | 80 | 34840
PR | 141 | 04/08/22 | 259 | Gonzalez Hernandez, Josue | 6 | 240 | 34873
PR | 141 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I | 8 | 480 | 35210
PR | 141 | 05/06/22 | 95 | Boss, Kyle A | 5 | 195 | 35216
PR | 141 | 05/06/22 | 107 | Eliassen, Cory H | 5 | 255 | 35228
PR | 141 | 05/06/22 | 148 | Paco Leyva, Orlando | 8 | 600 | 35269
PR | 141 | 05/06/22 | 158 | Romero Garza, Jesus I | 5 | 195 | 35279
PR | 141 | 05/06/22 | 160 | Sanders, Allen O | 4 | 342 | 35281
PR | 141 | 05/06/22 | 160 | Sanders, Allen O | 3 | 171 | 35281
PR | 141 | 05/06/22 | 163 | Taylor, Evan R | 5 | 185 | 35284
PR | 141 | 05/06/22 | 164 | Trower-Kelly, Fidel D | 5 | 130 | 35285
PR | 141 | 05/13/22 | 328 | Boss, Benjamin T | 5 | 187.5 | 35302
PR | 141 | 05/13/22 | 329 | Boss, Kyle A | 5 | -195 | 35303
PR | 142 | 06/04/21 | 65 | Hubbard, Robert W | 1 | 55 | 30870
PR | 142 | 07/02/21 | 42 | Hubbard, Robert W | 2 | 110 | 31165
PR | 142 | 07/23/21 | 527 | Hubbard, Robert W | 2 | 110 | 31395
PR | 142 | 08/06/21 | 79 | Hubbard, Robert W | 3 | 165 | 31557
PR | 142 | 08/13/21 | 341 | Hubbard, Robert W | 3 | 165 | 31636
PR | 142 | 08/20/21 | 614 | Gonzalez Hernandez, Josue | 16 | 608 | 31707
PR | 142 | 08/20/21 | 623 | Hubbard, Robert W | 4 | 220 | 31716
PR | 142 | 08/27/21 | 835 | Gonzalez Hernandez, Josue | 40 | 1520 | 31787
PR | 142 | 08/27/21 | 844 | Hubbard, Robert W | 16 | 880 | 31796
PR | 142 | 09/03/21 | 46 | Hubbard, Robert W | 3 | 165 | 31878
PR | 142 | 09/10/21 | 205 | Gonzalez Hernandez, Josue | 16 | 640 | 31953
PR | 142 | 09/17/21 | 367 | Gonzalez Hernandez, Josue | 24 | 960 | 32037
PR | 142 | 09/17/21 | 376 | Hubbard, Robert W | 2 | 112 | 32046
PR | 142 | 09/24/21 | 521 | Gonzalez Hernandez, Josue | 32 | 1280 | 32121
PR | 142 | 09/24/21 | 530 | Hubbard, Robert W | 3 | 168 | 32130
PR | 142 | 10/22/21 | 794 | Hubbard, Robert W | 1 | 56 | 32498
PR | 142 | 11/05/21 | 101 | Hubbard, Robert W | 2 | 112 | 32683
PR | 142 | 12/10/21 | 194 | Barnhart, Joseph N | 1 | 58 | 33093
PR | 142 | 01/07/22 | 77 | Hubbard, Robert W | 2 | 112 | 33657
PR | 142 | 01/14/22 | 229 | Balderas Ortiz, Ricardo I | 20 | 800 | 33701
PR | 142 | 01/14/22 | 274 | Herrera Hernandez, Manuel L | 8 | 152 | 33746
PR | 142 | 01/14/22 | 278 | Hubbard, Robert W | 1.5 | 84 | 33750
PR | 142 | 01/14/22 | 292 | Paco Leyva, Orlando | 4 | 200 | 33764
PR | 142 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I | 24 | 960 | 33890
PR | 142 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I | 12 | 480 | 33988
PR | 142 | 02/04/22 | 72 | Paco Leyva, Orlando | 1 | 50 | 34051
PR | 142 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I | 4 | 160 | 34180
PR | 142 | 02/25/22 | 708 | Balderas Ortiz, Ricardo I | 4 | 160 | 34273
PR | 142 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I | 4 | 160 | 34367
PR | 142 | 03/11/22 | 340 | Balderas Ortiz, Ricardo I | 20 | 800 | 34462
PR | 142 | 03/11/22 | 341 | Barnhart, Joseph N | 2 | 116 | 34463
PR | 142 | 03/11/22 | 387 | Hubbard, Robert W | 3 | 168 | 34509
PR | 142 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I | 34 | 1360 | 34558
PR | 142 | 03/18/22 | 672 | Hubbard, Robert W | 1 | 56 | 34605
PR | 142 | 03/18/22 | 689 | Paco Leyva, Orlando | 1 | 50 | 34622
PR | 142 | 03/25/22 | 874 | Balderas Ortiz, Ricardo I | 34 | 1360 | 34653
PR | 142 | 03/25/22 | 875 | Barnhart, Joseph N | 6 | 348 | 34654
PR | 142 | 03/25/22 | 919 | Hubbard, Robert W | 2 | 112 | 34698
PR | 142 | 03/25/22 | 936 | Paco Leyva, Orlando | 2 | 100 | 34715
PR | 142 | 04/01/22 | 20 | Balderas Ortiz, Ricardo I | 39 | 1560 | 34747
PR | 142 | 04/01/22 | 66 | Hubbard, Robert W | 1 | 56 | 34793
PR | 142 | 04/01/22 | 82 | Paco Leyva, Orlando | 1 | 50 | 34809
PR | 142 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I | 34 | 1360 | 34840
PR | 142 | 04/08/22 | 259 | Gonzalez Hernandez, Josue | 22 | 880 | 34873
PR | 142 | 04/08/22 | 272 | Hubbard, Robert W | 1 | 56 | 34886
PR | 142 | 04/08/22 | 288 | Paco Leyva, Orlando | 3 | 150 | 34902
PR | 142 | 04/15/22 | 474 | Balderas Ortiz, Ricardo I | 40 | 1600 | 34935
PR | 142 | 04/15/22 | 475 | Barnhart, Joseph N | 2 | 116 | 34936
PR | 142 | 04/15/22 | 506 | Gonzalez Hernandez, Josue | 22 | 880 | 34967
PR | 142 | 04/15/22 | 519 | Hubbard, Robert W | 10 | 560 | 34980
PR | 142 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I | 31 | 1240 | 35026
PR | 142 | 04/22/22 | 834 | Gonzalez Hernandez, Josue | 20 | 800 | 35058
PR | 142 | 04/22/22 | 847 | Hubbard, Robert W | 17 | 952 | 35071
PR | 142 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I | 14 | 560 | 35118
PR | 142 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue | 18 | 720 | 35150
PR | 142 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I | 18 | 720 | 35210
PR | 142 | 05/06/22 | 118 | Gonzalez Hernandez, Josue | 7 | 280 | 35239
PR | 142 | 05/06/22 | 131 | Hubbard, Robert W | 1 | 56 | 35252
PR | 142 | 05/13/22 | 323 | Balderas Ortiz, Ricardo I | 4 | 160 | 35297
PR | 142 | 05/13/22 | 366 | Hubbard, Robert W | 8 | 448 | 35340
GL | 210 | 12/03/20 | 74 | Req 7486 |  | 258.65
AP | 210 | 12/08/20 | 114 | Rosen Supply Kirkland |  | 2072.91 | 4286007-00
AP | 210 | 01/07/21 | 192 | Rosen Supply Kirkland |  | 930.47 | 4290408-00
AP | 210 | 01/13/21 | 107 | Rosen Supply Kirkland |  | 1351.26 | 4286007-01
AP | 210 | 01/13/21 | 108 | Rosen Supply Kirkland |  | 185.36 | 4290298-00
GL | 210 | 01/25/21 | 343 | Req 7547 |  | 217.72
AP | 210 | 01/31/21 | 458 | Rosen Supply Kirkland |  | 382.11 | 4290765-00
AP | 210 | 02/02/21 | 34 | Capital One Credit Card |  | 30.24 | 121020JB
AP | 210 | 02/02/21 | 35 | Capital One Credit Card |  | 84.68 | 121420JB
AP | 210 | 02/22/21 | 513 | Rosen Supply Kirkland |  | 15.61 | 4291873-00
GL | 210 | 02/25/21 | 662 | Richard Anderson |  | 17.89
AP | 210 | 03/24/21 | 486 | Rosen Supply Kirkland |  | 33.74 | 4292454-00
GL | 210 | 08/18/21 | 528 | Req 7772 |  | 181.59
GL | 211 | 03/31/21 | 709 | Req 7656 |  | 416.1
AP | 211 | 05/11/21 | 183 | Rosen Supply Kirkland |  | 11388.31 | 4288137-00
AP | 211 | 05/11/21 | 214 | Rosen Supply Kirkland |  | 1629.99 | 4295044-00
AP | 211 | 05/17/21 | 333 | Rosen Supply Kirkland |  | 1864.7 | 4295178-00
AP | 211 | 05/17/21 | 334 | Rosen Supply Kirkland |  | 143.18 | 4295232-00
AP | 211 | 05/18/21 | 350 | Rosen Supply Kirkland |  | 1205.79 | 4295390-00
AP | 211 | 06/02/21 | 17 | Rosen Supply Kirkland |  | 2539.67 | 4295592-00
AP | 211 | 07/26/21 | 662 | Rosen Supply Kirkland |  | 2835.42 | 4297883-00
GL | 211 | 08/18/21 | 530 | Req 7770 |  | 6149.43
GL | 211 | 08/30/21 | 925 | Req 7819 |  | 104.85
GL | 211 | 10/20/21 | 705 | Req 7967 |  | 195.52
AP | 211 | 10/27/21 | 996 | Rosen Supply Kirkland |  | 156.66 | 4302176-00
GL | 211 | 04/26/22 | 936 | Req 8123 |  | 526.28
GL | 211 | 04/27/22 | 997 | Req 8139 |  | -751.94
GL | 211 | 06/08/22 | 183 | Req 8382 |  | -111.74
GL | 212 | 03/29/21 | 646 | Req 7655 |  | 3544.14
AP | 212 | 04/27/21 | 540 | Capital One Credit Card |  | 43.67 | 031421JB2
GL | 212 | 08/18/21 | 529 | Req 7771 |  | 860.78
GL | 212 | 04/27/22 | 998 | Req 8143 |  | -112.01
GL | 220 | 01/25/21 | 341 | Req 7549 |  | 109.78
AP | 220 | 03/26/21 | 605 | Consolidated Supply Co. |  | 918.4 | S010192423.001
GL | 220 | 03/31/21 | 708 | Req 7657 |  | 402.68
GL | 220 | 06/07/21 | 112 | Req 7706 |  | -69.57
AP | 220 | 06/07/21 | 133 | Rosen Supply Kirkland |  | 34.88 | 4295784-00
AP | 220 | 06/07/21 | 156 | Rosen Supply Kirkland |  | 2071.06 | 4288253-00
AP | 220 | 06/08/21 | 194 | Rosen Supply Kirkland |  | 6219.65 | 4295268-00
AP | 220 | 06/15/21 | 334 | Rosen Supply Kirkland |  | 996.35 | 4296508-00
AP | 220 | 06/16/21 | 380 | Rosen Supply Kirkland |  | 4736.09 | 4288248-00
AP | 220 | 06/16/21 | 381 | Rosen Supply Kirkland |  | 1767.9 | 4288254-00
AP | 220 | 06/16/21 | 382 | Rosen Supply Kirkland |  | 1370.18 | 4288255-00
AP | 220 | 06/25/21 | 310 | Rosen Supply Kirkland |  | 10937.46 | 4296097-00
AP | 220 | 06/25/21 | 311 | Rosen Supply Kirkland |  | 239.07 | 4296277-00
GL | 220 | 06/25/21 | 684 | Req 7723 |  | -744.9
AP | 220 | 06/29/21 | 744 | Capital One Credit Card |  | 7.99 | 051321JB
AP | 220 | 06/30/21 | 757 | Rosen Supply Kirkland |  | 1223.14 | 4297095-00
AP | 220 | 07/17/21 | 440 | Rosen Supply Kirkland |  | 5514 | 4297342-00
AP | 220 | 07/17/21 | 450 | Rosen Supply Kirkland |  | 2262 | 4297544-00
AP | 220 | 07/27/21 | 673 | Rosen Supply Kirkland |  | 58.7 | 4298059-00
AP | 220 | 07/28/21 | 778 | Rosen Supply Kirkland |  | 640.5 | 4295270-00
AP | 220 | 07/28/21 | 779 | Rosen Supply Kirkland |  | 292.6 | 4295271-00
AP | 220 | 07/28/21 | 780 | Rosen Supply Kirkland |  | 290.8 | 4298122-00
AP | 220 | 08/05/21 | 22 | Rosen Supply Kirkland |  | 517.98 | 4296097-01
AP | 220 | 08/05/21 | 23 | Rosen Supply Kirkland |  | 377.2 | 4296508-01
AP | 220 | 08/05/21 | 24 | Rosen Supply Kirkland |  | 268 | 4297342-01
AP | 220 | 08/05/21 | 37 | Rosen Supply Kirkland |  | 2992.57 | 4298360-00
AP | 220 | 08/09/21 | 193 | Rosen Supply Kirkland |  | 1023.31 | 4298569-00
GL | 220 | 08/18/21 | 522 | Req 7767 |  | 3141.58
GL | 220 | 08/18/21 | 531 | Req 7769 |  | 1065.41
GL | 220 | 08/18/21 | 532 | Req 7768 |  | 3455.89
AP | 220 | 08/18/21 | 572 | Rosen Supply Kirkland |  | 4378.8 | 4299476-00
AP | 220 | 08/23/21 | 757 | Rosen Supply Kirkland |  | 359.66 | 4295270-01
AP | 220 | 08/23/21 | 772 | Rosen Supply Kirkland |  | 1158 | 4299855-00
GL | 220 | 08/27/21 | 898 | Req 7816 |  | 280.65
GL | 220 | 09/02/21 | 110 | Req 7869 |  | 313.7
AP | 220 | 09/15/21 | 323 | Rosen Supply Kirkland |  | 209.33 | 4300141-00
GL | 220 | 09/23/21 | 475 | Req 7919 |  | 530.13
GL | 220 | 09/23/21 | 476 | Req 7918 |  | 1298.27
AP | 220 | 10/01/21 | 102 | Rosen Supply Kirkland |  | 1170.21 | 4300994-00
AP | 220 | 10/01/21 | 116 | Rosen Supply Kirkland |  | 645.39 | 4301113-00
AP | 220 | 10/01/21 | 122 | Rosen Supply Kirkland |  | 1261.49 | 4301142-00
AP | 220 | 10/01/21 | 123 | Rosen Supply Kirkland |  | 379.25 | 4301203-00
AP | 220 | 10/01/21 | 435 | Rosen Supply Kirkland |  | 128.6 | 4301267-00
AP | 220 | 10/01/21 | 446 | Rosen Supply Kirkland |  | 61.21 | 4301333-00
AP | 220 | 10/12/21 | 507 | Rosen Supply Kirkland |  | 66.77 | 4298837-00
AP | 220 | 10/13/21 | 519 | Rosen Supply Kirkland |  | 16.5 | 4301461-00
GL | 220 | 10/18/21 | 659 | Req 7965 |  | 1921.31
AP | 220 | 10/18/21 | 693 | Rosen Supply Kirkland |  | 971.12 | 4301492-00
AP | 220 | 10/18/21 | 694 | Rosen Supply Kirkland |  | 292.46 | 4301576-00
AP | 220 | 10/20/21 | 714 | Rosen Supply Kirkland |  | 284.62 | 4301616-00
AP | 220 | 10/22/21 | 868 | Rosen Supply Kirkland |  | 247.64 | 4301704-00
AP | 220 | 10/22/21 | 890 | Rosen Supply Kirkland |  | 520.41 | 4301855-00
AP | 220 | 10/29/21 | 1114 | Rosen Supply Kirkland |  | 330.26 | 4302255-00
AP | 220 | 11/05/21 | 151 | Capital One Credit Card |  | 44.59 | 090821JB
AP | 220 | 11/05/21 | 158 | Capital One Credit Card |  | 24.81 | 091621JB3
AP | 220 | 11/30/21 | 779 | Capital One Credit Card |  | 13.13 | 102821JB2
AP | 220 | 11/30/21 | 784 | Capital One Credit Card |  | 2.73 | 110221JB
AP | 220 | 11/30/21 | 785 | Capital One Credit Card |  | 9.86 | 110221JB2
AP | 220 | 12/08/21 | 164 | Rosen Supply Kirkland |  | 559.2 | 4303222-00
AP | 220 | 12/08/21 | 176 | Rosen Supply Kirkland |  | 9.92 | 4303308-00
AP | 220 | 12/08/21 | 177 | Rosen Supply Kirkland |  | 209.7 | 4303374-00
AP | 220 | 12/10/21 | 350 | Rosen Supply Kirkland |  | 5219.49 | 4295270-02
AP | 220 | 12/10/21 | 351 | Rosen Supply Kirkland |  | 5927.05 | 4295271-01
AP | 220 | 12/11/21 | 292 | Rosen Supply Kirkland |  | 73.88 | 4303464-00
AP | 220 | 01/12/22 | 200 | Rosen Supply Kirkland |  | 112.08 | 4304699-00
AP | 220 | 01/14/22 | 349 | Capital One Credit Card |  | 12.68 | 121721JB
AP | 220 | 02/15/22 | 455 | Rosen Supply Kirkland |  | 312.13 | 4305679-00
AP | 220 | 03/02/22 | 2 | Rosen Supply Kirkland |  | 48.68 | 4306032-00
AP | 220 | 03/08/22 | 231 | Rosen Supply Kirkland |  | 285.22 | 4306705-00
AP | 220 | 03/17/22 | 610 | Rosen Supply Kirkland |  | 26.35 | 4306705-01
AP | 220 | 03/22/22 | 855 | Rosen Supply Kirkland |  | 231.45 | 4307535-00
AP | 220 | 04/18/22 | 666 | Rosen Supply Kirkland |  | 10.7 | 4306705-02
GL | 220 | 04/21/22 | 790 | Req 8104 |  | -1243.04
GL | 220 | 04/26/22 | 928 | Req 8131 |  | 79.08
GL | 220 | 04/26/22 | 937 | Req 8122 |  | 124.2
GL | 220 | 04/26/22 | 938 | Req 8121 |  | 7916.29
GL | 220 | 04/27/22 | 1002 | Req 8135 |  | -3191.99
GL | 220 | 04/27/22 | 1004 | Req 8137 |  | -363.49
AP | 220 | 05/03/22 | 35 | Rosen Supply Kirkland |  | 83.86 | 4309154-00
GL | 220 | 06/08/22 | 184 | Req 8381 |  | -60.71
AP | 230 | 12/30/20 | 647 | Keller Supply Company |  | 2758.11 | S014901133.002
GL | 230 | 01/25/21 | 342 | Req 7548 |  | 472.14
GL | 230 | 03/26/21 | 592 | Req 7650 |  | -64.13
GL | 230 | 03/31/21 | 707 | Req 7658 |  | 122.26
GL | 230 | 06/07/21 | 113 | Req 7705 |  | -120.86
AP | 230 | 06/08/21 | 172 | Rosen Supply Kirkland |  | 3287.54 | 4290510-00
AP | 230 | 06/30/21 | 769 | Best Bath Systems |  | 24659.58 | 30646
AP | 230 | 07/14/21 | 298 | California Hydronics Corp |  | 23008 | SIN089735
AP | 230 | 07/14/21 | 299 | California Hydronics Corp |  | 20008 | SIN089737
AP | 230 | 07/24/21 | 603 | Best Bath Systems |  | 16162.08 | 31226
AP | 230 | 08/10/21 | 238 | Best Bath Systems |  | 16162.08 | 31963
AP | 230 | 08/11/21 | 273 | Keller Supply Company |  | 2945.38 | S015250031.001
GL | 230 | 08/18/21 | 527 | Req 7773 |  | 5790.41
GL | 230 | 08/30/21 | 924 | Req 7820 |  | 694.72
AP | 230 | 08/31/21 | 955 | Best Bath Systems |  | 13468.4 | 32583
GL | 230 | 09/02/21 | 111 | Req 7868 |  | 44.98
AP | 230 | 09/21/21 | 450 | California Hydronics Corp |  | 552 | SIN095959
GL | 230 | 09/23/21 | 477 | Req 7917 |  | 2400.01
GL | 230 | 09/24/21 | 580 | Req 7923 |  | 251.38
AP | 230 | 09/27/21 | 707 | Rosen Supply Kirkland |  | 616.23 | 4300770-00
GL | 230 | 10/18/21 | 658 | Req 7966 |  | 50.87
AP | 230 | 11/30/21 | 812 | ACME Corp |  | 135 | S3943953.001
AP | 230 | 12/30/21 | 1054 | California Hydronics Corp |  | 840 | SIN105933
AP | 230 | 03/08/22 | 238 | Rosen Supply Kirkland |  | 318.76 | 4306781-00
AP | 230 | 03/09/22 | 291 | Keller Supply Company |  | 14186.51 | S020271909.001
AP | 230 | 03/09/22 | 307 | Keller Supply Company |  | 14186.51 | S020275275.001
AP | 230 | 03/09/22 | 308 | Keller Supply Company |  | 14186.51 | S020282194.001
AP | 230 | 03/14/22 | 479 | Keller Supply Company |  | 13010.51 | S020292606.001
AP | 230 | 03/14/22 | 496 | Keller Supply Company |  | 2061.34 | S015462455.001
AP | 230 | 03/14/22 | 497 | Keller Supply Company |  | 5367.32 | S015463099.001
AP | 230 | 03/17/22 | 611 | Rosen Supply Kirkland |  | 38.49 | 4306781-01
AP | 230 | 03/22/22 | 810 | Capital One Credit Card |  | 96.53 | 022422A
AP | 230 | 03/23/22 | 861 | Capital One Credit Card |  | 23.7 | 030222A
AP | 230 | 04/01/22 | 7 | Keller Supply Company |  | 276.42 | S015463099.002
AP | 230 | 04/05/22 | 142 | Rosen Supply Kirkland |  | 32.56 | 4307760-00
AP | 230 | 04/15/22 | 585 | Capital One Credit Card |  | 53.64 | 032122A2
AP | 230 | 04/15/22 | 599 | Capital One Credit Card |  | 51.12 | 032422JB1
AP | 230 | 04/15/22 | 605 | Capital One Credit Card |  | 14 | 033122JB
AP | 230 | 04/19/22 | 704 | Rosen Supply Kirkland |  | 29.63 | 4308498-00
GL | 230 | 04/26/22 | 930 | Req 8129 |  | 1270.4
GL | 230 | 04/26/22 | 933 | Req 8126 |  | 2071.77
GL | 230 | 04/26/22 | 934 | Req 8125 |  | 6157.05
GL | 230 | 04/27/22 | 1005 | Req 8140 |  | -455
AP | 230 | 05/03/22 | 26 | Keller Supply Company |  | 513.32 | S020479440.001
AP | 230 | 05/03/22 | 27 | Keller Supply Company |  | 1625.51 | S020479675.001
AP | 230 | 05/03/22 | 38 | Keller Supply Company |  | 85.55 | S015461265.004
AP | 230 | 05/03/22 | 39 | Keller Supply Company |  | 427.77 | S015462455.003
AP | 230 | 05/04/22 | 59 | Keller Supply Company |  | 385.61 | S020467160.001
AP | 230 | 05/04/22 | 60 | Keller Supply Company |  | 257.07 | S020467193.001
AP | 230 | 05/04/22 | 61 | Keller Supply Company |  | 2442.18 | S020467205.001
AP | 230 | 05/09/22 | 244 | Keller Supply Company |  | 257.07 | S015461265.002
AP | 230 | 05/09/22 | 245 | Keller Supply Company |  | 513.73 | S015462455.004
AP | 230 | 05/09/22 | 246 | Keller Supply Company |  | 3251.66 | S015463099.005
AP | 230 | 05/09/22 | 247 | Keller Supply Company |  | 167.59 | S020504196.001
AP | 230 | 05/18/22 | 515 | Capital One Credit Card |  | 17.59 | 042522A
AP | 230 | 05/20/22 | 769 | California Hydronics Corp |  | 902 | SIN119032
GL | 230 | 05/25/22 | 781 | Req 8296 |  | 208.34
GL | 230 | 06/08/22 | 181 | Req 8384 |  | -493.85
AP | 230 | 06/14/22 | 384 | Keller Supply Company |  | -1675.85 | S020504213.001
AP | 230 | 06/21/22 | 640 | Capital One Credit Card |  | 28.73 | 051922A
AP | 230 | 06/22/22 | 737 | Keller Supply Company |  | 324.4 | S020648727.001
AP | 240 | 05/24/21 | 538 | Rosen Supply Kirkland |  | 783 | 4295278-00
AP | 240 | 06/14/21 | 290 | Rosen Supply Kirkland |  | 159.04 | 4296163-00
GL | 240 | 08/18/21 | 526 | Req 7774 |  | 471.61
AP | 240 | 08/20/21 | 717 | Rosen Supply Kirkland |  | 104.82 | 4299618-00
AP | 240 | 09/14/21 | 314 | Rosen Supply Kirkland |  | 128.87 | 4300140-00
GL | 240 | 09/24/21 | 581 | Req 7922 |  | 31.01
AP | 240 | 10/01/21 | 101 | Rosen Supply Kirkland |  | 228.89 | 4300981-00
AP | 240 | 10/07/21 | 275 | Keller Supply Company |  | 144.34 | S015941544.001
AP | 240 | 10/28/21 | 1140 | Rosen Supply Kirkland |  | 286.37 | 4302338-00
AP | 240 | 11/03/21 | 36 | Rosen Supply Kirkland |  | 98.26 | 4302559-00
AP | 240 | 11/16/21 | 406 | Keller Supply Company |  | 41.85 | S016113275.001
AP | 240 | 11/16/21 | 411 | Rosen Supply Kirkland |  | 54.91 | 4302712-00
AP | 240 | 02/14/22 | 351 | Rosen Supply Kirkland |  | 174.01 | 4305381-00
AP | 240 | 02/15/22 | 454 | Rosen Supply Kirkland |  | 31.28 | 4305381-01
AP | 240 | 02/15/22 | 456 | Rosen Supply Kirkland |  | 403.59 | 4305680-00
AP | 240 | 04/20/22 | 740 | Rosen Supply Kirkland |  | 64.59 | 4308739-00
GL | 240 | 04/26/22 | 932 | Req 8127 |  | 678.12
AP | 240 | 04/26/22 | 967 | Rosen Supply Kirkland |  | 53.95 | 4308895-00
GL | 240 | 04/27/22 | 992 | Req 8148 |  | -173.18
GL | 240 | 04/27/22 | 1001 | Req 8132 |  | 1002.13
AP | 240 | 05/09/22 | 237 | Ferguson Enterprises, Inc. #3007 |  | 112.09 | 0418205
AP | 240 | 05/16/22 | 463 | Rosen Supply Kirkland |  | 1 | 281
GL | 240 | 05/25/22 | 780 | Req 8297 |  | 429.6
GL | 240 | 06/08/22 | 187 | Req 8378 |  | -324.66
GL | 240 | 06/08/22 | 188 | Req 8377 |  | -356.24
AP | 241 | 11/30/20 | 536 | Consolidated Supply Co. |  | 275.98 | S010051329.001
GL | 241 | 12/03/20 | 78 | Req 7463 |  | -223.5
AP | 241 | 05/11/21 | 220 | Consolidated Supply Co. |  | 10816.84 | S010247875.001
AP | 241 | 05/11/21 | 221 | Consolidated Supply Co. |  | 565.96 | S010247875.002
AP | 241 | 05/26/21 | 612 | Consolidated Supply Co. |  | 231.59 | S010290146.001
AP | 241 | 06/11/21 | 282 | Consolidated Supply Co. |  | 2231.41 | S010305938.001
AP | 241 | 06/30/21 | 795 | Consolidated Supply Co. |  | 168.1 | S010338274.001
AP | 241 | 07/17/21 | 423 | Consolidated Supply Co. |  | 45.34 | S010354916.001
AP | 241 | 07/17/21 | 424 | Consolidated Supply Co. |  | 115.22 | S010354916.002
AP | 241 | 07/17/21 | 425 | Consolidated Supply Co. |  | 58.63 | S010357350.002
AP | 241 | 07/17/21 | 426 | Consolidated Supply Co. |  | 390.4 | S010357350.001
AP | 241 | 07/17/21 | 436 | Consolidated Supply Co. |  | 33.17 | S010357350.003
AP | 241 | 07/26/21 | 636 | Consolidated Supply Co. |  | 252.57 | S010369356.001
AP | 241 | 08/05/21 | 140 | Consolidated Supply Co. |  | 33.17 | S010378069.001
AP | 241 | 08/05/21 | 141 | Consolidated Supply Co. |  | -33.17 | S010378069.002
GL | 241 | 08/18/21 | 523 | Req 7777 |  | 1325.48
GL | 241 | 08/18/21 | 524 | Req 7776 |  | 4559.78
AP | 241 | 08/19/21 | 667 | Consolidated Supply Co. |  | 170.94 | S010430430.001
AP | 241 | 09/10/21 | 288 | Consolidated Supply Co. |  | 490.9 | S010445682.001
AP | 241 | 09/10/21 | 289 | Consolidated Supply Co. |  | 352.95 | S010455894.001
GL | 241 | 09/23/21 | 474 | Req 7920 |  | 336.64
AP | 241 | 10/05/21 | 235 | Consolidated Supply Co. |  | 619.1 | S010457852.001
AP | 241 | 10/05/21 | 236 | Consolidated Supply Co. |  | 1007.41 | S010478730.001
GL | 241 | 10/20/21 | 704 | Req 7968 |  | 185.39
AP | 241 | 10/28/21 | 1146 | Rosen Supply Kirkland |  | 1726.11 | 4302163-00
AP | 241 | 11/05/21 | 176 | Rosen Supply Kirkland |  | 2871.6 | 4302536-00
AP | 241 | 11/30/21 | 824 | Rosen Supply Kirkland |  | 1019.04 | 4303021-00
AP | 241 | 12/07/21 | 153 | Rosen Supply Kirkland |  | 712.8 | 4303114-00
AP | 241 | 12/27/21 | 909 | Rosen Supply Kirkland |  | 460.8 | 4304260-00
AP | 241 | 04/20/22 | 739 | Rosen Supply Kirkland |  | 220.8 | 4308734-00
GL | 241 | 04/26/22 | 931 | Req 8128 |  | 1688.02
GL | 241 | 04/27/22 | 995 | Req 8145 |  | 332.1
GL | 241 | 04/27/22 | 1000 | Req 8138 |  | -668.6
GL | 241 | 06/08/22 | 182 | Req 8383 |  | -99.72
AP | 242 | 08/08/21 | 155 | Ferguson Enterprises, Inc. #3007 |  | 7008.34 | 9526128
AP | 242 | 08/08/21 | 156 | Ferguson Enterprises, Inc. #3007 |  | 777.54 | 9526128-1
AP | 242 | 08/09/21 | 183 | Consolidated Supply Co. |  | 9254.6 | S010386800.001
AP | 242 | 08/09/21 | 184 | Consolidated Supply Co. |  | 813.42 | S010386800.002
GL | 242 | 08/18/21 | 525 | Req 7775 |  | 779.82
AP | 242 | 08/19/21 | 677 | Ferguson Enterprises, Inc. #3007 |  | 4069.31 | 9616801
AP | 242 | 08/19/21 | 678 | Ferguson Enterprises, Inc. #3007 |  | 333.7 | 9616801-1
GL | 242 | 08/30/21 | 926 | Req 7818 |  | 567.44
GL | 242 | 09/02/21 | 112 | Req 7867 |  | 409.29
AP | 242 | 09/13/21 | 297 | Ferguson Enterprises, Inc. #3007 |  | 857.11 | 9664026
AP | 242 | 09/17/21 | 627 | Ferguson Enterprises, Inc. #3007 |  | 754.02 | 9691068
AP | 242 | 09/17/21 | 628 | Ferguson Enterprises, Inc. #3007 |  | 255.11 | 9697222
AP | 242 | 09/17/21 | 629 | Ferguson Enterprises, Inc. #3007 |  | -632.01 | CM043230
GL | 242 | 09/23/21 | 473 | Req 7921 |  | 381.28
AP | 242 | 10/06/21 | 253 | Consolidated Supply Co. |  | 53.99 | S010429425.001
AP | 242 | 10/06/21 | 262 | Ferguson Enterprises, Inc. #3007 |  | 1604.2 | 9743263
AP | 242 | 10/20/21 | 713 | Rosen Supply Kirkland |  | 32.52 | 4301609-00
AP | 242 | 01/31/22 | 748 | Rosen Supply Kirkland |  | 677.44 | 4304889-00
AP | 242 | 03/15/22 | 540 | Ferguson Enterprises, Inc. #3007 |  | 2572.39 | 0271888
AP | 242 | 03/30/22 | 1065 | Ferguson Enterprises, Inc. #3007 |  | 261.45 | 0301895
AP | 242 | 04/12/22 | 420 | Ferguson Enterprises, Inc. #3007 |  | 222.57 | 0344312
AP | 242 | 04/19/22 | 729 | Rosen Supply Kirkland |  | 587.44 | 4308602-00
AP | 242 | 04/20/22 | 737 | Rosen Supply Kirkland |  | 45.18 | 4308602-01
AP | 242 | 04/20/22 | 738 | Rosen Supply Kirkland |  | 10.7 | 4308602-02
AP | 242 | 04/20/22 | 741 | Rosen Supply Kirkland |  | 243.45 | 4308740-00
GL | 242 | 04/26/22 | 929 | Req 8130 |  | 248.53
GL | 242 | 04/26/22 | 935 | Req 8124 |  | 1624.93
GL | 242 | 04/27/22 | 996 | Req 8144 |  | 485.56
GL | 242 | 04/27/22 | 999 | Req 8142 |  | -110.88
GL | 242 | 04/27/22 | 1006 | Req 8141 |  | -1492.51
AP | 242 | 04/27/22 | 1019 | Rosen Supply Kirkland |  | 62.07 | 4309089-00
AP | 242 | 05/03/22 | 15 | Ferguson Enterprises, Inc. #3007 |  | 55.83 | 0386299
AP | 242 | 05/03/22 | 16 | Ferguson Enterprises, Inc. #3007 |  | 61.28 | 0399921
AP | 242 | 05/16/22 | 462 | Rosen Supply Kirkland |  | 1 | 165
AP | 242 | 05/16/22 | 464 | Rosen Supply Kirkland |  | 1 | 283
AP | 242 | 05/24/22 | 773 | Capital One Credit Card |  | 9.66 | 041422BH
AP | 242 | 05/24/22 | 774 | Capital One Credit Card |  | 25.9 | 041922BH
GL | 242 | 06/08/22 | 185 | Req 8380 |  | -114.62
GL | 242 | 06/08/22 | 186 | Req 8379 |  | -233.67
GL | 242 | 06/15/22 | 401 | Req 8416 |  | -3180.03
AP | 600 | 04/29/22 | 1175 | A.R. Brown Backflow Testing |  | 215 | 1903
AP | 600 | 05/24/22 | 776 | Mechanical Resource Services, Inc. |  | 6500 | 17190-5845
AP | 600 | 05/24/22 | 778 | Chemical Products Company |  | 3150 | 3384
AP | 601 | 01/30/19 | 892 | Franklin Engineering |  | 329.5 | 4219
AP | 601 | 02/27/19 | 741 | Franklin Engineering |  | 1869.5 | 7273
AP | 601 | 03/20/19 | 702 | Franklin Engineering |  | 3809.25 | 7301
AP | 601 | 04/26/19 | 824 | Franklin Engineering |  | 1083.5 | 7334
AP | 601 | 11/21/19 | 808 | Franklin Engineering |  | 1672.25 | 6543
AP | 601 | 12/19/19 | 694 | Franklin Engineering |  | 2593.25 | 7578
AP | 601 | 01/28/20 | 804 | Franklin Engineering |  | 6502 | 7596
AP | 601 | 02/05/20 | 7 | Franklin Engineering |  | 3184.5 | 7617
AP | 601 | 04/21/20 | 308 | Franklin Engineering |  | 6888.25 | 7674
AP | 601 | 05/31/20 | 717 | Franklin Engineering |  | 4113 | 7705
AP | 601 | 07/17/20 | 347 | Franklin Engineering |  | 1355.5 | 7781
AP | 601 | 08/21/20 | 471 | Franklin Engineering |  | 3239 | 7796
AP | 601 | 10/26/20 | 565 | Franklin Engineering |  | 287.5 | 7886
AP | 601 | 11/19/20 | 396 | Franklin Engineering |  | 747.5 | 7929
AP | 601 | 01/26/21 | 356 | Franklin Engineering |  | 115 | 7991
AP | 601 | 05/25/21 | 582 | Franklin Engineering |  | 1814.75 | 8151
AP | 601 | 06/16/21 | 368 | Franklin Engineering |  | 4355 | 8184
AP | 602 | 05/06/21 | 118 | H&E Equipment Services, Inc. |  | 529.2 | 95809243
AP | 602 | 05/25/21 | 583 | H&E Equipment Services, Inc. |  | 529.2 | 95817034
AP | 602 | 06/02/21 | 7 | H&E Equipment Services, Inc. |  | 424.46 | 95872765
AP | 602 | 06/02/21 | 9 | H&E Equipment Services, Inc. |  | 424.46 | 95864509
AP | 602 | 06/30/21 | 778 | H&E Equipment Services, Inc. |  | 381.47 | 95902748
AP | 602 | 06/30/21 | 781 | H&E Equipment Services, Inc. |  | 424.46 | 95918042
AP | 602 | 07/24/21 | 615 | H&E Equipment Services, Inc. |  | 424.46 | 95972211
AP | 602 | 08/23/21 | 754 | H&E Equipment Services, Inc. |  | 424.46 | 96029796
AP | 602 | 09/22/21 | 462 | H&E Equipment Services, Inc. |  | 424.46 | 96086584
AP | 602 | 10/04/21 | 211 | H&E Equipment Services, Inc. |  | 251.37 | 96114475
AP | 603 | 08/10/20 | 226 | Capital One Credit Card |  | 201 | 072220J
AP | 603 | 12/16/20 | 304 | Capital One Credit Card |  | 5796 | 111820J
AP | 603 | 08/16/21 | 429 | Capital One Credit Card |  | 210 | 080621J2
AP | 603 | 04/18/22 | 632 | Bank of America CC |  | 298 | 032122J1
AP | 607 | 11/11/20 | 155 | Capital One Credit Card |  | 180 | 102220R2
AP | 607 | 11/11/20 | 156 | Capital One Credit Card |  | 180 | 102220R3
GL | 607 | 11/30/20 | 526 | Reef Parking |  | 100
GL | 607 | 12/01/20 | 156 | Reef Parking |  | -100
AP | 607 | 12/16/20 | 329 | Capital One Credit Card |  | 1 | 112420R
AP | 607 | 02/02/21 | 24 | Capital One Credit Card |  | 180 | 122720R1
AP | 607 | 02/08/21 | 211 | Capital One Credit Card |  | 180 | 012721R1
AP | 607 | 02/08/21 | 212 | Capital One Credit Card |  | 180 | 012721R2
AP | 607 | 03/23/21 | 426 | Capital One Credit Card |  | 180 | 022421R
AP | 607 | 03/23/21 | 427 | Capital One Credit Card |  | 180 | 022421R2
AP | 607 | 04/27/21 | 535 | Capital One Credit Card |  | 180 | 032721R1
AP | 607 | 04/27/21 | 536 | Capital One Credit Card |  | 180 | 032721R2
AP | 607 | 05/24/21 | 509 | Capital One Credit Card |  | 180 | 042621R1
AP | 607 | 05/24/21 | 510 | Capital One Credit Card |  | 180 | 042621R2
AP | 607 | 06/29/21 | 740 | Capital One Credit Card |  | 180 | 052721R
AP | 607 | 06/29/21 | 741 | Capital One Credit Card |  | 180 | 052721R1
AP | 607 | 07/13/21 | 286 | Capital One Credit Card |  | 180 | 062621R
AP | 607 | 07/13/21 | 287 | Capital One Credit Card |  | 180 | 062621R2
AP | 607 | 08/16/21 | 462 | Capital One Credit Card |  | 180 | 072721R1
AP | 607 | 08/16/21 | 463 | Capital One Credit Card |  | 180 | 072721R2
AP | 607 | 10/04/21 | 180 | Capital One Credit Card |  | 180 | 082721R1
AP | 607 | 10/04/21 | 181 | Capital One Credit Card |  | 180 | 082721R2
AP | 607 | 10/12/21 | 483 | Capital One Credit Card |  | 180 | 092621R1
AP | 607 | 10/12/21 | 484 | Capital One Credit Card |  | 180 | 092621R2
AP | 607 | 11/30/21 | 762 | Capital One Credit Card |  | 180 | 102721R
AP | 607 | 11/30/21 | 763 | Capital One Credit Card |  | 180 | 102721R2
AP | 607 | 12/20/21 | 643 | Bank of America CC |  | 180 | 120121R
AP | 607 | 12/21/21 | 673 | Capital One Credit Card |  | 180 | 112621R
AP | 607 | 01/17/22 | 391 | Bank of America CC |  | 180 | 122721R
AP | 607 | 01/17/22 | 392 | Bank of America CC |  | 180 | 122721R2
AP | 607 | 02/15/22 | 400 | Bank of America CC |  | 180 | 012722R
AP | 607 | 02/15/22 | 401 | Bank of America CC |  | 180 | 012722R2
AP | 607 | 03/21/22 | 759 | Bank of America CC |  | 180 | 022422R1
AP | 607 | 03/21/22 | 760 | Bank of America CC |  | 180 | 022422R2
AP | 607 | 04/18/22 | 630 | Bank of America CC |  | 180 | 032722R1
AP | 607 | 04/18/22 | 631 | Bank of America CC |  | 180 | 032722R2
AP | 607 | 05/18/22 | 553 | Bank of America CC |  | 180 | 042722R
AP | 607 | 05/18/22 | 554 | Bank of America CC |  | 180 | 042622R2
PR | 995 | 10/25/19 | 664 | Donelson, Richard T |  | 105.88
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 26.47
PR | 995 | 11/08/19 | 253 | Donelson, Richard T |  | 26.47
PR | 995 | 11/15/19 | 512 | Donelson, Richard T |  | 26.47
PR | 995 | 04/24/20 | 424 | Donelson, Richard T |  | 52.94
PR | 995 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/14/20 | 332 | Donelson, Richard T |  | 79.41
PR | 995 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/28/20 | 604 | Donelson, Richard T |  | 26.47
PR | 995 | 09/11/20 | 120 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 09/25/20 | 479 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 10/02/20 | 52 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 10/16/20 | 339 | Donelson, Richard T |  | 26.47
PR | 995 | 10/16/20 | 340 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 10/23/20 | 482 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 10/30/20 | 637 | Gerard, Jeffrey S |  | 72.47
PR | 995 | 11/06/20 | 15 | Barnhart, Joseph N |  | 44.98
PR | 995 | 11/06/20 | 59 | Gerard, Jeffrey S |  | 48.31
PR | 995 | 11/06/20 | 59 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 11/13/20 | 231 | Gerard, Jeffrey S |  | 72.47
PR | 995 | 11/20/20 | 388 | Donelson, Richard T |  | 52.06
PR | 995 | 11/20/20 | 389 | Gerard, Jeffrey S |  | 48.31
PR | 995 | 11/25/20 | 456 | Barnhart, Joseph N |  | 67.47
PR | 995 | 12/04/20 | 7 | Barnhart, Joseph N |  | 427.33
PR | 995 | 12/04/20 | 31 | Martinez Reyes, Juan C |  | 215.75
PR | 995 | 12/04/20 | 51 | Gerard, Jeffrey S |  | 48.31
PR | 995 | 12/04/20 | 51 | Gerard, Jeffrey S |  | 36.24
PR | 995 | 12/11/20 | 183 | Barnhart, Joseph N |  | 314.87
PR | 995 | 12/11/20 | 224 | Donelson, Richard T |  | 26.03
PR | 995 | 12/11/20 | 225 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 12/11/20 | 225 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 12/18/20 | 344 | Barnhart, Joseph N |  | 44.98
PR | 995 | 12/18/20 | 344 | Barnhart, Joseph N |  | 22.49
PR | 995 | 12/18/20 | 387 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 12/23/20 | 485 | Barnhart, Joseph N |  | 89.96
PR | 995 | 12/23/20 | 529 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 12/31/20 | 581 | Anderson, Richard P |  | 326.54
PR | 995 | 12/31/20 | 585 | Barnhart, Joseph N |  | 44.98
PR | 995 | 12/31/20 | 609 | Martinez Reyes, Juan C |  | 246.57
PR | 995 | 12/31/20 | 627 | Donelson, Richard T |  | 26.03
PR | 995 | 12/31/20 | 628 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 01/08/21 | 4 | Anderson, Richard P |  | 571.44
PR | 995 | 01/08/21 | 32 | Martinez Reyes, Juan C |  | 431.49
PR | 995 | 01/08/21 | 52 | Donelson, Richard T |  | 26.03
PR | 995 | 01/08/21 | 53 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 01/08/21 | 53 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 01/15/21 | 117 | Anderson, Richard P |  | 40.82
PR | 995 | 01/15/21 | 146 | Martinez Reyes, Juan C |  | 30.82
PR | 995 | 01/15/21 | 171 | Donelson, Richard T |  | 52.06
PR | 995 | 01/29/21 | 386 | Barnhart, Joseph N |  | 22.49
PR | 995 | 01/29/21 | 386 | Barnhart, Joseph N |  | 22.49
PR | 995 | 01/29/21 | 433 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 02/05/21 | 67 | Anderson, Richard P |  | 163.27
PR | 995 | 02/05/21 | 99 | Martinez Reyes, Juan C |  | 123.28
PR | 995 | 02/05/21 | 122 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 02/12/21 | 252 | Anderson, Richard P |  | 306.13
PR | 995 | 02/12/21 | 285 | Martinez Reyes, Juan C |  | 61.64
PR | 995 | 02/12/21 | 308 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 02/19/21 | 416 | Anderson, Richard P |  | 30.61
PR | 995 | 02/19/21 | 474 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 02/26/21 | 593 | Anderson, Richard P |  | 489.8
PR | 995 | 02/26/21 | 597 | Barnhart, Joseph N |  | 22.49
PR | 995 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 323.62
PR | 995 | 03/05/21 | 52 | Anderson, Richard P |  | 285.72
PR | 995 | 03/05/21 | 56 | Barnhart, Joseph N |  | 22.49
PR | 995 | 03/05/21 | 87 | Martinez Reyes, Juan C |  | 61.64
PR | 995 | 03/05/21 | 107 | Donelson, Richard T |  | 26.03
PR | 995 | 03/05/21 | 108 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 03/12/21 | 233 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 03/12/21 | 233 | Gerard, Jeffrey S |  | 24.16
PR | 995 | 03/19/21 | 287 | Anderson, Richard P |  | 467.31
PR | 995 | 03/19/21 | 300 | Cortes Sepulveda, Jose R |  | 209.92
PR | 995 | 03/19/21 | 327 | Martinez Reyes, Juan C |  | 357.36
PR | 995 | 03/26/21 | 518 | Anderson, Richard P |  | 127.45
PR | 995 | 03/26/21 | 522 | Barnhart, Joseph N |  | 46.65
PR | 995 | 03/26/21 | 528 | Chevez, Herson G |  | 93.3
PR | 995 | 03/26/21 | 558 | Martinez Reyes, Juan C |  | 97.46
PR | 995 | 03/26/21 | 562 | Paco Leyva, Orlando |  | 97.88
PR | 995 | 04/02/21 | 7 | Barnhart, Joseph N |  | 23.32
PR | 995 | 04/02/21 | 13 | Chevez, Herson G |  | 58.31
PR | 995 | 04/02/21 | 25 | Galdamez, Dagoberto A |  | 87.47
PR | 995 | 04/02/21 | 47 | Paco Leyva, Orlando |  | 254.48
PR | 995 | 04/02/21 | 50 | Ramos Herrera, Franklin J |  | 54.98
PR | 995 | 04/02/21 | 64 | Donelson, Richard T |  | 26.03
PR | 995 | 04/09/21 | 110 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/09/21 | 128 | Galdamez, Dagoberto A |  | 116.62
PR | 995 | 04/09/21 | 151 | Paco Leyva, Orlando |  | 78.3
PR | 995 | 04/09/21 | 168 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I |  | 316.54
PR | 995 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I |  | 63.31
PR | 995 | 04/16/21 | 253 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/16/21 | 253 | Barnhart, Joseph N |  | 23.32
PR | 995 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 174.93
PR | 995 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 58.31
PR | 995 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 116.62
PR | 995 | 04/16/21 | 296 | Paco Leyva, Orlando |  | 293.63
PR | 995 | 04/16/21 | 315 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 04/23/21 | 402 | Balderas Ortiz, Ricardo I |  | 253.23
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 104.96
PR | 995 | 04/23/21 | 415 | Cruz Guzman, Joel A |  | 509.8
PR | 995 | 04/23/21 | 423 | Galdamez, Dagoberto A |  | 349.86
PR | 995 | 04/23/21 | 431 | Guerrero Espinoza, Mario |  | 73.3
PR | 995 | 04/23/21 | 431 | Guerrero Espinoza, Mario |  | 146.61
PR | 995 | 04/23/21 | 440 | Lopez, Maslin A |  | 199.92
PR | 995 | 04/23/21 | 440 | Lopez, Maslin A |  | 139.94
PR | 995 | 04/23/21 | 447 | Paco Leyva, Orlando |  | 234.91
PR | 995 | 04/23/21 | 447 | Paco Leyva, Orlando |  | 78.3
PR | 995 | 04/23/21 | 451 | Ramos Herrera, Franklin J |  | 219.91
PR | 995 | 04/23/21 | 466 | Donelson, Richard T |  | 26.03
PR | 995 | 04/23/21 | 467 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 04/23/21 | 467 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 04/30/21 | 572 | Balderas Ortiz, Ricardo I |  | 253.23
PR | 995 | 04/30/21 | 574 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/30/21 | 585 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 04/30/21 | 593 | Galdamez, Dagoberto A |  | 583.1
PR | 995 | 04/30/21 | 601 | Guerrero Espinoza, Mario |  | 311.54
PR | 995 | 04/30/21 | 601 | Guerrero Espinoza, Mario |  | 54.98
PR | 995 | 04/30/21 | 610 | Lopez, Maslin A |  | 209.92
PR | 995 | 04/30/21 | 610 | Lopez, Maslin A |  | 79.97
PR | 995 | 04/30/21 | 610 | Lopez, Maslin A |  | 29.99
PR | 995 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 508.96
PR | 995 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 117.45
PR | 995 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 39.15
PR | 995 | 04/30/21 | 622 | Ramos Herrera, Franklin J |  | 109.96
PR | 995 | 04/30/21 | 638 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 46.65
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/07/21 | 51 | Cruz Gonzalez, Julio C |  | 399.84
PR | 995 | 05/07/21 | 51 | Cruz Gonzalez, Julio C |  | 99.96
PR | 995 | 05/07/21 | 52 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 05/07/21 | 60 | Galdamez, Dagoberto A |  | 58.31
PR | 995 | 05/07/21 | 60 | Galdamez, Dagoberto A |  | 58.31
PR | 995 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 146.61
PR | 995 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 183.26
PR | 995 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 36.65
PR | 995 | 05/07/21 | 78 | Lopez, Maslin A |  | 159.94
PR | 995 | 05/07/21 | 78 | Lopez, Maslin A |  | 199.92
PR | 995 | 05/07/21 | 78 | Lopez, Maslin A |  | 39.98
PR | 995 | 05/07/21 | 86 | Paco Leyva, Orlando |  | 234.91
PR | 995 | 05/07/21 | 86 | Paco Leyva, Orlando |  | 176.18
PR | 995 | 05/07/21 | 90 | Ramos Herrera, Franklin J |  | 109.96
PR | 995 | 05/07/21 | 106 | Donelson, Richard T |  | 26.03
PR | 995 | 05/07/21 | 107 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 05/07/21 | 107 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 05/14/21 | 246 | Barnhart, Joseph N |  | 46.65
PR | 995 | 05/14/21 | 255 | Cruz Gonzalez, Julio C |  | 299.88
PR | 995 | 05/14/21 | 255 | Cruz Gonzalez, Julio C |  | 199.92
PR | 995 | 05/14/21 | 256 | Cruz Guzman, Joel A |  | 354.03
PR | 995 | 05/14/21 | 256 | Cruz Guzman, Joel A |  | 212.42
PR | 995 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 274.89
PR | 995 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 54.98
PR | 995 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 36.65
PR | 995 | 05/14/21 | 288 | Mendoza Morales, Jesus A |  | 453.15
PR | 995 | 05/14/21 | 288 | Mendoza Morales, Jesus A |  | 113.29
PR | 995 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 195.76
PR | 995 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 78.3
PR | 995 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 117.45
PR | 995 | 05/14/21 | 311 | Gerard, Jeffrey S |  | 49.98
PR | 995 | 05/14/21 | 311 | Gerard, Jeffrey S |  | 49.98
PR | 995 | 05/21/21 | 391 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/21/21 | 394 | Boss, Benjamin T |  | 18.33
PR | 995 | 05/21/21 | 395 | Boss, Kyle A |  | 19.16
PR | 995 | 05/21/21 | 400 | Cruz Gonzalez, Julio C |  | 449.82
PR | 995 | 05/21/21 | 400 | Cruz Gonzalez, Julio C |  | 49.98
PR | 995 | 05/21/21 | 401 | Cruz Guzman, Joel A |  | 453.15
PR | 995 | 05/21/21 | 401 | Cruz Guzman, Joel A |  | 113.29
PR | 995 | 05/21/21 | 405 | Eisenhauer, Tommy J |  | 36.65
PR | 995 | 05/21/21 | 417 | Guerrero Espinoza, Mario |  | 219.91
PR | 995 | 05/21/21 | 417 | Guerrero Espinoza, Mario |  | 73.3
PR | 995 | 05/21/21 | 434 | Mendoza Morales, Jesus A |  | 566.44
PR | 995 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 195.76
PR | 995 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 97.88
PR | 995 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 39.15
PR | 995 | 05/21/21 | 444 | Romero Garza, Jesus I |  | 399.84
PR | 995 | 05/21/21 | 451 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 05/21/21 | 457 | Gerard, Jeffrey S |  | 74.97
PR | 995 | 05/28/21 | 632 | Barnhart, Joseph N |  | 46.65
PR | 995 | 05/28/21 | 641 | Cruz Gonzalez, Julio C |  | 474.81
PR | 995 | 05/28/21 | 641 | Cruz Gonzalez, Julio C |  | 24.99
PR | 995 | 05/28/21 | 642 | Cruz Guzman, Joel A |  | 339.86
PR | 995 | 05/28/21 | 642 | Cruz Guzman, Joel A |  | 226.58
PR | 995 | 05/28/21 | 643 | Cruz Reyes, Jose |  | 453.15
PR | 995 | 05/28/21 | 658 | Guerrero Espinoza, Mario |  | 219.91
PR | 995 | 05/28/21 | 658 | Guerrero Espinoza, Mario |  | 146.61
PR | 995 | 05/28/21 | 665 | Hubbard, Robert W |  | 68.72
PR | 995 | 05/28/21 | 675 | Mendoza Morales, Jesus A |  | 566.44
PR | 995 | 05/28/21 | 678 | Paco Leyva, Orlando |  | 39.15
PR | 995 | 05/28/21 | 678 | Paco Leyva, Orlando |  | 78.3
PR | 995 | 05/28/21 | 687 | Romero Garza, Jesus I |  | 399.84
PR | 995 | 05/28/21 | 694 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 05/28/21 | 701 | Gerard, Jeffrey S |  | 49.98
PR | 995 | 06/04/21 | 26 | Ascencio, Jose L |  | 453.15
PR | 995 | 06/04/21 | 29 | Barnhart, Joseph N |  | 46.65
PR | 995 | 06/04/21 | 40 | Cruz Gonzalez, Julio C |  | 199.92
PR | 995 | 06/04/21 | 41 | Cruz Guzman, Joel A |  | 453.15
PR | 995 | 06/04/21 | 43 | Cruz Reyes, Jose |  | 226.58
PR | 995 | 06/04/21 | 58 | Guerrero Espinoza, Mario |  | 73.3
PR | 995 | 06/04/21 | 65 | Hubbard, Robert W |  | 45.82
PR | 995 | 06/04/21 | 65 | Hubbard, Robert W |  | 22.91
PR | 995 | 06/04/21 | 79 | Paco Leyva, Orlando |  | 137.03
PR | 995 | 06/04/21 | 89 | Sanders, Allen O |  | 22.91
PR | 995 | 06/04/21 | 94 | Trower-Kelly, Fidel D |  | 319.87
PR | 995 | 06/04/21 | 99 | Donelson, Richard T |  | 52.06
PR | 995 | 06/04/21 | 100 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 06/11/21 | 200 | Ascencio, Jose L |  | 566.44
PR | 995 | 06/11/21 | 201 | Balderas Ortiz, Ricardo I |  | 126.62
PR | 995 | 06/11/21 | 214 | Cruz Gonzalez, Julio C |  | 199.92
PR | 995 | 06/11/21 | 214 | Cruz Gonzalez, Julio C |  | 199.92
PR | 995 | 06/11/21 | 215 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 06/11/21 | 216 | Cruz Reyes, Jose |  | 566.44
PR | 995 | 06/11/21 | 231 | Guerrero Espinoza, Mario |  | 293.22
PR | 995 | 06/11/21 | 247 | Mendoza Morales, Jesus A |  | 339.86
PR | 995 | 06/11/21 | 251 | Paco Leyva, Orlando |  | 195.76
PR | 995 | 06/11/21 | 256 | Ramos Herrera, Franklin J |  | 109.96
PR | 995 | 06/11/21 | 266 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 06/18/21 | 402 | Ascencio, Jose L |  | 339.86
PR | 995 | 06/18/21 | 405 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/18/21 | 410 | Castro Hernandez, Jose A |  | 293.22
PR | 995 | 06/18/21 | 416 | Cruz Gonzalez, Julio C |  | 299.88
PR | 995 | 06/18/21 | 417 | Cruz Guzman, Joel A |  | 453.15
PR | 995 | 06/18/21 | 418 | Cruz Reyes, Jose |  | 339.86
PR | 995 | 06/18/21 | 433 | Guerrero Espinoza, Mario |  | 366.52
PR | 995 | 06/18/21 | 446 | Lucas Tzintzun, Rafael |  | 173.26
PR | 995 | 06/18/21 | 449 | Mendoza Morales, Jesus A |  | 226.58
PR | 995 | 06/18/21 | 453 | Paco Leyva, Orlando |  | 352.36
PR | 995 | 06/18/21 | 453 | Paco Leyva, Orlando |  | 39.15
PR | 995 | 06/18/21 | 463 | Ross, Kelli M |  | 53.73
PR | 995 | 06/18/21 | 469 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 06/18/21 | 476 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 06/25/21 | 597 | Ascencio, Jose L |  | 566.44
PR | 995 | 06/25/21 | 600 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/25/21 | 611 | Cruz Gonzalez, Julio C |  | 499.8
PR | 995 | 06/25/21 | 612 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 06/25/21 | 613 | Cruz Reyes, Jose |  | 566.44
PR | 995 | 06/25/21 | 628 | Guerrero Espinoza, Mario |  | 339.03
PR | 995 | 06/25/21 | 631 | Hawkins, Conor L |  | 226.58
PR | 995 | 06/25/21 | 641 | Lucas Tzintzun, Rafael |  | 346.53
PR | 995 | 06/25/21 | 648 | Paco Leyva, Orlando |  | 274.06
PR | 995 | 06/25/21 | 648 | Paco Leyva, Orlando |  | 58.73
PR | 995 | 06/25/21 | 664 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 06/25/21 | 673 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 07/02/21 | 6 | Ascencio, Jose L |  | 545.2
PR | 995 | 07/02/21 | 9 | Barnhart, Joseph N |  | 23.32
PR | 995 | 07/02/21 | 20 | Cruz Gonzalez, Julio C |  | 381.1
PR | 995 | 07/02/21 | 21 | Cruz Guzman, Joel A |  | 545.2
PR | 995 | 07/02/21 | 22 | Cruz Reyes, Jose |  | 545.2
PR | 995 | 07/02/21 | 37 | Guerrero Espinoza, Mario |  | 206.17
PR | 995 | 07/02/21 | 38 | Hawkins, Conor L |  | 169.93
PR | 995 | 07/02/21 | 42 | Hubbard, Robert W |  | 45.82
PR | 995 | 07/02/21 | 48 | Lucas Tzintzun, Rafael |  | 330.28
PR | 995 | 07/02/21 | 56 | Paco Leyva, Orlando |  | 293.63
PR | 995 | 07/02/21 | 56 | Paco Leyva, Orlando |  | 19.58
PR | 995 | 07/02/21 | 72 | Trower-Kelly, Fidel D |  | 369.85
PR | 995 | 07/02/21 | 78 | Donelson, Richard T |  | 26.03
PR | 995 | 07/09/21 | 101 | Ascencio, Jose L |  | 453.15
PR | 995 | 07/09/21 | 115 | Cruz Gonzalez, Julio C |  | 399.84
PR | 995 | 07/09/21 | 116 | Cruz Guzman, Joel A |  | 453.15
PR | 995 | 07/09/21 | 117 | Cruz Reyes, Jose |  | 453.15
PR | 995 | 07/09/21 | 132 | Guerrero Espinoza, Mario |  | 293.22
PR | 995 | 07/09/21 | 143 | Lucas Tzintzun, Rafael |  | 346.53
PR | 995 | 07/09/21 | 151 | Paco Leyva, Orlando |  | 234.91
PR | 995 | 07/09/21 | 151 | Paco Leyva, Orlando |  | 19.58
PR | 995 | 07/09/21 | 157 | Reed, Reuben H |  | 169.93
PR | 995 | 07/09/21 | 169 | Trower-Kelly, Fidel D |  | 159.94
PR | 995 | 07/09/21 | 176 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 07/16/21 | 319 | Ascencio, Jose L |  | 566.44
PR | 995 | 07/16/21 | 333 | Cruz Gonzalez, Julio C |  | 149.94
PR | 995 | 07/16/21 | 333 | Cruz Gonzalez, Julio C |  | 49.98
PR | 995 | 07/16/21 | 334 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 07/16/21 | 335 | Cruz Reyes, Jose |  | 566.44
PR | 995 | 07/16/21 | 350 | Guerrero Espinoza, Mario |  | 293.22
PR | 995 | 07/16/21 | 361 | Lucas Tzintzun, Rafael |  | 173.26
PR | 995 | 07/16/21 | 369 | Paco Leyva, Orlando |  | 293.63
PR | 995 | 07/16/21 | 369 | Paco Leyva, Orlando |  | 78.3
PR | 995 | 07/16/21 | 387 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 07/23/21 | 489 | Ascencio, Jose L |  | 453.15
PR | 995 | 07/23/21 | 504 | Cruz Gonzalez, Julio C |  | 343.61
PR | 995 | 07/23/21 | 504 | Cruz Gonzalez, Julio C |  | 124.95
PR | 995 | 07/23/21 | 505 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 07/23/21 | 506 | Cruz Reyes, Jose |  | 226.58
PR | 995 | 07/23/21 | 521 | Guerrero Espinoza, Mario |  | 293.22
PR | 995 | 07/23/21 | 527 | Hubbard, Robert W |  | 45.82
PR | 995 | 07/23/21 | 541 | Paco Leyva, Orlando |  | 274.06
PR | 995 | 07/23/21 | 541 | Paco Leyva, Orlando |  | 19.58
PR | 995 | 07/23/21 | 559 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 07/30/21 | 680 | Ascencio, Jose L |  | 566.44
PR | 995 | 07/30/21 | 696 | Cruz Gonzalez, Julio C |  | 299.88
PR | 995 | 07/30/21 | 696 | Cruz Gonzalez, Julio C |  | 99.96
PR | 995 | 07/30/21 | 697 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 07/30/21 | 698 | Cruz Reyes, Jose |  | 339.86
PR | 995 | 07/30/21 | 713 | Guerrero Espinoza, Mario |  | 366.52
PR | 995 | 07/30/21 | 734 | Paco Leyva, Orlando |  | 97.88
PR | 995 | 07/30/21 | 734 | Paco Leyva, Orlando |  | 156.6
PR | 995 | 07/30/21 | 751 | Trower-Kelly, Fidel D |  | 319.87
PR | 995 | 07/30/21 | 758 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 07/30/21 | 758 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 08/06/21 | 40 | Ascencio, Jose L |  | 566.44
PR | 995 | 08/06/21 | 56 | Cruz Gonzalez, Julio C |  | 399.84
PR | 995 | 08/06/21 | 57 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 08/06/21 | 70 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 08/06/21 | 70 | Gonzalez Hernandez, Josue |  | 126.62
PR | 995 | 08/06/21 | 72 | Guerrero Espinoza, Mario |  | 293.22
PR | 995 | 08/06/21 | 79 | Hubbard, Robert W |  | 68.72
PR | 995 | 08/06/21 | 93 | Paco Leyva, Orlando |  | 97.88
PR | 995 | 08/06/21 | 110 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 08/13/21 | 302 | Ascencio, Jose L |  | 226.58
PR | 995 | 08/13/21 | 306 | Barnhart, Joseph N |  | 116.62
PR | 995 | 08/13/21 | 318 | Cruz Gonzalez, Julio C |  | 99.96
PR | 995 | 08/13/21 | 318 | Cruz Gonzalez, Julio C |  | 99.96
PR | 995 | 08/13/21 | 319 | Cruz Guzman, Joel A |  | 226.58
PR | 995 | 08/13/21 | 332 | Gonzalez Hernandez, Josue |  | 63.31
PR | 995 | 08/13/21 | 332 | Gonzalez Hernandez, Josue |  | 63.31
PR | 995 | 08/13/21 | 334 | Guerrero Espinoza, Mario |  | 383.18
PR | 995 | 08/13/21 | 341 | Hubbard, Robert W |  | 68.72
PR | 995 | 08/13/21 | 341 | Hubbard, Robert W |  | 68.72
PR | 995 | 08/13/21 | 355 | Paco Leyva, Orlando |  | 215.33
PR | 995 | 08/13/21 | 371 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 08/13/21 | 379 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 08/20/21 | 583 | Ascencio, Jose L |  | 339.86
PR | 995 | 08/20/21 | 599 | Cruz Gonzalez, Julio C |  | 499.8
PR | 995 | 08/20/21 | 600 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 08/20/21 | 614 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 08/20/21 | 616 | Guerrero Espinoza, Mario |  | 383.18
PR | 995 | 08/20/21 | 623 | Hubbard, Robert W |  | 91.63
PR | 995 | 08/20/21 | 638 | Paco Leyva, Orlando |  | 176.18
PR | 995 | 08/20/21 | 654 | Trower-Kelly, Fidel D |  | 239.9
PR | 995 | 08/20/21 | 662 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 08/20/21 | 662 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 08/27/21 | 804 | Ascencio, Jose L |  | 566.44
PR | 995 | 08/27/21 | 807 | Barnhart, Joseph N |  | 69.97
PR | 995 | 08/27/21 | 820 | Cruz Gonzalez, Julio C |  | 299.88
PR | 995 | 08/27/21 | 820 | Cruz Gonzalez, Julio C |  | 99.96
PR | 995 | 08/27/21 | 821 | Cruz Guzman, Joel A |  | 566.44
PR | 995 | 08/27/21 | 835 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 08/27/21 | 837 | Guerrero Espinoza, Mario |  | 383.18
PR | 995 | 08/27/21 | 844 | Hubbard, Robert W |  | 366.52
PR | 995 | 08/27/21 | 844 | Hubbard, Robert W |  | 45.82
PR | 995 | 08/27/21 | 858 | Paco Leyva, Orlando |  | 117.45
PR | 995 | 08/27/21 | 869 | Ross, Kelli M |  | 716.38
PR | 995 | 08/27/21 | 875 | Trower-Kelly, Fidel D |  | 399.84
PR | 995 | 08/27/21 | 881 | Young, Joshua S |  | 253.23
PR | 995 | 08/27/21 | 883 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 09/03/21 | 5 | Ascencio, Jose L |  | 566.44
PR | 995 | 09/03/21 | 8 | Barnhart, Joseph N |  | 116.62
PR | 995 | 09/03/21 | 21 | Cruz Gonzalez, Julio C |  | 199.92
PR | 995 | 09/03/21 | 22 | Cruz Guzman, Joel A |  | 453.15
PR | 995 | 09/03/21 | 37 | Gonzalez Hernandez, Josue |  | 63.31
PR | 995 | 09/03/21 | 39 | Guerrero Espinoza, Mario |  | 383.18
PR | 995 | 09/03/21 | 46 | Hubbard, Robert W |  | 45.82
PR | 995 | 09/03/21 | 46 | Hubbard, Robert W |  | 68.72
PR | 995 | 09/03/21 | 60 | Paco Leyva, Orlando |  | 215.33
PR | 995 | 09/03/21 | 72 | Ross, Kelli M |  | 429.83
PR | 995 | 09/03/21 | 78 | Trower-Kelly, Fidel D |  | 319.87
PR | 995 | 09/03/21 | 87 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 09/10/21 | 173 | Ascencio, Jose L |  | 479.81
PR | 995 | 09/10/21 | 176 | Barnhart, Joseph N |  | 120.79
PR | 995 | 09/10/21 | 189 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 09/10/21 | 190 | Cruz Guzman, Joel A |  | 369.85
PR | 995 | 09/10/21 | 205 | Gonzalez Hernandez, Josue |  | 266.56
PR | 995 | 09/10/21 | 207 | Guerrero Espinoza, Mario |  | 239.49
PR | 995 | 09/10/21 | 214 | Hubbard, Robert W |  | 46.65
PR | 995 | 09/10/21 | 228 | Paco Leyva, Orlando |  | 333.2
PR | 995 | 09/10/21 | 241 | Ross, Kelli M |  | 299.88
PR | 995 | 09/10/21 | 247 | Trower-Kelly, Fidel D |  | 86.63
PR | 995 | 09/10/21 | 247 | Trower-Kelly, Fidel D |  | 86.63
PR | 995 | 09/10/21 | 254 | Donelson, Richard T |  | 26.03
PR | 995 | 09/17/21 | 335 | Ascencio, Jose L |  | 599.76
PR | 995 | 09/17/21 | 338 | Barnhart, Joseph N |  | 144.94
PR | 995 | 09/17/21 | 351 | Cruz Gonzalez, Julio C |  | 319.87
PR | 995 | 09/17/21 | 351 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 09/17/21 | 352 | Cruz Guzman, Joel A |  | 616.42
PR | 995 | 09/17/21 | 367 | Gonzalez Hernandez, Josue |  | 399.84
PR | 995 | 09/17/21 | 367 | Gonzalez Hernandez, Josue |  | 266.56
PR | 995 | 09/17/21 | 369 | Guerrero Espinoza, Mario |  | 416.5
PR | 995 | 09/17/21 | 376 | Hubbard, Robert W |  | 46.65
PR | 995 | 09/17/21 | 390 | Paco Leyva, Orlando |  | 166.6
PR | 995 | 09/17/21 | 409 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 09/24/21 | 489 | Ascencio, Jose L |  | 479.81
PR | 995 | 09/24/21 | 490 | Balderas Ortiz, Ricardo I |  | 133.28
PR | 995 | 09/24/21 | 492 | Barnhart, Joseph N |  | 217.41
PR | 995 | 09/24/21 | 505 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 09/24/21 | 505 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 09/24/21 | 506 | Cruz Guzman, Joel A |  | 493.14
PR | 995 | 09/24/21 | 506 | Cruz Guzman, Joel A |  | 123.28
PR | 995 | 09/24/21 | 516 | Galdamez, Dagoberto A |  | 123.28
PR | 995 | 09/24/21 | 521 | Gonzalez Hernandez, Josue |  | 533.12
PR | 995 | 09/24/21 | 521 | Gonzalez Hernandez, Josue |  | 91.63
PR | 995 | 09/24/21 | 523 | Guerrero Espinoza, Mario |  | 416.5
PR | 995 | 09/24/21 | 530 | Hubbard, Robert W |  | 69.97
PR | 995 | 09/24/21 | 534 | Lopez, Maslin A |  | 89.96
PR | 995 | 09/24/21 | 540 | Mendoza Morales, Jesus A |  | 119.95
PR | 995 | 09/24/21 | 544 | Paco Leyva, Orlando |  | 395.68
PR | 995 | 09/24/21 | 544 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 09/24/21 | 551 | Ramos Herrera, Franklin J |  | 119.95
PR | 995 | 09/24/21 | 564 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 09/24/21 | 570 | Young, Joshua S |  | 69.97
PR | 995 | 10/01/21 | 6 | Ascencio, Jose L |  | 179.93
PR | 995 | 10/01/21 | 6 | Ascencio, Jose L |  | 479.81
PR | 995 | 10/01/21 | 9 | Barnhart, Joseph N |  | 120.79
PR | 995 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 149.94
PR | 995 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 119.95
PR | 995 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 173.26
PR | 995 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 359.86
PR | 995 | 10/01/21 | 23 | Cruz Guzman, Joel A |  | 231.16
PR | 995 | 10/01/21 | 23 | Cruz Guzman, Joel A |  | 616.42
PR | 995 | 10/01/21 | 40 | Guerrero Espinoza, Mario |  | 124.95
PR | 995 | 10/01/21 | 40 | Guerrero Espinoza, Mario |  | 416.5
PR | 995 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 187.43
PR | 995 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 93.71
PR | 995 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 374.85
PR | 995 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 194.92
PR | 995 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 64.97
PR | 995 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 433.16
PR | 995 | 10/01/21 | 88 | Donelson, Richard T |  | 26.03
PR | 995 | 10/08/21 | 294 | Ascencio, Jose L |  | 179.93
PR | 995 | 10/08/21 | 294 | Ascencio, Jose L |  | 599.76
PR | 995 | 10/08/21 | 297 | Barnhart, Joseph N |  | 169.1
PR | 995 | 10/08/21 | 311 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 10/08/21 | 312 | Cruz Guzman, Joel A |  | 585.6
PR | 995 | 10/08/21 | 354 | Paco Leyva, Orlando |  | 499.8
PR | 995 | 10/08/21 | 362 | Reed, Reuben H |  | -169.93
PR | 995 | 10/08/21 | 374 | Trower-Kelly, Fidel D |  | 411.5
PR | 995 | 10/15/21 | 558 | Ascencio, Jose L |  | 179.93
PR | 995 | 10/15/21 | 558 | Ascencio, Jose L |  | 599.76
PR | 995 | 10/15/21 | 561 | Barnhart, Joseph N |  | 24.16
PR | 995 | 10/15/21 | 575 | Cruz Gonzalez, Julio C |  | 399.84
PR | 995 | 10/15/21 | 576 | Cruz Guzman, Joel A |  | 184.93
PR | 995 | 10/15/21 | 576 | Cruz Guzman, Joel A |  | 616.42
PR | 995 | 10/15/21 | 618 | Paco Leyva, Orlando |  | 124.95
PR | 995 | 10/15/21 | 618 | Paco Leyva, Orlando |  | 395.68
PR | 995 | 10/15/21 | 628 | Robles Arroyo, Alonso |  | 104.96
PR | 995 | 10/15/21 | 628 | Robles Arroyo, Alonso |  | 349.86
PR | 995 | 10/22/21 | 744 | Ascencio, Jose L |  | 599.76
PR | 995 | 10/22/21 | 748 | Barnhart, Joseph N |  | 72.47
PR | 995 | 10/22/21 | 763 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 10/22/21 | 764 | Cruz Guzman, Joel A |  | 462.32
PR | 995 | 10/22/21 | 764 | Cruz Guzman, Joel A |  | 30.82
PR | 995 | 10/22/21 | 790 | Herrera Hernandez, Manuel L |  | 126.62
PR | 995 | 10/22/21 | 794 | Hubbard, Robert W |  | 23.32
PR | 995 | 10/22/21 | 798 | Lopez, Maslin A |  | 89.96
PR | 995 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 354.03
PR | 995 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 10/22/21 | 815 | Ramos Herrera, Franklin J |  | 119.95
PR | 995 | 10/22/21 | 818 | Robles Arroyo, Alonso |  | 314.87
PR | 995 | 10/22/21 | 818 | Robles Arroyo, Alonso |  | 34.99
PR | 995 | 10/22/21 | 828 | Trower-Kelly, Fidel D |  | 259.9
PR | 995 | 10/29/21 | 1002 | Anderson, Richard P |  | 33.11
PR | 995 | 10/29/21 | 1004 | Ascencio, Jose L |  | 479.81
PR | 995 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 96.63
PR | 995 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 10/29/21 | 1024 | Cruz Guzman, Joel A |  | 616.42
PR | 995 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 229.49
PR | 995 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 23.74
PR | 995 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 63.31
PR | 995 | 10/29/21 | 1058 | Lopez, Maslin A |  | 292.38
PR | 995 | 10/29/21 | 1058 | Lopez, Maslin A |  | 22.49
PR | 995 | 10/29/21 | 1058 | Lopez, Maslin A |  | 44.98
PR | 995 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 333.2
PR | 995 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 145.78
PR | 995 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 10/29/21 | 1077 | Robles Arroyo, Alonso |  | 279.89
PR | 995 | 10/29/21 | 1086 | Trower-Kelly, Fidel D |  | 259.9
PR | 995 | 11/05/21 | 54 | Barnhart, Joseph N |  | 48.31
PR | 995 | 11/05/21 | 69 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 11/05/21 | 69 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 11/05/21 | 70 | Cruz Guzman, Joel A |  | 616.42
PR | 995 | 11/05/21 | 83 | Galdamez, Dagoberto A |  | 123.28
PR | 995 | 11/05/21 | 97 | Herrera Hernandez, Manuel L |  | 94.96
PR | 995 | 11/05/21 | 97 | Herrera Hernandez, Manuel L |  | 94.96
PR | 995 | 11/05/21 | 101 | Hubbard, Robert W |  | 46.65
PR | 995 | 11/05/21 | 106 | Lopez, Maslin A |  | 449.82
PR | 995 | 11/05/21 | 115 | Paco Leyva, Orlando |  | 333.2
PR | 995 | 11/05/21 | 115 | Paco Leyva, Orlando |  | 124.95
PR | 995 | 11/05/21 | 122 | Ramos Herrera, Franklin J |  | 239.9
PR | 995 | 11/05/21 | 125 | Robles Arroyo, Alonso |  | 209.92
PR | 995 | 11/05/21 | 125 | Robles Arroyo, Alonso |  | 69.97
PR | 995 | 11/05/21 | 140 | Young, Joshua S |  | 209.92
PR | 995 | 11/12/21 | 266 | Ascencio, Jose L |  | 239.9
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 72.47
PR | 995 | 11/12/21 | 284 | Cruz Gonzalez, Julio C |  | 186.59
PR | 995 | 11/12/21 | 284 | Cruz Gonzalez, Julio C |  | 319.87
PR | 995 | 11/12/21 | 285 | Cruz Guzman, Joel A |  | 246.57
PR | 995 | 11/12/21 | 297 | Galdamez, Dagoberto A |  | 369.85
PR | 995 | 11/12/21 | 311 | Herrera Hernandez, Manuel L |  | 189.92
PR | 995 | 11/12/21 | 311 | Herrera Hernandez, Manuel L |  | 63.31
PR | 995 | 11/12/21 | 320 | Lopez, Maslin A |  | 359.86
PR | 995 | 11/12/21 | 329 | Paco Leyva, Orlando |  | 395.68
PR | 995 | 11/12/21 | 329 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 11/12/21 | 336 | Ramos Herrera, Franklin J |  | 239.9
PR | 995 | 11/19/21 | 434 | Ascencio, Jose L |  | 239.9
PR | 995 | 11/19/21 | 437 | Barnhart, Joseph N |  | 24.16
PR | 995 | 11/19/21 | 452 | Cruz Gonzalez, Julio C |  | 479.81
PR | 995 | 11/19/21 | 453 | Cruz Guzman, Joel A |  | 246.57
PR | 995 | 11/19/21 | 465 | Galdamez, Dagoberto A |  | 246.57
PR | 995 | 11/19/21 | 479 | Herrera Hernandez, Manuel L |  | 126.62
PR | 995 | 11/19/21 | 488 | Lopez, Maslin A |  | 449.82
PR | 995 | 11/19/21 | 497 | Paco Leyva, Orlando |  | 354.03
PR | 995 | 11/19/21 | 520 | Young, Joshua S |  | 139.94
PR | 995 | 11/24/21 | 592 | Cruz Gonzalez, Julio C |  | 506.46
PR | 995 | 11/24/21 | 626 | Lopez, Maslin A |  | 427.33
PR | 995 | 11/24/21 | 635 | Paco Leyva, Orlando |  | 333.2
PR | 995 | 11/24/21 | 650 | Sanders, Allen O |  | 47.48
PR | 995 | 11/24/21 | 658 | Young, Joshua S |  | 139.94
PR | 995 | 11/24/21 | 660 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 12/03/21 | 29 | Cruz Gonzalez, Julio C |  | 426.5
PR | 995 | 12/03/21 | 64 | Lopez, Maslin A |  | 89.96
PR | 995 | 12/03/21 | 73 | Paco Leyva, Orlando |  | 291.55
PR | 995 | 12/03/21 | 73 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 12/03/21 | 88 | Sanders, Allen O |  | 154.31
PR | 995 | 12/10/21 | 194 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/10/21 | 210 | Cruz Gonzalez, Julio C |  | 319.87
PR | 995 | 12/10/21 | 210 | Cruz Gonzalez, Julio C |  | 213.25
PR | 995 | 12/10/21 | 256 | Paco Leyva, Orlando |  | 354.03
PR | 995 | 12/17/21 | 532 | Cruz Gonzalez, Julio C |  | 79.97
PR | 995 | 12/17/21 | 532 | Cruz Gonzalez, Julio C |  | 319.87
PR | 995 | 12/17/21 | 545 | Galdamez, Dagoberto A |  | 77.05
PR | 995 | 12/17/21 | 545 | Galdamez, Dagoberto A |  | 123.28
PR | 995 | 12/17/21 | 578 | Paco Leyva, Orlando |  | 166.6
PR | 995 | 12/17/21 | 578 | Paco Leyva, Orlando |  | 229.08
PR | 995 | 12/17/21 | 603 | Donelson, Richard T |  | 26.03
PR | 995 | 12/23/21 | 741 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/23/21 | 757 | Cruz Gonzalez, Julio C |  | 213.25
PR | 995 | 12/23/21 | 803 | Paco Leyva, Orlando |  | 499.8
PR | 995 | 12/30/21 | 998 | Paco Leyva, Orlando |  | 104.13
PR | 995 | 12/30/21 | 998 | Paco Leyva, Orlando |  | 62.48
PR | 995 | 01/07/22 | 30 | Barnhart, Joseph N |  | 24.16
PR | 995 | 01/07/22 | 73 | Herrera Hernandez, Manuel L |  | 126.62
PR | 995 | 01/07/22 | 77 | Hubbard, Robert W |  | 46.65
PR | 995 | 01/07/22 | 92 | Paco Leyva, Orlando |  | 312.38
PR | 995 | 01/14/22 | 229 | Balderas Ortiz, Ricardo I |  | 333.2
PR | 995 | 01/14/22 | 274 | Herrera Hernandez, Manuel L |  | 63.31
PR | 995 | 01/14/22 | 274 | Herrera Hernandez, Manuel L |  | 126.62
PR | 995 | 01/14/22 | 278 | Hubbard, Robert W |  | 34.99
PR | 995 | 01/14/22 | 292 | Paco Leyva, Orlando |  | 83.3
PR | 995 | 01/14/22 | 292 | Paco Leyva, Orlando |  | 187.43
PR | 995 | 01/21/22 | 476 | Paco Leyva, Orlando |  | 62.48
PR | 995 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I |  | 399.84
PR | 995 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I |  | 199.92
PR | 995 | 01/28/22 | 643 | Galdamez, Dagoberto A |  | 61.64
PR | 995 | 01/28/22 | 643 | Galdamez, Dagoberto A |  | 61.64
PR | 995 | 01/28/22 | 677 | Paco Leyva, Orlando |  | 83.3
PR | 995 | 01/28/22 | 677 | Paco Leyva, Orlando |  | 187.43
PR | 995 | 01/28/22 | 684 | Ramos Herrera, Franklin J |  | 59.98
PR | 995 | 01/28/22 | 684 | Ramos Herrera, Franklin J |  | 59.98
PR | 995 | 01/28/22 | 705 | Donelson, Richard T |  | 26.03
PR | 995 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I |  | 133.28
PR | 995 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I |  | 199.92
PR | 995 | 02/04/22 | 72 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 02/04/22 | 99 | Donelson, Richard T |  | 26.03
PR | 995 | 02/11/22 | 215 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 02/11/22 | 217 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 02/18/22 | 488 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/18/22 | 549 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 02/18/22 | 549 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 02/18/22 | 564 | Sanders, Allen O |  | 23.74
PR | 995 | 02/18/22 | 577 | Donelson, Richard T |  | 26.03
PR | 995 | 02/25/22 | 708 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 02/25/22 | 709 | Barnhart, Joseph N |  | 24.16
PR | 995 | 02/25/22 | 763 | McCabe, Thomas C |  | 314.87
PR | 995 | 02/25/22 | 769 | Paco Leyva, Orlando |  | 62.48
PR | 995 | 02/25/22 | 780 | Romero Garza, Jesus I |  | 238.24
PR | 995 | 02/25/22 | 784 | Sanders, Allen O |  | 118.7
PR | 995 | 02/25/22 | 789 | Trower-Kelly, Fidel D |  | 259.9
PR | 995 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 83.3
PR | 995 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 03/04/22 | 101 | McCabe, Thomas C |  | 34.99
PR | 995 | 03/04/22 | 107 | Paco Leyva, Orlando |  | 83.3
PR | 995 | 03/04/22 | 118 | Romero Garza, Jesus I |  | 433.16
PR | 995 | 03/04/22 | 122 | Sanders, Allen O |  | 47.48
PR | 995 | 03/04/22 | 127 | Trower-Kelly, Fidel D |  | 433.16
PR | 995 | 03/11/22 | 340 | Balderas Ortiz, Ricardo I |  | 333.2
PR | 995 | 03/11/22 | 341 | Barnhart, Joseph N |  | 48.31
PR | 995 | 03/11/22 | 387 | Hubbard, Robert W |  | 69.97
PR | 995 | 03/11/22 | 404 | Paco Leyva, Orlando |  | 62.48
PR | 995 | 03/11/22 | 415 | Romero Garza, Jesus I |  | 433.16
PR | 995 | 03/11/22 | 419 | Sanders, Allen O |  | 166.18
PR | 995 | 03/11/22 | 424 | Trower-Kelly, Fidel D |  | 433.16
PR | 995 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I |  | 566.44
PR | 995 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I |  | 99.96
PR | 995 | 03/18/22 | 672 | Hubbard, Robert W |  | 23.32
PR | 995 | 03/18/22 | 689 | Paco Leyva, Orlando |  | 166.6
PR | 995 | 03/18/22 | 689 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 03/18/22 | 700 | Romero Garza, Jesus I |  | 259.9
PR | 995 | 03/18/22 | 704 | Sanders, Allen O |  | 130.57
PR | 995 | 03/18/22 | 709 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 03/25/22 | 874 | Balderas Ortiz, Ricardo I |  | 566.44
PR | 995 | 03/25/22 | 875 | Barnhart, Joseph N |  | 144.94
PR | 995 | 03/25/22 | 919 | Hubbard, Robert W |  | 46.65
PR | 995 | 03/25/22 | 936 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 03/25/22 | 936 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 03/25/22 | 946 | Romero Garza, Jesus I |  | 433.16
PR | 995 | 03/25/22 | 950 | Sanders, Allen O |  | 166.18
PR | 995 | 03/25/22 | 954 | Trower-Kelly, Fidel D |  | 422.33
PR | 995 | 03/25/22 | 962 | Donelson, Richard T |  | 26.03
PR | 995 | 04/01/22 | 20 | Balderas Ortiz, Ricardo I |  | 649.74
PR | 995 | 04/01/22 | 66 | Hubbard, Robert W |  | 23.32
PR | 995 | 04/01/22 | 66 | Hubbard, Robert W |  | 23.32
PR | 995 | 04/01/22 | 82 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 04/01/22 | 82 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 04/01/22 | 92 | Romero Garza, Jesus I |  | 433.16
PR | 995 | 04/01/22 | 96 | Sanders, Allen O |  | 71.22
PR | 995 | 04/01/22 | 100 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 04/01/22 | 108 | Donelson, Richard T |  | 78.09
PR | 995 | 04/01/22 | 109 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I |  | 566.44
PR | 995 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I |  | 33.32
PR | 995 | 04/08/22 | 247 | Eliassen, Cory H |  | 339.86
PR | 995 | 04/08/22 | 259 | Gonzalez Hernandez, Josue |  | 366.52
PR | 995 | 04/08/22 | 259 | Gonzalez Hernandez, Josue |  | 99.96
PR | 995 | 04/08/22 | 272 | Hubbard, Robert W |  | 23.32
PR | 995 | 04/08/22 | 276 | Johnson, Jake E |  | 20.83
PR | 995 | 04/08/22 | 288 | Paco Leyva, Orlando |  | 62.48
PR | 995 | 04/08/22 | 298 | Romero Garza, Jesus I |  | 259.9
PR | 995 | 04/08/22 | 302 | Sanders, Allen O |  | 106.83
PR | 995 | 04/08/22 | 306 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 04/08/22 | 314 | Donelson, Richard T |  | 26.03
PR | 995 | 04/15/22 | 474 | Balderas Ortiz, Ricardo I |  | 666.4
PR | 995 | 04/15/22 | 475 | Barnhart, Joseph N |  | 48.31
PR | 995 | 04/15/22 | 476 | Barnhart, Thomas L |  | 126.62
PR | 995 | 04/15/22 | 494 | Eliassen, Cory H |  | 283.22
PR | 995 | 04/15/22 | 506 | Gonzalez Hernandez, Josue |  | 366.52
PR | 995 | 04/15/22 | 506 | Gonzalez Hernandez, Josue |  | 33.32
PR | 995 | 04/15/22 | 519 | Hubbard, Robert W |  | 233.24
PR | 995 | 04/15/22 | 519 | Hubbard, Robert W |  | 46.65
PR | 995 | 04/15/22 | 535 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 04/15/22 | 549 | Sanders, Allen O |  | 284.89
PR | 995 | 04/15/22 | 553 | Trower-Kelly, Fidel D |  | 259.9
PR | 995 | 04/15/22 | 561 | Donelson, Richard T |  | 26.03
PR | 995 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 516.46
PR | 995 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 04/22/22 | 822 | Eliassen, Cory H |  | 453.15
PR | 995 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 333.2
PR | 995 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 149.94
PR | 995 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 66.64
PR | 995 | 04/22/22 | 847 | Hubbard, Robert W |  | 396.51
PR | 995 | 04/22/22 | 847 | Hubbard, Robert W |  | 46.65
PR | 995 | 04/22/22 | 851 | Johnson, Jake E |  | 20.83
PR | 995 | 04/22/22 | 863 | Paco Leyva, Orlando |  | 41.65
PR | 995 | 04/22/22 | 873 | Romero Garza, Jesus I |  | 173.26
PR | 995 | 04/22/22 | 877 | Sanders, Allen O |  | 332.37
PR | 995 | 04/22/22 | 881 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 04/22/22 | 889 | Donelson, Richard T |  | 26.03
PR | 995 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 233.24
PR | 995 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 366.52
PR | 995 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 04/29/22 | 1082 | Eliassen, Cory H |  | 509.8
PR | 995 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 299.88
PR | 995 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 66.64
PR | 995 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 99.96
PR | 995 | 04/29/22 | 1107 | Hubbard, Robert W |  | 151.61
PR | 995 | 04/29/22 | 1107 | Hubbard, Robert W |  | 46.65
PR | 995 | 04/29/22 | 1111 | Johnson, Jake E |  | 41.65
PR | 995 | 04/29/22 | 1124 | Paco Leyva, Orlando |  | 20.83
PR | 995 | 04/29/22 | 1134 | Romero Garza, Jesus I |  | 433.16
PR | 995 | 04/29/22 | 1137 | Sanders, Allen O |  | 201.79
PR | 995 | 04/29/22 | 1141 | Trower-Kelly, Fidel D |  | 433.16
PR | 995 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 199.92
PR | 995 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 199.92
PR | 995 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 299.88
PR | 995 | 05/06/22 | 95 | Boss, Kyle A |  | 81.22
PR | 995 | 05/06/22 | 107 | Eliassen, Cory H |  | 106.21
PR | 995 | 05/06/22 | 107 | Eliassen, Cory H |  | 566.44
PR | 995 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 116.62
PR | 995 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 66.64
PR | 995 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 49.98
PR | 995 | 05/06/22 | 131 | Hubbard, Robert W |  | 163.27
PR | 995 | 05/06/22 | 131 | Hubbard, Robert W |  | 23.32
PR | 995 | 05/06/22 | 131 | Hubbard, Robert W |  | 69.97
PR | 995 | 05/06/22 | 148 | Paco Leyva, Orlando |  | 249.9
PR | 995 | 05/06/22 | 158 | Romero Garza, Jesus I |  | 81.22
PR | 995 | 05/06/22 | 158 | Romero Garza, Jesus I |  | 173.26
PR | 995 | 05/06/22 | 160 | Sanders, Allen O |  | 142.44
PR | 995 | 05/06/22 | 160 | Sanders, Allen O |  | 308.63
PR | 995 | 05/06/22 | 160 | Sanders, Allen O |  | 71.22
PR | 995 | 05/06/22 | 163 | Taylor, Evan R |  | 77.05
PR | 995 | 05/06/22 | 164 | Trower-Kelly, Fidel D |  | 346.53
PR | 995 | 05/06/22 | 164 | Trower-Kelly, Fidel D |  | 54.15
PR | 995 | 05/13/22 | 323 | Balderas Ortiz, Ricardo I |  | 66.64
PR | 995 | 05/13/22 | 328 | Boss, Benjamin T |  | 78.09
PR | 995 | 05/13/22 | 329 | Boss, Kyle A |  | -81.22
PR | 995 | 05/13/22 | 342 | Eliassen, Cory H |  | 566.44
PR | 995 | 05/13/22 | 366 | Hubbard, Robert W |  | 186.59
PR | 995 | 05/13/22 | 370 | Johnson, Jake E |  | 20.83
PR | 995 | 05/13/22 | 396 | Sanders, Allen O |  | 379.85
PR | 995 | 05/20/22 | 616 | Eliassen, Cory H |  | 14.58
PR | 995 | 05/20/22 | 669 | Sanders, Allen O |  | 159.73
PR | 995 | 05/20/22 | 681 | Donelson, Richard T |  | 26.03
PR | 995 | 05/27/22 | 937 | Sanders, Allen O |  | 122.87
PR | 995 | 06/03/22 | 56 | Johnson, Jake E |  | 20.83
PR | 995 | 06/03/22 | 93 | Donelson, Richard T |  | 26.03
PR | 995 | 06/10/22 | 289 | Sanders, Allen O |  | 98.29
PR | 995 | 06/10/22 | 301 | Donelson, Richard T |  | 104.13
PR | 995 | 06/17/22 | 537 | Sanders, Allen O |  | 49.15
PR | 995 | 07/01/22 | 31 | Eliassen, Cory H |  | 29.16
PR | 998 | 10/25/19 | 664 | Donelson, Richard T |  | 19.13
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 4.78
PR | 998 | 11/08/19 | 253 | Donelson, Richard T |  | 4.78
PR | 998 | 11/15/19 | 512 | Donelson, Richard T |  | 4.78
PR | 998 | 04/24/20 | 424 | Donelson, Richard T |  | 9.56
PR | 998 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/14/20 | 332 | Donelson, Richard T |  | 14.34
PR | 998 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/28/20 | 604 | Donelson, Richard T |  | 4.78
PR | 998 | 09/11/20 | 120 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 09/25/20 | 479 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 10/02/20 | 52 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 10/16/20 | 339 | Donelson, Richard T |  | 4.78
PR | 998 | 10/16/20 | 340 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 10/23/20 | 482 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 10/30/20 | 637 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 11/06/20 | 15 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/06/20 | 59 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/06/20 | 59 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/13/20 | 231 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 11/20/20 | 388 | Donelson, Richard T |  | 9.56
PR | 998 | 11/20/20 | 389 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/25/20 | 456 | Barnhart, Joseph N |  | 12.39
PR | 998 | 12/04/20 | 7 | Barnhart, Joseph N |  | 78.49
PR | 998 | 12/04/20 | 31 | Martinez Reyes, Juan C |  | 39.63
PR | 998 | 12/04/20 | 51 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/04/20 | 51 | Gerard, Jeffrey S |  | 6.66
PR | 998 | 12/11/20 | 183 | Barnhart, Joseph N |  | 57.83
PR | 998 | 12/11/20 | 224 | Donelson, Richard T |  | 4.78
PR | 998 | 12/11/20 | 225 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/11/20 | 225 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/18/20 | 344 | Barnhart, Joseph N |  | 8.26
PR | 998 | 12/18/20 | 344 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/18/20 | 387 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/23/20 | 485 | Barnhart, Joseph N |  | 16.52
PR | 998 | 12/23/20 | 529 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/31/20 | 581 | Anderson, Richard P |  | 59.98
PR | 998 | 12/31/20 | 585 | Barnhart, Joseph N |  | 8.26
PR | 998 | 12/31/20 | 609 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 12/31/20 | 627 | Donelson, Richard T |  | 4.78
PR | 998 | 12/31/20 | 628 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/08/21 | 4 | Anderson, Richard P |  | 104.96
PR | 998 | 01/08/21 | 32 | Martinez Reyes, Juan C |  | 79.25
PR | 998 | 01/08/21 | 52 | Donelson, Richard T |  | 4.78
PR | 998 | 01/08/21 | 53 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/08/21 | 53 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/15/21 | 117 | Anderson, Richard P |  | 7.5
PR | 998 | 01/15/21 | 146 | Martinez Reyes, Juan C |  | 5.66
PR | 998 | 01/15/21 | 171 | Donelson, Richard T |  | 9.56
PR | 998 | 01/29/21 | 386 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/29/21 | 386 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/29/21 | 433 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/05/21 | 67 | Anderson, Richard P |  | 29.99
PR | 998 | 02/05/21 | 99 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/05/21 | 122 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/12/21 | 252 | Anderson, Richard P |  | 56.23
PR | 998 | 02/12/21 | 285 | Martinez Reyes, Juan C |  | 11.32
PR | 998 | 02/12/21 | 308 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/19/21 | 416 | Anderson, Richard P |  | 5.62
PR | 998 | 02/19/21 | 474 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/26/21 | 593 | Anderson, Richard P |  | 89.96
PR | 998 | 02/26/21 | 597 | Barnhart, Joseph N |  | 4.13
PR | 998 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 59.44
PR | 998 | 03/05/21 | 52 | Anderson, Richard P |  | 52.48
PR | 998 | 03/05/21 | 56 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/05/21 | 87 | Martinez Reyes, Juan C |  | 11.32
PR | 998 | 03/05/21 | 107 | Donelson, Richard T |  | 4.78
PR | 998 | 03/05/21 | 108 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/12/21 | 233 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/12/21 | 233 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/19/21 | 287 | Anderson, Richard P |  | 85.83
PR | 998 | 03/19/21 | 300 | Cortes Sepulveda, Jose R |  | 38.56
PR | 998 | 03/19/21 | 327 | Martinez Reyes, Juan C |  | 65.64
PR | 998 | 03/26/21 | 518 | Anderson, Richard P |  | 23.41
PR | 998 | 03/26/21 | 522 | Barnhart, Joseph N |  | 8.57
PR | 998 | 03/26/21 | 528 | Chevez, Herson G |  | 17.14
PR | 998 | 03/26/21 | 558 | Martinez Reyes, Juan C |  | 17.9
PR | 998 | 03/26/21 | 562 | Paco Leyva, Orlando |  | 17.98
PR | 998 | 04/02/21 | 7 | Barnhart, Joseph N |  | 4.28
PR | 998 | 04/02/21 | 13 | Chevez, Herson G |  | 10.71
PR | 998 | 04/02/21 | 25 | Galdamez, Dagoberto A |  | 16.07
PR | 998 | 04/02/21 | 47 | Paco Leyva, Orlando |  | 46.74
PR | 998 | 04/02/21 | 50 | Ramos Herrera, Franklin J |  | 10.1
PR | 998 | 04/02/21 | 64 | Donelson, Richard T |  | 4.78
PR | 998 | 04/09/21 | 110 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/09/21 | 128 | Galdamez, Dagoberto A |  | 21.42
PR | 998 | 04/09/21 | 151 | Paco Leyva, Orlando |  | 14.38
PR | 998 | 04/09/21 | 168 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I |  | 58.14
PR | 998 | 04/16/21 | 251 | Balderas Ortiz, Ricardo I |  | 11.63
PR | 998 | 04/16/21 | 253 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/16/21 | 253 | Barnhart, Joseph N |  | 4.28
PR | 998 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 32.13
PR | 998 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 10.71
PR | 998 | 04/16/21 | 272 | Galdamez, Dagoberto A |  | 21.42
PR | 998 | 04/16/21 | 296 | Paco Leyva, Orlando |  | 53.93
PR | 998 | 04/16/21 | 315 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 04/23/21 | 402 | Balderas Ortiz, Ricardo I |  | 46.51
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 19.28
PR | 998 | 04/23/21 | 415 | Cruz Guzman, Joel A |  | 93.64
PR | 998 | 04/23/21 | 423 | Galdamez, Dagoberto A |  | 64.26
PR | 998 | 04/23/21 | 431 | Guerrero Espinoza, Mario |  | 13.46
PR | 998 | 04/23/21 | 431 | Guerrero Espinoza, Mario |  | 26.93
PR | 998 | 04/23/21 | 440 | Lopez, Maslin A |  | 36.72
PR | 998 | 04/23/21 | 440 | Lopez, Maslin A |  | 25.7
PR | 998 | 04/23/21 | 447 | Paco Leyva, Orlando |  | 43.15
PR | 998 | 04/23/21 | 447 | Paco Leyva, Orlando |  | 14.38
PR | 998 | 04/23/21 | 451 | Ramos Herrera, Franklin J |  | 40.39
PR | 998 | 04/23/21 | 466 | Donelson, Richard T |  | 4.78
PR | 998 | 04/23/21 | 467 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 04/23/21 | 467 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 04/30/21 | 572 | Balderas Ortiz, Ricardo I |  | 46.51
PR | 998 | 04/30/21 | 574 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/30/21 | 585 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 04/30/21 | 593 | Galdamez, Dagoberto A |  | 107.1
PR | 998 | 04/30/21 | 601 | Guerrero Espinoza, Mario |  | 57.22
PR | 998 | 04/30/21 | 601 | Guerrero Espinoza, Mario |  | 10.1
PR | 998 | 04/30/21 | 610 | Lopez, Maslin A |  | 38.56
PR | 998 | 04/30/21 | 610 | Lopez, Maslin A |  | 14.69
PR | 998 | 04/30/21 | 610 | Lopez, Maslin A |  | 5.51
PR | 998 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 93.48
PR | 998 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 21.57
PR | 998 | 04/30/21 | 618 | Paco Leyva, Orlando |  | 7.19
PR | 998 | 04/30/21 | 622 | Ramos Herrera, Franklin J |  | 20.2
PR | 998 | 04/30/21 | 638 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 8.57
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/07/21 | 51 | Cruz Gonzalez, Julio C |  | 73.44
PR | 998 | 05/07/21 | 51 | Cruz Gonzalez, Julio C |  | 18.36
PR | 998 | 05/07/21 | 52 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 05/07/21 | 60 | Galdamez, Dagoberto A |  | 10.71
PR | 998 | 05/07/21 | 60 | Galdamez, Dagoberto A |  | 10.71
PR | 998 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 26.93
PR | 998 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 33.66
PR | 998 | 05/07/21 | 68 | Guerrero Espinoza, Mario |  | 6.73
PR | 998 | 05/07/21 | 78 | Lopez, Maslin A |  | 29.38
PR | 998 | 05/07/21 | 78 | Lopez, Maslin A |  | 36.72
PR | 998 | 05/07/21 | 78 | Lopez, Maslin A |  | 7.34
PR | 998 | 05/07/21 | 86 | Paco Leyva, Orlando |  | 43.15
PR | 998 | 05/07/21 | 86 | Paco Leyva, Orlando |  | 32.36
PR | 998 | 05/07/21 | 90 | Ramos Herrera, Franklin J |  | 20.2
PR | 998 | 05/07/21 | 106 | Donelson, Richard T |  | 4.78
PR | 998 | 05/07/21 | 107 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 05/07/21 | 107 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 05/14/21 | 246 | Barnhart, Joseph N |  | 8.57
PR | 998 | 05/14/21 | 255 | Cruz Gonzalez, Julio C |  | 55.08
PR | 998 | 05/14/21 | 255 | Cruz Gonzalez, Julio C |  | 36.72
PR | 998 | 05/14/21 | 256 | Cruz Guzman, Joel A |  | 65.03
PR | 998 | 05/14/21 | 256 | Cruz Guzman, Joel A |  | 39.02
PR | 998 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 50.49
PR | 998 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 10.1
PR | 998 | 05/14/21 | 272 | Guerrero Espinoza, Mario |  | 6.73
PR | 998 | 05/14/21 | 288 | Mendoza Morales, Jesus A |  | 83.23
PR | 998 | 05/14/21 | 288 | Mendoza Morales, Jesus A |  | 20.81
PR | 998 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 35.96
PR | 998 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 14.38
PR | 998 | 05/14/21 | 290 | Paco Leyva, Orlando |  | 21.57
PR | 998 | 05/14/21 | 311 | Gerard, Jeffrey S |  | 9.18
PR | 998 | 05/14/21 | 311 | Gerard, Jeffrey S |  | 9.18
PR | 998 | 05/21/21 | 391 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/21/21 | 394 | Boss, Benjamin T |  | 3.37
PR | 998 | 05/21/21 | 395 | Boss, Kyle A |  | 3.52
PR | 998 | 05/21/21 | 400 | Cruz Gonzalez, Julio C |  | 82.62
PR | 998 | 05/21/21 | 400 | Cruz Gonzalez, Julio C |  | 9.18
PR | 998 | 05/21/21 | 401 | Cruz Guzman, Joel A |  | 83.23
PR | 998 | 05/21/21 | 401 | Cruz Guzman, Joel A |  | 20.81
PR | 998 | 05/21/21 | 405 | Eisenhauer, Tommy J |  | 6.73
PR | 998 | 05/21/21 | 417 | Guerrero Espinoza, Mario |  | 40.39
PR | 998 | 05/21/21 | 417 | Guerrero Espinoza, Mario |  | 13.46
PR | 998 | 05/21/21 | 434 | Mendoza Morales, Jesus A |  | 104.04
PR | 998 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 35.96
PR | 998 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 17.98
PR | 998 | 05/21/21 | 436 | Paco Leyva, Orlando |  | 7.19
PR | 998 | 05/21/21 | 444 | Romero Garza, Jesus I |  | 73.44
PR | 998 | 05/21/21 | 451 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 05/21/21 | 457 | Gerard, Jeffrey S |  | 13.77
PR | 998 | 05/28/21 | 632 | Barnhart, Joseph N |  | 8.57
PR | 998 | 05/28/21 | 641 | Cruz Gonzalez, Julio C |  | 87.21
PR | 998 | 05/28/21 | 641 | Cruz Gonzalez, Julio C |  | 4.59
PR | 998 | 05/28/21 | 642 | Cruz Guzman, Joel A |  | 62.42
PR | 998 | 05/28/21 | 642 | Cruz Guzman, Joel A |  | 41.62
PR | 998 | 05/28/21 | 643 | Cruz Reyes, Jose |  | 83.23
PR | 998 | 05/28/21 | 658 | Guerrero Espinoza, Mario |  | 40.39
PR | 998 | 05/28/21 | 658 | Guerrero Espinoza, Mario |  | 26.93
PR | 998 | 05/28/21 | 665 | Hubbard, Robert W |  | 12.62
PR | 998 | 05/28/21 | 675 | Mendoza Morales, Jesus A |  | 104.04
PR | 998 | 05/28/21 | 678 | Paco Leyva, Orlando |  | 7.19
PR | 998 | 05/28/21 | 678 | Paco Leyva, Orlando |  | 14.38
PR | 998 | 05/28/21 | 687 | Romero Garza, Jesus I |  | 73.44
PR | 998 | 05/28/21 | 694 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 05/28/21 | 701 | Gerard, Jeffrey S |  | 9.18
PR | 998 | 06/04/21 | 26 | Ascencio, Jose L |  | 83.23
PR | 998 | 06/04/21 | 29 | Barnhart, Joseph N |  | 8.57
PR | 998 | 06/04/21 | 40 | Cruz Gonzalez, Julio C |  | 36.72
PR | 998 | 06/04/21 | 41 | Cruz Guzman, Joel A |  | 83.23
PR | 998 | 06/04/21 | 43 | Cruz Reyes, Jose |  | 41.62
PR | 998 | 06/04/21 | 58 | Guerrero Espinoza, Mario |  | 13.46
PR | 998 | 06/04/21 | 65 | Hubbard, Robert W |  | 8.42
PR | 998 | 06/04/21 | 65 | Hubbard, Robert W |  | 4.21
PR | 998 | 06/04/21 | 79 | Paco Leyva, Orlando |  | 25.17
PR | 998 | 06/04/21 | 89 | Sanders, Allen O |  | 4.21
PR | 998 | 06/04/21 | 94 | Trower-Kelly, Fidel D |  | 58.75
PR | 998 | 06/04/21 | 99 | Donelson, Richard T |  | 9.56
PR | 998 | 06/04/21 | 100 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 06/11/21 | 200 | Ascencio, Jose L |  | 104.04
PR | 998 | 06/11/21 | 201 | Balderas Ortiz, Ricardo I |  | 23.26
PR | 998 | 06/11/21 | 214 | Cruz Gonzalez, Julio C |  | 36.72
PR | 998 | 06/11/21 | 214 | Cruz Gonzalez, Julio C |  | 36.72
PR | 998 | 06/11/21 | 215 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 06/11/21 | 216 | Cruz Reyes, Jose |  | 104.04
PR | 998 | 06/11/21 | 231 | Guerrero Espinoza, Mario |  | 53.86
PR | 998 | 06/11/21 | 247 | Mendoza Morales, Jesus A |  | 62.42
PR | 998 | 06/11/21 | 251 | Paco Leyva, Orlando |  | 35.96
PR | 998 | 06/11/21 | 256 | Ramos Herrera, Franklin J |  | 20.2
PR | 998 | 06/11/21 | 266 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 06/18/21 | 402 | Ascencio, Jose L |  | 62.42
PR | 998 | 06/18/21 | 405 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/18/21 | 410 | Castro Hernandez, Jose A |  | 53.86
PR | 998 | 06/18/21 | 416 | Cruz Gonzalez, Julio C |  | 55.08
PR | 998 | 06/18/21 | 417 | Cruz Guzman, Joel A |  | 83.23
PR | 998 | 06/18/21 | 418 | Cruz Reyes, Jose |  | 62.42
PR | 998 | 06/18/21 | 433 | Guerrero Espinoza, Mario |  | 67.32
PR | 998 | 06/18/21 | 446 | Lucas Tzintzun, Rafael |  | 31.82
PR | 998 | 06/18/21 | 449 | Mendoza Morales, Jesus A |  | 41.62
PR | 998 | 06/18/21 | 453 | Paco Leyva, Orlando |  | 64.72
PR | 998 | 06/18/21 | 453 | Paco Leyva, Orlando |  | 7.19
PR | 998 | 06/18/21 | 463 | Ross, Kelli M |  | 9.87
PR | 998 | 06/18/21 | 469 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 06/18/21 | 476 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 06/25/21 | 597 | Ascencio, Jose L |  | 104.04
PR | 998 | 06/25/21 | 600 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/25/21 | 611 | Cruz Gonzalez, Julio C |  | 91.8
PR | 998 | 06/25/21 | 612 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 06/25/21 | 613 | Cruz Reyes, Jose |  | 104.04
PR | 998 | 06/25/21 | 628 | Guerrero Espinoza, Mario |  | 62.27
PR | 998 | 06/25/21 | 631 | Hawkins, Conor L |  | 41.62
PR | 998 | 06/25/21 | 641 | Lucas Tzintzun, Rafael |  | 63.65
PR | 998 | 06/25/21 | 648 | Paco Leyva, Orlando |  | 50.34
PR | 998 | 06/25/21 | 648 | Paco Leyva, Orlando |  | 10.79
PR | 998 | 06/25/21 | 664 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 06/25/21 | 673 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 07/02/21 | 6 | Ascencio, Jose L |  | 100.14
PR | 998 | 07/02/21 | 9 | Barnhart, Joseph N |  | 4.28
PR | 998 | 07/02/21 | 20 | Cruz Gonzalez, Julio C |  | 70
PR | 998 | 07/02/21 | 21 | Cruz Guzman, Joel A |  | 100.14
PR | 998 | 07/02/21 | 22 | Cruz Reyes, Jose |  | 100.14
PR | 998 | 07/02/21 | 37 | Guerrero Espinoza, Mario |  | 37.87
PR | 998 | 07/02/21 | 38 | Hawkins, Conor L |  | 31.21
PR | 998 | 07/02/21 | 42 | Hubbard, Robert W |  | 8.42
PR | 998 | 07/02/21 | 48 | Lucas Tzintzun, Rafael |  | 60.66
PR | 998 | 07/02/21 | 56 | Paco Leyva, Orlando |  | 53.93
PR | 998 | 07/02/21 | 56 | Paco Leyva, Orlando |  | 3.6
PR | 998 | 07/02/21 | 72 | Trower-Kelly, Fidel D |  | 67.93
PR | 998 | 07/02/21 | 78 | Donelson, Richard T |  | 4.78
PR | 998 | 07/09/21 | 101 | Ascencio, Jose L |  | 83.23
PR | 998 | 07/09/21 | 115 | Cruz Gonzalez, Julio C |  | 73.44
PR | 998 | 07/09/21 | 116 | Cruz Guzman, Joel A |  | 83.23
PR | 998 | 07/09/21 | 117 | Cruz Reyes, Jose |  | 83.23
PR | 998 | 07/09/21 | 132 | Guerrero Espinoza, Mario |  | 53.86
PR | 998 | 07/09/21 | 143 | Lucas Tzintzun, Rafael |  | 63.65
PR | 998 | 07/09/21 | 151 | Paco Leyva, Orlando |  | 43.15
PR | 998 | 07/09/21 | 151 | Paco Leyva, Orlando |  | 3.6
PR | 998 | 07/09/21 | 157 | Reed, Reuben H |  | 31.21
PR | 998 | 07/09/21 | 169 | Trower-Kelly, Fidel D |  | 29.38
PR | 998 | 07/09/21 | 176 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 07/16/21 | 319 | Ascencio, Jose L |  | 104.04
PR | 998 | 07/16/21 | 333 | Cruz Gonzalez, Julio C |  | 27.54
PR | 998 | 07/16/21 | 333 | Cruz Gonzalez, Julio C |  | 9.18
PR | 998 | 07/16/21 | 334 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 07/16/21 | 335 | Cruz Reyes, Jose |  | 104.04
PR | 998 | 07/16/21 | 350 | Guerrero Espinoza, Mario |  | 53.86
PR | 998 | 07/16/21 | 361 | Lucas Tzintzun, Rafael |  | 31.82
PR | 998 | 07/16/21 | 369 | Paco Leyva, Orlando |  | 53.93
PR | 998 | 07/16/21 | 369 | Paco Leyva, Orlando |  | 14.38
PR | 998 | 07/16/21 | 387 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 07/23/21 | 489 | Ascencio, Jose L |  | 83.23
PR | 998 | 07/23/21 | 504 | Cruz Gonzalez, Julio C |  | 63.11
PR | 998 | 07/23/21 | 504 | Cruz Gonzalez, Julio C |  | 22.95
PR | 998 | 07/23/21 | 505 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 07/23/21 | 506 | Cruz Reyes, Jose |  | 41.62
PR | 998 | 07/23/21 | 521 | Guerrero Espinoza, Mario |  | 53.86
PR | 998 | 07/23/21 | 527 | Hubbard, Robert W |  | 8.42
PR | 998 | 07/23/21 | 541 | Paco Leyva, Orlando |  | 50.34
PR | 998 | 07/23/21 | 541 | Paco Leyva, Orlando |  | 3.6
PR | 998 | 07/23/21 | 559 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 07/30/21 | 680 | Ascencio, Jose L |  | 104.04
PR | 998 | 07/30/21 | 696 | Cruz Gonzalez, Julio C |  | 55.08
PR | 998 | 07/30/21 | 696 | Cruz Gonzalez, Julio C |  | 18.36
PR | 998 | 07/30/21 | 697 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 07/30/21 | 698 | Cruz Reyes, Jose |  | 62.42
PR | 998 | 07/30/21 | 713 | Guerrero Espinoza, Mario |  | 67.32
PR | 998 | 07/30/21 | 734 | Paco Leyva, Orlando |  | 17.98
PR | 998 | 07/30/21 | 734 | Paco Leyva, Orlando |  | 28.76
PR | 998 | 07/30/21 | 751 | Trower-Kelly, Fidel D |  | 58.75
PR | 998 | 07/30/21 | 758 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 07/30/21 | 758 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 08/06/21 | 40 | Ascencio, Jose L |  | 104.04
PR | 998 | 08/06/21 | 56 | Cruz Gonzalez, Julio C |  | 73.44
PR | 998 | 08/06/21 | 57 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 08/06/21 | 70 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 08/06/21 | 70 | Gonzalez Hernandez, Josue |  | 23.26
PR | 998 | 08/06/21 | 72 | Guerrero Espinoza, Mario |  | 53.86
PR | 998 | 08/06/21 | 79 | Hubbard, Robert W |  | 12.62
PR | 998 | 08/06/21 | 93 | Paco Leyva, Orlando |  | 17.98
PR | 998 | 08/06/21 | 110 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 08/13/21 | 302 | Ascencio, Jose L |  | 41.62
PR | 998 | 08/13/21 | 306 | Barnhart, Joseph N |  | 21.42
PR | 998 | 08/13/21 | 318 | Cruz Gonzalez, Julio C |  | 18.36
PR | 998 | 08/13/21 | 318 | Cruz Gonzalez, Julio C |  | 18.36
PR | 998 | 08/13/21 | 319 | Cruz Guzman, Joel A |  | 41.62
PR | 998 | 08/13/21 | 332 | Gonzalez Hernandez, Josue |  | 11.63
PR | 998 | 08/13/21 | 332 | Gonzalez Hernandez, Josue |  | 11.63
PR | 998 | 08/13/21 | 334 | Guerrero Espinoza, Mario |  | 70.38
PR | 998 | 08/13/21 | 341 | Hubbard, Robert W |  | 12.62
PR | 998 | 08/13/21 | 341 | Hubbard, Robert W |  | 12.62
PR | 998 | 08/13/21 | 355 | Paco Leyva, Orlando |  | 39.55
PR | 998 | 08/13/21 | 371 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 08/13/21 | 379 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 08/20/21 | 583 | Ascencio, Jose L |  | 62.42
PR | 998 | 08/20/21 | 599 | Cruz Gonzalez, Julio C |  | 91.8
PR | 998 | 08/20/21 | 600 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 08/20/21 | 614 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 08/20/21 | 616 | Guerrero Espinoza, Mario |  | 70.38
PR | 998 | 08/20/21 | 623 | Hubbard, Robert W |  | 16.83
PR | 998 | 08/20/21 | 638 | Paco Leyva, Orlando |  | 32.36
PR | 998 | 08/20/21 | 654 | Trower-Kelly, Fidel D |  | 44.06
PR | 998 | 08/20/21 | 662 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 08/20/21 | 662 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 08/27/21 | 804 | Ascencio, Jose L |  | 104.04
PR | 998 | 08/27/21 | 807 | Barnhart, Joseph N |  | 12.85
PR | 998 | 08/27/21 | 820 | Cruz Gonzalez, Julio C |  | 55.08
PR | 998 | 08/27/21 | 820 | Cruz Gonzalez, Julio C |  | 18.36
PR | 998 | 08/27/21 | 821 | Cruz Guzman, Joel A |  | 104.04
PR | 998 | 08/27/21 | 835 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 08/27/21 | 837 | Guerrero Espinoza, Mario |  | 70.38
PR | 998 | 08/27/21 | 844 | Hubbard, Robert W |  | 67.32
PR | 998 | 08/27/21 | 844 | Hubbard, Robert W |  | 8.42
PR | 998 | 08/27/21 | 858 | Paco Leyva, Orlando |  | 21.57
PR | 998 | 08/27/21 | 869 | Ross, Kelli M |  | 131.58
PR | 998 | 08/27/21 | 875 | Trower-Kelly, Fidel D |  | 73.44
PR | 998 | 08/27/21 | 881 | Young, Joshua S |  | 46.51
PR | 998 | 08/27/21 | 883 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 09/03/21 | 5 | Ascencio, Jose L |  | 104.04
PR | 998 | 09/03/21 | 8 | Barnhart, Joseph N |  | 21.42
PR | 998 | 09/03/21 | 21 | Cruz Gonzalez, Julio C |  | 36.72
PR | 998 | 09/03/21 | 22 | Cruz Guzman, Joel A |  | 83.23
PR | 998 | 09/03/21 | 37 | Gonzalez Hernandez, Josue |  | 11.63
PR | 998 | 09/03/21 | 39 | Guerrero Espinoza, Mario |  | 70.38
PR | 998 | 09/03/21 | 46 | Hubbard, Robert W |  | 8.42
PR | 998 | 09/03/21 | 46 | Hubbard, Robert W |  | 12.62
PR | 998 | 09/03/21 | 60 | Paco Leyva, Orlando |  | 39.55
PR | 998 | 09/03/21 | 72 | Ross, Kelli M |  | 78.95
PR | 998 | 09/03/21 | 78 | Trower-Kelly, Fidel D |  | 58.75
PR | 998 | 09/03/21 | 87 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 09/10/21 | 173 | Ascencio, Jose L |  | 88.13
PR | 998 | 09/10/21 | 176 | Barnhart, Joseph N |  | 22.19
PR | 998 | 09/10/21 | 189 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 09/10/21 | 190 | Cruz Guzman, Joel A |  | 67.93
PR | 998 | 09/10/21 | 205 | Gonzalez Hernandez, Josue |  | 48.96
PR | 998 | 09/10/21 | 207 | Guerrero Espinoza, Mario |  | 43.99
PR | 998 | 09/10/21 | 214 | Hubbard, Robert W |  | 8.57
PR | 998 | 09/10/21 | 228 | Paco Leyva, Orlando |  | 61.2
PR | 998 | 09/10/21 | 241 | Ross, Kelli M |  | 55.08
PR | 998 | 09/10/21 | 247 | Trower-Kelly, Fidel D |  | 15.91
PR | 998 | 09/10/21 | 247 | Trower-Kelly, Fidel D |  | 15.91
PR | 998 | 09/10/21 | 254 | Donelson, Richard T |  | 4.78
PR | 998 | 09/17/21 | 335 | Ascencio, Jose L |  | 110.16
PR | 998 | 09/17/21 | 338 | Barnhart, Joseph N |  | 26.62
PR | 998 | 09/17/21 | 351 | Cruz Gonzalez, Julio C |  | 58.75
PR | 998 | 09/17/21 | 351 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 09/17/21 | 352 | Cruz Guzman, Joel A |  | 113.22
PR | 998 | 09/17/21 | 367 | Gonzalez Hernandez, Josue |  | 73.44
PR | 998 | 09/17/21 | 367 | Gonzalez Hernandez, Josue |  | 48.96
PR | 998 | 09/17/21 | 369 | Guerrero Espinoza, Mario |  | 76.5
PR | 998 | 09/17/21 | 376 | Hubbard, Robert W |  | 8.57
PR | 998 | 09/17/21 | 390 | Paco Leyva, Orlando |  | 30.6
PR | 998 | 09/17/21 | 409 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 09/24/21 | 489 | Ascencio, Jose L |  | 88.13
PR | 998 | 09/24/21 | 490 | Balderas Ortiz, Ricardo I |  | 24.48
PR | 998 | 09/24/21 | 492 | Barnhart, Joseph N |  | 39.93
PR | 998 | 09/24/21 | 505 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 09/24/21 | 505 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 09/24/21 | 506 | Cruz Guzman, Joel A |  | 90.58
PR | 998 | 09/24/21 | 506 | Cruz Guzman, Joel A |  | 22.64
PR | 998 | 09/24/21 | 516 | Galdamez, Dagoberto A |  | 22.64
PR | 998 | 09/24/21 | 521 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 09/24/21 | 521 | Gonzalez Hernandez, Josue |  | 16.83
PR | 998 | 09/24/21 | 523 | Guerrero Espinoza, Mario |  | 76.5
PR | 998 | 09/24/21 | 530 | Hubbard, Robert W |  | 12.85
PR | 998 | 09/24/21 | 534 | Lopez, Maslin A |  | 16.52
PR | 998 | 09/24/21 | 540 | Mendoza Morales, Jesus A |  | 22.03
PR | 998 | 09/24/21 | 544 | Paco Leyva, Orlando |  | 72.68
PR | 998 | 09/24/21 | 544 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 09/24/21 | 551 | Ramos Herrera, Franklin J |  | 22.03
PR | 998 | 09/24/21 | 564 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 09/24/21 | 570 | Young, Joshua S |  | 12.85
PR | 998 | 10/01/21 | 6 | Ascencio, Jose L |  | 33.05
PR | 998 | 10/01/21 | 6 | Ascencio, Jose L |  | 88.13
PR | 998 | 10/01/21 | 9 | Barnhart, Joseph N |  | 22.19
PR | 998 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 27.54
PR | 998 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 22.03
PR | 998 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 31.82
PR | 998 | 10/01/21 | 22 | Cruz Gonzalez, Julio C |  | 66.1
PR | 998 | 10/01/21 | 23 | Cruz Guzman, Joel A |  | 42.46
PR | 998 | 10/01/21 | 23 | Cruz Guzman, Joel A |  | 113.22
PR | 998 | 10/01/21 | 40 | Guerrero Espinoza, Mario |  | 22.95
PR | 998 | 10/01/21 | 40 | Guerrero Espinoza, Mario |  | 76.5
PR | 998 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 34.43
PR | 998 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 17.21
PR | 998 | 10/01/21 | 61 | Paco Leyva, Orlando |  | 68.85
PR | 998 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 35.8
PR | 998 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 11.93
PR | 998 | 10/01/21 | 81 | Trower-Kelly, Fidel D |  | 79.56
PR | 998 | 10/01/21 | 88 | Donelson, Richard T |  | 4.78
PR | 998 | 10/08/21 | 294 | Ascencio, Jose L |  | 33.05
PR | 998 | 10/08/21 | 294 | Ascencio, Jose L |  | 110.16
PR | 998 | 10/08/21 | 297 | Barnhart, Joseph N |  | 31.06
PR | 998 | 10/08/21 | 311 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 10/08/21 | 312 | Cruz Guzman, Joel A |  | 107.56
PR | 998 | 10/08/21 | 354 | Paco Leyva, Orlando |  | 91.8
PR | 998 | 10/08/21 | 362 | Reed, Reuben H |  | -31.21
PR | 998 | 10/08/21 | 374 | Trower-Kelly, Fidel D |  | 75.58
PR | 998 | 10/15/21 | 558 | Ascencio, Jose L |  | 33.05
PR | 998 | 10/15/21 | 558 | Ascencio, Jose L |  | 110.16
PR | 998 | 10/15/21 | 561 | Barnhart, Joseph N |  | 4.44
PR | 998 | 10/15/21 | 575 | Cruz Gonzalez, Julio C |  | 73.44
PR | 998 | 10/15/21 | 576 | Cruz Guzman, Joel A |  | 33.97
PR | 998 | 10/15/21 | 576 | Cruz Guzman, Joel A |  | 113.22
PR | 998 | 10/15/21 | 618 | Paco Leyva, Orlando |  | 22.95
PR | 998 | 10/15/21 | 618 | Paco Leyva, Orlando |  | 72.68
PR | 998 | 10/15/21 | 628 | Robles Arroyo, Alonso |  | 19.28
PR | 998 | 10/15/21 | 628 | Robles Arroyo, Alonso |  | 64.26
PR | 998 | 10/22/21 | 744 | Ascencio, Jose L |  | 110.16
PR | 998 | 10/22/21 | 748 | Barnhart, Joseph N |  | 13.31
PR | 998 | 10/22/21 | 763 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 10/22/21 | 764 | Cruz Guzman, Joel A |  | 84.92
PR | 998 | 10/22/21 | 764 | Cruz Guzman, Joel A |  | 5.66
PR | 998 | 10/22/21 | 790 | Herrera Hernandez, Manuel L |  | 23.26
PR | 998 | 10/22/21 | 794 | Hubbard, Robert W |  | 4.28
PR | 998 | 10/22/21 | 798 | Lopez, Maslin A |  | 16.52
PR | 998 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 65.03
PR | 998 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 10/22/21 | 808 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 10/22/21 | 815 | Ramos Herrera, Franklin J |  | 22.03
PR | 998 | 10/22/21 | 818 | Robles Arroyo, Alonso |  | 57.83
PR | 998 | 10/22/21 | 818 | Robles Arroyo, Alonso |  | 6.43
PR | 998 | 10/22/21 | 828 | Trower-Kelly, Fidel D |  | 47.74
PR | 998 | 10/29/21 | 1002 | Anderson, Richard P |  | 6.08
PR | 998 | 10/29/21 | 1004 | Ascencio, Jose L |  | 88.13
PR | 998 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 17.75
PR | 998 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 10/29/21 | 1023 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 10/29/21 | 1024 | Cruz Guzman, Joel A |  | 113.22
PR | 998 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 42.15
PR | 998 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 4.36
PR | 998 | 10/29/21 | 1050 | Herrera Hernandez, Manuel L |  | 11.63
PR | 998 | 10/29/21 | 1058 | Lopez, Maslin A |  | 53.7
PR | 998 | 10/29/21 | 1058 | Lopez, Maslin A |  | 4.13
PR | 998 | 10/29/21 | 1058 | Lopez, Maslin A |  | 8.26
PR | 998 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 61.2
PR | 998 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 26.78
PR | 998 | 10/29/21 | 1067 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 10/29/21 | 1077 | Robles Arroyo, Alonso |  | 51.41
PR | 998 | 10/29/21 | 1086 | Trower-Kelly, Fidel D |  | 47.74
PR | 998 | 11/05/21 | 54 | Barnhart, Joseph N |  | 8.87
PR | 998 | 11/05/21 | 69 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 11/05/21 | 69 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 11/05/21 | 70 | Cruz Guzman, Joel A |  | 113.22
PR | 998 | 11/05/21 | 83 | Galdamez, Dagoberto A |  | 22.64
PR | 998 | 11/05/21 | 97 | Herrera Hernandez, Manuel L |  | 17.44
PR | 998 | 11/05/21 | 97 | Herrera Hernandez, Manuel L |  | 17.44
PR | 998 | 11/05/21 | 101 | Hubbard, Robert W |  | 8.57
PR | 998 | 11/05/21 | 106 | Lopez, Maslin A |  | 82.62
PR | 998 | 11/05/21 | 115 | Paco Leyva, Orlando |  | 61.2
PR | 998 | 11/05/21 | 115 | Paco Leyva, Orlando |  | 22.95
PR | 998 | 11/05/21 | 122 | Ramos Herrera, Franklin J |  | 44.06
PR | 998 | 11/05/21 | 125 | Robles Arroyo, Alonso |  | 38.56
PR | 998 | 11/05/21 | 125 | Robles Arroyo, Alonso |  | 12.85
PR | 998 | 11/05/21 | 140 | Young, Joshua S |  | 38.56
PR | 998 | 11/12/21 | 266 | Ascencio, Jose L |  | 44.06
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 13.31
PR | 998 | 11/12/21 | 284 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 11/12/21 | 284 | Cruz Gonzalez, Julio C |  | 58.75
PR | 998 | 11/12/21 | 285 | Cruz Guzman, Joel A |  | 45.29
PR | 998 | 11/12/21 | 297 | Galdamez, Dagoberto A |  | 67.93
PR | 998 | 11/12/21 | 311 | Herrera Hernandez, Manuel L |  | 34.88
PR | 998 | 11/12/21 | 311 | Herrera Hernandez, Manuel L |  | 11.63
PR | 998 | 11/12/21 | 320 | Lopez, Maslin A |  | 66.1
PR | 998 | 11/12/21 | 329 | Paco Leyva, Orlando |  | 72.68
PR | 998 | 11/12/21 | 329 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 11/12/21 | 336 | Ramos Herrera, Franklin J |  | 44.06
PR | 998 | 11/19/21 | 434 | Ascencio, Jose L |  | 44.06
PR | 998 | 11/19/21 | 437 | Barnhart, Joseph N |  | 4.44
PR | 998 | 11/19/21 | 452 | Cruz Gonzalez, Julio C |  | 88.13
PR | 998 | 11/19/21 | 453 | Cruz Guzman, Joel A |  | 45.29
PR | 998 | 11/19/21 | 465 | Galdamez, Dagoberto A |  | 45.29
PR | 998 | 11/19/21 | 479 | Herrera Hernandez, Manuel L |  | 23.26
PR | 998 | 11/19/21 | 488 | Lopez, Maslin A |  | 82.62
PR | 998 | 11/19/21 | 497 | Paco Leyva, Orlando |  | 65.03
PR | 998 | 11/19/21 | 520 | Young, Joshua S |  | 25.7
PR | 998 | 11/24/21 | 592 | Cruz Gonzalez, Julio C |  | 93.02
PR | 998 | 11/24/21 | 626 | Lopez, Maslin A |  | 78.49
PR | 998 | 11/24/21 | 635 | Paco Leyva, Orlando |  | 61.2
PR | 998 | 11/24/21 | 650 | Sanders, Allen O |  | 8.72
PR | 998 | 11/24/21 | 658 | Young, Joshua S |  | 25.7
PR | 998 | 11/24/21 | 660 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 12/03/21 | 29 | Cruz Gonzalez, Julio C |  | 78.34
PR | 998 | 12/03/21 | 64 | Lopez, Maslin A |  | 16.52
PR | 998 | 12/03/21 | 73 | Paco Leyva, Orlando |  | 53.55
PR | 998 | 12/03/21 | 73 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 12/03/21 | 88 | Sanders, Allen O |  | 28.34
PR | 998 | 12/10/21 | 194 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/10/21 | 210 | Cruz Gonzalez, Julio C |  | 58.75
PR | 998 | 12/10/21 | 210 | Cruz Gonzalez, Julio C |  | 39.17
PR | 998 | 12/10/21 | 256 | Paco Leyva, Orlando |  | 65.03
PR | 998 | 12/17/21 | 532 | Cruz Gonzalez, Julio C |  | 14.69
PR | 998 | 12/17/21 | 532 | Cruz Gonzalez, Julio C |  | 58.75
PR | 998 | 12/17/21 | 545 | Galdamez, Dagoberto A |  | 14.15
PR | 998 | 12/17/21 | 545 | Galdamez, Dagoberto A |  | 22.64
PR | 998 | 12/17/21 | 578 | Paco Leyva, Orlando |  | 30.6
PR | 998 | 12/17/21 | 578 | Paco Leyva, Orlando |  | 42.08
PR | 998 | 12/17/21 | 603 | Donelson, Richard T |  | 4.78
PR | 998 | 12/23/21 | 741 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/23/21 | 757 | Cruz Gonzalez, Julio C |  | 39.17
PR | 998 | 12/23/21 | 803 | Paco Leyva, Orlando |  | 91.8
PR | 998 | 12/30/21 | 998 | Paco Leyva, Orlando |  | 19.13
PR | 998 | 12/30/21 | 998 | Paco Leyva, Orlando |  | 11.48
PR | 998 | 01/07/22 | 30 | Barnhart, Joseph N |  | 4.44
PR | 998 | 01/07/22 | 73 | Herrera Hernandez, Manuel L |  | 23.26
PR | 998 | 01/07/22 | 77 | Hubbard, Robert W |  | 8.57
PR | 998 | 01/07/22 | 92 | Paco Leyva, Orlando |  | 57.38
PR | 998 | 01/14/22 | 229 | Balderas Ortiz, Ricardo I |  | 61.2
PR | 998 | 01/14/22 | 274 | Herrera Hernandez, Manuel L |  | 11.63
PR | 998 | 01/14/22 | 274 | Herrera Hernandez, Manuel L |  | 23.26
PR | 998 | 01/14/22 | 278 | Hubbard, Robert W |  | 6.43
PR | 998 | 01/14/22 | 292 | Paco Leyva, Orlando |  | 15.3
PR | 998 | 01/14/22 | 292 | Paco Leyva, Orlando |  | 34.43
PR | 998 | 01/21/22 | 476 | Paco Leyva, Orlando |  | 11.48
PR | 998 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I |  | 73.44
PR | 998 | 01/28/22 | 613 | Balderas Ortiz, Ricardo I |  | 36.72
PR | 998 | 01/28/22 | 643 | Galdamez, Dagoberto A |  | 11.32
PR | 998 | 01/28/22 | 643 | Galdamez, Dagoberto A |  | 11.32
PR | 998 | 01/28/22 | 677 | Paco Leyva, Orlando |  | 15.3
PR | 998 | 01/28/22 | 677 | Paco Leyva, Orlando |  | 34.43
PR | 998 | 01/28/22 | 684 | Ramos Herrera, Franklin J |  | 11.02
PR | 998 | 01/28/22 | 684 | Ramos Herrera, Franklin J |  | 11.02
PR | 998 | 01/28/22 | 705 | Donelson, Richard T |  | 4.78
PR | 998 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I |  | 24.48
PR | 998 | 02/04/22 | 9 | Balderas Ortiz, Ricardo I |  | 36.72
PR | 998 | 02/04/22 | 72 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 02/04/22 | 99 | Donelson, Richard T |  | 4.78
PR | 998 | 02/11/22 | 215 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 02/11/22 | 217 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 02/18/22 | 487 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 02/18/22 | 488 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/18/22 | 549 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 02/18/22 | 549 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 02/18/22 | 564 | Sanders, Allen O |  | 4.36
PR | 998 | 02/18/22 | 577 | Donelson, Richard T |  | 4.78
PR | 998 | 02/25/22 | 708 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 02/25/22 | 709 | Barnhart, Joseph N |  | 4.44
PR | 998 | 02/25/22 | 763 | McCabe, Thomas C |  | 57.83
PR | 998 | 02/25/22 | 769 | Paco Leyva, Orlando |  | 11.48
PR | 998 | 02/25/22 | 780 | Romero Garza, Jesus I |  | 43.76
PR | 998 | 02/25/22 | 784 | Sanders, Allen O |  | 21.8
PR | 998 | 02/25/22 | 789 | Trower-Kelly, Fidel D |  | 47.74
PR | 998 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 15.3
PR | 998 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 03/04/22 | 43 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 03/04/22 | 101 | McCabe, Thomas C |  | 6.43
PR | 998 | 03/04/22 | 107 | Paco Leyva, Orlando |  | 15.3
PR | 998 | 03/04/22 | 118 | Romero Garza, Jesus I |  | 79.56
PR | 998 | 03/04/22 | 122 | Sanders, Allen O |  | 8.72
PR | 998 | 03/04/22 | 127 | Trower-Kelly, Fidel D |  | 79.56
PR | 998 | 03/11/22 | 340 | Balderas Ortiz, Ricardo I |  | 61.2
PR | 998 | 03/11/22 | 341 | Barnhart, Joseph N |  | 8.87
PR | 998 | 03/11/22 | 387 | Hubbard, Robert W |  | 12.85
PR | 998 | 03/11/22 | 404 | Paco Leyva, Orlando |  | 11.48
PR | 998 | 03/11/22 | 415 | Romero Garza, Jesus I |  | 79.56
PR | 998 | 03/11/22 | 419 | Sanders, Allen O |  | 30.52
PR | 998 | 03/11/22 | 424 | Trower-Kelly, Fidel D |  | 79.56
PR | 998 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I |  | 104.04
PR | 998 | 03/18/22 | 625 | Balderas Ortiz, Ricardo I |  | 18.36
PR | 998 | 03/18/22 | 672 | Hubbard, Robert W |  | 4.28
PR | 998 | 03/18/22 | 689 | Paco Leyva, Orlando |  | 30.6
PR | 998 | 03/18/22 | 689 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 03/18/22 | 700 | Romero Garza, Jesus I |  | 47.74
PR | 998 | 03/18/22 | 704 | Sanders, Allen O |  | 23.98
PR | 998 | 03/18/22 | 709 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 03/25/22 | 874 | Balderas Ortiz, Ricardo I |  | 104.04
PR | 998 | 03/25/22 | 875 | Barnhart, Joseph N |  | 26.62
PR | 998 | 03/25/22 | 919 | Hubbard, Robert W |  | 8.57
PR | 998 | 03/25/22 | 936 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 03/25/22 | 936 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 03/25/22 | 946 | Romero Garza, Jesus I |  | 79.56
PR | 998 | 03/25/22 | 950 | Sanders, Allen O |  | 30.52
PR | 998 | 03/25/22 | 954 | Trower-Kelly, Fidel D |  | 77.57
PR | 998 | 03/25/22 | 962 | Donelson, Richard T |  | 4.78
PR | 998 | 04/01/22 | 20 | Balderas Ortiz, Ricardo I |  | 119.34
PR | 998 | 04/01/22 | 66 | Hubbard, Robert W |  | 4.28
PR | 998 | 04/01/22 | 66 | Hubbard, Robert W |  | 4.28
PR | 998 | 04/01/22 | 82 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 04/01/22 | 82 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 04/01/22 | 92 | Romero Garza, Jesus I |  | 79.56
PR | 998 | 04/01/22 | 96 | Sanders, Allen O |  | 13.08
PR | 998 | 04/01/22 | 100 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 04/01/22 | 108 | Donelson, Richard T |  | 14.34
PR | 998 | 04/01/22 | 109 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I |  | 104.04
PR | 998 | 04/08/22 | 226 | Balderas Ortiz, Ricardo I |  | 6.12
PR | 998 | 04/08/22 | 247 | Eliassen, Cory H |  | 62.42
PR | 998 | 04/08/22 | 259 | Gonzalez Hernandez, Josue |  | 67.32
PR | 998 | 04/08/22 | 259 | Gonzalez Hernandez, Josue |  | 18.36
PR | 998 | 04/08/22 | 272 | Hubbard, Robert W |  | 4.28
PR | 998 | 04/08/22 | 276 | Johnson, Jake E |  | 3.83
PR | 998 | 04/08/22 | 288 | Paco Leyva, Orlando |  | 11.48
PR | 998 | 04/08/22 | 298 | Romero Garza, Jesus I |  | 47.74
PR | 998 | 04/08/22 | 302 | Sanders, Allen O |  | 19.62
PR | 998 | 04/08/22 | 306 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 04/08/22 | 314 | Donelson, Richard T |  | 4.78
PR | 998 | 04/15/22 | 474 | Balderas Ortiz, Ricardo I |  | 122.4
PR | 998 | 04/15/22 | 475 | Barnhart, Joseph N |  | 8.87
PR | 998 | 04/15/22 | 476 | Barnhart, Thomas L |  | 23.26
PR | 998 | 04/15/22 | 494 | Eliassen, Cory H |  | 52.02
PR | 998 | 04/15/22 | 506 | Gonzalez Hernandez, Josue |  | 67.32
PR | 998 | 04/15/22 | 506 | Gonzalez Hernandez, Josue |  | 6.12
PR | 998 | 04/15/22 | 519 | Hubbard, Robert W |  | 42.84
PR | 998 | 04/15/22 | 519 | Hubbard, Robert W |  | 8.57
PR | 998 | 04/15/22 | 535 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 04/15/22 | 549 | Sanders, Allen O |  | 52.33
PR | 998 | 04/15/22 | 553 | Trower-Kelly, Fidel D |  | 47.74
PR | 998 | 04/15/22 | 561 | Donelson, Richard T |  | 4.78
PR | 998 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 94.86
PR | 998 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 04/22/22 | 802 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 04/22/22 | 822 | Eliassen, Cory H |  | 83.23
PR | 998 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 61.2
PR | 998 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 27.54
PR | 998 | 04/22/22 | 834 | Gonzalez Hernandez, Josue |  | 12.24
PR | 998 | 04/22/22 | 847 | Hubbard, Robert W |  | 72.83
PR | 998 | 04/22/22 | 847 | Hubbard, Robert W |  | 8.57
PR | 998 | 04/22/22 | 851 | Johnson, Jake E |  | 3.83
PR | 998 | 04/22/22 | 863 | Paco Leyva, Orlando |  | 7.65
PR | 998 | 04/22/22 | 873 | Romero Garza, Jesus I |  | 31.82
PR | 998 | 04/22/22 | 877 | Sanders, Allen O |  | 61.05
PR | 998 | 04/22/22 | 881 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 04/22/22 | 889 | Donelson, Richard T |  | 4.78
PR | 998 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 42.84
PR | 998 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 67.32
PR | 998 | 04/29/22 | 1062 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 04/29/22 | 1082 | Eliassen, Cory H |  | 93.64
PR | 998 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 55.08
PR | 998 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 12.24
PR | 998 | 04/29/22 | 1094 | Gonzalez Hernandez, Josue |  | 18.36
PR | 998 | 04/29/22 | 1107 | Hubbard, Robert W |  | 27.85
PR | 998 | 04/29/22 | 1107 | Hubbard, Robert W |  | 8.57
PR | 998 | 04/29/22 | 1111 | Johnson, Jake E |  | 7.65
PR | 998 | 04/29/22 | 1124 | Paco Leyva, Orlando |  | 3.83
PR | 998 | 04/29/22 | 1134 | Romero Garza, Jesus I |  | 79.56
PR | 998 | 04/29/22 | 1137 | Sanders, Allen O |  | 37.06
PR | 998 | 04/29/22 | 1141 | Trower-Kelly, Fidel D |  | 79.56
PR | 998 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 36.72
PR | 998 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 36.72
PR | 998 | 05/06/22 | 89 | Balderas Ortiz, Ricardo I |  | 55.08
PR | 998 | 05/06/22 | 95 | Boss, Kyle A |  | 14.92
PR | 998 | 05/06/22 | 107 | Eliassen, Cory H |  | 19.51
PR | 998 | 05/06/22 | 107 | Eliassen, Cory H |  | 104.04
PR | 998 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 21.42
PR | 998 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 12.24
PR | 998 | 05/06/22 | 118 | Gonzalez Hernandez, Josue |  | 9.18
PR | 998 | 05/06/22 | 131 | Hubbard, Robert W |  | 29.99
PR | 998 | 05/06/22 | 131 | Hubbard, Robert W |  | 4.28
PR | 998 | 05/06/22 | 131 | Hubbard, Robert W |  | 12.85
PR | 998 | 05/06/22 | 148 | Paco Leyva, Orlando |  | 45.9
PR | 998 | 05/06/22 | 158 | Romero Garza, Jesus I |  | 14.92
PR | 998 | 05/06/22 | 158 | Romero Garza, Jesus I |  | 31.82
PR | 998 | 05/06/22 | 160 | Sanders, Allen O |  | 26.16
PR | 998 | 05/06/22 | 160 | Sanders, Allen O |  | 56.69
PR | 998 | 05/06/22 | 160 | Sanders, Allen O |  | 13.08
PR | 998 | 05/06/22 | 163 | Taylor, Evan R |  | 14.15
PR | 998 | 05/06/22 | 164 | Trower-Kelly, Fidel D |  | 63.65
PR | 998 | 05/06/22 | 164 | Trower-Kelly, Fidel D |  | 9.95
PR | 998 | 05/13/22 | 323 | Balderas Ortiz, Ricardo I |  | 12.24
PR | 998 | 05/13/22 | 328 | Boss, Benjamin T |  | 14.34
PR | 998 | 05/13/22 | 329 | Boss, Kyle A |  | -14.92
PR | 998 | 05/13/22 | 342 | Eliassen, Cory H |  | 104.04
PR | 998 | 05/13/22 | 366 | Hubbard, Robert W |  | 34.27
PR | 998 | 05/13/22 | 370 | Johnson, Jake E |  | 3.83
PR | 998 | 05/13/22 | 396 | Sanders, Allen O |  | 69.77
PR | 998 | 05/20/22 | 616 | Eliassen, Cory H |  | 2.68
PR | 998 | 05/20/22 | 669 | Sanders, Allen O |  | 29.34
PR | 998 | 05/20/22 | 681 | Donelson, Richard T |  | 4.78
PR | 998 | 05/27/22 | 937 | Sanders, Allen O |  | 22.57
PR | 998 | 06/03/22 | 56 | Johnson, Jake E |  | 3.83
PR | 998 | 06/03/22 | 93 | Donelson, Richard T |  | 4.78
PR | 998 | 06/10/22 | 289 | Sanders, Allen O |  | 18.05
PR | 998 | 06/10/22 | 301 | Donelson, Richard T |  | 19.13
PR | 998 | 06/17/22 | 537 | Sanders, Allen O |  | 9.03
PR | 998 | 07/01/22 | 31 | Eliassen, Cory H |  | 5.36
AR | 999 | 04/26/19 | 822 | Blueprint Capital Services, LLC$Dockside |  | -7092 | 037337
AR | 999 | 11/18/20 | 332 | Blueprint Capital Services, LLC$Dockside |  | -41553 | 037555
AR | 999 | 11/18/20 | 332 | Blueprint Capital Services, LLC$Dockside |  | -9215 | 037555
AR | 999 | 12/14/20 | 246 | Blueprint Capital Services, LLC$Dockside |  | -22460 | 037573
AR | 999 | 01/20/21 | 239 | Blueprint Capital Services, LLC$Dockside |  | -20000 | 037585
AR | 999 | 02/19/21 | 492 | Blueprint Capital Services, LLC$Dockside |  | -13585 | 037600
AR | 999 | 02/19/21 | 492 | Blueprint Capital Services, LLC$Dockside |  | -14200 | 037600
AR | 999 | 03/19/21 | 351 | Blueprint Capital Services, LLC$Dockside |  | -100 | 037612
AR | 999 | 03/19/21 | 351 | Blueprint Capital Services, LLC$Dockside |  | -14000 | 037612
AR | 999 | 03/19/21 | 351 | Blueprint Capital Services, LLC$Dockside |  | -1806 | 037612
AR | 999 | 04/20/21 | 376 | Blueprint Capital Services, LLC$Dockside |  | -5910 | 037638
AR | 999 | 04/20/21 | 376 | Blueprint Capital Services, LLC$Dockside |  | -15880 | 037638
AR | 999 | 04/20/21 | 472 | Blueprint Capital Services, LLC$Dockside |  | 5910 | 037645
AR | 999 | 04/20/21 | 472 | Blueprint Capital Services, LLC$Dockside |  | 15880 | 037645
AR | 999 | 04/20/21 | 473 | Blueprint Capital Services, LLC$Dockside |  | -5910 | 037646
AR | 999 | 04/20/21 | 473 | Blueprint Capital Services, LLC$Dockside |  | -15880 | 037646
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -10450 | 037655
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -48830 | 037655
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -77679 | 037655
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -70795 | 037655
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -5785 | 037655
AR | 999 | 05/19/21 | 366 | Blueprint Capital Services, LLC$Dockside |  | -16006 | 037655
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -45000 | 037673
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -13538 | 037673
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -19532 | 037673
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -17698 | 037673
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -11572 | 037673
AR | 999 | 06/18/21 | 490 | Blueprint Capital Services, LLC$Dockside |  | -25000 | 037673
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -5415 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -9770 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -17700 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -86775 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -92570 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -81000 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -8325 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -44160 | 037694
AR | 999 | 07/16/21 | 408 | Blueprint Capital Services, LLC$Dockside |  | -6170 | 037694
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -10450 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -5415 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -9762 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -11570 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -23140 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -66573 | 037717
AR | 999 | 08/20/21 | 703 | Blueprint Capital Services, LLC$Dockside |  | -34730 | 037717
AR | 999 | 09/20/21 | 429 | Blueprint Capital Services, LLC$Dockside |  | -11570 | 037733
AR | 999 | 09/20/21 | 429 | Blueprint Capital Services, LLC$Dockside |  | -11570 | 037733
AR | 999 | 09/20/21 | 429 | Blueprint Capital Services, LLC$Dockside |  | -8322 | 037733
AR | 999 | 09/20/21 | 429 | Blueprint Capital Services, LLC$Dockside |  | -1992 | 037733
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -8180 | 037753
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -2707 | 037753
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -9766 | 037753
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -11951 | 037753
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -11797 | 037753
AR | 999 | 10/20/21 | 734 | Blueprint Capital Services, LLC$Dockside |  | -11578 | 037753
AR | 999 | 01/14/22 | 359 | Blueprint Capital Services, LLC$Dockside |  | -14165 | 037798
AR | 999 | 02/18/22 | 590 | Blueprint Capital Services, LLC$Dockside |  | -14165 | 037817
AR | 999 | 02/18/22 | 590 | Blueprint Capital Services, LLC$Dockside |  | -14165 | 037817
AR | 999 | 02/18/22 | 590 | Blueprint Capital Services, LLC$Dockside |  | -14165 | 037817
AR | 999 | 02/18/22 | 590 | Blueprint Capital Services, LLC$Dockside |  | -3941 | 037817
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -2023 | 037838
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -6070 | 037838
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -6070 | 037838
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -6070 | 037838
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -15100 | 037838
AR | 999 | 03/18/22 | 740 | Blueprint Capital Services, LLC$Dockside |  | -2892 | 037838
AR | 999 | 04/20/22 | 774 | Blueprint Capital Services, LLC$Dockside |  | -4105 | 037846
AR | 999 | 04/20/22 | 774 | Blueprint Capital Services, LLC$Dockside |  | -18212 | 037846
AR | 999 | 04/20/22 | 774 | Blueprint Capital Services, LLC$Dockside |  | -4047 | 037846
AR | 999 | 05/20/22 | 694 | Blueprint Capital Services, LLC$Dockside |  | -455 | 037863
AR | 999 | 05/20/22 | 694 | Blueprint Capital Services, LLC$Dockside |  | -2023 | 037863
AR | 999 | 05/20/22 | 694 | Blueprint Capital Services, LLC$Dockside |  | -57117 | 037863