## 01 Overview
OWP #2056 · Acme Farms
Exxel Pacific · 321 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 6034876
Revised budget (expenses) | 4362094.53
Forecast net profit | 1672781.47
Forecast margin | 27.72%
Progress to Date
Work complete (billed) | 6034876
Retention held | 296893.8
Earned less retention | 5737982.2
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 221469.76
AP | 1192245.52
PR | 1977161.81
AR | -6034876

## 02 Job Info
JOB #2056 · EXXEL PACIFIC · Acme Farms — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract L1.220000.
IDENTITY
OWP Job ID | 2056
Project Name | Acme Farms
Site Address | 1029 S Jackson Street, Seattle WA 98104 (Central District)
Subcontract Number | L1.220000
Effective Date | April 18, 2018
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Exxel Pacific
GC Address | (per Exxel standard)
GC Contract Signatory | Exxel
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Acme Farms
Owner Address | (per Exxel)
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | TBD per Exxel standard
Retention | 5% per contract
CONTRACT
Contract Value | $5,877,400 original
CHANGE-EVENT META
Executed CO Count | TBD — see GDrive Change Orders/CO's/
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | (see GDrive)
COR Themes | (see GDrive)
Key RFIs | RFI-051 fitness room bottle filler
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Exxel Acme Farms Job Ticket 09-02-2020.pdf
GDrive Folder | Job Books - Completed Jobs/2056-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets | 346 | 324 Gerber 21-912 Type B + 17 ADA Type A + 3 retail K-3519 + 2 ADA common
Lavs | 345 | 341 Lenova PU-01-W + 4 Kohler K-2035 common
Showers Type B | 110 | Best Bath LSS4838B5T 36x48 + Delta T14259
Tubs Type B | 214 | Aquatic 2603SMTE w/ backing + Delta T14459
Tubs Type A ADA | 17 | Aquatic 2603SMTE + grab bars + seat + Delta T14459-LHD
Kitchen sinks | 307 | Lenova LS18304 Type B + 17 Elkay ELUHAD ADA + 3 amenity Elkay
Urinal | 1 | Kohler K-4991
Drinking fountain | 1 | Elkay EZSTL8WSLK retail
Bottle filler | 1 | Elkay LZWSSM + ECH8 chiller fitness
Mop sink | 1 | Mustee 63M custodian
Bike room faucet | 1 | T&S Brass B-PG-8WREV
Dog wash tub | 1 | GROOMER'S BEST 58" ADA WALK-THROUGH
VERIFIED MAIN FIXTURE COUNT | 1363
Per unit (321): 4.25
AUDIT NOTE (2026-04-25): First-pass count of 1345 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 1363 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 5877400 | 6034876 | 157476
Executed change orders (net) | 0 | 157476 | 157476
Total contract value | 5877400 | 6192352 | 314952
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 38520 | 38620 | 8525.5 | 30094.5 | 0 | 22.08%
101 | Takeoff & Purchase Labor | 64200 | 64300 | 31609 | 32691 | 0 | 49.16%
110 | Underground Labor | 38820 | 44224 | 37974.25 | 6249.75 | 0 | 85.87%
111 | Garage Labor | 191150 | 192900 | 135710.5 | 57189.5 | 0 | 70.35%
112 | Canout Labor | 50640 | 50830 | 31518 | 19312 | 0 | 62.01%
120 | Roughin Labor | 688305 | 692715 | 802553.37 | -109838.37 | 0 | 115.9%
130 | Finish Labor | 105170 | 105765 | 119715 | -13950 | 0 | 113.2%
140 | Gas Labor | 20250 | 22750 | 12589 | 10161 | 0 | 55.34%
141 | Water Main/Insulation Lab | 172094 | 181004 | 142511.29 | 38492.71 | 0 | 78.73%
142 | Mech Room Labor | 115500 | 115500 | 35212 | 80288 | 0 | 30.49%
150 | Warranty Labor | 0 | 0 | 137.5 | -137.5 | 0 | 0%
210 | Underground Material | 57667 | 59247 | 31760.07 | 27486.93 | 0 | 53.61%
211 | Garage Material | 172517 | 173467 | 92755.74 | 80711.26 | 0 | 53.47%
212 | Canout Material | 68227 | 68417 | 32821.74 | 35595.26 | 0 | 47.97%
220 | Roughin Material | 429928 | 431128 | 239543.21 | 191584.79 | 0 | 55.56%
230 | Finish Material | 867882 | 870472 | 650099 | 220373 | 0 | 74.68%
240 | Gas Material | 27000 | 28800 | 8134.74 | 20665.26 | 0 | 28.25%
241 | Water Main/Insulation Mat | 205659 | 206189 | 103675.54 | 102513.46 | 0 | 50.28%
242 | Mech Room Material | 94000 | 94000 | 79516.1 | 14483.9 | 0 | 84.59%
600 | Subcontractor | 55000 | 59850 | 25977.47 | 33872.53 | 0 | 43.4%
601 | Engineering/Plans | 120000 | 120000 | 93899.29 | 26100.71 | 0 | 78.25%
602 | Rental Equipment | 12000 | 12000 | 19433.38 | -7433.38 | 0 | 161.9%
603 | Permits & Licenses | 26710 | 27010 | 20109.95 | 6900.05 | 0 | 74.45%
607 | Other Expenses | 12000 | 12000 | 20674.89 | -8674.89 | 0 | 172.3%
995 | Payroll Burden | 566393.59 | 575498.01 | 510170.4 | 65327.61 | 0 | 88.65%
998 | Payroll Taxes | 113575.65 | 115408.52 | 104250.16 | 11158.36 | 0 | 90.33%
TOTAL |  | 4313208.24 | 4362094.53 | 3390877.09 | 971217.44 | 0 | 77.74%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 1508608 | 1358055.41 | 150552.59 | 90.02%
Material | 8 | 1931720 | 1238306.14 | 693413.86 | 64.1%
Overhead | 5 | 230860 | 180094.98 | 50765.02 | 78.01%
Burden | 2 | 690906.53 | 614420.56 | 76485.97 | 88.93%
TOTAL | 26 | 4362094.53 | 3390877.09 | 971217.44 | 77.74%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 38620 | 8525.5 | 30094.5 | -77.92% | UNDER
101 | Takeoff & Purchase Labor | 64300 | 31609 | 32691 | -50.84% | UNDER
110 | Underground Labor | 44224 | 37974.25 | 6249.75 | -14.13% | UNDER
111 | Garage Labor | 192900 | 135710.5 | 57189.5 | -29.65% | UNDER
112 | Canout Labor | 50830 | 31518 | 19312 | -37.99% | UNDER
120 | Roughin Labor | 692715 | 802553.37 | -109838.37 | 15.86% | OVER
130 | Finish Labor | 105765 | 119715 | -13950 | 13.19% | OVER
140 | Gas Labor | 22750 | 12589 | 10161 | -44.66% | UNDER
141 | Water Main/Insulation Lab | 181004 | 142511.29 | 38492.71 | -21.27% | UNDER
142 | Mech Room Labor | 115500 | 35212 | 80288 | -69.51% | UNDER
150 | Warranty Labor | 0 | 137.5 | -137.5 | 0% | UNBUDGETED
210 | Underground Material | 59247 | 31760.07 | 27486.93 | -46.39% | UNDER
211 | Garage Material | 173467 | 92755.74 | 80711.26 | -46.53% | UNDER
212 | Canout Material | 68417 | 32821.74 | 35595.26 | -52.03% | UNDER
220 | Roughin Material | 431128 | 239543.21 | 191584.79 | -44.44% | UNDER
230 | Finish Material | 870472 | 650099 | 220373 | -25.32% | UNDER
240 | Gas Material | 28800 | 8134.74 | 20665.26 | -71.75% | UNDER
241 | Water Main/Insulation Mat | 206189 | 103675.54 | 102513.46 | -49.72% | UNDER
242 | Mech Room Material | 94000 | 79516.1 | 14483.9 | -15.41% | UNDER
600 | Subcontractor | 59850 | 25977.47 | 33872.53 | -56.6% | UNDER
601 | Engineering/Plans | 120000 | 93899.29 | 26100.71 | -21.75% | UNDER
602 | Rental Equipment | 12000 | 19433.38 | -7433.38 | 61.94% | CRITICAL
603 | Permits & Licenses | 27010 | 20109.95 | 6900.05 | -25.55% | UNDER
607 | Other Expenses | 12000 | 20674.89 | -8674.89 | 72.29% | CRITICAL
995 | Payroll Burden | 575498.01 | 510170.4 | 65327.61 | -11.35% | UNDER
998 | Payroll Taxes | 115408.52 | 104250.16 | 11158.36 | -9.669% | ON

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 366756.08 | 272 | 30.76%
Keller Supply Company | 172151.22 | 71 | 14.44%
California Hydronics Corp | 160520 | 12 | 13.46%
Consolidated Supply Co. | 136975.73 | 88 | 11.49%
Best Bath Systems | 92087.8 | 7 | 7.724%
Franklin Engineering | 87389.75 | 13 | 7.33%
Ferguson Enterprises, Inc. #3007 | 78590.46 | 62 | 6.592%
Capital One Credit Card | 23772.49 | 50 | 1.994%
H&E Equipment Services, Inc. | 18827.87 | 35 | 1.579%
Mechanical Resource Services, Inc. | 10125 | 1 | 0.8492%
Patchworks, Inc. | 8790 | 1 | 0.7373%
Beacon Building Products $Atlas | 8465.47 | 12 | 0.71%
Old Castle Infrastructure, Inc. | 5866 | 2 | 0.492%
Sider + Byers Associates, Inc. | 5590 | 2 | 0.4689%
Mechanical Sales, Inc. | 4980.97 | 3 | 0.4178%
Scan2Core, Inc. | 3732.47 | 5 | 0.3131%
Chemical Products Company | 3050 | 1 | 0.2558%
Platt $Rexel USA, Inc. | 1794.25 | 4 | 0.1505%
DRSi | 919.54 | 5 | 0.07713%
Herc Rentals, Inc. | 396 | 1 | 0.03321%
Core & Main LP $HD Supply Waterworks | 291.1 | 6 | 0.02442%
A.R. Brown Backflow Testing | 280 | 1 | 0.02349%
Kele, Inc $ MI Controls | 277.41 | 2 | 0.02327%
C.M. Hoskins Company | 270.4 | 1 | 0.02268%
Sunbelt Rentals, Inc. | 209.51 | 1 | 0.01757%
MechAgents | 136 | 1 | 0.01141%
TOTAL AP | 1192245.52 | 659

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Mitchell J | 2714.5 | 117388 | 43.2448 | LEAD/SUPERVISOR
Draves, Steven W | 2403 | 80280 | 33.4082 | JOURNEYMAN
Eisenhauer, Tommy J | 2355 | 80094 | 34.0102 | JOURNEYMAN
Portillo Soriano, Walter A | 1961 | 48482 | 24.7231 | JOURNEYMAN
Rodriguez Arevalos, Christian | 1951 | 56220 | 28.816 | JOURNEYMAN
Hubbard, Justin A | 1840.5 | 53341 | 28.9818 | JOURNEYMAN
Rivera, Eli P | 1745 | 57066 | 32.7026 | JOURNEYMAN
Gerard, Jordan E | 1696.5 | 71421 | 42.099 | LEAD/SUPERVISOR
Montenegro, Carlos E | 1444 | 44764 | 31 | JOURNEYMAN
Cornejo Orellana, Carlos E | 1411 | 36686 | 26 | JOURNEYMAN
King, Caleb A | 1373 | 29744 | 21.6635 | JOURNEYMAN
Vazquez Popoca, Jose N | 1346 | 27184 | 20.1961 | JOURNEYMAN
Sepulveda Gonzalez, Alfredo | 1180 | 46948 | 39.7864 | LEAD/SUPERVISOR
Rosenberg, Joshua M | 1013 | 37928 | 37.4413 | LEAD/SUPERVISOR
Barnhart, Joseph N | 993.5 | 53135 | 53.4826 | LEAD/SUPERVISOR
Fisher, Drew M | 923 | 19446 | 21.0683 | JOURNEYMAN
Cruz Reyes, Jose | 881 | 28512 | 32.3632 | JOURNEYMAN
Escalante Escobar, Boanerge | 768 | 19200 | 25 | JOURNEYMAN
Waites, Thaddeus Z | 722 | 35500 | 49.169 | LEAD/SUPERVISOR
Ross, Kelli M | 702.5 | 30208 | 43.0007 | LEAD/SUPERVISOR
Lopez, Maslin A | 646.5 | 12304 | 19.0317 | APPRENTICE/HELPER
Eliassen, Cory H | 593.5 | 18377 | 30.9638 | JOURNEYMAN
Trower-Kelly, Fidel D | 548 | 12170 | 22.208 | JOURNEYMAN
Hubbard, Robert W | 540 | 29166 | 54.0111 | LEAD/SUPERVISOR
Wennig, Johnathan M | 531 | 19224 | 36.2034 | LEAD/SUPERVISOR
Velasquez Cruz, Denis M | 511 | 17885 | 35 | JOURNEYMAN
Belcher, Jacob T | 480 | 10080 | 21 | JOURNEYMAN
Ascencio, Jose L | 480 | 15840 | 33 | JOURNEYMAN
Lucas Tzintzun, Rafael | 467.5 | 11220 | 24 | JOURNEYMAN
Velasquez Cruz, Osman N | 455 | 12740 | 28 | JOURNEYMAN
Sanders, Allen O | 443 | 24304 | 54.8623 | LEAD/SUPERVISOR
Villalobos Tejada, Carlos F | 440 | 8360 | 19 | APPRENTICE/HELPER
Reyes Cruz, Denis A | 431 | 14223 | 33 | JOURNEYMAN
Lima Romero, Melvin A | 414 | 15732 | 38 | LEAD/SUPERVISOR
Gutierrez Salas, Jose | 411.5 | 7248 | 17.6136 | APPRENTICE/HELPER
Gerard, Jeffrey S | 406 | 22947 | 56.5197 | LEAD/SUPERVISOR
Cortes Mendiola, Victor H | 368 | 18256 | 49.6087 | LEAD/SUPERVISOR
Castro Hernandez, Jose A | 350 | 14350 | 41 | LEAD/SUPERVISOR
Mackey, Cole J | 348 | 5696 | 16.3678 | APPRENTICE/HELPER
Petermeyer, Matthew W | 317.5 | 5124 | 16.1386 | APPRENTICE/HELPER
Stahlschmidt, John P | 298.5 | 6567 | 22 | JOURNEYMAN
Taylor, Evan R | 290 | 9668 | 33.3379 | JOURNEYMAN
Donelson, Richard T | 275 | 17188 | 62.5018 | LEAD/SUPERVISOR
Cruz Gonzalez, Julio C | 251 | 7098 | 28.2789 | JOURNEYMAN
Perez Araque, Manuel A | 230.5 | 3688 | 16 | APPRENTICE/HELPER
Romero Garza, Jesus I | 213 | 5092 | 23.9061 | JOURNEYMAN
McCabe, Thomas C | 176.5 | 6884 | 39.0028 | LEAD/SUPERVISOR
Jimenez Alvarenga, Gerson M | 176 | 4928 | 28 | JOURNEYMAN
Paco Leyva, Orlando | 148.5 | 6072 | 40.8889 | LEAD/SUPERVISOR
Gauthier, Dillon R | 141 | 2485 | 17.6241 | APPRENTICE/HELPER
Ramos Herrera, Franklin J | 120.5 | 3256 | 27.0207 | JOURNEYMAN
Cortes Sepulveda, Jose R | 88 | 2992 | 34 | JOURNEYMAN
Barnhart, Thomas L | 80 | 2880 | 36 | LEAD/SUPERVISOR
Boss, Benjamin T | 69 | 1302 | 18.8696 | APPRENTICE/HELPER
Balderas Ortiz, Ricardo I | 64 | 2304 | 36 | LEAD/SUPERVISOR
Boss, Kyle A | 57 | 1094 | 19.193 | APPRENTICE/HELPER
Wilson, Garret A | 55 | 2200 | 40 | LEAD/SUPERVISOR
Roberts, Lake A | 51 | 1275 | 25 | JOURNEYMAN
Amaya Gonzalez, Edilberto A | 44.5 | 1648 | 37.0337 | JOURNEYMAN
Hoeg, Xavier A | 40 | 720 | 18 | APPRENTICE/HELPER
Galdamez, Dagoberto A | 38 | 1254 | 33 | JOURNEYMAN
Martinez Reyes, Juan C | 32.5 | 1292 | 39.7538 | JOURNEYMAN
Gonzalez Hernandez, Josue | 29 | 1044 | 36 | LEAD/SUPERVISOR
Cudaback, Chane J | 19 | 760 | 40 | LEAD/SUPERVISOR
Lee, Ha Nul | 5 | 188 | 37.6 | OT-ONLY
Kinssies, Jr, John E | 2 | 70 | 35 | JOURNEYMAN

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 22 | 12921 | 575838 | 31.06%
JOURNEYMAN | 33 | 25972.5 | 738695 | 62.43%
APPRENTICE/HELPER | 10 | 2701 | 48020 | 6.493%
OT-ONLY | 1 | 5 | 188 | 0.01202%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 41600
Active workers | 66
Hours per unit (to date) | 129.6
Revenue per labor hour (billed) | 145.07
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 27.72% | 34% | -6.281%
Roughin labor share (code 120) | 45.92% | 45% | 0.9175%
Top vendor concentration | 30.76% | 38% | -7.238%
Hours per unit | 129.5935 | 95 | 34.5935

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Roughin Labor (120) over revised | ⚠ WATCH | Actual $802,553 vs revised $692,715 (+16%) — monitor
Finish Labor (130) over revised | ⚠ WATCH | Actual $119,715 vs revised $105,765 (+13%) — monitor
Rental Equipment (602) CRITICAL overrun | ⚠ WATCH | Actual $19,433 vs revised $12,000 (+62%) — needs immediate attention
Other Expenses (607) CRITICAL overrun | ⚠ WATCH | Actual $20,675 vs revised $12,000 (+72%) — needs immediate attention
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 31% of AP ($366,756) — acceptable
Retention aging | ✓ OK | $296,894 held · 4.9% of billed · standard range
Forecast margin | ✓ OK | 27.7% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 3390877.09 | 3390877.09 | 0
Revenue billed (AR ·-1) | -6034876 | 6034876 | -12069752
AP source total |  | 1192245.52 | —
PR source total |  | 1977161.81 | —
GL source total |  | 221469.76 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2056 live project. 17-tab JCR schema on revised budget basis.