## 01 Overview
OWP #2057 · Plaza Apartments
Natural & Built · 10 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 1133967
Revised budget (expenses) | 833731.04
Forecast net profit | 300235.96
Forecast margin | 26.48%
Progress to Date
Work complete (billed) | 1133967
Retention held | 56698.36
Earned less retention | 1077268.64
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 47903.11
AP | 189798.24
PR | 336529.36
AR | -1133967

## 02 Job Info
JOB #2057 · NATURAL & BUILT · Plaza Apartments — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract TBD (no contract on file in GDrive).
IDENTITY
OWP Job ID | 2057
Project Name | Plaza Apartments
Site Address | 330 4th Street, Kirkland WA 98033
Subcontract Number | TBD (no contract on file in GDrive)
Effective Date | 2018-2019
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Natural & Built
GC Address | (N&B Construction)
GC Contract Signatory | TBD
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Kirkland Sustainable Investments
Owner Address | Kirkland WA
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | TBD
Retention | 5% per contract
CONTRACT
Contract Value | $1,098,897 original
CHANGE-EVENT META
Executed CO Count | 10
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | CO #10 Water Meters at Studio Units
COR Themes | (see GDrive)
Key RFIs | (see GDrive)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Natural and Built Plaza Kirkland Job Ticket - October 15 2019.pdf
GDrive Folder | Job Books - Completed Jobs/2057-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets — SRO bathrooms | 110 | 101 Niagara N7716/14 + 6 Toto CST454CEF ADA + 3 common ADA
Lavs | 18 | 15 oval self-rim + 3 common K2028/2057
Bar sinks (unit kitchenettes) | 96 | Dayton D11516 + Delta 1959LF chrome bar faucet 0.5gpm
Showers | 107 | 101 Aquatic 1363EN + 6 1363BFSC w/ Moen 62370
Full-kitchen sinks | 10 | 9 Dayton K12522 + 1 ADA GE12522
Common kitchen sinks | 6 | Dayton GE12522 ADA + Peerless P188103LF
Drinking fountain | 1 | Elkay EZSTL8LC dual-level
Insta-hot | 1 | ISE FGN1100 L1 common
Watts FD15 deck drains | 2 | L1 restrooms
Retail bathrooms | 2 | Waste/water/vent roughin only
Urinal | 1 | Kohler K-4991-ET + Sloan ECOS
VERIFIED MAIN FIXTURE COUNT | 350
Per full-kitchen unit (10): 35.0 · Per SRO bedroom (101): 3.47
AUDIT NOTE (2026-04-25): First-pass count of 354 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 350 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 1098897 | 1133967 | 35070
Executed change orders (net) | 0 | 35070 | 35070
Total contract value | 1098897 | 1169037 | 70140
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 9630 | 9980 | 3488.5 | 6491.5 | 0 | 34.95%
101 | Takeoff & Purchase Labor | 13910 | 14210 | 9538 | 4672 | 0 | 67.12%
110 | Underground Labor | 9000 | 9000 | 2949 | 6051 | 0 | 32.77%
111 | Garage Labor | 31350 | 36848 | 32824 | 4024 | 0 | 89.08%
112 | Canout Labor | 9176 | 9601 | 9569 | 32 | 0 | 99.67%
120 | Roughin Labor | 98240 | 98240 | 96775 | 1465 | 0 | 98.51%
130 | Finish Labor | 23058 | 23938 | 17090.5 | 6847.5 | 0 | 71.39%
140 | Gas Labor | 6750 | 7520 | 8361 | -841 | 0 | 111.2%
141 | Water Main/Insulation Lab | 44440 | 46100 | 35756 | 10344 | 0 | 77.56%
142 | Mech Room Labor | 7000 | 7300 | 5049.5 | 2250.5 | 0 | 69.17%
210 | Underground Material | 9500 | 9500 | 648.12 | 8851.88 | 0 | 6.822%
211 | Garage Material | 30850 | 33497 | 17156.73 | 16340.27 | 0 | 51.22%
212 | Canout Material | 7440 | 7915 | 8186.91 | -271.91 | 0 | 103.4%
220 | Roughin Material | 53020 | 53020 | 25828.61 | 27191.39 | 0 | 48.71%
230 | Finish Material | 253455 | 260209 | 141842.79 | 118366.21 | 0 | 54.51%
240 | Gas Material | 10800 | 10972 | 1138.79 | 9833.21 | 0 | 10.38%
241 | Water Main/Insulation Mat | 47140 | 48750 | 30721.75 | 18028.25 | 0 | 63.02%
242 | Mech Room Material | 7000 | 7200 | 7324.66 | -124.66 | 0 | 101.7%
243 | Condensation Drains Mat | 0 | 0 | 0 | 0 | 0 | 0%
600 | Subcontractor | 1000 | 1000 | 4653.75 | -3653.75 | 0 | 465.4%
602 | Rental Equipment | 600 | 600 | 199.24 | 400.76 | 0 | 33.21%
995 | Payroll Burden | 113649.3 | 118231.65 | 98191.39 | 20040.26 | 0 | 83.05%
998 | Payroll Taxes | 19320.38 | 20099.39 | 16937.47 | 3161.92 | 0 | 84.27%
TOTAL |  | 806328.68 | 833731.04 | 574230.71 | 259500.33 | 0 | 68.87%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 262737 | 221400.5 | 41336.5 | 84.27%
Material | 9 | 431063 | 232848.36 | 198214.64 | 54.02%
Overhead | 2 | 1600 | 4852.99 | -3252.99 | 303.3%
Burden | 2 | 138331.04 | 115128.86 | 23202.18 | 83.23%
TOTAL | 23 | 833731.04 | 574230.71 | 259500.33 | 68.87%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 9980 | 3488.5 | 6491.5 | -65.05% | UNDER
101 | Takeoff & Purchase Labor | 14210 | 9538 | 4672 | -32.88% | UNDER
110 | Underground Labor | 9000 | 2949 | 6051 | -67.23% | UNDER
111 | Garage Labor | 36848 | 32824 | 4024 | -10.92% | UNDER
112 | Canout Labor | 9601 | 9569 | 32 | -0.3333% | ON
120 | Roughin Labor | 98240 | 96775 | 1465 | -1.491% | ON
130 | Finish Labor | 23938 | 17090.5 | 6847.5 | -28.61% | UNDER
140 | Gas Labor | 7520 | 8361 | -841 | 11.18% | OVER
141 | Water Main/Insulation Lab | 46100 | 35756 | 10344 | -22.44% | UNDER
142 | Mech Room Labor | 7300 | 5049.5 | 2250.5 | -30.83% | UNDER
210 | Underground Material | 9500 | 648.12 | 8851.88 | -93.18% | UNDER
211 | Garage Material | 33497 | 17156.73 | 16340.27 | -48.78% | UNDER
212 | Canout Material | 7915 | 8186.91 | -271.91 | 3.435% | ON
220 | Roughin Material | 53020 | 25828.61 | 27191.39 | -51.29% | UNDER
230 | Finish Material | 260209 | 141842.79 | 118366.21 | -45.49% | UNDER
240 | Gas Material | 10972 | 1138.79 | 9833.21 | -89.62% | UNDER
241 | Water Main/Insulation Mat | 48750 | 30721.75 | 18028.25 | -36.98% | UNDER
242 | Mech Room Material | 7200 | 7324.66 | -124.66 | 1.731% | ON
600 | Subcontractor | 1000 | 4653.75 | -3653.75 | 365.4% | CRITICAL
602 | Rental Equipment | 600 | 199.24 | 400.76 | -66.79% | UNDER
995 | Payroll Burden | 118231.65 | 98191.39 | 20040.26 | -16.95% | UNDER
998 | Payroll Taxes | 20099.39 | 16937.47 | 3161.92 | -15.73% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Keller Supply Company | 98249.98 | 32 | 51.77%
Consolidated Supply Co. | 36841.22 | 34 | 19.41%
Rosen Supply Kirkland | 32948.34 | 65 | 17.36%
Ferguson Enterprises, Inc. #3007 | 7236.35 | 19 | 3.813%
Patchworks, Inc. | 4393.75 | 1 | 2.315%
California Hydronics Corp | 4131 | 3 | 2.177%
Old Castle Infrastructure, Inc. | 2115 | 1 | 1.114%
Quality Concrete Products, Inc. $32 | 2061 | 2 | 1.086%
Minol, Inc. | 745.5 | 3 | 0.3928%
Manor Hardware & Construction Supply | 305.76 | 1 | 0.1611%
R.A. Brown Backflow Testing | 260 | 2 | 0.137%
Kele, Inc $ MI Controls | 231.39 | 1 | 0.1219%
AllWest Underground, Inc. | 199.24 | 1 | 0.105%
Capital One Credit Card | 79.71 | 4 | 0.042%
TOTAL AP | 189798.24 | 169

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Reed, Reuben H | 1459.5 | 64382 | 44.1124 | LEAD/SUPERVISOR
Castro Hernandez, Jose A | 1150 | 39171 | 34.0617 | JOURNEYMAN
Gauthier, Dillon R | 978 | 16590 | 16.9632 | APPRENTICE/HELPER
Silva Morales, Jair J | 968 | 25281 | 26.1167 | JOURNEYMAN
Lucas Tzintzun, Rafael | 471 | 8478 | 18 | APPRENTICE/HELPER
Kinssies, Jr, John E | 379 | 11051 | 29.1583 | JOURNEYMAN
Cruz Guzman, Joel A | 334 | 9385 | 28.0988 | JOURNEYMAN
Eliassen, Cory H | 305 | 8283 | 27.1574 | JOURNEYMAN
Gerard, Jeffrey S | 166 | 8776 | 52.8675 | LEAD/SUPERVISOR
McCabe, Thomas C | 145.5 | 4863 | 33.4227 | JOURNEYMAN
Hubbard, Robert W | 143.5 | 6869 | 47.8676 | LEAD/SUPERVISOR
Sepulveda Gonzalez, Alfredo | 131 | 4477 | 34.1756 | JOURNEYMAN
Romero Garza, Jesus I | 130 | 2484 | 19.1077 | APPRENTICE/HELPER
Guerrero, Ali A | 112 | 1904 | 17 | APPRENTICE/HELPER
Donelson, Richard T | 68 | 4250 | 62.5 | LEAD/SUPERVISOR
Sanders, Allen O | 58.5 | 2956 | 50.5299 | LEAD/SUPERVISOR
Roberts, Lake A | 24 | 600 | 25 | JOURNEYMAN
Vazquez Popoca, Jose N | 21 | 405 | 19.2857 | APPRENTICE/HELPER
Cruz Reyes, Jose | 16 | 384 | 24 | JOURNEYMAN
Trower-Kelly, Fidel D | 13 | 258 | 19.8462 | APPRENTICE/HELPER
Hubbard, Dustin R | 8 | 184 | 23 | JOURNEYMAN
Cruz Gonzalez, Julio C | 8 | 224 | 28 | JOURNEYMAN
Gerard, Jordan E | 4 | 144 | 36 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 6 | 1899.5 | 87378 | 26.78%
JOURNEYMAN | 11 | 3468.5 | 103903 | 48.9%
APPRENTICE/HELPER | 6 | 1725 | 30119 | 24.32%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 7093
Active workers | 23
Hours per unit (to date) | 709.3
Revenue per labor hour (billed) | 159.87
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 26.48% | 34% | -7.523%
Roughin labor share (code 120) | 37.39% | 45% | -7.609%
Top vendor concentration | 51.77% | 38% | 13.77%
Hours per unit | 709.3 | 95 | 614.3

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Gas Labor (140) over revised | ⚠ WATCH | Actual $8,361 vs revised $7,520 (+11%) — monitor
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $4,654 vs revised $1,000 (+365%) — needs immediate attention
Top vendor concentration (Keller Supply Compan) | ⚠ WATCH | 52% of AP ($98,250) — high, monitor
Retention aging | ✓ OK | $56,698 held · 5.0% of billed · standard range
Forecast margin | ✓ OK | 26.5% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 574230.71 | 574230.71 | 0
Revenue billed (AR ·-1) | -1133967 | 1133967 | -2267934
AP source total |  | 189798.24 | —
PR source total |  | 336529.36 | —
GL source total |  | 47903.11 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2057 live project. 17-tab JCR schema on revised budget basis.