## Summary
#2057 · Plaza Apartments
Natural & Built · 10 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
1133967 | 26.48% | 1133967 | 0
Key facts
Original contract |  | 1098897
Revised contract (CO impact) |  | 1133967
Executed COs (net) |  | 35070
Retention held |  | 56698.36
Revised expense budget |  | 833731.04
Forecast net profit |  | 300235.96
Percent complete |  | 100%
Live signals
Gas Labor (140) over | ⚠ WATCH | Actual $8,361 vs revised $7,520 (+11%) — monitor
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $4,654 vs revised $1,000 (+365%) — needs attention
Top vendor (Keller Supply Compan) | ⚠ WATCH | 52% of AP — high
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 26.5% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Keller Supply Company | 32 | 98249.98 | 51.77%
Consolidated Supply Co. | 34 | 36841.22 | 19.41%
Rosen Supply Kirkland | 65 | 32948.34 | 17.36%
Ferguson Enterprises, Inc. #3007 | 19 | 7236.35 | 3.813%
Patchworks, Inc. | 1 | 4393.75 | 2.315%
California Hydronics Corp | 3 | 4131 | 2.177%

## Transactions
Transactions Detail
JDR source transactions for job #2057 · 1993 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 07/06/18 | 76 | Donelson, Richard T | 2 | 125 | 920374
PR | 100 | 07/06/18 | 77 | Gerard, Jeffrey S | 1 | 50 | 920375
PR | 100 | 07/20/18 | 508 | Gerard, Jeffrey S | 1 | 50 | 920519
PR | 100 | 07/27/18 | 835 | Gerard, Jeffrey S | 1 | 50 | 20593
PR | 100 | 08/03/18 | 73 | Gerard, Jeffrey S | 2 | 100 | 20665
PR | 100 | 08/10/18 | 284 | Gerard, Jeffrey S | 1 | 50 | 920737
PR | 100 | 08/17/18 | 551 | Gerard, Jeffrey S | 2 | 100 | 20809
PR | 100 | 08/31/18 | 1070 | Gerard, Jeffrey S | 3 | 150 | 90962
PR | 100 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 100 | 10/05/18 | 103 | Gerard, Jeffrey S | 2 | 100 | 91392
PR | 100 | 10/26/18 | 775 | Gerard, Jeffrey S | 1 | 50 | 21616
PR | 100 | 11/09/18 | 258 | Gerard, Jeffrey S | 1 | 50 | 20892
PR | 100 | 11/16/18 | 513 | Donelson, Richard T | 1 | 62.5 | 21836
PR | 100 | 11/16/18 | 514 | Gerard, Jeffrey S | 1 | 50 | 21837
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 1 | 52 | 22057
PR | 100 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 100 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 100 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 100 | 01/04/19 | 73 | Gerard, Jeffrey S | 1 | 52 | 22301
PR | 100 | 01/11/19 | 282 | Gerard, Jeffrey S | 1 | 52 | 922484
PR | 100 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 100 | 02/01/19 | 71 | Gerard, Jeffrey S | 1 | 52 | 22700
PR | 100 | 02/22/19 | 648 | Gerard, Jeffrey S | 1 | 52 | 922910
PR | 100 | 03/15/19 | 563 | Gerard, Jeffrey S | 1 | 52 | 23125
PR | 100 | 03/22/19 | 776 | Donelson, Richard T | 1 | 62.5 | 923197
PR | 100 | 03/29/19 | 990 | Gerard, Jeffrey S | 2.5 | 130 | 23273
PR | 100 | 04/12/19 | 398 | Gerard, Jeffrey S | 2 | 104 | 23421
PR | 100 | 04/19/19 | 597 | Gerard, Jeffrey S | 1.5 | 78 | 923497
PR | 100 | 04/26/19 | 813 | Gerard, Jeffrey S | 1 | 55 | 23569
PR | 100 | 05/03/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 923644
PR | 100 | 05/10/19 | 235 | Gerard, Jeffrey S | 2 | 110 | 23720
PR | 100 | 05/17/19 | 468 | Gerard, Jeffrey S | 2 | 110 | 923799
PR | 100 | 05/24/19 | 681 | Gerard, Jeffrey S | 1.5 | 82.5 | 923876
PR | 100 | 05/31/19 | 953 | Gerard, Jeffrey S | 2 | 110 | 923953
PR | 100 | 06/07/19 | 255 | Gerard, Jeffrey S | 2 | 110 | 924030
PR | 100 | 06/14/19 | 524 | Gerard, Jeffrey S | 2 | 110 | 24104
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 1 | 55 | 24255
PR | 100 | 07/05/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 924330
PR | 100 | 07/12/19 | 353 | Gerard, Jeffrey S | 1 | 55 | 924405
PR | 100 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 100 | 07/26/19 | 686 | Gerard, Jeffrey S | 1 | 55 | 24635
PR | 100 | 08/02/19 | 77 | Gerard, Jeffrey S | 1 | 55 | 924708
PR | 100 | 08/09/19 | 329 | Gerard, Jeffrey S | 1 | 55 | 924782
PR | 100 | 08/16/19 | 637 | Gerard, Jeffrey S | 1 | 55 | 924856
PR | 100 | 11/15/19 | 513 | Gerard, Jeffrey S | 2.5 | 145 | 925849
PR | 100 | 11/22/19 | 685 | Gerard, Jeffrey S | 1 | 58 | 925924
PR | 100 | 12/20/19 | 619 | Gerard, Jeffrey S | 2 | 116 | 926308
PR | 101 | 06/29/18 | 1019 | Donelson, Richard T | 6 | 375 | 20300
PR | 101 | 07/06/18 | 76 | Donelson, Richard T | 4 | 250 | 920374
PR | 101 | 07/06/18 | 77 | Gerard, Jeffrey S | 1 | 50 | 920375
PR | 101 | 07/13/18 | 367 | Donelson, Richard T | 2 | 125 | 20400
PR | 101 | 07/20/18 | 507 | Donelson, Richard T | 2 | 125 | 920518
PR | 101 | 07/20/18 | 508 | Gerard, Jeffrey S | 3 | 150 | 920519
PR | 101 | 08/03/18 | 73 | Gerard, Jeffrey S | 1 | 50 | 20665
PR | 101 | 08/10/18 | 284 | Gerard, Jeffrey S | 1 | 50 | 920737
PR | 101 | 08/17/18 | 551 | Gerard, Jeffrey S | 1 | 50 | 20809
PR | 101 | 08/24/18 | 812 | Gerard, Jeffrey S | 3 | 150 | 20880
PR | 101 | 08/31/18 | 1070 | Gerard, Jeffrey S | 6 | 300 | 90962
PR | 101 | 09/07/18 | 106 | Gerard, Jeffrey S | 1 | 50 | 91032
PR | 101 | 09/14/18 | 341 | Gerard, Jeffrey S | 1 | 50 | 21174
PR | 101 | 09/21/18 | 553 | Gerard, Jeffrey S | 2 | 100 | 21245
PR | 101 | 09/28/18 | 740 | Gerard, Jeffrey S | 1 | 50 | 90884
PR | 101 | 10/05/18 | 102 | Donelson, Richard T | 4 | 250 | 91391
PR | 101 | 10/05/18 | 103 | Gerard, Jeffrey S | 2 | 100 | 91392
PR | 101 | 10/19/18 | 507 | Donelson, Richard T | 2 | 125 | 91541
PR | 101 | 10/26/18 | 775 | Gerard, Jeffrey S | 1 | 50 | 21616
PR | 101 | 11/02/18 | 76 | Donelson, Richard T | 2 | 125 | 21686
PR | 101 | 11/02/18 | 77 | Gerard, Jeffrey S | 1 | 50 | 21687
PR | 101 | 11/09/18 | 257 | Donelson, Richard T | 1 | 62.5 | 20891
PR | 101 | 11/16/18 | 513 | Donelson, Richard T | 3 | 187.5 | 21836
PR | 101 | 11/16/18 | 514 | Gerard, Jeffrey S | 2 | 100 | 21837
PR | 101 | 11/21/18 | 689 | Donelson, Richard T | 5 | 312.5 | 21911
PR | 101 | 11/30/18 | 900 | Donelson, Richard T | 1 | 62.5 | 921983
PR | 101 | 12/07/18 | 113 | Donelson, Richard T | 3 | 187.5 | 22056
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 12/21/18 | 578 | Gerard, Jeffrey S | 4 | 208 | 922269
PR | 101 | 12/28/18 | 769 | Gerard, Jeffrey S | 2 | 104 | 22343
PR | 101 | 01/04/19 | 73 | Gerard, Jeffrey S | 3 | 156 | 22301
PR | 101 | 01/11/19 | 282 | Gerard, Jeffrey S | 3 | 156 | 922484
PR | 101 | 01/18/19 | 543 | Gerard, Jeffrey S | 1 | 52 | 922558
PR | 101 | 01/25/19 | 786 | Donelson, Richard T | 1 | 62.5 | 922631
PR | 101 | 02/01/19 | 71 | Gerard, Jeffrey S | 3 | 156 | 22700
PR | 101 | 02/08/19 | 227 | Gerard, Jeffrey S | 2 | 104 | 22769
PR | 101 | 02/22/19 | 648 | Gerard, Jeffrey S | 3 | 156 | 922910
PR | 101 | 03/01/19 | 75 | Gerard, Jeffrey S | 1 | 52 | 22982
PR | 101 | 03/08/19 | 315 | Gerard, Jeffrey S | 1 | 52 | 923054
PR | 101 | 03/15/19 | 562 | Donelson, Richard T | 1 | 62.5 | 23124
PR | 101 | 03/15/19 | 563 | Gerard, Jeffrey S | 3 | 156 | 23125
PR | 101 | 03/22/19 | 777 | Gerard, Jeffrey S | 1 | 52 | 923198
PR | 101 | 03/29/19 | 990 | Gerard, Jeffrey S | 3 | 156 | 23273
PR | 101 | 04/12/19 | 398 | Gerard, Jeffrey S | 4 | 208 | 23421
PR | 101 | 04/19/19 | 597 | Gerard, Jeffrey S | 3 | 156 | 923497
PR | 101 | 04/26/19 | 813 | Gerard, Jeffrey S | 3 | 165 | 23569
PR | 101 | 05/03/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 923644
PR | 101 | 05/10/19 | 235 | Gerard, Jeffrey S | 3 | 165 | 23720
PR | 101 | 05/17/19 | 467 | Donelson, Richard T | 1 | 62.5 | 923798
PR | 101 | 05/17/19 | 468 | Gerard, Jeffrey S | 2 | 110 | 923799
PR | 101 | 05/24/19 | 680 | Donelson, Richard T | 3 | 187.5 | 923875
PR | 101 | 05/24/19 | 681 | Gerard, Jeffrey S | 1 | 55 | 923876
PR | 101 | 05/31/19 | 953 | Gerard, Jeffrey S | 1 | 55 | 923953
PR | 101 | 06/07/19 | 254 | Donelson, Richard T | 1 | 62.5 | 924029
PR | 101 | 06/07/19 | 255 | Gerard, Jeffrey S | 3 | 165 | 924030
PR | 101 | 06/14/19 | 523 | Donelson, Richard T | 2 | 125 | 24103
PR | 101 | 06/14/19 | 524 | Gerard, Jeffrey S | 2 | 110 | 24104
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 1 | 55 | 24180
PR | 101 | 06/28/19 | 911 | Gerard, Jeffrey S | 2 | 110 | 24255
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 1 | 62.5 | 924329
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 3 | 165 | 24485
PR | 101 | 07/26/19 | 685 | Donelson, Richard T | 1 | 62.5 | 24634
PR | 101 | 07/26/19 | 686 | Gerard, Jeffrey S | 1 | 55 | 24635
PR | 101 | 08/09/19 | 328 | Donelson, Richard T | 1 | 62.5 | 924781
PR | 101 | 08/09/19 | 329 | Gerard, Jeffrey S | 3 | 165 | 924782
PR | 101 | 08/16/19 | 637 | Gerard, Jeffrey S | 2 | 110 | 924856
PR | 101 | 09/06/19 | 85 | Donelson, Richard T | 2 | 125 | 925083
PR | 101 | 09/27/19 | 705 | Donelson, Richard T | 2 | 125 | 925310
PR | 101 | 09/27/19 | 706 | Gerard, Jeffrey S | 1 | 55 | 925311
PR | 101 | 10/04/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 25389
PR | 101 | 10/11/19 | 334 | Donelson, Richard T | 1 | 62.5 | 925468
PR | 101 | 10/11/19 | 335 | Gerard, Jeffrey S | 1 | 55 | 925469
PR | 101 | 10/18/19 | 527 | Donelson, Richard T | 1 | 62.5 | 25544
PR | 101 | 10/18/19 | 528 | Gerard, Jeffrey S | 1 | 55 | 25545
PR | 101 | 10/25/19 | 664 | Donelson, Richard T | 1 | 62.5 | 925504
PR | 101 | 11/08/19 | 253 | Donelson, Richard T | 1 | 62.5 | 925772
PR | 101 | 11/15/19 | 512 | Donelson, Richard T | 2 | 125 | 925848
PR | 101 | 11/27/19 | 917 | Donelson, Richard T | 3 | 187.5 | 925998
PR | 101 | 11/27/19 | 918 | Gerard, Jeffrey S | 1 | 58 | 925999
PR | 101 | 12/06/19 | 104 | Donelson, Richard T | 1 | 62.5 | 26076
PR | 101 | 12/13/19 | 465 | Donelson, Richard T | 1 | 62.5 | 926231
PR | 101 | 12/13/19 | 466 | Gerard, Jeffrey S | 1 | 58 | 926232
PR | 101 | 12/20/19 | 619 | Gerard, Jeffrey S | 1 | 58 | 926308
PR | 101 | 01/10/20 | 352 | Donelson, Richard T | 2 | 125 | 26540
PR | 101 | 01/10/20 | 353 | Gerard, Jeffrey S | 1 | 58 | 26541
PR | 101 | 01/24/20 | 751 | Gerard, Jeffrey S | 1 | 58 | 926401
PR | 110 | 07/13/18 | 350 | Reed, Reuben H | 4 | 164 | 20430
PR | 110 | 07/20/18 | 470 | Hubbard, Robert W | 2 | 94 | 20480
PR | 110 | 07/27/18 | 817 | Reed, Reuben H | 2 | 82 | 20574
PR | 110 | 08/03/18 | 35 | Hubbard, Robert W | 14 | 658 | 20626
PR | 110 | 08/03/18 | 46 | McCabe, Thomas C | 15 | 480 | 20637
PR | 110 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo | 16 | 496 | 20654
PR | 110 | 08/10/18 | 246 | Hubbard, Robert W | 4 | 188 | 20698
PR | 110 | 08/10/18 | 257 | McCabe, Thomas C | 6 | 192 | 20709
PR | 110 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo | 6 | 186 | 20726
PR | 110 | 08/17/18 | 514 | Hubbard, Robert W | 2 | 94 | 20771
PR | 110 | 08/17/18 | 524 | McCabe, Thomas C | 5 | 160 | 20781
PR | 110 | 08/17/18 | 541 | Sepulveda Gonzalez, Alfredo | 5 | 155 | 20798
PR | 111 | 11/30/18 | 879 | Reed, Reuben H | 8 | 344 | 21961
PR | 111 | 12/07/18 | 91 | Reed, Reuben H | 18 | 774 | 22033
PR | 111 | 12/14/18 | 316 | Reed, Reuben H | 32 | 1376 | 22175
PR | 111 | 12/21/18 | 514 | Castro Hernandez, Jose A | 24 | 792 | 22205
PR | 111 | 12/21/18 | 542 | Kinssies, Jr, John E | 18 | 486 | 22232
PR | 111 | 12/21/18 | 546 | Lucas Tzintzun, Rafael | 44 | 792 | 22236
PR | 111 | 12/21/18 | 556 | Reed, Reuben H | 38 | 1634 | 22246
PR | 111 | 12/21/18 | 567 | Silva Morales, Jair J | 46 | 1150 | 22257
PR | 111 | 12/28/18 | 705 | Castro Hernandez, Jose A | 26 | 858 | 22278
PR | 111 | 12/28/18 | 733 | Kinssies, Jr, John E | 16 | 432 | 22306
PR | 111 | 12/28/18 | 737 | Lucas Tzintzun, Rafael | 28 | 504 | 22310
PR | 111 | 12/28/18 | 747 | Reed, Reuben H | 20 | 860 | 22320
PR | 111 | 12/28/18 | 758 | Silva Morales, Jair J | 26 | 650 | 22331
PR | 111 | 01/04/19 | 10 | Castro Hernandez, Jose A | 26 | 858 | 22350
PR | 111 | 01/04/19 | 40 | Lucas Tzintzun, Rafael | 24 | 432 | 22381
PR | 111 | 01/04/19 | 50 | Reed, Reuben H | 24 | 1032 | 22391
PR | 111 | 01/04/19 | 61 | Silva Morales, Jair J | 16 | 400 | 22402
PR | 111 | 01/11/19 | 218 | Castro Hernandez, Jose A | 16 | 528 | 22420
PR | 111 | 01/11/19 | 244 | Hubbard, Robert W | 6 | 294 | 22446
PR | 111 | 01/11/19 | 246 | Kinssies, Jr, John E | 22 | 594 | 22448
PR | 111 | 01/11/19 | 250 | Lucas Tzintzun, Rafael | 28.5 | 513 | 22452
PR | 111 | 01/11/19 | 260 | Reed, Reuben H | 14.5 | 623.5 | 22462
PR | 111 | 01/11/19 | 271 | Silva Morales, Jair J | 40 | 1000 | 22473
PR | 111 | 01/18/19 | 473 | Castro Hernandez, Jose A | 24 | 792 | 22494
PR | 111 | 01/18/19 | 501 | Kinssies, Jr, John E | 38.5 | 1039.5 | 22522
PR | 111 | 01/18/19 | 526 | Silva Morales, Jair J | 39 | 975 | 22547
PR | 111 | 01/25/19 | 722 | Castro Hernandez, Jose A | 40 | 1320 | 22567
PR | 111 | 01/25/19 | 764 | Reed, Reuben H | 12 | 516 | 22609
PR | 111 | 01/25/19 | 775 | Silva Morales, Jair J | 32 | 800 | 22620
PR | 111 | 02/01/19 | 10 | Castro Hernandez, Jose A | 37 | 1221 | 22639
PR | 111 | 02/01/19 | 60 | Silva Morales, Jair J | 32 | 800 | 22689
PR | 111 | 02/08/19 | 165 | Castro Hernandez, Jose A | 24 | 792 | 22707
PR | 111 | 02/08/19 | 216 | Silva Morales, Jair J | 16 | 400 | 22758
PR | 111 | 02/15/19 | 327 | Castro Hernandez, Jose A | 21 | 693 | 22776
PR | 111 | 05/10/19 | 195 | Hubbard, Robert W | 1 | 50 | 23679
PR | 111 | 05/24/19 | 639 | Hubbard, Robert W | 1 | 50 | 23834
PR | 111 | 06/07/19 | 215 | Hubbard, Robert W | 4 | 200 | 23990
PR | 111 | 06/07/19 | 224 | McCabe, Thomas C | 4 | 140 | 23999
PR | 111 | 07/19/19 | 517 | Castro Hernandez, Jose A | 32 | 1120 | 24416
PR | 111 | 07/19/19 | 533 | Gauthier, Dillon R | 32 | 544 | 24432
PR | 111 | 07/19/19 | 558 | Reed, Reuben H | 16 | 720 | 24457
PR | 111 | 08/02/19 | 53 | Reed, Reuben H | 21 | 945 | 24684
PR | 111 | 08/09/19 | 306 | Reed, Reuben H | 8 | 360 | 24759
PR | 111 | 09/20/19 | 523 | Reed, Reuben H | 12 | 540 | 25209
PR | 111 | 10/04/19 | 58 | Reed, Reuben H | 16 | 720 | 25365
PR | 111 | 11/15/19 | 476 | Kinssies, Jr, John E | 16 | 560 | 25812
PR | 111 | 11/15/19 | 494 | Roberts, Lake A | 16 | 400 | 25830
PR | 111 | 11/22/19 | 665 | Roberts, Lake A | 8 | 200 | 25905
PR | 112 | 08/24/18 | 776 | Hubbard, Robert W | 1 | 47 | 20843
PR | 112 | 08/31/18 | 1031 | Hubbard, Robert W | 8 | 376 | 20926
PR | 112 | 08/31/18 | 1048 | Reed, Reuben H | 8 | 328 | 20943
PR | 112 | 09/07/18 | 50 | Cruz Guzman, Joel A | 16 | 368 | 20975
PR | 112 | 09/07/18 | 51 | Cruz Reyes, Jose | 16 | 384 | 20976
PR | 112 | 09/07/18 | 70 | Hubbard, Robert W | 9.5 | 446.5 | 20995
PR | 112 | 09/07/18 | 79 | McCabe, Thomas C | 8 | 256 | 21004
PR | 112 | 09/07/18 | 88 | Reed, Reuben H | 16 | 656 | 21013
PR | 112 | 09/14/18 | 302 | Hubbard, Robert W | 2 | 94 | 21136
PR | 112 | 09/14/18 | 320 | Reed, Reuben H | 8 | 328 | 21154
PR | 112 | 09/21/18 | 494 | Cruz Guzman, Joel A | 8 | 184 | 21186
PR | 112 | 09/21/18 | 533 | Reed, Reuben H | 1 | 41 | 21224
PR | 112 | 09/28/18 | 718 | Reed, Reuben H | 1 | 41 | 21296
PR | 112 | 10/12/18 | 288 | Reed, Reuben H | 3 | 123 | 21445
PR | 112 | 10/19/18 | 468 | Hubbard, Robert W | 1.5 | 70.5 | 21501
PR | 112 | 10/25/18 | 687 | Hubbard, Robert W | 15 | 705 | 21477
PR | 112 | 10/26/18 | 743 | McCabe, Thomas C | 24 | 768 | 21583
PR | 112 | 10/26/18 | 751 | Reed, Reuben H | 24 | 984 | 21591
PR | 112 | 11/02/18 | 39 | Hubbard, Robert W | 5 | 235 | 21648
PR | 112 | 11/02/18 | 55 | Reed, Reuben H | 20 | 820 | 21664
PR | 112 | 11/09/18 | 234 | Reed, Reuben H | 8 | 328 | 21737
PR | 112 | 11/16/18 | 465 | Hubbard, Robert W | 1 | 47 | 21793
PR | 112 | 11/16/18 | 467 | Kinssies, Jr, John E | 8 | 208 | 21795
PR | 112 | 11/16/18 | 474 | McCabe, Thomas C | 5 | 160 | 21802
PR | 112 | 11/16/18 | 482 | Reed, Reuben H | 26 | 1066 | 21810
PR | 112 | 11/16/18 | 504 | Hubbard, Robert W | 1 | -47 | 21793
PR | 112 | 11/16/18 | 508 | Hubbard, Robert W | 1 | 47 | 21833
PR | 112 | 11/21/18 | 650 | Hubbard, Robert W | 1 | 47 | 21871
PR | 112 | 11/21/18 | 658 | McCabe, Thomas C | 6.5 | 208 | 21879
PR | 112 | 11/21/18 | 666 | Reed, Reuben H | 4 | 164 | 21887
PR | 112 | 12/07/18 | 91 | Reed, Reuben H | 2 | 86 | 22033
PR | 120 | 09/28/18 | 718 | Reed, Reuben H | 2 | 82 | 21296
PR | 120 | 12/28/18 | 747 | Reed, Reuben H | 8 | 344 | 22320
PR | 120 | 01/11/19 | 244 | Hubbard, Robert W | 2 | 98 | 22446
PR | 120 | 01/11/19 | 260 | Reed, Reuben H | 7 | 301 | 22462
PR | 120 | 01/18/19 | 505 | Lucas Tzintzun, Rafael | 39.5 | 711 | 22526
PR | 120 | 01/18/19 | 515 | Reed, Reuben H | 30 | 1290 | 22536
PR | 120 | 01/25/19 | 750 | Kinssies, Jr, John E | 40 | 1080 | 22595
PR | 120 | 01/25/19 | 754 | Lucas Tzintzun, Rafael | 40 | 720 | 22599
PR | 120 | 01/25/19 | 764 | Reed, Reuben H | 25 | 1075 | 22609
PR | 120 | 02/01/19 | 38 | Kinssies, Jr, John E | 32 | 864 | 22667
PR | 120 | 02/01/19 | 42 | Lucas Tzintzun, Rafael | 40 | 720 | 22671
PR | 120 | 02/01/19 | 50 | Reed, Reuben H | 40 | 1720 | 22679
PR | 120 | 02/08/19 | 193 | Kinssies, Jr, John E | 24 | 648 | 22735
PR | 120 | 02/08/19 | 197 | Lucas Tzintzun, Rafael | 24 | 432 | 22739
PR | 120 | 02/08/19 | 205 | Reed, Reuben H | 24 | 1032 | 22747
PR | 120 | 02/08/19 | 216 | Silva Morales, Jair J | 8 | 200 | 22758
PR | 120 | 02/15/19 | 355 | Kinssies, Jr, John E | 14.5 | 391.5 | 22806
PR | 120 | 02/15/19 | 359 | Lucas Tzintzun, Rafael | 19 | 342 | 22810
PR | 120 | 02/15/19 | 367 | Reed, Reuben H | 21 | 903 | 22818
PR | 120 | 02/15/19 | 378 | Silva Morales, Jair J | 13 | 325 | 22829
PR | 120 | 02/22/19 | 585 | Castro Hernandez, Jose A | 40 | 1320 | 22847
PR | 120 | 02/22/19 | 613 | Kinssies, Jr, John E | 14.5 | 391.5 | 22875
PR | 120 | 02/22/19 | 617 | Lucas Tzintzun, Rafael | 48 | 864 | 22879
PR | 120 | 02/22/19 | 626 | Reed, Reuben H | 48 | 2064 | 22888
PR | 120 | 02/22/19 | 637 | Silva Morales, Jair J | 40 | 1000 | 22899
PR | 120 | 03/01/19 | 10 | Castro Hernandez, Jose A | 48 | 1584 | 22917
PR | 120 | 03/01/19 | 28 | Gauthier, Dillon R | 16 | 256 | 22935
PR | 120 | 03/01/19 | 44 | Lucas Tzintzun, Rafael | 40 | 720 | 22951
PR | 120 | 03/01/19 | 53 | Reed, Reuben H | 48 | 2064 | 22960
PR | 120 | 03/01/19 | 64 | Silva Morales, Jair J | 40 | 1000 | 22971
PR | 120 | 03/08/19 | 252 | Castro Hernandez, Jose A | 40 | 1320 | 22990
PR | 120 | 03/08/19 | 284 | Lucas Tzintzun, Rafael | 40 | 720 | 23023
PR | 120 | 03/08/19 | 293 | Reed, Reuben H | 36 | 1548 | 23032
PR | 120 | 03/08/19 | 303 | Silva Morales, Jair J | 40 | 1000 | 23042
PR | 120 | 03/15/19 | 499 | Castro Hernandez, Jose A | 40 | 1320 | 23061
PR | 120 | 03/15/19 | 516 | Gauthier, Dillon R | 40 | 640 | 23078
PR | 120 | 03/15/19 | 531 | Lucas Tzintzun, Rafael | 16 | 288 | 23093
PR | 120 | 03/15/19 | 540 | Reed, Reuben H | 32 | 1376 | 23102
PR | 120 | 03/15/19 | 551 | Silva Morales, Jair J | 32 | 800 | 23113
PR | 120 | 03/22/19 | 713 | Castro Hernandez, Jose A | 32 | 1056 | 23134
PR | 120 | 03/22/19 | 730 | Gauthier, Dillon R | 40 | 640 | 23151
PR | 120 | 03/22/19 | 745 | Lucas Tzintzun, Rafael | 40 | 720 | 23166
PR | 120 | 03/22/19 | 753 | Reed, Reuben H | 40 | 1720 | 23174
PR | 120 | 03/22/19 | 764 | Silva Morales, Jair J | 32 | 800 | 23185
PR | 120 | 03/29/19 | 924 | Castro Hernandez, Jose A | 40 | 1320 | 23208
PR | 120 | 03/29/19 | 942 | Gauthier, Dillon R | 40 | 640 | 23226
PR | 120 | 03/29/19 | 965 | Reed, Reuben H | 40 | 1720 | 23249
PR | 120 | 03/29/19 | 976 | Silva Morales, Jair J | 40 | 1000 | 23260
PR | 120 | 04/05/19 | 86 | Castro Hernandez, Jose A | 40 | 1320 | 23280
PR | 120 | 04/05/19 | 104 | Gauthier, Dillon R | 40 | 640 | 23298
PR | 120 | 04/05/19 | 128 | Reed, Reuben H | 40 | 1720 | 23322
PR | 120 | 04/05/19 | 139 | Silva Morales, Jair J | 40 | 1000 | 23333
PR | 120 | 04/12/19 | 330 | Castro Hernandez, Jose A | 4 | 198 | 23354
PR | 120 | 04/12/19 | 330 | Castro Hernandez, Jose A | 40 | 1320 | 23354
PR | 120 | 04/12/19 | 347 | Gauthier, Dillon R | 4 | 96 | 23371
PR | 120 | 04/12/19 | 347 | Gauthier, Dillon R | 40 | 640 | 23371
PR | 120 | 04/12/19 | 372 | Reed, Reuben H | 10 | 675 | 23396
PR | 120 | 04/12/19 | 372 | Reed, Reuben H | 33 | 1485 | 23396
PR | 120 | 04/12/19 | 383 | Silva Morales, Jair J | 4 | 150 | 23407
PR | 120 | 04/12/19 | 383 | Silva Morales, Jair J | 40 | 1000 | 23407
PR | 120 | 04/19/19 | 527 | Castro Hernandez, Jose A | 8 | 396 | 23428
PR | 120 | 04/19/19 | 527 | Castro Hernandez, Jose A | 40 | 1320 | 23428
PR | 120 | 04/19/19 | 534 | Cruz Guzman, Joel A | 6 | 225 | 23435
PR | 120 | 04/19/19 | 534 | Cruz Guzman, Joel A | 24 | 600 | 23435
PR | 120 | 04/19/19 | 545 | Gauthier, Dillon R | 8 | 192 | 23446
PR | 120 | 04/19/19 | 545 | Gauthier, Dillon R | 40 | 640 | 23446
PR | 120 | 04/19/19 | 570 | Reed, Reuben H | 38 | 1710 | 23471
PR | 120 | 04/19/19 | 576 | Romero Garza, Jesus I | 10 | 180 | 23477
PR | 120 | 04/19/19 | 581 | Silva Morales, Jair J | 8 | 300 | 23482
PR | 120 | 04/19/19 | 581 | Silva Morales, Jair J | 40 | 1000 | 23482
PR | 120 | 04/26/19 | 747 | Castro Hernandez, Jose A | 6 | 297 | 23504
PR | 120 | 04/26/19 | 747 | Castro Hernandez, Jose A | 40 | 1320 | 23504
PR | 120 | 04/26/19 | 754 | Cruz Guzman, Joel A | 6 | 252 | 23511
PR | 120 | 04/26/19 | 754 | Cruz Guzman, Joel A | 24 | 672 | 23511
PR | 120 | 04/26/19 | 764 | Gauthier, Dillon R | 8 | 204 | 23521
PR | 120 | 04/26/19 | 764 | Gauthier, Dillon R | 40 | 680 | 23521
PR | 120 | 04/26/19 | 774 | Hubbard, Robert W | 7 | 350 | 23531
PR | 120 | 04/26/19 | 789 | Reed, Reuben H | 37 | 1665 | 23546
PR | 120 | 04/26/19 | 795 | Romero Garza, Jesus I | 8 | 216 | 23552
PR | 120 | 04/26/19 | 795 | Romero Garza, Jesus I | 40 | 720 | 23552
PR | 120 | 04/26/19 | 800 | Silva Morales, Jair J | 6 | 243 | 23557
PR | 120 | 04/26/19 | 800 | Silva Morales, Jair J | 40 | 1080 | 23557
PR | 120 | 05/03/19 | 14 | Castro Hernandez, Jose A | 32 | 1056 | 23576
PR | 120 | 05/03/19 | 21 | Cruz Guzman, Joel A | 20 | 560 | 23583
PR | 120 | 05/03/19 | 32 | Gauthier, Dillon R | 4 | 102 | 23594
PR | 120 | 05/03/19 | 32 | Gauthier, Dillon R | 40 | 680 | 23594
PR | 120 | 05/03/19 | 58 | Reed, Reuben H | 6 | 405 | 23620
PR | 120 | 05/03/19 | 58 | Reed, Reuben H | 40 | 1800 | 23620
PR | 120 | 05/03/19 | 64 | Romero Garza, Jesus I | 6 | 162 | 23626
PR | 120 | 05/03/19 | 64 | Romero Garza, Jesus I | 40 | 720 | 23626
PR | 120 | 05/03/19 | 69 | Silva Morales, Jair J | 6 | 243 | 23631
PR | 120 | 05/03/19 | 69 | Silva Morales, Jair J | 40 | 1080 | 23631
PR | 120 | 05/10/19 | 167 | Castro Hernandez, Jose A | 36 | 1260 | 23651
PR | 120 | 05/10/19 | 174 | Cruz Guzman, Joel A | 6 | 252 | 23658
PR | 120 | 05/10/19 | 174 | Cruz Guzman, Joel A | 24 | 672 | 23658
PR | 120 | 05/10/19 | 185 | Gauthier, Dillon R | 4 | 102 | 23669
PR | 120 | 05/10/19 | 185 | Gauthier, Dillon R | 40 | 680 | 23669
PR | 120 | 05/10/19 | 195 | Hubbard, Robert W | 2 | 100 | 23679
PR | 120 | 05/10/19 | 211 | Reed, Reuben H | 38 | 1710 | 23695
PR | 120 | 05/10/19 | 217 | Romero Garza, Jesus I | 2 | 54 | 23702
PR | 120 | 05/10/19 | 217 | Romero Garza, Jesus I | 24 | 432 | 23702
PR | 120 | 05/10/19 | 222 | Silva Morales, Jair J | 6 | 243 | 23707
PR | 120 | 05/10/19 | 222 | Silva Morales, Jair J | 40 | 1080 | 23707
PR | 120 | 05/17/19 | 417 | Gauthier, Dillon R | 36 | 612 | 23748
PR | 120 | 05/17/19 | 427 | Hubbard, Robert W | 1 | 50 | 23758
PR | 120 | 05/17/19 | 443 | Reed, Reuben H | 30 | 1350 | 23774
PR | 120 | 05/17/19 | 453 | Silva Morales, Jair J | 40 | 1080 | 23784
PR | 120 | 05/24/19 | 629 | Gauthier, Dillon R | 4 | 68 | 23824
PR | 120 | 05/24/19 | 639 | Hubbard, Robert W | 6 | 300 | 23834
PR | 120 | 05/24/19 | 655 | Reed, Reuben H | 4 | 180 | 23850
PR | 120 | 05/31/19 | 913 | Hubbard, Robert W | 2 | 100 | 23913
PR | 120 | 05/31/19 | 929 | Reed, Reuben H | 4 | 180 | 23929
PR | 120 | 06/07/19 | 205 | Gauthier, Dillon R | 8 | 136 | 23980
PR | 120 | 06/07/19 | 215 | Hubbard, Robert W | 4 | 200 | 23990
PR | 120 | 06/07/19 | 224 | McCabe, Thomas C | 4 | 140 | 23999
PR | 120 | 06/07/19 | 230 | Reed, Reuben H | 2 | 90 | 24005
PR | 120 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo | 8 | 280 | 24015
PR | 120 | 06/07/19 | 241 | Silva Morales, Jair J | 8 | 216 | 24016
PR | 120 | 06/14/19 | 458 | Castro Hernandez, Jose A | 24 | 840 | 24039
PR | 120 | 06/14/19 | 464 | Cruz Guzman, Joel A | 16 | 448 | 24045
PR | 120 | 06/14/19 | 473 | Gauthier, Dillon R | 8 | 136 | 24054
PR | 120 | 06/14/19 | 499 | Reed, Reuben H | 21 | 945 | 24080
PR | 120 | 06/21/19 | 627 | Castro Hernandez, Jose A | 24 | 840 | 24113
PR | 120 | 06/21/19 | 634 | Cruz Guzman, Joel A | 32 | 896 | 24120
PR | 120 | 06/21/19 | 670 | Reed, Reuben H | 29 | 1305 | 24156
PR | 120 | 06/28/19 | 887 | Reed, Reuben H | 4 | 180 | 24231
PR | 120 | 07/12/19 | 328 | Reed, Reuben H | 16 | 720 | 24380
PR | 120 | 07/19/19 | 533 | Gauthier, Dillon R | 1 | 17 | 24432
PR | 120 | 07/19/19 | 543 | Hubbard, Robert W | 2 | 100 | 24442
PR | 120 | 07/26/19 | 661 | Reed, Reuben H | 6 | 270 | 24610
PR | 120 | 08/16/19 | 613 | Reed, Reuben H | 8 | 360 | 24832
PR | 120 | 08/23/19 | 850 | Reed, Reuben H | 8 | 360 | 24908
PR | 120 | 08/30/19 | 1028 | Kinssies, Jr, John E | 8 | 248 | 24970
PR | 120 | 09/27/19 | 669 | Kinssies, Jr, John E | 2 | 62 | 25274
PR | 120 | 10/11/19 | 274 | Cruz Guzman, Joel A | 8 | 224 | 25408
PR | 120 | 10/11/19 | 312 | Reed, Reuben H | 8 | 360 | 25446
PR | 120 | 10/11/19 | 323 | Silva Morales, Jair J | 8 | 216 | 25457
PR | 120 | 10/18/19 | 505 | Reed, Reuben H | 2 | 90 | 25522
PR | 120 | 11/08/19 | 231 | Reed, Reuben H | 2 | 98 | 25750
PR | 120 | 11/15/19 | 476 | Kinssies, Jr, John E | 13 | 455 | 25812
PR | 120 | 11/22/19 | 647 | Kinssies, Jr, John E | 22 | 770 | 25887
PR | 120 | 12/27/19 | 754 | Reed, Reuben H | 11 | 539 | 26362
PR | 120 | 01/03/20 | 57 | Reed, Reuben H | 3 | 147 | 26440
PR | 120 | 01/17/20 | 596 | Reed, Reuben H | 2 | 98 | 26595
PR | 130 | 05/31/19 | 937 | Sanders, Allen O | 3 | 147 | 23937
PR | 130 | 08/16/19 | 583 | Eliassen, Cory H | 3 | 81 | 24802
PR | 130 | 08/16/19 | 588 | Gauthier, Dillon R | 2 | 34 | 24807
PR | 130 | 08/16/19 | 621 | Sanders, Allen O | 3 | 147 | 24840
PR | 130 | 08/16/19 | 628 | Trower-Kelly, Fidel D | 3 | 54 | 24847
PR | 130 | 08/16/19 | 629 | Vazquez Popoca, Jose N | 3 | 51 | 24848
PR | 130 | 08/23/19 | 819 | Eliassen, Cory H | 37 | 999 | 24877
PR | 130 | 08/23/19 | 824 | Gauthier, Dillon R | 18 | 306 | 24882
PR | 130 | 08/23/19 | 837 | Kinssies, Jr, John E | 4 | 124 | 24895
PR | 130 | 08/23/19 | 858 | Sanders, Allen O | 3.5 | 171.5 | 24916
PR | 130 | 08/23/19 | 865 | Trower-Kelly, Fidel D | 2 | 36 | 24923
PR | 130 | 08/23/19 | 866 | Vazquez Popoca, Jose N | 2 | 34 | 24924
PR | 130 | 08/30/19 | 1010 | Eliassen, Cory H | 40 | 1080 | 24952
PR | 130 | 08/30/19 | 1015 | Gauthier, Dillon R | 8 | 136 | 24957
PR | 130 | 08/30/19 | 1019 | Guerrero, Ali A | 8 | 136 | 24961
PR | 130 | 09/06/19 | 31 | Eliassen, Cory H | 32 | 864 | 25029
PR | 130 | 09/06/19 | 40 | Guerrero, Ali A | 32 | 544 | 25038
PR | 130 | 09/06/19 | 70 | Sanders, Allen O | 3.5 | 171.5 | 25068
PR | 130 | 09/13/19 | 255 | Eliassen, Cory H | 40 | 1080 | 25104
PR | 130 | 09/13/19 | 260 | Gauthier, Dillon R | 40 | 680 | 25109
PR | 130 | 09/13/19 | 264 | Guerrero, Ali A | 24 | 408 | 25113
PR | 130 | 09/13/19 | 293 | Sanders, Allen O | 4 | 196 | 25142
PR | 130 | 09/20/19 | 492 | Eliassen, Cory H | 32 | 864 | 25178
PR | 130 | 09/20/19 | 497 | Gauthier, Dillon R | 24 | 408 | 25183
PR | 130 | 09/20/19 | 501 | Guerrero, Ali A | 40 | 680 | 25187
PR | 130 | 09/20/19 | 531 | Sanders, Allen O | 5 | 245 | 25217
PR | 130 | 09/27/19 | 648 | Eliassen, Cory H | 40 | 1080 | 25253
PR | 130 | 09/27/19 | 653 | Gauthier, Dillon R | 40 | 680 | 25258
PR | 130 | 09/27/19 | 654 | Gerard, Jordan E | 4 | 144 | 25259
PR | 130 | 09/27/19 | 657 | Guerrero, Ali A | 8 | 136 | 25262
PR | 130 | 09/27/19 | 690 | Sanders, Allen O | 6.5 | 318.5 | 25295
PR | 130 | 10/04/19 | 24 | Eliassen, Cory H | 24 | 648 | 25331
PR | 130 | 10/04/19 | 29 | Gauthier, Dillon R | 8 | 136 | 25336
PR | 130 | 10/04/19 | 66 | Sanders, Allen O | 3 | 147 | 25373
PR | 130 | 10/11/19 | 279 | Eliassen, Cory H | 16 | 432 | 25413
PR | 130 | 10/11/19 | 284 | Gauthier, Dillon R | 8 | 136 | 25418
PR | 130 | 10/11/19 | 321 | Sanders, Allen O | 5 | 245 | 25455
PR | 130 | 10/18/19 | 472 | Eliassen, Cory H | 21 | 567 | 25488
PR | 130 | 10/18/19 | 477 | Gauthier, Dillon R | 8 | 136 | 25493
PR | 130 | 10/18/19 | 514 | Sanders, Allen O | 3 | 147 | 25531
PR | 130 | 10/25/19 | 607 | Eliassen, Cory H | 4 | 108 | 25564
PR | 130 | 10/25/19 | 650 | Sanders, Allen O | 1 | 49 | 25607
PR | 130 | 11/01/19 | 23 | Eliassen, Cory H | 8 | 240 | 25640
PR | 130 | 11/01/19 | 66 | Sanders, Allen O | 5 | 270 | 25683
PR | 130 | 11/01/19 | 73 | Vazquez Popoca, Jose N | 8 | 160 | 25690
PR | 130 | 11/08/19 | 197 | Eliassen, Cory H | 8 | 240 | 25716
PR | 130 | 11/08/19 | 217 | Kinssies, Jr, John E | 4 | 140 | 25736
PR | 130 | 11/08/19 | 240 | Sanders, Allen O | 2 | 108 | 25759
PR | 130 | 11/08/19 | 246 | Trower-Kelly, Fidel D | 8 | 168 | 25765
PR | 130 | 11/08/19 | 247 | Vazquez Popoca, Jose N | 8 | 160 | 25766
PR | 130 | 11/15/19 | 499 | Sanders, Allen O | 2 | 108 | 25835
PR | 130 | 11/22/19 | 670 | Sanders, Allen O | 7.5 | 405 | 25910
PR | 130 | 12/06/19 | 91 | Sanders, Allen O | 1.5 | 81 | 26063
PR | 130 | 12/13/19 | 404 | Cruz Gonzalez, Julio C | 8 | 224 | 26169
PR | 140 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo | 8 | 280 | 24015
PR | 140 | 06/14/19 | 499 | Reed, Reuben H | 7 | 315 | 24080
PR | 140 | 06/28/19 | 845 | Castro Hernandez, Jose A | 16 | 560 | 24189
PR | 140 | 06/28/19 | 862 | Gauthier, Dillon R | 16 | 272 | 24206
PR | 140 | 07/05/19 | 34 | Gauthier, Dillon R | 16 | 272 | 24281
PR | 140 | 07/12/19 | 287 | Castro Hernandez, Jose A | 8 | 280 | 24339
PR | 140 | 07/12/19 | 303 | Gauthier, Dillon R | 8 | 136 | 24355
PR | 140 | 07/19/19 | 517 | Castro Hernandez, Jose A | 8 | 280 | 24416
PR | 140 | 07/19/19 | 558 | Reed, Reuben H | 12 | 540 | 24457
PR | 140 | 07/26/19 | 621 | Castro Hernandez, Jose A | 32 | 1120 | 24570
PR | 140 | 07/26/19 | 636 | Gauthier, Dillon R | 24 | 408 | 24585
PR | 140 | 07/26/19 | 661 | Reed, Reuben H | 16 | 720 | 24610
PR | 140 | 08/02/19 | 13 | Castro Hernandez, Jose A | 24 | 840 | 24644
PR | 140 | 08/02/19 | 38 | Hubbard, Robert W | 5 | 250 | 24669
PR | 140 | 08/09/19 | 281 | Gauthier, Dillon R | 12 | 204 | 24734
PR | 140 | 08/09/19 | 306 | Reed, Reuben H | 11 | 495 | 24759
PR | 140 | 08/23/19 | 835 | Hubbard, Robert W | 1 | 50 | 24893
PR | 140 | 08/23/19 | 837 | Kinssies, Jr, John E | 4 | 124 | 24895
PR | 140 | 09/13/19 | 285 | Reed, Reuben H | 15 | 675 | 25134
PR | 140 | 09/20/19 | 523 | Reed, Reuben H | 12 | 540 | 25209
PR | 141 | 01/11/19 | 260 | Reed, Reuben H | 2 | 86 | 22462
PR | 141 | 04/19/19 | 553 | Hubbard, Dustin R | 8 | 184 | 23454
PR | 141 | 05/17/19 | 399 | Castro Hernandez, Jose A | 40 | 1400 | 23730
PR | 141 | 05/17/19 | 406 | Cruz Guzman, Joel A | 40 | 1120 | 23737
PR | 141 | 05/17/19 | 443 | Reed, Reuben H | 10 | 450 | 23774
PR | 141 | 05/24/19 | 611 | Castro Hernandez, Jose A | 40 | 1400 | 23806
PR | 141 | 05/24/19 | 618 | Cruz Guzman, Joel A | 40 | 1120 | 23813
PR | 141 | 05/24/19 | 629 | Gauthier, Dillon R | 36 | 612 | 23824
PR | 141 | 05/24/19 | 639 | Hubbard, Robert W | 1 | 50 | 23834
PR | 141 | 05/24/19 | 649 | McCabe, Thomas C | 18 | 630 | 23844
PR | 141 | 05/24/19 | 655 | Reed, Reuben H | 36 | 1620 | 23850
PR | 141 | 05/24/19 | 664 | Sepulveda Gonzalez, Alfredo | 24 | 840 | 23859
PR | 141 | 05/24/19 | 665 | Silva Morales, Jair J | 32 | 864 | 23860
PR | 141 | 05/31/19 | 885 | Castro Hernandez, Jose A | 29 | 1015 | 23885
PR | 141 | 05/31/19 | 892 | Cruz Guzman, Joel A | 8 | 224 | 23892
PR | 141 | 05/31/19 | 903 | Gauthier, Dillon R | 32 | 544 | 23903
PR | 141 | 05/31/19 | 923 | McCabe, Thomas C | 19 | 665 | 23923
PR | 141 | 05/31/19 | 929 | Reed, Reuben H | 28 | 1260 | 23929
PR | 141 | 05/31/19 | 938 | Sepulveda Gonzalez, Alfredo | 24 | 840 | 23938
PR | 141 | 05/31/19 | 939 | Silva Morales, Jair J | 32 | 864 | 23939
PR | 141 | 06/07/19 | 187 | Castro Hernandez, Jose A | 40 | 1400 | 23962
PR | 141 | 06/07/19 | 194 | Cruz Guzman, Joel A | 40 | 1120 | 23969
PR | 141 | 06/07/19 | 205 | Gauthier, Dillon R | 24 | 408 | 23980
PR | 141 | 06/07/19 | 215 | Hubbard, Robert W | 4.5 | 225 | 23990
PR | 141 | 06/07/19 | 224 | McCabe, Thomas C | 24 | 840 | 23999
PR | 141 | 06/07/19 | 230 | Reed, Reuben H | 38 | 1710 | 24005
PR | 141 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo | 24 | 840 | 24015
PR | 141 | 06/07/19 | 241 | Silva Morales, Jair J | 16 | 432 | 24016
PR | 141 | 06/14/19 | 458 | Castro Hernandez, Jose A | 13 | 455 | 24039
PR | 141 | 06/14/19 | 464 | Cruz Guzman, Joel A | 16 | 448 | 24045
PR | 141 | 06/14/19 | 473 | Gauthier, Dillon R | 32 | 544 | 24054
PR | 141 | 06/14/19 | 499 | Reed, Reuben H | 12 | 540 | 24080
PR | 141 | 06/14/19 | 509 | Silva Morales, Jair J | 40 | 1080 | 24090
PR | 141 | 06/21/19 | 627 | Castro Hernandez, Jose A | 8 | 280 | 24113
PR | 141 | 06/21/19 | 644 | Gauthier, Dillon R | 37 | 629 | 24130
PR | 141 | 06/21/19 | 680 | Silva Morales, Jair J | 30 | 810 | 24166
PR | 141 | 06/28/19 | 845 | Castro Hernandez, Jose A | 24 | 840 | 24189
PR | 141 | 06/28/19 | 862 | Gauthier, Dillon R | 24 | 408 | 24206
PR | 141 | 06/28/19 | 887 | Reed, Reuben H | 24 | 1080 | 24231
PR | 141 | 07/05/19 | 17 | Castro Hernandez, Jose A | 32 | 1120 | 24264
PR | 141 | 07/05/19 | 34 | Gauthier, Dillon R | 16 | 272 | 24281
PR | 141 | 07/05/19 | 59 | Reed, Reuben H | 32 | 1440 | 24307
PR | 141 | 07/12/19 | 287 | Castro Hernandez, Jose A | 8 | 280 | 24339
PR | 141 | 07/12/19 | 303 | Gauthier, Dillon R | 8 | 136 | 24355
PR | 141 | 07/19/19 | 543 | Hubbard, Robert W | 1 | 50 | 24442
PR | 141 | 07/26/19 | 621 | Castro Hernandez, Jose A | 8 | 280 | 24570
PR | 141 | 07/26/19 | 636 | Gauthier, Dillon R | 16 | 272 | 24585
PR | 141 | 07/26/19 | 646 | Hubbard, Robert W | 4 | 200 | 24595
PR | 141 | 07/26/19 | 661 | Reed, Reuben H | 8 | 360 | 24610
PR | 141 | 08/02/19 | 28 | Gauthier, Dillon R | 24 | 408 | 24659
PR | 141 | 08/09/19 | 265 | Castro Hernandez, Jose A | 4 | 140 | 24718
PR | 141 | 08/09/19 | 281 | Gauthier, Dillon R | 4 | 68 | 24734
PR | 141 | 09/27/19 | 666 | Hubbard, Robert W | 2 | 100 | 25271
PR | 141 | 09/27/19 | 669 | Kinssies, Jr, John E | 8 | 248 | 25274
PR | 141 | 10/18/19 | 505 | Reed, Reuben H | 5 | 225 | 25522
PR | 141 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo | 8 | 280 | 25532
PR | 142 | 11/02/18 | 48 | McCabe, Thomas C | 7 | 224 | 21657
PR | 142 | 08/02/19 | 53 | Reed, Reuben H | 5 | 225 | 24684
PR | 142 | 08/09/19 | 265 | Castro Hernandez, Jose A | 12 | 420 | 24718
PR | 142 | 08/09/19 | 291 | Hubbard, Robert W | 2 | 100 | 24744
PR | 142 | 08/09/19 | 306 | Reed, Reuben H | 8 | 360 | 24759
PR | 142 | 08/16/19 | 598 | Hubbard, Robert W | 3 | 150 | 24817
PR | 142 | 08/16/19 | 600 | Kinssies, Jr, John E | 40 | 1240 | 24819
PR | 142 | 08/23/19 | 835 | Hubbard, Robert W | 8 | 400 | 24893
PR | 142 | 08/23/19 | 837 | Kinssies, Jr, John E | 30.5 | 945.5 | 24895
PR | 142 | 09/20/19 | 509 | Hubbard, Robert W | 2 | 100 | 25195
PR | 142 | 09/27/19 | 666 | Hubbard, Robert W | 2 | 100 | 25271
PR | 142 | 09/27/19 | 682 | Reed, Reuben H | 8 | 360 | 25287
PR | 142 | 10/25/19 | 624 | Hubbard, Robert W | 2 | 100 | 25581
PR | 142 | 10/25/19 | 641 | Reed, Reuben H | 1 | 45 | 25598
PR | 142 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo | 8 | 280 | 25608
GL | 210 | 08/10/18 | 346 | Req 4565 |  | 79.85
GL | 210 | 08/22/18 | 660 | Req 4627 |  | 13.36
AP | 210 | 08/22/18 | 721 | Rosen Supply Kirkland |  | 524.86 | 4255240-00
AP | 210 | 09/04/18 | 23 | Rosen Supply Kirkland |  | 30.05 | 4255796-00
AP | 211 | 10/10/18 | 148 | Rosen Supply Kirkland |  | 251.05 | 4257004-00
GL | 211 | 11/09/18 | 325 | Req 4767 |  | 570
AP | 211 | 11/30/18 | 1023 | Rosen Supply Kirkland |  | 249.74 | 4259483-00
GL | 211 | 12/31/18 | 872 | Req 5658 |  | 1160.69
GL | 211 | 01/15/19 | 425 | Req 4898 |  | 267.4
AP | 211 | 01/21/19 | 580 | Rosen Supply Kirkland |  | 3200.94 | 4260781-00
AP | 211 | 01/22/19 | 636 | Rosen Supply Kirkland |  | 898.8 | 4261295-00
AP | 211 | 01/22/19 | 637 | Rosen Supply Kirkland |  | 4272.56 | 4261492-00
GL | 211 | 01/23/19 | 687 | Req 4980 |  | 404.93
AP | 211 | 01/25/19 | 829 | Rosen Supply Kirkland |  | 64.25 | 4261492-01
AP | 211 | 02/08/19 | 279 | Rosen Supply Kirkland |  | 1309.19 | 4261918-00
AP | 211 | 02/22/19 | 681 | Rosen Supply Kirkland |  | 2499.9 | 4262841-00
AP | 211 | 02/22/19 | 682 | Rosen Supply Kirkland |  | 63.63 | 4263044-00
AP | 211 | 02/22/19 | 683 | Rosen Supply Kirkland |  | 348.68 | 4263107-00
GL | 211 | 03/04/19 | 195 | Req 5717 |  | 186.24
GL | 211 | 03/08/19 | 351 | Req 5041 |  | 75.88
GL | 211 | 03/28/19 | 1080 | Req 5857 |  | 80.79
GL | 211 | 04/30/19 | 903 | Req 5924 |  | 35
GL | 211 | 05/13/19 | 309 | Req 5198 |  | 28
GL | 211 | 05/30/19 | 839 | Req 5999 |  | 108.7
GL | 211 | 06/05/19 | 142 | Req 5258 |  | 9.62
AP | 211 | 06/12/19 | 425 | Ferguson Enterprises, Inc. #3007 |  | 33.3 | 7197016
AP | 211 | 06/13/19 | 546 | Rosen Supply Kirkland |  | 166.44 | 4268319-00
GL | 211 | 07/10/19 | 180 | Req 6137 |  | 268.74
AP | 211 | 08/14/19 | 546 | Rosen Supply Kirkland |  | 99.84 | 4270686-00
GL | 211 | 08/20/19 | 712 | Req 6241 |  | 134.72
GL | 211 | 09/16/19 | 368 | Req 6338 |  | 6.4
GL | 211 | 11/13/19 | 398 | Req 6559 |  | 52.4
GL | 211 | 11/19/19 | 574 | Req 6579 |  | 12.4
GL | 211 | 12/06/19 | 165 | Req 6602 |  | -228.54
AP | 211 | 12/09/19 | 217 | Rosen Supply Kirkland |  | 435.01 | 4274995-00
AP | 211 | 12/12/19 | 491 | Rosen Supply Kirkland |  | 20.73 | 4275492-00
AP | 211 | 01/06/20 | 113 | Rosen Supply Kirkland |  | 38.27 | 4276744-00
AP | 212 | 08/28/18 | 935 | Rosen Supply Kirkland |  | 254.41 | 4255337-00
AP | 212 | 09/01/18 | 395 | Rosen Supply Kirkland |  | -254.41 | 4255337-00A
AP | 212 | 09/01/18 | 396 | Rosen Supply Kirkland |  | 354.41 | 4255337-00B
GL | 212 | 09/10/18 | 168 | Req 5319 |  | 3206.02
GL | 212 | 09/25/18 | 635 | Req 5355 |  | 11
GL | 212 | 09/30/18 | 783 | Req 5426 |  | 3742.91
GL | 212 | 11/09/18 | 326 | Req 4766 |  | 2509.2
GL | 212 | 11/28/18 | 795 | Req 5548 |  | 280.11
GL | 220 | 09/25/18 | 634 | Req 5356 |  | 9.58
GL | 220 | 10/31/18 | 871 | Req 5520 |  | -142.5
GL | 220 | 12/31/18 | 871 | Req 5659 |  | 733.01
AP | 220 | 01/14/19 | 360 | Rosen Supply Kirkland |  | 4689.08 | 4259554-00
GL | 220 | 01/15/19 | 424 | Req 4897 |  | 906.34
GL | 220 | 01/30/19 | 867 | Req 5007 |  | 470.67
AP | 220 | 02/01/19 | 107 | Consolidated Supply Co. |  | 3597.66 | S9093338.002
AP | 220 | 02/16/19 | 490 | Rosen Supply Kirkland |  | 1220.45 | 4262231-00
AP | 220 | 02/18/19 | 501 | Rosen Supply Kirkland |  | 209.18 | 4262231-01
GL | 220 | 03/04/19 | 192 | Req 5714 |  | 158.09
GL | 220 | 03/08/19 | 353 | Req 5035 |  | 369.33
AP | 220 | 03/12/19 | 417 | Rosen Supply Kirkland |  | 1323.51 | 4263509-00
GL | 220 | 03/15/19 | 603 | Req 5802 |  | 250.55
AP | 220 | 03/19/19 | 643 | Rosen Supply Kirkland |  | 133.28 | 4263925-00
GL | 220 | 03/28/19 | 1079 | Req 5856 |  | 546.26
AP | 220 | 04/03/19 | 76 | Rosen Supply Kirkland |  | 588.34 | 4264722-00
GL | 220 | 04/08/19 | 225 | Req 5113 |  | 394.25
AP | 220 | 04/09/19 | 251 | Rosen Supply Kirkland |  | 196.62 | 4265077-00
AP | 220 | 04/09/19 | 252 | Rosen Supply Kirkland |  | 398.26 | 4265077-01
AP | 220 | 04/10/19 | 306 | Rosen Supply Kirkland |  | 148.5 | 4265239-00
AP | 220 | 04/16/19 | 514 | Rosen Supply Kirkland |  | 66.64 | 4265437-00
AP | 220 | 04/22/19 | 648 | Rosen Supply Kirkland |  | 131.4 | 4265077-02
AP | 220 | 04/23/19 | 678 | Rosen Supply Kirkland |  | 26.28 | 4265077-03
GL | 220 | 04/24/19 | 682 | Req 5915 |  | 931.7
AP | 220 | 04/30/19 | 875 | Manor Hardware & Construction Supply |  | 305.76 | 966424-00
GL | 220 | 04/30/19 | 904 | Req 5923 |  | 389.74
AP | 220 | 04/30/19 | 933 | Consolidated Supply Co. |  | 1010.54 | S9231321.001
GL | 220 | 05/13/19 | 307 | Req 5196 |  | 3144.9
AP | 220 | 05/15/19 | 368 | Rosen Supply Kirkland |  | 401.5 | 4266475-00
AP | 220 | 05/23/19 | 602 | Consolidated Supply Co. |  | 294.77 | S9241586.001
AP | 220 | 05/28/19 | 761 | Rosen Supply Kirkland |  | 290.2 | 4267168-00
GL | 220 | 06/05/19 | 140 | Req 5256 |  | 413.39
AP | 220 | 06/12/19 | 447 | Rosen Supply Kirkland |  | 172.42 | 4268492-00
AP | 220 | 06/21/19 | 717 | Rosen Supply Kirkland |  | 154.82 | 4268689-00
GL | 220 | 07/10/19 | 177 | Req 6138 |  | 318.79
AP | 220 | 08/07/19 | 187 | Rosen Supply Kirkland |  | 309.18 | 4270044-00
GL | 220 | 08/08/19 | 238 | Req 6186 |  | 63.05
AP | 220 | 08/10/19 | 444 | Rosen Supply Kirkland |  | 1.42 | 4270044-01
AP | 220 | 08/14/19 | 547 | Rosen Supply Kirkland |  | -62.88 | 4270835-00
GL | 220 | 08/20/19 | 710 | Req 6243 |  | 16.82
GL | 220 | 09/16/19 | 370 | Req 6340 |  | 56.59
AP | 220 | 09/23/19 | 597 | Rosen Supply Kirkland |  | 4.15 | 4272122-00
GL | 220 | 10/16/19 | 439 |  |  | 6.71
GL | 220 | 11/13/19 | 397 | Req 6560 |  | 121.32
GL | 220 | 11/19/19 | 575 | Req 6580 |  | 80.29
AP | 220 | 11/20/19 | 594 | Rosen Supply Kirkland |  | 4.19 | 4274246-00
GL | 220 | 12/06/19 | 163 | Req 6604 |  | -92.94
GL | 220 | 12/06/19 | 164 | Req 6603 |  | -106.08
GL | 220 | 12/09/19 | 182 | Req 6644 |  | 59.69
AP | 220 | 01/17/20 | 634 | Ferguson Enterprises, Inc. #3007 |  | 23.29 | 4277541-00
AP | 230 | 07/23/18 | 623 | Old Castle Infrastructure, Inc. |  | 2115 | 10220931
AP | 230 | 08/08/18 | 174 | Quality Concrete Products, Inc. $32 |  | 1716 | 55676
AP | 230 | 08/15/18 | 470 | Keller Supply Company |  | 933.8 | S012072717.001
AP | 230 | 08/15/18 | 471 | Keller Supply Company |  | 40.4 | S012072717.002
GL | 230 | 08/22/18 | 659 | Req 4626 |  | 112.58
GL | 230 | 09/25/18 | 636 | Req 5354 |  | 251.64
GL | 230 | 09/30/18 | 784 | Req 5425 |  | 1877.4
GL | 230 | 11/28/18 | 796 | Req 5547 |  | 730.1
AP | 230 | 11/30/18 | 931 | Quality Concrete Products, Inc. $32 |  | 345 | 56338
GL | 230 | 11/30/18 | 987 | Req 5589 |  | 130
GL | 230 | 12/21/18 | 642 | Req 5634 |  | -456.96
AP | 230 | 01/25/19 | 828 | Rosen Supply Kirkland |  | 3480.84 | 4261185-00
GL | 230 | 03/04/19 | 193 | Req 5715 |  | 162.21
GL | 230 | 03/08/19 | 354 | Req 5057 |  | 1101.66
GL | 230 | 03/12/19 | 413 | Adjustment. Issaquah Gateway damaged stalls credited on |  | 2270.3
GL | 230 | 03/28/19 | 1081 | Req 5858 |  | 345.79
GL | 230 | 04/08/19 | 226 | Req 5114 |  | 14.38
AP | 230 | 04/15/19 | 490 | Keller Supply Company |  | 11493.49 | S012491784.001
GL | 230 | 04/16/19 | 509 | Adj |  | -2270.3
GL | 230 | 04/24/19 | 681 | Req 5914 |  | 1293.28
AP | 230 | 05/06/19 | 119 | Keller Supply Company |  | 11950.45 | S012491780.001
AP | 230 | 05/06/19 | 120 | Keller Supply Company |  | 12864.37 | S012491772.001
GL | 230 | 05/13/19 | 306 | Req 5195 |  | 1145.51
AP | 230 | 05/21/19 | 535 | Keller Supply Company |  | 13460.31 | S012491521.001
AP | 230 | 05/21/19 | 536 | Keller Supply Company |  | 378.84 | S012491806.001
AP | 230 | 05/21/19 | 537 | Keller Supply Company |  | 668.03 | S012890793.001
GL | 230 | 05/30/19 | 843 | Req 5997 |  | 2497.92
GL | 230 | 06/05/19 | 141 | Req 5257 |  | 87.2
AP | 230 | 06/11/19 | 390 | Keller Supply Company |  | 6461.83 | S012832980.001
AP | 230 | 06/13/19 | 787 | Keller Supply Company |  | -96.91 | S01283298.002
AP | 230 | 06/13/19 | 788 | Keller Supply Company |  | 456.96 | S013015269.001
AP | 230 | 06/17/19 | 573 | Consolidated Supply Co. |  | 3350.56 | S9274266.001
AP | 230 | 06/24/19 | 761 | Consolidated Supply Co. |  | 163.35 | S9274266.002
GL | 230 | 07/09/19 | 110 | Req 6059 |  | 906.27
GL | 230 | 07/10/19 | 176 | Req 6140 |  | 703.3
AP | 230 | 07/16/19 | 459 | Consolidated Supply Co. |  | 472.85 | S009321684.001
AP | 230 | 07/16/19 | 460 | Consolidated Supply Co. |  | 2783.48 | S009321684.003
AP | 230 | 08/01/19 | 142 | California Hydronics Corp |  | 3271 | SIN023155
AP | 230 | 08/01/19 | 143 | California Hydronics Corp |  | 485 | SIN023419
AP | 230 | 08/05/19 | 114 | Consolidated Supply Co. |  | 77.94 | S009321684.005
AP | 230 | 08/06/19 | 176 | Minol, Inc. |  | 348 | 1006100000
AP | 230 | 08/08/19 | 207 | Rosen Supply Kirkland |  | 518.47 | 4270210-00
GL | 230 | 08/08/19 | 241 | Req 6189 |  | 1267.33
AP | 230 | 08/16/19 | 641 | Ferguson Enterprises, Inc. #3007 |  | 421.95 | 7349340
AP | 230 | 08/16/19 | 642 | Ferguson Enterprises, Inc. #3007 |  | 421.95 | 7228048
GL | 230 | 08/20/19 | 713 | Req 6240 |  | 1440.03
AP | 230 | 08/31/19 | 1119 | Kele, Inc $ MI Controls |  | 231.39 | 957643
AP | 230 | 08/31/19 | 1139 | Keller Supply Company |  | 8885.94 | S013065900.001
AP | 230 | 09/11/19 | 172 | Ferguson Enterprises, Inc. #3007 |  | -421.95 | CM801440
GL | 230 | 09/16/19 | 367 | Req 6335 |  | 1826.81
AP | 230 | 09/18/19 | 450 | Keller Supply Company |  | 8885.94 | S013065909.001
AP | 230 | 09/18/19 | 451 | Keller Supply Company |  | 2226.57 | S013065971.001
AP | 230 | 09/18/19 | 452 | Keller Supply Company |  | 434.02 | S013352446.002
AP | 230 | 09/18/19 | 453 | Keller Supply Company |  | 10159.24 | S013065677.001
AP | 230 | 09/18/19 | 454 | Keller Supply Company |  | 9996.59 | S013065804.001
AP | 230 | 09/18/19 | 455 | Keller Supply Company |  | -3554.16 | S013439857.001
AP | 230 | 09/18/19 | 460 | Consolidated Supply Co. |  | 2216.27 | S9276314.001
AP | 230 | 09/25/19 | 621 | Rosen Supply Kirkland |  | 26.88 | 4272309-00
AP | 230 | 09/25/19 | 622 | Rosen Supply Kirkland |  | 38.64 | 4272309-01
AP | 230 | 09/30/19 | 759 | Rosen Supply Kirkland |  | 79.56 | 4272765-00
AP | 230 | 10/01/19 | 240 | Capital One Credit Card |  | 11.35 | 091619A
AP | 230 | 10/01/19 | 247 | Capital One Credit Card |  | 21.59 | 100219A
AP | 230 | 10/07/19 | 138 | Rosen Supply Kirkland |  | 133.2 | 1547986-00
AP | 230 | 10/07/19 | 139 | Rosen Supply Kirkland |  | 16.75 | 1548058-00
AP | 230 | 10/14/19 | 385 | Keller Supply Company |  | 133.32 | S013648147.001
GL | 230 | 10/15/19 | 404 | Req 6410 |  | -775.28
AP | 230 | 10/22/19 | 553 | California Hydronics Corp |  | 375 | SIN031399
AP | 230 | 10/25/19 | 761 | Keller Supply Company |  | 157.72 | S013471978.001
AP | 230 | 10/25/19 | 763 | Keller Supply Company |  | 152.94 | S013499017.001
AP | 230 | 10/25/19 | 764 | Keller Supply Company |  | -135.29 | S013510466.001
AP | 230 | 10/25/19 | 770 | Keller Supply Company |  | 1689 | S013490138.001
AP | 230 | 10/25/19 | 771 | Keller Supply Company |  | 475.81 | S013415286.001
AP | 230 | 10/25/19 | 772 | Keller Supply Company |  | -613.06 | S0134947551.001
AP | 230 | 10/25/19 | 773 | Keller Supply Company |  | 245.68 | S013065677.002
AP | 230 | 11/01/19 | 95 | Keller Supply Company |  | 518.65 | S013471978.002
AP | 230 | 11/01/19 | 118 | Rosen Supply Kirkland |  | 113.66 | 4272765-01
GL | 230 | 11/04/19 | 136 | Req 6469 |  | 3208.65
GL | 230 | 11/04/19 | 137 | Req 6468 |  | 1239.05
GL | 230 | 11/13/19 | 399 | Req 6558 |  | 20.7
AP | 230 | 11/16/19 | 546 | Rosen Supply Kirkland |  | 1.15 | 4274053-00
AP | 230 | 11/21/19 | 776 | Capital One Credit Card |  | 11.59 | 110119A
AP | 230 | 11/21/19 | 777 | Capital One Credit Card |  | 35.18 | 110119A1
AP | 230 | 11/23/19 | 736 | Ferguson Enterprises, Inc. #3007 |  | 313.64 | 7628617
AP | 230 | 11/27/19 | 933 | Keller Supply Company |  | -615.81 | S013593202.001
AP | 230 | 12/01/19 | 511 | Keller Supply Company |  | 615.81 | S013593202.001A
AP | 230 | 12/01/19 | 512 | Keller Supply Company |  | -315.81 | S013593202.001B
GL | 230 | 12/09/19 | 183 | Req 6645 |  | 69.45
AP | 230 | 12/12/19 | 517 | Ferguson Enterprises, Inc. #3007 |  | 424.65 | 7676502
AP | 230 | 12/20/19 | 659 | Ferguson Enterprises, Inc. #3007 |  | 335.27 | 7628617-1
AP | 230 | 12/20/19 | 660 | Rosen Supply Kirkland |  | 91.88 | 4275844-00
GL | 230 | 12/27/19 | 808 | Req 6727 |  | 57.82
AP | 230 | 12/27/19 | 826 | Keller Supply Company |  | 206.69 | S013673822.001
AP | 230 | 01/09/20 | 271 | Minol, Inc. |  | 164 | 110196444
AP | 230 | 01/09/20 | 272 | Minol, Inc. |  | 233.5 | 11016445
GL | 240 | 03/04/19 | 194 | Req 5716 |  | 0.45
AP | 240 | 05/15/19 | 369 | Rosen Supply Kirkland |  | 243.26 | 4266505-00
AP | 240 | 05/21/19 | 534 | Keller Supply Company |  | 88.62 | S012969726.001
AP | 240 | 05/29/19 | 779 | Rosen Supply Kirkland |  | 10.86 | 4266505-01
GL | 240 | 07/10/19 | 175 | Req 6136 |  | 104.67
AP | 240 | 07/15/19 | 392 | Rosen Supply Kirkland |  | 376.47 | 4269120-00
AP | 240 | 07/16/19 | 444 | Rosen Supply Kirkland |  | 80.66 | 4269120-01
AP | 240 | 07/17/19 | 492 | Rosen Supply Kirkland |  | 34.54 | 4269616-00
GL | 240 | 08/08/19 | 242 | Req 6190 |  | 19.37
AP | 240 | 08/10/19 | 437 | Rosen Supply Kirkland |  | 31.24 | 4270312-00
AP | 240 | 08/10/19 | 453 | Rosen Supply Kirkland |  | 20.74 | 4270422-00
AP | 240 | 08/14/19 | 530 | Rosen Supply Kirkland |  | 123.69 | 4270757-00
GL | 240 | 08/20/19 | 711 | Req 6242 |  | 58.43
GL | 240 | 10/07/19 | 98 | Req 6392 |  | -5
GL | 240 | 10/15/19 | 402 | Req 6412 |  | -85.4
AP | 240 | 10/21/19 | 543 | Ferguson Enterprises, Inc. #3007 |  | 36.19 | 7558381
GL | 241 | 11/30/18 | 985 | Req 5587 |  | 445.86
AP | 241 | 04/24/19 | 729 | Consolidated Supply Co. |  | 1668.8 | S9207699.001
AP | 241 | 04/24/19 | 730 | Consolidated Supply Co. |  | 168.43 | S9207699.002
GL | 241 | 04/30/19 | 913 | Req 5179 |  | 143.8
AP | 241 | 04/30/19 | 932 | Consolidated Supply Co. |  | 5703.87 | S9213871.001
GL | 241 | 05/13/19 | 308 | Req 5197 |  | 388.78
AP | 241 | 05/29/19 | 780 | Rosen Supply Kirkland |  | 1609.5 | 4266652-00
GL | 241 | 05/30/19 | 841 | Req 5996 |  | 3838.96
AP | 241 | 06/01/19 | 413 | Rosen Supply Kirkland |  | -1609.5 | 4266652-00A
AP | 241 | 06/01/19 | 414 | Rosen Supply Kirkland |  | 1609.2 | 4266652-00B
AP | 241 | 06/03/19 | 20 | Consolidated Supply Co. |  | 2931.34 | S9258082.001
AP | 241 | 06/03/19 | 21 | Consolidated Supply Co. |  | 62.73 | S9266035.001
AP | 241 | 06/03/19 | 22 | Consolidated Supply Co. |  | 494.46 | S9258082.002
AP | 241 | 06/03/19 | 23 | Consolidated Supply Co. |  | 2607.84 | S9270299.001
AP | 241 | 06/03/19 | 24 | Consolidated Supply Co. |  | 806.88 | S9270299.002
GL | 241 | 06/05/19 | 139 | Req 5255 |  | 1298
AP | 241 | 06/08/19 | 295 | Rosen Supply Kirkland |  | 48.43 | 4267527-00
AP | 241 | 06/08/19 | 316 | Rosen Supply Kirkland |  | 69.69 | 4267527-01
AP | 241 | 06/11/19 | 397 | Consolidated Supply Co. |  | 553.5 | S9258082.003
AP | 241 | 06/11/19 | 406 | Consolidated Supply Co. |  | 250.92 | S9266035.002
AP | 241 | 06/11/19 | 407 | Consolidated Supply Co. |  | 441.36 | S9270299.003
AP | 241 | 06/11/19 | 408 | Consolidated Supply Co. |  | 103.32 | S9270299.004
AP | 241 | 06/24/19 | 760 | Consolidated Supply Co. |  | 1012 | S09301019.001
AP | 241 | 06/24/19 | 762 | Consolidated Supply Co. |  | 940.95 | S009308801.001
GL | 241 | 06/26/19 | 826 | Req 6058 |  | 71.24
GL | 241 | 07/10/19 | 179 | Req 6139 |  | 1321.61
AP | 241 | 07/10/19 | 373 | Consolidated Supply Co. |  | 1012 | S009308817.001
AP | 241 | 08/06/19 | 150 | Consolidated Supply Co. |  | 376.38 | S9266035.003
GL | 241 | 08/08/19 | 240 | Req 6188 |  | 1250.5
AP | 241 | 08/15/19 | 767 | Consolidated Supply Co. |  | 63.35 | S009380254.001
AP | 241 | 08/16/19 | 643 | Ferguson Enterprises, Inc. #3007 |  | 348.54 | 7389326
AP | 241 | 08/26/19 | 936 | Consolidated Supply Co. |  | 17.82 | S009380254.002
AP | 241 | 08/28/19 | 956 | Rosen Supply Kirkland |  | 563.64 | 4270716-00
GL | 241 | 09/16/19 | 369 | Req 6339 |  | 19.44
GL | 241 | 10/15/19 | 403 | Req 6411 |  | -549.24
AP | 241 | 10/29/19 | 732 | Consolidated Supply Co. |  | 125.55 | S009471540.001
AP | 241 | 10/29/19 | 733 | Consolidated Supply Co. |  | 439.04 | S009471540.002
GL | 241 | 11/19/19 | 579 | Req 6584 |  | -165.64
AP | 241 | 11/23/19 | 735 | Ferguson Enterprises, Inc. #3007 |  | 238.4 | 7602402
GL | 242 | 11/30/18 | 986 | Req 5588 |  | 9.4
GL | 242 | 07/10/19 | 178 | Req 6135 |  | 479.71
AP | 242 | 07/16/19 | 458 | Consolidated Supply Co. |  | 569.41 | S009323252.001
AP | 242 | 07/16/19 | 461 | Consolidated Supply Co. |  | 295.74 | S009323252.002
GL | 242 | 08/08/19 | 243 | Req 6191 |  | 24.82
AP | 242 | 08/13/19 | 518 | Consolidated Supply Co. |  | 1927.98 | S009368354.001
AP | 242 | 08/13/19 | 519 | Consolidated Supply Co. |  | 191.32 | S009368354.002
AP | 242 | 08/28/19 | 951 | Consolidated Supply Co. |  | 108.81 | S009383643.001
AP | 242 | 09/10/19 | 173 | Ferguson Enterprises, Inc. #3007 |  | 671.56 | 7420643-1
AP | 242 | 09/10/19 | 174 | Ferguson Enterprises, Inc. #3007 |  | 871.28 | 7445408
AP | 242 | 09/10/19 | 175 | Ferguson Enterprises, Inc. #3007 |  | 155.36 | 7449094-1
AP | 242 | 09/10/19 | 176 | Ferguson Enterprises, Inc. #3007 |  | 2659.65 | 7420643
AP | 242 | 09/11/19 | 170 | Ferguson Enterprises, Inc. #3007 |  | 51.79 | 7449094-2
AP | 242 | 09/11/19 | 171 | Ferguson Enterprises, Inc. #3007 |  | 75.01 | 7449094
AP | 242 | 09/16/19 | 388 | Ferguson Enterprises, Inc. #3007 |  | 396.1 | 7470532
AP | 242 | 09/16/19 | 389 | Ferguson Enterprises, Inc. #3007 |  | 180.37 | 7470532-1
GL | 242 | 10/07/19 | 99 | Req 6391 |  | -81.49
GL | 242 | 10/07/19 | 126 | Req 6388 |  | 588.45
GL | 242 | 10/15/19 | 405 | Req 6409 |  | -515.97
GL | 242 | 10/15/19 | 406 | Req 6408 |  | -1269.53
GL | 242 | 10/28/19 | 695 | Req 6431 |  | -65.11
GL | 243 | 05/30/19 | 840 | Req 6000 |  | 6.71
GL | 243 | 10/16/19 | 439 |  |  | -6.71
AP | 600 | 07/16/19 | 432 | R.A. Brown Backflow Testing |  | 140 | 19071502
AP | 600 | 10/07/19 | 149 | R.A. Brown Backflow Testing |  | 120 | 19100402
AP | 600 | 01/06/20 | 120 | Patchworks, Inc. |  | 4393.75 | 8961
AP | 602 | 06/11/19 | 399 | AllWest Underground, Inc. |  | 199.24 | 84630
PR | 995 | 06/29/18 | 1019 | Donelson, Richard T |  | 166.31
PR | 995 | 07/06/18 | 76 | Donelson, Richard T |  | 110.88
PR | 995 | 07/06/18 | 76 | Donelson, Richard T |  | 55.44
PR | 995 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/13/18 | 350 | Reed, Reuben H |  | 72.73
PR | 995 | 07/13/18 | 367 | Donelson, Richard T |  | 55.44
PR | 995 | 07/20/18 | 470 | Hubbard, Robert W |  | 41.69
PR | 995 | 07/20/18 | 507 | Donelson, Richard T |  | 55.44
PR | 995 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 07/27/18 | 817 | Reed, Reuben H |  | 36.37
PR | 995 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/03/18 | 35 | Hubbard, Robert W |  | 291.82
PR | 995 | 08/03/18 | 46 | McCabe, Thomas C |  | 212.88
PR | 995 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo |  | 219.98
PR | 995 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/10/18 | 246 | Hubbard, Robert W |  | 83.38
PR | 995 | 08/10/18 | 257 | McCabe, Thomas C |  | 85.15
PR | 995 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo |  | 82.49
PR | 995 | 08/10/18 | 284 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/10/18 | 284 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/17/18 | 514 | Hubbard, Robert W |  | 41.69
PR | 995 | 08/17/18 | 524 | McCabe, Thomas C |  | 70.96
PR | 995 | 08/17/18 | 541 | Sepulveda Gonzalez, Alfredo |  | 68.74
PR | 995 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 08/24/18 | 776 | Hubbard, Robert W |  | 20.84
PR | 995 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 08/31/18 | 1031 | Hubbard, Robert W |  | 166.76
PR | 995 | 08/31/18 | 1048 | Reed, Reuben H |  | 145.47
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 133.05
PR | 995 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 66.53
PR | 995 | 09/07/18 | 50 | Cruz Guzman, Joel A |  | 163.21
PR | 995 | 09/07/18 | 51 | Cruz Reyes, Jose |  | 170.3
PR | 995 | 09/07/18 | 70 | Hubbard, Robert W |  | 198.02
PR | 995 | 09/07/18 | 79 | McCabe, Thomas C |  | 113.54
PR | 995 | 09/07/18 | 88 | Reed, Reuben H |  | 290.94
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/14/18 | 302 | Hubbard, Robert W |  | 41.69
PR | 995 | 09/14/18 | 320 | Reed, Reuben H |  | 145.47
PR | 995 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 09/21/18 | 494 | Cruz Guzman, Joel A |  | 81.6
PR | 995 | 09/21/18 | 533 | Reed, Reuben H |  | 18.18
PR | 995 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 09/28/18 | 718 | Reed, Reuben H |  | 36.37
PR | 995 | 09/28/18 | 718 | Reed, Reuben H |  | 18.18
PR | 995 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/05/18 | 102 | Donelson, Richard T |  | 110.88
PR | 995 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 10/12/18 | 288 | Reed, Reuben H |  | 54.55
PR | 995 | 10/19/18 | 468 | Hubbard, Robert W |  | 31.27
PR | 995 | 10/19/18 | 507 | Donelson, Richard T |  | 55.44
PR | 995 | 10/25/18 | 687 | Hubbard, Robert W |  | 312.67
PR | 995 | 10/26/18 | 743 | McCabe, Thomas C |  | 340.61
PR | 995 | 10/26/18 | 751 | Reed, Reuben H |  | 436.4
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/02/18 | 39 | Hubbard, Robert W |  | 104.22
PR | 995 | 11/02/18 | 48 | McCabe, Thomas C |  | 99.34
PR | 995 | 11/02/18 | 55 | Reed, Reuben H |  | 363.67
PR | 995 | 11/02/18 | 76 | Donelson, Richard T |  | 55.44
PR | 995 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/09/18 | 234 | Reed, Reuben H |  | 145.47
PR | 995 | 11/09/18 | 257 | Donelson, Richard T |  | 27.72
PR | 995 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/16/18 | 465 | Hubbard, Robert W |  | 20.84
PR | 995 | 11/16/18 | 467 | Kinssies, Jr, John E |  | 92.25
PR | 995 | 11/16/18 | 474 | McCabe, Thomas C |  | 70.96
PR | 995 | 11/16/18 | 482 | Reed, Reuben H |  | 472.77
PR | 995 | 11/16/18 | 504 | Hubbard, Robert W |  | -20.84
PR | 995 | 11/16/18 | 508 | Hubbard, Robert W |  | 20.84
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 83.16
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 27.72
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 44.35
PR | 995 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/21/18 | 650 | Hubbard, Robert W |  | 20.84
PR | 995 | 11/21/18 | 658 | McCabe, Thomas C |  | 92.25
PR | 995 | 11/21/18 | 666 | Reed, Reuben H |  | 72.73
PR | 995 | 11/21/18 | 689 | Donelson, Richard T |  | 138.59
PR | 995 | 11/30/18 | 879 | Reed, Reuben H |  | 152.56
PR | 995 | 11/30/18 | 900 | Donelson, Richard T |  | 27.72
PR | 995 | 12/07/18 | 91 | Reed, Reuben H |  | 343.27
PR | 995 | 12/07/18 | 91 | Reed, Reuben H |  | 38.14
PR | 995 | 12/07/18 | 113 | Donelson, Richard T |  | 83.16
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 316 | Reed, Reuben H |  | 610.26
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/21/18 | 514 | Castro Hernandez, Jose A |  | 351.25
PR | 995 | 12/21/18 | 542 | Kinssies, Jr, John E |  | 215.54
PR | 995 | 12/21/18 | 546 | Lucas Tzintzun, Rafael |  | 351.25
PR | 995 | 12/21/18 | 556 | Reed, Reuben H |  | 724.68
PR | 995 | 12/21/18 | 567 | Silva Morales, Jair J |  | 510.03
PR | 995 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 92.25
PR | 995 | 12/28/18 | 705 | Castro Hernandez, Jose A |  | 380.52
PR | 995 | 12/28/18 | 733 | Kinssies, Jr, John E |  | 191.59
PR | 995 | 12/28/18 | 737 | Lucas Tzintzun, Rafael |  | 223.52
PR | 995 | 12/28/18 | 747 | Reed, Reuben H |  | 381.41
PR | 995 | 12/28/18 | 747 | Reed, Reuben H |  | 152.56
PR | 995 | 12/28/18 | 758 | Silva Morales, Jair J |  | 288.28
PR | 995 | 12/28/18 | 769 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 01/04/19 | 10 | Castro Hernandez, Jose A |  | 380.52
PR | 995 | 01/04/19 | 40 | Lucas Tzintzun, Rafael |  | 191.59
PR | 995 | 01/04/19 | 50 | Reed, Reuben H |  | 457.69
PR | 995 | 01/04/19 | 61 | Silva Morales, Jair J |  | 177.4
PR | 995 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/11/19 | 218 | Castro Hernandez, Jose A |  | 234.17
PR | 995 | 01/11/19 | 244 | Hubbard, Robert W |  | 130.39
PR | 995 | 01/11/19 | 244 | Hubbard, Robert W |  | 43.46
PR | 995 | 01/11/19 | 246 | Kinssies, Jr, John E |  | 263.44
PR | 995 | 01/11/19 | 250 | Lucas Tzintzun, Rafael |  | 227.52
PR | 995 | 01/11/19 | 260 | Reed, Reuben H |  | 276.52
PR | 995 | 01/11/19 | 260 | Reed, Reuben H |  | 133.49
PR | 995 | 01/11/19 | 260 | Reed, Reuben H |  | 38.14
PR | 995 | 01/11/19 | 271 | Silva Morales, Jair J |  | 443.5
PR | 995 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/18/19 | 473 | Castro Hernandez, Jose A |  | 351.25
PR | 995 | 01/18/19 | 501 | Kinssies, Jr, John E |  | 461.02
PR | 995 | 01/18/19 | 505 | Lucas Tzintzun, Rafael |  | 315.33
PR | 995 | 01/18/19 | 515 | Reed, Reuben H |  | 572.12
PR | 995 | 01/18/19 | 526 | Silva Morales, Jair J |  | 432.41
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 01/25/19 | 722 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 01/25/19 | 750 | Kinssies, Jr, John E |  | 478.98
PR | 995 | 01/25/19 | 754 | Lucas Tzintzun, Rafael |  | 319.32
PR | 995 | 01/25/19 | 764 | Reed, Reuben H |  | 228.85
PR | 995 | 01/25/19 | 764 | Reed, Reuben H |  | 476.76
PR | 995 | 01/25/19 | 775 | Silva Morales, Jair J |  | 354.8
PR | 995 | 01/25/19 | 786 | Donelson, Richard T |  | 27.72
PR | 995 | 02/01/19 | 10 | Castro Hernandez, Jose A |  | 541.51
PR | 995 | 02/01/19 | 38 | Kinssies, Jr, John E |  | 383.18
PR | 995 | 02/01/19 | 42 | Lucas Tzintzun, Rafael |  | 319.32
PR | 995 | 02/01/19 | 50 | Reed, Reuben H |  | 762.82
PR | 995 | 02/01/19 | 60 | Silva Morales, Jair J |  | 354.8
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 165 | Castro Hernandez, Jose A |  | 351.25
PR | 995 | 02/08/19 | 193 | Kinssies, Jr, John E |  | 287.39
PR | 995 | 02/08/19 | 197 | Lucas Tzintzun, Rafael |  | 191.59
PR | 995 | 02/08/19 | 205 | Reed, Reuben H |  | 457.69
PR | 995 | 02/08/19 | 216 | Silva Morales, Jair J |  | 88.7
PR | 995 | 02/08/19 | 216 | Silva Morales, Jair J |  | 177.4
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/15/19 | 327 | Castro Hernandez, Jose A |  | 307.35
PR | 995 | 02/15/19 | 355 | Kinssies, Jr, John E |  | 173.63
PR | 995 | 02/15/19 | 359 | Lucas Tzintzun, Rafael |  | 151.68
PR | 995 | 02/15/19 | 367 | Reed, Reuben H |  | 400.48
PR | 995 | 02/15/19 | 378 | Silva Morales, Jair J |  | 144.14
PR | 995 | 02/22/19 | 585 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 02/22/19 | 613 | Kinssies, Jr, John E |  | 173.63
PR | 995 | 02/22/19 | 617 | Lucas Tzintzun, Rafael |  | 383.18
PR | 995 | 02/22/19 | 626 | Reed, Reuben H |  | 915.38
PR | 995 | 02/22/19 | 637 | Silva Morales, Jair J |  | 443.5
PR | 995 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/01/19 | 10 | Castro Hernandez, Jose A |  | 702.5
PR | 995 | 03/01/19 | 28 | Gauthier, Dillon R |  | 113.54
PR | 995 | 03/01/19 | 44 | Lucas Tzintzun, Rafael |  | 319.32
PR | 995 | 03/01/19 | 53 | Reed, Reuben H |  | 915.38
PR | 995 | 03/01/19 | 64 | Silva Morales, Jair J |  | 443.5
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/08/19 | 252 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 03/08/19 | 284 | Lucas Tzintzun, Rafael |  | 319.32
PR | 995 | 03/08/19 | 293 | Reed, Reuben H |  | 686.54
PR | 995 | 03/08/19 | 303 | Silva Morales, Jair J |  | 443.5
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 499 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 03/15/19 | 516 | Gauthier, Dillon R |  | 283.84
PR | 995 | 03/15/19 | 531 | Lucas Tzintzun, Rafael |  | 127.73
PR | 995 | 03/15/19 | 540 | Reed, Reuben H |  | 610.26
PR | 995 | 03/15/19 | 551 | Silva Morales, Jair J |  | 354.8
PR | 995 | 03/15/19 | 562 | Donelson, Richard T |  | 27.72
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/22/19 | 713 | Castro Hernandez, Jose A |  | 468.34
PR | 995 | 03/22/19 | 730 | Gauthier, Dillon R |  | 283.84
PR | 995 | 03/22/19 | 745 | Lucas Tzintzun, Rafael |  | 319.32
PR | 995 | 03/22/19 | 753 | Reed, Reuben H |  | 762.82
PR | 995 | 03/22/19 | 764 | Silva Morales, Jair J |  | 354.8
PR | 995 | 03/22/19 | 776 | Donelson, Richard T |  | 27.72
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/29/19 | 924 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 03/29/19 | 942 | Gauthier, Dillon R |  | 283.84
PR | 995 | 03/29/19 | 965 | Reed, Reuben H |  | 762.82
PR | 995 | 03/29/19 | 976 | Silva Morales, Jair J |  | 443.5
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 57.66
PR | 995 | 04/05/19 | 86 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 04/05/19 | 104 | Gauthier, Dillon R |  | 283.84
PR | 995 | 04/05/19 | 128 | Reed, Reuben H |  | 762.82
PR | 995 | 04/05/19 | 139 | Silva Morales, Jair J |  | 443.5
PR | 995 | 04/12/19 | 330 | Castro Hernandez, Jose A |  | 87.81
PR | 995 | 04/12/19 | 330 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 04/12/19 | 347 | Gauthier, Dillon R |  | 42.58
PR | 995 | 04/12/19 | 347 | Gauthier, Dillon R |  | 283.84
PR | 995 | 04/12/19 | 372 | Reed, Reuben H |  | 299.36
PR | 995 | 04/12/19 | 372 | Reed, Reuben H |  | 658.6
PR | 995 | 04/12/19 | 383 | Silva Morales, Jair J |  | 66.53
PR | 995 | 04/12/19 | 383 | Silva Morales, Jair J |  | 443.5
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 92.25
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 04/19/19 | 527 | Castro Hernandez, Jose A |  | 175.63
PR | 995 | 04/19/19 | 527 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 04/19/19 | 534 | Cruz Guzman, Joel A |  | 99.79
PR | 995 | 04/19/19 | 534 | Cruz Guzman, Joel A |  | 266.1
PR | 995 | 04/19/19 | 545 | Gauthier, Dillon R |  | 85.15
PR | 995 | 04/19/19 | 545 | Gauthier, Dillon R |  | 283.84
PR | 995 | 04/19/19 | 553 | Hubbard, Dustin R |  | 81.6
PR | 995 | 04/19/19 | 570 | Reed, Reuben H |  | 758.39
PR | 995 | 04/19/19 | 576 | Romero Garza, Jesus I |  | 79.83
PR | 995 | 04/19/19 | 581 | Silva Morales, Jair J |  | 133.05
PR | 995 | 04/19/19 | 581 | Silva Morales, Jair J |  | 443.5
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 34.59
PR | 995 | 04/26/19 | 747 | Castro Hernandez, Jose A |  | 131.72
PR | 995 | 04/26/19 | 747 | Castro Hernandez, Jose A |  | 585.42
PR | 995 | 04/26/19 | 754 | Cruz Guzman, Joel A |  | 111.76
PR | 995 | 04/26/19 | 754 | Cruz Guzman, Joel A |  | 298.03
PR | 995 | 04/26/19 | 764 | Gauthier, Dillon R |  | 90.47
PR | 995 | 04/26/19 | 764 | Gauthier, Dillon R |  | 301.58
PR | 995 | 04/26/19 | 774 | Hubbard, Robert W |  | 155.23
PR | 995 | 04/26/19 | 789 | Reed, Reuben H |  | 738.43
PR | 995 | 04/26/19 | 795 | Romero Garza, Jesus I |  | 95.8
PR | 995 | 04/26/19 | 795 | Romero Garza, Jesus I |  | 319.32
PR | 995 | 04/26/19 | 800 | Silva Morales, Jair J |  | 107.77
PR | 995 | 04/26/19 | 800 | Silva Morales, Jair J |  | 478.98
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/03/19 | 14 | Castro Hernandez, Jose A |  | 468.34
PR | 995 | 05/03/19 | 21 | Cruz Guzman, Joel A |  | 248.36
PR | 995 | 05/03/19 | 32 | Gauthier, Dillon R |  | 45.24
PR | 995 | 05/03/19 | 32 | Gauthier, Dillon R |  | 301.58
PR | 995 | 05/03/19 | 58 | Reed, Reuben H |  | 179.62
PR | 995 | 05/03/19 | 58 | Reed, Reuben H |  | 798.3
PR | 995 | 05/03/19 | 64 | Romero Garza, Jesus I |  | 71.85
PR | 995 | 05/03/19 | 64 | Romero Garza, Jesus I |  | 319.32
PR | 995 | 05/03/19 | 69 | Silva Morales, Jair J |  | 107.77
PR | 995 | 05/03/19 | 69 | Silva Morales, Jair J |  | 478.98
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/10/19 | 167 | Castro Hernandez, Jose A |  | 558.81
PR | 995 | 05/10/19 | 174 | Cruz Guzman, Joel A |  | 111.76
PR | 995 | 05/10/19 | 174 | Cruz Guzman, Joel A |  | 298.03
PR | 995 | 05/10/19 | 185 | Gauthier, Dillon R |  | 45.24
PR | 995 | 05/10/19 | 185 | Gauthier, Dillon R |  | 301.58
PR | 995 | 05/10/19 | 195 | Hubbard, Robert W |  | 44.35
PR | 995 | 05/10/19 | 195 | Hubbard, Robert W |  | 22.18
PR | 995 | 05/10/19 | 211 | Reed, Reuben H |  | 758.39
PR | 995 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 23.95
PR | 995 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 191.59
PR | 995 | 05/10/19 | 222 | Silva Morales, Jair J |  | 107.77
PR | 995 | 05/10/19 | 222 | Silva Morales, Jair J |  | 478.98
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/17/19 | 399 | Castro Hernandez, Jose A |  | 620.9
PR | 995 | 05/17/19 | 406 | Cruz Guzman, Joel A |  | 496.72
PR | 995 | 05/17/19 | 417 | Gauthier, Dillon R |  | 271.42
PR | 995 | 05/17/19 | 427 | Hubbard, Robert W |  | 22.18
PR | 995 | 05/17/19 | 443 | Reed, Reuben H |  | 598.73
PR | 995 | 05/17/19 | 443 | Reed, Reuben H |  | 199.58
PR | 995 | 05/17/19 | 453 | Silva Morales, Jair J |  | 478.98
PR | 995 | 05/17/19 | 467 | Donelson, Richard T |  | 27.72
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/24/19 | 611 | Castro Hernandez, Jose A |  | 620.9
PR | 995 | 05/24/19 | 618 | Cruz Guzman, Joel A |  | 496.72
PR | 995 | 05/24/19 | 629 | Gauthier, Dillon R |  | 271.42
PR | 995 | 05/24/19 | 629 | Gauthier, Dillon R |  | 30.16
PR | 995 | 05/24/19 | 639 | Hubbard, Robert W |  | 133.05
PR | 995 | 05/24/19 | 639 | Hubbard, Robert W |  | 22.18
PR | 995 | 05/24/19 | 639 | Hubbard, Robert W |  | 22.18
PR | 995 | 05/24/19 | 649 | McCabe, Thomas C |  | 279.41
PR | 995 | 05/24/19 | 655 | Reed, Reuben H |  | 718.47
PR | 995 | 05/24/19 | 655 | Reed, Reuben H |  | 79.83
PR | 995 | 05/24/19 | 664 | Sepulveda Gonzalez, Alfredo |  | 372.54
PR | 995 | 05/24/19 | 665 | Silva Morales, Jair J |  | 383.18
PR | 995 | 05/24/19 | 680 | Donelson, Richard T |  | 83.16
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 36.59
PR | 995 | 05/31/19 | 885 | Castro Hernandez, Jose A |  | 450.15
PR | 995 | 05/31/19 | 892 | Cruz Guzman, Joel A |  | 99.34
PR | 995 | 05/31/19 | 903 | Gauthier, Dillon R |  | 241.26
PR | 995 | 05/31/19 | 913 | Hubbard, Robert W |  | 44.35
PR | 995 | 05/31/19 | 923 | McCabe, Thomas C |  | 294.93
PR | 995 | 05/31/19 | 929 | Reed, Reuben H |  | 79.83
PR | 995 | 05/31/19 | 929 | Reed, Reuben H |  | 558.81
PR | 995 | 05/31/19 | 937 | Sanders, Allen O |  | 65.19
PR | 995 | 05/31/19 | 938 | Sepulveda Gonzalez, Alfredo |  | 372.54
PR | 995 | 05/31/19 | 939 | Silva Morales, Jair J |  | 383.18
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 06/07/19 | 187 | Castro Hernandez, Jose A |  | 620.9
PR | 995 | 06/07/19 | 194 | Cruz Guzman, Joel A |  | 496.72
PR | 995 | 06/07/19 | 205 | Gauthier, Dillon R |  | 60.32
PR | 995 | 06/07/19 | 205 | Gauthier, Dillon R |  | 180.95
PR | 995 | 06/07/19 | 215 | Hubbard, Robert W |  | 88.7
PR | 995 | 06/07/19 | 215 | Hubbard, Robert W |  | 99.79
PR | 995 | 06/07/19 | 215 | Hubbard, Robert W |  | 88.7
PR | 995 | 06/07/19 | 224 | McCabe, Thomas C |  | 372.54
PR | 995 | 06/07/19 | 224 | McCabe, Thomas C |  | 62.09
PR | 995 | 06/07/19 | 224 | McCabe, Thomas C |  | 62.09
PR | 995 | 06/07/19 | 230 | Reed, Reuben H |  | 758.39
PR | 995 | 06/07/19 | 230 | Reed, Reuben H |  | 39.92
PR | 995 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 372.54
PR | 995 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 124.18
PR | 995 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 124.18
PR | 995 | 06/07/19 | 241 | Silva Morales, Jair J |  | 95.8
PR | 995 | 06/07/19 | 241 | Silva Morales, Jair J |  | 191.59
PR | 995 | 06/07/19 | 254 | Donelson, Richard T |  | 27.72
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 06/14/19 | 458 | Castro Hernandez, Jose A |  | 372.54
PR | 995 | 06/14/19 | 458 | Castro Hernandez, Jose A |  | 201.79
PR | 995 | 06/14/19 | 464 | Cruz Guzman, Joel A |  | 198.69
PR | 995 | 06/14/19 | 464 | Cruz Guzman, Joel A |  | 198.69
PR | 995 | 06/14/19 | 473 | Gauthier, Dillon R |  | 60.32
PR | 995 | 06/14/19 | 473 | Gauthier, Dillon R |  | 241.26
PR | 995 | 06/14/19 | 499 | Reed, Reuben H |  | 239.49
PR | 995 | 06/14/19 | 499 | Reed, Reuben H |  | 419.11
PR | 995 | 06/14/19 | 499 | Reed, Reuben H |  | 139.7
PR | 995 | 06/14/19 | 509 | Silva Morales, Jair J |  | 478.98
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 55.44
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 06/21/19 | 627 | Castro Hernandez, Jose A |  | 372.54
PR | 995 | 06/21/19 | 627 | Castro Hernandez, Jose A |  | 124.18
PR | 995 | 06/21/19 | 634 | Cruz Guzman, Joel A |  | 397.38
PR | 995 | 06/21/19 | 644 | Gauthier, Dillon R |  | 278.96
PR | 995 | 06/21/19 | 670 | Reed, Reuben H |  | 578.77
PR | 995 | 06/21/19 | 680 | Silva Morales, Jair J |  | 359.24
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 06/28/19 | 845 | Castro Hernandez, Jose A |  | 372.54
PR | 995 | 06/28/19 | 845 | Castro Hernandez, Jose A |  | 248.36
PR | 995 | 06/28/19 | 862 | Gauthier, Dillon R |  | 180.95
PR | 995 | 06/28/19 | 862 | Gauthier, Dillon R |  | 120.63
PR | 995 | 06/28/19 | 887 | Reed, Reuben H |  | 478.98
PR | 995 | 06/28/19 | 887 | Reed, Reuben H |  | 79.83
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 07/05/19 | 17 | Castro Hernandez, Jose A |  | 496.72
PR | 995 | 07/05/19 | 34 | Gauthier, Dillon R |  | 120.63
PR | 995 | 07/05/19 | 34 | Gauthier, Dillon R |  | 120.63
PR | 995 | 07/05/19 | 59 | Reed, Reuben H |  | 638.64
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 27.72
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 124.18
PR | 995 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 124.18
PR | 995 | 07/12/19 | 303 | Gauthier, Dillon R |  | 60.32
PR | 995 | 07/12/19 | 303 | Gauthier, Dillon R |  | 60.32
PR | 995 | 07/12/19 | 328 | Reed, Reuben H |  | 319.32
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 07/19/19 | 517 | Castro Hernandez, Jose A |  | 496.72
PR | 995 | 07/19/19 | 517 | Castro Hernandez, Jose A |  | 124.18
PR | 995 | 07/19/19 | 533 | Gauthier, Dillon R |  | 241.26
PR | 995 | 07/19/19 | 533 | Gauthier, Dillon R |  | 7.54
PR | 995 | 07/19/19 | 543 | Hubbard, Robert W |  | 44.35
PR | 995 | 07/19/19 | 543 | Hubbard, Robert W |  | 22.18
PR | 995 | 07/19/19 | 558 | Reed, Reuben H |  | 239.49
PR | 995 | 07/19/19 | 558 | Reed, Reuben H |  | 319.32
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 07/26/19 | 621 | Castro Hernandez, Jose A |  | 496.72
PR | 995 | 07/26/19 | 621 | Castro Hernandez, Jose A |  | 124.18
PR | 995 | 07/26/19 | 636 | Gauthier, Dillon R |  | 180.95
PR | 995 | 07/26/19 | 636 | Gauthier, Dillon R |  | 120.63
PR | 995 | 07/26/19 | 646 | Hubbard, Robert W |  | 88.7
PR | 995 | 07/26/19 | 661 | Reed, Reuben H |  | 319.32
PR | 995 | 07/26/19 | 661 | Reed, Reuben H |  | 159.66
PR | 995 | 07/26/19 | 661 | Reed, Reuben H |  | 119.75
PR | 995 | 07/26/19 | 685 | Donelson, Richard T |  | 27.72
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 08/02/19 | 13 | Castro Hernandez, Jose A |  | 372.54
PR | 995 | 08/02/19 | 28 | Gauthier, Dillon R |  | 180.95
PR | 995 | 08/02/19 | 38 | Hubbard, Robert W |  | 110.88
PR | 995 | 08/02/19 | 53 | Reed, Reuben H |  | 419.11
PR | 995 | 08/02/19 | 53 | Reed, Reuben H |  | 99.79
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 186.27
PR | 995 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 62.09
PR | 995 | 08/09/19 | 281 | Gauthier, Dillon R |  | 90.47
PR | 995 | 08/09/19 | 281 | Gauthier, Dillon R |  | 30.16
PR | 995 | 08/09/19 | 291 | Hubbard, Robert W |  | 44.35
PR | 995 | 08/09/19 | 306 | Reed, Reuben H |  | 219.53
PR | 995 | 08/09/19 | 306 | Reed, Reuben H |  | 159.66
PR | 995 | 08/09/19 | 306 | Reed, Reuben H |  | 159.66
PR | 995 | 08/09/19 | 328 | Donelson, Richard T |  | 27.72
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 08/16/19 | 583 | Eliassen, Cory H |  | 35.92
PR | 995 | 08/16/19 | 588 | Gauthier, Dillon R |  | 15.08
PR | 995 | 08/16/19 | 598 | Hubbard, Robert W |  | 66.53
PR | 995 | 08/16/19 | 600 | Kinssies, Jr, John E |  | 549.94
PR | 995 | 08/16/19 | 613 | Reed, Reuben H |  | 159.66
PR | 995 | 08/16/19 | 621 | Sanders, Allen O |  | 65.19
PR | 995 | 08/16/19 | 628 | Trower-Kelly, Fidel D |  | 23.95
PR | 995 | 08/16/19 | 629 | Vazquez Popoca, Jose N |  | 22.62
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 08/23/19 | 819 | Eliassen, Cory H |  | 443.06
PR | 995 | 08/23/19 | 824 | Gauthier, Dillon R |  | 135.71
PR | 995 | 08/23/19 | 835 | Hubbard, Robert W |  | 177.4
PR | 995 | 08/23/19 | 835 | Hubbard, Robert W |  | 22.18
PR | 995 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 419.33
PR | 995 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 54.99
PR | 995 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 54.99
PR | 995 | 08/23/19 | 850 | Reed, Reuben H |  | 159.66
PR | 995 | 08/23/19 | 858 | Sanders, Allen O |  | 76.06
PR | 995 | 08/23/19 | 865 | Trower-Kelly, Fidel D |  | 15.97
PR | 995 | 08/23/19 | 866 | Vazquez Popoca, Jose N |  | 15.08
PR | 995 | 08/30/19 | 1010 | Eliassen, Cory H |  | 478.98
PR | 995 | 08/30/19 | 1015 | Gauthier, Dillon R |  | 60.32
PR | 995 | 08/30/19 | 1019 | Guerrero, Ali A |  | 60.32
PR | 995 | 08/30/19 | 1028 | Kinssies, Jr, John E |  | 109.99
PR | 995 | 09/06/19 | 31 | Eliassen, Cory H |  | 383.18
PR | 995 | 09/06/19 | 40 | Guerrero, Ali A |  | 241.26
PR | 995 | 09/06/19 | 70 | Sanders, Allen O |  | 76.06
PR | 995 | 09/06/19 | 85 | Donelson, Richard T |  | 55.44
PR | 995 | 09/13/19 | 255 | Eliassen, Cory H |  | 478.98
PR | 995 | 09/13/19 | 260 | Gauthier, Dillon R |  | 301.58
PR | 995 | 09/13/19 | 264 | Guerrero, Ali A |  | 180.95
PR | 995 | 09/13/19 | 285 | Reed, Reuben H |  | 299.36
PR | 995 | 09/13/19 | 293 | Sanders, Allen O |  | 86.93
PR | 995 | 09/20/19 | 492 | Eliassen, Cory H |  | 383.18
PR | 995 | 09/20/19 | 497 | Gauthier, Dillon R |  | 180.95
PR | 995 | 09/20/19 | 501 | Guerrero, Ali A |  | 301.58
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 44.35
PR | 995 | 09/20/19 | 523 | Reed, Reuben H |  | 239.49
PR | 995 | 09/20/19 | 523 | Reed, Reuben H |  | 239.49
PR | 995 | 09/20/19 | 531 | Sanders, Allen O |  | 108.66
PR | 995 | 09/27/19 | 648 | Eliassen, Cory H |  | 478.98
PR | 995 | 09/27/19 | 653 | Gauthier, Dillon R |  | 301.58
PR | 995 | 09/27/19 | 654 | Gerard, Jordan E |  | 63.86
PR | 995 | 09/27/19 | 657 | Guerrero, Ali A |  | 60.32
PR | 995 | 09/27/19 | 666 | Hubbard, Robert W |  | 44.35
PR | 995 | 09/27/19 | 666 | Hubbard, Robert W |  | 44.35
PR | 995 | 09/27/19 | 669 | Kinssies, Jr, John E |  | 109.99
PR | 995 | 09/27/19 | 669 | Kinssies, Jr, John E |  | 27.5
PR | 995 | 09/27/19 | 682 | Reed, Reuben H |  | 159.66
PR | 995 | 09/27/19 | 690 | Sanders, Allen O |  | 141.25
PR | 995 | 09/27/19 | 705 | Donelson, Richard T |  | 55.44
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 10/04/19 | 24 | Eliassen, Cory H |  | 287.39
PR | 995 | 10/04/19 | 29 | Gauthier, Dillon R |  | 60.32
PR | 995 | 10/04/19 | 58 | Reed, Reuben H |  | 319.32
PR | 995 | 10/04/19 | 66 | Sanders, Allen O |  | 65.19
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 48.79
PR | 995 | 10/11/19 | 274 | Cruz Guzman, Joel A |  | 99.34
PR | 995 | 10/11/19 | 279 | Eliassen, Cory H |  | 191.59
PR | 995 | 10/11/19 | 284 | Gauthier, Dillon R |  | 60.32
PR | 995 | 10/11/19 | 312 | Reed, Reuben H |  | 159.66
PR | 995 | 10/11/19 | 321 | Sanders, Allen O |  | 108.66
PR | 995 | 10/11/19 | 323 | Silva Morales, Jair J |  | 95.8
PR | 995 | 10/11/19 | 334 | Donelson, Richard T |  | 27.72
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 10/18/19 | 472 | Eliassen, Cory H |  | 251.46
PR | 995 | 10/18/19 | 477 | Gauthier, Dillon R |  | 60.32
PR | 995 | 10/18/19 | 505 | Reed, Reuben H |  | 99.79
PR | 995 | 10/18/19 | 505 | Reed, Reuben H |  | 39.92
PR | 995 | 10/18/19 | 514 | Sanders, Allen O |  | 65.19
PR | 995 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo |  | 124.18
PR | 995 | 10/18/19 | 527 | Donelson, Richard T |  | 27.72
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 10/25/19 | 607 | Eliassen, Cory H |  | 47.9
PR | 995 | 10/25/19 | 624 | Hubbard, Robert W |  | 44.35
PR | 995 | 10/25/19 | 641 | Reed, Reuben H |  | 19.96
PR | 995 | 10/25/19 | 650 | Sanders, Allen O |  | 21.73
PR | 995 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo |  | 124.18
PR | 995 | 10/25/19 | 664 | Donelson, Richard T |  | 27.72
PR | 995 | 11/01/19 | 23 | Eliassen, Cory H |  | 106.44
PR | 995 | 11/01/19 | 66 | Sanders, Allen O |  | 119.75
PR | 995 | 11/01/19 | 73 | Vazquez Popoca, Jose N |  | 70.96
PR | 995 | 11/08/19 | 197 | Eliassen, Cory H |  | 106.44
PR | 995 | 11/08/19 | 217 | Kinssies, Jr, John E |  | 62.09
PR | 995 | 11/08/19 | 231 | Reed, Reuben H |  | 43.46
PR | 995 | 11/08/19 | 240 | Sanders, Allen O |  | 47.9
PR | 995 | 11/08/19 | 246 | Trower-Kelly, Fidel D |  | 74.51
PR | 995 | 11/08/19 | 247 | Vazquez Popoca, Jose N |  | 70.96
PR | 995 | 11/08/19 | 253 | Donelson, Richard T |  | 27.72
PR | 995 | 11/15/19 | 476 | Kinssies, Jr, John E |  | 248.36
PR | 995 | 11/15/19 | 476 | Kinssies, Jr, John E |  | 201.79
PR | 995 | 11/15/19 | 494 | Roberts, Lake A |  | 177.4
PR | 995 | 11/15/19 | 499 | Sanders, Allen O |  | 47.9
PR | 995 | 11/15/19 | 512 | Donelson, Richard T |  | 55.44
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 64.31
PR | 995 | 11/22/19 | 647 | Kinssies, Jr, John E |  | 341.5
PR | 995 | 11/22/19 | 665 | Roberts, Lake A |  | 88.7
PR | 995 | 11/22/19 | 670 | Sanders, Allen O |  | 179.62
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 25.72
PR | 995 | 11/27/19 | 917 | Donelson, Richard T |  | 83.16
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 25.72
PR | 995 | 12/06/19 | 91 | Sanders, Allen O |  | 35.92
PR | 995 | 12/06/19 | 104 | Donelson, Richard T |  | 27.72
PR | 995 | 12/13/19 | 404 | Cruz Gonzalez, Julio C |  | 99.34
PR | 995 | 12/13/19 | 465 | Donelson, Richard T |  | 27.72
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 25.72
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 25.72
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 51.45
PR | 995 | 12/27/19 | 754 | Reed, Reuben H |  | 239.05
PR | 995 | 01/03/20 | 57 | Reed, Reuben H |  | 65.19
PR | 995 | 01/10/20 | 352 | Donelson, Richard T |  | 55.44
PR | 995 | 01/10/20 | 353 | Gerard, Jeffrey S |  | 25.72
PR | 995 | 01/17/20 | 596 | Reed, Reuben H |  | 43.46
PR | 995 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 25.72
PR | 998 | 06/29/18 | 1019 | Donelson, Richard T |  | 28.69
PR | 998 | 07/06/18 | 76 | Donelson, Richard T |  | 19.13
PR | 998 | 07/06/18 | 76 | Donelson, Richard T |  | 9.56
PR | 998 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/06/18 | 77 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/13/18 | 350 | Reed, Reuben H |  | 12.55
PR | 998 | 07/13/18 | 367 | Donelson, Richard T |  | 9.56
PR | 998 | 07/20/18 | 470 | Hubbard, Robert W |  | 7.19
PR | 998 | 07/20/18 | 507 | Donelson, Richard T |  | 9.56
PR | 998 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 07/20/18 | 508 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 07/27/18 | 817 | Reed, Reuben H |  | 6.27
PR | 998 | 07/27/18 | 835 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/03/18 | 35 | Hubbard, Robert W |  | 50.34
PR | 998 | 08/03/18 | 46 | McCabe, Thomas C |  | 36.72
PR | 998 | 08/03/18 | 63 | Sepulveda Gonzalez, Alfredo |  | 37.94
PR | 998 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 08/03/18 | 73 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/10/18 | 246 | Hubbard, Robert W |  | 14.38
PR | 998 | 08/10/18 | 257 | McCabe, Thomas C |  | 14.69
PR | 998 | 08/10/18 | 274 | Sepulveda Gonzalez, Alfredo |  | 14.23
PR | 998 | 08/10/18 | 284 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/10/18 | 284 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/17/18 | 514 | Hubbard, Robert W |  | 7.19
PR | 998 | 08/17/18 | 524 | McCabe, Thomas C |  | 12.24
PR | 998 | 08/17/18 | 541 | Sepulveda Gonzalez, Alfredo |  | 11.86
PR | 998 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 08/17/18 | 551 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 08/24/18 | 776 | Hubbard, Robert W |  | 3.6
PR | 998 | 08/24/18 | 812 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 08/31/18 | 1031 | Hubbard, Robert W |  | 28.76
PR | 998 | 08/31/18 | 1048 | Reed, Reuben H |  | 25.09
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 22.95
PR | 998 | 08/31/18 | 1070 | Gerard, Jeffrey S |  | 11.48
PR | 998 | 09/07/18 | 50 | Cruz Guzman, Joel A |  | 28.15
PR | 998 | 09/07/18 | 51 | Cruz Reyes, Jose |  | 29.38
PR | 998 | 09/07/18 | 70 | Hubbard, Robert W |  | 34.16
PR | 998 | 09/07/18 | 79 | McCabe, Thomas C |  | 19.58
PR | 998 | 09/07/18 | 88 | Reed, Reuben H |  | 50.18
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/07/18 | 106 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/14/18 | 302 | Hubbard, Robert W |  | 7.19
PR | 998 | 09/14/18 | 320 | Reed, Reuben H |  | 25.09
PR | 998 | 09/14/18 | 341 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 09/21/18 | 494 | Cruz Guzman, Joel A |  | 14.08
PR | 998 | 09/21/18 | 533 | Reed, Reuben H |  | 3.14
PR | 998 | 09/21/18 | 553 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 09/28/18 | 718 | Reed, Reuben H |  | 6.27
PR | 998 | 09/28/18 | 718 | Reed, Reuben H |  | 3.14
PR | 998 | 09/28/18 | 740 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/05/18 | 102 | Donelson, Richard T |  | 19.13
PR | 998 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/05/18 | 103 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 10/12/18 | 288 | Reed, Reuben H |  | 9.41
PR | 998 | 10/19/18 | 468 | Hubbard, Robert W |  | 5.39
PR | 998 | 10/19/18 | 507 | Donelson, Richard T |  | 9.56
PR | 998 | 10/25/18 | 687 | Hubbard, Robert W |  | 53.93
PR | 998 | 10/26/18 | 743 | McCabe, Thomas C |  | 58.75
PR | 998 | 10/26/18 | 751 | Reed, Reuben H |  | 75.28
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 10/26/18 | 775 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/02/18 | 39 | Hubbard, Robert W |  | 17.98
PR | 998 | 11/02/18 | 48 | McCabe, Thomas C |  | 17.14
PR | 998 | 11/02/18 | 55 | Reed, Reuben H |  | 62.73
PR | 998 | 11/02/18 | 76 | Donelson, Richard T |  | 9.56
PR | 998 | 11/02/18 | 77 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/09/18 | 234 | Reed, Reuben H |  | 25.09
PR | 998 | 11/09/18 | 257 | Donelson, Richard T |  | 4.78
PR | 998 | 11/09/18 | 258 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/16/18 | 465 | Hubbard, Robert W |  | 3.6
PR | 998 | 11/16/18 | 467 | Kinssies, Jr, John E |  | 15.91
PR | 998 | 11/16/18 | 474 | McCabe, Thomas C |  | 12.24
PR | 998 | 11/16/18 | 482 | Reed, Reuben H |  | 81.55
PR | 998 | 11/16/18 | 504 | Hubbard, Robert W |  | -3.6
PR | 998 | 11/16/18 | 508 | Hubbard, Robert W |  | 3.6
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 14.34
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 4.78
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 7.65
PR | 998 | 11/16/18 | 514 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/21/18 | 650 | Hubbard, Robert W |  | 3.6
PR | 998 | 11/21/18 | 658 | McCabe, Thomas C |  | 15.91
PR | 998 | 11/21/18 | 666 | Reed, Reuben H |  | 12.55
PR | 998 | 11/21/18 | 689 | Donelson, Richard T |  | 23.91
PR | 998 | 11/30/18 | 879 | Reed, Reuben H |  | 26.32
PR | 998 | 11/30/18 | 900 | Donelson, Richard T |  | 4.78
PR | 998 | 12/07/18 | 91 | Reed, Reuben H |  | 59.21
PR | 998 | 12/07/18 | 91 | Reed, Reuben H |  | 6.58
PR | 998 | 12/07/18 | 113 | Donelson, Richard T |  | 14.34
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 316 | Reed, Reuben H |  | 105.26
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/21/18 | 514 | Castro Hernandez, Jose A |  | 60.59
PR | 998 | 12/21/18 | 542 | Kinssies, Jr, John E |  | 37.18
PR | 998 | 12/21/18 | 546 | Lucas Tzintzun, Rafael |  | 60.59
PR | 998 | 12/21/18 | 556 | Reed, Reuben H |  | 125
PR | 998 | 12/21/18 | 567 | Silva Morales, Jair J |  | 87.98
PR | 998 | 12/21/18 | 578 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 12/28/18 | 705 | Castro Hernandez, Jose A |  | 65.64
PR | 998 | 12/28/18 | 733 | Kinssies, Jr, John E |  | 33.05
PR | 998 | 12/28/18 | 737 | Lucas Tzintzun, Rafael |  | 38.56
PR | 998 | 12/28/18 | 747 | Reed, Reuben H |  | 65.79
PR | 998 | 12/28/18 | 747 | Reed, Reuben H |  | 26.32
PR | 998 | 12/28/18 | 758 | Silva Morales, Jair J |  | 49.73
PR | 998 | 12/28/18 | 769 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 01/04/19 | 10 | Castro Hernandez, Jose A |  | 65.64
PR | 998 | 01/04/19 | 40 | Lucas Tzintzun, Rafael |  | 33.05
PR | 998 | 01/04/19 | 50 | Reed, Reuben H |  | 78.95
PR | 998 | 01/04/19 | 61 | Silva Morales, Jair J |  | 30.6
PR | 998 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 01/04/19 | 73 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/11/19 | 218 | Castro Hernandez, Jose A |  | 40.39
PR | 998 | 01/11/19 | 244 | Hubbard, Robert W |  | 22.49
PR | 998 | 01/11/19 | 244 | Hubbard, Robert W |  | 7.5
PR | 998 | 01/11/19 | 246 | Kinssies, Jr, John E |  | 45.44
PR | 998 | 01/11/19 | 250 | Lucas Tzintzun, Rafael |  | 39.24
PR | 998 | 01/11/19 | 260 | Reed, Reuben H |  | 47.7
PR | 998 | 01/11/19 | 260 | Reed, Reuben H |  | 23.03
PR | 998 | 01/11/19 | 260 | Reed, Reuben H |  | 6.58
PR | 998 | 01/11/19 | 271 | Silva Morales, Jair J |  | 76.5
PR | 998 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 01/11/19 | 282 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/18/19 | 473 | Castro Hernandez, Jose A |  | 60.59
PR | 998 | 01/18/19 | 501 | Kinssies, Jr, John E |  | 79.52
PR | 998 | 01/18/19 | 505 | Lucas Tzintzun, Rafael |  | 54.39
PR | 998 | 01/18/19 | 515 | Reed, Reuben H |  | 98.69
PR | 998 | 01/18/19 | 526 | Silva Morales, Jair J |  | 74.59
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/18/19 | 543 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 01/25/19 | 722 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 01/25/19 | 750 | Kinssies, Jr, John E |  | 82.62
PR | 998 | 01/25/19 | 754 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 01/25/19 | 764 | Reed, Reuben H |  | 39.47
PR | 998 | 01/25/19 | 764 | Reed, Reuben H |  | 82.24
PR | 998 | 01/25/19 | 775 | Silva Morales, Jair J |  | 61.2
PR | 998 | 01/25/19 | 786 | Donelson, Richard T |  | 4.78
PR | 998 | 02/01/19 | 10 | Castro Hernandez, Jose A |  | 93.41
PR | 998 | 02/01/19 | 38 | Kinssies, Jr, John E |  | 66.1
PR | 998 | 02/01/19 | 42 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 02/01/19 | 50 | Reed, Reuben H |  | 131.58
PR | 998 | 02/01/19 | 60 | Silva Morales, Jair J |  | 61.2
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 165 | Castro Hernandez, Jose A |  | 60.59
PR | 998 | 02/08/19 | 193 | Kinssies, Jr, John E |  | 49.57
PR | 998 | 02/08/19 | 197 | Lucas Tzintzun, Rafael |  | 33.05
PR | 998 | 02/08/19 | 205 | Reed, Reuben H |  | 78.95
PR | 998 | 02/08/19 | 216 | Silva Morales, Jair J |  | 15.3
PR | 998 | 02/08/19 | 216 | Silva Morales, Jair J |  | 30.6
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/15/19 | 327 | Castro Hernandez, Jose A |  | 53.01
PR | 998 | 02/15/19 | 355 | Kinssies, Jr, John E |  | 29.95
PR | 998 | 02/15/19 | 359 | Lucas Tzintzun, Rafael |  | 26.16
PR | 998 | 02/15/19 | 367 | Reed, Reuben H |  | 69.08
PR | 998 | 02/15/19 | 378 | Silva Morales, Jair J |  | 24.86
PR | 998 | 02/22/19 | 585 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 02/22/19 | 613 | Kinssies, Jr, John E |  | 29.95
PR | 998 | 02/22/19 | 617 | Lucas Tzintzun, Rafael |  | 66.1
PR | 998 | 02/22/19 | 626 | Reed, Reuben H |  | 157.9
PR | 998 | 02/22/19 | 637 | Silva Morales, Jair J |  | 76.5
PR | 998 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 02/22/19 | 648 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/01/19 | 10 | Castro Hernandez, Jose A |  | 121.18
PR | 998 | 03/01/19 | 28 | Gauthier, Dillon R |  | 19.58
PR | 998 | 03/01/19 | 44 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 03/01/19 | 53 | Reed, Reuben H |  | 157.9
PR | 998 | 03/01/19 | 64 | Silva Morales, Jair J |  | 76.5
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/08/19 | 252 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 03/08/19 | 284 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 03/08/19 | 293 | Reed, Reuben H |  | 118.42
PR | 998 | 03/08/19 | 303 | Silva Morales, Jair J |  | 76.5
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 499 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 03/15/19 | 516 | Gauthier, Dillon R |  | 48.96
PR | 998 | 03/15/19 | 531 | Lucas Tzintzun, Rafael |  | 22.03
PR | 998 | 03/15/19 | 540 | Reed, Reuben H |  | 105.26
PR | 998 | 03/15/19 | 551 | Silva Morales, Jair J |  | 61.2
PR | 998 | 03/15/19 | 562 | Donelson, Richard T |  | 4.78
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/22/19 | 713 | Castro Hernandez, Jose A |  | 80.78
PR | 998 | 03/22/19 | 730 | Gauthier, Dillon R |  | 48.96
PR | 998 | 03/22/19 | 745 | Lucas Tzintzun, Rafael |  | 55.08
PR | 998 | 03/22/19 | 753 | Reed, Reuben H |  | 131.58
PR | 998 | 03/22/19 | 764 | Silva Morales, Jair J |  | 61.2
PR | 998 | 03/22/19 | 776 | Donelson, Richard T |  | 4.78
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/29/19 | 924 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 03/29/19 | 942 | Gauthier, Dillon R |  | 48.96
PR | 998 | 03/29/19 | 965 | Reed, Reuben H |  | 131.58
PR | 998 | 03/29/19 | 976 | Silva Morales, Jair J |  | 76.5
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 9.95
PR | 998 | 04/05/19 | 86 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 04/05/19 | 104 | Gauthier, Dillon R |  | 48.96
PR | 998 | 04/05/19 | 128 | Reed, Reuben H |  | 131.58
PR | 998 | 04/05/19 | 139 | Silva Morales, Jair J |  | 76.5
PR | 998 | 04/12/19 | 330 | Castro Hernandez, Jose A |  | 15.15
PR | 998 | 04/12/19 | 330 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 04/12/19 | 347 | Gauthier, Dillon R |  | 7.34
PR | 998 | 04/12/19 | 347 | Gauthier, Dillon R |  | 48.96
PR | 998 | 04/12/19 | 372 | Reed, Reuben H |  | 51.64
PR | 998 | 04/12/19 | 372 | Reed, Reuben H |  | 113.6
PR | 998 | 04/12/19 | 383 | Silva Morales, Jair J |  | 11.48
PR | 998 | 04/12/19 | 383 | Silva Morales, Jair J |  | 76.5
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 04/19/19 | 527 | Castro Hernandez, Jose A |  | 30.29
PR | 998 | 04/19/19 | 527 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 04/19/19 | 534 | Cruz Guzman, Joel A |  | 17.21
PR | 998 | 04/19/19 | 534 | Cruz Guzman, Joel A |  | 45.9
PR | 998 | 04/19/19 | 545 | Gauthier, Dillon R |  | 14.69
PR | 998 | 04/19/19 | 545 | Gauthier, Dillon R |  | 48.96
PR | 998 | 04/19/19 | 553 | Hubbard, Dustin R |  | 14.08
PR | 998 | 04/19/19 | 570 | Reed, Reuben H |  | 130.82
PR | 998 | 04/19/19 | 576 | Romero Garza, Jesus I |  | 13.77
PR | 998 | 04/19/19 | 581 | Silva Morales, Jair J |  | 22.95
PR | 998 | 04/19/19 | 581 | Silva Morales, Jair J |  | 76.5
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 5.97
PR | 998 | 04/26/19 | 747 | Castro Hernandez, Jose A |  | 22.72
PR | 998 | 04/26/19 | 747 | Castro Hernandez, Jose A |  | 100.98
PR | 998 | 04/26/19 | 754 | Cruz Guzman, Joel A |  | 19.28
PR | 998 | 04/26/19 | 754 | Cruz Guzman, Joel A |  | 51.41
PR | 998 | 04/26/19 | 764 | Gauthier, Dillon R |  | 15.61
PR | 998 | 04/26/19 | 764 | Gauthier, Dillon R |  | 52.02
PR | 998 | 04/26/19 | 774 | Hubbard, Robert W |  | 26.78
PR | 998 | 04/26/19 | 789 | Reed, Reuben H |  | 127.37
PR | 998 | 04/26/19 | 795 | Romero Garza, Jesus I |  | 16.52
PR | 998 | 04/26/19 | 795 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 04/26/19 | 800 | Silva Morales, Jair J |  | 18.59
PR | 998 | 04/26/19 | 800 | Silva Morales, Jair J |  | 82.62
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/03/19 | 14 | Castro Hernandez, Jose A |  | 80.78
PR | 998 | 05/03/19 | 21 | Cruz Guzman, Joel A |  | 42.84
PR | 998 | 05/03/19 | 32 | Gauthier, Dillon R |  | 7.8
PR | 998 | 05/03/19 | 32 | Gauthier, Dillon R |  | 52.02
PR | 998 | 05/03/19 | 58 | Reed, Reuben H |  | 30.98
PR | 998 | 05/03/19 | 58 | Reed, Reuben H |  | 137.7
PR | 998 | 05/03/19 | 64 | Romero Garza, Jesus I |  | 12.39
PR | 998 | 05/03/19 | 64 | Romero Garza, Jesus I |  | 55.08
PR | 998 | 05/03/19 | 69 | Silva Morales, Jair J |  | 18.59
PR | 998 | 05/03/19 | 69 | Silva Morales, Jair J |  | 82.62
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/10/19 | 167 | Castro Hernandez, Jose A |  | 96.39
PR | 998 | 05/10/19 | 174 | Cruz Guzman, Joel A |  | 19.28
PR | 998 | 05/10/19 | 174 | Cruz Guzman, Joel A |  | 51.41
PR | 998 | 05/10/19 | 185 | Gauthier, Dillon R |  | 7.8
PR | 998 | 05/10/19 | 185 | Gauthier, Dillon R |  | 52.02
PR | 998 | 05/10/19 | 195 | Hubbard, Robert W |  | 7.65
PR | 998 | 05/10/19 | 195 | Hubbard, Robert W |  | 3.83
PR | 998 | 05/10/19 | 211 | Reed, Reuben H |  | 130.82
PR | 998 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 4.13
PR | 998 | 05/10/19 | 217 | Romero Garza, Jesus I |  | 33.05
PR | 998 | 05/10/19 | 222 | Silva Morales, Jair J |  | 18.59
PR | 998 | 05/10/19 | 222 | Silva Morales, Jair J |  | 82.62
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/17/19 | 399 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 05/17/19 | 406 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 05/17/19 | 417 | Gauthier, Dillon R |  | 46.82
PR | 998 | 05/17/19 | 427 | Hubbard, Robert W |  | 3.83
PR | 998 | 05/17/19 | 443 | Reed, Reuben H |  | 103.28
PR | 998 | 05/17/19 | 443 | Reed, Reuben H |  | 34.43
PR | 998 | 05/17/19 | 453 | Silva Morales, Jair J |  | 82.62
PR | 998 | 05/17/19 | 467 | Donelson, Richard T |  | 4.78
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/24/19 | 611 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 05/24/19 | 618 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 05/24/19 | 629 | Gauthier, Dillon R |  | 46.82
PR | 998 | 05/24/19 | 629 | Gauthier, Dillon R |  | 5.2
PR | 998 | 05/24/19 | 639 | Hubbard, Robert W |  | 22.95
PR | 998 | 05/24/19 | 639 | Hubbard, Robert W |  | 3.83
PR | 998 | 05/24/19 | 639 | Hubbard, Robert W |  | 3.83
PR | 998 | 05/24/19 | 649 | McCabe, Thomas C |  | 48.2
PR | 998 | 05/24/19 | 655 | Reed, Reuben H |  | 123.93
PR | 998 | 05/24/19 | 655 | Reed, Reuben H |  | 13.77
PR | 998 | 05/24/19 | 664 | Sepulveda Gonzalez, Alfredo |  | 64.26
PR | 998 | 05/24/19 | 665 | Silva Morales, Jair J |  | 66.1
PR | 998 | 05/24/19 | 680 | Donelson, Richard T |  | 14.34
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 6.31
PR | 998 | 05/31/19 | 885 | Castro Hernandez, Jose A |  | 77.65
PR | 998 | 05/31/19 | 892 | Cruz Guzman, Joel A |  | 17.14
PR | 998 | 05/31/19 | 903 | Gauthier, Dillon R |  | 41.62
PR | 998 | 05/31/19 | 913 | Hubbard, Robert W |  | 7.65
PR | 998 | 05/31/19 | 923 | McCabe, Thomas C |  | 50.87
PR | 998 | 05/31/19 | 929 | Reed, Reuben H |  | 13.77
PR | 998 | 05/31/19 | 929 | Reed, Reuben H |  | 96.39
PR | 998 | 05/31/19 | 937 | Sanders, Allen O |  | 11.25
PR | 998 | 05/31/19 | 938 | Sepulveda Gonzalez, Alfredo |  | 64.26
PR | 998 | 05/31/19 | 939 | Silva Morales, Jair J |  | 66.1
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/07/19 | 187 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 06/07/19 | 194 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 06/07/19 | 205 | Gauthier, Dillon R |  | 10.4
PR | 998 | 06/07/19 | 205 | Gauthier, Dillon R |  | 31.21
PR | 998 | 06/07/19 | 215 | Hubbard, Robert W |  | 15.3
PR | 998 | 06/07/19 | 215 | Hubbard, Robert W |  | 17.21
PR | 998 | 06/07/19 | 215 | Hubbard, Robert W |  | 15.3
PR | 998 | 06/07/19 | 224 | McCabe, Thomas C |  | 64.26
PR | 998 | 06/07/19 | 224 | McCabe, Thomas C |  | 10.71
PR | 998 | 06/07/19 | 224 | McCabe, Thomas C |  | 10.71
PR | 998 | 06/07/19 | 230 | Reed, Reuben H |  | 130.82
PR | 998 | 06/07/19 | 230 | Reed, Reuben H |  | 6.89
PR | 998 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 64.26
PR | 998 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 21.42
PR | 998 | 06/07/19 | 240 | Sepulveda Gonzalez, Alfredo |  | 21.42
PR | 998 | 06/07/19 | 241 | Silva Morales, Jair J |  | 16.52
PR | 998 | 06/07/19 | 241 | Silva Morales, Jair J |  | 33.05
PR | 998 | 06/07/19 | 254 | Donelson, Richard T |  | 4.78
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/14/19 | 458 | Castro Hernandez, Jose A |  | 64.26
PR | 998 | 06/14/19 | 458 | Castro Hernandez, Jose A |  | 34.81
PR | 998 | 06/14/19 | 464 | Cruz Guzman, Joel A |  | 34.27
PR | 998 | 06/14/19 | 464 | Cruz Guzman, Joel A |  | 34.27
PR | 998 | 06/14/19 | 473 | Gauthier, Dillon R |  | 10.4
PR | 998 | 06/14/19 | 473 | Gauthier, Dillon R |  | 41.62
PR | 998 | 06/14/19 | 499 | Reed, Reuben H |  | 41.31
PR | 998 | 06/14/19 | 499 | Reed, Reuben H |  | 72.29
PR | 998 | 06/14/19 | 499 | Reed, Reuben H |  | 24.1
PR | 998 | 06/14/19 | 509 | Silva Morales, Jair J |  | 82.62
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 9.56
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/21/19 | 627 | Castro Hernandez, Jose A |  | 64.26
PR | 998 | 06/21/19 | 627 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 06/21/19 | 634 | Cruz Guzman, Joel A |  | 68.54
PR | 998 | 06/21/19 | 644 | Gauthier, Dillon R |  | 48.12
PR | 998 | 06/21/19 | 670 | Reed, Reuben H |  | 99.83
PR | 998 | 06/21/19 | 680 | Silva Morales, Jair J |  | 61.97
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 845 | Castro Hernandez, Jose A |  | 64.26
PR | 998 | 06/28/19 | 845 | Castro Hernandez, Jose A |  | 42.84
PR | 998 | 06/28/19 | 862 | Gauthier, Dillon R |  | 31.21
PR | 998 | 06/28/19 | 862 | Gauthier, Dillon R |  | 20.81
PR | 998 | 06/28/19 | 887 | Reed, Reuben H |  | 82.62
PR | 998 | 06/28/19 | 887 | Reed, Reuben H |  | 13.77
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/05/19 | 17 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 07/05/19 | 34 | Gauthier, Dillon R |  | 20.81
PR | 998 | 07/05/19 | 34 | Gauthier, Dillon R |  | 20.81
PR | 998 | 07/05/19 | 59 | Reed, Reuben H |  | 110.16
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 4.78
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 07/12/19 | 287 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 07/12/19 | 303 | Gauthier, Dillon R |  | 10.4
PR | 998 | 07/12/19 | 303 | Gauthier, Dillon R |  | 10.4
PR | 998 | 07/12/19 | 328 | Reed, Reuben H |  | 55.08
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/19/19 | 517 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 07/19/19 | 517 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 07/19/19 | 533 | Gauthier, Dillon R |  | 41.62
PR | 998 | 07/19/19 | 533 | Gauthier, Dillon R |  | 1.3
PR | 998 | 07/19/19 | 543 | Hubbard, Robert W |  | 7.65
PR | 998 | 07/19/19 | 543 | Hubbard, Robert W |  | 3.83
PR | 998 | 07/19/19 | 558 | Reed, Reuben H |  | 41.31
PR | 998 | 07/19/19 | 558 | Reed, Reuben H |  | 55.08
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 621 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 07/26/19 | 621 | Castro Hernandez, Jose A |  | 21.42
PR | 998 | 07/26/19 | 636 | Gauthier, Dillon R |  | 31.21
PR | 998 | 07/26/19 | 636 | Gauthier, Dillon R |  | 20.81
PR | 998 | 07/26/19 | 646 | Hubbard, Robert W |  | 15.3
PR | 998 | 07/26/19 | 661 | Reed, Reuben H |  | 55.08
PR | 998 | 07/26/19 | 661 | Reed, Reuben H |  | 27.54
PR | 998 | 07/26/19 | 661 | Reed, Reuben H |  | 20.66
PR | 998 | 07/26/19 | 685 | Donelson, Richard T |  | 4.78
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/02/19 | 13 | Castro Hernandez, Jose A |  | 64.26
PR | 998 | 08/02/19 | 28 | Gauthier, Dillon R |  | 31.21
PR | 998 | 08/02/19 | 38 | Hubbard, Robert W |  | 19.13
PR | 998 | 08/02/19 | 53 | Reed, Reuben H |  | 72.29
PR | 998 | 08/02/19 | 53 | Reed, Reuben H |  | 17.21
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 32.13
PR | 998 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 10.71
PR | 998 | 08/09/19 | 281 | Gauthier, Dillon R |  | 15.61
PR | 998 | 08/09/19 | 281 | Gauthier, Dillon R |  | 5.2
PR | 998 | 08/09/19 | 291 | Hubbard, Robert W |  | 7.65
PR | 998 | 08/09/19 | 306 | Reed, Reuben H |  | 37.87
PR | 998 | 08/09/19 | 306 | Reed, Reuben H |  | 27.54
PR | 998 | 08/09/19 | 306 | Reed, Reuben H |  | 27.54
PR | 998 | 08/09/19 | 328 | Donelson, Richard T |  | 4.78
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/16/19 | 583 | Eliassen, Cory H |  | 6.2
PR | 998 | 08/16/19 | 588 | Gauthier, Dillon R |  | 2.6
PR | 998 | 08/16/19 | 598 | Hubbard, Robert W |  | 11.48
PR | 998 | 08/16/19 | 600 | Kinssies, Jr, John E |  | 94.86
PR | 998 | 08/16/19 | 613 | Reed, Reuben H |  | 27.54
PR | 998 | 08/16/19 | 621 | Sanders, Allen O |  | 11.25
PR | 998 | 08/16/19 | 628 | Trower-Kelly, Fidel D |  | 4.13
PR | 998 | 08/16/19 | 629 | Vazquez Popoca, Jose N |  | 3.9
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/23/19 | 819 | Eliassen, Cory H |  | 76.42
PR | 998 | 08/23/19 | 824 | Gauthier, Dillon R |  | 23.41
PR | 998 | 08/23/19 | 835 | Hubbard, Robert W |  | 30.6
PR | 998 | 08/23/19 | 835 | Hubbard, Robert W |  | 3.83
PR | 998 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 72.33
PR | 998 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 9.49
PR | 998 | 08/23/19 | 837 | Kinssies, Jr, John E |  | 9.49
PR | 998 | 08/23/19 | 850 | Reed, Reuben H |  | 27.54
PR | 998 | 08/23/19 | 858 | Sanders, Allen O |  | 13.12
PR | 998 | 08/23/19 | 865 | Trower-Kelly, Fidel D |  | 2.75
PR | 998 | 08/23/19 | 866 | Vazquez Popoca, Jose N |  | 2.6
PR | 998 | 08/30/19 | 1010 | Eliassen, Cory H |  | 82.62
PR | 998 | 08/30/19 | 1015 | Gauthier, Dillon R |  | 10.4
PR | 998 | 08/30/19 | 1019 | Guerrero, Ali A |  | 10.4
PR | 998 | 08/30/19 | 1028 | Kinssies, Jr, John E |  | 18.97
PR | 998 | 09/06/19 | 31 | Eliassen, Cory H |  | 66.1
PR | 998 | 09/06/19 | 40 | Guerrero, Ali A |  | 41.62
PR | 998 | 09/06/19 | 70 | Sanders, Allen O |  | 13.12
PR | 998 | 09/06/19 | 85 | Donelson, Richard T |  | 9.56
PR | 998 | 09/13/19 | 255 | Eliassen, Cory H |  | 82.62
PR | 998 | 09/13/19 | 260 | Gauthier, Dillon R |  | 52.02
PR | 998 | 09/13/19 | 264 | Guerrero, Ali A |  | 31.21
PR | 998 | 09/13/19 | 285 | Reed, Reuben H |  | 51.64
PR | 998 | 09/13/19 | 293 | Sanders, Allen O |  | 14.99
PR | 998 | 09/20/19 | 492 | Eliassen, Cory H |  | 66.1
PR | 998 | 09/20/19 | 497 | Gauthier, Dillon R |  | 31.21
PR | 998 | 09/20/19 | 501 | Guerrero, Ali A |  | 52.02
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 7.65
PR | 998 | 09/20/19 | 523 | Reed, Reuben H |  | 41.31
PR | 998 | 09/20/19 | 523 | Reed, Reuben H |  | 41.31
PR | 998 | 09/20/19 | 531 | Sanders, Allen O |  | 18.74
PR | 998 | 09/27/19 | 648 | Eliassen, Cory H |  | 82.62
PR | 998 | 09/27/19 | 653 | Gauthier, Dillon R |  | 52.02
PR | 998 | 09/27/19 | 654 | Gerard, Jordan E |  | 11.02
PR | 998 | 09/27/19 | 657 | Guerrero, Ali A |  | 10.4
PR | 998 | 09/27/19 | 666 | Hubbard, Robert W |  | 7.65
PR | 998 | 09/27/19 | 666 | Hubbard, Robert W |  | 7.65
PR | 998 | 09/27/19 | 669 | Kinssies, Jr, John E |  | 18.97
PR | 998 | 09/27/19 | 669 | Kinssies, Jr, John E |  | 4.74
PR | 998 | 09/27/19 | 682 | Reed, Reuben H |  | 27.54
PR | 998 | 09/27/19 | 690 | Sanders, Allen O |  | 24.37
PR | 998 | 09/27/19 | 705 | Donelson, Richard T |  | 9.56
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/04/19 | 24 | Eliassen, Cory H |  | 49.57
PR | 998 | 10/04/19 | 29 | Gauthier, Dillon R |  | 10.4
PR | 998 | 10/04/19 | 58 | Reed, Reuben H |  | 55.08
PR | 998 | 10/04/19 | 66 | Sanders, Allen O |  | 11.25
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/11/19 | 274 | Cruz Guzman, Joel A |  | 17.14
PR | 998 | 10/11/19 | 279 | Eliassen, Cory H |  | 33.05
PR | 998 | 10/11/19 | 284 | Gauthier, Dillon R |  | 10.4
PR | 998 | 10/11/19 | 312 | Reed, Reuben H |  | 27.54
PR | 998 | 10/11/19 | 321 | Sanders, Allen O |  | 18.74
PR | 998 | 10/11/19 | 323 | Silva Morales, Jair J |  | 16.52
PR | 998 | 10/11/19 | 334 | Donelson, Richard T |  | 4.78
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/18/19 | 472 | Eliassen, Cory H |  | 43.38
PR | 998 | 10/18/19 | 477 | Gauthier, Dillon R |  | 10.4
PR | 998 | 10/18/19 | 505 | Reed, Reuben H |  | 17.21
PR | 998 | 10/18/19 | 505 | Reed, Reuben H |  | 6.89
PR | 998 | 10/18/19 | 514 | Sanders, Allen O |  | 11.25
PR | 998 | 10/18/19 | 515 | Sepulveda Gonzalez, Alfredo |  | 21.42
PR | 998 | 10/18/19 | 527 | Donelson, Richard T |  | 4.78
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/25/19 | 607 | Eliassen, Cory H |  | 8.26
PR | 998 | 10/25/19 | 624 | Hubbard, Robert W |  | 7.65
PR | 998 | 10/25/19 | 641 | Reed, Reuben H |  | 3.44
PR | 998 | 10/25/19 | 650 | Sanders, Allen O |  | 3.75
PR | 998 | 10/25/19 | 651 | Sepulveda Gonzalez, Alfredo |  | 21.42
PR | 998 | 10/25/19 | 664 | Donelson, Richard T |  | 4.78
PR | 998 | 11/01/19 | 23 | Eliassen, Cory H |  | 18.36
PR | 998 | 11/01/19 | 66 | Sanders, Allen O |  | 20.66
PR | 998 | 11/01/19 | 73 | Vazquez Popoca, Jose N |  | 12.24
PR | 998 | 11/08/19 | 197 | Eliassen, Cory H |  | 18.36
PR | 998 | 11/08/19 | 217 | Kinssies, Jr, John E |  | 10.71
PR | 998 | 11/08/19 | 231 | Reed, Reuben H |  | 7.5
PR | 998 | 11/08/19 | 240 | Sanders, Allen O |  | 8.26
PR | 998 | 11/08/19 | 246 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 11/08/19 | 247 | Vazquez Popoca, Jose N |  | 12.24
PR | 998 | 11/08/19 | 253 | Donelson, Richard T |  | 4.78
PR | 998 | 11/15/19 | 476 | Kinssies, Jr, John E |  | 42.84
PR | 998 | 11/15/19 | 476 | Kinssies, Jr, John E |  | 34.81
PR | 998 | 11/15/19 | 494 | Roberts, Lake A |  | 30.6
PR | 998 | 11/15/19 | 499 | Sanders, Allen O |  | 8.26
PR | 998 | 11/15/19 | 512 | Donelson, Richard T |  | 9.56
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 11.09
PR | 998 | 11/22/19 | 647 | Kinssies, Jr, John E |  | 58.91
PR | 998 | 11/22/19 | 665 | Roberts, Lake A |  | 15.3
PR | 998 | 11/22/19 | 670 | Sanders, Allen O |  | 30.98
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/27/19 | 917 | Donelson, Richard T |  | 14.34
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/06/19 | 91 | Sanders, Allen O |  | 6.2
PR | 998 | 12/06/19 | 104 | Donelson, Richard T |  | 4.78
PR | 998 | 12/13/19 | 404 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 12/13/19 | 465 | Donelson, Richard T |  | 4.78
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/27/19 | 754 | Reed, Reuben H |  | 41.23
PR | 998 | 01/03/20 | 57 | Reed, Reuben H |  | 11.25
PR | 998 | 01/10/20 | 352 | Donelson, Richard T |  | 9.56
PR | 998 | 01/10/20 | 353 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/17/20 | 596 | Reed, Reuben H |  | 7.5
PR | 998 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 4.44
AR | 999 | 07/20/18 | 529 | Kirkland Sustainable Investments, LLC$Pl |  | -7000 | 037141
AR | 999 | 08/20/18 | 595 | Kirkland Sustainable Investments, LLC$Pl |  | -66200 | 037166
AR | 999 | 08/20/18 | 595 | Kirkland Sustainable Investments, LLC$Pl |  | -9500 | 037166
AR | 999 | 10/19/18 | 522 | Kirkland Sustainable Investments, LLC$Pl |  | -13100 | 037208
AR | 999 | 11/16/18 | 532 | Kirkland Sustainable Investments, LLC$Pl |  | -13100 | 037238
AR | 999 | 11/16/18 | 728 | Kirkland Sustainable Investments, LLC$Pl |  | 13100 | 037243
AR | 999 | 11/16/18 | 729 | Kirkland Sustainable Investments, LLC$Pl |  | -13100 | 037244
AR | 999 | 11/16/18 | 729 | Kirkland Sustainable Investments, LLC$Pl |  | -3340 | 037244
AR | 999 | 12/14/18 | 358 | Kirkland Sustainable Investments, LLC$Pl |  | -19440 | 037261
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -12960 | 037265
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -90720 | 037265
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -36660 | 037265
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -40720 | 037265
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -17040 | 037265
AR | 999 | 01/18/19 | 547 | Kirkland Sustainable Investments, LLC$Pl |  | -1670 | 037265
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -18900 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -17040 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -15400 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -39760 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -20450 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -1305 | 037292
AR | 999 | 02/20/19 | 570 | Kirkland Sustainable Investments, LLC$Pl |  | -5965 | 037292
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -12960 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -14585 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -13630 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -7395 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -33795 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -29440 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -5500 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -36060 | 037309
AR | 999 | 03/20/19 | 688 | Kirkland Sustainable Investments, LLC$Pl |  | -17700 | 037309
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 12960 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 14585 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 13630 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 7395 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 33795 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 29440 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 5500 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 36060 | 037314
AR | 999 | 03/20/19 | 852 | Kirkland Sustainable Investments, LLC$Pl |  | 17700 | 037314
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -12960 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -14586 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -13630 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -7395 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -33795 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -29440 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -5500 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -36060 | 037315
AR | 999 | 03/20/19 | 853 | Kirkland Sustainable Investments, LLC$Pl |  | -17700 | 037315
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -25920 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -18970 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -19880 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -39760 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -21640 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -36060 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | -20100 | 037328
AR | 999 | 04/19/19 | 612 | Kirkland Sustainable Investments, LLC$Pl |  | 500 | 037328
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 25920 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 18970 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 19880 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 19070 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 39760 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 21640 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 19070 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 36060 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | 20100 | 037333
AR | 999 | 04/19/19 | 650 | Kirkland Sustainable Investments, LLC$Pl |  | -500 | 037333
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -25920 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -18970 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -19880 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -39760 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -21640 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -36060 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | -10050 | 037334
AR | 999 | 04/19/19 | 651 | Kirkland Sustainable Investments, LLC$Pl |  | 500 | 037334
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 25920 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 18970 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 19880 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 19070 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 39760 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 21640 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 19070 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 36060 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | 10050 | 037335
AR | 999 | 04/19/19 | 819 | Kirkland Sustainable Investments, LLC$Pl |  | -500 | 037335
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -25920 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -18970 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -19880 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -39760 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -21640 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -19070 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -36060 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | -10050 | 037336
AR | 999 | 04/19/19 | 820 | Kirkland Sustainable Investments, LLC$Pl |  | 500 | 037336
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -40720 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -21880 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -19880 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -21640 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -5000 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -10050 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -4450 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -4748 | 037350
AR | 999 | 05/20/19 | 517 | Kirkland Sustainable Investments, LLC$Pl |  | -3250 | 037350
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 40720 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 21880 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 19880 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 21640 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 5000 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 10050 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 4450 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 4748 | 037353
AR | 999 | 05/20/19 | 577 | Kirkland Sustainable Investments, LLC$Pl |  | 3250 | 037353
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -40720 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -21879 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -19880 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -21640 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -5000 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -10050 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -4450 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -4762.4 | 037354
AR | 999 | 05/20/19 | 578 | Kirkland Sustainable Investments, LLC$Pl |  | -3250 | 037354
AR | 999 | 06/19/19 | 614 | Kirkland Sustainable Investments, LLC$Pl |  | -36465 | 037370
AR | 999 | 06/19/19 | 614 | Kirkland Sustainable Investments, LLC$Pl |  | -5180 | 037370
AR | 999 | 06/19/19 | 614 | Kirkland Sustainable Investments, LLC$Pl |  | -5000 | 037370
AR | 999 | 06/19/19 | 614 | Kirkland Sustainable Investments, LLC$Pl |  | -3295 | 037370
AR | 999 | 08/15/19 | 754 | Kirkland Sustainable Investments, LLC$Pl |  | -9997 | 037391
AR | 999 | 08/15/19 | 754 | Kirkland Sustainable Investments, LLC$Pl |  | -20500 | 037391
AR | 999 | 08/15/19 | 754 | Kirkland Sustainable Investments, LLC$Pl |  | -1177 | 037391
AR | 999 | 08/15/19 | 754 | Kirkland Sustainable Investments, LLC$Pl |  | -2062 | 037391
AR | 999 | 08/15/19 | 754 | Kirkland Sustainable Investments, LLC$Pl |  | -1880 | 037391
AR | 999 | 08/15/19 | 1091 | Kirkland Sustainable Investments, LLC$Pl |  | 9997 | 037399
AR | 999 | 08/15/19 | 1091 | Kirkland Sustainable Investments, LLC$Pl |  | 20500 | 037399
AR | 999 | 08/15/19 | 1091 | Kirkland Sustainable Investments, LLC$Pl |  | 1177 | 037399
AR | 999 | 08/15/19 | 1091 | Kirkland Sustainable Investments, LLC$Pl |  | 2062 | 037399
AR | 999 | 08/15/19 | 1091 | Kirkland Sustainable Investments, LLC$Pl |  | 1880 | 037399
AR | 999 | 08/15/19 | 1092 | Kirkland Sustainable Investments, LLC$Pl |  | -9997 | 037400
AR | 999 | 08/15/19 | 1092 | Kirkland Sustainable Investments, LLC$Pl |  | -20500 | 037400
AR | 999 | 08/15/19 | 1092 | Kirkland Sustainable Investments, LLC$Pl |  | -1177.5 | 037400
AR | 999 | 08/15/19 | 1092 | Kirkland Sustainable Investments, LLC$Pl |  | -2061.6 | 037400
AR | 999 | 08/15/19 | 1092 | Kirkland Sustainable Investments, LLC$Pl |  | -1880 | 037400
AR | 999 | 09/20/19 | 560 | Kirkland Sustainable Investments, LLC$Pl |  | -925 | 037404
AR | 999 | 09/20/19 | 560 | Kirkland Sustainable Investments, LLC$Pl |  | -22122 | 037404
AR | 999 | 09/20/19 | 560 | Kirkland Sustainable Investments, LLC$Pl |  | -20664 | 037404
AR | 999 | 09/20/19 | 560 | Kirkland Sustainable Investments, LLC$Pl |  | -18450 | 037404
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -925 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -2458 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -2296 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -2050 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -1500 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -1177.5 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -1205 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -515.4 | 037421
AR | 999 | 10/18/19 | 534 | Kirkland Sustainable Investments, LLC$Pl |  | -2399 | 037421
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 925 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 2458 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 2296 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 2050 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 1500 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 1177.5 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 1205 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 515.4 | 037432
AR | 999 | 10/18/19 | 682 | Kirkland Sustainable Investments, LLC$Pl |  | 2399 | 037432
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -925 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -2458 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -2296 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -2050 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -1500 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -1177.5 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -1190.6 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -515.4 | 037433
AR | 999 | 10/18/19 | 683 | Kirkland Sustainable Investments, LLC$Pl |  | -2399 | 037433
AR | 999 | 11/18/19 | 555 | Kirkland Sustainable Investments, LLC$Pl |  | -1857 | 037437
AR | 999 | 11/18/19 | 555 | Kirkland Sustainable Investments, LLC$Pl |  | -412 | 037437
AR | 999 | 01/20/20 | 649 | Kirkland Sustainable Investments, LLC$Pl |  | -469 | 037464
AR | 999 | 01/20/20 | 649 | Kirkland Sustainable Investments, LLC$Pl |  | -6113 | 037464