## 01 Overview
OWP #2058 · Howell Apartments
Blueprint Capital Services, LLC · 76 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 961556
Revised budget (expenses) | 698608.42
Forecast net profit | 262947.58
Forecast margin | 27.35%
Progress to Date
Work complete (billed) | 961556
Retention held | 0
Earned less retention | 961556
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 125006.53
AP | 233739.79
PR | 416556.81
AR | -1037527

## 02 Job Info
JOB #2058 · BLUEPRINT CAPITAL SERVICES LLC · Howell Apartments — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract TBD (no contract on file).
IDENTITY
OWP Job ID | 2058
Project Name | Howell Apartments
Site Address | 600 E Howell Street, Seattle WA 98122 (Capitol Hill)
Subcontract Number | TBD (no contract on file)
Effective Date | 2019
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Blueprint Capital Services LLC
GC Address | PO Box 16309, Seattle WA 98116
GC Contract Signatory | Blueprint
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Blueprint
Owner Address | PO Box 16309, Seattle WA 98116
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | Not Wrap
Retention | 5% per contract
CONTRACT
Contract Value | $928,800 original
CHANGE-EVENT META
Executed CO Count | 7
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | CO #07 Convert Retail to Live/Work Units (added 2 Live/Work units with full plumbing scope)
COR Themes | (see GDrive)
Key RFIs | (see GDrive)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Howell job ticket 9-14-20.pdf
GDrive Folder | Job Books - Completed Jobs/2058-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets | 78 | 72 Gerber Maxwell 21-912 + 4 ADA + 2 added Live/Work
Lavs | 78 | Kohler K-2035-1 wall-hung; x07-x12 stacks owner-supplied
Faucets | 78 | Delta Trinsic 559HA-BL-DST matte black
Showers/tubs Type B | 73 | 70 Best Bath P3838 + 3 LSS3838B5T
Tubs Sterling | 2 | Sterling 71171110 plastic tub base
Tub/showers Type A ADA | 3 | 1 Aquatic 2603SMTE + 2 added Live/Work
Kitchen faucets | 76 | Delta Trinsic 9959-BL-DST matte black
Air gaps | 76 | Delta 72020-BL
VERIFIED MAIN FIXTURE COUNT | 310
Per unit (76): 4.08
AUDIT NOTE (2026-04-25): First-pass count of 464 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 310 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 928800 | 961556 | 32756
Executed change orders (net) | 0 | 32756 | 32756
Total contract value | 928800 | 994312 | 65512
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 6930 | 6980 | 1731.5 | 5248.5 | 0 | 24.81%
101 | Takeoff & Purchase Labor | 11165 | 11215 | 6184.5 | 5030.5 | 0 | 55.14%
110 | Underground Labor | 3760 | 4280 | 3766 | 514 | 0 | 87.99%
111 | Garage Labor | 12325 | 12815 | 1242 | 11573 | 0 | 9.692%
112 | Canout Labor | 12054 | 12154 | 3080 | 9074 | 0 | 25.34%
120 | Roughin Labor | 93340 | 102640 | 195332 | -92692 | 0 | 190.3%
130 | Finish Labor | 23100 | 23310 | 25477 | -2167 | 0 | 109.3%
140 | Gas Labor | 9750 | 10230 | 5276 | 4954 | 0 | 51.57%
141 | Water Main/Insulation Lab | 32180 | 32180 | 22890 | 9290 | 0 | 71.13%
142 | Mech Room Labor | 14400 | 14400 | 12628.5 | 1771.5 | 0 | 87.7%
210 | Underground Material | 2880 | 3580 | 2678.61 | 901.39 | 0 | 74.82%
211 | Garage Material | 13510 | 13960 | 16428.12 | -2468.12 | 0 | 117.7%
212 | Canout Material | 11466 | 11566 | 4845.32 | 6720.68 | 0 | 41.89%
220 | Roughin Material | 43040 | 44540 | 32023.13 | 12516.87 | 0 | 71.9%
230 | Finish Material | 159654 | 169208 | 150779.38 | 18428.62 | 0 | 89.11%
240 | Gas Material | 11050 | 11250 | 3600.92 | 7649.08 | 0 | 32.01%
241 | Water Main/Insulation Mat | 30640 | 30640 | 16093.43 | 14546.57 | 0 | 52.52%
242 | Mech Room Material | 15000 | 15000 | 17680.02 | -2680.02 | 0 | 117.9%
600 | Subcontractor | 1000 | 1000 | 5000 | -4000 | 0 | 500%
601 | Engineering/Plans | 30000 | 30000 | 19206.32 | 10793.68 | 0 | 64.02%
602 | Rental Equipment | 600 | 600 | 624.67 | -24.67 | 0 | 104.1%
603 | Permits & Licenses | 8858 | 8858 | 4751 | 4107 | 0 | 53.64%
607 | Other Expenses | 7000 | 7000 | 9064.4 | -2064.4 | 0 | 129.5%
995 | Payroll Burden | 98551.8 | 103591.8 | 117712.31 | -14120.51 | 0 | 113.6%
998 | Payroll Taxes | 16753.81 | 17610.62 | 21237 | -3626.38 | 0 | 120.6%
TOTAL |  | 669007.61 | 698608.42 | 699332.13 | -723.71 | 0 | 100.1%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 230204 | 277607.5 | -47403.5 | 120.6%
Material | 8 | 299744 | 244128.93 | 55615.07 | 81.45%
Overhead | 5 | 47458 | 38646.39 | 8811.61 | 81.43%
Burden | 2 | 121202.42 | 138949.31 | -17746.89 | 114.6%
TOTAL | 25 | 698608.42 | 699332.13 | -723.71 | 100.1%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 6980 | 1731.5 | 5248.5 | -75.19% | UNDER
101 | Takeoff & Purchase Labor | 11215 | 6184.5 | 5030.5 | -44.86% | UNDER
110 | Underground Labor | 4280 | 3766 | 514 | -12.01% | UNDER
111 | Garage Labor | 12815 | 1242 | 11573 | -90.31% | UNDER
112 | Canout Labor | 12154 | 3080 | 9074 | -74.66% | UNDER
120 | Roughin Labor | 102640 | 195332 | -92692 | 90.31% | CRITICAL
130 | Finish Labor | 23310 | 25477 | -2167 | 9.296% | ON
140 | Gas Labor | 10230 | 5276 | 4954 | -48.43% | UNDER
141 | Water Main/Insulation Lab | 32180 | 22890 | 9290 | -28.87% | UNDER
142 | Mech Room Labor | 14400 | 12628.5 | 1771.5 | -12.3% | UNDER
210 | Underground Material | 3580 | 2678.61 | 901.39 | -25.18% | UNDER
211 | Garage Material | 13960 | 16428.12 | -2468.12 | 17.68% | OVER
212 | Canout Material | 11566 | 4845.32 | 6720.68 | -58.11% | UNDER
220 | Roughin Material | 44540 | 32023.13 | 12516.87 | -28.1% | UNDER
230 | Finish Material | 169208 | 150779.38 | 18428.62 | -10.89% | UNDER
240 | Gas Material | 11250 | 3600.92 | 7649.08 | -67.99% | UNDER
241 | Water Main/Insulation Mat | 30640 | 16093.43 | 14546.57 | -47.48% | UNDER
242 | Mech Room Material | 15000 | 17680.02 | -2680.02 | 17.87% | OVER
600 | Subcontractor | 1000 | 5000 | -4000 | 400% | CRITICAL
601 | Engineering/Plans | 30000 | 19206.32 | 10793.68 | -35.98% | UNDER
602 | Rental Equipment | 600 | 624.67 | -24.67 | 4.112% | ON
603 | Permits & Licenses | 8858 | 4751 | 4107 | -46.36% | UNDER
607 | Other Expenses | 7000 | 9064.4 | -2064.4 | 29.49% | OVER
995 | Payroll Burden | 103591.8 | 117712.31 | -14120.51 | 13.63% | OVER
998 | Payroll Taxes | 17610.62 | 21237 | -3626.38 | 20.59% | OVER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 52512.17 | 57 | 22.47%
Keller Supply Company | 52411.12 | 13 | 22.42%
Best Bath Systems | 37617.22 | 2 | 16.09%
California Hydronics Corp | 21829 | 2 | 9.339%
Ferguson Enterprises, Inc. #3007 | 18946 | 21 | 8.106%
Franklin Engineering | 18537.75 | 8 | 7.931%
Capital One Credit Card | 14445.44 | 36 | 6.18%
Consolidated Supply Co. | 11224.38 | 7 | 4.802%
Mechanical Resource Services, Inc. | 5000 | 1 | 2.139%
H&E Equipment Services, Inc. | 624.67 | 2 | 0.2673%
Mechanical Sales, Inc. | 464.14 | 3 | 0.1986%
DRSi | 127.9 | 1 | 0.05472%
TOTAL AP | 233739.79 | 153

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Castro Hernandez, Jose A | 1259 | 46735 | 37.1207 | LEAD/SUPERVISOR
Reed, Reuben H | 1113 | 53117 | 47.7242 | LEAD/SUPERVISOR
Silva Morales, Jair J | 1050 | 30453 | 29.0029 | JOURNEYMAN
Guerrero Espinoza, Mario | 1021 | 16936 | 16.5877 | APPRENTICE/HELPER
Jimenez Alvarenga, Gerson M | 931 | 25069 | 26.927 | JOURNEYMAN
Garcia Perez, Ervey O | 784 | 14112 | 18 | APPRENTICE/HELPER
Cruz Guzman, Joel A | 776 | 23264 | 29.9794 | JOURNEYMAN
Frausto Mendoza, Pedro | 372 | 9300 | 25 | JOURNEYMAN
Kinssies, Jr, John E | 278.5 | 9748 | 35.0018 | JOURNEYMAN
Sanders, Allen O | 225.5 | 12177 | 54 | LEAD/SUPERVISOR
Cruz Reyes, Jose | 190 | 6080 | 32 | JOURNEYMAN
Gauthier, Dillon R | 163 | 2771 | 17 | APPRENTICE/HELPER
Cruz Gonzalez, Julio C | 152 | 4256 | 28 | JOURNEYMAN
Boss, Benjamin T | 128 | 2304 | 18 | APPRENTICE/HELPER
Hubbard, Robert W | 104.5 | 5551 | 53.1196 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 79.5 | 4416 | 55.5472 | LEAD/SUPERVISOR
Martinez Reyes, Juan C | 71 | 2388 | 33.6338 | JOURNEYMAN
Barnhart, Joseph N | 67.5 | 3501 | 51.8667 | LEAD/SUPERVISOR
Donelson, Richard T | 56 | 3500 | 62.5 | LEAD/SUPERVISOR
McCabe, Thomas C | 35 | 1345 | 38.4286 | LEAD/SUPERVISOR
Taylor, Evan R | 12 | 325 | 27.0833 | JOURNEYMAN
Mackey, Cole J | 8 | 120 | 15 | APPRENTICE/HELPER
Lopez, Maslin A | 4 | 68 | 17 | APPRENTICE/HELPER
Romero Garza, Jesus I | 4 | 72 | 18 | APPRENTICE/HELPER

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 8 | 2940 | 130342 | 33.09%
JOURNEYMAN | 9 | 3832.5 | 110882 | 43.14%
APPRENTICE/HELPER | 7 | 2112 | 36383 | 23.77%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 8884
Active workers | 24
Hours per unit (to date) | 116.9
Revenue per labor hour (billed) | 108.23
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 27.35% | 34% | -6.654%
Roughin labor share (code 120) | 44.59% | 45% | -0.4135%
Top vendor concentration | 22.47% | 38% | -15.53%
Hours per unit | 116.9013 | 95 | 21.9013

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Roughin Labor (120) CRITICAL overrun | ⚠ WATCH | Actual $195,332 vs revised $102,640 (+90%) — needs immediate attention
Garage Material (211) over revised | ⚠ WATCH | Actual $16,428 vs revised $13,960 (+18%) — monitor
Mech Room Material (242) over revised | ⚠ WATCH | Actual $17,680 vs revised $15,000 (+18%) — monitor
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $5,000 vs revised $1,000 (+400%) — needs immediate attention
Other Expenses (607) over revised | ⚠ WATCH | Actual $9,064 vs revised $7,000 (+29%) — monitor
Payroll Burden (995) over revised | ⚠ WATCH | Actual $117,712 vs revised $103,592 (+14%) — monitor
Payroll Taxes (998) over revised | ⚠ WATCH | Actual $21,237 vs revised $17,611 (+21%) — monitor
Top vendor concentration (Rosen Supply Kirklan) | ✓ OK | 22% of AP ($52,512) — acceptable
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range
Forecast margin | ✓ OK | 27.3% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 699332.13 | 699332.13 | 0
Revenue billed (AR ·-1) | -961556 | 1037527 | -1999083
AP source total |  | 233739.79 | —
PR source total |  | 416556.81 | —
GL source total |  | 125006.53 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2058 live project. 17-tab JCR schema on revised budget basis.