## Summary
#2058 · Howell Apartments
Blueprint Capital Service · 76 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
961556 | 27.35% | 961556 | 0
Key facts
Original contract |  | 928800
Revised contract (CO impact) |  | 961556
Executed COs (net) |  | 32756
Retention held |  | 0
Revised expense budget |  | 698608.42
Forecast net profit |  | 262947.58
Percent complete |  | 100%
Live signals
Roughin Labor (120) CRITICAL | ⚠ WATCH | Actual $195,332 vs revised $102,640 (+90%) — needs attention
Garage Material (211) over | ⚠ WATCH | Actual $16,428 vs revised $13,960 (+18%) — monitor
Mech Room Material (242) over | ⚠ WATCH | Actual $17,680 vs revised $15,000 (+18%) — monitor
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $5,000 vs revised $1,000 (+400%) — needs attention
Other Expenses (607) over | ⚠ WATCH | Actual $9,064 vs revised $7,000 (+29%) — monitor
Payroll Burden (995) over | ⚠ WATCH | Actual $117,712 vs revised $103,592 (+14%) — monitor
Payroll Taxes (998) over | ⚠ WATCH | Actual $21,237 vs revised $17,611 (+21%) — monitor
Top vendor (Rosen Supply Kirklan) | ✓ OK | 22% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 27.3% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Rosen Supply Kirkland | 57 | 52512.17 | 22.47%
Keller Supply Company | 13 | 52411.12 | 22.42%
Best Bath Systems | 2 | 37617.22 | 16.09%
California Hydronics Corp | 2 | 21829 | 9.339%
Ferguson Enterprises, Inc. #3007 | 21 | 18946 | 8.106%
Franklin Engineering | 8 | 18537.75 | 7.931%

## Transactions
Transactions Detail
JDR source transactions for job #2058 · 1798 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 1 | 52 | 22057
PR | 100 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 100 | 04/26/19 | 813 | Gerard, Jeffrey S | 1 | 55 | 23569
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 2 | 110 | 24255
PR | 100 | 07/05/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 924330
PR | 100 | 08/02/19 | 77 | Gerard, Jeffrey S | 1 | 55 | 924708
PR | 100 | 09/13/19 | 309 | Gerard, Jeffrey S | 1 | 55 | 25158
PR | 100 | 09/27/19 | 706 | Gerard, Jeffrey S | 1 | 55 | 925311
PR | 100 | 10/04/19 | 82 | Gerard, Jeffrey S | 1 | 55 | 25389
PR | 100 | 10/18/19 | 528 | Gerard, Jeffrey S | 1 | 55 | 25545
PR | 100 | 10/25/19 | 665 | Gerard, Jeffrey S | 1 | 55 | 925505
PR | 100 | 11/01/19 | 80 | Donelson, Richard T | 1 | 62.5 | 925696
PR | 100 | 11/01/19 | 81 | Gerard, Jeffrey S | 1 | 58 | 925697
PR | 100 | 11/08/19 | 254 | Gerard, Jeffrey S | 2 | 116 | 925773
PR | 100 | 11/15/19 | 513 | Gerard, Jeffrey S | 1 | 58 | 925849
PR | 100 | 11/22/19 | 685 | Gerard, Jeffrey S | 2 | 116 | 925924
PR | 100 | 11/27/19 | 918 | Gerard, Jeffrey S | 2 | 116 | 925999
PR | 100 | 12/06/19 | 105 | Gerard, Jeffrey S | 1 | 58 | 26077
PR | 100 | 12/13/19 | 466 | Gerard, Jeffrey S | 1 | 58 | 926232
PR | 100 | 12/20/19 | 619 | Gerard, Jeffrey S | 1 | 58 | 926308
PR | 100 | 01/03/20 | 82 | Gerard, Jeffrey S | 1 | 58 | 926463
PR | 100 | 01/17/20 | 619 | Gerard, Jeffrey S | 1.5 | 87 | 926618
PR | 100 | 03/26/20 | 821 | Gerard, Jeffrey S | 1 | 58 | 927397
PR | 100 | 07/31/20 | 544 | Gerard, Jeffrey S | 1 | 58 | 928490
PR | 100 | 08/21/20 | 460 | Gerard, Jeffrey S | 1 | 58 | 928614
PR | 100 | 09/18/20 | 331 | Gerard, Jeffrey S | 1 | 58 | 928802
PR | 101 | 09/07/18 | 105 | Donelson, Richard T | 2 | 125 | 91031
PR | 101 | 09/14/18 | 340 | Donelson, Richard T | 1 | 62.5 | 21173
PR | 101 | 09/28/18 | 739 | Donelson, Richard T | 1 | 62.5 | 90883
PR | 101 | 10/19/18 | 507 | Donelson, Richard T | 1 | 62.5 | 91541
PR | 101 | 11/02/18 | 76 | Donelson, Richard T | 1 | 62.5 | 21686
PR | 101 | 11/16/18 | 513 | Donelson, Richard T | 1 | 62.5 | 21836
PR | 101 | 11/30/18 | 900 | Donelson, Richard T | 1 | 62.5 | 921983
PR | 101 | 12/07/18 | 113 | Donelson, Richard T | 1 | 62.5 | 22056
PR | 101 | 01/11/19 | 281 | Donelson, Richard T | 1 | 62.5 | 922483
PR | 101 | 01/25/19 | 786 | Donelson, Richard T | 1 | 62.5 | 922631
PR | 101 | 02/01/19 | 70 | Donelson, Richard T | 2 | 125 | 22699
PR | 101 | 02/01/19 | 71 | Gerard, Jeffrey S | 1 | 52 | 22700
PR | 101 | 02/08/19 | 227 | Gerard, Jeffrey S | 1 | 52 | 22769
PR | 101 | 02/15/19 | 389 | Gerard, Jeffrey S | 2 | 104 | 922840
PR | 101 | 03/08/19 | 314 | Donelson, Richard T | 1 | 62.5 | 923053
PR | 101 | 03/29/19 | 989 | Donelson, Richard T | 2 | 125 | 23272
PR | 101 | 03/29/19 | 990 | Gerard, Jeffrey S | 1 | 52 | 23273
PR | 101 | 04/05/19 | 152 | Gerard, Jeffrey S | 3 | 156 | 923346
PR | 101 | 04/12/19 | 398 | Gerard, Jeffrey S | 3 | 156 | 23421
PR | 101 | 04/19/19 | 597 | Gerard, Jeffrey S | 1 | 52 | 923497
PR | 101 | 04/26/19 | 812 | Donelson, Richard T | 1 | 62.5 | 23568
PR | 101 | 04/26/19 | 813 | Gerard, Jeffrey S | 4 | 220 | 23569
PR | 101 | 05/10/19 | 234 | Donelson, Richard T | 2 | 125 | 23719
PR | 101 | 05/10/19 | 235 | Gerard, Jeffrey S | 1 | 55 | 23720
PR | 101 | 05/17/19 | 468 | Gerard, Jeffrey S | 1 | 55 | 923799
PR | 101 | 05/24/19 | 681 | Gerard, Jeffrey S | 1 | 55 | 923876
PR | 101 | 05/31/19 | 952 | Donelson, Richard T | 1 | 62.5 | 923952
PR | 101 | 06/07/19 | 255 | Gerard, Jeffrey S | 1 | 55 | 924030
PR | 101 | 06/14/19 | 523 | Donelson, Richard T | 1 | 62.5 | 24103
PR | 101 | 06/14/19 | 524 | Gerard, Jeffrey S | 1 | 55 | 24104
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 4 | 250 | 24179
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 1 | 55 | 24180
PR | 101 | 06/28/19 | 911 | Gerard, Jeffrey S | 3 | 165 | 24255
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 2 | 125 | 924329
PR | 101 | 07/12/19 | 353 | Gerard, Jeffrey S | 1 | 55 | 924405
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 1 | 55 | 24485
PR | 101 | 07/26/19 | 686 | Gerard, Jeffrey S | 1 | 55 | 24635
PR | 101 | 08/02/19 | 76 | Donelson, Richard T | 2 | 125 | 924707
PR | 101 | 08/02/19 | 77 | Gerard, Jeffrey S | 1 | 55 | 924708
PR | 101 | 08/09/19 | 328 | Donelson, Richard T | 2 | 125 | 924781
PR | 101 | 08/09/19 | 329 | Gerard, Jeffrey S | 1 | 55 | 924782
PR | 101 | 08/16/19 | 636 | Donelson, Richard T | 3 | 187.5 | 924855
PR | 101 | 08/23/19 | 874 | Gerard, Jeffrey S | 1 | 55 | 924932
PR | 101 | 09/06/19 | 86 | Gerard, Jeffrey S | 2 | 110 | 925084
PR | 101 | 09/13/19 | 308 | Donelson, Richard T | 1 | 62.5 | 25157
PR | 101 | 09/13/19 | 309 | Gerard, Jeffrey S | 1 | 55 | 25158
PR | 101 | 09/27/19 | 706 | Gerard, Jeffrey S | 2 | 110 | 925311
PR | 101 | 10/04/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 25389
PR | 101 | 10/18/19 | 528 | Gerard, Jeffrey S | 1 | 55 | 25545
PR | 101 | 11/22/19 | 684 | Donelson, Richard T | 1 | 62.5 | 925923
PR | 101 | 11/22/19 | 685 | Gerard, Jeffrey S | 1 | 58 | 925924
PR | 101 | 12/06/19 | 105 | Gerard, Jeffrey S | 1 | 58 | 26077
PR | 101 | 12/13/19 | 465 | Donelson, Richard T | 3 | 187.5 | 926231
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 1 | 62.5 | 926400
PR | 101 | 02/07/20 | 102 | Donelson, Richard T | 1 | 62.5 | 26850
PR | 101 | 03/06/20 | 119 | Donelson, Richard T | 1 | 62.5 | 927163
PR | 101 | 03/20/20 | 641 | Donelson, Richard T | 1 | 62.5 | 927321
PR | 101 | 03/26/20 | 820 | Donelson, Richard T | 1 | 62.5 | 927396
PR | 101 | 03/26/20 | 821 | Gerard, Jeffrey S | 1 | 58 | 927397
PR | 101 | 04/17/20 | 288 | Donelson, Richard T | 1 | 62.5 | 927551
PR | 101 | 05/01/20 | 79 | Gerard, Jeffrey S | 1 | 58 | 927706
PR | 101 | 05/15/20 | 385 | Gerard, Jeffrey S | 1 | 58 | 927863
PR | 101 | 05/29/20 | 659 | Donelson, Richard T | 1 | 62.5 | 928002
PR | 101 | 05/29/20 | 660 | Gerard, Jeffrey S | 2 | 116 | 928003
PR | 101 | 06/05/20 | 67 | Gerard, Jeffrey S | 1 | 58 | 928056
PR | 101 | 07/10/20 | 183 | Gerard, Jeffrey S | 1 | 58 | 28342
PR | 101 | 07/17/20 | 310 | Gerard, Jeffrey S | 1 | 58 | 928390
PR | 101 | 07/24/20 | 448 | Donelson, Richard T | 1 | 62.5 | 928440
PR | 101 | 08/07/20 | 128 | Donelson, Richard T | 1 | 62.5 | 928531
PR | 101 | 08/21/20 | 459 | Donelson, Richard T | 2 | 125 | 928613
PR | 101 | 08/21/20 | 460 | Gerard, Jeffrey S | 1 | 58 | 928614
PR | 101 | 08/28/20 | 604 | Donelson, Richard T | 1 | 62.5 | 928657
PR | 101 | 09/18/20 | 330 | Donelson, Richard T | 2 | 125 | 928801
PR | 101 | 09/25/20 | 478 | Donelson, Richard T | 1 | 62.5 | 928849
PR | 101 | 10/16/20 | 339 | Donelson, Richard T | 1 | 62.5 | 928993
PR | 110 | 02/08/19 | 162 | Barnhart, Joseph N | 2 | 96 | 22704
PR | 110 | 02/22/19 | 582 | Barnhart, Joseph N | 2 | 96 | 22844
PR | 110 | 03/22/19 | 710 | Barnhart, Joseph N | 1 | 48 | 23131
PR | 110 | 04/05/19 | 83 | Barnhart, Joseph N | 2 | 96 | 23277
PR | 110 | 04/12/19 | 327 | Barnhart, Joseph N | 1 | 75 | 23351
PR | 110 | 04/12/19 | 327 | Barnhart, Joseph N | 11 | 550 | 23351
PR | 110 | 04/12/19 | 365 | Martinez Reyes, Juan C | 3 | 126 | 23389
PR | 110 | 04/12/19 | 365 | Martinez Reyes, Juan C | 3 | 84 | 23389
PR | 110 | 04/12/19 | 387 | Taylor, Evan R | 1 | 39 | 23411
PR | 110 | 04/12/19 | 387 | Taylor, Evan R | 11 | 286 | 23411
PR | 110 | 04/26/19 | 744 | Barnhart, Joseph N | 6 | 300 | 23501
PR | 110 | 04/26/19 | 782 | Martinez Reyes, Juan C | 23 | 759 | 23539
PR | 110 | 05/03/19 | 11 | Barnhart, Joseph N | 2 | 150 | 23573
PR | 110 | 05/03/19 | 11 | Barnhart, Joseph N | 7 | 350 | 23573
PR | 110 | 05/03/19 | 51 | Martinez Reyes, Juan C | 2 | 99 | 23613
PR | 110 | 05/03/19 | 51 | Martinez Reyes, Juan C | 12 | 396 | 23613
PR | 110 | 02/14/20 | 271 | Hubbard, Robert W | 4 | 216 | 26887
PR | 111 | 08/09/19 | 265 | Castro Hernandez, Jose A | 16 | 560 | 24718
PR | 111 | 08/09/19 | 281 | Gauthier, Dillon R | 16 | 272 | 24734
PR | 111 | 08/09/19 | 306 | Reed, Reuben H | 8 | 360 | 24759
PR | 111 | 10/25/19 | 592 | Barnhart, Joseph N | 1 | 50 | 25549
PR | 112 | 12/21/18 | 511 | Barnhart, Joseph N | 1 | 48 | 22202
PR | 112 | 05/17/19 | 395 | Barnhart, Joseph N | 2 | 100 | 23726
PR | 112 | 05/17/19 | 436 | Martinez Reyes, Juan C | 20 | 660 | 23767
PR | 112 | 05/24/19 | 608 | Barnhart, Joseph N | 5 | 250 | 23803
PR | 112 | 05/31/19 | 881 | Barnhart, Joseph N | 2 | 100 | 23881
PR | 112 | 05/31/19 | 922 | Martinez Reyes, Juan C | 4 | 132 | 23922
PR | 112 | 06/28/19 | 872 | Hubbard, Robert W | 15 | 750 | 24216
PR | 112 | 06/28/19 | 887 | Reed, Reuben H | 12 | 540 | 24231
PR | 112 | 07/05/19 | 12 | Barnhart, Joseph N | 1 | 50 | 24259
PR | 112 | 07/12/19 | 322 | McCabe, Thomas C | 5 | 175 | 24374
PR | 112 | 07/19/19 | 512 | Barnhart, Joseph N | 1 | 50 | 24411
PR | 112 | 07/26/19 | 661 | Reed, Reuben H | 5 | 225 | 24610
PR | 120 | 04/12/19 | 327 | Barnhart, Joseph N | 1 | 75 | 23351
PR | 120 | 04/12/19 | 327 | Barnhart, Joseph N | 3 | 150 | 23351
PR | 120 | 05/17/19 | 395 | Barnhart, Joseph N | 5 | 250 | 23726
PR | 120 | 05/17/19 | 436 | Martinez Reyes, Juan C | 4 | 132 | 23767
PR | 120 | 07/19/19 | 512 | Barnhart, Joseph N | 1 | 50 | 24411
PR | 120 | 07/19/19 | 533 | Gauthier, Dillon R | 7 | 119 | 24432
PR | 120 | 07/19/19 | 543 | Hubbard, Robert W | 2 | 100 | 24442
PR | 120 | 07/19/19 | 558 | Reed, Reuben H | 7 | 315 | 24457
PR | 120 | 08/02/19 | 13 | Castro Hernandez, Jose A | 16 | 560 | 24644
PR | 120 | 08/02/19 | 28 | Gauthier, Dillon R | 16 | 272 | 24659
PR | 120 | 08/02/19 | 38 | Hubbard, Robert W | 2 | 100 | 24669
PR | 120 | 08/02/19 | 53 | Reed, Reuben H | 7 | 315 | 24684
PR | 120 | 08/16/19 | 572 | Castro Hernandez, Jose A | 40 | 1400 | 24791
PR | 120 | 08/16/19 | 588 | Gauthier, Dillon R | 38 | 646 | 24807
PR | 120 | 08/16/19 | 613 | Reed, Reuben H | 22 | 990 | 24832
PR | 120 | 08/23/19 | 808 | Castro Hernandez, Jose A | 40 | 1400 | 24866
PR | 120 | 08/23/19 | 814 | Cruz Guzman, Joel A | 24 | 672 | 24872
PR | 120 | 08/23/19 | 824 | Gauthier, Dillon R | 22 | 374 | 24882
PR | 120 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M | 24 | 600 | 24894
PR | 120 | 08/23/19 | 850 | Reed, Reuben H | 32 | 1440 | 24908
PR | 120 | 08/23/19 | 860 | Silva Morales, Jair J | 24 | 648 | 24918
PR | 120 | 08/30/19 | 999 | Castro Hernandez, Jose A | 32 | 1120 | 24941
PR | 120 | 08/30/19 | 1005 | Cruz Guzman, Joel A | 40 | 1120 | 24947
PR | 120 | 08/30/19 | 1015 | Gauthier, Dillon R | 24 | 408 | 24957
PR | 120 | 08/30/19 | 1026 | Hubbard, Robert W | 2 | 100 | 24968
PR | 120 | 08/30/19 | 1027 | Jimenez Alvarenga, Gerson M | 32 | 800 | 24969
PR | 120 | 08/30/19 | 1041 | Reed, Reuben H | 40 | 1800 | 24983
PR | 120 | 08/30/19 | 1051 | Silva Morales, Jair J | 40 | 1080 | 24993
PR | 120 | 09/06/19 | 20 | Castro Hernandez, Jose A | 32 | 1120 | 25018
PR | 120 | 09/06/19 | 26 | Cruz Guzman, Joel A | 32 | 896 | 25024
PR | 120 | 09/06/19 | 36 | Gauthier, Dillon R | 32 | 544 | 25034
PR | 120 | 09/06/19 | 48 | Jimenez Alvarenga, Gerson M | 16 | 400 | 25046
PR | 120 | 09/06/19 | 62 | Reed, Reuben H | 32 | 1440 | 25060
PR | 120 | 09/06/19 | 72 | Silva Morales, Jair J | 32 | 864 | 25070
PR | 120 | 09/13/19 | 244 | Castro Hernandez, Jose A | 32 | 1120 | 25093
PR | 120 | 09/13/19 | 250 | Cruz Guzman, Joel A | 40 | 1120 | 25099
PR | 120 | 09/13/19 | 272 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 25121
PR | 120 | 09/13/19 | 285 | Reed, Reuben H | 25 | 1125 | 25134
PR | 120 | 09/13/19 | 295 | Silva Morales, Jair J | 40 | 1080 | 25144
PR | 120 | 09/20/19 | 481 | Castro Hernandez, Jose A | 32 | 1120 | 25167
PR | 120 | 09/20/19 | 487 | Cruz Guzman, Joel A | 32 | 896 | 25173
PR | 120 | 09/20/19 | 497 | Gauthier, Dillon R | 8 | 136 | 25183
PR | 120 | 09/20/19 | 502 | Guerrero Espinoza, Mario | 32 | 512 | 25188
PR | 120 | 09/20/19 | 509 | Hubbard, Robert W | 2 | 100 | 25195
PR | 120 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M | 32 | 800 | 25196
PR | 120 | 09/20/19 | 523 | Reed, Reuben H | 16 | 720 | 25209
PR | 120 | 09/20/19 | 533 | Silva Morales, Jair J | 32 | 864 | 25219
PR | 120 | 09/27/19 | 637 | Castro Hernandez, Jose A | 40 | 1400 | 25242
PR | 120 | 09/27/19 | 643 | Cruz Guzman, Joel A | 40 | 1120 | 25248
PR | 120 | 09/27/19 | 658 | Guerrero Espinoza, Mario | 40 | 640 | 25263
PR | 120 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M | 32 | 800 | 25272
PR | 120 | 09/27/19 | 682 | Reed, Reuben H | 32 | 1440 | 25287
PR | 120 | 09/27/19 | 692 | Silva Morales, Jair J | 40 | 1080 | 25297
PR | 120 | 10/04/19 | 13 | Castro Hernandez, Jose A | 40 | 1400 | 25320
PR | 120 | 10/04/19 | 19 | Cruz Guzman, Joel A | 8 | 224 | 25326
PR | 120 | 10/04/19 | 33 | Guerrero Espinoza, Mario | 38 | 608 | 25340
PR | 120 | 10/04/19 | 42 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 25349
PR | 120 | 10/04/19 | 58 | Reed, Reuben H | 24 | 1080 | 25365
PR | 120 | 10/04/19 | 68 | Silva Morales, Jair J | 40 | 1080 | 25375
PR | 120 | 10/11/19 | 268 | Castro Hernandez, Jose A | 40 | 1400 | 25402
PR | 120 | 10/11/19 | 274 | Cruz Guzman, Joel A | 16 | 448 | 25408
PR | 120 | 10/11/19 | 288 | Guerrero Espinoza, Mario | 40 | 640 | 25422
PR | 120 | 10/11/19 | 297 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 25431
PR | 120 | 10/11/19 | 312 | Reed, Reuben H | 24 | 1080 | 25446
PR | 120 | 10/11/19 | 323 | Silva Morales, Jair J | 24 | 648 | 25457
PR | 120 | 10/18/19 | 462 | Castro Hernandez, Jose A | 40 | 1400 | 25478
PR | 120 | 10/18/19 | 481 | Guerrero Espinoza, Mario | 32 | 512 | 25497
PR | 120 | 10/18/19 | 490 | Jimenez Alvarenga, Gerson M | 40 | 1000 | 25507
PR | 120 | 10/18/19 | 505 | Reed, Reuben H | 3 | 135 | 25522
PR | 120 | 10/18/19 | 516 | Silva Morales, Jair J | 40 | 1080 | 25533
PR | 120 | 10/25/19 | 598 | Castro Hernandez, Jose A | 37 | 1295 | 25555
PR | 120 | 10/25/19 | 616 | Guerrero Espinoza, Mario | 37 | 592 | 25573
PR | 120 | 10/25/19 | 625 | Jimenez Alvarenga, Gerson M | 37 | 925 | 25582
PR | 120 | 10/25/19 | 652 | Silva Morales, Jair J | 37 | 999 | 25609
PR | 120 | 11/01/19 | 13 | Castro Hernandez, Jose A | 40 | 1520 | 25630
PR | 120 | 11/01/19 | 25 | Frausto Mendoza, Pedro | 24 | 600 | 25642
PR | 120 | 11/01/19 | 27 | Garcia Perez, Ervey O | 40 | 720 | 25644
PR | 120 | 11/01/19 | 32 | Guerrero Espinoza, Mario | 40 | 640 | 25649
PR | 120 | 11/01/19 | 41 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 25658
PR | 120 | 11/01/19 | 57 | Reed, Reuben H | 34 | 1666 | 25674
PR | 120 | 11/01/19 | 68 | Silva Morales, Jair J | 40 | 1200 | 25685
PR | 120 | 11/08/19 | 187 | Castro Hernandez, Jose A | 40 | 1520 | 25706
PR | 120 | 11/08/19 | 199 | Frausto Mendoza, Pedro | 39 | 975 | 25718
PR | 120 | 11/08/19 | 201 | Garcia Perez, Ervey O | 40 | 720 | 25720
PR | 120 | 11/08/19 | 206 | Guerrero Espinoza, Mario | 40 | 640 | 25725
PR | 120 | 11/08/19 | 215 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 25734
PR | 120 | 11/08/19 | 231 | Reed, Reuben H | 38 | 1862 | 25750
PR | 120 | 11/08/19 | 242 | Silva Morales, Jair J | 40 | 1200 | 25761
PR | 120 | 11/15/19 | 447 | Castro Hernandez, Jose A | 32 | 1216 | 25782
PR | 120 | 11/15/19 | 459 | Frausto Mendoza, Pedro | 40 | 1000 | 25794
PR | 120 | 11/15/19 | 461 | Garcia Perez, Ervey O | 40 | 720 | 25796
PR | 120 | 11/15/19 | 466 | Guerrero Espinoza, Mario | 40 | 640 | 25802
PR | 120 | 11/15/19 | 474 | Jimenez Alvarenga, Gerson M | 32 | 896 | 25810
PR | 120 | 11/15/19 | 490 | Reed, Reuben H | 40 | 1960 | 25826
PR | 120 | 11/22/19 | 618 | Castro Hernandez, Jose A | 38 | 1444 | 25858
PR | 120 | 11/22/19 | 630 | Frausto Mendoza, Pedro | 36 | 900 | 25870
PR | 120 | 11/22/19 | 632 | Garcia Perez, Ervey O | 38 | 684 | 25872
PR | 120 | 11/22/19 | 637 | Guerrero Espinoza, Mario | 38 | 608 | 25877
PR | 120 | 11/22/19 | 645 | Jimenez Alvarenga, Gerson M | 38 | 1064 | 25885
PR | 120 | 11/22/19 | 661 | Reed, Reuben H | 30 | 1470 | 25901
PR | 120 | 11/22/19 | 672 | Silva Morales, Jair J | 6 | 180 | 25912
PR | 120 | 11/27/19 | 852 | Castro Hernandez, Jose A | 40 | 1520 | 25933
PR | 120 | 11/27/19 | 864 | Frausto Mendoza, Pedro | 38 | 950 | 25945
PR | 120 | 11/27/19 | 866 | Garcia Perez, Ervey O | 40 | 720 | 25947
PR | 120 | 11/27/19 | 871 | Guerrero Espinoza, Mario | 40 | 640 | 25952
PR | 120 | 11/27/19 | 878 | Hubbard, Robert W | 1 | 54 | 25959
PR | 120 | 11/27/19 | 879 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 25960
PR | 120 | 11/27/19 | 895 | Reed, Reuben H | 40 | 1960 | 25976
PR | 120 | 11/27/19 | 906 | Silva Morales, Jair J | 20 | 600 | 25987
PR | 120 | 12/06/19 | 38 | Castro Hernandez, Jose A | 32 | 1216 | 26010
PR | 120 | 12/06/19 | 51 | Frausto Mendoza, Pedro | 28 | 700 | 26023
PR | 120 | 12/06/19 | 53 | Garcia Perez, Ervey O | 32 | 576 | 26025
PR | 120 | 12/06/19 | 58 | Guerrero Espinoza, Mario | 32 | 512 | 26030
PR | 120 | 12/06/19 | 66 | Jimenez Alvarenga, Gerson M | 32 | 896 | 26038
PR | 120 | 12/06/19 | 82 | Reed, Reuben H | 32 | 1568 | 26054
PR | 120 | 12/13/19 | 399 | Castro Hernandez, Jose A | 32 | 1216 | 26164
PR | 120 | 12/13/19 | 412 | Frausto Mendoza, Pedro | 32 | 800 | 26177
PR | 120 | 12/13/19 | 414 | Garcia Perez, Ervey O | 40 | 720 | 26179
PR | 120 | 12/13/19 | 419 | Guerrero Espinoza, Mario | 40 | 640 | 26184
PR | 120 | 12/13/19 | 427 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26192
PR | 120 | 12/13/19 | 443 | Reed, Reuben H | 40 | 1960 | 26209
PR | 120 | 12/13/19 | 454 | Silva Morales, Jair J | 40 | 1200 | 26220
PR | 120 | 12/20/19 | 552 | Castro Hernandez, Jose A | 40 | 1520 | 26241
PR | 120 | 12/20/19 | 565 | Frausto Mendoza, Pedro | 21 | 525 | 26254
PR | 120 | 12/20/19 | 567 | Garcia Perez, Ervey O | 24 | 432 | 26256
PR | 120 | 12/20/19 | 572 | Guerrero Espinoza, Mario | 32 | 512 | 26261
PR | 120 | 12/20/19 | 580 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26269
PR | 120 | 12/20/19 | 596 | Reed, Reuben H | 40 | 1960 | 26285
PR | 120 | 12/20/19 | 607 | Silva Morales, Jair J | 16 | 480 | 26296
PR | 120 | 12/27/19 | 709 | Castro Hernandez, Jose A | 24 | 912 | 26317
PR | 120 | 12/27/19 | 715 | Cruz Guzman, Joel A | 24 | 744 | 26323
PR | 120 | 12/27/19 | 723 | Frausto Mendoza, Pedro | 9 | 225 | 26331
PR | 120 | 12/27/19 | 725 | Garcia Perez, Ervey O | 16 | 288 | 26333
PR | 120 | 12/27/19 | 730 | Guerrero Espinoza, Mario | 24 | 384 | 26338
PR | 120 | 12/27/19 | 738 | Jimenez Alvarenga, Gerson M | 24 | 672 | 26346
PR | 120 | 12/27/19 | 740 | Kinssies, Jr, John E | 8 | 280 | 26348
PR | 120 | 12/27/19 | 754 | Reed, Reuben H | 13 | 637 | 26362
PR | 120 | 12/27/19 | 765 | Silva Morales, Jair J | 8 | 240 | 26373
PR | 120 | 01/03/20 | 12 | Castro Hernandez, Jose A | 32 | 1216 | 26394
PR | 120 | 01/03/20 | 18 | Cruz Guzman, Joel A | 12 | 372 | 26401
PR | 120 | 01/03/20 | 26 | Frausto Mendoza, Pedro | 32 | 800 | 26409
PR | 120 | 01/03/20 | 28 | Garcia Perez, Ervey O | 29 | 522 | 26411
PR | 120 | 01/03/20 | 33 | Guerrero Espinoza, Mario | 12 | 192 | 26416
PR | 120 | 01/03/20 | 41 | Jimenez Alvarenga, Gerson M | 32 | 896 | 26424
PR | 120 | 01/03/20 | 57 | Reed, Reuben H | 29 | 1421 | 26440
PR | 120 | 01/10/20 | 285 | Castro Hernandez, Jose A | 40 | 1520 | 26472
PR | 120 | 01/10/20 | 291 | Cruz Guzman, Joel A | 40 | 1240 | 26478
PR | 120 | 01/10/20 | 299 | Frausto Mendoza, Pedro | 29 | 725 | 26486
PR | 120 | 01/10/20 | 301 | Garcia Perez, Ervey O | 40 | 720 | 26488
PR | 120 | 01/10/20 | 306 | Guerrero Espinoza, Mario | 40 | 640 | 26493
PR | 120 | 01/10/20 | 314 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26501
PR | 120 | 01/10/20 | 330 | Reed, Reuben H | 39 | 1911 | 26518
PR | 120 | 01/10/20 | 341 | Silva Morales, Jair J | 40 | 1200 | 26529
PR | 120 | 01/17/20 | 551 | Castro Hernandez, Jose A | 40 | 1520 | 26550
PR | 120 | 01/17/20 | 557 | Cruz Guzman, Joel A | 32 | 992 | 26556
PR | 120 | 01/17/20 | 565 | Frausto Mendoza, Pedro | 16 | 400 | 26564
PR | 120 | 01/17/20 | 567 | Garcia Perez, Ervey O | 25 | 450 | 26566
PR | 120 | 01/17/20 | 572 | Guerrero Espinoza, Mario | 24 | 384 | 26571
PR | 120 | 01/17/20 | 580 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26579
PR | 120 | 01/17/20 | 596 | Reed, Reuben H | 14 | 686 | 26595
PR | 120 | 01/17/20 | 607 | Silva Morales, Jair J | 24 | 720 | 26606
PR | 120 | 01/24/20 | 684 | Castro Hernandez, Jose A | 32 | 1216 | 26627
PR | 120 | 01/24/20 | 699 | Garcia Perez, Ervey O | 40 | 720 | 26642
PR | 120 | 01/24/20 | 712 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26655
PR | 120 | 01/24/20 | 727 | Reed, Reuben H | 24 | 1176 | 26670
PR | 120 | 01/24/20 | 738 | Silva Morales, Jair J | 32 | 960 | 26681
PR | 120 | 01/31/20 | 774 | Frausto Mendoza, Pedro | 8 | 200 | 26505
PR | 120 | 01/31/20 | 843 | Castro Hernandez, Jose A | 40 | 1520 | 26704
PR | 120 | 01/31/20 | 857 | Frausto Mendoza, Pedro | 20 | 500 | 26718
PR | 120 | 01/31/20 | 859 | Garcia Perez, Ervey O | 40 | 720 | 26720
PR | 120 | 01/31/20 | 872 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26733
PR | 120 | 01/31/20 | 888 | Reed, Reuben H | 12 | 588 | 26749
PR | 120 | 01/31/20 | 899 | Silva Morales, Jair J | 16 | 480 | 26760
PR | 120 | 02/07/20 | 34 | Castro Hernandez, Jose A | 40 | 1520 | 26782
PR | 120 | 02/07/20 | 49 | Garcia Perez, Ervey O | 40 | 720 | 26797
PR | 120 | 02/07/20 | 62 | Jimenez Alvarenga, Gerson M | 40 | 1120 | 26810
PR | 120 | 02/07/20 | 78 | Reed, Reuben H | 27 | 1323 | 26826
PR | 120 | 02/07/20 | 90 | Silva Morales, Jair J | 40 | 1200 | 26838
PR | 120 | 02/14/20 | 244 | Castro Hernandez, Jose A | 24 | 912 | 26860
PR | 120 | 02/14/20 | 250 | Cruz Guzman, Joel A | 16 | 496 | 26866
PR | 120 | 02/14/20 | 259 | Garcia Perez, Ervey O | 40 | 720 | 26875
PR | 120 | 02/14/20 | 264 | Guerrero Espinoza, Mario | 16 | 288 | 26880
PR | 120 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M | 24 | 672 | 26888
PR | 120 | 02/14/20 | 288 | Reed, Reuben H | 31 | 1519 | 26904
PR | 120 | 02/14/20 | 300 | Silva Morales, Jair J | 40 | 1200 | 26916
PR | 120 | 02/21/20 | 461 | Castro Hernandez, Jose A | 20 | 760 | 26938
PR | 120 | 02/21/20 | 467 | Cruz Guzman, Joel A | 16 | 496 | 26944
PR | 120 | 02/21/20 | 475 | Garcia Perez, Ervey O | 28 | 504 | 26952
PR | 120 | 02/21/20 | 480 | Guerrero Espinoza, Mario | 20 | 360 | 26957
PR | 120 | 02/21/20 | 504 | Reed, Reuben H | 18 | 882 | 26981
PR | 120 | 02/21/20 | 516 | Silva Morales, Jair J | 36 | 1080 | 26993
PR | 120 | 02/28/20 | 689 | Castro Hernandez, Jose A | 32 | 1216 | 27017
PR | 120 | 02/28/20 | 695 | Cruz Guzman, Joel A | 16 | 496 | 27023
PR | 120 | 02/28/20 | 704 | Garcia Perez, Ervey O | 32 | 576 | 27032
PR | 120 | 02/28/20 | 709 | Guerrero Espinoza, Mario | 16 | 288 | 27037
PR | 120 | 02/28/20 | 733 | Reed, Reuben H | 19 | 931 | 27061
PR | 120 | 02/28/20 | 745 | Silva Morales, Jair J | 26 | 780 | 27073
PR | 120 | 03/06/20 | 51 | Castro Hernandez, Jose A | 32 | 1216 | 27095
PR | 120 | 03/06/20 | 67 | Garcia Perez, Ervey O | 8 | 144 | 27111
PR | 120 | 03/06/20 | 71 | Guerrero Espinoza, Mario | 24 | 432 | 27115
PR | 120 | 03/06/20 | 95 | Reed, Reuben H | 30 | 1470 | 27139
PR | 120 | 03/06/20 | 107 | Silva Morales, Jair J | 32 | 960 | 27151
PR | 120 | 03/13/20 | 316 | Castro Hernandez, Jose A | 32 | 1216 | 27176
PR | 120 | 03/13/20 | 322 | Cruz Guzman, Joel A | 24 | 744 | 27182
PR | 120 | 03/13/20 | 359 | Reed, Reuben H | 36 | 1764 | 27220
PR | 120 | 03/13/20 | 371 | Silva Morales, Jair J | 40 | 1200 | 27232
PR | 120 | 03/20/20 | 569 | Barnhart, Joseph N | 2 | 108 | 27249
PR | 120 | 03/20/20 | 574 | Castro Hernandez, Jose A | 40 | 1520 | 27254
PR | 120 | 03/20/20 | 580 | Cruz Guzman, Joel A | 40 | 1240 | 27260
PR | 120 | 03/20/20 | 589 | Garcia Perez, Ervey O | 16 | 288 | 27269
PR | 120 | 03/20/20 | 593 | Guerrero Espinoza, Mario | 16 | 288 | 27273
PR | 120 | 03/20/20 | 617 | Reed, Reuben H | 32 | 1568 | 27297
PR | 120 | 03/20/20 | 629 | Silva Morales, Jair J | 33 | 990 | 27309
PR | 120 | 03/26/20 | 752 | Barnhart, Joseph N | 2 | 108 | 27328
PR | 120 | 03/26/20 | 757 | Castro Hernandez, Jose A | 40 | 1640 | 27333
PR | 120 | 03/26/20 | 762 | Cruz Guzman, Joel A | 40 | 1240 | 27338
PR | 120 | 03/26/20 | 771 | Garcia Perez, Ervey O | 24 | 432 | 27347
PR | 120 | 03/26/20 | 775 | Guerrero Espinoza, Mario | 24 | 432 | 27351
PR | 120 | 03/26/20 | 797 | Reed, Reuben H | 31 | 1519 | 27373
PR | 120 | 03/26/20 | 808 | Silva Morales, Jair J | 40 | 1200 | 27384
PR | 120 | 05/08/20 | 188 | Hubbard, Robert W | 1 | 54 | 27743
PR | 120 | 05/08/20 | 205 | Reed, Reuben H | 10 | 490 | 27760
PR | 120 | 05/15/20 | 317 | Castro Hernandez, Jose A | 12 | 492 | 27795
PR | 120 | 05/15/20 | 343 | Hubbard, Robert W | 4 | 216 | 27821
PR | 120 | 05/15/20 | 360 | Reed, Reuben H | 12 | 588 | 27838
PR | 120 | 05/22/20 | 472 | Castro Hernandez, Jose A | 8 | 328 | 27872
PR | 120 | 05/22/20 | 511 | Reed, Reuben H | 8 | 392 | 27911
PR | 120 | 05/29/20 | 638 | Reed, Reuben H | 4 | 196 | 27981
PR | 120 | 06/05/20 | 26 | Cruz Guzman, Joel A | 8 | 248 | 28016
PR | 120 | 06/05/20 | 52 | Reed, Reuben H | 8 | 392 | 28042
PR | 120 | 06/11/20 | 191 | Reed, Reuben H | 2 | 98 | 28091
PR | 120 | 08/07/20 | 110 | Hubbard, Robert W | 1.5 | 81 | 28513
PR | 120 | 08/07/20 | 119 | Reed, Reuben H | 7 | 343 | 28522
PR | 120 | 08/21/20 | 435 | Hubbard, Robert W | 8 | 432 | 28595
PR | 120 | 10/02/20 | 38 | Reed, Reuben H | 6 | 294 | 28886
PR | 130 | 12/20/19 | 605 | Sanders, Allen O | 2 | 108 | 26294
PR | 130 | 01/24/20 | 679 | Barnhart, Joseph N | 4.5 | 243 | 26622
PR | 130 | 01/24/20 | 736 | Sanders, Allen O | 2 | 108 | 26679
PR | 130 | 05/29/20 | 646 | Sanders, Allen O | 1 | 54 | 27989
PR | 130 | 06/19/20 | 416 | Sanders, Allen O | 2 | 108 | 28193
PR | 130 | 07/17/20 | 303 | Sanders, Allen O | 2 | 108 | 28383
PR | 130 | 07/31/20 | 537 | Sanders, Allen O | 9 | 486 | 28483
PR | 130 | 08/14/20 | 296 | Boss, Benjamin T | 32 | 576 | 28536
PR | 130 | 08/14/20 | 301 | Cruz Gonzalez, Julio C | 32 | 896 | 28541
PR | 130 | 08/14/20 | 303 | Cruz Reyes, Jose | 32 | 1024 | 28543
PR | 130 | 08/14/20 | 315 | Hubbard, Robert W | 6 | 324 | 28555
PR | 130 | 08/14/20 | 327 | Sanders, Allen O | 22.5 | 1215 | 28567
PR | 130 | 08/21/20 | 417 | Boss, Benjamin T | 16 | 288 | 28577
PR | 130 | 08/21/20 | 422 | Cruz Gonzalez, Julio C | 16 | 448 | 28582
PR | 130 | 08/21/20 | 424 | Cruz Reyes, Jose | 16 | 512 | 28584
PR | 130 | 08/21/20 | 447 | Sanders, Allen O | 17 | 918 | 28608
PR | 130 | 08/28/20 | 565 | Boss, Benjamin T | 32 | 576 | 28618
PR | 130 | 08/28/20 | 570 | Cruz Gonzalez, Julio C | 32 | 896 | 28623
PR | 130 | 08/28/20 | 572 | Cruz Reyes, Jose | 32 | 1024 | 28625
PR | 130 | 08/28/20 | 598 | Sanders, Allen O | 29 | 1566 | 28651
PR | 130 | 09/04/20 | 8 | Boss, Benjamin T | 32 | 576 | 28664
PR | 130 | 09/04/20 | 14 | Cruz Gonzalez, Julio C | 32 | 896 | 28670
PR | 130 | 09/04/20 | 16 | Cruz Reyes, Jose | 32 | 1024 | 28672
PR | 130 | 09/04/20 | 43 | Sanders, Allen O | 32 | 1728 | 28699
PR | 130 | 09/11/20 | 77 | Barnhart, Joseph N | 1 | 54 | 28711
PR | 130 | 09/11/20 | 78 | Boss, Benjamin T | 16 | 288 | 28712
PR | 130 | 09/11/20 | 84 | Cruz Gonzalez, Julio C | 32 | 896 | 28718
PR | 130 | 09/11/20 | 86 | Cruz Reyes, Jose | 32 | 1024 | 28720
PR | 130 | 09/11/20 | 113 | Sanders, Allen O | 29 | 1566 | 28747
PR | 130 | 09/18/20 | 295 | Cruz Gonzalez, Julio C | 8 | 224 | 28766
PR | 130 | 09/18/20 | 297 | Cruz Reyes, Jose | 30 | 960 | 28768
PR | 130 | 09/18/20 | 313 | McCabe, Thomas C | 1 | 39 | 28784
PR | 130 | 09/18/20 | 324 | Sanders, Allen O | 30 | 1620 | 28795
PR | 130 | 09/25/20 | 438 | Cruz Reyes, Jose | 16 | 512 | 28815
PR | 130 | 09/25/20 | 466 | Sanders, Allen O | 21 | 1134 | 28843
PR | 130 | 10/02/20 | 43 | Sanders, Allen O | 15.5 | 837 | 28891
PR | 130 | 10/09/20 | 191 | Sanders, Allen O | 5.5 | 297 | 28940
PR | 130 | 10/16/20 | 333 | Sanders, Allen O | 3 | 162 | 28987
PR | 130 | 10/23/20 | 475 | Sanders, Allen O | 3 | 162 | 29035
PR | 140 | 01/03/20 | 18 | Cruz Guzman, Joel A | 20 | 620 | 26401
PR | 140 | 01/03/20 | 33 | Guerrero Espinoza, Mario | 20 | 320 | 26416
PR | 140 | 02/07/20 | 40 | Cruz Guzman, Joel A | 8 | 248 | 26788
PR | 140 | 02/07/20 | 54 | Guerrero Espinoza, Mario | 8 | 144 | 26802
PR | 140 | 02/14/20 | 250 | Cruz Guzman, Joel A | 24 | 744 | 26866
PR | 140 | 02/14/20 | 264 | Guerrero Espinoza, Mario | 24 | 432 | 26880
PR | 140 | 02/14/20 | 271 | Hubbard, Robert W | 2 | 108 | 26887
PR | 140 | 02/28/20 | 695 | Cruz Guzman, Joel A | 16 | 496 | 27023
PR | 140 | 02/28/20 | 709 | Guerrero Espinoza, Mario | 16 | 288 | 27037
PR | 140 | 03/06/20 | 57 | Cruz Guzman, Joel A | 40 | 1240 | 27101
PR | 140 | 03/06/20 | 71 | Guerrero Espinoza, Mario | 16 | 288 | 27115
PR | 140 | 03/13/20 | 342 | Hubbard, Robert W | 1 | 54 | 27203
PR | 140 | 08/07/20 | 119 | Reed, Reuben H | 6 | 294 | 28522
PR | 141 | 08/23/19 | 840 | Lopez, Maslin A | 4 | 68 | 24898
PR | 141 | 08/23/19 | 856 | Romero Garza, Jesus I | 4 | 72 | 24914
PR | 141 | 10/04/19 | 19 | Cruz Guzman, Joel A | 32 | 896 | 25326
PR | 141 | 10/04/19 | 50 | Mackey, Cole J | 8 | 120 | 25357
PR | 141 | 10/18/19 | 505 | Reed, Reuben H | 30 | 1350 | 25522
PR | 141 | 10/25/19 | 641 | Reed, Reuben H | 36 | 1620 | 25598
PR | 141 | 11/15/19 | 501 | Silva Morales, Jair J | 40 | 1200 | 25837
PR | 141 | 11/22/19 | 661 | Reed, Reuben H | 8 | 392 | 25901
PR | 141 | 11/22/19 | 672 | Silva Morales, Jair J | 32 | 960 | 25912
PR | 141 | 11/27/19 | 906 | Silva Morales, Jair J | 12 | 360 | 25987
PR | 141 | 12/06/19 | 68 | Kinssies, Jr, John E | 8 | 280 | 26040
PR | 141 | 12/06/19 | 93 | Silva Morales, Jair J | 32 | 960 | 26065
PR | 141 | 01/03/20 | 68 | Silva Morales, Jair J | 16 | 480 | 26451
PR | 141 | 01/24/20 | 690 | Cruz Guzman, Joel A | 40 | 1240 | 26633
PR | 141 | 01/24/20 | 704 | Guerrero Espinoza, Mario | 40 | 640 | 26647
PR | 141 | 01/31/20 | 849 | Cruz Guzman, Joel A | 40 | 1240 | 26710
PR | 141 | 01/31/20 | 864 | Guerrero Espinoza, Mario | 40 | 640 | 26725
PR | 141 | 02/07/20 | 40 | Cruz Guzman, Joel A | 32 | 992 | 26788
PR | 141 | 02/07/20 | 54 | Guerrero Espinoza, Mario | 32 | 576 | 26802
PR | 141 | 02/14/20 | 244 | Castro Hernandez, Jose A | 16 | 608 | 26860
PR | 141 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M | 16 | 448 | 26888
PR | 141 | 02/21/20 | 461 | Castro Hernandez, Jose A | 16 | 608 | 26938
PR | 141 | 02/21/20 | 467 | Cruz Guzman, Joel A | 16 | 496 | 26944
PR | 141 | 02/21/20 | 480 | Guerrero Espinoza, Mario | 16 | 288 | 26957
PR | 141 | 02/21/20 | 504 | Reed, Reuben H | 6 | 294 | 26981
PR | 141 | 03/06/20 | 67 | Garcia Perez, Ervey O | 32 | 576 | 27111
PR | 141 | 03/13/20 | 331 | Garcia Perez, Ervey O | 40 | 720 | 27191
PR | 141 | 03/13/20 | 335 | Guerrero Espinoza, Mario | 32 | 576 | 27195
PR | 141 | 03/20/20 | 589 | Garcia Perez, Ervey O | 24 | 432 | 27269
PR | 141 | 03/20/20 | 593 | Guerrero Espinoza, Mario | 24 | 432 | 27273
PR | 141 | 03/26/20 | 771 | Garcia Perez, Ervey O | 16 | 288 | 27347
PR | 141 | 03/26/20 | 775 | Guerrero Espinoza, Mario | 16 | 288 | 27351
PR | 141 | 05/22/20 | 472 | Castro Hernandez, Jose A | 8 | 328 | 27872
PR | 141 | 05/22/20 | 494 | Hubbard, Robert W | 2 | 108 | 27894
PR | 141 | 05/22/20 | 511 | Reed, Reuben H | 8 | 392 | 27911
PR | 141 | 07/17/20 | 293 | McCabe, Thomas C | 4 | 156 | 28373
PR | 141 | 07/17/20 | 298 | Reed, Reuben H | 4 | 196 | 28378
PR | 141 | 07/24/20 | 431 | McCabe, Thomas C | 16 | 624 | 28423
PR | 141 | 07/24/20 | 436 | Reed, Reuben H | 16 | 784 | 28428
PR | 141 | 08/28/20 | 584 | Hubbard, Robert W | 3 | 162 | 28637
PR | 142 | 11/08/19 | 214 | Hubbard, Robert W | 2 | 108 | 25733
PR | 142 | 11/22/19 | 644 | Hubbard, Robert W | 5 | 270 | 25884
PR | 142 | 11/22/19 | 647 | Kinssies, Jr, John E | 13 | 455 | 25887
PR | 142 | 11/27/19 | 878 | Hubbard, Robert W | 2 | 108 | 25959
PR | 142 | 11/27/19 | 881 | Kinssies, Jr, John E | 30.5 | 1067.5 | 25962
PR | 142 | 12/06/19 | 65 | Hubbard, Robert W | 4 | 216 | 26037
PR | 142 | 12/06/19 | 68 | Kinssies, Jr, John E | 8 | 280 | 26040
PR | 142 | 12/13/19 | 426 | Hubbard, Robert W | 6 | 324 | 26191
PR | 142 | 12/13/19 | 429 | Kinssies, Jr, John E | 39 | 1365 | 26194
PR | 142 | 12/20/19 | 579 | Hubbard, Robert W | 4 | 216 | 26268
PR | 142 | 12/20/19 | 582 | Kinssies, Jr, John E | 40 | 1400 | 26271
PR | 142 | 12/27/19 | 740 | Kinssies, Jr, John E | 4 | 140 | 26348
PR | 142 | 01/03/20 | 40 | Hubbard, Robert W | 2 | 108 | 26423
PR | 142 | 01/03/20 | 43 | Kinssies, Jr, John E | 18.5 | 647.5 | 26426
PR | 142 | 01/10/20 | 313 | Hubbard, Robert W | 2 | 108 | 26500
PR | 142 | 01/10/20 | 316 | Kinssies, Jr, John E | 29.5 | 1032.5 | 26503
PR | 142 | 01/17/20 | 582 | Kinssies, Jr, John E | 16 | 560 | 26581
PR | 142 | 01/24/20 | 711 | Hubbard, Robert W | 4 | 216 | 26654
PR | 142 | 02/07/20 | 61 | Hubbard, Robert W | 2 | 108 | 26809
PR | 142 | 02/07/20 | 64 | Kinssies, Jr, John E | 24 | 840 | 26812
PR | 142 | 02/14/20 | 271 | Hubbard, Robert W | 2 | 108 | 26887
PR | 142 | 02/14/20 | 274 | Kinssies, Jr, John E | 40 | 1400 | 26890
PR | 142 | 03/13/20 | 322 | Cruz Guzman, Joel A | 8 | 248 | 27182
PR | 142 | 05/22/20 | 494 | Hubbard, Robert W | 1 | 54 | 27894
PR | 142 | 07/17/20 | 293 | McCabe, Thomas C | 4 | 156 | 28373
PR | 142 | 07/17/20 | 298 | Reed, Reuben H | 4 | 196 | 28378
PR | 142 | 09/11/20 | 77 | Barnhart, Joseph N | 1 | 54 | 28711
PR | 142 | 09/18/20 | 309 | Hubbard, Robert W | 6 | 324 | 28780
PR | 142 | 09/18/20 | 313 | McCabe, Thomas C | 5 | 195 | 28784
PR | 142 | 10/02/20 | 28 | Hubbard, Robert W | 6 | 324 | 28876
AP | 210 | 04/23/19 | 679 | Rosen Supply Kirkland |  | 1802.17 | 4265671-00
GL | 210 | 04/24/19 | 690 | Req 5905 |  | 118.92
AP | 210 | 05/02/19 | 143 | Rosen Supply Kirkland |  | 459.2 | 4265970-00
GL | 210 | 05/13/19 | 301 | Req 5190 |  | 49.58
AP | 210 | 05/15/19 | 375 | Rosen Supply Kirkland |  | 185.38 | 4266645-00
GL | 210 | 01/30/20 | 914 | Richard Anderson |  | 63.36
GL | 211 | 07/10/19 | 195 | Req 6119 |  | 135.8
GL | 211 | 08/20/19 | 678 | Req 6271 |  | -167.72
GL | 211 | 08/20/19 | 687 | Req 6253 |  | 695.5
GL | 211 | 09/06/19 | 106 | Req 6312 |  | 919.58
GL | 211 | 09/06/19 | 108 | Req 6311 |  | 200.62
GL | 211 | 09/16/19 | 350 | Req 6309 |  | 1113.4
AP | 211 | 09/30/19 | 760 | Rosen Supply Kirkland |  | 3775.45 | 4272691-00
GL | 211 | 10/07/19 | 120 | Req 6381 |  | 995.34
AP | 211 | 10/16/19 | 450 | Rosen Supply Kirkland |  | 360.28 | 4273162-00
AP | 211 | 11/11/19 | 334 | Ferguson Enterprises, Inc. #3007 |  | 289.65 | 7647878
GL | 211 | 11/13/19 | 394 | Req 6563 |  | 886.98
GL | 211 | 11/19/19 | 580 | Req 6583 |  | 639.1
AP | 211 | 11/22/19 | 711 | Rosen Supply Kirkland |  | 4425.2 | 4274457-00
AP | 211 | 12/05/19 | 114 | Rosen Supply Kirkland |  | 79.42 | 4273162-01
GL | 211 | 12/06/19 | 139 | Req 6611 |  | 107.76
AP | 211 | 12/10/19 | 263 | Rosen Supply Kirkland |  | 175.83 | 4275178-00
GL | 211 | 12/20/19 | 658 | Req 6695 |  | 105.41
AP | 211 | 01/08/20 | 266 | Rosen Supply Kirkland |  | 1524.05 | 4277091-00
AP | 211 | 01/10/20 | 456 | Rosen Supply Kirkland |  | 64.34 | 4277137-00
AP | 211 | 01/13/20 | 522 | Rosen Supply Kirkland |  | 95.85 | 4277234-00
GL | 211 | 01/31/20 | 939 | Req 5765 |  | 216.38
AP | 211 | 02/14/20 | 341 | Rosen Supply Kirkland |  | 12.3 | 4277134-00
AP | 211 | 02/14/20 | 342 | Rosen Supply Kirkland |  | 17.36 | 4277137-01
AP | 211 | 02/18/20 | 412 | Rosen Supply Kirkland |  | 720.36 | 4278547-00
GL | 211 | 02/24/20 | 565 | Req 6806 |  | 378.32
GL | 211 | 03/10/20 | 240 | Req 6879 |  | 96.26
AP | 211 | 03/18/20 | 552 | Rosen Supply Kirkland |  | 117.54 | 4279959-00
GL | 211 | 03/26/20 | 845 | Req 6937 |  | -120.79
GL | 211 | 04/29/20 | 450 | Req 6954 |  | 45.22
GL | 211 | 05/14/20 | 390 | Req 7006 |  | -494.4
GL | 211 | 06/22/20 | 444 | Req 7116 |  | -693.3
GL | 211 | 06/22/20 | 449 | Req 7111 |  | -322.11
GL | 211 | 08/04/20 | 29 | Req 7186 |  | 16.36
GL | 211 | 08/27/20 | 557 | Req 7267 |  | -35.79
GL | 211 | 09/24/20 | 520 | Req 7311 |  | -2.77
GL | 211 | 09/24/20 | 523 | Req 7324 |  | 55.34
GL | 212 | 06/05/19 | 123 | Req 5235 |  | 2537.04
GL | 212 | 07/10/19 | 196 | Req 6118 |  | 2826.69
GL | 212 | 08/20/19 | 679 | Req 6270 |  | -454.1
GL | 212 | 08/20/19 | 697 | Req 6284 |  | -64.31
AP | 220 | 08/30/19 | 1085 | Rosen Supply Kirkland |  | 2997.43 | 4271615-00
AP | 220 | 08/30/19 | 1086 | Rosen Supply Kirkland |  | 2200 | 4271652-00
AP | 220 | 08/31/19 | 1109 | Rosen Supply Kirkland |  | 3182.96 | 4270642-00
AP | 220 | 09/01/19 | 396 | Rosen Supply Kirkland |  | -2200 | 4271652-00A
AP | 220 | 09/01/19 | 397 | Rosen Supply Kirkland |  | 2220 | 4271652-00B
GL | 220 | 09/06/19 | 105 | Req 6313 |  | 1137.55
GL | 220 | 09/06/19 | 107 | Req 6310 |  | 972.84
GL | 220 | 09/16/19 | 351 | Req 6315 |  | 352.71
AP | 220 | 09/23/19 | 583 | Rosen Supply Kirkland |  | -143.95 | 4271982-00
AP | 220 | 09/25/19 | 623 | Rosen Supply Kirkland |  | 44.95 | 4272396-00
GL | 220 | 10/07/19 | 101 | Req 6389 |  | -29.7
GL | 220 | 10/07/19 | 121 | Req 6382 |  | 2060.98
GL | 220 | 10/07/19 | 122 | Req 6383 |  | 687.74
GL | 220 | 10/15/19 | 409 | Req 6045 |  | -20
AP | 220 | 10/23/19 | 582 | Consolidated Supply Co. |  | 4636.19 | S009455892.001
GL | 220 | 11/13/19 | 395 | Req 6562 |  | 80.5
GL | 220 | 11/13/19 | 396 | Req 6561 |  | 3259.64
AP | 220 | 11/16/19 | 547 | Rosen Supply Kirkland |  | 2474.57 | 4273661-00
GL | 220 | 11/19/19 | 569 | Req 6574 |  | 607.6
AP | 220 | 11/20/19 | 595 | Rosen Supply Kirkland |  | 134.22 | 4274107-00
AP | 220 | 11/22/19 | 727 | Rosen Supply Kirkland |  | 80.74 | 4274641-00
GL | 220 | 12/06/19 | 135 | Req 6607 |  | 888.15
GL | 220 | 12/06/19 | 160 | Req 6596 |  | 980.5
AP | 220 | 12/10/19 | 270 | Rosen Supply Kirkland |  | 11.36 | 4274641-01
AP | 220 | 12/11/19 | 376 | Consolidated Supply Co. |  | 2274.02 | S009528233.001
AP | 220 | 12/13/19 | 534 | Rosen Supply Kirkland |  | 609.79 | 4275923-00
GL | 220 | 12/20/19 | 654 | Req 6691 |  | 587.77
GL | 220 | 12/27/19 | 809 | Req 6730 |  | -19.8
GL | 220 | 01/31/20 | 938 | Req 5762 |  | 288.46
GL | 220 | 02/24/20 | 564 | Req 6807 |  | 784.01
AP | 220 | 02/26/20 | 670 | Rosen Supply Kirkland |  | 116.17 | 4278938-00
AP | 220 | 02/28/20 | 782 | Ferguson Enterprises, Inc. #3007 |  | 346.42 | 8006526
AP | 220 | 02/28/20 | 783 | Ferguson Enterprises, Inc. #3007 |  | 7.94 | T006526
AP | 220 | 03/01/20 | 10 | Ferguson Enterprises, Inc. #3007 |  | -7.94 | T006526A
AP | 220 | 03/01/20 | 11 | Ferguson Enterprises, Inc. #3007 |  | 8.74 | T006526B
GL | 220 | 03/10/20 | 242 | Req 3881 |  | 151.55
AP | 220 | 03/18/20 | 553 | Rosen Supply Kirkland |  | 27.72 | 4280056-00
GL | 220 | 04/29/20 | 449 | Req 6953 |  | 57.46
GL | 220 | 05/27/20 | 581 | Req 7036 |  | 52.37
AP | 220 | 06/09/20 | 147 | Rosen Supply Kirkland |  | 1.88 | 4282264-00
GL | 220 | 08/04/20 | 28 | Req 7185 |  | 41.36
AP | 220 | 08/05/20 | 61 | Rosen Supply Kirkland |  | 78.23 | 4284420-00
AP | 230 | 02/27/19 | 757 | Rosen Supply Kirkland |  | 13965 | 4262043-00
GL | 230 | 05/13/19 | 302 | Req 5189 |  | 190.72
AP | 230 | 05/15/19 | 370 | Rosen Supply Kirkland |  | 1948.1 | 4264093-00
GL | 230 | 06/05/19 | 122 | Req 5236 |  | 260.75
AP | 230 | 06/08/19 | 317 | Rosen Supply Kirkland |  | 51.76 | 4268252-00
AP | 230 | 08/14/19 | 560 | Keller Supply Company |  | 2211.19 | S013277932.001
GL | 230 | 08/20/19 | 696 | Req 6285 |  | -371.2
AP | 230 | 09/17/19 | 406 | California Hydronics Corp |  | 4581 | SIN026967
AP | 230 | 09/17/19 | 407 | California Hydronics Corp |  | 17248 | SIN028044
GL | 230 | 10/07/19 | 124 | Req 6385 |  | 2745.14
AP | 230 | 10/21/19 | 547 | Best Bath Systems |  | 21192.8 | 10380
GL | 230 | 11/13/19 | 393 | Req 6564 |  | 1901.95
AP | 230 | 11/25/19 | 824 | Best Bath Systems |  | 16424.42 | 11034
GL | 230 | 12/06/19 | 136 | Req 6608 |  | 1113.28
GL | 230 | 12/06/19 | 151 | Req 6624 |  | 15.6
AP | 230 | 12/10/19 | 277 | Rosen Supply Kirkland |  | 2228.86 | 4275174-00
AP | 230 | 12/10/19 | 278 | Rosen Supply Kirkland |  | 2944.28 | 4275174-01
AP | 230 | 12/11/19 | 387 | Keller Supply Company |  | 776.79 | S013314212.001
GL | 230 | 12/20/19 | 657 | Req 6694 |  | 473.24
AP | 230 | 01/03/20 | 100 | Rosen Supply Kirkland |  | 364 | 4276285-00
AP | 230 | 01/13/20 | 531 | Rosen Supply Kirkland |  | 859.56 | 4276285-01
GL | 230 | 01/31/20 | 935 | Req 5766 |  | 1145.16
GL | 230 | 03/10/20 | 243 | Req 6882 |  | 50.61
GL | 230 | 03/13/20 | 398 | Req 6874 |  | 294.68
GL | 230 | 03/26/20 | 844 | Req 6936 |  | -107.95
GL | 230 | 04/29/20 | 447 | Req 6951 |  | 303.93
AP | 230 | 05/06/20 | 128 | Mechanical Sales, Inc. |  | 442 | 707971
AP | 230 | 05/06/20 | 136 | Mechanical Sales, Inc. |  | -442 | 707971A
AP | 230 | 05/06/20 | 137 | Mechanical Sales, Inc. |  | 464.14 | 707971B
GL | 230 | 05/27/20 | 582 | Req 7035 |  | 20.4
GL | 230 | 05/31/20 | 682 | Req 7068 |  | 10.67
GL | 230 | 06/22/20 | 446 | Req 7114 |  | -144.94
AP | 230 | 08/11/20 | 276 | Keller Supply Company |  | 7738.38 | S013366976.002
AP | 230 | 08/11/20 | 277 | Keller Supply Company |  | 7962.52 | S013367002.001
AP | 230 | 08/11/20 | 278 | Keller Supply Company |  | 7962.52 | S013367011.001
AP | 230 | 08/14/20 | 357 | Rosen Supply Kirkland |  | 82.15 | 4284856-00
GL | 230 | 08/17/20 | 382 | Req 7228 |  | 2555.96
AP | 230 | 08/26/20 | 522 | Keller Supply Company |  | 7962.52 | S013367016.001
AP | 230 | 08/26/20 | 523 | Keller Supply Company |  | 1584.36 | S014530634.001
GL | 230 | 08/27/20 | 559 | Req 7265 |  | -174
AP | 230 | 09/11/20 | 151 | Keller Supply Company |  | 7250.48 | S013367022.001
AP | 230 | 09/11/20 | 152 | Keller Supply Company |  | 7613.9 | S013367029.001
GL | 230 | 09/14/20 | 204 | Req 7277 |  | 1968.05
AP | 230 | 09/15/20 | 215 | Capital One Credit Card |  | 5.2 | 081120J
AP | 230 | 09/15/20 | 222 | Capital One Credit Card |  | 28.71 | 081920A
AP | 230 | 09/15/20 | 224 | Capital One Credit Card |  | 1 | 082720A1
AP | 230 | 09/15/20 | 225 | Capital One Credit Card |  | 7.36 | 082720A2
AP | 230 | 09/15/20 | 226 | Capital One Credit Card |  | 28.71 | 082820A
AP | 230 | 09/15/20 | 229 | Capital One Credit Card |  | 18.39 | 090120A
AP | 230 | 09/16/20 | 263 | Consolidated Supply Co. |  | 282.07 | S009561664.001
AP | 230 | 09/16/20 | 272 | Keller Supply Company |  | 1221.17 | S013728613.001
GL | 230 | 09/24/20 | 522 | Req 7309 |  | -149.04
GL | 230 | 09/24/20 | 525 | Req 7322 |  | 617.5
AP | 230 | 10/05/20 | 102 | Ferguson Enterprises, Inc. #3007 |  | 104.4 | 8646092
AP | 230 | 10/07/20 | 124 | Rosen Supply Kirkland |  | 31.88 | 4286868-00
GL | 230 | 10/15/20 | 348 | Req 7368 |  | 290.75
AP | 230 | 10/19/20 | 404 | Keller Supply Company |  | 127.29 | S014592682.001
GL | 240 | 10/07/19 | 125 | Req 6386 |  | 106.35
GL | 240 | 12/06/19 | 138 | Req 6610 |  | 190.49
AP | 240 | 01/06/20 | 149 | Ferguson Enterprises, Inc. #3007 |  | 1104.42 | 7828543
GL | 240 | 01/31/20 | 931 | Req 5767 |  | 116.54
AP | 240 | 02/10/20 | 145 | Rosen Supply Kirkland |  | 529.14 | 4277628-00
GL | 240 | 02/24/20 | 563 | Req 6808 |  | 136.84
AP | 240 | 02/26/20 | 666 | Rosen Supply Kirkland |  | 343.87 | 4278897-00
AP | 240 | 02/29/20 | 814 | Rosen Supply Kirkland |  | 9.7 | 4279207-00
AP | 240 | 03/03/20 | 6 | Rosen Supply Kirkland |  | 82.12 | 4279006-02
AP | 240 | 03/03/20 | 7 | Rosen Supply Kirkland |  | 12.47 | 4279409-00
GL | 240 | 03/10/20 | 241 | Req 6880 |  | 324.7
AP | 240 | 03/18/20 | 551 | Rosen Supply Kirkland |  | 107.45 | 4279841-00
GL | 240 | 04/29/20 | 448 | Req 6952 |  | 47.46
GL | 240 | 05/27/20 | 580 | Req 7037 |  | 15.81
AP | 240 | 08/04/20 | 41 | Rosen Supply Kirkland |  | 38.17 | 4284228-00
AP | 240 | 08/05/20 | 60 | Rosen Supply Kirkland |  | 37.73 | 7160053-00
AP | 240 | 08/10/20 | 265 | Rosen Supply Kirkland |  | 49.64 | 4284228-01
GL | 240 | 08/17/20 | 384 | Req 7230 |  | 304.98
AP | 240 | 08/26/20 | 539 | Rosen Supply Kirkland |  | 43.04 | 4284228-02
GL | 241 | 10/07/19 | 123 | Req 6384 |  | 1204.33
GL | 241 | 11/13/19 | 392 | Req 6567 |  | 782.32
GL | 241 | 12/06/19 | 157 | Req 6595 |  | 416.2
AP | 241 | 12/11/19 | 376 | Consolidated Supply Co. |  | 1390.2 | S009528233.001
AP | 241 | 12/12/19 | 504 | Keller Supply Company |  | 1308.61 | S013680445.001
AP | 241 | 12/12/19 | 505 | Keller Supply Company |  | -1308.61 | S013698218.001
GL | 241 | 12/20/19 | 656 | Req 6693 |  | 116.6
GL | 241 | 01/31/20 | 936 | Req 5764 |  | 908.92
GL | 241 | 01/31/20 | 937 | Req 5763 |  | 2729.83
AP | 241 | 02/05/20 | 17 | Consolidated Supply Co. |  | 1275.28 | S009614551.001
AP | 241 | 02/10/20 | 141 | Consolidated Supply Co. |  | 1143.12 | S009634478.001
GL | 241 | 02/24/20 | 566 | Req 6805 |  | 2441.4
AP | 241 | 02/26/20 | 669 | Rosen Supply Kirkland |  | 951.42 | 4278700-00
AP | 241 | 02/26/20 | 671 | Rosen Supply Kirkland |  | 1506.24 | 4278965-00
AP | 241 | 03/18/20 | 554 | Rosen Supply Kirkland |  | 64.08 | 4280058-00
AP | 241 | 03/25/20 | 523 | Consolidated Supply Co. |  | 223.5 | S009687736.001
AP | 241 | 03/25/20 | 529 | Ferguson Enterprises, Inc. #3007 |  | 501.82 | 8074999
GL | 241 | 03/26/20 | 847 | Req 6940 |  | -520.68
AP | 241 | 03/27/20 | 867 | Rosen Supply Kirkland |  | 613.2 | 4280418-00
AP | 241 | 04/21/20 | 302 | Rosen Supply Kirkland |  | -55.68 | 4279710-00
GL | 241 | 04/29/20 | 446 | Req 6950 |  | 913.83
GL | 241 | 05/27/20 | 583 | Req 7034 |  | 343.13
GL | 241 | 05/31/20 | 683 | Req 7069 |  | 59
GL | 241 | 06/22/20 | 445 | Req 7115 |  | -1194.94
GL | 241 | 08/04/20 | 27 | Req 7184 |  | 87.2
GL | 241 | 08/17/20 | 383 | Req 7229 |  | 19.44
GL | 241 | 09/24/20 | 524 | Req 7323 |  | 176.49
GL | 241 | 09/24/20 | 528 | Req 7310 |  | -2.82
GL | 242 | 09/06/19 | 104 | Req 6314 |  | 105
AP | 242 | 11/20/19 | 596 | Rosen Supply Kirkland |  | 26.39 | 4274181-00
GL | 242 | 11/30/19 | 953 | Req 6565 |  | 2742.2
GL | 242 | 11/30/19 | 954 | Req 6566 |  | 452.13
GL | 242 | 12/06/19 | 137 | Req 6609 |  | 454.4
GL | 242 | 12/06/19 | 152 | Req 6623 |  | 936.62
GL | 242 | 12/06/19 | 159 | Req 6597 |  | -23.42
AP | 242 | 12/12/19 | 489 | Ferguson Enterprises, Inc. #3007 |  | 14018.55 | 7743810
GL | 242 | 12/20/19 | 655 | Req 6692 |  | 315.15
AP | 242 | 01/06/20 | 147 | Ferguson Enterprises, Inc. #3007 |  | 15.93 | 7793394
AP | 242 | 01/06/20 | 148 | Ferguson Enterprises, Inc. #3007 |  | 734.17 | 7793394-1
AP | 242 | 01/06/20 | 150 | Ferguson Enterprises, Inc. #3007 |  | 1241.36 | 7829400
AP | 242 | 01/06/20 | 151 | Ferguson Enterprises, Inc. #3007 |  | 420.81 | 7829400-1
AP | 242 | 01/06/20 | 152 | Ferguson Enterprises, Inc. #3007 |  | 155.14 | 7837747
AP | 242 | 01/13/20 | 505 | Ferguson Enterprises, Inc. #3007 |  | 83.45 | 7863191
AP | 242 | 01/13/20 | 537 | Ferguson Enterprises, Inc. #3007 |  | 189.67 | 7877470
AP | 242 | 01/13/20 | 538 | Ferguson Enterprises, Inc. #3007 |  | -134.55 | CM845679
AP | 242 | 01/14/20 | 495 | Ferguson Enterprises, Inc. #3007 |  | 505.02 | 7846779
AP | 242 | 01/14/20 | 496 | Ferguson Enterprises, Inc. #3007 |  | 194.27 | 7846779-1
GL | 242 | 01/31/20 | 940 | Req 5768 |  | 48.97
AP | 242 | 02/10/20 | 158 | Ferguson Enterprises, Inc. #3007 |  | -1032.53 | CM857236
GL | 242 | 02/24/20 | 562 | Req 6809 |  | 799.05
AP | 242 | 02/28/20 | 781 | Ferguson Enterprises, Inc. #3007 |  | 199.26 | 7963541
GL | 242 | 05/26/20 | 571 | Req 7028 |  | -1252.97
GL | 242 | 05/26/20 | 572 | Req 7027 |  | -3147.29
GL | 242 | 08/27/20 | 558 | Req 7266 |  | -393.56
AP | 242 | 09/11/20 | 157 | Rosen Supply Kirkland |  | 26.8 | 4285567-00
AP | 600 | 09/25/20 | 502 | Mechanical Resource Services, Inc. |  | 5000 | 16901-5678
AP | 601 | 10/01/18 | 20 | Franklin Engineering |  | 2132.25 | 7107
AP | 601 | 10/16/18 | 658 | Franklin Engineering |  | 6964.5 | 7132
AP | 601 | 11/29/18 | 822 | Franklin Engineering |  | 3565 | 7157
AP | 601 | 12/10/18 | 142 | DRSi |  | 127.9 | 476914
AP | 601 | 01/03/19 | 91 | Franklin Engineering |  | 1686 | 7199
AP | 601 | 02/27/19 | 745 | Franklin Engineering |  | 436 | 7285
AP | 601 | 03/20/19 | 698 | Franklin Engineering |  | 1383 | 7296
AP | 601 | 06/24/19 | 752 | Franklin Engineering |  | 1838 | 7407
AP | 601 | 07/17/20 | 344 | Franklin Engineering |  | 533 | 7778
AP | 601 | 08/10/20 | 198 | Capital One Credit Card |  | 540.67 | 061520R1
AP | 602 | 03/09/20 | 152 | H&E Equipment Services, Inc. |  | 520.07 | 95042229
AP | 602 | 03/24/20 | 716 | H&E Equipment Services, Inc. |  | 104.6 | 95066392
AP | 603 | 11/30/18 | 941 | Capital One Credit Card |  | 210 | 113018A
AP | 603 | 11/30/18 | 942 | Capital One Credit Card |  | 210 | 113018B
AP | 603 | 11/30/18 | 943 | Capital One Credit Card |  | 3477 | 113018C
AP | 603 | 12/31/18 | 812 | Capital One Credit Card |  | 201 | 120318J1
AP | 603 | 03/01/19 | 104 | Capital One Credit Card |  | 603 | 013119J1
AP | 603 | 06/12/20 | 285 | Capital One Credit Card |  | 50 | 052920J
AP | 607 | 12/31/18 | 813 | Capital One Credit Card |  | 17.16 | 120318J2
AP | 607 | 03/01/19 | 105 | Capital One Credit Card |  | 12.26 | 013119J2
AP | 607 | 04/30/19 | 964 | Capital One Credit Card |  | 552.22 | 032819R2
AP | 607 | 04/30/19 | 979 | Capital One Credit Card |  | 524.92 | 041919R5
AP | 607 | 06/05/19 | 80 | Capital One Credit Card |  | 524.92 | 051619R4
AP | 607 | 07/10/19 | 245 | Capital One Credit Card |  | 524.92 | 061619R4
AP | 607 | 08/01/19 | 413 | Capital One Credit Card |  | 524.92 | 071519R2
AP | 607 | 09/10/19 | 211 | Capital One Credit Card |  | 524.92 | 081619R2
AP | 607 | 10/01/19 | 220 | Capital One Credit Card |  | 7.36 | 091019J
AP | 607 | 10/01/19 | 253 | Capital One Credit Card |  | 524.92 | 091619R2
AP | 607 | 11/21/19 | 781 | Capital One Credit Card |  | 524.92 | 101619R2
AP | 607 | 01/08/20 | 197 | Capital One Credit Card |  | 7.36 | 111919J
AP | 607 | 01/08/20 | 204 | Capital One Credit Card |  | 3.68 | 112319RH
AP | 607 | 01/08/20 | 217 | Capital One Credit Card |  | 524.92 | 111619R1
AP | 607 | 01/10/20 | 434 | Capital One Credit Card |  | 524.92 | 121619R2
AP | 607 | 03/09/20 | 211 | Capital One Credit Card |  | 524.92 | 011620R2
AP | 607 | 03/25/20 | 499 | Capital One Credit Card |  | 524.92 | 021620R3
AP | 607 | 04/15/20 | 193 | Capital One Credit Card |  | 524.92 | 031620R1
AP | 607 | 06/08/20 | 115 | Capital One Credit Card |  | 524.92 | 041620R1
AP | 607 | 06/12/20 | 298 | Capital One Credit Card |  | 540.67 | 051520R1
AP | 607 | 08/10/20 | 242 | Capital One Credit Card |  | 540.67 | 071520R1
AP | 607 | 09/15/20 | 228 | Capital One Credit Card |  | 18.39 | 083120A
AP | 607 | 09/15/20 | 232 | Capital One Credit Card |  | 540.67 | 081520R1
PR | 995 | 09/07/18 | 105 | Donelson, Richard T |  | 55.44
PR | 995 | 09/14/18 | 340 | Donelson, Richard T |  | 27.72
PR | 995 | 09/28/18 | 739 | Donelson, Richard T |  | 27.72
PR | 995 | 10/19/18 | 507 | Donelson, Richard T |  | 27.72
PR | 995 | 11/02/18 | 76 | Donelson, Richard T |  | 27.72
PR | 995 | 11/16/18 | 513 | Donelson, Richard T |  | 27.72
PR | 995 | 11/30/18 | 900 | Donelson, Richard T |  | 27.72
PR | 995 | 12/07/18 | 113 | Donelson, Richard T |  | 27.72
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/21/18 | 511 | Barnhart, Joseph N |  | 21.29
PR | 995 | 01/11/19 | 281 | Donelson, Richard T |  | 27.72
PR | 995 | 01/25/19 | 786 | Donelson, Richard T |  | 27.72
PR | 995 | 02/01/19 | 70 | Donelson, Richard T |  | 55.44
PR | 995 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 162 | Barnhart, Joseph N |  | 42.58
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/22/19 | 582 | Barnhart, Joseph N |  | 42.58
PR | 995 | 03/08/19 | 314 | Donelson, Richard T |  | 27.72
PR | 995 | 03/22/19 | 710 | Barnhart, Joseph N |  | 21.29
PR | 995 | 03/29/19 | 989 | Donelson, Richard T |  | 55.44
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/05/19 | 83 | Barnhart, Joseph N |  | 42.58
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 33.26
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 33.26
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 243.93
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 66.53
PR | 995 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 55.88
PR | 995 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 37.25
PR | 995 | 04/12/19 | 387 | Taylor, Evan R |  | 17.3
PR | 995 | 04/12/19 | 387 | Taylor, Evan R |  | 126.84
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/26/19 | 744 | Barnhart, Joseph N |  | 133.05
PR | 995 | 04/26/19 | 782 | Martinez Reyes, Juan C |  | 336.62
PR | 995 | 04/26/19 | 812 | Donelson, Richard T |  | 27.72
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 97.57
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/03/19 | 11 | Barnhart, Joseph N |  | 66.53
PR | 995 | 05/03/19 | 11 | Barnhart, Joseph N |  | 155.23
PR | 995 | 05/03/19 | 51 | Martinez Reyes, Juan C |  | 43.91
PR | 995 | 05/03/19 | 51 | Martinez Reyes, Juan C |  | 175.63
PR | 995 | 05/10/19 | 234 | Donelson, Richard T |  | 55.44
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/17/19 | 395 | Barnhart, Joseph N |  | 110.88
PR | 995 | 05/17/19 | 395 | Barnhart, Joseph N |  | 44.35
PR | 995 | 05/17/19 | 436 | Martinez Reyes, Juan C |  | 292.71
PR | 995 | 05/17/19 | 436 | Martinez Reyes, Juan C |  | 58.54
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/24/19 | 608 | Barnhart, Joseph N |  | 105.88
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 05/31/19 | 881 | Barnhart, Joseph N |  | 42.35
PR | 995 | 05/31/19 | 922 | Martinez Reyes, Juan C |  | 55.9
PR | 995 | 05/31/19 | 952 | Donelson, Richard T |  | 26.47
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 26.47
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 105.88
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/28/19 | 872 | Hubbard, Robert W |  | 317.63
PR | 995 | 06/28/19 | 887 | Reed, Reuben H |  | 228.69
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 07/05/19 | 12 | Barnhart, Joseph N |  | 21.18
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 52.94
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/12/19 | 322 | McCabe, Thomas C |  | 74.11
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/19/19 | 512 | Barnhart, Joseph N |  | 21.18
PR | 995 | 07/19/19 | 512 | Barnhart, Joseph N |  | 21.18
PR | 995 | 07/19/19 | 533 | Gauthier, Dillon R |  | 50.4
PR | 995 | 07/19/19 | 543 | Hubbard, Robert W |  | 42.35
PR | 995 | 07/19/19 | 558 | Reed, Reuben H |  | 133.4
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 07/26/19 | 661 | Reed, Reuben H |  | 95.29
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/02/19 | 13 | Castro Hernandez, Jose A |  | 237.16
PR | 995 | 08/02/19 | 28 | Gauthier, Dillon R |  | 115.19
PR | 995 | 08/02/19 | 38 | Hubbard, Robert W |  | 42.35
PR | 995 | 08/02/19 | 53 | Reed, Reuben H |  | 133.4
PR | 995 | 08/02/19 | 76 | Donelson, Richard T |  | 52.94
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 237.16
PR | 995 | 08/09/19 | 281 | Gauthier, Dillon R |  | 115.19
PR | 995 | 08/09/19 | 306 | Reed, Reuben H |  | 152.46
PR | 995 | 08/09/19 | 328 | Donelson, Richard T |  | 52.94
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/16/19 | 572 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 08/16/19 | 588 | Gauthier, Dillon R |  | 273.58
PR | 995 | 08/16/19 | 613 | Reed, Reuben H |  | 419.27
PR | 995 | 08/16/19 | 636 | Donelson, Richard T |  | 79.41
PR | 995 | 08/23/19 | 808 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 08/23/19 | 814 | Cruz Guzman, Joel A |  | 284.59
PR | 995 | 08/23/19 | 824 | Gauthier, Dillon R |  | 158.39
PR | 995 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M |  | 254.1
PR | 995 | 08/23/19 | 840 | Lopez, Maslin A |  | 28.8
PR | 995 | 08/23/19 | 850 | Reed, Reuben H |  | 609.84
PR | 995 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 30.49
PR | 995 | 08/23/19 | 860 | Silva Morales, Jair J |  | 274.43
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 08/30/19 | 999 | Castro Hernandez, Jose A |  | 474.32
PR | 995 | 08/30/19 | 1005 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 08/30/19 | 1015 | Gauthier, Dillon R |  | 172.79
PR | 995 | 08/30/19 | 1026 | Hubbard, Robert W |  | 42.35
PR | 995 | 08/30/19 | 1027 | Jimenez Alvarenga, Gerson M |  | 338.8
PR | 995 | 08/30/19 | 1041 | Reed, Reuben H |  | 762.3
PR | 995 | 08/30/19 | 1051 | Silva Morales, Jair J |  | 457.38
PR | 995 | 09/06/19 | 20 | Castro Hernandez, Jose A |  | 474.32
PR | 995 | 09/06/19 | 26 | Cruz Guzman, Joel A |  | 379.46
PR | 995 | 09/06/19 | 36 | Gauthier, Dillon R |  | 230.38
PR | 995 | 09/06/19 | 48 | Jimenez Alvarenga, Gerson M |  | 169.4
PR | 995 | 09/06/19 | 62 | Reed, Reuben H |  | 609.84
PR | 995 | 09/06/19 | 72 | Silva Morales, Jair J |  | 365.9
PR | 995 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/13/19 | 244 | Castro Hernandez, Jose A |  | 474.32
PR | 995 | 09/13/19 | 250 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 09/13/19 | 272 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 09/13/19 | 285 | Reed, Reuben H |  | 476.44
PR | 995 | 09/13/19 | 295 | Silva Morales, Jair J |  | 457.38
PR | 995 | 09/13/19 | 308 | Donelson, Richard T |  | 26.47
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 09/20/19 | 481 | Castro Hernandez, Jose A |  | 474.32
PR | 995 | 09/20/19 | 487 | Cruz Guzman, Joel A |  | 379.46
PR | 995 | 09/20/19 | 497 | Gauthier, Dillon R |  | 57.6
PR | 995 | 09/20/19 | 502 | Guerrero Espinoza, Mario |  | 216.83
PR | 995 | 09/20/19 | 509 | Hubbard, Robert W |  | 42.35
PR | 995 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M |  | 338.8
PR | 995 | 09/20/19 | 523 | Reed, Reuben H |  | 304.92
PR | 995 | 09/20/19 | 533 | Silva Morales, Jair J |  | 365.9
PR | 995 | 09/27/19 | 637 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 09/27/19 | 643 | Cruz Guzman, Joel A |  | 474.32
PR | 995 | 09/27/19 | 658 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M |  | 338.8
PR | 995 | 09/27/19 | 682 | Reed, Reuben H |  | 609.84
PR | 995 | 09/27/19 | 692 | Silva Morales, Jair J |  | 457.38
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/04/19 | 13 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 10/04/19 | 19 | Cruz Guzman, Joel A |  | 379.46
PR | 995 | 10/04/19 | 19 | Cruz Guzman, Joel A |  | 94.86
PR | 995 | 10/04/19 | 33 | Guerrero Espinoza, Mario |  | 257.49
PR | 995 | 10/04/19 | 42 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 10/04/19 | 50 | Mackey, Cole J |  | 50.82
PR | 995 | 10/04/19 | 58 | Reed, Reuben H |  | 457.38
PR | 995 | 10/04/19 | 68 | Silva Morales, Jair J |  | 457.38
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/11/19 | 268 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 10/11/19 | 274 | Cruz Guzman, Joel A |  | 189.73
PR | 995 | 10/11/19 | 288 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 10/11/19 | 297 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 10/11/19 | 312 | Reed, Reuben H |  | 457.38
PR | 995 | 10/11/19 | 323 | Silva Morales, Jair J |  | 274.43
PR | 995 | 10/18/19 | 462 | Castro Hernandez, Jose A |  | 592.9
PR | 995 | 10/18/19 | 481 | Guerrero Espinoza, Mario |  | 216.83
PR | 995 | 10/18/19 | 490 | Jimenez Alvarenga, Gerson M |  | 423.5
PR | 995 | 10/18/19 | 505 | Reed, Reuben H |  | 571.73
PR | 995 | 10/18/19 | 505 | Reed, Reuben H |  | 57.17
PR | 995 | 10/18/19 | 516 | Silva Morales, Jair J |  | 457.38
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 10/25/19 | 592 | Barnhart, Joseph N |  | 21.18
PR | 995 | 10/25/19 | 598 | Castro Hernandez, Jose A |  | 548.43
PR | 995 | 10/25/19 | 616 | Guerrero Espinoza, Mario |  | 250.71
PR | 995 | 10/25/19 | 625 | Jimenez Alvarenga, Gerson M |  | 391.74
PR | 995 | 10/25/19 | 641 | Reed, Reuben H |  | 686.07
PR | 995 | 10/25/19 | 652 | Silva Morales, Jair J |  | 423.08
PR | 995 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 11/01/19 | 13 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 11/01/19 | 25 | Frausto Mendoza, Pedro |  | 254.1
PR | 995 | 11/01/19 | 27 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 11/01/19 | 32 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 11/01/19 | 41 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 11/01/19 | 57 | Reed, Reuben H |  | 705.55
PR | 995 | 11/01/19 | 68 | Silva Morales, Jair J |  | 508.2
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 26.47
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/08/19 | 187 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 11/08/19 | 199 | Frausto Mendoza, Pedro |  | 412.91
PR | 995 | 11/08/19 | 201 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 11/08/19 | 206 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 11/08/19 | 214 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/08/19 | 215 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 11/08/19 | 231 | Reed, Reuben H |  | 788.56
PR | 995 | 11/08/19 | 242 | Silva Morales, Jair J |  | 508.2
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/15/19 | 447 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 11/15/19 | 459 | Frausto Mendoza, Pedro |  | 423.5
PR | 995 | 11/15/19 | 461 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 11/15/19 | 466 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 11/15/19 | 474 | Jimenez Alvarenga, Gerson M |  | 379.46
PR | 995 | 11/15/19 | 490 | Reed, Reuben H |  | 830.06
PR | 995 | 11/15/19 | 501 | Silva Morales, Jair J |  | 508.2
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/22/19 | 618 | Castro Hernandez, Jose A |  | 611.53
PR | 995 | 11/22/19 | 630 | Frausto Mendoza, Pedro |  | 381.15
PR | 995 | 11/22/19 | 632 | Garcia Perez, Ervey O |  | 289.67
PR | 995 | 11/22/19 | 637 | Guerrero Espinoza, Mario |  | 257.49
PR | 995 | 11/22/19 | 644 | Hubbard, Robert W |  | 114.35
PR | 995 | 11/22/19 | 645 | Jimenez Alvarenga, Gerson M |  | 450.6
PR | 995 | 11/22/19 | 647 | Kinssies, Jr, John E |  | 192.69
PR | 995 | 11/22/19 | 661 | Reed, Reuben H |  | 622.55
PR | 995 | 11/22/19 | 661 | Reed, Reuben H |  | 166.01
PR | 995 | 11/22/19 | 672 | Silva Morales, Jair J |  | 406.56
PR | 995 | 11/22/19 | 672 | Silva Morales, Jair J |  | 76.23
PR | 995 | 11/22/19 | 684 | Donelson, Richard T |  | 26.47
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/27/19 | 852 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 11/27/19 | 864 | Frausto Mendoza, Pedro |  | 402.33
PR | 995 | 11/27/19 | 866 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 11/27/19 | 871 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 11/27/19 | 878 | Hubbard, Robert W |  | 45.74
PR | 995 | 11/27/19 | 878 | Hubbard, Robert W |  | 22.87
PR | 995 | 11/27/19 | 879 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 11/27/19 | 881 | Kinssies, Jr, John E |  | 452.09
PR | 995 | 11/27/19 | 895 | Reed, Reuben H |  | 830.06
PR | 995 | 11/27/19 | 906 | Silva Morales, Jair J |  | 152.46
PR | 995 | 11/27/19 | 906 | Silva Morales, Jair J |  | 254.1
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/06/19 | 38 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 12/06/19 | 51 | Frausto Mendoza, Pedro |  | 296.45
PR | 995 | 12/06/19 | 53 | Garcia Perez, Ervey O |  | 243.94
PR | 995 | 12/06/19 | 58 | Guerrero Espinoza, Mario |  | 216.83
PR | 995 | 12/06/19 | 65 | Hubbard, Robert W |  | 91.48
PR | 995 | 12/06/19 | 66 | Jimenez Alvarenga, Gerson M |  | 379.46
PR | 995 | 12/06/19 | 68 | Kinssies, Jr, John E |  | 118.58
PR | 995 | 12/06/19 | 68 | Kinssies, Jr, John E |  | 118.58
PR | 995 | 12/06/19 | 82 | Reed, Reuben H |  | 664.05
PR | 995 | 12/06/19 | 93 | Silva Morales, Jair J |  | 406.56
PR | 995 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/13/19 | 399 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 12/13/19 | 412 | Frausto Mendoza, Pedro |  | 338.8
PR | 995 | 12/13/19 | 414 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 12/13/19 | 419 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 12/13/19 | 426 | Hubbard, Robert W |  | 137.21
PR | 995 | 12/13/19 | 427 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 12/13/19 | 429 | Kinssies, Jr, John E |  | 578.08
PR | 995 | 12/13/19 | 443 | Reed, Reuben H |  | 830.06
PR | 995 | 12/13/19 | 454 | Silva Morales, Jair J |  | 508.2
PR | 995 | 12/13/19 | 465 | Donelson, Richard T |  | 79.41
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/20/19 | 552 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 12/20/19 | 565 | Frausto Mendoza, Pedro |  | 222.34
PR | 995 | 12/20/19 | 567 | Garcia Perez, Ervey O |  | 182.95
PR | 995 | 12/20/19 | 572 | Guerrero Espinoza, Mario |  | 216.83
PR | 995 | 12/20/19 | 579 | Hubbard, Robert W |  | 91.48
PR | 995 | 12/20/19 | 580 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 12/20/19 | 582 | Kinssies, Jr, John E |  | 592.9
PR | 995 | 12/20/19 | 596 | Reed, Reuben H |  | 830.06
PR | 995 | 12/20/19 | 605 | Sanders, Allen O |  | 45.74
PR | 995 | 12/20/19 | 607 | Silva Morales, Jair J |  | 203.28
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/27/19 | 709 | Castro Hernandez, Jose A |  | 386.23
PR | 995 | 12/27/19 | 715 | Cruz Guzman, Joel A |  | 315.08
PR | 995 | 12/27/19 | 723 | Frausto Mendoza, Pedro |  | 95.29
PR | 995 | 12/27/19 | 725 | Garcia Perez, Ervey O |  | 121.97
PR | 995 | 12/27/19 | 730 | Guerrero Espinoza, Mario |  | 162.62
PR | 995 | 12/27/19 | 738 | Jimenez Alvarenga, Gerson M |  | 284.59
PR | 995 | 12/27/19 | 740 | Kinssies, Jr, John E |  | 118.58
PR | 995 | 12/27/19 | 740 | Kinssies, Jr, John E |  | 59.29
PR | 995 | 12/27/19 | 754 | Reed, Reuben H |  | 269.77
PR | 995 | 12/27/19 | 765 | Silva Morales, Jair J |  | 101.64
PR | 995 | 01/03/20 | 12 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 01/03/20 | 18 | Cruz Guzman, Joel A |  | 262.57
PR | 995 | 01/03/20 | 18 | Cruz Guzman, Joel A |  | 157.54
PR | 995 | 01/03/20 | 26 | Frausto Mendoza, Pedro |  | 338.8
PR | 995 | 01/03/20 | 28 | Garcia Perez, Ervey O |  | 221.07
PR | 995 | 01/03/20 | 33 | Guerrero Espinoza, Mario |  | 135.52
PR | 995 | 01/03/20 | 33 | Guerrero Espinoza, Mario |  | 81.31
PR | 995 | 01/03/20 | 40 | Hubbard, Robert W |  | 45.74
PR | 995 | 01/03/20 | 41 | Jimenez Alvarenga, Gerson M |  | 379.46
PR | 995 | 01/03/20 | 43 | Kinssies, Jr, John E |  | 274.22
PR | 995 | 01/03/20 | 57 | Reed, Reuben H |  | 601.79
PR | 995 | 01/03/20 | 68 | Silva Morales, Jair J |  | 203.28
PR | 995 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/10/20 | 285 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 01/10/20 | 291 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 01/10/20 | 299 | Frausto Mendoza, Pedro |  | 307.04
PR | 995 | 01/10/20 | 301 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 01/10/20 | 306 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 01/10/20 | 313 | Hubbard, Robert W |  | 45.74
PR | 995 | 01/10/20 | 314 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 01/10/20 | 316 | Kinssies, Jr, John E |  | 437.26
PR | 995 | 01/10/20 | 330 | Reed, Reuben H |  | 809.31
PR | 995 | 01/10/20 | 341 | Silva Morales, Jair J |  | 508.2
PR | 995 | 01/17/20 | 551 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 01/17/20 | 557 | Cruz Guzman, Joel A |  | 420.11
PR | 995 | 01/17/20 | 565 | Frausto Mendoza, Pedro |  | 169.4
PR | 995 | 01/17/20 | 567 | Garcia Perez, Ervey O |  | 190.58
PR | 995 | 01/17/20 | 572 | Guerrero Espinoza, Mario |  | 162.62
PR | 995 | 01/17/20 | 580 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 01/17/20 | 582 | Kinssies, Jr, John E |  | 237.16
PR | 995 | 01/17/20 | 596 | Reed, Reuben H |  | 290.52
PR | 995 | 01/17/20 | 607 | Silva Morales, Jair J |  | 304.92
PR | 995 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 36.84
PR | 995 | 01/24/20 | 679 | Barnhart, Joseph N |  | 102.91
PR | 995 | 01/24/20 | 684 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 01/24/20 | 690 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 01/24/20 | 699 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 01/24/20 | 704 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 01/24/20 | 711 | Hubbard, Robert W |  | 91.48
PR | 995 | 01/24/20 | 712 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 01/24/20 | 727 | Reed, Reuben H |  | 498.04
PR | 995 | 01/24/20 | 736 | Sanders, Allen O |  | 45.74
PR | 995 | 01/24/20 | 738 | Silva Morales, Jair J |  | 406.56
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 26.47
PR | 995 | 01/31/20 | 774 | Frausto Mendoza, Pedro |  | 84.7
PR | 995 | 01/31/20 | 843 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 01/31/20 | 849 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 01/31/20 | 857 | Frausto Mendoza, Pedro |  | 211.75
PR | 995 | 01/31/20 | 859 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 01/31/20 | 864 | Guerrero Espinoza, Mario |  | 271.04
PR | 995 | 01/31/20 | 872 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 01/31/20 | 888 | Reed, Reuben H |  | 249.02
PR | 995 | 01/31/20 | 899 | Silva Morales, Jair J |  | 203.28
PR | 995 | 02/07/20 | 34 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 02/07/20 | 40 | Cruz Guzman, Joel A |  | 420.11
PR | 995 | 02/07/20 | 40 | Cruz Guzman, Joel A |  | 105.03
PR | 995 | 02/07/20 | 49 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 02/07/20 | 54 | Guerrero Espinoza, Mario |  | 243.94
PR | 995 | 02/07/20 | 54 | Guerrero Espinoza, Mario |  | 60.98
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/07/20 | 62 | Jimenez Alvarenga, Gerson M |  | 474.32
PR | 995 | 02/07/20 | 64 | Kinssies, Jr, John E |  | 355.74
PR | 995 | 02/07/20 | 78 | Reed, Reuben H |  | 560.29
PR | 995 | 02/07/20 | 90 | Silva Morales, Jair J |  | 508.2
PR | 995 | 02/07/20 | 102 | Donelson, Richard T |  | 26.47
PR | 995 | 02/14/20 | 244 | Castro Hernandez, Jose A |  | 386.23
PR | 995 | 02/14/20 | 244 | Castro Hernandez, Jose A |  | 257.49
PR | 995 | 02/14/20 | 250 | Cruz Guzman, Joel A |  | 315.08
PR | 995 | 02/14/20 | 250 | Cruz Guzman, Joel A |  | 210.06
PR | 995 | 02/14/20 | 259 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 02/14/20 | 264 | Guerrero Espinoza, Mario |  | 182.95
PR | 995 | 02/14/20 | 264 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 45.74
PR | 995 | 02/14/20 | 271 | Hubbard, Robert W |  | 91.48
PR | 995 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M |  | 284.59
PR | 995 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M |  | 189.73
PR | 995 | 02/14/20 | 274 | Kinssies, Jr, John E |  | 592.9
PR | 995 | 02/14/20 | 288 | Reed, Reuben H |  | 643.3
PR | 995 | 02/14/20 | 300 | Silva Morales, Jair J |  | 508.2
PR | 995 | 02/21/20 | 461 | Castro Hernandez, Jose A |  | 321.86
PR | 995 | 02/21/20 | 461 | Castro Hernandez, Jose A |  | 257.49
PR | 995 | 02/21/20 | 467 | Cruz Guzman, Joel A |  | 210.06
PR | 995 | 02/21/20 | 467 | Cruz Guzman, Joel A |  | 210.06
PR | 995 | 02/21/20 | 475 | Garcia Perez, Ervey O |  | 213.44
PR | 995 | 02/21/20 | 480 | Guerrero Espinoza, Mario |  | 152.46
PR | 995 | 02/21/20 | 480 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 02/21/20 | 504 | Reed, Reuben H |  | 373.53
PR | 995 | 02/21/20 | 504 | Reed, Reuben H |  | 124.51
PR | 995 | 02/21/20 | 516 | Silva Morales, Jair J |  | 457.38
PR | 995 | 02/28/20 | 689 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 02/28/20 | 695 | Cruz Guzman, Joel A |  | 210.06
PR | 995 | 02/28/20 | 695 | Cruz Guzman, Joel A |  | 210.06
PR | 995 | 02/28/20 | 704 | Garcia Perez, Ervey O |  | 243.94
PR | 995 | 02/28/20 | 709 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 02/28/20 | 709 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 02/28/20 | 733 | Reed, Reuben H |  | 394.28
PR | 995 | 02/28/20 | 745 | Silva Morales, Jair J |  | 330.33
PR | 995 | 03/06/20 | 51 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 03/06/20 | 57 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 03/06/20 | 67 | Garcia Perez, Ervey O |  | 243.94
PR | 995 | 03/06/20 | 67 | Garcia Perez, Ervey O |  | 60.98
PR | 995 | 03/06/20 | 71 | Guerrero Espinoza, Mario |  | 182.95
PR | 995 | 03/06/20 | 71 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 03/06/20 | 95 | Reed, Reuben H |  | 622.55
PR | 995 | 03/06/20 | 107 | Silva Morales, Jair J |  | 406.56
PR | 995 | 03/06/20 | 119 | Donelson, Richard T |  | 26.47
PR | 995 | 03/13/20 | 316 | Castro Hernandez, Jose A |  | 514.98
PR | 995 | 03/13/20 | 322 | Cruz Guzman, Joel A |  | 105.03
PR | 995 | 03/13/20 | 322 | Cruz Guzman, Joel A |  | 315.08
PR | 995 | 03/13/20 | 331 | Garcia Perez, Ervey O |  | 304.92
PR | 995 | 03/13/20 | 335 | Guerrero Espinoza, Mario |  | 243.94
PR | 995 | 03/13/20 | 342 | Hubbard, Robert W |  | 22.87
PR | 995 | 03/13/20 | 359 | Reed, Reuben H |  | 747.05
PR | 995 | 03/13/20 | 371 | Silva Morales, Jair J |  | 508.2
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 45.74
PR | 995 | 03/20/20 | 574 | Castro Hernandez, Jose A |  | 643.72
PR | 995 | 03/20/20 | 580 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 03/20/20 | 589 | Garcia Perez, Ervey O |  | 182.95
PR | 995 | 03/20/20 | 589 | Garcia Perez, Ervey O |  | 121.97
PR | 995 | 03/20/20 | 593 | Guerrero Espinoza, Mario |  | 182.95
PR | 995 | 03/20/20 | 593 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 03/20/20 | 617 | Reed, Reuben H |  | 664.05
PR | 995 | 03/20/20 | 629 | Silva Morales, Jair J |  | 419.27
PR | 995 | 03/20/20 | 641 | Donelson, Richard T |  | 26.47
PR | 995 | 03/26/20 | 752 | Barnhart, Joseph N |  | 45.74
PR | 995 | 03/26/20 | 757 | Castro Hernandez, Jose A |  | 694.54
PR | 995 | 03/26/20 | 762 | Cruz Guzman, Joel A |  | 525.14
PR | 995 | 03/26/20 | 771 | Garcia Perez, Ervey O |  | 182.95
PR | 995 | 03/26/20 | 771 | Garcia Perez, Ervey O |  | 121.97
PR | 995 | 03/26/20 | 775 | Guerrero Espinoza, Mario |  | 182.95
PR | 995 | 03/26/20 | 775 | Guerrero Espinoza, Mario |  | 121.97
PR | 995 | 03/26/20 | 797 | Reed, Reuben H |  | 643.3
PR | 995 | 03/26/20 | 808 | Silva Morales, Jair J |  | 508.2
PR | 995 | 03/26/20 | 820 | Donelson, Richard T |  | 26.47
PR | 995 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 04/17/20 | 288 | Donelson, Richard T |  | 26.47
PR | 995 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 05/08/20 | 188 | Hubbard, Robert W |  | 22.87
PR | 995 | 05/08/20 | 205 | Reed, Reuben H |  | 207.52
PR | 995 | 05/15/20 | 317 | Castro Hernandez, Jose A |  | 208.36
PR | 995 | 05/15/20 | 343 | Hubbard, Robert W |  | 91.48
PR | 995 | 05/15/20 | 360 | Reed, Reuben H |  | 249.02
PR | 995 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 05/22/20 | 472 | Castro Hernandez, Jose A |  | 138.91
PR | 995 | 05/22/20 | 472 | Castro Hernandez, Jose A |  | 138.91
PR | 995 | 05/22/20 | 494 | Hubbard, Robert W |  | 22.87
PR | 995 | 05/22/20 | 494 | Hubbard, Robert W |  | 45.74
PR | 995 | 05/22/20 | 511 | Reed, Reuben H |  | 166.01
PR | 995 | 05/22/20 | 511 | Reed, Reuben H |  | 166.01
PR | 995 | 05/29/20 | 638 | Reed, Reuben H |  | 83.01
PR | 995 | 05/29/20 | 646 | Sanders, Allen O |  | 22.87
PR | 995 | 05/29/20 | 659 | Donelson, Richard T |  | 26.47
PR | 995 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 06/05/20 | 26 | Cruz Guzman, Joel A |  | 105.03
PR | 995 | 06/05/20 | 52 | Reed, Reuben H |  | 166.01
PR | 995 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/11/20 | 191 | Reed, Reuben H |  | 41.5
PR | 995 | 06/19/20 | 416 | Sanders, Allen O |  | 45.74
PR | 995 | 07/10/20 | 183 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/17/20 | 293 | McCabe, Thomas C |  | 66.07
PR | 995 | 07/17/20 | 293 | McCabe, Thomas C |  | 66.07
PR | 995 | 07/17/20 | 298 | Reed, Reuben H |  | 83.01
PR | 995 | 07/17/20 | 298 | Reed, Reuben H |  | 83.01
PR | 995 | 07/17/20 | 303 | Sanders, Allen O |  | 45.74
PR | 995 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/24/20 | 431 | McCabe, Thomas C |  | 264.26
PR | 995 | 07/24/20 | 436 | Reed, Reuben H |  | 332.02
PR | 995 | 07/24/20 | 448 | Donelson, Richard T |  | 26.47
PR | 995 | 07/31/20 | 537 | Sanders, Allen O |  | 205.82
PR | 995 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/07/20 | 110 | Hubbard, Robert W |  | 34.3
PR | 995 | 08/07/20 | 119 | Reed, Reuben H |  | 124.51
PR | 995 | 08/07/20 | 119 | Reed, Reuben H |  | 145.26
PR | 995 | 08/07/20 | 128 | Donelson, Richard T |  | 26.47
PR | 995 | 08/14/20 | 296 | Boss, Benjamin T |  | 243.94
PR | 995 | 08/14/20 | 301 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 08/14/20 | 303 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 08/14/20 | 315 | Hubbard, Robert W |  | 137.21
PR | 995 | 08/14/20 | 327 | Sanders, Allen O |  | 514.55
PR | 995 | 08/21/20 | 417 | Boss, Benjamin T |  | 121.97
PR | 995 | 08/21/20 | 422 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 08/21/20 | 424 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 08/21/20 | 435 | Hubbard, Robert W |  | 182.95
PR | 995 | 08/21/20 | 447 | Sanders, Allen O |  | 388.77
PR | 995 | 08/21/20 | 459 | Donelson, Richard T |  | 52.94
PR | 995 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/28/20 | 565 | Boss, Benjamin T |  | 243.94
PR | 995 | 08/28/20 | 570 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 08/28/20 | 572 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 08/28/20 | 584 | Hubbard, Robert W |  | 68.61
PR | 995 | 08/28/20 | 598 | Sanders, Allen O |  | 663.2
PR | 995 | 08/28/20 | 604 | Donelson, Richard T |  | 26.47
PR | 995 | 09/04/20 | 8 | Boss, Benjamin T |  | 243.94
PR | 995 | 09/04/20 | 14 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 09/04/20 | 16 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 09/04/20 | 43 | Sanders, Allen O |  | 731.81
PR | 995 | 09/11/20 | 77 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/11/20 | 77 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/11/20 | 78 | Boss, Benjamin T |  | 121.97
PR | 995 | 09/11/20 | 84 | Cruz Gonzalez, Julio C |  | 379.46
PR | 995 | 09/11/20 | 86 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 09/11/20 | 113 | Sanders, Allen O |  | 663.2
PR | 995 | 09/18/20 | 295 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 09/18/20 | 297 | Cruz Reyes, Jose |  | 406.56
PR | 995 | 09/18/20 | 309 | Hubbard, Robert W |  | 137.21
PR | 995 | 09/18/20 | 313 | McCabe, Thomas C |  | 82.58
PR | 995 | 09/18/20 | 313 | McCabe, Thomas C |  | 16.52
PR | 995 | 09/18/20 | 324 | Sanders, Allen O |  | 686.07
PR | 995 | 09/18/20 | 330 | Donelson, Richard T |  | 52.94
PR | 995 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 09/25/20 | 438 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 09/25/20 | 466 | Sanders, Allen O |  | 480.25
PR | 995 | 09/25/20 | 478 | Donelson, Richard T |  | 26.47
PR | 995 | 10/02/20 | 28 | Hubbard, Robert W |  | 137.21
PR | 995 | 10/02/20 | 38 | Reed, Reuben H |  | 124.51
PR | 995 | 10/02/20 | 43 | Sanders, Allen O |  | 354.47
PR | 995 | 10/09/20 | 191 | Sanders, Allen O |  | 125.78
PR | 995 | 10/16/20 | 333 | Sanders, Allen O |  | 68.61
PR | 995 | 10/16/20 | 339 | Donelson, Richard T |  | 26.47
PR | 995 | 10/23/20 | 475 | Sanders, Allen O |  | 68.61
PR | 998 | 09/07/18 | 105 | Donelson, Richard T |  | 9.56
PR | 998 | 09/14/18 | 340 | Donelson, Richard T |  | 4.78
PR | 998 | 09/28/18 | 739 | Donelson, Richard T |  | 4.78
PR | 998 | 10/19/18 | 507 | Donelson, Richard T |  | 4.78
PR | 998 | 11/02/18 | 76 | Donelson, Richard T |  | 4.78
PR | 998 | 11/16/18 | 513 | Donelson, Richard T |  | 4.78
PR | 998 | 11/30/18 | 900 | Donelson, Richard T |  | 4.78
PR | 998 | 12/07/18 | 113 | Donelson, Richard T |  | 4.78
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/21/18 | 511 | Barnhart, Joseph N |  | 3.67
PR | 998 | 01/11/19 | 281 | Donelson, Richard T |  | 4.78
PR | 998 | 01/25/19 | 786 | Donelson, Richard T |  | 4.78
PR | 998 | 02/01/19 | 70 | Donelson, Richard T |  | 9.56
PR | 998 | 02/01/19 | 71 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 162 | Barnhart, Joseph N |  | 7.34
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/22/19 | 582 | Barnhart, Joseph N |  | 7.34
PR | 998 | 03/08/19 | 314 | Donelson, Richard T |  | 4.78
PR | 998 | 03/22/19 | 710 | Barnhart, Joseph N |  | 3.67
PR | 998 | 03/29/19 | 989 | Donelson, Richard T |  | 9.56
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/05/19 | 83 | Barnhart, Joseph N |  | 7.34
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 5.74
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 5.74
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 42.08
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 11.48
PR | 998 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 9.64
PR | 998 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 6.43
PR | 998 | 04/12/19 | 387 | Taylor, Evan R |  | 2.98
PR | 998 | 04/12/19 | 387 | Taylor, Evan R |  | 21.88
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/26/19 | 744 | Barnhart, Joseph N |  | 22.95
PR | 998 | 04/26/19 | 782 | Martinez Reyes, Juan C |  | 58.06
PR | 998 | 04/26/19 | 812 | Donelson, Richard T |  | 4.78
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/03/19 | 11 | Barnhart, Joseph N |  | 11.48
PR | 998 | 05/03/19 | 11 | Barnhart, Joseph N |  | 26.78
PR | 998 | 05/03/19 | 51 | Martinez Reyes, Juan C |  | 7.57
PR | 998 | 05/03/19 | 51 | Martinez Reyes, Juan C |  | 30.29
PR | 998 | 05/10/19 | 234 | Donelson, Richard T |  | 9.56
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/17/19 | 395 | Barnhart, Joseph N |  | 19.13
PR | 998 | 05/17/19 | 395 | Barnhart, Joseph N |  | 7.65
PR | 998 | 05/17/19 | 436 | Martinez Reyes, Juan C |  | 50.49
PR | 998 | 05/17/19 | 436 | Martinez Reyes, Juan C |  | 10.1
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/24/19 | 608 | Barnhart, Joseph N |  | 19.13
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/31/19 | 881 | Barnhart, Joseph N |  | 7.65
PR | 998 | 05/31/19 | 922 | Martinez Reyes, Juan C |  | 10.1
PR | 998 | 05/31/19 | 952 | Donelson, Richard T |  | 4.78
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 4.78
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 19.13
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/28/19 | 872 | Hubbard, Robert W |  | 57.38
PR | 998 | 06/28/19 | 887 | Reed, Reuben H |  | 41.31
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/05/19 | 12 | Barnhart, Joseph N |  | 3.83
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 9.56
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/12/19 | 322 | McCabe, Thomas C |  | 13.39
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/19/19 | 512 | Barnhart, Joseph N |  | 3.83
PR | 998 | 07/19/19 | 512 | Barnhart, Joseph N |  | 3.83
PR | 998 | 07/19/19 | 533 | Gauthier, Dillon R |  | 9.1
PR | 998 | 07/19/19 | 543 | Hubbard, Robert W |  | 7.65
PR | 998 | 07/19/19 | 558 | Reed, Reuben H |  | 24.1
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 07/26/19 | 661 | Reed, Reuben H |  | 17.21
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/02/19 | 13 | Castro Hernandez, Jose A |  | 42.84
PR | 998 | 08/02/19 | 28 | Gauthier, Dillon R |  | 20.81
PR | 998 | 08/02/19 | 38 | Hubbard, Robert W |  | 7.65
PR | 998 | 08/02/19 | 53 | Reed, Reuben H |  | 24.1
PR | 998 | 08/02/19 | 76 | Donelson, Richard T |  | 9.56
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/09/19 | 265 | Castro Hernandez, Jose A |  | 42.84
PR | 998 | 08/09/19 | 281 | Gauthier, Dillon R |  | 20.81
PR | 998 | 08/09/19 | 306 | Reed, Reuben H |  | 27.54
PR | 998 | 08/09/19 | 328 | Donelson, Richard T |  | 9.56
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/16/19 | 572 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 08/16/19 | 588 | Gauthier, Dillon R |  | 49.42
PR | 998 | 08/16/19 | 613 | Reed, Reuben H |  | 75.74
PR | 998 | 08/16/19 | 636 | Donelson, Richard T |  | 14.34
PR | 998 | 08/23/19 | 808 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 08/23/19 | 814 | Cruz Guzman, Joel A |  | 51.41
PR | 998 | 08/23/19 | 824 | Gauthier, Dillon R |  | 28.61
PR | 998 | 08/23/19 | 836 | Jimenez Alvarenga, Gerson M |  | 45.9
PR | 998 | 08/23/19 | 840 | Lopez, Maslin A |  | 5.2
PR | 998 | 08/23/19 | 850 | Reed, Reuben H |  | 110.16
PR | 998 | 08/23/19 | 856 | Romero Garza, Jesus I |  | 5.51
PR | 998 | 08/23/19 | 860 | Silva Morales, Jair J |  | 49.57
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 08/30/19 | 999 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 08/30/19 | 1005 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 08/30/19 | 1015 | Gauthier, Dillon R |  | 31.21
PR | 998 | 08/30/19 | 1026 | Hubbard, Robert W |  | 7.65
PR | 998 | 08/30/19 | 1027 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 08/30/19 | 1041 | Reed, Reuben H |  | 137.7
PR | 998 | 08/30/19 | 1051 | Silva Morales, Jair J |  | 82.62
PR | 998 | 09/06/19 | 20 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 09/06/19 | 26 | Cruz Guzman, Joel A |  | 68.54
PR | 998 | 09/06/19 | 36 | Gauthier, Dillon R |  | 41.62
PR | 998 | 09/06/19 | 48 | Jimenez Alvarenga, Gerson M |  | 30.6
PR | 998 | 09/06/19 | 62 | Reed, Reuben H |  | 110.16
PR | 998 | 09/06/19 | 72 | Silva Morales, Jair J |  | 66.1
PR | 998 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/13/19 | 244 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 09/13/19 | 250 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 09/13/19 | 272 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 09/13/19 | 285 | Reed, Reuben H |  | 86.06
PR | 998 | 09/13/19 | 295 | Silva Morales, Jair J |  | 82.62
PR | 998 | 09/13/19 | 308 | Donelson, Richard T |  | 4.78
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/20/19 | 481 | Castro Hernandez, Jose A |  | 85.68
PR | 998 | 09/20/19 | 487 | Cruz Guzman, Joel A |  | 68.54
PR | 998 | 09/20/19 | 497 | Gauthier, Dillon R |  | 10.4
PR | 998 | 09/20/19 | 502 | Guerrero Espinoza, Mario |  | 39.17
PR | 998 | 09/20/19 | 509 | Hubbard, Robert W |  | 7.65
PR | 998 | 09/20/19 | 510 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 09/20/19 | 523 | Reed, Reuben H |  | 55.08
PR | 998 | 09/20/19 | 533 | Silva Morales, Jair J |  | 66.1
PR | 998 | 09/27/19 | 637 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 09/27/19 | 643 | Cruz Guzman, Joel A |  | 85.68
PR | 998 | 09/27/19 | 658 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 09/27/19 | 667 | Jimenez Alvarenga, Gerson M |  | 61.2
PR | 998 | 09/27/19 | 682 | Reed, Reuben H |  | 110.16
PR | 998 | 09/27/19 | 692 | Silva Morales, Jair J |  | 82.62
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/04/19 | 13 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 10/04/19 | 19 | Cruz Guzman, Joel A |  | 68.54
PR | 998 | 10/04/19 | 19 | Cruz Guzman, Joel A |  | 17.14
PR | 998 | 10/04/19 | 33 | Guerrero Espinoza, Mario |  | 46.51
PR | 998 | 10/04/19 | 42 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 10/04/19 | 50 | Mackey, Cole J |  | 9.18
PR | 998 | 10/04/19 | 58 | Reed, Reuben H |  | 82.62
PR | 998 | 10/04/19 | 68 | Silva Morales, Jair J |  | 82.62
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/11/19 | 268 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 10/11/19 | 274 | Cruz Guzman, Joel A |  | 34.27
PR | 998 | 10/11/19 | 288 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 10/11/19 | 297 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 10/11/19 | 312 | Reed, Reuben H |  | 82.62
PR | 998 | 10/11/19 | 323 | Silva Morales, Jair J |  | 49.57
PR | 998 | 10/18/19 | 462 | Castro Hernandez, Jose A |  | 107.1
PR | 998 | 10/18/19 | 481 | Guerrero Espinoza, Mario |  | 39.17
PR | 998 | 10/18/19 | 490 | Jimenez Alvarenga, Gerson M |  | 76.5
PR | 998 | 10/18/19 | 505 | Reed, Reuben H |  | 103.28
PR | 998 | 10/18/19 | 505 | Reed, Reuben H |  | 10.33
PR | 998 | 10/18/19 | 516 | Silva Morales, Jair J |  | 82.62
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 10/25/19 | 592 | Barnhart, Joseph N |  | 3.83
PR | 998 | 10/25/19 | 598 | Castro Hernandez, Jose A |  | 99.07
PR | 998 | 10/25/19 | 616 | Guerrero Espinoza, Mario |  | 45.29
PR | 998 | 10/25/19 | 625 | Jimenez Alvarenga, Gerson M |  | 70.76
PR | 998 | 10/25/19 | 641 | Reed, Reuben H |  | 123.93
PR | 998 | 10/25/19 | 652 | Silva Morales, Jair J |  | 76.42
PR | 998 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 11/01/19 | 13 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 11/01/19 | 25 | Frausto Mendoza, Pedro |  | 45.9
PR | 998 | 11/01/19 | 27 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 11/01/19 | 32 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 11/01/19 | 41 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 11/01/19 | 57 | Reed, Reuben H |  | 127.45
PR | 998 | 11/01/19 | 68 | Silva Morales, Jair J |  | 91.8
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 4.78
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/08/19 | 187 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 11/08/19 | 199 | Frausto Mendoza, Pedro |  | 74.59
PR | 998 | 11/08/19 | 201 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 11/08/19 | 206 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 11/08/19 | 214 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/08/19 | 215 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 11/08/19 | 231 | Reed, Reuben H |  | 142.44
PR | 998 | 11/08/19 | 242 | Silva Morales, Jair J |  | 91.8
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/15/19 | 447 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 11/15/19 | 459 | Frausto Mendoza, Pedro |  | 76.5
PR | 998 | 11/15/19 | 461 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 11/15/19 | 466 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 11/15/19 | 474 | Jimenez Alvarenga, Gerson M |  | 68.54
PR | 998 | 11/15/19 | 490 | Reed, Reuben H |  | 149.94
PR | 998 | 11/15/19 | 501 | Silva Morales, Jair J |  | 91.8
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/22/19 | 618 | Castro Hernandez, Jose A |  | 110.47
PR | 998 | 11/22/19 | 630 | Frausto Mendoza, Pedro |  | 68.85
PR | 998 | 11/22/19 | 632 | Garcia Perez, Ervey O |  | 52.33
PR | 998 | 11/22/19 | 637 | Guerrero Espinoza, Mario |  | 46.51
PR | 998 | 11/22/19 | 644 | Hubbard, Robert W |  | 20.66
PR | 998 | 11/22/19 | 645 | Jimenez Alvarenga, Gerson M |  | 81.4
PR | 998 | 11/22/19 | 647 | Kinssies, Jr, John E |  | 34.81
PR | 998 | 11/22/19 | 661 | Reed, Reuben H |  | 112.46
PR | 998 | 11/22/19 | 661 | Reed, Reuben H |  | 29.99
PR | 998 | 11/22/19 | 672 | Silva Morales, Jair J |  | 73.44
PR | 998 | 11/22/19 | 672 | Silva Morales, Jair J |  | 13.77
PR | 998 | 11/22/19 | 684 | Donelson, Richard T |  | 4.78
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/27/19 | 852 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 11/27/19 | 864 | Frausto Mendoza, Pedro |  | 72.68
PR | 998 | 11/27/19 | 866 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 11/27/19 | 871 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 11/27/19 | 878 | Hubbard, Robert W |  | 8.26
PR | 998 | 11/27/19 | 878 | Hubbard, Robert W |  | 4.13
PR | 998 | 11/27/19 | 879 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 11/27/19 | 881 | Kinssies, Jr, John E |  | 81.66
PR | 998 | 11/27/19 | 895 | Reed, Reuben H |  | 149.94
PR | 998 | 11/27/19 | 906 | Silva Morales, Jair J |  | 27.54
PR | 998 | 11/27/19 | 906 | Silva Morales, Jair J |  | 45.9
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/06/19 | 38 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 12/06/19 | 51 | Frausto Mendoza, Pedro |  | 53.55
PR | 998 | 12/06/19 | 53 | Garcia Perez, Ervey O |  | 44.06
PR | 998 | 12/06/19 | 58 | Guerrero Espinoza, Mario |  | 39.17
PR | 998 | 12/06/19 | 65 | Hubbard, Robert W |  | 16.52
PR | 998 | 12/06/19 | 66 | Jimenez Alvarenga, Gerson M |  | 68.54
PR | 998 | 12/06/19 | 68 | Kinssies, Jr, John E |  | 21.42
PR | 998 | 12/06/19 | 68 | Kinssies, Jr, John E |  | 21.42
PR | 998 | 12/06/19 | 82 | Reed, Reuben H |  | 119.95
PR | 998 | 12/06/19 | 93 | Silva Morales, Jair J |  | 73.44
PR | 998 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/13/19 | 399 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 12/13/19 | 412 | Frausto Mendoza, Pedro |  | 61.2
PR | 998 | 12/13/19 | 414 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 12/13/19 | 419 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 12/13/19 | 426 | Hubbard, Robert W |  | 24.79
PR | 998 | 12/13/19 | 427 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 12/13/19 | 429 | Kinssies, Jr, John E |  | 104.42
PR | 998 | 12/13/19 | 443 | Reed, Reuben H |  | 149.94
PR | 998 | 12/13/19 | 454 | Silva Morales, Jair J |  | 91.8
PR | 998 | 12/13/19 | 465 | Donelson, Richard T |  | 14.34
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/20/19 | 552 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 12/20/19 | 565 | Frausto Mendoza, Pedro |  | 40.16
PR | 998 | 12/20/19 | 567 | Garcia Perez, Ervey O |  | 33.05
PR | 998 | 12/20/19 | 572 | Guerrero Espinoza, Mario |  | 39.17
PR | 998 | 12/20/19 | 579 | Hubbard, Robert W |  | 16.52
PR | 998 | 12/20/19 | 580 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 12/20/19 | 582 | Kinssies, Jr, John E |  | 107.1
PR | 998 | 12/20/19 | 596 | Reed, Reuben H |  | 149.94
PR | 998 | 12/20/19 | 605 | Sanders, Allen O |  | 8.26
PR | 998 | 12/20/19 | 607 | Silva Morales, Jair J |  | 36.72
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/27/19 | 709 | Castro Hernandez, Jose A |  | 69.77
PR | 998 | 12/27/19 | 715 | Cruz Guzman, Joel A |  | 56.92
PR | 998 | 12/27/19 | 723 | Frausto Mendoza, Pedro |  | 17.21
PR | 998 | 12/27/19 | 725 | Garcia Perez, Ervey O |  | 22.03
PR | 998 | 12/27/19 | 730 | Guerrero Espinoza, Mario |  | 29.38
PR | 998 | 12/27/19 | 738 | Jimenez Alvarenga, Gerson M |  | 51.41
PR | 998 | 12/27/19 | 740 | Kinssies, Jr, John E |  | 21.42
PR | 998 | 12/27/19 | 740 | Kinssies, Jr, John E |  | 10.71
PR | 998 | 12/27/19 | 754 | Reed, Reuben H |  | 48.73
PR | 998 | 12/27/19 | 765 | Silva Morales, Jair J |  | 18.36
PR | 998 | 01/03/20 | 12 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 01/03/20 | 18 | Cruz Guzman, Joel A |  | 47.43
PR | 998 | 01/03/20 | 18 | Cruz Guzman, Joel A |  | 28.46
PR | 998 | 01/03/20 | 26 | Frausto Mendoza, Pedro |  | 61.2
PR | 998 | 01/03/20 | 28 | Garcia Perez, Ervey O |  | 39.93
PR | 998 | 01/03/20 | 33 | Guerrero Espinoza, Mario |  | 24.48
PR | 998 | 01/03/20 | 33 | Guerrero Espinoza, Mario |  | 14.69
PR | 998 | 01/03/20 | 40 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/03/20 | 41 | Jimenez Alvarenga, Gerson M |  | 68.54
PR | 998 | 01/03/20 | 43 | Kinssies, Jr, John E |  | 49.53
PR | 998 | 01/03/20 | 57 | Reed, Reuben H |  | 108.71
PR | 998 | 01/03/20 | 68 | Silva Morales, Jair J |  | 36.72
PR | 998 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/10/20 | 285 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 01/10/20 | 291 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 01/10/20 | 299 | Frausto Mendoza, Pedro |  | 55.46
PR | 998 | 01/10/20 | 301 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 01/10/20 | 306 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 01/10/20 | 313 | Hubbard, Robert W |  | 8.26
PR | 998 | 01/10/20 | 314 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 01/10/20 | 316 | Kinssies, Jr, John E |  | 78.99
PR | 998 | 01/10/20 | 330 | Reed, Reuben H |  | 146.19
PR | 998 | 01/10/20 | 341 | Silva Morales, Jair J |  | 91.8
PR | 998 | 01/17/20 | 551 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 01/17/20 | 557 | Cruz Guzman, Joel A |  | 75.89
PR | 998 | 01/17/20 | 565 | Frausto Mendoza, Pedro |  | 30.6
PR | 998 | 01/17/20 | 567 | Garcia Perez, Ervey O |  | 34.43
PR | 998 | 01/17/20 | 572 | Guerrero Espinoza, Mario |  | 29.38
PR | 998 | 01/17/20 | 580 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 01/17/20 | 582 | Kinssies, Jr, John E |  | 42.84
PR | 998 | 01/17/20 | 596 | Reed, Reuben H |  | 52.48
PR | 998 | 01/17/20 | 607 | Silva Morales, Jair J |  | 55.08
PR | 998 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 6.66
PR | 998 | 01/24/20 | 679 | Barnhart, Joseph N |  | 18.59
PR | 998 | 01/24/20 | 684 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 01/24/20 | 690 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 01/24/20 | 699 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 01/24/20 | 704 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 01/24/20 | 711 | Hubbard, Robert W |  | 16.52
PR | 998 | 01/24/20 | 712 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 01/24/20 | 727 | Reed, Reuben H |  | 89.96
PR | 998 | 01/24/20 | 736 | Sanders, Allen O |  | 8.26
PR | 998 | 01/24/20 | 738 | Silva Morales, Jair J |  | 73.44
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 4.78
PR | 998 | 01/31/20 | 774 | Frausto Mendoza, Pedro |  | 15.3
PR | 998 | 01/31/20 | 843 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 01/31/20 | 849 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 01/31/20 | 857 | Frausto Mendoza, Pedro |  | 38.25
PR | 998 | 01/31/20 | 859 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 01/31/20 | 864 | Guerrero Espinoza, Mario |  | 48.96
PR | 998 | 01/31/20 | 872 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 01/31/20 | 888 | Reed, Reuben H |  | 44.98
PR | 998 | 01/31/20 | 899 | Silva Morales, Jair J |  | 36.72
PR | 998 | 02/07/20 | 34 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 02/07/20 | 40 | Cruz Guzman, Joel A |  | 75.89
PR | 998 | 02/07/20 | 40 | Cruz Guzman, Joel A |  | 18.97
PR | 998 | 02/07/20 | 49 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 02/07/20 | 54 | Guerrero Espinoza, Mario |  | 44.06
PR | 998 | 02/07/20 | 54 | Guerrero Espinoza, Mario |  | 11.02
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/07/20 | 62 | Jimenez Alvarenga, Gerson M |  | 85.68
PR | 998 | 02/07/20 | 64 | Kinssies, Jr, John E |  | 64.26
PR | 998 | 02/07/20 | 78 | Reed, Reuben H |  | 101.21
PR | 998 | 02/07/20 | 90 | Silva Morales, Jair J |  | 91.8
PR | 998 | 02/07/20 | 102 | Donelson, Richard T |  | 4.78
PR | 998 | 02/14/20 | 244 | Castro Hernandez, Jose A |  | 69.77
PR | 998 | 02/14/20 | 244 | Castro Hernandez, Jose A |  | 46.51
PR | 998 | 02/14/20 | 250 | Cruz Guzman, Joel A |  | 56.92
PR | 998 | 02/14/20 | 250 | Cruz Guzman, Joel A |  | 37.94
PR | 998 | 02/14/20 | 259 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 02/14/20 | 264 | Guerrero Espinoza, Mario |  | 33.05
PR | 998 | 02/14/20 | 264 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 8.26
PR | 998 | 02/14/20 | 271 | Hubbard, Robert W |  | 16.52
PR | 998 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M |  | 51.41
PR | 998 | 02/14/20 | 272 | Jimenez Alvarenga, Gerson M |  | 34.27
PR | 998 | 02/14/20 | 274 | Kinssies, Jr, John E |  | 107.1
PR | 998 | 02/14/20 | 288 | Reed, Reuben H |  | 116.2
PR | 998 | 02/14/20 | 300 | Silva Morales, Jair J |  | 91.8
PR | 998 | 02/21/20 | 461 | Castro Hernandez, Jose A |  | 58.14
PR | 998 | 02/21/20 | 461 | Castro Hernandez, Jose A |  | 46.51
PR | 998 | 02/21/20 | 467 | Cruz Guzman, Joel A |  | 37.94
PR | 998 | 02/21/20 | 467 | Cruz Guzman, Joel A |  | 37.94
PR | 998 | 02/21/20 | 475 | Garcia Perez, Ervey O |  | 38.56
PR | 998 | 02/21/20 | 480 | Guerrero Espinoza, Mario |  | 27.54
PR | 998 | 02/21/20 | 480 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 02/21/20 | 504 | Reed, Reuben H |  | 67.47
PR | 998 | 02/21/20 | 504 | Reed, Reuben H |  | 22.49
PR | 998 | 02/21/20 | 516 | Silva Morales, Jair J |  | 82.62
PR | 998 | 02/28/20 | 689 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 02/28/20 | 695 | Cruz Guzman, Joel A |  | 37.94
PR | 998 | 02/28/20 | 695 | Cruz Guzman, Joel A |  | 37.94
PR | 998 | 02/28/20 | 704 | Garcia Perez, Ervey O |  | 44.06
PR | 998 | 02/28/20 | 709 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 02/28/20 | 709 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 02/28/20 | 733 | Reed, Reuben H |  | 71.22
PR | 998 | 02/28/20 | 745 | Silva Morales, Jair J |  | 59.67
PR | 998 | 03/06/20 | 51 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 03/06/20 | 57 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 03/06/20 | 67 | Garcia Perez, Ervey O |  | 44.06
PR | 998 | 03/06/20 | 67 | Garcia Perez, Ervey O |  | 11.02
PR | 998 | 03/06/20 | 71 | Guerrero Espinoza, Mario |  | 33.05
PR | 998 | 03/06/20 | 71 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 03/06/20 | 95 | Reed, Reuben H |  | 112.46
PR | 998 | 03/06/20 | 107 | Silva Morales, Jair J |  | 73.44
PR | 998 | 03/06/20 | 119 | Donelson, Richard T |  | 4.78
PR | 998 | 03/13/20 | 316 | Castro Hernandez, Jose A |  | 93.02
PR | 998 | 03/13/20 | 322 | Cruz Guzman, Joel A |  | 18.97
PR | 998 | 03/13/20 | 322 | Cruz Guzman, Joel A |  | 56.92
PR | 998 | 03/13/20 | 331 | Garcia Perez, Ervey O |  | 55.08
PR | 998 | 03/13/20 | 335 | Guerrero Espinoza, Mario |  | 44.06
PR | 998 | 03/13/20 | 342 | Hubbard, Robert W |  | 4.13
PR | 998 | 03/13/20 | 359 | Reed, Reuben H |  | 134.95
PR | 998 | 03/13/20 | 371 | Silva Morales, Jair J |  | 91.8
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 8.26
PR | 998 | 03/20/20 | 574 | Castro Hernandez, Jose A |  | 116.28
PR | 998 | 03/20/20 | 580 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 03/20/20 | 589 | Garcia Perez, Ervey O |  | 33.05
PR | 998 | 03/20/20 | 589 | Garcia Perez, Ervey O |  | 22.03
PR | 998 | 03/20/20 | 593 | Guerrero Espinoza, Mario |  | 33.05
PR | 998 | 03/20/20 | 593 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 03/20/20 | 617 | Reed, Reuben H |  | 119.95
PR | 998 | 03/20/20 | 629 | Silva Morales, Jair J |  | 75.74
PR | 998 | 03/20/20 | 641 | Donelson, Richard T |  | 4.78
PR | 998 | 03/26/20 | 752 | Barnhart, Joseph N |  | 8.26
PR | 998 | 03/26/20 | 757 | Castro Hernandez, Jose A |  | 125.46
PR | 998 | 03/26/20 | 762 | Cruz Guzman, Joel A |  | 94.86
PR | 998 | 03/26/20 | 771 | Garcia Perez, Ervey O |  | 33.05
PR | 998 | 03/26/20 | 771 | Garcia Perez, Ervey O |  | 22.03
PR | 998 | 03/26/20 | 775 | Guerrero Espinoza, Mario |  | 33.05
PR | 998 | 03/26/20 | 775 | Guerrero Espinoza, Mario |  | 22.03
PR | 998 | 03/26/20 | 797 | Reed, Reuben H |  | 116.2
PR | 998 | 03/26/20 | 808 | Silva Morales, Jair J |  | 91.8
PR | 998 | 03/26/20 | 820 | Donelson, Richard T |  | 4.78
PR | 998 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 04/17/20 | 288 | Donelson, Richard T |  | 4.78
PR | 998 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 05/08/20 | 188 | Hubbard, Robert W |  | 4.13
PR | 998 | 05/08/20 | 205 | Reed, Reuben H |  | 37.49
PR | 998 | 05/15/20 | 317 | Castro Hernandez, Jose A |  | 37.64
PR | 998 | 05/15/20 | 343 | Hubbard, Robert W |  | 16.52
PR | 998 | 05/15/20 | 360 | Reed, Reuben H |  | 44.98
PR | 998 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 05/22/20 | 472 | Castro Hernandez, Jose A |  | 25.09
PR | 998 | 05/22/20 | 472 | Castro Hernandez, Jose A |  | 25.09
PR | 998 | 05/22/20 | 494 | Hubbard, Robert W |  | 4.13
PR | 998 | 05/22/20 | 494 | Hubbard, Robert W |  | 8.26
PR | 998 | 05/22/20 | 511 | Reed, Reuben H |  | 29.99
PR | 998 | 05/22/20 | 511 | Reed, Reuben H |  | 29.99
PR | 998 | 05/29/20 | 638 | Reed, Reuben H |  | 14.99
PR | 998 | 05/29/20 | 646 | Sanders, Allen O |  | 4.13
PR | 998 | 05/29/20 | 659 | Donelson, Richard T |  | 4.78
PR | 998 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 06/05/20 | 26 | Cruz Guzman, Joel A |  | 18.97
PR | 998 | 06/05/20 | 52 | Reed, Reuben H |  | 29.99
PR | 998 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/11/20 | 191 | Reed, Reuben H |  | 7.5
PR | 998 | 06/19/20 | 416 | Sanders, Allen O |  | 8.26
PR | 998 | 07/10/20 | 183 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/17/20 | 293 | McCabe, Thomas C |  | 11.93
PR | 998 | 07/17/20 | 293 | McCabe, Thomas C |  | 11.93
PR | 998 | 07/17/20 | 298 | Reed, Reuben H |  | 14.99
PR | 998 | 07/17/20 | 298 | Reed, Reuben H |  | 14.99
PR | 998 | 07/17/20 | 303 | Sanders, Allen O |  | 8.26
PR | 998 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/24/20 | 431 | McCabe, Thomas C |  | 47.74
PR | 998 | 07/24/20 | 436 | Reed, Reuben H |  | 59.98
PR | 998 | 07/24/20 | 448 | Donelson, Richard T |  | 4.78
PR | 998 | 07/31/20 | 537 | Sanders, Allen O |  | 37.18
PR | 998 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/07/20 | 110 | Hubbard, Robert W |  | 6.2
PR | 998 | 08/07/20 | 119 | Reed, Reuben H |  | 22.49
PR | 998 | 08/07/20 | 119 | Reed, Reuben H |  | 26.24
PR | 998 | 08/07/20 | 128 | Donelson, Richard T |  | 4.78
PR | 998 | 08/14/20 | 296 | Boss, Benjamin T |  | 44.06
PR | 998 | 08/14/20 | 301 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 08/14/20 | 303 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 08/14/20 | 315 | Hubbard, Robert W |  | 24.79
PR | 998 | 08/14/20 | 327 | Sanders, Allen O |  | 92.95
PR | 998 | 08/21/20 | 417 | Boss, Benjamin T |  | 22.03
PR | 998 | 08/21/20 | 422 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 08/21/20 | 424 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 08/21/20 | 435 | Hubbard, Robert W |  | 33.05
PR | 998 | 08/21/20 | 447 | Sanders, Allen O |  | 70.23
PR | 998 | 08/21/20 | 459 | Donelson, Richard T |  | 9.56
PR | 998 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/28/20 | 565 | Boss, Benjamin T |  | 44.06
PR | 998 | 08/28/20 | 570 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 08/28/20 | 572 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 08/28/20 | 584 | Hubbard, Robert W |  | 12.39
PR | 998 | 08/28/20 | 598 | Sanders, Allen O |  | 119.8
PR | 998 | 08/28/20 | 604 | Donelson, Richard T |  | 4.78
PR | 998 | 09/04/20 | 8 | Boss, Benjamin T |  | 44.06
PR | 998 | 09/04/20 | 14 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 09/04/20 | 16 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 09/04/20 | 43 | Sanders, Allen O |  | 132.19
PR | 998 | 09/11/20 | 77 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/11/20 | 77 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/11/20 | 78 | Boss, Benjamin T |  | 22.03
PR | 998 | 09/11/20 | 84 | Cruz Gonzalez, Julio C |  | 68.54
PR | 998 | 09/11/20 | 86 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 09/11/20 | 113 | Sanders, Allen O |  | 119.8
PR | 998 | 09/18/20 | 295 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 09/18/20 | 297 | Cruz Reyes, Jose |  | 73.44
PR | 998 | 09/18/20 | 309 | Hubbard, Robert W |  | 24.79
PR | 998 | 09/18/20 | 313 | McCabe, Thomas C |  | 14.92
PR | 998 | 09/18/20 | 313 | McCabe, Thomas C |  | 2.98
PR | 998 | 09/18/20 | 324 | Sanders, Allen O |  | 123.93
PR | 998 | 09/18/20 | 330 | Donelson, Richard T |  | 9.56
PR | 998 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 09/25/20 | 438 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 09/25/20 | 466 | Sanders, Allen O |  | 86.75
PR | 998 | 09/25/20 | 478 | Donelson, Richard T |  | 4.78
PR | 998 | 10/02/20 | 28 | Hubbard, Robert W |  | 24.79
PR | 998 | 10/02/20 | 38 | Reed, Reuben H |  | 22.49
PR | 998 | 10/02/20 | 43 | Sanders, Allen O |  | 64.03
PR | 998 | 10/09/20 | 191 | Sanders, Allen O |  | 22.72
PR | 998 | 10/16/20 | 333 | Sanders, Allen O |  | 12.39
PR | 998 | 10/16/20 | 339 | Donelson, Richard T |  | 4.78
PR | 998 | 10/23/20 | 475 | Sanders, Allen O |  | 12.39
AR | 999 | 12/14/18 | 355 | Blueprint Capital Services, LLC $Howell |  | -36005 | 037258
AR | 999 | 12/14/18 | 355 | Blueprint Capital Services, LLC $Howell |  | -7885 | 037258
AR | 999 | 04/19/19 | 610 | Blueprint Capital Services, LLC $Howell |  | -27430 | 037326
AR | 999 | 05/20/19 | 507 | Blueprint Capital Services, LLC $Howell |  | -9145 | 037340
AR | 999 | 05/20/19 | 507 | Blueprint Capital Services, LLC $Howell |  | -7790 | 037340
AR | 999 | 06/19/19 | 611 | Blueprint Capital Services, LLC $Howell |  | -7866 | 037367
AR | 999 | 08/15/19 | 751 | Blueprint Capital Services, LLC $Howell |  | -7810 | 037388
AR | 999 | 08/15/19 | 751 | Blueprint Capital Services, LLC $Howell |  | -2932 | 037388
AR | 999 | 08/15/19 | 751 | Blueprint Capital Services, LLC $Howell |  | -650 | 037388
AR | 999 | 09/20/19 | 567 | Blueprint Capital Services, LLC $Howell |  | -9500 | 037411
AR | 999 | 09/20/19 | 567 | Blueprint Capital Services, LLC $Howell |  | -46853 | 037411
AR | 999 | 09/20/19 | 567 | Blueprint Capital Services, LLC $Howell |  | -46740 | 037411
AR | 999 | 09/20/19 | 567 | Blueprint Capital Services, LLC $Howell |  | -47196 | 037411
AR | 999 | 09/20/19 | 567 | Blueprint Capital Services, LLC $Howell |  | -8050 | 037411
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -4750 | 037420
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -20500 | 037420
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -15732 | 037420
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -66044 | 037420
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -57789 | 037420
AR | 999 | 10/18/19 | 533 | Blueprint Capital Services, LLC $Howell |  | -33022 | 037420
AR | 999 | 11/18/19 | 553 | Blueprint Capital Services, LLC $Howell |  | -2365 | 037435
AR | 999 | 11/18/19 | 553 | Blueprint Capital Services, LLC $Howell |  | -8256 | 037435
AR | 999 | 11/18/19 | 553 | Blueprint Capital Services, LLC $Howell |  | -16511 | 037435
AR | 999 | 11/18/19 | 553 | Blueprint Capital Services, LLC $Howell |  | -24767 | 037435
AR | 999 | 11/18/19 | 553 | Blueprint Capital Services, LLC $Howell |  | -18269 | 037435
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -4750 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -10750 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -2365 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -36890 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -7809 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -15580 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -16510 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -36536 | 037451
AR | 999 | 12/13/19 | 475 | Blueprint Capital Services, LLC $Howell |  | -4620 | 037451
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -5050 | 037465
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -6800 | 037465
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -24900 | 037465
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -24900 | 037465
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -6321 | 037465
AR | 999 | 01/20/20 | 650 | Blueprint Capital Services, LLC$800 5th |  | -8000 | 037465
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -32380 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -18925 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -24595 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -15618 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -7790 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -7866 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -8255 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -8255 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -8256 | 037466
AR | 999 | 01/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -6090 | 037466
AR | 999 | 03/20/20 | 651 | Blueprint Capital Services, LLC $Howell |  | -4757 | 037491
GL | 999 | 05/20/20 | 443 | Billing Adj |  | 75971
AR | 999 | 06/18/20 | 429 | Blueprint Capital Services, LLC $Howell |  | -4085 | 037509
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | -15295 | 037525
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | -15295 | 037525
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | -15295 | 037525
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | -15295 | 037525
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | -14049 | 037525
AR | 999 | 08/20/20 | 454 | Blueprint Capital Services, LLC $Howell |  | 7120 | 037525
AR | 999 | 09/21/20 | 351 | Blueprint Capital Services, LLC $Howell |  | -950 | 037537
AR | 999 | 09/21/20 | 351 | Blueprint Capital Services, LLC $Howell |  | -14155 | 037537
AR | 999 | 09/21/20 | 351 | Blueprint Capital Services, LLC $Howell |  | -14630 | 037537
AR | 999 | 09/21/20 | 351 | Blueprint Capital Services, LLC $Howell |  | -46440 | 037537
AR | 999 | 09/21/20 | 351 | Blueprint Capital Services, LLC $Howell |  | -733 | 037537