## 01 Overview
OWP #2059 · Meeker
GRE Construction LLC · 107 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 4492453
Revised budget (expenses) | 3325596.14
Forecast net profit | 1166856.86
Forecast margin | 25.97%
Progress to Date
Work complete (billed) | 4492453
Retention held | 224622.65
Earned less retention | 4267830.35
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 189320.4
AP | 958863.39
PR | 1867384.49
AR | -4492453

## 02 Job Info
JOB #2059 · GRE CONSTRUCTION LLC · Meeker — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract MasterSubcontract 78472.
IDENTITY
OWP Job ID | 2059
Project Name | Meeker
Site Address | 2030 West Meeker Street, Kent WA 98032
Subcontract Number | MasterSubcontract 78472
Effective Date | Feb 27, 2019
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | GRE Construction LLC
GC Address | (GRE)
GC Contract Signatory | GRE
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | GRE
Owner Address | (GRE)
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | TBD
Retention | 5% per contract
CONTRACT
Contract Value | $4,378,750 original
CHANGE-EVENT META
Executed CO Count | TBD — see GDrive Change Orders/CO's/
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | (see GDrive — multi-building)
COR Themes | (see GDrive)
Key RFIs | (see GDrive)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | GRE Meeker tenative job ticket by building 6-22-2020.pdf (8 pages — multi-building)
GDrive Folder | Job Books - Completed Jobs/2059-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Toilets — Building A | 134 | 117 Gerber SE 21-112 + 17 ADA SE 21-118
Lavs — Building A | 134 | Lenova UB-903W undercounter + Delta 573LF-PP
Tub/showers — Building A | 134 | 117 Aquatic 2603CT + 17 ADA 2603CTH + Delta BT13210/R10000MF
Kitchen sinks — Building A | 107 | 90 Dayton DCFU2115 + 17 Elkay ELUHAD ADA + Delta 9113
Garbage disposals | 107 | Moen GXP33C 1/3hp
Disposal air switches | 33 | Moen ARC-4200 (island sinks + ADA)
Water heaters per unit | 107 | 50-gallon electric Ruud ProE50-T2
Building A amenity | 17 | 4 ADA toilets + 4 lavs + 3 SS sinks + 6 Eemax on-demand WHs
VERIFIED MAIN FIXTURE COUNT | 767
Per unit (107): 7.17
AUDIT NOTE (2026-04-25): First-pass count of 773 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 767 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 4378750 | 4492453 | 113703
Executed change orders (net) | 0 | 113703 | 113703
Total contract value | 4378750 | 4606156 | 227406
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 24225 | 24225 | 10931.5 | 13293.5 | 0 | 45.12%
101 | Takeoff & Purchase Labor | 30200 | 30200 | 19998 | 10202 | 0 | 66.22%
110 | Underground Labor | 76650 | 83790 | 78123 | 5667 | 0 | 93.24%
111 | Garage Labor | 94950 | 96520 | 96984.5 | -464.5 | 0 | 100.5%
112 | Canout Labor | 27000 | 27000 | 27669 | -669 | 0 | 102.5%
120 | Roughin Labor | 559540 | 594524 | 700399 | -105875 | 0 | 117.8%
130 | Finish Labor | 184290 | 189240 | 171108.5 | 18131.5 | 0 | 90.42%
140 | Gas Labor | 7300 | 7300 | 7514 | -214 | 0 | 102.9%
141 | Water Main/Insulation Lab | 73190 | 73190 | 131285.25 | -58095.25 | 0 | 179.4%
143 | Condensation Drains Labor | 0 | 0 | 284 | -284 | 0 | 0%
210 | Underground Material | 63600 | 63800 | 26908.83 | 36891.17 | 0 | 42.18%
211 | Garage Material | 98250 | 98250 | 31688.57 | 66561.43 | 0 | 32.25%
212 | Canout Material | 31500 | 31500 | 15350.72 | 16149.28 | 0 | 48.73%
220 | Roughin Material | 342245 | 342415 | 205612.27 | 136802.73 | 0 | 60.05%
230 | Finish Material | 828580 | 866635 | 682969.44 | 183665.56 | 0 | 78.81%
240 | Gas Material | 7650 | 7650 | 6691.94 | 958.06 | 0 | 87.48%
241 | Water Main/Insulation Mat | 84760 | 84760 | 57918.56 | 26841.44 | 0 | 68.33%
242 | Mech Room Material | 21500 | 21500 | 7790.2 | 13709.8 | 0 | 36.23%
600 | Subcontractor | 3000 | 3000 | 5916 | -2916 | 0 | 197.2%
601 | Engineering/Plans | 50000 | 50000 | 54267.4 | -4267.4 | 0 | 108.5%
602 | Rental Equipment | 0 | 0 | 2267.08 | -2267.08 | 0 | 0%
603 | Permits & Licenses | 59000 | 59000 | 50576.78 | 8423.22 | 0 | 85.72%
607 | Other Expenses | 0 | 0 | 226 | -226 | 0 | 0%
995 | Payroll Burden | 462438.71 | 483842.07 | 527700.4 | -43858.33 | 0 | 109.1%
997 | Employee Benefits | 0 | 0 | 184 | -184 | 0 | 0%
998 | Payroll Taxes | 83533.79 | 87255.07 | 95203.34 | -7948.27 | 0 | 109.1%
TOTAL |  | 3213402.5 | 3325596.14 | 3015568.28 | 310027.86 | 0 | 90.68%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 1125989 | 1244296.75 | -118307.75 | 110.5%
Material | 8 | 1516510 | 1034930.53 | 481579.47 | 68.24%
Overhead | 5 | 112000 | 113253.26 | -1253.26 | 101.1%
Burden | 2 | 571097.14 | 622903.74 | -51806.6 | 109.1%
TOTAL | 25 | 3325596.14 | 3015384.28 | 310211.86 | 90.67%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 24225 | 10931.5 | 13293.5 | -54.88% | UNDER
101 | Takeoff & Purchase Labor | 30200 | 19998 | 10202 | -33.78% | UNDER
110 | Underground Labor | 83790 | 78123 | 5667 | -6.763% | ON
111 | Garage Labor | 96520 | 96984.5 | -464.5 | 0.4812% | ON
112 | Canout Labor | 27000 | 27669 | -669 | 2.478% | ON
120 | Roughin Labor | 594524 | 700399 | -105875 | 17.81% | OVER
130 | Finish Labor | 189240 | 171108.5 | 18131.5 | -9.581% | ON
140 | Gas Labor | 7300 | 7514 | -214 | 2.932% | ON
141 | Water Main/Insulation Lab | 73190 | 131285.25 | -58095.25 | 79.38% | CRITICAL
143 | Condensation Drains Labor | 0 | 284 | -284 | 0% | UNBUDGETED
210 | Underground Material | 63800 | 26908.83 | 36891.17 | -57.82% | UNDER
211 | Garage Material | 98250 | 31688.57 | 66561.43 | -67.75% | UNDER
212 | Canout Material | 31500 | 15350.72 | 16149.28 | -51.27% | UNDER
220 | Roughin Material | 342415 | 205612.27 | 136802.73 | -39.95% | UNDER
230 | Finish Material | 866635 | 682969.44 | 183665.56 | -21.19% | UNDER
240 | Gas Material | 7650 | 6691.94 | 958.06 | -12.52% | UNDER
241 | Water Main/Insulation Mat | 84760 | 57918.56 | 26841.44 | -31.67% | UNDER
242 | Mech Room Material | 21500 | 7790.2 | 13709.8 | -63.77% | UNDER
600 | Subcontractor | 3000 | 5916 | -2916 | 97.2% | CRITICAL
601 | Engineering/Plans | 50000 | 54267.4 | -4267.4 | 8.535% | ON
602 | Rental Equipment | 0 | 2267.08 | -2267.08 | 0% | UNBUDGETED
603 | Permits & Licenses | 59000 | 50576.78 | 8423.22 | -14.28% | UNDER
607 | Other Expenses | 0 | 226 | -226 | 0% | UNBUDGETED
995 | Payroll Burden | 483842.07 | 527700.4 | -43858.33 | 9.065% | ON
997 | Employee Benefits | 0 | 184 | -184 | 0% | UNBUDGETED
998 | Payroll Taxes | 87255.07 | 95203.34 | -7948.27 | 9.109% | ON

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Rosen Supply Kirkland | 438999.54 | 290 | 45.78%
Keller Supply Company | 236284.49 | 66 | 24.64%
Consolidated Supply Co. | 108314.63 | 64 | 11.3%
Franklin Engineering | 53781.5 | 36 | 5.609%
Capital One Credit Card | 52486.39 | 64 | 5.474%
Ferguson Enterprises, Inc. #3007 | 24110.42 | 44 | 2.514%
California Hydronics Corp | 16877 | 4 | 1.76%
Bank of America CC | 13622.9 | 1 | 1.421%
Old Castle Infrastructure, Inc. | 6250 | 3 | 0.6518%
Patchworks, Inc. | 5916 | 3 | 0.617%
Core & Main LP $HD Supply Waterworks | 1059.17 | 3 | 0.1105%
DRSi | 485.9 | 6 | 0.05067%
Manor Hardware & Construction Supply | 431.25 | 2 | 0.04498%
Mechanical Sales, Inc. | 175 | 1 | 0.01825%
Kele, Inc $ MI Controls | 69.2 | 1 | 0.007217%
TOTAL AP | 958863.39 | 588

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Martinez Reyes, Juan C | 2539 | 91466 | 36.0244 | JOURNEYMAN
Barbosa, Michael S | 2078.2 | 66426 | 31.9632 | JOURNEYMAN
Hernandez Gonzalez, Osbaldo | 2040.5 | 59232 | 29.0282 | JOURNEYMAN
Gonzalez Hernandez, Josue | 2007.5 | 70254 | 34.9958 | JOURNEYMAN
Holmes, Anthony R | 1924 | 81964 | 42.6008 | LEAD/SUPERVISOR
Lee, Ha Nul | 1738.5 | 41498 | 23.87 | JOURNEYMAN
Mendoza Morales, Jesus A | 1575 | 48921 | 31.061 | JOURNEYMAN
Rivera, Jorge A | 1559 | 57814 | 37.084 | LEAD/SUPERVISOR
Anderson, Richard P | 1554 | 75540 | 48.61 | LEAD/SUPERVISOR
Lima Romero, Melvin A | 1386 | 50952 | 36.7619 | LEAD/SUPERVISOR
Ramos Herrera, Franklin J | 1198 | 32851 | 27.4215 | JOURNEYMAN
Paco Leyva, Orlando | 1096 | 45956 | 41.9307 | LEAD/SUPERVISOR
Sanders, Allen O | 1066 | 57743 | 54.1679 | LEAD/SUPERVISOR
Chevez, Herson G | 1017.5 | 25942 | 25.4958 | JOURNEYMAN
Galdamez, Dagoberto A | 953 | 30765 | 32.2823 | JOURNEYMAN
Lovo, German G | 952.5 | 27908 | 29.2997 | JOURNEYMAN
Barnhart, Joseph N | 948 | 50152 | 52.903 | LEAD/SUPERVISOR
Benites Portillo, Marvin E | 831 | 24220 | 29.1456 | JOURNEYMAN
Belcher, Jacob T | 818 | 16654 | 20.3594 | JOURNEYMAN
Cruz Reyes, Jose | 817 | 26160 | 32.0196 | JOURNEYMAN
Reyes Cruz, Denis A | 806 | 25101 | 31.1427 | JOURNEYMAN
Rosas Olivares, Jorge C | 804.5 | 16090 | 20 | JOURNEYMAN
Boss, Benjamin T | 783 | 14230 | 18.1737 | APPRENTICE/HELPER
Stahlschmidt, John P | 763 | 16666 | 21.8427 | JOURNEYMAN
Ascencio, Jose L | 736 | 24288 | 33 | JOURNEYMAN
Hoeg, Xavier A | 706 | 12192 | 17.2691 | APPRENTICE/HELPER
Amaya Gonzalez, Edilberto A | 680 | 23432 | 34.4588 | JOURNEYMAN
Cruz Gonzalez, Julio C | 635.5 | 17878 | 28.1322 | JOURNEYMAN
Romero Garza, Jesus I | 628 | 14444 | 23 | JOURNEYMAN
Gutierrez Salas, Jose | 595.5 | 11314 | 18.9992 | APPRENTICE/HELPER
Velasquez Cruz, Osman N | 434 | 11780 | 27.1429 | JOURNEYMAN
Gerard, Jeffrey S | 428.5 | 23867 | 55.6989 | LEAD/SUPERVISOR
Velasquez Cruz, Denis M | 423 | 14433 | 34.1206 | JOURNEYMAN
Young, Joshua S | 320 | 5120 | 16 | APPRENTICE/HELPER
Eliassen, Cory H | 211 | 6330 | 30 | JOURNEYMAN
Guillen, Adrian | 164 | 2516 | 15.3415 | APPRENTICE/HELPER
Hubbard, Justin A | 154.5 | 4017 | 26 | JOURNEYMAN
Boss, Kyle A | 144 | 3024 | 21 | JOURNEYMAN
Donelson, Richard T | 113 | 7062 | 62.4956 | LEAD/SUPERVISOR
Trower-Kelly, Fidel D | 88 | 1848 | 21 | JOURNEYMAN
Gerard, Mitchell J | 48 | 1920 | 40 | LEAD/SUPERVISOR
Taylor, Evan R | 46.5 | 1534 | 32.9892 | JOURNEYMAN
Mackey, Cole J | 30 | 480 | 16 | APPRENTICE/HELPER
Gauthier, Dillon R | 24 | 432 | 18 | APPRENTICE/HELPER
Draves, Steven W | 16 | 496 | 31 | JOURNEYMAN
Gerard, Jordan E | 16 | 672 | 42 | LEAD/SUPERVISOR
Hubbard, Robert W | 9 | 486 | 54 | LEAD/SUPERVISOR
Kinssies, Jr, John E | 8 | 224 | 28 | JOURNEYMAN

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 12 | 10147.5 | 454129 | 26.76%
JOURNEYMAN | 29 | 25143.8 | 743884 | 66.32%
APPRENTICE/HELPER | 7 | 2622.5 | 46284 | 6.917%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 37914
Active workers | 48
Hours per unit (to date) | 354.3
Revenue per labor hour (billed) | 118.49
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 25.97% | 34% | -8.026%
Roughin labor share (code 120) | 52.8% | 45% | 7.8%
Top vendor concentration | 45.78% | 38% | 7.783%
Hours per unit | 354.3341 | 95 | 259.3341

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Roughin Labor (120) over revised | ⚠ WATCH | Actual $700,399 vs revised $594,524 (+18%) — monitor
Water Main/Insulation Lab (141) CRITICAL overrun | ⚠ WATCH | Actual $131,285 vs revised $73,190 (+79%) — needs immediate attention
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $5,916 vs revised $3,000 (+97%) — needs immediate attention
Top vendor concentration (Rosen Supply Kirklan) | ⚠ WATCH | 46% of AP ($439,000) — high, monitor
Retention aging | ✓ OK | $224,623 held · 5.0% of billed · standard range
Forecast margin | ✓ OK | 26.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 3015568.28 | 3015568.28 | 0
Revenue billed (AR ·-1) | -4492453 | 4492453 | -8984906
AP source total |  | 958863.39 | —
PR source total |  | 1867384.49 | —
GL source total |  | 189320.4 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2059 live project. 17-tab JCR schema on revised budget basis.