## Summary
#2059 · Meeker
GRE Construction LLC · 107 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
4492453 | 25.97% | 4492453 | 0
Key facts
Original contract |  | 4378750
Revised contract (CO impact) |  | 4492453
Executed COs (net) |  | 113703
Retention held |  | 224622.65
Revised expense budget |  | 3325596.14
Forecast net profit |  | 1166856.86
Percent complete |  | 100%
Live signals
Roughin Labor (120) over | ⚠ WATCH | Actual $700,399 vs revised $594,524 (+18%) — monitor
Water Main/Insulation Lab (141) CRITICAL | ⚠ WATCH | Actual $131,285 vs revised $73,190 (+79%) — needs attention
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $5,916 vs revised $3,000 (+97%) — needs attention
Top vendor (Rosen Supply Kirklan) | ⚠ WATCH | 46% of AP — high
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 26.0% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Rosen Supply Kirkland | 290 | 438999.54 | 45.78%
Keller Supply Company | 66 | 236284.49 | 24.64%
Consolidated Supply Co. | 64 | 108314.63 | 11.3%
Franklin Engineering | 36 | 53781.5 | 5.609%
Capital One Credit Card | 64 | 52486.39 | 5.474%
Ferguson Enterprises, Inc. #3007 | 44 | 24110.42 | 2.514%

## Transactions
Transactions Detail
JDR source transactions for job #2059 · 7205 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 12/07/18 | 114 | Gerard, Jeffrey S | 1 | 52 | 22057
PR | 100 | 02/08/19 | 227 | Gerard, Jeffrey S | 2 | 104 | 22769
PR | 100 | 03/01/19 | 75 | Gerard, Jeffrey S | 2 | 104 | 22982
PR | 100 | 03/08/19 | 315 | Gerard, Jeffrey S | 1 | 52 | 923054
PR | 100 | 03/15/19 | 563 | Gerard, Jeffrey S | 2 | 104 | 23125
PR | 100 | 03/22/19 | 777 | Gerard, Jeffrey S | 3 | 156 | 923198
PR | 100 | 03/29/19 | 990 | Gerard, Jeffrey S | 1 | 52 | 23273
PR | 100 | 04/05/19 | 152 | Gerard, Jeffrey S | 6.5 | 338 | 923346
PR | 100 | 04/12/19 | 398 | Gerard, Jeffrey S | 4 | 208 | 23421
PR | 100 | 04/19/19 | 597 | Gerard, Jeffrey S | 2 | 104 | 923497
PR | 100 | 04/26/19 | 813 | Gerard, Jeffrey S | 4 | 220 | 23569
PR | 100 | 05/03/19 | 82 | Gerard, Jeffrey S | 3 | 165 | 923644
PR | 100 | 05/10/19 | 235 | Gerard, Jeffrey S | 5 | 275 | 23720
PR | 100 | 05/17/19 | 468 | Gerard, Jeffrey S | 1 | 55 | 923799
PR | 100 | 05/24/19 | 681 | Gerard, Jeffrey S | 2 | 110 | 923876
PR | 100 | 06/07/19 | 255 | Gerard, Jeffrey S | 2 | 110 | 924030
PR | 100 | 06/14/19 | 524 | Gerard, Jeffrey S | 1 | 55 | 24104
PR | 100 | 06/28/19 | 911 | Gerard, Jeffrey S | 2.5 | 137.5 | 24255
PR | 100 | 07/05/19 | 82 | Gerard, Jeffrey S | 2 | 110 | 924330
PR | 100 | 07/12/19 | 353 | Gerard, Jeffrey S | 3 | 165 | 924405
PR | 100 | 07/19/19 | 586 | Gerard, Jeffrey S | 2 | 110 | 24485
PR | 100 | 07/26/19 | 686 | Gerard, Jeffrey S | 3 | 165 | 24635
PR | 100 | 08/09/19 | 329 | Gerard, Jeffrey S | 2 | 110 | 924782
PR | 100 | 08/16/19 | 637 | Gerard, Jeffrey S | 3 | 165 | 924856
PR | 100 | 08/23/19 | 874 | Gerard, Jeffrey S | 4 | 220 | 924932
PR | 100 | 08/30/19 | 1065 | Gerard, Jeffrey S | 1 | 55 | 25009
PR | 100 | 09/06/19 | 86 | Gerard, Jeffrey S | 2.5 | 137.5 | 925084
PR | 100 | 09/13/19 | 309 | Gerard, Jeffrey S | 4 | 220 | 25158
PR | 100 | 09/20/19 | 547 | Gerard, Jeffrey S | 2 | 110 | 925233
PR | 100 | 09/27/19 | 706 | Gerard, Jeffrey S | 2 | 110 | 925311
PR | 100 | 10/04/19 | 82 | Gerard, Jeffrey S | 5 | 275 | 25389
PR | 100 | 10/11/19 | 335 | Gerard, Jeffrey S | 4 | 220 | 925469
PR | 100 | 10/18/19 | 528 | Gerard, Jeffrey S | 4 | 220 | 25545
PR | 100 | 10/25/19 | 665 | Gerard, Jeffrey S | 5 | 275 | 925505
PR | 100 | 11/01/19 | 81 | Gerard, Jeffrey S | 5 | 290 | 925697
PR | 100 | 11/01/19 | 81 | Gerard, Jeffrey S | 1 | 58 | 925697
PR | 100 | 11/08/19 | 254 | Gerard, Jeffrey S | 4 | 232 | 925773
PR | 100 | 11/15/19 | 513 | Gerard, Jeffrey S | 5 | 290 | 925849
PR | 100 | 11/22/19 | 685 | Gerard, Jeffrey S | 4 | 232 | 925924
PR | 100 | 11/27/19 | 918 | Gerard, Jeffrey S | 2.5 | 145 | 925999
PR | 100 | 12/06/19 | 105 | Gerard, Jeffrey S | 2 | 116 | 26077
PR | 100 | 12/13/19 | 466 | Gerard, Jeffrey S | 2 | 116 | 926232
PR | 100 | 12/20/19 | 619 | Gerard, Jeffrey S | 1 | 58 | 926308
PR | 100 | 12/27/19 | 777 | Gerard, Jeffrey S | 3 | 174 | 26385
PR | 100 | 01/03/20 | 82 | Gerard, Jeffrey S | 3 | 174 | 926463
PR | 100 | 01/17/20 | 619 | Gerard, Jeffrey S | 1 | 58 | 926618
PR | 100 | 01/24/20 | 751 | Gerard, Jeffrey S | 3 | 174 | 926401
PR | 100 | 01/31/20 | 912 | Gerard, Jeffrey S | 2 | 116 | 26773
PR | 100 | 02/07/20 | 103 | Gerard, Jeffrey S | 2 | 116 | 26851
PR | 100 | 02/14/20 | 313 | Gerard, Jeffrey S | 3 | 174 | 926929
PR | 100 | 02/21/20 | 529 | Gerard, Jeffrey S | 2.5 | 145 | 27007
PR | 100 | 02/28/20 | 758 | Gerard, Jeffrey S | 4 | 232 | 927086
PR | 100 | 03/13/20 | 383 | Donelson, Richard T | 1 | 62.5 | 927244
PR | 100 | 03/13/20 | 384 | Gerard, Jeffrey S | 3 | 174 | 927245
PR | 100 | 03/20/20 | 642 | Gerard, Jeffrey S | 3 | 174 | 927322
PR | 100 | 05/08/20 | 232 | Gerard, Jeffrey S | 2 | 116 | 927785
PR | 100 | 05/15/20 | 385 | Gerard, Jeffrey S | 2 | 116 | 927863
PR | 100 | 05/22/20 | 535 | Gerard, Jeffrey S | 2 | 116 | 927934
PR | 100 | 05/29/20 | 660 | Gerard, Jeffrey S | 1 | 58 | 928003
PR | 100 | 06/05/20 | 67 | Gerard, Jeffrey S | 1.5 | 87 | 928056
PR | 100 | 06/19/20 | 423 | Gerard, Jeffrey S | 1 | 58 | 928200
PR | 100 | 06/26/20 | 565 | Gerard, Jeffrey S | 1 | 58 | 928247
PR | 100 | 07/02/20 | 51 | Gerard, Jeffrey S | 1.5 | 87 | 928294
PR | 100 | 07/24/20 | 449 | Gerard, Jeffrey S | 2 | 116 | 928441
PR | 100 | 07/31/20 | 544 | Gerard, Jeffrey S | 2 | 116 | 928490
PR | 100 | 08/07/20 | 129 | Gerard, Jeffrey S | 3.5 | 203 | 928532
PR | 100 | 08/14/20 | 333 | Gerard, Jeffrey S | 3.5 | 203 | 928573
PR | 100 | 08/21/20 | 460 | Gerard, Jeffrey S | 3 | 174 | 928614
PR | 100 | 08/28/20 | 605 | Gerard, Jeffrey S | 4 | 232 | 928658
PR | 100 | 09/04/20 | 50 | Gerard, Jeffrey S | 4 | 232 | 928706
PR | 100 | 09/18/20 | 331 | Gerard, Jeffrey S | 2 | 116 | 928802
PR | 100 | 09/25/20 | 479 | Gerard, Jeffrey S | 3 | 174 | 928850
PR | 100 | 10/02/20 | 52 | Gerard, Jeffrey S | 1 | 58 | 28601
PR | 100 | 10/09/20 | 199 | Gerard, Jeffrey S | 2 | 116 | 928948
PR | 100 | 11/20/20 | 389 | Gerard, Jeffrey S | 2 | 116 | 26226
PR | 101 | 10/12/18 | 310 | Gerard, Jeffrey S | 1 | 50 | 21467
PR | 101 | 11/30/18 | 901 | Gerard, Jeffrey S | 3 | 156 | 921984
PR | 101 | 12/07/18 | 114 | Gerard, Jeffrey S | 3 | 156 | 22057
PR | 101 | 12/14/18 | 338 | Gerard, Jeffrey S | 1 | 52 | 22198
PR | 101 | 02/08/19 | 227 | Gerard, Jeffrey S | 3 | 156 | 22769
PR | 101 | 02/15/19 | 389 | Gerard, Jeffrey S | 3 | 156 | 922840
PR | 101 | 03/01/19 | 75 | Gerard, Jeffrey S | 2 | 104 | 22982
PR | 101 | 03/08/19 | 315 | Gerard, Jeffrey S | 3 | 156 | 923054
PR | 101 | 03/15/19 | 562 | Donelson, Richard T | 2 | 125 | 23124
PR | 101 | 03/15/19 | 563 | Gerard, Jeffrey S | 5 | 260 | 23125
PR | 101 | 03/22/19 | 776 | Donelson, Richard T | 1 | 62.5 | 923197
PR | 101 | 03/22/19 | 777 | Gerard, Jeffrey S | 3 | 156 | 923198
PR | 101 | 03/29/19 | 989 | Donelson, Richard T | 1 | 62.5 | 23272
PR | 101 | 03/29/19 | 990 | Gerard, Jeffrey S | 5 | 260 | 23273
PR | 101 | 04/05/19 | 152 | Gerard, Jeffrey S | 3 | 156 | 923346
PR | 101 | 04/12/19 | 397 | Donelson, Richard T | 1 | 62.5 | 23420
PR | 101 | 04/12/19 | 398 | Gerard, Jeffrey S | 5 | 260 | 23421
PR | 101 | 04/19/19 | 597 | Gerard, Jeffrey S | 5 | 260 | 923497
PR | 101 | 04/26/19 | 812 | Donelson, Richard T | 1 | 62.5 | 23568
PR | 101 | 04/26/19 | 813 | Gerard, Jeffrey S | 6 | 330 | 23569
PR | 101 | 05/03/19 | 81 | Donelson, Richard T | 6 | 375 | 923643
PR | 101 | 05/03/19 | 82 | Gerard, Jeffrey S | 6 | 330 | 923644
PR | 101 | 05/10/19 | 234 | Donelson, Richard T | 11 | 687.5 | 23719
PR | 101 | 05/10/19 | 235 | Gerard, Jeffrey S | 6 | 330 | 23720
PR | 101 | 05/17/19 | 467 | Donelson, Richard T | 3 | 187.5 | 923798
PR | 101 | 05/17/19 | 468 | Gerard, Jeffrey S | 4 | 220 | 923799
PR | 101 | 05/24/19 | 681 | Gerard, Jeffrey S | 6 | 330 | 923876
PR | 101 | 05/31/19 | 953 | Gerard, Jeffrey S | 4 | 220 | 923953
PR | 101 | 06/07/19 | 254 | Donelson, Richard T | 5 | 312.5 | 924029
PR | 101 | 06/07/19 | 255 | Gerard, Jeffrey S | 5 | 275 | 924030
PR | 101 | 06/14/19 | 524 | Gerard, Jeffrey S | 3 | 165 | 24104
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 2 | 125 | 24179
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 6 | 330 | 24180
PR | 101 | 06/21/19 | 694 | Gerard, Jeffrey S | 1.5 | 82.5 | 24180
PR | 101 | 06/28/19 | 910 | Donelson, Richard T | 2 | 125 | 24254
PR | 101 | 06/28/19 | 911 | Gerard, Jeffrey S | 4 | 220 | 24255
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 1 | 62.5 | 924329
PR | 101 | 07/05/19 | 82 | Gerard, Jeffrey S | 6 | 330 | 924330
PR | 101 | 07/12/19 | 352 | Donelson, Richard T | 1 | 62.5 | 924404
PR | 101 | 07/12/19 | 353 | Gerard, Jeffrey S | 3 | 165 | 924405
PR | 101 | 07/19/19 | 586 | Gerard, Jeffrey S | 4 | 220 | 24485
PR | 101 | 07/26/19 | 686 | Gerard, Jeffrey S | 5.5 | 302.5 | 24635
PR | 101 | 08/02/19 | 77 | Gerard, Jeffrey S | 3 | 165 | 924708
PR | 101 | 08/09/19 | 329 | Gerard, Jeffrey S | 4 | 220 | 924782
PR | 101 | 08/16/19 | 636 | Donelson, Richard T | 1 | 62.5 | 924855
PR | 101 | 08/16/19 | 637 | Gerard, Jeffrey S | 4 | 220 | 924856
PR | 101 | 08/23/19 | 874 | Gerard, Jeffrey S | 4 | 220 | 924932
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 2 | 125 | 25008
PR | 101 | 08/30/19 | 1065 | Gerard, Jeffrey S | 4 | 220 | 25009
PR | 101 | 09/06/19 | 85 | Donelson, Richard T | 1 | 62.5 | 925083
PR | 101 | 09/06/19 | 86 | Gerard, Jeffrey S | 4 | 220 | 925084
PR | 101 | 09/13/19 | 309 | Gerard, Jeffrey S | 4 | 220 | 25158
PR | 101 | 09/20/19 | 546 | Donelson, Richard T | 2 | 125 | 925232
PR | 101 | 09/20/19 | 547 | Gerard, Jeffrey S | 3 | 165 | 925233
PR | 101 | 09/27/19 | 705 | Donelson, Richard T | 1 | 62.5 | 925310
PR | 101 | 09/27/19 | 706 | Gerard, Jeffrey S | 3 | 165 | 925311
PR | 101 | 10/04/19 | 82 | Gerard, Jeffrey S | 5 | 275 | 25389
PR | 101 | 10/11/19 | 335 | Gerard, Jeffrey S | 3 | 165 | 925469
PR | 101 | 10/18/19 | 528 | Gerard, Jeffrey S | 3 | 165 | 25545
PR | 101 | 10/25/19 | 665 | Gerard, Jeffrey S | 6 | 330 | 925505
PR | 101 | 11/01/19 | 81 | Gerard, Jeffrey S | 2 | 116 | 925697
PR | 101 | 11/08/19 | 253 | Donelson, Richard T | 1 | 62.5 | 925772
PR | 101 | 11/15/19 | 513 | Gerard, Jeffrey S | 1 | 58 | 925849
PR | 101 | 11/22/19 | 685 | Gerard, Jeffrey S | 2 | 116 | 925924
PR | 101 | 11/27/19 | 917 | Donelson, Richard T | 7 | 437.5 | 925998
PR | 101 | 11/27/19 | 918 | Gerard, Jeffrey S | 2 | 116 | 925999
PR | 101 | 12/06/19 | 104 | Donelson, Richard T | 1 | 62.5 | 26076
PR | 101 | 12/13/19 | 466 | Gerard, Jeffrey S | 3 | 174 | 926232
PR | 101 | 12/20/19 | 619 | Gerard, Jeffrey S | 1 | 58 | 926308
PR | 101 | 12/27/19 | 777 | Gerard, Jeffrey S | 1 | 58 | 26385
PR | 101 | 01/03/20 | 81 | Donelson, Richard T | 2 | 125 | 926462
PR | 101 | 01/03/20 | 82 | Gerard, Jeffrey S | 1 | 58 | 926463
PR | 101 | 01/10/20 | 352 | Donelson, Richard T | 2 | 125 | 26540
PR | 101 | 01/17/20 | 618 | Donelson, Richard T | 5 | 312.5 | 926617
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 1 | 62.5 | 926400
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 1 | 62.5 | 926400
PR | 101 | 01/24/20 | 751 | Gerard, Jeffrey S | 3 | 174 | 926401
PR | 101 | 01/31/20 | 911 | Donelson, Richard T | 2 | 125 | 26772
PR | 101 | 01/31/20 | 912 | Gerard, Jeffrey S | 3 | 174 | 26773
PR | 101 | 02/07/20 | 102 | Donelson, Richard T | 1 | 62.5 | 26850
PR | 101 | 02/07/20 | 103 | Gerard, Jeffrey S | 3 | 174 | 26851
PR | 101 | 02/14/20 | 313 | Gerard, Jeffrey S | 4 | 232 | 926929
PR | 101 | 02/21/20 | 528 | Donelson, Richard T | 1 | 62.5 | 27006
PR | 101 | 02/28/20 | 757 | Donelson, Richard T | 1 | 62.5 | 927085
PR | 101 | 03/13/20 | 383 | Donelson, Richard T | 1 | 62.5 | 927244
PR | 101 | 03/20/20 | 641 | Donelson, Richard T | 2 | 125 | 927321
PR | 101 | 03/20/20 | 642 | Gerard, Jeffrey S | 2 | 116 | 927322
PR | 101 | 03/26/20 | 820 | Donelson, Richard T | 3 | 187.5 | 927396
PR | 101 | 03/26/20 | 821 | Gerard, Jeffrey S | 2 | 116 | 927397
PR | 101 | 04/03/20 | 42 | Donelson, Richard T | 1 | 62.5 | 927434
PR | 101 | 04/17/20 | 288 | Donelson, Richard T | 1 | 62.5 | 927551
PR | 101 | 04/24/20 | 424 | Donelson, Richard T | 1 | 62.5 | 927628
PR | 101 | 05/01/20 | 78 | Donelson, Richard T | 1 | 62.5 | 927705
PR | 101 | 05/01/20 | 79 | Gerard, Jeffrey S | 4 | 232 | 927706
PR | 101 | 05/08/20 | 231 | Donelson, Richard T | 1 | 62.5 | 927784
PR | 101 | 05/08/20 | 232 | Gerard, Jeffrey S | 5 | 290 | 927785
PR | 101 | 05/15/20 | 384 | Donelson, Richard T | 5 | 312.5 | 927862
PR | 101 | 05/15/20 | 385 | Gerard, Jeffrey S | 4 | 232 | 927863
PR | 101 | 05/22/20 | 534 | Donelson, Richard T | 2 | 125 | 927933
PR | 101 | 05/22/20 | 535 | Gerard, Jeffrey S | 4 | 232 | 927934
PR | 101 | 05/29/20 | 659 | Donelson, Richard T | 3 | 187.5 | 928002
PR | 101 | 05/29/20 | 659 | Donelson, Richard T | 1 | 62.5 | 928002
PR | 101 | 05/29/20 | 660 | Gerard, Jeffrey S | 3 | 174 | 928003
PR | 101 | 06/05/20 | 66 | Donelson, Richard T | 1 | 62.5 | 928055
PR | 101 | 06/05/20 | 67 | Gerard, Jeffrey S | 4 | 232 | 928056
PR | 101 | 06/12/20 | 266 | Donelson, Richard T | 3 | 187.5 | 928151
PR | 101 | 06/12/20 | 267 | Gerard, Jeffrey S | 2 | 116 | 928152
PR | 101 | 06/19/20 | 422 | Donelson, Richard T | 2 | 125 | 928199
PR | 101 | 06/19/20 | 423 | Gerard, Jeffrey S | 1 | 58 | 928200
PR | 101 | 06/26/20 | 564 | Donelson, Richard T | 2 | 125 | 928246
PR | 101 | 06/26/20 | 565 | Gerard, Jeffrey S | 1 | 58 | 928247
PR | 101 | 07/10/20 | 182 | Donelson, Richard T | 1 | 62.5 | 28341
PR | 101 | 07/17/20 | 310 | Gerard, Jeffrey S | 1 | 58 | 928390
PR | 101 | 07/24/20 | 449 | Gerard, Jeffrey S | 2 | 116 | 928441
PR | 101 | 07/31/20 | 543 | Donelson, Richard T | 1 | 62.5 | 928489
PR | 101 | 07/31/20 | 544 | Gerard, Jeffrey S | 1 | 58 | 928490
PR | 101 | 08/07/20 | 129 | Gerard, Jeffrey S | 4 | 232 | 928532
PR | 101 | 08/14/20 | 333 | Gerard, Jeffrey S | 1 | 58 | 928573
PR | 101 | 08/21/20 | 459 | Donelson, Richard T | 1 | 62.5 | 928613
PR | 101 | 08/21/20 | 460 | Gerard, Jeffrey S | 2 | 116 | 928614
PR | 101 | 08/28/20 | 604 | Donelson, Richard T | 2 | 125 | 928657
PR | 101 | 09/11/20 | 119 | Donelson, Richard T | 1 | 62.5 | 28753
PR | 101 | 09/18/20 | 330 | Donelson, Richard T | 1 | 62.5 | 928801
PR | 101 | 09/25/20 | 478 | Donelson, Richard T | 1 | 62.5 | 928849
PR | 101 | 10/02/20 | 51 | Donelson, Richard T | 1 | 62.5 | 28600
PR | 101 | 10/09/20 | 198 | Donelson, Richard T | 1 | 62.5 | 928947
PR | 101 | 10/09/20 | 199 | Gerard, Jeffrey S | 1 | 58 | 928948
PR | 101 | 11/13/20 | 230 | Donelson, Richard T | 1 | 62.5 | 29181
PR | 101 | 11/25/20 | 498 | Donelson, Richard T | 1 | 62.5 | 929272
PR | 101 | 01/08/21 | 52 | Donelson, Richard T | 1 | 62.5 | 929603
PR | 110 | 04/05/19 | 83 | Barnhart, Joseph N | 3 | 216 | 23277
PR | 110 | 04/05/19 | 83 | Barnhart, Joseph N | 15 | 720 | 23277
PR | 110 | 04/05/19 | 125 | Paco Leyva, Orlando | 2.5 | 138.75 | 23319
PR | 110 | 04/05/19 | 125 | Paco Leyva, Orlando | 25 | 925 | 23319
PR | 110 | 04/05/19 | 127 | Ramos Herrera, Franklin J | 3.5 | 120.75 | 23321
PR | 110 | 04/05/19 | 127 | Ramos Herrera, Franklin J | 24 | 552 | 23321
PR | 110 | 04/12/19 | 327 | Barnhart, Joseph N | 2 | 150 | 23351
PR | 110 | 04/12/19 | 327 | Barnhart, Joseph N | 17 | 850 | 23351
PR | 110 | 04/12/19 | 365 | Martinez Reyes, Juan C | 2 | 84 | 23389
PR | 110 | 04/12/19 | 365 | Martinez Reyes, Juan C | 5 | 140 | 23389
PR | 110 | 04/12/19 | 369 | Paco Leyva, Orlando | 3 | 180 | 23393
PR | 110 | 04/12/19 | 369 | Paco Leyva, Orlando | 40 | 1600 | 23393
PR | 110 | 04/12/19 | 371 | Ramos Herrera, Franklin J | 3 | 103.5 | 23395
PR | 110 | 04/12/19 | 371 | Ramos Herrera, Franklin J | 40 | 920 | 23395
PR | 110 | 04/19/19 | 524 | Barnhart, Joseph N | 2 | 150 | 23425
PR | 110 | 04/19/19 | 524 | Barnhart, Joseph N | 32 | 1600 | 23425
PR | 110 | 04/19/19 | 563 | Martinez Reyes, Juan C | 16 | 448 | 23464
PR | 110 | 04/19/19 | 567 | Paco Leyva, Orlando | 33.5 | 1340 | 23468
PR | 110 | 04/19/19 | 569 | Ramos Herrera, Franklin J | 1.5 | 51.75 | 23470
PR | 110 | 04/19/19 | 569 | Ramos Herrera, Franklin J | 40 | 920 | 23470
PR | 110 | 04/26/19 | 744 | Barnhart, Joseph N | 8 | 400 | 23501
PR | 110 | 04/26/19 | 786 | Paco Leyva, Orlando | 31 | 1240 | 23543
PR | 110 | 04/26/19 | 788 | Ramos Herrera, Franklin J | 31 | 806 | 23545
PR | 110 | 05/03/19 | 11 | Barnhart, Joseph N | 26 | 1300 | 23573
PR | 110 | 05/03/19 | 55 | Paco Leyva, Orlando | 40 | 1600 | 23617
PR | 110 | 05/03/19 | 57 | Ramos Herrera, Franklin J | 40 | 1040 | 23619
PR | 110 | 05/10/19 | 164 | Barnhart, Joseph N | 2 | 150 | 23648
PR | 110 | 05/10/19 | 164 | Barnhart, Joseph N | 7 | 350 | 23648
PR | 110 | 05/10/19 | 208 | Paco Leyva, Orlando | 2 | 120 | 23692
PR | 110 | 05/10/19 | 208 | Paco Leyva, Orlando | 2 | 80 | 23692
PR | 110 | 05/10/19 | 210 | Ramos Herrera, Franklin J | 2 | 78 | 23694
PR | 110 | 05/10/19 | 210 | Ramos Herrera, Franklin J | 2 | 52 | 23694
PR | 110 | 05/17/19 | 391 | Anderson, Richard P | 8.5 | 399.5 | 23722
PR | 110 | 05/17/19 | 395 | Barnhart, Joseph N | 19 | 950 | 23726
PR | 110 | 05/17/19 | 430 | Kinssies, Jr, John E | 8 | 224 | 23761
PR | 110 | 05/17/19 | 442 | Ramos Herrera, Franklin J | 24 | 624 | 23773
PR | 110 | 05/24/19 | 604 | Anderson, Richard P | 1 | 47 | 23799
PR | 110 | 05/24/19 | 632 | Gonzalez Hernandez, Josue | 5 | 160 | 23827
PR | 110 | 05/31/19 | 881 | Barnhart, Joseph N | 2 | 100 | 23881
PR | 110 | 06/14/19 | 454 | Barnhart, Joseph N | 5 | 250 | 24035
PR | 110 | 06/14/19 | 496 | Paco Leyva, Orlando | 8 | 320 | 24077
PR | 110 | 06/14/19 | 498 | Ramos Herrera, Franklin J | 16 | 416 | 24079
PR | 110 | 06/21/19 | 622 | Barnhart, Joseph N | 10 | 500 | 24108
PR | 110 | 06/21/19 | 663 | Martinez Reyes, Juan C | 19 | 627 | 24149
PR | 110 | 06/21/19 | 667 | Paco Leyva, Orlando | 21 | 840 | 24153
PR | 110 | 06/21/19 | 669 | Ramos Herrera, Franklin J | 21 | 546 | 24155
PR | 110 | 06/28/19 | 840 | Barnhart, Joseph N | 14 | 700 | 24184
PR | 110 | 06/28/19 | 880 | Martinez Reyes, Juan C | 39 | 1287 | 24224
PR | 110 | 07/05/19 | 12 | Barnhart, Joseph N | 3 | 150 | 24259
PR | 110 | 07/05/19 | 52 | Martinez Reyes, Juan C | 8 | 264 | 24300
PR | 110 | 07/12/19 | 312 | Hubbard, Justin A | 5.5 | 143 | 24364
PR | 110 | 07/12/19 | 321 | Martinez Reyes, Juan C | 15 | 495 | 24373
PR | 110 | 07/19/19 | 512 | Barnhart, Joseph N | 10 | 500 | 24411
PR | 110 | 07/19/19 | 542 | Hubbard, Justin A | 8 | 208 | 24441
PR | 110 | 07/19/19 | 551 | Martinez Reyes, Juan C | 16 | 528 | 24450
PR | 110 | 07/19/19 | 555 | Paco Leyva, Orlando | 26 | 1040 | 24454
PR | 110 | 07/19/19 | 557 | Ramos Herrera, Franklin J | 1 | 39 | 24456
PR | 110 | 07/19/19 | 557 | Ramos Herrera, Franklin J | 24 | 624 | 24456
PR | 110 | 07/19/19 | 557 | Ramos Herrera, Franklin J | 16 | 416 | 24456
PR | 110 | 07/26/19 | 616 | Barnhart, Joseph N | 7 | 350 | 24565
PR | 110 | 07/26/19 | 654 | Martinez Reyes, Juan C | 32 | 1056 | 24603
PR | 110 | 07/26/19 | 658 | Paco Leyva, Orlando | 28 | 1120 | 24607
PR | 110 | 07/26/19 | 660 | Ramos Herrera, Franklin J | 32 | 832 | 24609
PR | 110 | 08/02/19 | 8 | Barnhart, Joseph N | 4 | 200 | 24639
PR | 110 | 08/02/19 | 46 | Martinez Reyes, Juan C | 4 | 132 | 24677
PR | 110 | 08/02/19 | 50 | Paco Leyva, Orlando | 4 | 160 | 24681
PR | 110 | 08/02/19 | 52 | Ramos Herrera, Franklin J | 3 | 78 | 24683
PR | 110 | 08/30/19 | 1034 | Martinez Reyes, Juan C | 8 | 264 | 24976
PR | 110 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A | 3 | 108 | 25620
PR | 110 | 11/01/19 | 4 | Anderson, Richard P | 10 | 490 | 25621
PR | 110 | 11/01/19 | 8 | Barnhart, Joseph N | 3 | 162 | 25625
PR | 110 | 11/01/19 | 44 | Lee, Ha Nul | 8 | 200 | 25661
PR | 110 | 11/01/19 | 54 | Paco Leyva, Orlando | 5 | 220 | 25671
PR | 110 | 11/01/19 | 56 | Ramos Herrera, Franklin J | 8 | 240 | 25673
PR | 110 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A | 8 | 432 | 25696
PR | 110 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A | 14 | 504 | 25696
PR | 110 | 11/08/19 | 178 | Anderson, Richard P | 10 | 490 | 25697
PR | 110 | 11/08/19 | 182 | Barnhart, Joseph N | 5 | 405 | 25701
PR | 110 | 11/08/19 | 182 | Barnhart, Joseph N | 12 | 648 | 25701
PR | 110 | 11/08/19 | 183 | Belcher, Jacob T | 30 | 630 | 25702
PR | 110 | 11/08/19 | 184 | Benites Portillo, Marvin E | 8 | 348 | 25703
PR | 110 | 11/08/19 | 184 | Benites Portillo, Marvin E | 8 | 232 | 25703
PR | 110 | 11/08/19 | 188 | Chevez, Herson G | 8 | 312 | 25707
PR | 110 | 11/08/19 | 188 | Chevez, Herson G | 2 | 52 | 25707
PR | 110 | 11/08/19 | 200 | Galdamez, Dagoberto A | 2 | 66 | 25719
PR | 110 | 11/08/19 | 218 | Lee, Ha Nul | 8 | 300 | 25737
PR | 110 | 11/08/19 | 218 | Lee, Ha Nul | 30 | 750 | 25737
PR | 110 | 11/08/19 | 224 | Martinez Reyes, Juan C | 16 | 592 | 25743
PR | 110 | 11/08/19 | 228 | Paco Leyva, Orlando | 9 | 594 | 25747
PR | 110 | 11/08/19 | 228 | Paco Leyva, Orlando | 18 | 792 | 25747
PR | 110 | 11/08/19 | 230 | Ramos Herrera, Franklin J | 9 | 405 | 25749
PR | 110 | 11/08/19 | 230 | Ramos Herrera, Franklin J | 18 | 540 | 25749
PR | 110 | 11/15/19 | 438 | Anderson, Richard P | 1 | 49 | 25773
PR | 110 | 11/15/19 | 442 | Barnhart, Joseph N | 3 | 162 | 25777
PR | 110 | 11/15/19 | 443 | Belcher, Jacob T | 8 | 168 | 25778
PR | 110 | 11/15/19 | 469 | Hoeg, Xavier A | 2 | 36 | 25805
PR | 110 | 11/15/19 | 487 | Paco Leyva, Orlando | 2 | 88 | 25823
PR | 110 | 11/15/19 | 489 | Ramos Herrera, Franklin J | 2 | 60 | 25825
PR | 110 | 11/22/19 | 609 | Anderson, Richard P | 6 | 294 | 25849
PR | 110 | 12/20/19 | 543 | Anderson, Richard P | 11 | 539 | 26232
PR | 110 | 12/20/19 | 547 | Barnhart, Joseph N | 8 | 432 | 26236
PR | 110 | 12/20/19 | 548 | Belcher, Jacob T | 2 | 42 | 26237
PR | 110 | 12/20/19 | 553 | Chevez, Herson G | 4 | 104 | 26242
PR | 110 | 12/20/19 | 583 | Lee, Ha Nul | 10 | 250 | 26272
PR | 110 | 12/20/19 | 586 | Lovo, German G | 4 | 120 | 26275
PR | 110 | 12/20/19 | 589 | Martinez Reyes, Juan C | 6 | 222 | 26278
PR | 110 | 12/20/19 | 591 | Mendoza Morales, Jesus A | 9 | 288 | 26280
PR | 110 | 12/20/19 | 593 | Paco Leyva, Orlando | 12 | 528 | 26282
PR | 110 | 12/20/19 | 597 | Reyes Cruz, Denis A | 10 | 330 | 26286
PR | 110 | 12/20/19 | 613 | Velasquez Cruz, Denis M | 10 | 350 | 26302
PR | 110 | 12/20/19 | 614 | Velasquez Cruz, Osman N | 10 | 280 | 26303
PR | 110 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A | 7 | 252 | 26307
PR | 110 | 12/27/19 | 700 | Anderson, Richard P | 19 | 931 | 26308
PR | 110 | 12/27/19 | 703 | Barbosa, Michael S | 14 | 462 | 26311
PR | 110 | 12/27/19 | 704 | Barnhart, Joseph N | 3 | 162 | 26312
PR | 110 | 12/27/19 | 706 | Benites Portillo, Marvin E | 6 | 174 | 26314
PR | 110 | 12/27/19 | 710 | Chevez, Herson G | 14 | 364 | 26318
PR | 110 | 12/27/19 | 724 | Galdamez, Dagoberto A | 6 | 198 | 26332
PR | 110 | 12/27/19 | 741 | Lee, Ha Nul | 22 | 550 | 26349
PR | 110 | 12/27/19 | 742 | Lima Romero, Melvin A | 4 | 152 | 26350
PR | 110 | 12/27/19 | 744 | Lovo, German G | 14 | 420 | 26352
PR | 110 | 12/27/19 | 747 | Martinez Reyes, Juan C | 9 | 333 | 26355
PR | 110 | 12/27/19 | 749 | Mendoza Morales, Jesus A | 10 | 320 | 26357
PR | 110 | 12/27/19 | 751 | Paco Leyva, Orlando | 18 | 792 | 26359
PR | 110 | 12/27/19 | 753 | Ramos Herrera, Franklin J | 6 | 180 | 26361
PR | 110 | 01/03/20 | 3 | Anderson, Richard P | 9 | 441 | 26385
PR | 110 | 01/03/20 | 13 | Chevez, Herson G | 4 | 104 | 26395
PR | 110 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo | 3 | 90 | 26418
PR | 110 | 01/03/20 | 44 | Lee, Ha Nul | 3 | 75 | 26427
PR | 110 | 01/03/20 | 50 | Martinez Reyes, Juan C | 5 | 185 | 26433
PR | 110 | 01/03/20 | 60 | Rivera, Jorge A | 2 | 76 | 26443
PR | 110 | 01/10/20 | 276 | Anderson, Richard P | 1 | 49 | 26463
PR | 110 | 01/10/20 | 323 | Martinez Reyes, Juan C | 7 | 259 | 26511
PR | 110 | 01/10/20 | 342 | Stahlschmidt, John P | 2 | 44 | 26530
PR | 110 | 03/06/20 | 42 | Anderson, Richard P | 7 | 343 | 27086
PR | 110 | 03/06/20 | 45 | Barbosa, Michael S | 16 | 528 | 27089
PR | 110 | 03/06/20 | 46 | Barnhart, Joseph N | 6.5 | 351 | 27090
PR | 110 | 03/06/20 | 52 | Chevez, Herson G | 3 | 78 | 27096
PR | 110 | 03/06/20 | 81 | Lee, Ha Nul | 4 | 100 | 27125
PR | 110 | 03/06/20 | 86 | Martinez Reyes, Juan C | 16 | 592 | 27130
PR | 110 | 03/06/20 | 90 | Paco Leyva, Orlando | 8 | 352 | 27134
PR | 110 | 03/06/20 | 94 | Ramos Herrera, Franklin J | 8 | 240 | 27138
PR | 110 | 03/13/20 | 307 | Anderson, Richard P | 7 | 514.5 | 27167
PR | 110 | 03/13/20 | 307 | Anderson, Richard P | 26 | 1274 | 27167
PR | 110 | 03/13/20 | 310 | Barbosa, Michael S | 38 | 1254 | 27170
PR | 110 | 03/13/20 | 311 | Barnhart, Joseph N | 5 | 270 | 27171
PR | 110 | 03/13/20 | 313 | Benites Portillo, Marvin E | 7 | 304.5 | 27173
PR | 110 | 03/13/20 | 313 | Benites Portillo, Marvin E | 40 | 1160 | 27173
PR | 110 | 03/13/20 | 317 | Chevez, Herson G | 7 | 273 | 27177
PR | 110 | 03/13/20 | 317 | Chevez, Herson G | 40 | 1040 | 27177
PR | 110 | 03/13/20 | 330 | Galdamez, Dagoberto A | 24 | 792 | 27190
PR | 110 | 03/13/20 | 334 | Gonzalez Hernandez, Josue | 36 | 1296 | 27194
PR | 110 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo | 7 | 315 | 27197
PR | 110 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 27197
PR | 110 | 03/13/20 | 350 | Martinez Reyes, Juan C | 6.5 | 360.75 | 27211
PR | 110 | 03/13/20 | 350 | Martinez Reyes, Juan C | 40 | 1480 | 27211
PR | 110 | 03/13/20 | 354 | Paco Leyva, Orlando | 16 | 704 | 27215
PR | 110 | 03/13/20 | 354 | Paco Leyva, Orlando | 7 | 462 | 27215
PR | 110 | 03/13/20 | 358 | Ramos Herrera, Franklin J | 12 | 360 | 27219
PR | 110 | 03/20/20 | 565 | Anderson, Richard P | 6 | 294 | 27245
PR | 110 | 03/20/20 | 568 | Barbosa, Michael S | 24 | 792 | 27248
PR | 110 | 03/20/20 | 571 | Benites Portillo, Marvin E | 16 | 464 | 27251
PR | 110 | 03/20/20 | 575 | Chevez, Herson G | 16 | 416 | 27255
PR | 110 | 03/20/20 | 588 | Galdamez, Dagoberto A | 16 | 528 | 27268
PR | 110 | 03/20/20 | 592 | Gonzalez Hernandez, Josue | 14 | 504 | 27272
PR | 110 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 27275
PR | 110 | 03/20/20 | 608 | Martinez Reyes, Juan C | 24 | 888 | 27288
PR | 110 | 03/20/20 | 612 | Paco Leyva, Orlando | 11 | 484 | 27292
PR | 110 | 03/20/20 | 616 | Ramos Herrera, Franklin J | 11 | 330 | 27296
PR | 110 | 03/26/20 | 751 | Barbosa, Michael S | 17 | 561 | 27327
PR | 110 | 03/26/20 | 789 | Martinez Reyes, Juan C | 17 | 629 | 27365
PR | 110 | 05/01/20 | 2 | Anderson, Richard P | 4 | 196 | 27629
PR | 110 | 05/01/20 | 5 | Barbosa, Michael S | 8 | 264 | 27632
PR | 110 | 05/01/20 | 45 | Martinez Reyes, Juan C | 8 | 296 | 27672
PR | 110 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo | 3 | 90 | 28362
PR | 110 | 07/17/20 | 283 | Holmes, Anthony R | 3 | 132 | 28363
PR | 110 | 07/17/20 | 289 | Lee, Ha Nul | 3 | 75 | 28369
PR | 110 | 12/18/20 | 344 | Barnhart, Joseph N | 1 | 54 | 29370
PR | 111 | 06/21/19 | 667 | Paco Leyva, Orlando | 3 | 120 | 24153
PR | 111 | 06/21/19 | 669 | Ramos Herrera, Franklin J | 3 | 78 | 24155
PR | 111 | 07/05/19 | 8 | Anderson, Richard P | 1 | 47 | 24255
PR | 111 | 07/05/19 | 12 | Barnhart, Joseph N | 10 | 500 | 24259
PR | 111 | 07/05/19 | 36 | Gerard, Mitchell J | 16 | 640 | 24283
PR | 111 | 07/05/19 | 41 | Holmes, Anthony R | 40 | 1600 | 24288
PR | 111 | 07/05/19 | 43 | Hubbard, Justin A | 16 | 416 | 24290
PR | 111 | 07/05/19 | 52 | Martinez Reyes, Juan C | 23 | 759 | 24300
PR | 111 | 07/12/19 | 310 | Holmes, Anthony R | 32 | 1280 | 24362
PR | 111 | 07/12/19 | 321 | Martinez Reyes, Juan C | 19 | 627 | 24373
PR | 111 | 07/12/19 | 325 | Paco Leyva, Orlando | 8 | 320 | 24377
PR | 111 | 07/12/19 | 327 | Ramos Herrera, Franklin J | 8 | 208 | 24379
PR | 111 | 07/19/19 | 540 | Holmes, Anthony R | 8 | 320 | 24439
PR | 111 | 07/19/19 | 551 | Martinez Reyes, Juan C | 14 | 462 | 24450
PR | 111 | 07/26/19 | 612 | Anderson, Richard P | 4 | 188 | 24561
PR | 111 | 07/26/19 | 615 | Barbosa, Michael S | 24 | 696 | 24564
PR | 111 | 07/26/19 | 639 | Gonzalez Hernandez, Josue | 36 | 1152 | 24588
PR | 111 | 07/26/19 | 641 | Hernandez Gonzalez, Osbaldo | 24 | 624 | 24590
PR | 111 | 07/26/19 | 662 | Reyes Cruz, Denis A | 24 | 720 | 24611
PR | 111 | 08/02/19 | 4 | Anderson, Richard P | 2 | 94 | 24635
PR | 111 | 08/02/19 | 7 | Barbosa, Michael S | 40 | 1160 | 24638
PR | 111 | 08/02/19 | 31 | Gonzalez Hernandez, Josue | 24 | 768 | 24662
PR | 111 | 08/02/19 | 33 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 24664
PR | 111 | 08/02/19 | 42 | Lima Romero, Melvin A | 40 | 1400 | 24673
PR | 111 | 08/02/19 | 46 | Martinez Reyes, Juan C | 4 | 132 | 24677
PR | 111 | 08/02/19 | 50 | Paco Leyva, Orlando | 4 | 160 | 24681
PR | 111 | 08/02/19 | 56 | Rivera, Jorge A | 32 | 1120 | 24687
PR | 111 | 08/09/19 | 256 | Anderson, Richard P | 5 | 235 | 24709
PR | 111 | 08/09/19 | 259 | Barbosa, Michael S | 40 | 1160 | 24712
PR | 111 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo | 24 | 624 | 24739
PR | 111 | 08/09/19 | 295 | Lima Romero, Melvin A | 32 | 1120 | 24748
PR | 111 | 08/09/19 | 303 | Paco Leyva, Orlando | 15 | 600 | 24756
PR | 111 | 08/09/19 | 305 | Ramos Herrera, Franklin J | 12 | 312 | 24758
PR | 111 | 08/09/19 | 309 | Rivera, Jorge A | 32 | 1120 | 24762
PR | 111 | 08/16/19 | 563 | Anderson, Richard P | 3 | 141 | 24782
PR | 111 | 08/16/19 | 566 | Barbosa, Michael S | 24 | 696 | 24785
PR | 111 | 08/16/19 | 567 | Barnhart, Joseph N | 2 | 100 | 24786
PR | 111 | 08/16/19 | 590 | Gerard, Mitchell J | 4 | 160 | 24809
PR | 111 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo | 16 | 416 | 24812
PR | 111 | 08/16/19 | 602 | Lima Romero, Melvin A | 24 | 840 | 24821
PR | 111 | 08/16/19 | 610 | Paco Leyva, Orlando | 4 | 160 | 24829
PR | 111 | 08/16/19 | 616 | Rivera, Jorge A | 40 | 1400 | 24835
PR | 111 | 08/23/19 | 799 | Anderson, Richard P | 4 | 188 | 24857
PR | 111 | 08/23/19 | 847 | Paco Leyva, Orlando | 8 | 320 | 24905
PR | 111 | 08/23/19 | 849 | Ramos Herrera, Franklin J | 8 | 208 | 24907
PR | 111 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A | 8 | 256 | 24931
PR | 111 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo | 24 | 624 | 24963
PR | 111 | 08/30/19 | 1038 | Paco Leyva, Orlando | 8 | 320 | 24980
PR | 111 | 08/30/19 | 1040 | Ramos Herrera, Franklin J | 8 | 208 | 24982
PR | 111 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A | 8 | 256 | 25008
PR | 111 | 09/06/19 | 59 | Paco Leyva, Orlando | 2 | 80 | 25057
PR | 111 | 09/13/19 | 239 | Barnhart, Joseph N | 1 | 50 | 25088
PR | 111 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A | 16 | 512 | 25157
PR | 111 | 09/20/19 | 476 | Barnhart, Joseph N | 1 | 50 | 25162
PR | 111 | 09/20/19 | 482 | Chevez, Herson G | 16 | 368 | 25168
PR | 111 | 09/20/19 | 495 | Galdamez, Dagoberto A | 16 | 480 | 25181
PR | 111 | 09/20/19 | 520 | Paco Leyva, Orlando | 9 | 360 | 25206
PR | 111 | 09/20/19 | 522 | Ramos Herrera, Franklin J | 32 | 832 | 25208
PR | 111 | 09/27/19 | 627 | Amaya Gonzalez, Edilberto A | 40 | 1280 | 25232
PR | 111 | 09/27/19 | 638 | Chevez, Herson G | 32 | 736 | 25243
PR | 111 | 09/27/19 | 651 | Galdamez, Dagoberto A | 40 | 1200 | 25256
PR | 111 | 09/27/19 | 661 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 25266
PR | 111 | 09/27/19 | 663 | Holmes, Anthony R | 4 | 160 | 25268
PR | 111 | 09/27/19 | 679 | Paco Leyva, Orlando | 5 | 200 | 25284
PR | 111 | 09/27/19 | 681 | Ramos Herrera, Franklin J | 16 | 416 | 25286
PR | 111 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A | 28 | 896 | 25310
PR | 111 | 10/04/19 | 55 | Paco Leyva, Orlando | 4 | 160 | 25362
PR | 111 | 10/04/19 | 57 | Ramos Herrera, Franklin J | 5 | 130 | 25364
PR | 111 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A | 16 | 512 | 25391
PR | 111 | 10/11/19 | 309 | Paco Leyva, Orlando | 12 | 480 | 25443
PR | 111 | 10/11/19 | 311 | Ramos Herrera, Franklin J | 12 | 312 | 25445
PR | 111 | 10/11/19 | 319 | Rosas Olivares, Jorge C | 10 | 200 | 25453
PR | 111 | 10/11/19 | 329 | Velasquez Cruz, Denis M | 26 | 832 | 25463
PR | 111 | 10/11/19 | 330 | Velasquez Cruz, Osman N | 26 | 650 | 25464
PR | 111 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A | 18 | 576 | 25468
PR | 111 | 10/18/19 | 456 | Barbosa, Michael S | 8 | 232 | 25472
PR | 111 | 10/18/19 | 457 | Barnhart, Joseph N | 2 | 100 | 25473
PR | 111 | 10/18/19 | 494 | Lima Romero, Melvin A | 8 | 280 | 25511
PR | 111 | 10/18/19 | 502 | Paco Leyva, Orlando | 7 | 280 | 25519
PR | 111 | 10/18/19 | 504 | Ramos Herrera, Franklin J | 16 | 416 | 25521
PR | 111 | 11/01/19 | 8 | Barnhart, Joseph N | 2 | 108 | 25625
PR | 111 | 11/01/19 | 54 | Paco Leyva, Orlando | 4 | 176 | 25671
PR | 111 | 11/15/19 | 444 | Benites Portillo, Marvin E | 4 | 116 | 25779
PR | 111 | 11/15/19 | 460 | Galdamez, Dagoberto A | 4 | 132 | 25795
PR | 111 | 11/15/19 | 469 | Hoeg, Xavier A | 38 | 684 | 25805
PR | 111 | 11/15/19 | 470 | Holmes, Anthony R | 36 | 1584 | 25806
PR | 111 | 11/15/19 | 478 | Lima Romero, Melvin A | 8 | 304 | 25814
PR | 111 | 11/15/19 | 487 | Paco Leyva, Orlando | 3 | 132 | 25823
PR | 111 | 11/15/19 | 491 | Reyes Cruz, Denis A | 8 | 264 | 25827
PR | 111 | 11/15/19 | 493 | Rivera, Jorge A | 16 | 608 | 25829
PR | 111 | 11/15/19 | 508 | Velasquez Cruz, Osman N | 16 | 448 | 25844
PR | 111 | 11/22/19 | 615 | Benites Portillo, Marvin E | 30 | 870 | 25855
PR | 111 | 11/22/19 | 619 | Chevez, Herson G | 8 | 208 | 25859
PR | 111 | 11/22/19 | 649 | Lima Romero, Melvin A | 38 | 1444 | 25889
PR | 111 | 11/22/19 | 658 | Paco Leyva, Orlando | 7 | 308 | 25898
PR | 111 | 11/22/19 | 662 | Reyes Cruz, Denis A | 38 | 1254 | 25902
PR | 111 | 11/27/19 | 892 | Paco Leyva, Orlando | 1 | 44 | 25973
PR | 111 | 12/06/19 | 39 | Chevez, Herson G | 16 | 416 | 26011
PR | 111 | 12/06/19 | 52 | Galdamez, Dagoberto A | 8 | 264 | 26024
PR | 111 | 12/06/19 | 83 | Reyes Cruz, Denis A | 8 | 264 | 26055
PR | 111 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A | 2 | 72 | 26231
PR | 111 | 12/20/19 | 593 | Paco Leyva, Orlando | 5 | 220 | 26282
PR | 111 | 12/20/19 | 595 | Ramos Herrera, Franklin J | 2 | 60 | 26284
PR | 111 | 01/03/20 | 2 | Amaya Gonzalez, Edilberto A | 29 | 1044 | 26384
PR | 111 | 01/03/20 | 3 | Anderson, Richard P | 8 | 392 | 26385
PR | 111 | 01/03/20 | 9 | Benites Portillo, Marvin E | 29 | 841 | 26391
PR | 111 | 01/03/20 | 13 | Chevez, Herson G | 25 | 650 | 26395
PR | 111 | 01/03/20 | 27 | Galdamez, Dagoberto A | 29 | 957 | 26410
PR | 111 | 01/03/20 | 32 | Gonzalez Hernandez, Josue | 16 | 576 | 26415
PR | 111 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo | 10 | 300 | 26418
PR | 111 | 01/03/20 | 47 | Lovo, German G | 29 | 870 | 26430
PR | 111 | 01/03/20 | 56 | Ramos Herrera, Franklin J | 29 | 870 | 26439
PR | 111 | 01/03/20 | 60 | Rivera, Jorge A | 11 | 418 | 26443
PR | 111 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A | 32 | 1152 | 26462
PR | 111 | 01/10/20 | 276 | Anderson, Richard P | 5 | 245 | 26463
PR | 111 | 01/10/20 | 282 | Benites Portillo, Marvin E | 24 | 696 | 26469
PR | 111 | 01/10/20 | 286 | Chevez, Herson G | 34 | 884 | 26473
PR | 111 | 01/10/20 | 300 | Galdamez, Dagoberto A | 40 | 1320 | 26487
PR | 111 | 01/10/20 | 305 | Gonzalez Hernandez, Josue | 32 | 1152 | 26492
PR | 111 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 26495
PR | 111 | 01/10/20 | 320 | Lovo, German G | 25 | 750 | 26508
PR | 111 | 01/10/20 | 323 | Martinez Reyes, Juan C | 19.5 | 721.5 | 26511
PR | 111 | 01/10/20 | 327 | Paco Leyva, Orlando | 8 | 352 | 26515
PR | 111 | 01/10/20 | 329 | Ramos Herrera, Franklin J | 29 | 870 | 26517
PR | 111 | 01/10/20 | 333 | Rivera, Jorge A | 32 | 1216 | 26521
PR | 111 | 01/17/20 | 552 | Chevez, Herson G | 8 | 208 | 26551
PR | 111 | 01/24/20 | 724 | Paco Leyva, Orlando | 4 | 176 | 26667
PR | 111 | 01/31/20 | 875 | Lima Romero, Melvin A | 8 | 304 | 26736
PR | 111 | 01/31/20 | 884 | Paco Leyva, Orlando | 2 | 88 | 26745
PR | 111 | 01/31/20 | 891 | Rivera, Jorge A | 8 | 304 | 26752
PR | 111 | 02/07/20 | 74 | Paco Leyva, Orlando | 2 | 88 | 26822
PR | 111 | 02/28/20 | 680 | Anderson, Richard P | 3 | 147 | 27008
PR | 111 | 02/28/20 | 683 | Barbosa, Michael S | 24 | 792 | 27011
PR | 111 | 02/28/20 | 685 | Benites Portillo, Marvin E | 16 | 464 | 27013
PR | 111 | 02/28/20 | 703 | Galdamez, Dagoberto A | 8 | 264 | 27031
PR | 111 | 02/28/20 | 708 | Gonzalez Hernandez, Josue | 8 | 288 | 27036
PR | 111 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 27039
PR | 111 | 02/28/20 | 722 | Lovo, German G | 16 | 480 | 27050
PR | 111 | 02/28/20 | 724 | Martinez Reyes, Juan C | 21 | 777 | 27052
PR | 111 | 03/06/20 | 42 | Anderson, Richard P | 1 | 49 | 27086
PR | 111 | 03/06/20 | 45 | Barbosa, Michael S | 16 | 528 | 27089
PR | 111 | 03/06/20 | 48 | Benites Portillo, Marvin E | 16 | 464 | 27092
PR | 111 | 03/06/20 | 66 | Galdamez, Dagoberto A | 16 | 528 | 27110
PR | 111 | 03/06/20 | 70 | Gonzalez Hernandez, Josue | 13 | 468 | 27114
PR | 111 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 27117
PR | 111 | 03/06/20 | 84 | Lovo, German G | 24 | 720 | 27128
PR | 111 | 03/06/20 | 86 | Martinez Reyes, Juan C | 16 | 592 | 27130
PR | 111 | 03/06/20 | 98 | Rivera, Jorge A | 24 | 912 | 27142
PR | 111 | 03/26/20 | 751 | Barbosa, Michael S | 8 | 264 | 27327
PR | 111 | 03/26/20 | 779 | Holmes, Anthony R | 8 | 352 | 27355
PR | 111 | 05/15/20 | 309 | Ascencio, Jose L | 4 | 132 | 27787
PR | 111 | 05/15/20 | 335 | Gonzalez Hernandez, Josue | 4 | 144 | 27813
PR | 111 | 06/05/20 | 18 | Barnhart, Joseph N | 2 | 108 | 28008
PR | 111 | 06/12/20 | 220 | Barbosa, Michael S | 8 | 264 | 28104
PR | 111 | 06/12/20 | 240 | Holmes, Anthony R | 16 | 704 | 28124
PR | 111 | 06/12/20 | 245 | Lee, Ha Nul | 24 | 600 | 28130
PR | 111 | 06/12/20 | 256 | Rivera, Jorge A | 24 | 912 | 28141
PR | 111 | 06/19/20 | 377 | Barbosa, Michael S | 16 | 528 | 28154
PR | 111 | 06/19/20 | 394 | Gonzalez Hernandez, Josue | 32 | 1152 | 28171
PR | 111 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 28172
PR | 111 | 06/19/20 | 396 | Holmes, Anthony R | 26 | 1144 | 28173
PR | 111 | 06/19/20 | 401 | Lee, Ha Nul | 24 | 600 | 28178
PR | 111 | 06/19/20 | 404 | Martinez Reyes, Juan C | 2 | 74 | 28181
PR | 111 | 06/19/20 | 406 | Mendoza Morales, Jesus A | 8 | 256 | 28183
PR | 111 | 06/19/20 | 412 | Rivera, Jorge A | 24 | 912 | 28189
PR | 111 | 06/26/20 | 520 | Barbosa, Michael S | 12 | 396 | 28202
PR | 111 | 06/26/20 | 554 | Rivera, Jorge A | 32 | 1216 | 28236
PR | 111 | 07/02/20 | 4 | Ascencio, Jose L | 2 | 66 | 28247
PR | 111 | 07/02/20 | 22 | Gonzalez Hernandez, Josue | 12 | 432 | 28265
PR | 111 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo | 12 | 360 | 28266
PR | 111 | 07/02/20 | 24 | Holmes, Anthony R | 3 | 132 | 28267
PR | 111 | 07/02/20 | 32 | Martinez Reyes, Juan C | 2 | 74 | 28275
PR | 111 | 07/10/20 | 154 | Gonzalez Hernandez, Josue | 8 | 288 | 28313
PR | 111 | 07/10/20 | 156 | Holmes, Anthony R | 8 | 352 | 28315
PR | 111 | 07/17/20 | 265 | Barnhart, Joseph N | 3 | 162 | 28345
PR | 111 | 07/17/20 | 283 | Holmes, Anthony R | 7 | 308 | 28363
PR | 111 | 07/17/20 | 291 | Mackey, Cole J | 1 | 16 | 28371
PR | 111 | 07/31/20 | 499 | Barnhart, Joseph N | 2 | 108 | 28444
PR | 111 | 08/07/20 | 90 | Barnhart, Joseph N | 5 | 270 | 28493
PR | 111 | 08/07/20 | 107 | Holmes, Anthony R | 13.5 | 594 | 28510
PR | 111 | 09/11/20 | 77 | Barnhart, Joseph N | 2 | 108 | 28711
PR | 111 | 09/18/20 | 284 | Anderson, Richard P | 27 | 1323 | 28755
PR | 111 | 09/25/20 | 425 | Anderson, Richard P | 7 | 343 | 28802
PR | 111 | 09/25/20 | 426 | Ascencio, Jose L | 22 | 726 | 28803
PR | 111 | 09/25/20 | 446 | Gonzalez Hernandez, Josue | 8 | 288 | 28823
PR | 111 | 09/25/20 | 448 | Holmes, Anthony R | 11 | 484 | 28825
PR | 111 | 10/02/20 | 2 | Anderson, Richard P | 4 | 196 | 28850
PR | 111 | 10/02/20 | 3 | Ascencio, Jose L | 19 | 627 | 28851
PR | 111 | 10/02/20 | 6 | Barnhart, Joseph N | 3 | 162 | 28854
PR | 111 | 10/02/20 | 23 | Gonzalez Hernandez, Josue | 3 | 108 | 28871
PR | 111 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 28872
PR | 111 | 10/02/20 | 25 | Holmes, Anthony R | 8 | 352 | 28873
PR | 111 | 10/02/20 | 31 | Martinez Reyes, Juan C | 3 | 111 | 28879
PR | 111 | 10/16/20 | 316 | Holmes, Anthony R | 6 | 264 | 28970
PR | 112 | 05/10/19 | 164 | Barnhart, Joseph N | 2 | 150 | 23648
PR | 112 | 05/10/19 | 164 | Barnhart, Joseph N | 14 | 700 | 23648
PR | 112 | 05/10/19 | 208 | Paco Leyva, Orlando | 1 | 60 | 23692
PR | 112 | 05/10/19 | 208 | Paco Leyva, Orlando | 38 | 1520 | 23692
PR | 112 | 05/10/19 | 210 | Ramos Herrera, Franklin J | 1 | 39 | 23694
PR | 112 | 05/10/19 | 210 | Ramos Herrera, Franklin J | 38 | 988 | 23694
PR | 112 | 05/17/19 | 391 | Anderson, Richard P | 18 | 846 | 23722
PR | 112 | 05/17/19 | 395 | Barnhart, Joseph N | 7 | 350 | 23726
PR | 112 | 05/17/19 | 420 | Gonzalez Hernandez, Josue | 21 | 672 | 23751
PR | 112 | 05/24/19 | 604 | Anderson, Richard P | 9 | 423 | 23799
PR | 112 | 05/24/19 | 608 | Barnhart, Joseph N | 9 | 450 | 23803
PR | 112 | 05/24/19 | 632 | Gonzalez Hernandez, Josue | 11 | 352 | 23827
PR | 112 | 05/24/19 | 648 | Martinez Reyes, Juan C | 3 | 99 | 23843
PR | 112 | 05/31/19 | 877 | Anderson, Richard P | 2 | 94 | 23877
PR | 112 | 05/31/19 | 881 | Barnhart, Joseph N | 16 | 800 | 23881
PR | 112 | 05/31/19 | 922 | Martinez Reyes, Juan C | 12 | 396 | 23922
PR | 112 | 06/07/19 | 183 | Barnhart, Joseph N | 14 | 700 | 23958
PR | 112 | 06/07/19 | 223 | Martinez Reyes, Juan C | 18 | 594 | 23998
PR | 112 | 06/28/19 | 880 | Martinez Reyes, Juan C | 1 | 33 | 24224
PR | 112 | 07/26/19 | 616 | Barnhart, Joseph N | 2 | 100 | 24565
PR | 112 | 07/26/19 | 654 | Martinez Reyes, Juan C | 8 | 264 | 24603
PR | 112 | 07/26/19 | 658 | Paco Leyva, Orlando | 8 | 320 | 24607
PR | 112 | 07/26/19 | 660 | Ramos Herrera, Franklin J | 8 | 208 | 24609
PR | 112 | 08/02/19 | 8 | Barnhart, Joseph N | 3 | 150 | 24639
PR | 112 | 08/02/19 | 46 | Martinez Reyes, Juan C | 24 | 792 | 24677
PR | 112 | 08/02/19 | 50 | Paco Leyva, Orlando | 24 | 960 | 24681
PR | 112 | 08/02/19 | 52 | Ramos Herrera, Franklin J | 21 | 546 | 24683
PR | 112 | 08/09/19 | 260 | Barnhart, Joseph N | 4 | 200 | 24713
PR | 112 | 08/09/19 | 299 | Martinez Reyes, Juan C | 16 | 528 | 24752
PR | 112 | 08/09/19 | 303 | Paco Leyva, Orlando | 18 | 720 | 24756
PR | 112 | 08/09/19 | 305 | Ramos Herrera, Franklin J | 13 | 338 | 24758
PR | 112 | 08/16/19 | 566 | Barbosa, Michael S | 8 | 232 | 24785
PR | 112 | 08/16/19 | 567 | Barnhart, Joseph N | 3 | 150 | 24786
PR | 112 | 08/16/19 | 606 | Martinez Reyes, Juan C | 8 | 264 | 24825
PR | 112 | 08/16/19 | 610 | Paco Leyva, Orlando | 28 | 1120 | 24829
PR | 112 | 08/16/19 | 612 | Ramos Herrera, Franklin J | 27 | 702 | 24831
PR | 112 | 08/23/19 | 799 | Anderson, Richard P | 1 | 47 | 24857
PR | 112 | 08/23/19 | 843 | Martinez Reyes, Juan C | 8 | 264 | 24901
PR | 112 | 08/23/19 | 847 | Paco Leyva, Orlando | 8 | 320 | 24905
PR | 112 | 08/23/19 | 849 | Ramos Herrera, Franklin J | 8 | 208 | 24907
PR | 112 | 08/30/19 | 1038 | Paco Leyva, Orlando | 5 | 200 | 24980
PR | 112 | 11/01/19 | 8 | Barnhart, Joseph N | 1 | 54 | 25625
PR | 112 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A | 12 | 432 | 25923
PR | 112 | 11/27/19 | 847 | Barnhart, Joseph N | 4 | 216 | 25928
PR | 112 | 11/27/19 | 848 | Belcher, Jacob T | 6 | 126 | 25929
PR | 112 | 11/27/19 | 892 | Paco Leyva, Orlando | 19 | 836 | 25973
PR | 112 | 11/27/19 | 894 | Ramos Herrera, Franklin J | 19 | 570 | 25975
PR | 112 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A | 8 | 288 | 25999
PR | 112 | 12/06/19 | 29 | Anderson, Richard P | 1 | 49 | 26000
PR | 112 | 12/06/19 | 33 | Barnhart, Joseph N | 1 | 54 | 26005
PR | 112 | 12/06/19 | 34 | Belcher, Jacob T | 8 | 168 | 26006
PR | 112 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 26032
PR | 112 | 12/06/19 | 69 | Lee, Ha Nul | 16 | 400 | 26041
PR | 112 | 12/06/19 | 79 | Paco Leyva, Orlando | 8 | 352 | 26051
PR | 112 | 12/06/19 | 81 | Ramos Herrera, Franklin J | 8 | 240 | 26053
PR | 112 | 12/13/19 | 394 | Barnhart, Joseph N | 1 | 54 | 26159
PR | 112 | 12/13/19 | 395 | Belcher, Jacob T | 18 | 378 | 26160
PR | 112 | 12/13/19 | 430 | Lee, Ha Nul | 8 | 200 | 26195
PR | 112 | 12/13/19 | 440 | Paco Leyva, Orlando | 6 | 264 | 26206
PR | 112 | 12/13/19 | 442 | Ramos Herrera, Franklin J | 5 | 150 | 26208
PR | 112 | 01/31/20 | 837 | Barbosa, Michael S | 4 | 132 | 26697
PR | 112 | 01/31/20 | 838 | Barnhart, Joseph N | 2 | 108 | 26698
PR | 112 | 01/31/20 | 880 | Martinez Reyes, Juan C | 4 | 148 | 26741
PR | 112 | 01/31/20 | 882 | Mendoza Morales, Jesus A | 6 | 192 | 26743
PR | 112 | 01/31/20 | 884 | Paco Leyva, Orlando | 6 | 264 | 26745
PR | 112 | 02/07/20 | 25 | Anderson, Richard P | 10 | 490 | 26773
PR | 112 | 02/07/20 | 28 | Barbosa, Michael S | 26 | 858 | 26776
PR | 112 | 02/07/20 | 65 | Lee, Ha Nul | 22 | 550 | 26813
PR | 112 | 02/07/20 | 70 | Martinez Reyes, Juan C | 13 | 481 | 26818
PR | 112 | 02/07/20 | 72 | Mendoza Morales, Jesus A | 24 | 768 | 26820
PR | 112 | 02/07/20 | 81 | Rivera, Jorge A | 4 | 152 | 26829
PR | 112 | 02/07/20 | 101 | Young, Joshua S | 6 | 96 | 26849
PR | 112 | 02/14/20 | 275 | Lee, Ha Nul | 4 | 100 | 26891
PR | 112 | 02/14/20 | 280 | Martinez Reyes, Juan C | 8 | 296 | 26896
PR | 112 | 02/14/20 | 311 | Young, Joshua S | 4 | 64 | 26927
PR | 120 | 06/14/19 | 450 | Anderson, Richard P | 2 | 94 | 24031
PR | 120 | 06/14/19 | 454 | Barnhart, Joseph N | 6 | 300 | 24035
PR | 120 | 06/14/19 | 492 | Martinez Reyes, Juan C | 8 | 264 | 24073
PR | 120 | 06/21/19 | 622 | Barnhart, Joseph N | 7 | 350 | 24108
PR | 120 | 06/21/19 | 651 | Holmes, Anthony R | 24 | 960 | 24137
PR | 120 | 06/21/19 | 663 | Martinez Reyes, Juan C | 8 | 264 | 24149
PR | 120 | 06/28/19 | 840 | Barnhart, Joseph N | 2 | 100 | 24184
PR | 120 | 06/28/19 | 869 | Holmes, Anthony R | 8 | 320 | 24213
PR | 120 | 07/19/19 | 508 | Anderson, Richard P | 1 | 47 | 24407
PR | 120 | 07/19/19 | 512 | Barnhart, Joseph N | 2 | 100 | 24411
PR | 120 | 07/19/19 | 540 | Holmes, Anthony R | 32 | 1280 | 24439
PR | 120 | 07/26/19 | 612 | Anderson, Richard P | 13 | 611 | 24561
PR | 120 | 07/26/19 | 616 | Barnhart, Joseph N | 5 | 250 | 24565
PR | 120 | 07/26/19 | 617 | Belcher, Jacob T | 24 | 480 | 24566
PR | 120 | 07/26/19 | 642 | Hoeg, Xavier A | 24 | 408 | 24591
PR | 120 | 07/26/19 | 643 | Holmes, Anthony R | 40 | 1600 | 24592
PR | 120 | 07/26/19 | 649 | Lee, Ha Nul | 24 | 504 | 24598
PR | 120 | 07/26/19 | 656 | Mendoza Morales, Jesus A | 24 | 696 | 24605
PR | 120 | 07/26/19 | 668 | Rosas Olivares, Jorge C | 22.5 | 450 | 24617
PR | 120 | 08/02/19 | 4 | Anderson, Richard P | 6 | 282 | 24635
PR | 120 | 08/02/19 | 9 | Belcher, Jacob T | 40 | 800 | 24640
PR | 120 | 08/02/19 | 34 | Hoeg, Xavier A | 40 | 680 | 24665
PR | 120 | 08/02/19 | 35 | Holmes, Anthony R | 37 | 1480 | 24666
PR | 120 | 08/02/19 | 41 | Lee, Ha Nul | 32 | 672 | 24672
PR | 120 | 08/02/19 | 54 | Reyes Cruz, Denis A | 40 | 1200 | 24685
PR | 120 | 08/09/19 | 256 | Anderson, Richard P | 14 | 658 | 24709
PR | 120 | 08/09/19 | 260 | Barnhart, Joseph N | 11 | 550 | 24713
PR | 120 | 08/09/19 | 261 | Belcher, Jacob T | 40 | 800 | 24714
PR | 120 | 08/09/19 | 283 | Gerard, Mitchell J | 8 | 320 | 24736
PR | 120 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo | 8 | 208 | 24739
PR | 120 | 08/09/19 | 287 | Hoeg, Xavier A | 32 | 544 | 24740
PR | 120 | 08/09/19 | 288 | Holmes, Anthony R | 40 | 1600 | 24741
PR | 120 | 08/09/19 | 290 | Hubbard, Justin A | 16 | 416 | 24743
PR | 120 | 08/09/19 | 294 | Lee, Ha Nul | 40 | 840 | 24747
PR | 120 | 08/09/19 | 299 | Martinez Reyes, Juan C | 24 | 792 | 24752
PR | 120 | 08/09/19 | 305 | Ramos Herrera, Franklin J | 8 | 208 | 24758
PR | 120 | 08/09/19 | 307 | Reyes Cruz, Denis A | 40 | 1200 | 24760
PR | 120 | 08/16/19 | 563 | Anderson, Richard P | 12 | 564 | 24782
PR | 120 | 08/16/19 | 567 | Barnhart, Joseph N | 5 | 250 | 24786
PR | 120 | 08/16/19 | 568 | Belcher, Jacob T | 40 | 800 | 24787
PR | 120 | 08/16/19 | 590 | Gerard, Mitchell J | 4 | 160 | 24809
PR | 120 | 08/16/19 | 591 | Gonzalez Hernandez, Josue | 40 | 1280 | 24810
PR | 120 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo | 24 | 624 | 24812
PR | 120 | 08/16/19 | 594 | Hoeg, Xavier A | 40 | 680 | 24813
PR | 120 | 08/16/19 | 595 | Holmes, Anthony R | 40 | 1600 | 24814
PR | 120 | 08/16/19 | 597 | Hubbard, Justin A | 37 | 962 | 24816
PR | 120 | 08/16/19 | 601 | Lee, Ha Nul | 40 | 840 | 24820
PR | 120 | 08/16/19 | 606 | Martinez Reyes, Juan C | 24 | 792 | 24825
PR | 120 | 08/16/19 | 612 | Ramos Herrera, Franklin J | 5 | 130 | 24831
PR | 120 | 08/16/19 | 614 | Reyes Cruz, Denis A | 32 | 960 | 24833
PR | 120 | 08/23/19 | 799 | Anderson, Richard P | 21 | 987 | 24857
PR | 120 | 08/23/19 | 802 | Barbosa, Michael S | 8 | 232 | 24860
PR | 120 | 08/23/19 | 804 | Belcher, Jacob T | 40 | 800 | 24862
PR | 120 | 08/23/19 | 827 | Gonzalez Hernandez, Josue | 35 | 1120 | 24885
PR | 120 | 08/23/19 | 829 | Gutierrez Salas, Jose | 15 | 285 | 24887
PR | 120 | 08/23/19 | 830 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 24888
PR | 120 | 08/23/19 | 831 | Hoeg, Xavier A | 40 | 680 | 24889
PR | 120 | 08/23/19 | 832 | Holmes, Anthony R | 40 | 1600 | 24890
PR | 120 | 08/23/19 | 834 | Hubbard, Justin A | 40 | 1040 | 24892
PR | 120 | 08/23/19 | 838 | Lee, Ha Nul | 40 | 840 | 24896
PR | 120 | 08/23/19 | 843 | Martinez Reyes, Juan C | 8 | 264 | 24901
PR | 120 | 08/23/19 | 849 | Ramos Herrera, Franklin J | 8 | 208 | 24907
PR | 120 | 08/23/19 | 851 | Reyes Cruz, Denis A | 40 | 1200 | 24909
PR | 120 | 08/23/19 | 853 | Rivera, Jorge A | 40 | 1400 | 24911
PR | 120 | 08/30/19 | 990 | Anderson, Richard P | 16 | 752 | 24932
PR | 120 | 08/30/19 | 994 | Barnhart, Joseph N | 18 | 900 | 24936
PR | 120 | 08/30/19 | 995 | Belcher, Jacob T | 40 | 800 | 24937
PR | 120 | 08/30/19 | 1017 | Gerard, Mitchell J | 16 | 640 | 24959
PR | 120 | 08/30/19 | 1018 | Gonzalez Hernandez, Josue | 40 | 1280 | 24960
PR | 120 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo | 16 | 416 | 24963
PR | 120 | 08/30/19 | 1022 | Hoeg, Xavier A | 40 | 680 | 24964
PR | 120 | 08/30/19 | 1023 | Holmes, Anthony R | 24 | 960 | 24965
PR | 120 | 08/30/19 | 1025 | Hubbard, Justin A | 32 | 832 | 24967
PR | 120 | 08/30/19 | 1029 | Lee, Ha Nul | 40 | 840 | 24971
PR | 120 | 08/30/19 | 1034 | Martinez Reyes, Juan C | 16 | 528 | 24976
PR | 120 | 08/30/19 | 1038 | Paco Leyva, Orlando | 11 | 440 | 24980
PR | 120 | 08/30/19 | 1040 | Ramos Herrera, Franklin J | 24 | 624 | 24982
PR | 120 | 08/30/19 | 1042 | Reyes Cruz, Denis A | 40 | 1200 | 24984
PR | 120 | 08/30/19 | 1044 | Rivera, Jorge A | 38.5 | 1347.5 | 24986
PR | 120 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A | 24 | 768 | 25008
PR | 120 | 09/06/19 | 11 | Anderson, Richard P | 16 | 752 | 25009
PR | 120 | 09/06/19 | 15 | Barnhart, Joseph N | 11 | 550 | 25013
PR | 120 | 09/06/19 | 16 | Belcher, Jacob T | 8 | 160 | 25014
PR | 120 | 09/06/19 | 39 | Gonzalez Hernandez, Josue | 32 | 1024 | 25037
PR | 120 | 09/06/19 | 42 | Hernandez Gonzalez, Osbaldo | 31 | 806 | 25040
PR | 120 | 09/06/19 | 43 | Hoeg, Xavier A | 16 | 272 | 25041
PR | 120 | 09/06/19 | 44 | Holmes, Anthony R | 32 | 1280 | 25042
PR | 120 | 09/06/19 | 55 | Martinez Reyes, Juan C | 8 | 264 | 25053
PR | 120 | 09/06/19 | 59 | Paco Leyva, Orlando | 22 | 880 | 25057
PR | 120 | 09/06/19 | 61 | Ramos Herrera, Franklin J | 32 | 832 | 25059
PR | 120 | 09/06/19 | 63 | Reyes Cruz, Denis A | 32 | 960 | 25061
PR | 120 | 09/06/19 | 65 | Rivera, Jorge A | 29 | 1015 | 25063
PR | 120 | 09/13/19 | 234 | Amaya Gonzalez, Edilberto A | 38 | 1216 | 25083
PR | 120 | 09/13/19 | 235 | Anderson, Richard P | 40 | 1880 | 25084
PR | 120 | 09/13/19 | 239 | Barnhart, Joseph N | 2 | 100 | 25088
PR | 120 | 09/13/19 | 240 | Belcher, Jacob T | 24 | 480 | 25089
PR | 120 | 09/13/19 | 263 | Gonzalez Hernandez, Josue | 32 | 1024 | 25112
PR | 120 | 09/13/19 | 266 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 25115
PR | 120 | 09/13/19 | 268 | Holmes, Anthony R | 40 | 1600 | 25117
PR | 120 | 09/13/19 | 278 | Martinez Reyes, Juan C | 23 | 759 | 25127
PR | 120 | 09/13/19 | 282 | Paco Leyva, Orlando | 23 | 920 | 25131
PR | 120 | 09/13/19 | 284 | Ramos Herrera, Franklin J | 22 | 572 | 25133
PR | 120 | 09/13/19 | 286 | Reyes Cruz, Denis A | 40 | 1200 | 25135
PR | 120 | 09/13/19 | 288 | Rivera, Jorge A | 40 | 1400 | 25137
PR | 120 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A | 16 | 512 | 25157
PR | 120 | 09/20/19 | 472 | Anderson, Richard P | 32 | 1504 | 25158
PR | 120 | 09/20/19 | 476 | Barnhart, Joseph N | 12 | 600 | 25162
PR | 120 | 09/20/19 | 477 | Belcher, Jacob T | 40 | 800 | 25163
PR | 120 | 09/20/19 | 482 | Chevez, Herson G | 24 | 552 | 25168
PR | 120 | 09/20/19 | 495 | Galdamez, Dagoberto A | 24 | 720 | 25181
PR | 120 | 09/20/19 | 500 | Gonzalez Hernandez, Josue | 37 | 1184 | 25186
PR | 120 | 09/20/19 | 504 | Hernandez Gonzalez, Osbaldo | 39 | 1014 | 25190
PR | 120 | 09/20/19 | 505 | Hoeg, Xavier A | 27 | 459 | 25191
PR | 120 | 09/20/19 | 506 | Holmes, Anthony R | 40 | 1600 | 25192
PR | 120 | 09/20/19 | 514 | Lovo, German G | 18.5 | 499.5 | 25200
PR | 120 | 09/20/19 | 516 | Martinez Reyes, Juan C | 40 | 1320 | 25202
PR | 120 | 09/20/19 | 520 | Paco Leyva, Orlando | 28 | 1120 | 25206
PR | 120 | 09/20/19 | 522 | Ramos Herrera, Franklin J | 5 | 130 | 25208
PR | 120 | 09/20/19 | 524 | Reyes Cruz, Denis A | 31 | 930 | 25210
PR | 120 | 09/20/19 | 526 | Rivera, Jorge A | 40 | 1400 | 25212
PR | 120 | 09/20/19 | 529 | Romero Garza, Jesus I | 8 | 144 | 25215
PR | 120 | 09/27/19 | 628 | Anderson, Richard P | 16 | 752 | 25233
PR | 120 | 09/27/19 | 632 | Barnhart, Joseph N | 3 | 150 | 25237
PR | 120 | 09/27/19 | 633 | Belcher, Jacob T | 40 | 800 | 25238
PR | 120 | 09/27/19 | 638 | Chevez, Herson G | 8 | 184 | 25243
PR | 120 | 09/27/19 | 656 | Gonzalez Hernandez, Josue | 40 | 1280 | 25261
PR | 120 | 09/27/19 | 659 | Guillen, Adrian | 24 | 408 | 25264
PR | 120 | 09/27/19 | 662 | Hoeg, Xavier A | 32 | 544 | 25267
PR | 120 | 09/27/19 | 663 | Holmes, Anthony R | 36 | 1440 | 25268
PR | 120 | 09/27/19 | 670 | Lee, Ha Nul | 40 | 840 | 25275
PR | 120 | 09/27/19 | 675 | Martinez Reyes, Juan C | 40 | 1320 | 25280
PR | 120 | 09/27/19 | 679 | Paco Leyva, Orlando | 11 | 440 | 25284
PR | 120 | 09/27/19 | 683 | Reyes Cruz, Denis A | 40 | 1200 | 25288
PR | 120 | 09/27/19 | 685 | Rivera, Jorge A | 40 | 1400 | 25290
PR | 120 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A | 12 | 384 | 25310
PR | 120 | 10/04/19 | 4 | Anderson, Richard P | 37 | 1739 | 25311
PR | 120 | 10/04/19 | 8 | Barnhart, Joseph N | 3 | 150 | 25315
PR | 120 | 10/04/19 | 9 | Belcher, Jacob T | 40 | 800 | 25316
PR | 120 | 10/04/19 | 14 | Chevez, Herson G | 40 | 920 | 25321
PR | 120 | 10/04/19 | 27 | Galdamez, Dagoberto A | 40 | 1200 | 25334
PR | 120 | 10/04/19 | 32 | Gonzalez Hernandez, Josue | 40 | 1280 | 25339
PR | 120 | 10/04/19 | 34 | Guillen, Adrian | 3 | 51 | 25341
PR | 120 | 10/04/19 | 36 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 25343
PR | 120 | 10/04/19 | 37 | Hoeg, Xavier A | 32 | 544 | 25344
PR | 120 | 10/04/19 | 38 | Holmes, Anthony R | 40 | 1600 | 25345
PR | 120 | 10/04/19 | 45 | Lee, Ha Nul | 32 | 672 | 25352
PR | 120 | 10/04/19 | 51 | Martinez Reyes, Juan C | 40 | 1320 | 25358
PR | 120 | 10/04/19 | 55 | Paco Leyva, Orlando | 9 | 360 | 25362
PR | 120 | 10/04/19 | 57 | Ramos Herrera, Franklin J | 16 | 416 | 25364
PR | 120 | 10/04/19 | 59 | Reyes Cruz, Denis A | 24 | 720 | 25366
PR | 120 | 10/04/19 | 61 | Rivera, Jorge A | 39.5 | 1382.5 | 25368
PR | 120 | 10/04/19 | 75 | Velasquez Cruz, Denis M | 8 | 256 | 25382
PR | 120 | 10/04/19 | 76 | Velasquez Cruz, Osman N | 8 | 200 | 25383
PR | 120 | 10/04/19 | 94 | Guillen, Adrian | 8 | 136 | 25389
PR | 120 | 10/04/19 | 95 | Guillen, Adrian | 8 | -136 | 25389
PR | 120 | 10/11/19 | 96 | Guillen, Adrian | 8 | 136 | 25389
PR | 120 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A | 16 | 512 | 25391
PR | 120 | 10/11/19 | 259 | Anderson, Richard P | 32 | 1504 | 25392
PR | 120 | 10/11/19 | 263 | Barnhart, Joseph N | 1 | 75 | 25396
PR | 120 | 10/11/19 | 263 | Barnhart, Joseph N | 1 | 50 | 25396
PR | 120 | 10/11/19 | 264 | Belcher, Jacob T | 32 | 640 | 25397
PR | 120 | 10/11/19 | 269 | Chevez, Herson G | 40 | 920 | 25403
PR | 120 | 10/11/19 | 282 | Galdamez, Dagoberto A | 40 | 1200 | 25416
PR | 120 | 10/11/19 | 287 | Gonzalez Hernandez, Josue | 32 | 1024 | 25421
PR | 120 | 10/11/19 | 289 | Guillen, Adrian | 15 | 255 | 25423
PR | 120 | 10/11/19 | 291 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 25425
PR | 120 | 10/11/19 | 292 | Hoeg, Xavier A | 24 | 408 | 25426
PR | 120 | 10/11/19 | 293 | Holmes, Anthony R | 40 | 1600 | 25427
PR | 120 | 10/11/19 | 300 | Lee, Ha Nul | 40 | 840 | 25434
PR | 120 | 10/11/19 | 306 | Martinez Reyes, Juan C | 38 | 1254 | 25440
PR | 120 | 10/11/19 | 309 | Paco Leyva, Orlando | 26 | 1040 | 25443
PR | 120 | 10/11/19 | 311 | Ramos Herrera, Franklin J | 18 | 468 | 25445
PR | 120 | 10/11/19 | 313 | Reyes Cruz, Denis A | 16 | 480 | 25447
PR | 120 | 10/11/19 | 315 | Rivera, Jorge A | 40 | 1400 | 25449
PR | 120 | 10/11/19 | 319 | Rosas Olivares, Jorge C | 30 | 600 | 25453
PR | 120 | 10/11/19 | 329 | Velasquez Cruz, Denis M | 14 | 448 | 25463
PR | 120 | 10/11/19 | 330 | Velasquez Cruz, Osman N | 14 | 350 | 25464
PR | 120 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A | 22 | 704 | 25468
PR | 120 | 10/18/19 | 453 | Anderson, Richard P | 40 | 1880 | 25469
PR | 120 | 10/18/19 | 457 | Barnhart, Joseph N | 9 | 450 | 25473
PR | 120 | 10/18/19 | 458 | Belcher, Jacob T | 40 | 800 | 25474
PR | 120 | 10/18/19 | 459 | Benites Portillo, Marvin E | 32 | 864 | 25475
PR | 120 | 10/18/19 | 463 | Chevez, Herson G | 40 | 920 | 25479
PR | 120 | 10/18/19 | 475 | Galdamez, Dagoberto A | 40 | 1200 | 25491
PR | 120 | 10/18/19 | 480 | Gonzalez Hernandez, Josue | 40 | 1280 | 25496
PR | 120 | 10/18/19 | 482 | Guillen, Adrian | 38 | 646 | 25498
PR | 120 | 10/18/19 | 484 | Hernandez Gonzalez, Osbaldo | 40 | 1040 | 25500
PR | 120 | 10/18/19 | 485 | Hoeg, Xavier A | 24 | 408 | 25501
PR | 120 | 10/18/19 | 486 | Holmes, Anthony R | 40 | 1600 | 25502
PR | 120 | 10/18/19 | 493 | Lee, Ha Nul | 40 | 840 | 25510
PR | 120 | 10/18/19 | 494 | Lima Romero, Melvin A | 8 | 280 | 25511
PR | 120 | 10/18/19 | 499 | Martinez Reyes, Juan C | 24 | 792 | 25516
PR | 120 | 10/18/19 | 502 | Paco Leyva, Orlando | 19 | 760 | 25519
PR | 120 | 10/18/19 | 504 | Ramos Herrera, Franklin J | 24 | 624 | 25521
PR | 120 | 10/18/19 | 506 | Reyes Cruz, Denis A | 28 | 840 | 25523
PR | 120 | 10/18/19 | 508 | Rivera, Jorge A | 29 | 1015 | 25525
PR | 120 | 10/18/19 | 517 | Stahlschmidt, John P | 8 | 152 | 25534
PR | 120 | 10/18/19 | 522 | Velasquez Cruz, Denis M | 40 | 1280 | 25539
PR | 120 | 10/18/19 | 523 | Velasquez Cruz, Osman N | 40 | 1000 | 25540
PR | 120 | 10/25/19 | 587 | Amaya Gonzalez, Edilberto A | 36 | 1152 | 25544
PR | 120 | 10/25/19 | 588 | Anderson, Richard P | 29 | 1363 | 25545
PR | 120 | 10/25/19 | 592 | Barnhart, Joseph N | 8 | 400 | 25549
PR | 120 | 10/25/19 | 593 | Belcher, Jacob T | 36 | 720 | 25550
PR | 120 | 10/25/19 | 594 | Benites Portillo, Marvin E | 16 | 432 | 25551
PR | 120 | 10/25/19 | 599 | Chevez, Herson G | 36 | 828 | 25556
PR | 120 | 10/25/19 | 610 | Galdamez, Dagoberto A | 28 | 840 | 25567
PR | 120 | 10/25/19 | 615 | Gonzalez Hernandez, Josue | 31 | 992 | 25572
PR | 120 | 10/25/19 | 617 | Guillen, Adrian | 12 | 204 | 25574
PR | 120 | 10/25/19 | 618 | Gutierrez Salas, Jose | 16 | 304 | 25575
PR | 120 | 10/25/19 | 619 | Hernandez Gonzalez, Osbaldo | 36 | 936 | 25576
PR | 120 | 10/25/19 | 620 | Hoeg, Xavier A | 28 | 476 | 25577
PR | 120 | 10/25/19 | 621 | Holmes, Anthony R | 28 | 1120 | 25578
PR | 120 | 10/25/19 | 628 | Lee, Ha Nul | 36 | 756 | 25585
PR | 120 | 10/25/19 | 631 | Lovo, German G | 16 | 432 | 25588
PR | 120 | 10/25/19 | 634 | Martinez Reyes, Juan C | 29 | 957 | 25591
PR | 120 | 10/25/19 | 638 | Paco Leyva, Orlando | 29 | 1160 | 25595
PR | 120 | 10/25/19 | 640 | Ramos Herrera, Franklin J | 36 | 936 | 25597
PR | 120 | 10/25/19 | 642 | Reyes Cruz, Denis A | 24 | 720 | 25599
PR | 120 | 10/25/19 | 644 | Rivera, Jorge A | 36 | 1260 | 25601
PR | 120 | 10/25/19 | 653 | Stahlschmidt, John P | 32 | 608 | 25610
PR | 120 | 10/25/19 | 658 | Velasquez Cruz, Denis M | 36 | 1152 | 25615
PR | 120 | 10/25/19 | 659 | Velasquez Cruz, Osman N | 36 | 900 | 25616
PR | 120 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A | 37 | 1332 | 25620
PR | 120 | 11/01/19 | 4 | Anderson, Richard P | 22 | 1078 | 25621
PR | 120 | 11/01/19 | 7 | Barbosa, Michael S | 23 | 759 | 25624
PR | 120 | 11/01/19 | 8 | Barnhart, Joseph N | 5 | 270 | 25625
PR | 120 | 11/01/19 | 9 | Belcher, Jacob T | 40 | 840 | 25626
PR | 120 | 11/01/19 | 10 | Benites Portillo, Marvin E | 32 | 928 | 25627
PR | 120 | 11/01/19 | 14 | Chevez, Herson G | 40 | 1040 | 25631
PR | 120 | 11/01/19 | 26 | Galdamez, Dagoberto A | 40 | 1320 | 25643
PR | 120 | 11/01/19 | 33 | Guillen, Adrian | 32 | 544 | 25650
PR | 120 | 11/01/19 | 34 | Gutierrez Salas, Jose | 8 | 152 | 25651
PR | 120 | 11/01/19 | 35 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 25652
PR | 120 | 11/01/19 | 36 | Hoeg, Xavier A | 26 | 468 | 25653
PR | 120 | 11/01/19 | 37 | Holmes, Anthony R | 22 | 968 | 25654
PR | 120 | 11/01/19 | 44 | Lee, Ha Nul | 16 | 400 | 25661
PR | 120 | 11/01/19 | 50 | Martinez Reyes, Juan C | 32 | 1184 | 25667
PR | 120 | 11/01/19 | 52 | Mendoza Morales, Jesus A | 2 | 64 | 25669
PR | 120 | 11/01/19 | 54 | Paco Leyva, Orlando | 17 | 748 | 25671
PR | 120 | 11/01/19 | 56 | Ramos Herrera, Franklin J | 32 | 960 | 25673
PR | 120 | 11/01/19 | 58 | Reyes Cruz, Denis A | 29 | 957 | 25675
PR | 120 | 11/01/19 | 60 | Rivera, Jorge A | 40 | 1520 | 25677
PR | 120 | 11/01/19 | 69 | Stahlschmidt, John P | 40 | 880 | 25686
PR | 120 | 11/01/19 | 74 | Velasquez Cruz, Denis M | 32 | 1120 | 25691
PR | 120 | 11/01/19 | 75 | Velasquez Cruz, Osman N | 32 | 896 | 25692
PR | 120 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A | 26 | 936 | 25696
PR | 120 | 11/08/19 | 178 | Anderson, Richard P | 25 | 1225 | 25697
PR | 120 | 11/08/19 | 181 | Barbosa, Michael S | 40 | 1320 | 25700
PR | 120 | 11/08/19 | 183 | Belcher, Jacob T | 10 | 210 | 25702
PR | 120 | 11/08/19 | 184 | Benites Portillo, Marvin E | 32 | 928 | 25703
PR | 120 | 11/08/19 | 188 | Chevez, Herson G | 38 | 988 | 25707
PR | 120 | 11/08/19 | 205 | Gonzalez Hernandez, Josue | 8 | 288 | 25724
PR | 120 | 11/08/19 | 207 | Guillen, Adrian | 16 | 272 | 25726
PR | 120 | 11/08/19 | 208 | Gutierrez Salas, Jose | 23 | 437 | 25727
PR | 120 | 11/08/19 | 209 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 25728
PR | 120 | 11/08/19 | 210 | Hoeg, Xavier A | 32 | 576 | 25729
PR | 120 | 11/08/19 | 218 | Lee, Ha Nul | 10 | 250 | 25737
PR | 120 | 11/08/19 | 221 | Lovo, German G | 23 | 690 | 25740
PR | 120 | 11/08/19 | 226 | Mendoza Morales, Jesus A | 24 | 768 | 25745
PR | 120 | 11/08/19 | 228 | Paco Leyva, Orlando | 5 | 220 | 25747
PR | 120 | 11/08/19 | 230 | Ramos Herrera, Franklin J | 6 | 180 | 25749
PR | 120 | 11/08/19 | 232 | Reyes Cruz, Denis A | 32 | 1056 | 25751
PR | 120 | 11/08/19 | 234 | Rivera, Jorge A | 32 | 1216 | 25753
PR | 120 | 11/08/19 | 243 | Stahlschmidt, John P | 29 | 638 | 25762
PR | 120 | 11/08/19 | 248 | Velasquez Cruz, Denis M | 40 | 1400 | 25767
PR | 120 | 11/08/19 | 249 | Velasquez Cruz, Osman N | 40 | 1120 | 25768
PR | 120 | 11/15/19 | 437 | Amaya Gonzalez, Edilberto A | 40 | 1440 | 25772
PR | 120 | 11/15/19 | 438 | Anderson, Richard P | 30 | 1470 | 25773
PR | 120 | 11/15/19 | 441 | Barbosa, Michael S | 32 | 1056 | 25776
PR | 120 | 11/15/19 | 443 | Belcher, Jacob T | 32 | 672 | 25778
PR | 120 | 11/15/19 | 444 | Benites Portillo, Marvin E | 36 | 1044 | 25779
PR | 120 | 11/15/19 | 448 | Chevez, Herson G | 39.5 | 1027 | 25783
PR | 120 | 11/15/19 | 460 | Galdamez, Dagoberto A | 36 | 1188 | 25795
PR | 120 | 11/15/19 | 467 | Gutierrez Salas, Jose | 24 | 456 | 25803
PR | 120 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 25804
PR | 120 | 11/15/19 | 470 | Holmes, Anthony R | 4 | 176 | 25806
PR | 120 | 11/15/19 | 477 | Lee, Ha Nul | 32 | 800 | 25813
PR | 120 | 11/15/19 | 478 | Lima Romero, Melvin A | 16 | 608 | 25814
PR | 120 | 11/15/19 | 480 | Lovo, German G | 8 | 240 | 25816
PR | 120 | 11/15/19 | 483 | Martinez Reyes, Juan C | 8 | 296 | 25819
PR | 120 | 11/15/19 | 487 | Paco Leyva, Orlando | 24 | 1056 | 25823
PR | 120 | 11/15/19 | 489 | Ramos Herrera, Franklin J | 30 | 900 | 25825
PR | 120 | 11/15/19 | 491 | Reyes Cruz, Denis A | 32 | 1056 | 25827
PR | 120 | 11/15/19 | 493 | Rivera, Jorge A | 24 | 912 | 25829
PR | 120 | 11/15/19 | 502 | Stahlschmidt, John P | 32 | 704 | 25838
PR | 120 | 11/15/19 | 507 | Velasquez Cruz, Denis M | 40 | 1400 | 25843
PR | 120 | 11/15/19 | 508 | Velasquez Cruz, Osman N | 24 | 672 | 25844
PR | 120 | 11/22/19 | 608 | Amaya Gonzalez, Edilberto A | 38 | 1368 | 25848
PR | 120 | 11/22/19 | 609 | Anderson, Richard P | 24 | 1176 | 25849
PR | 120 | 11/22/19 | 612 | Barbosa, Michael S | 38 | 1254 | 25852
PR | 120 | 11/22/19 | 613 | Barnhart, Joseph N | 14 | 756 | 25853
PR | 120 | 11/22/19 | 614 | Belcher, Jacob T | 38 | 798 | 25854
PR | 120 | 11/22/19 | 615 | Benites Portillo, Marvin E | 8 | 232 | 25855
PR | 120 | 11/22/19 | 619 | Chevez, Herson G | 30 | 780 | 25859
PR | 120 | 11/22/19 | 631 | Galdamez, Dagoberto A | 38 | 1254 | 25871
PR | 120 | 11/22/19 | 639 | Hernandez Gonzalez, Osbaldo | 38 | 1140 | 25879
PR | 120 | 11/22/19 | 640 | Hoeg, Xavier A | 34 | 612 | 25880
PR | 120 | 11/22/19 | 641 | Holmes, Anthony R | 38 | 1672 | 25881
PR | 120 | 11/22/19 | 648 | Lee, Ha Nul | 32 | 800 | 25888
PR | 120 | 11/22/19 | 654 | Martinez Reyes, Juan C | 38 | 1406 | 25894
PR | 120 | 11/22/19 | 656 | Mendoza Morales, Jesus A | 22 | 704 | 25896
PR | 120 | 11/22/19 | 658 | Paco Leyva, Orlando | 28 | 1232 | 25898
PR | 120 | 11/22/19 | 660 | Ramos Herrera, Franklin J | 38 | 1140 | 25900
PR | 120 | 11/22/19 | 664 | Rivera, Jorge A | 38 | 1444 | 25904
PR | 120 | 11/22/19 | 673 | Stahlschmidt, John P | 38 | 836 | 25913
PR | 120 | 11/22/19 | 678 | Velasquez Cruz, Denis M | 38 | 1330 | 25918
PR | 120 | 11/22/19 | 679 | Velasquez Cruz, Osman N | 38 | 1064 | 25919
PR | 120 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A | 28 | 1008 | 25923
PR | 120 | 11/27/19 | 843 | Anderson, Richard P | 11 | 539 | 25924
PR | 120 | 11/27/19 | 846 | Barbosa, Michael S | 31 | 1023 | 25927
PR | 120 | 11/27/19 | 847 | Barnhart, Joseph N | 11 | 594 | 25928
PR | 120 | 11/27/19 | 848 | Belcher, Jacob T | 18 | 378 | 25929
PR | 120 | 11/27/19 | 849 | Benites Portillo, Marvin E | 32 | 928 | 25930
PR | 120 | 11/27/19 | 853 | Chevez, Herson G | 40 | 1040 | 25934
PR | 120 | 11/27/19 | 865 | Galdamez, Dagoberto A | 32 | 1056 | 25946
PR | 120 | 11/27/19 | 872 | Gutierrez Salas, Jose | 14 | 266 | 25953
PR | 120 | 11/27/19 | 873 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 25954
PR | 120 | 11/27/19 | 874 | Hoeg, Xavier A | 30 | 540 | 25955
PR | 120 | 11/27/19 | 875 | Holmes, Anthony R | 24 | 1056 | 25956
PR | 120 | 11/27/19 | 882 | Lee, Ha Nul | 10 | 250 | 25963
PR | 120 | 11/27/19 | 883 | Lima Romero, Melvin A | 16 | 608 | 25964
PR | 120 | 11/27/19 | 885 | Lovo, German G | 40 | 1200 | 25966
PR | 120 | 11/27/19 | 888 | Martinez Reyes, Juan C | 24 | 888 | 25969
PR | 120 | 11/27/19 | 892 | Paco Leyva, Orlando | 18 | 792 | 25973
PR | 120 | 11/27/19 | 894 | Ramos Herrera, Franklin J | 21 | 630 | 25975
PR | 120 | 11/27/19 | 896 | Reyes Cruz, Denis A | 32 | 1056 | 25977
PR | 120 | 11/27/19 | 898 | Rivera, Jorge A | 40 | 1520 | 25979
PR | 120 | 11/27/19 | 907 | Stahlschmidt, John P | 32 | 704 | 25988
PR | 120 | 11/27/19 | 912 | Velasquez Cruz, Denis M | 38 | 1330 | 25993
PR | 120 | 11/27/19 | 913 | Velasquez Cruz, Osman N | 40 | 1120 | 25994
PR | 120 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A | 16 | 576 | 25999
PR | 120 | 12/06/19 | 29 | Anderson, Richard P | 22 | 1078 | 26000
PR | 120 | 12/06/19 | 32 | Barbosa, Michael S | 8 | 264 | 26003
PR | 120 | 12/06/19 | 33 | Barnhart, Joseph N | 2 | 108 | 26005
PR | 120 | 12/06/19 | 34 | Belcher, Jacob T | 24 | 504 | 26006
PR | 120 | 12/06/19 | 35 | Benites Portillo, Marvin E | 24 | 696 | 26007
PR | 120 | 12/06/19 | 39 | Chevez, Herson G | 16 | 416 | 26011
PR | 120 | 12/06/19 | 52 | Galdamez, Dagoberto A | 24 | 792 | 26024
PR | 120 | 12/06/19 | 57 | Gonzalez Hernandez, Josue | 8 | 288 | 26029
PR | 120 | 12/06/19 | 59 | Gutierrez Salas, Jose | 23 | 437 | 26031
PR | 120 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 26032
PR | 120 | 12/06/19 | 69 | Lee, Ha Nul | 16 | 400 | 26041
PR | 120 | 12/06/19 | 70 | Lima Romero, Melvin A | 6 | 228 | 26042
PR | 120 | 12/06/19 | 72 | Lovo, German G | 24 | 720 | 26044
PR | 120 | 12/06/19 | 75 | Martinez Reyes, Juan C | 32 | 1184 | 26047
PR | 120 | 12/06/19 | 77 | Mendoza Morales, Jesus A | 24 | 768 | 26049
PR | 120 | 12/06/19 | 79 | Paco Leyva, Orlando | 15 | 660 | 26051
PR | 120 | 12/06/19 | 81 | Ramos Herrera, Franklin J | 8 | 240 | 26053
PR | 120 | 12/06/19 | 83 | Reyes Cruz, Denis A | 16 | 528 | 26055
PR | 120 | 12/06/19 | 85 | Rivera, Jorge A | 24 | 912 | 26057
PR | 120 | 12/06/19 | 89 | Rosas Olivares, Jorge C | 8 | 160 | 26061
PR | 120 | 12/06/19 | 94 | Stahlschmidt, John P | 24 | 528 | 26066
PR | 120 | 12/06/19 | 99 | Velasquez Cruz, Denis M | 27 | 945 | 26071
PR | 120 | 12/06/19 | 100 | Velasquez Cruz, Osman N | 32 | 896 | 26072
PR | 120 | 12/13/19 | 389 | Amaya Gonzalez, Edilberto A | 32 | 1152 | 26154
PR | 120 | 12/13/19 | 390 | Anderson, Richard P | 39 | 1911 | 26155
PR | 120 | 12/13/19 | 393 | Barbosa, Michael S | 14 | 462 | 26158
PR | 120 | 12/13/19 | 394 | Barnhart, Joseph N | 7 | 378 | 26159
PR | 120 | 12/13/19 | 395 | Belcher, Jacob T | 22 | 462 | 26160
PR | 120 | 12/13/19 | 396 | Benites Portillo, Marvin E | 40 | 1160 | 26161
PR | 120 | 12/13/19 | 400 | Chevez, Herson G | 40 | 1040 | 26165
PR | 120 | 12/13/19 | 413 | Galdamez, Dagoberto A | 40 | 1320 | 26178
PR | 120 | 12/13/19 | 418 | Gonzalez Hernandez, Josue | 16 | 576 | 26183
PR | 120 | 12/13/19 | 420 | Gutierrez Salas, Jose | 32 | 608 | 26185
PR | 120 | 12/13/19 | 421 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 26186
PR | 120 | 12/13/19 | 430 | Lee, Ha Nul | 32 | 800 | 26195
PR | 120 | 12/13/19 | 431 | Lima Romero, Melvin A | 40 | 1520 | 26196
PR | 120 | 12/13/19 | 433 | Lovo, German G | 8 | 240 | 26198
PR | 120 | 12/13/19 | 436 | Martinez Reyes, Juan C | 39 | 1443 | 26202
PR | 120 | 12/13/19 | 438 | Mendoza Morales, Jesus A | 32 | 1024 | 26204
PR | 120 | 12/13/19 | 440 | Paco Leyva, Orlando | 25 | 1100 | 26206
PR | 120 | 12/13/19 | 442 | Ramos Herrera, Franklin J | 35 | 1050 | 26208
PR | 120 | 12/13/19 | 444 | Reyes Cruz, Denis A | 40 | 1320 | 26210
PR | 120 | 12/13/19 | 446 | Rivera, Jorge A | 32 | 1216 | 26212
PR | 120 | 12/13/19 | 450 | Rosas Olivares, Jorge C | 24 | 480 | 26216
PR | 120 | 12/13/19 | 455 | Stahlschmidt, John P | 40 | 880 | 26221
PR | 120 | 12/13/19 | 460 | Velasquez Cruz, Denis M | 36 | 1260 | 26226
PR | 120 | 12/13/19 | 461 | Velasquez Cruz, Osman N | 40 | 1120 | 26227
PR | 120 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A | 38 | 1368 | 26231
PR | 120 | 12/20/19 | 543 | Anderson, Richard P | 29 | 1421 | 26232
PR | 120 | 12/20/19 | 546 | Barbosa, Michael S | 24 | 792 | 26235
PR | 120 | 12/20/19 | 547 | Barnhart, Joseph N | 5 | 270 | 26236
PR | 120 | 12/20/19 | 548 | Belcher, Jacob T | 34 | 714 | 26237
PR | 120 | 12/20/19 | 549 | Benites Portillo, Marvin E | 40 | 1160 | 26238
PR | 120 | 12/20/19 | 553 | Chevez, Herson G | 36 | 936 | 26242
PR | 120 | 12/20/19 | 566 | Galdamez, Dagoberto A | 32 | 1056 | 26255
PR | 120 | 12/20/19 | 571 | Gonzalez Hernandez, Josue | 31.5 | 1134 | 26260
PR | 120 | 12/20/19 | 573 | Gutierrez Salas, Jose | 36 | 684 | 26262
PR | 120 | 12/20/19 | 574 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 26263
PR | 120 | 12/20/19 | 583 | Lee, Ha Nul | 27 | 675 | 26272
PR | 120 | 12/20/19 | 584 | Lima Romero, Melvin A | 16 | 608 | 26273
PR | 120 | 12/20/19 | 586 | Lovo, German G | 20 | 600 | 26275
PR | 120 | 12/20/19 | 589 | Martinez Reyes, Juan C | 31 | 1147 | 26278
PR | 120 | 12/20/19 | 591 | Mendoza Morales, Jesus A | 31 | 992 | 26280
PR | 120 | 12/20/19 | 593 | Paco Leyva, Orlando | 21 | 924 | 26282
PR | 120 | 12/20/19 | 595 | Ramos Herrera, Franklin J | 34 | 1020 | 26284
PR | 120 | 12/20/19 | 597 | Reyes Cruz, Denis A | 30 | 990 | 26286
PR | 120 | 12/20/19 | 599 | Rivera, Jorge A | 32 | 1216 | 26288
PR | 120 | 12/20/19 | 603 | Rosas Olivares, Jorge C | 24 | 480 | 26292
PR | 120 | 12/20/19 | 608 | Stahlschmidt, John P | 40 | 880 | 26297
PR | 120 | 12/20/19 | 613 | Velasquez Cruz, Denis M | 30 | 1050 | 26302
PR | 120 | 12/20/19 | 614 | Velasquez Cruz, Osman N | 30 | 840 | 26303
PR | 120 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A | 9 | 324 | 26307
PR | 120 | 12/27/19 | 700 | Anderson, Richard P | 5 | 245 | 26308
PR | 120 | 12/27/19 | 703 | Barbosa, Michael S | 10 | 330 | 26311
PR | 120 | 12/27/19 | 706 | Benites Portillo, Marvin E | 10 | 290 | 26314
PR | 120 | 12/27/19 | 710 | Chevez, Herson G | 10 | 260 | 26318
PR | 120 | 12/27/19 | 724 | Galdamez, Dagoberto A | 10 | 330 | 26332
PR | 120 | 12/27/19 | 729 | Gonzalez Hernandez, Josue | 24 | 864 | 26337
PR | 120 | 12/27/19 | 732 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 26340
PR | 120 | 12/27/19 | 741 | Lee, Ha Nul | 2 | 50 | 26349
PR | 120 | 12/27/19 | 742 | Lima Romero, Melvin A | 16 | 608 | 26350
PR | 120 | 12/27/19 | 744 | Lovo, German G | 10 | 300 | 26352
PR | 120 | 12/27/19 | 747 | Martinez Reyes, Juan C | 7 | 259 | 26355
PR | 120 | 12/27/19 | 749 | Mendoza Morales, Jesus A | 6 | 192 | 26357
PR | 120 | 12/27/19 | 751 | Paco Leyva, Orlando | 6 | 264 | 26359
PR | 120 | 12/27/19 | 753 | Ramos Herrera, Franklin J | 10 | 300 | 26361
PR | 120 | 12/27/19 | 755 | Reyes Cruz, Denis A | 16 | 528 | 26363
PR | 120 | 12/27/19 | 757 | Rivera, Jorge A | 24 | 912 | 26365
PR | 120 | 12/27/19 | 761 | Rosas Olivares, Jorge C | 24 | 480 | 26369
PR | 120 | 12/27/19 | 766 | Stahlschmidt, John P | 16 | 352 | 26374
PR | 120 | 01/03/20 | 3 | Anderson, Richard P | 12 | 588 | 26385
PR | 120 | 01/03/20 | 6 | Barbosa, Michael S | 16 | 528 | 26388
PR | 120 | 01/03/20 | 32 | Gonzalez Hernandez, Josue | 13 | 468 | 26415
PR | 120 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 26418
PR | 120 | 01/03/20 | 44 | Lee, Ha Nul | 26 | 650 | 26427
PR | 120 | 01/03/20 | 45 | Lima Romero, Melvin A | 16 | 608 | 26428
PR | 120 | 01/03/20 | 52 | Mendoza Morales, Jesus A | 21 | 672 | 26435
PR | 120 | 01/03/20 | 60 | Rivera, Jorge A | 16 | 608 | 26443
PR | 120 | 01/03/20 | 64 | Rosas Olivares, Jorge C | 21 | 420 | 26447
PR | 120 | 01/03/20 | 69 | Stahlschmidt, John P | 13 | 286 | 26452
PR | 120 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A | 3 | 108 | 26462
PR | 120 | 01/10/20 | 276 | Anderson, Richard P | 27 | 1323 | 26463
PR | 120 | 01/10/20 | 280 | Barnhart, Joseph N | 4 | 216 | 26467
PR | 120 | 01/10/20 | 282 | Benites Portillo, Marvin E | 8 | 232 | 26469
PR | 120 | 01/10/20 | 286 | Chevez, Herson G | 6 | 156 | 26473
PR | 120 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 26495
PR | 120 | 01/10/20 | 317 | Lee, Ha Nul | 38 | 950 | 26504
PR | 120 | 01/10/20 | 320 | Lovo, German G | 6 | 180 | 26508
PR | 120 | 01/10/20 | 325 | Mendoza Morales, Jesus A | 40 | 1280 | 26513
PR | 120 | 01/10/20 | 327 | Paco Leyva, Orlando | 8 | 352 | 26515
PR | 120 | 01/10/20 | 333 | Rivera, Jorge A | 8 | 304 | 26521
PR | 120 | 01/10/20 | 337 | Rosas Olivares, Jorge C | 13 | 260 | 26525
PR | 120 | 01/10/20 | 342 | Stahlschmidt, John P | 30 | 660 | 26530
PR | 120 | 01/17/20 | 542 | Anderson, Richard P | 27.5 | 1347.5 | 26541
PR | 120 | 01/17/20 | 545 | Barbosa, Michael S | 16 | 528 | 26544
PR | 120 | 01/17/20 | 546 | Barnhart, Joseph N | 3 | 162 | 26545
PR | 120 | 01/17/20 | 548 | Benites Portillo, Marvin E | 32 | 928 | 26547
PR | 120 | 01/17/20 | 552 | Chevez, Herson G | 24 | 624 | 26551
PR | 120 | 01/17/20 | 566 | Galdamez, Dagoberto A | 32 | 1056 | 26565
PR | 120 | 01/17/20 | 571 | Gonzalez Hernandez, Josue | 28.5 | 1026 | 26570
PR | 120 | 01/17/20 | 574 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 26573
PR | 120 | 01/17/20 | 583 | Lee, Ha Nul | 32 | 800 | 26582
PR | 120 | 01/17/20 | 584 | Lima Romero, Melvin A | 40 | 1520 | 26583
PR | 120 | 01/17/20 | 586 | Lovo, German G | 39 | 1170 | 26585
PR | 120 | 01/17/20 | 589 | Martinez Reyes, Juan C | 31 | 1147 | 26588
PR | 120 | 01/17/20 | 591 | Mendoza Morales, Jesus A | 24 | 768 | 26590
PR | 120 | 01/17/20 | 599 | Rivera, Jorge A | 40 | 1520 | 26598
PR | 120 | 01/17/20 | 608 | Stahlschmidt, John P | 24 | 528 | 26607
PR | 120 | 01/24/20 | 675 | Anderson, Richard P | 23 | 1127 | 26618
PR | 120 | 01/24/20 | 678 | Barbosa, Michael S | 16 | 528 | 26621
PR | 120 | 01/24/20 | 679 | Barnhart, Joseph N | 4 | 216 | 26622
PR | 120 | 01/24/20 | 681 | Benites Portillo, Marvin E | 40 | 1160 | 26624
PR | 120 | 01/24/20 | 685 | Chevez, Herson G | 40 | 1040 | 26628
PR | 120 | 01/24/20 | 698 | Galdamez, Dagoberto A | 40 | 1320 | 26641
PR | 120 | 01/24/20 | 703 | Gonzalez Hernandez, Josue | 8 | 288 | 26646
PR | 120 | 01/24/20 | 706 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 26649
PR | 120 | 01/24/20 | 714 | Lee, Ha Nul | 40 | 1000 | 26657
PR | 120 | 01/24/20 | 715 | Lima Romero, Melvin A | 16 | 608 | 26658
PR | 120 | 01/24/20 | 717 | Lovo, German G | 40 | 1200 | 26660
PR | 120 | 01/24/20 | 720 | Martinez Reyes, Juan C | 16 | 592 | 26663
PR | 120 | 01/24/20 | 722 | Mendoza Morales, Jesus A | 32 | 1024 | 26665
PR | 120 | 01/24/20 | 724 | Paco Leyva, Orlando | 13 | 572 | 26667
PR | 120 | 01/24/20 | 726 | Ramos Herrera, Franklin J | 24 | 720 | 26669
PR | 120 | 01/24/20 | 730 | Rivera, Jorge A | 40 | 1520 | 26673
PR | 120 | 01/24/20 | 739 | Stahlschmidt, John P | 40 | 880 | 26682
PR | 120 | 01/31/20 | 834 | Anderson, Richard P | 23 | 1127 | 26694
PR | 120 | 01/31/20 | 837 | Barbosa, Michael S | 36 | 1188 | 26697
PR | 120 | 01/31/20 | 838 | Barnhart, Joseph N | 1 | 54 | 26698
PR | 120 | 01/31/20 | 840 | Benites Portillo, Marvin E | 40 | 1160 | 26701
PR | 120 | 01/31/20 | 844 | Chevez, Herson G | 40 | 1040 | 26705
PR | 120 | 01/31/20 | 858 | Galdamez, Dagoberto A | 38 | 1254 | 26719
PR | 120 | 01/31/20 | 863 | Gonzalez Hernandez, Josue | 32 | 1152 | 26724
PR | 120 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo | 39 | 1170 | 26727
PR | 120 | 01/31/20 | 874 | Lee, Ha Nul | 37 | 925 | 26735
PR | 120 | 01/31/20 | 875 | Lima Romero, Melvin A | 21 | 798 | 26736
PR | 120 | 01/31/20 | 877 | Lovo, German G | 40 | 1200 | 26738
PR | 120 | 01/31/20 | 880 | Martinez Reyes, Juan C | 35 | 1295 | 26741
PR | 120 | 01/31/20 | 882 | Mendoza Morales, Jesus A | 34 | 1088 | 26743
PR | 120 | 01/31/20 | 884 | Paco Leyva, Orlando | 6 | 264 | 26745
PR | 120 | 01/31/20 | 887 | Ramos Herrera, Franklin J | 8 | 240 | 26748
PR | 120 | 01/31/20 | 891 | Rivera, Jorge A | 24 | 912 | 26752
PR | 120 | 01/31/20 | 895 | Rosas Olivares, Jorge C | 16 | 320 | 26756
PR | 120 | 01/31/20 | 900 | Stahlschmidt, John P | 3 | 66 | 26761
PR | 120 | 01/31/20 | 910 | Young, Joshua S | 19 | 304 | 26771
PR | 120 | 02/07/20 | 15 | Lovo, German G | 24 | 720 | 26699
PR | 120 | 02/07/20 | 25 | Anderson, Richard P | 17 | 833 | 26773
PR | 120 | 02/07/20 | 28 | Barbosa, Michael S | 14 | 462 | 26776
PR | 120 | 02/07/20 | 31 | Benites Portillo, Marvin E | 32 | 928 | 26779
PR | 120 | 02/07/20 | 35 | Chevez, Herson G | 40 | 1040 | 26783
PR | 120 | 02/07/20 | 48 | Galdamez, Dagoberto A | 40 | 1320 | 26796
PR | 120 | 02/07/20 | 53 | Gonzalez Hernandez, Josue | 24 | 864 | 26801
PR | 120 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 26804
PR | 120 | 02/07/20 | 65 | Lee, Ha Nul | 18 | 450 | 26813
PR | 120 | 02/07/20 | 66 | Lima Romero, Melvin A | 20 | 760 | 26814
PR | 120 | 02/07/20 | 68 | Lovo, German G | 8 | 240 | 26816
PR | 120 | 02/07/20 | 70 | Martinez Reyes, Juan C | 8 | 296 | 26818
PR | 120 | 02/07/20 | 72 | Mendoza Morales, Jesus A | 8 | 256 | 26820
PR | 120 | 02/07/20 | 74 | Paco Leyva, Orlando | 9 | 396 | 26822
PR | 120 | 02/07/20 | 77 | Ramos Herrera, Franklin J | 16 | 480 | 26825
PR | 120 | 02/07/20 | 81 | Rivera, Jorge A | 36 | 1368 | 26829
PR | 120 | 02/07/20 | 91 | Stahlschmidt, John P | 32 | 704 | 26839
PR | 120 | 02/07/20 | 101 | Young, Joshua S | 34 | 544 | 26849
PR | 120 | 02/14/20 | 235 | Anderson, Richard P | 30 | 1470 | 26851
PR | 120 | 02/14/20 | 238 | Barbosa, Michael S | 32 | 1056 | 26854
PR | 120 | 02/14/20 | 239 | Barnhart, Joseph N | 2 | 108 | 26855
PR | 120 | 02/14/20 | 241 | Benites Portillo, Marvin E | 37 | 1073 | 26857
PR | 120 | 02/14/20 | 245 | Chevez, Herson G | 28 | 728 | 26861
PR | 120 | 02/14/20 | 258 | Galdamez, Dagoberto A | 40 | 1320 | 26874
PR | 120 | 02/14/20 | 263 | Gonzalez Hernandez, Josue | 40 | 1440 | 26879
PR | 120 | 02/14/20 | 266 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 26882
PR | 120 | 02/14/20 | 275 | Lee, Ha Nul | 36 | 900 | 26891
PR | 120 | 02/14/20 | 276 | Lima Romero, Melvin A | 40 | 1520 | 26892
PR | 120 | 02/14/20 | 278 | Lovo, German G | 40 | 1200 | 26894
PR | 120 | 02/14/20 | 280 | Martinez Reyes, Juan C | 24 | 888 | 26896
PR | 120 | 02/14/20 | 282 | Mendoza Morales, Jesus A | 40 | 1280 | 26898
PR | 120 | 02/14/20 | 287 | Ramos Herrera, Franklin J | 4 | 120 | 26903
PR | 120 | 02/14/20 | 291 | Rivera, Jorge A | 40 | 1520 | 26907
PR | 120 | 02/14/20 | 301 | Stahlschmidt, John P | 24 | 528 | 26917
PR | 120 | 02/14/20 | 311 | Young, Joshua S | 36 | 576 | 26927
PR | 120 | 02/21/20 | 452 | Anderson, Richard P | 32 | 1568 | 26929
PR | 120 | 02/21/20 | 455 | Barbosa, Michael S | 38 | 1254 | 26932
PR | 120 | 02/21/20 | 458 | Benites Portillo, Marvin E | 39 | 1131 | 26935
PR | 120 | 02/21/20 | 462 | Chevez, Herson G | 23 | 598 | 26939
PR | 120 | 02/21/20 | 474 | Galdamez, Dagoberto A | 40 | 1320 | 26951
PR | 120 | 02/21/20 | 479 | Gonzalez Hernandez, Josue | 40 | 1440 | 26956
PR | 120 | 02/21/20 | 481 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 26958
PR | 120 | 02/21/20 | 490 | Lee, Ha Nul | 38 | 950 | 26967
PR | 120 | 02/21/20 | 491 | Lima Romero, Melvin A | 38 | 1444 | 26968
PR | 120 | 02/21/20 | 493 | Lovo, German G | 29 | 870 | 26970
PR | 120 | 02/21/20 | 495 | Martinez Reyes, Juan C | 8 | 296 | 26972
PR | 120 | 02/21/20 | 497 | Mendoza Morales, Jesus A | 40 | 1280 | 26974
PR | 120 | 02/21/20 | 507 | Rivera, Jorge A | 38 | 1444 | 26984
PR | 120 | 02/21/20 | 517 | Stahlschmidt, John P | 21 | 462 | 26994
PR | 120 | 02/21/20 | 527 | Young, Joshua S | 32 | 512 | 27005
PR | 120 | 02/28/20 | 680 | Anderson, Richard P | 31 | 1519 | 27008
PR | 120 | 02/28/20 | 683 | Barbosa, Michael S | 13 | 429 | 27011
PR | 120 | 02/28/20 | 684 | Barnhart, Joseph N | 2 | 108 | 27012
PR | 120 | 02/28/20 | 685 | Benites Portillo, Marvin E | 24 | 696 | 27013
PR | 120 | 02/28/20 | 690 | Chevez, Herson G | 32 | 832 | 27018
PR | 120 | 02/28/20 | 703 | Galdamez, Dagoberto A | 24 | 792 | 27031
PR | 120 | 02/28/20 | 708 | Gonzalez Hernandez, Josue | 32 | 1152 | 27036
PR | 120 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 27039
PR | 120 | 02/28/20 | 719 | Lee, Ha Nul | 40 | 1000 | 27047
PR | 120 | 02/28/20 | 720 | Lima Romero, Melvin A | 8 | 304 | 27048
PR | 120 | 02/28/20 | 722 | Lovo, German G | 24 | 720 | 27050
PR | 120 | 02/28/20 | 724 | Martinez Reyes, Juan C | 8 | 296 | 27052
PR | 120 | 02/28/20 | 726 | Mendoza Morales, Jesus A | 40 | 1280 | 27054
PR | 120 | 02/28/20 | 746 | Stahlschmidt, John P | 40 | 880 | 27074
PR | 120 | 02/28/20 | 756 | Young, Joshua S | 40 | 640 | 27084
PR | 120 | 03/06/20 | 42 | Anderson, Richard P | 25 | 1225 | 27086
PR | 120 | 03/06/20 | 46 | Barnhart, Joseph N | 5 | 270 | 27090
PR | 120 | 03/06/20 | 48 | Benites Portillo, Marvin E | 16 | 464 | 27092
PR | 120 | 03/06/20 | 52 | Chevez, Herson G | 37 | 962 | 27096
PR | 120 | 03/06/20 | 66 | Galdamez, Dagoberto A | 24 | 792 | 27110
PR | 120 | 03/06/20 | 70 | Gonzalez Hernandez, Josue | 5 | 180 | 27114
PR | 120 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 27117
PR | 120 | 03/06/20 | 81 | Lee, Ha Nul | 28 | 700 | 27125
PR | 120 | 03/06/20 | 82 | Lima Romero, Melvin A | 4 | 152 | 27126
PR | 120 | 03/06/20 | 84 | Lovo, German G | 16 | 480 | 27128
PR | 120 | 03/06/20 | 88 | Mendoza Morales, Jesus A | 32 | 1024 | 27132
PR | 120 | 03/06/20 | 98 | Rivera, Jorge A | 16 | 608 | 27142
PR | 120 | 03/06/20 | 102 | Rosas Olivares, Jorge C | 8 | 160 | 27146
PR | 120 | 03/06/20 | 108 | Stahlschmidt, John P | 40 | 880 | 27152
PR | 120 | 03/06/20 | 118 | Young, Joshua S | 40 | 640 | 27162
PR | 120 | 03/13/20 | 307 | Anderson, Richard P | 9 | 441 | 27167
PR | 120 | 03/13/20 | 311 | Barnhart, Joseph N | 4 | 324 | 27171
PR | 120 | 03/13/20 | 330 | Galdamez, Dagoberto A | 16 | 528 | 27190
PR | 120 | 03/13/20 | 334 | Gonzalez Hernandez, Josue | 4 | 144 | 27194
PR | 120 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 27197
PR | 120 | 03/13/20 | 345 | Lee, Ha Nul | 32 | 800 | 27206
PR | 120 | 03/13/20 | 348 | Lovo, German G | 40 | 1200 | 27209
PR | 120 | 03/13/20 | 352 | Mendoza Morales, Jesus A | 40 | 1280 | 27213
PR | 120 | 03/13/20 | 358 | Ramos Herrera, Franklin J | 4 | 120 | 27219
PR | 120 | 03/13/20 | 362 | Rivera, Jorge A | 38 | 1444 | 27223
PR | 120 | 03/13/20 | 366 | Rosas Olivares, Jorge C | 8 | 160 | 27227
PR | 120 | 03/13/20 | 372 | Stahlschmidt, John P | 40 | 880 | 27233
PR | 120 | 03/13/20 | 382 | Young, Joshua S | 40 | 640 | 27243
PR | 120 | 03/20/20 | 565 | Anderson, Richard P | 27 | 1323 | 27245
PR | 120 | 03/20/20 | 568 | Barbosa, Michael S | 8 | 264 | 27248
PR | 120 | 03/20/20 | 571 | Benites Portillo, Marvin E | 16 | 464 | 27251
PR | 120 | 03/20/20 | 592 | Gonzalez Hernandez, Josue | 26 | 936 | 27272
PR | 120 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 27275
PR | 120 | 03/20/20 | 603 | Lee, Ha Nul | 40 | 1000 | 27283
PR | 120 | 03/20/20 | 606 | Lovo, German G | 37 | 1110 | 27286
PR | 120 | 03/20/20 | 608 | Martinez Reyes, Juan C | 16 | 592 | 27288
PR | 120 | 03/20/20 | 610 | Mendoza Morales, Jesus A | 40 | 1280 | 27290
PR | 120 | 03/20/20 | 620 | Rivera, Jorge A | 24 | 912 | 27300
PR | 120 | 03/20/20 | 630 | Stahlschmidt, John P | 24 | 528 | 27310
PR | 120 | 03/20/20 | 640 | Young, Joshua S | 40 | 640 | 27320
PR | 120 | 03/26/20 | 748 | Anderson, Richard P | 33 | 1617 | 27324
PR | 120 | 03/26/20 | 751 | Barbosa, Michael S | 15 | 495 | 27327
PR | 120 | 03/26/20 | 754 | Benites Portillo, Marvin E | 40 | 1160 | 27330
PR | 120 | 03/26/20 | 758 | Chevez, Herson G | 24 | 624 | 27334
PR | 120 | 03/26/20 | 770 | Galdamez, Dagoberto A | 16 | 528 | 27346
PR | 120 | 03/26/20 | 774 | Gonzalez Hernandez, Josue | 38 | 1368 | 27350
PR | 120 | 03/26/20 | 777 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 27353
PR | 120 | 03/26/20 | 779 | Holmes, Anthony R | 5 | 220 | 27355
PR | 120 | 03/26/20 | 784 | Lee, Ha Nul | 24 | 600 | 27360
PR | 120 | 03/26/20 | 787 | Lovo, German G | 40 | 1200 | 27363
PR | 120 | 03/26/20 | 789 | Martinez Reyes, Juan C | 23 | 851 | 27365
PR | 120 | 03/26/20 | 791 | Mendoza Morales, Jesus A | 40 | 1280 | 27367
PR | 120 | 03/26/20 | 800 | Rivera, Jorge A | 40 | 1520 | 27376
PR | 120 | 03/26/20 | 809 | Stahlschmidt, John P | 8 | 176 | 27385
PR | 120 | 03/26/20 | 819 | Young, Joshua S | 24 | 384 | 27395
PR | 120 | 04/24/20 | 348 | Anderson, Richard P | 8 | 392 | 27552
PR | 120 | 04/24/20 | 351 | Barbosa, Michael S | 8 | 264 | 27555
PR | 120 | 04/24/20 | 391 | Martinez Reyes, Juan C | 8 | 296 | 27595
PR | 120 | 05/01/20 | 2 | Anderson, Richard P | 33 | 1617 | 27629
PR | 120 | 05/01/20 | 5 | Barbosa, Michael S | 32 | 1056 | 27632
PR | 120 | 05/01/20 | 45 | Martinez Reyes, Juan C | 32 | 1184 | 27672
PR | 120 | 05/08/20 | 153 | Anderson, Richard P | 35 | 1715 | 27708
PR | 120 | 05/08/20 | 156 | Barbosa, Michael S | 32 | 1056 | 27711
PR | 120 | 05/08/20 | 157 | Barnhart, Joseph N | 4 | 216 | 27712
PR | 120 | 05/08/20 | 183 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 27738
PR | 120 | 05/08/20 | 185 | Holmes, Anthony R | 8 | 352 | 27740
PR | 120 | 05/08/20 | 191 | Lee, Ha Nul | 8 | 200 | 27746
PR | 120 | 05/08/20 | 196 | Martinez Reyes, Juan C | 29 | 1073 | 27751
PR | 120 | 05/08/20 | 198 | Mendoza Morales, Jesus A | 8 | 256 | 27753
PR | 120 | 05/15/20 | 308 | Anderson, Richard P | 31 | 1519 | 27786
PR | 120 | 05/15/20 | 309 | Ascencio, Jose L | 28 | 924 | 27787
PR | 120 | 05/15/20 | 311 | Barbosa, Michael S | 40 | 1320 | 27789
PR | 120 | 05/15/20 | 312 | Barnhart, Joseph N | 1 | 54 | 27790
PR | 120 | 05/15/20 | 335 | Gonzalez Hernandez, Josue | 28 | 1008 | 27813
PR | 120 | 05/15/20 | 338 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 27816
PR | 120 | 05/15/20 | 340 | Holmes, Anthony R | 18 | 792 | 27818
PR | 120 | 05/15/20 | 346 | Lee, Ha Nul | 40 | 1000 | 27824
PR | 120 | 05/15/20 | 351 | Martinez Reyes, Juan C | 40 | 1480 | 27829
PR | 120 | 05/15/20 | 353 | Mendoza Morales, Jesus A | 35 | 1120 | 27831
PR | 120 | 05/22/20 | 463 | Anderson, Richard P | 23 | 1127 | 27863
PR | 120 | 05/22/20 | 464 | Ascencio, Jose L | 40 | 1320 | 27864
PR | 120 | 05/22/20 | 467 | Barnhart, Joseph N | 6.5 | 351 | 27867
PR | 120 | 05/22/20 | 483 | Eliassen, Cory H | 4 | 120 | 27883
PR | 120 | 05/22/20 | 489 | Gonzalez Hernandez, Josue | 40 | 1440 | 27889
PR | 120 | 05/22/20 | 490 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 27890
PR | 120 | 05/22/20 | 491 | Holmes, Anthony R | 22 | 968 | 27891
PR | 120 | 05/22/20 | 497 | Lee, Ha Nul | 40 | 1000 | 27897
PR | 120 | 05/22/20 | 502 | Martinez Reyes, Juan C | 39 | 1443 | 27902
PR | 120 | 05/22/20 | 504 | Mendoza Morales, Jesus A | 40 | 1280 | 27904
PR | 120 | 05/22/20 | 525 | Taylor, Evan R | 24 | 792 | 27925
PR | 120 | 05/29/20 | 591 | Anderson, Richard P | 13 | 637 | 27934
PR | 120 | 05/29/20 | 592 | Ascencio, Jose L | 32 | 1056 | 27935
PR | 120 | 05/29/20 | 594 | Barbosa, Michael S | 7 | 231 | 27937
PR | 120 | 05/29/20 | 595 | Barnhart, Joseph N | 8 | 432 | 27938
PR | 120 | 05/29/20 | 611 | Eliassen, Cory H | 24 | 720 | 27954
PR | 120 | 05/29/20 | 617 | Gonzalez Hernandez, Josue | 32 | 1152 | 27960
PR | 120 | 05/29/20 | 618 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 27961
PR | 120 | 05/29/20 | 619 | Holmes, Anthony R | 32 | 1408 | 27962
PR | 120 | 05/29/20 | 625 | Lee, Ha Nul | 32 | 800 | 27968
PR | 120 | 05/29/20 | 630 | Martinez Reyes, Juan C | 31.5 | 1165.5 | 27973
PR | 120 | 05/29/20 | 632 | Mendoza Morales, Jesus A | 24 | 768 | 27975
PR | 120 | 05/29/20 | 651 | Taylor, Evan R | 22.5 | 742.5 | 27994
PR | 120 | 06/05/20 | 14 | Anderson, Richard P | 28.5 | 1396.5 | 28004
PR | 120 | 06/05/20 | 15 | Ascencio, Jose L | 40 | 1320 | 28005
PR | 120 | 06/05/20 | 17 | Barbosa, Michael S | 8 | 264 | 28007
PR | 120 | 06/05/20 | 18 | Barnhart, Joseph N | 15 | 810 | 28008
PR | 120 | 06/05/20 | 36 | Gonzalez Hernandez, Josue | 40 | 1440 | 28026
PR | 120 | 06/05/20 | 37 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28027
PR | 120 | 06/05/20 | 38 | Holmes, Anthony R | 16 | 704 | 28028
PR | 120 | 06/05/20 | 43 | Lee, Ha Nul | 40 | 1000 | 28033
PR | 120 | 06/05/20 | 46 | Martinez Reyes, Juan C | 40 | 1480 | 28036
PR | 120 | 06/05/20 | 48 | Mendoza Morales, Jesus A | 40 | 1280 | 28038
PR | 120 | 06/05/20 | 54 | Rivera, Jorge A | 40 | 1520 | 28044
PR | 120 | 06/11/20 | 157 | Ascencio, Jose L | 16 | 528 | 28057
PR | 120 | 06/11/20 | 159 | Barbosa, Michael S | 8 | 264 | 28059
PR | 120 | 06/11/20 | 175 | Gonzalez Hernandez, Josue | 16 | 576 | 28075
PR | 120 | 06/11/20 | 176 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 28076
PR | 120 | 06/11/20 | 177 | Holmes, Anthony R | 16 | 704 | 28077
PR | 120 | 06/11/20 | 182 | Lee, Ha Nul | 8 | 200 | 28082
PR | 120 | 06/11/20 | 185 | Martinez Reyes, Juan C | 16 | 592 | 28085
PR | 120 | 06/11/20 | 187 | Mendoza Morales, Jesus A | 8 | 256 | 28087
PR | 120 | 06/11/20 | 193 | Rivera, Jorge A | 16 | 608 | 28093
PR | 120 | 06/12/20 | 218 | Ascencio, Jose L | 24 | 792 | 28102
PR | 120 | 06/12/20 | 221 | Barnhart, Joseph N | 22 | 1188 | 28105
PR | 120 | 06/12/20 | 238 | Gonzalez Hernandez, Josue | 24 | 864 | 28122
PR | 120 | 06/12/20 | 239 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 28123
PR | 120 | 06/12/20 | 248 | Martinez Reyes, Juan C | 16 | 592 | 28133
PR | 120 | 06/12/20 | 250 | Mendoza Morales, Jesus A | 24 | 768 | 28135
PR | 120 | 06/19/20 | 375 | Ascencio, Jose L | 32 | 1056 | 28152
PR | 120 | 06/19/20 | 377 | Barbosa, Michael S | 16 | 528 | 28154
PR | 120 | 06/19/20 | 378 | Barnhart, Joseph N | 14.5 | 783 | 28155
PR | 120 | 06/19/20 | 394 | Gonzalez Hernandez, Josue | 8 | 288 | 28171
PR | 120 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 28172
PR | 120 | 06/19/20 | 396 | Holmes, Anthony R | 11 | 484 | 28173
PR | 120 | 06/19/20 | 401 | Lee, Ha Nul | 8 | 200 | 28178
PR | 120 | 06/19/20 | 404 | Martinez Reyes, Juan C | 30 | 1110 | 28181
PR | 120 | 06/19/20 | 406 | Mendoza Morales, Jesus A | 32 | 1024 | 28183
PR | 120 | 06/19/20 | 412 | Rivera, Jorge A | 16 | 608 | 28189
PR | 120 | 06/26/20 | 518 | Ascencio, Jose L | 40 | 1320 | 28200
PR | 120 | 06/26/20 | 520 | Barbosa, Michael S | 28 | 924 | 28202
PR | 120 | 06/26/20 | 521 | Barnhart, Joseph N | 15 | 810 | 28203
PR | 120 | 06/26/20 | 536 | Gonzalez Hernandez, Josue | 36 | 1296 | 28218
PR | 120 | 06/26/20 | 537 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28219
PR | 120 | 06/26/20 | 538 | Holmes, Anthony R | 39.5 | 1738 | 28220
PR | 120 | 06/26/20 | 543 | Lee, Ha Nul | 40 | 1000 | 28225
PR | 120 | 06/26/20 | 546 | Martinez Reyes, Juan C | 32 | 1184 | 28228
PR | 120 | 06/26/20 | 548 | Mendoza Morales, Jesus A | 39 | 1248 | 28230
PR | 120 | 06/26/20 | 554 | Rivera, Jorge A | 8 | 304 | 28236
PR | 120 | 07/02/20 | 4 | Ascencio, Jose L | 38 | 1254 | 28247
PR | 120 | 07/02/20 | 6 | Barbosa, Michael S | 40 | 1320 | 28249
PR | 120 | 07/02/20 | 7 | Barnhart, Joseph N | 6 | 324 | 28250
PR | 120 | 07/02/20 | 22 | Gonzalez Hernandez, Josue | 28 | 1008 | 28265
PR | 120 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo | 28 | 840 | 28266
PR | 120 | 07/02/20 | 24 | Holmes, Anthony R | 34 | 1496 | 28267
PR | 120 | 07/02/20 | 29 | Lee, Ha Nul | 40 | 1000 | 28272
PR | 120 | 07/02/20 | 32 | Martinez Reyes, Juan C | 37 | 1369 | 28275
PR | 120 | 07/02/20 | 34 | Mendoza Morales, Jesus A | 16 | 512 | 28277
PR | 120 | 07/02/20 | 40 | Rivera, Jorge A | 40 | 1520 | 28283
PR | 120 | 07/10/20 | 137 | Ascencio, Jose L | 24 | 792 | 28296
PR | 120 | 07/10/20 | 139 | Barbosa, Michael S | 24 | 792 | 28298
PR | 120 | 07/10/20 | 140 | Barnhart, Joseph N | 16 | 864 | 28299
PR | 120 | 07/10/20 | 154 | Gonzalez Hernandez, Josue | 16 | 576 | 28313
PR | 120 | 07/10/20 | 155 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 28314
PR | 120 | 07/10/20 | 156 | Holmes, Anthony R | 16 | 704 | 28315
PR | 120 | 07/10/20 | 161 | Lee, Ha Nul | 24 | 600 | 28320
PR | 120 | 07/10/20 | 164 | Martinez Reyes, Juan C | 23 | 851 | 28323
PR | 120 | 07/10/20 | 172 | Rivera, Jorge A | 24 | 912 | 28331
PR | 120 | 07/17/20 | 262 | Ascencio, Jose L | 40 | 1320 | 28342
PR | 120 | 07/17/20 | 264 | Barbosa, Michael S | 39 | 1287 | 28344
PR | 120 | 07/17/20 | 265 | Barnhart, Joseph N | 15 | 810 | 28345
PR | 120 | 07/17/20 | 281 | Gonzalez Hernandez, Josue | 36 | 1296 | 28361
PR | 120 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo | 37 | 1110 | 28362
PR | 120 | 07/17/20 | 283 | Holmes, Anthony R | 28 | 1232 | 28363
PR | 120 | 07/17/20 | 289 | Lee, Ha Nul | 37 | 925 | 28369
PR | 120 | 07/17/20 | 292 | Martinez Reyes, Juan C | 38 | 1406 | 28372
PR | 120 | 07/17/20 | 300 | Rivera, Jorge A | 40 | 1520 | 28380
PR | 120 | 07/24/20 | 401 | Ascencio, Jose L | 40 | 1320 | 28393
PR | 120 | 07/24/20 | 403 | Barbosa, Michael S | 40 | 1320 | 28395
PR | 120 | 07/24/20 | 404 | Barnhart, Joseph N | 16 | 864 | 28396
PR | 120 | 07/24/20 | 420 | Gonzalez Hernandez, Josue | 16 | 576 | 28412
PR | 120 | 07/24/20 | 421 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28413
PR | 120 | 07/24/20 | 422 | Holmes, Anthony R | 40 | 1760 | 28414
PR | 120 | 07/24/20 | 428 | Lee, Ha Nul | 30.5 | 762.5 | 28420
PR | 120 | 07/24/20 | 430 | Martinez Reyes, Juan C | 40 | 1480 | 28422
PR | 120 | 07/24/20 | 438 | Rivera, Jorge A | 40 | 1520 | 28430
PR | 120 | 07/31/20 | 496 | Ascencio, Jose L | 40 | 1320 | 28441
PR | 120 | 07/31/20 | 498 | Barbosa, Michael S | 38 | 1254 | 28443
PR | 120 | 07/31/20 | 499 | Barnhart, Joseph N | 16 | 864 | 28444
PR | 120 | 07/31/20 | 516 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28462
PR | 120 | 07/31/20 | 517 | Holmes, Anthony R | 40 | 1760 | 28463
PR | 120 | 07/31/20 | 523 | Lee, Ha Nul | 16 | 400 | 28469
PR | 120 | 07/31/20 | 525 | Martinez Reyes, Juan C | 40 | 1480 | 28471
PR | 120 | 07/31/20 | 533 | Rivera, Jorge A | 16 | 608 | 28479
PR | 120 | 08/07/20 | 87 | Ascencio, Jose L | 40 | 1320 | 28490
PR | 120 | 08/07/20 | 89 | Barbosa, Michael S | 40 | 1320 | 28492
PR | 120 | 08/07/20 | 90 | Barnhart, Joseph N | 17 | 918 | 28493
PR | 120 | 08/07/20 | 106 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28509
PR | 120 | 08/07/20 | 107 | Holmes, Anthony R | 26.5 | 1166 | 28510
PR | 120 | 08/07/20 | 114 | Martinez Reyes, Juan C | 40 | 1480 | 28517
PR | 120 | 08/14/20 | 292 | Ascencio, Jose L | 40 | 1320 | 28532
PR | 120 | 08/14/20 | 294 | Barbosa, Michael S | 39.5 | 1303.5 | 28534
PR | 120 | 08/14/20 | 295 | Barnhart, Joseph N | 22 | 1188 | 28535
PR | 120 | 08/14/20 | 310 | Gonzalez Hernandez, Josue | 8 | 288 | 28550
PR | 120 | 08/14/20 | 311 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28551
PR | 120 | 08/14/20 | 312 | Holmes, Anthony R | 40 | 1760 | 28552
PR | 120 | 08/14/20 | 318 | Martinez Reyes, Juan C | 36 | 1332 | 28558
PR | 120 | 08/21/20 | 413 | Ascencio, Jose L | 40 | 1320 | 28573
PR | 120 | 08/21/20 | 415 | Barbosa, Michael S | 32 | 1056 | 28575
PR | 120 | 08/21/20 | 430 | Gonzalez Hernandez, Josue | 8 | 288 | 28590
PR | 120 | 08/21/20 | 431 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28591
PR | 120 | 08/21/20 | 432 | Holmes, Anthony R | 40 | 1760 | 28592
PR | 120 | 08/21/20 | 438 | Martinez Reyes, Juan C | 40 | 1480 | 28598
PR | 120 | 08/28/20 | 561 | Ascencio, Jose L | 32 | 1056 | 28614
PR | 120 | 08/28/20 | 563 | Barbosa, Michael S | 40 | 1320 | 28616
PR | 120 | 08/28/20 | 564 | Barnhart, Joseph N | 17 | 918 | 28617
PR | 120 | 08/28/20 | 579 | Gonzalez Hernandez, Josue | 40 | 1440 | 28632
PR | 120 | 08/28/20 | 580 | Hernandez Gonzalez, Osbaldo | 40 | 1200 | 28633
PR | 120 | 08/28/20 | 581 | Holmes, Anthony R | 16 | 704 | 28634
PR | 120 | 08/28/20 | 587 | Martinez Reyes, Juan C | 24 | 888 | 28640
PR | 120 | 09/04/20 | 3 | Anderson, Richard P | 24 | 1176 | 28659
PR | 120 | 09/04/20 | 4 | Ascencio, Jose L | 40 | 1320 | 28660
PR | 120 | 09/04/20 | 6 | Barbosa, Michael S | 40 | 1320 | 28662
PR | 120 | 09/04/20 | 7 | Barnhart, Joseph N | 31 | 1674 | 28663
PR | 120 | 09/04/20 | 23 | Gonzalez Hernandez, Josue | 40 | 1440 | 28679
PR | 120 | 09/04/20 | 24 | Hernandez Gonzalez, Osbaldo | 32 | 960 | 28680
PR | 120 | 09/04/20 | 25 | Holmes, Anthony R | 40 | 1760 | 28681
PR | 120 | 09/04/20 | 31 | Martinez Reyes, Juan C | 24 | 888 | 28687
PR | 120 | 09/11/20 | 73 | Anderson, Richard P | 20 | 980 | 28707
PR | 120 | 09/11/20 | 74 | Ascencio, Jose L | 32 | 1056 | 28708
PR | 120 | 09/11/20 | 76 | Barbosa, Michael S | 32 | 1056 | 28710
PR | 120 | 09/11/20 | 77 | Barnhart, Joseph N | 13 | 702 | 28711
PR | 120 | 09/11/20 | 94 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 28728
PR | 120 | 09/11/20 | 95 | Holmes, Anthony R | 8 | 352 | 28729
PR | 120 | 09/11/20 | 101 | Martinez Reyes, Juan C | 32 | 1184 | 28735
PR | 120 | 09/18/20 | 284 | Anderson, Richard P | 12 | 588 | 28755
PR | 120 | 09/18/20 | 285 | Ascencio, Jose L | 24 | 792 | 28756
PR | 120 | 09/18/20 | 287 | Barbosa, Michael S | 8 | 264 | 28758
PR | 120 | 09/18/20 | 288 | Barnhart, Joseph N | 9 | 486 | 28759
PR | 120 | 09/18/20 | 304 | Gonzalez Hernandez, Josue | 40 | 1440 | 28775
PR | 120 | 09/18/20 | 305 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 28776
PR | 120 | 09/18/20 | 306 | Holmes, Anthony R | 24 | 1056 | 28777
PR | 120 | 09/18/20 | 312 | Martinez Reyes, Juan C | 40 | 1480 | 28783
PR | 120 | 09/18/20 | 324 | Sanders, Allen O | 10 | 540 | 28795
PR | 120 | 09/25/20 | 425 | Anderson, Richard P | 17 | 833 | 28802
PR | 120 | 09/25/20 | 426 | Ascencio, Jose L | 2 | 66 | 28803
PR | 120 | 09/25/20 | 429 | Barnhart, Joseph N | 26 | 1404 | 28806
PR | 120 | 09/25/20 | 446 | Gonzalez Hernandez, Josue | 16 | 576 | 28823
PR | 120 | 09/25/20 | 447 | Hernandez Gonzalez, Osbaldo | 24 | 720 | 28824
PR | 120 | 09/25/20 | 448 | Holmes, Anthony R | 13 | 572 | 28825
PR | 120 | 09/25/20 | 454 | Martinez Reyes, Juan C | 24 | 888 | 28831
PR | 120 | 10/02/20 | 2 | Anderson, Richard P | 7.5 | 367.5 | 28850
PR | 120 | 10/02/20 | 3 | Ascencio, Jose L | 5 | 165 | 28851
PR | 120 | 10/02/20 | 6 | Barnhart, Joseph N | 12 | 648 | 28854
PR | 120 | 10/02/20 | 23 | Gonzalez Hernandez, Josue | 21 | 756 | 28871
PR | 120 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo | 16 | 480 | 28872
PR | 120 | 10/02/20 | 25 | Holmes, Anthony R | 16 | 704 | 28873
PR | 120 | 10/02/20 | 31 | Martinez Reyes, Juan C | 21 | 777 | 28879
PR | 120 | 10/09/20 | 151 | Anderson, Richard P | 23 | 1127 | 28900
PR | 120 | 10/09/20 | 155 | Barnhart, Joseph N | 8 | 432 | 28904
PR | 120 | 10/09/20 | 172 | Gonzalez Hernandez, Josue | 24 | 864 | 28921
PR | 120 | 10/09/20 | 173 | Hernandez Gonzalez, Osbaldo | 20.5 | 615 | 28922
PR | 120 | 10/09/20 | 174 | Holmes, Anthony R | 17.5 | 770 | 28923
PR | 120 | 10/09/20 | 180 | Martinez Reyes, Juan C | 24 | 888 | 28929
PR | 120 | 10/16/20 | 293 | Anderson, Richard P | 22.5 | 1102.5 | 28947
PR | 120 | 10/16/20 | 297 | Barnhart, Joseph N | 5 | 270 | 28951
PR | 120 | 10/16/20 | 314 | Gonzalez Hernandez, Josue | 16 | 576 | 28968
PR | 120 | 10/16/20 | 316 | Holmes, Anthony R | 10 | 440 | 28970
PR | 120 | 10/16/20 | 322 | Martinez Reyes, Juan C | 40 | 1480 | 28976
PR | 120 | 10/23/20 | 434 | Anderson, Richard P | 24 | 1176 | 28994
PR | 120 | 10/23/20 | 438 | Barnhart, Joseph N | 2 | 108 | 28998
PR | 120 | 10/23/20 | 457 | Holmes, Anthony R | 16 | 704 | 29017
PR | 120 | 10/23/20 | 463 | Martinez Reyes, Juan C | 16 | 592 | 29023
PR | 120 | 10/30/20 | 614 | Holmes, Anthony R | 16 | 704 | 29065
PR | 120 | 11/06/20 | 34 | Holmes, Anthony R | 40 | 1760 | 29112
PR | 120 | 11/06/20 | 39 | Martinez Reyes, Juan C | 38.5 | 1424.5 | 29117
PR | 120 | 11/13/20 | 208 | Holmes, Anthony R | 39.5 | 1738 | 29159
PR | 120 | 11/13/20 | 213 | Martinez Reyes, Juan C | 16 | 592 | 29164
PR | 120 | 11/20/20 | 341 | Anderson, Richard P | 13 | 637 | 29182
PR | 120 | 11/20/20 | 364 | Holmes, Anthony R | 18 | 792 | 29205
PR | 120 | 12/23/20 | 485 | Barnhart, Joseph N | 1 | 54 | 29465
PR | 120 | 12/23/20 | 504 | Holmes, Anthony R | 6 | 264 | 29484
PR | 120 | 12/23/20 | 509 | Martinez Reyes, Juan C | 6 | 222 | 29489
PR | 120 | 12/31/20 | 585 | Barnhart, Joseph N | 1 | 54 | 29513
PR | 120 | 12/31/20 | 602 | Gonzalez Hernandez, Josue | 16 | 576 | 29530
PR | 120 | 12/31/20 | 604 | Holmes, Anthony R | 16 | 704 | 29532
PR | 120 | 01/08/21 | 25 | Gonzalez Hernandez, Josue | 16 | 576 | 29577
PR | 120 | 01/08/21 | 27 | Holmes, Anthony R | 11 | 484 | 29579
PR | 120 | 01/15/21 | 141 | Holmes, Anthony R | 15.5 | 682 | 29628
PR | 120 | 01/22/21 | 280 | Holmes, Anthony R | 10.5 | 462 | 29680
PR | 130 | 08/16/19 | 621 | Sanders, Allen O | 2 | 98 | 24840
PR | 130 | 09/06/19 | 70 | Sanders, Allen O | 3 | 147 | 25068
PR | 130 | 09/27/19 | 690 | Sanders, Allen O | 2 | 98 | 25295
PR | 130 | 10/11/19 | 321 | Sanders, Allen O | 1 | 49 | 25455
PR | 130 | 11/01/19 | 66 | Sanders, Allen O | 4.5 | 243 | 25683
PR | 130 | 11/27/19 | 904 | Sanders, Allen O | 6 | 324 | 25985
PR | 130 | 12/06/19 | 91 | Sanders, Allen O | 4 | 216 | 26063
PR | 130 | 12/13/19 | 452 | Sanders, Allen O | 7 | 378 | 26218
PR | 130 | 01/03/20 | 66 | Sanders, Allen O | 2.5 | 135 | 26449
PR | 130 | 01/10/20 | 276 | Anderson, Richard P | 3 | 147 | 26463
PR | 130 | 01/10/20 | 317 | Lee, Ha Nul | 2 | 50 | 26504
PR | 130 | 01/10/20 | 339 | Sanders, Allen O | 4.5 | 243 | 26527
PR | 130 | 01/17/20 | 542 | Anderson, Richard P | 1 | 49 | 26541
PR | 130 | 01/17/20 | 605 | Sanders, Allen O | 2.5 | 135 | 26604
PR | 130 | 01/24/20 | 675 | Anderson, Richard P | 1 | 49 | 26618
PR | 130 | 01/24/20 | 736 | Sanders, Allen O | 1.5 | 81 | 26679
PR | 130 | 01/31/20 | 834 | Anderson, Richard P | 9 | 441 | 26694
PR | 130 | 01/31/20 | 838 | Barnhart, Joseph N | 2 | 108 | 26698
PR | 130 | 01/31/20 | 858 | Galdamez, Dagoberto A | 2 | 66 | 26719
PR | 130 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo | 1 | 30 | 26727
PR | 130 | 01/31/20 | 874 | Lee, Ha Nul | 3 | 75 | 26735
PR | 130 | 01/31/20 | 897 | Sanders, Allen O | 6.5 | 351 | 26758
PR | 130 | 01/31/20 | 900 | Stahlschmidt, John P | 24 | 528 | 26761
PR | 130 | 01/31/20 | 910 | Young, Joshua S | 5 | 80 | 26771
PR | 130 | 02/07/20 | 25 | Anderson, Richard P | 5 | 245 | 26773
PR | 130 | 02/07/20 | 39 | Cruz Gonzalez, Julio C | 24 | 672 | 26787
PR | 130 | 02/07/20 | 41 | Cruz Reyes, Jose | 24 | 768 | 26789
PR | 130 | 02/07/20 | 43 | Draves, Steven W | 16 | 496 | 26791
PR | 130 | 02/07/20 | 51 | Gerard, Jordan E | 16 | 672 | 26799
PR | 130 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 26804
PR | 130 | 02/07/20 | 84 | Romero Garza, Jesus I | 40 | 920 | 26832
PR | 130 | 02/07/20 | 88 | Sanders, Allen O | 14.5 | 783 | 26836
PR | 130 | 02/14/20 | 235 | Anderson, Richard P | 1 | 49 | 26851
PR | 130 | 02/14/20 | 249 | Cruz Gonzalez, Julio C | 14 | 392 | 26865
PR | 130 | 02/14/20 | 251 | Cruz Reyes, Jose | 16 | 512 | 26867
PR | 130 | 02/14/20 | 260 | Gauthier, Dillon R | 8 | 144 | 26876
PR | 130 | 02/14/20 | 294 | Romero Garza, Jesus I | 32 | 736 | 26910
PR | 130 | 02/14/20 | 298 | Sanders, Allen O | 4 | 216 | 26914
PR | 130 | 02/14/20 | 301 | Stahlschmidt, John P | 8 | 176 | 26917
PR | 130 | 02/14/20 | 304 | Trower-Kelly, Fidel D | 8 | 168 | 26920
PR | 130 | 02/21/20 | 452 | Anderson, Richard P | 3 | 147 | 26929
PR | 130 | 02/21/20 | 459 | Boss, Benjamin T | 16 | 288 | 26936
PR | 130 | 02/21/20 | 460 | Boss, Kyle A | 16 | 336 | 26937
PR | 130 | 02/21/20 | 466 | Cruz Gonzalez, Julio C | 16 | 448 | 26943
PR | 130 | 02/21/20 | 468 | Cruz Reyes, Jose | 32 | 1024 | 26945
PR | 130 | 02/21/20 | 476 | Gauthier, Dillon R | 8 | 144 | 26953
PR | 130 | 02/21/20 | 510 | Romero Garza, Jesus I | 40 | 920 | 26987
PR | 130 | 02/21/20 | 514 | Sanders, Allen O | 11.5 | 621 | 26991
PR | 130 | 02/21/20 | 517 | Stahlschmidt, John P | 19 | 418 | 26994
PR | 130 | 02/21/20 | 520 | Trower-Kelly, Fidel D | 8 | 168 | 26997
PR | 130 | 02/28/20 | 680 | Anderson, Richard P | 1 | 49 | 27008
PR | 130 | 02/28/20 | 684 | Barnhart, Joseph N | 1 | 54 | 27012
PR | 130 | 02/28/20 | 687 | Boss, Benjamin T | 16 | 288 | 27015
PR | 130 | 02/28/20 | 688 | Boss, Kyle A | 16 | 336 | 27016
PR | 130 | 02/28/20 | 694 | Cruz Gonzalez, Julio C | 16 | 448 | 27022
PR | 130 | 02/28/20 | 696 | Cruz Reyes, Jose | 16 | 512 | 27024
PR | 130 | 02/28/20 | 705 | Gauthier, Dillon R | 8 | 144 | 27033
PR | 130 | 02/28/20 | 739 | Romero Garza, Jesus I | 32 | 736 | 27067
PR | 130 | 02/28/20 | 743 | Sanders, Allen O | 8.5 | 459 | 27071
PR | 130 | 02/28/20 | 749 | Trower-Kelly, Fidel D | 16 | 336 | 27077
PR | 130 | 03/06/20 | 46 | Barnhart, Joseph N | 0.5 | 27 | 27090
PR | 130 | 03/06/20 | 49 | Boss, Benjamin T | 40 | 720 | 27093
PR | 130 | 03/06/20 | 50 | Boss, Kyle A | 16 | 336 | 27094
PR | 130 | 03/06/20 | 56 | Cruz Gonzalez, Julio C | 13 | 364 | 27100
PR | 130 | 03/06/20 | 58 | Cruz Reyes, Jose | 16 | 512 | 27102
PR | 130 | 03/06/20 | 101 | Romero Garza, Jesus I | 21 | 483 | 27145
PR | 130 | 03/06/20 | 105 | Sanders, Allen O | 14.5 | 783 | 27149
PR | 130 | 03/13/20 | 307 | Anderson, Richard P | 1 | 49 | 27167
PR | 130 | 03/13/20 | 314 | Boss, Benjamin T | 40 | 720 | 27174
PR | 130 | 03/13/20 | 315 | Boss, Kyle A | 40 | 840 | 27175
PR | 130 | 03/13/20 | 321 | Cruz Gonzalez, Julio C | 39.5 | 1106 | 27181
PR | 130 | 03/13/20 | 323 | Cruz Reyes, Jose | 32 | 1024 | 27183
PR | 130 | 03/13/20 | 327 | Eliassen, Cory H | 16 | 480 | 27187
PR | 130 | 03/13/20 | 365 | Romero Garza, Jesus I | 40 | 920 | 27226
PR | 130 | 03/13/20 | 369 | Sanders, Allen O | 17.5 | 945 | 27230
PR | 130 | 03/13/20 | 375 | Trower-Kelly, Fidel D | 8 | 168 | 27236
PR | 130 | 03/20/20 | 565 | Anderson, Richard P | 1 | 49 | 27245
PR | 130 | 03/20/20 | 572 | Boss, Benjamin T | 8 | 144 | 27252
PR | 130 | 03/20/20 | 573 | Boss, Kyle A | 8 | 168 | 27253
PR | 130 | 03/20/20 | 581 | Cruz Reyes, Jose | 8 | 256 | 27261
PR | 130 | 03/20/20 | 585 | Eliassen, Cory H | 8 | 240 | 27265
PR | 130 | 03/20/20 | 627 | Sanders, Allen O | 15.5 | 837 | 27307
PR | 130 | 03/26/20 | 748 | Anderson, Richard P | 2 | 98 | 27324
PR | 130 | 03/26/20 | 755 | Boss, Benjamin T | 40 | 720 | 27331
PR | 130 | 03/26/20 | 756 | Boss, Kyle A | 40 | 840 | 27332
PR | 130 | 03/26/20 | 763 | Cruz Reyes, Jose | 40 | 1280 | 27339
PR | 130 | 03/26/20 | 767 | Eliassen, Cory H | 40 | 1200 | 27343
PR | 130 | 03/26/20 | 774 | Gonzalez Hernandez, Josue | 2 | 72 | 27350
PR | 130 | 03/26/20 | 803 | Romero Garza, Jesus I | 32 | 736 | 27379
PR | 130 | 03/26/20 | 806 | Sanders, Allen O | 24.5 | 1323 | 27382
PR | 130 | 03/26/20 | 812 | Trower-Kelly, Fidel D | 32 | 672 | 27388
PR | 130 | 05/01/20 | 2 | Anderson, Richard P | 1 | 49 | 27629
PR | 130 | 05/01/20 | 10 | Boss, Kyle A | 8 | 168 | 27637
PR | 130 | 05/01/20 | 18 | Cruz Reyes, Jose | 8 | 256 | 27645
PR | 130 | 05/01/20 | 22 | Eliassen, Cory H | 5.5 | 165 | 27649
PR | 130 | 05/01/20 | 60 | Romero Garza, Jesus I | 8 | 184 | 27687
PR | 130 | 05/01/20 | 64 | Sanders, Allen O | 7 | 378 | 27691
PR | 130 | 05/01/20 | 70 | Trower-Kelly, Fidel D | 8 | 168 | 27697
PR | 130 | 05/08/20 | 153 | Anderson, Richard P | 3 | 147 | 27708
PR | 130 | 05/08/20 | 169 | Cruz Reyes, Jose | 40 | 1280 | 27724
PR | 130 | 05/08/20 | 173 | Eliassen, Cory H | 40 | 1200 | 27728
PR | 130 | 05/08/20 | 196 | Martinez Reyes, Juan C | 3 | 111 | 27751
PR | 130 | 05/08/20 | 211 | Romero Garza, Jesus I | 40 | 920 | 27766
PR | 130 | 05/08/20 | 215 | Sanders, Allen O | 8.5 | 459 | 27770
PR | 130 | 05/15/20 | 312 | Barnhart, Joseph N | 2 | 108 | 27790
PR | 130 | 05/15/20 | 324 | Cruz Reyes, Jose | 16 | 512 | 27802
PR | 130 | 05/15/20 | 328 | Eliassen, Cory H | 21.5 | 645 | 27806
PR | 130 | 05/15/20 | 366 | Romero Garza, Jesus I | 24 | 552 | 27844
PR | 130 | 05/15/20 | 370 | Sanders, Allen O | 4 | 216 | 27848
PR | 130 | 05/22/20 | 463 | Anderson, Richard P | 1 | 49 | 27863
PR | 130 | 05/22/20 | 467 | Barnhart, Joseph N | 6.5 | 351 | 27867
PR | 130 | 05/22/20 | 477 | Cruz Gonzalez, Julio C | 16 | 448 | 27877
PR | 130 | 05/22/20 | 479 | Cruz Reyes, Jose | 16 | 512 | 27879
PR | 130 | 05/22/20 | 483 | Eliassen, Cory H | 18 | 540 | 27883
PR | 130 | 05/22/20 | 517 | Romero Garza, Jesus I | 16 | 368 | 27917
PR | 130 | 05/22/20 | 520 | Sanders, Allen O | 10.5 | 567 | 27920
PR | 130 | 05/29/20 | 595 | Barnhart, Joseph N | 6 | 324 | 27938
PR | 130 | 05/29/20 | 598 | Boss, Benjamin T | 16 | 288 | 27941
PR | 130 | 05/29/20 | 605 | Cruz Gonzalez, Julio C | 24 | 672 | 27948
PR | 130 | 05/29/20 | 607 | Cruz Reyes, Jose | 24 | 768 | 27950
PR | 130 | 05/29/20 | 622 | Hubbard, Robert W | 2 | 108 | 27965
PR | 130 | 05/29/20 | 643 | Romero Garza, Jesus I | 24 | 552 | 27986
PR | 130 | 05/29/20 | 646 | Sanders, Allen O | 8 | 432 | 27989
PR | 130 | 06/05/20 | 18 | Barnhart, Joseph N | 2 | 108 | 28008
PR | 130 | 06/05/20 | 19 | Boss, Benjamin T | 32 | 576 | 28009
PR | 130 | 06/05/20 | 25 | Cruz Gonzalez, Julio C | 40 | 1120 | 28015
PR | 130 | 06/05/20 | 27 | Cruz Reyes, Jose | 40 | 1280 | 28017
PR | 130 | 06/05/20 | 31 | Eliassen, Cory H | 34 | 1020 | 28021
PR | 130 | 06/05/20 | 58 | Sanders, Allen O | 15 | 810 | 28048
PR | 130 | 06/05/20 | 62 | Trower-Kelly, Fidel D | 8 | 168 | 28052
PR | 130 | 06/11/20 | 160 | Boss, Benjamin T | 16 | 288 | 28060
PR | 130 | 06/11/20 | 166 | Cruz Gonzalez, Julio C | 16 | 448 | 28066
PR | 130 | 06/11/20 | 168 | Cruz Reyes, Jose | 16 | 512 | 28068
PR | 130 | 06/12/20 | 221 | Barnhart, Joseph N | 3 | 162 | 28105
PR | 130 | 06/12/20 | 222 | Boss, Benjamin T | 24 | 432 | 28106
PR | 130 | 06/12/20 | 228 | Cruz Gonzalez, Julio C | 24 | 672 | 28112
PR | 130 | 06/12/20 | 230 | Cruz Reyes, Jose | 24 | 768 | 28114
PR | 130 | 06/12/20 | 260 | Sanders, Allen O | 15.5 | 837 | 28145
PR | 130 | 06/19/20 | 378 | Barnhart, Joseph N | 3 | 162 | 28155
PR | 130 | 06/19/20 | 379 | Boss, Benjamin T | 8 | 144 | 28156
PR | 130 | 06/19/20 | 385 | Cruz Gonzalez, Julio C | 16 | 448 | 28162
PR | 130 | 06/19/20 | 416 | Sanders, Allen O | 16.5 | 891 | 28193
PR | 130 | 06/26/20 | 521 | Barnhart, Joseph N | 1 | 54 | 28203
PR | 130 | 06/26/20 | 522 | Boss, Benjamin T | 8 | 144 | 28204
PR | 130 | 06/26/20 | 528 | Cruz Gonzalez, Julio C | 8 | 224 | 28210
PR | 130 | 06/26/20 | 558 | Sanders, Allen O | 8 | 432 | 28240
PR | 130 | 07/02/20 | 7 | Barnhart, Joseph N | 1 | 54 | 28250
PR | 130 | 07/02/20 | 8 | Boss, Benjamin T | 40 | 720 | 28251
PR | 130 | 07/02/20 | 14 | Cruz Gonzalez, Julio C | 40 | 1120 | 28257
PR | 130 | 07/02/20 | 44 | Sanders, Allen O | 31 | 1674 | 28287
PR | 130 | 07/10/20 | 140 | Barnhart, Joseph N | 4 | 216 | 28299
PR | 130 | 07/10/20 | 141 | Boss, Benjamin T | 24 | 432 | 28300
PR | 130 | 07/10/20 | 147 | Cruz Gonzalez, Julio C | 24 | 672 | 28306
PR | 130 | 07/10/20 | 176 | Sanders, Allen O | 24 | 1296 | 28335
PR | 130 | 07/17/20 | 265 | Barnhart, Joseph N | 1 | 54 | 28345
PR | 130 | 07/17/20 | 266 | Boss, Benjamin T | 40 | 720 | 28346
PR | 130 | 07/17/20 | 272 | Cruz Gonzalez, Julio C | 40 | 1120 | 28352
PR | 130 | 07/17/20 | 274 | Cruz Reyes, Jose | 24 | 768 | 28354
PR | 130 | 07/17/20 | 303 | Sanders, Allen O | 34 | 1836 | 28383
PR | 130 | 07/24/20 | 404 | Barnhart, Joseph N | 6 | 324 | 28396
PR | 130 | 07/24/20 | 405 | Boss, Benjamin T | 40 | 720 | 28397
PR | 130 | 07/24/20 | 411 | Cruz Gonzalez, Julio C | 40 | 1120 | 28403
PR | 130 | 07/24/20 | 413 | Cruz Reyes, Jose | 40 | 1280 | 28405
PR | 130 | 07/24/20 | 442 | Sanders, Allen O | 22 | 1188 | 28434
PR | 130 | 07/31/20 | 500 | Boss, Benjamin T | 40 | 720 | 28445
PR | 130 | 07/31/20 | 506 | Cruz Gonzalez, Julio C | 40 | 1120 | 28451
PR | 130 | 07/31/20 | 508 | Cruz Reyes, Jose | 40 | 1280 | 28454
PR | 130 | 07/31/20 | 537 | Sanders, Allen O | 19.5 | 1053 | 28483
PR | 130 | 08/07/20 | 90 | Barnhart, Joseph N | 7 | 378 | 28493
PR | 130 | 08/07/20 | 91 | Boss, Benjamin T | 16 | 288 | 28494
PR | 130 | 08/07/20 | 96 | Cruz Gonzalez, Julio C | 3 | 84 | 28499
PR | 130 | 08/07/20 | 98 | Cruz Reyes, Jose | 8 | 256 | 28501
PR | 130 | 08/07/20 | 123 | Sanders, Allen O | 35.5 | 1917 | 28526
PR | 130 | 08/14/20 | 295 | Barnhart, Joseph N | 3 | 162 | 28535
PR | 130 | 08/14/20 | 296 | Boss, Benjamin T | 8 | 144 | 28536
PR | 130 | 08/14/20 | 327 | Sanders, Allen O | 13 | 702 | 28567
PR | 130 | 08/21/20 | 417 | Boss, Benjamin T | 8 | 144 | 28577
PR | 130 | 08/21/20 | 422 | Cruz Gonzalez, Julio C | 8 | 224 | 28582
PR | 130 | 08/21/20 | 424 | Cruz Reyes, Jose | 8 | 256 | 28584
PR | 130 | 08/21/20 | 447 | Sanders, Allen O | 23 | 1242 | 28608
PR | 130 | 08/28/20 | 564 | Barnhart, Joseph N | 2 | 108 | 28617
PR | 130 | 08/28/20 | 565 | Boss, Benjamin T | 8 | 144 | 28618
PR | 130 | 08/28/20 | 570 | Cruz Gonzalez, Julio C | 8 | 224 | 28623
PR | 130 | 08/28/20 | 572 | Cruz Reyes, Jose | 8 | 256 | 28625
PR | 130 | 08/28/20 | 598 | Sanders, Allen O | 2 | 108 | 28651
PR | 130 | 09/04/20 | 7 | Barnhart, Joseph N | 1 | 54 | 28663
PR | 130 | 09/04/20 | 43 | Sanders, Allen O | 8 | 432 | 28699
PR | 130 | 09/11/20 | 113 | Sanders, Allen O | 2 | 108 | 28747
PR | 130 | 09/18/20 | 284 | Anderson, Richard P | 1 | 49 | 28755
PR | 130 | 09/18/20 | 288 | Barnhart, Joseph N | 1 | 54 | 28759
PR | 130 | 09/18/20 | 289 | Boss, Benjamin T | 8 | 144 | 28760
PR | 130 | 09/18/20 | 295 | Cruz Gonzalez, Julio C | 8 | 224 | 28766
PR | 130 | 09/18/20 | 297 | Cruz Reyes, Jose | 8 | 256 | 28768
PR | 130 | 09/25/20 | 429 | Barnhart, Joseph N | 1 | 54 | 28806
PR | 130 | 09/25/20 | 430 | Boss, Benjamin T | 8 | 144 | 28807
PR | 130 | 09/25/20 | 436 | Cruz Gonzalez, Julio C | 8 | 224 | 28813
PR | 130 | 09/25/20 | 466 | Sanders, Allen O | 12 | 648 | 28843
PR | 130 | 10/02/20 | 2 | Anderson, Richard P | 10 | 490 | 28850
PR | 130 | 10/02/20 | 6 | Barnhart, Joseph N | 4 | 216 | 28854
PR | 130 | 10/02/20 | 7 | Boss, Benjamin T | 8 | 144 | 28855
PR | 130 | 10/02/20 | 13 | Cruz Gonzalez, Julio C | 8 | 224 | 28861
PR | 130 | 10/02/20 | 28 | Hubbard, Robert W | 7 | 378 | 28876
PR | 130 | 10/02/20 | 43 | Sanders, Allen O | 16 | 864 | 28891
PR | 130 | 10/09/20 | 151 | Anderson, Richard P | 1 | 49 | 28900
PR | 130 | 10/09/20 | 155 | Barnhart, Joseph N | 3 | 162 | 28904
PR | 130 | 10/09/20 | 156 | Boss, Benjamin T | 8 | 144 | 28905
PR | 130 | 10/09/20 | 162 | Cruz Gonzalez, Julio C | 8 | 224 | 28911
PR | 130 | 10/09/20 | 164 | Cruz Reyes, Jose | 8 | 256 | 28913
PR | 130 | 10/09/20 | 191 | Sanders, Allen O | 23.5 | 1269 | 28940
PR | 130 | 10/16/20 | 293 | Anderson, Richard P | 1.5 | 73.5 | 28947
PR | 130 | 10/16/20 | 298 | Boss, Benjamin T | 8 | 144 | 28952
PR | 130 | 10/16/20 | 333 | Sanders, Allen O | 21 | 1134 | 28987
PR | 130 | 10/23/20 | 475 | Sanders, Allen O | 13.5 | 729 | 29035
PR | 130 | 10/30/20 | 591 | Anderson, Richard P | 24 | 1176 | 29042
PR | 130 | 10/30/20 | 604 | Cruz Reyes, Jose | 32 | 1024 | 29055
PR | 130 | 10/30/20 | 619 | Martinez Reyes, Juan C | 40 | 1480 | 29070
PR | 130 | 10/30/20 | 630 | Sanders, Allen O | 22 | 1188 | 29081
PR | 130 | 11/06/20 | 50 | Sanders, Allen O | 13 | 702 | 29128
PR | 130 | 11/13/20 | 224 | Sanders, Allen O | 19.5 | 1053 | 29175
PR | 130 | 11/20/20 | 341 | Anderson, Richard P | 3 | 147 | 29182
PR | 130 | 11/20/20 | 346 | Boss, Benjamin T | 40 | 720 | 29187
PR | 130 | 11/20/20 | 364 | Holmes, Anthony R | 6 | 264 | 29205
PR | 130 | 11/20/20 | 379 | Sanders, Allen O | 39 | 2106 | 29220
PR | 130 | 11/25/20 | 456 | Barnhart, Joseph N | 4 | 216 | 29231
PR | 130 | 11/25/20 | 457 | Boss, Benjamin T | 32 | 576 | 29232
PR | 130 | 11/25/20 | 491 | Sanders, Allen O | 34 | 1836 | 29266
PR | 130 | 12/04/20 | 7 | Barnhart, Joseph N | 2 | 108 | 29278
PR | 130 | 12/04/20 | 8 | Boss, Benjamin T | 30 | 540 | 29279
PR | 130 | 12/04/20 | 26 | Holmes, Anthony R | 16 | 704 | 29297
PR | 130 | 12/04/20 | 31 | Martinez Reyes, Juan C | 8 | 296 | 29302
PR | 130 | 12/04/20 | 42 | Sanders, Allen O | 30 | 1620 | 29313
PR | 130 | 12/11/20 | 184 | Boss, Benjamin T | 40 | 720 | 29325
PR | 130 | 12/11/20 | 202 | Holmes, Anthony R | 40 | 1760 | 29343
PR | 130 | 12/11/20 | 207 | Martinez Reyes, Juan C | 39 | 1443 | 29348
PR | 130 | 12/11/20 | 218 | Sanders, Allen O | 32.5 | 1755 | 29359
PR | 130 | 12/18/20 | 345 | Boss, Benjamin T | 40 | 720 | 29371
PR | 130 | 12/18/20 | 363 | Holmes, Anthony R | 40 | 1760 | 29389
PR | 130 | 12/18/20 | 368 | Martinez Reyes, Juan C | 32 | 1184 | 29394
PR | 130 | 12/18/20 | 379 | Sanders, Allen O | 37 | 1998 | 29405
PR | 130 | 12/23/20 | 485 | Barnhart, Joseph N | 1 | 54 | 29465
PR | 130 | 12/23/20 | 486 | Boss, Benjamin T | 13.5 | 243 | 29466
PR | 130 | 12/23/20 | 492 | Cruz Gonzalez, Julio C | 8 | 224 | 29472
PR | 130 | 12/23/20 | 494 | Cruz Reyes, Jose | 8 | 256 | 29474
PR | 130 | 12/23/20 | 504 | Holmes, Anthony R | 26 | 1144 | 29484
PR | 130 | 12/23/20 | 509 | Martinez Reyes, Juan C | 26 | 962 | 29489
PR | 130 | 12/23/20 | 520 | Sanders, Allen O | 25.5 | 1377 | 29500
PR | 130 | 12/31/20 | 594 | Cruz Reyes, Jose | 8 | 256 | 29522
PR | 130 | 12/31/20 | 604 | Holmes, Anthony R | 8 | 352 | 29532
PR | 130 | 12/31/20 | 609 | Martinez Reyes, Juan C | 8 | 296 | 29537
PR | 130 | 01/08/21 | 9 | Boss, Benjamin T | 8 | 144 | 29561
PR | 130 | 01/08/21 | 17 | Cruz Reyes, Jose | 24 | 768 | 29569
PR | 130 | 01/08/21 | 27 | Holmes, Anthony R | 13 | 572 | 29579
PR | 130 | 01/08/21 | 43 | Sanders, Allen O | 16 | 864 | 29595
PR | 130 | 01/15/21 | 122 | Boss, Benjamin T | 13.5 | 243 | 29609
PR | 130 | 01/15/21 | 141 | Holmes, Anthony R | 19 | 836 | 29628
PR | 130 | 01/15/21 | 146 | Martinez Reyes, Juan C | 16 | 592 | 29633
PR | 130 | 01/15/21 | 157 | Romero Garza, Jesus I | 24 | 552 | 29644
PR | 130 | 01/15/21 | 159 | Sanders, Allen O | 19.5 | 1053 | 29646
PR | 130 | 01/22/21 | 270 | Cruz Reyes, Jose | 40 | 1280 | 29670
PR | 130 | 01/22/21 | 285 | Martinez Reyes, Juan C | 18 | 666 | 29685
PR | 130 | 01/22/21 | 296 | Romero Garza, Jesus I | 40 | 920 | 29696
PR | 130 | 01/22/21 | 298 | Sanders, Allen O | 19.5 | 1053 | 29698
PR | 130 | 01/29/21 | 396 | Cruz Reyes, Jose | 40 | 1280 | 29721
PR | 130 | 01/29/21 | 412 | Martinez Reyes, Juan C | 32 | 1184 | 29737
PR | 130 | 01/29/21 | 422 | Romero Garza, Jesus I | 40 | 920 | 29747
PR | 130 | 01/29/21 | 424 | Sanders, Allen O | 23.5 | 1269 | 29749
PR | 130 | 02/05/21 | 82 | Cruz Reyes, Jose | 40 | 1280 | 29773
PR | 130 | 02/05/21 | 99 | Martinez Reyes, Juan C | 32 | 1184 | 29790
PR | 130 | 02/05/21 | 110 | Romero Garza, Jesus I | 40 | 920 | 29801
PR | 130 | 02/05/21 | 112 | Sanders, Allen O | 27.5 | 1485 | 29803
PR | 130 | 02/12/21 | 265 | Cruz Gonzalez, Julio C | 24 | 672 | 29826
PR | 130 | 02/12/21 | 267 | Cruz Reyes, Jose | 40 | 1280 | 29828
PR | 130 | 02/12/21 | 285 | Martinez Reyes, Juan C | 16 | 592 | 29846
PR | 130 | 02/12/21 | 296 | Romero Garza, Jesus I | 40 | 920 | 29857
PR | 130 | 02/12/21 | 298 | Sanders, Allen O | 36 | 1944 | 29859
PR | 130 | 02/19/21 | 420 | Barnhart, Joseph N | 2 | 108 | 29873
PR | 130 | 02/19/21 | 429 | Cruz Gonzalez, Julio C | 40 | 1120 | 29882
PR | 130 | 02/19/21 | 431 | Cruz Reyes, Jose | 40 | 1280 | 29884
PR | 130 | 02/19/21 | 452 | Martinez Reyes, Juan C | 39 | 1443 | 29905
PR | 130 | 02/19/21 | 463 | Romero Garza, Jesus I | 32 | 736 | 29916
PR | 130 | 02/19/21 | 465 | Sanders, Allen O | 30.5 | 1647 | 29918
PR | 130 | 02/26/21 | 599 | Boss, Benjamin T | 6 | 180 | 29935
PR | 130 | 02/26/21 | 599 | Boss, Benjamin T | 32 | 640 | 29935
PR | 130 | 02/26/21 | 606 | Cruz Gonzalez, Julio C | 6 | 252 | 29942
PR | 130 | 02/26/21 | 606 | Cruz Gonzalez, Julio C | 40 | 1120 | 29942
PR | 130 | 02/26/21 | 608 | Cruz Reyes, Jose | 1 | 48 | 29944
PR | 130 | 02/26/21 | 608 | Cruz Reyes, Jose | 32 | 1024 | 29944
PR | 130 | 02/26/21 | 629 | Martinez Reyes, Juan C | 7 | 388.5 | 29965
PR | 130 | 02/26/21 | 629 | Martinez Reyes, Juan C | 19 | 703 | 29965
PR | 130 | 02/26/21 | 639 | Romero Garza, Jesus I | 7 | 241.5 | 29975
PR | 130 | 02/26/21 | 639 | Romero Garza, Jesus I | 40 | 920 | 29975
PR | 130 | 02/26/21 | 641 | Sanders, Allen O | 7.5 | 607.5 | 29977
PR | 130 | 02/26/21 | 641 | Sanders, Allen O | 32 | 1728 | 29977
PR | 130 | 03/05/21 | 65 | Cruz Gonzalez, Julio C | 16 | 448 | 30000
PR | 130 | 03/05/21 | 99 | Sanders, Allen O | 21.5 | 1161 | 30034
PR | 130 | 03/12/21 | 224 | Sanders, Allen O | 3 | 162 | 30090
PR | 130 | 03/19/21 | 338 | Sanders, Allen O | 8.5 | 467.5 | 30151
PR | 130 | 03/26/21 | 569 | Sanders, Allen O | 3 | 165 | 30212
PR | 130 | 04/02/21 | 55 | Sanders, Allen O | 2.5 | 137.5 | 30274
PR | 130 | 04/09/21 | 159 | Sanders, Allen O | 1 | 55 | 30337
PR | 130 | 04/30/21 | 627 | Sanders, Allen O | 1.5 | 82.5 | 30537
PR | 140 | 07/12/19 | 282 | Barnhart, Joseph N | 2 | 100 | 24334
PR | 140 | 02/21/20 | 452 | Anderson, Richard P | 5 | 245 | 26929
PR | 140 | 02/21/20 | 458 | Benites Portillo, Marvin E | 1 | 29 | 26935
PR | 140 | 02/21/20 | 462 | Chevez, Herson G | 1 | 26 | 26939
PR | 140 | 02/21/20 | 490 | Lee, Ha Nul | 2 | 50 | 26967
PR | 140 | 02/21/20 | 507 | Rivera, Jorge A | 2 | 76 | 26984
PR | 140 | 02/28/20 | 680 | Anderson, Richard P | 2 | 98 | 27008
PR | 140 | 02/28/20 | 690 | Chevez, Herson G | 8 | 208 | 27018
PR | 140 | 03/06/20 | 42 | Anderson, Richard P | 6 | 294 | 27086
PR | 140 | 03/06/20 | 45 | Barbosa, Michael S | 8 | 264 | 27089
PR | 140 | 03/06/20 | 46 | Barnhart, Joseph N | 2.5 | 135 | 27090
PR | 140 | 03/06/20 | 70 | Gonzalez Hernandez, Josue | 3 | 108 | 27114
PR | 140 | 03/06/20 | 86 | Martinez Reyes, Juan C | 8 | 296 | 27130
PR | 140 | 03/13/20 | 307 | Anderson, Richard P | 4 | 196 | 27167
PR | 140 | 03/13/20 | 362 | Rivera, Jorge A | 2 | 76 | 27223
PR | 140 | 03/20/20 | 565 | Anderson, Richard P | 5 | 245 | 27245
PR | 140 | 03/20/20 | 620 | Rivera, Jorge A | 16 | 608 | 27300
PR | 140 | 03/20/20 | 630 | Stahlschmidt, John P | 16 | 352 | 27310
PR | 140 | 03/26/20 | 748 | Anderson, Richard P | 1 | 49 | 27324
PR | 140 | 03/26/20 | 779 | Holmes, Anthony R | 5 | 220 | 27355
PR | 140 | 05/01/20 | 2 | Anderson, Richard P | 2 | 98 | 27629
PR | 140 | 05/15/20 | 308 | Anderson, Richard P | 1 | 49 | 27786
PR | 140 | 05/15/20 | 340 | Holmes, Anthony R | 17 | 748 | 27818
PR | 140 | 05/22/20 | 491 | Holmes, Anthony R | 18 | 792 | 27891
PR | 140 | 06/05/20 | 18 | Barnhart, Joseph N | 1 | 54 | 28008
PR | 140 | 06/19/20 | 396 | Holmes, Anthony R | 3 | 132 | 28173
PR | 140 | 06/26/20 | 536 | Gonzalez Hernandez, Josue | 4 | 144 | 28218
PR | 140 | 07/10/20 | 140 | Barnhart, Joseph N | 7 | 378 | 28299
PR | 140 | 07/17/20 | 265 | Barnhart, Joseph N | 2 | 108 | 28345
PR | 140 | 07/17/20 | 281 | Gonzalez Hernandez, Josue | 1 | 36 | 28361
PR | 140 | 07/17/20 | 283 | Holmes, Anthony R | 2 | 88 | 28363
PR | 140 | 09/25/20 | 429 | Barnhart, Joseph N | 1 | 54 | 28806
PR | 140 | 10/02/20 | 6 | Barnhart, Joseph N | 3 | 162 | 28854
PR | 140 | 10/09/20 | 155 | Barnhart, Joseph N | 5 | 270 | 28904
PR | 140 | 10/09/20 | 174 | Holmes, Anthony R | 6.5 | 286 | 28923
PR | 140 | 01/08/21 | 27 | Holmes, Anthony R | 8 | 352 | 29579
PR | 140 | 01/15/21 | 141 | Holmes, Anthony R | 2 | 88 | 29628
PR | 141 | 06/07/19 | 179 | Anderson, Richard P | 2 | 94 | 23954
PR | 141 | 07/12/19 | 281 | Barbosa, Michael S | 8 | 232 | 24333
PR | 141 | 07/12/19 | 317 | Lima Romero, Melvin A | 8 | 280 | 24369
PR | 141 | 07/19/19 | 511 | Barbosa, Michael S | 16 | 464 | 24410
PR | 141 | 07/19/19 | 536 | Gonzalez Hernandez, Josue | 8 | 256 | 24435
PR | 141 | 07/19/19 | 547 | Lima Romero, Melvin A | 40 | 1400 | 24446
PR | 141 | 07/26/19 | 615 | Barbosa, Michael S | 16 | 464 | 24564
PR | 141 | 07/26/19 | 650 | Lima Romero, Melvin A | 40 | 1400 | 24599
PR | 141 | 08/02/19 | 48 | Mendoza Morales, Jesus A | 32 | 928 | 24679
PR | 141 | 08/09/19 | 301 | Mendoza Morales, Jesus A | 32 | 928 | 24754
PR | 141 | 08/16/19 | 566 | Barbosa, Michael S | 8 | 232 | 24785
PR | 141 | 08/16/19 | 602 | Lima Romero, Melvin A | 16 | 560 | 24821
PR | 141 | 08/16/19 | 608 | Mendoza Morales, Jesus A | 40 | 1160 | 24827
PR | 141 | 08/23/19 | 799 | Anderson, Richard P | 1 | 47 | 24857
PR | 141 | 08/23/19 | 802 | Barbosa, Michael S | 16 | 464 | 24860
PR | 141 | 08/23/19 | 839 | Lima Romero, Melvin A | 32 | 1120 | 24897
PR | 141 | 08/23/19 | 845 | Mendoza Morales, Jesus A | 40 | 1160 | 24903
PR | 141 | 08/30/19 | 993 | Barbosa, Michael S | 40 | 1160 | 24935
PR | 141 | 08/30/19 | 1020 | Gutierrez Salas, Jose | 32 | 608 | 24962
PR | 141 | 08/30/19 | 1030 | Lima Romero, Melvin A | 40 | 1400 | 24972
PR | 141 | 08/30/19 | 1036 | Mendoza Morales, Jesus A | 39 | 1131 | 24978
PR | 141 | 09/06/19 | 14 | Barbosa, Michael S | 32 | 928 | 25012
PR | 141 | 09/06/19 | 16 | Belcher, Jacob T | 24 | 480 | 25014
PR | 141 | 09/06/19 | 41 | Gutierrez Salas, Jose | 16 | 304 | 25039
PR | 141 | 09/06/19 | 43 | Hoeg, Xavier A | 16 | 272 | 25041
PR | 141 | 09/06/19 | 50 | Lee, Ha Nul | 32 | 672 | 25048
PR | 141 | 09/06/19 | 51 | Lima Romero, Melvin A | 24 | 840 | 25049
PR | 141 | 09/06/19 | 55 | Martinez Reyes, Juan C | 8 | 264 | 25053
PR | 141 | 09/06/19 | 57 | Mendoza Morales, Jesus A | 32 | 928 | 25055
PR | 141 | 09/06/19 | 68 | Romero Garza, Jesus I | 8 | 144 | 25066
PR | 141 | 09/13/19 | 238 | Barbosa, Michael S | 32 | 928 | 25087
PR | 141 | 09/13/19 | 240 | Belcher, Jacob T | 16 | 320 | 25089
PR | 141 | 09/13/19 | 265 | Gutierrez Salas, Jose | 40 | 760 | 25114
PR | 141 | 09/13/19 | 267 | Hoeg, Xavier A | 40 | 680 | 25116
PR | 141 | 09/13/19 | 273 | Lee, Ha Nul | 40 | 840 | 25122
PR | 141 | 09/13/19 | 274 | Lima Romero, Melvin A | 40 | 1400 | 25123
PR | 141 | 09/13/19 | 280 | Mendoza Morales, Jesus A | 40 | 1160 | 25129
PR | 141 | 09/20/19 | 475 | Barbosa, Michael S | 32 | 928 | 25161
PR | 141 | 09/20/19 | 503 | Gutierrez Salas, Jose | 40 | 760 | 25189
PR | 141 | 09/20/19 | 505 | Hoeg, Xavier A | 13 | 221 | 25191
PR | 141 | 09/20/19 | 511 | Lee, Ha Nul | 40 | 840 | 25197
PR | 141 | 09/20/19 | 512 | Lima Romero, Melvin A | 40 | 1400 | 25198
PR | 141 | 09/20/19 | 514 | Lovo, German G | 16 | 432 | 25200
PR | 141 | 09/20/19 | 518 | Mendoza Morales, Jesus A | 37 | 1073 | 25204
PR | 141 | 09/27/19 | 631 | Barbosa, Michael S | 40 | 1160 | 25236
PR | 141 | 09/27/19 | 660 | Gutierrez Salas, Jose | 32 | 608 | 25265
PR | 141 | 09/27/19 | 662 | Hoeg, Xavier A | 8 | 136 | 25267
PR | 141 | 09/27/19 | 671 | Lima Romero, Melvin A | 40 | 1400 | 25276
PR | 141 | 09/27/19 | 673 | Lovo, German G | 40 | 1080 | 25278
PR | 141 | 09/27/19 | 677 | Mendoza Morales, Jesus A | 32 | 928 | 25282
PR | 141 | 10/04/19 | 7 | Barbosa, Michael S | 39.5 | 1145.5 | 25314
PR | 141 | 10/04/19 | 35 | Gutierrez Salas, Jose | 39.5 | 750.5 | 25342
PR | 141 | 10/04/19 | 37 | Hoeg, Xavier A | 8 | 136 | 25344
PR | 141 | 10/04/19 | 46 | Lima Romero, Melvin A | 40 | 1400 | 25353
PR | 141 | 10/04/19 | 48 | Lovo, German G | 40 | 1080 | 25355
PR | 141 | 10/04/19 | 53 | Mendoza Morales, Jesus A | 40 | 1160 | 25360
PR | 141 | 10/11/19 | 262 | Barbosa, Michael S | 40 | 1160 | 25395
PR | 141 | 10/11/19 | 290 | Gutierrez Salas, Jose | 38 | 722 | 25424
PR | 141 | 10/11/19 | 292 | Hoeg, Xavier A | 16 | 272 | 25426
PR | 141 | 10/11/19 | 301 | Lima Romero, Melvin A | 40 | 1400 | 25435
PR | 141 | 10/11/19 | 303 | Lovo, German G | 40 | 1080 | 25437
PR | 141 | 10/11/19 | 308 | Mendoza Morales, Jesus A | 40 | 1160 | 25442
PR | 141 | 10/11/19 | 313 | Reyes Cruz, Denis A | 24 | 720 | 25447
PR | 141 | 10/18/19 | 456 | Barbosa, Michael S | 32 | 928 | 25472
PR | 141 | 10/18/19 | 483 | Gutierrez Salas, Jose | 30 | 570 | 25499
PR | 141 | 10/18/19 | 485 | Hoeg, Xavier A | 8 | 136 | 25501
PR | 141 | 10/18/19 | 494 | Lima Romero, Melvin A | 24 | 840 | 25511
PR | 141 | 10/18/19 | 496 | Lovo, German G | 32 | 864 | 25513
PR | 141 | 10/18/19 | 501 | Mendoza Morales, Jesus A | 37 | 1073 | 25518
PR | 141 | 10/18/19 | 502 | Paco Leyva, Orlando | 6 | 240 | 25519
PR | 141 | 10/18/19 | 506 | Reyes Cruz, Denis A | 12 | 360 | 25523
PR | 141 | 10/18/19 | 512 | Rosas Olivares, Jorge C | 32 | 640 | 25529
PR | 141 | 10/25/19 | 591 | Barbosa, Michael S | 35.5 | 1029.5 | 25548
PR | 141 | 10/25/19 | 618 | Gutierrez Salas, Jose | 20 | 380 | 25575
PR | 141 | 10/25/19 | 620 | Hoeg, Xavier A | 8 | 136 | 25577
PR | 141 | 10/25/19 | 621 | Holmes, Anthony R | 8 | 320 | 25578
PR | 141 | 10/25/19 | 629 | Lima Romero, Melvin A | 36 | 1260 | 25586
PR | 141 | 10/25/19 | 631 | Lovo, German G | 20 | 540 | 25588
PR | 141 | 10/25/19 | 636 | Mendoza Morales, Jesus A | 28 | 812 | 25593
PR | 141 | 10/25/19 | 638 | Paco Leyva, Orlando | 7 | 280 | 25595
PR | 141 | 10/25/19 | 642 | Reyes Cruz, Denis A | 12 | 360 | 25599
PR | 141 | 10/25/19 | 648 | Rosas Olivares, Jorge C | 27 | 540 | 25605
PR | 141 | 11/01/19 | 7 | Barbosa, Michael S | 16 | 528 | 25624
PR | 141 | 11/01/19 | 31 | Gonzalez Hernandez, Josue | 40 | 1440 | 25648
PR | 141 | 11/01/19 | 34 | Gutierrez Salas, Jose | 32 | 608 | 25651
PR | 141 | 11/01/19 | 36 | Hoeg, Xavier A | 14 | 252 | 25653
PR | 141 | 11/01/19 | 37 | Holmes, Anthony R | 18 | 792 | 25654
PR | 141 | 11/01/19 | 44 | Lee, Ha Nul | 16 | 400 | 25661
PR | 141 | 11/01/19 | 45 | Lima Romero, Melvin A | 40 | 1520 | 25662
PR | 141 | 11/01/19 | 47 | Lovo, German G | 40 | 1200 | 25664
PR | 141 | 11/01/19 | 52 | Mendoza Morales, Jesus A | 38 | 1216 | 25669
PR | 141 | 11/01/19 | 54 | Paco Leyva, Orlando | 6 | 264 | 25671
PR | 141 | 11/01/19 | 64 | Rosas Olivares, Jorge C | 32 | 640 | 25681
PR | 141 | 11/01/19 | 74 | Velasquez Cruz, Denis M | 8 | 280 | 25691
PR | 141 | 11/01/19 | 75 | Velasquez Cruz, Osman N | 8 | 224 | 25692
PR | 141 | 11/08/19 | 178 | Anderson, Richard P | 1 | 49 | 25697
PR | 141 | 11/08/19 | 205 | Gonzalez Hernandez, Josue | 24 | 864 | 25724
PR | 141 | 11/08/19 | 208 | Gutierrez Salas, Jose | 16 | 304 | 25727
PR | 141 | 11/08/19 | 210 | Hoeg, Xavier A | 6 | 108 | 25729
PR | 141 | 11/08/19 | 219 | Lima Romero, Melvin A | 39 | 1482 | 25738
PR | 141 | 11/08/19 | 221 | Lovo, German G | 8 | 240 | 25740
PR | 141 | 11/08/19 | 226 | Mendoza Morales, Jesus A | 16 | 512 | 25745
PR | 141 | 11/08/19 | 228 | Paco Leyva, Orlando | 1 | 44 | 25747
PR | 141 | 11/08/19 | 238 | Rosas Olivares, Jorge C | 40 | 800 | 25757
PR | 141 | 11/08/19 | 243 | Stahlschmidt, John P | 8 | 176 | 25762
PR | 141 | 11/15/19 | 441 | Barbosa, Michael S | 8 | 264 | 25776
PR | 141 | 11/15/19 | 465 | Gonzalez Hernandez, Josue | 40 | 1440 | 25801
PR | 141 | 11/15/19 | 467 | Gutierrez Salas, Jose | 7 | 133 | 25803
PR | 141 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo | 8 | 240 | 25804
PR | 141 | 11/15/19 | 477 | Lee, Ha Nul | 8 | 200 | 25813
PR | 141 | 11/15/19 | 478 | Lima Romero, Melvin A | 16 | 608 | 25814
PR | 141 | 11/15/19 | 480 | Lovo, German G | 8 | 240 | 25816
PR | 141 | 11/15/19 | 485 | Mendoza Morales, Jesus A | 32 | 1024 | 25821
PR | 141 | 11/15/19 | 487 | Paco Leyva, Orlando | 3 | 132 | 25823
PR | 141 | 11/15/19 | 497 | Rosas Olivares, Jorge C | 40 | 800 | 25833
PR | 141 | 11/15/19 | 502 | Stahlschmidt, John P | 8 | 176 | 25838
PR | 141 | 11/22/19 | 636 | Gonzalez Hernandez, Josue | 32 | 1152 | 25876
PR | 141 | 11/22/19 | 638 | Gutierrez Salas, Jose | 38 | 722 | 25878
PR | 141 | 11/22/19 | 640 | Hoeg, Xavier A | 4 | 72 | 25880
PR | 141 | 11/22/19 | 648 | Lee, Ha Nul | 6 | 150 | 25888
PR | 141 | 11/22/19 | 651 | Lovo, German G | 22 | 660 | 25891
PR | 141 | 11/22/19 | 656 | Mendoza Morales, Jesus A | 16 | 512 | 25896
PR | 141 | 11/22/19 | 658 | Paco Leyva, Orlando | 3 | 132 | 25898
PR | 141 | 11/22/19 | 668 | Rosas Olivares, Jorge C | 38 | 760 | 25908
PR | 141 | 11/27/19 | 870 | Gonzalez Hernandez, Josue | 31.5 | 1134 | 25951
PR | 141 | 11/27/19 | 872 | Gutierrez Salas, Jose | 16 | 304 | 25953
PR | 141 | 11/27/19 | 874 | Hoeg, Xavier A | 2 | 36 | 25955
PR | 141 | 11/27/19 | 882 | Lee, Ha Nul | 22 | 550 | 25963
PR | 141 | 11/27/19 | 883 | Lima Romero, Melvin A | 24 | 912 | 25964
PR | 141 | 11/27/19 | 890 | Mendoza Morales, Jesus A | 32 | 1024 | 25971
PR | 141 | 11/27/19 | 896 | Reyes Cruz, Denis A | 8 | 264 | 25977
PR | 141 | 11/27/19 | 902 | Rosas Olivares, Jorge C | 37 | 740 | 25983
PR | 141 | 12/06/19 | 29 | Anderson, Richard P | 1 | 49 | 26000
PR | 141 | 12/06/19 | 32 | Barbosa, Michael S | 24 | 792 | 26003
PR | 141 | 12/06/19 | 33 | Barnhart, Joseph N | 1 | 54 | 26005
PR | 141 | 12/06/19 | 57 | Gonzalez Hernandez, Josue | 16 | 576 | 26029
PR | 141 | 12/06/19 | 59 | Gutierrez Salas, Jose | 8 | 152 | 26031
PR | 141 | 12/06/19 | 70 | Lima Romero, Melvin A | 26 | 988 | 26042
PR | 141 | 12/06/19 | 72 | Lovo, German G | 8 | 240 | 26044
PR | 141 | 12/06/19 | 77 | Mendoza Morales, Jesus A | 16 | 512 | 26049
PR | 141 | 12/06/19 | 79 | Paco Leyva, Orlando | 9 | 396 | 26051
PR | 141 | 12/06/19 | 83 | Reyes Cruz, Denis A | 8 | 264 | 26055
PR | 141 | 12/06/19 | 89 | Rosas Olivares, Jorge C | 8 | 160 | 26061
PR | 141 | 12/06/19 | 94 | Stahlschmidt, John P | 8 | 176 | 26066
PR | 141 | 12/13/19 | 390 | Anderson, Richard P | 1 | 49 | 26155
PR | 141 | 12/13/19 | 393 | Barbosa, Michael S | 26 | 858 | 26158
PR | 141 | 12/13/19 | 418 | Gonzalez Hernandez, Josue | 24 | 864 | 26183
PR | 141 | 12/13/19 | 438 | Mendoza Morales, Jesus A | 8 | 256 | 26204
PR | 141 | 12/13/19 | 440 | Paco Leyva, Orlando | 9 | 396 | 26206
PR | 141 | 12/13/19 | 450 | Rosas Olivares, Jorge C | 8 | 160 | 26216
PR | 141 | 12/20/19 | 546 | Barbosa, Michael S | 8 | 264 | 26235
PR | 141 | 12/20/19 | 566 | Galdamez, Dagoberto A | 8 | 264 | 26255
PR | 141 | 12/20/19 | 584 | Lima Romero, Melvin A | 24 | 912 | 26273
PR | 141 | 12/20/19 | 586 | Lovo, German G | 16 | 480 | 26275
PR | 141 | 12/20/19 | 593 | Paco Leyva, Orlando | 1 | 44 | 26282
PR | 141 | 12/20/19 | 603 | Rosas Olivares, Jorge C | 16 | 320 | 26292
PR | 141 | 12/27/19 | 742 | Lima Romero, Melvin A | 4 | 152 | 26350
PR | 141 | 01/03/20 | 6 | Barbosa, Michael S | 13 | 429 | 26388
PR | 141 | 01/03/20 | 45 | Lima Romero, Melvin A | 13 | 494 | 26428
PR | 141 | 01/10/20 | 276 | Anderson, Richard P | 4 | 196 | 26463
PR | 141 | 01/10/20 | 279 | Barbosa, Michael S | 31.75 | 1047.75 | 26466
PR | 141 | 01/10/20 | 318 | Lima Romero, Melvin A | 40 | 1520 | 26506
PR | 141 | 01/10/20 | 337 | Rosas Olivares, Jorge C | 26 | 520 | 26525
PR | 141 | 01/17/20 | 545 | Barbosa, Michael S | 8 | 264 | 26544
PR | 141 | 01/17/20 | 603 | Rosas Olivares, Jorge C | 24 | 480 | 26602
PR | 141 | 01/24/20 | 678 | Barbosa, Michael S | 24 | 792 | 26621
PR | 141 | 01/24/20 | 715 | Lima Romero, Melvin A | 24 | 912 | 26658
PR | 141 | 01/24/20 | 722 | Mendoza Morales, Jesus A | 8 | 256 | 26665
PR | 141 | 01/24/20 | 724 | Paco Leyva, Orlando | 7 | 308 | 26667
PR | 141 | 01/24/20 | 734 | Rosas Olivares, Jorge C | 32 | 640 | 26677
PR | 141 | 01/31/20 | 863 | Gonzalez Hernandez, Josue | 8 | 288 | 26724
PR | 141 | 01/31/20 | 884 | Paco Leyva, Orlando | 2 | 88 | 26745
PR | 141 | 01/31/20 | 895 | Rosas Olivares, Jorge C | 16 | 320 | 26756
PR | 141 | 02/07/20 | 66 | Lima Romero, Melvin A | 20 | 760 | 26814
PR | 141 | 02/07/20 | 69 | Mackey, Cole J | 4 | 64 | 26817
PR | 141 | 02/07/20 | 74 | Paco Leyva, Orlando | 2 | 88 | 26822
PR | 141 | 02/07/20 | 85 | Rosas Olivares, Jorge C | 40 | 800 | 26833
PR | 141 | 02/14/20 | 235 | Anderson, Richard P | 1 | 49 | 26851
PR | 141 | 02/14/20 | 279 | Mackey, Cole J | 5 | 80 | 26895
PR | 141 | 02/14/20 | 295 | Rosas Olivares, Jorge C | 40 | 800 | 26911
PR | 141 | 02/21/20 | 455 | Barbosa, Michael S | 2 | 66 | 26932
PR | 141 | 02/21/20 | 491 | Lima Romero, Melvin A | 2 | 76 | 26968
PR | 141 | 02/21/20 | 494 | Mackey, Cole J | 5 | 80 | 26971
PR | 141 | 02/21/20 | 511 | Rosas Olivares, Jorge C | 8 | 160 | 26988
PR | 141 | 02/28/20 | 680 | Anderson, Richard P | 3 | 147 | 27008
PR | 141 | 02/28/20 | 683 | Barbosa, Michael S | 3 | 99 | 27011
PR | 141 | 02/28/20 | 720 | Lima Romero, Melvin A | 24 | 912 | 27048
PR | 141 | 02/28/20 | 723 | Mackey, Cole J | 5 | 80 | 27051
PR | 141 | 02/28/20 | 740 | Rosas Olivares, Jorge C | 29 | 580 | 27068
PR | 141 | 03/06/20 | 42 | Anderson, Richard P | 1 | 49 | 27086
PR | 141 | 03/06/20 | 82 | Lima Romero, Melvin A | 36 | 1368 | 27126
PR | 141 | 03/06/20 | 85 | Mackey, Cole J | 5 | 80 | 27129
PR | 141 | 03/06/20 | 102 | Rosas Olivares, Jorge C | 32 | 640 | 27146
PR | 141 | 03/13/20 | 346 | Lima Romero, Melvin A | 40 | 1520 | 27207
PR | 141 | 03/13/20 | 349 | Mackey, Cole J | 5 | 80 | 27210
PR | 141 | 03/13/20 | 366 | Rosas Olivares, Jorge C | 32 | 640 | 27227
PR | 141 | 03/20/20 | 565 | Anderson, Richard P | 1 | 49 | 27245
PR | 141 | 03/20/20 | 604 | Lima Romero, Melvin A | 39 | 1482 | 27284
PR | 141 | 03/20/20 | 624 | Rosas Olivares, Jorge C | 31 | 620 | 27304
PR | 141 | 03/26/20 | 785 | Lima Romero, Melvin A | 32 | 1216 | 27361
PR | 141 | 03/26/20 | 804 | Rosas Olivares, Jorge C | 8 | 160 | 27380
PR | 141 | 05/15/20 | 340 | Holmes, Anthony R | 5 | 220 | 27818
PR | 141 | 05/15/20 | 353 | Mendoza Morales, Jesus A | 5 | 160 | 27831
PR | 141 | 05/22/20 | 466 | Barbosa, Michael S | 40 | 1320 | 27866
PR | 141 | 05/29/20 | 594 | Barbosa, Michael S | 25 | 825 | 27937
PR | 141 | 06/05/20 | 17 | Barbosa, Michael S | 32 | 1056 | 28007
PR | 141 | 06/11/20 | 159 | Barbosa, Michael S | 8 | 264 | 28059
PR | 141 | 06/11/20 | 182 | Lee, Ha Nul | 8 | 200 | 28082
PR | 141 | 06/11/20 | 187 | Mendoza Morales, Jesus A | 8 | 256 | 28087
PR | 141 | 06/12/20 | 220 | Barbosa, Michael S | 16 | 528 | 28104
PR | 141 | 07/10/20 | 166 | Mendoza Morales, Jesus A | 8 | 256 | 28325
PR | 141 | 07/24/20 | 404 | Barnhart, Joseph N | 3 | 162 | 28396
PR | 141 | 07/24/20 | 420 | Gonzalez Hernandez, Josue | 21 | 756 | 28412
PR | 141 | 07/31/20 | 499 | Barnhart, Joseph N | 2 | 108 | 28444
PR | 141 | 07/31/20 | 515 | Gonzalez Hernandez, Josue | 40 | 1440 | 28461
PR | 141 | 08/07/20 | 90 | Barnhart, Joseph N | 2 | 108 | 28493
PR | 141 | 08/07/20 | 105 | Gonzalez Hernandez, Josue | 32 | 1152 | 28508
PR | 141 | 08/14/20 | 310 | Gonzalez Hernandez, Josue | 32 | 1152 | 28550
PR | 141 | 08/21/20 | 430 | Gonzalez Hernandez, Josue | 24 | 864 | 28590
PR | 141 | 09/11/20 | 73 | Anderson, Richard P | 12 | 588 | 28707
PR | 143 | 11/08/19 | 210 | Hoeg, Xavier A | 2 | 36 | 25729
PR | 143 | 12/20/19 | 548 | Belcher, Jacob T | 4 | 84 | 26237
PR | 143 | 12/20/19 | 593 | Paco Leyva, Orlando | 1 | 44 | 26282
PR | 143 | 12/20/19 | 595 | Ramos Herrera, Franklin J | 4 | 120 | 26284
GL | 210 | 04/12/19 | 440 | Req 5136 |  | 312.62
GL | 210 | 04/22/19 | 622 | Joseph Barhnart |  | 128.55
AP | 210 | 04/23/19 | 660 | Rosen Supply Kirkland |  | 8518.63 | 4264628-00
AP | 210 | 04/23/19 | 680 | Rosen Supply Kirkland |  | 29.69 | 4265787-00
GL | 210 | 04/24/19 | 700 | Req 5916 |  | 58.71
AP | 210 | 04/24/19 | 716 | Rosen Supply Kirkland |  | 89.3 | 4265832-00
GL | 210 | 04/30/19 | 894 | Req 5933 |  | 164.98
AP | 210 | 05/02/19 | 144 | Rosen Supply Kirkland |  | 1290.24 | 4265894-00
AP | 210 | 05/10/19 | 285 | Rosen Supply Kirkland |  | 349.92 | 4266167-00
AP | 210 | 05/10/19 | 286 | Rosen Supply Kirkland |  | 1483.5 | 4266193-00
AP | 210 | 05/10/19 | 287 | Rosen Supply Kirkland |  | 24.75 | 4266231-00
GL | 210 | 05/13/19 | 297 | Req 5194 |  | 159.22
AP | 210 | 05/13/19 | 330 | Rosen Supply Kirkland |  | 132.87 | 4266374-00
AP | 210 | 05/15/19 | 376 | Rosen Supply Kirkland |  | 268.8 | 4266667-00
GL | 210 | 05/16/19 | 699 | Joseph Barnhart |  | 10.93
AP | 210 | 05/28/19 | 724 | Rosen Supply Kirkland |  | 436.88 | 4266711-00
AP | 210 | 05/28/19 | 729 | Rosen Supply Kirkland |  | 114.86 | 1537371-00
AP | 210 | 05/28/19 | 733 | Rosen Supply Kirkland |  | 71.71 | 4266822-00
AP | 210 | 05/28/19 | 746 | Rosen Supply Kirkland |  | 137.88 | 4266927-00
AP | 210 | 06/05/19 | 96 | Ferguson Enterprises, Inc. #3007 |  | 217.89 | 7223194
AP | 210 | 06/06/19 | 264 | Rosen Supply Kirkland |  | 249.06 | 1538453-00
AP | 210 | 06/06/19 | 265 | Rosen Supply Kirkland |  | 46.02 | 1538460-00
AP | 210 | 06/06/19 | 266 | Rosen Supply Kirkland |  | 1233.4 | 4267411-00
AP | 210 | 06/21/19 | 718 | Rosen Supply Kirkland |  | 377.81 | 4268748-00
GL | 210 | 07/10/19 | 171 | Req 6144 |  | 210.69
AP | 210 | 07/15/19 | 406 | Rosen Supply Kirkland |  | 140.63 | 4269313-00
AP | 210 | 07/16/19 | 445 | Rosen Supply Kirkland |  | 134.4 | 4269404-00
AP | 210 | 08/10/19 | 446 | Rosen Supply Kirkland |  | 875.01 | 4270313-00
AP | 210 | 08/14/19 | 549 | Rosen Supply Kirkland |  | 40.65 | 4270852-00
GL | 210 | 11/04/19 | 129 | Req 6464 |  | 23.73
AP | 210 | 12/05/19 | 119 | Rosen Supply Kirkland |  | 1027.11 | 4274778-00
AP | 210 | 12/09/19 | 214 | Rosen Supply Kirkland |  | 651.85 | 1551549-00
AP | 210 | 01/06/20 | 114 | Rosen Supply Kirkland |  | 2970.68 | 4276606-00
AP | 210 | 01/06/20 | 144 | Consolidated Supply Co. |  | 254.53 | S009576525.001
AP | 210 | 01/10/20 | 453 | Capital One Credit Card |  | 7.04 | 121719JB
AP | 210 | 02/18/20 | 414 | Rosen Supply Kirkland |  | 22.52 | 4278503-00
AP | 210 | 03/11/20 | 288 | Consolidated Supply Co. |  | 2588.99 | S009663110.001
GL | 210 | 03/13/20 | 405 | Req 6863 |  | 74.58
AP | 210 | 03/16/20 | 448 | Rosen Supply Kirkland |  | 1743.91 | 4279519-00
GL | 210 | 03/20/20 | 677 | Req 6912 |  | 114.1
AP | 210 | 03/25/20 | 520 | Capital One Credit Card |  | 29.59 | 030320JB2
AP | 210 | 07/30/20 | 558 | Core & Main LP $HD Supply Waterworks |  | 77.69 | M738873
AP | 210 | 11/11/20 | 159 | Capital One Credit Card |  | 12.91 | 100820JB2
GL | 211 | 03/28/19 | 1062 | Req 5855 |  | 316.18
GL | 211 | 05/13/19 | 310 | Req 5204 |  | 1020.71
GL | 211 | 05/13/19 | 311 | Req 5203 |  | 375.66
AP | 211 | 05/21/19 | 538 | Keller Supply Company |  | 62 | S013010284.001
GL | 211 | 05/30/19 | 859 | Req 5942 |  | 799.68
AP | 211 | 06/03/19 | 25 | Consolidated Supply Co. |  | 882.32 | S9266825.001
AP | 211 | 06/03/19 | 26 | Consolidated Supply Co. |  | 882.32 | S9266825.002
GL | 211 | 06/05/19 | 126 | Req 5232 |  | 142.5
AP | 211 | 06/08/19 | 318 | Rosen Supply Kirkland |  | 263.55 | 4268020-00
AP | 211 | 06/11/19 | 391 | Keller Supply Company |  | 209.6 | S013077997.001
GL | 211 | 07/10/19 | 170 | Req 6145 |  | 368.85
GL | 211 | 07/10/19 | 199 | Req 6115 |  | 1211.21
AP | 211 | 07/16/19 | 446 | Rosen Supply Kirkland |  | 40.22 | 1542099-00
AP | 211 | 07/30/19 | 710 | Rosen Supply Kirkland |  | 4427.04 | 4269967-00
AP | 211 | 08/07/19 | 194 | Rosen Supply Kirkland |  | 283.08 | 4270184-00
GL | 211 | 08/08/19 | 225 | Req 6174 |  | 312.8
GL | 211 | 08/20/19 | 686 | Req 6252 |  | 118.65
GL | 211 | 08/20/19 | 701 | Req 6264 |  | -113.65
GL | 211 | 08/20/19 | 706 | Req 6246 |  | 1268.2
AP | 211 | 08/28/19 | 968 | Rosen Supply Kirkland |  | 590.45 | 4270962-00
AP | 211 | 08/28/19 | 970 | Rosen Supply Kirkland |  | 883.05 | 4271034-00
AP | 211 | 08/28/19 | 973 | Rosen Supply Kirkland |  | 353.22 | 4271140-00
GL | 211 | 09/16/19 | 358 | Req 6322 |  | 758.65
AP | 211 | 09/23/19 | 584 | Rosen Supply Kirkland |  | 134.4 | 1546489-00
AP | 211 | 09/25/19 | 625 | Rosen Supply Kirkland |  | 1290.24 | 4272348-00
AP | 211 | 10/15/19 | 436 | Rosen Supply Kirkland |  | 470.5 | 4273013-00
GL | 211 | 11/04/19 | 123 | Req 6461 |  | 1717.93
GL | 211 | 11/04/19 | 125 | Req 6462 |  | 243.58
GL | 211 | 11/19/19 | 572 | Req 6577 |  | 8.38
GL | 211 | 11/19/19 | 577 | Req 6586 |  | -39.2
GL | 211 | 11/19/19 | 578 | Req 6585 |  | 282.24
GL | 211 | 11/30/19 | 942 | Req 6544 |  | 316.57
AP | 211 | 12/05/19 | 115 | Rosen Supply Kirkland |  | 1006.03 | 4274586-00
GL | 211 | 12/06/19 | 134 | Req 6616 |  | 178.86
GL | 211 | 12/06/19 | 171 | Req 6590 |  | 87.97
AP | 211 | 12/09/19 | 206 | Rosen Supply Kirkland |  | 145.11 | 4274927-00
AP | 211 | 12/09/19 | 213 | Rosen Supply Kirkland |  | 630.31 | 4274971-00
AP | 211 | 12/09/19 | 215 | Rosen Supply Kirkland |  | 151.72 | 4274952-00
AP | 211 | 12/13/19 | 535 | Rosen Supply Kirkland |  | 1566.87 | 4275598-00
GL | 211 | 12/27/19 | 790 | Req 6698 |  | 220.36
AP | 211 | 12/31/19 | 859 | Rosen Supply Kirkland |  | 189.95 | 4275598-01
AP | 211 | 01/03/20 | 96 | Rosen Supply Kirkland |  | 36.41 | 4276357-00
AP | 211 | 01/08/20 | 247 | Rosen Supply Kirkland |  | 18.32 | 4276882-00
AP | 211 | 01/08/20 | 267 | Rosen Supply Kirkland |  | 742.94 | 4277056-00
AP | 211 | 01/10/20 | 452 | Capital One Credit Card |  | 29.67 | 121619JB
AP | 211 | 01/13/20 | 523 | Rosen Supply Kirkland |  | 9.26 | 4277159-00
AP | 211 | 01/13/20 | 532 | Rosen Supply Kirkland |  | 3228.7 | 4277238-00
GL | 211 | 01/31/20 | 944 | Req 5772 |  | 263.48
GL | 211 | 02/24/20 | 540 | Req 6825 |  | -90.25
GL | 211 | 02/24/20 | 571 | Req 6798 |  | 2003.92
GL | 211 | 03/13/20 | 396 | Req 6892 |  | -11.38
GL | 211 | 03/13/20 | 403 | Req 6860 |  | 490.87
AP | 211 | 03/16/20 | 460 | Rosen Supply Kirkland |  | 23.5 | 427979900
GL | 211 | 03/20/20 | 678 | Req 6914 |  | 195.1
GL | 211 | 05/11/20 | 262 | Req 6990 |  | 467.1
GL | 211 | 05/15/20 | 396 | Req 7018 |  | -127.79
GL | 211 | 05/27/20 | 578 | Req 7039 |  | 257.53
GL | 211 | 05/31/20 | 719 | Req 7086 |  | 412
AP | 211 | 06/09/20 | 150 | Rosen Supply Kirkland |  | 118.08 | 4282435-00
GL | 211 | 06/16/20 | 336 | Req 7101 |  | 424.39
AP | 211 | 06/24/20 | 501 | Rosen Supply Kirkland |  | 74.66 | 4282758-00
AP | 211 | 06/25/20 | 362 | Rosen Supply Kirkland |  | 609.27 | 4282600-00
GL | 211 | 07/07/20 | 82 | Req 7146 |  | 88.74
GL | 211 | 07/14/20 | 254 | Req 7178 |  | -591.36
GL | 211 | 07/24/20 | 468 | Req 7192 |  | 584.25
AP | 211 | 08/10/20 | 254 | Capital One Credit Card |  | 30.9 | 070720JB
AP | 211 | 08/10/20 | 255 | Capital One Credit Card |  | 13.53 | 070720JB2
AP | 211 | 08/10/20 | 256 | Capital One Credit Card |  | 7.61 | 070820JB
GL | 211 | 08/17/20 | 388 | Req 7234 |  | 181
GL | 211 | 09/14/20 | 186 | Req 7288 |  | -381.8
GL | 211 | 09/14/20 | 191 | Req 7283 |  | -38.92
GL | 211 | 09/14/20 | 194 | Req 7280 |  | -368
GL | 211 | 09/24/20 | 512 | Req 7318 |  | -28.52
GL | 211 | 09/29/20 | 535 | Req 7329 |  | 66
GL | 211 | 10/08/20 | 203 | Req 7353 |  | -142.5
GL | 211 | 10/20/20 | 422 | Req 7377 |  | 39.66
GL | 211 | 11/04/20 | 3 | Req 7407 |  | -177.63
GL | 211 | 12/03/20 | 83 | Req 7468 |  | -386.18
GL | 211 | 03/25/21 | 505 | Req 7647 |  | -442.1
GL | 212 | 05/16/19 | 699 | Joseph Barnhart |  | 52.47
GL | 212 | 06/05/19 | 127 | Req 5231 |  | 2401.43
AP | 212 | 06/05/19 | 172 | Ferguson Enterprises, Inc. #3007 |  | 15.24 | 7212764
AP | 212 | 06/08/19 | 293 | Rosen Supply Kirkland |  | 129 | 4267669-00
AP | 212 | 08/12/19 | 486 | Keller Supply Company |  | 1197.26 | S013276342.001
GL | 212 | 08/20/19 | 704 | Req 6248 |  | 2266.13
GL | 212 | 08/21/19 | 880 | Orlando Paco Leyva |  | 54.71
AP | 212 | 08/28/19 | 981 | Rosen Supply Kirkland |  | 10.54 | 4271391-00
AP | 212 | 08/31/19 | 1112 | Rosen Supply Kirkland |  | 6.46 | 4271391-01
GL | 212 | 09/16/19 | 355 | Req 6319 |  | 3353.29
AP | 212 | 11/21/19 | 798 | Capital One Credit Card |  | 25.34 | 1008919JB4
GL | 212 | 12/06/19 | 131 | Req 6612 |  | 3638.6
GL | 212 | 01/31/20 | 945 | Req 5773 |  | 2321.79
GL | 212 | 02/13/20 | 436 | 5961 Richard Anderson |  | 25.37
GL | 212 | 02/24/20 | 539 | Req 6824 |  | -752.63
GL | 212 | 02/24/20 | 570 | Req 6800 |  | 555.4
AP | 212 | 03/09/20 | 229 | Capital One Credit Card |  | 50.32 | 012920JB
GL | 220 | 04/24/19 | 703 | Req 5919 |  | 312.78
GL | 220 | 05/30/19 | 858 | Req 5943 |  | 1289.02
GL | 220 | 06/05/19 | 124 | Req 5234 |  | 62.56
GL | 220 | 07/10/19 | 172 | Req 6143 |  | 473.21
GL | 220 | 07/10/19 | 173 | Req 6142 |  | 805.45
GL | 220 | 07/10/19 | 174 | Req 6141 |  | 5900.35
AP | 220 | 07/16/19 | 447 | Rosen Supply Kirkland |  | 301.2 | 4269643-00
GL | 220 | 08/01/19 | 125 | Req 6199 |  | 990
AP | 220 | 08/08/19 | 208 | Rosen Supply Kirkland |  | 1351.35 | 4270157-00
GL | 220 | 08/08/19 | 227 | Req 6176 |  | 737.15
AP | 220 | 08/12/19 | 474 | Rosen Supply Kirkland |  | 203.22 | 4270463-00
AP | 220 | 08/12/19 | 475 | Rosen Supply Kirkland |  | 4064.11 | 4270471-00
AP | 220 | 08/14/19 | 548 | Rosen Supply Kirkland |  | 792.65 | 4270814-00
GL | 220 | 08/20/19 | 684 | Req 6250 |  | 239.52
GL | 220 | 08/20/19 | 707 | Req 6245 |  | 727.34
AP | 220 | 08/21/19 | 785 | Ferguson Enterprises, Inc. #3007 |  | 201.56 | 7433648
AP | 220 | 08/28/19 | 969 | Rosen Supply Kirkland |  | 961.4 | 4271024-00
AP | 220 | 08/28/19 | 972 | Rosen Supply Kirkland |  | 1479 | 4271216-00
AP | 220 | 08/28/19 | 986 | Rosen Supply Kirkland |  | 1969.16 | 4271466-00
AP | 220 | 08/30/19 | 1078 | Rosen Supply Kirkland |  | 290.2 | 4271564-00
AP | 220 | 08/30/19 | 1079 | Rosen Supply Kirkland |  | 783.6 | 4271588-00
AP | 220 | 08/30/19 | 1083 | Rosen Supply Kirkland |  | -18.43 | 4271676-00
AP | 220 | 08/31/19 | 1110 | Rosen Supply Kirkland |  | 701.1 | 4270471-01
AP | 220 | 08/31/19 | 1111 | Rosen Supply Kirkland |  | 21.45 | 4271216-01
AP | 220 | 09/01/19 | 399 | Rosen Supply Kirkland |  | -701.1 | 4270471-01A
AP | 220 | 09/01/19 | 400 | Rosen Supply Kirkland |  | 704.1 | 4270471-01B
AP | 220 | 09/04/19 | 6 | Consolidated Supply Co. |  | 6096.94 | S9284452.001
AP | 220 | 09/10/19 | 231 | Capital One Credit Card |  | 33.76 | 090319JB
GL | 220 | 09/16/19 | 356 | Req 6320 |  | 3359.76
GL | 220 | 09/16/19 | 357 | Req 6321 |  | 1167.9
AP | 220 | 09/16/19 | 387 | Rosen Supply Kirkland |  | 505.42 | 4271931-00
AP | 220 | 09/17/19 | 430 | Ferguson Enterprises, Inc. #3007 |  | 191.43 | 7538730
AP | 220 | 09/23/19 | 598 | Rosen Supply Kirkland |  | 53.64 | 4271931-01
AP | 220 | 09/23/19 | 599 | Rosen Supply Kirkland |  | 4028.24 | 4272056-00
AP | 220 | 09/23/19 | 600 | Rosen Supply Kirkland |  | 112.5 | 4271564-01
AP | 220 | 09/25/19 | 624 | Rosen Supply Kirkland |  | 800.35 | 4272347-00
AP | 220 | 09/25/19 | 626 | Rosen Supply Kirkland |  | 897.78 | 4272398-00
AP | 220 | 09/27/19 | 729 | Rosen Supply Kirkland |  | 36.51 | 4272578-00
AP | 220 | 09/27/19 | 730 | Rosen Supply Kirkland |  | 4383.35 | 4272629-00
AP | 220 | 09/30/19 | 761 | Rosen Supply Kirkland |  | 52.96 | 4272056-01
AP | 220 | 09/30/19 | 762 | Rosen Supply Kirkland |  | 968.42 | 4272747-00
AP | 220 | 10/08/19 | 164 | Consolidated Supply Co. |  | 6096.94 | S009297513.001
AP | 220 | 10/15/19 | 423 | Rosen Supply Kirkland |  | 170.52 | 4272964-00
AP | 220 | 10/15/19 | 433 | Rosen Supply Kirkland |  | 88 | 4273076-00
GL | 220 | 11/01/19 | 85 | Req 6458 |  | 7209.5
AP | 220 | 11/01/19 | 119 | Rosen Supply Kirkland |  | 122.76 | 4272747-01
AP | 220 | 11/01/19 | 120 | Rosen Supply Kirkland |  | 1959.46 | 4273257-00
GL | 220 | 11/04/19 | 124 | Req 6459 |  | 5019.29
GL | 220 | 11/04/19 | 128 | Req 6460 |  | 2993.15
GL | 220 | 11/04/19 | 132 | Req 6473 |  | 177.74
AP | 220 | 11/06/19 | 172 | Rosen Supply Kirkland |  | 47.43 | 4273257-01
GL | 220 | 11/11/19 | 310 | Req 6494 |  | 396
AP | 220 | 11/11/19 | 324 | Consolidated Supply Co. |  | 786.14 | S009478667.001
AP | 220 | 11/12/19 | 364 | Rosen Supply Kirkland |  | 760 | 1549114-00
AP | 220 | 11/12/19 | 365 | Rosen Supply Kirkland |  | 1196.3 | 1549115-00
AP | 220 | 11/12/19 | 388 | Rosen Supply Kirkland |  | 1416 | 4273654-00
AP | 220 | 11/12/19 | 389 | Rosen Supply Kirkland |  | 196.44 | 4273730-00
AP | 220 | 11/12/19 | 391 | Rosen Supply Kirkland |  | 87.95 | 4273772-00
GL | 220 | 11/13/19 | 414 | Req 6541 |  | 4897.94
GL | 220 | 11/13/19 | 415 | Req 6540 |  | 2892.89
AP | 220 | 11/16/19 | 548 | Rosen Supply Kirkland |  | 363.81 | 4273853-00
GL | 220 | 11/19/19 | 571 | Req 6576 |  | 477.34
AP | 220 | 11/20/19 | 597 | Rosen Supply Kirkland |  | 148.29 | 4273287-00
AP | 220 | 11/20/19 | 599 | Rosen Supply Kirkland |  | 1565.95 | 4274143-00
AP | 220 | 11/20/19 | 600 | Rosen Supply Kirkland |  | 1354.5 | 4274144-00
AP | 220 | 11/20/19 | 601 | Rosen Supply Kirkland |  | 123.32 | 4274171-00
AP | 220 | 11/20/19 | 603 | Rosen Supply Kirkland |  | 272.3 | 4274244-00
AP | 220 | 11/22/19 | 712 | Rosen Supply Kirkland |  | 30.19 | 4273287-01
AP | 220 | 11/22/19 | 713 | Rosen Supply Kirkland |  | 745.3 | 4274342-00
AP | 220 | 11/22/19 | 714 | Rosen Supply Kirkland |  | 1341 | 4274488-00
AP | 220 | 11/22/19 | 722 | Rosen Supply Kirkland |  | 149.95 | 4274143-01
AP | 220 | 11/22/19 | 728 | Rosen Supply Kirkland |  | 49.34 | 4274678-00
AP | 220 | 11/30/19 | 961 | Consolidated Supply Co. |  | 98.26 | S009503411.002
AP | 220 | 11/30/19 | 969 | Consolidated Supply Co. |  | 3832.42 | S009503411.001
AP | 220 | 11/30/19 | 970 | Consolidated Supply Co. |  | 164 | S009505549.001
AP | 220 | 12/05/19 | 116 | Rosen Supply Kirkland |  | 182.5 | 4274720-00
AP | 220 | 12/05/19 | 117 | Rosen Supply Kirkland |  | 51.04 | 4274779-00
AP | 220 | 12/05/19 | 118 | Rosen Supply Kirkland |  | 118.55 | 4274799-00
GL | 220 | 12/06/19 | 132 | Req 6614 |  | 1263.9
GL | 220 | 12/06/19 | 158 | Req 6613 |  | 2073.82
GL | 220 | 12/09/19 | 177 | Req 6639 |  | 595.2
AP | 220 | 12/09/19 | 212 | Rosen Supply Kirkland |  | 553.6 | 4274896-00
AP | 220 | 12/10/19 | 221 | Rosen Supply Kirkland |  | 7.65 | 4274928-00
AP | 220 | 12/10/19 | 224 | Rosen Supply Kirkland |  | 3023.81 | 4275033-00
AP | 220 | 12/10/19 | 225 | Rosen Supply Kirkland |  | 495 | 4275083-00
AP | 220 | 12/10/19 | 226 | Rosen Supply Kirkland |  | 10.22 | 4275105-00
AP | 220 | 12/10/19 | 227 | Rosen Supply Kirkland |  | 295.2 | 4275131-00
AP | 220 | 12/10/19 | 271 | Rosen Supply Kirkland |  | 399.5 | 4275394-00
AP | 220 | 12/10/19 | 279 | Rosen Supply Kirkland |  | 85.92 | 4275512-00
AP | 220 | 12/11/19 | 377 | Consolidated Supply Co. |  | 4127.73 | S009298072.001
AP | 220 | 12/11/19 | 378 | Consolidated Supply Co. |  | 982.57 | S009298079.001
AP | 220 | 12/12/19 | 492 | Rosen Supply Kirkland |  | 374.82 | 4275254-00
AP | 220 | 12/13/19 | 536 | Rosen Supply Kirkland |  | -35.48 | 4275719-00
AP | 220 | 12/13/19 | 537 | Rosen Supply Kirkland |  | 137.98 | 4275732-00
AP | 220 | 12/13/19 | 538 | Rosen Supply Kirkland |  | 43.5 | 4275769-00
AP | 220 | 12/13/19 | 539 | Rosen Supply Kirkland |  | 2206.99 | 4275033-01
AP | 220 | 12/13/19 | 540 | Rosen Supply Kirkland |  | 203.18 | 1552986-00
GL | 220 | 12/27/19 | 788 | Req 6696 |  | 1992.82
GL | 220 | 12/27/19 | 789 | Req 6697 |  | 1833.63
AP | 220 | 12/31/19 | 874 | Rosen Supply Kirkland |  | 383.86 | 4276183-00
AP | 220 | 01/06/20 | 142 | Consolidated Supply Co. |  | 2526.59 | S9284393.001
AP | 220 | 01/08/20 | 232 | Capital One Credit Card |  | 104 | 112119JB1
AP | 220 | 01/08/20 | 233 | Capital One Credit Card |  | 8.55 | 112219JB
AP | 220 | 01/08/20 | 246 | Rosen Supply Kirkland |  | 1819.23 | 4276790-00
AP | 220 | 01/08/20 | 254 | Rosen Supply Kirkland |  | 3.84 | 4276995-00
AP | 220 | 01/08/20 | 258 | Rosen Supply Kirkland |  | 498.77 | 4276926-00
AP | 220 | 01/08/20 | 259 | Rosen Supply Kirkland |  | 51.56 | 4277019-00
AP | 220 | 01/08/20 | 268 | Rosen Supply Kirkland |  | 53.08 | 4277067-00
AP | 220 | 01/10/20 | 450 | Capital One Credit Card |  | 32.34 | 120919JB
AP | 220 | 01/13/20 | 534 | Rosen Supply Kirkland |  | 112.86 | 4276183-01
AP | 220 | 01/14/20 | 491 | Consolidated Supply Co. |  | 6096.94 | S009598315.001
GL | 220 | 01/31/20 | 942 | Req 5770 |  | 2337.45
GL | 220 | 01/31/20 | 943 | Req 5771 |  | 805
AP | 220 | 02/10/20 | 146 | Rosen Supply Kirkland |  | 3916.69 | 4277470-00
AP | 220 | 02/10/20 | 147 | Rosen Supply Kirkland |  | 19.75 | 4277591-00
AP | 220 | 02/10/20 | 148 | Rosen Supply Kirkland |  | 92.34 | 4277702-00
AP | 220 | 02/12/20 | 227 | Rosen Supply Kirkland |  | 506.55 | 4277851-00
AP | 220 | 02/14/20 | 343 | Rosen Supply Kirkland |  | 221.56 | 4277470-01
AP | 220 | 02/14/20 | 344 | Rosen Supply Kirkland |  | 7746.34 | 4277817-01
AP | 220 | 02/14/20 | 345 | Rosen Supply Kirkland |  | 291.27 | 4278086-00
AP | 220 | 02/14/20 | 346 | Rosen Supply Kirkland |  | 44.95 | 4277470-02
AP | 220 | 02/18/20 | 413 | Rosen Supply Kirkland |  | 6391.18 | 4278203-00
AP | 220 | 02/18/20 | 415 | Rosen Supply Kirkland |  | 6.69 | 4278508-00
AP | 220 | 02/18/20 | 420 | Rosen Supply Kirkland |  | 23.3 | 4278508-01
AP | 220 | 02/19/20 | 432 | Consolidated Supply Co. |  | 5912.6 | S009298003.001
AP | 220 | 02/19/20 | 433 | Consolidated Supply Co. |  | 184.34 | S009298003.002
GL | 220 | 02/24/20 | 541 | Req 6826 |  | -58.45
GL | 220 | 02/24/20 | 558 | Req 6829 |  | 3229.23
GL | 220 | 02/24/20 | 572 | Req 6797 |  | 3832.44
GL | 220 | 02/24/20 | 573 | Req 6795 |  | 2552.67
AP | 220 | 02/26/20 | 672 | Rosen Supply Kirkland |  | 92.94 | 4278203-02
AP | 220 | 02/29/20 | 816 | Rosen Supply Kirkland |  | 54.98 | 4279020-00
AP | 220 | 02/29/20 | 817 | Rosen Supply Kirkland |  | 109.48 | 4279202-00
AP | 220 | 02/29/20 | 818 | Rosen Supply Kirkland |  | 106.23 | 4279249-00
AP | 220 | 02/29/20 | 820 | Rosen Supply Kirkland |  | 24.6 | 4279357-00
AP | 220 | 03/03/20 | 9 | Rosen Supply Kirkland |  | 20.44 | 4279452-00
GL | 220 | 03/13/20 | 402 | Req 6862 |  | 1455.23
AP | 220 | 03/16/20 | 449 | Rosen Supply Kirkland |  | 514.9 | 4279683-00
AP | 220 | 03/16/20 | 450 | Rosen Supply Kirkland |  | 166.68 | 4279712-00
AP | 220 | 03/16/20 | 461 | Rosen Supply Kirkland |  | 437.8 | 4279842-00
AP | 220 | 03/18/20 | 540 | Rosen Supply Kirkland |  | 312.55 | 4279930-00
AP | 220 | 03/18/20 | 555 | Rosen Supply Kirkland |  | 411.35 | 4280048-00
AP | 220 | 03/18/20 | 556 | Rosen Supply Kirkland |  | 315.8 | 4280184-00
GL | 220 | 03/20/20 | 661 | Req 6916 |  | -174.6
GL | 220 | 03/20/20 | 676 | Req 6911 |  | 1563.24
AP | 220 | 03/24/20 | 736 | Rosen Supply Kirkland |  | 88 | 4280415-00
GL | 220 | 03/26/20 | 846 | Req 6938 |  | -302.5
AP | 220 | 03/27/20 | 857 | Rosen Supply Kirkland |  | 26.48 | 4280464-00
AP | 220 | 03/27/20 | 860 | Rosen Supply Kirkland |  | 191.96 | 4280507-00
AP | 220 | 03/27/20 | 861 | Rosen Supply Kirkland |  | -13.68 | 4280518-00
AP | 220 | 03/27/20 | 865 | Rosen Supply Kirkland |  | 67.25 | 4280600-00
AP | 220 | 04/13/20 | 152 | Rosen Supply Kirkland |  | 149.5 | 4280648-00
GL | 220 | 05/05/20 | 99 | Req 6966 |  | 198.79
GL | 220 | 05/05/20 | 100 | Req 6965 |  | 1296.89
AP | 220 | 05/06/20 | 148 | Rosen Supply Kirkland |  | 786.18 | 4281290-00
GL | 220 | 05/11/20 | 263 | Req 6989 |  | 303.58
AP | 220 | 05/11/20 | 271 | Rosen Supply Kirkland |  | 25.22 | 4281483-00
GL | 220 | 05/14/20 | 389 | Req 7007 |  | -45.43
AP | 220 | 05/19/20 | 411 | Consolidated Supply Co. |  | 168.3 | S009768227.001
AP | 220 | 05/19/20 | 412 | Consolidated Supply Co. |  | 3025.8 | S009769615.001
AP | 220 | 05/19/20 | 425 | Rosen Supply Kirkland |  | 263.95 | 4281699-00
AP | 220 | 05/19/20 | 432 | Rosen Supply Kirkland |  | 3136.8 | 4281731-00
AP | 220 | 05/22/20 | 558 | Rosen Supply Kirkland |  | 9.91 | 4281483-01
GL | 220 | 05/22/20 | 562 | Req 7040 |  | 2530.01
GL | 220 | 05/27/20 | 574 | Req 7043 |  | 36.29
GL | 220 | 05/27/20 | 577 | Req 7041 |  | 481.29
GL | 220 | 05/31/20 | 680 | Req 7071 |  | 1029.3
AP | 220 | 05/31/20 | 745 | Rosen Supply Kirkland |  | 29.24 | 4282239-00
GL | 220 | 06/03/20 | 4 | Req 7093 |  | 493.75
AP | 220 | 06/08/20 | 134 | Capital One Credit Card |  | 10.2 | 050420JB
AP | 220 | 06/09/20 | 148 | Rosen Supply Kirkland |  | 40.45 | 4282265-00
AP | 220 | 06/09/20 | 149 | Rosen Supply Kirkland |  | 402.16 | 4282384-00
AP | 220 | 06/09/20 | 152 | Rosen Supply Kirkland |  | 111 | 4282475-00
AP | 220 | 06/12/20 | 309 | Capital One Credit Card |  | 30.85 | 060420JB
AP | 220 | 06/15/20 | 314 | Consolidated Supply Co. |  | 403.44 | S009803773.001
GL | 220 | 06/16/20 | 337 | Req 7099 |  | 322.73
AP | 220 | 06/25/20 | 363 | Rosen Supply Kirkland |  | 516.59 | 4282623-00
AP | 220 | 06/30/20 | 608 | Rosen Supply Kirkland |  | 35.8 | 4283047-00
AP | 220 | 06/30/20 | 609 | Rosen Supply Kirkland |  | 93.32 | 4282953-01
GL | 220 | 07/02/20 | 62 | Req 7141 |  | 330.2
GL | 220 | 07/07/20 | 84 | Req 7150 |  | 351.87
AP | 220 | 07/08/20 | 100 | Rosen Supply Kirkland |  | 609.83 | 4282953-00
AP | 220 | 07/08/20 | 124 | Rosen Supply Kirkland |  | 733.65 | 4283338-00
AP | 220 | 07/13/20 | 234 | Rosen Supply Kirkland |  | 26.06 | 4283587-00
AP | 220 | 07/13/20 | 248 | Rosen Supply Kirkland |  | 219.5 | 4283709-00
GL | 220 | 07/16/20 | 319 | Req 6473 adj |  | -177.74
AP | 220 | 07/22/20 | 379 | Rosen Supply Kirkland |  | 83.1 | 4283768-00
AP | 220 | 07/23/20 | 396 | Rosen Supply Kirkland |  | 603.95 | 4283867-00
AP | 220 | 08/03/20 | 14 | Manor Hardware & Construction Supply |  | 225 | 61828-00
GL | 220 | 08/04/20 | 33 | Req 7190 |  | 2876.73
AP | 220 | 08/04/20 | 34 | Consolidated Supply Co. |  | 3500.75 | S9284177.001
AP | 220 | 08/05/20 | 55 | Rosen Supply Kirkland |  | 702.83 | 4284308-00
AP | 220 | 08/05/20 | 75 | Rosen Supply Kirkland |  | 100.07 | 4284454-00
AP | 220 | 08/05/20 | 78 | Consolidated Supply Co. |  | 224.4 | S009880871.001
AP | 220 | 08/10/20 | 211 | Capital One Credit Card |  | 22.96 | 061520JB
AP | 220 | 08/10/20 | 214 | Capital One Credit Card |  | 31.87 | 062320JB
AP | 220 | 08/12/20 | 288 | Capital One Credit Card |  | 52.71 | 080520JB
AP | 220 | 08/12/20 | 289 | Capital One Credit Card |  | 35.13 | 071320JB
AP | 220 | 08/14/20 | 348 | Consolidated Supply Co. |  | 3500.75 | S9284397.001
AP | 220 | 08/14/20 | 358 | Rosen Supply Kirkland |  | 382.85 | 4284806-00
AP | 220 | 08/14/20 | 359 | Rosen Supply Kirkland |  | 139.66 | 4284897-00
AP | 220 | 08/14/20 | 360 | Rosen Supply Kirkland |  | 57.22 | 4284942-00
AP | 220 | 08/14/20 | 361 | Rosen Supply Kirkland |  | 415.24 | 4285016-00
GL | 220 | 08/17/20 | 368 | Req 7239 |  | 111.01
GL | 220 | 08/17/20 | 386 | Req 7232 |  | 2771.82
GL | 220 | 08/17/20 | 387 | Req 7233 |  | 57.75
AP | 220 | 08/18/20 | 408 | Rosen Supply Kirkland |  | 99 | 4285129-00
AP | 220 | 08/26/20 | 531 | Rosen Supply Kirkland |  | 69.83 | 4285219-00
AP | 220 | 08/26/20 | 551 | Rosen Supply Kirkland |  | 21.26 | 4284941-00
AP | 220 | 08/26/20 | 552 | Rosen Supply Kirkland |  | 27.73 | 4285461-00
AP | 220 | 09/11/20 | 147 | Consolidated Supply Co. |  | 3550.75 | S9284209.001
AP | 220 | 09/11/20 | 158 | Rosen Supply Kirkland |  | 54.73 | 4285546-00
GL | 220 | 09/14/20 | 185 | Req 7289 |  | -511.55
GL | 220 | 09/14/20 | 200 | Req 7268 |  | 2845.68
AP | 220 | 09/18/20 | 342 | Rosen Supply Kirkland |  | 18.45 | 4286081-00
AP | 220 | 09/21/20 | 363 | Rosen Supply Kirkland |  | 58.6 | 4286145-00
GL | 220 | 09/22/20 | 372 | Req 7294 |  | -409.46
GL | 220 | 09/22/20 | 373 | Req 7295 |  | -2299.11
GL | 220 | 09/22/20 | 374 | Req 7296 |  | -988.01
AP | 220 | 09/22/20 | 387 | Rosen Supply Kirkland |  | 46.28 | 4286359-00
AP | 220 | 09/24/20 | 488 | Rosen Supply Kirkland |  | 20.4 | 4286542-00
GL | 220 | 09/29/20 | 536 | Req 7328 |  | 751.38
AP | 220 | 10/01/20 | 63 | Consolidated Supply Co. |  | -3550.75 | S9284209.001A
AP | 220 | 10/01/20 | 64 | Consolidated Supply Co. |  | 3500.75 | S9284209.001B
GL | 220 | 10/08/20 | 204 | Req 7352 |  | -1475.48
AP | 220 | 10/15/20 | 376 | Rosen Supply Kirkland |  | 183.15 | 4287131-00
AP | 220 | 10/15/20 | 378 | Rosen Supply Kirkland |  | 3.96 | 4286359-01
AP | 220 | 10/15/20 | 379 | Rosen Supply Kirkland |  | 30.05 | 4287217-00
GL | 220 | 10/20/20 | 423 | Req 7379 |  | 120.7
AP | 220 | 11/16/20 | 302 | Rosen Supply Kirkland |  | 125.28 | 4288579-00
GL | 220 | 11/16/20 | 317 | Req 7435 |  | 443.52
GL | 220 | 12/03/20 | 76 | Req 7488 |  | 36.21
GL | 220 | 12/22/20 | 478 | Req 7509 |  | 31.73
GL | 220 | 12/31/20 | 686 | Req 7522 |  | 121.33
AP | 220 | 02/16/21 | 366 | Rosen Supply Kirkland |  | 109.8 | 1579145-00
AP | 220 | 02/22/21 | 516 | Rosen Supply Kirkland |  | 106.88 | 4292104-00
AP | 220 | 03/09/21 | 152 | Rosen Supply Kirkland |  | 51.01 | 4292650-00
GL | 220 | 03/23/21 | 374 | Req 7639 |  | -637.48
GL | 220 | 03/24/21 | 451 | Req 7643 |  | -135.17
GL | 220 | 03/24/21 | 452 | Req 7642 |  | -197.96
GL | 220 | 03/24/21 | 453 | Req 7641 |  | -234.86
GL | 220 | 03/24/21 | 454 | Req 7640 |  | -1156.77
AP | 230 | 04/10/19 | 317 | Old Castle Infrastructure, Inc. |  | 1586 | 11000157
GL | 230 | 04/30/19 | 895 | Req 5932 |  | 530.38
GL | 230 | 05/13/19 | 298 | Req 5193 |  | 623.28
AP | 230 | 05/29/19 | 798 | Old Castle Infrastructure, Inc. |  | 1752 | 11000366
GL | 230 | 06/05/19 | 125 | Req 5233 |  | 260.75
AP | 230 | 06/13/19 | 783 | Old Castle Infrastructure, Inc. |  | 2912 | 11000513
GL | 230 | 07/10/19 | 198 | Req 6116 |  | 1049.96
AP | 230 | 07/31/19 | 737 | Keller Supply Company |  | 4870.94 | S013198881.001
AP | 230 | 08/07/19 | 191 | Rosen Supply Kirkland |  | 82.97 | 4269919-00
GL | 230 | 08/08/19 | 226 | Req 6175 |  | 403.4
AP | 230 | 08/10/19 | 445 | Rosen Supply Kirkland |  | 718.84 | 4270194-00
AP | 230 | 08/12/19 | 481 | Consolidated Supply Co. |  | 715.24 | S009349260.001
AP | 230 | 08/19/19 | 664 | Consolidated Supply Co. |  | 2366.41 | S009366170.001
AP | 230 | 08/19/19 | 665 | Consolidated Supply Co. |  | 105.16 | S009366170.002
GL | 230 | 08/20/19 | 683 | Req 6249 |  | 80.84
GL | 230 | 08/20/19 | 705 | Req 6247 |  | 3652.92
AP | 230 | 08/28/19 | 958 | Rosen Supply Kirkland |  | 173.51 | 4270724-00
AP | 230 | 08/28/19 | 971 | Rosen Supply Kirkland |  | 13994 | 4269469-00
AP | 230 | 08/28/19 | 984 | Rosen Supply Kirkland |  | 340.27 | 4269469-01
AP | 230 | 08/28/19 | 985 | Rosen Supply Kirkland |  | 14377.2 | 4269470-00
AP | 230 | 08/30/19 | 1082 | Rosen Supply Kirkland |  | 1361.08 | 4269468-00
AP | 230 | 08/30/19 | 1087 | Rosen Supply Kirkland |  | 1063.74 | 4269468-01
AP | 230 | 08/30/19 | 1088 | Rosen Supply Kirkland |  | 14377.2 | 4269472-00
AP | 230 | 08/31/19 | 1140 | Keller Supply Company |  | 111.41 | S013263384.001
AP | 230 | 08/31/19 | 1141 | Keller Supply Company |  | 36.38 | S013263384.002
GL | 230 | 09/16/19 | 359 | Req 6323 |  | 3625.26
AP | 230 | 10/07/19 | 140 | Rosen Supply Kirkland |  | 2194.96 | 4272359-00
AP | 230 | 10/25/19 | 758 | Consolidated Supply Co. |  | 734.83 | S009468989.001
GL | 230 | 11/04/19 | 126 | Req 6463 |  | 15660.49
AP | 230 | 11/11/19 | 323 | Consolidated Supply Co. |  | 31.7 | S009466741.001
AP | 230 | 11/11/19 | 325 | Consolidated Supply Co. |  | 1189.65 | S009485483.001
AP | 230 | 11/11/19 | 335 | Ferguson Enterprises, Inc. #3007 |  | 218.13 | 7540303
AP | 230 | 11/12/19 | 390 | Rosen Supply Kirkland |  | 561.72 | 4273349-00
GL | 230 | 11/13/19 | 416 | Req 6542 |  | 4817.52
AP | 230 | 11/20/19 | 602 | Rosen Supply Kirkland |  | 14036.93 | 4269465-00
AP | 230 | 12/03/19 | 12 | Rosen Supply Kirkland |  | 14079.86 | 4269467-00
GL | 230 | 12/06/19 | 140 | Req 6626 |  | 417.2
GL | 230 | 12/09/19 | 174 | Req 6636 |  | 44.79
AP | 230 | 12/10/19 | 233 | California Hydronics Corp |  | 377 | SIN036958
AP | 230 | 12/10/19 | 264 | Rosen Supply Kirkland |  | 2424.82 | 4269464-00
AP | 230 | 12/10/19 | 265 | Rosen Supply Kirkland |  | 13994 | 4269466-00
AP | 230 | 12/10/19 | 280 | Rosen Supply Kirkland |  | 1361.08 | 4269464-01
AP | 230 | 12/12/19 | 506 | Keller Supply Company |  | 4465.03 | S013198911.001
AP | 230 | 12/19/19 | 687 | California Hydronics Corp |  | 5500 | SIN038859
AP | 230 | 12/19/19 | 688 | California Hydronics Corp |  | 5500 | SIN038912
GL | 230 | 12/27/19 | 791 | Req 6699 |  | 2023.3
AP | 230 | 12/31/19 | 853 | Manor Hardware & Construction Supply |  | 206.25 | 21282-00
AP | 230 | 01/03/20 | 95 | Rosen Supply Kirkland |  | 57.95 | 4276308-00
AP | 230 | 01/13/20 | 510 | Keller Supply Company |  | 3775.54 | S013691924.001
AP | 230 | 01/13/20 | 511 | Keller Supply Company |  | 601.86 | S013733623.001
AP | 230 | 01/13/20 | 533 | Rosen Supply Kirkland |  | 341.42 | 4273733-00
AP | 230 | 01/29/20 | 831 | Keller Supply Company |  | 7246.9 | S013825833.001
GL | 230 | 01/30/20 | 914 | Richard Anderson |  | 32.36
GL | 230 | 01/31/20 | 941 | Req 5769 |  | 4293.44
AP | 230 | 02/10/20 | 190 | Keller Supply Company |  | 10939.75 | S013733623.002
AP | 230 | 02/10/20 | 191 | Keller Supply Company |  | 3775.54 | S013691924.002
AP | 230 | 02/10/20 | 192 | Keller Supply Company |  | 441.96 | S013691950.001
AP | 230 | 02/10/20 | 193 | Keller Supply Company |  | 943.51 | S013733623.003
AP | 230 | 02/10/20 | 194 | Keller Supply Company |  | 6811.95 | S013733652.001
AP | 230 | 02/10/20 | 195 | Keller Supply Company |  | 324.6 | S013898506.001
AP | 230 | 02/17/20 | 352 | Rosen Supply Kirkland |  | 99.52 | 4278094-00
AP | 230 | 02/18/20 | 416 | Rosen Supply Kirkland |  | 11111.7 | 4273733-01
AP | 230 | 02/18/20 | 417 | Rosen Supply Kirkland |  | 2428.49 | 4275950-00
AP | 230 | 02/18/20 | 418 | Rosen Supply Kirkland |  | 744.42 | 4275953-00
AP | 230 | 02/18/20 | 419 | Rosen Supply Kirkland |  | 91.88 | 4278324-00
GL | 230 | 02/24/20 | 568 | Req 6803 |  | 2371.33
GL | 230 | 02/24/20 | 569 | Req 6802 |  | 6572.14
AP | 230 | 02/25/20 | 607 | Rosen Supply Kirkland |  | 81.18 | 4278640-00
AP | 230 | 02/26/20 | 633 | Keller Supply Company |  | 4870.94 | S013198905.001
AP | 230 | 02/26/20 | 634 | Keller Supply Company |  | 2841.38 | S013198920.001
AP | 230 | 02/26/20 | 635 | Keller Supply Company |  | 75.6 | S013907998.001
AP | 230 | 02/26/20 | 636 | Keller Supply Company |  | 3642.07 | S013691924.003
AP | 230 | 02/26/20 | 654 | Ferguson Enterprises, Inc. #3007 |  | 77.98 | 7983788
AP | 230 | 02/28/20 | 786 | Keller Supply Company |  | 12484.67 | S013733628.001
AP | 230 | 02/29/20 | 819 | Rosen Supply Kirkland |  | 60.01 | 4279279-00
AP | 230 | 03/03/20 | 8 | Rosen Supply Kirkland |  | -134.82 | 4279445-00
AP | 230 | 03/09/20 | 155 | Mechanical Sales, Inc. |  | 175 | 707102
AP | 230 | 03/09/20 | 187 | Capital One Credit Card |  | 44.46 | 012120J
AP | 230 | 03/09/20 | 188 | Capital One Credit Card |  | 97.66 | 012820J
GL | 230 | 03/10/20 | 235 | Req 6866 |  | 73.17
GL | 230 | 03/13/20 | 404 | Req 6861 |  | 2216.31
AP | 230 | 03/16/20 | 438 | Keller Supply Company |  | 12337.9 | S013733624.001
AP | 230 | 03/16/20 | 457 | Rosen Supply Kirkland |  | 11453.12 | 4273734-00
AP | 230 | 03/18/20 | 537 | Keller Supply Company |  | 188.45 | S014028938.001
AP | 230 | 03/18/20 | 559 | Rosen Supply Kirkland |  | 321.25 | 4280237-00
GL | 230 | 03/20/20 | 675 | Req 6910 |  | 1723.67
GL | 230 | 03/20/20 | 685 | Req 6893 |  | -678.96
AP | 230 | 03/27/20 | 858 | Rosen Supply Kirkland |  | 29.46 | 1560811-00
AP | 230 | 03/27/20 | 868 | Rosen Supply Kirkland |  | 11678.08 | 4273735-00
AP | 230 | 03/27/20 | 875 | Rosen Supply Kirkland |  | 61.5 | 4280753-00
AP | 230 | 04/13/20 | 150 | Rosen Supply Kirkland |  | -73.11 | 4280533-00
AP | 230 | 04/15/20 | 182 | Capital One Credit Card |  | 46.32 | 031220A
AP | 230 | 04/21/20 | 303 | Rosen Supply Kirkland |  | 3785.9 | 4269455-00
AP | 230 | 04/21/20 | 304 | Rosen Supply Kirkland |  | 14036.93 | 4269459-00
AP | 230 | 04/21/20 | 305 | Rosen Supply Kirkland |  | 14079.86 | 4269460-00
AP | 230 | 04/21/20 | 306 | Rosen Supply Kirkland |  | 680.54 | 4269461-00
AP | 230 | 04/21/20 | 307 | Rosen Supply Kirkland |  | 12632.92 | 4269461-01
AP | 230 | 04/21/20 | 319 | Rosen Supply Kirkland |  | 680.54 | 4269461-02
AP | 230 | 04/21/20 | 322 | Keller Supply Company |  | 1696.65 | S013691924.004
GL | 230 | 05/05/20 | 101 | Req 6964 |  | 888.78
AP | 230 | 05/06/20 | 146 | Keller Supply Company |  | 3614.69 | S013691886.001
AP | 230 | 05/06/20 | 147 | Keller Supply Company |  | 2905 | S013733606.001
GL | 230 | 05/11/20 | 264 | Req 6988 |  | 3412.1
AP | 230 | 05/11/20 | 281 | Rosen Supply Kirkland |  | 23.02 | 4281553-00
AP | 230 | 05/12/20 | 289 | Keller Supply Company |  | 138.39 | S014055138.001
AP | 230 | 05/12/20 | 291 | Rosen Supply Kirkland |  | 23.02 | 4281553-01
AP | 230 | 05/19/20 | 419 | Keller Supply Company |  | 335.61 | S014217412.001
AP | 230 | 05/19/20 | 424 | Rosen Supply Kirkland |  | 12.34 | 4281688-00
AP | 230 | 05/19/20 | 430 | Rosen Supply Kirkland |  | 2919.52 | 4273737-00
AP | 230 | 05/19/20 | 431 | Rosen Supply Kirkland |  | 262.8 | 4280528-00
AP | 230 | 05/22/20 | 559 | Rosen Supply Kirkland |  | 19.82 | 4281688-01
AP | 230 | 05/22/20 | 560 | Rosen Supply Kirkland |  | 11453.12 | 4273743-00
GL | 230 | 05/27/20 | 579 | Req 7038 |  | 4562.11
GL | 230 | 05/31/20 | 684 | Req 7070 |  | 137.3
AP | 230 | 05/31/20 | 732 | Keller Supply Company |  | 3881.62 | S013691886.002
AP | 230 | 05/31/20 | 733 | Keller Supply Company |  | 8943.07 | S013733598.001
AP | 230 | 05/31/20 | 744 | Rosen Supply Kirkland |  | 609.6 | 4275953-01
AP | 230 | 06/04/20 | 71 | Core & Main LP $HD Supply Waterworks |  | 861.61 | M423520
AP | 230 | 06/05/20 | 86 | Keller Supply Company |  | 3171.94 | S013733598.002
AP | 230 | 06/05/20 | 87 | Keller Supply Company |  | 255.83 | S014209294.001
AP | 230 | 06/09/20 | 138 | California Hydronics Corp |  | 5500 | SIN053885
AP | 230 | 06/09/20 | 151 | Rosen Supply Kirkland |  | 181.45 | 4282448-00
AP | 230 | 06/12/20 | 293 | Capital One Credit Card |  | 31.44 | 052020A
GL | 230 | 06/16/20 | 338 | Req 7100 |  | 1574.42
AP | 230 | 06/23/20 | 471 | Keller Supply Company |  | 3748.16 | S013691886.003
AP | 230 | 06/23/20 | 472 | Keller Supply Company |  | 12395.13 | S013733573.001
AP | 230 | 06/23/20 | 473 | Keller Supply Company |  | 1010.42 | S014343527.001
AP | 230 | 06/24/20 | 500 | Rosen Supply Kirkland |  | 11420.9 | 4273744-00
AP | 230 | 06/25/20 | 355 | Keller Supply Company |  | 2346.69 | S014196415.001
AP | 230 | 06/25/20 | 356 | Keller Supply Company |  | 288.59 | S014307084.001
AP | 230 | 06/25/20 | 357 | Keller Supply Company |  | 20.74 | S014307131.001
GL | 230 | 07/02/20 | 60 | Req 7143 |  | 22.57
GL | 230 | 07/02/20 | 61 | Req 7142 |  | 2230.55
GL | 230 | 07/07/20 | 83 | Req 7149 |  | 748.1
AP | 230 | 07/08/20 | 102 | Core & Main LP $HD Supply Waterworks |  | 119.87 | M483850
AP | 230 | 07/08/20 | 115 | Keller Supply Company |  | 1386.8 | S014241915.001
GL | 230 | 07/10/20 | 193 | Req 7170 |  | -306.38
AP | 230 | 07/13/20 | 247 | Rosen Supply Kirkland |  | 125.35 | 4282448-01
GL | 230 | 07/17/20 | 327 | Req 7179 |  | 3414.02
AP | 230 | 07/17/20 | 352 | Keller Supply Company |  | 2842.05 | S013691886.004
AP | 230 | 07/17/20 | 353 | Keller Supply Company |  | 12264.08 | S0137335939.001
AP | 230 | 07/17/20 | 354 | Keller Supply Company |  | 111.62 | S014307084.002
AP | 230 | 07/22/20 | 387 | Rosen Supply Kirkland |  | 11678.08 | 4273745-00
AP | 230 | 07/22/20 | 388 | Rosen Supply Kirkland |  | 32.22 | 4273744-01
AP | 230 | 07/22/20 | 389 | Rosen Supply Kirkland |  | 1582.9 | 4275951-00
GL | 230 | 07/24/20 | 469 | Req 7191 |  | 1848.85
AP | 230 | 08/05/20 | 50 | Keller Supply Company |  | 3549.86 | S013733520.001
AP | 230 | 08/05/20 | 62 | Rosen Supply Kirkland |  | 16418.82 | 4269474-00
AP | 230 | 08/05/20 | 63 | Rosen Supply Kirkland |  | 680.54 | 4269476-00
AP | 230 | 08/05/20 | 64 | Rosen Supply Kirkland |  | 15738.28 | 4269476-01
AP | 230 | 08/05/20 | 65 | Rosen Supply Kirkland |  | 4014.34 | 4273746-00
AP | 230 | 08/05/20 | 66 | Rosen Supply Kirkland |  | 1051.2 | 4275953-02
AP | 230 | 08/05/20 | 82 | Keller Supply Company |  | 494.22 | S013733520.002
AP | 230 | 08/10/20 | 192 | Capital One Credit Card |  | 7.01 | 062520A
AP | 230 | 08/10/20 | 195 | Capital One Credit Card |  | 2.73 | 070220A
AP | 230 | 08/10/20 | 236 | Capital One Credit Card |  | 61.69 | 072820A
AP | 230 | 08/10/20 | 238 | Capital One Credit Card |  | 2.44 | 080420A
AP | 230 | 08/10/20 | 239 | Capital One Credit Card |  | 11980 | 070720R
AP | 230 | 08/10/20 | 261 | Keller Supply Company |  | 815.16 | S01449787.001
AP | 230 | 08/11/20 | 274 | Ferguson Enterprises, Inc. #3007 |  | 507 | 8482853
AP | 230 | 08/11/20 | 275 | Ferguson Enterprises, Inc. #3007 |  | 1581 | 8482853-1
AP | 230 | 08/12/20 | 287 | Capital One Credit Card |  | 44.13 | 080420JB
AP | 230 | 08/14/20 | 350 | Ferguson Enterprises, Inc. #3007 |  | 450 | 8482853-2
AP | 230 | 08/14/20 | 351 | Ferguson Enterprises, Inc. #3007 |  | 2638.5 | 8486200
GL | 230 | 08/17/20 | 385 | Req 7231 |  | 3398.38
AP | 230 | 08/26/20 | 524 | Keller Supply Company |  | -11.12 | S014307084.003
AP | 230 | 08/26/20 | 530 | Rosen Supply Kirkland |  | 1248.3 | 4280528-01
AP | 230 | 08/26/20 | 550 | Rosen Supply Kirkland |  | 11453.12 | 4279586-00
GL | 230 | 09/14/20 | 188 | Req 7286 |  | -672.81
GL | 230 | 09/14/20 | 190 | Req 7284 |  | -73.3
GL | 230 | 09/14/20 | 193 | Req 7281 |  | -316.95
GL | 230 | 09/14/20 | 199 | Req 7269 |  | 398.65
AP | 230 | 09/15/20 | 223 | Capital One Credit Card |  | 16.35 | 081920A2
AP | 230 | 09/16/20 | 274 | Keller Supply Company |  | 3696.82 | S013691818.001
GL | 230 | 09/22/20 | 375 | Req 7297 |  | -492.41
AP | 230 | 09/22/20 | 380 | Ferguson Enterprises, Inc. #3007 |  | 2301.65 | 8586421
AP | 230 | 09/22/20 | 386 | Rosen Supply Kirkland |  | 70.24 | 4286260-00
AP | 230 | 09/24/20 | 484 | Ferguson Enterprises, Inc. #3007 |  | 124.4 | 8610955
GL | 230 | 09/29/20 | 537 | Req 7327 |  | 2335.2
AP | 230 | 10/02/20 | 80 | Keller Supply Company |  | 234.83 | S014704074.001
AP | 230 | 10/05/20 | 104 | Keller Supply Company |  | 24.88 | S014729383.001
AP | 230 | 10/13/20 | 265 | Capital One Credit Card |  | 24.87 | 093020A2
AP | 230 | 10/15/20 | 369 | Keller Supply Company |  | 221.13 | S014694668.001
AP | 230 | 10/15/20 | 375 | Rosen Supply Kirkland |  | 1951.35 | 4284459-00
AP | 230 | 10/15/20 | 377 | Rosen Supply Kirkland |  | 11453.12 | 4279585-00
AP | 230 | 10/15/20 | 380 | Rosen Supply Kirkland |  | -250 | 4287321-00
GL | 230 | 10/20/20 | 419 | Req 7375 |  | 325.65
AP | 230 | 10/26/20 | 517 | Keller Supply Company |  | 3794.9 | S013691818.002
AP | 230 | 10/27/20 | 574 | Keller Supply Company |  | 12488.45 | S013733498.001
AP | 230 | 11/16/20 | 280 | Rosen Supply Kirkland |  | 11228.16 | 4279584-00
AP | 230 | 11/16/20 | 281 | Rosen Supply Kirkland |  | 3157.92 | 4279588-00
GL | 230 | 11/16/20 | 318 | Req 7434 |  | 2389.91
AP | 230 | 11/20/20 | 430 | Keller Supply Company |  | 3661.44 | S013691818.003
AP | 230 | 11/23/20 | 445 | Keller Supply Company |  | 12408.81 | S013733481.001
GL | 230 | 12/03/20 | 75 | Req 7487 |  | 1353.14
AP | 230 | 12/08/20 | 141 | Rosen Supply Kirkland |  | 4677.12 | 4273748-00
AP | 230 | 12/08/20 | 142 | Rosen Supply Kirkland |  | 3744 | 4273748-01
AP | 230 | 12/08/20 | 143 | Rosen Supply Kirkland |  | 764.16 | 4273749-00
AP | 230 | 12/08/20 | 144 | Rosen Supply Kirkland |  | 7488 | 42723749-01
GL | 230 | 12/15/20 | 261 | Req 7499 |  | 1512.52
AP | 230 | 12/16/20 | 280 | Keller Supply Company |  | 12261.96 | S013733468.001
AP | 230 | 12/16/20 | 314 | Capital One Credit Card |  | 9.76 | 111420AS
AP | 230 | 12/16/20 | 315 | Capital One Credit Card |  | 14.27 | 112020AS
GL | 230 | 12/31/20 | 687 | Req 7521 |  | 857.58
GL | 230 | 01/27/21 | 377 | Req 7558 |  | 791.06
GL | 230 | 01/27/21 | 379 | Req 7555 |  | 1671.68
AP | 230 | 01/31/21 | 325 | Keller Supply Company |  | 3350.12 | S013691965.001
AP | 230 | 01/31/21 | 326 | Keller Supply Company |  | 12401.34 | S013733702.001
AP | 230 | 01/31/21 | 459 | Rosen Supply Kirkland |  | 44.54 | 4290807-00
AP | 230 | 02/02/21 | 47 | Rosen Supply Kirkland |  | 357.5 | 4290893-00
AP | 230 | 02/08/21 | 198 | Capital One Credit Card |  | 8.15 | 011321A
AP | 230 | 02/08/21 | 199 | Capital One Credit Card |  | 8.15 | 011521A
AP | 230 | 02/10/21 | 238 | Rosen Supply Kirkland |  | 30.24 | 4290807-01
AP | 230 | 02/10/21 | 248 | Keller Supply Company |  | 12032.32 | S013733722.001
AP | 230 | 02/10/21 | 249 | Keller Supply Company |  | 3350.12 | S013691951.001
AP | 230 | 02/17/21 | 398 | Rosen Supply Kirkland |  | 291.13 | 4291824-00
AP | 230 | 02/17/21 | 409 | Keller Supply Company |  | 237.23 | S01373396.001
GL | 230 | 02/18/21 | 481 | Req 7593 |  | 1676.76
AP | 230 | 02/22/21 | 515 | Rosen Supply Kirkland |  | 21.4 | 4292017-00
AP | 230 | 02/23/21 | 566 | Keller Supply Company |  | 224.62 | S013733722.002
AP | 230 | 02/23/21 | 567 | Keller Supply Company |  | 144.4 | S013733722.003
AP | 230 | 02/23/21 | 568 | Rosen Supply Kirkland |  | 624 | 4292106-00
AP | 230 | 03/02/21 | 11 | Kele, Inc $ MI Controls |  | 69.2 | IMIS0807010910
AP | 230 | 03/03/21 | 44 | Keller Supply Company |  | 2996.47 | S013691818.004
AP | 230 | 03/03/21 | 45 | Keller Supply Company |  | 3924.88 | S013733396.002
AP | 230 | 03/03/21 | 46 | Keller Supply Company |  | 41.48 | S015163779.001
AP | 230 | 03/03/21 | 47 | Keller Supply Company |  | 327.85 | S015187111.001
AP | 230 | 03/05/21 | 125 | Ferguson Enterprises, Inc. #3007 |  | 3.47 | 9067911
AP | 230 | 03/23/21 | 412 | Capital One Credit Card |  | 27.45 | 021621A
AP | 230 | 03/23/21 | 413 | Capital One Credit Card |  | 12.2 | 021821A
AP | 230 | 03/23/21 | 414 | Capital One Credit Card |  | 2.14 | 021921A
AP | 230 | 03/23/21 | 415 | Capital One Credit Card |  | 12.14 | 022421A
GL | 230 | 03/24/21 | 450 | Req 7644 |  | -1445.46
AP | 230 | 03/24/21 | 487 | Rosen Supply Kirkland |  | 440 | 4292662-00
GL | 230 | 03/25/21 | 506 | Req 7646 |  | -177.6
GL | 230 | 03/25/21 | 507 | Req 7645 |  | -572.07
AP | 230 | 03/30/21 | 681 | Rosen Supply Kirkland |  | 337.96 | 4292657-00
AP | 230 | 04/14/21 | 236 | Rosen Supply Kirkland |  | 40 | 1582895-00
AP | 240 | 10/23/19 | 576 | Ferguson Enterprises, Inc. #3007 |  | 997.19 | 7602901
AP | 240 | 10/29/19 | 735 | Consolidated Supply Co. |  | 386.06 | S009462599.001
GL | 240 | 11/04/19 | 127 | Req 6465 |  | 64.65
GL | 240 | 11/04/19 | 135 | Req 6471 |  | 60.96
AP | 240 | 11/12/19 | 368 | Rosen Supply Kirkland |  | 21.91 | 4273689-00
AP | 240 | 11/16/19 | 549 | Rosen Supply Kirkland |  | 16.29 | 4274050-00
AP | 240 | 11/20/19 | 598 | Rosen Supply Kirkland |  | 16.29 | 4274043-00
AP | 240 | 01/29/20 | 825 | Ferguson Enterprises, Inc. #3007 |  | 871.2 | 7916390
GL | 240 | 02/24/20 | 575 | Req 6801 |  | 2.31
AP | 240 | 02/26/20 | 644 | Ferguson Enterprises, Inc. #3007 |  | 928.51 | 7986884
AP | 240 | 02/29/20 | 815 | Rosen Supply Kirkland |  | 21.74 | 4279107-00
AP | 240 | 03/11/20 | 297 | Ferguson Enterprises, Inc. #3007 |  | 58.57 | 8051908
GL | 240 | 03/13/20 | 406 | Req 6864 |  | 7.79
AP | 240 | 03/16/20 | 451 | Rosen Supply Kirkland |  | 148.8 | 4279729-00
GL | 240 | 03/16/20 | 709 | Richard Anderson |  | 26.72
AP | 240 | 03/18/20 | 558 | Rosen Supply Kirkland |  | 381.34 | 4280236-00
GL | 240 | 03/20/20 | 679 | Req 6915 |  | 328.25
AP | 240 | 03/25/20 | 530 | Ferguson Enterprises, Inc. #3007 |  | 82.11 | 8059985
AP | 240 | 03/27/20 | 859 | Rosen Supply Kirkland |  | 1.16 | 4280236-01
AP | 240 | 05/19/20 | 433 | Rosen Supply Kirkland |  | 50.4 | 4281732-00
GL | 240 | 05/31/20 | 678 | Req 7073 |  | 24.63
GL | 240 | 07/07/20 | 79 | Req 7144 |  | 30.21
AP | 240 | 07/08/20 | 125 | Rosen Supply Kirkland |  | 317.69 | 1566138-00
AP | 240 | 07/13/20 | 235 | Rosen Supply Kirkland |  | 187.4 | 4283606-00
GL | 240 | 07/16/20 | 320 | Req 6471 adj |  | -60.96
AP | 240 | 07/24/20 | 487 | Rosen Supply Kirkland |  | 82.88 | 1567095-00
AP | 240 | 07/24/20 | 488 | Rosen Supply Kirkland |  | 16.74 | 4284023-00
GL | 240 | 08/04/20 | 18 | Req 7194 |  | 895.7
GL | 240 | 08/17/20 | 390 | Req 7236 |  | 121.92
GL | 240 | 09/14/20 | 189 | Req 7285 |  | -185.85
AP | 240 | 10/07/20 | 125 | Rosen Supply Kirkland |  | 23.57 | 4286860-00
AP | 240 | 10/13/20 | 283 | Capital One Credit Card |  | 16.79 | 092420JB
GL | 240 | 10/20/20 | 420 | Req 7376 |  | 550.38
AP | 240 | 11/06/20 | 102 | Rosen Supply Kirkland |  | 13.89 | 4286860-01
AP | 240 | 01/20/21 | 249 | Rosen Supply Kirkland |  | 6.14 | 4290548-00
GL | 240 | 01/27/21 | 378 | Req 7557 |  | 150.63
AP | 240 | 02/05/21 | 147 | Rosen Supply Kirkland |  | 15.93 | 4291040-00
GL | 240 | 02/18/21 | 480 | Req 7594 |  | 79.05
GL | 240 | 04/07/21 | 96 | Req 7661 |  | -67.05
GL | 241 | 07/10/19 | 197 | Req 6117 |  | 57.8
AP | 241 | 07/17/19 | 479 | Consolidated Supply Co. |  | 7838.77 | S9268015.002
AP | 241 | 08/05/19 | 115 | Consolidated Supply Co. |  | 1296.62 | S9268015.003
AP | 241 | 08/06/19 | 172 | Ferguson Enterprises, Inc. #3007 |  | 1996.5 | 7396170
GL | 241 | 08/08/19 | 224 | Req 6173 |  | 1356.93
AP | 241 | 08/12/19 | 457 | Consolidated Supply Co. |  | 1781.29 | S00935977.001
AP | 241 | 08/12/19 | 482 | Consolidated Supply Co. |  | 399.17 | S009356645.001
AP | 241 | 08/12/19 | 483 | Consolidated Supply Co. |  | 174.74 | S009359777.002
AP | 241 | 08/13/19 | 520 | Consolidated Supply Co. |  | 138.36 | S009356645.002
GL | 241 | 08/20/19 | 685 | Req 6251 |  | 2036.1
GL | 241 | 08/20/19 | 698 | Req 6263 |  | -1016.4
AP | 241 | 09/04/19 | 5 | Consolidated Supply Co. |  | 5818.43 | S9271745.001
AP | 241 | 09/04/19 | 164 | Consolidated Supply Co. |  | -5818.43 | S9271745.001A
AP | 241 | 09/04/19 | 165 | Consolidated Supply Co. |  | 5815.43 | S9271745.001B
GL | 241 | 09/06/19 | 103 | Req 6325 |  | -994.52
AP | 241 | 09/09/19 | 121 | Consolidated Supply Co. |  | 220.58 | S009399760.001
GL | 241 | 09/16/19 | 342 | Req 6359 |  | -304.92
GL | 241 | 09/16/19 | 360 | Req 6324 |  | 310.19
AP | 241 | 09/18/19 | 468 | Consolidated Supply Co. |  | 673.2 | S009422749.001
AP | 241 | 10/08/19 | 175 | Consolidated Supply Co. |  | 192.29 | S009440682.001
AP | 241 | 10/08/19 | 176 | Consolidated Supply Co. |  | 45.92 | S009440682.002
AP | 241 | 10/23/19 | 583 | Consolidated Supply Co. |  | 1179.2 | S009460198.001
AP | 241 | 10/29/19 | 734 | Consolidated Supply Co. |  | 628 | S009461774.001
GL | 241 | 11/04/19 | 130 | Req 6466 |  | 4079.07
GL | 241 | 11/04/19 | 131 | Req 6467 |  | 670.28
GL | 241 | 11/04/19 | 133 | Req 6470 |  | 150.16
AP | 241 | 11/11/19 | 326 | Consolidated Supply Co. |  | 5645.53 | S009483097.002
AP | 241 | 11/11/19 | 336 | Ferguson Enterprises, Inc. #3007 |  | 223.74 | 7646612
AP | 241 | 11/11/19 | 337 | Ferguson Enterprises, Inc. #3007 |  | 2089.41 | 7646359
AP | 241 | 11/11/19 | 338 | Ferguson Enterprises, Inc. #3007 |  | 204.37 | 7646359-1
AP | 241 | 11/12/19 | 374 | Consolidated Supply Co. |  | 3168.13 | S009481625.001
GL | 241 | 11/13/19 | 413 | Req 6543 |  | 2421.19
AP | 241 | 12/05/19 | 24 | Consolidated Supply Co. |  | 673.2 | S009502131.001
AP | 241 | 12/05/19 | 25 | Consolidated Supply Co. |  | 174.74 | S009502131.002
AP | 241 | 12/05/19 | 26 | Consolidated Supply Co. |  | 81.8 | S009502131.003
GL | 241 | 12/06/19 | 133 | Req 6615 |  | 762.13
GL | 241 | 12/09/19 | 176 | Req 6638 |  | 17.4
GL | 241 | 12/20/19 | 637 | Req 6701 |  | -14.67
GL | 241 | 12/27/19 | 792 | Req 6700 |  | 323.53
AP | 241 | 01/06/20 | 143 | Consolidated Supply Co. |  | 446.51 | S009570080.001
AP | 241 | 01/14/20 | 490 | Consolidated Supply Co. |  | 6209.29 | S009593999.001
GL | 241 | 01/31/20 | 925 | Req 5776 |  | 221.91
GL | 241 | 01/31/20 | 947 | Req 5775 |  | 2029.29
AP | 241 | 02/10/20 | 142 | Consolidated Supply Co. |  | 2051.78 | S009632645.001
GL | 241 | 02/24/20 | 574 | Req 6799 |  | 1103.82
GL | 241 | 03/13/20 | 407 | Req 6865 |  | 212.34
GL | 241 | 03/20/20 | 680 | Req 6913 |  | 1934.88
GL | 241 | 03/20/20 | 681 | Req 6894 |  | -129.15
AP | 241 | 03/25/20 | 521 | Consolidated Supply Co. |  | 306.81 | S009689221.001
AP | 241 | 03/25/20 | 524 | Consolidated Supply Co. |  | 4933.01 | S009298920.001
AP | 241 | 03/25/20 | 525 | Consolidated Supply Co. |  | 29.93 | S009298920.002
AP | 241 | 03/25/20 | 526 | Consolidated Supply Co. |  | 825.58 | S009687821.001
AP | 241 | 03/25/20 | 531 | Ferguson Enterprises, Inc. #3007 |  | 488.93 | 8065169
AP | 241 | 03/25/20 | 532 | Ferguson Enterprises, Inc. #3007 |  | 265.5 | 8075217
AP | 241 | 03/27/20 | 882 | Ferguson Enterprises, Inc. #3007 |  | 70.87 | 8083403
GL | 241 | 05/26/20 | 573 | Req 7026 |  | -1917.07
GL | 241 | 05/27/20 | 575 | Req 7042 |  | 271.49
GL | 241 | 05/31/20 | 679 | Req 7072 |  | 129.2
GL | 241 | 06/16/20 | 335 | Req 7102 |  | 135.21
GL | 241 | 07/07/20 | 80 | Req 7147 |  | 417.59
GL | 241 | 07/16/20 | 321 | Req 6470 adj |  | -150.16
AP | 241 | 07/17/20 | 358 | Consolidated Supply Co. |  | 693.1 | S009850187.001
AP | 241 | 07/17/20 | 359 | Consolidated Supply Co. |  | 318.03 | S009853513.001
AP | 241 | 07/17/20 | 360 | Consolidated Supply Co. |  | 405.94 | S009855760.001
GL | 241 | 07/24/20 | 470 | Req 7193 |  | 1509.06
AP | 241 | 07/24/20 | 474 | Consolidated Supply Co. |  | 76.01 | S009855760.002
AP | 241 | 08/10/20 | 258 | Consolidated Supply Co. |  | 524.8 | S009884740.001
GL | 241 | 08/17/20 | 389 | Req 7235 |  | 615.47
GL | 241 | 09/14/20 | 187 | Req 7287 |  | -1286.7
GL | 241 | 09/14/20 | 192 | Req 7282 |  | -27.69
GL | 241 | 09/22/20 | 376 | Req 7298 |  | -2151.4
GL | 241 | 09/22/20 | 377 | Req 7299 |  | -4682.27
GL | 241 | 09/23/20 | 405 | Req 7302 |  | -190.98
GL | 241 | 09/23/20 | 406 | Req 7301 |  | -240.52
GL | 241 | 09/23/20 | 407 | Req 7300 |  | -1341.1
GL | 241 | 10/20/20 | 421 | Req 7378 |  | 98.89
GL | 241 | 03/26/21 | 593 | Req 7648 |  | -784.9
AP | 242 | 10/23/19 | 577 | Ferguson Enterprises, Inc. #3007 |  | 340.9 | 7604656
GL | 242 | 11/04/19 | 134 | Req 6472 |  | 139.15
AP | 242 | 11/11/19 | 339 | Ferguson Enterprises, Inc. #3007 |  | 316.48 | 7671212
AP | 242 | 11/11/19 | 340 | Ferguson Enterprises, Inc. #3007 |  | 173.52 | 7473936
GL | 242 | 12/09/19 | 175 | Req 6637 |  | 36.19
AP | 242 | 12/11/19 | 385 | Ferguson Enterprises, Inc. #3007 |  | 347.04 | 7752872
AP | 242 | 12/11/19 | 386 | Ferguson Enterprises, Inc. #3007 |  | 194.27 | 7752872-1
AP | 242 | 12/31/19 | 863 | Rosen Supply Kirkland |  | 5.37 | 4276091-00
AP | 242 | 01/13/20 | 506 | Ferguson Enterprises, Inc. #3007 |  | 3439.44 | 7868206
AP | 242 | 01/13/20 | 539 | Ferguson Enterprises, Inc. #3007 |  | 985.05 | 7868206-1
AP | 242 | 01/17/20 | 629 | Ferguson Enterprises, Inc. #3007 |  | 500.36 | 7882023
AP | 242 | 01/17/20 | 633 | Ferguson Enterprises, Inc. #3007 |  | 174.84 | 7868206-2
AP | 242 | 01/29/20 | 823 | Ferguson Enterprises, Inc. #3007 |  | 524.25 | 7881989
AP | 242 | 01/29/20 | 824 | Ferguson Enterprises, Inc. #3007 |  | 226.54 | 7868206-3
GL | 242 | 01/31/20 | 946 | Req 5774 |  | 292.54
AP | 242 | 02/07/20 | 119 | Ferguson Enterprises, Inc. #3007 |  | 476.03 | 7927755
AP | 242 | 02/10/20 | 152 | Ferguson Enterprises, Inc. #3007 |  | -62.9 | CM857289
AP | 242 | 02/10/20 | 159 | Ferguson Enterprises, Inc. #3007 |  | -397.92 | CM856672-1
AP | 242 | 02/10/20 | 160 | Ferguson Enterprises, Inc. #3007 |  | -373.32 | CM856672-2
AP | 242 | 02/26/20 | 645 | Ferguson Enterprises, Inc. #3007 |  | 97.88 | 7993568
AP | 242 | 02/29/20 | 815 | Rosen Supply Kirkland |  | 45.26 | 4279107-00
AP | 242 | 03/11/20 | 296 | Ferguson Enterprises, Inc. #3007 |  | 158.17 | 8030263
AP | 242 | 03/18/20 | 557 | Rosen Supply Kirkland |  | 24.24 | 4280213-00
GL | 242 | 05/05/20 | 97 | Req 6967 |  | 14.2
GL | 242 | 05/31/20 | 677 | Req 7074 |  | 120.23
AP | 242 | 05/31/20 | 730 | Ferguson Enterprises, Inc. #3007 |  | 109.77 | 8276409
AP | 242 | 06/23/20 | 468 | Ferguson Enterprises, Inc. #3007 |  | 74.87 | 8336086
GL | 242 | 07/07/20 | 81 | Req 7148 |  | 235.67
GL | 242 | 07/10/20 | 192 | Req 7171 |  | -288.77
AP | 600 | 09/09/20 | 69 | Patchworks, Inc. |  | 2636.25 | 9536
AP | 600 | 09/09/20 | 70 | Patchworks, Inc. |  | 2778.5 | 9537
AP | 600 | 03/16/21 | 267 | Patchworks, Inc. |  | 501.25 | 9808
AP | 601 | 10/16/18 | 659 | Franklin Engineering |  | 1388.75 | 7136
AP | 601 | 10/16/18 | 660 | Franklin Engineering |  | 498 | 7139
AP | 601 | 10/16/18 | 661 | Franklin Engineering |  | 498 | 7140
AP | 601 | 11/29/18 | 819 | Franklin Engineering |  | 3965.25 | 7154
AP | 601 | 11/29/18 | 820 | Franklin Engineering |  | 832.75 | 7155
AP | 601 | 11/29/18 | 821 | Franklin Engineering |  | 3823 | 7156
AP | 601 | 11/29/18 | 823 | Franklin Engineering |  | 519.5 | 7165
AP | 601 | 11/29/18 | 824 | Franklin Engineering |  | 1774.5 | 7166
AP | 601 | 11/29/18 | 825 | Franklin Engineering |  | 1049.25 | 7167
AP | 601 | 01/03/19 | 87 | Franklin Engineering |  | 4311 | 7185
AP | 601 | 01/03/19 | 88 | Franklin Engineering |  | 1367.5 | 7186
AP | 601 | 01/03/19 | 89 | Franklin Engineering |  | 1967 | 7187
AP | 601 | 01/03/19 | 92 | Franklin Engineering |  | 541 | 7201
AP | 601 | 01/03/19 | 94 | Franklin Engineering |  | 1466 | 7204
AP | 601 | 01/03/19 | 95 | Franklin Engineering |  | 3847 | 7205
AP | 601 | 01/30/19 | 886 | Franklin Engineering |  | 2016.5 | 7209
AP | 601 | 01/30/19 | 887 | Franklin Engineering |  | 872 | 7210
AP | 601 | 01/30/19 | 888 | Franklin Engineering |  | 1417 | 7211
AP | 601 | 01/30/19 | 889 | Franklin Engineering |  | 490.5 | 7212
AP | 601 | 01/30/19 | 890 | Franklin Engineering |  | 463.25 | 7213
AP | 601 | 01/30/19 | 891 | Franklin Engineering |  | 953.75 | 7214
AP | 601 | 02/27/19 | 742 | Franklin Engineering |  | 845.25 | 7275
AP | 601 | 02/27/19 | 743 | Franklin Engineering |  | 245.25 | 7276
AP | 601 | 03/13/19 | 483 | DRSi |  | 102.05 | 481972
AP | 601 | 03/20/19 | 693 | Franklin Engineering |  | 3071.75 | 7291
AP | 601 | 03/20/19 | 694 | Franklin Engineering |  | 1905 | 7292
AP | 601 | 03/20/19 | 695 | Franklin Engineering |  | 2782.5 | 7293
AP | 601 | 03/20/19 | 696 | Franklin Engineering |  | 3110 | 7294
AP | 601 | 03/20/19 | 700 | Franklin Engineering |  | 297.5 | 7298
AP | 601 | 03/20/19 | 701 | Franklin Engineering |  | 297.5 | 7299
AP | 601 | 04/02/19 | 16 | DRSi |  | 76.45 | 483737
AP | 601 | 04/10/19 | 311 | DRSi |  | 196.3 | 484133
AP | 601 | 04/10/19 | 312 | DRSi |  | 110.1 | 527234
AP | 601 | 04/26/19 | 823 | Franklin Engineering |  | 1706.5 | 7328
AP | 601 | 04/26/19 | 825 | Franklin Engineering |  | 2181 | 7335
AP | 601 | 04/26/19 | 826 | Franklin Engineering |  | 772.5 | 7336
AP | 601 | 04/26/19 | 827 | Franklin Engineering |  | 478.75 | 7337
AP | 601 | 04/26/19 | 830 | Franklin Engineering |  | 1110.5 | 7346
AP | 601 | 04/26/19 | 831 | Franklin Engineering |  | 262 | 7349
AP | 601 | 05/01/19 | 150 | DRSi |  | -110.1 | 527234A
AP | 601 | 05/01/19 | 151 | DRSi |  | 111.1 | 527234B
AP | 601 | 05/29/19 | 802 | Franklin Engineering |  | 654 | 7360
AP | 602 | 04/30/19 | 983 | Capital One Credit Card |  | 304 | 042419R2
AP | 602 | 09/10/19 | 207 | Capital One Credit Card |  | 160.63 | 081019R
AP | 602 | 10/01/19 | 249 | Capital One Credit Card |  | 160.63 | 090719R
AP | 602 | 10/11/19 | 345 | Capital One Credit Card |  | 160.63 | 100519R
AP | 602 | 11/21/19 | 791 | Capital One Credit Card |  | 160.63 | 110219R1
AP | 602 | 01/08/20 | 226 | Capital One Credit Card |  | 160.63 | 113019R
AP | 602 | 01/10/20 | 444 | Capital One Credit Card |  | 160.63 | 122819R
AP | 602 | 03/09/20 | 219 | Capital One Credit Card |  | 160.63 | 012520R
AP | 602 | 03/25/20 | 506 | Capital One Credit Card |  | 160.63 | 022220R
AP | 602 | 04/15/20 | 198 | Capital One Credit Card |  | 160.63 | 032120R
AP | 602 | 06/08/20 | 120 | Capital One Credit Card |  | 172.47 | 041820R2
AP | 602 | 06/12/20 | 303 | Capital One Credit Card |  | 172.47 | 051620R
AP | 602 | 08/10/20 | 197 | Capital One Credit Card |  | 172.47 | 061320R
AP | 603 | 03/31/19 | 1049 | Capital One Credit Card |  | 13563.15 | 032819J2
AP | 603 | 04/16/19 | 493 | Capital One Credit Card |  | 1627.32 | 041519J
AP | 603 | 05/07/19 | 121 | Capital One Credit Card |  | 21453.62 | 050619J1
AP | 603 | 05/07/19 | 122 | Capital One Credit Card |  | 13622.9 | 050619J2
AP | 603 | 05/29/19 | 781 | Capital One Credit Card |  | -13622.9 | 050619C
AP | 603 | 05/29/19 | 782 | Bank of America CC |  | 13622.9 | 050619
AP | 603 | 11/21/19 | 759 | Capital One Credit Card |  | 92.81 | 102419J
AP | 603 | 08/10/20 | 228 | Capital One Credit Card |  | 5.6 | 073120J
AP | 603 | 08/10/20 | 229 | Capital One Credit Card |  | 211.38 | 073120J2
AP | 607 | 10/01/19 | 212 | Capital One Credit Card |  | 109 | 092119B
AP | 607 | 11/21/19 | 755 | Capital One Credit Card |  | 8 | 101419J
AP | 607 | 10/13/20 | 242 | Capital One Credit Card |  | 109 | 091820B
PR | 995 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 22.18
PR | 995 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 03/15/19 | 562 | Donelson, Richard T |  | 55.44
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 115.31
PR | 995 | 03/22/19 | 776 | Donelson, Richard T |  | 27.72
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 03/29/19 | 989 | Donelson, Richard T |  | 27.72
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 115.31
PR | 995 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 23.06
PR | 995 | 04/05/19 | 83 | Barnhart, Joseph N |  | 95.8
PR | 995 | 04/05/19 | 83 | Barnhart, Joseph N |  | 319.32
PR | 995 | 04/05/19 | 125 | Paco Leyva, Orlando |  | 61.54
PR | 995 | 04/05/19 | 125 | Paco Leyva, Orlando |  | 410.24
PR | 995 | 04/05/19 | 127 | Ramos Herrera, Franklin J |  | 53.55
PR | 995 | 04/05/19 | 127 | Ramos Herrera, Franklin J |  | 244.81
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 69.19
PR | 995 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 149.9
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 66.53
PR | 995 | 04/12/19 | 327 | Barnhart, Joseph N |  | 376.98
PR | 995 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 37.25
PR | 995 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 62.09
PR | 995 | 04/12/19 | 369 | Paco Leyva, Orlando |  | 79.83
PR | 995 | 04/12/19 | 369 | Paco Leyva, Orlando |  | 709.6
PR | 995 | 04/12/19 | 371 | Ramos Herrera, Franklin J |  | 45.9
PR | 995 | 04/12/19 | 371 | Ramos Herrera, Franklin J |  | 408.02
PR | 995 | 04/12/19 | 397 | Donelson, Richard T |  | 27.72
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 115.31
PR | 995 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 92.25
PR | 995 | 04/19/19 | 524 | Barnhart, Joseph N |  | 66.53
PR | 995 | 04/19/19 | 524 | Barnhart, Joseph N |  | 709.6
PR | 995 | 04/19/19 | 563 | Martinez Reyes, Juan C |  | 198.69
PR | 995 | 04/19/19 | 567 | Paco Leyva, Orlando |  | 594.29
PR | 995 | 04/19/19 | 569 | Ramos Herrera, Franklin J |  | 22.95
PR | 995 | 04/19/19 | 569 | Ramos Herrera, Franklin J |  | 408.02
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 115.31
PR | 995 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 46.12
PR | 995 | 04/26/19 | 744 | Barnhart, Joseph N |  | 177.4
PR | 995 | 04/26/19 | 786 | Paco Leyva, Orlando |  | 549.94
PR | 995 | 04/26/19 | 788 | Ramos Herrera, Franklin J |  | 357.46
PR | 995 | 04/26/19 | 812 | Donelson, Richard T |  | 27.72
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 146.36
PR | 995 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 97.57
PR | 995 | 05/03/19 | 11 | Barnhart, Joseph N |  | 576.55
PR | 995 | 05/03/19 | 55 | Paco Leyva, Orlando |  | 709.6
PR | 995 | 05/03/19 | 57 | Ramos Herrera, Franklin J |  | 461.24
PR | 995 | 05/03/19 | 81 | Donelson, Richard T |  | 166.31
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 146.36
PR | 995 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 73.18
PR | 995 | 05/10/19 | 164 | Barnhart, Joseph N |  | 66.53
PR | 995 | 05/10/19 | 164 | Barnhart, Joseph N |  | 66.53
PR | 995 | 05/10/19 | 164 | Barnhart, Joseph N |  | 310.45
PR | 995 | 05/10/19 | 164 | Barnhart, Joseph N |  | 155.23
PR | 995 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 26.61
PR | 995 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 53.22
PR | 995 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 674.12
PR | 995 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 35.48
PR | 995 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 17.3
PR | 995 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 34.59
PR | 995 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 438.18
PR | 995 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 23.06
PR | 995 | 05/10/19 | 234 | Donelson, Richard T |  | 304.91
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 146.36
PR | 995 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 121.96
PR | 995 | 05/17/19 | 391 | Anderson, Richard P |  | 375.2
PR | 995 | 05/17/19 | 391 | Anderson, Richard P |  | 177.18
PR | 995 | 05/17/19 | 395 | Barnhart, Joseph N |  | 421.33
PR | 995 | 05/17/19 | 395 | Barnhart, Joseph N |  | 155.23
PR | 995 | 05/17/19 | 420 | Gonzalez Hernandez, Josue |  | 298.03
PR | 995 | 05/17/19 | 430 | Kinssies, Jr, John E |  | 99.34
PR | 995 | 05/17/19 | 442 | Ramos Herrera, Franklin J |  | 276.74
PR | 995 | 05/17/19 | 467 | Donelson, Richard T |  | 83.16
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 97.57
PR | 995 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 24.39
PR | 995 | 05/24/19 | 604 | Anderson, Richard P |  | 19.9
PR | 995 | 05/24/19 | 604 | Anderson, Richard P |  | 179.14
PR | 995 | 05/24/19 | 608 | Barnhart, Joseph N |  | 190.58
PR | 995 | 05/24/19 | 632 | Gonzalez Hernandez, Josue |  | 67.76
PR | 995 | 05/24/19 | 632 | Gonzalez Hernandez, Josue |  | 149.07
PR | 995 | 05/24/19 | 648 | Martinez Reyes, Juan C |  | 41.93
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 139.76
PR | 995 | 05/31/19 | 877 | Anderson, Richard P |  | 39.81
PR | 995 | 05/31/19 | 881 | Barnhart, Joseph N |  | 42.35
PR | 995 | 05/31/19 | 881 | Barnhart, Joseph N |  | 338.8
PR | 995 | 05/31/19 | 922 | Martinez Reyes, Juan C |  | 167.71
PR | 995 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 06/07/19 | 179 | Anderson, Richard P |  | 39.81
PR | 995 | 06/07/19 | 183 | Barnhart, Joseph N |  | 296.45
PR | 995 | 06/07/19 | 223 | Martinez Reyes, Juan C |  | 251.56
PR | 995 | 06/07/19 | 254 | Donelson, Richard T |  | 132.34
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 06/14/19 | 450 | Anderson, Richard P |  | 39.81
PR | 995 | 06/14/19 | 454 | Barnhart, Joseph N |  | 127.05
PR | 995 | 06/14/19 | 454 | Barnhart, Joseph N |  | 105.88
PR | 995 | 06/14/19 | 492 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 06/14/19 | 496 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 06/14/19 | 498 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 06/21/19 | 622 | Barnhart, Joseph N |  | 148.23
PR | 995 | 06/21/19 | 622 | Barnhart, Joseph N |  | 211.75
PR | 995 | 06/21/19 | 651 | Holmes, Anthony R |  | 406.56
PR | 995 | 06/21/19 | 663 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 06/21/19 | 663 | Martinez Reyes, Juan C |  | 265.53
PR | 995 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 355.74
PR | 995 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 50.82
PR | 995 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 231.23
PR | 995 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 33.03
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 52.94
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 139.76
PR | 995 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 34.94
PR | 995 | 06/28/19 | 840 | Barnhart, Joseph N |  | 296.45
PR | 995 | 06/28/19 | 840 | Barnhart, Joseph N |  | 42.35
PR | 995 | 06/28/19 | 869 | Holmes, Anthony R |  | 135.52
PR | 995 | 06/28/19 | 880 | Martinez Reyes, Juan C |  | 545.04
PR | 995 | 06/28/19 | 880 | Martinez Reyes, Juan C |  | 13.98
PR | 995 | 06/28/19 | 910 | Donelson, Richard T |  | 52.94
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 58.23
PR | 995 | 07/05/19 | 8 | Anderson, Richard P |  | 19.9
PR | 995 | 07/05/19 | 12 | Barnhart, Joseph N |  | 211.75
PR | 995 | 07/05/19 | 12 | Barnhart, Joseph N |  | 63.53
PR | 995 | 07/05/19 | 36 | Gerard, Mitchell J |  | 271.04
PR | 995 | 07/05/19 | 41 | Holmes, Anthony R |  | 677.6
PR | 995 | 07/05/19 | 43 | Hubbard, Justin A |  | 176.18
PR | 995 | 07/05/19 | 52 | Martinez Reyes, Juan C |  | 321.44
PR | 995 | 07/05/19 | 52 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 26.47
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 139.76
PR | 995 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 07/12/19 | 281 | Barbosa, Michael S |  | 98.25
PR | 995 | 07/12/19 | 282 | Barnhart, Joseph N |  | 42.35
PR | 995 | 07/12/19 | 310 | Holmes, Anthony R |  | 542.08
PR | 995 | 07/12/19 | 312 | Hubbard, Justin A |  | 60.56
PR | 995 | 07/12/19 | 317 | Lima Romero, Melvin A |  | 118.58
PR | 995 | 07/12/19 | 321 | Martinez Reyes, Juan C |  | 265.53
PR | 995 | 07/12/19 | 321 | Martinez Reyes, Juan C |  | 209.63
PR | 995 | 07/12/19 | 325 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 07/12/19 | 327 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 07/12/19 | 352 | Donelson, Richard T |  | 26.47
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 07/19/19 | 508 | Anderson, Richard P |  | 19.9
PR | 995 | 07/19/19 | 511 | Barbosa, Michael S |  | 196.5
PR | 995 | 07/19/19 | 512 | Barnhart, Joseph N |  | 211.75
PR | 995 | 07/19/19 | 512 | Barnhart, Joseph N |  | 42.35
PR | 995 | 07/19/19 | 536 | Gonzalez Hernandez, Josue |  | 108.42
PR | 995 | 07/19/19 | 540 | Holmes, Anthony R |  | 542.08
PR | 995 | 07/19/19 | 540 | Holmes, Anthony R |  | 135.52
PR | 995 | 07/19/19 | 542 | Hubbard, Justin A |  | 88.09
PR | 995 | 07/19/19 | 547 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 07/19/19 | 551 | Martinez Reyes, Juan C |  | 223.61
PR | 995 | 07/19/19 | 551 | Martinez Reyes, Juan C |  | 195.66
PR | 995 | 07/19/19 | 555 | Paco Leyva, Orlando |  | 440.44
PR | 995 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 16.52
PR | 995 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 264.26
PR | 995 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 07/26/19 | 612 | Anderson, Richard P |  | 79.62
PR | 995 | 07/26/19 | 612 | Anderson, Richard P |  | 258.76
PR | 995 | 07/26/19 | 615 | Barbosa, Michael S |  | 294.76
PR | 995 | 07/26/19 | 615 | Barbosa, Michael S |  | 196.5
PR | 995 | 07/26/19 | 616 | Barnhart, Joseph N |  | 148.23
PR | 995 | 07/26/19 | 616 | Barnhart, Joseph N |  | 105.88
PR | 995 | 07/26/19 | 616 | Barnhart, Joseph N |  | 42.35
PR | 995 | 07/26/19 | 617 | Belcher, Jacob T |  | 203.28
PR | 995 | 07/26/19 | 639 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 07/26/19 | 641 | Hernandez Gonzalez, Osbaldo |  | 264.26
PR | 995 | 07/26/19 | 642 | Hoeg, Xavier A |  | 172.79
PR | 995 | 07/26/19 | 643 | Holmes, Anthony R |  | 677.6
PR | 995 | 07/26/19 | 649 | Lee, Ha Nul |  | 213.44
PR | 995 | 07/26/19 | 650 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 07/26/19 | 654 | Martinez Reyes, Juan C |  | 447.22
PR | 995 | 07/26/19 | 654 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 07/26/19 | 656 | Mendoza Morales, Jesus A |  | 294.76
PR | 995 | 07/26/19 | 658 | Paco Leyva, Orlando |  | 474.32
PR | 995 | 07/26/19 | 658 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 07/26/19 | 660 | Ramos Herrera, Franklin J |  | 352.35
PR | 995 | 07/26/19 | 660 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 07/26/19 | 662 | Reyes Cruz, Denis A |  | 304.92
PR | 995 | 07/26/19 | 668 | Rosas Olivares, Jorge C |  | 190.58
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 128.11
PR | 995 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/02/19 | 4 | Anderson, Richard P |  | 39.81
PR | 995 | 08/02/19 | 4 | Anderson, Richard P |  | 119.43
PR | 995 | 08/02/19 | 7 | Barbosa, Michael S |  | 491.26
PR | 995 | 08/02/19 | 8 | Barnhart, Joseph N |  | 63.53
PR | 995 | 08/02/19 | 8 | Barnhart, Joseph N |  | 84.7
PR | 995 | 08/02/19 | 9 | Belcher, Jacob T |  | 338.8
PR | 995 | 08/02/19 | 31 | Gonzalez Hernandez, Josue |  | 325.25
PR | 995 | 08/02/19 | 33 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 08/02/19 | 34 | Hoeg, Xavier A |  | 287.98
PR | 995 | 08/02/19 | 35 | Holmes, Anthony R |  | 626.78
PR | 995 | 08/02/19 | 41 | Lee, Ha Nul |  | 284.59
PR | 995 | 08/02/19 | 42 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 335.41
PR | 995 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 55.9
PR | 995 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 55.9
PR | 995 | 08/02/19 | 48 | Mendoza Morales, Jesus A |  | 393.01
PR | 995 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 406.56
PR | 995 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 08/02/19 | 52 | Ramos Herrera, Franklin J |  | 231.23
PR | 995 | 08/02/19 | 52 | Ramos Herrera, Franklin J |  | 33.03
PR | 995 | 08/02/19 | 54 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 08/02/19 | 56 | Rivera, Jorge A |  | 474.32
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/09/19 | 256 | Anderson, Richard P |  | 278.66
PR | 995 | 08/09/19 | 256 | Anderson, Richard P |  | 99.52
PR | 995 | 08/09/19 | 259 | Barbosa, Michael S |  | 491.26
PR | 995 | 08/09/19 | 260 | Barnhart, Joseph N |  | 232.93
PR | 995 | 08/09/19 | 260 | Barnhart, Joseph N |  | 84.7
PR | 995 | 08/09/19 | 261 | Belcher, Jacob T |  | 338.8
PR | 995 | 08/09/19 | 283 | Gerard, Mitchell J |  | 135.52
PR | 995 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo |  | 264.26
PR | 995 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo |  | 88.09
PR | 995 | 08/09/19 | 287 | Hoeg, Xavier A |  | 230.38
PR | 995 | 08/09/19 | 288 | Holmes, Anthony R |  | 677.6
PR | 995 | 08/09/19 | 290 | Hubbard, Justin A |  | 176.18
PR | 995 | 08/09/19 | 294 | Lee, Ha Nul |  | 355.74
PR | 995 | 08/09/19 | 295 | Lima Romero, Melvin A |  | 474.32
PR | 995 | 08/09/19 | 299 | Martinez Reyes, Juan C |  | 335.41
PR | 995 | 08/09/19 | 299 | Martinez Reyes, Juan C |  | 223.61
PR | 995 | 08/09/19 | 301 | Mendoza Morales, Jesus A |  | 393.01
PR | 995 | 08/09/19 | 303 | Paco Leyva, Orlando |  | 304.92
PR | 995 | 08/09/19 | 303 | Paco Leyva, Orlando |  | 254.1
PR | 995 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 143.14
PR | 995 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 132.13
PR | 995 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/09/19 | 307 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 08/09/19 | 309 | Rivera, Jorge A |  | 474.32
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/16/19 | 563 | Anderson, Richard P |  | 59.71
PR | 995 | 08/16/19 | 563 | Anderson, Richard P |  | 238.85
PR | 995 | 08/16/19 | 566 | Barbosa, Michael S |  | 294.76
PR | 995 | 08/16/19 | 566 | Barbosa, Michael S |  | 98.25
PR | 995 | 08/16/19 | 566 | Barbosa, Michael S |  | 98.25
PR | 995 | 08/16/19 | 567 | Barnhart, Joseph N |  | 63.53
PR | 995 | 08/16/19 | 567 | Barnhart, Joseph N |  | 42.35
PR | 995 | 08/16/19 | 567 | Barnhart, Joseph N |  | 105.88
PR | 995 | 08/16/19 | 568 | Belcher, Jacob T |  | 338.8
PR | 995 | 08/16/19 | 590 | Gerard, Mitchell J |  | 67.76
PR | 995 | 08/16/19 | 590 | Gerard, Mitchell J |  | 67.76
PR | 995 | 08/16/19 | 591 | Gonzalez Hernandez, Josue |  | 542.08
PR | 995 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo |  | 264.26
PR | 995 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo |  | 176.18
PR | 995 | 08/16/19 | 594 | Hoeg, Xavier A |  | 287.98
PR | 995 | 08/16/19 | 595 | Holmes, Anthony R |  | 677.6
PR | 995 | 08/16/19 | 597 | Hubbard, Justin A |  | 407.41
PR | 995 | 08/16/19 | 601 | Lee, Ha Nul |  | 355.74
PR | 995 | 08/16/19 | 602 | Lima Romero, Melvin A |  | 355.74
PR | 995 | 08/16/19 | 602 | Lima Romero, Melvin A |  | 237.16
PR | 995 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 335.41
PR | 995 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/16/19 | 608 | Mendoza Morales, Jesus A |  | 491.26
PR | 995 | 08/16/19 | 610 | Paco Leyva, Orlando |  | 474.32
PR | 995 | 08/16/19 | 610 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 08/16/19 | 612 | Ramos Herrera, Franklin J |  | 297.3
PR | 995 | 08/16/19 | 612 | Ramos Herrera, Franklin J |  | 55.06
PR | 995 | 08/16/19 | 614 | Reyes Cruz, Denis A |  | 406.56
PR | 995 | 08/16/19 | 616 | Rivera, Jorge A |  | 592.9
PR | 995 | 08/16/19 | 621 | Sanders, Allen O |  | 41.5
PR | 995 | 08/16/19 | 636 | Donelson, Richard T |  | 26.47
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/23/19 | 799 | Anderson, Richard P |  | 79.62
PR | 995 | 08/23/19 | 799 | Anderson, Richard P |  | 417.99
PR | 995 | 08/23/19 | 799 | Anderson, Richard P |  | 19.9
PR | 995 | 08/23/19 | 799 | Anderson, Richard P |  | 19.9
PR | 995 | 08/23/19 | 802 | Barbosa, Michael S |  | 196.5
PR | 995 | 08/23/19 | 802 | Barbosa, Michael S |  | 98.25
PR | 995 | 08/23/19 | 804 | Belcher, Jacob T |  | 338.8
PR | 995 | 08/23/19 | 827 | Gonzalez Hernandez, Josue |  | 474.32
PR | 995 | 08/23/19 | 829 | Gutierrez Salas, Jose |  | 120.7
PR | 995 | 08/23/19 | 830 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 08/23/19 | 831 | Hoeg, Xavier A |  | 287.98
PR | 995 | 08/23/19 | 832 | Holmes, Anthony R |  | 677.6
PR | 995 | 08/23/19 | 834 | Hubbard, Justin A |  | 440.44
PR | 995 | 08/23/19 | 838 | Lee, Ha Nul |  | 355.74
PR | 995 | 08/23/19 | 839 | Lima Romero, Melvin A |  | 474.32
PR | 995 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/23/19 | 845 | Mendoza Morales, Jesus A |  | 491.26
PR | 995 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/23/19 | 851 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 08/23/19 | 853 | Rivera, Jorge A |  | 592.9
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 108.42
PR | 995 | 08/30/19 | 990 | Anderson, Richard P |  | 318.47
PR | 995 | 08/30/19 | 993 | Barbosa, Michael S |  | 491.26
PR | 995 | 08/30/19 | 994 | Barnhart, Joseph N |  | 381.15
PR | 995 | 08/30/19 | 995 | Belcher, Jacob T |  | 338.8
PR | 995 | 08/30/19 | 1017 | Gerard, Mitchell J |  | 271.04
PR | 995 | 08/30/19 | 1018 | Gonzalez Hernandez, Josue |  | 542.08
PR | 995 | 08/30/19 | 1020 | Gutierrez Salas, Jose |  | 257.49
PR | 995 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo |  | 264.26
PR | 995 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo |  | 176.18
PR | 995 | 08/30/19 | 1022 | Hoeg, Xavier A |  | 287.98
PR | 995 | 08/30/19 | 1023 | Holmes, Anthony R |  | 406.56
PR | 995 | 08/30/19 | 1025 | Hubbard, Justin A |  | 352.35
PR | 995 | 08/30/19 | 1029 | Lee, Ha Nul |  | 355.74
PR | 995 | 08/30/19 | 1030 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 223.61
PR | 995 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/30/19 | 1036 | Mendoza Morales, Jesus A |  | 478.98
PR | 995 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 84.7
PR | 995 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 186.34
PR | 995 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 264.26
PR | 995 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/30/19 | 1042 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 08/30/19 | 1044 | Rivera, Jorge A |  | 570.67
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 52.94
PR | 995 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 23.29
PR | 995 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A |  | 108.42
PR | 995 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A |  | 325.25
PR | 995 | 09/06/19 | 11 | Anderson, Richard P |  | 318.47
PR | 995 | 09/06/19 | 14 | Barbosa, Michael S |  | 393.01
PR | 995 | 09/06/19 | 15 | Barnhart, Joseph N |  | 232.93
PR | 995 | 09/06/19 | 16 | Belcher, Jacob T |  | 67.76
PR | 995 | 09/06/19 | 16 | Belcher, Jacob T |  | 203.28
PR | 995 | 09/06/19 | 39 | Gonzalez Hernandez, Josue |  | 433.66
PR | 995 | 09/06/19 | 41 | Gutierrez Salas, Jose |  | 128.74
PR | 995 | 09/06/19 | 42 | Hernandez Gonzalez, Osbaldo |  | 341.34
PR | 995 | 09/06/19 | 43 | Hoeg, Xavier A |  | 115.19
PR | 995 | 09/06/19 | 43 | Hoeg, Xavier A |  | 115.19
PR | 995 | 09/06/19 | 44 | Holmes, Anthony R |  | 542.08
PR | 995 | 09/06/19 | 50 | Lee, Ha Nul |  | 284.59
PR | 995 | 09/06/19 | 51 | Lima Romero, Melvin A |  | 355.74
PR | 995 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 09/06/19 | 57 | Mendoza Morales, Jesus A |  | 393.01
PR | 995 | 09/06/19 | 59 | Paco Leyva, Orlando |  | 372.68
PR | 995 | 09/06/19 | 59 | Paco Leyva, Orlando |  | 33.88
PR | 995 | 09/06/19 | 61 | Ramos Herrera, Franklin J |  | 352.35
PR | 995 | 09/06/19 | 63 | Reyes Cruz, Denis A |  | 406.56
PR | 995 | 09/06/19 | 65 | Rivera, Jorge A |  | 429.85
PR | 995 | 09/06/19 | 68 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 09/06/19 | 70 | Sanders, Allen O |  | 62.25
PR | 995 | 09/06/19 | 85 | Donelson, Richard T |  | 26.47
PR | 995 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 58.23
PR | 995 | 09/13/19 | 234 | Amaya Gonzalez, Edilberto A |  | 514.98
PR | 995 | 09/13/19 | 235 | Anderson, Richard P |  | 796.18
PR | 995 | 09/13/19 | 238 | Barbosa, Michael S |  | 393.01
PR | 995 | 09/13/19 | 239 | Barnhart, Joseph N |  | 42.35
PR | 995 | 09/13/19 | 239 | Barnhart, Joseph N |  | 21.18
PR | 995 | 09/13/19 | 240 | Belcher, Jacob T |  | 135.52
PR | 995 | 09/13/19 | 240 | Belcher, Jacob T |  | 203.28
PR | 995 | 09/13/19 | 263 | Gonzalez Hernandez, Josue |  | 433.66
PR | 995 | 09/13/19 | 265 | Gutierrez Salas, Jose |  | 321.86
PR | 995 | 09/13/19 | 266 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 09/13/19 | 267 | Hoeg, Xavier A |  | 287.98
PR | 995 | 09/13/19 | 268 | Holmes, Anthony R |  | 677.6
PR | 995 | 09/13/19 | 273 | Lee, Ha Nul |  | 355.74
PR | 995 | 09/13/19 | 274 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 09/13/19 | 278 | Martinez Reyes, Juan C |  | 321.44
PR | 995 | 09/13/19 | 280 | Mendoza Morales, Jesus A |  | 491.26
PR | 995 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 389.62
PR | 995 | 09/13/19 | 284 | Ramos Herrera, Franklin J |  | 242.24
PR | 995 | 09/13/19 | 286 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 09/13/19 | 288 | Rivera, Jorge A |  | 592.9
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A |  | 216.83
PR | 995 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A |  | 216.83
PR | 995 | 09/20/19 | 472 | Anderson, Richard P |  | 636.94
PR | 995 | 09/20/19 | 475 | Barbosa, Michael S |  | 393.01
PR | 995 | 09/20/19 | 476 | Barnhart, Joseph N |  | 21.18
PR | 995 | 09/20/19 | 476 | Barnhart, Joseph N |  | 254.1
PR | 995 | 09/20/19 | 477 | Belcher, Jacob T |  | 338.8
PR | 995 | 09/20/19 | 482 | Chevez, Herson G |  | 155.85
PR | 995 | 09/20/19 | 482 | Chevez, Herson G |  | 233.77
PR | 995 | 09/20/19 | 495 | Galdamez, Dagoberto A |  | 203.28
PR | 995 | 09/20/19 | 495 | Galdamez, Dagoberto A |  | 304.92
PR | 995 | 09/20/19 | 500 | Gonzalez Hernandez, Josue |  | 501.42
PR | 995 | 09/20/19 | 503 | Gutierrez Salas, Jose |  | 321.86
PR | 995 | 09/20/19 | 504 | Hernandez Gonzalez, Osbaldo |  | 429.43
PR | 995 | 09/20/19 | 505 | Hoeg, Xavier A |  | 194.39
PR | 995 | 09/20/19 | 505 | Hoeg, Xavier A |  | 93.59
PR | 995 | 09/20/19 | 506 | Holmes, Anthony R |  | 677.6
PR | 995 | 09/20/19 | 511 | Lee, Ha Nul |  | 355.74
PR | 995 | 09/20/19 | 512 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 09/20/19 | 514 | Lovo, German G |  | 211.54
PR | 995 | 09/20/19 | 514 | Lovo, German G |  | 182.95
PR | 995 | 09/20/19 | 516 | Martinez Reyes, Juan C |  | 559.02
PR | 995 | 09/20/19 | 518 | Mendoza Morales, Jesus A |  | 454.42
PR | 995 | 09/20/19 | 520 | Paco Leyva, Orlando |  | 474.32
PR | 995 | 09/20/19 | 520 | Paco Leyva, Orlando |  | 152.46
PR | 995 | 09/20/19 | 522 | Ramos Herrera, Franklin J |  | 352.35
PR | 995 | 09/20/19 | 522 | Ramos Herrera, Franklin J |  | 55.06
PR | 995 | 09/20/19 | 524 | Reyes Cruz, Denis A |  | 393.86
PR | 995 | 09/20/19 | 526 | Rivera, Jorge A |  | 592.9
PR | 995 | 09/20/19 | 529 | Romero Garza, Jesus I |  | 60.98
PR | 995 | 09/20/19 | 546 | Donelson, Richard T |  | 52.94
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/27/19 | 627 | Amaya Gonzalez, Edilberto A |  | 542.08
PR | 995 | 09/27/19 | 628 | Anderson, Richard P |  | 318.47
PR | 995 | 09/27/19 | 631 | Barbosa, Michael S |  | 491.26
PR | 995 | 09/27/19 | 632 | Barnhart, Joseph N |  | 63.53
PR | 995 | 09/27/19 | 633 | Belcher, Jacob T |  | 338.8
PR | 995 | 09/27/19 | 638 | Chevez, Herson G |  | 311.7
PR | 995 | 09/27/19 | 638 | Chevez, Herson G |  | 77.92
PR | 995 | 09/27/19 | 651 | Galdamez, Dagoberto A |  | 508.2
PR | 995 | 09/27/19 | 656 | Gonzalez Hernandez, Josue |  | 542.08
PR | 995 | 09/27/19 | 659 | Guillen, Adrian |  | 172.79
PR | 995 | 09/27/19 | 660 | Gutierrez Salas, Jose |  | 257.49
PR | 995 | 09/27/19 | 661 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 09/27/19 | 662 | Hoeg, Xavier A |  | 230.38
PR | 995 | 09/27/19 | 662 | Hoeg, Xavier A |  | 57.6
PR | 995 | 09/27/19 | 663 | Holmes, Anthony R |  | 609.84
PR | 995 | 09/27/19 | 663 | Holmes, Anthony R |  | 67.76
PR | 995 | 09/27/19 | 670 | Lee, Ha Nul |  | 355.74
PR | 995 | 09/27/19 | 671 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 09/27/19 | 673 | Lovo, German G |  | 457.38
PR | 995 | 09/27/19 | 675 | Martinez Reyes, Juan C |  | 559.02
PR | 995 | 09/27/19 | 677 | Mendoza Morales, Jesus A |  | 393.01
PR | 995 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 84.7
PR | 995 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 186.34
PR | 995 | 09/27/19 | 681 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 09/27/19 | 683 | Reyes Cruz, Denis A |  | 508.2
PR | 995 | 09/27/19 | 685 | Rivera, Jorge A |  | 592.9
PR | 995 | 09/27/19 | 690 | Sanders, Allen O |  | 41.5
PR | 995 | 09/27/19 | 705 | Donelson, Richard T |  | 26.47
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A |  | 379.46
PR | 995 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A |  | 162.62
PR | 995 | 10/04/19 | 4 | Anderson, Richard P |  | 736.47
PR | 995 | 10/04/19 | 7 | Barbosa, Michael S |  | 485.12
PR | 995 | 10/04/19 | 8 | Barnhart, Joseph N |  | 63.53
PR | 995 | 10/04/19 | 9 | Belcher, Jacob T |  | 338.8
PR | 995 | 10/04/19 | 14 | Chevez, Herson G |  | 389.62
PR | 995 | 10/04/19 | 27 | Galdamez, Dagoberto A |  | 508.2
PR | 995 | 10/04/19 | 32 | Gonzalez Hernandez, Josue |  | 542.08
PR | 995 | 10/04/19 | 34 | Guillen, Adrian |  | 21.6
PR | 995 | 10/04/19 | 35 | Gutierrez Salas, Jose |  | 317.84
PR | 995 | 10/04/19 | 36 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 10/04/19 | 37 | Hoeg, Xavier A |  | 230.38
PR | 995 | 10/04/19 | 37 | Hoeg, Xavier A |  | 57.6
PR | 995 | 10/04/19 | 38 | Holmes, Anthony R |  | 677.6
PR | 995 | 10/04/19 | 45 | Lee, Ha Nul |  | 284.59
PR | 995 | 10/04/19 | 46 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 10/04/19 | 48 | Lovo, German G |  | 457.38
PR | 995 | 10/04/19 | 51 | Martinez Reyes, Juan C |  | 559.02
PR | 995 | 10/04/19 | 53 | Mendoza Morales, Jesus A |  | 491.26
PR | 995 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 152.46
PR | 995 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 67.76
PR | 995 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 55.06
PR | 995 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 10/04/19 | 59 | Reyes Cruz, Denis A |  | 304.92
PR | 995 | 10/04/19 | 61 | Rivera, Jorge A |  | 585.49
PR | 995 | 10/04/19 | 75 | Velasquez Cruz, Denis M |  | 108.42
PR | 995 | 10/04/19 | 76 | Velasquez Cruz, Osman N |  | 84.7
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 10/04/19 | 94 | Guillen, Adrian |  | 57.6
PR | 995 | 10/04/19 | 95 | Guillen, Adrian |  | -57.6
PR | 995 | 10/11/19 | 96 | Guillen, Adrian |  | 57.6
PR | 995 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A |  | 216.83
PR | 995 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A |  | 216.83
PR | 995 | 10/11/19 | 259 | Anderson, Richard P |  | 636.94
PR | 995 | 10/11/19 | 262 | Barbosa, Michael S |  | 491.26
PR | 995 | 10/11/19 | 263 | Barnhart, Joseph N |  | 31.76
PR | 995 | 10/11/19 | 263 | Barnhart, Joseph N |  | 21.18
PR | 995 | 10/11/19 | 264 | Belcher, Jacob T |  | 271.04
PR | 995 | 10/11/19 | 269 | Chevez, Herson G |  | 389.62
PR | 995 | 10/11/19 | 282 | Galdamez, Dagoberto A |  | 508.2
PR | 995 | 10/11/19 | 287 | Gonzalez Hernandez, Josue |  | 433.66
PR | 995 | 10/11/19 | 289 | Guillen, Adrian |  | 107.99
PR | 995 | 10/11/19 | 290 | Gutierrez Salas, Jose |  | 305.77
PR | 995 | 10/11/19 | 291 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 10/11/19 | 292 | Hoeg, Xavier A |  | 172.79
PR | 995 | 10/11/19 | 292 | Hoeg, Xavier A |  | 115.19
PR | 995 | 10/11/19 | 293 | Holmes, Anthony R |  | 677.6
PR | 995 | 10/11/19 | 300 | Lee, Ha Nul |  | 355.74
PR | 995 | 10/11/19 | 301 | Lima Romero, Melvin A |  | 592.9
PR | 995 | 10/11/19 | 303 | Lovo, German G |  | 457.38
PR | 995 | 10/11/19 | 306 | Martinez Reyes, Juan C |  | 531.07
PR | 995 | 10/11/19 | 308 | Mendoza Morales, Jesus A |  | 491.26
PR | 995 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 203.28
PR | 995 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 440.44
PR | 995 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 132.13
PR | 995 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 198.2
PR | 995 | 10/11/19 | 313 | Reyes Cruz, Denis A |  | 304.92
PR | 995 | 10/11/19 | 313 | Reyes Cruz, Denis A |  | 203.28
PR | 995 | 10/11/19 | 315 | Rivera, Jorge A |  | 592.9
PR | 995 | 10/11/19 | 319 | Rosas Olivares, Jorge C |  | 254.1
PR | 995 | 10/11/19 | 319 | Rosas Olivares, Jorge C |  | 84.7
PR | 995 | 10/11/19 | 321 | Sanders, Allen O |  | 20.75
PR | 995 | 10/11/19 | 329 | Velasquez Cruz, Denis M |  | 352.35
PR | 995 | 10/11/19 | 329 | Velasquez Cruz, Denis M |  | 189.73
PR | 995 | 10/11/19 | 330 | Velasquez Cruz, Osman N |  | 275.28
PR | 995 | 10/11/19 | 330 | Velasquez Cruz, Osman N |  | 148.23
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A |  | 243.94
PR | 995 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A |  | 298.14
PR | 995 | 10/18/19 | 453 | Anderson, Richard P |  | 796.18
PR | 995 | 10/18/19 | 456 | Barbosa, Michael S |  | 393.01
PR | 995 | 10/18/19 | 456 | Barbosa, Michael S |  | 98.25
PR | 995 | 10/18/19 | 457 | Barnhart, Joseph N |  | 190.58
PR | 995 | 10/18/19 | 457 | Barnhart, Joseph N |  | 42.35
PR | 995 | 10/18/19 | 458 | Belcher, Jacob T |  | 338.8
PR | 995 | 10/18/19 | 459 | Benites Portillo, Marvin E |  | 365.9
PR | 995 | 10/18/19 | 463 | Chevez, Herson G |  | 389.62
PR | 995 | 10/18/19 | 475 | Galdamez, Dagoberto A |  | 508.2
PR | 995 | 10/18/19 | 480 | Gonzalez Hernandez, Josue |  | 542.08
PR | 995 | 10/18/19 | 482 | Guillen, Adrian |  | 273.58
PR | 995 | 10/18/19 | 483 | Gutierrez Salas, Jose |  | 241.4
PR | 995 | 10/18/19 | 484 | Hernandez Gonzalez, Osbaldo |  | 440.44
PR | 995 | 10/18/19 | 485 | Hoeg, Xavier A |  | 172.79
PR | 995 | 10/18/19 | 485 | Hoeg, Xavier A |  | 57.6
PR | 995 | 10/18/19 | 486 | Holmes, Anthony R |  | 677.6
PR | 995 | 10/18/19 | 493 | Lee, Ha Nul |  | 355.74
PR | 995 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 355.74
PR | 995 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 118.58
PR | 995 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 118.58
PR | 995 | 10/18/19 | 496 | Lovo, German G |  | 365.9
PR | 995 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 335.41
PR | 995 | 10/18/19 | 501 | Mendoza Morales, Jesus A |  | 454.42
PR | 995 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 118.58
PR | 995 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 101.64
PR | 995 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 321.86
PR | 995 | 10/18/19 | 504 | Ramos Herrera, Franklin J |  | 264.26
PR | 995 | 10/18/19 | 504 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 10/18/19 | 506 | Reyes Cruz, Denis A |  | 355.74
PR | 995 | 10/18/19 | 506 | Reyes Cruz, Denis A |  | 152.46
PR | 995 | 10/18/19 | 508 | Rivera, Jorge A |  | 429.85
PR | 995 | 10/18/19 | 512 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 10/18/19 | 517 | Stahlschmidt, John P |  | 64.37
PR | 995 | 10/18/19 | 522 | Velasquez Cruz, Denis M |  | 542.08
PR | 995 | 10/18/19 | 523 | Velasquez Cruz, Osman N |  | 423.5
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 10/25/19 | 587 | Amaya Gonzalez, Edilberto A |  | 487.87
PR | 995 | 10/25/19 | 588 | Anderson, Richard P |  | 577.23
PR | 995 | 10/25/19 | 591 | Barbosa, Michael S |  | 435.99
PR | 995 | 10/25/19 | 592 | Barnhart, Joseph N |  | 169.4
PR | 995 | 10/25/19 | 593 | Belcher, Jacob T |  | 304.92
PR | 995 | 10/25/19 | 594 | Benites Portillo, Marvin E |  | 182.95
PR | 995 | 10/25/19 | 599 | Chevez, Herson G |  | 350.66
PR | 995 | 10/25/19 | 610 | Galdamez, Dagoberto A |  | 355.74
PR | 995 | 10/25/19 | 615 | Gonzalez Hernandez, Josue |  | 420.11
PR | 995 | 10/25/19 | 617 | Guillen, Adrian |  | 86.39
PR | 995 | 10/25/19 | 618 | Gutierrez Salas, Jose |  | 128.74
PR | 995 | 10/25/19 | 618 | Gutierrez Salas, Jose |  | 160.93
PR | 995 | 10/25/19 | 619 | Hernandez Gonzalez, Osbaldo |  | 396.4
PR | 995 | 10/25/19 | 620 | Hoeg, Xavier A |  | 201.59
PR | 995 | 10/25/19 | 620 | Hoeg, Xavier A |  | 57.6
PR | 995 | 10/25/19 | 621 | Holmes, Anthony R |  | 474.32
PR | 995 | 10/25/19 | 621 | Holmes, Anthony R |  | 135.52
PR | 995 | 10/25/19 | 628 | Lee, Ha Nul |  | 320.17
PR | 995 | 10/25/19 | 629 | Lima Romero, Melvin A |  | 533.61
PR | 995 | 10/25/19 | 631 | Lovo, German G |  | 182.95
PR | 995 | 10/25/19 | 631 | Lovo, German G |  | 228.69
PR | 995 | 10/25/19 | 634 | Martinez Reyes, Juan C |  | 405.29
PR | 995 | 10/25/19 | 636 | Mendoza Morales, Jesus A |  | 343.88
PR | 995 | 10/25/19 | 638 | Paco Leyva, Orlando |  | 491.26
PR | 995 | 10/25/19 | 638 | Paco Leyva, Orlando |  | 118.58
PR | 995 | 10/25/19 | 640 | Ramos Herrera, Franklin J |  | 396.4
PR | 995 | 10/25/19 | 642 | Reyes Cruz, Denis A |  | 304.92
PR | 995 | 10/25/19 | 642 | Reyes Cruz, Denis A |  | 152.46
PR | 995 | 10/25/19 | 644 | Rivera, Jorge A |  | 533.61
PR | 995 | 10/25/19 | 648 | Rosas Olivares, Jorge C |  | 228.69
PR | 995 | 10/25/19 | 653 | Stahlschmidt, John P |  | 257.49
PR | 995 | 10/25/19 | 658 | Velasquez Cruz, Denis M |  | 487.87
PR | 995 | 10/25/19 | 659 | Velasquez Cruz, Osman N |  | 381.15
PR | 995 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 139.76
PR | 995 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A |  | 564.1
PR | 995 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A |  | 45.74
PR | 995 | 11/01/19 | 4 | Anderson, Richard P |  | 456.53
PR | 995 | 11/01/19 | 4 | Anderson, Richard P |  | 207.52
PR | 995 | 11/01/19 | 7 | Barbosa, Michael S |  | 321.44
PR | 995 | 11/01/19 | 7 | Barbosa, Michael S |  | 223.61
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 22.87
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 45.74
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 114.35
PR | 995 | 11/01/19 | 9 | Belcher, Jacob T |  | 355.74
PR | 995 | 11/01/19 | 10 | Benites Portillo, Marvin E |  | 393.01
PR | 995 | 11/01/19 | 14 | Chevez, Herson G |  | 440.44
PR | 995 | 11/01/19 | 26 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 11/01/19 | 31 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 11/01/19 | 33 | Guillen, Adrian |  | 230.38
PR | 995 | 11/01/19 | 34 | Gutierrez Salas, Jose |  | 257.49
PR | 995 | 11/01/19 | 34 | Gutierrez Salas, Jose |  | 64.37
PR | 995 | 11/01/19 | 35 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 11/01/19 | 36 | Hoeg, Xavier A |  | 198.2
PR | 995 | 11/01/19 | 36 | Hoeg, Xavier A |  | 106.72
PR | 995 | 11/01/19 | 37 | Holmes, Anthony R |  | 409.95
PR | 995 | 11/01/19 | 37 | Holmes, Anthony R |  | 335.41
PR | 995 | 11/01/19 | 44 | Lee, Ha Nul |  | 169.4
PR | 995 | 11/01/19 | 44 | Lee, Ha Nul |  | 84.7
PR | 995 | 11/01/19 | 44 | Lee, Ha Nul |  | 169.4
PR | 995 | 11/01/19 | 45 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 11/01/19 | 47 | Lovo, German G |  | 508.2
PR | 995 | 11/01/19 | 50 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 11/01/19 | 52 | Mendoza Morales, Jesus A |  | 514.98
PR | 995 | 11/01/19 | 52 | Mendoza Morales, Jesus A |  | 27.1
PR | 995 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 93.17
PR | 995 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 316.78
PR | 995 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 74.54
PR | 995 | 11/01/19 | 56 | Ramos Herrera, Franklin J |  | 406.56
PR | 995 | 11/01/19 | 56 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 11/01/19 | 58 | Reyes Cruz, Denis A |  | 405.29
PR | 995 | 11/01/19 | 60 | Rivera, Jorge A |  | 643.72
PR | 995 | 11/01/19 | 64 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 11/01/19 | 66 | Sanders, Allen O |  | 102.91
PR | 995 | 11/01/19 | 69 | Stahlschmidt, John P |  | 372.68
PR | 995 | 11/01/19 | 74 | Velasquez Cruz, Denis M |  | 474.32
PR | 995 | 11/01/19 | 74 | Velasquez Cruz, Denis M |  | 118.58
PR | 995 | 11/01/19 | 75 | Velasquez Cruz, Osman N |  | 379.46
PR | 995 | 11/01/19 | 75 | Velasquez Cruz, Osman N |  | 94.86
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 182.95
PR | 995 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 213.44
PR | 995 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 396.4
PR | 995 | 11/08/19 | 178 | Anderson, Richard P |  | 207.52
PR | 995 | 11/08/19 | 178 | Anderson, Richard P |  | 518.79
PR | 995 | 11/08/19 | 178 | Anderson, Richard P |  | 20.75
PR | 995 | 11/08/19 | 181 | Barbosa, Michael S |  | 559.02
PR | 995 | 11/08/19 | 182 | Barnhart, Joseph N |  | 171.52
PR | 995 | 11/08/19 | 182 | Barnhart, Joseph N |  | 274.43
PR | 995 | 11/08/19 | 183 | Belcher, Jacob T |  | 266.81
PR | 995 | 11/08/19 | 183 | Belcher, Jacob T |  | 88.94
PR | 995 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 147.38
PR | 995 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 98.25
PR | 995 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 393.01
PR | 995 | 11/08/19 | 188 | Chevez, Herson G |  | 132.13
PR | 995 | 11/08/19 | 188 | Chevez, Herson G |  | 22.02
PR | 995 | 11/08/19 | 188 | Chevez, Herson G |  | 418.42
PR | 995 | 11/08/19 | 200 | Galdamez, Dagoberto A |  | 27.95
PR | 995 | 11/08/19 | 205 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 11/08/19 | 205 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 11/08/19 | 207 | Guillen, Adrian |  | 115.19
PR | 995 | 11/08/19 | 208 | Gutierrez Salas, Jose |  | 185.07
PR | 995 | 11/08/19 | 208 | Gutierrez Salas, Jose |  | 128.74
PR | 995 | 11/08/19 | 209 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 11/08/19 | 210 | Hoeg, Xavier A |  | 243.94
PR | 995 | 11/08/19 | 210 | Hoeg, Xavier A |  | 15.25
PR | 995 | 11/08/19 | 210 | Hoeg, Xavier A |  | 45.74
PR | 995 | 11/08/19 | 218 | Lee, Ha Nul |  | 127.05
PR | 995 | 11/08/19 | 218 | Lee, Ha Nul |  | 317.63
PR | 995 | 11/08/19 | 218 | Lee, Ha Nul |  | 105.88
PR | 995 | 11/08/19 | 219 | Lima Romero, Melvin A |  | 627.63
PR | 995 | 11/08/19 | 221 | Lovo, German G |  | 292.22
PR | 995 | 11/08/19 | 221 | Lovo, German G |  | 101.64
PR | 995 | 11/08/19 | 224 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 11/08/19 | 226 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 11/08/19 | 226 | Mendoza Morales, Jesus A |  | 216.83
PR | 995 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 251.56
PR | 995 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 335.41
PR | 995 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 93.17
PR | 995 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 18.63
PR | 995 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 171.52
PR | 995 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 228.69
PR | 995 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 76.23
PR | 995 | 11/08/19 | 232 | Reyes Cruz, Denis A |  | 447.22
PR | 995 | 11/08/19 | 234 | Rivera, Jorge A |  | 514.98
PR | 995 | 11/08/19 | 238 | Rosas Olivares, Jorge C |  | 338.8
PR | 995 | 11/08/19 | 243 | Stahlschmidt, John P |  | 270.19
PR | 995 | 11/08/19 | 243 | Stahlschmidt, John P |  | 74.54
PR | 995 | 11/08/19 | 248 | Velasquez Cruz, Denis M |  | 592.9
PR | 995 | 11/08/19 | 249 | Velasquez Cruz, Osman N |  | 474.32
PR | 995 | 11/08/19 | 253 | Donelson, Richard T |  | 26.47
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 11/15/19 | 437 | Amaya Gonzalez, Edilberto A |  | 609.84
PR | 995 | 11/15/19 | 438 | Anderson, Richard P |  | 622.55
PR | 995 | 11/15/19 | 438 | Anderson, Richard P |  | 20.75
PR | 995 | 11/15/19 | 441 | Barbosa, Michael S |  | 447.22
PR | 995 | 11/15/19 | 441 | Barbosa, Michael S |  | 111.8
PR | 995 | 11/15/19 | 442 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/15/19 | 443 | Belcher, Jacob T |  | 284.59
PR | 995 | 11/15/19 | 443 | Belcher, Jacob T |  | 71.15
PR | 995 | 11/15/19 | 444 | Benites Portillo, Marvin E |  | 442.13
PR | 995 | 11/15/19 | 444 | Benites Portillo, Marvin E |  | 49.13
PR | 995 | 11/15/19 | 448 | Chevez, Herson G |  | 434.93
PR | 995 | 11/15/19 | 460 | Galdamez, Dagoberto A |  | 503.12
PR | 995 | 11/15/19 | 460 | Galdamez, Dagoberto A |  | 55.9
PR | 995 | 11/15/19 | 465 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 11/15/19 | 467 | Gutierrez Salas, Jose |  | 193.12
PR | 995 | 11/15/19 | 467 | Gutierrez Salas, Jose |  | 56.33
PR | 995 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 11/15/19 | 469 | Hoeg, Xavier A |  | 289.67
PR | 995 | 11/15/19 | 469 | Hoeg, Xavier A |  | 15.25
PR | 995 | 11/15/19 | 470 | Holmes, Anthony R |  | 74.54
PR | 995 | 11/15/19 | 470 | Holmes, Anthony R |  | 670.82
PR | 995 | 11/15/19 | 477 | Lee, Ha Nul |  | 338.8
PR | 995 | 11/15/19 | 477 | Lee, Ha Nul |  | 84.7
PR | 995 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 128.74
PR | 995 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 11/15/19 | 480 | Lovo, German G |  | 101.64
PR | 995 | 11/15/19 | 480 | Lovo, German G |  | 101.64
PR | 995 | 11/15/19 | 483 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 11/15/19 | 485 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 447.22
PR | 995 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 37.27
PR | 995 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 55.9
PR | 995 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 55.9
PR | 995 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 381.15
PR | 995 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 25.41
PR | 995 | 11/15/19 | 491 | Reyes Cruz, Denis A |  | 447.22
PR | 995 | 11/15/19 | 491 | Reyes Cruz, Denis A |  | 111.8
PR | 995 | 11/15/19 | 493 | Rivera, Jorge A |  | 386.23
PR | 995 | 11/15/19 | 493 | Rivera, Jorge A |  | 257.49
PR | 995 | 11/15/19 | 497 | Rosas Olivares, Jorge C |  | 338.8
PR | 995 | 11/15/19 | 502 | Stahlschmidt, John P |  | 298.14
PR | 995 | 11/15/19 | 502 | Stahlschmidt, John P |  | 74.54
PR | 995 | 11/15/19 | 507 | Velasquez Cruz, Denis M |  | 592.9
PR | 995 | 11/15/19 | 508 | Velasquez Cruz, Osman N |  | 284.59
PR | 995 | 11/15/19 | 508 | Velasquez Cruz, Osman N |  | 189.73
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 11/22/19 | 608 | Amaya Gonzalez, Edilberto A |  | 579.35
PR | 995 | 11/22/19 | 609 | Anderson, Richard P |  | 498.04
PR | 995 | 11/22/19 | 609 | Anderson, Richard P |  | 124.51
PR | 995 | 11/22/19 | 612 | Barbosa, Michael S |  | 531.07
PR | 995 | 11/22/19 | 613 | Barnhart, Joseph N |  | 320.17
PR | 995 | 11/22/19 | 614 | Belcher, Jacob T |  | 337.95
PR | 995 | 11/22/19 | 615 | Benites Portillo, Marvin E |  | 368.45
PR | 995 | 11/22/19 | 615 | Benites Portillo, Marvin E |  | 98.25
PR | 995 | 11/22/19 | 619 | Chevez, Herson G |  | 330.33
PR | 995 | 11/22/19 | 619 | Chevez, Herson G |  | 88.09
PR | 995 | 11/22/19 | 631 | Galdamez, Dagoberto A |  | 531.07
PR | 995 | 11/22/19 | 636 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 11/22/19 | 638 | Gutierrez Salas, Jose |  | 305.77
PR | 995 | 11/22/19 | 639 | Hernandez Gonzalez, Osbaldo |  | 482.79
PR | 995 | 11/22/19 | 640 | Hoeg, Xavier A |  | 259.18
PR | 995 | 11/22/19 | 640 | Hoeg, Xavier A |  | 30.49
PR | 995 | 11/22/19 | 641 | Holmes, Anthony R |  | 708.09
PR | 995 | 11/22/19 | 648 | Lee, Ha Nul |  | 338.8
PR | 995 | 11/22/19 | 648 | Lee, Ha Nul |  | 63.53
PR | 995 | 11/22/19 | 649 | Lima Romero, Melvin A |  | 611.53
PR | 995 | 11/22/19 | 651 | Lovo, German G |  | 279.51
PR | 995 | 11/22/19 | 654 | Martinez Reyes, Juan C |  | 595.44
PR | 995 | 11/22/19 | 656 | Mendoza Morales, Jesus A |  | 298.14
PR | 995 | 11/22/19 | 656 | Mendoza Morales, Jesus A |  | 216.83
PR | 995 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 521.75
PR | 995 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 130.44
PR | 995 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 55.9
PR | 995 | 11/22/19 | 660 | Ramos Herrera, Franklin J |  | 482.79
PR | 995 | 11/22/19 | 662 | Reyes Cruz, Denis A |  | 531.07
PR | 995 | 11/22/19 | 664 | Rivera, Jorge A |  | 611.53
PR | 995 | 11/22/19 | 668 | Rosas Olivares, Jorge C |  | 321.86
PR | 995 | 11/22/19 | 673 | Stahlschmidt, John P |  | 354.05
PR | 995 | 11/22/19 | 678 | Velasquez Cruz, Denis M |  | 563.26
PR | 995 | 11/22/19 | 679 | Velasquez Cruz, Osman N |  | 450.6
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A |  | 426.89
PR | 995 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A |  | 182.95
PR | 995 | 11/27/19 | 843 | Anderson, Richard P |  | 228.27
PR | 995 | 11/27/19 | 846 | Barbosa, Michael S |  | 433.24
PR | 995 | 11/27/19 | 847 | Barnhart, Joseph N |  | 251.56
PR | 995 | 11/27/19 | 847 | Barnhart, Joseph N |  | 91.48
PR | 995 | 11/27/19 | 848 | Belcher, Jacob T |  | 160.08
PR | 995 | 11/27/19 | 848 | Belcher, Jacob T |  | 53.36
PR | 995 | 11/27/19 | 849 | Benites Portillo, Marvin E |  | 393.01
PR | 995 | 11/27/19 | 853 | Chevez, Herson G |  | 440.44
PR | 995 | 11/27/19 | 865 | Galdamez, Dagoberto A |  | 447.22
PR | 995 | 11/27/19 | 870 | Gonzalez Hernandez, Josue |  | 480.25
PR | 995 | 11/27/19 | 872 | Gutierrez Salas, Jose |  | 128.74
PR | 995 | 11/27/19 | 872 | Gutierrez Salas, Jose |  | 112.65
PR | 995 | 11/27/19 | 873 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 11/27/19 | 874 | Hoeg, Xavier A |  | 228.69
PR | 995 | 11/27/19 | 874 | Hoeg, Xavier A |  | 15.25
PR | 995 | 11/27/19 | 875 | Holmes, Anthony R |  | 447.22
PR | 995 | 11/27/19 | 882 | Lee, Ha Nul |  | 232.93
PR | 995 | 11/27/19 | 882 | Lee, Ha Nul |  | 105.88
PR | 995 | 11/27/19 | 883 | Lima Romero, Melvin A |  | 386.23
PR | 995 | 11/27/19 | 883 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 11/27/19 | 885 | Lovo, German G |  | 508.2
PR | 995 | 11/27/19 | 888 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 11/27/19 | 890 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 354.05
PR | 995 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 335.41
PR | 995 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 18.63
PR | 995 | 11/27/19 | 894 | Ramos Herrera, Franklin J |  | 266.81
PR | 995 | 11/27/19 | 894 | Ramos Herrera, Franklin J |  | 241.4
PR | 995 | 11/27/19 | 896 | Reyes Cruz, Denis A |  | 447.22
PR | 995 | 11/27/19 | 896 | Reyes Cruz, Denis A |  | 111.8
PR | 995 | 11/27/19 | 898 | Rivera, Jorge A |  | 643.72
PR | 995 | 11/27/19 | 902 | Rosas Olivares, Jorge C |  | 313.39
PR | 995 | 11/27/19 | 904 | Sanders, Allen O |  | 137.21
PR | 995 | 11/27/19 | 907 | Stahlschmidt, John P |  | 298.14
PR | 995 | 11/27/19 | 912 | Velasquez Cruz, Denis M |  | 563.26
PR | 995 | 11/27/19 | 913 | Velasquez Cruz, Osman N |  | 474.32
PR | 995 | 11/27/19 | 917 | Donelson, Richard T |  | 185.28
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 61.41
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A |  | 243.94
PR | 995 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A |  | 121.97
PR | 995 | 12/06/19 | 29 | Anderson, Richard P |  | 456.53
PR | 995 | 12/06/19 | 29 | Anderson, Richard P |  | 20.75
PR | 995 | 12/06/19 | 29 | Anderson, Richard P |  | 20.75
PR | 995 | 12/06/19 | 32 | Barbosa, Michael S |  | 335.41
PR | 995 | 12/06/19 | 32 | Barbosa, Michael S |  | 111.8
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 45.74
PR | 995 | 12/06/19 | 34 | Belcher, Jacob T |  | 213.44
PR | 995 | 12/06/19 | 34 | Belcher, Jacob T |  | 71.15
PR | 995 | 12/06/19 | 35 | Benites Portillo, Marvin E |  | 294.76
PR | 995 | 12/06/19 | 39 | Chevez, Herson G |  | 176.18
PR | 995 | 12/06/19 | 39 | Chevez, Herson G |  | 176.18
PR | 995 | 12/06/19 | 52 | Galdamez, Dagoberto A |  | 335.41
PR | 995 | 12/06/19 | 52 | Galdamez, Dagoberto A |  | 111.8
PR | 995 | 12/06/19 | 57 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 12/06/19 | 57 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 12/06/19 | 59 | Gutierrez Salas, Jose |  | 64.37
PR | 995 | 12/06/19 | 59 | Gutierrez Salas, Jose |  | 185.07
PR | 995 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 12/06/19 | 69 | Lee, Ha Nul |  | 169.4
PR | 995 | 12/06/19 | 69 | Lee, Ha Nul |  | 169.4
PR | 995 | 12/06/19 | 70 | Lima Romero, Melvin A |  | 418.42
PR | 995 | 12/06/19 | 70 | Lima Romero, Melvin A |  | 96.56
PR | 995 | 12/06/19 | 72 | Lovo, German G |  | 304.92
PR | 995 | 12/06/19 | 72 | Lovo, German G |  | 101.64
PR | 995 | 12/06/19 | 75 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 12/06/19 | 77 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 12/06/19 | 77 | Mendoza Morales, Jesus A |  | 216.83
PR | 995 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 279.51
PR | 995 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 167.71
PR | 995 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 149.07
PR | 995 | 12/06/19 | 81 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 12/06/19 | 81 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 111.8
PR | 995 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 223.61
PR | 995 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 111.8
PR | 995 | 12/06/19 | 85 | Rivera, Jorge A |  | 386.23
PR | 995 | 12/06/19 | 89 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 12/06/19 | 89 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 12/06/19 | 91 | Sanders, Allen O |  | 91.48
PR | 995 | 12/06/19 | 94 | Stahlschmidt, John P |  | 223.61
PR | 995 | 12/06/19 | 94 | Stahlschmidt, John P |  | 74.54
PR | 995 | 12/06/19 | 99 | Velasquez Cruz, Denis M |  | 400.21
PR | 995 | 12/06/19 | 100 | Velasquez Cruz, Osman N |  | 379.46
PR | 995 | 12/06/19 | 104 | Donelson, Richard T |  | 26.47
PR | 995 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/13/19 | 389 | Amaya Gonzalez, Edilberto A |  | 487.87
PR | 995 | 12/13/19 | 390 | Anderson, Richard P |  | 809.31
PR | 995 | 12/13/19 | 390 | Anderson, Richard P |  | 20.75
PR | 995 | 12/13/19 | 393 | Barbosa, Michael S |  | 195.66
PR | 995 | 12/13/19 | 393 | Barbosa, Michael S |  | 363.36
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 160.08
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/13/19 | 395 | Belcher, Jacob T |  | 160.08
PR | 995 | 12/13/19 | 395 | Belcher, Jacob T |  | 195.66
PR | 995 | 12/13/19 | 396 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 12/13/19 | 400 | Chevez, Herson G |  | 440.44
PR | 995 | 12/13/19 | 413 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 12/13/19 | 418 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 12/13/19 | 418 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 12/13/19 | 420 | Gutierrez Salas, Jose |  | 257.49
PR | 995 | 12/13/19 | 421 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 12/13/19 | 430 | Lee, Ha Nul |  | 338.8
PR | 995 | 12/13/19 | 430 | Lee, Ha Nul |  | 84.7
PR | 995 | 12/13/19 | 431 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 12/13/19 | 433 | Lovo, German G |  | 101.64
PR | 995 | 12/13/19 | 436 | Martinez Reyes, Juan C |  | 611.11
PR | 995 | 12/13/19 | 438 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 12/13/19 | 438 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 465.85
PR | 995 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 167.71
PR | 995 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 12/13/19 | 442 | Ramos Herrera, Franklin J |  | 444.68
PR | 995 | 12/13/19 | 442 | Ramos Herrera, Franklin J |  | 63.53
PR | 995 | 12/13/19 | 444 | Reyes Cruz, Denis A |  | 559.02
PR | 995 | 12/13/19 | 446 | Rivera, Jorge A |  | 514.98
PR | 995 | 12/13/19 | 450 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 12/13/19 | 450 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 12/13/19 | 452 | Sanders, Allen O |  | 160.08
PR | 995 | 12/13/19 | 455 | Stahlschmidt, John P |  | 372.68
PR | 995 | 12/13/19 | 460 | Velasquez Cruz, Denis M |  | 533.61
PR | 995 | 12/13/19 | 461 | Velasquez Cruz, Osman N |  | 474.32
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A |  | 579.35
PR | 995 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A |  | 30.49
PR | 995 | 12/20/19 | 543 | Anderson, Richard P |  | 601.79
PR | 995 | 12/20/19 | 543 | Anderson, Richard P |  | 228.27
PR | 995 | 12/20/19 | 546 | Barbosa, Michael S |  | 111.8
PR | 995 | 12/20/19 | 546 | Barbosa, Michael S |  | 335.41
PR | 995 | 12/20/19 | 547 | Barnhart, Joseph N |  | 182.95
PR | 995 | 12/20/19 | 547 | Barnhart, Joseph N |  | 114.35
PR | 995 | 12/20/19 | 548 | Belcher, Jacob T |  | 302.38
PR | 995 | 12/20/19 | 548 | Belcher, Jacob T |  | 35.57
PR | 995 | 12/20/19 | 548 | Belcher, Jacob T |  | 17.79
PR | 995 | 12/20/19 | 549 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 12/20/19 | 553 | Chevez, Herson G |  | 396.4
PR | 995 | 12/20/19 | 553 | Chevez, Herson G |  | 44.04
PR | 995 | 12/20/19 | 566 | Galdamez, Dagoberto A |  | 447.22
PR | 995 | 12/20/19 | 566 | Galdamez, Dagoberto A |  | 111.8
PR | 995 | 12/20/19 | 571 | Gonzalez Hernandez, Josue |  | 480.25
PR | 995 | 12/20/19 | 573 | Gutierrez Salas, Jose |  | 289.67
PR | 995 | 12/20/19 | 574 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 12/20/19 | 583 | Lee, Ha Nul |  | 285.86
PR | 995 | 12/20/19 | 583 | Lee, Ha Nul |  | 105.88
PR | 995 | 12/20/19 | 584 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 12/20/19 | 584 | Lima Romero, Melvin A |  | 386.23
PR | 995 | 12/20/19 | 586 | Lovo, German G |  | 254.1
PR | 995 | 12/20/19 | 586 | Lovo, German G |  | 50.82
PR | 995 | 12/20/19 | 586 | Lovo, German G |  | 203.28
PR | 995 | 12/20/19 | 589 | Martinez Reyes, Juan C |  | 485.75
PR | 995 | 12/20/19 | 589 | Martinez Reyes, Juan C |  | 94.02
PR | 995 | 12/20/19 | 591 | Mendoza Morales, Jesus A |  | 420.11
PR | 995 | 12/20/19 | 591 | Mendoza Morales, Jesus A |  | 121.97
PR | 995 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 391.31
PR | 995 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 223.61
PR | 995 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 93.17
PR | 995 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 18.63
PR | 995 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 18.63
PR | 995 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 431.97
PR | 995 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 50.82
PR | 995 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 25.41
PR | 995 | 12/20/19 | 597 | Reyes Cruz, Denis A |  | 419.27
PR | 995 | 12/20/19 | 597 | Reyes Cruz, Denis A |  | 139.76
PR | 995 | 12/20/19 | 599 | Rivera, Jorge A |  | 514.98
PR | 995 | 12/20/19 | 603 | Rosas Olivares, Jorge C |  | 135.52
PR | 995 | 12/20/19 | 603 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 12/20/19 | 608 | Stahlschmidt, John P |  | 372.68
PR | 995 | 12/20/19 | 613 | Velasquez Cruz, Denis M |  | 444.68
PR | 995 | 12/20/19 | 613 | Velasquez Cruz, Denis M |  | 148.23
PR | 995 | 12/20/19 | 614 | Velasquez Cruz, Osman N |  | 355.74
PR | 995 | 12/20/19 | 614 | Velasquez Cruz, Osman N |  | 118.58
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A |  | 137.21
PR | 995 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A |  | 106.72
PR | 995 | 12/27/19 | 700 | Anderson, Richard P |  | 394.28
PR | 995 | 12/27/19 | 700 | Anderson, Richard P |  | 103.76
PR | 995 | 12/27/19 | 703 | Barbosa, Michael S |  | 195.66
PR | 995 | 12/27/19 | 703 | Barbosa, Michael S |  | 139.76
PR | 995 | 12/27/19 | 704 | Barnhart, Joseph N |  | 68.61
PR | 995 | 12/27/19 | 706 | Benites Portillo, Marvin E |  | 122.82
PR | 995 | 12/27/19 | 706 | Benites Portillo, Marvin E |  | 73.69
PR | 995 | 12/27/19 | 710 | Chevez, Herson G |  | 154.15
PR | 995 | 12/27/19 | 710 | Chevez, Herson G |  | 110.11
PR | 995 | 12/27/19 | 724 | Galdamez, Dagoberto A |  | 139.76
PR | 995 | 12/27/19 | 724 | Galdamez, Dagoberto A |  | 83.85
PR | 995 | 12/27/19 | 729 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 12/27/19 | 732 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 12/27/19 | 741 | Lee, Ha Nul |  | 232.93
PR | 995 | 12/27/19 | 741 | Lee, Ha Nul |  | 21.18
PR | 995 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 64.37
PR | 995 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 64.37
PR | 995 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 12/27/19 | 744 | Lovo, German G |  | 177.87
PR | 995 | 12/27/19 | 744 | Lovo, German G |  | 127.05
PR | 995 | 12/27/19 | 747 | Martinez Reyes, Juan C |  | 109.69
PR | 995 | 12/27/19 | 747 | Martinez Reyes, Juan C |  | 141.03
PR | 995 | 12/27/19 | 749 | Mendoza Morales, Jesus A |  | 135.52
PR | 995 | 12/27/19 | 749 | Mendoza Morales, Jesus A |  | 81.31
PR | 995 | 12/27/19 | 751 | Paco Leyva, Orlando |  | 335.41
PR | 995 | 12/27/19 | 751 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 12/27/19 | 753 | Ramos Herrera, Franklin J |  | 127.05
PR | 995 | 12/27/19 | 753 | Ramos Herrera, Franklin J |  | 76.23
PR | 995 | 12/27/19 | 755 | Reyes Cruz, Denis A |  | 223.61
PR | 995 | 12/27/19 | 757 | Rivera, Jorge A |  | 386.23
PR | 995 | 12/27/19 | 761 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 12/27/19 | 766 | Stahlschmidt, John P |  | 149.07
PR | 995 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/03/20 | 2 | Amaya Gonzalez, Edilberto A |  | 442.13
PR | 995 | 01/03/20 | 3 | Anderson, Richard P |  | 186.76
PR | 995 | 01/03/20 | 3 | Anderson, Richard P |  | 166.01
PR | 995 | 01/03/20 | 3 | Anderson, Richard P |  | 249.02
PR | 995 | 01/03/20 | 6 | Barbosa, Michael S |  | 181.68
PR | 995 | 01/03/20 | 6 | Barbosa, Michael S |  | 223.61
PR | 995 | 01/03/20 | 9 | Benites Portillo, Marvin E |  | 356.16
PR | 995 | 01/03/20 | 13 | Chevez, Herson G |  | 275.28
PR | 995 | 01/03/20 | 13 | Chevez, Herson G |  | 44.04
PR | 995 | 01/03/20 | 27 | Galdamez, Dagoberto A |  | 405.29
PR | 995 | 01/03/20 | 32 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 01/03/20 | 32 | Gonzalez Hernandez, Josue |  | 198.2
PR | 995 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 38.12
PR | 995 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 127.05
PR | 995 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 01/03/20 | 44 | Lee, Ha Nul |  | 275.28
PR | 995 | 01/03/20 | 44 | Lee, Ha Nul |  | 31.76
PR | 995 | 01/03/20 | 45 | Lima Romero, Melvin A |  | 209.21
PR | 995 | 01/03/20 | 45 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 01/03/20 | 47 | Lovo, German G |  | 368.45
PR | 995 | 01/03/20 | 50 | Martinez Reyes, Juan C |  | 78.35
PR | 995 | 01/03/20 | 52 | Mendoza Morales, Jesus A |  | 284.59
PR | 995 | 01/03/20 | 56 | Ramos Herrera, Franklin J |  | 368.45
PR | 995 | 01/03/20 | 60 | Rivera, Jorge A |  | 32.19
PR | 995 | 01/03/20 | 60 | Rivera, Jorge A |  | 177.02
PR | 995 | 01/03/20 | 60 | Rivera, Jorge A |  | 257.49
PR | 995 | 01/03/20 | 63 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 01/03/20 | 64 | Rosas Olivares, Jorge C |  | 177.87
PR | 995 | 01/03/20 | 66 | Sanders, Allen O |  | 57.17
PR | 995 | 01/03/20 | 69 | Stahlschmidt, John P |  | 121.12
PR | 995 | 01/03/20 | 81 | Donelson, Richard T |  | 52.94
PR | 995 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A |  | 487.87
PR | 995 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A |  | 45.74
PR | 995 | 01/10/20 | 276 | Anderson, Richard P |  | 103.76
PR | 995 | 01/10/20 | 276 | Anderson, Richard P |  | 83.01
PR | 995 | 01/10/20 | 276 | Anderson, Richard P |  | 560.29
PR | 995 | 01/10/20 | 276 | Anderson, Richard P |  | 62.25
PR | 995 | 01/10/20 | 276 | Anderson, Richard P |  | 20.75
PR | 995 | 01/10/20 | 279 | Barbosa, Michael S |  | 443.72
PR | 995 | 01/10/20 | 280 | Barnhart, Joseph N |  | 91.48
PR | 995 | 01/10/20 | 282 | Benites Portillo, Marvin E |  | 98.25
PR | 995 | 01/10/20 | 282 | Benites Portillo, Marvin E |  | 294.76
PR | 995 | 01/10/20 | 286 | Chevez, Herson G |  | 374.37
PR | 995 | 01/10/20 | 286 | Chevez, Herson G |  | 66.07
PR | 995 | 01/10/20 | 300 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 01/10/20 | 305 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 01/10/20 | 317 | Lee, Ha Nul |  | 402.33
PR | 995 | 01/10/20 | 317 | Lee, Ha Nul |  | 21.18
PR | 995 | 01/10/20 | 318 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 01/10/20 | 320 | Lovo, German G |  | 317.63
PR | 995 | 01/10/20 | 320 | Lovo, German G |  | 76.23
PR | 995 | 01/10/20 | 323 | Martinez Reyes, Juan C |  | 305.56
PR | 995 | 01/10/20 | 323 | Martinez Reyes, Juan C |  | 109.69
PR | 995 | 01/10/20 | 325 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 01/10/20 | 327 | Paco Leyva, Orlando |  | 149.07
PR | 995 | 01/10/20 | 327 | Paco Leyva, Orlando |  | 149.07
PR | 995 | 01/10/20 | 329 | Ramos Herrera, Franklin J |  | 368.45
PR | 995 | 01/10/20 | 333 | Rivera, Jorge A |  | 514.98
PR | 995 | 01/10/20 | 333 | Rivera, Jorge A |  | 128.74
PR | 995 | 01/10/20 | 337 | Rosas Olivares, Jorge C |  | 110.11
PR | 995 | 01/10/20 | 337 | Rosas Olivares, Jorge C |  | 220.22
PR | 995 | 01/10/20 | 339 | Sanders, Allen O |  | 102.91
PR | 995 | 01/10/20 | 342 | Stahlschmidt, John P |  | 279.51
PR | 995 | 01/10/20 | 342 | Stahlschmidt, John P |  | 18.63
PR | 995 | 01/10/20 | 352 | Donelson, Richard T |  | 52.94
PR | 995 | 01/17/20 | 542 | Anderson, Richard P |  | 570.67
PR | 995 | 01/17/20 | 542 | Anderson, Richard P |  | 20.75
PR | 995 | 01/17/20 | 545 | Barbosa, Michael S |  | 223.61
PR | 995 | 01/17/20 | 545 | Barbosa, Michael S |  | 111.8
PR | 995 | 01/17/20 | 546 | Barnhart, Joseph N |  | 68.61
PR | 995 | 01/17/20 | 548 | Benites Portillo, Marvin E |  | 393.01
PR | 995 | 01/17/20 | 552 | Chevez, Herson G |  | 264.26
PR | 995 | 01/17/20 | 552 | Chevez, Herson G |  | 88.09
PR | 995 | 01/17/20 | 566 | Galdamez, Dagoberto A |  | 447.22
PR | 995 | 01/17/20 | 571 | Gonzalez Hernandez, Josue |  | 434.51
PR | 995 | 01/17/20 | 574 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 01/17/20 | 583 | Lee, Ha Nul |  | 338.8
PR | 995 | 01/17/20 | 584 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 01/17/20 | 586 | Lovo, German G |  | 495.5
PR | 995 | 01/17/20 | 589 | Martinez Reyes, Juan C |  | 485.75
PR | 995 | 01/17/20 | 591 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 01/17/20 | 599 | Rivera, Jorge A |  | 643.72
PR | 995 | 01/17/20 | 603 | Rosas Olivares, Jorge C |  | 203.28
PR | 995 | 01/17/20 | 605 | Sanders, Allen O |  | 57.17
PR | 995 | 01/17/20 | 608 | Stahlschmidt, John P |  | 223.61
PR | 995 | 01/17/20 | 618 | Donelson, Richard T |  | 132.34
PR | 995 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 01/24/20 | 675 | Anderson, Richard P |  | 477.28
PR | 995 | 01/24/20 | 675 | Anderson, Richard P |  | 20.75
PR | 995 | 01/24/20 | 678 | Barbosa, Michael S |  | 335.41
PR | 995 | 01/24/20 | 678 | Barbosa, Michael S |  | 223.61
PR | 995 | 01/24/20 | 679 | Barnhart, Joseph N |  | 91.48
PR | 995 | 01/24/20 | 681 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 01/24/20 | 685 | Chevez, Herson G |  | 440.44
PR | 995 | 01/24/20 | 698 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 01/24/20 | 706 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 01/24/20 | 714 | Lee, Ha Nul |  | 423.5
PR | 995 | 01/24/20 | 715 | Lima Romero, Melvin A |  | 386.23
PR | 995 | 01/24/20 | 715 | Lima Romero, Melvin A |  | 257.49
PR | 995 | 01/24/20 | 717 | Lovo, German G |  | 508.2
PR | 995 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 01/24/20 | 722 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 01/24/20 | 722 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 242.24
PR | 995 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 130.44
PR | 995 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 74.54
PR | 995 | 01/24/20 | 726 | Ramos Herrera, Franklin J |  | 304.92
PR | 995 | 01/24/20 | 730 | Rivera, Jorge A |  | 643.72
PR | 995 | 01/24/20 | 734 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 01/24/20 | 736 | Sanders, Allen O |  | 34.3
PR | 995 | 01/24/20 | 739 | Stahlschmidt, John P |  | 372.68
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 26.47
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 26.47
PR | 995 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 01/31/20 | 834 | Anderson, Richard P |  | 186.76
PR | 995 | 01/31/20 | 834 | Anderson, Richard P |  | 477.28
PR | 995 | 01/31/20 | 837 | Barbosa, Michael S |  | 503.12
PR | 995 | 01/31/20 | 837 | Barbosa, Michael S |  | 55.9
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 45.74
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 22.87
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 45.74
PR | 995 | 01/31/20 | 840 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 01/31/20 | 844 | Chevez, Herson G |  | 440.44
PR | 995 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 531.07
PR | 995 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 27.95
PR | 995 | 01/31/20 | 863 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 01/31/20 | 863 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo |  | 495.5
PR | 995 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo |  | 12.71
PR | 995 | 01/31/20 | 874 | Lee, Ha Nul |  | 391.74
PR | 995 | 01/31/20 | 874 | Lee, Ha Nul |  | 31.76
PR | 995 | 01/31/20 | 875 | Lima Romero, Melvin A |  | 128.74
PR | 995 | 01/31/20 | 875 | Lima Romero, Melvin A |  | 337.95
PR | 995 | 01/31/20 | 877 | Lovo, German G |  | 508.2
PR | 995 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 548.43
PR | 995 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 62.68
PR | 995 | 01/31/20 | 882 | Mendoza Morales, Jesus A |  | 460.77
PR | 995 | 01/31/20 | 882 | Mendoza Morales, Jesus A |  | 81.31
PR | 995 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 37.27
PR | 995 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 37.27
PR | 995 | 01/31/20 | 887 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 01/31/20 | 891 | Rivera, Jorge A |  | 386.23
PR | 995 | 01/31/20 | 891 | Rivera, Jorge A |  | 128.74
PR | 995 | 01/31/20 | 895 | Rosas Olivares, Jorge C |  | 135.52
PR | 995 | 01/31/20 | 895 | Rosas Olivares, Jorge C |  | 135.52
PR | 995 | 01/31/20 | 897 | Sanders, Allen O |  | 148.65
PR | 995 | 01/31/20 | 900 | Stahlschmidt, John P |  | 223.61
PR | 995 | 01/31/20 | 900 | Stahlschmidt, John P |  | 27.95
PR | 995 | 01/31/20 | 910 | Young, Joshua S |  | 33.88
PR | 995 | 01/31/20 | 910 | Young, Joshua S |  | 128.74
PR | 995 | 01/31/20 | 911 | Donelson, Richard T |  | 52.94
PR | 995 | 01/31/20 | 912 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 01/31/20 | 912 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 02/07/20 | 15 | Lovo, German G |  | 304.92
PR | 995 | 02/07/20 | 25 | Anderson, Richard P |  | 103.76
PR | 995 | 02/07/20 | 25 | Anderson, Richard P |  | 352.78
PR | 995 | 02/07/20 | 25 | Anderson, Richard P |  | 207.52
PR | 995 | 02/07/20 | 28 | Barbosa, Michael S |  | 195.66
PR | 995 | 02/07/20 | 28 | Barbosa, Michael S |  | 363.36
PR | 995 | 02/07/20 | 31 | Benites Portillo, Marvin E |  | 393.01
PR | 995 | 02/07/20 | 35 | Chevez, Herson G |  | 440.44
PR | 995 | 02/07/20 | 39 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 02/07/20 | 41 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 02/07/20 | 43 | Draves, Steven W |  | 210.06
PR | 995 | 02/07/20 | 48 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 02/07/20 | 51 | Gerard, Jordan E |  | 284.59
PR | 995 | 02/07/20 | 53 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 02/07/20 | 65 | Lee, Ha Nul |  | 190.58
PR | 995 | 02/07/20 | 65 | Lee, Ha Nul |  | 232.93
PR | 995 | 02/07/20 | 66 | Lima Romero, Melvin A |  | 321.86
PR | 995 | 02/07/20 | 66 | Lima Romero, Melvin A |  | 321.86
PR | 995 | 02/07/20 | 68 | Lovo, German G |  | 101.64
PR | 995 | 02/07/20 | 69 | Mackey, Cole J |  | 27.1
PR | 995 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 203.7
PR | 995 | 02/07/20 | 72 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 02/07/20 | 72 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 167.71
PR | 995 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 37.27
PR | 995 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 37.27
PR | 995 | 02/07/20 | 77 | Ramos Herrera, Franklin J |  | 203.28
PR | 995 | 02/07/20 | 81 | Rivera, Jorge A |  | 579.35
PR | 995 | 02/07/20 | 81 | Rivera, Jorge A |  | 64.37
PR | 995 | 02/07/20 | 84 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 02/07/20 | 85 | Rosas Olivares, Jorge C |  | 338.8
PR | 995 | 02/07/20 | 88 | Sanders, Allen O |  | 331.6
PR | 995 | 02/07/20 | 91 | Stahlschmidt, John P |  | 298.14
PR | 995 | 02/07/20 | 101 | Young, Joshua S |  | 230.38
PR | 995 | 02/07/20 | 101 | Young, Joshua S |  | 40.66
PR | 995 | 02/07/20 | 102 | Donelson, Richard T |  | 26.47
PR | 995 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 02/14/20 | 235 | Anderson, Richard P |  | 622.55
PR | 995 | 02/14/20 | 235 | Anderson, Richard P |  | 20.75
PR | 995 | 02/14/20 | 235 | Anderson, Richard P |  | 20.75
PR | 995 | 02/14/20 | 238 | Barbosa, Michael S |  | 447.22
PR | 995 | 02/14/20 | 239 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/14/20 | 241 | Benites Portillo, Marvin E |  | 454.42
PR | 995 | 02/14/20 | 245 | Chevez, Herson G |  | 308.31
PR | 995 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 166.01
PR | 995 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 02/14/20 | 258 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 02/14/20 | 260 | Gauthier, Dillon R |  | 60.98
PR | 995 | 02/14/20 | 263 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 02/14/20 | 266 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 02/14/20 | 275 | Lee, Ha Nul |  | 381.15
PR | 995 | 02/14/20 | 275 | Lee, Ha Nul |  | 42.35
PR | 995 | 02/14/20 | 276 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 02/14/20 | 278 | Lovo, German G |  | 508.2
PR | 995 | 02/14/20 | 279 | Mackey, Cole J |  | 33.88
PR | 995 | 02/14/20 | 280 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/14/20 | 280 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 02/14/20 | 282 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 02/14/20 | 287 | Ramos Herrera, Franklin J |  | 50.82
PR | 995 | 02/14/20 | 291 | Rivera, Jorge A |  | 643.72
PR | 995 | 02/14/20 | 294 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 02/14/20 | 295 | Rosas Olivares, Jorge C |  | 338.8
PR | 995 | 02/14/20 | 298 | Sanders, Allen O |  | 91.48
PR | 995 | 02/14/20 | 301 | Stahlschmidt, John P |  | 223.61
PR | 995 | 02/14/20 | 301 | Stahlschmidt, John P |  | 74.54
PR | 995 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 02/14/20 | 311 | Young, Joshua S |  | 243.94
PR | 995 | 02/14/20 | 311 | Young, Joshua S |  | 27.1
PR | 995 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 02/21/20 | 452 | Anderson, Richard P |  | 62.25
PR | 995 | 02/21/20 | 452 | Anderson, Richard P |  | 664.05
PR | 995 | 02/21/20 | 452 | Anderson, Richard P |  | 103.76
PR | 995 | 02/21/20 | 455 | Barbosa, Michael S |  | 531.07
PR | 995 | 02/21/20 | 455 | Barbosa, Michael S |  | 27.95
PR | 995 | 02/21/20 | 458 | Benites Portillo, Marvin E |  | 478.98
PR | 995 | 02/21/20 | 458 | Benites Portillo, Marvin E |  | 12.28
PR | 995 | 02/21/20 | 459 | Boss, Benjamin T |  | 121.97
PR | 995 | 02/21/20 | 460 | Boss, Kyle A |  | 142.3
PR | 995 | 02/21/20 | 462 | Chevez, Herson G |  | 253.25
PR | 995 | 02/21/20 | 462 | Chevez, Herson G |  | 11.01
PR | 995 | 02/21/20 | 466 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 02/21/20 | 468 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 02/21/20 | 474 | Galdamez, Dagoberto A |  | 559.02
PR | 995 | 02/21/20 | 476 | Gauthier, Dillon R |  | 60.98
PR | 995 | 02/21/20 | 479 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 02/21/20 | 481 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 02/21/20 | 490 | Lee, Ha Nul |  | 402.33
PR | 995 | 02/21/20 | 490 | Lee, Ha Nul |  | 21.18
PR | 995 | 02/21/20 | 491 | Lima Romero, Melvin A |  | 611.53
PR | 995 | 02/21/20 | 491 | Lima Romero, Melvin A |  | 32.19
PR | 995 | 02/21/20 | 493 | Lovo, German G |  | 368.45
PR | 995 | 02/21/20 | 494 | Mackey, Cole J |  | 33.88
PR | 995 | 02/21/20 | 495 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/21/20 | 497 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 02/21/20 | 507 | Rivera, Jorge A |  | 611.53
PR | 995 | 02/21/20 | 507 | Rivera, Jorge A |  | 32.19
PR | 995 | 02/21/20 | 510 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 02/21/20 | 511 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 02/21/20 | 514 | Sanders, Allen O |  | 262.99
PR | 995 | 02/21/20 | 517 | Stahlschmidt, John P |  | 177.02
PR | 995 | 02/21/20 | 517 | Stahlschmidt, John P |  | 195.66
PR | 995 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 02/21/20 | 527 | Young, Joshua S |  | 216.83
PR | 995 | 02/21/20 | 528 | Donelson, Richard T |  | 26.47
PR | 995 | 02/21/20 | 529 | Gerard, Jeffrey S |  | 61.41
PR | 995 | 02/28/20 | 680 | Anderson, Richard P |  | 20.75
PR | 995 | 02/28/20 | 680 | Anderson, Richard P |  | 643.3
PR | 995 | 02/28/20 | 680 | Anderson, Richard P |  | 62.25
PR | 995 | 02/28/20 | 680 | Anderson, Richard P |  | 62.25
PR | 995 | 02/28/20 | 680 | Anderson, Richard P |  | 41.5
PR | 995 | 02/28/20 | 683 | Barbosa, Michael S |  | 335.41
PR | 995 | 02/28/20 | 683 | Barbosa, Michael S |  | 181.68
PR | 995 | 02/28/20 | 683 | Barbosa, Michael S |  | 41.93
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 22.87
PR | 995 | 02/28/20 | 685 | Benites Portillo, Marvin E |  | 294.76
PR | 995 | 02/28/20 | 685 | Benites Portillo, Marvin E |  | 196.5
PR | 995 | 02/28/20 | 687 | Boss, Benjamin T |  | 121.97
PR | 995 | 02/28/20 | 688 | Boss, Kyle A |  | 142.3
PR | 995 | 02/28/20 | 690 | Chevez, Herson G |  | 352.35
PR | 995 | 02/28/20 | 690 | Chevez, Herson G |  | 88.09
PR | 995 | 02/28/20 | 694 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 02/28/20 | 696 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 02/28/20 | 703 | Galdamez, Dagoberto A |  | 335.41
PR | 995 | 02/28/20 | 703 | Galdamez, Dagoberto A |  | 111.8
PR | 995 | 02/28/20 | 705 | Gauthier, Dillon R |  | 60.98
PR | 995 | 02/28/20 | 708 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 02/28/20 | 708 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 02/28/20 | 719 | Lee, Ha Nul |  | 423.5
PR | 995 | 02/28/20 | 720 | Lima Romero, Melvin A |  | 386.23
PR | 995 | 02/28/20 | 720 | Lima Romero, Melvin A |  | 128.74
PR | 995 | 02/28/20 | 722 | Lovo, German G |  | 304.92
PR | 995 | 02/28/20 | 722 | Lovo, German G |  | 203.28
PR | 995 | 02/28/20 | 723 | Mackey, Cole J |  | 33.88
PR | 995 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 329.06
PR | 995 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/28/20 | 726 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 02/28/20 | 739 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 02/28/20 | 740 | Rosas Olivares, Jorge C |  | 245.63
PR | 995 | 02/28/20 | 743 | Sanders, Allen O |  | 194.39
PR | 995 | 02/28/20 | 746 | Stahlschmidt, John P |  | 372.68
PR | 995 | 02/28/20 | 749 | Trower-Kelly, Fidel D |  | 142.3
PR | 995 | 02/28/20 | 756 | Young, Joshua S |  | 271.04
PR | 995 | 02/28/20 | 757 | Donelson, Richard T |  | 26.47
PR | 995 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 03/06/20 | 42 | Anderson, Richard P |  | 124.51
PR | 995 | 03/06/20 | 42 | Anderson, Richard P |  | 518.79
PR | 995 | 03/06/20 | 42 | Anderson, Richard P |  | 145.26
PR | 995 | 03/06/20 | 42 | Anderson, Richard P |  | 20.75
PR | 995 | 03/06/20 | 42 | Anderson, Richard P |  | 20.75
PR | 995 | 03/06/20 | 45 | Barbosa, Michael S |  | 111.8
PR | 995 | 03/06/20 | 45 | Barbosa, Michael S |  | 223.61
PR | 995 | 03/06/20 | 45 | Barbosa, Michael S |  | 223.61
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 114.35
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 148.65
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 57.17
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 11.43
PR | 995 | 03/06/20 | 48 | Benites Portillo, Marvin E |  | 196.5
PR | 995 | 03/06/20 | 48 | Benites Portillo, Marvin E |  | 196.5
PR | 995 | 03/06/20 | 49 | Boss, Benjamin T |  | 304.92
PR | 995 | 03/06/20 | 50 | Boss, Kyle A |  | 142.3
PR | 995 | 03/06/20 | 52 | Chevez, Herson G |  | 407.41
PR | 995 | 03/06/20 | 52 | Chevez, Herson G |  | 33.03
PR | 995 | 03/06/20 | 56 | Cruz Gonzalez, Julio C |  | 154.15
PR | 995 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 03/06/20 | 66 | Galdamez, Dagoberto A |  | 335.41
PR | 995 | 03/06/20 | 66 | Galdamez, Dagoberto A |  | 223.61
PR | 995 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 45.74
PR | 995 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 76.23
PR | 995 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 198.2
PR | 995 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 03/06/20 | 81 | Lee, Ha Nul |  | 296.45
PR | 995 | 03/06/20 | 81 | Lee, Ha Nul |  | 42.35
PR | 995 | 03/06/20 | 82 | Lima Romero, Melvin A |  | 579.35
PR | 995 | 03/06/20 | 82 | Lima Romero, Melvin A |  | 64.37
PR | 995 | 03/06/20 | 84 | Lovo, German G |  | 304.92
PR | 995 | 03/06/20 | 84 | Lovo, German G |  | 203.28
PR | 995 | 03/06/20 | 85 | Mackey, Cole J |  | 33.88
PR | 995 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 03/06/20 | 88 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 03/06/20 | 90 | Paco Leyva, Orlando |  | 149.07
PR | 995 | 03/06/20 | 94 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 03/06/20 | 98 | Rivera, Jorge A |  | 386.23
PR | 995 | 03/06/20 | 98 | Rivera, Jorge A |  | 257.49
PR | 995 | 03/06/20 | 101 | Romero Garza, Jesus I |  | 204.55
PR | 995 | 03/06/20 | 102 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 03/06/20 | 102 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 03/06/20 | 105 | Sanders, Allen O |  | 331.6
PR | 995 | 03/06/20 | 108 | Stahlschmidt, John P |  | 372.68
PR | 995 | 03/06/20 | 118 | Young, Joshua S |  | 271.04
PR | 995 | 03/13/20 | 307 | Anderson, Richard P |  | 217.89
PR | 995 | 03/13/20 | 307 | Anderson, Richard P |  | 186.76
PR | 995 | 03/13/20 | 307 | Anderson, Richard P |  | 539.54
PR | 995 | 03/13/20 | 307 | Anderson, Richard P |  | 83.01
PR | 995 | 03/13/20 | 307 | Anderson, Richard P |  | 20.75
PR | 995 | 03/13/20 | 310 | Barbosa, Michael S |  | 531.07
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 137.21
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 114.35
PR | 995 | 03/13/20 | 313 | Benites Portillo, Marvin E |  | 128.96
PR | 995 | 03/13/20 | 313 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 03/13/20 | 314 | Boss, Benjamin T |  | 304.92
PR | 995 | 03/13/20 | 315 | Boss, Kyle A |  | 355.74
PR | 995 | 03/13/20 | 317 | Chevez, Herson G |  | 115.62
PR | 995 | 03/13/20 | 317 | Chevez, Herson G |  | 440.44
PR | 995 | 03/13/20 | 321 | Cruz Gonzalez, Julio C |  | 468.39
PR | 995 | 03/13/20 | 323 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 03/13/20 | 327 | Eliassen, Cory H |  | 203.28
PR | 995 | 03/13/20 | 330 | Galdamez, Dagoberto A |  | 223.61
PR | 995 | 03/13/20 | 330 | Galdamez, Dagoberto A |  | 335.41
PR | 995 | 03/13/20 | 334 | Gonzalez Hernandez, Josue |  | 548.86
PR | 995 | 03/13/20 | 334 | Gonzalez Hernandez, Josue |  | 60.98
PR | 995 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 133.4
PR | 995 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 03/13/20 | 345 | Lee, Ha Nul |  | 338.8
PR | 995 | 03/13/20 | 346 | Lima Romero, Melvin A |  | 643.72
PR | 995 | 03/13/20 | 348 | Lovo, German G |  | 508.2
PR | 995 | 03/13/20 | 349 | Mackey, Cole J |  | 33.88
PR | 995 | 03/13/20 | 350 | Martinez Reyes, Juan C |  | 152.78
PR | 995 | 03/13/20 | 350 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 03/13/20 | 352 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 03/13/20 | 354 | Paco Leyva, Orlando |  | 298.14
PR | 995 | 03/13/20 | 354 | Paco Leyva, Orlando |  | 195.66
PR | 995 | 03/13/20 | 358 | Ramos Herrera, Franklin J |  | 152.46
PR | 995 | 03/13/20 | 358 | Ramos Herrera, Franklin J |  | 50.82
PR | 995 | 03/13/20 | 362 | Rivera, Jorge A |  | 611.53
PR | 995 | 03/13/20 | 362 | Rivera, Jorge A |  | 32.19
PR | 995 | 03/13/20 | 365 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 03/13/20 | 366 | Rosas Olivares, Jorge C |  | 271.04
PR | 995 | 03/13/20 | 366 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 03/13/20 | 369 | Sanders, Allen O |  | 400.21
PR | 995 | 03/13/20 | 372 | Stahlschmidt, John P |  | 372.68
PR | 995 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 03/13/20 | 382 | Young, Joshua S |  | 271.04
PR | 995 | 03/13/20 | 383 | Donelson, Richard T |  | 26.47
PR | 995 | 03/13/20 | 383 | Donelson, Richard T |  | 26.47
PR | 995 | 03/13/20 | 384 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 03/20/20 | 565 | Anderson, Richard P |  | 560.29
PR | 995 | 03/20/20 | 565 | Anderson, Richard P |  | 124.51
PR | 995 | 03/20/20 | 565 | Anderson, Richard P |  | 103.76
PR | 995 | 03/20/20 | 565 | Anderson, Richard P |  | 20.75
PR | 995 | 03/20/20 | 565 | Anderson, Richard P |  | 20.75
PR | 995 | 03/20/20 | 568 | Barbosa, Michael S |  | 335.41
PR | 995 | 03/20/20 | 568 | Barbosa, Michael S |  | 111.8
PR | 995 | 03/20/20 | 571 | Benites Portillo, Marvin E |  | 196.5
PR | 995 | 03/20/20 | 571 | Benites Portillo, Marvin E |  | 196.5
PR | 995 | 03/20/20 | 572 | Boss, Benjamin T |  | 60.98
PR | 995 | 03/20/20 | 573 | Boss, Kyle A |  | 71.15
PR | 995 | 03/20/20 | 575 | Chevez, Herson G |  | 176.18
PR | 995 | 03/20/20 | 581 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 03/20/20 | 585 | Eliassen, Cory H |  | 101.64
PR | 995 | 03/20/20 | 588 | Galdamez, Dagoberto A |  | 223.61
PR | 995 | 03/20/20 | 592 | Gonzalez Hernandez, Josue |  | 213.44
PR | 995 | 03/20/20 | 592 | Gonzalez Hernandez, Josue |  | 396.4
PR | 995 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 03/20/20 | 603 | Lee, Ha Nul |  | 423.5
PR | 995 | 03/20/20 | 604 | Lima Romero, Melvin A |  | 627.63
PR | 995 | 03/20/20 | 606 | Lovo, German G |  | 470.09
PR | 995 | 03/20/20 | 608 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 03/20/20 | 608 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 03/20/20 | 610 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 03/20/20 | 612 | Paco Leyva, Orlando |  | 204.97
PR | 995 | 03/20/20 | 616 | Ramos Herrera, Franklin J |  | 139.76
PR | 995 | 03/20/20 | 620 | Rivera, Jorge A |  | 386.23
PR | 995 | 03/20/20 | 620 | Rivera, Jorge A |  | 257.49
PR | 995 | 03/20/20 | 624 | Rosas Olivares, Jorge C |  | 262.57
PR | 995 | 03/20/20 | 627 | Sanders, Allen O |  | 354.47
PR | 995 | 03/20/20 | 630 | Stahlschmidt, John P |  | 223.61
PR | 995 | 03/20/20 | 630 | Stahlschmidt, John P |  | 149.07
PR | 995 | 03/20/20 | 640 | Young, Joshua S |  | 271.04
PR | 995 | 03/20/20 | 641 | Donelson, Richard T |  | 52.94
PR | 995 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 03/26/20 | 748 | Anderson, Richard P |  | 684.8
PR | 995 | 03/26/20 | 748 | Anderson, Richard P |  | 20.75
PR | 995 | 03/26/20 | 748 | Anderson, Richard P |  | 41.5
PR | 995 | 03/26/20 | 751 | Barbosa, Michael S |  | 237.58
PR | 995 | 03/26/20 | 751 | Barbosa, Michael S |  | 209.63
PR | 995 | 03/26/20 | 751 | Barbosa, Michael S |  | 111.8
PR | 995 | 03/26/20 | 754 | Benites Portillo, Marvin E |  | 491.26
PR | 995 | 03/26/20 | 755 | Boss, Benjamin T |  | 304.92
PR | 995 | 03/26/20 | 756 | Boss, Kyle A |  | 355.74
PR | 995 | 03/26/20 | 758 | Chevez, Herson G |  | 264.26
PR | 995 | 03/26/20 | 763 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 03/26/20 | 767 | Eliassen, Cory H |  | 508.2
PR | 995 | 03/26/20 | 770 | Galdamez, Dagoberto A |  | 223.61
PR | 995 | 03/26/20 | 774 | Gonzalez Hernandez, Josue |  | 579.35
PR | 995 | 03/26/20 | 774 | Gonzalez Hernandez, Josue |  | 30.49
PR | 995 | 03/26/20 | 777 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 93.17
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 149.07
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 93.17
PR | 995 | 03/26/20 | 784 | Lee, Ha Nul |  | 254.1
PR | 995 | 03/26/20 | 785 | Lima Romero, Melvin A |  | 514.98
PR | 995 | 03/26/20 | 787 | Lovo, German G |  | 508.2
PR | 995 | 03/26/20 | 789 | Martinez Reyes, Juan C |  | 266.38
PR | 995 | 03/26/20 | 789 | Martinez Reyes, Juan C |  | 360.4
PR | 995 | 03/26/20 | 791 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 03/26/20 | 800 | Rivera, Jorge A |  | 643.72
PR | 995 | 03/26/20 | 803 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 03/26/20 | 804 | Rosas Olivares, Jorge C |  | 67.76
PR | 995 | 03/26/20 | 806 | Sanders, Allen O |  | 560.29
PR | 995 | 03/26/20 | 809 | Stahlschmidt, John P |  | 74.54
PR | 995 | 03/26/20 | 812 | Trower-Kelly, Fidel D |  | 284.59
PR | 995 | 03/26/20 | 819 | Young, Joshua S |  | 162.62
PR | 995 | 03/26/20 | 820 | Donelson, Richard T |  | 79.41
PR | 995 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 04/03/20 | 42 | Donelson, Richard T |  | 26.47
PR | 995 | 04/17/20 | 288 | Donelson, Richard T |  | 26.47
PR | 995 | 04/24/20 | 348 | Anderson, Richard P |  | 166.01
PR | 995 | 04/24/20 | 351 | Barbosa, Michael S |  | 111.8
PR | 995 | 04/24/20 | 391 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 04/24/20 | 424 | Donelson, Richard T |  | 26.47
PR | 995 | 05/01/20 | 2 | Anderson, Richard P |  | 83.01
PR | 995 | 05/01/20 | 2 | Anderson, Richard P |  | 684.8
PR | 995 | 05/01/20 | 2 | Anderson, Richard P |  | 20.75
PR | 995 | 05/01/20 | 2 | Anderson, Richard P |  | 41.5
PR | 995 | 05/01/20 | 5 | Barbosa, Michael S |  | 111.8
PR | 995 | 05/01/20 | 5 | Barbosa, Michael S |  | 447.22
PR | 995 | 05/01/20 | 10 | Boss, Kyle A |  | 71.15
PR | 995 | 05/01/20 | 18 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 05/01/20 | 22 | Eliassen, Cory H |  | 69.88
PR | 995 | 05/01/20 | 45 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 05/01/20 | 45 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 05/01/20 | 60 | Romero Garza, Jesus I |  | 77.92
PR | 995 | 05/01/20 | 64 | Sanders, Allen O |  | 160.08
PR | 995 | 05/01/20 | 70 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 05/01/20 | 78 | Donelson, Richard T |  | 26.47
PR | 995 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 05/08/20 | 153 | Anderson, Richard P |  | 726.3
PR | 995 | 05/08/20 | 153 | Anderson, Richard P |  | 62.25
PR | 995 | 05/08/20 | 156 | Barbosa, Michael S |  | 447.22
PR | 995 | 05/08/20 | 157 | Barnhart, Joseph N |  | 91.48
PR | 995 | 05/08/20 | 169 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 05/08/20 | 173 | Eliassen, Cory H |  | 508.2
PR | 995 | 05/08/20 | 183 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 05/08/20 | 185 | Holmes, Anthony R |  | 149.07
PR | 995 | 05/08/20 | 191 | Lee, Ha Nul |  | 84.7
PR | 995 | 05/08/20 | 196 | Martinez Reyes, Juan C |  | 454.42
PR | 995 | 05/08/20 | 196 | Martinez Reyes, Juan C |  | 47.01
PR | 995 | 05/08/20 | 198 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 05/08/20 | 211 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 05/08/20 | 215 | Sanders, Allen O |  | 194.39
PR | 995 | 05/08/20 | 231 | Donelson, Richard T |  | 26.47
PR | 995 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 05/15/20 | 308 | Anderson, Richard P |  | 20.75
PR | 995 | 05/15/20 | 308 | Anderson, Richard P |  | 643.3
PR | 995 | 05/15/20 | 309 | Ascencio, Jose L |  | 391.31
PR | 995 | 05/15/20 | 309 | Ascencio, Jose L |  | 55.9
PR | 995 | 05/15/20 | 311 | Barbosa, Michael S |  | 559.02
PR | 995 | 05/15/20 | 312 | Barnhart, Joseph N |  | 45.74
PR | 995 | 05/15/20 | 312 | Barnhart, Joseph N |  | 22.87
PR | 995 | 05/15/20 | 324 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 05/15/20 | 328 | Eliassen, Cory H |  | 273.16
PR | 995 | 05/15/20 | 335 | Gonzalez Hernandez, Josue |  | 426.89
PR | 995 | 05/15/20 | 335 | Gonzalez Hernandez, Josue |  | 60.98
PR | 995 | 05/15/20 | 338 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 05/15/20 | 340 | Holmes, Anthony R |  | 316.78
PR | 995 | 05/15/20 | 340 | Holmes, Anthony R |  | 335.41
PR | 995 | 05/15/20 | 340 | Holmes, Anthony R |  | 93.17
PR | 995 | 05/15/20 | 346 | Lee, Ha Nul |  | 423.5
PR | 995 | 05/15/20 | 351 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 05/15/20 | 353 | Mendoza Morales, Jesus A |  | 474.32
PR | 995 | 05/15/20 | 353 | Mendoza Morales, Jesus A |  | 67.76
PR | 995 | 05/15/20 | 366 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 05/15/20 | 370 | Sanders, Allen O |  | 91.48
PR | 995 | 05/15/20 | 384 | Donelson, Richard T |  | 132.34
PR | 995 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 05/22/20 | 463 | Anderson, Richard P |  | 477.28
PR | 995 | 05/22/20 | 463 | Anderson, Richard P |  | 20.75
PR | 995 | 05/22/20 | 464 | Ascencio, Jose L |  | 559.02
PR | 995 | 05/22/20 | 466 | Barbosa, Michael S |  | 559.02
PR | 995 | 05/22/20 | 467 | Barnhart, Joseph N |  | 148.65
PR | 995 | 05/22/20 | 467 | Barnhart, Joseph N |  | 148.65
PR | 995 | 05/22/20 | 477 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 05/22/20 | 479 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 05/22/20 | 483 | Eliassen, Cory H |  | 228.69
PR | 995 | 05/22/20 | 483 | Eliassen, Cory H |  | 50.82
PR | 995 | 05/22/20 | 489 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 05/22/20 | 490 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 05/22/20 | 491 | Holmes, Anthony R |  | 409.95
PR | 995 | 05/22/20 | 491 | Holmes, Anthony R |  | 335.41
PR | 995 | 05/22/20 | 497 | Lee, Ha Nul |  | 423.5
PR | 995 | 05/22/20 | 502 | Martinez Reyes, Juan C |  | 611.11
PR | 995 | 05/22/20 | 504 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 05/22/20 | 517 | Romero Garza, Jesus I |  | 155.85
PR | 995 | 05/22/20 | 520 | Sanders, Allen O |  | 240.12
PR | 995 | 05/22/20 | 525 | Taylor, Evan R |  | 335.41
PR | 995 | 05/22/20 | 534 | Donelson, Richard T |  | 52.94
PR | 995 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 05/29/20 | 591 | Anderson, Richard P |  | 269.77
PR | 995 | 05/29/20 | 592 | Ascencio, Jose L |  | 447.22
PR | 995 | 05/29/20 | 594 | Barbosa, Michael S |  | 349.39
PR | 995 | 05/29/20 | 594 | Barbosa, Michael S |  | 97.83
PR | 995 | 05/29/20 | 595 | Barnhart, Joseph N |  | 137.21
PR | 995 | 05/29/20 | 595 | Barnhart, Joseph N |  | 182.95
PR | 995 | 05/29/20 | 598 | Boss, Benjamin T |  | 121.97
PR | 995 | 05/29/20 | 605 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 05/29/20 | 607 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 05/29/20 | 611 | Eliassen, Cory H |  | 304.92
PR | 995 | 05/29/20 | 617 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 05/29/20 | 618 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 05/29/20 | 619 | Holmes, Anthony R |  | 596.29
PR | 995 | 05/29/20 | 622 | Hubbard, Robert W |  | 45.74
PR | 995 | 05/29/20 | 625 | Lee, Ha Nul |  | 338.8
PR | 995 | 05/29/20 | 630 | Martinez Reyes, Juan C |  | 493.59
PR | 995 | 05/29/20 | 632 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 05/29/20 | 643 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 05/29/20 | 646 | Sanders, Allen O |  | 182.95
PR | 995 | 05/29/20 | 651 | Taylor, Evan R |  | 314.45
PR | 995 | 05/29/20 | 659 | Donelson, Richard T |  | 79.41
PR | 995 | 05/29/20 | 659 | Donelson, Richard T |  | 26.47
PR | 995 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/05/20 | 14 | Anderson, Richard P |  | 591.42
PR | 995 | 06/05/20 | 15 | Ascencio, Jose L |  | 559.02
PR | 995 | 06/05/20 | 17 | Barbosa, Michael S |  | 447.22
PR | 995 | 06/05/20 | 17 | Barbosa, Michael S |  | 111.8
PR | 995 | 06/05/20 | 18 | Barnhart, Joseph N |  | 343.04
PR | 995 | 06/05/20 | 18 | Barnhart, Joseph N |  | 22.87
PR | 995 | 06/05/20 | 18 | Barnhart, Joseph N |  | 45.74
PR | 995 | 06/05/20 | 18 | Barnhart, Joseph N |  | 45.74
PR | 995 | 06/05/20 | 19 | Boss, Benjamin T |  | 243.94
PR | 995 | 06/05/20 | 25 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 06/05/20 | 27 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 06/05/20 | 31 | Eliassen, Cory H |  | 431.97
PR | 995 | 06/05/20 | 36 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 06/05/20 | 37 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 06/05/20 | 38 | Holmes, Anthony R |  | 298.14
PR | 995 | 06/05/20 | 43 | Lee, Ha Nul |  | 423.5
PR | 995 | 06/05/20 | 46 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 06/05/20 | 48 | Mendoza Morales, Jesus A |  | 542.08
PR | 995 | 06/05/20 | 54 | Rivera, Jorge A |  | 643.72
PR | 995 | 06/05/20 | 58 | Sanders, Allen O |  | 343.04
PR | 995 | 06/05/20 | 62 | Trower-Kelly, Fidel D |  | 71.15
PR | 995 | 06/05/20 | 66 | Donelson, Richard T |  | 26.47
PR | 995 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 36.84
PR | 995 | 06/11/20 | 157 | Ascencio, Jose L |  | 223.61
PR | 995 | 06/11/20 | 159 | Barbosa, Michael S |  | 111.8
PR | 995 | 06/11/20 | 159 | Barbosa, Michael S |  | 111.8
PR | 995 | 06/11/20 | 160 | Boss, Benjamin T |  | 121.97
PR | 995 | 06/11/20 | 166 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 06/11/20 | 168 | Cruz Reyes, Jose |  | 216.83
PR | 995 | 06/11/20 | 175 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 06/11/20 | 176 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 06/11/20 | 177 | Holmes, Anthony R |  | 298.14
PR | 995 | 06/11/20 | 182 | Lee, Ha Nul |  | 84.7
PR | 995 | 06/11/20 | 182 | Lee, Ha Nul |  | 84.7
PR | 995 | 06/11/20 | 185 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 06/11/20 | 187 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 06/11/20 | 187 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 06/11/20 | 193 | Rivera, Jorge A |  | 257.49
PR | 995 | 06/12/20 | 218 | Ascencio, Jose L |  | 335.41
PR | 995 | 06/12/20 | 220 | Barbosa, Michael S |  | 223.61
PR | 995 | 06/12/20 | 220 | Barbosa, Michael S |  | 111.8
PR | 995 | 06/12/20 | 221 | Barnhart, Joseph N |  | 503.12
PR | 995 | 06/12/20 | 221 | Barnhart, Joseph N |  | 68.61
PR | 995 | 06/12/20 | 222 | Boss, Benjamin T |  | 182.95
PR | 995 | 06/12/20 | 228 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 06/12/20 | 230 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 06/12/20 | 238 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 06/12/20 | 239 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 06/12/20 | 240 | Holmes, Anthony R |  | 298.14
PR | 995 | 06/12/20 | 245 | Lee, Ha Nul |  | 254.1
PR | 995 | 06/12/20 | 248 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 06/12/20 | 250 | Mendoza Morales, Jesus A |  | 325.25
PR | 995 | 06/12/20 | 256 | Rivera, Jorge A |  | 386.23
PR | 995 | 06/12/20 | 260 | Sanders, Allen O |  | 354.47
PR | 995 | 06/12/20 | 266 | Donelson, Richard T |  | 79.41
PR | 995 | 06/12/20 | 267 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 06/19/20 | 375 | Ascencio, Jose L |  | 447.22
PR | 995 | 06/19/20 | 377 | Barbosa, Michael S |  | 223.61
PR | 995 | 06/19/20 | 377 | Barbosa, Michael S |  | 223.61
PR | 995 | 06/19/20 | 378 | Barnhart, Joseph N |  | 331.6
PR | 995 | 06/19/20 | 378 | Barnhart, Joseph N |  | 68.61
PR | 995 | 06/19/20 | 379 | Boss, Benjamin T |  | 60.98
PR | 995 | 06/19/20 | 385 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 06/19/20 | 394 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 06/19/20 | 394 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 06/19/20 | 396 | Holmes, Anthony R |  | 484.48
PR | 995 | 06/19/20 | 396 | Holmes, Anthony R |  | 204.97
PR | 995 | 06/19/20 | 396 | Holmes, Anthony R |  | 55.9
PR | 995 | 06/19/20 | 401 | Lee, Ha Nul |  | 254.1
PR | 995 | 06/19/20 | 401 | Lee, Ha Nul |  | 84.7
PR | 995 | 06/19/20 | 404 | Martinez Reyes, Juan C |  | 470.09
PR | 995 | 06/19/20 | 404 | Martinez Reyes, Juan C |  | 31.34
PR | 995 | 06/19/20 | 406 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 06/19/20 | 406 | Mendoza Morales, Jesus A |  | 433.66
PR | 995 | 06/19/20 | 412 | Rivera, Jorge A |  | 386.23
PR | 995 | 06/19/20 | 412 | Rivera, Jorge A |  | 257.49
PR | 995 | 06/19/20 | 416 | Sanders, Allen O |  | 377.34
PR | 995 | 06/19/20 | 422 | Donelson, Richard T |  | 52.94
PR | 995 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/26/20 | 518 | Ascencio, Jose L |  | 559.02
PR | 995 | 06/26/20 | 520 | Barbosa, Michael S |  | 391.31
PR | 995 | 06/26/20 | 520 | Barbosa, Michael S |  | 167.71
PR | 995 | 06/26/20 | 521 | Barnhart, Joseph N |  | 343.04
PR | 995 | 06/26/20 | 521 | Barnhart, Joseph N |  | 22.87
PR | 995 | 06/26/20 | 522 | Boss, Benjamin T |  | 60.98
PR | 995 | 06/26/20 | 528 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 06/26/20 | 536 | Gonzalez Hernandez, Josue |  | 548.86
PR | 995 | 06/26/20 | 536 | Gonzalez Hernandez, Josue |  | 60.98
PR | 995 | 06/26/20 | 537 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 06/26/20 | 538 | Holmes, Anthony R |  | 736.04
PR | 995 | 06/26/20 | 543 | Lee, Ha Nul |  | 423.5
PR | 995 | 06/26/20 | 546 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 06/26/20 | 548 | Mendoza Morales, Jesus A |  | 528.53
PR | 995 | 06/26/20 | 554 | Rivera, Jorge A |  | 514.98
PR | 995 | 06/26/20 | 554 | Rivera, Jorge A |  | 128.74
PR | 995 | 06/26/20 | 558 | Sanders, Allen O |  | 182.95
PR | 995 | 06/26/20 | 564 | Donelson, Richard T |  | 52.94
PR | 995 | 06/26/20 | 565 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/26/20 | 565 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/02/20 | 4 | Ascencio, Jose L |  | 531.07
PR | 995 | 07/02/20 | 4 | Ascencio, Jose L |  | 27.95
PR | 995 | 07/02/20 | 6 | Barbosa, Michael S |  | 559.02
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 137.21
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 22.87
PR | 995 | 07/02/20 | 8 | Boss, Benjamin T |  | 304.92
PR | 995 | 07/02/20 | 14 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 07/02/20 | 22 | Gonzalez Hernandez, Josue |  | 426.89
PR | 995 | 07/02/20 | 22 | Gonzalez Hernandez, Josue |  | 182.95
PR | 995 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo |  | 355.74
PR | 995 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo |  | 152.46
PR | 995 | 07/02/20 | 24 | Holmes, Anthony R |  | 633.56
PR | 995 | 07/02/20 | 24 | Holmes, Anthony R |  | 55.9
PR | 995 | 07/02/20 | 29 | Lee, Ha Nul |  | 423.5
PR | 995 | 07/02/20 | 32 | Martinez Reyes, Juan C |  | 579.77
PR | 995 | 07/02/20 | 32 | Martinez Reyes, Juan C |  | 31.34
PR | 995 | 07/02/20 | 34 | Mendoza Morales, Jesus A |  | 216.83
PR | 995 | 07/02/20 | 40 | Rivera, Jorge A |  | 643.72
PR | 995 | 07/02/20 | 44 | Sanders, Allen O |  | 708.94
PR | 995 | 07/02/20 | 51 | Gerard, Jeffrey S |  | 36.84
PR | 995 | 07/10/20 | 137 | Ascencio, Jose L |  | 335.41
PR | 995 | 07/10/20 | 139 | Barbosa, Michael S |  | 335.41
PR | 995 | 07/10/20 | 140 | Barnhart, Joseph N |  | 160.08
PR | 995 | 07/10/20 | 140 | Barnhart, Joseph N |  | 91.48
PR | 995 | 07/10/20 | 140 | Barnhart, Joseph N |  | 365.9
PR | 995 | 07/10/20 | 141 | Boss, Benjamin T |  | 182.95
PR | 995 | 07/10/20 | 147 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 07/10/20 | 154 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 07/10/20 | 154 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 07/10/20 | 155 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 07/10/20 | 156 | Holmes, Anthony R |  | 149.07
PR | 995 | 07/10/20 | 156 | Holmes, Anthony R |  | 298.14
PR | 995 | 07/10/20 | 161 | Lee, Ha Nul |  | 254.1
PR | 995 | 07/10/20 | 164 | Martinez Reyes, Juan C |  | 360.4
PR | 995 | 07/10/20 | 166 | Mendoza Morales, Jesus A |  | 108.42
PR | 995 | 07/10/20 | 172 | Rivera, Jorge A |  | 386.23
PR | 995 | 07/10/20 | 176 | Sanders, Allen O |  | 548.86
PR | 995 | 07/10/20 | 182 | Donelson, Richard T |  | 26.47
PR | 995 | 07/17/20 | 262 | Ascencio, Jose L |  | 559.02
PR | 995 | 07/17/20 | 264 | Barbosa, Michael S |  | 545.04
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 343.04
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 68.61
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 22.87
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 45.74
PR | 995 | 07/17/20 | 266 | Boss, Benjamin T |  | 304.92
PR | 995 | 07/17/20 | 272 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 07/17/20 | 274 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 07/17/20 | 281 | Gonzalez Hernandez, Josue |  | 548.86
PR | 995 | 07/17/20 | 281 | Gonzalez Hernandez, Josue |  | 15.25
PR | 995 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo |  | 470.09
PR | 995 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo |  | 38.12
PR | 995 | 07/17/20 | 283 | Holmes, Anthony R |  | 521.75
PR | 995 | 07/17/20 | 283 | Holmes, Anthony R |  | 130.44
PR | 995 | 07/17/20 | 283 | Holmes, Anthony R |  | 55.9
PR | 995 | 07/17/20 | 283 | Holmes, Anthony R |  | 37.27
PR | 995 | 07/17/20 | 289 | Lee, Ha Nul |  | 391.74
PR | 995 | 07/17/20 | 289 | Lee, Ha Nul |  | 31.76
PR | 995 | 07/17/20 | 291 | Mackey, Cole J |  | 6.78
PR | 995 | 07/17/20 | 292 | Martinez Reyes, Juan C |  | 595.44
PR | 995 | 07/17/20 | 300 | Rivera, Jorge A |  | 643.72
PR | 995 | 07/17/20 | 303 | Sanders, Allen O |  | 777.55
PR | 995 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/24/20 | 401 | Ascencio, Jose L |  | 559.02
PR | 995 | 07/24/20 | 403 | Barbosa, Michael S |  | 559.02
PR | 995 | 07/24/20 | 404 | Barnhart, Joseph N |  | 365.9
PR | 995 | 07/24/20 | 404 | Barnhart, Joseph N |  | 137.21
PR | 995 | 07/24/20 | 404 | Barnhart, Joseph N |  | 68.61
PR | 995 | 07/24/20 | 405 | Boss, Benjamin T |  | 304.92
PR | 995 | 07/24/20 | 411 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 07/24/20 | 413 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 07/24/20 | 420 | Gonzalez Hernandez, Josue |  | 320.17
PR | 995 | 07/24/20 | 420 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 07/24/20 | 421 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 07/24/20 | 422 | Holmes, Anthony R |  | 745.36
PR | 995 | 07/24/20 | 428 | Lee, Ha Nul |  | 322.92
PR | 995 | 07/24/20 | 430 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 07/24/20 | 438 | Rivera, Jorge A |  | 643.72
PR | 995 | 07/24/20 | 442 | Sanders, Allen O |  | 503.12
PR | 995 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 07/31/20 | 496 | Ascencio, Jose L |  | 559.02
PR | 995 | 07/31/20 | 498 | Barbosa, Michael S |  | 531.07
PR | 995 | 07/31/20 | 499 | Barnhart, Joseph N |  | 365.9
PR | 995 | 07/31/20 | 499 | Barnhart, Joseph N |  | 45.74
PR | 995 | 07/31/20 | 499 | Barnhart, Joseph N |  | 45.74
PR | 995 | 07/31/20 | 500 | Boss, Benjamin T |  | 304.92
PR | 995 | 07/31/20 | 506 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 07/31/20 | 508 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 07/31/20 | 515 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 07/31/20 | 516 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 07/31/20 | 517 | Holmes, Anthony R |  | 745.36
PR | 995 | 07/31/20 | 523 | Lee, Ha Nul |  | 169.4
PR | 995 | 07/31/20 | 525 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 07/31/20 | 533 | Rivera, Jorge A |  | 257.49
PR | 995 | 07/31/20 | 537 | Sanders, Allen O |  | 445.95
PR | 995 | 07/31/20 | 543 | Donelson, Richard T |  | 26.47
PR | 995 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 08/07/20 | 87 | Ascencio, Jose L |  | 559.02
PR | 995 | 08/07/20 | 89 | Barbosa, Michael S |  | 559.02
PR | 995 | 08/07/20 | 90 | Barnhart, Joseph N |  | 388.77
PR | 995 | 08/07/20 | 90 | Barnhart, Joseph N |  | 114.35
PR | 995 | 08/07/20 | 90 | Barnhart, Joseph N |  | 45.74
PR | 995 | 08/07/20 | 90 | Barnhart, Joseph N |  | 160.08
PR | 995 | 08/07/20 | 91 | Boss, Benjamin T |  | 121.97
PR | 995 | 08/07/20 | 96 | Cruz Gonzalez, Julio C |  | 35.57
PR | 995 | 08/07/20 | 98 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 08/07/20 | 105 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 08/07/20 | 106 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 08/07/20 | 107 | Holmes, Anthony R |  | 493.8
PR | 995 | 08/07/20 | 107 | Holmes, Anthony R |  | 251.56
PR | 995 | 08/07/20 | 114 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 08/07/20 | 123 | Sanders, Allen O |  | 811.85
PR | 995 | 08/07/20 | 129 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 08/07/20 | 129 | Gerard, Jeffrey S |  | 85.97
PR | 995 | 08/14/20 | 292 | Ascencio, Jose L |  | 559.02
PR | 995 | 08/14/20 | 294 | Barbosa, Michael S |  | 552.03
PR | 995 | 08/14/20 | 295 | Barnhart, Joseph N |  | 503.12
PR | 995 | 08/14/20 | 295 | Barnhart, Joseph N |  | 68.61
PR | 995 | 08/14/20 | 296 | Boss, Benjamin T |  | 60.98
PR | 995 | 08/14/20 | 310 | Gonzalez Hernandez, Josue |  | 487.87
PR | 995 | 08/14/20 | 310 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 08/14/20 | 311 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 08/14/20 | 312 | Holmes, Anthony R |  | 745.36
PR | 995 | 08/14/20 | 318 | Martinez Reyes, Juan C |  | 564.1
PR | 995 | 08/14/20 | 327 | Sanders, Allen O |  | 297.3
PR | 995 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 85.97
PR | 995 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 08/21/20 | 413 | Ascencio, Jose L |  | 559.02
PR | 995 | 08/21/20 | 415 | Barbosa, Michael S |  | 447.22
PR | 995 | 08/21/20 | 417 | Boss, Benjamin T |  | 60.98
PR | 995 | 08/21/20 | 422 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 08/21/20 | 424 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 08/21/20 | 430 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 08/21/20 | 430 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 08/21/20 | 431 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 08/21/20 | 432 | Holmes, Anthony R |  | 745.36
PR | 995 | 08/21/20 | 438 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 08/21/20 | 447 | Sanders, Allen O |  | 525.99
PR | 995 | 08/21/20 | 459 | Donelson, Richard T |  | 26.47
PR | 995 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 08/28/20 | 561 | Ascencio, Jose L |  | 447.22
PR | 995 | 08/28/20 | 563 | Barbosa, Michael S |  | 559.02
PR | 995 | 08/28/20 | 564 | Barnhart, Joseph N |  | 388.77
PR | 995 | 08/28/20 | 564 | Barnhart, Joseph N |  | 45.74
PR | 995 | 08/28/20 | 565 | Boss, Benjamin T |  | 60.98
PR | 995 | 08/28/20 | 570 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 08/28/20 | 572 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 08/28/20 | 579 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 08/28/20 | 580 | Hernandez Gonzalez, Osbaldo |  | 508.2
PR | 995 | 08/28/20 | 581 | Holmes, Anthony R |  | 298.14
PR | 995 | 08/28/20 | 587 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 08/28/20 | 598 | Sanders, Allen O |  | 45.74
PR | 995 | 08/28/20 | 604 | Donelson, Richard T |  | 52.94
PR | 995 | 08/28/20 | 605 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 09/04/20 | 3 | Anderson, Richard P |  | 498.04
PR | 995 | 09/04/20 | 4 | Ascencio, Jose L |  | 559.02
PR | 995 | 09/04/20 | 6 | Barbosa, Michael S |  | 559.02
PR | 995 | 09/04/20 | 7 | Barnhart, Joseph N |  | 708.94
PR | 995 | 09/04/20 | 7 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/04/20 | 23 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 09/04/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 406.56
PR | 995 | 09/04/20 | 25 | Holmes, Anthony R |  | 745.36
PR | 995 | 09/04/20 | 31 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 09/04/20 | 43 | Sanders, Allen O |  | 182.95
PR | 995 | 09/04/20 | 50 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 09/11/20 | 73 | Anderson, Richard P |  | 415.03
PR | 995 | 09/11/20 | 73 | Anderson, Richard P |  | 249.02
PR | 995 | 09/11/20 | 74 | Ascencio, Jose L |  | 447.22
PR | 995 | 09/11/20 | 76 | Barbosa, Michael S |  | 447.22
PR | 995 | 09/11/20 | 77 | Barnhart, Joseph N |  | 297.3
PR | 995 | 09/11/20 | 77 | Barnhart, Joseph N |  | 45.74
PR | 995 | 09/11/20 | 94 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 09/11/20 | 95 | Holmes, Anthony R |  | 149.07
PR | 995 | 09/11/20 | 101 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 09/11/20 | 113 | Sanders, Allen O |  | 45.74
PR | 995 | 09/11/20 | 119 | Donelson, Richard T |  | 26.47
PR | 995 | 09/18/20 | 284 | Anderson, Richard P |  | 249.02
PR | 995 | 09/18/20 | 284 | Anderson, Richard P |  | 560.29
PR | 995 | 09/18/20 | 284 | Anderson, Richard P |  | 20.75
PR | 995 | 09/18/20 | 285 | Ascencio, Jose L |  | 335.41
PR | 995 | 09/18/20 | 287 | Barbosa, Michael S |  | 111.8
PR | 995 | 09/18/20 | 288 | Barnhart, Joseph N |  | 205.82
PR | 995 | 09/18/20 | 288 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/18/20 | 289 | Boss, Benjamin T |  | 60.98
PR | 995 | 09/18/20 | 295 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 09/18/20 | 297 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 09/18/20 | 304 | Gonzalez Hernandez, Josue |  | 609.84
PR | 995 | 09/18/20 | 305 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 09/18/20 | 306 | Holmes, Anthony R |  | 447.22
PR | 995 | 09/18/20 | 312 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 09/18/20 | 324 | Sanders, Allen O |  | 228.69
PR | 995 | 09/18/20 | 330 | Donelson, Richard T |  | 26.47
PR | 995 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 09/25/20 | 425 | Anderson, Richard P |  | 352.78
PR | 995 | 09/25/20 | 425 | Anderson, Richard P |  | 145.26
PR | 995 | 09/25/20 | 426 | Ascencio, Jose L |  | 307.46
PR | 995 | 09/25/20 | 426 | Ascencio, Jose L |  | 27.95
PR | 995 | 09/25/20 | 429 | Barnhart, Joseph N |  | 594.59
PR | 995 | 09/25/20 | 429 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/25/20 | 429 | Barnhart, Joseph N |  | 22.87
PR | 995 | 09/25/20 | 430 | Boss, Benjamin T |  | 60.98
PR | 995 | 09/25/20 | 436 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 09/25/20 | 446 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 09/25/20 | 446 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 09/25/20 | 447 | Hernandez Gonzalez, Osbaldo |  | 304.92
PR | 995 | 09/25/20 | 448 | Holmes, Anthony R |  | 204.97
PR | 995 | 09/25/20 | 448 | Holmes, Anthony R |  | 242.24
PR | 995 | 09/25/20 | 454 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 09/25/20 | 466 | Sanders, Allen O |  | 274.43
PR | 995 | 09/25/20 | 478 | Donelson, Richard T |  | 26.47
PR | 995 | 09/25/20 | 479 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 10/02/20 | 2 | Anderson, Richard P |  | 207.52
PR | 995 | 10/02/20 | 2 | Anderson, Richard P |  | 155.64
PR | 995 | 10/02/20 | 2 | Anderson, Richard P |  | 83.01
PR | 995 | 10/02/20 | 3 | Ascencio, Jose L |  | 69.88
PR | 995 | 10/02/20 | 3 | Ascencio, Jose L |  | 265.53
PR | 995 | 10/02/20 | 6 | Barnhart, Joseph N |  | 274.43
PR | 995 | 10/02/20 | 6 | Barnhart, Joseph N |  | 91.48
PR | 995 | 10/02/20 | 6 | Barnhart, Joseph N |  | 68.61
PR | 995 | 10/02/20 | 6 | Barnhart, Joseph N |  | 68.61
PR | 995 | 10/02/20 | 7 | Boss, Benjamin T |  | 60.98
PR | 995 | 10/02/20 | 13 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 10/02/20 | 23 | Gonzalez Hernandez, Josue |  | 45.74
PR | 995 | 10/02/20 | 23 | Gonzalez Hernandez, Josue |  | 320.17
PR | 995 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 203.28
PR | 995 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 101.64
PR | 995 | 10/02/20 | 25 | Holmes, Anthony R |  | 298.14
PR | 995 | 10/02/20 | 25 | Holmes, Anthony R |  | 149.07
PR | 995 | 10/02/20 | 28 | Hubbard, Robert W |  | 160.08
PR | 995 | 10/02/20 | 31 | Martinez Reyes, Juan C |  | 47.01
PR | 995 | 10/02/20 | 31 | Martinez Reyes, Juan C |  | 329.06
PR | 995 | 10/02/20 | 43 | Sanders, Allen O |  | 365.9
PR | 995 | 10/02/20 | 51 | Donelson, Richard T |  | 26.47
PR | 995 | 10/02/20 | 52 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 10/09/20 | 151 | Anderson, Richard P |  | 20.75
PR | 995 | 10/09/20 | 151 | Anderson, Richard P |  | 477.28
PR | 995 | 10/09/20 | 155 | Barnhart, Joseph N |  | 182.95
PR | 995 | 10/09/20 | 155 | Barnhart, Joseph N |  | 114.35
PR | 995 | 10/09/20 | 155 | Barnhart, Joseph N |  | 68.61
PR | 995 | 10/09/20 | 156 | Boss, Benjamin T |  | 60.98
PR | 995 | 10/09/20 | 162 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 10/09/20 | 164 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 10/09/20 | 172 | Gonzalez Hernandez, Josue |  | 365.9
PR | 995 | 10/09/20 | 173 | Hernandez Gonzalez, Osbaldo |  | 260.45
PR | 995 | 10/09/20 | 174 | Holmes, Anthony R |  | 326.1
PR | 995 | 10/09/20 | 174 | Holmes, Anthony R |  | 121.12
PR | 995 | 10/09/20 | 180 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 10/09/20 | 191 | Sanders, Allen O |  | 537.42
PR | 995 | 10/09/20 | 198 | Donelson, Richard T |  | 26.47
PR | 995 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 10/16/20 | 293 | Anderson, Richard P |  | 466.91
PR | 995 | 10/16/20 | 293 | Anderson, Richard P |  | 31.13
PR | 995 | 10/16/20 | 297 | Barnhart, Joseph N |  | 114.35
PR | 995 | 10/16/20 | 298 | Boss, Benjamin T |  | 60.98
PR | 995 | 10/16/20 | 314 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 10/16/20 | 316 | Holmes, Anthony R |  | 186.34
PR | 995 | 10/16/20 | 316 | Holmes, Anthony R |  | 111.8
PR | 995 | 10/16/20 | 322 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 10/16/20 | 333 | Sanders, Allen O |  | 480.25
PR | 995 | 10/23/20 | 434 | Anderson, Richard P |  | 498.04
PR | 995 | 10/23/20 | 438 | Barnhart, Joseph N |  | 45.74
PR | 995 | 10/23/20 | 457 | Holmes, Anthony R |  | 298.14
PR | 995 | 10/23/20 | 463 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 10/23/20 | 475 | Sanders, Allen O |  | 308.73
PR | 995 | 10/30/20 | 591 | Anderson, Richard P |  | 498.04
PR | 995 | 10/30/20 | 604 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 10/30/20 | 614 | Holmes, Anthony R |  | 298.14
PR | 995 | 10/30/20 | 619 | Martinez Reyes, Juan C |  | 626.78
PR | 995 | 10/30/20 | 630 | Sanders, Allen O |  | 503.12
PR | 995 | 11/06/20 | 34 | Holmes, Anthony R |  | 745.36
PR | 995 | 11/06/20 | 39 | Martinez Reyes, Juan C |  | 603.28
PR | 995 | 11/06/20 | 50 | Sanders, Allen O |  | 297.3
PR | 995 | 11/13/20 | 208 | Holmes, Anthony R |  | 736.04
PR | 995 | 11/13/20 | 213 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 11/13/20 | 224 | Sanders, Allen O |  | 445.95
PR | 995 | 11/13/20 | 230 | Donelson, Richard T |  | 26.47
PR | 995 | 11/20/20 | 341 | Anderson, Richard P |  | 269.77
PR | 995 | 11/20/20 | 341 | Anderson, Richard P |  | 62.25
PR | 995 | 11/20/20 | 346 | Boss, Benjamin T |  | 304.92
PR | 995 | 11/20/20 | 364 | Holmes, Anthony R |  | 335.41
PR | 995 | 11/20/20 | 364 | Holmes, Anthony R |  | 111.8
PR | 995 | 11/20/20 | 379 | Sanders, Allen O |  | 891.89
PR | 995 | 11/20/20 | 389 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 11/25/20 | 456 | Barnhart, Joseph N |  | 91.48
PR | 995 | 11/25/20 | 457 | Boss, Benjamin T |  | 243.94
PR | 995 | 11/25/20 | 491 | Sanders, Allen O |  | 777.55
PR | 995 | 11/25/20 | 498 | Donelson, Richard T |  | 26.47
PR | 995 | 12/04/20 | 7 | Barnhart, Joseph N |  | 45.74
PR | 995 | 12/04/20 | 8 | Boss, Benjamin T |  | 228.69
PR | 995 | 12/04/20 | 26 | Holmes, Anthony R |  | 298.14
PR | 995 | 12/04/20 | 31 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 12/04/20 | 42 | Sanders, Allen O |  | 686.07
PR | 995 | 12/11/20 | 184 | Boss, Benjamin T |  | 304.92
PR | 995 | 12/11/20 | 202 | Holmes, Anthony R |  | 745.36
PR | 995 | 12/11/20 | 207 | Martinez Reyes, Juan C |  | 611.11
PR | 995 | 12/11/20 | 218 | Sanders, Allen O |  | 743.24
PR | 995 | 12/18/20 | 344 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/18/20 | 345 | Boss, Benjamin T |  | 304.92
PR | 995 | 12/18/20 | 363 | Holmes, Anthony R |  | 745.36
PR | 995 | 12/18/20 | 368 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 12/18/20 | 379 | Sanders, Allen O |  | 846.15
PR | 995 | 12/23/20 | 485 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/23/20 | 485 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/23/20 | 486 | Boss, Benjamin T |  | 102.91
PR | 995 | 12/23/20 | 492 | Cruz Gonzalez, Julio C |  | 94.86
PR | 995 | 12/23/20 | 494 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 12/23/20 | 504 | Holmes, Anthony R |  | 484.48
PR | 995 | 12/23/20 | 504 | Holmes, Anthony R |  | 111.8
PR | 995 | 12/23/20 | 509 | Martinez Reyes, Juan C |  | 407.41
PR | 995 | 12/23/20 | 509 | Martinez Reyes, Juan C |  | 94.02
PR | 995 | 12/23/20 | 520 | Sanders, Allen O |  | 583.16
PR | 995 | 12/31/20 | 585 | Barnhart, Joseph N |  | 22.87
PR | 995 | 12/31/20 | 594 | Cruz Reyes, Jose |  | 108.42
PR | 995 | 12/31/20 | 602 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 12/31/20 | 604 | Holmes, Anthony R |  | 149.07
PR | 995 | 12/31/20 | 604 | Holmes, Anthony R |  | 298.14
PR | 995 | 12/31/20 | 609 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 01/08/21 | 9 | Boss, Benjamin T |  | 60.98
PR | 995 | 01/08/21 | 17 | Cruz Reyes, Jose |  | 325.25
PR | 995 | 01/08/21 | 25 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 01/08/21 | 27 | Holmes, Anthony R |  | 242.24
PR | 995 | 01/08/21 | 27 | Holmes, Anthony R |  | 149.07
PR | 995 | 01/08/21 | 27 | Holmes, Anthony R |  | 204.97
PR | 995 | 01/08/21 | 43 | Sanders, Allen O |  | 365.9
PR | 995 | 01/08/21 | 52 | Donelson, Richard T |  | 26.47
PR | 995 | 01/15/21 | 122 | Boss, Benjamin T |  | 102.91
PR | 995 | 01/15/21 | 141 | Holmes, Anthony R |  | 354.05
PR | 995 | 01/15/21 | 141 | Holmes, Anthony R |  | 288.83
PR | 995 | 01/15/21 | 141 | Holmes, Anthony R |  | 37.27
PR | 995 | 01/15/21 | 146 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 01/15/21 | 157 | Romero Garza, Jesus I |  | 233.77
PR | 995 | 01/15/21 | 159 | Sanders, Allen O |  | 445.95
PR | 995 | 01/22/21 | 270 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 01/22/21 | 280 | Holmes, Anthony R |  | 195.66
PR | 995 | 01/22/21 | 285 | Martinez Reyes, Juan C |  | 282.05
PR | 995 | 01/22/21 | 296 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 01/22/21 | 298 | Sanders, Allen O |  | 445.95
PR | 995 | 01/29/21 | 396 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 01/29/21 | 412 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 01/29/21 | 422 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 01/29/21 | 424 | Sanders, Allen O |  | 537.42
PR | 995 | 02/05/21 | 82 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 02/05/21 | 99 | Martinez Reyes, Juan C |  | 501.42
PR | 995 | 02/05/21 | 110 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 02/05/21 | 112 | Sanders, Allen O |  | 628.9
PR | 995 | 02/12/21 | 265 | Cruz Gonzalez, Julio C |  | 284.59
PR | 995 | 02/12/21 | 267 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 02/12/21 | 285 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 02/12/21 | 296 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 02/12/21 | 298 | Sanders, Allen O |  | 823.28
PR | 995 | 02/19/21 | 420 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/19/21 | 429 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 02/19/21 | 431 | Cruz Reyes, Jose |  | 542.08
PR | 995 | 02/19/21 | 452 | Martinez Reyes, Juan C |  | 611.11
PR | 995 | 02/19/21 | 463 | Romero Garza, Jesus I |  | 311.7
PR | 995 | 02/19/21 | 465 | Sanders, Allen O |  | 697.5
PR | 995 | 02/26/21 | 599 | Boss, Benjamin T |  | 76.23
PR | 995 | 02/26/21 | 599 | Boss, Benjamin T |  | 271.04
PR | 995 | 02/26/21 | 606 | Cruz Gonzalez, Julio C |  | 106.72
PR | 995 | 02/26/21 | 606 | Cruz Gonzalez, Julio C |  | 474.32
PR | 995 | 02/26/21 | 608 | Cruz Reyes, Jose |  | 20.33
PR | 995 | 02/26/21 | 608 | Cruz Reyes, Jose |  | 433.66
PR | 995 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 164.53
PR | 995 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 297.72
PR | 995 | 02/26/21 | 639 | Romero Garza, Jesus I |  | 102.28
PR | 995 | 02/26/21 | 639 | Romero Garza, Jesus I |  | 389.62
PR | 995 | 02/26/21 | 641 | Sanders, Allen O |  | 257.28
PR | 995 | 02/26/21 | 641 | Sanders, Allen O |  | 731.81
PR | 995 | 03/05/21 | 65 | Cruz Gonzalez, Julio C |  | 189.73
PR | 995 | 03/05/21 | 99 | Sanders, Allen O |  | 491.68
PR | 995 | 03/12/21 | 224 | Sanders, Allen O |  | 68.61
PR | 995 | 03/19/21 | 338 | Sanders, Allen O |  | 197.99
PR | 995 | 03/26/21 | 569 | Sanders, Allen O |  | 69.88
PR | 995 | 04/02/21 | 55 | Sanders, Allen O |  | 58.23
PR | 995 | 04/09/21 | 159 | Sanders, Allen O |  | 23.29
PR | 995 | 04/30/21 | 627 | Sanders, Allen O |  | 34.94
PR | 998 | 10/12/18 | 310 | Gerard, Jeffrey S |  | 3.83
PR | 998 | 11/30/18 | 901 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 12/07/18 | 114 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 12/14/18 | 338 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 02/08/19 | 227 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 02/15/19 | 389 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/01/19 | 75 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/08/19 | 315 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 03/15/19 | 562 | Donelson, Richard T |  | 9.56
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 03/15/19 | 563 | Gerard, Jeffrey S |  | 19.89
PR | 998 | 03/22/19 | 776 | Donelson, Richard T |  | 4.78
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/22/19 | 777 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 03/29/19 | 989 | Donelson, Richard T |  | 4.78
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 19.89
PR | 998 | 03/29/19 | 990 | Gerard, Jeffrey S |  | 3.98
PR | 998 | 04/05/19 | 83 | Barnhart, Joseph N |  | 16.52
PR | 998 | 04/05/19 | 83 | Barnhart, Joseph N |  | 55.08
PR | 998 | 04/05/19 | 125 | Paco Leyva, Orlando |  | 10.61
PR | 998 | 04/05/19 | 125 | Paco Leyva, Orlando |  | 70.76
PR | 998 | 04/05/19 | 127 | Ramos Herrera, Franklin J |  | 9.24
PR | 998 | 04/05/19 | 127 | Ramos Herrera, Franklin J |  | 42.23
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 11.93
PR | 998 | 04/05/19 | 152 | Gerard, Jeffrey S |  | 25.86
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 11.48
PR | 998 | 04/12/19 | 327 | Barnhart, Joseph N |  | 65.03
PR | 998 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 6.43
PR | 998 | 04/12/19 | 365 | Martinez Reyes, Juan C |  | 10.71
PR | 998 | 04/12/19 | 369 | Paco Leyva, Orlando |  | 13.77
PR | 998 | 04/12/19 | 369 | Paco Leyva, Orlando |  | 122.4
PR | 998 | 04/12/19 | 371 | Ramos Herrera, Franklin J |  | 7.92
PR | 998 | 04/12/19 | 371 | Ramos Herrera, Franklin J |  | 70.38
PR | 998 | 04/12/19 | 397 | Donelson, Richard T |  | 4.78
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 19.89
PR | 998 | 04/12/19 | 398 | Gerard, Jeffrey S |  | 15.91
PR | 998 | 04/19/19 | 524 | Barnhart, Joseph N |  | 11.48
PR | 998 | 04/19/19 | 524 | Barnhart, Joseph N |  | 122.4
PR | 998 | 04/19/19 | 563 | Martinez Reyes, Juan C |  | 34.27
PR | 998 | 04/19/19 | 567 | Paco Leyva, Orlando |  | 102.51
PR | 998 | 04/19/19 | 569 | Ramos Herrera, Franklin J |  | 3.96
PR | 998 | 04/19/19 | 569 | Ramos Herrera, Franklin J |  | 70.38
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 19.89
PR | 998 | 04/19/19 | 597 | Gerard, Jeffrey S |  | 7.96
PR | 998 | 04/26/19 | 744 | Barnhart, Joseph N |  | 30.6
PR | 998 | 04/26/19 | 786 | Paco Leyva, Orlando |  | 94.86
PR | 998 | 04/26/19 | 788 | Ramos Herrera, Franklin J |  | 61.66
PR | 998 | 04/26/19 | 812 | Donelson, Richard T |  | 4.78
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 04/26/19 | 813 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 05/03/19 | 11 | Barnhart, Joseph N |  | 99.45
PR | 998 | 05/03/19 | 55 | Paco Leyva, Orlando |  | 122.4
PR | 998 | 05/03/19 | 57 | Ramos Herrera, Franklin J |  | 79.56
PR | 998 | 05/03/19 | 81 | Donelson, Richard T |  | 28.69
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 05/03/19 | 82 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 05/10/19 | 164 | Barnhart, Joseph N |  | 11.48
PR | 998 | 05/10/19 | 164 | Barnhart, Joseph N |  | 11.48
PR | 998 | 05/10/19 | 164 | Barnhart, Joseph N |  | 53.55
PR | 998 | 05/10/19 | 164 | Barnhart, Joseph N |  | 26.78
PR | 998 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 4.59
PR | 998 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 9.18
PR | 998 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 116.28
PR | 998 | 05/10/19 | 208 | Paco Leyva, Orlando |  | 6.12
PR | 998 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 2.98
PR | 998 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 5.97
PR | 998 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 75.58
PR | 998 | 05/10/19 | 210 | Ramos Herrera, Franklin J |  | 3.98
PR | 998 | 05/10/19 | 234 | Donelson, Richard T |  | 52.59
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 05/10/19 | 235 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 05/17/19 | 391 | Anderson, Richard P |  | 64.72
PR | 998 | 05/17/19 | 391 | Anderson, Richard P |  | 30.56
PR | 998 | 05/17/19 | 395 | Barnhart, Joseph N |  | 72.68
PR | 998 | 05/17/19 | 395 | Barnhart, Joseph N |  | 26.78
PR | 998 | 05/17/19 | 420 | Gonzalez Hernandez, Josue |  | 51.41
PR | 998 | 05/17/19 | 430 | Kinssies, Jr, John E |  | 17.14
PR | 998 | 05/17/19 | 442 | Ramos Herrera, Franklin J |  | 47.74
PR | 998 | 05/17/19 | 467 | Donelson, Richard T |  | 14.34
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 05/17/19 | 468 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 05/24/19 | 604 | Anderson, Richard P |  | 3.6
PR | 998 | 05/24/19 | 604 | Anderson, Richard P |  | 32.36
PR | 998 | 05/24/19 | 608 | Barnhart, Joseph N |  | 34.43
PR | 998 | 05/24/19 | 632 | Gonzalez Hernandez, Josue |  | 12.24
PR | 998 | 05/24/19 | 632 | Gonzalez Hernandez, Josue |  | 26.93
PR | 998 | 05/24/19 | 648 | Martinez Reyes, Juan C |  | 7.57
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 05/24/19 | 681 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 05/31/19 | 877 | Anderson, Richard P |  | 7.19
PR | 998 | 05/31/19 | 881 | Barnhart, Joseph N |  | 7.65
PR | 998 | 05/31/19 | 881 | Barnhart, Joseph N |  | 61.2
PR | 998 | 05/31/19 | 922 | Martinez Reyes, Juan C |  | 30.29
PR | 998 | 05/31/19 | 953 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 06/07/19 | 179 | Anderson, Richard P |  | 7.19
PR | 998 | 06/07/19 | 183 | Barnhart, Joseph N |  | 53.55
PR | 998 | 06/07/19 | 223 | Martinez Reyes, Juan C |  | 45.44
PR | 998 | 06/07/19 | 254 | Donelson, Richard T |  | 23.91
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 06/07/19 | 255 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 06/14/19 | 450 | Anderson, Richard P |  | 7.19
PR | 998 | 06/14/19 | 454 | Barnhart, Joseph N |  | 22.95
PR | 998 | 06/14/19 | 454 | Barnhart, Joseph N |  | 19.13
PR | 998 | 06/14/19 | 492 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 06/14/19 | 496 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 06/14/19 | 498 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 06/14/19 | 524 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 06/21/19 | 622 | Barnhart, Joseph N |  | 26.78
PR | 998 | 06/21/19 | 622 | Barnhart, Joseph N |  | 38.25
PR | 998 | 06/21/19 | 651 | Holmes, Anthony R |  | 73.44
PR | 998 | 06/21/19 | 663 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 06/21/19 | 663 | Martinez Reyes, Juan C |  | 47.97
PR | 998 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 64.26
PR | 998 | 06/21/19 | 667 | Paco Leyva, Orlando |  | 9.18
PR | 998 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 41.77
PR | 998 | 06/21/19 | 669 | Ramos Herrera, Franklin J |  | 5.97
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 9.56
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 06/21/19 | 694 | Gerard, Jeffrey S |  | 6.31
PR | 998 | 06/28/19 | 840 | Barnhart, Joseph N |  | 53.55
PR | 998 | 06/28/19 | 840 | Barnhart, Joseph N |  | 7.65
PR | 998 | 06/28/19 | 869 | Holmes, Anthony R |  | 24.48
PR | 998 | 06/28/19 | 880 | Martinez Reyes, Juan C |  | 98.46
PR | 998 | 06/28/19 | 880 | Martinez Reyes, Juan C |  | 2.52
PR | 998 | 06/28/19 | 910 | Donelson, Richard T |  | 9.56
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 06/28/19 | 911 | Gerard, Jeffrey S |  | 10.52
PR | 998 | 07/05/19 | 8 | Anderson, Richard P |  | 3.6
PR | 998 | 07/05/19 | 12 | Barnhart, Joseph N |  | 38.25
PR | 998 | 07/05/19 | 12 | Barnhart, Joseph N |  | 11.48
PR | 998 | 07/05/19 | 36 | Gerard, Mitchell J |  | 48.96
PR | 998 | 07/05/19 | 41 | Holmes, Anthony R |  | 122.4
PR | 998 | 07/05/19 | 43 | Hubbard, Justin A |  | 31.82
PR | 998 | 07/05/19 | 52 | Martinez Reyes, Juan C |  | 58.06
PR | 998 | 07/05/19 | 52 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 4.78
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 07/05/19 | 82 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/12/19 | 281 | Barbosa, Michael S |  | 17.75
PR | 998 | 07/12/19 | 282 | Barnhart, Joseph N |  | 7.65
PR | 998 | 07/12/19 | 310 | Holmes, Anthony R |  | 97.92
PR | 998 | 07/12/19 | 312 | Hubbard, Justin A |  | 10.94
PR | 998 | 07/12/19 | 317 | Lima Romero, Melvin A |  | 21.42
PR | 998 | 07/12/19 | 321 | Martinez Reyes, Juan C |  | 47.97
PR | 998 | 07/12/19 | 321 | Martinez Reyes, Juan C |  | 37.87
PR | 998 | 07/12/19 | 325 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 07/12/19 | 327 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 07/12/19 | 352 | Donelson, Richard T |  | 4.78
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/12/19 | 353 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 07/19/19 | 508 | Anderson, Richard P |  | 3.6
PR | 998 | 07/19/19 | 511 | Barbosa, Michael S |  | 35.5
PR | 998 | 07/19/19 | 512 | Barnhart, Joseph N |  | 38.25
PR | 998 | 07/19/19 | 512 | Barnhart, Joseph N |  | 7.65
PR | 998 | 07/19/19 | 536 | Gonzalez Hernandez, Josue |  | 19.58
PR | 998 | 07/19/19 | 540 | Holmes, Anthony R |  | 97.92
PR | 998 | 07/19/19 | 540 | Holmes, Anthony R |  | 24.48
PR | 998 | 07/19/19 | 542 | Hubbard, Justin A |  | 15.91
PR | 998 | 07/19/19 | 547 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 07/19/19 | 551 | Martinez Reyes, Juan C |  | 40.39
PR | 998 | 07/19/19 | 551 | Martinez Reyes, Juan C |  | 35.34
PR | 998 | 07/19/19 | 555 | Paco Leyva, Orlando |  | 79.56
PR | 998 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 2.98
PR | 998 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 47.74
PR | 998 | 07/19/19 | 557 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 07/19/19 | 586 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 07/26/19 | 612 | Anderson, Richard P |  | 14.38
PR | 998 | 07/26/19 | 612 | Anderson, Richard P |  | 46.74
PR | 998 | 07/26/19 | 615 | Barbosa, Michael S |  | 53.24
PR | 998 | 07/26/19 | 615 | Barbosa, Michael S |  | 35.5
PR | 998 | 07/26/19 | 616 | Barnhart, Joseph N |  | 26.78
PR | 998 | 07/26/19 | 616 | Barnhart, Joseph N |  | 19.13
PR | 998 | 07/26/19 | 616 | Barnhart, Joseph N |  | 7.65
PR | 998 | 07/26/19 | 617 | Belcher, Jacob T |  | 36.72
PR | 998 | 07/26/19 | 639 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 07/26/19 | 641 | Hernandez Gonzalez, Osbaldo |  | 47.74
PR | 998 | 07/26/19 | 642 | Hoeg, Xavier A |  | 31.21
PR | 998 | 07/26/19 | 643 | Holmes, Anthony R |  | 122.4
PR | 998 | 07/26/19 | 649 | Lee, Ha Nul |  | 38.56
PR | 998 | 07/26/19 | 650 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 07/26/19 | 654 | Martinez Reyes, Juan C |  | 80.78
PR | 998 | 07/26/19 | 654 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 07/26/19 | 656 | Mendoza Morales, Jesus A |  | 53.24
PR | 998 | 07/26/19 | 658 | Paco Leyva, Orlando |  | 85.68
PR | 998 | 07/26/19 | 658 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 07/26/19 | 660 | Ramos Herrera, Franklin J |  | 63.65
PR | 998 | 07/26/19 | 660 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 07/26/19 | 662 | Reyes Cruz, Denis A |  | 55.08
PR | 998 | 07/26/19 | 668 | Rosas Olivares, Jorge C |  | 34.43
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 23.14
PR | 998 | 07/26/19 | 686 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/02/19 | 4 | Anderson, Richard P |  | 7.19
PR | 998 | 08/02/19 | 4 | Anderson, Richard P |  | 21.57
PR | 998 | 08/02/19 | 7 | Barbosa, Michael S |  | 88.74
PR | 998 | 08/02/19 | 8 | Barnhart, Joseph N |  | 11.48
PR | 998 | 08/02/19 | 8 | Barnhart, Joseph N |  | 15.3
PR | 998 | 08/02/19 | 9 | Belcher, Jacob T |  | 61.2
PR | 998 | 08/02/19 | 31 | Gonzalez Hernandez, Josue |  | 58.75
PR | 998 | 08/02/19 | 33 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 08/02/19 | 34 | Hoeg, Xavier A |  | 52.02
PR | 998 | 08/02/19 | 35 | Holmes, Anthony R |  | 113.22
PR | 998 | 08/02/19 | 41 | Lee, Ha Nul |  | 51.41
PR | 998 | 08/02/19 | 42 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 60.59
PR | 998 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 10.1
PR | 998 | 08/02/19 | 46 | Martinez Reyes, Juan C |  | 10.1
PR | 998 | 08/02/19 | 48 | Mendoza Morales, Jesus A |  | 70.99
PR | 998 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 73.44
PR | 998 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 08/02/19 | 50 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 08/02/19 | 52 | Ramos Herrera, Franklin J |  | 41.77
PR | 998 | 08/02/19 | 52 | Ramos Herrera, Franklin J |  | 5.97
PR | 998 | 08/02/19 | 54 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 08/02/19 | 56 | Rivera, Jorge A |  | 85.68
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/09/19 | 256 | Anderson, Richard P |  | 50.34
PR | 998 | 08/09/19 | 256 | Anderson, Richard P |  | 17.98
PR | 998 | 08/09/19 | 259 | Barbosa, Michael S |  | 88.74
PR | 998 | 08/09/19 | 260 | Barnhart, Joseph N |  | 42.08
PR | 998 | 08/09/19 | 260 | Barnhart, Joseph N |  | 15.3
PR | 998 | 08/09/19 | 261 | Belcher, Jacob T |  | 61.2
PR | 998 | 08/09/19 | 283 | Gerard, Mitchell J |  | 24.48
PR | 998 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo |  | 47.74
PR | 998 | 08/09/19 | 286 | Hernandez Gonzalez, Osbaldo |  | 15.91
PR | 998 | 08/09/19 | 287 | Hoeg, Xavier A |  | 41.62
PR | 998 | 08/09/19 | 288 | Holmes, Anthony R |  | 122.4
PR | 998 | 08/09/19 | 290 | Hubbard, Justin A |  | 31.82
PR | 998 | 08/09/19 | 294 | Lee, Ha Nul |  | 64.26
PR | 998 | 08/09/19 | 295 | Lima Romero, Melvin A |  | 85.68
PR | 998 | 08/09/19 | 299 | Martinez Reyes, Juan C |  | 60.59
PR | 998 | 08/09/19 | 299 | Martinez Reyes, Juan C |  | 40.39
PR | 998 | 08/09/19 | 301 | Mendoza Morales, Jesus A |  | 70.99
PR | 998 | 08/09/19 | 303 | Paco Leyva, Orlando |  | 55.08
PR | 998 | 08/09/19 | 303 | Paco Leyva, Orlando |  | 45.9
PR | 998 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 25.86
PR | 998 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 23.87
PR | 998 | 08/09/19 | 305 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/09/19 | 307 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 08/09/19 | 309 | Rivera, Jorge A |  | 85.68
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/16/19 | 563 | Anderson, Richard P |  | 10.79
PR | 998 | 08/16/19 | 563 | Anderson, Richard P |  | 43.15
PR | 998 | 08/16/19 | 566 | Barbosa, Michael S |  | 53.24
PR | 998 | 08/16/19 | 566 | Barbosa, Michael S |  | 17.75
PR | 998 | 08/16/19 | 566 | Barbosa, Michael S |  | 17.75
PR | 998 | 08/16/19 | 567 | Barnhart, Joseph N |  | 11.48
PR | 998 | 08/16/19 | 567 | Barnhart, Joseph N |  | 7.65
PR | 998 | 08/16/19 | 567 | Barnhart, Joseph N |  | 19.13
PR | 998 | 08/16/19 | 568 | Belcher, Jacob T |  | 61.2
PR | 998 | 08/16/19 | 590 | Gerard, Mitchell J |  | 12.24
PR | 998 | 08/16/19 | 590 | Gerard, Mitchell J |  | 12.24
PR | 998 | 08/16/19 | 591 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo |  | 47.74
PR | 998 | 08/16/19 | 593 | Hernandez Gonzalez, Osbaldo |  | 31.82
PR | 998 | 08/16/19 | 594 | Hoeg, Xavier A |  | 52.02
PR | 998 | 08/16/19 | 595 | Holmes, Anthony R |  | 122.4
PR | 998 | 08/16/19 | 597 | Hubbard, Justin A |  | 73.59
PR | 998 | 08/16/19 | 601 | Lee, Ha Nul |  | 64.26
PR | 998 | 08/16/19 | 602 | Lima Romero, Melvin A |  | 64.26
PR | 998 | 08/16/19 | 602 | Lima Romero, Melvin A |  | 42.84
PR | 998 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 60.59
PR | 998 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/16/19 | 608 | Mendoza Morales, Jesus A |  | 88.74
PR | 998 | 08/16/19 | 610 | Paco Leyva, Orlando |  | 85.68
PR | 998 | 08/16/19 | 610 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 08/16/19 | 612 | Ramos Herrera, Franklin J |  | 53.7
PR | 998 | 08/16/19 | 612 | Ramos Herrera, Franklin J |  | 9.95
PR | 998 | 08/16/19 | 614 | Reyes Cruz, Denis A |  | 73.44
PR | 998 | 08/16/19 | 616 | Rivera, Jorge A |  | 107.1
PR | 998 | 08/16/19 | 621 | Sanders, Allen O |  | 7.5
PR | 998 | 08/16/19 | 636 | Donelson, Richard T |  | 4.78
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/23/19 | 799 | Anderson, Richard P |  | 14.38
PR | 998 | 08/23/19 | 799 | Anderson, Richard P |  | 75.51
PR | 998 | 08/23/19 | 799 | Anderson, Richard P |  | 3.6
PR | 998 | 08/23/19 | 799 | Anderson, Richard P |  | 3.6
PR | 998 | 08/23/19 | 802 | Barbosa, Michael S |  | 35.5
PR | 998 | 08/23/19 | 802 | Barbosa, Michael S |  | 17.75
PR | 998 | 08/23/19 | 804 | Belcher, Jacob T |  | 61.2
PR | 998 | 08/23/19 | 827 | Gonzalez Hernandez, Josue |  | 85.68
PR | 998 | 08/23/19 | 829 | Gutierrez Salas, Jose |  | 21.8
PR | 998 | 08/23/19 | 830 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 08/23/19 | 831 | Hoeg, Xavier A |  | 52.02
PR | 998 | 08/23/19 | 832 | Holmes, Anthony R |  | 122.4
PR | 998 | 08/23/19 | 834 | Hubbard, Justin A |  | 79.56
PR | 998 | 08/23/19 | 838 | Lee, Ha Nul |  | 64.26
PR | 998 | 08/23/19 | 839 | Lima Romero, Melvin A |  | 85.68
PR | 998 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/23/19 | 845 | Mendoza Morales, Jesus A |  | 88.74
PR | 998 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/23/19 | 851 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 08/23/19 | 853 | Rivera, Jorge A |  | 107.1
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/30/19 | 989 | Amaya Gonzalez, Edilberto A |  | 19.58
PR | 998 | 08/30/19 | 990 | Anderson, Richard P |  | 57.53
PR | 998 | 08/30/19 | 993 | Barbosa, Michael S |  | 88.74
PR | 998 | 08/30/19 | 994 | Barnhart, Joseph N |  | 68.85
PR | 998 | 08/30/19 | 995 | Belcher, Jacob T |  | 61.2
PR | 998 | 08/30/19 | 1017 | Gerard, Mitchell J |  | 48.96
PR | 998 | 08/30/19 | 1018 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 08/30/19 | 1020 | Gutierrez Salas, Jose |  | 46.51
PR | 998 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo |  | 47.74
PR | 998 | 08/30/19 | 1021 | Hernandez Gonzalez, Osbaldo |  | 31.82
PR | 998 | 08/30/19 | 1022 | Hoeg, Xavier A |  | 52.02
PR | 998 | 08/30/19 | 1023 | Holmes, Anthony R |  | 73.44
PR | 998 | 08/30/19 | 1025 | Hubbard, Justin A |  | 63.65
PR | 998 | 08/30/19 | 1029 | Lee, Ha Nul |  | 64.26
PR | 998 | 08/30/19 | 1030 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 40.39
PR | 998 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/30/19 | 1036 | Mendoza Morales, Jesus A |  | 86.52
PR | 998 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 15.3
PR | 998 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 33.66
PR | 998 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 47.74
PR | 998 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/30/19 | 1042 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 08/30/19 | 1044 | Rivera, Jorge A |  | 103.08
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 9.56
PR | 998 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 4.21
PR | 998 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A |  | 19.58
PR | 998 | 09/06/19 | 10 | Amaya Gonzalez, Edilberto A |  | 58.75
PR | 998 | 09/06/19 | 11 | Anderson, Richard P |  | 57.53
PR | 998 | 09/06/19 | 14 | Barbosa, Michael S |  | 70.99
PR | 998 | 09/06/19 | 15 | Barnhart, Joseph N |  | 42.08
PR | 998 | 09/06/19 | 16 | Belcher, Jacob T |  | 12.24
PR | 998 | 09/06/19 | 16 | Belcher, Jacob T |  | 36.72
PR | 998 | 09/06/19 | 39 | Gonzalez Hernandez, Josue |  | 78.34
PR | 998 | 09/06/19 | 41 | Gutierrez Salas, Jose |  | 23.26
PR | 998 | 09/06/19 | 42 | Hernandez Gonzalez, Osbaldo |  | 61.66
PR | 998 | 09/06/19 | 43 | Hoeg, Xavier A |  | 20.81
PR | 998 | 09/06/19 | 43 | Hoeg, Xavier A |  | 20.81
PR | 998 | 09/06/19 | 44 | Holmes, Anthony R |  | 97.92
PR | 998 | 09/06/19 | 50 | Lee, Ha Nul |  | 51.41
PR | 998 | 09/06/19 | 51 | Lima Romero, Melvin A |  | 64.26
PR | 998 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 09/06/19 | 57 | Mendoza Morales, Jesus A |  | 70.99
PR | 998 | 09/06/19 | 59 | Paco Leyva, Orlando |  | 67.32
PR | 998 | 09/06/19 | 59 | Paco Leyva, Orlando |  | 6.12
PR | 998 | 09/06/19 | 61 | Ramos Herrera, Franklin J |  | 63.65
PR | 998 | 09/06/19 | 63 | Reyes Cruz, Denis A |  | 73.44
PR | 998 | 09/06/19 | 65 | Rivera, Jorge A |  | 77.65
PR | 998 | 09/06/19 | 68 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 09/06/19 | 70 | Sanders, Allen O |  | 11.25
PR | 998 | 09/06/19 | 85 | Donelson, Richard T |  | 4.78
PR | 998 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 10.52
PR | 998 | 09/13/19 | 234 | Amaya Gonzalez, Edilberto A |  | 93.02
PR | 998 | 09/13/19 | 235 | Anderson, Richard P |  | 143.82
PR | 998 | 09/13/19 | 238 | Barbosa, Michael S |  | 70.99
PR | 998 | 09/13/19 | 239 | Barnhart, Joseph N |  | 7.65
PR | 998 | 09/13/19 | 239 | Barnhart, Joseph N |  | 3.83
PR | 998 | 09/13/19 | 240 | Belcher, Jacob T |  | 24.48
PR | 998 | 09/13/19 | 240 | Belcher, Jacob T |  | 36.72
PR | 998 | 09/13/19 | 263 | Gonzalez Hernandez, Josue |  | 78.34
PR | 998 | 09/13/19 | 265 | Gutierrez Salas, Jose |  | 58.14
PR | 998 | 09/13/19 | 266 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 09/13/19 | 267 | Hoeg, Xavier A |  | 52.02
PR | 998 | 09/13/19 | 268 | Holmes, Anthony R |  | 122.4
PR | 998 | 09/13/19 | 273 | Lee, Ha Nul |  | 64.26
PR | 998 | 09/13/19 | 274 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 09/13/19 | 278 | Martinez Reyes, Juan C |  | 58.06
PR | 998 | 09/13/19 | 280 | Mendoza Morales, Jesus A |  | 88.74
PR | 998 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 70.38
PR | 998 | 09/13/19 | 284 | Ramos Herrera, Franklin J |  | 43.76
PR | 998 | 09/13/19 | 286 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 09/13/19 | 288 | Rivera, Jorge A |  | 107.1
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 09/20/19 | 471 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 09/20/19 | 472 | Anderson, Richard P |  | 115.06
PR | 998 | 09/20/19 | 475 | Barbosa, Michael S |  | 70.99
PR | 998 | 09/20/19 | 476 | Barnhart, Joseph N |  | 3.83
PR | 998 | 09/20/19 | 476 | Barnhart, Joseph N |  | 45.9
PR | 998 | 09/20/19 | 477 | Belcher, Jacob T |  | 61.2
PR | 998 | 09/20/19 | 482 | Chevez, Herson G |  | 28.15
PR | 998 | 09/20/19 | 482 | Chevez, Herson G |  | 42.23
PR | 998 | 09/20/19 | 495 | Galdamez, Dagoberto A |  | 36.72
PR | 998 | 09/20/19 | 495 | Galdamez, Dagoberto A |  | 55.08
PR | 998 | 09/20/19 | 500 | Gonzalez Hernandez, Josue |  | 90.58
PR | 998 | 09/20/19 | 503 | Gutierrez Salas, Jose |  | 58.14
PR | 998 | 09/20/19 | 504 | Hernandez Gonzalez, Osbaldo |  | 77.57
PR | 998 | 09/20/19 | 505 | Hoeg, Xavier A |  | 35.11
PR | 998 | 09/20/19 | 505 | Hoeg, Xavier A |  | 16.91
PR | 998 | 09/20/19 | 506 | Holmes, Anthony R |  | 122.4
PR | 998 | 09/20/19 | 511 | Lee, Ha Nul |  | 64.26
PR | 998 | 09/20/19 | 512 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 09/20/19 | 514 | Lovo, German G |  | 38.21
PR | 998 | 09/20/19 | 514 | Lovo, German G |  | 33.05
PR | 998 | 09/20/19 | 516 | Martinez Reyes, Juan C |  | 100.98
PR | 998 | 09/20/19 | 518 | Mendoza Morales, Jesus A |  | 82.08
PR | 998 | 09/20/19 | 520 | Paco Leyva, Orlando |  | 85.68
PR | 998 | 09/20/19 | 520 | Paco Leyva, Orlando |  | 27.54
PR | 998 | 09/20/19 | 522 | Ramos Herrera, Franklin J |  | 63.65
PR | 998 | 09/20/19 | 522 | Ramos Herrera, Franklin J |  | 9.95
PR | 998 | 09/20/19 | 524 | Reyes Cruz, Denis A |  | 71.15
PR | 998 | 09/20/19 | 526 | Rivera, Jorge A |  | 107.1
PR | 998 | 09/20/19 | 529 | Romero Garza, Jesus I |  | 11.02
PR | 998 | 09/20/19 | 546 | Donelson, Richard T |  | 9.56
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/27/19 | 627 | Amaya Gonzalez, Edilberto A |  | 97.92
PR | 998 | 09/27/19 | 628 | Anderson, Richard P |  | 57.53
PR | 998 | 09/27/19 | 631 | Barbosa, Michael S |  | 88.74
PR | 998 | 09/27/19 | 632 | Barnhart, Joseph N |  | 11.48
PR | 998 | 09/27/19 | 633 | Belcher, Jacob T |  | 61.2
PR | 998 | 09/27/19 | 638 | Chevez, Herson G |  | 56.3
PR | 998 | 09/27/19 | 638 | Chevez, Herson G |  | 14.08
PR | 998 | 09/27/19 | 651 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 09/27/19 | 656 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 09/27/19 | 659 | Guillen, Adrian |  | 31.21
PR | 998 | 09/27/19 | 660 | Gutierrez Salas, Jose |  | 46.51
PR | 998 | 09/27/19 | 661 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 09/27/19 | 662 | Hoeg, Xavier A |  | 41.62
PR | 998 | 09/27/19 | 662 | Hoeg, Xavier A |  | 10.4
PR | 998 | 09/27/19 | 663 | Holmes, Anthony R |  | 110.16
PR | 998 | 09/27/19 | 663 | Holmes, Anthony R |  | 12.24
PR | 998 | 09/27/19 | 670 | Lee, Ha Nul |  | 64.26
PR | 998 | 09/27/19 | 671 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 09/27/19 | 673 | Lovo, German G |  | 82.62
PR | 998 | 09/27/19 | 675 | Martinez Reyes, Juan C |  | 100.98
PR | 998 | 09/27/19 | 677 | Mendoza Morales, Jesus A |  | 70.99
PR | 998 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 15.3
PR | 998 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 33.66
PR | 998 | 09/27/19 | 681 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 09/27/19 | 683 | Reyes Cruz, Denis A |  | 91.8
PR | 998 | 09/27/19 | 685 | Rivera, Jorge A |  | 107.1
PR | 998 | 09/27/19 | 690 | Sanders, Allen O |  | 7.5
PR | 998 | 09/27/19 | 705 | Donelson, Richard T |  | 4.78
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A |  | 68.54
PR | 998 | 10/04/19 | 3 | Amaya Gonzalez, Edilberto A |  | 29.38
PR | 998 | 10/04/19 | 4 | Anderson, Richard P |  | 133.03
PR | 998 | 10/04/19 | 7 | Barbosa, Michael S |  | 87.63
PR | 998 | 10/04/19 | 8 | Barnhart, Joseph N |  | 11.48
PR | 998 | 10/04/19 | 9 | Belcher, Jacob T |  | 61.2
PR | 998 | 10/04/19 | 14 | Chevez, Herson G |  | 70.38
PR | 998 | 10/04/19 | 27 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 10/04/19 | 32 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 10/04/19 | 34 | Guillen, Adrian |  | 3.9
PR | 998 | 10/04/19 | 35 | Gutierrez Salas, Jose |  | 57.41
PR | 998 | 10/04/19 | 36 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 10/04/19 | 37 | Hoeg, Xavier A |  | 41.62
PR | 998 | 10/04/19 | 37 | Hoeg, Xavier A |  | 10.4
PR | 998 | 10/04/19 | 38 | Holmes, Anthony R |  | 122.4
PR | 998 | 10/04/19 | 45 | Lee, Ha Nul |  | 51.41
PR | 998 | 10/04/19 | 46 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 10/04/19 | 48 | Lovo, German G |  | 82.62
PR | 998 | 10/04/19 | 51 | Martinez Reyes, Juan C |  | 100.98
PR | 998 | 10/04/19 | 53 | Mendoza Morales, Jesus A |  | 88.74
PR | 998 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 27.54
PR | 998 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 12.24
PR | 998 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 9.95
PR | 998 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 10/04/19 | 59 | Reyes Cruz, Denis A |  | 55.08
PR | 998 | 10/04/19 | 61 | Rivera, Jorge A |  | 105.76
PR | 998 | 10/04/19 | 75 | Velasquez Cruz, Denis M |  | 19.58
PR | 998 | 10/04/19 | 76 | Velasquez Cruz, Osman N |  | 15.3
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 10/04/19 | 94 | Guillen, Adrian |  | 10.4
PR | 998 | 10/04/19 | 95 | Guillen, Adrian |  | -10.4
PR | 998 | 10/11/19 | 96 | Guillen, Adrian |  | 10.4
PR | 998 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 10/11/19 | 258 | Amaya Gonzalez, Edilberto A |  | 39.17
PR | 998 | 10/11/19 | 259 | Anderson, Richard P |  | 115.06
PR | 998 | 10/11/19 | 262 | Barbosa, Michael S |  | 88.74
PR | 998 | 10/11/19 | 263 | Barnhart, Joseph N |  | 5.74
PR | 998 | 10/11/19 | 263 | Barnhart, Joseph N |  | 3.83
PR | 998 | 10/11/19 | 264 | Belcher, Jacob T |  | 48.96
PR | 998 | 10/11/19 | 269 | Chevez, Herson G |  | 70.38
PR | 998 | 10/11/19 | 282 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 10/11/19 | 287 | Gonzalez Hernandez, Josue |  | 78.34
PR | 998 | 10/11/19 | 289 | Guillen, Adrian |  | 19.51
PR | 998 | 10/11/19 | 290 | Gutierrez Salas, Jose |  | 55.23
PR | 998 | 10/11/19 | 291 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 10/11/19 | 292 | Hoeg, Xavier A |  | 31.21
PR | 998 | 10/11/19 | 292 | Hoeg, Xavier A |  | 20.81
PR | 998 | 10/11/19 | 293 | Holmes, Anthony R |  | 122.4
PR | 998 | 10/11/19 | 300 | Lee, Ha Nul |  | 64.26
PR | 998 | 10/11/19 | 301 | Lima Romero, Melvin A |  | 107.1
PR | 998 | 10/11/19 | 303 | Lovo, German G |  | 82.62
PR | 998 | 10/11/19 | 306 | Martinez Reyes, Juan C |  | 95.93
PR | 998 | 10/11/19 | 308 | Mendoza Morales, Jesus A |  | 88.74
PR | 998 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 36.72
PR | 998 | 10/11/19 | 309 | Paco Leyva, Orlando |  | 79.56
PR | 998 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 23.87
PR | 998 | 10/11/19 | 311 | Ramos Herrera, Franklin J |  | 35.8
PR | 998 | 10/11/19 | 313 | Reyes Cruz, Denis A |  | 55.08
PR | 998 | 10/11/19 | 313 | Reyes Cruz, Denis A |  | 36.72
PR | 998 | 10/11/19 | 315 | Rivera, Jorge A |  | 107.1
PR | 998 | 10/11/19 | 319 | Rosas Olivares, Jorge C |  | 45.9
PR | 998 | 10/11/19 | 319 | Rosas Olivares, Jorge C |  | 15.3
PR | 998 | 10/11/19 | 321 | Sanders, Allen O |  | 3.75
PR | 998 | 10/11/19 | 329 | Velasquez Cruz, Denis M |  | 63.65
PR | 998 | 10/11/19 | 329 | Velasquez Cruz, Denis M |  | 34.27
PR | 998 | 10/11/19 | 330 | Velasquez Cruz, Osman N |  | 49.73
PR | 998 | 10/11/19 | 330 | Velasquez Cruz, Osman N |  | 26.78
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A |  | 44.06
PR | 998 | 10/18/19 | 452 | Amaya Gonzalez, Edilberto A |  | 53.86
PR | 998 | 10/18/19 | 453 | Anderson, Richard P |  | 143.82
PR | 998 | 10/18/19 | 456 | Barbosa, Michael S |  | 70.99
PR | 998 | 10/18/19 | 456 | Barbosa, Michael S |  | 17.75
PR | 998 | 10/18/19 | 457 | Barnhart, Joseph N |  | 34.43
PR | 998 | 10/18/19 | 457 | Barnhart, Joseph N |  | 7.65
PR | 998 | 10/18/19 | 458 | Belcher, Jacob T |  | 61.2
PR | 998 | 10/18/19 | 459 | Benites Portillo, Marvin E |  | 66.1
PR | 998 | 10/18/19 | 463 | Chevez, Herson G |  | 70.38
PR | 998 | 10/18/19 | 475 | Galdamez, Dagoberto A |  | 91.8
PR | 998 | 10/18/19 | 480 | Gonzalez Hernandez, Josue |  | 97.92
PR | 998 | 10/18/19 | 482 | Guillen, Adrian |  | 49.42
PR | 998 | 10/18/19 | 483 | Gutierrez Salas, Jose |  | 43.61
PR | 998 | 10/18/19 | 484 | Hernandez Gonzalez, Osbaldo |  | 79.56
PR | 998 | 10/18/19 | 485 | Hoeg, Xavier A |  | 31.21
PR | 998 | 10/18/19 | 485 | Hoeg, Xavier A |  | 10.4
PR | 998 | 10/18/19 | 486 | Holmes, Anthony R |  | 122.4
PR | 998 | 10/18/19 | 493 | Lee, Ha Nul |  | 64.26
PR | 998 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 64.26
PR | 998 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 21.42
PR | 998 | 10/18/19 | 494 | Lima Romero, Melvin A |  | 21.42
PR | 998 | 10/18/19 | 496 | Lovo, German G |  | 66.1
PR | 998 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 60.59
PR | 998 | 10/18/19 | 501 | Mendoza Morales, Jesus A |  | 82.08
PR | 998 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 21.42
PR | 998 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 18.36
PR | 998 | 10/18/19 | 502 | Paco Leyva, Orlando |  | 58.14
PR | 998 | 10/18/19 | 504 | Ramos Herrera, Franklin J |  | 47.74
PR | 998 | 10/18/19 | 504 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 10/18/19 | 506 | Reyes Cruz, Denis A |  | 64.26
PR | 998 | 10/18/19 | 506 | Reyes Cruz, Denis A |  | 27.54
PR | 998 | 10/18/19 | 508 | Rivera, Jorge A |  | 77.65
PR | 998 | 10/18/19 | 512 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 10/18/19 | 517 | Stahlschmidt, John P |  | 11.63
PR | 998 | 10/18/19 | 522 | Velasquez Cruz, Denis M |  | 97.92
PR | 998 | 10/18/19 | 523 | Velasquez Cruz, Osman N |  | 76.5
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 10/18/19 | 528 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 10/25/19 | 587 | Amaya Gonzalez, Edilberto A |  | 88.13
PR | 998 | 10/25/19 | 588 | Anderson, Richard P |  | 104.27
PR | 998 | 10/25/19 | 591 | Barbosa, Michael S |  | 78.76
PR | 998 | 10/25/19 | 592 | Barnhart, Joseph N |  | 30.6
PR | 998 | 10/25/19 | 593 | Belcher, Jacob T |  | 55.08
PR | 998 | 10/25/19 | 594 | Benites Portillo, Marvin E |  | 33.05
PR | 998 | 10/25/19 | 599 | Chevez, Herson G |  | 63.34
PR | 998 | 10/25/19 | 610 | Galdamez, Dagoberto A |  | 64.26
PR | 998 | 10/25/19 | 615 | Gonzalez Hernandez, Josue |  | 75.89
PR | 998 | 10/25/19 | 617 | Guillen, Adrian |  | 15.61
PR | 998 | 10/25/19 | 618 | Gutierrez Salas, Jose |  | 23.26
PR | 998 | 10/25/19 | 618 | Gutierrez Salas, Jose |  | 29.07
PR | 998 | 10/25/19 | 619 | Hernandez Gonzalez, Osbaldo |  | 71.6
PR | 998 | 10/25/19 | 620 | Hoeg, Xavier A |  | 36.41
PR | 998 | 10/25/19 | 620 | Hoeg, Xavier A |  | 10.4
PR | 998 | 10/25/19 | 621 | Holmes, Anthony R |  | 85.68
PR | 998 | 10/25/19 | 621 | Holmes, Anthony R |  | 24.48
PR | 998 | 10/25/19 | 628 | Lee, Ha Nul |  | 57.83
PR | 998 | 10/25/19 | 629 | Lima Romero, Melvin A |  | 96.39
PR | 998 | 10/25/19 | 631 | Lovo, German G |  | 33.05
PR | 998 | 10/25/19 | 631 | Lovo, German G |  | 41.31
PR | 998 | 10/25/19 | 634 | Martinez Reyes, Juan C |  | 73.21
PR | 998 | 10/25/19 | 636 | Mendoza Morales, Jesus A |  | 62.12
PR | 998 | 10/25/19 | 638 | Paco Leyva, Orlando |  | 88.74
PR | 998 | 10/25/19 | 638 | Paco Leyva, Orlando |  | 21.42
PR | 998 | 10/25/19 | 640 | Ramos Herrera, Franklin J |  | 71.6
PR | 998 | 10/25/19 | 642 | Reyes Cruz, Denis A |  | 55.08
PR | 998 | 10/25/19 | 642 | Reyes Cruz, Denis A |  | 27.54
PR | 998 | 10/25/19 | 644 | Rivera, Jorge A |  | 96.39
PR | 998 | 10/25/19 | 648 | Rosas Olivares, Jorge C |  | 41.31
PR | 998 | 10/25/19 | 653 | Stahlschmidt, John P |  | 46.51
PR | 998 | 10/25/19 | 658 | Velasquez Cruz, Denis M |  | 88.13
PR | 998 | 10/25/19 | 659 | Velasquez Cruz, Osman N |  | 68.85
PR | 998 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 25.25
PR | 998 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A |  | 101.9
PR | 998 | 11/01/19 | 3 | Amaya Gonzalez, Edilberto A |  | 8.26
PR | 998 | 11/01/19 | 4 | Anderson, Richard P |  | 82.47
PR | 998 | 11/01/19 | 4 | Anderson, Richard P |  | 37.49
PR | 998 | 11/01/19 | 7 | Barbosa, Michael S |  | 58.06
PR | 998 | 11/01/19 | 7 | Barbosa, Michael S |  | 40.39
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 4.13
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 20.66
PR | 998 | 11/01/19 | 9 | Belcher, Jacob T |  | 64.26
PR | 998 | 11/01/19 | 10 | Benites Portillo, Marvin E |  | 70.99
PR | 998 | 11/01/19 | 14 | Chevez, Herson G |  | 79.56
PR | 998 | 11/01/19 | 26 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 11/01/19 | 31 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 11/01/19 | 33 | Guillen, Adrian |  | 41.62
PR | 998 | 11/01/19 | 34 | Gutierrez Salas, Jose |  | 46.51
PR | 998 | 11/01/19 | 34 | Gutierrez Salas, Jose |  | 11.63
PR | 998 | 11/01/19 | 35 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 11/01/19 | 36 | Hoeg, Xavier A |  | 35.8
PR | 998 | 11/01/19 | 36 | Hoeg, Xavier A |  | 19.28
PR | 998 | 11/01/19 | 37 | Holmes, Anthony R |  | 74.05
PR | 998 | 11/01/19 | 37 | Holmes, Anthony R |  | 60.59
PR | 998 | 11/01/19 | 44 | Lee, Ha Nul |  | 30.6
PR | 998 | 11/01/19 | 44 | Lee, Ha Nul |  | 15.3
PR | 998 | 11/01/19 | 44 | Lee, Ha Nul |  | 30.6
PR | 998 | 11/01/19 | 45 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 11/01/19 | 47 | Lovo, German G |  | 91.8
PR | 998 | 11/01/19 | 50 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 11/01/19 | 52 | Mendoza Morales, Jesus A |  | 93.02
PR | 998 | 11/01/19 | 52 | Mendoza Morales, Jesus A |  | 4.9
PR | 998 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 16.83
PR | 998 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 57.22
PR | 998 | 11/01/19 | 54 | Paco Leyva, Orlando |  | 13.46
PR | 998 | 11/01/19 | 56 | Ramos Herrera, Franklin J |  | 73.44
PR | 998 | 11/01/19 | 56 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 11/01/19 | 58 | Reyes Cruz, Denis A |  | 73.21
PR | 998 | 11/01/19 | 60 | Rivera, Jorge A |  | 116.28
PR | 998 | 11/01/19 | 64 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 11/01/19 | 66 | Sanders, Allen O |  | 18.59
PR | 998 | 11/01/19 | 69 | Stahlschmidt, John P |  | 67.32
PR | 998 | 11/01/19 | 74 | Velasquez Cruz, Denis M |  | 85.68
PR | 998 | 11/01/19 | 74 | Velasquez Cruz, Denis M |  | 21.42
PR | 998 | 11/01/19 | 75 | Velasquez Cruz, Osman N |  | 68.54
PR | 998 | 11/01/19 | 75 | Velasquez Cruz, Osman N |  | 17.14
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 33.05
PR | 998 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 38.56
PR | 998 | 11/08/19 | 177 | Amaya Gonzalez, Edilberto A |  | 71.6
PR | 998 | 11/08/19 | 178 | Anderson, Richard P |  | 37.49
PR | 998 | 11/08/19 | 178 | Anderson, Richard P |  | 93.71
PR | 998 | 11/08/19 | 178 | Anderson, Richard P |  | 3.75
PR | 998 | 11/08/19 | 181 | Barbosa, Michael S |  | 100.98
PR | 998 | 11/08/19 | 182 | Barnhart, Joseph N |  | 30.98
PR | 998 | 11/08/19 | 182 | Barnhart, Joseph N |  | 49.57
PR | 998 | 11/08/19 | 183 | Belcher, Jacob T |  | 48.2
PR | 998 | 11/08/19 | 183 | Belcher, Jacob T |  | 16.07
PR | 998 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 26.62
PR | 998 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 17.75
PR | 998 | 11/08/19 | 184 | Benites Portillo, Marvin E |  | 70.99
PR | 998 | 11/08/19 | 188 | Chevez, Herson G |  | 23.87
PR | 998 | 11/08/19 | 188 | Chevez, Herson G |  | 3.98
PR | 998 | 11/08/19 | 188 | Chevez, Herson G |  | 75.58
PR | 998 | 11/08/19 | 200 | Galdamez, Dagoberto A |  | 5.05
PR | 998 | 11/08/19 | 205 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 11/08/19 | 205 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 11/08/19 | 207 | Guillen, Adrian |  | 20.81
PR | 998 | 11/08/19 | 208 | Gutierrez Salas, Jose |  | 33.43
PR | 998 | 11/08/19 | 208 | Gutierrez Salas, Jose |  | 23.26
PR | 998 | 11/08/19 | 209 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 11/08/19 | 210 | Hoeg, Xavier A |  | 44.06
PR | 998 | 11/08/19 | 210 | Hoeg, Xavier A |  | 2.75
PR | 998 | 11/08/19 | 210 | Hoeg, Xavier A |  | 8.26
PR | 998 | 11/08/19 | 218 | Lee, Ha Nul |  | 22.95
PR | 998 | 11/08/19 | 218 | Lee, Ha Nul |  | 57.38
PR | 998 | 11/08/19 | 218 | Lee, Ha Nul |  | 19.13
PR | 998 | 11/08/19 | 219 | Lima Romero, Melvin A |  | 113.37
PR | 998 | 11/08/19 | 221 | Lovo, German G |  | 52.79
PR | 998 | 11/08/19 | 221 | Lovo, German G |  | 18.36
PR | 998 | 11/08/19 | 224 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 11/08/19 | 226 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 11/08/19 | 226 | Mendoza Morales, Jesus A |  | 39.17
PR | 998 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 45.44
PR | 998 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 60.59
PR | 998 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 16.83
PR | 998 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 3.37
PR | 998 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 30.98
PR | 998 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 41.31
PR | 998 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 13.77
PR | 998 | 11/08/19 | 232 | Reyes Cruz, Denis A |  | 80.78
PR | 998 | 11/08/19 | 234 | Rivera, Jorge A |  | 93.02
PR | 998 | 11/08/19 | 238 | Rosas Olivares, Jorge C |  | 61.2
PR | 998 | 11/08/19 | 243 | Stahlschmidt, John P |  | 48.81
PR | 998 | 11/08/19 | 243 | Stahlschmidt, John P |  | 13.46
PR | 998 | 11/08/19 | 248 | Velasquez Cruz, Denis M |  | 107.1
PR | 998 | 11/08/19 | 249 | Velasquez Cruz, Osman N |  | 85.68
PR | 998 | 11/08/19 | 253 | Donelson, Richard T |  | 4.78
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 11/15/19 | 437 | Amaya Gonzalez, Edilberto A |  | 110.16
PR | 998 | 11/15/19 | 438 | Anderson, Richard P |  | 112.46
PR | 998 | 11/15/19 | 438 | Anderson, Richard P |  | 3.75
PR | 998 | 11/15/19 | 441 | Barbosa, Michael S |  | 80.78
PR | 998 | 11/15/19 | 441 | Barbosa, Michael S |  | 20.2
PR | 998 | 11/15/19 | 442 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/15/19 | 443 | Belcher, Jacob T |  | 51.41
PR | 998 | 11/15/19 | 443 | Belcher, Jacob T |  | 12.85
PR | 998 | 11/15/19 | 444 | Benites Portillo, Marvin E |  | 79.87
PR | 998 | 11/15/19 | 444 | Benites Portillo, Marvin E |  | 8.87
PR | 998 | 11/15/19 | 448 | Chevez, Herson G |  | 78.57
PR | 998 | 11/15/19 | 460 | Galdamez, Dagoberto A |  | 90.88
PR | 998 | 11/15/19 | 460 | Galdamez, Dagoberto A |  | 10.1
PR | 998 | 11/15/19 | 465 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 11/15/19 | 467 | Gutierrez Salas, Jose |  | 34.88
PR | 998 | 11/15/19 | 467 | Gutierrez Salas, Jose |  | 10.17
PR | 998 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 11/15/19 | 468 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 11/15/19 | 469 | Hoeg, Xavier A |  | 52.33
PR | 998 | 11/15/19 | 469 | Hoeg, Xavier A |  | 2.75
PR | 998 | 11/15/19 | 470 | Holmes, Anthony R |  | 13.46
PR | 998 | 11/15/19 | 470 | Holmes, Anthony R |  | 121.18
PR | 998 | 11/15/19 | 477 | Lee, Ha Nul |  | 61.2
PR | 998 | 11/15/19 | 477 | Lee, Ha Nul |  | 15.3
PR | 998 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 23.26
PR | 998 | 11/15/19 | 478 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 11/15/19 | 480 | Lovo, German G |  | 18.36
PR | 998 | 11/15/19 | 480 | Lovo, German G |  | 18.36
PR | 998 | 11/15/19 | 483 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 11/15/19 | 485 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 80.78
PR | 998 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 6.73
PR | 998 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 10.1
PR | 998 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 10.1
PR | 998 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 68.85
PR | 998 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 4.59
PR | 998 | 11/15/19 | 491 | Reyes Cruz, Denis A |  | 80.78
PR | 998 | 11/15/19 | 491 | Reyes Cruz, Denis A |  | 20.2
PR | 998 | 11/15/19 | 493 | Rivera, Jorge A |  | 69.77
PR | 998 | 11/15/19 | 493 | Rivera, Jorge A |  | 46.51
PR | 998 | 11/15/19 | 497 | Rosas Olivares, Jorge C |  | 61.2
PR | 998 | 11/15/19 | 502 | Stahlschmidt, John P |  | 53.86
PR | 998 | 11/15/19 | 502 | Stahlschmidt, John P |  | 13.46
PR | 998 | 11/15/19 | 507 | Velasquez Cruz, Denis M |  | 107.1
PR | 998 | 11/15/19 | 508 | Velasquez Cruz, Osman N |  | 51.41
PR | 998 | 11/15/19 | 508 | Velasquez Cruz, Osman N |  | 34.27
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 11/22/19 | 608 | Amaya Gonzalez, Edilberto A |  | 104.65
PR | 998 | 11/22/19 | 609 | Anderson, Richard P |  | 89.96
PR | 998 | 11/22/19 | 609 | Anderson, Richard P |  | 22.49
PR | 998 | 11/22/19 | 612 | Barbosa, Michael S |  | 95.93
PR | 998 | 11/22/19 | 613 | Barnhart, Joseph N |  | 57.83
PR | 998 | 11/22/19 | 614 | Belcher, Jacob T |  | 61.05
PR | 998 | 11/22/19 | 615 | Benites Portillo, Marvin E |  | 66.56
PR | 998 | 11/22/19 | 615 | Benites Portillo, Marvin E |  | 17.75
PR | 998 | 11/22/19 | 619 | Chevez, Herson G |  | 59.67
PR | 998 | 11/22/19 | 619 | Chevez, Herson G |  | 15.91
PR | 998 | 11/22/19 | 631 | Galdamez, Dagoberto A |  | 95.93
PR | 998 | 11/22/19 | 636 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 11/22/19 | 638 | Gutierrez Salas, Jose |  | 55.23
PR | 998 | 11/22/19 | 639 | Hernandez Gonzalez, Osbaldo |  | 87.21
PR | 998 | 11/22/19 | 640 | Hoeg, Xavier A |  | 46.82
PR | 998 | 11/22/19 | 640 | Hoeg, Xavier A |  | 5.51
PR | 998 | 11/22/19 | 641 | Holmes, Anthony R |  | 127.91
PR | 998 | 11/22/19 | 648 | Lee, Ha Nul |  | 61.2
PR | 998 | 11/22/19 | 648 | Lee, Ha Nul |  | 11.48
PR | 998 | 11/22/19 | 649 | Lima Romero, Melvin A |  | 110.47
PR | 998 | 11/22/19 | 651 | Lovo, German G |  | 50.49
PR | 998 | 11/22/19 | 654 | Martinez Reyes, Juan C |  | 107.56
PR | 998 | 11/22/19 | 656 | Mendoza Morales, Jesus A |  | 53.86
PR | 998 | 11/22/19 | 656 | Mendoza Morales, Jesus A |  | 39.17
PR | 998 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 94.25
PR | 998 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 23.56
PR | 998 | 11/22/19 | 658 | Paco Leyva, Orlando |  | 10.1
PR | 998 | 11/22/19 | 660 | Ramos Herrera, Franklin J |  | 87.21
PR | 998 | 11/22/19 | 662 | Reyes Cruz, Denis A |  | 95.93
PR | 998 | 11/22/19 | 664 | Rivera, Jorge A |  | 110.47
PR | 998 | 11/22/19 | 668 | Rosas Olivares, Jorge C |  | 58.14
PR | 998 | 11/22/19 | 673 | Stahlschmidt, John P |  | 63.95
PR | 998 | 11/22/19 | 678 | Velasquez Cruz, Denis M |  | 101.75
PR | 998 | 11/22/19 | 679 | Velasquez Cruz, Osman N |  | 81.4
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A |  | 77.11
PR | 998 | 11/27/19 | 842 | Amaya Gonzalez, Edilberto A |  | 33.05
PR | 998 | 11/27/19 | 843 | Anderson, Richard P |  | 41.23
PR | 998 | 11/27/19 | 846 | Barbosa, Michael S |  | 78.26
PR | 998 | 11/27/19 | 847 | Barnhart, Joseph N |  | 45.44
PR | 998 | 11/27/19 | 847 | Barnhart, Joseph N |  | 16.52
PR | 998 | 11/27/19 | 848 | Belcher, Jacob T |  | 28.92
PR | 998 | 11/27/19 | 848 | Belcher, Jacob T |  | 9.64
PR | 998 | 11/27/19 | 849 | Benites Portillo, Marvin E |  | 70.99
PR | 998 | 11/27/19 | 853 | Chevez, Herson G |  | 79.56
PR | 998 | 11/27/19 | 865 | Galdamez, Dagoberto A |  | 80.78
PR | 998 | 11/27/19 | 870 | Gonzalez Hernandez, Josue |  | 86.75
PR | 998 | 11/27/19 | 872 | Gutierrez Salas, Jose |  | 23.26
PR | 998 | 11/27/19 | 872 | Gutierrez Salas, Jose |  | 20.35
PR | 998 | 11/27/19 | 873 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 11/27/19 | 874 | Hoeg, Xavier A |  | 41.31
PR | 998 | 11/27/19 | 874 | Hoeg, Xavier A |  | 2.75
PR | 998 | 11/27/19 | 875 | Holmes, Anthony R |  | 80.78
PR | 998 | 11/27/19 | 882 | Lee, Ha Nul |  | 42.08
PR | 998 | 11/27/19 | 882 | Lee, Ha Nul |  | 19.13
PR | 998 | 11/27/19 | 883 | Lima Romero, Melvin A |  | 69.77
PR | 998 | 11/27/19 | 883 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 11/27/19 | 885 | Lovo, German G |  | 91.8
PR | 998 | 11/27/19 | 888 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 11/27/19 | 890 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 63.95
PR | 998 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 60.59
PR | 998 | 11/27/19 | 892 | Paco Leyva, Orlando |  | 3.37
PR | 998 | 11/27/19 | 894 | Ramos Herrera, Franklin J |  | 48.2
PR | 998 | 11/27/19 | 894 | Ramos Herrera, Franklin J |  | 43.61
PR | 998 | 11/27/19 | 896 | Reyes Cruz, Denis A |  | 80.78
PR | 998 | 11/27/19 | 896 | Reyes Cruz, Denis A |  | 20.2
PR | 998 | 11/27/19 | 898 | Rivera, Jorge A |  | 116.28
PR | 998 | 11/27/19 | 902 | Rosas Olivares, Jorge C |  | 56.61
PR | 998 | 11/27/19 | 904 | Sanders, Allen O |  | 24.79
PR | 998 | 11/27/19 | 907 | Stahlschmidt, John P |  | 53.86
PR | 998 | 11/27/19 | 912 | Velasquez Cruz, Denis M |  | 101.75
PR | 998 | 11/27/19 | 913 | Velasquez Cruz, Osman N |  | 85.68
PR | 998 | 11/27/19 | 917 | Donelson, Richard T |  | 33.47
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 11.09
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A |  | 44.06
PR | 998 | 12/06/19 | 28 | Amaya Gonzalez, Edilberto A |  | 22.03
PR | 998 | 12/06/19 | 29 | Anderson, Richard P |  | 82.47
PR | 998 | 12/06/19 | 29 | Anderson, Richard P |  | 3.75
PR | 998 | 12/06/19 | 29 | Anderson, Richard P |  | 3.75
PR | 998 | 12/06/19 | 32 | Barbosa, Michael S |  | 60.59
PR | 998 | 12/06/19 | 32 | Barbosa, Michael S |  | 20.2
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 8.26
PR | 998 | 12/06/19 | 34 | Belcher, Jacob T |  | 38.56
PR | 998 | 12/06/19 | 34 | Belcher, Jacob T |  | 12.85
PR | 998 | 12/06/19 | 35 | Benites Portillo, Marvin E |  | 53.24
PR | 998 | 12/06/19 | 39 | Chevez, Herson G |  | 31.82
PR | 998 | 12/06/19 | 39 | Chevez, Herson G |  | 31.82
PR | 998 | 12/06/19 | 52 | Galdamez, Dagoberto A |  | 60.59
PR | 998 | 12/06/19 | 52 | Galdamez, Dagoberto A |  | 20.2
PR | 998 | 12/06/19 | 57 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 12/06/19 | 57 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 12/06/19 | 59 | Gutierrez Salas, Jose |  | 11.63
PR | 998 | 12/06/19 | 59 | Gutierrez Salas, Jose |  | 33.43
PR | 998 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 12/06/19 | 60 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 12/06/19 | 69 | Lee, Ha Nul |  | 30.6
PR | 998 | 12/06/19 | 69 | Lee, Ha Nul |  | 30.6
PR | 998 | 12/06/19 | 70 | Lima Romero, Melvin A |  | 75.58
PR | 998 | 12/06/19 | 70 | Lima Romero, Melvin A |  | 17.44
PR | 998 | 12/06/19 | 72 | Lovo, German G |  | 55.08
PR | 998 | 12/06/19 | 72 | Lovo, German G |  | 18.36
PR | 998 | 12/06/19 | 75 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 12/06/19 | 77 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 12/06/19 | 77 | Mendoza Morales, Jesus A |  | 39.17
PR | 998 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 50.49
PR | 998 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 30.29
PR | 998 | 12/06/19 | 79 | Paco Leyva, Orlando |  | 26.93
PR | 998 | 12/06/19 | 81 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 12/06/19 | 81 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 20.2
PR | 998 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 40.39
PR | 998 | 12/06/19 | 83 | Reyes Cruz, Denis A |  | 20.2
PR | 998 | 12/06/19 | 85 | Rivera, Jorge A |  | 69.77
PR | 998 | 12/06/19 | 89 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 12/06/19 | 89 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 12/06/19 | 91 | Sanders, Allen O |  | 16.52
PR | 998 | 12/06/19 | 94 | Stahlschmidt, John P |  | 40.39
PR | 998 | 12/06/19 | 94 | Stahlschmidt, John P |  | 13.46
PR | 998 | 12/06/19 | 99 | Velasquez Cruz, Denis M |  | 72.29
PR | 998 | 12/06/19 | 100 | Velasquez Cruz, Osman N |  | 68.54
PR | 998 | 12/06/19 | 104 | Donelson, Richard T |  | 4.78
PR | 998 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/13/19 | 389 | Amaya Gonzalez, Edilberto A |  | 88.13
PR | 998 | 12/13/19 | 390 | Anderson, Richard P |  | 146.19
PR | 998 | 12/13/19 | 390 | Anderson, Richard P |  | 3.75
PR | 998 | 12/13/19 | 393 | Barbosa, Michael S |  | 35.34
PR | 998 | 12/13/19 | 393 | Barbosa, Michael S |  | 65.64
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 28.92
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/13/19 | 395 | Belcher, Jacob T |  | 28.92
PR | 998 | 12/13/19 | 395 | Belcher, Jacob T |  | 35.34
PR | 998 | 12/13/19 | 396 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 12/13/19 | 400 | Chevez, Herson G |  | 79.56
PR | 998 | 12/13/19 | 413 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 12/13/19 | 418 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 12/13/19 | 418 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 12/13/19 | 420 | Gutierrez Salas, Jose |  | 46.51
PR | 998 | 12/13/19 | 421 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 12/13/19 | 430 | Lee, Ha Nul |  | 61.2
PR | 998 | 12/13/19 | 430 | Lee, Ha Nul |  | 15.3
PR | 998 | 12/13/19 | 431 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 12/13/19 | 433 | Lovo, German G |  | 18.36
PR | 998 | 12/13/19 | 436 | Martinez Reyes, Juan C |  | 110.39
PR | 998 | 12/13/19 | 438 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 12/13/19 | 438 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 84.15
PR | 998 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 30.29
PR | 998 | 12/13/19 | 440 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 12/13/19 | 442 | Ramos Herrera, Franklin J |  | 80.33
PR | 998 | 12/13/19 | 442 | Ramos Herrera, Franklin J |  | 11.48
PR | 998 | 12/13/19 | 444 | Reyes Cruz, Denis A |  | 100.98
PR | 998 | 12/13/19 | 446 | Rivera, Jorge A |  | 93.02
PR | 998 | 12/13/19 | 450 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 12/13/19 | 450 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 12/13/19 | 452 | Sanders, Allen O |  | 28.92
PR | 998 | 12/13/19 | 455 | Stahlschmidt, John P |  | 67.32
PR | 998 | 12/13/19 | 460 | Velasquez Cruz, Denis M |  | 96.39
PR | 998 | 12/13/19 | 461 | Velasquez Cruz, Osman N |  | 85.68
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A |  | 104.65
PR | 998 | 12/20/19 | 542 | Amaya Gonzalez, Edilberto A |  | 5.51
PR | 998 | 12/20/19 | 543 | Anderson, Richard P |  | 108.71
PR | 998 | 12/20/19 | 543 | Anderson, Richard P |  | 41.23
PR | 998 | 12/20/19 | 546 | Barbosa, Michael S |  | 20.2
PR | 998 | 12/20/19 | 546 | Barbosa, Michael S |  | 60.59
PR | 998 | 12/20/19 | 547 | Barnhart, Joseph N |  | 33.05
PR | 998 | 12/20/19 | 547 | Barnhart, Joseph N |  | 20.66
PR | 998 | 12/20/19 | 548 | Belcher, Jacob T |  | 54.62
PR | 998 | 12/20/19 | 548 | Belcher, Jacob T |  | 6.43
PR | 998 | 12/20/19 | 548 | Belcher, Jacob T |  | 3.21
PR | 998 | 12/20/19 | 549 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 12/20/19 | 553 | Chevez, Herson G |  | 71.6
PR | 998 | 12/20/19 | 553 | Chevez, Herson G |  | 7.96
PR | 998 | 12/20/19 | 566 | Galdamez, Dagoberto A |  | 80.78
PR | 998 | 12/20/19 | 566 | Galdamez, Dagoberto A |  | 20.2
PR | 998 | 12/20/19 | 571 | Gonzalez Hernandez, Josue |  | 86.75
PR | 998 | 12/20/19 | 573 | Gutierrez Salas, Jose |  | 52.33
PR | 998 | 12/20/19 | 574 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 12/20/19 | 583 | Lee, Ha Nul |  | 51.64
PR | 998 | 12/20/19 | 583 | Lee, Ha Nul |  | 19.13
PR | 998 | 12/20/19 | 584 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 12/20/19 | 584 | Lima Romero, Melvin A |  | 69.77
PR | 998 | 12/20/19 | 586 | Lovo, German G |  | 45.9
PR | 998 | 12/20/19 | 586 | Lovo, German G |  | 9.18
PR | 998 | 12/20/19 | 586 | Lovo, German G |  | 36.72
PR | 998 | 12/20/19 | 589 | Martinez Reyes, Juan C |  | 87.75
PR | 998 | 12/20/19 | 589 | Martinez Reyes, Juan C |  | 16.98
PR | 998 | 12/20/19 | 591 | Mendoza Morales, Jesus A |  | 75.89
PR | 998 | 12/20/19 | 591 | Mendoza Morales, Jesus A |  | 22.03
PR | 998 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 70.69
PR | 998 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 40.39
PR | 998 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 16.83
PR | 998 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 3.37
PR | 998 | 12/20/19 | 593 | Paco Leyva, Orlando |  | 3.37
PR | 998 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 78.03
PR | 998 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 9.18
PR | 998 | 12/20/19 | 595 | Ramos Herrera, Franklin J |  | 4.59
PR | 998 | 12/20/19 | 597 | Reyes Cruz, Denis A |  | 75.74
PR | 998 | 12/20/19 | 597 | Reyes Cruz, Denis A |  | 25.25
PR | 998 | 12/20/19 | 599 | Rivera, Jorge A |  | 93.02
PR | 998 | 12/20/19 | 603 | Rosas Olivares, Jorge C |  | 24.48
PR | 998 | 12/20/19 | 603 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 12/20/19 | 608 | Stahlschmidt, John P |  | 67.32
PR | 998 | 12/20/19 | 613 | Velasquez Cruz, Denis M |  | 80.33
PR | 998 | 12/20/19 | 613 | Velasquez Cruz, Denis M |  | 26.78
PR | 998 | 12/20/19 | 614 | Velasquez Cruz, Osman N |  | 64.26
PR | 998 | 12/20/19 | 614 | Velasquez Cruz, Osman N |  | 21.42
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/20/19 | 619 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A |  | 24.79
PR | 998 | 12/27/19 | 699 | Amaya Gonzalez, Edilberto A |  | 19.28
PR | 998 | 12/27/19 | 700 | Anderson, Richard P |  | 71.22
PR | 998 | 12/27/19 | 700 | Anderson, Richard P |  | 18.74
PR | 998 | 12/27/19 | 703 | Barbosa, Michael S |  | 35.34
PR | 998 | 12/27/19 | 703 | Barbosa, Michael S |  | 25.25
PR | 998 | 12/27/19 | 704 | Barnhart, Joseph N |  | 12.39
PR | 998 | 12/27/19 | 706 | Benites Portillo, Marvin E |  | 22.19
PR | 998 | 12/27/19 | 706 | Benites Portillo, Marvin E |  | 13.31
PR | 998 | 12/27/19 | 710 | Chevez, Herson G |  | 27.85
PR | 998 | 12/27/19 | 710 | Chevez, Herson G |  | 19.89
PR | 998 | 12/27/19 | 724 | Galdamez, Dagoberto A |  | 25.25
PR | 998 | 12/27/19 | 724 | Galdamez, Dagoberto A |  | 15.15
PR | 998 | 12/27/19 | 729 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 12/27/19 | 732 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 12/27/19 | 741 | Lee, Ha Nul |  | 42.08
PR | 998 | 12/27/19 | 741 | Lee, Ha Nul |  | 3.83
PR | 998 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 11.63
PR | 998 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 11.63
PR | 998 | 12/27/19 | 742 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 12/27/19 | 744 | Lovo, German G |  | 32.13
PR | 998 | 12/27/19 | 744 | Lovo, German G |  | 22.95
PR | 998 | 12/27/19 | 747 | Martinez Reyes, Juan C |  | 19.81
PR | 998 | 12/27/19 | 747 | Martinez Reyes, Juan C |  | 25.47
PR | 998 | 12/27/19 | 749 | Mendoza Morales, Jesus A |  | 24.48
PR | 998 | 12/27/19 | 749 | Mendoza Morales, Jesus A |  | 14.69
PR | 998 | 12/27/19 | 751 | Paco Leyva, Orlando |  | 60.59
PR | 998 | 12/27/19 | 751 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 12/27/19 | 753 | Ramos Herrera, Franklin J |  | 22.95
PR | 998 | 12/27/19 | 753 | Ramos Herrera, Franklin J |  | 13.77
PR | 998 | 12/27/19 | 755 | Reyes Cruz, Denis A |  | 40.39
PR | 998 | 12/27/19 | 757 | Rivera, Jorge A |  | 69.77
PR | 998 | 12/27/19 | 761 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 12/27/19 | 766 | Stahlschmidt, John P |  | 26.93
PR | 998 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 12/27/19 | 777 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/03/20 | 2 | Amaya Gonzalez, Edilberto A |  | 79.87
PR | 998 | 01/03/20 | 3 | Anderson, Richard P |  | 33.74
PR | 998 | 01/03/20 | 3 | Anderson, Richard P |  | 29.99
PR | 998 | 01/03/20 | 3 | Anderson, Richard P |  | 44.98
PR | 998 | 01/03/20 | 6 | Barbosa, Michael S |  | 32.82
PR | 998 | 01/03/20 | 6 | Barbosa, Michael S |  | 40.39
PR | 998 | 01/03/20 | 9 | Benites Portillo, Marvin E |  | 64.34
PR | 998 | 01/03/20 | 13 | Chevez, Herson G |  | 49.73
PR | 998 | 01/03/20 | 13 | Chevez, Herson G |  | 7.96
PR | 998 | 01/03/20 | 27 | Galdamez, Dagoberto A |  | 73.21
PR | 998 | 01/03/20 | 32 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 01/03/20 | 32 | Gonzalez Hernandez, Josue |  | 35.8
PR | 998 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 6.89
PR | 998 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 22.95
PR | 998 | 01/03/20 | 35 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 01/03/20 | 44 | Lee, Ha Nul |  | 49.73
PR | 998 | 01/03/20 | 44 | Lee, Ha Nul |  | 5.74
PR | 998 | 01/03/20 | 45 | Lima Romero, Melvin A |  | 37.79
PR | 998 | 01/03/20 | 45 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 01/03/20 | 47 | Lovo, German G |  | 66.56
PR | 998 | 01/03/20 | 50 | Martinez Reyes, Juan C |  | 14.15
PR | 998 | 01/03/20 | 52 | Mendoza Morales, Jesus A |  | 51.41
PR | 998 | 01/03/20 | 56 | Ramos Herrera, Franklin J |  | 66.56
PR | 998 | 01/03/20 | 60 | Rivera, Jorge A |  | 5.81
PR | 998 | 01/03/20 | 60 | Rivera, Jorge A |  | 31.98
PR | 998 | 01/03/20 | 60 | Rivera, Jorge A |  | 46.51
PR | 998 | 01/03/20 | 63 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 01/03/20 | 64 | Rosas Olivares, Jorge C |  | 32.13
PR | 998 | 01/03/20 | 66 | Sanders, Allen O |  | 10.33
PR | 998 | 01/03/20 | 69 | Stahlschmidt, John P |  | 21.88
PR | 998 | 01/03/20 | 81 | Donelson, Richard T |  | 9.56
PR | 998 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 01/03/20 | 82 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A |  | 88.13
PR | 998 | 01/10/20 | 275 | Amaya Gonzalez, Edilberto A |  | 8.26
PR | 998 | 01/10/20 | 276 | Anderson, Richard P |  | 18.74
PR | 998 | 01/10/20 | 276 | Anderson, Richard P |  | 14.99
PR | 998 | 01/10/20 | 276 | Anderson, Richard P |  | 101.21
PR | 998 | 01/10/20 | 276 | Anderson, Richard P |  | 11.25
PR | 998 | 01/10/20 | 276 | Anderson, Richard P |  | 3.75
PR | 998 | 01/10/20 | 279 | Barbosa, Michael S |  | 80.15
PR | 998 | 01/10/20 | 280 | Barnhart, Joseph N |  | 16.52
PR | 998 | 01/10/20 | 282 | Benites Portillo, Marvin E |  | 17.75
PR | 998 | 01/10/20 | 282 | Benites Portillo, Marvin E |  | 53.24
PR | 998 | 01/10/20 | 286 | Chevez, Herson G |  | 67.63
PR | 998 | 01/10/20 | 286 | Chevez, Herson G |  | 11.93
PR | 998 | 01/10/20 | 300 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 01/10/20 | 305 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 01/10/20 | 308 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 01/10/20 | 317 | Lee, Ha Nul |  | 72.68
PR | 998 | 01/10/20 | 317 | Lee, Ha Nul |  | 3.83
PR | 998 | 01/10/20 | 318 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 01/10/20 | 320 | Lovo, German G |  | 57.38
PR | 998 | 01/10/20 | 320 | Lovo, German G |  | 13.77
PR | 998 | 01/10/20 | 323 | Martinez Reyes, Juan C |  | 55.19
PR | 998 | 01/10/20 | 323 | Martinez Reyes, Juan C |  | 19.81
PR | 998 | 01/10/20 | 325 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 01/10/20 | 327 | Paco Leyva, Orlando |  | 26.93
PR | 998 | 01/10/20 | 327 | Paco Leyva, Orlando |  | 26.93
PR | 998 | 01/10/20 | 329 | Ramos Herrera, Franklin J |  | 66.56
PR | 998 | 01/10/20 | 333 | Rivera, Jorge A |  | 93.02
PR | 998 | 01/10/20 | 333 | Rivera, Jorge A |  | 23.26
PR | 998 | 01/10/20 | 337 | Rosas Olivares, Jorge C |  | 19.89
PR | 998 | 01/10/20 | 337 | Rosas Olivares, Jorge C |  | 39.78
PR | 998 | 01/10/20 | 339 | Sanders, Allen O |  | 18.59
PR | 998 | 01/10/20 | 342 | Stahlschmidt, John P |  | 50.49
PR | 998 | 01/10/20 | 342 | Stahlschmidt, John P |  | 3.37
PR | 998 | 01/10/20 | 352 | Donelson, Richard T |  | 9.56
PR | 998 | 01/17/20 | 542 | Anderson, Richard P |  | 103.08
PR | 998 | 01/17/20 | 542 | Anderson, Richard P |  | 3.75
PR | 998 | 01/17/20 | 545 | Barbosa, Michael S |  | 40.39
PR | 998 | 01/17/20 | 545 | Barbosa, Michael S |  | 20.2
PR | 998 | 01/17/20 | 546 | Barnhart, Joseph N |  | 12.39
PR | 998 | 01/17/20 | 548 | Benites Portillo, Marvin E |  | 70.99
PR | 998 | 01/17/20 | 552 | Chevez, Herson G |  | 47.74
PR | 998 | 01/17/20 | 552 | Chevez, Herson G |  | 15.91
PR | 998 | 01/17/20 | 566 | Galdamez, Dagoberto A |  | 80.78
PR | 998 | 01/17/20 | 571 | Gonzalez Hernandez, Josue |  | 78.49
PR | 998 | 01/17/20 | 574 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 01/17/20 | 583 | Lee, Ha Nul |  | 61.2
PR | 998 | 01/17/20 | 584 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 01/17/20 | 586 | Lovo, German G |  | 89.51
PR | 998 | 01/17/20 | 589 | Martinez Reyes, Juan C |  | 87.75
PR | 998 | 01/17/20 | 591 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 01/17/20 | 599 | Rivera, Jorge A |  | 116.28
PR | 998 | 01/17/20 | 603 | Rosas Olivares, Jorge C |  | 36.72
PR | 998 | 01/17/20 | 605 | Sanders, Allen O |  | 10.33
PR | 998 | 01/17/20 | 608 | Stahlschmidt, John P |  | 40.39
PR | 998 | 01/17/20 | 618 | Donelson, Richard T |  | 23.91
PR | 998 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 01/24/20 | 675 | Anderson, Richard P |  | 86.22
PR | 998 | 01/24/20 | 675 | Anderson, Richard P |  | 3.75
PR | 998 | 01/24/20 | 678 | Barbosa, Michael S |  | 60.59
PR | 998 | 01/24/20 | 678 | Barbosa, Michael S |  | 40.39
PR | 998 | 01/24/20 | 679 | Barnhart, Joseph N |  | 16.52
PR | 998 | 01/24/20 | 681 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 01/24/20 | 685 | Chevez, Herson G |  | 79.56
PR | 998 | 01/24/20 | 698 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 01/24/20 | 706 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 01/24/20 | 714 | Lee, Ha Nul |  | 76.5
PR | 998 | 01/24/20 | 715 | Lima Romero, Melvin A |  | 69.77
PR | 998 | 01/24/20 | 715 | Lima Romero, Melvin A |  | 46.51
PR | 998 | 01/24/20 | 717 | Lovo, German G |  | 91.8
PR | 998 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 01/24/20 | 722 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 01/24/20 | 722 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 43.76
PR | 998 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 23.56
PR | 998 | 01/24/20 | 724 | Paco Leyva, Orlando |  | 13.46
PR | 998 | 01/24/20 | 726 | Ramos Herrera, Franklin J |  | 55.08
PR | 998 | 01/24/20 | 730 | Rivera, Jorge A |  | 116.28
PR | 998 | 01/24/20 | 734 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 01/24/20 | 736 | Sanders, Allen O |  | 6.2
PR | 998 | 01/24/20 | 739 | Stahlschmidt, John P |  | 67.32
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 4.78
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 4.78
PR | 998 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 01/31/20 | 834 | Anderson, Richard P |  | 33.74
PR | 998 | 01/31/20 | 834 | Anderson, Richard P |  | 86.22
PR | 998 | 01/31/20 | 837 | Barbosa, Michael S |  | 90.88
PR | 998 | 01/31/20 | 837 | Barbosa, Michael S |  | 10.1
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 8.26
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 4.13
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 8.26
PR | 998 | 01/31/20 | 840 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 01/31/20 | 844 | Chevez, Herson G |  | 79.56
PR | 998 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 95.93
PR | 998 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 5.05
PR | 998 | 01/31/20 | 863 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 01/31/20 | 863 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo |  | 89.51
PR | 998 | 01/31/20 | 866 | Hernandez Gonzalez, Osbaldo |  | 2.3
PR | 998 | 01/31/20 | 874 | Lee, Ha Nul |  | 70.76
PR | 998 | 01/31/20 | 874 | Lee, Ha Nul |  | 5.74
PR | 998 | 01/31/20 | 875 | Lima Romero, Melvin A |  | 23.26
PR | 998 | 01/31/20 | 875 | Lima Romero, Melvin A |  | 61.05
PR | 998 | 01/31/20 | 877 | Lovo, German G |  | 91.8
PR | 998 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 99.07
PR | 998 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 11.32
PR | 998 | 01/31/20 | 882 | Mendoza Morales, Jesus A |  | 83.23
PR | 998 | 01/31/20 | 882 | Mendoza Morales, Jesus A |  | 14.69
PR | 998 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 6.73
PR | 998 | 01/31/20 | 884 | Paco Leyva, Orlando |  | 6.73
PR | 998 | 01/31/20 | 887 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 01/31/20 | 891 | Rivera, Jorge A |  | 69.77
PR | 998 | 01/31/20 | 891 | Rivera, Jorge A |  | 23.26
PR | 998 | 01/31/20 | 895 | Rosas Olivares, Jorge C |  | 24.48
PR | 998 | 01/31/20 | 895 | Rosas Olivares, Jorge C |  | 24.48
PR | 998 | 01/31/20 | 897 | Sanders, Allen O |  | 26.85
PR | 998 | 01/31/20 | 900 | Stahlschmidt, John P |  | 40.39
PR | 998 | 01/31/20 | 900 | Stahlschmidt, John P |  | 5.05
PR | 998 | 01/31/20 | 910 | Young, Joshua S |  | 6.12
PR | 998 | 01/31/20 | 910 | Young, Joshua S |  | 23.26
PR | 998 | 01/31/20 | 911 | Donelson, Richard T |  | 9.56
PR | 998 | 01/31/20 | 912 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 01/31/20 | 912 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 02/07/20 | 15 | Lovo, German G |  | 55.08
PR | 998 | 02/07/20 | 25 | Anderson, Richard P |  | 18.74
PR | 998 | 02/07/20 | 25 | Anderson, Richard P |  | 63.72
PR | 998 | 02/07/20 | 25 | Anderson, Richard P |  | 37.49
PR | 998 | 02/07/20 | 28 | Barbosa, Michael S |  | 35.34
PR | 998 | 02/07/20 | 28 | Barbosa, Michael S |  | 65.64
PR | 998 | 02/07/20 | 31 | Benites Portillo, Marvin E |  | 70.99
PR | 998 | 02/07/20 | 35 | Chevez, Herson G |  | 79.56
PR | 998 | 02/07/20 | 39 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 02/07/20 | 41 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 02/07/20 | 43 | Draves, Steven W |  | 37.94
PR | 998 | 02/07/20 | 48 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 02/07/20 | 51 | Gerard, Jordan E |  | 51.41
PR | 998 | 02/07/20 | 53 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 02/07/20 | 65 | Lee, Ha Nul |  | 34.43
PR | 998 | 02/07/20 | 65 | Lee, Ha Nul |  | 42.08
PR | 998 | 02/07/20 | 66 | Lima Romero, Melvin A |  | 58.14
PR | 998 | 02/07/20 | 66 | Lima Romero, Melvin A |  | 58.14
PR | 998 | 02/07/20 | 68 | Lovo, German G |  | 18.36
PR | 998 | 02/07/20 | 69 | Mackey, Cole J |  | 4.9
PR | 998 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 36.8
PR | 998 | 02/07/20 | 72 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 02/07/20 | 72 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 30.29
PR | 998 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 6.73
PR | 998 | 02/07/20 | 74 | Paco Leyva, Orlando |  | 6.73
PR | 998 | 02/07/20 | 77 | Ramos Herrera, Franklin J |  | 36.72
PR | 998 | 02/07/20 | 81 | Rivera, Jorge A |  | 104.65
PR | 998 | 02/07/20 | 81 | Rivera, Jorge A |  | 11.63
PR | 998 | 02/07/20 | 84 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/07/20 | 85 | Rosas Olivares, Jorge C |  | 61.2
PR | 998 | 02/07/20 | 88 | Sanders, Allen O |  | 59.9
PR | 998 | 02/07/20 | 91 | Stahlschmidt, John P |  | 53.86
PR | 998 | 02/07/20 | 101 | Young, Joshua S |  | 41.62
PR | 998 | 02/07/20 | 101 | Young, Joshua S |  | 7.34
PR | 998 | 02/07/20 | 102 | Donelson, Richard T |  | 4.78
PR | 998 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 02/14/20 | 235 | Anderson, Richard P |  | 112.46
PR | 998 | 02/14/20 | 235 | Anderson, Richard P |  | 3.75
PR | 998 | 02/14/20 | 235 | Anderson, Richard P |  | 3.75
PR | 998 | 02/14/20 | 238 | Barbosa, Michael S |  | 80.78
PR | 998 | 02/14/20 | 239 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/14/20 | 241 | Benites Portillo, Marvin E |  | 82.08
PR | 998 | 02/14/20 | 245 | Chevez, Herson G |  | 55.69
PR | 998 | 02/14/20 | 249 | Cruz Gonzalez, Julio C |  | 29.99
PR | 998 | 02/14/20 | 251 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 02/14/20 | 258 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 02/14/20 | 260 | Gauthier, Dillon R |  | 11.02
PR | 998 | 02/14/20 | 263 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 02/14/20 | 266 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 02/14/20 | 275 | Lee, Ha Nul |  | 68.85
PR | 998 | 02/14/20 | 275 | Lee, Ha Nul |  | 7.65
PR | 998 | 02/14/20 | 276 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 02/14/20 | 278 | Lovo, German G |  | 91.8
PR | 998 | 02/14/20 | 279 | Mackey, Cole J |  | 6.12
PR | 998 | 02/14/20 | 280 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/14/20 | 280 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 02/14/20 | 282 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 02/14/20 | 287 | Ramos Herrera, Franklin J |  | 9.18
PR | 998 | 02/14/20 | 291 | Rivera, Jorge A |  | 116.28
PR | 998 | 02/14/20 | 294 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 02/14/20 | 295 | Rosas Olivares, Jorge C |  | 61.2
PR | 998 | 02/14/20 | 298 | Sanders, Allen O |  | 16.52
PR | 998 | 02/14/20 | 301 | Stahlschmidt, John P |  | 40.39
PR | 998 | 02/14/20 | 301 | Stahlschmidt, John P |  | 13.46
PR | 998 | 02/14/20 | 304 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 02/14/20 | 311 | Young, Joshua S |  | 44.06
PR | 998 | 02/14/20 | 311 | Young, Joshua S |  | 4.9
PR | 998 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 02/21/20 | 452 | Anderson, Richard P |  | 11.25
PR | 998 | 02/21/20 | 452 | Anderson, Richard P |  | 119.95
PR | 998 | 02/21/20 | 452 | Anderson, Richard P |  | 18.74
PR | 998 | 02/21/20 | 455 | Barbosa, Michael S |  | 95.93
PR | 998 | 02/21/20 | 455 | Barbosa, Michael S |  | 5.05
PR | 998 | 02/21/20 | 458 | Benites Portillo, Marvin E |  | 86.52
PR | 998 | 02/21/20 | 458 | Benites Portillo, Marvin E |  | 2.22
PR | 998 | 02/21/20 | 459 | Boss, Benjamin T |  | 22.03
PR | 998 | 02/21/20 | 460 | Boss, Kyle A |  | 25.7
PR | 998 | 02/21/20 | 462 | Chevez, Herson G |  | 45.75
PR | 998 | 02/21/20 | 462 | Chevez, Herson G |  | 1.99
PR | 998 | 02/21/20 | 466 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 02/21/20 | 468 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 02/21/20 | 474 | Galdamez, Dagoberto A |  | 100.98
PR | 998 | 02/21/20 | 476 | Gauthier, Dillon R |  | 11.02
PR | 998 | 02/21/20 | 479 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 02/21/20 | 481 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 02/21/20 | 490 | Lee, Ha Nul |  | 72.68
PR | 998 | 02/21/20 | 490 | Lee, Ha Nul |  | 3.83
PR | 998 | 02/21/20 | 491 | Lima Romero, Melvin A |  | 110.47
PR | 998 | 02/21/20 | 491 | Lima Romero, Melvin A |  | 5.81
PR | 998 | 02/21/20 | 493 | Lovo, German G |  | 66.56
PR | 998 | 02/21/20 | 494 | Mackey, Cole J |  | 6.12
PR | 998 | 02/21/20 | 495 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/21/20 | 497 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 02/21/20 | 507 | Rivera, Jorge A |  | 110.47
PR | 998 | 02/21/20 | 507 | Rivera, Jorge A |  | 5.81
PR | 998 | 02/21/20 | 510 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/21/20 | 511 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 02/21/20 | 514 | Sanders, Allen O |  | 47.51
PR | 998 | 02/21/20 | 517 | Stahlschmidt, John P |  | 31.98
PR | 998 | 02/21/20 | 517 | Stahlschmidt, John P |  | 35.34
PR | 998 | 02/21/20 | 520 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 02/21/20 | 527 | Young, Joshua S |  | 39.17
PR | 998 | 02/21/20 | 528 | Donelson, Richard T |  | 4.78
PR | 998 | 02/21/20 | 529 | Gerard, Jeffrey S |  | 11.09
PR | 998 | 02/28/20 | 680 | Anderson, Richard P |  | 3.75
PR | 998 | 02/28/20 | 680 | Anderson, Richard P |  | 116.2
PR | 998 | 02/28/20 | 680 | Anderson, Richard P |  | 11.25
PR | 998 | 02/28/20 | 680 | Anderson, Richard P |  | 11.25
PR | 998 | 02/28/20 | 680 | Anderson, Richard P |  | 7.5
PR | 998 | 02/28/20 | 683 | Barbosa, Michael S |  | 60.59
PR | 998 | 02/28/20 | 683 | Barbosa, Michael S |  | 32.82
PR | 998 | 02/28/20 | 683 | Barbosa, Michael S |  | 7.57
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 4.13
PR | 998 | 02/28/20 | 685 | Benites Portillo, Marvin E |  | 53.24
PR | 998 | 02/28/20 | 685 | Benites Portillo, Marvin E |  | 35.5
PR | 998 | 02/28/20 | 687 | Boss, Benjamin T |  | 22.03
PR | 998 | 02/28/20 | 688 | Boss, Kyle A |  | 25.7
PR | 998 | 02/28/20 | 690 | Chevez, Herson G |  | 63.65
PR | 998 | 02/28/20 | 690 | Chevez, Herson G |  | 15.91
PR | 998 | 02/28/20 | 694 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 02/28/20 | 696 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 02/28/20 | 703 | Galdamez, Dagoberto A |  | 60.59
PR | 998 | 02/28/20 | 703 | Galdamez, Dagoberto A |  | 20.2
PR | 998 | 02/28/20 | 705 | Gauthier, Dillon R |  | 11.02
PR | 998 | 02/28/20 | 708 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 02/28/20 | 708 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 02/28/20 | 711 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 02/28/20 | 719 | Lee, Ha Nul |  | 76.5
PR | 998 | 02/28/20 | 720 | Lima Romero, Melvin A |  | 69.77
PR | 998 | 02/28/20 | 720 | Lima Romero, Melvin A |  | 23.26
PR | 998 | 02/28/20 | 722 | Lovo, German G |  | 55.08
PR | 998 | 02/28/20 | 722 | Lovo, German G |  | 36.72
PR | 998 | 02/28/20 | 723 | Mackey, Cole J |  | 6.12
PR | 998 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 59.44
PR | 998 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/28/20 | 726 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 02/28/20 | 739 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 02/28/20 | 740 | Rosas Olivares, Jorge C |  | 44.37
PR | 998 | 02/28/20 | 743 | Sanders, Allen O |  | 35.11
PR | 998 | 02/28/20 | 746 | Stahlschmidt, John P |  | 67.32
PR | 998 | 02/28/20 | 749 | Trower-Kelly, Fidel D |  | 25.7
PR | 998 | 02/28/20 | 756 | Young, Joshua S |  | 48.96
PR | 998 | 02/28/20 | 757 | Donelson, Richard T |  | 4.78
PR | 998 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 03/06/20 | 42 | Anderson, Richard P |  | 22.49
PR | 998 | 03/06/20 | 42 | Anderson, Richard P |  | 93.71
PR | 998 | 03/06/20 | 42 | Anderson, Richard P |  | 26.24
PR | 998 | 03/06/20 | 42 | Anderson, Richard P |  | 3.75
PR | 998 | 03/06/20 | 42 | Anderson, Richard P |  | 3.75
PR | 998 | 03/06/20 | 45 | Barbosa, Michael S |  | 20.2
PR | 998 | 03/06/20 | 45 | Barbosa, Michael S |  | 40.39
PR | 998 | 03/06/20 | 45 | Barbosa, Michael S |  | 40.39
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 20.66
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 26.85
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 10.33
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 2.07
PR | 998 | 03/06/20 | 48 | Benites Portillo, Marvin E |  | 35.5
PR | 998 | 03/06/20 | 48 | Benites Portillo, Marvin E |  | 35.5
PR | 998 | 03/06/20 | 49 | Boss, Benjamin T |  | 55.08
PR | 998 | 03/06/20 | 50 | Boss, Kyle A |  | 25.7
PR | 998 | 03/06/20 | 52 | Chevez, Herson G |  | 73.59
PR | 998 | 03/06/20 | 52 | Chevez, Herson G |  | 5.97
PR | 998 | 03/06/20 | 56 | Cruz Gonzalez, Julio C |  | 27.85
PR | 998 | 03/06/20 | 58 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 03/06/20 | 66 | Galdamez, Dagoberto A |  | 60.59
PR | 998 | 03/06/20 | 66 | Galdamez, Dagoberto A |  | 40.39
PR | 998 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 8.26
PR | 998 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 13.77
PR | 998 | 03/06/20 | 70 | Gonzalez Hernandez, Josue |  | 35.8
PR | 998 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 03/06/20 | 73 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 03/06/20 | 81 | Lee, Ha Nul |  | 53.55
PR | 998 | 03/06/20 | 81 | Lee, Ha Nul |  | 7.65
PR | 998 | 03/06/20 | 82 | Lima Romero, Melvin A |  | 104.65
PR | 998 | 03/06/20 | 82 | Lima Romero, Melvin A |  | 11.63
PR | 998 | 03/06/20 | 84 | Lovo, German G |  | 55.08
PR | 998 | 03/06/20 | 84 | Lovo, German G |  | 36.72
PR | 998 | 03/06/20 | 85 | Mackey, Cole J |  | 6.12
PR | 998 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 03/06/20 | 86 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 03/06/20 | 88 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 03/06/20 | 90 | Paco Leyva, Orlando |  | 26.93
PR | 998 | 03/06/20 | 94 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 03/06/20 | 98 | Rivera, Jorge A |  | 69.77
PR | 998 | 03/06/20 | 98 | Rivera, Jorge A |  | 46.51
PR | 998 | 03/06/20 | 101 | Romero Garza, Jesus I |  | 36.95
PR | 998 | 03/06/20 | 102 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 03/06/20 | 102 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 03/06/20 | 105 | Sanders, Allen O |  | 59.9
PR | 998 | 03/06/20 | 108 | Stahlschmidt, John P |  | 67.32
PR | 998 | 03/06/20 | 118 | Young, Joshua S |  | 48.96
PR | 998 | 03/13/20 | 307 | Anderson, Richard P |  | 39.36
PR | 998 | 03/13/20 | 307 | Anderson, Richard P |  | 33.74
PR | 998 | 03/13/20 | 307 | Anderson, Richard P |  | 97.46
PR | 998 | 03/13/20 | 307 | Anderson, Richard P |  | 14.99
PR | 998 | 03/13/20 | 307 | Anderson, Richard P |  | 3.75
PR | 998 | 03/13/20 | 310 | Barbosa, Michael S |  | 95.93
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 24.79
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 20.66
PR | 998 | 03/13/20 | 313 | Benites Portillo, Marvin E |  | 23.29
PR | 998 | 03/13/20 | 313 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 03/13/20 | 314 | Boss, Benjamin T |  | 55.08
PR | 998 | 03/13/20 | 315 | Boss, Kyle A |  | 64.26
PR | 998 | 03/13/20 | 317 | Chevez, Herson G |  | 20.88
PR | 998 | 03/13/20 | 317 | Chevez, Herson G |  | 79.56
PR | 998 | 03/13/20 | 321 | Cruz Gonzalez, Julio C |  | 84.61
PR | 998 | 03/13/20 | 323 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 03/13/20 | 327 | Eliassen, Cory H |  | 36.72
PR | 998 | 03/13/20 | 330 | Galdamez, Dagoberto A |  | 40.39
PR | 998 | 03/13/20 | 330 | Galdamez, Dagoberto A |  | 60.59
PR | 998 | 03/13/20 | 334 | Gonzalez Hernandez, Josue |  | 99.14
PR | 998 | 03/13/20 | 334 | Gonzalez Hernandez, Josue |  | 11.02
PR | 998 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 24.1
PR | 998 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 03/13/20 | 337 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 03/13/20 | 345 | Lee, Ha Nul |  | 61.2
PR | 998 | 03/13/20 | 346 | Lima Romero, Melvin A |  | 116.28
PR | 998 | 03/13/20 | 348 | Lovo, German G |  | 91.8
PR | 998 | 03/13/20 | 349 | Mackey, Cole J |  | 6.12
PR | 998 | 03/13/20 | 350 | Martinez Reyes, Juan C |  | 27.6
PR | 998 | 03/13/20 | 350 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 03/13/20 | 352 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 03/13/20 | 354 | Paco Leyva, Orlando |  | 53.86
PR | 998 | 03/13/20 | 354 | Paco Leyva, Orlando |  | 35.34
PR | 998 | 03/13/20 | 358 | Ramos Herrera, Franklin J |  | 27.54
PR | 998 | 03/13/20 | 358 | Ramos Herrera, Franklin J |  | 9.18
PR | 998 | 03/13/20 | 362 | Rivera, Jorge A |  | 110.47
PR | 998 | 03/13/20 | 362 | Rivera, Jorge A |  | 5.81
PR | 998 | 03/13/20 | 365 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 03/13/20 | 366 | Rosas Olivares, Jorge C |  | 48.96
PR | 998 | 03/13/20 | 366 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 03/13/20 | 369 | Sanders, Allen O |  | 72.29
PR | 998 | 03/13/20 | 372 | Stahlschmidt, John P |  | 67.32
PR | 998 | 03/13/20 | 375 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 03/13/20 | 382 | Young, Joshua S |  | 48.96
PR | 998 | 03/13/20 | 383 | Donelson, Richard T |  | 4.78
PR | 998 | 03/13/20 | 383 | Donelson, Richard T |  | 4.78
PR | 998 | 03/13/20 | 384 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 03/20/20 | 565 | Anderson, Richard P |  | 101.21
PR | 998 | 03/20/20 | 565 | Anderson, Richard P |  | 22.49
PR | 998 | 03/20/20 | 565 | Anderson, Richard P |  | 18.74
PR | 998 | 03/20/20 | 565 | Anderson, Richard P |  | 3.75
PR | 998 | 03/20/20 | 565 | Anderson, Richard P |  | 3.75
PR | 998 | 03/20/20 | 568 | Barbosa, Michael S |  | 60.59
PR | 998 | 03/20/20 | 568 | Barbosa, Michael S |  | 20.2
PR | 998 | 03/20/20 | 571 | Benites Portillo, Marvin E |  | 35.5
PR | 998 | 03/20/20 | 571 | Benites Portillo, Marvin E |  | 35.5
PR | 998 | 03/20/20 | 572 | Boss, Benjamin T |  | 11.02
PR | 998 | 03/20/20 | 573 | Boss, Kyle A |  | 12.85
PR | 998 | 03/20/20 | 575 | Chevez, Herson G |  | 31.82
PR | 998 | 03/20/20 | 581 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 03/20/20 | 585 | Eliassen, Cory H |  | 18.36
PR | 998 | 03/20/20 | 588 | Galdamez, Dagoberto A |  | 40.39
PR | 998 | 03/20/20 | 592 | Gonzalez Hernandez, Josue |  | 38.56
PR | 998 | 03/20/20 | 592 | Gonzalez Hernandez, Josue |  | 71.6
PR | 998 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 03/20/20 | 595 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 03/20/20 | 603 | Lee, Ha Nul |  | 76.5
PR | 998 | 03/20/20 | 604 | Lima Romero, Melvin A |  | 113.37
PR | 998 | 03/20/20 | 606 | Lovo, German G |  | 84.92
PR | 998 | 03/20/20 | 608 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 03/20/20 | 608 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 03/20/20 | 610 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 03/20/20 | 612 | Paco Leyva, Orlando |  | 37.03
PR | 998 | 03/20/20 | 616 | Ramos Herrera, Franklin J |  | 25.25
PR | 998 | 03/20/20 | 620 | Rivera, Jorge A |  | 69.77
PR | 998 | 03/20/20 | 620 | Rivera, Jorge A |  | 46.51
PR | 998 | 03/20/20 | 624 | Rosas Olivares, Jorge C |  | 47.43
PR | 998 | 03/20/20 | 627 | Sanders, Allen O |  | 64.03
PR | 998 | 03/20/20 | 630 | Stahlschmidt, John P |  | 40.39
PR | 998 | 03/20/20 | 630 | Stahlschmidt, John P |  | 26.93
PR | 998 | 03/20/20 | 640 | Young, Joshua S |  | 48.96
PR | 998 | 03/20/20 | 641 | Donelson, Richard T |  | 9.56
PR | 998 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 03/26/20 | 748 | Anderson, Richard P |  | 123.7
PR | 998 | 03/26/20 | 748 | Anderson, Richard P |  | 3.75
PR | 998 | 03/26/20 | 748 | Anderson, Richard P |  | 7.5
PR | 998 | 03/26/20 | 751 | Barbosa, Michael S |  | 42.92
PR | 998 | 03/26/20 | 751 | Barbosa, Michael S |  | 37.87
PR | 998 | 03/26/20 | 751 | Barbosa, Michael S |  | 20.2
PR | 998 | 03/26/20 | 754 | Benites Portillo, Marvin E |  | 88.74
PR | 998 | 03/26/20 | 755 | Boss, Benjamin T |  | 55.08
PR | 998 | 03/26/20 | 756 | Boss, Kyle A |  | 64.26
PR | 998 | 03/26/20 | 758 | Chevez, Herson G |  | 47.74
PR | 998 | 03/26/20 | 763 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 03/26/20 | 767 | Eliassen, Cory H |  | 91.8
PR | 998 | 03/26/20 | 770 | Galdamez, Dagoberto A |  | 40.39
PR | 998 | 03/26/20 | 774 | Gonzalez Hernandez, Josue |  | 104.65
PR | 998 | 03/26/20 | 774 | Gonzalez Hernandez, Josue |  | 5.51
PR | 998 | 03/26/20 | 777 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 16.83
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 26.93
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 16.83
PR | 998 | 03/26/20 | 784 | Lee, Ha Nul |  | 45.9
PR | 998 | 03/26/20 | 785 | Lima Romero, Melvin A |  | 93.02
PR | 998 | 03/26/20 | 787 | Lovo, German G |  | 91.8
PR | 998 | 03/26/20 | 789 | Martinez Reyes, Juan C |  | 48.12
PR | 998 | 03/26/20 | 789 | Martinez Reyes, Juan C |  | 65.1
PR | 998 | 03/26/20 | 791 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 03/26/20 | 800 | Rivera, Jorge A |  | 116.28
PR | 998 | 03/26/20 | 803 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 03/26/20 | 804 | Rosas Olivares, Jorge C |  | 12.24
PR | 998 | 03/26/20 | 806 | Sanders, Allen O |  | 101.21
PR | 998 | 03/26/20 | 809 | Stahlschmidt, John P |  | 13.46
PR | 998 | 03/26/20 | 812 | Trower-Kelly, Fidel D |  | 51.41
PR | 998 | 03/26/20 | 819 | Young, Joshua S |  | 29.38
PR | 998 | 03/26/20 | 820 | Donelson, Richard T |  | 14.34
PR | 998 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 04/03/20 | 42 | Donelson, Richard T |  | 4.78
PR | 998 | 04/17/20 | 288 | Donelson, Richard T |  | 4.78
PR | 998 | 04/24/20 | 348 | Anderson, Richard P |  | 29.99
PR | 998 | 04/24/20 | 351 | Barbosa, Michael S |  | 20.2
PR | 998 | 04/24/20 | 391 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 04/24/20 | 424 | Donelson, Richard T |  | 4.78
PR | 998 | 05/01/20 | 2 | Anderson, Richard P |  | 14.99
PR | 998 | 05/01/20 | 2 | Anderson, Richard P |  | 123.7
PR | 998 | 05/01/20 | 2 | Anderson, Richard P |  | 3.75
PR | 998 | 05/01/20 | 2 | Anderson, Richard P |  | 7.5
PR | 998 | 05/01/20 | 5 | Barbosa, Michael S |  | 20.2
PR | 998 | 05/01/20 | 5 | Barbosa, Michael S |  | 80.78
PR | 998 | 05/01/20 | 10 | Boss, Kyle A |  | 12.85
PR | 998 | 05/01/20 | 18 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 05/01/20 | 22 | Eliassen, Cory H |  | 12.62
PR | 998 | 05/01/20 | 45 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 05/01/20 | 45 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 05/01/20 | 60 | Romero Garza, Jesus I |  | 14.08
PR | 998 | 05/01/20 | 64 | Sanders, Allen O |  | 28.92
PR | 998 | 05/01/20 | 70 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 05/01/20 | 78 | Donelson, Richard T |  | 4.78
PR | 998 | 05/01/20 | 79 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 05/08/20 | 153 | Anderson, Richard P |  | 131.2
PR | 998 | 05/08/20 | 153 | Anderson, Richard P |  | 11.25
PR | 998 | 05/08/20 | 156 | Barbosa, Michael S |  | 80.78
PR | 998 | 05/08/20 | 157 | Barnhart, Joseph N |  | 16.52
PR | 998 | 05/08/20 | 169 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 05/08/20 | 173 | Eliassen, Cory H |  | 91.8
PR | 998 | 05/08/20 | 183 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 05/08/20 | 185 | Holmes, Anthony R |  | 26.93
PR | 998 | 05/08/20 | 191 | Lee, Ha Nul |  | 15.3
PR | 998 | 05/08/20 | 196 | Martinez Reyes, Juan C |  | 82.08
PR | 998 | 05/08/20 | 196 | Martinez Reyes, Juan C |  | 8.49
PR | 998 | 05/08/20 | 198 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 05/08/20 | 211 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 05/08/20 | 215 | Sanders, Allen O |  | 35.11
PR | 998 | 05/08/20 | 231 | Donelson, Richard T |  | 4.78
PR | 998 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 05/08/20 | 232 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 05/15/20 | 308 | Anderson, Richard P |  | 3.75
PR | 998 | 05/15/20 | 308 | Anderson, Richard P |  | 116.2
PR | 998 | 05/15/20 | 309 | Ascencio, Jose L |  | 70.69
PR | 998 | 05/15/20 | 309 | Ascencio, Jose L |  | 10.1
PR | 998 | 05/15/20 | 311 | Barbosa, Michael S |  | 100.98
PR | 998 | 05/15/20 | 312 | Barnhart, Joseph N |  | 8.26
PR | 998 | 05/15/20 | 312 | Barnhart, Joseph N |  | 4.13
PR | 998 | 05/15/20 | 324 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 05/15/20 | 328 | Eliassen, Cory H |  | 49.34
PR | 998 | 05/15/20 | 335 | Gonzalez Hernandez, Josue |  | 77.11
PR | 998 | 05/15/20 | 335 | Gonzalez Hernandez, Josue |  | 11.02
PR | 998 | 05/15/20 | 338 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 05/15/20 | 340 | Holmes, Anthony R |  | 57.22
PR | 998 | 05/15/20 | 340 | Holmes, Anthony R |  | 60.59
PR | 998 | 05/15/20 | 340 | Holmes, Anthony R |  | 16.83
PR | 998 | 05/15/20 | 346 | Lee, Ha Nul |  | 76.5
PR | 998 | 05/15/20 | 351 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 05/15/20 | 353 | Mendoza Morales, Jesus A |  | 85.68
PR | 998 | 05/15/20 | 353 | Mendoza Morales, Jesus A |  | 12.24
PR | 998 | 05/15/20 | 366 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 05/15/20 | 370 | Sanders, Allen O |  | 16.52
PR | 998 | 05/15/20 | 384 | Donelson, Richard T |  | 23.91
PR | 998 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 05/15/20 | 385 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 05/22/20 | 463 | Anderson, Richard P |  | 86.22
PR | 998 | 05/22/20 | 463 | Anderson, Richard P |  | 3.75
PR | 998 | 05/22/20 | 464 | Ascencio, Jose L |  | 100.98
PR | 998 | 05/22/20 | 466 | Barbosa, Michael S |  | 100.98
PR | 998 | 05/22/20 | 467 | Barnhart, Joseph N |  | 26.85
PR | 998 | 05/22/20 | 467 | Barnhart, Joseph N |  | 26.85
PR | 998 | 05/22/20 | 477 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 05/22/20 | 479 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 05/22/20 | 483 | Eliassen, Cory H |  | 41.31
PR | 998 | 05/22/20 | 483 | Eliassen, Cory H |  | 9.18
PR | 998 | 05/22/20 | 489 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 05/22/20 | 490 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 05/22/20 | 491 | Holmes, Anthony R |  | 74.05
PR | 998 | 05/22/20 | 491 | Holmes, Anthony R |  | 60.59
PR | 998 | 05/22/20 | 497 | Lee, Ha Nul |  | 76.5
PR | 998 | 05/22/20 | 502 | Martinez Reyes, Juan C |  | 110.39
PR | 998 | 05/22/20 | 504 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 05/22/20 | 517 | Romero Garza, Jesus I |  | 28.15
PR | 998 | 05/22/20 | 520 | Sanders, Allen O |  | 43.38
PR | 998 | 05/22/20 | 525 | Taylor, Evan R |  | 60.59
PR | 998 | 05/22/20 | 534 | Donelson, Richard T |  | 9.56
PR | 998 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 05/22/20 | 535 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 05/29/20 | 591 | Anderson, Richard P |  | 48.73
PR | 998 | 05/29/20 | 592 | Ascencio, Jose L |  | 80.78
PR | 998 | 05/29/20 | 594 | Barbosa, Michael S |  | 63.11
PR | 998 | 05/29/20 | 594 | Barbosa, Michael S |  | 17.67
PR | 998 | 05/29/20 | 595 | Barnhart, Joseph N |  | 24.79
PR | 998 | 05/29/20 | 595 | Barnhart, Joseph N |  | 33.05
PR | 998 | 05/29/20 | 598 | Boss, Benjamin T |  | 22.03
PR | 998 | 05/29/20 | 605 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 05/29/20 | 607 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 05/29/20 | 611 | Eliassen, Cory H |  | 55.08
PR | 998 | 05/29/20 | 617 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 05/29/20 | 618 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 05/29/20 | 619 | Holmes, Anthony R |  | 107.71
PR | 998 | 05/29/20 | 622 | Hubbard, Robert W |  | 8.26
PR | 998 | 05/29/20 | 625 | Lee, Ha Nul |  | 61.2
PR | 998 | 05/29/20 | 630 | Martinez Reyes, Juan C |  | 89.16
PR | 998 | 05/29/20 | 632 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 05/29/20 | 643 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 05/29/20 | 646 | Sanders, Allen O |  | 33.05
PR | 998 | 05/29/20 | 651 | Taylor, Evan R |  | 56.8
PR | 998 | 05/29/20 | 659 | Donelson, Richard T |  | 14.34
PR | 998 | 05/29/20 | 659 | Donelson, Richard T |  | 4.78
PR | 998 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 05/29/20 | 660 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/05/20 | 14 | Anderson, Richard P |  | 106.83
PR | 998 | 06/05/20 | 15 | Ascencio, Jose L |  | 100.98
PR | 998 | 06/05/20 | 17 | Barbosa, Michael S |  | 80.78
PR | 998 | 06/05/20 | 17 | Barbosa, Michael S |  | 20.2
PR | 998 | 06/05/20 | 18 | Barnhart, Joseph N |  | 61.97
PR | 998 | 06/05/20 | 18 | Barnhart, Joseph N |  | 4.13
PR | 998 | 06/05/20 | 18 | Barnhart, Joseph N |  | 8.26
PR | 998 | 06/05/20 | 18 | Barnhart, Joseph N |  | 8.26
PR | 998 | 06/05/20 | 19 | Boss, Benjamin T |  | 44.06
PR | 998 | 06/05/20 | 25 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 06/05/20 | 27 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 06/05/20 | 31 | Eliassen, Cory H |  | 78.03
PR | 998 | 06/05/20 | 36 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 06/05/20 | 37 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 06/05/20 | 38 | Holmes, Anthony R |  | 53.86
PR | 998 | 06/05/20 | 43 | Lee, Ha Nul |  | 76.5
PR | 998 | 06/05/20 | 46 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 06/05/20 | 48 | Mendoza Morales, Jesus A |  | 97.92
PR | 998 | 06/05/20 | 54 | Rivera, Jorge A |  | 116.28
PR | 998 | 06/05/20 | 58 | Sanders, Allen O |  | 61.97
PR | 998 | 06/05/20 | 62 | Trower-Kelly, Fidel D |  | 12.85
PR | 998 | 06/05/20 | 66 | Donelson, Richard T |  | 4.78
PR | 998 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 6.66
PR | 998 | 06/11/20 | 157 | Ascencio, Jose L |  | 40.39
PR | 998 | 06/11/20 | 159 | Barbosa, Michael S |  | 20.2
PR | 998 | 06/11/20 | 159 | Barbosa, Michael S |  | 20.2
PR | 998 | 06/11/20 | 160 | Boss, Benjamin T |  | 22.03
PR | 998 | 06/11/20 | 166 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 06/11/20 | 168 | Cruz Reyes, Jose |  | 39.17
PR | 998 | 06/11/20 | 175 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 06/11/20 | 176 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 06/11/20 | 177 | Holmes, Anthony R |  | 53.86
PR | 998 | 06/11/20 | 182 | Lee, Ha Nul |  | 15.3
PR | 998 | 06/11/20 | 182 | Lee, Ha Nul |  | 15.3
PR | 998 | 06/11/20 | 185 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 06/11/20 | 187 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 06/11/20 | 187 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 06/11/20 | 193 | Rivera, Jorge A |  | 46.51
PR | 998 | 06/12/20 | 218 | Ascencio, Jose L |  | 60.59
PR | 998 | 06/12/20 | 220 | Barbosa, Michael S |  | 40.39
PR | 998 | 06/12/20 | 220 | Barbosa, Michael S |  | 20.2
PR | 998 | 06/12/20 | 221 | Barnhart, Joseph N |  | 90.88
PR | 998 | 06/12/20 | 221 | Barnhart, Joseph N |  | 12.39
PR | 998 | 06/12/20 | 222 | Boss, Benjamin T |  | 33.05
PR | 998 | 06/12/20 | 228 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 06/12/20 | 230 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 06/12/20 | 238 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 06/12/20 | 239 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 06/12/20 | 240 | Holmes, Anthony R |  | 53.86
PR | 998 | 06/12/20 | 245 | Lee, Ha Nul |  | 45.9
PR | 998 | 06/12/20 | 248 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 06/12/20 | 250 | Mendoza Morales, Jesus A |  | 58.75
PR | 998 | 06/12/20 | 256 | Rivera, Jorge A |  | 69.77
PR | 998 | 06/12/20 | 260 | Sanders, Allen O |  | 64.03
PR | 998 | 06/12/20 | 266 | Donelson, Richard T |  | 14.34
PR | 998 | 06/12/20 | 267 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 06/19/20 | 375 | Ascencio, Jose L |  | 80.78
PR | 998 | 06/19/20 | 377 | Barbosa, Michael S |  | 40.39
PR | 998 | 06/19/20 | 377 | Barbosa, Michael S |  | 40.39
PR | 998 | 06/19/20 | 378 | Barnhart, Joseph N |  | 59.9
PR | 998 | 06/19/20 | 378 | Barnhart, Joseph N |  | 12.39
PR | 998 | 06/19/20 | 379 | Boss, Benjamin T |  | 11.02
PR | 998 | 06/19/20 | 385 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 06/19/20 | 394 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 06/19/20 | 394 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 06/19/20 | 395 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 06/19/20 | 396 | Holmes, Anthony R |  | 87.52
PR | 998 | 06/19/20 | 396 | Holmes, Anthony R |  | 37.03
PR | 998 | 06/19/20 | 396 | Holmes, Anthony R |  | 10.1
PR | 998 | 06/19/20 | 401 | Lee, Ha Nul |  | 45.9
PR | 998 | 06/19/20 | 401 | Lee, Ha Nul |  | 15.3
PR | 998 | 06/19/20 | 404 | Martinez Reyes, Juan C |  | 84.92
PR | 998 | 06/19/20 | 404 | Martinez Reyes, Juan C |  | 5.66
PR | 998 | 06/19/20 | 406 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 06/19/20 | 406 | Mendoza Morales, Jesus A |  | 78.34
PR | 998 | 06/19/20 | 412 | Rivera, Jorge A |  | 69.77
PR | 998 | 06/19/20 | 412 | Rivera, Jorge A |  | 46.51
PR | 998 | 06/19/20 | 416 | Sanders, Allen O |  | 68.16
PR | 998 | 06/19/20 | 422 | Donelson, Richard T |  | 9.56
PR | 998 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/19/20 | 423 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/26/20 | 518 | Ascencio, Jose L |  | 100.98
PR | 998 | 06/26/20 | 520 | Barbosa, Michael S |  | 70.69
PR | 998 | 06/26/20 | 520 | Barbosa, Michael S |  | 30.29
PR | 998 | 06/26/20 | 521 | Barnhart, Joseph N |  | 61.97
PR | 998 | 06/26/20 | 521 | Barnhart, Joseph N |  | 4.13
PR | 998 | 06/26/20 | 522 | Boss, Benjamin T |  | 11.02
PR | 998 | 06/26/20 | 528 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 06/26/20 | 536 | Gonzalez Hernandez, Josue |  | 99.14
PR | 998 | 06/26/20 | 536 | Gonzalez Hernandez, Josue |  | 11.02
PR | 998 | 06/26/20 | 537 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 06/26/20 | 538 | Holmes, Anthony R |  | 132.96
PR | 998 | 06/26/20 | 543 | Lee, Ha Nul |  | 76.5
PR | 998 | 06/26/20 | 546 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 06/26/20 | 548 | Mendoza Morales, Jesus A |  | 95.47
PR | 998 | 06/26/20 | 554 | Rivera, Jorge A |  | 93.02
PR | 998 | 06/26/20 | 554 | Rivera, Jorge A |  | 23.26
PR | 998 | 06/26/20 | 558 | Sanders, Allen O |  | 33.05
PR | 998 | 06/26/20 | 564 | Donelson, Richard T |  | 9.56
PR | 998 | 06/26/20 | 565 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/26/20 | 565 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/02/20 | 4 | Ascencio, Jose L |  | 95.93
PR | 998 | 07/02/20 | 4 | Ascencio, Jose L |  | 5.05
PR | 998 | 07/02/20 | 6 | Barbosa, Michael S |  | 100.98
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 24.79
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 4.13
PR | 998 | 07/02/20 | 8 | Boss, Benjamin T |  | 55.08
PR | 998 | 07/02/20 | 14 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 07/02/20 | 22 | Gonzalez Hernandez, Josue |  | 77.11
PR | 998 | 07/02/20 | 22 | Gonzalez Hernandez, Josue |  | 33.05
PR | 998 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo |  | 64.26
PR | 998 | 07/02/20 | 23 | Hernandez Gonzalez, Osbaldo |  | 27.54
PR | 998 | 07/02/20 | 24 | Holmes, Anthony R |  | 114.44
PR | 998 | 07/02/20 | 24 | Holmes, Anthony R |  | 10.1
PR | 998 | 07/02/20 | 29 | Lee, Ha Nul |  | 76.5
PR | 998 | 07/02/20 | 32 | Martinez Reyes, Juan C |  | 104.73
PR | 998 | 07/02/20 | 32 | Martinez Reyes, Juan C |  | 5.66
PR | 998 | 07/02/20 | 34 | Mendoza Morales, Jesus A |  | 39.17
PR | 998 | 07/02/20 | 40 | Rivera, Jorge A |  | 116.28
PR | 998 | 07/02/20 | 44 | Sanders, Allen O |  | 128.06
PR | 998 | 07/02/20 | 51 | Gerard, Jeffrey S |  | 6.66
PR | 998 | 07/10/20 | 137 | Ascencio, Jose L |  | 60.59
PR | 998 | 07/10/20 | 139 | Barbosa, Michael S |  | 60.59
PR | 998 | 07/10/20 | 140 | Barnhart, Joseph N |  | 28.92
PR | 998 | 07/10/20 | 140 | Barnhart, Joseph N |  | 16.52
PR | 998 | 07/10/20 | 140 | Barnhart, Joseph N |  | 66.1
PR | 998 | 07/10/20 | 141 | Boss, Benjamin T |  | 33.05
PR | 998 | 07/10/20 | 147 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 07/10/20 | 154 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 07/10/20 | 154 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 07/10/20 | 155 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 07/10/20 | 156 | Holmes, Anthony R |  | 26.93
PR | 998 | 07/10/20 | 156 | Holmes, Anthony R |  | 53.86
PR | 998 | 07/10/20 | 161 | Lee, Ha Nul |  | 45.9
PR | 998 | 07/10/20 | 164 | Martinez Reyes, Juan C |  | 65.1
PR | 998 | 07/10/20 | 166 | Mendoza Morales, Jesus A |  | 19.58
PR | 998 | 07/10/20 | 172 | Rivera, Jorge A |  | 69.77
PR | 998 | 07/10/20 | 176 | Sanders, Allen O |  | 99.14
PR | 998 | 07/10/20 | 182 | Donelson, Richard T |  | 4.78
PR | 998 | 07/17/20 | 262 | Ascencio, Jose L |  | 100.98
PR | 998 | 07/17/20 | 264 | Barbosa, Michael S |  | 98.46
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 61.97
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 12.39
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 4.13
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 8.26
PR | 998 | 07/17/20 | 266 | Boss, Benjamin T |  | 55.08
PR | 998 | 07/17/20 | 272 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 07/17/20 | 274 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 07/17/20 | 281 | Gonzalez Hernandez, Josue |  | 99.14
PR | 998 | 07/17/20 | 281 | Gonzalez Hernandez, Josue |  | 2.75
PR | 998 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo |  | 84.92
PR | 998 | 07/17/20 | 282 | Hernandez Gonzalez, Osbaldo |  | 6.89
PR | 998 | 07/17/20 | 283 | Holmes, Anthony R |  | 94.25
PR | 998 | 07/17/20 | 283 | Holmes, Anthony R |  | 23.56
PR | 998 | 07/17/20 | 283 | Holmes, Anthony R |  | 10.1
PR | 998 | 07/17/20 | 283 | Holmes, Anthony R |  | 6.73
PR | 998 | 07/17/20 | 289 | Lee, Ha Nul |  | 70.76
PR | 998 | 07/17/20 | 289 | Lee, Ha Nul |  | 5.74
PR | 998 | 07/17/20 | 291 | Mackey, Cole J |  | 1.22
PR | 998 | 07/17/20 | 292 | Martinez Reyes, Juan C |  | 107.56
PR | 998 | 07/17/20 | 300 | Rivera, Jorge A |  | 116.28
PR | 998 | 07/17/20 | 303 | Sanders, Allen O |  | 140.45
PR | 998 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/24/20 | 401 | Ascencio, Jose L |  | 100.98
PR | 998 | 07/24/20 | 403 | Barbosa, Michael S |  | 100.98
PR | 998 | 07/24/20 | 404 | Barnhart, Joseph N |  | 66.1
PR | 998 | 07/24/20 | 404 | Barnhart, Joseph N |  | 24.79
PR | 998 | 07/24/20 | 404 | Barnhart, Joseph N |  | 12.39
PR | 998 | 07/24/20 | 405 | Boss, Benjamin T |  | 55.08
PR | 998 | 07/24/20 | 411 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 07/24/20 | 413 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 07/24/20 | 420 | Gonzalez Hernandez, Josue |  | 57.83
PR | 998 | 07/24/20 | 420 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 07/24/20 | 421 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 07/24/20 | 422 | Holmes, Anthony R |  | 134.64
PR | 998 | 07/24/20 | 428 | Lee, Ha Nul |  | 58.33
PR | 998 | 07/24/20 | 430 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 07/24/20 | 438 | Rivera, Jorge A |  | 116.28
PR | 998 | 07/24/20 | 442 | Sanders, Allen O |  | 90.88
PR | 998 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 07/31/20 | 496 | Ascencio, Jose L |  | 100.98
PR | 998 | 07/31/20 | 498 | Barbosa, Michael S |  | 95.93
PR | 998 | 07/31/20 | 499 | Barnhart, Joseph N |  | 66.1
PR | 998 | 07/31/20 | 499 | Barnhart, Joseph N |  | 8.26
PR | 998 | 07/31/20 | 499 | Barnhart, Joseph N |  | 8.26
PR | 998 | 07/31/20 | 500 | Boss, Benjamin T |  | 55.08
PR | 998 | 07/31/20 | 506 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 07/31/20 | 508 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 07/31/20 | 515 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 07/31/20 | 516 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 07/31/20 | 517 | Holmes, Anthony R |  | 134.64
PR | 998 | 07/31/20 | 523 | Lee, Ha Nul |  | 30.6
PR | 998 | 07/31/20 | 525 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 07/31/20 | 533 | Rivera, Jorge A |  | 46.51
PR | 998 | 07/31/20 | 537 | Sanders, Allen O |  | 80.55
PR | 998 | 07/31/20 | 543 | Donelson, Richard T |  | 4.78
PR | 998 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/31/20 | 544 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 08/07/20 | 87 | Ascencio, Jose L |  | 100.98
PR | 998 | 08/07/20 | 89 | Barbosa, Michael S |  | 100.98
PR | 998 | 08/07/20 | 90 | Barnhart, Joseph N |  | 70.23
PR | 998 | 08/07/20 | 90 | Barnhart, Joseph N |  | 20.66
PR | 998 | 08/07/20 | 90 | Barnhart, Joseph N |  | 8.26
PR | 998 | 08/07/20 | 90 | Barnhart, Joseph N |  | 28.92
PR | 998 | 08/07/20 | 91 | Boss, Benjamin T |  | 22.03
PR | 998 | 08/07/20 | 96 | Cruz Gonzalez, Julio C |  | 6.43
PR | 998 | 08/07/20 | 98 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 08/07/20 | 105 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 08/07/20 | 106 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 08/07/20 | 107 | Holmes, Anthony R |  | 89.2
PR | 998 | 08/07/20 | 107 | Holmes, Anthony R |  | 45.44
PR | 998 | 08/07/20 | 114 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 08/07/20 | 123 | Sanders, Allen O |  | 146.65
PR | 998 | 08/07/20 | 129 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 08/07/20 | 129 | Gerard, Jeffrey S |  | 15.53
PR | 998 | 08/14/20 | 292 | Ascencio, Jose L |  | 100.98
PR | 998 | 08/14/20 | 294 | Barbosa, Michael S |  | 99.72
PR | 998 | 08/14/20 | 295 | Barnhart, Joseph N |  | 90.88
PR | 998 | 08/14/20 | 295 | Barnhart, Joseph N |  | 12.39
PR | 998 | 08/14/20 | 296 | Boss, Benjamin T |  | 11.02
PR | 998 | 08/14/20 | 310 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 08/14/20 | 310 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 08/14/20 | 311 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 08/14/20 | 312 | Holmes, Anthony R |  | 134.64
PR | 998 | 08/14/20 | 318 | Martinez Reyes, Juan C |  | 101.9
PR | 998 | 08/14/20 | 327 | Sanders, Allen O |  | 53.7
PR | 998 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 15.53
PR | 998 | 08/14/20 | 333 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 08/21/20 | 413 | Ascencio, Jose L |  | 100.98
PR | 998 | 08/21/20 | 415 | Barbosa, Michael S |  | 80.78
PR | 998 | 08/21/20 | 417 | Boss, Benjamin T |  | 11.02
PR | 998 | 08/21/20 | 422 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 08/21/20 | 424 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 08/21/20 | 430 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 08/21/20 | 430 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 08/21/20 | 431 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 08/21/20 | 432 | Holmes, Anthony R |  | 134.64
PR | 998 | 08/21/20 | 438 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 08/21/20 | 447 | Sanders, Allen O |  | 95.01
PR | 998 | 08/21/20 | 459 | Donelson, Richard T |  | 4.78
PR | 998 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 08/21/20 | 460 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 08/28/20 | 561 | Ascencio, Jose L |  | 80.78
PR | 998 | 08/28/20 | 563 | Barbosa, Michael S |  | 100.98
PR | 998 | 08/28/20 | 564 | Barnhart, Joseph N |  | 70.23
PR | 998 | 08/28/20 | 564 | Barnhart, Joseph N |  | 8.26
PR | 998 | 08/28/20 | 565 | Boss, Benjamin T |  | 11.02
PR | 998 | 08/28/20 | 570 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 08/28/20 | 572 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 08/28/20 | 579 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 08/28/20 | 580 | Hernandez Gonzalez, Osbaldo |  | 91.8
PR | 998 | 08/28/20 | 581 | Holmes, Anthony R |  | 53.86
PR | 998 | 08/28/20 | 587 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 08/28/20 | 598 | Sanders, Allen O |  | 8.26
PR | 998 | 08/28/20 | 604 | Donelson, Richard T |  | 9.56
PR | 998 | 08/28/20 | 605 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 09/04/20 | 3 | Anderson, Richard P |  | 89.96
PR | 998 | 09/04/20 | 4 | Ascencio, Jose L |  | 100.98
PR | 998 | 09/04/20 | 6 | Barbosa, Michael S |  | 100.98
PR | 998 | 09/04/20 | 7 | Barnhart, Joseph N |  | 128.06
PR | 998 | 09/04/20 | 7 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/04/20 | 23 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 09/04/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 73.44
PR | 998 | 09/04/20 | 25 | Holmes, Anthony R |  | 134.64
PR | 998 | 09/04/20 | 31 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 09/04/20 | 43 | Sanders, Allen O |  | 33.05
PR | 998 | 09/04/20 | 50 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 09/11/20 | 73 | Anderson, Richard P |  | 74.97
PR | 998 | 09/11/20 | 73 | Anderson, Richard P |  | 44.98
PR | 998 | 09/11/20 | 74 | Ascencio, Jose L |  | 80.78
PR | 998 | 09/11/20 | 76 | Barbosa, Michael S |  | 80.78
PR | 998 | 09/11/20 | 77 | Barnhart, Joseph N |  | 53.7
PR | 998 | 09/11/20 | 77 | Barnhart, Joseph N |  | 8.26
PR | 998 | 09/11/20 | 94 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 09/11/20 | 95 | Holmes, Anthony R |  | 26.93
PR | 998 | 09/11/20 | 101 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 09/11/20 | 113 | Sanders, Allen O |  | 8.26
PR | 998 | 09/11/20 | 119 | Donelson, Richard T |  | 4.78
PR | 998 | 09/18/20 | 284 | Anderson, Richard P |  | 44.98
PR | 998 | 09/18/20 | 284 | Anderson, Richard P |  | 101.21
PR | 998 | 09/18/20 | 284 | Anderson, Richard P |  | 3.75
PR | 998 | 09/18/20 | 285 | Ascencio, Jose L |  | 60.59
PR | 998 | 09/18/20 | 287 | Barbosa, Michael S |  | 20.2
PR | 998 | 09/18/20 | 288 | Barnhart, Joseph N |  | 37.18
PR | 998 | 09/18/20 | 288 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/18/20 | 289 | Boss, Benjamin T |  | 11.02
PR | 998 | 09/18/20 | 295 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 09/18/20 | 297 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 09/18/20 | 304 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 09/18/20 | 305 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 09/18/20 | 306 | Holmes, Anthony R |  | 80.78
PR | 998 | 09/18/20 | 312 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 09/18/20 | 324 | Sanders, Allen O |  | 41.31
PR | 998 | 09/18/20 | 330 | Donelson, Richard T |  | 4.78
PR | 998 | 09/18/20 | 331 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 09/25/20 | 425 | Anderson, Richard P |  | 63.72
PR | 998 | 09/25/20 | 425 | Anderson, Richard P |  | 26.24
PR | 998 | 09/25/20 | 426 | Ascencio, Jose L |  | 55.54
PR | 998 | 09/25/20 | 426 | Ascencio, Jose L |  | 5.05
PR | 998 | 09/25/20 | 429 | Barnhart, Joseph N |  | 107.41
PR | 998 | 09/25/20 | 429 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/25/20 | 429 | Barnhart, Joseph N |  | 4.13
PR | 998 | 09/25/20 | 430 | Boss, Benjamin T |  | 11.02
PR | 998 | 09/25/20 | 436 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 09/25/20 | 446 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 09/25/20 | 446 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 09/25/20 | 447 | Hernandez Gonzalez, Osbaldo |  | 55.08
PR | 998 | 09/25/20 | 448 | Holmes, Anthony R |  | 37.03
PR | 998 | 09/25/20 | 448 | Holmes, Anthony R |  | 43.76
PR | 998 | 09/25/20 | 454 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 09/25/20 | 466 | Sanders, Allen O |  | 49.57
PR | 998 | 09/25/20 | 478 | Donelson, Richard T |  | 4.78
PR | 998 | 09/25/20 | 479 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 10/02/20 | 2 | Anderson, Richard P |  | 37.49
PR | 998 | 10/02/20 | 2 | Anderson, Richard P |  | 28.11
PR | 998 | 10/02/20 | 2 | Anderson, Richard P |  | 14.99
PR | 998 | 10/02/20 | 3 | Ascencio, Jose L |  | 12.62
PR | 998 | 10/02/20 | 3 | Ascencio, Jose L |  | 47.97
PR | 998 | 10/02/20 | 6 | Barnhart, Joseph N |  | 49.57
PR | 998 | 10/02/20 | 6 | Barnhart, Joseph N |  | 16.52
PR | 998 | 10/02/20 | 6 | Barnhart, Joseph N |  | 12.39
PR | 998 | 10/02/20 | 6 | Barnhart, Joseph N |  | 12.39
PR | 998 | 10/02/20 | 7 | Boss, Benjamin T |  | 11.02
PR | 998 | 10/02/20 | 13 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 10/02/20 | 23 | Gonzalez Hernandez, Josue |  | 8.26
PR | 998 | 10/02/20 | 23 | Gonzalez Hernandez, Josue |  | 57.83
PR | 998 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 36.72
PR | 998 | 10/02/20 | 24 | Hernandez Gonzalez, Osbaldo |  | 18.36
PR | 998 | 10/02/20 | 25 | Holmes, Anthony R |  | 53.86
PR | 998 | 10/02/20 | 25 | Holmes, Anthony R |  | 26.93
PR | 998 | 10/02/20 | 28 | Hubbard, Robert W |  | 28.92
PR | 998 | 10/02/20 | 31 | Martinez Reyes, Juan C |  | 8.49
PR | 998 | 10/02/20 | 31 | Martinez Reyes, Juan C |  | 59.44
PR | 998 | 10/02/20 | 43 | Sanders, Allen O |  | 66.1
PR | 998 | 10/02/20 | 51 | Donelson, Richard T |  | 4.78
PR | 998 | 10/02/20 | 52 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 10/09/20 | 151 | Anderson, Richard P |  | 3.75
PR | 998 | 10/09/20 | 151 | Anderson, Richard P |  | 86.22
PR | 998 | 10/09/20 | 155 | Barnhart, Joseph N |  | 33.05
PR | 998 | 10/09/20 | 155 | Barnhart, Joseph N |  | 20.66
PR | 998 | 10/09/20 | 155 | Barnhart, Joseph N |  | 12.39
PR | 998 | 10/09/20 | 156 | Boss, Benjamin T |  | 11.02
PR | 998 | 10/09/20 | 162 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 10/09/20 | 164 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 10/09/20 | 172 | Gonzalez Hernandez, Josue |  | 66.1
PR | 998 | 10/09/20 | 173 | Hernandez Gonzalez, Osbaldo |  | 47.05
PR | 998 | 10/09/20 | 174 | Holmes, Anthony R |  | 58.91
PR | 998 | 10/09/20 | 174 | Holmes, Anthony R |  | 21.88
PR | 998 | 10/09/20 | 180 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 10/09/20 | 191 | Sanders, Allen O |  | 97.08
PR | 998 | 10/09/20 | 198 | Donelson, Richard T |  | 4.78
PR | 998 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 10/09/20 | 199 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 10/16/20 | 293 | Anderson, Richard P |  | 84.34
PR | 998 | 10/16/20 | 293 | Anderson, Richard P |  | 5.62
PR | 998 | 10/16/20 | 297 | Barnhart, Joseph N |  | 20.66
PR | 998 | 10/16/20 | 298 | Boss, Benjamin T |  | 11.02
PR | 998 | 10/16/20 | 314 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 10/16/20 | 316 | Holmes, Anthony R |  | 33.66
PR | 998 | 10/16/20 | 316 | Holmes, Anthony R |  | 20.2
PR | 998 | 10/16/20 | 322 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 10/16/20 | 333 | Sanders, Allen O |  | 86.75
PR | 998 | 10/23/20 | 434 | Anderson, Richard P |  | 89.96
PR | 998 | 10/23/20 | 438 | Barnhart, Joseph N |  | 8.26
PR | 998 | 10/23/20 | 457 | Holmes, Anthony R |  | 53.86
PR | 998 | 10/23/20 | 463 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 10/23/20 | 475 | Sanders, Allen O |  | 55.77
PR | 998 | 10/30/20 | 591 | Anderson, Richard P |  | 89.96
PR | 998 | 10/30/20 | 604 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 10/30/20 | 614 | Holmes, Anthony R |  | 53.86
PR | 998 | 10/30/20 | 619 | Martinez Reyes, Juan C |  | 113.22
PR | 998 | 10/30/20 | 630 | Sanders, Allen O |  | 90.88
PR | 998 | 11/06/20 | 34 | Holmes, Anthony R |  | 134.64
PR | 998 | 11/06/20 | 39 | Martinez Reyes, Juan C |  | 108.97
PR | 998 | 11/06/20 | 50 | Sanders, Allen O |  | 53.7
PR | 998 | 11/13/20 | 208 | Holmes, Anthony R |  | 132.96
PR | 998 | 11/13/20 | 213 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 11/13/20 | 224 | Sanders, Allen O |  | 80.55
PR | 998 | 11/13/20 | 230 | Donelson, Richard T |  | 4.78
PR | 998 | 11/20/20 | 341 | Anderson, Richard P |  | 48.73
PR | 998 | 11/20/20 | 341 | Anderson, Richard P |  | 11.25
PR | 998 | 11/20/20 | 346 | Boss, Benjamin T |  | 55.08
PR | 998 | 11/20/20 | 364 | Holmes, Anthony R |  | 60.59
PR | 998 | 11/20/20 | 364 | Holmes, Anthony R |  | 20.2
PR | 998 | 11/20/20 | 379 | Sanders, Allen O |  | 161.11
PR | 998 | 11/20/20 | 389 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 11/25/20 | 456 | Barnhart, Joseph N |  | 16.52
PR | 998 | 11/25/20 | 457 | Boss, Benjamin T |  | 44.06
PR | 998 | 11/25/20 | 491 | Sanders, Allen O |  | 140.45
PR | 998 | 11/25/20 | 498 | Donelson, Richard T |  | 4.78
PR | 998 | 12/04/20 | 7 | Barnhart, Joseph N |  | 8.26
PR | 998 | 12/04/20 | 8 | Boss, Benjamin T |  | 41.31
PR | 998 | 12/04/20 | 26 | Holmes, Anthony R |  | 53.86
PR | 998 | 12/04/20 | 31 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 12/04/20 | 42 | Sanders, Allen O |  | 123.93
PR | 998 | 12/11/20 | 184 | Boss, Benjamin T |  | 55.08
PR | 998 | 12/11/20 | 202 | Holmes, Anthony R |  | 134.64
PR | 998 | 12/11/20 | 207 | Martinez Reyes, Juan C |  | 110.39
PR | 998 | 12/11/20 | 218 | Sanders, Allen O |  | 134.26
PR | 998 | 12/18/20 | 344 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/18/20 | 345 | Boss, Benjamin T |  | 55.08
PR | 998 | 12/18/20 | 363 | Holmes, Anthony R |  | 134.64
PR | 998 | 12/18/20 | 368 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 12/18/20 | 379 | Sanders, Allen O |  | 152.85
PR | 998 | 12/23/20 | 485 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/23/20 | 485 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/23/20 | 486 | Boss, Benjamin T |  | 18.59
PR | 998 | 12/23/20 | 492 | Cruz Gonzalez, Julio C |  | 17.14
PR | 998 | 12/23/20 | 494 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 12/23/20 | 504 | Holmes, Anthony R |  | 87.52
PR | 998 | 12/23/20 | 504 | Holmes, Anthony R |  | 20.2
PR | 998 | 12/23/20 | 509 | Martinez Reyes, Juan C |  | 73.59
PR | 998 | 12/23/20 | 509 | Martinez Reyes, Juan C |  | 16.98
PR | 998 | 12/23/20 | 520 | Sanders, Allen O |  | 105.34
PR | 998 | 12/31/20 | 585 | Barnhart, Joseph N |  | 4.13
PR | 998 | 12/31/20 | 594 | Cruz Reyes, Jose |  | 19.58
PR | 998 | 12/31/20 | 602 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 12/31/20 | 604 | Holmes, Anthony R |  | 26.93
PR | 998 | 12/31/20 | 604 | Holmes, Anthony R |  | 53.86
PR | 998 | 12/31/20 | 609 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 01/08/21 | 9 | Boss, Benjamin T |  | 11.02
PR | 998 | 01/08/21 | 17 | Cruz Reyes, Jose |  | 58.75
PR | 998 | 01/08/21 | 25 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 01/08/21 | 27 | Holmes, Anthony R |  | 43.76
PR | 998 | 01/08/21 | 27 | Holmes, Anthony R |  | 26.93
PR | 998 | 01/08/21 | 27 | Holmes, Anthony R |  | 37.03
PR | 998 | 01/08/21 | 43 | Sanders, Allen O |  | 66.1
PR | 998 | 01/08/21 | 52 | Donelson, Richard T |  | 4.78
PR | 998 | 01/15/21 | 122 | Boss, Benjamin T |  | 18.59
PR | 998 | 01/15/21 | 141 | Holmes, Anthony R |  | 63.95
PR | 998 | 01/15/21 | 141 | Holmes, Anthony R |  | 52.17
PR | 998 | 01/15/21 | 141 | Holmes, Anthony R |  | 6.73
PR | 998 | 01/15/21 | 146 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 01/15/21 | 157 | Romero Garza, Jesus I |  | 42.23
PR | 998 | 01/15/21 | 159 | Sanders, Allen O |  | 80.55
PR | 998 | 01/22/21 | 270 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 01/22/21 | 280 | Holmes, Anthony R |  | 35.34
PR | 998 | 01/22/21 | 285 | Martinez Reyes, Juan C |  | 50.95
PR | 998 | 01/22/21 | 296 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 01/22/21 | 298 | Sanders, Allen O |  | 80.55
PR | 998 | 01/29/21 | 396 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 01/29/21 | 412 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 01/29/21 | 422 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 01/29/21 | 424 | Sanders, Allen O |  | 97.08
PR | 998 | 02/05/21 | 82 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 02/05/21 | 99 | Martinez Reyes, Juan C |  | 90.58
PR | 998 | 02/05/21 | 110 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/05/21 | 112 | Sanders, Allen O |  | 113.6
PR | 998 | 02/12/21 | 265 | Cruz Gonzalez, Julio C |  | 51.41
PR | 998 | 02/12/21 | 267 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 02/12/21 | 285 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 02/12/21 | 296 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/12/21 | 298 | Sanders, Allen O |  | 148.72
PR | 998 | 02/19/21 | 420 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/19/21 | 429 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 02/19/21 | 431 | Cruz Reyes, Jose |  | 97.92
PR | 998 | 02/19/21 | 452 | Martinez Reyes, Juan C |  | 110.39
PR | 998 | 02/19/21 | 463 | Romero Garza, Jesus I |  | 56.3
PR | 998 | 02/19/21 | 465 | Sanders, Allen O |  | 126
PR | 998 | 02/26/21 | 599 | Boss, Benjamin T |  | 13.77
PR | 998 | 02/26/21 | 599 | Boss, Benjamin T |  | 48.96
PR | 998 | 02/26/21 | 606 | Cruz Gonzalez, Julio C |  | 19.28
PR | 998 | 02/26/21 | 606 | Cruz Gonzalez, Julio C |  | 85.68
PR | 998 | 02/26/21 | 608 | Cruz Reyes, Jose |  | 3.67
PR | 998 | 02/26/21 | 608 | Cruz Reyes, Jose |  | 78.34
PR | 998 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 29.72
PR | 998 | 02/26/21 | 629 | Martinez Reyes, Juan C |  | 53.78
PR | 998 | 02/26/21 | 639 | Romero Garza, Jesus I |  | 18.47
PR | 998 | 02/26/21 | 639 | Romero Garza, Jesus I |  | 70.38
PR | 998 | 02/26/21 | 641 | Sanders, Allen O |  | 46.47
PR | 998 | 02/26/21 | 641 | Sanders, Allen O |  | 132.19
PR | 998 | 03/05/21 | 65 | Cruz Gonzalez, Julio C |  | 34.27
PR | 998 | 03/05/21 | 99 | Sanders, Allen O |  | 88.82
PR | 998 | 03/12/21 | 224 | Sanders, Allen O |  | 12.39
PR | 998 | 03/19/21 | 338 | Sanders, Allen O |  | 35.76
PR | 998 | 03/26/21 | 569 | Sanders, Allen O |  | 12.62
PR | 998 | 04/02/21 | 55 | Sanders, Allen O |  | 10.52
PR | 998 | 04/09/21 | 159 | Sanders, Allen O |  | 4.21
PR | 998 | 04/30/21 | 627 | Sanders, Allen O |  | 6.31
AR | 999 | 04/19/19 | 613 | GRE Construction, LLC $Meeker |  | -98800 | 037329
AR | 999 | 04/19/19 | 613 | GRE Construction, LLC $Meeker |  | -17200 | 037329
AR | 999 | 04/19/19 | 613 | GRE Construction, LLC $Meeker |  | -94500 | 037329
AR | 999 | 04/19/19 | 613 | GRE Construction, LLC $Meeker |  | -1400 | 037329
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -17700 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -17600 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -23625 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -39100 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -28200 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -4900 | 037349
AR | 999 | 05/20/19 | 516 | GRE Construction, LLC $Meeker |  | -4900 | 037349
AR | 999 | 06/19/19 | 609 | GRE Construction, LLC $Meeker |  | -47250 | 037365
AR | 999 | 06/19/19 | 609 | GRE Construction, LLC $Meeker |  | -9735 | 037365
AR | 999 | 06/19/19 | 609 | GRE Construction, LLC $Meeker |  | -5850 | 037365
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -23625 | 037374
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -19550 | 037374
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -68145 | 037374
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -52650 | 037374
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -41020 | 037374
AR | 999 | 07/19/19 | 599 | GRE Construction, LLC $Meeker |  | -8530 | 037374
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -19550 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -9735 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -19470 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -3360 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -123060 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -20160 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -42620 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -20160 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -12881 | 037384
AR | 999 | 08/15/19 | 747 | GRE Construction, LLC $Meeker |  | -20160 | 037384
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -38940 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -14625 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -31692 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -35242 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -41020 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -119420 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -103048 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -6300 | 037407
AR | 999 | 09/20/19 | 563 | GRE Construction, LLC $Meeker |  | -62450 | 037407
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -48675 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -29250 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -126768 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -19680 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -44225 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -19680 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -6496 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -11748 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -12881 | 037424
AR | 999 | 10/18/19 | 537 | GRE Construction, LLC $Meeker |  | -6300 | 037424
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -47250 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -14625 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -5280 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -31692 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -114985 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -123414 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -19680 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -12600 | 037438
AR | 999 | 11/18/19 | 556 | GRE Construction, LLC $Meeker |  | -12600 | 037438
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -47250 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -19550 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -19470 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -11700 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -73910 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -21128 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -17690 | 037449
AR | 999 | 12/12/19 | 468 | GRE Construction, LLC $Meeker |  | -2100 | 037449
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -29205 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -17550 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -105640 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -35380 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -12300 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -12300 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -1136 | 037463
AR | 999 | 01/20/20 | 648 | GRE Construction, LLC $Meeker |  | -22417 | 037463
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -19550 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -53070 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -64955 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -3300 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -12300 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -4000 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -41475 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -59520 | 037478
AR | 999 | 02/19/20 | 443 | GRE Construction, LLC $Meeker |  | -13545 | 037478
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -48675 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -29250 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -5280 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -105640 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -19680 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -44225 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -19680 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -19680 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -55520 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -18045 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -1505 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -39600 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -39600 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -1456 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -1682 | 037489
AR | 999 | 03/20/20 | 649 | GRE Construction, LLC $Meeker |  | -20806 | 037489
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -44225 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -64955 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -5952 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -47616 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -13020 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -520 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -500 | 037501
AR | 999 | 05/20/20 | 447 | GRE Construction, LLC $Meeker |  | -1703 | 037501
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -73910 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -12300 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -5952 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -47616 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -11904 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -6561 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -3280 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 06/18/20 | 428 | GRE Construction, LLC $Meeker |  | -7680 | 037508
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -12300 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -53567 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -5952 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -11500 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -45927 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -40020 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -28385 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -9842 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -13300 | 037519
AR | 999 | 07/20/20 | 367 | GRE Construction, LLC $Meeker |  | -14812 | 037519
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -3300 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -12300 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -20460 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -13122 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -17150 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -12165 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -11500 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -26244 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -40020 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -40550 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -4200 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -14300 | 037524
AR | 999 | 08/20/20 | 453 | GRE Construction, LLC $Meeker |  | -9823 | 037524
AR | 999 | 09/21/20 | 350 | GRE Construction, LLC $Meeker |  | -26244 | 037536
AR | 999 | 09/21/20 | 350 | GRE Construction, LLC $Meeker |  | -17150 | 037536
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -23850 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -47615 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -4800 | 037543
AR | 999 | 10/20/20 | 425 | GRE Construction, LLC $Meeker |  | -1925 | 037543
AR | 999 | 11/18/20 | 328 | GRE Construction, LLC $Meeker |  | -11904 | 037551
AR | 999 | 11/18/20 | 328 | GRE Construction, LLC $Meeker |  | -23766 | 037551
AR | 999 | 11/18/20 | 328 | GRE Construction, LLC $Meeker |  | -11905 | 037551
AR | 999 | 11/18/20 | 328 | GRE Construction, LLC $Meeker |  | -3824 | 037551
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -35712 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -11904 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -4200 | 037566
AR | 999 | 12/14/20 | 236 | GRE Construction, LLC $Meeker |  | -1299 | 037566
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -11904 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -12560 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -12560 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -12560 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -8790 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -8790 | 037584
AR | 999 | 01/20/21 | 238 | GRE Construction, LLC $Meeker |  | -8790 | 037584
AR | 999 | 02/19/21 | 489 | GRE Construction, LLC $Meeker |  | -20460 | 037597
AR | 999 | 02/19/21 | 489 | GRE Construction, LLC $Meeker |  | -3770 | 037597
AR | 999 | 02/19/21 | 489 | GRE Construction, LLC $Meeker |  | -3770 | 037597
AR | 999 | 02/19/21 | 489 | GRE Construction, LLC $Meeker |  | -3770 | 037597
AR | 999 | 03/19/21 | 356 | GRE Construction, LLC $Meeker |  | -1 | 037617
AR | 999 | 03/19/21 | 356 | GRE Construction, LLC $Meeker |  | -30 | 037617