## 01 Overview
OWP #2060 · Marina Square
Compass Construction · 254 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 6156577
Revised budget (expenses) | 4490515.68
Forecast net profit | 1666061.32
Forecast margin | 27.06%
Progress to Date
Work complete (billed) | 6156577
Retention held | 300553.85
Earned less retention | 5856023.15
Balance to finish | 0
Percent complete | 100%
Transaction Totals by Source
Source | Dollars
GL | 191488.04
AP | 1004314.51
PR | 1379870.39
AR | -6156577

## 02 Job Info
JOB #2060 · COMPASS CONSTRUCTION · Marina Square (MSQ) — FULL PROJECT INFORMATION
Sourced from contract + ticket + GDrive folder + JDR. Subcontract MSQ Subcontract + SCO #2 Full Subcontract.
IDENTITY
OWP Job ID | 2060
Project Name | Marina Square (MSQ)
Site Address | 280 Washington Ave, Bremerton WA 98337
Subcontract Number | MSQ Subcontract + SCO #2 Full Subcontract
Effective Date | 2019-2022 (Tower 2 conversion of former hotel)
PROJECT TEAM — GENERAL CONTRACTOR
GC Legal Name | Compass Construction
GC Address | (Compass)
GC Contract Signatory | Compass
PROJECT TEAM — OWP
OWP Legal Name | One Way Plumbing LLC
OWP Address | 127 10th Street S Suite 200, Kirkland WA 98033
OWP Contract Signatory | Richard Donelson
OWP License # | ONEWAWP895BU
OWP Federal Tax ID | 27-4605928
PROJECT TEAM — OWNER
Owner Legal Name | Compass Construction (MSQ)
Owner Address | (MSQ entity)
PROJECT TEAM — DESIGN
Architect | TBD
MEP / Plumbing Engineer | TBD
INSURANCE & BONDING
Insurance Type | TBD
Retention | 5% per contract
CONTRACT
Contract Value | $5,307,510 original
CHANGE-EVENT META
Executed CO Count | 2
COR Count | TBD
RFI Count | TBD
ASI Count | TBD
CO Inventory | SCO #2 Full Subcontract (Tower 2 = former hotel L5-L9 conversion to extended-stay)
COR Themes | (see GDrive)
Key RFIs | (see GDrive)
DOCUMENTS ON FILE (GDrive)
Latest Job Ticket | Compass Marina Square Job Ticket - Updated 7-27-2022.pdf (2-tower)
GDrive Folder | Job Books - Completed Jobs/2060-...
Subfolders surveyed | # Job Ticket, ASI-RFI, Billing, Change Orders, Contract, Insurance, Meetings-Schedules, Permits, PO's, Plans, Submittals, Vendor Lien Waivers, Vendor Quotes
FIXTURE SCHEDULE (verified from latest Job Ticket)
Tower 1 Toilets | 139 | 128 Gerber 21-912 + 11 ADA Gerber 21-918
Tower 1 Lavs | 139 | Gerber 12-791 undercounter + Delta 559LF-TP
Tower 1 Tub/showers | 139 | 130 Aquatic 2603SMTE + 7 ADA + 2 SMTH (alcove)
Tower 1 Kitchen sinks | 129 | 118 Amerisink AS3337 + 11 ADA AS3336 + Delta 9659-DST
Tower 1 Dishwasher rough-ins | 129 | incl amenity
Tower 2 Toilets | 125 | Kohler K-3609 elongated
Tower 2 Lavs | 125 | Kohler K-2355 undercounter
Tower 2 Tub/showers | 132 | 94 Aquatic 2603SMTE + 24 SMTH L5 + 5 ADA + 1 ADA SMTH L5
Tower 2 Kitchen sinks | 119 | Elkay ECTRU12179T undercounter SS
VERIFIED MAIN FIXTURE COUNT | 1039
Per unit (254): 4.09
AUDIT NOTE (2026-04-25): First-pass count of 1176 was the all-itemized sum (included drains, hose bibs, condensate stacks, water heaters, appliance rough-ins). Verified main count of 1039 matches plumbing-engineering 'fixture schedule' definition (toilets + lavs + tub/showers + kitchen sinks + drinking fountains + mop sinks + dog wash + bar sinks). Same convention as 2051 (803) and 2052 (482).

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 5307510 | 6156577 | 849067
Executed change orders (net) | 0 | 849067 | 849067
Total contract value | 5307510 | 7005644 | 1698134
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 39900 | 39900 | 1166 | 38734 | 0 | 2.922%
101 | Takeoff & Purchase Labor | 66500 | 81000 | 30723 | 50277 | 0 | 37.93%
110 | Underground Labor | 63020 | 67110 | 27494.5 | 39615.5 | 0 | 40.97%
111 | Garage Labor | 271830 | 291758 | 110765.25 | 180992.75 | 0 | 37.96%
112 | Canout Labor | 54450 | 56815 | 41968 | 14847 | 0 | 73.87%
120 | Roughin Labor | 479570 | 618308 | 422639.89 | 195668.11 | 0 | 68.35%
130 | Finish Labor | 110025 | 129670 | 107754 | 21916 | 0 | 83.1%
140 | Gas Labor | 60000 | 55700 | 17179.5 | 38520.5 | 0 | 30.84%
141 | Water Main/Insulation Lab | 151330 | 159280 | 114150.95 | 45129.05 | 0 | 71.67%
142 | Mech Room Labor | 40000 | 40500 | 47501.5 | -7001.5 | 0 | 117.3%
150 | Warranty Labor | 0 | 0 | 829 | -829 | 0 | 0%
210 | Underground Material | 50000 | 50750 | 26001.45 | 24748.55 | 0 | 51.23%
211 | Garage Material | 246784 | 250234 | 39400.27 | 210833.73 | 0 | 15.75%
212 | Canout Material | 54450 | 54950 | 24014.23 | 30935.77 | 0 | 43.7%
220 | Roughin Material | 205194 | 376194 | 162471.68 | 213722.32 | 0 | 43.19%
230 | Finish Material | 875550 | 998490 | 539813.97 | 458676.03 | 0 | 54.06%
240 | Gas Material | 78000 | 71950 | 13263.56 | 58686.44 | 0 | 18.43%
241 | Water Main/Insulation Mat | 189170 | 195680 | 134603.6 | 61076.4 | 0 | 68.79%
242 | Mech Room Material | 40000 | 40000 | 69474.91 | -29474.91 | 0 | 173.7%
600 | Subcontractor | 2000 | 8300 | 25781.65 | -17481.65 | 0 | 310.6%
601 | Engineering/Plans | 90000 | 120000 | 100995.25 | 19004.75 | 0 | 84.16%
602 | Rental Equipment | 10000 | 10000 | 1673.84 | 8326.16 | 0 | 16.74%
603 | Permits & Licenses | 32000 | 35400 | 29026.58 | 6373.42 | 0 | 82%
607 | Other Expenses | 30000 | 30000 | 30712.97 | -712.97 | 0 | 102.4%
995 | Payroll Burden | 499229.44 | 590721.42 | 385611.57 | 205109.85 | 0 | 65.28%
998 | Payroll Taxes | 102251.81 | 117805.26 | 70655.82 | 47149.44 | 0 | 59.98%
TOTAL |  | 3841254.25 | 4490515.68 | 2575672.94 | 1914842.74 | 0 | 57.36%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 1540041 | 922171.59 | 617869.41 | 59.88%
Material | 8 | 2038248 | 1009043.67 | 1029204.33 | 49.51%
Overhead | 5 | 203700 | 188190.29 | 15509.71 | 92.39%
Burden | 2 | 708526.68 | 456267.39 | 252259.29 | 64.4%
TOTAL | 26 | 4490515.68 | 2575672.94 | 1914842.74 | 57.36%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 39900 | 1166 | 38734 | -97.08% | UNDER
101 | Takeoff & Purchase Labor | 81000 | 30723 | 50277 | -62.07% | UNDER
110 | Underground Labor | 67110 | 27494.5 | 39615.5 | -59.03% | UNDER
111 | Garage Labor | 291758 | 110765.25 | 180992.75 | -62.04% | UNDER
112 | Canout Labor | 56815 | 41968 | 14847 | -26.13% | UNDER
120 | Roughin Labor | 618308 | 422639.89 | 195668.11 | -31.65% | UNDER
130 | Finish Labor | 129670 | 107754 | 21916 | -16.9% | UNDER
140 | Gas Labor | 55700 | 17179.5 | 38520.5 | -69.16% | UNDER
141 | Water Main/Insulation Lab | 159280 | 114150.95 | 45129.05 | -28.33% | UNDER
142 | Mech Room Labor | 40500 | 47501.5 | -7001.5 | 17.29% | OVER
150 | Warranty Labor | 0 | 829 | -829 | 0% | UNBUDGETED
210 | Underground Material | 50750 | 26001.45 | 24748.55 | -48.77% | UNDER
211 | Garage Material | 250234 | 39400.27 | 210833.73 | -84.25% | UNDER
212 | Canout Material | 54950 | 24014.23 | 30935.77 | -56.3% | UNDER
220 | Roughin Material | 376194 | 162471.68 | 213722.32 | -56.81% | UNDER
230 | Finish Material | 998490 | 539813.97 | 458676.03 | -45.94% | UNDER
240 | Gas Material | 71950 | 13263.56 | 58686.44 | -81.57% | UNDER
241 | Water Main/Insulation Mat | 195680 | 134603.6 | 61076.4 | -31.21% | UNDER
242 | Mech Room Material | 40000 | 69474.91 | -29474.91 | 73.69% | CRITICAL
600 | Subcontractor | 8300 | 25781.65 | -17481.65 | 210.6% | CRITICAL
601 | Engineering/Plans | 120000 | 100995.25 | 19004.75 | -15.84% | UNDER
602 | Rental Equipment | 10000 | 1673.84 | 8326.16 | -83.26% | UNDER
603 | Permits & Licenses | 35400 | 29026.58 | 6373.42 | -18% | UNDER
607 | Other Expenses | 30000 | 30712.97 | -712.97 | 2.377% | ON
995 | Payroll Burden | 590721.42 | 385611.57 | 205109.85 | -34.72% | UNDER
998 | Payroll Taxes | 117805.26 | 70655.82 | 47149.44 | -40.02% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Keller Supply Company | 338444.3 | 75 | 33.7%
Rosen Supply Kirkland | 196759.71 | 212 | 19.59%
California Hydronics Corp | 111606.23 | 4 | 11.11%
Franklin Engineering | 100995.25 | 17 | 10.06%
Consolidated Supply Co. | 82037.71 | 33 | 8.169%
Ferguson Enterprises, Inc. #3007 | 68801.51 | 40 | 6.851%
Capital One Credit Card | 40021.65 | 195 | 3.985%
Mechanical Resource Services, Inc. | 17750 | 2 | 1.767%
Washington State Ferries | 17506.05 | 29 | 1.743%
Old Castle Infrastructure, Inc. | 9534 | 3 | 0.9493%
Chemical Products Company | 6300 | 2 | 0.6273%
Granite Precast | 5141 | 1 | 0.5119%
Bank of America CC | 4482.3 | 23 | 0.4463%
Core & Main LP $HD Supply Waterworks | 1822.07 | 2 | 0.1814%
United Rentals, Inc. | 1419.28 | 2 | 0.1413%
Scan2Core, Inc. | 675 | 1 | 0.06721%
Patchworks, Inc. | 650 | 1 | 0.06472%
Sunbelt Rentals, Inc. | 199.43 | 1 | 0.01986%
ACME Corp | 169.02 | 1 | 0.01683%
AJ's Backflow Testing | 0 | 2 | 0%
TOTAL AP | 1004314.51 | 646

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Holmes, Anthony R | 3946 | 188262 | 47.7096 | LEAD/SUPERVISOR
Gordillo, Emanuel D | 3107.5 | 59762 | 19.2315 | APPRENTICE/HELPER
Platero Navas, Julio A | 2337.5 | 43592 | 18.649 | APPRENTICE/HELPER
Lovo, German G | 2252 | 78288 | 34.7638 | JOURNEYMAN
Gonzalez Hernandez, Josue | 1562.5 | 60737 | 38.8717 | LEAD/SUPERVISOR
Barnhart, Joseph N | 1389 | 78828 | 56.7516 | LEAD/SUPERVISOR
Velasquez Cruz, Denis M | 1384 | 54028 | 39.0376 | LEAD/SUPERVISOR
Platero Navas, Mario N | 1380 | 24817 | 17.9833 | APPRENTICE/HELPER
Velasquez Cruz, Osman N | 1353 | 45496 | 33.626 | JOURNEYMAN
Lee, Ha Nul | 1176 | 31266 | 26.5867 | JOURNEYMAN
Barnhart, Thomas L | 1148 | 44128 | 38.439 | LEAD/SUPERVISOR
Cruz, Azael S | 1051 | 29400 | 27.9734 | JOURNEYMAN
Ortiz Carmona, Jose | 1015 | 33364 | 32.8709 | JOURNEYMAN
Hoeg, Xavier A | 536 | 9648 | 18 | APPRENTICE/HELPER
Waites, Thaddeus Z | 477 | 23621 | 49.5199 | LEAD/SUPERVISOR
Gutierrez, Brian A | 463 | 11467 | 24.7667 | JOURNEYMAN
Donelson, Richard T | 393 | 24562 | 62.4987 | LEAD/SUPERVISOR
Castro Urena, Yanely | 365.5 | 6460 | 17.6744 | APPRENTICE/HELPER
Martinez Reyes, Juan C | 213 | 7643 | 35.8826 | JOURNEYMAN
Sanders, Allen O | 179.5 | 10793 | 60.1281 | LEAD/SUPERVISOR
Rodriguez Arevalos, Christian | 173 | 5190 | 30 | JOURNEYMAN
Hubbard, Robert W | 138.5 | 7658 | 55.2924 | LEAD/SUPERVISOR
Stahlschmidt, John P | 126 | 3002 | 23.8254 | JOURNEYMAN
Paco Leyva, Orlando | 122 | 5104 | 41.8361 | LEAD/SUPERVISOR
Vazquez Popoca, Jose N | 117 | 3321 | 28.3846 | JOURNEYMAN
Ramos Herrera, Franklin J | 116 | 3158 | 27.2241 | JOURNEYMAN
Eliassen, Cory H | 113.5 | 4091 | 36.0441 | JOURNEYMAN
Gerard, Jeffrey S | 98 | 5574 | 56.8776 | LEAD/SUPERVISOR
Sepulveda Gonzalez, Alfredo | 75.5 | 3398 | 45.0066 | LEAD/SUPERVISOR
Taylor, Evan R | 69.5 | 2759 | 39.6978 | JOURNEYMAN
Lara, Eric E | 65.5 | 2198 | 33.5573 | JOURNEYMAN
Balderas Ortiz, Ricardo I | 45 | 1620 | 36 | LEAD/SUPERVISOR
Cruz Reyes, Jose | 42 | 1548 | 36.8571 | LEAD/SUPERVISOR
Anderson, Richard P | 41 | 2046 | 49.9024 | LEAD/SUPERVISOR
Hernandez Gonzalez, Osbaldo | 27 | 1015 | 37.5926 | JOURNEYMAN
Trower-Kelly, Fidel D | 26 | 746 | 28.6923 | JOURNEYMAN
Cruz Gonzalez, Julio C | 25 | 816 | 32.64 | JOURNEYMAN
Barbosa, Michael S | 16 | 628 | 39.25 | JOURNEYMAN
Ross, Kelli M | 16 | 688 | 43 | LEAD/SUPERVISOR
Johnson, Jake E | 14 | 700 | 50 | LEAD/SUPERVISOR
McCabe, Thomas C | 9.5 | 556 | 58.5263 | LEAD/SUPERVISOR
Reyes Cruz, Denis A | 8 | 264 | 33 | JOURNEYMAN
Castro Hernandez, Jose A | 8 | 352 | 44 | LEAD/SUPERVISOR
Amaya Gonzalez, Edilberto A | 8 | 432 | 54 | OT-ONLY
Galdamez, Dagoberto A | 8 | 396 | 49.5 | OT-ONLY
Romero Garza, Jesus I | 4.5 | 182 | 40.4444 | OT-ONLY

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 19 | 11088.5 | 514202 | 40.71%
JOURNEYMAN | 19 | 8405.5 | 264112 | 30.86%
APPRENTICE/HELPER | 5 | 7726.5 | 144278 | 28.36%
OT-ONLY | 3 | 20.5 | 1010 | 0.07525%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 27241
Active workers | 46
Hours per unit (to date) | 107.2
Revenue per labor hour (billed) | 226
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 27.06% | 34% | -6.939%
Roughin labor share (code 120) | 40.15% | 45% | -4.851%
Top vendor concentration | 33.7% | 38% | -4.301%
Hours per unit | 107.248 | 95 | 12.248

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Mech Room Labor (142) over revised | ⚠ WATCH | Actual $47,502 vs revised $40,500 (+17%) — monitor
Mech Room Material (242) CRITICAL overrun | ⚠ WATCH | Actual $69,475 vs revised $40,000 (+74%) — needs immediate attention
Subcontractor (600) CRITICAL overrun | ⚠ WATCH | Actual $25,782 vs revised $8,300 (+211%) — needs immediate attention
Top vendor concentration (Keller Supply Compan) | ✓ OK | 34% of AP ($338,444) — acceptable
Retention aging | ✓ OK | $300,554 held · 4.9% of billed · standard range
Forecast margin | ✓ OK | 27.1% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 2575672.94 | 2575672.94 | 0
Revenue billed (AR ·-1) | -6156577 | 6156577 | -12313154
AP source total |  | 1004314.51 | —
PR source total |  | 1379870.39 | —
GL source total |  | 191488.04 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-25 | v1.0 · live | Initial build for #2060 live project. 17-tab JCR schema on revised budget basis.