## Summary
#2060 · Marina Square
Compass Construction · 254 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
6156577 | 27.06% | 6156577 | 0
Key facts
Original contract |  | 5307510
Revised contract (CO impact) |  | 6156577
Executed COs (net) |  | 849067
Retention held |  | 300553.85
Revised expense budget |  | 4490515.68
Forecast net profit |  | 1666061.32
Percent complete |  | 100%
Live signals
Mech Room Labor (142) over | ⚠ WATCH | Actual $47,502 vs revised $40,500 (+17%) — monitor
Mech Room Material (242) CRITICAL | ⚠ WATCH | Actual $69,475 vs revised $40,000 (+74%) — needs attention
Subcontractor (600) CRITICAL | ⚠ WATCH | Actual $25,782 vs revised $8,300 (+211%) — needs attention
Top vendor (Keller Supply Compan) | ✓ OK | 34% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 27.1% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Keller Supply Company | 75 | 338444.3 | 33.7%
Rosen Supply Kirkland | 212 | 196759.71 | 19.59%
California Hydronics Corp | 4 | 111606.23 | 11.11%
Franklin Engineering | 17 | 100995.25 | 10.06%
Consolidated Supply Co. | 33 | 82037.71 | 8.169%
Ferguson Enterprises, Inc. #3007 | 40 | 68801.51 | 6.851%

## Transactions
Transactions Detail
JDR source transactions for job #2060 · 5748 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 06/14/19 | 523 | Donelson, Richard T | 5 | 312.5 | 24103
PR | 100 | 08/23/19 | 874 | Gerard, Jeffrey S | 5 | 275 | 924932
PR | 100 | 11/08/19 | 254 | Gerard, Jeffrey S | 4 | 232 | 925773
PR | 100 | 02/07/20 | 103 | Gerard, Jeffrey S | 2 | 116 | 26851
PR | 100 | 02/14/20 | 313 | Gerard, Jeffrey S | 1 | 58 | 926929
PR | 100 | 03/26/20 | 820 | Donelson, Richard T | 1 | 62.5 | 927396
PR | 100 | 06/11/21 | 271 | Gerard, Jeffrey S | 1 | 60 | 930977
PR | 100 | 04/29/22 | 1111 | Johnson, Jake E | 1 | 50 | 35167
PR | 101 | 06/21/19 | 693 | Donelson, Richard T | 7 | 437.5 | 24179
PR | 101 | 06/28/19 | 910 | Donelson, Richard T | 11 | 687.5 | 24254
PR | 101 | 07/05/19 | 81 | Donelson, Richard T | 9 | 562.5 | 924329
PR | 101 | 07/12/19 | 352 | Donelson, Richard T | 1 | 62.5 | 924404
PR | 101 | 07/19/19 | 585 | Donelson, Richard T | 13 | 812.5 | 24484
PR | 101 | 07/26/19 | 685 | Donelson, Richard T | 4 | 250 | 24634
PR | 101 | 08/02/19 | 76 | Donelson, Richard T | 1 | 62.5 | 924707
PR | 101 | 08/02/19 | 77 | Gerard, Jeffrey S | 5 | 275 | 924708
PR | 101 | 08/09/19 | 328 | Donelson, Richard T | 7 | 437.5 | 924781
PR | 101 | 08/09/19 | 329 | Gerard, Jeffrey S | 3 | 165 | 924782
PR | 101 | 08/16/19 | 636 | Donelson, Richard T | 7 | 437.5 | 924855
PR | 101 | 08/16/19 | 637 | Gerard, Jeffrey S | 4 | 220 | 924856
PR | 101 | 08/23/19 | 874 | Gerard, Jeffrey S | 2 | 110 | 924932
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 5 | 312.5 | 25008
PR | 101 | 08/30/19 | 1064 | Donelson, Richard T | 1 | 62.5 | 25008
PR | 101 | 08/30/19 | 1065 | Gerard, Jeffrey S | 4 | 220 | 25009
PR | 101 | 09/06/19 | 85 | Donelson, Richard T | 2 | 125 | 925083
PR | 101 | 09/06/19 | 86 | Gerard, Jeffrey S | 2 | 110 | 925084
PR | 101 | 09/13/19 | 308 | Donelson, Richard T | 12 | 750 | 25157
PR | 101 | 09/13/19 | 309 | Gerard, Jeffrey S | 3 | 165 | 25158
PR | 101 | 09/20/19 | 546 | Donelson, Richard T | 10 | 625 | 925232
PR | 101 | 09/20/19 | 547 | Gerard, Jeffrey S | 3 | 165 | 925233
PR | 101 | 09/27/19 | 705 | Donelson, Richard T | 5 | 312.5 | 925310
PR | 101 | 09/27/19 | 706 | Gerard, Jeffrey S | 3 | 165 | 925311
PR | 101 | 10/04/19 | 81 | Donelson, Richard T | 3 | 187.5 | 25388
PR | 101 | 10/04/19 | 82 | Gerard, Jeffrey S | 3 | 165 | 25389
PR | 101 | 10/11/19 | 334 | Donelson, Richard T | 3 | 187.5 | 925468
PR | 101 | 10/11/19 | 335 | Gerard, Jeffrey S | 2 | 110 | 925469
PR | 101 | 10/18/19 | 527 | Donelson, Richard T | 1 | 62.5 | 25544
PR | 101 | 10/25/19 | 664 | Donelson, Richard T | 6 | 375 | 925504
PR | 101 | 10/25/19 | 665 | Gerard, Jeffrey S | 2 | 110 | 925505
PR | 101 | 11/01/19 | 80 | Donelson, Richard T | 10 | 625 | 925696
PR | 101 | 11/01/19 | 81 | Gerard, Jeffrey S | 4 | 232 | 925697
PR | 101 | 11/08/19 | 253 | Donelson, Richard T | 17 | 1062.5 | 925772
PR | 101 | 11/08/19 | 254 | Gerard, Jeffrey S | 5 | 290 | 925773
PR | 101 | 11/15/19 | 512 | Donelson, Richard T | 8 | 500 | 925848
PR | 101 | 11/15/19 | 513 | Gerard, Jeffrey S | 4 | 232 | 925849
PR | 101 | 11/22/19 | 685 | Gerard, Jeffrey S | 3 | 174 | 925924
PR | 101 | 11/27/19 | 918 | Gerard, Jeffrey S | 5 | 290 | 925999
PR | 101 | 12/06/19 | 104 | Donelson, Richard T | 5 | 312.5 | 26076
PR | 101 | 12/06/19 | 105 | Gerard, Jeffrey S | 1 | 58 | 26077
PR | 101 | 12/13/19 | 394 | Barnhart, Joseph N | 3 | 162 | 26159
PR | 101 | 12/13/19 | 465 | Donelson, Richard T | 3 | 187.5 | 926231
PR | 101 | 12/13/19 | 466 | Gerard, Jeffrey S | 3 | 174 | 926232
PR | 101 | 12/20/19 | 618 | Donelson, Richard T | 2 | 125 | 926307
PR | 101 | 12/27/19 | 776 | Donelson, Richard T | 1 | 62.5 | 26384
PR | 101 | 01/03/20 | 81 | Donelson, Richard T | 6 | 375 | 926462
PR | 101 | 01/10/20 | 280 | Barnhart, Joseph N | 8.5 | 459 | 26467
PR | 101 | 01/10/20 | 352 | Donelson, Richard T | 10 | 625 | 26540
PR | 101 | 01/17/20 | 618 | Donelson, Richard T | 8 | 500 | 926617
PR | 101 | 01/17/20 | 619 | Gerard, Jeffrey S | 4 | 232 | 926618
PR | 101 | 01/24/20 | 750 | Donelson, Richard T | 5 | 312.5 | 926400
PR | 101 | 01/24/20 | 751 | Gerard, Jeffrey S | 2 | 116 | 926401
PR | 101 | 01/31/20 | 911 | Donelson, Richard T | 8 | 500 | 26772
PR | 101 | 02/07/20 | 102 | Donelson, Richard T | 2 | 125 | 26850
PR | 101 | 02/07/20 | 103 | Gerard, Jeffrey S | 3 | 174 | 26851
PR | 101 | 02/14/20 | 312 | Donelson, Richard T | 1 | 62.5 | 926928
PR | 101 | 02/21/20 | 528 | Donelson, Richard T | 3 | 187.5 | 27006
PR | 101 | 02/21/20 | 529 | Gerard, Jeffrey S | 1 | 58 | 27007
PR | 101 | 02/28/20 | 758 | Gerard, Jeffrey S | 3 | 174 | 927086
PR | 101 | 03/06/20 | 119 | Donelson, Richard T | 4 | 250 | 927163
PR | 101 | 03/06/20 | 120 | Gerard, Jeffrey S | 1 | 58 | 927164
PR | 101 | 03/13/20 | 383 | Donelson, Richard T | 7 | 437.5 | 927244
PR | 101 | 03/13/20 | 384 | Gerard, Jeffrey S | 1 | 58 | 927245
PR | 101 | 03/20/20 | 641 | Donelson, Richard T | 3 | 187.5 | 927321
PR | 101 | 03/20/20 | 642 | Gerard, Jeffrey S | 1 | 58 | 927322
PR | 101 | 03/26/20 | 820 | Donelson, Richard T | 2 | 125 | 927396
PR | 101 | 03/26/20 | 821 | Gerard, Jeffrey S | 1 | 58 | 927397
PR | 101 | 04/03/20 | 42 | Donelson, Richard T | 2 | 125 | 927434
PR | 101 | 04/10/20 | 99 | Donelson, Richard T | 4 | 250 | 927474
PR | 101 | 04/17/20 | 288 | Donelson, Richard T | 2 | 125 | 927551
PR | 101 | 05/08/20 | 231 | Donelson, Richard T | 1 | 62.5 | 927784
PR | 101 | 06/05/20 | 67 | Gerard, Jeffrey S | 1 | 58 | 928056
PR | 101 | 07/02/20 | 50 | Donelson, Richard T | 5 | 312.5 | 928293
PR | 101 | 07/17/20 | 265 | Barnhart, Joseph N | 2 | 108 | 28345
PR | 101 | 07/17/20 | 310 | Gerard, Jeffrey S | 1 | 58 | 928390
PR | 101 | 07/24/20 | 448 | Donelson, Richard T | 5 | 312.5 | 928440
PR | 101 | 07/24/20 | 449 | Gerard, Jeffrey S | 1 | 58 | 928441
PR | 101 | 07/31/20 | 543 | Donelson, Richard T | 3 | 187.5 | 928489
PR | 101 | 08/07/20 | 128 | Donelson, Richard T | 10 | 625 | 928531
PR | 101 | 08/14/20 | 332 | Donelson, Richard T | 7 | 437.5 | 928572
PR | 101 | 08/21/20 | 459 | Donelson, Richard T | 4 | 250 | 928613
PR | 101 | 08/28/20 | 604 | Donelson, Richard T | 1 | 62.5 | 928657
PR | 101 | 09/04/20 | 49 | Donelson, Richard T | 1 | 62.5 | 928705
PR | 101 | 10/09/20 | 198 | Donelson, Richard T | 2 | 125 | 928947
PR | 101 | 11/13/20 | 230 | Donelson, Richard T | 3 | 187.5 | 29181
PR | 101 | 12/31/20 | 627 | Donelson, Richard T | 1 | 62.5 | 929555
PR | 101 | 01/08/21 | 52 | Donelson, Richard T | 1 | 62.5 | 929603
PR | 101 | 01/15/21 | 171 | Donelson, Richard T | 2 | 125 | 929656
PR | 101 | 01/22/21 | 306 | Donelson, Richard T | 2 | 125 | 929706
PR | 101 | 01/29/21 | 432 | Donelson, Richard T | 1 | 62.5 | 929757
PR | 101 | 02/05/21 | 121 | Donelson, Richard T | 1 | 62.5 | 929812
PR | 101 | 02/12/21 | 256 | Barnhart, Joseph N | 6 | 324 | 29817
PR | 101 | 02/12/21 | 307 | Donelson, Richard T | 3 | 187.5 | 929868
PR | 101 | 02/26/21 | 649 | Donelson, Richard T | 1 | 62.5 | 929985
PR | 101 | 03/19/21 | 346 | Donelson, Richard T | 1 | 62.5 | 930159
PR | 101 | 04/02/21 | 64 | Donelson, Richard T | 1 | 62.5 | 930283
PR | 101 | 04/09/21 | 167 | Donelson, Richard T | 5 | 312.5 | 930345
PR | 101 | 04/16/21 | 314 | Donelson, Richard T | 8 | 500 | 930412
PR | 101 | 04/16/21 | 314 | Donelson, Richard T | 2 | 125 | 930412
PR | 101 | 04/23/21 | 466 | Donelson, Richard T | 2 | 125 | 930479
PR | 101 | 04/30/21 | 637 | Donelson, Richard T | 4 | 250 | 930547
PR | 101 | 05/07/21 | 106 | Donelson, Richard T | 8 | 500 | 930619
PR | 101 | 05/14/21 | 310 | Donelson, Richard T | 3 | 187.5 | 930688
PR | 101 | 05/21/21 | 456 | Donelson, Richard T | 2 | 125 | 930757
PR | 101 | 05/28/21 | 700 | Donelson, Richard T | 1 | 62.5 | 930829
PR | 101 | 06/04/21 | 99 | Donelson, Richard T | 4 | 250 | 930904
PR | 101 | 06/11/21 | 270 | Donelson, Richard T | 8 | 500 | 930976
PR | 101 | 06/18/21 | 475 | Donelson, Richard T | 5 | 312.5 | 931053
PR | 101 | 06/25/21 | 672 | Donelson, Richard T | 1 | 62.5 | 931131
PR | 101 | 07/02/21 | 78 | Donelson, Richard T | 2 | 125 | 931201
PR | 101 | 07/16/21 | 393 | Donelson, Richard T | 4 | 250 | 931354
PR | 101 | 07/23/21 | 565 | Donelson, Richard T | 2 | 125 | 931433
PR | 101 | 08/06/21 | 116 | Donelson, Richard T | 2 | 125 | 931594
PR | 101 | 08/20/21 | 661 | Donelson, Richard T | 1 | 62.5 | 931754
PR | 101 | 09/03/21 | 87 | Gerard, Jeffrey S | 1 | 60 | 931919
PR | 101 | 09/24/21 | 572 | Donelson, Richard T | 1 | 62.5 | 932171
PR | 101 | 09/24/21 | 573 | Gerard, Jeffrey S | 1 | 60 | 932172
PR | 101 | 10/08/21 | 381 | Donelson, Richard T | 2 | 125 | 932352
PR | 101 | 10/15/21 | 645 | Donelson, Richard T | 1 | 62.5 | 32442
PR | 101 | 10/29/21 | 1092 | Donelson, Richard T | 1 | 62.5 | 932629
PR | 101 | 11/24/21 | 659 | Donelson, Richard T | 1 | 62.5 | 932996
PR | 101 | 12/10/21 | 281 | Donelson, Richard T | 2 | 125 | 933180
PR | 101 | 12/23/21 | 827 | Donelson, Richard T | 4 | 250 | 933509
PR | 101 | 02/18/22 | 577 | Donelson, Richard T | 3 | 187.5 | 934269
PR | 101 | 02/18/22 | 578 | Gerard, Jeffrey S | 1 | 60 | 934270
PR | 101 | 03/04/22 | 134 | Donelson, Richard T | 3 | 187.5 | 34458
PR | 101 | 03/11/22 | 391 | Johnson, Jake E | 2 | 100 | 34513
PR | 101 | 03/18/22 | 676 | Johnson, Jake E | 1 | 50 | 34609
PR | 101 | 04/01/22 | 108 | Donelson, Richard T | 1 | 62.5 | 934835
PR | 101 | 04/22/22 | 889 | Donelson, Richard T | 1 | 62.5 | 935113
PR | 101 | 04/29/22 | 1111 | Johnson, Jake E | 2 | 100 | 35167
PR | 101 | 05/20/22 | 681 | Donelson, Richard T | 8 | 500 | 935472
PR | 101 | 05/27/22 | 951 | Donelson, Richard T | 4 | 250 | 935561
PR | 101 | 06/03/22 | 56 | Johnson, Jake E | 1 | 50 | 35615
PR | 101 | 06/03/22 | 93 | Donelson, Richard T | 3 | 187.5 | 935652
PR | 101 | 06/10/22 | 301 | Donelson, Richard T | 5 | 312.5 | 935740
PR | 101 | 06/17/22 | 549 | Donelson, Richard T | 5 | 312.5 | 935829
PR | 101 | 06/24/22 | 851 | Donelson, Richard T | 1 | 62.5 | 935917
PR | 101 | 07/15/22 | 414 | Johnson, Jake E | 1 | 50 | 36137
PR | 101 | 07/29/22 | 798 | Gerard, Jeffrey S | 1 | 62.5 | 936343
PR | 101 | 09/09/22 | 241 | Johnson, Jake E | 1 | 50 | 36783
PR | 101 | 09/16/22 | 470 | Johnson, Jake E | 1 | 50 | 36860
PR | 101 | 10/21/22 | 518 | Johnson, Jake E | 1 | 50 | 37267
PR | 101 | 11/18/22 | 411 | Johnson, Jake E | 1 | 50 | 37613
PR | 101 | 11/23/22 | 555 | Johnson, Jake E | 1 | 50 | 37703
PR | 101 | 12/02/22 | 49 | Johnson, Jake E | 1 | 50 | 37788
PR | 110 | 04/26/19 | 744 | Barnhart, Joseph N | 3 | 150 | 23501
PR | 110 | 08/02/19 | 8 | Barnhart, Joseph N | 6 | 300 | 24639
PR | 110 | 08/09/19 | 260 | Barnhart, Joseph N | 5 | 250 | 24713
PR | 110 | 08/16/19 | 567 | Barnhart, Joseph N | 17 | 850 | 24786
PR | 110 | 08/16/19 | 606 | Martinez Reyes, Juan C | 8 | 264 | 24825
PR | 110 | 08/23/19 | 802 | Barbosa, Michael S | 8 | 232 | 24860
PR | 110 | 08/23/19 | 803 | Barnhart, Joseph N | 17 | 850 | 24861
PR | 110 | 08/23/19 | 843 | Martinez Reyes, Juan C | 1 | 49.5 | 24901
PR | 110 | 08/23/19 | 843 | Martinez Reyes, Juan C | 24 | 792 | 24901
PR | 110 | 08/23/19 | 847 | Paco Leyva, Orlando | 24 | 960 | 24905
PR | 110 | 08/23/19 | 849 | Ramos Herrera, Franklin J | 2 | 78 | 24907
PR | 110 | 08/23/19 | 849 | Ramos Herrera, Franklin J | 16 | 416 | 24907
PR | 110 | 08/30/19 | 994 | Barnhart, Joseph N | 15 | 750 | 24936
PR | 110 | 08/30/19 | 1034 | Martinez Reyes, Juan C | 8 | 264 | 24976
PR | 110 | 08/30/19 | 1038 | Paco Leyva, Orlando | 8 | 320 | 24980
PR | 110 | 08/30/19 | 1040 | Ramos Herrera, Franklin J | 8 | 208 | 24982
PR | 110 | 09/06/19 | 15 | Barnhart, Joseph N | 11 | 550 | 25013
PR | 110 | 09/06/19 | 55 | Martinez Reyes, Juan C | 6 | 198 | 25053
PR | 110 | 09/13/19 | 239 | Barnhart, Joseph N | 19 | 950 | 25088
PR | 110 | 09/13/19 | 278 | Martinez Reyes, Juan C | 17 | 561 | 25127
PR | 110 | 09/13/19 | 282 | Paco Leyva, Orlando | 1 | 60 | 25131
PR | 110 | 09/13/19 | 282 | Paco Leyva, Orlando | 17 | 680 | 25131
PR | 110 | 09/13/19 | 284 | Ramos Herrera, Franklin J | 18 | 468 | 25133
PR | 110 | 09/20/19 | 476 | Barnhart, Joseph N | 8 | 400 | 25162
PR | 110 | 09/27/19 | 632 | Barnhart, Joseph N | 34 | 1700 | 25237
PR | 110 | 09/27/19 | 679 | Paco Leyva, Orlando | 24 | 960 | 25284
PR | 110 | 09/27/19 | 681 | Ramos Herrera, Franklin J | 24 | 624 | 25286
PR | 110 | 10/04/19 | 8 | Barnhart, Joseph N | 20 | 1000 | 25315
PR | 110 | 10/04/19 | 55 | Paco Leyva, Orlando | 16 | 640 | 25362
PR | 110 | 10/04/19 | 57 | Ramos Herrera, Franklin J | 16 | 416 | 25364
PR | 110 | 10/11/19 | 263 | Barnhart, Joseph N | 2 | 100 | 25396
PR | 110 | 10/18/19 | 457 | Barnhart, Joseph N | 1 | 50 | 25473
PR | 110 | 10/18/19 | 499 | Martinez Reyes, Juan C | 8 | 264 | 25516
PR | 110 | 10/25/19 | 592 | Barnhart, Joseph N | 2.5 | 125 | 25549
PR | 110 | 11/01/19 | 8 | Barnhart, Joseph N | 3 | 162 | 25625
PR | 110 | 11/08/19 | 182 | Barnhart, Joseph N | 23 | 1242 | 25701
PR | 110 | 11/08/19 | 211 | Holmes, Anthony R | 1 | 66 | 25730
PR | 110 | 11/08/19 | 211 | Holmes, Anthony R | 24 | 1056 | 25730
PR | 110 | 11/08/19 | 224 | Martinez Reyes, Juan C | 24 | 888 | 25743
PR | 110 | 11/08/19 | 228 | Paco Leyva, Orlando | 16 | 704 | 25747
PR | 110 | 11/08/19 | 230 | Ramos Herrera, Franklin J | 16 | 480 | 25749
PR | 110 | 11/15/19 | 442 | Barnhart, Joseph N | 23 | 1242 | 25777
PR | 110 | 11/15/19 | 483 | Martinez Reyes, Juan C | 29 | 1073 | 25819
PR | 110 | 11/15/19 | 487 | Paco Leyva, Orlando | 8 | 352 | 25823
PR | 110 | 11/15/19 | 489 | Ramos Herrera, Franklin J | 8 | 240 | 25825
PR | 110 | 11/27/19 | 888 | Martinez Reyes, Juan C | 8 | 296 | 25969
PR | 110 | 12/06/19 | 33 | Barnhart, Joseph N | 5 | 270 | 26005
PR | 110 | 12/06/19 | 61 | Hoeg, Xavier A | 10 | 180 | 26033
PR | 110 | 12/06/19 | 62 | Holmes, Anthony R | 8 | 352 | 26034
PR | 110 | 03/06/20 | 78 | Hubbard, Robert W | 2 | 108 | 27122
PR | 110 | 02/19/21 | 442 | Gordillo, Emanuel D | 8 | 128 | 29895
PR | 110 | 02/19/21 | 444 | Holmes, Anthony R | 8 | 352 | 29897
PR | 110 | 04/16/21 | 279 | Gordillo, Emanuel D | 8 | 136 | 30377
PR | 110 | 04/16/21 | 284 | Holmes, Anthony R | 7 | 322 | 30382
PR | 110 | 05/14/21 | 276 | Holmes, Anthony R | 3 | 138 | 30655
PR | 110 | 06/11/21 | 236 | Holmes, Anthony R | 10 | 460 | 30942
PR | 110 | 10/21/22 | 477 | Barnhart, Joseph N | 12 | 768 | 37226
PR | 111 | 11/27/19 | 847 | Barnhart, Joseph N | 13 | 702 | 25928
PR | 111 | 11/27/19 | 875 | Holmes, Anthony R | 16 | 704 | 25956
PR | 111 | 12/06/19 | 33 | Barnhart, Joseph N | 3 | 162 | 26005
PR | 111 | 12/06/19 | 61 | Hoeg, Xavier A | 14 | 252 | 26033
PR | 111 | 12/06/19 | 62 | Holmes, Anthony R | 14 | 616 | 26034
PR | 111 | 12/13/19 | 394 | Barnhart, Joseph N | 5 | 270 | 26159
PR | 111 | 12/13/19 | 422 | Hoeg, Xavier A | 25 | 450 | 26187
PR | 111 | 12/13/19 | 423 | Holmes, Anthony R | 29 | 1276 | 26188
PR | 111 | 12/20/19 | 547 | Barnhart, Joseph N | 8 | 432 | 26236
PR | 111 | 12/20/19 | 575 | Hoeg, Xavier A | 2 | 36 | 26264
PR | 111 | 12/20/19 | 576 | Holmes, Anthony R | 25 | 1100 | 26265
PR | 111 | 12/27/19 | 704 | Barnhart, Joseph N | 4 | 216 | 26312
PR | 111 | 12/27/19 | 733 | Hoeg, Xavier A | 11 | 198 | 26341
PR | 111 | 12/27/19 | 734 | Holmes, Anthony R | 6 | 264 | 26342
PR | 111 | 01/03/20 | 36 | Hoeg, Xavier A | 5 | 90 | 26419
PR | 111 | 01/03/20 | 37 | Holmes, Anthony R | 5 | 220 | 26420
PR | 111 | 01/10/20 | 280 | Barnhart, Joseph N | 4 | 216 | 26467
PR | 111 | 01/10/20 | 309 | Hoeg, Xavier A | 2 | 36 | 26496
PR | 111 | 01/17/20 | 546 | Barnhart, Joseph N | 3 | 162 | 26545
PR | 111 | 01/17/20 | 575 | Hoeg, Xavier A | 12 | 216 | 26574
PR | 111 | 01/17/20 | 576 | Holmes, Anthony R | 9 | 396 | 26575
PR | 111 | 01/24/20 | 679 | Barnhart, Joseph N | 4 | 216 | 26622
PR | 111 | 01/24/20 | 703 | Gonzalez Hernandez, Josue | 8 | 288 | 26646
PR | 111 | 01/24/20 | 707 | Hoeg, Xavier A | 12 | 216 | 26650
PR | 111 | 01/24/20 | 708 | Holmes, Anthony R | 12 | 528 | 26651
PR | 111 | 01/24/20 | 720 | Martinez Reyes, Juan C | 8 | 296 | 26663
PR | 111 | 01/31/20 | 838 | Barnhart, Joseph N | 5 | 270 | 26698
PR | 111 | 01/31/20 | 867 | Hoeg, Xavier A | 2 | 36 | 26728
PR | 111 | 01/31/20 | 868 | Holmes, Anthony R | 2 | 88 | 26729
PR | 111 | 02/07/20 | 29 | Barnhart, Joseph N | 2 | 108 | 26777
PR | 111 | 02/07/20 | 57 | Hoeg, Xavier A | 6 | 108 | 26805
PR | 111 | 02/07/20 | 58 | Holmes, Anthony R | 6 | 264 | 26806
PR | 111 | 02/14/20 | 239 | Barnhart, Joseph N | 1 | 54 | 26855
PR | 111 | 02/21/20 | 456 | Barnhart, Joseph N | 3 | 162 | 26933
PR | 111 | 02/21/20 | 482 | Hoeg, Xavier A | 6 | 108 | 26959
PR | 111 | 02/21/20 | 483 | Holmes, Anthony R | 6 | 264 | 26960
PR | 111 | 02/28/20 | 684 | Barnhart, Joseph N | 4 | 216 | 27012
PR | 111 | 02/28/20 | 712 | Hoeg, Xavier A | 13 | 234 | 27040
PR | 111 | 02/28/20 | 713 | Holmes, Anthony R | 13 | 572 | 27041
PR | 111 | 03/06/20 | 46 | Barnhart, Joseph N | 1 | 54 | 27090
PR | 111 | 03/06/20 | 74 | Hoeg, Xavier A | 5 | 90 | 27118
PR | 111 | 03/06/20 | 75 | Holmes, Anthony R | 15 | 660 | 27119
PR | 111 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I | 35 | 1260 | 27247
PR | 111 | 03/20/20 | 569 | Barnhart, Joseph N | 11 | 594 | 27249
PR | 111 | 03/20/20 | 596 | Hoeg, Xavier A | 14 | 252 | 27276
PR | 111 | 03/20/20 | 597 | Holmes, Anthony R | 13 | 572 | 27277
PR | 111 | 03/20/20 | 622 | Rodriguez Arevalos, Christian | 35 | 1050 | 27302
PR | 111 | 03/20/20 | 632 | Taylor, Evan R | 34 | 1122 | 27312
PR | 111 | 03/20/20 | 638 | Waites, Thaddeus Z | 34 | 1666 | 27318
PR | 111 | 03/26/20 | 748 | Anderson, Richard P | 1.5 | 110.25 | 27324
PR | 111 | 03/26/20 | 748 | Anderson, Richard P | 4 | 196 | 27324
PR | 111 | 03/26/20 | 752 | Barnhart, Joseph N | 5 | 270 | 27328
PR | 111 | 03/26/20 | 778 | Hoeg, Xavier A | 14 | 252 | 27354
PR | 111 | 03/26/20 | 779 | Holmes, Anthony R | 15 | 660 | 27355
PR | 111 | 04/24/20 | 352 | Barnhart, Joseph N | 3 | 162 | 27556
PR | 111 | 06/26/20 | 521 | Barnhart, Joseph N | 4 | 216 | 28203
PR | 111 | 06/26/20 | 560 | Stahlschmidt, John P | 8 | 176 | 28242
PR | 111 | 06/26/20 | 563 | Waites, Thaddeus Z | 8 | 392 | 28245
PR | 111 | 07/02/20 | 7 | Barnhart, Joseph N | 12 | 648 | 28250
PR | 111 | 07/02/20 | 46 | Stahlschmidt, John P | 40 | 880 | 28289
PR | 111 | 07/02/20 | 49 | Waites, Thaddeus Z | 40 | 1960 | 28292
PR | 111 | 07/10/20 | 140 | Barnhart, Joseph N | 3 | 162 | 28299
PR | 111 | 07/10/20 | 178 | Stahlschmidt, John P | 8 | 176 | 28337
PR | 111 | 07/10/20 | 181 | Waites, Thaddeus Z | 8 | 392 | 28340
PR | 111 | 07/17/20 | 265 | Barnhart, Joseph N | 6 | 324 | 28345
PR | 111 | 07/17/20 | 305 | Stahlschmidt, John P | 8 | 176 | 28385
PR | 111 | 07/17/20 | 308 | Waites, Thaddeus Z | 8 | 392 | 28388
PR | 111 | 11/13/20 | 189 | Barnhart, Joseph N | 4 | 216 | 29140
PR | 111 | 01/22/21 | 261 | Barnhart, Joseph N | 5 | 270 | 29661
PR | 111 | 01/22/21 | 280 | Holmes, Anthony R | 21 | 924 | 29680
PR | 111 | 01/29/21 | 386 | Barnhart, Joseph N | 15 | 810 | 29711
PR | 111 | 01/29/21 | 404 | Gonzalez Hernandez, Josue | 40 | 1440 | 29729
PR | 111 | 01/29/21 | 406 | Holmes, Anthony R | 40 | 1760 | 29731
PR | 111 | 01/29/21 | 410 | Lee, Ha Nul | 40 | 1000 | 29735
PR | 111 | 01/29/21 | 421 | Rodriguez Arevalos, Christian | 24 | 720 | 29746
PR | 111 | 01/29/21 | 431 | Waites, Thaddeus Z | 24 | 1176 | 29756
PR | 111 | 02/05/21 | 71 | Barnhart, Joseph N | 5 | 270 | 29762
PR | 111 | 02/05/21 | 90 | Gonzalez Hernandez, Josue | 40 | 1440 | 29781
PR | 111 | 02/05/21 | 91 | Gordillo, Emanuel D | 32 | 512 | 29782
PR | 111 | 02/05/21 | 93 | Holmes, Anthony R | 32 | 1408 | 29784
PR | 111 | 02/05/21 | 97 | Lee, Ha Nul | 40 | 1000 | 29788
PR | 111 | 02/05/21 | 109 | Rodriguez Arevalos, Christian | 40 | 1200 | 29800
PR | 111 | 02/05/21 | 119 | Waites, Thaddeus Z | 32 | 1568 | 29810
PR | 111 | 02/12/21 | 276 | Gonzalez Hernandez, Josue | 40 | 1440 | 29837
PR | 111 | 02/12/21 | 277 | Gordillo, Emanuel D | 20 | 320 | 29838
PR | 111 | 02/12/21 | 279 | Holmes, Anthony R | 32 | 1408 | 29840
PR | 111 | 02/12/21 | 283 | Lee, Ha Nul | 40 | 1000 | 29844
PR | 111 | 02/12/21 | 295 | Rodriguez Arevalos, Christian | 32 | 960 | 29856
PR | 111 | 02/12/21 | 305 | Waites, Thaddeus Z | 32 | 1568 | 29866
PR | 111 | 02/19/21 | 441 | Gonzalez Hernandez, Josue | 29 | 1044 | 29894
PR | 111 | 02/19/21 | 442 | Gordillo, Emanuel D | 32 | 512 | 29895
PR | 111 | 02/19/21 | 444 | Holmes, Anthony R | 32 | 1408 | 29897
PR | 111 | 02/19/21 | 448 | Lee, Ha Nul | 40 | 1000 | 29901
PR | 111 | 02/19/21 | 462 | Rodriguez Arevalos, Christian | 40 | 1200 | 29915
PR | 111 | 02/19/21 | 472 | Waites, Thaddeus Z | 32 | 1568 | 29925
PR | 111 | 02/26/21 | 618 | Gonzalez Hernandez, Josue | 40 | 1440 | 29954
PR | 111 | 02/26/21 | 619 | Gordillo, Emanuel D | 40 | 640 | 29955
PR | 111 | 02/26/21 | 621 | Holmes, Anthony R | 16 | 704 | 29957
PR | 111 | 02/26/21 | 625 | Lee, Ha Nul | 40 | 1000 | 29961
PR | 111 | 02/26/21 | 648 | Waites, Thaddeus Z | 36 | 1764 | 29984
PR | 111 | 03/05/21 | 76 | Gonzalez Hernandez, Josue | 32 | 1152 | 30011
PR | 111 | 03/05/21 | 77 | Gordillo, Emanuel D | 16 | 256 | 30012
PR | 111 | 03/05/21 | 79 | Holmes, Anthony R | 4 | 176 | 30014
PR | 111 | 03/05/21 | 83 | Lee, Ha Nul | 40 | 1000 | 30018
PR | 111 | 03/05/21 | 106 | Waites, Thaddeus Z | 40 | 1960 | 30041
PR | 111 | 03/12/21 | 201 | Gonzalez Hernandez, Josue | 27 | 972 | 30067
PR | 111 | 03/12/21 | 209 | Lee, Ha Nul | 27 | 675 | 30075
PR | 111 | 03/12/21 | 231 | Waites, Thaddeus Z | 40 | 1960 | 30097
PR | 111 | 03/19/21 | 291 | Barnhart, Joseph N | 3 | 168 | 30104
PR | 111 | 03/19/21 | 345 | Waites, Thaddeus Z | 24 | 1200 | 30158
PR | 111 | 03/26/21 | 546 | Gordillo, Emanuel D | 35 | 595 | 30189
PR | 111 | 03/26/21 | 549 | Holmes, Anthony R | 40 | 1840 | 30192
PR | 111 | 03/26/21 | 577 | Waites, Thaddeus Z | 40 | 2000 | 30220
PR | 111 | 04/02/21 | 7 | Barnhart, Joseph N | 2 | 112 | 30226
PR | 111 | 04/02/21 | 31 | Gordillo, Emanuel D | 40 | 680 | 30250
PR | 111 | 04/02/21 | 34 | Holmes, Anthony R | 19 | 874 | 30253
PR | 111 | 04/09/21 | 135 | Gordillo, Emanuel D | 21 | 357 | 30313
PR | 111 | 04/09/21 | 138 | Holmes, Anthony R | 21 | 966 | 30316
PR | 111 | 04/16/21 | 284 | Holmes, Anthony R | 5 | 230 | 30382
PR | 111 | 04/23/21 | 404 | Barnhart, Joseph N | 1 | 56 | 30417
PR | 111 | 04/23/21 | 430 | Gordillo, Emanuel D | 8 | 136 | 30443
PR | 111 | 04/30/21 | 574 | Barnhart, Joseph N | 2 | 112 | 30484
PR | 111 | 05/07/21 | 41 | Barnhart, Joseph N | 4 | 224 | 30554
PR | 111 | 05/14/21 | 246 | Barnhart, Joseph N | 1 | 56 | 30625
PR | 111 | 05/21/21 | 391 | Barnhart, Joseph N | 6 | 336 | 30693
PR | 111 | 05/21/21 | 415 | Gonzalez Hernandez, Josue | 40 | 1520 | 30717
PR | 111 | 05/21/21 | 438 | Platero Navas, Julio A | 40 | 720 | 30740
PR | 111 | 05/28/21 | 656 | Gonzalez Hernandez, Josue | 1 | 38 | 30786
PR | 111 | 05/28/21 | 663 | Holmes, Anthony R | 1 | 46 | 30793
PR | 111 | 05/28/21 | 680 | Platero Navas, Julio A | 1 | 18 | 30810
PR | 111 | 05/28/21 | 681 | Platero Navas, Mario N | 16 | 272 | 30811
PR | 111 | 06/11/21 | 203 | Barnhart, Joseph N | 1 | 56 | 30909
PR | 111 | 06/11/21 | 229 | Gonzalez Hernandez, Josue | 8 | 304 | 30935
PR | 111 | 06/25/21 | 669 | Gutierrez, Brian A | 11 | -286 | 931129
PR | 111 | 06/25/21 | 670 | Hubbard, Robert W | 2 | 110 | 931130
PR | 111 | 07/16/21 | 322 | Barnhart, Joseph N | 2 | 112 | 31283
PR | 111 | 07/23/21 | 519 | Gonzalez Hernandez, Josue | 4 | 152 | 31387
PR | 111 | 07/23/21 | 529 | Lee, Ha Nul | 30 | 810 | 31397
PR | 111 | 11/12/21 | 269 | Barnhart, Joseph N | 2 | 116 | 32731
PR | 111 | 12/17/21 | 516 | Barnhart, Joseph N | 1 | 58 | 33328
PR | 111 | 12/17/21 | 581 | Platero Navas, Mario N | 4 | 72 | 33393
PR | 111 | 12/23/21 | 741 | Barnhart, Joseph N | 2 | 116 | 33423
PR | 111 | 01/07/22 | 74 | Holmes, Anthony R | 8 | 384 | 33654
PR | 111 | 01/21/22 | 458 | Holmes, Anthony R | 8 | 384 | 33840
PR | 111 | 01/21/22 | 467 | Lovo, German G | 16 | 560 | 33849
PR | 111 | 01/21/22 | 480 | Platero Navas, Mario N | 16 | 288 | 33862
PR | 111 | 02/04/22 | 11 | Barnhart, Joseph N | 2 | 116 | 33990
PR | 111 | 02/18/22 | 488 | Barnhart, Joseph N | 2 | 116 | 34181
PR | 111 | 02/25/22 | 709 | Barnhart, Joseph N | 5 | 290 | 34274
PR | 111 | 03/11/22 | 341 | Barnhart, Joseph N | 2.5 | 145 | 34463
PR | 111 | 03/18/22 | 626 | Barnhart, Joseph N | 1 | 58 | 34559
PR | 111 | 04/08/22 | 227 | Barnhart, Joseph N | 1 | 58 | 34841
PR | 111 | 05/13/22 | 363 | Holmes, Anthony R | 20 | 960 | 35337
PR | 111 | 05/13/22 | 373 | Lovo, German G | 16 | 560 | 35347
PR | 111 | 05/13/22 | 385 | Platero Navas, Julio A | 16 | 336 | 35359
PR | 111 | 05/20/22 | 598 | Barnhart, Joseph N | 2 | 120 | 35389
PR | 111 | 05/20/22 | 629 | Gordillo, Emanuel D | 4 | 88 | 35420
PR | 111 | 05/20/22 | 637 | Holmes, Anthony R | 20 | 1000 | 35428
PR | 111 | 05/27/22 | 867 | Barnhart, Joseph N | 21 | 1260 | 35477
PR | 111 | 05/27/22 | 906 | Holmes, Anthony R | 40 | 2000 | 35516
PR | 111 | 06/03/22 | 59 | Lovo, German G | 8 | 288 | 35618
PR | 111 | 06/03/22 | 71 | Platero Navas, Julio A | 8 | 168 | 35630
PR | 111 | 06/10/22 | 257 | Holmes, Anthony R | 24 | 1200 | 35696
PR | 111 | 06/17/22 | 465 | Barnhart, Joseph N | 4 | 240 | 35745
PR | 111 | 06/24/22 | 771 | Barnhart, Joseph N | 8 | 480 | 35837
PR | 111 | 07/01/22 | 78 | Sanders, Allen O | 5 | 295 | 35988
PR | 111 | 07/08/22 | 213 | Holmes, Anthony R | 8 | 400 | 36046
PR | 111 | 07/29/22 | 724 | Barnhart, Joseph N | 7 | 420 | 36269
PR | 111 | 07/29/22 | 753 | Gordillo, Emanuel D | 8 | 176 | 36298
PR | 111 | 07/29/22 | 759 | Holmes, Anthony R | 8 | 400 | 36304
PR | 111 | 08/05/22 | 89 | Barnhart, Joseph N | 4 | 240 | 36353
PR | 111 | 08/05/22 | 118 | Gordillo, Emanuel D | 24 | 528 | 36382
PR | 111 | 08/05/22 | 124 | Holmes, Anthony R | 24 | 1200 | 36388
PR | 111 | 08/05/22 | 133 | Lovo, German G | 16 | 576 | 36397
PR | 111 | 08/12/22 | 288 | Barnhart, Joseph N | 6 | 360 | 36430
PR | 111 | 08/12/22 | 289 | Barnhart, Thomas L | 40 | 1560 | 36431
PR | 111 | 08/12/22 | 316 | Gordillo, Emanuel D | 24 | 528 | 36458
PR | 111 | 08/12/22 | 331 | Lovo, German G | 40 | 1440 | 36473
PR | 111 | 08/19/22 | 524 | Gordillo, Emanuel D | 32 | 704 | 36536
PR | 111 | 08/19/22 | 530 | Holmes, Anthony R | 8 | 400 | 36542
PR | 111 | 08/19/22 | 539 | Lovo, German G | 24 | 864 | 36551
PR | 111 | 08/26/22 | 790 | Gordillo, Emanuel D | 21 | 462 | 36615
PR | 111 | 08/26/22 | 796 | Holmes, Anthony R | 5 | 250 | 36621
PR | 111 | 08/26/22 | 805 | Lovo, German G | 8 | 288 | 36630
PR | 111 | 09/02/22 | 37 | Gordillo, Emanuel D | 12.5 | 275 | 36693
PR | 111 | 09/02/22 | 43 | Holmes, Anthony R | 13.5 | 675 | 36699
PR | 111 | 09/09/22 | 236 | Holmes, Anthony R | 13 | 650 | 36778
PR | 111 | 09/16/22 | 430 | Barnhart, Joseph N | 5 | 300 | 36820
PR | 111 | 09/16/22 | 460 | Gordillo, Emanuel D | 4 | 88 | 36850
PR | 111 | 09/16/22 | 465 | Holmes, Anthony R | 4 | 200 | 36855
PR | 111 | 09/30/22 | 815 | Barnhart, Joseph N | 1 | 60 | 36977
PR | 111 | 10/07/22 | 28 | Barnhart, Joseph N | 5 | 320 | 37056
PR | 111 | 10/07/22 | 58 | Gordillo, Emanuel D | 3 | 66 | 37086
PR | 111 | 10/07/22 | 63 | Holmes, Anthony R | 3 | 162 | 37091
PR | 111 | 10/14/22 | 283 | Barnhart, Joseph N | 4 | 256 | 37140
PR | 111 | 10/21/22 | 477 | Barnhart, Joseph N | 4 | 256 | 37226
PR | 111 | 10/28/22 | 754 | Barnhart, Joseph N | 4 | 256 | 37311
PR | 111 | 11/18/22 | 368 | Barnhart, Joseph N | 3 | 192 | 37570
PR | 111 | 11/23/22 | 513 | Barnhart, Joseph N | 6 | 384 | 37661
PR | 111 | 12/02/22 | 9 | Barnhart, Joseph N | 4 | 256 | 37748
PR | 111 | 12/23/22 | 845 | Barnhart, Joseph N | 4 | 256 | 38120
PR | 112 | 09/27/19 | 632 | Barnhart, Joseph N | 1 | 50 | 25237
PR | 112 | 10/04/19 | 8 | Barnhart, Joseph N | 5 | 250 | 25315
PR | 112 | 10/04/19 | 55 | Paco Leyva, Orlando | 3 | 120 | 25362
PR | 112 | 10/04/19 | 57 | Ramos Herrera, Franklin J | 3 | 78 | 25364
PR | 112 | 10/11/19 | 263 | Barnhart, Joseph N | 18 | 900 | 25396
PR | 112 | 10/18/19 | 457 | Barnhart, Joseph N | 17 | 850 | 25473
PR | 112 | 10/18/19 | 499 | Martinez Reyes, Juan C | 8 | 264 | 25516
PR | 112 | 10/25/19 | 592 | Barnhart, Joseph N | 10 | 500 | 25549
PR | 112 | 10/25/19 | 634 | Martinez Reyes, Juan C | 8 | 264 | 25591
PR | 112 | 11/01/19 | 8 | Barnhart, Joseph N | 2 | 108 | 25625
PR | 112 | 11/01/19 | 50 | Martinez Reyes, Juan C | 8 | 296 | 25667
PR | 112 | 11/08/19 | 182 | Barnhart, Joseph N | 3 | 162 | 25701
PR | 112 | 11/15/19 | 442 | Barnhart, Joseph N | 3 | 162 | 25777
PR | 112 | 11/22/19 | 613 | Barnhart, Joseph N | 3 | 162 | 25853
PR | 112 | 12/06/19 | 33 | Barnhart, Joseph N | 5 | 270 | 26005
PR | 112 | 12/06/19 | 61 | Hoeg, Xavier A | 8 | 144 | 26033
PR | 112 | 12/06/19 | 62 | Holmes, Anthony R | 10 | 440 | 26034
PR | 112 | 12/13/19 | 394 | Barnhart, Joseph N | 4 | 216 | 26159
PR | 112 | 12/13/19 | 422 | Hoeg, Xavier A | 7 | 126 | 26187
PR | 112 | 12/13/19 | 423 | Holmes, Anthony R | 11 | 484 | 26188
PR | 112 | 12/20/19 | 547 | Barnhart, Joseph N | 8 | 432 | 26236
PR | 112 | 12/20/19 | 576 | Holmes, Anthony R | 15 | 660 | 26265
PR | 112 | 12/27/19 | 704 | Barnhart, Joseph N | 4 | 216 | 26312
PR | 112 | 12/27/19 | 733 | Hoeg, Xavier A | 5 | 90 | 26341
PR | 112 | 12/27/19 | 734 | Holmes, Anthony R | 18 | 792 | 26342
PR | 112 | 01/03/20 | 36 | Hoeg, Xavier A | 19 | 342 | 26419
PR | 112 | 01/03/20 | 37 | Holmes, Anthony R | 22.5 | 990 | 26420
PR | 112 | 01/10/20 | 280 | Barnhart, Joseph N | 11 | 594 | 26467
PR | 112 | 01/10/20 | 309 | Hoeg, Xavier A | 38 | 684 | 26496
PR | 112 | 01/10/20 | 310 | Holmes, Anthony R | 40 | 1760 | 26497
PR | 112 | 01/17/20 | 542 | Anderson, Richard P | 3.5 | 171.5 | 26541
PR | 112 | 01/17/20 | 546 | Barnhart, Joseph N | 13 | 702 | 26545
PR | 112 | 01/17/20 | 571 | Gonzalez Hernandez, Josue | 3.5 | 126 | 26570
PR | 112 | 01/17/20 | 575 | Hoeg, Xavier A | 26 | 468 | 26574
PR | 112 | 01/17/20 | 576 | Holmes, Anthony R | 29 | 1276 | 26575
PR | 112 | 01/24/20 | 675 | Anderson, Richard P | 16 | 784 | 26618
PR | 112 | 01/24/20 | 679 | Barnhart, Joseph N | 12 | 648 | 26622
PR | 112 | 01/24/20 | 703 | Gonzalez Hernandez, Josue | 16 | 576 | 26646
PR | 112 | 01/24/20 | 707 | Hoeg, Xavier A | 28 | 504 | 26650
PR | 112 | 01/24/20 | 708 | Holmes, Anthony R | 28 | 1232 | 26651
PR | 112 | 01/24/20 | 720 | Martinez Reyes, Juan C | 16 | 592 | 26663
PR | 112 | 01/31/20 | 833 | Amaya Gonzalez, Edilberto A | 8 | 432 | 26693
PR | 112 | 01/31/20 | 834 | Anderson, Richard P | 8 | 392 | 26694
PR | 112 | 01/31/20 | 837 | Barbosa, Michael S | 8 | 396 | 26697
PR | 112 | 01/31/20 | 838 | Barnhart, Joseph N | 8 | 648 | 26698
PR | 112 | 01/31/20 | 838 | Barnhart, Joseph N | 12 | 648 | 26698
PR | 112 | 01/31/20 | 858 | Galdamez, Dagoberto A | 8 | 396 | 26719
PR | 112 | 01/31/20 | 867 | Hoeg, Xavier A | 30 | 540 | 26728
PR | 112 | 01/31/20 | 868 | Holmes, Anthony R | 10 | 660 | 26729
PR | 112 | 01/31/20 | 868 | Holmes, Anthony R | 38 | 1672 | 26729
PR | 112 | 01/31/20 | 880 | Martinez Reyes, Juan C | 7 | 388.5 | 26741
PR | 112 | 01/31/20 | 880 | Martinez Reyes, Juan C | 1 | 37 | 26741
PR | 112 | 02/07/20 | 25 | Anderson, Richard P | 8 | 392 | 26773
PR | 112 | 02/07/20 | 29 | Barnhart, Joseph N | 15 | 810 | 26777
PR | 112 | 02/07/20 | 53 | Gonzalez Hernandez, Josue | 8 | 288 | 26801
PR | 112 | 02/07/20 | 57 | Hoeg, Xavier A | 32 | 576 | 26805
PR | 112 | 02/07/20 | 58 | Holmes, Anthony R | 29 | 1276 | 26806
PR | 112 | 02/07/20 | 61 | Hubbard, Robert W | 4 | 216 | 26809
PR | 112 | 02/07/20 | 70 | Martinez Reyes, Juan C | 8 | 296 | 26818
PR | 112 | 02/14/20 | 239 | Barnhart, Joseph N | 8 | 432 | 26855
PR | 112 | 02/14/20 | 267 | Hoeg, Xavier A | 12 | 216 | 26883
PR | 112 | 02/14/20 | 268 | Holmes, Anthony R | 16 | 704 | 26884
PR | 112 | 02/21/20 | 456 | Barnhart, Joseph N | 4 | 216 | 26933
PR | 112 | 02/21/20 | 482 | Hoeg, Xavier A | 10 | 180 | 26959
PR | 112 | 02/21/20 | 483 | Holmes, Anthony R | 10 | 440 | 26960
PR | 112 | 02/28/20 | 684 | Barnhart, Joseph N | 5 | 405 | 27012
PR | 112 | 02/28/20 | 684 | Barnhart, Joseph N | 8 | 432 | 27012
PR | 112 | 02/28/20 | 712 | Hoeg, Xavier A | 19 | 342 | 27040
PR | 112 | 02/28/20 | 713 | Holmes, Anthony R | 5 | 330 | 27041
PR | 112 | 02/28/20 | 713 | Holmes, Anthony R | 27 | 1188 | 27041
PR | 112 | 02/28/20 | 724 | Martinez Reyes, Juan C | 8 | 296 | 27052
PR | 112 | 02/28/20 | 728 | Paco Leyva, Orlando | 4 | 264 | 27056
PR | 112 | 02/28/20 | 728 | Paco Leyva, Orlando | 1 | 44 | 27056
PR | 112 | 02/28/20 | 732 | Ramos Herrera, Franklin J | 5 | 150 | 27060
PR | 112 | 03/06/20 | 46 | Barnhart, Joseph N | 10 | 540 | 27090
PR | 112 | 03/06/20 | 74 | Hoeg, Xavier A | 22 | 396 | 27118
PR | 112 | 03/06/20 | 75 | Holmes, Anthony R | 21 | 924 | 27119
PR | 112 | 03/13/20 | 311 | Barnhart, Joseph N | 12 | 648 | 27171
PR | 112 | 03/13/20 | 338 | Hoeg, Xavier A | 30 | 540 | 27198
PR | 112 | 03/13/20 | 339 | Holmes, Anthony R | 26 | 1144 | 27200
PR | 112 | 03/20/20 | 569 | Barnhart, Joseph N | 3 | 162 | 27249
PR | 112 | 03/20/20 | 596 | Hoeg, Xavier A | 20 | 360 | 27276
PR | 112 | 03/20/20 | 597 | Holmes, Anthony R | 17 | 748 | 27277
PR | 112 | 03/26/20 | 778 | Hoeg, Xavier A | 2 | 36 | 27354
PR | 112 | 03/26/20 | 779 | Holmes, Anthony R | 3 | 132 | 27355
PR | 112 | 04/10/20 | 64 | Barnhart, Joseph N | 2 | 108 | 27439
PR | 112 | 04/17/20 | 216 | Barnhart, Joseph N | 6 | 324 | 27479
PR | 112 | 07/02/20 | 7 | Barnhart, Joseph N | 8 | 432 | 28250
PR | 112 | 06/25/21 | 629 | Gutierrez, Brian A | 11 | 286 | 31087
PR | 120 | 08/30/19 | 1034 | Martinez Reyes, Juan C | 8 | 264 | 24976
PR | 120 | 11/01/19 | 8 | Barnhart, Joseph N | 3 | 162 | 25625
PR | 120 | 11/08/19 | 182 | Barnhart, Joseph N | 2 | 108 | 25701
PR | 120 | 11/08/19 | 211 | Holmes, Anthony R | 16 | 704 | 25730
PR | 120 | 11/08/19 | 232 | Reyes Cruz, Denis A | 8 | 264 | 25751
PR | 120 | 01/31/20 | 838 | Barnhart, Joseph N | 4 | 216 | 26698
PR | 120 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo | 7 | 315 | 26804
PR | 120 | 02/07/20 | 65 | Lee, Ha Nul | 7 | 262.5 | 26813
PR | 120 | 02/14/20 | 267 | Hoeg, Xavier A | 28 | 504 | 26883
PR | 120 | 02/14/20 | 268 | Holmes, Anthony R | 24 | 1056 | 26884
PR | 120 | 02/21/20 | 456 | Barnhart, Joseph N | 4 | 216 | 26933
PR | 120 | 02/21/20 | 482 | Hoeg, Xavier A | 24 | 432 | 26959
PR | 120 | 02/21/20 | 483 | Holmes, Anthony R | 16 | 704 | 26960
PR | 120 | 02/28/20 | 684 | Barnhart, Joseph N | 6 | 324 | 27012
PR | 120 | 03/06/20 | 46 | Barnhart, Joseph N | 4 | 216 | 27090
PR | 120 | 03/06/20 | 74 | Hoeg, Xavier A | 5 | 90 | 27118
PR | 120 | 03/06/20 | 75 | Holmes, Anthony R | 4 | 176 | 27119
PR | 120 | 03/13/20 | 311 | Barnhart, Joseph N | 2 | 108 | 27171
PR | 120 | 03/13/20 | 338 | Hoeg, Xavier A | 10 | 180 | 27198
PR | 120 | 03/13/20 | 339 | Holmes, Anthony R | 14 | 616 | 27200
PR | 120 | 03/20/20 | 569 | Barnhart, Joseph N | 7 | 378 | 27249
PR | 120 | 03/20/20 | 596 | Hoeg, Xavier A | 6 | 108 | 27276
PR | 120 | 03/20/20 | 597 | Holmes, Anthony R | 10 | 440 | 27277
PR | 120 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I | 8 | 288 | 27326
PR | 120 | 03/26/20 | 779 | Holmes, Anthony R | 4 | 176 | 27355
PR | 120 | 06/05/20 | 18 | Barnhart, Joseph N | 4 | 216 | 28008
PR | 120 | 06/12/20 | 221 | Barnhart, Joseph N | 3 | 162 | 28105
PR | 120 | 06/26/20 | 521 | Barnhart, Joseph N | 4 | 216 | 28203
PR | 120 | 07/02/20 | 7 | Barnhart, Joseph N | 3 | 162 | 28250
PR | 120 | 07/24/20 | 404 | Barnhart, Joseph N | 6 | 324 | 28396
PR | 120 | 07/31/20 | 499 | Barnhart, Joseph N | 16 | 864 | 28444
PR | 120 | 02/05/21 | 71 | Barnhart, Joseph N | 1 | 54 | 29762
PR | 120 | 02/12/21 | 256 | Barnhart, Joseph N | 4 | 216 | 29817
PR | 120 | 02/12/21 | 277 | Gordillo, Emanuel D | 12 | 192 | 29838
PR | 120 | 02/26/21 | 621 | Holmes, Anthony R | 24 | 1056 | 29957
PR | 120 | 02/26/21 | 648 | Waites, Thaddeus Z | 4 | 196 | 29984
PR | 120 | 03/05/21 | 77 | Gordillo, Emanuel D | 24 | 384 | 30012
PR | 120 | 03/05/21 | 79 | Holmes, Anthony R | 36 | 1584 | 30014
PR | 120 | 03/12/21 | 202 | Gordillo, Emanuel D | 40 | 640 | 30068
PR | 120 | 03/12/21 | 205 | Holmes, Anthony R | 37 | 1628 | 30071
PR | 120 | 03/19/21 | 291 | Barnhart, Joseph N | 2 | 112 | 30104
PR | 120 | 03/19/21 | 315 | Gordillo, Emanuel D | 40 | 680 | 30128
PR | 120 | 03/19/21 | 318 | Holmes, Anthony R | 40 | 1840 | 30131
PR | 120 | 03/19/21 | 345 | Waites, Thaddeus Z | 16 | 800 | 30158
PR | 120 | 03/26/21 | 546 | Gordillo, Emanuel D | 5 | 85 | 30189
PR | 120 | 04/02/21 | 62 | Waites, Thaddeus Z | 1 | 50 | 30281
PR | 120 | 04/09/21 | 135 | Gordillo, Emanuel D | 1 | 17 | 30313
PR | 120 | 04/09/21 | 138 | Holmes, Anthony R | 1 | 46 | 30316
PR | 120 | 04/16/21 | 279 | Gordillo, Emanuel D | 13 | 221 | 30377
PR | 120 | 04/16/21 | 284 | Holmes, Anthony R | 10 | 460 | 30382
PR | 120 | 04/16/21 | 290 | Lovo, German G | 32 | 1056 | 30388
PR | 120 | 04/16/21 | 310 | Velasquez Cruz, Denis M | 40 | 1480 | 30408
PR | 120 | 04/16/21 | 311 | Velasquez Cruz, Osman N | 40 | 1280 | 30409
PR | 120 | 04/23/21 | 404 | Barnhart, Joseph N | 2 | 112 | 30417
PR | 120 | 04/23/21 | 430 | Gordillo, Emanuel D | 32 | 544 | 30443
PR | 120 | 04/23/21 | 432 | Gutierrez, Brian A | 16 | 416 | 30445
PR | 120 | 04/23/21 | 436 | Holmes, Anthony R | 39 | 1794 | 30449
PR | 120 | 04/23/21 | 439 | Lee, Ha Nul | 16 | 432 | 30452
PR | 120 | 04/23/21 | 441 | Lovo, German G | 40 | 1320 | 30454
PR | 120 | 04/23/21 | 463 | Velasquez Cruz, Denis M | 40 | 1480 | 30476
PR | 120 | 04/23/21 | 464 | Velasquez Cruz, Osman N | 40 | 1280 | 30477
PR | 120 | 04/30/21 | 574 | Barnhart, Joseph N | 2 | 112 | 30484
PR | 120 | 04/30/21 | 600 | Gordillo, Emanuel D | 40 | 680 | 30510
PR | 120 | 04/30/21 | 606 | Holmes, Anthony R | 38 | 1748 | 30516
PR | 120 | 04/30/21 | 609 | Lee, Ha Nul | 40 | 1080 | 30519
PR | 120 | 04/30/21 | 611 | Lovo, German G | 40 | 1320 | 30521
PR | 120 | 04/30/21 | 634 | Velasquez Cruz, Denis M | 40 | 1480 | 30544
PR | 120 | 04/30/21 | 635 | Velasquez Cruz, Osman N | 40 | 1280 | 30545
PR | 120 | 05/07/21 | 41 | Barnhart, Joseph N | 3 | 168 | 30554
PR | 120 | 05/07/21 | 67 | Gordillo, Emanuel D | 40 | 680 | 30580
PR | 120 | 05/07/21 | 73 | Holmes, Anthony R | 40 | 1840 | 30586
PR | 120 | 05/07/21 | 77 | Lee, Ha Nul | 40 | 1080 | 30590
PR | 120 | 05/07/21 | 79 | Lovo, German G | 32 | 1056 | 30592
PR | 120 | 05/07/21 | 102 | Velasquez Cruz, Denis M | 32 | 1184 | 30615
PR | 120 | 05/07/21 | 103 | Velasquez Cruz, Osman N | 32 | 1024 | 30616
PR | 120 | 05/14/21 | 246 | Barnhart, Joseph N | 1 | 56 | 30625
PR | 120 | 05/14/21 | 270 | Gonzalez Hernandez, Josue | 7 | 266 | 30649
PR | 120 | 05/14/21 | 271 | Gordillo, Emanuel D | 40 | 680 | 30650
PR | 120 | 05/14/21 | 276 | Holmes, Anthony R | 36 | 1656 | 30655
PR | 120 | 05/14/21 | 280 | Lee, Ha Nul | 39 | 1053 | 30659
PR | 120 | 05/14/21 | 283 | Lovo, German G | 40 | 1320 | 30662
PR | 120 | 05/14/21 | 292 | Platero Navas, Julio A | 16 | 288 | 30671
PR | 120 | 05/14/21 | 306 | Velasquez Cruz, Denis M | 40 | 1480 | 30685
PR | 120 | 05/14/21 | 307 | Velasquez Cruz, Osman N | 40 | 1280 | 30686
PR | 120 | 05/21/21 | 391 | Barnhart, Joseph N | 3 | 168 | 30693
PR | 120 | 05/21/21 | 416 | Gordillo, Emanuel D | 40 | 680 | 30718
PR | 120 | 05/21/21 | 422 | Holmes, Anthony R | 40 | 1840 | 30724
PR | 120 | 05/21/21 | 426 | Lee, Ha Nul | 40 | 1080 | 30728
PR | 120 | 05/21/21 | 429 | Lovo, German G | 32 | 1056 | 30731
PR | 120 | 05/21/21 | 452 | Velasquez Cruz, Denis M | 32 | 1184 | 30754
PR | 120 | 05/21/21 | 453 | Velasquez Cruz, Osman N | 40 | 1280 | 30755
PR | 120 | 05/28/21 | 656 | Gonzalez Hernandez, Josue | 7 | 266 | 30786
PR | 120 | 05/28/21 | 657 | Gordillo, Emanuel D | 40 | 680 | 30787
PR | 120 | 05/28/21 | 663 | Holmes, Anthony R | 38 | 1748 | 30793
PR | 120 | 05/28/21 | 667 | Lee, Ha Nul | 24 | 648 | 30797
PR | 120 | 05/28/21 | 670 | Lovo, German G | 40 | 1320 | 30800
PR | 120 | 05/28/21 | 680 | Platero Navas, Julio A | 7 | 126 | 30810
PR | 120 | 05/28/21 | 695 | Velasquez Cruz, Denis M | 40 | 1480 | 30825
PR | 120 | 05/28/21 | 696 | Velasquez Cruz, Osman N | 40 | 1280 | 30826
PR | 120 | 06/04/21 | 57 | Gordillo, Emanuel D | 32 | 544 | 30862
PR | 120 | 06/04/21 | 63 | Holmes, Anthony R | 32 | 1472 | 30868
PR | 120 | 06/04/21 | 67 | Lee, Ha Nul | 22 | 594 | 30872
PR | 120 | 06/04/21 | 70 | Lovo, German G | 24 | 792 | 30875
PR | 120 | 06/04/21 | 95 | Velasquez Cruz, Denis M | 24 | 888 | 30900
PR | 120 | 06/04/21 | 96 | Velasquez Cruz, Osman N | 24 | 768 | 30901
PR | 120 | 06/11/21 | 203 | Barnhart, Joseph N | 1 | 56 | 30909
PR | 120 | 06/11/21 | 213 | Cruz, Azael S | 24 | 648 | 30919
PR | 120 | 06/11/21 | 229 | Gonzalez Hernandez, Josue | 2 | 76 | 30935
PR | 120 | 06/11/21 | 230 | Gordillo, Emanuel D | 40 | 680 | 30936
PR | 120 | 06/11/21 | 236 | Holmes, Anthony R | 27 | 1242 | 30942
PR | 120 | 06/11/21 | 240 | Lee, Ha Nul | 40 | 1080 | 30946
PR | 120 | 06/11/21 | 243 | Lovo, German G | 40 | 1320 | 30949
PR | 120 | 06/11/21 | 254 | Platero Navas, Mario N | 32 | 544 | 30960
PR | 120 | 06/11/21 | 267 | Velasquez Cruz, Denis M | 40 | 1480 | 30973
PR | 120 | 06/11/21 | 268 | Velasquez Cruz, Osman N | 40 | 1280 | 30974
PR | 120 | 06/18/21 | 415 | Cruz, Azael S | 40 | 1080 | 30993
PR | 120 | 06/18/21 | 432 | Gordillo, Emanuel D | 40 | 680 | 31010
PR | 120 | 06/18/21 | 438 | Holmes, Anthony R | 28 | 1288 | 31016
PR | 120 | 06/18/21 | 442 | Lee, Ha Nul | 38 | 1026 | 31020
PR | 120 | 06/18/21 | 445 | Lovo, German G | 40 | 1320 | 31023
PR | 120 | 06/18/21 | 452 | Ortiz Carmona, Jose | 40 | 1280 | 31030
PR | 120 | 06/18/21 | 455 | Platero Navas, Julio A | 40 | 720 | 31033
PR | 120 | 06/18/21 | 456 | Platero Navas, Mario N | 40 | 680 | 31034
PR | 120 | 06/18/21 | 471 | Velasquez Cruz, Denis M | 40 | 1480 | 31049
PR | 120 | 06/18/21 | 472 | Velasquez Cruz, Osman N | 40 | 1280 | 31050
PR | 120 | 06/25/21 | 610 | Cruz, Azael S | 40 | 1080 | 31068
PR | 120 | 06/25/21 | 627 | Gordillo, Emanuel D | 40 | 680 | 31085
PR | 120 | 06/25/21 | 633 | Holmes, Anthony R | 29 | 1334 | 31091
PR | 120 | 06/25/21 | 635 | Hubbard, Robert W | 4 | 220 | 31093
PR | 120 | 06/25/21 | 637 | Lee, Ha Nul | 32 | 864 | 31095
PR | 120 | 06/25/21 | 640 | Lovo, German G | 40 | 1320 | 31098
PR | 120 | 06/25/21 | 647 | Ortiz Carmona, Jose | 40 | 1280 | 31105
PR | 120 | 06/25/21 | 650 | Platero Navas, Julio A | 24 | 432 | 31108
PR | 120 | 06/25/21 | 651 | Platero Navas, Mario N | 40 | 680 | 31109
PR | 120 | 06/25/21 | 666 | Velasquez Cruz, Denis M | 40 | 1480 | 31124
PR | 120 | 06/25/21 | 667 | Velasquez Cruz, Osman N | 40 | 1280 | 31125
PR | 120 | 07/02/21 | 19 | Cruz, Azael S | 35.5 | 958.5 | 31142
PR | 120 | 07/02/21 | 35 | Gonzalez Hernandez, Josue | 16 | 608 | 31158
PR | 120 | 07/02/21 | 36 | Gordillo, Emanuel D | 40 | 680 | 31159
PR | 120 | 07/02/21 | 40 | Holmes, Anthony R | 27 | 1242 | 31163
PR | 120 | 07/02/21 | 42 | Hubbard, Robert W | 2.5 | 137.5 | 31165
PR | 120 | 07/02/21 | 44 | Lee, Ha Nul | 29.5 | 796.5 | 31167
PR | 120 | 07/02/21 | 47 | Lovo, German G | 32 | 1056 | 31170
PR | 120 | 07/02/21 | 55 | Ortiz Carmona, Jose | 15.5 | 496 | 31178
PR | 120 | 07/02/21 | 58 | Platero Navas, Julio A | 21.5 | 387 | 31181
PR | 120 | 07/02/21 | 59 | Platero Navas, Mario N | 37.5 | 637.5 | 31182
PR | 120 | 07/02/21 | 74 | Velasquez Cruz, Denis M | 35.5 | 1313.5 | 31197
PR | 120 | 07/02/21 | 75 | Velasquez Cruz, Osman N | 35.5 | 1136 | 31198
PR | 120 | 07/09/21 | 114 | Cruz, Azael S | 30 | 810 | 31217
PR | 120 | 07/09/21 | 130 | Gonzalez Hernandez, Josue | 24 | 912 | 31233
PR | 120 | 07/09/21 | 131 | Gordillo, Emanuel D | 28 | 476 | 31234
PR | 120 | 07/09/21 | 135 | Holmes, Anthony R | 24 | 1104 | 31238
PR | 120 | 07/09/21 | 137 | Hubbard, Robert W | 4 | 220 | 31240
PR | 120 | 07/09/21 | 139 | Lee, Ha Nul | 20 | 540 | 31242
PR | 120 | 07/09/21 | 142 | Lovo, German G | 32 | 1056 | 31245
PR | 120 | 07/09/21 | 154 | Platero Navas, Mario N | 32 | 544 | 31257
PR | 120 | 07/09/21 | 171 | Velasquez Cruz, Denis M | 30 | 1110 | 31274
PR | 120 | 07/09/21 | 172 | Velasquez Cruz, Osman N | 30 | 960 | 31275
PR | 120 | 07/16/21 | 322 | Barnhart, Joseph N | 2 | 112 | 31283
PR | 120 | 07/16/21 | 332 | Cruz, Azael S | 40 | 1080 | 31293
PR | 120 | 07/16/21 | 353 | Holmes, Anthony R | 40 | 1840 | 31314
PR | 120 | 07/16/21 | 357 | Lee, Ha Nul | 40 | 1080 | 31318
PR | 120 | 07/16/21 | 360 | Lovo, German G | 40 | 1320 | 31321
PR | 120 | 07/16/21 | 372 | Platero Navas, Mario N | 24 | 408 | 31333
PR | 120 | 07/16/21 | 389 | Velasquez Cruz, Denis M | 40 | 1480 | 31350
PR | 120 | 07/16/21 | 390 | Velasquez Cruz, Osman N | 40 | 1280 | 31351
PR | 120 | 07/23/21 | 493 | Barnhart, Joseph N | 2 | 168 | 31361
PR | 120 | 07/23/21 | 493 | Barnhart, Joseph N | 4 | 224 | 31361
PR | 120 | 07/23/21 | 503 | Cruz, Azael S | 40 | 1080 | 31371
PR | 120 | 07/23/21 | 520 | Gordillo, Emanuel D | 40 | 680 | 31388
PR | 120 | 07/23/21 | 524 | Holmes, Anthony R | 40 | 1840 | 31392
PR | 120 | 07/23/21 | 527 | Hubbard, Robert W | 3 | 165 | 31395
PR | 120 | 07/23/21 | 529 | Lee, Ha Nul | 10 | 270 | 31397
PR | 120 | 07/23/21 | 532 | Lovo, German G | 32 | 1056 | 31400
PR | 120 | 07/23/21 | 544 | Platero Navas, Mario N | 40 | 680 | 31412
PR | 120 | 07/23/21 | 561 | Velasquez Cruz, Denis M | 40 | 1480 | 31429
PR | 120 | 07/23/21 | 562 | Velasquez Cruz, Osman N | 40 | 1280 | 31430
PR | 120 | 07/30/21 | 684 | Barnhart, Joseph N | 10 | 560 | 31440
PR | 120 | 07/30/21 | 695 | Cruz, Azael S | 40 | 1080 | 31451
PR | 120 | 07/30/21 | 712 | Gordillo, Emanuel D | 40 | 680 | 31468
PR | 120 | 07/30/21 | 717 | Holmes, Anthony R | 40 | 1840 | 31473
PR | 120 | 07/30/21 | 722 | Lee, Ha Nul | 40 | 1080 | 31478
PR | 120 | 07/30/21 | 725 | Lovo, German G | 40 | 1320 | 31481
PR | 120 | 07/30/21 | 737 | Platero Navas, Mario N | 40 | 680 | 31493
PR | 120 | 07/30/21 | 753 | Velasquez Cruz, Denis M | 40 | 1480 | 31509
PR | 120 | 07/30/21 | 754 | Velasquez Cruz, Osman N | 40 | 1280 | 31510
PR | 120 | 08/06/21 | 55 | Cruz, Azael S | 40 | 1080 | 31533
PR | 120 | 08/06/21 | 71 | Gordillo, Emanuel D | 40 | 680 | 31549
PR | 120 | 08/06/21 | 76 | Holmes, Anthony R | 40 | 1840 | 31554
PR | 120 | 08/06/21 | 79 | Hubbard, Robert W | 2 | 165 | 31557
PR | 120 | 08/06/21 | 79 | Hubbard, Robert W | 4 | 220 | 31557
PR | 120 | 08/06/21 | 81 | Lee, Ha Nul | 40 | 1080 | 31559
PR | 120 | 08/06/21 | 84 | Lovo, German G | 40 | 1320 | 31562
PR | 120 | 08/06/21 | 96 | Platero Navas, Mario N | 40 | 680 | 31574
PR | 120 | 08/06/21 | 112 | Velasquez Cruz, Denis M | 40 | 1480 | 31590
PR | 120 | 08/06/21 | 113 | Velasquez Cruz, Osman N | 40 | 1280 | 31591
PR | 120 | 08/13/21 | 317 | Cruz, Azael S | 40 | 1080 | 31612
PR | 120 | 08/13/21 | 333 | Gordillo, Emanuel D | 40 | 680 | 31628
PR | 120 | 08/13/21 | 338 | Holmes, Anthony R | 36 | 1656 | 31633
PR | 120 | 08/13/21 | 341 | Hubbard, Robert W | 8 | 440 | 31636
PR | 120 | 08/13/21 | 343 | Lee, Ha Nul | 48 | 1296 | 31638
PR | 120 | 08/13/21 | 346 | Lovo, German G | 26 | 858 | 31641
PR | 120 | 08/13/21 | 357 | Platero Navas, Julio A | 8 | 144 | 31652
PR | 120 | 08/13/21 | 358 | Platero Navas, Mario N | 36 | 612 | 31653
PR | 120 | 08/13/21 | 373 | Velasquez Cruz, Denis M | 30 | 1110 | 31668
PR | 120 | 08/13/21 | 374 | Velasquez Cruz, Osman N | 24 | 768 | 31669
PR | 120 | 08/20/21 | 587 | Barnhart, Joseph N | 7 | 392 | 31680
PR | 120 | 08/20/21 | 598 | Cruz, Azael S | 40 | 1080 | 31691
PR | 120 | 08/20/21 | 615 | Gordillo, Emanuel D | 40 | 680 | 31708
PR | 120 | 08/20/21 | 620 | Holmes, Anthony R | 10 | 460 | 31713
PR | 120 | 08/20/21 | 626 | Lee, Ha Nul | 10 | 270 | 31719
PR | 120 | 08/20/21 | 641 | Platero Navas, Mario N | 16 | 272 | 31734
PR | 120 | 08/20/21 | 656 | Velasquez Cruz, Denis M | 10 | 370 | 31749
PR | 120 | 08/20/21 | 657 | Velasquez Cruz, Osman N | 10 | 320 | 31750
PR | 120 | 08/27/21 | 807 | Barnhart, Joseph N | 9 | 504 | 31759
PR | 120 | 08/27/21 | 819 | Cruz, Azael S | 40 | 1080 | 31771
PR | 120 | 08/27/21 | 836 | Gordillo, Emanuel D | 40 | 680 | 31788
PR | 120 | 08/27/21 | 849 | Lovo, German G | 24 | 792 | 31801
PR | 120 | 08/27/21 | 857 | Ortiz Carmona, Jose | 20 | 640 | 31809
PR | 120 | 08/27/21 | 877 | Velasquez Cruz, Denis M | 30 | 1110 | 31829
PR | 120 | 08/27/21 | 878 | Velasquez Cruz, Osman N | 10 | 320 | 31830
PR | 120 | 09/03/21 | 8 | Barnhart, Joseph N | 14 | 784 | 31840
PR | 120 | 09/03/21 | 20 | Cruz, Azael S | 10 | 270 | 31852
PR | 120 | 09/03/21 | 38 | Gordillo, Emanuel D | 20 | 340 | 31870
PR | 120 | 09/03/21 | 43 | Holmes, Anthony R | 20 | 920 | 31875
PR | 120 | 09/03/21 | 46 | Hubbard, Robert W | 8 | 440 | 31878
PR | 120 | 09/03/21 | 51 | Lovo, German G | 40 | 1320 | 31883
PR | 120 | 09/03/21 | 59 | Ortiz Carmona, Jose | 10 | 320 | 31891
PR | 120 | 09/03/21 | 62 | Platero Navas, Julio A | 32 | 576 | 31894
PR | 120 | 09/03/21 | 63 | Platero Navas, Mario N | 24 | 408 | 31895
PR | 120 | 09/03/21 | 80 | Velasquez Cruz, Denis M | 40 | 1480 | 31912
PR | 120 | 09/03/21 | 81 | Velasquez Cruz, Osman N | 40 | 1280 | 31913
PR | 120 | 09/10/21 | 206 | Gordillo, Emanuel D | 40 | 760 | 31954
PR | 120 | 09/10/21 | 211 | Holmes, Anthony R | 40 | 1920 | 31959
PR | 120 | 09/10/21 | 219 | Lovo, German G | 16 | 560 | 31967
PR | 120 | 09/10/21 | 227 | Ortiz Carmona, Jose | 10 | 330 | 31975
PR | 120 | 09/10/21 | 231 | Platero Navas, Julio A | 32 | 608 | 31979
PR | 120 | 09/10/21 | 232 | Platero Navas, Mario N | 32 | 576 | 31980
PR | 120 | 09/10/21 | 249 | Velasquez Cruz, Denis M | 30 | 1170 | 31997
PR | 120 | 09/10/21 | 250 | Velasquez Cruz, Osman N | 30 | 1020 | 31998
PR | 120 | 09/17/21 | 338 | Barnhart, Joseph N | 1 | 58 | 32008
PR | 120 | 09/17/21 | 350 | Cruz, Azael S | 40 | 1120 | 32020
PR | 120 | 09/17/21 | 368 | Gordillo, Emanuel D | 8 | 228 | 32038
PR | 120 | 09/17/21 | 368 | Gordillo, Emanuel D | 40 | 760 | 32038
PR | 120 | 09/17/21 | 373 | Holmes, Anthony R | 8 | 576 | 32043
PR | 120 | 09/17/21 | 373 | Holmes, Anthony R | 39 | 1872 | 32043
PR | 120 | 09/17/21 | 381 | Lovo, German G | 1 | 52.5 | 32051
PR | 120 | 09/17/21 | 381 | Lovo, German G | 40 | 1400 | 32051
PR | 120 | 09/17/21 | 393 | Platero Navas, Julio A | 1 | 28.5 | 32063
PR | 120 | 09/17/21 | 393 | Platero Navas, Julio A | 40 | 760 | 32063
PR | 120 | 09/17/21 | 394 | Platero Navas, Mario N | 1 | 27 | 32064
PR | 120 | 09/17/21 | 394 | Platero Navas, Mario N | 40 | 720 | 32064
PR | 120 | 09/17/21 | 411 | Velasquez Cruz, Denis M | 7 | 409.5 | 32081
PR | 120 | 09/17/21 | 411 | Velasquez Cruz, Denis M | 40 | 1560 | 32081
PR | 120 | 09/17/21 | 412 | Velasquez Cruz, Osman N | 7 | 357 | 32082
PR | 120 | 09/17/21 | 412 | Velasquez Cruz, Osman N | 40 | 1360 | 32082
PR | 120 | 09/24/21 | 492 | Barnhart, Joseph N | 11 | 638 | 32092
PR | 120 | 09/24/21 | 504 | Cruz, Azael S | 7 | 294 | 32104
PR | 120 | 09/24/21 | 504 | Cruz, Azael S | 30 | 840 | 32104
PR | 120 | 09/24/21 | 522 | Gordillo, Emanuel D | 8 | 228 | 32122
PR | 120 | 09/24/21 | 522 | Gordillo, Emanuel D | 40 | 760 | 32122
PR | 120 | 09/24/21 | 527 | Holmes, Anthony R | 8 | 576 | 32127
PR | 120 | 09/24/21 | 527 | Holmes, Anthony R | 40 | 1920 | 32127
PR | 120 | 09/24/21 | 535 | Lovo, German G | 6 | 315 | 32135
PR | 120 | 09/24/21 | 535 | Lovo, German G | 40 | 1400 | 32135
PR | 120 | 09/24/21 | 547 | Platero Navas, Julio A | 38 | 722 | 32147
PR | 120 | 09/24/21 | 548 | Platero Navas, Mario N | 10 | 180 | 32148
PR | 120 | 09/24/21 | 566 | Velasquez Cruz, Denis M | 7 | 409.5 | 32166
PR | 120 | 09/24/21 | 566 | Velasquez Cruz, Denis M | 40 | 1560 | 32166
PR | 120 | 09/24/21 | 567 | Velasquez Cruz, Osman N | 7 | 357 | 32167
PR | 120 | 09/24/21 | 567 | Velasquez Cruz, Osman N | 40 | 1360 | 32167
PR | 120 | 10/01/21 | 9 | Barnhart, Joseph N | 10 | 870 | 32179
PR | 120 | 10/01/21 | 9 | Barnhart, Joseph N | 10 | 580 | 32179
PR | 120 | 10/01/21 | 16 | Castro Urena, Yanely | 15 | 382.5 | 32186
PR | 120 | 10/01/21 | 16 | Castro Urena, Yanely | 40 | 680 | 32186
PR | 120 | 10/01/21 | 38 | Gonzalez Hernandez, Josue | 30 | 1200 | 32208
PR | 120 | 10/01/21 | 39 | Gordillo, Emanuel D | 16 | 456 | 32209
PR | 120 | 10/01/21 | 39 | Gordillo, Emanuel D | 40 | 760 | 32209
PR | 120 | 10/01/21 | 41 | Gutierrez, Brian A | 7 | 273 | 32211
PR | 120 | 10/01/21 | 41 | Gutierrez, Brian A | 40 | 1040 | 32211
PR | 120 | 10/01/21 | 43 | Hernandez Gonzalez, Osbaldo | 20 | 700 | 32213
PR | 120 | 10/01/21 | 44 | Holmes, Anthony R | 16 | 1152 | 32214
PR | 120 | 10/01/21 | 44 | Holmes, Anthony R | 40 | 1920 | 32214
PR | 120 | 10/01/21 | 50 | Lara, Eric E | 10 | 300 | 32220
PR | 120 | 10/01/21 | 53 | Lovo, German G | 6 | 315 | 32223
PR | 120 | 10/01/21 | 53 | Lovo, German G | 40 | 1400 | 32223
PR | 120 | 10/01/21 | 60 | Ortiz Carmona, Jose | 10 | 330 | 32230
PR | 120 | 10/01/21 | 64 | Platero Navas, Julio A | 6 | 171 | 32234
PR | 120 | 10/01/21 | 64 | Platero Navas, Julio A | 40 | 760 | 32234
PR | 120 | 10/01/21 | 65 | Platero Navas, Mario N | 6 | 162 | 32235
PR | 120 | 10/01/21 | 65 | Platero Navas, Mario N | 40 | 720 | 32235
PR | 120 | 10/01/21 | 78 | Stahlschmidt, John P | 6 | 234 | 32248
PR | 120 | 10/01/21 | 78 | Stahlschmidt, John P | 32 | 832 | 32248
PR | 120 | 10/01/21 | 82 | Vazquez Popoca, Jose N | 6 | 243 | 32252
PR | 120 | 10/01/21 | 82 | Vazquez Popoca, Jose N | 24 | 648 | 32252
PR | 120 | 10/01/21 | 83 | Velasquez Cruz, Denis M | 15 | 877.5 | 32253
PR | 120 | 10/01/21 | 83 | Velasquez Cruz, Denis M | 40 | 1560 | 32253
PR | 120 | 10/01/21 | 84 | Velasquez Cruz, Osman N | 7 | 357 | 32254
PR | 120 | 10/01/21 | 84 | Velasquez Cruz, Osman N | 40 | 1360 | 32254
PR | 120 | 10/08/21 | 297 | Barnhart, Joseph N | 14 | 812 | 32268
PR | 120 | 10/08/21 | 305 | Castro Urena, Yanely | 37 | 629 | 32276
PR | 120 | 10/08/21 | 329 | Gonzalez Hernandez, Josue | 8 | 480 | 32300
PR | 120 | 10/08/21 | 329 | Gonzalez Hernandez, Josue | 15 | 600 | 32300
PR | 120 | 10/08/21 | 331 | Gordillo, Emanuel D | 16 | 456 | 32302
PR | 120 | 10/08/21 | 331 | Gordillo, Emanuel D | 40 | 760 | 32302
PR | 120 | 10/08/21 | 333 | Gutierrez, Brian A | 8 | 336 | 32304
PR | 120 | 10/08/21 | 333 | Gutierrez, Brian A | 40 | 1120 | 32304
PR | 120 | 10/08/21 | 336 | Holmes, Anthony R | 16 | 1152 | 32307
PR | 120 | 10/08/21 | 336 | Holmes, Anthony R | 39 | 1872 | 32307
PR | 120 | 10/08/21 | 342 | Lara, Eric E | 15.5 | 697.5 | 32313
PR | 120 | 10/08/21 | 342 | Lara, Eric E | 40 | 1200 | 32313
PR | 120 | 10/08/21 | 345 | Lovo, German G | 2 | 105 | 32316
PR | 120 | 10/08/21 | 345 | Lovo, German G | 40 | 1400 | 32316
PR | 120 | 10/08/21 | 353 | Ortiz Carmona, Jose | 10 | 330 | 32324
PR | 120 | 10/08/21 | 357 | Platero Navas, Julio A | 12 | 342 | 32328
PR | 120 | 10/08/21 | 357 | Platero Navas, Julio A | 17 | 323 | 32328
PR | 120 | 10/08/21 | 358 | Platero Navas, Mario N | 12 | 324 | 32329
PR | 120 | 10/08/21 | 358 | Platero Navas, Mario N | 40 | 720 | 32329
PR | 120 | 10/08/21 | 375 | Vazquez Popoca, Jose N | 6 | 243 | 32346
PR | 120 | 10/08/21 | 375 | Vazquez Popoca, Jose N | 40 | 1080 | 32346
PR | 120 | 10/08/21 | 376 | Velasquez Cruz, Denis M | 7 | 409.5 | 32347
PR | 120 | 10/08/21 | 376 | Velasquez Cruz, Denis M | 40 | 1560 | 32347
PR | 120 | 10/08/21 | 377 | Velasquez Cruz, Osman N | 7 | 357 | 32348
PR | 120 | 10/08/21 | 377 | Velasquez Cruz, Osman N | 40 | 1360 | 32348
PR | 120 | 10/15/21 | 561 | Barnhart, Joseph N | 14 | 812 | 32358
PR | 120 | 10/15/21 | 569 | Castro Urena, Yanely | 7 | 178.5 | 32366
PR | 120 | 10/15/21 | 569 | Castro Urena, Yanely | 40 | 680 | 32366
PR | 120 | 10/15/21 | 596 | Gordillo, Emanuel D | 16 | 456 | 32393
PR | 120 | 10/15/21 | 596 | Gordillo, Emanuel D | 40 | 760 | 32393
PR | 120 | 10/15/21 | 598 | Gutierrez, Brian A | 7 | 294 | 32395
PR | 120 | 10/15/21 | 598 | Gutierrez, Brian A | 40 | 1120 | 32395
PR | 120 | 10/15/21 | 601 | Holmes, Anthony R | 16 | 1152 | 32398
PR | 120 | 10/15/21 | 601 | Holmes, Anthony R | 38 | 1824 | 32398
PR | 120 | 10/15/21 | 609 | Lovo, German G | 38 | 1330 | 32406
PR | 120 | 10/15/21 | 622 | Platero Navas, Mario N | 36 | 648 | 32419
PR | 120 | 10/15/21 | 638 | Vazquez Popoca, Jose N | 23 | 621 | 32435
PR | 120 | 10/15/21 | 639 | Velasquez Cruz, Denis M | 7 | 409.5 | 32436
PR | 120 | 10/15/21 | 639 | Velasquez Cruz, Denis M | 40 | 1560 | 32436
PR | 120 | 10/15/21 | 640 | Velasquez Cruz, Osman N | 7 | 357 | 32437
PR | 120 | 10/15/21 | 640 | Velasquez Cruz, Osman N | 40 | 1360 | 32437
PR | 120 | 10/22/21 | 748 | Barnhart, Joseph N | 13 | 1131 | 32452
PR | 120 | 10/22/21 | 748 | Barnhart, Joseph N | 16 | 928 | 32452
PR | 120 | 10/22/21 | 757 | Castro Urena, Yanely | 38 | 646 | 32461
PR | 120 | 10/22/21 | 784 | Gordillo, Emanuel D | 18 | 513 | 32488
PR | 120 | 10/22/21 | 784 | Gordillo, Emanuel D | 40 | 760 | 32488
PR | 120 | 10/22/21 | 787 | Gutierrez, Brian A | 37 | 1036 | 32491
PR | 120 | 10/22/21 | 791 | Holmes, Anthony R | 18 | 1296 | 32495
PR | 120 | 10/22/21 | 791 | Holmes, Anthony R | 40 | 1920 | 32495
PR | 120 | 10/22/21 | 799 | Lovo, German G | 6 | 315 | 32503
PR | 120 | 10/22/21 | 799 | Lovo, German G | 40 | 1400 | 32503
PR | 120 | 10/22/21 | 812 | Platero Navas, Mario N | 18 | 486 | 32516
PR | 120 | 10/22/21 | 812 | Platero Navas, Mario N | 40 | 720 | 32516
PR | 120 | 10/22/21 | 829 | Vazquez Popoca, Jose N | 18 | 486 | 32533
PR | 120 | 10/22/21 | 830 | Velasquez Cruz, Denis M | 7 | 409.5 | 32534
PR | 120 | 10/22/21 | 830 | Velasquez Cruz, Denis M | 40 | 1560 | 32534
PR | 120 | 10/22/21 | 831 | Velasquez Cruz, Osman N | 7 | 357 | 32535
PR | 120 | 10/22/21 | 831 | Velasquez Cruz, Osman N | 40 | 1360 | 32535
PR | 120 | 10/29/21 | 1008 | Barnhart, Joseph N | 13 | 754 | 32545
PR | 120 | 10/29/21 | 1017 | Castro Urena, Yanely | 40 | 680 | 32554
PR | 120 | 10/29/21 | 1022 | Cruz, Azael S | 40 | 1120 | 32559
PR | 120 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue | 20 | 800 | 32579
PR | 120 | 10/29/21 | 1043 | Gordillo, Emanuel D | 15 | 427.5 | 32580
PR | 120 | 10/29/21 | 1043 | Gordillo, Emanuel D | 40 | 760 | 32580
PR | 120 | 10/29/21 | 1046 | Gutierrez, Brian A | 40 | 1120 | 32583
PR | 120 | 10/29/21 | 1051 | Holmes, Anthony R | 15 | 1080 | 32588
PR | 120 | 10/29/21 | 1051 | Holmes, Anthony R | 40 | 1920 | 32588
PR | 120 | 10/29/21 | 1059 | Lovo, German G | 10 | 350 | 32596
PR | 120 | 10/29/21 | 1066 | Ortiz Carmona, Jose | 30 | 990 | 32603
PR | 120 | 10/29/21 | 1070 | Platero Navas, Julio A | 37.5 | 712.5 | 32607
PR | 120 | 10/29/21 | 1071 | Platero Navas, Mario N | 13.5 | 364.5 | 32608
PR | 120 | 10/29/21 | 1071 | Platero Navas, Mario N | 40 | 720 | 32608
PR | 120 | 10/29/21 | 1088 | Velasquez Cruz, Denis M | 7 | 409.5 | 32625
PR | 120 | 10/29/21 | 1088 | Velasquez Cruz, Denis M | 40 | 1560 | 32625
PR | 120 | 10/29/21 | 1089 | Velasquez Cruz, Osman N | 40 | 1360 | 32626
PR | 120 | 11/05/21 | 54 | Barnhart, Joseph N | 7 | 406 | 32636
PR | 120 | 11/05/21 | 63 | Castro Urena, Yanely | 7 | 178.5 | 32645
PR | 120 | 11/05/21 | 63 | Castro Urena, Yanely | 30 | 510 | 32645
PR | 120 | 11/05/21 | 68 | Cruz, Azael S | 35 | 980 | 32650
PR | 120 | 11/05/21 | 89 | Gonzalez Hernandez, Josue | 6 | 360 | 32671
PR | 120 | 11/05/21 | 89 | Gonzalez Hernandez, Josue | 35 | 1400 | 32671
PR | 120 | 11/05/21 | 90 | Gordillo, Emanuel D | 8 | 228 | 32672
PR | 120 | 11/05/21 | 90 | Gordillo, Emanuel D | 35 | 665 | 32672
PR | 120 | 11/05/21 | 93 | Gutierrez, Brian A | 25 | 700 | 32675
PR | 120 | 11/05/21 | 98 | Holmes, Anthony R | 9 | 648 | 32680
PR | 120 | 11/05/21 | 98 | Holmes, Anthony R | 28 | 1344 | 32680
PR | 120 | 11/05/21 | 107 | Lovo, German G | 2 | 105 | 32689
PR | 120 | 11/05/21 | 107 | Lovo, German G | 8 | 280 | 32689
PR | 120 | 11/05/21 | 114 | Ortiz Carmona, Jose | 25 | 825 | 32696
PR | 120 | 11/05/21 | 118 | Platero Navas, Julio A | 35 | 665 | 32700
PR | 120 | 11/05/21 | 119 | Platero Navas, Mario N | 8 | 216 | 32701
PR | 120 | 11/05/21 | 119 | Platero Navas, Mario N | 35 | 630 | 32701
PR | 120 | 11/05/21 | 137 | Velasquez Cruz, Denis M | 13 | 760.5 | 32719
PR | 120 | 11/05/21 | 137 | Velasquez Cruz, Denis M | 35 | 1365 | 32719
PR | 120 | 11/05/21 | 138 | Velasquez Cruz, Osman N | 7 | 357 | 32720
PR | 120 | 11/05/21 | 138 | Velasquez Cruz, Osman N | 35 | 1190 | 32720
PR | 120 | 11/12/21 | 269 | Barnhart, Joseph N | 2 | 174 | 32731
PR | 120 | 11/12/21 | 269 | Barnhart, Joseph N | 2 | 116 | 32731
PR | 120 | 11/12/21 | 278 | Castro Urena, Yanely | 40 | 680 | 32740
PR | 120 | 11/12/21 | 283 | Cruz, Azael S | 40 | 1120 | 32745
PR | 120 | 11/12/21 | 304 | Gordillo, Emanuel D | 8 | 228 | 32766
PR | 120 | 11/12/21 | 304 | Gordillo, Emanuel D | 40 | 760 | 32766
PR | 120 | 11/12/21 | 307 | Gutierrez, Brian A | 40 | 1120 | 32769
PR | 120 | 11/12/21 | 312 | Holmes, Anthony R | 8 | 576 | 32774
PR | 120 | 11/12/21 | 312 | Holmes, Anthony R | 24 | 1152 | 32774
PR | 120 | 11/12/21 | 321 | Lovo, German G | 6 | 315 | 32783
PR | 120 | 11/12/21 | 321 | Lovo, German G | 40 | 1400 | 32783
PR | 120 | 11/12/21 | 328 | Ortiz Carmona, Jose | 40 | 1320 | 32790
PR | 120 | 11/12/21 | 332 | Platero Navas, Julio A | 8 | 228 | 32794
PR | 120 | 11/12/21 | 332 | Platero Navas, Julio A | 40 | 760 | 32794
PR | 120 | 11/12/21 | 333 | Platero Navas, Mario N | 38 | 684 | 32795
PR | 120 | 11/12/21 | 351 | Velasquez Cruz, Denis M | 7 | 409.5 | 32813
PR | 120 | 11/12/21 | 351 | Velasquez Cruz, Denis M | 40 | 1560 | 32813
PR | 120 | 11/12/21 | 352 | Velasquez Cruz, Osman N | 7 | 357 | 32814
PR | 120 | 11/12/21 | 352 | Velasquez Cruz, Osman N | 40 | 1360 | 32814
PR | 120 | 11/19/21 | 446 | Castro Urena, Yanely | 35 | 595 | 32832
PR | 120 | 11/19/21 | 451 | Cruz, Azael S | 5 | 210 | 32837
PR | 120 | 11/19/21 | 451 | Cruz, Azael S | 40 | 1120 | 32837
PR | 120 | 11/19/21 | 471 | Gonzalez Hernandez, Josue | 20 | 800 | 32857
PR | 120 | 11/19/21 | 472 | Gordillo, Emanuel D | 6 | 171 | 32858
PR | 120 | 11/19/21 | 472 | Gordillo, Emanuel D | 40 | 760 | 32858
PR | 120 | 11/19/21 | 475 | Gutierrez, Brian A | 20 | 560 | 32861
PR | 120 | 11/19/21 | 480 | Holmes, Anthony R | 1 | 72 | 32866
PR | 120 | 11/19/21 | 480 | Holmes, Anthony R | 4 | 192 | 32866
PR | 120 | 11/19/21 | 489 | Lovo, German G | 2 | 105 | 32875
PR | 120 | 11/19/21 | 489 | Lovo, German G | 40 | 1400 | 32875
PR | 120 | 11/19/21 | 496 | Ortiz Carmona, Jose | 38 | 1254 | 32882
PR | 120 | 11/19/21 | 500 | Platero Navas, Julio A | 4 | 114 | 32886
PR | 120 | 11/19/21 | 500 | Platero Navas, Julio A | 40 | 760 | 32886
PR | 120 | 11/19/21 | 501 | Platero Navas, Mario N | 36 | 648 | 32887
PR | 120 | 11/19/21 | 517 | Velasquez Cruz, Denis M | 10 | 390 | 32903
PR | 120 | 11/19/21 | 518 | Velasquez Cruz, Osman N | 5 | 255 | 32904
PR | 120 | 11/19/21 | 518 | Velasquez Cruz, Osman N | 12 | 408 | 32904
PR | 120 | 11/24/21 | 586 | Castro Urena, Yanely | 26.5 | 450.5 | 32923
PR | 120 | 11/24/21 | 591 | Cruz, Azael S | 36.5 | 1022 | 32928
PR | 120 | 11/24/21 | 611 | Gonzalez Hernandez, Josue | 38 | 1520 | 32948
PR | 120 | 11/24/21 | 615 | Gutierrez, Brian A | 20 | 560 | 32952
PR | 120 | 11/24/21 | 618 | Holmes, Anthony R | 38 | 1824 | 32955
PR | 120 | 11/24/21 | 627 | Lovo, German G | 36 | 1260 | 32964
PR | 120 | 11/24/21 | 634 | Ortiz Carmona, Jose | 36.5 | 1204.5 | 32971
PR | 120 | 11/24/21 | 638 | Platero Navas, Julio A | 29 | 551 | 32975
PR | 120 | 11/24/21 | 639 | Platero Navas, Mario N | 38 | 684 | 32976
PR | 120 | 11/24/21 | 655 | Velasquez Cruz, Denis M | 30 | 1170 | 32992
PR | 120 | 11/24/21 | 656 | Velasquez Cruz, Osman N | 16.5 | 561 | 32993
PR | 120 | 12/03/21 | 13 | Barnhart, Joseph N | 5 | 290 | 33003
PR | 120 | 12/03/21 | 28 | Cruz, Azael S | 38 | 1064 | 33018
PR | 120 | 12/03/21 | 48 | Gonzalez Hernandez, Josue | 38 | 1520 | 33038
PR | 120 | 12/03/21 | 49 | Gordillo, Emanuel D | 38 | 722 | 33039
PR | 120 | 12/03/21 | 56 | Holmes, Anthony R | 38 | 1824 | 33046
PR | 120 | 12/03/21 | 65 | Lovo, German G | 36 | 1260 | 33055
PR | 120 | 12/03/21 | 72 | Ortiz Carmona, Jose | 28 | 924 | 33062
PR | 120 | 12/03/21 | 76 | Platero Navas, Julio A | 38 | 722 | 33066
PR | 120 | 12/03/21 | 77 | Platero Navas, Mario N | 38 | 684 | 33067
PR | 120 | 12/03/21 | 94 | Velasquez Cruz, Denis M | 38 | 1482 | 33084
PR | 120 | 12/03/21 | 95 | Velasquez Cruz, Osman N | 38 | 1292 | 33085
PR | 120 | 12/10/21 | 194 | Barnhart, Joseph N | 8 | 464 | 33093
PR | 120 | 12/10/21 | 229 | Gonzalez Hernandez, Josue | 31 | 1240 | 33128
PR | 120 | 12/10/21 | 230 | Gordillo, Emanuel D | 40 | 760 | 33129
PR | 120 | 12/10/21 | 238 | Holmes, Anthony R | 40 | 1920 | 33137
PR | 120 | 12/10/21 | 247 | Lovo, German G | 24 | 840 | 33146
PR | 120 | 12/10/21 | 255 | Ortiz Carmona, Jose | 24 | 792 | 33154
PR | 120 | 12/10/21 | 259 | Platero Navas, Julio A | 40 | 760 | 33158
PR | 120 | 12/10/21 | 260 | Platero Navas, Mario N | 40 | 720 | 33159
PR | 120 | 12/10/21 | 277 | Velasquez Cruz, Denis M | 24 | 936 | 33176
PR | 120 | 12/10/21 | 278 | Velasquez Cruz, Osman N | 16 | 544 | 33177
PR | 120 | 12/17/21 | 516 | Barnhart, Joseph N | 3 | 174 | 33328
PR | 120 | 12/17/21 | 551 | Gonzalez Hernandez, Josue | 40 | 1600 | 33363
PR | 120 | 12/17/21 | 552 | Gordillo, Emanuel D | 40 | 760 | 33364
PR | 120 | 12/17/21 | 560 | Holmes, Anthony R | 39 | 1872 | 33372
PR | 120 | 12/17/21 | 569 | Lovo, German G | 40 | 1400 | 33381
PR | 120 | 12/17/21 | 581 | Platero Navas, Mario N | 32 | 576 | 33393
PR | 120 | 12/23/21 | 741 | Barnhart, Joseph N | 2 | 116 | 33423
PR | 120 | 12/23/21 | 776 | Gonzalez Hernandez, Josue | 24 | 960 | 33458
PR | 120 | 12/23/21 | 785 | Holmes, Anthony R | 40 | 1920 | 33467
PR | 120 | 12/23/21 | 794 | Lovo, German G | 40 | 1400 | 33476
PR | 120 | 12/23/21 | 806 | Platero Navas, Mario N | 32 | 576 | 33488
PR | 120 | 12/30/21 | 971 | Gonzalez Hernandez, Josue | 8 | 320 | 33551
PR | 120 | 12/30/21 | 980 | Holmes, Anthony R | 13.5 | 648 | 33560
PR | 120 | 12/30/21 | 989 | Lovo, German G | 8 | 280 | 33569
PR | 120 | 12/30/21 | 1002 | Platero Navas, Mario N | 8 | 144 | 33582
PR | 120 | 01/07/22 | 74 | Holmes, Anthony R | 16 | 768 | 33654
PR | 120 | 01/07/22 | 83 | Lovo, German G | 16 | 560 | 33663
PR | 120 | 01/07/22 | 96 | Platero Navas, Mario N | 16 | 288 | 33676
PR | 120 | 01/14/22 | 275 | Holmes, Anthony R | 40 | 1920 | 33747
PR | 120 | 01/14/22 | 283 | Lovo, German G | 40 | 1400 | 33755
PR | 120 | 01/14/22 | 295 | Platero Navas, Julio A | 24 | 456 | 33767
PR | 120 | 01/14/22 | 296 | Platero Navas, Mario N | 40 | 720 | 33768
PR | 120 | 01/21/22 | 458 | Holmes, Anthony R | 32 | 1536 | 33840
PR | 120 | 01/21/22 | 467 | Lovo, German G | 24 | 840 | 33849
PR | 120 | 01/21/22 | 479 | Platero Navas, Julio A | 40 | 760 | 33861
PR | 120 | 01/21/22 | 480 | Platero Navas, Mario N | 24 | 432 | 33862
PR | 120 | 01/28/22 | 659 | Holmes, Anthony R | 40 | 1920 | 33936
PR | 120 | 01/28/22 | 668 | Lovo, German G | 8 | 280 | 33945
PR | 120 | 02/04/22 | 55 | Holmes, Anthony R | 24 | 1152 | 34034
PR | 120 | 02/11/22 | 262 | Holmes, Anthony R | 8 | 384 | 34130
PR | 120 | 02/18/22 | 523 | Gordillo, Emanuel D | 16 | 304 | 34216
PR | 120 | 02/18/22 | 532 | Holmes, Anthony R | 40 | 1920 | 34225
PR | 120 | 02/18/22 | 552 | Platero Navas, Julio A | 16 | 304 | 34245
PR | 120 | 02/25/22 | 752 | Holmes, Anthony R | 40 | 1920 | 34317
PR | 120 | 03/04/22 | 88 | Holmes, Anthony R | 40 | 1920 | 34412
PR | 120 | 03/04/22 | 98 | Lovo, German G | 40 | 1400 | 34422
PR | 120 | 03/04/22 | 110 | Platero Navas, Julio A | 40 | 760 | 34434
PR | 120 | 03/11/22 | 384 | Holmes, Anthony R | 35 | 1680 | 34506
PR | 120 | 03/11/22 | 395 | Lovo, German G | 32 | 1120 | 34517
PR | 120 | 03/11/22 | 407 | Platero Navas, Julio A | 32 | 608 | 34529
PR | 120 | 03/18/22 | 669 | Holmes, Anthony R | 16 | 768 | 34602
PR | 120 | 03/18/22 | 680 | Lovo, German G | 40 | 1400 | 34613
PR | 120 | 03/18/22 | 692 | Platero Navas, Julio A | 40 | 760 | 34625
PR | 120 | 03/25/22 | 927 | Lovo, German G | 38 | 1330 | 34706
PR | 120 | 03/25/22 | 939 | Platero Navas, Julio A | 38 | 722 | 34718
GL | 120 | 03/29/22 | 1042 | Grip SAW Reimb Jose Noe Vazquez BG16730 |  | -534.63
GL | 120 | 04/15/22 | 566 | SAW Reimb Jose Noe Vazquez Popoca |  | -531.48
PR | 120 | 04/22/22 | 803 | Barnhart, Joseph N | 5 | 290 | 35027
PR | 120 | 04/29/22 | 1063 | Barnhart, Joseph N | 3 | 174 | 35119
PR | 120 | 05/06/22 | 128 | Holmes, Anthony R | 13 | 624 | 35249
PR | 120 | 05/13/22 | 363 | Holmes, Anthony R | 4 | 192 | 35337
PR | 120 | 05/20/22 | 598 | Barnhart, Joseph N | 1 | 60 | 35389
PR | 120 | 06/03/22 | 49 | Holmes, Anthony R | 8 | 400 | 35608
PR | 120 | 06/10/22 | 249 | Gordillo, Emanuel D | 8 | 176 | 35688
PR | 120 | 06/17/22 | 465 | Barnhart, Joseph N | 4 | 240 | 35745
PR | 120 | 06/17/22 | 505 | Holmes, Anthony R | 40 | 2000 | 35785
PR | 120 | 06/24/22 | 771 | Barnhart, Joseph N | 2 | 120 | 35837
PR | 120 | 06/24/22 | 809 | Holmes, Anthony R | 39 | 1950 | 35875
PR | 120 | 07/01/22 | 50 | Holmes, Anthony R | 40 | 2000 | 35960
PR | 120 | 07/08/22 | 205 | Gordillo, Emanuel D | 16 | 352 | 36038
PR | 120 | 07/08/22 | 213 | Holmes, Anthony R | 8 | 400 | 36046
PR | 120 | 07/08/22 | 223 | Lovo, German G | 16 | 576 | 36056
PR | 120 | 07/08/22 | 234 | Platero Navas, Julio A | 16 | 336 | 36067
PR | 120 | 07/15/22 | 408 | Holmes, Anthony R | 24 | 1200 | 36131
PR | 120 | 07/22/22 | 608 | Barnhart, Joseph N | 1 | 60 | 36179
PR | 120 | 08/05/22 | 90 | Barnhart, Thomas L | 16 | 624 | 36354
PR | 120 | 08/12/22 | 322 | Holmes, Anthony R | 24 | 1200 | 36464
PR | 120 | 08/19/22 | 495 | Barnhart, Joseph N | 1 | 60 | 36507
PR | 120 | 08/19/22 | 495 | Barnhart, Joseph N | 3 | 180 | 36507
PR | 120 | 09/30/22 | 848 | Holmes, Anthony R | 1 | 50 | 37010
PR | 120 | 10/21/22 | 477 | Barnhart, Joseph N | 6 | 384 | 37226
PR | 120 | 11/18/22 | 368 | Barnhart, Joseph N | 2 | 128 | 37570
PR | 130 | 12/03/21 | 13 | Barnhart, Joseph N | 1 | 58 | 33003
PR | 130 | 12/17/21 | 516 | Barnhart, Joseph N | 3 | 174 | 33328
PR | 130 | 12/17/21 | 517 | Barnhart, Thomas L | 16 | 608 | 33329
PR | 130 | 12/17/21 | 592 | Sanders, Allen O | 3 | 171 | 33404
PR | 130 | 12/23/21 | 742 | Barnhart, Thomas L | 6 | 228 | 33424
PR | 130 | 01/07/22 | 31 | Barnhart, Thomas L | 8 | 304 | 33611
PR | 130 | 01/14/22 | 232 | Barnhart, Thomas L | 40 | 1520 | 33704
PR | 130 | 01/21/22 | 414 | Barnhart, Joseph N | 4 | 232 | 33796
PR | 130 | 01/21/22 | 415 | Barnhart, Thomas L | 32 | 1216 | 33797
PR | 130 | 01/28/22 | 616 | Barnhart, Thomas L | 40 | 1520 | 33893
PR | 130 | 01/28/22 | 630 | Cruz Gonzalez, Julio C | 8 | 256 | 33907
PR | 130 | 01/28/22 | 632 | Cruz Reyes, Jose | 8 | 288 | 33909
PR | 130 | 01/28/22 | 637 | Eliassen, Cory H | 8 | 272 | 33914
PR | 130 | 01/28/22 | 692 | Sanders, Allen O | 4 | 228 | 33969
PR | 130 | 02/04/22 | 12 | Barnhart, Thomas L | 40 | 1520 | 33991
PR | 130 | 02/04/22 | 26 | Cruz Gonzalez, Julio C | 8 | 256 | 34005
PR | 130 | 02/04/22 | 28 | Cruz Reyes, Jose | 8 | 288 | 34007
PR | 130 | 02/04/22 | 33 | Eliassen, Cory H | 8 | 272 | 34012
PR | 130 | 02/04/22 | 87 | Sanders, Allen O | 6 | 342 | 34066
PR | 130 | 02/04/22 | 92 | Trower-Kelly, Fidel D | 8 | 208 | 34071
PR | 130 | 02/11/22 | 217 | Barnhart, Joseph N | 3 | 174 | 34085
PR | 130 | 02/11/22 | 218 | Barnhart, Thomas L | 1 | 57 | 34086
PR | 130 | 02/11/22 | 218 | Barnhart, Thomas L | 40 | 1520 | 34086
PR | 130 | 02/11/22 | 232 | Cruz Gonzalez, Julio C | 1 | 48 | 34100
PR | 130 | 02/11/22 | 232 | Cruz Gonzalez, Julio C | 8 | 256 | 34100
PR | 130 | 02/11/22 | 234 | Cruz Reyes, Jose | 1 | 54 | 34102
PR | 130 | 02/11/22 | 234 | Cruz Reyes, Jose | 8 | 288 | 34102
PR | 130 | 02/11/22 | 239 | Eliassen, Cory H | 8 | 272 | 34107
PR | 130 | 02/11/22 | 295 | Sanders, Allen O | 8.5 | 484.5 | 34163
PR | 130 | 02/18/22 | 488 | Barnhart, Joseph N | 1 | 58 | 34181
PR | 130 | 02/18/22 | 489 | Barnhart, Thomas L | 40 | 1520 | 34182
PR | 130 | 02/18/22 | 504 | Cruz Reyes, Jose | 1 | 54 | 34197
PR | 130 | 02/18/22 | 504 | Cruz Reyes, Jose | 8 | 288 | 34197
PR | 130 | 02/18/22 | 509 | Eliassen, Cory H | 8 | 272 | 34202
PR | 130 | 02/18/22 | 523 | Gordillo, Emanuel D | 16 | 304 | 34216
PR | 130 | 02/18/22 | 552 | Platero Navas, Julio A | 16 | 304 | 34245
PR | 130 | 02/18/22 | 564 | Sanders, Allen O | 12.5 | 712.5 | 34257
PR | 130 | 02/18/22 | 569 | Trower-Kelly, Fidel D | 8.5 | 221 | 34262
PR | 130 | 02/25/22 | 709 | Barnhart, Joseph N | 2 | 116 | 34274
PR | 130 | 02/25/22 | 710 | Barnhart, Thomas L | 40 | 1520 | 34275
PR | 130 | 02/25/22 | 743 | Gordillo, Emanuel D | 40 | 760 | 34308
PR | 130 | 02/25/22 | 772 | Platero Navas, Julio A | 40 | 760 | 34337
PR | 130 | 02/25/22 | 784 | Sanders, Allen O | 5 | 285 | 34349
PR | 130 | 03/04/22 | 45 | Barnhart, Thomas L | 24 | 912 | 34369
PR | 130 | 03/04/22 | 60 | Cruz Reyes, Jose | 8 | 288 | 34384
PR | 130 | 03/04/22 | 79 | Gordillo, Emanuel D | 40 | 760 | 34403
PR | 130 | 03/04/22 | 122 | Sanders, Allen O | 5 | 285 | 34446
PR | 130 | 03/11/22 | 342 | Barnhart, Thomas L | 40 | 1520 | 34464
PR | 130 | 03/11/22 | 376 | Gordillo, Emanuel D | 40 | 760 | 34498
PR | 130 | 03/11/22 | 384 | Holmes, Anthony R | 5 | 240 | 34506
PR | 130 | 03/11/22 | 419 | Sanders, Allen O | 4.5 | 256.5 | 34541
PR | 130 | 03/18/22 | 626 | Barnhart, Joseph N | 1 | 58 | 34559
PR | 130 | 03/18/22 | 627 | Barnhart, Thomas L | 40 | 1520 | 34560
PR | 130 | 03/18/22 | 661 | Gordillo, Emanuel D | 32 | 608 | 34594
PR | 130 | 03/18/22 | 704 | Sanders, Allen O | 7 | 399 | 34637
PR | 130 | 03/25/22 | 876 | Barnhart, Thomas L | 40 | 1520 | 34655
PR | 130 | 03/25/22 | 908 | Gordillo, Emanuel D | 40 | 760 | 34687
PR | 130 | 03/25/22 | 927 | Lovo, German G | 2 | 70 | 34706
PR | 130 | 03/25/22 | 939 | Platero Navas, Julio A | 2 | 38 | 34718
PR | 130 | 03/25/22 | 950 | Sanders, Allen O | 5 | 285 | 34729
PR | 130 | 04/01/22 | 21 | Barnhart, Joseph N | 3 | 174 | 34748
PR | 130 | 04/01/22 | 22 | Barnhart, Thomas L | 40 | 1520 | 34749
PR | 130 | 04/01/22 | 41 | Eliassen, Cory H | 16 | 544 | 34768
PR | 130 | 04/01/22 | 55 | Gordillo, Emanuel D | 40 | 760 | 34782
PR | 130 | 04/01/22 | 74 | Lovo, German G | 40 | 1400 | 34801
PR | 130 | 04/01/22 | 85 | Platero Navas, Julio A | 40 | 760 | 34812
PR | 130 | 04/01/22 | 96 | Sanders, Allen O | 4 | 228 | 34823
PR | 130 | 04/08/22 | 228 | Barnhart, Thomas L | 32 | 1216 | 34842
PR | 130 | 04/08/22 | 261 | Gordillo, Emanuel D | 40 | 760 | 34875
PR | 130 | 04/08/22 | 280 | Lovo, German G | 37.5 | 1312.5 | 34894
PR | 130 | 04/08/22 | 291 | Platero Navas, Julio A | 37.5 | 712.5 | 34905
PR | 130 | 04/08/22 | 317 | Platero Navas, Julio A | 37.5 | -712.5 | 34905
PR | 130 | 04/08/22 | 318 | Platero Navas, Julio A | 37.5 | 712.5 | 34928
PR | 130 | 04/15/22 | 475 | Barnhart, Joseph N | 2 | 116 | 34936
PR | 130 | 04/15/22 | 476 | Barnhart, Thomas L | 24 | 912 | 34937
PR | 130 | 04/15/22 | 508 | Gordillo, Emanuel D | 40 | 880 | 34969
PR | 130 | 04/15/22 | 527 | Lovo, German G | 37.5 | 1312.5 | 34988
PR | 130 | 04/15/22 | 538 | Platero Navas, Julio A | 40 | 840 | 34999
PR | 130 | 04/15/22 | 549 | Sanders, Allen O | 4 | 228 | 35010
PR | 130 | 04/22/22 | 804 | Barnhart, Thomas L | 32 | 1216 | 35028
PR | 130 | 04/22/22 | 836 | Gordillo, Emanuel D | 16 | 352 | 35060
PR | 130 | 04/22/22 | 855 | Lovo, German G | 32 | 1120 | 35079
PR | 130 | 04/22/22 | 866 | Platero Navas, Julio A | 40 | 840 | 35090
PR | 130 | 04/22/22 | 877 | Sanders, Allen O | 6 | 342 | 35101
PR | 130 | 04/29/22 | 1063 | Barnhart, Joseph N | 2 | 116 | 35119
PR | 130 | 04/29/22 | 1064 | Barnhart, Thomas L | 24 | 912 | 35120
PR | 130 | 04/29/22 | 1096 | Gordillo, Emanuel D | 24 | 528 | 35152
PR | 130 | 04/29/22 | 1115 | Lovo, German G | 40 | 1400 | 35171
PR | 130 | 04/29/22 | 1127 | Platero Navas, Julio A | 32 | 672 | 35183
PR | 130 | 04/29/22 | 1137 | Sanders, Allen O | 8 | 456 | 35193
PR | 130 | 05/06/22 | 90 | Barnhart, Joseph N | 3 | 174 | 35211
PR | 130 | 05/06/22 | 91 | Barnhart, Thomas L | 32 | 1216 | 35212
PR | 130 | 05/06/22 | 120 | Gordillo, Emanuel D | 32 | 704 | 35241
PR | 130 | 05/06/22 | 139 | Lovo, German G | 29.5 | 1032.5 | 35260
PR | 130 | 05/06/22 | 151 | Platero Navas, Julio A | 37.5 | 787.5 | 35272
PR | 130 | 05/06/22 | 160 | Sanders, Allen O | 4.5 | 256.5 | 35281
PR | 130 | 05/13/22 | 325 | Barnhart, Thomas L | 32 | 1216 | 35299
PR | 130 | 05/13/22 | 355 | Gordillo, Emanuel D | 40 | 880 | 35329
PR | 130 | 05/13/22 | 373 | Lovo, German G | 24 | 840 | 35347
PR | 130 | 05/13/22 | 385 | Platero Navas, Julio A | 16 | 336 | 35359
PR | 130 | 05/13/22 | 396 | Sanders, Allen O | 8.5 | 484.5 | 35370
PR | 130 | 05/20/22 | 598 | Barnhart, Joseph N | 3 | 180 | 35389
PR | 130 | 05/20/22 | 599 | Barnhart, Thomas L | 32 | 1248 | 35390
PR | 130 | 05/20/22 | 616 | Eliassen, Cory H | 16 | 560 | 35407
PR | 130 | 05/20/22 | 629 | Gordillo, Emanuel D | 16 | 352 | 35420
PR | 130 | 05/20/22 | 647 | Lovo, German G | 24 | 864 | 35438
PR | 130 | 05/20/22 | 659 | Platero Navas, Julio A | 40 | 840 | 35450
PR | 130 | 05/20/22 | 669 | Sanders, Allen O | 5.5 | 324.5 | 35460
PR | 130 | 05/27/22 | 868 | Barnhart, Thomas L | 32 | 1248 | 35478
PR | 130 | 05/27/22 | 886 | Eliassen, Cory H | 16 | 560 | 35496
PR | 130 | 05/27/22 | 899 | Gordillo, Emanuel D | 40 | 880 | 35509
PR | 130 | 05/27/22 | 916 | Lovo, German G | 40 | 1440 | 35526
PR | 130 | 05/27/22 | 928 | Platero Navas, Julio A | 40 | 840 | 35538
PR | 130 | 06/03/22 | 11 | Barnhart, Thomas L | 32 | 1248 | 35570
PR | 130 | 06/03/22 | 29 | Eliassen, Cory H | 16 | 560 | 35588
PR | 130 | 06/03/22 | 41 | Gordillo, Emanuel D | 32 | 704 | 35600
PR | 130 | 06/03/22 | 59 | Lovo, German G | 24 | 864 | 35618
PR | 130 | 06/03/22 | 71 | Platero Navas, Julio A | 24 | 504 | 35630
PR | 130 | 06/10/22 | 220 | Barnhart, Thomas L | 24 | 936 | 35659
PR | 130 | 06/10/22 | 237 | Eliassen, Cory H | 8 | 280 | 35676
PR | 130 | 06/10/22 | 249 | Gordillo, Emanuel D | 24 | 528 | 35688
PR | 130 | 06/10/22 | 257 | Holmes, Anthony R | 8 | 400 | 35696
PR | 130 | 06/10/22 | 267 | Lovo, German G | 32 | 1152 | 35706
PR | 130 | 06/10/22 | 279 | Platero Navas, Julio A | 29.5 | 619.5 | 35718
PR | 130 | 06/10/22 | 289 | Sanders, Allen O | 7 | 413 | 35728
PR | 130 | 06/17/22 | 465 | Barnhart, Joseph N | 1 | 60 | 35745
PR | 130 | 06/17/22 | 466 | Barnhart, Thomas L | 32 | 1248 | 35746
PR | 130 | 06/17/22 | 497 | Gordillo, Emanuel D | 40 | 880 | 35777
PR | 130 | 06/17/22 | 515 | Lovo, German G | 40 | 1440 | 35795
PR | 130 | 06/17/22 | 527 | Platero Navas, Julio A | 40 | 840 | 35807
PR | 130 | 06/17/22 | 537 | Sanders, Allen O | 6.5 | 383.5 | 35817
PR | 130 | 06/24/22 | 771 | Barnhart, Joseph N | 4 | 240 | 35837
PR | 130 | 06/24/22 | 772 | Barnhart, Thomas L | 32 | 1248 | 35838
PR | 130 | 06/24/22 | 801 | Gordillo, Emanuel D | 23 | 506 | 35867
PR | 130 | 06/24/22 | 819 | Lovo, German G | 24 | 864 | 35885
PR | 130 | 06/24/22 | 830 | Platero Navas, Julio A | 32 | 672 | 35896
PR | 130 | 06/24/22 | 839 | Sanders, Allen O | 8 | 472 | 35905
PR | 130 | 07/01/22 | 13 | Barnhart, Thomas L | 32 | 1248 | 35923
PR | 130 | 07/01/22 | 42 | Gordillo, Emanuel D | 40 | 880 | 35952
PR | 130 | 07/01/22 | 70 | Platero Navas, Julio A | 26 | 546 | 35980
PR | 130 | 07/08/22 | 175 | Barnhart, Thomas L | 24 | 936 | 36008
PR | 130 | 07/08/22 | 205 | Gordillo, Emanuel D | 16 | 352 | 36038
PR | 130 | 07/08/22 | 213 | Holmes, Anthony R | 16 | 800 | 36046
PR | 130 | 07/08/22 | 223 | Lovo, German G | 16 | 576 | 36056
PR | 130 | 07/08/22 | 234 | Platero Navas, Julio A | 16 | 336 | 36067
PR | 130 | 07/15/22 | 369 | Barnhart, Joseph N | 1 | 60 | 36092
PR | 130 | 07/15/22 | 370 | Barnhart, Thomas L | 32 | 1248 | 36093
PR | 130 | 07/15/22 | 400 | Gordillo, Emanuel D | 39 | 858 | 36123
PR | 130 | 07/15/22 | 417 | Lovo, German G | 40 | 1440 | 36140
PR | 130 | 07/15/22 | 429 | Platero Navas, Julio A | 40 | 840 | 36152
PR | 130 | 07/22/22 | 609 | Barnhart, Thomas L | 40 | 1560 | 36180
PR | 130 | 07/22/22 | 638 | Gordillo, Emanuel D | 31 | 682 | 36209
PR | 130 | 07/22/22 | 644 | Holmes, Anthony R | 31 | 1550 | 36215
PR | 130 | 07/22/22 | 673 | Sanders, Allen O | 10.5 | 619.5 | 36244
PR | 130 | 07/29/22 | 753 | Gordillo, Emanuel D | 28 | 616 | 36298
PR | 130 | 07/29/22 | 759 | Holmes, Anthony R | 28 | 1400 | 36304
PR | 130 | 08/05/22 | 90 | Barnhart, Thomas L | 8 | 312 | 36354
PR | 130 | 08/19/22 | 496 | Barnhart, Thomas L | 16 | 624 | 36508
PR | 130 | 08/26/22 | 762 | Barnhart, Thomas L | 8 | 312 | 36587
PR | 130 | 09/02/22 | 9 | Barnhart, Thomas L | 24 | 936 | 36665
PR | 130 | 09/02/22 | 37 | Gordillo, Emanuel D | 1 | 22 | 36693
PR | 130 | 09/09/22 | 201 | Barnhart, Thomas L | 16 | 624 | 36743
PR | 130 | 09/09/22 | 265 | Sanders, Allen O | 3 | 177 | 36807
PR | 130 | 09/16/22 | 430 | Barnhart, Joseph N | 2 | 120 | 36820
PR | 130 | 09/23/22 | 565 | Barnhart, Thomas L | 8 | 312 | 36900
PR | 130 | 09/23/22 | 625 | Sanders, Allen O | 4 | 236 | 36960
PR | 130 | 09/30/22 | 815 | Barnhart, Joseph N | 2 | 120 | 36977
PR | 130 | 09/30/22 | 816 | Barnhart, Thomas L | 8 | 312 | 36978
PR | 130 | 10/07/22 | 28 | Barnhart, Joseph N | 4 | 256 | 37056
PR | 130 | 10/14/22 | 283 | Barnhart, Joseph N | 1 | 64 | 37140
PR | 130 | 10/21/22 | 477 | Barnhart, Joseph N | 1 | 64 | 37226
PR | 130 | 11/18/22 | 368 | Barnhart, Joseph N | 2 | 128 | 37570
PR | 130 | 12/02/22 | 9 | Barnhart, Joseph N | 1 | 64 | 37748
PR | 140 | 04/09/21 | 135 | Gordillo, Emanuel D | 18 | 306 | 30313
PR | 140 | 04/09/21 | 138 | Holmes, Anthony R | 18 | 828 | 30316
PR | 140 | 04/16/21 | 279 | Gordillo, Emanuel D | 19 | 323 | 30377
PR | 140 | 04/16/21 | 284 | Holmes, Anthony R | 17 | 782 | 30382
PR | 140 | 04/23/21 | 404 | Barnhart, Joseph N | 1 | 56 | 30417
PR | 140 | 08/20/21 | 587 | Barnhart, Joseph N | 1 | 56 | 31680
PR | 140 | 08/20/21 | 629 | Lovo, German G | 12 | 396 | 31722
PR | 140 | 08/20/21 | 656 | Velasquez Cruz, Denis M | 20 | 740 | 31749
PR | 140 | 08/20/21 | 657 | Velasquez Cruz, Osman N | 20 | 640 | 31750
PR | 140 | 08/27/21 | 807 | Barnhart, Joseph N | 2 | 112 | 31759
PR | 140 | 08/27/21 | 841 | Holmes, Anthony R | 5 | 230 | 31793
PR | 140 | 08/27/21 | 877 | Velasquez Cruz, Denis M | 10 | 370 | 31829
PR | 140 | 08/27/21 | 878 | Velasquez Cruz, Osman N | 10 | 320 | 31830
PR | 140 | 09/17/21 | 373 | Holmes, Anthony R | 1 | 48 | 32043
PR | 140 | 10/01/21 | 9 | Barnhart, Joseph N | 1 | 58 | 32179
PR | 140 | 10/08/21 | 297 | Barnhart, Joseph N | 2 | 116 | 32268
PR | 140 | 10/08/21 | 336 | Holmes, Anthony R | 1 | 48 | 32307
PR | 140 | 10/29/21 | 1059 | Lovo, German G | 24.5 | 857.5 | 32596
PR | 140 | 11/05/21 | 98 | Holmes, Anthony R | 2 | 144 | 32680
PR | 140 | 11/05/21 | 98 | Holmes, Anthony R | 7 | 336 | 32680
PR | 140 | 11/05/21 | 107 | Lovo, German G | 4 | 210 | 32689
PR | 140 | 11/05/21 | 107 | Lovo, German G | 27 | 945 | 32689
PR | 140 | 11/12/21 | 269 | Barnhart, Joseph N | 2 | 116 | 32731
PR | 140 | 11/12/21 | 312 | Holmes, Anthony R | 7 | 336 | 32774
PR | 140 | 11/19/21 | 480 | Holmes, Anthony R | 3 | 216 | 32866
PR | 140 | 11/19/21 | 480 | Holmes, Anthony R | 7 | 336 | 32866
PR | 140 | 11/19/21 | 517 | Velasquez Cruz, Denis M | 5 | 292.5 | 32903
PR | 140 | 11/19/21 | 517 | Velasquez Cruz, Denis M | 28 | 1092 | 32903
PR | 140 | 11/19/21 | 518 | Velasquez Cruz, Osman N | 26 | 884 | 32904
PR | 140 | 11/24/21 | 655 | Velasquez Cruz, Denis M | 6.5 | 253.5 | 32992
PR | 140 | 11/24/21 | 656 | Velasquez Cruz, Osman N | 20 | 680 | 32993
PR | 140 | 12/03/21 | 13 | Barnhart, Joseph N | 1 | 58 | 33003
PR | 140 | 12/17/21 | 560 | Holmes, Anthony R | 1 | 48 | 33372
PR | 140 | 02/11/22 | 262 | Holmes, Anthony R | 1 | 48 | 34130
PR | 140 | 04/29/22 | 1063 | Barnhart, Joseph N | 1 | 58 | 35119
PR | 140 | 06/03/22 | 49 | Holmes, Anthony R | 24 | 1200 | 35608
PR | 140 | 08/19/22 | 496 | Barnhart, Thomas L | 24 | 936 | 36508
PR | 140 | 08/19/22 | 530 | Holmes, Anthony R | 24 | 1200 | 36542
PR | 140 | 09/16/22 | 430 | Barnhart, Joseph N | 3 | 180 | 36820
PR | 140 | 09/16/22 | 460 | Gordillo, Emanuel D | 7 | 154 | 36850
PR | 140 | 09/16/22 | 465 | Holmes, Anthony R | 7 | 350 | 36855
PR | 140 | 09/30/22 | 815 | Barnhart, Joseph N | 4 | 240 | 36977
PR | 140 | 10/07/22 | 28 | Barnhart, Joseph N | 3 | 192 | 37056
PR | 140 | 10/14/22 | 283 | Barnhart, Joseph N | 1 | 64 | 37140
PR | 140 | 11/23/22 | 513 | Barnhart, Joseph N | 1 | 64 | 37661
PR | 140 | 12/02/22 | 39 | Gordillo, Emanuel D | 2 | 44 | 37778
PR | 140 | 12/02/22 | 44 | Holmes, Anthony R | 2 | 108 | 37783
PR | 140 | 12/09/22 | 303 | Holmes, Anthony R | 2 | 108 | 37875
PR | 141 | 02/07/20 | 57 | Hoeg, Xavier A | 2 | 36 | 26805
PR | 141 | 02/07/20 | 58 | Holmes, Anthony R | 4 | 176 | 26806
PR | 141 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I | 2 | 72 | 27247
PR | 141 | 03/20/20 | 569 | Barnhart, Joseph N | 3 | 162 | 27249
PR | 141 | 03/20/20 | 622 | Rodriguez Arevalos, Christian | 2 | 60 | 27302
PR | 141 | 03/20/20 | 632 | Taylor, Evan R | 6 | 198 | 27312
PR | 141 | 03/20/20 | 638 | Waites, Thaddeus Z | 6 | 294 | 27318
PR | 141 | 03/26/20 | 811 | Taylor, Evan R | 16 | 528 | 27387
PR | 141 | 03/26/20 | 817 | Waites, Thaddeus Z | 16 | 784 | 27393
PR | 141 | 07/02/20 | 7 | Barnhart, Joseph N | 2 | 108 | 28250
PR | 141 | 07/10/20 | 175 | Ross, Kelli M | 16 | 688 | 28334
PR | 141 | 07/10/20 | 178 | Stahlschmidt, John P | 16 | 352 | 28337
PR | 141 | 07/10/20 | 181 | Waites, Thaddeus Z | 16 | 784 | 28340
PR | 141 | 07/17/20 | 305 | Stahlschmidt, John P | 8 | 176 | 28385
PR | 141 | 07/17/20 | 308 | Waites, Thaddeus Z | 8 | 392 | 28388
GL | 141 | 12/31/20 | 654 | Reimb Kelli Ross |  | -365.3
PR | 141 | 02/05/21 | 71 | Barnhart, Joseph N | 2 | 108 | 29762
PR | 141 | 02/05/21 | 91 | Gordillo, Emanuel D | 8 | 128 | 29782
PR | 141 | 02/05/21 | 93 | Holmes, Anthony R | 8 | 352 | 29784
PR | 141 | 02/12/21 | 277 | Gordillo, Emanuel D | 8 | 128 | 29838
PR | 141 | 02/12/21 | 279 | Holmes, Anthony R | 8 | 352 | 29840
PR | 141 | 03/12/21 | 201 | Gonzalez Hernandez, Josue | 13 | 468 | 30067
PR | 141 | 03/12/21 | 205 | Holmes, Anthony R | 3 | 132 | 30071
PR | 141 | 03/12/21 | 209 | Lee, Ha Nul | 13 | 325 | 30075
PR | 141 | 03/19/21 | 314 | Gonzalez Hernandez, Josue | 40 | 1520 | 30127
PR | 141 | 03/19/21 | 322 | Lee, Ha Nul | 40 | 1080 | 30135
PR | 141 | 03/26/21 | 545 | Gonzalez Hernandez, Josue | 32 | 1216 | 30188
PR | 141 | 03/26/21 | 553 | Lee, Ha Nul | 38 | 1026 | 30196
PR | 141 | 04/02/21 | 7 | Barnhart, Joseph N | 2 | 112 | 30226
PR | 141 | 04/02/21 | 30 | Gonzalez Hernandez, Josue | 40 | 1520 | 30249
PR | 141 | 04/02/21 | 34 | Holmes, Anthony R | 21 | 966 | 30253
PR | 141 | 04/02/21 | 38 | Lee, Ha Nul | 40 | 1080 | 30257
PR | 141 | 04/02/21 | 62 | Waites, Thaddeus Z | 7 | 350 | 30281
PR | 141 | 04/09/21 | 134 | Gonzalez Hernandez, Josue | 40 | 1520 | 30312
PR | 141 | 04/09/21 | 142 | Lee, Ha Nul | 40 | 1080 | 30320
PR | 141 | 04/16/21 | 278 | Gonzalez Hernandez, Josue | 32 | 1216 | 30376
PR | 141 | 04/16/21 | 284 | Holmes, Anthony R | 1 | 46 | 30382
PR | 141 | 04/16/21 | 287 | Lee, Ha Nul | 40 | 1080 | 30385
PR | 141 | 04/23/21 | 404 | Barnhart, Joseph N | 1 | 56 | 30417
PR | 141 | 04/23/21 | 429 | Gonzalez Hernandez, Josue | 40 | 1520 | 30442
PR | 141 | 04/23/21 | 436 | Holmes, Anthony R | 1 | 46 | 30449
PR | 141 | 04/23/21 | 439 | Lee, Ha Nul | 24 | 648 | 30452
PR | 141 | 04/23/21 | 449 | Platero Navas, Julio A | 24 | 432 | 30462
PR | 141 | 04/30/21 | 574 | Barnhart, Joseph N | 2 | 112 | 30484
PR | 141 | 04/30/21 | 599 | Gonzalez Hernandez, Josue | 40 | 1520 | 30509
PR | 141 | 04/30/21 | 606 | Holmes, Anthony R | 2 | 92 | 30516
PR | 141 | 04/30/21 | 620 | Platero Navas, Julio A | 40 | 720 | 30530
PR | 141 | 05/07/21 | 41 | Barnhart, Joseph N | 1 | 56 | 30554
PR | 141 | 05/07/21 | 66 | Gonzalez Hernandez, Josue | 40 | 1520 | 30579
PR | 141 | 05/07/21 | 88 | Platero Navas, Julio A | 40 | 720 | 30601
PR | 141 | 05/14/21 | 246 | Barnhart, Joseph N | 1 | 56 | 30625
PR | 141 | 05/14/21 | 270 | Gonzalez Hernandez, Josue | 21 | 798 | 30649
PR | 141 | 05/14/21 | 276 | Holmes, Anthony R | 1 | 46 | 30655
PR | 141 | 05/14/21 | 280 | Lee, Ha Nul | 1 | 27 | 30659
PR | 141 | 05/14/21 | 292 | Platero Navas, Julio A | 24 | 432 | 30671
PR | 141 | 05/28/21 | 656 | Gonzalez Hernandez, Josue | 32 | 1216 | 30786
PR | 141 | 05/28/21 | 663 | Holmes, Anthony R | 1 | 46 | 30793
PR | 141 | 05/28/21 | 665 | Hubbard, Robert W | 5 | 275 | 30795
PR | 141 | 05/28/21 | 667 | Lee, Ha Nul | 16 | 432 | 30797
PR | 141 | 05/28/21 | 680 | Platero Navas, Julio A | 32 | 576 | 30810
PR | 141 | 06/04/21 | 56 | Gonzalez Hernandez, Josue | 32 | 1216 | 30861
PR | 141 | 06/04/21 | 67 | Lee, Ha Nul | 10 | 270 | 30872
PR | 141 | 06/04/21 | 81 | Platero Navas, Julio A | 32 | 576 | 30886
PR | 141 | 06/04/21 | 82 | Platero Navas, Mario N | 32 | 544 | 30887
PR | 141 | 06/11/21 | 203 | Barnhart, Joseph N | 1 | 56 | 30909
PR | 141 | 06/11/21 | 229 | Gonzalez Hernandez, Josue | 16 | 608 | 30935
PR | 141 | 06/11/21 | 236 | Holmes, Anthony R | 3 | 138 | 30942
PR | 141 | 06/11/21 | 250 | Ortiz Carmona, Jose | 24 | 768 | 30956
PR | 141 | 06/11/21 | 253 | Platero Navas, Julio A | 40 | 720 | 30959
PR | 141 | 06/18/21 | 410 | Castro Hernandez, Jose A | 8 | 352 | 30988
PR | 141 | 06/18/21 | 438 | Holmes, Anthony R | 12 | 552 | 31016
PR | 141 | 06/18/21 | 442 | Lee, Ha Nul | 2 | 54 | 31020
PR | 141 | 06/25/21 | 626 | Gonzalez Hernandez, Josue | 16 | 608 | 31084
PR | 141 | 06/25/21 | 633 | Holmes, Anthony R | 11 | 506 | 31091
PR | 141 | 06/25/21 | 637 | Lee, Ha Nul | 8 | 216 | 31095
PR | 141 | 06/25/21 | 650 | Platero Navas, Julio A | 16 | 288 | 31108
PR | 141 | 07/02/21 | 35 | Gonzalez Hernandez, Josue | 5.5 | 209 | 31158
PR | 141 | 07/02/21 | 40 | Holmes, Anthony R | 13 | 598 | 31163
PR | 141 | 07/02/21 | 44 | Lee, Ha Nul | 6 | 162 | 31167
PR | 141 | 07/02/21 | 55 | Ortiz Carmona, Jose | 20 | 640 | 31178
PR | 141 | 07/02/21 | 58 | Platero Navas, Julio A | 16 | 288 | 31181
PR | 141 | 07/09/21 | 135 | Holmes, Anthony R | 4 | 184 | 31238
PR | 141 | 07/09/21 | 150 | Ortiz Carmona, Jose | 30 | 960 | 31253
PR | 141 | 07/09/21 | 153 | Platero Navas, Julio A | 32 | 576 | 31256
PR | 141 | 07/16/21 | 322 | Barnhart, Joseph N | 2 | 112 | 31283
PR | 141 | 07/16/21 | 368 | Ortiz Carmona, Jose | 40 | 1280 | 31329
PR | 141 | 07/16/21 | 371 | Platero Navas, Julio A | 40 | 720 | 31332
PR | 141 | 07/16/21 | 372 | Platero Navas, Mario N | 16 | 272 | 31333
PR | 141 | 07/23/21 | 519 | Gonzalez Hernandez, Josue | 4 | 152 | 31387
PR | 141 | 07/23/21 | 540 | Ortiz Carmona, Jose | 40 | 1280 | 31408
PR | 141 | 07/23/21 | 543 | Platero Navas, Julio A | 40 | 720 | 31411
PR | 141 | 07/30/21 | 684 | Barnhart, Joseph N | 2 | 112 | 31440
PR | 141 | 07/30/21 | 733 | Ortiz Carmona, Jose | 40 | 1280 | 31489
PR | 141 | 07/30/21 | 736 | Platero Navas, Julio A | 40 | 720 | 31492
PR | 141 | 08/06/21 | 92 | Ortiz Carmona, Jose | 40 | 1280 | 31570
PR | 141 | 08/06/21 | 95 | Platero Navas, Julio A | 40 | 720 | 31573
PR | 141 | 08/13/21 | 338 | Holmes, Anthony R | 4 | 184 | 31633
PR | 141 | 08/13/21 | 346 | Lovo, German G | 6 | 198 | 31641
PR | 141 | 08/13/21 | 354 | Ortiz Carmona, Jose | 28 | 896 | 31649
PR | 141 | 08/13/21 | 357 | Platero Navas, Julio A | 32 | 576 | 31652
PR | 141 | 08/13/21 | 358 | Platero Navas, Mario N | 4 | 68 | 31653
PR | 141 | 08/13/21 | 374 | Velasquez Cruz, Osman N | 6 | 192 | 31669
PR | 141 | 08/20/21 | 617 | Gutierrez, Brian A | 39 | 663 | 31710
PR | 141 | 08/20/21 | 620 | Holmes, Anthony R | 30 | 1380 | 31713
PR | 141 | 08/20/21 | 626 | Lee, Ha Nul | 25.5 | 688.5 | 31719
PR | 141 | 08/20/21 | 629 | Lovo, German G | 28 | 924 | 31722
PR | 141 | 08/20/21 | 637 | Ortiz Carmona, Jose | 40 | 1280 | 31730
PR | 141 | 08/20/21 | 640 | Platero Navas, Julio A | 33.5 | 603 | 31733
PR | 141 | 08/20/21 | 641 | Platero Navas, Mario N | 24 | 408 | 31734
PR | 141 | 08/20/21 | 657 | Velasquez Cruz, Osman N | 10 | 320 | 31750
PR | 141 | 08/27/21 | 807 | Barnhart, Joseph N | 1 | 56 | 31759
PR | 141 | 08/27/21 | 838 | Gutierrez, Brian A | 32 | 544 | 31790
PR | 141 | 08/27/21 | 841 | Holmes, Anthony R | 35 | 1610 | 31793
PR | 141 | 08/27/21 | 857 | Ortiz Carmona, Jose | 20 | 640 | 31809
PR | 141 | 08/27/21 | 860 | Platero Navas, Julio A | 33.5 | 603 | 31812
PR | 141 | 08/27/21 | 861 | Platero Navas, Mario N | 40 | 680 | 31813
PR | 141 | 09/03/21 | 8 | Barnhart, Joseph N | 5 | 280 | 31840
PR | 141 | 09/03/21 | 20 | Cruz, Azael S | 30 | 810 | 31852
PR | 141 | 09/03/21 | 40 | Gutierrez, Brian A | 16 | 272 | 31872
PR | 141 | 09/03/21 | 59 | Ortiz Carmona, Jose | 30 | 960 | 31891
PR | 141 | 09/03/21 | 62 | Platero Navas, Julio A | 8 | 144 | 31894
PR | 141 | 09/03/21 | 63 | Platero Navas, Mario N | 16 | 272 | 31895
PR | 141 | 09/10/21 | 188 | Cruz, Azael S | 30 | 840 | 31936
PR | 141 | 09/10/21 | 208 | Gutierrez, Brian A | 9 | 153 | 31956
PR | 141 | 09/10/21 | 227 | Ortiz Carmona, Jose | 20 | 660 | 31975
PR | 141 | 09/17/21 | 338 | Barnhart, Joseph N | 1 | 58 | 32008
PR | 141 | 09/17/21 | 389 | Ortiz Carmona, Jose | 40 | 1320 | 32059
PR | 141 | 09/24/21 | 492 | Barnhart, Joseph N | 2 | 116 | 32092
PR | 141 | 09/24/21 | 504 | Cruz, Azael S | 10 | 280 | 32104
PR | 141 | 09/24/21 | 543 | Ortiz Carmona, Jose | 7 | 346.5 | 32143
PR | 141 | 09/24/21 | 543 | Ortiz Carmona, Jose | 40 | 1320 | 32143
PR | 141 | 10/01/21 | 21 | Cruz, Azael S | 40 | 1120 | 32191
PR | 141 | 10/01/21 | 60 | Ortiz Carmona, Jose | 30 | 990 | 32230
PR | 141 | 10/08/21 | 310 | Cruz, Azael S | 7 | 294 | 32281
PR | 141 | 10/08/21 | 310 | Cruz, Azael S | 40 | 1120 | 32281
PR | 141 | 10/08/21 | 329 | Gonzalez Hernandez, Josue | 25 | 1000 | 32300
PR | 141 | 10/08/21 | 353 | Ortiz Carmona, Jose | 7 | 346.5 | 32324
PR | 141 | 10/08/21 | 353 | Ortiz Carmona, Jose | 30 | 990 | 32324
PR | 141 | 10/08/21 | 357 | Platero Navas, Julio A | 23 | 437 | 32328
PR | 141 | 10/15/21 | 561 | Barnhart, Joseph N | 2 | 116 | 32358
PR | 141 | 10/15/21 | 574 | Cruz, Azael S | 7 | 294 | 32371
PR | 141 | 10/15/21 | 574 | Cruz, Azael S | 40 | 1120 | 32371
PR | 141 | 10/15/21 | 594 | Gonzalez Hernandez, Josue | 8 | 480 | 32391
PR | 141 | 10/15/21 | 594 | Gonzalez Hernandez, Josue | 40 | 1600 | 32391
PR | 141 | 10/15/21 | 601 | Holmes, Anthony R | 2 | 96 | 32398
PR | 141 | 10/15/21 | 617 | Ortiz Carmona, Jose | 7 | 346.5 | 32414
PR | 141 | 10/15/21 | 617 | Ortiz Carmona, Jose | 40 | 1320 | 32414
PR | 141 | 10/15/21 | 621 | Platero Navas, Julio A | 38 | 722 | 32418
PR | 141 | 10/22/21 | 762 | Cruz, Azael S | 7 | 294 | 32466
PR | 141 | 10/22/21 | 762 | Cruz, Azael S | 40 | 1120 | 32466
PR | 141 | 10/22/21 | 782 | Gonzalez Hernandez, Josue | 8 | 480 | 32486
PR | 141 | 10/22/21 | 782 | Gonzalez Hernandez, Josue | 40 | 1600 | 32486
PR | 141 | 10/22/21 | 807 | Ortiz Carmona, Jose | 40 | 1320 | 32511
PR | 141 | 10/22/21 | 811 | Platero Navas, Julio A | 8 | 228 | 32515
PR | 141 | 10/22/21 | 811 | Platero Navas, Julio A | 40 | 760 | 32515
PR | 141 | 10/29/21 | 1008 | Barnhart, Joseph N | 2 | 174 | 32545
PR | 141 | 10/29/21 | 1008 | Barnhart, Joseph N | 1 | 58 | 32545
PR | 141 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue | 6.5 | 390 | 32579
PR | 141 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue | 20 | 800 | 32579
PR | 141 | 10/29/21 | 1066 | Ortiz Carmona, Jose | 10 | 330 | 32603
PR | 141 | 11/05/21 | 63 | Castro Urena, Yanely | 10 | 170 | 32645
PR | 141 | 11/05/21 | 68 | Cruz, Azael S | 5 | 140 | 32650
PR | 141 | 11/05/21 | 89 | Gonzalez Hernandez, Josue | 5 | 200 | 32671
PR | 141 | 11/05/21 | 90 | Gordillo, Emanuel D | 10 | 285 | 32672
PR | 141 | 11/05/21 | 90 | Gordillo, Emanuel D | 5 | 95 | 32672
PR | 141 | 11/05/21 | 93 | Gutierrez, Brian A | 5 | 140 | 32675
PR | 141 | 11/05/21 | 98 | Holmes, Anthony R | 7 | 504 | 32680
PR | 141 | 11/05/21 | 98 | Holmes, Anthony R | 5 | 240 | 32680
PR | 141 | 11/05/21 | 107 | Lovo, German G | 5 | 175 | 32689
PR | 141 | 11/05/21 | 114 | Ortiz Carmona, Jose | 15 | 495 | 32696
PR | 141 | 11/05/21 | 118 | Platero Navas, Julio A | 5 | 95 | 32700
PR | 141 | 11/05/21 | 119 | Platero Navas, Mario N | 5 | 90 | 32701
PR | 141 | 11/05/21 | 137 | Velasquez Cruz, Denis M | 5 | 195 | 32719
PR | 141 | 11/05/21 | 138 | Velasquez Cruz, Osman N | 5 | 170 | 32720
PR | 141 | 11/12/21 | 269 | Barnhart, Joseph N | 2 | 116 | 32731
PR | 141 | 11/12/21 | 303 | Gonzalez Hernandez, Josue | 8 | 480 | 32765
PR | 141 | 11/12/21 | 303 | Gonzalez Hernandez, Josue | 40 | 1600 | 32765
PR | 141 | 11/12/21 | 312 | Holmes, Anthony R | 9 | 432 | 32774
PR | 141 | 11/19/21 | 437 | Barnhart, Joseph N | 5 | 290 | 32823
PR | 141 | 11/19/21 | 471 | Gonzalez Hernandez, Josue | 18 | 720 | 32857
PR | 141 | 11/19/21 | 480 | Holmes, Anthony R | 10 | 480 | 32866
PR | 141 | 11/19/21 | 518 | Velasquez Cruz, Osman N | 2 | 68 | 32904
PR | 141 | 11/24/21 | 612 | Gordillo, Emanuel D | 38 | 722 | 32949
PR | 141 | 12/03/21 | 13 | Barnhart, Joseph N | 1 | 58 | 33003
PR | 141 | 12/10/21 | 209 | Cruz, Azael S | 24 | 672 | 33108
PR | 141 | 12/10/21 | 229 | Gonzalez Hernandez, Josue | 1 | 40 | 33128
PR | 141 | 12/17/21 | 516 | Barnhart, Joseph N | 1 | 58 | 33328
PR | 141 | 12/17/21 | 581 | Platero Navas, Mario N | 4 | 72 | 33393
PR | 141 | 12/23/21 | 777 | Gordillo, Emanuel D | 32 | 608 | 33459
PR | 141 | 12/23/21 | 806 | Platero Navas, Mario N | 8 | 144 | 33488
PR | 141 | 12/30/21 | 972 | Gordillo, Emanuel D | 13.5 | 256.5 | 33552
PR | 141 | 01/07/22 | 65 | Gordillo, Emanuel D | 24 | 456 | 33645
PR | 141 | 01/14/22 | 266 | Gordillo, Emanuel D | 40 | 760 | 33738
PR | 141 | 01/21/22 | 449 | Gordillo, Emanuel D | 40 | 760 | 33831
PR | 141 | 01/28/22 | 650 | Gordillo, Emanuel D | 40 | 760 | 33927
PR | 141 | 01/28/22 | 680 | Platero Navas, Julio A | 40 | 760 | 33957
PR | 141 | 01/28/22 | 681 | Platero Navas, Mario N | 40 | 720 | 33958
PR | 141 | 02/04/22 | 11 | Barnhart, Joseph N | 8 | 464 | 33990
PR | 141 | 02/04/22 | 46 | Gordillo, Emanuel D | 32 | 608 | 34025
PR | 141 | 02/04/22 | 75 | Platero Navas, Mario N | 24 | 432 | 34054
PR | 141 | 02/11/22 | 253 | Gordillo, Emanuel D | 40 | 760 | 34121
PR | 141 | 02/11/22 | 282 | Platero Navas, Julio A | 40 | 760 | 34150
PR | 141 | 02/11/22 | 283 | Platero Navas, Mario N | 16 | 288 | 34151
PR | 141 | 06/17/22 | 484 | Eliassen, Cory H | 4.5 | 236.25 | 35764
PR | 141 | 06/17/22 | 497 | Gordillo, Emanuel D | 7.5 | 247.5 | 35777
PR | 141 | 06/17/22 | 505 | Holmes, Anthony R | 7.5 | 562.5 | 35785
PR | 141 | 06/17/22 | 518 | McCabe, Thomas C | 3.5 | 220.5 | 35798
PR | 141 | 06/17/22 | 518 | McCabe, Thomas C | 1 | 42 | 35798
PR | 141 | 06/17/22 | 534 | Romero Garza, Jesus I | 4.5 | 182.25 | 35814
PR | 141 | 06/17/22 | 537 | Sanders, Allen O | 4.5 | 398.25 | 35817
PR | 141 | 06/17/22 | 537 | Sanders, Allen O | 3 | 177 | 35817
PR | 141 | 06/17/22 | 540 | Taylor, Evan R | 4.5 | 303.75 | 35820
PR | 141 | 06/17/22 | 541 | Trower-Kelly, Fidel D | 4.5 | 182.25 | 35821
PR | 141 | 07/01/22 | 13 | Barnhart, Thomas L | 5 | 195 | 35923
PR | 141 | 07/01/22 | 31 | Eliassen, Cory H | 5 | 262.5 | 35941
PR | 141 | 07/01/22 | 62 | McCabe, Thomas C | 4 | 252 | 35972
PR | 141 | 07/01/22 | 62 | McCabe, Thomas C | 1 | 42 | 35972
PR | 141 | 07/01/22 | 78 | Sanders, Allen O | 7 | 619.5 | 35988
PR | 141 | 07/01/22 | 78 | Sanders, Allen O | 2 | 118 | 35988
PR | 141 | 07/01/22 | 81 | Taylor, Evan R | 9 | 607.5 | 35991
PR | 141 | 07/01/22 | 82 | Trower-Kelly, Fidel D | 5 | 135 | 35992
PR | 141 | 07/01/22 | 84 | Waites, Thaddeus Z | 5 | 405 | 35994
PR | 142 | 02/07/20 | 61 | Hubbard, Robert W | 4 | 216 | 26809
PR | 142 | 02/28/20 | 684 | Barnhart, Joseph N | 2 | 108 | 27012
PR | 142 | 03/13/20 | 311 | Barnhart, Joseph N | 3 | 162 | 27171
PR | 142 | 03/20/20 | 569 | Barnhart, Joseph N | 6 | 324 | 27249
PR | 142 | 03/20/20 | 600 | Hubbard, Robert W | 4 | 216 | 27280
PR | 142 | 02/26/21 | 597 | Barnhart, Joseph N | 2 | 108 | 29933
PR | 142 | 04/23/21 | 404 | Barnhart, Joseph N | 3 | 168 | 30417
PR | 142 | 04/30/21 | 574 | Barnhart, Joseph N | 2 | 112 | 30484
PR | 142 | 05/07/21 | 41 | Barnhart, Joseph N | 1 | 56 | 30554
PR | 142 | 05/14/21 | 246 | Barnhart, Joseph N | 5 | 280 | 30625
PR | 142 | 05/14/21 | 278 | Hubbard, Robert W | 13 | 715 | 30657
PR | 142 | 05/21/21 | 391 | Barnhart, Joseph N | 1 | 56 | 30693
PR | 142 | 05/28/21 | 665 | Hubbard, Robert W | 3 | 165 | 30795
PR | 142 | 06/11/21 | 203 | Barnhart, Joseph N | 1 | 56 | 30909
PR | 142 | 06/11/21 | 229 | Gonzalez Hernandez, Josue | 14 | 532 | 30935
PR | 142 | 06/11/21 | 238 | Hubbard, Robert W | 16 | 880 | 30944
PR | 142 | 06/18/21 | 431 | Gonzalez Hernandez, Josue | 24 | 912 | 31009
PR | 142 | 06/18/21 | 440 | Hubbard, Robert W | 12 | 660 | 31018
PR | 142 | 06/25/21 | 626 | Gonzalez Hernandez, Josue | 24 | 912 | 31084
PR | 142 | 06/25/21 | 635 | Hubbard, Robert W | 10 | 550 | 31093
PR | 142 | 07/02/21 | 35 | Gonzalez Hernandez, Josue | 16 | 608 | 31158
PR | 142 | 07/02/21 | 42 | Hubbard, Robert W | 9 | 495 | 31165
PR | 142 | 07/09/21 | 130 | Gonzalez Hernandez, Josue | 7 | 266 | 31233
PR | 142 | 07/09/21 | 137 | Hubbard, Robert W | 12 | 660 | 31240
PR | 142 | 07/09/21 | 165 | Sepulveda Gonzalez, Alfredo | 30 | 1350 | 31268
PR | 142 | 07/16/21 | 322 | Barnhart, Joseph N | 2 | 112 | 31283
PR | 142 | 07/16/21 | 348 | Gonzalez Hernandez, Josue | 40 | 1520 | 31309
PR | 142 | 07/16/21 | 383 | Sepulveda Gonzalez, Alfredo | 35.5 | 1597.5 | 31344
PR | 142 | 07/23/21 | 519 | Gonzalez Hernandez, Josue | 32 | 1216 | 31387
PR | 142 | 07/23/21 | 527 | Hubbard, Robert W | 3 | 165 | 31395
PR | 142 | 07/23/21 | 555 | Sepulveda Gonzalez, Alfredo | 10 | 450 | 31423
PR | 142 | 07/30/21 | 684 | Barnhart, Joseph N | 4 | 224 | 31440
PR | 142 | 07/30/21 | 711 | Gonzalez Hernandez, Josue | 37 | 1406 | 31467
PR | 142 | 08/06/21 | 79 | Hubbard, Robert W | 4 | 220 | 31557
PR | 142 | 08/20/21 | 587 | Barnhart, Joseph N | 2 | 112 | 31680
PR | 142 | 08/27/21 | 807 | Barnhart, Joseph N | 7 | 392 | 31759
PR | 142 | 09/17/21 | 338 | Barnhart, Joseph N | 2 | 174 | 32008
PR | 142 | 09/17/21 | 338 | Barnhart, Joseph N | 6 | 348 | 32008
PR | 142 | 09/24/21 | 492 | Barnhart, Joseph N | 2 | 174 | 32092
PR | 142 | 11/19/21 | 437 | Barnhart, Joseph N | 1 | 58 | 32823
PR | 142 | 11/19/21 | 480 | Holmes, Anthony R | 2 | 144 | 32866
PR | 142 | 11/19/21 | 480 | Holmes, Anthony R | 19 | 912 | 32866
PR | 142 | 11/19/21 | 517 | Velasquez Cruz, Denis M | 2 | 78 | 32903
PR | 142 | 12/23/21 | 741 | Barnhart, Joseph N | 4 | 232 | 33423
PR | 142 | 02/04/22 | 11 | Barnhart, Joseph N | 3 | 174 | 33990
PR | 142 | 02/04/22 | 55 | Holmes, Anthony R | 16 | 768 | 34034
PR | 142 | 02/11/22 | 217 | Barnhart, Joseph N | 21 | 1218 | 34085
PR | 142 | 02/11/22 | 262 | Holmes, Anthony R | 31 | 1488 | 34130
PR | 142 | 02/18/22 | 488 | Barnhart, Joseph N | 2 | 116 | 34181
PR | 142 | 02/25/22 | 709 | Barnhart, Joseph N | 7 | 406 | 34274
PR | 142 | 03/04/22 | 44 | Barnhart, Joseph N | 20 | 1160 | 34368
PR | 142 | 03/11/22 | 341 | Barnhart, Joseph N | 2 | 116 | 34463
PR | 142 | 03/18/22 | 626 | Barnhart, Joseph N | 6.5 | 377 | 34559
PR | 142 | 03/18/22 | 669 | Holmes, Anthony R | 16 | 768 | 34602
PR | 142 | 03/25/22 | 875 | Barnhart, Joseph N | 16 | 928 | 34654
PR | 142 | 03/25/22 | 916 | Holmes, Anthony R | 40 | 1920 | 34695
PR | 142 | 04/01/22 | 21 | Barnhart, Joseph N | 10 | 580 | 34748
PR | 142 | 04/01/22 | 63 | Holmes, Anthony R | 40 | 1920 | 34790
PR | 142 | 04/08/22 | 227 | Barnhart, Joseph N | 5 | 290 | 34841
PR | 142 | 04/08/22 | 227 | Barnhart, Joseph N | 4 | 232 | 34841
PR | 142 | 04/08/22 | 269 | Holmes, Anthony R | 40 | 1920 | 34883
PR | 142 | 04/15/22 | 475 | Barnhart, Joseph N | 13 | 754 | 34936
PR | 142 | 04/15/22 | 516 | Holmes, Anthony R | 40 | 1920 | 34977
PR | 142 | 04/22/22 | 803 | Barnhart, Joseph N | 18 | 1044 | 35027
PR | 142 | 04/22/22 | 844 | Holmes, Anthony R | 16 | 768 | 35068
PR | 142 | 04/29/22 | 1063 | Barnhart, Joseph N | 9 | 522 | 35119
PR | 142 | 04/29/22 | 1104 | Holmes, Anthony R | 24 | 1152 | 35160
PR | 142 | 05/06/22 | 90 | Barnhart, Joseph N | 6 | 348 | 35211
PR | 142 | 05/06/22 | 128 | Holmes, Anthony R | 27 | 1296 | 35249
PR | 142 | 05/13/22 | 363 | Holmes, Anthony R | 16 | 768 | 35337
PR | 142 | 05/20/22 | 598 | Barnhart, Joseph N | 2 | 120 | 35389
PR | 142 | 06/17/22 | 465 | Barnhart, Joseph N | 3 | 180 | 35745
PR | 142 | 06/24/22 | 771 | Barnhart, Joseph N | 2 | 120 | 35837
PR | 142 | 07/15/22 | 369 | Barnhart, Joseph N | 1 | 60 | 36092
PR | 142 | 07/15/22 | 408 | Holmes, Anthony R | 15 | 750 | 36131
PR | 142 | 08/12/22 | 288 | Barnhart, Joseph N | 2 | 120 | 36430
PR | 142 | 08/19/22 | 495 | Barnhart, Joseph N | 2 | 120 | 36507
PR | 142 | 08/19/22 | 539 | Lovo, German G | 8 | 288 | 36551
PR | 142 | 08/26/22 | 761 | Barnhart, Joseph N | 3 | 180 | 36586
PR | 142 | 08/26/22 | 790 | Gordillo, Emanuel D | 2 | 44 | 36615
PR | 142 | 08/26/22 | 796 | Holmes, Anthony R | 2 | 100 | 36621
PR | 142 | 09/30/22 | 815 | Barnhart, Joseph N | 1 | 60 | 36977
PR | 142 | 10/07/22 | 28 | Barnhart, Joseph N | 4 | 256 | 37056
PR | 142 | 10/14/22 | 283 | Barnhart, Joseph N | 1 | 64 | 37140
PR | 142 | 10/28/22 | 754 | Barnhart, Joseph N | 4 | 256 | 37311
PR | 142 | 11/04/22 | 75 | Sanders, Allen O | 8 | 496 | 37463
PR | 142 | 11/18/22 | 368 | Barnhart, Joseph N | 1 | 64 | 37570
PR | 142 | 11/18/22 | 435 | Sanders, Allen O | 7.5 | 465 | 37637
PR | 142 | 11/23/22 | 513 | Barnhart, Joseph N | 9 | 576 | 37661
PR | 142 | 12/02/22 | 9 | Barnhart, Joseph N | 2 | 128 | 37748
PR | 150 | 12/23/22 | 845 | Barnhart, Joseph N | 4.5 | 288 | 38120
PR | 150 | 12/23/22 | 916 | Sanders, Allen O | 2.5 | 155 | 38191
PR | 150 | 12/30/22 | 1015 | Barnhart, Joseph N | 3.5 | 224 | 38214
PR | 150 | 12/30/22 | 1052 | Holmes, Anthony R | 3 | 162 | 38251
AP | 210 | 05/13/19 | 320 | Rosen Supply Kirkland |  | 83.11 | 4266291-00
AP | 210 | 05/13/19 | 322 | Rosen Supply Kirkland |  | 39.53 | 4266291-01
AP | 210 | 06/03/19 | 39 | Rosen Supply Kirkland |  | -36.25 | 4268065-00
AP | 210 | 08/28/19 | 976 | Rosen Supply Kirkland |  | 4109.93 | 2175920-00
AP | 210 | 08/28/19 | 977 | Rosen Supply Kirkland |  | 322.42 | 1544684-00
AP | 210 | 08/28/19 | 987 | Rosen Supply Kirkland |  | 2214.05 | 2175920-01
AP | 210 | 08/28/19 | 988 | Rosen Supply Kirkland |  | 258.71 | 2176025-00
AP | 210 | 08/30/19 | 1076 | Rosen Supply Kirkland |  | 216.43 | 4271419-00
AP | 210 | 09/23/19 | 601 | Rosen Supply Kirkland |  | 2880 | 2176009-00
AP | 210 | 09/27/19 | 731 | Rosen Supply Kirkland |  | 58.37 | 2175920-02
AP | 210 | 09/27/19 | 732 | Rosen Supply Kirkland |  | 6307.53 | 21765184-00
AP | 210 | 09/27/19 | 733 | Rosen Supply Kirkland |  | 38.9 | 2176471-00
AP | 210 | 10/15/19 | 424 | Rosen Supply Kirkland |  | 367.7 | 1548348-00
AP | 210 | 10/16/19 | 445 | Rosen Supply Kirkland |  | 348 | 1548589-00
AP | 210 | 10/16/19 | 446 | Rosen Supply Kirkland |  | 604.03 | 2176752-00
AP | 210 | 10/16/19 | 447 | Rosen Supply Kirkland |  | 519.78 | 2176753-00
AP | 210 | 11/01/19 | 121 | Rosen Supply Kirkland |  | 94.94 | 1548951-00
AP | 210 | 11/01/19 | 122 | Rosen Supply Kirkland |  | 191.77 | 2176821-00
GL | 210 | 11/13/19 | 411 | Req 6546 |  | 133.2
AP | 210 | 11/20/19 | 604 | Rosen Supply Kirkland |  | 364.42 | 4273284-00
AP | 210 | 11/27/19 | 924 | Capital One Credit Card |  | 29.8 | 110419JB
AP | 210 | 11/30/19 | 976 | Ferguson Enterprises, Inc. #3007 |  | 110.54 | 7699437
AP | 210 | 12/09/19 | 218 | Rosen Supply Kirkland |  | 1317.39 | 1551694-00
AP | 210 | 12/10/19 | 219 | Rosen Supply Kirkland |  | 175 | 2177618-00
AP | 210 | 12/10/19 | 228 | Rosen Supply Kirkland |  | 1813.58 | 2176187-00
AP | 210 | 12/10/19 | 229 | Rosen Supply Kirkland |  | 352.57 | 1551803-00
AP | 210 | 12/10/19 | 230 | Rosen Supply Kirkland |  | 169.9 | 2176184-01
AP | 210 | 12/10/19 | 272 | Rosen Supply Kirkland |  | 169.9 | 1551961-00
AP | 210 | 12/10/19 | 273 | Rosen Supply Kirkland |  | 118.68 | 1552158-00
AP | 210 | 12/31/19 | 866 | Rosen Supply Kirkland |  | 623.05 | 4276125-00
AP | 210 | 01/03/20 | 97 | Rosen Supply Kirkland |  | 119.18 | 4276276-00
AP | 210 | 06/08/21 | 180 | Core & Main LP $HD Supply Waterworks |  | 1748.82 | 217892
AP | 210 | 06/16/21 | 396 | Core & Main LP $HD Supply Waterworks |  | 73.25 | P028124
AP | 210 | 12/30/22 | 1171 | Capital One Credit Card |  | 63.22 | 111622J
GL | 211 | 09/16/19 | 353 | Req 6317 |  | 197.44
GL | 211 | 11/01/19 | 88 | Req 6455 |  | 366.8
GL | 211 | 11/13/19 | 410 | Req 6547 |  | 16
GL | 211 | 12/09/19 | 178 | Req 6640 |  | 262.78
GL | 211 | 12/27/19 | 797 | Req 6713 |  | 543.92
AP | 211 | 12/31/19 | 875 | Rosen Supply Kirkland |  | 2061.95 | 2178071-00
AP | 211 | 12/31/19 | 876 | Rosen Supply Kirkland |  | 266.79 | 2178071-01
AP | 211 | 01/03/20 | 101 | Rosen Supply Kirkland |  | 162.7 | 4276546-00
AP | 211 | 01/03/20 | 102 | Rosen Supply Kirkland |  | 37.41 | 4276546-01
AP | 211 | 01/06/20 | 115 | Rosen Supply Kirkland |  | 191.01 | 4276752-00
AP | 211 | 01/10/20 | 454 | Capital One Credit Card |  | 102.13 | 010320JB
AP | 211 | 01/13/20 | 514 | Rosen Supply Kirkland |  | 98.34 | 4277307-00
GL | 211 | 02/18/20 | 391 | Req 6779 |  | 855.16
GL | 211 | 03/09/20 | 139 | Req 6846 |  | 1590.78
GL | 211 | 03/20/20 | 666 | Req 6923 |  | 389.5
AP | 211 | 03/25/20 | 519 | Capital One Credit Card |  | 29.69 | 030320JB1
AP | 211 | 03/25/20 | 536 | Rosen Supply Kirkland |  | 4781.02 | 2178934-00
GL | 211 | 05/05/20 | 96 | Req 6968 |  | 587.36
GL | 211 | 05/15/20 | 398 | Req 7015 |  | -893.82
AP | 211 | 06/15/20 | 322 | Rosen Supply Kirkland |  | -4226.95 | 2181349-00
GL | 211 | 01/27/21 | 376 | Req 7559 |  | 687.18
AP | 211 | 02/10/21 | 239 | Rosen Supply Kirkland |  | 4825.63 | 2185557-00
AP | 211 | 02/10/21 | 250 | Rosen Supply Kirkland |  | 829.48 | 2185557-01
AP | 211 | 02/16/21 | 367 | Rosen Supply Kirkland |  | 2830.14 | 2185686-00
GL | 211 | 02/16/21 | 381 | Req 7586 |  | 1388.51
AP | 211 | 02/22/21 | 517 | Rosen Supply Kirkland |  | 847.45 | 2185686-01
AP | 211 | 02/22/21 | 518 | Rosen Supply Kirkland |  | 161.28 | 2185686-03
AP | 211 | 02/22/21 | 519 | Rosen Supply Kirkland |  | 45.07 | 2185691-00
AP | 211 | 02/22/21 | 520 | Rosen Supply Kirkland |  | 84.16 | 2185691-01
GL | 211 | 02/28/21 | 667 | Req 7615 |  | 452.8
AP | 211 | 03/02/21 | 15 | Rosen Supply Kirkland |  | 5602.68 | 2186012-00
AP | 211 | 03/05/21 | 129 | Rosen Supply Kirkland |  | 44.61 | 2185686-02
AP | 211 | 03/05/21 | 131 | Rosen Supply Kirkland |  | 142.42 | 2186012-01
AP | 211 | 03/17/21 | 272 | Rosen Supply Kirkland |  | 225.49 | 2186012-02
AP | 211 | 03/17/21 | 273 | Rosen Supply Kirkland |  | 305.06 | 2186202-00
AP | 211 | 03/29/21 | 635 | Rosen Supply Kirkland |  | 701.23 | 2186448-00
AP | 211 | 03/29/21 | 636 | Rosen Supply Kirkland |  | 77.14 | 2186489-00
AP | 211 | 03/31/21 | 694 | Rosen Supply Kirkland |  | 3719.15 | 2186557-00
AP | 211 | 03/31/21 | 721 | Rosen Supply Kirkland |  | 17.78 | 4293736-00
AP | 211 | 05/11/21 | 188 | Rosen Supply Kirkland |  | 31.25 | 2186557-01
AP | 211 | 05/11/21 | 189 | Rosen Supply Kirkland |  | 1972.96 | 2186557-02
AP | 211 | 05/11/21 | 190 | Rosen Supply Kirkland |  | 15.63 | 2186557-03
AP | 211 | 05/11/21 | 191 | Rosen Supply Kirkland |  | 363.11 | 2187162-00
AP | 211 | 05/11/21 | 192 | Rosen Supply Kirkland |  | 311.18 | 2187162-01
AP | 211 | 05/24/21 | 540 | Rosen Supply Kirkland |  | 107.84 | 2186557-04
AP | 211 | 06/30/21 | 760 | Rosen Supply Kirkland |  | 1420.1 | 4297181-00
AP | 211 | 08/10/21 | 242 | Rosen Supply Kirkland |  | 660.8 | 2186557-05
GL | 211 | 08/20/21 | 687 | Req 7788 |  | 2279.25
GL | 211 | 10/05/21 | 218 | Req 7947 |  | 569.64
GL | 211 | 10/29/21 | 1104 | Req 7987 |  | 540.86
AP | 211 | 03/01/22 | 1023 | Rosen Supply Kirkland |  | 105.17 | 4307672-00
GL | 211 | 05/10/22 | 271 | Req 8239 |  | 422.81
GL | 211 | 05/26/22 | 974 | Req 8331 |  | 219
GL | 211 | 07/18/22 | 480 | Req 8498 |  | 135.15
GL | 211 | 09/06/22 | 101 | Req 8618 |  | 74.66
AP | 211 | 09/30/22 | 984 | Capital One Credit Card |  | 100.88 | 081122J
AP | 211 | 10/21/22 | 571 | Rosen Supply Kirkland |  | 168.02 | 2504.01
GL | 211 | 10/31/22 | 941 | Req 8805 |  | -152.47
GL | 211 | 11/16/22 | 302 | Req 8813 |  | -57.12
GL | 211 | 11/29/22 | 627 | Req 8857 |  | 87.79
AP | 211 | 12/06/22 | 228 | Rosen Supply Kirkland |  | -168.02 | 2817.01B
AP | 211 | 12/06/22 | 229 | Rosen Supply Kirkland |  | 117.99 | 2817.02B
AP | 211 | 12/22/22 | 820 | Rosen Supply Kirkland |  | -168.02 | 3382.01B
AP | 211 | 12/22/22 | 821 | Rosen Supply Kirkland |  | 117.98 | 3383.01B
AP | 211 | 12/30/22 | 1178 | Capital One Credit Card |  | 31.61 | 112822J
GL | 211 | 12/31/22 | 1191 | Req 8948 |  | -429.86
AP | 212 | 10/23/19 | 578 | Ferguson Enterprises, Inc. #3007 |  | 238.36 | 7600195
GL | 212 | 11/01/19 | 89 | Req 6454 |  | 678.82
AP | 212 | 11/11/19 | 341 | Ferguson Enterprises, Inc. #3007 |  | 238.36 | 7628671
GL | 212 | 11/13/19 | 408 | Req 6549 |  | 1999.55
AP | 212 | 12/19/19 | 683 | ACME Corp |  | 169.02 | S3462637.002
GL | 212 | 12/27/19 | 796 | Req 6712 |  | 2094.92
AP | 212 | 01/06/20 | 153 | Ferguson Enterprises, Inc. #3007 |  | 238.36 | 7786250
AP | 212 | 01/08/20 | 231 | Capital One Credit Card |  | 10.95 | 112119JB
GL | 212 | 02/18/20 | 386 | Req 6778 |  | 7970.5
AP | 212 | 02/25/20 | 608 | Rosen Supply Kirkland |  | 3391.54 | 2179061-00
AP | 212 | 02/26/20 | 673 | Rosen Supply Kirkland |  | 324.5 | 2179061-01
AP | 212 | 02/26/20 | 674 | Rosen Supply Kirkland |  | 385.76 | 4278839-00
GL | 212 | 03/09/20 | 142 | Req 6845 |  | 6801.82
AP | 212 | 03/25/20 | 517 | Capital One Credit Card |  | 43.58 | 021220JB
AP | 212 | 03/27/20 | 891 | Rosen Supply Kirkland |  | 365.4 | 2180239-00
GL | 212 | 05/15/20 | 399 | Req 7016 |  | -1253.81
AP | 212 | 02/22/21 | 522 | Rosen Supply Kirkland |  | 9.04 | 4292105-00
GL | 212 | 02/28/21 | 668 | Req 7616 |  | 49.56
GL | 220 | 09/16/19 | 352 | Req 6316 |  | 333.78
GL | 220 | 11/01/19 | 86 | Req 6457 |  | 176.4
AP | 220 | 11/06/19 | 165 | Ferguson Enterprises, Inc. #3007 |  | 451.85 | 7628432
AP | 220 | 11/20/19 | 605 | Rosen Supply Kirkland |  | 9.8 | 2177207-00
GL | 220 | 12/27/19 | 798 | Req 6714 |  | 538.41
GL | 220 | 02/18/20 | 387 | Req 6780 |  | 4148.04
GL | 220 | 03/09/20 | 140 | Req 6848 |  | 1048.28
GL | 220 | 03/20/20 | 665 | Req 6922 |  | 522.3
AP | 220 | 04/22/20 | 330 | Capital One Credit Card |  | 11.05 | 031220JB1
AP | 220 | 04/22/20 | 332 | Capital One Credit Card |  | 149.11 | 031620JB1
GL | 220 | 05/05/20 | 94 | Req 6970 |  | 77.94
GL | 220 | 05/15/20 | 397 | Req 7017 |  | -886.29
GL | 220 | 01/31/21 | 466 | Req 7561 |  | 81.5
GL | 220 | 02/18/21 | 487 | Req 7587 |  | 789.61
AP | 220 | 02/22/21 | 521 | Rosen Supply Kirkland |  | 719.4 | 2185812-00
GL | 220 | 02/28/21 | 666 | Req 7617 |  | 603.86
AP | 220 | 03/05/21 | 130 | Rosen Supply Kirkland |  | 213.62 | 2185812-02
AP | 220 | 03/24/21 | 488 | Rosen Supply Kirkland |  | 1237.8 | 2186128-00
AP | 220 | 03/24/21 | 489 | Rosen Supply Kirkland |  | 693.95 | 2186128-01
AP | 220 | 04/01/21 | 77 | Rosen Supply Kirkland |  | 229.84 | 4293866-00
AP | 220 | 04/01/21 | 88 | Rosen Supply Kirkland |  | -229.84 | 4293866-00A
AP | 220 | 04/01/21 | 89 | Rosen Supply Kirkland |  | 229.82 | 4293866-00B
AP | 220 | 05/11/21 | 178 | Rosen Supply Kirkland |  | 527.47 | 2187099-00
AP | 220 | 05/11/21 | 179 | Rosen Supply Kirkland |  | 2549.9 | 2187195-00
AP | 220 | 05/24/21 | 541 | Rosen Supply Kirkland |  | 3345.51 | 2187508-00
AP | 220 | 06/07/21 | 146 | Rosen Supply Kirkland |  | 16.03 | 4295717-00
AP | 220 | 06/07/21 | 159 | Rosen Supply Kirkland |  | 3929.58 | 2187730-00
AP | 220 | 06/14/21 | 292 | Rosen Supply Kirkland |  | 1401.5 | 2187831-00
AP | 220 | 06/14/21 | 293 | Rosen Supply Kirkland |  | 28.02 | 4296197-00
AP | 220 | 06/15/21 | 327 | Rosen Supply Kirkland |  | 2184.82 | 2187889-00
AP | 220 | 06/21/21 | 535 | Rosen Supply Kirkland |  | 2.64 | 2187889-01
AP | 220 | 06/23/21 | 576 | Rosen Supply Kirkland |  | 1557.85 | 2188038-00
AP | 220 | 06/23/21 | 578 | Rosen Supply Kirkland |  | 1772 | 2188153-00
AP | 220 | 06/29/21 | 752 | Capital One Credit Card |  | 67.74 | 060321JB4
AP | 220 | 06/30/21 | 758 | Rosen Supply Kirkland |  | 1222.75 | 4297174-00
AP | 220 | 07/17/21 | 469 | Rosen Supply Kirkland |  | 6046.18 | 2188549-00
AP | 220 | 07/23/21 | 575 | Rosen Supply Kirkland |  | 920.26 | 2188402-00
AP | 220 | 07/26/21 | 663 | Rosen Supply Kirkland |  | 519.66 | 4297933-00
AP | 220 | 07/28/21 | 804 | Rosen Supply Kirkland |  | 3181 | 2187429-00
AP | 220 | 07/28/21 | 805 | Rosen Supply Kirkland |  | 5905 | 2187429-01
AP | 220 | 07/31/21 | 815 | Rosen Supply Kirkland |  | 2447.9 | 2188699-00
AP | 220 | 07/31/21 | 816 | Rosen Supply Kirkland |  | 429.77 | 2188699-01
AP | 220 | 08/05/21 | 129 | Rosen Supply Kirkland |  | 977.32 | 4298462-00
AP | 220 | 08/08/21 | 150 | Consolidated Supply Co. |  | 1099.62 | S010398404.001
AP | 220 | 08/09/21 | 174 | Rosen Supply Kirkland |  | 125.58 | 4298462-01
AP | 220 | 08/10/21 | 243 | Rosen Supply Kirkland |  | 843 | 2187429-02
AP | 220 | 08/10/21 | 244 | Rosen Supply Kirkland |  | 840.85 | 2188549-01
AP | 220 | 08/10/21 | 245 | Rosen Supply Kirkland |  | 1048.18 | 2188904-00
AP | 220 | 08/10/21 | 246 | Rosen Supply Kirkland |  | 112.15 | 4298757-00
AP | 220 | 08/10/21 | 256 | Rosen Supply Kirkland |  | 909.74 | 2188983-00
AP | 220 | 08/10/21 | 257 | Rosen Supply Kirkland |  | 787.94 | 2188984-00
AP | 220 | 08/10/21 | 258 | Rosen Supply Kirkland |  | 1419 | 2189000-00
AP | 220 | 08/17/21 | 503 | Rosen Supply Kirkland |  | 376.09 | 2189164-00
AP | 220 | 08/18/21 | 566 | Rosen Supply Kirkland |  | 677.56 | 2189164-01
GL | 220 | 08/20/21 | 689 | Req 7786 |  | 8629.35
GL | 220 | 08/20/21 | 690 | Req 7785 |  | 9206.08
GL | 220 | 08/20/21 | 691 | Req 7784 |  | 5274.3
GL | 220 | 08/20/21 | 692 | Req 7783 |  | 3225.93
GL | 220 | 08/31/21 | 973 | Req 7847 |  | 2269.34
GL | 220 | 08/31/21 | 974 | Req 7846 |  | 4892.5
AP | 220 | 09/27/21 | 669 | Rosen Supply Kirkland |  | 1026.4 | 4300271-00
AP | 220 | 09/27/21 | 670 | Rosen Supply Kirkland |  | 48 | 4300603-00
AP | 220 | 09/27/21 | 681 | Rosen Supply Kirkland |  | 794.5 | 4300660-00
AP | 220 | 09/27/21 | 687 | Rosen Supply Kirkland |  | 1597.78 | 2189536-00
AP | 220 | 09/27/21 | 708 | Rosen Supply Kirkland |  | 1236.48 | 4300869-00
AP | 220 | 10/01/21 | 124 | Rosen Supply Kirkland |  | 645 | 2189000-01
AP | 220 | 10/01/21 | 125 | Rosen Supply Kirkland |  | 2744.42 | 2189857-00
AP | 220 | 10/01/21 | 447 | Rosen Supply Kirkland |  | 4285.36 | 2189932-00
AP | 220 | 10/04/21 | 194 | Capital One Credit Card |  | 54.3 | 081921JB2
GL | 220 | 10/05/21 | 220 | Req 7945 |  | 6418.76
GL | 220 | 10/12/21 | 457 | Req 7953 |  | -178.94
AP | 220 | 10/18/21 | 695 | Rosen Supply Kirkland |  | 841.2 | 4301573-00
AP | 220 | 10/20/21 | 715 | Rosen Supply Kirkland |  | 5230.58 | 2190041-00
AP | 220 | 10/20/21 | 716 | Rosen Supply Kirkland |  | 447.6 | 4298462-02
AP | 220 | 10/22/21 | 869 | Rosen Supply Kirkland |  | 834.5 | 4301717-00
AP | 220 | 10/22/21 | 897 | Rosen Supply Kirkland |  | 140.58 | 4301941-00
GL | 220 | 10/25/21 | 901 | Req 7985 |  | 2568.11
AP | 220 | 10/25/21 | 912 | Rosen Supply Kirkland |  | 9997.8 | 2190226-00
AP | 220 | 10/26/21 | 944 | Rosen Supply Kirkland |  | 1138.08 | 4302129-00
AP | 220 | 10/27/21 | 997 | Rosen Supply Kirkland |  | 313.95 | 4302221-00
AP | 220 | 10/28/21 | 1147 | Rosen Supply Kirkland |  | 395.52 | 1596085-00
AP | 220 | 10/29/21 | 1115 | Rosen Supply Kirkland |  | 215.1 | 2190401-00
AP | 220 | 11/02/21 | 7 | Rosen Supply Kirkland |  | 237.08 | 1596055-00
AP | 220 | 11/02/21 | 9 | Rosen Supply Kirkland |  | 396.06 | 4302456-00
AP | 220 | 11/05/21 | 160 | Capital One Credit Card |  | 56.19 | 092221JB
AP | 220 | 11/22/21 | 720 | Rosen Supply Kirkland |  | -27.99 | 4302986-00
AP | 220 | 12/02/21 | 3 | Rosen Supply Kirkland |  | 3006.12 | 4303081-00
AP | 220 | 12/08/21 | 178 | Rosen Supply Kirkland |  | 1387.44 | 4303313-00
AP | 220 | 12/10/21 | 343 | Rosen Supply Kirkland |  | 140.2 | 4303662-00
AP | 220 | 12/21/21 | 698 | Rosen Supply Kirkland |  | 330.3 | 4303903-00
AP | 220 | 12/27/21 | 882 | Rosen Supply Kirkland |  | 269380 | 2191091-00
AP | 220 | 01/01/22 | 216 | Rosen Supply Kirkland |  | -269380 | 2191091-00A
AP | 220 | 01/01/22 | 217 | Rosen Supply Kirkland |  | 269.8 | 2191091-00B
AP | 220 | 01/11/22 | 166 | Rosen Supply Kirkland |  | 150.58 | 4304509-00
AP | 220 | 01/31/22 | 749 | Rosen Supply Kirkland |  | 329.75 | 4304933-00
AP | 220 | 02/09/22 | 185 | Rosen Supply Kirkland |  | 205.5 | 4305199-00
AP | 220 | 02/09/22 | 186 | Rosen Supply Kirkland |  | 137.3 | 4305222-00
AP | 220 | 02/11/22 | 333 | Rosen Supply Kirkland |  | 47.1 | 4305540-00
AP | 220 | 02/24/22 | 815 | Rosen Supply Kirkland |  | 95.52 | 4305824-00
AP | 220 | 03/07/22 | 196 | Rosen Supply Kirkland |  | 73 | 4306628-00
AP | 220 | 03/16/22 | 584 | Rosen Supply Kirkland |  | 503.47 | 2192391-00
AP | 220 | 03/22/22 | 856 | Rosen Supply Kirkland |  | 413.51 | 2192391-01
AP | 220 | 03/23/22 | 866 | Rosen Supply Kirkland |  | 47.03 | 4307637-00
AP | 220 | 04/05/22 | 151 | Rosen Supply Kirkland |  | 12.96 | 4307480-01
AP | 220 | 04/07/22 | 372 | Rosen Supply Kirkland |  | 69.3 | 4308082-00
AP | 220 | 04/07/22 | 375 | Rosen Supply Kirkland |  | 440.96 | 4307480-00
GL | 220 | 05/06/22 | 177 | Req 5227 |  | 14447
GL | 220 | 05/09/22 | 206 | Req 8229 |  | 4017.77
GL | 220 | 05/09/22 | 207 | Req 8228 |  | 6462.34
GL | 220 | 05/10/22 | 269 | Req 8241 |  | 49.65
GL | 220 | 05/26/22 | 976 | Req 8329 |  | 175
GL | 220 | 06/08/22 | 177 | Req 8389 |  | -3019.5
GL | 220 | 06/15/22 | 405 | Req 8412 |  | 31.36
AP | 220 | 07/11/22 | 292 | Rosen Supply Kirkland |  | 8.43 | 3666.01
AP | 220 | 08/17/22 | 460 | Rosen Supply Kirkland |  | 237.64 | 3373.01
GL | 220 | 09/06/22 | 104 | Req 8615 |  | 120.88
AP | 220 | 09/07/22 | 188 | Capital One Credit Card |  | 57.46 | 071222J2
AP | 220 | 09/07/22 | 190 | Capital One Credit Card |  | 32.44 | 071922JB
AP | 220 | 09/30/22 | 986 | Capital One Credit Card |  | 39.3 | 081522J
AP | 220 | 09/30/22 | 987 | Capital One Credit Card |  | 12.67 | 081622J
GL | 220 | 10/10/22 | 159 | Req 8714 |  | 40.84
AP | 220 | 10/31/22 | 918 | Rosen Supply Kirkland |  | 405.12 | 5678.01
GL | 220 | 11/08/22 | 138 | Req 8810 |  | -179.89
GL | 220 | 11/08/22 | 139 | Req 8809 |  | -1305.86
GL | 220 | 11/08/22 | 140 | Req 8808 |  | -816.87
GL | 220 | 11/29/22 | 630 | Req 8854 |  | 133.71
AP | 220 | 11/30/22 | 687 | Capital One Credit Card |  | 39.16 | 101422J
AP | 220 | 11/30/22 | 688 | Capital One Credit Card |  | 30.46 | 102122J
AP | 220 | 12/20/22 | 765 | Rosen Supply Kirkland |  | 123.72 | 3299.01B
GL | 220 | 12/30/22 | 1110 | Req 8945 |  | -679.83
GL | 220 | 12/31/22 | 1190 | Req 8949 |  | -106.91
AP | 230 | 08/26/19 | 911 | Granite Precast |  | 5141 | 83103
AP | 230 | 08/26/19 | 916 | Old Castle Infrastructure, Inc. |  | 5843 | 11000750
GL | 230 | 09/16/19 | 354 | Req 6318 |  | 444.29
AP | 230 | 10/21/19 | 545 | Old Castle Infrastructure, Inc. |  | 2659 | 11000859
AP | 230 | 10/21/19 | 546 | Old Castle Infrastructure, Inc. |  | 1032 | 11000863
GL | 230 | 11/01/19 | 87 | Req 6456 |  | 860.23
AP | 230 | 11/12/19 | 375 | Keller Supply Company |  | 21.44 | S013566289.001
GL | 230 | 11/13/19 | 409 | Req 6548 |  | 236.9
AP | 230 | 12/10/19 | 274 | Rosen Supply Kirkland |  | 103 | 4275201-00
AP | 230 | 12/10/19 | 281 | Rosen Supply Kirkland |  | 413.88 | 4275551-00
GL | 230 | 12/27/19 | 799 | Req 6715 |  | 473.8
AP | 230 | 12/27/19 | 827 | Keller Supply Company |  | 423.72 | S013640820.001
AP | 230 | 12/27/19 | 828 | Keller Supply Company |  | 1408.92 | S013473330.001
AP | 230 | 02/10/20 | 183 | Keller Supply Company |  | 35.64 | S013857274.001
AP | 230 | 02/14/20 | 347 | Rosen Supply Kirkland |  | 365.4 | 2178764-00
GL | 230 | 02/18/20 | 388 | Req 6781 |  | 1044.98
GL | 230 | 03/09/20 | 141 | Req 6847 |  | 1180.05
AP | 230 | 03/18/20 | 560 | Rosen Supply Kirkland |  | 365.4 | 2179856-00
GL | 230 | 05/05/20 | 93 | Req 6971 |  | 24
AP | 230 | 07/17/20 | 356 | Consolidated Supply Co. |  | 408.74 | S009852824.001
GL | 230 | 01/27/21 | 375 | Req 7560 |  | 62.96
GL | 230 | 02/22/21 | 499 | Req 7608 |  | 1778.1
AP | 230 | 04/19/21 | 347 | California Hydronics Corp |  | 8655 | SIN083067
AP | 230 | 04/19/21 | 348 | California Hydronics Corp |  | 41753 | SIN083066
AP | 230 | 05/12/21 | 226 | California Hydronics Corp |  | 60515 | SIN085244
AP | 230 | 07/24/21 | 607 | California Hydronics Corp |  | 683.23 | SIN090175
AP | 230 | 07/26/21 | 647 | Keller Supply Company |  | 1692.62 | S015538481.001
AP | 230 | 07/26/21 | 648 | Keller Supply Company |  | 8039.96 | S015538481.003
AP | 230 | 07/26/21 | 649 | Keller Supply Company |  | 8671.67 | S015445072.001
AP | 230 | 07/26/21 | 650 | Keller Supply Company |  | 13965.25 | S015445072.003
AP | 230 | 08/08/21 | 159 | Keller Supply Company |  | 52.75 | S015630452.001
AP | 230 | 08/08/21 | 160 | Keller Supply Company |  | 107.62 | S015630452.002
AP | 230 | 08/11/21 | 274 | Keller Supply Company |  | 12041.21 | S01540175.001
AP | 230 | 08/11/21 | 275 | Keller Supply Company |  | 13656.79 | S015459945.001
GL | 230 | 08/20/21 | 688 | Req 7787 |  | 11938.56
AP | 230 | 08/23/21 | 747 | Rosen Supply Kirkland |  | 3475.66 | 4295902-00
AP | 230 | 08/23/21 | 749 | Keller Supply Company |  | 2204.28 | S015709194.001
AP | 230 | 08/23/21 | 751 | Keller Supply Company |  | 12041.21 | S015460011.001
GL | 230 | 08/31/21 | 972 | Req 7848 |  | 4801.74
AP | 230 | 09/10/21 | 290 | Consolidated Supply Co. |  | 731.82 | S010423917.001
AP | 230 | 09/13/21 | 301 | Keller Supply Company |  | 11048.29 | S015460094.001
AP | 230 | 09/17/21 | 618 | Keller Supply Company |  | 1985.83 | S015460094.003
AP | 230 | 09/17/21 | 619 | Keller Supply Company |  | 1985.83 | S015460203.001
AP | 230 | 09/17/21 | 620 | Keller Supply Company |  | 11048.29 | S015460203.003
AP | 230 | 09/17/21 | 621 | Keller Supply Company |  | 11048.29 | S015462700.001
GL | 230 | 10/04/21 | 203 | Req 7944 |  | 1993
AP | 230 | 10/07/21 | 276 | Keller Supply Company |  | 11670.96 | S015459488.001
AP | 230 | 10/07/21 | 277 | Keller Supply Company |  | 992.92 | S015459488.003
AP | 230 | 10/07/21 | 278 | Keller Supply Company |  | 992.92 | S015459799.001
AP | 230 | 10/07/21 | 279 | Keller Supply Company |  | 992.92 | S015462700.003
AP | 230 | 10/07/21 | 287 | Keller Supply Company |  | 11048.29 | S015459799.003
AP | 230 | 10/13/21 | 547 | Keller Supply Company |  | 496.46 | S015459799.005
AP | 230 | 10/13/21 | 548 | Keller Supply Company |  | 12913.57 | S015845788.001
AP | 230 | 10/13/21 | 549 | Keller Supply Company |  | 13340.06 | S015845803.001
AP | 230 | 10/18/21 | 687 | Keller Supply Company |  | 1088.45 | S014845788.003
AP | 230 | 10/18/21 | 688 | Keller Supply Company |  | 2422.99 | S015845803.003
GL | 230 | 10/25/21 | 900 | Req 7986 |  | 2498.51
AP | 230 | 10/26/21 | 943 | Rosen Supply Kirkland |  | 3475.66 | 4295284-00
AP | 230 | 11/16/21 | 412 | Rosen Supply Kirkland |  | 75.12 | 4302711-00
AP | 230 | 12/31/21 | 1088 | Keller Supply Company |  | 5150.86 | S020064180.001
AP | 230 | 12/31/21 | 1089 | Keller Supply Company |  | 5258.47 | S020064241.001
AP | 230 | 12/31/21 | 1090 | Keller Supply Company |  | 5203.61 | S020064290.001
AP | 230 | 12/31/21 | 1091 | Keller Supply Company |  | 5258.47 | S020064313.001
AP | 230 | 12/31/21 | 1092 | Keller Supply Company |  | 5258.47 | S020064332.001
AP | 230 | 01/12/22 | 178 | Keller Supply Company |  | 8987.87 | S020062241.001
AP | 230 | 01/26/22 | 586 | Keller Supply Company |  | 2124.64 | S020097033.001
AP | 230 | 02/16/22 | 468 | Keller Supply Company |  | 8987.87 | S020061242.001
AP | 230 | 02/23/22 | 648 | Ferguson Enterprises, Inc. #3007 |  | 1895 | 0164136
AP | 230 | 02/23/22 | 659 | Keller Supply Company |  | 9185.56 | S020062222.001
AP | 230 | 02/23/22 | 660 | Keller Supply Company |  | 2732.43 | S020200953.001
AP | 230 | 03/02/22 | 5 | Rosen Supply Kirkland |  | 33.78 | 4306325-00
AP | 230 | 03/09/22 | 276 | Keller Supply Company |  | 8987.87 | S020062205.001
AP | 230 | 03/09/22 | 292 | Keller Supply Company |  | 8987.87 | S020062182.001
AP | 230 | 03/09/22 | 293 | Keller Supply Company |  | 4797.51 | S020173195.001
AP | 230 | 03/09/22 | 294 | Keller Supply Company |  | 8740.15 | S020062149.001
AP | 230 | 03/09/22 | 295 | Keller Supply Company |  | 3613.87 | S020255834.001
AP | 230 | 03/09/22 | 296 | Keller Supply Company |  | 3613.87 | S020255849.001
AP | 230 | 03/14/22 | 480 | Keller Supply Company |  | 1900.54 | S020039401.001
AP | 230 | 03/14/22 | 498 | Keller Supply Company |  | 4662.48 | S020062031.001
AP | 230 | 03/14/22 | 499 | Keller Supply Company |  | 8324.04 | S020062100.001
AP | 230 | 03/15/22 | 512 | Keller Supply Company |  | 1417.64 | S020062031.002
AP | 230 | 03/15/22 | 513 | Keller Supply Company |  | 1758.9 | S020062043.001
AP | 230 | 03/15/22 | 514 | Keller Supply Company |  | 1758.9 | S020062059.001
AP | 230 | 03/15/22 | 515 | Keller Supply Company |  | 1730.24 | S020062078.002
AP | 230 | 03/15/22 | 516 | Keller Supply Company |  | 1730.24 | S020062086.001
AP | 230 | 03/15/22 | 518 | Keller Supply Company |  | 3613.87 | S020266358.001
AP | 230 | 03/15/22 | 519 | Keller Supply Company |  | 3613.87 | S020266373.001
AP | 230 | 03/15/22 | 520 | Keller Supply Company |  | 3613.87 | S020266385.001
AP | 230 | 03/15/22 | 521 | Keller Supply Company |  | 4217.96 | S020266390.001
AP | 230 | 03/16/22 | 585 | Rosen Supply Kirkland |  | 85.47 | 4307247-00
AP | 230 | 03/30/22 | 1069 | Keller Supply Company |  | 266.77 | S020337448.001
AP | 230 | 04/01/22 | 8 | Keller Supply Company |  | -419.64 | S020369973.001
AP | 230 | 04/07/22 | 370 | Rosen Supply Kirkland |  | 21.72 | 1604845-00
AP | 230 | 04/12/22 | 427 | Keller Supply Company |  | 5855.25 | S020062078.003
AP | 230 | 04/12/22 | 428 | Keller Supply Company |  | 5855.25 | S020062086.002
AP | 230 | 04/15/22 | 604 | Capital One Credit Card |  | 27.32 | 033122JB1
AP | 230 | 04/15/22 | 609 | Capital One Credit Card |  | 40.23 | 040722JB2
AP | 230 | 04/19/22 | 715 | Rosen Supply Kirkland |  | 120.45 | 7182749-00
AP | 230 | 05/03/22 | 21 | Keller Supply Company |  | 187.99 | S020389026.001
GL | 230 | 05/09/22 | 203 | Req 8232 |  | 11524.82
GL | 230 | 05/09/22 | 204 | Req 8231 |  | 10095.57
GL | 230 | 05/09/22 | 205 | Req 8230 |  | 8877.65
AP | 230 | 05/09/22 | 248 | Keller Supply Company |  | 578.36 | S020347757.001
GL | 230 | 05/10/22 | 274 | Req 8236 |  | 556.6
AP | 230 | 05/10/22 | 294 | Keller Supply Company |  | 6024.28 | S020062059.002
AP | 230 | 05/18/22 | 521 | Capital One Credit Card |  | 35.22 | 050922A
AP | 230 | 05/25/22 | 852 | Keller Supply Company |  | 6024.28 | S020062043.002
AP | 230 | 05/25/22 | 858 | Rosen Supply Kirkland |  | 133.4 | 1303.01
GL | 230 | 05/26/22 | 977 | Req 8328 |  | 3287.63
GL | 230 | 06/08/22 | 178 | Req 8388 |  | -1006.49
AP | 230 | 06/08/22 | 204 | Keller Supply Company |  | 635.1 | S020454086.001
AP | 230 | 06/08/22 | 205 | Keller Supply Company |  | 419.45 | S020584372.001
AP | 230 | 06/14/22 | 385 | Keller Supply Company |  | -104.77 | S020590125.001
AP | 230 | 06/21/22 | 669 | Bank of America CC |  | 1155.8 | 052822R
AP | 230 | 06/22/22 | 738 | Keller Supply Company |  | 4812.92 | S020062031.003
AP | 230 | 06/22/22 | 739 | Keller Supply Company |  | -564.54 | S020637185.001
AP | 230 | 06/22/22 | 747 | Ferguson Enterprises, Inc. #3007 |  | 79.72 | 0540958
AP | 230 | 06/27/22 | 919 | Keller Supply Company |  | 256.36 | S020672817.001
GL | 230 | 07/18/22 | 481 | Req 8497 |  | 895.91
AP | 230 | 07/19/22 | 553 | Capital One Credit Card |  | 51.61 | 062022JB
AP | 230 | 08/05/22 | 169 | Keller Supply Company |  | -367.57 | S020769723.001
GL | 230 | 09/06/22 | 105 | Req 8611 |  | 634.01
AP | 230 | 09/13/22 | 391 | Keller Supply Company |  | 1785.26 | S020883583.001
AP | 230 | 09/30/22 | 982 | Capital One Credit Card |  | 8.37 | 090822A
GL | 230 | 10/10/22 | 161 | Req 8712 |  | 288.14
AP | 230 | 11/01/22 | 174 | Keller Supply Company |  | 1218.91 | S021078926.001
GL | 230 | 11/01/22 | 322 | AP Coating LLC |  | 260
AP | 230 | 11/08/22 | 164 | Keller Supply Company |  | 3309.55 | S021026556.001
GL | 230 | 11/16/22 | 299 | Req 8816 |  | -512.07
GL | 230 | 11/29/22 | 629 | Req 8855 |  | 1588.45
GL | 230 | 12/30/22 | 1109 | Req 8946 |  | -1841.67
AP | 240 | 04/19/21 | 362 | Rosen Supply Kirkland |  | 3040.02 | 1583232-00
AP | 240 | 06/21/21 | 540 | Rosen Supply Kirkland |  | 831.01 | 2187973-00
AP | 240 | 06/30/21 | 759 | Rosen Supply Kirkland |  | 37.72 | 4297176-00
GL | 240 | 08/17/21 | 468 | Req 7766 |  | 597.45
AP | 240 | 08/17/21 | 504 | Rosen Supply Kirkland |  | 138.6 | 2189165-00
AP | 240 | 08/17/21 | 511 | Rosen Supply Kirkland |  | 138.6 | 2189165-01
GL | 240 | 08/23/21 | 725 | Req 7791 |  | 459.84
AP | 240 | 08/23/21 | 773 | Rosen Supply Kirkland |  | 318.04 | 4299923-00
GL | 240 | 08/31/21 | 971 | Req 7849 |  | 35.49
AP | 240 | 09/27/21 | 694 | Rosen Supply Kirkland |  | 875.77 | 4300711-00
AP | 240 | 09/27/21 | 709 | Rosen Supply Kirkland |  | 436.01 | 4300885-00
GL | 240 | 10/05/21 | 219 | Req 7946 |  | 126.8
AP | 240 | 11/02/21 | 8 | Rosen Supply Kirkland |  | 963.23 | 1595731-00
AP | 240 | 11/22/21 | 701 | Rosen Supply Kirkland |  | 151.17 | 4302819-00
AP | 240 | 12/08/21 | 171 | Rosen Supply Kirkland |  | 524.93 | 4303284-00
AP | 240 | 12/30/21 | 1038 | Rosen Supply Kirkland |  | 135.58 | 4303284-01
AP | 240 | 03/02/22 | 4 | Rosen Supply Kirkland |  | 88.27 | 1602195-00
AP | 240 | 04/05/22 | 182 | Rosen Supply Kirkland |  | 99.18 | 4307938-00
GL | 240 | 05/09/22 | 202 | Req 8234 |  | 583.29
GL | 240 | 05/26/22 | 972 | Req 8333 |  | 11.39
AP | 240 | 06/15/22 | 387 | Ferguson Enterprises, Inc. #3007 |  | 506.27 | 0505924
GL | 240 | 06/15/22 | 404 | Req 8413 |  | -122.57
AP | 240 | 08/16/22 | 437 | Ferguson Enterprises, Inc. #3007 |  | 283.07 | 0709869
AP | 240 | 08/17/22 | 466 | Rosen Supply Kirkland |  | 1824.03 | 3378.01
AP | 240 | 08/19/22 | 603 | Rosen Supply Kirkland |  | 101.48 | 3656.01
AP | 240 | 08/23/22 | 653 | Rosen Supply Kirkland |  | 57.1 | 3705.01
AP | 240 | 08/23/22 | 664 | Rosen Supply Kirkland |  | 60.61 | 6327.01
AP | 240 | 08/24/22 | 687 | Rosen Supply Kirkland |  | 161.65 | 3846.01
AP | 240 | 08/24/22 | 699 | Rosen Supply Kirkland |  | 236.23 | 6591.01
GL | 240 | 09/06/22 | 100 | Req 8619 |  | 229.52
AP | 240 | 09/07/22 | 160 | Rosen Supply Kirkland |  | 248.14 | 3378.03
GL | 240 | 09/28/22 | 761 | Req 8669 |  | -24.81
GL | 240 | 10/10/22 | 162 | Req 8711 |  | 26.75
GL | 240 | 10/10/22 | 163 | Req 8710 |  | 765.23
AP | 240 | 10/14/22 | 377 | Rosen Supply Kirkland |  | 83.98 | 8597.01
AP | 240 | 10/17/22 | 402 | Rosen Supply Kirkland |  | 24.81 | 3705.03
AP | 240 | 10/26/22 | 690 | Capital One Credit Card |  | 7.48 | 100422J
GL | 240 | 11/10/22 | 181 | Req 8812 |  | -595.15
GL | 240 | 11/16/22 | 298 | Req 8817 |  | -309.9
AP | 240 | 12/29/22 | 1133 | Bank of America CC |  | 107.25 | 120322J
AP | 241 | 02/10/20 | 143 | Consolidated Supply Co. |  | 542.92 | S009625862.001
AP | 241 | 04/22/20 | 331 | Capital One Credit Card |  | 71.94 | 031220JB2
GL | 241 | 02/16/21 | 382 | Req 7585 |  | 1402.91
GL | 241 | 02/28/21 | 665 | Req 7618 |  | 1381.48
AP | 241 | 03/16/21 | 255 | Consolidated Supply Co. |  | 25887.39 | S010152673.001
AP | 241 | 03/30/21 | 668 | Ferguson Enterprises, Inc. #3007 |  | 5864.21 | 9129144
AP | 241 | 04/14/21 | 229 | Ferguson Enterprises, Inc. #3007 |  | 148.61 | 9129144-1
AP | 241 | 04/14/21 | 237 | Rosen Supply Kirkland |  | 66.8 | 7168778-00
AP | 241 | 04/16/21 | 332 | Consolidated Supply Co. |  | 778.33 | S010228964.001
AP | 241 | 04/16/21 | 333 | Consolidated Supply Co. |  | 1087.32 | S010230255.001
AP | 241 | 04/16/21 | 334 | Consolidated Supply Co. |  | 137.76 | S010230255.003
AP | 241 | 04/16/21 | 335 | Consolidated Supply Co. |  | 275.52 | S010230255.002
AP | 241 | 04/16/21 | 336 | Consolidated Supply Co. |  | 122.88 | S010234805.002
AP | 241 | 04/28/21 | 564 | Consolidated Supply Co. |  | 141.24 | S010247698.002
AP | 241 | 05/12/21 | 236 | Consolidated Supply Co. |  | 6687.14 | S01023405.001
AP | 241 | 05/26/21 | 621 | Consolidated Supply Co. |  | 1561.36 | S010292177.001
AP | 241 | 06/23/21 | 577 | Rosen Supply Kirkland |  | 1872 | 2188039-00
AP | 241 | 07/17/21 | 437 | Consolidated Supply Co. |  | 863.63 | S010360145.001
AP | 241 | 07/17/21 | 438 | Consolidated Supply Co. |  | 8314.92 | S010362257.001
AP | 241 | 07/26/21 | 638 | Consolidated Supply Co. |  | 4304.4 | S010362257.002
AP | 241 | 07/26/21 | 645 | Ferguson Enterprises, Inc. #3007 |  | 2717.06 | 9469148
AP | 241 | 08/08/21 | 151 | Consolidated Supply Co. |  | 377.2 | S010362257.003
AP | 241 | 08/09/21 | 185 | Consolidated Supply Co. |  | 1267.27 | S010385612.001
AP | 241 | 08/09/21 | 186 | Consolidated Supply Co. |  | 991.19 | S010385612.002
GL | 241 | 08/17/21 | 469 | Req 7765 |  | 877.6
AP | 241 | 08/19/21 | 668 | Consolidated Supply Co. |  | 718.32 | S010385612.003
GL | 241 | 08/23/21 | 722 | Req 7794 |  | 7960.43
GL | 241 | 08/23/21 | 723 | Req 7793 |  | 2269.27
GL | 241 | 08/23/21 | 724 | Req 7792 |  | 3510.22
GL | 241 | 08/31/21 | 967 | Req 7853 |  | 1222.99
GL | 241 | 08/31/21 | 968 | Req 7852 |  | 3398.43
GL | 241 | 08/31/21 | 969 | Req 7851 |  | 5473.06
AP | 241 | 09/14/21 | 315 | Rosen Supply Kirkland |  | 2968.98 | 4300056-00
AP | 241 | 09/27/21 | 655 | Rosen Supply Kirkland |  | 3649.2 | 4300461-00
AP | 241 | 09/27/21 | 668 | Rosen Supply Kirkland |  | 1014.66 | 2189666-00
GL | 241 | 10/05/21 | 216 | Req 7949 |  | 343.92
GL | 241 | 10/05/21 | 217 | Req 7948 |  | 1882.77
AP | 241 | 10/06/21 | 254 | Consolidated Supply Co. |  | 3571.19 | S010488540.001
AP | 241 | 10/06/21 | 255 | Consolidated Supply Co. |  | 454.28 | S010488540.002
AP | 241 | 10/06/21 | 256 | Consolidated Supply Co. |  | 543.58 | S010496932.001
AP | 241 | 10/20/21 | 717 | Rosen Supply Kirkland |  | 183.75 | 4301615-00
AP | 241 | 10/27/21 | 970 | Consolidated Supply Co. |  | 3880.08 | S010520967.001
GL | 241 | 10/29/21 | 1105 | Req 7988 |  | 997.15
AP | 241 | 11/15/21 | 369 | Consolidated Supply Co. |  | 2346.99 | S010520967.002
AP | 241 | 12/11/21 | 298 | Rosen Supply Kirkland |  | 311.4 | 4303420-00
AP | 241 | 12/14/21 | 366 | Rosen Supply Kirkland |  | 449.28 | 1597826-00
AP | 241 | 12/27/21 | 898 | Rosen Supply Kirkland |  | 21.74 | 7178526-00
AP | 241 | 12/30/21 | 1059 | Consolidated Supply Co. |  | 482.47 | S010621942.001
AP | 241 | 01/11/22 | 165 | Rosen Supply Kirkland |  | 16746.06 | 2191070-00
AP | 241 | 01/13/22 | 214 | Rosen Supply Kirkland |  | 93.3 | 4304753-00
AP | 241 | 01/13/22 | 221 | Rosen Supply Kirkland |  | 258.72 | 4301615-02
AP | 241 | 04/07/22 | 367 | Ferguson Enterprises, Inc. #3007 |  | 185.52 | 0302046
GL | 241 | 04/27/22 | 993 | Req 8147 |  | -463.71
GL | 241 | 05/09/22 | 200 | Req 8235 |  | 1689.5
GL | 241 | 05/10/22 | 270 | Req 8240 |  | 1722.67
GL | 241 | 05/26/22 | 973 | Req 8332 |  | 16.74
GL | 241 | 06/08/22 | 175 | Req 8391 |  | -1409.44
GL | 241 | 07/19/22 | 503 | Req 8500 |  | 365.63
AP | 241 | 08/17/22 | 467 | Rosen Supply Kirkland |  | 713.07 | 3382.01
GL | 241 | 09/06/22 | 102 | Req 8617 |  | 346.5
GL | 241 | 10/10/22 | 160 | Req 8713 |  | 531.23
GL | 241 | 11/10/22 | 182 | Req 8811 |  | -893.52
GL | 241 | 11/16/22 | 300 | Req 8815 |  | -500.24
GL | 241 | 11/29/22 | 628 | Req 8856 |  | 188.74
GL | 241 | 12/30/22 | 1108 | Req 8947 |  | -384.41
AP | 242 | 06/07/21 | 158 | Rosen Supply Kirkland |  | 451.08 | 1586169-00
AP | 242 | 06/21/21 | 531 | Ferguson Enterprises, Inc. #3007 |  | 19888.24 | 9367143
AP | 242 | 06/21/21 | 532 | Ferguson Enterprises, Inc. #3007 |  | 1768.09 | 9367143-1
AP | 242 | 06/21/21 | 533 | Ferguson Enterprises, Inc. #3007 |  | 57.15 | 9367143-2
GL | 242 | 06/25/21 | 685 | Req 7725 |  | 651.03
AP | 242 | 06/30/21 | 805 | Ferguson Enterprises, Inc. #3007 |  | 1020.18 | 9430277
AP | 242 | 07/26/21 | 637 | Consolidated Supply Co. |  | 107.97 | S010356101.001
AP | 242 | 07/26/21 | 646 | Ferguson Enterprises, Inc. #3007 |  | 487.71 | 9484382
AP | 242 | 08/08/21 | 157 | Ferguson Enterprises, Inc. #3007 |  | 2296.79 | 9526040
GL | 242 | 08/20/21 | 686 | Req 7789 |  | 1163.3
GL | 242 | 08/23/21 | 726 | Req 7790 |  | 1981.85
GL | 242 | 08/31/21 | 966 | Req 7854 |  | 59.94
AP | 242 | 09/17/21 | 610 | Ferguson Enterprises, Inc. #3007 |  | 1613.33 | 9675787
AP | 242 | 10/01/21 | 442 | Consolidated Supply Co. |  | 84.93 | S010497221.001
AP | 242 | 10/05/21 | 237 | Consolidated Supply Co. |  | 120.11 | S010481210.001
AP | 242 | 10/06/21 | 263 | Ferguson Enterprises, Inc. #3007 |  | 5615.08 | 9724905
AP | 242 | 10/06/21 | 264 | Ferguson Enterprises, Inc. #3007 |  | 4977.1 | 9724905-1
AP | 242 | 10/06/21 | 265 | Ferguson Enterprises, Inc. #3007 |  | 88.97 | 9726746
AP | 242 | 10/13/21 | 529 | Ferguson Enterprises, Inc. #3007 |  | 1295.47 | 9725334
AP | 242 | 10/13/21 | 536 | Consolidated Supply Co. |  | 8408.23 | S010497221.002
AP | 242 | 10/13/21 | 537 | Consolidated Supply Co. |  | 303.28 | S010507800.001
AP | 242 | 10/13/21 | 538 | Consolidated Supply Co. |  | 5380.5 | S010507800.002
AP | 242 | 10/13/21 | 543 | Ferguson Enterprises, Inc. #3007 |  | 1591.28 | 9779250
AP | 242 | 10/13/21 | 544 | Ferguson Enterprises, Inc. #3007 |  | 233.29 | 9780063
AP | 242 | 10/27/21 | 980 | Ferguson Enterprises, Inc. #3007 |  | 412.9 | 9817306
AP | 242 | 11/09/21 | 219 | Ferguson Enterprises, Inc. #3007 |  | 82.58 | 9817306-1
AP | 242 | 11/15/21 | 373 | Ferguson Enterprises, Inc. #3007 |  | 1525.81 | 9860840
AP | 242 | 11/15/21 | 377 | Ferguson Enterprises, Inc. #3007 |  | 381.45 | 9860840-1
AP | 242 | 02/23/22 | 647 | Ferguson Enterprises, Inc. #3007 |  | 46.5 | 0175636
AP | 242 | 02/28/22 | 875 | Rosen Supply Kirkland |  | 29.75 | 1601966-00
AP | 242 | 03/04/22 | 258 | Rosen Supply Kirkland |  | 94.23 | 1603043-00
AP | 242 | 03/04/22 | 259 | Rosen Supply Kirkland |  | 38.76 | 4306787-00
AP | 242 | 03/22/22 | 814 | Capital One Credit Card |  | 20.7 | 020722JB
AP | 242 | 03/22/22 | 850 | Rosen Supply Kirkland |  | 126.93 | 2192549-00
AP | 242 | 03/30/22 | 1066 | Ferguson Enterprises, Inc. #3007 |  | 7553.2 | 0293386
AP | 242 | 04/12/22 | 421 | Ferguson Enterprises, Inc. #3007 |  | 1054.71 | 0328371
AP | 242 | 04/12/22 | 422 | Ferguson Enterprises, Inc. #3007 |  | 2099.62 | 0328371-1
AP | 242 | 04/15/22 | 591 | Capital One Credit Card |  | 29.96 | 031722JB
AP | 242 | 04/15/22 | 594 | Capital One Credit Card |  | 39.63 | 032122JB
AP | 242 | 04/15/22 | 601 | Capital One Credit Card |  | 19.19 | 032422JB3
AP | 242 | 04/15/22 | 608 | Capital One Credit Card |  | 37.91 | 040722JB
AP | 242 | 04/18/22 | 659 | Ferguson Enterprises, Inc. #3007 |  | 26.53 | 0328371-2
AP | 242 | 04/20/22 | 753 | Ferguson Enterprises, Inc. #3007 |  | 1371.95 | 0364906
AP | 242 | 04/20/22 | 754 | Ferguson Enterprises, Inc. #3007 |  | 158.82 | 0364906-1
AP | 242 | 04/20/22 | 755 | Ferguson Enterprises, Inc. #3007 |  | 130.73 | 0374835
AP | 242 | 04/20/22 | 756 | Ferguson Enterprises, Inc. #3007 |  | 38.52 | 0382930
GL | 242 | 04/28/22 | 1048 | Req 8166 |  | -4752.87
AP | 242 | 05/09/22 | 238 | Ferguson Enterprises, Inc. #3007 |  | 28.58 | 0439531
GL | 242 | 05/10/22 | 273 | Req 8237 |  | 557.65
AP | 242 | 05/18/22 | 532 | Capital One Credit Card |  | 24 | 041922J2
AP | 242 | 05/18/22 | 538 | Capital One Credit Card |  | 27.11 | 042522J
GL | 242 | 05/26/22 | 975 | Req 8330 |  | 451.56
GL | 242 | 06/08/22 | 176 | Req 8390 |  | -4716.87
AP | 242 | 06/20/22 | 599 | Rosen Supply Kirkland |  | 638.61 | 1517.01
GL | 242 | 07/18/22 | 479 | Req 8499 |  | 180.19
AP | 242 | 08/03/22 | 24 | Rosen Supply Kirkland |  | 56.52 | 2741.01
GL | 242 | 09/06/22 | 103 | Req 8616 |  | 484.04
AP | 242 | 09/22/22 | 646 | Rosen Supply Kirkland |  | 1509.32 | 4036.01
GL | 242 | 10/10/22 | 164 | Req 8709 |  | 181.91
AP | 242 | 10/12/22 | 267 | Rosen Supply Kirkland |  | -1331.12 | 4916.01
AP | 242 | 10/12/22 | 268 | Rosen Supply Kirkland |  | 163.29 | 4916.02
GL | 242 | 10/31/22 | 940 | Req 8806 |  | -589.59
GL | 242 | 11/08/22 | 141 | Req 8807 |  | -252.08
GL | 242 | 11/16/22 | 301 | Req 8814 |  | -46.96
AP | 242 | 12/30/22 | 1172 | Capital One Credit Card |  | 31.84 | 111822J
AP | 600 | 07/26/21 | 624 | Scan2Core, Inc. |  | 675 | 76176
AP | 600 | 05/24/22 | 777 | Mechanical Resource Services, Inc. |  | 10650 | 17196-5843
AP | 600 | 06/27/22 | 914 | Chemical Products Company |  | 3150 | 3404
AP | 600 | 07/01/22 | 107 | Chemical Products Company |  | 3150 | 3409
AP | 600 | 07/18/22 | 495 | Mechanical Resource Services, Inc. |  | 7100 | 172296-5843
GL | 600 | 08/01/22 | 18 | AJ's Backflow Service |  | 300
GL | 600 | 08/22/22 | 622 | Backflow Testing, Online Bill Pay |  | 50
AP | 600 | 10/26/22 | 717 | AJ's Backflow Testing |  | 55 | 280-22
AP | 600 | 10/26/22 | 734 | Patchworks, Inc. |  | 650 | 11042
AP | 600 | 11/09/22 | 640 | AJ's Backflow Testing |  | -55 | 280-22A
AP | 600 | 11/30/22 | 698 | Bank of America CC |  | 56.65 | 101822R
AP | 601 | 01/03/19 | 93 | Franklin Engineering |  | 2101.25 | 7202
AP | 601 | 01/30/19 | 885 | Franklin Engineering |  | 1202.5 | 7208
AP | 601 | 02/27/19 | 746 | Franklin Engineering |  | 850.75 | 7287
AP | 601 | 03/20/19 | 699 | Franklin Engineering |  | 8071.75 | 7297
AP | 601 | 04/26/19 | 832 | Franklin Engineering |  | 7994.5 | 7351
AP | 601 | 05/29/19 | 799 | Franklin Engineering |  | 19738.75 | 7357
AP | 601 | 06/24/19 | 749 | Franklin Engineering |  | 9314.25 | 7404
AP | 601 | 07/31/19 | 723 | Franklin Engineering |  | 6723.25 | 7425
AP | 601 | 08/21/19 | 793 | Franklin Engineering |  | 4214 | 7463
AP | 601 | 09/30/19 | 748 | Franklin Engineering |  | 4872.5 | 7490
AP | 601 | 10/22/19 | 557 | Franklin Engineering |  | 6992 | 7516
AP | 601 | 11/21/19 | 805 | Franklin Engineering |  | 8946 | 7540
AP | 601 | 03/23/20 | 705 | Franklin Engineering |  | 1152.75 | 7648
AP | 601 | 07/17/20 | 348 | Franklin Engineering |  | 1740 | 7784
AP | 601 | 04/30/21 | 661 | Franklin Engineering |  | 3203 | 8100
AP | 601 | 05/25/21 | 575 | Franklin Engineering |  | 8665.5 | 8144
AP | 601 | 06/30/21 | 771 | Franklin Engineering |  | 5212.5 | 8186
AP | 602 | 11/09/21 | 205 | Consolidated Supply Co. |  | 55.13 | S010539471.003
AP | 602 | 06/06/22 | 160 | United Rentals, Inc. |  | 1065.84 | 206496795-001
AP | 602 | 07/01/22 | 151 | Sunbelt Rentals, Inc. |  | 199.43 | 127387711-0001
AP | 602 | 10/27/22 | 840 | United Rentals, Inc. |  | 353.44 | 211890828-001
AP | 603 | 08/01/19 | 379 | Capital One Credit Card |  | 10897.9 | 072919B
AP | 603 | 08/15/19 | 561 | Capital One Credit Card |  | 17629.3 | 081519R
AP | 603 | 09/08/22 | 320 | Bank of America CC |  | 487.2 | 080322J2
AP | 603 | 09/08/22 | 321 | Bank of America CC |  | 12.18 | 080322J1
AP | 607 | 04/30/19 | 965 | Capital One Credit Card |  | 16 | 032919R1
AP | 607 | 07/10/19 | 240 | Capital One Credit Card |  | 19.15 | 061219R1
GL | 607 | 08/21/19 | 880 | Orlando Paco Leyva |  | 93.6
AP | 607 | 09/09/19 | 131 | Capital One Credit Card |  | 30 | 082119B
AP | 607 | 09/09/19 | 132 | Capital One Credit Card |  | 383.6 | 082119B1
AP | 607 | 09/09/19 | 133 | Capital One Credit Card |  | 8.5 | 082119B2
AP | 607 | 09/10/19 | 185 | Capital One Credit Card |  | 8.5 | 082119J
AP | 607 | 09/10/19 | 186 | Capital One Credit Card |  | 20 | 082119J1
AP | 607 | 09/10/19 | 227 | Capital One Credit Card |  | 19.15 | 082719JB
AP | 607 | 09/10/19 | 232 | Capital One Credit Card |  | 19.15 | 090519JB
GL | 607 | 09/26/19 | 738 | Juan Martinez Reyes |  | 24
GL | 607 | 09/26/19 | 739 | Orlando Paco Leyva |  | 38.3
AP | 607 | 10/01/19 | 207 | Capital One Credit Card |  | 13 | 090919B
AP | 607 | 10/01/19 | 215 | Capital One Credit Card |  | 60 | 092619B2
AP | 607 | 10/01/19 | 218 | Capital One Credit Card |  | 120 | 100319B2
GL | 607 | 10/03/19 | 91 | Orlando Paco Leyva |  | 46.8
GL | 607 | 10/10/19 | 369 | Juan Martinez Reyes |  | 24
GL | 607 | 10/10/19 | 370 | Orlando Paco Leyva |  | 19.15
AP | 607 | 10/11/19 | 346 | Capital One Credit Card |  | 111.5 | 100419JB1
GL | 607 | 11/01/19 | 142 | Franklin Ramos Herrera |  | 17
AP | 607 | 11/05/19 | 159 | Washington State Ferries |  | 122.45 | *RK336538
GL | 607 | 11/07/19 | 431 | Juan Martinez Reyes |  | 33
AP | 607 | 11/21/19 | 750 | Capital One Credit Card |  | 216 | 102419B1
AP | 607 | 11/21/19 | 794 | Capital One Credit Card |  | 15.75 | 100719JB
AP | 607 | 11/21/19 | 796 | Capital One Credit Card |  | 15.75 | 101819JB2
AP | 607 | 12/09/19 | 203 | Washington State Ferries |  | 181.9 | *RK337995
AP | 607 | 01/08/20 | 221 | Capital One Credit Card |  | 110 | 112019R
AP | 607 | 01/08/20 | 222 | Capital One Credit Card |  | 140 | 112019R2
AP | 607 | 01/08/20 | 229 | Capital One Credit Card |  | 117.37 | 111419J
AP | 607 | 01/08/20 | 230 | Capital One Credit Card |  | 15.75 | 111419J1
AP | 607 | 01/10/20 | 409 | Capital One Credit Card |  | 150 | 122819B
AP | 607 | 01/10/20 | 435 | Capital One Credit Card |  | 110 | 121619R3
AP | 607 | 01/10/20 | 436 | Capital One Credit Card |  | 140 | 121619R4
AP | 607 | 02/10/20 | 130 | Washington State Ferries |  | 113 | *RK340904
AP | 607 | 03/09/20 | 158 | Washington State Ferries |  | 138.2 | *RK342363
AP | 607 | 03/09/20 | 173 | Capital One Credit Card |  | 200 | 012420B
AP | 607 | 03/09/20 | 199 | Capital One Credit Card |  | 13.55 | 020420BH
AP | 607 | 03/09/20 | 200 | Capital One Credit Card |  | 15.75 | 020420BH2
AP | 607 | 03/09/20 | 201 | Capital One Credit Card |  | 13 | 020420BH3
AP | 607 | 03/09/20 | 212 | Capital One Credit Card |  | 110 | 011620R3
AP | 607 | 03/09/20 | 213 | Capital One Credit Card |  | 140 | 011620R4
AP | 607 | 03/25/20 | 467 | Capital One Credit Card |  | 150 | 021220B
AP | 607 | 03/25/20 | 479 | Capital One Credit Card |  | 150 | 022820B
AP | 607 | 03/25/20 | 500 | Capital One Credit Card |  | 110 | 021620R4
AP | 607 | 03/25/20 | 501 | Capital One Credit Card |  | 150 | 021620R5
AP | 607 | 04/09/20 | 109 | Washington State Ferries |  | 620.75 | *RK343823
AP | 607 | 04/15/20 | 164 | Capital One Credit Card |  | 170 | 031720B
AP | 607 | 04/15/20 | 179 | Capital One Credit Card |  | 15.75 | 031320BH1
AP | 607 | 04/15/20 | 180 | Capital One Credit Card |  | 15.75 | 031320RH2
AP | 607 | 04/15/20 | 194 | Capital One Credit Card |  | 110 | 031620R2
AP | 607 | 04/15/20 | 195 | Capital One Credit Card |  | 150 | 031620R3
AP | 607 | 06/08/20 | 116 | Capital One Credit Card |  | 120 | 041620R2
AP | 607 | 06/08/20 | 117 | Capital One Credit Card |  | 150 | 041620R3
AP | 607 | 06/12/20 | 299 | Capital One Credit Card |  | 123.6 | 051520R2
AP | 607 | 06/12/20 | 300 | Capital One Credit Card |  | 154.5 | 051520R3
AP | 607 | 07/08/20 | 97 | Washington State Ferries |  | 204 | *RK348206
AP | 607 | 08/06/20 | 136 | Washington State Ferries |  | 285.6 | *RK349671
AP | 607 | 08/10/20 | 199 | Capital One Credit Card |  | 123.6 | 061520R2
AP | 607 | 08/10/20 | 200 | Capital One Credit Card |  | 154.5 | 061520R3
AP | 607 | 08/10/20 | 243 | Capital One Credit Card |  | 123.6 | 071520R2
AP | 607 | 08/10/20 | 244 | Capital One Credit Card |  | 154.5 | 071520R3
AP | 607 | 09/15/20 | 233 | Capital One Credit Card |  | 123.6 | 081520R2
AP | 607 | 09/15/20 | 234 | Capital One Credit Card |  | 154.5 | 081520R3
AP | 607 | 10/13/20 | 272 | Capital One Credit Card |  | 123.6 | 091520R2
AP | 607 | 10/13/20 | 273 | Capital One Credit Card |  | 154.5 | 091520R3
AP | 607 | 11/11/20 | 149 | Capital One Credit Card |  | 123.6 | 101520R1
AP | 607 | 11/11/20 | 150 | Capital One Credit Card |  | 154.5 | 101520R2
AP | 607 | 12/16/20 | 321 | Capital One Credit Card |  | 123.6 | 111520R1
AP | 607 | 12/16/20 | 322 | Capital One Credit Card |  | 154.5 | 121520R2
AP | 607 | 02/02/21 | 19 | Capital One Credit Card |  | 123.6 | 121520R1
AP | 607 | 02/02/21 | 20 | Capital One Credit Card |  | 154.5 | 121520R3
AP | 607 | 02/05/21 | 165 | Washington State Ferries |  | 409.25 | *RK363032
AP | 607 | 02/08/21 | 205 | Capital One Credit Card |  | 123.6 | 011521R1
AP | 607 | 02/08/21 | 206 | Capital One Credit Card |  | 154.5 | 011521R2
AP | 607 | 03/03/21 | 49 | Washington State Ferries |  | 1348 | *RK364537
AP | 607 | 03/23/21 | 419 | Capital One Credit Card |  | 122.78 | 021521R1
AP | 607 | 03/23/21 | 420 | Capital One Credit Card |  | 153.38 | 021521R2
AP | 607 | 04/07/21 | 103 | Washington State Ferries |  | 1410.4 | *RK366045
AP | 607 | 04/27/21 | 528 | Capital One Credit Card |  | 133.02 | 031521R1
AP | 607 | 04/27/21 | 529 | Capital One Credit Card |  | 153.38 | 031521R2
AP | 607 | 05/06/21 | 131 | Washington State Ferries |  | 1060.4 | *RK372084
AP | 607 | 05/24/21 | 503 | Capital One Credit Card |  | 133.02 | 041521R
AP | 607 | 05/24/21 | 504 | Capital One Credit Card |  | 153.38 | 041521R2
AP | 607 | 06/07/21 | 121 | Washington State Ferries |  | 1191.65 | *RK373595
AP | 607 | 06/29/21 | 724 | Capital One Credit Card |  | 20.4 | 051021BH
AP | 607 | 06/29/21 | 725 | Capital One Credit Card |  | 20.4 | 051021BH2
AP | 607 | 06/29/21 | 726 | Capital One Credit Card |  | 11 | 051021BH3
AP | 607 | 06/29/21 | 727 | Capital One Credit Card |  | 40.8 | 052521BH
AP | 607 | 06/29/21 | 733 | Capital One Credit Card |  | 133.02 | 051521R1
AP | 607 | 06/29/21 | 734 | Capital One Credit Card |  | 153.38 | 051521R
AP | 607 | 07/09/21 | 185 | Washington State Ferries |  | 1753.2 | *RK375110
AP | 607 | 07/13/21 | 261 | Capital One Credit Card |  | 13 | 061021BH
AP | 607 | 07/13/21 | 262 | Capital One Credit Card |  | 11 | 070621BH
AP | 607 | 07/13/21 | 278 | Capital One Credit Card |  | 133.02 | 061521R1
AP | 607 | 07/13/21 | 279 | Capital One Credit Card |  | 153.38 | 061521R2
AP | 607 | 08/09/21 | 170 | Washington State Ferries |  | 1454.1 | 2021-07-31
AP | 607 | 08/16/21 | 436 | Capital One Credit Card |  | 7.67 | 071521RH
AP | 607 | 08/16/21 | 437 | Capital One Credit Card |  | 11 | 071921RH
AP | 607 | 08/16/21 | 439 | Capital One Credit Card |  | 11.3 | 080221RH
AP | 607 | 08/16/21 | 450 | Capital One Credit Card |  | 133.02 | 071521R
AP | 607 | 08/16/21 | 451 | Capital One Credit Card |  | 153.38 | 071521R2
AP | 607 | 08/18/21 | 533 | Capital One Credit Card |  | 8.3 | 071921JB
AP | 607 | 08/18/21 | 536 | Capital One Credit Card |  | 13.3 | 072621JB
AP | 607 | 09/08/21 | 166 | Washington State Ferries |  | 1461 | *RK378144
AP | 607 | 10/04/21 | 163 | Capital One Credit Card |  | 11 | 080921RH
AP | 607 | 10/04/21 | 164 | Capital One Credit Card |  | 11 | 082721RH
AP | 607 | 10/04/21 | 172 | Capital One Credit Card |  | 133.02 | 081521R1
AP | 607 | 10/04/21 | 173 | Capital One Credit Card |  | 173.88 | 081521R2
AP | 607 | 10/04/21 | 189 | Capital One Credit Card |  | 13 | 081621JB2
AP | 607 | 10/04/21 | 193 | Capital One Credit Card |  | 13.3 | 081921JB
AP | 607 | 10/04/21 | 195 | Capital One Credit Card |  | 13.3 | 082321JB
AP | 607 | 10/04/21 | 198 | Capital One Credit Card |  | 13.3 | 082621JB
AP | 607 | 10/04/21 | 199 | Capital One Credit Card |  | 13.3 | 083021JB
AP | 607 | 10/05/21 | 228 | Washington State Ferries |  | 1562.7 | *RK379661
AP | 607 | 10/12/21 | 477 | Capital One Credit Card |  | 133.02 | 091521R2
AP | 607 | 10/12/21 | 478 | Capital One Credit Card |  | 173.88 | 091521R3
AP | 607 | 11/05/21 | 153 | Capital One Credit Card |  | 13.3 | 091321JB
AP | 607 | 11/05/21 | 162 | Capital One Credit Card |  | 13.3 | 092821JB
AP | 607 | 11/05/21 | 165 | Capital One Credit Card |  | 13.3 | 093021JB
AP | 607 | 11/05/21 | 167 | Capital One Credit Card |  | 7.67 | 100121JB1
AP | 607 | 11/05/21 | 168 | Capital One Credit Card |  | 13.3 | 100421JB
AP | 607 | 11/08/21 | 195 | Washington State Ferries |  | 1793.4 | *RK381180
AP | 607 | 11/30/21 | 756 | Capital One Credit Card |  | 133.02 | 101521R1
AP | 607 | 11/30/21 | 757 | Capital One Credit Card |  | 173.88 | 101521R2
AP | 607 | 11/30/21 | 767 | Capital One Credit Card |  | 13.3 | 101121JB
AP | 607 | 11/30/21 | 771 | Capital One Credit Card |  | 13.3 | 101821JB
AP | 607 | 11/30/21 | 775 | Capital One Credit Card |  | 13.3 | 102121JB
AP | 607 | 11/30/21 | 776 | Capital One Credit Card |  | 13.3 | 102521JB
AP | 607 | 11/30/21 | 781 | Capital One Credit Card |  | 7.3 | 110121JB2
AP | 607 | 11/30/21 | 782 | Capital One Credit Card |  | 7.3 | 110121JB3
AP | 607 | 11/30/21 | 786 | Capital One Credit Card |  | 13.3 | 110421JB
AP | 607 | 12/07/21 | 150 | Washington State Ferries |  | 1176.8 | *RK382702
AP | 607 | 12/21/21 | 690 | Capital One Credit Card |  | 13.3 | 112921JB
AP | 607 | 12/22/21 | 839 | Capital One Credit Card |  | 133.02 | 111521R
AP | 607 | 12/22/21 | 840 | Capital One Credit Card |  | 173.88 | 111521R2
AP | 607 | 01/07/22 | 127 | Washington State Ferries |  | 236.15 | *RK384229
AP | 607 | 01/14/22 | 344 | Capital One Credit Card |  | 13 | 121321A
AP | 607 | 01/14/22 | 348 | Capital One Credit Card |  | 13.3 | 121321JB
AP | 607 | 01/17/22 | 386 | Bank of America CC |  | 133.02 | 121521R
AP | 607 | 01/17/22 | 387 | Bank of America CC |  | 173.88 | 121521R2
AP | 607 | 02/03/22 | 139 | Washington State Ferries |  | 109.65 | *RK385763
GL | 607 | 02/14/22 | 349 | Jose Cruz Reyes |  | 24.16
GL | 607 | 02/14/22 | 350 | Cory Eliassen |  | 37.43
AP | 607 | 02/14/22 | 364 | Capital One Credit Card |  | 13 | 012522A
AP | 607 | 02/14/22 | 366 | Capital One Credit Card |  | 13 | 012822A
AP | 607 | 02/14/22 | 368 | Capital One Credit Card |  | 13.55 | 011922JB
AP | 607 | 02/14/22 | 383 | Capital One Credit Card |  | 13.55 | 020222JB
AP | 607 | 02/14/22 | 386 | Capital One Credit Card |  | 13.55 | 020422JB
AP | 607 | 02/15/22 | 394 | Bank of America CC |  | 133.02 | 011522R1
AP | 607 | 02/15/22 | 395 | Bank of America CC |  | 173.88 | 011522R2
AP | 607 | 03/07/22 | 193 | Washington State Ferries |  | 94.95 | *RK387303
AP | 607 | 03/21/22 | 755 | Bank of America CC |  | 133.02 | 021522R1
AP | 607 | 03/21/22 | 756 | Bank of America CC |  | 173.88 | 021522R2
AP | 607 | 03/22/22 | 799 | Capital One Credit Card |  | 13 | 020822A
AP | 607 | 03/22/22 | 804 | Capital One Credit Card |  | 8.47 | 021522A1
AP | 607 | 03/22/22 | 805 | Capital One Credit Card |  | 8.47 | 021522A2
AP | 607 | 03/22/22 | 806 | Capital One Credit Card |  | 11.16 | 021622A
AP | 607 | 03/22/22 | 807 | Capital One Credit Card |  | 12.19 | 021822A
AP | 607 | 03/22/22 | 811 | Capital One Credit Card |  | 12.19 | 022522A
AP | 607 | 03/22/22 | 815 | Capital One Credit Card |  | 13.55 | 020822JB
AP | 607 | 03/22/22 | 826 | Capital One Credit Card |  | 9.23 | 021822JB
AP | 607 | 03/22/22 | 828 | Capital One Credit Card |  | 14.19 | 022222JB
AP | 607 | 03/22/22 | 830 | Capital One Credit Card |  | 13.57 | 022522JB
AP | 607 | 03/22/22 | 834 | Capital One Credit Card |  | 14.19 | 030122JB2
GL | 607 | 04/01/22 | 203 | pymt adj |  | 0.3
GL | 607 | 04/01/22 | 204 | Ferry pymt adj |  | -0.6
AP | 607 | 04/01/22 | 205 | Washington State Ferries |  | 80.55 | *RK388844
AP | 607 | 04/15/22 | 582 | Capital One Credit Card |  | 12.19 | 031122A
AP | 607 | 04/15/22 | 583 | Capital One Credit Card |  | 14.04 | 031822A
AP | 607 | 04/15/22 | 586 | Capital One Credit Card |  | 8.47 | 032522A
AP | 607 | 04/15/22 | 592 | Capital One Credit Card |  | 9.23 | 031922JB
AP | 607 | 04/15/22 | 596 | Capital One Credit Card |  | 14.19 | 032222JB2
AP | 607 | 04/18/22 | 624 | Bank of America CC |  | 173.88 | 031522R2
AP | 607 | 04/19/22 | 695 | Capital One Credit Card |  | 12.33 | 032522J
AP | 607 | 05/05/22 | 84 | Washington State Ferries |  | 80.25 | *RK390387
AP | 607 | 05/18/22 | 516 | Capital One Credit Card |  | 12.19 | 042722A
AP | 607 | 05/18/22 | 523 | Capital One Credit Card |  | 12.33 | 041322J
AP | 607 | 05/18/22 | 531 | Capital One Credit Card |  | 7.99 | 041922J
AP | 607 | 05/18/22 | 533 | Capital One Credit Card |  | 13.57 | 042022J
AP | 607 | 05/18/22 | 535 | Capital One Credit Card |  | 13.57 | 042122J2
AP | 607 | 05/18/22 | 536 | Capital One Credit Card |  | 8.06 | 042222J
AP | 607 | 05/18/22 | 537 | Capital One Credit Card |  | 13.57 | 042322J
AP | 607 | 05/18/22 | 540 | Capital One Credit Card |  | 8.06 | 043022J
AP | 607 | 05/18/22 | 547 | Bank of America CC |  | 133.02 | 041522R3
AP | 607 | 05/18/22 | 548 | Bank of America CC |  | 173.88 | 041522R4
AP | 607 | 06/06/22 | 159 | Washington State Ferries |  | 232.4 | *RK391851
GL | 607 | 06/09/22 | 565 | Cory Eliassen |  | 126.36
AP | 607 | 06/21/22 | 638 | Capital One Credit Card |  | 12.19 | 050922A1
AP | 607 | 06/21/22 | 639 | Capital One Credit Card |  | 8.47 | 051322A
AP | 607 | 06/21/22 | 644 | Capital One Credit Card |  | 12.19 | 060322A
AP | 607 | 06/21/22 | 661 | Bank of America CC |  | 143.27 | 051522R2
AP | 607 | 06/21/22 | 662 | Bank of America CC |  | 204.6 | 051522R3
AP | 607 | 06/21/22 | 690 | Capital One Credit Card |  | 14.19 | 052122J
AP | 607 | 06/21/22 | 692 | Capital One Credit Card |  | 13.57 | 052622J
AP | 607 | 07/11/22 | 263 | Washington State Ferries |  | 141.6 | *RK393206
AP | 607 | 07/19/22 | 509 | Bank of America CC |  | 143.27 | 061522R4
AP | 607 | 07/19/22 | 510 | Bank of America CC |  | 204.6 | 061522R5
AP | 607 | 07/19/22 | 537 | Capital One Credit Card |  | 12.19 | 060922A
AP | 607 | 07/19/22 | 543 | Capital One Credit Card |  | 12.19 | 062222A
AP | 607 | 07/19/22 | 544 | Capital One Credit Card |  | 8.47 | 062222A2
AP | 607 | 07/19/22 | 545 | Capital One Credit Card |  | 12.19 | 062322A
AP | 607 | 07/19/22 | 549 | Capital One Credit Card |  | 13.57 | 061422JB
AP | 607 | 07/19/22 | 550 | Capital One Credit Card |  | 9.08 | 061522JB
AP | 607 | 07/19/22 | 552 | Capital One Credit Card |  | 13.43 | 061622JB
AP | 607 | 08/08/22 | 197 | Washington State Ferries |  | 65.2 | *RK394565
AP | 607 | 09/07/22 | 145 | Washington State Ferries |  | 78.9 | *RK395928
AP | 607 | 09/07/22 | 182 | Capital One Credit Card |  | 8.47 | 071522A
AP | 607 | 09/07/22 | 183 | Capital One Credit Card |  | 8.47 | 071922A
AP | 607 | 09/07/22 | 289 | Bank of America CC |  | 143.5 | 071522R2
AP | 607 | 09/07/22 | 290 | Bank of America CC |  | 207 | 071522R3
AP | 607 | 09/09/22 | 301 | Capital One Credit Card |  | 11.93 | 071222J
AP | 607 | 09/09/22 | 307 | Capital One Credit Card |  | 4.44 | 080422JB
AP | 607 | 09/29/22 | 925 | Bank of America CC |  | -135 | 082622R
AP | 607 | 09/29/22 | 931 | Bank of America CC |  | 143.5 | 081522R2
AP | 607 | 09/29/22 | 932 | Bank of America CC |  | 207 | 081522R3
AP | 607 | 10/03/22 | 126 | Washington State Ferries |  | 65.2 | 2022-09
AP | 607 | 10/26/22 | 681 | Capital One Credit Card |  | 2 | 090822J
AP | 607 | 10/26/22 | 683 | Capital One Credit Card |  | 6.94 | 091022J
AP | 607 | 11/08/22 | 152 | Washington State Ferries |  | 34.4 | *RK398664
PR | 995 | 04/26/19 | 744 | Barnhart, Joseph N |  | 66.53
PR | 995 | 06/14/19 | 523 | Donelson, Richard T |  | 132.34
PR | 995 | 06/21/19 | 693 | Donelson, Richard T |  | 185.28
PR | 995 | 06/28/19 | 910 | Donelson, Richard T |  | 291.16
PR | 995 | 07/05/19 | 81 | Donelson, Richard T |  | 238.22
PR | 995 | 07/12/19 | 352 | Donelson, Richard T |  | 26.47
PR | 995 | 07/19/19 | 585 | Donelson, Richard T |  | 344.09
PR | 995 | 07/26/19 | 685 | Donelson, Richard T |  | 105.88
PR | 995 | 08/02/19 | 8 | Barnhart, Joseph N |  | 127.05
PR | 995 | 08/02/19 | 76 | Donelson, Richard T |  | 26.47
PR | 995 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 08/09/19 | 260 | Barnhart, Joseph N |  | 105.88
PR | 995 | 08/09/19 | 328 | Donelson, Richard T |  | 185.28
PR | 995 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 08/16/19 | 567 | Barnhart, Joseph N |  | 359.98
PR | 995 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/16/19 | 636 | Donelson, Richard T |  | 185.28
PR | 995 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 08/23/19 | 802 | Barbosa, Michael S |  | 98.25
PR | 995 | 08/23/19 | 803 | Barnhart, Joseph N |  | 359.98
PR | 995 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 20.96
PR | 995 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 335.41
PR | 995 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 406.56
PR | 995 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 33.03
PR | 995 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 116.46
PR | 995 | 08/30/19 | 994 | Barnhart, Joseph N |  | 317.63
PR | 995 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 135.52
PR | 995 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 88.09
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 132.34
PR | 995 | 08/30/19 | 1064 | Donelson, Richard T |  | 26.47
PR | 995 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 93.17
PR | 995 | 09/06/19 | 15 | Barnhart, Joseph N |  | 232.93
PR | 995 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 83.85
PR | 995 | 09/06/19 | 85 | Donelson, Richard T |  | 52.94
PR | 995 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 09/13/19 | 239 | Barnhart, Joseph N |  | 402.33
PR | 995 | 09/13/19 | 278 | Martinez Reyes, Juan C |  | 237.58
PR | 995 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 25.41
PR | 995 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 287.98
PR | 995 | 09/13/19 | 284 | Ramos Herrera, Franklin J |  | 198.2
PR | 995 | 09/13/19 | 308 | Donelson, Richard T |  | 317.63
PR | 995 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 09/20/19 | 476 | Barnhart, Joseph N |  | 169.4
PR | 995 | 09/20/19 | 546 | Donelson, Richard T |  | 264.69
PR | 995 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 09/27/19 | 632 | Barnhart, Joseph N |  | 719.95
PR | 995 | 09/27/19 | 632 | Barnhart, Joseph N |  | 21.18
PR | 995 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 406.56
PR | 995 | 09/27/19 | 681 | Ramos Herrera, Franklin J |  | 264.26
PR | 995 | 09/27/19 | 705 | Donelson, Richard T |  | 132.34
PR | 995 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 10/04/19 | 8 | Barnhart, Joseph N |  | 423.5
PR | 995 | 10/04/19 | 8 | Barnhart, Joseph N |  | 105.88
PR | 995 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 50.82
PR | 995 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 271.04
PR | 995 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 33.03
PR | 995 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 176.18
PR | 995 | 10/04/19 | 81 | Donelson, Richard T |  | 79.41
PR | 995 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 69.88
PR | 995 | 10/11/19 | 263 | Barnhart, Joseph N |  | 381.15
PR | 995 | 10/11/19 | 263 | Barnhart, Joseph N |  | 42.35
PR | 995 | 10/11/19 | 334 | Donelson, Richard T |  | 79.41
PR | 995 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 10/18/19 | 457 | Barnhart, Joseph N |  | 359.98
PR | 995 | 10/18/19 | 457 | Barnhart, Joseph N |  | 21.18
PR | 995 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 10/18/19 | 527 | Donelson, Richard T |  | 26.47
PR | 995 | 10/25/19 | 592 | Barnhart, Joseph N |  | 52.94
PR | 995 | 10/25/19 | 592 | Barnhart, Joseph N |  | 211.75
PR | 995 | 10/25/19 | 634 | Martinez Reyes, Juan C |  | 111.8
PR | 995 | 10/25/19 | 664 | Donelson, Richard T |  | 158.81
PR | 995 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 46.59
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 45.74
PR | 995 | 11/01/19 | 8 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/01/19 | 50 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 11/01/19 | 80 | Donelson, Richard T |  | 264.69
PR | 995 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 11/08/19 | 182 | Barnhart, Joseph N |  | 525.99
PR | 995 | 11/08/19 | 182 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/08/19 | 182 | Barnhart, Joseph N |  | 45.74
PR | 995 | 11/08/19 | 211 | Holmes, Anthony R |  | 27.95
PR | 995 | 11/08/19 | 211 | Holmes, Anthony R |  | 447.22
PR | 995 | 11/08/19 | 211 | Holmes, Anthony R |  | 298.14
PR | 995 | 11/08/19 | 224 | Martinez Reyes, Juan C |  | 376.07
PR | 995 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 298.14
PR | 995 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 203.28
PR | 995 | 11/08/19 | 232 | Reyes Cruz, Denis A |  | 111.8
PR | 995 | 11/08/19 | 253 | Donelson, Richard T |  | 449.97
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 11/15/19 | 442 | Barnhart, Joseph N |  | 525.99
PR | 995 | 11/15/19 | 442 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/15/19 | 483 | Martinez Reyes, Juan C |  | 454.42
PR | 995 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 149.07
PR | 995 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 101.64
PR | 995 | 11/15/19 | 512 | Donelson, Richard T |  | 211.75
PR | 995 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 11/22/19 | 613 | Barnhart, Joseph N |  | 68.61
PR | 995 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 11/27/19 | 847 | Barnhart, Joseph N |  | 297.3
PR | 995 | 11/27/19 | 875 | Holmes, Anthony R |  | 298.14
PR | 995 | 11/27/19 | 888 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 122.82
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 114.35
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 68.61
PR | 995 | 12/06/19 | 33 | Barnhart, Joseph N |  | 114.35
PR | 995 | 12/06/19 | 61 | Hoeg, Xavier A |  | 76.23
PR | 995 | 12/06/19 | 61 | Hoeg, Xavier A |  | 60.98
PR | 995 | 12/06/19 | 61 | Hoeg, Xavier A |  | 106.72
PR | 995 | 12/06/19 | 62 | Holmes, Anthony R |  | 149.07
PR | 995 | 12/06/19 | 62 | Holmes, Anthony R |  | 186.34
PR | 995 | 12/06/19 | 62 | Holmes, Anthony R |  | 260.88
PR | 995 | 12/06/19 | 104 | Donelson, Richard T |  | 132.34
PR | 995 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 91.48
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 114.35
PR | 995 | 12/13/19 | 394 | Barnhart, Joseph N |  | 68.61
PR | 995 | 12/13/19 | 422 | Hoeg, Xavier A |  | 53.36
PR | 995 | 12/13/19 | 422 | Hoeg, Xavier A |  | 190.58
PR | 995 | 12/13/19 | 423 | Holmes, Anthony R |  | 204.97
PR | 995 | 12/13/19 | 423 | Holmes, Anthony R |  | 540.39
PR | 995 | 12/13/19 | 465 | Donelson, Richard T |  | 79.41
PR | 995 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 12/20/19 | 547 | Barnhart, Joseph N |  | 182.95
PR | 995 | 12/20/19 | 547 | Barnhart, Joseph N |  | 182.95
PR | 995 | 12/20/19 | 575 | Hoeg, Xavier A |  | 15.25
PR | 995 | 12/20/19 | 576 | Holmes, Anthony R |  | 465.85
PR | 995 | 12/20/19 | 576 | Holmes, Anthony R |  | 279.51
PR | 995 | 12/20/19 | 618 | Donelson, Richard T |  | 52.94
PR | 995 | 12/27/19 | 704 | Barnhart, Joseph N |  | 91.48
PR | 995 | 12/27/19 | 704 | Barnhart, Joseph N |  | 91.48
PR | 995 | 12/27/19 | 733 | Hoeg, Xavier A |  | 83.85
PR | 995 | 12/27/19 | 733 | Hoeg, Xavier A |  | 38.12
PR | 995 | 12/27/19 | 734 | Holmes, Anthony R |  | 335.41
PR | 995 | 12/27/19 | 734 | Holmes, Anthony R |  | 111.8
PR | 995 | 12/27/19 | 776 | Donelson, Richard T |  | 26.47
PR | 995 | 01/03/20 | 36 | Hoeg, Xavier A |  | 144.84
PR | 995 | 01/03/20 | 36 | Hoeg, Xavier A |  | 38.12
PR | 995 | 01/03/20 | 37 | Holmes, Anthony R |  | 419.27
PR | 995 | 01/03/20 | 37 | Holmes, Anthony R |  | 93.17
PR | 995 | 01/03/20 | 81 | Donelson, Richard T |  | 158.81
PR | 995 | 01/10/20 | 280 | Barnhart, Joseph N |  | 251.56
PR | 995 | 01/10/20 | 280 | Barnhart, Joseph N |  | 194.39
PR | 995 | 01/10/20 | 280 | Barnhart, Joseph N |  | 91.48
PR | 995 | 01/10/20 | 309 | Hoeg, Xavier A |  | 289.67
PR | 995 | 01/10/20 | 309 | Hoeg, Xavier A |  | 15.25
PR | 995 | 01/10/20 | 310 | Holmes, Anthony R |  | 745.36
PR | 995 | 01/10/20 | 352 | Donelson, Richard T |  | 264.69
PR | 995 | 01/17/20 | 542 | Anderson, Richard P |  | 72.63
PR | 995 | 01/17/20 | 546 | Barnhart, Joseph N |  | 297.3
PR | 995 | 01/17/20 | 546 | Barnhart, Joseph N |  | 68.61
PR | 995 | 01/17/20 | 571 | Gonzalez Hernandez, Josue |  | 53.36
PR | 995 | 01/17/20 | 575 | Hoeg, Xavier A |  | 198.2
PR | 995 | 01/17/20 | 575 | Hoeg, Xavier A |  | 91.48
PR | 995 | 01/17/20 | 576 | Holmes, Anthony R |  | 540.39
PR | 995 | 01/17/20 | 576 | Holmes, Anthony R |  | 167.71
PR | 995 | 01/17/20 | 618 | Donelson, Richard T |  | 211.75
PR | 995 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 98.25
PR | 995 | 01/24/20 | 675 | Anderson, Richard P |  | 332.02
PR | 995 | 01/24/20 | 679 | Barnhart, Joseph N |  | 274.43
PR | 995 | 01/24/20 | 679 | Barnhart, Joseph N |  | 91.48
PR | 995 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 243.94
PR | 995 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 01/24/20 | 707 | Hoeg, Xavier A |  | 213.44
PR | 995 | 01/24/20 | 707 | Hoeg, Xavier A |  | 91.48
PR | 995 | 01/24/20 | 708 | Holmes, Anthony R |  | 521.75
PR | 995 | 01/24/20 | 708 | Holmes, Anthony R |  | 223.61
PR | 995 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 250.71
PR | 995 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 01/24/20 | 750 | Donelson, Richard T |  | 132.34
PR | 995 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 01/31/20 | 833 | Amaya Gonzalez, Edilberto A |  | 182.95
PR | 995 | 01/31/20 | 834 | Anderson, Richard P |  | 166.01
PR | 995 | 01/31/20 | 837 | Barbosa, Michael S |  | 167.71
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 274.43
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 91.48
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 114.35
PR | 995 | 01/31/20 | 838 | Barnhart, Joseph N |  | 274.43
PR | 995 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 167.71
PR | 995 | 01/31/20 | 867 | Hoeg, Xavier A |  | 228.69
PR | 995 | 01/31/20 | 867 | Hoeg, Xavier A |  | 15.25
PR | 995 | 01/31/20 | 868 | Holmes, Anthony R |  | 279.51
PR | 995 | 01/31/20 | 868 | Holmes, Anthony R |  | 708.09
PR | 995 | 01/31/20 | 868 | Holmes, Anthony R |  | 37.27
PR | 995 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 164.53
PR | 995 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 15.67
PR | 995 | 01/31/20 | 911 | Donelson, Richard T |  | 211.75
PR | 995 | 02/07/20 | 25 | Anderson, Richard P |  | 166.01
PR | 995 | 02/07/20 | 29 | Barnhart, Joseph N |  | 343.04
PR | 995 | 02/07/20 | 29 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/07/20 | 53 | Gonzalez Hernandez, Josue |  | 121.97
PR | 995 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 133.4
PR | 995 | 02/07/20 | 57 | Hoeg, Xavier A |  | 243.94
PR | 995 | 02/07/20 | 57 | Hoeg, Xavier A |  | 15.25
PR | 995 | 02/07/20 | 57 | Hoeg, Xavier A |  | 45.74
PR | 995 | 02/07/20 | 58 | Holmes, Anthony R |  | 540.39
PR | 995 | 02/07/20 | 58 | Holmes, Anthony R |  | 74.54
PR | 995 | 02/07/20 | 58 | Holmes, Anthony R |  | 111.8
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 91.48
PR | 995 | 02/07/20 | 61 | Hubbard, Robert W |  | 91.48
PR | 995 | 02/07/20 | 65 | Lee, Ha Nul |  | 111.17
PR | 995 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/07/20 | 102 | Donelson, Richard T |  | 52.94
PR | 995 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 49.13
PR | 995 | 02/14/20 | 239 | Barnhart, Joseph N |  | 182.95
PR | 995 | 02/14/20 | 239 | Barnhart, Joseph N |  | 22.87
PR | 995 | 02/14/20 | 267 | Hoeg, Xavier A |  | 213.44
PR | 995 | 02/14/20 | 267 | Hoeg, Xavier A |  | 91.48
PR | 995 | 02/14/20 | 268 | Holmes, Anthony R |  | 447.22
PR | 995 | 02/14/20 | 268 | Holmes, Anthony R |  | 298.14
PR | 995 | 02/14/20 | 312 | Donelson, Richard T |  | 26.47
PR | 995 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 02/21/20 | 456 | Barnhart, Joseph N |  | 68.61
PR | 995 | 02/21/20 | 456 | Barnhart, Joseph N |  | 91.48
PR | 995 | 02/21/20 | 456 | Barnhart, Joseph N |  | 91.48
PR | 995 | 02/21/20 | 482 | Hoeg, Xavier A |  | 182.95
PR | 995 | 02/21/20 | 482 | Hoeg, Xavier A |  | 76.23
PR | 995 | 02/21/20 | 482 | Hoeg, Xavier A |  | 45.74
PR | 995 | 02/21/20 | 483 | Holmes, Anthony R |  | 298.14
PR | 995 | 02/21/20 | 483 | Holmes, Anthony R |  | 186.34
PR | 995 | 02/21/20 | 483 | Holmes, Anthony R |  | 111.8
PR | 995 | 02/21/20 | 528 | Donelson, Richard T |  | 79.41
PR | 995 | 02/21/20 | 529 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 171.52
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 137.21
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 182.95
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 91.48
PR | 995 | 02/28/20 | 684 | Barnhart, Joseph N |  | 45.74
PR | 995 | 02/28/20 | 712 | Hoeg, Xavier A |  | 144.84
PR | 995 | 02/28/20 | 712 | Hoeg, Xavier A |  | 99.1
PR | 995 | 02/28/20 | 713 | Holmes, Anthony R |  | 139.76
PR | 995 | 02/28/20 | 713 | Holmes, Anthony R |  | 503.12
PR | 995 | 02/28/20 | 713 | Holmes, Anthony R |  | 242.24
PR | 995 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 125.36
PR | 995 | 02/28/20 | 728 | Paco Leyva, Orlando |  | 111.8
PR | 995 | 02/28/20 | 728 | Paco Leyva, Orlando |  | 18.63
PR | 995 | 02/28/20 | 732 | Ramos Herrera, Franklin J |  | 63.53
PR | 995 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 73.69
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 228.69
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 22.87
PR | 995 | 03/06/20 | 46 | Barnhart, Joseph N |  | 91.48
PR | 995 | 03/06/20 | 74 | Hoeg, Xavier A |  | 167.71
PR | 995 | 03/06/20 | 74 | Hoeg, Xavier A |  | 38.12
PR | 995 | 03/06/20 | 74 | Hoeg, Xavier A |  | 38.12
PR | 995 | 03/06/20 | 75 | Holmes, Anthony R |  | 279.51
PR | 995 | 03/06/20 | 75 | Holmes, Anthony R |  | 391.31
PR | 995 | 03/06/20 | 75 | Holmes, Anthony R |  | 74.54
PR | 995 | 03/06/20 | 78 | Hubbard, Robert W |  | 45.74
PR | 995 | 03/06/20 | 119 | Donelson, Richard T |  | 105.88
PR | 995 | 03/06/20 | 120 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 68.61
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 45.74
PR | 995 | 03/13/20 | 311 | Barnhart, Joseph N |  | 274.43
PR | 995 | 03/13/20 | 338 | Hoeg, Xavier A |  | 228.69
PR | 995 | 03/13/20 | 338 | Hoeg, Xavier A |  | 76.23
PR | 995 | 03/13/20 | 339 | Holmes, Anthony R |  | 260.88
PR | 995 | 03/13/20 | 339 | Holmes, Anthony R |  | 484.48
PR | 995 | 03/13/20 | 383 | Donelson, Richard T |  | 185.28
PR | 995 | 03/13/20 | 384 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I |  | 533.61
PR | 995 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I |  | 30.49
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 251.56
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 68.61
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 137.21
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 68.61
PR | 995 | 03/20/20 | 569 | Barnhart, Joseph N |  | 160.08
PR | 995 | 03/20/20 | 596 | Hoeg, Xavier A |  | 152.46
PR | 995 | 03/20/20 | 596 | Hoeg, Xavier A |  | 45.74
PR | 995 | 03/20/20 | 596 | Hoeg, Xavier A |  | 106.72
PR | 995 | 03/20/20 | 597 | Holmes, Anthony R |  | 186.34
PR | 995 | 03/20/20 | 597 | Holmes, Anthony R |  | 242.24
PR | 995 | 03/20/20 | 597 | Holmes, Anthony R |  | 316.78
PR | 995 | 03/20/20 | 600 | Hubbard, Robert W |  | 91.48
PR | 995 | 03/20/20 | 622 | Rodriguez Arevalos, Christian |  | 444.68
PR | 995 | 03/20/20 | 622 | Rodriguez Arevalos, Christian |  | 25.41
PR | 995 | 03/20/20 | 632 | Taylor, Evan R |  | 475.17
PR | 995 | 03/20/20 | 632 | Taylor, Evan R |  | 83.85
PR | 995 | 03/20/20 | 638 | Waites, Thaddeus Z |  | 705.55
PR | 995 | 03/20/20 | 638 | Waites, Thaddeus Z |  | 124.51
PR | 995 | 03/20/20 | 641 | Donelson, Richard T |  | 79.41
PR | 995 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 03/26/20 | 748 | Anderson, Richard P |  | 46.69
PR | 995 | 03/26/20 | 748 | Anderson, Richard P |  | 83.01
PR | 995 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I |  | 121.97
PR | 995 | 03/26/20 | 752 | Barnhart, Joseph N |  | 114.35
PR | 995 | 03/26/20 | 778 | Hoeg, Xavier A |  | 106.72
PR | 995 | 03/26/20 | 778 | Hoeg, Xavier A |  | 15.25
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 279.51
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 55.9
PR | 995 | 03/26/20 | 779 | Holmes, Anthony R |  | 74.54
PR | 995 | 03/26/20 | 811 | Taylor, Evan R |  | 223.61
PR | 995 | 03/26/20 | 817 | Waites, Thaddeus Z |  | 332.02
PR | 995 | 03/26/20 | 820 | Donelson, Richard T |  | 52.94
PR | 995 | 03/26/20 | 820 | Donelson, Richard T |  | 26.47
PR | 995 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 04/03/20 | 42 | Donelson, Richard T |  | 52.94
PR | 995 | 04/10/20 | 64 | Barnhart, Joseph N |  | 45.74
PR | 995 | 04/10/20 | 99 | Donelson, Richard T |  | 105.88
PR | 995 | 04/17/20 | 216 | Barnhart, Joseph N |  | 137.21
PR | 995 | 04/17/20 | 288 | Donelson, Richard T |  | 52.94
PR | 995 | 04/24/20 | 352 | Barnhart, Joseph N |  | 68.61
PR | 995 | 05/08/20 | 231 | Donelson, Richard T |  | 26.47
PR | 995 | 06/05/20 | 18 | Barnhart, Joseph N |  | 91.48
PR | 995 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 06/12/20 | 221 | Barnhart, Joseph N |  | 68.61
PR | 995 | 06/26/20 | 521 | Barnhart, Joseph N |  | 91.48
PR | 995 | 06/26/20 | 521 | Barnhart, Joseph N |  | 91.48
PR | 995 | 06/26/20 | 560 | Stahlschmidt, John P |  | 74.54
PR | 995 | 06/26/20 | 563 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 68.61
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 274.43
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 182.95
PR | 995 | 07/02/20 | 7 | Barnhart, Joseph N |  | 45.74
PR | 995 | 07/02/20 | 46 | Stahlschmidt, John P |  | 372.68
PR | 995 | 07/02/20 | 49 | Waites, Thaddeus Z |  | 830.06
PR | 995 | 07/02/20 | 50 | Donelson, Richard T |  | 132.34
PR | 995 | 07/10/20 | 140 | Barnhart, Joseph N |  | 68.61
PR | 995 | 07/10/20 | 175 | Ross, Kelli M |  | 291.37
PR | 995 | 07/10/20 | 178 | Stahlschmidt, John P |  | 74.54
PR | 995 | 07/10/20 | 178 | Stahlschmidt, John P |  | 149.07
PR | 995 | 07/10/20 | 181 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 07/10/20 | 181 | Waites, Thaddeus Z |  | 332.02
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 45.74
PR | 995 | 07/17/20 | 265 | Barnhart, Joseph N |  | 137.21
PR | 995 | 07/17/20 | 305 | Stahlschmidt, John P |  | 74.54
PR | 995 | 07/17/20 | 305 | Stahlschmidt, John P |  | 74.54
PR | 995 | 07/17/20 | 308 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 07/17/20 | 308 | Waites, Thaddeus Z |  | 166.01
PR | 995 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/24/20 | 404 | Barnhart, Joseph N |  | 137.21
PR | 995 | 07/24/20 | 448 | Donelson, Richard T |  | 132.34
PR | 995 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 24.56
PR | 995 | 07/31/20 | 499 | Barnhart, Joseph N |  | 365.9
PR | 995 | 07/31/20 | 543 | Donelson, Richard T |  | 79.41
PR | 995 | 08/07/20 | 128 | Donelson, Richard T |  | 264.69
PR | 995 | 08/14/20 | 332 | Donelson, Richard T |  | 185.28
PR | 995 | 08/21/20 | 459 | Donelson, Richard T |  | 105.88
PR | 995 | 08/28/20 | 604 | Donelson, Richard T |  | 26.47
PR | 995 | 09/04/20 | 49 | Donelson, Richard T |  | 26.47
PR | 995 | 10/09/20 | 198 | Donelson, Richard T |  | 52.94
PR | 995 | 11/13/20 | 189 | Barnhart, Joseph N |  | 89.96
PR | 995 | 11/13/20 | 230 | Donelson, Richard T |  | 78.09
PR | 995 | 12/31/20 | 627 | Donelson, Richard T |  | 26.03
PR | 995 | 01/08/21 | 52 | Donelson, Richard T |  | 26.03
PR | 995 | 01/15/21 | 171 | Donelson, Richard T |  | 52.06
PR | 995 | 01/22/21 | 261 | Barnhart, Joseph N |  | 112.46
PR | 995 | 01/22/21 | 280 | Holmes, Anthony R |  | 384.85
PR | 995 | 01/22/21 | 306 | Donelson, Richard T |  | 52.06
PR | 995 | 01/29/21 | 386 | Barnhart, Joseph N |  | 337.37
PR | 995 | 01/29/21 | 404 | Gonzalez Hernandez, Josue |  | 599.76
PR | 995 | 01/29/21 | 406 | Holmes, Anthony R |  | 733.04
PR | 995 | 01/29/21 | 410 | Lee, Ha Nul |  | 416.5
PR | 995 | 01/29/21 | 421 | Rodriguez Arevalos, Christian |  | 299.88
PR | 995 | 01/29/21 | 431 | Waites, Thaddeus Z |  | 489.8
PR | 995 | 01/29/21 | 432 | Donelson, Richard T |  | 26.03
PR | 995 | 02/05/21 | 71 | Barnhart, Joseph N |  | 112.46
PR | 995 | 02/05/21 | 71 | Barnhart, Joseph N |  | 44.98
PR | 995 | 02/05/21 | 71 | Barnhart, Joseph N |  | 22.49
PR | 995 | 02/05/21 | 90 | Gonzalez Hernandez, Josue |  | 599.76
PR | 995 | 02/05/21 | 91 | Gordillo, Emanuel D |  | 213.25
PR | 995 | 02/05/21 | 91 | Gordillo, Emanuel D |  | 53.31
PR | 995 | 02/05/21 | 93 | Holmes, Anthony R |  | 586.43
PR | 995 | 02/05/21 | 93 | Holmes, Anthony R |  | 146.61
PR | 995 | 02/05/21 | 97 | Lee, Ha Nul |  | 416.5
PR | 995 | 02/05/21 | 109 | Rodriguez Arevalos, Christian |  | 499.8
PR | 995 | 02/05/21 | 119 | Waites, Thaddeus Z |  | 653.07
PR | 995 | 02/05/21 | 121 | Donelson, Richard T |  | 26.03
PR | 995 | 02/12/21 | 256 | Barnhart, Joseph N |  | 134.95
PR | 995 | 02/12/21 | 256 | Barnhart, Joseph N |  | 89.96
PR | 995 | 02/12/21 | 276 | Gonzalez Hernandez, Josue |  | 599.76
PR | 995 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 79.97
PR | 995 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 133.28
PR | 995 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 53.31
PR | 995 | 02/12/21 | 279 | Holmes, Anthony R |  | 586.43
PR | 995 | 02/12/21 | 279 | Holmes, Anthony R |  | 146.61
PR | 995 | 02/12/21 | 283 | Lee, Ha Nul |  | 416.5
PR | 995 | 02/12/21 | 295 | Rodriguez Arevalos, Christian |  | 399.84
PR | 995 | 02/12/21 | 305 | Waites, Thaddeus Z |  | 653.07
PR | 995 | 02/12/21 | 307 | Donelson, Richard T |  | 78.09
PR | 995 | 02/19/21 | 441 | Gonzalez Hernandez, Josue |  | 434.83
PR | 995 | 02/19/21 | 442 | Gordillo, Emanuel D |  | 213.25
PR | 995 | 02/19/21 | 442 | Gordillo, Emanuel D |  | 53.31
PR | 995 | 02/19/21 | 444 | Holmes, Anthony R |  | 586.43
PR | 995 | 02/19/21 | 444 | Holmes, Anthony R |  | 146.61
PR | 995 | 02/19/21 | 448 | Lee, Ha Nul |  | 416.5
PR | 995 | 02/19/21 | 462 | Rodriguez Arevalos, Christian |  | 499.8
PR | 995 | 02/19/21 | 472 | Waites, Thaddeus Z |  | 653.07
PR | 995 | 02/26/21 | 597 | Barnhart, Joseph N |  | 44.98
PR | 995 | 02/26/21 | 618 | Gonzalez Hernandez, Josue |  | 599.76
PR | 995 | 02/26/21 | 619 | Gordillo, Emanuel D |  | 266.56
PR | 995 | 02/26/21 | 621 | Holmes, Anthony R |  | 439.82
PR | 995 | 02/26/21 | 621 | Holmes, Anthony R |  | 293.22
PR | 995 | 02/26/21 | 625 | Lee, Ha Nul |  | 416.5
PR | 995 | 02/26/21 | 648 | Waites, Thaddeus Z |  | 734.71
PR | 995 | 02/26/21 | 648 | Waites, Thaddeus Z |  | 81.63
PR | 995 | 02/26/21 | 649 | Donelson, Richard T |  | 26.03
PR | 995 | 03/05/21 | 76 | Gonzalez Hernandez, Josue |  | 479.81
PR | 995 | 03/05/21 | 77 | Gordillo, Emanuel D |  | 159.94
PR | 995 | 03/05/21 | 77 | Gordillo, Emanuel D |  | 106.62
PR | 995 | 03/05/21 | 79 | Holmes, Anthony R |  | 659.74
PR | 995 | 03/05/21 | 79 | Holmes, Anthony R |  | 73.3
PR | 995 | 03/05/21 | 83 | Lee, Ha Nul |  | 416.5
PR | 995 | 03/05/21 | 106 | Waites, Thaddeus Z |  | 816.34
PR | 995 | 03/12/21 | 201 | Gonzalez Hernandez, Josue |  | 404.84
PR | 995 | 03/12/21 | 201 | Gonzalez Hernandez, Josue |  | 194.92
PR | 995 | 03/12/21 | 202 | Gordillo, Emanuel D |  | 266.56
PR | 995 | 03/12/21 | 205 | Holmes, Anthony R |  | 678.06
PR | 995 | 03/12/21 | 205 | Holmes, Anthony R |  | 54.98
PR | 995 | 03/12/21 | 209 | Lee, Ha Nul |  | 281.14
PR | 995 | 03/12/21 | 209 | Lee, Ha Nul |  | 135.36
PR | 995 | 03/12/21 | 231 | Waites, Thaddeus Z |  | 816.34
PR | 995 | 03/19/21 | 291 | Barnhart, Joseph N |  | 46.65
PR | 995 | 03/19/21 | 291 | Barnhart, Joseph N |  | 69.97
PR | 995 | 03/19/21 | 314 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 03/19/21 | 315 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 03/19/21 | 318 | Holmes, Anthony R |  | 766.36
PR | 995 | 03/19/21 | 322 | Lee, Ha Nul |  | 449.82
PR | 995 | 03/19/21 | 345 | Waites, Thaddeus Z |  | 499.8
PR | 995 | 03/19/21 | 345 | Waites, Thaddeus Z |  | 333.2
PR | 995 | 03/19/21 | 346 | Donelson, Richard T |  | 26.03
PR | 995 | 03/26/21 | 545 | Gonzalez Hernandez, Josue |  | 506.46
PR | 995 | 03/26/21 | 546 | Gordillo, Emanuel D |  | 247.82
PR | 995 | 03/26/21 | 546 | Gordillo, Emanuel D |  | 35.4
PR | 995 | 03/26/21 | 549 | Holmes, Anthony R |  | 766.36
PR | 995 | 03/26/21 | 553 | Lee, Ha Nul |  | 427.33
PR | 995 | 03/26/21 | 577 | Waites, Thaddeus Z |  | 833
PR | 995 | 04/02/21 | 7 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/02/21 | 7 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/02/21 | 30 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 04/02/21 | 31 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 04/02/21 | 34 | Holmes, Anthony R |  | 364.02
PR | 995 | 04/02/21 | 34 | Holmes, Anthony R |  | 402.34
PR | 995 | 04/02/21 | 38 | Lee, Ha Nul |  | 449.82
PR | 995 | 04/02/21 | 62 | Waites, Thaddeus Z |  | 145.78
PR | 995 | 04/02/21 | 62 | Waites, Thaddeus Z |  | 20.83
PR | 995 | 04/02/21 | 64 | Donelson, Richard T |  | 26.03
PR | 995 | 04/09/21 | 134 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 148.69
PR | 995 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 127.45
PR | 995 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 7.08
PR | 995 | 04/09/21 | 138 | Holmes, Anthony R |  | 402.34
PR | 995 | 04/09/21 | 138 | Holmes, Anthony R |  | 344.86
PR | 995 | 04/09/21 | 138 | Holmes, Anthony R |  | 19.16
PR | 995 | 04/09/21 | 142 | Lee, Ha Nul |  | 449.82
PR | 995 | 04/09/21 | 167 | Donelson, Richard T |  | 130.16
PR | 995 | 04/16/21 | 278 | Gonzalez Hernandez, Josue |  | 506.46
PR | 995 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 56.64
PR | 995 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 134.53
PR | 995 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 92.05
PR | 995 | 04/16/21 | 284 | Holmes, Anthony R |  | 325.7
PR | 995 | 04/16/21 | 284 | Holmes, Anthony R |  | 134.11
PR | 995 | 04/16/21 | 284 | Holmes, Anthony R |  | 191.59
PR | 995 | 04/16/21 | 284 | Holmes, Anthony R |  | 19.16
PR | 995 | 04/16/21 | 284 | Holmes, Anthony R |  | 95.8
PR | 995 | 04/16/21 | 287 | Lee, Ha Nul |  | 449.82
PR | 995 | 04/16/21 | 290 | Lovo, German G |  | 439.82
PR | 995 | 04/16/21 | 310 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 04/16/21 | 311 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 04/16/21 | 314 | Donelson, Richard T |  | 208.25
PR | 995 | 04/16/21 | 314 | Donelson, Richard T |  | 52.06
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 69.97
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 23.32
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 23.32
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/23/21 | 404 | Barnhart, Joseph N |  | 23.32
PR | 995 | 04/23/21 | 429 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 04/23/21 | 430 | Gordillo, Emanuel D |  | 226.58
PR | 995 | 04/23/21 | 430 | Gordillo, Emanuel D |  | 56.64
PR | 995 | 04/23/21 | 432 | Gutierrez, Brian A |  | 173.26
PR | 995 | 04/23/21 | 436 | Holmes, Anthony R |  | 747.2
PR | 995 | 04/23/21 | 436 | Holmes, Anthony R |  | 19.16
PR | 995 | 04/23/21 | 439 | Lee, Ha Nul |  | 269.89
PR | 995 | 04/23/21 | 439 | Lee, Ha Nul |  | 179.93
PR | 995 | 04/23/21 | 441 | Lovo, German G |  | 549.78
PR | 995 | 04/23/21 | 449 | Platero Navas, Julio A |  | 179.93
PR | 995 | 04/23/21 | 463 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 04/23/21 | 464 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 04/23/21 | 466 | Donelson, Richard T |  | 52.06
PR | 995 | 04/30/21 | 574 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/30/21 | 574 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/30/21 | 574 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/30/21 | 574 | Barnhart, Joseph N |  | 46.65
PR | 995 | 04/30/21 | 599 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 04/30/21 | 600 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 04/30/21 | 606 | Holmes, Anthony R |  | 728.04
PR | 995 | 04/30/21 | 606 | Holmes, Anthony R |  | 38.32
PR | 995 | 04/30/21 | 609 | Lee, Ha Nul |  | 449.82
PR | 995 | 04/30/21 | 611 | Lovo, German G |  | 549.78
PR | 995 | 04/30/21 | 620 | Platero Navas, Julio A |  | 299.88
PR | 995 | 04/30/21 | 634 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 04/30/21 | 635 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 04/30/21 | 637 | Donelson, Richard T |  | 104.13
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 69.97
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 93.3
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/07/21 | 41 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/07/21 | 66 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 05/07/21 | 67 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 05/07/21 | 73 | Holmes, Anthony R |  | 766.36
PR | 995 | 05/07/21 | 77 | Lee, Ha Nul |  | 449.82
PR | 995 | 05/07/21 | 79 | Lovo, German G |  | 439.82
PR | 995 | 05/07/21 | 88 | Platero Navas, Julio A |  | 299.88
PR | 995 | 05/07/21 | 102 | Velasquez Cruz, Denis M |  | 493.14
PR | 995 | 05/07/21 | 103 | Velasquez Cruz, Osman N |  | 426.5
PR | 995 | 05/07/21 | 106 | Donelson, Richard T |  | 208.25
PR | 995 | 05/14/21 | 246 | Barnhart, Joseph N |  | 116.62
PR | 995 | 05/14/21 | 246 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/14/21 | 246 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/14/21 | 246 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/14/21 | 270 | Gonzalez Hernandez, Josue |  | 332.37
PR | 995 | 05/14/21 | 270 | Gonzalez Hernandez, Josue |  | 110.79
PR | 995 | 05/14/21 | 271 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 05/14/21 | 276 | Holmes, Anthony R |  | 689.72
PR | 995 | 05/14/21 | 276 | Holmes, Anthony R |  | 57.48
PR | 995 | 05/14/21 | 276 | Holmes, Anthony R |  | 19.16
PR | 995 | 05/14/21 | 278 | Hubbard, Robert W |  | 297.8
PR | 995 | 05/14/21 | 280 | Lee, Ha Nul |  | 438.57
PR | 995 | 05/14/21 | 280 | Lee, Ha Nul |  | 11.25
PR | 995 | 05/14/21 | 283 | Lovo, German G |  | 549.78
PR | 995 | 05/14/21 | 292 | Platero Navas, Julio A |  | 179.93
PR | 995 | 05/14/21 | 292 | Platero Navas, Julio A |  | 119.95
PR | 995 | 05/14/21 | 306 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 05/14/21 | 307 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 05/14/21 | 310 | Donelson, Richard T |  | 78.09
PR | 995 | 05/21/21 | 391 | Barnhart, Joseph N |  | 139.94
PR | 995 | 05/21/21 | 391 | Barnhart, Joseph N |  | 69.97
PR | 995 | 05/21/21 | 391 | Barnhart, Joseph N |  | 23.32
PR | 995 | 05/21/21 | 415 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 05/21/21 | 416 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 05/21/21 | 422 | Holmes, Anthony R |  | 766.36
PR | 995 | 05/21/21 | 426 | Lee, Ha Nul |  | 449.82
PR | 995 | 05/21/21 | 429 | Lovo, German G |  | 439.82
PR | 995 | 05/21/21 | 438 | Platero Navas, Julio A |  | 299.88
PR | 995 | 05/21/21 | 452 | Velasquez Cruz, Denis M |  | 493.14
PR | 995 | 05/21/21 | 453 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 05/21/21 | 456 | Donelson, Richard T |  | 52.06
PR | 995 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 506.46
PR | 995 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 110.79
PR | 995 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 15.83
PR | 995 | 05/28/21 | 657 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 05/28/21 | 663 | Holmes, Anthony R |  | 728.04
PR | 995 | 05/28/21 | 663 | Holmes, Anthony R |  | 19.16
PR | 995 | 05/28/21 | 663 | Holmes, Anthony R |  | 19.16
PR | 995 | 05/28/21 | 665 | Hubbard, Robert W |  | 114.54
PR | 995 | 05/28/21 | 665 | Hubbard, Robert W |  | 68.72
PR | 995 | 05/28/21 | 667 | Lee, Ha Nul |  | 269.89
PR | 995 | 05/28/21 | 667 | Lee, Ha Nul |  | 179.93
PR | 995 | 05/28/21 | 670 | Lovo, German G |  | 549.78
PR | 995 | 05/28/21 | 680 | Platero Navas, Julio A |  | 239.9
PR | 995 | 05/28/21 | 680 | Platero Navas, Julio A |  | 52.48
PR | 995 | 05/28/21 | 680 | Platero Navas, Julio A |  | 7.5
PR | 995 | 05/28/21 | 681 | Platero Navas, Mario N |  | 113.29
PR | 995 | 05/28/21 | 695 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 05/28/21 | 696 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 05/28/21 | 700 | Donelson, Richard T |  | 26.03
PR | 995 | 06/04/21 | 56 | Gonzalez Hernandez, Josue |  | 506.46
PR | 995 | 06/04/21 | 57 | Gordillo, Emanuel D |  | 226.58
PR | 995 | 06/04/21 | 63 | Holmes, Anthony R |  | 613.09
PR | 995 | 06/04/21 | 67 | Lee, Ha Nul |  | 247.4
PR | 995 | 06/04/21 | 67 | Lee, Ha Nul |  | 112.46
PR | 995 | 06/04/21 | 70 | Lovo, German G |  | 329.87
PR | 995 | 06/04/21 | 81 | Platero Navas, Julio A |  | 239.9
PR | 995 | 06/04/21 | 82 | Platero Navas, Mario N |  | 226.58
PR | 995 | 06/04/21 | 95 | Velasquez Cruz, Denis M |  | 369.85
PR | 995 | 06/04/21 | 96 | Velasquez Cruz, Osman N |  | 319.87
PR | 995 | 06/04/21 | 99 | Donelson, Richard T |  | 104.13
PR | 995 | 06/11/21 | 203 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/11/21 | 203 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/11/21 | 203 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/11/21 | 203 | Barnhart, Joseph N |  | 23.32
PR | 995 | 06/11/21 | 213 | Cruz, Azael S |  | 269.89
PR | 995 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 126.62
PR | 995 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 221.58
PR | 995 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 31.65
PR | 995 | 06/11/21 | 230 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 06/11/21 | 236 | Holmes, Anthony R |  | 191.59
PR | 995 | 06/11/21 | 236 | Holmes, Anthony R |  | 517.29
PR | 995 | 06/11/21 | 236 | Holmes, Anthony R |  | 57.48
PR | 995 | 06/11/21 | 238 | Hubbard, Robert W |  | 366.52
PR | 995 | 06/11/21 | 240 | Lee, Ha Nul |  | 449.82
PR | 995 | 06/11/21 | 243 | Lovo, German G |  | 549.78
PR | 995 | 06/11/21 | 250 | Ortiz Carmona, Jose |  | 319.87
PR | 995 | 06/11/21 | 253 | Platero Navas, Julio A |  | 299.88
PR | 995 | 06/11/21 | 254 | Platero Navas, Mario N |  | 226.58
PR | 995 | 06/11/21 | 267 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 06/11/21 | 268 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 06/11/21 | 270 | Donelson, Richard T |  | 208.25
PR | 995 | 06/11/21 | 271 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 06/18/21 | 410 | Castro Hernandez, Jose A |  | 146.61
PR | 995 | 06/18/21 | 415 | Cruz, Azael S |  | 449.82
PR | 995 | 06/18/21 | 431 | Gonzalez Hernandez, Josue |  | 379.85
PR | 995 | 06/18/21 | 432 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 06/18/21 | 438 | Holmes, Anthony R |  | 536.45
PR | 995 | 06/18/21 | 438 | Holmes, Anthony R |  | 229.91
PR | 995 | 06/18/21 | 440 | Hubbard, Robert W |  | 274.89
PR | 995 | 06/18/21 | 442 | Lee, Ha Nul |  | 427.33
PR | 995 | 06/18/21 | 442 | Lee, Ha Nul |  | 22.49
PR | 995 | 06/18/21 | 445 | Lovo, German G |  | 549.78
PR | 995 | 06/18/21 | 452 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 06/18/21 | 455 | Platero Navas, Julio A |  | 299.88
PR | 995 | 06/18/21 | 456 | Platero Navas, Mario N |  | 283.22
PR | 995 | 06/18/21 | 471 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 06/18/21 | 472 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 06/18/21 | 475 | Donelson, Richard T |  | 130.16
PR | 995 | 06/25/21 | 610 | Cruz, Azael S |  | 449.82
PR | 995 | 06/25/21 | 626 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 06/25/21 | 626 | Gonzalez Hernandez, Josue |  | 379.85
PR | 995 | 06/25/21 | 627 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 06/25/21 | 629 | Gutierrez, Brian A |  | 119.12
PR | 995 | 06/25/21 | 633 | Holmes, Anthony R |  | 210.75
PR | 995 | 06/25/21 | 633 | Holmes, Anthony R |  | 555.61
PR | 995 | 06/25/21 | 635 | Hubbard, Robert W |  | 229.08
PR | 995 | 06/25/21 | 635 | Hubbard, Robert W |  | 91.63
PR | 995 | 06/25/21 | 637 | Lee, Ha Nul |  | 359.86
PR | 995 | 06/25/21 | 637 | Lee, Ha Nul |  | 89.96
PR | 995 | 06/25/21 | 640 | Lovo, German G |  | 549.78
PR | 995 | 06/25/21 | 647 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 06/25/21 | 650 | Platero Navas, Julio A |  | 119.95
PR | 995 | 06/25/21 | 650 | Platero Navas, Julio A |  | 179.93
PR | 995 | 06/25/21 | 651 | Platero Navas, Mario N |  | 283.22
PR | 995 | 06/25/21 | 666 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 06/25/21 | 667 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 06/25/21 | 669 | Gutierrez, Brian A |  | -119.12
PR | 995 | 06/25/21 | 670 | Hubbard, Robert W |  | 45.82
PR | 995 | 06/25/21 | 672 | Donelson, Richard T |  | 26.03
PR | 995 | 07/02/21 | 19 | Cruz, Azael S |  | 399.22
PR | 995 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 87.05
PR | 995 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 253.23
PR | 995 | 07/02/21 | 36 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 07/02/21 | 40 | Holmes, Anthony R |  | 517.29
PR | 995 | 07/02/21 | 40 | Holmes, Anthony R |  | 249.07
PR | 995 | 07/02/21 | 42 | Hubbard, Robert W |  | 206.17
PR | 995 | 07/02/21 | 42 | Hubbard, Robert W |  | 57.27
PR | 995 | 07/02/21 | 44 | Lee, Ha Nul |  | 331.74
PR | 995 | 07/02/21 | 44 | Lee, Ha Nul |  | 67.47
PR | 995 | 07/02/21 | 47 | Lovo, German G |  | 439.82
PR | 995 | 07/02/21 | 55 | Ortiz Carmona, Jose |  | 206.58
PR | 995 | 07/02/21 | 55 | Ortiz Carmona, Jose |  | 266.56
PR | 995 | 07/02/21 | 58 | Platero Navas, Julio A |  | 161.19
PR | 995 | 07/02/21 | 58 | Platero Navas, Julio A |  | 119.95
PR | 995 | 07/02/21 | 59 | Platero Navas, Mario N |  | 265.52
PR | 995 | 07/02/21 | 74 | Velasquez Cruz, Denis M |  | 547.07
PR | 995 | 07/02/21 | 75 | Velasquez Cruz, Osman N |  | 473.14
PR | 995 | 07/02/21 | 78 | Donelson, Richard T |  | 52.06
PR | 995 | 07/09/21 | 114 | Cruz, Azael S |  | 337.37
PR | 995 | 07/09/21 | 130 | Gonzalez Hernandez, Josue |  | 110.79
PR | 995 | 07/09/21 | 130 | Gonzalez Hernandez, Josue |  | 379.85
PR | 995 | 07/09/21 | 131 | Gordillo, Emanuel D |  | 198.25
PR | 995 | 07/09/21 | 135 | Holmes, Anthony R |  | 459.82
PR | 995 | 07/09/21 | 135 | Holmes, Anthony R |  | 76.64
PR | 995 | 07/09/21 | 137 | Hubbard, Robert W |  | 274.89
PR | 995 | 07/09/21 | 137 | Hubbard, Robert W |  | 91.63
PR | 995 | 07/09/21 | 139 | Lee, Ha Nul |  | 224.91
PR | 995 | 07/09/21 | 142 | Lovo, German G |  | 439.82
PR | 995 | 07/09/21 | 150 | Ortiz Carmona, Jose |  | 399.84
PR | 995 | 07/09/21 | 153 | Platero Navas, Julio A |  | 239.9
PR | 995 | 07/09/21 | 154 | Platero Navas, Mario N |  | 226.58
PR | 995 | 07/09/21 | 165 | Sepulveda Gonzalez, Alfredo |  | 562.28
PR | 995 | 07/09/21 | 171 | Velasquez Cruz, Denis M |  | 462.32
PR | 995 | 07/09/21 | 172 | Velasquez Cruz, Osman N |  | 399.84
PR | 995 | 07/16/21 | 322 | Barnhart, Joseph N |  | 46.65
PR | 995 | 07/16/21 | 322 | Barnhart, Joseph N |  | 46.65
PR | 995 | 07/16/21 | 322 | Barnhart, Joseph N |  | 46.65
PR | 995 | 07/16/21 | 322 | Barnhart, Joseph N |  | 46.65
PR | 995 | 07/16/21 | 332 | Cruz, Azael S |  | 449.82
PR | 995 | 07/16/21 | 348 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 07/16/21 | 353 | Holmes, Anthony R |  | 766.36
PR | 995 | 07/16/21 | 357 | Lee, Ha Nul |  | 449.82
PR | 995 | 07/16/21 | 360 | Lovo, German G |  | 549.78
PR | 995 | 07/16/21 | 368 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 07/16/21 | 371 | Platero Navas, Julio A |  | 299.88
PR | 995 | 07/16/21 | 372 | Platero Navas, Mario N |  | 169.93
PR | 995 | 07/16/21 | 372 | Platero Navas, Mario N |  | 113.29
PR | 995 | 07/16/21 | 383 | Sepulveda Gonzalez, Alfredo |  | 665.36
PR | 995 | 07/16/21 | 389 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 07/16/21 | 390 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 07/16/21 | 393 | Donelson, Richard T |  | 104.13
PR | 995 | 07/23/21 | 493 | Barnhart, Joseph N |  | 69.97
PR | 995 | 07/23/21 | 493 | Barnhart, Joseph N |  | 93.3
PR | 995 | 07/23/21 | 503 | Cruz, Azael S |  | 449.82
PR | 995 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 506.46
PR | 995 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 63.31
PR | 995 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 63.31
PR | 995 | 07/23/21 | 520 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 07/23/21 | 524 | Holmes, Anthony R |  | 766.36
PR | 995 | 07/23/21 | 527 | Hubbard, Robert W |  | 68.72
PR | 995 | 07/23/21 | 527 | Hubbard, Robert W |  | 68.72
PR | 995 | 07/23/21 | 529 | Lee, Ha Nul |  | 337.37
PR | 995 | 07/23/21 | 529 | Lee, Ha Nul |  | 112.46
PR | 995 | 07/23/21 | 532 | Lovo, German G |  | 439.82
PR | 995 | 07/23/21 | 540 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 07/23/21 | 543 | Platero Navas, Julio A |  | 299.88
PR | 995 | 07/23/21 | 544 | Platero Navas, Mario N |  | 283.22
PR | 995 | 07/23/21 | 555 | Sepulveda Gonzalez, Alfredo |  | 187.43
PR | 995 | 07/23/21 | 561 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 07/23/21 | 562 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 07/23/21 | 565 | Donelson, Richard T |  | 52.06
PR | 995 | 07/30/21 | 684 | Barnhart, Joseph N |  | 233.24
PR | 995 | 07/30/21 | 684 | Barnhart, Joseph N |  | 93.3
PR | 995 | 07/30/21 | 684 | Barnhart, Joseph N |  | 46.65
PR | 995 | 07/30/21 | 695 | Cruz, Azael S |  | 449.82
PR | 995 | 07/30/21 | 711 | Gonzalez Hernandez, Josue |  | 585.6
PR | 995 | 07/30/21 | 712 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 07/30/21 | 717 | Holmes, Anthony R |  | 766.36
PR | 995 | 07/30/21 | 722 | Lee, Ha Nul |  | 449.82
PR | 995 | 07/30/21 | 725 | Lovo, German G |  | 549.78
PR | 995 | 07/30/21 | 733 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 07/30/21 | 736 | Platero Navas, Julio A |  | 299.88
PR | 995 | 07/30/21 | 737 | Platero Navas, Mario N |  | 283.22
PR | 995 | 07/30/21 | 753 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 07/30/21 | 754 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 08/06/21 | 55 | Cruz, Azael S |  | 449.82
PR | 995 | 08/06/21 | 71 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 08/06/21 | 76 | Holmes, Anthony R |  | 766.36
PR | 995 | 08/06/21 | 79 | Hubbard, Robert W |  | 68.72
PR | 995 | 08/06/21 | 79 | Hubbard, Robert W |  | 91.63
PR | 995 | 08/06/21 | 79 | Hubbard, Robert W |  | 91.63
PR | 995 | 08/06/21 | 81 | Lee, Ha Nul |  | 449.82
PR | 995 | 08/06/21 | 84 | Lovo, German G |  | 549.78
PR | 995 | 08/06/21 | 92 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 08/06/21 | 95 | Platero Navas, Julio A |  | 299.88
PR | 995 | 08/06/21 | 96 | Platero Navas, Mario N |  | 283.22
PR | 995 | 08/06/21 | 112 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 08/06/21 | 113 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 08/06/21 | 116 | Donelson, Richard T |  | 52.06
PR | 995 | 08/13/21 | 317 | Cruz, Azael S |  | 449.82
PR | 995 | 08/13/21 | 333 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 08/13/21 | 338 | Holmes, Anthony R |  | 689.72
PR | 995 | 08/13/21 | 338 | Holmes, Anthony R |  | 76.64
PR | 995 | 08/13/21 | 341 | Hubbard, Robert W |  | 183.26
PR | 995 | 08/13/21 | 343 | Lee, Ha Nul |  | 539.78
PR | 995 | 08/13/21 | 346 | Lovo, German G |  | 357.36
PR | 995 | 08/13/21 | 346 | Lovo, German G |  | 82.47
PR | 995 | 08/13/21 | 354 | Ortiz Carmona, Jose |  | 373.18
PR | 995 | 08/13/21 | 357 | Platero Navas, Julio A |  | 239.9
PR | 995 | 08/13/21 | 357 | Platero Navas, Julio A |  | 59.98
PR | 995 | 08/13/21 | 358 | Platero Navas, Mario N |  | 254.9
PR | 995 | 08/13/21 | 358 | Platero Navas, Mario N |  | 28.32
PR | 995 | 08/13/21 | 373 | Velasquez Cruz, Denis M |  | 462.32
PR | 995 | 08/13/21 | 374 | Velasquez Cruz, Osman N |  | 319.87
PR | 995 | 08/13/21 | 374 | Velasquez Cruz, Osman N |  | 79.97
PR | 995 | 08/20/21 | 587 | Barnhart, Joseph N |  | 163.27
PR | 995 | 08/20/21 | 587 | Barnhart, Joseph N |  | 46.65
PR | 995 | 08/20/21 | 587 | Barnhart, Joseph N |  | 23.32
PR | 995 | 08/20/21 | 598 | Cruz, Azael S |  | 449.82
PR | 995 | 08/20/21 | 615 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 08/20/21 | 617 | Gutierrez, Brian A |  | 276.14
PR | 995 | 08/20/21 | 620 | Holmes, Anthony R |  | 191.59
PR | 995 | 08/20/21 | 620 | Holmes, Anthony R |  | 574.77
PR | 995 | 08/20/21 | 626 | Lee, Ha Nul |  | 112.46
PR | 995 | 08/20/21 | 626 | Lee, Ha Nul |  | 286.76
PR | 995 | 08/20/21 | 629 | Lovo, German G |  | 384.85
PR | 995 | 08/20/21 | 629 | Lovo, German G |  | 164.93
PR | 995 | 08/20/21 | 637 | Ortiz Carmona, Jose |  | 533.12
PR | 995 | 08/20/21 | 640 | Platero Navas, Julio A |  | 251.15
PR | 995 | 08/20/21 | 641 | Platero Navas, Mario N |  | 169.93
PR | 995 | 08/20/21 | 641 | Platero Navas, Mario N |  | 113.29
PR | 995 | 08/20/21 | 656 | Velasquez Cruz, Denis M |  | 154.11
PR | 995 | 08/20/21 | 656 | Velasquez Cruz, Denis M |  | 308.21
PR | 995 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 133.28
PR | 995 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 266.56
PR | 995 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 133.28
PR | 995 | 08/20/21 | 661 | Donelson, Richard T |  | 26.03
PR | 995 | 08/27/21 | 807 | Barnhart, Joseph N |  | 209.92
PR | 995 | 08/27/21 | 807 | Barnhart, Joseph N |  | 46.65
PR | 995 | 08/27/21 | 807 | Barnhart, Joseph N |  | 163.27
PR | 995 | 08/27/21 | 807 | Barnhart, Joseph N |  | 23.32
PR | 995 | 08/27/21 | 819 | Cruz, Azael S |  | 449.82
PR | 995 | 08/27/21 | 836 | Gordillo, Emanuel D |  | 283.22
PR | 995 | 08/27/21 | 838 | Gutierrez, Brian A |  | 226.58
PR | 995 | 08/27/21 | 841 | Holmes, Anthony R |  | 670.57
PR | 995 | 08/27/21 | 841 | Holmes, Anthony R |  | 95.8
PR | 995 | 08/27/21 | 849 | Lovo, German G |  | 329.87
PR | 995 | 08/27/21 | 857 | Ortiz Carmona, Jose |  | 266.56
PR | 995 | 08/27/21 | 857 | Ortiz Carmona, Jose |  | 266.56
PR | 995 | 08/27/21 | 860 | Platero Navas, Julio A |  | 251.15
PR | 995 | 08/27/21 | 861 | Platero Navas, Mario N |  | 283.22
PR | 995 | 08/27/21 | 877 | Velasquez Cruz, Denis M |  | 462.32
PR | 995 | 08/27/21 | 877 | Velasquez Cruz, Denis M |  | 154.11
PR | 995 | 08/27/21 | 878 | Velasquez Cruz, Osman N |  | 133.28
PR | 995 | 08/27/21 | 878 | Velasquez Cruz, Osman N |  | 133.28
PR | 995 | 09/03/21 | 8 | Barnhart, Joseph N |  | 326.54
PR | 995 | 09/03/21 | 8 | Barnhart, Joseph N |  | 116.62
PR | 995 | 09/03/21 | 20 | Cruz, Azael S |  | 337.37
PR | 995 | 09/03/21 | 20 | Cruz, Azael S |  | 112.46
PR | 995 | 09/03/21 | 38 | Gordillo, Emanuel D |  | 141.61
PR | 995 | 09/03/21 | 40 | Gutierrez, Brian A |  | 113.29
PR | 995 | 09/03/21 | 43 | Holmes, Anthony R |  | 383.18
PR | 995 | 09/03/21 | 46 | Hubbard, Robert W |  | 183.26
PR | 995 | 09/03/21 | 51 | Lovo, German G |  | 549.78
PR | 995 | 09/03/21 | 59 | Ortiz Carmona, Jose |  | 399.84
PR | 995 | 09/03/21 | 59 | Ortiz Carmona, Jose |  | 133.28
PR | 995 | 09/03/21 | 62 | Platero Navas, Julio A |  | 239.9
PR | 995 | 09/03/21 | 62 | Platero Navas, Julio A |  | 59.98
PR | 995 | 09/03/21 | 63 | Platero Navas, Mario N |  | 169.93
PR | 995 | 09/03/21 | 63 | Platero Navas, Mario N |  | 113.29
PR | 995 | 09/03/21 | 80 | Velasquez Cruz, Denis M |  | 616.42
PR | 995 | 09/03/21 | 81 | Velasquez Cruz, Osman N |  | 533.12
PR | 995 | 09/03/21 | 87 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 09/10/21 | 188 | Cruz, Azael S |  | 349.86
PR | 995 | 09/10/21 | 206 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 09/10/21 | 208 | Gutierrez, Brian A |  | 63.72
PR | 995 | 09/10/21 | 211 | Holmes, Anthony R |  | 799.68
PR | 995 | 09/10/21 | 219 | Lovo, German G |  | 233.24
PR | 995 | 09/10/21 | 227 | Ortiz Carmona, Jose |  | 274.89
PR | 995 | 09/10/21 | 227 | Ortiz Carmona, Jose |  | 137.45
PR | 995 | 09/10/21 | 231 | Platero Navas, Julio A |  | 253.23
PR | 995 | 09/10/21 | 232 | Platero Navas, Mario N |  | 239.9
PR | 995 | 09/10/21 | 249 | Velasquez Cruz, Denis M |  | 487.31
PR | 995 | 09/10/21 | 250 | Velasquez Cruz, Osman N |  | 424.83
PR | 995 | 09/17/21 | 338 | Barnhart, Joseph N |  | 72.47
PR | 995 | 09/17/21 | 338 | Barnhart, Joseph N |  | 24.16
PR | 995 | 09/17/21 | 338 | Barnhart, Joseph N |  | 24.16
PR | 995 | 09/17/21 | 338 | Barnhart, Joseph N |  | 144.94
PR | 995 | 09/17/21 | 350 | Cruz, Azael S |  | 466.48
PR | 995 | 09/17/21 | 368 | Gordillo, Emanuel D |  | 94.96
PR | 995 | 09/17/21 | 368 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 09/17/21 | 373 | Holmes, Anthony R |  | 239.9
PR | 995 | 09/17/21 | 373 | Holmes, Anthony R |  | 779.69
PR | 995 | 09/17/21 | 373 | Holmes, Anthony R |  | 19.99
PR | 995 | 09/17/21 | 381 | Lovo, German G |  | 21.87
PR | 995 | 09/17/21 | 381 | Lovo, German G |  | 583.1
PR | 995 | 09/17/21 | 389 | Ortiz Carmona, Jose |  | 549.78
PR | 995 | 09/17/21 | 393 | Platero Navas, Julio A |  | 11.87
PR | 995 | 09/17/21 | 393 | Platero Navas, Julio A |  | 316.54
PR | 995 | 09/17/21 | 394 | Platero Navas, Mario N |  | 11.25
PR | 995 | 09/17/21 | 394 | Platero Navas, Mario N |  | 299.88
PR | 995 | 09/17/21 | 411 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 09/17/21 | 411 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 09/17/21 | 412 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 09/17/21 | 412 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 09/24/21 | 492 | Barnhart, Joseph N |  | 72.47
PR | 995 | 09/24/21 | 492 | Barnhart, Joseph N |  | 265.73
PR | 995 | 09/24/21 | 492 | Barnhart, Joseph N |  | 48.31
PR | 995 | 09/24/21 | 504 | Cruz, Azael S |  | 122.45
PR | 995 | 09/24/21 | 504 | Cruz, Azael S |  | 349.86
PR | 995 | 09/24/21 | 504 | Cruz, Azael S |  | 116.62
PR | 995 | 09/24/21 | 522 | Gordillo, Emanuel D |  | 94.96
PR | 995 | 09/24/21 | 522 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 09/24/21 | 527 | Holmes, Anthony R |  | 239.9
PR | 995 | 09/24/21 | 527 | Holmes, Anthony R |  | 799.68
PR | 995 | 09/24/21 | 535 | Lovo, German G |  | 131.2
PR | 995 | 09/24/21 | 535 | Lovo, German G |  | 583.1
PR | 995 | 09/24/21 | 543 | Ortiz Carmona, Jose |  | 144.32
PR | 995 | 09/24/21 | 543 | Ortiz Carmona, Jose |  | 549.78
PR | 995 | 09/24/21 | 547 | Platero Navas, Julio A |  | 300.71
PR | 995 | 09/24/21 | 548 | Platero Navas, Mario N |  | 74.97
PR | 995 | 09/24/21 | 566 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 09/24/21 | 566 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 09/24/21 | 567 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 09/24/21 | 567 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 09/24/21 | 572 | Donelson, Richard T |  | 26.03
PR | 995 | 09/24/21 | 573 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 10/01/21 | 9 | Barnhart, Joseph N |  | 362.36
PR | 995 | 10/01/21 | 9 | Barnhart, Joseph N |  | 241.57
PR | 995 | 10/01/21 | 9 | Barnhart, Joseph N |  | 24.16
PR | 995 | 10/01/21 | 16 | Castro Urena, Yanely |  | 159.31
PR | 995 | 10/01/21 | 16 | Castro Urena, Yanely |  | 283.22
PR | 995 | 10/01/21 | 21 | Cruz, Azael S |  | 466.48
PR | 995 | 10/01/21 | 38 | Gonzalez Hernandez, Josue |  | 499.8
PR | 995 | 10/01/21 | 39 | Gordillo, Emanuel D |  | 189.92
PR | 995 | 10/01/21 | 39 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 10/01/21 | 41 | Gutierrez, Brian A |  | 113.7
PR | 995 | 10/01/21 | 41 | Gutierrez, Brian A |  | 433.16
PR | 995 | 10/01/21 | 43 | Hernandez Gonzalez, Osbaldo |  | 291.55
PR | 995 | 10/01/21 | 44 | Holmes, Anthony R |  | 479.81
PR | 995 | 10/01/21 | 44 | Holmes, Anthony R |  | 799.68
PR | 995 | 10/01/21 | 50 | Lara, Eric E |  | 124.95
PR | 995 | 10/01/21 | 53 | Lovo, German G |  | 131.2
PR | 995 | 10/01/21 | 53 | Lovo, German G |  | 583.1
PR | 995 | 10/01/21 | 60 | Ortiz Carmona, Jose |  | 412.34
PR | 995 | 10/01/21 | 60 | Ortiz Carmona, Jose |  | 137.45
PR | 995 | 10/01/21 | 64 | Platero Navas, Julio A |  | 71.22
PR | 995 | 10/01/21 | 64 | Platero Navas, Julio A |  | 316.54
PR | 995 | 10/01/21 | 65 | Platero Navas, Mario N |  | 67.47
PR | 995 | 10/01/21 | 65 | Platero Navas, Mario N |  | 299.88
PR | 995 | 10/01/21 | 78 | Stahlschmidt, John P |  | 97.46
PR | 995 | 10/01/21 | 78 | Stahlschmidt, John P |  | 346.53
PR | 995 | 10/01/21 | 82 | Vazquez Popoca, Jose N |  | 101.21
PR | 995 | 10/01/21 | 82 | Vazquez Popoca, Jose N |  | 269.89
PR | 995 | 10/01/21 | 83 | Velasquez Cruz, Denis M |  | 365.48
PR | 995 | 10/01/21 | 83 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 10/01/21 | 84 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 10/01/21 | 84 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 10/08/21 | 297 | Barnhart, Joseph N |  | 338.2
PR | 995 | 10/08/21 | 297 | Barnhart, Joseph N |  | 48.31
PR | 995 | 10/08/21 | 305 | Castro Urena, Yanely |  | 261.98
PR | 995 | 10/08/21 | 310 | Cruz, Azael S |  | 122.45
PR | 995 | 10/08/21 | 310 | Cruz, Azael S |  | 466.48
PR | 995 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 199.92
PR | 995 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 416.5
PR | 995 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 249.9
PR | 995 | 10/08/21 | 331 | Gordillo, Emanuel D |  | 189.92
PR | 995 | 10/08/21 | 331 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 10/08/21 | 333 | Gutierrez, Brian A |  | 139.94
PR | 995 | 10/08/21 | 333 | Gutierrez, Brian A |  | 466.48
PR | 995 | 10/08/21 | 336 | Holmes, Anthony R |  | 479.81
PR | 995 | 10/08/21 | 336 | Holmes, Anthony R |  | 779.69
PR | 995 | 10/08/21 | 336 | Holmes, Anthony R |  | 19.99
PR | 995 | 10/08/21 | 342 | Lara, Eric E |  | 290.51
PR | 995 | 10/08/21 | 342 | Lara, Eric E |  | 499.8
PR | 995 | 10/08/21 | 345 | Lovo, German G |  | 43.73
PR | 995 | 10/08/21 | 345 | Lovo, German G |  | 583.1
PR | 995 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 144.32
PR | 995 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 137.45
PR | 995 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 412.34
PR | 995 | 10/08/21 | 357 | Platero Navas, Julio A |  | 142.44
PR | 995 | 10/08/21 | 357 | Platero Navas, Julio A |  | 134.53
PR | 995 | 10/08/21 | 357 | Platero Navas, Julio A |  | 182.01
PR | 995 | 10/08/21 | 358 | Platero Navas, Mario N |  | 134.95
PR | 995 | 10/08/21 | 358 | Platero Navas, Mario N |  | 299.88
PR | 995 | 10/08/21 | 375 | Vazquez Popoca, Jose N |  | 101.21
PR | 995 | 10/08/21 | 375 | Vazquez Popoca, Jose N |  | 449.82
PR | 995 | 10/08/21 | 376 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 10/08/21 | 376 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 10/08/21 | 377 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 10/08/21 | 377 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 10/08/21 | 381 | Donelson, Richard T |  | 52.06
PR | 995 | 10/15/21 | 561 | Barnhart, Joseph N |  | 338.2
PR | 995 | 10/15/21 | 561 | Barnhart, Joseph N |  | 48.31
PR | 995 | 10/15/21 | 569 | Castro Urena, Yanely |  | 74.35
PR | 995 | 10/15/21 | 569 | Castro Urena, Yanely |  | 283.22
PR | 995 | 10/15/21 | 574 | Cruz, Azael S |  | 122.45
PR | 995 | 10/15/21 | 574 | Cruz, Azael S |  | 466.48
PR | 995 | 10/15/21 | 594 | Gonzalez Hernandez, Josue |  | 199.92
PR | 995 | 10/15/21 | 594 | Gonzalez Hernandez, Josue |  | 666.4
PR | 995 | 10/15/21 | 596 | Gordillo, Emanuel D |  | 189.92
PR | 995 | 10/15/21 | 596 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 10/15/21 | 598 | Gutierrez, Brian A |  | 122.45
PR | 995 | 10/15/21 | 598 | Gutierrez, Brian A |  | 466.48
PR | 995 | 10/15/21 | 601 | Holmes, Anthony R |  | 479.81
PR | 995 | 10/15/21 | 601 | Holmes, Anthony R |  | 759.7
PR | 995 | 10/15/21 | 601 | Holmes, Anthony R |  | 39.98
PR | 995 | 10/15/21 | 609 | Lovo, German G |  | 553.95
PR | 995 | 10/15/21 | 617 | Ortiz Carmona, Jose |  | 144.32
PR | 995 | 10/15/21 | 617 | Ortiz Carmona, Jose |  | 549.78
PR | 995 | 10/15/21 | 621 | Platero Navas, Julio A |  | 300.71
PR | 995 | 10/15/21 | 622 | Platero Navas, Mario N |  | 269.89
PR | 995 | 10/15/21 | 638 | Vazquez Popoca, Jose N |  | 258.65
PR | 995 | 10/15/21 | 639 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 10/15/21 | 639 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 10/15/21 | 640 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 10/15/21 | 640 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 10/15/21 | 645 | Donelson, Richard T |  | 26.03
PR | 995 | 10/22/21 | 748 | Barnhart, Joseph N |  | 471.06
PR | 995 | 10/22/21 | 748 | Barnhart, Joseph N |  | 386.51
PR | 995 | 10/22/21 | 757 | Castro Urena, Yanely |  | 269.06
PR | 995 | 10/22/21 | 762 | Cruz, Azael S |  | 122.45
PR | 995 | 10/22/21 | 762 | Cruz, Azael S |  | 466.48
PR | 995 | 10/22/21 | 782 | Gonzalez Hernandez, Josue |  | 199.92
PR | 995 | 10/22/21 | 782 | Gonzalez Hernandez, Josue |  | 666.4
PR | 995 | 10/22/21 | 784 | Gordillo, Emanuel D |  | 213.66
PR | 995 | 10/22/21 | 784 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 10/22/21 | 787 | Gutierrez, Brian A |  | 431.49
PR | 995 | 10/22/21 | 791 | Holmes, Anthony R |  | 539.78
PR | 995 | 10/22/21 | 791 | Holmes, Anthony R |  | 799.68
PR | 995 | 10/22/21 | 799 | Lovo, German G |  | 131.2
PR | 995 | 10/22/21 | 799 | Lovo, German G |  | 583.1
PR | 995 | 10/22/21 | 807 | Ortiz Carmona, Jose |  | 549.78
PR | 995 | 10/22/21 | 811 | Platero Navas, Julio A |  | 94.96
PR | 995 | 10/22/21 | 811 | Platero Navas, Julio A |  | 316.54
PR | 995 | 10/22/21 | 812 | Platero Navas, Mario N |  | 202.42
PR | 995 | 10/22/21 | 812 | Platero Navas, Mario N |  | 299.88
PR | 995 | 10/22/21 | 829 | Vazquez Popoca, Jose N |  | 202.42
PR | 995 | 10/22/21 | 830 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 10/22/21 | 830 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 10/22/21 | 831 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 10/22/21 | 831 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 72.47
PR | 995 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 314.04
PR | 995 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 24.16
PR | 995 | 10/29/21 | 1017 | Castro Urena, Yanely |  | 283.22
PR | 995 | 10/29/21 | 1022 | Cruz, Azael S |  | 466.48
PR | 995 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 162.44
PR | 995 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 333.2
PR | 995 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 333.2
PR | 995 | 10/29/21 | 1043 | Gordillo, Emanuel D |  | 178.05
PR | 995 | 10/29/21 | 1043 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 10/29/21 | 1046 | Gutierrez, Brian A |  | 466.48
PR | 995 | 10/29/21 | 1051 | Holmes, Anthony R |  | 449.82
PR | 995 | 10/29/21 | 1051 | Holmes, Anthony R |  | 799.68
PR | 995 | 10/29/21 | 1059 | Lovo, German G |  | 357.15
PR | 995 | 10/29/21 | 1059 | Lovo, German G |  | 145.78
PR | 995 | 10/29/21 | 1066 | Ortiz Carmona, Jose |  | 412.34
PR | 995 | 10/29/21 | 1066 | Ortiz Carmona, Jose |  | 137.45
PR | 995 | 10/29/21 | 1070 | Platero Navas, Julio A |  | 296.76
PR | 995 | 10/29/21 | 1071 | Platero Navas, Mario N |  | 151.81
PR | 995 | 10/29/21 | 1071 | Platero Navas, Mario N |  | 299.88
PR | 995 | 10/29/21 | 1088 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 10/29/21 | 1088 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 10/29/21 | 1089 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 10/29/21 | 1092 | Donelson, Richard T |  | 26.03
PR | 995 | 11/05/21 | 54 | Barnhart, Joseph N |  | 169.1
PR | 995 | 11/05/21 | 63 | Castro Urena, Yanely |  | 74.35
PR | 995 | 11/05/21 | 63 | Castro Urena, Yanely |  | 70.81
PR | 995 | 11/05/21 | 63 | Castro Urena, Yanely |  | 212.42
PR | 995 | 11/05/21 | 68 | Cruz, Azael S |  | 408.17
PR | 995 | 11/05/21 | 68 | Cruz, Azael S |  | 58.31
PR | 995 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 149.94
PR | 995 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 583.1
PR | 995 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 83.3
PR | 995 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 94.96
PR | 995 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 118.7
PR | 995 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 276.97
PR | 995 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 39.57
PR | 995 | 11/05/21 | 93 | Gutierrez, Brian A |  | 291.55
PR | 995 | 11/05/21 | 93 | Gutierrez, Brian A |  | 58.31
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 269.89
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 59.98
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 209.92
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 559.78
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 139.94
PR | 995 | 11/05/21 | 98 | Holmes, Anthony R |  | 99.96
PR | 995 | 11/05/21 | 107 | Lovo, German G |  | 43.73
PR | 995 | 11/05/21 | 107 | Lovo, German G |  | 87.47
PR | 995 | 11/05/21 | 107 | Lovo, German G |  | 393.59
PR | 995 | 11/05/21 | 107 | Lovo, German G |  | 116.62
PR | 995 | 11/05/21 | 107 | Lovo, German G |  | 72.89
PR | 995 | 11/05/21 | 114 | Ortiz Carmona, Jose |  | 343.61
PR | 995 | 11/05/21 | 114 | Ortiz Carmona, Jose |  | 206.17
PR | 995 | 11/05/21 | 118 | Platero Navas, Julio A |  | 276.97
PR | 995 | 11/05/21 | 118 | Platero Navas, Julio A |  | 39.57
PR | 995 | 11/05/21 | 119 | Platero Navas, Mario N |  | 89.96
PR | 995 | 11/05/21 | 119 | Platero Navas, Mario N |  | 262.4
PR | 995 | 11/05/21 | 119 | Platero Navas, Mario N |  | 37.49
PR | 995 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 316.75
PR | 995 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 568.52
PR | 995 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 81.22
PR | 995 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 495.64
PR | 995 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 70.81
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 72.47
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 48.31
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 48.31
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 48.31
PR | 995 | 11/12/21 | 269 | Barnhart, Joseph N |  | 48.31
PR | 995 | 11/12/21 | 278 | Castro Urena, Yanely |  | 283.22
PR | 995 | 11/12/21 | 283 | Cruz, Azael S |  | 466.48
PR | 995 | 11/12/21 | 303 | Gonzalez Hernandez, Josue |  | 199.92
PR | 995 | 11/12/21 | 303 | Gonzalez Hernandez, Josue |  | 666.4
PR | 995 | 11/12/21 | 304 | Gordillo, Emanuel D |  | 94.96
PR | 995 | 11/12/21 | 304 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 11/12/21 | 307 | Gutierrez, Brian A |  | 466.48
PR | 995 | 11/12/21 | 312 | Holmes, Anthony R |  | 239.9
PR | 995 | 11/12/21 | 312 | Holmes, Anthony R |  | 479.81
PR | 995 | 11/12/21 | 312 | Holmes, Anthony R |  | 179.93
PR | 995 | 11/12/21 | 312 | Holmes, Anthony R |  | 139.94
PR | 995 | 11/12/21 | 321 | Lovo, German G |  | 131.2
PR | 995 | 11/12/21 | 321 | Lovo, German G |  | 583.1
PR | 995 | 11/12/21 | 328 | Ortiz Carmona, Jose |  | 549.78
PR | 995 | 11/12/21 | 332 | Platero Navas, Julio A |  | 94.96
PR | 995 | 11/12/21 | 332 | Platero Navas, Julio A |  | 316.54
PR | 995 | 11/12/21 | 333 | Platero Navas, Mario N |  | 284.89
PR | 995 | 11/12/21 | 351 | Velasquez Cruz, Denis M |  | 170.56
PR | 995 | 11/12/21 | 351 | Velasquez Cruz, Denis M |  | 649.74
PR | 995 | 11/12/21 | 352 | Velasquez Cruz, Osman N |  | 148.69
PR | 995 | 11/12/21 | 352 | Velasquez Cruz, Osman N |  | 566.44
PR | 995 | 11/19/21 | 437 | Barnhart, Joseph N |  | 120.79
PR | 995 | 11/19/21 | 437 | Barnhart, Joseph N |  | 24.16
PR | 995 | 11/19/21 | 446 | Castro Urena, Yanely |  | 247.82
PR | 995 | 11/19/21 | 451 | Cruz, Azael S |  | 87.47
PR | 995 | 11/19/21 | 451 | Cruz, Azael S |  | 466.48
PR | 995 | 11/19/21 | 471 | Gonzalez Hernandez, Josue |  | 333.2
PR | 995 | 11/19/21 | 471 | Gonzalez Hernandez, Josue |  | 299.88
PR | 995 | 11/19/21 | 472 | Gordillo, Emanuel D |  | 71.22
PR | 995 | 11/19/21 | 472 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 11/19/21 | 475 | Gutierrez, Brian A |  | 233.24
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 29.99
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 59.98
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 89.96
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 379.85
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 139.94
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 199.92
PR | 995 | 11/19/21 | 480 | Holmes, Anthony R |  | 79.97
PR | 995 | 11/19/21 | 489 | Lovo, German G |  | 43.73
PR | 995 | 11/19/21 | 489 | Lovo, German G |  | 583.1
PR | 995 | 11/19/21 | 496 | Ortiz Carmona, Jose |  | 522.29
PR | 995 | 11/19/21 | 500 | Platero Navas, Julio A |  | 47.48
PR | 995 | 11/19/21 | 500 | Platero Navas, Julio A |  | 316.54
PR | 995 | 11/19/21 | 501 | Platero Navas, Mario N |  | 269.89
PR | 995 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 121.83
PR | 995 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 454.82
PR | 995 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 32.49
PR | 995 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 162.44
PR | 995 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 106.21
PR | 995 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 368.19
PR | 995 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 28.32
PR | 995 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 169.93
PR | 995 | 11/24/21 | 586 | Castro Urena, Yanely |  | 187.63
PR | 995 | 11/24/21 | 591 | Cruz, Azael S |  | 425.66
PR | 995 | 11/24/21 | 611 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 11/24/21 | 612 | Gordillo, Emanuel D |  | 300.71
PR | 995 | 11/24/21 | 615 | Gutierrez, Brian A |  | 233.24
PR | 995 | 11/24/21 | 618 | Holmes, Anthony R |  | 759.7
PR | 995 | 11/24/21 | 627 | Lovo, German G |  | 524.79
PR | 995 | 11/24/21 | 634 | Ortiz Carmona, Jose |  | 501.67
PR | 995 | 11/24/21 | 638 | Platero Navas, Julio A |  | 229.49
PR | 995 | 11/24/21 | 639 | Platero Navas, Mario N |  | 284.89
PR | 995 | 11/24/21 | 655 | Velasquez Cruz, Denis M |  | 487.31
PR | 995 | 11/24/21 | 655 | Velasquez Cruz, Denis M |  | 105.58
PR | 995 | 11/24/21 | 656 | Velasquez Cruz, Osman N |  | 283.22
PR | 995 | 11/24/21 | 656 | Velasquez Cruz, Osman N |  | 233.66
PR | 995 | 11/24/21 | 659 | Donelson, Richard T |  | 26.03
PR | 995 | 12/03/21 | 13 | Barnhart, Joseph N |  | 120.79
PR | 995 | 12/03/21 | 13 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/03/21 | 13 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/03/21 | 13 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/03/21 | 28 | Cruz, Azael S |  | 443.16
PR | 995 | 12/03/21 | 48 | Gonzalez Hernandez, Josue |  | 633.08
PR | 995 | 12/03/21 | 49 | Gordillo, Emanuel D |  | 300.71
PR | 995 | 12/03/21 | 56 | Holmes, Anthony R |  | 759.7
PR | 995 | 12/03/21 | 65 | Lovo, German G |  | 524.79
PR | 995 | 12/03/21 | 72 | Ortiz Carmona, Jose |  | 384.85
PR | 995 | 12/03/21 | 76 | Platero Navas, Julio A |  | 300.71
PR | 995 | 12/03/21 | 77 | Platero Navas, Mario N |  | 284.89
PR | 995 | 12/03/21 | 94 | Velasquez Cruz, Denis M |  | 617.25
PR | 995 | 12/03/21 | 95 | Velasquez Cruz, Osman N |  | 538.12
PR | 995 | 12/10/21 | 194 | Barnhart, Joseph N |  | 193.26
PR | 995 | 12/10/21 | 209 | Cruz, Azael S |  | 279.89
PR | 995 | 12/10/21 | 229 | Gonzalez Hernandez, Josue |  | 516.46
PR | 995 | 12/10/21 | 229 | Gonzalez Hernandez, Josue |  | 16.66
PR | 995 | 12/10/21 | 230 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 12/10/21 | 238 | Holmes, Anthony R |  | 799.68
PR | 995 | 12/10/21 | 247 | Lovo, German G |  | 349.86
PR | 995 | 12/10/21 | 255 | Ortiz Carmona, Jose |  | 329.87
PR | 995 | 12/10/21 | 259 | Platero Navas, Julio A |  | 316.54
PR | 995 | 12/10/21 | 260 | Platero Navas, Mario N |  | 299.88
PR | 995 | 12/10/21 | 277 | Velasquez Cruz, Denis M |  | 389.84
PR | 995 | 12/10/21 | 278 | Velasquez Cruz, Osman N |  | 226.58
PR | 995 | 12/10/21 | 281 | Donelson, Richard T |  | 52.06
PR | 995 | 12/17/21 | 516 | Barnhart, Joseph N |  | 72.47
PR | 995 | 12/17/21 | 516 | Barnhart, Joseph N |  | 72.47
PR | 995 | 12/17/21 | 516 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/17/21 | 516 | Barnhart, Joseph N |  | 24.16
PR | 995 | 12/17/21 | 517 | Barnhart, Thomas L |  | 253.23
PR | 995 | 12/17/21 | 551 | Gonzalez Hernandez, Josue |  | 666.4
PR | 995 | 12/17/21 | 552 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 12/17/21 | 560 | Holmes, Anthony R |  | 779.69
PR | 995 | 12/17/21 | 560 | Holmes, Anthony R |  | 19.99
PR | 995 | 12/17/21 | 569 | Lovo, German G |  | 583.1
PR | 995 | 12/17/21 | 581 | Platero Navas, Mario N |  | 239.9
PR | 995 | 12/17/21 | 581 | Platero Navas, Mario N |  | 29.99
PR | 995 | 12/17/21 | 581 | Platero Navas, Mario N |  | 29.99
PR | 995 | 12/17/21 | 592 | Sanders, Allen O |  | 71.22
PR | 995 | 12/23/21 | 741 | Barnhart, Joseph N |  | 48.31
PR | 995 | 12/23/21 | 741 | Barnhart, Joseph N |  | 96.63
PR | 995 | 12/23/21 | 741 | Barnhart, Joseph N |  | 48.31
PR | 995 | 12/23/21 | 742 | Barnhart, Thomas L |  | 94.96
PR | 995 | 12/23/21 | 776 | Gonzalez Hernandez, Josue |  | 399.84
PR | 995 | 12/23/21 | 777 | Gordillo, Emanuel D |  | 253.23
PR | 995 | 12/23/21 | 785 | Holmes, Anthony R |  | 799.68
PR | 995 | 12/23/21 | 794 | Lovo, German G |  | 583.1
PR | 995 | 12/23/21 | 806 | Platero Navas, Mario N |  | 239.9
PR | 995 | 12/23/21 | 806 | Platero Navas, Mario N |  | 59.98
PR | 995 | 12/23/21 | 827 | Donelson, Richard T |  | 104.13
PR | 995 | 12/30/21 | 971 | Gonzalez Hernandez, Josue |  | 133.28
PR | 995 | 12/30/21 | 972 | Gordillo, Emanuel D |  | 106.83
PR | 995 | 12/30/21 | 980 | Holmes, Anthony R |  | 269.89
PR | 995 | 12/30/21 | 989 | Lovo, German G |  | 116.62
PR | 995 | 12/30/21 | 1002 | Platero Navas, Mario N |  | 59.98
PR | 995 | 01/07/22 | 31 | Barnhart, Thomas L |  | 126.62
PR | 995 | 01/07/22 | 65 | Gordillo, Emanuel D |  | 189.92
PR | 995 | 01/07/22 | 74 | Holmes, Anthony R |  | 319.87
PR | 995 | 01/07/22 | 74 | Holmes, Anthony R |  | 159.94
PR | 995 | 01/07/22 | 83 | Lovo, German G |  | 233.24
PR | 995 | 01/07/22 | 96 | Platero Navas, Mario N |  | 119.95
PR | 995 | 01/14/22 | 232 | Barnhart, Thomas L |  | 633.08
PR | 995 | 01/14/22 | 266 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 01/14/22 | 275 | Holmes, Anthony R |  | 799.68
PR | 995 | 01/14/22 | 283 | Lovo, German G |  | 583.1
PR | 995 | 01/14/22 | 295 | Platero Navas, Julio A |  | 189.92
PR | 995 | 01/14/22 | 296 | Platero Navas, Mario N |  | 299.88
PR | 995 | 01/21/22 | 414 | Barnhart, Joseph N |  | 96.63
PR | 995 | 01/21/22 | 415 | Barnhart, Thomas L |  | 506.46
PR | 995 | 01/21/22 | 449 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 01/21/22 | 458 | Holmes, Anthony R |  | 159.94
PR | 995 | 01/21/22 | 458 | Holmes, Anthony R |  | 639.74
PR | 995 | 01/21/22 | 467 | Lovo, German G |  | 233.24
PR | 995 | 01/21/22 | 467 | Lovo, German G |  | 349.86
PR | 995 | 01/21/22 | 479 | Platero Navas, Julio A |  | 316.54
PR | 995 | 01/21/22 | 480 | Platero Navas, Mario N |  | 119.95
PR | 995 | 01/21/22 | 480 | Platero Navas, Mario N |  | 179.93
PR | 995 | 01/28/22 | 616 | Barnhart, Thomas L |  | 633.08
PR | 995 | 01/28/22 | 630 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 01/28/22 | 632 | Cruz Reyes, Jose |  | 119.95
PR | 995 | 01/28/22 | 637 | Eliassen, Cory H |  | 113.29
PR | 995 | 01/28/22 | 650 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 01/28/22 | 659 | Holmes, Anthony R |  | 799.68
PR | 995 | 01/28/22 | 668 | Lovo, German G |  | 116.62
PR | 995 | 01/28/22 | 680 | Platero Navas, Julio A |  | 316.54
PR | 995 | 01/28/22 | 681 | Platero Navas, Mario N |  | 299.88
PR | 995 | 01/28/22 | 692 | Sanders, Allen O |  | 94.96
PR | 995 | 02/04/22 | 11 | Barnhart, Joseph N |  | 193.26
PR | 995 | 02/04/22 | 11 | Barnhart, Joseph N |  | 72.47
PR | 995 | 02/04/22 | 11 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/04/22 | 12 | Barnhart, Thomas L |  | 633.08
PR | 995 | 02/04/22 | 26 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 02/04/22 | 28 | Cruz Reyes, Jose |  | 119.95
PR | 995 | 02/04/22 | 33 | Eliassen, Cory H |  | 113.29
PR | 995 | 02/04/22 | 46 | Gordillo, Emanuel D |  | 253.23
PR | 995 | 02/04/22 | 55 | Holmes, Anthony R |  | 479.81
PR | 995 | 02/04/22 | 55 | Holmes, Anthony R |  | 319.87
PR | 995 | 02/04/22 | 75 | Platero Navas, Mario N |  | 179.93
PR | 995 | 02/04/22 | 87 | Sanders, Allen O |  | 142.44
PR | 995 | 02/04/22 | 92 | Trower-Kelly, Fidel D |  | 86.63
PR | 995 | 02/11/22 | 217 | Barnhart, Joseph N |  | 72.47
PR | 995 | 02/11/22 | 217 | Barnhart, Joseph N |  | 507.3
PR | 995 | 02/11/22 | 218 | Barnhart, Thomas L |  | 23.74
PR | 995 | 02/11/22 | 218 | Barnhart, Thomas L |  | 633.08
PR | 995 | 02/11/22 | 232 | Cruz Gonzalez, Julio C |  | 19.99
PR | 995 | 02/11/22 | 232 | Cruz Gonzalez, Julio C |  | 106.62
PR | 995 | 02/11/22 | 234 | Cruz Reyes, Jose |  | 22.49
PR | 995 | 02/11/22 | 234 | Cruz Reyes, Jose |  | 119.95
PR | 995 | 02/11/22 | 239 | Eliassen, Cory H |  | 113.29
PR | 995 | 02/11/22 | 253 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 02/11/22 | 262 | Holmes, Anthony R |  | 619.75
PR | 995 | 02/11/22 | 262 | Holmes, Anthony R |  | 159.94
PR | 995 | 02/11/22 | 262 | Holmes, Anthony R |  | 19.99
PR | 995 | 02/11/22 | 282 | Platero Navas, Julio A |  | 316.54
PR | 995 | 02/11/22 | 283 | Platero Navas, Mario N |  | 119.95
PR | 995 | 02/11/22 | 295 | Sanders, Allen O |  | 201.79
PR | 995 | 02/18/22 | 488 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/18/22 | 488 | Barnhart, Joseph N |  | 24.16
PR | 995 | 02/18/22 | 488 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/18/22 | 489 | Barnhart, Thomas L |  | 633.08
PR | 995 | 02/18/22 | 504 | Cruz Reyes, Jose |  | 22.49
PR | 995 | 02/18/22 | 504 | Cruz Reyes, Jose |  | 119.95
PR | 995 | 02/18/22 | 509 | Eliassen, Cory H |  | 113.29
PR | 995 | 02/18/22 | 523 | Gordillo, Emanuel D |  | 126.62
PR | 995 | 02/18/22 | 523 | Gordillo, Emanuel D |  | 126.62
PR | 995 | 02/18/22 | 532 | Holmes, Anthony R |  | 799.68
PR | 995 | 02/18/22 | 552 | Platero Navas, Julio A |  | 126.62
PR | 995 | 02/18/22 | 552 | Platero Navas, Julio A |  | 126.62
PR | 995 | 02/18/22 | 564 | Sanders, Allen O |  | 296.76
PR | 995 | 02/18/22 | 569 | Trower-Kelly, Fidel D |  | 92.05
PR | 995 | 02/18/22 | 577 | Donelson, Richard T |  | 78.09
PR | 995 | 02/18/22 | 578 | Gerard, Jeffrey S |  | 24.99
PR | 995 | 02/25/22 | 709 | Barnhart, Joseph N |  | 48.31
PR | 995 | 02/25/22 | 709 | Barnhart, Joseph N |  | 120.79
PR | 995 | 02/25/22 | 709 | Barnhart, Joseph N |  | 169.1
PR | 995 | 02/25/22 | 710 | Barnhart, Thomas L |  | 633.08
PR | 995 | 02/25/22 | 743 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 02/25/22 | 752 | Holmes, Anthony R |  | 799.68
PR | 995 | 02/25/22 | 772 | Platero Navas, Julio A |  | 316.54
PR | 995 | 02/25/22 | 784 | Sanders, Allen O |  | 118.7
PR | 995 | 03/04/22 | 44 | Barnhart, Joseph N |  | 483.14
PR | 995 | 03/04/22 | 45 | Barnhart, Thomas L |  | 379.85
PR | 995 | 03/04/22 | 60 | Cruz Reyes, Jose |  | 119.95
PR | 995 | 03/04/22 | 79 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 03/04/22 | 88 | Holmes, Anthony R |  | 799.68
PR | 995 | 03/04/22 | 98 | Lovo, German G |  | 583.1
PR | 995 | 03/04/22 | 110 | Platero Navas, Julio A |  | 316.54
PR | 995 | 03/04/22 | 122 | Sanders, Allen O |  | 118.7
PR | 995 | 03/04/22 | 134 | Donelson, Richard T |  | 78.09
PR | 995 | 03/11/22 | 341 | Barnhart, Joseph N |  | 48.31
PR | 995 | 03/11/22 | 341 | Barnhart, Joseph N |  | 60.39
PR | 995 | 03/11/22 | 342 | Barnhart, Thomas L |  | 633.08
PR | 995 | 03/11/22 | 376 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 03/11/22 | 384 | Holmes, Anthony R |  | 699.72
PR | 995 | 03/11/22 | 384 | Holmes, Anthony R |  | 99.96
PR | 995 | 03/11/22 | 391 | Johnson, Jake E |  | 41.65
PR | 995 | 03/11/22 | 395 | Lovo, German G |  | 466.48
PR | 995 | 03/11/22 | 407 | Platero Navas, Julio A |  | 253.23
PR | 995 | 03/11/22 | 419 | Sanders, Allen O |  | 106.83
PR | 995 | 03/18/22 | 626 | Barnhart, Joseph N |  | 157.02
PR | 995 | 03/18/22 | 626 | Barnhart, Joseph N |  | 24.16
PR | 995 | 03/18/22 | 626 | Barnhart, Joseph N |  | 24.16
PR | 995 | 03/18/22 | 627 | Barnhart, Thomas L |  | 633.08
PR | 995 | 03/18/22 | 661 | Gordillo, Emanuel D |  | 253.23
PR | 995 | 03/18/22 | 669 | Holmes, Anthony R |  | 319.87
PR | 995 | 03/18/22 | 669 | Holmes, Anthony R |  | 319.87
PR | 995 | 03/18/22 | 676 | Johnson, Jake E |  | 20.83
PR | 995 | 03/18/22 | 680 | Lovo, German G |  | 583.1
PR | 995 | 03/18/22 | 692 | Platero Navas, Julio A |  | 316.54
PR | 995 | 03/18/22 | 704 | Sanders, Allen O |  | 166.18
PR | 995 | 03/25/22 | 875 | Barnhart, Joseph N |  | 386.51
PR | 995 | 03/25/22 | 876 | Barnhart, Thomas L |  | 633.08
PR | 995 | 03/25/22 | 908 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 03/25/22 | 916 | Holmes, Anthony R |  | 799.68
PR | 995 | 03/25/22 | 927 | Lovo, German G |  | 553.95
PR | 995 | 03/25/22 | 927 | Lovo, German G |  | 29.16
PR | 995 | 03/25/22 | 939 | Platero Navas, Julio A |  | 300.71
PR | 995 | 03/25/22 | 939 | Platero Navas, Julio A |  | 15.83
PR | 995 | 03/25/22 | 950 | Sanders, Allen O |  | 118.7
PR | 995 | 04/01/22 | 21 | Barnhart, Joseph N |  | 241.57
PR | 995 | 04/01/22 | 21 | Barnhart, Joseph N |  | 72.47
PR | 995 | 04/01/22 | 22 | Barnhart, Thomas L |  | 633.08
PR | 995 | 04/01/22 | 41 | Eliassen, Cory H |  | 226.58
PR | 995 | 04/01/22 | 55 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 04/01/22 | 63 | Holmes, Anthony R |  | 799.68
PR | 995 | 04/01/22 | 74 | Lovo, German G |  | 583.1
PR | 995 | 04/01/22 | 85 | Platero Navas, Julio A |  | 316.54
PR | 995 | 04/01/22 | 96 | Sanders, Allen O |  | 94.96
PR | 995 | 04/01/22 | 108 | Donelson, Richard T |  | 26.03
PR | 995 | 04/08/22 | 227 | Barnhart, Joseph N |  | 120.79
PR | 995 | 04/08/22 | 227 | Barnhart, Joseph N |  | 96.63
PR | 995 | 04/08/22 | 227 | Barnhart, Joseph N |  | 24.16
PR | 995 | 04/08/22 | 228 | Barnhart, Thomas L |  | 506.46
PR | 995 | 04/08/22 | 261 | Gordillo, Emanuel D |  | 316.54
PR | 995 | 04/08/22 | 269 | Holmes, Anthony R |  | 799.68
PR | 995 | 04/08/22 | 280 | Lovo, German G |  | 546.66
PR | 995 | 04/08/22 | 291 | Platero Navas, Julio A |  | 296.76
PR | 995 | 04/08/22 | 317 | Platero Navas, Julio A |  | -296.76
PR | 995 | 04/08/22 | 318 | Platero Navas, Julio A |  | 296.76
PR | 995 | 04/15/22 | 475 | Barnhart, Joseph N |  | 314.04
PR | 995 | 04/15/22 | 475 | Barnhart, Joseph N |  | 48.31
PR | 995 | 04/15/22 | 476 | Barnhart, Thomas L |  | 379.85
PR | 995 | 04/15/22 | 508 | Gordillo, Emanuel D |  | 366.52
PR | 995 | 04/15/22 | 516 | Holmes, Anthony R |  | 799.68
PR | 995 | 04/15/22 | 527 | Lovo, German G |  | 546.66
PR | 995 | 04/15/22 | 538 | Platero Navas, Julio A |  | 349.86
PR | 995 | 04/15/22 | 549 | Sanders, Allen O |  | 94.96
PR | 995 | 04/22/22 | 803 | Barnhart, Joseph N |  | 120.79
PR | 995 | 04/22/22 | 803 | Barnhart, Joseph N |  | 434.83
PR | 995 | 04/22/22 | 804 | Barnhart, Thomas L |  | 506.46
PR | 995 | 04/22/22 | 836 | Gordillo, Emanuel D |  | 146.61
PR | 995 | 04/22/22 | 844 | Holmes, Anthony R |  | 319.87
PR | 995 | 04/22/22 | 855 | Lovo, German G |  | 466.48
PR | 995 | 04/22/22 | 866 | Platero Navas, Julio A |  | 349.86
PR | 995 | 04/22/22 | 877 | Sanders, Allen O |  | 142.44
PR | 995 | 04/22/22 | 889 | Donelson, Richard T |  | 26.03
PR | 995 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 217.41
PR | 995 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 72.47
PR | 995 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 24.16
PR | 995 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 48.31
PR | 995 | 04/29/22 | 1064 | Barnhart, Thomas L |  | 379.85
PR | 995 | 04/29/22 | 1096 | Gordillo, Emanuel D |  | 219.91
PR | 995 | 04/29/22 | 1104 | Holmes, Anthony R |  | 479.81
PR | 995 | 04/29/22 | 1111 | Johnson, Jake E |  | 41.65
PR | 995 | 04/29/22 | 1111 | Johnson, Jake E |  | 20.83
PR | 995 | 04/29/22 | 1115 | Lovo, German G |  | 583.1
PR | 995 | 04/29/22 | 1127 | Platero Navas, Julio A |  | 279.89
PR | 995 | 04/29/22 | 1137 | Sanders, Allen O |  | 189.92
PR | 995 | 05/06/22 | 90 | Barnhart, Joseph N |  | 144.94
PR | 995 | 05/06/22 | 90 | Barnhart, Joseph N |  | 72.47
PR | 995 | 05/06/22 | 91 | Barnhart, Thomas L |  | 506.46
PR | 995 | 05/06/22 | 120 | Gordillo, Emanuel D |  | 293.22
PR | 995 | 05/06/22 | 128 | Holmes, Anthony R |  | 539.78
PR | 995 | 05/06/22 | 128 | Holmes, Anthony R |  | 259.9
PR | 995 | 05/06/22 | 139 | Lovo, German G |  | 430.04
PR | 995 | 05/06/22 | 151 | Platero Navas, Julio A |  | 327.99
PR | 995 | 05/06/22 | 160 | Sanders, Allen O |  | 106.83
PR | 995 | 05/13/22 | 325 | Barnhart, Thomas L |  | 506.46
PR | 995 | 05/13/22 | 355 | Gordillo, Emanuel D |  | 366.52
PR | 995 | 05/13/22 | 363 | Holmes, Anthony R |  | 399.84
PR | 995 | 05/13/22 | 363 | Holmes, Anthony R |  | 79.97
PR | 995 | 05/13/22 | 363 | Holmes, Anthony R |  | 319.87
PR | 995 | 05/13/22 | 373 | Lovo, German G |  | 233.24
PR | 995 | 05/13/22 | 373 | Lovo, German G |  | 349.86
PR | 995 | 05/13/22 | 385 | Platero Navas, Julio A |  | 139.94
PR | 995 | 05/13/22 | 385 | Platero Navas, Julio A |  | 139.94
PR | 995 | 05/13/22 | 396 | Sanders, Allen O |  | 201.79
PR | 995 | 05/20/22 | 598 | Barnhart, Joseph N |  | 74.97
PR | 995 | 05/20/22 | 598 | Barnhart, Joseph N |  | 49.98
PR | 995 | 05/20/22 | 598 | Barnhart, Joseph N |  | 24.99
PR | 995 | 05/20/22 | 598 | Barnhart, Joseph N |  | 49.98
PR | 995 | 05/20/22 | 599 | Barnhart, Thomas L |  | 519.79
PR | 995 | 05/20/22 | 616 | Eliassen, Cory H |  | 233.24
PR | 995 | 05/20/22 | 629 | Gordillo, Emanuel D |  | 36.65
PR | 995 | 05/20/22 | 629 | Gordillo, Emanuel D |  | 146.61
PR | 995 | 05/20/22 | 637 | Holmes, Anthony R |  | 416.5
PR | 995 | 05/20/22 | 647 | Lovo, German G |  | 359.86
PR | 995 | 05/20/22 | 659 | Platero Navas, Julio A |  | 349.86
PR | 995 | 05/20/22 | 669 | Sanders, Allen O |  | 135.15
PR | 995 | 05/20/22 | 681 | Donelson, Richard T |  | 208.25
PR | 995 | 05/27/22 | 867 | Barnhart, Joseph N |  | 524.79
PR | 995 | 05/27/22 | 868 | Barnhart, Thomas L |  | 519.79
PR | 995 | 05/27/22 | 886 | Eliassen, Cory H |  | 233.24
PR | 995 | 05/27/22 | 899 | Gordillo, Emanuel D |  | 366.52
PR | 995 | 05/27/22 | 906 | Holmes, Anthony R |  | 833
PR | 995 | 05/27/22 | 916 | Lovo, German G |  | 599.76
PR | 995 | 05/27/22 | 928 | Platero Navas, Julio A |  | 349.86
PR | 995 | 05/27/22 | 951 | Donelson, Richard T |  | 104.13
PR | 995 | 06/03/22 | 11 | Barnhart, Thomas L |  | 519.79
PR | 995 | 06/03/22 | 29 | Eliassen, Cory H |  | 233.24
PR | 995 | 06/03/22 | 41 | Gordillo, Emanuel D |  | 293.22
PR | 995 | 06/03/22 | 49 | Holmes, Anthony R |  | 166.6
PR | 995 | 06/03/22 | 49 | Holmes, Anthony R |  | 499.8
PR | 995 | 06/03/22 | 56 | Johnson, Jake E |  | 20.83
PR | 995 | 06/03/22 | 59 | Lovo, German G |  | 359.86
PR | 995 | 06/03/22 | 59 | Lovo, German G |  | 119.95
PR | 995 | 06/03/22 | 71 | Platero Navas, Julio A |  | 209.92
PR | 995 | 06/03/22 | 71 | Platero Navas, Julio A |  | 69.97
PR | 995 | 06/03/22 | 93 | Donelson, Richard T |  | 78.09
PR | 995 | 06/10/22 | 220 | Barnhart, Thomas L |  | 389.84
PR | 995 | 06/10/22 | 237 | Eliassen, Cory H |  | 116.62
PR | 995 | 06/10/22 | 249 | Gordillo, Emanuel D |  | 219.91
PR | 995 | 06/10/22 | 249 | Gordillo, Emanuel D |  | 73.3
PR | 995 | 06/10/22 | 257 | Holmes, Anthony R |  | 499.8
PR | 995 | 06/10/22 | 257 | Holmes, Anthony R |  | 166.6
PR | 995 | 06/10/22 | 267 | Lovo, German G |  | 479.81
PR | 995 | 06/10/22 | 279 | Platero Navas, Julio A |  | 258.02
PR | 995 | 06/10/22 | 289 | Sanders, Allen O |  | 172.01
PR | 995 | 06/10/22 | 301 | Donelson, Richard T |  | 130.16
PR | 995 | 06/17/22 | 465 | Barnhart, Joseph N |  | 24.99
PR | 995 | 06/17/22 | 465 | Barnhart, Joseph N |  | 74.97
PR | 995 | 06/17/22 | 465 | Barnhart, Joseph N |  | 99.96
PR | 995 | 06/17/22 | 465 | Barnhart, Joseph N |  | 99.96
PR | 995 | 06/17/22 | 466 | Barnhart, Thomas L |  | 519.79
PR | 995 | 06/17/22 | 484 | Eliassen, Cory H |  | 98.4
PR | 995 | 06/17/22 | 497 | Gordillo, Emanuel D |  | 103.08
PR | 995 | 06/17/22 | 497 | Gordillo, Emanuel D |  | 366.52
PR | 995 | 06/17/22 | 505 | Holmes, Anthony R |  | 234.28
PR | 995 | 06/17/22 | 505 | Holmes, Anthony R |  | 833
PR | 995 | 06/17/22 | 515 | Lovo, German G |  | 599.76
PR | 995 | 06/17/22 | 518 | McCabe, Thomas C |  | 91.84
PR | 995 | 06/17/22 | 518 | McCabe, Thomas C |  | 17.49
PR | 995 | 06/17/22 | 527 | Platero Navas, Julio A |  | 349.86
PR | 995 | 06/17/22 | 534 | Romero Garza, Jesus I |  | 75.91
PR | 995 | 06/17/22 | 537 | Sanders, Allen O |  | 165.87
PR | 995 | 06/17/22 | 537 | Sanders, Allen O |  | 159.73
PR | 995 | 06/17/22 | 537 | Sanders, Allen O |  | 73.72
PR | 995 | 06/17/22 | 540 | Taylor, Evan R |  | 126.51
PR | 995 | 06/17/22 | 541 | Trower-Kelly, Fidel D |  | 75.91
PR | 995 | 06/17/22 | 549 | Donelson, Richard T |  | 130.16
PR | 995 | 06/24/22 | 771 | Barnhart, Joseph N |  | 199.92
PR | 995 | 06/24/22 | 771 | Barnhart, Joseph N |  | 99.96
PR | 995 | 06/24/22 | 771 | Barnhart, Joseph N |  | 49.98
PR | 995 | 06/24/22 | 771 | Barnhart, Joseph N |  | 49.98
PR | 995 | 06/24/22 | 772 | Barnhart, Thomas L |  | 519.79
PR | 995 | 06/24/22 | 801 | Gordillo, Emanuel D |  | 210.75
PR | 995 | 06/24/22 | 809 | Holmes, Anthony R |  | 812.18
PR | 995 | 06/24/22 | 819 | Lovo, German G |  | 359.86
PR | 995 | 06/24/22 | 830 | Platero Navas, Julio A |  | 279.89
PR | 995 | 06/24/22 | 839 | Sanders, Allen O |  | 196.59
PR | 995 | 06/24/22 | 851 | Donelson, Richard T |  | 26.03
PR | 995 | 07/01/22 | 13 | Barnhart, Thomas L |  | 519.79
PR | 995 | 07/01/22 | 13 | Barnhart, Thomas L |  | 81.22
PR | 995 | 07/01/22 | 31 | Eliassen, Cory H |  | 109.33
PR | 995 | 07/01/22 | 42 | Gordillo, Emanuel D |  | 366.52
PR | 995 | 07/01/22 | 50 | Holmes, Anthony R |  | 833
PR | 995 | 07/01/22 | 62 | McCabe, Thomas C |  | 104.96
PR | 995 | 07/01/22 | 62 | McCabe, Thomas C |  | 17.49
PR | 995 | 07/01/22 | 70 | Platero Navas, Julio A |  | 227.41
PR | 995 | 07/01/22 | 78 | Sanders, Allen O |  | 258.02
PR | 995 | 07/01/22 | 78 | Sanders, Allen O |  | 122.87
PR | 995 | 07/01/22 | 78 | Sanders, Allen O |  | 49.15
PR | 995 | 07/01/22 | 81 | Taylor, Evan R |  | 253.02
PR | 995 | 07/01/22 | 82 | Trower-Kelly, Fidel D |  | 56.23
PR | 995 | 07/01/22 | 84 | Waites, Thaddeus Z |  | 168.68
PR | 995 | 07/08/22 | 175 | Barnhart, Thomas L |  | 389.84
PR | 995 | 07/08/22 | 205 | Gordillo, Emanuel D |  | 146.61
PR | 995 | 07/08/22 | 205 | Gordillo, Emanuel D |  | 146.61
PR | 995 | 07/08/22 | 213 | Holmes, Anthony R |  | 333.2
PR | 995 | 07/08/22 | 213 | Holmes, Anthony R |  | 166.6
PR | 995 | 07/08/22 | 213 | Holmes, Anthony R |  | 166.6
PR | 995 | 07/08/22 | 223 | Lovo, German G |  | 239.9
PR | 995 | 07/08/22 | 223 | Lovo, German G |  | 239.9
PR | 995 | 07/08/22 | 234 | Platero Navas, Julio A |  | 139.94
PR | 995 | 07/08/22 | 234 | Platero Navas, Julio A |  | 139.94
PR | 995 | 07/15/22 | 369 | Barnhart, Joseph N |  | 24.99
PR | 995 | 07/15/22 | 369 | Barnhart, Joseph N |  | 24.99
PR | 995 | 07/15/22 | 370 | Barnhart, Thomas L |  | 519.79
PR | 995 | 07/15/22 | 400 | Gordillo, Emanuel D |  | 357.36
PR | 995 | 07/15/22 | 408 | Holmes, Anthony R |  | 499.8
PR | 995 | 07/15/22 | 408 | Holmes, Anthony R |  | 312.38
PR | 995 | 07/15/22 | 414 | Johnson, Jake E |  | 20.83
PR | 995 | 07/15/22 | 417 | Lovo, German G |  | 599.76
PR | 995 | 07/15/22 | 429 | Platero Navas, Julio A |  | 349.86
PR | 995 | 07/22/22 | 608 | Barnhart, Joseph N |  | 24.99
PR | 995 | 07/22/22 | 609 | Barnhart, Thomas L |  | 649.74
PR | 995 | 07/22/22 | 638 | Gordillo, Emanuel D |  | 284.05
PR | 995 | 07/22/22 | 644 | Holmes, Anthony R |  | 645.58
PR | 995 | 07/22/22 | 673 | Sanders, Allen O |  | 258.02
PR | 995 | 07/29/22 | 724 | Barnhart, Joseph N |  | 174.93
PR | 995 | 07/29/22 | 753 | Gordillo, Emanuel D |  | 256.56
PR | 995 | 07/29/22 | 753 | Gordillo, Emanuel D |  | 73.3
PR | 995 | 07/29/22 | 759 | Holmes, Anthony R |  | 583.1
PR | 995 | 07/29/22 | 759 | Holmes, Anthony R |  | 166.6
PR | 995 | 07/29/22 | 798 | Gerard, Jeffrey S |  | 26.03
PR | 995 | 08/05/22 | 89 | Barnhart, Joseph N |  | 99.96
PR | 995 | 08/05/22 | 90 | Barnhart, Thomas L |  | 259.9
PR | 995 | 08/05/22 | 90 | Barnhart, Thomas L |  | 129.95
PR | 995 | 08/05/22 | 118 | Gordillo, Emanuel D |  | 219.91
PR | 995 | 08/05/22 | 124 | Holmes, Anthony R |  | 499.8
PR | 995 | 08/05/22 | 133 | Lovo, German G |  | 239.9
PR | 995 | 08/12/22 | 288 | Barnhart, Joseph N |  | 49.98
PR | 995 | 08/12/22 | 288 | Barnhart, Joseph N |  | 149.94
PR | 995 | 08/12/22 | 289 | Barnhart, Thomas L |  | 649.74
PR | 995 | 08/12/22 | 316 | Gordillo, Emanuel D |  | 219.91
PR | 995 | 08/12/22 | 322 | Holmes, Anthony R |  | 499.8
PR | 995 | 08/12/22 | 331 | Lovo, German G |  | 599.76
PR | 995 | 08/19/22 | 495 | Barnhart, Joseph N |  | 24.99
PR | 995 | 08/19/22 | 495 | Barnhart, Joseph N |  | 74.97
PR | 995 | 08/19/22 | 495 | Barnhart, Joseph N |  | 49.98
PR | 995 | 08/19/22 | 496 | Barnhart, Thomas L |  | 389.84
PR | 995 | 08/19/22 | 496 | Barnhart, Thomas L |  | 259.9
PR | 995 | 08/19/22 | 524 | Gordillo, Emanuel D |  | 293.22
PR | 995 | 08/19/22 | 530 | Holmes, Anthony R |  | 499.8
PR | 995 | 08/19/22 | 530 | Holmes, Anthony R |  | 166.6
PR | 995 | 08/19/22 | 539 | Lovo, German G |  | 359.86
PR | 995 | 08/19/22 | 539 | Lovo, German G |  | 119.95
PR | 995 | 08/26/22 | 761 | Barnhart, Joseph N |  | 74.97
PR | 995 | 08/26/22 | 762 | Barnhart, Thomas L |  | 129.95
PR | 995 | 08/26/22 | 790 | Gordillo, Emanuel D |  | 192.42
PR | 995 | 08/26/22 | 790 | Gordillo, Emanuel D |  | 18.33
PR | 995 | 08/26/22 | 796 | Holmes, Anthony R |  | 104.13
PR | 995 | 08/26/22 | 796 | Holmes, Anthony R |  | 41.65
PR | 995 | 08/26/22 | 805 | Lovo, German G |  | 119.95
PR | 995 | 09/02/22 | 9 | Barnhart, Thomas L |  | 389.84
PR | 995 | 09/02/22 | 37 | Gordillo, Emanuel D |  | 114.54
PR | 995 | 09/02/22 | 37 | Gordillo, Emanuel D |  | 9.16
PR | 995 | 09/02/22 | 43 | Holmes, Anthony R |  | 281.14
PR | 995 | 09/09/22 | 201 | Barnhart, Thomas L |  | 259.9
PR | 995 | 09/09/22 | 236 | Holmes, Anthony R |  | 270.73
PR | 995 | 09/09/22 | 241 | Johnson, Jake E |  | 20.83
PR | 995 | 09/09/22 | 265 | Sanders, Allen O |  | 73.72
PR | 995 | 09/16/22 | 430 | Barnhart, Joseph N |  | 124.95
PR | 995 | 09/16/22 | 430 | Barnhart, Joseph N |  | 49.98
PR | 995 | 09/16/22 | 430 | Barnhart, Joseph N |  | 74.97
PR | 995 | 09/16/22 | 460 | Gordillo, Emanuel D |  | 64.14
PR | 995 | 09/16/22 | 460 | Gordillo, Emanuel D |  | 36.65
PR | 995 | 09/16/22 | 465 | Holmes, Anthony R |  | 145.78
PR | 995 | 09/16/22 | 465 | Holmes, Anthony R |  | 83.3
PR | 995 | 09/16/22 | 470 | Johnson, Jake E |  | 20.83
PR | 995 | 09/23/22 | 565 | Barnhart, Thomas L |  | 129.95
PR | 995 | 09/23/22 | 625 | Sanders, Allen O |  | 98.29
PR | 995 | 09/30/22 | 815 | Barnhart, Joseph N |  | 99.96
PR | 995 | 09/30/22 | 815 | Barnhart, Joseph N |  | 49.98
PR | 995 | 09/30/22 | 815 | Barnhart, Joseph N |  | 24.99
PR | 995 | 09/30/22 | 815 | Barnhart, Joseph N |  | 24.99
PR | 995 | 09/30/22 | 816 | Barnhart, Thomas L |  | 129.95
PR | 995 | 09/30/22 | 848 | Holmes, Anthony R |  | 20.83
PR | 995 | 10/07/22 | 28 | Barnhart, Joseph N |  | 106.62
PR | 995 | 10/07/22 | 28 | Barnhart, Joseph N |  | 133.28
PR | 995 | 10/07/22 | 28 | Barnhart, Joseph N |  | 79.97
PR | 995 | 10/07/22 | 28 | Barnhart, Joseph N |  | 106.62
PR | 995 | 10/07/22 | 58 | Gordillo, Emanuel D |  | 27.49
PR | 995 | 10/07/22 | 63 | Holmes, Anthony R |  | 67.47
PR | 995 | 10/14/22 | 283 | Barnhart, Joseph N |  | 106.62
PR | 995 | 10/14/22 | 283 | Barnhart, Joseph N |  | 26.66
PR | 995 | 10/14/22 | 283 | Barnhart, Joseph N |  | 26.66
PR | 995 | 10/14/22 | 283 | Barnhart, Joseph N |  | 26.66
PR | 995 | 10/21/22 | 477 | Barnhart, Joseph N |  | 319.87
PR | 995 | 10/21/22 | 477 | Barnhart, Joseph N |  | 26.66
PR | 995 | 10/21/22 | 477 | Barnhart, Joseph N |  | 106.62
PR | 995 | 10/21/22 | 477 | Barnhart, Joseph N |  | 159.94
PR | 995 | 10/21/22 | 518 | Johnson, Jake E |  | 20.83
PR | 995 | 10/28/22 | 754 | Barnhart, Joseph N |  | 106.62
PR | 995 | 10/28/22 | 754 | Barnhart, Joseph N |  | 106.62
PR | 995 | 11/04/22 | 75 | Sanders, Allen O |  | 206.58
PR | 995 | 11/18/22 | 368 | Barnhart, Joseph N |  | 53.31
PR | 995 | 11/18/22 | 368 | Barnhart, Joseph N |  | 79.97
PR | 995 | 11/18/22 | 368 | Barnhart, Joseph N |  | 26.66
PR | 995 | 11/18/22 | 368 | Barnhart, Joseph N |  | 53.31
PR | 995 | 11/18/22 | 411 | Johnson, Jake E |  | 20.83
PR | 995 | 11/18/22 | 435 | Sanders, Allen O |  | 193.67
PR | 995 | 11/23/22 | 513 | Barnhart, Joseph N |  | 239.9
PR | 995 | 11/23/22 | 513 | Barnhart, Joseph N |  | 159.94
PR | 995 | 11/23/22 | 513 | Barnhart, Joseph N |  | 26.66
PR | 995 | 11/23/22 | 555 | Johnson, Jake E |  | 20.83
PR | 995 | 12/02/22 | 9 | Barnhart, Joseph N |  | 106.62
PR | 995 | 12/02/22 | 9 | Barnhart, Joseph N |  | 53.31
PR | 995 | 12/02/22 | 9 | Barnhart, Joseph N |  | 26.66
PR | 995 | 12/02/22 | 39 | Gordillo, Emanuel D |  | 18.33
PR | 995 | 12/02/22 | 44 | Holmes, Anthony R |  | 44.98
PR | 995 | 12/02/22 | 49 | Johnson, Jake E |  | 20.83
PR | 995 | 12/09/22 | 303 | Holmes, Anthony R |  | 44.98
PR | 995 | 12/23/22 | 845 | Barnhart, Joseph N |  | 119.95
PR | 995 | 12/23/22 | 845 | Barnhart, Joseph N |  | 106.62
PR | 995 | 12/23/22 | 916 | Sanders, Allen O |  | 64.56
PR | 995 | 12/30/22 | 1015 | Barnhart, Joseph N |  | 93.3
PR | 995 | 12/30/22 | 1052 | Holmes, Anthony R |  | 67.47
PR | 998 | 04/26/19 | 744 | Barnhart, Joseph N |  | 11.48
PR | 998 | 06/14/19 | 523 | Donelson, Richard T |  | 23.91
PR | 998 | 06/21/19 | 693 | Donelson, Richard T |  | 33.47
PR | 998 | 06/28/19 | 910 | Donelson, Richard T |  | 52.59
PR | 998 | 07/05/19 | 81 | Donelson, Richard T |  | 43.03
PR | 998 | 07/12/19 | 352 | Donelson, Richard T |  | 4.78
PR | 998 | 07/19/19 | 585 | Donelson, Richard T |  | 62.16
PR | 998 | 07/26/19 | 685 | Donelson, Richard T |  | 19.13
PR | 998 | 08/02/19 | 8 | Barnhart, Joseph N |  | 22.95
PR | 998 | 08/02/19 | 76 | Donelson, Richard T |  | 4.78
PR | 998 | 08/02/19 | 77 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 08/09/19 | 260 | Barnhart, Joseph N |  | 19.13
PR | 998 | 08/09/19 | 328 | Donelson, Richard T |  | 33.47
PR | 998 | 08/09/19 | 329 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 08/16/19 | 567 | Barnhart, Joseph N |  | 65.03
PR | 998 | 08/16/19 | 606 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/16/19 | 636 | Donelson, Richard T |  | 33.47
PR | 998 | 08/16/19 | 637 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 08/23/19 | 802 | Barbosa, Michael S |  | 17.75
PR | 998 | 08/23/19 | 803 | Barnhart, Joseph N |  | 65.03
PR | 998 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 3.79
PR | 998 | 08/23/19 | 843 | Martinez Reyes, Juan C |  | 60.59
PR | 998 | 08/23/19 | 847 | Paco Leyva, Orlando |  | 73.44
PR | 998 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 5.97
PR | 998 | 08/23/19 | 849 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 08/23/19 | 874 | Gerard, Jeffrey S |  | 21.04
PR | 998 | 08/30/19 | 994 | Barnhart, Joseph N |  | 57.38
PR | 998 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/30/19 | 1034 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 08/30/19 | 1038 | Paco Leyva, Orlando |  | 24.48
PR | 998 | 08/30/19 | 1040 | Ramos Herrera, Franklin J |  | 15.91
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 23.91
PR | 998 | 08/30/19 | 1064 | Donelson, Richard T |  | 4.78
PR | 998 | 08/30/19 | 1065 | Gerard, Jeffrey S |  | 16.83
PR | 998 | 09/06/19 | 15 | Barnhart, Joseph N |  | 42.08
PR | 998 | 09/06/19 | 55 | Martinez Reyes, Juan C |  | 15.15
PR | 998 | 09/06/19 | 85 | Donelson, Richard T |  | 9.56
PR | 998 | 09/06/19 | 86 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 09/13/19 | 239 | Barnhart, Joseph N |  | 72.68
PR | 998 | 09/13/19 | 278 | Martinez Reyes, Juan C |  | 42.92
PR | 998 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 4.59
PR | 998 | 09/13/19 | 282 | Paco Leyva, Orlando |  | 52.02
PR | 998 | 09/13/19 | 284 | Ramos Herrera, Franklin J |  | 35.8
PR | 998 | 09/13/19 | 308 | Donelson, Richard T |  | 57.38
PR | 998 | 09/13/19 | 309 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 09/20/19 | 476 | Barnhart, Joseph N |  | 30.6
PR | 998 | 09/20/19 | 546 | Donelson, Richard T |  | 47.81
PR | 998 | 09/20/19 | 547 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 09/27/19 | 632 | Barnhart, Joseph N |  | 130.05
PR | 998 | 09/27/19 | 632 | Barnhart, Joseph N |  | 3.83
PR | 998 | 09/27/19 | 679 | Paco Leyva, Orlando |  | 73.44
PR | 998 | 09/27/19 | 681 | Ramos Herrera, Franklin J |  | 47.74
PR | 998 | 09/27/19 | 705 | Donelson, Richard T |  | 23.91
PR | 998 | 09/27/19 | 706 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 10/04/19 | 8 | Barnhart, Joseph N |  | 76.5
PR | 998 | 10/04/19 | 8 | Barnhart, Joseph N |  | 19.13
PR | 998 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 9.18
PR | 998 | 10/04/19 | 55 | Paco Leyva, Orlando |  | 48.96
PR | 998 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 5.97
PR | 998 | 10/04/19 | 57 | Ramos Herrera, Franklin J |  | 31.82
PR | 998 | 10/04/19 | 81 | Donelson, Richard T |  | 14.34
PR | 998 | 10/04/19 | 82 | Gerard, Jeffrey S |  | 12.62
PR | 998 | 10/11/19 | 263 | Barnhart, Joseph N |  | 68.85
PR | 998 | 10/11/19 | 263 | Barnhart, Joseph N |  | 7.65
PR | 998 | 10/11/19 | 334 | Donelson, Richard T |  | 14.34
PR | 998 | 10/11/19 | 335 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 10/18/19 | 457 | Barnhart, Joseph N |  | 65.03
PR | 998 | 10/18/19 | 457 | Barnhart, Joseph N |  | 3.83
PR | 998 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 10/18/19 | 499 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 10/18/19 | 527 | Donelson, Richard T |  | 4.78
PR | 998 | 10/25/19 | 592 | Barnhart, Joseph N |  | 9.56
PR | 998 | 10/25/19 | 592 | Barnhart, Joseph N |  | 38.25
PR | 998 | 10/25/19 | 634 | Martinez Reyes, Juan C |  | 20.2
PR | 998 | 10/25/19 | 664 | Donelson, Richard T |  | 28.69
PR | 998 | 10/25/19 | 665 | Gerard, Jeffrey S |  | 8.42
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/01/19 | 8 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/01/19 | 50 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 11/01/19 | 80 | Donelson, Richard T |  | 47.81
PR | 998 | 11/01/19 | 81 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 11/08/19 | 182 | Barnhart, Joseph N |  | 95.01
PR | 998 | 11/08/19 | 182 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/08/19 | 182 | Barnhart, Joseph N |  | 8.26
PR | 998 | 11/08/19 | 211 | Holmes, Anthony R |  | 5.05
PR | 998 | 11/08/19 | 211 | Holmes, Anthony R |  | 80.78
PR | 998 | 11/08/19 | 211 | Holmes, Anthony R |  | 53.86
PR | 998 | 11/08/19 | 224 | Martinez Reyes, Juan C |  | 67.93
PR | 998 | 11/08/19 | 228 | Paco Leyva, Orlando |  | 53.86
PR | 998 | 11/08/19 | 230 | Ramos Herrera, Franklin J |  | 36.72
PR | 998 | 11/08/19 | 232 | Reyes Cruz, Denis A |  | 20.2
PR | 998 | 11/08/19 | 253 | Donelson, Richard T |  | 81.28
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 11/08/19 | 254 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 11/15/19 | 442 | Barnhart, Joseph N |  | 95.01
PR | 998 | 11/15/19 | 442 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/15/19 | 483 | Martinez Reyes, Juan C |  | 82.08
PR | 998 | 11/15/19 | 487 | Paco Leyva, Orlando |  | 26.93
PR | 998 | 11/15/19 | 489 | Ramos Herrera, Franklin J |  | 18.36
PR | 998 | 11/15/19 | 512 | Donelson, Richard T |  | 38.25
PR | 998 | 11/15/19 | 513 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 11/22/19 | 613 | Barnhart, Joseph N |  | 12.39
PR | 998 | 11/22/19 | 685 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 11/27/19 | 847 | Barnhart, Joseph N |  | 53.7
PR | 998 | 11/27/19 | 875 | Holmes, Anthony R |  | 53.86
PR | 998 | 11/27/19 | 888 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 11/27/19 | 918 | Gerard, Jeffrey S |  | 22.19
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 20.66
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 12.39
PR | 998 | 12/06/19 | 33 | Barnhart, Joseph N |  | 20.66
PR | 998 | 12/06/19 | 61 | Hoeg, Xavier A |  | 13.77
PR | 998 | 12/06/19 | 61 | Hoeg, Xavier A |  | 11.02
PR | 998 | 12/06/19 | 61 | Hoeg, Xavier A |  | 19.28
PR | 998 | 12/06/19 | 62 | Holmes, Anthony R |  | 26.93
PR | 998 | 12/06/19 | 62 | Holmes, Anthony R |  | 33.66
PR | 998 | 12/06/19 | 62 | Holmes, Anthony R |  | 47.12
PR | 998 | 12/06/19 | 104 | Donelson, Richard T |  | 23.91
PR | 998 | 12/06/19 | 105 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 16.52
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 20.66
PR | 998 | 12/13/19 | 394 | Barnhart, Joseph N |  | 12.39
PR | 998 | 12/13/19 | 422 | Hoeg, Xavier A |  | 9.64
PR | 998 | 12/13/19 | 422 | Hoeg, Xavier A |  | 34.43
PR | 998 | 12/13/19 | 423 | Holmes, Anthony R |  | 37.03
PR | 998 | 12/13/19 | 423 | Holmes, Anthony R |  | 97.61
PR | 998 | 12/13/19 | 465 | Donelson, Richard T |  | 14.34
PR | 998 | 12/13/19 | 466 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 12/20/19 | 547 | Barnhart, Joseph N |  | 33.05
PR | 998 | 12/20/19 | 547 | Barnhart, Joseph N |  | 33.05
PR | 998 | 12/20/19 | 575 | Hoeg, Xavier A |  | 2.75
PR | 998 | 12/20/19 | 576 | Holmes, Anthony R |  | 84.15
PR | 998 | 12/20/19 | 576 | Holmes, Anthony R |  | 50.49
PR | 998 | 12/20/19 | 618 | Donelson, Richard T |  | 9.56
PR | 998 | 12/27/19 | 704 | Barnhart, Joseph N |  | 16.52
PR | 998 | 12/27/19 | 704 | Barnhart, Joseph N |  | 16.52
PR | 998 | 12/27/19 | 733 | Hoeg, Xavier A |  | 15.15
PR | 998 | 12/27/19 | 733 | Hoeg, Xavier A |  | 6.89
PR | 998 | 12/27/19 | 734 | Holmes, Anthony R |  | 60.59
PR | 998 | 12/27/19 | 734 | Holmes, Anthony R |  | 20.2
PR | 998 | 12/27/19 | 776 | Donelson, Richard T |  | 4.78
PR | 998 | 01/03/20 | 36 | Hoeg, Xavier A |  | 26.16
PR | 998 | 01/03/20 | 36 | Hoeg, Xavier A |  | 6.89
PR | 998 | 01/03/20 | 37 | Holmes, Anthony R |  | 75.74
PR | 998 | 01/03/20 | 37 | Holmes, Anthony R |  | 16.83
PR | 998 | 01/03/20 | 81 | Donelson, Richard T |  | 28.69
PR | 998 | 01/10/20 | 280 | Barnhart, Joseph N |  | 45.44
PR | 998 | 01/10/20 | 280 | Barnhart, Joseph N |  | 35.11
PR | 998 | 01/10/20 | 280 | Barnhart, Joseph N |  | 16.52
PR | 998 | 01/10/20 | 309 | Hoeg, Xavier A |  | 52.33
PR | 998 | 01/10/20 | 309 | Hoeg, Xavier A |  | 2.75
PR | 998 | 01/10/20 | 310 | Holmes, Anthony R |  | 134.64
PR | 998 | 01/10/20 | 352 | Donelson, Richard T |  | 47.81
PR | 998 | 01/17/20 | 542 | Anderson, Richard P |  | 13.12
PR | 998 | 01/17/20 | 546 | Barnhart, Joseph N |  | 53.7
PR | 998 | 01/17/20 | 546 | Barnhart, Joseph N |  | 12.39
PR | 998 | 01/17/20 | 571 | Gonzalez Hernandez, Josue |  | 9.64
PR | 998 | 01/17/20 | 575 | Hoeg, Xavier A |  | 35.8
PR | 998 | 01/17/20 | 575 | Hoeg, Xavier A |  | 16.52
PR | 998 | 01/17/20 | 576 | Holmes, Anthony R |  | 97.61
PR | 998 | 01/17/20 | 576 | Holmes, Anthony R |  | 30.29
PR | 998 | 01/17/20 | 618 | Donelson, Richard T |  | 38.25
PR | 998 | 01/17/20 | 619 | Gerard, Jeffrey S |  | 17.75
PR | 998 | 01/24/20 | 675 | Anderson, Richard P |  | 59.98
PR | 998 | 01/24/20 | 679 | Barnhart, Joseph N |  | 49.57
PR | 998 | 01/24/20 | 679 | Barnhart, Joseph N |  | 16.52
PR | 998 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 44.06
PR | 998 | 01/24/20 | 703 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 01/24/20 | 707 | Hoeg, Xavier A |  | 38.56
PR | 998 | 01/24/20 | 707 | Hoeg, Xavier A |  | 16.52
PR | 998 | 01/24/20 | 708 | Holmes, Anthony R |  | 94.25
PR | 998 | 01/24/20 | 708 | Holmes, Anthony R |  | 40.39
PR | 998 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 45.29
PR | 998 | 01/24/20 | 720 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 01/24/20 | 750 | Donelson, Richard T |  | 23.91
PR | 998 | 01/24/20 | 751 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 01/31/20 | 833 | Amaya Gonzalez, Edilberto A |  | 33.05
PR | 998 | 01/31/20 | 834 | Anderson, Richard P |  | 29.99
PR | 998 | 01/31/20 | 837 | Barbosa, Michael S |  | 30.29
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 49.57
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 16.52
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 20.66
PR | 998 | 01/31/20 | 838 | Barnhart, Joseph N |  | 49.57
PR | 998 | 01/31/20 | 858 | Galdamez, Dagoberto A |  | 30.29
PR | 998 | 01/31/20 | 867 | Hoeg, Xavier A |  | 41.31
PR | 998 | 01/31/20 | 867 | Hoeg, Xavier A |  | 2.75
PR | 998 | 01/31/20 | 868 | Holmes, Anthony R |  | 50.49
PR | 998 | 01/31/20 | 868 | Holmes, Anthony R |  | 127.91
PR | 998 | 01/31/20 | 868 | Holmes, Anthony R |  | 6.73
PR | 998 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 29.72
PR | 998 | 01/31/20 | 880 | Martinez Reyes, Juan C |  | 2.83
PR | 998 | 01/31/20 | 911 | Donelson, Richard T |  | 38.25
PR | 998 | 02/07/20 | 25 | Anderson, Richard P |  | 29.99
PR | 998 | 02/07/20 | 29 | Barnhart, Joseph N |  | 61.97
PR | 998 | 02/07/20 | 29 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/07/20 | 53 | Gonzalez Hernandez, Josue |  | 22.03
PR | 998 | 02/07/20 | 56 | Hernandez Gonzalez, Osbaldo |  | 24.1
PR | 998 | 02/07/20 | 57 | Hoeg, Xavier A |  | 44.06
PR | 998 | 02/07/20 | 57 | Hoeg, Xavier A |  | 2.75
PR | 998 | 02/07/20 | 57 | Hoeg, Xavier A |  | 8.26
PR | 998 | 02/07/20 | 58 | Holmes, Anthony R |  | 97.61
PR | 998 | 02/07/20 | 58 | Holmes, Anthony R |  | 13.46
PR | 998 | 02/07/20 | 58 | Holmes, Anthony R |  | 20.2
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 16.52
PR | 998 | 02/07/20 | 61 | Hubbard, Robert W |  | 16.52
PR | 998 | 02/07/20 | 65 | Lee, Ha Nul |  | 20.08
PR | 998 | 02/07/20 | 70 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/07/20 | 102 | Donelson, Richard T |  | 9.56
PR | 998 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 02/07/20 | 103 | Gerard, Jeffrey S |  | 8.87
PR | 998 | 02/14/20 | 239 | Barnhart, Joseph N |  | 33.05
PR | 998 | 02/14/20 | 239 | Barnhart, Joseph N |  | 4.13
PR | 998 | 02/14/20 | 267 | Hoeg, Xavier A |  | 38.56
PR | 998 | 02/14/20 | 267 | Hoeg, Xavier A |  | 16.52
PR | 998 | 02/14/20 | 268 | Holmes, Anthony R |  | 80.78
PR | 998 | 02/14/20 | 268 | Holmes, Anthony R |  | 53.86
PR | 998 | 02/14/20 | 312 | Donelson, Richard T |  | 4.78
PR | 998 | 02/14/20 | 313 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/21/20 | 456 | Barnhart, Joseph N |  | 12.39
PR | 998 | 02/21/20 | 456 | Barnhart, Joseph N |  | 16.52
PR | 998 | 02/21/20 | 456 | Barnhart, Joseph N |  | 16.52
PR | 998 | 02/21/20 | 482 | Hoeg, Xavier A |  | 33.05
PR | 998 | 02/21/20 | 482 | Hoeg, Xavier A |  | 13.77
PR | 998 | 02/21/20 | 482 | Hoeg, Xavier A |  | 8.26
PR | 998 | 02/21/20 | 483 | Holmes, Anthony R |  | 53.86
PR | 998 | 02/21/20 | 483 | Holmes, Anthony R |  | 33.66
PR | 998 | 02/21/20 | 483 | Holmes, Anthony R |  | 20.2
PR | 998 | 02/21/20 | 528 | Donelson, Richard T |  | 14.34
PR | 998 | 02/21/20 | 529 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 30.98
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 24.79
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 33.05
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 16.52
PR | 998 | 02/28/20 | 684 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/28/20 | 712 | Hoeg, Xavier A |  | 26.16
PR | 998 | 02/28/20 | 712 | Hoeg, Xavier A |  | 17.9
PR | 998 | 02/28/20 | 713 | Holmes, Anthony R |  | 25.25
PR | 998 | 02/28/20 | 713 | Holmes, Anthony R |  | 90.88
PR | 998 | 02/28/20 | 713 | Holmes, Anthony R |  | 43.76
PR | 998 | 02/28/20 | 724 | Martinez Reyes, Juan C |  | 22.64
PR | 998 | 02/28/20 | 728 | Paco Leyva, Orlando |  | 20.2
PR | 998 | 02/28/20 | 728 | Paco Leyva, Orlando |  | 3.37
PR | 998 | 02/28/20 | 732 | Ramos Herrera, Franklin J |  | 11.48
PR | 998 | 02/28/20 | 758 | Gerard, Jeffrey S |  | 13.31
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 41.31
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 4.13
PR | 998 | 03/06/20 | 46 | Barnhart, Joseph N |  | 16.52
PR | 998 | 03/06/20 | 74 | Hoeg, Xavier A |  | 30.29
PR | 998 | 03/06/20 | 74 | Hoeg, Xavier A |  | 6.89
PR | 998 | 03/06/20 | 74 | Hoeg, Xavier A |  | 6.89
PR | 998 | 03/06/20 | 75 | Holmes, Anthony R |  | 50.49
PR | 998 | 03/06/20 | 75 | Holmes, Anthony R |  | 70.69
PR | 998 | 03/06/20 | 75 | Holmes, Anthony R |  | 13.46
PR | 998 | 03/06/20 | 78 | Hubbard, Robert W |  | 8.26
PR | 998 | 03/06/20 | 119 | Donelson, Richard T |  | 19.13
PR | 998 | 03/06/20 | 120 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 12.39
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 8.26
PR | 998 | 03/13/20 | 311 | Barnhart, Joseph N |  | 49.57
PR | 998 | 03/13/20 | 338 | Hoeg, Xavier A |  | 41.31
PR | 998 | 03/13/20 | 338 | Hoeg, Xavier A |  | 13.77
PR | 998 | 03/13/20 | 339 | Holmes, Anthony R |  | 47.12
PR | 998 | 03/13/20 | 339 | Holmes, Anthony R |  | 87.52
PR | 998 | 03/13/20 | 383 | Donelson, Richard T |  | 33.47
PR | 998 | 03/13/20 | 384 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I |  | 96.39
PR | 998 | 03/20/20 | 567 | Balderas Ortiz, Ricardo I |  | 5.51
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 45.44
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 12.39
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 24.79
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 12.39
PR | 998 | 03/20/20 | 569 | Barnhart, Joseph N |  | 28.92
PR | 998 | 03/20/20 | 596 | Hoeg, Xavier A |  | 27.54
PR | 998 | 03/20/20 | 596 | Hoeg, Xavier A |  | 8.26
PR | 998 | 03/20/20 | 596 | Hoeg, Xavier A |  | 19.28
PR | 998 | 03/20/20 | 597 | Holmes, Anthony R |  | 33.66
PR | 998 | 03/20/20 | 597 | Holmes, Anthony R |  | 43.76
PR | 998 | 03/20/20 | 597 | Holmes, Anthony R |  | 57.22
PR | 998 | 03/20/20 | 600 | Hubbard, Robert W |  | 16.52
PR | 998 | 03/20/20 | 622 | Rodriguez Arevalos, Christian |  | 80.33
PR | 998 | 03/20/20 | 622 | Rodriguez Arevalos, Christian |  | 4.59
PR | 998 | 03/20/20 | 632 | Taylor, Evan R |  | 85.83
PR | 998 | 03/20/20 | 632 | Taylor, Evan R |  | 15.15
PR | 998 | 03/20/20 | 638 | Waites, Thaddeus Z |  | 127.45
PR | 998 | 03/20/20 | 638 | Waites, Thaddeus Z |  | 22.49
PR | 998 | 03/20/20 | 641 | Donelson, Richard T |  | 14.34
PR | 998 | 03/20/20 | 642 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 03/26/20 | 748 | Anderson, Richard P |  | 8.43
PR | 998 | 03/26/20 | 748 | Anderson, Richard P |  | 14.99
PR | 998 | 03/26/20 | 750 | Balderas Ortiz, Ricardo I |  | 22.03
PR | 998 | 03/26/20 | 752 | Barnhart, Joseph N |  | 20.66
PR | 998 | 03/26/20 | 778 | Hoeg, Xavier A |  | 19.28
PR | 998 | 03/26/20 | 778 | Hoeg, Xavier A |  | 2.75
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 50.49
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 10.1
PR | 998 | 03/26/20 | 779 | Holmes, Anthony R |  | 13.46
PR | 998 | 03/26/20 | 811 | Taylor, Evan R |  | 40.39
PR | 998 | 03/26/20 | 817 | Waites, Thaddeus Z |  | 59.98
PR | 998 | 03/26/20 | 820 | Donelson, Richard T |  | 9.56
PR | 998 | 03/26/20 | 820 | Donelson, Richard T |  | 4.78
PR | 998 | 03/26/20 | 821 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 04/03/20 | 42 | Donelson, Richard T |  | 9.56
PR | 998 | 04/10/20 | 64 | Barnhart, Joseph N |  | 8.26
PR | 998 | 04/10/20 | 99 | Donelson, Richard T |  | 19.13
PR | 998 | 04/17/20 | 216 | Barnhart, Joseph N |  | 24.79
PR | 998 | 04/17/20 | 288 | Donelson, Richard T |  | 9.56
PR | 998 | 04/24/20 | 352 | Barnhart, Joseph N |  | 12.39
PR | 998 | 05/08/20 | 231 | Donelson, Richard T |  | 4.78
PR | 998 | 06/05/20 | 18 | Barnhart, Joseph N |  | 16.52
PR | 998 | 06/05/20 | 67 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 06/12/20 | 221 | Barnhart, Joseph N |  | 12.39
PR | 998 | 06/26/20 | 521 | Barnhart, Joseph N |  | 16.52
PR | 998 | 06/26/20 | 521 | Barnhart, Joseph N |  | 16.52
PR | 998 | 06/26/20 | 560 | Stahlschmidt, John P |  | 13.46
PR | 998 | 06/26/20 | 563 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 12.39
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 49.57
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 33.05
PR | 998 | 07/02/20 | 7 | Barnhart, Joseph N |  | 8.26
PR | 998 | 07/02/20 | 46 | Stahlschmidt, John P |  | 67.32
PR | 998 | 07/02/20 | 49 | Waites, Thaddeus Z |  | 149.94
PR | 998 | 07/02/20 | 50 | Donelson, Richard T |  | 23.91
PR | 998 | 07/10/20 | 140 | Barnhart, Joseph N |  | 12.39
PR | 998 | 07/10/20 | 175 | Ross, Kelli M |  | 52.63
PR | 998 | 07/10/20 | 178 | Stahlschmidt, John P |  | 13.46
PR | 998 | 07/10/20 | 178 | Stahlschmidt, John P |  | 26.93
PR | 998 | 07/10/20 | 181 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 07/10/20 | 181 | Waites, Thaddeus Z |  | 59.98
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 8.26
PR | 998 | 07/17/20 | 265 | Barnhart, Joseph N |  | 24.79
PR | 998 | 07/17/20 | 305 | Stahlschmidt, John P |  | 13.46
PR | 998 | 07/17/20 | 305 | Stahlschmidt, John P |  | 13.46
PR | 998 | 07/17/20 | 308 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 07/17/20 | 308 | Waites, Thaddeus Z |  | 29.99
PR | 998 | 07/17/20 | 310 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/24/20 | 404 | Barnhart, Joseph N |  | 24.79
PR | 998 | 07/24/20 | 448 | Donelson, Richard T |  | 23.91
PR | 998 | 07/24/20 | 449 | Gerard, Jeffrey S |  | 4.44
PR | 998 | 07/31/20 | 499 | Barnhart, Joseph N |  | 66.1
PR | 998 | 07/31/20 | 543 | Donelson, Richard T |  | 14.34
PR | 998 | 08/07/20 | 128 | Donelson, Richard T |  | 47.81
PR | 998 | 08/14/20 | 332 | Donelson, Richard T |  | 33.47
PR | 998 | 08/21/20 | 459 | Donelson, Richard T |  | 19.13
PR | 998 | 08/28/20 | 604 | Donelson, Richard T |  | 4.78
PR | 998 | 09/04/20 | 49 | Donelson, Richard T |  | 4.78
PR | 998 | 10/09/20 | 198 | Donelson, Richard T |  | 9.56
PR | 998 | 11/13/20 | 189 | Barnhart, Joseph N |  | 16.52
PR | 998 | 11/13/20 | 230 | Donelson, Richard T |  | 14.34
PR | 998 | 12/31/20 | 627 | Donelson, Richard T |  | 4.78
PR | 998 | 01/08/21 | 52 | Donelson, Richard T |  | 4.78
PR | 998 | 01/15/21 | 171 | Donelson, Richard T |  | 9.56
PR | 998 | 01/22/21 | 261 | Barnhart, Joseph N |  | 20.66
PR | 998 | 01/22/21 | 280 | Holmes, Anthony R |  | 70.69
PR | 998 | 01/22/21 | 306 | Donelson, Richard T |  | 9.56
PR | 998 | 01/29/21 | 386 | Barnhart, Joseph N |  | 61.97
PR | 998 | 01/29/21 | 404 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 01/29/21 | 406 | Holmes, Anthony R |  | 134.64
PR | 998 | 01/29/21 | 410 | Lee, Ha Nul |  | 76.5
PR | 998 | 01/29/21 | 421 | Rodriguez Arevalos, Christian |  | 55.08
PR | 998 | 01/29/21 | 431 | Waites, Thaddeus Z |  | 89.96
PR | 998 | 01/29/21 | 432 | Donelson, Richard T |  | 4.78
PR | 998 | 02/05/21 | 71 | Barnhart, Joseph N |  | 20.66
PR | 998 | 02/05/21 | 71 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/05/21 | 71 | Barnhart, Joseph N |  | 4.13
PR | 998 | 02/05/21 | 90 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 02/05/21 | 91 | Gordillo, Emanuel D |  | 39.17
PR | 998 | 02/05/21 | 91 | Gordillo, Emanuel D |  | 9.79
PR | 998 | 02/05/21 | 93 | Holmes, Anthony R |  | 107.71
PR | 998 | 02/05/21 | 93 | Holmes, Anthony R |  | 26.93
PR | 998 | 02/05/21 | 97 | Lee, Ha Nul |  | 76.5
PR | 998 | 02/05/21 | 109 | Rodriguez Arevalos, Christian |  | 91.8
PR | 998 | 02/05/21 | 119 | Waites, Thaddeus Z |  | 119.95
PR | 998 | 02/05/21 | 121 | Donelson, Richard T |  | 4.78
PR | 998 | 02/12/21 | 256 | Barnhart, Joseph N |  | 24.79
PR | 998 | 02/12/21 | 256 | Barnhart, Joseph N |  | 16.52
PR | 998 | 02/12/21 | 276 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 14.69
PR | 998 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 24.48
PR | 998 | 02/12/21 | 277 | Gordillo, Emanuel D |  | 9.79
PR | 998 | 02/12/21 | 279 | Holmes, Anthony R |  | 107.71
PR | 998 | 02/12/21 | 279 | Holmes, Anthony R |  | 26.93
PR | 998 | 02/12/21 | 283 | Lee, Ha Nul |  | 76.5
PR | 998 | 02/12/21 | 295 | Rodriguez Arevalos, Christian |  | 73.44
PR | 998 | 02/12/21 | 305 | Waites, Thaddeus Z |  | 119.95
PR | 998 | 02/12/21 | 307 | Donelson, Richard T |  | 14.34
PR | 998 | 02/19/21 | 441 | Gonzalez Hernandez, Josue |  | 79.87
PR | 998 | 02/19/21 | 442 | Gordillo, Emanuel D |  | 39.17
PR | 998 | 02/19/21 | 442 | Gordillo, Emanuel D |  | 9.79
PR | 998 | 02/19/21 | 444 | Holmes, Anthony R |  | 107.71
PR | 998 | 02/19/21 | 444 | Holmes, Anthony R |  | 26.93
PR | 998 | 02/19/21 | 448 | Lee, Ha Nul |  | 76.5
PR | 998 | 02/19/21 | 462 | Rodriguez Arevalos, Christian |  | 91.8
PR | 998 | 02/19/21 | 472 | Waites, Thaddeus Z |  | 119.95
PR | 998 | 02/26/21 | 597 | Barnhart, Joseph N |  | 8.26
PR | 998 | 02/26/21 | 618 | Gonzalez Hernandez, Josue |  | 110.16
PR | 998 | 02/26/21 | 619 | Gordillo, Emanuel D |  | 48.96
PR | 998 | 02/26/21 | 621 | Holmes, Anthony R |  | 80.78
PR | 998 | 02/26/21 | 621 | Holmes, Anthony R |  | 53.86
PR | 998 | 02/26/21 | 625 | Lee, Ha Nul |  | 76.5
PR | 998 | 02/26/21 | 648 | Waites, Thaddeus Z |  | 134.95
PR | 998 | 02/26/21 | 648 | Waites, Thaddeus Z |  | 14.99
PR | 998 | 02/26/21 | 649 | Donelson, Richard T |  | 4.78
PR | 998 | 03/05/21 | 76 | Gonzalez Hernandez, Josue |  | 88.13
PR | 998 | 03/05/21 | 77 | Gordillo, Emanuel D |  | 29.38
PR | 998 | 03/05/21 | 77 | Gordillo, Emanuel D |  | 19.58
PR | 998 | 03/05/21 | 79 | Holmes, Anthony R |  | 121.18
PR | 998 | 03/05/21 | 79 | Holmes, Anthony R |  | 13.46
PR | 998 | 03/05/21 | 83 | Lee, Ha Nul |  | 76.5
PR | 998 | 03/05/21 | 106 | Waites, Thaddeus Z |  | 149.94
PR | 998 | 03/12/21 | 201 | Gonzalez Hernandez, Josue |  | 74.36
PR | 998 | 03/12/21 | 201 | Gonzalez Hernandez, Josue |  | 35.8
PR | 998 | 03/12/21 | 202 | Gordillo, Emanuel D |  | 48.96
PR | 998 | 03/12/21 | 205 | Holmes, Anthony R |  | 124.54
PR | 998 | 03/12/21 | 205 | Holmes, Anthony R |  | 10.1
PR | 998 | 03/12/21 | 209 | Lee, Ha Nul |  | 51.64
PR | 998 | 03/12/21 | 209 | Lee, Ha Nul |  | 24.86
PR | 998 | 03/12/21 | 231 | Waites, Thaddeus Z |  | 149.94
PR | 998 | 03/19/21 | 291 | Barnhart, Joseph N |  | 8.57
PR | 998 | 03/19/21 | 291 | Barnhart, Joseph N |  | 12.85
PR | 998 | 03/19/21 | 314 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 03/19/21 | 315 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 03/19/21 | 318 | Holmes, Anthony R |  | 140.76
PR | 998 | 03/19/21 | 322 | Lee, Ha Nul |  | 82.62
PR | 998 | 03/19/21 | 345 | Waites, Thaddeus Z |  | 91.8
PR | 998 | 03/19/21 | 345 | Waites, Thaddeus Z |  | 61.2
PR | 998 | 03/19/21 | 346 | Donelson, Richard T |  | 4.78
PR | 998 | 03/26/21 | 545 | Gonzalez Hernandez, Josue |  | 93.02
PR | 998 | 03/26/21 | 546 | Gordillo, Emanuel D |  | 45.52
PR | 998 | 03/26/21 | 546 | Gordillo, Emanuel D |  | 6.5
PR | 998 | 03/26/21 | 549 | Holmes, Anthony R |  | 140.76
PR | 998 | 03/26/21 | 553 | Lee, Ha Nul |  | 78.49
PR | 998 | 03/26/21 | 577 | Waites, Thaddeus Z |  | 153
PR | 998 | 04/02/21 | 7 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/02/21 | 7 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/02/21 | 30 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 04/02/21 | 31 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 04/02/21 | 34 | Holmes, Anthony R |  | 66.86
PR | 998 | 04/02/21 | 34 | Holmes, Anthony R |  | 73.9
PR | 998 | 04/02/21 | 38 | Lee, Ha Nul |  | 82.62
PR | 998 | 04/02/21 | 62 | Waites, Thaddeus Z |  | 26.78
PR | 998 | 04/02/21 | 62 | Waites, Thaddeus Z |  | 3.83
PR | 998 | 04/02/21 | 64 | Donelson, Richard T |  | 4.78
PR | 998 | 04/09/21 | 134 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 27.31
PR | 998 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 23.41
PR | 998 | 04/09/21 | 135 | Gordillo, Emanuel D |  | 1.3
PR | 998 | 04/09/21 | 138 | Holmes, Anthony R |  | 73.9
PR | 998 | 04/09/21 | 138 | Holmes, Anthony R |  | 63.34
PR | 998 | 04/09/21 | 138 | Holmes, Anthony R |  | 3.52
PR | 998 | 04/09/21 | 142 | Lee, Ha Nul |  | 82.62
PR | 998 | 04/09/21 | 167 | Donelson, Richard T |  | 23.91
PR | 998 | 04/16/21 | 278 | Gonzalez Hernandez, Josue |  | 93.02
PR | 998 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 10.4
PR | 998 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 24.71
PR | 998 | 04/16/21 | 279 | Gordillo, Emanuel D |  | 16.91
PR | 998 | 04/16/21 | 284 | Holmes, Anthony R |  | 59.82
PR | 998 | 04/16/21 | 284 | Holmes, Anthony R |  | 24.63
PR | 998 | 04/16/21 | 284 | Holmes, Anthony R |  | 35.19
PR | 998 | 04/16/21 | 284 | Holmes, Anthony R |  | 3.52
PR | 998 | 04/16/21 | 284 | Holmes, Anthony R |  | 17.6
PR | 998 | 04/16/21 | 287 | Lee, Ha Nul |  | 82.62
PR | 998 | 04/16/21 | 290 | Lovo, German G |  | 80.78
PR | 998 | 04/16/21 | 310 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 04/16/21 | 311 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 04/16/21 | 314 | Donelson, Richard T |  | 38.25
PR | 998 | 04/16/21 | 314 | Donelson, Richard T |  | 9.56
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 12.85
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 4.28
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 4.28
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/23/21 | 404 | Barnhart, Joseph N |  | 4.28
PR | 998 | 04/23/21 | 429 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 04/23/21 | 430 | Gordillo, Emanuel D |  | 41.62
PR | 998 | 04/23/21 | 430 | Gordillo, Emanuel D |  | 10.4
PR | 998 | 04/23/21 | 432 | Gutierrez, Brian A |  | 31.82
PR | 998 | 04/23/21 | 436 | Holmes, Anthony R |  | 137.24
PR | 998 | 04/23/21 | 436 | Holmes, Anthony R |  | 3.52
PR | 998 | 04/23/21 | 439 | Lee, Ha Nul |  | 49.57
PR | 998 | 04/23/21 | 439 | Lee, Ha Nul |  | 33.05
PR | 998 | 04/23/21 | 441 | Lovo, German G |  | 100.98
PR | 998 | 04/23/21 | 449 | Platero Navas, Julio A |  | 33.05
PR | 998 | 04/23/21 | 463 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 04/23/21 | 464 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 04/23/21 | 466 | Donelson, Richard T |  | 9.56
PR | 998 | 04/30/21 | 574 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/30/21 | 574 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/30/21 | 574 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/30/21 | 574 | Barnhart, Joseph N |  | 8.57
PR | 998 | 04/30/21 | 599 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 04/30/21 | 600 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 04/30/21 | 606 | Holmes, Anthony R |  | 133.72
PR | 998 | 04/30/21 | 606 | Holmes, Anthony R |  | 7.04
PR | 998 | 04/30/21 | 609 | Lee, Ha Nul |  | 82.62
PR | 998 | 04/30/21 | 611 | Lovo, German G |  | 100.98
PR | 998 | 04/30/21 | 620 | Platero Navas, Julio A |  | 55.08
PR | 998 | 04/30/21 | 634 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 04/30/21 | 635 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 04/30/21 | 637 | Donelson, Richard T |  | 19.13
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 12.85
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 17.14
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/07/21 | 41 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/07/21 | 66 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 05/07/21 | 67 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 05/07/21 | 73 | Holmes, Anthony R |  | 140.76
PR | 998 | 05/07/21 | 77 | Lee, Ha Nul |  | 82.62
PR | 998 | 05/07/21 | 79 | Lovo, German G |  | 80.78
PR | 998 | 05/07/21 | 88 | Platero Navas, Julio A |  | 55.08
PR | 998 | 05/07/21 | 102 | Velasquez Cruz, Denis M |  | 90.58
PR | 998 | 05/07/21 | 103 | Velasquez Cruz, Osman N |  | 78.34
PR | 998 | 05/07/21 | 106 | Donelson, Richard T |  | 38.25
PR | 998 | 05/14/21 | 246 | Barnhart, Joseph N |  | 21.42
PR | 998 | 05/14/21 | 246 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/14/21 | 246 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/14/21 | 246 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/14/21 | 270 | Gonzalez Hernandez, Josue |  | 61.05
PR | 998 | 05/14/21 | 270 | Gonzalez Hernandez, Josue |  | 20.35
PR | 998 | 05/14/21 | 271 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 05/14/21 | 276 | Holmes, Anthony R |  | 126.68
PR | 998 | 05/14/21 | 276 | Holmes, Anthony R |  | 10.56
PR | 998 | 05/14/21 | 276 | Holmes, Anthony R |  | 3.52
PR | 998 | 05/14/21 | 278 | Hubbard, Robert W |  | 54.7
PR | 998 | 05/14/21 | 280 | Lee, Ha Nul |  | 80.55
PR | 998 | 05/14/21 | 280 | Lee, Ha Nul |  | 2.07
PR | 998 | 05/14/21 | 283 | Lovo, German G |  | 100.98
PR | 998 | 05/14/21 | 292 | Platero Navas, Julio A |  | 33.05
PR | 998 | 05/14/21 | 292 | Platero Navas, Julio A |  | 22.03
PR | 998 | 05/14/21 | 306 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 05/14/21 | 307 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 05/14/21 | 310 | Donelson, Richard T |  | 14.34
PR | 998 | 05/21/21 | 391 | Barnhart, Joseph N |  | 25.7
PR | 998 | 05/21/21 | 391 | Barnhart, Joseph N |  | 12.85
PR | 998 | 05/21/21 | 391 | Barnhart, Joseph N |  | 4.28
PR | 998 | 05/21/21 | 415 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 05/21/21 | 416 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 05/21/21 | 422 | Holmes, Anthony R |  | 140.76
PR | 998 | 05/21/21 | 426 | Lee, Ha Nul |  | 82.62
PR | 998 | 05/21/21 | 429 | Lovo, German G |  | 80.78
PR | 998 | 05/21/21 | 438 | Platero Navas, Julio A |  | 55.08
PR | 998 | 05/21/21 | 452 | Velasquez Cruz, Denis M |  | 90.58
PR | 998 | 05/21/21 | 453 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 05/21/21 | 456 | Donelson, Richard T |  | 9.56
PR | 998 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 93.02
PR | 998 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 20.35
PR | 998 | 05/28/21 | 656 | Gonzalez Hernandez, Josue |  | 2.91
PR | 998 | 05/28/21 | 657 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 05/28/21 | 663 | Holmes, Anthony R |  | 133.72
PR | 998 | 05/28/21 | 663 | Holmes, Anthony R |  | 3.52
PR | 998 | 05/28/21 | 663 | Holmes, Anthony R |  | 3.52
PR | 998 | 05/28/21 | 665 | Hubbard, Robert W |  | 21.04
PR | 998 | 05/28/21 | 665 | Hubbard, Robert W |  | 12.62
PR | 998 | 05/28/21 | 667 | Lee, Ha Nul |  | 49.57
PR | 998 | 05/28/21 | 667 | Lee, Ha Nul |  | 33.05
PR | 998 | 05/28/21 | 670 | Lovo, German G |  | 100.98
PR | 998 | 05/28/21 | 680 | Platero Navas, Julio A |  | 44.06
PR | 998 | 05/28/21 | 680 | Platero Navas, Julio A |  | 9.64
PR | 998 | 05/28/21 | 680 | Platero Navas, Julio A |  | 1.38
PR | 998 | 05/28/21 | 681 | Platero Navas, Mario N |  | 20.81
PR | 998 | 05/28/21 | 695 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 05/28/21 | 696 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 05/28/21 | 700 | Donelson, Richard T |  | 4.78
PR | 998 | 06/04/21 | 56 | Gonzalez Hernandez, Josue |  | 93.02
PR | 998 | 06/04/21 | 57 | Gordillo, Emanuel D |  | 41.62
PR | 998 | 06/04/21 | 63 | Holmes, Anthony R |  | 112.61
PR | 998 | 06/04/21 | 67 | Lee, Ha Nul |  | 45.44
PR | 998 | 06/04/21 | 67 | Lee, Ha Nul |  | 20.66
PR | 998 | 06/04/21 | 70 | Lovo, German G |  | 60.59
PR | 998 | 06/04/21 | 81 | Platero Navas, Julio A |  | 44.06
PR | 998 | 06/04/21 | 82 | Platero Navas, Mario N |  | 41.62
PR | 998 | 06/04/21 | 95 | Velasquez Cruz, Denis M |  | 67.93
PR | 998 | 06/04/21 | 96 | Velasquez Cruz, Osman N |  | 58.75
PR | 998 | 06/04/21 | 99 | Donelson, Richard T |  | 19.13
PR | 998 | 06/11/21 | 203 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/11/21 | 203 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/11/21 | 203 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/11/21 | 203 | Barnhart, Joseph N |  | 4.28
PR | 998 | 06/11/21 | 213 | Cruz, Azael S |  | 49.57
PR | 998 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 23.26
PR | 998 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 40.7
PR | 998 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 06/11/21 | 229 | Gonzalez Hernandez, Josue |  | 5.81
PR | 998 | 06/11/21 | 230 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 06/11/21 | 236 | Holmes, Anthony R |  | 35.19
PR | 998 | 06/11/21 | 236 | Holmes, Anthony R |  | 95.01
PR | 998 | 06/11/21 | 236 | Holmes, Anthony R |  | 10.56
PR | 998 | 06/11/21 | 238 | Hubbard, Robert W |  | 67.32
PR | 998 | 06/11/21 | 240 | Lee, Ha Nul |  | 82.62
PR | 998 | 06/11/21 | 243 | Lovo, German G |  | 100.98
PR | 998 | 06/11/21 | 250 | Ortiz Carmona, Jose |  | 58.75
PR | 998 | 06/11/21 | 253 | Platero Navas, Julio A |  | 55.08
PR | 998 | 06/11/21 | 254 | Platero Navas, Mario N |  | 41.62
PR | 998 | 06/11/21 | 267 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 06/11/21 | 268 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 06/11/21 | 270 | Donelson, Richard T |  | 38.25
PR | 998 | 06/11/21 | 271 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 06/18/21 | 410 | Castro Hernandez, Jose A |  | 26.93
PR | 998 | 06/18/21 | 415 | Cruz, Azael S |  | 82.62
PR | 998 | 06/18/21 | 431 | Gonzalez Hernandez, Josue |  | 69.77
PR | 998 | 06/18/21 | 432 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 06/18/21 | 438 | Holmes, Anthony R |  | 98.53
PR | 998 | 06/18/21 | 438 | Holmes, Anthony R |  | 42.23
PR | 998 | 06/18/21 | 440 | Hubbard, Robert W |  | 50.49
PR | 998 | 06/18/21 | 442 | Lee, Ha Nul |  | 78.49
PR | 998 | 06/18/21 | 442 | Lee, Ha Nul |  | 4.13
PR | 998 | 06/18/21 | 445 | Lovo, German G |  | 100.98
PR | 998 | 06/18/21 | 452 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 06/18/21 | 455 | Platero Navas, Julio A |  | 55.08
PR | 998 | 06/18/21 | 456 | Platero Navas, Mario N |  | 52.02
PR | 998 | 06/18/21 | 471 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 06/18/21 | 472 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 06/18/21 | 475 | Donelson, Richard T |  | 23.91
PR | 998 | 06/25/21 | 610 | Cruz, Azael S |  | 82.62
PR | 998 | 06/25/21 | 626 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 06/25/21 | 626 | Gonzalez Hernandez, Josue |  | 69.77
PR | 998 | 06/25/21 | 627 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 06/25/21 | 629 | Gutierrez, Brian A |  | 21.88
PR | 998 | 06/25/21 | 633 | Holmes, Anthony R |  | 38.71
PR | 998 | 06/25/21 | 633 | Holmes, Anthony R |  | 102.05
PR | 998 | 06/25/21 | 635 | Hubbard, Robert W |  | 42.08
PR | 998 | 06/25/21 | 635 | Hubbard, Robert W |  | 16.83
PR | 998 | 06/25/21 | 637 | Lee, Ha Nul |  | 66.1
PR | 998 | 06/25/21 | 637 | Lee, Ha Nul |  | 16.52
PR | 998 | 06/25/21 | 640 | Lovo, German G |  | 100.98
PR | 998 | 06/25/21 | 647 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 06/25/21 | 650 | Platero Navas, Julio A |  | 22.03
PR | 998 | 06/25/21 | 650 | Platero Navas, Julio A |  | 33.05
PR | 998 | 06/25/21 | 651 | Platero Navas, Mario N |  | 52.02
PR | 998 | 06/25/21 | 666 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 06/25/21 | 667 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 06/25/21 | 669 | Gutierrez, Brian A |  | -21.88
PR | 998 | 06/25/21 | 670 | Hubbard, Robert W |  | 8.42
PR | 998 | 06/25/21 | 672 | Donelson, Richard T |  | 4.78
PR | 998 | 07/02/21 | 19 | Cruz, Azael S |  | 73.33
PR | 998 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 15.99
PR | 998 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 07/02/21 | 35 | Gonzalez Hernandez, Josue |  | 46.51
PR | 998 | 07/02/21 | 36 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 07/02/21 | 40 | Holmes, Anthony R |  | 95.01
PR | 998 | 07/02/21 | 40 | Holmes, Anthony R |  | 45.75
PR | 998 | 07/02/21 | 42 | Hubbard, Robert W |  | 37.87
PR | 998 | 07/02/21 | 42 | Hubbard, Robert W |  | 10.52
PR | 998 | 07/02/21 | 44 | Lee, Ha Nul |  | 60.93
PR | 998 | 07/02/21 | 44 | Lee, Ha Nul |  | 12.39
PR | 998 | 07/02/21 | 47 | Lovo, German G |  | 80.78
PR | 998 | 07/02/21 | 55 | Ortiz Carmona, Jose |  | 37.94
PR | 998 | 07/02/21 | 55 | Ortiz Carmona, Jose |  | 48.96
PR | 998 | 07/02/21 | 58 | Platero Navas, Julio A |  | 29.61
PR | 998 | 07/02/21 | 58 | Platero Navas, Julio A |  | 22.03
PR | 998 | 07/02/21 | 59 | Platero Navas, Mario N |  | 48.77
PR | 998 | 07/02/21 | 74 | Velasquez Cruz, Denis M |  | 100.48
PR | 998 | 07/02/21 | 75 | Velasquez Cruz, Osman N |  | 86.9
PR | 998 | 07/02/21 | 78 | Donelson, Richard T |  | 9.56
PR | 998 | 07/09/21 | 114 | Cruz, Azael S |  | 61.97
PR | 998 | 07/09/21 | 130 | Gonzalez Hernandez, Josue |  | 20.35
PR | 998 | 07/09/21 | 130 | Gonzalez Hernandez, Josue |  | 69.77
PR | 998 | 07/09/21 | 131 | Gordillo, Emanuel D |  | 36.41
PR | 998 | 07/09/21 | 135 | Holmes, Anthony R |  | 84.46
PR | 998 | 07/09/21 | 135 | Holmes, Anthony R |  | 14.08
PR | 998 | 07/09/21 | 137 | Hubbard, Robert W |  | 50.49
PR | 998 | 07/09/21 | 137 | Hubbard, Robert W |  | 16.83
PR | 998 | 07/09/21 | 139 | Lee, Ha Nul |  | 41.31
PR | 998 | 07/09/21 | 142 | Lovo, German G |  | 80.78
PR | 998 | 07/09/21 | 150 | Ortiz Carmona, Jose |  | 73.44
PR | 998 | 07/09/21 | 153 | Platero Navas, Julio A |  | 44.06
PR | 998 | 07/09/21 | 154 | Platero Navas, Mario N |  | 41.62
PR | 998 | 07/09/21 | 165 | Sepulveda Gonzalez, Alfredo |  | 103.28
PR | 998 | 07/09/21 | 171 | Velasquez Cruz, Denis M |  | 84.92
PR | 998 | 07/09/21 | 172 | Velasquez Cruz, Osman N |  | 73.44
PR | 998 | 07/16/21 | 322 | Barnhart, Joseph N |  | 8.57
PR | 998 | 07/16/21 | 322 | Barnhart, Joseph N |  | 8.57
PR | 998 | 07/16/21 | 322 | Barnhart, Joseph N |  | 8.57
PR | 998 | 07/16/21 | 322 | Barnhart, Joseph N |  | 8.57
PR | 998 | 07/16/21 | 332 | Cruz, Azael S |  | 82.62
PR | 998 | 07/16/21 | 348 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 07/16/21 | 353 | Holmes, Anthony R |  | 140.76
PR | 998 | 07/16/21 | 357 | Lee, Ha Nul |  | 82.62
PR | 998 | 07/16/21 | 360 | Lovo, German G |  | 100.98
PR | 998 | 07/16/21 | 368 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 07/16/21 | 371 | Platero Navas, Julio A |  | 55.08
PR | 998 | 07/16/21 | 372 | Platero Navas, Mario N |  | 31.21
PR | 998 | 07/16/21 | 372 | Platero Navas, Mario N |  | 20.81
PR | 998 | 07/16/21 | 383 | Sepulveda Gonzalez, Alfredo |  | 122.21
PR | 998 | 07/16/21 | 389 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 07/16/21 | 390 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 07/16/21 | 393 | Donelson, Richard T |  | 19.13
PR | 998 | 07/23/21 | 493 | Barnhart, Joseph N |  | 12.85
PR | 998 | 07/23/21 | 493 | Barnhart, Joseph N |  | 17.14
PR | 998 | 07/23/21 | 503 | Cruz, Azael S |  | 82.62
PR | 998 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 93.02
PR | 998 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 11.63
PR | 998 | 07/23/21 | 519 | Gonzalez Hernandez, Josue |  | 11.63
PR | 998 | 07/23/21 | 520 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 07/23/21 | 524 | Holmes, Anthony R |  | 140.76
PR | 998 | 07/23/21 | 527 | Hubbard, Robert W |  | 12.62
PR | 998 | 07/23/21 | 527 | Hubbard, Robert W |  | 12.62
PR | 998 | 07/23/21 | 529 | Lee, Ha Nul |  | 61.97
PR | 998 | 07/23/21 | 529 | Lee, Ha Nul |  | 20.66
PR | 998 | 07/23/21 | 532 | Lovo, German G |  | 80.78
PR | 998 | 07/23/21 | 540 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 07/23/21 | 543 | Platero Navas, Julio A |  | 55.08
PR | 998 | 07/23/21 | 544 | Platero Navas, Mario N |  | 52.02
PR | 998 | 07/23/21 | 555 | Sepulveda Gonzalez, Alfredo |  | 34.43
PR | 998 | 07/23/21 | 561 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 07/23/21 | 562 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 07/23/21 | 565 | Donelson, Richard T |  | 9.56
PR | 998 | 07/30/21 | 684 | Barnhart, Joseph N |  | 42.84
PR | 998 | 07/30/21 | 684 | Barnhart, Joseph N |  | 17.14
PR | 998 | 07/30/21 | 684 | Barnhart, Joseph N |  | 8.57
PR | 998 | 07/30/21 | 695 | Cruz, Azael S |  | 82.62
PR | 998 | 07/30/21 | 711 | Gonzalez Hernandez, Josue |  | 107.56
PR | 998 | 07/30/21 | 712 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 07/30/21 | 717 | Holmes, Anthony R |  | 140.76
PR | 998 | 07/30/21 | 722 | Lee, Ha Nul |  | 82.62
PR | 998 | 07/30/21 | 725 | Lovo, German G |  | 100.98
PR | 998 | 07/30/21 | 733 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 07/30/21 | 736 | Platero Navas, Julio A |  | 55.08
PR | 998 | 07/30/21 | 737 | Platero Navas, Mario N |  | 52.02
PR | 998 | 07/30/21 | 753 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 07/30/21 | 754 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 08/06/21 | 55 | Cruz, Azael S |  | 82.62
PR | 998 | 08/06/21 | 71 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 08/06/21 | 76 | Holmes, Anthony R |  | 140.76
PR | 998 | 08/06/21 | 79 | Hubbard, Robert W |  | 12.62
PR | 998 | 08/06/21 | 79 | Hubbard, Robert W |  | 16.83
PR | 998 | 08/06/21 | 79 | Hubbard, Robert W |  | 16.83
PR | 998 | 08/06/21 | 81 | Lee, Ha Nul |  | 82.62
PR | 998 | 08/06/21 | 84 | Lovo, German G |  | 100.98
PR | 998 | 08/06/21 | 92 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 08/06/21 | 95 | Platero Navas, Julio A |  | 55.08
PR | 998 | 08/06/21 | 96 | Platero Navas, Mario N |  | 52.02
PR | 998 | 08/06/21 | 112 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 08/06/21 | 113 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 08/06/21 | 116 | Donelson, Richard T |  | 9.56
PR | 998 | 08/13/21 | 317 | Cruz, Azael S |  | 82.62
PR | 998 | 08/13/21 | 333 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 08/13/21 | 338 | Holmes, Anthony R |  | 126.68
PR | 998 | 08/13/21 | 338 | Holmes, Anthony R |  | 14.08
PR | 998 | 08/13/21 | 341 | Hubbard, Robert W |  | 33.66
PR | 998 | 08/13/21 | 343 | Lee, Ha Nul |  | 99.14
PR | 998 | 08/13/21 | 346 | Lovo, German G |  | 65.64
PR | 998 | 08/13/21 | 346 | Lovo, German G |  | 15.15
PR | 998 | 08/13/21 | 354 | Ortiz Carmona, Jose |  | 68.54
PR | 998 | 08/13/21 | 357 | Platero Navas, Julio A |  | 44.06
PR | 998 | 08/13/21 | 357 | Platero Navas, Julio A |  | 11.02
PR | 998 | 08/13/21 | 358 | Platero Navas, Mario N |  | 46.82
PR | 998 | 08/13/21 | 358 | Platero Navas, Mario N |  | 5.2
PR | 998 | 08/13/21 | 373 | Velasquez Cruz, Denis M |  | 84.92
PR | 998 | 08/13/21 | 374 | Velasquez Cruz, Osman N |  | 58.75
PR | 998 | 08/13/21 | 374 | Velasquez Cruz, Osman N |  | 14.69
PR | 998 | 08/20/21 | 587 | Barnhart, Joseph N |  | 29.99
PR | 998 | 08/20/21 | 587 | Barnhart, Joseph N |  | 8.57
PR | 998 | 08/20/21 | 587 | Barnhart, Joseph N |  | 4.28
PR | 998 | 08/20/21 | 598 | Cruz, Azael S |  | 82.62
PR | 998 | 08/20/21 | 615 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 08/20/21 | 617 | Gutierrez, Brian A |  | 50.72
PR | 998 | 08/20/21 | 620 | Holmes, Anthony R |  | 35.19
PR | 998 | 08/20/21 | 620 | Holmes, Anthony R |  | 105.57
PR | 998 | 08/20/21 | 626 | Lee, Ha Nul |  | 20.66
PR | 998 | 08/20/21 | 626 | Lee, Ha Nul |  | 52.67
PR | 998 | 08/20/21 | 629 | Lovo, German G |  | 70.69
PR | 998 | 08/20/21 | 629 | Lovo, German G |  | 30.29
PR | 998 | 08/20/21 | 637 | Ortiz Carmona, Jose |  | 97.92
PR | 998 | 08/20/21 | 640 | Platero Navas, Julio A |  | 46.13
PR | 998 | 08/20/21 | 641 | Platero Navas, Mario N |  | 31.21
PR | 998 | 08/20/21 | 641 | Platero Navas, Mario N |  | 20.81
PR | 998 | 08/20/21 | 656 | Velasquez Cruz, Denis M |  | 28.31
PR | 998 | 08/20/21 | 656 | Velasquez Cruz, Denis M |  | 56.61
PR | 998 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 24.48
PR | 998 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 48.96
PR | 998 | 08/20/21 | 657 | Velasquez Cruz, Osman N |  | 24.48
PR | 998 | 08/20/21 | 661 | Donelson, Richard T |  | 4.78
PR | 998 | 08/27/21 | 807 | Barnhart, Joseph N |  | 38.56
PR | 998 | 08/27/21 | 807 | Barnhart, Joseph N |  | 8.57
PR | 998 | 08/27/21 | 807 | Barnhart, Joseph N |  | 29.99
PR | 998 | 08/27/21 | 807 | Barnhart, Joseph N |  | 4.28
PR | 998 | 08/27/21 | 819 | Cruz, Azael S |  | 82.62
PR | 998 | 08/27/21 | 836 | Gordillo, Emanuel D |  | 52.02
PR | 998 | 08/27/21 | 838 | Gutierrez, Brian A |  | 41.62
PR | 998 | 08/27/21 | 841 | Holmes, Anthony R |  | 123.17
PR | 998 | 08/27/21 | 841 | Holmes, Anthony R |  | 17.6
PR | 998 | 08/27/21 | 849 | Lovo, German G |  | 60.59
PR | 998 | 08/27/21 | 857 | Ortiz Carmona, Jose |  | 48.96
PR | 998 | 08/27/21 | 857 | Ortiz Carmona, Jose |  | 48.96
PR | 998 | 08/27/21 | 860 | Platero Navas, Julio A |  | 46.13
PR | 998 | 08/27/21 | 861 | Platero Navas, Mario N |  | 52.02
PR | 998 | 08/27/21 | 877 | Velasquez Cruz, Denis M |  | 84.92
PR | 998 | 08/27/21 | 877 | Velasquez Cruz, Denis M |  | 28.31
PR | 998 | 08/27/21 | 878 | Velasquez Cruz, Osman N |  | 24.48
PR | 998 | 08/27/21 | 878 | Velasquez Cruz, Osman N |  | 24.48
PR | 998 | 09/03/21 | 8 | Barnhart, Joseph N |  | 59.98
PR | 998 | 09/03/21 | 8 | Barnhart, Joseph N |  | 21.42
PR | 998 | 09/03/21 | 20 | Cruz, Azael S |  | 61.97
PR | 998 | 09/03/21 | 20 | Cruz, Azael S |  | 20.66
PR | 998 | 09/03/21 | 38 | Gordillo, Emanuel D |  | 26.01
PR | 998 | 09/03/21 | 40 | Gutierrez, Brian A |  | 20.81
PR | 998 | 09/03/21 | 43 | Holmes, Anthony R |  | 70.38
PR | 998 | 09/03/21 | 46 | Hubbard, Robert W |  | 33.66
PR | 998 | 09/03/21 | 51 | Lovo, German G |  | 100.98
PR | 998 | 09/03/21 | 59 | Ortiz Carmona, Jose |  | 73.44
PR | 998 | 09/03/21 | 59 | Ortiz Carmona, Jose |  | 24.48
PR | 998 | 09/03/21 | 62 | Platero Navas, Julio A |  | 44.06
PR | 998 | 09/03/21 | 62 | Platero Navas, Julio A |  | 11.02
PR | 998 | 09/03/21 | 63 | Platero Navas, Mario N |  | 31.21
PR | 998 | 09/03/21 | 63 | Platero Navas, Mario N |  | 20.81
PR | 998 | 09/03/21 | 80 | Velasquez Cruz, Denis M |  | 113.22
PR | 998 | 09/03/21 | 81 | Velasquez Cruz, Osman N |  | 97.92
PR | 998 | 09/03/21 | 87 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 09/10/21 | 188 | Cruz, Azael S |  | 64.26
PR | 998 | 09/10/21 | 206 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 09/10/21 | 208 | Gutierrez, Brian A |  | 11.7
PR | 998 | 09/10/21 | 211 | Holmes, Anthony R |  | 146.88
PR | 998 | 09/10/21 | 219 | Lovo, German G |  | 42.84
PR | 998 | 09/10/21 | 227 | Ortiz Carmona, Jose |  | 50.49
PR | 998 | 09/10/21 | 227 | Ortiz Carmona, Jose |  | 25.25
PR | 998 | 09/10/21 | 231 | Platero Navas, Julio A |  | 46.51
PR | 998 | 09/10/21 | 232 | Platero Navas, Mario N |  | 44.06
PR | 998 | 09/10/21 | 249 | Velasquez Cruz, Denis M |  | 89.51
PR | 998 | 09/10/21 | 250 | Velasquez Cruz, Osman N |  | 78.03
PR | 998 | 09/17/21 | 338 | Barnhart, Joseph N |  | 13.31
PR | 998 | 09/17/21 | 338 | Barnhart, Joseph N |  | 4.44
PR | 998 | 09/17/21 | 338 | Barnhart, Joseph N |  | 4.44
PR | 998 | 09/17/21 | 338 | Barnhart, Joseph N |  | 26.62
PR | 998 | 09/17/21 | 350 | Cruz, Azael S |  | 85.68
PR | 998 | 09/17/21 | 368 | Gordillo, Emanuel D |  | 17.44
PR | 998 | 09/17/21 | 368 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 09/17/21 | 373 | Holmes, Anthony R |  | 44.06
PR | 998 | 09/17/21 | 373 | Holmes, Anthony R |  | 143.21
PR | 998 | 09/17/21 | 373 | Holmes, Anthony R |  | 3.67
PR | 998 | 09/17/21 | 381 | Lovo, German G |  | 4.02
PR | 998 | 09/17/21 | 381 | Lovo, German G |  | 107.1
PR | 998 | 09/17/21 | 389 | Ortiz Carmona, Jose |  | 100.98
PR | 998 | 09/17/21 | 393 | Platero Navas, Julio A |  | 2.18
PR | 998 | 09/17/21 | 393 | Platero Navas, Julio A |  | 58.14
PR | 998 | 09/17/21 | 394 | Platero Navas, Mario N |  | 2.07
PR | 998 | 09/17/21 | 394 | Platero Navas, Mario N |  | 55.08
PR | 998 | 09/17/21 | 411 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 09/17/21 | 411 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 09/17/21 | 412 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 09/17/21 | 412 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 09/24/21 | 492 | Barnhart, Joseph N |  | 13.31
PR | 998 | 09/24/21 | 492 | Barnhart, Joseph N |  | 48.81
PR | 998 | 09/24/21 | 492 | Barnhart, Joseph N |  | 8.87
PR | 998 | 09/24/21 | 504 | Cruz, Azael S |  | 22.49
PR | 998 | 09/24/21 | 504 | Cruz, Azael S |  | 64.26
PR | 998 | 09/24/21 | 504 | Cruz, Azael S |  | 21.42
PR | 998 | 09/24/21 | 522 | Gordillo, Emanuel D |  | 17.44
PR | 998 | 09/24/21 | 522 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 09/24/21 | 527 | Holmes, Anthony R |  | 44.06
PR | 998 | 09/24/21 | 527 | Holmes, Anthony R |  | 146.88
PR | 998 | 09/24/21 | 535 | Lovo, German G |  | 24.1
PR | 998 | 09/24/21 | 535 | Lovo, German G |  | 107.1
PR | 998 | 09/24/21 | 543 | Ortiz Carmona, Jose |  | 26.51
PR | 998 | 09/24/21 | 543 | Ortiz Carmona, Jose |  | 100.98
PR | 998 | 09/24/21 | 547 | Platero Navas, Julio A |  | 55.23
PR | 998 | 09/24/21 | 548 | Platero Navas, Mario N |  | 13.77
PR | 998 | 09/24/21 | 566 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 09/24/21 | 566 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 09/24/21 | 567 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 09/24/21 | 567 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 09/24/21 | 572 | Donelson, Richard T |  | 4.78
PR | 998 | 09/24/21 | 573 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 10/01/21 | 9 | Barnhart, Joseph N |  | 66.56
PR | 998 | 10/01/21 | 9 | Barnhart, Joseph N |  | 44.37
PR | 998 | 10/01/21 | 9 | Barnhart, Joseph N |  | 4.44
PR | 998 | 10/01/21 | 16 | Castro Urena, Yanely |  | 29.26
PR | 998 | 10/01/21 | 16 | Castro Urena, Yanely |  | 52.02
PR | 998 | 10/01/21 | 21 | Cruz, Azael S |  | 85.68
PR | 998 | 10/01/21 | 38 | Gonzalez Hernandez, Josue |  | 91.8
PR | 998 | 10/01/21 | 39 | Gordillo, Emanuel D |  | 34.88
PR | 998 | 10/01/21 | 39 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 10/01/21 | 41 | Gutierrez, Brian A |  | 20.88
PR | 998 | 10/01/21 | 41 | Gutierrez, Brian A |  | 79.56
PR | 998 | 10/01/21 | 43 | Hernandez Gonzalez, Osbaldo |  | 53.55
PR | 998 | 10/01/21 | 44 | Holmes, Anthony R |  | 88.13
PR | 998 | 10/01/21 | 44 | Holmes, Anthony R |  | 146.88
PR | 998 | 10/01/21 | 50 | Lara, Eric E |  | 22.95
PR | 998 | 10/01/21 | 53 | Lovo, German G |  | 24.1
PR | 998 | 10/01/21 | 53 | Lovo, German G |  | 107.1
PR | 998 | 10/01/21 | 60 | Ortiz Carmona, Jose |  | 75.74
PR | 998 | 10/01/21 | 60 | Ortiz Carmona, Jose |  | 25.25
PR | 998 | 10/01/21 | 64 | Platero Navas, Julio A |  | 13.08
PR | 998 | 10/01/21 | 64 | Platero Navas, Julio A |  | 58.14
PR | 998 | 10/01/21 | 65 | Platero Navas, Mario N |  | 12.39
PR | 998 | 10/01/21 | 65 | Platero Navas, Mario N |  | 55.08
PR | 998 | 10/01/21 | 78 | Stahlschmidt, John P |  | 17.9
PR | 998 | 10/01/21 | 78 | Stahlschmidt, John P |  | 63.65
PR | 998 | 10/01/21 | 82 | Vazquez Popoca, Jose N |  | 18.59
PR | 998 | 10/01/21 | 82 | Vazquez Popoca, Jose N |  | 49.57
PR | 998 | 10/01/21 | 83 | Velasquez Cruz, Denis M |  | 67.13
PR | 998 | 10/01/21 | 83 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 10/01/21 | 84 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 10/01/21 | 84 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 10/08/21 | 297 | Barnhart, Joseph N |  | 62.12
PR | 998 | 10/08/21 | 297 | Barnhart, Joseph N |  | 8.87
PR | 998 | 10/08/21 | 305 | Castro Urena, Yanely |  | 48.12
PR | 998 | 10/08/21 | 310 | Cruz, Azael S |  | 22.49
PR | 998 | 10/08/21 | 310 | Cruz, Azael S |  | 85.68
PR | 998 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 36.72
PR | 998 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 76.5
PR | 998 | 10/08/21 | 329 | Gonzalez Hernandez, Josue |  | 45.9
PR | 998 | 10/08/21 | 331 | Gordillo, Emanuel D |  | 34.88
PR | 998 | 10/08/21 | 331 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 10/08/21 | 333 | Gutierrez, Brian A |  | 25.7
PR | 998 | 10/08/21 | 333 | Gutierrez, Brian A |  | 85.68
PR | 998 | 10/08/21 | 336 | Holmes, Anthony R |  | 88.13
PR | 998 | 10/08/21 | 336 | Holmes, Anthony R |  | 143.21
PR | 998 | 10/08/21 | 336 | Holmes, Anthony R |  | 3.67
PR | 998 | 10/08/21 | 342 | Lara, Eric E |  | 53.36
PR | 998 | 10/08/21 | 342 | Lara, Eric E |  | 91.8
PR | 998 | 10/08/21 | 345 | Lovo, German G |  | 8.03
PR | 998 | 10/08/21 | 345 | Lovo, German G |  | 107.1
PR | 998 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 26.51
PR | 998 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 25.25
PR | 998 | 10/08/21 | 353 | Ortiz Carmona, Jose |  | 75.74
PR | 998 | 10/08/21 | 357 | Platero Navas, Julio A |  | 26.16
PR | 998 | 10/08/21 | 357 | Platero Navas, Julio A |  | 24.71
PR | 998 | 10/08/21 | 357 | Platero Navas, Julio A |  | 33.43
PR | 998 | 10/08/21 | 358 | Platero Navas, Mario N |  | 24.79
PR | 998 | 10/08/21 | 358 | Platero Navas, Mario N |  | 55.08
PR | 998 | 10/08/21 | 375 | Vazquez Popoca, Jose N |  | 18.59
PR | 998 | 10/08/21 | 375 | Vazquez Popoca, Jose N |  | 82.62
PR | 998 | 10/08/21 | 376 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 10/08/21 | 376 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 10/08/21 | 377 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 10/08/21 | 377 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 10/08/21 | 381 | Donelson, Richard T |  | 9.56
PR | 998 | 10/15/21 | 561 | Barnhart, Joseph N |  | 62.12
PR | 998 | 10/15/21 | 561 | Barnhart, Joseph N |  | 8.87
PR | 998 | 10/15/21 | 569 | Castro Urena, Yanely |  | 13.66
PR | 998 | 10/15/21 | 569 | Castro Urena, Yanely |  | 52.02
PR | 998 | 10/15/21 | 574 | Cruz, Azael S |  | 22.49
PR | 998 | 10/15/21 | 574 | Cruz, Azael S |  | 85.68
PR | 998 | 10/15/21 | 594 | Gonzalez Hernandez, Josue |  | 36.72
PR | 998 | 10/15/21 | 594 | Gonzalez Hernandez, Josue |  | 122.4
PR | 998 | 10/15/21 | 596 | Gordillo, Emanuel D |  | 34.88
PR | 998 | 10/15/21 | 596 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 10/15/21 | 598 | Gutierrez, Brian A |  | 22.49
PR | 998 | 10/15/21 | 598 | Gutierrez, Brian A |  | 85.68
PR | 998 | 10/15/21 | 601 | Holmes, Anthony R |  | 88.13
PR | 998 | 10/15/21 | 601 | Holmes, Anthony R |  | 139.54
PR | 998 | 10/15/21 | 601 | Holmes, Anthony R |  | 7.34
PR | 998 | 10/15/21 | 609 | Lovo, German G |  | 101.75
PR | 998 | 10/15/21 | 617 | Ortiz Carmona, Jose |  | 26.51
PR | 998 | 10/15/21 | 617 | Ortiz Carmona, Jose |  | 100.98
PR | 998 | 10/15/21 | 621 | Platero Navas, Julio A |  | 55.23
PR | 998 | 10/15/21 | 622 | Platero Navas, Mario N |  | 49.57
PR | 998 | 10/15/21 | 638 | Vazquez Popoca, Jose N |  | 47.51
PR | 998 | 10/15/21 | 639 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 10/15/21 | 639 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 10/15/21 | 640 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 10/15/21 | 640 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 10/15/21 | 645 | Donelson, Richard T |  | 4.78
PR | 998 | 10/22/21 | 748 | Barnhart, Joseph N |  | 86.52
PR | 998 | 10/22/21 | 748 | Barnhart, Joseph N |  | 70.99
PR | 998 | 10/22/21 | 757 | Castro Urena, Yanely |  | 49.42
PR | 998 | 10/22/21 | 762 | Cruz, Azael S |  | 22.49
PR | 998 | 10/22/21 | 762 | Cruz, Azael S |  | 85.68
PR | 998 | 10/22/21 | 782 | Gonzalez Hernandez, Josue |  | 36.72
PR | 998 | 10/22/21 | 782 | Gonzalez Hernandez, Josue |  | 122.4
PR | 998 | 10/22/21 | 784 | Gordillo, Emanuel D |  | 39.24
PR | 998 | 10/22/21 | 784 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 10/22/21 | 787 | Gutierrez, Brian A |  | 79.25
PR | 998 | 10/22/21 | 791 | Holmes, Anthony R |  | 99.14
PR | 998 | 10/22/21 | 791 | Holmes, Anthony R |  | 146.88
PR | 998 | 10/22/21 | 799 | Lovo, German G |  | 24.1
PR | 998 | 10/22/21 | 799 | Lovo, German G |  | 107.1
PR | 998 | 10/22/21 | 807 | Ortiz Carmona, Jose |  | 100.98
PR | 998 | 10/22/21 | 811 | Platero Navas, Julio A |  | 17.44
PR | 998 | 10/22/21 | 811 | Platero Navas, Julio A |  | 58.14
PR | 998 | 10/22/21 | 812 | Platero Navas, Mario N |  | 37.18
PR | 998 | 10/22/21 | 812 | Platero Navas, Mario N |  | 55.08
PR | 998 | 10/22/21 | 829 | Vazquez Popoca, Jose N |  | 37.18
PR | 998 | 10/22/21 | 830 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 10/22/21 | 830 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 10/22/21 | 831 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 10/22/21 | 831 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 13.31
PR | 998 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 57.68
PR | 998 | 10/29/21 | 1008 | Barnhart, Joseph N |  | 4.44
PR | 998 | 10/29/21 | 1017 | Castro Urena, Yanely |  | 52.02
PR | 998 | 10/29/21 | 1022 | Cruz, Azael S |  | 85.68
PR | 998 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 29.84
PR | 998 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 61.2
PR | 998 | 10/29/21 | 1042 | Gonzalez Hernandez, Josue |  | 61.2
PR | 998 | 10/29/21 | 1043 | Gordillo, Emanuel D |  | 32.7
PR | 998 | 10/29/21 | 1043 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 10/29/21 | 1046 | Gutierrez, Brian A |  | 85.68
PR | 998 | 10/29/21 | 1051 | Holmes, Anthony R |  | 82.62
PR | 998 | 10/29/21 | 1051 | Holmes, Anthony R |  | 146.88
PR | 998 | 10/29/21 | 1059 | Lovo, German G |  | 65.6
PR | 998 | 10/29/21 | 1059 | Lovo, German G |  | 26.78
PR | 998 | 10/29/21 | 1066 | Ortiz Carmona, Jose |  | 75.74
PR | 998 | 10/29/21 | 1066 | Ortiz Carmona, Jose |  | 25.25
PR | 998 | 10/29/21 | 1070 | Platero Navas, Julio A |  | 54.51
PR | 998 | 10/29/21 | 1071 | Platero Navas, Mario N |  | 27.88
PR | 998 | 10/29/21 | 1071 | Platero Navas, Mario N |  | 55.08
PR | 998 | 10/29/21 | 1088 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 10/29/21 | 1088 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 10/29/21 | 1089 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 10/29/21 | 1092 | Donelson, Richard T |  | 4.78
PR | 998 | 11/05/21 | 54 | Barnhart, Joseph N |  | 31.06
PR | 998 | 11/05/21 | 63 | Castro Urena, Yanely |  | 13.66
PR | 998 | 11/05/21 | 63 | Castro Urena, Yanely |  | 13.01
PR | 998 | 11/05/21 | 63 | Castro Urena, Yanely |  | 39.02
PR | 998 | 11/05/21 | 68 | Cruz, Azael S |  | 74.97
PR | 998 | 11/05/21 | 68 | Cruz, Azael S |  | 10.71
PR | 998 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 27.54
PR | 998 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 107.1
PR | 998 | 11/05/21 | 89 | Gonzalez Hernandez, Josue |  | 15.3
PR | 998 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 17.44
PR | 998 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 21.8
PR | 998 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 50.87
PR | 998 | 11/05/21 | 90 | Gordillo, Emanuel D |  | 7.27
PR | 998 | 11/05/21 | 93 | Gutierrez, Brian A |  | 53.55
PR | 998 | 11/05/21 | 93 | Gutierrez, Brian A |  | 10.71
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 49.57
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 11.02
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 38.56
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 102.82
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 25.7
PR | 998 | 11/05/21 | 98 | Holmes, Anthony R |  | 18.36
PR | 998 | 11/05/21 | 107 | Lovo, German G |  | 8.03
PR | 998 | 11/05/21 | 107 | Lovo, German G |  | 16.07
PR | 998 | 11/05/21 | 107 | Lovo, German G |  | 72.29
PR | 998 | 11/05/21 | 107 | Lovo, German G |  | 21.42
PR | 998 | 11/05/21 | 107 | Lovo, German G |  | 13.39
PR | 998 | 11/05/21 | 114 | Ortiz Carmona, Jose |  | 63.11
PR | 998 | 11/05/21 | 114 | Ortiz Carmona, Jose |  | 37.87
PR | 998 | 11/05/21 | 118 | Platero Navas, Julio A |  | 50.87
PR | 998 | 11/05/21 | 118 | Platero Navas, Julio A |  | 7.27
PR | 998 | 11/05/21 | 119 | Platero Navas, Mario N |  | 16.52
PR | 998 | 11/05/21 | 119 | Platero Navas, Mario N |  | 48.2
PR | 998 | 11/05/21 | 119 | Platero Navas, Mario N |  | 6.89
PR | 998 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 58.18
PR | 998 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 104.42
PR | 998 | 11/05/21 | 137 | Velasquez Cruz, Denis M |  | 14.92
PR | 998 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 91.04
PR | 998 | 11/05/21 | 138 | Velasquez Cruz, Osman N |  | 13.01
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 13.31
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 8.87
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 8.87
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 8.87
PR | 998 | 11/12/21 | 269 | Barnhart, Joseph N |  | 8.87
PR | 998 | 11/12/21 | 278 | Castro Urena, Yanely |  | 52.02
PR | 998 | 11/12/21 | 283 | Cruz, Azael S |  | 85.68
PR | 998 | 11/12/21 | 303 | Gonzalez Hernandez, Josue |  | 36.72
PR | 998 | 11/12/21 | 303 | Gonzalez Hernandez, Josue |  | 122.4
PR | 998 | 11/12/21 | 304 | Gordillo, Emanuel D |  | 17.44
PR | 998 | 11/12/21 | 304 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 11/12/21 | 307 | Gutierrez, Brian A |  | 85.68
PR | 998 | 11/12/21 | 312 | Holmes, Anthony R |  | 44.06
PR | 998 | 11/12/21 | 312 | Holmes, Anthony R |  | 88.13
PR | 998 | 11/12/21 | 312 | Holmes, Anthony R |  | 33.05
PR | 998 | 11/12/21 | 312 | Holmes, Anthony R |  | 25.7
PR | 998 | 11/12/21 | 321 | Lovo, German G |  | 24.1
PR | 998 | 11/12/21 | 321 | Lovo, German G |  | 107.1
PR | 998 | 11/12/21 | 328 | Ortiz Carmona, Jose |  | 100.98
PR | 998 | 11/12/21 | 332 | Platero Navas, Julio A |  | 17.44
PR | 998 | 11/12/21 | 332 | Platero Navas, Julio A |  | 58.14
PR | 998 | 11/12/21 | 333 | Platero Navas, Mario N |  | 52.33
PR | 998 | 11/12/21 | 351 | Velasquez Cruz, Denis M |  | 31.33
PR | 998 | 11/12/21 | 351 | Velasquez Cruz, Denis M |  | 119.34
PR | 998 | 11/12/21 | 352 | Velasquez Cruz, Osman N |  | 27.31
PR | 998 | 11/12/21 | 352 | Velasquez Cruz, Osman N |  | 104.04
PR | 998 | 11/19/21 | 437 | Barnhart, Joseph N |  | 22.19
PR | 998 | 11/19/21 | 437 | Barnhart, Joseph N |  | 4.44
PR | 998 | 11/19/21 | 446 | Castro Urena, Yanely |  | 45.52
PR | 998 | 11/19/21 | 451 | Cruz, Azael S |  | 16.07
PR | 998 | 11/19/21 | 451 | Cruz, Azael S |  | 85.68
PR | 998 | 11/19/21 | 471 | Gonzalez Hernandez, Josue |  | 61.2
PR | 998 | 11/19/21 | 471 | Gonzalez Hernandez, Josue |  | 55.08
PR | 998 | 11/19/21 | 472 | Gordillo, Emanuel D |  | 13.08
PR | 998 | 11/19/21 | 472 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 11/19/21 | 475 | Gutierrez, Brian A |  | 42.84
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 5.51
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 11.02
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 16.52
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 69.77
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 25.7
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 36.72
PR | 998 | 11/19/21 | 480 | Holmes, Anthony R |  | 14.69
PR | 998 | 11/19/21 | 489 | Lovo, German G |  | 8.03
PR | 998 | 11/19/21 | 489 | Lovo, German G |  | 107.1
PR | 998 | 11/19/21 | 496 | Ortiz Carmona, Jose |  | 95.93
PR | 998 | 11/19/21 | 500 | Platero Navas, Julio A |  | 8.72
PR | 998 | 11/19/21 | 500 | Platero Navas, Julio A |  | 58.14
PR | 998 | 11/19/21 | 501 | Platero Navas, Mario N |  | 49.57
PR | 998 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 22.38
PR | 998 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 83.54
PR | 998 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 5.97
PR | 998 | 11/19/21 | 517 | Velasquez Cruz, Denis M |  | 29.84
PR | 998 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 19.51
PR | 998 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 67.63
PR | 998 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 5.2
PR | 998 | 11/19/21 | 518 | Velasquez Cruz, Osman N |  | 31.21
PR | 998 | 11/24/21 | 586 | Castro Urena, Yanely |  | 34.46
PR | 998 | 11/24/21 | 591 | Cruz, Azael S |  | 78.18
PR | 998 | 11/24/21 | 611 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 11/24/21 | 612 | Gordillo, Emanuel D |  | 55.23
PR | 998 | 11/24/21 | 615 | Gutierrez, Brian A |  | 42.84
PR | 998 | 11/24/21 | 618 | Holmes, Anthony R |  | 139.54
PR | 998 | 11/24/21 | 627 | Lovo, German G |  | 96.39
PR | 998 | 11/24/21 | 634 | Ortiz Carmona, Jose |  | 92.14
PR | 998 | 11/24/21 | 638 | Platero Navas, Julio A |  | 42.15
PR | 998 | 11/24/21 | 639 | Platero Navas, Mario N |  | 52.33
PR | 998 | 11/24/21 | 655 | Velasquez Cruz, Denis M |  | 89.51
PR | 998 | 11/24/21 | 655 | Velasquez Cruz, Denis M |  | 19.39
PR | 998 | 11/24/21 | 656 | Velasquez Cruz, Osman N |  | 52.02
PR | 998 | 11/24/21 | 656 | Velasquez Cruz, Osman N |  | 42.92
PR | 998 | 11/24/21 | 659 | Donelson, Richard T |  | 4.78
PR | 998 | 12/03/21 | 13 | Barnhart, Joseph N |  | 22.19
PR | 998 | 12/03/21 | 13 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/03/21 | 13 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/03/21 | 13 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/03/21 | 28 | Cruz, Azael S |  | 81.4
PR | 998 | 12/03/21 | 48 | Gonzalez Hernandez, Josue |  | 116.28
PR | 998 | 12/03/21 | 49 | Gordillo, Emanuel D |  | 55.23
PR | 998 | 12/03/21 | 56 | Holmes, Anthony R |  | 139.54
PR | 998 | 12/03/21 | 65 | Lovo, German G |  | 96.39
PR | 998 | 12/03/21 | 72 | Ortiz Carmona, Jose |  | 70.69
PR | 998 | 12/03/21 | 76 | Platero Navas, Julio A |  | 55.23
PR | 998 | 12/03/21 | 77 | Platero Navas, Mario N |  | 52.33
PR | 998 | 12/03/21 | 94 | Velasquez Cruz, Denis M |  | 113.37
PR | 998 | 12/03/21 | 95 | Velasquez Cruz, Osman N |  | 98.84
PR | 998 | 12/10/21 | 194 | Barnhart, Joseph N |  | 35.5
PR | 998 | 12/10/21 | 209 | Cruz, Azael S |  | 51.41
PR | 998 | 12/10/21 | 229 | Gonzalez Hernandez, Josue |  | 94.86
PR | 998 | 12/10/21 | 229 | Gonzalez Hernandez, Josue |  | 3.06
PR | 998 | 12/10/21 | 230 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 12/10/21 | 238 | Holmes, Anthony R |  | 146.88
PR | 998 | 12/10/21 | 247 | Lovo, German G |  | 64.26
PR | 998 | 12/10/21 | 255 | Ortiz Carmona, Jose |  | 60.59
PR | 998 | 12/10/21 | 259 | Platero Navas, Julio A |  | 58.14
PR | 998 | 12/10/21 | 260 | Platero Navas, Mario N |  | 55.08
PR | 998 | 12/10/21 | 277 | Velasquez Cruz, Denis M |  | 71.6
PR | 998 | 12/10/21 | 278 | Velasquez Cruz, Osman N |  | 41.62
PR | 998 | 12/10/21 | 281 | Donelson, Richard T |  | 9.56
PR | 998 | 12/17/21 | 516 | Barnhart, Joseph N |  | 13.31
PR | 998 | 12/17/21 | 516 | Barnhart, Joseph N |  | 13.31
PR | 998 | 12/17/21 | 516 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/17/21 | 516 | Barnhart, Joseph N |  | 4.44
PR | 998 | 12/17/21 | 517 | Barnhart, Thomas L |  | 46.51
PR | 998 | 12/17/21 | 551 | Gonzalez Hernandez, Josue |  | 122.4
PR | 998 | 12/17/21 | 552 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 12/17/21 | 560 | Holmes, Anthony R |  | 143.21
PR | 998 | 12/17/21 | 560 | Holmes, Anthony R |  | 3.67
PR | 998 | 12/17/21 | 569 | Lovo, German G |  | 107.1
PR | 998 | 12/17/21 | 581 | Platero Navas, Mario N |  | 44.06
PR | 998 | 12/17/21 | 581 | Platero Navas, Mario N |  | 5.51
PR | 998 | 12/17/21 | 581 | Platero Navas, Mario N |  | 5.51
PR | 998 | 12/17/21 | 592 | Sanders, Allen O |  | 13.08
PR | 998 | 12/23/21 | 741 | Barnhart, Joseph N |  | 8.87
PR | 998 | 12/23/21 | 741 | Barnhart, Joseph N |  | 17.75
PR | 998 | 12/23/21 | 741 | Barnhart, Joseph N |  | 8.87
PR | 998 | 12/23/21 | 742 | Barnhart, Thomas L |  | 17.44
PR | 998 | 12/23/21 | 776 | Gonzalez Hernandez, Josue |  | 73.44
PR | 998 | 12/23/21 | 777 | Gordillo, Emanuel D |  | 46.51
PR | 998 | 12/23/21 | 785 | Holmes, Anthony R |  | 146.88
PR | 998 | 12/23/21 | 794 | Lovo, German G |  | 107.1
PR | 998 | 12/23/21 | 806 | Platero Navas, Mario N |  | 44.06
PR | 998 | 12/23/21 | 806 | Platero Navas, Mario N |  | 11.02
PR | 998 | 12/23/21 | 827 | Donelson, Richard T |  | 19.13
PR | 998 | 12/30/21 | 971 | Gonzalez Hernandez, Josue |  | 24.48
PR | 998 | 12/30/21 | 972 | Gordillo, Emanuel D |  | 19.62
PR | 998 | 12/30/21 | 980 | Holmes, Anthony R |  | 49.57
PR | 998 | 12/30/21 | 989 | Lovo, German G |  | 21.42
PR | 998 | 12/30/21 | 1002 | Platero Navas, Mario N |  | 11.02
PR | 998 | 01/07/22 | 31 | Barnhart, Thomas L |  | 23.26
PR | 998 | 01/07/22 | 65 | Gordillo, Emanuel D |  | 34.88
PR | 998 | 01/07/22 | 74 | Holmes, Anthony R |  | 58.75
PR | 998 | 01/07/22 | 74 | Holmes, Anthony R |  | 29.38
PR | 998 | 01/07/22 | 83 | Lovo, German G |  | 42.84
PR | 998 | 01/07/22 | 96 | Platero Navas, Mario N |  | 22.03
PR | 998 | 01/14/22 | 232 | Barnhart, Thomas L |  | 116.28
PR | 998 | 01/14/22 | 266 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 01/14/22 | 275 | Holmes, Anthony R |  | 146.88
PR | 998 | 01/14/22 | 283 | Lovo, German G |  | 107.1
PR | 998 | 01/14/22 | 295 | Platero Navas, Julio A |  | 34.88
PR | 998 | 01/14/22 | 296 | Platero Navas, Mario N |  | 55.08
PR | 998 | 01/21/22 | 414 | Barnhart, Joseph N |  | 17.75
PR | 998 | 01/21/22 | 415 | Barnhart, Thomas L |  | 93.02
PR | 998 | 01/21/22 | 449 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 01/21/22 | 458 | Holmes, Anthony R |  | 29.38
PR | 998 | 01/21/22 | 458 | Holmes, Anthony R |  | 117.5
PR | 998 | 01/21/22 | 467 | Lovo, German G |  | 42.84
PR | 998 | 01/21/22 | 467 | Lovo, German G |  | 64.26
PR | 998 | 01/21/22 | 479 | Platero Navas, Julio A |  | 58.14
PR | 998 | 01/21/22 | 480 | Platero Navas, Mario N |  | 22.03
PR | 998 | 01/21/22 | 480 | Platero Navas, Mario N |  | 33.05
PR | 998 | 01/28/22 | 616 | Barnhart, Thomas L |  | 116.28
PR | 998 | 01/28/22 | 630 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 01/28/22 | 632 | Cruz Reyes, Jose |  | 22.03
PR | 998 | 01/28/22 | 637 | Eliassen, Cory H |  | 20.81
PR | 998 | 01/28/22 | 650 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 01/28/22 | 659 | Holmes, Anthony R |  | 146.88
PR | 998 | 01/28/22 | 668 | Lovo, German G |  | 21.42
PR | 998 | 01/28/22 | 680 | Platero Navas, Julio A |  | 58.14
PR | 998 | 01/28/22 | 681 | Platero Navas, Mario N |  | 55.08
PR | 998 | 01/28/22 | 692 | Sanders, Allen O |  | 17.44
PR | 998 | 02/04/22 | 11 | Barnhart, Joseph N |  | 35.5
PR | 998 | 02/04/22 | 11 | Barnhart, Joseph N |  | 13.31
PR | 998 | 02/04/22 | 11 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/04/22 | 12 | Barnhart, Thomas L |  | 116.28
PR | 998 | 02/04/22 | 26 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 02/04/22 | 28 | Cruz Reyes, Jose |  | 22.03
PR | 998 | 02/04/22 | 33 | Eliassen, Cory H |  | 20.81
PR | 998 | 02/04/22 | 46 | Gordillo, Emanuel D |  | 46.51
PR | 998 | 02/04/22 | 55 | Holmes, Anthony R |  | 88.13
PR | 998 | 02/04/22 | 55 | Holmes, Anthony R |  | 58.75
PR | 998 | 02/04/22 | 75 | Platero Navas, Mario N |  | 33.05
PR | 998 | 02/04/22 | 87 | Sanders, Allen O |  | 26.16
PR | 998 | 02/04/22 | 92 | Trower-Kelly, Fidel D |  | 15.91
PR | 998 | 02/11/22 | 217 | Barnhart, Joseph N |  | 13.31
PR | 998 | 02/11/22 | 217 | Barnhart, Joseph N |  | 93.18
PR | 998 | 02/11/22 | 218 | Barnhart, Thomas L |  | 4.36
PR | 998 | 02/11/22 | 218 | Barnhart, Thomas L |  | 116.28
PR | 998 | 02/11/22 | 232 | Cruz Gonzalez, Julio C |  | 3.67
PR | 998 | 02/11/22 | 232 | Cruz Gonzalez, Julio C |  | 19.58
PR | 998 | 02/11/22 | 234 | Cruz Reyes, Jose |  | 4.13
PR | 998 | 02/11/22 | 234 | Cruz Reyes, Jose |  | 22.03
PR | 998 | 02/11/22 | 239 | Eliassen, Cory H |  | 20.81
PR | 998 | 02/11/22 | 253 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 02/11/22 | 262 | Holmes, Anthony R |  | 113.83
PR | 998 | 02/11/22 | 262 | Holmes, Anthony R |  | 29.38
PR | 998 | 02/11/22 | 262 | Holmes, Anthony R |  | 3.67
PR | 998 | 02/11/22 | 282 | Platero Navas, Julio A |  | 58.14
PR | 998 | 02/11/22 | 283 | Platero Navas, Mario N |  | 22.03
PR | 998 | 02/11/22 | 295 | Sanders, Allen O |  | 37.06
PR | 998 | 02/18/22 | 488 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/18/22 | 488 | Barnhart, Joseph N |  | 4.44
PR | 998 | 02/18/22 | 488 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/18/22 | 489 | Barnhart, Thomas L |  | 116.28
PR | 998 | 02/18/22 | 504 | Cruz Reyes, Jose |  | 4.13
PR | 998 | 02/18/22 | 504 | Cruz Reyes, Jose |  | 22.03
PR | 998 | 02/18/22 | 509 | Eliassen, Cory H |  | 20.81
PR | 998 | 02/18/22 | 523 | Gordillo, Emanuel D |  | 23.26
PR | 998 | 02/18/22 | 523 | Gordillo, Emanuel D |  | 23.26
PR | 998 | 02/18/22 | 532 | Holmes, Anthony R |  | 146.88
PR | 998 | 02/18/22 | 552 | Platero Navas, Julio A |  | 23.26
PR | 998 | 02/18/22 | 552 | Platero Navas, Julio A |  | 23.26
PR | 998 | 02/18/22 | 564 | Sanders, Allen O |  | 54.51
PR | 998 | 02/18/22 | 569 | Trower-Kelly, Fidel D |  | 16.91
PR | 998 | 02/18/22 | 577 | Donelson, Richard T |  | 14.34
PR | 998 | 02/18/22 | 578 | Gerard, Jeffrey S |  | 4.59
PR | 998 | 02/25/22 | 709 | Barnhart, Joseph N |  | 8.87
PR | 998 | 02/25/22 | 709 | Barnhart, Joseph N |  | 22.19
PR | 998 | 02/25/22 | 709 | Barnhart, Joseph N |  | 31.06
PR | 998 | 02/25/22 | 710 | Barnhart, Thomas L |  | 116.28
PR | 998 | 02/25/22 | 743 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 02/25/22 | 752 | Holmes, Anthony R |  | 146.88
PR | 998 | 02/25/22 | 772 | Platero Navas, Julio A |  | 58.14
PR | 998 | 02/25/22 | 784 | Sanders, Allen O |  | 21.8
PR | 998 | 03/04/22 | 44 | Barnhart, Joseph N |  | 88.74
PR | 998 | 03/04/22 | 45 | Barnhart, Thomas L |  | 69.77
PR | 998 | 03/04/22 | 60 | Cruz Reyes, Jose |  | 22.03
PR | 998 | 03/04/22 | 79 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 03/04/22 | 88 | Holmes, Anthony R |  | 146.88
PR | 998 | 03/04/22 | 98 | Lovo, German G |  | 107.1
PR | 998 | 03/04/22 | 110 | Platero Navas, Julio A |  | 58.14
PR | 998 | 03/04/22 | 122 | Sanders, Allen O |  | 21.8
PR | 998 | 03/04/22 | 134 | Donelson, Richard T |  | 14.34
PR | 998 | 03/11/22 | 341 | Barnhart, Joseph N |  | 8.87
PR | 998 | 03/11/22 | 341 | Barnhart, Joseph N |  | 11.09
PR | 998 | 03/11/22 | 342 | Barnhart, Thomas L |  | 116.28
PR | 998 | 03/11/22 | 376 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 03/11/22 | 384 | Holmes, Anthony R |  | 128.52
PR | 998 | 03/11/22 | 384 | Holmes, Anthony R |  | 18.36
PR | 998 | 03/11/22 | 391 | Johnson, Jake E |  | 7.65
PR | 998 | 03/11/22 | 395 | Lovo, German G |  | 85.68
PR | 998 | 03/11/22 | 407 | Platero Navas, Julio A |  | 46.51
PR | 998 | 03/11/22 | 419 | Sanders, Allen O |  | 19.62
PR | 998 | 03/18/22 | 626 | Barnhart, Joseph N |  | 28.84
PR | 998 | 03/18/22 | 626 | Barnhart, Joseph N |  | 4.44
PR | 998 | 03/18/22 | 626 | Barnhart, Joseph N |  | 4.44
PR | 998 | 03/18/22 | 627 | Barnhart, Thomas L |  | 116.28
PR | 998 | 03/18/22 | 661 | Gordillo, Emanuel D |  | 46.51
PR | 998 | 03/18/22 | 669 | Holmes, Anthony R |  | 58.75
PR | 998 | 03/18/22 | 669 | Holmes, Anthony R |  | 58.75
PR | 998 | 03/18/22 | 676 | Johnson, Jake E |  | 3.83
PR | 998 | 03/18/22 | 680 | Lovo, German G |  | 107.1
PR | 998 | 03/18/22 | 692 | Platero Navas, Julio A |  | 58.14
PR | 998 | 03/18/22 | 704 | Sanders, Allen O |  | 30.52
PR | 998 | 03/25/22 | 875 | Barnhart, Joseph N |  | 70.99
PR | 998 | 03/25/22 | 876 | Barnhart, Thomas L |  | 116.28
PR | 998 | 03/25/22 | 908 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 03/25/22 | 916 | Holmes, Anthony R |  | 146.88
PR | 998 | 03/25/22 | 927 | Lovo, German G |  | 101.75
PR | 998 | 03/25/22 | 927 | Lovo, German G |  | 5.36
PR | 998 | 03/25/22 | 939 | Platero Navas, Julio A |  | 55.23
PR | 998 | 03/25/22 | 939 | Platero Navas, Julio A |  | 2.91
PR | 998 | 03/25/22 | 950 | Sanders, Allen O |  | 21.8
PR | 998 | 04/01/22 | 21 | Barnhart, Joseph N |  | 44.37
PR | 998 | 04/01/22 | 21 | Barnhart, Joseph N |  | 13.31
PR | 998 | 04/01/22 | 22 | Barnhart, Thomas L |  | 116.28
PR | 998 | 04/01/22 | 41 | Eliassen, Cory H |  | 41.62
PR | 998 | 04/01/22 | 55 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 04/01/22 | 63 | Holmes, Anthony R |  | 146.88
PR | 998 | 04/01/22 | 74 | Lovo, German G |  | 107.1
PR | 998 | 04/01/22 | 85 | Platero Navas, Julio A |  | 58.14
PR | 998 | 04/01/22 | 96 | Sanders, Allen O |  | 17.44
PR | 998 | 04/01/22 | 108 | Donelson, Richard T |  | 4.78
PR | 998 | 04/08/22 | 227 | Barnhart, Joseph N |  | 22.19
PR | 998 | 04/08/22 | 227 | Barnhart, Joseph N |  | 17.75
PR | 998 | 04/08/22 | 227 | Barnhart, Joseph N |  | 4.44
PR | 998 | 04/08/22 | 228 | Barnhart, Thomas L |  | 93.02
PR | 998 | 04/08/22 | 261 | Gordillo, Emanuel D |  | 58.14
PR | 998 | 04/08/22 | 269 | Holmes, Anthony R |  | 146.88
PR | 998 | 04/08/22 | 280 | Lovo, German G |  | 100.41
PR | 998 | 04/08/22 | 291 | Platero Navas, Julio A |  | 54.51
PR | 998 | 04/08/22 | 317 | Platero Navas, Julio A |  | -54.51
PR | 998 | 04/08/22 | 318 | Platero Navas, Julio A |  | 54.51
PR | 998 | 04/15/22 | 475 | Barnhart, Joseph N |  | 57.68
PR | 998 | 04/15/22 | 475 | Barnhart, Joseph N |  | 8.87
PR | 998 | 04/15/22 | 476 | Barnhart, Thomas L |  | 69.77
PR | 998 | 04/15/22 | 508 | Gordillo, Emanuel D |  | 67.32
PR | 998 | 04/15/22 | 516 | Holmes, Anthony R |  | 146.88
PR | 998 | 04/15/22 | 527 | Lovo, German G |  | 100.41
PR | 998 | 04/15/22 | 538 | Platero Navas, Julio A |  | 64.26
PR | 998 | 04/15/22 | 549 | Sanders, Allen O |  | 17.44
PR | 998 | 04/22/22 | 803 | Barnhart, Joseph N |  | 22.19
PR | 998 | 04/22/22 | 803 | Barnhart, Joseph N |  | 79.87
PR | 998 | 04/22/22 | 804 | Barnhart, Thomas L |  | 93.02
PR | 998 | 04/22/22 | 836 | Gordillo, Emanuel D |  | 26.93
PR | 998 | 04/22/22 | 844 | Holmes, Anthony R |  | 58.75
PR | 998 | 04/22/22 | 855 | Lovo, German G |  | 85.68
PR | 998 | 04/22/22 | 866 | Platero Navas, Julio A |  | 64.26
PR | 998 | 04/22/22 | 877 | Sanders, Allen O |  | 26.16
PR | 998 | 04/22/22 | 889 | Donelson, Richard T |  | 4.78
PR | 998 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 39.93
PR | 998 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 13.31
PR | 998 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 4.44
PR | 998 | 04/29/22 | 1063 | Barnhart, Joseph N |  | 8.87
PR | 998 | 04/29/22 | 1064 | Barnhart, Thomas L |  | 69.77
PR | 998 | 04/29/22 | 1096 | Gordillo, Emanuel D |  | 40.39
PR | 998 | 04/29/22 | 1104 | Holmes, Anthony R |  | 88.13
PR | 998 | 04/29/22 | 1111 | Johnson, Jake E |  | 7.65
PR | 998 | 04/29/22 | 1111 | Johnson, Jake E |  | 3.83
PR | 998 | 04/29/22 | 1115 | Lovo, German G |  | 107.1
PR | 998 | 04/29/22 | 1127 | Platero Navas, Julio A |  | 51.41
PR | 998 | 04/29/22 | 1137 | Sanders, Allen O |  | 34.88
PR | 998 | 05/06/22 | 90 | Barnhart, Joseph N |  | 26.62
PR | 998 | 05/06/22 | 90 | Barnhart, Joseph N |  | 13.31
PR | 998 | 05/06/22 | 91 | Barnhart, Thomas L |  | 93.02
PR | 998 | 05/06/22 | 120 | Gordillo, Emanuel D |  | 53.86
PR | 998 | 05/06/22 | 128 | Holmes, Anthony R |  | 99.14
PR | 998 | 05/06/22 | 128 | Holmes, Anthony R |  | 47.74
PR | 998 | 05/06/22 | 139 | Lovo, German G |  | 78.99
PR | 998 | 05/06/22 | 151 | Platero Navas, Julio A |  | 60.24
PR | 998 | 05/06/22 | 160 | Sanders, Allen O |  | 19.62
PR | 998 | 05/13/22 | 325 | Barnhart, Thomas L |  | 93.02
PR | 998 | 05/13/22 | 355 | Gordillo, Emanuel D |  | 67.32
PR | 998 | 05/13/22 | 363 | Holmes, Anthony R |  | 73.44
PR | 998 | 05/13/22 | 363 | Holmes, Anthony R |  | 14.69
PR | 998 | 05/13/22 | 363 | Holmes, Anthony R |  | 58.75
PR | 998 | 05/13/22 | 373 | Lovo, German G |  | 42.84
PR | 998 | 05/13/22 | 373 | Lovo, German G |  | 64.26
PR | 998 | 05/13/22 | 385 | Platero Navas, Julio A |  | 25.7
PR | 998 | 05/13/22 | 385 | Platero Navas, Julio A |  | 25.7
PR | 998 | 05/13/22 | 396 | Sanders, Allen O |  | 37.06
PR | 998 | 05/20/22 | 598 | Barnhart, Joseph N |  | 13.77
PR | 998 | 05/20/22 | 598 | Barnhart, Joseph N |  | 9.18
PR | 998 | 05/20/22 | 598 | Barnhart, Joseph N |  | 4.59
PR | 998 | 05/20/22 | 598 | Barnhart, Joseph N |  | 9.18
PR | 998 | 05/20/22 | 599 | Barnhart, Thomas L |  | 95.47
PR | 998 | 05/20/22 | 616 | Eliassen, Cory H |  | 42.84
PR | 998 | 05/20/22 | 629 | Gordillo, Emanuel D |  | 6.73
PR | 998 | 05/20/22 | 629 | Gordillo, Emanuel D |  | 26.93
PR | 998 | 05/20/22 | 637 | Holmes, Anthony R |  | 76.5
PR | 998 | 05/20/22 | 647 | Lovo, German G |  | 66.1
PR | 998 | 05/20/22 | 659 | Platero Navas, Julio A |  | 64.26
PR | 998 | 05/20/22 | 669 | Sanders, Allen O |  | 24.82
PR | 998 | 05/20/22 | 681 | Donelson, Richard T |  | 38.25
PR | 998 | 05/27/22 | 867 | Barnhart, Joseph N |  | 96.39
PR | 998 | 05/27/22 | 868 | Barnhart, Thomas L |  | 95.47
PR | 998 | 05/27/22 | 886 | Eliassen, Cory H |  | 42.84
PR | 998 | 05/27/22 | 899 | Gordillo, Emanuel D |  | 67.32
PR | 998 | 05/27/22 | 906 | Holmes, Anthony R |  | 153
PR | 998 | 05/27/22 | 916 | Lovo, German G |  | 110.16
PR | 998 | 05/27/22 | 928 | Platero Navas, Julio A |  | 64.26
PR | 998 | 05/27/22 | 951 | Donelson, Richard T |  | 19.13
PR | 998 | 06/03/22 | 11 | Barnhart, Thomas L |  | 95.47
PR | 998 | 06/03/22 | 29 | Eliassen, Cory H |  | 42.84
PR | 998 | 06/03/22 | 41 | Gordillo, Emanuel D |  | 53.86
PR | 998 | 06/03/22 | 49 | Holmes, Anthony R |  | 30.6
PR | 998 | 06/03/22 | 49 | Holmes, Anthony R |  | 91.8
PR | 998 | 06/03/22 | 56 | Johnson, Jake E |  | 3.83
PR | 998 | 06/03/22 | 59 | Lovo, German G |  | 66.1
PR | 998 | 06/03/22 | 59 | Lovo, German G |  | 22.03
PR | 998 | 06/03/22 | 71 | Platero Navas, Julio A |  | 38.56
PR | 998 | 06/03/22 | 71 | Platero Navas, Julio A |  | 12.85
PR | 998 | 06/03/22 | 93 | Donelson, Richard T |  | 14.34
PR | 998 | 06/10/22 | 220 | Barnhart, Thomas L |  | 71.6
PR | 998 | 06/10/22 | 237 | Eliassen, Cory H |  | 21.42
PR | 998 | 06/10/22 | 249 | Gordillo, Emanuel D |  | 40.39
PR | 998 | 06/10/22 | 249 | Gordillo, Emanuel D |  | 13.46
PR | 998 | 06/10/22 | 257 | Holmes, Anthony R |  | 91.8
PR | 998 | 06/10/22 | 257 | Holmes, Anthony R |  | 30.6
PR | 998 | 06/10/22 | 267 | Lovo, German G |  | 88.13
PR | 998 | 06/10/22 | 279 | Platero Navas, Julio A |  | 47.39
PR | 998 | 06/10/22 | 289 | Sanders, Allen O |  | 31.59
PR | 998 | 06/10/22 | 301 | Donelson, Richard T |  | 23.91
PR | 998 | 06/17/22 | 465 | Barnhart, Joseph N |  | 4.59
PR | 998 | 06/17/22 | 465 | Barnhart, Joseph N |  | 13.77
PR | 998 | 06/17/22 | 465 | Barnhart, Joseph N |  | 18.36
PR | 998 | 06/17/22 | 465 | Barnhart, Joseph N |  | 18.36
PR | 998 | 06/17/22 | 466 | Barnhart, Thomas L |  | 95.47
PR | 998 | 06/17/22 | 484 | Eliassen, Cory H |  | 18.07
PR | 998 | 06/17/22 | 497 | Gordillo, Emanuel D |  | 18.93
PR | 998 | 06/17/22 | 497 | Gordillo, Emanuel D |  | 67.32
PR | 998 | 06/17/22 | 505 | Holmes, Anthony R |  | 43.03
PR | 998 | 06/17/22 | 505 | Holmes, Anthony R |  | 153
PR | 998 | 06/17/22 | 515 | Lovo, German G |  | 110.16
PR | 998 | 06/17/22 | 518 | McCabe, Thomas C |  | 16.87
PR | 998 | 06/17/22 | 518 | McCabe, Thomas C |  | 3.21
PR | 998 | 06/17/22 | 527 | Platero Navas, Julio A |  | 64.26
PR | 998 | 06/17/22 | 534 | Romero Garza, Jesus I |  | 13.94
PR | 998 | 06/17/22 | 537 | Sanders, Allen O |  | 30.47
PR | 998 | 06/17/22 | 537 | Sanders, Allen O |  | 29.34
PR | 998 | 06/17/22 | 537 | Sanders, Allen O |  | 13.54
PR | 998 | 06/17/22 | 540 | Taylor, Evan R |  | 23.24
PR | 998 | 06/17/22 | 541 | Trower-Kelly, Fidel D |  | 13.94
PR | 998 | 06/17/22 | 549 | Donelson, Richard T |  | 23.91
PR | 998 | 06/24/22 | 771 | Barnhart, Joseph N |  | 36.72
PR | 998 | 06/24/22 | 771 | Barnhart, Joseph N |  | 18.36
PR | 998 | 06/24/22 | 771 | Barnhart, Joseph N |  | 9.18
PR | 998 | 06/24/22 | 771 | Barnhart, Joseph N |  | 9.18
PR | 998 | 06/24/22 | 772 | Barnhart, Thomas L |  | 95.47
PR | 998 | 06/24/22 | 801 | Gordillo, Emanuel D |  | 38.71
PR | 998 | 06/24/22 | 809 | Holmes, Anthony R |  | 149.18
PR | 998 | 06/24/22 | 819 | Lovo, German G |  | 66.1
PR | 998 | 06/24/22 | 830 | Platero Navas, Julio A |  | 51.41
PR | 998 | 06/24/22 | 839 | Sanders, Allen O |  | 36.11
PR | 998 | 06/24/22 | 851 | Donelson, Richard T |  | 4.78
PR | 998 | 07/01/22 | 13 | Barnhart, Thomas L |  | 95.47
PR | 998 | 07/01/22 | 13 | Barnhart, Thomas L |  | 14.92
PR | 998 | 07/01/22 | 31 | Eliassen, Cory H |  | 20.08
PR | 998 | 07/01/22 | 42 | Gordillo, Emanuel D |  | 67.32
PR | 998 | 07/01/22 | 50 | Holmes, Anthony R |  | 153
PR | 998 | 07/01/22 | 62 | McCabe, Thomas C |  | 19.28
PR | 998 | 07/01/22 | 62 | McCabe, Thomas C |  | 3.21
PR | 998 | 07/01/22 | 70 | Platero Navas, Julio A |  | 41.77
PR | 998 | 07/01/22 | 78 | Sanders, Allen O |  | 47.39
PR | 998 | 07/01/22 | 78 | Sanders, Allen O |  | 22.57
PR | 998 | 07/01/22 | 78 | Sanders, Allen O |  | 9.03
PR | 998 | 07/01/22 | 81 | Taylor, Evan R |  | 46.47
PR | 998 | 07/01/22 | 82 | Trower-Kelly, Fidel D |  | 10.33
PR | 998 | 07/01/22 | 84 | Waites, Thaddeus Z |  | 30.98
PR | 998 | 07/08/22 | 175 | Barnhart, Thomas L |  | 71.6
PR | 998 | 07/08/22 | 205 | Gordillo, Emanuel D |  | 26.93
PR | 998 | 07/08/22 | 205 | Gordillo, Emanuel D |  | 26.93
PR | 998 | 07/08/22 | 213 | Holmes, Anthony R |  | 61.2
PR | 998 | 07/08/22 | 213 | Holmes, Anthony R |  | 30.6
PR | 998 | 07/08/22 | 213 | Holmes, Anthony R |  | 30.6
PR | 998 | 07/08/22 | 223 | Lovo, German G |  | 44.06
PR | 998 | 07/08/22 | 223 | Lovo, German G |  | 44.06
PR | 998 | 07/08/22 | 234 | Platero Navas, Julio A |  | 25.7
PR | 998 | 07/08/22 | 234 | Platero Navas, Julio A |  | 25.7
PR | 998 | 07/15/22 | 369 | Barnhart, Joseph N |  | 4.59
PR | 998 | 07/15/22 | 369 | Barnhart, Joseph N |  | 4.59
PR | 998 | 07/15/22 | 370 | Barnhart, Thomas L |  | 95.47
PR | 998 | 07/15/22 | 400 | Gordillo, Emanuel D |  | 65.64
PR | 998 | 07/15/22 | 408 | Holmes, Anthony R |  | 91.8
PR | 998 | 07/15/22 | 408 | Holmes, Anthony R |  | 57.38
PR | 998 | 07/15/22 | 414 | Johnson, Jake E |  | 3.83
PR | 998 | 07/15/22 | 417 | Lovo, German G |  | 110.16
PR | 998 | 07/15/22 | 429 | Platero Navas, Julio A |  | 64.26
PR | 998 | 07/22/22 | 608 | Barnhart, Joseph N |  | 4.59
PR | 998 | 07/22/22 | 609 | Barnhart, Thomas L |  | 119.34
PR | 998 | 07/22/22 | 638 | Gordillo, Emanuel D |  | 52.17
PR | 998 | 07/22/22 | 644 | Holmes, Anthony R |  | 118.58
PR | 998 | 07/22/22 | 673 | Sanders, Allen O |  | 47.39
PR | 998 | 07/29/22 | 724 | Barnhart, Joseph N |  | 32.13
PR | 998 | 07/29/22 | 753 | Gordillo, Emanuel D |  | 47.12
PR | 998 | 07/29/22 | 753 | Gordillo, Emanuel D |  | 13.46
PR | 998 | 07/29/22 | 759 | Holmes, Anthony R |  | 107.1
PR | 998 | 07/29/22 | 759 | Holmes, Anthony R |  | 30.6
PR | 998 | 07/29/22 | 798 | Gerard, Jeffrey S |  | 4.78
PR | 998 | 08/05/22 | 89 | Barnhart, Joseph N |  | 18.36
PR | 998 | 08/05/22 | 90 | Barnhart, Thomas L |  | 47.74
PR | 998 | 08/05/22 | 90 | Barnhart, Thomas L |  | 23.87
PR | 998 | 08/05/22 | 118 | Gordillo, Emanuel D |  | 40.39
PR | 998 | 08/05/22 | 124 | Holmes, Anthony R |  | 91.8
PR | 998 | 08/05/22 | 133 | Lovo, German G |  | 44.06
PR | 998 | 08/12/22 | 288 | Barnhart, Joseph N |  | 9.18
PR | 998 | 08/12/22 | 288 | Barnhart, Joseph N |  | 27.54
PR | 998 | 08/12/22 | 289 | Barnhart, Thomas L |  | 119.34
PR | 998 | 08/12/22 | 316 | Gordillo, Emanuel D |  | 40.39
PR | 998 | 08/12/22 | 322 | Holmes, Anthony R |  | 91.8
PR | 998 | 08/12/22 | 331 | Lovo, German G |  | 110.16
PR | 998 | 08/19/22 | 495 | Barnhart, Joseph N |  | 4.59
PR | 998 | 08/19/22 | 495 | Barnhart, Joseph N |  | 13.77
PR | 998 | 08/19/22 | 495 | Barnhart, Joseph N |  | 9.18
PR | 998 | 08/19/22 | 496 | Barnhart, Thomas L |  | 71.6
PR | 998 | 08/19/22 | 496 | Barnhart, Thomas L |  | 47.74
PR | 998 | 08/19/22 | 524 | Gordillo, Emanuel D |  | 53.86
PR | 998 | 08/19/22 | 530 | Holmes, Anthony R |  | 91.8
PR | 998 | 08/19/22 | 530 | Holmes, Anthony R |  | 30.6
PR | 998 | 08/19/22 | 539 | Lovo, German G |  | 66.1
PR | 998 | 08/19/22 | 539 | Lovo, German G |  | 22.03
PR | 998 | 08/26/22 | 761 | Barnhart, Joseph N |  | 13.77
PR | 998 | 08/26/22 | 762 | Barnhart, Thomas L |  | 23.87
PR | 998 | 08/26/22 | 790 | Gordillo, Emanuel D |  | 35.34
PR | 998 | 08/26/22 | 790 | Gordillo, Emanuel D |  | 3.37
PR | 998 | 08/26/22 | 796 | Holmes, Anthony R |  | 19.13
PR | 998 | 08/26/22 | 796 | Holmes, Anthony R |  | 7.65
PR | 998 | 08/26/22 | 805 | Lovo, German G |  | 22.03
PR | 998 | 09/02/22 | 9 | Barnhart, Thomas L |  | 71.6
PR | 998 | 09/02/22 | 37 | Gordillo, Emanuel D |  | 21.04
PR | 998 | 09/02/22 | 37 | Gordillo, Emanuel D |  | 1.68
PR | 998 | 09/02/22 | 43 | Holmes, Anthony R |  | 51.64
PR | 998 | 09/09/22 | 201 | Barnhart, Thomas L |  | 47.74
PR | 998 | 09/09/22 | 236 | Holmes, Anthony R |  | 49.73
PR | 998 | 09/09/22 | 241 | Johnson, Jake E |  | 3.83
PR | 998 | 09/09/22 | 265 | Sanders, Allen O |  | 13.54
PR | 998 | 09/16/22 | 430 | Barnhart, Joseph N |  | 22.95
PR | 998 | 09/16/22 | 430 | Barnhart, Joseph N |  | 9.18
PR | 998 | 09/16/22 | 430 | Barnhart, Joseph N |  | 13.77
PR | 998 | 09/16/22 | 460 | Gordillo, Emanuel D |  | 11.78
PR | 998 | 09/16/22 | 460 | Gordillo, Emanuel D |  | 6.73
PR | 998 | 09/16/22 | 465 | Holmes, Anthony R |  | 26.78
PR | 998 | 09/16/22 | 465 | Holmes, Anthony R |  | 15.3
PR | 998 | 09/16/22 | 470 | Johnson, Jake E |  | 3.83
PR | 998 | 09/23/22 | 565 | Barnhart, Thomas L |  | 23.87
PR | 998 | 09/23/22 | 625 | Sanders, Allen O |  | 18.05
PR | 998 | 09/30/22 | 815 | Barnhart, Joseph N |  | 18.36
PR | 998 | 09/30/22 | 815 | Barnhart, Joseph N |  | 9.18
PR | 998 | 09/30/22 | 815 | Barnhart, Joseph N |  | 4.59
PR | 998 | 09/30/22 | 815 | Barnhart, Joseph N |  | 4.59
PR | 998 | 09/30/22 | 816 | Barnhart, Thomas L |  | 23.87
PR | 998 | 09/30/22 | 848 | Holmes, Anthony R |  | 3.83
PR | 998 | 10/07/22 | 28 | Barnhart, Joseph N |  | 19.58
PR | 998 | 10/07/22 | 28 | Barnhart, Joseph N |  | 24.48
PR | 998 | 10/07/22 | 28 | Barnhart, Joseph N |  | 14.69
PR | 998 | 10/07/22 | 28 | Barnhart, Joseph N |  | 19.58
PR | 998 | 10/07/22 | 58 | Gordillo, Emanuel D |  | 5.05
PR | 998 | 10/07/22 | 63 | Holmes, Anthony R |  | 12.39
PR | 998 | 10/14/22 | 283 | Barnhart, Joseph N |  | 19.58
PR | 998 | 10/14/22 | 283 | Barnhart, Joseph N |  | 4.9
PR | 998 | 10/14/22 | 283 | Barnhart, Joseph N |  | 4.9
PR | 998 | 10/14/22 | 283 | Barnhart, Joseph N |  | 4.9
PR | 998 | 10/21/22 | 477 | Barnhart, Joseph N |  | 58.75
PR | 998 | 10/21/22 | 477 | Barnhart, Joseph N |  | 4.9
PR | 998 | 10/21/22 | 477 | Barnhart, Joseph N |  | 19.58
PR | 998 | 10/21/22 | 477 | Barnhart, Joseph N |  | 29.38
PR | 998 | 10/21/22 | 518 | Johnson, Jake E |  | 3.83
PR | 998 | 10/28/22 | 754 | Barnhart, Joseph N |  | 19.58
PR | 998 | 10/28/22 | 754 | Barnhart, Joseph N |  | 19.58
PR | 998 | 11/04/22 | 75 | Sanders, Allen O |  | 37.94
PR | 998 | 11/18/22 | 368 | Barnhart, Joseph N |  | 9.79
PR | 998 | 11/18/22 | 368 | Barnhart, Joseph N |  | 14.69
PR | 998 | 11/18/22 | 368 | Barnhart, Joseph N |  | 4.9
PR | 998 | 11/18/22 | 368 | Barnhart, Joseph N |  | 9.79
PR | 998 | 11/18/22 | 411 | Johnson, Jake E |  | 3.83
PR | 998 | 11/18/22 | 435 | Sanders, Allen O |  | 35.57
PR | 998 | 11/23/22 | 513 | Barnhart, Joseph N |  | 44.06
PR | 998 | 11/23/22 | 513 | Barnhart, Joseph N |  | 29.38
PR | 998 | 11/23/22 | 513 | Barnhart, Joseph N |  | 4.9
PR | 998 | 11/23/22 | 555 | Johnson, Jake E |  | 3.83
PR | 998 | 12/02/22 | 9 | Barnhart, Joseph N |  | 19.58
PR | 998 | 12/02/22 | 9 | Barnhart, Joseph N |  | 9.79
PR | 998 | 12/02/22 | 9 | Barnhart, Joseph N |  | 4.9
PR | 998 | 12/02/22 | 39 | Gordillo, Emanuel D |  | 3.37
PR | 998 | 12/02/22 | 44 | Holmes, Anthony R |  | 8.26
PR | 998 | 12/02/22 | 49 | Johnson, Jake E |  | 3.83
PR | 998 | 12/09/22 | 303 | Holmes, Anthony R |  | 8.26
PR | 998 | 12/23/22 | 845 | Barnhart, Joseph N |  | 22.03
PR | 998 | 12/23/22 | 845 | Barnhart, Joseph N |  | 19.58
PR | 998 | 12/23/22 | 916 | Sanders, Allen O |  | 11.86
PR | 998 | 12/30/22 | 1015 | Barnhart, Joseph N |  | 17.14
PR | 998 | 12/30/22 | 1052 | Holmes, Anthony R |  | 12.39
AR | 999 | 07/19/19 | 604 | Compass General Construction I, LLC$Mari |  | -86400 | 037379
AR | 999 | 08/15/19 | 759 | Compass General Construction I, LLC$Mari |  | -32000 | 037396
AR | 999 | 08/15/19 | 759 | Compass General Construction I, LLC$Mari |  | -14800 | 037396
AR | 999 | 08/15/19 | 759 | Compass General Construction I, LLC$Mari |  | -55800 | 037396
AR | 999 | 08/15/19 | 759 | Compass General Construction I, LLC$Mari |  | -20000 | 037396
AR | 999 | 09/20/19 | 569 | Compass General Construction I, LLC$Mari |  | -55800 | 037413
AR | 999 | 09/20/19 | 569 | Compass General Construction I, LLC$Mari |  | -64600 | 037413
AR | 999 | 09/20/19 | 569 | Compass General Construction I, LLC$Mari |  | -8080 | 037413
AR | 999 | 10/18/19 | 538 | Compass General Construction I, LLC$Mari |  | -23400 | 037425
AR | 999 | 11/04/19 | 138 | Compass General Construction I, LLC$Mari |  | -21600 | 037434
AR | 999 | 11/19/19 | 562 | Compass General Construction I, LLC$Mari |  | -64600 | 037443
AR | 999 | 11/19/19 | 562 | Compass General Construction I, LLC$Mari |  | -8500 | 037443
AR | 999 | 11/19/19 | 562 | Compass General Construction I, LLC$Mari |  | -8600 | 037443
AR | 999 | 11/19/19 | 562 | Compass General Construction I, LLC$Mari |  | -961 | 037443
AR | 999 | 12/13/19 | 478 | Compass General Construction I, LLC$Mari |  | -7800 | 037454
AR | 999 | 12/13/19 | 478 | Compass General Construction I, LLC$Mari |  | -8600 | 037454
AR | 999 | 12/13/19 | 478 | Compass General Construction I, LLC$Mari |  | -80700 | 037454
AR | 999 | 12/13/19 | 478 | Compass General Construction I, LLC$Mari |  | -98300 | 037454
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -8500 | 037469
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -25700 | 037469
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -35100 | 037469
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -31900 | 037469
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -49100 | 037469
AR | 999 | 01/20/20 | 654 | Compass General Construction I, LLC$Mari |  | -52750 | 037469
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 8500 | 037474
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 25700 | 037474
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 35100 | 037474
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 31900 | 037474
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 49100 | 037474
AR | 999 | 01/20/20 | 665 | Compass General Construction I, LLC$Mari |  | 52750 | 037474
AR | 999 | 01/20/20 | 666 | Compass General Construction I, LLC$Mari |  | -8500 | 037475
AR | 999 | 01/20/20 | 666 | Compass General Construction I, LLC$Mari |  | -35100 | 037475
AR | 999 | 01/20/20 | 666 | Compass General Construction I, LLC$Mari |  | -7975 | 037475
AR | 999 | 01/20/20 | 666 | Compass General Construction I, LLC$Mari |  | -49100 | 037475
AR | 999 | 01/20/20 | 666 | Compass General Construction I, LLC$Mari |  | -52750 | 037475
AR | 999 | 02/19/20 | 446 | Compass General Construction I, LLC$Mari |  | -25700 | 037481
AR | 999 | 02/19/20 | 446 | Compass General Construction I, LLC$Mari |  | -16150 | 037481
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -23700 | 037492
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -16150 | 037492
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -168160 | 037492
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -48100 | 037492
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -4950 | 037492
AR | 999 | 03/20/20 | 652 | Compass General Construction I, LLC$Mari |  | -3425 | 037492
AR | 999 | 07/20/20 | 369 | Compass General Construction I, LLC$Mari |  | -6000 | 037521
AR | 999 | 07/20/20 | 369 | Compass General Construction I, LLC$Mari |  | -15500 | 037521
AR | 999 | 11/23/20 | 435 | Compass General Construction I, LLC$Mari |  | -2000 | 037563
AR | 999 | 11/23/20 | 435 | Compass General Construction I, LLC$Mari |  | -2000 | 037563
AR | 999 | 01/22/21 | 317 | Compass General Construction I, LLC$Mari |  | -9820 | 037590
AR | 999 | 01/22/21 | 317 | Compass General Construction I, LLC$Mari |  | -10550 | 037590
AR | 999 | 01/22/21 | 317 | Compass General Construction I, LLC$Mari |  | -25950 | 037590
AR | 999 | 01/22/21 | 317 | Compass General Construction I, LLC$Mari |  | -25950 | 037590
AR | 999 | 02/17/21 | 411 | Compass General Construction I, LLC$Mari |  | -39280 | 037595
AR | 999 | 02/17/21 | 411 | Compass General Construction I, LLC$Mari |  | -21100 | 037595
AR | 999 | 02/17/21 | 411 | Compass General Construction I, LLC$Mari |  | -165520 | 037595
AR | 999 | 02/17/21 | 411 | Compass General Construction I, LLC$Mari |  | -3854 | 037595
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -23925 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -21100 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -39800 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -40040 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -41380 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -144300 | 037623
AR | 999 | 03/19/21 | 362 | Compass General Construction I, LLC$Mari |  | -27820 | 037623
AR | 999 | 04/20/21 | 380 | Compass General Construction I, LLC$Mari |  | -73950 | 037642
AR | 999 | 04/20/21 | 380 | Compass General Construction I, LLC$Mari |  | -28880 | 037642
AR | 999 | 04/20/21 | 380 | Compass General Construction I, LLC$Mari |  | -166140 | 037642
AR | 999 | 04/20/21 | 380 | Compass General Construction I, LLC$Mari |  | -28500 | 037642
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -24650 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -106150 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -110760 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -24537 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -53750 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -3250 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -4094 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -2094 | 037659
AR | 999 | 05/19/21 | 371 | Compass General Construction I, LLC$Mari |  | -3618 | 037659
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | 6900 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | 35100 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | 10513 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -264100 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -7650 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -255900 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -39285 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -2100 | 037685
AR | 999 | 06/18/21 | 502 | Compass General Construction I, LLC$Mari |  | -4144 | 037685
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -196425 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -235710 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -235710 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -167470 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -3280 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -43380 | 037702
AR | 999 | 07/16/21 | 416 | Compass General Construction I, LLC$Mari |  | -8750 | 037702
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -11250 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -26190 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -11250 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -26190 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -11250 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -26190 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -11250 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -18605 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -11250 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -9600 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -3280 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -4820 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -33000 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -18770 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -38150 | 037716
AR | 999 | 08/20/21 | 702 | Compass General Construction I, LLC$Mari |  | -50250 | 037716
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -9600 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -9600 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -820 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -6300 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -187653 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -8100 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -43305 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -8100 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -28870 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -28870 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -22500 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -5750 | 037739
AR | 999 | 09/20/21 | 435 | Compass General Construction I, LLC$Mari |  | -20342 | 037739
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -6500 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -9600 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -9600 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -158785 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -173220 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -8100 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -173220 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -8100 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -180000 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -8100 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -3450 | 037757
AR | 999 | 10/20/21 | 738 | Compass General Construction I, LLC$Mari |  | -22378 | 037757
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -820 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -28870 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -57740 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -86610 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -86610 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -22500 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -8800 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -2300 | 037772
AR | 999 | 11/19/21 | 531 | Compass General Construction I, LLC$Mari |  | -8000 | 037772
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -3273 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -3273 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -3273 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -3273 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -3273 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -2400 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -6900 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -28870 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -8800 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -28870 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -8800 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -8800 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -8800 | 037787
AR | 999 | 12/17/21 | 621 | Compass General Construction I, LLC$Mari |  | -2356 | 037787
AR | 999 | 01/18/22 | 366 | Compass General Construction I, LLC$Mari |  | -29452 | 037803
AR | 999 | 01/18/22 | 366 | Compass General Construction I, LLC$Mari |  | -29452 | 037803
AR | 999 | 01/18/22 | 366 | Compass General Construction I, LLC$Mari |  | 1262 | 037803
AR | 999 | 01/31/22 | 723 | SW Marina Square, LLC |  | -37500 | 037809
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -3510 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -29452 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -29452 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -29452 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -19260 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -1970 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -1970 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -12300 | 037818
AR | 999 | 02/18/22 | 591 | Compass General Construction I, LLC$Mari |  | -7300 | 037818
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 3510 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 29452 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 29452 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 29452 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 19260 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 1970 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 1970 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 12300 | 037822
AR | 999 | 02/18/22 | 595 | Compass General Construction I, LLC$Mari |  | 7300 | 037822
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -3510 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -29452 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -29452 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -29452 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -19268 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -1970 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -1970 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -12300 | 037823
AR | 999 | 02/18/22 | 596 | Compass General Construction I, LLC$Mari |  | -7300 | 037823
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | -3510 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | -8257 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | -2600 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | -13790 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | -36900 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | 5048 | 037835
AR | 999 | 03/18/22 | 737 | Compass General Construction I, LLC$Mari |  | 83 | 037835
AR | 999 | 04/20/22 | 778 | Compass General Construction I, LLC$Mari |  | -3400 | 037850
AR | 999 | 04/20/22 | 778 | Compass General Construction I, LLC$Mari |  | -3940 | 037850
AR | 999 | 04/20/22 | 778 | Compass General Construction I, LLC$Mari |  | -17730 | 037850
AR | 999 | 04/20/22 | 778 | Compass General Construction I, LLC$Mari |  | -19700 | 037850
AR | 999 | 04/20/22 | 778 | Compass General Construction I, LLC$Mari |  | -1970 | 037850
AR | 999 | 04/20/22 | 794 | Compass General Construction I, LLC$Mari |  | 3400 | 037856
AR | 999 | 04/20/22 | 794 | Compass General Construction I, LLC$Mari |  | 3940 | 037856
AR | 999 | 04/20/22 | 794 | Compass General Construction I, LLC$Mari |  | 17730 | 037856
AR | 999 | 04/20/22 | 794 | Compass General Construction I, LLC$Mari |  | 19700 | 037856
AR | 999 | 04/20/22 | 794 | Compass General Construction I, LLC$Mari |  | 1970 | 037856
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -3940 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -17730 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -19700 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -1970 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -2400 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -1900 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -1900 | 037857
AR | 999 | 04/20/22 | 795 | Compass General Construction I, LLC$Mari |  | -429 | 037857
AR | 999 | 05/20/22 | 704 | Compass General Construction I, LLC$Mari |  | -3400 | 037873
AR | 999 | 05/20/22 | 704 | Compass General Construction I, LLC$Mari |  | -17730 | 037873
AR | 999 | 05/20/22 | 704 | Compass General Construction I, LLC$Mari |  | -19700 | 037873
AR | 999 | 05/20/22 | 704 | Compass General Construction I, LLC$Mari |  | -13020 | 037873
AR | 999 | 06/20/22 | 608 | Compass General Construction I, LLC$Mari |  | -5580 | 037887
AR | 999 | 06/20/22 | 608 | Compass General Construction I, LLC$Mari |  | -3110 | 037887
AR | 999 | 06/20/22 | 608 | Compass General Construction I, LLC$Mari |  | -1739 | 037887
AR | 999 | 06/20/22 | 608 | Compass General Construction I, LLC$Mari |  | -19404 | 037887
AR | 999 | 08/19/22 | 585 | Compass General Construction I, LLC$Mari |  | -16308 | 037925
AR | 999 | 09/19/22 | 530 | Compass General Construction I, LLC$Mari |  | -1494 | 037938
AR | 999 | 09/19/22 | 530 | Compass General Construction I, LLC$Mari |  | -4539 | 037938
AR | 999 | 10/20/22 | 471 | Compass General Construction I, LLC$Mari |  | -6575 | 037973
AR | 999 | 10/20/22 | 471 | Compass General Construction I, LLC$Mari |  | -944 | 037973