## 01 Overview
OWP #2098 · Trailside Apartment Community Phase II
Chinn Construction, LLC · 170 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 6917965.74
Revised budget (expenses) | 5187333
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 6917965.74
Retention held | 345898.29
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 74155.97
AP | 1652638.19
PR | 2334399.23
AR | -6906115.74

## 02 Job Info
Job Information
Job ID | 2098
Project name | Trailside Apartment Community Phase II
General contractor | Chinn Construction, LLC
Owner | Trailside Ph II SH Holdings, LLC (Dallas, TX)
Units | 170
Insurance | Standard (non-OCIP)
Job start | Aug 2023
Expected completion | TBD (active)
Architect | Weber Thompson Architects
MEP Engineer | Marx-Okubo
Status | ACTIVE · in-progress
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 6885880 | 6917965.74
Executed change orders (net) | 0 | 32085.74
Total contract value
Executed Change Orders
CO # | Description | Amount
1 | Pet Wash Budget Reallocation | 0
2 | Gas Meter at Boiler Room | 4426
3 | Condensate Drains at Units | 60075
4 | Lixil Trim Reduction + Sink Upgrades | 12975
5 | OT Premium 12/16/23 | 1272
6 | Reduced Cost on Toilets | -2055
7 | Maint. Room Plumbing Fixtures | 9500
8 | Toilet Flange Backcharge | -18984.26
9 | Corrections to Toilet Flange Backcharge | 2904
10 | Shower Stall Backcharges | -52104
11 | Retail Gas & Condensate Changes | 5019
12 | Damaged Toilet Seats | 308
13 | Move Retail Condensate | 464
14 | L2 Amenity Coffee Maker | 489
15 | L2 Amenity Coffee Maker - CANCELLED | -489
16 | Attic Stock | 1220
17 | Boiler Room Cond Drain + Attic Stock Premium | 803
18 | Garage Heat Trace | 6263

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 12750 | 13000 | 10219 |  | 0
101 | Takeoff & Purchase Labor | 29750 | 30000 | 28199 |  | 0
110 | Underground Labor | 100467 | 100967 | 71186.76 |  | 0
111 | Garage Labor | 116833 | 117133 | 112004.5 |  | 0
112 | Canout Labor | 48144 | 48994 | 37993.5 |  | 0
120 | Roughin Labor | 1037606 | 1069806 | 797900.1 |  | 0
130 | Finish Labor | 196840 | 197570 | 222921 |  | 0
140 | Gas Labor | 11400 | 13400 | 23969.5 |  | 0
141 | Water Main/Insulation Lab | 141720 | 142820 | 120399.72 |  | 0
142 | Mech Room Labor | 65600 | 65600 | 80791 |  | 0
143 | Condensation Drains Labor | 0 | 0 | 0 |  | 0
150 | Warranty Labor | 0 | 0 | 26715.88 |  | 0
151 | T&M Labor | 0 | 0 | 224 |  | 0
210 | Underground Material | 85150 | 85650 | 101624.25 |  | 0
211 | Garage Material | 106000 | 106150 | 17998.09 |  | 0
212 | Canout Material | 47200 | 47200 | 23927.32 |  | 0
220 | Roughin Material | 611575 | 623175 | 266624.03 |  | 0
230 | Finish Material | 1131147 | 1114762 | 912915.01 |  | -492.4
240 | Gas Material | 10450 | 22400 | 14686.12 |  | 0
241 | Water Main/Insulation Mat | 136575 | 138575 | 121627.31 |  | 0
242 | Mech Room Material | 71500 | 71500 | 58031.73 |  | 0
250 | Warranty Material | 0 | 0 | 1481.84 |  | 0
600 | Subcontractor | 25130 | 25130 | 16200 |  | 0
601 | Engineering/Plans | 124500 | 124500 | 106959.5 |  | 0
602 | Rental Equipment | 18000 | 18000 | 13081.86 |  | 0
603 | Permits & Licenses | 40500 | 40500 | 26503.77 |  | 0
607 | Other Expenses | 83451 | 83451 | 77812.75 |  | 0
995 | Payroll Burden | 733502.32 | 749404.3 | 662213.84 |  | 0
998 | Payroll Taxes | 134724.92 | 137645.7 | 118832.01 |  | 0
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 12 | 1799290 | 1532299.96
Material | 8 | 2209412 | 1517433.86
Overhead | 5 | 291581 | 240557.88
Burden | 2 | 887050 | 781045.85
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 13000 | 10219
101 | Takeoff & Purchase Labor | 30000 | 28199
110 | Underground Labor | 100967 | 71186.76
111 | Garage Labor | 117133 | 112004.5
112 | Canout Labor | 48994 | 37993.5
120 | Roughin Labor | 1069806 | 797900.1
130 | Finish Labor | 197570 | 222921
140 | Gas Labor | 13400 | 23969.5
141 | Water Main/Insulation Lab | 142820 | 120399.72
142 | Mech Room Labor | 65600 | 80791
150 | Warranty Labor | 0 | 26715.88
151 | T&M Labor | 0 | 224
210 | Underground Material | 85650 | 101624.25
211 | Garage Material | 106150 | 17998.09
212 | Canout Material | 47200 | 23927.32
220 | Roughin Material | 623175 | 266624.03
230 | Finish Material | 1114762 | 912915.01
240 | Gas Material | 22400 | 14686.12
241 | Water Main/Insulation Mat | 138575 | 121627.31
242 | Mech Room Material | 71500 | 58031.73
250 | Warranty Material | 0 | 1481.84
600 | Subcontractor | 25130 | 16200
601 | Engineering/Plans | 124500 | 106959.5
602 | Rental Equipment | 18000 | 13081.86
603 | Permits & Licenses | 40500 | 26503.77
607 | Other Expenses | 83451 | 77812.75
995 | Payroll Burden | 749404.3 | 662213.84
998 | Payroll Taxes | 137645.7 | 118832.01

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Keller Supply Company | 580995.8 | 93
Consolidated Supply Co. | 372631.96 | 250
Rosen Supply Kirkland | 172522.87 | 131
California Hydronics Corp | 147326.5 | 7
Franklin Engineering | 106959.5 | 14
Pacific Plumbing Supply Co., LLC | 105473.62 | 135
Hub International Northwest | 60451 | 1
Bank of America CC | 31431.65 | 18
University Silver Cloud Hotel $Trailside | 16313.32 | 20
Mechanical Resource Services, Inc. | 10350 | 1
MacArthur Co. NW 6276 | 10064.08 | 6
Sunstate Equipment Co | 9483.84 | 21
Ferguson Enterprises, Inc. #3007 | 5547.94 | 10
Kele, Inc $ MI Controls | 5463.56 | 10
Williams Scotsman, Inc. $Mobile Mini | 3598.02 | 17
Capital One Credit Card | 3262.4 | 54
Chemical Products Company | 3150 | 1
Mechanical Sales, Inc. | 2941.3 | 6
Patchworks, Inc. | 1800 | 1
Seton Identification Products | 1069.75 | 2
Cascade Restoration Co. | 620 | 1
ACME Corp | 442.73 | 5
A.R. Brown Backflow Testing | 280 | 1
Core & Main LP $HD Supply Waterworks | 196.16 | 1
Sunbelt Rentals, Inc. | 0 | 2
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Paco Leyva, Orlando | 2900.8 | 177226 |  | LEAD/SUPERVISOR
Galdamez, Dagoberto A | 2484.5 | 104538 |  | LEAD/SUPERVISOR
Balderas Ortiz, Ricardo I | 2342.5 | 103246 |  | LEAD/SUPERVISOR
Lopez, Maslin A | 1792 | 59136 |  | JOURNEYMAN
Carmona, Raul O | 1766 | 93757 |  | LEAD/SUPERVISOR
Jimenez Alvarenga, Gerson M | 1594 | 59222 |  | LEAD/SUPERVISOR
Mendoza Morales, Jesus A | 1445.5 | 59388 |  | LEAD/SUPERVISOR
Gochez Molina, Douglas O | 1326 | 33225 |  | JOURNEYMAN
Suniga Aviles, Kelvin A | 1303 | 27702 |  | JOURNEYMAN
Zuniga Avilez, Eduar A | 1298 | 26406 |  | JOURNEYMAN
Games, Jordan M | 1236.5 | 66095 |  | LEAD/SUPERVISOR
Escobar Ramirez, Carlos M | 1106 | 22120 |  | JOURNEYMAN
Nunez Bravo, Jose L | 1031 | 23721 |  | JOURNEYMAN
Escalante Escobar, Boanerge | 904 | 31640 |  | JOURNEYMAN
Weeks, Gregg A | 874 | 41952 |  | LEAD/SUPERVISOR
Lima Romero, Melvin A | 866 | 36696 |  | LEAD/SUPERVISOR
Anderson, Richard P | 775.5 | 50474 |  | LEAD/SUPERVISOR
Melgar Moz, Brandon | 733 | 16270 |  | JOURNEYMAN
Boss, Benjamin T | 692 | 34884 |  | LEAD/SUPERVISOR
Puentez, Victor M | 656 | 12672 |  | APPRENTICE/HELPER
Trower-Kelly, Fidel D | 633.5 | 19732 |  | JOURNEYMAN
Yohannes Jr., Samson | 633.5 | 20906 |  | JOURNEYMAN
Castro Hernandez, Jose A | 632 | 34128 |  | LEAD/SUPERVISOR
Chastain, Aaron R | 617.5 | 14082 |  | JOURNEYMAN
Martinez Garcia, Cesar B | 583 | 11660 |  | JOURNEYMAN
Taylor, Evan R | 576.8 | 29991 |  | LEAD/SUPERVISOR
Aquino, Juan | 572 | 15452 |  | JOURNEYMAN
Storozhuk, Maxim A | 562 | 12364 |  | JOURNEYMAN
Cosentino, Brandon C | 544.5 | 12300 |  | JOURNEYMAN
Eliassen, Cory H | 534.8 | 20320 |  | LEAD/SUPERVISOR
Sontay Garcia, Juan C | 503 | 10563 |  | JOURNEYMAN
Cruz Reyes, Jose | 484 | 19967 |  | LEAD/SUPERVISOR
McCurry, Maxwell J | 477 | 11448 |  | JOURNEYMAN
Ortiz Carmona, Juan M | 439 | 14048 |  | JOURNEYMAN
Barnhart, Joseph N | 416.5 | 28518 |  | LEAD/SUPERVISOR
Molina, Carlos G | 375 | 9750 |  | JOURNEYMAN
Gerard, Jeffrey S | 343.5 | 23454 |  | LEAD/SUPERVISOR
Hubbard, Justin A | 336 | 15456 |  | LEAD/SUPERVISOR
Platero Navas, Ronald A | 312 | 6240 |  | JOURNEYMAN
Portillo Soriano, Walter A | 294 | 10395 |  | JOURNEYMAN
Ascencio, Jose L | 278 | 11802 |  | LEAD/SUPERVISOR
Belcher, Jacob T | 277 | 7756 |  | JOURNEYMAN
Johnson, Jake E | 273 | 14168 |  | LEAD/SUPERVISOR
Young, Joshua S | 256 | 6912 |  | JOURNEYMAN
Vazquez Popoca, Jose N | 252 | 8820 |  | JOURNEYMAN
Gomez Aguirre, Exequiel | 240 | 5760 |  | JOURNEYMAN
Araque, Mario W | 238 | 5398 |  | JOURNEYMAN
Zepeda Mendoza, Cesar | 214 | 4708 |  | JOURNEYMAN
Diaz Morales, Guni | 204 | 4488 |  | JOURNEYMAN
Diaz Morales, Teofilo | 200 | 4400 |  | JOURNEYMAN
Zamudio Sanchez, Jose R | 189 | 9072 |  | LEAD/SUPERVISOR
Diaz Morales, Cristian A | 168 | 3696 |  | JOURNEYMAN
Barnhart, Thomas L | 163.5 | 7030 |  | LEAD/SUPERVISOR
McCabe, Thomas C | 163.5 | 7194 |  | LEAD/SUPERVISOR
Guerrero Espinoza, Mario | 150 | 4500 |  | JOURNEYMAN
Romero Garza, Jesus I | 134 | 4521 |  | JOURNEYMAN
Rodriguez Arevalos, Christian | 76 | 3539 |  | LEAD/SUPERVISOR
Diaz Morales, Elber | 56 | 1232 |  | JOURNEYMAN
Diaz Morales, Urias | 48 | 1056 |  | JOURNEYMAN
Cruz, Azael S | 47 | 1504 |  | JOURNEYMAN
Perez Araque, Manuel A | 46 | 1345 |  | JOURNEYMAN
Nuno Ordonez, Roberto F | 40 | 960 |  | JOURNEYMAN
Rodriguez, Eduardo D | 40 | 1040 |  | JOURNEYMAN
Draves, Steven W | 32.2 | 1774 |  | LEAD/SUPERVISOR
Jimenez, D'angelo J | 28 | 784 |  | JOURNEYMAN
Reed, Reuben H | 24 | 1488 |  | LEAD/SUPERVISOR
Gerard, Mitchell J | 22 | 1342 |  | LEAD/SUPERVISOR
Wilson, Garret A | 21 | 1134 |  | LEAD/SUPERVISOR
Gerard, Jordan E | 17 | 1200 |  | LEAD/SUPERVISOR
Silva Morales, Jair J | 16 | 544 |  | JOURNEYMAN
Castro, Marcus J | 14 | 358 |  | JOURNEYMAN
Eisenhauer, Tommy J | 12 | 798 |  | LEAD/SUPERVISOR
Bautista Quintero, Isidoro | 8 | 160 |  | JOURNEYMAN
Fox, Tamron P | 8 | 216 |  | JOURNEYMAN
Hernandez Gonzalez, Osbaldo | 7 | 294 |  | LEAD/SUPERVISOR
Waites, Thaddeus Z | 6 | 427 |  | LEAD/SUPERVISOR
Amaya Gonzalez, Edilberto A | 6 | 459 |  | OT-ONLY
Goodwin, Marcus A | 6 | 225 |  | OT-ONLY
de Dios, Pedro | 4 | 104 |  | JOURNEYMAN

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 32 | 21585 | 1060576
JOURNEYMAN | 44 | 18727 | 479422
APPRENTICE/HELPER | 1 | 656 | 12672
OT-ONLY | 2 | 12 | 684

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 40980
Active workers | 79
Hours per unit (to date) | 241.1
Revenue per labor hour (billed) | 168.81
Percent complete | 100%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 25.02% | 34%
Roughin labor share (code 120) | 59.46% | 45%
Top vendor concentration | 35.16% | 38%
Hours per unit | 241.0588 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Finish Labor (130) over revised | ⚠ WATCH | Actual $222,921 vs revised $197,570 (+13%) — monitor
Gas Labor (140) CRITICAL overrun | ⚠ WATCH | Actual $23,970 vs revised $13,400 (+79%) — needs immediate attention
Mech Room Labor (142) over revised | ⚠ WATCH | Actual $80,791 vs revised $65,600 (+23%) — monitor
Warranty Labor (150) unbudgeted | ⚠ WATCH | No revised budget but $26,716 actual spend — needs CO or budget transfer
Underground Material (210) over revised | ⚠ WATCH | Actual $101,624 vs revised $85,650 (+19%) — monitor
Top vendor concentration (Keller Supply Compan) | ✓ OK | 35% of AP ($580,996) — acceptable
Retention aging | ✓ OK | $345,898 held · 5.0% of billed · standard range
Forecast margin | ✓ OK | 25.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 4073043.39 | 4073043.39
Revenue billed (AR ·-1) | -6917965.74 | 6906115.74
AP source total |  | 1652638.19
PR source total |  | 2334399.23
GL source total |  | 74155.97

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-23 | v1.0 · live | Initial build for #2098 live project. 17-tab JCR schema on revised budget basis.