## Summary
#2098 · Trailside 2
Chinn Construction, LLC · 170 units · ACTIVE · 100.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
6917965.74 | 25.02% | 6917965.74 | 0
Key facts
Original contract |  | 6885880
Revised contract (CO impact) |  | 6917965.74
Executed COs (net) |  | 32085.74
Retention held |  | 345898.29
Revised expense budget |  | 5187333
Forecast net profit |  | 1730632.74
Percent complete |  | 100%
Live signals
Finish Labor (130) over | ⚠ WATCH | Actual $222,921 vs revised $197,570 (+13%) — monitor
Gas Labor (140) CRITICAL | ⚠ WATCH | Actual $23,970 vs revised $13,400 (+79%) — needs attention
Mech Room Labor (142) over | ⚠ WATCH | Actual $80,791 vs revised $65,600 (+23%) — monitor
Warranty Labor (150) unbudgeted | ⚠ WATCH | No revised budget but $26,716 actual — needs CO or budget transfer
Underground Material (210) over | ⚠ WATCH | Actual $101,624 vs revised $85,650 (+19%) — monitor
Top vendor (Keller Supply Compan) | ✓ OK | 35% of AP — acceptable
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ✓ OK | 25.0% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Keller Supply Company | 93 | 580995.8 | 35.16%
Consolidated Supply Co. | 250 | 372631.96 | 22.55%
Rosen Supply Kirkland | 131 | 172522.87 | 10.44%
California Hydronics Corp | 7 | 147326.5 | 8.916%
Franklin Engineering | 14 | 106959.5 | 6.473%
Pacific Plumbing Supply Co., LLC | 135 | 105473.62 | 6.383%

## Transactions
Transactions Detail
JDR source transactions for job #2098 · 8138 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 05/12/23 | 423 | Gerard, Jeffrey S | 3 | 187.5 | 940188
PR | 100 | 05/26/23 | 974 | Gerard, Jeffrey S | 2 | 125 | 940386
PR | 100 | 06/30/23 | 1080 | Gerard, Jeffrey S | 2 | 125 | 940894
PR | 100 | 08/18/23 | 612 | Gerard, Jeffrey S | 1 | 69 | 941639
PR | 100 | 08/25/23 | 834 | Gerard, Jeffrey S | 1 | 69 | 941748
PR | 100 | 09/01/23 | 115 | Gerard, Jeffrey S | 2 | 138 | 941863
PR | 100 | 09/08/23 | 344 | Gerard, Jeffrey S | 2 | 138 | 941977
PR | 100 | 09/15/23 | 623 | Gerard, Jeffrey S | 3 | 207 | 942094
PR | 100 | 09/22/23 | 918 | Gerard, Jeffrey S | 4.5 | 310.5 | 942206
PR | 100 | 09/29/23 | 1245 | Gerard, Jeffrey S | 1 | 69 | 942325
PR | 100 | 10/06/23 | 142 | Gerard, Jeffrey S | 1 | 69 | 942448
PR | 100 | 10/13/23 | 442 | Gerard, Jeffrey S | 2 | 138 | 942570
PR | 100 | 10/27/23 | 961 | Gerard, Jeffrey S | 4 | 276 | 942811
PR | 100 | 11/03/23 | 123 | Gerard, Jeffrey S | 3 | 207 | 942932
PR | 100 | 11/10/23 | 567 | Gerard, Jeffrey S | 1.5 | 103.5 | 943052
PR | 100 | 11/17/23 | 923 | Gerard, Jeffrey S | 2 | 138 | 943171
PR | 100 | 11/22/23 | 1116 | Johnson, Jake E | 2 | 104 | 43232
PR | 100 | 11/22/23 | 1172 | Gerard, Jeffrey S | 1 | 69 | 943289
PR | 100 | 12/08/23 | 443 | Gerard, Jeffrey S | 3.5 | 241.5 | 101
PR | 100 | 12/15/23 | 794 | Gerard, Jeffrey S | 2.5 | 172.5 | 91237
PR | 100 | 12/22/23 | 1073 | Gerard, Jeffrey S | 3.5 | 241.5 | 91353
PR | 100 | 12/22/23 | 1075 | Johnson, Jake E | 1 | 52 | 91355
PR | 100 | 12/29/23 | 1220 | Gerard, Jeffrey S | 1.5 | 103.5 | 91469
PR | 100 | 01/05/24 | 130 | Gerard, Jeffrey S | 3 | 207 | 91586
PR | 100 | 01/19/24 | 758 | Gerard, Jeffrey S | 4 | 276 | 91809
PR | 100 | 01/26/24 | 1029 | Gerard, Jeffrey S | 1.5 | 103.5 | 91921
PR | 100 | 02/02/24 | 121 | Gerard, Jeffrey S | 3 | 207 | 92033
PR | 100 | 02/09/24 | 343 | Gerard, Jeffrey S | 1.5 | 103.5 | 92147
PR | 100 | 02/09/24 | 343 | Gerard, Jeffrey S | 1.5 | 103.5 | 92147
PR | 100 | 02/16/24 | 599 | Gerard, Jeffrey S | 1 | 69 | 92259
PR | 100 | 02/23/24 | 770 | Gerard, Jeffrey S | 1.5 | 103.5 | 92370
PR | 100 | 03/01/24 | 105 | Gerard, Jeffrey S | 1.5 | 103.5 | 92471
PR | 100 | 03/08/24 | 334 | Gerard, Jeffrey S | 3.5 | 241.5 | 92552
PR | 100 | 03/15/24 | 599 | Gerard, Jeffrey S | 1 | 69 | 92617
PR | 100 | 03/22/24 | 869 | Gerard, Jeffrey S | 3.5 | 241.5 | 92666
PR | 100 | 03/29/24 | 1246 | Gerard, Jeffrey S | 1 | 69 | 92706
PR | 100 | 04/05/24 | 62 | Gerard, Jeffrey S | 1.5 | 103.5 | 92737
PR | 100 | 04/12/24 | 223 | Gerard, Jeffrey S | 1.5 | 103.5 | 92767
PR | 100 | 04/19/24 | 504 | Gerard, Jeffrey S | 2.5 | 172.5 | 92797
PR | 100 | 04/26/24 | 828 | Gerard, Jeffrey S | 3.5 | 241.5 | 92822
PR | 100 | 05/03/24 | 56 | Gerard, Jeffrey S | 2 | 138 | 92843
PR | 100 | 05/10/24 | 294 | Gerard, Jeffrey S | 2 | 138 | 92864
PR | 100 | 05/17/24 | 521 | Gerard, Jeffrey S | 5 | 345 | 92888
PR | 100 | 05/17/24 | 521 | Gerard, Jeffrey S | 1.5 | 103.5 | 92888
PR | 100 | 05/24/24 | 726 | Gerard, Jeffrey S | 2 | 138 | 92910
PR | 100 | 05/31/24 | 840 | Gerard, Jeffrey S | 1.5 | 103.5 | 92930
PR | 100 | 06/07/24 | 129 | Gerard, Jeffrey S | 2.5 | 172.5 | 92951
PR | 100 | 06/14/24 | 352 | Gerard, Jeffrey S | 1.5 | 103.5 | 92971
PR | 100 | 06/21/24 | 524 | Gerard, Jeffrey S | 1.5 | 103.5 | 92987
PR | 100 | 06/28/24 | 731 | Gerard, Jeffrey S | 1 | 69 | 93003
PR | 100 | 07/05/24 | 45 | Gerard, Jeffrey S | 3.5 | 241.5 | 93017
PR | 100 | 07/19/24 | 413 | Gerard, Jeffrey S | 2 | 138 | 93043
PR | 100 | 07/26/24 | 600 | Gerard, Jeffrey S | 1.5 | 103.5 | 93052
PR | 100 | 08/16/24 | 463 | Gerard, Jeffrey S | 2 | 138 | 33083
PR | 100 | 10/04/24 | 43 | Gerard, Jeffrey S | 1.5 | 103.5 | 13172
PR | 100 | 10/11/24 | 250 | Gerard, Jeffrey S | 1 | 69 | 23184
PR | 100 | 10/18/24 | 462 | Gerard, Jeffrey S | 2 | 138 | 33195
PR | 100 | 10/18/24 | 462 | Gerard, Jeffrey S | 1 | 69 | 33195
PR | 100 | 10/25/24 | 609 | Gerard, Jeffrey S | 2 | 138 | 43206
PR | 100 | 11/01/24 | 38 | Gerard, Jeffrey S | 1.5 | 103.5 | 13218
PR | 100 | 11/29/24 | 681 | Gerard, Jeffrey S | 1 | 69 | 53267
PR | 100 | 12/13/24 | 265 | Gerard, Jeffrey S | 1 | 69 | 23300
PR | 100 | 12/27/24 | 570 | Gerard, Jeffrey S | 1 | 69 | 43320
PR | 100 | 01/10/25 | 204 | Gerard, Jeffrey S | 1 | 69 | 23342
PR | 100 | 05/02/25 | 31 | Gerard, Jeffrey S | 1 | 69 | 13516
PR | 100 | 05/16/25 | 373 | Gerard, Jeffrey S | 1 | 69 | 33532
PR | 100 | 06/06/25 | 46 | Gerard, Jeffrey S | 1 | 69 | 13558
PR | 100 | 06/13/25 | 207 | Gerard, Jeffrey S | 1 | 69 | 23566
PR | 100 | 07/03/25 | 32 | Gerard, Jeffrey S | 3 | 207 | 13589
PR | 100 | 07/11/25 | 157 | Gerard, Jeffrey S | 1 | 69 | 23596
PR | 100 | 07/25/25 | 492 | Gerard, Jeffrey S | 1 | 69 | 43610
PR | 100 | 08/22/25 | 385 | Gerard, Jeffrey S | 1 | 69 | 43635
PR | 100 | 09/12/25 | 130 | Gerard, Jeffrey S | 3 | 207 | 23652
PR | 100 | 09/19/25 | 262 | Gerard, Jeffrey S | 2 | 138 | 33658
PR | 100 | 11/21/25 | 352 | Gerard, Jeffrey S | 0.5 | 34.5 | 33721
PR | 100 | 12/05/25 | 62 | Gerard, Jeffrey S | 5 | 345 | 13730
PR | 101 | 04/14/23 | 355 | Gerard, Jeffrey S | 1 | 62.5 | 939789
PR | 101 | 04/28/23 | 783 | Gerard, Jeffrey S | 1 | 62.5 | 939989
PR | 101 | 05/05/23 | 185 | Gerard, Jeffrey S | 3 | 187.5 | 940089
PR | 101 | 05/12/23 | 423 | Gerard, Jeffrey S | 6 | 375 | 940188
PR | 101 | 05/19/23 | 644 | Gerard, Jeffrey S | 4 | 250 | 940286
PR | 101 | 05/26/23 | 974 | Gerard, Jeffrey S | 6 | 375 | 940386
PR | 101 | 06/02/23 | 102 | Gerard, Jeffrey S | 2 | 125 | 940485
PR | 101 | 06/09/23 | 357 | Gerard, Jeffrey S | 2 | 125 | 940586
PR | 101 | 06/23/23 | 835 | Johnson, Jake E | 2 | 100 | 40741
PR | 101 | 06/23/23 | 887 | Gerard, Jeffrey S | 2 | 125 | 940794
PR | 101 | 06/30/23 | 1030 | Johnson, Jake E | 10 | 500 | 40843
PR | 101 | 06/30/23 | 1080 | Gerard, Jeffrey S | 3 | 187.5 | 940894
PR | 101 | 07/07/23 | 63 | Johnson, Jake E | 2 | 100 | 40948
PR | 101 | 07/07/23 | 113 | Gerard, Jeffrey S | 1 | 62.5 | 940999
PR | 101 | 07/14/23 | 379 | Gerard, Jeffrey S | 1 | 69 | 941101
PR | 101 | 07/20/23 | 568 | Johnson, Jake E | 2 | 104 | 41151
PR | 101 | 07/20/23 | 615 | Gerard, Jeffrey S | 1 | 69 | 941199
PR | 101 | 07/28/23 | 707 | Johnson, Jake E | 2 | 104 | 41257
PR | 101 | 08/04/23 | 109 | Gerard, Jeffrey S | 1 | 69 | 941422
PR | 101 | 08/11/23 | 323 | Johnson, Jake E | 2 | 104 | 41478
PR | 101 | 08/11/23 | 375 | Gerard, Jeffrey S | 4 | 276 | 941531
PR | 101 | 08/18/23 | 559 | Johnson, Jake E | 3 | 156 | 41585
PR | 101 | 08/18/23 | 612 | Gerard, Jeffrey S | 3 | 207 | 941639
PR | 101 | 08/25/23 | 780 | Johnson, Jake E | 5 | 260 | 41693
PR | 101 | 08/25/23 | 834 | Gerard, Jeffrey S | 4.5 | 310.5 | 941748
PR | 101 | 09/01/23 | 61 | Johnson, Jake E | 3 | 156 | 41808
PR | 101 | 09/01/23 | 115 | Gerard, Jeffrey S | 6 | 414 | 941863
PR | 101 | 09/08/23 | 344 | Gerard, Jeffrey S | 5 | 345 | 941977
PR | 101 | 09/15/23 | 567 | Johnson, Jake E | 2 | 104 | 42037
PR | 101 | 09/15/23 | 623 | Gerard, Jeffrey S | 7 | 483 | 942094
PR | 101 | 09/22/23 | 865 | Johnson, Jake E | 6 | 312 | 42152
PR | 101 | 09/22/23 | 918 | Gerard, Jeffrey S | 7 | 483 | 942206
PR | 101 | 09/29/23 | 1189 | Johnson, Jake E | 4 | 208 | 42268
PR | 101 | 09/29/23 | 1245 | Gerard, Jeffrey S | 3 | 207 | 942325
PR | 101 | 10/06/23 | 86 | Johnson, Jake E | 5 | 260 | 42391
PR | 101 | 10/06/23 | 142 | Gerard, Jeffrey S | 3 | 207 | 942448
PR | 101 | 10/13/23 | 386 | Johnson, Jake E | 5 | 260 | 42514
PR | 101 | 10/13/23 | 442 | Gerard, Jeffrey S | 6 | 414 | 942570
PR | 101 | 10/20/23 | 654 | Johnson, Jake E | 8 | 416 | 42634
PR | 101 | 10/20/23 | 711 | Gerard, Jeffrey S | 3 | 207 | 942691
PR | 101 | 10/27/23 | 905 | Johnson, Jake E | 5 | 260 | 42754
PR | 101 | 10/27/23 | 961 | Gerard, Jeffrey S | 6 | 414 | 942811
PR | 101 | 11/03/23 | 68 | Johnson, Jake E | 7 | 364 | 42876
PR | 101 | 11/03/23 | 123 | Gerard, Jeffrey S | 1 | 69 | 942932
PR | 101 | 11/10/23 | 511 | Johnson, Jake E | 4 | 208 | 42995
PR | 101 | 11/10/23 | 567 | Gerard, Jeffrey S | 2 | 138 | 943052
PR | 101 | 11/10/23 | 567 | Gerard, Jeffrey S | 1 | 69 | 943052
PR | 101 | 11/17/23 | 867 | Johnson, Jake E | 4 | 208 | 43114
PR | 101 | 11/17/23 | 923 | Gerard, Jeffrey S | 8 | 552 | 943171
PR | 101 | 11/22/23 | 1116 | Johnson, Jake E | 1 | 52 | 43232
PR | 101 | 12/01/23 | 66 | Johnson, Jake E | 1 | 52 | 43349
PR | 101 | 12/01/23 | 123 | Gerard, Jeffrey S | 2 | 138 | 943407
PR | 101 | 12/08/23 | 385 | Johnson, Jake E | 5 | 260 | 43471
PR | 101 | 12/08/23 | 443 | Gerard, Jeffrey S | 3 | 207 | 101
PR | 101 | 12/15/23 | 738 | Johnson, Jake E | 1 | 52 | 1180
PR | 101 | 12/15/23 | 794 | Gerard, Jeffrey S | 6 | 414 | 91237
PR | 101 | 12/22/23 | 1073 | Gerard, Jeffrey S | 5 | 345 | 91353
PR | 101 | 12/22/23 | 1075 | Johnson, Jake E | 2 | 104 | 91355
PR | 101 | 12/29/23 | 1220 | Gerard, Jeffrey S | 3 | 207 | 91469
PR | 101 | 12/29/23 | 1222 | Johnson, Jake E | 1 | 52 | 91471
PR | 101 | 01/05/24 | 130 | Gerard, Jeffrey S | 5 | 345 | 91586
PR | 101 | 01/05/24 | 132 | Johnson, Jake E | 2 | 104 | 91588
PR | 101 | 01/12/24 | 465 | Gerard, Jeffrey S | 2 | 138 | 91698
PR | 101 | 01/12/24 | 465 | Gerard, Jeffrey S | 1.5 | 103.5 | 91698
PR | 101 | 01/12/24 | 467 | Johnson, Jake E | 3 | 156 | 91700
PR | 101 | 01/19/24 | 758 | Gerard, Jeffrey S | 4 | 276 | 91809
PR | 101 | 01/19/24 | 760 | Johnson, Jake E | 4 | 208 | 91811
PR | 101 | 01/26/24 | 1029 | Gerard, Jeffrey S | 4 | 276 | 91921
PR | 101 | 01/26/24 | 1031 | Johnson, Jake E | 2 | 104 | 91923
PR | 101 | 02/02/24 | 16 | Barnhart, Joseph N | 2.5 | 170 | 1928
PR | 101 | 02/02/24 | 121 | Gerard, Jeffrey S | 3 | 207 | 92033
PR | 101 | 02/02/24 | 123 | Johnson, Jake E | 3 | 156 | 92035
PR | 101 | 02/09/24 | 343 | Gerard, Jeffrey S | 1 | 69 | 92147
PR | 101 | 02/09/24 | 345 | Johnson, Jake E | 3 | 156 | 92149
PR | 101 | 02/16/24 | 599 | Gerard, Jeffrey S | 2 | 138 | 92259
PR | 101 | 02/16/24 | 601 | Johnson, Jake E | 2 | 104 | 92261
PR | 101 | 02/23/24 | 770 | Gerard, Jeffrey S | 2 | 138 | 92370
PR | 101 | 02/23/24 | 773 | Johnson, Jake E | 4 | 208 | 92373
PR | 101 | 03/01/24 | 110 | Johnson, Jake E | 1 | 52 | 92476
PR | 101 | 03/08/24 | 334 | Gerard, Jeffrey S | 2 | 138 | 92552
PR | 101 | 03/08/24 | 343 | Johnson, Jake E | 3 | 156 | 92561
PR | 101 | 03/15/24 | 608 | Johnson, Jake E | 3 | 156 | 92626
PR | 101 | 03/22/24 | 869 | Gerard, Jeffrey S | 1 | 69 | 92666
PR | 101 | 03/22/24 | 878 | Johnson, Jake E | 3 | 156 | 92675
PR | 101 | 03/29/24 | 1246 | Gerard, Jeffrey S | 2 | 138 | 92706
PR | 101 | 03/29/24 | 1256 | Johnson, Jake E | 6 | 312 | 92716
PR | 101 | 04/05/24 | 62 | Gerard, Jeffrey S | 1 | 69 | 92737
PR | 101 | 04/05/24 | 74 | Johnson, Jake E | 7 | 364 | 92749
PR | 101 | 04/12/24 | 223 | Gerard, Jeffrey S | 2 | 138 | 92767
PR | 101 | 04/12/24 | 236 | Johnson, Jake E | 2 | 104 | 92780
PR | 101 | 04/19/24 | 504 | Gerard, Jeffrey S | 2 | 138 | 92797
PR | 101 | 04/19/24 | 517 | Johnson, Jake E | 3 | 156 | 92810
PR | 101 | 04/26/24 | 828 | Gerard, Jeffrey S | 2 | 138 | 92822
PR | 101 | 04/26/24 | 841 | Johnson, Jake E | 5 | 260 | 92835
PR | 101 | 05/03/24 | 56 | Gerard, Jeffrey S | 3 | 207 | 92843
PR | 101 | 05/03/24 | 68 | Johnson, Jake E | 3 | 156 | 92855
PR | 101 | 05/10/24 | 294 | Gerard, Jeffrey S | 1 | 69 | 92864
PR | 101 | 05/10/24 | 306 | Johnson, Jake E | 4 | 208 | 92876
PR | 101 | 05/17/24 | 521 | Gerard, Jeffrey S | 1 | 69 | 92888
PR | 101 | 05/24/24 | 726 | Gerard, Jeffrey S | 2 | 138 | 92910
PR | 101 | 05/24/24 | 738 | Johnson, Jake E | 4 | 208 | 92922
PR | 101 | 05/31/24 | 840 | Gerard, Jeffrey S | 3 | 207 | 92930
PR | 101 | 05/31/24 | 850 | Johnson, Jake E | 5 | 260 | 92940
PR | 101 | 06/07/24 | 129 | Gerard, Jeffrey S | 3 | 207 | 92951
PR | 101 | 06/07/24 | 139 | Johnson, Jake E | 5 | 260 | 92961
PR | 101 | 06/14/24 | 352 | Gerard, Jeffrey S | 1.5 | 103.5 | 92971
PR | 101 | 06/14/24 | 362 | Johnson, Jake E | 4 | 208 | 92981
PR | 101 | 06/21/24 | 524 | Gerard, Jeffrey S | 2 | 138 | 92987
PR | 101 | 06/21/24 | 533 | Johnson, Jake E | 2 | 104 | 92996
PR | 101 | 06/28/24 | 740 | Johnson, Jake E | 4 | 208 | 93012
PR | 101 | 07/05/24 | 53 | Johnson, Jake E | 3 | 156 | 93025
PR | 101 | 07/12/24 | 216 | Johnson, Jake E | 1 | 52 | 93040
PR | 101 | 07/19/24 | 422 | Johnson, Jake E | 2 | 104 | 93052
PR | 101 | 07/26/24 | 609 | Johnson, Jake E | 2 | 104 | 93061
PR | 101 | 08/02/24 | 49 | Johnson, Jake E | 1 | 52 | 93072
PR | 101 | 08/09/24 | 274 | Gerard, Jeffrey S | 1 | 69 | 23074
PR | 101 | 08/09/24 | 283 | Johnson, Jake E | 5 | 260 | 23083
PR | 101 | 08/16/24 | 463 | Gerard, Jeffrey S | 1 | 69 | 33083
PR | 101 | 08/16/24 | 472 | Johnson, Jake E | 4 | 208 | 33092
PR | 101 | 08/23/24 | 734 | Johnson, Jake E | 6 | 312 | 43103
PR | 101 | 08/30/24 | 876 | Johnson, Jake E | 3 | 156 | 53121
PR | 101 | 09/06/24 | 53 | Johnson, Jake E | 4 | 208 | 13133
PR | 101 | 09/13/24 | 261 | Johnson, Jake E | 1 | 52 | 23144
PR | 101 | 09/20/24 | 432 | Johnson, Jake E | 1 | 52 | 33156
PR | 101 | 09/27/24 | 568 | Johnson, Jake E | 1 | 52 | 43167
PR | 101 | 10/04/24 | 52 | Johnson, Jake E | 2 | 104 | 13181
PR | 101 | 10/11/24 | 259 | Johnson, Jake E | 2 | 104 | 23193
PR | 101 | 10/18/24 | 462 | Gerard, Jeffrey S | 1 | 69 | 33195
PR | 101 | 10/18/24 | 471 | Johnson, Jake E | 1 | 52 | 33204
PR | 101 | 10/25/24 | 609 | Gerard, Jeffrey S | 1 | 69 | 43206
PR | 101 | 10/25/24 | 618 | Johnson, Jake E | 1 | 52 | 43215
PR | 101 | 11/01/24 | 38 | Gerard, Jeffrey S | 2 | 138 | 13218
PR | 101 | 11/01/24 | 47 | Johnson, Jake E | 2 | 104 | 13227
PR | 101 | 11/08/24 | 158 | Gerard, Jeffrey S | 1 | 69 | 23230
PR | 101 | 11/08/24 | 167 | Johnson, Jake E | 4 | 208 | 23239
PR | 101 | 11/15/24 | 378 | Gerard, Jeffrey S | 3 | 207 | 33242
PR | 101 | 11/15/24 | 387 | Johnson, Jake E | 3 | 156 | 33251
PR | 101 | 11/29/24 | 648 | Johnson, Jake E | 1 | 52 | 43295
PR | 101 | 11/29/24 | 681 | Gerard, Jeffrey S | 1 | 69 | 53267
PR | 101 | 11/29/24 | 690 | Johnson, Jake E | 2 | 104 | 53276
PR | 101 | 12/06/24 | 92 | Johnson, Jake E | 1 | 52 | 13288
PR | 101 | 12/13/24 | 274 | Johnson, Jake E | 1 | 52 | 23309
PR | 101 | 12/20/24 | 460 | Johnson, Jake E | 3 | 156 | 33318
PR | 101 | 12/27/24 | 579 | Johnson, Jake E | 1 | 52 | 43329
PR | 101 | 01/03/25 | 49 | Johnson, Jake E | 1 | 52 | 13338
PR | 101 | 01/10/25 | 212 | Johnson, Jake E | 1 | 52 | 23350
PR | 101 | 01/17/25 | 375 | Johnson, Jake E | 1 | 52 | 33361
PR | 101 | 01/24/25 | 611 | Johnson, Jake E | 1 | 52 | 43400
PR | 101 | 01/31/25 | 734 | Johnson, Jake E | 1 | 52 | 53382
PR | 101 | 02/07/25 | 64 | Johnson, Jake E | 4 | 208 | 13391
PR | 101 | 02/14/25 | 230 | Johnson, Jake E | 3 | 156 | 23400
PR | 101 | 02/21/25 | 348 | Johnson, Jake E | 4 | 208 | 33410
PR | 101 | 02/28/25 | 538 | Johnson, Jake E | 3 | 156 | 43421
PR | 101 | 03/07/25 | 51 | Johnson, Jake E | 2 | 104 | 13431
PR | 101 | 03/14/25 | 251 | Johnson, Jake E | 1 | 52 | 23442
PR | 101 | 03/28/25 | 600 | Johnson, Jake E | 4 | 208 | 93474
PR | 101 | 04/04/25 | 43 | Johnson, Jake E | 3 | 156 | 13485
PR | 101 | 04/18/25 | 447 | Johnson, Jake E | 3 | 156 | 33505
PR | 101 | 04/25/25 | 586 | Johnson, Jake E | 1 | 52 | 43515
PR | 101 | 05/02/25 | 31 | Gerard, Jeffrey S | 1 | 69 | 13516
PR | 101 | 05/02/25 | 32 | Gerard, Jordan E | 1 | 60 | 13517
PR | 101 | 06/13/25 | 208 | Gerard, Jordan E | 2 | 120 | 23567
PR | 101 | 06/27/25 | 489 | Gerard, Jeffrey S | 1 | 69 | 43582
PR | 101 | 06/27/25 | 490 | Gerard, Jordan E | 1 | 60 | 43583
PR | 101 | 07/03/25 | 32 | Gerard, Jeffrey S | 2 | 138 | 13589
PR | 101 | 07/11/25 | 157 | Gerard, Jeffrey S | 1 | 69 | 23596
PR | 101 | 07/18/25 | 324 | Gerard, Jeffrey S | 1 | 69 | 33603
PR | 101 | 07/18/25 | 325 | Gerard, Jordan E | 1 | 60 | 33604
PR | 101 | 07/25/25 | 492 | Gerard, Jeffrey S | 1 | 69 | 43610
PR | 101 | 07/25/25 | 493 | Gerard, Jordan E | 2 | 120 | 43611
PR | 101 | 08/22/25 | 386 | Gerard, Jordan E | 2 | 120 | 43636
PR | 101 | 09/05/25 | 33 | Gerard, Jeffrey S | 3 | 207 | 13647
PR | 101 | 09/12/25 | 131 | Gerard, Jordan E | 1 | 60 | 23653
PR | 101 | 09/12/25 | 131 | Gerard, Jordan E | 1 | 60 | 23653
PR | 110 | 09/15/23 | 508 | Anderson, Richard P | 5 | 325 | 41979
PR | 110 | 09/15/23 | 514 | Barnhart, Joseph N | 2 | 136 | 41985
PR | 110 | 09/15/23 | 587 | Paco Leyva, Orlando | 4 | 244 | 42057
PR | 110 | 09/22/23 | 807 | Anderson, Richard P | 29.5 | 1917.5 | 42094
PR | 110 | 09/22/23 | 811 | Balderas Ortiz, Ricardo I | 24 | 1056 | 42098
PR | 110 | 09/22/23 | 813 | Barnhart, Joseph N | 4 | 272 | 42101
PR | 110 | 09/22/23 | 847 | Galdamez, Dagoberto A | 24 | 1008 | 42134
PR | 110 | 09/22/23 | 864 | Jimenez Alvarenga, Gerson M | 24 | 936 | 42151
PR | 110 | 09/22/23 | 884 | Paco Leyva, Orlando | 24 | 1464 | 42171
PR | 110 | 09/22/23 | 896 | Rodriguez, Eduardo D | 24 | 624 | 42183
PR | 110 | 09/29/23 | 1128 | Anderson, Richard P | 27.5 | 1787.5 | 42208
PR | 110 | 09/29/23 | 1132 | Balderas Ortiz, Ricardo I | 40 | 1760 | 42212
PR | 110 | 09/29/23 | 1170 | Galdamez, Dagoberto A | 40 | 1680 | 42249
PR | 110 | 09/29/23 | 1188 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 42267
PR | 110 | 09/29/23 | 1210 | Paco Leyva, Orlando | 40 | 2440 | 42289
PR | 110 | 09/29/23 | 1221 | Rodriguez, Eduardo D | 16 | 416 | 42300
PR | 110 | 10/06/23 | 23 | Anderson, Richard P | 11 | 715 | 42328
PR | 110 | 10/06/23 | 27 | Balderas Ortiz, Ricardo I | 16 | 704 | 42332
PR | 110 | 10/06/23 | 65 | Galdamez, Dagoberto A | 16 | 672 | 42370
PR | 110 | 10/06/23 | 85 | Jimenez Alvarenga, Gerson M | 26 | 1014 | 42390
PR | 110 | 10/06/23 | 107 | Paco Leyva, Orlando | 36 | 2196 | 42412
PR | 110 | 10/13/23 | 322 | Anderson, Richard P | 23.5 | 1527.5 | 42450
PR | 110 | 10/13/23 | 364 | Fox, Tamron P | 8 | 216 | 42492
PR | 110 | 10/13/23 | 365 | Galdamez, Dagoberto A | 40 | 1680 | 42493
PR | 110 | 10/13/23 | 385 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 42513
PR | 110 | 10/13/23 | 404 | Nunez Bravo, Jose L | 8 | 184 | 42532
PR | 110 | 10/13/23 | 407 | Paco Leyva, Orlando | 32 | 1952 | 42535
PR | 110 | 10/13/23 | 415 | Reed, Reuben H | 8 | 496 | 42543
PR | 110 | 10/20/23 | 591 | Anderson, Richard P | 15 | 975 | 42571
PR | 110 | 10/20/23 | 595 | Balderas Ortiz, Ricardo I | 8 | 352 | 42575
PR | 110 | 10/20/23 | 597 | Barnhart, Joseph N | 1 | 68 | 42578
PR | 110 | 10/20/23 | 633 | Galdamez, Dagoberto A | 32 | 1344 | 42613
PR | 110 | 10/20/23 | 653 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 42633
PR | 110 | 10/20/23 | 671 | Nunez Bravo, Jose L | 8 | 184 | 42651
PR | 110 | 10/20/23 | 675 | Paco Leyva, Orlando | 35 | 2135 | 42655
PR | 110 | 10/27/23 | 842 | Anderson, Richard P | 15 | 975 | 42692
PR | 110 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I | 11.5 | 506 | 42696
PR | 110 | 10/27/23 | 884 | Galdamez, Dagoberto A | 33.5 | 1407 | 42733
PR | 110 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M | 2 | 78 | 42753
PR | 110 | 10/27/23 | 926 | Paco Leyva, Orlando | 2 | 122 | 42775
PR | 110 | 11/03/23 | 5 | Anderson, Richard P | 19 | 1235 | 42813
PR | 110 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I | 23 | 1012 | 42817
PR | 110 | 11/03/23 | 11 | Barnhart, Joseph N | 1 | 68 | 42819
PR | 110 | 11/03/23 | 47 | Galdamez, Dagoberto A | 12 | 504 | 42855
PR | 110 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M | 23 | 897 | 42875
PR | 110 | 11/03/23 | 85 | Nunez Bravo, Jose L | 18 | 414 | 42893
PR | 110 | 11/10/23 | 448 | Anderson, Richard P | 34.5 | 2242.5 | 42933
PR | 110 | 11/10/23 | 452 | Balderas Ortiz, Ricardo I | 40 | 1760 | 42937
PR | 110 | 11/10/23 | 490 | Galdamez, Dagoberto A | 40 | 1680 | 42974
PR | 110 | 11/10/23 | 510 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 42994
PR | 110 | 11/10/23 | 528 | Nunez Bravo, Jose L | 40 | 920 | 43012
PR | 110 | 11/10/23 | 532 | Paco Leyva, Orlando | 8 | 488 | 43016
PR | 110 | 11/17/23 | 807 | Anderson, Richard P | 33 | 2145 | 43055
PR | 110 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I | 2 | 132 | 43059
PR | 110 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43059
PR | 110 | 11/17/23 | 847 | Galdamez, Dagoberto A | 2 | 126 | 43094
PR | 110 | 11/17/23 | 847 | Galdamez, Dagoberto A | 40 | 1680 | 43094
PR | 110 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M | 2 | 117 | 43113
PR | 110 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 43113
PR | 110 | 11/17/23 | 884 | Nunez Bravo, Jose L | 31 | 713 | 43131
PR | 110 | 11/17/23 | 888 | Paco Leyva, Orlando | 38 | 2318 | 43135
PR | 110 | 11/22/23 | 1056 | Anderson, Richard P | 4 | 260 | 43173
PR | 110 | 11/22/23 | 1060 | Balderas Ortiz, Ricardo I | 32 | 1408 | 43177
PR | 110 | 11/22/23 | 1095 | Galdamez, Dagoberto A | 24 | 1008 | 43211
PR | 110 | 11/22/23 | 1115 | Jimenez Alvarenga, Gerson M | 8 | 312 | 43231
PR | 110 | 11/22/23 | 1133 | Nunez Bravo, Jose L | 8 | 184 | 43249
PR | 110 | 11/22/23 | 1137 | Paco Leyva, Orlando | 28 | 1708 | 43253
PR | 110 | 12/01/23 | 45 | Galdamez, Dagoberto A | 6 | 252 | 43328
PR | 110 | 12/01/23 | 87 | Paco Leyva, Orlando | 23 | 1403 | 43370
PR | 110 | 12/08/23 | 406 | Paco Leyva, Orlando | 8 | 488 | 43492
AP | 110 | 02/27/24 | 856 | Capital One Credit Card |  | 11.76 | 011024
PR | 110 | 03/15/24 | 552 | Rodriguez Arevalos, Christian | 13 | 572 | 2581
PR | 111 | 12/01/23 | 87 | Paco Leyva, Orlando | 4 | 244 | 43370
PR | 111 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I | 16 | 704 | 1591
PR | 111 | 01/12/24 | 393 | Galdamez, Dagoberto A | 16 | 672 | 1625
PR | 111 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M | 16 | 624 | 1643
PR | 111 | 01/12/24 | 428 | Nunez Bravo, Jose L | 8 | 184 | 1660
PR | 111 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I | 37 | 1628 | 1703
PR | 111 | 01/19/24 | 687 | Galdamez, Dagoberto A | 40 | 1680 | 1737
PR | 111 | 01/19/24 | 693 | Gochez Molina, Douglas O | 8 | 200 | 1743
PR | 111 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M | 24 | 936 | 1755
PR | 111 | 01/19/24 | 721 | Nunez Bravo, Jose L | 8 | 184 | 1771
PR | 111 | 01/19/24 | 725 | Paco Leyva, Orlando | 18 | 1098 | 1775
PR | 111 | 01/26/24 | 918 | Anderson, Richard P | 3 | 195 | 1810
PR | 111 | 01/26/24 | 930 | Carmona, Raul O | 40 | 2120 | 1822
PR | 111 | 01/26/24 | 957 | Galdamez, Dagoberto A | 8 | 336 | 1848
PR | 111 | 01/26/24 | 963 | Gochez Molina, Douglas O | 32 | 800 | 1854
PR | 111 | 01/26/24 | 985 | McCurry, Maxwell J | 8 | 192 | 1876
PR | 111 | 01/26/24 | 991 | Nunez Bravo, Jose L | 16 | 368 | 1882
PR | 111 | 01/26/24 | 995 | Paco Leyva, Orlando | 17 | 1037 | 1886
PR | 111 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I | 24 | 1056 | 1927
PR | 111 | 02/02/24 | 23 | Carmona, Raul O | 12 | 636 | 1935
PR | 111 | 02/02/24 | 50 | Galdamez, Dagoberto A | 12 | 504 | 1961
PR | 111 | 02/02/24 | 56 | Gochez Molina, Douglas O | 24 | 600 | 1967
PR | 111 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M | 16 | 624 | 1979
PR | 111 | 02/02/24 | 78 | McCurry, Maxwell J | 12 | 288 | 1989
PR | 111 | 02/02/24 | 84 | Nunez Bravo, Jose L | 12 | 276 | 1995
PR | 111 | 02/02/24 | 88 | Paco Leyva, Orlando | 9 | 549 | 1999
PR | 111 | 02/02/24 | 105 | Storozhuk, Maxim A | 4 | 88 | 2016
PR | 111 | 02/09/24 | 239 | Belcher, Jacob T | 32 | 896 | 2043
PR | 111 | 02/09/24 | 243 | Carmona, Raul O | 24 | 1272 | 2047
PR | 111 | 02/09/24 | 270 | Galdamez, Dagoberto A | 20 | 840 | 2073
PR | 111 | 02/09/24 | 276 | Gochez Molina, Douglas O | 32 | 800 | 2079
PR | 111 | 02/09/24 | 298 | McCurry, Maxwell J | 24 | 576 | 2101
PR | 111 | 02/09/24 | 304 | Nunez Bravo, Jose L | 16 | 368 | 2107
PR | 111 | 02/09/24 | 308 | Paco Leyva, Orlando | 15 | 915 | 2111
PR | 111 | 02/16/24 | 523 | Escalante Escobar, Boanerge | 8 | 280 | 2182
PR | 111 | 02/16/24 | 543 | Hubbard, Justin A | 24 | 1104 | 2202
PR | 111 | 02/16/24 | 561 | Nunez Bravo, Jose L | 25 | 575 | 2220
PR | 111 | 02/16/24 | 565 | Paco Leyva, Orlando | 7.5 | 457.5 | 2224
PR | 111 | 02/23/24 | 711 | Hubbard, Justin A | 31 | 1426 | 2311
PR | 111 | 02/23/24 | 722 | McCabe, Thomas C | 23 | 1012 | 2322
PR | 111 | 02/23/24 | 723 | McCurry, Maxwell J | 22.5 | 540 | 2323
PR | 111 | 02/23/24 | 733 | Paco Leyva, Orlando | 13 | 793 | 2333
PR | 111 | 03/01/24 | 12 | Belcher, Jacob T | 24 | 672 | 2378
PR | 111 | 03/01/24 | 51 | Hubbard, Justin A | 40 | 1840 | 2416
PR | 111 | 03/01/24 | 60 | McCabe, Thomas C | 24 | 1056 | 2425
PR | 111 | 03/01/24 | 61 | McCurry, Maxwell J | 24 | 576 | 2426
PR | 111 | 03/01/24 | 71 | Paco Leyva, Orlando | 10 | 610 | 2436
PR | 111 | 03/08/24 | 254 | Belcher, Jacob T | 8 | 224 | 2473
PR | 111 | 03/08/24 | 278 | Hubbard, Justin A | 8 | 368 | 2497
PR | 111 | 03/08/24 | 292 | Paco Leyva, Orlando | 5 | 305 | 2511
PR | 111 | 03/15/24 | 533 | Hubbard, Justin A | 8 | 368 | 2562
PR | 111 | 03/15/24 | 538 | McCurry, Maxwell J | 8 | 192 | 2567
PR | 111 | 03/15/24 | 545 | Paco Leyva, Orlando | 2 | 122 | 2574
PR | 111 | 03/22/24 | 821 | Hubbard, Justin A | 16 | 736 | 2619
PR | 111 | 03/22/24 | 824 | McCurry, Maxwell J | 24 | 576 | 2622
PR | 111 | 03/22/24 | 829 | Paco Leyva, Orlando | 5 | 305 | 2627
PR | 111 | 03/29/24 | 1205 | Paco Leyva, Orlando | 5 | 305 | 2666
PR | 111 | 04/05/24 | 19 | Hubbard, Justin A | 23.5 | 1081 | 2695
PR | 111 | 04/05/24 | 24 | Paco Leyva, Orlando | 4 | 244 | 2700
PR | 111 | 04/05/24 | 82 | McCurry, Maxwell J | 23 | 552 | 92757
PR | 111 | 04/12/24 | 183 | Paco Leyva, Orlando | 5 | 305 | 2728
PR | 111 | 04/12/24 | 234 | Hubbard, Justin A | 24 | 1104 | 92778
PR | 111 | 04/12/24 | 244 | McCurry, Maxwell J | 8 | 192 | 92788
PR | 111 | 04/19/24 | 461 | Paco Leyva, Orlando | 8 | 488 | 2755
PR | 111 | 04/19/24 | 515 | Hubbard, Justin A | 11 | 506 | 92808
PR | 111 | 04/19/24 | 525 | McCurry, Maxwell J | 32 | 768 | 92818
PR | 111 | 04/26/24 | 786 | Paco Leyva, Orlando | 5 | 305 | 2781
PR | 111 | 04/26/24 | 807 | Castro Hernandez, Jose A | 8 | 432 | 92802
PR | 111 | 04/26/24 | 839 | Hubbard, Justin A | 8 | 368 | 92833
PR | 111 | 04/26/24 | 868 | Suniga Aviles, Kelvin A | 16 | 336 | 92862
PR | 111 | 05/03/24 | 18 | Paco Leyva, Orlando | 2 | 122 | 2806
PR | 111 | 05/03/24 | 29 | Ascencio, Jose L | 16 | 672 | 92817
PR | 111 | 05/03/24 | 36 | Castro Hernandez, Jose A | 8 | 432 | 92824
PR | 111 | 05/10/24 | 274 | Castro Hernandez, Jose A | 8 | 432 | 92845
PR | 111 | 05/17/24 | 494 | Ascencio, Jose L | 16 | 672 | 92862
PR | 111 | 05/24/24 | 692 | Paco Leyva, Orlando | 2 | 122 | 2877
PR | 111 | 05/24/24 | 701 | Ascencio, Jose L | 8 | 336 | 92886
PR | 111 | 05/24/24 | 739 | Lima Romero, Melvin A | 4 | 176 | 92923
PR | 111 | 06/14/24 | 363 | Lima Romero, Melvin A | 8 | 352 | 92982
PR | 111 | 06/21/24 | 491 | Paco Leyva, Orlando | 8 | 488 | 2955
PR | 111 | 06/21/24 | 534 | Lima Romero, Melvin A | 8 | 352 | 92997
PR | 111 | 06/28/24 | 698 | Paco Leyva, Orlando | 2 | 122 | 2971
PR | 111 | 07/05/24 | 14 | Paco Leyva, Orlando | 11 | 671 | 2986
PR | 111 | 07/12/24 | 176 | Paco Leyva, Orlando | 5 | 305 | 3000
PR | 111 | 07/12/24 | 203 | Escalante Escobar, Boanerge | 24 | 840 | 93027
PR | 111 | 07/19/24 | 383 | Paco Leyva, Orlando | 15 | 915 | 3013
PR | 111 | 07/19/24 | 423 | Lima Romero, Melvin A | 16 | 704 | 93053
PR | 111 | 07/19/24 | 424 | Lopez, Maslin A | 16 | 528 | 93054
PR | 111 | 07/26/24 | 571 | Paco Leyva, Orlando | 7 | 427 | 3023
PR | 111 | 07/26/24 | 583 | Carmona, Raul O | 8 | 424 | 93035
PR | 111 | 07/26/24 | 598 | Escobar Ramirez, Carlos M | 16 | 320 | 93050
PR | 111 | 07/26/24 | 610 | Lima Romero, Melvin A | 8 | 352 | 93062
PR | 111 | 08/02/24 | 11 | Paco Leyva, Orlando | 6 | 366 | 3034
PR | 111 | 08/09/24 | 246 | Paco Leyva, Orlando | 12 | 732 | 3046
PR | 111 | 08/09/24 | 258 | Carmona, Raul O | 8 | 424 | 23058
PR | 111 | 08/09/24 | 272 | Escobar Ramirez, Carlos M | 8 | 160 | 23072
PR | 111 | 08/09/24 | 277 | Gochez Molina, Douglas O | 8 | 200 | 23077
PR | 111 | 08/09/24 | 284 | Lima Romero, Melvin A | 8 | 352 | 23084
PR | 111 | 08/09/24 | 291 | Mendoza Morales, Jesus A | 8 | 328 | 23091
PR | 111 | 08/09/24 | 304 | Suniga Aviles, Kelvin A | 8 | 168 | 23104
PR | 111 | 08/16/24 | 435 | Galdamez, Dagoberto A | 8 | 336 | 3055
PR | 111 | 08/16/24 | 437 | Paco Leyva, Orlando | 9 | 549 | 3057
PR | 111 | 08/16/24 | 449 | Carmona, Raul O | 8 | 424 | 33069
PR | 111 | 08/16/24 | 461 | Escobar Ramirez, Carlos M | 16 | 320 | 33081
PR | 111 | 08/16/24 | 474 | Lopez, Maslin A | 8 | 264 | 33094
PR | 111 | 08/23/24 | 699 | Paco Leyva, Orlando | 12 | 732 | 3068
PR | 111 | 08/23/24 | 711 | Carmona, Raul O | 8 | 424 | 43080
PR | 111 | 08/23/24 | 723 | Escobar Ramirez, Carlos M | 8 | 160 | 43092
PR | 111 | 08/23/24 | 736 | Lopez, Maslin A | 16 | 528 | 43105
PR | 111 | 08/23/24 | 742 | Mendoza Morales, Jesus A | 16 | 656 | 43111
PR | 111 | 08/23/24 | 761 | Weeks, Gregg A | 8 | 384 | 43130
PR | 111 | 08/23/24 | 765 | Zuniga Avilez, Eduar A | 8 | 160 | 43134
PR | 111 | 08/30/24 | 842 | Paco Leyva, Orlando | 9 | 549 | 3087
PR | 111 | 08/30/24 | 854 | Carmona, Raul O | 24 | 1272 | 53099
PR | 111 | 08/30/24 | 865 | Escobar Ramirez, Carlos M | 24 | 480 | 53110
PR | 111 | 09/06/24 | 18 | Paco Leyva, Orlando | 4 | 244 | 3098
PR | 111 | 09/06/24 | 30 | Carmona, Raul O | 8 | 424 | 13110
PR | 111 | 09/06/24 | 41 | Escobar Ramirez, Carlos M | 16 | 320 | 13121
PR | 111 | 09/06/24 | 61 | Mendoza Morales, Jesus A | 8 | 328 | 13141
PR | 111 | 09/13/24 | 226 | Paco Leyva, Orlando | 4 | 244 | 3109
PR | 111 | 09/13/24 | 249 | Escobar Ramirez, Carlos M | 8 | 160 | 23132
PR | 111 | 09/13/24 | 281 | Suniga Aviles, Kelvin A | 10 | 210 | 23164
PR | 111 | 09/13/24 | 291 | Zuniga Avilez, Eduar A | 4 | 80 | 23174
PR | 111 | 09/20/24 | 398 | Paco Leyva, Orlando | 8 | 488 | 3122
PR | 111 | 09/20/24 | 410 | Carmona, Raul O | 16 | 848 | 33134
PR | 111 | 09/20/24 | 421 | Escobar Ramirez, Carlos M | 24 | 480 | 33145
PR | 111 | 09/20/24 | 434 | Lopez, Maslin A | 8 | 264 | 33158
PR | 111 | 09/20/24 | 452 | Suniga Aviles, Kelvin A | 12 | 252 | 33176
PR | 111 | 09/20/24 | 458 | Weeks, Gregg A | 8 | 384 | 33182
PR | 111 | 09/20/24 | 462 | Zuniga Avilez, Eduar A | 8 | 160 | 33186
PR | 111 | 09/27/24 | 525 | Anderson, Richard P | 1 | 65 | 3124
PR | 111 | 09/27/24 | 535 | Paco Leyva, Orlando | 12 | 732 | 3134
PR | 111 | 09/27/24 | 546 | Carmona, Raul O | 16 | 848 | 43145
PR | 111 | 09/27/24 | 570 | Lopez, Maslin A | 8 | 264 | 43169
PR | 111 | 09/27/24 | 588 | Suniga Aviles, Kelvin A | 12 | 252 | 43187
PR | 111 | 10/04/24 | 19 | Paco Leyva, Orlando | 9 | 549 | 3148
PR | 111 | 10/04/24 | 30 | Carmona, Raul O | 8 | 424 | 13159
PR | 111 | 10/04/24 | 54 | Lopez, Maslin A | 8 | 264 | 13183
PR | 111 | 10/04/24 | 59 | Mendoza Morales, Jesus A | 16 | 656 | 13188
PR | 111 | 10/04/24 | 82 | Zuniga Avilez, Eduar A | 8 | 160 | 13211
PR | 111 | 10/11/24 | 226 | Paco Leyva, Orlando | 2 | 122 | 3160
PR | 111 | 10/11/24 | 237 | Carmona, Raul O | 24 | 1272 | 23171
PR | 111 | 10/18/24 | 439 | Paco Leyva, Orlando | 20 | 1220 | 3172
PR | 111 | 10/18/24 | 450 | Carmona, Raul O | 28 | 1484 | 33183
PR | 111 | 10/18/24 | 477 | Mendoza Morales, Jesus A | 8 | 328 | 33210
PR | 111 | 10/25/24 | 584 | Galdamez, Dagoberto A | 3 | 126 | 3181
PR | 111 | 10/25/24 | 587 | Paco Leyva, Orlando | 9 | 549 | 3184
PR | 111 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I | 8 | 352 | 43190
PR | 111 | 10/25/24 | 597 | Carmona, Raul O | 20 | 1060 | 43194
PR | 111 | 10/25/24 | 619 | Lopez, Maslin A | 8 | 264 | 43216
PR | 111 | 11/01/24 | 13 | Galdamez, Dagoberto A | 16 | 672 | 3193
PR | 111 | 11/01/24 | 26 | Carmona, Raul O | 16 | 848 | 13206
PR | 111 | 11/01/24 | 48 | Lopez, Maslin A | 8 | 264 | 13228
PR | 111 | 11/08/24 | 133 | Galdamez, Dagoberto A | 16 | 672 | 3205
PR | 111 | 11/08/24 | 136 | Paco Leyva, Orlando | 6 | 366 | 3208
PR | 111 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I | 8 | 352 | 23214
PR | 111 | 11/08/24 | 146 | Carmona, Raul O | 16 | 848 | 23218
PR | 111 | 11/15/24 | 353 | Galdamez, Dagoberto A | 16 | 672 | 3217
PR | 111 | 11/15/24 | 356 | Paco Leyva, Orlando | 12 | 732 | 3220
PR | 111 | 11/15/24 | 366 | Carmona, Raul O | 16 | 848 | 33230
PR | 111 | 11/15/24 | 389 | Lopez, Maslin A | 8 | 264 | 33253
PR | 111 | 11/22/24 | 508 | Galdamez, Dagoberto A | 16 | 672 | 3230
PR | 111 | 11/22/24 | 511 | Paco Leyva, Orlando | 13 | 793 | 3233
PR | 111 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I | 8 | 352 | 43239
PR | 111 | 11/22/24 | 521 | Carmona, Raul O | 16 | 848 | 43243
PR | 111 | 11/22/24 | 543 | Lima Romero, Melvin A | 8 | 352 | 43265
PR | 111 | 11/22/24 | 544 | Lopez, Maslin A | 8 | 264 | 43266
PR | 111 | 11/29/24 | 656 | Galdamez, Dagoberto A | 16 | 672 | 3242
PR | 111 | 11/29/24 | 659 | Paco Leyva, Orlando | 8 | 488 | 3245
PR | 111 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I | 16 | 704 | 53251
PR | 111 | 12/06/24 | 58 | Galdamez, Dagoberto A | 4 | 168 | 3254
PR | 111 | 12/06/24 | 61 | Paco Leyva, Orlando | 4 | 244 | 3257
PR | 111 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I | 4 | 176 | 13263
PR | 111 | 12/06/24 | 71 | Carmona, Raul O | 12 | 636 | 13267
PR | 111 | 12/13/24 | 235 | Anderson, Richard P | 2 | 130 | 3270
PR | 111 | 12/13/24 | 241 | Galdamez, Dagoberto A | 16 | 672 | 3276
PR | 111 | 12/13/24 | 243 | Paco Leyva, Orlando | 2 | 122 | 3278
PR | 111 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I | 16 | 704 | 23284
PR | 111 | 12/13/24 | 253 | Carmona, Raul O | 16 | 848 | 23288
PR | 111 | 12/20/24 | 428 | Galdamez, Dagoberto A | 8 | 336 | 3286
PR | 111 | 12/20/24 | 430 | Paco Leyva, Orlando | 4 | 244 | 3288
PR | 111 | 12/20/24 | 440 | Carmona, Raul O | 8 | 424 | 33298
PR | 111 | 12/27/24 | 559 | Carmona, Raul O | 8 | 424 | 43309
PR | 111 | 01/10/25 | 181 | Galdamez, Dagoberto A | 12 | 504 | 3319
PR | 111 | 01/10/25 | 183 | Paco Leyva, Orlando | 4 | 244 | 3321
PR | 111 | 01/17/25 | 346 | Galdamez, Dagoberto A | 8 | 336 | 3332
PR | 111 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I | 8 | 352 | 33339
PR | 111 | 01/17/25 | 384 | Paco Leyva, Orlando | 18 | 1098 | 33370
PR | 111 | 01/24/25 | 512 | Galdamez, Dagoberto A | 24 | 1008 | 3342
PR | 111 | 01/24/25 | 551 | Paco Leyva, Orlando | 16 | 976 | 43381
PR | 111 | 01/31/25 | 736 | Lopez, Maslin A | 4 | 132 | 53384
PR | 111 | 01/31/25 | 743 | Paco Leyva, Orlando | 12 | 732 | 53391
PR | 111 | 02/07/25 | 66 | Lopez, Maslin A | 12 | 396 | 13393
PR | 111 | 02/07/25 | 73 | Paco Leyva, Orlando | 4 | 244 | 13400
PR | 111 | 02/14/25 | 232 | Lopez, Maslin A | 16 | 528 | 23402
PR | 111 | 02/14/25 | 239 | Paco Leyva, Orlando | 20 | 1220 | 23409
PR | 111 | 02/14/25 | 242 | Reed, Reuben H | 16 | 992 | 23412
PR | 111 | 02/21/25 | 350 | Lopez, Maslin A | 16 | 528 | 33412
PR | 111 | 02/21/25 | 357 | Paco Leyva, Orlando | 12 | 732 | 33419
PR | 111 | 02/28/25 | 540 | Lopez, Maslin A | 8 | 264 | 43423
PR | 111 | 02/28/25 | 547 | Paco Leyva, Orlando | 9 | 549 | 43430
PR | 111 | 03/07/25 | 53 | Lopez, Maslin A | 20 | 660 | 13433
PR | 111 | 03/07/25 | 60 | Paco Leyva, Orlando | 22 | 1342 | 13440
PR | 111 | 03/14/25 | 260 | Paco Leyva, Orlando | 9 | 549 | 23451
PR | 111 | 04/18/25 | 416 | Galdamez, Dagoberto A | 8 | 336 | 3474
PR | 111 | 06/27/25 | 468 | Galdamez, Dagoberto A | 8 | 336 | 3561
PR | 111 | 07/03/25 | 12 | Galdamez, Dagoberto A | 8 | 336 | 3569
PR | 111 | 07/11/25 | 144 | Barnhart, Joseph N | 1 | 68 | 23583
PR | 111 | 07/18/25 | 341 | Paco Leyva, Orlando | 5 | 305 | 33620
PR | 111 | 08/01/25 | 12 | Barnhart, Joseph N | 1 | 68 | 13603
PR | 111 | 08/22/25 | 371 | Barnhart, Joseph N | 2 | 136 | 43621
PR | 112 | 10/20/23 | 597 | Barnhart, Joseph N | 1 | 68 | 42578
PR | 112 | 10/27/23 | 842 | Anderson, Richard P | 6 | 390 | 42692
PR | 112 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I | 22 | 968 | 42696
PR | 112 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M | 22 | 858 | 42753
PR | 112 | 10/27/23 | 926 | Paco Leyva, Orlando | 3 | 183 | 42775
PR | 112 | 11/03/23 | 5 | Anderson, Richard P | 16 | 1040 | 42813
PR | 112 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I | 17 | 748 | 42817
PR | 112 | 11/03/23 | 47 | Galdamez, Dagoberto A | 12 | 504 | 42855
PR | 112 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M | 17 | 663 | 42875
PR | 112 | 11/03/23 | 85 | Nunez Bravo, Jose L | 14 | 322 | 42893
PR | 112 | 12/08/23 | 326 | Anderson, Richard P | 5 | 325 | 43412
PR | 112 | 12/08/23 | 330 | Balderas Ortiz, Ricardo I | 16 | 704 | 43416
PR | 112 | 12/08/23 | 331 | Barnhart, Joseph N | 1 | 68 | 43417
PR | 112 | 12/08/23 | 364 | Galdamez, Dagoberto A | 24 | 1008 | 43450
PR | 112 | 12/08/23 | 384 | Jimenez Alvarenga, Gerson M | 24 | 936 | 43470
PR | 112 | 12/08/23 | 406 | Paco Leyva, Orlando | 26 | 1586 | 43492
PR | 112 | 12/15/23 | 678 | Anderson, Richard P | 4 | 260 | 1121
PR | 112 | 12/15/23 | 682 | Balderas Ortiz, Ricardo I | 24 | 1056 | 1125
PR | 112 | 12/15/23 | 717 | Galdamez, Dagoberto A | 32 | 1344 | 1159
PR | 112 | 12/15/23 | 737 | Jimenez Alvarenga, Gerson M | 24 | 936 | 1179
PR | 112 | 12/15/23 | 759 | Paco Leyva, Orlando | 34 | 2074 | 1201
PR | 112 | 12/22/23 | 958 | Anderson, Richard P | 3 | 195 | 1239
PR | 112 | 12/22/23 | 962 | Balderas Ortiz, Ricardo I | 15 | 660 | 1243
PR | 112 | 12/22/23 | 997 | Galdamez, Dagoberto A | 7 | 441 | 1277
PR | 112 | 12/22/23 | 997 | Galdamez, Dagoberto A | 32 | 1344 | 1277
PR | 112 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M | 7 | 409.5 | 1296
PR | 112 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M | 16 | 624 | 1296
PR | 112 | 12/22/23 | 1033 | Nunez Bravo, Jose L | 7 | 161 | 1313
PR | 112 | 12/22/23 | 1037 | Paco Leyva, Orlando | 7 | 640.5 | 1317
PR | 112 | 12/22/23 | 1037 | Paco Leyva, Orlando | 32 | 1952 | 1317
PR | 112 | 12/29/23 | 1106 | Anderson, Richard P | 3 | 195 | 1355
PR | 112 | 12/29/23 | 1110 | Balderas Ortiz, Ricardo I | 8 | 352 | 1359
PR | 112 | 12/29/23 | 1164 | Jimenez Alvarenga, Gerson M | 8 | 312 | 1412
PR | 112 | 12/29/23 | 1181 | Nunez Bravo, Jose L | 8 | 184 | 1429
PR | 112 | 12/29/23 | 1185 | Paco Leyva, Orlando | 28 | 1708 | 1433
PR | 112 | 01/05/24 | 16 | Anderson, Richard P | 20 | 1300 | 1472
PR | 112 | 01/05/24 | 20 | Balderas Ortiz, Ricardo I | 24 | 1056 | 1476
PR | 112 | 01/05/24 | 21 | Barnhart, Joseph N | 2 | 136 | 1477
PR | 112 | 01/05/24 | 55 | Galdamez, Dagoberto A | 16 | 672 | 1510
PR | 112 | 01/05/24 | 61 | Gochez Molina, Douglas O | 4 | 100 | 1516
PR | 112 | 01/05/24 | 74 | Jimenez Alvarenga, Gerson M | 8 | 312 | 1529
PR | 112 | 01/05/24 | 91 | Nunez Bravo, Jose L | 16 | 368 | 1546
PR | 112 | 01/05/24 | 92 | Nuno Ordonez, Roberto F | 4 | 96 | 1547
PR | 112 | 01/05/24 | 95 | Paco Leyva, Orlando | 32 | 1952 | 1550
PR | 112 | 01/12/24 | 354 | Anderson, Richard P | 6.5 | 422.5 | 1587
PR | 112 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I | 20 | 880 | 1591
PR | 112 | 01/12/24 | 393 | Galdamez, Dagoberto A | 20 | 840 | 1625
PR | 112 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M | 20 | 780 | 1643
PR | 112 | 01/12/24 | 428 | Nunez Bravo, Jose L | 28 | 644 | 1660
PR | 112 | 01/12/24 | 432 | Paco Leyva, Orlando | 36 | 2196 | 1664
PR | 112 | 01/19/24 | 721 | Nunez Bravo, Jose L | 16 | 368 | 1771
PR | 112 | 01/19/24 | 725 | Paco Leyva, Orlando | 8 | 488 | 1775
PR | 112 | 07/26/24 | 563 | Anderson, Richard P | 2 | 130 | 3015
PR | 112 | 10/25/24 | 594 | Barnhart, Joseph N | 0.5 | 34 | 43191
PR | 120 | 11/10/23 | 482 | Draves, Steven W | 3 | 165 | 42966
PR | 120 | 12/01/23 | 45 | Galdamez, Dagoberto A | 4 | 168 | 43328
PR | 120 | 12/08/23 | 326 | Anderson, Richard P | 6 | 390 | 43412
PR | 120 | 12/08/23 | 331 | Barnhart, Joseph N | 1 | 68 | 43417
PR | 120 | 12/15/23 | 717 | Galdamez, Dagoberto A | 8 | 336 | 1159
PR | 120 | 01/05/24 | 61 | Gochez Molina, Douglas O | 28 | 700 | 1516
PR | 120 | 01/05/24 | 92 | Nuno Ordonez, Roberto F | 4 | 96 | 1547
PR | 120 | 01/12/24 | 354 | Anderson, Richard P | 1.5 | 97.5 | 1587
PR | 120 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I | 4 | 176 | 1591
PR | 120 | 01/12/24 | 378 | de Dios, Pedro | 4 | 104 | 1696
PR | 120 | 01/12/24 | 393 | Galdamez, Dagoberto A | 4 | 168 | 1625
PR | 120 | 01/12/24 | 399 | Gochez Molina, Douglas O | 24 | 600 | 1631
PR | 120 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M | 4 | 156 | 1643
PR | 120 | 01/12/24 | 422 | McCurry, Maxwell J | 4 | 96 | 1654
PR | 120 | 01/12/24 | 428 | Nunez Bravo, Jose L | 4 | 92 | 1660
PR | 120 | 01/12/24 | 429 | Nuno Ordonez, Roberto F | 16 | 384 | 1661
PR | 120 | 01/12/24 | 432 | Paco Leyva, Orlando | 2 | 122 | 1664
PR | 120 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I | 3 | 132 | 1703
PR | 120 | 01/19/24 | 653 | Barnhart, Joseph N | 1 | 68 | 1704
PR | 120 | 01/19/24 | 656 | Belcher, Jacob T | 4 | 112 | 1707
PR | 120 | 01/19/24 | 660 | Carmona, Raul O | 16 | 848 | 1711
PR | 120 | 01/19/24 | 688 | Games, Jordan M | 6 | 276 | 1738
PR | 120 | 01/19/24 | 693 | Gochez Molina, Douglas O | 32 | 800 | 1743
PR | 120 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M | 16 | 624 | 1755
PR | 120 | 01/19/24 | 715 | McCurry, Maxwell J | 4 | 96 | 1765
PR | 120 | 01/19/24 | 721 | Nunez Bravo, Jose L | 8 | 184 | 1771
PR | 120 | 01/19/24 | 722 | Nuno Ordonez, Roberto F | 16 | 384 | 1772
PR | 120 | 01/19/24 | 725 | Paco Leyva, Orlando | 4 | 244 | 1775
PR | 120 | 01/19/24 | 740 | Sontay Garcia, Juan C | 24 | 504 | 1790
PR | 120 | 01/26/24 | 922 | Balderas Ortiz, Ricardo I | 40 | 1760 | 1814
PR | 120 | 01/26/24 | 926 | Belcher, Jacob T | 40 | 1120 | 1818
PR | 120 | 01/26/24 | 957 | Galdamez, Dagoberto A | 32 | 1344 | 1848
PR | 120 | 01/26/24 | 975 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 1866
PR | 120 | 01/26/24 | 985 | McCurry, Maxwell J | 24 | 576 | 1876
PR | 120 | 01/26/24 | 991 | Nunez Bravo, Jose L | 22 | 506 | 1882
PR | 120 | 01/26/24 | 995 | Paco Leyva, Orlando | 19 | 1159 | 1886
PR | 120 | 01/26/24 | 1011 | Sontay Garcia, Juan C | 32 | 672 | 1902
PR | 120 | 02/02/24 | 11 | Anderson, Richard P | 3 | 195 | 1923
PR | 120 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I | 16 | 704 | 1927
PR | 120 | 02/02/24 | 19 | Belcher, Jacob T | 12 | 336 | 1931
PR | 120 | 02/02/24 | 23 | Carmona, Raul O | 28 | 1484 | 1935
PR | 120 | 02/02/24 | 50 | Galdamez, Dagoberto A | 28 | 1176 | 1961
PR | 120 | 02/02/24 | 56 | Gochez Molina, Douglas O | 16 | 400 | 1967
PR | 120 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M | 24 | 936 | 1979
PR | 120 | 02/02/24 | 78 | McCurry, Maxwell J | 12 | 288 | 1989
PR | 120 | 02/02/24 | 84 | Nunez Bravo, Jose L | 28 | 644 | 1995
PR | 120 | 02/02/24 | 88 | Paco Leyva, Orlando | 22 | 1342 | 1999
PR | 120 | 02/02/24 | 104 | Sontay Garcia, Juan C | 40 | 840 | 2015
PR | 120 | 02/02/24 | 105 | Storozhuk, Maxim A | 20 | 440 | 2016
PR | 120 | 02/09/24 | 231 | Anderson, Richard P | 1 | 65 | 2035
PR | 120 | 02/09/24 | 235 | Balderas Ortiz, Ricardo I | 40 | 1760 | 2039
PR | 120 | 02/09/24 | 239 | Belcher, Jacob T | 8 | 224 | 2043
PR | 120 | 02/09/24 | 243 | Carmona, Raul O | 16 | 848 | 2047
PR | 120 | 02/09/24 | 266 | Escalante Escobar, Boanerge | 16 | 560 | 2069
PR | 120 | 02/09/24 | 270 | Galdamez, Dagoberto A | 20 | 840 | 2073
PR | 120 | 02/09/24 | 276 | Gochez Molina, Douglas O | 8 | 200 | 2079
PR | 120 | 02/09/24 | 288 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2091
PR | 120 | 02/09/24 | 297 | McCabe, Thomas C | 24 | 1056 | 2100
PR | 120 | 02/09/24 | 298 | McCurry, Maxwell J | 16 | 384 | 2101
PR | 120 | 02/09/24 | 304 | Nunez Bravo, Jose L | 24 | 552 | 2107
PR | 120 | 02/09/24 | 308 | Paco Leyva, Orlando | 21 | 1281 | 2111
PR | 120 | 02/16/24 | 488 | Anderson, Richard P | 4 | 260 | 2148
PR | 120 | 02/16/24 | 492 | Balderas Ortiz, Ricardo I | 40 | 1760 | 2152
PR | 120 | 02/16/24 | 496 | Belcher, Jacob T | 32 | 896 | 2156
PR | 120 | 02/16/24 | 500 | Carmona, Raul O | 40 | 2120 | 2160
PR | 120 | 02/16/24 | 523 | Escalante Escobar, Boanerge | 32 | 1120 | 2182
PR | 120 | 02/16/24 | 527 | Galdamez, Dagoberto A | 40 | 1680 | 2186
PR | 120 | 02/16/24 | 533 | Gochez Molina, Douglas O | 40 | 1000 | 2192
PR | 120 | 02/16/24 | 545 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2204
PR | 120 | 02/16/24 | 554 | McCabe, Thomas C | 39.5 | 1738 | 2213
PR | 120 | 02/16/24 | 555 | McCurry, Maxwell J | 39.5 | 948 | 2214
PR | 120 | 02/16/24 | 561 | Nunez Bravo, Jose L | 15 | 345 | 2220
PR | 120 | 02/16/24 | 565 | Paco Leyva, Orlando | 21 | 1281 | 2224
PR | 120 | 02/16/24 | 582 | Sontay Garcia, Juan C | 32 | 672 | 2241
PR | 120 | 02/16/24 | 583 | Storozhuk, Maxim A | 32 | 704 | 2242
PR | 120 | 02/16/24 | 584 | Suniga Aviles, Kelvin A | 40 | 840 | 2243
PR | 120 | 02/16/24 | 597 | Zuniga Avilez, Eduar A | 32 | 640 | 2256
PR | 120 | 02/23/24 | 659 | Anderson, Richard P | 3 | 195 | 2260
PR | 120 | 02/23/24 | 663 | Balderas Ortiz, Ricardo I | 40 | 1760 | 2264
PR | 120 | 02/23/24 | 667 | Belcher, Jacob T | 33 | 924 | 2268
PR | 120 | 02/23/24 | 671 | Carmona, Raul O | 24 | 1272 | 2272
PR | 120 | 02/23/24 | 693 | Escalante Escobar, Boanerge | 40 | 1400 | 2293
PR | 120 | 02/23/24 | 697 | Galdamez, Dagoberto A | 39 | 1638 | 2297
PR | 120 | 02/23/24 | 701 | Gochez Molina, Douglas O | 40 | 1000 | 2301
PR | 120 | 02/23/24 | 713 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2313
PR | 120 | 02/23/24 | 722 | McCabe, Thomas C | 16 | 704 | 2322
PR | 120 | 02/23/24 | 723 | McCurry, Maxwell J | 8 | 192 | 2323
PR | 120 | 02/23/24 | 724 | Melgar Moz, Brandon | 40 | 880 | 2324
PR | 120 | 02/23/24 | 729 | Nunez Bravo, Jose L | 40 | 920 | 2329
PR | 120 | 02/23/24 | 733 | Paco Leyva, Orlando | 21 | 1281 | 2333
PR | 120 | 02/23/24 | 750 | Sontay Garcia, Juan C | 40 | 840 | 2350
PR | 120 | 02/23/24 | 751 | Storozhuk, Maxim A | 40 | 880 | 2351
PR | 120 | 02/23/24 | 752 | Suniga Aviles, Kelvin A | 40 | 840 | 2352
PR | 120 | 02/23/24 | 765 | Zuniga Avilez, Eduar A | 40 | 800 | 2365
PR | 120 | 03/01/24 | 4 | Anderson, Richard P | 4 | 260 | 2370
PR | 120 | 03/01/24 | 8 | Balderas Ortiz, Ricardo I | 40 | 1760 | 2374
PR | 120 | 03/01/24 | 12 | Belcher, Jacob T | 8 | 224 | 2378
PR | 120 | 03/01/24 | 15 | Carmona, Raul O | 32 | 1696 | 2381
PR | 120 | 03/01/24 | 36 | Escalante Escobar, Boanerge | 40 | 1400 | 2401
PR | 120 | 03/01/24 | 37 | Escobar Ramirez, Carlos M | 22 | 440 | 2402
PR | 120 | 03/01/24 | 42 | Gochez Molina, Douglas O | 40 | 1000 | 2407
PR | 120 | 03/01/24 | 48 | Guerrero Espinoza, Mario | 14 | 420 | 2413
PR | 120 | 03/01/24 | 53 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2418
PR | 120 | 03/01/24 | 55 | Lopez, Maslin A | 14 | 462 | 2420
PR | 120 | 03/01/24 | 60 | McCabe, Thomas C | 6 | 264 | 2425
PR | 120 | 03/01/24 | 61 | McCurry, Maxwell J | 16 | 384 | 2426
PR | 120 | 03/01/24 | 62 | Melgar Moz, Brandon | 40 | 880 | 2427
PR | 120 | 03/01/24 | 67 | Nunez Bravo, Jose L | 40 | 920 | 2432
PR | 120 | 03/01/24 | 71 | Paco Leyva, Orlando | 22 | 1342 | 2436
PR | 120 | 03/01/24 | 80 | Rodriguez Arevalos, Christian | 8 | 352 | 2445
PR | 120 | 03/01/24 | 86 | Sontay Garcia, Juan C | 40 | 840 | 2451
PR | 120 | 03/01/24 | 87 | Storozhuk, Maxim A | 32 | 704 | 2452
PR | 120 | 03/01/24 | 88 | Suniga Aviles, Kelvin A | 32 | 672 | 2453
PR | 120 | 03/01/24 | 95 | Wilson, Garret A | 8 | 432 | 2460
PR | 120 | 03/01/24 | 96 | Yohannes Jr., Samson | 22 | 726 | 2461
PR | 120 | 03/01/24 | 100 | Zuniga Avilez, Eduar A | 32 | 640 | 2465
PR | 120 | 03/01/24 | 107 | Gerard, Mitchell J | 16 | 976 | 92473
PR | 120 | 03/08/24 | 250 | Anderson, Richard P | 6 | 390 | 2469
PR | 120 | 03/08/24 | 251 | Aquino, Juan | 32 | 864 | 2470
PR | 120 | 03/08/24 | 252 | Barnhart, Joseph N | 1 | 68 | 2471
PR | 120 | 03/08/24 | 254 | Belcher, Jacob T | 24 | 672 | 2473
PR | 120 | 03/08/24 | 255 | Carmona, Raul O | 32 | 1696 | 2474
PR | 120 | 03/08/24 | 269 | Escalante Escobar, Boanerge | 40 | 1400 | 2488
PR | 120 | 03/08/24 | 270 | Escobar Ramirez, Carlos M | 32 | 640 | 2489
PR | 120 | 03/08/24 | 273 | Gochez Molina, Douglas O | 40 | 1000 | 2492
PR | 120 | 03/08/24 | 276 | Guerrero Espinoza, Mario | 24 | 720 | 2495
PR | 120 | 03/08/24 | 278 | Hubbard, Justin A | 31 | 1426 | 2497
PR | 120 | 03/08/24 | 280 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2499
PR | 120 | 03/08/24 | 283 | Martinez Garcia, Cesar B | 32 | 640 | 2502
PR | 120 | 03/08/24 | 284 | McCabe, Thomas C | 31 | 1364 | 2503
PR | 120 | 03/08/24 | 285 | McCurry, Maxwell J | 40 | 960 | 2504
PR | 120 | 03/08/24 | 286 | Melgar Moz, Brandon | 40 | 880 | 2505
PR | 120 | 03/08/24 | 290 | Nunez Bravo, Jose L | 32 | 736 | 2509
PR | 120 | 03/08/24 | 292 | Paco Leyva, Orlando | 20 | 1220 | 2511
PR | 120 | 03/08/24 | 294 | Platero Navas, Ronald A | 32 | 640 | 2513
PR | 120 | 03/08/24 | 296 | Puentez, Victor M | 24 | 528 | 2515
PR | 120 | 03/08/24 | 299 | Rodriguez Arevalos, Christian | 4 | 176 | 2518
PR | 120 | 03/08/24 | 305 | Sontay Garcia, Juan C | 32 | 672 | 2524
PR | 120 | 03/08/24 | 306 | Storozhuk, Maxim A | 24 | 528 | 2525
PR | 120 | 03/08/24 | 307 | Suniga Aviles, Kelvin A | 16 | 336 | 2526
PR | 120 | 03/08/24 | 311 | Yohannes Jr., Samson | 40 | 1320 | 2530
PR | 120 | 03/08/24 | 317 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92536
PR | 120 | 03/08/24 | 358 | Taylor, Evan R | 25 | 1300 | 92576
PR | 120 | 03/08/24 | 363 | Young, Joshua S | 40 | 1080 | 92581
PR | 120 | 03/15/24 | 505 | Anderson, Richard P | 5 | 325 | 2534
PR | 120 | 03/15/24 | 506 | Aquino, Juan | 40 | 1080 | 2535
PR | 120 | 03/15/24 | 509 | Belcher, Jacob T | 16 | 448 | 2538
PR | 120 | 03/15/24 | 510 | Carmona, Raul O | 40 | 2120 | 2539
PR | 120 | 03/15/24 | 523 | Escalante Escobar, Boanerge | 40 | 1400 | 2552
PR | 120 | 03/15/24 | 524 | Escobar Ramirez, Carlos M | 40 | 800 | 2553
PR | 120 | 03/15/24 | 526 | Galdamez, Dagoberto A | 24 | 1008 | 2555
PR | 120 | 03/15/24 | 528 | Gochez Molina, Douglas O | 40 | 1000 | 2557
PR | 120 | 03/15/24 | 531 | Guerrero Espinoza, Mario | 32 | 960 | 2560
PR | 120 | 03/15/24 | 535 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2564
PR | 120 | 03/15/24 | 537 | Martinez Garcia, Cesar B | 40 | 800 | 2566
PR | 120 | 03/15/24 | 538 | McCurry, Maxwell J | 16 | 384 | 2567
PR | 120 | 03/15/24 | 539 | Melgar Moz, Brandon | 40 | 880 | 2568
PR | 120 | 03/15/24 | 543 | Nunez Bravo, Jose L | 24 | 552 | 2572
PR | 120 | 03/15/24 | 545 | Paco Leyva, Orlando | 16 | 976 | 2574
PR | 120 | 03/15/24 | 547 | Platero Navas, Ronald A | 40 | 800 | 2576
PR | 120 | 03/15/24 | 549 | Puentez, Victor M | 40 | 880 | 2578
PR | 120 | 03/15/24 | 558 | Sontay Garcia, Juan C | 32 | 672 | 2587
PR | 120 | 03/15/24 | 559 | Storozhuk, Maxim A | 32 | 704 | 2588
PR | 120 | 03/15/24 | 560 | Suniga Aviles, Kelvin A | 24 | 504 | 2589
PR | 120 | 03/15/24 | 564 | Yohannes Jr., Samson | 40 | 1320 | 2593
PR | 120 | 03/15/24 | 574 | Puentez, Victor M | 40 | -880 | 2578
PR | 120 | 03/15/24 | 580 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92599
PR | 120 | 03/15/24 | 601 | Gerard, Mitchell J | 4 | 244 | 92619
PR | 120 | 03/15/24 | 610 | Lopez, Maslin A | 16 | 528 | 92628
PR | 120 | 03/15/24 | 625 | Puentez, Victor M | 40 | 880 | 92643
PR | 120 | 03/15/24 | 629 | Taylor, Evan R | 40 | 2080 | 92647
PR | 120 | 03/15/24 | 635 | Young, Joshua S | 40 | 1080 | 92653
PR | 120 | 03/22/24 | 798 | Anderson, Richard P | 10 | 650 | 2596
PR | 120 | 03/22/24 | 799 | Aquino, Juan | 40 | 1080 | 2597
PR | 120 | 03/22/24 | 802 | Belcher, Jacob T | 8 | 224 | 2600
PR | 120 | 03/22/24 | 803 | Carmona, Raul O | 40 | 2120 | 2601
PR | 120 | 03/22/24 | 811 | Escalante Escobar, Boanerge | 40 | 1400 | 2609
PR | 120 | 03/22/24 | 812 | Escobar Ramirez, Carlos M | 40 | 800 | 2610
PR | 120 | 03/22/24 | 814 | Galdamez, Dagoberto A | 40 | 1680 | 2612
PR | 120 | 03/22/24 | 816 | Gochez Molina, Douglas O | 40 | 1000 | 2614
PR | 120 | 03/22/24 | 821 | Hubbard, Justin A | 16 | 736 | 2619
PR | 120 | 03/22/24 | 823 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2621
PR | 120 | 03/22/24 | 825 | Melgar Moz, Brandon | 40 | 880 | 2623
PR | 120 | 03/22/24 | 828 | Nunez Bravo, Jose L | 39 | 897 | 2626
PR | 120 | 03/22/24 | 829 | Paco Leyva, Orlando | 18 | 1098 | 2627
PR | 120 | 03/22/24 | 830 | Platero Navas, Ronald A | 40 | 800 | 2628
PR | 120 | 03/22/24 | 832 | Rodriguez Arevalos, Christian | 32 | 1408 | 2630
PR | 120 | 03/22/24 | 836 | Sontay Garcia, Juan C | 39 | 819 | 2634
PR | 120 | 03/22/24 | 837 | Storozhuk, Maxim A | 26 | 572 | 2635
PR | 120 | 03/22/24 | 847 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92645
PR | 120 | 03/22/24 | 880 | Lopez, Maslin A | 24 | 792 | 92677
PR | 120 | 03/22/24 | 884 | Martinez Garcia, Cesar B | 40 | 800 | 92681
PR | 120 | 03/22/24 | 896 | Puentez, Victor M | 40 | 880 | 92693
PR | 120 | 03/22/24 | 902 | Taylor, Evan R | 40 | 2080 | 92699
PR | 120 | 03/22/24 | 907 | Wilson, Garret A | 13 | 702 | 92704
PR | 120 | 03/22/24 | 908 | Yohannes Jr., Samson | 40 | 1320 | 92705
PR | 120 | 03/22/24 | 909 | Young, Joshua S | 40 | 1080 | 92706
PR | 120 | 03/29/24 | 1180 | Anderson, Richard P | 2 | 130 | 2641
PR | 120 | 03/29/24 | 1181 | Aquino, Juan | 40 | 1080 | 2642
PR | 120 | 03/29/24 | 1182 | Barnhart, Joseph N | 2 | 136 | 2643
PR | 120 | 03/29/24 | 1190 | Escalante Escobar, Boanerge | 40 | 1400 | 2651
PR | 120 | 03/29/24 | 1192 | Galdamez, Dagoberto A | 40 | 1680 | 2653
PR | 120 | 03/29/24 | 1198 | Hubbard, Justin A | 31.5 | 1449 | 2659
PR | 120 | 03/29/24 | 1200 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 2661
PR | 120 | 03/29/24 | 1204 | Nunez Bravo, Jose L | 40 | 920 | 2665
PR | 120 | 03/29/24 | 1205 | Paco Leyva, Orlando | 18 | 1098 | 2666
PR | 120 | 03/29/24 | 1210 | Sontay Garcia, Juan C | 40 | 840 | 2671
PR | 120 | 03/29/24 | 1219 | Araque, Mario W | 40 | 880 | 92680
PR | 120 | 03/29/24 | 1221 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92682
PR | 120 | 03/29/24 | 1226 | Carmona, Raul O | 40 | 2120 | 92687
PR | 120 | 03/29/24 | 1243 | Escobar Ramirez, Carlos M | 40 | 800 | 92703
PR | 120 | 03/29/24 | 1249 | Gochez Molina, Douglas O | 40 | 1000 | 92709
PR | 120 | 03/29/24 | 1258 | Lopez, Maslin A | 40 | 1320 | 92718
PR | 120 | 03/29/24 | 1262 | Martinez Garcia, Cesar B | 40 | 800 | 92722
PR | 120 | 03/29/24 | 1264 | Melgar Moz, Brandon | 40 | 880 | 92724
PR | 120 | 03/29/24 | 1273 | Platero Navas, Ronald A | 40 | 800 | 92733
PR | 120 | 03/29/24 | 1276 | Puentez, Victor M | 40 | 880 | 92736
PR | 120 | 03/29/24 | 1283 | Taylor, Evan R | 40 | 2080 | 92743
PR | 120 | 03/29/24 | 1289 | Yohannes Jr., Samson | 32 | 1056 | 92749
PR | 120 | 03/29/24 | 1290 | Young, Joshua S | 32 | 864 | 92750
PR | 120 | 04/05/24 | 2 | Anderson, Richard P | 3 | 195 | 2678
PR | 120 | 04/05/24 | 3 | Aquino, Juan | 40 | 1080 | 2679
PR | 120 | 04/05/24 | 4 | Barnhart, Joseph N | 1 | 68 | 2680
PR | 120 | 04/05/24 | 12 | Escalante Escobar, Boanerge | 40 | 1400 | 2688
PR | 120 | 04/05/24 | 14 | Galdamez, Dagoberto A | 40 | 1680 | 2690
PR | 120 | 04/05/24 | 17 | Guerrero Espinoza, Mario | 24 | 720 | 2693
PR | 120 | 04/05/24 | 21 | Molina, Carlos G | 24 | 624 | 2697
PR | 120 | 04/05/24 | 23 | Nunez Bravo, Jose L | 40 | 920 | 2699
PR | 120 | 04/05/24 | 24 | Paco Leyva, Orlando | 18 | 1098 | 2700
PR | 120 | 04/05/24 | 25 | Rodriguez Arevalos, Christian | 13 | 572 | 2701
PR | 120 | 04/05/24 | 29 | Storozhuk, Maxim A | 40 | 880 | 2705
PR | 120 | 04/05/24 | 32 | Zuniga Avilez, Eduar A | 32 | 640 | 2708
PR | 120 | 04/05/24 | 36 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92712
PR | 120 | 04/05/24 | 41 | Carmona, Raul O | 40 | 2120 | 92717
PR | 120 | 04/05/24 | 59 | Escobar Ramirez, Carlos M | 37 | 740 | 92734
PR | 120 | 04/05/24 | 65 | Gochez Molina, Douglas O | 40 | 1000 | 92740
PR | 120 | 04/05/24 | 73 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92748
PR | 120 | 04/05/24 | 76 | Lopez, Maslin A | 38 | 1254 | 92751
PR | 120 | 04/05/24 | 80 | Martinez Garcia, Cesar B | 40 | 800 | 92755
PR | 120 | 04/05/24 | 82 | McCurry, Maxwell J | 16 | 384 | 92757
PR | 120 | 04/05/24 | 83 | Melgar Moz, Brandon | 40 | 880 | 92758
PR | 120 | 04/05/24 | 92 | Platero Navas, Ronald A | 40 | 800 | 92767
PR | 120 | 04/05/24 | 95 | Puentez, Victor M | 40 | 880 | 92770
PR | 120 | 04/05/24 | 101 | Sontay Garcia, Juan C | 40 | 840 | 92776
PR | 120 | 04/05/24 | 104 | Taylor, Evan R | 24 | 1248 | 92779
PR | 120 | 04/05/24 | 111 | Yohannes Jr., Samson | 40 | 1320 | 92786
PR | 120 | 04/05/24 | 112 | Young, Joshua S | 24 | 648 | 92787
PR | 120 | 04/05/24 | 113 | Zepeda Mendoza, Cesar | 8 | 176 | 92788
PR | 120 | 04/05/24 | 132 | Jimenez Alvarenga, Gerson M | 40 | -1560 | 92748
PR | 120 | 04/05/24 | 133 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92790
PR | 120 | 04/12/24 | 165 | Aquino, Juan | 40 | 1080 | 2710
PR | 120 | 04/12/24 | 166 | Barnhart, Joseph N | 4 | 272 | 2711
PR | 120 | 04/12/24 | 174 | Galdamez, Dagoberto A | 32 | 1344 | 2719
PR | 120 | 04/12/24 | 177 | Guerrero Espinoza, Mario | 24 | 720 | 2722
PR | 120 | 04/12/24 | 180 | Molina, Carlos G | 32 | 832 | 2725
PR | 120 | 04/12/24 | 182 | Nunez Bravo, Jose L | 40 | 920 | 2727
PR | 120 | 04/12/24 | 183 | Paco Leyva, Orlando | 23 | 1403 | 2728
PR | 120 | 04/12/24 | 188 | Storozhuk, Maxim A | 40 | 880 | 2733
PR | 120 | 04/12/24 | 190 | Weeks, Gregg A | 40 | 1920 | 2735
PR | 120 | 04/12/24 | 192 | Zuniga Avilez, Eduar A | 8 | 160 | 2737
PR | 120 | 04/12/24 | 196 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92741
PR | 120 | 04/12/24 | 201 | Carmona, Raul O | 40 | 2120 | 92746
PR | 120 | 04/12/24 | 211 | Diaz Morales, Guni | 36 | 792 | 92755
PR | 120 | 04/12/24 | 212 | Diaz Morales, Teofilo | 40 | 880 | 92756
PR | 120 | 04/12/24 | 219 | Escalante Escobar, Boanerge | 24 | 840 | 92763
PR | 120 | 04/12/24 | 220 | Escobar Ramirez, Carlos M | 40 | 800 | 92764
PR | 120 | 04/12/24 | 226 | Gochez Molina, Douglas O | 40 | 1000 | 92770
PR | 120 | 04/12/24 | 234 | Hubbard, Justin A | 8 | 368 | 92778
PR | 120 | 04/12/24 | 235 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92779
PR | 120 | 04/12/24 | 238 | Lopez, Maslin A | 33 | 1089 | 92782
PR | 120 | 04/12/24 | 242 | Martinez Garcia, Cesar B | 40 | 800 | 92786
PR | 120 | 04/12/24 | 244 | McCurry, Maxwell J | 16 | 384 | 92788
PR | 120 | 04/12/24 | 245 | Melgar Moz, Brandon | 32 | 704 | 92789
PR | 120 | 04/12/24 | 254 | Platero Navas, Ronald A | 40 | 800 | 92798
PR | 120 | 04/12/24 | 257 | Puentez, Victor M | 40 | 880 | 92801
PR | 120 | 04/12/24 | 262 | Sontay Garcia, Juan C | 32 | 672 | 92806
PR | 120 | 04/12/24 | 263 | Suniga Aviles, Kelvin A | 16 | 336 | 92807
PR | 120 | 04/12/24 | 265 | Taylor, Evan R | 40 | 2080 | 92809
PR | 120 | 04/12/24 | 271 | Yohannes Jr., Samson | 32 | 1056 | 92815
PR | 120 | 04/12/24 | 272 | Young, Joshua S | 40 | 1080 | 92816
PR | 120 | 04/12/24 | 273 | Zepeda Mendoza, Cesar | 40 | 880 | 92817
PR | 120 | 04/19/24 | 444 | Anderson, Richard P | 25 | 1625 | 2738
PR | 120 | 04/19/24 | 445 | Barnhart, Joseph N | 2 | 136 | 2739
PR | 120 | 04/19/24 | 452 | Diaz Morales, Cristian A | 40 | 880 | 2746
PR | 120 | 04/19/24 | 453 | Galdamez, Dagoberto A | 40 | 1680 | 2747
PR | 120 | 04/19/24 | 458 | Molina, Carlos G | 24 | 624 | 2752
PR | 120 | 04/19/24 | 461 | Paco Leyva, Orlando | 20 | 1220 | 2755
PR | 120 | 04/19/24 | 466 | Storozhuk, Maxim A | 40 | 880 | 2760
PR | 120 | 04/19/24 | 468 | Weeks, Gregg A | 32 | 1536 | 2762
PR | 120 | 04/19/24 | 473 | Aquino, Juan | 40 | 1080 | 92767
PR | 120 | 04/19/24 | 476 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92770
PR | 120 | 04/19/24 | 481 | Carmona, Raul O | 40 | 2120 | 92775
PR | 120 | 04/19/24 | 490 | Diaz Morales, Elber | 40 | 880 | 92783
PR | 120 | 04/19/24 | 491 | Diaz Morales, Guni | 40 | 880 | 92784
PR | 120 | 04/19/24 | 492 | Diaz Morales, Teofilo | 40 | 880 | 92785
PR | 120 | 04/19/24 | 493 | Diaz Morales, Urias | 40 | 880 | 92786
PR | 120 | 04/19/24 | 495 | Draves, Steven W | 4 | 220 | 92788
PR | 120 | 04/19/24 | 499 | Escalante Escobar, Boanerge | 40 | 1400 | 92792
PR | 120 | 04/19/24 | 500 | Escobar Ramirez, Carlos M | 40 | 800 | 92793
PR | 120 | 04/19/24 | 507 | Gochez Molina, Douglas O | 32 | 800 | 92800
PR | 120 | 04/19/24 | 515 | Hubbard, Justin A | 16 | 736 | 92808
PR | 120 | 04/19/24 | 516 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92809
PR | 120 | 04/19/24 | 519 | Lopez, Maslin A | 40 | 1320 | 92812
PR | 120 | 04/19/24 | 523 | Martinez Garcia, Cesar B | 40 | 800 | 92816
PR | 120 | 04/19/24 | 525 | McCurry, Maxwell J | 8 | 192 | 92818
PR | 120 | 04/19/24 | 526 | Melgar Moz, Brandon | 40 | 880 | 92819
PR | 120 | 04/19/24 | 532 | Ortiz Carmona, Juan M | 40 | 1280 | 92825
PR | 120 | 04/19/24 | 535 | Platero Navas, Ronald A | 40 | 800 | 92828
PR | 120 | 04/19/24 | 538 | Puentez, Victor M | 40 | 880 | 92831
PR | 120 | 04/19/24 | 543 | Sontay Garcia, Juan C | 40 | 840 | 92836
PR | 120 | 04/19/24 | 546 | Taylor, Evan R | 40 | 2080 | 92839
PR | 120 | 04/19/24 | 552 | Yohannes Jr., Samson | 40 | 1320 | 92845
PR | 120 | 04/19/24 | 553 | Young, Joshua S | 40 | 1080 | 92846
PR | 120 | 04/19/24 | 554 | Zepeda Mendoza, Cesar | 40 | 880 | 92847
PR | 120 | 04/26/24 | 770 | Anderson, Richard P | 7 | 455 | 2765
PR | 120 | 04/26/24 | 778 | Diaz Morales, Cristian A | 40 | 880 | 2773
PR | 120 | 04/26/24 | 779 | Galdamez, Dagoberto A | 40 | 1680 | 2774
PR | 120 | 04/26/24 | 783 | Molina, Carlos G | 8 | 208 | 2778
PR | 120 | 04/26/24 | 785 | Nunez Bravo, Jose L | 32 | 736 | 2780
PR | 120 | 04/26/24 | 786 | Paco Leyva, Orlando | 21 | 1281 | 2781
PR | 120 | 04/26/24 | 791 | Storozhuk, Maxim A | 40 | 880 | 2786
PR | 120 | 04/26/24 | 798 | Aquino, Juan | 32 | 864 | 92793
PR | 120 | 04/26/24 | 801 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92796
PR | 120 | 04/26/24 | 806 | Carmona, Raul O | 40 | 2120 | 92801
PR | 120 | 04/26/24 | 815 | Diaz Morales, Elber | 16 | 352 | 92809
PR | 120 | 04/26/24 | 816 | Diaz Morales, Guni | 40 | 880 | 92810
PR | 120 | 04/26/24 | 817 | Diaz Morales, Teofilo | 32 | 704 | 92811
PR | 120 | 04/26/24 | 818 | Diaz Morales, Urias | 8 | 176 | 92812
PR | 120 | 04/26/24 | 823 | Escalante Escobar, Boanerge | 40 | 1400 | 92817
PR | 120 | 04/26/24 | 824 | Escobar Ramirez, Carlos M | 40 | 800 | 92818
PR | 120 | 04/26/24 | 831 | Gochez Molina, Douglas O | 40 | 1000 | 92825
PR | 120 | 04/26/24 | 840 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92834
PR | 120 | 04/26/24 | 843 | Lopez, Maslin A | 39 | 1287 | 92837
PR | 120 | 04/26/24 | 847 | Martinez Garcia, Cesar B | 39 | 780 | 92841
PR | 120 | 04/26/24 | 849 | McCurry, Maxwell J | 32 | 768 | 92843
PR | 120 | 04/26/24 | 850 | Melgar Moz, Brandon | 32 | 704 | 92844
PR | 120 | 04/26/24 | 851 | Mendoza Morales, Jesus A | 8 | 328 | 92845
PR | 120 | 04/26/24 | 856 | Ortiz Carmona, Juan M | 31 | 992 | 92850
PR | 120 | 04/26/24 | 859 | Platero Navas, Ronald A | 40 | 800 | 92853
PR | 120 | 04/26/24 | 862 | Puentez, Victor M | 40 | 880 | 92856
PR | 120 | 04/26/24 | 867 | Sontay Garcia, Juan C | 40 | 840 | 92861
PR | 120 | 04/26/24 | 868 | Suniga Aviles, Kelvin A | 16 | 336 | 92862
PR | 120 | 04/26/24 | 870 | Taylor, Evan R | 30 | 1560 | 92864
PR | 120 | 04/26/24 | 876 | Yohannes Jr., Samson | 40 | 1320 | 92870
PR | 120 | 04/26/24 | 878 | Zepeda Mendoza, Cesar | 38 | 836 | 92872
PR | 120 | 05/03/24 | 3 | Anderson, Richard P | 36 | 2340 | 2791
PR | 120 | 05/03/24 | 7 | Cosentino, Brandon C | 16 | 384 | 2795
PR | 120 | 05/03/24 | 11 | Diaz Morales, Cristian A | 40 | 880 | 2799
PR | 120 | 05/03/24 | 12 | Galdamez, Dagoberto A | 40 | 1680 | 2800
PR | 120 | 05/03/24 | 17 | Nunez Bravo, Jose L | 40 | 920 | 2805
PR | 120 | 05/03/24 | 18 | Paco Leyva, Orlando | 20 | 1220 | 2806
PR | 120 | 05/03/24 | 21 | Storozhuk, Maxim A | 40 | 880 | 2809
PR | 120 | 05/03/24 | 23 | Weeks, Gregg A | 32 | 1536 | 2811
PR | 120 | 05/03/24 | 24 | Zamudio Sanchez, Jose R | 8 | 384 | 2812
PR | 120 | 05/03/24 | 25 | Zuniga Avilez, Eduar A | 16 | 320 | 2813
PR | 120 | 05/03/24 | 27 | Aquino, Juan | 32 | 864 | 92815
PR | 120 | 05/03/24 | 29 | Ascencio, Jose L | 16 | 672 | 92817
PR | 120 | 05/03/24 | 30 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92818
PR | 120 | 05/03/24 | 33 | Boss, Benjamin T | 32 | 1632 | 92821
PR | 120 | 05/03/24 | 35 | Carmona, Raul O | 40 | 2120 | 92823
PR | 120 | 05/03/24 | 36 | Castro Hernandez, Jose A | 32 | 1728 | 92824
PR | 120 | 05/03/24 | 45 | Diaz Morales, Guni | 40 | 880 | 92832
PR | 120 | 05/03/24 | 46 | Diaz Morales, Teofilo | 40 | 880 | 92833
PR | 120 | 05/03/24 | 52 | Escalante Escobar, Boanerge | 40 | 1400 | 92839
PR | 120 | 05/03/24 | 53 | Escobar Ramirez, Carlos M | 40 | 800 | 92840
PR | 120 | 05/03/24 | 67 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92854
PR | 120 | 05/03/24 | 70 | Lopez, Maslin A | 40 | 1320 | 92857
PR | 120 | 05/03/24 | 74 | Martinez Garcia, Cesar B | 40 | 800 | 92861
PR | 120 | 05/03/24 | 77 | Melgar Moz, Brandon | 40 | 880 | 92864
PR | 120 | 05/03/24 | 78 | Mendoza Morales, Jesus A | 8 | 328 | 92865
PR | 120 | 05/03/24 | 83 | Ortiz Carmona, Juan M | 40 | 1280 | 92870
PR | 120 | 05/03/24 | 87 | Portillo Soriano, Walter A | 24 | 840 | 92874
PR | 120 | 05/03/24 | 88 | Puentez, Victor M | 40 | 880 | 92875
PR | 120 | 05/03/24 | 91 | Romero Garza, Jesus I | 32 | 1056 | 92878
PR | 120 | 05/03/24 | 93 | Suniga Aviles, Kelvin A | 16 | 336 | 92880
PR | 120 | 05/03/24 | 95 | Taylor, Evan R | 40 | 2080 | 92882
PR | 120 | 05/03/24 | 101 | Yohannes Jr., Samson | 40 | 1320 | 92888
PR | 120 | 05/03/24 | 103 | Zepeda Mendoza, Cesar | 40 | 880 | 92890
PR | 120 | 05/10/24 | 241 | Anderson, Richard P | 6 | 390 | 2814
PR | 120 | 05/10/24 | 242 | Barnhart, Joseph N | 2 | 136 | 2815
PR | 120 | 05/10/24 | 249 | Diaz Morales, Cristian A | 40 | 880 | 2836
PR | 120 | 05/10/24 | 250 | Galdamez, Dagoberto A | 40 | 1680 | 2821
PR | 120 | 05/10/24 | 255 | Nunez Bravo, Jose L | 36 | 828 | 2826
PR | 120 | 05/10/24 | 256 | Paco Leyva, Orlando | 22 | 1342 | 2827
PR | 120 | 05/10/24 | 259 | Storozhuk, Maxim A | 40 | 880 | 2830
PR | 120 | 05/10/24 | 261 | Weeks, Gregg A | 40 | 1920 | 2832
PR | 120 | 05/10/24 | 262 | Zamudio Sanchez, Jose R | 40 | 1920 | 2833
PR | 120 | 05/10/24 | 265 | Aquino, Juan | 40 | 1080 | 92836
PR | 120 | 05/10/24 | 268 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92839
PR | 120 | 05/10/24 | 271 | Boss, Benjamin T | 8 | 408 | 92842
PR | 120 | 05/10/24 | 273 | Carmona, Raul O | 40 | 2120 | 92844
PR | 120 | 05/10/24 | 274 | Castro Hernandez, Jose A | 32 | 1728 | 92845
PR | 120 | 05/10/24 | 283 | Diaz Morales, Guni | 40 | 880 | 92853
PR | 120 | 05/10/24 | 284 | Diaz Morales, Teofilo | 40 | 880 | 92854
PR | 120 | 05/10/24 | 290 | Escalante Escobar, Boanerge | 40 | 1400 | 92860
PR | 120 | 05/10/24 | 291 | Escobar Ramirez, Carlos M | 39 | 780 | 92861
PR | 120 | 05/10/24 | 297 | Gochez Molina, Douglas O | 40 | 1000 | 92867
PR | 120 | 05/10/24 | 299 | Gomez Aguirre, Exequiel | 40 | 960 | 92869
PR | 120 | 05/10/24 | 305 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92875
PR | 120 | 05/10/24 | 308 | Lopez, Maslin A | 31 | 1023 | 92878
PR | 120 | 05/10/24 | 312 | Martinez Garcia, Cesar B | 40 | 800 | 92882
PR | 120 | 05/10/24 | 315 | Melgar Moz, Brandon | 40 | 880 | 92885
PR | 120 | 05/10/24 | 321 | Ortiz Carmona, Juan M | 40 | 1280 | 92891
PR | 120 | 05/10/24 | 325 | Portillo Soriano, Walter A | 40 | 1400 | 92895
PR | 120 | 05/10/24 | 326 | Puentez, Victor M | 40 | 880 | 92896
PR | 120 | 05/10/24 | 329 | Romero Garza, Jesus I | 24 | 792 | 92899
PR | 120 | 05/10/24 | 333 | Taylor, Evan R | 40 | 2080 | 92903
PR | 120 | 05/10/24 | 339 | Yohannes Jr., Samson | 40 | 1320 | 92909
PR | 120 | 05/10/24 | 341 | Zepeda Mendoza, Cesar | 40 | 880 | 92911
PR | 120 | 05/17/24 | 469 | Anderson, Richard P | 35 | 2275 | 2837
PR | 120 | 05/17/24 | 470 | Barnhart, Joseph N | 6 | 408 | 2838
PR | 120 | 05/17/24 | 477 | Diaz Morales, Cristian A | 8 | 176 | 2845
PR | 120 | 05/17/24 | 478 | Galdamez, Dagoberto A | 40 | 1680 | 2846
PR | 120 | 05/17/24 | 483 | Nunez Bravo, Jose L | 40 | 920 | 2851
PR | 120 | 05/17/24 | 484 | Paco Leyva, Orlando | 22 | 1342 | 2852
PR | 120 | 05/17/24 | 487 | Storozhuk, Maxim A | 40 | 880 | 2855
PR | 120 | 05/17/24 | 489 | Weeks, Gregg A | 32 | 1536 | 2857
PR | 120 | 05/17/24 | 490 | Zamudio Sanchez, Jose R | 40 | 1920 | 2858
PR | 120 | 05/17/24 | 492 | Aquino, Juan | 40 | 1080 | 92860
PR | 120 | 05/17/24 | 494 | Ascencio, Jose L | 24 | 1008 | 92862
PR | 120 | 05/17/24 | 495 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92863
PR | 120 | 05/17/24 | 498 | Boss, Benjamin T | 24 | 1224 | 92866
PR | 120 | 05/17/24 | 500 | Carmona, Raul O | 40 | 2120 | 92868
PR | 120 | 05/17/24 | 501 | Castro Hernandez, Jose A | 40 | 2160 | 92869
PR | 120 | 05/17/24 | 510 | Diaz Morales, Guni | 8 | 176 | 92877
PR | 120 | 05/17/24 | 511 | Diaz Morales, Teofilo | 8 | 176 | 92878
PR | 120 | 05/17/24 | 517 | Escalante Escobar, Boanerge | 40 | 1400 | 92884
PR | 120 | 05/17/24 | 518 | Escobar Ramirez, Carlos M | 40 | 800 | 92885
PR | 120 | 05/17/24 | 524 | Gochez Molina, Douglas O | 40 | 1000 | 92891
PR | 120 | 05/17/24 | 526 | Gomez Aguirre, Exequiel | 40 | 960 | 92893
PR | 120 | 05/17/24 | 532 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92899
PR | 120 | 05/17/24 | 535 | Lopez, Maslin A | 40 | 1320 | 92902
PR | 120 | 05/17/24 | 539 | Martinez Garcia, Cesar B | 24 | 480 | 92906
PR | 120 | 05/17/24 | 542 | Melgar Moz, Brandon | 40 | 880 | 92909
PR | 120 | 05/17/24 | 548 | Ortiz Carmona, Juan M | 40 | 1280 | 92915
PR | 120 | 05/17/24 | 552 | Portillo Soriano, Walter A | 40 | 1400 | 92919
PR | 120 | 05/17/24 | 553 | Puentez, Victor M | 40 | 880 | 92920
PR | 120 | 05/17/24 | 556 | Romero Garza, Jesus I | 32 | 1056 | 92923
PR | 120 | 05/17/24 | 558 | Suniga Aviles, Kelvin A | 8 | 168 | 92925
PR | 120 | 05/17/24 | 560 | Taylor, Evan R | 40 | 2080 | 92927
PR | 120 | 05/17/24 | 566 | Yohannes Jr., Samson | 32 | 1056 | 92933
PR | 120 | 05/17/24 | 568 | Zepeda Mendoza, Cesar | 8 | 176 | 92935
PR | 120 | 05/17/24 | 569 | Zuniga Avilez, Eduar A | 8 | 160 | 92936
PR | 120 | 05/24/24 | 678 | Anderson, Richard P | 32 | 2080 | 2863
PR | 120 | 05/24/24 | 686 | Galdamez, Dagoberto A | 40 | 1680 | 2871
PR | 120 | 05/24/24 | 691 | Nunez Bravo, Jose L | 40 | 920 | 2876
PR | 120 | 05/24/24 | 692 | Paco Leyva, Orlando | 21 | 1281 | 2877
PR | 120 | 05/24/24 | 696 | Weeks, Gregg A | 37 | 1776 | 2881
PR | 120 | 05/24/24 | 697 | Zamudio Sanchez, Jose R | 28 | 1344 | 2882
PR | 120 | 05/24/24 | 699 | Aquino, Juan | 36 | 972 | 92884
PR | 120 | 05/24/24 | 701 | Ascencio, Jose L | 32 | 1344 | 92886
PR | 120 | 05/24/24 | 702 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92887
PR | 120 | 05/24/24 | 705 | Boss, Benjamin T | 40 | 2040 | 92890
PR | 120 | 05/24/24 | 707 | Carmona, Raul O | 40 | 2120 | 92892
PR | 120 | 05/24/24 | 708 | Castro Hernandez, Jose A | 40 | 2160 | 92893
PR | 120 | 05/24/24 | 722 | Escalante Escobar, Boanerge | 40 | 1400 | 92906
PR | 120 | 05/24/24 | 723 | Escobar Ramirez, Carlos M | 40 | 800 | 92907
PR | 120 | 05/24/24 | 731 | Gomez Aguirre, Exequiel | 24 | 576 | 92915
PR | 120 | 05/24/24 | 737 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92921
PR | 120 | 05/24/24 | 740 | Lopez, Maslin A | 37 | 1221 | 92924
PR | 120 | 05/24/24 | 744 | Martinez Garcia, Cesar B | 40 | 800 | 92928
PR | 120 | 05/24/24 | 747 | Melgar Moz, Brandon | 40 | 880 | 92931
PR | 120 | 05/24/24 | 752 | Ortiz Carmona, Juan M | 40 | 1280 | 92936
PR | 120 | 05/24/24 | 756 | Portillo Soriano, Walter A | 40 | 1400 | 92940
PR | 120 | 05/24/24 | 757 | Puentez, Victor M | 24 | 528 | 92941
PR | 120 | 05/24/24 | 760 | Romero Garza, Jesus I | 8 | 264 | 92944
PR | 120 | 05/24/24 | 762 | Storozhuk, Maxim A | 40 | 880 | 92946
PR | 120 | 05/24/24 | 763 | Suniga Aviles, Kelvin A | 40 | 840 | 92947
PR | 120 | 05/24/24 | 765 | Taylor, Evan R | 40 | 2080 | 92949
PR | 120 | 05/24/24 | 770 | Yohannes Jr., Samson | 37.5 | 1237.5 | 92954
PR | 120 | 05/24/24 | 772 | Zuniga Avilez, Eduar A | 32 | 640 | 92956
PR | 120 | 05/31/24 | 792 | Anderson, Richard P | 29 | 1885 | 2883
PR | 120 | 05/31/24 | 793 | Barnhart, Joseph N | 1 | 68 | 2884
PR | 120 | 05/31/24 | 800 | Galdamez, Dagoberto A | 32 | 1344 | 2891
PR | 120 | 05/31/24 | 805 | Nunez Bravo, Jose L | 32 | 736 | 2896
PR | 120 | 05/31/24 | 806 | Paco Leyva, Orlando | 9 | 549 | 2897
PR | 120 | 05/31/24 | 810 | Weeks, Gregg A | 24 | 1152 | 2901
PR | 120 | 05/31/24 | 811 | Zamudio Sanchez, Jose R | 22 | 1056 | 2902
PR | 120 | 05/31/24 | 813 | Aquino, Juan | 32 | 864 | 92904
PR | 120 | 05/31/24 | 815 | Ascencio, Jose L | 32 | 1344 | 92906
PR | 120 | 05/31/24 | 816 | Balderas Ortiz, Ricardo I | 32 | 1408 | 92907
PR | 120 | 05/31/24 | 819 | Boss, Benjamin T | 32 | 1632 | 92910
PR | 120 | 05/31/24 | 821 | Carmona, Raul O | 32 | 1696 | 92912
PR | 120 | 05/31/24 | 822 | Castro Hernandez, Jose A | 32 | 1728 | 92913
PR | 120 | 05/31/24 | 836 | Escalante Escobar, Boanerge | 32 | 1120 | 92926
PR | 120 | 05/31/24 | 837 | Escobar Ramirez, Carlos M | 32 | 640 | 92927
PR | 120 | 05/31/24 | 843 | Gochez Molina, Douglas O | 32 | 800 | 92933
PR | 120 | 05/31/24 | 845 | Gomez Aguirre, Exequiel | 32 | 768 | 92935
PR | 120 | 05/31/24 | 849 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 92939
PR | 120 | 05/31/24 | 851 | Lima Romero, Melvin A | 8 | 352 | 92941
PR | 120 | 05/31/24 | 852 | Lopez, Maslin A | 32 | 1056 | 92942
PR | 120 | 05/31/24 | 856 | Martinez Garcia, Cesar B | 32 | 640 | 92946
PR | 120 | 05/31/24 | 859 | Melgar Moz, Brandon | 32 | 704 | 92949
PR | 120 | 05/31/24 | 864 | Ortiz Carmona, Juan M | 32 | 1024 | 92954
PR | 120 | 05/31/24 | 868 | Portillo Soriano, Walter A | 32 | 1120 | 92958
PR | 120 | 05/31/24 | 869 | Puentez, Victor M | 32 | 704 | 92959
PR | 120 | 05/31/24 | 872 | Romero Garza, Jesus I | 8 | 264 | 92962
PR | 120 | 05/31/24 | 874 | Storozhuk, Maxim A | 32 | 704 | 92964
PR | 120 | 05/31/24 | 875 | Suniga Aviles, Kelvin A | 8 | 168 | 92965
PR | 120 | 05/31/24 | 877 | Taylor, Evan R | 32 | 1664 | 92967
PR | 120 | 05/31/24 | 882 | Yohannes Jr., Samson | 32 | 1056 | 92972
PR | 120 | 05/31/24 | 884 | Zuniga Avilez, Eduar A | 32 | 640 | 92974
PR | 120 | 06/07/24 | 80 | Anderson, Richard P | 16 | 1040 | 2904
PR | 120 | 06/07/24 | 81 | Barnhart, Joseph N | 2 | 136 | 2905
PR | 120 | 06/07/24 | 88 | Galdamez, Dagoberto A | 40 | 1680 | 2912
PR | 120 | 06/07/24 | 94 | Nunez Bravo, Jose L | 40 | 920 | 2918
PR | 120 | 06/07/24 | 95 | Paco Leyva, Orlando | 16 | 976 | 2919
PR | 120 | 06/07/24 | 98 | Weeks, Gregg A | 29 | 1392 | 2922
PR | 120 | 06/07/24 | 99 | Zamudio Sanchez, Jose R | 32 | 1536 | 2923
PR | 120 | 06/07/24 | 102 | Aquino, Juan | 40 | 1080 | 92925
PR | 120 | 06/07/24 | 104 | Ascencio, Jose L | 40 | 1680 | 92927
PR | 120 | 06/07/24 | 105 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92928
PR | 120 | 06/07/24 | 108 | Boss, Benjamin T | 24 | 1224 | 92931
PR | 120 | 06/07/24 | 110 | Carmona, Raul O | 40 | 2120 | 92933
PR | 120 | 06/07/24 | 111 | Castro Hernandez, Jose A | 40 | 2160 | 92934
PR | 120 | 06/07/24 | 125 | Escalante Escobar, Boanerge | 40 | 1400 | 92947
PR | 120 | 06/07/24 | 126 | Escobar Ramirez, Carlos M | 40 | 800 | 92948
PR | 120 | 06/07/24 | 132 | Gochez Molina, Douglas O | 40 | 1000 | 92954
PR | 120 | 06/07/24 | 134 | Gomez Aguirre, Exequiel | 32 | 768 | 92956
PR | 120 | 06/07/24 | 138 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92960
PR | 120 | 06/07/24 | 140 | Lima Romero, Melvin A | 40 | 1760 | 92962
PR | 120 | 06/07/24 | 141 | Lopez, Maslin A | 40 | 1320 | 92963
PR | 120 | 06/07/24 | 145 | Martinez Garcia, Cesar B | 40 | 800 | 92967
PR | 120 | 06/07/24 | 148 | Melgar Moz, Brandon | 40 | 880 | 92970
PR | 120 | 06/07/24 | 149 | Mendoza Morales, Jesus A | 8 | 328 | 92971
PR | 120 | 06/07/24 | 153 | Ortiz Carmona, Juan M | 40 | 1280 | 92975
PR | 120 | 06/07/24 | 157 | Portillo Soriano, Walter A | 40 | 1400 | 92979
PR | 120 | 06/07/24 | 158 | Puentez, Victor M | 40 | 880 | 92980
PR | 120 | 06/07/24 | 164 | Suniga Aviles, Kelvin A | 24 | 504 | 92986
PR | 120 | 06/07/24 | 166 | Taylor, Evan R | 40 | 2080 | 92988
PR | 120 | 06/14/24 | 304 | Anderson, Richard P | 25.5 | 1657.5 | 2924
PR | 120 | 06/14/24 | 311 | Galdamez, Dagoberto A | 40 | 1680 | 2931
PR | 120 | 06/14/24 | 317 | Nunez Bravo, Jose L | 40 | 920 | 2937
PR | 120 | 06/14/24 | 318 | Paco Leyva, Orlando | 18 | 1098 | 2938
PR | 120 | 06/14/24 | 321 | Weeks, Gregg A | 32 | 1536 | 2941
PR | 120 | 06/14/24 | 322 | Zamudio Sanchez, Jose R | 19 | 912 | 2942
PR | 120 | 06/14/24 | 324 | Aquino, Juan | 16 | 432 | 92944
PR | 120 | 06/14/24 | 326 | Ascencio, Jose L | 40 | 1680 | 92946
PR | 120 | 06/14/24 | 327 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92947
PR | 120 | 06/14/24 | 330 | Boss, Benjamin T | 24 | 1224 | 92950
PR | 120 | 06/14/24 | 332 | Carmona, Raul O | 40 | 2120 | 92952
PR | 120 | 06/14/24 | 333 | Castro Hernandez, Jose A | 40 | 2160 | 92953
PR | 120 | 06/14/24 | 348 | Escalante Escobar, Boanerge | 40 | 1400 | 92967
PR | 120 | 06/14/24 | 349 | Escobar Ramirez, Carlos M | 40 | 800 | 92968
PR | 120 | 06/14/24 | 355 | Gochez Molina, Douglas O | 40 | 1000 | 92974
PR | 120 | 06/14/24 | 357 | Gomez Aguirre, Exequiel | 40 | 960 | 92976
PR | 120 | 06/14/24 | 361 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 92980
PR | 120 | 06/14/24 | 363 | Lima Romero, Melvin A | 8 | 352 | 92982
PR | 120 | 06/14/24 | 364 | Lopez, Maslin A | 30 | 990 | 92983
PR | 120 | 06/14/24 | 368 | Martinez Garcia, Cesar B | 40 | 800 | 92987
PR | 120 | 06/14/24 | 371 | Melgar Moz, Brandon | 40 | 880 | 92990
PR | 120 | 06/14/24 | 372 | Mendoza Morales, Jesus A | 8 | 328 | 92991
PR | 120 | 06/14/24 | 376 | Ortiz Carmona, Juan M | 40 | 1280 | 92995
PR | 120 | 06/14/24 | 380 | Portillo Soriano, Walter A | 40 | 1400 | 92999
PR | 120 | 06/14/24 | 381 | Puentez, Victor M | 40 | 880 | 93000
PR | 120 | 06/14/24 | 387 | Suniga Aviles, Kelvin A | 40 | 840 | 93006
PR | 120 | 06/14/24 | 389 | Taylor, Evan R | 16 | 832 | 93008
PR | 120 | 06/14/24 | 394 | Yohannes Jr., Samson | 16 | 528 | 93013
PR | 120 | 06/14/24 | 396 | Zuniga Avilez, Eduar A | 40 | 800 | 93015
PR | 120 | 06/21/24 | 479 | Anderson, Richard P | 3 | 195 | 2943
PR | 120 | 06/21/24 | 480 | Barnhart, Joseph N | 2 | 136 | 2944
PR | 120 | 06/21/24 | 486 | Galdamez, Dagoberto A | 40 | 1680 | 2950
PR | 120 | 06/21/24 | 491 | Paco Leyva, Orlando | 20 | 1220 | 2955
PR | 120 | 06/21/24 | 494 | Weeks, Gregg A | 32 | 1536 | 2958
PR | 120 | 06/21/24 | 496 | Aquino, Juan | 16 | 432 | 92960
PR | 120 | 06/21/24 | 499 | Balderas Ortiz, Ricardo I | 39 | 1716 | 92963
PR | 120 | 06/21/24 | 502 | Boss, Benjamin T | 24 | 1224 | 92966
PR | 120 | 06/21/24 | 504 | Carmona, Raul O | 32 | 1696 | 92968
PR | 120 | 06/21/24 | 505 | Castro Hernandez, Jose A | 40 | 2160 | 92969
PR | 120 | 06/21/24 | 520 | Escalante Escobar, Boanerge | 40 | 1400 | 92983
PR | 120 | 06/21/24 | 521 | Escobar Ramirez, Carlos M | 40 | 800 | 92984
PR | 120 | 06/21/24 | 527 | Gochez Molina, Douglas O | 40 | 1000 | 92990
PR | 120 | 06/21/24 | 532 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 92995
PR | 120 | 06/21/24 | 534 | Lima Romero, Melvin A | 16 | 704 | 92997
PR | 120 | 06/21/24 | 535 | Lopez, Maslin A | 40 | 1320 | 92998
PR | 120 | 06/21/24 | 541 | Melgar Moz, Brandon | 32 | 704 | 93004
PR | 120 | 06/21/24 | 542 | Mendoza Morales, Jesus A | 16 | 656 | 93005
PR | 120 | 06/21/24 | 546 | Ortiz Carmona, Juan M | 32 | 1024 | 93009
PR | 120 | 06/21/24 | 549 | Portillo Soriano, Walter A | 32 | 1120 | 93012
PR | 120 | 06/21/24 | 555 | Suniga Aviles, Kelvin A | 32 | 672 | 93018
PR | 120 | 06/21/24 | 557 | Taylor, Evan R | 24 | 1248 | 93020
PR | 120 | 06/21/24 | 562 | Yohannes Jr., Samson | 16 | 528 | 93025
PR | 120 | 06/21/24 | 564 | Zuniga Avilez, Eduar A | 32 | 640 | 93027
PR | 120 | 06/28/24 | 686 | Anderson, Richard P | 9.5 | 617.5 | 2959
PR | 120 | 06/28/24 | 687 | Barnhart, Joseph N | 4 | 272 | 2960
PR | 120 | 06/28/24 | 693 | Galdamez, Dagoberto A | 32 | 1344 | 2966
PR | 120 | 06/28/24 | 698 | Paco Leyva, Orlando | 29 | 1769 | 2971
PR | 120 | 06/28/24 | 701 | Weeks, Gregg A | 24 | 1152 | 2974
PR | 120 | 06/28/24 | 706 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92979
PR | 120 | 06/28/24 | 709 | Boss, Benjamin T | 16 | 816 | 92982
PR | 120 | 06/28/24 | 711 | Carmona, Raul O | 32 | 1696 | 92984
PR | 120 | 06/28/24 | 712 | Castro Hernandez, Jose A | 32 | 1728 | 92985
PR | 120 | 06/28/24 | 727 | Escalante Escobar, Boanerge | 24 | 840 | 92999
PR | 120 | 06/28/24 | 728 | Escobar Ramirez, Carlos M | 32 | 640 | 93000
PR | 120 | 06/28/24 | 734 | Gochez Molina, Douglas O | 24 | 600 | 93006
PR | 120 | 06/28/24 | 739 | Jimenez Alvarenga, Gerson M | 24 | 936 | 93011
PR | 120 | 06/28/24 | 741 | Lima Romero, Melvin A | 16 | 704 | 93013
PR | 120 | 06/28/24 | 742 | Lopez, Maslin A | 24 | 792 | 93014
PR | 120 | 06/28/24 | 749 | Mendoza Morales, Jesus A | 8 | 328 | 93021
PR | 120 | 06/28/24 | 753 | Ortiz Carmona, Juan M | 24 | 768 | 93025
PR | 120 | 06/28/24 | 762 | Suniga Aviles, Kelvin A | 24 | 504 | 93034
PR | 120 | 06/28/24 | 769 | Yohannes Jr., Samson | 16 | 528 | 93041
PR | 120 | 06/28/24 | 771 | Zuniga Avilez, Eduar A | 32 | 640 | 93043
PR | 120 | 07/05/24 | 3 | Anderson, Richard P | 12 | 780 | 2975
PR | 120 | 07/05/24 | 10 | Galdamez, Dagoberto A | 32 | 1344 | 2982
PR | 120 | 07/05/24 | 14 | Paco Leyva, Orlando | 17 | 1037 | 2986
PR | 120 | 07/05/24 | 17 | Weeks, Gregg A | 32 | 1536 | 2989
PR | 120 | 07/05/24 | 21 | Ascencio, Jose L | 8 | 336 | 92993
PR | 120 | 07/05/24 | 22 | Balderas Ortiz, Ricardo I | 40 | 1760 | 92994
PR | 120 | 07/05/24 | 25 | Boss, Benjamin T | 32 | 1632 | 92997
PR | 120 | 07/05/24 | 27 | Carmona, Raul O | 32 | 1696 | 92999
PR | 120 | 07/05/24 | 28 | Castro Hernandez, Jose A | 32 | 1728 | 93000
PR | 120 | 07/05/24 | 41 | Escalante Escobar, Boanerge | 32 | 1120 | 93013
PR | 120 | 07/05/24 | 42 | Escobar Ramirez, Carlos M | 16 | 320 | 93014
PR | 120 | 07/05/24 | 48 | Gochez Molina, Douglas O | 32 | 800 | 93020
PR | 120 | 07/05/24 | 52 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 93024
PR | 120 | 07/05/24 | 54 | Lima Romero, Melvin A | 32 | 1408 | 93026
PR | 120 | 07/05/24 | 55 | Lopez, Maslin A | 16 | 528 | 93027
PR | 120 | 07/05/24 | 61 | Mendoza Morales, Jesus A | 24 | 984 | 93033
PR | 120 | 07/05/24 | 65 | Ortiz Carmona, Juan M | 40 | 1280 | 93037
PR | 120 | 07/05/24 | 74 | Suniga Aviles, Kelvin A | 16 | 336 | 93046
PR | 120 | 07/05/24 | 76 | Taylor, Evan R | 8 | 416 | 93048
PR | 120 | 07/05/24 | 81 | Yohannes Jr., Samson | 16 | 528 | 93053
PR | 120 | 07/05/24 | 83 | Zuniga Avilez, Eduar A | 16 | 320 | 93055
PR | 120 | 07/12/24 | 166 | Anderson, Richard P | 4.5 | 292.5 | 2990
PR | 120 | 07/12/24 | 167 | Barnhart, Joseph N | 2.5 | 170 | 2991
PR | 120 | 07/12/24 | 173 | Galdamez, Dagoberto A | 24 | 1008 | 2997
PR | 120 | 07/12/24 | 176 | Paco Leyva, Orlando | 12 | 732 | 3000
PR | 120 | 07/12/24 | 179 | Weeks, Gregg A | 24 | 1152 | 3003
PR | 120 | 07/12/24 | 184 | Balderas Ortiz, Ricardo I | 24 | 1056 | 93008
PR | 120 | 07/12/24 | 187 | Boss, Benjamin T | 24 | 1224 | 93011
PR | 120 | 07/12/24 | 189 | Carmona, Raul O | 24 | 1272 | 93013
PR | 120 | 07/12/24 | 190 | Castro Hernandez, Jose A | 24 | 1296 | 93014
PR | 120 | 07/12/24 | 204 | Escobar Ramirez, Carlos M | 16 | 320 | 93028
PR | 120 | 07/12/24 | 210 | Gochez Molina, Douglas O | 8 | 200 | 93034
PR | 120 | 07/12/24 | 215 | Jimenez Alvarenga, Gerson M | 16 | 624 | 93039
PR | 120 | 07/12/24 | 218 | Lopez, Maslin A | 24 | 792 | 93042
PR | 120 | 07/12/24 | 224 | Mendoza Morales, Jesus A | 8 | 328 | 93048
PR | 120 | 07/12/24 | 236 | Suniga Aviles, Kelvin A | 16 | 336 | 93060
PR | 120 | 07/12/24 | 245 | Zuniga Avilez, Eduar A | 24 | 480 | 93069
PR | 120 | 07/19/24 | 374 | Anderson, Richard P | 5 | 325 | 3004
PR | 120 | 07/19/24 | 380 | Galdamez, Dagoberto A | 32 | 1344 | 3010
PR | 120 | 07/19/24 | 389 | Balderas Ortiz, Ricardo I | 40 | 1760 | 93019
PR | 120 | 07/19/24 | 390 | Barnhart, Joseph N | 1 | 68 | 93020
PR | 120 | 07/19/24 | 393 | Boss, Benjamin T | 24 | 1224 | 93023
PR | 120 | 07/19/24 | 395 | Carmona, Raul O | 40 | 2120 | 93025
PR | 120 | 07/19/24 | 396 | Castro Hernandez, Jose A | 32 | 1728 | 93026
PR | 120 | 07/19/24 | 409 | Escalante Escobar, Boanerge | 32 | 1120 | 93039
PR | 120 | 07/19/24 | 410 | Escobar Ramirez, Carlos M | 16 | 320 | 93040
PR | 120 | 07/19/24 | 416 | Gochez Molina, Douglas O | 32 | 800 | 93046
PR | 120 | 07/19/24 | 421 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 93051
PR | 120 | 07/19/24 | 423 | Lima Romero, Melvin A | 8 | 352 | 93053
PR | 120 | 07/19/24 | 424 | Lopez, Maslin A | 16 | 528 | 93054
PR | 120 | 07/19/24 | 430 | Mendoza Morales, Jesus A | 16 | 656 | 93060
PR | 120 | 07/19/24 | 443 | Suniga Aviles, Kelvin A | 24 | 504 | 93073
PR | 120 | 07/19/24 | 449 | Weeks, Gregg A | 24 | 1152 | 93079
PR | 120 | 07/19/24 | 453 | Zuniga Avilez, Eduar A | 16 | 320 | 93083
PR | 120 | 07/26/24 | 563 | Anderson, Richard P | 15.5 | 1007.5 | 3015
PR | 120 | 07/26/24 | 569 | Galdamez, Dagoberto A | 32 | 1344 | 3021
PR | 120 | 07/26/24 | 571 | Paco Leyva, Orlando | 11 | 671 | 3023
PR | 120 | 07/26/24 | 577 | Balderas Ortiz, Ricardo I | 32 | 1408 | 93029
PR | 120 | 07/26/24 | 581 | Boss, Benjamin T | 32 | 1632 | 93033
PR | 120 | 07/26/24 | 583 | Carmona, Raul O | 24 | 1272 | 93035
PR | 120 | 07/26/24 | 584 | Castro Hernandez, Jose A | 32 | 1728 | 93036
PR | 120 | 07/26/24 | 597 | Escalante Escobar, Boanerge | 32 | 1120 | 93049
PR | 120 | 07/26/24 | 598 | Escobar Ramirez, Carlos M | 12 | 240 | 93050
PR | 120 | 07/26/24 | 603 | Gochez Molina, Douglas O | 32 | 800 | 93055
PR | 120 | 07/26/24 | 608 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 93060
PR | 120 | 07/26/24 | 610 | Lima Romero, Melvin A | 24 | 1056 | 93062
PR | 120 | 07/26/24 | 611 | Lopez, Maslin A | 32 | 1056 | 93063
PR | 120 | 07/26/24 | 617 | Mendoza Morales, Jesus A | 8 | 328 | 93069
PR | 120 | 07/26/24 | 630 | Suniga Aviles, Kelvin A | 24 | 504 | 93082
PR | 120 | 07/26/24 | 636 | Weeks, Gregg A | 32 | 1536 | 93088
PR | 120 | 07/26/24 | 640 | Zuniga Avilez, Eduar A | 20 | 400 | 93092
PR | 120 | 08/02/24 | 9 | Galdamez, Dagoberto A | 32 | 1344 | 3032
PR | 120 | 08/02/24 | 11 | Paco Leyva, Orlando | 16 | 976 | 3034
PR | 120 | 08/02/24 | 17 | Balderas Ortiz, Ricardo I | 40 | 1760 | 93040
PR | 120 | 08/02/24 | 18 | Barnhart, Joseph N | 1 | 68 | 93041
PR | 120 | 08/02/24 | 21 | Boss, Benjamin T | 32 | 1632 | 93044
PR | 120 | 08/02/24 | 23 | Carmona, Raul O | 40 | 2120 | 93046
PR | 120 | 08/02/24 | 24 | Castro Hernandez, Jose A | 32 | 1728 | 93047
PR | 120 | 08/02/24 | 37 | Escalante Escobar, Boanerge | 8 | 280 | 93060
PR | 120 | 08/02/24 | 38 | Escobar Ramirez, Carlos M | 8 | 160 | 93061
PR | 120 | 08/02/24 | 43 | Gochez Molina, Douglas O | 32 | 800 | 93066
PR | 120 | 08/02/24 | 48 | Jimenez Alvarenga, Gerson M | 8 | 312 | 93071
PR | 120 | 08/02/24 | 50 | Lima Romero, Melvin A | 16 | 704 | 93073
PR | 120 | 08/02/24 | 51 | Lopez, Maslin A | 16 | 528 | 93074
PR | 120 | 08/02/24 | 57 | Mendoza Morales, Jesus A | 16 | 656 | 93080
PR | 120 | 08/02/24 | 70 | Suniga Aviles, Kelvin A | 32 | 672 | 93093
PR | 120 | 08/02/24 | 76 | Weeks, Gregg A | 32 | 1536 | 93099
PR | 120 | 08/02/24 | 80 | Zuniga Avilez, Eduar A | 12 | 240 | 93103
PR | 120 | 08/09/24 | 244 | Galdamez, Dagoberto A | 32 | 1344 | 3044
PR | 120 | 08/09/24 | 246 | Paco Leyva, Orlando | 13 | 793 | 3046
PR | 120 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I | 32 | 1408 | 23052
PR | 120 | 08/09/24 | 256 | Boss, Benjamin T | 24 | 1224 | 23056
PR | 120 | 08/09/24 | 258 | Carmona, Raul O | 32 | 1696 | 23058
PR | 120 | 08/09/24 | 259 | Castro Hernandez, Jose A | 40 | 2160 | 23059
PR | 120 | 08/09/24 | 272 | Escobar Ramirez, Carlos M | 32 | 640 | 23072
PR | 120 | 08/09/24 | 277 | Gochez Molina, Douglas O | 32 | 800 | 23077
PR | 120 | 08/09/24 | 284 | Lima Romero, Melvin A | 8 | 352 | 23084
PR | 120 | 08/09/24 | 285 | Lopez, Maslin A | 40 | 1320 | 23085
PR | 120 | 08/09/24 | 291 | Mendoza Morales, Jesus A | 8 | 328 | 23091
PR | 120 | 08/09/24 | 304 | Suniga Aviles, Kelvin A | 16 | 336 | 23104
PR | 120 | 08/09/24 | 310 | Weeks, Gregg A | 32 | 1536 | 23110
PR | 120 | 08/09/24 | 314 | Zuniga Avilez, Eduar A | 16 | 320 | 23114
PR | 120 | 08/16/24 | 428 | Anderson, Richard P | 5 | 325 | 3048
PR | 120 | 08/16/24 | 435 | Galdamez, Dagoberto A | 24 | 1008 | 3055
PR | 120 | 08/16/24 | 437 | Paco Leyva, Orlando | 16 | 976 | 3057
PR | 120 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I | 8 | 352 | 33063
PR | 120 | 08/16/24 | 444 | Barnhart, Joseph N | 3 | 204 | 33064
PR | 120 | 08/16/24 | 447 | Boss, Benjamin T | 8 | 408 | 33067
PR | 120 | 08/16/24 | 449 | Carmona, Raul O | 32 | 1696 | 33069
PR | 120 | 08/16/24 | 450 | Castro Hernandez, Jose A | 24 | 1296 | 33070
PR | 120 | 08/16/24 | 461 | Escobar Ramirez, Carlos M | 16 | 320 | 33081
PR | 120 | 08/16/24 | 466 | Gochez Molina, Douglas O | 40 | 1000 | 33086
PR | 120 | 08/16/24 | 473 | Lima Romero, Melvin A | 8 | 352 | 33093
PR | 120 | 08/16/24 | 474 | Lopez, Maslin A | 24 | 792 | 33094
PR | 120 | 08/16/24 | 480 | Mendoza Morales, Jesus A | 24 | 984 | 33100
PR | 120 | 08/16/24 | 492 | Silva Morales, Jair J | 16 | 544 | 33112
PR | 120 | 08/16/24 | 493 | Suniga Aviles, Kelvin A | 40 | 840 | 33113
PR | 120 | 08/16/24 | 499 | Weeks, Gregg A | 40 | 1920 | 33119
PR | 120 | 08/16/24 | 501 | Yohannes Jr., Samson | 16 | 528 | 33121
PR | 120 | 08/16/24 | 503 | Zuniga Avilez, Eduar A | 40 | 800 | 33123
PR | 120 | 08/23/24 | 690 | Anderson, Richard P | 10.5 | 682.5 | 3059
PR | 120 | 08/23/24 | 697 | Galdamez, Dagoberto A | 40 | 1680 | 3066
PR | 120 | 08/23/24 | 699 | Paco Leyva, Orlando | 19 | 1159 | 3068
PR | 120 | 08/23/24 | 709 | Boss, Benjamin T | 8 | 408 | 43078
PR | 120 | 08/23/24 | 711 | Carmona, Raul O | 16 | 848 | 43080
PR | 120 | 08/23/24 | 723 | Escobar Ramirez, Carlos M | 24 | 480 | 43092
PR | 120 | 08/23/24 | 728 | Gochez Molina, Douglas O | 40 | 1000 | 43097
PR | 120 | 08/23/24 | 735 | Lima Romero, Melvin A | 40 | 1760 | 43104
PR | 120 | 08/23/24 | 736 | Lopez, Maslin A | 16 | 528 | 43105
PR | 120 | 08/23/24 | 755 | Suniga Aviles, Kelvin A | 16 | 336 | 43124
PR | 120 | 08/23/24 | 761 | Weeks, Gregg A | 16 | 768 | 43130
PR | 120 | 08/23/24 | 765 | Zuniga Avilez, Eduar A | 8 | 160 | 43134
PR | 120 | 08/30/24 | 833 | Anderson, Richard P | 13 | 845 | 3078
PR | 120 | 08/30/24 | 840 | Galdamez, Dagoberto A | 40 | 1680 | 3085
PR | 120 | 08/30/24 | 842 | Paco Leyva, Orlando | 17 | 1037 | 3087
PR | 120 | 08/30/24 | 854 | Carmona, Raul O | 8 | 424 | 53099
PR | 120 | 08/30/24 | 865 | Escobar Ramirez, Carlos M | 16 | 320 | 53110
PR | 120 | 08/30/24 | 870 | Gochez Molina, Douglas O | 32 | 800 | 53115
PR | 120 | 08/30/24 | 878 | Lopez, Maslin A | 24 | 792 | 53123
PR | 120 | 08/30/24 | 884 | Mendoza Morales, Jesus A | 32 | 1312 | 53129
PR | 120 | 08/30/24 | 897 | Suniga Aviles, Kelvin A | 32 | 672 | 53142
PR | 120 | 08/30/24 | 903 | Weeks, Gregg A | 24 | 1152 | 53148
PR | 120 | 08/30/24 | 907 | Zuniga Avilez, Eduar A | 24 | 480 | 53152
PR | 120 | 09/06/24 | 9 | Anderson, Richard P | 2 | 130 | 3089
PR | 120 | 09/06/24 | 16 | Galdamez, Dagoberto A | 24 | 1008 | 3096
PR | 120 | 09/06/24 | 18 | Paco Leyva, Orlando | 9 | 549 | 3098
PR | 120 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I | 8 | 352 | 13104
PR | 120 | 09/06/24 | 25 | Barnhart, Joseph N | 1 | 68 | 13105
PR | 120 | 09/06/24 | 28 | Boss, Benjamin T | 8 | 408 | 13108
PR | 120 | 09/06/24 | 30 | Carmona, Raul O | 16 | 848 | 13110
PR | 120 | 09/06/24 | 31 | Castro Hernandez, Jose A | 32 | 1728 | 13111
PR | 120 | 09/06/24 | 41 | Escobar Ramirez, Carlos M | 16 | 320 | 13121
PR | 120 | 09/06/24 | 47 | Gochez Molina, Douglas O | 24 | 600 | 13127
PR | 120 | 09/06/24 | 55 | Lopez, Maslin A | 24 | 792 | 13135
PR | 120 | 09/06/24 | 74 | Suniga Aviles, Kelvin A | 24 | 504 | 13154
PR | 120 | 09/06/24 | 80 | Weeks, Gregg A | 24 | 1152 | 13160
PR | 120 | 09/06/24 | 84 | Zuniga Avilez, Eduar A | 8 | 160 | 13164
PR | 120 | 09/13/24 | 217 | Anderson, Richard P | 4.5 | 292.5 | 3100
PR | 120 | 09/13/24 | 224 | Galdamez, Dagoberto A | 32 | 1344 | 3107
PR | 120 | 09/13/24 | 226 | Paco Leyva, Orlando | 17 | 1037 | 3109
PR | 120 | 09/13/24 | 233 | Barnhart, Joseph N | 1 | 68 | 23116
PR | 120 | 09/13/24 | 238 | Carmona, Raul O | 32 | 1696 | 23121
PR | 120 | 09/13/24 | 239 | Castro Hernandez, Jose A | 24 | 1296 | 23122
PR | 120 | 09/13/24 | 249 | Escobar Ramirez, Carlos M | 24 | 480 | 23132
PR | 120 | 09/13/24 | 255 | Gochez Molina, Douglas O | 12 | 300 | 23138
PR | 120 | 09/13/24 | 263 | Lopez, Maslin A | 39 | 1287 | 23146
PR | 120 | 09/13/24 | 281 | Suniga Aviles, Kelvin A | 10 | 210 | 23164
PR | 120 | 09/13/24 | 287 | Weeks, Gregg A | 8 | 384 | 23170
PR | 120 | 09/20/24 | 389 | Anderson, Richard P | 5 | 325 | 3113
PR | 120 | 09/20/24 | 396 | Galdamez, Dagoberto A | 32 | 1344 | 3120
PR | 120 | 09/20/24 | 398 | Paco Leyva, Orlando | 13 | 793 | 3122
PR | 120 | 09/20/24 | 405 | Barnhart, Joseph N | 1 | 68 | 33129
PR | 120 | 09/20/24 | 410 | Carmona, Raul O | 16 | 848 | 33134
PR | 120 | 09/20/24 | 411 | Castro Hernandez, Jose A | 8 | 432 | 33135
PR | 120 | 09/20/24 | 421 | Escobar Ramirez, Carlos M | 8 | 160 | 33145
PR | 120 | 09/20/24 | 433 | Lima Romero, Melvin A | 12 | 528 | 33157
PR | 120 | 09/20/24 | 434 | Lopez, Maslin A | 24 | 792 | 33158
PR | 120 | 09/20/24 | 452 | Suniga Aviles, Kelvin A | 8 | 168 | 33176
PR | 120 | 09/20/24 | 462 | Zuniga Avilez, Eduar A | 16 | 320 | 33186
PR | 120 | 09/27/24 | 525 | Anderson, Richard P | 2 | 130 | 3124
PR | 120 | 09/27/24 | 532 | Galdamez, Dagoberto A | 40 | 1680 | 3131
PR | 120 | 09/27/24 | 535 | Paco Leyva, Orlando | 18 | 1098 | 3134
PR | 120 | 09/27/24 | 546 | Carmona, Raul O | 16 | 848 | 43145
PR | 120 | 09/27/24 | 557 | Escobar Ramirez, Carlos M | 32 | 640 | 43156
PR | 120 | 09/27/24 | 570 | Lopez, Maslin A | 24 | 792 | 43169
PR | 120 | 09/27/24 | 575 | Mendoza Morales, Jesus A | 8 | 328 | 43174
PR | 120 | 09/27/24 | 588 | Suniga Aviles, Kelvin A | 20 | 420 | 43187
PR | 120 | 09/27/24 | 598 | Zuniga Avilez, Eduar A | 8 | 160 | 43197
PR | 120 | 10/04/24 | 9 | Anderson, Richard P | 2 | 130 | 3138
PR | 120 | 10/04/24 | 16 | Galdamez, Dagoberto A | 40 | 1680 | 3145
PR | 120 | 10/04/24 | 19 | Paco Leyva, Orlando | 12 | 732 | 3148
PR | 120 | 10/04/24 | 26 | Barnhart, Joseph N | 2 | 136 | 13155
PR | 120 | 10/04/24 | 30 | Carmona, Raul O | 32 | 1696 | 13159
PR | 120 | 10/04/24 | 41 | Escobar Ramirez, Carlos M | 32 | 640 | 13170
PR | 120 | 10/04/24 | 54 | Lopez, Maslin A | 24 | 792 | 13183
PR | 120 | 10/04/24 | 59 | Mendoza Morales, Jesus A | 16 | 656 | 13188
PR | 120 | 10/11/24 | 216 | Anderson, Richard P | 3 | 195 | 3150
PR | 120 | 10/11/24 | 223 | Galdamez, Dagoberto A | 32 | 1344 | 3157
PR | 120 | 10/11/24 | 226 | Paco Leyva, Orlando | 14 | 854 | 3160
PR | 120 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I | 8 | 352 | 23166
PR | 120 | 10/11/24 | 233 | Barnhart, Joseph N | 2 | 136 | 23167
PR | 120 | 10/11/24 | 237 | Carmona, Raul O | 8 | 424 | 23171
PR | 120 | 10/11/24 | 248 | Escobar Ramirez, Carlos M | 8 | 160 | 23182
PR | 120 | 10/11/24 | 260 | Lima Romero, Melvin A | 8 | 352 | 23194
PR | 120 | 10/11/24 | 261 | Lopez, Maslin A | 24 | 792 | 23195
PR | 120 | 10/11/24 | 266 | Mendoza Morales, Jesus A | 16 | 656 | 23200
PR | 120 | 10/18/24 | 429 | Anderson, Richard P | 2 | 130 | 3162
PR | 120 | 10/18/24 | 436 | Galdamez, Dagoberto A | 40 | 1680 | 3169
PR | 120 | 10/18/24 | 439 | Paco Leyva, Orlando | 12 | 732 | 3172
PR | 120 | 10/18/24 | 446 | Barnhart, Joseph N | 2 | 136 | 33179
PR | 120 | 10/18/24 | 450 | Carmona, Raul O | 4 | 212 | 33183
PR | 120 | 10/18/24 | 472 | Lopez, Maslin A | 32 | 1056 | 33205
PR | 120 | 10/18/24 | 477 | Mendoza Morales, Jesus A | 4 | 164 | 33210
PR | 120 | 10/25/24 | 577 | Anderson, Richard P | 18 | 1170 | 3174
PR | 120 | 10/25/24 | 584 | Galdamez, Dagoberto A | 27 | 1134 | 3181
PR | 120 | 10/25/24 | 587 | Paco Leyva, Orlando | 25 | 1525 | 3184
PR | 120 | 10/25/24 | 594 | Barnhart, Joseph N | 2.5 | 170 | 43191
PR | 120 | 10/25/24 | 597 | Carmona, Raul O | 20 | 1060 | 43194
PR | 120 | 10/25/24 | 619 | Lopez, Maslin A | 16 | 528 | 43216
PR | 120 | 11/01/24 | 6 | Anderson, Richard P | 16 | 1040 | 3186
PR | 120 | 11/01/24 | 13 | Galdamez, Dagoberto A | 16 | 672 | 3193
PR | 120 | 11/01/24 | 16 | Paco Leyva, Orlando | 17 | 1037 | 3196
PR | 120 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I | 16 | 704 | 13202
PR | 120 | 11/01/24 | 23 | Barnhart, Joseph N | 2 | 136 | 13203
PR | 120 | 11/01/24 | 26 | Carmona, Raul O | 24 | 1272 | 13206
PR | 120 | 11/01/24 | 48 | Lopez, Maslin A | 24 | 792 | 13228
PR | 120 | 11/01/24 | 53 | Mendoza Morales, Jesus A | 16 | 656 | 13233
PR | 120 | 11/08/24 | 126 | Anderson, Richard P | 2 | 130 | 3198
PR | 120 | 11/08/24 | 133 | Galdamez, Dagoberto A | 24 | 1008 | 3205
PR | 120 | 11/08/24 | 136 | Paco Leyva, Orlando | 18 | 1098 | 3208
PR | 120 | 11/08/24 | 146 | Carmona, Raul O | 16 | 848 | 23218
PR | 120 | 11/08/24 | 169 | Lopez, Maslin A | 24 | 792 | 23241
PR | 120 | 11/15/24 | 346 | Anderson, Richard P | 3 | 195 | 3210
PR | 120 | 11/15/24 | 353 | Galdamez, Dagoberto A | 8 | 336 | 3217
PR | 120 | 11/15/24 | 356 | Paco Leyva, Orlando | 11 | 671 | 3220
PR | 120 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I | 16 | 704 | 33226
PR | 120 | 11/15/24 | 366 | Carmona, Raul O | 8 | 424 | 33230
PR | 120 | 11/15/24 | 388 | Lima Romero, Melvin A | 16 | 704 | 33252
PR | 120 | 11/15/24 | 389 | Lopez, Maslin A | 16 | 528 | 33253
PR | 120 | 11/22/24 | 501 | Anderson, Richard P | 5 | 325 | 3223
PR | 120 | 11/22/24 | 508 | Galdamez, Dagoberto A | 8 | 336 | 3230
PR | 120 | 11/22/24 | 511 | Paco Leyva, Orlando | 12 | 732 | 3233
PR | 120 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I | 8 | 352 | 43239
PR | 120 | 11/22/24 | 518 | Barnhart, Joseph N | 2 | 136 | 43240
PR | 120 | 11/22/24 | 521 | Carmona, Raul O | 16 | 848 | 43243
PR | 120 | 11/22/24 | 543 | Lima Romero, Melvin A | 8 | 352 | 43265
PR | 120 | 11/22/24 | 544 | Lopez, Maslin A | 16 | 528 | 43266
PR | 120 | 11/29/24 | 649 | Anderson, Richard P | 1.5 | 97.5 | 3235
PR | 120 | 11/29/24 | 659 | Paco Leyva, Orlando | 8 | 488 | 3245
PR | 120 | 11/29/24 | 666 | Barnhart, Joseph N | 2 | 136 | 53252
PR | 120 | 11/29/24 | 669 | Carmona, Raul O | 8 | 424 | 53255
PR | 120 | 11/29/24 | 691 | Lima Romero, Melvin A | 4 | 176 | 53277
PR | 120 | 12/06/24 | 51 | Anderson, Richard P | 2 | 130 | 3247
PR | 120 | 12/06/24 | 58 | Galdamez, Dagoberto A | 4 | 168 | 3254
PR | 120 | 12/06/24 | 61 | Paco Leyva, Orlando | 4 | 244 | 3257
PR | 120 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I | 4 | 176 | 13263
PR | 120 | 12/06/24 | 71 | Carmona, Raul O | 8 | 424 | 13267
PR | 120 | 12/13/24 | 235 | Anderson, Richard P | 2 | 130 | 3270
PR | 120 | 12/13/24 | 243 | Paco Leyva, Orlando | 2 | 122 | 3278
PR | 120 | 12/13/24 | 253 | Carmona, Raul O | 8 | 424 | 23288
PR | 120 | 01/10/25 | 174 | Anderson, Richard P | 0.5 | 32.5 | 3312
PR | 120 | 01/10/25 | 174 | Anderson, Richard P | 6.5 | 422.5 | 3312
PR | 120 | 01/24/25 | 520 | Barnhart, Joseph N | 1 | 68 | 43350
PR | 120 | 01/24/25 | 551 | Paco Leyva, Orlando | 4 | 244 | 43381
PR | 120 | 02/07/25 | 42 | Barnhart, Joseph N | 1 | 68 | 13369
PR | 120 | 02/14/25 | 194 | Anderson, Richard P | 2 | 130 | 3364
PR | 120 | 02/14/25 | 239 | Paco Leyva, Orlando | 2 | 122 | 23409
PR | 120 | 02/28/25 | 516 | Barnhart, Joseph N | 0.5 | 34 | 43399
PR | 120 | 02/28/25 | 540 | Lopez, Maslin A | 4 | 132 | 43423
GL | 120 | 03/04/25 | 4 | Deposit, Jesus Romero Garza |  | -871.2
PR | 120 | 05/09/25 | 162 | Barnhart, Joseph N | 2 | 136 | 23511
PR | 120 | 05/16/25 | 361 | Barnhart, Joseph N | 1 | 68 | 33520
GL | 120 | 05/19/25 | 414 | Romero Garza LNI SAW Reimb |  | -871.2
PR | 120 | 06/13/25 | 217 | Lopez, Maslin A | 4 | 132 | 23576
PR | 120 | 07/18/25 | 311 | Barnhart, Joseph N | 3 | 204 | 33590
PR | 120 | 10/03/25 | 15 | Barnhart, Joseph N | 0.25 | 17 | 13658
PR | 120 | 10/03/25 | 15 | Barnhart, Joseph N | 0.5 | 51 | 13658
PR | 130 | 08/09/24 | 256 | Boss, Benjamin T | 8 | 408 | 23056
PR | 130 | 08/16/24 | 444 | Barnhart, Joseph N | 1 | 68 | 33064
PR | 130 | 08/23/24 | 690 | Anderson, Richard P | 2 | 130 | 3059
PR | 130 | 08/23/24 | 742 | Mendoza Morales, Jesus A | 16 | 656 | 43111
PR | 130 | 08/30/24 | 833 | Anderson, Richard P | 4 | 260 | 3078
PR | 130 | 08/30/24 | 852 | Boss, Benjamin T | 16 | 816 | 53097
PR | 130 | 09/06/24 | 9 | Anderson, Richard P | 1 | 65 | 3089
PR | 130 | 09/06/24 | 28 | Boss, Benjamin T | 16 | 816 | 13108
PR | 130 | 09/13/24 | 217 | Anderson, Richard P | 1 | 65 | 3100
PR | 130 | 09/13/24 | 221 | Cruz Reyes, Jose | 24 | 984 | 3104
PR | 130 | 09/13/24 | 226 | Paco Leyva, Orlando | 8 | 488 | 3109
PR | 130 | 09/13/24 | 233 | Barnhart, Joseph N | 3 | 204 | 23116
PR | 130 | 09/13/24 | 236 | Boss, Benjamin T | 40 | 2040 | 23119
PR | 130 | 09/13/24 | 255 | Gochez Molina, Douglas O | 4 | 100 | 23138
PR | 130 | 09/13/24 | 281 | Suniga Aviles, Kelvin A | 6 | 126 | 23164
PR | 130 | 09/13/24 | 287 | Weeks, Gregg A | 24 | 1152 | 23170
PR | 130 | 09/13/24 | 291 | Zuniga Avilez, Eduar A | 4 | 80 | 23174
PR | 130 | 09/20/24 | 390 | Barnhart, Thomas L | 6.5 | 279.5 | 3114
PR | 130 | 09/20/24 | 393 | Cruz Reyes, Jose | 32 | 1312 | 3117
PR | 130 | 09/20/24 | 398 | Paco Leyva, Orlando | 3 | 183 | 3122
PR | 130 | 09/20/24 | 405 | Barnhart, Joseph N | 1 | 68 | 33129
PR | 130 | 09/20/24 | 408 | Boss, Benjamin T | 40 | 2040 | 33132
PR | 130 | 09/20/24 | 458 | Weeks, Gregg A | 32 | 1536 | 33182
PR | 130 | 09/27/24 | 529 | Cruz Reyes, Jose | 24 | 984 | 3128
PR | 130 | 09/27/24 | 535 | Paco Leyva, Orlando | 1 | 61 | 3134
PR | 130 | 09/27/24 | 544 | Boss, Benjamin T | 40 | 2040 | 43143
PR | 130 | 09/27/24 | 594 | Weeks, Gregg A | 24 | 1152 | 43193
PR | 130 | 10/04/24 | 9 | Anderson, Richard P | 1 | 65 | 3138
PR | 130 | 10/04/24 | 13 | Cruz Reyes, Jose | 32 | 1312 | 3142
PR | 130 | 10/04/24 | 19 | Paco Leyva, Orlando | 2 | 122 | 3148
PR | 130 | 10/04/24 | 28 | Boss, Benjamin T | 40 | 2040 | 13157
PR | 130 | 10/04/24 | 42 | Games, Jordan M | 32 | 1696 | 13171
PR | 130 | 10/04/24 | 78 | Weeks, Gregg A | 40 | 1920 | 13207
PR | 130 | 10/11/24 | 217 | Barnhart, Thomas L | 19 | 817 | 3151
PR | 130 | 10/11/24 | 220 | Cruz Reyes, Jose | 32 | 1312 | 3154
PR | 130 | 10/11/24 | 226 | Paco Leyva, Orlando | 2 | 122 | 3160
PR | 130 | 10/11/24 | 233 | Barnhart, Joseph N | 1 | 68 | 23167
PR | 130 | 10/11/24 | 235 | Boss, Benjamin T | 40 | 2040 | 23169
PR | 130 | 10/11/24 | 284 | Weeks, Gregg A | 24 | 1152 | 23218
PR | 130 | 10/18/24 | 433 | Cruz Reyes, Jose | 40 | 1640 | 3166
PR | 130 | 10/18/24 | 439 | Paco Leyva, Orlando | 1 | 61 | 3172
PR | 130 | 10/18/24 | 446 | Barnhart, Joseph N | 2 | 136 | 33179
PR | 130 | 10/18/24 | 448 | Boss, Benjamin T | 16 | 816 | 33181
PR | 130 | 10/18/24 | 460 | Eliassen, Cory H | 34 | 1292 | 33193
PR | 130 | 10/18/24 | 477 | Mendoza Morales, Jesus A | 16 | 656 | 33210
PR | 130 | 10/18/24 | 496 | Weeks, Gregg A | 40 | 1920 | 33229
PR | 130 | 10/25/24 | 581 | Cruz Reyes, Jose | 38 | 1558 | 3178
PR | 130 | 10/25/24 | 584 | Galdamez, Dagoberto A | 2 | 84 | 3181
PR | 130 | 10/25/24 | 587 | Paco Leyva, Orlando | 2 | 122 | 3184
PR | 130 | 10/25/24 | 594 | Barnhart, Joseph N | 1 | 68 | 43191
PR | 130 | 10/25/24 | 607 | Eliassen, Cory H | 24 | 912 | 43204
PR | 130 | 10/25/24 | 608 | Games, Jordan M | 32 | 1696 | 43205
PR | 130 | 10/25/24 | 624 | Mendoza Morales, Jesus A | 32 | 1312 | 43221
PR | 130 | 10/25/24 | 643 | Weeks, Gregg A | 32 | 1536 | 43240
PR | 130 | 11/01/24 | 10 | Cruz Reyes, Jose | 16 | 656 | 3190
PR | 130 | 11/08/24 | 126 | Anderson, Richard P | 3 | 195 | 3198
PR | 130 | 11/08/24 | 128 | Castro, Marcus J | 8 | 160 | 3200
PR | 130 | 11/08/24 | 130 | Cruz Reyes, Jose | 24 | 984 | 3202
PR | 130 | 11/08/24 | 139 | Aquino, Juan | 8 | 216 | 23211
PR | 130 | 11/08/24 | 143 | Barnhart, Joseph N | 1 | 68 | 23215
PR | 130 | 11/08/24 | 144 | Bautista Quintero, Isidoro | 8 | 160 | 23216
PR | 130 | 11/08/24 | 156 | Eliassen, Cory H | 24 | 912 | 23228
PR | 130 | 11/08/24 | 174 | Mendoza Morales, Jesus A | 40 | 1640 | 23246
PR | 130 | 11/08/24 | 187 | Suniga Aviles, Kelvin A | 8 | 168 | 23259
PR | 130 | 11/08/24 | 197 | Zuniga Avilez, Eduar A | 8 | 160 | 23269
PR | 130 | 11/15/24 | 350 | Cruz Reyes, Jose | 40 | 1640 | 3214
PR | 130 | 11/15/24 | 356 | Paco Leyva, Orlando | 5 | 305 | 3220
PR | 130 | 11/15/24 | 376 | Eliassen, Cory H | 13 | 494 | 33240
PR | 130 | 11/15/24 | 394 | Mendoza Morales, Jesus A | 40 | 1640 | 33258
PR | 130 | 11/22/24 | 505 | Cruz Reyes, Jose | 32 | 1312 | 3227
PR | 130 | 11/22/24 | 531 | Eliassen, Cory H | 24 | 912 | 43253
PR | 130 | 11/22/24 | 549 | Mendoza Morales, Jesus A | 40 | 1640 | 43271
PR | 130 | 11/22/24 | 565 | Trower-Kelly, Fidel D | 40 | 1240 | 43287
PR | 130 | 11/29/24 | 653 | Cruz Reyes, Jose | 40 | 1640 | 3239
PR | 130 | 11/29/24 | 663 | Araque, Mario W | 40 | 880 | 53249
PR | 130 | 11/29/24 | 679 | Eliassen, Cory H | 21 | 798 | 53265
PR | 130 | 11/29/24 | 697 | Mendoza Morales, Jesus A | 40 | 1640 | 53283
PR | 130 | 11/29/24 | 713 | Trower-Kelly, Fidel D | 16 | 496 | 53299
PR | 130 | 12/06/24 | 55 | Cruz Reyes, Jose | 24 | 984 | 3251
PR | 130 | 12/06/24 | 65 | Araque, Mario W | 24 | 528 | 13261
PR | 130 | 12/06/24 | 73 | Chastain, Aaron R | 3 | 63 | 13269
PR | 130 | 12/06/24 | 81 | Eliassen, Cory H | 24 | 912 | 13277
PR | 130 | 12/06/24 | 82 | Games, Jordan M | 3 | 159 | 13278
PR | 130 | 12/06/24 | 99 | Mendoza Morales, Jesus A | 24 | 984 | 13295
PR | 130 | 12/06/24 | 114 | Trower-Kelly, Fidel D | 16 | 496 | 13310
PR | 130 | 12/13/24 | 235 | Anderson, Richard P | 3 | 195 | 3270
PR | 130 | 12/13/24 | 236 | Barnhart, Thomas L | 16 | 688 | 3271
PR | 130 | 12/13/24 | 238 | Cruz Reyes, Jose | 24 | 984 | 3273
PR | 130 | 12/13/24 | 243 | Paco Leyva, Orlando | 10 | 610 | 3278
PR | 130 | 12/13/24 | 247 | Araque, Mario W | 24 | 528 | 23282
PR | 130 | 12/13/24 | 255 | Chastain, Aaron R | 13 | 273 | 23290
PR | 130 | 12/13/24 | 263 | Eliassen, Cory H | 22 | 836 | 23298
PR | 130 | 12/13/24 | 264 | Games, Jordan M | 15 | 795 | 23299
PR | 130 | 12/13/24 | 281 | Mendoza Morales, Jesus A | 32 | 1312 | 23316
PR | 130 | 12/13/24 | 296 | Trower-Kelly, Fidel D | 24 | 744 | 23331
PR | 130 | 12/20/24 | 422 | Anderson, Richard P | 1 | 65 | 3280
PR | 130 | 12/20/24 | 425 | Cruz Reyes, Jose | 24 | 984 | 3283
PR | 130 | 12/20/24 | 434 | Araque, Mario W | 24 | 528 | 33292
PR | 130 | 12/20/24 | 437 | Barnhart, Joseph N | 3 | 204 | 33295
PR | 130 | 12/20/24 | 442 | Chastain, Aaron R | 12 | 252 | 33300
PR | 130 | 12/20/24 | 449 | Eliassen, Cory H | 24 | 912 | 33307
PR | 130 | 12/20/24 | 450 | Games, Jordan M | 17 | 901 | 33308
PR | 130 | 12/20/24 | 467 | Mendoza Morales, Jesus A | 32 | 1312 | 33325
PR | 130 | 12/20/24 | 483 | Trower-Kelly, Fidel D | 24 | 744 | 33340
PR | 130 | 12/27/24 | 543 | Cruz Reyes, Jose | 16 | 656 | 3294
PR | 130 | 12/27/24 | 553 | Araque, Mario W | 16 | 352 | 43303
PR | 130 | 12/27/24 | 561 | Chastain, Aaron R | 16 | 336 | 43311
PR | 130 | 12/27/24 | 568 | Eliassen, Cory H | 14.5 | 551 | 43318
PR | 130 | 12/27/24 | 569 | Games, Jordan M | 16 | 848 | 43319
PR | 130 | 12/27/24 | 599 | Trower-Kelly, Fidel D | 16 | 496 | 43349
PR | 130 | 01/03/25 | 16 | Cruz Reyes, Jose | 16 | 656 | 3305
PR | 130 | 01/03/25 | 25 | Araque, Mario W | 16 | 352 | 13314
PR | 130 | 01/03/25 | 32 | Chastain, Aaron R | 16 | 336 | 13321
PR | 130 | 01/03/25 | 39 | Eliassen, Cory H | 8 | 304 | 13328
PR | 130 | 01/03/25 | 40 | Games, Jordan M | 21.5 | 1139.5 | 13329
PR | 130 | 01/03/25 | 67 | Trower-Kelly, Fidel D | 16 | 496 | 13356
PR | 130 | 01/10/25 | 175 | Barnhart, Thomas L | 8 | 344 | 3313
PR | 130 | 01/10/25 | 190 | Barnhart, Joseph N | 6 | 408 | 23328
PR | 130 | 01/10/25 | 194 | Chastain, Aaron R | 16 | 368 | 23332
PR | 130 | 01/10/25 | 203 | Games, Jordan M | 31 | 1643 | 23341
GL | 130 | 01/14/25 | 315 | Fiberglass ck to credit Trailside labor |  | -9586
PR | 130 | 01/17/25 | 340 | Barnhart, Thomas L | 16 | 688 | 3326
PR | 130 | 01/17/25 | 342 | Cosentino, Brandon C | 32 | 768 | 3328
PR | 130 | 01/17/25 | 354 | Barnhart, Joseph N | 4 | 272 | 33340
PR | 130 | 01/17/25 | 358 | Chastain, Aaron R | 40 | 920 | 33344
PR | 130 | 01/17/25 | 366 | Games, Jordan M | 36 | 1908 | 33352
PR | 130 | 01/17/25 | 395 | Trower-Kelly, Fidel D | 8 | 248 | 33381
PR | 130 | 01/24/25 | 506 | Barnhart, Thomas L | 8 | 344 | 3336
PR | 130 | 01/24/25 | 508 | Cosentino, Brandon C | 40 | 960 | 3338
PR | 130 | 01/24/25 | 520 | Barnhart, Joseph N | 2 | 136 | 43350
PR | 130 | 01/24/25 | 524 | Chastain, Aaron R | 40 | 920 | 43354
PR | 130 | 01/24/25 | 533 | Games, Jordan M | 40 | 2120 | 43363
PR | 130 | 01/24/25 | 562 | Trower-Kelly, Fidel D | 32 | 992 | 43392
PR | 130 | 01/31/25 | 700 | Cosentino, Brandon C | 40 | 960 | 3348
PR | 130 | 01/31/25 | 712 | Barnhart, Joseph N | 3 | 204 | 53360
PR | 130 | 01/31/25 | 716 | Chastain, Aaron R | 32 | 736 | 53364
PR | 130 | 01/31/25 | 725 | Games, Jordan M | 38 | 2014 | 53373
PR | 130 | 01/31/25 | 753 | Trower-Kelly, Fidel D | 40 | 1240 | 53401
PR | 130 | 02/07/25 | 31 | Cosentino, Brandon C | 24 | 576 | 3358
PR | 130 | 02/07/25 | 42 | Barnhart, Joseph N | 2 | 136 | 13369
PR | 130 | 02/07/25 | 46 | Chastain, Aaron R | 36 | 828 | 13373
PR | 130 | 02/07/25 | 55 | Games, Jordan M | 36 | 1908 | 13382
PR | 130 | 02/07/25 | 84 | Trower-Kelly, Fidel D | 39 | 1209 | 13411
PR | 130 | 02/14/25 | 194 | Anderson, Richard P | 1 | 65 | 3364
PR | 130 | 02/14/25 | 197 | Cosentino, Brandon C | 32 | 768 | 3367
PR | 130 | 02/14/25 | 208 | Barnhart, Joseph N | 3 | 204 | 23378
PR | 130 | 02/14/25 | 212 | Chastain, Aaron R | 40 | 920 | 23382
PR | 130 | 02/14/25 | 221 | Games, Jordan M | 32 | 1696 | 23391
PR | 130 | 02/14/25 | 250 | Trower-Kelly, Fidel D | 24 | 744 | 23420
PR | 130 | 02/21/25 | 311 | Anderson, Richard P | 1 | 65 | 3373
PR | 130 | 02/21/25 | 314 | Cosentino, Brandon C | 40 | 960 | 3376
PR | 130 | 02/21/25 | 326 | Barnhart, Joseph N | 2 | 136 | 33388
PR | 130 | 02/21/25 | 330 | Chastain, Aaron R | 40 | 920 | 33392
PR | 130 | 02/21/25 | 338 | Eliassen, Cory H | 32 | 1216 | 33400
PR | 130 | 02/21/25 | 339 | Games, Jordan M | 40 | 2120 | 33401
PR | 130 | 02/21/25 | 368 | Trower-Kelly, Fidel D | 32 | 992 | 33430
PR | 130 | 02/28/25 | 504 | Cosentino, Brandon C | 32 | 768 | 3387
PR | 130 | 02/28/25 | 516 | Barnhart, Joseph N | 2 | 136 | 43399
PR | 130 | 02/28/25 | 520 | Chastain, Aaron R | 32 | 736 | 43403
PR | 130 | 02/28/25 | 528 | Eliassen, Cory H | 24 | 912 | 43411
PR | 130 | 02/28/25 | 529 | Games, Jordan M | 40 | 2120 | 43412
PR | 130 | 02/28/25 | 558 | Trower-Kelly, Fidel D | 31.5 | 976.5 | 43441
PR | 130 | 03/07/25 | 17 | Cosentino, Brandon C | 38 | 912 | 3397
PR | 130 | 03/07/25 | 33 | Chastain, Aaron R | 37 | 851 | 13413
PR | 130 | 03/07/25 | 41 | Eliassen, Cory H | 37 | 1406 | 13421
PR | 130 | 03/07/25 | 42 | Games, Jordan M | 40 | 2120 | 13422
PR | 130 | 03/07/25 | 71 | Trower-Kelly, Fidel D | 29 | 899 | 13451
PR | 130 | 03/14/25 | 217 | Cosentino, Brandon C | 24 | 576 | 3408
PR | 130 | 03/14/25 | 233 | Chastain, Aaron R | 40 | 920 | 23424
PR | 130 | 03/14/25 | 241 | Eliassen, Cory H | 32 | 1216 | 23432
PR | 130 | 03/14/25 | 242 | Games, Jordan M | 32 | 1696 | 23433
PR | 130 | 03/14/25 | 253 | Lopez, Maslin A | 8 | 264 | 23444
PR | 130 | 03/14/25 | 271 | Trower-Kelly, Fidel D | 32 | 992 | 23462
PR | 130 | 03/14/25 | 400 | Cosentino, Brandon C | 16 | 384 | 3418
PR | 130 | 03/14/25 | 410 | Cosentino, Brandon C | 16 | -384 | 3418
PR | 130 | 03/21/25 | 422 | Barnhart, Joseph N | 4.5 | 306 | 93430
PR | 130 | 03/21/25 | 426 | Chastain, Aaron R | 24 | 552 | 93434
PR | 130 | 03/21/25 | 434 | Eliassen, Cory H | 32 | 1216 | 93442
PR | 130 | 03/21/25 | 435 | Games, Jordan M | 38 | 2014 | 93443
PR | 130 | 03/21/25 | 465 | Trower-Kelly, Fidel D | 32 | 992 | 93473
PR | 130 | 03/21/25 | 476 | Cosentino, Brandon C | 16 | 384 | 3428
PR | 130 | 03/28/25 | 565 | Cosentino, Brandon C | 20.5 | 492 | 3439
PR | 130 | 03/28/25 | 581 | Chastain, Aaron R | 24 | 552 | 93455
PR | 130 | 03/28/25 | 589 | Eliassen, Cory H | 27.25 | 1035.5 | 93463
PR | 130 | 03/28/25 | 590 | Games, Jordan M | 24 | 1272 | 93464
PR | 130 | 03/28/25 | 622 | Trower-Kelly, Fidel D | 32 | 992 | 93496
PR | 130 | 04/04/25 | 8 | Cosentino, Brandon C | 40 | 960 | 3450
PR | 130 | 04/04/25 | 24 | Chastain, Aaron R | 40 | 920 | 13466
PR | 130 | 04/04/25 | 32 | Eliassen, Cory H | 32 | 1216 | 13474
PR | 130 | 04/04/25 | 33 | Games, Jordan M | 35 | 1855 | 13475
PR | 130 | 04/04/25 | 65 | Trower-Kelly, Fidel D | 32 | 992 | 13507
PR | 130 | 04/11/25 | 171 | Cosentino, Brandon C | 40 | 960 | 3460
PR | 130 | 04/11/25 | 204 | Chastain, Aaron R | 39 | 897 | 93476
PR | 130 | 04/11/25 | 210 | Draves, Steven W | 16 | 880 | 93482
PR | 130 | 04/11/25 | 212 | Eliassen, Cory H | 24 | 912 | 93484
PR | 130 | 04/11/25 | 213 | Games, Jordan M | 40 | 2120 | 93485
PR | 130 | 04/11/25 | 245 | Trower-Kelly, Fidel D | 40 | 1240 | 93517
PR | 130 | 04/18/25 | 412 | Cosentino, Brandon C | 32 | 768 | 3470
PR | 130 | 04/18/25 | 424 | Barnhart, Joseph N | 2 | 136 | 33482
PR | 130 | 04/18/25 | 428 | Chastain, Aaron R | 37.5 | 862.5 | 33486
PR | 130 | 04/18/25 | 436 | Eliassen, Cory H | 24 | 912 | 33494
PR | 130 | 04/18/25 | 437 | Games, Jordan M | 40 | 2120 | 33495
PR | 130 | 04/18/25 | 469 | Trower-Kelly, Fidel D | 40 | 1240 | 33527
PR | 130 | 04/25/25 | 551 | Cosentino, Brandon C | 32 | 768 | 3480
PR | 130 | 04/25/25 | 555 | Galdamez, Dagoberto A | 8 | 336 | 3484
PR | 130 | 04/25/25 | 563 | Barnhart, Joseph N | 5 | 340 | 43492
PR | 130 | 04/25/25 | 567 | Chastain, Aaron R | 32 | 736 | 43496
PR | 130 | 04/25/25 | 575 | Eliassen, Cory H | 24 | 912 | 43504
PR | 130 | 04/25/25 | 576 | Games, Jordan M | 24 | 1272 | 43505
PR | 130 | 04/25/25 | 608 | Trower-Kelly, Fidel D | 24 | 744 | 43537
PR | 130 | 05/02/25 | 5 | Cosentino, Brandon C | 8 | 192 | 3490
PR | 130 | 05/02/25 | 21 | Chastain, Aaron R | 8 | 184 | 13506
PR | 130 | 05/02/25 | 29 | Eliassen, Cory H | 8 | 304 | 13514
PR | 130 | 05/02/25 | 30 | Games, Jordan M | 33 | 1749 | 13515
PR | 130 | 05/02/25 | 41 | Lopez, Maslin A | 4 | 132 | 13526
PR | 130 | 05/02/25 | 49 | Paco Leyva, Orlando | 2 | 122 | 13534
PR | 130 | 05/02/25 | 61 | Trower-Kelly, Fidel D | 8 | 248 | 13546
PR | 130 | 05/02/25 | 62 | Vazquez Popoca, Jose N | 8 | 280 | 13547
PR | 130 | 05/09/25 | 162 | Barnhart, Joseph N | 1 | 68 | 23511
PR | 130 | 05/09/25 | 173 | Games, Jordan M | 17 | 901 | 23522
PR | 130 | 05/09/25 | 184 | Lopez, Maslin A | 8 | 264 | 23533
PR | 130 | 05/16/25 | 372 | Games, Jordan M | 19 | 1007 | 33531
PR | 130 | 05/16/25 | 391 | Paco Leyva, Orlando | 4 | 244 | 33550
PR | 130 | 05/16/25 | 403 | Vazquez Popoca, Jose N | 24 | 840 | 33562
PR | 130 | 05/23/25 | 468 | Games, Jordan M | 16 | 848 | 43540
PR | 130 | 05/23/25 | 487 | Paco Leyva, Orlando | 3 | 183 | 43559
PR | 130 | 05/23/25 | 499 | Vazquez Popoca, Jose N | 29 | 1015 | 43571
PR | 130 | 05/30/25 | 545 | Barnhart, Joseph N | 1 | 68 | 53537
PR | 130 | 05/30/25 | 557 | Games, Jordan M | 16 | 848 | 53549
PR | 130 | 05/30/25 | 588 | Vazquez Popoca, Jose N | 8 | 280 | 53580
PR | 130 | 06/06/25 | 24 | Galdamez, Dagoberto A | 16 | 672 | 3537
PR | 130 | 06/06/25 | 45 | Games, Jordan M | 8 | 424 | 13557
PR | 130 | 06/06/25 | 75 | Vazquez Popoca, Jose N | 40 | 1400 | 13587
PR | 130 | 06/13/25 | 186 | Galdamez, Dagoberto A | 4 | 168 | 3545
PR | 130 | 06/13/25 | 206 | Games, Jordan M | 24 | 1272 | 23565
PR | 130 | 06/13/25 | 217 | Lopez, Maslin A | 4 | 132 | 23576
PR | 130 | 06/13/25 | 225 | Paco Leyva, Orlando | 18 | 1098 | 23584
PR | 130 | 06/13/25 | 237 | Vazquez Popoca, Jose N | 16 | 560 | 23596
PR | 130 | 06/20/25 | 314 | Galdamez, Dagoberto A | 12 | 504 | 3553
PR | 130 | 06/20/25 | 333 | Games, Jordan M | 29.5 | 1563.5 | 33572
PR | 130 | 06/20/25 | 344 | Lopez, Maslin A | 24 | 792 | 33583
PR | 130 | 06/20/25 | 352 | Paco Leyva, Orlando | 15 | 915 | 33591
PR | 130 | 06/20/25 | 364 | Vazquez Popoca, Jose N | 32 | 1120 | 33603
PR | 130 | 06/27/25 | 464 | Barnhart, Thomas L | 32 | 1376 | 3557
PR | 130 | 06/27/25 | 488 | Games, Jordan M | 31.5 | 1669.5 | 43581
PR | 130 | 06/27/25 | 499 | Lopez, Maslin A | 40 | 1320 | 43592
PR | 130 | 06/27/25 | 507 | Paco Leyva, Orlando | 16 | 976 | 43600
PR | 130 | 06/27/25 | 519 | Vazquez Popoca, Jose N | 40 | 1400 | 43612
PR | 130 | 07/03/25 | 8 | Barnhart, Thomas L | 12 | 516 | 3565
PR | 130 | 07/03/25 | 12 | Galdamez, Dagoberto A | 8 | 336 | 3569
PR | 130 | 07/03/25 | 19 | Barnhart, Joseph N | 4 | 272 | 13576
PR | 130 | 07/03/25 | 31 | Games, Jordan M | 24 | 1272 | 13588
PR | 130 | 07/03/25 | 42 | Lopez, Maslin A | 40 | 1320 | 13599
PR | 130 | 07/03/25 | 50 | Paco Leyva, Orlando | 17 | 1037 | 13607
PR | 130 | 07/03/25 | 62 | Vazquez Popoca, Jose N | 16 | 560 | 13619
PR | 130 | 07/11/25 | 133 | Barnhart, Thomas L | 16 | 688 | 3572
PR | 130 | 07/11/25 | 137 | Galdamez, Dagoberto A | 31 | 1302 | 3576
PR | 130 | 07/11/25 | 144 | Barnhart, Joseph N | 2 | 136 | 23583
PR | 130 | 07/11/25 | 156 | Games, Jordan M | 31 | 1643 | 23595
PR | 130 | 07/11/25 | 166 | Lopez, Maslin A | 23 | 759 | 23605
PR | 130 | 07/11/25 | 174 | Paco Leyva, Orlando | 18 | 1098 | 23613
PR | 130 | 07/11/25 | 186 | Vazquez Popoca, Jose N | 31 | 1085 | 23625
PR | 130 | 07/18/25 | 301 | Barnhart, Thomas L | 22 | 946 | 3580
PR | 130 | 07/18/25 | 304 | Galdamez, Dagoberto A | 32 | 1344 | 3583
PR | 130 | 07/18/25 | 311 | Barnhart, Joseph N | 5 | 340 | 33590
PR | 130 | 07/18/25 | 323 | Games, Jordan M | 20.5 | 1086.5 | 33602
PR | 130 | 07/18/25 | 333 | Lopez, Maslin A | 34 | 1122 | 33612
PR | 130 | 07/18/25 | 341 | Paco Leyva, Orlando | 20 | 1220 | 33620
PR | 130 | 07/18/25 | 353 | Vazquez Popoca, Jose N | 8 | 280 | 33632
PR | 130 | 07/25/25 | 467 | Anderson, Richard P | 2 | 130 | 3585
PR | 130 | 07/25/25 | 468 | Barnhart, Thomas L | 8 | 344 | 3586
PR | 130 | 07/25/25 | 472 | Galdamez, Dagoberto A | 8 | 336 | 3590
PR | 130 | 07/25/25 | 479 | Barnhart, Joseph N | 3 | 204 | 43597
PR | 130 | 07/25/25 | 491 | Games, Jordan M | 18 | 954 | 43609
PR | 130 | 07/25/25 | 501 | Lopez, Maslin A | 20 | 660 | 43619
PR | 130 | 07/25/25 | 509 | Paco Leyva, Orlando | 8 | 488 | 43627
PR | 130 | 08/01/25 | 9 | Araque, Mario W | 24 | 576 | 13600
PR | 130 | 08/01/25 | 24 | Games, Jordan M | 24 | 1272 | 13615
PR | 130 | 08/01/25 | 34 | Lopez, Maslin A | 16 | 528 | 13625
PR | 130 | 08/01/25 | 42 | Paco Leyva, Orlando | 4 | 244 | 13633
PR | 130 | 08/01/25 | 43 | Perez Araque, Manuel A | 24 | 672 | 13634
PR | 130 | 08/08/25 | 140 | Araque, Mario W | 24 | 576 | 23607
PR | 130 | 08/08/25 | 150 | Cruz, Azael S | 16 | 512 | 23617
PR | 130 | 08/08/25 | 155 | Games, Jordan M | 26 | 1378 | 23622
PR | 130 | 08/08/25 | 165 | Lopez, Maslin A | 16 | 528 | 23632
PR | 130 | 08/08/25 | 173 | Paco Leyva, Orlando | 8 | 488 | 23640
PR | 130 | 08/08/25 | 174 | Perez Araque, Manuel A | 16 | 448 | 23641
PR | 130 | 08/15/25 | 268 | Barnhart, Joseph N | 1 | 68 | 33615
PR | 130 | 08/15/25 | 280 | Games, Jordan M | 19 | 1007 | 33627
PR | 130 | 08/22/25 | 371 | Barnhart, Joseph N | 3 | 204 | 43621
PR | 130 | 08/22/25 | 384 | Games, Jordan M | 24 | 1272 | 43634
PR | 130 | 08/22/25 | 394 | Lopez, Maslin A | 8 | 264 | 43644
PR | 130 | 08/29/25 | 547 | Games, Jordan M | 1 | 53 | 53640
PR | 130 | 09/05/25 | 42 | Lopez, Maslin A | 2 | 66 | 13656
PR | 130 | 09/26/25 | 461 | Taylor, Evan R | 7 | 364 | 43693
PR | 130 | 09/26/25 | 461 | Taylor, Evan R | 4.75 | 247 | 43693
PR | 140 | 03/15/24 | 533 | Hubbard, Justin A | 16 | 736 | 2562
PR | 140 | 03/15/24 | 538 | McCurry, Maxwell J | 8 | 192 | 2567
PR | 140 | 03/15/24 | 545 | Paco Leyva, Orlando | 2 | 122 | 2574
PR | 140 | 04/05/24 | 21 | Molina, Carlos G | 8 | 208 | 2697
PR | 140 | 04/12/24 | 244 | McCurry, Maxwell J | 8 | 192 | 92788
PR | 140 | 05/03/24 | 18 | Paco Leyva, Orlando | 8 | 488 | 2806
PR | 140 | 05/03/24 | 93 | Suniga Aviles, Kelvin A | 8 | 168 | 92880
PR | 140 | 05/10/24 | 256 | Paco Leyva, Orlando | 6 | 366 | 2827
PR | 140 | 05/10/24 | 331 | Suniga Aviles, Kelvin A | 16 | 336 | 92901
PR | 140 | 05/17/24 | 484 | Paco Leyva, Orlando | 8 | 488 | 2852
PR | 140 | 05/17/24 | 539 | Martinez Garcia, Cesar B | 8 | 160 | 92906
PR | 140 | 05/17/24 | 543 | Mendoza Morales, Jesus A | 8 | 328 | 92910
PR | 140 | 05/17/24 | 558 | Suniga Aviles, Kelvin A | 8 | 168 | 92925
PR | 140 | 05/24/24 | 692 | Paco Leyva, Orlando | 4 | 244 | 2877
PR | 140 | 05/31/24 | 806 | Paco Leyva, Orlando | 4 | 244 | 2897
PR | 140 | 06/07/24 | 80 | Anderson, Richard P | 2 | 130 | 2904
PR | 140 | 06/07/24 | 95 | Paco Leyva, Orlando | 8 | 488 | 2919
PR | 140 | 06/14/24 | 318 | Paco Leyva, Orlando | 4 | 244 | 2938
PR | 140 | 06/14/24 | 363 | Lima Romero, Melvin A | 8 | 352 | 92982
PR | 140 | 07/05/24 | 4 | Barnhart, Joseph N | 1 | 68 | 2976
PR | 140 | 09/20/24 | 398 | Paco Leyva, Orlando | 4 | 244 | 3122
PR | 140 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I | 16 | 704 | 43190
PR | 140 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I | 8 | 352 | 13202
PR | 140 | 11/08/24 | 136 | Paco Leyva, Orlando | 6 | 366 | 3208
PR | 140 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I | 8 | 352 | 23214
PR | 140 | 11/08/24 | 146 | Carmona, Raul O | 8 | 424 | 23218
PR | 140 | 11/08/24 | 168 | Lima Romero, Melvin A | 8 | 352 | 23240
PR | 140 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I | 8 | 352 | 33226
PR | 140 | 11/22/24 | 508 | Galdamez, Dagoberto A | 8 | 336 | 3230
PR | 140 | 11/22/24 | 511 | Paco Leyva, Orlando | 2 | 122 | 3233
PR | 140 | 11/29/24 | 649 | Anderson, Richard P | 6 | 390 | 3235
PR | 140 | 11/29/24 | 656 | Galdamez, Dagoberto A | 8 | 336 | 3242
PR | 140 | 11/29/24 | 659 | Paco Leyva, Orlando | 8 | 488 | 3245
PR | 140 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I | 8 | 352 | 53251
PR | 140 | 11/29/24 | 669 | Carmona, Raul O | 8 | 424 | 53255
PR | 140 | 12/27/24 | 546 | Galdamez, Dagoberto A | 8 | 336 | 3297
PR | 140 | 01/10/25 | 174 | Anderson, Richard P | 1 | 65 | 3312
PR | 140 | 01/10/25 | 181 | Galdamez, Dagoberto A | 12 | 504 | 3319
PR | 140 | 01/10/25 | 183 | Paco Leyva, Orlando | 2 | 122 | 3321
PR | 140 | 01/10/25 | 190 | Barnhart, Joseph N | 2 | 136 | 23328
PR | 140 | 01/17/25 | 339 | Anderson, Richard P | 2 | 130 | 3325
PR | 140 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I | 8 | 352 | 33339
PR | 140 | 01/17/25 | 354 | Barnhart, Joseph N | 2 | 136 | 33340
PR | 140 | 01/17/25 | 384 | Paco Leyva, Orlando | 4 | 244 | 33370
PR | 140 | 01/24/25 | 551 | Paco Leyva, Orlando | 5 | 305 | 43381
PR | 140 | 01/31/25 | 704 | Galdamez, Dagoberto A | 8 | 336 | 3352
PR | 140 | 01/31/25 | 743 | Paco Leyva, Orlando | 8 | 488 | 53391
PR | 140 | 02/07/25 | 42 | Barnhart, Joseph N | 1 | 68 | 13369
PR | 140 | 02/07/25 | 73 | Paco Leyva, Orlando | 12 | 732 | 13400
PR | 140 | 02/14/25 | 208 | Barnhart, Joseph N | 2 | 136 | 23378
PR | 140 | 02/14/25 | 232 | Lopez, Maslin A | 12 | 396 | 23402
PR | 140 | 02/14/25 | 239 | Paco Leyva, Orlando | 14 | 854 | 23409
PR | 140 | 02/21/25 | 326 | Barnhart, Joseph N | 1 | 102 | 33388
PR | 140 | 02/21/25 | 357 | Paco Leyva, Orlando | 12 | 732 | 33419
PR | 140 | 02/28/25 | 516 | Barnhart, Joseph N | 2 | 136 | 43399
PR | 140 | 02/28/25 | 540 | Lopez, Maslin A | 16 | 528 | 43423
PR | 140 | 02/28/25 | 547 | Paco Leyva, Orlando | 18.5 | 1128.5 | 43430
PR | 140 | 03/07/25 | 29 | Barnhart, Joseph N | 1 | 68 | 13409
PR | 140 | 03/07/25 | 53 | Lopez, Maslin A | 7 | 231 | 13433
PR | 140 | 03/07/25 | 60 | Paco Leyva, Orlando | 7 | 427 | 13440
PR | 140 | 03/14/25 | 260 | Paco Leyva, Orlando | 4 | 244 | 23451
PR | 140 | 03/21/25 | 422 | Barnhart, Joseph N | 1 | 68 | 93430
PR | 140 | 03/28/25 | 577 | Barnhart, Joseph N | 1 | 68 | 93451
PR | 140 | 04/04/25 | 12 | Galdamez, Dagoberto A | 6 | 252 | 3454
PR | 140 | 04/04/25 | 53 | Paco Leyva, Orlando | 7 | 427 | 13495
PR | 140 | 04/25/25 | 563 | Barnhart, Joseph N | 1 | 68 | 43492
PR | 140 | 04/25/25 | 596 | Paco Leyva, Orlando | 16 | 976 | 43525
PR | 140 | 05/02/25 | 49 | Paco Leyva, Orlando | 3 | 183 | 13534
PR | 140 | 05/30/25 | 545 | Barnhart, Joseph N | 1 | 68 | 53537
PR | 140 | 06/06/25 | 33 | Barnhart, Joseph N | 2 | 136 | 13545
PR | 140 | 06/06/25 | 63 | Paco Leyva, Orlando | 6 | 366 | 13575
PR | 140 | 06/27/25 | 476 | Barnhart, Joseph N | 2 | 136 | 43569
PR | 140 | 07/03/25 | 19 | Barnhart, Joseph N | 2 | 136 | 13576
PR | 140 | 07/11/25 | 144 | Barnhart, Joseph N | 2 | 136 | 23583
PR | 140 | 07/11/25 | 174 | Paco Leyva, Orlando | 3 | 183 | 23613
PR | 140 | 07/18/25 | 311 | Barnhart, Joseph N | 2 | 136 | 33590
PR | 140 | 07/18/25 | 333 | Lopez, Maslin A | 2 | 66 | 33612
PR | 140 | 07/25/25 | 479 | Barnhart, Joseph N | 1 | 68 | 43597
PR | 140 | 07/25/25 | 509 | Paco Leyva, Orlando | 4 | 244 | 43627
PR | 141 | 01/19/24 | 704 | Jimenez, D'angelo J | 28 | 784 | 1754
PR | 141 | 01/26/24 | 995 | Paco Leyva, Orlando | 4 | 244 | 1886
PR | 141 | 02/02/24 | 19 | Belcher, Jacob T | 28 | 784 | 1931
PR | 141 | 02/02/24 | 78 | McCurry, Maxwell J | 8 | 192 | 1989
PR | 141 | 02/02/24 | 88 | Paco Leyva, Orlando | 9 | 549 | 1999
PR | 141 | 02/09/24 | 308 | Paco Leyva, Orlando | 3 | 183 | 2111
PR | 141 | 02/16/24 | 559 | Molina, Carlos G | 40 | 1040 | 2218
PR | 141 | 02/16/24 | 565 | Paco Leyva, Orlando | 10 | 610 | 2224
PR | 141 | 02/23/24 | 727 | Molina, Carlos G | 31 | 806 | 2327
PR | 141 | 02/23/24 | 733 | Paco Leyva, Orlando | 6 | 366 | 2333
PR | 141 | 03/01/24 | 55 | Lopez, Maslin A | 8 | 264 | 2420
PR | 141 | 03/01/24 | 65 | Molina, Carlos G | 16 | 416 | 2430
PR | 141 | 03/01/24 | 71 | Paco Leyva, Orlando | 4 | 244 | 2436
PR | 141 | 03/01/24 | 100 | Zuniga Avilez, Eduar A | 8 | 160 | 2465
PR | 141 | 03/08/24 | 288 | Molina, Carlos G | 16 | 416 | 2507
PR | 141 | 03/08/24 | 292 | Paco Leyva, Orlando | 14 | 854 | 2511
PR | 141 | 03/08/24 | 296 | Puentez, Victor M | 16 | 352 | 2515
PR | 141 | 03/08/24 | 307 | Suniga Aviles, Kelvin A | 24 | 504 | 2526
PR | 141 | 03/08/24 | 313 | Zuniga Avilez, Eduar A | 40 | 800 | 2532
PR | 141 | 03/08/24 | 344 | Lopez, Maslin A | 40 | 1320 | 92562
PR | 141 | 03/15/24 | 533 | Hubbard, Justin A | 16 | 736 | 2562
PR | 141 | 03/15/24 | 538 | McCurry, Maxwell J | 8 | 192 | 2567
PR | 141 | 03/15/24 | 541 | Molina, Carlos G | 40 | 1040 | 2570
PR | 141 | 03/15/24 | 545 | Paco Leyva, Orlando | 6 | 366 | 2574
PR | 141 | 03/15/24 | 560 | Suniga Aviles, Kelvin A | 16 | 336 | 2589
PR | 141 | 03/15/24 | 566 | Zuniga Avilez, Eduar A | 40 | 800 | 2595
PR | 141 | 03/15/24 | 601 | Gerard, Mitchell J | 2 | 122 | 92619
PR | 141 | 03/15/24 | 610 | Lopez, Maslin A | 24 | 792 | 92628
PR | 141 | 03/22/24 | 821 | Hubbard, Justin A | 8 | 368 | 2619
PR | 141 | 03/22/24 | 824 | McCurry, Maxwell J | 8 | 192 | 2622
PR | 141 | 03/22/24 | 826 | Molina, Carlos G | 40 | 1040 | 2624
PR | 141 | 03/22/24 | 829 | Paco Leyva, Orlando | 9 | 549 | 2627
PR | 141 | 03/22/24 | 838 | Suniga Aviles, Kelvin A | 40 | 840 | 2636
PR | 141 | 03/22/24 | 842 | Zuniga Avilez, Eduar A | 40 | 800 | 2640
PR | 141 | 03/22/24 | 880 | Lopez, Maslin A | 8 | 264 | 92677
PR | 141 | 03/22/24 | 886 | Mendoza Morales, Jesus A | 24 | 984 | 92683
PR | 141 | 03/29/24 | 1180 | Anderson, Richard P | 6 | 390 | 2641
PR | 141 | 03/29/24 | 1202 | Molina, Carlos G | 40 | 1040 | 2663
PR | 141 | 03/29/24 | 1205 | Paco Leyva, Orlando | 9 | 549 | 2666
PR | 141 | 03/29/24 | 1212 | Suniga Aviles, Kelvin A | 40 | 840 | 2673
PR | 141 | 03/29/24 | 1216 | Zuniga Avilez, Eduar A | 40 | 800 | 2677
PR | 141 | 03/29/24 | 1265 | Mendoza Morales, Jesus A | 40 | 1640 | 92725
PR | 141 | 04/05/24 | 21 | Molina, Carlos G | 8 | 208 | 2697
PR | 141 | 04/05/24 | 24 | Paco Leyva, Orlando | 10 | 610 | 2700
PR | 141 | 04/05/24 | 32 | Zuniga Avilez, Eduar A | 8 | 160 | 2708
PR | 141 | 04/05/24 | 84 | Mendoza Morales, Jesus A | 40 | 1640 | 92759
PR | 141 | 04/05/24 | 102 | Suniga Aviles, Kelvin A | 40 | 840 | 92777
PR | 141 | 04/12/24 | 180 | Molina, Carlos G | 8 | 208 | 2725
PR | 141 | 04/12/24 | 183 | Paco Leyva, Orlando | 9 | 549 | 2728
PR | 141 | 04/12/24 | 192 | Zuniga Avilez, Eduar A | 32 | 640 | 2737
PR | 141 | 04/12/24 | 246 | Mendoza Morales, Jesus A | 40 | 1640 | 92790
PR | 141 | 04/12/24 | 263 | Suniga Aviles, Kelvin A | 24 | 504 | 92807
PR | 141 | 04/19/24 | 458 | Molina, Carlos G | 16 | 416 | 2752
PR | 141 | 04/19/24 | 461 | Paco Leyva, Orlando | 12 | 732 | 2755
PR | 141 | 04/19/24 | 470 | Zuniga Avilez, Eduar A | 40 | 800 | 2764
PR | 141 | 04/19/24 | 527 | Mendoza Morales, Jesus A | 40 | 1640 | 92820
PR | 141 | 04/19/24 | 544 | Suniga Aviles, Kelvin A | 40 | 840 | 92837
PR | 141 | 04/26/24 | 770 | Anderson, Richard P | 1 | 65 | 2765
PR | 141 | 04/26/24 | 783 | Molina, Carlos G | 24 | 624 | 2778
PR | 141 | 04/26/24 | 786 | Paco Leyva, Orlando | 13 | 793 | 2781
PR | 141 | 04/26/24 | 795 | Zuniga Avilez, Eduar A | 40 | 800 | 2790
PR | 141 | 04/26/24 | 851 | Mendoza Morales, Jesus A | 31.5 | 1291.5 | 92845
PR | 141 | 05/03/24 | 4 | Barnhart, Joseph N | 2 | 136 | 2792
PR | 141 | 05/03/24 | 18 | Paco Leyva, Orlando | 10 | 610 | 2806
PR | 141 | 05/03/24 | 25 | Zuniga Avilez, Eduar A | 24 | 480 | 2813
PR | 141 | 05/03/24 | 78 | Mendoza Morales, Jesus A | 32 | 1312 | 92865
PR | 141 | 05/03/24 | 93 | Suniga Aviles, Kelvin A | 16 | 336 | 92880
PR | 141 | 05/10/24 | 256 | Paco Leyva, Orlando | 10 | 610 | 2827
PR | 141 | 05/10/24 | 263 | Zuniga Avilez, Eduar A | 40 | 800 | 2834
PR | 141 | 05/10/24 | 316 | Mendoza Morales, Jesus A | 40 | 1640 | 92886
PR | 141 | 05/10/24 | 331 | Suniga Aviles, Kelvin A | 24 | 504 | 92901
PR | 141 | 05/17/24 | 484 | Paco Leyva, Orlando | 10 | 610 | 2852
PR | 141 | 05/17/24 | 539 | Martinez Garcia, Cesar B | 8 | 160 | 92906
PR | 141 | 05/17/24 | 543 | Mendoza Morales, Jesus A | 32 | 1312 | 92910
PR | 141 | 05/17/24 | 558 | Suniga Aviles, Kelvin A | 16 | 336 | 92925
PR | 141 | 05/17/24 | 569 | Zuniga Avilez, Eduar A | 24 | 480 | 92936
PR | 141 | 05/24/24 | 692 | Paco Leyva, Orlando | 13 | 793 | 2877
PR | 141 | 05/24/24 | 739 | Lima Romero, Melvin A | 20 | 880 | 92923
PR | 141 | 05/24/24 | 748 | Mendoza Morales, Jesus A | 40 | 1640 | 92932
PR | 141 | 05/31/24 | 792 | Anderson, Richard P | 1 | 65 | 2883
PR | 141 | 05/31/24 | 806 | Paco Leyva, Orlando | 11 | 671 | 2897
PR | 141 | 05/31/24 | 851 | Lima Romero, Melvin A | 24 | 1056 | 92941
PR | 141 | 05/31/24 | 860 | Mendoza Morales, Jesus A | 32 | 1312 | 92950
PR | 141 | 05/31/24 | 875 | Suniga Aviles, Kelvin A | 16 | 336 | 92965
PR | 141 | 06/07/24 | 80 | Anderson, Richard P | 4 | 260 | 2904
PR | 141 | 06/07/24 | 95 | Paco Leyva, Orlando | 16 | 976 | 2919
PR | 141 | 06/07/24 | 149 | Mendoza Morales, Jesus A | 32 | 1312 | 92971
PR | 141 | 06/07/24 | 164 | Suniga Aviles, Kelvin A | 16 | 336 | 92986
PR | 141 | 06/07/24 | 173 | Zuniga Avilez, Eduar A | 8 | 160 | 92995
GL | 141 | 06/11/24 | 268 | Reimb |  | -370.78
PR | 141 | 06/14/24 | 305 | Barnhart, Joseph N | 1 | 68 | 2925
PR | 141 | 06/14/24 | 318 | Paco Leyva, Orlando | 17 | 1037 | 2938
PR | 141 | 06/14/24 | 363 | Lima Romero, Melvin A | 16 | 704 | 92982
PR | 141 | 06/14/24 | 372 | Mendoza Morales, Jesus A | 32 | 1312 | 92991
PR | 141 | 06/21/24 | 491 | Paco Leyva, Orlando | 12 | 732 | 2955
PR | 141 | 06/21/24 | 534 | Lima Romero, Melvin A | 8 | 352 | 92997
PR | 141 | 06/21/24 | 542 | Mendoza Morales, Jesus A | 16 | 656 | 93005
PR | 141 | 06/21/24 | 552 | Romero Garza, Jesus I | 24 | 792 | 93015
PR | 141 | 06/28/24 | 698 | Paco Leyva, Orlando | 9 | 549 | 2971
PR | 141 | 06/28/24 | 741 | Lima Romero, Melvin A | 8 | 352 | 93013
PR | 141 | 06/28/24 | 749 | Mendoza Morales, Jesus A | 16 | 656 | 93021
PR | 141 | 07/05/24 | 14 | Paco Leyva, Orlando | 8 | 488 | 2986
PR | 141 | 07/05/24 | 42 | Escobar Ramirez, Carlos M | 16 | 320 | 93014
PR | 141 | 07/05/24 | 61 | Mendoza Morales, Jesus A | 8 | 328 | 93033
PR | 141 | 07/05/24 | 74 | Suniga Aviles, Kelvin A | 21 | 441 | 93046
PR | 141 | 07/05/24 | 83 | Zuniga Avilez, Eduar A | 16 | 320 | 93055
PR | 141 | 07/12/24 | 176 | Paco Leyva, Orlando | 7 | 427 | 3000
PR | 141 | 07/12/24 | 210 | Gochez Molina, Douglas O | 16 | 400 | 93034
PR | 141 | 07/12/24 | 217 | Lima Romero, Melvin A | 24 | 1056 | 93041
PR | 141 | 07/12/24 | 224 | Mendoza Morales, Jesus A | 16 | 656 | 93048
PR | 141 | 07/12/24 | 236 | Suniga Aviles, Kelvin A | 8 | 168 | 93060
PR | 141 | 07/19/24 | 383 | Paco Leyva, Orlando | 11 | 671 | 3013
PR | 141 | 07/19/24 | 390 | Barnhart, Joseph N | 0.5 | 34 | 93020
PR | 141 | 07/19/24 | 410 | Escobar Ramirez, Carlos M | 16 | 320 | 93040
PR | 141 | 07/19/24 | 423 | Lima Romero, Melvin A | 8 | 352 | 93053
PR | 141 | 07/19/24 | 430 | Mendoza Morales, Jesus A | 16 | 656 | 93060
PR | 141 | 07/19/24 | 443 | Suniga Aviles, Kelvin A | 8 | 168 | 93073
PR | 141 | 07/19/24 | 453 | Zuniga Avilez, Eduar A | 16 | 320 | 93083
PR | 141 | 07/26/24 | 571 | Paco Leyva, Orlando | 6 | 366 | 3023
PR | 141 | 07/26/24 | 598 | Escobar Ramirez, Carlos M | 4 | 80 | 93050
PR | 141 | 07/26/24 | 617 | Mendoza Morales, Jesus A | 24 | 984 | 93069
PR | 141 | 07/26/24 | 630 | Suniga Aviles, Kelvin A | 8 | 168 | 93082
PR | 141 | 07/26/24 | 640 | Zuniga Avilez, Eduar A | 4 | 80 | 93092
PR | 141 | 08/02/24 | 11 | Paco Leyva, Orlando | 10 | 610 | 3034
PR | 141 | 08/02/24 | 50 | Lima Romero, Melvin A | 16 | 704 | 93073
PR | 141 | 08/02/24 | 51 | Lopez, Maslin A | 16 | 528 | 93074
PR | 141 | 08/02/24 | 57 | Mendoza Morales, Jesus A | 24 | 984 | 93080
PR | 141 | 08/02/24 | 80 | Zuniga Avilez, Eduar A | 20 | 400 | 93103
PR | 141 | 08/09/24 | 244 | Galdamez, Dagoberto A | 8 | 336 | 3044
PR | 141 | 08/09/24 | 246 | Paco Leyva, Orlando | 7 | 427 | 3046
PR | 141 | 08/09/24 | 284 | Lima Romero, Melvin A | 16 | 704 | 23084
PR | 141 | 08/09/24 | 291 | Mendoza Morales, Jesus A | 24 | 984 | 23091
PR | 141 | 08/09/24 | 314 | Zuniga Avilez, Eduar A | 8 | 160 | 23114
PR | 141 | 08/16/24 | 437 | Paco Leyva, Orlando | 12 | 732 | 3057
PR | 141 | 08/16/24 | 473 | Lima Romero, Melvin A | 16 | 704 | 33093
PR | 141 | 08/16/24 | 480 | Mendoza Morales, Jesus A | 8 | 328 | 33100
PR | 141 | 08/23/24 | 699 | Paco Leyva, Orlando | 9 | 549 | 3068
PR | 141 | 08/23/24 | 709 | Boss, Benjamin T | 8 | 408 | 43078
PR | 141 | 08/23/24 | 742 | Mendoza Morales, Jesus A | 8 | 328 | 43111
PR | 141 | 08/23/24 | 755 | Suniga Aviles, Kelvin A | 24 | 504 | 43124
PR | 141 | 08/23/24 | 765 | Zuniga Avilez, Eduar A | 24 | 480 | 43134
PR | 141 | 08/30/24 | 842 | Paco Leyva, Orlando | 14 | 854 | 3087
PR | 141 | 08/30/24 | 907 | Zuniga Avilez, Eduar A | 8 | 160 | 53152
PR | 141 | 09/06/24 | 18 | Paco Leyva, Orlando | 5 | 305 | 3098
PR | 141 | 09/13/24 | 281 | Suniga Aviles, Kelvin A | 4 | 84 | 23164
PR | 141 | 09/13/24 | 291 | Zuniga Avilez, Eduar A | 8 | 160 | 23174
PR | 141 | 09/20/24 | 452 | Suniga Aviles, Kelvin A | 12 | 252 | 33176
PR | 141 | 09/20/24 | 462 | Zuniga Avilez, Eduar A | 8 | 160 | 33186
PR | 141 | 09/27/24 | 569 | Lima Romero, Melvin A | 8 | 352 | 43168
PR | 141 | 09/27/24 | 598 | Zuniga Avilez, Eduar A | 8 | 160 | 43197
PR | 141 | 10/04/24 | 59 | Mendoza Morales, Jesus A | 4 | 164 | 13188
PR | 141 | 10/04/24 | 72 | Suniga Aviles, Kelvin A | 40 | 840 | 13201
PR | 141 | 10/04/24 | 82 | Zuniga Avilez, Eduar A | 24 | 480 | 13211
PR | 141 | 10/11/24 | 226 | Paco Leyva, Orlando | 16 | 976 | 3160
PR | 141 | 10/11/24 | 237 | Carmona, Raul O | 8 | 424 | 23171
PR | 141 | 10/11/24 | 260 | Lima Romero, Melvin A | 16 | 704 | 23194
PR | 141 | 10/11/24 | 266 | Mendoza Morales, Jesus A | 24 | 984 | 23200
PR | 141 | 10/18/24 | 439 | Paco Leyva, Orlando | 2 | 122 | 3172
PR | 141 | 10/18/24 | 450 | Carmona, Raul O | 8 | 424 | 33183
PR | 141 | 10/18/24 | 477 | Mendoza Morales, Jesus A | 4 | 164 | 33210
PR | 141 | 10/25/24 | 584 | Galdamez, Dagoberto A | 8 | 336 | 3181
PR | 141 | 10/25/24 | 619 | Lopez, Maslin A | 8 | 264 | 43216
PR | 141 | 11/01/24 | 16 | Paco Leyva, Orlando | 4 | 244 | 3196
PR | 141 | 11/01/24 | 53 | Mendoza Morales, Jesus A | 24 | 984 | 13233
PR | 141 | 11/08/24 | 136 | Paco Leyva, Orlando | 3 | 183 | 3208
PR | 141 | 11/08/24 | 168 | Lima Romero, Melvin A | 16 | 704 | 23240
PR | 141 | 11/15/24 | 353 | Galdamez, Dagoberto A | 8 | 336 | 3217
PR | 141 | 11/15/24 | 356 | Paco Leyva, Orlando | 3 | 183 | 3220
PR | 141 | 11/15/24 | 366 | Carmona, Raul O | 16 | 848 | 33230
PR | 141 | 11/15/24 | 388 | Lima Romero, Melvin A | 24 | 1056 | 33252
PR | 141 | 11/15/24 | 389 | Lopez, Maslin A | 8 | 264 | 33253
PR | 141 | 11/22/24 | 543 | Lima Romero, Melvin A | 8 | 352 | 43265
PR | 141 | 11/29/24 | 669 | Carmona, Raul O | 8 | 424 | 53255
PR | 141 | 11/29/24 | 691 | Lima Romero, Melvin A | 4 | 176 | 53277
PR | 141 | 12/06/24 | 58 | Galdamez, Dagoberto A | 16 | 672 | 3254
PR | 141 | 12/06/24 | 61 | Paco Leyva, Orlando | 16 | 976 | 3257
PR | 141 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I | 16 | 704 | 13263
PR | 141 | 12/06/24 | 71 | Carmona, Raul O | 4 | 212 | 13267
PR | 141 | 12/13/24 | 241 | Galdamez, Dagoberto A | 8 | 336 | 3276
PR | 141 | 12/13/24 | 243 | Paco Leyva, Orlando | 10 | 610 | 3278
PR | 141 | 12/13/24 | 276 | Lopez, Maslin A | 8 | 264 | 23311
PR | 141 | 12/20/24 | 428 | Galdamez, Dagoberto A | 16 | 672 | 3286
PR | 141 | 12/20/24 | 430 | Paco Leyva, Orlando | 12 | 732 | 3288
PR | 141 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I | 8 | 352 | 33294
PR | 141 | 12/20/24 | 437 | Barnhart, Joseph N | 1 | 68 | 33295
PR | 141 | 12/20/24 | 440 | Carmona, Raul O | 24 | 1272 | 33298
PR | 141 | 12/27/24 | 546 | Galdamez, Dagoberto A | 4 | 168 | 3297
PR | 141 | 12/27/24 | 548 | Paco Leyva, Orlando | 8 | 488 | 3299
PR | 141 | 12/27/24 | 559 | Carmona, Raul O | 8 | 424 | 43309
PR | 141 | 01/10/25 | 183 | Paco Leyva, Orlando | 2 | 122 | 3321
PR | 141 | 01/17/25 | 381 | Mendoza Morales, Jesus A | 8 | 328 | 33367
PR | 141 | 01/17/25 | 384 | Paco Leyva, Orlando | 2 | 122 | 33370
PR | 141 | 01/31/25 | 743 | Paco Leyva, Orlando | 4 | 244 | 53391
PR | 141 | 02/21/25 | 357 | Paco Leyva, Orlando | 6 | 366 | 33419
PR | 141 | 03/07/25 | 60 | Paco Leyva, Orlando | 2 | 122 | 13440
PR | 141 | 03/07/25 | 99 | Lopez, Maslin A | 4 | 132 | 13460
PR | 141 | 04/18/25 | 409 | Anderson, Richard P | 2 | 195 | 3467
PR | 141 | 04/18/25 | 409 | Anderson, Richard P | 4 | 260 | 3467
PR | 141 | 04/18/25 | 411 | Castro, Marcus J | 6 | 198 | 3469
PR | 141 | 04/18/25 | 412 | Cosentino, Brandon C | 6 | 144 | 3470
PR | 141 | 04/18/25 | 413 | Cruz Reyes, Jose | 6 | 369 | 3471
PR | 141 | 04/18/25 | 418 | Waites, Thaddeus Z | 2 | 183 | 3476
PR | 141 | 04/18/25 | 418 | Waites, Thaddeus Z | 4 | 244 | 3476
PR | 141 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A | 6 | 459 | 33477
PR | 141 | 04/18/25 | 422 | Ascencio, Jose L | 6 | 378 | 33480
PR | 141 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I | 6 | 396 | 33481
PR | 141 | 04/18/25 | 424 | Barnhart, Joseph N | 4 | 408 | 33482
PR | 141 | 04/18/25 | 424 | Barnhart, Joseph N | 2 | 136 | 33482
PR | 141 | 04/18/25 | 426 | Carmona, Raul O | 6 | 477 | 33484
PR | 141 | 04/18/25 | 435 | Eisenhauer, Tommy J | 4 | 342 | 33493
PR | 141 | 04/18/25 | 435 | Eisenhauer, Tommy J | 8 | 456 | 33493
PR | 141 | 04/18/25 | 436 | Eliassen, Cory H | 6 | 228 | 33494
PR | 141 | 04/18/25 | 437 | Games, Jordan M | 10 | 795 | 33495
PR | 141 | 04/18/25 | 439 | Gerard, Jordan E | 6 | 540 | 33497
PR | 141 | 04/18/25 | 441 | Gochez Molina, Douglas O | 6 | 225 | 33499
PR | 141 | 04/18/25 | 443 | Goodwin, Marcus A | 6 | 225 | 33501
PR | 141 | 04/18/25 | 449 | Lopez, Maslin A | 6 | 198 | 33507
PR | 141 | 04/18/25 | 453 | Melgar Moz, Brandon | 6 | 198 | 33511
PR | 141 | 04/18/25 | 454 | Mendoza Morales, Jesus A | 6 | 369 | 33512
PR | 141 | 04/18/25 | 457 | Paco Leyva, Orlando | 2 | 183 | 33515
PR | 141 | 04/18/25 | 457 | Paco Leyva, Orlando | 8 | 488 | 33515
PR | 141 | 04/18/25 | 458 | Perez Araque, Manuel A | 6 | 225 | 33516
PR | 141 | 04/18/25 | 459 | Portillo Soriano, Walter A | 6 | 315 | 33517
PR | 141 | 04/18/25 | 462 | Rodriguez Arevalos, Christian | 6 | 459 | 33520
PR | 141 | 04/18/25 | 466 | Suniga Aviles, Kelvin A | 6 | 189 | 33524
PR | 141 | 04/18/25 | 468 | Taylor, Evan R | 6 | 312 | 33526
PR | 141 | 04/18/25 | 469 | Trower-Kelly, Fidel D | 6 | 279 | 33527
PR | 141 | 04/18/25 | 473 | Yohannes Jr., Samson | 6 | 198 | 33531
PR | 141 | 04/18/25 | 475 | Zuniga Avilez, Eduar A | 6 | 198 | 33533
PR | 141 | 04/25/25 | 560 | Araque, Mario W | 6 | 198 | 43489
PR | 141 | 04/25/25 | 602 | Romero Garza, Jesus I | 6 | 297 | 43531
PR | 141 | 06/27/25 | 476 | Barnhart, Joseph N | 2 | 136 | 43569
PR | 141 | 07/18/25 | 333 | Lopez, Maslin A | 2 | 66 | 33612
PR | 141 | 07/25/25 | 479 | Barnhart, Joseph N | 1 | 68 | 43597
PR | 141 | 11/21/25 | 336 | Barnhart, Joseph N | 3.75 | 255 | 33705
PR | 141 | 11/28/25 | 519 | Barnhart, Joseph N | 0.25 | 17 | 43709
PR | 141 | 02/20/26 | 336 | Nunez Bravo, Jose L | 8 | 192 | 33800
PR | 141 | 02/20/26 | 337 | Paco Leyva, Orlando | 2.5 | 157.5 | 33801
PR | 141 | 02/20/26 | 337 | Paco Leyva, Orlando | 0.5 | 31.5 | 33801
PR | 142 | 04/05/24 | 2 | Anderson, Richard P | 1 | 65 | 2678
PR | 142 | 04/12/24 | 166 | Barnhart, Joseph N | 1 | 68 | 2711
PR | 142 | 05/24/24 | 678 | Anderson, Richard P | 2 | 130 | 2863
PR | 142 | 05/24/24 | 679 | Barnhart, Joseph N | 3 | 204 | 2864
PR | 142 | 05/31/24 | 875 | Suniga Aviles, Kelvin A | 8 | 168 | 92965
PR | 142 | 06/07/24 | 81 | Barnhart, Joseph N | 2 | 136 | 2905
PR | 142 | 06/14/24 | 305 | Barnhart, Joseph N | 4 | 272 | 2925
PR | 142 | 06/28/24 | 687 | Barnhart, Joseph N | 3 | 204 | 2960
PR | 142 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I | 8 | 352 | 23052
PR | 142 | 08/09/24 | 253 | Barnhart, Joseph N | 2 | 136 | 23053
PR | 142 | 08/09/24 | 284 | Lima Romero, Melvin A | 8 | 352 | 23084
PR | 142 | 08/16/24 | 428 | Anderson, Richard P | 1 | 65 | 3048
PR | 142 | 08/16/24 | 437 | Paco Leyva, Orlando | 3 | 183 | 3057
PR | 142 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I | 31 | 1364 | 33063
PR | 142 | 08/16/24 | 444 | Barnhart, Joseph N | 1 | 68 | 33064
PR | 142 | 08/16/24 | 473 | Lima Romero, Melvin A | 16 | 704 | 33093
PR | 142 | 08/23/24 | 705 | Balderas Ortiz, Ricardo I | 16 | 704 | 43074
PR | 142 | 08/30/24 | 833 | Anderson, Richard P | 1 | 65 | 3078
PR | 142 | 08/30/24 | 848 | Balderas Ortiz, Ricardo I | 16 | 704 | 53093
PR | 142 | 08/30/24 | 849 | Barnhart, Joseph N | 3 | 204 | 53094
PR | 142 | 08/30/24 | 877 | Lima Romero, Melvin A | 16 | 704 | 53122
PR | 142 | 09/06/24 | 9 | Anderson, Richard P | 2 | 130 | 3089
PR | 142 | 09/06/24 | 18 | Paco Leyva, Orlando | 6 | 366 | 3098
PR | 142 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I | 24 | 1056 | 13104
PR | 142 | 09/06/24 | 25 | Barnhart, Joseph N | 4 | 272 | 13105
PR | 142 | 09/06/24 | 54 | Lima Romero, Melvin A | 24 | 1056 | 13134
PR | 142 | 09/06/24 | 61 | Mendoza Morales, Jesus A | 16 | 656 | 13141
PR | 142 | 09/06/24 | 84 | Zuniga Avilez, Eduar A | 16 | 320 | 13164
PR | 142 | 09/13/24 | 226 | Paco Leyva, Orlando | 11 | 671 | 3109
PR | 142 | 09/13/24 | 232 | Balderas Ortiz, Ricardo I | 32 | 1408 | 23115
PR | 142 | 09/13/24 | 262 | Lima Romero, Melvin A | 32 | 1408 | 23145
PR | 142 | 09/13/24 | 268 | Mendoza Morales, Jesus A | 32 | 1312 | 23151
PR | 142 | 09/13/24 | 281 | Suniga Aviles, Kelvin A | 2 | 42 | 23164
PR | 142 | 09/13/24 | 291 | Zuniga Avilez, Eduar A | 16 | 320 | 23174
PR | 142 | 09/20/24 | 398 | Paco Leyva, Orlando | 11 | 671 | 3122
PR | 142 | 09/20/24 | 404 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33128
PR | 142 | 09/20/24 | 405 | Barnhart, Joseph N | 5 | 340 | 33129
PR | 142 | 09/20/24 | 433 | Lima Romero, Melvin A | 20 | 880 | 33157
PR | 142 | 09/20/24 | 439 | Mendoza Morales, Jesus A | 32 | 1312 | 33163
PR | 142 | 09/27/24 | 525 | Anderson, Richard P | 1 | 65 | 3124
PR | 142 | 09/27/24 | 535 | Paco Leyva, Orlando | 7 | 427 | 3134
PR | 142 | 09/27/24 | 541 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43140
PR | 142 | 09/27/24 | 542 | Barnhart, Joseph N | 2 | 136 | 43141
PR | 142 | 09/27/24 | 569 | Lima Romero, Melvin A | 24 | 1056 | 43168
PR | 142 | 09/27/24 | 575 | Mendoza Morales, Jesus A | 32 | 1312 | 43174
PR | 142 | 09/27/24 | 598 | Zuniga Avilez, Eduar A | 16 | 320 | 43197
PR | 142 | 10/04/24 | 9 | Anderson, Richard P | 2 | 130 | 3138
PR | 142 | 10/04/24 | 19 | Paco Leyva, Orlando | 9 | 549 | 3148
PR | 142 | 10/04/24 | 25 | Balderas Ortiz, Ricardo I | 40 | 1760 | 13154
PR | 142 | 10/04/24 | 53 | Lima Romero, Melvin A | 40 | 1760 | 13182
PR | 142 | 10/04/24 | 59 | Mendoza Morales, Jesus A | 4 | 164 | 13188
PR | 142 | 10/04/24 | 82 | Zuniga Avilez, Eduar A | 8 | 160 | 13211
PR | 142 | 10/11/24 | 226 | Paco Leyva, Orlando | 4 | 244 | 3160
PR | 142 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I | 32 | 1408 | 23166
PR | 142 | 10/11/24 | 233 | Barnhart, Joseph N | 1 | 68 | 23167
PR | 142 | 10/11/24 | 260 | Lima Romero, Melvin A | 8 | 352 | 23194
PR | 142 | 10/18/24 | 428 | Lima Romero, Melvin A | 16 | 704 | 23230
PR | 142 | 10/18/24 | 429 | Anderson, Richard P | 3 | 195 | 3162
PR | 142 | 10/18/24 | 439 | Paco Leyva, Orlando | 4 | 244 | 3172
PR | 142 | 10/18/24 | 445 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33178
PR | 142 | 10/18/24 | 446 | Barnhart, Joseph N | 2 | 136 | 33179
PR | 142 | 10/18/24 | 448 | Boss, Benjamin T | 4 | 204 | 33181
PR | 142 | 10/18/24 | 477 | Mendoza Morales, Jesus A | 8 | 328 | 33210
PR | 142 | 10/25/24 | 577 | Anderson, Richard P | 1 | 65 | 3174
PR | 142 | 10/25/24 | 587 | Paco Leyva, Orlando | 4 | 244 | 3184
PR | 142 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I | 16 | 704 | 43190
PR | 142 | 10/25/24 | 624 | Mendoza Morales, Jesus A | 8 | 328 | 43221
PR | 142 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I | 16 | 704 | 13202
PR | 142 | 11/08/24 | 136 | Paco Leyva, Orlando | 7 | 427 | 3208
PR | 142 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I | 24 | 1056 | 23214
PR | 142 | 11/08/24 | 143 | Barnhart, Joseph N | 2 | 136 | 23215
PR | 142 | 11/08/24 | 168 | Lima Romero, Melvin A | 16 | 704 | 23240
PR | 142 | 11/15/24 | 356 | Paco Leyva, Orlando | 1 | 61 | 3220
PR | 142 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I | 16 | 704 | 33226
PR | 142 | 11/22/24 | 511 | Paco Leyva, Orlando | 5 | 305 | 3233
PR | 142 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I | 24 | 1056 | 43239
PR | 142 | 11/22/24 | 518 | Barnhart, Joseph N | 1 | 68 | 43240
PR | 142 | 11/22/24 | 543 | Lima Romero, Melvin A | 8 | 352 | 43265
PR | 142 | 11/29/24 | 649 | Anderson, Richard P | 3 | 195 | 3235
PR | 142 | 11/29/24 | 656 | Galdamez, Dagoberto A | 8 | 336 | 3242
PR | 142 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I | 16 | 704 | 53251
PR | 142 | 11/29/24 | 669 | Carmona, Raul O | 8 | 424 | 53255
PR | 142 | 12/13/24 | 241 | Galdamez, Dagoberto A | 8 | 336 | 3276
PR | 142 | 12/13/24 | 243 | Paco Leyva, Orlando | 16 | 976 | 3278
PR | 142 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I | 16 | 704 | 23284
PR | 142 | 12/13/24 | 250 | Barnhart, Joseph N | 2 | 136 | 23285
PR | 142 | 12/13/24 | 253 | Carmona, Raul O | 8 | 424 | 23288
PR | 142 | 12/20/24 | 422 | Anderson, Richard P | 2 | 130 | 3280
PR | 142 | 12/20/24 | 430 | Paco Leyva, Orlando | 16 | 976 | 3288
PR | 142 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I | 24 | 1056 | 33294
PR | 142 | 12/20/24 | 437 | Barnhart, Joseph N | 1 | 68 | 33295
PR | 142 | 12/27/24 | 539 | Anderson, Richard P | 1 | 65 | 3290
PR | 142 | 12/27/24 | 546 | Galdamez, Dagoberto A | 12 | 504 | 3297
PR | 142 | 12/27/24 | 548 | Paco Leyva, Orlando | 8 | 488 | 3299
PR | 142 | 12/27/24 | 555 | Balderas Ortiz, Ricardo I | 24 | 1056 | 43305
PR | 142 | 12/27/24 | 559 | Carmona, Raul O | 8 | 424 | 43309
PR | 142 | 01/03/25 | 19 | Galdamez, Dagoberto A | 16 | 672 | 3308
PR | 142 | 01/03/25 | 27 | Balderas Ortiz, Ricardo I | 16 | 704 | 13316
PR | 142 | 01/03/25 | 37 | Draves, Steven W | 4 | 220 | 13326
PR | 142 | 01/10/25 | 181 | Galdamez, Dagoberto A | 8 | 336 | 3319
PR | 142 | 01/10/25 | 183 | Paco Leyva, Orlando | 16 | 976 | 3321
PR | 142 | 01/10/25 | 189 | Balderas Ortiz, Ricardo I | 24 | 1056 | 23327
PR | 142 | 01/10/25 | 190 | Barnhart, Joseph N | 3 | 204 | 23328
PR | 142 | 01/17/25 | 346 | Galdamez, Dagoberto A | 8 | 336 | 3332
PR | 142 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I | 8 | 352 | 33339
PR | 142 | 01/17/25 | 354 | Barnhart, Joseph N | 1 | 68 | 33340
PR | 142 | 01/17/25 | 384 | Paco Leyva, Orlando | 12 | 732 | 33370
PR | 142 | 01/24/25 | 512 | Galdamez, Dagoberto A | 16 | 672 | 3342
PR | 142 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I | 16 | 704 | 43349
PR | 142 | 01/24/25 | 520 | Barnhart, Joseph N | 2 | 136 | 43350
PR | 142 | 01/24/25 | 551 | Paco Leyva, Orlando | 12 | 732 | 43381
PR | 142 | 01/31/25 | 704 | Galdamez, Dagoberto A | 16 | 672 | 3352
PR | 142 | 01/31/25 | 712 | Barnhart, Joseph N | 1 | 68 | 53360
PR | 142 | 01/31/25 | 736 | Lopez, Maslin A | 24 | 792 | 53384
PR | 142 | 01/31/25 | 743 | Paco Leyva, Orlando | 16 | 976 | 53391
PR | 142 | 02/07/25 | 42 | Barnhart, Joseph N | 1 | 68 | 13369
PR | 142 | 02/07/25 | 66 | Lopez, Maslin A | 12 | 396 | 13393
PR | 142 | 02/07/25 | 73 | Paco Leyva, Orlando | 16 | 976 | 13400
PR | 142 | 02/14/25 | 232 | Lopez, Maslin A | 12 | 396 | 23402
PR | 142 | 02/14/25 | 239 | Paco Leyva, Orlando | 4 | 244 | 23409
PR | 142 | 02/21/25 | 326 | Barnhart, Joseph N | 2 | 136 | 33388
PR | 142 | 02/21/25 | 350 | Lopez, Maslin A | 16 | 528 | 33412
PR | 142 | 02/21/25 | 357 | Paco Leyva, Orlando | 9 | 549 | 33419
PR | 142 | 02/28/25 | 516 | Barnhart, Joseph N | 2 | 136 | 43399
PR | 142 | 02/28/25 | 540 | Lopez, Maslin A | 4 | 132 | 43423
PR | 142 | 02/28/25 | 547 | Paco Leyva, Orlando | 12 | 732 | 43430
PR | 142 | 03/07/25 | 53 | Lopez, Maslin A | 13 | 429 | 13433
PR | 142 | 03/07/25 | 60 | Paco Leyva, Orlando | 7 | 427 | 13440
PR | 142 | 03/14/25 | 260 | Paco Leyva, Orlando | 4 | 244 | 23451
PR | 142 | 03/28/25 | 610 | Paco Leyva, Orlando | 2 | 122 | 93484
PR | 142 | 05/09/25 | 162 | Barnhart, Joseph N | 2 | 136 | 23511
PR | 142 | 05/09/25 | 192 | Paco Leyva, Orlando | 8 | 488 | 23541
PR | 142 | 05/30/25 | 545 | Barnhart, Joseph N | 3 | 204 | 53537
PR | 142 | 06/06/25 | 33 | Barnhart, Joseph N | 15.5 | 1054 | 13545
PR | 142 | 06/06/25 | 63 | Paco Leyva, Orlando | 18 | 1098 | 13575
PR | 142 | 06/13/25 | 186 | Galdamez, Dagoberto A | 12 | 504 | 3545
PR | 142 | 06/13/25 | 194 | Barnhart, Joseph N | 10 | 680 | 23553
PR | 142 | 06/13/25 | 217 | Lopez, Maslin A | 8 | 264 | 23576
PR | 142 | 06/13/25 | 225 | Paco Leyva, Orlando | 12 | 732 | 23584
PR | 142 | 06/20/25 | 322 | Barnhart, Joseph N | 9 | 612 | 33561
PR | 142 | 06/27/25 | 476 | Barnhart, Joseph N | 19 | 1292 | 43569
PR | 142 | 06/27/25 | 507 | Paco Leyva, Orlando | 8 | 488 | 43600
PR | 142 | 07/03/25 | 19 | Barnhart, Joseph N | 6 | 408 | 13576
PR | 142 | 07/11/25 | 144 | Barnhart, Joseph N | 2 | 136 | 23583
PR | 142 | 07/11/25 | 174 | Paco Leyva, Orlando | 3 | 183 | 23613
PR | 142 | 07/18/25 | 304 | Galdamez, Dagoberto A | 8 | 336 | 3583
PR | 142 | 07/18/25 | 311 | Barnhart, Joseph N | 10 | 680 | 33590
PR | 142 | 07/18/25 | 333 | Lopez, Maslin A | 2 | 66 | 33612
PR | 142 | 07/18/25 | 341 | Paco Leyva, Orlando | 6 | 366 | 33620
PR | 142 | 07/25/25 | 472 | Galdamez, Dagoberto A | 8 | 336 | 3590
PR | 142 | 07/25/25 | 479 | Barnhart, Joseph N | 4 | 272 | 43597
PR | 142 | 07/25/25 | 501 | Lopez, Maslin A | 4 | 132 | 43619
PR | 142 | 07/25/25 | 509 | Paco Leyva, Orlando | 15 | 915 | 43627
PR | 142 | 08/01/25 | 12 | Barnhart, Joseph N | 4 | 272 | 13603
PR | 142 | 08/08/25 | 143 | Barnhart, Joseph N | 9 | 612 | 23610
PR | 142 | 08/15/25 | 268 | Barnhart, Joseph N | 1 | 68 | 33615
PR | 142 | 08/29/25 | 534 | Barnhart, Joseph N | 1 | 68 | 53627
PR | 142 | 09/05/25 | 19 | Barnhart, Joseph N | 7 | 476 | 13633
PR | 143 | 08/30/24 | 852 | Boss, Benjamin T | 4 | 204 | 53097
PR | 143 | 08/30/24 | 877 | Lima Romero, Melvin A | 16 | 704 | 53122
PR | 143 | 10/18/24 | 428 | Lima Romero, Melvin A | 16 | -704 | 23230
PR | 143 | 10/18/24 | 448 | Boss, Benjamin T | 4 | -204 | 33181
PR | 150 | 09/05/25 | 13 | Hernandez Gonzalez, Osbaldo | 7 | 294 | 3627
PR | 150 | 09/05/25 | 19 | Barnhart, Joseph N | 10 | 680 | 13633
PR | 150 | 09/05/25 | 26 | Cruz, Azael S | 15 | 480 | 13640
PR | 150 | 09/05/25 | 32 | Games, Jordan M | 16 | 848 | 13646
PR | 150 | 09/05/25 | 40 | Jimenez Alvarenga, Gerson M | 7 | 273 | 13654
PR | 150 | 09/05/25 | 42 | Lopez, Maslin A | 16 | 528 | 13656
PR | 150 | 09/05/25 | 46 | Melgar Moz, Brandon | 15 | 360 | 13660
PR | 150 | 09/05/25 | 50 | Paco Leyva, Orlando | 16 | 976 | 13664
PR | 150 | 09/05/25 | 59 | Suniga Aviles, Kelvin A | 15 | 360 | 13673
PR | 150 | 09/05/25 | 63 | Zuniga Avilez, Eduar A | 15 | 360 | 13677
PR | 150 | 09/12/25 | 116 | Barnhart, Joseph N | 7 | 476 | 23638
PR | 150 | 09/12/25 | 123 | Cruz, Azael S | 16 | 512 | 23645
PR | 150 | 09/12/25 | 129 | Games, Jordan M | 31 | 1643 | 23651
PR | 150 | 09/12/25 | 139 | Lopez, Maslin A | 16 | 528 | 23661
PR | 150 | 09/12/25 | 143 | Melgar Moz, Brandon | 16 | 384 | 23665
PR | 150 | 09/12/25 | 147 | Paco Leyva, Orlando | 13 | 793 | 23669
PR | 150 | 09/12/25 | 156 | Suniga Aviles, Kelvin A | 40 | 960 | 23678
PR | 150 | 09/12/25 | 160 | Zuniga Avilez, Eduar A | 40 | 960 | 23682
PR | 150 | 09/19/25 | 248 | Barnhart, Joseph N | 29 | 1972 | 33644
PR | 150 | 09/19/25 | 261 | Games, Jordan M | 15 | 795 | 33657
PR | 150 | 09/19/25 | 270 | Lima Romero, Melvin A | 26 | 1144 | 33666
PR | 150 | 09/19/25 | 275 | Melgar Moz, Brandon | 8 | 192 | 33671
PR | 150 | 09/19/25 | 279 | Paco Leyva, Orlando | 37 | 2257 | 33675
PR | 150 | 09/19/25 | 288 | Suniga Aviles, Kelvin A | 37 | 888 | 33684
PR | 150 | 09/19/25 | 293 | Zuniga Avilez, Eduar A | 37 | 888 | 33689
PR | 150 | 09/26/25 | 419 | Barnhart, Joseph N | 2 | 136 | 43651
PR | 150 | 09/26/25 | 419 | Barnhart, Joseph N | 1.75 | 119 | 43651
PR | 150 | 09/26/25 | 419 | Barnhart, Joseph N | 0.75 | 51 | 43651
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 8 | 424 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 12.5 | 662.5 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 8.25 | 437.25 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 8 | 424 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 3.25 | 172.25 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 4.75 | 377.63 | 43664
PR | 150 | 09/26/25 | 432 | Games, Jordan M | 8 | 636 | 43664
PR | 150 | 09/26/25 | 442 | Lopez, Maslin A | 8 | 264 | 43674
PR | 150 | 09/26/25 | 442 | Lopez, Maslin A | 8 | 264 | 43674
PR | 150 | 09/26/25 | 450 | Paco Leyva, Orlando | 2.25 | 137.25 | 43682
PR | 150 | 09/26/25 | 450 | Paco Leyva, Orlando | 1 | 61 | 43682
PR | 150 | 10/03/25 | 15 | Barnhart, Joseph N | 4.25 | 289 | 13658
PR | 150 | 10/03/25 | 29 | Games, Jordan M | 4.25 | 225.25 | 13672
PR | 150 | 10/03/25 | 29 | Games, Jordan M | 3.25 | 172.25 | 13672
PR | 150 | 10/03/25 | 29 | Games, Jordan M | 3.5 | 185.5 | 13672
PR | 150 | 10/10/25 | 177 | Draves, Steven W | 5.25 | 288.75 | 23675
PR | 150 | 10/10/25 | 181 | Games, Jordan M | 8 | 424 | 23679
PR | 150 | 10/10/25 | 181 | Games, Jordan M | 0.75 | 39.75 | 23679
PR | 150 | 10/10/25 | 200 | Paco Leyva, Orlando | 0.25 | 15.25 | 23698
PR | 150 | 10/31/25 | 686 | Games, Jordan M | 2 | 106 | 53703
PR | 150 | 11/14/25 | 219 | Barnhart, Joseph N | 4.25 | 289 | 23699
PR | 150 | 11/14/25 | 219 | Barnhart, Joseph N | 2.25 | 153 | 23699
PR | 150 | 11/14/25 | 255 | Paco Leyva, Orlando | 4.25 | 259.25 | 23735
PR | 150 | 11/28/25 | 519 | Barnhart, Joseph N | 2 | 136 | 43709
PR | 150 | 12/12/25 | 182 | Barnhart, Joseph N | 0.25 | 17 | 23717
PR | 150 | 01/16/26 | 276 | Barnhart, Joseph N | 0.5 | 35 | 33741
PR | 150 | 01/16/26 | 293 | Gerard, Jeffrey S | 0.5 | 34.5 | 33758
PR | 150 | 01/30/26 | 575 | Anderson, Richard P | 1 | 67 | 53746
PR | 150 | 01/30/26 | 580 | Barnhart, Joseph N | 1.25 | 87.5 | 53751
PR | 150 | 02/06/26 | 56 | Barnhart, Joseph N | 1.75 | 122.5 | 13756
PR | 150 | 03/13/26 | 193 | Barnhart, Joseph N | 0.75 | 52.5 | 23780
PR | 151 | 06/13/25 | 190 | Aquino, Juan | 8 | 224 | 23549
AP | 210 | 10/10/23 | 297 | Consolidated Supply Co. |  | 111.35 | S011570038.001
AP | 210 | 10/17/23 | 549 | Rosen Supply Kirkland |  | 18098.35 | 14905.01
AP | 210 | 10/17/23 | 550 | Rosen Supply Kirkland |  | 3945.6 | 14911.01
GL | 210 | 10/25/23 | 790 | Req 9735 |  | 1358.72
GL | 210 | 10/25/23 | 791 | Req 9736 |  | 1152.55
GL | 210 | 10/25/23 | 792 | Req 9738 |  | 74.7
GL | 210 | 10/25/23 | 793 | Req 9737 |  | 1318.45
GL | 210 | 10/25/23 | 794 | Req 9739 |  | 1879.59
GL | 210 | 10/25/23 | 815 | Req 9711 |  | 2466.12
GL | 210 | 11/03/23 | 189 | Req 113 |  | 196.38
GL | 210 | 11/03/23 | 197 | Req 121 |  | 820.8
AP | 210 | 11/06/23 | 267 | Rosen Supply Kirkland |  | 174.69 | 16474.01
AP | 210 | 11/06/23 | 279 | Capital One Credit Card |  | 109.81 | 091323J4
AP | 210 | 11/06/23 | 284 | Capital One Credit Card |  | 109.64 | 091823J1
AP | 210 | 11/06/23 | 293 | Capital One Credit Card |  | 113.01 | 092723J
AP | 210 | 11/06/23 | 296 | Capital One Credit Card |  | 78.18 | 093023J
AP | 210 | 11/08/23 | 418 | Consolidated Supply Co. |  | 693.56 | S011602176.001
AP | 210 | 11/11/23 | 666 | Rosen Supply Kirkland |  | 8269.81 | 16659.01
AP | 210 | 11/13/23 | 682 | Consolidated Supply Co. |  | 1856.28 | S011644575.001
AP | 210 | 11/14/23 | 728 | Rosen Supply Kirkland |  | 8828.84 | 14907.01
AP | 210 | 11/14/23 | 729 | Rosen Supply Kirkland |  | 3945.6 | 14913.01
AP | 210 | 11/14/23 | 764 | Rosen Supply Kirkland |  | 23.39 | 16797.01
AP | 210 | 11/15/23 | 801 | Rosen Supply Kirkland |  | 15122.67 | 14907.02
AP | 210 | 11/19/23 | 993 | Consolidated Supply Co. |  | 5289 | S011533453.002
AP | 210 | 11/20/23 | 1038 | Rosen Supply Kirkland |  | 679.76 | 14907.03
AP | 210 | 11/20/23 | 1039 | Rosen Supply Kirkland |  | 339.79 | 17482.01
AP | 210 | 11/21/23 | 1176 | Rosen Supply Kirkland |  | 180.98 | 17320.01
GL | 210 | 11/28/23 | 1267 | Req 229 |  | 116.7
AP | 210 | 11/28/23 | 1291 | Rosen Supply Kirkland |  | 324.82 | 17946.01
AP | 210 | 11/28/23 | 1311 | Rosen Supply Kirkland |  | -1253.33 | 18070.01
AP | 210 | 11/28/23 | 1312 | Rosen Supply Kirkland |  | 735.3 | 18070.02
AP | 210 | 12/01/23 | 252 | Consolidated Supply Co. |  | 56.82 | S011647566.002
AP | 210 | 12/01/23 | 257 | Consolidated Supply Co. |  | 225.2 | S011647566.001
AP | 210 | 12/01/23 | 844 | Rosen Supply Kirkland |  | 1253.33 | 18070.01A
AP | 210 | 12/01/23 | 845 | Rosen Supply Kirkland |  | -1235.33 | 18070.01B
AP | 210 | 12/02/23 | 228 | Capital One Credit Card |  | 38.54 | 101923J1
AP | 210 | 12/02/23 | 237 | Capital One Credit Card |  | 65.97 | 102723J
AP | 210 | 12/06/23 | 303 | Rosen Supply Kirkland |  | 3945.6 | 14912.01
AP | 210 | 12/06/23 | 304 | Rosen Supply Kirkland |  | 372.6 | 17777.01
AP | 210 | 12/11/23 | 481 | Rosen Supply Kirkland |  | 797.11 | 18025.01
AP | 210 | 12/11/23 | 489 | Rosen Supply Kirkland |  | 1999.4 | 18013.01
AP | 210 | 12/13/23 | 517 | Rosen Supply Kirkland |  | 378.53 | 18084.01
AP | 210 | 12/31/23 | 1301 | Capital One Credit Card |  | 178.26 | 111223J
AP | 210 | 12/31/23 | 1306 | Capital One Credit Card |  | 48.63 | 111523J3
AP | 210 | 12/31/23 | 1317 | Capital One Credit Card |  | 54.26 | 120123J
GL | 210 | 01/07/24 | 174 | Req 308 |  | 119.47
AP | 210 | 01/15/24 | 568 | Consolidated Supply Co. |  | 5289.3 | S011533453.003
AP | 210 | 01/15/24 | 635 | Consolidated Supply Co. |  | -5289.3 | S011533453.003A
AP | 210 | 01/15/24 | 636 | Consolidated Supply Co. |  | 5289 | S011533453.003B
PR | 210 | 03/22/24 | 819 | Guerrero Espinoza, Mario | 32 | 960 | 2617
PR | 210 | 04/19/24 | 460 | Nunez Bravo, Jose L | 40 | 920 | 2754
PR | 210 | 05/03/24 | 59 | Gochez Molina, Douglas O | 40 | 1000 | 92846
PR | 210 | 05/03/24 | 61 | Gomez Aguirre, Exequiel | 32 | 768 | 92848
PR | 210 | 05/10/24 | 267 | Ascencio, Jose L | 40 | 1680 | 92838
PR | 210 | 05/24/24 | 729 | Gochez Molina, Douglas O | 40 | 1000 | 92913
PR | 210 | 06/07/24 | 171 | Yohannes Jr., Samson | 40 | 1320 | 92993
PR | 210 | 06/07/24 | 173 | Zuniga Avilez, Eduar A | 32 | 640 | 92995
PR | 210 | 07/19/24 | 383 | Paco Leyva, Orlando | 14 | 854 | 3013
AP | 210 | 02/13/25 | 614 | Rosen Supply Kirkland |  | 977.58 | 30093.01
AP | 210 | 04/11/25 | 281 | Pacific Plumbing Supply Co., LLC |  | 25 | 51823497
AP | 210 | 05/09/25 | 244 | Rosen Supply Kirkland |  | 106.17 | 31481.01
AP | 210 | 05/09/25 | 245 | Rosen Supply Kirkland |  | 625 | 30121.01
AP | 211 | 10/18/23 | 581 | Rosen Supply Kirkland |  | 62.77 | 16369.01
GL | 211 | 10/25/23 | 817 | Req 9713 |  | 324.48
GL | 211 | 10/25/23 | 821 | Req 9717 |  | 64.52
GL | 211 | 11/03/23 | 192 | Req 116 |  | 424.7
GL | 211 | 11/10/23 | 634 | Req 212 |  | 85.87
AP | 211 | 11/13/23 | 689 | Rosen Supply Kirkland |  | 69.67 | 16939.01
GL | 211 | 11/28/23 | 1266 | Req 228 |  | 121.06
AP | 211 | 12/06/23 | 305 | Rosen Supply Kirkland |  | 361.1 | 17907.01
GL | 211 | 01/07/24 | 183 | Req 317 |  | 255.33
GL | 211 | 01/10/24 | 294 | Req 353 |  | -191.82
GL | 211 | 01/12/24 | 488 | Req 380 |  | 351.66
AP | 211 | 01/24/24 | 909 | Rosen Supply Kirkland |  | 23.83 | 19280.01
AP | 211 | 01/30/24 | 1175 | Rosen Supply Kirkland |  | 919.02 | 19626.01
AP | 211 | 02/12/24 | 409 | Keller Supply Company |  | 179 | S022569453.001
GL | 211 | 02/19/24 | 629 | 2/11/24 - 2/17/24 |  | 1599.12
GL | 211 | 02/27/24 | 806 | Transfer 02/19/24 - 2/24/24 |  | 776.91
AP | 211 | 02/27/24 | 817 | Consolidated Supply Co. |  | 478.39 | S011750378.001
AP | 211 | 02/27/24 | 818 | Consolidated Supply Co. |  | 550.9 | S011750378.002
AP | 211 | 02/28/24 | 878 | Consolidated Supply Co. |  | 189.57 | S011750378.003
GL | 211 | 03/01/24 | 140 | 2/26 - 3/1 |  | 113.48
AP | 211 | 03/06/24 | 229 | Consolidated Supply Co. |  | 525.5 | S011768145.002
AP | 211 | 03/06/24 | 242 | Consolidated Supply Co. |  | 2001.4 | S011768145.001
AP | 211 | 03/06/24 | 243 | Consolidated Supply Co. |  | -389.5 | S011768145.003
AP | 211 | 03/08/24 | 415 | Rosen Supply Kirkland |  | 175.84 | 20675.01
GL | 211 | 03/13/24 | 489 | 03/04/2024 - 03/08/2024 |  | 117.83
AP | 211 | 03/19/24 | 711 | Consolidated Supply Co. |  | 603.4 | S011793167.003
AP | 211 | 03/19/24 | 732 | Rosen Supply Kirkland |  | 449.04 | 21051.01
AP | 211 | 03/20/24 | 774 | Pacific Plumbing Supply Co., LLC |  | 648.92 | 51510673
AP | 211 | 03/20/24 | 796 | Consolidated Supply Co. |  | 607.5 | S01101421.001
AP | 211 | 03/22/24 | 994 | Pacific Plumbing Supply Co., LLC |  | 452.75 | 51513739
AP | 211 | 03/22/24 | 997 | Pacific Plumbing Supply Co., LLC |  | 113.27 | 51514500
GL | 211 | 03/25/24 | 1045 | Req 444 |  | 82.56
GL | 211 | 03/25/24 | 1054 | Req 454 |  | 246.08
GL | 211 | 03/25/24 | 1075 | 03/17/2024 - 03/23-2024 |  | 613.43
GL | 211 | 03/31/24 | 1308 | 03/24/2024 - 03/30/204 |  | 157.18
AP | 211 | 03/31/24 | 1314 | Keller Supply Company |  | 42.02 | S022759717.001
AP | 211 | 03/31/24 | 1338 | Consolidated Supply Co. |  | 47.7 | S0118832796.001
GL | 211 | 04/11/24 | 285 | 03/31/2024 - 04/06/2024 |  | 86.99
GL | 211 | 04/15/24 | 398 | 04/07/24 - 04/13/24 |  | 510.48
GL | 211 | 04/15/24 | 398 | 04/07/24 - 04/13/24 |  | 1024.77
GL | 211 | 04/22/24 | 587 | 04/14/24 - 04/20/24 |  | 52
AP | 211 | 04/22/24 | 600 | Consolidated Supply Co. |  | 68.11 | S011848200.001
AP | 211 | 04/22/24 | 602 | Consolidated Supply Co. |  | 497.82 | S011851028.003
AP | 211 | 04/22/24 | 603 | Consolidated Supply Co. |  | 12.24 | S011851028.004
AP | 211 | 04/23/24 | 664 | Consolidated Supply Co. |  | 142.4 | S011848200.002
GL | 211 | 04/29/24 | 926 | 04/21/2024 to 04/27/2024 |  | 658.41
GL | 211 | 05/07/24 | 190 | 4/28/2024 to 5/04/2024 |  | 72.18
GL | 211 | 05/13/24 | 426 | 5/5/24 - 5/11/24 |  | 114
GL | 211 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 36.68
GL | 211 | 05/31/24 | 958 | Transfer 2024-05-26 to 2024-05-31 |  | 11.58
GL | 211 | 06/25/24 | 577 | Req 496 |  | 401.11
GL | 211 | 06/25/24 | 625 | 2024-06-16 to 2024-06-22 |  | 115.71
GL | 211 | 08/12/24 | 372 |  |  | 19.15
GL | 211 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 24.43
AP | 211 | 08/20/24 | 567 | Pacific Plumbing Supply Co., LLC |  | 9.55 | 51638008
GL | 211 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 18.25
GL | 211 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 311.27
GL | 211 | 09/09/24 | 297 | 2024-09-01 to 2024-09-07 |  | 159.04
GL | 211 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 8.11
GL | 211 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 34.9
GL | 211 | 10/15/24 | 345 | 2024-10-06 to 2024-10-12 |  | 82.5
GL | 211 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 27.5
GL | 211 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 16.22
AP | 211 | 10/28/24 | 694 | ACME Corp |  | 12.95 | S4602447.001
AP | 211 | 10/28/24 | 696 | ACME Corp |  | 4.21 | S4602447.002
AP | 211 | 11/15/24 | 457 | Pacific Plumbing Supply Co., LLC |  | 252.94 | 51713291
GL | 211 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 50.56
GL | 211 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 29.66
GL | 211 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 158.98
AP | 211 | 01/08/25 | 155 | Pacific Plumbing Supply Co., LLC |  | 83.9 | 51739431
AP | 211 | 01/08/25 | 163 | Pacific Plumbing Supply Co., LLC |  | 89.43 | 51740510
AP | 211 | 01/28/25 | 656 | Pacific Plumbing Supply Co., LLC |  | 234.59 | 51764336
GL | 211 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 13
GL | 211 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 68.19
GL | 211 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 7.8
GL | 211 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | -4.8
GL | 211 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 35.56
GL | 211 | 05/12/25 | 271 | Req 655 |  | -852.14
GL | 211 | 05/31/25 | 681 | 2025-05-26 to 2025-05-30 |  | 47.9
GL | 211 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 2.65
GL | 211 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 13.07
GL | 211 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 36.5
GL | 211 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | -4.63
GL | 211 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 10.22
AP | 211 | 08/26/25 | 470 | Capital One Credit Card |  | 10.07 | 080725J2
GL | 211 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -72.4
GL | 212 | 10/27/23 | 972 | Richard Anderson |  | 127.4
GL | 212 | 11/03/23 | 190 | Req 114 |  | 4953.43
AP | 212 | 11/20/23 | 1040 | Rosen Supply Kirkland |  | 500.3 | 17519.02
AP | 212 | 12/20/23 | 902 | ACME Corp |  | 127.8 | S4411769.001
GL | 212 | 01/07/24 | 180 | Req 314 |  | 6562.73
AP | 212 | 01/08/24 | 236 | Keller Supply Company |  | 1306.75 | S022429612.001
AP | 212 | 01/08/24 | 237 | Keller Supply Company |  | 2613.5 | S022445939.001
AP | 212 | 01/10/24 | 309 | Keller Supply Company |  | 7650.6 | S022461302.001
GL | 212 | 01/12/24 | 490 | Req 382 |  | 101.2
AP | 212 | 01/12/24 | 525 | Rosen Supply Kirkland |  | 222.63 | 18735.01
AP | 212 | 01/23/24 | 858 | Keller Supply Company |  | 784.05 | S022509258.001
GL | 212 | 01/23/24 | 865 | Req 396 |  | -1023.07
GL | 220 | 10/25/23 | 816 | Req 9712 |  | 424.74
GL | 220 | 10/25/23 | 819 | Req 9715 |  | 35.12
GL | 220 | 10/25/23 | 820 | Req 9716 |  | 189.77
GL | 220 | 11/03/23 | 191 | Req 115 |  | 1865.45
GL | 220 | 11/10/23 | 633 | Req 211 |  | 428
AP | 220 | 11/14/23 | 768 | Rosen Supply Kirkland |  | 591.94 | 16977.01
GL | 220 | 11/28/23 | 1268 | Req 230 |  | 538.77
AP | 220 | 12/18/23 | 838 | Rosen Supply Kirkland |  | 388.99 | 18276.01
GL | 220 | 01/07/24 | 182 | Req 316 |  | 2986.26
GL | 220 | 01/23/24 | 872 | Req 403 |  | 208.8
AP | 220 | 01/29/24 | 1124 | Capital One Credit Card |  | 69.23 | 010324J2
AP | 220 | 01/30/24 | 1173 | Rosen Supply Kirkland |  | 11555.9 | 19565.01
AP | 220 | 01/30/24 | 1181 | Rosen Supply Kirkland |  | 14972.53 | 19565.02
AP | 220 | 02/12/24 | 395 | Keller Supply Company |  | 691.33 | S022538142.001
AP | 220 | 02/12/24 | 427 | Rosen Supply Kirkland |  | 4062.4 | 19820.01
GL | 220 | 02/19/24 | 629 | 2/11/24 - 2/17/24 |  | 1914.05
GL | 220 | 02/27/24 | 806 | Transfer 02/19/24 - 2/24/24 |  | 2645.96
AP | 220 | 02/27/24 | 853 | Capital One Credit Card |  | 87.63 | 010924J
AP | 220 | 02/27/24 | 864 | Capital One Credit Card |  | 11.31 | 012424J3
AP | 220 | 02/28/24 | 872 | Consolidated Supply Co. |  | 2389 | S011758032.001
GL | 220 | 03/01/24 | 140 | 2/26 - 3/1 |  | 1162.63
AP | 220 | 03/01/24 | 758 | Rosen Supply Kirkland |  | 11365.35 | 21242.01
AP | 220 | 03/05/24 | 155 | Pacific Plumbing Supply Co., LLC |  | 715.37 | 51484371
AP | 220 | 03/06/24 | 195 | Pacific Plumbing Supply Co., LLC |  | 566.17 | 51500541
AP | 220 | 03/06/24 | 196 | Pacific Plumbing Supply Co., LLC |  | 1014.57 | 51501818
AP | 220 | 03/06/24 | 217 | Consolidated Supply Co. |  | 421.16 | S011766226.001
AP | 220 | 03/06/24 | 220 | Consolidated Supply Co. |  | 570.88 | S011773932.001
AP | 220 | 03/06/24 | 244 | Consolidated Supply Co. |  | 1312.5 | S011776477.001
AP | 220 | 03/08/24 | 408 | Rosen Supply Kirkland |  | 11879.65 | 20506.01
AP | 220 | 03/08/24 | 417 | Rosen Supply Kirkland |  | 1764.78 | 20673.01
AP | 220 | 03/08/24 | 418 | Rosen Supply Kirkland |  | 672 | 20715.01
AP | 220 | 03/11/24 | 435 | Consolidated Supply Co. |  | 5611.49 | S011776216.001
AP | 220 | 03/11/24 | 448 | Consolidated Supply Co. |  | 410.71 | S011789476.001
AP | 220 | 03/11/24 | 453 | Consolidated Supply Co. |  | 147.99 | S011789476.002
AP | 220 | 03/11/24 | 454 | Consolidated Supply Co. |  | -309.87 | S011789476.003
GL | 220 | 03/13/24 | 489 | 03/04/2024 - 03/08/2024 |  | 2371.95
AP | 220 | 03/14/24 | 502 | Keller Supply Company |  | 394.17 | S022668184.001
GL | 220 | 03/18/24 | 677 | 3/10/24 - 3/16/24 |  | 3154.56
AP | 220 | 03/19/24 | 710 | Consolidated Supply Co. |  | 5264.63 | S011776490.001
AP | 220 | 03/19/24 | 712 | Consolidated Supply Co. |  | 10407 | S011787302.001
AP | 220 | 03/19/24 | 731 | Rosen Supply Kirkland |  | 56.3 | 20987.01
AP | 220 | 03/19/24 | 733 | Rosen Supply Kirkland |  | 536.2 | 21049.01
AP | 220 | 03/19/24 | 741 | Rosen Supply Kirkland |  | -1764.78 | 21102.01
AP | 220 | 03/19/24 | 742 | Rosen Supply Kirkland |  | 1389.12 | 21102.02
AP | 220 | 03/19/24 | 743 | Rosen Supply Kirkland |  | -294.12 | 21103.01
AP | 220 | 03/19/24 | 744 | Rosen Supply Kirkland |  | 231.52 | 21103.02
AP | 220 | 03/19/24 | 754 | Rosen Supply Kirkland |  | 347.28 | 21235.01
AP | 220 | 03/20/24 | 797 | Consolidated Supply Co. |  | 3014.06 | S011802836.001
GL | 220 | 03/25/24 | 1050 | Req 450 |  | 2141.3
GL | 220 | 03/25/24 | 1051 | Req 451 |  | 1375.92
GL | 220 | 03/25/24 | 1064 | Req 464 |  | 242.02
GL | 220 | 03/25/24 | 1075 | 03/17/2024 - 03/23-2024 |  | 2459.97
AP | 220 | 03/26/24 | 1116 | Consolidated Supply Co. |  | 5611.49 | S011776548.001
AP | 220 | 03/26/24 | 1122 | Consolidated Supply Co. |  | 735.7 | S011819044.001
AP | 220 | 03/27/24 | 1149 | Rosen Supply Kirkland |  | 856.7 | 21563.01
AP | 220 | 03/27/24 | 1162 | Rosen Supply Kirkland |  | 468.46 | 21666.01
GL | 220 | 03/31/24 | 1308 | 03/24/2024 - 03/30/204 |  | 2371.51
AP | 220 | 03/31/24 | 1313 | Consolidated Supply Co. |  | 2369.26 | S011819044.002
AP | 220 | 03/31/24 | 1324 | Consolidated Supply Co. |  | 406.08 | S011825087.001
AP | 220 | 03/31/24 | 1337 | Consolidated Supply Co. |  | 5611.49 | S011776571.001
AP | 220 | 04/01/24 | 717 | Capital One Credit Card |  | 48.7 | 031124J
AP | 220 | 04/01/24 | 731 | Capital One Credit Card |  | 88 | 032724J2
AP | 220 | 04/01/24 | 737 | Capital One Credit Card |  | 78.69 | 040124J2
AP | 220 | 04/01/24 | 754 | Consolidated Supply Co. |  | 2007.35 | S011864821.001
GL | 220 | 04/12/24 | 303 | Req 483 |  | 205.19
GL | 220 | 04/12/24 | 304 | Req 484 |  | 171
AP | 220 | 04/15/24 | 355 | Consolidated Supply Co. |  | 1242.73 | S011839986.001
AP | 220 | 04/15/24 | 363 | Consolidated Supply Co. |  | 1506.42 | S011819044.003
AP | 220 | 04/15/24 | 382 | Rosen Supply Kirkland |  | 7701.49 | 21563.03
AP | 220 | 04/15/24 | 383 | Rosen Supply Kirkland |  | 445.68 | 21824.01
AP | 220 | 04/15/24 | 384 | Rosen Supply Kirkland |  | 1157.6 | 21563.06
AP | 220 | 04/16/24 | 416 | Pacific Plumbing Supply Co., LLC |  | 3580 | 51529465
AP | 220 | 04/18/24 | 559 | Consolidated Supply Co. |  | 534.39 | S011844578.001
AP | 220 | 04/18/24 | 562 | Consolidated Supply Co. |  | -534.39 | S011839986.003
AP | 220 | 04/19/24 | 580 | Consolidated Supply Co. |  | 2936.9 | S011844117.001
GL | 220 | 04/22/24 | 587 | 04/14/24 - 04/20/24 |  | 1701.34
AP | 220 | 04/22/24 | 594 | Consolidated Supply Co. |  | 5611.49 | S011776702.001
AP | 220 | 04/22/24 | 595 | Consolidated Supply Co. |  | 563.09 | S011838194.002
AP | 220 | 04/23/24 | 641 | Consolidated Supply Co. |  | 297.75 | S011865183.001
AP | 220 | 04/23/24 | 654 | Consolidated Supply Co. |  | 2422.39 | S011856350.002
AP | 220 | 04/23/24 | 655 | Consolidated Supply Co. |  | 70.94 | S011865183.003
AP | 220 | 04/23/24 | 656 | Consolidated Supply Co. |  | -27.93 | S011865183.004
AP | 220 | 04/23/24 | 657 | Consolidated Supply Co. |  | -70.94 | S011865183.005
AP | 220 | 04/23/24 | 662 | Consolidated Supply Co. |  | 5611.49 | S011776675.001
AP | 220 | 04/23/24 | 663 | Consolidated Supply Co. |  | 388.52 | S011844117.002
AP | 220 | 04/26/24 | 891 | Pacific Plumbing Supply Co., LLC |  | 25.71 | 51540558
GL | 220 | 04/29/24 | 926 | 04/21/2024 to 04/27/2024 |  | 1521.01
AP | 220 | 04/30/24 | 958 | Rosen Supply Kirkland |  | 471.9 | 22319.01
AP | 220 | 04/30/24 | 989 | Consolidated Supply Co. |  | 281.25 | S011844117.003
AP | 220 | 04/30/24 | 990 | Consolidated Supply Co. |  | 946 | S011846821.002
AP | 220 | 04/30/24 | 993 | Consolidated Supply Co. |  | 1728.95 | S011869617.001
AP | 220 | 04/30/24 | 1001 | Consolidated Supply Co. |  | 787.07 | S011872570.001
AP | 220 | 04/30/24 | 1002 | Rosen Supply Kirkland |  | 767.46 | 22433.01
AP | 220 | 04/30/24 | 1003 | Rosen Supply Kirkland |  | 1066.32 | 22607.001
AP | 220 | 04/30/24 | 1018 | Consolidated Supply Co. |  | 98.03 | S011856350.003
AP | 220 | 04/30/24 | 1019 | Consolidated Supply Co. |  | 2603.99 | S011878429.001
AP | 220 | 04/30/24 | 1021 | Consolidated Supply Co. |  | 814.8 | S011881177.001
AP | 220 | 05/02/24 | 109 | Rosen Supply Kirkland |  | 1017.91 | 22693.01
AP | 220 | 05/02/24 | 114 | Consolidated Supply Co. |  | 3815.46 | S011872006.001
AP | 220 | 05/02/24 | 119 | Consolidated Supply Co. |  | 3981.51 | S011883173.001
AP | 220 | 05/06/24 | 148 | Consolidated Supply Co. |  | 94.51 | S011864821.003
AP | 220 | 05/06/24 | 149 | Consolidated Supply Co. |  | 646.25 | S011869617.002
AP | 220 | 05/06/24 | 170 | Rosen Supply Kirkland |  | 1163.98 | 22801.01
AP | 220 | 05/06/24 | 184 | Rosen Supply Kirkland |  | 145.26 | 22770.01
AP | 220 | 05/06/24 | 185 | Rosen Supply Kirkland |  | -297.9 | 22693.02
AP | 220 | 05/06/24 | 187 | Rosen Supply Kirkland |  | 1487.92 | 22871.01
AP | 220 | 05/06/24 | 188 | Rosen Supply Kirkland |  | 121.07 | 22873.01
GL | 220 | 05/07/24 | 190 | 4/28/2024 to 5/04/2024 |  | 2499.71
AP | 220 | 05/07/24 | 201 | Consolidated Supply Co. |  | 56.7 | S011872570.002
AP | 220 | 05/07/24 | 203 | Consolidated Supply Co. |  | 143.72 | S011878429.002
AP | 220 | 05/07/24 | 204 | Consolidated Supply Co. |  | 77.76 | S011878429.003
AP | 220 | 05/07/24 | 207 | Consolidated Supply Co. |  | 600.19 | S011890228.001
AP | 220 | 05/07/24 | 208 | Consolidated Supply Co. |  | 4498.95 | S011890228.002
AP | 220 | 05/07/24 | 214 | Consolidated Supply Co. |  | -166.05 | S011883173.002
AP | 220 | 05/07/24 | 215 | Consolidated Supply Co. |  | 681.74 | S011896734.001
AP | 220 | 05/08/24 | 225 | Rosen Supply Kirkland |  | 657 | 22908.01
AP | 220 | 05/08/24 | 238 | Consolidated Supply Co. |  | 1639.75 | S011898916.001
AP | 220 | 05/08/24 | 239 | Consolidated Supply Co. |  | 3815.46 | S011899550.001
AP | 220 | 05/13/24 | 385 | Pacific Plumbing Supply Co., LLC |  | 1285.8 | 51562233
AP | 220 | 05/13/24 | 407 | Consolidated Supply Co. |  | 537.2 | S011890228.005
AP | 220 | 05/13/24 | 408 | Consolidated Supply Co. |  | 1734.3 | S011902173.001
AP | 220 | 05/13/24 | 409 | Consolidated Supply Co. |  | 66.11 | S011904718.001
AP | 220 | 05/14/24 | 436 | Consolidated Supply Co. |  | 1892 | S011890228.003
AP | 220 | 05/14/24 | 437 | Consolidated Supply Co. |  | 1451.6 | S011890228.004
AP | 220 | 05/14/24 | 438 | Consolidated Supply Co. |  | 625.94 | S011906446.001
AP | 220 | 05/15/24 | 455 | Rosen Supply Kirkland |  | 119.83 | 23145.01
AP | 220 | 05/16/24 | 463 | Consolidated Supply Co. |  | 4624.8 | S011906565.001
AP | 220 | 05/17/24 | 586 | Pacific Plumbing Supply Co., LLC |  | 1675.78 | 51567434
AP | 220 | 05/20/24 | 623 | Consolidated Supply Co. |  | 766.53 | S011914633.001
AP | 220 | 05/21/24 | 637 | Consolidated Supply Co. |  | 1336.5 | S011872570.003
AP | 220 | 05/21/24 | 640 | Consolidated Supply Co. |  | 52.14 | S011919712.001
AP | 220 | 05/21/24 | 643 | Rosen Supply Kirkland |  | 165.59 | 23312.01
AP | 220 | 05/21/24 | 651 | Pacific Plumbing Supply Co., LLC |  | 27.25 | 51569589
GL | 220 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 2513.42
AP | 220 | 05/31/24 | 907 | Consolidated Supply Co. |  | 49.56 | S011923774.001
GL | 220 | 05/31/24 | 958 | Transfer 2024-05-26 to 2024-05-31 |  | 769.71
AP | 220 | 05/31/24 | 972 | Consolidated Supply Co. |  | 121.9 | S011923831.001
AP | 220 | 05/31/24 | 973 | Consolidated Supply Co. |  | 1618.68 | S011923940.001
AP | 220 | 05/31/24 | 974 | Consolidated Supply Co. |  | 1070.72 | S011914633.002
AP | 220 | 06/04/24 | 16 | Rosen Supply Kirkland |  | 268.89 | 23396.01
AP | 220 | 06/04/24 | 29 | Capital One Credit Card |  | 165.08 | 050224J
AP | 220 | 06/04/24 | 31 | Capital One Credit Card |  | 33.07 | 050624J
AP | 220 | 06/04/24 | 42 | Capital One Credit Card |  | 84.32 | 041524J
AP | 220 | 06/05/24 | 50 | Rosen Supply Kirkland |  | 182.98 | 23411.01
AP | 220 | 06/05/24 | 51 | Rosen Supply Kirkland |  | 504.21 | 23465.01
AP | 220 | 06/05/24 | 52 | Rosen Supply Kirkland |  | 130.96 | 23495.01
AP | 220 | 06/10/24 | 218 | Consolidated Supply Co. |  | 424.79 | S011940632.002
AP | 220 | 06/10/24 | 221 | Consolidated Supply Co. |  | 144.79 | S011934362.001
AP | 220 | 06/11/24 | 245 | Rosen Supply Kirkland |  | 239.35 | 23659.01
AP | 220 | 06/11/24 | 258 | Consolidated Supply Co. |  | 1156.2 | S011940555.001
AP | 220 | 06/11/24 | 259 | Consolidated Supply Co. |  | 429.85 | S011942564.001
AP | 220 | 06/11/24 | 260 | Consolidated Supply Co. |  | 1066.12 | S011942564.002
AP | 220 | 06/11/24 | 261 | Consolidated Supply Co. |  | 353.03 | S011942564.003
AP | 220 | 06/11/24 | 262 | Consolidated Supply Co. |  | 373.81 | S011942564.004
AP | 220 | 06/11/24 | 263 | Consolidated Supply Co. |  | 332.37 | S011942564.005
AP | 220 | 06/11/24 | 264 | Consolidated Supply Co. |  | -1128.6 | S011942564.006
AP | 220 | 06/11/24 | 265 | Consolidated Supply Co. |  | 259.58 | S011942564.007
AP | 220 | 06/12/24 | 297 | Consolidated Supply Co. |  | 1023.3 | S011946759.001
AP | 220 | 06/12/24 | 298 | Consolidated Supply Co. |  | 113.3 | S011942564.008
AP | 220 | 06/12/24 | 299 | Consolidated Supply Co. |  | 912.23 | S011950647.001
AP | 220 | 06/12/24 | 300 | Consolidated Supply Co. |  | 69.39 | S011950647.002
GL | 220 | 06/25/24 | 581 | Req 503 |  | 109.7
GL | 220 | 06/25/24 | 583 | Req 505 |  | 44.01
GL | 220 | 06/25/24 | 601 | Req 523 |  | 153.4
GL | 220 | 06/25/24 | 612 | Req 534 |  | 59.69
GL | 220 | 06/25/24 | 625 | 2024-06-16 to 2024-06-22 |  | 1778.14
AP | 220 | 06/26/24 | 654 | Consolidated Supply Co. |  | 7566.4 | S011945560.001
AP | 220 | 06/26/24 | 655 | Consolidated Supply Co. |  | 267.3 | S011946759.002
AP | 220 | 06/26/24 | 668 | Pacific Plumbing Supply Co., LLC |  | 534.32 | 51592928
AP | 220 | 06/26/24 | 677 | Rosen Supply Kirkland |  | 104.68 | 24127.01
AP | 220 | 06/30/24 | 795 | Rosen Supply Kirkland |  | 31.72 | 24210.01
AP | 220 | 06/30/24 | 800 | Rosen Supply Kirkland |  | 220.69 | 24226.01
AP | 220 | 06/30/24 | 812 | Capital One Credit Card |  | 220.61 | 052024J3
GL | 220 | 06/30/24 | 851 | Req 538 |  | 15.89
GL | 220 | 06/30/24 | 859 | 2024-06-24 to 2024-06-28 |  | 236.46
AP | 220 | 07/01/24 | 126 | Consolidated Supply Co. |  | -373.81 | S011942564.004A
AP | 220 | 07/01/24 | 127 | Consolidated Supply Co. |  | -373.81 | S011942564.004B
AP | 220 | 07/01/24 | 130 | Rosen Supply Kirkland |  | -239.35 | 23659.01A
AP | 220 | 07/01/24 | 311 | Pacific Plumbing Supply Co., LLC |  | 287.12 | 51606968
AP | 220 | 07/01/24 | 333 | Consolidated Supply Co. |  | 202.19 | S011945560.002
AP | 220 | 07/08/24 | 105 | Consolidated Supply Co. |  | 425.7 | S011973408.001
GL | 220 | 07/09/24 | 113 | 06/30/2024 to 07/06/2024 |  | 891.88
AP | 220 | 07/09/24 | 124 | Pacific Plumbing Supply Co., LLC |  | 716 | 51598829
GL | 220 | 07/15/24 | 292 | 2024-07-07 to 2024-07-13 |  | 265.43
AP | 220 | 07/17/24 | 358 | Rosen Supply Kirkland |  | 268.89 | 23396.03
AP | 220 | 07/22/24 | 496 | Pacific Plumbing Supply Co., LLC |  | 147.63 | 51613424
AP | 220 | 07/22/24 | 505 | Rosen Supply Kirkland |  | 173.38 | 24873.01
AP | 220 | 07/22/24 | 508 | Rosen Supply Kirkland |  | -227.34 | 24897.01
AP | 220 | 07/22/24 | 509 | Rosen Supply Kirkland |  | 200.6 | 24897.02
GL | 220 | 07/23/24 | 522 | Transfer 2024-07-14 to 2024-07-20 |  | 912.79
AP | 220 | 07/24/24 | 552 | Consolidated Supply Co. |  | 752.08 | S012012078.001
GL | 220 | 07/25/24 | 562 | Richard Anderson reimb |  | 28.67
AP | 220 | 07/30/24 | 264 | Rosen Supply Kirkland |  | 227.34 | 24418.01
GL | 220 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 296.39
AP | 220 | 07/31/24 | 680 | Capital One Credit Card |  | 33.02 | 062424J
AP | 220 | 07/31/24 | 681 | Capital One Credit Card |  | 123.42 | 062624J
AP | 220 | 07/31/24 | 682 | Capital One Credit Card |  | 42.83 | 062624J1
AP | 220 | 08/01/24 | 131 | Rosen Supply Kirkland |  | 234.47 | 25035.01
AP | 220 | 08/05/24 | 156 | Pacific Plumbing Supply Co., LLC |  | 127.27 | 51623468
GL | 220 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 1189.2
AP | 220 | 08/06/24 | 177 | Rosen Supply Kirkland |  | 41.36 | 24650.01
AP | 220 | 08/06/24 | 195 | Rosen Supply Kirkland |  | 245.43 | 25170.01
AP | 220 | 08/07/24 | 226 | Consolidated Supply Co. |  | 556.98 | S012032209.001
AP | 220 | 08/07/24 | 227 | Consolidated Supply Co. |  | 94.5 | S012032209.002
AP | 220 | 08/07/24 | 228 | Consolidated Supply Co. |  | 47.62 | S012033538.001
GL | 220 | 08/12/24 | 372 |  |  | 166.8
AP | 220 | 08/13/24 | 382 | Consolidated Supply Co. |  | 140.96 | S012039908.001
AP | 220 | 08/13/24 | 386 | Rosen Supply Kirkland |  | 478.92 | 25473.01
AP | 220 | 08/14/24 | 418 | Pacific Plumbing Supply Co., LLC |  | 344.61 | 51635715
GL | 220 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 286.79
AP | 220 | 08/20/24 | 577 | Rosen Supply Kirkland |  | 41 | 25671.01
AP | 220 | 08/20/24 | 596 | Consolidated Supply Co. |  | 265.65 | S012044876.001
AP | 220 | 08/21/24 | 644 | Capital One Credit Card |  | 6.43 | 071624J1
AP | 220 | 08/21/24 | 646 | Capital One Credit Card |  | 66.08 | 073024J
AP | 220 | 08/21/24 | 651 | Capital One Credit Card |  | 68.98 | 080524J
AP | 220 | 08/21/24 | 676 | Consolidated Supply Co. |  | 87.36 | S012055740.001
AP | 220 | 08/21/24 | 677 | Consolidated Supply Co. |  | 7.46 | S012055740.002
AP | 220 | 08/23/24 | 795 | Pacific Plumbing Supply Co., LLC |  | 512.25 | 51643396
AP | 220 | 08/26/24 | 810 | Rosen Supply Kirkland |  | 163.01 | 25896.01
GL | 220 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 275.91
AP | 220 | 08/30/24 | 935 | ACME Corp |  | 158.35 | S4566830.001
GL | 220 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 311.51
GL | 220 | 09/09/24 | 297 | 2024-09-01 to 2024-09-07 |  | 96.49
AP | 220 | 09/10/24 | 196 | Rosen Supply Kirkland |  | 425.85 | 26166.01
GL | 220 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 156.3
AP | 220 | 09/17/24 | 345 | Pacific Plumbing Supply Co., LLC |  | 321.98 | 51661088
AP | 220 | 09/17/24 | 354 | Rosen Supply Kirkland |  | 108.49 | 26347.01
AP | 220 | 09/20/24 | 472 | Consolidated Supply Co. |  | 395.28 | S012086848.001
AP | 220 | 09/20/24 | 474 | Consolidated Supply Co. |  | -395.28 | S012086848.002
AP | 220 | 09/20/24 | 476 | Pacific Plumbing Supply Co., LLC |  | 280.2 | 51664550
GL | 220 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 21.46
GL | 220 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 492.11
AP | 220 | 09/30/24 | 672 | Capital One Credit Card |  | 64.5 | 081624J
AP | 220 | 09/30/24 | 681 | Capital One Credit Card |  | 83.39 | 090424J
AP | 220 | 09/30/24 | 689 | ACME Corp |  | 139.42 | S4584802.001
AP | 220 | 09/30/24 | 719 | Rosen Supply Kirkland |  | 241.67 | 26714.01
AP | 220 | 09/30/24 | 722 | Rosen Supply Kirkland |  | 113.31 | 26623.01
AP | 220 | 10/09/24 | 145 | Pacific Plumbing Supply Co., LLC |  | 76.76 | 51674279
AP | 220 | 10/09/24 | 152 | Pacific Plumbing Supply Co., LLC |  | 16.72 | 51676612
AP | 220 | 10/11/24 | 300 | Pacific Plumbing Supply Co., LLC |  | 142.68 | 51682412
AP | 220 | 10/14/24 | 333 | Rosen Supply Kirkland |  | 45.24 | 27104.01
GL | 220 | 10/15/24 | 345 | 2024-10-06 to 2024-10-12 |  | 60.75
AP | 220 | 10/15/24 | 388 | Bank of America CC |  | 79.02 | 092024D
AP | 220 | 10/15/24 | 407 | Pacific Plumbing Supply Co., LLC |  | 120.8 | 51687130
GL | 220 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 585.41
AP | 220 | 10/22/24 | 558 | Rosen Supply Kirkland |  | 934.42 | 27660.01
GL | 220 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 149.38
AP | 220 | 10/25/24 | 682 | Consolidated Supply Co. |  | 63.52 | S012150952.001
GL | 220 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 33.24
AP | 220 | 11/12/24 | 265 | Rosen Supply Kirkland |  | 32.34 | 27532.01
AP | 220 | 11/13/24 | 318 | Rosen Supply Kirkland |  | 71.57 | 27636.01
AP | 220 | 11/13/24 | 320 | Rosen Supply Kirkland |  | 40.44 | 27730.01
GL | 220 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 62.29
AP | 220 | 11/30/24 | 740 | Capital One Credit Card |  | 61.62 | 102524J
AP | 220 | 11/30/24 | 767 | Bank of America CC |  | 39.51 | 101624D
GL | 220 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 137.71
AP | 220 | 12/18/24 | 376 | Pacific Plumbing Supply Co., LLC |  | 72.63 | 51731255
GL | 220 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 19.72
AP | 220 | 12/20/24 | 512 | Rosen Supply Kirkland |  | 48.33 | 27948.01
GL | 220 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 32.08
GL | 220 | 01/20/25 | 425 | 2025-01-12 to 2025-01-18 |  | 3.29
GL | 220 | 01/20/25 | 430 | Req 619 |  | -1016.46
AP | 220 | 01/21/25 | 454 | Ferguson Enterprises, Inc. #3007 |  | 94.07 | 3357391
AP | 220 | 01/22/25 | 498 | Consolidated Supply Co. |  | 33.32 | S012256325.001
AP | 220 | 01/22/25 | 499 | Consolidated Supply Co. |  | 21.22 | S012256325.002
AP | 220 | 01/22/25 | 500 | Consolidated Supply Co. |  | 26.12 | S012256325.003
AP | 220 | 01/22/25 | 501 | Consolidated Supply Co. |  | -21.22 | S012256325.004
AP | 220 | 01/24/25 | 635 | Pacific Plumbing Supply Co., LLC |  | 169.89 | 51760312
GL | 220 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 18.19
GL | 220 | 02/05/25 | 21 | 2025-01-26 to 2025-02-01 |  | 69.24
AP | 220 | 02/13/25 | 609 | Pacific Plumbing Supply Co., LLC |  | 122.99 | 51793656
GL | 220 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 178.72
GL | 220 | 02/21/25 | 399 | Req 630 |  | 25.22
AP | 220 | 02/24/25 | 418 | Pacific Plumbing Supply Co., LLC |  | 0.32 | 51786753
GL | 220 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 25.56
GL | 220 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 32.8
GL | 220 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 57.27
AP | 220 | 04/16/25 | 372 | Capital One Credit Card |  | 48.85 | 031125
GL | 220 | 04/16/25 | 386 | Req 644 |  | -358.83
GL | 220 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | -939.43
GL | 220 | 05/12/25 | 272 | Req 656 |  | -3430.23
GL | 220 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 10.53
GL | 220 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 73.97
GL | 220 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 25.86
GL | 220 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 112.95
AP | 220 | 07/09/25 | 107 | Rosen Supply Kirkland |  | 21.29 | 32531.01
AP | 220 | 07/09/25 | 112 | Pacific Plumbing Supply Co., LLC |  | 1082.08 | 51896714
GL | 220 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 55.53
GL | 220 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | -122.79
AP | 220 | 07/15/25 | 270 | Seton Identification Products |  | 237.09 | 9359461136
AP | 220 | 07/15/25 | 271 | Seton Identification Products |  | 832.66 | 9359492228
GL | 220 | 07/21/25 | 373 | Req 685 |  | -51.51
GL | 220 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 3.18
AP | 220 | 07/25/25 | 246 | Rosen Supply Kirkland |  | 59.02 | 32602.01
AP | 220 | 08/26/25 | 459 | Capital One Credit Card |  | 7.58 | 071525J3
AP | 220 | 09/24/25 | 378 | Pacific Plumbing Supply Co., LLC |  | -990.9 | 51959495
GL | 230 | 10/25/23 | 818 | Req 9714 |  | 171.62
GL | 230 | 11/03/23 | 193 | Req 117 |  | 213.86
AP | 230 | 11/10/23 | 654 | Keller Supply Company |  | 4609 | S022180191.001
AP | 230 | 11/11/23 | 665 | Rosen Supply Kirkland |  | 5257 | 15984.01
AP | 230 | 11/15/23 | 1199 | Core & Main LP $HD Supply Waterworks |  | 196.16 | T978480
AP | 230 | 11/27/23 | 1230 | Keller Supply Company |  | 3010.62 | S022180068.001
AP | 230 | 01/11/24 | 578 | Consolidated Supply Co. |  | 378.2 | S011686597.003
GL | 230 | 01/12/24 | 491 | Req 383 |  | 158.25
AP | 230 | 01/15/24 | 571 | Consolidated Supply Co. |  | 9157.2 | S011686597.001
AP | 230 | 01/23/24 | 857 | Keller Supply Company |  | 3635.4 | S022493797.001
AP | 230 | 01/23/24 | 859 | Keller Supply Company |  | 17093.16 | S022231424.001
AP | 230 | 01/23/24 | 860 | Keller Supply Company |  | 17093.16 | S022231320.001
AP | 230 | 01/23/24 | 861 | Keller Supply Company |  | 12209.4 | S022231460.001
AP | 230 | 02/07/24 | 214 | Consolidated Supply Co. |  | -1968 | S011686597.005
AP | 230 | 02/07/24 | 222 | Keller Supply Company |  | 12209.4 | S022231447.001
AP | 230 | 02/07/24 | 223 | Keller Supply Company |  | 4883.76 | S022231460.003
AP | 230 | 02/07/24 | 224 | Keller Supply Company |  | 4883.76 | S022231480.001
AP | 230 | 02/13/24 | 453 | Keller Supply Company |  | 17093.16 | S022231536.001
AP | 230 | 02/13/24 | 454 | Keller Supply Company |  | 17093.16 | S022231559.001
AP | 230 | 02/16/24 | 618 | Keller Supply Company |  | 12209.4 | S022231480.003
GL | 230 | 02/19/24 | 629 | 2/11/24 - 2/17/24 |  | 1223.73
AP | 230 | 02/27/24 | 822 | Keller Supply Company |  | 4883.76 | S022231447.003
AP | 230 | 03/05/24 | 174 | Pacific Plumbing Supply Co., LLC |  | 427.99 | 51493189
AP | 230 | 03/11/24 | 455 | Consolidated Supply Co. |  | 1968 | S011740524.001
AP | 230 | 03/11/24 | 459 | Keller Supply Company |  | 17093.16 | S022231630.001
AP | 230 | 03/11/24 | 460 | Keller Supply Company |  | 17093.16 | S022231658.001
AP | 230 | 03/12/24 | 468 | Keller Supply Company |  | 17093.16 | S022231579.001
AP | 230 | 03/12/24 | 469 | Keller Supply Company |  | 17093.16 | S022231675.001
AP | 230 | 03/12/24 | 478 | Keller Supply Company |  | 17093.16 | S022231686.001
GL | 230 | 03/13/24 | 489 | 03/04/2024 - 03/08/2024 |  | 399.68
GL | 230 | 03/18/24 | 677 | 3/10/24 - 3/16/24 |  | 2470.1
AP | 230 | 03/20/24 | 772 | Keller Supply Company |  | 13837.32 | S022231709.001
AP | 230 | 03/20/24 | 773 | Keller Supply Company |  | 17093.16 | S022231724.001
AP | 230 | 03/20/24 | 779 | Keller Supply Company |  | 17093.16 | S022231746.001
AP | 230 | 03/20/24 | 792 | Keller Supply Company |  | 3255.84 | S022231709.003
AP | 230 | 03/20/24 | 793 | Keller Supply Company |  | 15465.24 | S022231783.001
AP | 230 | 03/25/24 | 659 | Keller Supply Company |  | 16279.2 | S022231517.001
AP | 230 | 03/25/24 | 660 | Keller Supply Company |  | 17093.16 | S022231577.001
AP | 230 | 03/25/24 | 661 | Keller Supply Company |  | 813.96 | S022231517.003
AP | 230 | 03/25/24 | 662 | Keller Supply Company |  | 17093.16 | S022231607.001
GL | 230 | 03/25/24 | 1075 | 03/17/2024 - 03/23-2024 |  | 2410.92
AP | 230 | 03/26/24 | 1095 | Consolidated Supply Co. |  | 1697.4 | S011656510.001
AP | 230 | 03/27/24 | 1172 | Keller Supply Company |  | 1627.92 | S022231783.003
AP | 230 | 03/27/24 | 1173 | Keller Supply Company |  | 17093.16 | S022231789.001
AP | 230 | 03/27/24 | 1174 | Keller Supply Company |  | 12209.4 | S022231813.001
GL | 230 | 03/31/24 | 1308 | 03/24/2024 - 03/30/204 |  | 694.46
AP | 230 | 03/31/24 | 1362 | Keller Supply Company |  | 4883.76 | S022231813.003
GL | 230 | 04/11/24 | 285 | 03/31/2024 - 04/06/2024 |  | 560.31
AP | 230 | 04/15/24 | 364 | Consolidated Supply Co. |  | 96.09 | S011844020.001
AP | 230 | 04/15/24 | 394 | Keller Supply Company |  | 17093.16 | S022231828.001
AP | 230 | 04/15/24 | 395 | Keller Supply Company |  | 17093.16 | S022231850.001
AP | 230 | 04/15/24 | 396 | Keller Supply Company |  | 17093.16 | S022231869.001
GL | 230 | 04/15/24 | 398 | 04/07/24 - 04/13/24 |  | 1559.78
GL | 230 | 04/22/24 | 587 | 04/14/24 - 04/20/24 |  | 14.46
AP | 230 | 04/23/24 | 634 | Consolidated Supply Co. |  | -1697.4 | S011656510.002
AP | 230 | 04/23/24 | 642 | Consolidated Supply Co. |  | 38.44 | S011865213.001
AP | 230 | 04/29/24 | 925 | Keller Supply Company |  | 3350.92 | S022231910.001
GL | 230 | 04/29/24 | 926 | 04/21/2024 to 04/27/2024 |  | 1237.37
AP | 230 | 04/30/24 | 991 | Consolidated Supply Co. |  | 153.74 | S011865213.002
AP | 230 | 04/30/24 | 1008 | Consolidated Supply Co. |  | 1107 | S011656510.004
AP | 230 | 05/02/24 | 115 | Consolidated Supply Co. |  | 590.4 | S011656510.005
AP | 230 | 05/02/24 | 116 | Consolidated Supply Co. |  | 2693.7 | S011656534.001
AP | 230 | 05/02/24 | 117 | Consolidated Supply Co. |  | 2915.1 | S011656564.001
AP | 230 | 05/06/24 | 152 | Consolidated Supply Co. |  | 2915.1 | S011656560.001
AP | 230 | 05/06/24 | 153 | Consolidated Supply Co. |  | 2915.1 | S011656623.001
GL | 230 | 05/07/24 | 190 | 4/28/2024 to 5/04/2024 |  | 2006.01
AP | 230 | 05/08/24 | 236 | Consolidated Supply Co. |  | 2915.1 | S011656641.001
AP | 230 | 05/08/24 | 237 | Consolidated Supply Co. |  | 1771.2 | S011656703.001
AP | 230 | 05/13/24 | 401 | Keller Supply Company |  | 2521.89 | S022857779.001
AP | 230 | 05/13/24 | 423 | Rosen Supply Kirkland |  | 4213.73 | 22331.02
AP | 230 | 05/17/24 | 577 | California Hydronics Corp |  | 100594 | SIN183477
AP | 230 | 05/20/24 | 616 | Consolidated Supply Co. |  | 1033.2 | S011656703.002
GL | 230 | 05/21/24 | 629 | 5/12/2024 - 5/18/2024 |  | 2392.51
GL | 230 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 88.62
AP | 230 | 05/31/24 | 949 | California Hydronics Corp |  | 550 | SIN184673
AP | 230 | 05/31/24 | 950 | California Hydronics Corp |  | 3130 | SIN184683
AP | 230 | 05/31/24 | 975 | Ferguson Enterprises, Inc. #3007 |  | 1151.32 | 2643026
AP | 230 | 06/04/24 | 17 | Rosen Supply Kirkland |  | 192.78 | 23404.01
AP | 230 | 06/06/24 | 78 | California Hydronics Corp |  | 33826 | SIN182885
AP | 230 | 06/11/24 | 231 | Keller Supply Company |  | 2306.3 | S022902916.001
AP | 230 | 06/11/24 | 266 | Consolidated Supply Co. |  | 524.81 | S011942577.001
AP | 230 | 06/14/24 | 409 | Consolidated Supply Co. |  | 73.8 | S011656703.003
AP | 230 | 06/14/24 | 414 | Pacific Plumbing Supply Co., LLC |  | 761.4 | 51588533
AP | 230 | 06/18/24 | 452 | California Hydronics Corp |  | 7361 | SIN185953
AP | 230 | 06/19/24 | 455 | Consolidated Supply Co. |  | 3851.64 | S011925996.001
AP | 230 | 06/19/24 | 465 | California Hydronics Corp |  | 1840 | SIN186055
GL | 230 | 06/25/24 | 580 | Req 502 |  | 84
GL | 230 | 06/25/24 | 599 | Req 521 |  | -2521.89
GL | 230 | 06/25/24 | 625 | 2024-06-16 to 2024-06-22 |  | 5760.83
AP | 230 | 06/30/24 | 790 | Consolidated Supply Co. |  | 1469.29 | S011923736.001
AP | 230 | 06/30/24 | 815 | Capital One Credit Card |  | 47.17 | 052924J
GL | 230 | 06/30/24 | 859 | 2024-06-24 to 2024-06-28 |  | 1497.72
AP | 230 | 07/01/24 | 310 | Pacific Plumbing Supply Co., LLC |  | 934.06 | 51606967
AP | 230 | 07/01/24 | 334 | Consolidated Supply Co. |  | 5731.84 | S011975011.001
AP | 230 | 07/08/24 | 104 | Consolidated Supply Co. |  | 14769.59 | S011934353.001
GL | 230 | 07/09/24 | 113 | 06/30/2024 to 07/06/2024 |  | 140.37
GL | 230 | 07/15/24 | 292 | 2024-07-07 to 2024-07-13 |  | 743.48
AP | 230 | 07/22/24 | 482 | Keller Supply Company |  | 461.13 | S022984323.001
GL | 230 | 07/23/24 | 522 | Transfer 2024-07-14 to 2024-07-20 |  | 63.18
AP | 230 | 07/30/24 | 273 | Keller Supply Company |  | 1643 | S022693078.001
GL | 230 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 826.4
GL | 230 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 1227.01
GL | 230 | 08/12/24 | 372 |  |  | 3.86
AP | 230 | 08/13/24 | 383 | Keller Supply Company |  | 381.26 | S022535723.001
AP | 230 | 08/13/24 | 393 | Keller Supply Company |  | 159.91 | S022535881.001
AP | 230 | 08/16/24 | 522 | Keller Supply Company |  | 806.03 | S022535723.002
AP | 230 | 08/16/24 | 523 | Keller Supply Company |  | 3320.04 | S022535881.002
GL | 230 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 77.14
AP | 230 | 08/20/24 | 574 | Pacific Plumbing Supply Co., LLC |  | 80.92 | 51638981
AP | 230 | 08/20/24 | 595 | Consolidated Supply Co. |  | 3447.25 | S011684118.001
GL | 230 | 08/21/24 | 685 | Req 575 |  | 3167.5
AP | 230 | 08/23/24 | 793 | Pacific Plumbing Supply Co., LLC |  | 323.69 | 51643394
GL | 230 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 1374.37
GL | 230 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 33.89
GL | 230 | 09/09/24 | 297 | 2024-09-01 to 2024-09-07 |  | 1095.26
AP | 230 | 09/10/24 | 154 | Consolidated Supply Co. |  | 6560.34 | S011684118.002
AP | 230 | 09/10/24 | 163 | Keller Supply Company |  | 2648.25 | S022535723.003
AP | 230 | 09/10/24 | 164 | Keller Supply Company |  | 1880.74 | S022535723.004
AP | 230 | 09/10/24 | 165 | Keller Supply Company |  | 9422.84 | S022535881.003
AP | 230 | 09/10/24 | 174 | Pacific Plumbing Supply Co., LLC |  | 120.14 | 51654092
AP | 230 | 09/10/24 | 204 | Keller Supply Company |  | 5961.75 | S022535772.001
GL | 230 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 1963.54
GL | 230 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 1956.83
AP | 230 | 09/17/24 | 340 | Consolidated Supply Co. |  | 78.87 | S012087983.002
AP | 230 | 09/17/24 | 357 | Consolidated Supply Co. |  | 73.8 | S012087983.001
GL | 230 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 721.89
GL | 230 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 538.71
AP | 230 | 09/30/24 | 676 | Capital One Credit Card |  | 39.12 | 082924J
AP | 230 | 09/30/24 | 700 | Keller Supply Company |  | 32.18 | S023392334.001
AP | 230 | 09/30/24 | 709 | Mechanical Sales, Inc. |  | 179 | INV-0810719
GL | 230 | 10/08/24 | 122 | Req 593 |  | 633.5
AP | 230 | 10/08/24 | 126 | Keller Supply Company |  | 6051.31 | S022535787.001
AP | 230 | 10/08/24 | 127 | Keller Supply Company |  | 12986.9 | S022536077.001
AP | 230 | 10/08/24 | 136 | Consolidated Supply Co. |  | 10184.12 | S011684142.001
AP | 230 | 10/09/24 | 167 | Consolidated Supply Co. |  | 630.18 | S012119762.001
AP | 230 | 10/09/24 | 171 | Consolidated Supply Co. |  | -146.39 | S012119762.002
AP | 230 | 10/14/24 | 334 | Rosen Supply Kirkland |  | 287.77 | 27105.01
GL | 230 | 10/15/24 | 345 | 2024-10-06 to 2024-10-12 |  | 601.47
GL | 230 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 1898.94
AP | 230 | 10/21/24 | 540 | Pacific Plumbing Supply Co., LLC |  | 36.36 | 51690625
GL | 230 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 1235.34
GL | 230 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 19.41
AP | 230 | 10/29/24 | 723 | Keller Supply Company |  | 5560.36 | S022535806.001
GL | 230 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 1284.31
AP | 230 | 11/11/24 | 262 | Keller Supply Company |  | 13207.98 | S022536084.001
AP | 230 | 11/12/24 | 277 | Consolidated Supply Co. |  | 10184.13 | S011684155.001
AP | 230 | 11/12/24 | 281 | Pacific Plumbing Supply Co., LLC |  | 19.25 | 51701592
AP | 230 | 11/13/24 | 317 | Keller Supply Company |  | 929.27 | S022495396.001
AP | 230 | 11/13/24 | 340 | Consolidated Supply Co. |  | 52.39 | S011684115.002
GL | 230 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 265.24
AP | 230 | 11/25/24 | 610 | Keller Supply Company |  | 5805.84 | S022535825.001
AP | 230 | 11/26/24 | 621 | Ferguson Enterprises, Inc. #3007 |  | 520.8 | 3196617
AP | 230 | 11/26/24 | 623 | Rosen Supply Kirkland |  | 4271.89 | 28032.01
GL | 230 | 11/26/24 | 639 | Solutions IN77573 |  | 1020
GL | 230 | 11/26/24 | 640 | Solutions IN77706 |  | 13222.8
GL | 230 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 445.93
GL | 230 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 14.48
AP | 230 | 12/03/24 | 18 | Consolidated Supply Co. |  | 242.46 | S012180788.001
GL | 230 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 576.31
AP | 230 | 12/17/24 | 332 | Rosen Supply Kirkland |  | 694 | 27859.01
AP | 230 | 12/17/24 | 337 | Pacific Plumbing Supply Co., LLC |  | 86.39 | 51723564
AP | 230 | 12/17/24 | 351 | Consolidated Supply Co. |  | 10086.4 | S011684149.001
AP | 230 | 12/18/24 | 375 | Pacific Plumbing Supply Co., LLC |  | 232.33 | 51731254
AP | 230 | 12/18/24 | 403 | Consolidated Supply Co. |  | 33.32 | S012219643.001
AP | 230 | 12/18/24 | 421 | Keller Supply Company |  | 13098.43 | S022536131.001
GL | 230 | 12/19/24 | 492 | Jordan Games |  | 9.07
GL | 230 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 30.08
GL | 230 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 9.49
AP | 230 | 12/25/24 | 634 | Capital One Credit Card |  | 22.02 | 112624J3
AP | 230 | 12/30/24 | 651 | Bank of America CC |  | 3392 | 120324R
AP | 230 | 01/02/25 | 95 | Consolidated Supply Co. |  | 10374.35 | S011648176.001
AP | 230 | 01/02/25 | 140 | Keller Supply Company |  | 5461.09 | S022535832.002
AP | 230 | 01/02/25 | 141 | Keller Supply Company |  | 13156.61 | S022536137.001
AP | 230 | 01/02/25 | 309 | Consolidated Supply Co. |  | -10374.35 | S011648176.001A
AP | 230 | 01/02/25 | 310 | Consolidated Supply Co. |  | 10372.35 | S011648176.001B
AP | 230 | 01/08/25 | 154 | Pacific Plumbing Supply Co., LLC |  | 22.13 | 51739231
GL | 230 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 7.71
AP | 230 | 01/15/25 | 333 | Pacific Plumbing Supply Co., LLC |  | 546.5 | 51752961
GL | 230 | 01/20/25 | 425 | 2025-01-12 to 2025-01-18 |  | 55.48
AP | 230 | 01/24/25 | 615 | Rosen Supply Kirkland |  | 1461.54 | 28925.01
AP | 230 | 01/24/25 | 617 | Rosen Supply Kirkland |  | 273 | 28477.02
AP | 230 | 01/27/25 | 682 | Ferguson Enterprises, Inc. #3007 |  | 437.8 | 3389117
AP | 230 | 01/27/25 | 692 | Keller Supply Company |  | 437.2 | S023772977.002
AP | 230 | 01/27/25 | 694 | Rosen Supply Kirkland |  | 639.16 | 29037.02
AP | 230 | 01/28/25 | 666 | Rosen Supply Kirkland |  | 297.8 | 29193.01
AP | 230 | 01/28/25 | 667 | Rosen Supply Kirkland |  | 476.92 | 29254.01
AP | 230 | 01/28/25 | 675 | Capital One Credit Card |  | 104.47 | 010925J
GL | 230 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 318.49
GL | 230 | 02/05/25 | 21 | 2025-01-26 to 2025-02-01 |  | 117.94
AP | 230 | 02/07/25 | 106 | Keller Supply Company |  | 3480.1 | S0122535839.001
GL | 230 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 130.11
AP | 230 | 02/11/25 | 151 | Consolidated Supply Co. |  | 9687.04 | S011684185.001
AP | 230 | 02/12/25 | 163 | Keller Supply Company |  | 12239.41 | S022536172.001
AP | 230 | 02/14/25 | 280 | Pacific Plumbing Supply Co., LLC |  | 644.91 | 51780902
GL | 230 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 21.04
AP | 230 | 02/17/25 | 293 | Pacific Plumbing Supply Co., LLC |  | 200.4 | 51783330
AP | 230 | 02/21/25 | 410 | Keller Supply Company |  | 211.86 | S022535839.002
AP | 230 | 02/21/25 | 411 | Keller Supply Company |  | 73.45 | S023832364.001
AP | 230 | 02/24/25 | 416 | Pacific Plumbing Supply Co., LLC |  | 35.41 | 51786746
AP | 230 | 02/25/25 | 452 | Capital One Credit Card |  | 22.55 | 011025J
AP | 230 | 02/25/25 | 468 | Capital One Credit Card |  | 20.12 | 012825J
GL | 230 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 721.76
AP | 230 | 02/26/25 | 490 | Keller Supply Company |  | 69.43 | S023855263.001
GL | 230 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 347.28
AP | 230 | 03/05/25 | 138 | Consolidated Supply Co. |  | 1570.5 | S011673398.001
AP | 230 | 03/05/25 | 143 | Keller Supply Company |  | 7673.63 | S022536240.001
AP | 230 | 03/06/25 | 91 | Consolidated Supply Co. |  | 418.85 | S012279152.001
GL | 230 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 11.87
AP | 230 | 03/17/25 | 295 | Consolidated Supply Co. |  | 38.21 | S012305299.001
AP | 230 | 03/17/25 | 296 | Consolidated Supply Co. |  | 136.65 | S012325528.001
AP | 230 | 03/19/25 | 351 | Rosen Supply Kirkland |  | 434.75 | 30394.01
AP | 230 | 03/21/25 | 506 | Rosen Supply Kirkland |  | 375.4 | 29163.01
AP | 230 | 03/21/25 | 507 | Rosen Supply Kirkland |  | 46.6 | 29193.03
AP | 230 | 03/21/25 | 509 | Rosen Supply Kirkland |  | 86.67 | 30486.01
AP | 230 | 03/24/25 | 515 | Kele, Inc $ MI Controls |  | 684 | IMIS0807036261
GL | 230 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 30.23
AP | 230 | 03/25/25 | 549 | Keller Supply Company |  | 7661.75 | S022536198.001
GL | 230 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 68.51
AP | 230 | 04/04/25 | 98 | Consolidated Supply Co. |  | 6026.48 | S011684212.001
AP | 230 | 04/04/25 | 99 | Consolidated Supply Co. |  | 45.56 | S011684212.002
AP | 230 | 04/07/25 | 107 | Consolidated Supply Co. |  | -45.56 | S011684212.003
AP | 230 | 04/07/25 | 108 | Consolidated Supply Co. |  | 233.3 | S012325528.002
GL | 230 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 65.99
AP | 230 | 04/11/25 | 263 | Keller Supply Company |  | 458.76 | S023947372.001
AP | 230 | 04/11/25 | 272 | Rosen Supply Kirkland |  | 103.35 | 30268.01
AP | 230 | 04/11/25 | 273 | Rosen Supply Kirkland |  | 34.47 | 30818.01
AP | 230 | 04/11/25 | 280 | Pacific Plumbing Supply Co., LLC |  | 876.43 | 51823496
GL | 230 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 59.73
AP | 230 | 04/18/25 | 496 | Consolidated Supply Co. |  | 196.66 | S012335823.001
AP | 230 | 04/23/25 | 541 | Keller Supply Company |  | 184.8 | S024046332.001
AP | 230 | 04/23/25 | 542 | Keller Supply Company |  | 431.08 | S024047317.001
AP | 230 | 04/28/25 | 650 | Pacific Plumbing Supply Co., LLC |  | 773.94 | 51841000
GL | 230 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 59.63
AP | 230 | 05/02/25 | 83 | Consolidated Supply Co. |  | 306.38 | S012367081.001
AP | 230 | 05/02/25 | 95 | Consolidated Supply Co. |  | 145.8 | S012396824.001
AP | 230 | 05/02/25 | 96 | Consolidated Supply Co. |  | -145.8 | S012396824.003
AP | 230 | 05/02/25 | 97 | Consolidated Supply Co. |  | 173.22 | S012403764.001
GL | 230 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 30.71
AP | 230 | 05/09/25 | 240 | Keller Supply Company |  | 31.43 | S024086687.001
GL | 230 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 7.23
AP | 230 | 05/22/25 | 522 | Consolidated Supply Co. |  | -356.49 | S012422981.001
AP | 230 | 05/27/25 | 294 | Capital One Credit Card |  | 20.41 | 042125J
GL | 230 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 35.03
AP | 230 | 05/30/25 | 645 | Rosen Supply Kirkland |  | 41.16 | 31743.01
AP | 230 | 05/31/25 | 669 | Rosen Supply Kirkland |  | 193.68 | 31698.01
AP | 230 | 05/31/25 | 679 | Rosen Supply Kirkland |  | 8.23 | 31818.01
AP | 230 | 06/09/25 | 110 | Ferguson Enterprises, Inc. #3007 |  | 735.08 | 3727352
AP | 230 | 06/09/25 | 113 | Rosen Supply Kirkland |  | 140.1 | 30394.03
GL | 230 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 36.98
AP | 230 | 06/12/25 | 245 | Keller Supply Company |  | 56.5 | S023850393.001
AP | 230 | 06/12/25 | 246 | Keller Supply Company |  | 48.08 | S024232548.001
AP | 230 | 06/12/25 | 247 | Keller Supply Company |  | 433.91 | S024236171.001
AP | 230 | 06/27/25 | 551 | Ferguson Enterprises, Inc. #3007 |  | 408.38 | 3790389
AP | 230 | 06/27/25 | 553 | Keller Supply Company |  | 245.13 | S024285099.002
AP | 230 | 06/27/25 | 556 | Keller Supply Company |  | 368.46 | S024218841.002
AP | 230 | 06/27/25 | 557 | Keller Supply Company |  | 12.62 | S024280732.001
AP | 230 | 06/27/25 | 558 | Keller Supply Company |  | -317.79 | S024286038.001
AP | 230 | 06/30/25 | 581 | Keller Supply Company |  | 83.83 | S024264042.003
AP | 230 | 06/30/25 | 582 | Keller Supply Company |  | -208.54 | S024288944.001
AP | 230 | 07/01/25 | 4 | Keller Supply Company |  | -368.46 | S024218841.002A
AP | 230 | 07/01/25 | 5 | Keller Supply Company |  | 73.69 | S024218841.002B
AP | 230 | 07/09/25 | 103 | Keller Supply Company |  | 221.08 | S024218841.003
AP | 230 | 07/09/25 | 110 | Pacific Plumbing Supply Co., LLC |  | 128.99 | 51896711
GL | 230 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 143.78
GL | 230 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | -1418.04
AP | 230 | 07/14/25 | 255 | Ferguson Enterprises, Inc. #3007 |  | 22.48 | 3843507
GL | 230 | 07/21/25 | 372 | Req 684 |  | -2961
AP | 230 | 07/21/25 | 392 | Consolidated Supply Co. |  | 65.65 | S012509239.001
AP | 230 | 07/22/25 | 440 | Consolidated Supply Co. |  | 277.36 | S012509239.002
AP | 230 | 07/22/25 | 441 | Consolidated Supply Co. |  | 126.81 | S012488294.001
AP | 230 | 07/22/25 | 445 | Pacific Plumbing Supply Co., LLC |  | 139.84 | 51909736
AP | 230 | 07/22/25 | 446 | Pacific Plumbing Supply Co., LLC |  | 69.92 | 51910105
AP | 230 | 07/22/25 | 451 | Rosen Supply Kirkland |  | 12.8 | 32815.01
AP | 230 | 07/25/25 | 233 | Pacific Plumbing Supply Co., LLC |  | 1118.72 | 51900855
AP | 230 | 07/25/25 | 238 | Pacific Plumbing Supply Co., LLC |  | 139.84 | 51903792
AP | 230 | 07/29/25 | 586 | Kele, Inc $ MI Controls |  | -319.3 | MSCRED7004220
AP | 230 | 08/01/25 | 62 | California Hydronics Corp |  | 25.5 | SIN219495
AP | 230 | 08/01/25 | 97 | Keller Supply Company |  | 25.24 | S024408023.001
GL | 230 | 08/03/25 | 78 | 2025-07-20 to 07-26 |  | 52.04
GL | 230 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 5.44
AP | 230 | 08/08/25 | 230 | Keller Supply Company |  | 91.52 | S024400310.001
AP | 230 | 08/08/25 | 231 | Keller Supply Company |  | 81.48 | S024395229.001
AP | 230 | 08/26/25 | 457 | Capital One Credit Card |  | 28.3 | 071425J3
AP | 230 | 08/26/25 | 463 | Capital One Credit Card |  | 33.66 | 072825J
AP | 230 | 08/26/25 | 464 | Capital One Credit Card |  | 15.35 | 072925J
AP | 230 | 08/26/25 | 484 | Bank of America CC |  | 24.63 | 072425J
GL | 230 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 51.53
AP | 230 | 10/07/25 | 128 | Keller Supply Company |  | 889.84 | S024462934.001
AP | 230 | 10/10/25 | 250 | Consolidated Supply Co. |  | 250.85 | S012556606.001
GL | 230 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -148.85
AP | 230 | 11/18/25 | 317 | Mechanical Sales, Inc. |  | 2620.7 | INV-0816097
AP | 230 | 11/21/25 | 409 | Mechanical Sales, Inc. |  | 643 | INV-0816141
AP | 230 | 11/21/25 | 418 | Consolidated Supply Co. |  | 63.4 | S012691627.001
AP | 230 | 12/01/25 | 144 | Mechanical Sales, Inc. |  | -643 | INV-0816141A
AP | 230 | 12/01/25 | 145 | Mechanical Sales, Inc. |  | 634 | INV-0816141B
AP | 230 | 01/30/26 | 645 | Mechanical Sales, Inc. |  | -492.4 | CM-0816097
GL | 240 | 02/27/24 | 806 | Transfer 02/19/24 - 2/24/24 |  | 3.77
GL | 240 | 03/13/24 | 489 | 03/04/2024 - 03/08/2024 |  | 72.88
AP | 240 | 03/25/24 | 1082 | Consolidated Supply Co. |  | 2347.16 | S011804519.001
AP | 240 | 03/25/24 | 1083 | Consolidated Supply Co. |  | 446.95 | S011804519.002
AP | 240 | 03/26/24 | 1123 | Consolidated Supply Co. |  | 322.84 | S011821017.001
AP | 240 | 03/26/24 | 1124 | Consolidated Supply Co. |  | 121.54 | S011821017.002
AP | 240 | 03/27/24 | 1164 | Pacific Plumbing Supply Co., LLC |  | 1250.59 | 51524579
AP | 240 | 03/31/24 | 1364 | Consolidated Supply Co. |  | 231.69 | S011836623.001
AP | 240 | 04/01/24 | 753 | Consolidated Supply Co. |  | 54.22 | S011848149.002
GL | 240 | 04/12/24 | 308 | Req 488 |  | 538.89
AP | 240 | 04/19/24 | 579 | Consolidated Supply Co. |  | 687.58 | S011844037.001
AP | 240 | 04/22/24 | 596 | Consolidated Supply Co. |  | 1202.4 | S011846882.001
AP | 240 | 04/22/24 | 597 | Consolidated Supply Co. |  | 715.53 | S011846882.002
AP | 240 | 04/22/24 | 598 | Consolidated Supply Co. |  | 106.16 | S011848149.001
AP | 240 | 04/23/24 | 638 | Consolidated Supply Co. |  | 252.54 | S011861152.001
AP | 240 | 04/23/24 | 666 | Consolidated Supply Co. |  | 169.47 | S011861152.002
AP | 240 | 05/06/24 | 186 | Rosen Supply Kirkland |  | 151.36 | 22870.01
GL | 240 | 05/07/24 | 190 | 4/28/2024 to 5/04/2024 |  | 153.92
AP | 240 | 05/14/24 | 432 | Rosen Supply Kirkland |  | 196.13 | 23104.01
AP | 240 | 05/15/24 | 453 | Consolidated Supply Co. |  | 399.92 | S011836623.002
AP | 240 | 05/20/24 | 598 | Rosen Supply Kirkland |  | -196.13 | 23251.01
AP | 240 | 05/20/24 | 599 | Rosen Supply Kirkland |  | 183.28 | 23251.02
GL | 240 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 92.76
AP | 240 | 06/04/24 | 14 | Rosen Supply Kirkland |  | 163.63 | 23104.03
GL | 240 | 06/25/24 | 600 | Req 522 |  | 100.8
GL | 240 | 06/30/24 | 859 | 2024-06-24 to 2024-06-28 |  | 1.34
AP | 240 | 07/09/24 | 112 | Kele, Inc $ MI Controls |  | 975.68 | IMIS0807031996
GL | 240 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 43.01
AP | 240 | 10/14/24 | 316 | Consolidated Supply Co. |  | -1673.72 | S012122458.001
AP | 240 | 10/25/24 | 673 | Pacific Plumbing Supply Co., LLC |  | 438.97 | 51694080
GL | 240 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 78.8
AP | 240 | 11/12/24 | 263 | Rosen Supply Kirkland |  | 9.76 | 27507.01
AP | 240 | 11/12/24 | 283 | Pacific Plumbing Supply Co., LLC |  | 43.94 | 51703015
AP | 240 | 11/12/24 | 298 | Pacific Plumbing Supply Co., LLC |  | 84.05 | 51706318
AP | 240 | 11/25/24 | 612 | Pacific Plumbing Supply Co., LLC |  | 205.21 | 51716822
AP | 240 | 11/25/24 | 616 | Pacific Plumbing Supply Co., LLC |  | 440.99 | 51720652
GL | 240 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 324.39
AP | 240 | 12/03/24 | 11 | Consolidated Supply Co. |  | 49.85 | S012193618.001
AP | 240 | 12/03/24 | 12 | Consolidated Supply Co. |  | 77.64 | S012193618.002
AP | 240 | 12/17/24 | 359 | Pacific Plumbing Supply Co., LLC |  | 59.47 | 51727161
GL | 240 | 01/02/25 | 126 | 2024-12-30 to 2025-01-03 |  | 12.24
AP | 240 | 01/08/25 | 166 | Pacific Plumbing Supply Co., LLC |  | 204.97 | 51741543
AP | 240 | 01/13/25 | 300 | Kele, Inc $ MI Controls |  | 995.52 | IMIS0807035308
AP | 240 | 01/13/25 | 301 | Kele, Inc $ MI Controls |  | 511.2 | IMIS0807035370
GL | 240 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 109.09
AP | 240 | 01/15/25 | 332 | Pacific Plumbing Supply Co., LLC |  | 172.01 | 51752229
AP | 240 | 01/15/25 | 334 | Pacific Plumbing Supply Co., LLC |  | 128.41 | 51752964
AP | 240 | 01/24/25 | 621 | Pacific Plumbing Supply Co., LLC |  | 162.84 | 51756718
AP | 240 | 01/24/25 | 637 | Pacific Plumbing Supply Co., LLC |  | 38.1 | 51760313
AP | 240 | 01/28/25 | 657 | Pacific Plumbing Supply Co., LLC |  | 33.95 | 51764337
AP | 240 | 02/11/25 | 156 | Pacific Plumbing Supply Co., LLC |  | 46.95 | 51777537
AP | 240 | 02/14/25 | 285 | Rosen Supply Kirkland |  | 177.37 | 29774.01
AP | 240 | 02/24/25 | 417 | Pacific Plumbing Supply Co., LLC |  | 276.57 | 51786752
AP | 240 | 02/24/25 | 436 | Pacific Plumbing Supply Co., LLC |  | 30.59 | 51788954
AP | 240 | 02/25/25 | 458 | Capital One Credit Card |  | 24.92 | 011625J2
GL | 240 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 3.82
GL | 240 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 30.59
AP | 240 | 04/08/25 | 128 | Kele, Inc $ MI Controls |  | 852 | IMIS0807036421
GL | 240 | 04/16/25 | 393 | Req 651 |  | -149.54
GL | 240 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 44.24
AP | 240 | 04/23/25 | 547 | Rosen Supply Kirkland |  | 126.9 | 31135.01
AP | 240 | 04/28/25 | 656 | Rosen Supply Kirkland |  | 7.58 | 31221.01
AP | 240 | 05/01/25 | 71 | Kele, Inc $ MI Controls |  | 355.2 | IMIS0807036759
GL | 240 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 22.32
GL | 240 | 05/30/25 | 604 | Req 659 |  | -1418.87
GL | 240 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 68.77
GL | 240 | 06/17/25 | 296 | Req 666 |  | 25.24
AP | 240 | 07/09/25 | 109 | Pacific Plumbing Supply Co., LLC |  | 263.98 | 51893592
AP | 240 | 07/21/25 | 393 | Pacific Plumbing Supply Co., LLC |  | 295.52 | 51906018
AP | 240 | 07/22/25 | 411 | Bank of America CC |  | 88.2 | 062725J
AP | 240 | 07/22/25 | 414 | Bank of America CC |  | 155.04 | 070725J2
AP | 240 | 07/25/25 | 235 | Pacific Plumbing Supply Co., LLC |  | 3.96 | 51903783
AP | 240 | 07/25/25 | 236 | Pacific Plumbing Supply Co., LLC |  | 7.76 | 51903785
AP | 240 | 07/25/25 | 237 | Pacific Plumbing Supply Co., LLC |  | 4.36 | 51903791
AP | 240 | 07/25/25 | 289 | Pacific Plumbing Supply Co., LLC |  | 27.22 | 51908493
AP | 240 | 08/26/25 | 458 | Capital One Credit Card |  | 19.18 | 071525J2
GL | 240 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -1.34
AP | 241 | 12/01/23 | 256 | Consolidated Supply Co. |  | 926.6 | S011631116.001
GL | 241 | 01/12/24 | 492 | Req 384 |  | 23.56
AP | 241 | 02/27/24 | 815 | Consolidated Supply Co. |  | 3899.94 | S011746328.001
AP | 241 | 02/27/24 | 816 | Consolidated Supply Co. |  | 17.96 | S011746328.002
GL | 241 | 03/13/24 | 489 | 03/04/2024 - 03/08/2024 |  | 99.33
GL | 241 | 03/18/24 | 677 | 3/10/24 - 3/16/24 |  | 325.15
AP | 241 | 03/19/24 | 709 | Consolidated Supply Co. |  | 15157.2 | S011653597.001
GL | 241 | 03/25/24 | 1075 | 03/17/2024 - 03/23-2024 |  | 34.28
AP | 241 | 03/26/24 | 1114 | Consolidated Supply Co. |  | 14623.95 | S011654622.001
AP | 241 | 03/26/24 | 1115 | Consolidated Supply Co. |  | 533.21 | S011654622.002
AP | 241 | 03/27/24 | 1160 | Pacific Plumbing Supply Co., LLC |  | 10596.6 | 51522098
GL | 241 | 03/31/24 | 1308 | 03/24/2024 - 03/30/204 |  | 352.17
AP | 241 | 03/31/24 | 1325 | Consolidated Supply Co. |  | 1301.86 | S011827586.001
AP | 241 | 03/31/24 | 1344 | Consolidated Supply Co. |  | 377.54 | S011833534.001
AP | 241 | 04/01/24 | 756 | Ferguson Enterprises, Inc. #3007 |  | 47.68 | 2458120
GL | 241 | 04/11/24 | 285 | 03/31/2024 - 04/06/2024 |  | 72.74
GL | 241 | 04/15/24 | 398 | 04/07/24 - 04/13/24 |  | 36.41
AP | 241 | 04/17/24 | 427 | Pacific Plumbing Supply Co., LLC |  | 400.89 | 51535231
GL | 241 | 04/22/24 | 587 | 04/14/24 - 04/20/24 |  | 188.6
AP | 241 | 04/22/24 | 599 | Consolidated Supply Co. |  | 454.3 | S011848179.001
AP | 241 | 04/22/24 | 601 | Consolidated Supply Co. |  | 11705.88 | S011848436.001
AP | 241 | 04/22/24 | 614 | Consolidated Supply Co. |  | 254.58 | S011854428.001
AP | 241 | 04/23/24 | 637 | Consolidated Supply Co. |  | 3243.21 | S011861123.001
AP | 241 | 04/23/24 | 665 | Consolidated Supply Co. |  | 185.33 | S011848436.002
AP | 241 | 04/25/24 | 763 | Pacific Plumbing Supply Co., LLC |  | 1365.33 | 51539579
AP | 241 | 04/26/24 | 897 | Pacific Plumbing Supply Co., LLC |  | 1985.72 | 51544075
GL | 241 | 04/29/24 | 926 | 04/21/2024 to 04/27/2024 |  | 2368.76
AP | 241 | 04/30/24 | 992 | Consolidated Supply Co. |  | 942.8 | S011868032.001
AP | 241 | 04/30/24 | 994 | Consolidated Supply Co. |  | 996.06 | S011872576.001
AP | 241 | 04/30/24 | 1020 | Consolidated Supply Co. |  | 147.98 | S011878479.001
AP | 241 | 05/02/24 | 118 | Consolidated Supply Co. |  | 5290.95 | S011882765.001
AP | 241 | 05/06/24 | 150 | Consolidated Supply Co. |  | 144.3 | S011848436.003
AP | 241 | 05/06/24 | 151 | Consolidated Supply Co. |  | 1737.42 | S011890223.001
AP | 241 | 05/06/24 | 154 | Consolidated Supply Co. |  | -144.3 | S011848436.004
AP | 241 | 05/06/24 | 157 | Pacific Plumbing Supply Co., LLC |  | 215.32 | 51552730
AP | 241 | 05/06/24 | 158 | Pacific Plumbing Supply Co., LLC |  | 12415.34 | 51552732
AP | 241 | 05/06/24 | 168 | Pacific Plumbing Supply Co., LLC |  | 645.95 | 51552731
GL | 241 | 05/07/24 | 190 | 4/28/2024 to 5/04/2024 |  | 1229.51
AP | 241 | 05/07/24 | 200 | Consolidated Supply Co. |  | 225 | S011848436.005
AP | 241 | 05/07/24 | 202 | Consolidated Supply Co. |  | 241.28 | S011872576.002
AP | 241 | 05/07/24 | 205 | Consolidated Supply Co. |  | 72.47 | S011878479.002
AP | 241 | 05/07/24 | 206 | Consolidated Supply Co. |  | 80.77 | S011882765.002
AP | 241 | 05/07/24 | 213 | Consolidated Supply Co. |  | 190.24 | S011861123.002
AP | 241 | 05/08/24 | 235 | Consolidated Supply Co. |  | 190.24 | S011882765.003
AP | 241 | 05/13/24 | 389 | Pacific Plumbing Supply Co., LLC |  | 479.95 | 51564137
AP | 241 | 05/13/24 | 410 | Consolidated Supply Co. |  | 706.08 | S011905401.001
AP | 241 | 05/13/24 | 411 | Consolidated Supply Co. |  | 91.47 | S011906273.001
GL | 241 | 05/13/24 | 426 | 5/5/24 - 5/11/24 |  | 297.25
AP | 241 | 05/16/24 | 464 | Consolidated Supply Co. |  | 447 | S011910537.001
AP | 241 | 05/16/24 | 465 | Consolidated Supply Co. |  | 7.57 | S011910794.001
AP | 241 | 05/20/24 | 593 | Consolidated Supply Co. |  | 178.35 | S011878479.003
GL | 241 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 323.43
AP | 241 | 05/31/24 | 953 | MacArthur Co. NW 6276 |  | 5576.04 | 2024001911271
AP | 241 | 05/31/24 | 954 | MacArthur Co. NW 6276 |  | 310.59 | 2024001912157
GL | 241 | 05/31/24 | 958 | Transfer 2024-05-26 to 2024-05-31 |  | 884.32
AP | 241 | 05/31/24 | 971 | Consolidated Supply Co. |  | 455.12 | S011882765.004
AP | 241 | 05/31/24 | 977 | Pacific Plumbing Supply Co., LLC |  | 690.69 | 51572463
AP | 241 | 05/31/24 | 978 | Pacific Plumbing Supply Co., LLC |  | 2593.17 | 51572464
AP | 241 | 06/01/24 | 66 | Consolidated Supply Co. |  | -7.57 | S011910794.001A
AP | 241 | 06/01/24 | 67 | Consolidated Supply Co. |  | 73.57 | S011910794.001B
AP | 241 | 06/10/24 | 204 | MacArthur Co. NW 6276 |  | 2464.92 | 2024001916449
AP | 241 | 06/10/24 | 219 | Consolidated Supply Co. |  | 362 | S011932337.001
AP | 241 | 06/10/24 | 220 | Consolidated Supply Co. |  | 1299.85 | S011932337.002
AP | 241 | 06/10/24 | 222 | Consolidated Supply Co. |  | 490.78 | S011928477.001
AP | 241 | 06/11/24 | 233 | Pacific Plumbing Supply Co., LLC |  | 793.25 | 51580669
AP | 241 | 06/11/24 | 267 | Consolidated Supply Co. |  | 8.72 | S011942587.001
AP | 241 | 06/18/24 | 441 | Consolidated Supply Co. |  | 13.15 | S011958642.001
AP | 241 | 06/19/24 | 462 | Consolidated Supply Co. |  | 627.7 | S011960234.001
GL | 241 | 06/25/24 | 576 | Req 495 |  | 1598.58
GL | 241 | 06/25/24 | 625 | 2024-06-16 to 2024-06-22 |  | 1611.48
AP | 241 | 06/26/24 | 645 | Consolidated Supply Co. |  | 71.2 | S011966759.001
AP | 241 | 06/26/24 | 657 | MacArthur Co. NW 6276 |  | 1880.64 | 2024001929058
GL | 241 | 06/30/24 | 859 | 2024-06-24 to 2024-06-28 |  | 11.73
GL | 241 | 07/23/24 | 522 | Transfer 2024-07-14 to 2024-07-20 |  | 52.42
GL | 241 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 17.16
GL | 241 | 08/12/24 | 372 |  |  | 17.16
AP | 241 | 08/14/24 | 417 | Pacific Plumbing Supply Co., LLC |  | 8981.78 | 51635021
AP | 241 | 08/14/24 | 423 | Pacific Plumbing Supply Co., LLC |  | 1667.56 | 51635716
GL | 241 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 31.8
AP | 241 | 08/20/24 | 564 | Pacific Plumbing Supply Co., LLC |  | 33.2 | 51637120
GL | 241 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 207.77
AP | 241 | 09/10/24 | 170 | Pacific Plumbing Supply Co., LLC |  | 1683.1 | 51651109
GL | 241 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 863.37
AP | 241 | 09/18/24 | 385 | Pacific Plumbing Supply Co., LLC |  | 203.91 | 51662054
AP | 241 | 09/20/24 | 473 | Consolidated Supply Co. |  | 958.8 | S012095267.001
AP | 241 | 09/20/24 | 477 | Pacific Plumbing Supply Co., LLC |  | 204.47 | 51664551
AP | 241 | 09/20/24 | 754 | Consolidated Supply Co. |  | -958.8 | S012095267.001A
AP | 241 | 09/20/24 | 755 | Consolidated Supply Co. |  | 658.8 | S012095267.001B
GL | 241 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 218.25
GL | 241 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 413.92
AP | 241 | 09/30/24 | 728 | Consolidated Supply Co. |  | 310.84 | S012102223.001
GL | 241 | 10/08/24 | 118 | Req 589 |  | 62.52
AP | 241 | 10/08/24 | 137 | Consolidated Supply Co. |  | 508.7 | S012107352.001
AP | 241 | 10/14/24 | 342 | Pacific Plumbing Supply Co., LLC |  | 185.2 | 51685737
GL | 241 | 10/15/24 | 345 | 2024-10-06 to 2024-10-12 |  | 5.37
GL | 241 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 13.98
GL | 241 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 11.44
GL | 241 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 59.11
AP | 241 | 11/26/24 | 647 | MacArthur Co. NW 6276 |  | -1125.25 | 202600239588
GL | 241 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 28.28
GL | 241 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 21.87
AP | 241 | 12/04/24 | 45 | Pacific Plumbing Supply Co., LLC |  | 81.89 | 51721922
GL | 241 | 12/18/24 | 399 | Req 612 |  | 145.56
GL | 241 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 32.14
GL | 241 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 2.16
AP | 241 | 01/22/25 | 473 | Consolidated Supply Co. |  | 141.22 | S012245756.001
GL | 241 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 53.03
GL | 241 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 69.98
GL | 241 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 69.45
GL | 241 | 03/10/25 | 554 | Req 641 |  | -1519.09
GL | 241 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | -557.35
GL | 241 | 04/16/25 | 390 | Req 648 |  | -8722.88
GL | 241 | 05/30/25 | 606 | Req 661 |  | -3069.76
GL | 241 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 23.34
GL | 241 | 08/03/25 | 78 | 2025-07-20 to 07-26 |  | 33.84
GL | 241 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -71.81
GL | 242 | 04/15/24 | 398 | 04/07/24 - 04/13/24 |  | 5.35
AP | 242 | 04/23/24 | 636 | Consolidated Supply Co. |  | 575.95 | S011861095.001
AP | 242 | 04/26/24 | 896 | Pacific Plumbing Supply Co., LLC |  | 432.29 | 51544074
GL | 242 | 04/29/24 | 926 | 04/21/2024 to 04/27/2024 |  | 193.37
AP | 242 | 04/30/24 | 979 | Pacific Plumbing Supply Co., LLC |  | 295.96 | 51552070
AP | 242 | 05/13/24 | 386 | Pacific Plumbing Supply Co., LLC |  | 4689.99 | 51562234
GL | 242 | 05/13/24 | 426 | 5/5/24 - 5/11/24 |  | 14.78
AP | 242 | 05/17/24 | 585 | Pacific Plumbing Supply Co., LLC |  | 333.36 | 51567433
GL | 242 | 05/29/24 | 784 | 2024-05-19 to 2024-05-25 |  | 96.65
GL | 242 | 06/25/24 | 625 | 2024-06-16 to 2024-06-22 |  | 72.81
GL | 242 | 06/30/24 | 859 | 2024-06-24 to 2024-06-28 |  | 1339.05
AP | 242 | 07/24/24 | 542 | Pacific Plumbing Supply Co., LLC |  | 6765.02 | 51617930
AP | 242 | 07/24/24 | 543 | Pacific Plumbing Supply Co., LLC |  | 2753.49 | 51617935
AP | 242 | 07/31/24 | 661 | Consolidated Supply Co. |  | 26614.35 | S011972360.001
GL | 242 | 08/12/24 | 372 |  |  | 752.78
GL | 242 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 129.83
AP | 242 | 08/23/24 | 829 | Consolidated Supply Co. |  | 45.28 | S012061380.001
GL | 242 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 3.08
AP | 242 | 09/10/24 | 171 | Pacific Plumbing Supply Co., LLC |  | 319.45 | 51651489
AP | 242 | 09/10/24 | 178 | Pacific Plumbing Supply Co., LLC |  | 2551.18 | 51654896
GL | 242 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 615.71
AP | 242 | 09/17/24 | 339 | Consolidated Supply Co. |  | 433.3 | S011972360.002
AP | 242 | 09/17/24 | 343 | Pacific Plumbing Supply Co., LLC |  | 64.51 | 51659500
AP | 242 | 09/17/24 | 346 | Pacific Plumbing Supply Co., LLC |  | 410.28 | 51661090
AP | 242 | 09/18/24 | 386 | Pacific Plumbing Supply Co., LLC |  | 763.21 | 51662203
AP | 242 | 09/20/24 | 491 | Pacific Plumbing Supply Co., LLC |  | 451.66 | 51666006
AP | 242 | 09/20/24 | 492 | Pacific Plumbing Supply Co., LLC |  | 51.97 | 51666007
GL | 242 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 400.47
GL | 242 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 173.18
AP | 242 | 09/30/24 | 678 | Capital One Credit Card |  | 19.8 | 082924J2
AP | 242 | 09/30/24 | 680 | Capital One Credit Card |  | 13.19 | 090324J1
AP | 242 | 09/30/24 | 682 | Capital One Credit Card |  | 37.14 | 090424J1
AP | 242 | 09/30/24 | 702 | Pacific Plumbing Supply Co., LLC |  | 4142.14 | 51667056
AP | 242 | 09/30/24 | 704 | Pacific Plumbing Supply Co., LLC |  | 143.84 | 51667097
GL | 242 | 10/08/24 | 117 | Req 588 |  | 134.63
AP | 242 | 10/09/24 | 140 | Pacific Plumbing Supply Co., LLC |  | 1114.21 | 51672272
AP | 242 | 10/09/24 | 141 | Pacific Plumbing Supply Co., LLC |  | 193.61 | 51672273
AP | 242 | 10/09/24 | 151 | Pacific Plumbing Supply Co., LLC |  | 83.38 | 51676608
AP | 242 | 10/15/24 | 351 | Capital One Credit Card |  | 52.21 | 091724J
AP | 242 | 10/15/24 | 406 | Pacific Plumbing Supply Co., LLC |  | 643.5 | 51687129
AP | 242 | 10/21/24 | 536 | Pacific Plumbing Supply Co., LLC |  | 127.15 | 51688637
GL | 242 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 213.19
AP | 242 | 11/13/24 | 329 | Ferguson Enterprises, Inc. #3007 |  | 1410.24 | 3121814
GL | 242 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 51.35
AP | 242 | 12/18/24 | 381 | Pacific Plumbing Supply Co., LLC |  | 419.95 | 51734303
GL | 242 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 62.94
GL | 242 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 23.29
AP | 242 | 01/08/25 | 167 | Pacific Plumbing Supply Co., LLC |  | 166.57 | 51741546
GL | 242 | 01/20/25 | 426 | Req 615 |  | -1052.86
GL | 242 | 01/20/25 | 431 | Req 620 |  | -799.64
AP | 242 | 01/24/25 | 627 | Pacific Plumbing Supply Co., LLC |  | 8.47 | 51758718
AP | 242 | 01/28/25 | 660 | Pacific Plumbing Supply Co., LLC |  | 272.89 | 51765696
GL | 242 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 139.03
AP | 242 | 01/31/25 | 794 | Pacific Plumbing Supply Co., LLC |  | 148.67 | 51769113
AP | 242 | 02/11/25 | 153 | Rosen Supply Kirkland |  | 31.43 | 29616.01
GL | 242 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 22.01
AP | 242 | 02/24/25 | 437 | Pacific Plumbing Supply Co., LLC |  | 37.26 | 51788955
AP | 242 | 02/25/25 | 459 | Capital One Credit Card |  | 96.44 | 012025J
AP | 242 | 02/25/25 | 465 | Capital One Credit Card |  | 51.54 | 022325J
GL | 242 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 33.14
GL | 242 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 6.63
GL | 242 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | -3.7
AP | 242 | 05/27/25 | 299 | Capital One Credit Card |  | 206.63 | 050725J
GL | 242 | 05/30/25 | 605 | Req 660 |  | -3882.62
GL | 242 | 05/31/25 | 681 | 2025-05-26 to 2025-05-30 |  | 193.6
GL | 242 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 119.69
AP | 242 | 06/10/25 | 156 | Consolidated Supply Co. |  | 132.85 | S012449950.001
AP | 242 | 06/11/25 | 164 | Pacific Plumbing Supply Co., LLC |  | 7.98 | 51877304
AP | 242 | 06/11/25 | 165 | Pacific Plumbing Supply Co., LLC |  | 7.98 | 51877305
AP | 242 | 06/11/25 | 166 | Pacific Plumbing Supply Co., LLC |  | 43.75 | 51877307
GL | 242 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 1.87
AP | 242 | 06/25/25 | 458 | Kele, Inc $ MI Controls |  | 638.6 | IMIS0807037329
AP | 242 | 06/30/25 | 585 | Pacific Plumbing Supply Co., LLC |  | 3312 | 51890810
AP | 242 | 06/30/25 | 586 | Pacific Plumbing Supply Co., LLC |  | 87.24 | 51891499
AP | 242 | 06/30/25 | 603 | Kele, Inc $ MI Controls |  | 307.6 | IMIS0807037411
AP | 242 | 06/30/25 | 607 | Ferguson Enterprises, Inc. #3007 |  | 720.09 | 9811134
AP | 242 | 07/07/25 | 79 | Pacific Plumbing Supply Co., LLC |  | 1668.91 | 51890730
AP | 242 | 07/09/25 | 108 | Pacific Plumbing Supply Co., LLC |  | 15.04 | 51893591
GL | 242 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 45.26
GL | 242 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | -22.71
AP | 242 | 07/15/25 | 269 | Kele, Inc $ MI Controls |  | 463.06 | IMIS0807037430
GL | 242 | 07/21/25 | 371 | Req 683 |  | -916.56
GL | 242 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 5.2
AP | 242 | 07/22/25 | 413 | Bank of America CC |  | 44.1 | 070725J
AP | 242 | 07/25/25 | 288 | Pacific Plumbing Supply Co., LLC |  | 432.91 | 51906096
AP | 242 | 07/25/25 | 290 | Pacific Plumbing Supply Co., LLC |  | 432.91 | 51908495
AP | 242 | 07/25/25 | 549 | MacArthur Co. NW 6276 |  | 957.14 | 252205279
AP | 242 | 08/01/25 | 93 | Consolidated Supply Co. |  | 158.38 | S012532536.001
AP | 242 | 08/26/25 | 483 | Bank of America CC |  | 65.03 | 071525J
AP | 242 | 08/29/25 | 588 | Capital One Credit Card |  | 13.06 | 071525J1
AP | 242 | 09/17/25 | 230 | Pacific Plumbing Supply Co., LLC |  | 31.25 | 51945830
AP | 242 | 09/30/25 | 500 | Capital One Credit Card |  | 19.79 | 081825J
GL | 242 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -29.36
GL | 250 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 1.55
GL | 250 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 206.89
AP | 250 | 09/23/25 | 345 | Bank of America CC |  | 1040.35 | 090625J
GL | 250 | 09/25/25 | 478 | Jordan Games |  | 151.29
GL | 250 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 34.09
AP | 250 | 10/14/25 | 313 | Rosen Supply Kirkland |  | 3.81 | 34152.01
AP | 250 | 10/24/25 | 628 | Capital One Credit Card |  | 43.86 | 091825J
AP | 600 | 06/19/24 | 464 | Cascade Restoration Co. |  | 620 | 2838
AP | 600 | 07/30/24 | 654 | Patchworks, Inc. |  | 1800 | 12152
AP | 600 | 02/20/25 | 386 | A.R. Brown Backflow Testing |  | 280 | 3225
AP | 600 | 04/30/25 | 681 | Chemical Products Company |  | 3150 | 4061
AP | 600 | 06/24/25 | 411 | Mechanical Resource Services, Inc. |  | 10350 | 17794-6216
AP | 601 | 01/30/23 | 643 | Franklin Engineering |  | 10912 | 8862
AP | 601 | 02/20/23 | 618 | Franklin Engineering |  | 18944 | 8893
AP | 601 | 03/22/23 | 683 | Franklin Engineering |  | 15387.5 | 8937
AP | 601 | 05/02/23 | 23 | Franklin Engineering |  | 13785.25 | 8973
AP | 601 | 06/05/23 | 136 | Franklin Engineering |  | 1346 | 9017
AP | 601 | 06/30/23 | 1132 | Franklin Engineering |  | 6179 | 9051
AP | 601 | 07/31/23 | 882 | Franklin Engineering |  | 6529 | 9087
AP | 601 | 09/05/23 | 164 | Franklin Engineering |  | 5943 | 9124
AP | 601 | 09/25/23 | 984 | Franklin Engineering |  | 4795 | 9163
AP | 601 | 10/31/23 | 1062 | Franklin Engineering |  | 16390 | 9194
AP | 601 | 11/15/23 | 1201 | Franklin Engineering |  | 2277.5 | 9228
AP | 601 | 12/20/23 | 916 | Franklin Engineering |  | 1550 | 9261
AP | 601 | 01/26/24 | 1069 | Franklin Engineering |  | 1286.25 | 1005
AP | 601 | 08/14/24 | 408 | Franklin Engineering |  | 1635 | 1174
AP | 602 | 09/25/23 | 998 | Williams Scotsman, Inc. $Mobile Mini |  | 1225.34 | 9018867328
AP | 602 | 10/31/23 | 1065 | Williams Scotsman, Inc. $Mobile Mini |  | 216.42 | 9019130820
AP | 602 | 11/27/23 | 1253 | Williams Scotsman, Inc. $Mobile Mini |  | 216.42 | 9019391656
AP | 602 | 12/20/23 | 921 | Williams Scotsman, Inc. $Mobile Mini |  | 216.42 | 9019641992
AP | 602 | 01/16/24 | 591 | Williams Scotsman, Inc. $Mobile Mini |  | 216.42 | 9019877934
AP | 602 | 02/05/24 | 180 | Sunstate Equipment Co |  | 584.75 | 12199777-001
AP | 602 | 02/05/24 | 181 | Sunstate Equipment Co |  | 446.94 | 12199792-001
AP | 602 | 02/13/24 | 475 | Sunstate Equipment Co |  | 584.75 | 12220619-002
AP | 602 | 02/20/24 | 633 | Williams Scotsman, Inc. $Mobile Mini |  | -18.74 | 9020224711
AP | 602 | 02/20/24 | 634 | Williams Scotsman, Inc. $Mobile Mini |  | -18.74 | 9020224712
AP | 602 | 02/20/24 | 635 | Williams Scotsman, Inc. $Mobile Mini |  | -18.74 | 9020224713
AP | 602 | 02/20/24 | 636 | Williams Scotsman, Inc. $Mobile Mini |  | -18.74 | 9020224714
AP | 602 | 02/20/24 | 637 | Williams Scotsman, Inc. $Mobile Mini |  | 216.42 | 9020109201
AP | 602 | 02/28/24 | 899 | Sunstate Equipment Co |  | 446.94 | 12199777-002
AP | 602 | 02/28/24 | 900 | Sunstate Equipment Co |  | 446.94 | 12199792-002
AP | 602 | 03/18/24 | 692 | Williams Scotsman, Inc. $Mobile Mini |  | 197.68 | 9020337141
AP | 602 | 03/18/24 | 697 | Sunstate Equipment Co |  | 446.94 | 12220619-003
AP | 602 | 03/28/24 | 1298 | Sunstate Equipment Co |  | 446.94 | 121997777-003
AP | 602 | 03/28/24 | 1299 | Sunstate Equipment Co |  | 446.94 | 12199792-003
AP | 602 | 03/31/24 | 1348 | Williams Scotsman, Inc. $Mobile Mini |  | 197.68 | 9020563996
AP | 602 | 04/01/24 | 748 | Sunstate Equipment Co |  | 447.33 | 12199777-004
AP | 602 | 04/01/24 | 749 | Sunstate Equipment Co |  | 447.33 | 1299792-004
AP | 602 | 04/12/24 | 326 | Sunstate Equipment Co |  | 446.94 | 12220619-004
AP | 602 | 04/12/24 | 327 | Sunstate Equipment Co |  | 137.81 | 12220619-005
AP | 602 | 04/30/24 | 940 | Williams Scotsman, Inc. $Mobile Mini |  | 197.86 | 9020791813
AP | 602 | 05/22/24 | 661 | Sunstate Equipment Co |  | 447.33 | 12199777-005
AP | 602 | 05/22/24 | 662 | Sunstate Equipment Co |  | 447.33 | 12199792-005
AP | 602 | 05/29/24 | 790 | Williams Scotsman, Inc. $Mobile Mini |  | 197.86 | 9021019469
AP | 602 | 06/17/24 | 435 | Sunstate Equipment Co |  | 585.27 | 12199777-006
AP | 602 | 06/19/24 | 467 | Sunstate Equipment Co |  | 447.33 | 12199792-006
AP | 602 | 06/25/24 | 634 | Williams Scotsman, Inc. $Mobile Mini |  | 197.86 | 9021244603
AP | 602 | 07/17/24 | 367 | Sunstate Equipment Co |  | 447.33 | 12199792-007
AP | 602 | 07/22/24 | 477 | Williams Scotsman, Inc. $Mobile Mini |  | 197.86 | 9021465479
AP | 602 | 08/09/24 | 348 | Williams Scotsman, Inc. $Mobile Mini |  | 178.74 | 9021585548
AP | 602 | 08/14/24 | 411 | Sunstate Equipment Co |  | 447.33 | 12199792-008
AP | 602 | 09/11/24 | 214 | Sunstate Equipment Co |  | 447.33 | 12199792-009
AP | 602 | 10/09/24 | 194 | Sunstate Equipment Co |  | 447.33 | 12199792-010
AP | 602 | 10/22/24 | 560 | Sunbelt Rentals, Inc. |  | 436.71 | 12199792-011
AP | 602 | 11/01/24 | 117 | Sunbelt Rentals, Inc. |  | -436.71 | 12199792-011A
AP | 602 | 11/01/24 | 118 | Sunstate Equipment Co |  | 436.71 | 12199792-011B
AP | 603 | 04/26/23 | 641 | Bank of America CC |  | 201 | 032823B
AP | 603 | 08/30/23 | 993 | Bank of America CC |  | 3115.5 | 073123B
AP | 603 | 08/30/23 | 994 | Bank of America CC |  | 18581 | 080223B
AP | 603 | 06/30/24 | 828 | Bank of America CC |  | 210 | 052824J
AP | 603 | 06/30/24 | 842 | Bank of America CC |  | 201 | 052124B
AP | 603 | 08/20/24 | 617 | Bank of America CC |  | 130 | 073024J
AP | 603 | 03/18/25 | 321 | Bank of America CC |  | 236 | 022025J
AP | 603 | 03/18/25 | 325 | Bank of America CC |  | 50 | 022525J
AP | 603 | 03/18/25 | 337 | Bank of America CC |  | 3779.27 | 022725B
AP | 607 | 09/06/23 | 223 | Hub International Northwest |  | 60451 | 3309214
GL | 607 | 09/30/23 | 1298 | Silver Coud University Hotel |  | 786.24
AP | 607 | 10/20/23 | 838 | University Silver Cloud Hotel $Trailside |  | 748.8 | 90521-0221
AP | 607 | 11/27/23 | 1255 | University Silver Cloud Hotel $Trailside |  | 748.8 | 090521-0221
AP | 607 | 12/22/23 | 1091 | University Silver Cloud Hotel $Trailside |  | 785.93 | 090521-2035
AP | 607 | 01/23/24 | 880 | University Silver Cloud Hotel $Trailside |  | 711.08 | 090521-2025
AP | 607 | 03/07/24 | 248 | University Silver Cloud Hotel $Trailside |  | 1284.93 | 90521-2026
AP | 607 | 03/25/24 | 1011 | University Silver Cloud Hotel $Trailside |  | 1097.8 | 90521-2027
AP | 607 | 04/23/24 | 621 | University Silver Cloud Hotel $Trailside |  | 1097.8 | 090521-2028
AP | 607 | 05/23/24 | 675 | University Silver Cloud Hotel $Trailside |  | 948.86 | 052224
AP | 607 | 06/21/24 | 573 | University Silver Cloud Hotel $Trailside |  | 1098.68 | 90521-2030
AP | 607 | 07/23/24 | 521 | University Silver Cloud Hotel $Trailside |  | 1098.68 | 09521-2031
AP | 607 | 08/22/24 | 687 | University Silver Cloud Hotel $Trailside |  | 998.8 | 090521-2032
AP | 607 | 09/24/24 | 494 | University Silver Cloud Hotel $Trailside |  | 1098.68 | 090521-2034
AP | 607 | 10/28/24 | 691 | University Silver Cloud Hotel $Trailside |  | 948.86 | 2024-11
AP | 607 | 11/25/24 | 593 | University Silver Cloud Hotel $Trailside |  | 1048.74 | 90521-2036
AP | 607 | 12/26/24 | 536 | University Silver Cloud Hotel $Trailside |  | 524.37 | 90521-2026.
AP | 607 | 01/23/25 | 570 | University Silver Cloud Hotel $Trailside |  | 474.43 | 90521-2027.
AP | 607 | 02/26/25 | 483 | University Silver Cloud Hotel $Trailside |  | 524.37 | 02262025
AP | 607 | 03/25/25 | 532 | University Silver Cloud Hotel $Trailside |  | 549.34 | 090521-2029
AP | 607 | 05/28/25 | 529 | University Silver Cloud Hotel $Trailside |  | 249.7 | 90521-2031
AP | 607 | 06/24/25 | 393 | University Silver Cloud Hotel $Trailside |  | 274.67 | 90521-2032
PR | 995 | 04/14/23 | 355 | Gerard, Jeffrey S |  | 26.03
PR | 995 | 04/28/23 | 783 | Gerard, Jeffrey S |  | 26.03
PR | 995 | 05/05/23 | 185 | Gerard, Jeffrey S |  | 78.09
PR | 995 | 05/12/23 | 423 | Gerard, Jeffrey S |  | 156.19
PR | 995 | 05/12/23 | 423 | Gerard, Jeffrey S |  | 78.09
PR | 995 | 05/19/23 | 644 | Gerard, Jeffrey S |  | 104.13
PR | 995 | 05/26/23 | 974 | Gerard, Jeffrey S |  | 156.19
PR | 995 | 05/26/23 | 974 | Gerard, Jeffrey S |  | 52.06
PR | 995 | 06/02/23 | 102 | Gerard, Jeffrey S |  | 52.06
PR | 995 | 06/09/23 | 357 | Gerard, Jeffrey S |  | 52.06
PR | 995 | 06/23/23 | 835 | Johnson, Jake E |  | 41.65
PR | 995 | 06/23/23 | 887 | Gerard, Jeffrey S |  | 52.06
PR | 995 | 06/30/23 | 1030 | Johnson, Jake E |  | 208.25
PR | 995 | 06/30/23 | 1080 | Gerard, Jeffrey S |  | 78.09
PR | 995 | 06/30/23 | 1080 | Gerard, Jeffrey S |  | 52.06
PR | 995 | 07/07/23 | 63 | Johnson, Jake E |  | 41.65
PR | 995 | 07/07/23 | 113 | Gerard, Jeffrey S |  | 26.03
PR | 995 | 07/14/23 | 379 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 07/20/23 | 568 | Johnson, Jake E |  | 43.32
PR | 995 | 07/20/23 | 615 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 07/28/23 | 707 | Johnson, Jake E |  | 43.32
PR | 995 | 08/04/23 | 109 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/11/23 | 323 | Johnson, Jake E |  | 43.32
PR | 995 | 08/11/23 | 375 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 08/18/23 | 559 | Johnson, Jake E |  | 64.97
PR | 995 | 08/18/23 | 612 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 08/18/23 | 612 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/25/23 | 780 | Johnson, Jake E |  | 108.29
PR | 995 | 08/25/23 | 834 | Gerard, Jeffrey S |  | 129.32
PR | 995 | 08/25/23 | 834 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 09/01/23 | 61 | Johnson, Jake E |  | 64.97
PR | 995 | 09/01/23 | 115 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 09/01/23 | 115 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 09/08/23 | 344 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 09/08/23 | 344 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 09/15/23 | 508 | Anderson, Richard P |  | 135.36
PR | 995 | 09/15/23 | 514 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/15/23 | 567 | Johnson, Jake E |  | 43.32
PR | 995 | 09/15/23 | 587 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 09/15/23 | 623 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 09/15/23 | 623 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 09/22/23 | 807 | Anderson, Richard P |  | 798.64
PR | 995 | 09/22/23 | 811 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 09/22/23 | 813 | Barnhart, Joseph N |  | 113.29
PR | 995 | 09/22/23 | 847 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 09/22/23 | 864 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 09/22/23 | 865 | Johnson, Jake E |  | 129.95
PR | 995 | 09/22/23 | 884 | Paco Leyva, Orlando |  | 609.76
PR | 995 | 09/22/23 | 896 | Rodriguez, Eduardo D |  | 259.9
PR | 995 | 09/22/23 | 918 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 09/22/23 | 918 | Gerard, Jeffrey S |  | 129.32
PR | 995 | 09/29/23 | 1128 | Anderson, Richard P |  | 744.49
PR | 995 | 09/29/23 | 1132 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 09/29/23 | 1170 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 09/29/23 | 1188 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 09/29/23 | 1189 | Johnson, Jake E |  | 86.63
PR | 995 | 09/29/23 | 1210 | Paco Leyva, Orlando |  | 1016.26
PR | 995 | 09/29/23 | 1221 | Rodriguez, Eduardo D |  | 173.26
PR | 995 | 09/29/23 | 1245 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 09/29/23 | 1245 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/06/23 | 23 | Anderson, Richard P |  | 297.8
PR | 995 | 10/06/23 | 27 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 10/06/23 | 65 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 10/06/23 | 85 | Jimenez Alvarenga, Gerson M |  | 422.33
PR | 995 | 10/06/23 | 86 | Johnson, Jake E |  | 108.29
PR | 995 | 10/06/23 | 107 | Paco Leyva, Orlando |  | 914.63
PR | 995 | 10/06/23 | 142 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 10/06/23 | 142 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/13/23 | 322 | Anderson, Richard P |  | 636.2
PR | 995 | 10/13/23 | 364 | Fox, Tamron P |  | 89.96
PR | 995 | 10/13/23 | 365 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 10/13/23 | 385 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 10/13/23 | 386 | Johnson, Jake E |  | 108.29
PR | 995 | 10/13/23 | 404 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 10/13/23 | 407 | Paco Leyva, Orlando |  | 813.01
PR | 995 | 10/13/23 | 415 | Reed, Reuben H |  | 206.58
PR | 995 | 10/13/23 | 442 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 10/13/23 | 442 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 10/20/23 | 591 | Anderson, Richard P |  | 406.09
PR | 995 | 10/20/23 | 595 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 10/20/23 | 597 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/20/23 | 597 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/20/23 | 633 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 10/20/23 | 653 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 10/20/23 | 654 | Johnson, Jake E |  | 173.26
PR | 995 | 10/20/23 | 671 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 10/20/23 | 675 | Paco Leyva, Orlando |  | 889.23
PR | 995 | 10/20/23 | 711 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 10/27/23 | 842 | Anderson, Richard P |  | 406.09
PR | 995 | 10/27/23 | 842 | Anderson, Richard P |  | 162.44
PR | 995 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I |  | 210.75
PR | 995 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I |  | 403.17
PR | 995 | 10/27/23 | 884 | Galdamez, Dagoberto A |  | 586.02
PR | 995 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M |  | 357.36
PR | 995 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M |  | 32.49
PR | 995 | 10/27/23 | 905 | Johnson, Jake E |  | 108.29
PR | 995 | 10/27/23 | 926 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/27/23 | 926 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 10/27/23 | 961 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 10/27/23 | 961 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 11/03/23 | 5 | Anderson, Richard P |  | 433.16
PR | 995 | 11/03/23 | 5 | Anderson, Richard P |  | 514.38
PR | 995 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I |  | 311.54
PR | 995 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I |  | 421.5
PR | 995 | 11/03/23 | 11 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/03/23 | 47 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 11/03/23 | 47 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M |  | 276.14
PR | 995 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M |  | 373.6
PR | 995 | 11/03/23 | 68 | Johnson, Jake E |  | 151.61
PR | 995 | 11/03/23 | 85 | Nunez Bravo, Jose L |  | 134.11
PR | 995 | 11/03/23 | 85 | Nunez Bravo, Jose L |  | 172.43
PR | 995 | 11/03/23 | 123 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 11/03/23 | 123 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/10/23 | 448 | Anderson, Richard P |  | 934
PR | 995 | 11/10/23 | 452 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 11/10/23 | 482 | Draves, Steven W |  | 68.72
PR | 995 | 11/10/23 | 490 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 11/10/23 | 510 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 11/10/23 | 511 | Johnson, Jake E |  | 86.63
PR | 995 | 11/10/23 | 528 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 11/10/23 | 532 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/17/23 | 807 | Anderson, Richard P |  | 893.39
PR | 995 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I |  | 54.98
PR | 995 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 11/17/23 | 847 | Galdamez, Dagoberto A |  | 52.48
PR | 995 | 11/17/23 | 847 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M |  | 48.73
PR | 995 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 11/17/23 | 867 | Johnson, Jake E |  | 86.63
PR | 995 | 11/17/23 | 884 | Nunez Bravo, Jose L |  | 296.96
PR | 995 | 11/17/23 | 888 | Paco Leyva, Orlando |  | 965.45
PR | 995 | 11/17/23 | 923 | Gerard, Jeffrey S |  | 229.91
PR | 995 | 11/17/23 | 923 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/22/23 | 1056 | Anderson, Richard P |  | 108.29
PR | 995 | 11/22/23 | 1060 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 11/22/23 | 1095 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 11/22/23 | 1115 | Jimenez Alvarenga, Gerson M |  | 129.95
PR | 995 | 11/22/23 | 1116 | Johnson, Jake E |  | 43.32
PR | 995 | 11/22/23 | 1116 | Johnson, Jake E |  | 21.66
PR | 995 | 11/22/23 | 1133 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 11/22/23 | 1137 | Paco Leyva, Orlando |  | 711.38
PR | 995 | 11/22/23 | 1172 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/01/23 | 45 | Galdamez, Dagoberto A |  | 69.97
PR | 995 | 12/01/23 | 45 | Galdamez, Dagoberto A |  | 104.96
PR | 995 | 12/01/23 | 66 | Johnson, Jake E |  | 21.66
PR | 995 | 12/01/23 | 87 | Paco Leyva, Orlando |  | 584.35
PR | 995 | 12/01/23 | 87 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 12/01/23 | 123 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 12/08/23 | 326 | Anderson, Richard P |  | 135.36
PR | 995 | 12/08/23 | 326 | Anderson, Richard P |  | 162.44
PR | 995 | 12/08/23 | 330 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 12/08/23 | 331 | Barnhart, Joseph N |  | 28.32
PR | 995 | 12/08/23 | 331 | Barnhart, Joseph N |  | 28.32
PR | 995 | 12/08/23 | 364 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 12/08/23 | 384 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 12/08/23 | 385 | Johnson, Jake E |  | 108.29
PR | 995 | 12/08/23 | 406 | Paco Leyva, Orlando |  | 660.57
PR | 995 | 12/08/23 | 406 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 12/08/23 | 443 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 12/08/23 | 443 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 12/15/23 | 678 | Anderson, Richard P |  | 108.29
PR | 995 | 12/15/23 | 682 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 12/15/23 | 717 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 12/15/23 | 717 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 12/15/23 | 737 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 12/15/23 | 738 | Johnson, Jake E |  | 21.66
PR | 995 | 12/15/23 | 759 | Paco Leyva, Orlando |  | 863.82
PR | 995 | 12/15/23 | 794 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 12/15/23 | 794 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 12/22/23 | 958 | Anderson, Richard P |  | 81.22
PR | 995 | 12/22/23 | 962 | Balderas Ortiz, Ricardo I |  | 274.89
PR | 995 | 12/22/23 | 997 | Galdamez, Dagoberto A |  | 183.68
PR | 995 | 12/22/23 | 997 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M |  | 170.56
PR | 995 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M |  | 259.9
PR | 995 | 12/22/23 | 1033 | Nunez Bravo, Jose L |  | 67.06
PR | 995 | 12/22/23 | 1037 | Paco Leyva, Orlando |  | 266.77
PR | 995 | 12/22/23 | 1037 | Paco Leyva, Orlando |  | 813.01
PR | 995 | 12/22/23 | 1073 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 12/22/23 | 1073 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 12/22/23 | 1075 | Johnson, Jake E |  | 43.32
PR | 995 | 12/22/23 | 1075 | Johnson, Jake E |  | 21.66
PR | 995 | 12/29/23 | 1106 | Anderson, Richard P |  | 81.22
PR | 995 | 12/29/23 | 1110 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 12/29/23 | 1164 | Jimenez Alvarenga, Gerson M |  | 129.95
PR | 995 | 12/29/23 | 1181 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 12/29/23 | 1185 | Paco Leyva, Orlando |  | 711.38
PR | 995 | 12/29/23 | 1220 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 12/29/23 | 1220 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 12/29/23 | 1222 | Johnson, Jake E |  | 21.66
PR | 995 | 01/05/24 | 16 | Anderson, Richard P |  | 541.45
PR | 995 | 01/05/24 | 20 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 01/05/24 | 21 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/05/24 | 55 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 01/05/24 | 61 | Gochez Molina, Douglas O |  | 291.55
PR | 995 | 01/05/24 | 61 | Gochez Molina, Douglas O |  | 41.65
PR | 995 | 01/05/24 | 74 | Jimenez Alvarenga, Gerson M |  | 129.95
PR | 995 | 01/05/24 | 91 | Nunez Bravo, Jose L |  | 153.27
PR | 995 | 01/05/24 | 92 | Nuno Ordonez, Roberto F |  | 39.98
PR | 995 | 01/05/24 | 92 | Nuno Ordonez, Roberto F |  | 39.98
PR | 995 | 01/05/24 | 95 | Paco Leyva, Orlando |  | 813.01
PR | 995 | 01/05/24 | 130 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 01/05/24 | 130 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 01/05/24 | 132 | Johnson, Jake E |  | 43.32
PR | 995 | 01/12/24 | 354 | Anderson, Richard P |  | 175.97
PR | 995 | 01/12/24 | 354 | Anderson, Richard P |  | 40.61
PR | 995 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 366.52
PR | 995 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 73.3
PR | 995 | 01/12/24 | 378 | de Dios, Pedro |  | 43.32
PR | 995 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 349.86
PR | 995 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 69.97
PR | 995 | 01/12/24 | 399 | Gochez Molina, Douglas O |  | 249.9
PR | 995 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 324.87
PR | 995 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 64.97
PR | 995 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 259.9
PR | 995 | 01/12/24 | 422 | McCurry, Maxwell J |  | 39.98
PR | 995 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 268.23
PR | 995 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 38.32
PR | 995 | 01/12/24 | 429 | Nuno Ordonez, Roberto F |  | 159.94
PR | 995 | 01/12/24 | 432 | Paco Leyva, Orlando |  | 914.63
PR | 995 | 01/12/24 | 432 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 01/12/24 | 465 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 01/12/24 | 465 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 01/12/24 | 467 | Johnson, Jake E |  | 64.97
PR | 995 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I |  | 678.06
PR | 995 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I |  | 54.98
PR | 995 | 01/19/24 | 653 | Barnhart, Joseph N |  | 28.32
PR | 995 | 01/19/24 | 656 | Belcher, Jacob T |  | 46.65
PR | 995 | 01/19/24 | 660 | Carmona, Raul O |  | 353.19
PR | 995 | 01/19/24 | 687 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 01/19/24 | 688 | Games, Jordan M |  | 114.95
PR | 995 | 01/19/24 | 693 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 01/19/24 | 693 | Gochez Molina, Douglas O |  | 83.3
PR | 995 | 01/19/24 | 704 | Jimenez, D'angelo J |  | 326.54
PR | 995 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M |  | 259.9
PR | 995 | 01/19/24 | 715 | McCurry, Maxwell J |  | 39.98
PR | 995 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 76.64
PR | 995 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 153.27
PR | 995 | 01/19/24 | 722 | Nuno Ordonez, Roberto F |  | 159.94
PR | 995 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/19/24 | 740 | Sontay Garcia, Juan C |  | 209.92
PR | 995 | 01/19/24 | 758 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 01/19/24 | 758 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 01/19/24 | 760 | Johnson, Jake E |  | 86.63
PR | 995 | 01/26/24 | 918 | Anderson, Richard P |  | 81.22
PR | 995 | 01/26/24 | 922 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 01/26/24 | 926 | Belcher, Jacob T |  | 466.48
PR | 995 | 01/26/24 | 930 | Carmona, Raul O |  | 882.98
PR | 995 | 01/26/24 | 957 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 01/26/24 | 957 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 01/26/24 | 963 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 01/26/24 | 975 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 01/26/24 | 985 | McCurry, Maxwell J |  | 239.9
PR | 995 | 01/26/24 | 985 | McCurry, Maxwell J |  | 79.97
PR | 995 | 01/26/24 | 991 | Nunez Bravo, Jose L |  | 210.75
PR | 995 | 01/26/24 | 991 | Nunez Bravo, Jose L |  | 153.27
PR | 995 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 482.72
PR | 995 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/26/24 | 1011 | Sontay Garcia, Juan C |  | 279.89
PR | 995 | 01/26/24 | 1029 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 01/26/24 | 1029 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 01/26/24 | 1031 | Johnson, Jake E |  | 43.32
PR | 995 | 02/02/24 | 11 | Anderson, Richard P |  | 81.22
PR | 995 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 02/02/24 | 16 | Barnhart, Joseph N |  | 70.81
PR | 995 | 02/02/24 | 19 | Belcher, Jacob T |  | 326.54
PR | 995 | 02/02/24 | 19 | Belcher, Jacob T |  | 139.94
PR | 995 | 02/02/24 | 23 | Carmona, Raul O |  | 618.09
PR | 995 | 02/02/24 | 23 | Carmona, Raul O |  | 264.89
PR | 995 | 02/02/24 | 50 | Galdamez, Dagoberto A |  | 489.8
PR | 995 | 02/02/24 | 50 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 02/02/24 | 56 | Gochez Molina, Douglas O |  | 166.6
PR | 995 | 02/02/24 | 56 | Gochez Molina, Douglas O |  | 249.9
PR | 995 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M |  | 259.9
PR | 995 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 02/02/24 | 78 | McCurry, Maxwell J |  | 79.97
PR | 995 | 02/02/24 | 78 | McCurry, Maxwell J |  | 119.95
PR | 995 | 02/02/24 | 78 | McCurry, Maxwell J |  | 119.95
PR | 995 | 02/02/24 | 84 | Nunez Bravo, Jose L |  | 268.23
PR | 995 | 02/02/24 | 84 | Nunez Bravo, Jose L |  | 114.95
PR | 995 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 558.94
PR | 995 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 02/02/24 | 104 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 02/02/24 | 105 | Storozhuk, Maxim A |  | 183.26
PR | 995 | 02/02/24 | 105 | Storozhuk, Maxim A |  | 36.65
PR | 995 | 02/02/24 | 121 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 02/02/24 | 121 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 02/02/24 | 123 | Johnson, Jake E |  | 64.97
PR | 995 | 02/09/24 | 231 | Anderson, Richard P |  | 27.07
PR | 995 | 02/09/24 | 235 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 02/09/24 | 239 | Belcher, Jacob T |  | 93.3
PR | 995 | 02/09/24 | 239 | Belcher, Jacob T |  | 373.18
PR | 995 | 02/09/24 | 243 | Carmona, Raul O |  | 353.19
PR | 995 | 02/09/24 | 243 | Carmona, Raul O |  | 529.79
PR | 995 | 02/09/24 | 266 | Escalante Escobar, Boanerge |  | 233.24
PR | 995 | 02/09/24 | 270 | Galdamez, Dagoberto A |  | 349.86
PR | 995 | 02/09/24 | 270 | Galdamez, Dagoberto A |  | 349.86
PR | 995 | 02/09/24 | 276 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 02/09/24 | 276 | Gochez Molina, Douglas O |  | 83.3
PR | 995 | 02/09/24 | 288 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 02/09/24 | 297 | McCabe, Thomas C |  | 439.82
PR | 995 | 02/09/24 | 298 | McCurry, Maxwell J |  | 239.9
PR | 995 | 02/09/24 | 298 | McCurry, Maxwell J |  | 159.94
PR | 995 | 02/09/24 | 304 | Nunez Bravo, Jose L |  | 229.91
PR | 995 | 02/09/24 | 304 | Nunez Bravo, Jose L |  | 153.27
PR | 995 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 533.54
PR | 995 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 381.1
PR | 995 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 02/09/24 | 345 | Johnson, Jake E |  | 64.97
PR | 995 | 02/16/24 | 488 | Anderson, Richard P |  | 108.29
PR | 995 | 02/16/24 | 492 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 02/16/24 | 496 | Belcher, Jacob T |  | 373.18
PR | 995 | 02/16/24 | 500 | Carmona, Raul O |  | 882.98
PR | 995 | 02/16/24 | 523 | Escalante Escobar, Boanerge |  | 116.62
PR | 995 | 02/16/24 | 523 | Escalante Escobar, Boanerge |  | 466.48
PR | 995 | 02/16/24 | 527 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 02/16/24 | 533 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 02/16/24 | 543 | Hubbard, Justin A |  | 459.82
PR | 995 | 02/16/24 | 545 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 02/16/24 | 554 | McCabe, Thomas C |  | 723.88
PR | 995 | 02/16/24 | 555 | McCurry, Maxwell J |  | 394.84
PR | 995 | 02/16/24 | 559 | Molina, Carlos G |  | 433.16
PR | 995 | 02/16/24 | 561 | Nunez Bravo, Jose L |  | 239.49
PR | 995 | 02/16/24 | 561 | Nunez Bravo, Jose L |  | 143.69
PR | 995 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 533.54
PR | 995 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 190.55
PR | 995 | 02/16/24 | 582 | Sontay Garcia, Juan C |  | 279.89
PR | 995 | 02/16/24 | 583 | Storozhuk, Maxim A |  | 293.22
PR | 995 | 02/16/24 | 584 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 02/16/24 | 597 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 02/16/24 | 599 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 02/16/24 | 599 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 02/16/24 | 601 | Johnson, Jake E |  | 43.32
PR | 995 | 02/23/24 | 659 | Anderson, Richard P |  | 81.22
PR | 995 | 02/23/24 | 663 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 02/23/24 | 667 | Belcher, Jacob T |  | 384.85
PR | 995 | 02/23/24 | 671 | Carmona, Raul O |  | 529.79
PR | 995 | 02/23/24 | 693 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 02/23/24 | 697 | Galdamez, Dagoberto A |  | 682.23
PR | 995 | 02/23/24 | 701 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 02/23/24 | 711 | Hubbard, Justin A |  | 593.93
PR | 995 | 02/23/24 | 713 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 02/23/24 | 722 | McCabe, Thomas C |  | 293.22
PR | 995 | 02/23/24 | 722 | McCabe, Thomas C |  | 421.5
PR | 995 | 02/23/24 | 723 | McCurry, Maxwell J |  | 79.97
PR | 995 | 02/23/24 | 723 | McCurry, Maxwell J |  | 224.91
PR | 995 | 02/23/24 | 724 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 02/23/24 | 727 | Molina, Carlos G |  | 335.7
PR | 995 | 02/23/24 | 729 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 533.54
PR | 995 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 02/23/24 | 750 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 02/23/24 | 751 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 02/23/24 | 752 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 02/23/24 | 765 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 02/23/24 | 770 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 02/23/24 | 770 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 02/23/24 | 773 | Johnson, Jake E |  | 86.63
PR | 995 | 03/01/24 | 4 | Anderson, Richard P |  | 108.29
PR | 995 | 03/01/24 | 8 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 03/01/24 | 12 | Belcher, Jacob T |  | 279.89
PR | 995 | 03/01/24 | 12 | Belcher, Jacob T |  | 93.3
PR | 995 | 03/01/24 | 15 | Carmona, Raul O |  | 706.38
PR | 995 | 03/01/24 | 36 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 03/01/24 | 37 | Escobar Ramirez, Carlos M |  | 183.26
PR | 995 | 03/01/24 | 42 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 03/01/24 | 48 | Guerrero Espinoza, Mario |  | 174.93
PR | 995 | 03/01/24 | 51 | Hubbard, Justin A |  | 766.36
PR | 995 | 03/01/24 | 53 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 03/01/24 | 55 | Lopez, Maslin A |  | 192.42
PR | 995 | 03/01/24 | 55 | Lopez, Maslin A |  | 109.96
PR | 995 | 03/01/24 | 60 | McCabe, Thomas C |  | 439.82
PR | 995 | 03/01/24 | 60 | McCabe, Thomas C |  | 109.96
PR | 995 | 03/01/24 | 61 | McCurry, Maxwell J |  | 239.9
PR | 995 | 03/01/24 | 61 | McCurry, Maxwell J |  | 159.94
PR | 995 | 03/01/24 | 62 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 03/01/24 | 65 | Molina, Carlos G |  | 173.26
PR | 995 | 03/01/24 | 67 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 558.94
PR | 995 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 03/01/24 | 80 | Rodriguez Arevalos, Christian |  | 146.61
PR | 995 | 03/01/24 | 86 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 03/01/24 | 87 | Storozhuk, Maxim A |  | 293.22
PR | 995 | 03/01/24 | 88 | Suniga Aviles, Kelvin A |  | 279.89
PR | 995 | 03/01/24 | 95 | Wilson, Garret A |  | 179.93
PR | 995 | 03/01/24 | 96 | Yohannes Jr., Samson |  | 302.38
PR | 995 | 03/01/24 | 100 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 03/01/24 | 100 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 03/01/24 | 105 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 03/01/24 | 107 | Gerard, Mitchell J |  | 406.5
PR | 995 | 03/01/24 | 110 | Johnson, Jake E |  | 21.66
PR | 995 | 03/08/24 | 250 | Anderson, Richard P |  | 162.44
PR | 995 | 03/08/24 | 251 | Aquino, Juan |  | 359.86
PR | 995 | 03/08/24 | 252 | Barnhart, Joseph N |  | 28.32
PR | 995 | 03/08/24 | 254 | Belcher, Jacob T |  | 279.89
PR | 995 | 03/08/24 | 254 | Belcher, Jacob T |  | 93.3
PR | 995 | 03/08/24 | 255 | Carmona, Raul O |  | 706.38
PR | 995 | 03/08/24 | 269 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 03/08/24 | 270 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 03/08/24 | 273 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 03/08/24 | 276 | Guerrero Espinoza, Mario |  | 299.88
PR | 995 | 03/08/24 | 278 | Hubbard, Justin A |  | 593.93
PR | 995 | 03/08/24 | 278 | Hubbard, Justin A |  | 153.27
PR | 995 | 03/08/24 | 280 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 03/08/24 | 283 | Martinez Garcia, Cesar B |  | 266.56
PR | 995 | 03/08/24 | 284 | McCabe, Thomas C |  | 568.11
PR | 995 | 03/08/24 | 285 | McCurry, Maxwell J |  | 399.84
PR | 995 | 03/08/24 | 286 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 03/08/24 | 288 | Molina, Carlos G |  | 173.26
PR | 995 | 03/08/24 | 290 | Nunez Bravo, Jose L |  | 306.54
PR | 995 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 508.13
PR | 995 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 355.69
PR | 995 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 03/08/24 | 294 | Platero Navas, Ronald A |  | 266.56
PR | 995 | 03/08/24 | 296 | Puentez, Victor M |  | 146.61
PR | 995 | 03/08/24 | 296 | Puentez, Victor M |  | 219.91
PR | 995 | 03/08/24 | 299 | Rodriguez Arevalos, Christian |  | 73.3
PR | 995 | 03/08/24 | 305 | Sontay Garcia, Juan C |  | 279.89
PR | 995 | 03/08/24 | 306 | Storozhuk, Maxim A |  | 219.91
PR | 995 | 03/08/24 | 307 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 03/08/24 | 307 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 03/08/24 | 311 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 03/08/24 | 313 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 03/08/24 | 317 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 03/08/24 | 343 | Johnson, Jake E |  | 64.97
PR | 995 | 03/08/24 | 344 | Lopez, Maslin A |  | 549.78
PR | 995 | 03/08/24 | 358 | Taylor, Evan R |  | 541.45
PR | 995 | 03/08/24 | 363 | Young, Joshua S |  | 449.82
PR | 995 | 03/15/24 | 505 | Anderson, Richard P |  | 135.36
PR | 995 | 03/15/24 | 506 | Aquino, Juan |  | 449.82
PR | 995 | 03/15/24 | 509 | Belcher, Jacob T |  | 186.59
PR | 995 | 03/15/24 | 510 | Carmona, Raul O |  | 882.98
PR | 995 | 03/15/24 | 523 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 03/15/24 | 524 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 03/15/24 | 526 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 03/15/24 | 528 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 03/15/24 | 531 | Guerrero Espinoza, Mario |  | 399.84
PR | 995 | 03/15/24 | 533 | Hubbard, Justin A |  | 306.54
PR | 995 | 03/15/24 | 533 | Hubbard, Justin A |  | 306.54
PR | 995 | 03/15/24 | 533 | Hubbard, Justin A |  | 153.27
PR | 995 | 03/15/24 | 535 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 03/15/24 | 537 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 03/15/24 | 538 | McCurry, Maxwell J |  | 79.97
PR | 995 | 03/15/24 | 538 | McCurry, Maxwell J |  | 79.97
PR | 995 | 03/15/24 | 538 | McCurry, Maxwell J |  | 159.94
PR | 995 | 03/15/24 | 538 | McCurry, Maxwell J |  | 79.97
PR | 995 | 03/15/24 | 539 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 03/15/24 | 541 | Molina, Carlos G |  | 433.16
PR | 995 | 03/15/24 | 543 | Nunez Bravo, Jose L |  | 229.91
PR | 995 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 03/15/24 | 547 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 03/15/24 | 549 | Puentez, Victor M |  | 366.52
PR | 995 | 03/15/24 | 552 | Rodriguez Arevalos, Christian |  | 238.24
PR | 995 | 03/15/24 | 558 | Sontay Garcia, Juan C |  | 279.89
PR | 995 | 03/15/24 | 559 | Storozhuk, Maxim A |  | 293.22
PR | 995 | 03/15/24 | 560 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 03/15/24 | 560 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 03/15/24 | 564 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 03/15/24 | 566 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 03/15/24 | 574 | Puentez, Victor M |  | -366.52
PR | 995 | 03/15/24 | 580 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 03/15/24 | 599 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 03/15/24 | 601 | Gerard, Mitchell J |  | 50.81
PR | 995 | 03/15/24 | 601 | Gerard, Mitchell J |  | 101.63
PR | 995 | 03/15/24 | 608 | Johnson, Jake E |  | 64.97
PR | 995 | 03/15/24 | 610 | Lopez, Maslin A |  | 329.87
PR | 995 | 03/15/24 | 610 | Lopez, Maslin A |  | 219.91
PR | 995 | 03/15/24 | 625 | Puentez, Victor M |  | 366.52
PR | 995 | 03/15/24 | 629 | Taylor, Evan R |  | 866.32
PR | 995 | 03/15/24 | 635 | Young, Joshua S |  | 449.82
PR | 995 | 03/22/24 | 798 | Anderson, Richard P |  | 270.73
PR | 995 | 03/22/24 | 799 | Aquino, Juan |  | 449.82
PR | 995 | 03/22/24 | 802 | Belcher, Jacob T |  | 93.3
PR | 995 | 03/22/24 | 803 | Carmona, Raul O |  | 882.98
PR | 995 | 03/22/24 | 811 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 03/22/24 | 812 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 03/22/24 | 814 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 03/22/24 | 816 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 03/22/24 | 819 | Guerrero Espinoza, Mario |  | 399.84
PR | 995 | 03/22/24 | 821 | Hubbard, Justin A |  | 153.27
PR | 995 | 03/22/24 | 821 | Hubbard, Justin A |  | 306.54
PR | 995 | 03/22/24 | 821 | Hubbard, Justin A |  | 306.54
PR | 995 | 03/22/24 | 823 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 03/22/24 | 824 | McCurry, Maxwell J |  | 239.9
PR | 995 | 03/22/24 | 824 | McCurry, Maxwell J |  | 79.97
PR | 995 | 03/22/24 | 825 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 03/22/24 | 826 | Molina, Carlos G |  | 433.16
PR | 995 | 03/22/24 | 828 | Nunez Bravo, Jose L |  | 373.6
PR | 995 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 03/22/24 | 830 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 03/22/24 | 832 | Rodriguez Arevalos, Christian |  | 586.43
PR | 995 | 03/22/24 | 836 | Sontay Garcia, Juan C |  | 341.11
PR | 995 | 03/22/24 | 837 | Storozhuk, Maxim A |  | 238.24
PR | 995 | 03/22/24 | 838 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 03/22/24 | 842 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 03/22/24 | 847 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 03/22/24 | 878 | Johnson, Jake E |  | 64.97
PR | 995 | 03/22/24 | 880 | Lopez, Maslin A |  | 109.96
PR | 995 | 03/22/24 | 880 | Lopez, Maslin A |  | 329.87
PR | 995 | 03/22/24 | 884 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 03/22/24 | 886 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 03/22/24 | 896 | Puentez, Victor M |  | 366.52
PR | 995 | 03/22/24 | 902 | Taylor, Evan R |  | 866.32
PR | 995 | 03/22/24 | 907 | Wilson, Garret A |  | 292.38
PR | 995 | 03/22/24 | 908 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 03/22/24 | 909 | Young, Joshua S |  | 449.82
PR | 995 | 03/29/24 | 1180 | Anderson, Richard P |  | 162.44
PR | 995 | 03/29/24 | 1180 | Anderson, Richard P |  | 54.15
PR | 995 | 03/29/24 | 1181 | Aquino, Juan |  | 449.82
PR | 995 | 03/29/24 | 1182 | Barnhart, Joseph N |  | 56.64
PR | 995 | 03/29/24 | 1190 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 03/29/24 | 1192 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 03/29/24 | 1198 | Hubbard, Justin A |  | 603.51
PR | 995 | 03/29/24 | 1200 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 03/29/24 | 1202 | Molina, Carlos G |  | 433.16
PR | 995 | 03/29/24 | 1204 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 03/29/24 | 1210 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 03/29/24 | 1212 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 03/29/24 | 1216 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 03/29/24 | 1219 | Araque, Mario W |  | 366.52
PR | 995 | 03/29/24 | 1221 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 03/29/24 | 1226 | Carmona, Raul O |  | 882.98
PR | 995 | 03/29/24 | 1243 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 03/29/24 | 1249 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 03/29/24 | 1256 | Johnson, Jake E |  | 129.95
PR | 995 | 03/29/24 | 1258 | Lopez, Maslin A |  | 549.78
PR | 995 | 03/29/24 | 1262 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 03/29/24 | 1264 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 03/29/24 | 1265 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 03/29/24 | 1273 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 03/29/24 | 1276 | Puentez, Victor M |  | 366.52
PR | 995 | 03/29/24 | 1283 | Taylor, Evan R |  | 866.32
PR | 995 | 03/29/24 | 1289 | Yohannes Jr., Samson |  | 439.82
PR | 995 | 03/29/24 | 1290 | Young, Joshua S |  | 359.86
PR | 995 | 04/05/24 | 2 | Anderson, Richard P |  | 81.22
PR | 995 | 04/05/24 | 2 | Anderson, Richard P |  | 27.07
PR | 995 | 04/05/24 | 3 | Aquino, Juan |  | 449.82
PR | 995 | 04/05/24 | 4 | Barnhart, Joseph N |  | 28.32
PR | 995 | 04/05/24 | 12 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 04/05/24 | 14 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 04/05/24 | 17 | Guerrero Espinoza, Mario |  | 299.88
PR | 995 | 04/05/24 | 19 | Hubbard, Justin A |  | 450.24
PR | 995 | 04/05/24 | 21 | Molina, Carlos G |  | 259.9
PR | 995 | 04/05/24 | 21 | Molina, Carlos G |  | 86.63
PR | 995 | 04/05/24 | 21 | Molina, Carlos G |  | 86.63
PR | 995 | 04/05/24 | 23 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 04/05/24 | 25 | Rodriguez Arevalos, Christian |  | 238.24
PR | 995 | 04/05/24 | 29 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 04/05/24 | 32 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 04/05/24 | 32 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 04/05/24 | 36 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 04/05/24 | 41 | Carmona, Raul O |  | 882.98
PR | 995 | 04/05/24 | 59 | Escobar Ramirez, Carlos M |  | 308.21
PR | 995 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 04/05/24 | 65 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 04/05/24 | 73 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 04/05/24 | 74 | Johnson, Jake E |  | 151.61
PR | 995 | 04/05/24 | 76 | Lopez, Maslin A |  | 522.29
PR | 995 | 04/05/24 | 80 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 04/05/24 | 82 | McCurry, Maxwell J |  | 229.91
PR | 995 | 04/05/24 | 82 | McCurry, Maxwell J |  | 159.94
PR | 995 | 04/05/24 | 83 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 04/05/24 | 84 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 04/05/24 | 92 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 04/05/24 | 95 | Puentez, Victor M |  | 366.52
PR | 995 | 04/05/24 | 101 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 04/05/24 | 102 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 04/05/24 | 104 | Taylor, Evan R |  | 519.79
PR | 995 | 04/05/24 | 111 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 04/05/24 | 112 | Young, Joshua S |  | 269.89
PR | 995 | 04/05/24 | 113 | Zepeda Mendoza, Cesar |  | 73.3
PR | 995 | 04/05/24 | 132 | Jimenez Alvarenga, Gerson M |  | -649.74
PR | 995 | 04/05/24 | 133 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 04/12/24 | 165 | Aquino, Juan |  | 449.82
PR | 995 | 04/12/24 | 166 | Barnhart, Joseph N |  | 113.29
PR | 995 | 04/12/24 | 166 | Barnhart, Joseph N |  | 28.32
PR | 995 | 04/12/24 | 174 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 04/12/24 | 177 | Guerrero Espinoza, Mario |  | 299.88
PR | 995 | 04/12/24 | 180 | Molina, Carlos G |  | 346.53
PR | 995 | 04/12/24 | 180 | Molina, Carlos G |  | 86.63
PR | 995 | 04/12/24 | 182 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 584.35
PR | 995 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 04/12/24 | 188 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 04/12/24 | 190 | Weeks, Gregg A |  | 799.68
PR | 995 | 04/12/24 | 192 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 04/12/24 | 192 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 04/12/24 | 196 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 04/12/24 | 201 | Carmona, Raul O |  | 882.98
PR | 995 | 04/12/24 | 211 | Diaz Morales, Guni |  | 329.87
PR | 995 | 04/12/24 | 212 | Diaz Morales, Teofilo |  | 366.52
PR | 995 | 04/12/24 | 219 | Escalante Escobar, Boanerge |  | 349.86
PR | 995 | 04/12/24 | 220 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 04/12/24 | 226 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 04/12/24 | 234 | Hubbard, Justin A |  | 153.27
PR | 995 | 04/12/24 | 234 | Hubbard, Justin A |  | 459.82
PR | 995 | 04/12/24 | 235 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 04/12/24 | 236 | Johnson, Jake E |  | 43.32
PR | 995 | 04/12/24 | 238 | Lopez, Maslin A |  | 453.57
PR | 995 | 04/12/24 | 242 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 04/12/24 | 244 | McCurry, Maxwell J |  | 159.94
PR | 995 | 04/12/24 | 244 | McCurry, Maxwell J |  | 79.97
PR | 995 | 04/12/24 | 244 | McCurry, Maxwell J |  | 79.97
PR | 995 | 04/12/24 | 245 | Melgar Moz, Brandon |  | 293.22
PR | 995 | 04/12/24 | 246 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 04/12/24 | 254 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 04/12/24 | 257 | Puentez, Victor M |  | 366.52
PR | 995 | 04/12/24 | 262 | Sontay Garcia, Juan C |  | 279.89
PR | 995 | 04/12/24 | 263 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 04/12/24 | 263 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 04/12/24 | 265 | Taylor, Evan R |  | 866.32
PR | 995 | 04/12/24 | 271 | Yohannes Jr., Samson |  | 439.82
PR | 995 | 04/12/24 | 272 | Young, Joshua S |  | 449.82
PR | 995 | 04/12/24 | 273 | Zepeda Mendoza, Cesar |  | 366.52
PR | 995 | 04/19/24 | 444 | Anderson, Richard P |  | 676.81
PR | 995 | 04/19/24 | 445 | Barnhart, Joseph N |  | 56.64
PR | 995 | 04/19/24 | 452 | Diaz Morales, Cristian A |  | 366.52
PR | 995 | 04/19/24 | 453 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 04/19/24 | 458 | Molina, Carlos G |  | 259.9
PR | 995 | 04/19/24 | 458 | Molina, Carlos G |  | 173.26
PR | 995 | 04/19/24 | 460 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 508.13
PR | 995 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 04/19/24 | 466 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 04/19/24 | 468 | Weeks, Gregg A |  | 639.74
PR | 995 | 04/19/24 | 470 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 04/19/24 | 473 | Aquino, Juan |  | 449.82
PR | 995 | 04/19/24 | 476 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 04/19/24 | 481 | Carmona, Raul O |  | 882.98
PR | 995 | 04/19/24 | 490 | Diaz Morales, Elber |  | 366.52
PR | 995 | 04/19/24 | 491 | Diaz Morales, Guni |  | 366.52
PR | 995 | 04/19/24 | 492 | Diaz Morales, Teofilo |  | 366.52
PR | 995 | 04/19/24 | 493 | Diaz Morales, Urias |  | 366.52
PR | 995 | 04/19/24 | 495 | Draves, Steven W |  | 91.63
PR | 995 | 04/19/24 | 499 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 04/19/24 | 500 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 04/19/24 | 507 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 04/19/24 | 515 | Hubbard, Justin A |  | 210.75
PR | 995 | 04/19/24 | 515 | Hubbard, Justin A |  | 306.54
PR | 995 | 04/19/24 | 516 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 04/19/24 | 517 | Johnson, Jake E |  | 64.97
PR | 995 | 04/19/24 | 519 | Lopez, Maslin A |  | 549.78
PR | 995 | 04/19/24 | 523 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 04/19/24 | 525 | McCurry, Maxwell J |  | 319.87
PR | 995 | 04/19/24 | 525 | McCurry, Maxwell J |  | 79.97
PR | 995 | 04/19/24 | 526 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 04/19/24 | 527 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 04/19/24 | 532 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 04/19/24 | 535 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 04/19/24 | 538 | Puentez, Victor M |  | 366.52
PR | 995 | 04/19/24 | 543 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 04/19/24 | 544 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 04/19/24 | 546 | Taylor, Evan R |  | 866.32
PR | 995 | 04/19/24 | 552 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 04/19/24 | 553 | Young, Joshua S |  | 449.82
PR | 995 | 04/19/24 | 554 | Zepeda Mendoza, Cesar |  | 366.52
PR | 995 | 04/26/24 | 770 | Anderson, Richard P |  | 189.51
PR | 995 | 04/26/24 | 770 | Anderson, Richard P |  | 27.07
PR | 995 | 04/26/24 | 778 | Diaz Morales, Cristian A |  | 366.52
PR | 995 | 04/26/24 | 779 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 04/26/24 | 783 | Molina, Carlos G |  | 259.9
PR | 995 | 04/26/24 | 783 | Molina, Carlos G |  | 86.63
PR | 995 | 04/26/24 | 785 | Nunez Bravo, Jose L |  | 306.54
PR | 995 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 533.54
PR | 995 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 04/26/24 | 791 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 04/26/24 | 795 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 04/26/24 | 798 | Aquino, Juan |  | 359.86
PR | 995 | 04/26/24 | 801 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 04/26/24 | 806 | Carmona, Raul O |  | 882.98
PR | 995 | 04/26/24 | 807 | Castro Hernandez, Jose A |  | 179.93
PR | 995 | 04/26/24 | 815 | Diaz Morales, Elber |  | 146.61
PR | 995 | 04/26/24 | 815 | Diaz Morales, Elber |  | 146.61
PR | 995 | 04/26/24 | 816 | Diaz Morales, Guni |  | 366.52
PR | 995 | 04/26/24 | 817 | Diaz Morales, Teofilo |  | 293.22
PR | 995 | 04/26/24 | 818 | Diaz Morales, Urias |  | 73.3
PR | 995 | 04/26/24 | 823 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 04/26/24 | 824 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 04/26/24 | 831 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 04/26/24 | 839 | Hubbard, Justin A |  | 153.27
PR | 995 | 04/26/24 | 840 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 04/26/24 | 841 | Johnson, Jake E |  | 108.29
PR | 995 | 04/26/24 | 843 | Lopez, Maslin A |  | 536.04
PR | 995 | 04/26/24 | 847 | Martinez Garcia, Cesar B |  | 324.87
PR | 995 | 04/26/24 | 849 | McCurry, Maxwell J |  | 319.87
PR | 995 | 04/26/24 | 850 | Melgar Moz, Brandon |  | 293.22
PR | 995 | 04/26/24 | 851 | Mendoza Morales, Jesus A |  | 537.91
PR | 995 | 04/26/24 | 851 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 04/26/24 | 856 | Ortiz Carmona, Juan M |  | 413.17
PR | 995 | 04/26/24 | 859 | Platero Navas, Ronald A |  | 333.2
PR | 995 | 04/26/24 | 862 | Puentez, Victor M |  | 366.52
PR | 995 | 04/26/24 | 867 | Sontay Garcia, Juan C |  | 349.86
PR | 995 | 04/26/24 | 868 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 04/26/24 | 868 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 04/26/24 | 870 | Taylor, Evan R |  | 649.74
PR | 995 | 04/26/24 | 876 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 04/26/24 | 878 | Zepeda Mendoza, Cesar |  | 348.19
PR | 995 | 05/03/24 | 3 | Anderson, Richard P |  | 974.61
PR | 995 | 05/03/24 | 4 | Barnhart, Joseph N |  | 56.64
PR | 995 | 05/03/24 | 7 | Cosentino, Brandon C |  | 159.94
PR | 995 | 05/03/24 | 11 | Diaz Morales, Cristian A |  | 366.52
PR | 995 | 05/03/24 | 12 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 05/03/24 | 17 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 508.13
PR | 995 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 05/03/24 | 21 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 05/03/24 | 23 | Weeks, Gregg A |  | 639.74
PR | 995 | 05/03/24 | 24 | Zamudio Sanchez, Jose R |  | 159.94
PR | 995 | 05/03/24 | 25 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 05/03/24 | 25 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 05/03/24 | 27 | Aquino, Juan |  | 359.86
PR | 995 | 05/03/24 | 29 | Ascencio, Jose L |  | 279.89
PR | 995 | 05/03/24 | 29 | Ascencio, Jose L |  | 279.89
PR | 995 | 05/03/24 | 30 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 05/03/24 | 33 | Boss, Benjamin T |  | 679.73
PR | 995 | 05/03/24 | 35 | Carmona, Raul O |  | 882.98
PR | 995 | 05/03/24 | 36 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 05/03/24 | 36 | Castro Hernandez, Jose A |  | 179.93
PR | 995 | 05/03/24 | 45 | Diaz Morales, Guni |  | 366.52
PR | 995 | 05/03/24 | 46 | Diaz Morales, Teofilo |  | 366.52
PR | 995 | 05/03/24 | 52 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 05/03/24 | 53 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 05/03/24 | 59 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 05/03/24 | 61 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 05/03/24 | 67 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 05/03/24 | 68 | Johnson, Jake E |  | 64.97
PR | 995 | 05/03/24 | 70 | Lopez, Maslin A |  | 549.78
PR | 995 | 05/03/24 | 74 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 05/03/24 | 77 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 05/03/24 | 78 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 05/03/24 | 78 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 05/03/24 | 83 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 05/03/24 | 87 | Portillo Soriano, Walter A |  | 349.86
PR | 995 | 05/03/24 | 88 | Puentez, Victor M |  | 366.52
PR | 995 | 05/03/24 | 91 | Romero Garza, Jesus I |  | 439.82
PR | 995 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 05/03/24 | 95 | Taylor, Evan R |  | 866.32
PR | 995 | 05/03/24 | 101 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 05/03/24 | 103 | Zepeda Mendoza, Cesar |  | 366.52
PR | 995 | 05/10/24 | 241 | Anderson, Richard P |  | 162.44
PR | 995 | 05/10/24 | 242 | Barnhart, Joseph N |  | 56.64
PR | 995 | 05/10/24 | 249 | Diaz Morales, Cristian A |  | 366.52
PR | 995 | 05/10/24 | 250 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 05/10/24 | 255 | Nunez Bravo, Jose L |  | 344.86
PR | 995 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 558.94
PR | 995 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 05/10/24 | 259 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 05/10/24 | 261 | Weeks, Gregg A |  | 799.68
PR | 995 | 05/10/24 | 262 | Zamudio Sanchez, Jose R |  | 799.68
PR | 995 | 05/10/24 | 263 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 05/10/24 | 265 | Aquino, Juan |  | 449.82
PR | 995 | 05/10/24 | 267 | Ascencio, Jose L |  | 699.72
PR | 995 | 05/10/24 | 268 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 05/10/24 | 271 | Boss, Benjamin T |  | 169.93
PR | 995 | 05/10/24 | 273 | Carmona, Raul O |  | 882.98
PR | 995 | 05/10/24 | 274 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 05/10/24 | 274 | Castro Hernandez, Jose A |  | 179.93
PR | 995 | 05/10/24 | 283 | Diaz Morales, Guni |  | 366.52
PR | 995 | 05/10/24 | 284 | Diaz Morales, Teofilo |  | 366.52
PR | 995 | 05/10/24 | 290 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 05/10/24 | 291 | Escobar Ramirez, Carlos M |  | 324.87
PR | 995 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 05/10/24 | 297 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 05/10/24 | 299 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 05/10/24 | 305 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 05/10/24 | 306 | Johnson, Jake E |  | 86.63
PR | 995 | 05/10/24 | 308 | Lopez, Maslin A |  | 426.08
PR | 995 | 05/10/24 | 312 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 05/10/24 | 315 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 05/10/24 | 316 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 05/10/24 | 321 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 05/10/24 | 325 | Portillo Soriano, Walter A |  | 583.1
PR | 995 | 05/10/24 | 326 | Puentez, Victor M |  | 366.52
PR | 995 | 05/10/24 | 329 | Romero Garza, Jesus I |  | 329.87
PR | 995 | 05/10/24 | 331 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 05/10/24 | 331 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 05/10/24 | 333 | Taylor, Evan R |  | 866.32
PR | 995 | 05/10/24 | 339 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 05/10/24 | 341 | Zepeda Mendoza, Cesar |  | 366.52
PR | 995 | 05/17/24 | 469 | Anderson, Richard P |  | 947.54
PR | 995 | 05/17/24 | 470 | Barnhart, Joseph N |  | 169.93
PR | 995 | 05/17/24 | 477 | Diaz Morales, Cristian A |  | 73.3
PR | 995 | 05/17/24 | 478 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 05/17/24 | 483 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 558.94
PR | 995 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 05/17/24 | 487 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 05/17/24 | 489 | Weeks, Gregg A |  | 639.74
PR | 995 | 05/17/24 | 490 | Zamudio Sanchez, Jose R |  | 799.68
PR | 995 | 05/17/24 | 492 | Aquino, Juan |  | 449.82
PR | 995 | 05/17/24 | 494 | Ascencio, Jose L |  | 419.83
PR | 995 | 05/17/24 | 494 | Ascencio, Jose L |  | 279.89
PR | 995 | 05/17/24 | 495 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 05/17/24 | 498 | Boss, Benjamin T |  | 509.8
PR | 995 | 05/17/24 | 500 | Carmona, Raul O |  | 882.98
PR | 995 | 05/17/24 | 501 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 05/17/24 | 510 | Diaz Morales, Guni |  | 73.3
PR | 995 | 05/17/24 | 511 | Diaz Morales, Teofilo |  | 73.3
PR | 995 | 05/17/24 | 517 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 05/17/24 | 518 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 05/17/24 | 524 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 05/17/24 | 526 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 05/17/24 | 532 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 05/17/24 | 535 | Lopez, Maslin A |  | 549.78
PR | 995 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 66.64
PR | 995 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 199.92
PR | 995 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 66.64
PR | 995 | 05/17/24 | 542 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 05/17/24 | 543 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 05/17/24 | 543 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 05/17/24 | 548 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 05/17/24 | 552 | Portillo Soriano, Walter A |  | 583.1
PR | 995 | 05/17/24 | 553 | Puentez, Victor M |  | 366.52
PR | 995 | 05/17/24 | 556 | Romero Garza, Jesus I |  | 439.82
PR | 995 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 05/17/24 | 560 | Taylor, Evan R |  | 866.32
PR | 995 | 05/17/24 | 566 | Yohannes Jr., Samson |  | 439.82
PR | 995 | 05/17/24 | 568 | Zepeda Mendoza, Cesar |  | 73.3
PR | 995 | 05/17/24 | 569 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 05/17/24 | 569 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 05/24/24 | 678 | Anderson, Richard P |  | 866.32
PR | 995 | 05/24/24 | 678 | Anderson, Richard P |  | 54.15
PR | 995 | 05/24/24 | 679 | Barnhart, Joseph N |  | 84.97
PR | 995 | 05/24/24 | 686 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 05/24/24 | 691 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 533.54
PR | 995 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 05/24/24 | 696 | Weeks, Gregg A |  | 739.7
PR | 995 | 05/24/24 | 697 | Zamudio Sanchez, Jose R |  | 559.78
PR | 995 | 05/24/24 | 699 | Aquino, Juan |  | 404.84
PR | 995 | 05/24/24 | 701 | Ascencio, Jose L |  | 559.78
PR | 995 | 05/24/24 | 701 | Ascencio, Jose L |  | 139.94
PR | 995 | 05/24/24 | 702 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 05/24/24 | 705 | Boss, Benjamin T |  | 849.66
PR | 995 | 05/24/24 | 707 | Carmona, Raul O |  | 882.98
PR | 995 | 05/24/24 | 708 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 05/24/24 | 722 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 05/24/24 | 723 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 05/24/24 | 729 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 05/24/24 | 731 | Gomez Aguirre, Exequiel |  | 239.9
PR | 995 | 05/24/24 | 737 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 05/24/24 | 738 | Johnson, Jake E |  | 86.63
PR | 995 | 05/24/24 | 739 | Lima Romero, Melvin A |  | 366.52
PR | 995 | 05/24/24 | 739 | Lima Romero, Melvin A |  | 73.3
PR | 995 | 05/24/24 | 740 | Lopez, Maslin A |  | 508.55
PR | 995 | 05/24/24 | 744 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 05/24/24 | 747 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 05/24/24 | 748 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 05/24/24 | 752 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 05/24/24 | 756 | Portillo Soriano, Walter A |  | 583.1
PR | 995 | 05/24/24 | 757 | Puentez, Victor M |  | 219.91
PR | 995 | 05/24/24 | 760 | Romero Garza, Jesus I |  | 109.96
PR | 995 | 05/24/24 | 762 | Storozhuk, Maxim A |  | 366.52
PR | 995 | 05/24/24 | 763 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 05/24/24 | 765 | Taylor, Evan R |  | 866.32
PR | 995 | 05/24/24 | 770 | Yohannes Jr., Samson |  | 515.42
PR | 995 | 05/24/24 | 772 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 05/31/24 | 792 | Anderson, Richard P |  | 785.1
PR | 995 | 05/31/24 | 792 | Anderson, Richard P |  | 27.07
PR | 995 | 05/31/24 | 793 | Barnhart, Joseph N |  | 28.32
PR | 995 | 05/31/24 | 800 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 05/31/24 | 805 | Nunez Bravo, Jose L |  | 306.54
PR | 995 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 05/31/24 | 810 | Weeks, Gregg A |  | 479.81
PR | 995 | 05/31/24 | 811 | Zamudio Sanchez, Jose R |  | 439.82
PR | 995 | 05/31/24 | 813 | Aquino, Juan |  | 359.86
PR | 995 | 05/31/24 | 815 | Ascencio, Jose L |  | 559.78
PR | 995 | 05/31/24 | 816 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 05/31/24 | 819 | Boss, Benjamin T |  | 679.73
PR | 995 | 05/31/24 | 821 | Carmona, Raul O |  | 706.38
PR | 995 | 05/31/24 | 822 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 05/31/24 | 836 | Escalante Escobar, Boanerge |  | 466.48
PR | 995 | 05/31/24 | 837 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 05/31/24 | 843 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 05/31/24 | 845 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 05/31/24 | 849 | Jimenez Alvarenga, Gerson M |  | 519.79
PR | 995 | 05/31/24 | 850 | Johnson, Jake E |  | 108.29
PR | 995 | 05/31/24 | 851 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 05/31/24 | 851 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 05/31/24 | 852 | Lopez, Maslin A |  | 439.82
PR | 995 | 05/31/24 | 856 | Martinez Garcia, Cesar B |  | 266.56
PR | 995 | 05/31/24 | 859 | Melgar Moz, Brandon |  | 293.22
PR | 995 | 05/31/24 | 860 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 05/31/24 | 864 | Ortiz Carmona, Juan M |  | 426.5
PR | 995 | 05/31/24 | 868 | Portillo Soriano, Walter A |  | 466.48
PR | 995 | 05/31/24 | 869 | Puentez, Victor M |  | 293.22
PR | 995 | 05/31/24 | 872 | Romero Garza, Jesus I |  | 109.96
PR | 995 | 05/31/24 | 874 | Storozhuk, Maxim A |  | 293.22
PR | 995 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 05/31/24 | 877 | Taylor, Evan R |  | 693.06
PR | 995 | 05/31/24 | 882 | Yohannes Jr., Samson |  | 439.82
PR | 995 | 05/31/24 | 884 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 06/07/24 | 80 | Anderson, Richard P |  | 54.15
PR | 995 | 06/07/24 | 80 | Anderson, Richard P |  | 108.29
PR | 995 | 06/07/24 | 80 | Anderson, Richard P |  | 433.16
PR | 995 | 06/07/24 | 81 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/07/24 | 81 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/07/24 | 88 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 06/07/24 | 94 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 06/07/24 | 98 | Weeks, Gregg A |  | 579.77
PR | 995 | 06/07/24 | 99 | Zamudio Sanchez, Jose R |  | 639.74
PR | 995 | 06/07/24 | 102 | Aquino, Juan |  | 449.82
PR | 995 | 06/07/24 | 104 | Ascencio, Jose L |  | 699.72
PR | 995 | 06/07/24 | 105 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 06/07/24 | 108 | Boss, Benjamin T |  | 509.8
PR | 995 | 06/07/24 | 110 | Carmona, Raul O |  | 882.98
PR | 995 | 06/07/24 | 111 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 06/07/24 | 125 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 06/07/24 | 126 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 06/07/24 | 132 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 06/07/24 | 134 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 06/07/24 | 138 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 06/07/24 | 139 | Johnson, Jake E |  | 108.29
PR | 995 | 06/07/24 | 140 | Lima Romero, Melvin A |  | 733.04
PR | 995 | 06/07/24 | 141 | Lopez, Maslin A |  | 549.78
PR | 995 | 06/07/24 | 145 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 06/07/24 | 148 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 06/07/24 | 149 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 06/07/24 | 149 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 06/07/24 | 153 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 06/07/24 | 157 | Portillo Soriano, Walter A |  | 583.1
PR | 995 | 06/07/24 | 158 | Puentez, Victor M |  | 366.52
PR | 995 | 06/07/24 | 164 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 06/07/24 | 164 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 06/07/24 | 166 | Taylor, Evan R |  | 866.32
PR | 995 | 06/07/24 | 171 | Yohannes Jr., Samson |  | 549.78
PR | 995 | 06/07/24 | 173 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 06/07/24 | 173 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 06/14/24 | 304 | Anderson, Richard P |  | 690.35
PR | 995 | 06/14/24 | 305 | Barnhart, Joseph N |  | 113.29
PR | 995 | 06/14/24 | 305 | Barnhart, Joseph N |  | 28.32
PR | 995 | 06/14/24 | 311 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 06/14/24 | 317 | Nunez Bravo, Jose L |  | 383.18
PR | 995 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 06/14/24 | 321 | Weeks, Gregg A |  | 639.74
PR | 995 | 06/14/24 | 322 | Zamudio Sanchez, Jose R |  | 379.85
PR | 995 | 06/14/24 | 324 | Aquino, Juan |  | 179.93
PR | 995 | 06/14/24 | 326 | Ascencio, Jose L |  | 699.72
PR | 995 | 06/14/24 | 327 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 06/14/24 | 330 | Boss, Benjamin T |  | 509.8
PR | 995 | 06/14/24 | 332 | Carmona, Raul O |  | 882.98
PR | 995 | 06/14/24 | 333 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 06/14/24 | 348 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 06/14/24 | 349 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 06/14/24 | 355 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 06/14/24 | 357 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 06/14/24 | 361 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 06/14/24 | 362 | Johnson, Jake E |  | 86.63
PR | 995 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/14/24 | 364 | Lopez, Maslin A |  | 412.34
PR | 995 | 06/14/24 | 368 | Martinez Garcia, Cesar B |  | 333.2
PR | 995 | 06/14/24 | 371 | Melgar Moz, Brandon |  | 366.52
PR | 995 | 06/14/24 | 372 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 06/14/24 | 372 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 06/14/24 | 376 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 06/14/24 | 380 | Portillo Soriano, Walter A |  | 583.1
PR | 995 | 06/14/24 | 381 | Puentez, Victor M |  | 366.52
PR | 995 | 06/14/24 | 387 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 06/14/24 | 389 | Taylor, Evan R |  | 346.53
PR | 995 | 06/14/24 | 394 | Yohannes Jr., Samson |  | 219.91
PR | 995 | 06/14/24 | 396 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 06/21/24 | 479 | Anderson, Richard P |  | 81.22
PR | 995 | 06/21/24 | 480 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/21/24 | 486 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 508.13
PR | 995 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 06/21/24 | 494 | Weeks, Gregg A |  | 639.74
PR | 995 | 06/21/24 | 496 | Aquino, Juan |  | 179.93
PR | 995 | 06/21/24 | 499 | Balderas Ortiz, Ricardo I |  | 714.71
PR | 995 | 06/21/24 | 502 | Boss, Benjamin T |  | 509.8
PR | 995 | 06/21/24 | 504 | Carmona, Raul O |  | 706.38
PR | 995 | 06/21/24 | 505 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 06/21/24 | 520 | Escalante Escobar, Boanerge |  | 583.1
PR | 995 | 06/21/24 | 521 | Escobar Ramirez, Carlos M |  | 333.2
PR | 995 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 06/21/24 | 527 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 06/21/24 | 532 | Jimenez Alvarenga, Gerson M |  | 519.79
PR | 995 | 06/21/24 | 533 | Johnson, Jake E |  | 43.32
PR | 995 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/21/24 | 535 | Lopez, Maslin A |  | 549.78
PR | 995 | 06/21/24 | 540 | McCabe, Thomas C |  | 586.43
PR | 995 | 06/21/24 | 541 | Melgar Moz, Brandon |  | 293.22
PR | 995 | 06/21/24 | 542 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 06/21/24 | 542 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 06/21/24 | 546 | Ortiz Carmona, Juan M |  | 426.5
PR | 995 | 06/21/24 | 549 | Portillo Soriano, Walter A |  | 466.48
PR | 995 | 06/21/24 | 552 | Romero Garza, Jesus I |  | 329.87
PR | 995 | 06/21/24 | 555 | Suniga Aviles, Kelvin A |  | 279.89
PR | 995 | 06/21/24 | 557 | Taylor, Evan R |  | 519.79
PR | 995 | 06/21/24 | 562 | Yohannes Jr., Samson |  | 219.91
PR | 995 | 06/21/24 | 564 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 06/28/24 | 686 | Anderson, Richard P |  | 257.19
PR | 995 | 06/28/24 | 687 | Barnhart, Joseph N |  | 113.29
PR | 995 | 06/28/24 | 687 | Barnhart, Joseph N |  | 84.97
PR | 995 | 06/28/24 | 693 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 736.79
PR | 995 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 06/28/24 | 701 | Weeks, Gregg A |  | 479.81
PR | 995 | 06/28/24 | 706 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 06/28/24 | 709 | Boss, Benjamin T |  | 339.86
PR | 995 | 06/28/24 | 711 | Carmona, Raul O |  | 706.38
PR | 995 | 06/28/24 | 712 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 06/28/24 | 727 | Escalante Escobar, Boanerge |  | 349.86
PR | 995 | 06/28/24 | 728 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 06/28/24 | 734 | Gochez Molina, Douglas O |  | 249.9
PR | 995 | 06/28/24 | 739 | Jimenez Alvarenga, Gerson M |  | 389.84
PR | 995 | 06/28/24 | 740 | Johnson, Jake E |  | 86.63
PR | 995 | 06/28/24 | 741 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 06/28/24 | 741 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 06/28/24 | 742 | Lopez, Maslin A |  | 329.87
PR | 995 | 06/28/24 | 749 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 06/28/24 | 749 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 06/28/24 | 753 | Ortiz Carmona, Juan M |  | 319.87
PR | 995 | 06/28/24 | 762 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 06/28/24 | 769 | Yohannes Jr., Samson |  | 219.91
PR | 995 | 06/28/24 | 771 | Zuniga Avilez, Eduar A |  | 266.56
PR | 995 | 07/05/24 | 3 | Anderson, Richard P |  | 324.87
PR | 995 | 07/05/24 | 4 | Barnhart, Joseph N |  | 28.32
PR | 995 | 07/05/24 | 10 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 07/05/24 | 15 | Rodriguez Arevalos, Christian |  | 106.21
PR | 995 | 07/05/24 | 17 | Weeks, Gregg A |  | 639.74
PR | 995 | 07/05/24 | 21 | Ascencio, Jose L |  | 139.94
PR | 995 | 07/05/24 | 22 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 07/05/24 | 25 | Boss, Benjamin T |  | 679.73
PR | 995 | 07/05/24 | 27 | Carmona, Raul O |  | 706.38
PR | 995 | 07/05/24 | 28 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 07/05/24 | 41 | Escalante Escobar, Boanerge |  | 466.48
PR | 995 | 07/05/24 | 42 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/05/24 | 42 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 07/05/24 | 48 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 07/05/24 | 52 | Jimenez Alvarenga, Gerson M |  | 519.79
PR | 995 | 07/05/24 | 53 | Johnson, Jake E |  | 64.97
PR | 995 | 07/05/24 | 54 | Lima Romero, Melvin A |  | 586.43
PR | 995 | 07/05/24 | 55 | Lopez, Maslin A |  | 219.91
PR | 995 | 07/05/24 | 61 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 07/05/24 | 61 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 07/05/24 | 65 | Ortiz Carmona, Juan M |  | 533.12
PR | 995 | 07/05/24 | 74 | Suniga Aviles, Kelvin A |  | 183.68
PR | 995 | 07/05/24 | 74 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 07/05/24 | 76 | Taylor, Evan R |  | 173.26
PR | 995 | 07/05/24 | 81 | Yohannes Jr., Samson |  | 219.91
PR | 995 | 07/05/24 | 83 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 07/05/24 | 83 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 07/12/24 | 166 | Anderson, Richard P |  | 121.83
PR | 995 | 07/12/24 | 167 | Barnhart, Joseph N |  | 70.81
PR | 995 | 07/12/24 | 173 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 177.85
PR | 995 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 07/12/24 | 179 | Weeks, Gregg A |  | 479.81
PR | 995 | 07/12/24 | 184 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 07/12/24 | 187 | Boss, Benjamin T |  | 509.8
PR | 995 | 07/12/24 | 189 | Carmona, Raul O |  | 529.79
PR | 995 | 07/12/24 | 190 | Castro Hernandez, Jose A |  | 539.78
PR | 995 | 07/12/24 | 203 | Escalante Escobar, Boanerge |  | 349.86
PR | 995 | 07/12/24 | 204 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/12/24 | 210 | Gochez Molina, Douglas O |  | 83.3
PR | 995 | 07/12/24 | 210 | Gochez Molina, Douglas O |  | 166.6
PR | 995 | 07/12/24 | 215 | Jimenez Alvarenga, Gerson M |  | 259.9
PR | 995 | 07/12/24 | 216 | Johnson, Jake E |  | 21.66
PR | 995 | 07/12/24 | 217 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 07/12/24 | 218 | Lopez, Maslin A |  | 329.87
PR | 995 | 07/12/24 | 224 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 07/12/24 | 224 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 07/12/24 | 236 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 07/12/24 | 236 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 07/12/24 | 245 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 07/19/24 | 374 | Anderson, Richard P |  | 135.36
PR | 995 | 07/19/24 | 380 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 355.69
PR | 995 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 381.1
PR | 995 | 07/19/24 | 389 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 07/19/24 | 390 | Barnhart, Joseph N |  | 28.32
PR | 995 | 07/19/24 | 390 | Barnhart, Joseph N |  | 14.16
PR | 995 | 07/19/24 | 393 | Boss, Benjamin T |  | 509.8
PR | 995 | 07/19/24 | 395 | Carmona, Raul O |  | 882.98
PR | 995 | 07/19/24 | 396 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 07/19/24 | 409 | Escalante Escobar, Boanerge |  | 466.48
PR | 995 | 07/19/24 | 410 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/19/24 | 410 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 07/19/24 | 416 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 07/19/24 | 421 | Jimenez Alvarenga, Gerson M |  | 649.74
PR | 995 | 07/19/24 | 422 | Johnson, Jake E |  | 43.32
PR | 995 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 07/19/24 | 424 | Lopez, Maslin A |  | 219.91
PR | 995 | 07/19/24 | 424 | Lopez, Maslin A |  | 219.91
PR | 995 | 07/19/24 | 430 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 07/19/24 | 430 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 07/19/24 | 443 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 07/19/24 | 443 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 07/19/24 | 449 | Weeks, Gregg A |  | 479.81
PR | 995 | 07/19/24 | 453 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 07/19/24 | 453 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 07/26/24 | 563 | Anderson, Richard P |  | 419.62
PR | 995 | 07/26/24 | 563 | Anderson, Richard P |  | 54.15
PR | 995 | 07/26/24 | 569 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 177.85
PR | 995 | 07/26/24 | 577 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 07/26/24 | 581 | Boss, Benjamin T |  | 679.73
PR | 995 | 07/26/24 | 583 | Carmona, Raul O |  | 176.6
PR | 995 | 07/26/24 | 583 | Carmona, Raul O |  | 529.79
PR | 995 | 07/26/24 | 584 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 07/26/24 | 597 | Escalante Escobar, Boanerge |  | 466.48
PR | 995 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 99.96
PR | 995 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 33.32
PR | 995 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 07/26/24 | 603 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 07/26/24 | 608 | Jimenez Alvarenga, Gerson M |  | 519.79
PR | 995 | 07/26/24 | 609 | Johnson, Jake E |  | 43.32
PR | 995 | 07/26/24 | 610 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 07/26/24 | 610 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 07/26/24 | 611 | Lopez, Maslin A |  | 439.82
PR | 995 | 07/26/24 | 617 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 07/26/24 | 617 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 07/26/24 | 630 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 07/26/24 | 630 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 07/26/24 | 636 | Weeks, Gregg A |  | 639.74
PR | 995 | 07/26/24 | 640 | Zuniga Avilez, Eduar A |  | 166.6
PR | 995 | 07/26/24 | 640 | Zuniga Avilez, Eduar A |  | 33.32
PR | 995 | 08/02/24 | 9 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 08/02/24 | 17 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 08/02/24 | 18 | Barnhart, Joseph N |  | 28.32
PR | 995 | 08/02/24 | 21 | Boss, Benjamin T |  | 679.73
PR | 995 | 08/02/24 | 23 | Carmona, Raul O |  | 882.98
PR | 995 | 08/02/24 | 24 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 08/02/24 | 37 | Escalante Escobar, Boanerge |  | 116.62
PR | 995 | 08/02/24 | 38 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 08/02/24 | 43 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 08/02/24 | 48 | Jimenez Alvarenga, Gerson M |  | 129.95
PR | 995 | 08/02/24 | 49 | Johnson, Jake E |  | 21.66
PR | 995 | 08/02/24 | 50 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/02/24 | 50 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/02/24 | 51 | Lopez, Maslin A |  | 219.91
PR | 995 | 08/02/24 | 51 | Lopez, Maslin A |  | 219.91
PR | 995 | 08/02/24 | 57 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 08/02/24 | 57 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 08/02/24 | 70 | Suniga Aviles, Kelvin A |  | 279.89
PR | 995 | 08/02/24 | 76 | Weeks, Gregg A |  | 639.74
PR | 995 | 08/02/24 | 80 | Zuniga Avilez, Eduar A |  | 166.6
PR | 995 | 08/02/24 | 80 | Zuniga Avilez, Eduar A |  | 99.96
PR | 995 | 08/02/24 | 213 | Diaz Morales, Elber |  | -146.61
PR | 995 | 08/02/24 | 214 | McCabe, Thomas C |  | -586.43
PR | 995 | 08/02/24 | 215 | Rodriguez Arevalos, Christian |  | -106.21
PR | 995 | 08/09/24 | 244 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 08/09/24 | 244 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 177.85
PR | 995 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 08/09/24 | 253 | Barnhart, Joseph N |  | 56.64
PR | 995 | 08/09/24 | 256 | Boss, Benjamin T |  | 509.8
PR | 995 | 08/09/24 | 256 | Boss, Benjamin T |  | 169.93
PR | 995 | 08/09/24 | 258 | Carmona, Raul O |  | 706.38
PR | 995 | 08/09/24 | 258 | Carmona, Raul O |  | 176.6
PR | 995 | 08/09/24 | 259 | Castro Hernandez, Jose A |  | 899.64
PR | 995 | 08/09/24 | 272 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 08/09/24 | 272 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/09/24 | 277 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 08/09/24 | 277 | Gochez Molina, Douglas O |  | 83.3
PR | 995 | 08/09/24 | 283 | Johnson, Jake E |  | 108.29
PR | 995 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 08/09/24 | 285 | Lopez, Maslin A |  | 549.78
PR | 995 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 08/09/24 | 304 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 08/09/24 | 304 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 08/09/24 | 310 | Weeks, Gregg A |  | 639.74
PR | 995 | 08/09/24 | 314 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 08/09/24 | 314 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 08/16/24 | 428 | Anderson, Richard P |  | 135.36
PR | 995 | 08/16/24 | 428 | Anderson, Richard P |  | 27.07
PR | 995 | 08/16/24 | 435 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 08/16/24 | 435 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I |  | 568.11
PR | 995 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 08/16/24 | 444 | Barnhart, Joseph N |  | 84.97
PR | 995 | 08/16/24 | 444 | Barnhart, Joseph N |  | 28.32
PR | 995 | 08/16/24 | 444 | Barnhart, Joseph N |  | 28.32
PR | 995 | 08/16/24 | 447 | Boss, Benjamin T |  | 169.93
PR | 995 | 08/16/24 | 449 | Carmona, Raul O |  | 706.38
PR | 995 | 08/16/24 | 449 | Carmona, Raul O |  | 176.6
PR | 995 | 08/16/24 | 450 | Castro Hernandez, Jose A |  | 539.78
PR | 995 | 08/16/24 | 461 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 08/16/24 | 461 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/16/24 | 466 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 08/16/24 | 472 | Johnson, Jake E |  | 86.63
PR | 995 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/16/24 | 474 | Lopez, Maslin A |  | 329.87
PR | 995 | 08/16/24 | 474 | Lopez, Maslin A |  | 109.96
PR | 995 | 08/16/24 | 478 | McCabe, Thomas C |  | 293.22
PR | 995 | 08/16/24 | 480 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 08/16/24 | 480 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 08/16/24 | 492 | Silva Morales, Jair J |  | 226.58
PR | 995 | 08/16/24 | 493 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 08/16/24 | 499 | Weeks, Gregg A |  | 799.68
PR | 995 | 08/16/24 | 501 | Yohannes Jr., Samson |  | 219.91
PR | 995 | 08/16/24 | 503 | Zuniga Avilez, Eduar A |  | 333.2
PR | 995 | 08/23/24 | 690 | Anderson, Richard P |  | 54.15
PR | 995 | 08/23/24 | 690 | Anderson, Richard P |  | 284.26
PR | 995 | 08/23/24 | 697 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 482.72
PR | 995 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 08/23/24 | 705 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 08/23/24 | 709 | Boss, Benjamin T |  | 169.93
PR | 995 | 08/23/24 | 709 | Boss, Benjamin T |  | 169.93
PR | 995 | 08/23/24 | 711 | Carmona, Raul O |  | 353.19
PR | 995 | 08/23/24 | 711 | Carmona, Raul O |  | 176.6
PR | 995 | 08/23/24 | 723 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 08/23/24 | 723 | Escobar Ramirez, Carlos M |  | 199.92
PR | 995 | 08/23/24 | 728 | Gochez Molina, Douglas O |  | 416.5
PR | 995 | 08/23/24 | 734 | Johnson, Jake E |  | 129.95
PR | 995 | 08/23/24 | 735 | Lima Romero, Melvin A |  | 733.04
PR | 995 | 08/23/24 | 736 | Lopez, Maslin A |  | 219.91
PR | 995 | 08/23/24 | 736 | Lopez, Maslin A |  | 219.91
PR | 995 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 08/23/24 | 755 | Suniga Aviles, Kelvin A |  | 139.94
PR | 995 | 08/23/24 | 755 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 08/23/24 | 761 | Weeks, Gregg A |  | 159.94
PR | 995 | 08/23/24 | 761 | Weeks, Gregg A |  | 319.87
PR | 995 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 08/30/24 | 833 | Anderson, Richard P |  | 351.94
PR | 995 | 08/30/24 | 833 | Anderson, Richard P |  | 108.29
PR | 995 | 08/30/24 | 833 | Anderson, Richard P |  | 27.07
PR | 995 | 08/30/24 | 840 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 355.69
PR | 995 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 08/30/24 | 848 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 08/30/24 | 849 | Barnhart, Joseph N |  | 84.97
PR | 995 | 08/30/24 | 852 | Boss, Benjamin T |  | 84.97
PR | 995 | 08/30/24 | 852 | Boss, Benjamin T |  | 339.86
PR | 995 | 08/30/24 | 854 | Carmona, Raul O |  | 529.79
PR | 995 | 08/30/24 | 854 | Carmona, Raul O |  | 176.6
PR | 995 | 08/30/24 | 865 | Escobar Ramirez, Carlos M |  | 199.92
PR | 995 | 08/30/24 | 865 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 08/30/24 | 870 | Gochez Molina, Douglas O |  | 333.2
PR | 995 | 08/30/24 | 876 | Johnson, Jake E |  | 64.97
PR | 995 | 08/30/24 | 877 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/30/24 | 877 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 08/30/24 | 878 | Lopez, Maslin A |  | 329.87
PR | 995 | 08/30/24 | 884 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 08/30/24 | 897 | Suniga Aviles, Kelvin A |  | 279.89
PR | 995 | 08/30/24 | 903 | Weeks, Gregg A |  | 479.81
PR | 995 | 08/30/24 | 907 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 08/30/24 | 907 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/06/24 | 9 | Anderson, Richard P |  | 54.15
PR | 995 | 09/06/24 | 9 | Anderson, Richard P |  | 27.07
PR | 995 | 09/06/24 | 9 | Anderson, Richard P |  | 54.15
PR | 995 | 09/06/24 | 16 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 09/06/24 | 25 | Barnhart, Joseph N |  | 28.32
PR | 995 | 09/06/24 | 25 | Barnhart, Joseph N |  | 113.29
PR | 995 | 09/06/24 | 28 | Boss, Benjamin T |  | 169.93
PR | 995 | 09/06/24 | 28 | Boss, Benjamin T |  | 339.86
PR | 995 | 09/06/24 | 30 | Carmona, Raul O |  | 353.19
PR | 995 | 09/06/24 | 30 | Carmona, Raul O |  | 176.6
PR | 995 | 09/06/24 | 31 | Castro Hernandez, Jose A |  | 719.71
PR | 995 | 09/06/24 | 41 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 09/06/24 | 41 | Escobar Ramirez, Carlos M |  | 133.28
PR | 995 | 09/06/24 | 47 | Gochez Molina, Douglas O |  | 249.9
PR | 995 | 09/06/24 | 53 | Johnson, Jake E |  | 86.63
PR | 995 | 09/06/24 | 54 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 09/06/24 | 55 | Lopez, Maslin A |  | 329.87
PR | 995 | 09/06/24 | 61 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 09/06/24 | 61 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 09/06/24 | 74 | Suniga Aviles, Kelvin A |  | 209.92
PR | 995 | 09/06/24 | 80 | Weeks, Gregg A |  | 479.81
PR | 995 | 09/06/24 | 84 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/06/24 | 84 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 09/13/24 | 217 | Anderson, Richard P |  | 121.83
PR | 995 | 09/13/24 | 217 | Anderson, Richard P |  | 27.07
PR | 995 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 09/13/24 | 224 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 09/13/24 | 232 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 84.97
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 28.32
PR | 995 | 09/13/24 | 236 | Boss, Benjamin T |  | 849.66
PR | 995 | 09/13/24 | 238 | Carmona, Raul O |  | 706.38
PR | 995 | 09/13/24 | 239 | Castro Hernandez, Jose A |  | 539.78
PR | 995 | 09/13/24 | 249 | Escobar Ramirez, Carlos M |  | 199.92
PR | 995 | 09/13/24 | 249 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 09/13/24 | 255 | Gochez Molina, Douglas O |  | 124.95
PR | 995 | 09/13/24 | 255 | Gochez Molina, Douglas O |  | 41.65
PR | 995 | 09/13/24 | 261 | Johnson, Jake E |  | 21.66
PR | 995 | 09/13/24 | 262 | Lima Romero, Melvin A |  | 586.43
PR | 995 | 09/13/24 | 263 | Lopez, Maslin A |  | 536.04
PR | 995 | 09/13/24 | 268 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 52.48
PR | 995 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 87.47
PR | 995 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 87.47
PR | 995 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 17.49
PR | 995 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 34.99
PR | 995 | 09/13/24 | 287 | Weeks, Gregg A |  | 479.81
PR | 995 | 09/13/24 | 287 | Weeks, Gregg A |  | 159.94
PR | 995 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 33.32
PR | 995 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 33.32
PR | 995 | 09/20/24 | 389 | Anderson, Richard P |  | 135.36
PR | 995 | 09/20/24 | 390 | Barnhart, Thomas L |  | 116.41
PR | 995 | 09/20/24 | 393 | Cruz Reyes, Jose |  | 546.45
PR | 995 | 09/20/24 | 396 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 09/20/24 | 404 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 09/20/24 | 405 | Barnhart, Joseph N |  | 28.32
PR | 995 | 09/20/24 | 405 | Barnhart, Joseph N |  | 28.32
PR | 995 | 09/20/24 | 405 | Barnhart, Joseph N |  | 141.61
PR | 995 | 09/20/24 | 408 | Boss, Benjamin T |  | 849.66
PR | 995 | 09/20/24 | 410 | Carmona, Raul O |  | 353.19
PR | 995 | 09/20/24 | 410 | Carmona, Raul O |  | 353.19
PR | 995 | 09/20/24 | 411 | Castro Hernandez, Jose A |  | 179.93
PR | 995 | 09/20/24 | 421 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 09/20/24 | 421 | Escobar Ramirez, Carlos M |  | 199.92
PR | 995 | 09/20/24 | 426 | Gochez Molina, Douglas O |  | 249.9
PR | 995 | 09/20/24 | 432 | Johnson, Jake E |  | 21.66
PR | 995 | 09/20/24 | 433 | Lima Romero, Melvin A |  | 366.52
PR | 995 | 09/20/24 | 433 | Lima Romero, Melvin A |  | 219.91
PR | 995 | 09/20/24 | 434 | Lopez, Maslin A |  | 109.96
PR | 995 | 09/20/24 | 434 | Lopez, Maslin A |  | 329.87
PR | 995 | 09/20/24 | 439 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 104.96
PR | 995 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 104.96
PR | 995 | 09/20/24 | 458 | Weeks, Gregg A |  | 639.74
PR | 995 | 09/20/24 | 458 | Weeks, Gregg A |  | 159.94
PR | 995 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/27/24 | 525 | Anderson, Richard P |  | 27.07
PR | 995 | 09/27/24 | 525 | Anderson, Richard P |  | 27.07
PR | 995 | 09/27/24 | 525 | Anderson, Richard P |  | 54.15
PR | 995 | 09/27/24 | 529 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 09/27/24 | 532 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 177.85
PR | 995 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 25.41
PR | 995 | 09/27/24 | 541 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 09/27/24 | 542 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/27/24 | 544 | Boss, Benjamin T |  | 849.66
PR | 995 | 09/27/24 | 546 | Carmona, Raul O |  | 353.19
PR | 995 | 09/27/24 | 546 | Carmona, Raul O |  | 353.19
PR | 995 | 09/27/24 | 557 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 09/27/24 | 562 | Gochez Molina, Douglas O |  | 83.3
PR | 995 | 09/27/24 | 568 | Johnson, Jake E |  | 21.66
PR | 995 | 09/27/24 | 569 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 09/27/24 | 569 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 09/27/24 | 570 | Lopez, Maslin A |  | 109.96
PR | 995 | 09/27/24 | 570 | Lopez, Maslin A |  | 329.87
PR | 995 | 09/27/24 | 575 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 09/27/24 | 575 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 09/27/24 | 588 | Suniga Aviles, Kelvin A |  | 174.93
PR | 995 | 09/27/24 | 588 | Suniga Aviles, Kelvin A |  | 104.96
PR | 995 | 09/27/24 | 594 | Weeks, Gregg A |  | 479.81
PR | 995 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 133.28
PR | 995 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 10/04/24 | 9 | Anderson, Richard P |  | 27.07
PR | 995 | 10/04/24 | 9 | Anderson, Richard P |  | 54.15
PR | 995 | 10/04/24 | 9 | Anderson, Richard P |  | 54.15
PR | 995 | 10/04/24 | 13 | Cruz Reyes, Jose |  | 546.45
PR | 995 | 10/04/24 | 16 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/04/24 | 25 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 10/04/24 | 26 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/04/24 | 28 | Boss, Benjamin T |  | 849.66
PR | 995 | 10/04/24 | 30 | Carmona, Raul O |  | 706.38
PR | 995 | 10/04/24 | 30 | Carmona, Raul O |  | 176.6
PR | 995 | 10/04/24 | 41 | Escobar Ramirez, Carlos M |  | 266.56
PR | 995 | 10/04/24 | 42 | Games, Jordan M |  | 706.38
PR | 995 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 10/04/24 | 52 | Johnson, Jake E |  | 43.32
PR | 995 | 10/04/24 | 53 | Lima Romero, Melvin A |  | 733.04
PR | 995 | 10/04/24 | 54 | Lopez, Maslin A |  | 109.96
PR | 995 | 10/04/24 | 54 | Lopez, Maslin A |  | 329.87
PR | 995 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 68.31
PR | 995 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 68.31
PR | 995 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 10/04/24 | 72 | Suniga Aviles, Kelvin A |  | 349.86
PR | 995 | 10/04/24 | 78 | Weeks, Gregg A |  | 799.68
PR | 995 | 10/04/24 | 79 | Wilson, Garret A |  | 67.47
PR | 995 | 10/04/24 | 79 | Wilson, Garret A |  | 157.44
PR | 995 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 199.92
PR | 995 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 10/11/24 | 216 | Anderson, Richard P |  | 81.22
PR | 995 | 10/11/24 | 217 | Barnhart, Thomas L |  | 340.28
PR | 995 | 10/11/24 | 220 | Cruz Reyes, Jose |  | 546.45
PR | 995 | 10/11/24 | 223 | Galdamez, Dagoberto A |  | 559.78
PR | 995 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 355.69
PR | 995 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/11/24 | 235 | Boss, Benjamin T |  | 849.66
PR | 995 | 10/11/24 | 237 | Carmona, Raul O |  | 529.79
PR | 995 | 10/11/24 | 237 | Carmona, Raul O |  | 176.6
PR | 995 | 10/11/24 | 237 | Carmona, Raul O |  | 176.6
PR | 995 | 10/11/24 | 248 | Escobar Ramirez, Carlos M |  | 66.64
PR | 995 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/11/24 | 259 | Johnson, Jake E |  | 43.32
PR | 995 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 10/11/24 | 261 | Lopez, Maslin A |  | 329.87
PR | 995 | 10/11/24 | 266 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 10/11/24 | 266 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 10/11/24 | 284 | Weeks, Gregg A |  | 479.81
PR | 995 | 10/18/24 | 414 | Gochez Molina, Douglas O |  | -83.3
PR | 995 | 10/18/24 | 414 | Gochez Molina, Douglas O |  | -249.9
PR | 995 | 10/18/24 | 415 | McCabe, Thomas C |  | -293.22
PR | 995 | 10/18/24 | 418 | Wilson, Garret A |  | -67.47
PR | 995 | 10/18/24 | 418 | Wilson, Garret A |  | -157.44
PR | 995 | 10/18/24 | 428 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 10/18/24 | 428 | Lima Romero, Melvin A |  | -293.22
PR | 995 | 10/18/24 | 429 | Anderson, Richard P |  | 81.22
PR | 995 | 10/18/24 | 429 | Anderson, Richard P |  | 54.15
PR | 995 | 10/18/24 | 433 | Cruz Reyes, Jose |  | 683.06
PR | 995 | 10/18/24 | 436 | Galdamez, Dagoberto A |  | 699.72
PR | 995 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 508.13
PR | 995 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 25.41
PR | 995 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/18/24 | 445 | Balderas Ortiz, Ricardo I |  | 733.04
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/18/24 | 448 | Boss, Benjamin T |  | 84.97
PR | 995 | 10/18/24 | 448 | Boss, Benjamin T |  | -84.97
PR | 995 | 10/18/24 | 448 | Boss, Benjamin T |  | 339.86
PR | 995 | 10/18/24 | 450 | Carmona, Raul O |  | 618.09
PR | 995 | 10/18/24 | 450 | Carmona, Raul O |  | 88.3
PR | 995 | 10/18/24 | 450 | Carmona, Raul O |  | 176.6
PR | 995 | 10/18/24 | 460 | Eliassen, Cory H |  | 538.12
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/18/24 | 471 | Johnson, Jake E |  | 21.66
PR | 995 | 10/18/24 | 472 | Lopez, Maslin A |  | 439.82
PR | 995 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 68.31
PR | 995 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 68.31
PR | 995 | 10/18/24 | 496 | Weeks, Gregg A |  | 799.68
PR | 995 | 10/25/24 | 577 | Anderson, Richard P |  | 487.31
PR | 995 | 10/25/24 | 577 | Anderson, Richard P |  | 27.07
PR | 995 | 10/25/24 | 581 | Cruz Reyes, Jose |  | 648.91
PR | 995 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 472.31
PR | 995 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 52.48
PR | 995 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 34.99
PR | 995 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 635.16
PR | 995 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 228.66
PR | 995 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 10/25/24 | 594 | Barnhart, Joseph N |  | 70.81
PR | 995 | 10/25/24 | 594 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/25/24 | 594 | Barnhart, Joseph N |  | 14.16
PR | 995 | 10/25/24 | 597 | Carmona, Raul O |  | 441.49
PR | 995 | 10/25/24 | 597 | Carmona, Raul O |  | 441.49
PR | 995 | 10/25/24 | 607 | Eliassen, Cory H |  | 379.85
PR | 995 | 10/25/24 | 608 | Games, Jordan M |  | 706.38
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 10/25/24 | 618 | Johnson, Jake E |  | 21.66
PR | 995 | 10/25/24 | 619 | Lopez, Maslin A |  | 219.91
PR | 995 | 10/25/24 | 619 | Lopez, Maslin A |  | 109.96
PR | 995 | 10/25/24 | 619 | Lopez, Maslin A |  | 109.96
PR | 995 | 10/25/24 | 624 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 10/25/24 | 624 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 10/25/24 | 643 | Weeks, Gregg A |  | 639.74
PR | 995 | 11/01/24 | 6 | Anderson, Richard P |  | 433.16
PR | 995 | 11/01/24 | 10 | Cruz Reyes, Jose |  | 273.22
PR | 995 | 11/01/24 | 13 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/01/24 | 13 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/01/24 | 16 | Paco Leyva, Orlando |  | 431.91
PR | 995 | 11/01/24 | 16 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/01/24 | 23 | Barnhart, Joseph N |  | 56.64
PR | 995 | 11/01/24 | 26 | Carmona, Raul O |  | 353.19
PR | 995 | 11/01/24 | 26 | Carmona, Raul O |  | 529.79
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/01/24 | 47 | Johnson, Jake E |  | 43.32
PR | 995 | 11/01/24 | 48 | Lopez, Maslin A |  | 109.96
PR | 995 | 11/01/24 | 48 | Lopez, Maslin A |  | 329.87
PR | 995 | 11/01/24 | 53 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 11/01/24 | 53 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 11/08/24 | 126 | Anderson, Richard P |  | 81.22
PR | 995 | 11/08/24 | 126 | Anderson, Richard P |  | 54.15
PR | 995 | 11/08/24 | 128 | Castro, Marcus J |  | 66.64
PR | 995 | 11/08/24 | 130 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 11/08/24 | 133 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/08/24 | 133 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 177.85
PR | 995 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 152.44
PR | 995 | 11/08/24 | 139 | Aquino, Juan |  | 89.96
PR | 995 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/08/24 | 143 | Barnhart, Joseph N |  | 56.64
PR | 995 | 11/08/24 | 143 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/08/24 | 146 | Carmona, Raul O |  | 353.19
PR | 995 | 11/08/24 | 146 | Carmona, Raul O |  | 353.19
PR | 995 | 11/08/24 | 146 | Carmona, Raul O |  | 176.6
PR | 995 | 11/08/24 | 156 | Eliassen, Cory H |  | 379.85
PR | 995 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/08/24 | 167 | Johnson, Jake E |  | 86.63
PR | 995 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 11/08/24 | 169 | Lopez, Maslin A |  | 329.87
PR | 995 | 11/08/24 | 174 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 11/08/24 | 187 | Suniga Aviles, Kelvin A |  | 69.97
PR | 995 | 11/08/24 | 197 | Zuniga Avilez, Eduar A |  | 66.64
PR | 995 | 11/15/24 | 346 | Anderson, Richard P |  | 81.22
PR | 995 | 11/15/24 | 350 | Cruz Reyes, Jose |  | 683.06
PR | 995 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 279.47
PR | 995 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 76.22
PR | 995 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 25.41
PR | 995 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/15/24 | 366 | Carmona, Raul O |  | 353.19
PR | 995 | 11/15/24 | 366 | Carmona, Raul O |  | 176.6
PR | 995 | 11/15/24 | 366 | Carmona, Raul O |  | 353.19
PR | 995 | 11/15/24 | 376 | Eliassen, Cory H |  | 205.75
PR | 995 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 11/15/24 | 387 | Johnson, Jake E |  | 64.97
PR | 995 | 11/15/24 | 388 | Lima Romero, Melvin A |  | 439.82
PR | 995 | 11/15/24 | 388 | Lima Romero, Melvin A |  | 293.22
PR | 995 | 11/15/24 | 389 | Lopez, Maslin A |  | 109.96
PR | 995 | 11/15/24 | 389 | Lopez, Maslin A |  | 219.91
PR | 995 | 11/15/24 | 389 | Lopez, Maslin A |  | 109.96
PR | 995 | 11/15/24 | 394 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 11/22/24 | 501 | Anderson, Richard P |  | 135.36
PR | 995 | 11/22/24 | 505 | Cruz Reyes, Jose |  | 546.45
PR | 995 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 330.28
PR | 995 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/22/24 | 518 | Barnhart, Joseph N |  | 56.64
PR | 995 | 11/22/24 | 518 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/22/24 | 521 | Carmona, Raul O |  | 353.19
PR | 995 | 11/22/24 | 521 | Carmona, Raul O |  | 353.19
PR | 995 | 11/22/24 | 531 | Eliassen, Cory H |  | 379.85
PR | 995 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 146.61
PR | 995 | 11/22/24 | 544 | Lopez, Maslin A |  | 219.91
PR | 995 | 11/22/24 | 544 | Lopez, Maslin A |  | 109.96
PR | 995 | 11/22/24 | 549 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 11/22/24 | 565 | Trower-Kelly, Fidel D |  | 516.46
PR | 995 | 11/29/24 | 648 | Johnson, Jake E |  | 21.66
PR | 995 | 11/29/24 | 649 | Anderson, Richard P |  | 162.44
PR | 995 | 11/29/24 | 649 | Anderson, Richard P |  | 81.22
PR | 995 | 11/29/24 | 649 | Anderson, Richard P |  | 40.61
PR | 995 | 11/29/24 | 653 | Cruz Reyes, Jose |  | 683.06
PR | 995 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 11/29/24 | 663 | Araque, Mario W |  | 366.52
PR | 995 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 11/29/24 | 666 | Barnhart, Joseph N |  | 56.64
PR | 995 | 11/29/24 | 669 | Carmona, Raul O |  | 176.6
PR | 995 | 11/29/24 | 669 | Carmona, Raul O |  | 176.6
PR | 995 | 11/29/24 | 669 | Carmona, Raul O |  | 176.6
PR | 995 | 11/29/24 | 669 | Carmona, Raul O |  | 176.6
PR | 995 | 11/29/24 | 679 | Eliassen, Cory H |  | 332.37
PR | 995 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/29/24 | 690 | Johnson, Jake E |  | 43.32
PR | 995 | 11/29/24 | 691 | Lima Romero, Melvin A |  | 73.3
PR | 995 | 11/29/24 | 691 | Lima Romero, Melvin A |  | 73.3
PR | 995 | 11/29/24 | 697 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 11/29/24 | 713 | Trower-Kelly, Fidel D |  | 206.58
PR | 995 | 12/06/24 | 51 | Anderson, Richard P |  | 54.15
PR | 995 | 12/06/24 | 55 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 69.97
PR | 995 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 69.97
PR | 995 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 12/06/24 | 65 | Araque, Mario W |  | 219.91
PR | 995 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 73.3
PR | 995 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 73.3
PR | 995 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 12/06/24 | 71 | Carmona, Raul O |  | 264.89
PR | 995 | 12/06/24 | 71 | Carmona, Raul O |  | 176.6
PR | 995 | 12/06/24 | 71 | Carmona, Raul O |  | 88.3
PR | 995 | 12/06/24 | 73 | Chastain, Aaron R |  | 26.24
PR | 995 | 12/06/24 | 81 | Eliassen, Cory H |  | 379.85
PR | 995 | 12/06/24 | 82 | Games, Jordan M |  | 66.22
PR | 995 | 12/06/24 | 92 | Johnson, Jake E |  | 21.66
PR | 995 | 12/06/24 | 99 | Mendoza Morales, Jesus A |  | 409.84
PR | 995 | 12/06/24 | 114 | Trower-Kelly, Fidel D |  | 206.58
PR | 995 | 12/13/24 | 235 | Anderson, Richard P |  | 54.15
PR | 995 | 12/13/24 | 235 | Anderson, Richard P |  | 81.22
PR | 995 | 12/13/24 | 235 | Anderson, Richard P |  | 54.15
PR | 995 | 12/13/24 | 236 | Barnhart, Thomas L |  | 286.55
PR | 995 | 12/13/24 | 238 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 254.07
PR | 995 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 12/13/24 | 247 | Araque, Mario W |  | 219.91
PR | 995 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 12/13/24 | 250 | Barnhart, Joseph N |  | 56.64
PR | 995 | 12/13/24 | 253 | Carmona, Raul O |  | 353.19
PR | 995 | 12/13/24 | 253 | Carmona, Raul O |  | 176.6
PR | 995 | 12/13/24 | 253 | Carmona, Raul O |  | 176.6
PR | 995 | 12/13/24 | 255 | Chastain, Aaron R |  | 113.7
PR | 995 | 12/13/24 | 263 | Eliassen, Cory H |  | 348.19
PR | 995 | 12/13/24 | 264 | Games, Jordan M |  | 331.12
PR | 995 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/13/24 | 274 | Johnson, Jake E |  | 21.66
PR | 995 | 12/13/24 | 276 | Lopez, Maslin A |  | 109.96
PR | 995 | 12/13/24 | 281 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 12/13/24 | 296 | Trower-Kelly, Fidel D |  | 309.88
PR | 995 | 12/20/24 | 422 | Anderson, Richard P |  | 54.15
PR | 995 | 12/20/24 | 422 | Anderson, Richard P |  | 27.07
PR | 995 | 12/20/24 | 425 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 12/20/24 | 428 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 12/20/24 | 428 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 12/20/24 | 434 | Araque, Mario W |  | 219.91
PR | 995 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 28.32
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 28.32
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 84.97
PR | 995 | 12/20/24 | 440 | Carmona, Raul O |  | 529.79
PR | 995 | 12/20/24 | 440 | Carmona, Raul O |  | 176.6
PR | 995 | 12/20/24 | 442 | Chastain, Aaron R |  | 104.96
PR | 995 | 12/20/24 | 449 | Eliassen, Cory H |  | 379.85
PR | 995 | 12/20/24 | 450 | Games, Jordan M |  | 375.27
PR | 995 | 12/20/24 | 460 | Johnson, Jake E |  | 64.97
PR | 995 | 12/20/24 | 467 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 12/20/24 | 483 | Trower-Kelly, Fidel D |  | 309.88
PR | 995 | 12/27/24 | 539 | Anderson, Richard P |  | 27.07
PR | 995 | 12/27/24 | 543 | Cruz Reyes, Jose |  | 273.22
PR | 995 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 69.97
PR | 995 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 12/27/24 | 548 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 12/27/24 | 548 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 12/27/24 | 553 | Araque, Mario W |  | 146.61
PR | 995 | 12/27/24 | 555 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 12/27/24 | 559 | Carmona, Raul O |  | 176.6
PR | 995 | 12/27/24 | 559 | Carmona, Raul O |  | 176.6
PR | 995 | 12/27/24 | 559 | Carmona, Raul O |  | 176.6
PR | 995 | 12/27/24 | 561 | Chastain, Aaron R |  | 139.94
PR | 995 | 12/27/24 | 568 | Eliassen, Cory H |  | 229.49
PR | 995 | 12/27/24 | 569 | Games, Jordan M |  | 353.19
PR | 995 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/27/24 | 579 | Johnson, Jake E |  | 21.66
PR | 995 | 12/27/24 | 599 | Trower-Kelly, Fidel D |  | 206.58
PR | 995 | 01/03/25 | 16 | Cruz Reyes, Jose |  | 273.22
PR | 995 | 01/03/25 | 19 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 01/03/25 | 25 | Araque, Mario W |  | 146.61
PR | 995 | 01/03/25 | 27 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 01/03/25 | 32 | Chastain, Aaron R |  | 139.94
PR | 995 | 01/03/25 | 37 | Draves, Steven W |  | 91.63
PR | 995 | 01/03/25 | 39 | Eliassen, Cory H |  | 126.62
PR | 995 | 01/03/25 | 40 | Games, Jordan M |  | 474.6
PR | 995 | 01/03/25 | 49 | Johnson, Jake E |  | 21.66
PR | 995 | 01/03/25 | 67 | Trower-Kelly, Fidel D |  | 206.58
PR | 995 | 01/10/25 | 174 | Anderson, Richard P |  | 13.54
PR | 995 | 01/10/25 | 174 | Anderson, Richard P |  | 27.07
PR | 995 | 01/10/25 | 174 | Anderson, Richard P |  | 175.97
PR | 995 | 01/10/25 | 175 | Barnhart, Thomas L |  | 143.28
PR | 995 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 209.92
PR | 995 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 01/10/25 | 189 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 01/10/25 | 190 | Barnhart, Joseph N |  | 84.97
PR | 995 | 01/10/25 | 190 | Barnhart, Joseph N |  | 169.93
PR | 995 | 01/10/25 | 190 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/10/25 | 194 | Chastain, Aaron R |  | 153.27
PR | 995 | 01/10/25 | 203 | Games, Jordan M |  | 684.31
PR | 995 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 01/10/25 | 212 | Johnson, Jake E |  | 21.66
PR | 995 | 01/17/25 | 339 | Anderson, Richard P |  | 54.15
PR | 995 | 01/17/25 | 340 | Barnhart, Thomas L |  | 286.55
PR | 995 | 01/17/25 | 342 | Cosentino, Brandon C |  | 319.87
PR | 995 | 01/17/25 | 346 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 01/17/25 | 346 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 146.61
PR | 995 | 01/17/25 | 354 | Barnhart, Joseph N |  | 113.29
PR | 995 | 01/17/25 | 354 | Barnhart, Joseph N |  | 28.32
PR | 995 | 01/17/25 | 354 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/17/25 | 358 | Chastain, Aaron R |  | 383.18
PR | 995 | 01/17/25 | 366 | Games, Jordan M |  | 794.68
PR | 995 | 01/17/25 | 375 | Johnson, Jake E |  | 21.66
PR | 995 | 01/17/25 | 381 | Mendoza Morales, Jesus A |  | 136.61
PR | 995 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 457.32
PR | 995 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 50.81
PR | 995 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/17/25 | 395 | Trower-Kelly, Fidel D |  | 103.29
PR | 995 | 01/24/25 | 506 | Barnhart, Thomas L |  | 143.28
PR | 995 | 01/24/25 | 508 | Cosentino, Brandon C |  | 399.84
PR | 995 | 01/24/25 | 512 | Galdamez, Dagoberto A |  | 419.83
PR | 995 | 01/24/25 | 512 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 28.32
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/24/25 | 524 | Chastain, Aaron R |  | 383.18
PR | 995 | 01/24/25 | 533 | Games, Jordan M |  | 882.98
PR | 995 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 127.03
PR | 995 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/24/25 | 562 | Trower-Kelly, Fidel D |  | 413.17
PR | 995 | 01/24/25 | 611 | Johnson, Jake E |  | 21.66
PR | 995 | 01/31/25 | 700 | Cosentino, Brandon C |  | 399.84
PR | 995 | 01/31/25 | 704 | Galdamez, Dagoberto A |  | 279.89
PR | 995 | 01/31/25 | 704 | Galdamez, Dagoberto A |  | 139.94
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 28.32
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 84.97
PR | 995 | 01/31/25 | 716 | Chastain, Aaron R |  | 306.54
PR | 995 | 01/31/25 | 725 | Games, Jordan M |  | 838.83
PR | 995 | 01/31/25 | 734 | Johnson, Jake E |  | 21.66
PR | 995 | 01/31/25 | 736 | Lopez, Maslin A |  | 329.87
PR | 995 | 01/31/25 | 736 | Lopez, Maslin A |  | 54.98
PR | 995 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 203.25
PR | 995 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 01/31/25 | 753 | Trower-Kelly, Fidel D |  | 516.46
PR | 995 | 02/07/25 | 31 | Cosentino, Brandon C |  | 239.9
PR | 995 | 02/07/25 | 42 | Barnhart, Joseph N |  | 28.32
PR | 995 | 02/07/25 | 42 | Barnhart, Joseph N |  | 28.32
PR | 995 | 02/07/25 | 42 | Barnhart, Joseph N |  | 28.32
PR | 995 | 02/07/25 | 42 | Barnhart, Joseph N |  | 56.64
PR | 995 | 02/07/25 | 46 | Chastain, Aaron R |  | 344.86
PR | 995 | 02/07/25 | 55 | Games, Jordan M |  | 794.68
PR | 995 | 02/07/25 | 64 | Johnson, Jake E |  | 86.63
PR | 995 | 02/07/25 | 66 | Lopez, Maslin A |  | 164.93
PR | 995 | 02/07/25 | 66 | Lopez, Maslin A |  | 164.93
PR | 995 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 406.5
PR | 995 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 304.88
PR | 995 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 101.63
PR | 995 | 02/07/25 | 84 | Trower-Kelly, Fidel D |  | 503.55
PR | 995 | 02/14/25 | 194 | Anderson, Richard P |  | 64.09
PR | 995 | 02/14/25 | 194 | Anderson, Richard P |  | 32.05
PR | 995 | 02/14/25 | 197 | Cosentino, Brandon C |  | 378.62
PR | 995 | 02/14/25 | 208 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/14/25 | 208 | Barnhart, Joseph N |  | 100.57
PR | 995 | 02/14/25 | 212 | Chastain, Aaron R |  | 453.56
PR | 995 | 02/14/25 | 221 | Games, Jordan M |  | 836.13
PR | 995 | 02/14/25 | 230 | Johnson, Jake E |  | 64.97
PR | 995 | 02/14/25 | 232 | Lopez, Maslin A |  | 260.3
PR | 995 | 02/14/25 | 232 | Lopez, Maslin A |  | 195.23
PR | 995 | 02/14/25 | 232 | Lopez, Maslin A |  | 195.23
PR | 995 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 601.46
PR | 995 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 421.02
PR | 995 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 60.15
PR | 995 | 02/14/25 | 242 | Reed, Reuben H |  | 489.06
PR | 995 | 02/14/25 | 250 | Trower-Kelly, Fidel D |  | 366.79
PR | 995 | 02/21/25 | 311 | Anderson, Richard P |  | 32.05
PR | 995 | 02/21/25 | 314 | Cosentino, Brandon C |  | 473.28
PR | 995 | 02/21/25 | 326 | Barnhart, Joseph N |  | 50.29
PR | 995 | 02/21/25 | 326 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/21/25 | 326 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/21/25 | 330 | Chastain, Aaron R |  | 453.56
PR | 995 | 02/21/25 | 338 | Eliassen, Cory H |  | 599.49
PR | 995 | 02/21/25 | 339 | Games, Jordan M |  | 1045.16
PR | 995 | 02/21/25 | 348 | Johnson, Jake E |  | 86.63
PR | 995 | 02/21/25 | 350 | Lopez, Maslin A |  | 260.3
PR | 995 | 02/21/25 | 350 | Lopez, Maslin A |  | 260.3
PR | 995 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 360.88
PR | 995 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 180.44
PR | 995 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 360.88
PR | 995 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 270.66
PR | 995 | 02/21/25 | 368 | Trower-Kelly, Fidel D |  | 489.06
PR | 995 | 02/28/25 | 504 | Cosentino, Brandon C |  | 378.62
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 16.76
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 67.05
PR | 995 | 02/28/25 | 520 | Chastain, Aaron R |  | 362.85
PR | 995 | 02/28/25 | 528 | Eliassen, Cory H |  | 449.62
PR | 995 | 02/28/25 | 529 | Games, Jordan M |  | 1045.16
PR | 995 | 02/28/25 | 538 | Johnson, Jake E |  | 64.97
PR | 995 | 02/28/25 | 540 | Lopez, Maslin A |  | 65.08
PR | 995 | 02/28/25 | 540 | Lopez, Maslin A |  | 130.15
PR | 995 | 02/28/25 | 540 | Lopez, Maslin A |  | 260.3
PR | 995 | 02/28/25 | 540 | Lopez, Maslin A |  | 65.08
PR | 995 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 270.66
PR | 995 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 556.35
PR | 995 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 360.88
PR | 995 | 02/28/25 | 558 | Trower-Kelly, Fidel D |  | 481.41
PR | 995 | 03/07/25 | 17 | Cosentino, Brandon C |  | 449.62
PR | 995 | 03/07/25 | 29 | Barnhart, Joseph N |  | 33.52
PR | 995 | 03/07/25 | 33 | Chastain, Aaron R |  | 419.54
PR | 995 | 03/07/25 | 41 | Eliassen, Cory H |  | 693.16
PR | 995 | 03/07/25 | 42 | Games, Jordan M |  | 1045.16
PR | 995 | 03/07/25 | 51 | Johnson, Jake E |  | 43.32
PR | 995 | 03/07/25 | 53 | Lopez, Maslin A |  | 325.38
PR | 995 | 03/07/25 | 53 | Lopez, Maslin A |  | 113.88
PR | 995 | 03/07/25 | 53 | Lopez, Maslin A |  | 211.5
PR | 995 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 661.61
PR | 995 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 210.51
PR | 995 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 210.51
PR | 995 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 60.15
PR | 995 | 03/07/25 | 71 | Trower-Kelly, Fidel D |  | 443.21
PR | 995 | 03/07/25 | 99 | Lopez, Maslin A |  | 65.08
PR | 995 | 03/14/25 | 217 | Cosentino, Brandon C |  | 283.97
PR | 995 | 03/14/25 | 233 | Chastain, Aaron R |  | 453.56
PR | 995 | 03/14/25 | 241 | Eliassen, Cory H |  | 599.49
PR | 995 | 03/14/25 | 242 | Games, Jordan M |  | 836.13
PR | 995 | 03/14/25 | 251 | Johnson, Jake E |  | 21.66
PR | 995 | 03/14/25 | 253 | Lopez, Maslin A |  | 130.15
PR | 995 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 270.66
PR | 995 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 03/14/25 | 271 | Trower-Kelly, Fidel D |  | 489.06
PR | 995 | 03/14/25 | 275 | Wilson, Garret A |  | 133.11
PR | 995 | 03/14/25 | 400 | Cosentino, Brandon C |  | 189.31
PR | 995 | 03/14/25 | 401 | Cruz Reyes, Jose |  | 161.7
PR | 995 | 03/14/25 | 410 | Cosentino, Brandon C |  | -189.31
PR | 995 | 03/14/25 | 411 | Cruz Reyes, Jose |  | -161.7
PR | 995 | 03/21/25 | 422 | Barnhart, Joseph N |  | 150.86
PR | 995 | 03/21/25 | 422 | Barnhart, Joseph N |  | 33.52
PR | 995 | 03/21/25 | 426 | Chastain, Aaron R |  | 272.14
PR | 995 | 03/21/25 | 434 | Eliassen, Cory H |  | 599.49
PR | 995 | 03/21/25 | 435 | Games, Jordan M |  | 992.9
PR | 995 | 03/21/25 | 465 | Trower-Kelly, Fidel D |  | 489.06
PR | 995 | 03/21/25 | 476 | Cosentino, Brandon C |  | 189.31
PR | 995 | 03/28/25 | 565 | Cosentino, Brandon C |  | 242.56
PR | 995 | 03/28/25 | 577 | Barnhart, Joseph N |  | 33.52
PR | 995 | 03/28/25 | 581 | Chastain, Aaron R |  | 272.14
PR | 995 | 03/28/25 | 589 | Eliassen, Cory H |  | 510.5
PR | 995 | 03/28/25 | 590 | Games, Jordan M |  | 627.1
PR | 995 | 03/28/25 | 600 | Johnson, Jake E |  | 86.63
PR | 995 | 03/28/25 | 610 | Paco Leyva, Orlando |  | 60.15
PR | 995 | 03/28/25 | 622 | Trower-Kelly, Fidel D |  | 489.06
PR | 995 | 04/04/25 | 8 | Cosentino, Brandon C |  | 473.28
PR | 995 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 124.24
PR | 995 | 04/04/25 | 24 | Chastain, Aaron R |  | 453.56
PR | 995 | 04/04/25 | 32 | Eliassen, Cory H |  | 599.49
PR | 995 | 04/04/25 | 33 | Games, Jordan M |  | 914.52
PR | 995 | 04/04/25 | 43 | Johnson, Jake E |  | 64.97
PR | 995 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 210.51
PR | 995 | 04/04/25 | 65 | Trower-Kelly, Fidel D |  | 489.06
PR | 995 | 04/04/25 | 104 | Wilson, Garret A |  | -133.11
PR | 995 | 04/11/25 | 171 | Cosentino, Brandon C |  | 473.28
PR | 995 | 04/11/25 | 204 | Chastain, Aaron R |  | 442.22
PR | 995 | 04/11/25 | 210 | Draves, Steven W |  | 433.84
PR | 995 | 04/11/25 | 212 | Eliassen, Cory H |  | 449.62
PR | 995 | 04/11/25 | 213 | Games, Jordan M |  | 1045.16
PR | 995 | 04/11/25 | 245 | Trower-Kelly, Fidel D |  | 611.32
PR | 995 | 04/18/25 | 409 | Anderson, Richard P |  | 96.14
PR | 995 | 04/18/25 | 409 | Anderson, Richard P |  | 128.18
PR | 995 | 04/18/25 | 411 | Castro, Marcus J |  | 97.61
PR | 995 | 04/18/25 | 412 | Cosentino, Brandon C |  | 378.62
PR | 995 | 04/18/25 | 412 | Cosentino, Brandon C |  | 70.99
PR | 995 | 04/18/25 | 413 | Cruz Reyes, Jose |  | 181.92
PR | 995 | 04/18/25 | 416 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 90.22
PR | 995 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 120.29
PR | 995 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A |  | 226.29
PR | 995 | 04/18/25 | 422 | Ascencio, Jose L |  | 186.35
PR | 995 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I |  | 195.23
PR | 995 | 04/18/25 | 424 | Barnhart, Joseph N |  | 201.14
PR | 995 | 04/18/25 | 424 | Barnhart, Joseph N |  | 67.05
PR | 995 | 04/18/25 | 424 | Barnhart, Joseph N |  | 67.05
PR | 995 | 04/18/25 | 426 | Carmona, Raul O |  | 235.16
PR | 995 | 04/18/25 | 428 | Chastain, Aaron R |  | 425.21
PR | 995 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 168.61
PR | 995 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 04/18/25 | 436 | Eliassen, Cory H |  | 449.62
PR | 995 | 04/18/25 | 436 | Eliassen, Cory H |  | 112.4
PR | 995 | 04/18/25 | 437 | Games, Jordan M |  | 391.94
PR | 995 | 04/18/25 | 437 | Games, Jordan M |  | 1045.16
PR | 995 | 04/18/25 | 439 | Gerard, Jordan E |  | 266.22
PR | 995 | 04/18/25 | 441 | Gochez Molina, Douglas O |  | 110.93
PR | 995 | 04/18/25 | 443 | Goodwin, Marcus A |  | 110.93
PR | 995 | 04/18/25 | 447 | Johnson, Jake E |  | 64.97
PR | 995 | 04/18/25 | 449 | Lopez, Maslin A |  | 97.61
PR | 995 | 04/18/25 | 453 | Melgar Moz, Brandon |  | 97.61
PR | 995 | 04/18/25 | 454 | Mendoza Morales, Jesus A |  | 181.92
PR | 995 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 90.22
PR | 995 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 240.58
PR | 995 | 04/18/25 | 458 | Perez Araque, Manuel A |  | 110.93
PR | 995 | 04/18/25 | 459 | Portillo Soriano, Walter A |  | 155.3
PR | 995 | 04/18/25 | 462 | Rodriguez Arevalos, Christian |  | 226.29
PR | 995 | 04/18/25 | 466 | Suniga Aviles, Kelvin A |  | 93.18
PR | 995 | 04/18/25 | 468 | Taylor, Evan R |  | 153.82
PR | 995 | 04/18/25 | 469 | Trower-Kelly, Fidel D |  | 137.55
PR | 995 | 04/18/25 | 469 | Trower-Kelly, Fidel D |  | 611.32
PR | 995 | 04/18/25 | 473 | Yohannes Jr., Samson |  | 97.61
PR | 995 | 04/18/25 | 475 | Zuniga Avilez, Eduar A |  | 97.61
PR | 995 | 04/25/25 | 551 | Cosentino, Brandon C |  | 378.62
PR | 995 | 04/25/25 | 555 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 04/25/25 | 560 | Araque, Mario W |  | 97.61
PR | 995 | 04/25/25 | 563 | Barnhart, Joseph N |  | 167.62
PR | 995 | 04/25/25 | 563 | Barnhart, Joseph N |  | 33.52
PR | 995 | 04/25/25 | 567 | Chastain, Aaron R |  | 362.85
PR | 995 | 04/25/25 | 575 | Eliassen, Cory H |  | 449.62
PR | 995 | 04/25/25 | 576 | Games, Jordan M |  | 627.1
PR | 995 | 04/25/25 | 586 | Johnson, Jake E |  | 21.66
PR | 995 | 04/25/25 | 596 | Paco Leyva, Orlando |  | 481.17
PR | 995 | 04/25/25 | 602 | Romero Garza, Jesus I |  | 146.42
PR | 995 | 04/25/25 | 608 | Trower-Kelly, Fidel D |  | 366.79
PR | 995 | 05/02/25 | 5 | Cosentino, Brandon C |  | 94.66
PR | 995 | 05/02/25 | 21 | Chastain, Aaron R |  | 90.71
PR | 995 | 05/02/25 | 29 | Eliassen, Cory H |  | 149.87
PR | 995 | 05/02/25 | 30 | Games, Jordan M |  | 862.26
PR | 995 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 05/02/25 | 32 | Gerard, Jordan E |  | 29.58
PR | 995 | 05/02/25 | 41 | Lopez, Maslin A |  | 65.08
PR | 995 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 60.15
PR | 995 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 90.22
PR | 995 | 05/02/25 | 61 | Trower-Kelly, Fidel D |  | 122.26
PR | 995 | 05/02/25 | 62 | Vazquez Popoca, Jose N |  | 138.04
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 67.05
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 67.05
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 33.52
PR | 995 | 05/09/25 | 173 | Games, Jordan M |  | 444.19
PR | 995 | 05/09/25 | 184 | Lopez, Maslin A |  | 130.15
PR | 995 | 05/09/25 | 192 | Paco Leyva, Orlando |  | 240.58
PR | 995 | 05/16/25 | 361 | Barnhart, Joseph N |  | 33.52
PR | 995 | 05/16/25 | 372 | Games, Jordan M |  | 496.45
PR | 995 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 05/16/25 | 403 | Vazquez Popoca, Jose N |  | 414.12
PR | 995 | 05/23/25 | 468 | Games, Jordan M |  | 418.06
PR | 995 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 90.22
PR | 995 | 05/23/25 | 499 | Vazquez Popoca, Jose N |  | 500.4
PR | 995 | 05/30/25 | 545 | Barnhart, Joseph N |  | 100.57
PR | 995 | 05/30/25 | 545 | Barnhart, Joseph N |  | 33.52
PR | 995 | 05/30/25 | 545 | Barnhart, Joseph N |  | 33.52
PR | 995 | 05/30/25 | 557 | Games, Jordan M |  | 418.06
PR | 995 | 05/30/25 | 588 | Vazquez Popoca, Jose N |  | 138.04
PR | 995 | 06/06/25 | 24 | Galdamez, Dagoberto A |  | 331.3
PR | 995 | 06/06/25 | 33 | Barnhart, Joseph N |  | 519.62
PR | 995 | 06/06/25 | 33 | Barnhart, Joseph N |  | 67.05
PR | 995 | 06/06/25 | 45 | Games, Jordan M |  | 209.03
PR | 995 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 06/06/25 | 63 | Paco Leyva, Orlando |  | 541.31
PR | 995 | 06/06/25 | 63 | Paco Leyva, Orlando |  | 180.44
PR | 995 | 06/06/25 | 75 | Vazquez Popoca, Jose N |  | 690.2
PR | 995 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 248.47
PR | 995 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 82.82
PR | 995 | 06/13/25 | 190 | Aquino, Juan |  | 110.43
PR | 995 | 06/13/25 | 194 | Barnhart, Joseph N |  | 335.24
PR | 995 | 06/13/25 | 206 | Games, Jordan M |  | 627.1
PR | 995 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 06/13/25 | 208 | Gerard, Jordan E |  | 59.16
PR | 995 | 06/13/25 | 217 | Lopez, Maslin A |  | 130.15
PR | 995 | 06/13/25 | 217 | Lopez, Maslin A |  | 65.08
PR | 995 | 06/13/25 | 217 | Lopez, Maslin A |  | 65.08
PR | 995 | 06/13/25 | 225 | Paco Leyva, Orlando |  | 541.31
PR | 995 | 06/13/25 | 225 | Paco Leyva, Orlando |  | 360.88
PR | 995 | 06/13/25 | 237 | Vazquez Popoca, Jose N |  | 276.08
PR | 995 | 06/20/25 | 314 | Galdamez, Dagoberto A |  | 248.47
PR | 995 | 06/20/25 | 322 | Barnhart, Joseph N |  | 301.72
PR | 995 | 06/20/25 | 333 | Games, Jordan M |  | 770.81
PR | 995 | 06/20/25 | 344 | Lopez, Maslin A |  | 390.46
PR | 995 | 06/20/25 | 352 | Paco Leyva, Orlando |  | 451.1
PR | 995 | 06/20/25 | 364 | Vazquez Popoca, Jose N |  | 552.16
PR | 995 | 06/27/25 | 464 | Barnhart, Thomas L |  | 678.37
PR | 995 | 06/27/25 | 468 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 636.96
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 67.05
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 67.05
PR | 995 | 06/27/25 | 488 | Games, Jordan M |  | 823.06
PR | 995 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 06/27/25 | 490 | Gerard, Jordan E |  | 29.58
PR | 995 | 06/27/25 | 499 | Lopez, Maslin A |  | 650.76
PR | 995 | 06/27/25 | 507 | Paco Leyva, Orlando |  | 481.17
PR | 995 | 06/27/25 | 507 | Paco Leyva, Orlando |  | 240.58
PR | 995 | 06/27/25 | 519 | Vazquez Popoca, Jose N |  | 690.2
PR | 995 | 07/03/25 | 8 | Barnhart, Thomas L |  | 254.39
PR | 995 | 07/03/25 | 12 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 07/03/25 | 12 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 07/03/25 | 19 | Barnhart, Joseph N |  | 134.1
PR | 995 | 07/03/25 | 19 | Barnhart, Joseph N |  | 201.14
PR | 995 | 07/03/25 | 19 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/03/25 | 31 | Games, Jordan M |  | 627.1
PR | 995 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 68.03
PR | 995 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 102.05
PR | 995 | 07/03/25 | 42 | Lopez, Maslin A |  | 650.76
PR | 995 | 07/03/25 | 50 | Paco Leyva, Orlando |  | 511.24
PR | 995 | 07/03/25 | 62 | Vazquez Popoca, Jose N |  | 276.08
PR | 995 | 07/11/25 | 133 | Barnhart, Thomas L |  | 339.18
PR | 995 | 07/11/25 | 137 | Galdamez, Dagoberto A |  | 641.89
PR | 995 | 07/11/25 | 144 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/11/25 | 144 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/11/25 | 144 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/11/25 | 144 | Barnhart, Joseph N |  | 33.52
PR | 995 | 07/11/25 | 156 | Games, Jordan M |  | 810
PR | 995 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/11/25 | 166 | Lopez, Maslin A |  | 374.19
PR | 995 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 541.31
PR | 995 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 90.22
PR | 995 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 90.22
PR | 995 | 07/11/25 | 186 | Vazquez Popoca, Jose N |  | 534.91
PR | 995 | 07/18/25 | 301 | Barnhart, Thomas L |  | 466.38
PR | 995 | 07/18/25 | 304 | Galdamez, Dagoberto A |  | 662.59
PR | 995 | 07/18/25 | 304 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 335.24
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 167.62
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 100.57
PR | 995 | 07/18/25 | 323 | Games, Jordan M |  | 535.64
PR | 995 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/18/25 | 325 | Gerard, Jordan E |  | 29.58
PR | 995 | 07/18/25 | 333 | Lopez, Maslin A |  | 553.15
PR | 995 | 07/18/25 | 333 | Lopez, Maslin A |  | 32.54
PR | 995 | 07/18/25 | 333 | Lopez, Maslin A |  | 32.54
PR | 995 | 07/18/25 | 333 | Lopez, Maslin A |  | 32.54
PR | 995 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 601.46
PR | 995 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 150.37
PR | 995 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 180.44
PR | 995 | 07/18/25 | 353 | Vazquez Popoca, Jose N |  | 138.04
PR | 995 | 07/25/25 | 467 | Anderson, Richard P |  | 64.09
PR | 995 | 07/25/25 | 468 | Barnhart, Thomas L |  | 169.59
PR | 995 | 07/25/25 | 472 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 07/25/25 | 472 | Galdamez, Dagoberto A |  | 165.65
PR | 995 | 07/25/25 | 479 | Barnhart, Joseph N |  | 100.57
PR | 995 | 07/25/25 | 479 | Barnhart, Joseph N |  | 33.52
PR | 995 | 07/25/25 | 479 | Barnhart, Joseph N |  | 134.1
PR | 995 | 07/25/25 | 479 | Barnhart, Joseph N |  | 33.52
PR | 995 | 07/25/25 | 491 | Games, Jordan M |  | 470.32
PR | 995 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/25/25 | 493 | Gerard, Jordan E |  | 59.16
PR | 995 | 07/25/25 | 501 | Lopez, Maslin A |  | 325.38
PR | 995 | 07/25/25 | 501 | Lopez, Maslin A |  | 65.08
PR | 995 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 451.1
PR | 995 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 240.58
PR | 995 | 08/01/25 | 9 | Araque, Mario W |  | 283.97
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 134.1
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/01/25 | 24 | Games, Jordan M |  | 627.1
PR | 995 | 08/01/25 | 34 | Lopez, Maslin A |  | 260.3
PR | 995 | 08/01/25 | 42 | Paco Leyva, Orlando |  | 120.29
PR | 995 | 08/01/25 | 43 | Perez Araque, Manuel A |  | 331.3
PR | 995 | 08/08/25 | 140 | Araque, Mario W |  | 283.97
PR | 995 | 08/08/25 | 143 | Barnhart, Joseph N |  | 301.72
PR | 995 | 08/08/25 | 150 | Cruz, Azael S |  | 252.42
PR | 995 | 08/08/25 | 155 | Games, Jordan M |  | 679.35
PR | 995 | 08/08/25 | 165 | Lopez, Maslin A |  | 260.3
PR | 995 | 08/08/25 | 173 | Paco Leyva, Orlando |  | 240.58
PR | 995 | 08/08/25 | 174 | Perez Araque, Manuel A |  | 220.86
PR | 995 | 08/15/25 | 268 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/15/25 | 268 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/15/25 | 280 | Games, Jordan M |  | 496.45
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 67.05
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 100.57
PR | 995 | 08/22/25 | 384 | Games, Jordan M |  | 627.1
PR | 995 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 08/22/25 | 386 | Gerard, Jordan E |  | 59.16
PR | 995 | 08/22/25 | 394 | Lopez, Maslin A |  | 130.15
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/29/25 | 547 | Games, Jordan M |  | 26.13
PR | 995 | 09/05/25 | 13 | Hernandez Gonzalez, Osbaldo |  | 144.94
PR | 995 | 09/05/25 | 19 | Barnhart, Joseph N |  | 335.24
PR | 995 | 09/05/25 | 19 | Barnhart, Joseph N |  | 234.67
PR | 995 | 09/05/25 | 26 | Cruz, Azael S |  | 236.64
PR | 995 | 09/05/25 | 32 | Games, Jordan M |  | 418.06
PR | 995 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 102.05
PR | 995 | 09/05/25 | 40 | Jimenez Alvarenga, Gerson M |  | 134.59
PR | 995 | 09/05/25 | 42 | Lopez, Maslin A |  | 260.3
PR | 995 | 09/05/25 | 42 | Lopez, Maslin A |  | 32.54
PR | 995 | 09/05/25 | 46 | Melgar Moz, Brandon |  | 177.48
PR | 995 | 09/05/25 | 50 | Paco Leyva, Orlando |  | 481.17
PR | 995 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 177.48
PR | 995 | 09/05/25 | 63 | Zuniga Avilez, Eduar A |  | 177.48
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 234.67
PR | 995 | 09/12/25 | 123 | Cruz, Azael S |  | 252.42
PR | 995 | 09/12/25 | 129 | Games, Jordan M |  | 810
PR | 995 | 09/12/25 | 130 | Gerard, Jeffrey S |  | 102.05
PR | 995 | 09/12/25 | 131 | Gerard, Jordan E |  | 29.58
PR | 995 | 09/12/25 | 131 | Gerard, Jordan E |  | 29.58
PR | 995 | 09/12/25 | 139 | Lopez, Maslin A |  | 260.3
PR | 995 | 09/12/25 | 143 | Melgar Moz, Brandon |  | 189.31
PR | 995 | 09/12/25 | 147 | Paco Leyva, Orlando |  | 390.95
PR | 995 | 09/12/25 | 156 | Suniga Aviles, Kelvin A |  | 473.28
PR | 995 | 09/12/25 | 160 | Zuniga Avilez, Eduar A |  | 473.28
PR | 995 | 09/19/25 | 248 | Barnhart, Joseph N |  | 972.2
PR | 995 | 09/19/25 | 261 | Games, Jordan M |  | 391.94
PR | 995 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 68.03
PR | 995 | 09/19/25 | 270 | Lima Romero, Melvin A |  | 563.99
PR | 995 | 09/19/25 | 275 | Melgar Moz, Brandon |  | 94.66
PR | 995 | 09/19/25 | 279 | Paco Leyva, Orlando |  | 1112.7
PR | 995 | 09/19/25 | 288 | Suniga Aviles, Kelvin A |  | 437.78
PR | 995 | 09/19/25 | 293 | Zuniga Avilez, Eduar A |  | 437.78
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 67.05
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 58.67
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 25.14
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 209.03
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 326.61
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 215.56
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 209.03
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 84.92
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 186.17
PR | 995 | 09/26/25 | 432 | Games, Jordan M |  | 313.55
PR | 995 | 09/26/25 | 442 | Lopez, Maslin A |  | 130.15
PR | 995 | 09/26/25 | 442 | Lopez, Maslin A |  | 130.15
PR | 995 | 09/26/25 | 450 | Paco Leyva, Orlando |  | 67.66
PR | 995 | 09/26/25 | 450 | Paco Leyva, Orlando |  | 30.07
PR | 995 | 09/26/25 | 461 | Taylor, Evan R |  | 179.45
PR | 995 | 09/26/25 | 461 | Taylor, Evan R |  | 121.77
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 142.48
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 8.38
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 25.14
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 111.05
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 84.92
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 91.45
PR | 995 | 10/10/25 | 177 | Draves, Steven W |  | 142.35
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 209.03
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 19.6
PR | 995 | 10/10/25 | 200 | Paco Leyva, Orlando |  | 7.52
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 52.26
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 142.48
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 75.43
PR | 995 | 11/14/25 | 255 | Paco Leyva, Orlando |  | 127.81
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 125.72
PR | 995 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 17.01
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 8.38
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 67.05
PR | 995 | 12/05/25 | 62 | Gerard, Jeffrey S |  | 170.09
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 8.38
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 17.26
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 17.01
PR | 995 | 01/30/26 | 575 | Anderson, Richard P |  | 33.03
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 43.14
PR | 995 | 02/06/26 | 56 | Barnhart, Joseph N |  | 60.39
PR | 995 | 02/20/26 | 336 | Nunez Bravo, Jose L |  | 94.66
PR | 995 | 02/20/26 | 337 | Paco Leyva, Orlando |  | 77.65
PR | 995 | 02/20/26 | 337 | Paco Leyva, Orlando |  | 15.53
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 25.88
PR | 998 | 04/14/23 | 355 | Gerard, Jeffrey S |  | 4.78
PR | 998 | 04/28/23 | 783 | Gerard, Jeffrey S |  | 4.78
PR | 998 | 05/05/23 | 185 | Gerard, Jeffrey S |  | 14.34
PR | 998 | 05/12/23 | 423 | Gerard, Jeffrey S |  | 28.69
PR | 998 | 05/12/23 | 423 | Gerard, Jeffrey S |  | 14.34
PR | 998 | 05/19/23 | 644 | Gerard, Jeffrey S |  | 19.13
PR | 998 | 05/26/23 | 974 | Gerard, Jeffrey S |  | 28.69
PR | 998 | 05/26/23 | 974 | Gerard, Jeffrey S |  | 9.56
PR | 998 | 06/02/23 | 102 | Gerard, Jeffrey S |  | 9.56
PR | 998 | 06/09/23 | 357 | Gerard, Jeffrey S |  | 9.56
PR | 998 | 06/23/23 | 835 | Johnson, Jake E |  | 7.65
PR | 998 | 06/23/23 | 887 | Gerard, Jeffrey S |  | 9.56
PR | 998 | 06/30/23 | 1030 | Johnson, Jake E |  | 38.25
PR | 998 | 06/30/23 | 1080 | Gerard, Jeffrey S |  | 14.34
PR | 998 | 06/30/23 | 1080 | Gerard, Jeffrey S |  | 9.56
PR | 998 | 07/07/23 | 63 | Johnson, Jake E |  | 7.65
PR | 998 | 07/07/23 | 113 | Gerard, Jeffrey S |  | 4.78
PR | 998 | 07/14/23 | 379 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/20/23 | 568 | Johnson, Jake E |  | 7.96
PR | 998 | 07/20/23 | 615 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/28/23 | 707 | Johnson, Jake E |  | 7.96
PR | 998 | 08/04/23 | 109 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/11/23 | 323 | Johnson, Jake E |  | 7.96
PR | 998 | 08/11/23 | 375 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 08/18/23 | 559 | Johnson, Jake E |  | 11.93
PR | 998 | 08/18/23 | 612 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/18/23 | 612 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/25/23 | 780 | Johnson, Jake E |  | 19.89
PR | 998 | 08/25/23 | 834 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 08/25/23 | 834 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/01/23 | 61 | Johnson, Jake E |  | 11.93
PR | 998 | 09/01/23 | 115 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 09/01/23 | 115 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/08/23 | 344 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 09/08/23 | 344 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/15/23 | 508 | Anderson, Richard P |  | 24.86
PR | 998 | 09/15/23 | 514 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/15/23 | 567 | Johnson, Jake E |  | 7.96
PR | 998 | 09/15/23 | 587 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 09/15/23 | 623 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 09/15/23 | 623 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 09/22/23 | 807 | Anderson, Richard P |  | 146.69
PR | 998 | 09/22/23 | 811 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 09/22/23 | 813 | Barnhart, Joseph N |  | 20.81
PR | 998 | 09/22/23 | 847 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 09/22/23 | 864 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 09/22/23 | 865 | Johnson, Jake E |  | 23.87
PR | 998 | 09/22/23 | 884 | Paco Leyva, Orlando |  | 112
PR | 998 | 09/22/23 | 896 | Rodriguez, Eduardo D |  | 47.74
PR | 998 | 09/22/23 | 918 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 09/22/23 | 918 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 09/29/23 | 1128 | Anderson, Richard P |  | 136.74
PR | 998 | 09/29/23 | 1132 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 09/29/23 | 1170 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 09/29/23 | 1188 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 09/29/23 | 1189 | Johnson, Jake E |  | 15.91
PR | 998 | 09/29/23 | 1210 | Paco Leyva, Orlando |  | 186.66
PR | 998 | 09/29/23 | 1221 | Rodriguez, Eduardo D |  | 31.82
PR | 998 | 09/29/23 | 1245 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 09/29/23 | 1245 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/06/23 | 23 | Anderson, Richard P |  | 54.7
PR | 998 | 10/06/23 | 27 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 10/06/23 | 65 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 10/06/23 | 85 | Jimenez Alvarenga, Gerson M |  | 77.57
PR | 998 | 10/06/23 | 86 | Johnson, Jake E |  | 19.89
PR | 998 | 10/06/23 | 107 | Paco Leyva, Orlando |  | 167.99
PR | 998 | 10/06/23 | 142 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 10/06/23 | 142 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/13/23 | 322 | Anderson, Richard P |  | 116.85
PR | 998 | 10/13/23 | 364 | Fox, Tamron P |  | 16.52
PR | 998 | 10/13/23 | 365 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 10/13/23 | 385 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 10/13/23 | 386 | Johnson, Jake E |  | 19.89
PR | 998 | 10/13/23 | 404 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 10/13/23 | 407 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 10/13/23 | 415 | Reed, Reuben H |  | 37.94
PR | 998 | 10/13/23 | 442 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 10/13/23 | 442 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 10/20/23 | 591 | Anderson, Richard P |  | 74.59
PR | 998 | 10/20/23 | 595 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 10/20/23 | 597 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/20/23 | 597 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/20/23 | 633 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 10/20/23 | 653 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 10/20/23 | 654 | Johnson, Jake E |  | 31.82
PR | 998 | 10/20/23 | 671 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 10/20/23 | 675 | Paco Leyva, Orlando |  | 163.33
PR | 998 | 10/20/23 | 711 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 10/27/23 | 842 | Anderson, Richard P |  | 74.59
PR | 998 | 10/27/23 | 842 | Anderson, Richard P |  | 29.84
PR | 998 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I |  | 38.71
PR | 998 | 10/27/23 | 846 | Balderas Ortiz, Ricardo I |  | 74.05
PR | 998 | 10/27/23 | 884 | Galdamez, Dagoberto A |  | 107.64
PR | 998 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M |  | 65.64
PR | 998 | 10/27/23 | 904 | Jimenez Alvarenga, Gerson M |  | 5.97
PR | 998 | 10/27/23 | 905 | Johnson, Jake E |  | 19.89
PR | 998 | 10/27/23 | 926 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/27/23 | 926 | Paco Leyva, Orlando |  | 14
PR | 998 | 10/27/23 | 961 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 10/27/23 | 961 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 11/03/23 | 5 | Anderson, Richard P |  | 79.56
PR | 998 | 11/03/23 | 5 | Anderson, Richard P |  | 94.48
PR | 998 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I |  | 57.22
PR | 998 | 11/03/23 | 9 | Balderas Ortiz, Ricardo I |  | 77.42
PR | 998 | 11/03/23 | 11 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/03/23 | 47 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 11/03/23 | 47 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M |  | 50.72
PR | 998 | 11/03/23 | 67 | Jimenez Alvarenga, Gerson M |  | 68.62
PR | 998 | 11/03/23 | 68 | Johnson, Jake E |  | 27.85
PR | 998 | 11/03/23 | 85 | Nunez Bravo, Jose L |  | 24.63
PR | 998 | 11/03/23 | 85 | Nunez Bravo, Jose L |  | 31.67
PR | 998 | 11/03/23 | 123 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 11/03/23 | 123 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/10/23 | 448 | Anderson, Richard P |  | 171.55
PR | 998 | 11/10/23 | 452 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 11/10/23 | 482 | Draves, Steven W |  | 12.62
PR | 998 | 11/10/23 | 490 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 11/10/23 | 510 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 11/10/23 | 511 | Johnson, Jake E |  | 15.91
PR | 998 | 11/10/23 | 528 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 11/10/23 | 532 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 11/10/23 | 567 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/17/23 | 807 | Anderson, Richard P |  | 164.09
PR | 998 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I |  | 10.1
PR | 998 | 11/17/23 | 811 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 11/17/23 | 847 | Galdamez, Dagoberto A |  | 9.64
PR | 998 | 11/17/23 | 847 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M |  | 8.95
PR | 998 | 11/17/23 | 866 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 11/17/23 | 867 | Johnson, Jake E |  | 15.91
PR | 998 | 11/17/23 | 884 | Nunez Bravo, Jose L |  | 54.54
PR | 998 | 11/17/23 | 888 | Paco Leyva, Orlando |  | 177.33
PR | 998 | 11/17/23 | 923 | Gerard, Jeffrey S |  | 42.23
PR | 998 | 11/17/23 | 923 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/22/23 | 1056 | Anderson, Richard P |  | 19.89
PR | 998 | 11/22/23 | 1060 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 11/22/23 | 1095 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 11/22/23 | 1115 | Jimenez Alvarenga, Gerson M |  | 23.87
PR | 998 | 11/22/23 | 1116 | Johnson, Jake E |  | 7.96
PR | 998 | 11/22/23 | 1116 | Johnson, Jake E |  | 3.98
PR | 998 | 11/22/23 | 1133 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 11/22/23 | 1137 | Paco Leyva, Orlando |  | 130.66
PR | 998 | 11/22/23 | 1172 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/01/23 | 45 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 12/01/23 | 45 | Galdamez, Dagoberto A |  | 19.28
PR | 998 | 12/01/23 | 66 | Johnson, Jake E |  | 3.98
PR | 998 | 12/01/23 | 87 | Paco Leyva, Orlando |  | 107.33
PR | 998 | 12/01/23 | 87 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 12/01/23 | 123 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 12/08/23 | 326 | Anderson, Richard P |  | 24.86
PR | 998 | 12/08/23 | 326 | Anderson, Richard P |  | 29.84
PR | 998 | 12/08/23 | 330 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 12/08/23 | 331 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/08/23 | 331 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/08/23 | 364 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 12/08/23 | 384 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 12/08/23 | 385 | Johnson, Jake E |  | 19.89
PR | 998 | 12/08/23 | 406 | Paco Leyva, Orlando |  | 121.33
PR | 998 | 12/08/23 | 406 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 12/08/23 | 443 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 12/08/23 | 443 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 12/15/23 | 678 | Anderson, Richard P |  | 19.89
PR | 998 | 12/15/23 | 682 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 12/15/23 | 717 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 12/15/23 | 717 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 12/15/23 | 737 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 12/15/23 | 738 | Johnson, Jake E |  | 3.98
PR | 998 | 12/15/23 | 759 | Paco Leyva, Orlando |  | 158.66
PR | 998 | 12/15/23 | 794 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 12/15/23 | 794 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 12/22/23 | 958 | Anderson, Richard P |  | 14.92
PR | 998 | 12/22/23 | 962 | Balderas Ortiz, Ricardo I |  | 50.49
PR | 998 | 12/22/23 | 997 | Galdamez, Dagoberto A |  | 33.74
PR | 998 | 12/22/23 | 997 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M |  | 31.33
PR | 998 | 12/22/23 | 1016 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 12/22/23 | 1033 | Nunez Bravo, Jose L |  | 12.32
PR | 998 | 12/22/23 | 1037 | Paco Leyva, Orlando |  | 49
PR | 998 | 12/22/23 | 1037 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 12/22/23 | 1073 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 12/22/23 | 1073 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 12/22/23 | 1075 | Johnson, Jake E |  | 7.96
PR | 998 | 12/22/23 | 1075 | Johnson, Jake E |  | 3.98
PR | 998 | 12/29/23 | 1106 | Anderson, Richard P |  | 14.92
PR | 998 | 12/29/23 | 1110 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 12/29/23 | 1164 | Jimenez Alvarenga, Gerson M |  | 23.87
PR | 998 | 12/29/23 | 1181 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 12/29/23 | 1185 | Paco Leyva, Orlando |  | 130.66
PR | 998 | 12/29/23 | 1220 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 12/29/23 | 1220 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 12/29/23 | 1222 | Johnson, Jake E |  | 3.98
PR | 998 | 01/05/24 | 16 | Anderson, Richard P |  | 99.45
PR | 998 | 01/05/24 | 20 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 01/05/24 | 21 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/05/24 | 55 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 01/05/24 | 61 | Gochez Molina, Douglas O |  | 53.55
PR | 998 | 01/05/24 | 61 | Gochez Molina, Douglas O |  | 7.65
PR | 998 | 01/05/24 | 74 | Jimenez Alvarenga, Gerson M |  | 23.87
PR | 998 | 01/05/24 | 91 | Nunez Bravo, Jose L |  | 28.15
PR | 998 | 01/05/24 | 92 | Nuno Ordonez, Roberto F |  | 7.34
PR | 998 | 01/05/24 | 92 | Nuno Ordonez, Roberto F |  | 7.34
PR | 998 | 01/05/24 | 95 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 01/05/24 | 130 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 01/05/24 | 130 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 01/05/24 | 132 | Johnson, Jake E |  | 7.96
PR | 998 | 01/12/24 | 354 | Anderson, Richard P |  | 32.32
PR | 998 | 01/12/24 | 354 | Anderson, Richard P |  | 7.46
PR | 998 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 67.32
PR | 998 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 01/12/24 | 358 | Balderas Ortiz, Ricardo I |  | 13.46
PR | 998 | 01/12/24 | 378 | de Dios, Pedro |  | 7.96
PR | 998 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 64.26
PR | 998 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 01/12/24 | 393 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 01/12/24 | 399 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 59.67
PR | 998 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 11.93
PR | 998 | 01/12/24 | 411 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 01/12/24 | 422 | McCurry, Maxwell J |  | 7.34
PR | 998 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 49.27
PR | 998 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 01/12/24 | 428 | Nunez Bravo, Jose L |  | 7.04
PR | 998 | 01/12/24 | 429 | Nuno Ordonez, Roberto F |  | 29.38
PR | 998 | 01/12/24 | 432 | Paco Leyva, Orlando |  | 167.99
PR | 998 | 01/12/24 | 432 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 01/12/24 | 465 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 01/12/24 | 465 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 01/12/24 | 467 | Johnson, Jake E |  | 11.93
PR | 998 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I |  | 124.54
PR | 998 | 01/19/24 | 652 | Balderas Ortiz, Ricardo I |  | 10.1
PR | 998 | 01/19/24 | 653 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/19/24 | 656 | Belcher, Jacob T |  | 8.57
PR | 998 | 01/19/24 | 660 | Carmona, Raul O |  | 64.87
PR | 998 | 01/19/24 | 687 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 01/19/24 | 688 | Games, Jordan M |  | 21.11
PR | 998 | 01/19/24 | 693 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 01/19/24 | 693 | Gochez Molina, Douglas O |  | 15.3
PR | 998 | 01/19/24 | 704 | Jimenez, D'angelo J |  | 59.98
PR | 998 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 01/19/24 | 705 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 01/19/24 | 715 | McCurry, Maxwell J |  | 7.34
PR | 998 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 14.08
PR | 998 | 01/19/24 | 721 | Nunez Bravo, Jose L |  | 28.15
PR | 998 | 01/19/24 | 722 | Nuno Ordonez, Roberto F |  | 29.38
PR | 998 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 84
PR | 998 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 01/19/24 | 725 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/19/24 | 740 | Sontay Garcia, Juan C |  | 38.56
PR | 998 | 01/19/24 | 758 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 01/19/24 | 758 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 01/19/24 | 760 | Johnson, Jake E |  | 15.91
PR | 998 | 01/26/24 | 918 | Anderson, Richard P |  | 14.92
PR | 998 | 01/26/24 | 922 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 01/26/24 | 926 | Belcher, Jacob T |  | 85.68
PR | 998 | 01/26/24 | 930 | Carmona, Raul O |  | 162.18
PR | 998 | 01/26/24 | 957 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 01/26/24 | 957 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 01/26/24 | 963 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 01/26/24 | 975 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 01/26/24 | 985 | McCurry, Maxwell J |  | 44.06
PR | 998 | 01/26/24 | 985 | McCurry, Maxwell J |  | 14.69
PR | 998 | 01/26/24 | 991 | Nunez Bravo, Jose L |  | 38.71
PR | 998 | 01/26/24 | 991 | Nunez Bravo, Jose L |  | 28.15
PR | 998 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 88.66
PR | 998 | 01/26/24 | 995 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/26/24 | 1011 | Sontay Garcia, Juan C |  | 51.41
PR | 998 | 01/26/24 | 1029 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 01/26/24 | 1029 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 01/26/24 | 1031 | Johnson, Jake E |  | 7.96
PR | 998 | 02/02/24 | 11 | Anderson, Richard P |  | 14.92
PR | 998 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 02/02/24 | 15 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 02/02/24 | 16 | Barnhart, Joseph N |  | 13.01
PR | 998 | 02/02/24 | 19 | Belcher, Jacob T |  | 59.98
PR | 998 | 02/02/24 | 19 | Belcher, Jacob T |  | 25.7
PR | 998 | 02/02/24 | 23 | Carmona, Raul O |  | 113.53
PR | 998 | 02/02/24 | 23 | Carmona, Raul O |  | 48.65
PR | 998 | 02/02/24 | 50 | Galdamez, Dagoberto A |  | 89.96
PR | 998 | 02/02/24 | 50 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 02/02/24 | 56 | Gochez Molina, Douglas O |  | 30.6
PR | 998 | 02/02/24 | 56 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 02/02/24 | 68 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 02/02/24 | 78 | McCurry, Maxwell J |  | 14.69
PR | 998 | 02/02/24 | 78 | McCurry, Maxwell J |  | 22.03
PR | 998 | 02/02/24 | 78 | McCurry, Maxwell J |  | 22.03
PR | 998 | 02/02/24 | 84 | Nunez Bravo, Jose L |  | 49.27
PR | 998 | 02/02/24 | 84 | Nunez Bravo, Jose L |  | 21.11
PR | 998 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 102.66
PR | 998 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 42
PR | 998 | 02/02/24 | 88 | Paco Leyva, Orlando |  | 42
PR | 998 | 02/02/24 | 104 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 02/02/24 | 105 | Storozhuk, Maxim A |  | 33.66
PR | 998 | 02/02/24 | 105 | Storozhuk, Maxim A |  | 6.73
PR | 998 | 02/02/24 | 121 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 02/02/24 | 121 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 02/02/24 | 123 | Johnson, Jake E |  | 11.93
PR | 998 | 02/09/24 | 231 | Anderson, Richard P |  | 4.97
PR | 998 | 02/09/24 | 235 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/09/24 | 239 | Belcher, Jacob T |  | 17.14
PR | 998 | 02/09/24 | 239 | Belcher, Jacob T |  | 68.54
PR | 998 | 02/09/24 | 243 | Carmona, Raul O |  | 64.87
PR | 998 | 02/09/24 | 243 | Carmona, Raul O |  | 97.31
PR | 998 | 02/09/24 | 266 | Escalante Escobar, Boanerge |  | 42.84
PR | 998 | 02/09/24 | 270 | Galdamez, Dagoberto A |  | 64.26
PR | 998 | 02/09/24 | 270 | Galdamez, Dagoberto A |  | 64.26
PR | 998 | 02/09/24 | 276 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 02/09/24 | 276 | Gochez Molina, Douglas O |  | 15.3
PR | 998 | 02/09/24 | 288 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 02/09/24 | 297 | McCabe, Thomas C |  | 80.78
PR | 998 | 02/09/24 | 298 | McCurry, Maxwell J |  | 44.06
PR | 998 | 02/09/24 | 298 | McCurry, Maxwell J |  | 29.38
PR | 998 | 02/09/24 | 304 | Nunez Bravo, Jose L |  | 42.23
PR | 998 | 02/09/24 | 304 | Nunez Bravo, Jose L |  | 28.15
PR | 998 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 98
PR | 998 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 70
PR | 998 | 02/09/24 | 308 | Paco Leyva, Orlando |  | 14
PR | 998 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/09/24 | 343 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/09/24 | 345 | Johnson, Jake E |  | 11.93
PR | 998 | 02/16/24 | 488 | Anderson, Richard P |  | 19.89
PR | 998 | 02/16/24 | 492 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/16/24 | 496 | Belcher, Jacob T |  | 68.54
PR | 998 | 02/16/24 | 500 | Carmona, Raul O |  | 162.18
PR | 998 | 02/16/24 | 523 | Escalante Escobar, Boanerge |  | 21.42
PR | 998 | 02/16/24 | 523 | Escalante Escobar, Boanerge |  | 85.68
PR | 998 | 02/16/24 | 527 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 02/16/24 | 533 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 02/16/24 | 543 | Hubbard, Justin A |  | 84.46
PR | 998 | 02/16/24 | 545 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 02/16/24 | 554 | McCabe, Thomas C |  | 132.96
PR | 998 | 02/16/24 | 555 | McCurry, Maxwell J |  | 72.52
PR | 998 | 02/16/24 | 559 | Molina, Carlos G |  | 79.56
PR | 998 | 02/16/24 | 561 | Nunez Bravo, Jose L |  | 43.99
PR | 998 | 02/16/24 | 561 | Nunez Bravo, Jose L |  | 26.39
PR | 998 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 98
PR | 998 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 02/16/24 | 565 | Paco Leyva, Orlando |  | 35
PR | 998 | 02/16/24 | 582 | Sontay Garcia, Juan C |  | 51.41
PR | 998 | 02/16/24 | 583 | Storozhuk, Maxim A |  | 53.86
PR | 998 | 02/16/24 | 584 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 02/16/24 | 597 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 02/16/24 | 599 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/16/24 | 599 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/16/24 | 601 | Johnson, Jake E |  | 7.96
PR | 998 | 02/23/24 | 659 | Anderson, Richard P |  | 14.92
PR | 998 | 02/23/24 | 663 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/23/24 | 667 | Belcher, Jacob T |  | 70.69
PR | 998 | 02/23/24 | 671 | Carmona, Raul O |  | 97.31
PR | 998 | 02/23/24 | 693 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 02/23/24 | 697 | Galdamez, Dagoberto A |  | 125.31
PR | 998 | 02/23/24 | 701 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 02/23/24 | 711 | Hubbard, Justin A |  | 109.09
PR | 998 | 02/23/24 | 713 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 02/23/24 | 722 | McCabe, Thomas C |  | 53.86
PR | 998 | 02/23/24 | 722 | McCabe, Thomas C |  | 77.42
PR | 998 | 02/23/24 | 723 | McCurry, Maxwell J |  | 14.69
PR | 998 | 02/23/24 | 723 | McCurry, Maxwell J |  | 41.31
PR | 998 | 02/23/24 | 724 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 02/23/24 | 727 | Molina, Carlos G |  | 61.66
PR | 998 | 02/23/24 | 729 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 98
PR | 998 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 28
PR | 998 | 02/23/24 | 733 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 02/23/24 | 750 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 02/23/24 | 751 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 02/23/24 | 752 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 02/23/24 | 765 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 02/23/24 | 770 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/23/24 | 770 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/23/24 | 773 | Johnson, Jake E |  | 15.91
PR | 998 | 03/01/24 | 4 | Anderson, Richard P |  | 19.89
PR | 998 | 03/01/24 | 8 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/01/24 | 12 | Belcher, Jacob T |  | 51.41
PR | 998 | 03/01/24 | 12 | Belcher, Jacob T |  | 17.14
PR | 998 | 03/01/24 | 15 | Carmona, Raul O |  | 129.74
PR | 998 | 03/01/24 | 36 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 03/01/24 | 37 | Escobar Ramirez, Carlos M |  | 33.66
PR | 998 | 03/01/24 | 42 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/01/24 | 48 | Guerrero Espinoza, Mario |  | 32.13
PR | 998 | 03/01/24 | 51 | Hubbard, Justin A |  | 140.76
PR | 998 | 03/01/24 | 53 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/01/24 | 55 | Lopez, Maslin A |  | 35.34
PR | 998 | 03/01/24 | 55 | Lopez, Maslin A |  | 20.2
PR | 998 | 03/01/24 | 60 | McCabe, Thomas C |  | 80.78
PR | 998 | 03/01/24 | 60 | McCabe, Thomas C |  | 20.2
PR | 998 | 03/01/24 | 61 | McCurry, Maxwell J |  | 44.06
PR | 998 | 03/01/24 | 61 | McCurry, Maxwell J |  | 29.38
PR | 998 | 03/01/24 | 62 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 03/01/24 | 65 | Molina, Carlos G |  | 31.82
PR | 998 | 03/01/24 | 67 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 102.66
PR | 998 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 03/01/24 | 71 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 03/01/24 | 80 | Rodriguez Arevalos, Christian |  | 26.93
PR | 998 | 03/01/24 | 86 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 03/01/24 | 87 | Storozhuk, Maxim A |  | 53.86
PR | 998 | 03/01/24 | 88 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 03/01/24 | 95 | Wilson, Garret A |  | 33.05
PR | 998 | 03/01/24 | 96 | Yohannes Jr., Samson |  | 55.54
PR | 998 | 03/01/24 | 100 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 03/01/24 | 100 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 03/01/24 | 105 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 03/01/24 | 107 | Gerard, Mitchell J |  | 74.66
PR | 998 | 03/01/24 | 110 | Johnson, Jake E |  | 3.98
PR | 998 | 03/08/24 | 250 | Anderson, Richard P |  | 29.84
PR | 998 | 03/08/24 | 251 | Aquino, Juan |  | 66.1
PR | 998 | 03/08/24 | 252 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/08/24 | 254 | Belcher, Jacob T |  | 51.41
PR | 998 | 03/08/24 | 254 | Belcher, Jacob T |  | 17.14
PR | 998 | 03/08/24 | 255 | Carmona, Raul O |  | 129.74
PR | 998 | 03/08/24 | 269 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 03/08/24 | 270 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 03/08/24 | 273 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/08/24 | 276 | Guerrero Espinoza, Mario |  | 55.08
PR | 998 | 03/08/24 | 278 | Hubbard, Justin A |  | 109.09
PR | 998 | 03/08/24 | 278 | Hubbard, Justin A |  | 28.15
PR | 998 | 03/08/24 | 280 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/08/24 | 283 | Martinez Garcia, Cesar B |  | 48.96
PR | 998 | 03/08/24 | 284 | McCabe, Thomas C |  | 104.35
PR | 998 | 03/08/24 | 285 | McCurry, Maxwell J |  | 73.44
PR | 998 | 03/08/24 | 286 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 03/08/24 | 288 | Molina, Carlos G |  | 31.82
PR | 998 | 03/08/24 | 290 | Nunez Bravo, Jose L |  | 56.3
PR | 998 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 65.33
PR | 998 | 03/08/24 | 292 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 03/08/24 | 294 | Platero Navas, Ronald A |  | 48.96
PR | 998 | 03/08/24 | 296 | Puentez, Victor M |  | 26.93
PR | 998 | 03/08/24 | 296 | Puentez, Victor M |  | 40.39
PR | 998 | 03/08/24 | 299 | Rodriguez Arevalos, Christian |  | 13.46
PR | 998 | 03/08/24 | 305 | Sontay Garcia, Juan C |  | 51.41
PR | 998 | 03/08/24 | 306 | Storozhuk, Maxim A |  | 40.39
PR | 998 | 03/08/24 | 307 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 03/08/24 | 307 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 03/08/24 | 311 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 03/08/24 | 313 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 03/08/24 | 317 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 03/08/24 | 343 | Johnson, Jake E |  | 11.93
PR | 998 | 03/08/24 | 344 | Lopez, Maslin A |  | 100.98
PR | 998 | 03/08/24 | 358 | Taylor, Evan R |  | 99.45
PR | 998 | 03/08/24 | 363 | Young, Joshua S |  | 82.62
PR | 998 | 03/15/24 | 505 | Anderson, Richard P |  | 24.86
PR | 998 | 03/15/24 | 506 | Aquino, Juan |  | 82.62
PR | 998 | 03/15/24 | 509 | Belcher, Jacob T |  | 34.27
PR | 998 | 03/15/24 | 510 | Carmona, Raul O |  | 162.18
PR | 998 | 03/15/24 | 523 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 03/15/24 | 524 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 03/15/24 | 526 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 03/15/24 | 528 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/15/24 | 531 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 03/15/24 | 533 | Hubbard, Justin A |  | 56.3
PR | 998 | 03/15/24 | 533 | Hubbard, Justin A |  | 56.3
PR | 998 | 03/15/24 | 533 | Hubbard, Justin A |  | 28.15
PR | 998 | 03/15/24 | 535 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/15/24 | 537 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 03/15/24 | 538 | McCurry, Maxwell J |  | 14.69
PR | 998 | 03/15/24 | 538 | McCurry, Maxwell J |  | 14.69
PR | 998 | 03/15/24 | 538 | McCurry, Maxwell J |  | 29.38
PR | 998 | 03/15/24 | 538 | McCurry, Maxwell J |  | 14.69
PR | 998 | 03/15/24 | 539 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 03/15/24 | 541 | Molina, Carlos G |  | 79.56
PR | 998 | 03/15/24 | 543 | Nunez Bravo, Jose L |  | 42.23
PR | 998 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 28
PR | 998 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 03/15/24 | 545 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 03/15/24 | 547 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 03/15/24 | 549 | Puentez, Victor M |  | 67.32
PR | 998 | 03/15/24 | 552 | Rodriguez Arevalos, Christian |  | 43.76
PR | 998 | 03/15/24 | 558 | Sontay Garcia, Juan C |  | 51.41
PR | 998 | 03/15/24 | 559 | Storozhuk, Maxim A |  | 53.86
PR | 998 | 03/15/24 | 560 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 03/15/24 | 560 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 03/15/24 | 564 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 03/15/24 | 566 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 03/15/24 | 574 | Puentez, Victor M |  | -67.32
PR | 998 | 03/15/24 | 580 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/15/24 | 599 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/15/24 | 601 | Gerard, Mitchell J |  | 9.33
PR | 998 | 03/15/24 | 601 | Gerard, Mitchell J |  | 18.67
PR | 998 | 03/15/24 | 608 | Johnson, Jake E |  | 11.93
PR | 998 | 03/15/24 | 610 | Lopez, Maslin A |  | 60.59
PR | 998 | 03/15/24 | 610 | Lopez, Maslin A |  | 40.39
PR | 998 | 03/15/24 | 625 | Puentez, Victor M |  | 67.32
PR | 998 | 03/15/24 | 629 | Taylor, Evan R |  | 159.12
PR | 998 | 03/15/24 | 635 | Young, Joshua S |  | 82.62
PR | 998 | 03/22/24 | 798 | Anderson, Richard P |  | 49.73
PR | 998 | 03/22/24 | 799 | Aquino, Juan |  | 82.62
PR | 998 | 03/22/24 | 802 | Belcher, Jacob T |  | 17.14
PR | 998 | 03/22/24 | 803 | Carmona, Raul O |  | 162.18
PR | 998 | 03/22/24 | 811 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 03/22/24 | 812 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 03/22/24 | 814 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 03/22/24 | 816 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/22/24 | 819 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 03/22/24 | 821 | Hubbard, Justin A |  | 28.15
PR | 998 | 03/22/24 | 821 | Hubbard, Justin A |  | 56.3
PR | 998 | 03/22/24 | 821 | Hubbard, Justin A |  | 56.3
PR | 998 | 03/22/24 | 823 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/22/24 | 824 | McCurry, Maxwell J |  | 44.06
PR | 998 | 03/22/24 | 824 | McCurry, Maxwell J |  | 14.69
PR | 998 | 03/22/24 | 825 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 03/22/24 | 826 | Molina, Carlos G |  | 79.56
PR | 998 | 03/22/24 | 828 | Nunez Bravo, Jose L |  | 68.62
PR | 998 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 84
PR | 998 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 42
PR | 998 | 03/22/24 | 829 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 03/22/24 | 830 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 03/22/24 | 832 | Rodriguez Arevalos, Christian |  | 107.71
PR | 998 | 03/22/24 | 836 | Sontay Garcia, Juan C |  | 62.65
PR | 998 | 03/22/24 | 837 | Storozhuk, Maxim A |  | 43.76
PR | 998 | 03/22/24 | 838 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/22/24 | 842 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 03/22/24 | 847 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/22/24 | 878 | Johnson, Jake E |  | 11.93
PR | 998 | 03/22/24 | 880 | Lopez, Maslin A |  | 20.2
PR | 998 | 03/22/24 | 880 | Lopez, Maslin A |  | 60.59
PR | 998 | 03/22/24 | 884 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 03/22/24 | 886 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 03/22/24 | 896 | Puentez, Victor M |  | 67.32
PR | 998 | 03/22/24 | 902 | Taylor, Evan R |  | 159.12
PR | 998 | 03/22/24 | 907 | Wilson, Garret A |  | 53.7
PR | 998 | 03/22/24 | 908 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 03/22/24 | 909 | Young, Joshua S |  | 82.62
PR | 998 | 03/29/24 | 1180 | Anderson, Richard P |  | 29.84
PR | 998 | 03/29/24 | 1180 | Anderson, Richard P |  | 9.95
PR | 998 | 03/29/24 | 1181 | Aquino, Juan |  | 82.62
PR | 998 | 03/29/24 | 1182 | Barnhart, Joseph N |  | 10.4
PR | 998 | 03/29/24 | 1190 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 03/29/24 | 1192 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 03/29/24 | 1198 | Hubbard, Justin A |  | 110.85
PR | 998 | 03/29/24 | 1200 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/29/24 | 1202 | Molina, Carlos G |  | 79.56
PR | 998 | 03/29/24 | 1204 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 84
PR | 998 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 03/29/24 | 1205 | Paco Leyva, Orlando |  | 42
PR | 998 | 03/29/24 | 1210 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 03/29/24 | 1212 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/29/24 | 1216 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 03/29/24 | 1219 | Araque, Mario W |  | 67.32
PR | 998 | 03/29/24 | 1221 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/29/24 | 1226 | Carmona, Raul O |  | 162.18
PR | 998 | 03/29/24 | 1243 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/29/24 | 1249 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/29/24 | 1256 | Johnson, Jake E |  | 23.87
PR | 998 | 03/29/24 | 1258 | Lopez, Maslin A |  | 100.98
PR | 998 | 03/29/24 | 1262 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 03/29/24 | 1264 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 03/29/24 | 1265 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 03/29/24 | 1273 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 03/29/24 | 1276 | Puentez, Victor M |  | 67.32
PR | 998 | 03/29/24 | 1283 | Taylor, Evan R |  | 159.12
PR | 998 | 03/29/24 | 1289 | Yohannes Jr., Samson |  | 80.78
PR | 998 | 03/29/24 | 1290 | Young, Joshua S |  | 66.1
PR | 998 | 04/05/24 | 2 | Anderson, Richard P |  | 14.92
PR | 998 | 04/05/24 | 2 | Anderson, Richard P |  | 4.97
PR | 998 | 04/05/24 | 3 | Aquino, Juan |  | 82.62
PR | 998 | 04/05/24 | 4 | Barnhart, Joseph N |  | 5.2
PR | 998 | 04/05/24 | 12 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 04/05/24 | 14 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 04/05/24 | 17 | Guerrero Espinoza, Mario |  | 55.08
PR | 998 | 04/05/24 | 19 | Hubbard, Justin A |  | 82.7
PR | 998 | 04/05/24 | 21 | Molina, Carlos G |  | 47.74
PR | 998 | 04/05/24 | 21 | Molina, Carlos G |  | 15.91
PR | 998 | 04/05/24 | 21 | Molina, Carlos G |  | 15.91
PR | 998 | 04/05/24 | 23 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 84
PR | 998 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 04/05/24 | 24 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 04/05/24 | 25 | Rodriguez Arevalos, Christian |  | 43.76
PR | 998 | 04/05/24 | 29 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 04/05/24 | 32 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 04/05/24 | 32 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 04/05/24 | 36 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/05/24 | 41 | Carmona, Raul O |  | 162.18
PR | 998 | 04/05/24 | 59 | Escobar Ramirez, Carlos M |  | 56.61
PR | 998 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/05/24 | 65 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/05/24 | 73 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/05/24 | 74 | Johnson, Jake E |  | 27.85
PR | 998 | 04/05/24 | 76 | Lopez, Maslin A |  | 95.93
PR | 998 | 04/05/24 | 80 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 04/05/24 | 82 | McCurry, Maxwell J |  | 42.23
PR | 998 | 04/05/24 | 82 | McCurry, Maxwell J |  | 29.38
PR | 998 | 04/05/24 | 83 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 04/05/24 | 84 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 04/05/24 | 92 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 04/05/24 | 95 | Puentez, Victor M |  | 67.32
PR | 998 | 04/05/24 | 101 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 04/05/24 | 102 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 04/05/24 | 104 | Taylor, Evan R |  | 95.47
PR | 998 | 04/05/24 | 111 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 04/05/24 | 112 | Young, Joshua S |  | 49.57
PR | 998 | 04/05/24 | 113 | Zepeda Mendoza, Cesar |  | 13.46
PR | 998 | 04/05/24 | 132 | Jimenez Alvarenga, Gerson M |  | -119.34
PR | 998 | 04/05/24 | 133 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/12/24 | 165 | Aquino, Juan |  | 82.62
PR | 998 | 04/12/24 | 166 | Barnhart, Joseph N |  | 20.81
PR | 998 | 04/12/24 | 166 | Barnhart, Joseph N |  | 5.2
PR | 998 | 04/12/24 | 174 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 04/12/24 | 177 | Guerrero Espinoza, Mario |  | 55.08
PR | 998 | 04/12/24 | 180 | Molina, Carlos G |  | 63.65
PR | 998 | 04/12/24 | 180 | Molina, Carlos G |  | 15.91
PR | 998 | 04/12/24 | 182 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 107.33
PR | 998 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 42
PR | 998 | 04/12/24 | 183 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 04/12/24 | 188 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 04/12/24 | 190 | Weeks, Gregg A |  | 146.88
PR | 998 | 04/12/24 | 192 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 04/12/24 | 192 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 04/12/24 | 196 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/12/24 | 201 | Carmona, Raul O |  | 162.18
PR | 998 | 04/12/24 | 211 | Diaz Morales, Guni |  | 60.59
PR | 998 | 04/12/24 | 212 | Diaz Morales, Teofilo |  | 67.32
PR | 998 | 04/12/24 | 219 | Escalante Escobar, Boanerge |  | 64.26
PR | 998 | 04/12/24 | 220 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 04/12/24 | 226 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/12/24 | 234 | Hubbard, Justin A |  | 28.15
PR | 998 | 04/12/24 | 234 | Hubbard, Justin A |  | 84.46
PR | 998 | 04/12/24 | 235 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/12/24 | 236 | Johnson, Jake E |  | 7.96
PR | 998 | 04/12/24 | 238 | Lopez, Maslin A |  | 83.31
PR | 998 | 04/12/24 | 242 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 04/12/24 | 244 | McCurry, Maxwell J |  | 29.38
PR | 998 | 04/12/24 | 244 | McCurry, Maxwell J |  | 14.69
PR | 998 | 04/12/24 | 244 | McCurry, Maxwell J |  | 14.69
PR | 998 | 04/12/24 | 245 | Melgar Moz, Brandon |  | 53.86
PR | 998 | 04/12/24 | 246 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 04/12/24 | 254 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 04/12/24 | 257 | Puentez, Victor M |  | 67.32
PR | 998 | 04/12/24 | 262 | Sontay Garcia, Juan C |  | 51.41
PR | 998 | 04/12/24 | 263 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 04/12/24 | 263 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 04/12/24 | 265 | Taylor, Evan R |  | 159.12
PR | 998 | 04/12/24 | 271 | Yohannes Jr., Samson |  | 80.78
PR | 998 | 04/12/24 | 272 | Young, Joshua S |  | 82.62
PR | 998 | 04/12/24 | 273 | Zepeda Mendoza, Cesar |  | 67.32
PR | 998 | 04/19/24 | 444 | Anderson, Richard P |  | 124.31
PR | 998 | 04/19/24 | 445 | Barnhart, Joseph N |  | 10.4
PR | 998 | 04/19/24 | 452 | Diaz Morales, Cristian A |  | 67.32
PR | 998 | 04/19/24 | 453 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 04/19/24 | 458 | Molina, Carlos G |  | 47.74
PR | 998 | 04/19/24 | 458 | Molina, Carlos G |  | 31.82
PR | 998 | 04/19/24 | 460 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 56
PR | 998 | 04/19/24 | 461 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 04/19/24 | 466 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 04/19/24 | 468 | Weeks, Gregg A |  | 117.5
PR | 998 | 04/19/24 | 470 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 04/19/24 | 473 | Aquino, Juan |  | 82.62
PR | 998 | 04/19/24 | 476 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/19/24 | 481 | Carmona, Raul O |  | 162.18
PR | 998 | 04/19/24 | 490 | Diaz Morales, Elber |  | 67.32
PR | 998 | 04/19/24 | 491 | Diaz Morales, Guni |  | 67.32
PR | 998 | 04/19/24 | 492 | Diaz Morales, Teofilo |  | 67.32
PR | 998 | 04/19/24 | 493 | Diaz Morales, Urias |  | 67.32
PR | 998 | 04/19/24 | 495 | Draves, Steven W |  | 16.83
PR | 998 | 04/19/24 | 499 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 04/19/24 | 500 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 04/19/24 | 507 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 04/19/24 | 515 | Hubbard, Justin A |  | 38.71
PR | 998 | 04/19/24 | 515 | Hubbard, Justin A |  | 56.3
PR | 998 | 04/19/24 | 516 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/19/24 | 517 | Johnson, Jake E |  | 11.93
PR | 998 | 04/19/24 | 519 | Lopez, Maslin A |  | 100.98
PR | 998 | 04/19/24 | 523 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 04/19/24 | 525 | McCurry, Maxwell J |  | 58.75
PR | 998 | 04/19/24 | 525 | McCurry, Maxwell J |  | 14.69
PR | 998 | 04/19/24 | 526 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 04/19/24 | 527 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 04/19/24 | 532 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 04/19/24 | 535 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 04/19/24 | 538 | Puentez, Victor M |  | 67.32
PR | 998 | 04/19/24 | 543 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 04/19/24 | 544 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 04/19/24 | 546 | Taylor, Evan R |  | 159.12
PR | 998 | 04/19/24 | 552 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 04/19/24 | 553 | Young, Joshua S |  | 82.62
PR | 998 | 04/19/24 | 554 | Zepeda Mendoza, Cesar |  | 67.32
PR | 998 | 04/26/24 | 770 | Anderson, Richard P |  | 34.81
PR | 998 | 04/26/24 | 770 | Anderson, Richard P |  | 4.97
PR | 998 | 04/26/24 | 778 | Diaz Morales, Cristian A |  | 67.32
PR | 998 | 04/26/24 | 779 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 04/26/24 | 783 | Molina, Carlos G |  | 47.74
PR | 998 | 04/26/24 | 783 | Molina, Carlos G |  | 15.91
PR | 998 | 04/26/24 | 785 | Nunez Bravo, Jose L |  | 56.3
PR | 998 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 98
PR | 998 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 04/26/24 | 786 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 04/26/24 | 791 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 04/26/24 | 795 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 04/26/24 | 798 | Aquino, Juan |  | 66.1
PR | 998 | 04/26/24 | 801 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/26/24 | 806 | Carmona, Raul O |  | 162.18
PR | 998 | 04/26/24 | 807 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 04/26/24 | 815 | Diaz Morales, Elber |  | 26.93
PR | 998 | 04/26/24 | 815 | Diaz Morales, Elber |  | 26.93
PR | 998 | 04/26/24 | 816 | Diaz Morales, Guni |  | 67.32
PR | 998 | 04/26/24 | 817 | Diaz Morales, Teofilo |  | 53.86
PR | 998 | 04/26/24 | 818 | Diaz Morales, Urias |  | 13.46
PR | 998 | 04/26/24 | 823 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 04/26/24 | 824 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 04/26/24 | 831 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/26/24 | 839 | Hubbard, Justin A |  | 28.15
PR | 998 | 04/26/24 | 840 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/26/24 | 841 | Johnson, Jake E |  | 19.89
PR | 998 | 04/26/24 | 843 | Lopez, Maslin A |  | 98.46
PR | 998 | 04/26/24 | 847 | Martinez Garcia, Cesar B |  | 59.67
PR | 998 | 04/26/24 | 849 | McCurry, Maxwell J |  | 58.75
PR | 998 | 04/26/24 | 850 | Melgar Moz, Brandon |  | 53.86
PR | 998 | 04/26/24 | 851 | Mendoza Morales, Jesus A |  | 98.8
PR | 998 | 04/26/24 | 851 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 04/26/24 | 856 | Ortiz Carmona, Juan M |  | 75.89
PR | 998 | 04/26/24 | 859 | Platero Navas, Ronald A |  | 61.2
PR | 998 | 04/26/24 | 862 | Puentez, Victor M |  | 67.32
PR | 998 | 04/26/24 | 867 | Sontay Garcia, Juan C |  | 64.26
PR | 998 | 04/26/24 | 868 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 04/26/24 | 868 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 04/26/24 | 870 | Taylor, Evan R |  | 119.34
PR | 998 | 04/26/24 | 876 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 04/26/24 | 878 | Zepeda Mendoza, Cesar |  | 63.95
PR | 998 | 05/03/24 | 3 | Anderson, Richard P |  | 179.01
PR | 998 | 05/03/24 | 4 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/03/24 | 7 | Cosentino, Brandon C |  | 29.38
PR | 998 | 05/03/24 | 11 | Diaz Morales, Cristian A |  | 67.32
PR | 998 | 05/03/24 | 12 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 05/03/24 | 17 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 05/03/24 | 18 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 05/03/24 | 21 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 05/03/24 | 23 | Weeks, Gregg A |  | 117.5
PR | 998 | 05/03/24 | 24 | Zamudio Sanchez, Jose R |  | 29.38
PR | 998 | 05/03/24 | 25 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 05/03/24 | 25 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 05/03/24 | 27 | Aquino, Juan |  | 66.1
PR | 998 | 05/03/24 | 29 | Ascencio, Jose L |  | 51.41
PR | 998 | 05/03/24 | 29 | Ascencio, Jose L |  | 51.41
PR | 998 | 05/03/24 | 30 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/03/24 | 33 | Boss, Benjamin T |  | 124.85
PR | 998 | 05/03/24 | 35 | Carmona, Raul O |  | 162.18
PR | 998 | 05/03/24 | 36 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 05/03/24 | 36 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 05/03/24 | 45 | Diaz Morales, Guni |  | 67.32
PR | 998 | 05/03/24 | 46 | Diaz Morales, Teofilo |  | 67.32
PR | 998 | 05/03/24 | 52 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 05/03/24 | 53 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/03/24 | 59 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/03/24 | 61 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 05/03/24 | 67 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/03/24 | 68 | Johnson, Jake E |  | 11.93
PR | 998 | 05/03/24 | 70 | Lopez, Maslin A |  | 100.98
PR | 998 | 05/03/24 | 74 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 05/03/24 | 77 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/03/24 | 78 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 05/03/24 | 78 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 05/03/24 | 83 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 05/03/24 | 87 | Portillo Soriano, Walter A |  | 64.26
PR | 998 | 05/03/24 | 88 | Puentez, Victor M |  | 67.32
PR | 998 | 05/03/24 | 91 | Romero Garza, Jesus I |  | 80.78
PR | 998 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 05/03/24 | 93 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 05/03/24 | 95 | Taylor, Evan R |  | 159.12
PR | 998 | 05/03/24 | 101 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 05/03/24 | 103 | Zepeda Mendoza, Cesar |  | 67.32
PR | 998 | 05/10/24 | 241 | Anderson, Richard P |  | 29.84
PR | 998 | 05/10/24 | 242 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/10/24 | 249 | Diaz Morales, Cristian A |  | 67.32
PR | 998 | 05/10/24 | 250 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 05/10/24 | 255 | Nunez Bravo, Jose L |  | 63.34
PR | 998 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 102.66
PR | 998 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 05/10/24 | 256 | Paco Leyva, Orlando |  | 28
PR | 998 | 05/10/24 | 259 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 05/10/24 | 261 | Weeks, Gregg A |  | 146.88
PR | 998 | 05/10/24 | 262 | Zamudio Sanchez, Jose R |  | 146.88
PR | 998 | 05/10/24 | 263 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 05/10/24 | 265 | Aquino, Juan |  | 82.62
PR | 998 | 05/10/24 | 267 | Ascencio, Jose L |  | 128.52
PR | 998 | 05/10/24 | 268 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/10/24 | 271 | Boss, Benjamin T |  | 31.21
PR | 998 | 05/10/24 | 273 | Carmona, Raul O |  | 162.18
PR | 998 | 05/10/24 | 274 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 05/10/24 | 274 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 05/10/24 | 283 | Diaz Morales, Guni |  | 67.32
PR | 998 | 05/10/24 | 284 | Diaz Morales, Teofilo |  | 67.32
PR | 998 | 05/10/24 | 290 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 05/10/24 | 291 | Escobar Ramirez, Carlos M |  | 59.67
PR | 998 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/10/24 | 297 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/10/24 | 299 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 05/10/24 | 305 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/10/24 | 306 | Johnson, Jake E |  | 15.91
PR | 998 | 05/10/24 | 308 | Lopez, Maslin A |  | 78.26
PR | 998 | 05/10/24 | 312 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 05/10/24 | 315 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/10/24 | 316 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 05/10/24 | 321 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 05/10/24 | 325 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/10/24 | 326 | Puentez, Victor M |  | 67.32
PR | 998 | 05/10/24 | 329 | Romero Garza, Jesus I |  | 60.59
PR | 998 | 05/10/24 | 331 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 05/10/24 | 331 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 05/10/24 | 333 | Taylor, Evan R |  | 159.12
PR | 998 | 05/10/24 | 339 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 05/10/24 | 341 | Zepeda Mendoza, Cesar |  | 67.32
PR | 998 | 05/17/24 | 469 | Anderson, Richard P |  | 174.04
PR | 998 | 05/17/24 | 470 | Barnhart, Joseph N |  | 31.21
PR | 998 | 05/17/24 | 477 | Diaz Morales, Cristian A |  | 13.46
PR | 998 | 05/17/24 | 478 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 05/17/24 | 483 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 102.66
PR | 998 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 05/17/24 | 484 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 05/17/24 | 487 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 05/17/24 | 489 | Weeks, Gregg A |  | 117.5
PR | 998 | 05/17/24 | 490 | Zamudio Sanchez, Jose R |  | 146.88
PR | 998 | 05/17/24 | 492 | Aquino, Juan |  | 82.62
PR | 998 | 05/17/24 | 494 | Ascencio, Jose L |  | 77.11
PR | 998 | 05/17/24 | 494 | Ascencio, Jose L |  | 51.41
PR | 998 | 05/17/24 | 495 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/17/24 | 498 | Boss, Benjamin T |  | 93.64
PR | 998 | 05/17/24 | 500 | Carmona, Raul O |  | 162.18
PR | 998 | 05/17/24 | 501 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 05/17/24 | 510 | Diaz Morales, Guni |  | 13.46
PR | 998 | 05/17/24 | 511 | Diaz Morales, Teofilo |  | 13.46
PR | 998 | 05/17/24 | 517 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 05/17/24 | 518 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/17/24 | 524 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/17/24 | 526 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 05/17/24 | 532 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/17/24 | 535 | Lopez, Maslin A |  | 100.98
PR | 998 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 12.24
PR | 998 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 36.72
PR | 998 | 05/17/24 | 539 | Martinez Garcia, Cesar B |  | 12.24
PR | 998 | 05/17/24 | 542 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/17/24 | 543 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 05/17/24 | 543 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 05/17/24 | 548 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 05/17/24 | 552 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/17/24 | 553 | Puentez, Victor M |  | 67.32
PR | 998 | 05/17/24 | 556 | Romero Garza, Jesus I |  | 80.78
PR | 998 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 05/17/24 | 558 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 05/17/24 | 560 | Taylor, Evan R |  | 159.12
PR | 998 | 05/17/24 | 566 | Yohannes Jr., Samson |  | 80.78
PR | 998 | 05/17/24 | 568 | Zepeda Mendoza, Cesar |  | 13.46
PR | 998 | 05/17/24 | 569 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 05/17/24 | 569 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 05/24/24 | 678 | Anderson, Richard P |  | 159.12
PR | 998 | 05/24/24 | 678 | Anderson, Richard P |  | 9.95
PR | 998 | 05/24/24 | 679 | Barnhart, Joseph N |  | 15.61
PR | 998 | 05/24/24 | 686 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 05/24/24 | 691 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 98
PR | 998 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 05/24/24 | 692 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 05/24/24 | 696 | Weeks, Gregg A |  | 135.86
PR | 998 | 05/24/24 | 697 | Zamudio Sanchez, Jose R |  | 102.82
PR | 998 | 05/24/24 | 699 | Aquino, Juan |  | 74.36
PR | 998 | 05/24/24 | 701 | Ascencio, Jose L |  | 102.82
PR | 998 | 05/24/24 | 701 | Ascencio, Jose L |  | 25.7
PR | 998 | 05/24/24 | 702 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/24/24 | 705 | Boss, Benjamin T |  | 156.06
PR | 998 | 05/24/24 | 707 | Carmona, Raul O |  | 162.18
PR | 998 | 05/24/24 | 708 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 05/24/24 | 722 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 05/24/24 | 723 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/24/24 | 729 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/24/24 | 731 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 05/24/24 | 737 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/24/24 | 738 | Johnson, Jake E |  | 15.91
PR | 998 | 05/24/24 | 739 | Lima Romero, Melvin A |  | 67.32
PR | 998 | 05/24/24 | 739 | Lima Romero, Melvin A |  | 13.46
PR | 998 | 05/24/24 | 740 | Lopez, Maslin A |  | 93.41
PR | 998 | 05/24/24 | 744 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 05/24/24 | 747 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/24/24 | 748 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 05/24/24 | 752 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 05/24/24 | 756 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/24/24 | 757 | Puentez, Victor M |  | 40.39
PR | 998 | 05/24/24 | 760 | Romero Garza, Jesus I |  | 20.2
PR | 998 | 05/24/24 | 762 | Storozhuk, Maxim A |  | 67.32
PR | 998 | 05/24/24 | 763 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 05/24/24 | 765 | Taylor, Evan R |  | 159.12
PR | 998 | 05/24/24 | 770 | Yohannes Jr., Samson |  | 94.67
PR | 998 | 05/24/24 | 772 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 05/31/24 | 792 | Anderson, Richard P |  | 144.2
PR | 998 | 05/31/24 | 792 | Anderson, Richard P |  | 4.97
PR | 998 | 05/31/24 | 793 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/31/24 | 800 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 05/31/24 | 805 | Nunez Bravo, Jose L |  | 56.3
PR | 998 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 42
PR | 998 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 05/31/24 | 806 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 05/31/24 | 810 | Weeks, Gregg A |  | 88.13
PR | 998 | 05/31/24 | 811 | Zamudio Sanchez, Jose R |  | 80.78
PR | 998 | 05/31/24 | 813 | Aquino, Juan |  | 66.1
PR | 998 | 05/31/24 | 815 | Ascencio, Jose L |  | 102.82
PR | 998 | 05/31/24 | 816 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 05/31/24 | 819 | Boss, Benjamin T |  | 124.85
PR | 998 | 05/31/24 | 821 | Carmona, Raul O |  | 129.74
PR | 998 | 05/31/24 | 822 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 05/31/24 | 836 | Escalante Escobar, Boanerge |  | 85.68
PR | 998 | 05/31/24 | 837 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 05/31/24 | 843 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 05/31/24 | 845 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 05/31/24 | 849 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 05/31/24 | 850 | Johnson, Jake E |  | 19.89
PR | 998 | 05/31/24 | 851 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 05/31/24 | 851 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 05/31/24 | 852 | Lopez, Maslin A |  | 80.78
PR | 998 | 05/31/24 | 856 | Martinez Garcia, Cesar B |  | 48.96
PR | 998 | 05/31/24 | 859 | Melgar Moz, Brandon |  | 53.86
PR | 998 | 05/31/24 | 860 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 05/31/24 | 864 | Ortiz Carmona, Juan M |  | 78.34
PR | 998 | 05/31/24 | 868 | Portillo Soriano, Walter A |  | 85.68
PR | 998 | 05/31/24 | 869 | Puentez, Victor M |  | 53.86
PR | 998 | 05/31/24 | 872 | Romero Garza, Jesus I |  | 20.2
PR | 998 | 05/31/24 | 874 | Storozhuk, Maxim A |  | 53.86
PR | 998 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 05/31/24 | 875 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 05/31/24 | 877 | Taylor, Evan R |  | 127.3
PR | 998 | 05/31/24 | 882 | Yohannes Jr., Samson |  | 80.78
PR | 998 | 05/31/24 | 884 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 06/07/24 | 80 | Anderson, Richard P |  | 9.95
PR | 998 | 06/07/24 | 80 | Anderson, Richard P |  | 19.89
PR | 998 | 06/07/24 | 80 | Anderson, Richard P |  | 79.56
PR | 998 | 06/07/24 | 81 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/07/24 | 81 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/07/24 | 88 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 06/07/24 | 94 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 06/07/24 | 95 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 06/07/24 | 98 | Weeks, Gregg A |  | 106.49
PR | 998 | 06/07/24 | 99 | Zamudio Sanchez, Jose R |  | 117.5
PR | 998 | 06/07/24 | 102 | Aquino, Juan |  | 82.62
PR | 998 | 06/07/24 | 104 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/07/24 | 105 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/07/24 | 108 | Boss, Benjamin T |  | 93.64
PR | 998 | 06/07/24 | 110 | Carmona, Raul O |  | 162.18
PR | 998 | 06/07/24 | 111 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/07/24 | 125 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 06/07/24 | 126 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 06/07/24 | 132 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 06/07/24 | 134 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 06/07/24 | 138 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 06/07/24 | 139 | Johnson, Jake E |  | 19.89
PR | 998 | 06/07/24 | 140 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 06/07/24 | 141 | Lopez, Maslin A |  | 100.98
PR | 998 | 06/07/24 | 145 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 06/07/24 | 148 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 06/07/24 | 149 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 06/07/24 | 149 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 06/07/24 | 153 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 06/07/24 | 157 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/07/24 | 158 | Puentez, Victor M |  | 67.32
PR | 998 | 06/07/24 | 164 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 06/07/24 | 164 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 06/07/24 | 166 | Taylor, Evan R |  | 159.12
PR | 998 | 06/07/24 | 171 | Yohannes Jr., Samson |  | 100.98
PR | 998 | 06/07/24 | 173 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 06/07/24 | 173 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 06/14/24 | 304 | Anderson, Richard P |  | 126.8
PR | 998 | 06/14/24 | 305 | Barnhart, Joseph N |  | 20.81
PR | 998 | 06/14/24 | 305 | Barnhart, Joseph N |  | 5.2
PR | 998 | 06/14/24 | 311 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 06/14/24 | 317 | Nunez Bravo, Jose L |  | 70.38
PR | 998 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 84
PR | 998 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 06/14/24 | 318 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 06/14/24 | 321 | Weeks, Gregg A |  | 117.5
PR | 998 | 06/14/24 | 322 | Zamudio Sanchez, Jose R |  | 69.77
PR | 998 | 06/14/24 | 324 | Aquino, Juan |  | 33.05
PR | 998 | 06/14/24 | 326 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/14/24 | 327 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/14/24 | 330 | Boss, Benjamin T |  | 93.64
PR | 998 | 06/14/24 | 332 | Carmona, Raul O |  | 162.18
PR | 998 | 06/14/24 | 333 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/14/24 | 348 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 06/14/24 | 349 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 06/14/24 | 355 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 06/14/24 | 357 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 06/14/24 | 361 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 06/14/24 | 362 | Johnson, Jake E |  | 15.91
PR | 998 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 06/14/24 | 363 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/14/24 | 364 | Lopez, Maslin A |  | 75.74
PR | 998 | 06/14/24 | 368 | Martinez Garcia, Cesar B |  | 61.2
PR | 998 | 06/14/24 | 371 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 06/14/24 | 372 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 06/14/24 | 372 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 06/14/24 | 376 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 06/14/24 | 380 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/14/24 | 381 | Puentez, Victor M |  | 67.32
PR | 998 | 06/14/24 | 387 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 06/14/24 | 389 | Taylor, Evan R |  | 63.65
PR | 998 | 06/14/24 | 394 | Yohannes Jr., Samson |  | 40.39
PR | 998 | 06/14/24 | 396 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 06/21/24 | 479 | Anderson, Richard P |  | 14.92
PR | 998 | 06/21/24 | 480 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/21/24 | 486 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 56
PR | 998 | 06/21/24 | 491 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 06/21/24 | 494 | Weeks, Gregg A |  | 117.5
PR | 998 | 06/21/24 | 496 | Aquino, Juan |  | 33.05
PR | 998 | 06/21/24 | 499 | Balderas Ortiz, Ricardo I |  | 131.27
PR | 998 | 06/21/24 | 502 | Boss, Benjamin T |  | 93.64
PR | 998 | 06/21/24 | 504 | Carmona, Raul O |  | 129.74
PR | 998 | 06/21/24 | 505 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/21/24 | 520 | Escalante Escobar, Boanerge |  | 107.1
PR | 998 | 06/21/24 | 521 | Escobar Ramirez, Carlos M |  | 61.2
PR | 998 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 06/21/24 | 527 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 06/21/24 | 532 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 06/21/24 | 533 | Johnson, Jake E |  | 7.96
PR | 998 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/21/24 | 534 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/21/24 | 535 | Lopez, Maslin A |  | 100.98
PR | 998 | 06/21/24 | 540 | McCabe, Thomas C |  | 107.71
PR | 998 | 06/21/24 | 541 | Melgar Moz, Brandon |  | 53.86
PR | 998 | 06/21/24 | 542 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 06/21/24 | 542 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 06/21/24 | 546 | Ortiz Carmona, Juan M |  | 78.34
PR | 998 | 06/21/24 | 549 | Portillo Soriano, Walter A |  | 85.68
PR | 998 | 06/21/24 | 552 | Romero Garza, Jesus I |  | 60.59
PR | 998 | 06/21/24 | 555 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 06/21/24 | 557 | Taylor, Evan R |  | 95.47
PR | 998 | 06/21/24 | 562 | Yohannes Jr., Samson |  | 40.39
PR | 998 | 06/21/24 | 564 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 06/28/24 | 686 | Anderson, Richard P |  | 47.24
PR | 998 | 06/28/24 | 687 | Barnhart, Joseph N |  | 20.81
PR | 998 | 06/28/24 | 687 | Barnhart, Joseph N |  | 15.61
PR | 998 | 06/28/24 | 693 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 135.33
PR | 998 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 42
PR | 998 | 06/28/24 | 698 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 06/28/24 | 701 | Weeks, Gregg A |  | 88.13
PR | 998 | 06/28/24 | 706 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/28/24 | 709 | Boss, Benjamin T |  | 62.42
PR | 998 | 06/28/24 | 711 | Carmona, Raul O |  | 129.74
PR | 998 | 06/28/24 | 712 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 06/28/24 | 727 | Escalante Escobar, Boanerge |  | 64.26
PR | 998 | 06/28/24 | 728 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/28/24 | 734 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 06/28/24 | 739 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 06/28/24 | 740 | Johnson, Jake E |  | 15.91
PR | 998 | 06/28/24 | 741 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 06/28/24 | 741 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 06/28/24 | 742 | Lopez, Maslin A |  | 60.59
PR | 998 | 06/28/24 | 749 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 06/28/24 | 749 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 06/28/24 | 753 | Ortiz Carmona, Juan M |  | 58.75
PR | 998 | 06/28/24 | 762 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 06/28/24 | 769 | Yohannes Jr., Samson |  | 40.39
PR | 998 | 06/28/24 | 771 | Zuniga Avilez, Eduar A |  | 48.96
PR | 998 | 07/05/24 | 3 | Anderson, Richard P |  | 59.67
PR | 998 | 07/05/24 | 4 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/05/24 | 10 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 07/05/24 | 14 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 07/05/24 | 15 | Rodriguez Arevalos, Christian |  | 19.51
PR | 998 | 07/05/24 | 17 | Weeks, Gregg A |  | 117.5
PR | 998 | 07/05/24 | 21 | Ascencio, Jose L |  | 25.7
PR | 998 | 07/05/24 | 22 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 07/05/24 | 25 | Boss, Benjamin T |  | 124.85
PR | 998 | 07/05/24 | 27 | Carmona, Raul O |  | 129.74
PR | 998 | 07/05/24 | 28 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 07/05/24 | 41 | Escalante Escobar, Boanerge |  | 85.68
PR | 998 | 07/05/24 | 42 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/05/24 | 42 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 07/05/24 | 48 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 07/05/24 | 52 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 07/05/24 | 53 | Johnson, Jake E |  | 11.93
PR | 998 | 07/05/24 | 54 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 07/05/24 | 55 | Lopez, Maslin A |  | 40.39
PR | 998 | 07/05/24 | 61 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 07/05/24 | 61 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 07/05/24 | 65 | Ortiz Carmona, Juan M |  | 97.92
PR | 998 | 07/05/24 | 74 | Suniga Aviles, Kelvin A |  | 33.74
PR | 998 | 07/05/24 | 74 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 07/05/24 | 76 | Taylor, Evan R |  | 31.82
PR | 998 | 07/05/24 | 81 | Yohannes Jr., Samson |  | 40.39
PR | 998 | 07/05/24 | 83 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 07/05/24 | 83 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 07/12/24 | 166 | Anderson, Richard P |  | 22.38
PR | 998 | 07/12/24 | 167 | Barnhart, Joseph N |  | 13.01
PR | 998 | 07/12/24 | 173 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 56
PR | 998 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 07/12/24 | 176 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 07/12/24 | 179 | Weeks, Gregg A |  | 88.13
PR | 998 | 07/12/24 | 184 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 07/12/24 | 187 | Boss, Benjamin T |  | 93.64
PR | 998 | 07/12/24 | 189 | Carmona, Raul O |  | 97.31
PR | 998 | 07/12/24 | 190 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 07/12/24 | 203 | Escalante Escobar, Boanerge |  | 64.26
PR | 998 | 07/12/24 | 204 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/12/24 | 210 | Gochez Molina, Douglas O |  | 15.3
PR | 998 | 07/12/24 | 210 | Gochez Molina, Douglas O |  | 30.6
PR | 998 | 07/12/24 | 215 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 07/12/24 | 216 | Johnson, Jake E |  | 3.98
PR | 998 | 07/12/24 | 217 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 07/12/24 | 218 | Lopez, Maslin A |  | 60.59
PR | 998 | 07/12/24 | 224 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 07/12/24 | 224 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 07/12/24 | 236 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 07/12/24 | 236 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 07/12/24 | 245 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 07/19/24 | 374 | Anderson, Richard P |  | 24.86
PR | 998 | 07/19/24 | 380 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 65.33
PR | 998 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 07/19/24 | 383 | Paco Leyva, Orlando |  | 70
PR | 998 | 07/19/24 | 389 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 07/19/24 | 390 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/19/24 | 390 | Barnhart, Joseph N |  | 2.6
PR | 998 | 07/19/24 | 393 | Boss, Benjamin T |  | 93.64
PR | 998 | 07/19/24 | 395 | Carmona, Raul O |  | 162.18
PR | 998 | 07/19/24 | 396 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 07/19/24 | 409 | Escalante Escobar, Boanerge |  | 85.68
PR | 998 | 07/19/24 | 410 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/19/24 | 410 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/19/24 | 416 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 07/19/24 | 421 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 07/19/24 | 422 | Johnson, Jake E |  | 7.96
PR | 998 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 07/19/24 | 423 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 07/19/24 | 424 | Lopez, Maslin A |  | 40.39
PR | 998 | 07/19/24 | 424 | Lopez, Maslin A |  | 40.39
PR | 998 | 07/19/24 | 430 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 07/19/24 | 430 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 07/19/24 | 443 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 07/19/24 | 443 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 07/19/24 | 449 | Weeks, Gregg A |  | 88.13
PR | 998 | 07/19/24 | 453 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 07/19/24 | 453 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 07/26/24 | 563 | Anderson, Richard P |  | 77.07
PR | 998 | 07/26/24 | 563 | Anderson, Richard P |  | 9.95
PR | 998 | 07/26/24 | 569 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 28
PR | 998 | 07/26/24 | 571 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 07/26/24 | 577 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 07/26/24 | 581 | Boss, Benjamin T |  | 124.85
PR | 998 | 07/26/24 | 583 | Carmona, Raul O |  | 32.44
PR | 998 | 07/26/24 | 583 | Carmona, Raul O |  | 97.31
PR | 998 | 07/26/24 | 584 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 07/26/24 | 597 | Escalante Escobar, Boanerge |  | 85.68
PR | 998 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 18.36
PR | 998 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 6.12
PR | 998 | 07/26/24 | 598 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 07/26/24 | 603 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 07/26/24 | 608 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 07/26/24 | 609 | Johnson, Jake E |  | 7.96
PR | 998 | 07/26/24 | 610 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 07/26/24 | 610 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 07/26/24 | 611 | Lopez, Maslin A |  | 80.78
PR | 998 | 07/26/24 | 617 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 07/26/24 | 617 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 07/26/24 | 630 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 07/26/24 | 630 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 07/26/24 | 636 | Weeks, Gregg A |  | 117.5
PR | 998 | 07/26/24 | 640 | Zuniga Avilez, Eduar A |  | 30.6
PR | 998 | 07/26/24 | 640 | Zuniga Avilez, Eduar A |  | 6.12
PR | 998 | 08/02/24 | 9 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 08/02/24 | 11 | Paco Leyva, Orlando |  | 28
PR | 998 | 08/02/24 | 17 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 08/02/24 | 18 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/02/24 | 21 | Boss, Benjamin T |  | 124.85
PR | 998 | 08/02/24 | 23 | Carmona, Raul O |  | 162.18
PR | 998 | 08/02/24 | 24 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 08/02/24 | 37 | Escalante Escobar, Boanerge |  | 21.42
PR | 998 | 08/02/24 | 38 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 08/02/24 | 43 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 08/02/24 | 48 | Jimenez Alvarenga, Gerson M |  | 23.87
PR | 998 | 08/02/24 | 49 | Johnson, Jake E |  | 3.98
PR | 998 | 08/02/24 | 50 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/02/24 | 50 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/02/24 | 51 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/02/24 | 51 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/02/24 | 57 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 08/02/24 | 57 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 08/02/24 | 70 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 08/02/24 | 76 | Weeks, Gregg A |  | 117.5
PR | 998 | 08/02/24 | 80 | Zuniga Avilez, Eduar A |  | 30.6
PR | 998 | 08/02/24 | 80 | Zuniga Avilez, Eduar A |  | 18.36
PR | 998 | 08/02/24 | 213 | Diaz Morales, Elber |  | -26.93
PR | 998 | 08/02/24 | 214 | McCabe, Thomas C |  | -107.71
PR | 998 | 08/02/24 | 215 | Rodriguez Arevalos, Christian |  | -19.51
PR | 998 | 08/09/24 | 244 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 08/09/24 | 244 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 08/09/24 | 246 | Paco Leyva, Orlando |  | 56
PR | 998 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 08/09/24 | 252 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 08/09/24 | 253 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/09/24 | 256 | Boss, Benjamin T |  | 93.64
PR | 998 | 08/09/24 | 256 | Boss, Benjamin T |  | 31.21
PR | 998 | 08/09/24 | 258 | Carmona, Raul O |  | 129.74
PR | 998 | 08/09/24 | 258 | Carmona, Raul O |  | 32.44
PR | 998 | 08/09/24 | 259 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 08/09/24 | 272 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 08/09/24 | 272 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/09/24 | 277 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 08/09/24 | 277 | Gochez Molina, Douglas O |  | 15.3
PR | 998 | 08/09/24 | 283 | Johnson, Jake E |  | 19.89
PR | 998 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/09/24 | 284 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 08/09/24 | 285 | Lopez, Maslin A |  | 100.98
PR | 998 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 08/09/24 | 291 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 08/09/24 | 304 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 08/09/24 | 304 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 08/09/24 | 310 | Weeks, Gregg A |  | 117.5
PR | 998 | 08/09/24 | 314 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 08/09/24 | 314 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 08/16/24 | 428 | Anderson, Richard P |  | 24.86
PR | 998 | 08/16/24 | 428 | Anderson, Richard P |  | 4.97
PR | 998 | 08/16/24 | 435 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 08/16/24 | 435 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 14
PR | 998 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 42
PR | 998 | 08/16/24 | 437 | Paco Leyva, Orlando |  | 56
PR | 998 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I |  | 104.35
PR | 998 | 08/16/24 | 443 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 08/16/24 | 444 | Barnhart, Joseph N |  | 15.61
PR | 998 | 08/16/24 | 444 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/16/24 | 444 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/16/24 | 447 | Boss, Benjamin T |  | 31.21
PR | 998 | 08/16/24 | 449 | Carmona, Raul O |  | 129.74
PR | 998 | 08/16/24 | 449 | Carmona, Raul O |  | 32.44
PR | 998 | 08/16/24 | 450 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 08/16/24 | 461 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 08/16/24 | 461 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/16/24 | 466 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 08/16/24 | 472 | Johnson, Jake E |  | 15.91
PR | 998 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/16/24 | 473 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/16/24 | 474 | Lopez, Maslin A |  | 60.59
PR | 998 | 08/16/24 | 474 | Lopez, Maslin A |  | 20.2
PR | 998 | 08/16/24 | 478 | McCabe, Thomas C |  | 53.86
PR | 998 | 08/16/24 | 480 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 08/16/24 | 480 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 08/16/24 | 492 | Silva Morales, Jair J |  | 41.62
PR | 998 | 08/16/24 | 493 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 08/16/24 | 499 | Weeks, Gregg A |  | 146.88
PR | 998 | 08/16/24 | 501 | Yohannes Jr., Samson |  | 40.39
PR | 998 | 08/16/24 | 503 | Zuniga Avilez, Eduar A |  | 61.2
PR | 998 | 08/23/24 | 690 | Anderson, Richard P |  | 9.95
PR | 998 | 08/23/24 | 690 | Anderson, Richard P |  | 52.21
PR | 998 | 08/23/24 | 697 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 88.66
PR | 998 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 56
PR | 998 | 08/23/24 | 699 | Paco Leyva, Orlando |  | 42
PR | 998 | 08/23/24 | 705 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 08/23/24 | 709 | Boss, Benjamin T |  | 31.21
PR | 998 | 08/23/24 | 709 | Boss, Benjamin T |  | 31.21
PR | 998 | 08/23/24 | 711 | Carmona, Raul O |  | 64.87
PR | 998 | 08/23/24 | 711 | Carmona, Raul O |  | 32.44
PR | 998 | 08/23/24 | 723 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 08/23/24 | 723 | Escobar Ramirez, Carlos M |  | 36.72
PR | 998 | 08/23/24 | 728 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 08/23/24 | 734 | Johnson, Jake E |  | 23.87
PR | 998 | 08/23/24 | 735 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 08/23/24 | 736 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/23/24 | 736 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 08/23/24 | 742 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 08/23/24 | 755 | Suniga Aviles, Kelvin A |  | 25.7
PR | 998 | 08/23/24 | 755 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 08/23/24 | 761 | Weeks, Gregg A |  | 29.38
PR | 998 | 08/23/24 | 761 | Weeks, Gregg A |  | 58.75
PR | 998 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 08/23/24 | 765 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 08/30/24 | 833 | Anderson, Richard P |  | 64.64
PR | 998 | 08/30/24 | 833 | Anderson, Richard P |  | 19.89
PR | 998 | 08/30/24 | 833 | Anderson, Richard P |  | 4.97
PR | 998 | 08/30/24 | 840 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 65.33
PR | 998 | 08/30/24 | 842 | Paco Leyva, Orlando |  | 42
PR | 998 | 08/30/24 | 848 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 08/30/24 | 849 | Barnhart, Joseph N |  | 15.61
PR | 998 | 08/30/24 | 852 | Boss, Benjamin T |  | 15.61
PR | 998 | 08/30/24 | 852 | Boss, Benjamin T |  | 62.42
PR | 998 | 08/30/24 | 854 | Carmona, Raul O |  | 97.31
PR | 998 | 08/30/24 | 854 | Carmona, Raul O |  | 32.44
PR | 998 | 08/30/24 | 865 | Escobar Ramirez, Carlos M |  | 36.72
PR | 998 | 08/30/24 | 865 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 08/30/24 | 870 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 08/30/24 | 876 | Johnson, Jake E |  | 11.93
PR | 998 | 08/30/24 | 877 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/30/24 | 877 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/30/24 | 878 | Lopez, Maslin A |  | 60.59
PR | 998 | 08/30/24 | 884 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 08/30/24 | 897 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 08/30/24 | 903 | Weeks, Gregg A |  | 88.13
PR | 998 | 08/30/24 | 907 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 08/30/24 | 907 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/06/24 | 9 | Anderson, Richard P |  | 9.95
PR | 998 | 09/06/24 | 9 | Anderson, Richard P |  | 4.97
PR | 998 | 09/06/24 | 9 | Anderson, Richard P |  | 9.95
PR | 998 | 09/06/24 | 16 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 42
PR | 998 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 28
PR | 998 | 09/06/24 | 18 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 09/06/24 | 24 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 09/06/24 | 25 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/06/24 | 25 | Barnhart, Joseph N |  | 20.81
PR | 998 | 09/06/24 | 28 | Boss, Benjamin T |  | 31.21
PR | 998 | 09/06/24 | 28 | Boss, Benjamin T |  | 62.42
PR | 998 | 09/06/24 | 30 | Carmona, Raul O |  | 64.87
PR | 998 | 09/06/24 | 30 | Carmona, Raul O |  | 32.44
PR | 998 | 09/06/24 | 31 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 09/06/24 | 41 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 09/06/24 | 41 | Escobar Ramirez, Carlos M |  | 24.48
PR | 998 | 09/06/24 | 47 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 09/06/24 | 53 | Johnson, Jake E |  | 15.91
PR | 998 | 09/06/24 | 54 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 09/06/24 | 55 | Lopez, Maslin A |  | 60.59
PR | 998 | 09/06/24 | 61 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 09/06/24 | 61 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 09/06/24 | 74 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 09/06/24 | 80 | Weeks, Gregg A |  | 88.13
PR | 998 | 09/06/24 | 84 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/06/24 | 84 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 09/13/24 | 217 | Anderson, Richard P |  | 22.38
PR | 998 | 09/13/24 | 217 | Anderson, Richard P |  | 4.97
PR | 998 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 09/13/24 | 224 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 09/13/24 | 226 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 09/13/24 | 232 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 15.61
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/13/24 | 236 | Boss, Benjamin T |  | 156.06
PR | 998 | 09/13/24 | 238 | Carmona, Raul O |  | 129.74
PR | 998 | 09/13/24 | 239 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 09/13/24 | 249 | Escobar Ramirez, Carlos M |  | 36.72
PR | 998 | 09/13/24 | 249 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 09/13/24 | 255 | Gochez Molina, Douglas O |  | 22.95
PR | 998 | 09/13/24 | 255 | Gochez Molina, Douglas O |  | 7.65
PR | 998 | 09/13/24 | 261 | Johnson, Jake E |  | 3.98
PR | 998 | 09/13/24 | 262 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 09/13/24 | 263 | Lopez, Maslin A |  | 98.46
PR | 998 | 09/13/24 | 268 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 9.64
PR | 998 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 16.07
PR | 998 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 16.07
PR | 998 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 3.21
PR | 998 | 09/13/24 | 281 | Suniga Aviles, Kelvin A |  | 6.43
PR | 998 | 09/13/24 | 287 | Weeks, Gregg A |  | 88.13
PR | 998 | 09/13/24 | 287 | Weeks, Gregg A |  | 29.38
PR | 998 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 6.12
PR | 998 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 09/13/24 | 291 | Zuniga Avilez, Eduar A |  | 6.12
PR | 998 | 09/20/24 | 389 | Anderson, Richard P |  | 24.86
PR | 998 | 09/20/24 | 390 | Barnhart, Thomas L |  | 21.38
PR | 998 | 09/20/24 | 393 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 09/20/24 | 396 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 14
PR | 998 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 09/20/24 | 398 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 09/20/24 | 404 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 09/20/24 | 405 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/20/24 | 405 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/20/24 | 405 | Barnhart, Joseph N |  | 26.01
PR | 998 | 09/20/24 | 408 | Boss, Benjamin T |  | 156.06
PR | 998 | 09/20/24 | 410 | Carmona, Raul O |  | 64.87
PR | 998 | 09/20/24 | 410 | Carmona, Raul O |  | 64.87
PR | 998 | 09/20/24 | 411 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 09/20/24 | 421 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 09/20/24 | 421 | Escobar Ramirez, Carlos M |  | 36.72
PR | 998 | 09/20/24 | 426 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 09/20/24 | 432 | Johnson, Jake E |  | 3.98
PR | 998 | 09/20/24 | 433 | Lima Romero, Melvin A |  | 67.32
PR | 998 | 09/20/24 | 433 | Lima Romero, Melvin A |  | 40.39
PR | 998 | 09/20/24 | 434 | Lopez, Maslin A |  | 20.2
PR | 998 | 09/20/24 | 434 | Lopez, Maslin A |  | 60.59
PR | 998 | 09/20/24 | 439 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 19.28
PR | 998 | 09/20/24 | 452 | Suniga Aviles, Kelvin A |  | 19.28
PR | 998 | 09/20/24 | 458 | Weeks, Gregg A |  | 117.5
PR | 998 | 09/20/24 | 458 | Weeks, Gregg A |  | 29.38
PR | 998 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/20/24 | 462 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/27/24 | 525 | Anderson, Richard P |  | 4.97
PR | 998 | 09/27/24 | 525 | Anderson, Richard P |  | 4.97
PR | 998 | 09/27/24 | 525 | Anderson, Richard P |  | 9.95
PR | 998 | 09/27/24 | 529 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 09/27/24 | 532 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 84
PR | 998 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 56
PR | 998 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 09/27/24 | 535 | Paco Leyva, Orlando |  | 4.67
PR | 998 | 09/27/24 | 541 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 09/27/24 | 542 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/27/24 | 544 | Boss, Benjamin T |  | 156.06
PR | 998 | 09/27/24 | 546 | Carmona, Raul O |  | 64.87
PR | 998 | 09/27/24 | 546 | Carmona, Raul O |  | 64.87
PR | 998 | 09/27/24 | 557 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 09/27/24 | 562 | Gochez Molina, Douglas O |  | 15.3
PR | 998 | 09/27/24 | 568 | Johnson, Jake E |  | 3.98
PR | 998 | 09/27/24 | 569 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 09/27/24 | 569 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 09/27/24 | 570 | Lopez, Maslin A |  | 20.2
PR | 998 | 09/27/24 | 570 | Lopez, Maslin A |  | 60.59
PR | 998 | 09/27/24 | 575 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 09/27/24 | 575 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 09/27/24 | 588 | Suniga Aviles, Kelvin A |  | 32.13
PR | 998 | 09/27/24 | 588 | Suniga Aviles, Kelvin A |  | 19.28
PR | 998 | 09/27/24 | 594 | Weeks, Gregg A |  | 88.13
PR | 998 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 24.48
PR | 998 | 09/27/24 | 598 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 10/04/24 | 9 | Anderson, Richard P |  | 4.97
PR | 998 | 10/04/24 | 9 | Anderson, Richard P |  | 9.95
PR | 998 | 10/04/24 | 9 | Anderson, Richard P |  | 9.95
PR | 998 | 10/04/24 | 13 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 10/04/24 | 16 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 56
PR | 998 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 42
PR | 998 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 42
PR | 998 | 10/04/24 | 19 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/04/24 | 25 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 10/04/24 | 26 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/04/24 | 28 | Boss, Benjamin T |  | 156.06
PR | 998 | 10/04/24 | 30 | Carmona, Raul O |  | 129.74
PR | 998 | 10/04/24 | 30 | Carmona, Raul O |  | 32.44
PR | 998 | 10/04/24 | 41 | Escobar Ramirez, Carlos M |  | 48.96
PR | 998 | 10/04/24 | 42 | Games, Jordan M |  | 129.74
PR | 998 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/04/24 | 52 | Johnson, Jake E |  | 7.96
PR | 998 | 10/04/24 | 53 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 10/04/24 | 54 | Lopez, Maslin A |  | 20.2
PR | 998 | 10/04/24 | 54 | Lopez, Maslin A |  | 60.59
PR | 998 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 12.55
PR | 998 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 12.55
PR | 998 | 10/04/24 | 59 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 10/04/24 | 72 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 10/04/24 | 78 | Weeks, Gregg A |  | 146.88
PR | 998 | 10/04/24 | 79 | Wilson, Garret A |  | 12.39
PR | 998 | 10/04/24 | 79 | Wilson, Garret A |  | 28.92
PR | 998 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 36.72
PR | 998 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 10/04/24 | 82 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 10/11/24 | 216 | Anderson, Richard P |  | 14.92
PR | 998 | 10/11/24 | 217 | Barnhart, Thomas L |  | 62.5
PR | 998 | 10/11/24 | 220 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 10/11/24 | 223 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 65.33
PR | 998 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 10/11/24 | 226 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 10/11/24 | 232 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/11/24 | 235 | Boss, Benjamin T |  | 156.06
PR | 998 | 10/11/24 | 237 | Carmona, Raul O |  | 97.31
PR | 998 | 10/11/24 | 237 | Carmona, Raul O |  | 32.44
PR | 998 | 10/11/24 | 237 | Carmona, Raul O |  | 32.44
PR | 998 | 10/11/24 | 248 | Escobar Ramirez, Carlos M |  | 12.24
PR | 998 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/11/24 | 259 | Johnson, Jake E |  | 7.96
PR | 998 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 10/11/24 | 260 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 10/11/24 | 261 | Lopez, Maslin A |  | 60.59
PR | 998 | 10/11/24 | 266 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 10/11/24 | 266 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 10/11/24 | 284 | Weeks, Gregg A |  | 88.13
PR | 998 | 10/18/24 | 414 | Gochez Molina, Douglas O |  | -15.3
PR | 998 | 10/18/24 | 414 | Gochez Molina, Douglas O |  | -45.9
PR | 998 | 10/18/24 | 415 | McCabe, Thomas C |  | -53.86
PR | 998 | 10/18/24 | 418 | Wilson, Garret A |  | -12.39
PR | 998 | 10/18/24 | 418 | Wilson, Garret A |  | -28.92
PR | 998 | 10/18/24 | 428 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 10/18/24 | 428 | Lima Romero, Melvin A |  | -53.86
PR | 998 | 10/18/24 | 429 | Anderson, Richard P |  | 14.92
PR | 998 | 10/18/24 | 429 | Anderson, Richard P |  | 9.95
PR | 998 | 10/18/24 | 433 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 10/18/24 | 436 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 56
PR | 998 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 4.67
PR | 998 | 10/18/24 | 439 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/18/24 | 445 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/18/24 | 448 | Boss, Benjamin T |  | 15.61
PR | 998 | 10/18/24 | 448 | Boss, Benjamin T |  | -15.61
PR | 998 | 10/18/24 | 448 | Boss, Benjamin T |  | 62.42
PR | 998 | 10/18/24 | 450 | Carmona, Raul O |  | 113.53
PR | 998 | 10/18/24 | 450 | Carmona, Raul O |  | 16.22
PR | 998 | 10/18/24 | 450 | Carmona, Raul O |  | 32.44
PR | 998 | 10/18/24 | 460 | Eliassen, Cory H |  | 98.84
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/18/24 | 471 | Johnson, Jake E |  | 3.98
PR | 998 | 10/18/24 | 472 | Lopez, Maslin A |  | 80.78
PR | 998 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 12.55
PR | 998 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 10/18/24 | 477 | Mendoza Morales, Jesus A |  | 12.55
PR | 998 | 10/18/24 | 496 | Weeks, Gregg A |  | 146.88
PR | 998 | 10/25/24 | 577 | Anderson, Richard P |  | 89.51
PR | 998 | 10/25/24 | 577 | Anderson, Richard P |  | 4.97
PR | 998 | 10/25/24 | 581 | Cruz Reyes, Jose |  | 119.19
PR | 998 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 86.75
PR | 998 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 9.64
PR | 998 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 6.43
PR | 998 | 10/25/24 | 584 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 116.66
PR | 998 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 42
PR | 998 | 10/25/24 | 587 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 10/25/24 | 593 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 10/25/24 | 594 | Barnhart, Joseph N |  | 13.01
PR | 998 | 10/25/24 | 594 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/25/24 | 594 | Barnhart, Joseph N |  | 2.6
PR | 998 | 10/25/24 | 597 | Carmona, Raul O |  | 81.09
PR | 998 | 10/25/24 | 597 | Carmona, Raul O |  | 81.09
PR | 998 | 10/25/24 | 607 | Eliassen, Cory H |  | 69.77
PR | 998 | 10/25/24 | 608 | Games, Jordan M |  | 129.74
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 10/25/24 | 618 | Johnson, Jake E |  | 3.98
PR | 998 | 10/25/24 | 619 | Lopez, Maslin A |  | 40.39
PR | 998 | 10/25/24 | 619 | Lopez, Maslin A |  | 20.2
PR | 998 | 10/25/24 | 619 | Lopez, Maslin A |  | 20.2
PR | 998 | 10/25/24 | 624 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 10/25/24 | 624 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 10/25/24 | 643 | Weeks, Gregg A |  | 117.5
PR | 998 | 11/01/24 | 6 | Anderson, Richard P |  | 79.56
PR | 998 | 11/01/24 | 10 | Cruz Reyes, Jose |  | 50.18
PR | 998 | 11/01/24 | 13 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/01/24 | 13 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/01/24 | 16 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 11/01/24 | 16 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/01/24 | 22 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/01/24 | 23 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/01/24 | 26 | Carmona, Raul O |  | 64.87
PR | 998 | 11/01/24 | 26 | Carmona, Raul O |  | 97.31
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/01/24 | 47 | Johnson, Jake E |  | 7.96
PR | 998 | 11/01/24 | 48 | Lopez, Maslin A |  | 20.2
PR | 998 | 11/01/24 | 48 | Lopez, Maslin A |  | 60.59
PR | 998 | 11/01/24 | 53 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 11/01/24 | 53 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 11/08/24 | 126 | Anderson, Richard P |  | 14.92
PR | 998 | 11/08/24 | 126 | Anderson, Richard P |  | 9.95
PR | 998 | 11/08/24 | 128 | Castro, Marcus J |  | 12.24
PR | 998 | 11/08/24 | 130 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 11/08/24 | 133 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/08/24 | 133 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 84
PR | 998 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 14
PR | 998 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 28
PR | 998 | 11/08/24 | 136 | Paco Leyva, Orlando |  | 28
PR | 998 | 11/08/24 | 139 | Aquino, Juan |  | 16.52
PR | 998 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 11/08/24 | 142 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/08/24 | 143 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/08/24 | 143 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/08/24 | 146 | Carmona, Raul O |  | 64.87
PR | 998 | 11/08/24 | 146 | Carmona, Raul O |  | 64.87
PR | 998 | 11/08/24 | 146 | Carmona, Raul O |  | 32.44
PR | 998 | 11/08/24 | 156 | Eliassen, Cory H |  | 69.77
PR | 998 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/08/24 | 167 | Johnson, Jake E |  | 15.91
PR | 998 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 11/08/24 | 168 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 11/08/24 | 169 | Lopez, Maslin A |  | 60.59
PR | 998 | 11/08/24 | 174 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 11/08/24 | 187 | Suniga Aviles, Kelvin A |  | 12.85
PR | 998 | 11/08/24 | 197 | Zuniga Avilez, Eduar A |  | 12.24
PR | 998 | 11/15/24 | 346 | Anderson, Richard P |  | 14.92
PR | 998 | 11/15/24 | 350 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/15/24 | 353 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 51.33
PR | 998 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 14
PR | 998 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 56
PR | 998 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 11/15/24 | 356 | Paco Leyva, Orlando |  | 4.67
PR | 998 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/15/24 | 362 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/15/24 | 366 | Carmona, Raul O |  | 64.87
PR | 998 | 11/15/24 | 366 | Carmona, Raul O |  | 32.44
PR | 998 | 11/15/24 | 366 | Carmona, Raul O |  | 64.87
PR | 998 | 11/15/24 | 376 | Eliassen, Cory H |  | 37.79
PR | 998 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 11/15/24 | 387 | Johnson, Jake E |  | 11.93
PR | 998 | 11/15/24 | 388 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 11/15/24 | 388 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 11/15/24 | 389 | Lopez, Maslin A |  | 20.2
PR | 998 | 11/15/24 | 389 | Lopez, Maslin A |  | 40.39
PR | 998 | 11/15/24 | 389 | Lopez, Maslin A |  | 20.2
PR | 998 | 11/15/24 | 394 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 11/22/24 | 501 | Anderson, Richard P |  | 24.86
PR | 998 | 11/22/24 | 505 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/22/24 | 508 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 56
PR | 998 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 11/22/24 | 511 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/22/24 | 517 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/22/24 | 518 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/22/24 | 518 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/22/24 | 521 | Carmona, Raul O |  | 64.87
PR | 998 | 11/22/24 | 521 | Carmona, Raul O |  | 64.87
PR | 998 | 11/22/24 | 531 | Eliassen, Cory H |  | 69.77
PR | 998 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 11/22/24 | 543 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 11/22/24 | 544 | Lopez, Maslin A |  | 40.39
PR | 998 | 11/22/24 | 544 | Lopez, Maslin A |  | 20.2
PR | 998 | 11/22/24 | 549 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 11/22/24 | 565 | Trower-Kelly, Fidel D |  | 94.86
PR | 998 | 11/29/24 | 648 | Johnson, Jake E |  | 3.98
PR | 998 | 11/29/24 | 649 | Anderson, Richard P |  | 29.84
PR | 998 | 11/29/24 | 649 | Anderson, Richard P |  | 14.92
PR | 998 | 11/29/24 | 649 | Anderson, Richard P |  | 7.46
PR | 998 | 11/29/24 | 653 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 11/29/24 | 656 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 11/29/24 | 659 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 11/29/24 | 663 | Araque, Mario W |  | 67.32
PR | 998 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 11/29/24 | 665 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 11/29/24 | 666 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/29/24 | 669 | Carmona, Raul O |  | 32.44
PR | 998 | 11/29/24 | 669 | Carmona, Raul O |  | 32.44
PR | 998 | 11/29/24 | 669 | Carmona, Raul O |  | 32.44
PR | 998 | 11/29/24 | 669 | Carmona, Raul O |  | 32.44
PR | 998 | 11/29/24 | 679 | Eliassen, Cory H |  | 61.05
PR | 998 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/29/24 | 690 | Johnson, Jake E |  | 7.96
PR | 998 | 11/29/24 | 691 | Lima Romero, Melvin A |  | 13.46
PR | 998 | 11/29/24 | 691 | Lima Romero, Melvin A |  | 13.46
PR | 998 | 11/29/24 | 697 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 11/29/24 | 713 | Trower-Kelly, Fidel D |  | 37.94
PR | 998 | 12/06/24 | 51 | Anderson, Richard P |  | 9.95
PR | 998 | 12/06/24 | 55 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 12/06/24 | 58 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 12/06/24 | 61 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 12/06/24 | 65 | Araque, Mario W |  | 40.39
PR | 998 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 13.46
PR | 998 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 13.46
PR | 998 | 12/06/24 | 67 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 12/06/24 | 71 | Carmona, Raul O |  | 48.65
PR | 998 | 12/06/24 | 71 | Carmona, Raul O |  | 32.44
PR | 998 | 12/06/24 | 71 | Carmona, Raul O |  | 16.22
PR | 998 | 12/06/24 | 73 | Chastain, Aaron R |  | 4.82
PR | 998 | 12/06/24 | 81 | Eliassen, Cory H |  | 69.77
PR | 998 | 12/06/24 | 82 | Games, Jordan M |  | 12.16
PR | 998 | 12/06/24 | 92 | Johnson, Jake E |  | 3.98
PR | 998 | 12/06/24 | 99 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 12/06/24 | 114 | Trower-Kelly, Fidel D |  | 37.94
PR | 998 | 12/13/24 | 235 | Anderson, Richard P |  | 9.95
PR | 998 | 12/13/24 | 235 | Anderson, Richard P |  | 14.92
PR | 998 | 12/13/24 | 235 | Anderson, Richard P |  | 9.95
PR | 998 | 12/13/24 | 236 | Barnhart, Thomas L |  | 52.63
PR | 998 | 12/13/24 | 238 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 12/13/24 | 241 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 46.67
PR | 998 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 12/13/24 | 243 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 12/13/24 | 247 | Araque, Mario W |  | 40.39
PR | 998 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 12/13/24 | 249 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 12/13/24 | 250 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/13/24 | 253 | Carmona, Raul O |  | 64.87
PR | 998 | 12/13/24 | 253 | Carmona, Raul O |  | 32.44
PR | 998 | 12/13/24 | 253 | Carmona, Raul O |  | 32.44
PR | 998 | 12/13/24 | 255 | Chastain, Aaron R |  | 20.88
PR | 998 | 12/13/24 | 263 | Eliassen, Cory H |  | 63.95
PR | 998 | 12/13/24 | 264 | Games, Jordan M |  | 60.82
PR | 998 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/13/24 | 274 | Johnson, Jake E |  | 3.98
PR | 998 | 12/13/24 | 276 | Lopez, Maslin A |  | 20.2
PR | 998 | 12/13/24 | 281 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 12/13/24 | 296 | Trower-Kelly, Fidel D |  | 56.92
PR | 998 | 12/20/24 | 422 | Anderson, Richard P |  | 9.95
PR | 998 | 12/20/24 | 422 | Anderson, Richard P |  | 4.97
PR | 998 | 12/20/24 | 425 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 12/20/24 | 428 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 12/20/24 | 428 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 56
PR | 998 | 12/20/24 | 430 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 12/20/24 | 434 | Araque, Mario W |  | 40.39
PR | 998 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 12/20/24 | 436 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 15.61
PR | 998 | 12/20/24 | 440 | Carmona, Raul O |  | 97.31
PR | 998 | 12/20/24 | 440 | Carmona, Raul O |  | 32.44
PR | 998 | 12/20/24 | 442 | Chastain, Aaron R |  | 19.28
PR | 998 | 12/20/24 | 449 | Eliassen, Cory H |  | 69.77
PR | 998 | 12/20/24 | 450 | Games, Jordan M |  | 68.93
PR | 998 | 12/20/24 | 460 | Johnson, Jake E |  | 11.93
PR | 998 | 12/20/24 | 467 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 12/20/24 | 483 | Trower-Kelly, Fidel D |  | 56.92
PR | 998 | 12/27/24 | 539 | Anderson, Richard P |  | 4.97
PR | 998 | 12/27/24 | 543 | Cruz Reyes, Jose |  | 50.18
PR | 998 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 12/27/24 | 546 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 12/27/24 | 548 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 12/27/24 | 548 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 12/27/24 | 553 | Araque, Mario W |  | 26.93
PR | 998 | 12/27/24 | 555 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 12/27/24 | 559 | Carmona, Raul O |  | 32.44
PR | 998 | 12/27/24 | 559 | Carmona, Raul O |  | 32.44
PR | 998 | 12/27/24 | 559 | Carmona, Raul O |  | 32.44
PR | 998 | 12/27/24 | 561 | Chastain, Aaron R |  | 25.7
PR | 998 | 12/27/24 | 568 | Eliassen, Cory H |  | 42.15
PR | 998 | 12/27/24 | 569 | Games, Jordan M |  | 64.87
PR | 998 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/27/24 | 579 | Johnson, Jake E |  | 3.98
PR | 998 | 12/27/24 | 599 | Trower-Kelly, Fidel D |  | 37.94
PR | 998 | 01/03/25 | 16 | Cruz Reyes, Jose |  | 50.18
PR | 998 | 01/03/25 | 19 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 01/03/25 | 25 | Araque, Mario W |  | 26.93
PR | 998 | 01/03/25 | 27 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 01/03/25 | 32 | Chastain, Aaron R |  | 25.7
PR | 998 | 01/03/25 | 37 | Draves, Steven W |  | 16.83
PR | 998 | 01/03/25 | 39 | Eliassen, Cory H |  | 23.26
PR | 998 | 01/03/25 | 40 | Games, Jordan M |  | 87.17
PR | 998 | 01/03/25 | 49 | Johnson, Jake E |  | 3.98
PR | 998 | 01/03/25 | 67 | Trower-Kelly, Fidel D |  | 37.94
PR | 998 | 01/10/25 | 174 | Anderson, Richard P |  | 2.49
PR | 998 | 01/10/25 | 174 | Anderson, Richard P |  | 4.97
PR | 998 | 01/10/25 | 174 | Anderson, Richard P |  | 32.32
PR | 998 | 01/10/25 | 175 | Barnhart, Thomas L |  | 26.32
PR | 998 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 01/10/25 | 181 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 01/10/25 | 183 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 01/10/25 | 189 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 01/10/25 | 190 | Barnhart, Joseph N |  | 15.61
PR | 998 | 01/10/25 | 190 | Barnhart, Joseph N |  | 31.21
PR | 998 | 01/10/25 | 190 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/10/25 | 194 | Chastain, Aaron R |  | 28.15
PR | 998 | 01/10/25 | 203 | Games, Jordan M |  | 125.69
PR | 998 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/10/25 | 212 | Johnson, Jake E |  | 3.98
PR | 998 | 01/17/25 | 339 | Anderson, Richard P |  | 9.95
PR | 998 | 01/17/25 | 340 | Barnhart, Thomas L |  | 52.63
PR | 998 | 01/17/25 | 342 | Cosentino, Brandon C |  | 58.75
PR | 998 | 01/17/25 | 346 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 01/17/25 | 346 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 01/17/25 | 354 | Barnhart, Joseph N |  | 20.81
PR | 998 | 01/17/25 | 354 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/17/25 | 354 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/17/25 | 358 | Chastain, Aaron R |  | 70.38
PR | 998 | 01/17/25 | 366 | Games, Jordan M |  | 145.96
PR | 998 | 01/17/25 | 375 | Johnson, Jake E |  | 3.98
PR | 998 | 01/17/25 | 381 | Mendoza Morales, Jesus A |  | 25.09
PR | 998 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 84
PR | 998 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 56
PR | 998 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 01/17/25 | 384 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/17/25 | 395 | Trower-Kelly, Fidel D |  | 18.97
PR | 998 | 01/24/25 | 506 | Barnhart, Thomas L |  | 26.32
PR | 998 | 01/24/25 | 508 | Cosentino, Brandon C |  | 73.44
PR | 998 | 01/24/25 | 512 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 01/24/25 | 512 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/24/25 | 524 | Chastain, Aaron R |  | 70.38
PR | 998 | 01/24/25 | 533 | Games, Jordan M |  | 162.18
PR | 998 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 56
PR | 998 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 01/24/25 | 551 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/24/25 | 562 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 01/24/25 | 611 | Johnson, Jake E |  | 3.98
PR | 998 | 01/31/25 | 700 | Cosentino, Brandon C |  | 73.44
PR | 998 | 01/31/25 | 704 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 01/31/25 | 704 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 15.61
PR | 998 | 01/31/25 | 716 | Chastain, Aaron R |  | 56.3
PR | 998 | 01/31/25 | 725 | Games, Jordan M |  | 154.07
PR | 998 | 01/31/25 | 734 | Johnson, Jake E |  | 3.98
PR | 998 | 01/31/25 | 736 | Lopez, Maslin A |  | 60.59
PR | 998 | 01/31/25 | 736 | Lopez, Maslin A |  | 10.1
PR | 998 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 56
PR | 998 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 01/31/25 | 743 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 01/31/25 | 753 | Trower-Kelly, Fidel D |  | 94.86
PR | 998 | 02/07/25 | 31 | Cosentino, Brandon C |  | 44.06
PR | 998 | 02/07/25 | 42 | Barnhart, Joseph N |  | 5.2
PR | 998 | 02/07/25 | 42 | Barnhart, Joseph N |  | 5.2
PR | 998 | 02/07/25 | 42 | Barnhart, Joseph N |  | 5.2
PR | 998 | 02/07/25 | 42 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/07/25 | 46 | Chastain, Aaron R |  | 63.34
PR | 998 | 02/07/25 | 55 | Games, Jordan M |  | 145.96
PR | 998 | 02/07/25 | 64 | Johnson, Jake E |  | 15.91
PR | 998 | 02/07/25 | 66 | Lopez, Maslin A |  | 30.29
PR | 998 | 02/07/25 | 66 | Lopez, Maslin A |  | 30.29
PR | 998 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 56
PR | 998 | 02/07/25 | 73 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 02/07/25 | 84 | Trower-Kelly, Fidel D |  | 92.49
PR | 998 | 02/14/25 | 194 | Anderson, Richard P |  | 9.95
PR | 998 | 02/14/25 | 194 | Anderson, Richard P |  | 4.97
PR | 998 | 02/14/25 | 197 | Cosentino, Brandon C |  | 58.75
PR | 998 | 02/14/25 | 208 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/14/25 | 208 | Barnhart, Joseph N |  | 15.61
PR | 998 | 02/14/25 | 212 | Chastain, Aaron R |  | 70.38
PR | 998 | 02/14/25 | 221 | Games, Jordan M |  | 129.74
PR | 998 | 02/14/25 | 230 | Johnson, Jake E |  | 11.93
PR | 998 | 02/14/25 | 232 | Lopez, Maslin A |  | 40.39
PR | 998 | 02/14/25 | 232 | Lopez, Maslin A |  | 30.29
PR | 998 | 02/14/25 | 232 | Lopez, Maslin A |  | 30.29
PR | 998 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 65.33
PR | 998 | 02/14/25 | 239 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 02/14/25 | 242 | Reed, Reuben H |  | 75.89
PR | 998 | 02/14/25 | 250 | Trower-Kelly, Fidel D |  | 56.92
PR | 998 | 02/21/25 | 311 | Anderson, Richard P |  | 4.97
PR | 998 | 02/21/25 | 314 | Cosentino, Brandon C |  | 73.44
PR | 998 | 02/21/25 | 326 | Barnhart, Joseph N |  | 7.8
PR | 998 | 02/21/25 | 326 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/21/25 | 326 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/21/25 | 330 | Chastain, Aaron R |  | 70.38
PR | 998 | 02/21/25 | 338 | Eliassen, Cory H |  | 93.02
PR | 998 | 02/21/25 | 339 | Games, Jordan M |  | 162.18
PR | 998 | 02/21/25 | 348 | Johnson, Jake E |  | 15.91
PR | 998 | 02/21/25 | 350 | Lopez, Maslin A |  | 40.39
PR | 998 | 02/21/25 | 350 | Lopez, Maslin A |  | 40.39
PR | 998 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 56
PR | 998 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 28
PR | 998 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 56
PR | 998 | 02/21/25 | 357 | Paco Leyva, Orlando |  | 42
PR | 998 | 02/21/25 | 368 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 02/28/25 | 504 | Cosentino, Brandon C |  | 58.75
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 2.6
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/28/25 | 520 | Chastain, Aaron R |  | 56.3
PR | 998 | 02/28/25 | 528 | Eliassen, Cory H |  | 69.77
PR | 998 | 02/28/25 | 529 | Games, Jordan M |  | 162.18
PR | 998 | 02/28/25 | 538 | Johnson, Jake E |  | 11.93
PR | 998 | 02/28/25 | 540 | Lopez, Maslin A |  | 10.1
PR | 998 | 02/28/25 | 540 | Lopez, Maslin A |  | 20.2
PR | 998 | 02/28/25 | 540 | Lopez, Maslin A |  | 40.39
PR | 998 | 02/28/25 | 540 | Lopez, Maslin A |  | 10.1
PR | 998 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 42
PR | 998 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 86.33
PR | 998 | 02/28/25 | 547 | Paco Leyva, Orlando |  | 56
PR | 998 | 02/28/25 | 558 | Trower-Kelly, Fidel D |  | 74.7
PR | 998 | 03/07/25 | 17 | Cosentino, Brandon C |  | 69.77
PR | 998 | 03/07/25 | 29 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/07/25 | 33 | Chastain, Aaron R |  | 65.1
PR | 998 | 03/07/25 | 41 | Eliassen, Cory H |  | 107.56
PR | 998 | 03/07/25 | 42 | Games, Jordan M |  | 162.18
PR | 998 | 03/07/25 | 51 | Johnson, Jake E |  | 7.96
PR | 998 | 03/07/25 | 53 | Lopez, Maslin A |  | 50.49
PR | 998 | 03/07/25 | 53 | Lopez, Maslin A |  | 17.67
PR | 998 | 03/07/25 | 53 | Lopez, Maslin A |  | 32.82
PR | 998 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 102.66
PR | 998 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 03/07/25 | 60 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 03/07/25 | 71 | Trower-Kelly, Fidel D |  | 68.77
PR | 998 | 03/07/25 | 99 | Lopez, Maslin A |  | 10.1
PR | 998 | 03/14/25 | 217 | Cosentino, Brandon C |  | 44.06
PR | 998 | 03/14/25 | 233 | Chastain, Aaron R |  | 70.38
PR | 998 | 03/14/25 | 241 | Eliassen, Cory H |  | 93.02
PR | 998 | 03/14/25 | 242 | Games, Jordan M |  | 129.74
PR | 998 | 03/14/25 | 251 | Johnson, Jake E |  | 3.98
PR | 998 | 03/14/25 | 253 | Lopez, Maslin A |  | 20.2
PR | 998 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 42
PR | 998 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 03/14/25 | 271 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 03/14/25 | 275 | Wilson, Garret A |  | 20.66
PR | 998 | 03/14/25 | 400 | Cosentino, Brandon C |  | 29.38
PR | 998 | 03/14/25 | 401 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 03/14/25 | 410 | Cosentino, Brandon C |  | -29.38
PR | 998 | 03/14/25 | 411 | Cruz Reyes, Jose |  | -25.09
PR | 998 | 03/21/25 | 422 | Barnhart, Joseph N |  | 23.41
PR | 998 | 03/21/25 | 422 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/21/25 | 426 | Chastain, Aaron R |  | 42.23
PR | 998 | 03/21/25 | 434 | Eliassen, Cory H |  | 93.02
PR | 998 | 03/21/25 | 435 | Games, Jordan M |  | 154.07
PR | 998 | 03/21/25 | 465 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 03/21/25 | 476 | Cosentino, Brandon C |  | 29.38
PR | 998 | 03/28/25 | 565 | Cosentino, Brandon C |  | 37.64
PR | 998 | 03/28/25 | 577 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/28/25 | 581 | Chastain, Aaron R |  | 42.23
PR | 998 | 03/28/25 | 589 | Eliassen, Cory H |  | 79.22
PR | 998 | 03/28/25 | 590 | Games, Jordan M |  | 97.31
PR | 998 | 03/28/25 | 600 | Johnson, Jake E |  | 15.91
PR | 998 | 03/28/25 | 610 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 03/28/25 | 622 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 04/04/25 | 8 | Cosentino, Brandon C |  | 73.44
PR | 998 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 19.28
PR | 998 | 04/04/25 | 24 | Chastain, Aaron R |  | 70.38
PR | 998 | 04/04/25 | 32 | Eliassen, Cory H |  | 93.02
PR | 998 | 04/04/25 | 33 | Games, Jordan M |  | 141.91
PR | 998 | 04/04/25 | 43 | Johnson, Jake E |  | 11.93
PR | 998 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 32.67
PR | 998 | 04/04/25 | 65 | Trower-Kelly, Fidel D |  | 75.89
PR | 998 | 04/04/25 | 104 | Wilson, Garret A |  | -20.66
PR | 998 | 04/11/25 | 171 | Cosentino, Brandon C |  | 73.44
PR | 998 | 04/11/25 | 204 | Chastain, Aaron R |  | 68.62
PR | 998 | 04/11/25 | 210 | Draves, Steven W |  | 67.32
PR | 998 | 04/11/25 | 212 | Eliassen, Cory H |  | 69.77
PR | 998 | 04/11/25 | 213 | Games, Jordan M |  | 162.18
PR | 998 | 04/11/25 | 245 | Trower-Kelly, Fidel D |  | 94.86
PR | 998 | 04/18/25 | 409 | Anderson, Richard P |  | 14.92
PR | 998 | 04/18/25 | 409 | Anderson, Richard P |  | 19.89
PR | 998 | 04/18/25 | 411 | Castro, Marcus J |  | 15.15
PR | 998 | 04/18/25 | 412 | Cosentino, Brandon C |  | 58.75
PR | 998 | 04/18/25 | 412 | Cosentino, Brandon C |  | 11.02
PR | 998 | 04/18/25 | 413 | Cruz Reyes, Jose |  | 28.23
PR | 998 | 04/18/25 | 416 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 14
PR | 998 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 18.67
PR | 998 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A |  | 35.11
PR | 998 | 04/18/25 | 422 | Ascencio, Jose L |  | 28.92
PR | 998 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I |  | 30.29
PR | 998 | 04/18/25 | 424 | Barnhart, Joseph N |  | 31.21
PR | 998 | 04/18/25 | 424 | Barnhart, Joseph N |  | 10.4
PR | 998 | 04/18/25 | 424 | Barnhart, Joseph N |  | 10.4
PR | 998 | 04/18/25 | 426 | Carmona, Raul O |  | 36.49
PR | 998 | 04/18/25 | 428 | Chastain, Aaron R |  | 65.98
PR | 998 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 26.16
PR | 998 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 04/18/25 | 436 | Eliassen, Cory H |  | 69.77
PR | 998 | 04/18/25 | 436 | Eliassen, Cory H |  | 17.44
PR | 998 | 04/18/25 | 437 | Games, Jordan M |  | 60.82
PR | 998 | 04/18/25 | 437 | Games, Jordan M |  | 162.18
PR | 998 | 04/18/25 | 439 | Gerard, Jordan E |  | 41.31
PR | 998 | 04/18/25 | 441 | Gochez Molina, Douglas O |  | 17.21
PR | 998 | 04/18/25 | 443 | Goodwin, Marcus A |  | 17.21
PR | 998 | 04/18/25 | 447 | Johnson, Jake E |  | 11.93
PR | 998 | 04/18/25 | 449 | Lopez, Maslin A |  | 15.15
PR | 998 | 04/18/25 | 453 | Melgar Moz, Brandon |  | 15.15
PR | 998 | 04/18/25 | 454 | Mendoza Morales, Jesus A |  | 28.23
PR | 998 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 14
PR | 998 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 04/18/25 | 458 | Perez Araque, Manuel A |  | 17.21
PR | 998 | 04/18/25 | 459 | Portillo Soriano, Walter A |  | 24.1
PR | 998 | 04/18/25 | 462 | Rodriguez Arevalos, Christian |  | 35.11
PR | 998 | 04/18/25 | 466 | Suniga Aviles, Kelvin A |  | 14.46
PR | 998 | 04/18/25 | 468 | Taylor, Evan R |  | 23.87
PR | 998 | 04/18/25 | 469 | Trower-Kelly, Fidel D |  | 21.34
PR | 998 | 04/18/25 | 469 | Trower-Kelly, Fidel D |  | 94.86
PR | 998 | 04/18/25 | 473 | Yohannes Jr., Samson |  | 15.15
PR | 998 | 04/18/25 | 475 | Zuniga Avilez, Eduar A |  | 15.15
PR | 998 | 04/25/25 | 551 | Cosentino, Brandon C |  | 58.75
PR | 998 | 04/25/25 | 555 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 04/25/25 | 560 | Araque, Mario W |  | 15.15
PR | 998 | 04/25/25 | 563 | Barnhart, Joseph N |  | 26.01
PR | 998 | 04/25/25 | 563 | Barnhart, Joseph N |  | 5.2
PR | 998 | 04/25/25 | 567 | Chastain, Aaron R |  | 56.3
PR | 998 | 04/25/25 | 575 | Eliassen, Cory H |  | 69.77
PR | 998 | 04/25/25 | 576 | Games, Jordan M |  | 97.31
PR | 998 | 04/25/25 | 586 | Johnson, Jake E |  | 3.98
PR | 998 | 04/25/25 | 596 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 04/25/25 | 602 | Romero Garza, Jesus I |  | 22.72
PR | 998 | 04/25/25 | 608 | Trower-Kelly, Fidel D |  | 56.92
PR | 998 | 05/02/25 | 5 | Cosentino, Brandon C |  | 14.69
PR | 998 | 05/02/25 | 21 | Chastain, Aaron R |  | 14.08
PR | 998 | 05/02/25 | 29 | Eliassen, Cory H |  | 23.26
PR | 998 | 05/02/25 | 30 | Games, Jordan M |  | 133.8
PR | 998 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/02/25 | 32 | Gerard, Jordan E |  | 4.59
PR | 998 | 05/02/25 | 41 | Lopez, Maslin A |  | 10.1
PR | 998 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 14
PR | 998 | 05/02/25 | 61 | Trower-Kelly, Fidel D |  | 18.97
PR | 998 | 05/02/25 | 62 | Vazquez Popoca, Jose N |  | 21.42
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/09/25 | 173 | Games, Jordan M |  | 68.93
PR | 998 | 05/09/25 | 184 | Lopez, Maslin A |  | 20.2
PR | 998 | 05/09/25 | 192 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 05/16/25 | 361 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/16/25 | 372 | Games, Jordan M |  | 77.04
PR | 998 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 05/16/25 | 403 | Vazquez Popoca, Jose N |  | 64.26
PR | 998 | 05/23/25 | 468 | Games, Jordan M |  | 64.87
PR | 998 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 14
PR | 998 | 05/23/25 | 499 | Vazquez Popoca, Jose N |  | 77.65
PR | 998 | 05/30/25 | 545 | Barnhart, Joseph N |  | 15.61
PR | 998 | 05/30/25 | 545 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/30/25 | 545 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/30/25 | 557 | Games, Jordan M |  | 64.87
PR | 998 | 05/30/25 | 588 | Vazquez Popoca, Jose N |  | 21.42
PR | 998 | 06/06/25 | 24 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 06/06/25 | 33 | Barnhart, Joseph N |  | 80.63
PR | 998 | 06/06/25 | 33 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/06/25 | 45 | Games, Jordan M |  | 32.44
PR | 998 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/06/25 | 63 | Paco Leyva, Orlando |  | 84
PR | 998 | 06/06/25 | 63 | Paco Leyva, Orlando |  | 28
PR | 998 | 06/06/25 | 75 | Vazquez Popoca, Jose N |  | 107.1
PR | 998 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 12.85
PR | 998 | 06/13/25 | 190 | Aquino, Juan |  | 17.14
PR | 998 | 06/13/25 | 194 | Barnhart, Joseph N |  | 52.02
PR | 998 | 06/13/25 | 206 | Games, Jordan M |  | 97.31
PR | 998 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/13/25 | 208 | Gerard, Jordan E |  | 9.18
PR | 998 | 06/13/25 | 217 | Lopez, Maslin A |  | 20.2
PR | 998 | 06/13/25 | 217 | Lopez, Maslin A |  | 10.1
PR | 998 | 06/13/25 | 217 | Lopez, Maslin A |  | 10.1
PR | 998 | 06/13/25 | 225 | Paco Leyva, Orlando |  | 84
PR | 998 | 06/13/25 | 225 | Paco Leyva, Orlando |  | 56
PR | 998 | 06/13/25 | 237 | Vazquez Popoca, Jose N |  | 42.84
PR | 998 | 06/20/25 | 314 | Galdamez, Dagoberto A |  | 38.56
PR | 998 | 06/20/25 | 322 | Barnhart, Joseph N |  | 46.82
PR | 998 | 06/20/25 | 333 | Games, Jordan M |  | 119.61
PR | 998 | 06/20/25 | 344 | Lopez, Maslin A |  | 60.59
PR | 998 | 06/20/25 | 352 | Paco Leyva, Orlando |  | 70
PR | 998 | 06/20/25 | 364 | Vazquez Popoca, Jose N |  | 85.68
PR | 998 | 06/27/25 | 464 | Barnhart, Thomas L |  | 105.26
PR | 998 | 06/27/25 | 468 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 98.84
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/27/25 | 488 | Games, Jordan M |  | 127.72
PR | 998 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/27/25 | 490 | Gerard, Jordan E |  | 4.59
PR | 998 | 06/27/25 | 499 | Lopez, Maslin A |  | 100.98
PR | 998 | 06/27/25 | 507 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 06/27/25 | 507 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 06/27/25 | 519 | Vazquez Popoca, Jose N |  | 107.1
PR | 998 | 07/03/25 | 8 | Barnhart, Thomas L |  | 39.47
PR | 998 | 07/03/25 | 12 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 07/03/25 | 12 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 07/03/25 | 19 | Barnhart, Joseph N |  | 20.81
PR | 998 | 07/03/25 | 19 | Barnhart, Joseph N |  | 31.21
PR | 998 | 07/03/25 | 19 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/03/25 | 31 | Games, Jordan M |  | 97.31
PR | 998 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 07/03/25 | 42 | Lopez, Maslin A |  | 100.98
PR | 998 | 07/03/25 | 50 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 07/03/25 | 62 | Vazquez Popoca, Jose N |  | 42.84
PR | 998 | 07/11/25 | 133 | Barnhart, Thomas L |  | 52.63
PR | 998 | 07/11/25 | 137 | Galdamez, Dagoberto A |  | 99.6
PR | 998 | 07/11/25 | 144 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/11/25 | 144 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/11/25 | 144 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/11/25 | 144 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/11/25 | 156 | Games, Jordan M |  | 125.69
PR | 998 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/11/25 | 166 | Lopez, Maslin A |  | 58.06
PR | 998 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 84
PR | 998 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 14
PR | 998 | 07/11/25 | 174 | Paco Leyva, Orlando |  | 14
PR | 998 | 07/11/25 | 186 | Vazquez Popoca, Jose N |  | 83
PR | 998 | 07/18/25 | 301 | Barnhart, Thomas L |  | 72.37
PR | 998 | 07/18/25 | 304 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 07/18/25 | 304 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 52.02
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 26.01
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 15.61
PR | 998 | 07/18/25 | 323 | Games, Jordan M |  | 83.12
PR | 998 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/18/25 | 325 | Gerard, Jordan E |  | 4.59
PR | 998 | 07/18/25 | 333 | Lopez, Maslin A |  | 85.83
PR | 998 | 07/18/25 | 333 | Lopez, Maslin A |  | 5.05
PR | 998 | 07/18/25 | 333 | Lopez, Maslin A |  | 5.05
PR | 998 | 07/18/25 | 333 | Lopez, Maslin A |  | 5.05
PR | 998 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 93.33
PR | 998 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 07/18/25 | 341 | Paco Leyva, Orlando |  | 28
PR | 998 | 07/18/25 | 353 | Vazquez Popoca, Jose N |  | 21.42
PR | 998 | 07/25/25 | 467 | Anderson, Richard P |  | 9.95
PR | 998 | 07/25/25 | 468 | Barnhart, Thomas L |  | 26.32
PR | 998 | 07/25/25 | 472 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 07/25/25 | 472 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 07/25/25 | 479 | Barnhart, Joseph N |  | 15.61
PR | 998 | 07/25/25 | 479 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/25/25 | 479 | Barnhart, Joseph N |  | 20.81
PR | 998 | 07/25/25 | 479 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/25/25 | 491 | Games, Jordan M |  | 72.98
PR | 998 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/25/25 | 493 | Gerard, Jordan E |  | 9.18
PR | 998 | 07/25/25 | 501 | Lopez, Maslin A |  | 50.49
PR | 998 | 07/25/25 | 501 | Lopez, Maslin A |  | 10.1
PR | 998 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 70
PR | 998 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 07/25/25 | 509 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 08/01/25 | 9 | Araque, Mario W |  | 44.06
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 20.81
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/01/25 | 24 | Games, Jordan M |  | 97.31
PR | 998 | 08/01/25 | 34 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/01/25 | 42 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 08/01/25 | 43 | Perez Araque, Manuel A |  | 51.41
PR | 998 | 08/08/25 | 140 | Araque, Mario W |  | 44.06
PR | 998 | 08/08/25 | 143 | Barnhart, Joseph N |  | 46.82
PR | 998 | 08/08/25 | 150 | Cruz, Azael S |  | 39.17
PR | 998 | 08/08/25 | 155 | Games, Jordan M |  | 105.42
PR | 998 | 08/08/25 | 165 | Lopez, Maslin A |  | 40.39
PR | 998 | 08/08/25 | 173 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 08/08/25 | 174 | Perez Araque, Manuel A |  | 34.27
PR | 998 | 08/15/25 | 268 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/15/25 | 268 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/15/25 | 280 | Games, Jordan M |  | 77.04
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 15.61
PR | 998 | 08/22/25 | 384 | Games, Jordan M |  | 97.31
PR | 998 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/22/25 | 386 | Gerard, Jordan E |  | 9.18
PR | 998 | 08/22/25 | 394 | Lopez, Maslin A |  | 20.2
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/29/25 | 547 | Games, Jordan M |  | 4.05
PR | 998 | 09/05/25 | 13 | Hernandez Gonzalez, Osbaldo |  | 22.49
PR | 998 | 09/05/25 | 19 | Barnhart, Joseph N |  | 52.02
PR | 998 | 09/05/25 | 19 | Barnhart, Joseph N |  | 36.41
PR | 998 | 09/05/25 | 26 | Cruz, Azael S |  | 36.72
PR | 998 | 09/05/25 | 32 | Games, Jordan M |  | 64.87
PR | 998 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 09/05/25 | 40 | Jimenez Alvarenga, Gerson M |  | 20.88
PR | 998 | 09/05/25 | 42 | Lopez, Maslin A |  | 40.39
PR | 998 | 09/05/25 | 42 | Lopez, Maslin A |  | 5.05
PR | 998 | 09/05/25 | 46 | Melgar Moz, Brandon |  | 27.54
PR | 998 | 09/05/25 | 50 | Paco Leyva, Orlando |  | 74.66
PR | 998 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 27.54
PR | 998 | 09/05/25 | 63 | Zuniga Avilez, Eduar A |  | 27.54
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 36.41
PR | 998 | 09/12/25 | 123 | Cruz, Azael S |  | 39.17
PR | 998 | 09/12/25 | 129 | Games, Jordan M |  | 125.69
PR | 998 | 09/12/25 | 130 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 09/12/25 | 131 | Gerard, Jordan E |  | 4.59
PR | 998 | 09/12/25 | 131 | Gerard, Jordan E |  | 4.59
PR | 998 | 09/12/25 | 139 | Lopez, Maslin A |  | 40.39
PR | 998 | 09/12/25 | 143 | Melgar Moz, Brandon |  | 29.38
PR | 998 | 09/12/25 | 147 | Paco Leyva, Orlando |  | 60.66
PR | 998 | 09/12/25 | 156 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 09/12/25 | 160 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 09/19/25 | 248 | Barnhart, Joseph N |  | 150.86
PR | 998 | 09/19/25 | 261 | Games, Jordan M |  | 60.82
PR | 998 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/19/25 | 270 | Lima Romero, Melvin A |  | 87.52
PR | 998 | 09/19/25 | 275 | Melgar Moz, Brandon |  | 14.69
PR | 998 | 09/19/25 | 279 | Paco Leyva, Orlando |  | 172.66
PR | 998 | 09/19/25 | 288 | Suniga Aviles, Kelvin A |  | 67.93
PR | 998 | 09/19/25 | 293 | Zuniga Avilez, Eduar A |  | 67.93
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 9.1
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 3.9
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 32.44
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 50.68
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 33.45
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 32.44
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 13.18
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 28.89
PR | 998 | 09/26/25 | 432 | Games, Jordan M |  | 48.65
PR | 998 | 09/26/25 | 442 | Lopez, Maslin A |  | 20.2
PR | 998 | 09/26/25 | 442 | Lopez, Maslin A |  | 20.2
PR | 998 | 09/26/25 | 450 | Paco Leyva, Orlando |  | 10.5
PR | 998 | 09/26/25 | 450 | Paco Leyva, Orlando |  | 4.67
PR | 998 | 09/26/25 | 461 | Taylor, Evan R |  | 27.85
PR | 998 | 09/26/25 | 461 | Taylor, Evan R |  | 18.9
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 22.11
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 1.3
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 17.23
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 13.18
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 14.19
PR | 998 | 10/10/25 | 177 | Draves, Steven W |  | 22.09
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 32.44
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 3.04
PR | 998 | 10/10/25 | 200 | Paco Leyva, Orlando |  | 1.17
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 8.11
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 22.11
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 11.7
PR | 998 | 11/14/25 | 255 | Paco Leyva, Orlando |  | 19.83
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 19.51
PR | 998 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 1.3
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/05/25 | 62 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 1.3
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 2.68
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/30/26 | 575 | Anderson, Richard P |  | 5.13
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 6.69
PR | 998 | 02/06/26 | 56 | Barnhart, Joseph N |  | 9.37
PR | 998 | 02/20/26 | 336 | Nunez Bravo, Jose L |  | 14.69
PR | 998 | 02/20/26 | 337 | Paco Leyva, Orlando |  | 12.05
PR | 998 | 02/20/26 | 337 | Paco Leyva, Orlando |  | 2.41
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 4.02
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -24850 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -43748 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -81575 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -44742 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -32811 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -22371 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -24856 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -21874 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -22371 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -24856 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -43748 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -111855 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -198848 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -190152 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -140277 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -164050 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -136170 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -116195 | 038258
AR | 999 | 05/20/24 | 604 | Chinn Construction, LLC $Trailside II |  | -15019 | 038258
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 24850 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 43748 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 81575 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 44742 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 32811 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 22371 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 24856 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 21874 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 22371 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 24856 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 43748 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 111855 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 198848 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 190152 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 140277 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 164050 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 136170 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 116195 | 038263
AR | 999 | 05/20/24 | 626 | Chinn Construction, LLC $Trailside II |  | 15019 | 038263
GL | 999 | 09/01/24 | 604 | Aug Billing Adj |  | -11850
AR | 999 | 05/20/25 | 423 | Chinn Construction, LLC $Trailside II |  | -1980 | 038431
AR | 999 | 05/20/25 | 423 | Chinn Construction, LLC $Trailside II |  | -9500 | 038431
AR | 999 | 05/20/25 | 423 | Chinn Construction, LLC $Trailside II |  | -5019 | 038431
AR | 999 | 05/20/25 | 427 | Chinn Construction, LLC $Trailside II |  | 1980 | 038435
AR | 999 | 05/20/25 | 427 | Chinn Construction, LLC $Trailside II |  | 9500 | 038435
AR | 999 | 05/20/25 | 427 | Chinn Construction, LLC $Trailside II |  | 5019 | 038435
AR | 999 | 11/11/25 | 186 | Chinn Construction, LLC $Trailside II |  | -6263 | 038495