## 01 Overview
OWP #2103 · Northgate Station M2
Compass General Construction I, LLC · 234 units · Live / in-progress · OCIP
Forecast at Completion (Revised Basis)
Revised contract value | 6625153.34
Revised budget (expenses) | 5172943.45
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 6608301.34
Retention held | 305091.57
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 130080.51
AP | 1784123.02
PR | 2766581.81
AR | -6608301.34

## 02 Job Info
Job Information
Job ID | 2103
Project name | Northgate Station M2
General contractor | Compass General Construction I, LLC
Owner | Simon Property Group (Indianapolis, IN)
Units | 234
Insurance | OCIP
Job start | Jan 2024
Expected completion | TBD (active)
Architect | GGLO
MEP Engineer | Ecotope
Status | ACTIVE · in-progress
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 6030791 | 6625153.34
Executed change orders (net) | 0 | 594362.34
Total contract value
Executed Change Orders
CO # | Description | Amount
1 | RFI #94 - Type A/B Toilet Product Change | 1676
2 | Jobsite Office Bottle Filler | 2167
3 | RFI #108 - Delete L2 Lounge Sink & Dishwasher | -3200
4 | ASI#4 - Plumbing Permit Revisions | 35521
5 | Foundation Drain Filter Fabric | 2675
6 | RFI 55 - Water Meter Clarification | 10071
7 | RFI #89 - Retail MEP Updates | 5878
8 | RFI 49 - Bike Room 1-A2 Shower | 2329
9 | RFI 124 - Explosion Proof Sump Pumps | 11295
10 | L8 Amenity Gas Fire Pit/Fire Place Supply | 7664
11 | ASI 10 - Plumbing Vent & Waste Routing Revisions | 18764
12 | ASI 12 - Storm and Plumbing Vent Revisions | 8074
13 | ASI 14 - King County Plumbing Revisions & Permit Cost | 3506
14 | Temp Gas Risers | 34604
15 | RFI #163 - Bioretention 6A Trench Drain | 4535
16 | RFI #334 - Add Icemakers to All Unit Types | 45869
17 | ASI 9 - Relocation of HWHP | 18692
18 | OCIP Credit | -20453.66
19 | RFI #238 - Added L4 Roof Drains | 2715
20 | RFI #266 - Add OHP-COMM Condensate Drain Line | 1175
21 | RFI #237 - Plumbing Adjustment to Fur Wall | 4322
22 | Hot and Cold Unit Water Meters - Furnish & Install | 174800
23 | RFI #278.1 - L2 Landscape North Alcove Ramp Drain | 4109
24 | Copper Condensates in Retail Area | 44230
25 | ASI-07 Extend Garage Trench Drain + Civil Storm POC | 6895
26 | RFI-446 Unit Riser Shutoff Valves | 29700
27 | RFI-363 Added Hosebib | 1100
28 | RFI #517 - RPBP-1&2 Pipe Size | 5110
29 | Flex Connector Changes | 4860
30 | Remove & Reinstall Tubs & Showers for Framing | 3090
31 | Temp Roof Drains | 1330
32 | L9 Temp Roof Drains | 1240
33 | Leak Sensor Install | 3950
34 | ASI-19 Retail Revisions - Add POCs, Move Rainleader | 5450
35 | Additional Control Panel for Water Heating System | 4320
36 | Casework Revisions @ X25-X41 | 10170
37 | L7 Temp Roof Drains | 1470
38 | RFI #432.1 - Plumbing Rework | 9600
39 | Water Stub Out Extensions at Cabinets | 6160
40 | ASI-028 Dog & Bike Wash | 7520
41 | Fix Temp Heat Gas Hoses | 5230
42 | Add GI Stub | 4520
43 | RFI 673 - Add Drain Fire Pump Room | 950
44 | Move Plumbing Per RFI 667 | 790
45 | Cap Temp Gas / Move Waste Lines / Move ADA Tub Spouts | 5930
46 | RFI 519 - Reroute Condensates Units 128-129 | 2630
47 | Add Level 2 Floor Drain | 1630
48 | Remove Tubs Per RFI 639 | 1660
49 | Disconnect Temp Gas | 880
50 | ASI 30 - Added Sink | 3860
51 | ASI 33 - Fitness Room | 34610
52 | Maintenance Room Sink Replacement | 410
53 | Permit Revision Fees | 2130
54 | RFI 694 - Add Grease Stub | 6170

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 15210 | 16210 | 11762 |  | 0
101 | Takeoff & Purchase Labor | 40950 | 50300 | 52674 |  | 0
110 | Underground Labor | 53163 | 75888 | 95456 |  | 0
111 | Garage Labor | 109938 | 136288 | 167884.75 |  | 0
112 | Canout Labor | 51050 | 52600 | 41039 |  | 0
120 | Roughin Labor | 890865 | 936025 | 1041296.25 |  | 0
130 | Finish Labor | 136060 | 185910 | 132682.75 |  | 0
140 | Gas Labor | 9550 | 25250 | 21237.25 |  | 0
141 | Water Main/Insulation Lab | 181470 | 193670 | 185051 |  | 0
142 | Mech Room Labor | 99200 | 107100 | 61170.75 |  | 0
151 | T&M Labor | 0 | 0 | 869 |  | 0
210 | Underground Material | 64300 | 75460 | 49664.33 |  | 0
211 | Garage Material | 105025 | 122695 | 169337.63 |  | 0
212 | Canout Material | 51050 | 52900 | 22272.59 |  | 0
220 | Roughin Material | 636571 | 657496 | 429974.35 |  | 775.09
230 | Finish Material | 1011650 | 1140441 | 971188.26 |  | 1896.23
240 | Gas Material | 8463 | 21708 | 14023.31 |  | 594.01
241 | Water Main/Insulation Mat | 192848 | 207528 | 126781.38 |  | 1533.67
242 | Mech Room Material | 102300 | 109400 | 71241.58 |  | 704.14
251 | T&M Material | 0 | 0 | 0 |  | 0
600 | Subcontractor | 30983 | 35083 | 17950 |  | 3450
601 | Engineering/Plans | 99450 | 99450 | 8252.5 |  | 0
602 | Rental Equipment | 15000 | 17990 | 17684.58 |  | 0
603 | Permits & Licenses | 24660 | 31010 | 22521.02 |  | 0
995 | Payroll Burden | 613551.26 | 686429.56 | 809708.06 |  | 0
998 | Payroll Taxes | 121440.29 | 136111.89 | 139063 |  | 0
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 1779241 | 1810253.75
Material | 9 | 2387628 | 1854483.43
Overhead | 4 | 183533 | 66408.1
Burden | 2 | 822541.45 | 948771.06
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 16210 | 11762
101 | Takeoff & Purchase Labor | 50300 | 52674
110 | Underground Labor | 75888 | 95456
111 | Garage Labor | 136288 | 167884.75
112 | Canout Labor | 52600 | 41039
120 | Roughin Labor | 936025 | 1041296.25
130 | Finish Labor | 185910 | 132682.75
140 | Gas Labor | 25250 | 21237.25
141 | Water Main/Insulation Lab | 193670 | 185051
142 | Mech Room Labor | 107100 | 61170.75
151 | T&M Labor | 0 | 869
210 | Underground Material | 75460 | 49664.33
211 | Garage Material | 122695 | 169337.63
212 | Canout Material | 52900 | 22272.59
220 | Roughin Material | 657496 | 429974.35
230 | Finish Material | 1140441 | 971188.26
240 | Gas Material | 21708 | 14023.31
241 | Water Main/Insulation Mat | 207528 | 126781.38
242 | Mech Room Material | 109400 | 71241.58
600 | Subcontractor | 35083 | 17950
601 | Engineering/Plans | 99450 | 8252.5
602 | Rental Equipment | 17990 | 17684.58
603 | Permits & Licenses | 31010 | 22521.02
995 | Payroll Burden | 686429.56 | 809708.06
998 | Payroll Taxes | 136111.89 | 139063

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Consolidated Supply Co. | 513807.97 | 202
Keller Supply Company | 308409.55 | 84
Trane US, Inc | 293172 | 7
Pacific Plumbing Supply Co., LLC | 186883.36 | 122
Rosen Supply Kirkland | 174323.23 | 112
California Hydronics Corp | 93309.6 | 10
MacArthur Co. NW 6276 | 56828.56 | 12
Pioneer Energy Management | 53820 | 1
Bank of America CC | 22578.38 | 12
Old Castle Infrastructure, Inc. | 15437.21 | 1
Mechanical Resource Services, Inc. | 14500 | 1
Herc Rentals, Inc. | 13086 | 26
Franklin Engineering | 8252.5 | 1
Submeter Solutions, Inc. | 7032.28 | 1
Ferguson Enterprises, Inc. #3007 | 6986.43 | 13
Williams Scotsman, Inc. $Mobile Mini | 4299.63 | 16
Chemical Products Company | 3450 | 1
Best Bath Systems | 2146.94 | 1
Core & Main LP $HD Supply Waterworks | 1852.06 | 7
Pac West Sales | 1754.6 | 4
Capital One Credit Card | 824.24 | 18
Kele, Inc $ MI Controls | 536 | 1
United Rentals, Inc. | 298.95 | 1
Mechanical Sales, Inc. | 229.7 | 1
ACME Corp | 185.6 | 1
Seton Identification Products | 118.23 | 1
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Cortes Mendiola, Victor H | 2493 | 159865 |  | LEAD/SUPERVISOR
Bautista Quintero, Isidoro | 2392.5 | 52836 |  | JOURNEYMAN
Amaya Gonzalez, Edilberto A | 2358.2 | 119093 |  | LEAD/SUPERVISOR
Silva Morales, Jair J | 2301 | 78326 |  | JOURNEYMAN
Cruz Reyes, Jose | 2035.8 | 81328 |  | LEAD/SUPERVISOR
Carmona, Raul O | 1848.5 | 98110 |  | LEAD/SUPERVISOR
Gerard, Mitchell J | 1796 | 110429 |  | LEAD/SUPERVISOR
Portillo Soriano, Walter A | 1252 | 43820 |  | JOURNEYMAN
Cruz Guzman, Joel A | 1236 | 63036 |  | LEAD/SUPERVISOR
Draves, Steven W | 1229.5 | 68635 |  | LEAD/SUPERVISOR
Mendoza Morales, Jesus A | 1088 | 44726 |  | LEAD/SUPERVISOR
McCabe, Thomas C | 1078 | 47432 |  | LEAD/SUPERVISOR
Balderas Ortiz, Ricardo I | 1012 | 44528 |  | LEAD/SUPERVISOR
Zuniga Avilez, Eduar A | 986 | 22815 |  | JOURNEYMAN
Lima Romero, Melvin A | 981 | 43164 |  | LEAD/SUPERVISOR
Suniga Aviles, Kelvin A | 980 | 22227 |  | JOURNEYMAN
Waites, Thaddeus Z | 964.5 | 54930 |  | LEAD/SUPERVISOR
Castro Hernandez, Jose A | 948 | 51192 |  | LEAD/SUPERVISOR
Cornejo Orellana, Carlos E | 919 | 32165 |  | JOURNEYMAN
Merino Martinez, Humberto | 916 | 25648 |  | JOURNEYMAN
Barnhart, Thomas L | 894 | 39152 |  | LEAD/SUPERVISOR
Barnhart, Joseph N | 856.5 | 58974 |  | LEAD/SUPERVISOR
Gochez Molina, Douglas O | 824 | 21224 |  | JOURNEYMAN
Rodriguez Arevalos, Christian | 787.2 | 40264 |  | LEAD/SUPERVISOR
Jimenez Alvarenga, Gerson M | 775 | 30225 |  | LEAD/SUPERVISOR
Eliassen, Cory H | 737.8 | 27230 |  | LEAD/SUPERVISOR
Taylor, Evan R | 701 | 36452 |  | LEAD/SUPERVISOR
Lopez, Maslin A | 692 | 22836 |  | JOURNEYMAN
Guerrero Espinoza, Mario | 640 | 19200 |  | JOURNEYMAN
Hernandez Gonzalez, Osbaldo | 640 | 24864 |  | LEAD/SUPERVISOR
Ross, Kelli M | 639 | 32589 |  | LEAD/SUPERVISOR
Ascencio, Jose L | 565 | 23842 |  | LEAD/SUPERVISOR
Galdamez, Dagoberto A | 544 | 19488 |  | JOURNEYMAN
Gerard, Jeffrey S | 495 | 34155 |  | LEAD/SUPERVISOR
Ramos Herrera, Franklin J | 485 | 20482 |  | LEAD/SUPERVISOR
Perez Araque, Manuel A | 364.2 | 9328 |  | JOURNEYMAN
Paco Leyva, Orlando | 339.5 | 20877 |  | LEAD/SUPERVISOR
Melgar Moz, Brandon | 297 | 6619 |  | JOURNEYMAN
Johnson, Jake E | 264 | 13728 |  | LEAD/SUPERVISOR
Gerard, Jordan E | 214.2 | 12821 |  | LEAD/SUPERVISOR
Da Cruz, Eduardo E | 183.5 | 3972 |  | JOURNEYMAN
Portillo Rivera, Josue N | 168 | 3696 |  | JOURNEYMAN
Fox, Tamron P | 143 | 3974 |  | JOURNEYMAN
Reed, Reuben H | 138 | 8556 |  | LEAD/SUPERVISOR
Del Villar, Flabio | 116 | 4648 |  | LEAD/SUPERVISOR
Games, Jordan M | 69.2 | 3670 |  | LEAD/SUPERVISOR
Young, Joshua S | 53 | 2230 |  | LEAD/SUPERVISOR
Swails, Melanie L | 48 | 0 |  | APPRENTICE/HELPER
Castro, Marcus J | 48 | 1088 |  | JOURNEYMAN
Anderson, Richard P | 46 | 2990 |  | LEAD/SUPERVISOR
Aquino, Juan | 40 | 1298 |  | JOURNEYMAN
Eisenhauer, Tommy J | 19 | 1083 |  | LEAD/SUPERVISOR
Romero Garza, Jesus I | 11 | 363 |  | JOURNEYMAN
Araque, Mario W | 8 | 192 |  | JOURNEYMAN
Countryman, Matthew K | 5 | 344 |  | LEAD/SUPERVISOR
Chevez, Herson G | 5 | 285 |  | OT-ONLY
Gorman, Nathan W | 5 | 195 |  | OT-ONLY
Mackey, Cole J | 5 | 390 |  | OT-ONLY
Nunez Bravo, Jose L | 5 | 180 |  | OT-ONLY

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 34 | 27908 | 1425645
JOURNEYMAN | 20 | 13709.2 | 391116
APPRENTICE/HELPER | 1 | 48 | 0
OT-ONLY | 4 | 20 | 1050

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 41685
Active workers | 59
Hours per unit (to date) | 178.1
Revenue per labor hour (billed) | 158.53
Percent complete | 99.75%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 21.92% | 34%
Roughin labor share (code 120) | 52.61% | 45%
Top vendor concentration | 28.8% | 38%
Hours per unit | 178.1421 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Underground Labor (110) over revised | ⚠ WATCH | Actual $95,456 vs revised $75,888 (+26%) — monitor
Garage Labor (111) over revised | ⚠ WATCH | Actual $167,885 vs revised $136,288 (+23%) — monitor
Roughin Labor (120) over revised | ⚠ WATCH | Actual $1,041,296 vs revised $936,025 (+11%) — monitor
Garage Material (211) over revised | ⚠ WATCH | Actual $169,338 vs revised $122,695 (+38%) — monitor
Payroll Burden (995) over revised | ⚠ WATCH | Actual $809,708 vs revised $686,430 (+18%) — monitor
Top vendor concentration (Consolidated Supply ) | ✓ OK | 29% of AP ($513,808) — acceptable
Retention aging | ✓ OK | $305,092 held · 4.6% of billed · standard range
Forecast margin | ⚠ WATCH | 21.9% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 4680785.34 | 4680785.34
Revenue billed (AR ·-1) | -6608301.34 | 6608301.34
AP source total |  | 1784123.02
PR source total |  | 2766581.81
GL source total |  | 130080.51

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-23 | v1.0 · live | Initial build for #2103 live project. 17-tab JCR schema on revised budget basis.