## Summary
#2103 · Northgate Station M2
Compass General Construction I, LLC · 234 units · ACTIVE · 99.7% billed · OCIP
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
6625153.34 | 21.92% | 6608301.34 | 16852
Key facts
Original contract |  | 6030791
Revised contract (CO impact) |  | 6625153.34
Executed COs (net) |  | 594362.34
Retention held |  | 305091.57
Revised expense budget |  | 5172943.45
Forecast net profit |  | 1452209.89
Percent complete |  | 99.75%
Live signals
Underground Labor (110) over | ⚠ WATCH | Actual $95,456 vs revised $75,888 (+26%) — monitor
Garage Labor (111) over | ⚠ WATCH | Actual $167,885 vs revised $136,288 (+23%) — monitor
Roughin Labor (120) over | ⚠ WATCH | Actual $1,041,296 vs revised $936,025 (+11%) — monitor
Garage Material (211) over | ⚠ WATCH | Actual $169,338 vs revised $122,695 (+38%) — monitor
Payroll Burden (995) over | ⚠ WATCH | Actual $809,708 vs revised $686,430 (+18%) — monitor
Top vendor (Consolidated Supply ) | ✓ OK | 29% of AP — acceptable
Retention | ✓ OK | $305,092 held · 5% standard
Forecast margin | ⚠ WATCH | 21.9% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Consolidated Supply Co. | 202 | 513807.97 | 28.8%
Keller Supply Company | 84 | 308409.55 | 17.29%
Trane US, Inc | 7 | 293172 | 16.43%
Pacific Plumbing Supply Co., LLC | 122 | 186883.36 | 10.47%
Rosen Supply Kirkland | 112 | 174323.23 | 9.771%
California Hydronics Corp | 10 | 93309.6 | 5.23%

## Transactions
Transactions Detail
JDR source transactions for job #2103 · 9405 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 03/08/24 | 334 | Gerard, Jeffrey S | 2 | 138 | 92552
PR | 100 | 03/15/24 | 507 | Barnhart, Joseph N | 3 | 204 | 2536
PR | 100 | 03/15/24 | 599 | Gerard, Jeffrey S | 2 | 138 | 92617
PR | 100 | 05/03/24 | 56 | Gerard, Jeffrey S | 1 | 69 | 92843
PR | 100 | 06/28/24 | 731 | Gerard, Jeffrey S | 2 | 138 | 93003
PR | 100 | 07/19/24 | 413 | Gerard, Jeffrey S | 2 | 138 | 93043
PR | 100 | 07/26/24 | 600 | Gerard, Jeffrey S | 1.5 | 103.5 | 93052
PR | 100 | 08/02/24 | 40 | Gerard, Jeffrey S | 2.5 | 172.5 | 93063
PR | 100 | 08/09/24 | 274 | Gerard, Jeffrey S | 3 | 207 | 23074
PR | 100 | 08/16/24 | 463 | Gerard, Jeffrey S | 3.5 | 241.5 | 33083
PR | 100 | 08/23/24 | 725 | Gerard, Jeffrey S | 4.5 | 310.5 | 43094
PR | 100 | 08/30/24 | 867 | Gerard, Jeffrey S | 1 | 69 | 53112
PR | 100 | 09/06/24 | 44 | Gerard, Jeffrey S | 2 | 138 | 13124
PR | 100 | 09/13/24 | 252 | Gerard, Jeffrey S | 3 | 207 | 23135
PR | 100 | 09/20/24 | 423 | Gerard, Jeffrey S | 3.5 | 241.5 | 33147
PR | 100 | 09/27/24 | 559 | Gerard, Jeffrey S | 1 | 69 | 43158
PR | 100 | 10/04/24 | 43 | Gerard, Jeffrey S | 3.5 | 241.5 | 13172
PR | 100 | 10/11/24 | 250 | Gerard, Jeffrey S | 1 | 69 | 23184
PR | 100 | 10/18/24 | 462 | Gerard, Jeffrey S | 4.5 | 310.5 | 33195
PR | 100 | 10/25/24 | 609 | Gerard, Jeffrey S | 1.5 | 103.5 | 43206
PR | 100 | 11/01/24 | 38 | Gerard, Jeffrey S | 4 | 276 | 13218
PR | 100 | 11/08/24 | 158 | Gerard, Jeffrey S | 2.5 | 172.5 | 23230
PR | 100 | 11/15/24 | 378 | Gerard, Jeffrey S | 2 | 138 | 33242
PR | 100 | 11/22/24 | 533 | Gerard, Jeffrey S | 3 | 207 | 43255
PR | 100 | 11/29/24 | 648 | Johnson, Jake E | 2 | 104 | 43295
PR | 100 | 11/29/24 | 681 | Gerard, Jeffrey S | 3 | 207 | 53267
PR | 100 | 12/06/24 | 83 | Gerard, Jeffrey S | 1 | 69 | 13279
PR | 100 | 12/13/24 | 265 | Gerard, Jeffrey S | 1 | 69 | 23300
PR | 100 | 12/20/24 | 451 | Gerard, Jeffrey S | 3 | 207 | 33309
PR | 100 | 12/27/24 | 570 | Gerard, Jeffrey S | 4 | 276 | 43320
PR | 100 | 01/03/25 | 41 | Gerard, Jeffrey S | 1 | 69 | 13330
PR | 100 | 01/10/25 | 204 | Gerard, Jeffrey S | 2 | 138 | 23342
PR | 100 | 01/17/25 | 367 | Gerard, Jeffrey S | 3 | 207 | 33353
PR | 100 | 01/24/25 | 534 | Gerard, Jeffrey S | 2.5 | 172.5 | 43364
PR | 100 | 01/31/25 | 726 | Gerard, Jeffrey S | 1.5 | 103.5 | 53374
PR | 100 | 02/07/25 | 56 | Gerard, Jeffrey S | 1.5 | 103.5 | 13383
PR | 100 | 02/14/25 | 222 | Gerard, Jeffrey S | 5.5 | 379.5 | 23392
PR | 100 | 02/21/25 | 340 | Gerard, Jeffrey S | 1.5 | 103.5 | 33402
PR | 100 | 03/07/25 | 43 | Gerard, Jeffrey S | 2 | 138 | 13423
PR | 100 | 03/14/25 | 243 | Gerard, Jeffrey S | 3 | 207 | 23434
PR | 100 | 03/21/25 | 436 | Gerard, Jeffrey S | 1 | 69 | 93444
PR | 100 | 03/28/25 | 591 | Gerard, Jeffrey S | 1 | 69 | 93465
PR | 100 | 04/04/25 | 34 | Gerard, Jeffrey S | 5 | 345 | 13476
PR | 100 | 04/11/25 | 214 | Gerard, Jeffrey S | 2.5 | 172.5 | 93486
PR | 100 | 04/18/25 | 438 | Gerard, Jeffrey S | 3 | 207 | 33496
PR | 100 | 04/25/25 | 577 | Gerard, Jeffrey S | 3 | 207 | 43506
PR | 100 | 05/02/25 | 31 | Gerard, Jeffrey S | 3 | 207 | 13516
PR | 100 | 05/09/25 | 174 | Gerard, Jeffrey S | 1 | 69 | 23523
PR | 100 | 05/16/25 | 373 | Gerard, Jeffrey S | 2 | 138 | 33532
PR | 100 | 05/23/25 | 469 | Gerard, Jeffrey S | 3 | 207 | 43541
PR | 100 | 05/30/25 | 558 | Gerard, Jeffrey S | 1 | 69 | 53550
PR | 100 | 06/06/25 | 46 | Gerard, Jeffrey S | 1 | 69 | 13558
PR | 100 | 06/13/25 | 207 | Gerard, Jeffrey S | 1 | 69 | 23566
PR | 100 | 06/20/25 | 334 | Gerard, Jeffrey S | 1 | 69 | 33573
PR | 100 | 06/27/25 | 489 | Gerard, Jeffrey S | 2.5 | 172.5 | 43582
PR | 100 | 07/03/25 | 32 | Gerard, Jeffrey S | 2 | 138 | 13589
PR | 100 | 07/11/25 | 157 | Gerard, Jeffrey S | 1.5 | 103.5 | 23596
PR | 100 | 07/18/25 | 324 | Gerard, Jeffrey S | 2 | 138 | 33603
PR | 100 | 07/25/25 | 492 | Gerard, Jeffrey S | 3.5 | 241.5 | 43610
PR | 100 | 08/01/25 | 25 | Gerard, Jeffrey S | 2 | 138 | 13616
PR | 100 | 08/08/25 | 156 | Gerard, Jeffrey S | 1 | 69 | 23623
PR | 100 | 08/15/25 | 281 | Gerard, Jeffrey S | 1 | 69 | 33628
PR | 100 | 08/22/25 | 385 | Gerard, Jeffrey S | 2 | 138 | 43635
PR | 100 | 08/29/25 | 548 | Gerard, Jeffrey S | 2 | 138 | 53641
PR | 100 | 09/05/25 | 33 | Gerard, Jeffrey S | 1 | 69 | 13647
PR | 100 | 09/19/25 | 262 | Gerard, Jeffrey S | 1 | 69 | 33658
PR | 100 | 10/03/25 | 30 | Gerard, Jeffrey S | 1 | 69 | 13673
PR | 100 | 10/03/25 | 30 | Gerard, Jeffrey S | 1.5 | 103.5 | 13673
PR | 100 | 10/10/25 | 182 | Gerard, Jeffrey S | 1 | 69 | 23680
PR | 100 | 10/17/25 | 387 | Gerard, Jeffrey S | 1 | 69 | 33688
PR | 100 | 10/31/25 | 687 | Gerard, Jeffrey S | 1 | 69 | 53704
PR | 100 | 11/07/25 | 75 | Gerard, Jeffrey S | 0.5 | 34.5 | 13709
PR | 100 | 11/14/25 | 235 | Gerard, Jeffrey S | 0.5 | 34.5 | 23715
PR | 100 | 11/14/25 | 235 | Gerard, Jeffrey S | 1 | 69 | 23715
PR | 100 | 11/14/25 | 235 | Gerard, Jeffrey S | 0.5 | 34.5 | 23715
PR | 100 | 11/21/25 | 352 | Gerard, Jeffrey S | 1 | 69 | 33721
PR | 100 | 11/28/25 | 536 | Gerard, Jeffrey S | 1 | 69 | 43726
PR | 100 | 11/28/25 | 536 | Gerard, Jeffrey S | 1 | 69 | 43726
PR | 100 | 12/12/25 | 199 | Gerard, Jeffrey S | 1 | 69 | 23734
PR | 100 | 12/19/25 | 340 | Gerard, Jeffrey S | 0.5 | 34.5 | 33738
PR | 100 | 12/26/25 | 528 | Gerard, Jeffrey S | 0.5 | 34.5 | 43746
PR | 100 | 01/02/26 | 32 | Gerard, Jeffrey S | 1 | 69 | 13750
PR | 100 | 01/09/26 | 147 | Gerard, Jeffrey S | 0.5 | 34.5 | 23754
PR | 100 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 100 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 100 | 01/23/26 | 484 | Gerard, Jeffrey S | 0.5 | 34.5 | 43763
PR | 100 | 01/30/26 | 597 | Gerard, Jeffrey S | 0.5 | 34.5 | 53768
PR | 100 | 01/30/26 | 597 | Gerard, Jeffrey S | 1 | 69 | 53768
PR | 100 | 02/06/26 | 72 | Gerard, Jeffrey S | 0.5 | 34.5 | 13772
PR | 100 | 02/20/26 | 320 | Gerard, Jeffrey S | 1 | 69 | 33784
PR | 100 | 03/06/26 | 63 | Gerard, Jeffrey S | 1 | 69 | 13791
PR | 100 | 03/06/26 | 63 | Gerard, Jeffrey S | 1 | 69 | 13791
PR | 100 | 03/20/26 | 326 | Gerard, Jeffrey S | 1 | 69 | 33799
PR | 100 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/22/24 | 869 | Gerard, Jeffrey S | 1 | 69 | 92666
PR | 101 | 03/22/24 | 878 | Johnson, Jake E | 1 | 52 | 92675
PR | 101 | 03/29/24 | 1182 | Barnhart, Joseph N | 3 | 204 | 2643
PR | 101 | 03/29/24 | 1246 | Gerard, Jeffrey S | 3 | 207 | 92706
PR | 101 | 03/29/24 | 1256 | Johnson, Jake E | 2 | 104 | 92716
PR | 101 | 04/05/24 | 62 | Gerard, Jeffrey S | 4 | 276 | 92737
PR | 101 | 04/05/24 | 74 | Johnson, Jake E | 1 | 52 | 92749
PR | 101 | 04/12/24 | 166 | Barnhart, Joseph N | 8 | 544 | 2711
PR | 101 | 04/12/24 | 223 | Gerard, Jeffrey S | 3 | 207 | 92767
PR | 101 | 04/12/24 | 236 | Johnson, Jake E | 4 | 208 | 92780
PR | 101 | 04/19/24 | 445 | Barnhart, Joseph N | 5 | 340 | 2739
PR | 101 | 04/19/24 | 504 | Gerard, Jeffrey S | 6 | 414 | 92797
PR | 101 | 04/19/24 | 517 | Johnson, Jake E | 3 | 156 | 92810
PR | 101 | 04/26/24 | 828 | Gerard, Jeffrey S | 3 | 207 | 92822
PR | 101 | 05/03/24 | 56 | Gerard, Jeffrey S | 2 | 138 | 92843
PR | 101 | 05/03/24 | 68 | Johnson, Jake E | 8 | 416 | 92855
PR | 101 | 05/10/24 | 242 | Barnhart, Joseph N | 3 | 204 | 2815
PR | 101 | 05/10/24 | 294 | Gerard, Jeffrey S | 6 | 414 | 92864
PR | 101 | 05/10/24 | 306 | Johnson, Jake E | 9 | 468 | 92876
PR | 101 | 05/17/24 | 470 | Barnhart, Joseph N | 11 | 748 | 2838
PR | 101 | 05/17/24 | 521 | Gerard, Jeffrey S | 6 | 414 | 92888
PR | 101 | 05/24/24 | 726 | Gerard, Jeffrey S | 5 | 345 | 92910
PR | 101 | 05/24/24 | 738 | Johnson, Jake E | 4 | 208 | 92922
PR | 101 | 05/31/24 | 793 | Barnhart, Joseph N | 7 | 476 | 2884
PR | 101 | 05/31/24 | 840 | Gerard, Jeffrey S | 8 | 552 | 92930
PR | 101 | 05/31/24 | 850 | Johnson, Jake E | 5 | 260 | 92940
PR | 101 | 06/07/24 | 129 | Gerard, Jeffrey S | 4 | 276 | 92951
PR | 101 | 06/07/24 | 139 | Johnson, Jake E | 4 | 208 | 92961
PR | 101 | 06/14/24 | 305 | Barnhart, Joseph N | 2 | 136 | 2925
PR | 101 | 06/14/24 | 352 | Gerard, Jeffrey S | 4 | 276 | 92971
PR | 101 | 06/14/24 | 362 | Johnson, Jake E | 4 | 208 | 92981
PR | 101 | 06/21/24 | 524 | Gerard, Jeffrey S | 1 | 69 | 92987
PR | 101 | 06/21/24 | 533 | Johnson, Jake E | 1 | 52 | 92996
PR | 101 | 06/28/24 | 731 | Gerard, Jeffrey S | 4 | 276 | 93003
PR | 101 | 06/28/24 | 740 | Johnson, Jake E | 4 | 208 | 93012
PR | 101 | 07/05/24 | 45 | Gerard, Jeffrey S | 3 | 207 | 93017
PR | 101 | 07/05/24 | 53 | Johnson, Jake E | 8 | 416 | 93025
PR | 101 | 07/12/24 | 207 | Gerard, Jeffrey S | 3 | 207 | 93031
PR | 101 | 07/12/24 | 216 | Johnson, Jake E | 3 | 156 | 93040
PR | 101 | 07/19/24 | 390 | Barnhart, Joseph N | 1.5 | 102 | 93020
PR | 101 | 07/19/24 | 413 | Gerard, Jeffrey S | 7 | 483 | 93043
PR | 101 | 07/19/24 | 422 | Johnson, Jake E | 4 | 208 | 93052
PR | 101 | 07/26/24 | 600 | Gerard, Jeffrey S | 5 | 345 | 93052
PR | 101 | 07/26/24 | 609 | Johnson, Jake E | 3 | 156 | 93061
PR | 101 | 08/02/24 | 40 | Gerard, Jeffrey S | 7 | 483 | 93063
PR | 101 | 08/02/24 | 49 | Johnson, Jake E | 5 | 260 | 93072
PR | 101 | 08/02/24 | 49 | Johnson, Jake E | 2 | 104 | 93072
PR | 101 | 08/09/24 | 274 | Gerard, Jeffrey S | 4 | 276 | 23074
PR | 101 | 08/09/24 | 283 | Johnson, Jake E | 1 | 52 | 23083
PR | 101 | 08/16/24 | 463 | Gerard, Jeffrey S | 3 | 207 | 33083
PR | 101 | 08/16/24 | 472 | Johnson, Jake E | 1 | 52 | 33092
PR | 101 | 08/23/24 | 706 | Barnhart, Joseph N | 5 | 340 | 43075
PR | 101 | 08/23/24 | 725 | Gerard, Jeffrey S | 10 | 690 | 43094
PR | 101 | 08/23/24 | 734 | Johnson, Jake E | 1 | 52 | 43103
PR | 101 | 08/30/24 | 849 | Barnhart, Joseph N | 3 | 204 | 53094
PR | 101 | 08/30/24 | 867 | Gerard, Jeffrey S | 5 | 345 | 53112
PR | 101 | 08/30/24 | 876 | Johnson, Jake E | 7 | 364 | 53121
PR | 101 | 09/06/24 | 44 | Gerard, Jeffrey S | 7 | 483 | 13124
PR | 101 | 09/06/24 | 53 | Johnson, Jake E | 8 | 416 | 13133
PR | 101 | 09/13/24 | 233 | Barnhart, Joseph N | 2 | 136 | 23116
PR | 101 | 09/13/24 | 252 | Gerard, Jeffrey S | 9 | 621 | 23135
PR | 101 | 09/13/24 | 261 | Johnson, Jake E | 11 | 572 | 23144
PR | 101 | 09/20/24 | 423 | Gerard, Jeffrey S | 11 | 759 | 33147
PR | 101 | 09/20/24 | 432 | Johnson, Jake E | 9 | 468 | 33156
PR | 101 | 09/27/24 | 559 | Gerard, Jeffrey S | 8 | 552 | 43158
PR | 101 | 09/27/24 | 568 | Johnson, Jake E | 2 | 104 | 43167
PR | 101 | 10/04/24 | 43 | Gerard, Jeffrey S | 9 | 621 | 13172
PR | 101 | 10/04/24 | 52 | Johnson, Jake E | 3 | 156 | 13181
PR | 101 | 10/11/24 | 233 | Barnhart, Joseph N | 3 | 204 | 23167
PR | 101 | 10/11/24 | 250 | Gerard, Jeffrey S | 11 | 759 | 23184
PR | 101 | 10/11/24 | 259 | Johnson, Jake E | 6 | 312 | 23193
PR | 101 | 10/18/24 | 446 | Barnhart, Joseph N | 3 | 204 | 33179
PR | 101 | 10/18/24 | 462 | Gerard, Jeffrey S | 11 | 759 | 33195
PR | 101 | 10/18/24 | 471 | Johnson, Jake E | 8 | 416 | 33204
PR | 101 | 10/25/24 | 609 | Gerard, Jeffrey S | 7 | 483 | 43206
PR | 101 | 10/25/24 | 618 | Johnson, Jake E | 6 | 312 | 43215
PR | 101 | 11/01/24 | 38 | Gerard, Jeffrey S | 7 | 483 | 13218
PR | 101 | 11/01/24 | 47 | Johnson, Jake E | 4 | 208 | 13227
PR | 101 | 11/08/24 | 158 | Gerard, Jeffrey S | 5 | 345 | 23230
PR | 101 | 11/08/24 | 167 | Johnson, Jake E | 4 | 208 | 23239
PR | 101 | 11/15/24 | 363 | Barnhart, Joseph N | 1 | 68 | 33227
PR | 101 | 11/15/24 | 378 | Gerard, Jeffrey S | 6 | 414 | 33242
PR | 101 | 11/15/24 | 387 | Johnson, Jake E | 6 | 312 | 33251
PR | 101 | 11/22/24 | 533 | Gerard, Jeffrey S | 3 | 207 | 43255
PR | 101 | 11/29/24 | 648 | Johnson, Jake E | 1 | 52 | 43295
PR | 101 | 11/29/24 | 681 | Gerard, Jeffrey S | 4 | 276 | 53267
PR | 101 | 11/29/24 | 690 | Johnson, Jake E | 4 | 208 | 53276
PR | 101 | 12/06/24 | 83 | Gerard, Jeffrey S | 2 | 138 | 13279
PR | 101 | 12/06/24 | 92 | Johnson, Jake E | 4 | 208 | 13288
PR | 101 | 12/13/24 | 250 | Barnhart, Joseph N | 2 | 136 | 23285
PR | 101 | 12/13/24 | 265 | Gerard, Jeffrey S | 5 | 345 | 23300
PR | 101 | 12/13/24 | 274 | Johnson, Jake E | 2 | 104 | 23309
PR | 101 | 12/20/24 | 451 | Gerard, Jeffrey S | 4 | 276 | 33309
PR | 101 | 12/20/24 | 460 | Johnson, Jake E | 3 | 156 | 33318
PR | 101 | 12/27/24 | 570 | Gerard, Jeffrey S | 3 | 207 | 43320
PR | 101 | 12/27/24 | 579 | Johnson, Jake E | 2 | 104 | 43329
PR | 101 | 01/03/25 | 41 | Gerard, Jeffrey S | 3 | 207 | 13330
PR | 101 | 01/03/25 | 49 | Johnson, Jake E | 1 | 52 | 13338
PR | 101 | 01/10/25 | 204 | Gerard, Jeffrey S | 3 | 207 | 23342
PR | 101 | 01/10/25 | 212 | Johnson, Jake E | 7 | 364 | 23350
PR | 101 | 01/17/25 | 367 | Gerard, Jeffrey S | 4 | 276 | 33353
PR | 101 | 01/17/25 | 375 | Johnson, Jake E | 8 | 416 | 33361
PR | 101 | 01/24/25 | 534 | Gerard, Jeffrey S | 3 | 207 | 43364
PR | 101 | 01/24/25 | 611 | Johnson, Jake E | 3 | 156 | 43400
PR | 101 | 01/31/25 | 726 | Gerard, Jeffrey S | 2 | 138 | 53374
PR | 101 | 01/31/25 | 734 | Johnson, Jake E | 6 | 312 | 53382
PR | 101 | 02/07/25 | 56 | Gerard, Jeffrey S | 1 | 69 | 13383
PR | 101 | 02/07/25 | 64 | Johnson, Jake E | 5 | 260 | 13391
PR | 101 | 02/14/25 | 222 | Gerard, Jeffrey S | 4 | 276 | 23392
PR | 101 | 02/14/25 | 230 | Johnson, Jake E | 2 | 104 | 23400
PR | 101 | 02/21/25 | 340 | Gerard, Jeffrey S | 7 | 483 | 33402
PR | 101 | 02/21/25 | 348 | Johnson, Jake E | 5 | 260 | 33410
PR | 101 | 02/28/25 | 530 | Gerard, Jeffrey S | 4.5 | 310.5 | 43413
PR | 101 | 02/28/25 | 538 | Johnson, Jake E | 5 | 260 | 43421
PR | 101 | 03/07/25 | 43 | Gerard, Jeffrey S | 4 | 276 | 13423
PR | 101 | 03/07/25 | 51 | Johnson, Jake E | 7 | 364 | 13431
PR | 101 | 03/14/25 | 243 | Gerard, Jeffrey S | 5 | 345 | 23434
PR | 101 | 03/14/25 | 251 | Johnson, Jake E | 6 | 312 | 23442
PR | 101 | 03/21/25 | 436 | Gerard, Jeffrey S | 1 | 69 | 93444
PR | 101 | 03/21/25 | 444 | Johnson, Jake E | 6 | 312 | 93452
PR | 101 | 03/28/25 | 591 | Gerard, Jeffrey S | 1 | 69 | 93465
PR | 101 | 03/28/25 | 600 | Johnson, Jake E | 9 | 468 | 93474
PR | 101 | 04/04/25 | 34 | Gerard, Jeffrey S | 3 | 207 | 13476
PR | 101 | 04/04/25 | 43 | Johnson, Jake E | 7 | 364 | 13485
PR | 101 | 04/11/25 | 200 | Barnhart, Joseph N | 1 | 68 | 93472
PR | 101 | 04/11/25 | 214 | Gerard, Jeffrey S | 1 | 69 | 93486
PR | 101 | 04/11/25 | 223 | Johnson, Jake E | 7 | 364 | 93495
PR | 101 | 04/18/25 | 438 | Gerard, Jeffrey S | 3 | 207 | 33496
PR | 101 | 04/18/25 | 447 | Johnson, Jake E | 8 | 416 | 33505
PR | 101 | 04/25/25 | 577 | Gerard, Jeffrey S | 4 | 276 | 43506
PR | 101 | 04/25/25 | 586 | Johnson, Jake E | 2 | 104 | 43515
PR | 101 | 05/02/25 | 31 | Gerard, Jeffrey S | 3 | 207 | 13516
PR | 101 | 05/09/25 | 162 | Barnhart, Joseph N | 2 | 136 | 23511
PR | 101 | 05/09/25 | 174 | Gerard, Jeffrey S | 2 | 138 | 23523
PR | 101 | 05/09/25 | 175 | Gerard, Jordan E | 8 | 480 | 23524
PR | 101 | 05/16/25 | 373 | Gerard, Jeffrey S | 4.5 | 310.5 | 33532
PR | 101 | 05/23/25 | 469 | Gerard, Jeffrey S | 4 | 276 | 43541
PR | 101 | 05/23/25 | 470 | Gerard, Jordan E | 6 | 360 | 43542
PR | 101 | 05/30/25 | 558 | Gerard, Jeffrey S | 1 | 69 | 53550
PR | 101 | 05/30/25 | 559 | Gerard, Jordan E | 1 | 60 | 53551
PR | 101 | 06/06/25 | 46 | Gerard, Jeffrey S | 3 | 207 | 13558
PR | 101 | 06/13/25 | 207 | Gerard, Jeffrey S | 3 | 207 | 23566
PR | 101 | 06/13/25 | 208 | Gerard, Jordan E | 7 | 420 | 23567
PR | 101 | 06/20/25 | 334 | Gerard, Jeffrey S | 1 | 69 | 33573
PR | 101 | 06/20/25 | 334 | Gerard, Jeffrey S | 1 | 69 | 33573
PR | 101 | 06/20/25 | 335 | Gerard, Jordan E | 7 | 420 | 33574
PR | 101 | 06/27/25 | 489 | Gerard, Jeffrey S | 2 | 138 | 43582
PR | 101 | 06/27/25 | 490 | Gerard, Jordan E | 2 | 120 | 43583
PR | 101 | 07/03/25 | 32 | Gerard, Jeffrey S | 2 | 138 | 13589
PR | 101 | 07/03/25 | 33 | Gerard, Jordan E | 1 | 60 | 13590
PR | 101 | 07/11/25 | 157 | Gerard, Jeffrey S | 1 | 69 | 23596
PR | 101 | 07/11/25 | 158 | Gerard, Jordan E | 1 | 60 | 23597
PR | 101 | 07/18/25 | 324 | Gerard, Jeffrey S | 3 | 207 | 33603
PR | 101 | 07/18/25 | 325 | Gerard, Jordan E | 2 | 120 | 33604
PR | 101 | 07/25/25 | 492 | Gerard, Jeffrey S | 3 | 207 | 43610
PR | 101 | 07/25/25 | 493 | Gerard, Jordan E | 6 | 360 | 43611
PR | 101 | 08/01/25 | 26 | Gerard, Jordan E | 3 | 180 | 13617
PR | 101 | 08/08/25 | 156 | Gerard, Jeffrey S | 1 | 69 | 23623
PR | 101 | 08/15/25 | 281 | Gerard, Jeffrey S | 1 | 69 | 33628
PR | 101 | 08/15/25 | 282 | Gerard, Jordan E | 1 | 60 | 33629
PR | 101 | 08/22/25 | 385 | Gerard, Jeffrey S | 3 | 207 | 43635
PR | 101 | 08/22/25 | 386 | Gerard, Jordan E | 5 | 300 | 43636
PR | 101 | 08/29/25 | 548 | Gerard, Jeffrey S | 1 | 69 | 53641
PR | 101 | 09/05/25 | 33 | Gerard, Jeffrey S | 2 | 138 | 13647
PR | 101 | 09/05/25 | 34 | Gerard, Jordan E | 7 | 420 | 13648
PR | 101 | 09/12/25 | 130 | Gerard, Jeffrey S | 1 | 69 | 23652
PR | 101 | 09/12/25 | 131 | Gerard, Jordan E | 6 | 360 | 23653
PR | 101 | 09/19/25 | 262 | Gerard, Jeffrey S | 2 | 138 | 33658
PR | 101 | 09/19/25 | 263 | Gerard, Jordan E | 3 | 180 | 33659
PR | 101 | 09/26/25 | 419 | Barnhart, Joseph N | 0.75 | 51 | 43651
PR | 101 | 09/26/25 | 434 | Gerard, Jordan E | 2 | 120 | 43666
PR | 101 | 10/03/25 | 15 | Barnhart, Joseph N | 1.5 | 102 | 13658
PR | 101 | 10/03/25 | 15 | Barnhart, Joseph N | 1 | 68 | 13658
PR | 101 | 10/03/25 | 30 | Gerard, Jeffrey S | 1 | 69 | 13673
PR | 101 | 10/03/25 | 30 | Gerard, Jeffrey S | 1 | 69 | 13673
PR | 101 | 10/03/25 | 30 | Gerard, Jeffrey S | 1 | 69 | 13673
PR | 101 | 10/03/25 | 31 | Gerard, Jordan E | 0.75 | 45 | 13674
PR | 101 | 10/10/25 | 182 | Gerard, Jeffrey S | 1 | 69 | 23680
PR | 101 | 10/10/25 | 182 | Gerard, Jeffrey S | 1 | 69 | 23680
PR | 101 | 10/10/25 | 182 | Gerard, Jeffrey S | 1 | 69 | 23680
PR | 101 | 10/17/25 | 387 | Gerard, Jeffrey S | 1 | 69 | 33688
PR | 101 | 10/17/25 | 387 | Gerard, Jeffrey S | 1 | 69 | 33688
PR | 101 | 10/17/25 | 388 | Gerard, Jordan E | 1 | 60 | 33689
PR | 101 | 10/17/25 | 388 | Gerard, Jordan E | 2 | 120 | 33689
PR | 101 | 10/24/25 | 522 | Gerard, Jordan E | 2.25 | 135 | 43698
PR | 101 | 10/24/25 | 522 | Gerard, Jordan E | 2 | 120 | 43698
PR | 101 | 10/24/25 | 522 | Gerard, Jordan E | 1.25 | 75 | 43698
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 3.5 | 210 | 53705
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 1.25 | 75 | 53705
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 1.5 | 90 | 53705
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 0.75 | 45 | 53705
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 0.75 | 45 | 53705
PR | 101 | 10/31/25 | 688 | Gerard, Jordan E | 0.75 | 45 | 53705
PR | 101 | 11/07/25 | 75 | Gerard, Jeffrey S | 0.5 | 34.5 | 13709
PR | 101 | 11/07/25 | 76 | Gerard, Jordan E | 1 | 60 | 13710
PR | 101 | 11/07/25 | 76 | Gerard, Jordan E | 1.75 | 105 | 13710
PR | 101 | 11/07/25 | 76 | Gerard, Jordan E | 3.5 | 210 | 13710
PR | 101 | 11/14/25 | 219 | Barnhart, Joseph N | 0.25 | 17 | 23699
PR | 101 | 11/14/25 | 235 | Gerard, Jeffrey S | 1 | 69 | 23715
PR | 101 | 11/14/25 | 236 | Gerard, Jordan E | 1.25 | 75 | 23716
PR | 101 | 11/14/25 | 236 | Gerard, Jordan E | 3 | 180 | 23716
PR | 101 | 11/14/25 | 236 | Gerard, Jordan E | 6.5 | 390 | 23716
PR | 101 | 11/14/25 | 236 | Gerard, Jordan E | 2.25 | 135 | 23716
PR | 101 | 11/21/25 | 352 | Gerard, Jeffrey S | 0.5 | 34.5 | 33721
PR | 101 | 11/21/25 | 352 | Gerard, Jeffrey S | 0.5 | 34.5 | 33721
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 2.75 | 165 | 33722
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 2.25 | 135 | 33722
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 3.25 | 195 | 33722
PR | 101 | 11/28/25 | 537 | Gerard, Jordan E | 0.75 | 45 | 43727
PR | 101 | 11/28/25 | 537 | Gerard, Jordan E | 3.75 | 225 | 43727
PR | 101 | 11/28/25 | 537 | Gerard, Jordan E | 1.5 | 90 | 43727
PR | 101 | 11/28/25 | 537 | Gerard, Jordan E | 1.75 | 105 | 43727
PR | 101 | 11/28/25 | 537 | Gerard, Jordan E | 1.25 | 75 | 43727
PR | 101 | 12/05/25 | 63 | Gerard, Jordan E | 1.25 | 75 | 13731
PR | 101 | 12/05/25 | 63 | Gerard, Jordan E | 2.5 | 150 | 13731
PR | 101 | 12/05/25 | 63 | Gerard, Jordan E | 2 | 120 | 13731
PR | 101 | 12/12/25 | 200 | Gerard, Jordan E | 2 | 120 | 23735
PR | 101 | 12/12/25 | 200 | Gerard, Jordan E | 2.75 | 165 | 23735
PR | 101 | 12/12/25 | 200 | Gerard, Jordan E | 4.75 | 285 | 23735
PR | 101 | 12/12/25 | 200 | Gerard, Jordan E | 5.25 | 315 | 23735
PR | 101 | 12/19/25 | 341 | Gerard, Jordan E | 1.75 | 105 | 33739
PR | 101 | 12/19/25 | 341 | Gerard, Jordan E | 2.5 | 150 | 33739
PR | 101 | 12/19/25 | 341 | Gerard, Jordan E | 2.5 | 150 | 33739
PR | 101 | 12/26/25 | 529 | Gerard, Jordan E | 2.75 | 165 | 43747
PR | 101 | 12/26/25 | 529 | Gerard, Jordan E | 3 | 180 | 43747
PR | 101 | 12/26/25 | 529 | Gerard, Jordan E | 2 | 120 | 43747
PR | 101 | 01/02/26 | 33 | Gerard, Jordan E | 2.25 | 135 | 13751
PR | 101 | 01/02/26 | 33 | Gerard, Jordan E | 3.5 | 210 | 13751
PR | 101 | 01/02/26 | 33 | Gerard, Jordan E | 1.25 | 75 | 13751
PR | 101 | 01/09/26 | 148 | Gerard, Jordan E | 1.25 | 73.75 | 23755
PR | 101 | 01/09/26 | 148 | Gerard, Jordan E | 1.5 | 88.5 | 23755
PR | 101 | 01/16/26 | 294 | Gerard, Jordan E | 1.25 | 73.75 | 33759
PR | 101 | 01/16/26 | 294 | Gerard, Jordan E | 1.25 | 73.75 | 33759
PR | 101 | 01/23/26 | 484 | Gerard, Jeffrey S | 0.5 | 34.5 | 43763
PR | 101 | 01/23/26 | 485 | Gerard, Jordan E | 1 | 59 | 43764
PR | 101 | 01/23/26 | 485 | Gerard, Jordan E | 1.75 | 103.25 | 43764
PR | 101 | 01/30/26 | 597 | Gerard, Jeffrey S | 0.5 | 34.5 | 53768
PR | 101 | 01/30/26 | 598 | Gerard, Jordan E | 1.5 | 88.5 | 53769
PR | 101 | 01/30/26 | 598 | Gerard, Jordan E | 1.5 | 88.5 | 53769
PR | 101 | 01/30/26 | 598 | Gerard, Jordan E | 0.25 | 14.75 | 53769
PR | 101 | 02/06/26 | 73 | Gerard, Jordan E | 2.25 | 132.75 | 13773
PR | 101 | 02/06/26 | 73 | Gerard, Jordan E | 3 | 177 | 13773
PR | 101 | 02/13/26 | 204 | Gerard, Jeffrey S | 0.5 | 34.5 | 23777
PR | 101 | 02/13/26 | 205 | Gerard, Jordan E | 2.25 | 132.75 | 23778
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 1.5 | 88.5 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 1.25 | 73.75 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 2.75 | 162.25 | 33785
PR | 101 | 02/27/26 | 468 | Gerard, Jordan E | 2.75 | 162.25 | 43788
PR | 101 | 02/27/26 | 468 | Gerard, Jordan E | 1.5 | 88.5 | 43788
PR | 101 | 02/27/26 | 468 | Gerard, Jordan E | 2.5 | 147.5 | 43788
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 0.75 | 44.25 | 13792
PR | 101 | 04/03/26 | 28 | Gerard, Jordan E | 2.25 | 132.75 | 13808
PR | 110 | 06/07/24 | 81 | Barnhart, Joseph N | 2 | 136 | 2905
PR | 110 | 06/21/24 | 480 | Barnhart, Joseph N | 8 | 544 | 2944
PR | 110 | 06/28/24 | 687 | Barnhart, Joseph N | 6 | 408 | 2960
PR | 110 | 06/28/24 | 716 | Cortes Mendiola, Victor H | 4 | 256 | 92989
PR | 110 | 06/28/24 | 719 | Da Cruz, Eduardo E | 4 | 84 | 92992
PR | 110 | 07/05/24 | 4 | Barnhart, Joseph N | 2 | 136 | 2976
PR | 110 | 07/05/24 | 34 | Da Cruz, Eduardo E | 4 | 84 | 93006
PR | 110 | 07/12/24 | 166 | Anderson, Richard P | 2 | 130 | 2990
PR | 110 | 07/12/24 | 167 | Barnhart, Joseph N | 8.5 | 578 | 2991
PR | 110 | 07/12/24 | 193 | Cortes Mendiola, Victor H | 5 | 320 | 93017
PR | 110 | 07/19/24 | 374 | Anderson, Richard P | 3.5 | 227.5 | 3004
PR | 110 | 07/19/24 | 390 | Barnhart, Joseph N | 16.5 | 1122 | 93020
PR | 110 | 07/19/24 | 391 | Bautista Quintero, Isidoro | 3 | 60 | 93021
PR | 110 | 07/19/24 | 399 | Cortes Mendiola, Victor H | 8 | 512 | 93029
PR | 110 | 07/19/24 | 402 | Da Cruz, Eduardo E | 3 | 63 | 93032
PR | 110 | 07/19/24 | 407 | Eisenhauer, Tommy J | 3 | 171 | 93037
PR | 110 | 07/26/24 | 563 | Anderson, Richard P | 22.5 | 1462.5 | 3015
PR | 110 | 07/26/24 | 573 | Amaya Gonzalez, Edilberto A | 6 | 264 | 93025
PR | 110 | 07/26/24 | 579 | Bautista Quintero, Isidoro | 6 | 120 | 93031
PR | 110 | 07/26/24 | 587 | Cortes Mendiola, Victor H | 26 | 1664 | 93039
PR | 110 | 07/26/24 | 590 | Da Cruz, Eduardo E | 6 | 126 | 93042
PR | 110 | 08/02/24 | 2 | Anderson, Richard P | 13 | 845 | 3025
PR | 110 | 08/02/24 | 13 | Amaya Gonzalez, Edilberto A | 40 | 1760 | 93036
PR | 110 | 08/02/24 | 18 | Barnhart, Joseph N | 18 | 1224 | 93041
PR | 110 | 08/02/24 | 19 | Bautista Quintero, Isidoro | 40 | 800 | 93042
PR | 110 | 08/02/24 | 27 | Cortes Mendiola, Victor H | 40 | 2560 | 93050
PR | 110 | 08/02/24 | 30 | Da Cruz, Eduardo E | 40 | 840 | 93053
PR | 110 | 08/09/24 | 248 | Amaya Gonzalez, Edilberto A | 37 | 1628 | 23048
PR | 110 | 08/09/24 | 253 | Barnhart, Joseph N | 14 | 952 | 23053
PR | 110 | 08/09/24 | 254 | Bautista Quintero, Isidoro | 40 | 800 | 23054
PR | 110 | 08/09/24 | 262 | Cortes Mendiola, Victor H | 38 | 2432 | 23062
PR | 110 | 08/09/24 | 265 | Da Cruz, Eduardo E | 40 | 840 | 23065
PR | 110 | 08/16/24 | 439 | Amaya Gonzalez, Edilberto A | 40 | 1760 | 33059
PR | 110 | 08/16/24 | 444 | Barnhart, Joseph N | 4 | 272 | 33064
PR | 110 | 08/16/24 | 445 | Bautista Quintero, Isidoro | 40 | 800 | 33065
PR | 110 | 08/16/24 | 453 | Cortes Mendiola, Victor H | 40 | 2560 | 33073
PR | 110 | 08/16/24 | 456 | Da Cruz, Eduardo E | 40 | 840 | 33076
PR | 110 | 08/23/24 | 694 | Cruz Reyes, Jose | 4 | 164 | 3063
PR | 110 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A | 32 | 1408 | 43070
PR | 110 | 08/23/24 | 706 | Barnhart, Joseph N | 5 | 340 | 43075
PR | 110 | 08/23/24 | 707 | Bautista Quintero, Isidoro | 32 | 640 | 43076
PR | 110 | 08/23/24 | 715 | Cortes Mendiola, Victor H | 32 | 2048 | 43084
PR | 110 | 08/23/24 | 718 | Da Cruz, Eduardo E | 16 | 336 | 43087
PR | 110 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A | 22 | 968 | 53089
PR | 110 | 08/30/24 | 849 | Barnhart, Joseph N | 4 | 272 | 53094
PR | 110 | 08/30/24 | 850 | Bautista Quintero, Isidoro | 30 | 600 | 53095
PR | 110 | 08/30/24 | 858 | Cortes Mendiola, Victor H | 38 | 2432 | 53103
PR | 110 | 08/30/24 | 896 | Silva Morales, Jair J | 30 | 1020 | 53141
PR | 110 | 09/06/24 | 13 | Cruz Reyes, Jose | 24 | 984 | 3093
PR | 110 | 09/06/24 | 19 | Waites, Thaddeus Z | 7 | 427 | 3099
PR | 110 | 09/06/24 | 20 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 13100
PR | 110 | 09/06/24 | 25 | Barnhart, Joseph N | 8 | 544 | 13105
PR | 110 | 09/06/24 | 26 | Bautista Quintero, Isidoro | 32 | 640 | 13106
PR | 110 | 09/06/24 | 34 | Cortes Mendiola, Victor H | 32 | 2048 | 13114
PR | 110 | 09/06/24 | 73 | Silva Morales, Jair J | 32 | 1088 | 13153
PR | 110 | 09/13/24 | 221 | Cruz Reyes, Jose | 8 | 328 | 3104
PR | 110 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A | 30 | 1530 | 23111
PR | 110 | 09/13/24 | 233 | Barnhart, Joseph N | 7 | 476 | 23116
PR | 110 | 09/13/24 | 234 | Bautista Quintero, Isidoro | 37 | 740 | 23117
PR | 110 | 09/13/24 | 242 | Cortes Mendiola, Victor H | 29 | 1856 | 23125
PR | 110 | 09/13/24 | 280 | Silva Morales, Jair J | 32 | 1088 | 23163
PR | 110 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A | 29 | 1479 | 33124
PR | 110 | 09/20/24 | 405 | Barnhart, Joseph N | 10 | 680 | 33129
PR | 110 | 09/20/24 | 406 | Bautista Quintero, Isidoro | 37 | 740 | 33130
PR | 110 | 09/20/24 | 414 | Cortes Mendiola, Victor H | 35 | 2240 | 33138
PR | 110 | 09/20/24 | 451 | Silva Morales, Jair J | 29 | 986 | 33175
PR | 110 | 09/27/24 | 537 | Amaya Gonzalez, Edilberto A | 37 | 1887 | 43136
PR | 110 | 09/27/24 | 542 | Barnhart, Joseph N | 20 | 1360 | 43141
PR | 110 | 09/27/24 | 543 | Bautista Quintero, Isidoro | 40 | 800 | 43142
PR | 110 | 09/27/24 | 550 | Cortes Mendiola, Victor H | 32 | 2048 | 43149
PR | 110 | 09/27/24 | 587 | Silva Morales, Jair J | 32 | 1088 | 43186
PR | 110 | 10/04/24 | 20 | Waites, Thaddeus Z | 18 | 1098 | 3149
PR | 110 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 13150
PR | 110 | 10/04/24 | 26 | Barnhart, Joseph N | 12 | 816 | 13155
PR | 110 | 10/04/24 | 27 | Bautista Quintero, Isidoro | 24 | 480 | 13156
PR | 110 | 10/04/24 | 34 | Cortes Mendiola, Victor H | 24 | 1536 | 13163
PR | 110 | 10/04/24 | 39 | Eisenhauer, Tommy J | 16 | 912 | 13168
PR | 110 | 10/04/24 | 66 | Ramos Herrera, Franklin J | 16 | 672 | 13195
PR | 110 | 10/04/24 | 71 | Silva Morales, Jair J | 24 | 816 | 13200
PR | 110 | 10/04/24 | 81 | Young, Joshua S | 16 | 432 | 13210
PR | 110 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23162
PR | 110 | 10/11/24 | 233 | Barnhart, Joseph N | 3.5 | 238 | 23167
PR | 110 | 10/11/24 | 234 | Bautista Quintero, Isidoro | 8 | 160 | 23168
PR | 110 | 10/11/24 | 241 | Cortes Mendiola, Victor H | 8 | 512 | 23175
PR | 110 | 10/11/24 | 277 | Silva Morales, Jair J | 8 | 272 | 23211
PR | 110 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 33174
PR | 110 | 10/18/24 | 446 | Barnhart, Joseph N | 10 | 680 | 33179
PR | 110 | 10/18/24 | 447 | Bautista Quintero, Isidoro | 16 | 320 | 33180
PR | 110 | 10/18/24 | 454 | Cortes Mendiola, Victor H | 36 | 2304 | 33187
PR | 110 | 10/18/24 | 489 | Silva Morales, Jair J | 36 | 1224 | 33222
PR | 110 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A | 35 | 1785 | 43186
PR | 110 | 10/25/24 | 594 | Barnhart, Joseph N | 2 | 136 | 43191
PR | 110 | 10/25/24 | 595 | Bautista Quintero, Isidoro | 35 | 700 | 43192
PR | 110 | 10/25/24 | 601 | Cortes Mendiola, Victor H | 28 | 1792 | 43198
PR | 110 | 11/08/24 | 144 | Bautista Quintero, Isidoro | 8 | 160 | 23216
PR | 110 | 11/08/24 | 179 | Portillo Rivera, Josue N | 8 | 176 | 23251
PR | 110 | 11/08/24 | 186 | Silva Morales, Jair J | 8 | 272 | 23258
PR | 110 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A | 4 | 204 | 33222
PR | 110 | 11/15/24 | 364 | Bautista Quintero, Isidoro | 4 | 80 | 33228
PR | 110 | 11/15/24 | 370 | Cortes Mendiola, Victor H | 4 | 256 | 33234
PR | 110 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A | 3 | 153 | 13404
PR | 110 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I | 8 | 352 | 13501
PR | 110 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo | 8 | 336 | 3504
PR | 110 | 05/23/25 | 457 | Barnhart, Joseph N | 2 | 136 | 43529
PR | 110 | 09/19/25 | 253 | Cortes Mendiola, Victor H | 1 | 64 | 33649
PR | 110 | 10/24/25 | 496 | Da Cruz, Eduardo E | 4.75 | 109.25 | 3672
PR | 110 | 10/24/25 | 506 | Bautista Quintero, Isidoro | 4.25 | 102 | 43682
PR | 110 | 10/24/25 | 511 | Cortes Mendiola, Victor H | 5.5 | 352 | 43687
PR | 110 | 10/24/25 | 548 | Silva Morales, Jair J | 4.75 | 161.5 | 43724
PR | 110 | 11/07/25 | 59 | Barnhart, Joseph N | 1 | 68 | 13693
PR | 110 | 12/05/25 | 45 | Barnhart, Joseph N | 5 | 340 | 13713
PR | 110 | 12/12/25 | 182 | Barnhart, Joseph N | 1.75 | 119 | 23717
PR | 110 | 12/19/25 | 323 | Barnhart, Joseph N | 1.25 | 85 | 33721
PR | 110 | 01/02/26 | 21 | Cortes Mendiola, Victor H | 1.25 | 80 | 13739
PR | 110 | 01/16/26 | 276 | Barnhart, Joseph N | 7.25 | 507.5 | 33741
PR | 110 | 01/16/26 | 295 | Gerard, Mitchell J | 1.75 | 110.25 | 33760
PR | 110 | 01/23/26 | 467 | Barnhart, Joseph N | 5 | 350 | 43746
PR | 110 | 01/23/26 | 467 | Barnhart, Joseph N | 2.25 | 157.5 | 43746
PR | 110 | 01/23/26 | 473 | Cortes Mendiola, Victor H | 8 | 528 | 43752
PR | 110 | 01/30/26 | 580 | Barnhart, Joseph N | 1.25 | 87.5 | 53751
PR | 110 | 01/30/26 | 586 | Cortes Mendiola, Victor H | 8 | 528 | 53757
PR | 110 | 01/30/26 | 586 | Cortes Mendiola, Victor H | 5 | 330 | 53757
PR | 110 | 01/30/26 | 599 | Gerard, Mitchell J | 1.5 | 94.5 | 53770
PR | 110 | 02/20/26 | 304 | Barnhart, Joseph N | 0.5 | 35 | 33768
PR | 110 | 02/20/26 | 304 | Barnhart, Joseph N | 2.75 | 192.5 | 33768
PR | 110 | 02/20/26 | 305 | Bautista Quintero, Isidoro | 4.25 | 110.5 | 33769
PR | 110 | 02/20/26 | 305 | Bautista Quintero, Isidoro | 8 | 208 | 33769
PR | 110 | 02/20/26 | 310 | Cortes Mendiola, Victor H | 4.25 | 280.5 | 33774
PR | 110 | 02/20/26 | 310 | Cortes Mendiola, Victor H | 8 | 528 | 33774
PR | 110 | 02/20/26 | 322 | Gerard, Mitchell J | 0.75 | 47.25 | 33786
PR | 110 | 02/20/26 | 322 | Gerard, Mitchell J | 3 | 189 | 33786
PR | 110 | 02/27/26 | 453 | Bautista Quintero, Isidoro | 8 | 208 | 43773
PR | 110 | 02/27/26 | 458 | Cortes Mendiola, Victor H | 8 | 528 | 43778
PR | 110 | 03/06/26 | 65 | Gerard, Mitchell J | 1.75 | 110.25 | 13793
PR | 110 | 03/20/26 | 311 | Barnhart, Joseph N | 2 | 140 | 33784
PR | 110 | 04/03/26 | 12 | Barnhart, Joseph N | 1 | 70 | 13792
PR | 110 | 04/03/26 | 29 | Gerard, Mitchell J | 1 | 63 | 13809
PR | 111 | 09/13/24 | 233 | Barnhart, Joseph N | 2 | 136 | 23116
PR | 111 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A | 30 | 1530 | 13198
PR | 111 | 11/01/24 | 23 | Barnhart, Joseph N | 1 | 68 | 13203
PR | 111 | 11/01/24 | 24 | Bautista Quintero, Isidoro | 24 | 480 | 13204
PR | 111 | 11/01/24 | 30 | Cortes Mendiola, Victor H | 33 | 2112 | 13210
PR | 111 | 11/01/24 | 58 | Portillo Rivera, Josue N | 32 | 704 | 13238
PR | 111 | 11/01/24 | 65 | Silva Morales, Jair J | 37 | 1258 | 13245
PR | 111 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23210
PR | 111 | 11/08/24 | 144 | Bautista Quintero, Isidoro | 8 | 160 | 23216
PR | 111 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A | 12 | 612 | 33222
PR | 111 | 11/15/24 | 364 | Bautista Quintero, Isidoro | 12 | 240 | 33228
PR | 111 | 11/15/24 | 370 | Cortes Mendiola, Victor H | 4 | 256 | 33234
PR | 111 | 11/15/24 | 399 | Portillo Rivera, Josue N | 16 | 352 | 33263
PR | 111 | 11/15/24 | 406 | Silva Morales, Jair J | 16 | 544 | 33270
PR | 111 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A | 16 | 816 | 43235
PR | 111 | 11/22/24 | 519 | Bautista Quintero, Isidoro | 8 | 160 | 43241
PR | 111 | 11/22/24 | 525 | Cortes Mendiola, Victor H | 10 | 640 | 43247
PR | 111 | 11/22/24 | 554 | Portillo Rivera, Josue N | 24 | 528 | 43276
PR | 111 | 11/22/24 | 561 | Silva Morales, Jair J | 32 | 1088 | 43283
PR | 111 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A | 16 | 816 | 53247
PR | 111 | 11/29/24 | 667 | Bautista Quintero, Isidoro | 16 | 320 | 53253
PR | 111 | 11/29/24 | 673 | Cortes Mendiola, Victor H | 15 | 960 | 53259
PR | 111 | 11/29/24 | 702 | Portillo Rivera, Josue N | 8 | 176 | 53288
PR | 111 | 11/29/24 | 709 | Silva Morales, Jair J | 8 | 272 | 53295
PR | 111 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A | 3 | 153 | 13259
PR | 111 | 12/06/24 | 69 | Bautista Quintero, Isidoro | 3 | 60 | 13265
PR | 111 | 12/06/24 | 75 | Cortes Mendiola, Victor H | 1 | 64 | 13271
PR | 111 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A | 16 | 816 | 23280
PR | 111 | 12/13/24 | 251 | Bautista Quintero, Isidoro | 24 | 480 | 23286
PR | 111 | 12/13/24 | 257 | Cortes Mendiola, Victor H | 18 | 1152 | 23292
PR | 111 | 01/10/25 | 185 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 23323
PR | 111 | 01/10/25 | 191 | Bautista Quintero, Isidoro | 8 | 176 | 23329
PR | 111 | 01/10/25 | 192 | Carmona, Raul O | 32 | 1696 | 23330
PR | 111 | 01/10/25 | 218 | Mendoza Morales, Jesus A | 16 | 656 | 23356
PR | 111 | 01/17/25 | 349 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33335
PR | 111 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I | 16 | 704 | 33339
PR | 111 | 01/17/25 | 355 | Bautista Quintero, Isidoro | 32 | 704 | 33341
PR | 111 | 01/17/25 | 356 | Carmona, Raul O | 40 | 2120 | 33342
PR | 111 | 01/17/25 | 360 | Cortes Mendiola, Victor H | 22 | 1408 | 33346
PR | 111 | 01/17/25 | 381 | Mendoza Morales, Jesus A | 32 | 1312 | 33367
PR | 111 | 01/24/25 | 515 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 43345
PR | 111 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I | 24 | 1056 | 43349
PR | 111 | 01/24/25 | 520 | Barnhart, Joseph N | 1.5 | 102 | 43350
PR | 111 | 01/24/25 | 521 | Bautista Quintero, Isidoro | 36 | 792 | 43351
PR | 111 | 01/24/25 | 522 | Carmona, Raul O | 40 | 2120 | 43352
PR | 111 | 01/24/25 | 526 | Cortes Mendiola, Victor H | 28 | 1792 | 43356
PR | 111 | 01/24/25 | 548 | Mendoza Morales, Jesus A | 40 | 1640 | 43378
PR | 111 | 01/31/25 | 707 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 53355
PR | 111 | 01/31/25 | 711 | Balderas Ortiz, Ricardo I | 32 | 1408 | 53359
PR | 111 | 01/31/25 | 713 | Bautista Quintero, Isidoro | 40 | 880 | 53361
PR | 111 | 01/31/25 | 714 | Carmona, Raul O | 40 | 2120 | 53362
PR | 111 | 01/31/25 | 718 | Cortes Mendiola, Victor H | 26 | 1664 | 53366
PR | 111 | 01/31/25 | 736 | Lopez, Maslin A | 8 | 264 | 53384
PR | 111 | 01/31/25 | 740 | Mendoza Morales, Jesus A | 40 | 1640 | 53388
PR | 111 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A | 16 | 816 | 13364
PR | 111 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I | 24 | 1056 | 13368
PR | 111 | 02/07/25 | 43 | Bautista Quintero, Isidoro | 16 | 352 | 13370
PR | 111 | 02/07/25 | 44 | Carmona, Raul O | 32 | 1696 | 13371
PR | 111 | 02/07/25 | 48 | Cortes Mendiola, Victor H | 22 | 1408 | 13375
PR | 111 | 02/07/25 | 70 | Mendoza Morales, Jesus A | 40 | 1640 | 13397
PR | 111 | 02/14/25 | 203 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23373
PR | 111 | 02/14/25 | 207 | Balderas Ortiz, Ricardo I | 40 | 1760 | 23377
PR | 111 | 02/14/25 | 210 | Carmona, Raul O | 32 | 1696 | 23380
PR | 111 | 02/14/25 | 214 | Cortes Mendiola, Victor H | 12 | 768 | 23384
PR | 111 | 02/14/25 | 236 | Mendoza Morales, Jesus A | 24 | 984 | 23406
PR | 111 | 02/21/25 | 318 | Galdamez, Dagoberto A | 16 | 672 | 3380
PR | 111 | 02/21/25 | 320 | Waites, Thaddeus Z | 40 | 2440 | 3382
PR | 111 | 02/21/25 | 321 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33383
PR | 111 | 02/21/25 | 325 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33387
PR | 111 | 02/21/25 | 328 | Carmona, Raul O | 32 | 1696 | 33390
PR | 111 | 02/21/25 | 332 | Cortes Mendiola, Victor H | 5 | 320 | 33394
PR | 111 | 02/21/25 | 336 | Draves, Steven W | 16 | 880 | 33398
PR | 111 | 02/21/25 | 345 | Guerrero Espinoza, Mario | 32 | 960 | 33407
PR | 111 | 02/28/25 | 508 | Galdamez, Dagoberto A | 40 | 1680 | 3391
PR | 111 | 02/28/25 | 510 | Waites, Thaddeus Z | 24 | 1464 | 3393
PR | 111 | 02/28/25 | 511 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 43394
PR | 111 | 02/28/25 | 515 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43398
PR | 111 | 02/28/25 | 518 | Carmona, Raul O | 40 | 2120 | 43401
PR | 111 | 02/28/25 | 522 | Cortes Mendiola, Victor H | 7 | 448 | 43405
PR | 111 | 02/28/25 | 526 | Draves, Steven W | 32 | 1760 | 43409
PR | 111 | 02/28/25 | 535 | Guerrero Espinoza, Mario | 40 | 1200 | 43418
PR | 111 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A | 29 | 1479 | 13404
PR | 111 | 03/07/25 | 28 | Balderas Ortiz, Ricardo I | 40 | 1760 | 13408
PR | 111 | 03/07/25 | 31 | Carmona, Raul O | 40 | 2120 | 13411
PR | 111 | 03/07/25 | 35 | Cortes Mendiola, Victor H | 6 | 384 | 13415
PR | 111 | 03/07/25 | 39 | Draves, Steven W | 16 | 880 | 13419
PR | 111 | 03/07/25 | 48 | Guerrero Espinoza, Mario | 40 | 1200 | 13428
PR | 111 | 03/14/25 | 223 | Waites, Thaddeus Z | 23 | 1403 | 3414
PR | 111 | 03/14/25 | 224 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23415
PR | 111 | 03/14/25 | 228 | Balderas Ortiz, Ricardo I | 40 | 1760 | 23419
PR | 111 | 03/14/25 | 231 | Carmona, Raul O | 40 | 2120 | 23422
PR | 111 | 03/14/25 | 235 | Cortes Mendiola, Victor H | 5 | 320 | 23426
PR | 111 | 03/14/25 | 239 | Draves, Steven W | 38 | 2090 | 23430
PR | 111 | 03/14/25 | 248 | Guerrero Espinoza, Mario | 16 | 480 | 23439
PR | 111 | 03/14/25 | 406 | Waites, Thaddeus Z | 32 | 1952 | 3424
PR | 111 | 03/14/25 | 416 | Waites, Thaddeus Z | 32 | -1952 | 3424
PR | 111 | 03/21/25 | 432 | Draves, Steven W | 40 | 2200 | 93440
PR | 111 | 03/21/25 | 482 | Waites, Thaddeus Z | 32 | 1952 | 3434
PR | 111 | 03/28/25 | 571 | Waites, Thaddeus Z | 40 | 2440 | 3445
PR | 111 | 03/28/25 | 587 | Draves, Steven W | 32 | 1760 | 93461
PR | 111 | 04/04/25 | 14 | Waites, Thaddeus Z | 31 | 1891 | 3456
PR | 111 | 04/04/25 | 30 | Draves, Steven W | 40 | 2200 | 13472
PR | 111 | 04/11/25 | 177 | Waites, Thaddeus Z | 35.5 | 2165.5 | 3466
PR | 111 | 04/11/25 | 202 | Carmona, Raul O | 40 | 2120 | 93474
PR | 111 | 04/11/25 | 206 | Cortes Mendiola, Victor H | 3 | 192 | 93478
PR | 111 | 04/11/25 | 210 | Draves, Steven W | 24 | 1320 | 93482
PR | 111 | 04/18/25 | 416 | Galdamez, Dagoberto A | 32 | 1344 | 3474
PR | 111 | 04/18/25 | 426 | Carmona, Raul O | 40 | 2120 | 33484
PR | 111 | 04/18/25 | 430 | Cortes Mendiola, Victor H | 2 | 128 | 33488
PR | 111 | 04/18/25 | 434 | Draves, Steven W | 32 | 1760 | 33492
PR | 111 | 04/25/25 | 555 | Galdamez, Dagoberto A | 32 | 1344 | 3484
PR | 111 | 04/25/25 | 557 | Waites, Thaddeus Z | 34 | 2074 | 3486
PR | 111 | 04/25/25 | 565 | Carmona, Raul O | 40 | 2120 | 43494
PR | 111 | 04/25/25 | 569 | Cortes Mendiola, Victor H | 4 | 256 | 43498
PR | 111 | 04/25/25 | 573 | Draves, Steven W | 29 | 1595 | 43502
PR | 111 | 05/02/25 | 9 | Galdamez, Dagoberto A | 32 | 1344 | 3494
PR | 111 | 05/02/25 | 11 | Waites, Thaddeus Z | 40 | 2440 | 3496
PR | 111 | 05/02/25 | 19 | Carmona, Raul O | 32 | 1696 | 13504
PR | 111 | 05/02/25 | 23 | Cortes Mendiola, Victor H | 5 | 320 | 13508
PR | 111 | 05/02/25 | 27 | Draves, Steven W | 37 | 2035 | 13512
PR | 111 | 05/09/25 | 154 | Galdamez, Dagoberto A | 24 | 1008 | 3503
PR | 111 | 05/09/25 | 164 | Carmona, Raul O | 40 | 2120 | 23513
PR | 111 | 05/09/25 | 167 | Cortes Mendiola, Victor H | 4 | 256 | 23516
PR | 111 | 05/09/25 | 171 | Draves, Steven W | 21 | 1155 | 23520
PR | 111 | 05/16/25 | 353 | Galdamez, Dagoberto A | 40 | 1680 | 3512
PR | 111 | 05/16/25 | 363 | Carmona, Raul O | 40 | 2120 | 33522
PR | 111 | 05/16/25 | 366 | Cortes Mendiola, Victor H | 4 | 256 | 33525
PR | 111 | 05/16/25 | 370 | Draves, Steven W | 16 | 880 | 33529
PR | 111 | 05/16/25 | 391 | Paco Leyva, Orlando | 2 | 122 | 33550
PR | 111 | 05/23/25 | 449 | Galdamez, Dagoberto A | 24 | 1008 | 3521
PR | 111 | 05/23/25 | 459 | Carmona, Raul O | 32 | 1696 | 43531
PR | 111 | 05/23/25 | 462 | Cortes Mendiola, Victor H | 2 | 128 | 43534
PR | 111 | 05/23/25 | 466 | Draves, Steven W | 39 | 2145 | 43538
PR | 111 | 05/30/25 | 554 | Draves, Steven W | 24 | 1320 | 53546
PR | 111 | 06/06/25 | 42 | Draves, Steven W | 32 | 1760 | 13554
PR | 111 | 07/25/25 | 506 | Mendoza Morales, Jesus A | 1 | 41 | 43624
PR | 111 | 08/22/25 | 371 | Barnhart, Joseph N | 1 | 68 | 43621
PR | 111 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 33639
PR | 111 | 09/19/25 | 249 | Bautista Quintero, Isidoro | 24 | 576 | 33645
PR | 111 | 09/19/25 | 253 | Cortes Mendiola, Victor H | 4 | 256 | 33649
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 3.75 | 191.25 | 43646
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 2.75 | 140.25 | 43646
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 8 | 408 | 43646
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 8 | 408 | 43646
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 8 | 408 | 43646
PR | 111 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A | 8 | 408 | 43646
PR | 111 | 09/26/25 | 419 | Barnhart, Joseph N | 1.25 | 85 | 43651
PR | 111 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13653
PR | 111 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13653
PR | 111 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A | 8 | 408 | 33668
PR | 111 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A | 2 | 102 | 33668
PR | 111 | 10/31/25 | 689 | Gerard, Mitchell J | 3.5 | 213.5 | 53706
PR | 111 | 10/31/25 | 689 | Gerard, Mitchell J | 6 | 366 | 53706
PR | 111 | 12/12/25 | 201 | Gerard, Mitchell J | 0.5 | 30.5 | 23736
PR | 111 | 12/12/25 | 201 | Gerard, Mitchell J | 2.25 | 137.25 | 23736
PR | 111 | 12/19/25 | 342 | Gerard, Mitchell J | 1.5 | 91.5 | 33740
PR | 111 | 12/19/25 | 342 | Gerard, Mitchell J | 0.5 | 30.5 | 33740
PR | 111 | 01/23/26 | 486 | Gerard, Mitchell J | 0.5 | 31.5 | 43765
PR | 111 | 01/23/26 | 486 | Gerard, Mitchell J | 1.25 | 78.75 | 43765
PR | 111 | 03/06/26 | 48 | Barnhart, Joseph N | 0.75 | 52.5 | 13776
PR | 111 | 03/27/26 | 496 | Gerard, Mitchell J | 5.75 | 362.25 | 43805
PR | 111 | 04/03/26 | 12 | Barnhart, Joseph N | 0.5 | 35 | 13792
PR | 111 | 04/03/26 | 12 | Barnhart, Joseph N | 3.25 | 227.5 | 13792
PR | 111 | 04/03/26 | 12 | Barnhart, Joseph N | 2.25 | 157.5 | 13792
PR | 111 | 04/03/26 | 12 | Barnhart, Joseph N | 0.25 | 17.5 | 13792
PR | 112 | 08/23/24 | 694 | Cruz Reyes, Jose | 4 | 164 | 3063
PR | 112 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A | 8 | 352 | 43070
PR | 112 | 08/23/24 | 706 | Barnhart, Joseph N | 6 | 408 | 43075
PR | 112 | 08/23/24 | 707 | Bautista Quintero, Isidoro | 8 | 160 | 43076
PR | 112 | 08/23/24 | 715 | Cortes Mendiola, Victor H | 8 | 512 | 43084
PR | 112 | 08/30/24 | 833 | Anderson, Richard P | 3 | 195 | 3078
PR | 112 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A | 10 | 440 | 53089
PR | 112 | 08/30/24 | 849 | Barnhart, Joseph N | 12 | 816 | 53094
PR | 112 | 08/30/24 | 850 | Bautista Quintero, Isidoro | 10 | 200 | 53095
PR | 112 | 08/30/24 | 858 | Cortes Mendiola, Victor H | 2 | 128 | 53103
PR | 112 | 08/30/24 | 896 | Silva Morales, Jair J | 10 | 340 | 53141
PR | 112 | 09/06/24 | 13 | Cruz Reyes, Jose | 8 | 328 | 3093
PR | 112 | 09/06/24 | 25 | Barnhart, Joseph N | 2 | 136 | 13105
PR | 112 | 09/13/24 | 221 | Cruz Reyes, Jose | 8 | 328 | 3104
PR | 112 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A | 5 | 255 | 23111
PR | 112 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A | 11 | 561 | 33124
PR | 112 | 09/20/24 | 405 | Barnhart, Joseph N | 2 | 136 | 33129
PR | 112 | 09/20/24 | 406 | Bautista Quintero, Isidoro | 3 | 60 | 33130
PR | 112 | 09/20/24 | 414 | Cortes Mendiola, Victor H | 2 | 128 | 33138
PR | 112 | 09/20/24 | 451 | Silva Morales, Jair J | 11 | 374 | 33175
PR | 112 | 09/27/24 | 542 | Barnhart, Joseph N | 4 | 272 | 43141
PR | 112 | 09/27/24 | 587 | Silva Morales, Jair J | 8 | 272 | 43186
PR | 112 | 10/04/24 | 20 | Waites, Thaddeus Z | 6 | 366 | 3149
PR | 112 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13150
PR | 112 | 10/04/24 | 27 | Bautista Quintero, Isidoro | 8 | 160 | 13156
PR | 112 | 10/04/24 | 34 | Cortes Mendiola, Victor H | 9 | 576 | 13163
PR | 112 | 10/04/24 | 71 | Silva Morales, Jair J | 16 | 544 | 13200
PR | 112 | 10/11/24 | 227 | Waites, Thaddeus Z | 5 | 305 | 3161
PR | 112 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A | 16 | 816 | 23162
PR | 112 | 10/11/24 | 233 | Barnhart, Joseph N | 5.5 | 374 | 23167
PR | 112 | 10/11/24 | 234 | Bautista Quintero, Isidoro | 16 | 320 | 23168
PR | 112 | 10/11/24 | 241 | Cortes Mendiola, Victor H | 28 | 1792 | 23175
PR | 112 | 10/11/24 | 277 | Silva Morales, Jair J | 24 | 816 | 23211
PR | 112 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A | 8 | 408 | 33174
PR | 112 | 10/18/24 | 446 | Barnhart, Joseph N | 1 | 68 | 33179
PR | 112 | 10/18/24 | 454 | Cortes Mendiola, Victor H | 4 | 256 | 33187
PR | 112 | 10/18/24 | 489 | Silva Morales, Jair J | 4 | 136 | 33222
PR | 112 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13198
PR | 112 | 11/01/24 | 23 | Barnhart, Joseph N | 1 | 68 | 13203
PR | 112 | 11/01/24 | 24 | Bautista Quintero, Isidoro | 8 | 160 | 13204
PR | 112 | 11/01/24 | 30 | Cortes Mendiola, Victor H | 7 | 448 | 13210
PR | 112 | 11/01/24 | 65 | Silva Morales, Jair J | 3 | 102 | 13245
PR | 112 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A | 26 | 1326 | 23210
PR | 112 | 11/08/24 | 143 | Barnhart, Joseph N | 2 | 136 | 23215
PR | 112 | 11/08/24 | 144 | Bautista Quintero, Isidoro | 10 | 200 | 23216
PR | 112 | 11/08/24 | 150 | Cortes Mendiola, Victor H | 34 | 2176 | 23222
PR | 112 | 11/08/24 | 179 | Portillo Rivera, Josue N | 24 | 528 | 23251
PR | 112 | 11/08/24 | 186 | Silva Morales, Jair J | 32 | 1088 | 23258
PR | 112 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 33222
PR | 112 | 11/15/24 | 363 | Barnhart, Joseph N | 3 | 204 | 33227
PR | 112 | 11/15/24 | 364 | Bautista Quintero, Isidoro | 19 | 380 | 33228
PR | 112 | 11/15/24 | 370 | Cortes Mendiola, Victor H | 27 | 1728 | 33234
PR | 112 | 11/15/24 | 399 | Portillo Rivera, Josue N | 8 | 176 | 33263
PR | 112 | 11/15/24 | 406 | Silva Morales, Jair J | 24 | 816 | 33270
PR | 112 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 43235
PR | 112 | 11/22/24 | 519 | Bautista Quintero, Isidoro | 32 | 640 | 43241
PR | 112 | 11/22/24 | 525 | Cortes Mendiola, Victor H | 28 | 1792 | 43247
PR | 112 | 11/22/24 | 554 | Portillo Rivera, Josue N | 16 | 352 | 43276
PR | 112 | 11/22/24 | 561 | Silva Morales, Jair J | 8 | 272 | 43283
PR | 112 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A | 16 | 816 | 53247
PR | 112 | 11/29/24 | 666 | Barnhart, Joseph N | 4 | 272 | 53252
PR | 112 | 11/29/24 | 667 | Bautista Quintero, Isidoro | 16 | 320 | 53253
PR | 112 | 11/29/24 | 673 | Cortes Mendiola, Victor H | 15 | 960 | 53259
PR | 112 | 11/29/24 | 702 | Portillo Rivera, Josue N | 8 | 176 | 53288
PR | 112 | 11/29/24 | 709 | Silva Morales, Jair J | 16 | 544 | 53295
PR | 112 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13259
PR | 112 | 12/06/24 | 69 | Bautista Quintero, Isidoro | 8 | 160 | 13265
PR | 112 | 12/06/24 | 75 | Cortes Mendiola, Victor H | 20 | 1280 | 13271
PR | 112 | 12/06/24 | 110 | Silva Morales, Jair J | 8 | 272 | 13306
PR | 112 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23280
PR | 112 | 12/13/24 | 250 | Barnhart, Joseph N | 3 | 204 | 23285
PR | 112 | 12/13/24 | 251 | Bautista Quintero, Isidoro | 8 | 160 | 23286
PR | 112 | 12/13/24 | 257 | Cortes Mendiola, Victor H | 8 | 512 | 23292
PR | 112 | 12/13/24 | 276 | Lopez, Maslin A | 8 | 264 | 23311
PR | 112 | 12/13/24 | 292 | Silva Morales, Jair J | 8 | 272 | 23327
PR | 112 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A | 20 | 1020 | 33290
PR | 112 | 12/20/24 | 437 | Barnhart, Joseph N | 1 | 68 | 33295
PR | 112 | 12/20/24 | 438 | Bautista Quintero, Isidoro | 20 | 400 | 33296
PR | 112 | 12/20/24 | 444 | Cortes Mendiola, Victor H | 16 | 1024 | 33302
PR | 112 | 12/27/24 | 556 | Barnhart, Joseph N | 2 | 136 | 43306
PR | 112 | 12/27/24 | 563 | Cortes Mendiola, Victor H | 4 | 256 | 43313
PR | 112 | 01/03/25 | 34 | Cortes Mendiola, Victor H | 4 | 256 | 13323
PR | 112 | 01/03/25 | 63 | Silva Morales, Jair J | 4 | 136 | 13352
PR | 112 | 01/10/25 | 191 | Bautista Quintero, Isidoro | 8 | 176 | 23329
PR | 112 | 01/24/25 | 520 | Barnhart, Joseph N | 1 | 68 | 43350
PR | 112 | 01/24/25 | 521 | Bautista Quintero, Isidoro | 4 | 88 | 43351
PR | 112 | 01/31/25 | 718 | Cortes Mendiola, Victor H | 4 | 256 | 53366
PR | 112 | 02/21/25 | 327 | Bautista Quintero, Isidoro | 3 | 66 | 33389
PR | 112 | 02/21/25 | 332 | Cortes Mendiola, Victor H | 3 | 192 | 33394
PR | 112 | 02/28/25 | 522 | Cortes Mendiola, Victor H | 4 | 256 | 43405
PR | 112 | 11/28/25 | 519 | Barnhart, Joseph N | 3.75 | 255 | 43709
PR | 120 | 06/07/24 | 81 | Barnhart, Joseph N | 2 | 136 | 2905
PR | 120 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A | 5 | 255 | 43186
PR | 120 | 10/25/24 | 594 | Barnhart, Joseph N | 1 | 68 | 43191
PR | 120 | 10/25/24 | 595 | Bautista Quintero, Isidoro | 5 | 100 | 43192
PR | 120 | 10/25/24 | 601 | Cortes Mendiola, Victor H | 12 | 768 | 43198
PR | 120 | 10/25/24 | 629 | Portillo Rivera, Josue N | 24 | 528 | 43226
PR | 120 | 10/25/24 | 636 | Silva Morales, Jair J | 40 | 1360 | 43233
PR | 120 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A | 8 | 408 | 53247
PR | 120 | 11/29/24 | 667 | Bautista Quintero, Isidoro | 8 | 160 | 53253
PR | 120 | 11/29/24 | 673 | Cortes Mendiola, Victor H | 10 | 640 | 53259
PR | 120 | 11/29/24 | 692 | Lopez, Maslin A | 40 | 1320 | 53278
PR | 120 | 11/29/24 | 709 | Silva Morales, Jair J | 16 | 544 | 53295
PR | 120 | 12/06/24 | 51 | Anderson, Richard P | 1 | 65 | 3247
PR | 120 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A | 13 | 663 | 13259
PR | 120 | 12/06/24 | 69 | Bautista Quintero, Isidoro | 5 | 100 | 13265
PR | 120 | 12/06/24 | 75 | Cortes Mendiola, Victor H | 3 | 192 | 13271
PR | 120 | 12/06/24 | 94 | Lopez, Maslin A | 24 | 792 | 13290
PR | 120 | 12/06/24 | 110 | Silva Morales, Jair J | 16 | 544 | 13306
PR | 120 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A | 16 | 816 | 23280
PR | 120 | 12/13/24 | 251 | Bautista Quintero, Isidoro | 8 | 160 | 23286
PR | 120 | 12/13/24 | 257 | Cortes Mendiola, Victor H | 14 | 896 | 23292
PR | 120 | 12/13/24 | 276 | Lopez, Maslin A | 24 | 792 | 23311
PR | 120 | 12/13/24 | 292 | Silva Morales, Jair J | 32 | 1088 | 23327
PR | 120 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A | 20 | 1020 | 33290
PR | 120 | 12/20/24 | 437 | Barnhart, Joseph N | 7 | 476 | 33295
PR | 120 | 12/20/24 | 438 | Bautista Quintero, Isidoro | 20 | 400 | 33296
PR | 120 | 12/20/24 | 444 | Cortes Mendiola, Victor H | 24 | 1536 | 33302
PR | 120 | 12/20/24 | 462 | Lopez, Maslin A | 32 | 1056 | 33320
PR | 120 | 12/20/24 | 479 | Silva Morales, Jair J | 40 | 1360 | 33336
PR | 120 | 12/27/24 | 551 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 43301
PR | 120 | 12/27/24 | 556 | Barnhart, Joseph N | 2 | 136 | 43306
PR | 120 | 12/27/24 | 557 | Bautista Quintero, Isidoro | 24 | 480 | 43307
PR | 120 | 12/27/24 | 563 | Cortes Mendiola, Victor H | 20 | 1280 | 43313
PR | 120 | 12/27/24 | 581 | Lopez, Maslin A | 24 | 792 | 43331
PR | 120 | 12/27/24 | 595 | Silva Morales, Jair J | 24 | 816 | 43345
PR | 120 | 01/03/25 | 29 | Bautista Quintero, Isidoro | 8 | 160 | 13318
PR | 120 | 01/03/25 | 30 | Carmona, Raul O | 16 | 848 | 13319
PR | 120 | 01/03/25 | 34 | Cortes Mendiola, Victor H | 12 | 768 | 13323
PR | 120 | 01/03/25 | 51 | Lopez, Maslin A | 8 | 264 | 13340
PR | 120 | 01/03/25 | 63 | Silva Morales, Jair J | 12 | 408 | 13352
PR | 120 | 01/10/25 | 191 | Bautista Quintero, Isidoro | 16 | 352 | 23329
PR | 120 | 01/10/25 | 196 | Cortes Mendiola, Victor H | 32 | 2048 | 23334
PR | 120 | 01/10/25 | 198 | Cruz Guzman, Joel A | 8 | 408 | 23336
PR | 120 | 01/10/25 | 214 | Lopez, Maslin A | 32 | 1056 | 23352
PR | 120 | 01/10/25 | 227 | Silva Morales, Jair J | 32 | 1088 | 23365
PR | 120 | 01/17/25 | 354 | Barnhart, Joseph N | 9 | 612 | 33340
PR | 120 | 01/17/25 | 360 | Cortes Mendiola, Victor H | 18 | 1152 | 33346
PR | 120 | 01/17/25 | 377 | Lopez, Maslin A | 32 | 1056 | 33363
PR | 120 | 01/17/25 | 391 | Silva Morales, Jair J | 40 | 1360 | 33377
PR | 120 | 01/24/25 | 514 | Waites, Thaddeus Z | 40 | 2440 | 3344
PR | 120 | 01/24/25 | 520 | Barnhart, Joseph N | 8 | 544 | 43350
PR | 120 | 01/24/25 | 526 | Cortes Mendiola, Victor H | 12 | 768 | 43356
PR | 120 | 01/24/25 | 528 | Cruz Guzman, Joel A | 40 | 2040 | 43358
PR | 120 | 01/24/25 | 530 | Draves, Steven W | 5 | 275 | 43360
PR | 120 | 01/24/25 | 544 | Lopez, Maslin A | 32 | 1056 | 43374
PR | 120 | 01/24/25 | 558 | Silva Morales, Jair J | 32 | 1088 | 43388
PR | 120 | 01/31/25 | 706 | Waites, Thaddeus Z | 40 | 2440 | 3354
PR | 120 | 01/31/25 | 712 | Barnhart, Joseph N | 5 | 340 | 53360
PR | 120 | 01/31/25 | 718 | Cortes Mendiola, Victor H | 10 | 640 | 53366
PR | 120 | 01/31/25 | 720 | Cruz Guzman, Joel A | 40 | 2040 | 53368
PR | 120 | 01/31/25 | 749 | Silva Morales, Jair J | 40 | 1360 | 53397
PR | 120 | 02/07/25 | 36 | Waites, Thaddeus Z | 24 | 1464 | 3363
PR | 120 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A | 16 | 816 | 13364
PR | 120 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I | 16 | 704 | 13368
PR | 120 | 02/07/25 | 43 | Bautista Quintero, Isidoro | 16 | 352 | 13370
PR | 120 | 02/07/25 | 48 | Cortes Mendiola, Victor H | 18 | 1152 | 13375
PR | 120 | 02/07/25 | 50 | Cruz Guzman, Joel A | 32 | 1632 | 13377
PR | 120 | 02/07/25 | 52 | Draves, Steven W | 22 | 1210 | 13379
PR | 120 | 02/07/25 | 80 | Silva Morales, Jair J | 32 | 1088 | 13407
PR | 120 | 02/14/25 | 201 | Hernandez Gonzalez, Osbaldo | 32 | 1344 | 3371
PR | 120 | 02/14/25 | 202 | Waites, Thaddeus Z | 32 | 1952 | 3372
PR | 120 | 02/14/25 | 208 | Barnhart, Joseph N | 9 | 612 | 23378
PR | 120 | 02/14/25 | 209 | Bautista Quintero, Isidoro | 40 | 880 | 23379
PR | 120 | 02/14/25 | 214 | Cortes Mendiola, Victor H | 28 | 1792 | 23384
PR | 120 | 02/14/25 | 216 | Cruz Guzman, Joel A | 32 | 1632 | 23386
PR | 120 | 02/14/25 | 223 | Gerard, Jordan E | 8 | 480 | 23393
PR | 120 | 02/14/25 | 224 | Gochez Molina, Douglas O | 40 | 1000 | 23394
PR | 120 | 02/14/25 | 227 | Guerrero Espinoza, Mario | 24 | 720 | 23397
PR | 120 | 02/14/25 | 240 | Perez Araque, Manuel A | 40 | 1000 | 23410
PR | 120 | 02/14/25 | 241 | Portillo Soriano, Walter A | 40 | 1400 | 23411
PR | 120 | 02/14/25 | 246 | Silva Morales, Jair J | 40 | 1360 | 23416
PR | 120 | 02/14/25 | 249 | Taylor, Evan R | 8 | 416 | 23419
PR | 120 | 02/21/25 | 311 | Anderson, Richard P | 1 | 65 | 3373
PR | 120 | 02/21/25 | 319 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3381
PR | 120 | 02/21/25 | 326 | Barnhart, Joseph N | 3 | 204 | 33388
PR | 120 | 02/21/25 | 327 | Bautista Quintero, Isidoro | 37 | 814 | 33389
PR | 120 | 02/21/25 | 332 | Cortes Mendiola, Victor H | 29 | 1856 | 33394
PR | 120 | 02/21/25 | 334 | Cruz Guzman, Joel A | 32 | 1632 | 33396
PR | 120 | 02/21/25 | 341 | Gerard, Jordan E | 8 | 480 | 33403
PR | 120 | 02/21/25 | 342 | Gochez Molina, Douglas O | 40 | 1000 | 33404
PR | 120 | 02/21/25 | 358 | Perez Araque, Manuel A | 32 | 800 | 33420
PR | 120 | 02/21/25 | 359 | Portillo Soriano, Walter A | 40 | 1400 | 33421
PR | 120 | 02/21/25 | 364 | Silva Morales, Jair J | 40 | 1360 | 33426
PR | 120 | 02/21/25 | 367 | Taylor, Evan R | 24 | 1248 | 33429
PR | 120 | 02/28/25 | 509 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3392
PR | 120 | 02/28/25 | 516 | Barnhart, Joseph N | 7 | 476 | 43399
PR | 120 | 02/28/25 | 517 | Bautista Quintero, Isidoro | 40 | 880 | 43400
PR | 120 | 02/28/25 | 521 | Cornejo Orellana, Carlos E | 24 | 840 | 43404
PR | 120 | 02/28/25 | 522 | Cortes Mendiola, Victor H | 26 | 1664 | 43405
PR | 120 | 02/28/25 | 524 | Cruz Guzman, Joel A | 40 | 2040 | 43407
PR | 120 | 02/28/25 | 532 | Gochez Molina, Douglas O | 40 | 1000 | 43415
PR | 120 | 02/28/25 | 537 | Jimenez Alvarenga, Gerson M | 24 | 936 | 43420
PR | 120 | 02/28/25 | 548 | Perez Araque, Manuel A | 40 | 1000 | 43431
PR | 120 | 02/28/25 | 549 | Portillo Soriano, Walter A | 40 | 1400 | 43432
PR | 120 | 02/28/25 | 551 | Rodriguez Arevalos, Christian | 24 | 1224 | 43434
PR | 120 | 02/28/25 | 554 | Silva Morales, Jair J | 40 | 1360 | 43437
PR | 120 | 02/28/25 | 557 | Taylor, Evan R | 40 | 2080 | 43440
PR | 120 | 03/07/25 | 18 | Cruz Reyes, Jose | 16 | 656 | 3398
PR | 120 | 03/07/25 | 21 | Galdamez, Dagoberto A | 32 | 1344 | 3401
PR | 120 | 03/07/25 | 22 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3402
PR | 120 | 03/07/25 | 23 | Waites, Thaddeus Z | 40 | 2440 | 3403
PR | 120 | 03/07/25 | 29 | Barnhart, Joseph N | 3.5 | 238 | 13409
PR | 120 | 03/07/25 | 30 | Bautista Quintero, Isidoro | 40 | 880 | 13410
PR | 120 | 03/07/25 | 34 | Cornejo Orellana, Carlos E | 40 | 1400 | 13414
PR | 120 | 03/07/25 | 35 | Cortes Mendiola, Victor H | 31 | 1984 | 13415
PR | 120 | 03/07/25 | 37 | Cruz Guzman, Joel A | 32 | 1632 | 13417
PR | 120 | 03/07/25 | 45 | Gochez Molina, Douglas O | 32 | 800 | 13425
PR | 120 | 03/07/25 | 50 | Jimenez Alvarenga, Gerson M | 24 | 936 | 13430
PR | 120 | 03/07/25 | 61 | Perez Araque, Manuel A | 24 | 600 | 13441
PR | 120 | 03/07/25 | 62 | Portillo Soriano, Walter A | 40 | 1400 | 13442
PR | 120 | 03/07/25 | 64 | Rodriguez Arevalos, Christian | 40 | 2040 | 13444
PR | 120 | 03/07/25 | 67 | Silva Morales, Jair J | 40 | 1360 | 13447
PR | 120 | 03/07/25 | 68 | Suniga Aviles, Kelvin A | 40 | 840 | 13448
PR | 120 | 03/07/25 | 70 | Taylor, Evan R | 24 | 1248 | 13450
PR | 120 | 03/07/25 | 78 | Zuniga Avilez, Eduar A | 40 | 880 | 13458
PR | 120 | 03/14/25 | 222 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3413
PR | 120 | 03/14/25 | 229 | Barnhart, Joseph N | 10 | 680 | 23420
PR | 120 | 03/14/25 | 230 | Bautista Quintero, Isidoro | 40 | 880 | 23421
PR | 120 | 03/14/25 | 234 | Cornejo Orellana, Carlos E | 32 | 1120 | 23425
PR | 120 | 03/14/25 | 235 | Cortes Mendiola, Victor H | 35 | 2240 | 23426
PR | 120 | 03/14/25 | 237 | Cruz Guzman, Joel A | 32 | 1632 | 23428
PR | 120 | 03/14/25 | 245 | Gochez Molina, Douglas O | 40 | 1000 | 23436
PR | 120 | 03/14/25 | 250 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 23441
PR | 120 | 03/14/25 | 253 | Lopez, Maslin A | 16 | 528 | 23444
PR | 120 | 03/14/25 | 264 | Rodriguez Arevalos, Christian | 40 | 2040 | 23455
PR | 120 | 03/14/25 | 267 | Silva Morales, Jair J | 32 | 1088 | 23458
PR | 120 | 03/14/25 | 268 | Suniga Aviles, Kelvin A | 40 | 840 | 23459
PR | 120 | 03/14/25 | 270 | Taylor, Evan R | 38 | 1976 | 23461
PR | 120 | 03/14/25 | 278 | Zuniga Avilez, Eduar A | 40 | 880 | 23469
PR | 120 | 03/14/25 | 401 | Cruz Reyes, Jose | 32 | 1312 | 3419
PR | 120 | 03/14/25 | 404 | Galdamez, Dagoberto A | 40 | 1680 | 3422
PR | 120 | 03/14/25 | 405 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3423
PR | 120 | 03/14/25 | 411 | Cruz Reyes, Jose | 32 | -1312 | 3419
PR | 120 | 03/14/25 | 414 | Galdamez, Dagoberto A | 40 | -1680 | 3422
PR | 120 | 03/14/25 | 415 | Hernandez Gonzalez, Osbaldo | 24 | -1008 | 3423
PR | 120 | 03/21/25 | 417 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 93425
PR | 120 | 03/21/25 | 420 | Ascencio, Jose L | 32 | 1344 | 93428
PR | 120 | 03/21/25 | 421 | Balderas Ortiz, Ricardo I | 40 | 1760 | 93429
PR | 120 | 03/21/25 | 422 | Barnhart, Joseph N | 16.5 | 1122 | 93430
PR | 120 | 03/21/25 | 423 | Bautista Quintero, Isidoro | 40 | 880 | 93431
PR | 120 | 03/21/25 | 424 | Carmona, Raul O | 32 | 1696 | 93432
PR | 120 | 03/21/25 | 427 | Cornejo Orellana, Carlos E | 32 | 1120 | 93435
PR | 120 | 03/21/25 | 428 | Cortes Mendiola, Victor H | 32 | 2048 | 93436
PR | 120 | 03/21/25 | 430 | Cruz Guzman, Joel A | 40 | 2040 | 93438
PR | 120 | 03/21/25 | 438 | Gochez Molina, Douglas O | 40 | 1000 | 93446
PR | 120 | 03/21/25 | 441 | Guerrero Espinoza, Mario | 8 | 240 | 93449
PR | 120 | 03/21/25 | 443 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 93451
PR | 120 | 03/21/25 | 446 | Lopez, Maslin A | 8 | 264 | 93454
PR | 120 | 03/21/25 | 454 | Perez Araque, Manuel A | 32 | 800 | 93462
PR | 120 | 03/21/25 | 455 | Portillo Soriano, Walter A | 40 | 1400 | 93463
PR | 120 | 03/21/25 | 458 | Rodriguez Arevalos, Christian | 40 | 2040 | 93466
PR | 120 | 03/21/25 | 461 | Silva Morales, Jair J | 40 | 1360 | 93469
PR | 120 | 03/21/25 | 462 | Suniga Aviles, Kelvin A | 40 | 840 | 93470
PR | 120 | 03/21/25 | 464 | Taylor, Evan R | 40 | 2080 | 93472
PR | 120 | 03/21/25 | 472 | Zuniga Avilez, Eduar A | 40 | 880 | 93480
PR | 120 | 03/21/25 | 477 | Cruz Reyes, Jose | 32 | 1312 | 3429
PR | 120 | 03/21/25 | 480 | Galdamez, Dagoberto A | 40 | 1680 | 3432
PR | 120 | 03/21/25 | 481 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3433
PR | 120 | 03/28/25 | 566 | Cruz Reyes, Jose | 32 | 1312 | 3440
PR | 120 | 03/28/25 | 567 | Del Villar, Flabio | 8 | 200 | 3441
PR | 120 | 03/28/25 | 569 | Galdamez, Dagoberto A | 32 | 1344 | 3443
PR | 120 | 03/28/25 | 570 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3444
PR | 120 | 03/28/25 | 572 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 93446
PR | 120 | 03/28/25 | 575 | Ascencio, Jose L | 40 | 1680 | 93449
PR | 120 | 03/28/25 | 576 | Balderas Ortiz, Ricardo I | 40 | 1760 | 93450
PR | 120 | 03/28/25 | 577 | Barnhart, Joseph N | 3 | 204 | 93451
PR | 120 | 03/28/25 | 578 | Bautista Quintero, Isidoro | 40 | 880 | 93452
PR | 120 | 03/28/25 | 579 | Carmona, Raul O | 40 | 2120 | 93453
PR | 120 | 03/28/25 | 582 | Cornejo Orellana, Carlos E | 40 | 1400 | 93456
PR | 120 | 03/28/25 | 583 | Cortes Mendiola, Victor H | 35 | 2240 | 93457
PR | 120 | 03/28/25 | 585 | Cruz Guzman, Joel A | 32 | 1632 | 93459
PR | 120 | 03/28/25 | 593 | Gerard, Mitchell J | 24 | 1464 | 93467
PR | 120 | 03/28/25 | 594 | Gochez Molina, Douglas O | 40 | 1000 | 93468
PR | 120 | 03/28/25 | 597 | Guerrero Espinoza, Mario | 40 | 1200 | 93471
PR | 120 | 03/28/25 | 599 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 93473
PR | 120 | 03/28/25 | 602 | Lopez, Maslin A | 40 | 1320 | 93476
PR | 120 | 03/28/25 | 606 | Melgar Moz, Brandon | 8 | 176 | 93480
PR | 120 | 03/28/25 | 612 | Portillo Soriano, Walter A | 40 | 1400 | 93486
PR | 120 | 03/28/25 | 615 | Rodriguez Arevalos, Christian | 40 | 2040 | 93489
PR | 120 | 03/28/25 | 617 | Ross, Kelli M | 8 | 408 | 93491
PR | 120 | 03/28/25 | 618 | Silva Morales, Jair J | 40 | 1360 | 93492
PR | 120 | 03/28/25 | 619 | Suniga Aviles, Kelvin A | 40 | 840 | 93493
PR | 120 | 03/28/25 | 621 | Taylor, Evan R | 32 | 1664 | 93495
PR | 120 | 03/28/25 | 629 | Zuniga Avilez, Eduar A | 40 | 880 | 93503
PR | 120 | 04/04/25 | 9 | Cruz Reyes, Jose | 40 | 1640 | 3451
PR | 120 | 04/04/25 | 10 | Del Villar, Flabio | 16 | 400 | 3452
PR | 120 | 04/04/25 | 12 | Galdamez, Dagoberto A | 16 | 672 | 3454
PR | 120 | 04/04/25 | 13 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3455
PR | 120 | 04/04/25 | 15 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 13457
PR | 120 | 04/04/25 | 18 | Ascencio, Jose L | 40 | 1680 | 13460
PR | 120 | 04/04/25 | 19 | Balderas Ortiz, Ricardo I | 40 | 1760 | 13461
PR | 120 | 04/04/25 | 20 | Barnhart, Joseph N | 9 | 612 | 13462
PR | 120 | 04/04/25 | 21 | Bautista Quintero, Isidoro | 40 | 880 | 13463
PR | 120 | 04/04/25 | 22 | Carmona, Raul O | 40 | 2120 | 13464
PR | 120 | 04/04/25 | 25 | Cornejo Orellana, Carlos E | 32 | 1120 | 13467
PR | 120 | 04/04/25 | 26 | Cortes Mendiola, Victor H | 35 | 2240 | 13468
PR | 120 | 04/04/25 | 28 | Cruz Guzman, Joel A | 40 | 2040 | 13470
PR | 120 | 04/04/25 | 37 | Gochez Molina, Douglas O | 40 | 1000 | 13479
PR | 120 | 04/04/25 | 40 | Guerrero Espinoza, Mario | 32 | 960 | 13482
PR | 120 | 04/04/25 | 42 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 13484
PR | 120 | 04/04/25 | 45 | Lopez, Maslin A | 32 | 1056 | 13487
PR | 120 | 04/04/25 | 49 | Melgar Moz, Brandon | 16 | 352 | 13491
PR | 120 | 04/04/25 | 53 | Paco Leyva, Orlando | 8 | 488 | 13495
PR | 120 | 04/04/25 | 55 | Portillo Soriano, Walter A | 40 | 1400 | 13497
PR | 120 | 04/04/25 | 58 | Rodriguez Arevalos, Christian | 40 | 2040 | 13500
PR | 120 | 04/04/25 | 60 | Ross, Kelli M | 40 | 2040 | 13502
PR | 120 | 04/04/25 | 61 | Silva Morales, Jair J | 32 | 1088 | 13503
PR | 120 | 04/04/25 | 62 | Suniga Aviles, Kelvin A | 38 | 798 | 13504
PR | 120 | 04/04/25 | 64 | Taylor, Evan R | 32 | 1664 | 13506
PR | 120 | 04/04/25 | 71 | Zuniga Avilez, Eduar A | 38 | 836 | 13513
PR | 120 | 04/11/25 | 172 | Cruz Reyes, Jose | 40 | 1640 | 3461
PR | 120 | 04/11/25 | 173 | Del Villar, Flabio | 40 | 1760 | 3462
PR | 120 | 04/11/25 | 175 | Galdamez, Dagoberto A | 16 | 672 | 3464
PR | 120 | 04/11/25 | 176 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3465
PR | 120 | 04/11/25 | 195 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 93467
PR | 120 | 04/11/25 | 198 | Ascencio, Jose L | 40 | 1680 | 93470
PR | 120 | 04/11/25 | 199 | Balderas Ortiz, Ricardo I | 40 | 1760 | 93471
PR | 120 | 04/11/25 | 200 | Barnhart, Joseph N | 6 | 408 | 93472
PR | 120 | 04/11/25 | 201 | Bautista Quintero, Isidoro | 40 | 880 | 93473
PR | 120 | 04/11/25 | 205 | Cornejo Orellana, Carlos E | 40 | 1400 | 93477
PR | 120 | 04/11/25 | 206 | Cortes Mendiola, Victor H | 37 | 2368 | 93478
PR | 120 | 04/11/25 | 208 | Cruz Guzman, Joel A | 32 | 1632 | 93480
PR | 120 | 04/11/25 | 217 | Gochez Molina, Douglas O | 40 | 1000 | 93489
PR | 120 | 04/11/25 | 220 | Guerrero Espinoza, Mario | 16 | 480 | 93492
PR | 120 | 04/11/25 | 222 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 93494
PR | 120 | 04/11/25 | 225 | Lopez, Maslin A | 40 | 1320 | 93497
PR | 120 | 04/11/25 | 228 | McCabe, Thomas C | 24 | 1056 | 93500
PR | 120 | 04/11/25 | 229 | Melgar Moz, Brandon | 40 | 880 | 93501
PR | 120 | 04/11/25 | 231 | Merino Martinez, Humberto | 16 | 448 | 93503
PR | 120 | 04/11/25 | 235 | Portillo Soriano, Walter A | 40 | 1400 | 93507
PR | 120 | 04/11/25 | 238 | Rodriguez Arevalos, Christian | 40 | 2040 | 93510
PR | 120 | 04/11/25 | 240 | Ross, Kelli M | 32 | 1632 | 93512
PR | 120 | 04/11/25 | 241 | Silva Morales, Jair J | 40 | 1360 | 93513
PR | 120 | 04/11/25 | 242 | Suniga Aviles, Kelvin A | 24 | 504 | 93514
PR | 120 | 04/11/25 | 244 | Taylor, Evan R | 32 | 1664 | 93516
PR | 120 | 04/11/25 | 251 | Zuniga Avilez, Eduar A | 32 | 704 | 93523
PR | 120 | 04/18/25 | 413 | Cruz Reyes, Jose | 40 | 1640 | 3471
PR | 120 | 04/18/25 | 414 | Del Villar, Flabio | 20 | 880 | 3472
PR | 120 | 04/18/25 | 417 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3475
PR | 120 | 04/18/25 | 418 | Waites, Thaddeus Z | 36 | 2196 | 3476
PR | 120 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33477
PR | 120 | 04/18/25 | 422 | Ascencio, Jose L | 40 | 1680 | 33480
PR | 120 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33481
PR | 120 | 04/18/25 | 424 | Barnhart, Joseph N | 15 | 1020 | 33482
PR | 120 | 04/18/25 | 425 | Bautista Quintero, Isidoro | 40 | 880 | 33483
PR | 120 | 04/18/25 | 429 | Cornejo Orellana, Carlos E | 32 | 1120 | 33487
PR | 120 | 04/18/25 | 430 | Cortes Mendiola, Victor H | 35 | 2240 | 33488
PR | 120 | 04/18/25 | 432 | Cruz Guzman, Joel A | 40 | 2040 | 33490
PR | 120 | 04/18/25 | 441 | Gochez Molina, Douglas O | 40 | 1000 | 33499
PR | 120 | 04/18/25 | 444 | Guerrero Espinoza, Mario | 40 | 1200 | 33502
PR | 120 | 04/18/25 | 448 | Lima Romero, Melvin A | 24 | 1056 | 33506
PR | 120 | 04/18/25 | 449 | Lopez, Maslin A | 32 | 1056 | 33507
PR | 120 | 04/18/25 | 452 | McCabe, Thomas C | 40 | 1760 | 33510
PR | 120 | 04/18/25 | 453 | Melgar Moz, Brandon | 28 | 616 | 33511
PR | 120 | 04/18/25 | 455 | Merino Martinez, Humberto | 40 | 1120 | 33513
PR | 120 | 04/18/25 | 459 | Portillo Soriano, Walter A | 40 | 1400 | 33517
PR | 120 | 04/18/25 | 462 | Rodriguez Arevalos, Christian | 40 | 2040 | 33520
PR | 120 | 04/18/25 | 464 | Ross, Kelli M | 40 | 2040 | 33522
PR | 120 | 04/18/25 | 465 | Silva Morales, Jair J | 40 | 1360 | 33523
PR | 120 | 04/18/25 | 466 | Suniga Aviles, Kelvin A | 40 | 840 | 33524
PR | 120 | 04/18/25 | 468 | Taylor, Evan R | 16 | 832 | 33526
PR | 120 | 04/18/25 | 475 | Zuniga Avilez, Eduar A | 40 | 880 | 33533
PR | 120 | 04/25/25 | 550 | Castro, Marcus J | 16 | 352 | 3479
PR | 120 | 04/25/25 | 552 | Cruz Reyes, Jose | 40 | 1640 | 3481
PR | 120 | 04/25/25 | 553 | Del Villar, Flabio | 24 | 1056 | 3482
PR | 120 | 04/25/25 | 556 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3485
PR | 120 | 04/25/25 | 558 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 43487
PR | 120 | 04/25/25 | 559 | Aquino, Juan | 19 | 513 | 43488
PR | 120 | 04/25/25 | 561 | Ascencio, Jose L | 40 | 1680 | 43490
PR | 120 | 04/25/25 | 562 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43491
PR | 120 | 04/25/25 | 563 | Barnhart, Joseph N | 11 | 748 | 43492
PR | 120 | 04/25/25 | 564 | Bautista Quintero, Isidoro | 40 | 880 | 43493
PR | 120 | 04/25/25 | 568 | Cornejo Orellana, Carlos E | 32 | 1120 | 43497
PR | 120 | 04/25/25 | 569 | Cortes Mendiola, Victor H | 30 | 1920 | 43498
PR | 120 | 04/25/25 | 571 | Cruz Guzman, Joel A | 40 | 2040 | 43500
PR | 120 | 04/25/25 | 580 | Gochez Molina, Douglas O | 40 | 1000 | 43509
PR | 120 | 04/25/25 | 583 | Guerrero Espinoza, Mario | 40 | 1200 | 43512
PR | 120 | 04/25/25 | 585 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 43514
PR | 120 | 04/25/25 | 587 | Lima Romero, Melvin A | 40 | 1760 | 43516
PR | 120 | 04/25/25 | 588 | Lopez, Maslin A | 40 | 1320 | 43517
PR | 120 | 04/25/25 | 591 | McCabe, Thomas C | 40 | 1760 | 43520
PR | 120 | 04/25/25 | 592 | Melgar Moz, Brandon | 40 | 880 | 43521
PR | 120 | 04/25/25 | 598 | Portillo Soriano, Walter A | 32 | 1120 | 43527
PR | 120 | 04/25/25 | 601 | Rodriguez Arevalos, Christian | 40 | 2040 | 43530
PR | 120 | 04/25/25 | 603 | Ross, Kelli M | 16 | 816 | 43532
PR | 120 | 04/25/25 | 604 | Silva Morales, Jair J | 40 | 1360 | 43533
PR | 120 | 04/25/25 | 605 | Suniga Aviles, Kelvin A | 32 | 672 | 43534
PR | 120 | 04/25/25 | 607 | Taylor, Evan R | 24 | 1248 | 43536
PR | 120 | 04/25/25 | 614 | Zuniga Avilez, Eduar A | 32 | 704 | 43543
PR | 120 | 05/02/25 | 4 | Castro, Marcus J | 16 | 352 | 3489
PR | 120 | 05/02/25 | 6 | Cruz Reyes, Jose | 40 | 1640 | 3491
PR | 120 | 05/02/25 | 10 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3495
PR | 120 | 05/02/25 | 12 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 13497
PR | 120 | 05/02/25 | 13 | Aquino, Juan | 8 | 216 | 13498
PR | 120 | 05/02/25 | 15 | Ascencio, Jose L | 32 | 1344 | 13500
PR | 120 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I | 32 | 1408 | 13501
PR | 120 | 05/02/25 | 17 | Barnhart, Joseph N | 6.5 | 442 | 13502
PR | 120 | 05/02/25 | 18 | Bautista Quintero, Isidoro | 40 | 880 | 13503
PR | 120 | 05/02/25 | 22 | Cornejo Orellana, Carlos E | 40 | 1400 | 13507
PR | 120 | 05/02/25 | 23 | Cortes Mendiola, Victor H | 32 | 2048 | 13508
PR | 120 | 05/02/25 | 25 | Cruz Guzman, Joel A | 32 | 1632 | 13510
PR | 120 | 05/02/25 | 34 | Gochez Molina, Douglas O | 40 | 1000 | 13519
PR | 120 | 05/02/25 | 37 | Guerrero Espinoza, Mario | 40 | 1200 | 13522
PR | 120 | 05/02/25 | 39 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 13524
PR | 120 | 05/02/25 | 40 | Lima Romero, Melvin A | 40 | 1760 | 13525
PR | 120 | 05/02/25 | 41 | Lopez, Maslin A | 28 | 924 | 13526
PR | 120 | 05/02/25 | 44 | McCabe, Thomas C | 40 | 1760 | 13529
PR | 120 | 05/02/25 | 45 | Melgar Moz, Brandon | 40 | 880 | 13530
PR | 120 | 05/02/25 | 51 | Portillo Soriano, Walter A | 40 | 1400 | 13536
PR | 120 | 05/02/25 | 54 | Rodriguez Arevalos, Christian | 40 | 2040 | 13539
PR | 120 | 05/02/25 | 56 | Ross, Kelli M | 32 | 1632 | 13541
PR | 120 | 05/02/25 | 57 | Silva Morales, Jair J | 40 | 1360 | 13542
PR | 120 | 05/02/25 | 58 | Suniga Aviles, Kelvin A | 32 | 672 | 13543
PR | 120 | 05/02/25 | 60 | Taylor, Evan R | 40 | 2080 | 13545
PR | 120 | 05/02/25 | 66 | Zuniga Avilez, Eduar A | 40 | 880 | 13551
PR | 120 | 05/09/25 | 151 | Cruz Reyes, Jose | 40 | 1640 | 3500
PR | 120 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3504
PR | 120 | 05/09/25 | 156 | Waites, Thaddeus Z | 40 | 2440 | 3505
PR | 120 | 05/09/25 | 157 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23506
PR | 120 | 05/09/25 | 160 | Ascencio, Jose L | 32 | 1344 | 23509
PR | 120 | 05/09/25 | 161 | Balderas Ortiz, Ricardo I | 40 | 1760 | 23510
PR | 120 | 05/09/25 | 162 | Barnhart, Joseph N | 11 | 748 | 23511
PR | 120 | 05/09/25 | 163 | Bautista Quintero, Isidoro | 40 | 880 | 23512
PR | 120 | 05/09/25 | 166 | Cornejo Orellana, Carlos E | 40 | 1400 | 23515
PR | 120 | 05/09/25 | 167 | Cortes Mendiola, Victor H | 34 | 2176 | 23516
PR | 120 | 05/09/25 | 169 | Cruz Guzman, Joel A | 40 | 2040 | 23518
PR | 120 | 05/09/25 | 177 | Gochez Molina, Douglas O | 40 | 1000 | 23526
PR | 120 | 05/09/25 | 180 | Guerrero Espinoza, Mario | 32 | 960 | 23529
PR | 120 | 05/09/25 | 182 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 23531
PR | 120 | 05/09/25 | 183 | Lima Romero, Melvin A | 40 | 1760 | 23532
PR | 120 | 05/09/25 | 184 | Lopez, Maslin A | 24 | 792 | 23533
PR | 120 | 05/09/25 | 187 | McCabe, Thomas C | 40 | 1760 | 23536
PR | 120 | 05/09/25 | 188 | Melgar Moz, Brandon | 40 | 880 | 23537
PR | 120 | 05/09/25 | 190 | Merino Martinez, Humberto | 40 | 1120 | 23539
PR | 120 | 05/09/25 | 194 | Portillo Soriano, Walter A | 40 | 1400 | 23543
PR | 120 | 05/09/25 | 197 | Rodriguez Arevalos, Christian | 32 | 1632 | 23546
PR | 120 | 05/09/25 | 199 | Ross, Kelli M | 40 | 2040 | 23548
PR | 120 | 05/09/25 | 200 | Silva Morales, Jair J | 40 | 1360 | 23549
PR | 120 | 05/09/25 | 201 | Suniga Aviles, Kelvin A | 40 | 840 | 23550
PR | 120 | 05/09/25 | 203 | Taylor, Evan R | 32 | 1664 | 23552
PR | 120 | 05/09/25 | 207 | Zuniga Avilez, Eduar A | 40 | 880 | 23556
PR | 120 | 05/16/25 | 350 | Cruz Reyes, Jose | 40 | 1640 | 3509
PR | 120 | 05/16/25 | 354 | Hernandez Gonzalez, Osbaldo | 40 | 1680 | 3513
PR | 120 | 05/16/25 | 355 | Waites, Thaddeus Z | 18 | 1098 | 3514
PR | 120 | 05/16/25 | 356 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33515
PR | 120 | 05/16/25 | 359 | Ascencio, Jose L | 40 | 1680 | 33518
PR | 120 | 05/16/25 | 360 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33519
PR | 120 | 05/16/25 | 361 | Barnhart, Joseph N | 6 | 408 | 33520
PR | 120 | 05/16/25 | 362 | Bautista Quintero, Isidoro | 40 | 880 | 33521
PR | 120 | 05/16/25 | 365 | Cornejo Orellana, Carlos E | 32 | 1120 | 33524
PR | 120 | 05/16/25 | 366 | Cortes Mendiola, Victor H | 24 | 1536 | 33525
PR | 120 | 05/16/25 | 368 | Cruz Guzman, Joel A | 40 | 2040 | 33527
PR | 120 | 05/16/25 | 376 | Gochez Molina, Douglas O | 40 | 1000 | 33535
PR | 120 | 05/16/25 | 379 | Guerrero Espinoza, Mario | 40 | 1200 | 33538
PR | 120 | 05/16/25 | 381 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 33540
PR | 120 | 05/16/25 | 382 | Lima Romero, Melvin A | 40 | 1760 | 33541
PR | 120 | 05/16/25 | 383 | Lopez, Maslin A | 32 | 1056 | 33542
PR | 120 | 05/16/25 | 386 | McCabe, Thomas C | 40 | 1760 | 33545
PR | 120 | 05/16/25 | 387 | Melgar Moz, Brandon | 40 | 880 | 33546
PR | 120 | 05/16/25 | 389 | Merino Martinez, Humberto | 40 | 1120 | 33548
PR | 120 | 05/16/25 | 391 | Paco Leyva, Orlando | 6 | 366 | 33550
PR | 120 | 05/16/25 | 393 | Portillo Soriano, Walter A | 40 | 1400 | 33552
PR | 120 | 05/16/25 | 394 | Ramos Herrera, Franklin J | 16 | 672 | 33553
PR | 120 | 05/16/25 | 396 | Rodriguez Arevalos, Christian | 40 | 2040 | 33555
PR | 120 | 05/16/25 | 398 | Ross, Kelli M | 40 | 2040 | 33557
PR | 120 | 05/16/25 | 399 | Silva Morales, Jair J | 40 | 1360 | 33558
PR | 120 | 05/16/25 | 400 | Suniga Aviles, Kelvin A | 32 | 672 | 33559
PR | 120 | 05/16/25 | 402 | Taylor, Evan R | 24 | 1248 | 33561
PR | 120 | 05/16/25 | 406 | Zuniga Avilez, Eduar A | 32 | 704 | 33565
PR | 120 | 05/23/25 | 446 | Cruz Reyes, Jose | 40 | 1640 | 3518
PR | 120 | 05/23/25 | 447 | Del Villar, Flabio | 8 | 352 | 3519
PR | 120 | 05/23/25 | 449 | Galdamez, Dagoberto A | 8 | 336 | 3521
PR | 120 | 05/23/25 | 450 | Hernandez Gonzalez, Osbaldo | 32 | 1344 | 3522
PR | 120 | 05/23/25 | 451 | Waites, Thaddeus Z | 40 | 2440 | 3523
PR | 120 | 05/23/25 | 452 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 43524
PR | 120 | 05/23/25 | 455 | Ascencio, Jose L | 40 | 1680 | 43527
PR | 120 | 05/23/25 | 456 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43528
PR | 120 | 05/23/25 | 457 | Barnhart, Joseph N | 3 | 204 | 43529
PR | 120 | 05/23/25 | 458 | Bautista Quintero, Isidoro | 40 | 880 | 43530
PR | 120 | 05/23/25 | 459 | Carmona, Raul O | 8 | 424 | 43531
PR | 120 | 05/23/25 | 460 | Castro Hernandez, Jose A | 24 | 1296 | 43532
PR | 120 | 05/23/25 | 461 | Cornejo Orellana, Carlos E | 40 | 1400 | 43533
PR | 120 | 05/23/25 | 462 | Cortes Mendiola, Victor H | 32 | 2048 | 43534
PR | 120 | 05/23/25 | 464 | Cruz Guzman, Joel A | 40 | 2040 | 43536
PR | 120 | 05/23/25 | 471 | Gerard, Mitchell J | 4 | 244 | 43543
PR | 120 | 05/23/25 | 472 | Gochez Molina, Douglas O | 40 | 1000 | 43544
PR | 120 | 05/23/25 | 475 | Guerrero Espinoza, Mario | 32 | 960 | 43547
PR | 120 | 05/23/25 | 477 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 43549
PR | 120 | 05/23/25 | 478 | Lima Romero, Melvin A | 40 | 1760 | 43550
PR | 120 | 05/23/25 | 479 | Lopez, Maslin A | 40 | 1320 | 43551
PR | 120 | 05/23/25 | 482 | McCabe, Thomas C | 40 | 1760 | 43554
PR | 120 | 05/23/25 | 483 | Melgar Moz, Brandon | 32 | 704 | 43555
PR | 120 | 05/23/25 | 485 | Merino Martinez, Humberto | 40 | 1120 | 43557
PR | 120 | 05/23/25 | 487 | Paco Leyva, Orlando | 5 | 305 | 43559
PR | 120 | 05/23/25 | 489 | Portillo Soriano, Walter A | 40 | 1400 | 43561
PR | 120 | 05/23/25 | 490 | Ramos Herrera, Franklin J | 40 | 1680 | 43562
PR | 120 | 05/23/25 | 492 | Rodriguez Arevalos, Christian | 40 | 2040 | 43564
PR | 120 | 05/23/25 | 494 | Ross, Kelli M | 32 | 1632 | 43566
PR | 120 | 05/23/25 | 495 | Silva Morales, Jair J | 40 | 1360 | 43567
PR | 120 | 05/23/25 | 496 | Suniga Aviles, Kelvin A | 34 | 714 | 43568
PR | 120 | 05/23/25 | 498 | Taylor, Evan R | 40 | 2080 | 43570
PR | 120 | 05/23/25 | 502 | Zuniga Avilez, Eduar A | 24 | 528 | 43574
PR | 120 | 05/30/25 | 535 | Cruz Reyes, Jose | 24 | 984 | 3527
PR | 120 | 05/30/25 | 537 | Galdamez, Dagoberto A | 8 | 336 | 3529
PR | 120 | 05/30/25 | 538 | Hernandez Gonzalez, Osbaldo | 8 | 336 | 3530
PR | 120 | 05/30/25 | 539 | Waites, Thaddeus Z | 24 | 1464 | 3531
PR | 120 | 05/30/25 | 540 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 53532
PR | 120 | 05/30/25 | 543 | Ascencio, Jose L | 24 | 1008 | 53535
PR | 120 | 05/30/25 | 544 | Balderas Ortiz, Ricardo I | 24 | 1056 | 53536
PR | 120 | 05/30/25 | 545 | Barnhart, Joseph N | 7 | 476 | 53537
PR | 120 | 05/30/25 | 546 | Bautista Quintero, Isidoro | 24 | 528 | 53538
PR | 120 | 05/30/25 | 547 | Carmona, Raul O | 24 | 1272 | 53539
PR | 120 | 05/30/25 | 548 | Castro Hernandez, Jose A | 24 | 1296 | 53540
PR | 120 | 05/30/25 | 549 | Cornejo Orellana, Carlos E | 24 | 840 | 53541
PR | 120 | 05/30/25 | 550 | Cortes Mendiola, Victor H | 24 | 1536 | 53542
PR | 120 | 05/30/25 | 552 | Cruz Guzman, Joel A | 16 | 816 | 53544
PR | 120 | 05/30/25 | 561 | Gochez Molina, Douglas O | 24 | 600 | 53553
PR | 120 | 05/30/25 | 564 | Guerrero Espinoza, Mario | 24 | 720 | 53556
PR | 120 | 05/30/25 | 566 | Jimenez Alvarenga, Gerson M | 24 | 936 | 53558
PR | 120 | 05/30/25 | 567 | Lima Romero, Melvin A | 24 | 1056 | 53559
PR | 120 | 05/30/25 | 568 | Lopez, Maslin A | 24 | 792 | 53560
PR | 120 | 05/30/25 | 571 | McCabe, Thomas C | 24 | 1056 | 53563
PR | 120 | 05/30/25 | 572 | Melgar Moz, Brandon | 8 | 176 | 53564
PR | 120 | 05/30/25 | 574 | Merino Martinez, Humberto | 24 | 672 | 53566
PR | 120 | 05/30/25 | 578 | Portillo Soriano, Walter A | 24 | 840 | 53570
PR | 120 | 05/30/25 | 579 | Ramos Herrera, Franklin J | 24 | 1008 | 53571
PR | 120 | 05/30/25 | 581 | Rodriguez Arevalos, Christian | 24 | 1224 | 53573
PR | 120 | 05/30/25 | 583 | Ross, Kelli M | 24 | 1224 | 53575
PR | 120 | 05/30/25 | 584 | Silva Morales, Jair J | 24 | 816 | 53576
PR | 120 | 05/30/25 | 585 | Suniga Aviles, Kelvin A | 24 | 504 | 53577
PR | 120 | 05/30/25 | 587 | Taylor, Evan R | 24 | 1248 | 53579
PR | 120 | 05/30/25 | 591 | Zuniga Avilez, Eduar A | 24 | 528 | 53583
PR | 120 | 06/06/25 | 22 | Cruz Reyes, Jose | 40 | 1640 | 3535
PR | 120 | 06/06/25 | 25 | Hernandez Gonzalez, Osbaldo | 24 | 1008 | 3538
PR | 120 | 06/06/25 | 26 | Waites, Thaddeus Z | 35 | 2135 | 3539
PR | 120 | 06/06/25 | 28 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 13540
PR | 120 | 06/06/25 | 31 | Ascencio, Jose L | 40 | 1680 | 13543
PR | 120 | 06/06/25 | 32 | Balderas Ortiz, Ricardo I | 40 | 1760 | 13544
PR | 120 | 06/06/25 | 33 | Barnhart, Joseph N | 2 | 136 | 13545
PR | 120 | 06/06/25 | 34 | Bautista Quintero, Isidoro | 40 | 960 | 13546
PR | 120 | 06/06/25 | 35 | Carmona, Raul O | 40 | 2120 | 13547
PR | 120 | 06/06/25 | 36 | Castro Hernandez, Jose A | 40 | 2160 | 13548
PR | 120 | 06/06/25 | 37 | Cornejo Orellana, Carlos E | 40 | 1400 | 13549
PR | 120 | 06/06/25 | 38 | Cortes Mendiola, Victor H | 38 | 2432 | 13550
PR | 120 | 06/06/25 | 40 | Cruz Guzman, Joel A | 16 | 816 | 13552
PR | 120 | 06/06/25 | 49 | Gochez Molina, Douglas O | 40 | 1120 | 13561
PR | 120 | 06/06/25 | 51 | Guerrero Espinoza, Mario | 32 | 960 | 13563
PR | 120 | 06/06/25 | 53 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 13565
PR | 120 | 06/06/25 | 54 | Lima Romero, Melvin A | 40 | 1760 | 13566
PR | 120 | 06/06/25 | 55 | Lopez, Maslin A | 32 | 1056 | 13567
PR | 120 | 06/06/25 | 58 | McCabe, Thomas C | 40 | 1760 | 13570
PR | 120 | 06/06/25 | 61 | Merino Martinez, Humberto | 24 | 672 | 13573
PR | 120 | 06/06/25 | 65 | Portillo Soriano, Walter A | 40 | 1400 | 13577
PR | 120 | 06/06/25 | 66 | Ramos Herrera, Franklin J | 32 | 1344 | 13578
PR | 120 | 06/06/25 | 68 | Rodriguez Arevalos, Christian | 40 | 2040 | 13580
PR | 120 | 06/06/25 | 70 | Ross, Kelli M | 24 | 1224 | 13582
PR | 120 | 06/06/25 | 71 | Silva Morales, Jair J | 40 | 1360 | 13583
PR | 120 | 06/06/25 | 72 | Suniga Aviles, Kelvin A | 40 | 960 | 13584
PR | 120 | 06/06/25 | 74 | Taylor, Evan R | 24 | 1248 | 13586
PR | 120 | 06/06/25 | 78 | Zuniga Avilez, Eduar A | 40 | 960 | 13590
PR | 120 | 06/13/25 | 184 | Cruz Reyes, Jose | 40 | 1640 | 3543
PR | 120 | 06/13/25 | 186 | Galdamez, Dagoberto A | 24 | 1008 | 3545
PR | 120 | 06/13/25 | 187 | Hernandez Gonzalez, Osbaldo | 32 | 1344 | 3546
PR | 120 | 06/13/25 | 188 | Waites, Thaddeus Z | 40 | 2440 | 3547
PR | 120 | 06/13/25 | 189 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23548
PR | 120 | 06/13/25 | 192 | Ascencio, Jose L | 40 | 1680 | 23551
PR | 120 | 06/13/25 | 193 | Balderas Ortiz, Ricardo I | 40 | 1760 | 23552
PR | 120 | 06/13/25 | 196 | Carmona, Raul O | 40 | 2120 | 23555
PR | 120 | 06/13/25 | 197 | Castro Hernandez, Jose A | 40 | 2160 | 23556
PR | 120 | 06/13/25 | 198 | Cornejo Orellana, Carlos E | 40 | 1400 | 23557
PR | 120 | 06/13/25 | 199 | Cortes Mendiola, Victor H | 35 | 2240 | 23558
PR | 120 | 06/13/25 | 201 | Cruz Guzman, Joel A | 24 | 1224 | 23560
PR | 120 | 06/13/25 | 203 | Draves, Steven W | 16 | 880 | 23562
PR | 120 | 06/13/25 | 209 | Gerard, Mitchell J | 40 | 2440 | 23568
PR | 120 | 06/13/25 | 210 | Gochez Molina, Douglas O | 40 | 1120 | 23569
PR | 120 | 06/13/25 | 213 | Guerrero Espinoza, Mario | 40 | 1200 | 23572
PR | 120 | 06/13/25 | 215 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 23574
PR | 120 | 06/13/25 | 216 | Lima Romero, Melvin A | 32 | 1408 | 23575
PR | 120 | 06/13/25 | 217 | Lopez, Maslin A | 24 | 792 | 23576
PR | 120 | 06/13/25 | 220 | McCabe, Thomas C | 40 | 1760 | 23579
PR | 120 | 06/13/25 | 223 | Merino Martinez, Humberto | 16 | 448 | 23582
PR | 120 | 06/13/25 | 227 | Portillo Soriano, Walter A | 40 | 1400 | 23586
PR | 120 | 06/13/25 | 230 | Rodriguez Arevalos, Christian | 40 | 2040 | 23589
PR | 120 | 06/13/25 | 232 | Ross, Kelli M | 32 | 1632 | 23591
PR | 120 | 06/13/25 | 233 | Silva Morales, Jair J | 40 | 1360 | 23592
PR | 120 | 06/13/25 | 234 | Suniga Aviles, Kelvin A | 40 | 960 | 23593
PR | 120 | 06/13/25 | 236 | Taylor, Evan R | 24 | 1248 | 23595
PR | 120 | 06/13/25 | 240 | Zuniga Avilez, Eduar A | 40 | 960 | 23599
PR | 120 | 06/20/25 | 311 | Castro, Marcus J | 16 | 384 | 3550
PR | 120 | 06/20/25 | 312 | Cruz Reyes, Jose | 24 | 984 | 3551
PR | 120 | 06/20/25 | 316 | Waites, Thaddeus Z | 37 | 2257 | 3555
PR | 120 | 06/20/25 | 317 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33556
PR | 120 | 06/20/25 | 318 | Aquino, Juan | 8 | 224 | 33557
PR | 120 | 06/20/25 | 320 | Ascencio, Jose L | 40 | 1680 | 33559
PR | 120 | 06/20/25 | 321 | Balderas Ortiz, Ricardo I | 32 | 1408 | 33560
PR | 120 | 06/20/25 | 323 | Bautista Quintero, Isidoro | 40 | 960 | 33562
PR | 120 | 06/20/25 | 324 | Carmona, Raul O | 40 | 2120 | 33563
PR | 120 | 06/20/25 | 325 | Castro Hernandez, Jose A | 32 | 1728 | 33564
PR | 120 | 06/20/25 | 326 | Cornejo Orellana, Carlos E | 40 | 1400 | 33565
PR | 120 | 06/20/25 | 327 | Cortes Mendiola, Victor H | 30 | 1920 | 33566
PR | 120 | 06/20/25 | 329 | Cruz Guzman, Joel A | 40 | 2040 | 33568
PR | 120 | 06/20/25 | 332 | Fox, Tamron P | 4 | 112 | 33571
PR | 120 | 06/20/25 | 337 | Gochez Molina, Douglas O | 40 | 1120 | 33576
PR | 120 | 06/20/25 | 340 | Guerrero Espinoza, Mario | 40 | 1200 | 33579
PR | 120 | 06/20/25 | 342 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 33581
PR | 120 | 06/20/25 | 343 | Lima Romero, Melvin A | 40 | 1760 | 33582
PR | 120 | 06/20/25 | 344 | Lopez, Maslin A | 16 | 528 | 33583
PR | 120 | 06/20/25 | 347 | McCabe, Thomas C | 40 | 1760 | 33586
PR | 120 | 06/20/25 | 350 | Merino Martinez, Humberto | 40 | 1120 | 33589
PR | 120 | 06/20/25 | 354 | Portillo Soriano, Walter A | 40 | 1400 | 33593
PR | 120 | 06/20/25 | 355 | Ramos Herrera, Franklin J | 24 | 1008 | 33594
PR | 120 | 06/20/25 | 356 | Reed, Reuben H | 4 | 248 | 33595
PR | 120 | 06/20/25 | 357 | Rodriguez Arevalos, Christian | 32 | 1632 | 33596
PR | 120 | 06/20/25 | 359 | Ross, Kelli M | 32 | 1632 | 33598
PR | 120 | 06/20/25 | 360 | Silva Morales, Jair J | 32 | 1088 | 33599
PR | 120 | 06/20/25 | 361 | Suniga Aviles, Kelvin A | 40 | 960 | 33600
PR | 120 | 06/20/25 | 363 | Taylor, Evan R | 24 | 1248 | 33602
PR | 120 | 06/20/25 | 366 | Young, Joshua S | 24 | 1056 | 33605
PR | 120 | 06/20/25 | 367 | Zuniga Avilez, Eduar A | 40 | 960 | 33606
PR | 120 | 06/27/25 | 466 | Cruz Reyes, Jose | 32 | 1312 | 3559
PR | 120 | 06/27/25 | 470 | Waites, Thaddeus Z | 36 | 2196 | 3563
PR | 120 | 06/27/25 | 471 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 43564
PR | 120 | 06/27/25 | 474 | Ascencio, Jose L | 40 | 1680 | 43567
PR | 120 | 06/27/25 | 475 | Balderas Ortiz, Ricardo I | 40 | 1760 | 43568
PR | 120 | 06/27/25 | 476 | Barnhart, Joseph N | 8 | 544 | 43569
PR | 120 | 06/27/25 | 477 | Bautista Quintero, Isidoro | 40 | 960 | 43570
PR | 120 | 06/27/25 | 478 | Carmona, Raul O | 40 | 2120 | 43571
PR | 120 | 06/27/25 | 479 | Castro Hernandez, Jose A | 40 | 2160 | 43572
PR | 120 | 06/27/25 | 480 | Cornejo Orellana, Carlos E | 32 | 1120 | 43573
PR | 120 | 06/27/25 | 481 | Cortes Mendiola, Victor H | 32 | 2048 | 43574
PR | 120 | 06/27/25 | 484 | Cruz Guzman, Joel A | 40 | 2040 | 43577
PR | 120 | 06/27/25 | 491 | Gerard, Mitchell J | 32 | 1952 | 43584
PR | 120 | 06/27/25 | 492 | Gochez Molina, Douglas O | 40 | 1120 | 43585
PR | 120 | 06/27/25 | 495 | Guerrero Espinoza, Mario | 32 | 960 | 43588
PR | 120 | 06/27/25 | 497 | Jimenez Alvarenga, Gerson M | 32 | 1248 | 43590
PR | 120 | 06/27/25 | 502 | McCabe, Thomas C | 40 | 1760 | 43595
PR | 120 | 06/27/25 | 505 | Merino Martinez, Humberto | 40 | 1120 | 43598
PR | 120 | 06/27/25 | 509 | Portillo Soriano, Walter A | 40 | 1400 | 43602
PR | 120 | 06/27/25 | 510 | Ramos Herrera, Franklin J | 8 | 336 | 43603
PR | 120 | 06/27/25 | 512 | Rodriguez Arevalos, Christian | 40 | 2040 | 43605
PR | 120 | 06/27/25 | 514 | Ross, Kelli M | 32 | 1632 | 43607
PR | 120 | 06/27/25 | 515 | Silva Morales, Jair J | 40 | 1360 | 43608
PR | 120 | 06/27/25 | 516 | Suniga Aviles, Kelvin A | 40 | 960 | 43609
PR | 120 | 06/27/25 | 518 | Taylor, Evan R | 24 | 1248 | 43611
PR | 120 | 06/27/25 | 522 | Zuniga Avilez, Eduar A | 40 | 960 | 43615
PR | 120 | 07/03/25 | 10 | Cruz Reyes, Jose | 32 | 1312 | 3567
PR | 120 | 07/03/25 | 14 | Amaya Gonzalez, Edilberto A | 24 | 1224 | 13571
PR | 120 | 07/03/25 | 20 | Bautista Quintero, Isidoro | 40 | 960 | 13577
PR | 120 | 07/03/25 | 21 | Carmona, Raul O | 40 | 2120 | 13578
PR | 120 | 07/03/25 | 22 | Castro Hernandez, Jose A | 32 | 1728 | 13579
PR | 120 | 07/03/25 | 23 | Cornejo Orellana, Carlos E | 32 | 1120 | 13580
PR | 120 | 07/03/25 | 24 | Cortes Mendiola, Victor H | 21 | 1344 | 13581
PR | 120 | 07/03/25 | 27 | Cruz Guzman, Joel A | 32 | 1632 | 13584
PR | 120 | 07/03/25 | 34 | Gerard, Mitchell J | 32 | 1952 | 13591
PR | 120 | 07/03/25 | 40 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 13597
PR | 120 | 07/03/25 | 45 | McCabe, Thomas C | 40 | 1760 | 13602
PR | 120 | 07/03/25 | 48 | Merino Martinez, Humberto | 40 | 1120 | 13605
PR | 120 | 07/03/25 | 52 | Portillo Soriano, Walter A | 40 | 1400 | 13609
PR | 120 | 07/03/25 | 55 | Rodriguez Arevalos, Christian | 40 | 2040 | 13612
PR | 120 | 07/03/25 | 57 | Ross, Kelli M | 32 | 1632 | 13614
PR | 120 | 07/03/25 | 58 | Silva Morales, Jair J | 32 | 1088 | 13615
PR | 120 | 07/03/25 | 61 | Taylor, Evan R | 24 | 1248 | 13618
PR | 120 | 07/03/25 | 63 | Waites, Thaddeus Z | 24 | 1464 | 13620
PR | 120 | 07/03/25 | 66 | Zuniga Avilez, Eduar A | 40 | 960 | 13623
PR | 120 | 07/11/25 | 135 | Cruz Reyes, Jose | 31 | 1271 | 3574
PR | 120 | 07/11/25 | 139 | Amaya Gonzalez, Edilberto A | 31 | 1581 | 23578
PR | 120 | 07/11/25 | 144 | Barnhart, Joseph N | 3 | 204 | 23583
PR | 120 | 07/11/25 | 145 | Bautista Quintero, Isidoro | 31 | 744 | 23584
PR | 120 | 07/11/25 | 146 | Carmona, Raul O | 31 | 1643 | 23585
PR | 120 | 07/11/25 | 147 | Castro Hernandez, Jose A | 31 | 1674 | 23586
PR | 120 | 07/11/25 | 148 | Cornejo Orellana, Carlos E | 23 | 805 | 23587
PR | 120 | 07/11/25 | 149 | Cortes Mendiola, Victor H | 25 | 1600 | 23588
PR | 120 | 07/11/25 | 152 | Cruz Guzman, Joel A | 31 | 1581 | 23591
PR | 120 | 07/11/25 | 159 | Gerard, Mitchell J | 30 | 1830 | 23598
PR | 120 | 07/11/25 | 164 | Jimenez Alvarenga, Gerson M | 31 | 1209 | 23603
PR | 120 | 07/11/25 | 165 | Lima Romero, Melvin A | 23 | 1012 | 23604
PR | 120 | 07/11/25 | 169 | McCabe, Thomas C | 31 | 1364 | 23608
PR | 120 | 07/11/25 | 172 | Merino Martinez, Humberto | 31 | 868 | 23611
PR | 120 | 07/11/25 | 176 | Portillo Soriano, Walter A | 31 | 1085 | 23615
PR | 120 | 07/11/25 | 179 | Rodriguez Arevalos, Christian | 23 | 1173 | 23618
PR | 120 | 07/11/25 | 181 | Ross, Kelli M | 23 | 1173 | 23620
PR | 120 | 07/11/25 | 182 | Silva Morales, Jair J | 31 | 1054 | 23621
PR | 120 | 07/11/25 | 183 | Suniga Aviles, Kelvin A | 31 | 744 | 23622
PR | 120 | 07/11/25 | 185 | Taylor, Evan R | 15 | 780 | 23624
PR | 120 | 07/11/25 | 187 | Waites, Thaddeus Z | 8 | 488 | 23626
PR | 120 | 07/11/25 | 190 | Zuniga Avilez, Eduar A | 31 | 744 | 23629
PR | 120 | 07/18/25 | 303 | Cruz Reyes, Jose | 40 | 1640 | 3582
PR | 120 | 07/18/25 | 306 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33585
PR | 120 | 07/18/25 | 310 | Balderas Ortiz, Ricardo I | 40 | 1760 | 33589
PR | 120 | 07/18/25 | 311 | Barnhart, Joseph N | 5 | 340 | 33590
PR | 120 | 07/18/25 | 312 | Bautista Quintero, Isidoro | 32 | 768 | 33591
PR | 120 | 07/18/25 | 313 | Carmona, Raul O | 40 | 2120 | 33592
PR | 120 | 07/18/25 | 314 | Castro Hernandez, Jose A | 40 | 2160 | 33593
PR | 120 | 07/18/25 | 315 | Cornejo Orellana, Carlos E | 32 | 1120 | 33594
PR | 120 | 07/18/25 | 316 | Cortes Mendiola, Victor H | 36 | 2304 | 33595
PR | 120 | 07/18/25 | 319 | Cruz Guzman, Joel A | 24 | 1224 | 33598
PR | 120 | 07/18/25 | 326 | Gerard, Mitchell J | 38 | 2318 | 33605
PR | 120 | 07/18/25 | 331 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 33610
PR | 120 | 07/18/25 | 336 | McCabe, Thomas C | 40 | 1760 | 33615
PR | 120 | 07/18/25 | 339 | Merino Martinez, Humberto | 40 | 1120 | 33618
PR | 120 | 07/18/25 | 343 | Portillo Soriano, Walter A | 40 | 1400 | 33622
PR | 120 | 07/18/25 | 346 | Rodriguez Arevalos, Christian | 40 | 2040 | 33625
PR | 120 | 07/18/25 | 348 | Ross, Kelli M | 24 | 1224 | 33627
PR | 120 | 07/18/25 | 349 | Silva Morales, Jair J | 40 | 1360 | 33628
PR | 120 | 07/18/25 | 350 | Suniga Aviles, Kelvin A | 40 | 960 | 33629
PR | 120 | 07/18/25 | 354 | Waites, Thaddeus Z | 39 | 2379 | 33633
PR | 120 | 07/18/25 | 357 | Zuniga Avilez, Eduar A | 40 | 960 | 33636
PR | 120 | 07/25/25 | 470 | Cruz Reyes, Jose | 40 | 1640 | 3588
PR | 120 | 07/25/25 | 474 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 43592
PR | 120 | 07/25/25 | 478 | Balderas Ortiz, Ricardo I | 8 | 352 | 43596
PR | 120 | 07/25/25 | 480 | Bautista Quintero, Isidoro | 40 | 960 | 43598
PR | 120 | 07/25/25 | 481 | Carmona, Raul O | 32 | 1696 | 43599
PR | 120 | 07/25/25 | 482 | Castro Hernandez, Jose A | 32 | 1728 | 43600
PR | 120 | 07/25/25 | 483 | Cornejo Orellana, Carlos E | 40 | 1400 | 43601
PR | 120 | 07/25/25 | 484 | Cortes Mendiola, Victor H | 29 | 1856 | 43602
PR | 120 | 07/25/25 | 487 | Cruz Guzman, Joel A | 40 | 2040 | 43605
PR | 120 | 07/25/25 | 494 | Gerard, Mitchell J | 40 | 2440 | 43612
PR | 120 | 07/25/25 | 499 | Jimenez Alvarenga, Gerson M | 16 | 624 | 43617
PR | 120 | 07/25/25 | 504 | McCabe, Thomas C | 40 | 1760 | 43622
PR | 120 | 07/25/25 | 507 | Merino Martinez, Humberto | 40 | 1120 | 43625
PR | 120 | 07/25/25 | 511 | Portillo Soriano, Walter A | 40 | 1400 | 43629
PR | 120 | 07/25/25 | 514 | Rodriguez Arevalos, Christian | 8 | 408 | 43632
PR | 120 | 07/25/25 | 516 | Ross, Kelli M | 24 | 1224 | 43634
PR | 120 | 07/25/25 | 517 | Silva Morales, Jair J | 40 | 1360 | 43635
PR | 120 | 07/25/25 | 518 | Suniga Aviles, Kelvin A | 40 | 960 | 43636
PR | 120 | 07/25/25 | 520 | Waites, Thaddeus Z | 12 | 732 | 43638
PR | 120 | 07/25/25 | 523 | Zuniga Avilez, Eduar A | 40 | 960 | 43641
PR | 120 | 08/01/25 | 3 | Cruz Reyes, Jose | 40 | 1640 | 3594
PR | 120 | 08/01/25 | 7 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 13598
PR | 120 | 08/01/25 | 12 | Barnhart, Joseph N | 4 | 272 | 13603
PR | 120 | 08/01/25 | 13 | Bautista Quintero, Isidoro | 24 | 576 | 13604
PR | 120 | 08/01/25 | 14 | Carmona, Raul O | 40 | 2120 | 13605
PR | 120 | 08/01/25 | 15 | Castro Hernandez, Jose A | 32 | 1728 | 13606
PR | 120 | 08/01/25 | 16 | Cornejo Orellana, Carlos E | 40 | 1400 | 13607
PR | 120 | 08/01/25 | 17 | Cortes Mendiola, Victor H | 33 | 2112 | 13608
PR | 120 | 08/01/25 | 20 | Cruz Guzman, Joel A | 40 | 2040 | 13611
PR | 120 | 08/01/25 | 27 | Gerard, Mitchell J | 40 | 2440 | 13618
PR | 120 | 08/01/25 | 37 | McCabe, Thomas C | 32 | 1408 | 13628
PR | 120 | 08/01/25 | 40 | Merino Martinez, Humberto | 40 | 1120 | 13631
PR | 120 | 08/01/25 | 44 | Portillo Soriano, Walter A | 40 | 1400 | 13635
PR | 120 | 08/01/25 | 49 | Ross, Kelli M | 24 | 1224 | 13640
PR | 120 | 08/01/25 | 50 | Silva Morales, Jair J | 40 | 1360 | 13641
PR | 120 | 08/01/25 | 51 | Suniga Aviles, Kelvin A | 24 | 576 | 13642
PR | 120 | 08/01/25 | 53 | Taylor, Evan R | 8 | 416 | 13644
PR | 120 | 08/01/25 | 56 | Zuniga Avilez, Eduar A | 40 | 960 | 13647
PR | 120 | 08/08/25 | 134 | Cruz Reyes, Jose | 40 | 1640 | 3601
PR | 120 | 08/08/25 | 138 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23605
PR | 120 | 08/08/25 | 143 | Barnhart, Joseph N | 5 | 340 | 23610
PR | 120 | 08/08/25 | 145 | Carmona, Raul O | 40 | 2120 | 23612
PR | 120 | 08/08/25 | 146 | Castro Hernandez, Jose A | 40 | 2160 | 23613
PR | 120 | 08/08/25 | 147 | Cornejo Orellana, Carlos E | 32 | 1120 | 23614
PR | 120 | 08/08/25 | 148 | Cortes Mendiola, Victor H | 30 | 1920 | 23615
PR | 120 | 08/08/25 | 151 | Cruz Guzman, Joel A | 32 | 1632 | 23618
PR | 120 | 08/08/25 | 158 | Gerard, Mitchell J | 40 | 2440 | 23625
PR | 120 | 08/08/25 | 164 | Lima Romero, Melvin A | 8 | 352 | 23631
PR | 120 | 08/08/25 | 168 | McCabe, Thomas C | 40 | 1760 | 23635
PR | 120 | 08/08/25 | 171 | Merino Martinez, Humberto | 40 | 1120 | 23638
PR | 120 | 08/08/25 | 175 | Portillo Soriano, Walter A | 40 | 1400 | 23642
PR | 120 | 08/08/25 | 180 | Ross, Kelli M | 24 | 1224 | 23647
PR | 120 | 08/08/25 | 181 | Silva Morales, Jair J | 40 | 1360 | 23648
PR | 120 | 08/08/25 | 184 | Taylor, Evan R | 16 | 832 | 23651
PR | 120 | 08/08/25 | 187 | Zuniga Avilez, Eduar A | 24 | 576 | 23654
PR | 120 | 08/15/25 | 260 | Cruz Reyes, Jose | 40 | 1640 | 3607
PR | 120 | 08/15/25 | 268 | Barnhart, Joseph N | 2 | 136 | 33615
PR | 120 | 08/15/25 | 270 | Carmona, Raul O | 40 | 2120 | 33617
PR | 120 | 08/15/25 | 271 | Castro Hernandez, Jose A | 40 | 2160 | 33618
PR | 120 | 08/15/25 | 272 | Cornejo Orellana, Carlos E | 32 | 1120 | 33619
PR | 120 | 08/15/25 | 273 | Cortes Mendiola, Victor H | 30 | 1920 | 33620
PR | 120 | 08/15/25 | 276 | Cruz Guzman, Joel A | 40 | 2040 | 33623
PR | 120 | 08/15/25 | 283 | Gerard, Mitchell J | 40 | 2440 | 33630
PR | 120 | 08/15/25 | 296 | Merino Martinez, Humberto | 40 | 1120 | 33643
PR | 120 | 08/15/25 | 300 | Portillo Soriano, Walter A | 40 | 1400 | 33647
PR | 120 | 08/15/25 | 305 | Ross, Kelli M | 32 | 1632 | 33652
PR | 120 | 08/15/25 | 306 | Silva Morales, Jair J | 32 | 1088 | 33653
PR | 120 | 08/15/25 | 307 | Suniga Aviles, Kelvin A | 32 | 768 | 33654
PR | 120 | 08/15/25 | 309 | Taylor, Evan R | 16 | 832 | 33656
PR | 120 | 08/15/25 | 312 | Zuniga Avilez, Eduar A | 32 | 768 | 33659
PR | 120 | 08/22/25 | 362 | Cruz Reyes, Jose | 40 | 1640 | 3612
PR | 120 | 08/22/25 | 366 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 43616
PR | 120 | 08/22/25 | 371 | Barnhart, Joseph N | 5 | 340 | 43621
PR | 120 | 08/22/25 | 373 | Carmona, Raul O | 40 | 2120 | 43623
PR | 120 | 08/22/25 | 374 | Castro Hernandez, Jose A | 40 | 2160 | 43624
PR | 120 | 08/22/25 | 375 | Cornejo Orellana, Carlos E | 40 | 1400 | 43625
PR | 120 | 08/22/25 | 376 | Cortes Mendiola, Victor H | 34 | 2176 | 43626
PR | 120 | 08/22/25 | 379 | Cruz Guzman, Joel A | 40 | 2040 | 43629
PR | 120 | 08/22/25 | 387 | Gerard, Mitchell J | 32 | 1952 | 43637
PR | 120 | 08/22/25 | 397 | McCabe, Thomas C | 40 | 1760 | 43647
PR | 120 | 08/22/25 | 400 | Merino Martinez, Humberto | 40 | 1120 | 43650
PR | 120 | 08/22/25 | 404 | Portillo Soriano, Walter A | 40 | 1400 | 43654
PR | 120 | 08/22/25 | 409 | Ross, Kelli M | 32 | 1632 | 43659
PR | 120 | 08/22/25 | 410 | Silva Morales, Jair J | 40 | 1360 | 43660
PR | 120 | 08/22/25 | 413 | Taylor, Evan R | 16 | 832 | 43663
PR | 120 | 08/22/25 | 416 | Zuniga Avilez, Eduar A | 40 | 960 | 43666
PR | 120 | 08/29/25 | 525 | Cruz Reyes, Jose | 40 | 1640 | 3618
PR | 120 | 08/29/25 | 529 | Amaya Gonzalez, Edilberto A | 36 | 1836 | 53622
PR | 120 | 08/29/25 | 534 | Barnhart, Joseph N | 2 | 136 | 53627
PR | 120 | 08/29/25 | 536 | Carmona, Raul O | 40 | 2120 | 53629
PR | 120 | 08/29/25 | 538 | Cornejo Orellana, Carlos E | 16 | 560 | 53631
PR | 120 | 08/29/25 | 539 | Cortes Mendiola, Victor H | 31 | 1984 | 53632
PR | 120 | 08/29/25 | 542 | Cruz Guzman, Joel A | 32 | 1632 | 53635
PR | 120 | 08/29/25 | 550 | Gerard, Mitchell J | 40 | 2440 | 53643
PR | 120 | 08/29/25 | 560 | McCabe, Thomas C | 16 | 704 | 53653
PR | 120 | 08/29/25 | 563 | Merino Martinez, Humberto | 40 | 1120 | 53656
PR | 120 | 08/29/25 | 567 | Portillo Soriano, Walter A | 40 | 1400 | 53660
PR | 120 | 08/29/25 | 573 | Silva Morales, Jair J | 40 | 1360 | 53666
PR | 120 | 08/29/25 | 576 | Taylor, Evan R | 16 | 832 | 53669
PR | 120 | 08/29/25 | 579 | Zuniga Avilez, Eduar A | 40 | 960 | 53672
PR | 120 | 09/05/25 | 10 | Cruz Reyes, Jose | 32 | 1312 | 3624
PR | 120 | 09/05/25 | 14 | Amaya Gonzalez, Edilberto A | 32 | 1632 | 13628
PR | 120 | 09/05/25 | 19 | Barnhart, Joseph N | 1 | 68 | 13633
PR | 120 | 09/05/25 | 20 | Bautista Quintero, Isidoro | 16 | 384 | 13634
PR | 120 | 09/05/25 | 21 | Carmona, Raul O | 32 | 1696 | 13635
PR | 120 | 09/05/25 | 22 | Castro Hernandez, Jose A | 24 | 1296 | 13636
PR | 120 | 09/05/25 | 24 | Cortes Mendiola, Victor H | 27 | 1728 | 13638
PR | 120 | 09/05/25 | 27 | Cruz Guzman, Joel A | 32 | 1632 | 13641
PR | 120 | 09/05/25 | 35 | Gerard, Mitchell J | 30 | 1830 | 13649
PR | 120 | 09/05/25 | 45 | McCabe, Thomas C | 24 | 1056 | 13659
PR | 120 | 09/05/25 | 48 | Merino Martinez, Humberto | 32 | 896 | 13662
PR | 120 | 09/05/25 | 52 | Portillo Soriano, Walter A | 32 | 1120 | 13666
PR | 120 | 09/05/25 | 58 | Silva Morales, Jair J | 32 | 1088 | 13672
PR | 120 | 09/05/25 | 59 | Suniga Aviles, Kelvin A | 8 | 192 | 13673
PR | 120 | 09/05/25 | 63 | Zuniga Avilez, Eduar A | 16 | 384 | 13677
PR | 120 | 09/12/25 | 108 | Cruz Reyes, Jose | 40 | 1640 | 3630
PR | 120 | 09/12/25 | 111 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 23633
PR | 120 | 09/12/25 | 116 | Barnhart, Joseph N | 6 | 408 | 23638
PR | 120 | 09/12/25 | 117 | Bautista Quintero, Isidoro | 40 | 960 | 23639
PR | 120 | 09/12/25 | 118 | Carmona, Raul O | 40 | 2120 | 23640
PR | 120 | 09/12/25 | 119 | Castro Hernandez, Jose A | 40 | 2160 | 23641
PR | 120 | 09/12/25 | 121 | Cortes Mendiola, Victor H | 24 | 1536 | 23643
PR | 120 | 09/12/25 | 124 | Cruz Guzman, Joel A | 40 | 2040 | 23646
PR | 120 | 09/12/25 | 132 | Gerard, Mitchell J | 40 | 2440 | 23654
PR | 120 | 09/12/25 | 142 | McCabe, Thomas C | 40 | 1760 | 23664
PR | 120 | 09/12/25 | 145 | Merino Martinez, Humberto | 40 | 1120 | 23667
PR | 120 | 09/12/25 | 149 | Portillo Soriano, Walter A | 40 | 1400 | 23671
PR | 120 | 09/12/25 | 155 | Silva Morales, Jair J | 40 | 1360 | 23677
PR | 120 | 09/19/25 | 240 | Cruz Reyes, Jose | 37 | 1517 | 3636
PR | 120 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A | 3 | 153 | 33639
PR | 120 | 09/19/25 | 248 | Barnhart, Joseph N | 2 | 136 | 33644
PR | 120 | 09/19/25 | 249 | Bautista Quintero, Isidoro | 13 | 312 | 33645
PR | 120 | 09/19/25 | 250 | Carmona, Raul O | 37 | 1961 | 33646
PR | 120 | 09/19/25 | 251 | Castro Hernandez, Jose A | 37 | 1998 | 33647
PR | 120 | 09/19/25 | 253 | Cortes Mendiola, Victor H | 32 | 2048 | 33649
PR | 120 | 09/19/25 | 256 | Cruz Guzman, Joel A | 37 | 1887 | 33652
PR | 120 | 09/19/25 | 264 | Gerard, Mitchell J | 37 | 2257 | 33660
PR | 120 | 09/19/25 | 274 | McCabe, Thomas C | 32 | 1408 | 33670
PR | 120 | 09/19/25 | 277 | Merino Martinez, Humberto | 37 | 1036 | 33673
PR | 120 | 09/19/25 | 281 | Portillo Soriano, Walter A | 37 | 1295 | 33677
PR | 120 | 09/19/25 | 287 | Silva Morales, Jair J | 37 | 1258 | 33683
PR | 120 | 09/26/25 | 410 | Cruz Reyes, Jose | 8 | 328 | 3642
PR | 120 | 09/26/25 | 410 | Cruz Reyes, Jose | 8 | 328 | 3642
PR | 120 | 09/26/25 | 419 | Barnhart, Joseph N | 4.5 | 306 | 43651
PR | 120 | 09/26/25 | 420 | Bautista Quintero, Isidoro | 8 | 192 | 43652
PR | 120 | 09/26/25 | 420 | Bautista Quintero, Isidoro | 8 | 192 | 43652
PR | 120 | 09/26/25 | 420 | Bautista Quintero, Isidoro | 8 | 192 | 43652
PR | 120 | 09/26/25 | 420 | Bautista Quintero, Isidoro | 8 | 192 | 43652
PR | 120 | 09/26/25 | 421 | Carmona, Raul O | 8 | 424 | 43653
PR | 120 | 09/26/25 | 421 | Carmona, Raul O | 8 | 424 | 43653
PR | 120 | 09/26/25 | 421 | Carmona, Raul O | 8 | 424 | 43653
PR | 120 | 09/26/25 | 421 | Carmona, Raul O | 8 | 424 | 43653
PR | 120 | 09/26/25 | 421 | Carmona, Raul O | 8 | 424 | 43653
PR | 120 | 09/26/25 | 422 | Castro Hernandez, Jose A | 8 | 432 | 43654
PR | 120 | 09/26/25 | 422 | Castro Hernandez, Jose A | 8 | 432 | 43654
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 3.75 | 240 | 43656
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 2.75 | 176 | 43656
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 8 | 512 | 43656
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 8 | 512 | 43656
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 8 | 512 | 43656
PR | 120 | 09/26/25 | 424 | Cortes Mendiola, Victor H | 8 | 512 | 43656
PR | 120 | 09/26/25 | 427 | Cruz Guzman, Joel A | 8 | 408 | 43659
PR | 120 | 09/26/25 | 427 | Cruz Guzman, Joel A | 8 | 408 | 43659
PR | 120 | 09/26/25 | 435 | Gerard, Mitchell J | 8 | 488 | 43667
PR | 120 | 09/26/25 | 435 | Gerard, Mitchell J | 8 | 488 | 43667
PR | 120 | 09/26/25 | 435 | Gerard, Mitchell J | 8 | 488 | 43667
PR | 120 | 09/26/25 | 435 | Gerard, Mitchell J | 8 | 488 | 43667
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 8 | 352 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 2 | 88 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 2.5 | 110 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 2 | 88 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 1.25 | 55 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 1.25 | 55 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 1.75 | 77 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 5.5 | 242 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 2.75 | 121 | 43677
PR | 120 | 09/26/25 | 445 | McCabe, Thomas C | 1.75 | 77 | 43677
PR | 120 | 09/26/25 | 452 | Portillo Soriano, Walter A | 8 | 280 | 43684
PR | 120 | 09/26/25 | 458 | Silva Morales, Jair J | 8 | 272 | 43690
PR | 120 | 09/26/25 | 458 | Silva Morales, Jair J | 8 | 272 | 43690
PR | 120 | 09/26/25 | 458 | Silva Morales, Jair J | 8 | 272 | 43690
PR | 120 | 09/26/25 | 458 | Silva Morales, Jair J | 8 | 272 | 43690
PR | 120 | 09/26/25 | 458 | Silva Morales, Jair J | 8 | 272 | 43690
PR | 120 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 4.75 | 242.25 | 13653
PR | 120 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13653
PR | 120 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 8 | 408 | 13653
PR | 120 | 10/03/25 | 15 | Barnhart, Joseph N | 0.75 | 51 | 13658
PR | 120 | 10/03/25 | 15 | Barnhart, Joseph N | 4.75 | 323 | 13658
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 8 | 192 | 13659
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 4.5 | 108 | 13659
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 2.25 | 54 | 13659
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 4.25 | 102 | 13659
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 8 | 192 | 13659
PR | 120 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 8 | 192 | 13659
PR | 120 | 10/03/25 | 17 | Carmona, Raul O | 8 | 424 | 13660
PR | 120 | 10/03/25 | 17 | Carmona, Raul O | 8 | 424 | 13660
PR | 120 | 10/03/25 | 17 | Carmona, Raul O | 8 | 424 | 13660
PR | 120 | 10/03/25 | 17 | Carmona, Raul O | 8 | 424 | 13660
PR | 120 | 10/03/25 | 17 | Carmona, Raul O | 8 | 424 | 13660
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 8 | 512 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 4.75 | 304 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 1.75 | 112 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 5 | 320 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 8 | 512 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 7.75 | 496 | 13663
PR | 120 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 0.25 | 24 | 13663
PR | 120 | 10/03/25 | 32 | Gerard, Mitchell J | 8 | 488 | 13675
PR | 120 | 10/03/25 | 32 | Gerard, Mitchell J | 8 | 488 | 13675
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 8 | 352 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 3 | 132 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 1.5 | 66 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 3 | 132 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 2.5 | 110 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 5.75 | 253 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 1 | 44 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 2.25 | 99 | 13685
PR | 120 | 10/03/25 | 42 | McCabe, Thomas C | 1 | 44 | 13685
PR | 120 | 10/03/25 | 55 | Silva Morales, Jair J | 8 | 272 | 13698
PR | 120 | 10/03/25 | 55 | Silva Morales, Jair J | 8 | 272 | 13698
PR | 120 | 10/03/25 | 55 | Silva Morales, Jair J | 8 | 272 | 13698
PR | 120 | 10/03/25 | 55 | Silva Morales, Jair J | 8 | 272 | 13698
PR | 120 | 10/03/25 | 55 | Silva Morales, Jair J | 8 | 272 | 13698
PR | 120 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23660
PR | 120 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23660
PR | 120 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23660
PR | 120 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23660
PR | 120 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A | 8 | 408 | 23660
PR | 120 | 10/10/25 | 167 | Barnhart, Joseph N | 0.5 | 34 | 23665
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 2.25 | 54 | 23666
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 3 | 72 | 23666
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 8 | 192 | 23666
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 8 | 192 | 23666
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 8 | 192 | 23666
PR | 120 | 10/10/25 | 168 | Bautista Quintero, Isidoro | 8 | 192 | 23666
PR | 120 | 10/10/25 | 169 | Carmona, Raul O | 8 | 424 | 23667
PR | 120 | 10/10/25 | 169 | Carmona, Raul O | 8 | 424 | 23667
PR | 120 | 10/10/25 | 169 | Carmona, Raul O | 8 | 424 | 23667
PR | 120 | 10/10/25 | 169 | Carmona, Raul O | 8 | 424 | 23667
PR | 120 | 10/10/25 | 169 | Carmona, Raul O | 8 | 424 | 23667
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 2.25 | 144 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 3 | 192 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 8 | 512 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 6.25 | 400 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 0.75 | 48 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 8 | 512 | 23670
PR | 120 | 10/10/25 | 172 | Cortes Mendiola, Victor H | 8 | 512 | 23670
PR | 120 | 10/10/25 | 184 | Gerard, Mitchell J | 8 | 488 | 23682
PR | 120 | 10/10/25 | 184 | Gerard, Mitchell J | 0.25 | 15.25 | 23682
PR | 120 | 10/10/25 | 184 | Gerard, Mitchell J | 7.5 | 457.5 | 23682
PR | 120 | 10/10/25 | 184 | Gerard, Mitchell J | 8.25 | 503.25 | 23682
PR | 120 | 10/10/25 | 184 | Gerard, Mitchell J | 8 | 488 | 23682
PR | 120 | 10/10/25 | 185 | Gochez Molina, Douglas O | 8 | 224 | 23683
PR | 120 | 10/10/25 | 185 | Gochez Molina, Douglas O | 8 | 224 | 23683
PR | 120 | 10/10/25 | 185 | Gochez Molina, Douglas O | 8 | 224 | 23683
PR | 120 | 10/10/25 | 195 | McCabe, Thomas C | 4 | 176 | 23693
PR | 120 | 10/10/25 | 195 | McCabe, Thomas C | 3.75 | 165 | 23693
PR | 120 | 10/10/25 | 195 | McCabe, Thomas C | 4 | 176 | 23693
PR | 120 | 10/10/25 | 195 | McCabe, Thomas C | 1 | 44 | 23693
PR | 120 | 10/10/25 | 208 | Silva Morales, Jair J | 8 | 272 | 23706
PR | 120 | 10/10/25 | 208 | Silva Morales, Jair J | 8 | 272 | 23706
PR | 120 | 10/10/25 | 208 | Silva Morales, Jair J | 8 | 272 | 23706
PR | 120 | 10/10/25 | 208 | Silva Morales, Jair J | 8 | 272 | 23706
PR | 120 | 10/17/25 | 363 | Da Cruz, Eduardo E | 8 | 184 | 3664
PR | 120 | 10/17/25 | 363 | Da Cruz, Eduardo E | 2.75 | 63.25 | 3664
PR | 120 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A | 8 | 408 | 33668
PR | 120 | 10/17/25 | 373 | Bautista Quintero, Isidoro | 8 | 192 | 33674
PR | 120 | 10/17/25 | 373 | Bautista Quintero, Isidoro | 8 | 192 | 33674
PR | 120 | 10/17/25 | 373 | Bautista Quintero, Isidoro | 2 | 48 | 33674
PR | 120 | 10/17/25 | 373 | Bautista Quintero, Isidoro | 5.5 | 132 | 33674
PR | 120 | 10/17/25 | 373 | Bautista Quintero, Isidoro | 2.75 | 66 | 33674
PR | 120 | 10/17/25 | 374 | Carmona, Raul O | 8 | 424 | 33675
PR | 120 | 10/17/25 | 374 | Carmona, Raul O | 8 | 424 | 33675
PR | 120 | 10/17/25 | 374 | Carmona, Raul O | 8 | 424 | 33675
PR | 120 | 10/17/25 | 374 | Carmona, Raul O | 8 | 424 | 33675
PR | 120 | 10/17/25 | 374 | Carmona, Raul O | 8 | 424 | 33675
PR | 120 | 10/17/25 | 377 | Cortes Mendiola, Victor H | 8 | 512 | 33678
PR | 120 | 10/17/25 | 377 | Cortes Mendiola, Victor H | 8 | 512 | 33678
PR | 120 | 10/17/25 | 377 | Cortes Mendiola, Victor H | 1.75 | 112 | 33678
PR | 120 | 10/17/25 | 389 | Gerard, Mitchell J | 7.75 | 472.75 | 33690
PR | 120 | 10/17/25 | 389 | Gerard, Mitchell J | 4.25 | 259.25 | 33690
PR | 120 | 10/17/25 | 400 | McCabe, Thomas C | 2 | 88 | 33701
PR | 120 | 10/17/25 | 413 | Silva Morales, Jair J | 8 | 272 | 33714
PR | 120 | 10/17/25 | 413 | Silva Morales, Jair J | 8 | 272 | 33714
PR | 120 | 10/17/25 | 413 | Silva Morales, Jair J | 8 | 272 | 33714
PR | 120 | 10/17/25 | 413 | Silva Morales, Jair J | 8 | 272 | 33714
PR | 120 | 10/17/25 | 413 | Silva Morales, Jair J | 8 | 272 | 33714
PR | 120 | 10/24/25 | 507 | Carmona, Raul O | 8 | 424 | 43683
PR | 120 | 10/24/25 | 507 | Carmona, Raul O | 6.25 | 331.25 | 43683
PR | 120 | 10/24/25 | 507 | Carmona, Raul O | 8 | 424 | 43683
PR | 120 | 10/24/25 | 507 | Carmona, Raul O | 8 | 424 | 43683
PR | 120 | 10/24/25 | 523 | Gerard, Mitchell J | 2.5 | 152.5 | 43699
PR | 120 | 10/24/25 | 523 | Gerard, Mitchell J | 3.75 | 228.75 | 43699
PR | 120 | 10/24/25 | 523 | Gerard, Mitchell J | 7.75 | 472.75 | 43699
PR | 120 | 10/24/25 | 523 | Gerard, Mitchell J | 7.75 | 472.75 | 43699
PR | 120 | 10/24/25 | 534 | McCabe, Thomas C | 0.75 | 33 | 43710
PR | 120 | 10/24/25 | 548 | Silva Morales, Jair J | 8 | 272 | 43724
PR | 120 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A | 6.5 | 331.5 | 53682
PR | 120 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A | 8 | 408 | 53682
PR | 120 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A | 8 | 408 | 53682
PR | 120 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A | 2 | 102 | 53682
PR | 120 | 10/31/25 | 670 | Barnhart, Joseph N | 3 | 204 | 53687
PR | 120 | 10/31/25 | 670 | Barnhart, Joseph N | 0.75 | 51 | 53687
PR | 120 | 10/31/25 | 671 | Bautista Quintero, Isidoro | 2.75 | 66 | 53688
PR | 120 | 10/31/25 | 671 | Bautista Quintero, Isidoro | 8 | 192 | 53688
PR | 120 | 10/31/25 | 671 | Bautista Quintero, Isidoro | 2 | 48 | 53688
PR | 120 | 10/31/25 | 671 | Bautista Quintero, Isidoro | 5.25 | 126 | 53688
PR | 120 | 10/31/25 | 671 | Bautista Quintero, Isidoro | 2 | 48 | 53688
PR | 120 | 10/31/25 | 672 | Carmona, Raul O | 8 | 424 | 53689
PR | 120 | 10/31/25 | 672 | Carmona, Raul O | 8.25 | 437.25 | 53689
PR | 120 | 10/31/25 | 672 | Carmona, Raul O | 8 | 424 | 53689
PR | 120 | 10/31/25 | 672 | Carmona, Raul O | 7.75 | 410.75 | 53689
PR | 120 | 10/31/25 | 676 | Cortes Mendiola, Victor H | 2.25 | 144 | 53693
PR | 120 | 10/31/25 | 676 | Cortes Mendiola, Victor H | 8 | 512 | 53693
PR | 120 | 10/31/25 | 676 | Cortes Mendiola, Victor H | 2 | 128 | 53693
PR | 120 | 10/31/25 | 676 | Cortes Mendiola, Victor H | 5 | 320 | 53693
PR | 120 | 10/31/25 | 680 | Da Cruz, Eduardo E | 1.75 | 40.25 | 53697
PR | 120 | 10/31/25 | 680 | Da Cruz, Eduardo E | 8.25 | 189.75 | 53697
PR | 120 | 10/31/25 | 689 | Gerard, Mitchell J | 4.25 | 259.25 | 53706
PR | 120 | 10/31/25 | 689 | Gerard, Mitchell J | 8 | 488 | 53706
PR | 120 | 10/31/25 | 689 | Gerard, Mitchell J | 7.5 | 457.5 | 53706
PR | 120 | 10/31/25 | 689 | Gerard, Mitchell J | 7.5 | 457.5 | 53706
PR | 120 | 10/31/25 | 702 | McCabe, Thomas C | 0.75 | 33 | 53719
PR | 120 | 10/31/25 | 715 | Silva Morales, Jair J | 2.5 | 85 | 53732
PR | 120 | 10/31/25 | 715 | Silva Morales, Jair J | 8 | 272 | 53732
PR | 120 | 10/31/25 | 715 | Silva Morales, Jair J | 8 | 272 | 53732
PR | 120 | 10/31/25 | 715 | Silva Morales, Jair J | 8 | 272 | 53732
PR | 120 | 10/31/25 | 715 | Silva Morales, Jair J | 8 | 272 | 53732
PR | 120 | 11/07/25 | 61 | Carmona, Raul O | 1.25 | 66.25 | 13695
PR | 120 | 11/07/25 | 61 | Carmona, Raul O | 8 | 424 | 13695
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 4.25 | 259.25 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 1 | 61 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 0.75 | 45.75 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 0.75 | 45.75 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 0.25 | 15.25 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 6.25 | 381.25 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 1 | 61 | 13711
PR | 120 | 11/07/25 | 77 | Gerard, Mitchell J | 5.5 | 335.5 | 13711
PR | 120 | 11/07/25 | 103 | Silva Morales, Jair J | 1.25 | 42.5 | 13737
PR | 120 | 11/14/25 | 221 | Carmona, Raul O | 8 | 424 | 23701
PR | 120 | 11/14/25 | 221 | Carmona, Raul O | 8 | 424 | 23701
PR | 120 | 11/14/25 | 221 | Carmona, Raul O | 8 | 424 | 23701
PR | 120 | 11/14/25 | 221 | Carmona, Raul O | 8 | 424 | 23701
PR | 120 | 11/14/25 | 221 | Carmona, Raul O | 8 | 424 | 23701
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 2 | 122 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 0.75 | 45.75 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 4.25 | 259.25 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 1.75 | 106.75 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 2.25 | 137.25 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 1.25 | 76.25 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 2 | 122 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 0.75 | 45.75 | 23717
PR | 120 | 11/14/25 | 237 | Gerard, Mitchell J | 7.75 | 472.75 | 23717
PR | 120 | 11/14/25 | 263 | Silva Morales, Jair J | 5.5 | 187 | 23743
PR | 120 | 11/21/25 | 338 | Carmona, Raul O | 8 | 424 | 33707
PR | 120 | 11/21/25 | 338 | Carmona, Raul O | 8 | 424 | 33707
PR | 120 | 11/21/25 | 338 | Carmona, Raul O | 8 | 424 | 33707
PR | 120 | 11/21/25 | 338 | Carmona, Raul O | 8 | 424 | 33707
PR | 120 | 11/21/25 | 338 | Carmona, Raul O | 8 | 424 | 33707
PR | 120 | 11/21/25 | 342 | Cortes Mendiola, Victor H | 5 | 320 | 33711
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 1.25 | 76.25 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 2 | 122 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 4.25 | 259.25 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 0.5 | 30.5 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 4.75 | 289.75 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 0.25 | 15.25 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 2.25 | 137.25 | 33723
PR | 120 | 11/21/25 | 354 | Gerard, Mitchell J | 8 | 488 | 33723
PR | 120 | 11/21/25 | 379 | Silva Morales, Jair J | 8 | 272 | 33748
PR | 120 | 11/21/25 | 379 | Silva Morales, Jair J | 8 | 272 | 33748
PR | 120 | 11/21/25 | 379 | Silva Morales, Jair J | 8 | 272 | 33748
PR | 120 | 11/21/25 | 379 | Silva Morales, Jair J | 3.5 | 119 | 33748
PR | 120 | 11/28/25 | 519 | Barnhart, Joseph N | 1 | 68 | 43709
PR | 120 | 11/28/25 | 521 | Carmona, Raul O | 8 | 424 | 43711
PR | 120 | 11/28/25 | 521 | Carmona, Raul O | 8 | 424 | 43711
PR | 120 | 11/28/25 | 521 | Carmona, Raul O | 8 | 424 | 43711
PR | 120 | 11/28/25 | 521 | Carmona, Raul O | 8 | 424 | 43711
PR | 120 | 11/28/25 | 521 | Carmona, Raul O | 8 | 424 | 43711
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 0.5 | 30.5 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 6 | 366 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 0.5 | 30.5 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 2.25 | 137.25 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 3 | 183 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 3.25 | 198.25 | 43728
PR | 120 | 11/28/25 | 538 | Gerard, Mitchell J | 5.5 | 335.5 | 43728
PR | 120 | 11/28/25 | 563 | Silva Morales, Jair J | 2.5 | 85 | 43753
PR | 120 | 12/05/25 | 47 | Carmona, Raul O | 8 | 424 | 13715
PR | 120 | 12/05/25 | 47 | Carmona, Raul O | 8 | 424 | 13715
PR | 120 | 12/05/25 | 47 | Carmona, Raul O | 8 | 424 | 13715
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 2.25 | 137.25 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 3.25 | 198.25 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 1.5 | 91.5 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 1 | 61 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 1.25 | 76.25 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 1.75 | 106.75 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 0.5 | 30.5 | 13732
PR | 120 | 12/05/25 | 64 | Gerard, Mitchell J | 2 | 122 | 13732
PR | 120 | 12/12/25 | 182 | Barnhart, Joseph N | 2 | 136 | 23717
PR | 120 | 12/12/25 | 184 | Carmona, Raul O | 8 | 424 | 23719
PR | 120 | 12/12/25 | 184 | Carmona, Raul O | 8 | 424 | 23719
PR | 120 | 12/12/25 | 184 | Carmona, Raul O | 8 | 424 | 23719
PR | 120 | 12/12/25 | 184 | Carmona, Raul O | 8 | 424 | 23719
PR | 120 | 12/12/25 | 184 | Carmona, Raul O | 8 | 424 | 23719
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 2 | 122 | 23736
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 0.25 | 15.25 | 23736
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 3.75 | 228.75 | 23736
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 5.25 | 320.25 | 23736
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 3.5 | 213.5 | 23736
PR | 120 | 12/12/25 | 201 | Gerard, Mitchell J | 1 | 61 | 23736
PR | 120 | 12/19/25 | 325 | Carmona, Raul O | 8 | 424 | 33723
PR | 120 | 12/19/25 | 325 | Carmona, Raul O | 8 | 424 | 33723
PR | 120 | 12/19/25 | 325 | Carmona, Raul O | 8 | 424 | 33723
PR | 120 | 12/19/25 | 342 | Gerard, Mitchell J | 1.5 | 91.5 | 33740
PR | 120 | 12/19/25 | 342 | Gerard, Mitchell J | 3 | 183 | 33740
PR | 120 | 12/19/25 | 342 | Gerard, Mitchell J | 4.5 | 274.5 | 33740
PR | 120 | 12/19/25 | 342 | Gerard, Mitchell J | 1.75 | 106.75 | 33740
PR | 120 | 12/26/25 | 511 | Barnhart, Joseph N | 0.5 | 34 | 43729
PR | 120 | 01/02/26 | 15 | Barnhart, Joseph N | 2.25 | 153 | 13733
PR | 120 | 01/02/26 | 15 | Barnhart, Joseph N | 0.5 | 34 | 13733
PR | 120 | 01/02/26 | 15 | Barnhart, Joseph N | 1 | 68 | 13733
PR | 120 | 01/02/26 | 34 | Gerard, Mitchell J | 3.75 | 228.75 | 13752
PR | 120 | 01/02/26 | 34 | Gerard, Mitchell J | 5 | 305 | 13752
PR | 120 | 01/09/26 | 149 | Gerard, Mitchell J | 1.75 | 110.25 | 23756
PR | 120 | 01/16/26 | 276 | Barnhart, Joseph N | 1 | 70 | 33741
PR | 120 | 01/16/26 | 276 | Barnhart, Joseph N | 0.5 | 35 | 33741
PR | 120 | 01/16/26 | 276 | Barnhart, Joseph N | 0.75 | 52.5 | 33741
PR | 120 | 01/23/26 | 467 | Barnhart, Joseph N | 0.25 | 17.5 | 43746
PR | 120 | 01/23/26 | 486 | Gerard, Mitchell J | 3.25 | 204.75 | 43765
PR | 120 | 01/23/26 | 486 | Gerard, Mitchell J | 4.5 | 283.5 | 43765
PR | 120 | 01/30/26 | 599 | Gerard, Mitchell J | 0.75 | 47.25 | 53770
PR | 120 | 01/30/26 | 599 | Gerard, Mitchell J | 3.75 | 236.25 | 53770
PR | 120 | 02/06/26 | 74 | Gerard, Mitchell J | 2.25 | 141.75 | 13774
PR | 120 | 02/06/26 | 74 | Gerard, Mitchell J | 2.5 | 157.5 | 13774
PR | 120 | 02/06/26 | 74 | Gerard, Mitchell J | 3 | 189 | 13774
PR | 120 | 02/13/26 | 189 | Bautista Quintero, Isidoro | 8 | 208 | 23762
PR | 120 | 02/13/26 | 206 | Gerard, Mitchell J | 1.5 | 94.5 | 23779
PR | 120 | 02/20/26 | 304 | Barnhart, Joseph N | 0.5 | 35 | 33768
PR | 120 | 02/20/26 | 322 | Gerard, Mitchell J | 3 | 189 | 33786
PR | 120 | 02/27/26 | 452 | Barnhart, Joseph N | 3.5 | 245 | 43772
PR | 120 | 03/06/26 | 65 | Gerard, Mitchell J | 8 | 504 | 13793
PR | 120 | 03/06/26 | 65 | Gerard, Mitchell J | 8 | 504 | 13793
PR | 120 | 03/06/26 | 65 | Gerard, Mitchell J | 2.25 | 141.75 | 13793
PR | 120 | 03/13/26 | 210 | Gerard, Mitchell J | 4.25 | 267.75 | 23797
PR | 120 | 03/13/26 | 210 | Gerard, Mitchell J | 2.75 | 173.25 | 23797
PR | 120 | 03/20/26 | 311 | Barnhart, Joseph N | 1.5 | 105 | 33784
PR | 120 | 03/20/26 | 311 | Barnhart, Joseph N | 0.75 | 52.5 | 33784
PR | 120 | 03/20/26 | 328 | Gerard, Mitchell J | 1.75 | 110.25 | 33801
PR | 120 | 03/20/26 | 328 | Gerard, Mitchell J | 6.25 | 393.75 | 33801
PR | 120 | 03/27/26 | 479 | Barnhart, Joseph N | 1 | 70 | 43788
PR | 120 | 03/27/26 | 496 | Gerard, Mitchell J | 8 | 504 | 43805
PR | 120 | 03/27/26 | 496 | Gerard, Mitchell J | 1.75 | 110.25 | 43805
PR | 120 | 03/27/26 | 496 | Gerard, Mitchell J | 5.75 | 362.25 | 43805
PR | 120 | 03/27/26 | 496 | Gerard, Mitchell J | 0.75 | 47.25 | 43805
PR | 120 | 04/03/26 | 24 | Draves, Steven W | 8 | 456 | 13804
PR | 120 | 04/03/26 | 24 | Draves, Steven W | 8 | 456 | 13804
PR | 120 | 04/03/26 | 29 | Gerard, Mitchell J | 0.25 | 15.75 | 13809
PR | 120 | 04/03/26 | 29 | Gerard, Mitchell J | 8 | 504 | 13809
PR | 120 | 04/03/26 | 29 | Gerard, Mitchell J | 8 | 504 | 13809
PR | 120 | 04/03/26 | 29 | Gerard, Mitchell J | 6.75 | 425.25 | 13809
PR | 130 | 11/22/24 | 531 | Eliassen, Cory H | 13.5 | 513 | 43253
PR | 130 | 11/29/24 | 679 | Eliassen, Cory H | 13.5 | -513 | 53265
PR | 130 | 12/27/24 | 568 | Eliassen, Cory H | 1.5 | 57 | 43318
PR | 130 | 05/02/25 | 9 | Galdamez, Dagoberto A | 8 | 336 | 3494
PR | 130 | 09/05/25 | 19 | Barnhart, Joseph N | 2 | 136 | 13633
PR | 130 | 09/19/25 | 238 | Barnhart, Thomas L | 24 | 1032 | 3634
PR | 130 | 09/19/25 | 248 | Barnhart, Joseph N | 1 | 68 | 33644
PR | 130 | 09/19/25 | 261 | Games, Jordan M | 5 | 265 | 33657
PR | 130 | 09/26/25 | 408 | Barnhart, Thomas L | 8 | 344 | 3640
PR | 130 | 09/26/25 | 410 | Cruz Reyes, Jose | 8 | 328 | 3642
PR | 130 | 09/26/25 | 410 | Cruz Reyes, Jose | 8 | 328 | 3642
PR | 130 | 09/26/25 | 410 | Cruz Reyes, Jose | 8 | 328 | 3642
PR | 130 | 09/26/25 | 419 | Barnhart, Joseph N | 1 | 68 | 43651
PR | 130 | 09/26/25 | 445 | McCabe, Thomas C | 2 | 88 | 43677
PR | 130 | 10/03/25 | 4 | Barnhart, Thomas L | 8 | 344 | 3647
PR | 130 | 10/03/25 | 4 | Barnhart, Thomas L | 8 | 344 | 3647
PR | 130 | 10/03/25 | 4 | Barnhart, Thomas L | 8 | 344 | 3647
PR | 130 | 10/03/25 | 4 | Barnhart, Thomas L | 8 | 344 | 3647
PR | 130 | 10/03/25 | 6 | Cruz Reyes, Jose | 8 | 328 | 3649
PR | 130 | 10/03/25 | 6 | Cruz Reyes, Jose | 8 | 328 | 3649
PR | 130 | 10/03/25 | 6 | Cruz Reyes, Jose | 8 | 328 | 3649
PR | 130 | 10/03/25 | 6 | Cruz Reyes, Jose | 8 | 328 | 3649
PR | 130 | 10/03/25 | 6 | Cruz Reyes, Jose | 8 | 328 | 3649
PR | 130 | 10/03/25 | 15 | Barnhart, Joseph N | 1.25 | 85 | 13658
PR | 130 | 10/03/25 | 15 | Barnhart, Joseph N | 0.75 | 51 | 13658
PR | 130 | 10/03/25 | 15 | Barnhart, Joseph N | 1.25 | 85 | 13658
PR | 130 | 10/03/25 | 15 | Barnhart, Joseph N | 0.75 | 51 | 13658
PR | 130 | 10/03/25 | 15 | Barnhart, Joseph N | 0.25 | 17 | 13658
PR | 130 | 10/03/25 | 27 | Eliassen, Cory H | 7.25 | 275.5 | 13670
PR | 130 | 10/03/25 | 27 | Eliassen, Cory H | 8 | 304 | 13670
PR | 130 | 10/03/25 | 27 | Eliassen, Cory H | 8 | 304 | 13670
PR | 130 | 10/03/25 | 27 | Eliassen, Cory H | 8 | 304 | 13670
PR | 130 | 10/03/25 | 27 | Eliassen, Cory H | 8 | 304 | 13670
PR | 130 | 10/03/25 | 29 | Games, Jordan M | 2 | 106 | 13672
PR | 130 | 10/03/25 | 42 | McCabe, Thomas C | 0.5 | 22 | 13685
PR | 130 | 10/03/25 | 42 | McCabe, Thomas C | 4.25 | 187 | 13685
PR | 130 | 10/10/25 | 156 | Barnhart, Thomas L | 8 | 344 | 3654
PR | 130 | 10/10/25 | 156 | Barnhart, Thomas L | 8 | 344 | 3654
PR | 130 | 10/10/25 | 156 | Barnhart, Thomas L | 8 | 344 | 3654
PR | 130 | 10/10/25 | 156 | Barnhart, Thomas L | 8 | 344 | 3654
PR | 130 | 10/10/25 | 156 | Barnhart, Thomas L | 8 | 344 | 3654
PR | 130 | 10/10/25 | 158 | Cruz Reyes, Jose | 8 | 328 | 3656
PR | 130 | 10/10/25 | 158 | Cruz Reyes, Jose | 8 | 328 | 3656
PR | 130 | 10/10/25 | 158 | Cruz Reyes, Jose | 8 | 328 | 3656
PR | 130 | 10/10/25 | 158 | Cruz Reyes, Jose | 8 | 328 | 3656
PR | 130 | 10/10/25 | 158 | Cruz Reyes, Jose | 8 | 328 | 3656
PR | 130 | 10/10/25 | 167 | Barnhart, Joseph N | 1.5 | 102 | 23665
PR | 130 | 10/10/25 | 167 | Barnhart, Joseph N | 2.75 | 187 | 23665
PR | 130 | 10/10/25 | 179 | Eliassen, Cory H | 8 | 304 | 23677
PR | 130 | 10/10/25 | 179 | Eliassen, Cory H | 8 | 304 | 23677
PR | 130 | 10/10/25 | 179 | Eliassen, Cory H | 8 | 304 | 23677
PR | 130 | 10/10/25 | 179 | Eliassen, Cory H | 8 | 304 | 23677
PR | 130 | 10/10/25 | 179 | Eliassen, Cory H | 8 | 304 | 23677
PR | 130 | 10/10/25 | 195 | McCabe, Thomas C | 0.25 | 11 | 23693
PR | 130 | 10/10/25 | 195 | McCabe, Thomas C | 0.25 | 11 | 23693
PR | 130 | 10/10/25 | 195 | McCabe, Thomas C | 0.25 | 11 | 23693
PR | 130 | 10/17/25 | 360 | Barnhart, Thomas L | 8 | 344 | 3661
PR | 130 | 10/17/25 | 360 | Barnhart, Thomas L | 7 | 301 | 3661
PR | 130 | 10/17/25 | 360 | Barnhart, Thomas L | 8 | 344 | 3661
PR | 130 | 10/17/25 | 360 | Barnhart, Thomas L | 8 | 344 | 3661
PR | 130 | 10/17/25 | 360 | Barnhart, Thomas L | 8 | 344 | 3661
PR | 130 | 10/17/25 | 362 | Cruz Reyes, Jose | 8 | 328 | 3663
PR | 130 | 10/17/25 | 362 | Cruz Reyes, Jose | 8 | 328 | 3663
PR | 130 | 10/17/25 | 362 | Cruz Reyes, Jose | 8 | 328 | 3663
PR | 130 | 10/17/25 | 362 | Cruz Reyes, Jose | 8 | 328 | 3663
PR | 130 | 10/17/25 | 369 | Araque, Mario W | 8 | 192 | 33670
PR | 130 | 10/17/25 | 372 | Barnhart, Joseph N | 2.75 | 187 | 33673
PR | 130 | 10/17/25 | 372 | Barnhart, Joseph N | 0.75 | 51 | 33673
PR | 130 | 10/17/25 | 372 | Barnhart, Joseph N | 1 | 68 | 33673
PR | 130 | 10/17/25 | 384 | Eliassen, Cory H | 4 | 152 | 33685
PR | 130 | 10/17/25 | 384 | Eliassen, Cory H | 8.25 | 313.5 | 33685
PR | 130 | 10/17/25 | 384 | Eliassen, Cory H | 8.25 | 313.5 | 33685
PR | 130 | 10/17/25 | 384 | Eliassen, Cory H | 8 | 304 | 33685
PR | 130 | 10/17/25 | 384 | Eliassen, Cory H | 8 | 304 | 33685
PR | 130 | 10/17/25 | 386 | Games, Jordan M | 8 | 424 | 33687
PR | 130 | 10/17/25 | 400 | McCabe, Thomas C | 1.5 | 66 | 33701
PR | 130 | 10/17/25 | 400 | McCabe, Thomas C | 1.75 | 77 | 33701
PR | 130 | 10/24/25 | 493 | Barnhart, Thomas L | 7.5 | 322.5 | 3669
PR | 130 | 10/24/25 | 493 | Barnhart, Thomas L | 8 | 344 | 3669
PR | 130 | 10/24/25 | 493 | Barnhart, Thomas L | 8 | 344 | 3669
PR | 130 | 10/24/25 | 493 | Barnhart, Thomas L | 8 | 344 | 3669
PR | 130 | 10/24/25 | 493 | Barnhart, Thomas L | 8 | 344 | 3669
PR | 130 | 10/24/25 | 495 | Cruz Reyes, Jose | 8 | 328 | 3671
PR | 130 | 10/24/25 | 495 | Cruz Reyes, Jose | 8 | 328 | 3671
PR | 130 | 10/24/25 | 495 | Cruz Reyes, Jose | 8 | 328 | 3671
PR | 130 | 10/24/25 | 495 | Cruz Reyes, Jose | 8 | 328 | 3671
PR | 130 | 10/24/25 | 495 | Cruz Reyes, Jose | 8 | 328 | 3671
PR | 130 | 10/24/25 | 505 | Barnhart, Joseph N | 4 | 272 | 43681
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 8 | 304 | 43694
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 8.25 | 313.5 | 43694
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 8 | 304 | 43694
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 8 | 304 | 43694
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 7.75 | 294.5 | 43694
PR | 130 | 10/24/25 | 518 | Eliassen, Cory H | 0.25 | 14.25 | 43694
PR | 130 | 10/24/25 | 520 | Games, Jordan M | 8 | 424 | 43696
PR | 130 | 10/24/25 | 520 | Games, Jordan M | 6.25 | 331.25 | 43696
PR | 130 | 10/24/25 | 520 | Games, Jordan M | 8 | 424 | 43696
PR | 130 | 10/24/25 | 534 | McCabe, Thomas C | 1 | 44 | 43710
PR | 130 | 10/31/25 | 660 | Barnhart, Thomas L | 8 | 344 | 3677
PR | 130 | 10/31/25 | 660 | Barnhart, Thomas L | 8 | 344 | 3677
PR | 130 | 10/31/25 | 660 | Barnhart, Thomas L | 8 | 344 | 3677
PR | 130 | 10/31/25 | 660 | Barnhart, Thomas L | 8 | 344 | 3677
PR | 130 | 10/31/25 | 660 | Barnhart, Thomas L | 8 | 344 | 3677
PR | 130 | 10/31/25 | 662 | Cruz Reyes, Jose | 8 | 328 | 3679
PR | 130 | 10/31/25 | 662 | Cruz Reyes, Jose | 8 | 328 | 3679
PR | 130 | 10/31/25 | 662 | Cruz Reyes, Jose | 8 | 328 | 3679
PR | 130 | 10/31/25 | 662 | Cruz Reyes, Jose | 8 | 328 | 3679
PR | 130 | 10/31/25 | 662 | Cruz Reyes, Jose | 7 | 287 | 3679
PR | 130 | 10/31/25 | 670 | Barnhart, Joseph N | 1 | 68 | 53687
PR | 130 | 10/31/25 | 670 | Barnhart, Joseph N | 2.25 | 153 | 53687
PR | 130 | 10/31/25 | 684 | Eliassen, Cory H | 8 | 304 | 53701
PR | 130 | 10/31/25 | 684 | Eliassen, Cory H | 8 | 304 | 53701
PR | 130 | 10/31/25 | 684 | Eliassen, Cory H | 8 | 304 | 53701
PR | 130 | 10/31/25 | 684 | Eliassen, Cory H | 8 | 304 | 53701
PR | 130 | 10/31/25 | 684 | Eliassen, Cory H | 8 | 304 | 53701
PR | 130 | 10/31/25 | 686 | Games, Jordan M | 2.25 | 119.25 | 53703
PR | 130 | 10/31/25 | 702 | McCabe, Thomas C | 1 | 44 | 53719
PR | 130 | 11/07/25 | 49 | Barnhart, Thomas L | 8 | 344 | 3683
PR | 130 | 11/07/25 | 49 | Barnhart, Thomas L | 8 | 344 | 3683
PR | 130 | 11/07/25 | 49 | Barnhart, Thomas L | 8 | 344 | 3683
PR | 130 | 11/07/25 | 49 | Barnhart, Thomas L | 8 | 344 | 3683
PR | 130 | 11/07/25 | 49 | Barnhart, Thomas L | 8 | 344 | 3683
PR | 130 | 11/07/25 | 51 | Cruz Reyes, Jose | 8 | 328 | 3685
PR | 130 | 11/07/25 | 51 | Cruz Reyes, Jose | 8 | 328 | 3685
PR | 130 | 11/07/25 | 51 | Cruz Reyes, Jose | 8 | 328 | 3685
PR | 130 | 11/07/25 | 51 | Cruz Reyes, Jose | 8 | 328 | 3685
PR | 130 | 11/07/25 | 51 | Cruz Reyes, Jose | 8 | 328 | 3685
PR | 130 | 11/07/25 | 59 | Barnhart, Joseph N | 1.5 | 102 | 13693
PR | 130 | 11/07/25 | 59 | Barnhart, Joseph N | 1.5 | 102 | 13693
PR | 130 | 11/07/25 | 59 | Barnhart, Joseph N | 1.75 | 119 | 13693
PR | 130 | 11/07/25 | 73 | Eliassen, Cory H | 8 | 304 | 13707
PR | 130 | 11/07/25 | 73 | Eliassen, Cory H | 8 | 304 | 13707
PR | 130 | 11/07/25 | 73 | Eliassen, Cory H | 8 | 304 | 13707
PR | 130 | 11/07/25 | 73 | Eliassen, Cory H | 4.25 | 161.5 | 13707
PR | 130 | 11/07/25 | 73 | Eliassen, Cory H | 8 | 304 | 13707
PR | 130 | 11/07/25 | 77 | Gerard, Mitchell J | 0.5 | 30.5 | 13711
PR | 130 | 11/14/25 | 209 | Barnhart, Thomas L | 8 | 344 | 3689
PR | 130 | 11/14/25 | 209 | Barnhart, Thomas L | 8 | 344 | 3689
PR | 130 | 11/14/25 | 209 | Barnhart, Thomas L | 8 | 344 | 3689
PR | 130 | 11/14/25 | 209 | Barnhart, Thomas L | 8 | 344 | 3689
PR | 130 | 11/14/25 | 209 | Barnhart, Thomas L | 8 | 344 | 3689
PR | 130 | 11/14/25 | 211 | Cruz Reyes, Jose | 8 | 328 | 3691
PR | 130 | 11/14/25 | 211 | Cruz Reyes, Jose | 8 | 328 | 3691
PR | 130 | 11/14/25 | 211 | Cruz Reyes, Jose | 7.75 | 317.75 | 3691
PR | 130 | 11/14/25 | 219 | Barnhart, Joseph N | 2 | 136 | 23699
PR | 130 | 11/14/25 | 219 | Barnhart, Joseph N | 1.25 | 85 | 23699
PR | 130 | 11/14/25 | 233 | Eliassen, Cory H | 8 | 304 | 23713
PR | 130 | 11/14/25 | 233 | Eliassen, Cory H | 8 | 304 | 23713
PR | 130 | 11/14/25 | 233 | Eliassen, Cory H | 8 | 304 | 23713
PR | 130 | 11/14/25 | 233 | Eliassen, Cory H | 8 | 304 | 23713
PR | 130 | 11/14/25 | 233 | Eliassen, Cory H | 8 | 304 | 23713
PR | 130 | 11/14/25 | 237 | Gerard, Mitchell J | 1 | 61 | 23717
PR | 130 | 11/14/25 | 237 | Gerard, Mitchell J | 4 | 244 | 23717
PR | 130 | 11/21/25 | 325 | Barnhart, Thomas L | 7.5 | 322.5 | 3694
PR | 130 | 11/21/25 | 325 | Barnhart, Thomas L | 8 | 344 | 3694
PR | 130 | 11/21/25 | 325 | Barnhart, Thomas L | 8 | 344 | 3694
PR | 130 | 11/21/25 | 325 | Barnhart, Thomas L | 8 | 344 | 3694
PR | 130 | 11/21/25 | 325 | Barnhart, Thomas L | 8 | 344 | 3694
PR | 130 | 11/21/25 | 327 | Cruz Reyes, Jose | 8 | 328 | 3696
PR | 130 | 11/21/25 | 327 | Cruz Reyes, Jose | 8 | 328 | 3696
PR | 130 | 11/21/25 | 327 | Cruz Reyes, Jose | 8 | 328 | 3696
PR | 130 | 11/21/25 | 327 | Cruz Reyes, Jose | 7 | 287 | 3696
PR | 130 | 11/21/25 | 350 | Eliassen, Cory H | 8 | 304 | 33719
PR | 130 | 11/21/25 | 350 | Eliassen, Cory H | 8.25 | 313.5 | 33719
PR | 130 | 11/21/25 | 350 | Eliassen, Cory H | 8 | 304 | 33719
PR | 130 | 11/21/25 | 350 | Eliassen, Cory H | 8 | 304 | 33719
PR | 130 | 11/21/25 | 354 | Gerard, Mitchell J | 2.25 | 137.25 | 33723
PR | 130 | 11/21/25 | 354 | Gerard, Mitchell J | 1.25 | 76.25 | 33723
PR | 130 | 11/21/25 | 354 | Gerard, Mitchell J | 1 | 61 | 33723
PR | 130 | 11/28/25 | 509 | Barnhart, Thomas L | 8 | 344 | 3699
PR | 130 | 11/28/25 | 509 | Barnhart, Thomas L | 8 | 344 | 3699
PR | 130 | 11/28/25 | 509 | Barnhart, Thomas L | 8 | 344 | 3699
PR | 130 | 11/28/25 | 509 | Barnhart, Thomas L | 8 | 344 | 3699
PR | 130 | 11/28/25 | 509 | Barnhart, Thomas L | 8 | 344 | 3699
PR | 130 | 11/28/25 | 511 | Cruz Reyes, Jose | 8 | 328 | 3701
PR | 130 | 11/28/25 | 511 | Cruz Reyes, Jose | 8 | 328 | 3701
PR | 130 | 11/28/25 | 511 | Cruz Reyes, Jose | 8 | 328 | 3701
PR | 130 | 11/28/25 | 511 | Cruz Reyes, Jose | 8 | 328 | 3701
PR | 130 | 11/28/25 | 511 | Cruz Reyes, Jose | 8 | 328 | 3701
PR | 130 | 11/28/25 | 519 | Barnhart, Joseph N | 0.25 | 17 | 43709
PR | 130 | 11/28/25 | 519 | Barnhart, Joseph N | 0.25 | 17 | 43709
PR | 130 | 11/28/25 | 533 | Eliassen, Cory H | 8 | 304 | 43723
PR | 130 | 11/28/25 | 533 | Eliassen, Cory H | 8 | 304 | 43723
PR | 130 | 11/28/25 | 533 | Eliassen, Cory H | 8 | 304 | 43723
PR | 130 | 11/28/25 | 533 | Eliassen, Cory H | 8 | 304 | 43723
PR | 130 | 11/28/25 | 533 | Eliassen, Cory H | 8 | 304 | 43723
PR | 130 | 11/28/25 | 538 | Gerard, Mitchell J | 2 | 122 | 43728
PR | 130 | 12/05/25 | 35 | Barnhart, Thomas L | 8 | 344 | 3703
PR | 130 | 12/05/25 | 35 | Barnhart, Thomas L | 8 | 344 | 3703
PR | 130 | 12/05/25 | 35 | Barnhart, Thomas L | 8 | 344 | 3703
PR | 130 | 12/05/25 | 37 | Cruz Reyes, Jose | 8 | 328 | 3705
PR | 130 | 12/05/25 | 37 | Cruz Reyes, Jose | 8 | 328 | 3705
PR | 130 | 12/05/25 | 37 | Cruz Reyes, Jose | 8 | 328 | 3705
PR | 130 | 12/05/25 | 59 | Eliassen, Cory H | 8 | 304 | 13727
PR | 130 | 12/05/25 | 59 | Eliassen, Cory H | 8 | 304 | 13727
PR | 130 | 12/05/25 | 59 | Eliassen, Cory H | 8 | 304 | 13727
PR | 130 | 12/05/25 | 64 | Gerard, Mitchell J | 0.75 | 45.75 | 13732
PR | 130 | 12/05/25 | 64 | Gerard, Mitchell J | 0.75 | 45.75 | 13732
PR | 130 | 12/12/25 | 172 | Barnhart, Thomas L | 8 | 344 | 3707
PR | 130 | 12/12/25 | 172 | Barnhart, Thomas L | 8 | 344 | 3707
PR | 130 | 12/12/25 | 172 | Barnhart, Thomas L | 8 | 344 | 3707
PR | 130 | 12/12/25 | 172 | Barnhart, Thomas L | 8 | 344 | 3707
PR | 130 | 12/12/25 | 172 | Barnhart, Thomas L | 8 | 344 | 3707
PR | 130 | 12/12/25 | 174 | Cruz Reyes, Jose | 8 | 328 | 3709
PR | 130 | 12/12/25 | 174 | Cruz Reyes, Jose | 8 | 328 | 3709
PR | 130 | 12/12/25 | 174 | Cruz Reyes, Jose | 8 | 328 | 3709
PR | 130 | 12/12/25 | 174 | Cruz Reyes, Jose | 5 | 205 | 3709
PR | 130 | 12/12/25 | 174 | Cruz Reyes, Jose | 8 | 328 | 3709
PR | 130 | 12/12/25 | 182 | Barnhart, Joseph N | 1 | 68 | 23717
PR | 130 | 12/12/25 | 182 | Barnhart, Joseph N | 1.25 | 85 | 23717
PR | 130 | 12/12/25 | 182 | Barnhart, Joseph N | 0.5 | 34 | 23717
PR | 130 | 12/12/25 | 196 | Eliassen, Cory H | 8 | 304 | 23731
PR | 130 | 12/12/25 | 196 | Eliassen, Cory H | 8 | 304 | 23731
PR | 130 | 12/12/25 | 196 | Eliassen, Cory H | 8 | 304 | 23731
PR | 130 | 12/12/25 | 196 | Eliassen, Cory H | 8 | 304 | 23731
PR | 130 | 12/12/25 | 196 | Eliassen, Cory H | 8 | 304 | 23731
PR | 130 | 12/12/25 | 201 | Gerard, Mitchell J | 2.75 | 167.75 | 23736
PR | 130 | 12/12/25 | 201 | Gerard, Mitchell J | 2.25 | 137.25 | 23736
PR | 130 | 12/12/25 | 201 | Gerard, Mitchell J | 3.25 | 198.25 | 23736
PR | 130 | 12/12/25 | 201 | Gerard, Mitchell J | 3.75 | 228.75 | 23736
PR | 130 | 12/19/25 | 313 | Barnhart, Thomas L | 7.5 | 322.5 | 3711
PR | 130 | 12/19/25 | 313 | Barnhart, Thomas L | 8 | 344 | 3711
PR | 130 | 12/19/25 | 313 | Barnhart, Thomas L | 8 | 344 | 3711
PR | 130 | 12/19/25 | 313 | Barnhart, Thomas L | 8 | 344 | 3711
PR | 130 | 12/19/25 | 313 | Barnhart, Thomas L | 8 | 344 | 3711
PR | 130 | 12/19/25 | 315 | Cruz Reyes, Jose | 8 | 328 | 3713
PR | 130 | 12/19/25 | 315 | Cruz Reyes, Jose | 8 | 328 | 3713
PR | 130 | 12/19/25 | 315 | Cruz Reyes, Jose | 8 | 328 | 3713
PR | 130 | 12/19/25 | 315 | Cruz Reyes, Jose | 8 | 328 | 3713
PR | 130 | 12/19/25 | 315 | Cruz Reyes, Jose | 8 | 328 | 3713
PR | 130 | 12/19/25 | 323 | Barnhart, Joseph N | 0.5 | 34 | 33721
PR | 130 | 12/19/25 | 337 | Eliassen, Cory H | 7.75 | 294.5 | 33735
PR | 130 | 12/19/25 | 337 | Eliassen, Cory H | 8 | 304 | 33735
PR | 130 | 12/19/25 | 337 | Eliassen, Cory H | 8 | 304 | 33735
PR | 130 | 12/19/25 | 337 | Eliassen, Cory H | 8 | 304 | 33735
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 1.25 | 76.25 | 33740
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 6.25 | 381.25 | 33740
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 7.25 | 442.25 | 33740
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 2 | 122 | 33740
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 3.25 | 198.25 | 33740
PR | 130 | 12/19/25 | 342 | Gerard, Mitchell J | 1.5 | 91.5 | 33740
PR | 130 | 12/26/25 | 501 | Barnhart, Thomas L | 8 | 344 | 3719
PR | 130 | 12/26/25 | 501 | Barnhart, Thomas L | 8 | 344 | 3719
PR | 130 | 12/26/25 | 501 | Barnhart, Thomas L | 8 | 344 | 3719
PR | 130 | 12/26/25 | 501 | Barnhart, Thomas L | 8 | 344 | 3719
PR | 130 | 12/26/25 | 503 | Cruz Reyes, Jose | 8 | 328 | 3721
PR | 130 | 12/26/25 | 503 | Cruz Reyes, Jose | 8 | 328 | 3721
PR | 130 | 12/26/25 | 503 | Cruz Reyes, Jose | 8 | 328 | 3721
PR | 130 | 12/26/25 | 503 | Cruz Reyes, Jose | 8 | 328 | 3721
PR | 130 | 12/26/25 | 511 | Barnhart, Joseph N | 1 | 68 | 43729
PR | 130 | 12/26/25 | 525 | Eliassen, Cory H | 8 | 304 | 43743
PR | 130 | 12/26/25 | 525 | Eliassen, Cory H | 7.75 | 294.5 | 43743
PR | 130 | 12/26/25 | 525 | Eliassen, Cory H | 8 | 304 | 43743
PR | 130 | 12/26/25 | 525 | Eliassen, Cory H | 8 | 304 | 43743
PR | 130 | 12/26/25 | 530 | Gerard, Mitchell J | 6.5 | 396.5 | 43748
PR | 130 | 12/26/25 | 530 | Gerard, Mitchell J | 7.25 | 442.25 | 43748
PR | 130 | 12/26/25 | 530 | Gerard, Mitchell J | 7.75 | 472.75 | 43748
PR | 130 | 01/02/26 | 5 | Barnhart, Thomas L | 8 | 344 | 3723
PR | 130 | 01/02/26 | 5 | Barnhart, Thomas L | 8 | 344 | 3723
PR | 130 | 01/02/26 | 5 | Barnhart, Thomas L | 5.5 | 236.5 | 3723
PR | 130 | 01/02/26 | 7 | Cruz Reyes, Jose | 8 | 328 | 3725
PR | 130 | 01/02/26 | 7 | Cruz Reyes, Jose | 8 | 328 | 3725
PR | 130 | 01/02/26 | 7 | Cruz Reyes, Jose | 8 | 328 | 3725
PR | 130 | 01/02/26 | 15 | Barnhart, Joseph N | 0.5 | 34 | 13733
PR | 130 | 01/02/26 | 15 | Barnhart, Joseph N | 0.75 | 51 | 13733
PR | 130 | 01/02/26 | 15 | Barnhart, Joseph N | 2 | 136 | 13733
PR | 130 | 01/02/26 | 29 | Eliassen, Cory H | 8 | 304 | 13747
PR | 130 | 01/02/26 | 29 | Eliassen, Cory H | 4.5 | 171 | 13747
PR | 130 | 01/02/26 | 29 | Eliassen, Cory H | 8 | 304 | 13747
PR | 130 | 01/09/26 | 120 | Barnhart, Thomas L | 8 | 360 | 3727
PR | 130 | 01/09/26 | 120 | Barnhart, Thomas L | 8 | 360 | 3727
PR | 130 | 01/09/26 | 120 | Barnhart, Thomas L | 7.5 | 337.5 | 3727
PR | 130 | 01/09/26 | 122 | Cruz Reyes, Jose | 8 | 336 | 3729
PR | 130 | 01/09/26 | 122 | Cruz Reyes, Jose | 8 | 336 | 3729
PR | 130 | 01/09/26 | 122 | Cruz Reyes, Jose | 8 | 336 | 3729
PR | 130 | 01/09/26 | 130 | Barnhart, Joseph N | 1.5 | 105 | 23737
PR | 130 | 01/09/26 | 130 | Barnhart, Joseph N | 1.75 | 122.5 | 23737
PR | 130 | 01/09/26 | 144 | Eliassen, Cory H | 8.25 | 321.75 | 23751
PR | 130 | 01/09/26 | 144 | Eliassen, Cory H | 5.5 | 214.5 | 23751
PR | 130 | 01/09/26 | 144 | Eliassen, Cory H | 8 | 312 | 23751
PR | 130 | 01/09/26 | 149 | Gerard, Mitchell J | 5.75 | 362.25 | 23756
PR | 130 | 01/09/26 | 149 | Gerard, Mitchell J | 1 | 63 | 23756
PR | 130 | 01/09/26 | 149 | Gerard, Mitchell J | 0.75 | 47.25 | 23756
PR | 130 | 01/09/26 | 149 | Gerard, Mitchell J | 3.25 | 204.75 | 23756
PR | 130 | 01/09/26 | 176 | Swails, Melanie L | 8 | 464 | 23783
PR | 130 | 01/09/26 | 176 | Swails, Melanie L | 8 | 464 | 23783
PR | 130 | 01/09/26 | 176 | Swails, Melanie L | 8 | 464 | 23783
PR | 130 | 01/09/26 | 188 | Swails, Melanie L | 24 | -1392 | 23790
PR | 130 | 01/16/26 | 266 | Barnhart, Thomas L | 8 | 360 | 3731
PR | 130 | 01/16/26 | 266 | Barnhart, Thomas L | 8 | 360 | 3731
PR | 130 | 01/16/26 | 268 | Cruz Reyes, Jose | 8 | 336 | 3733
PR | 130 | 01/16/26 | 268 | Cruz Reyes, Jose | 8 | 336 | 3733
PR | 130 | 01/16/26 | 268 | Cruz Reyes, Jose | 8 | 336 | 3733
PR | 130 | 01/16/26 | 268 | Cruz Reyes, Jose | 8 | 336 | 3733
PR | 130 | 01/16/26 | 268 | Cruz Reyes, Jose | 8 | 336 | 3733
PR | 130 | 01/16/26 | 276 | Barnhart, Joseph N | 5.5 | 385 | 33741
PR | 130 | 01/16/26 | 276 | Barnhart, Joseph N | 3.25 | 227.5 | 33741
PR | 130 | 01/16/26 | 290 | Eliassen, Cory H | 8 | 312 | 33755
PR | 130 | 01/16/26 | 290 | Eliassen, Cory H | 8 | 312 | 33755
PR | 130 | 01/16/26 | 290 | Eliassen, Cory H | 6 | 234 | 33755
PR | 130 | 01/16/26 | 290 | Eliassen, Cory H | 8 | 312 | 33755
PR | 130 | 01/16/26 | 290 | Eliassen, Cory H | 8 | 312 | 33755
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 8 | 504 | 33760
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 4.25 | 267.75 | 33760
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 1.75 | 110.25 | 33760
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 5 | 315 | 33760
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 6.25 | 393.75 | 33760
PR | 130 | 01/16/26 | 295 | Gerard, Mitchell J | 1 | 63 | 33760
PR | 130 | 01/23/26 | 458 | Cruz Reyes, Jose | 8 | 336 | 3737
PR | 130 | 01/23/26 | 458 | Cruz Reyes, Jose | 8 | 336 | 3737
PR | 130 | 01/23/26 | 458 | Cruz Reyes, Jose | 8 | 336 | 3737
PR | 130 | 01/23/26 | 458 | Cruz Reyes, Jose | 8 | 336 | 3737
PR | 130 | 01/23/26 | 458 | Cruz Reyes, Jose | 8 | 336 | 3737
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 1.75 | 122.5 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 0.75 | 52.5 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 3.25 | 227.5 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 1.5 | 105 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 8 | 560 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 0.75 | 52.5 | 43746
PR | 130 | 01/23/26 | 467 | Barnhart, Joseph N | 1.75 | 122.5 | 43746
PR | 130 | 01/23/26 | 481 | Eliassen, Cory H | 8 | 312 | 43760
PR | 130 | 01/23/26 | 481 | Eliassen, Cory H | 8 | 312 | 43760
PR | 130 | 01/23/26 | 481 | Eliassen, Cory H | 8 | 312 | 43760
PR | 130 | 01/23/26 | 481 | Eliassen, Cory H | 8 | 312 | 43760
PR | 130 | 01/23/26 | 481 | Eliassen, Cory H | 8 | 312 | 43760
PR | 130 | 01/23/26 | 486 | Gerard, Mitchell J | 4.75 | 299.25 | 43765
PR | 130 | 01/23/26 | 486 | Gerard, Mitchell J | 2.5 | 157.5 | 43765
PR | 130 | 01/23/26 | 486 | Gerard, Mitchell J | 6.25 | 393.75 | 43765
PR | 130 | 01/23/26 | 486 | Gerard, Mitchell J | 8 | 504 | 43765
PR | 130 | 01/23/26 | 486 | Gerard, Mitchell J | 8 | 504 | 43765
PR | 130 | 01/30/26 | 569 | Barnhart, Thomas L | 8 | 360 | 3740
PR | 130 | 01/30/26 | 569 | Barnhart, Thomas L | 8 | 360 | 3740
PR | 130 | 01/30/26 | 569 | Barnhart, Thomas L | 8 | 360 | 3740
PR | 130 | 01/30/26 | 571 | Cruz Reyes, Jose | 8 | 336 | 3742
PR | 130 | 01/30/26 | 571 | Cruz Reyes, Jose | 8 | 336 | 3742
PR | 130 | 01/30/26 | 571 | Cruz Reyes, Jose | 8 | 336 | 3742
PR | 130 | 01/30/26 | 571 | Cruz Reyes, Jose | 8 | 336 | 3742
PR | 130 | 01/30/26 | 571 | Cruz Reyes, Jose | 8 | 336 | 3742
PR | 130 | 01/30/26 | 580 | Barnhart, Joseph N | 1.5 | 105 | 53751
PR | 130 | 01/30/26 | 594 | Eliassen, Cory H | 8 | 312 | 53765
PR | 130 | 01/30/26 | 594 | Eliassen, Cory H | 8 | 312 | 53765
PR | 130 | 01/30/26 | 594 | Eliassen, Cory H | 8 | 312 | 53765
PR | 130 | 01/30/26 | 594 | Eliassen, Cory H | 7.75 | 302.25 | 53765
PR | 130 | 01/30/26 | 594 | Eliassen, Cory H | 8 | 312 | 53765
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 0.75 | 47.25 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 3.5 | 220.5 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 8 | 504 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 4.75 | 299.25 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 1 | 63 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 6.75 | 425.25 | 53770
PR | 130 | 01/30/26 | 599 | Gerard, Mitchell J | 4.25 | 267.75 | 53770
PR | 130 | 02/06/26 | 45 | Barnhart, Thomas L | 8 | 360 | 3745
PR | 130 | 02/06/26 | 45 | Barnhart, Thomas L | 8 | 360 | 3745
PR | 130 | 02/06/26 | 45 | Barnhart, Thomas L | 8 | 360 | 3745
PR | 130 | 02/06/26 | 45 | Barnhart, Thomas L | 8 | 360 | 3745
PR | 130 | 02/06/26 | 45 | Barnhart, Thomas L | 8 | 360 | 3745
PR | 130 | 02/06/26 | 47 | Cruz Reyes, Jose | 8 | 336 | 3747
PR | 130 | 02/06/26 | 47 | Cruz Reyes, Jose | 8 | 336 | 3747
PR | 130 | 02/06/26 | 47 | Cruz Reyes, Jose | 8 | 336 | 3747
PR | 130 | 02/06/26 | 47 | Cruz Reyes, Jose | 8 | 336 | 3747
PR | 130 | 02/06/26 | 47 | Cruz Reyes, Jose | 8 | 336 | 3747
PR | 130 | 02/06/26 | 69 | Eliassen, Cory H | 8 | 312 | 13769
PR | 130 | 02/06/26 | 69 | Eliassen, Cory H | 8 | 312 | 13769
PR | 130 | 02/06/26 | 69 | Eliassen, Cory H | 7.75 | 302.25 | 13769
PR | 130 | 02/06/26 | 69 | Eliassen, Cory H | 8 | 312 | 13769
PR | 130 | 02/06/26 | 69 | Eliassen, Cory H | 8 | 312 | 13769
PR | 130 | 02/06/26 | 74 | Gerard, Mitchell J | 3 | 189 | 13774
PR | 130 | 02/06/26 | 74 | Gerard, Mitchell J | 5.75 | 362.25 | 13774
PR | 130 | 02/06/26 | 74 | Gerard, Mitchell J | 8 | 504 | 13774
PR | 130 | 02/06/26 | 74 | Gerard, Mitchell J | 1 | 63 | 13774
PR | 130 | 02/06/26 | 74 | Gerard, Mitchell J | 6.25 | 393.75 | 13774
PR | 130 | 02/13/26 | 177 | Barnhart, Thomas L | 8 | 360 | 3750
PR | 130 | 02/13/26 | 177 | Barnhart, Thomas L | 8 | 360 | 3750
PR | 130 | 02/13/26 | 177 | Barnhart, Thomas L | 8 | 360 | 3750
PR | 130 | 02/13/26 | 177 | Barnhart, Thomas L | 8 | 360 | 3750
PR | 130 | 02/13/26 | 177 | Barnhart, Thomas L | 8 | 360 | 3750
PR | 130 | 02/13/26 | 179 | Cruz Reyes, Jose | 8 | 336 | 3752
PR | 130 | 02/13/26 | 179 | Cruz Reyes, Jose | 8 | 336 | 3752
PR | 130 | 02/13/26 | 179 | Cruz Reyes, Jose | 8 | 336 | 3752
PR | 130 | 02/13/26 | 179 | Cruz Reyes, Jose | 8 | 336 | 3752
PR | 130 | 02/13/26 | 179 | Cruz Reyes, Jose | 8 | 336 | 3752
PR | 130 | 02/13/26 | 201 | Eliassen, Cory H | 5.5 | 214.5 | 23774
PR | 130 | 02/13/26 | 201 | Eliassen, Cory H | 8 | 312 | 23774
PR | 130 | 02/13/26 | 201 | Eliassen, Cory H | 8 | 312 | 23774
PR | 130 | 02/13/26 | 201 | Eliassen, Cory H | 7.75 | 302.25 | 23774
PR | 130 | 02/13/26 | 201 | Eliassen, Cory H | 8.25 | 321.75 | 23774
PR | 130 | 02/13/26 | 206 | Gerard, Mitchell J | 1 | 63 | 23779
PR | 130 | 02/13/26 | 206 | Gerard, Mitchell J | 1.25 | 78.75 | 23779
PR | 130 | 02/13/26 | 206 | Gerard, Mitchell J | 2.75 | 173.25 | 23779
PR | 130 | 02/13/26 | 206 | Gerard, Mitchell J | 3 | 189 | 23779
PR | 130 | 02/20/26 | 293 | Barnhart, Thomas L | 8 | 360 | 3757
PR | 130 | 02/20/26 | 293 | Barnhart, Thomas L | 8 | 360 | 3757
PR | 130 | 02/20/26 | 293 | Barnhart, Thomas L | 8 | 360 | 3757
PR | 130 | 02/20/26 | 293 | Barnhart, Thomas L | 8 | 360 | 3757
PR | 130 | 02/20/26 | 293 | Barnhart, Thomas L | 8 | 360 | 3757
PR | 130 | 02/20/26 | 295 | Cruz Reyes, Jose | 8 | 336 | 3759
PR | 130 | 02/20/26 | 295 | Cruz Reyes, Jose | 8 | 336 | 3759
PR | 130 | 02/20/26 | 295 | Cruz Reyes, Jose | 8 | 336 | 3759
PR | 130 | 02/20/26 | 295 | Cruz Reyes, Jose | 8 | 336 | 3759
PR | 130 | 02/20/26 | 295 | Cruz Reyes, Jose | 8 | 336 | 3759
PR | 130 | 02/20/26 | 304 | Barnhart, Joseph N | 1.25 | 87.5 | 33768
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 2.5 | 157.5 | 33786
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 8.25 | 519.75 | 33786
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 1.5 | 94.5 | 33786
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 2.75 | 173.25 | 33786
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 1 | 63 | 33786
PR | 130 | 02/20/26 | 322 | Gerard, Mitchell J | 5 | 315 | 33786
PR | 130 | 02/27/26 | 442 | Barnhart, Thomas L | 8 | 360 | 3762
PR | 130 | 02/27/26 | 442 | Barnhart, Thomas L | 8 | 360 | 3762
PR | 130 | 02/27/26 | 442 | Barnhart, Thomas L | 8 | 360 | 3762
PR | 130 | 02/27/26 | 442 | Barnhart, Thomas L | 8 | 360 | 3762
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 8 | 336 | 3764
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 8 | 336 | 3764
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 8 | 336 | 3764
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 8 | 336 | 3764
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 3 | 126 | 3764
PR | 130 | 02/27/26 | 444 | Cruz Reyes, Jose | 5 | 210 | 3764
PR | 130 | 02/27/26 | 452 | Barnhart, Joseph N | 5.25 | 367.5 | 43772
PR | 130 | 02/27/26 | 452 | Barnhart, Joseph N | 0.5 | 35 | 43772
PR | 130 | 02/27/26 | 464 | Draves, Steven W | 8 | 456 | 43784
PR | 130 | 02/27/26 | 464 | Draves, Steven W | 8 | 456 | 43784
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 8 | 504 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 8 | 504 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 8 | 504 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 6.75 | 425.25 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 2.25 | 141.75 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 0.75 | 47.25 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 0.25 | 15.75 | 43789
PR | 130 | 02/27/26 | 469 | Gerard, Mitchell J | 2 | 126 | 43789
PR | 130 | 03/06/26 | 38 | Barnhart, Thomas L | 8 | 360 | 3766
PR | 130 | 03/06/26 | 38 | Barnhart, Thomas L | 8 | 360 | 3766
PR | 130 | 03/06/26 | 38 | Barnhart, Thomas L | 8 | 360 | 3766
PR | 130 | 03/06/26 | 38 | Barnhart, Thomas L | 8 | 360 | 3766
PR | 130 | 03/06/26 | 38 | Barnhart, Thomas L | 8 | 360 | 3766
PR | 130 | 03/06/26 | 40 | Cruz Reyes, Jose | 8 | 336 | 3768
PR | 130 | 03/06/26 | 40 | Cruz Reyes, Jose | 8 | 336 | 3768
PR | 130 | 03/06/26 | 40 | Cruz Reyes, Jose | 8 | 336 | 3768
PR | 130 | 03/06/26 | 40 | Cruz Reyes, Jose | 8 | 336 | 3768
PR | 130 | 03/06/26 | 48 | Barnhart, Joseph N | 1.5 | 105 | 13776
PR | 130 | 03/06/26 | 65 | Gerard, Mitchell J | 8 | 504 | 13793
PR | 130 | 03/06/26 | 65 | Gerard, Mitchell J | 6.25 | 393.75 | 13793
PR | 130 | 03/06/26 | 65 | Gerard, Mitchell J | 5.75 | 362.25 | 13793
PR | 130 | 03/06/26 | 82 | Perez Araque, Manuel A | 7.25 | 217.5 | 13810
PR | 130 | 03/06/26 | 82 | Perez Araque, Manuel A | 8 | 240 | 13810
PR | 130 | 03/06/26 | 82 | Perez Araque, Manuel A | 8 | 240 | 13810
PR | 130 | 03/13/26 | 183 | Barnhart, Thomas L | 8 | 360 | 3770
PR | 130 | 03/13/26 | 183 | Barnhart, Thomas L | 8 | 360 | 3770
PR | 130 | 03/13/26 | 183 | Barnhart, Thomas L | 8 | 360 | 3770
PR | 130 | 03/13/26 | 183 | Barnhart, Thomas L | 8 | 360 | 3770
PR | 130 | 03/13/26 | 183 | Barnhart, Thomas L | 8 | 360 | 3770
PR | 130 | 03/13/26 | 185 | Cruz Reyes, Jose | 8 | 336 | 3772
PR | 130 | 03/13/26 | 185 | Cruz Reyes, Jose | 8 | 336 | 3772
PR | 130 | 03/13/26 | 185 | Cruz Reyes, Jose | 8 | 336 | 3772
PR | 130 | 03/13/26 | 185 | Cruz Reyes, Jose | 8 | 336 | 3772
PR | 130 | 03/13/26 | 185 | Cruz Reyes, Jose | 8 | 336 | 3772
PR | 130 | 03/13/26 | 210 | Gerard, Mitchell J | 2.75 | 173.25 | 23797
PR | 130 | 03/13/26 | 210 | Gerard, Mitchell J | 1 | 63 | 23797
PR | 130 | 03/13/26 | 210 | Gerard, Mitchell J | 1.25 | 78.75 | 23797
PR | 130 | 03/13/26 | 210 | Gerard, Mitchell J | 5 | 315 | 23797
PR | 130 | 03/13/26 | 210 | Gerard, Mitchell J | 5.75 | 362.25 | 23797
PR | 130 | 03/13/26 | 227 | Perez Araque, Manuel A | 8 | 240 | 23814
PR | 130 | 03/13/26 | 227 | Perez Araque, Manuel A | 8 | 240 | 23814
PR | 130 | 03/20/26 | 301 | Barnhart, Thomas L | 7.5 | 337.5 | 3774
PR | 130 | 03/20/26 | 301 | Barnhart, Thomas L | 7 | 315 | 3774
PR | 130 | 03/20/26 | 301 | Barnhart, Thomas L | 8 | 360 | 3774
PR | 130 | 03/20/26 | 301 | Barnhart, Thomas L | 8 | 360 | 3774
PR | 130 | 03/20/26 | 301 | Barnhart, Thomas L | 8 | 360 | 3774
PR | 130 | 03/20/26 | 311 | Barnhart, Joseph N | 2.75 | 192.5 | 33784
PR | 130 | 03/20/26 | 328 | Gerard, Mitchell J | 1 | 63 | 33801
PR | 130 | 03/20/26 | 328 | Gerard, Mitchell J | 1.5 | 94.5 | 33801
PR | 130 | 03/20/26 | 328 | Gerard, Mitchell J | 0.75 | 47.25 | 33801
PR | 130 | 03/20/26 | 328 | Gerard, Mitchell J | 6 | 378 | 33801
PR | 130 | 03/27/26 | 469 | Barnhart, Thomas L | 8 | 360 | 3778
PR | 130 | 03/27/26 | 469 | Barnhart, Thomas L | 8 | 360 | 3778
PR | 130 | 03/27/26 | 496 | Gerard, Mitchell J | 0.5 | 31.5 | 43805
PR | 130 | 03/27/26 | 496 | Gerard, Mitchell J | 0.75 | 47.25 | 43805
PR | 130 | 03/27/26 | 496 | Gerard, Mitchell J | 0.5 | 31.5 | 43805
PR | 130 | 03/27/26 | 496 | Gerard, Mitchell J | 2.75 | 173.25 | 43805
PR | 130 | 04/03/26 | 12 | Barnhart, Joseph N | 0.75 | 52.5 | 13792
PR | 140 | 02/28/25 | 516 | Barnhart, Joseph N | 2 | 136 | 43399
PR | 140 | 04/04/25 | 11 | Fox, Tamron P | 6 | 162 | 3453
PR | 140 | 04/04/25 | 20 | Barnhart, Joseph N | 1 | 68 | 13462
PR | 140 | 04/04/25 | 57 | Reed, Reuben H | 6 | 372 | 13499
PR | 140 | 04/11/25 | 174 | Fox, Tamron P | 22 | 594 | 3463
PR | 140 | 04/11/25 | 237 | Reed, Reuben H | 22 | 1364 | 93509
PR | 140 | 04/18/25 | 415 | Fox, Tamron P | 16 | 432 | 3473
PR | 140 | 04/18/25 | 461 | Reed, Reuben H | 16 | 992 | 33519
PR | 140 | 04/25/25 | 554 | Fox, Tamron P | 24 | 648 | 3483
PR | 140 | 04/25/25 | 569 | Cortes Mendiola, Victor H | 3 | 192 | 43498
PR | 140 | 04/25/25 | 600 | Reed, Reuben H | 24 | 1488 | 43529
PR | 140 | 05/02/25 | 8 | Fox, Tamron P | 8 | 216 | 3493
PR | 140 | 05/09/25 | 153 | Fox, Tamron P | 16 | 432 | 3502
PR | 140 | 05/09/25 | 196 | Reed, Reuben H | 16 | 992 | 23545
PR | 140 | 05/16/25 | 395 | Reed, Reuben H | 16 | 992 | 33554
PR | 140 | 05/23/25 | 448 | Fox, Tamron P | 23 | 621 | 3520
PR | 140 | 05/23/25 | 491 | Reed, Reuben H | 15 | 930 | 43563
PR | 140 | 06/20/25 | 332 | Fox, Tamron P | 19 | 532 | 33571
PR | 140 | 06/20/25 | 356 | Reed, Reuben H | 19 | 1178 | 33595
PR | 140 | 07/18/25 | 311 | Barnhart, Joseph N | 0.5 | 34 | 33590
PR | 140 | 08/01/25 | 12 | Barnhart, Joseph N | 2 | 136 | 13603
PR | 140 | 08/01/25 | 17 | Cortes Mendiola, Victor H | 4 | 256 | 13608
PR | 140 | 08/08/25 | 143 | Barnhart, Joseph N | 4 | 272 | 23610
PR | 140 | 08/08/25 | 148 | Cortes Mendiola, Victor H | 3 | 192 | 23615
PR | 140 | 08/08/25 | 164 | Lima Romero, Melvin A | 16 | 704 | 23631
PR | 140 | 08/08/25 | 187 | Zuniga Avilez, Eduar A | 16 | 384 | 23654
PR | 140 | 08/22/25 | 371 | Barnhart, Joseph N | 2 | 136 | 43621
PR | 140 | 08/22/25 | 376 | Cortes Mendiola, Victor H | 1 | 64 | 43626
PR | 140 | 09/12/25 | 116 | Barnhart, Joseph N | 1 | 68 | 23638
PR | 140 | 09/26/25 | 419 | Barnhart, Joseph N | 1.5 | 102 | 43651
PR | 140 | 09/26/25 | 435 | Gerard, Mitchell J | 8 | 488 | 43667
PR | 140 | 10/03/25 | 32 | Gerard, Mitchell J | 8 | 488 | 13675
PR | 140 | 10/03/25 | 32 | Gerard, Mitchell J | 6.5 | 396.5 | 13675
PR | 140 | 10/10/25 | 184 | Gerard, Mitchell J | 8 | 488 | 23682
PR | 140 | 10/17/25 | 389 | Gerard, Mitchell J | 3.5 | 213.5 | 33690
PR | 140 | 10/17/25 | 389 | Gerard, Mitchell J | 7.5 | 457.5 | 33690
PR | 140 | 10/24/25 | 505 | Barnhart, Joseph N | 2 | 136 | 43681
PR | 140 | 10/24/25 | 523 | Gerard, Mitchell J | 2 | 122 | 43699
PR | 140 | 11/07/25 | 77 | Gerard, Mitchell J | 1 | 61 | 13711
PR | 140 | 11/07/25 | 77 | Gerard, Mitchell J | 6 | 366 | 13711
PR | 140 | 11/14/25 | 237 | Gerard, Mitchell J | 2.5 | 152.5 | 23717
PR | 140 | 11/14/25 | 237 | Gerard, Mitchell J | 0.5 | 30.5 | 23717
PR | 140 | 11/14/25 | 237 | Gerard, Mitchell J | 0.5 | 30.5 | 23717
PR | 140 | 11/21/25 | 354 | Gerard, Mitchell J | 1 | 61 | 33723
PR | 140 | 11/21/25 | 354 | Gerard, Mitchell J | 0.5 | 30.5 | 33723
PR | 140 | 11/28/25 | 538 | Gerard, Mitchell J | 2.75 | 167.75 | 43728
PR | 140 | 12/05/25 | 64 | Gerard, Mitchell J | 0.25 | 15.25 | 13732
PR | 140 | 12/05/25 | 64 | Gerard, Mitchell J | 1 | 61 | 13732
PR | 140 | 12/05/25 | 64 | Gerard, Mitchell J | 4.75 | 289.75 | 13732
PR | 140 | 12/19/25 | 342 | Gerard, Mitchell J | 0.5 | 30.5 | 33740
PR | 140 | 12/19/25 | 342 | Gerard, Mitchell J | 0.75 | 45.75 | 33740
PR | 140 | 01/09/26 | 149 | Gerard, Mitchell J | 1 | 63 | 23756
PR | 140 | 01/09/26 | 149 | Gerard, Mitchell J | 1 | 63 | 23756
PR | 140 | 01/16/26 | 295 | Gerard, Mitchell J | 1 | 63 | 33760
PR | 140 | 01/16/26 | 295 | Gerard, Mitchell J | 2.25 | 141.75 | 33760
PR | 140 | 01/16/26 | 295 | Gerard, Mitchell J | 3.25 | 204.75 | 33760
PR | 140 | 01/30/26 | 599 | Gerard, Mitchell J | 2.25 | 141.75 | 53770
PR | 140 | 01/30/26 | 599 | Gerard, Mitchell J | 1.5 | 94.5 | 53770
PR | 140 | 03/20/26 | 328 | Gerard, Mitchell J | 3.5 | 220.5 | 33801
PR | 140 | 03/27/26 | 479 | Barnhart, Joseph N | 0.25 | 17.5 | 43788
PR | 140 | 03/27/26 | 479 | Barnhart, Joseph N | 0.75 | 52.5 | 43788
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 0.5 | 31.5 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 1 | 63 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 2.25 | 141.75 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 0.75 | 47.25 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 1 | 63 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 2.75 | 173.25 | 43805
PR | 140 | 03/27/26 | 496 | Gerard, Mitchell J | 1.5 | 94.5 | 43805
PR | 140 | 04/03/26 | 29 | Gerard, Mitchell J | 8 | 504 | 13809
PR | 140 | 04/03/26 | 29 | Gerard, Mitchell J | 0.5 | 31.5 | 13809
PR | 140 | 04/03/26 | 29 | Gerard, Mitchell J | 1.5 | 94.5 | 13809
PR | 140 | 04/03/26 | 29 | Gerard, Mitchell J | 1.75 | 110.25 | 13809
PR | 141 | 01/17/25 | 354 | Barnhart, Joseph N | 2 | 136 | 33340
PR | 141 | 02/14/25 | 208 | Barnhart, Joseph N | 2.5 | 170 | 23378
PR | 141 | 02/14/25 | 236 | Mendoza Morales, Jesus A | 16 | 656 | 23406
PR | 141 | 02/21/25 | 332 | Cortes Mendiola, Victor H | 3 | 192 | 33394
PR | 141 | 02/21/25 | 354 | Mendoza Morales, Jesus A | 40 | 1640 | 33416
PR | 141 | 02/28/25 | 516 | Barnhart, Joseph N | 2 | 136 | 43399
PR | 141 | 02/28/25 | 522 | Cortes Mendiola, Victor H | 3 | 192 | 43405
PR | 141 | 02/28/25 | 544 | Mendoza Morales, Jesus A | 40 | 1640 | 43427
PR | 141 | 03/07/25 | 35 | Cortes Mendiola, Victor H | 3 | 192 | 13415
PR | 141 | 03/07/25 | 52 | Lima Romero, Melvin A | 40 | 1760 | 13432
PR | 141 | 03/07/25 | 57 | Mendoza Morales, Jesus A | 40 | 1640 | 13437
PR | 141 | 03/07/25 | 61 | Perez Araque, Manuel A | 16 | 400 | 13441
PR | 141 | 03/14/25 | 229 | Barnhart, Joseph N | 1 | 68 | 23420
PR | 141 | 03/14/25 | 252 | Lima Romero, Melvin A | 40 | 1760 | 23443
PR | 141 | 03/14/25 | 257 | Mendoza Morales, Jesus A | 40 | 1640 | 23448
PR | 141 | 03/14/25 | 260 | Paco Leyva, Orlando | 23 | 1403 | 23451
PR | 141 | 03/14/25 | 261 | Perez Araque, Manuel A | 40 | 1000 | 23452
PR | 141 | 03/14/25 | 262 | Portillo Soriano, Walter A | 40 | 1400 | 23453
PR | 141 | 03/21/25 | 422 | Barnhart, Joseph N | 3 | 204 | 93430
PR | 141 | 03/21/25 | 425 | Castro Hernandez, Jose A | 32 | 1728 | 93433
PR | 141 | 03/21/25 | 428 | Cortes Mendiola, Victor H | 8 | 512 | 93436
PR | 141 | 03/21/25 | 445 | Lima Romero, Melvin A | 40 | 1760 | 93453
PR | 141 | 03/21/25 | 450 | Mendoza Morales, Jesus A | 40 | 1640 | 93458
PR | 141 | 03/21/25 | 453 | Paco Leyva, Orlando | 32 | 1952 | 93461
PR | 141 | 03/21/25 | 456 | Ramos Herrera, Franklin J | 24 | 1008 | 93464
PR | 141 | 03/28/25 | 580 | Castro Hernandez, Jose A | 40 | 2160 | 93454
PR | 141 | 03/28/25 | 583 | Cortes Mendiola, Victor H | 5 | 320 | 93457
PR | 141 | 03/28/25 | 601 | Lima Romero, Melvin A | 40 | 1760 | 93475
PR | 141 | 03/28/25 | 607 | Mendoza Morales, Jesus A | 40 | 1640 | 93481
PR | 141 | 03/28/25 | 610 | Paco Leyva, Orlando | 38 | 2318 | 93484
PR | 141 | 03/28/25 | 611 | Perez Araque, Manuel A | 40 | 1000 | 93485
PR | 141 | 03/28/25 | 613 | Ramos Herrera, Franklin J | 40 | 1680 | 93487
PR | 141 | 04/04/25 | 12 | Galdamez, Dagoberto A | 16 | 672 | 3454
PR | 141 | 04/04/25 | 20 | Barnhart, Joseph N | 3 | 204 | 13462
PR | 141 | 04/04/25 | 23 | Castro Hernandez, Jose A | 32 | 1728 | 13465
PR | 141 | 04/04/25 | 26 | Cortes Mendiola, Victor H | 5 | 320 | 13468
PR | 141 | 04/04/25 | 36 | Gerard, Mitchell J | 40 | 2440 | 13478
PR | 141 | 04/04/25 | 44 | Lima Romero, Melvin A | 40 | 1760 | 13486
PR | 141 | 04/04/25 | 50 | Mendoza Morales, Jesus A | 36 | 1476 | 13492
PR | 141 | 04/04/25 | 53 | Paco Leyva, Orlando | 17 | 1037 | 13495
PR | 141 | 04/04/25 | 54 | Perez Araque, Manuel A | 40 | 1000 | 13496
PR | 141 | 04/04/25 | 56 | Ramos Herrera, Franklin J | 40 | 1680 | 13498
PR | 141 | 04/11/25 | 175 | Galdamez, Dagoberto A | 24 | 1008 | 3464
PR | 141 | 04/11/25 | 203 | Castro Hernandez, Jose A | 40 | 2160 | 93475
PR | 141 | 04/11/25 | 216 | Gerard, Mitchell J | 40 | 2440 | 93488
PR | 141 | 04/11/25 | 224 | Lima Romero, Melvin A | 40 | 1760 | 93496
PR | 141 | 04/11/25 | 230 | Mendoza Morales, Jesus A | 32 | 1312 | 93502
PR | 141 | 04/11/25 | 233 | Paco Leyva, Orlando | 40 | 2440 | 93505
PR | 141 | 04/11/25 | 234 | Perez Araque, Manuel A | 16 | 400 | 93506
PR | 141 | 04/11/25 | 236 | Ramos Herrera, Franklin J | 40 | 1680 | 93508
PR | 141 | 04/18/25 | 427 | Castro Hernandez, Jose A | 40 | 2160 | 33485
PR | 141 | 04/18/25 | 430 | Cortes Mendiola, Victor H | 3 | 192 | 33488
PR | 141 | 04/18/25 | 440 | Gerard, Mitchell J | 40 | 2440 | 33498
PR | 141 | 04/18/25 | 448 | Lima Romero, Melvin A | 8 | 352 | 33506
PR | 141 | 04/18/25 | 454 | Mendoza Morales, Jesus A | 40 | 1640 | 33512
PR | 141 | 04/18/25 | 457 | Paco Leyva, Orlando | 32 | 1952 | 33515
PR | 141 | 04/18/25 | 460 | Ramos Herrera, Franklin J | 40 | 1680 | 33518
PR | 141 | 04/25/25 | 566 | Castro Hernandez, Jose A | 32 | 1728 | 43495
PR | 141 | 04/25/25 | 569 | Cortes Mendiola, Victor H | 3 | 192 | 43498
PR | 141 | 04/25/25 | 579 | Gerard, Mitchell J | 40 | 2440 | 43508
PR | 141 | 04/25/25 | 593 | Mendoza Morales, Jesus A | 40 | 1640 | 43522
PR | 141 | 04/25/25 | 594 | Merino Martinez, Humberto | 40 | 1120 | 43523
PR | 141 | 04/25/25 | 596 | Paco Leyva, Orlando | 24 | 1464 | 43525
PR | 141 | 04/25/25 | 599 | Ramos Herrera, Franklin J | 40 | 1680 | 43528
PR | 141 | 05/02/25 | 20 | Castro Hernandez, Jose A | 40 | 2160 | 13505
PR | 141 | 05/02/25 | 23 | Cortes Mendiola, Victor H | 3 | 192 | 13508
PR | 141 | 05/02/25 | 33 | Gerard, Mitchell J | 40 | 2440 | 13518
PR | 141 | 05/02/25 | 46 | Mendoza Morales, Jesus A | 40 | 1640 | 13531
PR | 141 | 05/02/25 | 47 | Merino Martinez, Humberto | 40 | 1120 | 13532
PR | 141 | 05/02/25 | 49 | Paco Leyva, Orlando | 35 | 2135 | 13534
PR | 141 | 05/02/25 | 52 | Ramos Herrera, Franklin J | 24 | 1008 | 13537
PR | 141 | 05/09/25 | 165 | Castro Hernandez, Jose A | 40 | 2160 | 23514
PR | 141 | 05/09/25 | 167 | Cortes Mendiola, Victor H | 2 | 128 | 23516
PR | 141 | 05/09/25 | 176 | Gerard, Mitchell J | 32 | 1952 | 23525
PR | 141 | 05/09/25 | 189 | Mendoza Morales, Jesus A | 32 | 1312 | 23538
PR | 141 | 05/09/25 | 192 | Paco Leyva, Orlando | 32 | 1952 | 23541
PR | 141 | 05/09/25 | 195 | Ramos Herrera, Franklin J | 40 | 1680 | 23544
PR | 141 | 05/16/25 | 364 | Castro Hernandez, Jose A | 40 | 2160 | 33523
PR | 141 | 05/16/25 | 366 | Cortes Mendiola, Victor H | 4 | 256 | 33525
PR | 141 | 05/16/25 | 375 | Gerard, Mitchell J | 40 | 2440 | 33534
PR | 141 | 05/16/25 | 388 | Mendoza Morales, Jesus A | 40 | 1640 | 33547
PR | 141 | 05/16/25 | 391 | Paco Leyva, Orlando | 24 | 1464 | 33550
PR | 141 | 05/16/25 | 394 | Ramos Herrera, Franklin J | 24 | 1008 | 33553
PR | 141 | 05/23/25 | 460 | Castro Hernandez, Jose A | 8 | 432 | 43532
PR | 141 | 05/23/25 | 462 | Cortes Mendiola, Victor H | 6 | 384 | 43534
PR | 141 | 05/23/25 | 471 | Gerard, Mitchell J | 32 | 1952 | 43543
PR | 141 | 05/23/25 | 484 | Mendoza Morales, Jesus A | 40 | 1640 | 43556
PR | 141 | 05/23/25 | 487 | Paco Leyva, Orlando | 8 | 488 | 43559
PR | 141 | 05/30/25 | 560 | Gerard, Mitchell J | 24 | 1464 | 53552
PR | 141 | 05/30/25 | 573 | Mendoza Morales, Jesus A | 24 | 984 | 53565
PR | 141 | 05/30/25 | 576 | Paco Leyva, Orlando | 4 | 244 | 53568
PR | 141 | 06/06/25 | 33 | Barnhart, Joseph N | 2 | 136 | 13545
PR | 141 | 06/06/25 | 38 | Cortes Mendiola, Victor H | 2 | 128 | 13550
PR | 141 | 06/06/25 | 48 | Gerard, Mitchell J | 40 | 2440 | 13560
PR | 141 | 06/06/25 | 60 | Mendoza Morales, Jesus A | 40 | 1640 | 13572
PR | 141 | 06/06/25 | 61 | Merino Martinez, Humberto | 16 | 448 | 13573
PR | 141 | 06/13/25 | 195 | Bautista Quintero, Isidoro | 40 | 960 | 23554
PR | 141 | 06/13/25 | 199 | Cortes Mendiola, Victor H | 5 | 320 | 23558
PR | 141 | 06/13/25 | 222 | Mendoza Morales, Jesus A | 40 | 1640 | 23581
PR | 141 | 06/13/25 | 223 | Merino Martinez, Humberto | 24 | 672 | 23582
PR | 141 | 06/20/25 | 327 | Cortes Mendiola, Victor H | 10 | 640 | 33566
PR | 141 | 06/20/25 | 336 | Gerard, Mitchell J | 40 | 2440 | 33575
PR | 141 | 06/20/25 | 349 | Mendoza Morales, Jesus A | 40 | 1640 | 33588
PR | 141 | 06/27/25 | 481 | Cortes Mendiola, Victor H | 8 | 512 | 43574
PR | 141 | 06/27/25 | 491 | Gerard, Mitchell J | 8 | 488 | 43584
PR | 141 | 06/27/25 | 498 | Lima Romero, Melvin A | 32 | 1408 | 43591
PR | 141 | 06/27/25 | 504 | Mendoza Morales, Jesus A | 40 | 1640 | 43597
PR | 141 | 07/03/25 | 18 | Balderas Ortiz, Ricardo I | 40 | 1760 | 13575
PR | 141 | 07/03/25 | 24 | Cortes Mendiola, Victor H | 19 | 1216 | 13581
PR | 141 | 07/03/25 | 41 | Lima Romero, Melvin A | 40 | 1760 | 13598
PR | 141 | 07/03/25 | 47 | Mendoza Morales, Jesus A | 40 | 1640 | 13604
PR | 141 | 07/03/25 | 59 | Suniga Aviles, Kelvin A | 40 | 960 | 13616
PR | 141 | 07/11/25 | 143 | Balderas Ortiz, Ricardo I | 31 | 1364 | 23582
PR | 141 | 07/11/25 | 149 | Cortes Mendiola, Victor H | 6 | 384 | 23588
PR | 141 | 07/11/25 | 171 | Mendoza Morales, Jesus A | 31 | 1271 | 23610
PR | 141 | 07/11/25 | 180 | Romero Garza, Jesus I | 2 | 66 | 23619
PR | 141 | 07/18/25 | 311 | Barnhart, Joseph N | 2.5 | 170 | 33590
PR | 141 | 07/18/25 | 316 | Cortes Mendiola, Victor H | 4 | 256 | 33595
PR | 141 | 07/18/25 | 332 | Lima Romero, Melvin A | 40 | 1760 | 33611
PR | 141 | 07/18/25 | 338 | Mendoza Morales, Jesus A | 40 | 1640 | 33617
PR | 141 | 07/18/25 | 347 | Romero Garza, Jesus I | 9 | 297 | 33626
PR | 141 | 07/25/25 | 484 | Cortes Mendiola, Victor H | 11 | 704 | 43602
PR | 141 | 07/25/25 | 500 | Lima Romero, Melvin A | 38 | 1672 | 43618
PR | 141 | 07/25/25 | 506 | Mendoza Morales, Jesus A | 39 | 1599 | 43624
PR | 141 | 08/01/25 | 13 | Bautista Quintero, Isidoro | 16 | 384 | 13604
PR | 141 | 08/01/25 | 17 | Cortes Mendiola, Victor H | 3 | 192 | 13608
PR | 141 | 08/01/25 | 33 | Lima Romero, Melvin A | 32 | 1408 | 13624
PR | 141 | 08/01/25 | 51 | Suniga Aviles, Kelvin A | 16 | 384 | 13642
PR | 141 | 08/08/25 | 144 | Bautista Quintero, Isidoro | 40 | 960 | 23611
PR | 141 | 08/08/25 | 148 | Cortes Mendiola, Victor H | 3 | 192 | 23615
PR | 141 | 08/08/25 | 164 | Lima Romero, Melvin A | 16 | 704 | 23631
PR | 141 | 08/08/25 | 182 | Suniga Aviles, Kelvin A | 40 | 960 | 23649
PR | 141 | 08/15/25 | 269 | Bautista Quintero, Isidoro | 40 | 960 | 33616
PR | 141 | 08/15/25 | 273 | Cortes Mendiola, Victor H | 5 | 320 | 33620
PR | 141 | 08/15/25 | 289 | Lima Romero, Melvin A | 40 | 1760 | 33636
PR | 141 | 08/15/25 | 293 | McCabe, Thomas C | 8 | 352 | 33640
PR | 141 | 08/22/25 | 371 | Barnhart, Joseph N | 1 | 68 | 43621
PR | 141 | 08/22/25 | 372 | Bautista Quintero, Isidoro | 40 | 960 | 43622
PR | 141 | 08/22/25 | 376 | Cortes Mendiola, Victor H | 5 | 320 | 43626
PR | 141 | 08/22/25 | 393 | Lima Romero, Melvin A | 32 | 1408 | 43643
PR | 141 | 08/22/25 | 411 | Suniga Aviles, Kelvin A | 40 | 960 | 43661
PR | 141 | 08/29/25 | 534 | Barnhart, Joseph N | 2 | 136 | 53627
PR | 141 | 08/29/25 | 535 | Bautista Quintero, Isidoro | 40 | 960 | 53628
PR | 141 | 08/29/25 | 539 | Cortes Mendiola, Victor H | 7 | 448 | 53632
PR | 141 | 08/29/25 | 556 | Lima Romero, Melvin A | 40 | 1760 | 53649
PR | 141 | 08/29/25 | 574 | Suniga Aviles, Kelvin A | 40 | 960 | 53667
PR | 141 | 09/05/25 | 20 | Bautista Quintero, Isidoro | 16 | 384 | 13634
PR | 141 | 09/05/25 | 59 | Suniga Aviles, Kelvin A | 8 | 192 | 13673
PR | 141 | 09/26/25 | 445 | McCabe, Thomas C | 1.5 | 66 | 43677
PR | 141 | 09/26/25 | 445 | McCabe, Thomas C | 3.5 | 154 | 43677
PR | 141 | 09/26/25 | 445 | McCabe, Thomas C | 0.75 | 33 | 43677
PR | 141 | 09/26/25 | 448 | Merino Martinez, Humberto | 8 | 224 | 43680
PR | 141 | 09/26/25 | 448 | Merino Martinez, Humberto | 8 | 224 | 43680
PR | 141 | 09/26/25 | 452 | Portillo Soriano, Walter A | 8 | 280 | 43684
PR | 141 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A | 3.25 | 165.75 | 13653
PR | 141 | 10/03/25 | 16 | Bautista Quintero, Isidoro | 3.5 | 84 | 13659
PR | 141 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 2 | 128 | 13663
PR | 141 | 10/03/25 | 20 | Cortes Mendiola, Victor H | 0.75 | 48 | 13663
PR | 141 | 10/03/25 | 42 | McCabe, Thomas C | 1.25 | 55 | 13685
PR | 141 | 10/03/25 | 42 | McCabe, Thomas C | 2.75 | 121 | 13685
PR | 141 | 10/03/25 | 42 | McCabe, Thomas C | 1.5 | 66 | 13685
PR | 141 | 10/03/25 | 42 | McCabe, Thomas C | 0.75 | 33 | 13685
PR | 141 | 10/10/25 | 200 | Paco Leyva, Orlando | 0.5 | 30.5 | 23698
PR | 141 | 12/05/25 | 46 | Bautista Quintero, Isidoro | 1 | 24 | 13714
PR | 141 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A | 6.25 | 331.25 | 23755
PR | 141 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A | 8 | 424 | 23755
PR | 141 | 02/13/26 | 189 | Bautista Quintero, Isidoro | 7.25 | 188.5 | 23762
PR | 141 | 02/13/26 | 189 | Bautista Quintero, Isidoro | 6.75 | 175.5 | 23762
PR | 141 | 02/13/26 | 194 | Cortes Mendiola, Victor H | 3 | 198 | 23767
PR | 141 | 02/13/26 | 194 | Cortes Mendiola, Victor H | 8.25 | 544.5 | 23767
PR | 141 | 02/13/26 | 194 | Cortes Mendiola, Victor H | 5 | 330 | 23767
PR | 141 | 02/13/26 | 194 | Cortes Mendiola, Victor H | 3 | 198 | 23767
PR | 141 | 02/13/26 | 194 | Cortes Mendiola, Victor H | 0.25 | 24.75 | 23767
PR | 141 | 02/13/26 | 206 | Gerard, Mitchell J | 1.75 | 110.25 | 23779
PR | 141 | 02/20/26 | 298 | Amaya Gonzalez, Edilberto A | 8 | 424 | 33762
PR | 141 | 02/20/26 | 305 | Bautista Quintero, Isidoro | 8 | 208 | 33769
PR | 141 | 02/27/26 | 444 | Cruz Reyes, Jose | 5 | 315 | 3764
PR | 141 | 02/27/26 | 446 | Amaya Gonzalez, Edilberto A | 5 | 397.5 | 43766
PR | 141 | 02/27/26 | 448 | Aquino, Juan | 5 | 345 | 43768
PR | 141 | 02/27/26 | 450 | Ascencio, Jose L | 5 | 322.5 | 43770
PR | 141 | 02/27/26 | 451 | Balderas Ortiz, Ricardo I | 5 | 220 | 43771
PR | 141 | 02/27/26 | 452 | Barnhart, Joseph N | 2 | 140 | 43772
PR | 141 | 02/27/26 | 452 | Barnhart, Joseph N | 5 | 525 | 43772
PR | 141 | 02/27/26 | 452 | Barnhart, Joseph N | 2 | 210 | 43772
PR | 141 | 02/27/26 | 454 | Carmona, Raul O | 5 | 405 | 43774
PR | 141 | 02/27/26 | 456 | Chevez, Herson G | 5 | 285 | 43776
PR | 141 | 02/27/26 | 458 | Cortes Mendiola, Victor H | 5 | 495 | 43778
PR | 141 | 02/27/26 | 459 | Countryman, Matthew K | 3.25 | 253.5 | 43779
PR | 141 | 02/27/26 | 459 | Countryman, Matthew K | 1.75 | 91 | 43779
PR | 141 | 02/27/26 | 462 | Da Cruz, Eduardo E | 5 | 172.5 | 43782
PR | 141 | 02/27/26 | 464 | Draves, Steven W | 2 | 171 | 43784
PR | 141 | 02/27/26 | 464 | Draves, Steven W | 5 | 427.5 | 43784
PR | 141 | 02/27/26 | 465 | Fox, Tamron P | 5 | 225 | 43785
PR | 141 | 02/27/26 | 469 | Gerard, Mitchell J | 2 | 189 | 43789
PR | 141 | 02/27/26 | 473 | Gorman, Nathan W | 5 | 195 | 43793
PR | 141 | 02/27/26 | 478 | Mackey, Cole J | 5 | 390 | 43798
PR | 141 | 02/27/26 | 480 | Melgar Moz, Brandon | 5 | 195 | 43800
PR | 141 | 02/27/26 | 481 | Mendoza Morales, Jesus A | 5 | 322.5 | 43801
PR | 141 | 02/27/26 | 484 | Nunez Bravo, Jose L | 5 | 180 | 43804
PR | 141 | 02/27/26 | 485 | Paco Leyva, Orlando | 5 | 472.5 | 43805
PR | 141 | 02/27/26 | 486 | Perez Araque, Manuel A | 5 | 150 | 43806
PR | 141 | 02/27/26 | 488 | Ramos Herrera, Franklin J | 5 | 322.5 | 43808
PR | 141 | 02/27/26 | 490 | Rodriguez Arevalos, Christian | 4.25 | 331.5 | 43810
PR | 141 | 02/27/26 | 492 | Silva Morales, Jair J | 5 | 262.5 | 43812
PR | 141 | 02/27/26 | 493 | Suniga Aviles, Kelvin A | 5 | 195 | 43813
PR | 141 | 02/27/26 | 498 | Young, Joshua S | 5 | 390 | 43818
PR | 141 | 02/27/26 | 499 | Zuniga Avilez, Eduar A | 5 | 195 | 43819
PR | 141 | 03/06/26 | 38 | Barnhart, Thomas L | 5 | 225 | 3766
PR | 142 | 03/14/25 | 229 | Barnhart, Joseph N | 1 | 68 | 23420
PR | 142 | 03/21/25 | 422 | Barnhart, Joseph N | 1 | 68 | 93430
PR | 142 | 05/02/25 | 52 | Ramos Herrera, Franklin J | 8 | 336 | 13537
PR | 142 | 05/09/25 | 162 | Barnhart, Joseph N | 1 | 68 | 23511
PR | 142 | 05/16/25 | 391 | Paco Leyva, Orlando | 4 | 244 | 33550
PR | 142 | 07/18/25 | 311 | Barnhart, Joseph N | 1 | 68 | 33590
PR | 142 | 08/01/25 | 12 | Barnhart, Joseph N | 5 | 340 | 13603
PR | 142 | 08/08/25 | 143 | Barnhart, Joseph N | 3 | 204 | 23610
PR | 142 | 08/08/25 | 148 | Cortes Mendiola, Victor H | 4 | 256 | 23615
PR | 142 | 08/15/25 | 273 | Cortes Mendiola, Victor H | 5 | 320 | 33620
PR | 142 | 08/15/25 | 293 | McCabe, Thomas C | 24 | 1056 | 33640
PR | 142 | 08/22/25 | 371 | Barnhart, Joseph N | 5 | 340 | 43621
PR | 142 | 08/29/25 | 534 | Barnhart, Joseph N | 2 | 136 | 53627
PR | 142 | 08/29/25 | 539 | Cortes Mendiola, Victor H | 2 | 128 | 53632
PR | 142 | 09/05/25 | 19 | Barnhart, Joseph N | 4 | 272 | 13633
PR | 142 | 09/05/25 | 24 | Cortes Mendiola, Victor H | 5 | 320 | 13638
PR | 142 | 09/05/25 | 41 | Lima Romero, Melvin A | 16 | 704 | 13655
PR | 142 | 09/12/25 | 116 | Barnhart, Joseph N | 10 | 680 | 23638
PR | 142 | 09/19/25 | 248 | Barnhart, Joseph N | 2 | 136 | 33644
PR | 142 | 10/03/25 | 15 | Barnhart, Joseph N | 3 | 204 | 13658
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 1 | 68 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 3.25 | 221 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 6 | 408 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 1 | 68 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 0.5 | 34 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 3 | 204 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 0.5 | 34 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 1.25 | 85 | 23665
PR | 142 | 10/10/25 | 195 | McCabe, Thomas C | 0.5 | 22 | 23693
PR | 142 | 10/10/25 | 195 | McCabe, Thomas C | 4.5 | 198 | 23693
PR | 142 | 10/10/25 | 195 | McCabe, Thomas C | 5.25 | 231 | 23693
PR | 142 | 10/10/25 | 195 | McCabe, Thomas C | 2.25 | 99 | 23693
PR | 142 | 10/10/25 | 195 | McCabe, Thomas C | 8 | 352 | 23693
PR | 142 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A | 4.5 | 229.5 | 33668
PR | 142 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A | 4.5 | 229.5 | 33668
PR | 142 | 10/17/25 | 372 | Barnhart, Joseph N | 1.25 | 85 | 33673
PR | 142 | 10/17/25 | 372 | Barnhart, Joseph N | 3 | 204 | 33673
PR | 142 | 10/17/25 | 372 | Barnhart, Joseph N | 2 | 136 | 33673
PR | 142 | 10/17/25 | 372 | Barnhart, Joseph N | 1.75 | 119 | 33673
PR | 142 | 10/17/25 | 372 | Barnhart, Joseph N | 0.75 | 51 | 33673
PR | 142 | 10/17/25 | 377 | Cortes Mendiola, Victor H | 4.5 | 288 | 33678
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 2.75 | 121 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 5 | 220 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 6 | 264 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 2.5 | 110 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 4 | 176 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 3.5 | 154 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 2.75 | 121 | 33701
PR | 142 | 10/17/25 | 400 | McCabe, Thomas C | 8 | 352 | 33701
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 3 | 204 | 43681
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 0.75 | 51 | 43681
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 2.25 | 153 | 43681
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 2 | 136 | 43681
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 2.5 | 170 | 43681
PR | 142 | 10/24/25 | 505 | Barnhart, Joseph N | 5.5 | 374 | 43681
PR | 142 | 10/24/25 | 516 | Draves, Steven W | 8 | 440 | 43692
PR | 142 | 10/24/25 | 516 | Draves, Steven W | 8 | 440 | 43692
PR | 142 | 10/24/25 | 516 | Draves, Steven W | 8 | 440 | 43692
PR | 142 | 10/24/25 | 520 | Games, Jordan M | 8 | 424 | 43696
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 1.25 | 55 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 4.75 | 209 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 2 | 88 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 1.25 | 55 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 6.5 | 286 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 2 | 88 | 43710
PR | 142 | 10/24/25 | 534 | McCabe, Thomas C | 3.75 | 165 | 43710
PR | 142 | 10/31/25 | 670 | Barnhart, Joseph N | 0.75 | 51 | 53687
PR | 142 | 10/31/25 | 670 | Barnhart, Joseph N | 2.25 | 153 | 53687
PR | 142 | 10/31/25 | 670 | Barnhart, Joseph N | 1.25 | 85 | 53687
PR | 142 | 10/31/25 | 670 | Barnhart, Joseph N | 1.75 | 119 | 53687
PR | 142 | 10/31/25 | 682 | Draves, Steven W | 8 | 440 | 53699
PR | 142 | 10/31/25 | 682 | Draves, Steven W | 6.75 | 371.25 | 53699
PR | 142 | 10/31/25 | 682 | Draves, Steven W | 8 | 440 | 53699
PR | 142 | 10/31/25 | 682 | Draves, Steven W | 8 | 440 | 53699
PR | 142 | 10/31/25 | 682 | Draves, Steven W | 8 | 440 | 53699
PR | 142 | 10/31/25 | 686 | Games, Jordan M | 8 | 424 | 53703
PR | 142 | 10/31/25 | 686 | Games, Jordan M | 7.75 | 410.75 | 53703
PR | 142 | 10/31/25 | 686 | Games, Jordan M | 6 | 318 | 53703
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 7.75 | 341 | 53719
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 7.25 | 319 | 53719
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 3.5 | 154 | 53719
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 4.25 | 187 | 53719
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 2.5 | 110 | 53719
PR | 142 | 10/31/25 | 702 | McCabe, Thomas C | 3.75 | 165 | 53719
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 0.5 | 34 | 13693
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 0.5 | 34 | 13693
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 1 | 68 | 13693
PR | 142 | 11/07/25 | 71 | Draves, Steven W | 8 | 440 | 13705
PR | 142 | 11/07/25 | 71 | Draves, Steven W | 7.5 | 412.5 | 13705
PR | 142 | 11/07/25 | 71 | Draves, Steven W | 8 | 440 | 13705
PR | 142 | 11/07/25 | 71 | Draves, Steven W | 8 | 440 | 13705
PR | 142 | 11/07/25 | 71 | Draves, Steven W | 8 | 440 | 13705
PR | 142 | 11/07/25 | 77 | Gerard, Mitchell J | 0.75 | 45.75 | 13711
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 3.75 | 255 | 23699
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 4.25 | 289 | 23699
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 0.75 | 51 | 23699
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 0.25 | 17 | 23699
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 2.75 | 187 | 23699
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 0.5 | 34 | 23699
PR | 142 | 11/14/25 | 231 | Draves, Steven W | 8 | 440 | 23711
PR | 142 | 11/14/25 | 231 | Draves, Steven W | 8 | 440 | 23711
PR | 142 | 11/14/25 | 231 | Draves, Steven W | 8 | 440 | 23711
PR | 142 | 11/14/25 | 231 | Draves, Steven W | 8 | 440 | 23711
PR | 142 | 11/14/25 | 231 | Draves, Steven W | 8 | 440 | 23711
PR | 142 | 11/14/25 | 237 | Gerard, Mitchell J | 2.5 | 152.5 | 23717
PR | 142 | 11/21/25 | 348 | Draves, Steven W | 8 | 440 | 33717
PR | 142 | 11/21/25 | 348 | Draves, Steven W | 8 | 440 | 33717
PR | 142 | 11/21/25 | 348 | Draves, Steven W | 8 | 440 | 33717
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 1.75 | 119 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 0.5 | 34 | 43709
PR | 142 | 11/28/25 | 531 | Draves, Steven W | 8.25 | 453.75 | 43721
PR | 142 | 11/28/25 | 531 | Draves, Steven W | 7.5 | 412.5 | 43721
PR | 142 | 11/28/25 | 531 | Draves, Steven W | 8 | 440 | 43721
PR | 142 | 11/28/25 | 531 | Draves, Steven W | 8 | 440 | 43721
PR | 142 | 11/28/25 | 531 | Draves, Steven W | 5.5 | 302.5 | 43721
PR | 142 | 11/28/25 | 538 | Gerard, Mitchell J | 0.25 | 15.25 | 43728
PR | 142 | 12/05/25 | 45 | Barnhart, Joseph N | 0.5 | 34 | 13713
PR | 142 | 12/05/25 | 57 | Draves, Steven W | 8 | 440 | 13725
PR | 142 | 12/05/25 | 57 | Draves, Steven W | 8.5 | 467.5 | 13725
PR | 142 | 12/05/25 | 57 | Draves, Steven W | 8 | 440 | 13725
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 1 | 68 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 5.5 | 374 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 0.75 | 51 | 23717
PR | 142 | 12/12/25 | 194 | Draves, Steven W | 8 | 440 | 23729
PR | 142 | 12/12/25 | 194 | Draves, Steven W | 8 | 440 | 23729
PR | 142 | 12/12/25 | 194 | Draves, Steven W | 8 | 440 | 23729
PR | 142 | 12/12/25 | 194 | Draves, Steven W | 8 | 440 | 23729
PR | 142 | 12/12/25 | 194 | Draves, Steven W | 8 | 440 | 23729
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 1.5 | 102 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 0.5 | 34 | 33721
PR | 142 | 12/19/25 | 335 | Draves, Steven W | 5.5 | 302.5 | 33733
PR | 142 | 12/19/25 | 335 | Draves, Steven W | 8 | 440 | 33733
PR | 142 | 12/19/25 | 335 | Draves, Steven W | 8 | 440 | 33733
PR | 142 | 12/19/25 | 335 | Draves, Steven W | 8 | 440 | 33733
PR | 142 | 12/19/25 | 335 | Draves, Steven W | 8 | 440 | 33733
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 2.25 | 153 | 43729
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 3.25 | 221 | 43729
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 0.25 | 17 | 43729
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 2 | 136 | 43729
PR | 142 | 12/26/25 | 523 | Draves, Steven W | 7.5 | 412.5 | 43741
PR | 142 | 12/26/25 | 523 | Draves, Steven W | 8 | 440 | 43741
PR | 142 | 12/26/25 | 523 | Draves, Steven W | 5.25 | 288.75 | 43741
PR | 142 | 01/02/26 | 15 | Barnhart, Joseph N | 0.25 | 17 | 13733
PR | 142 | 01/02/26 | 15 | Barnhart, Joseph N | 0.75 | 51 | 13733
PR | 142 | 01/02/26 | 15 | Barnhart, Joseph N | 1 | 68 | 13733
PR | 142 | 01/02/26 | 15 | Barnhart, Joseph N | 1 | 68 | 13733
PR | 142 | 01/02/26 | 27 | Draves, Steven W | 8.5 | 467.5 | 13745
PR | 142 | 01/02/26 | 27 | Draves, Steven W | 8 | 440 | 13745
PR | 142 | 01/02/26 | 27 | Draves, Steven W | 5 | 275 | 13745
PR | 142 | 01/02/26 | 34 | Gerard, Mitchell J | 0.75 | 45.75 | 13752
PR | 142 | 01/02/26 | 34 | Gerard, Mitchell J | 7 | 427 | 13752
PR | 142 | 01/09/26 | 130 | Barnhart, Joseph N | 2.75 | 192.5 | 23737
PR | 142 | 01/09/26 | 142 | Draves, Steven W | 8 | 456 | 23749
PR | 142 | 01/09/26 | 142 | Draves, Steven W | 8 | 456 | 23749
PR | 142 | 01/09/26 | 142 | Draves, Steven W | 8 | 456 | 23749
PR | 142 | 01/16/26 | 276 | Barnhart, Joseph N | 0.75 | 52.5 | 33741
PR | 142 | 01/16/26 | 288 | Draves, Steven W | 6 | 342 | 33753
PR | 142 | 01/16/26 | 288 | Draves, Steven W | 8.25 | 470.25 | 33753
PR | 142 | 01/16/26 | 288 | Draves, Steven W | 8 | 456 | 33753
PR | 142 | 01/16/26 | 288 | Draves, Steven W | 8 | 456 | 33753
PR | 142 | 01/16/26 | 288 | Draves, Steven W | 8 | 456 | 33753
PR | 142 | 01/23/26 | 467 | Barnhart, Joseph N | 0.5 | 35 | 43746
PR | 142 | 01/23/26 | 479 | Draves, Steven W | 8 | 456 | 43758
PR | 142 | 01/23/26 | 479 | Draves, Steven W | 7.25 | 413.25 | 43758
PR | 142 | 01/23/26 | 479 | Draves, Steven W | 8 | 456 | 43758
PR | 142 | 01/23/26 | 479 | Draves, Steven W | 8 | 456 | 43758
PR | 142 | 01/23/26 | 479 | Draves, Steven W | 8 | 456 | 43758
PR | 142 | 01/30/26 | 580 | Barnhart, Joseph N | 2.5 | 175 | 53751
PR | 142 | 01/30/26 | 592 | Draves, Steven W | 8 | 456 | 53763
PR | 142 | 01/30/26 | 592 | Draves, Steven W | 8 | 456 | 53763
PR | 142 | 01/30/26 | 592 | Draves, Steven W | 8 | 456 | 53763
PR | 142 | 01/30/26 | 592 | Draves, Steven W | 8 | 456 | 53763
PR | 142 | 01/30/26 | 592 | Draves, Steven W | 8 | 456 | 53763
PR | 142 | 02/06/26 | 56 | Barnhart, Joseph N | 0.5 | 35 | 13756
PR | 142 | 02/06/26 | 56 | Barnhart, Joseph N | 1.25 | 87.5 | 13756
PR | 142 | 02/06/26 | 68 | Draves, Steven W | 8 | 456 | 13768
PR | 142 | 02/06/26 | 68 | Draves, Steven W | 8 | 456 | 13768
PR | 142 | 02/06/26 | 68 | Draves, Steven W | 8 | 456 | 13768
PR | 142 | 02/06/26 | 68 | Draves, Steven W | 8 | 456 | 13768
PR | 142 | 02/06/26 | 68 | Draves, Steven W | 8 | 456 | 13768
PR | 142 | 02/13/26 | 188 | Barnhart, Joseph N | 4.75 | 332.5 | 23761
PR | 142 | 02/13/26 | 188 | Barnhart, Joseph N | 3.75 | 262.5 | 23761
PR | 142 | 02/13/26 | 188 | Barnhart, Joseph N | 6.5 | 682.5 | 23761
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 8 | 456 | 23773
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 8 | 456 | 23773
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 8 | 456 | 23773
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 8 | 456 | 23773
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 8 | 456 | 23773
PR | 142 | 02/13/26 | 200 | Draves, Steven W | 2.5 | 213.75 | 23773
PR | 142 | 02/13/26 | 206 | Gerard, Mitchell J | 5 | 315 | 23779
PR | 142 | 02/13/26 | 206 | Gerard, Mitchell J | 6.5 | 409.5 | 23779
PR | 142 | 02/20/26 | 304 | Barnhart, Joseph N | 5.5 | 385 | 33768
PR | 142 | 02/20/26 | 304 | Barnhart, Joseph N | 0.75 | 52.5 | 33768
PR | 142 | 02/20/26 | 304 | Barnhart, Joseph N | 2 | 140 | 33768
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 2.25 | 128.25 | 33780
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 3.5 | 199.5 | 33780
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 6.5 | 370.5 | 33780
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 8 | 456 | 33780
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 7.5 | 427.5 | 33780
PR | 142 | 02/20/26 | 316 | Draves, Steven W | 8 | 456 | 33780
PR | 142 | 02/20/26 | 322 | Gerard, Mitchell J | 2.5 | 157.5 | 33786
PR | 142 | 02/27/26 | 464 | Draves, Steven W | 8 | 456 | 43784
PR | 142 | 02/27/26 | 464 | Draves, Steven W | 8 | 456 | 43784
PR | 142 | 02/27/26 | 464 | Draves, Steven W | 1 | 57 | 43784
PR | 142 | 02/27/26 | 464 | Draves, Steven W | 7 | 399 | 43784
PR | 142 | 03/06/26 | 60 | Draves, Steven W | 8 | 456 | 13788
PR | 142 | 03/06/26 | 60 | Draves, Steven W | 8 | 456 | 13788
PR | 142 | 03/06/26 | 60 | Draves, Steven W | 8 | 456 | 13788
PR | 142 | 03/06/26 | 60 | Draves, Steven W | 8 | 456 | 13788
PR | 142 | 03/13/26 | 193 | Barnhart, Joseph N | 2.25 | 157.5 | 23780
PR | 142 | 03/27/26 | 479 | Barnhart, Joseph N | 1 | 70 | 43788
PR | 142 | 03/27/26 | 479 | Barnhart, Joseph N | 2.75 | 192.5 | 43788
PR | 142 | 03/27/26 | 491 | Draves, Steven W | 8 | 456 | 43800
PR | 142 | 03/27/26 | 491 | Draves, Steven W | 8 | 456 | 43800
PR | 151 | 10/10/25 | 195 | McCabe, Thomas C | 3.5 | 154 | 23693
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 1 | 44 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 1.5 | 66 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 5 | 220 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 1.25 | 55 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 1 | 44 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 5.25 | 231 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 0.25 | 11 | 43710
PR | 151 | 10/24/25 | 534 | McCabe, Thomas C | 0.5 | 22 | 43710
PR | 151 | 10/31/25 | 702 | McCabe, Thomas C | 0.5 | 22 | 53719
GL | 210 | 07/15/24 | 292 | 2024-07-07 to 2024-07-13 |  | 215.64
AP | 210 | 07/22/24 | 515 | Rosen Supply Kirkland |  | 1068.65 | 24593.01
AP | 210 | 07/22/24 | 516 | Rosen Supply Kirkland |  | 459.44 | 24800.01
GL | 210 | 07/23/24 | 522 | Transfer 2024-07-14 to 2024-07-20 |  | 12.97
GL | 210 | 07/23/24 | 531 | Req 561 |  | 62.18
GL | 210 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 636.19
AP | 210 | 08/01/24 | 130 | Rosen Supply Kirkland |  | 7290.13 | 24983.01
AP | 210 | 08/01/24 | 148 | Pacific Plumbing Supply Co., LLC |  | 66.92 | 51619626
GL | 210 | 08/05/24 | 168 | Req 565 |  | 74.93
GL | 210 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 218.87
AP | 210 | 08/06/24 | 193 | Rosen Supply Kirkland |  | 2037.87 | 25104.01
AP | 210 | 08/06/24 | 197 | Rosen Supply Kirkland |  | 30.56 | 25235.01
GL | 210 | 08/12/24 | 372 |  |  | 346.68
AP | 210 | 08/14/24 | 424 | Core & Main LP $HD Supply Waterworks |  | 417.48 | V415522
AP | 210 | 08/16/24 | 524 | Rosen Supply Kirkland |  | 3190.51 | 25461.01
AP | 210 | 08/16/24 | 525 | Rosen Supply Kirkland |  | 5165.13 | 24593.02
AP | 210 | 08/20/24 | 588 | Keller Supply Company |  | 184.02 | S023114408.001
AP | 210 | 08/20/24 | 589 | Consolidated Supply Co. |  | 7748.68 | S012019633.001
AP | 210 | 08/23/24 | 794 | Pacific Plumbing Supply Co., LLC |  | 12.36 | 51643395
GL | 210 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 126.98
GL | 210 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 174.87
AP | 210 | 09/09/24 | 115 | Core & Main LP $HD Supply Waterworks |  | 375.6 | V570663
GL | 210 | 09/09/24 | 297 | 2024-09-01 to 2024-09-07 |  | 164.71
AP | 210 | 09/10/24 | 180 | Pacific Plumbing Supply Co., LLC |  | 181.81 | 51649181
AP | 210 | 09/10/24 | 181 | Pacific Plumbing Supply Co., LLC |  | 1088.66 | 51651575
AP | 210 | 09/10/24 | 186 | Rosen Supply Kirkland |  | 142.29 | 26199.01
GL | 210 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 134.98
AP | 210 | 09/17/24 | 331 | Pac West Sales |  | 204 | 243932
AP | 210 | 09/20/24 | 483 | Rosen Supply Kirkland |  | 399.73 | 26489.01
AP | 210 | 09/20/24 | 740 | Rosen Supply Kirkland |  | -399.73 | 26489.01A
AP | 210 | 09/20/24 | 741 | Rosen Supply Kirkland |  | 339.73 | 26489.01B
GL | 210 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 59.64
GL | 210 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 462.07
AP | 210 | 09/30/24 | 695 | Core & Main LP $HD Supply Waterworks |  | 92.63 | V656358
AP | 210 | 09/30/24 | 711 | Rosen Supply Kirkland |  | 1251.28 | 26538.01
GL | 210 | 10/08/24 | 123 | Req 594 |  | 104.78
AP | 210 | 10/08/24 | 128 | Rosen Supply Kirkland |  | 450.64 | 26740.01
AP | 210 | 10/08/24 | 129 | Rosen Supply Kirkland |  | 2048.87 | 26741.01
AP | 210 | 10/08/24 | 130 | Rosen Supply Kirkland |  | 54.43 | 26781.01
AP | 210 | 10/14/24 | 330 | Rosen Supply Kirkland |  | 2364.47 | 27064.01
GL | 210 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 45.95
AP | 210 | 10/22/24 | 555 | Pacific Plumbing Supply Co., LLC |  | 97.82 | 51691647
AP | 210 | 10/22/24 | 557 | Rosen Supply Kirkland |  | 101.93 | 27311.01
AP | 210 | 10/29/24 | 711 | Capital One Credit Card |  | 48.74 | 100324J
GL | 210 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 178.92
GL | 210 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 59.64
AP | 210 | 11/12/24 | 307 | Core & Main LP $HD Supply Waterworks |  | 119.28 | V965991
PR | 210 | 01/03/25 | 23 | Amaya Gonzalez, Edilberto A | 16 | 816 | 13312
AP | 210 | 03/12/25 | 181 | Pacific Plumbing Supply Co., LLC |  | 329.78 | 51800462
PR | 210 | 04/18/25 | 446 | Jimenez Alvarenga, Gerson M | 40 | 1560 | 33504
PR | 210 | 06/27/25 | 521 | Young, Joshua S | 8 | 352 | 43614
PR | 210 | 07/03/25 | 35 | Gochez Molina, Douglas O | 24 | 672 | 13592
PR | 210 | 07/18/25 | 352 | Taylor, Evan R | 24 | 1248 | 33631
PR | 210 | 08/15/25 | 263 | Amaya Gonzalez, Edilberto A | 40 | 2040 | 33610
AP | 210 | 10/09/25 | 217 | Core & Main LP $HD Supply Waterworks |  | 283.23 | X762210
GL | 210 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -137.85
AP | 210 | 11/11/25 | 188 | ACME Corp |  | 185.6 | S4815869.001
AP | 210 | 11/18/25 | 312 | Consolidated Supply Co. |  | 120.01 | S012672270.001
GL | 210 | 12/18/25 | 444 | Mitchell Gerard |  | 22.58
GL | 210 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 29.53
AP | 210 | 02/02/26 | 22 | Rosen Supply Kirkland |  | 107.79 | 36050.01
AP | 210 | 02/09/26 | 133 | Rosen Supply Kirkland |  | 2277 | 36153.01
AP | 210 | 03/04/26 | 13 | Capital One Credit Card |  | 16.33 | 011526J1
AP | 210 | 03/04/26 | 15 | Capital One Credit Card |  | 28.4 | 011526J3
AP | 211 | 08/20/24 | 569 | Pacific Plumbing Supply Co., LLC |  | 649.37 | 51638011
GL | 211 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 249.15
GL | 211 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 12.53
AP | 211 | 10/15/24 | 412 | Rosen Supply Kirkland |  | 82.35 | 27175.01
GL | 211 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 419.14
AP | 211 | 10/22/24 | 561 | Consolidated Supply Co. |  | 436.9 | S012142557.001
GL | 211 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 16.23
GL | 211 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 21.59
AP | 211 | 10/29/24 | 724 | Pacific Plumbing Supply Co., LLC |  | 2046.88 | 51697698
GL | 211 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 161.55
GL | 211 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 200
GL | 211 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 3.47
GL | 211 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 200
GL | 211 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 38.85
GL | 211 | 12/30/24 | 679 | 2024-12-22 to 2024-12-28 |  | 201.75
GL | 211 | 01/02/25 | 126 | 2024-12-30 to 2025-01-03 |  | 1384.5
AP | 211 | 01/08/25 | 168 | Pacific Plumbing Supply Co., LLC |  | 1437.56 | 51741259
AP | 211 | 01/13/25 | 271 | Consolidated Supply Co. |  | 19683.27 | S012097701.001
AP | 211 | 01/13/25 | 272 | Consolidated Supply Co. |  | 16818.02 | S012101288.001
AP | 211 | 01/13/25 | 273 | Consolidated Supply Co. |  | 16818.02 | S012101827.001
GL | 211 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 21.59
GL | 211 | 01/20/25 | 425 | 2025-01-12 to 2025-01-18 |  | 681.73
AP | 211 | 01/20/25 | 442 | Pacific Plumbing Supply Co., LLC |  | 7650.24 | 51754895
AP | 211 | 01/22/25 | 479 | Core & Main LP $HD Supply Waterworks |  | 286.76 | W279884
AP | 211 | 01/24/25 | 613 | Rosen Supply Kirkland |  | 2887.32 | 28864.01
AP | 211 | 01/24/25 | 619 | Rosen Supply Kirkland |  | 1487.95 | 29031.01
AP | 211 | 01/24/25 | 628 | Pacific Plumbing Supply Co., LLC |  | 8120.15 | 51758363
AP | 211 | 01/28/25 | 648 | Consolidated Supply Co. |  | 376.83 | S012261275.001
GL | 211 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 471.17
AP | 211 | 02/05/25 | 20 | Rosen Supply Kirkland |  | 3139.03 | 29349.02
GL | 211 | 02/05/25 | 21 | 2025-01-26 to 2025-02-01 |  | 154.83
AP | 211 | 02/07/25 | 101 | Consolidated Supply Co. |  | 18608.87 | S012283500.001
AP | 211 | 02/07/25 | 102 | Consolidated Supply Co. |  | 107.6 | S012283500.002
GL | 211 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 255.92
AP | 211 | 02/11/25 | 145 | Consolidated Supply Co. |  | 9759.69 | S012097701.002
AP | 211 | 02/11/25 | 147 | Consolidated Supply Co. |  | 8693.54 | S012101288.002
AP | 211 | 02/11/25 | 148 | Consolidated Supply Co. |  | 7390.14 | S012101827.002
AP | 211 | 02/11/25 | 149 | Consolidated Supply Co. |  | 1154.6 | S012283500.003
AP | 211 | 02/14/25 | 286 | Rosen Supply Kirkland |  | 1242.97 | 29784.01
GL | 211 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 172.07
GL | 211 | 02/21/25 | 395 | Req 626 |  | 132.3
GL | 211 | 02/21/25 | 396 | Req 627 |  | 230.61
GL | 211 | 02/21/25 | 397 | Req 628 |  | 771.15
AP | 211 | 02/24/25 | 432 | Rosen Supply Kirkland |  | 1378.15 | 29967.01
GL | 211 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 172.53
GL | 211 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 114.78
AP | 211 | 03/06/25 | 88 | Consolidated Supply Co. |  | 1624.25 | S012312601.001
AP | 211 | 03/06/25 | 89 | Consolidated Supply Co. |  | 48.02 | S012312849.001
GL | 211 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 248.98
AP | 211 | 03/12/25 | 183 | Pacific Plumbing Supply Co., LLC |  | 12124.55 | 51799302
AP | 211 | 03/12/25 | 184 | Pacific Plumbing Supply Co., LLC |  | 220.84 | 51799303
AP | 211 | 03/12/25 | 199 | Pacific Plumbing Supply Co., LLC |  | 1061.44 | 51803089
AP | 211 | 03/12/25 | 200 | Pacific Plumbing Supply Co., LLC |  | 349.74 | 51803090
AP | 211 | 03/19/25 | 361 | Consolidated Supply Co. |  | 1128.6 | S012312601.002
AP | 211 | 03/21/25 | 505 | Rosen Supply Kirkland |  | 48.25 | 29031.03
GL | 211 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 367.04
AP | 211 | 03/25/25 | 543 | Consolidated Supply Co. |  | 326.14 | S012340499.001
AP | 211 | 03/25/25 | 544 | Consolidated Supply Co. |  | 100.76 | S012340499.002
AP | 211 | 03/25/25 | 546 | Consolidated Supply Co. |  | 165.73 | S012312601.003
GL | 211 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 161.4
GL | 211 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 125.49
GL | 211 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 270.16
AP | 211 | 04/15/25 | 332 | Pacific Plumbing Supply Co., LLC |  | 10015.89 | 51830542
AP | 211 | 04/21/25 | 510 | Consolidated Supply Co. |  | 607.5 | S012340499.003
AP | 211 | 04/22/25 | 523 | Consolidated Supply Co. |  | 382.81 | S012385026.001
AP | 211 | 04/22/25 | 524 | Consolidated Supply Co. |  | 14.99 | S012385026.002
GL | 211 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 99.67
AP | 211 | 04/23/25 | 532 | Consolidated Supply Co. |  | 222.84 | S012380466.001
GL | 211 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 52
AP | 211 | 05/02/25 | 82 | Consolidated Supply Co. |  | 46.06 | S012380466.002
AP | 211 | 05/02/25 | 99 | Pacific Plumbing Supply Co., LLC |  | 243.86 | 51842905
GL | 211 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 129.38
AP | 211 | 05/12/25 | 264 | Pacific Plumbing Supply Co., LLC |  | 129 | 51852414
GL | 211 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 183.49
GL | 211 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 38.35
AP | 211 | 05/22/25 | 514 | Consolidated Supply Co. |  | 385.54 | S012425693.001
AP | 211 | 05/22/25 | 517 | Consolidated Supply Co. |  | 103.4 | S012428991.001
GL | 211 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 80.27
GL | 211 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 127.5
AP | 211 | 06/11/25 | 170 | Consolidated Supply Co. |  | 103.4 | S012428991.002
GL | 211 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 43.3
GL | 211 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 75.76
GL | 211 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 9.9
GL | 211 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 143.36
AP | 211 | 07/25/25 | 228 | Consolidated Supply Co. |  | 111.08 | S012494177.001
GL | 211 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 145.61
GL | 211 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 18.33
GL | 211 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 176.86
GL | 211 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 111.55
GL | 211 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 119
GL | 211 | 09/30/25 | 504 | 2025-09-22 to 09-26 |  | 9.61
GL | 211 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 6.49
AP | 211 | 10/14/25 | 306 | Rosen Supply Kirkland |  | 160.87 | 34051.01
GL | 211 | 10/21/25 | 459 | 2025-10-12 to 10-18 |  | 35.4
AP | 211 | 10/22/25 | 490 | Pacific Plumbing Supply Co., LLC |  | 215.32 | 51990360
GL | 211 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 162.89
GL | 211 | 11/24/25 | 475 | 2025-11-16 to 11-22 |  | 73.75
GL | 211 | 11/24/25 | 475 | 2025-11-16 to 11-22 |  | -88.43
GL | 211 | 12/04/25 | 103 | Mitchell Gerard |  | 83.69
GL | 211 | 12/08/25 | 126 | 2025-11-30 to 12-06 |  | 23.8
GL | 211 | 12/18/25 | 444 | Mitchell Gerard |  | 30.85
GL | 211 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | -12.35
GL | 212 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 50.58
GL | 212 | 08/07/24 | 216 | & Main |  | 277.08
GL | 212 | 08/21/24 | 686 | Req 576 |  | 465.06
GL | 212 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 173.58
GL | 212 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 121.18
AP | 212 | 09/10/24 | 179 | Pacific Plumbing Supply Co., LLC |  | 1126.2 | 51649179
AP | 212 | 09/18/24 | 373 | Keller Supply Company |  | 4454 | S023360068.001
GL | 212 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 867.21
GL | 212 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 1207.04
AP | 212 | 10/21/24 | 544 | Rosen Supply Kirkland |  | 102.27 | 27241.02
GL | 212 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 1416.64
GL | 212 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 8347.96
GL | 212 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 350.46
AP | 212 | 11/15/24 | 433 | Consolidated Supply Co. |  | 2296.2 | S012155103.001
GL | 212 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 461.52
GL | 212 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 156.72
GL | 212 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 165.71
GL | 212 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 117.9
GL | 212 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 115.28
GL | 220 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 25.56
GL | 220 | 09/03/24 | 5 | 2024-08-25 to 2024-08-31 |  | 323.48
GL | 220 | 09/09/24 | 297 | 2024-09-01 to 2024-09-07 |  | 67.35
GL | 220 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 168.8
AP | 220 | 09/18/24 | 367 | Rosen Supply Kirkland |  | 1021.76 | 25839.01
GL | 220 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 35.74
GL | 220 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 244.49
AP | 220 | 10/09/24 | 159 | California Hydronics Corp |  | 10718 | SIN194277
GL | 220 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 38.29
AP | 220 | 10/22/24 | 556 | Rosen Supply Kirkland |  | 7476.78 | 26682.01
AP | 220 | 10/22/24 | 571 | Consolidated Supply Co. |  | 10068.47 | S012097248.001
GL | 220 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 367.83
GL | 220 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 9817.59
GL | 220 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 106.24
AP | 220 | 11/12/24 | 284 | Pacific Plumbing Supply Co., LLC |  | 134.87 | 51700585
GL | 220 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 46.09
AP | 220 | 11/26/24 | 622 | Pacific Plumbing Supply Co., LLC |  | 11931.74 | 51716064
GL | 220 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 122.76
AP | 220 | 11/30/24 | 737 | Capital One Credit Card |  | 59.3 | 102124J
GL | 220 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 25.56
GL | 220 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 308.21
AP | 220 | 12/17/24 | 363 | Pacific Plumbing Supply Co., LLC |  | 360.23 | 51727165
GL | 220 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 25.56
AP | 220 | 01/01/25 | 2 | Consolidated Supply Co. |  | 1539.3 | S012189993.001
AP | 220 | 01/02/25 | 88 | Consolidated Supply Co. |  | 10376.85 | S012097312.001
GL | 220 | 01/02/25 | 126 | 2024-12-30 to 2025-01-03 |  | 32.39
AP | 220 | 01/15/25 | 329 | Pacific Plumbing Supply Co., LLC |  | 162.96 | 51749959
AP | 220 | 01/16/25 | 408 | Pacific Plumbing Supply Co., LLC |  | 82.28 | 51752962
GL | 220 | 01/20/25 | 425 | 2025-01-12 to 2025-01-18 |  | 84.22
AP | 220 | 01/24/25 | 636 | Pacific Plumbing Supply Co., LLC |  | 1046.15 | 51760569
AP | 220 | 01/28/25 | 646 | Consolidated Supply Co. |  | 6802.2 | S012044219.001
AP | 220 | 01/28/25 | 647 | Consolidated Supply Co. |  | 13069.4 | S012097366.001
AP | 220 | 01/28/25 | 661 | Pacific Plumbing Supply Co., LLC |  | 85.14 | 51765695
AP | 220 | 01/28/25 | 668 | Rosen Supply Kirkland |  | 467.02 | 29255.01
GL | 220 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 183.6
GL | 220 | 02/05/25 | 21 | 2025-01-26 to 2025-02-01 |  | 90.3
GL | 220 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 90.2
AP | 220 | 02/11/25 | 144 | Consolidated Supply Co. |  | 10376.85 | S012097525.001
AP | 220 | 02/11/25 | 146 | Consolidated Supply Co. |  | 15753.86 | S012101242.001
AP | 220 | 02/11/25 | 150 | Consolidated Supply Co. |  | 418.48 | S012285923.001
AP | 220 | 02/12/25 | 164 | Pacific Plumbing Supply Co., LLC |  | 517.02 | 51779349
AP | 220 | 02/14/25 | 275 | Consolidated Supply Co. |  | 11.6 | S012285923.002
GL | 220 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 458.78
AP | 220 | 02/18/25 | 303 | Consolidated Supply Co. |  | 338.58 | S012297620.001
GL | 220 | 02/21/25 | 394 | Req 625 |  | 6386.19
AP | 220 | 02/24/25 | 425 | Consolidated Supply Co. |  | 2007.62 | S012306163.001
AP | 220 | 02/24/25 | 438 | Pacific Plumbing Supply Co., LLC |  | 1097.67 | 51788558
AP | 220 | 02/24/25 | 439 | Pacific Plumbing Supply Co., LLC |  | 672.05 | 51788560
AP | 220 | 02/25/25 | 463 | Capital One Credit Card |  | 41.59 | 012225J2
GL | 220 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 107.8
AP | 220 | 02/26/25 | 486 | Consolidated Supply Co. |  | 6802.2 | S012044231.001
AP | 220 | 02/26/25 | 489 | Keller Supply Company |  | 13.25 | S023845364.001
AP | 220 | 02/27/25 | 571 | Pacific Plumbing Supply Co., LLC |  | 330.79 | 51791068
GL | 220 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 1210.52
AP | 220 | 03/06/25 | 86 | Consolidated Supply Co. |  | 15669.66 | S012101778.001
AP | 220 | 03/10/25 | 555 | Seton Identification Products |  | 118.23 | 9358510322
GL | 220 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 533.13
AP | 220 | 03/11/25 | 166 | Consolidated Supply Co. |  | 11906.22 | S012107284.001
AP | 220 | 03/11/25 | 167 | Consolidated Supply Co. |  | 667.53 | S012107284.002
AP | 220 | 03/11/25 | 168 | Consolidated Supply Co. |  | 11352.2 | S012107324.001
AP | 220 | 03/11/25 | 176 | Pacific Plumbing Supply Co., LLC |  | 12573.6 | 51798204
AP | 220 | 03/11/25 | 180 | Pacific Plumbing Supply Co., LLC |  | 12573.6 | 51798206
AP | 220 | 03/17/25 | 291 | Consolidated Supply Co. |  | 84.2 | S012101778.002
AP | 220 | 03/17/25 | 292 | Consolidated Supply Co. |  | 790.02 | S012297620.002
GL | 220 | 03/18/25 | 348 | 2025-03-09 to 2025-03-15 |  | 747.78
AP | 220 | 03/19/25 | 354 | Rosen Supply Kirkland |  | 4406.25 | 30363.01
AP | 220 | 03/19/25 | 360 | Consolidated Supply Co. |  | 785.53 | S012107324.002
AP | 220 | 03/19/25 | 368 | Capital One Credit Card |  | 48.74 | 022425J1
AP | 220 | 03/19/25 | 369 | Capital One Credit Card |  | 48.68 | 022525J
AP | 220 | 03/19/25 | 383 | Consolidated Supply Co. |  | 12508.01 | S012107391.001
AP | 220 | 03/21/25 | 510 | Rosen Supply Kirkland |  | 192.76 | 29255.03
GL | 220 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 739.58
AP | 220 | 03/25/25 | 545 | Consolidated Supply Co. |  | 243.24 | S012340522.001
AP | 220 | 03/25/25 | 547 | Consolidated Supply Co. |  | 52.08 | S012340522.002
GL | 220 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 1494.55
AP | 220 | 04/04/25 | 95 | Consolidated Supply Co. |  | 78.67 | S012347080.001
AP | 220 | 04/04/25 | 96 | Consolidated Supply Co. |  | 926.64 | S012347885.002
AP | 220 | 04/04/25 | 102 | Rosen Supply Kirkland |  | 323.22 | 30618.01
AP | 220 | 04/04/25 | 112 | Consolidated Supply Co. |  | -78.67 | S012347080.001A
AP | 220 | 04/04/25 | 113 | Consolidated Supply Co. |  | 788.67 | S012347080.001B
AP | 220 | 04/07/25 | 106 | Consolidated Supply Co. |  | 489.53 | S012354450.001
GL | 220 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 932.78
AP | 220 | 04/09/25 | 159 | Consolidated Supply Co. |  | 6802.2 | S012044243.001
AP | 220 | 04/09/25 | 160 | Consolidated Supply Co. |  | 6802.2 | S012044248.001
AP | 220 | 04/09/25 | 161 | Pacific Plumbing Supply Co., LLC |  | 592.72 | 51817655
AP | 220 | 04/11/25 | 270 | Rosen Supply Kirkland |  | 2902.11 | 30628.01
AP | 220 | 04/11/25 | 282 | Pacific Plumbing Supply Co., LLC |  | 407.09 | 51822755
AP | 220 | 04/11/25 | 289 | Consolidated Supply Co. |  | -223.8 | S012044248.002
AP | 220 | 04/11/25 | 290 | Consolidated Supply Co. |  | 12449.83 | S012107358.001
AP | 220 | 04/11/25 | 291 | Consolidated Supply Co. |  | 1141.08 | S012361756.001
AP | 220 | 04/11/25 | 300 | Consolidated Supply Co. |  | 315.19 | S012340522.003
GL | 220 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 1077.16
AP | 220 | 04/11/25 | 310 | Pacific Plumbing Supply Co., LLC |  | 613.02 | 51824883
AP | 220 | 04/11/25 | 311 | Pacific Plumbing Supply Co., LLC |  | 2819.27 | 51824886
AP | 220 | 04/15/25 | 325 | Consolidated Supply Co. |  | 13139.14 | S012114072.001
AP | 220 | 04/15/25 | 326 | Consolidated Supply Co. |  | 241.75 | S012369923.001
AP | 220 | 04/15/25 | 329 | Pacific Plumbing Supply Co., LLC |  | 498.56 | 51829514
AP | 220 | 04/16/25 | 381 | Capital One Credit Card |  | 55.23 | 040325
GL | 220 | 04/16/25 | 389 | Req 647 |  | 1593.78
AP | 220 | 04/16/25 | 405 | Pacific Plumbing Supply Co., LLC |  | 88.65 | 51832101
AP | 220 | 04/18/25 | 490 | Consolidated Supply Co. |  | 112.27 | S012107324.003
AP | 220 | 04/18/25 | 491 | Consolidated Supply Co. |  | 501.64 | S012107391.002
AP | 220 | 04/18/25 | 492 | Consolidated Supply Co. |  | 598.92 | S012114072.002
AP | 220 | 04/21/25 | 512 | Pacific Plumbing Supply Co., LLC |  | 1874.15 | 51835589
GL | 220 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 453.63
AP | 220 | 04/23/25 | 530 | Consolidated Supply Co. |  | 32.9 | S012369923.002
AP | 220 | 04/23/25 | 531 | Consolidated Supply Co. |  | 888.55 | S012380351.001
AP | 220 | 04/23/25 | 535 | Consolidated Supply Co. |  | 4636.2 | S012380714.001
AP | 220 | 04/28/25 | 632 | Consolidated Supply Co. |  | 6802.2 | S012044086.001
AP | 220 | 04/28/25 | 633 | Consolidated Supply Co. |  | 6802.2 | S012044203.001
AP | 220 | 04/28/25 | 657 | Rosen Supply Kirkland |  | 5054.8 | 31184.01
GL | 220 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 1273.61
AP | 220 | 05/01/25 | 70 | California Hydronics Corp |  | 16448 | SIN212555
AP | 220 | 05/01/25 | 75 | Pacific Plumbing Supply Co., LLC |  | -592.72 | 51817655A
AP | 220 | 05/01/25 | 76 | Pacific Plumbing Supply Co., LLC |  | 592.74 | 51817655B
AP | 220 | 05/02/25 | 86 | Consolidated Supply Co. |  | 323.74 | S012107324.004
AP | 220 | 05/02/25 | 87 | Consolidated Supply Co. |  | 4140.07 | S012114077.001
AP | 220 | 05/02/25 | 88 | Consolidated Supply Co. |  | 6005.92 | S012114100.001
AP | 220 | 05/02/25 | 89 | Consolidated Supply Co. |  | 652.05 | S012396318.001
AP | 220 | 05/02/25 | 91 | Consolidated Supply Co. |  | -734.5 | S012403661.002
AP | 220 | 05/02/25 | 94 | Consolidated Supply Co. |  | 451.2 | S012403436.001
AP | 220 | 05/02/25 | 100 | Pacific Plumbing Supply Co., LLC |  | 480.87 | 51844320
GL | 220 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 538.66
AP | 220 | 05/06/25 | 127 | Consolidated Supply Co. |  | 4742.39 | S012403661.001
AP | 220 | 05/06/25 | 128 | Consolidated Supply Co. |  | 232.54 | S012403661.003
AP | 220 | 05/06/25 | 132 | Pacific Plumbing Supply Co., LLC |  | 117.34 | 51847425
AP | 220 | 05/07/25 | 136 | Ferguson Enterprises, Inc. #3007 |  | 177.02 | 3647879
AP | 220 | 05/09/25 | 239 | Consolidated Supply Co. |  | 382.4 | S012407167.001
AP | 220 | 05/09/25 | 255 | Consolidated Supply Co. |  | 4020.06 | S012114053.002
AP | 220 | 05/09/25 | 256 | Consolidated Supply Co. |  | 280.67 | S012114077.002
AP | 220 | 05/09/25 | 257 | Consolidated Supply Co. |  | 226.62 | S012114100.002
AP | 220 | 05/09/25 | 258 | Consolidated Supply Co. |  | 133.15 | S012396318.002
AP | 220 | 05/09/25 | 259 | Consolidated Supply Co. |  | 779.52 | S012403661.004
GL | 220 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 690.03
AP | 220 | 05/13/25 | 281 | Consolidated Supply Co. |  | 1440.6 | S012414213.001
AP | 220 | 05/13/25 | 282 | Consolidated Supply Co. |  | -308.93 | S012403661.005
GL | 220 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 669.41
AP | 220 | 05/21/25 | 430 | Consolidated Supply Co. |  | 230.83 | S012422219.001
AP | 220 | 05/22/25 | 513 | Consolidated Supply Co. |  | 112.8 | S012422362.001
AP | 220 | 05/22/25 | 515 | Consolidated Supply Co. |  | 42.87 | S012425716.001
GL | 220 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 760.93
AP | 220 | 05/30/25 | 623 | Pacific Plumbing Supply Co., LLC |  | 177.34 | 51859146
AP | 220 | 05/30/25 | 640 | Ferguson Enterprises, Inc. #3007 |  | -175.74 | CM532264
AP | 220 | 05/30/25 | 647 | Consolidated Supply Co. |  | 13117.46 | S012114264.001
AP | 220 | 05/30/25 | 648 | Consolidated Supply Co. |  | 1002.59 | S012429042.001
AP | 220 | 05/30/25 | 649 | Consolidated Supply Co. |  | 902.4 | S012434480.001
AP | 220 | 05/31/25 | 663 | Consolidated Supply Co. |  | 380.36 | S012432948.001
AP | 220 | 05/31/25 | 664 | Consolidated Supply Co. |  | 68.43 | S012434480.002
GL | 220 | 05/31/25 | 681 | 2025-05-26 to 2025-05-30 |  | 806.65
AP | 220 | 06/05/25 | 80 | Rosen Supply Kirkland |  | 4308.36 | 31836.01
AP | 220 | 06/05/25 | 86 | Pacific Plumbing Supply Co., LLC |  | 436.35 | 51869438
AP | 220 | 06/05/25 | 87 | Pacific Plumbing Supply Co., LLC |  | 61.5 | 51869448
AP | 220 | 06/06/25 | 95 | Ferguson Enterprises, Inc. #3007 |  | 911 | 3729797
AP | 220 | 06/09/25 | 103 | Rosen Supply Kirkland |  | 572.67 | 31913.01
GL | 220 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 898.63
AP | 220 | 06/11/25 | 159 | Consolidated Supply Co. |  | 3821.67 | S012454739.001
AP | 220 | 06/11/25 | 171 | Consolidated Supply Co. |  | 2122.75 | S012457366.001
AP | 220 | 06/13/25 | 267 | Consolidated Supply Co. |  | 2981.05 | S012463326.001
AP | 220 | 06/13/25 | 268 | Consolidated Supply Co. |  | -2065.92 | S012463326.003
AP | 220 | 06/13/25 | 269 | Consolidated Supply Co. |  | 2857.2 | S012463326.002
AP | 220 | 06/13/25 | 270 | Consolidated Supply Co. |  | -265.67 | S012463326.004
AP | 220 | 06/13/25 | 271 | Consolidated Supply Co. |  | 265.67 | S012463326.005
AP | 220 | 06/16/25 | 276 | Rosen Supply Kirkland |  | 1761.2 | 32019.01
GL | 220 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 747.87
AP | 220 | 06/16/25 | 290 | Rosen Supply Kirkland |  | 363.85 | 32130.01
GL | 220 | 06/17/25 | 295 | Req 665 |  | 109.76
GL | 220 | 06/17/25 | 297 | Req 667 |  | -3198.08
GL | 220 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 707.41
AP | 220 | 06/24/25 | 396 | Consolidated Supply Co. |  | 728.42 | S012107391.003
AP | 220 | 06/24/25 | 397 | Consolidated Supply Co. |  | 620.6 | S012114264.002
AP | 220 | 06/24/25 | 398 | Consolidated Supply Co. |  | -74.55 | S012457366.002
AP | 220 | 06/24/25 | 399 | Consolidated Supply Co. |  | 561.34 | S012463326.006
AP | 220 | 06/24/25 | 412 | Pacific Plumbing Supply Co., LLC |  | 16.02 | 51884556
AP | 220 | 06/24/25 | 418 | Pacific Plumbing Supply Co., LLC |  | 173.05 | 51888214
AP | 220 | 06/25/25 | 459 | Consolidated Supply Co. |  | 3204.54 | S012472680.001
AP | 220 | 06/26/25 | 534 | Capital One Credit Card |  | 40.69 | 060525J1
AP | 220 | 06/27/25 | 546 | Consolidated Supply Co. |  | 647.48 | S012114077.003
AP | 220 | 06/27/25 | 547 | Consolidated Supply Co. |  | 437.5 | S012475193.001
AP | 220 | 06/27/25 | 552 | Ferguson Enterprises, Inc. #3007 |  | 214.18 | 3784806
AP | 220 | 06/27/25 | 561 | Consolidated Supply Co. |  | 457.9 | S012480675.001
AP | 220 | 06/27/25 | 562 | Rosen Supply Kirkland |  | 529.62 | 32338.01
GL | 220 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 1360.76
AP | 220 | 06/30/25 | 569 | Consolidated Supply Co. |  | 223.74 | S012429042.002
AP | 220 | 06/30/25 | 577 | Consolidated Supply Co. |  | 7547.47 | S012480683.001
AP | 220 | 06/30/25 | 580 | Consolidated Supply Co. |  | 39.21 | S012483154.001
GL | 220 | 06/30/25 | 590 | Req 670 |  | 130.55
GL | 220 | 06/30/25 | 594 | Req 674 |  | 1459.2
AP | 220 | 06/30/25 | 604 | California Hydronics Corp |  | -2782 | SCR012685
AP | 220 | 06/30/25 | 605 | California Hydronics Corp |  | -5147.4 | SCR012686
GL | 220 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 92.81
AP | 220 | 07/09/25 | 91 | Consolidated Supply Co. |  | 9057.15 | S012486299.001
AP | 220 | 07/09/25 | 106 | Rosen Supply Kirkland |  | 107.23 | 32534.01
AP | 220 | 07/09/25 | 127 | California Hydronics Corp |  | 3032 | SIN217658
GL | 220 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 556.51
AP | 220 | 07/14/25 | 250 | Consolidated Supply Co. |  | 233.5 | S012486299.002
AP | 220 | 07/14/25 | 251 | Consolidated Supply Co. |  | 2470.95 | S012502761.001
AP | 220 | 07/14/25 | 257 | Pacific Plumbing Supply Co., LLC |  | 55.58 | 51905033
AP | 220 | 07/16/25 | 275 | Ferguson Enterprises, Inc. #3007 |  | 123.49 | 3832405
AP | 220 | 07/16/25 | 277 | Rosen Supply Kirkland |  | 399.6 | 32667.01
AP | 220 | 07/16/25 | 279 | Rosen Supply Kirkland |  | 72.4 | 32668.01
GL | 220 | 07/21/25 | 375 | Req 687 |  | -20.35
GL | 220 | 07/21/25 | 376 | Req 688 |  | 96.5
GL | 220 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 445.14
AP | 220 | 07/22/25 | 436 | Consolidated Supply Co. |  | 262.38 | S012510681.001
AP | 220 | 07/22/25 | 437 | Consolidated Supply Co. |  | 37.42 | S012517618.001
GL | 220 | 07/24/25 | 530 | Mitchell Gerard |  | 53.21
AP | 220 | 07/28/25 | 553 | Consolidated Supply Co. |  | -2136.84 | S012520776.001
AP | 220 | 07/28/25 | 559 | Pacific Plumbing Supply Co., LLC |  | 176.24 | 51916274
AP | 220 | 07/28/25 | 573 | Rosen Supply Kirkland |  | 1056.43 | 32893.01
GL | 220 | 07/30/25 | 591 | Req 670-2 |  | 737.38
AP | 220 | 08/01/25 | 88 | Consolidated Supply Co. |  | 12.46 | S012536882.001
GL | 220 | 08/03/25 | 78 | 2025-07-20 to 07-26 |  | 432.94
GL | 220 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 308.29
AP | 220 | 08/07/25 | 191 | Consolidated Supply Co. |  | 536.7 | S012543356.001
GL | 220 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 30.16
AP | 220 | 08/13/25 | 255 | Rosen Supply Kirkland |  | 87.67 | 33254.01
GL | 220 | 08/21/25 | 417 | Mitchell Gerard |  | 31.53
AP | 220 | 08/26/25 | 509 | Pacific Plumbing Supply Co., LLC |  | 832 | 51939318
AP | 220 | 08/31/25 | 601 | Consolidated Supply Co. |  | 134.8 | S012569670.001
GL | 220 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 386.8
GL | 220 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 12.97
GL | 220 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 212.26
AP | 220 | 09/16/25 | 175 | Consolidated Supply Co. |  | 688.64 | S012570622.001
AP | 220 | 09/17/25 | 225 | Consolidated Supply Co. |  | 7.43 | S012583946.001
GL | 220 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 252.48
AP | 220 | 09/22/25 | 327 | Consolidated Supply Co. |  | 31.37 | S012528163.002
AP | 220 | 09/22/25 | 329 | Consolidated Supply Co. |  | 7163.64 | S12581175.001
AP | 220 | 09/23/25 | 357 | Consolidated Supply Co. |  | 688.64 | S012592746.001
AP | 220 | 09/24/25 | 377 | Consolidated Supply Co. |  | 14.31 | S012590264.001
AP | 220 | 09/24/25 | 386 | Rosen Supply Kirkland |  | 82.1 | 33670.01
GL | 220 | 09/30/25 | 504 | 2025-09-22 to 09-26 |  | 20.03
AP | 220 | 10/03/25 | 101 | Consolidated Supply Co. |  | 186.8 | S012581175.002
GL | 220 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 84.03
AP | 220 | 10/07/25 | 115 | Consolidated Supply Co. |  | 1055.03 | S012609036.001
AP | 220 | 10/07/25 | 116 | Consolidated Supply Co. |  | -124.43 | S012609036.003
AP | 220 | 10/07/25 | 133 | Pacific Plumbing Supply Co., LLC |  | 431.4 | 51965569
AP | 220 | 10/10/25 | 255 | Consolidated Supply Co. |  | 156.85 | S012614352.001
AP | 220 | 10/10/25 | 265 | Keller Supply Company |  | 2878.09 | S023333043.001
GL | 220 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 59.18
AP | 220 | 10/15/25 | 353 | Rosen Supply Kirkland |  | 92.51 | 34244.01
AP | 220 | 10/15/25 | 357 | Consolidated Supply Co. |  | 322.63 | S012633681.001
GL | 220 | 10/21/25 | 459 | 2025-10-12 to 10-18 |  | 115.51
AP | 220 | 10/23/25 | 564 | Consolidated Supply Co. |  | 4.47 | S012650208.001
AP | 220 | 10/24/25 | 623 | Capital One Credit Card |  | 84.42 | 091025J
AP | 220 | 10/24/25 | 629 | Capital One Credit Card |  | 69.76 | 092425J
GL | 220 | 10/28/25 | 633 | 2025-10-19 to 10-25 |  | 138.7
GL | 220 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | 213.32
AP | 220 | 11/07/25 | 132 | Rosen Supply Kirkland |  | 663.81 | 34685.01
GL | 220 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 1.79
AP | 220 | 11/21/25 | 421 | Pacific Plumbing Supply Co., LLC |  | 111 | 52019723
GL | 220 | 11/21/25 | 426 | Req 714 |  | -912.79
AP | 220 | 12/02/25 | 14 | Consolidated Supply Co. |  | 52.18 | S012703218.001
AP | 220 | 12/08/25 | 132 | Consolidated Supply Co. |  | 97.3 | S012709001.001
AP | 220 | 12/11/25 | 234 | Rosen Supply Kirkland |  | 99.03 | 35285.01
AP | 220 | 12/11/25 | 241 | Rosen Supply Kirkland |  | 25.29 | 35353.01
AP | 220 | 12/12/25 | 254 | Consolidated Supply Co. |  | 22.64 | S012716707.001
AP | 220 | 12/17/25 | 303 | Consolidated Supply Co. |  | 38.67 | S012709001.002
GL | 220 | 12/22/25 | 500 | 2025-12-14 to 12-20 |  | 14.84
AP | 220 | 01/01/26 | 87 | Consolidated Supply Co. |  | -97.3 | S012709001.001A
AP | 220 | 01/01/26 | 88 | Consolidated Supply Co. |  | 97.23 | S012709001.001B
AP | 220 | 01/14/26 | 262 | Pacific Plumbing Supply Co., LLC |  | 42.5 | 52058981
GL | 220 | 01/21/26 | 425 | 2026-01-11 to 01-17 |  | 54.97
GL | 220 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 13.81
AP | 220 | 02/02/26 | 23 | Rosen Supply Kirkland |  | 126.58 | 36070.01
AP | 220 | 02/02/26 | 25 | Rosen Supply Kirkland |  | -124.37 | 36105.01
AP | 220 | 02/02/26 | 26 | Rosen Supply Kirkland |  | 109.5 | 36105.02
GL | 220 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 17.63
AP | 220 | 02/17/26 | 276 | Rosen Supply Kirkland |  | 1029.95 | 36381.01
AP | 220 | 02/18/26 | 355 | Pacific Plumbing Supply Co., LLC |  | 110.34 | 52089987
AP | 220 | 02/27/26 | 539 | Rosen Supply Kirkland |  | 25.57 | 36381.03
GL | 220 | 02/28/26 | 549 | 2026-02-22 to 02-28 |  | 209.35
AP | 220 | 03/06/26 | 107 | Consolidated Supply Co. |  | 151.59 | S012827607.001
AP | 220 | 03/09/26 | 130 | Rosen Supply Kirkland |  | 209.5 | 36614.01
AP | 220 | 03/09/26 | 134 | Rosen Supply Kirkland |  | 414.51 | 36590.01
GL | 220 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 22.14
AP | 220 | 03/18/26 | 296 | Rosen Supply Kirkland |  | 7.89 | 36658.01
AP | 220 | 03/20/26 | 388 | Consolidated Supply Co. |  | 7.42 | S012827607.002
GL | 220 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | 72.19
GL | 220 | 03/30/26 | 583 | 2026-03-23 to 03-27 |  | 19.77
AP | 230 | 03/27/24 | 1161 | Pacific Plumbing Supply Co., LLC |  | 1648.57 | 51521875
AP | 230 | 06/30/24 | 826 | Bank of America CC |  | 57.36 | 051724J
AP | 230 | 07/15/24 | 300 | Old Castle Infrastructure, Inc. |  | 15437.21 | 10272778
AP | 230 | 07/25/24 | 343 | Consolidated Supply Co. |  | 1979.04 | S011985761.001
GL | 230 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 343.24
GL | 230 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 497.83
AP | 230 | 08/21/24 | 658 | Keller Supply Company |  | 709.4 | S023284699.001
AP | 230 | 08/21/24 | 659 | Keller Supply Company |  | 3804.88 | S023212384.001
GL | 230 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 889.95
GL | 230 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 124
AP | 230 | 09/17/24 | 360 | Pacific Plumbing Supply Co., LLC |  | 488.74 | 51662049
AP | 230 | 09/18/24 | 363 | Ferguson Enterprises, Inc. #3007 |  | 74.18 | 2973584
GL | 230 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 224.25
AP | 230 | 09/30/24 | 696 | Ferguson Enterprises, Inc. #3007 |  | -20.33 | CM434468
AP | 230 | 10/09/24 | 178 | Ferguson Enterprises, Inc. #3007 |  | 86.27 | 2973584-1
AP | 230 | 10/14/24 | 325 | Rosen Supply Kirkland |  | 2242.5 | 26462.01
GL | 230 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 385.64
GL | 230 | 10/22/24 | 569 | 2024-10-13 to 2024-10-19 |  | 372
AP | 230 | 11/05/24 | 116 | Consolidated Supply Co. |  | 2677.68 | S012151493.001
AP | 230 | 11/11/24 | 233 | Keller Supply Company |  | 1283.61 | S023325523.001
AP | 230 | 11/15/24 | 434 | Consolidated Supply Co. |  | 13980.58 | S012151493.002
AP | 230 | 11/15/24 | 454 | Keller Supply Company |  | 365.69 | S023497078.001
GL | 230 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 355.38
AP | 230 | 11/25/24 | 617 | Pacific Plumbing Supply Co., LLC |  | 8715.84 | 51719030
GL | 230 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 177.69
GL | 230 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 296.15
AP | 230 | 01/02/25 | 142 | Keller Supply Company |  | 236.38 | S023306993.001
AP | 230 | 01/08/25 | 157 | Pacific Plumbing Supply Co., LLC |  | 1303.09 | 51739226
AP | 230 | 01/15/25 | 330 | Pacific Plumbing Supply Co., LLC |  | 3474.91 | 51749960
AP | 230 | 01/15/25 | 331 | Pacific Plumbing Supply Co., LLC |  | 2527.36 | 51751625
AP | 230 | 01/21/25 | 461 | Keller Supply Company |  | 2326.69 | S023733241.001
AP | 230 | 01/24/25 | 622 | Pacific Plumbing Supply Co., LLC |  | 43.54 | 51756719
AP | 230 | 01/28/25 | 652 | Keller Supply Company |  | 1371.74 | S023105883.001
GL | 230 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 234.52
AP | 230 | 02/05/25 | 14 | Keller Supply Company |  | 953.14 | S023781239.001
AP | 230 | 02/07/25 | 104 | Keller Supply Company |  | 12476.83 | S023315542.001
AP | 230 | 02/07/25 | 108 | Submeter Solutions, Inc. |  | 7032.28 | IN86401
GL | 230 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 16.77
AP | 230 | 02/13/25 | 607 | Keller Supply Company |  | 3317.87 | S023855006.001
AP | 230 | 02/13/25 | 608 | Keller Supply Company |  | 1141.07 | S023781239.002
AP | 230 | 02/13/25 | 612 | Pacific Plumbing Supply Co., LLC |  | 27.06 | 51793713
GL | 230 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 593.04
AP | 230 | 02/20/25 | 389 | Trane US, Inc |  | 14845.92 | 315201696
AP | 230 | 02/24/25 | 419 | Pacific Plumbing Supply Co., LLC |  | 410.65 | 51786222
GL | 230 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 2089.28
AP | 230 | 02/28/25 | 584 | Consolidated Supply Co. |  | 2007.62 | S012305272.001
AP | 230 | 02/28/25 | 585 | Consolidated Supply Co. |  | -2007.62 | S012305272.002
GL | 230 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 72.19
AP | 230 | 03/07/25 | 103 | Trane US, Inc |  | 5285.8 | 315233063
AP | 230 | 03/07/25 | 104 | Trane US, Inc |  | 2068.03 | 315232206
GL | 230 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 13.81
AP | 230 | 03/12/25 | 191 | Trane US, Inc |  | 179583.36 | 315243668
AP | 230 | 03/17/25 | 288 | Keller Supply Company |  | 614.72 | S023371022.001
GL | 230 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 1336.74
GL | 230 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 2102.37
GL | 230 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 277.56
GL | 230 | 04/09/25 | 155 | Cole Industrial, Inc. |  | 17845
AP | 230 | 04/11/25 | 306 | Keller Supply Company |  | 2465.52 | S023205555.001
GL | 230 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 680.49
AP | 230 | 04/14/25 | 288 | Trane US, Inc |  | 80449.45 | 315309971
AP | 230 | 04/16/25 | 396 | Keller Supply Company |  | 2465.52 | S023205547.001
AP | 230 | 04/21/25 | 503 | Keller Supply Company |  | 2360.64 | S023295650.001
AP | 230 | 04/21/25 | 511 | Pacific Plumbing Supply Co., LLC |  | 265.2 | 51833088
GL | 230 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 673.77
AP | 230 | 04/23/25 | 533 | Consolidated Supply Co. |  | 18.47 | S012380635.001
AP | 230 | 04/28/25 | 643 | Keller Supply Company |  | 2739.47 | S023205512.001
GL | 230 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 1146.19
AP | 230 | 05/02/25 | 81 | Consolidated Supply Co. |  | 859.87 | S012377818.001
GL | 230 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 513.33
AP | 230 | 05/07/25 | 137 | Keller Supply Company |  | 2224.09 | S023310040.001
GL | 230 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 602.76
GL | 230 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 158.12
AP | 230 | 05/22/25 | 516 | Consolidated Supply Co. |  | 19062.54 | S012405640.002
AP | 230 | 05/27/25 | 345 | Consolidated Supply Co. |  | 917.7 | S012405640.001
AP | 230 | 05/30/25 | 620 | Keller Supply Company |  | 930.67 | S023733241.002
AP | 230 | 05/30/25 | 625 | Pacific Plumbing Supply Co., LLC |  | 2365 | 51859535
AP | 230 | 05/30/25 | 650 | Consolidated Supply Co. |  | 2125 | S012405640.003
GL | 230 | 05/31/25 | 681 | 2025-05-26 to 2025-05-30 |  | 253.03
AP | 230 | 06/03/25 | 12 | California Hydronics Corp |  | 66411 | SIN214581
AP | 230 | 06/06/25 | 92 | Keller Supply Company |  | 3561.32 | S023205424.001
AP | 230 | 06/06/25 | 93 | Keller Supply Company |  | 3561.32 | S023205440.001
AP | 230 | 06/06/25 | 94 | Keller Supply Company |  | 3688.3 | S023371022.002
GL | 230 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 561.68
AP | 230 | 06/11/25 | 160 | Consolidated Supply Co. |  | 1254.1 | S012393912.001
AP | 230 | 06/13/25 | 252 | Keller Supply Company |  | 3561.32 | S023205454.001
AP | 230 | 06/13/25 | 253 | Keller Supply Company |  | 3561.32 | S023205454.002
AP | 230 | 06/13/25 | 254 | Keller Supply Company |  | 3688.3 | S023371022.003
AP | 230 | 06/13/25 | 255 | Pacific Plumbing Supply Co., LLC |  | 5223.6 | 51880149
AP | 230 | 06/13/25 | 273 | Pacific Plumbing Supply Co., LLC |  | 322.5 | 51881707
GL | 230 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 850.69
AP | 230 | 06/18/25 | 307 | Rosen Supply Kirkland |  | 78.86 | 32109.01
AP | 230 | 06/20/25 | 383 | Consolidated Supply Co. |  | 236.59 | S012460700.001
GL | 230 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 181.53
AP | 230 | 06/27/25 | 548 | Consolidated Supply Co. |  | 175.79 | S012479155.001
AP | 230 | 06/27/25 | 549 | Consolidated Supply Co. |  | 58.6 | S012479155.002
AP | 230 | 06/30/25 | 583 | Trane US, Inc |  | 7539.44 | 315481282
AP | 230 | 06/30/25 | 608 | Rosen Supply Kirkland |  | 7280 | 31881.02
GL | 230 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 343.04
GL | 230 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 981.38
GL | 230 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 1314.14
AP | 230 | 07/22/25 | 443 | Keller Supply Company |  | 4931.04 | S023205368.001
AP | 230 | 07/23/25 | 459 | Keller Supply Company |  | 8492.36 | S023205414.001
AP | 230 | 07/25/25 | 244 | Rosen Supply Kirkland |  | 1571.27 | 31100.01
AP | 230 | 07/25/25 | 245 | Rosen Supply Kirkland |  | 7340.72 | 31600.02
AP | 230 | 07/25/25 | 285 | Keller Supply Company |  | 614.72 | S023371022.004
AP | 230 | 07/28/25 | 558 | Keller Supply Company |  | 15367.9 | S023371022.005
AP | 230 | 07/28/25 | 567 | California Hydronics Corp |  | 3520 | SIN219148
AP | 230 | 08/01/25 | 87 | Consolidated Supply Co. |  | 358.83 | S012528163.001
AP | 230 | 08/01/25 | 96 | Keller Supply Company |  | 1490.22 | S023713408.001
GL | 230 | 08/03/25 | 78 | 2025-07-20 to 07-26 |  | 36.32
GL | 230 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 129.79
AP | 230 | 08/06/25 | 119 | Keller Supply Company |  | 4109.2 | S023205424.002
GL | 230 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 43.5
AP | 230 | 08/15/25 | 324 | Keller Supply Company |  | 4383.15 | S023205424.003
AP | 230 | 08/19/25 | 337 | Keller Supply Company |  | 131.4 | S023306873.001
AP | 230 | 08/19/25 | 338 | Keller Supply Company |  | 1522.72 | S024188106.001
AP | 230 | 08/19/25 | 339 | Keller Supply Company |  | 441.03 | S024430279.001
AP | 230 | 08/25/25 | 446 | Pioneer Energy Management |  | 53820 | IN95706
AP | 230 | 08/25/25 | 452 | Keller Supply Company |  | 8492.36 | S023205440.002
GL | 230 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 704.52
GL | 230 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 1110.25
GL | 230 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 977.12
GL | 230 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 368.63
AP | 230 | 09/16/25 | 185 | Best Bath Systems |  | 2146.94 | 80254
AP | 230 | 09/16/25 | 197 | Trane US, Inc |  | 3400 | 990267725
AP | 230 | 09/16/25 | 208 | California Hydronics Corp |  | 669 | SIN222439
AP | 230 | 09/16/25 | 209 | California Hydronics Corp |  | 342 | SIN22662
AP | 230 | 09/16/25 | 210 | California Hydronics Corp |  | 99 | SIN222997
AP | 230 | 09/16/25 | 221 | Keller Supply Company |  | 4931.05 | S023205454.003
GL | 230 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 118.17
AP | 230 | 09/22/25 | 322 | Rosen Supply Kirkland |  | 472 | 33637.01
AP | 230 | 09/23/25 | 366 | Keller Supply Company |  | 1157.52 | S023307062.001
AP | 230 | 09/23/25 | 367 | Keller Supply Company |  | 5752.89 | S023490259.002
AP | 230 | 09/23/25 | 368 | Keller Supply Company |  | 1131.02 | S023306997.001
AP | 230 | 09/24/25 | 369 | Pacific Plumbing Supply Co., LLC |  | 312.24 | 51956001
AP | 230 | 09/24/25 | 370 | Pacific Plumbing Supply Co., LLC |  | 376.86 | 51958533
AP | 230 | 09/24/25 | 399 | Rosen Supply Kirkland |  | 1620.97 | 31024.01
AP | 230 | 09/24/25 | 400 | Rosen Supply Kirkland |  | 1620.97 | 31025.02
AP | 230 | 09/24/25 | 404 | Keller Supply Company |  | 6574.73 | S023490259.001
AP | 230 | 10/03/25 | 106 | Keller Supply Company |  | 517.16 | S024499537.001
GL | 230 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 1025.03
AP | 230 | 10/07/25 | 125 | Keller Supply Company |  | 407.63 | S024522869.001
AP | 230 | 10/07/25 | 129 | Keller Supply Company |  | 6104.54 | S023307580.001
AP | 230 | 10/07/25 | 130 | Keller Supply Company |  | -273.95 | S024596508.001
AP | 230 | 10/07/25 | 131 | Keller Supply Company |  | 1369.42 | S023308038.001
AP | 230 | 10/10/25 | 266 | Keller Supply Company |  | 2902.36 | S023333060.001
GL | 230 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 3118.2
AP | 230 | 10/14/25 | 307 | Rosen Supply Kirkland |  | 311.11 | 34052.01
AP | 230 | 10/14/25 | 308 | Rosen Supply Kirkland |  | 751.77 | 34064.01
AP | 230 | 10/14/25 | 314 | Rosen Supply Kirkland |  | 2701.64 | 31028.01
AP | 230 | 10/14/25 | 320 | Consolidated Supply Co. |  | 2048.57 | S012616680.001
AP | 230 | 10/14/25 | 336 | Keller Supply Company |  | 15821.68 | S02333141.001
AP | 230 | 10/14/25 | 341 | Pacific Plumbing Supply Co., LLC |  | 690.2 | 51981900
AP | 230 | 10/16/25 | 427 | Rosen Supply Kirkland |  | 9545.78 | 31029.01
AP | 230 | 10/16/25 | 428 | Rosen Supply Kirkland |  | 5366.89 | 34323.01
AP | 230 | 10/17/25 | 456 | Keller Supply Company |  | 273.95 | S024596508.002
GL | 230 | 10/21/25 | 459 | 2025-10-12 to 10-18 |  | 976.52
AP | 230 | 10/22/25 | 474 | Keller Supply Company |  | 6131.04 | S023307593.001
AP | 230 | 10/22/25 | 475 | Keller Supply Company |  | 543.37 | S023333141.002
AP | 230 | 10/22/25 | 476 | Keller Supply Company |  | 66.27 | S023333060.002
AP | 230 | 10/22/25 | 480 | Rosen Supply Kirkland |  | 22.77 | 34398.01
AP | 230 | 10/22/25 | 483 | Rosen Supply Kirkland |  | 268.07 | 34323.03
AP | 230 | 10/22/25 | 484 | Rosen Supply Kirkland |  | 1091.32 | 34373.01
AP | 230 | 10/23/25 | 558 | Keller Supply Company |  | 531.33 | S024674405.001
GL | 230 | 10/28/25 | 633 | 2025-10-19 to 10-25 |  | 187.97
AP | 230 | 10/29/25 | 640 | Rosen Supply Kirkland |  | 777.78 | 34473.01
AP | 230 | 10/29/25 | 641 | Rosen Supply Kirkland |  | -152.76 | 34481.01
AP | 230 | 10/29/25 | 642 | Rosen Supply Kirkland |  | -32.64 | 34483.01
AP | 230 | 10/29/25 | 648 | Rosen Supply Kirkland |  | 261 | 34555.01
GL | 230 | 10/30/25 | 740 | Req 711 |  | -54.46
AP | 230 | 10/31/25 | 763 | Mechanical Sales, Inc. |  | 229.7 | INV-0815879
GL | 230 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | 9.82
AP | 230 | 11/01/25 | 9 | Pacific Plumbing Supply Co., LLC |  | -690.2 | 51981900A
AP | 230 | 11/01/25 | 10 | Pacific Plumbing Supply Co., LLC |  | 699.2 | 51981900B
AP | 230 | 11/01/25 | 158 | Rosen Supply Kirkland |  | 135.89 | 34703.01
AP | 230 | 11/01/25 | 162 | Rosen Supply Kirkland |  | 2161.3 | 31023.01
AP | 230 | 11/01/25 | 165 | Keller Supply Company |  | 2130.6 | S023306993.002
AP | 230 | 11/01/25 | 166 | Keller Supply Company |  | 316.28 | S024722146.002
AP | 230 | 11/01/25 | 167 | Keller Supply Company |  | 3894.44 | S023307385.001
AP | 230 | 11/01/25 | 168 | Keller Supply Company |  | 6474.94 | S023333087.001
AP | 230 | 11/05/25 | 21 | Keller Supply Company |  | 16203.52 | S023333155.001
AP | 230 | 11/05/25 | 24 | Rosen Supply Kirkland |  | 666.75 | 34064.03
AP | 230 | 11/10/25 | 184 | Rosen Supply Kirkland |  | 31.98 | 34871.01
AP | 230 | 11/12/25 | 202 | Rosen Supply Kirkland |  | 3782.3 | 31026.01
AP | 230 | 11/14/25 | 288 | Consolidated Supply Co. |  | 1786.4 | S012664687.001
GL | 230 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 118.48
AP | 230 | 11/17/25 | 303 | Rosen Supply Kirkland |  | 18.53 | 34703.03
AP | 230 | 11/17/25 | 307 | Rosen Supply Kirkland |  | 109.16 | 34982.01
GL | 230 | 11/24/25 | 475 | 2025-11-16 to 11-22 |  | 16.77
AP | 230 | 11/25/25 | 502 | Rosen Supply Kirkland |  | 116.04 | 35019.02
AP | 230 | 11/25/25 | 504 | Rosen Supply Kirkland |  | 6664.03 | 31027.01
AP | 230 | 11/25/25 | 505 | Rosen Supply Kirkland |  | 136.36 | 34323.04
AP | 230 | 11/25/25 | 506 | Rosen Supply Kirkland |  | 486.04 | 34373.02
GL | 230 | 11/30/25 | 586 | 2025-11-23 to 11-29 |  | 337.53
AP | 230 | 12/02/25 | 29 | Keller Supply Company |  | 6184.04 | S023307607.001
AP | 230 | 12/05/25 | 123 | Keller Supply Company |  | 10831.01 | S023333125.001
AP | 230 | 12/08/25 | 138 | Pacific Plumbing Supply Co., LLC |  | 81.6 | 52029895
GL | 230 | 12/15/25 | 260 | 2025-12-07 to 12/13 |  | 157.02
AP | 230 | 12/15/25 | 262 | Keller Supply Company |  | 5787.6 | S023307618.001
AP | 230 | 12/15/25 | 270 | Keller Supply Company |  | 16122.05 | S023333170.001
AP | 230 | 12/15/25 | 271 | Pacific Plumbing Supply Co., LLC |  | 598.32 | 52035898
AP | 230 | 12/15/25 | 272 | Pacific Plumbing Supply Co., LLC |  | 220.54 | 52035902
AP | 230 | 12/15/25 | 291 | Rosen Supply Kirkland |  | 6844.15 | 31028.02
AP | 230 | 12/22/25 | 461 | Capital One Credit Card |  | 41.81 | 111125J
AP | 230 | 12/29/25 | 599 | Keller Supply Company |  | 1368.1 | S023306873.002
AP | 230 | 12/29/25 | 600 | Keller Supply Company |  | 316.94 | S023307618.002
AP | 230 | 01/06/26 | 82 | Rosen Supply Kirkland |  | 22.5 | 35019.03
AP | 230 | 01/09/26 | 216 | Keller Supply Company |  | 15520.25 | S023333190.001
AP | 230 | 01/09/26 | 217 | Keller Supply Company |  | 209.88 | S024599583.001
GL | 230 | 01/12/26 | 238 | 2026-01-04 to 01-10 |  | 37.92
AP | 230 | 01/12/26 | 242 | Consolidated Supply Co. |  | 2115.92 | S012261862.001
AP | 230 | 01/12/26 | 243 | Pacific Plumbing Supply Co., LLC |  | 1352.08 | 52057993
AP | 230 | 01/12/26 | 351 | Rosen Supply Kirkland |  | 3981.45 | 34163.01
AP | 230 | 01/21/26 | 422 | Capital One Credit Card |  | 47.83 | 010826J
GL | 230 | 01/21/26 | 425 | 2026-01-11 to 01-17 |  | 31.14
GL | 230 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 92.32
AP | 230 | 01/31/26 | 231 | Rosen Supply Kirkland |  | 9545.78 | 31030.01
AP | 230 | 01/31/26 | 232 | Rosen Supply Kirkland |  | 9545.78 | 31031.01
AP | 230 | 01/31/26 | 233 | Keller Supply Company |  | 2996.03 | S023333003.001
AP | 230 | 01/31/26 | 234 | Keller Supply Company |  | 11224.09 | S024188106.002
AP | 230 | 02/01/26 | 262 | Keller Supply Company |  | 524.89 | S023333190.002
AP | 230 | 02/01/26 | 263 | Keller Supply Company |  | 999.55 | S023333003.002
AP | 230 | 02/01/26 | 264 | Keller Supply Company |  | 532.9 | S024960308.001
AP | 230 | 02/02/26 | 14 | Rosen Supply Kirkland |  | 227.6 | 36000.02
AP | 230 | 02/02/26 | 28 | Rosen Supply Kirkland |  | 27.35 | 36150.01
AP | 230 | 02/02/26 | 119 | Keller Supply Company |  | 57.19 | S024991661.001
AP | 230 | 02/03/26 | 42 | Rosen Supply Kirkland |  | 11944.35 | 34163.02
AP | 230 | 02/09/26 | 134 | Rosen Supply Kirkland |  | 77.78 | 36204.01
GL | 230 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 119.83
AP | 230 | 02/17/26 | 288 | Consolidated Supply Co. |  | -848 | S025028172.001
GL | 230 | 02/23/26 | 414 | 2026-02-15 to 02-21 |  | 121.23
AP | 230 | 02/24/26 | 420 | Keller Supply Company |  | 301.3 | S025023068.001
AP | 230 | 02/24/26 | 421 | Keller Supply Company |  | 4299.35 | S024534204.001
AP | 230 | 02/24/26 | 422 | Keller Supply Company |  | 37.84 | S025045979.001
AP | 230 | 02/24/26 | 423 | Keller Supply Company |  | 26231.22 | S023216616.001
AP | 230 | 02/26/26 | 511 | Rosen Supply Kirkland |  | 131.33 | 36196.01
AP | 230 | 02/26/26 | 524 | Rosen Supply Kirkland |  | -114.1 | 36196.02
AP | 230 | 02/26/26 | 525 | Rosen Supply Kirkland |  | 63 | 36196.03
GL | 230 | 02/28/26 | 549 | 2026-02-22 to 02-28 |  | 465.18
AP | 230 | 03/01/26 | 3 | Consolidated Supply Co. |  | 848 | S025028172.001A
AP | 230 | 03/01/26 | 4 | Keller Supply Company |  | -848 | S025028172.001
AP | 230 | 03/05/26 | 98 | Keller Supply Company |  | 70.51 | S025041007.001
AP | 230 | 03/05/26 | 99 | Keller Supply Company |  | 1161.2 | S024960308.002
AP | 230 | 03/09/26 | 136 | Rosen Supply Kirkland |  | 173.32 | 36680.01
GL | 230 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 258.65
AP | 230 | 03/13/26 | 259 | Keller Supply Company |  | 547.36 | S025052437.001
GL | 230 | 03/16/26 | 278 | 2026-03-09 to 03-13 |  | 58.35
AP | 230 | 03/19/26 | 370 | Rosen Supply Kirkland |  | -7.89 | 36658.02
AP | 230 | 03/19/26 | 371 | Rosen Supply Kirkland |  | 5.8 | 36658.03
AP | 230 | 03/20/26 | 387 | Consolidated Supply Co. |  | 92.73 | S012261862.002
AP | 230 | 03/23/26 | 403 | Keller Supply Company |  | 57.19 | S025023068.003
GL | 230 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | 30.44
GL | 230 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | -59.52
AP | 230 | 03/24/26 | 418 | Consolidated Supply Co. |  | -92.73 | S012261862.003
AP | 230 | 03/26/26 | 535 | Capital One Credit Card |  | 16.45 | 022326J
AP | 230 | 03/26/26 | 548 | Capital One Credit Card |  | 37.45 | 030326J1
GL | 230 | 03/30/26 | 583 | 2026-03-23 to 03-27 |  | 14.46
AP | 240 | 04/11/25 | 296 | Pacific Plumbing Supply Co., LLC |  | 2939.21 | 51822751
AP | 240 | 04/11/25 | 297 | Pacific Plumbing Supply Co., LLC |  | 899.44 | 51822754
GL | 240 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 462.13
AP | 240 | 04/15/25 | 330 | Pacific Plumbing Supply Co., LLC |  | 2863.64 | 51830540
AP | 240 | 04/15/25 | 331 | Pacific Plumbing Supply Co., LLC |  | 181.04 | 51830541
AP | 240 | 04/15/25 | 333 | Pacific Plumbing Supply Co., LLC |  | 716.26 | 51830577
GL | 240 | 04/16/25 | 393 | Req 651 |  | 149.54
AP | 240 | 04/22/25 | 522 | Consolidated Supply Co. |  | 66.11 | S012382760.001
GL | 240 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 42.2
AP | 240 | 04/28/25 | 635 | Consolidated Supply Co. |  | 743.84 | S012394944.001
AP | 240 | 04/28/25 | 651 | Pacific Plumbing Supply Co., LLC |  | 690.49 | 51839404
GL | 240 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 91.71
AP | 240 | 05/27/25 | 333 | Pacific Plumbing Supply Co., LLC |  | 851.05 | 51855881
AP | 240 | 05/30/25 | 624 | Pacific Plumbing Supply Co., LLC |  | 67.92 | 51859534
GL | 240 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 83.57
AP | 240 | 08/01/25 | 98 | Pacific Plumbing Supply Co., LLC |  | 1139.18 | 51923903
GL | 240 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 117.9
GL | 240 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 7.89
AP | 240 | 08/19/25 | 340 | Pacific Plumbing Supply Co., LLC |  | 81.85 | 51934688
AP | 240 | 08/20/25 | 358 | Pacific Plumbing Supply Co., LLC |  | 141.36 | 51937961
GL | 240 | 09/30/25 | 504 | 2025-09-22 to 09-26 |  | 4.12
AP | 240 | 10/07/25 | 117 | Consolidated Supply Co. |  | 33.63 | S012609036.004
AP | 240 | 10/07/25 | 141 | Rosen Supply Kirkland |  | 38.28 | 33964.01
AP | 240 | 10/21/25 | 468 | Consolidated Supply Co. |  | 51.77 | S012641098.001
GL | 240 | 11/30/25 | 586 | 2025-11-23 to 11-29 |  | 8.89
GL | 240 | 12/04/25 | 103 | Mitchell Gerard |  | 23.35
GL | 240 | 12/04/25 | 103 | Mitchell Gerard |  | 77.71
GL | 240 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 75.21
GL | 240 | 01/29/26 | 634 | Mitchell Gerard |  | 36.45
GL | 240 | 03/16/26 | 278 | 2026-03-09 to 03-13 |  | 547.67
AP | 240 | 03/25/26 | 466 | Consolidated Supply Co. |  | 59.19 | S012856371.001
GL | 240 | 03/30/26 | 583 | 2026-03-23 to 03-27 |  | 113.8
GL | 240 | 04/02/26 | 67 | Mitchell Gerard |  | 80.91
AP | 240 | 04/02/26 | 69 | Kele, Inc $ MI Controls |  | 536 | INV4113476
GL | 241 | 08/06/24 | 172 | Transfer 2024-07-28 to 2024-08-03 |  | 303.6
GL | 241 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 42.97
GL | 241 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 1123.9
GL | 241 | 09/30/24 | 658 | 2024-09-22 to 2024-09-28 |  | 156
AP | 241 | 10/08/24 | 131 | Consolidated Supply Co. |  | 318.84 | S012113888.001
GL | 241 | 10/18/24 | 115 | 2024-09-29 to 2024-10-05 |  | 319.5
AP | 241 | 10/21/24 | 523 | Pac West Sales |  | 975.2 | 244527
GL | 241 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 5.72
GL | 241 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 46.62
AP | 241 | 02/14/25 | 274 | Consolidated Supply Co. |  | 24385.49 | S012157092.001
GL | 241 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 13.99
AP | 241 | 03/06/25 | 84 | Consolidated Supply Co. |  | 11510.8 | S012157306.001
AP | 241 | 03/06/25 | 87 | Consolidated Supply Co. |  | 694.98 | S012310810.001
AP | 241 | 03/17/25 | 290 | MacArthur Co. NW 6276 |  | 1932.9 | 252108330
GL | 241 | 03/18/25 | 348 | 2025-03-09 to 2025-03-15 |  | 572.79
AP | 241 | 03/19/25 | 384 | Consolidated Supply Co. |  | 904.42 | S012334645.001
AP | 241 | 03/19/25 | 385 | Consolidated Supply Co. |  | 751.05 | S012334645.002
GL | 241 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 1140.77
GL | 241 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 1140.33
AP | 241 | 04/04/25 | 94 | Consolidated Supply Co. |  | 2406.72 | S012340438.001
AP | 241 | 04/07/25 | 105 | Consolidated Supply Co. |  | 748.77 | S012354154.002
GL | 241 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 5.23
AP | 241 | 04/11/25 | 277 | Rosen Supply Kirkland |  | 298.44 | 30736.01
AP | 241 | 04/11/25 | 298 | Rosen Supply Kirkland |  | 520.51 | 30688.01
AP | 241 | 04/11/25 | 301 | Consolidated Supply Co. |  | 212.16 | S012354154.003
GL | 241 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 108.95
AP | 241 | 04/15/25 | 323 | MacArthur Co. NW 6276 |  | 1317.68 | 252128252
AP | 241 | 04/15/25 | 327 | Consolidated Supply Co. |  | 752 | S012369934.001
AP | 241 | 04/15/25 | 335 | Rosen Supply Kirkland |  | 155.71 | 30688.03
AP | 241 | 04/18/25 | 489 | MacArthur Co. NW 6276 |  | 1108.8 | 252132087
GL | 241 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 320.5
AP | 241 | 04/23/25 | 529 | Consolidated Supply Co. |  | 319.02 | S012340438.002
AP | 241 | 04/28/25 | 631 | Consolidated Supply Co. |  | 2069.36 | S012388163.001
AP | 241 | 04/28/25 | 634 | Consolidated Supply Co. |  | 19.27 | S012389705.001
GL | 241 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 88.13
AP | 241 | 05/02/25 | 90 | Consolidated Supply Co. |  | 73.31 | S012398980.001
GL | 241 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 76.08
AP | 241 | 05/06/25 | 129 | Consolidated Supply Co. |  | 346.92 | S012405674.001
AP | 241 | 05/07/25 | 146 | Consolidated Supply Co. |  | 411.64 | S012354154.004
AP | 241 | 05/08/25 | 215 | MacArthur Co. NW 6276 |  | 798.3 | 252147782
AP | 241 | 05/12/25 | 260 | MacArthur Co. NW 6276 |  | 25502.87 | 252149759
GL | 241 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 174
AP | 241 | 05/27/25 | 332 | MacArthur Co. NW 6276 |  | 371.28 | 252151765
GL | 241 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 11.93
AP | 241 | 05/31/25 | 671 | MacArthur Co. NW 6276 |  | 136.6 | 252158093
AP | 241 | 05/31/25 | 672 | MacArthur Co. NW 6276 |  | 904.4 | 252158092
AP | 241 | 05/31/25 | 673 | MacArthur Co. NW 6276 |  | 979.8 | 252160772
AP | 241 | 06/16/25 | 274 | Consolidated Supply Co. |  | 1480.92 | S012463376.001
GL | 241 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 1109.02
GL | 241 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 145.78
GL | 241 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 505.75
AP | 241 | 06/30/25 | 578 | Consolidated Supply Co. |  | 2306.06 | S012482970.001
AP | 241 | 06/30/25 | 579 | Consolidated Supply Co. |  | 77.41 | S012482970.002
GL | 241 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 523.29
AP | 241 | 07/09/25 | 89 | Consolidated Supply Co. |  | 442.8 | S012482970.003
AP | 241 | 07/09/25 | 90 | Consolidated Supply Co. |  | 621.97 | S012488834.001
GL | 241 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 410.62
GL | 241 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 2197.51
AP | 241 | 07/25/25 | 227 | Consolidated Supply Co. |  | 785.46 | S012494172.001
AP | 241 | 07/25/25 | 229 | Consolidated Supply Co. |  | 346.92 | S012498433.001
AP | 241 | 07/30/25 | 595 | MacArthur Co. NW 6276 |  | 12785.13 | 252208417
AP | 241 | 08/01/25 | 114 | MacArthur Co. NW 6276 |  | 9892.8 | 252213161
GL | 241 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 168.1
GL | 241 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 33.66
AP | 241 | 08/13/25 | 242 | Ferguson Enterprises, Inc. #3007 |  | 1206.15 | 3918199
GL | 241 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 1261.88
AP | 241 | 09/08/25 | 72 | MacArthur Co. NW 6276 |  | 1098 | 252234945
AP | 241 | 09/16/25 | 174 | Consolidated Supply Co. |  | 692.9 | S012570620.001
AP | 241 | 09/16/25 | 176 | Consolidated Supply Co. |  | 75.15 | S012573093.001
GL | 241 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 15.98
AP | 241 | 09/22/25 | 312 | Consolidated Supply Co. |  | 1150.05 | S012541414.001
AP | 241 | 09/22/25 | 328 | Consolidated Supply Co. |  | 106.03 | S012573093.002
GL | 241 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 19.07
GL | 241 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 4.27
GL | 241 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | -237.98
GL | 241 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 161.93
GL | 241 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 86.87
GL | 241 | 11/21/25 | 425 | Req 713 |  | -2730
GL | 241 | 12/15/25 | 260 | 2025-12-07 to 12/13 |  | 2.42
AP | 241 | 12/22/25 | 493 | Pac West Sales |  | 438.4 | I-2513289
GL | 241 | 12/22/25 | 500 | 2025-12-14 to 12-20 |  | 6.36
AP | 241 | 01/13/26 | 248 | Pac West Sales |  | 137 | I-2613625
GL | 241 | 01/21/26 | 425 | 2026-01-11 to 01-17 |  | 12.71
GL | 241 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 6.36
GL | 241 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 24.56
GL | 241 | 02/23/26 | 414 | 2026-02-15 to 02-21 |  | 1096.1
AP | 241 | 03/04/26 | 31 | Ferguson Enterprises, Inc. #3007 |  | 18.41 | 4424139
AP | 241 | 03/04/26 | 33 | Pacific Plumbing Supply Co., LLC |  | 1546.56 | 52103653
GL | 241 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 128.25
GL | 241 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | -16.24
GL | 241 | 03/30/26 | 583 | 2026-03-23 to 03-27 |  | 58.74
GL | 242 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 10.03
GL | 242 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 34.78
AP | 242 | 05/02/25 | 101 | Pacific Plumbing Supply Co., LLC |  | 36.39 | 51846076
GL | 242 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 15.19
AP | 242 | 05/27/25 | 298 | Capital One Credit Card |  | 65.05 | 050325J
GL | 242 | 08/04/25 | 77 | 2025-07-27 to 2025-08-02 |  | 68.58
GL | 242 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 159.26
AP | 242 | 08/13/25 | 243 | Pacific Plumbing Supply Co., LLC |  | 17904.08 | 51929544
AP | 242 | 08/13/25 | 256 | Consolidated Supply Co. |  | 630.05 | S012547644.001
AP | 242 | 08/15/25 | 325 | Pacific Plumbing Supply Co., LLC |  | 896.63 | 51934154
AP | 242 | 08/19/25 | 342 | Pacific Plumbing Supply Co., LLC |  | 447.18 | 51935528
AP | 242 | 08/25/25 | 447 | Consolidated Supply Co. |  | 225.26 | S012547644.002
AP | 242 | 08/26/25 | 508 | Pacific Plumbing Supply Co., LLC |  | 149 | 51939316
GL | 242 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 237.37
GL | 242 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 112.87
AP | 242 | 09/24/25 | 379 | Pacific Plumbing Supply Co., LLC |  | 413.12 | 51959598
AP | 242 | 09/24/25 | 384 | Pacific Plumbing Supply Co., LLC |  | 181.68 | 51960727
AP | 242 | 09/30/25 | 501 | Capital One Credit Card |  | 48.74 | 082925J
GL | 242 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 2335.03
GL | 242 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 860.61
AP | 242 | 10/14/25 | 298 | Pacific Plumbing Supply Co., LLC |  | 5476.6 | 51974835
AP | 242 | 10/14/25 | 331 | Consolidated Supply Co. |  | 7164.72 | S012588585.001
AP | 242 | 10/14/25 | 342 | Pacific Plumbing Supply Co., LLC |  | 10031 | 51982114
AP | 242 | 10/15/25 | 356 | Consolidated Supply Co. |  | 4421.14 | S012631770.001
AP | 242 | 10/17/25 | 453 | Pacific Plumbing Supply Co., LLC |  | 236.96 | 51984931
AP | 242 | 10/17/25 | 454 | Pacific Plumbing Supply Co., LLC |  | 50.04 | 51986259
GL | 242 | 10/21/25 | 459 | 2025-10-12 to 10-18 |  | 246.97
AP | 242 | 10/21/25 | 469 | Consolidated Supply Co. |  | 2581.99 | S012631770.002
GL | 242 | 10/28/25 | 633 | 2025-10-19 to 10-25 |  | 174.4
AP | 242 | 10/29/25 | 645 | Rosen Supply Kirkland |  | 67.45 | 34518.01
AP | 242 | 10/31/25 | 768 | Pacific Plumbing Supply Co., LLC |  | 4280.24 | 51996091
GL | 242 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | 97.05
AP | 242 | 11/05/25 | 30 | Pacific Plumbing Supply Co., LLC |  | 137 | 51998659
AP | 242 | 11/05/25 | 31 | Pacific Plumbing Supply Co., LLC |  | 530.4 | 52000720
AP | 242 | 11/07/25 | 128 | Rosen Supply Kirkland |  | 227.83 | 34697.01
GL | 242 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 77.36
GL | 242 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | -6.56
AP | 242 | 11/10/25 | 172 | Pacific Plumbing Supply Co., LLC |  | 90 | 52006601
AP | 242 | 11/14/25 | 284 | Pacific Plumbing Supply Co., LLC |  | 153.36 | 52012941
AP | 242 | 11/14/25 | 285 | Pacific Plumbing Supply Co., LLC |  | 219.64 | 52012942
GL | 242 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 687.44
AP | 242 | 11/20/25 | 396 | Ferguson Enterprises, Inc. #3007 |  | 3880.78 | 4173496
AP | 242 | 11/20/25 | 397 | Ferguson Enterprises, Inc. #3007 |  | 91.52 | 4173527
AP | 242 | 11/21/25 | 408 | Ferguson Enterprises, Inc. #3007 |  | 399.5 | 4180212
GL | 242 | 11/24/25 | 475 | 2025-11-16 to 11-22 |  | 58.79
GL | 242 | 11/30/25 | 586 | 2025-11-23 to 11-29 |  | 131.67
AP | 242 | 12/02/25 | 17 | Pacific Plumbing Supply Co., LLC |  | 1396.03 | 52023770
GL | 242 | 12/08/25 | 126 | 2025-11-30 to 12-06 |  | 106.4
AP | 242 | 12/08/25 | 137 | Pacific Plumbing Supply Co., LLC |  | 40.33 | 52029893
AP | 242 | 12/11/25 | 245 | Pacific Plumbing Supply Co., LLC |  | 607.62 | 52033874
GL | 242 | 12/15/25 | 260 | 2025-12-07 to 12/13 |  | 213.79
AP | 242 | 12/17/25 | 304 | Pacific Plumbing Supply Co., LLC |  | 36.8 | 52041372
AP | 242 | 12/22/25 | 495 | Pacific Plumbing Supply Co., LLC |  | 550.8 | 52042706
GL | 242 | 12/22/25 | 500 | 2025-12-14 to 12-20 |  | 216.44
GL | 242 | 12/29/25 | 584 | 2025-12-21 to 12-27 |  | 1.56
AP | 242 | 01/09/26 | 218 | Pacific Plumbing Supply Co., LLC |  | 197.54 | 52053688
GL | 242 | 01/12/26 | 238 | 2026-01-04 to 01-10 |  | 65.39
AP | 242 | 01/21/26 | 420 | Capital One Credit Card |  | 25.03 | 010526J
AP | 242 | 01/21/26 | 447 | Pacific Plumbing Supply Co., LLC |  | 20.88 | 52067459
AP | 242 | 01/22/26 | 533 | Pacific Plumbing Supply Co., LLC |  | 20.74 | 52068628
GL | 242 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 90.53
AP | 242 | 02/01/26 | 267 | Pacific Plumbing Supply Co., LLC |  | 17.52 | 52090284
AP | 242 | 02/02/26 | 24 | Rosen Supply Kirkland |  | 322.93 | 36091.01
AP | 242 | 02/10/26 | 167 | Pacific Plumbing Supply Co., LLC |  | 365.28 | 52085033
AP | 242 | 02/11/26 | 170 | Pacific Plumbing Supply Co., LLC |  | 35.84 | 52086215
GL | 242 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 73.35
AP | 242 | 02/26/26 | 505 | Pacific Plumbing Supply Co., LLC |  | 215.75 | 52097849
GL | 242 | 02/28/26 | 549 | 2026-02-22 to 02-28 |  | 22.64
AP | 242 | 03/04/26 | 32 | Pacific Plumbing Supply Co., LLC |  | 573.4 | 52102620
AP | 242 | 03/06/26 | 114 | Pacific Plumbing Supply Co., LLC |  | 22.51 | 52105636
AP | 242 | 03/06/26 | 115 | Pacific Plumbing Supply Co., LLC |  | 122.6 | 52107862
GL | 242 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | -458.31
AP | 251 | 04/01/24 | 744 | Core & Main LP $HD Supply Waterworks |  | 277.08 | U647855
GL | 251 | 08/07/24 | 216 | & Main |  | -277.08
AP | 600 | 02/24/26 | 429 | Mechanical Resource Services, Inc. |  | 14500 | 17955-6340
AP | 600 | 03/06/26 | 119 | Chemical Products Company |  | 3450 | 4250
AP | 601 | 03/26/24 | 1107 | Franklin Engineering |  | 8252.5 | 1060
AP | 602 | 08/12/24 | 374 | Williams Scotsman, Inc. $Mobile Mini |  | 871.16 | 9021601542
AP | 602 | 09/09/24 | 109 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9021814762
AP | 602 | 09/30/24 | 691 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9022032988
AP | 602 | 10/30/24 | 731 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9022259303
AP | 602 | 11/26/24 | 641 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9022488799
AP | 602 | 01/02/25 | 113 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9022708288
AP | 602 | 01/22/25 | 481 | Herc Rentals, Inc. |  | 991.84 | 35188743-001
AP | 602 | 01/22/25 | 491 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9022906374
AP | 602 | 02/14/25 | 272 | Herc Rentals, Inc. |  | 807.12 | 35218565-001
AP | 602 | 02/18/25 | 299 | Herc Rentals, Inc. |  | 796.52 | 35188743-002
AP | 602 | 02/18/25 | 301 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 923107520
AP | 602 | 02/20/25 | 388 | Herc Rentals, Inc. |  | 655.16 | 35243828-001
AP | 602 | 03/12/25 | 193 | Herc Rentals, Inc. |  | 398.26 | 35218565-002
AP | 602 | 03/18/25 | 307 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9023311314
AP | 602 | 03/18/25 | 309 | Herc Rentals, Inc. |  | 796.52 | 35188743-003
AP | 602 | 03/21/25 | 495 | Herc Rentals, Inc. |  | 398.26 | 35243828-002
AP | 602 | 04/04/25 | 88 | Herc Rentals, Inc. |  | 814.52 | 35188743-004
AP | 602 | 04/08/25 | 134 | Herc Rentals, Inc. |  | 398.26 | 35218565-003
AP | 602 | 04/15/25 | 321 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9023510349
AP | 602 | 04/18/25 | 488 | Herc Rentals, Inc. |  | 398.26 | 35243828-003
AP | 602 | 05/06/25 | 123 | Herc Rentals, Inc. |  | 398.26 | 35218565-004
AP | 602 | 05/08/25 | 216 | Herc Rentals, Inc. |  | 659.3 | 35428308-001
AP | 602 | 05/13/25 | 275 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9023707990
AP | 602 | 05/19/25 | 419 | Herc Rentals, Inc. |  | 398.26 | 35243828-004
AP | 602 | 05/31/25 | 661 | Herc Rentals, Inc. |  | 398.26 | 35218565-005
AP | 602 | 06/03/25 | 10 | United Rentals, Inc. |  | 298.95 | 248140869-001
AP | 602 | 06/11/25 | 172 | Herc Rentals, Inc. |  | 398.26 | 35428308-002
AP | 602 | 06/11/25 | 173 | Herc Rentals, Inc. |  | 443.97 | 35428308-003
AP | 602 | 06/11/25 | 174 | Herc Rentals, Inc. |  | 364.12 | 35218565-006
AP | 602 | 06/11/25 | 177 | Williams Scotsman, Inc. $Mobile Mini |  | 220.09 | 9023904666
AP | 602 | 06/13/25 | 265 | Herc Rentals, Inc. |  | 398.26 | 35243828-005
AP | 602 | 07/09/25 | 129 | Williams Scotsman, Inc. $Mobile Mini |  | 251.87 | 9024098464
AP | 602 | 07/15/25 | 265 | Herc Rentals, Inc. |  | 398.26 | 35243828-007
AP | 602 | 08/01/25 | 116 | Williams Scotsman, Inc. $Mobile Mini |  | 251.87 | 9024294185
AP | 602 | 08/08/25 | 226 | Herc Rentals, Inc. |  | 390.61 | 35243828-008
AP | 602 | 09/16/25 | 188 | Herc Rentals, Inc. |  | 390.61 | 35243828-010
AP | 602 | 09/16/25 | 195 | Williams Scotsman, Inc. $Mobile Mini |  | 251.87 | 9024487037
AP | 602 | 10/03/25 | 95 | Williams Scotsman, Inc. $Mobile Mini |  | 251.87 | 9024680488
AP | 602 | 10/14/25 | 288 | Herc Rentals, Inc. |  | 390.61 | 35243828-011
AP | 602 | 10/31/25 | 762 | Herc Rentals, Inc. |  | 400.27 | 35243828-012
AP | 602 | 12/02/25 | 11 | Herc Rentals, Inc. |  | 400.27 | 325243828-013
AP | 602 | 01/22/26 | 529 | Herc Rentals, Inc. |  | 400.98 | 35243828-015
AP | 602 | 02/20/26 | 377 | Herc Rentals, Inc. |  | 400.98 | 35243828-016
AP | 603 | 04/01/24 | 683 | Bank of America CC |  | 14944 | 031324J
AP | 603 | 08/02/24 | 103 | Bank of America CC |  | 1206 | 070824J
AP | 603 | 09/30/24 | 632 | Bank of America CC |  | 130 | 082724J
AP | 603 | 10/15/24 | 378 | Bank of America CC |  | 1206 | 092724J
AP | 603 | 11/30/24 | 762 | Bank of America CC |  | 50 | 110524J
AP | 603 | 04/16/25 | 353 | Bank of America CC |  | 964 | 040925J
AP | 603 | 08/26/25 | 504 | Bank of America CC |  | 236 | 080725B2
AP | 603 | 12/22/25 | 476 | Bank of America CC |  | 340 | 112425J
AP | 603 | 01/20/26 | 396 | Bank of America CC |  | 1796.02 | 122925B
AP | 603 | 03/24/26 | 432 | Bank of America CC |  | 284 | 021926J
AP | 603 | 03/24/26 | 438 | Bank of America CC |  | 1365 | 021326B
PR | 995 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 03/15/24 | 507 | Barnhart, Joseph N |  | 84.97
PR | 995 | 03/15/24 | 599 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 03/22/24 | 878 | Johnson, Jake E |  | 21.66
PR | 995 | 03/29/24 | 1182 | Barnhart, Joseph N |  | 84.97
PR | 995 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 03/29/24 | 1256 | Johnson, Jake E |  | 43.32
PR | 995 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 04/05/24 | 74 | Johnson, Jake E |  | 21.66
PR | 995 | 04/12/24 | 166 | Barnhart, Joseph N |  | 226.58
PR | 995 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 04/12/24 | 236 | Johnson, Jake E |  | 86.63
PR | 995 | 04/19/24 | 445 | Barnhart, Joseph N |  | 141.61
PR | 995 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 04/19/24 | 517 | Johnson, Jake E |  | 64.97
PR | 995 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 05/03/24 | 68 | Johnson, Jake E |  | 173.26
PR | 995 | 05/10/24 | 242 | Barnhart, Joseph N |  | 84.97
PR | 995 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 05/10/24 | 306 | Johnson, Jake E |  | 194.92
PR | 995 | 05/17/24 | 470 | Barnhart, Joseph N |  | 311.54
PR | 995 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 05/24/24 | 738 | Johnson, Jake E |  | 86.63
PR | 995 | 05/31/24 | 793 | Barnhart, Joseph N |  | 198.25
PR | 995 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 229.91
PR | 995 | 05/31/24 | 850 | Johnson, Jake E |  | 108.29
PR | 995 | 06/07/24 | 81 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/07/24 | 81 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 06/07/24 | 139 | Johnson, Jake E |  | 86.63
PR | 995 | 06/14/24 | 305 | Barnhart, Joseph N |  | 56.64
PR | 995 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 06/14/24 | 362 | Johnson, Jake E |  | 86.63
PR | 995 | 06/21/24 | 480 | Barnhart, Joseph N |  | 226.58
PR | 995 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 06/21/24 | 533 | Johnson, Jake E |  | 21.66
PR | 995 | 06/28/24 | 687 | Barnhart, Joseph N |  | 169.93
PR | 995 | 06/28/24 | 716 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 06/28/24 | 719 | Da Cruz, Eduardo E |  | 34.99
PR | 995 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 06/28/24 | 740 | Johnson, Jake E |  | 86.63
PR | 995 | 07/05/24 | 4 | Barnhart, Joseph N |  | 56.64
PR | 995 | 07/05/24 | 34 | Da Cruz, Eduardo E |  | 34.99
PR | 995 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 07/05/24 | 53 | Johnson, Jake E |  | 173.26
PR | 995 | 07/12/24 | 166 | Anderson, Richard P |  | 54.15
PR | 995 | 07/12/24 | 167 | Barnhart, Joseph N |  | 240.74
PR | 995 | 07/12/24 | 193 | Cortes Mendiola, Victor H |  | 133.28
PR | 995 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 07/12/24 | 216 | Johnson, Jake E |  | 64.97
PR | 995 | 07/19/24 | 374 | Anderson, Richard P |  | 94.75
PR | 995 | 07/19/24 | 390 | Barnhart, Joseph N |  | 467.31
PR | 995 | 07/19/24 | 390 | Barnhart, Joseph N |  | 42.48
PR | 995 | 07/19/24 | 391 | Bautista Quintero, Isidoro |  | 24.99
PR | 995 | 07/19/24 | 399 | Cortes Mendiola, Victor H |  | 213.25
PR | 995 | 07/19/24 | 402 | Da Cruz, Eduardo E |  | 26.24
PR | 995 | 07/19/24 | 407 | Eisenhauer, Tommy J |  | 71.22
PR | 995 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 07/19/24 | 422 | Johnson, Jake E |  | 86.63
PR | 995 | 07/26/24 | 563 | Anderson, Richard P |  | 609.13
PR | 995 | 07/26/24 | 573 | Amaya Gonzalez, Edilberto A |  | 109.96
PR | 995 | 07/26/24 | 579 | Bautista Quintero, Isidoro |  | 49.98
PR | 995 | 07/26/24 | 587 | Cortes Mendiola, Victor H |  | 693.06
PR | 995 | 07/26/24 | 590 | Da Cruz, Eduardo E |  | 52.48
PR | 995 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 07/26/24 | 609 | Johnson, Jake E |  | 64.97
PR | 995 | 08/02/24 | 2 | Anderson, Richard P |  | 351.94
PR | 995 | 08/02/24 | 13 | Amaya Gonzalez, Edilberto A |  | 733.04
PR | 995 | 08/02/24 | 18 | Barnhart, Joseph N |  | 509.8
PR | 995 | 08/02/24 | 19 | Bautista Quintero, Isidoro |  | 333.2
PR | 995 | 08/02/24 | 27 | Cortes Mendiola, Victor H |  | 1066.24
PR | 995 | 08/02/24 | 30 | Da Cruz, Eduardo E |  | 349.86
PR | 995 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 08/02/24 | 49 | Johnson, Jake E |  | 108.29
PR | 995 | 08/02/24 | 49 | Johnson, Jake E |  | 43.32
PR | 995 | 08/09/24 | 248 | Amaya Gonzalez, Edilberto A |  | 678.06
PR | 995 | 08/09/24 | 253 | Barnhart, Joseph N |  | 396.51
PR | 995 | 08/09/24 | 254 | Bautista Quintero, Isidoro |  | 333.2
PR | 995 | 08/09/24 | 262 | Cortes Mendiola, Victor H |  | 1012.93
PR | 995 | 08/09/24 | 265 | Da Cruz, Eduardo E |  | 349.86
PR | 995 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 08/09/24 | 283 | Johnson, Jake E |  | 21.66
PR | 995 | 08/16/24 | 439 | Amaya Gonzalez, Edilberto A |  | 733.04
PR | 995 | 08/16/24 | 444 | Barnhart, Joseph N |  | 113.29
PR | 995 | 08/16/24 | 445 | Bautista Quintero, Isidoro |  | 333.2
PR | 995 | 08/16/24 | 453 | Cortes Mendiola, Victor H |  | 1066.24
PR | 995 | 08/16/24 | 456 | Da Cruz, Eduardo E |  | 349.86
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 08/16/24 | 472 | Johnson, Jake E |  | 21.66
PR | 995 | 08/23/24 | 694 | Cruz Reyes, Jose |  | 68.31
PR | 995 | 08/23/24 | 694 | Cruz Reyes, Jose |  | 68.31
PR | 995 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A |  | 586.43
PR | 995 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A |  | 146.61
PR | 995 | 08/23/24 | 706 | Barnhart, Joseph N |  | 141.61
PR | 995 | 08/23/24 | 706 | Barnhart, Joseph N |  | 141.61
PR | 995 | 08/23/24 | 706 | Barnhart, Joseph N |  | 169.93
PR | 995 | 08/23/24 | 707 | Bautista Quintero, Isidoro |  | 266.56
PR | 995 | 08/23/24 | 707 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 08/23/24 | 715 | Cortes Mendiola, Victor H |  | 852.99
PR | 995 | 08/23/24 | 715 | Cortes Mendiola, Victor H |  | 213.25
PR | 995 | 08/23/24 | 718 | Da Cruz, Eduardo E |  | 139.94
PR | 995 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 287.39
PR | 995 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 129.32
PR | 995 | 08/23/24 | 734 | Johnson, Jake E |  | 21.66
PR | 995 | 08/30/24 | 833 | Anderson, Richard P |  | 81.22
PR | 995 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A |  | 403.17
PR | 995 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A |  | 183.26
PR | 995 | 08/30/24 | 849 | Barnhart, Joseph N |  | 339.86
PR | 995 | 08/30/24 | 849 | Barnhart, Joseph N |  | 113.29
PR | 995 | 08/30/24 | 849 | Barnhart, Joseph N |  | 84.97
PR | 995 | 08/30/24 | 850 | Bautista Quintero, Isidoro |  | 249.9
PR | 995 | 08/30/24 | 850 | Bautista Quintero, Isidoro |  | 83.3
PR | 995 | 08/30/24 | 858 | Cortes Mendiola, Victor H |  | 1012.93
PR | 995 | 08/30/24 | 858 | Cortes Mendiola, Victor H |  | 53.31
PR | 995 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/30/24 | 876 | Johnson, Jake E |  | 151.61
PR | 995 | 08/30/24 | 896 | Silva Morales, Jair J |  | 424.83
PR | 995 | 08/30/24 | 896 | Silva Morales, Jair J |  | 141.61
PR | 995 | 09/06/24 | 13 | Cruz Reyes, Jose |  | 136.61
PR | 995 | 09/06/24 | 13 | Cruz Reyes, Jose |  | 409.84
PR | 995 | 09/06/24 | 19 | Waites, Thaddeus Z |  | 177.85
PR | 995 | 09/06/24 | 20 | Amaya Gonzalez, Edilberto A |  | 679.73
PR | 995 | 09/06/24 | 25 | Barnhart, Joseph N |  | 226.58
PR | 995 | 09/06/24 | 25 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/06/24 | 26 | Bautista Quintero, Isidoro |  | 266.56
PR | 995 | 09/06/24 | 34 | Cortes Mendiola, Victor H |  | 852.99
PR | 995 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 09/06/24 | 53 | Johnson, Jake E |  | 173.26
PR | 995 | 09/06/24 | 73 | Silva Morales, Jair J |  | 453.15
PR | 995 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 136.61
PR | 995 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 136.61
PR | 995 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A |  | 637.25
PR | 995 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A |  | 106.21
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 198.25
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/13/24 | 234 | Bautista Quintero, Isidoro |  | 308.21
PR | 995 | 09/13/24 | 242 | Cortes Mendiola, Victor H |  | 773.02
PR | 995 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 258.65
PR | 995 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 09/13/24 | 261 | Johnson, Jake E |  | 238.24
PR | 995 | 09/13/24 | 280 | Silva Morales, Jair J |  | 453.15
PR | 995 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A |  | 233.66
PR | 995 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A |  | 616
PR | 995 | 09/20/24 | 405 | Barnhart, Joseph N |  | 283.22
PR | 995 | 09/20/24 | 405 | Barnhart, Joseph N |  | 56.64
PR | 995 | 09/20/24 | 406 | Bautista Quintero, Isidoro |  | 308.21
PR | 995 | 09/20/24 | 406 | Bautista Quintero, Isidoro |  | 24.99
PR | 995 | 09/20/24 | 414 | Cortes Mendiola, Victor H |  | 932.96
PR | 995 | 09/20/24 | 414 | Cortes Mendiola, Victor H |  | 53.31
PR | 995 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 316.12
PR | 995 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 09/20/24 | 432 | Johnson, Jake E |  | 194.92
PR | 995 | 09/20/24 | 451 | Silva Morales, Jair J |  | 155.77
PR | 995 | 09/20/24 | 451 | Silva Morales, Jair J |  | 410.67
PR | 995 | 09/27/24 | 537 | Amaya Gonzalez, Edilberto A |  | 785.94
PR | 995 | 09/27/24 | 542 | Barnhart, Joseph N |  | 566.44
PR | 995 | 09/27/24 | 542 | Barnhart, Joseph N |  | 113.29
PR | 995 | 09/27/24 | 543 | Bautista Quintero, Isidoro |  | 333.2
PR | 995 | 09/27/24 | 550 | Cortes Mendiola, Victor H |  | 852.99
PR | 995 | 09/27/24 | 559 | Gerard, Jeffrey S |  | 229.91
PR | 995 | 09/27/24 | 559 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 09/27/24 | 568 | Johnson, Jake E |  | 43.32
PR | 995 | 09/27/24 | 587 | Silva Morales, Jair J |  | 453.15
PR | 995 | 09/27/24 | 587 | Silva Morales, Jair J |  | 113.29
PR | 995 | 10/04/24 | 20 | Waites, Thaddeus Z |  | 457.32
PR | 995 | 10/04/24 | 20 | Waites, Thaddeus Z |  | 152.44
PR | 995 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A |  | 509.8
PR | 995 | 10/04/24 | 26 | Barnhart, Joseph N |  | 339.86
PR | 995 | 10/04/24 | 27 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 10/04/24 | 27 | Bautista Quintero, Isidoro |  | 199.92
PR | 995 | 10/04/24 | 34 | Cortes Mendiola, Victor H |  | 239.9
PR | 995 | 10/04/24 | 34 | Cortes Mendiola, Victor H |  | 639.74
PR | 995 | 10/04/24 | 39 | Eisenhauer, Tommy J |  | 379.85
PR | 995 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 258.65
PR | 995 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 100.58
PR | 995 | 10/04/24 | 52 | Johnson, Jake E |  | 64.97
PR | 995 | 10/04/24 | 66 | Ramos Herrera, Franklin J |  | 279.89
PR | 995 | 10/04/24 | 71 | Silva Morales, Jair J |  | 226.58
PR | 995 | 10/04/24 | 71 | Silva Morales, Jair J |  | 339.86
PR | 995 | 10/04/24 | 81 | Young, Joshua S |  | 179.93
PR | 995 | 10/11/24 | 227 | Waites, Thaddeus Z |  | 127.03
PR | 995 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 99.13
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 155.77
PR | 995 | 10/11/24 | 233 | Barnhart, Joseph N |  | 84.97
PR | 995 | 10/11/24 | 234 | Bautista Quintero, Isidoro |  | 133.28
PR | 995 | 10/11/24 | 234 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 10/11/24 | 241 | Cortes Mendiola, Victor H |  | 746.37
PR | 995 | 10/11/24 | 241 | Cortes Mendiola, Victor H |  | 213.25
PR | 995 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 316.12
PR | 995 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/11/24 | 259 | Johnson, Jake E |  | 129.95
PR | 995 | 10/11/24 | 277 | Silva Morales, Jair J |  | 339.86
PR | 995 | 10/11/24 | 277 | Silva Morales, Jair J |  | 113.29
PR | 995 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A |  | 679.73
PR | 995 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 283.22
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/18/24 | 446 | Barnhart, Joseph N |  | 84.97
PR | 995 | 10/18/24 | 447 | Bautista Quintero, Isidoro |  | 133.28
PR | 995 | 10/18/24 | 454 | Cortes Mendiola, Victor H |  | 959.62
PR | 995 | 10/18/24 | 454 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 316.12
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 129.32
PR | 995 | 10/18/24 | 471 | Johnson, Jake E |  | 173.26
PR | 995 | 10/18/24 | 489 | Silva Morales, Jair J |  | 509.8
PR | 995 | 10/18/24 | 489 | Silva Morales, Jair J |  | 56.64
PR | 995 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A |  | 743.45
PR | 995 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A |  | 106.21
PR | 995 | 10/25/24 | 594 | Barnhart, Joseph N |  | 28.32
PR | 995 | 10/25/24 | 594 | Barnhart, Joseph N |  | 56.64
PR | 995 | 10/25/24 | 595 | Bautista Quintero, Isidoro |  | 291.55
PR | 995 | 10/25/24 | 595 | Bautista Quintero, Isidoro |  | 41.65
PR | 995 | 10/25/24 | 601 | Cortes Mendiola, Victor H |  | 746.37
PR | 995 | 10/25/24 | 601 | Cortes Mendiola, Victor H |  | 319.87
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 10/25/24 | 618 | Johnson, Jake E |  | 129.95
PR | 995 | 10/25/24 | 629 | Portillo Rivera, Josue N |  | 219.91
PR | 995 | 10/25/24 | 636 | Silva Morales, Jair J |  | 566.44
PR | 995 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A |  | 637.25
PR | 995 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 11/01/24 | 23 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/01/24 | 23 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/01/24 | 24 | Bautista Quintero, Isidoro |  | 199.92
PR | 995 | 11/01/24 | 24 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/01/24 | 30 | Cortes Mendiola, Victor H |  | 879.65
PR | 995 | 11/01/24 | 30 | Cortes Mendiola, Victor H |  | 186.59
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 201.17
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 11/01/24 | 47 | Johnson, Jake E |  | 86.63
PR | 995 | 11/01/24 | 58 | Portillo Rivera, Josue N |  | 293.22
PR | 995 | 11/01/24 | 65 | Silva Morales, Jair J |  | 523.96
PR | 995 | 11/01/24 | 65 | Silva Morales, Jair J |  | 42.48
PR | 995 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A |  | 552.28
PR | 995 | 11/08/24 | 143 | Barnhart, Joseph N |  | 56.64
PR | 995 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 83.3
PR | 995 | 11/08/24 | 150 | Cortes Mendiola, Victor H |  | 906.3
PR | 995 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 11/08/24 | 167 | Johnson, Jake E |  | 86.63
PR | 995 | 11/08/24 | 179 | Portillo Rivera, Josue N |  | 219.91
PR | 995 | 11/08/24 | 179 | Portillo Rivera, Josue N |  | 73.3
PR | 995 | 11/08/24 | 186 | Silva Morales, Jair J |  | 453.15
PR | 995 | 11/08/24 | 186 | Silva Morales, Jair J |  | 113.29
PR | 995 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 509.8
PR | 995 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 254.9
PR | 995 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 84.97
PR | 995 | 11/15/24 | 363 | Barnhart, Joseph N |  | 84.97
PR | 995 | 11/15/24 | 363 | Barnhart, Joseph N |  | 28.32
PR | 995 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 158.27
PR | 995 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 99.96
PR | 995 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 33.32
PR | 995 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 719.71
PR | 995 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/15/24 | 387 | Johnson, Jake E |  | 129.95
PR | 995 | 11/15/24 | 399 | Portillo Rivera, Josue N |  | 73.3
PR | 995 | 11/15/24 | 399 | Portillo Rivera, Josue N |  | 146.61
PR | 995 | 11/15/24 | 406 | Silva Morales, Jair J |  | 339.86
PR | 995 | 11/15/24 | 406 | Silva Morales, Jair J |  | 226.58
PR | 995 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A |  | 509.8
PR | 995 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 11/22/24 | 519 | Bautista Quintero, Isidoro |  | 266.56
PR | 995 | 11/22/24 | 519 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/22/24 | 525 | Cortes Mendiola, Victor H |  | 266.56
PR | 995 | 11/22/24 | 525 | Cortes Mendiola, Victor H |  | 746.37
PR | 995 | 11/22/24 | 531 | Eliassen, Cory H |  | 213.66
PR | 995 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 11/22/24 | 554 | Portillo Rivera, Josue N |  | 219.91
PR | 995 | 11/22/24 | 554 | Portillo Rivera, Josue N |  | 146.61
PR | 995 | 11/22/24 | 561 | Silva Morales, Jair J |  | 453.15
PR | 995 | 11/22/24 | 561 | Silva Morales, Jair J |  | 113.29
PR | 995 | 11/29/24 | 648 | Johnson, Jake E |  | 21.66
PR | 995 | 11/29/24 | 648 | Johnson, Jake E |  | 43.32
PR | 995 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 11/29/24 | 666 | Barnhart, Joseph N |  | 113.29
PR | 995 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 133.28
PR | 995 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 133.28
PR | 995 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 399.84
PR | 995 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 266.56
PR | 995 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 399.84
PR | 995 | 11/29/24 | 679 | Eliassen, Cory H |  | -213.66
PR | 995 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 11/29/24 | 690 | Johnson, Jake E |  | 86.63
PR | 995 | 11/29/24 | 692 | Lopez, Maslin A |  | 549.78
PR | 995 | 11/29/24 | 702 | Portillo Rivera, Josue N |  | 73.3
PR | 995 | 11/29/24 | 702 | Portillo Rivera, Josue N |  | 73.3
PR | 995 | 11/29/24 | 709 | Silva Morales, Jair J |  | 226.58
PR | 995 | 11/29/24 | 709 | Silva Morales, Jair J |  | 113.29
PR | 995 | 11/29/24 | 709 | Silva Morales, Jair J |  | 226.58
PR | 995 | 12/06/24 | 51 | Anderson, Richard P |  | 27.07
PR | 995 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 276.14
PR | 995 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 63.72
PR | 995 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 41.65
PR | 995 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 24.99
PR | 995 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 533.12
PR | 995 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 79.97
PR | 995 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 26.66
PR | 995 | 12/06/24 | 83 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 12/06/24 | 83 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/06/24 | 92 | Johnson, Jake E |  | 86.63
PR | 995 | 12/06/24 | 94 | Lopez, Maslin A |  | 329.87
PR | 995 | 12/06/24 | 110 | Silva Morales, Jair J |  | 226.58
PR | 995 | 12/06/24 | 110 | Silva Morales, Jair J |  | 113.29
PR | 995 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 169.93
PR | 995 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 12/13/24 | 250 | Barnhart, Joseph N |  | 84.97
PR | 995 | 12/13/24 | 250 | Barnhart, Joseph N |  | 56.64
PR | 995 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 199.92
PR | 995 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 479.81
PR | 995 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 373.18
PR | 995 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 213.25
PR | 995 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/13/24 | 274 | Johnson, Jake E |  | 43.32
PR | 995 | 12/13/24 | 276 | Lopez, Maslin A |  | 109.96
PR | 995 | 12/13/24 | 276 | Lopez, Maslin A |  | 329.87
PR | 995 | 12/13/24 | 292 | Silva Morales, Jair J |  | 453.15
PR | 995 | 12/13/24 | 292 | Silva Morales, Jair J |  | 113.29
PR | 995 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A |  | 424.83
PR | 995 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A |  | 424.83
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 198.25
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 28.32
PR | 995 | 12/20/24 | 438 | Bautista Quintero, Isidoro |  | 166.6
PR | 995 | 12/20/24 | 438 | Bautista Quintero, Isidoro |  | 166.6
PR | 995 | 12/20/24 | 444 | Cortes Mendiola, Victor H |  | 639.74
PR | 995 | 12/20/24 | 444 | Cortes Mendiola, Victor H |  | 426.5
PR | 995 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 12/20/24 | 460 | Johnson, Jake E |  | 64.97
PR | 995 | 12/20/24 | 462 | Lopez, Maslin A |  | 439.82
PR | 995 | 12/20/24 | 479 | Silva Morales, Jair J |  | 566.44
PR | 995 | 12/27/24 | 551 | Amaya Gonzalez, Edilberto A |  | 509.8
PR | 995 | 12/27/24 | 556 | Barnhart, Joseph N |  | 56.64
PR | 995 | 12/27/24 | 556 | Barnhart, Joseph N |  | 56.64
PR | 995 | 12/27/24 | 557 | Bautista Quintero, Isidoro |  | 199.92
PR | 995 | 12/27/24 | 563 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 12/27/24 | 563 | Cortes Mendiola, Victor H |  | 533.12
PR | 995 | 12/27/24 | 568 | Eliassen, Cory H |  | 23.74
PR | 995 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 12/27/24 | 579 | Johnson, Jake E |  | 43.32
PR | 995 | 12/27/24 | 581 | Lopez, Maslin A |  | 329.87
PR | 995 | 12/27/24 | 595 | Silva Morales, Jair J |  | 339.86
PR | 995 | 01/03/25 | 23 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 01/03/25 | 29 | Bautista Quintero, Isidoro |  | 66.64
PR | 995 | 01/03/25 | 30 | Carmona, Raul O |  | 353.19
PR | 995 | 01/03/25 | 34 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 01/03/25 | 34 | Cortes Mendiola, Victor H |  | 319.87
PR | 995 | 01/03/25 | 41 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 01/03/25 | 41 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 01/03/25 | 49 | Johnson, Jake E |  | 21.66
PR | 995 | 01/03/25 | 51 | Lopez, Maslin A |  | 109.96
PR | 995 | 01/03/25 | 63 | Silva Morales, Jair J |  | 56.64
PR | 995 | 01/03/25 | 63 | Silva Morales, Jair J |  | 169.93
PR | 995 | 01/10/25 | 185 | Amaya Gonzalez, Edilberto A |  | 679.73
PR | 995 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 73.3
PR | 995 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 146.61
PR | 995 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 73.3
PR | 995 | 01/10/25 | 192 | Carmona, Raul O |  | 706.38
PR | 995 | 01/10/25 | 196 | Cortes Mendiola, Victor H |  | 852.99
PR | 995 | 01/10/25 | 198 | Cruz Guzman, Joel A |  | 169.93
PR | 995 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 01/10/25 | 212 | Johnson, Jake E |  | 151.61
PR | 995 | 01/10/25 | 214 | Lopez, Maslin A |  | 439.82
PR | 995 | 01/10/25 | 218 | Mendoza Morales, Jesus A |  | 273.22
PR | 995 | 01/10/25 | 227 | Silva Morales, Jair J |  | 453.15
PR | 995 | 01/17/25 | 349 | Amaya Gonzalez, Edilberto A |  | 849.66
PR | 995 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 01/17/25 | 354 | Barnhart, Joseph N |  | 254.9
PR | 995 | 01/17/25 | 354 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/17/25 | 355 | Bautista Quintero, Isidoro |  | 293.22
PR | 995 | 01/17/25 | 356 | Carmona, Raul O |  | 882.98
PR | 995 | 01/17/25 | 360 | Cortes Mendiola, Victor H |  | 586.43
PR | 995 | 01/17/25 | 360 | Cortes Mendiola, Victor H |  | 479.81
PR | 995 | 01/17/25 | 367 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 01/17/25 | 367 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 01/17/25 | 375 | Johnson, Jake E |  | 173.26
PR | 995 | 01/17/25 | 377 | Lopez, Maslin A |  | 439.82
PR | 995 | 01/17/25 | 381 | Mendoza Morales, Jesus A |  | 546.45
PR | 995 | 01/17/25 | 391 | Silva Morales, Jair J |  | 566.44
PR | 995 | 01/24/25 | 514 | Waites, Thaddeus Z |  | 1016.26
PR | 995 | 01/24/25 | 515 | Amaya Gonzalez, Edilberto A |  | 509.8
PR | 995 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 42.48
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 226.58
PR | 995 | 01/24/25 | 520 | Barnhart, Joseph N |  | 28.32
PR | 995 | 01/24/25 | 521 | Bautista Quintero, Isidoro |  | 329.87
PR | 995 | 01/24/25 | 521 | Bautista Quintero, Isidoro |  | 36.65
PR | 995 | 01/24/25 | 522 | Carmona, Raul O |  | 882.98
PR | 995 | 01/24/25 | 526 | Cortes Mendiola, Victor H |  | 746.37
PR | 995 | 01/24/25 | 526 | Cortes Mendiola, Victor H |  | 319.87
PR | 995 | 01/24/25 | 528 | Cruz Guzman, Joel A |  | 849.66
PR | 995 | 01/24/25 | 530 | Draves, Steven W |  | 114.54
PR | 995 | 01/24/25 | 534 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 01/24/25 | 534 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 01/24/25 | 544 | Lopez, Maslin A |  | 439.82
PR | 995 | 01/24/25 | 548 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 01/24/25 | 558 | Silva Morales, Jair J |  | 453.15
PR | 995 | 01/24/25 | 611 | Johnson, Jake E |  | 64.97
PR | 995 | 01/31/25 | 706 | Waites, Thaddeus Z |  | 1016.26
PR | 995 | 01/31/25 | 707 | Amaya Gonzalez, Edilberto A |  | 849.66
PR | 995 | 01/31/25 | 711 | Balderas Ortiz, Ricardo I |  | 586.43
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 141.61
PR | 995 | 01/31/25 | 713 | Bautista Quintero, Isidoro |  | 366.52
PR | 995 | 01/31/25 | 714 | Carmona, Raul O |  | 882.98
PR | 995 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 693.06
PR | 995 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 106.62
PR | 995 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 266.56
PR | 995 | 01/31/25 | 720 | Cruz Guzman, Joel A |  | 849.66
PR | 995 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 01/31/25 | 734 | Johnson, Jake E |  | 129.95
PR | 995 | 01/31/25 | 736 | Lopez, Maslin A |  | 109.96
PR | 995 | 01/31/25 | 740 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 01/31/25 | 749 | Silva Morales, Jair J |  | 566.44
PR | 995 | 02/07/25 | 36 | Waites, Thaddeus Z |  | 609.76
PR | 995 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A |  | 339.86
PR | 995 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I |  | 439.82
PR | 995 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I |  | 293.22
PR | 995 | 02/07/25 | 43 | Bautista Quintero, Isidoro |  | 146.61
PR | 995 | 02/07/25 | 43 | Bautista Quintero, Isidoro |  | 146.61
PR | 995 | 02/07/25 | 44 | Carmona, Raul O |  | 706.38
PR | 995 | 02/07/25 | 48 | Cortes Mendiola, Victor H |  | 479.81
PR | 995 | 02/07/25 | 48 | Cortes Mendiola, Victor H |  | 586.43
PR | 995 | 02/07/25 | 50 | Cruz Guzman, Joel A |  | 679.73
PR | 995 | 02/07/25 | 52 | Draves, Steven W |  | 503.97
PR | 995 | 02/07/25 | 56 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 02/07/25 | 56 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 02/07/25 | 64 | Johnson, Jake E |  | 108.29
PR | 995 | 02/07/25 | 70 | Mendoza Morales, Jesus A |  | 683.06
PR | 995 | 02/07/25 | 80 | Silva Morales, Jair J |  | 453.15
PR | 995 | 02/14/25 | 201 | Hernandez Gonzalez, Osbaldo |  | 608.83
PR | 995 | 02/14/25 | 202 | Waites, Thaddeus Z |  | 884.26
PR | 995 | 02/14/25 | 203 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 02/14/25 | 207 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 02/14/25 | 208 | Barnhart, Joseph N |  | 277.24
PR | 995 | 02/14/25 | 208 | Barnhart, Joseph N |  | 77.01
PR | 995 | 02/14/25 | 209 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 02/14/25 | 210 | Carmona, Raul O |  | 768.29
PR | 995 | 02/14/25 | 214 | Cortes Mendiola, Victor H |  | 811.78
PR | 995 | 02/14/25 | 214 | Cortes Mendiola, Victor H |  | 347.9
PR | 995 | 02/14/25 | 216 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 02/14/25 | 222 | Gerard, Jeffrey S |  | 125.03
PR | 995 | 02/14/25 | 222 | Gerard, Jeffrey S |  | 171.91
PR | 995 | 02/14/25 | 223 | Gerard, Jordan E |  | 217.44
PR | 995 | 02/14/25 | 224 | Gochez Molina, Douglas O |  | 453
PR | 995 | 02/14/25 | 227 | Guerrero Espinoza, Mario |  | 326.16
PR | 995 | 02/14/25 | 230 | Johnson, Jake E |  | 43.32
PR | 995 | 02/14/25 | 236 | Mendoza Morales, Jesus A |  | 445.75
PR | 995 | 02/14/25 | 236 | Mendoza Morales, Jesus A |  | 297.17
PR | 995 | 02/14/25 | 240 | Perez Araque, Manuel A |  | 453
PR | 995 | 02/14/25 | 241 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 02/14/25 | 246 | Silva Morales, Jair J |  | 616.08
PR | 995 | 02/14/25 | 249 | Taylor, Evan R |  | 188.45
PR | 995 | 02/21/25 | 311 | Anderson, Richard P |  | 29.45
PR | 995 | 02/21/25 | 318 | Galdamez, Dagoberto A |  | 304.42
PR | 995 | 02/21/25 | 319 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 02/21/25 | 320 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 02/21/25 | 321 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 02/21/25 | 325 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 02/21/25 | 326 | Barnhart, Joseph N |  | 92.41
PR | 995 | 02/21/25 | 327 | Bautista Quintero, Isidoro |  | 368.74
PR | 995 | 02/21/25 | 327 | Bautista Quintero, Isidoro |  | 29.9
PR | 995 | 02/21/25 | 328 | Carmona, Raul O |  | 768.29
PR | 995 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 840.77
PR | 995 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 02/21/25 | 334 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 02/21/25 | 336 | Draves, Steven W |  | 398.64
PR | 995 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 218.8
PR | 995 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 46.89
PR | 995 | 02/21/25 | 341 | Gerard, Jordan E |  | 217.44
PR | 995 | 02/21/25 | 342 | Gochez Molina, Douglas O |  | 453
PR | 995 | 02/21/25 | 345 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 02/21/25 | 348 | Johnson, Jake E |  | 108.29
PR | 995 | 02/21/25 | 354 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 02/21/25 | 358 | Perez Araque, Manuel A |  | 362.4
PR | 995 | 02/21/25 | 359 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 02/21/25 | 364 | Silva Morales, Jair J |  | 616.08
PR | 995 | 02/21/25 | 367 | Taylor, Evan R |  | 565.34
PR | 995 | 02/28/25 | 508 | Galdamez, Dagoberto A |  | 761.04
PR | 995 | 02/28/25 | 509 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 02/28/25 | 510 | Waites, Thaddeus Z |  | 663.19
PR | 995 | 02/28/25 | 511 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 02/28/25 | 515 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 215.63
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 61.61
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 61.61
PR | 995 | 02/28/25 | 517 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 02/28/25 | 518 | Carmona, Raul O |  | 960.36
PR | 995 | 02/28/25 | 521 | Cornejo Orellana, Carlos E |  | 380.52
PR | 995 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 753.79
PR | 995 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 202.94
PR | 995 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 02/28/25 | 524 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 02/28/25 | 526 | Draves, Steven W |  | 797.28
PR | 995 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 140.66
PR | 995 | 02/28/25 | 532 | Gochez Molina, Douglas O |  | 453
PR | 995 | 02/28/25 | 535 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 02/28/25 | 537 | Jimenez Alvarenga, Gerson M |  | 424.01
PR | 995 | 02/28/25 | 538 | Johnson, Jake E |  | 108.29
PR | 995 | 02/28/25 | 544 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 02/28/25 | 548 | Perez Araque, Manuel A |  | 453
PR | 995 | 02/28/25 | 549 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 02/28/25 | 551 | Rodriguez Arevalos, Christian |  | 554.47
PR | 995 | 02/28/25 | 554 | Silva Morales, Jair J |  | 616.08
PR | 995 | 02/28/25 | 557 | Taylor, Evan R |  | 942.24
PR | 995 | 03/07/25 | 18 | Cruz Reyes, Jose |  | 297.17
PR | 995 | 03/07/25 | 21 | Galdamez, Dagoberto A |  | 608.83
PR | 995 | 03/07/25 | 22 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 03/07/25 | 23 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A |  | 669.99
PR | 995 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A |  | 69.31
PR | 995 | 03/07/25 | 28 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 03/07/25 | 29 | Barnhart, Joseph N |  | 107.81
PR | 995 | 03/07/25 | 30 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 03/07/25 | 31 | Carmona, Raul O |  | 960.36
PR | 995 | 03/07/25 | 34 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 898.75
PR | 995 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 173.95
PR | 995 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 03/07/25 | 37 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 03/07/25 | 39 | Draves, Steven W |  | 398.64
PR | 995 | 03/07/25 | 43 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 03/07/25 | 43 | Gerard, Jeffrey S |  | 125.03
PR | 995 | 03/07/25 | 45 | Gochez Molina, Douglas O |  | 362.4
PR | 995 | 03/07/25 | 48 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 03/07/25 | 50 | Jimenez Alvarenga, Gerson M |  | 424.01
PR | 995 | 03/07/25 | 51 | Johnson, Jake E |  | 151.61
PR | 995 | 03/07/25 | 52 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 03/07/25 | 57 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 03/07/25 | 61 | Perez Araque, Manuel A |  | 271.8
PR | 995 | 03/07/25 | 61 | Perez Araque, Manuel A |  | 181.2
PR | 995 | 03/07/25 | 62 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 03/07/25 | 64 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 03/07/25 | 67 | Silva Morales, Jair J |  | 616.08
PR | 995 | 03/07/25 | 68 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 03/07/25 | 70 | Taylor, Evan R |  | 565.34
PR | 995 | 03/07/25 | 78 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 03/14/25 | 222 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 03/14/25 | 223 | Waites, Thaddeus Z |  | 635.56
PR | 995 | 03/14/25 | 224 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 03/14/25 | 228 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 03/14/25 | 229 | Barnhart, Joseph N |  | 30.8
PR | 995 | 03/14/25 | 229 | Barnhart, Joseph N |  | 308.04
PR | 995 | 03/14/25 | 229 | Barnhart, Joseph N |  | 30.8
PR | 995 | 03/14/25 | 230 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 03/14/25 | 231 | Carmona, Raul O |  | 960.36
PR | 995 | 03/14/25 | 234 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 03/14/25 | 235 | Cortes Mendiola, Victor H |  | 1014.72
PR | 995 | 03/14/25 | 235 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 03/14/25 | 237 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 03/14/25 | 239 | Draves, Steven W |  | 946.77
PR | 995 | 03/14/25 | 243 | Gerard, Jeffrey S |  | 156.29
PR | 995 | 03/14/25 | 243 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 03/14/25 | 245 | Gochez Molina, Douglas O |  | 453
PR | 995 | 03/14/25 | 248 | Guerrero Espinoza, Mario |  | 217.44
PR | 995 | 03/14/25 | 250 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 03/14/25 | 251 | Johnson, Jake E |  | 129.95
PR | 995 | 03/14/25 | 252 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 03/14/25 | 253 | Lopez, Maslin A |  | 239.18
PR | 995 | 03/14/25 | 257 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 635.56
PR | 995 | 03/14/25 | 261 | Perez Araque, Manuel A |  | 453
PR | 995 | 03/14/25 | 262 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 03/14/25 | 264 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 03/14/25 | 267 | Silva Morales, Jair J |  | 492.86
PR | 995 | 03/14/25 | 268 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 03/14/25 | 270 | Taylor, Evan R |  | 895.13
PR | 995 | 03/14/25 | 278 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 03/14/25 | 401 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 03/14/25 | 404 | Galdamez, Dagoberto A |  | 761.04
PR | 995 | 03/14/25 | 405 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 03/14/25 | 406 | Waites, Thaddeus Z |  | 884.26
PR | 995 | 03/14/25 | 411 | Cruz Reyes, Jose |  | -594.34
PR | 995 | 03/14/25 | 414 | Galdamez, Dagoberto A |  | -761.04
PR | 995 | 03/14/25 | 415 | Hernandez Gonzalez, Osbaldo |  | -456.62
PR | 995 | 03/14/25 | 416 | Waites, Thaddeus Z |  | -884.26
PR | 995 | 03/21/25 | 417 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 03/21/25 | 420 | Ascencio, Jose L |  | 608.83
PR | 995 | 03/21/25 | 421 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 03/21/25 | 422 | Barnhart, Joseph N |  | 508.27
PR | 995 | 03/21/25 | 422 | Barnhart, Joseph N |  | 30.8
PR | 995 | 03/21/25 | 422 | Barnhart, Joseph N |  | 92.41
PR | 995 | 03/21/25 | 423 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 03/21/25 | 424 | Carmona, Raul O |  | 768.29
PR | 995 | 03/21/25 | 425 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 03/21/25 | 427 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 03/21/25 | 428 | Cortes Mendiola, Victor H |  | 927.74
PR | 995 | 03/21/25 | 428 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 03/21/25 | 430 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 03/21/25 | 432 | Draves, Steven W |  | 996.6
PR | 995 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 03/21/25 | 438 | Gochez Molina, Douglas O |  | 453
PR | 995 | 03/21/25 | 441 | Guerrero Espinoza, Mario |  | 108.72
PR | 995 | 03/21/25 | 443 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 03/21/25 | 444 | Johnson, Jake E |  | 129.95
PR | 995 | 03/21/25 | 445 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 03/21/25 | 446 | Lopez, Maslin A |  | 119.59
PR | 995 | 03/21/25 | 450 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 03/21/25 | 453 | Paco Leyva, Orlando |  | 884.26
PR | 995 | 03/21/25 | 454 | Perez Araque, Manuel A |  | 362.4
PR | 995 | 03/21/25 | 455 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 03/21/25 | 456 | Ramos Herrera, Franklin J |  | 456.62
PR | 995 | 03/21/25 | 458 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 03/21/25 | 461 | Silva Morales, Jair J |  | 616.08
PR | 995 | 03/21/25 | 462 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 03/21/25 | 464 | Taylor, Evan R |  | 942.24
PR | 995 | 03/21/25 | 472 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 03/21/25 | 477 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 03/21/25 | 480 | Galdamez, Dagoberto A |  | 761.04
PR | 995 | 03/21/25 | 481 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 03/21/25 | 482 | Waites, Thaddeus Z |  | 884.26
PR | 995 | 03/28/25 | 566 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 03/28/25 | 567 | Del Villar, Flabio |  | 90.6
PR | 995 | 03/28/25 | 569 | Galdamez, Dagoberto A |  | 608.83
PR | 995 | 03/28/25 | 570 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 03/28/25 | 571 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 03/28/25 | 572 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 03/28/25 | 575 | Ascencio, Jose L |  | 761.04
PR | 995 | 03/28/25 | 576 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 03/28/25 | 577 | Barnhart, Joseph N |  | 92.41
PR | 995 | 03/28/25 | 578 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 03/28/25 | 579 | Carmona, Raul O |  | 960.36
PR | 995 | 03/28/25 | 580 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 03/28/25 | 582 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 03/28/25 | 583 | Cortes Mendiola, Victor H |  | 1014.72
PR | 995 | 03/28/25 | 583 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 03/28/25 | 585 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 03/28/25 | 587 | Draves, Steven W |  | 797.28
PR | 995 | 03/28/25 | 591 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 03/28/25 | 591 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 03/28/25 | 593 | Gerard, Mitchell J |  | 663.19
PR | 995 | 03/28/25 | 594 | Gochez Molina, Douglas O |  | 453
PR | 995 | 03/28/25 | 597 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 03/28/25 | 599 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 03/28/25 | 600 | Johnson, Jake E |  | 194.92
PR | 995 | 03/28/25 | 601 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 03/28/25 | 602 | Lopez, Maslin A |  | 597.96
PR | 995 | 03/28/25 | 606 | Melgar Moz, Brandon |  | 79.73
PR | 995 | 03/28/25 | 607 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 03/28/25 | 610 | Paco Leyva, Orlando |  | 1050.05
PR | 995 | 03/28/25 | 611 | Perez Araque, Manuel A |  | 453
PR | 995 | 03/28/25 | 612 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 03/28/25 | 613 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 03/28/25 | 615 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 03/28/25 | 617 | Ross, Kelli M |  | 184.82
PR | 995 | 03/28/25 | 618 | Silva Morales, Jair J |  | 616.08
PR | 995 | 03/28/25 | 619 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 03/28/25 | 621 | Taylor, Evan R |  | 753.79
PR | 995 | 03/28/25 | 629 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 04/04/25 | 9 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 04/04/25 | 10 | Del Villar, Flabio |  | 181.2
PR | 995 | 04/04/25 | 11 | Fox, Tamron P |  | 73.39
PR | 995 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 304.42
PR | 995 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 304.42
PR | 995 | 04/04/25 | 13 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 04/04/25 | 14 | Waites, Thaddeus Z |  | 856.62
PR | 995 | 04/04/25 | 15 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 04/04/25 | 18 | Ascencio, Jose L |  | 761.04
PR | 995 | 04/04/25 | 19 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 04/04/25 | 20 | Barnhart, Joseph N |  | 92.41
PR | 995 | 04/04/25 | 20 | Barnhart, Joseph N |  | 277.24
PR | 995 | 04/04/25 | 20 | Barnhart, Joseph N |  | 30.8
PR | 995 | 04/04/25 | 21 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 04/04/25 | 22 | Carmona, Raul O |  | 960.36
PR | 995 | 04/04/25 | 23 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 04/04/25 | 25 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 04/04/25 | 26 | Cortes Mendiola, Victor H |  | 1014.72
PR | 995 | 04/04/25 | 26 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 04/04/25 | 28 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 04/04/25 | 30 | Draves, Steven W |  | 996.6
PR | 995 | 04/04/25 | 34 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 04/04/25 | 34 | Gerard, Jeffrey S |  | 156.29
PR | 995 | 04/04/25 | 36 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 04/04/25 | 37 | Gochez Molina, Douglas O |  | 453
PR | 995 | 04/04/25 | 40 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 04/04/25 | 42 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 04/04/25 | 43 | Johnson, Jake E |  | 151.61
PR | 995 | 04/04/25 | 44 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 04/04/25 | 45 | Lopez, Maslin A |  | 478.37
PR | 995 | 04/04/25 | 49 | Melgar Moz, Brandon |  | 159.46
PR | 995 | 04/04/25 | 50 | Mendoza Morales, Jesus A |  | 668.63
PR | 995 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 469.76
PR | 995 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 221.06
PR | 995 | 04/04/25 | 54 | Perez Araque, Manuel A |  | 453
PR | 995 | 04/04/25 | 55 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 04/04/25 | 56 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 04/04/25 | 57 | Reed, Reuben H |  | 168.52
PR | 995 | 04/04/25 | 58 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 04/04/25 | 60 | Ross, Kelli M |  | 924.12
PR | 995 | 04/04/25 | 61 | Silva Morales, Jair J |  | 492.86
PR | 995 | 04/04/25 | 62 | Suniga Aviles, Kelvin A |  | 361.49
PR | 995 | 04/04/25 | 64 | Taylor, Evan R |  | 753.79
PR | 995 | 04/04/25 | 71 | Zuniga Avilez, Eduar A |  | 378.71
PR | 995 | 04/11/25 | 172 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 04/11/25 | 173 | Del Villar, Flabio |  | 797.28
PR | 995 | 04/11/25 | 174 | Fox, Tamron P |  | 269.08
PR | 995 | 04/11/25 | 175 | Galdamez, Dagoberto A |  | 456.62
PR | 995 | 04/11/25 | 175 | Galdamez, Dagoberto A |  | 304.42
PR | 995 | 04/11/25 | 176 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 04/11/25 | 177 | Waites, Thaddeus Z |  | 980.97
PR | 995 | 04/11/25 | 195 | Amaya Gonzalez, Edilberto A |  | 739.3
PR | 995 | 04/11/25 | 198 | Ascencio, Jose L |  | 761.04
PR | 995 | 04/11/25 | 199 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 04/11/25 | 200 | Barnhart, Joseph N |  | 184.82
PR | 995 | 04/11/25 | 200 | Barnhart, Joseph N |  | 30.8
PR | 995 | 04/11/25 | 201 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 04/11/25 | 202 | Carmona, Raul O |  | 960.36
PR | 995 | 04/11/25 | 203 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 04/11/25 | 205 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 04/11/25 | 206 | Cortes Mendiola, Victor H |  | 1072.7
PR | 995 | 04/11/25 | 206 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 04/11/25 | 208 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 04/11/25 | 210 | Draves, Steven W |  | 597.96
PR | 995 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 78.14
PR | 995 | 04/11/25 | 216 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 04/11/25 | 217 | Gochez Molina, Douglas O |  | 453
PR | 995 | 04/11/25 | 220 | Guerrero Espinoza, Mario |  | 217.44
PR | 995 | 04/11/25 | 222 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 04/11/25 | 223 | Johnson, Jake E |  | 151.61
PR | 995 | 04/11/25 | 224 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 04/11/25 | 225 | Lopez, Maslin A |  | 597.96
PR | 995 | 04/11/25 | 228 | McCabe, Thomas C |  | 478.37
PR | 995 | 04/11/25 | 229 | Melgar Moz, Brandon |  | 398.64
PR | 995 | 04/11/25 | 230 | Mendoza Morales, Jesus A |  | 594.34
PR | 995 | 04/11/25 | 231 | Merino Martinez, Humberto |  | 202.94
PR | 995 | 04/11/25 | 233 | Paco Leyva, Orlando |  | 1105.32
PR | 995 | 04/11/25 | 234 | Perez Araque, Manuel A |  | 181.2
PR | 995 | 04/11/25 | 235 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 04/11/25 | 236 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 04/11/25 | 237 | Reed, Reuben H |  | 617.89
PR | 995 | 04/11/25 | 238 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 04/11/25 | 240 | Ross, Kelli M |  | 739.3
PR | 995 | 04/11/25 | 241 | Silva Morales, Jair J |  | 616.08
PR | 995 | 04/11/25 | 242 | Suniga Aviles, Kelvin A |  | 228.31
PR | 995 | 04/11/25 | 244 | Taylor, Evan R |  | 753.79
PR | 995 | 04/11/25 | 251 | Zuniga Avilez, Eduar A |  | 318.91
PR | 995 | 04/18/25 | 413 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 04/18/25 | 414 | Del Villar, Flabio |  | 398.64
PR | 995 | 04/18/25 | 415 | Fox, Tamron P |  | 195.7
PR | 995 | 04/18/25 | 416 | Galdamez, Dagoberto A |  | 608.83
PR | 995 | 04/18/25 | 417 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 994.79
PR | 995 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 04/18/25 | 422 | Ascencio, Jose L |  | 761.04
PR | 995 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 04/18/25 | 424 | Barnhart, Joseph N |  | 462.06
PR | 995 | 04/18/25 | 425 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 04/18/25 | 426 | Carmona, Raul O |  | 960.36
PR | 995 | 04/18/25 | 427 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 04/18/25 | 429 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 1014.72
PR | 995 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 04/18/25 | 432 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 04/18/25 | 434 | Draves, Steven W |  | 797.28
PR | 995 | 04/18/25 | 438 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 04/18/25 | 438 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 04/18/25 | 440 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 04/18/25 | 441 | Gochez Molina, Douglas O |  | 453
PR | 995 | 04/18/25 | 444 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 04/18/25 | 446 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 04/18/25 | 447 | Johnson, Jake E |  | 173.26
PR | 995 | 04/18/25 | 448 | Lima Romero, Melvin A |  | 478.37
PR | 995 | 04/18/25 | 448 | Lima Romero, Melvin A |  | 159.46
PR | 995 | 04/18/25 | 449 | Lopez, Maslin A |  | 478.37
PR | 995 | 04/18/25 | 452 | McCabe, Thomas C |  | 797.28
PR | 995 | 04/18/25 | 453 | Melgar Moz, Brandon |  | 279.05
PR | 995 | 04/18/25 | 454 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 04/18/25 | 455 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 884.26
PR | 995 | 04/18/25 | 459 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 04/18/25 | 460 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 04/18/25 | 461 | Reed, Reuben H |  | 449.38
PR | 995 | 04/18/25 | 462 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 04/18/25 | 464 | Ross, Kelli M |  | 924.12
PR | 995 | 04/18/25 | 465 | Silva Morales, Jair J |  | 616.08
PR | 995 | 04/18/25 | 466 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 04/18/25 | 468 | Taylor, Evan R |  | 376.9
PR | 995 | 04/18/25 | 475 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 04/25/25 | 550 | Castro, Marcus J |  | 159.46
PR | 995 | 04/25/25 | 552 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 04/25/25 | 553 | Del Villar, Flabio |  | 478.37
PR | 995 | 04/25/25 | 554 | Fox, Tamron P |  | 293.54
PR | 995 | 04/25/25 | 555 | Galdamez, Dagoberto A |  | 608.83
PR | 995 | 04/25/25 | 556 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 04/25/25 | 557 | Waites, Thaddeus Z |  | 939.52
PR | 995 | 04/25/25 | 558 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 04/25/25 | 559 | Aquino, Juan |  | 232.39
PR | 995 | 04/25/25 | 561 | Ascencio, Jose L |  | 761.04
PR | 995 | 04/25/25 | 562 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 04/25/25 | 563 | Barnhart, Joseph N |  | 338.84
PR | 995 | 04/25/25 | 564 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 04/25/25 | 565 | Carmona, Raul O |  | 960.36
PR | 995 | 04/25/25 | 566 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 04/25/25 | 568 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 869.76
PR | 995 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 04/25/25 | 571 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 04/25/25 | 573 | Draves, Steven W |  | 722.54
PR | 995 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 125.03
PR | 995 | 04/25/25 | 579 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 04/25/25 | 580 | Gochez Molina, Douglas O |  | 453
PR | 995 | 04/25/25 | 583 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 04/25/25 | 585 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 04/25/25 | 586 | Johnson, Jake E |  | 43.32
PR | 995 | 04/25/25 | 587 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 04/25/25 | 588 | Lopez, Maslin A |  | 597.96
PR | 995 | 04/25/25 | 591 | McCabe, Thomas C |  | 797.28
PR | 995 | 04/25/25 | 592 | Melgar Moz, Brandon |  | 398.64
PR | 995 | 04/25/25 | 593 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 04/25/25 | 594 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 04/25/25 | 596 | Paco Leyva, Orlando |  | 663.19
PR | 995 | 04/25/25 | 598 | Portillo Soriano, Walter A |  | 507.36
PR | 995 | 04/25/25 | 599 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 04/25/25 | 600 | Reed, Reuben H |  | 674.06
PR | 995 | 04/25/25 | 601 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 04/25/25 | 603 | Ross, Kelli M |  | 369.65
PR | 995 | 04/25/25 | 604 | Silva Morales, Jair J |  | 616.08
PR | 995 | 04/25/25 | 605 | Suniga Aviles, Kelvin A |  | 304.42
PR | 995 | 04/25/25 | 607 | Taylor, Evan R |  | 565.34
PR | 995 | 04/25/25 | 614 | Zuniga Avilez, Eduar A |  | 318.91
PR | 995 | 05/02/25 | 4 | Castro, Marcus J |  | 159.46
PR | 995 | 05/02/25 | 6 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 05/02/25 | 8 | Fox, Tamron P |  | 97.85
PR | 995 | 05/02/25 | 9 | Galdamez, Dagoberto A |  | 608.83
PR | 995 | 05/02/25 | 9 | Galdamez, Dagoberto A |  | 152.21
PR | 995 | 05/02/25 | 10 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 05/02/25 | 11 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 05/02/25 | 12 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 05/02/25 | 13 | Aquino, Juan |  | 97.85
PR | 995 | 05/02/25 | 15 | Ascencio, Jose L |  | 608.83
PR | 995 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I |  | 637.82
PR | 995 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I |  | 159.46
PR | 995 | 05/02/25 | 17 | Barnhart, Joseph N |  | 200.23
PR | 995 | 05/02/25 | 18 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 05/02/25 | 19 | Carmona, Raul O |  | 768.29
PR | 995 | 05/02/25 | 20 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 05/02/25 | 22 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 927.74
PR | 995 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 05/02/25 | 25 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 05/02/25 | 27 | Draves, Steven W |  | 921.86
PR | 995 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 05/02/25 | 33 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 05/02/25 | 34 | Gochez Molina, Douglas O |  | 453
PR | 995 | 05/02/25 | 37 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 05/02/25 | 39 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 05/02/25 | 40 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 05/02/25 | 41 | Lopez, Maslin A |  | 418.57
PR | 995 | 05/02/25 | 44 | McCabe, Thomas C |  | 797.28
PR | 995 | 05/02/25 | 45 | Melgar Moz, Brandon |  | 398.64
PR | 995 | 05/02/25 | 46 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 05/02/25 | 47 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 967.16
PR | 995 | 05/02/25 | 51 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 05/02/25 | 52 | Ramos Herrera, Franklin J |  | 456.62
PR | 995 | 05/02/25 | 52 | Ramos Herrera, Franklin J |  | 152.21
PR | 995 | 05/02/25 | 54 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 05/02/25 | 56 | Ross, Kelli M |  | 739.3
PR | 995 | 05/02/25 | 57 | Silva Morales, Jair J |  | 616.08
PR | 995 | 05/02/25 | 58 | Suniga Aviles, Kelvin A |  | 304.42
PR | 995 | 05/02/25 | 60 | Taylor, Evan R |  | 942.24
PR | 995 | 05/02/25 | 66 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 05/09/25 | 151 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 05/09/25 | 153 | Fox, Tamron P |  | 195.7
PR | 995 | 05/09/25 | 154 | Galdamez, Dagoberto A |  | 456.62
PR | 995 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo |  | 152.21
PR | 995 | 05/09/25 | 156 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 05/09/25 | 157 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 05/09/25 | 160 | Ascencio, Jose L |  | 608.83
PR | 995 | 05/09/25 | 161 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 338.84
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 30.8
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 61.61
PR | 995 | 05/09/25 | 163 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 05/09/25 | 164 | Carmona, Raul O |  | 960.36
PR | 995 | 05/09/25 | 165 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 05/09/25 | 166 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 985.73
PR | 995 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 05/09/25 | 169 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 05/09/25 | 171 | Draves, Steven W |  | 523.22
PR | 995 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 05/09/25 | 175 | Gerard, Jordan E |  | 217.44
PR | 995 | 05/09/25 | 176 | Gerard, Mitchell J |  | 884.26
PR | 995 | 05/09/25 | 177 | Gochez Molina, Douglas O |  | 453
PR | 995 | 05/09/25 | 180 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 05/09/25 | 182 | Jimenez Alvarenga, Gerson M |  | 565.34
PR | 995 | 05/09/25 | 183 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 05/09/25 | 184 | Lopez, Maslin A |  | 358.78
PR | 995 | 05/09/25 | 187 | McCabe, Thomas C |  | 797.28
PR | 995 | 05/09/25 | 188 | Melgar Moz, Brandon |  | 398.64
PR | 995 | 05/09/25 | 189 | Mendoza Morales, Jesus A |  | 594.34
PR | 995 | 05/09/25 | 190 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 05/09/25 | 192 | Paco Leyva, Orlando |  | 884.26
PR | 995 | 05/09/25 | 194 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 05/09/25 | 195 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 05/09/25 | 196 | Reed, Reuben H |  | 449.38
PR | 995 | 05/09/25 | 197 | Rodriguez Arevalos, Christian |  | 739.3
PR | 995 | 05/09/25 | 199 | Ross, Kelli M |  | 924.12
PR | 995 | 05/09/25 | 200 | Silva Morales, Jair J |  | 616.08
PR | 995 | 05/09/25 | 201 | Suniga Aviles, Kelvin A |  | 380.52
PR | 995 | 05/09/25 | 203 | Taylor, Evan R |  | 753.79
PR | 995 | 05/09/25 | 207 | Zuniga Avilez, Eduar A |  | 398.64
PR | 995 | 05/16/25 | 350 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 05/16/25 | 353 | Galdamez, Dagoberto A |  | 761.04
PR | 995 | 05/16/25 | 354 | Hernandez Gonzalez, Osbaldo |  | 761.04
PR | 995 | 05/16/25 | 355 | Waites, Thaddeus Z |  | 497.39
PR | 995 | 05/16/25 | 356 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 05/16/25 | 359 | Ascencio, Jose L |  | 761.04
PR | 995 | 05/16/25 | 360 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 05/16/25 | 361 | Barnhart, Joseph N |  | 184.82
PR | 995 | 05/16/25 | 362 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 05/16/25 | 363 | Carmona, Raul O |  | 960.36
PR | 995 | 05/16/25 | 364 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 05/16/25 | 365 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 695.81
PR | 995 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 05/16/25 | 368 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 05/16/25 | 370 | Draves, Steven W |  | 398.64
PR | 995 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 140.66
PR | 995 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 05/16/25 | 375 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 05/16/25 | 376 | Gochez Molina, Douglas O |  | 453
PR | 995 | 05/16/25 | 379 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 05/16/25 | 381 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 05/16/25 | 382 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 05/16/25 | 383 | Lopez, Maslin A |  | 478.37
PR | 995 | 05/16/25 | 386 | McCabe, Thomas C |  | 797.28
PR | 995 | 05/16/25 | 387 | Melgar Moz, Brandon |  | 398.64
PR | 995 | 05/16/25 | 388 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 05/16/25 | 389 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 663.19
PR | 995 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 165.8
PR | 995 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 55.27
PR | 995 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 110.53
PR | 995 | 05/16/25 | 393 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 05/16/25 | 394 | Ramos Herrera, Franklin J |  | 456.62
PR | 995 | 05/16/25 | 394 | Ramos Herrera, Franklin J |  | 304.42
PR | 995 | 05/16/25 | 395 | Reed, Reuben H |  | 449.38
PR | 995 | 05/16/25 | 396 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 05/16/25 | 398 | Ross, Kelli M |  | 924.12
PR | 995 | 05/16/25 | 399 | Silva Morales, Jair J |  | 616.08
PR | 995 | 05/16/25 | 400 | Suniga Aviles, Kelvin A |  | 304.42
PR | 995 | 05/16/25 | 402 | Taylor, Evan R |  | 565.34
PR | 995 | 05/16/25 | 406 | Zuniga Avilez, Eduar A |  | 318.91
PR | 995 | 05/23/25 | 446 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 05/23/25 | 447 | Del Villar, Flabio |  | 159.46
PR | 995 | 05/23/25 | 448 | Fox, Tamron P |  | 281.31
PR | 995 | 05/23/25 | 449 | Galdamez, Dagoberto A |  | 456.62
PR | 995 | 05/23/25 | 449 | Galdamez, Dagoberto A |  | 152.21
PR | 995 | 05/23/25 | 450 | Hernandez Gonzalez, Osbaldo |  | 608.83
PR | 995 | 05/23/25 | 451 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 05/23/25 | 452 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 05/23/25 | 455 | Ascencio, Jose L |  | 761.04
PR | 995 | 05/23/25 | 456 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 05/23/25 | 457 | Barnhart, Joseph N |  | 92.41
PR | 995 | 05/23/25 | 457 | Barnhart, Joseph N |  | 61.61
PR | 995 | 05/23/25 | 458 | Bautista Quintero, Isidoro |  | 398.64
PR | 995 | 05/23/25 | 459 | Carmona, Raul O |  | 768.29
PR | 995 | 05/23/25 | 459 | Carmona, Raul O |  | 192.07
PR | 995 | 05/23/25 | 460 | Castro Hernandez, Jose A |  | 587.09
PR | 995 | 05/23/25 | 460 | Castro Hernandez, Jose A |  | 195.7
PR | 995 | 05/23/25 | 461 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 927.74
PR | 995 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 173.95
PR | 995 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 05/23/25 | 464 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 05/23/25 | 466 | Draves, Steven W |  | 971.69
PR | 995 | 05/23/25 | 469 | Gerard, Jeffrey S |  | 125.03
PR | 995 | 05/23/25 | 469 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 05/23/25 | 470 | Gerard, Jordan E |  | 163.08
PR | 995 | 05/23/25 | 471 | Gerard, Mitchell J |  | 884.26
PR | 995 | 05/23/25 | 471 | Gerard, Mitchell J |  | 110.53
PR | 995 | 05/23/25 | 472 | Gochez Molina, Douglas O |  | 453
PR | 995 | 05/23/25 | 475 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 05/23/25 | 477 | Jimenez Alvarenga, Gerson M |  | 565.34
PR | 995 | 05/23/25 | 478 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 05/23/25 | 479 | Lopez, Maslin A |  | 597.96
PR | 995 | 05/23/25 | 482 | McCabe, Thomas C |  | 797.28
PR | 995 | 05/23/25 | 483 | Melgar Moz, Brandon |  | 318.91
PR | 995 | 05/23/25 | 484 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 05/23/25 | 485 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 221.06
PR | 995 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 138.17
PR | 995 | 05/23/25 | 489 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 05/23/25 | 490 | Ramos Herrera, Franklin J |  | 761.04
PR | 995 | 05/23/25 | 491 | Reed, Reuben H |  | 421.29
PR | 995 | 05/23/25 | 492 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 05/23/25 | 494 | Ross, Kelli M |  | 739.3
PR | 995 | 05/23/25 | 495 | Silva Morales, Jair J |  | 616.08
PR | 995 | 05/23/25 | 496 | Suniga Aviles, Kelvin A |  | 323.44
PR | 995 | 05/23/25 | 498 | Taylor, Evan R |  | 942.24
PR | 995 | 05/23/25 | 502 | Zuniga Avilez, Eduar A |  | 239.18
PR | 995 | 05/30/25 | 535 | Cruz Reyes, Jose |  | 445.75
PR | 995 | 05/30/25 | 537 | Galdamez, Dagoberto A |  | 152.21
PR | 995 | 05/30/25 | 538 | Hernandez Gonzalez, Osbaldo |  | 152.21
PR | 995 | 05/30/25 | 539 | Waites, Thaddeus Z |  | 663.19
PR | 995 | 05/30/25 | 540 | Amaya Gonzalez, Edilberto A |  | 554.47
PR | 995 | 05/30/25 | 543 | Ascencio, Jose L |  | 456.62
PR | 995 | 05/30/25 | 544 | Balderas Ortiz, Ricardo I |  | 478.37
PR | 995 | 05/30/25 | 545 | Barnhart, Joseph N |  | 215.63
PR | 995 | 05/30/25 | 546 | Bautista Quintero, Isidoro |  | 239.18
PR | 995 | 05/30/25 | 547 | Carmona, Raul O |  | 576.22
PR | 995 | 05/30/25 | 548 | Castro Hernandez, Jose A |  | 587.09
PR | 995 | 05/30/25 | 549 | Cornejo Orellana, Carlos E |  | 380.52
PR | 995 | 05/30/25 | 550 | Cortes Mendiola, Victor H |  | 695.81
PR | 995 | 05/30/25 | 552 | Cruz Guzman, Joel A |  | 369.65
PR | 995 | 05/30/25 | 554 | Draves, Steven W |  | 597.96
PR | 995 | 05/30/25 | 558 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 05/30/25 | 558 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 05/30/25 | 559 | Gerard, Jordan E |  | 27.18
PR | 995 | 05/30/25 | 560 | Gerard, Mitchell J |  | 663.19
PR | 995 | 05/30/25 | 561 | Gochez Molina, Douglas O |  | 271.8
PR | 995 | 05/30/25 | 564 | Guerrero Espinoza, Mario |  | 326.16
PR | 995 | 05/30/25 | 566 | Jimenez Alvarenga, Gerson M |  | 424.01
PR | 995 | 05/30/25 | 567 | Lima Romero, Melvin A |  | 478.37
PR | 995 | 05/30/25 | 568 | Lopez, Maslin A |  | 358.78
PR | 995 | 05/30/25 | 571 | McCabe, Thomas C |  | 478.37
PR | 995 | 05/30/25 | 572 | Melgar Moz, Brandon |  | 79.73
PR | 995 | 05/30/25 | 573 | Mendoza Morales, Jesus A |  | 445.75
PR | 995 | 05/30/25 | 574 | Merino Martinez, Humberto |  | 304.42
PR | 995 | 05/30/25 | 576 | Paco Leyva, Orlando |  | 110.53
PR | 995 | 05/30/25 | 578 | Portillo Soriano, Walter A |  | 380.52
PR | 995 | 05/30/25 | 579 | Ramos Herrera, Franklin J |  | 456.62
PR | 995 | 05/30/25 | 581 | Rodriguez Arevalos, Christian |  | 554.47
PR | 995 | 05/30/25 | 583 | Ross, Kelli M |  | 554.47
PR | 995 | 05/30/25 | 584 | Silva Morales, Jair J |  | 369.65
PR | 995 | 05/30/25 | 585 | Suniga Aviles, Kelvin A |  | 228.31
PR | 995 | 05/30/25 | 587 | Taylor, Evan R |  | 565.34
PR | 995 | 05/30/25 | 591 | Zuniga Avilez, Eduar A |  | 239.18
PR | 995 | 06/06/25 | 22 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 06/06/25 | 25 | Hernandez Gonzalez, Osbaldo |  | 456.62
PR | 995 | 06/06/25 | 26 | Waites, Thaddeus Z |  | 967.16
PR | 995 | 06/06/25 | 28 | Amaya Gonzalez, Edilberto A |  | 739.3
PR | 995 | 06/06/25 | 31 | Ascencio, Jose L |  | 761.04
PR | 995 | 06/06/25 | 32 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 06/06/25 | 33 | Barnhart, Joseph N |  | 61.61
PR | 995 | 06/06/25 | 33 | Barnhart, Joseph N |  | 61.61
PR | 995 | 06/06/25 | 34 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 06/06/25 | 35 | Carmona, Raul O |  | 960.36
PR | 995 | 06/06/25 | 36 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 06/06/25 | 37 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 06/06/25 | 38 | Cortes Mendiola, Victor H |  | 1101.7
PR | 995 | 06/06/25 | 38 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 06/06/25 | 40 | Cruz Guzman, Joel A |  | 369.65
PR | 995 | 06/06/25 | 42 | Draves, Steven W |  | 797.28
PR | 995 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 06/06/25 | 48 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 06/06/25 | 49 | Gochez Molina, Douglas O |  | 507.36
PR | 995 | 06/06/25 | 51 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 06/06/25 | 53 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 06/06/25 | 54 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 06/06/25 | 55 | Lopez, Maslin A |  | 478.37
PR | 995 | 06/06/25 | 58 | McCabe, Thomas C |  | 797.28
PR | 995 | 06/06/25 | 60 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 06/06/25 | 61 | Merino Martinez, Humberto |  | 202.94
PR | 995 | 06/06/25 | 61 | Merino Martinez, Humberto |  | 304.42
PR | 995 | 06/06/25 | 65 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 06/06/25 | 66 | Ramos Herrera, Franklin J |  | 608.83
PR | 995 | 06/06/25 | 68 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 06/06/25 | 70 | Ross, Kelli M |  | 554.47
PR | 995 | 06/06/25 | 71 | Silva Morales, Jair J |  | 616.08
PR | 995 | 06/06/25 | 72 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 06/06/25 | 74 | Taylor, Evan R |  | 565.34
PR | 995 | 06/06/25 | 78 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 06/13/25 | 184 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 456.62
PR | 995 | 06/13/25 | 187 | Hernandez Gonzalez, Osbaldo |  | 608.83
PR | 995 | 06/13/25 | 188 | Waites, Thaddeus Z |  | 1105.32
PR | 995 | 06/13/25 | 189 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 06/13/25 | 192 | Ascencio, Jose L |  | 761.04
PR | 995 | 06/13/25 | 193 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 06/13/25 | 195 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 06/13/25 | 196 | Carmona, Raul O |  | 960.36
PR | 995 | 06/13/25 | 197 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 06/13/25 | 198 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 06/13/25 | 199 | Cortes Mendiola, Victor H |  | 1014.72
PR | 995 | 06/13/25 | 199 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 06/13/25 | 201 | Cruz Guzman, Joel A |  | 554.47
PR | 995 | 06/13/25 | 203 | Draves, Steven W |  | 398.64
PR | 995 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 06/13/25 | 208 | Gerard, Jordan E |  | 190.26
PR | 995 | 06/13/25 | 209 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 06/13/25 | 210 | Gochez Molina, Douglas O |  | 507.36
PR | 995 | 06/13/25 | 213 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 06/13/25 | 215 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 06/13/25 | 216 | Lima Romero, Melvin A |  | 637.82
PR | 995 | 06/13/25 | 217 | Lopez, Maslin A |  | 358.78
PR | 995 | 06/13/25 | 220 | McCabe, Thomas C |  | 797.28
PR | 995 | 06/13/25 | 222 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 06/13/25 | 223 | Merino Martinez, Humberto |  | 304.42
PR | 995 | 06/13/25 | 223 | Merino Martinez, Humberto |  | 202.94
PR | 995 | 06/13/25 | 227 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 06/13/25 | 230 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 06/13/25 | 232 | Ross, Kelli M |  | 739.3
PR | 995 | 06/13/25 | 233 | Silva Morales, Jair J |  | 616.08
PR | 995 | 06/13/25 | 234 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 06/13/25 | 236 | Taylor, Evan R |  | 565.34
PR | 995 | 06/13/25 | 240 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 06/20/25 | 311 | Castro, Marcus J |  | 173.95
PR | 995 | 06/20/25 | 312 | Cruz Reyes, Jose |  | 445.75
PR | 995 | 06/20/25 | 316 | Waites, Thaddeus Z |  | 1022.42
PR | 995 | 06/20/25 | 317 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 06/20/25 | 318 | Aquino, Juan |  | 101.47
PR | 995 | 06/20/25 | 320 | Ascencio, Jose L |  | 761.04
PR | 995 | 06/20/25 | 321 | Balderas Ortiz, Ricardo I |  | 637.82
PR | 995 | 06/20/25 | 323 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 06/20/25 | 324 | Carmona, Raul O |  | 960.36
PR | 995 | 06/20/25 | 325 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 06/20/25 | 326 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 06/20/25 | 327 | Cortes Mendiola, Victor H |  | 869.76
PR | 995 | 06/20/25 | 327 | Cortes Mendiola, Victor H |  | 289.92
PR | 995 | 06/20/25 | 329 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 06/20/25 | 332 | Fox, Tamron P |  | 241
PR | 995 | 06/20/25 | 332 | Fox, Tamron P |  | 50.74
PR | 995 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 06/20/25 | 335 | Gerard, Jordan E |  | 190.26
PR | 995 | 06/20/25 | 336 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 06/20/25 | 337 | Gochez Molina, Douglas O |  | 507.36
PR | 995 | 06/20/25 | 340 | Guerrero Espinoza, Mario |  | 543.6
PR | 995 | 06/20/25 | 342 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 06/20/25 | 343 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 06/20/25 | 344 | Lopez, Maslin A |  | 239.18
PR | 995 | 06/20/25 | 347 | McCabe, Thomas C |  | 797.28
PR | 995 | 06/20/25 | 349 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 06/20/25 | 350 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 06/20/25 | 354 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 06/20/25 | 355 | Ramos Herrera, Franklin J |  | 456.62
PR | 995 | 06/20/25 | 356 | Reed, Reuben H |  | 533.63
PR | 995 | 06/20/25 | 356 | Reed, Reuben H |  | 112.34
PR | 995 | 06/20/25 | 357 | Rodriguez Arevalos, Christian |  | 739.3
PR | 995 | 06/20/25 | 359 | Ross, Kelli M |  | 739.3
PR | 995 | 06/20/25 | 360 | Silva Morales, Jair J |  | 492.86
PR | 995 | 06/20/25 | 361 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 06/20/25 | 363 | Taylor, Evan R |  | 565.34
PR | 995 | 06/20/25 | 366 | Young, Joshua S |  | 478.37
PR | 995 | 06/20/25 | 367 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 06/27/25 | 466 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 06/27/25 | 470 | Waites, Thaddeus Z |  | 994.79
PR | 995 | 06/27/25 | 471 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 06/27/25 | 474 | Ascencio, Jose L |  | 761.04
PR | 995 | 06/27/25 | 475 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 246.43
PR | 995 | 06/27/25 | 477 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 06/27/25 | 478 | Carmona, Raul O |  | 960.36
PR | 995 | 06/27/25 | 479 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 06/27/25 | 480 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 06/27/25 | 481 | Cortes Mendiola, Victor H |  | 927.74
PR | 995 | 06/27/25 | 481 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 06/27/25 | 484 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 78.14
PR | 995 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 06/27/25 | 490 | Gerard, Jordan E |  | 54.36
PR | 995 | 06/27/25 | 491 | Gerard, Mitchell J |  | 884.26
PR | 995 | 06/27/25 | 491 | Gerard, Mitchell J |  | 221.06
PR | 995 | 06/27/25 | 492 | Gochez Molina, Douglas O |  | 507.36
PR | 995 | 06/27/25 | 495 | Guerrero Espinoza, Mario |  | 434.88
PR | 995 | 06/27/25 | 497 | Jimenez Alvarenga, Gerson M |  | 565.34
PR | 995 | 06/27/25 | 498 | Lima Romero, Melvin A |  | 637.82
PR | 995 | 06/27/25 | 502 | McCabe, Thomas C |  | 797.28
PR | 995 | 06/27/25 | 504 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 06/27/25 | 505 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 06/27/25 | 509 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 06/27/25 | 510 | Ramos Herrera, Franklin J |  | 152.21
PR | 995 | 06/27/25 | 512 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 06/27/25 | 514 | Ross, Kelli M |  | 739.3
PR | 995 | 06/27/25 | 515 | Silva Morales, Jair J |  | 616.08
PR | 995 | 06/27/25 | 516 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 06/27/25 | 518 | Taylor, Evan R |  | 565.34
PR | 995 | 06/27/25 | 521 | Young, Joshua S |  | 159.46
PR | 995 | 06/27/25 | 522 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 07/03/25 | 10 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 07/03/25 | 14 | Amaya Gonzalez, Edilberto A |  | 554.47
PR | 995 | 07/03/25 | 18 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 07/03/25 | 20 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 07/03/25 | 21 | Carmona, Raul O |  | 960.36
PR | 995 | 07/03/25 | 22 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 07/03/25 | 23 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 07/03/25 | 24 | Cortes Mendiola, Victor H |  | 608.83
PR | 995 | 07/03/25 | 24 | Cortes Mendiola, Victor H |  | 550.85
PR | 995 | 07/03/25 | 27 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 07/03/25 | 33 | Gerard, Jordan E |  | 27.18
PR | 995 | 07/03/25 | 34 | Gerard, Mitchell J |  | 884.26
PR | 995 | 07/03/25 | 35 | Gochez Molina, Douglas O |  | 304.42
PR | 995 | 07/03/25 | 40 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 07/03/25 | 41 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 07/03/25 | 45 | McCabe, Thomas C |  | 797.28
PR | 995 | 07/03/25 | 47 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 07/03/25 | 48 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 07/03/25 | 52 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 07/03/25 | 55 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 07/03/25 | 57 | Ross, Kelli M |  | 739.3
PR | 995 | 07/03/25 | 58 | Silva Morales, Jair J |  | 492.86
PR | 995 | 07/03/25 | 59 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 07/03/25 | 61 | Taylor, Evan R |  | 565.34
PR | 995 | 07/03/25 | 63 | Waites, Thaddeus Z |  | 663.19
PR | 995 | 07/03/25 | 66 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 07/11/25 | 135 | Cruz Reyes, Jose |  | 575.76
PR | 995 | 07/11/25 | 139 | Amaya Gonzalez, Edilberto A |  | 716.19
PR | 995 | 07/11/25 | 143 | Balderas Ortiz, Ricardo I |  | 617.89
PR | 995 | 07/11/25 | 144 | Barnhart, Joseph N |  | 92.41
PR | 995 | 07/11/25 | 145 | Bautista Quintero, Isidoro |  | 337.03
PR | 995 | 07/11/25 | 146 | Carmona, Raul O |  | 744.28
PR | 995 | 07/11/25 | 147 | Castro Hernandez, Jose A |  | 758.32
PR | 995 | 07/11/25 | 148 | Cornejo Orellana, Carlos E |  | 364.67
PR | 995 | 07/11/25 | 149 | Cortes Mendiola, Victor H |  | 724.8
PR | 995 | 07/11/25 | 149 | Cortes Mendiola, Victor H |  | 173.95
PR | 995 | 07/11/25 | 152 | Cruz Guzman, Joel A |  | 716.19
PR | 995 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 46.89
PR | 995 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 07/11/25 | 158 | Gerard, Jordan E |  | 27.18
PR | 995 | 07/11/25 | 159 | Gerard, Mitchell J |  | 828.99
PR | 995 | 07/11/25 | 164 | Jimenez Alvarenga, Gerson M |  | 547.68
PR | 995 | 07/11/25 | 165 | Lima Romero, Melvin A |  | 458.44
PR | 995 | 07/11/25 | 169 | McCabe, Thomas C |  | 617.89
PR | 995 | 07/11/25 | 171 | Mendoza Morales, Jesus A |  | 575.76
PR | 995 | 07/11/25 | 172 | Merino Martinez, Humberto |  | 393.2
PR | 995 | 07/11/25 | 176 | Portillo Soriano, Walter A |  | 491.51
PR | 995 | 07/11/25 | 179 | Rodriguez Arevalos, Christian |  | 531.37
PR | 995 | 07/11/25 | 180 | Romero Garza, Jesus I |  | 29.9
PR | 995 | 07/11/25 | 181 | Ross, Kelli M |  | 531.37
PR | 995 | 07/11/25 | 182 | Silva Morales, Jair J |  | 477.46
PR | 995 | 07/11/25 | 183 | Suniga Aviles, Kelvin A |  | 337.03
PR | 995 | 07/11/25 | 185 | Taylor, Evan R |  | 353.34
PR | 995 | 07/11/25 | 187 | Waites, Thaddeus Z |  | 221.06
PR | 995 | 07/11/25 | 190 | Zuniga Avilez, Eduar A |  | 337.03
PR | 995 | 07/18/25 | 303 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 07/18/25 | 306 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 07/18/25 | 310 | Balderas Ortiz, Ricardo I |  | 797.28
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 154.02
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 30.8
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 15.4
PR | 995 | 07/18/25 | 311 | Barnhart, Joseph N |  | 77.01
PR | 995 | 07/18/25 | 312 | Bautista Quintero, Isidoro |  | 347.9
PR | 995 | 07/18/25 | 313 | Carmona, Raul O |  | 960.36
PR | 995 | 07/18/25 | 314 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 07/18/25 | 315 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 07/18/25 | 316 | Cortes Mendiola, Victor H |  | 1043.71
PR | 995 | 07/18/25 | 316 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 07/18/25 | 319 | Cruz Guzman, Joel A |  | 554.47
PR | 995 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 07/18/25 | 325 | Gerard, Jordan E |  | 54.36
PR | 995 | 07/18/25 | 326 | Gerard, Mitchell J |  | 1050.05
PR | 995 | 07/18/25 | 331 | Jimenez Alvarenga, Gerson M |  | 706.68
PR | 995 | 07/18/25 | 332 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 07/18/25 | 336 | McCabe, Thomas C |  | 797.28
PR | 995 | 07/18/25 | 338 | Mendoza Morales, Jesus A |  | 742.92
PR | 995 | 07/18/25 | 339 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 07/18/25 | 343 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 07/18/25 | 346 | Rodriguez Arevalos, Christian |  | 924.12
PR | 995 | 07/18/25 | 347 | Romero Garza, Jesus I |  | 134.54
PR | 995 | 07/18/25 | 348 | Ross, Kelli M |  | 554.47
PR | 995 | 07/18/25 | 349 | Silva Morales, Jair J |  | 616.08
PR | 995 | 07/18/25 | 350 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 07/18/25 | 352 | Taylor, Evan R |  | 565.34
PR | 995 | 07/18/25 | 354 | Waites, Thaddeus Z |  | 1077.69
PR | 995 | 07/18/25 | 357 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 07/25/25 | 470 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 07/25/25 | 474 | Amaya Gonzalez, Edilberto A |  | 739.3
PR | 995 | 07/25/25 | 478 | Balderas Ortiz, Ricardo I |  | 159.46
PR | 995 | 07/25/25 | 480 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 07/25/25 | 481 | Carmona, Raul O |  | 768.29
PR | 995 | 07/25/25 | 482 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 07/25/25 | 483 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 07/25/25 | 484 | Cortes Mendiola, Victor H |  | 840.77
PR | 995 | 07/25/25 | 484 | Cortes Mendiola, Victor H |  | 318.91
PR | 995 | 07/25/25 | 487 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 109.4
PR | 995 | 07/25/25 | 493 | Gerard, Jordan E |  | 163.08
PR | 995 | 07/25/25 | 494 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 07/25/25 | 499 | Jimenez Alvarenga, Gerson M |  | 282.67
PR | 995 | 07/25/25 | 500 | Lima Romero, Melvin A |  | 757.42
PR | 995 | 07/25/25 | 504 | McCabe, Thomas C |  | 797.28
PR | 995 | 07/25/25 | 506 | Mendoza Morales, Jesus A |  | 724.35
PR | 995 | 07/25/25 | 506 | Mendoza Morales, Jesus A |  | 18.57
PR | 995 | 07/25/25 | 507 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 07/25/25 | 511 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 07/25/25 | 514 | Rodriguez Arevalos, Christian |  | 184.82
PR | 995 | 07/25/25 | 516 | Ross, Kelli M |  | 554.47
PR | 995 | 07/25/25 | 517 | Silva Morales, Jair J |  | 616.08
PR | 995 | 07/25/25 | 518 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 07/25/25 | 520 | Waites, Thaddeus Z |  | 331.6
PR | 995 | 07/25/25 | 523 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 08/01/25 | 3 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 08/01/25 | 7 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 154.02
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 123.22
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/01/25 | 13 | Bautista Quintero, Isidoro |  | 260.93
PR | 995 | 08/01/25 | 13 | Bautista Quintero, Isidoro |  | 173.95
PR | 995 | 08/01/25 | 14 | Carmona, Raul O |  | 960.36
PR | 995 | 08/01/25 | 15 | Castro Hernandez, Jose A |  | 782.78
PR | 995 | 08/01/25 | 16 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 956.74
PR | 995 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 08/01/25 | 20 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 08/01/25 | 25 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 08/01/25 | 26 | Gerard, Jordan E |  | 81.54
PR | 995 | 08/01/25 | 27 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 08/01/25 | 33 | Lima Romero, Melvin A |  | 637.82
PR | 995 | 08/01/25 | 37 | McCabe, Thomas C |  | 637.82
PR | 995 | 08/01/25 | 40 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 08/01/25 | 44 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 08/01/25 | 49 | Ross, Kelli M |  | 554.47
PR | 995 | 08/01/25 | 50 | Silva Morales, Jair J |  | 616.08
PR | 995 | 08/01/25 | 51 | Suniga Aviles, Kelvin A |  | 260.93
PR | 995 | 08/01/25 | 51 | Suniga Aviles, Kelvin A |  | 173.95
PR | 995 | 08/01/25 | 53 | Taylor, Evan R |  | 188.45
PR | 995 | 08/01/25 | 56 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 08/08/25 | 134 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 08/08/25 | 138 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 08/08/25 | 143 | Barnhart, Joseph N |  | 123.22
PR | 995 | 08/08/25 | 143 | Barnhart, Joseph N |  | 154.02
PR | 995 | 08/08/25 | 143 | Barnhart, Joseph N |  | 92.41
PR | 995 | 08/08/25 | 144 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 08/08/25 | 145 | Carmona, Raul O |  | 960.36
PR | 995 | 08/08/25 | 146 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 08/08/25 | 147 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 869.76
PR | 995 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 08/08/25 | 151 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 08/08/25 | 156 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 08/08/25 | 156 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 08/08/25 | 158 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 159.46
PR | 995 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 318.91
PR | 995 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 318.91
PR | 995 | 08/08/25 | 168 | McCabe, Thomas C |  | 797.28
PR | 995 | 08/08/25 | 171 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 08/08/25 | 175 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 08/08/25 | 180 | Ross, Kelli M |  | 554.47
PR | 995 | 08/08/25 | 181 | Silva Morales, Jair J |  | 616.08
PR | 995 | 08/08/25 | 182 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 08/08/25 | 184 | Taylor, Evan R |  | 376.9
PR | 995 | 08/08/25 | 187 | Zuniga Avilez, Eduar A |  | 260.93
PR | 995 | 08/08/25 | 187 | Zuniga Avilez, Eduar A |  | 173.95
PR | 995 | 08/15/25 | 260 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 08/15/25 | 263 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 08/15/25 | 268 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/15/25 | 269 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 08/15/25 | 270 | Carmona, Raul O |  | 960.36
PR | 995 | 08/15/25 | 271 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 08/15/25 | 272 | Cornejo Orellana, Carlos E |  | 507.36
PR | 995 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 869.76
PR | 995 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 08/15/25 | 276 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 08/15/25 | 281 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 08/15/25 | 281 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 08/15/25 | 282 | Gerard, Jordan E |  | 27.18
PR | 995 | 08/15/25 | 283 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 08/15/25 | 289 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 08/15/25 | 293 | McCabe, Thomas C |  | 478.37
PR | 995 | 08/15/25 | 293 | McCabe, Thomas C |  | 159.46
PR | 995 | 08/15/25 | 296 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 08/15/25 | 300 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 08/15/25 | 305 | Ross, Kelli M |  | 739.3
PR | 995 | 08/15/25 | 306 | Silva Morales, Jair J |  | 492.86
PR | 995 | 08/15/25 | 307 | Suniga Aviles, Kelvin A |  | 347.9
PR | 995 | 08/15/25 | 309 | Taylor, Evan R |  | 376.9
PR | 995 | 08/15/25 | 312 | Zuniga Avilez, Eduar A |  | 347.9
PR | 995 | 08/22/25 | 362 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 08/22/25 | 366 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 154.02
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 154.02
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 30.8
PR | 995 | 08/22/25 | 371 | Barnhart, Joseph N |  | 30.8
PR | 995 | 08/22/25 | 372 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 08/22/25 | 373 | Carmona, Raul O |  | 960.36
PR | 995 | 08/22/25 | 374 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 08/22/25 | 375 | Cornejo Orellana, Carlos E |  | 634.2
PR | 995 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 985.73
PR | 995 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 28.99
PR | 995 | 08/22/25 | 379 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 93.77
PR | 995 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 08/22/25 | 386 | Gerard, Jordan E |  | 135.9
PR | 995 | 08/22/25 | 387 | Gerard, Mitchell J |  | 884.26
PR | 995 | 08/22/25 | 393 | Lima Romero, Melvin A |  | 637.82
PR | 995 | 08/22/25 | 397 | McCabe, Thomas C |  | 797.28
PR | 995 | 08/22/25 | 400 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 08/22/25 | 404 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 08/22/25 | 409 | Ross, Kelli M |  | 739.3
PR | 995 | 08/22/25 | 410 | Silva Morales, Jair J |  | 616.08
PR | 995 | 08/22/25 | 411 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 08/22/25 | 413 | Taylor, Evan R |  | 376.9
PR | 995 | 08/22/25 | 416 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 08/29/25 | 525 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 08/29/25 | 529 | Amaya Gonzalez, Edilberto A |  | 831.71
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 61.61
PR | 995 | 08/29/25 | 535 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 08/29/25 | 536 | Carmona, Raul O |  | 960.36
PR | 995 | 08/29/25 | 538 | Cornejo Orellana, Carlos E |  | 253.68
PR | 995 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 898.75
PR | 995 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 202.94
PR | 995 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 08/29/25 | 542 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 08/29/25 | 548 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 08/29/25 | 548 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 08/29/25 | 550 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 08/29/25 | 556 | Lima Romero, Melvin A |  | 797.28
PR | 995 | 08/29/25 | 560 | McCabe, Thomas C |  | 318.91
PR | 995 | 08/29/25 | 563 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 08/29/25 | 567 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 08/29/25 | 573 | Silva Morales, Jair J |  | 616.08
PR | 995 | 08/29/25 | 574 | Suniga Aviles, Kelvin A |  | 434.88
PR | 995 | 08/29/25 | 576 | Taylor, Evan R |  | 376.9
PR | 995 | 08/29/25 | 579 | Zuniga Avilez, Eduar A |  | 434.88
PR | 995 | 09/05/25 | 10 | Cruz Reyes, Jose |  | 594.34
PR | 995 | 09/05/25 | 14 | Amaya Gonzalez, Edilberto A |  | 739.3
PR | 995 | 09/05/25 | 19 | Barnhart, Joseph N |  | 123.22
PR | 995 | 09/05/25 | 19 | Barnhart, Joseph N |  | 61.61
PR | 995 | 09/05/25 | 19 | Barnhart, Joseph N |  | 30.8
PR | 995 | 09/05/25 | 20 | Bautista Quintero, Isidoro |  | 173.95
PR | 995 | 09/05/25 | 20 | Bautista Quintero, Isidoro |  | 173.95
PR | 995 | 09/05/25 | 21 | Carmona, Raul O |  | 768.29
PR | 995 | 09/05/25 | 22 | Castro Hernandez, Jose A |  | 587.09
PR | 995 | 09/05/25 | 24 | Cortes Mendiola, Victor H |  | 782.78
PR | 995 | 09/05/25 | 24 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 09/05/25 | 27 | Cruz Guzman, Joel A |  | 739.3
PR | 995 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 09/05/25 | 34 | Gerard, Jordan E |  | 190.26
PR | 995 | 09/05/25 | 35 | Gerard, Mitchell J |  | 828.99
PR | 995 | 09/05/25 | 41 | Lima Romero, Melvin A |  | 318.91
PR | 995 | 09/05/25 | 45 | McCabe, Thomas C |  | 478.37
PR | 995 | 09/05/25 | 48 | Merino Martinez, Humberto |  | 405.89
PR | 995 | 09/05/25 | 52 | Portillo Soriano, Walter A |  | 507.36
PR | 995 | 09/05/25 | 58 | Silva Morales, Jair J |  | 492.86
PR | 995 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 86.98
PR | 995 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 86.98
PR | 995 | 09/05/25 | 63 | Zuniga Avilez, Eduar A |  | 173.95
PR | 995 | 09/12/25 | 108 | Cruz Reyes, Jose |  | 742.92
PR | 995 | 09/12/25 | 111 | Amaya Gonzalez, Edilberto A |  | 924.12
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 308.04
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 30.8
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 184.82
PR | 995 | 09/12/25 | 117 | Bautista Quintero, Isidoro |  | 434.88
PR | 995 | 09/12/25 | 118 | Carmona, Raul O |  | 960.36
PR | 995 | 09/12/25 | 119 | Castro Hernandez, Jose A |  | 978.48
PR | 995 | 09/12/25 | 121 | Cortes Mendiola, Victor H |  | 695.81
PR | 995 | 09/12/25 | 124 | Cruz Guzman, Joel A |  | 924.12
PR | 995 | 09/12/25 | 130 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 09/12/25 | 131 | Gerard, Jordan E |  | 163.08
PR | 995 | 09/12/25 | 132 | Gerard, Mitchell J |  | 1105.32
PR | 995 | 09/12/25 | 142 | McCabe, Thomas C |  | 797.28
PR | 995 | 09/12/25 | 145 | Merino Martinez, Humberto |  | 507.36
PR | 995 | 09/12/25 | 149 | Portillo Soriano, Walter A |  | 634.2
PR | 995 | 09/12/25 | 155 | Silva Morales, Jair J |  | 616.08
PR | 995 | 09/19/25 | 238 | Barnhart, Thomas L |  | 467.5
PR | 995 | 09/19/25 | 240 | Cruz Reyes, Jose |  | 687.2
PR | 995 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A |  | 554.47
PR | 995 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A |  | 69.31
PR | 995 | 09/19/25 | 248 | Barnhart, Joseph N |  | 61.61
PR | 995 | 09/19/25 | 248 | Barnhart, Joseph N |  | 61.61
PR | 995 | 09/19/25 | 248 | Barnhart, Joseph N |  | 30.8
PR | 995 | 09/19/25 | 249 | Bautista Quintero, Isidoro |  | 260.93
PR | 995 | 09/19/25 | 249 | Bautista Quintero, Isidoro |  | 141.34
PR | 995 | 09/19/25 | 250 | Carmona, Raul O |  | 888.33
PR | 995 | 09/19/25 | 251 | Castro Hernandez, Jose A |  | 905.09
PR | 995 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 927.74
PR | 995 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 115.97
PR | 995 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 28.99
PR | 995 | 09/19/25 | 256 | Cruz Guzman, Joel A |  | 854.81
PR | 995 | 09/19/25 | 261 | Games, Jordan M |  | 120.05
PR | 995 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 62.51
PR | 995 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 09/19/25 | 263 | Gerard, Jordan E |  | 81.54
PR | 995 | 09/19/25 | 264 | Gerard, Mitchell J |  | 1022.42
PR | 995 | 09/19/25 | 274 | McCabe, Thomas C |  | 637.82
PR | 995 | 09/19/25 | 277 | Merino Martinez, Humberto |  | 469.31
PR | 995 | 09/19/25 | 281 | Portillo Soriano, Walter A |  | 586.64
PR | 995 | 09/19/25 | 287 | Silva Morales, Jair J |  | 569.87
PR | 995 | 09/26/25 | 408 | Barnhart, Thomas L |  | 155.83
PR | 995 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 86.64
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 63.53
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 23.1
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 30.8
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 46.21
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 38.51
PR | 995 | 09/26/25 | 419 | Barnhart, Joseph N |  | 138.62
PR | 995 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 09/26/25 | 421 | Carmona, Raul O |  | 192.07
PR | 995 | 09/26/25 | 421 | Carmona, Raul O |  | 192.07
PR | 995 | 09/26/25 | 421 | Carmona, Raul O |  | 192.07
PR | 995 | 09/26/25 | 421 | Carmona, Raul O |  | 192.07
PR | 995 | 09/26/25 | 421 | Carmona, Raul O |  | 192.07
PR | 995 | 09/26/25 | 422 | Castro Hernandez, Jose A |  | 195.7
PR | 995 | 09/26/25 | 422 | Castro Hernandez, Jose A |  | 195.7
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 108.72
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 79.73
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 09/26/25 | 427 | Cruz Guzman, Joel A |  | 184.82
PR | 995 | 09/26/25 | 427 | Cruz Guzman, Joel A |  | 184.82
PR | 995 | 09/26/25 | 434 | Gerard, Jordan E |  | 54.36
PR | 995 | 09/26/25 | 435 | Gerard, Mitchell J |  | 221.06
PR | 995 | 09/26/25 | 435 | Gerard, Mitchell J |  | 221.06
PR | 995 | 09/26/25 | 435 | Gerard, Mitchell J |  | 221.06
PR | 995 | 09/26/25 | 435 | Gerard, Mitchell J |  | 221.06
PR | 995 | 09/26/25 | 435 | Gerard, Mitchell J |  | 221.06
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 159.46
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 39.86
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 49.83
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 29.9
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 39.86
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 24.92
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 69.76
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 24.92
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 34.88
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 14.95
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 109.63
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 54.81
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 39.86
PR | 995 | 09/26/25 | 445 | McCabe, Thomas C |  | 34.88
PR | 995 | 09/26/25 | 448 | Merino Martinez, Humberto |  | 101.47
PR | 995 | 09/26/25 | 448 | Merino Martinez, Humberto |  | 101.47
PR | 995 | 09/26/25 | 452 | Portillo Soriano, Walter A |  | 126.84
PR | 995 | 09/26/25 | 452 | Portillo Soriano, Walter A |  | 126.84
PR | 995 | 09/26/25 | 458 | Silva Morales, Jair J |  | 123.22
PR | 995 | 09/26/25 | 458 | Silva Morales, Jair J |  | 123.22
PR | 995 | 09/26/25 | 458 | Silva Morales, Jair J |  | 123.22
PR | 995 | 09/26/25 | 458 | Silva Morales, Jair J |  | 123.22
PR | 995 | 09/26/25 | 458 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/03/25 | 4 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/03/25 | 4 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/03/25 | 4 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/03/25 | 4 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 109.74
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 75.08
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 38.51
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 38.51
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 92.41
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 46.21
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 30.8
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 146.32
PR | 995 | 10/03/25 | 15 | Barnhart, Joseph N |  | 7.7
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 48.92
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 38.05
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 24.46
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 46.21
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/03/25 | 17 | Carmona, Raul O |  | 192.07
PR | 995 | 10/03/25 | 17 | Carmona, Raul O |  | 192.07
PR | 995 | 10/03/25 | 17 | Carmona, Raul O |  | 192.07
PR | 995 | 10/03/25 | 17 | Carmona, Raul O |  | 192.07
PR | 995 | 10/03/25 | 17 | Carmona, Raul O |  | 192.07
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 137.71
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 21.74
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 50.74
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 224.69
PR | 995 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 10.87
PR | 995 | 10/03/25 | 27 | Eliassen, Cory H |  | 124.8
PR | 995 | 10/03/25 | 27 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/03/25 | 27 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/03/25 | 27 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/03/25 | 27 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 48.02
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 46.89
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/03/25 | 31 | Gerard, Jordan E |  | 20.39
PR | 995 | 10/03/25 | 32 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/03/25 | 32 | Gerard, Mitchell J |  | 179.61
PR | 995 | 10/03/25 | 32 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/03/25 | 32 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 159.46
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 59.8
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 9.97
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 29.9
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 24.92
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 59.8
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 54.81
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 49.83
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 114.61
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 29.9
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 44.85
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 84.71
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 14.95
PR | 995 | 10/03/25 | 42 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/03/25 | 55 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/03/25 | 55 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/03/25 | 55 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/03/25 | 55 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/03/25 | 55 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/10/25 | 156 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/10/25 | 156 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/10/25 | 156 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/10/25 | 156 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/10/25 | 156 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 30.8
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 100.11
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 184.82
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 46.21
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 30.8
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 15.4
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 15.4
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 92.41
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 15.4
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 84.71
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 38.51
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 24.46
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 32.62
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/10/25 | 169 | Carmona, Raul O |  | 192.07
PR | 995 | 10/10/25 | 169 | Carmona, Raul O |  | 192.07
PR | 995 | 10/10/25 | 169 | Carmona, Raul O |  | 192.07
PR | 995 | 10/10/25 | 169 | Carmona, Raul O |  | 192.07
PR | 995 | 10/10/25 | 169 | Carmona, Raul O |  | 192.07
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 65.23
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 86.98
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 181.2
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 21.74
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/10/25 | 179 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/10/25 | 179 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/10/25 | 179 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/10/25 | 179 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/10/25 | 179 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 6.91
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 207.25
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 227.97
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/10/25 | 184 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 101.47
PR | 995 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 101.47
PR | 995 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 101.47
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 79.73
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 9.97
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 69.76
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 74.75
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 4.98
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 79.73
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 89.69
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 104.64
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 4.98
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 4.98
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 44.85
PR | 995 | 10/10/25 | 195 | McCabe, Thomas C |  | 159.46
PR | 995 | 10/10/25 | 200 | Paco Leyva, Orlando |  | 13.82
PR | 995 | 10/10/25 | 208 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/10/25 | 208 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/10/25 | 208 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/10/25 | 208 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/17/25 | 360 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/17/25 | 360 | Barnhart, Thomas L |  | 136.35
PR | 995 | 10/17/25 | 360 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/17/25 | 360 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/17/25 | 360 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/17/25 | 363 | Da Cruz, Eduardo E |  | 83.35
PR | 995 | 10/17/25 | 363 | Da Cruz, Eduardo E |  | 28.65
PR | 995 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 46.21
PR | 995 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 103.96
PR | 995 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 103.96
PR | 995 | 10/17/25 | 369 | Araque, Mario W |  | 86.98
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 84.71
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 38.51
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 92.41
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 61.61
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 53.91
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 30.8
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 21.74
PR | 995 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 59.8
PR | 995 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 29.9
PR | 995 | 10/17/25 | 374 | Carmona, Raul O |  | 192.07
PR | 995 | 10/17/25 | 374 | Carmona, Raul O |  | 192.07
PR | 995 | 10/17/25 | 374 | Carmona, Raul O |  | 192.07
PR | 995 | 10/17/25 | 374 | Carmona, Raul O |  | 192.07
PR | 995 | 10/17/25 | 374 | Carmona, Raul O |  | 192.07
PR | 995 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 130.46
PR | 995 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 50.74
PR | 995 | 10/17/25 | 384 | Eliassen, Cory H |  | 68.86
PR | 995 | 10/17/25 | 384 | Eliassen, Cory H |  | 142.02
PR | 995 | 10/17/25 | 384 | Eliassen, Cory H |  | 142.02
PR | 995 | 10/17/25 | 384 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/17/25 | 384 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/17/25 | 386 | Games, Jordan M |  | 192.07
PR | 995 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/17/25 | 388 | Gerard, Jordan E |  | 27.18
PR | 995 | 10/17/25 | 388 | Gerard, Jordan E |  | 54.36
PR | 995 | 10/17/25 | 389 | Gerard, Mitchell J |  | 214.16
PR | 995 | 10/17/25 | 389 | Gerard, Mitchell J |  | 117.44
PR | 995 | 10/17/25 | 389 | Gerard, Mitchell J |  | 96.72
PR | 995 | 10/17/25 | 389 | Gerard, Mitchell J |  | 207.25
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 54.81
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 99.66
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 119.59
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 39.86
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 49.83
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 29.9
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 79.73
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 69.76
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 34.88
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 54.81
PR | 995 | 10/17/25 | 400 | McCabe, Thomas C |  | 159.46
PR | 995 | 10/17/25 | 413 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/17/25 | 413 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/17/25 | 413 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/17/25 | 413 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/17/25 | 413 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/24/25 | 493 | Barnhart, Thomas L |  | 146.09
PR | 995 | 10/24/25 | 493 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/24/25 | 493 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/24/25 | 493 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/24/25 | 493 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/24/25 | 496 | Da Cruz, Eduardo E |  | 49.49
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 92.41
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 61.61
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 123.22
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 69.31
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 61.61
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 77.01
PR | 995 | 10/24/25 | 505 | Barnhart, Joseph N |  | 169.42
PR | 995 | 10/24/25 | 506 | Bautista Quintero, Isidoro |  | 46.21
PR | 995 | 10/24/25 | 507 | Carmona, Raul O |  | 192.07
PR | 995 | 10/24/25 | 507 | Carmona, Raul O |  | 150.06
PR | 995 | 10/24/25 | 507 | Carmona, Raul O |  | 192.07
PR | 995 | 10/24/25 | 507 | Carmona, Raul O |  | 192.07
PR | 995 | 10/24/25 | 511 | Cortes Mendiola, Victor H |  | 159.46
PR | 995 | 10/24/25 | 516 | Draves, Steven W |  | 199.32
PR | 995 | 10/24/25 | 516 | Draves, Steven W |  | 199.32
PR | 995 | 10/24/25 | 516 | Draves, Steven W |  | 199.32
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 142.02
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 133.41
PR | 995 | 10/24/25 | 518 | Eliassen, Cory H |  | 6.46
PR | 995 | 10/24/25 | 520 | Games, Jordan M |  | 192.07
PR | 995 | 10/24/25 | 520 | Games, Jordan M |  | 150.06
PR | 995 | 10/24/25 | 520 | Games, Jordan M |  | 192.07
PR | 995 | 10/24/25 | 520 | Games, Jordan M |  | 192.07
PR | 995 | 10/24/25 | 522 | Gerard, Jordan E |  | 61.16
PR | 995 | 10/24/25 | 522 | Gerard, Jordan E |  | 54.36
PR | 995 | 10/24/25 | 522 | Gerard, Jordan E |  | 33.98
PR | 995 | 10/24/25 | 523 | Gerard, Mitchell J |  | 69.08
PR | 995 | 10/24/25 | 523 | Gerard, Mitchell J |  | 55.27
PR | 995 | 10/24/25 | 523 | Gerard, Mitchell J |  | 103.62
PR | 995 | 10/24/25 | 523 | Gerard, Mitchell J |  | 214.16
PR | 995 | 10/24/25 | 523 | Gerard, Mitchell J |  | 214.16
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 24.92
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 94.68
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 29.9
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 39.86
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 99.66
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 24.92
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 104.64
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 24.92
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 4.98
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 129.56
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 14.95
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 39.86
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 9.97
PR | 995 | 10/24/25 | 534 | McCabe, Thomas C |  | 74.75
PR | 995 | 10/24/25 | 548 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/24/25 | 548 | Silva Morales, Jair J |  | 73.16
PR | 995 | 10/31/25 | 660 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/31/25 | 660 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/31/25 | 660 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/31/25 | 660 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/31/25 | 660 | Barnhart, Thomas L |  | 155.83
PR | 995 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 130.01
PR | 995 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 150.17
PR | 995 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 184.82
PR | 995 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 46.21
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 30.8
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 69.31
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 92.41
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 38.51
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 69.31
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 23.1
PR | 995 | 10/31/25 | 670 | Barnhart, Joseph N |  | 53.91
PR | 995 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 29.9
PR | 995 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 86.98
PR | 995 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 21.74
PR | 995 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 57.08
PR | 995 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 21.74
PR | 995 | 10/31/25 | 672 | Carmona, Raul O |  | 192.07
PR | 995 | 10/31/25 | 672 | Carmona, Raul O |  | 198.07
PR | 995 | 10/31/25 | 672 | Carmona, Raul O |  | 192.07
PR | 995 | 10/31/25 | 672 | Carmona, Raul O |  | 186.07
PR | 995 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 65.23
PR | 995 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 231.94
PR | 995 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 57.98
PR | 995 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 144.96
PR | 995 | 10/31/25 | 680 | Da Cruz, Eduardo E |  | 18.23
PR | 995 | 10/31/25 | 680 | Da Cruz, Eduardo E |  | 85.96
PR | 995 | 10/31/25 | 682 | Draves, Steven W |  | 199.32
PR | 995 | 10/31/25 | 682 | Draves, Steven W |  | 168.18
PR | 995 | 10/31/25 | 682 | Draves, Steven W |  | 199.32
PR | 995 | 10/31/25 | 682 | Draves, Steven W |  | 199.32
PR | 995 | 10/31/25 | 682 | Draves, Steven W |  | 199.32
PR | 995 | 10/31/25 | 684 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/31/25 | 684 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/31/25 | 684 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/31/25 | 684 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/31/25 | 684 | Eliassen, Cory H |  | 137.71
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 192.07
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 186.07
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 144.05
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 54.02
PR | 995 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 95.13
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 33.98
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 40.77
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 20.39
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 20.39
PR | 995 | 10/31/25 | 688 | Gerard, Jordan E |  | 20.39
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 117.44
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 96.72
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 165.8
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 221.06
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 207.25
PR | 995 | 10/31/25 | 689 | Gerard, Mitchell J |  | 207.25
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 154.47
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 144.51
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 69.76
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 9.97
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 84.71
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 49.83
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 19.93
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 74.75
PR | 995 | 10/31/25 | 702 | McCabe, Thomas C |  | 14.95
PR | 995 | 10/31/25 | 715 | Silva Morales, Jair J |  | 38.51
PR | 995 | 10/31/25 | 715 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/31/25 | 715 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/31/25 | 715 | Silva Morales, Jair J |  | 123.22
PR | 995 | 10/31/25 | 715 | Silva Morales, Jair J |  | 123.22
PR | 995 | 11/07/25 | 49 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/07/25 | 49 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/07/25 | 49 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/07/25 | 49 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/07/25 | 49 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 30.8
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 46.21
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 15.4
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 46.21
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 15.4
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 53.91
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 30.8
PR | 995 | 11/07/25 | 61 | Carmona, Raul O |  | 30.01
PR | 995 | 11/07/25 | 61 | Carmona, Raul O |  | 192.07
PR | 995 | 11/07/25 | 71 | Draves, Steven W |  | 199.32
PR | 995 | 11/07/25 | 71 | Draves, Steven W |  | 186.86
PR | 995 | 11/07/25 | 71 | Draves, Steven W |  | 199.32
PR | 995 | 11/07/25 | 71 | Draves, Steven W |  | 199.32
PR | 995 | 11/07/25 | 71 | Draves, Steven W |  | 199.32
PR | 995 | 11/07/25 | 73 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/07/25 | 73 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/07/25 | 73 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/07/25 | 73 | Eliassen, Cory H |  | 73.16
PR | 995 | 11/07/25 | 73 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/07/25 | 75 | Gerard, Jeffrey S |  | 15.63
PR | 995 | 11/07/25 | 75 | Gerard, Jeffrey S |  | 15.63
PR | 995 | 11/07/25 | 76 | Gerard, Jordan E |  | 27.18
PR | 995 | 11/07/25 | 76 | Gerard, Jordan E |  | 47.57
PR | 995 | 11/07/25 | 76 | Gerard, Jordan E |  | 95.13
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 117.44
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 27.63
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 27.63
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 20.72
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 20.72
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 165.8
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 6.91
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 172.71
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 13.82
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 27.63
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 20.72
PR | 995 | 11/07/25 | 77 | Gerard, Mitchell J |  | 151.98
PR | 995 | 11/07/25 | 103 | Silva Morales, Jair J |  | 19.25
PR | 995 | 11/14/25 | 209 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/14/25 | 209 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/14/25 | 209 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/14/25 | 209 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/14/25 | 209 | Barnhart, Thomas L |  | 155.83
PR | 995 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 148.58
PR | 995 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 143.94
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 115.52
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 130.92
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 23.1
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 7.7
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 7.7
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 61.61
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 84.71
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 15.4
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 38.51
PR | 995 | 11/14/25 | 221 | Carmona, Raul O |  | 192.07
PR | 995 | 11/14/25 | 221 | Carmona, Raul O |  | 192.07
PR | 995 | 11/14/25 | 221 | Carmona, Raul O |  | 192.07
PR | 995 | 11/14/25 | 221 | Carmona, Raul O |  | 192.07
PR | 995 | 11/14/25 | 221 | Carmona, Raul O |  | 192.07
PR | 995 | 11/14/25 | 231 | Draves, Steven W |  | 199.32
PR | 995 | 11/14/25 | 231 | Draves, Steven W |  | 199.32
PR | 995 | 11/14/25 | 231 | Draves, Steven W |  | 199.32
PR | 995 | 11/14/25 | 231 | Draves, Steven W |  | 199.32
PR | 995 | 11/14/25 | 231 | Draves, Steven W |  | 199.32
PR | 995 | 11/14/25 | 233 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/14/25 | 233 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/14/25 | 233 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/14/25 | 233 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/14/25 | 233 | Eliassen, Cory H |  | 137.71
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 15.63
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 15.63
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 11/14/25 | 236 | Gerard, Jordan E |  | 33.98
PR | 995 | 11/14/25 | 236 | Gerard, Jordan E |  | 81.54
PR | 995 | 11/14/25 | 236 | Gerard, Jordan E |  | 176.67
PR | 995 | 11/14/25 | 236 | Gerard, Jordan E |  | 61.16
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 55.27
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 69.08
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 13.82
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 20.72
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 117.44
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 27.63
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 69.08
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 48.36
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 110.53
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 62.17
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 34.54
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 55.27
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 13.82
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 20.72
PR | 995 | 11/14/25 | 237 | Gerard, Mitchell J |  | 214.16
PR | 995 | 11/14/25 | 263 | Silva Morales, Jair J |  | 84.71
PR | 995 | 11/21/25 | 325 | Barnhart, Thomas L |  | 139.97
PR | 995 | 11/21/25 | 325 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/21/25 | 325 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/21/25 | 325 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/21/25 | 325 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 124.56
PR | 995 | 11/21/25 | 338 | Carmona, Raul O |  | 184.02
PR | 995 | 11/21/25 | 338 | Carmona, Raul O |  | 184.02
PR | 995 | 11/21/25 | 338 | Carmona, Raul O |  | 184.02
PR | 995 | 11/21/25 | 338 | Carmona, Raul O |  | 184.02
PR | 995 | 11/21/25 | 338 | Carmona, Raul O |  | 184.02
PR | 995 | 11/21/25 | 342 | Cortes Mendiola, Victor H |  | 138.88
PR | 995 | 11/21/25 | 348 | Draves, Steven W |  | 190.96
PR | 995 | 11/21/25 | 348 | Draves, Steven W |  | 190.96
PR | 995 | 11/21/25 | 348 | Draves, Steven W |  | 190.96
PR | 995 | 11/21/25 | 350 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/21/25 | 350 | Eliassen, Cory H |  | 136.06
PR | 995 | 11/21/25 | 350 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/21/25 | 350 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 71.61
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 58.59
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 84.63
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 59.57
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 33.09
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 52.95
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 33.09
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 112.51
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 13.24
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 26.47
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 125.75
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 13.24
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 26.47
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 6.62
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 59.57
PR | 995 | 11/21/25 | 354 | Gerard, Mitchell J |  | 211.79
PR | 995 | 11/21/25 | 379 | Silva Morales, Jair J |  | 118.05
PR | 995 | 11/21/25 | 379 | Silva Morales, Jair J |  | 118.05
PR | 995 | 11/21/25 | 379 | Silva Morales, Jair J |  | 118.05
PR | 995 | 11/21/25 | 379 | Silva Morales, Jair J |  | 51.65
PR | 995 | 11/28/25 | 509 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/28/25 | 509 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/28/25 | 509 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/28/25 | 509 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/28/25 | 509 | Barnhart, Thomas L |  | 149.3
PR | 995 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 51.65
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 7.38
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 14.76
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 110.67
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 7.38
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 29.51
PR | 995 | 11/28/25 | 521 | Carmona, Raul O |  | 184.02
PR | 995 | 11/28/25 | 521 | Carmona, Raul O |  | 184.02
PR | 995 | 11/28/25 | 521 | Carmona, Raul O |  | 184.02
PR | 995 | 11/28/25 | 521 | Carmona, Raul O |  | 184.02
PR | 995 | 11/28/25 | 521 | Carmona, Raul O |  | 184.02
PR | 995 | 11/28/25 | 531 | Draves, Steven W |  | 196.93
PR | 995 | 11/28/25 | 531 | Draves, Steven W |  | 179.03
PR | 995 | 11/28/25 | 531 | Draves, Steven W |  | 190.96
PR | 995 | 11/28/25 | 531 | Draves, Steven W |  | 190.96
PR | 995 | 11/28/25 | 531 | Draves, Steven W |  | 131.29
PR | 995 | 11/28/25 | 533 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/28/25 | 533 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/28/25 | 533 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/28/25 | 533 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/28/25 | 533 | Eliassen, Cory H |  | 131.94
PR | 995 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 11/28/25 | 537 | Gerard, Jordan E |  | 19.53
PR | 995 | 11/28/25 | 537 | Gerard, Jordan E |  | 97.65
PR | 995 | 11/28/25 | 537 | Gerard, Jordan E |  | 39.06
PR | 995 | 11/28/25 | 537 | Gerard, Jordan E |  | 45.57
PR | 995 | 11/28/25 | 537 | Gerard, Jordan E |  | 32.55
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 13.24
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 158.84
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 13.24
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 59.57
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 6.62
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 79.42
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 72.8
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 86.04
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 52.95
PR | 995 | 11/28/25 | 538 | Gerard, Mitchell J |  | 145.61
PR | 995 | 11/28/25 | 563 | Silva Morales, Jair J |  | 36.89
PR | 995 | 12/05/25 | 35 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/05/25 | 35 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/05/25 | 35 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/05/25 | 45 | Barnhart, Joseph N |  | 14.76
PR | 995 | 12/05/25 | 45 | Barnhart, Joseph N |  | 147.56
PR | 995 | 12/05/25 | 46 | Bautista Quintero, Isidoro |  | 10.42
PR | 995 | 12/05/25 | 47 | Carmona, Raul O |  | 184.02
PR | 995 | 12/05/25 | 47 | Carmona, Raul O |  | 184.02
PR | 995 | 12/05/25 | 47 | Carmona, Raul O |  | 184.02
PR | 995 | 12/05/25 | 57 | Draves, Steven W |  | 190.96
PR | 995 | 12/05/25 | 57 | Draves, Steven W |  | 202.9
PR | 995 | 12/05/25 | 57 | Draves, Steven W |  | 190.96
PR | 995 | 12/05/25 | 59 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/05/25 | 59 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/05/25 | 59 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/05/25 | 63 | Gerard, Jordan E |  | 32.55
PR | 995 | 12/05/25 | 63 | Gerard, Jordan E |  | 65.1
PR | 995 | 12/05/25 | 63 | Gerard, Jordan E |  | 52.08
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 59.57
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 19.86
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 86.04
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 6.62
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 39.71
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 26.47
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 26.47
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 33.09
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 46.33
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 13.24
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 125.75
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 52.95
PR | 995 | 12/05/25 | 64 | Gerard, Mitchell J |  | 19.86
PR | 995 | 12/12/25 | 172 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/12/25 | 172 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/12/25 | 172 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/12/25 | 172 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/12/25 | 172 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 88.97
PR | 995 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 59.02
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 51.65
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 29.51
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 29.51
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 36.89
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 162.32
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 14.76
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 22.13
PR | 995 | 12/12/25 | 184 | Carmona, Raul O |  | 184.02
PR | 995 | 12/12/25 | 184 | Carmona, Raul O |  | 184.02
PR | 995 | 12/12/25 | 184 | Carmona, Raul O |  | 184.02
PR | 995 | 12/12/25 | 184 | Carmona, Raul O |  | 184.02
PR | 995 | 12/12/25 | 184 | Carmona, Raul O |  | 184.02
PR | 995 | 12/12/25 | 194 | Draves, Steven W |  | 190.96
PR | 995 | 12/12/25 | 194 | Draves, Steven W |  | 190.96
PR | 995 | 12/12/25 | 194 | Draves, Steven W |  | 190.96
PR | 995 | 12/12/25 | 194 | Draves, Steven W |  | 190.96
PR | 995 | 12/12/25 | 194 | Draves, Steven W |  | 190.96
PR | 995 | 12/12/25 | 196 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/12/25 | 196 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/12/25 | 196 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/12/25 | 196 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/12/25 | 196 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 12/12/25 | 200 | Gerard, Jordan E |  | 52.08
PR | 995 | 12/12/25 | 200 | Gerard, Jordan E |  | 71.61
PR | 995 | 12/12/25 | 200 | Gerard, Jordan E |  | 123.69
PR | 995 | 12/12/25 | 200 | Gerard, Jordan E |  | 136.71
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 52.95
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 13.24
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 6.62
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 99.28
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 138.99
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 72.8
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 92.66
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 59.57
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 59.57
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 26.47
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 86.04
PR | 995 | 12/12/25 | 201 | Gerard, Mitchell J |  | 99.28
PR | 995 | 12/19/25 | 313 | Barnhart, Thomas L |  | 139.97
PR | 995 | 12/19/25 | 313 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/19/25 | 313 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/19/25 | 313 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/19/25 | 313 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 36.89
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 44.27
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 14.76
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 14.76
PR | 995 | 12/19/25 | 325 | Carmona, Raul O |  | 184.02
PR | 995 | 12/19/25 | 325 | Carmona, Raul O |  | 184.02
PR | 995 | 12/19/25 | 325 | Carmona, Raul O |  | 184.02
PR | 995 | 12/19/25 | 335 | Draves, Steven W |  | 131.29
PR | 995 | 12/19/25 | 335 | Draves, Steven W |  | 190.96
PR | 995 | 12/19/25 | 335 | Draves, Steven W |  | 190.96
PR | 995 | 12/19/25 | 335 | Draves, Steven W |  | 190.96
PR | 995 | 12/19/25 | 335 | Draves, Steven W |  | 190.96
PR | 995 | 12/19/25 | 337 | Eliassen, Cory H |  | 127.81
PR | 995 | 12/19/25 | 337 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/19/25 | 337 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/19/25 | 337 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/19/25 | 340 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 12/19/25 | 341 | Gerard, Jordan E |  | 45.57
PR | 995 | 12/19/25 | 341 | Gerard, Jordan E |  | 65.1
PR | 995 | 12/19/25 | 341 | Gerard, Jordan E |  | 65.1
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 39.71
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 33.09
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 39.71
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 79.42
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 13.24
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 119.13
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 46.33
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 165.46
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 191.94
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 52.95
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 13.24
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 86.04
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 19.86
PR | 995 | 12/19/25 | 342 | Gerard, Mitchell J |  | 39.71
PR | 995 | 12/26/25 | 501 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/26/25 | 501 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/26/25 | 501 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/26/25 | 501 | Barnhart, Thomas L |  | 149.3
PR | 995 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 66.4
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 14.76
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 95.91
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 7.38
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 59.02
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 29.51
PR | 995 | 12/26/25 | 523 | Draves, Steven W |  | 179.03
PR | 995 | 12/26/25 | 523 | Draves, Steven W |  | 190.96
PR | 995 | 12/26/25 | 523 | Draves, Steven W |  | 125.32
PR | 995 | 12/26/25 | 525 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/26/25 | 525 | Eliassen, Cory H |  | 127.81
PR | 995 | 12/26/25 | 525 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/26/25 | 525 | Eliassen, Cory H |  | 131.94
PR | 995 | 12/26/25 | 528 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 12/26/25 | 529 | Gerard, Jordan E |  | 71.61
PR | 995 | 12/26/25 | 529 | Gerard, Jordan E |  | 78.12
PR | 995 | 12/26/25 | 529 | Gerard, Jordan E |  | 52.08
PR | 995 | 12/26/25 | 530 | Gerard, Mitchell J |  | 172.08
PR | 995 | 12/26/25 | 530 | Gerard, Mitchell J |  | 191.94
PR | 995 | 12/26/25 | 530 | Gerard, Mitchell J |  | 205.17
PR | 995 | 01/02/26 | 5 | Barnhart, Thomas L |  | 149.3
PR | 995 | 01/02/26 | 5 | Barnhart, Thomas L |  | 149.3
PR | 995 | 01/02/26 | 5 | Barnhart, Thomas L |  | 102.64
PR | 995 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 142.35
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 7.38
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 14.76
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 66.4
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 22.13
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 14.76
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 29.51
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 22.13
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 29.51
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 29.51
PR | 995 | 01/02/26 | 15 | Barnhart, Joseph N |  | 59.02
PR | 995 | 01/02/26 | 21 | Cortes Mendiola, Victor H |  | 34.72
PR | 995 | 01/02/26 | 27 | Draves, Steven W |  | 202.9
PR | 995 | 01/02/26 | 27 | Draves, Steven W |  | 190.96
PR | 995 | 01/02/26 | 27 | Draves, Steven W |  | 119.35
PR | 995 | 01/02/26 | 29 | Eliassen, Cory H |  | 131.94
PR | 995 | 01/02/26 | 29 | Eliassen, Cory H |  | 74.21
PR | 995 | 01/02/26 | 29 | Eliassen, Cory H |  | 131.94
PR | 995 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 01/02/26 | 33 | Gerard, Jordan E |  | 58.59
PR | 995 | 01/02/26 | 33 | Gerard, Jordan E |  | 91.14
PR | 995 | 01/02/26 | 33 | Gerard, Jordan E |  | 32.55
PR | 995 | 01/02/26 | 34 | Gerard, Mitchell J |  | 99.28
PR | 995 | 01/02/26 | 34 | Gerard, Mitchell J |  | 19.86
PR | 995 | 01/02/26 | 34 | Gerard, Mitchell J |  | 185.32
PR | 995 | 01/02/26 | 34 | Gerard, Mitchell J |  | 132.37
PR | 995 | 01/09/26 | 120 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/09/26 | 120 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/09/26 | 120 | Barnhart, Thomas L |  | 146.48
PR | 995 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 83.55
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 45.57
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 53.17
PR | 995 | 01/09/26 | 142 | Draves, Steven W |  | 197.9
PR | 995 | 01/09/26 | 142 | Draves, Steven W |  | 197.9
PR | 995 | 01/09/26 | 142 | Draves, Steven W |  | 197.9
PR | 995 | 01/09/26 | 144 | Eliassen, Cory H |  | 139.64
PR | 995 | 01/09/26 | 144 | Eliassen, Cory H |  | 93.09
PR | 995 | 01/09/26 | 144 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/09/26 | 147 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 01/09/26 | 148 | Gerard, Jordan E |  | 32.01
PR | 995 | 01/09/26 | 148 | Gerard, Jordan E |  | 38.41
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 47.85
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 157.22
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 20.51
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/09/26 | 149 | Gerard, Mitchell J |  | 88.86
PR | 995 | 01/16/26 | 266 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/16/26 | 266 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 30.38
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 167.09
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 15.19
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 22.79
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 98.74
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 22.79
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 220.26
PR | 995 | 01/16/26 | 288 | Draves, Steven W |  | 148.43
PR | 995 | 01/16/26 | 288 | Draves, Steven W |  | 204.09
PR | 995 | 01/16/26 | 288 | Draves, Steven W |  | 197.9
PR | 995 | 01/16/26 | 288 | Draves, Steven W |  | 197.9
PR | 995 | 01/16/26 | 288 | Draves, Steven W |  | 197.9
PR | 995 | 01/16/26 | 290 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/16/26 | 290 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/16/26 | 290 | Eliassen, Cory H |  | 101.56
PR | 995 | 01/16/26 | 290 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/16/26 | 290 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 01/16/26 | 294 | Gerard, Jordan E |  | 32.01
PR | 995 | 01/16/26 | 294 | Gerard, Jordan E |  | 32.01
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 218.74
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 116.2
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 47.85
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 136.71
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 61.52
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 170.89
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 88.86
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 47.85
PR | 995 | 01/16/26 | 295 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 151.9
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 53.17
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 68.36
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 22.79
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 98.74
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 7.6
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 15.19
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 45.57
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 243.04
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 22.79
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 53.17
PR | 995 | 01/23/26 | 473 | Cortes Mendiola, Victor H |  | 229.15
PR | 995 | 01/23/26 | 479 | Draves, Steven W |  | 197.9
PR | 995 | 01/23/26 | 479 | Draves, Steven W |  | 179.35
PR | 995 | 01/23/26 | 479 | Draves, Steven W |  | 197.9
PR | 995 | 01/23/26 | 479 | Draves, Steven W |  | 197.9
PR | 995 | 01/23/26 | 479 | Draves, Steven W |  | 197.9
PR | 995 | 01/23/26 | 481 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/23/26 | 481 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/23/26 | 481 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/23/26 | 481 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/23/26 | 481 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 01/23/26 | 485 | Gerard, Jordan E |  | 25.61
PR | 995 | 01/23/26 | 485 | Gerard, Jordan E |  | 44.81
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 129.87
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 88.86
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 68.36
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 123.04
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 170.89
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 13.67
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 34.18
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 218.74
PR | 995 | 01/23/26 | 486 | Gerard, Mitchell J |  | 218.74
PR | 995 | 01/30/26 | 569 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/30/26 | 569 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/30/26 | 569 | Barnhart, Thomas L |  | 156.24
PR | 995 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 75.95
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 45.57
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 37.98
PR | 995 | 01/30/26 | 586 | Cortes Mendiola, Victor H |  | 229.15
PR | 995 | 01/30/26 | 586 | Cortes Mendiola, Victor H |  | 143.22
PR | 995 | 01/30/26 | 592 | Draves, Steven W |  | 197.9
PR | 995 | 01/30/26 | 592 | Draves, Steven W |  | 197.9
PR | 995 | 01/30/26 | 592 | Draves, Steven W |  | 197.9
PR | 995 | 01/30/26 | 592 | Draves, Steven W |  | 197.9
PR | 995 | 01/30/26 | 592 | Draves, Steven W |  | 197.9
PR | 995 | 01/30/26 | 594 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/30/26 | 594 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/30/26 | 594 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/30/26 | 594 | Eliassen, Cory H |  | 131.18
PR | 995 | 01/30/26 | 594 | Eliassen, Cory H |  | 135.41
PR | 995 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 01/30/26 | 598 | Gerard, Jordan E |  | 38.41
PR | 995 | 01/30/26 | 598 | Gerard, Jordan E |  | 38.41
PR | 995 | 01/30/26 | 598 | Gerard, Jordan E |  | 6.4
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 61.52
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 20.51
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 41.01
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 95.7
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 218.74
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 41.01
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 129.87
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 20.51
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 27.34
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 184.56
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 102.53
PR | 995 | 01/30/26 | 599 | Gerard, Mitchell J |  | 116.2
PR | 995 | 02/06/26 | 45 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/06/26 | 45 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/06/26 | 45 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/06/26 | 45 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/06/26 | 45 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/06/26 | 56 | Barnhart, Joseph N |  | 15.19
PR | 995 | 02/06/26 | 56 | Barnhart, Joseph N |  | 37.98
PR | 995 | 02/06/26 | 68 | Draves, Steven W |  | 197.9
PR | 995 | 02/06/26 | 68 | Draves, Steven W |  | 197.9
PR | 995 | 02/06/26 | 68 | Draves, Steven W |  | 197.9
PR | 995 | 02/06/26 | 68 | Draves, Steven W |  | 197.9
PR | 995 | 02/06/26 | 68 | Draves, Steven W |  | 197.9
PR | 995 | 02/06/26 | 69 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/06/26 | 69 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/06/26 | 69 | Eliassen, Cory H |  | 131.18
PR | 995 | 02/06/26 | 69 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/06/26 | 69 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 02/06/26 | 73 | Gerard, Jordan E |  | 57.61
PR | 995 | 02/06/26 | 73 | Gerard, Jordan E |  | 76.82
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 157.22
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 61.52
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 68.36
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 218.74
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 27.34
PR | 995 | 02/06/26 | 74 | Gerard, Mitchell J |  | 170.89
PR | 995 | 02/13/26 | 177 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/13/26 | 177 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/13/26 | 177 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/13/26 | 177 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/13/26 | 177 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A |  | 143.76
PR | 995 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A |  | 184.02
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 144.31
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 113.93
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 296.21
PR | 995 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 81.81
PR | 995 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 90.27
PR | 995 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 76.17
PR | 995 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 85.93
PR | 995 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 236.31
PR | 995 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 143.22
PR | 995 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 85.93
PR | 995 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 10.74
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 197.9
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 197.9
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 197.9
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 197.9
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 197.9
PR | 995 | 02/13/26 | 200 | Draves, Steven W |  | 92.77
PR | 995 | 02/13/26 | 201 | Eliassen, Cory H |  | 93.09
PR | 995 | 02/13/26 | 201 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/13/26 | 201 | Eliassen, Cory H |  | 135.41
PR | 995 | 02/13/26 | 201 | Eliassen, Cory H |  | 131.18
PR | 995 | 02/13/26 | 201 | Eliassen, Cory H |  | 139.64
PR | 995 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 14.97
PR | 995 | 02/13/26 | 205 | Gerard, Jordan E |  | 57.61
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 27.34
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 34.18
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 41.01
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 75.19
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 47.85
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 136.71
PR | 995 | 02/13/26 | 206 | Gerard, Mitchell J |  | 177.72
PR | 995 | 02/20/26 | 293 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/20/26 | 293 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/20/26 | 293 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/20/26 | 293 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/20/26 | 293 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/20/26 | 298 | Amaya Gonzalez, Edilberto A |  | 184.02
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 167.09
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 15.19
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 37.98
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 15.19
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 22.79
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 60.76
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 83.55
PR | 995 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 90.27
PR | 995 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 47.96
PR | 995 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 90.27
PR | 995 | 02/20/26 | 310 | Cortes Mendiola, Victor H |  | 121.74
PR | 995 | 02/20/26 | 310 | Cortes Mendiola, Victor H |  | 229.15
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 55.66
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 86.58
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 160.8
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 197.9
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 185.54
PR | 995 | 02/20/26 | 316 | Draves, Steven W |  | 197.9
PR | 995 | 02/20/26 | 320 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 38.41
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 32.01
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 70.42
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 68.36
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 225.57
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 41.01
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 20.51
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 75.19
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 68.36
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 27.34
PR | 995 | 02/20/26 | 322 | Gerard, Mitchell J |  | 136.71
PR | 995 | 02/27/26 | 442 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/27/26 | 442 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/27/26 | 442 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/27/26 | 442 | Barnhart, Thomas L |  | 156.24
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 136.71
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 54.68
PR | 995 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 91.14
PR | 995 | 02/27/26 | 446 | Amaya Gonzalez, Edilberto A |  | 172.52
PR | 995 | 02/27/26 | 448 | Aquino, Juan |  | 149.73
PR | 995 | 02/27/26 | 450 | Ascencio, Jose L |  | 139.97
PR | 995 | 02/27/26 | 451 | Balderas Ortiz, Ricardo I |  | 95.48
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 159.5
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 60.76
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 227.85
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 91.14
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 15.19
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 106.33
PR | 995 | 02/27/26 | 453 | Bautista Quintero, Isidoro |  | 90.27
PR | 995 | 02/27/26 | 454 | Carmona, Raul O |  | 175.77
PR | 995 | 02/27/26 | 456 | Chevez, Herson G |  | 123.69
PR | 995 | 02/27/26 | 458 | Cortes Mendiola, Victor H |  | 229.15
PR | 995 | 02/27/26 | 458 | Cortes Mendiola, Victor H |  | 214.83
PR | 995 | 02/27/26 | 459 | Countryman, Matthew K |  | 110.02
PR | 995 | 02/27/26 | 459 | Countryman, Matthew K |  | 39.49
PR | 995 | 02/27/26 | 462 | Da Cruz, Eduardo E |  | 74.87
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 197.9
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 197.9
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 74.21
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 185.54
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 197.9
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 197.9
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 24.74
PR | 995 | 02/27/26 | 464 | Draves, Steven W |  | 173.17
PR | 995 | 02/27/26 | 465 | Fox, Tamron P |  | 97.65
PR | 995 | 02/27/26 | 468 | Gerard, Jordan E |  | 70.42
PR | 995 | 02/27/26 | 468 | Gerard, Jordan E |  | 38.41
PR | 995 | 02/27/26 | 468 | Gerard, Jordan E |  | 64.02
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 218.74
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 218.74
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 82.03
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 218.74
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 184.56
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 61.52
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 20.51
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 6.84
PR | 995 | 02/27/26 | 469 | Gerard, Mitchell J |  | 54.68
PR | 995 | 02/27/26 | 473 | Gorman, Nathan W |  | 84.63
PR | 995 | 02/27/26 | 478 | Mackey, Cole J |  | 169.26
PR | 995 | 02/27/26 | 480 | Melgar Moz, Brandon |  | 84.63
PR | 995 | 02/27/26 | 481 | Mendoza Morales, Jesus A |  | 139.97
PR | 995 | 02/27/26 | 484 | Nunez Bravo, Jose L |  | 78.12
PR | 995 | 02/27/26 | 485 | Paco Leyva, Orlando |  | 205.07
PR | 995 | 02/27/26 | 486 | Perez Araque, Manuel A |  | 65.1
PR | 995 | 02/27/26 | 488 | Ramos Herrera, Franklin J |  | 139.97
PR | 995 | 02/27/26 | 490 | Rodriguez Arevalos, Christian |  | 143.87
PR | 995 | 02/27/26 | 492 | Silva Morales, Jair J |  | 113.93
PR | 995 | 02/27/26 | 493 | Suniga Aviles, Kelvin A |  | 84.63
PR | 995 | 02/27/26 | 498 | Young, Joshua S |  | 169.26
PR | 995 | 02/27/26 | 499 | Zuniga Avilez, Eduar A |  | 84.63
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 97.65
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/06/26 | 38 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 22.79
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 45.57
PR | 995 | 03/06/26 | 60 | Draves, Steven W |  | 197.9
PR | 995 | 03/06/26 | 60 | Draves, Steven W |  | 197.9
PR | 995 | 03/06/26 | 60 | Draves, Steven W |  | 197.9
PR | 995 | 03/06/26 | 60 | Draves, Steven W |  | 197.9
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 19.2
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 218.74
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 47.85
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 170.89
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 218.74
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 218.74
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 61.52
PR | 995 | 03/06/26 | 65 | Gerard, Mitchell J |  | 157.22
PR | 995 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 94.4
PR | 995 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 104.16
PR | 995 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 104.16
PR | 995 | 03/13/26 | 183 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/13/26 | 183 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/13/26 | 183 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/13/26 | 183 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/13/26 | 183 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 145.82
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 68.36
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 116.2
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 75.19
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 27.34
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 75.19
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 34.18
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 136.71
PR | 995 | 03/13/26 | 210 | Gerard, Mitchell J |  | 157.22
PR | 995 | 03/13/26 | 227 | Perez Araque, Manuel A |  | 104.16
PR | 995 | 03/13/26 | 227 | Perez Araque, Manuel A |  | 104.16
PR | 995 | 03/20/26 | 301 | Barnhart, Thomas L |  | 146.48
PR | 995 | 03/20/26 | 301 | Barnhart, Thomas L |  | 136.71
PR | 995 | 03/20/26 | 301 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/20/26 | 301 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/20/26 | 301 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 45.57
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 83.55
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 22.79
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 60.76
PR | 995 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 95.7
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 27.34
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 47.85
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 41.01
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 20.51
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 164.05
PR | 995 | 03/20/26 | 328 | Gerard, Mitchell J |  | 170.89
PR | 995 | 03/27/26 | 469 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/27/26 | 469 | Barnhart, Thomas L |  | 156.24
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 30.38
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 30.38
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 7.6
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 22.79
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 83.55
PR | 995 | 03/27/26 | 491 | Draves, Steven W |  | 197.9
PR | 995 | 03/27/26 | 491 | Draves, Steven W |  | 197.9
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 29.95
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 218.74
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 47.85
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 157.22
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 20.51
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 13.67
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 13.67
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 27.34
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 20.51
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 61.52
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 20.51
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 27.34
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 157.22
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 13.67
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 75.19
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 41.01
PR | 995 | 03/27/26 | 496 | Gerard, Mitchell J |  | 75.19
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 15.19
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 98.74
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 30.38
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 68.36
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 22.79
PR | 995 | 04/03/26 | 12 | Barnhart, Joseph N |  | 7.6
PR | 995 | 04/03/26 | 24 | Draves, Steven W |  | 197.9
PR | 995 | 04/03/26 | 24 | Draves, Steven W |  | 197.9
PR | 995 | 04/03/26 | 28 | Gerard, Jordan E |  | 57.61
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 218.74
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 13.67
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 41.01
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 27.34
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 47.85
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 6.84
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 218.74
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 218.74
PR | 995 | 04/03/26 | 29 | Gerard, Mitchell J |  | 184.56
PR | 998 | 03/08/24 | 334 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/15/24 | 507 | Barnhart, Joseph N |  | 15.61
PR | 998 | 03/15/24 | 599 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/22/24 | 869 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/22/24 | 878 | Johnson, Jake E |  | 3.98
PR | 998 | 03/29/24 | 1182 | Barnhart, Joseph N |  | 15.61
PR | 998 | 03/29/24 | 1246 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 03/29/24 | 1256 | Johnson, Jake E |  | 7.96
PR | 998 | 04/05/24 | 62 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 04/05/24 | 74 | Johnson, Jake E |  | 3.98
PR | 998 | 04/12/24 | 166 | Barnhart, Joseph N |  | 41.62
PR | 998 | 04/12/24 | 223 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 04/12/24 | 236 | Johnson, Jake E |  | 15.91
PR | 998 | 04/19/24 | 445 | Barnhart, Joseph N |  | 26.01
PR | 998 | 04/19/24 | 504 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 04/19/24 | 517 | Johnson, Jake E |  | 11.93
PR | 998 | 04/26/24 | 828 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/03/24 | 56 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/03/24 | 68 | Johnson, Jake E |  | 31.82
PR | 998 | 05/10/24 | 242 | Barnhart, Joseph N |  | 15.61
PR | 998 | 05/10/24 | 294 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 05/10/24 | 306 | Johnson, Jake E |  | 35.8
PR | 998 | 05/17/24 | 470 | Barnhart, Joseph N |  | 57.22
PR | 998 | 05/17/24 | 521 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 05/24/24 | 726 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 05/24/24 | 738 | Johnson, Jake E |  | 15.91
PR | 998 | 05/31/24 | 793 | Barnhart, Joseph N |  | 36.41
PR | 998 | 05/31/24 | 840 | Gerard, Jeffrey S |  | 42.23
PR | 998 | 05/31/24 | 850 | Johnson, Jake E |  | 19.89
PR | 998 | 06/07/24 | 81 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/07/24 | 81 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/07/24 | 129 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 06/07/24 | 139 | Johnson, Jake E |  | 15.91
PR | 998 | 06/14/24 | 305 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 06/14/24 | 362 | Johnson, Jake E |  | 15.91
PR | 998 | 06/21/24 | 480 | Barnhart, Joseph N |  | 41.62
PR | 998 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/21/24 | 533 | Johnson, Jake E |  | 3.98
PR | 998 | 06/28/24 | 687 | Barnhart, Joseph N |  | 31.21
PR | 998 | 06/28/24 | 716 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 06/28/24 | 719 | Da Cruz, Eduardo E |  | 6.43
PR | 998 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 06/28/24 | 740 | Johnson, Jake E |  | 15.91
PR | 998 | 07/05/24 | 4 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/05/24 | 34 | Da Cruz, Eduardo E |  | 6.43
PR | 998 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 07/05/24 | 53 | Johnson, Jake E |  | 31.82
PR | 998 | 07/12/24 | 166 | Anderson, Richard P |  | 9.95
PR | 998 | 07/12/24 | 167 | Barnhart, Joseph N |  | 44.22
PR | 998 | 07/12/24 | 193 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 07/12/24 | 216 | Johnson, Jake E |  | 11.93
PR | 998 | 07/19/24 | 374 | Anderson, Richard P |  | 17.4
PR | 998 | 07/19/24 | 390 | Barnhart, Joseph N |  | 85.83
PR | 998 | 07/19/24 | 390 | Barnhart, Joseph N |  | 7.8
PR | 998 | 07/19/24 | 391 | Bautista Quintero, Isidoro |  | 4.59
PR | 998 | 07/19/24 | 399 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 07/19/24 | 402 | Da Cruz, Eduardo E |  | 4.82
PR | 998 | 07/19/24 | 407 | Eisenhauer, Tommy J |  | 13.08
PR | 998 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/19/24 | 422 | Johnson, Jake E |  | 15.91
PR | 998 | 07/26/24 | 563 | Anderson, Richard P |  | 111.88
PR | 998 | 07/26/24 | 573 | Amaya Gonzalez, Edilberto A |  | 20.2
PR | 998 | 07/26/24 | 579 | Bautista Quintero, Isidoro |  | 9.18
PR | 998 | 07/26/24 | 587 | Cortes Mendiola, Victor H |  | 127.3
PR | 998 | 07/26/24 | 590 | Da Cruz, Eduardo E |  | 9.64
PR | 998 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 07/26/24 | 609 | Johnson, Jake E |  | 11.93
PR | 998 | 08/02/24 | 2 | Anderson, Richard P |  | 64.64
PR | 998 | 08/02/24 | 13 | Amaya Gonzalez, Edilberto A |  | 134.64
PR | 998 | 08/02/24 | 18 | Barnhart, Joseph N |  | 93.64
PR | 998 | 08/02/24 | 19 | Bautista Quintero, Isidoro |  | 61.2
PR | 998 | 08/02/24 | 27 | Cortes Mendiola, Victor H |  | 195.84
PR | 998 | 08/02/24 | 30 | Da Cruz, Eduardo E |  | 64.26
PR | 998 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 08/02/24 | 49 | Johnson, Jake E |  | 19.89
PR | 998 | 08/02/24 | 49 | Johnson, Jake E |  | 7.96
PR | 998 | 08/09/24 | 248 | Amaya Gonzalez, Edilberto A |  | 124.54
PR | 998 | 08/09/24 | 253 | Barnhart, Joseph N |  | 72.83
PR | 998 | 08/09/24 | 254 | Bautista Quintero, Isidoro |  | 61.2
PR | 998 | 08/09/24 | 262 | Cortes Mendiola, Victor H |  | 186.05
PR | 998 | 08/09/24 | 265 | Da Cruz, Eduardo E |  | 64.26
PR | 998 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/09/24 | 283 | Johnson, Jake E |  | 3.98
PR | 998 | 08/16/24 | 439 | Amaya Gonzalez, Edilberto A |  | 134.64
PR | 998 | 08/16/24 | 444 | Barnhart, Joseph N |  | 20.81
PR | 998 | 08/16/24 | 445 | Bautista Quintero, Isidoro |  | 61.2
PR | 998 | 08/16/24 | 453 | Cortes Mendiola, Victor H |  | 195.84
PR | 998 | 08/16/24 | 456 | Da Cruz, Eduardo E |  | 64.26
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 08/16/24 | 472 | Johnson, Jake E |  | 3.98
PR | 998 | 08/23/24 | 694 | Cruz Reyes, Jose |  | 12.55
PR | 998 | 08/23/24 | 694 | Cruz Reyes, Jose |  | 12.55
PR | 998 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A |  | 107.71
PR | 998 | 08/23/24 | 701 | Amaya Gonzalez, Edilberto A |  | 26.93
PR | 998 | 08/23/24 | 706 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/23/24 | 706 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/23/24 | 706 | Barnhart, Joseph N |  | 31.21
PR | 998 | 08/23/24 | 707 | Bautista Quintero, Isidoro |  | 48.96
PR | 998 | 08/23/24 | 707 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 08/23/24 | 715 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 08/23/24 | 715 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 08/23/24 | 718 | Da Cruz, Eduardo E |  | 25.7
PR | 998 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 52.79
PR | 998 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 08/23/24 | 734 | Johnson, Jake E |  | 3.98
PR | 998 | 08/30/24 | 833 | Anderson, Richard P |  | 14.92
PR | 998 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A |  | 74.05
PR | 998 | 08/30/24 | 844 | Amaya Gonzalez, Edilberto A |  | 33.66
PR | 998 | 08/30/24 | 849 | Barnhart, Joseph N |  | 62.42
PR | 998 | 08/30/24 | 849 | Barnhart, Joseph N |  | 20.81
PR | 998 | 08/30/24 | 849 | Barnhart, Joseph N |  | 15.61
PR | 998 | 08/30/24 | 850 | Bautista Quintero, Isidoro |  | 45.9
PR | 998 | 08/30/24 | 850 | Bautista Quintero, Isidoro |  | 15.3
PR | 998 | 08/30/24 | 858 | Cortes Mendiola, Victor H |  | 186.05
PR | 998 | 08/30/24 | 858 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/30/24 | 876 | Johnson, Jake E |  | 27.85
PR | 998 | 08/30/24 | 896 | Silva Morales, Jair J |  | 78.03
PR | 998 | 08/30/24 | 896 | Silva Morales, Jair J |  | 26.01
PR | 998 | 09/06/24 | 13 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/06/24 | 13 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 09/06/24 | 19 | Waites, Thaddeus Z |  | 32.67
PR | 998 | 09/06/24 | 20 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 09/06/24 | 25 | Barnhart, Joseph N |  | 41.62
PR | 998 | 09/06/24 | 25 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/06/24 | 26 | Bautista Quintero, Isidoro |  | 48.96
PR | 998 | 09/06/24 | 34 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/06/24 | 53 | Johnson, Jake E |  | 31.82
PR | 998 | 09/06/24 | 73 | Silva Morales, Jair J |  | 83.23
PR | 998 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/13/24 | 221 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A |  | 117.05
PR | 998 | 09/13/24 | 228 | Amaya Gonzalez, Edilberto A |  | 19.51
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 36.41
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/13/24 | 234 | Bautista Quintero, Isidoro |  | 56.61
PR | 998 | 09/13/24 | 242 | Cortes Mendiola, Victor H |  | 141.98
PR | 998 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 47.51
PR | 998 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 09/13/24 | 261 | Johnson, Jake E |  | 43.76
PR | 998 | 09/13/24 | 280 | Silva Morales, Jair J |  | 83.23
PR | 998 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A |  | 42.92
PR | 998 | 09/20/24 | 400 | Amaya Gonzalez, Edilberto A |  | 113.14
PR | 998 | 09/20/24 | 405 | Barnhart, Joseph N |  | 52.02
PR | 998 | 09/20/24 | 405 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/20/24 | 406 | Bautista Quintero, Isidoro |  | 56.61
PR | 998 | 09/20/24 | 406 | Bautista Quintero, Isidoro |  | 4.59
PR | 998 | 09/20/24 | 414 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 09/20/24 | 414 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 58.06
PR | 998 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 09/20/24 | 432 | Johnson, Jake E |  | 35.8
PR | 998 | 09/20/24 | 451 | Silva Morales, Jair J |  | 28.61
PR | 998 | 09/20/24 | 451 | Silva Morales, Jair J |  | 75.43
PR | 998 | 09/27/24 | 537 | Amaya Gonzalez, Edilberto A |  | 144.36
PR | 998 | 09/27/24 | 542 | Barnhart, Joseph N |  | 104.04
PR | 998 | 09/27/24 | 542 | Barnhart, Joseph N |  | 20.81
PR | 998 | 09/27/24 | 543 | Bautista Quintero, Isidoro |  | 61.2
PR | 998 | 09/27/24 | 550 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 09/27/24 | 559 | Gerard, Jeffrey S |  | 42.23
PR | 998 | 09/27/24 | 559 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/27/24 | 568 | Johnson, Jake E |  | 7.96
PR | 998 | 09/27/24 | 587 | Silva Morales, Jair J |  | 83.23
PR | 998 | 09/27/24 | 587 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/04/24 | 20 | Waites, Thaddeus Z |  | 84
PR | 998 | 10/04/24 | 20 | Waites, Thaddeus Z |  | 28
PR | 998 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/04/24 | 21 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 10/04/24 | 26 | Barnhart, Joseph N |  | 62.42
PR | 998 | 10/04/24 | 27 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 10/04/24 | 27 | Bautista Quintero, Isidoro |  | 36.72
PR | 998 | 10/04/24 | 34 | Cortes Mendiola, Victor H |  | 44.06
PR | 998 | 10/04/24 | 34 | Cortes Mendiola, Victor H |  | 117.5
PR | 998 | 10/04/24 | 39 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 47.51
PR | 998 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 10/04/24 | 52 | Johnson, Jake E |  | 11.93
PR | 998 | 10/04/24 | 66 | Ramos Herrera, Franklin J |  | 51.41
PR | 998 | 10/04/24 | 71 | Silva Morales, Jair J |  | 41.62
PR | 998 | 10/04/24 | 71 | Silva Morales, Jair J |  | 62.42
PR | 998 | 10/04/24 | 81 | Young, Joshua S |  | 33.05
PR | 998 | 10/11/24 | 227 | Waites, Thaddeus Z |  | 23.33
PR | 998 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 10/11/24 | 228 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 18.21
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 28.61
PR | 998 | 10/11/24 | 233 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/11/24 | 234 | Bautista Quintero, Isidoro |  | 24.48
PR | 998 | 10/11/24 | 234 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 10/11/24 | 241 | Cortes Mendiola, Victor H |  | 137.09
PR | 998 | 10/11/24 | 241 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 58.06
PR | 998 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/11/24 | 259 | Johnson, Jake E |  | 23.87
PR | 998 | 10/11/24 | 277 | Silva Morales, Jair J |  | 62.42
PR | 998 | 10/11/24 | 277 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 10/18/24 | 441 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 52.02
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/18/24 | 446 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/18/24 | 447 | Bautista Quintero, Isidoro |  | 24.48
PR | 998 | 10/18/24 | 454 | Cortes Mendiola, Victor H |  | 176.26
PR | 998 | 10/18/24 | 454 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 58.06
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 10/18/24 | 471 | Johnson, Jake E |  | 31.82
PR | 998 | 10/18/24 | 489 | Silva Morales, Jair J |  | 93.64
PR | 998 | 10/18/24 | 489 | Silva Morales, Jair J |  | 10.4
PR | 998 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A |  | 136.55
PR | 998 | 10/25/24 | 589 | Amaya Gonzalez, Edilberto A |  | 19.51
PR | 998 | 10/25/24 | 594 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/25/24 | 594 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/25/24 | 595 | Bautista Quintero, Isidoro |  | 53.55
PR | 998 | 10/25/24 | 595 | Bautista Quintero, Isidoro |  | 7.65
PR | 998 | 10/25/24 | 601 | Cortes Mendiola, Victor H |  | 137.09
PR | 998 | 10/25/24 | 601 | Cortes Mendiola, Victor H |  | 58.75
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/25/24 | 618 | Johnson, Jake E |  | 23.87
PR | 998 | 10/25/24 | 629 | Portillo Rivera, Josue N |  | 40.39
PR | 998 | 10/25/24 | 636 | Silva Morales, Jair J |  | 104.04
PR | 998 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A |  | 117.05
PR | 998 | 11/01/24 | 18 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 11/01/24 | 23 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/01/24 | 23 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/01/24 | 24 | Bautista Quintero, Isidoro |  | 36.72
PR | 998 | 11/01/24 | 24 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/01/24 | 30 | Cortes Mendiola, Victor H |  | 161.57
PR | 998 | 11/01/24 | 30 | Cortes Mendiola, Victor H |  | 34.27
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 11/01/24 | 47 | Johnson, Jake E |  | 15.91
PR | 998 | 11/01/24 | 58 | Portillo Rivera, Josue N |  | 53.86
PR | 998 | 11/01/24 | 65 | Silva Morales, Jair J |  | 96.24
PR | 998 | 11/01/24 | 65 | Silva Morales, Jair J |  | 7.8
PR | 998 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 11/08/24 | 138 | Amaya Gonzalez, Edilberto A |  | 101.44
PR | 998 | 11/08/24 | 143 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/08/24 | 144 | Bautista Quintero, Isidoro |  | 15.3
PR | 998 | 11/08/24 | 150 | Cortes Mendiola, Victor H |  | 166.46
PR | 998 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 11/08/24 | 167 | Johnson, Jake E |  | 15.91
PR | 998 | 11/08/24 | 179 | Portillo Rivera, Josue N |  | 40.39
PR | 998 | 11/08/24 | 179 | Portillo Rivera, Josue N |  | 13.46
PR | 998 | 11/08/24 | 186 | Silva Morales, Jair J |  | 83.23
PR | 998 | 11/08/24 | 186 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 46.82
PR | 998 | 11/15/24 | 358 | Amaya Gonzalez, Edilberto A |  | 15.61
PR | 998 | 11/15/24 | 363 | Barnhart, Joseph N |  | 15.61
PR | 998 | 11/15/24 | 363 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 29.07
PR | 998 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 18.36
PR | 998 | 11/15/24 | 364 | Bautista Quintero, Isidoro |  | 6.12
PR | 998 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 132.19
PR | 998 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 11/15/24 | 370 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/15/24 | 387 | Johnson, Jake E |  | 23.87
PR | 998 | 11/15/24 | 399 | Portillo Rivera, Josue N |  | 13.46
PR | 998 | 11/15/24 | 399 | Portillo Rivera, Josue N |  | 26.93
PR | 998 | 11/15/24 | 406 | Silva Morales, Jair J |  | 62.42
PR | 998 | 11/15/24 | 406 | Silva Morales, Jair J |  | 41.62
PR | 998 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 11/22/24 | 513 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 11/22/24 | 519 | Bautista Quintero, Isidoro |  | 48.96
PR | 998 | 11/22/24 | 519 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/22/24 | 525 | Cortes Mendiola, Victor H |  | 48.96
PR | 998 | 11/22/24 | 525 | Cortes Mendiola, Victor H |  | 137.09
PR | 998 | 11/22/24 | 531 | Eliassen, Cory H |  | 39.24
PR | 998 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 11/22/24 | 554 | Portillo Rivera, Josue N |  | 40.39
PR | 998 | 11/22/24 | 554 | Portillo Rivera, Josue N |  | 26.93
PR | 998 | 11/22/24 | 561 | Silva Morales, Jair J |  | 83.23
PR | 998 | 11/22/24 | 561 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/29/24 | 648 | Johnson, Jake E |  | 3.98
PR | 998 | 11/29/24 | 648 | Johnson, Jake E |  | 7.96
PR | 998 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 11/29/24 | 661 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 11/29/24 | 666 | Barnhart, Joseph N |  | 20.81
PR | 998 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 24.48
PR | 998 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 24.48
PR | 998 | 11/29/24 | 667 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 73.44
PR | 998 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 48.96
PR | 998 | 11/29/24 | 673 | Cortes Mendiola, Victor H |  | 73.44
PR | 998 | 11/29/24 | 679 | Eliassen, Cory H |  | -39.24
PR | 998 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 11/29/24 | 690 | Johnson, Jake E |  | 15.91
PR | 998 | 11/29/24 | 692 | Lopez, Maslin A |  | 100.98
PR | 998 | 11/29/24 | 702 | Portillo Rivera, Josue N |  | 13.46
PR | 998 | 11/29/24 | 702 | Portillo Rivera, Josue N |  | 13.46
PR | 998 | 11/29/24 | 709 | Silva Morales, Jair J |  | 41.62
PR | 998 | 11/29/24 | 709 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/29/24 | 709 | Silva Morales, Jair J |  | 41.62
PR | 998 | 12/06/24 | 51 | Anderson, Richard P |  | 4.97
PR | 998 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 50.72
PR | 998 | 12/06/24 | 63 | Amaya Gonzalez, Edilberto A |  | 11.7
PR | 998 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 7.65
PR | 998 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 4.59
PR | 998 | 12/06/24 | 69 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 97.92
PR | 998 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 12/06/24 | 75 | Cortes Mendiola, Victor H |  | 4.9
PR | 998 | 12/06/24 | 83 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 12/06/24 | 83 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/06/24 | 92 | Johnson, Jake E |  | 15.91
PR | 998 | 12/06/24 | 94 | Lopez, Maslin A |  | 60.59
PR | 998 | 12/06/24 | 110 | Silva Morales, Jair J |  | 41.62
PR | 998 | 12/06/24 | 110 | Silva Morales, Jair J |  | 20.81
PR | 998 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 12/13/24 | 245 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 12/13/24 | 250 | Barnhart, Joseph N |  | 15.61
PR | 998 | 12/13/24 | 250 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 36.72
PR | 998 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 12/13/24 | 251 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 88.13
PR | 998 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 68.54
PR | 998 | 12/13/24 | 257 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/13/24 | 274 | Johnson, Jake E |  | 7.96
PR | 998 | 12/13/24 | 276 | Lopez, Maslin A |  | 20.2
PR | 998 | 12/13/24 | 276 | Lopez, Maslin A |  | 60.59
PR | 998 | 12/13/24 | 292 | Silva Morales, Jair J |  | 83.23
PR | 998 | 12/13/24 | 292 | Silva Morales, Jair J |  | 20.81
PR | 998 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A |  | 78.03
PR | 998 | 12/20/24 | 432 | Amaya Gonzalez, Edilberto A |  | 78.03
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 36.41
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/20/24 | 438 | Bautista Quintero, Isidoro |  | 30.6
PR | 998 | 12/20/24 | 438 | Bautista Quintero, Isidoro |  | 30.6
PR | 998 | 12/20/24 | 444 | Cortes Mendiola, Victor H |  | 117.5
PR | 998 | 12/20/24 | 444 | Cortes Mendiola, Victor H |  | 78.34
PR | 998 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 12/20/24 | 460 | Johnson, Jake E |  | 11.93
PR | 998 | 12/20/24 | 462 | Lopez, Maslin A |  | 80.78
PR | 998 | 12/20/24 | 479 | Silva Morales, Jair J |  | 104.04
PR | 998 | 12/27/24 | 551 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 12/27/24 | 556 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/27/24 | 556 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/27/24 | 557 | Bautista Quintero, Isidoro |  | 36.72
PR | 998 | 12/27/24 | 563 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 12/27/24 | 563 | Cortes Mendiola, Victor H |  | 97.92
PR | 998 | 12/27/24 | 568 | Eliassen, Cory H |  | 4.36
PR | 998 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 12/27/24 | 579 | Johnson, Jake E |  | 7.96
PR | 998 | 12/27/24 | 581 | Lopez, Maslin A |  | 60.59
PR | 998 | 12/27/24 | 595 | Silva Morales, Jair J |  | 62.42
PR | 998 | 01/03/25 | 23 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 01/03/25 | 29 | Bautista Quintero, Isidoro |  | 12.24
PR | 998 | 01/03/25 | 30 | Carmona, Raul O |  | 64.87
PR | 998 | 01/03/25 | 34 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 01/03/25 | 34 | Cortes Mendiola, Victor H |  | 58.75
PR | 998 | 01/03/25 | 41 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 01/03/25 | 41 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/03/25 | 49 | Johnson, Jake E |  | 3.98
PR | 998 | 01/03/25 | 51 | Lopez, Maslin A |  | 20.2
PR | 998 | 01/03/25 | 63 | Silva Morales, Jair J |  | 10.4
PR | 998 | 01/03/25 | 63 | Silva Morales, Jair J |  | 31.21
PR | 998 | 01/10/25 | 185 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 13.46
PR | 998 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 26.93
PR | 998 | 01/10/25 | 191 | Bautista Quintero, Isidoro |  | 13.46
PR | 998 | 01/10/25 | 192 | Carmona, Raul O |  | 129.74
PR | 998 | 01/10/25 | 196 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 01/10/25 | 198 | Cruz Guzman, Joel A |  | 31.21
PR | 998 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 01/10/25 | 212 | Johnson, Jake E |  | 27.85
PR | 998 | 01/10/25 | 214 | Lopez, Maslin A |  | 80.78
PR | 998 | 01/10/25 | 218 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 01/10/25 | 227 | Silva Morales, Jair J |  | 83.23
PR | 998 | 01/17/25 | 349 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 01/17/25 | 353 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 01/17/25 | 354 | Barnhart, Joseph N |  | 46.82
PR | 998 | 01/17/25 | 354 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/17/25 | 355 | Bautista Quintero, Isidoro |  | 53.86
PR | 998 | 01/17/25 | 356 | Carmona, Raul O |  | 162.18
PR | 998 | 01/17/25 | 360 | Cortes Mendiola, Victor H |  | 107.71
PR | 998 | 01/17/25 | 360 | Cortes Mendiola, Victor H |  | 88.13
PR | 998 | 01/17/25 | 367 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 01/17/25 | 367 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 01/17/25 | 375 | Johnson, Jake E |  | 31.82
PR | 998 | 01/17/25 | 377 | Lopez, Maslin A |  | 80.78
PR | 998 | 01/17/25 | 381 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 01/17/25 | 391 | Silva Morales, Jair J |  | 104.04
PR | 998 | 01/24/25 | 514 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 01/24/25 | 515 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 01/24/25 | 519 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 7.8
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 41.62
PR | 998 | 01/24/25 | 520 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/24/25 | 521 | Bautista Quintero, Isidoro |  | 60.59
PR | 998 | 01/24/25 | 521 | Bautista Quintero, Isidoro |  | 6.73
PR | 998 | 01/24/25 | 522 | Carmona, Raul O |  | 162.18
PR | 998 | 01/24/25 | 526 | Cortes Mendiola, Victor H |  | 137.09
PR | 998 | 01/24/25 | 526 | Cortes Mendiola, Victor H |  | 58.75
PR | 998 | 01/24/25 | 528 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 01/24/25 | 530 | Draves, Steven W |  | 21.04
PR | 998 | 01/24/25 | 534 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 01/24/25 | 534 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 01/24/25 | 544 | Lopez, Maslin A |  | 80.78
PR | 998 | 01/24/25 | 548 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 01/24/25 | 558 | Silva Morales, Jair J |  | 83.23
PR | 998 | 01/24/25 | 611 | Johnson, Jake E |  | 11.93
PR | 998 | 01/31/25 | 706 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 01/31/25 | 707 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 01/31/25 | 711 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 26.01
PR | 998 | 01/31/25 | 713 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 01/31/25 | 714 | Carmona, Raul O |  | 162.18
PR | 998 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 127.3
PR | 998 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 01/31/25 | 718 | Cortes Mendiola, Victor H |  | 48.96
PR | 998 | 01/31/25 | 720 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 01/31/25 | 734 | Johnson, Jake E |  | 23.87
PR | 998 | 01/31/25 | 736 | Lopez, Maslin A |  | 20.2
PR | 998 | 01/31/25 | 740 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 01/31/25 | 749 | Silva Morales, Jair J |  | 104.04
PR | 998 | 02/07/25 | 36 | Waites, Thaddeus Z |  | 112
PR | 998 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 02/07/25 | 37 | Amaya Gonzalez, Edilberto A |  | 62.42
PR | 998 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 02/07/25 | 41 | Balderas Ortiz, Ricardo I |  | 53.86
PR | 998 | 02/07/25 | 43 | Bautista Quintero, Isidoro |  | 26.93
PR | 998 | 02/07/25 | 43 | Bautista Quintero, Isidoro |  | 26.93
PR | 998 | 02/07/25 | 44 | Carmona, Raul O |  | 129.74
PR | 998 | 02/07/25 | 48 | Cortes Mendiola, Victor H |  | 88.13
PR | 998 | 02/07/25 | 48 | Cortes Mendiola, Victor H |  | 107.71
PR | 998 | 02/07/25 | 50 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 02/07/25 | 52 | Draves, Steven W |  | 92.57
PR | 998 | 02/07/25 | 56 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/07/25 | 56 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/07/25 | 64 | Johnson, Jake E |  | 19.89
PR | 998 | 02/07/25 | 70 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 02/07/25 | 80 | Silva Morales, Jair J |  | 83.23
PR | 998 | 02/14/25 | 201 | Hernandez Gonzalez, Osbaldo |  | 102.82
PR | 998 | 02/14/25 | 202 | Waites, Thaddeus Z |  | 149.33
PR | 998 | 02/14/25 | 203 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 02/14/25 | 207 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/14/25 | 208 | Barnhart, Joseph N |  | 46.82
PR | 998 | 02/14/25 | 208 | Barnhart, Joseph N |  | 13.01
PR | 998 | 02/14/25 | 209 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 02/14/25 | 210 | Carmona, Raul O |  | 129.74
PR | 998 | 02/14/25 | 214 | Cortes Mendiola, Victor H |  | 137.09
PR | 998 | 02/14/25 | 214 | Cortes Mendiola, Victor H |  | 58.75
PR | 998 | 02/14/25 | 216 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 02/14/25 | 222 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 02/14/25 | 222 | Gerard, Jeffrey S |  | 29.03
PR | 998 | 02/14/25 | 223 | Gerard, Jordan E |  | 36.72
PR | 998 | 02/14/25 | 224 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 02/14/25 | 227 | Guerrero Espinoza, Mario |  | 55.08
PR | 998 | 02/14/25 | 230 | Johnson, Jake E |  | 7.96
PR | 998 | 02/14/25 | 236 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 02/14/25 | 236 | Mendoza Morales, Jesus A |  | 50.18
PR | 998 | 02/14/25 | 240 | Perez Araque, Manuel A |  | 76.5
PR | 998 | 02/14/25 | 241 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 02/14/25 | 246 | Silva Morales, Jair J |  | 104.04
PR | 998 | 02/14/25 | 249 | Taylor, Evan R |  | 31.82
PR | 998 | 02/21/25 | 311 | Anderson, Richard P |  | 4.97
PR | 998 | 02/21/25 | 318 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 02/21/25 | 319 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 02/21/25 | 320 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 02/21/25 | 321 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 02/21/25 | 325 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/21/25 | 326 | Barnhart, Joseph N |  | 15.61
PR | 998 | 02/21/25 | 327 | Bautista Quintero, Isidoro |  | 62.27
PR | 998 | 02/21/25 | 327 | Bautista Quintero, Isidoro |  | 5.05
PR | 998 | 02/21/25 | 328 | Carmona, Raul O |  | 129.74
PR | 998 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 141.98
PR | 998 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 02/21/25 | 332 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 02/21/25 | 334 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 02/21/25 | 336 | Draves, Steven W |  | 67.32
PR | 998 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 36.95
PR | 998 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/21/25 | 341 | Gerard, Jordan E |  | 36.72
PR | 998 | 02/21/25 | 342 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 02/21/25 | 345 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 02/21/25 | 348 | Johnson, Jake E |  | 19.89
PR | 998 | 02/21/25 | 354 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 02/21/25 | 358 | Perez Araque, Manuel A |  | 61.2
PR | 998 | 02/21/25 | 359 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 02/21/25 | 364 | Silva Morales, Jair J |  | 104.04
PR | 998 | 02/21/25 | 367 | Taylor, Evan R |  | 95.47
PR | 998 | 02/28/25 | 508 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 02/28/25 | 509 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 02/28/25 | 510 | Waites, Thaddeus Z |  | 112
PR | 998 | 02/28/25 | 511 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 02/28/25 | 515 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 36.41
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 10.4
PR | 998 | 02/28/25 | 517 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 02/28/25 | 518 | Carmona, Raul O |  | 162.18
PR | 998 | 02/28/25 | 521 | Cornejo Orellana, Carlos E |  | 64.26
PR | 998 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 127.3
PR | 998 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 34.27
PR | 998 | 02/28/25 | 522 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 02/28/25 | 524 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 02/28/25 | 526 | Draves, Steven W |  | 134.64
PR | 998 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 02/28/25 | 532 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 02/28/25 | 535 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 02/28/25 | 537 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 02/28/25 | 538 | Johnson, Jake E |  | 19.89
PR | 998 | 02/28/25 | 544 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 02/28/25 | 548 | Perez Araque, Manuel A |  | 76.5
PR | 998 | 02/28/25 | 549 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 02/28/25 | 551 | Rodriguez Arevalos, Christian |  | 93.64
PR | 998 | 02/28/25 | 554 | Silva Morales, Jair J |  | 104.04
PR | 998 | 02/28/25 | 557 | Taylor, Evan R |  | 159.12
PR | 998 | 03/07/25 | 18 | Cruz Reyes, Jose |  | 50.18
PR | 998 | 03/07/25 | 21 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 03/07/25 | 22 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 03/07/25 | 23 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A |  | 113.14
PR | 998 | 03/07/25 | 24 | Amaya Gonzalez, Edilberto A |  | 11.7
PR | 998 | 03/07/25 | 28 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/07/25 | 29 | Barnhart, Joseph N |  | 18.21
PR | 998 | 03/07/25 | 30 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 03/07/25 | 31 | Carmona, Raul O |  | 162.18
PR | 998 | 03/07/25 | 34 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 151.78
PR | 998 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 29.38
PR | 998 | 03/07/25 | 35 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 03/07/25 | 37 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 03/07/25 | 39 | Draves, Steven W |  | 67.32
PR | 998 | 03/07/25 | 43 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/07/25 | 43 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 03/07/25 | 45 | Gochez Molina, Douglas O |  | 61.2
PR | 998 | 03/07/25 | 48 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 03/07/25 | 50 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 03/07/25 | 51 | Johnson, Jake E |  | 27.85
PR | 998 | 03/07/25 | 52 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 03/07/25 | 57 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 03/07/25 | 61 | Perez Araque, Manuel A |  | 45.9
PR | 998 | 03/07/25 | 61 | Perez Araque, Manuel A |  | 30.6
PR | 998 | 03/07/25 | 62 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 03/07/25 | 64 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 03/07/25 | 67 | Silva Morales, Jair J |  | 104.04
PR | 998 | 03/07/25 | 68 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/07/25 | 70 | Taylor, Evan R |  | 95.47
PR | 998 | 03/07/25 | 78 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 03/14/25 | 222 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 03/14/25 | 223 | Waites, Thaddeus Z |  | 107.33
PR | 998 | 03/14/25 | 224 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 03/14/25 | 228 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/14/25 | 229 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/14/25 | 229 | Barnhart, Joseph N |  | 52.02
PR | 998 | 03/14/25 | 229 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/14/25 | 230 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 03/14/25 | 231 | Carmona, Raul O |  | 162.18
PR | 998 | 03/14/25 | 234 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 03/14/25 | 235 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 03/14/25 | 235 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 03/14/25 | 237 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 03/14/25 | 239 | Draves, Steven W |  | 159.89
PR | 998 | 03/14/25 | 243 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 03/14/25 | 243 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 03/14/25 | 245 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/14/25 | 248 | Guerrero Espinoza, Mario |  | 36.72
PR | 998 | 03/14/25 | 250 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/14/25 | 251 | Johnson, Jake E |  | 23.87
PR | 998 | 03/14/25 | 252 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 03/14/25 | 253 | Lopez, Maslin A |  | 40.39
PR | 998 | 03/14/25 | 257 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 03/14/25 | 260 | Paco Leyva, Orlando |  | 107.33
PR | 998 | 03/14/25 | 261 | Perez Araque, Manuel A |  | 76.5
PR | 998 | 03/14/25 | 262 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 03/14/25 | 264 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 03/14/25 | 267 | Silva Morales, Jair J |  | 83.23
PR | 998 | 03/14/25 | 268 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/14/25 | 270 | Taylor, Evan R |  | 151.16
PR | 998 | 03/14/25 | 278 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 03/14/25 | 401 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 03/14/25 | 404 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 03/14/25 | 405 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 03/14/25 | 406 | Waites, Thaddeus Z |  | 149.33
PR | 998 | 03/14/25 | 411 | Cruz Reyes, Jose |  | -100.37
PR | 998 | 03/14/25 | 414 | Galdamez, Dagoberto A |  | -128.52
PR | 998 | 03/14/25 | 415 | Hernandez Gonzalez, Osbaldo |  | -77.11
PR | 998 | 03/14/25 | 416 | Waites, Thaddeus Z |  | -149.33
PR | 998 | 03/21/25 | 417 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 03/21/25 | 420 | Ascencio, Jose L |  | 102.82
PR | 998 | 03/21/25 | 421 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/21/25 | 422 | Barnhart, Joseph N |  | 85.83
PR | 998 | 03/21/25 | 422 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/21/25 | 422 | Barnhart, Joseph N |  | 15.61
PR | 998 | 03/21/25 | 423 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 03/21/25 | 424 | Carmona, Raul O |  | 129.74
PR | 998 | 03/21/25 | 425 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 03/21/25 | 427 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 03/21/25 | 428 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 03/21/25 | 428 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 03/21/25 | 430 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 03/21/25 | 432 | Draves, Steven W |  | 168.3
PR | 998 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/21/25 | 438 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/21/25 | 441 | Guerrero Espinoza, Mario |  | 18.36
PR | 998 | 03/21/25 | 443 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/21/25 | 444 | Johnson, Jake E |  | 23.87
PR | 998 | 03/21/25 | 445 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 03/21/25 | 446 | Lopez, Maslin A |  | 20.2
PR | 998 | 03/21/25 | 450 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 03/21/25 | 453 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 03/21/25 | 454 | Perez Araque, Manuel A |  | 61.2
PR | 998 | 03/21/25 | 455 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 03/21/25 | 456 | Ramos Herrera, Franklin J |  | 77.11
PR | 998 | 03/21/25 | 458 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 03/21/25 | 461 | Silva Morales, Jair J |  | 104.04
PR | 998 | 03/21/25 | 462 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/21/25 | 464 | Taylor, Evan R |  | 159.12
PR | 998 | 03/21/25 | 472 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 03/21/25 | 477 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 03/21/25 | 480 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 03/21/25 | 481 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 03/21/25 | 482 | Waites, Thaddeus Z |  | 149.33
PR | 998 | 03/28/25 | 566 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 03/28/25 | 567 | Del Villar, Flabio |  | 15.3
PR | 998 | 03/28/25 | 569 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 03/28/25 | 570 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 03/28/25 | 571 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 03/28/25 | 572 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 03/28/25 | 575 | Ascencio, Jose L |  | 128.52
PR | 998 | 03/28/25 | 576 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 03/28/25 | 577 | Barnhart, Joseph N |  | 15.61
PR | 998 | 03/28/25 | 578 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 03/28/25 | 579 | Carmona, Raul O |  | 162.18
PR | 998 | 03/28/25 | 580 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 03/28/25 | 582 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 03/28/25 | 583 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 03/28/25 | 583 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 03/28/25 | 585 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 03/28/25 | 587 | Draves, Steven W |  | 134.64
PR | 998 | 03/28/25 | 591 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/28/25 | 591 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/28/25 | 593 | Gerard, Mitchell J |  | 112
PR | 998 | 03/28/25 | 594 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 03/28/25 | 597 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 03/28/25 | 599 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 03/28/25 | 600 | Johnson, Jake E |  | 35.8
PR | 998 | 03/28/25 | 601 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 03/28/25 | 602 | Lopez, Maslin A |  | 100.98
PR | 998 | 03/28/25 | 606 | Melgar Moz, Brandon |  | 13.46
PR | 998 | 03/28/25 | 607 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 03/28/25 | 610 | Paco Leyva, Orlando |  | 177.33
PR | 998 | 03/28/25 | 611 | Perez Araque, Manuel A |  | 76.5
PR | 998 | 03/28/25 | 612 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 03/28/25 | 613 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 03/28/25 | 615 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 03/28/25 | 617 | Ross, Kelli M |  | 31.21
PR | 998 | 03/28/25 | 618 | Silva Morales, Jair J |  | 104.04
PR | 998 | 03/28/25 | 619 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 03/28/25 | 621 | Taylor, Evan R |  | 127.3
PR | 998 | 03/28/25 | 629 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 04/04/25 | 9 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 04/04/25 | 10 | Del Villar, Flabio |  | 30.6
PR | 998 | 04/04/25 | 11 | Fox, Tamron P |  | 12.39
PR | 998 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 04/04/25 | 12 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 04/04/25 | 13 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 04/04/25 | 14 | Waites, Thaddeus Z |  | 144.66
PR | 998 | 04/04/25 | 15 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 04/04/25 | 18 | Ascencio, Jose L |  | 128.52
PR | 998 | 04/04/25 | 19 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/04/25 | 20 | Barnhart, Joseph N |  | 15.61
PR | 998 | 04/04/25 | 20 | Barnhart, Joseph N |  | 46.82
PR | 998 | 04/04/25 | 20 | Barnhart, Joseph N |  | 5.2
PR | 998 | 04/04/25 | 21 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 04/04/25 | 22 | Carmona, Raul O |  | 162.18
PR | 998 | 04/04/25 | 23 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 04/04/25 | 25 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 04/04/25 | 26 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 04/04/25 | 26 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 04/04/25 | 28 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 04/04/25 | 30 | Draves, Steven W |  | 168.3
PR | 998 | 04/04/25 | 34 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 04/04/25 | 34 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 04/04/25 | 36 | Gerard, Mitchell J |  | 186.66
PR | 998 | 04/04/25 | 37 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/04/25 | 40 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 04/04/25 | 42 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/04/25 | 43 | Johnson, Jake E |  | 27.85
PR | 998 | 04/04/25 | 44 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 04/04/25 | 45 | Lopez, Maslin A |  | 80.78
PR | 998 | 04/04/25 | 49 | Melgar Moz, Brandon |  | 26.93
PR | 998 | 04/04/25 | 50 | Mendoza Morales, Jesus A |  | 112.91
PR | 998 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 79.33
PR | 998 | 04/04/25 | 53 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 04/04/25 | 54 | Perez Araque, Manuel A |  | 76.5
PR | 998 | 04/04/25 | 55 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 04/04/25 | 56 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 04/04/25 | 57 | Reed, Reuben H |  | 28.46
PR | 998 | 04/04/25 | 58 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 04/04/25 | 60 | Ross, Kelli M |  | 156.06
PR | 998 | 04/04/25 | 61 | Silva Morales, Jair J |  | 83.23
PR | 998 | 04/04/25 | 62 | Suniga Aviles, Kelvin A |  | 61.05
PR | 998 | 04/04/25 | 64 | Taylor, Evan R |  | 127.3
PR | 998 | 04/04/25 | 71 | Zuniga Avilez, Eduar A |  | 63.95
PR | 998 | 04/11/25 | 172 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 04/11/25 | 173 | Del Villar, Flabio |  | 134.64
PR | 998 | 04/11/25 | 174 | Fox, Tamron P |  | 45.44
PR | 998 | 04/11/25 | 175 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 04/11/25 | 175 | Galdamez, Dagoberto A |  | 51.41
PR | 998 | 04/11/25 | 176 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 04/11/25 | 177 | Waites, Thaddeus Z |  | 165.66
PR | 998 | 04/11/25 | 195 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 04/11/25 | 198 | Ascencio, Jose L |  | 128.52
PR | 998 | 04/11/25 | 199 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/11/25 | 200 | Barnhart, Joseph N |  | 31.21
PR | 998 | 04/11/25 | 200 | Barnhart, Joseph N |  | 5.2
PR | 998 | 04/11/25 | 201 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 04/11/25 | 202 | Carmona, Raul O |  | 162.18
PR | 998 | 04/11/25 | 203 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 04/11/25 | 205 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 04/11/25 | 206 | Cortes Mendiola, Victor H |  | 181.15
PR | 998 | 04/11/25 | 206 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 04/11/25 | 208 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 04/11/25 | 210 | Draves, Steven W |  | 100.98
PR | 998 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 04/11/25 | 216 | Gerard, Mitchell J |  | 186.66
PR | 998 | 04/11/25 | 217 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/11/25 | 220 | Guerrero Espinoza, Mario |  | 36.72
PR | 998 | 04/11/25 | 222 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/11/25 | 223 | Johnson, Jake E |  | 27.85
PR | 998 | 04/11/25 | 224 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 04/11/25 | 225 | Lopez, Maslin A |  | 100.98
PR | 998 | 04/11/25 | 228 | McCabe, Thomas C |  | 80.78
PR | 998 | 04/11/25 | 229 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 04/11/25 | 230 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 04/11/25 | 231 | Merino Martinez, Humberto |  | 34.27
PR | 998 | 04/11/25 | 233 | Paco Leyva, Orlando |  | 186.66
PR | 998 | 04/11/25 | 234 | Perez Araque, Manuel A |  | 30.6
PR | 998 | 04/11/25 | 235 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 04/11/25 | 236 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 04/11/25 | 237 | Reed, Reuben H |  | 104.35
PR | 998 | 04/11/25 | 238 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 04/11/25 | 240 | Ross, Kelli M |  | 124.85
PR | 998 | 04/11/25 | 241 | Silva Morales, Jair J |  | 104.04
PR | 998 | 04/11/25 | 242 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 04/11/25 | 244 | Taylor, Evan R |  | 127.3
PR | 998 | 04/11/25 | 251 | Zuniga Avilez, Eduar A |  | 53.86
PR | 998 | 04/18/25 | 413 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 04/18/25 | 414 | Del Villar, Flabio |  | 67.32
PR | 998 | 04/18/25 | 415 | Fox, Tamron P |  | 33.05
PR | 998 | 04/18/25 | 416 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 04/18/25 | 417 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 04/18/25 | 418 | Waites, Thaddeus Z |  | 167.99
PR | 998 | 04/18/25 | 419 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 04/18/25 | 422 | Ascencio, Jose L |  | 128.52
PR | 998 | 04/18/25 | 423 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/18/25 | 424 | Barnhart, Joseph N |  | 78.03
PR | 998 | 04/18/25 | 425 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 04/18/25 | 426 | Carmona, Raul O |  | 162.18
PR | 998 | 04/18/25 | 427 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 04/18/25 | 429 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 04/18/25 | 430 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 04/18/25 | 432 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 04/18/25 | 434 | Draves, Steven W |  | 134.64
PR | 998 | 04/18/25 | 438 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 04/18/25 | 438 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 04/18/25 | 440 | Gerard, Mitchell J |  | 186.66
PR | 998 | 04/18/25 | 441 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/18/25 | 444 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 04/18/25 | 446 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/18/25 | 447 | Johnson, Jake E |  | 31.82
PR | 998 | 04/18/25 | 448 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 04/18/25 | 448 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 04/18/25 | 449 | Lopez, Maslin A |  | 80.78
PR | 998 | 04/18/25 | 452 | McCabe, Thomas C |  | 134.64
PR | 998 | 04/18/25 | 453 | Melgar Moz, Brandon |  | 47.12
PR | 998 | 04/18/25 | 454 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 04/18/25 | 455 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 04/18/25 | 457 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 04/18/25 | 459 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 04/18/25 | 460 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 04/18/25 | 461 | Reed, Reuben H |  | 75.89
PR | 998 | 04/18/25 | 462 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 04/18/25 | 464 | Ross, Kelli M |  | 156.06
PR | 998 | 04/18/25 | 465 | Silva Morales, Jair J |  | 104.04
PR | 998 | 04/18/25 | 466 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 04/18/25 | 468 | Taylor, Evan R |  | 63.65
PR | 998 | 04/18/25 | 475 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 04/25/25 | 550 | Castro, Marcus J |  | 26.93
PR | 998 | 04/25/25 | 552 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 04/25/25 | 553 | Del Villar, Flabio |  | 80.78
PR | 998 | 04/25/25 | 554 | Fox, Tamron P |  | 49.57
PR | 998 | 04/25/25 | 555 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 04/25/25 | 556 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 04/25/25 | 557 | Waites, Thaddeus Z |  | 158.66
PR | 998 | 04/25/25 | 558 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 04/25/25 | 559 | Aquino, Juan |  | 39.24
PR | 998 | 04/25/25 | 561 | Ascencio, Jose L |  | 128.52
PR | 998 | 04/25/25 | 562 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 04/25/25 | 563 | Barnhart, Joseph N |  | 57.22
PR | 998 | 04/25/25 | 564 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 04/25/25 | 565 | Carmona, Raul O |  | 162.18
PR | 998 | 04/25/25 | 566 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 04/25/25 | 568 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 146.88
PR | 998 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 04/25/25 | 569 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 04/25/25 | 571 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 04/25/25 | 573 | Draves, Steven W |  | 122.02
PR | 998 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 04/25/25 | 579 | Gerard, Mitchell J |  | 186.66
PR | 998 | 04/25/25 | 580 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 04/25/25 | 583 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 04/25/25 | 585 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 04/25/25 | 586 | Johnson, Jake E |  | 7.96
PR | 998 | 04/25/25 | 587 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 04/25/25 | 588 | Lopez, Maslin A |  | 100.98
PR | 998 | 04/25/25 | 591 | McCabe, Thomas C |  | 134.64
PR | 998 | 04/25/25 | 592 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 04/25/25 | 593 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 04/25/25 | 594 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 04/25/25 | 596 | Paco Leyva, Orlando |  | 112
PR | 998 | 04/25/25 | 598 | Portillo Soriano, Walter A |  | 85.68
PR | 998 | 04/25/25 | 599 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 04/25/25 | 600 | Reed, Reuben H |  | 113.83
PR | 998 | 04/25/25 | 601 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 04/25/25 | 603 | Ross, Kelli M |  | 62.42
PR | 998 | 04/25/25 | 604 | Silva Morales, Jair J |  | 104.04
PR | 998 | 04/25/25 | 605 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 04/25/25 | 607 | Taylor, Evan R |  | 95.47
PR | 998 | 04/25/25 | 614 | Zuniga Avilez, Eduar A |  | 53.86
PR | 998 | 05/02/25 | 4 | Castro, Marcus J |  | 26.93
PR | 998 | 05/02/25 | 6 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 05/02/25 | 8 | Fox, Tamron P |  | 16.52
PR | 998 | 05/02/25 | 9 | Galdamez, Dagoberto A |  | 102.82
PR | 998 | 05/02/25 | 9 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 05/02/25 | 10 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 05/02/25 | 11 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 05/02/25 | 12 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 05/02/25 | 13 | Aquino, Juan |  | 16.52
PR | 998 | 05/02/25 | 15 | Ascencio, Jose L |  | 102.82
PR | 998 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 05/02/25 | 16 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 05/02/25 | 17 | Barnhart, Joseph N |  | 33.81
PR | 998 | 05/02/25 | 18 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 05/02/25 | 19 | Carmona, Raul O |  | 129.74
PR | 998 | 05/02/25 | 20 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 05/02/25 | 22 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 05/02/25 | 23 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 05/02/25 | 25 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 05/02/25 | 27 | Draves, Steven W |  | 155.68
PR | 998 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/02/25 | 31 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/02/25 | 33 | Gerard, Mitchell J |  | 186.66
PR | 998 | 05/02/25 | 34 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/02/25 | 37 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 05/02/25 | 39 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/02/25 | 40 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 05/02/25 | 41 | Lopez, Maslin A |  | 70.69
PR | 998 | 05/02/25 | 44 | McCabe, Thomas C |  | 134.64
PR | 998 | 05/02/25 | 45 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/02/25 | 46 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 05/02/25 | 47 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 05/02/25 | 49 | Paco Leyva, Orlando |  | 163.33
PR | 998 | 05/02/25 | 51 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/02/25 | 52 | Ramos Herrera, Franklin J |  | 77.11
PR | 998 | 05/02/25 | 52 | Ramos Herrera, Franklin J |  | 25.7
PR | 998 | 05/02/25 | 54 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 05/02/25 | 56 | Ross, Kelli M |  | 124.85
PR | 998 | 05/02/25 | 57 | Silva Morales, Jair J |  | 104.04
PR | 998 | 05/02/25 | 58 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 05/02/25 | 60 | Taylor, Evan R |  | 159.12
PR | 998 | 05/02/25 | 66 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 05/09/25 | 151 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 05/09/25 | 153 | Fox, Tamron P |  | 33.05
PR | 998 | 05/09/25 | 154 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 05/09/25 | 155 | Hernandez Gonzalez, Osbaldo |  | 25.7
PR | 998 | 05/09/25 | 156 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 05/09/25 | 157 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 05/09/25 | 160 | Ascencio, Jose L |  | 102.82
PR | 998 | 05/09/25 | 161 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 57.22
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 5.2
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/09/25 | 163 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 05/09/25 | 164 | Carmona, Raul O |  | 162.18
PR | 998 | 05/09/25 | 165 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 05/09/25 | 166 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 166.46
PR | 998 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 05/09/25 | 167 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 05/09/25 | 169 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 05/09/25 | 171 | Draves, Steven W |  | 88.36
PR | 998 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/09/25 | 175 | Gerard, Jordan E |  | 36.72
PR | 998 | 05/09/25 | 176 | Gerard, Mitchell J |  | 149.33
PR | 998 | 05/09/25 | 177 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/09/25 | 180 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 05/09/25 | 182 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 05/09/25 | 183 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 05/09/25 | 184 | Lopez, Maslin A |  | 60.59
PR | 998 | 05/09/25 | 187 | McCabe, Thomas C |  | 134.64
PR | 998 | 05/09/25 | 188 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/09/25 | 189 | Mendoza Morales, Jesus A |  | 100.37
PR | 998 | 05/09/25 | 190 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 05/09/25 | 192 | Paco Leyva, Orlando |  | 149.33
PR | 998 | 05/09/25 | 194 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/09/25 | 195 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 05/09/25 | 196 | Reed, Reuben H |  | 75.89
PR | 998 | 05/09/25 | 197 | Rodriguez Arevalos, Christian |  | 124.85
PR | 998 | 05/09/25 | 199 | Ross, Kelli M |  | 156.06
PR | 998 | 05/09/25 | 200 | Silva Morales, Jair J |  | 104.04
PR | 998 | 05/09/25 | 201 | Suniga Aviles, Kelvin A |  | 64.26
PR | 998 | 05/09/25 | 203 | Taylor, Evan R |  | 127.3
PR | 998 | 05/09/25 | 207 | Zuniga Avilez, Eduar A |  | 67.32
PR | 998 | 05/16/25 | 350 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 05/16/25 | 353 | Galdamez, Dagoberto A |  | 128.52
PR | 998 | 05/16/25 | 354 | Hernandez Gonzalez, Osbaldo |  | 128.52
PR | 998 | 05/16/25 | 355 | Waites, Thaddeus Z |  | 84
PR | 998 | 05/16/25 | 356 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 05/16/25 | 359 | Ascencio, Jose L |  | 128.52
PR | 998 | 05/16/25 | 360 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/16/25 | 361 | Barnhart, Joseph N |  | 31.21
PR | 998 | 05/16/25 | 362 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 05/16/25 | 363 | Carmona, Raul O |  | 162.18
PR | 998 | 05/16/25 | 364 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 05/16/25 | 365 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 117.5
PR | 998 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 05/16/25 | 366 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 05/16/25 | 368 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 05/16/25 | 370 | Draves, Steven W |  | 67.32
PR | 998 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 23.75
PR | 998 | 05/16/25 | 373 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/16/25 | 375 | Gerard, Mitchell J |  | 186.66
PR | 998 | 05/16/25 | 376 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/16/25 | 379 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 05/16/25 | 381 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 05/16/25 | 382 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 05/16/25 | 383 | Lopez, Maslin A |  | 80.78
PR | 998 | 05/16/25 | 386 | McCabe, Thomas C |  | 134.64
PR | 998 | 05/16/25 | 387 | Melgar Moz, Brandon |  | 67.32
PR | 998 | 05/16/25 | 388 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 05/16/25 | 389 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 112
PR | 998 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 28
PR | 998 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 9.33
PR | 998 | 05/16/25 | 391 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 05/16/25 | 393 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/16/25 | 394 | Ramos Herrera, Franklin J |  | 77.11
PR | 998 | 05/16/25 | 394 | Ramos Herrera, Franklin J |  | 51.41
PR | 998 | 05/16/25 | 395 | Reed, Reuben H |  | 75.89
PR | 998 | 05/16/25 | 396 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 05/16/25 | 398 | Ross, Kelli M |  | 156.06
PR | 998 | 05/16/25 | 399 | Silva Morales, Jair J |  | 104.04
PR | 998 | 05/16/25 | 400 | Suniga Aviles, Kelvin A |  | 51.41
PR | 998 | 05/16/25 | 402 | Taylor, Evan R |  | 95.47
PR | 998 | 05/16/25 | 406 | Zuniga Avilez, Eduar A |  | 53.86
PR | 998 | 05/23/25 | 446 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 05/23/25 | 447 | Del Villar, Flabio |  | 26.93
PR | 998 | 05/23/25 | 448 | Fox, Tamron P |  | 47.51
PR | 998 | 05/23/25 | 449 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 05/23/25 | 449 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 05/23/25 | 450 | Hernandez Gonzalez, Osbaldo |  | 102.82
PR | 998 | 05/23/25 | 451 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 05/23/25 | 452 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 05/23/25 | 455 | Ascencio, Jose L |  | 128.52
PR | 998 | 05/23/25 | 456 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 05/23/25 | 457 | Barnhart, Joseph N |  | 15.61
PR | 998 | 05/23/25 | 457 | Barnhart, Joseph N |  | 10.4
PR | 998 | 05/23/25 | 458 | Bautista Quintero, Isidoro |  | 67.32
PR | 998 | 05/23/25 | 459 | Carmona, Raul O |  | 129.74
PR | 998 | 05/23/25 | 459 | Carmona, Raul O |  | 32.44
PR | 998 | 05/23/25 | 460 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 05/23/25 | 460 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 05/23/25 | 461 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 29.38
PR | 998 | 05/23/25 | 462 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 05/23/25 | 464 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 05/23/25 | 466 | Draves, Steven W |  | 164.09
PR | 998 | 05/23/25 | 469 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 05/23/25 | 469 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 05/23/25 | 470 | Gerard, Jordan E |  | 27.54
PR | 998 | 05/23/25 | 471 | Gerard, Mitchell J |  | 149.33
PR | 998 | 05/23/25 | 471 | Gerard, Mitchell J |  | 18.67
PR | 998 | 05/23/25 | 472 | Gochez Molina, Douglas O |  | 76.5
PR | 998 | 05/23/25 | 475 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 05/23/25 | 477 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 05/23/25 | 478 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 05/23/25 | 479 | Lopez, Maslin A |  | 100.98
PR | 998 | 05/23/25 | 482 | McCabe, Thomas C |  | 134.64
PR | 998 | 05/23/25 | 483 | Melgar Moz, Brandon |  | 53.86
PR | 998 | 05/23/25 | 484 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 05/23/25 | 485 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 37.33
PR | 998 | 05/23/25 | 487 | Paco Leyva, Orlando |  | 23.33
PR | 998 | 05/23/25 | 489 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 05/23/25 | 490 | Ramos Herrera, Franklin J |  | 128.52
PR | 998 | 05/23/25 | 491 | Reed, Reuben H |  | 71.15
PR | 998 | 05/23/25 | 492 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 05/23/25 | 494 | Ross, Kelli M |  | 124.85
PR | 998 | 05/23/25 | 495 | Silva Morales, Jair J |  | 104.04
PR | 998 | 05/23/25 | 496 | Suniga Aviles, Kelvin A |  | 54.62
PR | 998 | 05/23/25 | 498 | Taylor, Evan R |  | 159.12
PR | 998 | 05/23/25 | 502 | Zuniga Avilez, Eduar A |  | 40.39
PR | 998 | 05/30/25 | 535 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 05/30/25 | 537 | Galdamez, Dagoberto A |  | 25.7
PR | 998 | 05/30/25 | 538 | Hernandez Gonzalez, Osbaldo |  | 25.7
PR | 998 | 05/30/25 | 539 | Waites, Thaddeus Z |  | 112
PR | 998 | 05/30/25 | 540 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 05/30/25 | 543 | Ascencio, Jose L |  | 77.11
PR | 998 | 05/30/25 | 544 | Balderas Ortiz, Ricardo I |  | 80.78
PR | 998 | 05/30/25 | 545 | Barnhart, Joseph N |  | 36.41
PR | 998 | 05/30/25 | 546 | Bautista Quintero, Isidoro |  | 40.39
PR | 998 | 05/30/25 | 547 | Carmona, Raul O |  | 97.31
PR | 998 | 05/30/25 | 548 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 05/30/25 | 549 | Cornejo Orellana, Carlos E |  | 64.26
PR | 998 | 05/30/25 | 550 | Cortes Mendiola, Victor H |  | 117.5
PR | 998 | 05/30/25 | 552 | Cruz Guzman, Joel A |  | 62.42
PR | 998 | 05/30/25 | 554 | Draves, Steven W |  | 100.98
PR | 998 | 05/30/25 | 558 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/30/25 | 558 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/30/25 | 559 | Gerard, Jordan E |  | 4.59
PR | 998 | 05/30/25 | 560 | Gerard, Mitchell J |  | 112
PR | 998 | 05/30/25 | 561 | Gochez Molina, Douglas O |  | 45.9
PR | 998 | 05/30/25 | 564 | Guerrero Espinoza, Mario |  | 55.08
PR | 998 | 05/30/25 | 566 | Jimenez Alvarenga, Gerson M |  | 71.6
PR | 998 | 05/30/25 | 567 | Lima Romero, Melvin A |  | 80.78
PR | 998 | 05/30/25 | 568 | Lopez, Maslin A |  | 60.59
PR | 998 | 05/30/25 | 571 | McCabe, Thomas C |  | 80.78
PR | 998 | 05/30/25 | 572 | Melgar Moz, Brandon |  | 13.46
PR | 998 | 05/30/25 | 573 | Mendoza Morales, Jesus A |  | 75.28
PR | 998 | 05/30/25 | 574 | Merino Martinez, Humberto |  | 51.41
PR | 998 | 05/30/25 | 576 | Paco Leyva, Orlando |  | 18.67
PR | 998 | 05/30/25 | 578 | Portillo Soriano, Walter A |  | 64.26
PR | 998 | 05/30/25 | 579 | Ramos Herrera, Franklin J |  | 77.11
PR | 998 | 05/30/25 | 581 | Rodriguez Arevalos, Christian |  | 93.64
PR | 998 | 05/30/25 | 583 | Ross, Kelli M |  | 93.64
PR | 998 | 05/30/25 | 584 | Silva Morales, Jair J |  | 62.42
PR | 998 | 05/30/25 | 585 | Suniga Aviles, Kelvin A |  | 38.56
PR | 998 | 05/30/25 | 587 | Taylor, Evan R |  | 95.47
PR | 998 | 05/30/25 | 591 | Zuniga Avilez, Eduar A |  | 40.39
PR | 998 | 06/06/25 | 22 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 06/06/25 | 25 | Hernandez Gonzalez, Osbaldo |  | 77.11
PR | 998 | 06/06/25 | 26 | Waites, Thaddeus Z |  | 163.33
PR | 998 | 06/06/25 | 28 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 06/06/25 | 31 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/06/25 | 32 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/06/25 | 33 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/06/25 | 33 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/06/25 | 34 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 06/06/25 | 35 | Carmona, Raul O |  | 162.18
PR | 998 | 06/06/25 | 36 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/06/25 | 37 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 06/06/25 | 38 | Cortes Mendiola, Victor H |  | 186.05
PR | 998 | 06/06/25 | 38 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 06/06/25 | 40 | Cruz Guzman, Joel A |  | 62.42
PR | 998 | 06/06/25 | 42 | Draves, Steven W |  | 134.64
PR | 998 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 06/06/25 | 46 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/06/25 | 48 | Gerard, Mitchell J |  | 186.66
PR | 998 | 06/06/25 | 49 | Gochez Molina, Douglas O |  | 85.68
PR | 998 | 06/06/25 | 51 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 06/06/25 | 53 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 06/06/25 | 54 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 06/06/25 | 55 | Lopez, Maslin A |  | 80.78
PR | 998 | 06/06/25 | 58 | McCabe, Thomas C |  | 134.64
PR | 998 | 06/06/25 | 60 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 06/06/25 | 61 | Merino Martinez, Humberto |  | 34.27
PR | 998 | 06/06/25 | 61 | Merino Martinez, Humberto |  | 51.41
PR | 998 | 06/06/25 | 65 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/06/25 | 66 | Ramos Herrera, Franklin J |  | 102.82
PR | 998 | 06/06/25 | 68 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 06/06/25 | 70 | Ross, Kelli M |  | 93.64
PR | 998 | 06/06/25 | 71 | Silva Morales, Jair J |  | 104.04
PR | 998 | 06/06/25 | 72 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 06/06/25 | 74 | Taylor, Evan R |  | 95.47
PR | 998 | 06/06/25 | 78 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 06/13/25 | 184 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 06/13/25 | 186 | Galdamez, Dagoberto A |  | 77.11
PR | 998 | 06/13/25 | 187 | Hernandez Gonzalez, Osbaldo |  | 102.82
PR | 998 | 06/13/25 | 188 | Waites, Thaddeus Z |  | 186.66
PR | 998 | 06/13/25 | 189 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 06/13/25 | 192 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/13/25 | 193 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/13/25 | 195 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 06/13/25 | 196 | Carmona, Raul O |  | 162.18
PR | 998 | 06/13/25 | 197 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/13/25 | 198 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 06/13/25 | 199 | Cortes Mendiola, Victor H |  | 171.36
PR | 998 | 06/13/25 | 199 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 06/13/25 | 201 | Cruz Guzman, Joel A |  | 93.64
PR | 998 | 06/13/25 | 203 | Draves, Steven W |  | 67.32
PR | 998 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 06/13/25 | 208 | Gerard, Jordan E |  | 32.13
PR | 998 | 06/13/25 | 209 | Gerard, Mitchell J |  | 186.66
PR | 998 | 06/13/25 | 210 | Gochez Molina, Douglas O |  | 85.68
PR | 998 | 06/13/25 | 213 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 06/13/25 | 215 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 06/13/25 | 216 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 06/13/25 | 217 | Lopez, Maslin A |  | 60.59
PR | 998 | 06/13/25 | 220 | McCabe, Thomas C |  | 134.64
PR | 998 | 06/13/25 | 222 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 06/13/25 | 223 | Merino Martinez, Humberto |  | 51.41
PR | 998 | 06/13/25 | 223 | Merino Martinez, Humberto |  | 34.27
PR | 998 | 06/13/25 | 227 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/13/25 | 230 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 06/13/25 | 232 | Ross, Kelli M |  | 124.85
PR | 998 | 06/13/25 | 233 | Silva Morales, Jair J |  | 104.04
PR | 998 | 06/13/25 | 234 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 06/13/25 | 236 | Taylor, Evan R |  | 95.47
PR | 998 | 06/13/25 | 240 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 06/20/25 | 311 | Castro, Marcus J |  | 29.38
PR | 998 | 06/20/25 | 312 | Cruz Reyes, Jose |  | 75.28
PR | 998 | 06/20/25 | 316 | Waites, Thaddeus Z |  | 172.66
PR | 998 | 06/20/25 | 317 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 06/20/25 | 318 | Aquino, Juan |  | 17.14
PR | 998 | 06/20/25 | 320 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/20/25 | 321 | Balderas Ortiz, Ricardo I |  | 107.71
PR | 998 | 06/20/25 | 323 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 06/20/25 | 324 | Carmona, Raul O |  | 162.18
PR | 998 | 06/20/25 | 325 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 06/20/25 | 326 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 06/20/25 | 327 | Cortes Mendiola, Victor H |  | 146.88
PR | 998 | 06/20/25 | 327 | Cortes Mendiola, Victor H |  | 48.96
PR | 998 | 06/20/25 | 329 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 06/20/25 | 332 | Fox, Tamron P |  | 40.7
PR | 998 | 06/20/25 | 332 | Fox, Tamron P |  | 8.57
PR | 998 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/20/25 | 335 | Gerard, Jordan E |  | 32.13
PR | 998 | 06/20/25 | 336 | Gerard, Mitchell J |  | 186.66
PR | 998 | 06/20/25 | 337 | Gochez Molina, Douglas O |  | 85.68
PR | 998 | 06/20/25 | 340 | Guerrero Espinoza, Mario |  | 91.8
PR | 998 | 06/20/25 | 342 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 06/20/25 | 343 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 06/20/25 | 344 | Lopez, Maslin A |  | 40.39
PR | 998 | 06/20/25 | 347 | McCabe, Thomas C |  | 134.64
PR | 998 | 06/20/25 | 349 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 06/20/25 | 350 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 06/20/25 | 354 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/20/25 | 355 | Ramos Herrera, Franklin J |  | 77.11
PR | 998 | 06/20/25 | 356 | Reed, Reuben H |  | 90.12
PR | 998 | 06/20/25 | 356 | Reed, Reuben H |  | 18.97
PR | 998 | 06/20/25 | 357 | Rodriguez Arevalos, Christian |  | 124.85
PR | 998 | 06/20/25 | 359 | Ross, Kelli M |  | 124.85
PR | 998 | 06/20/25 | 360 | Silva Morales, Jair J |  | 83.23
PR | 998 | 06/20/25 | 361 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 06/20/25 | 363 | Taylor, Evan R |  | 95.47
PR | 998 | 06/20/25 | 366 | Young, Joshua S |  | 80.78
PR | 998 | 06/20/25 | 367 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 06/27/25 | 466 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 06/27/25 | 470 | Waites, Thaddeus Z |  | 167.99
PR | 998 | 06/27/25 | 471 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 06/27/25 | 474 | Ascencio, Jose L |  | 128.52
PR | 998 | 06/27/25 | 475 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 41.62
PR | 998 | 06/27/25 | 477 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 06/27/25 | 478 | Carmona, Raul O |  | 162.18
PR | 998 | 06/27/25 | 479 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 06/27/25 | 480 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 06/27/25 | 481 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 06/27/25 | 481 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 06/27/25 | 484 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 06/27/25 | 489 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 06/27/25 | 490 | Gerard, Jordan E |  | 9.18
PR | 998 | 06/27/25 | 491 | Gerard, Mitchell J |  | 149.33
PR | 998 | 06/27/25 | 491 | Gerard, Mitchell J |  | 37.33
PR | 998 | 06/27/25 | 492 | Gochez Molina, Douglas O |  | 85.68
PR | 998 | 06/27/25 | 495 | Guerrero Espinoza, Mario |  | 73.44
PR | 998 | 06/27/25 | 497 | Jimenez Alvarenga, Gerson M |  | 95.47
PR | 998 | 06/27/25 | 498 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 06/27/25 | 502 | McCabe, Thomas C |  | 134.64
PR | 998 | 06/27/25 | 504 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 06/27/25 | 505 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 06/27/25 | 509 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 06/27/25 | 510 | Ramos Herrera, Franklin J |  | 25.7
PR | 998 | 06/27/25 | 512 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 06/27/25 | 514 | Ross, Kelli M |  | 124.85
PR | 998 | 06/27/25 | 515 | Silva Morales, Jair J |  | 104.04
PR | 998 | 06/27/25 | 516 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 06/27/25 | 518 | Taylor, Evan R |  | 95.47
PR | 998 | 06/27/25 | 521 | Young, Joshua S |  | 26.93
PR | 998 | 06/27/25 | 522 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 07/03/25 | 10 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 07/03/25 | 14 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 07/03/25 | 18 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 07/03/25 | 20 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 07/03/25 | 21 | Carmona, Raul O |  | 162.18
PR | 998 | 07/03/25 | 22 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 07/03/25 | 23 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 07/03/25 | 24 | Cortes Mendiola, Victor H |  | 102.82
PR | 998 | 07/03/25 | 24 | Cortes Mendiola, Victor H |  | 93.02
PR | 998 | 07/03/25 | 27 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/03/25 | 32 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/03/25 | 33 | Gerard, Jordan E |  | 4.59
PR | 998 | 07/03/25 | 34 | Gerard, Mitchell J |  | 149.33
PR | 998 | 07/03/25 | 35 | Gochez Molina, Douglas O |  | 51.41
PR | 998 | 07/03/25 | 40 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 07/03/25 | 41 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 07/03/25 | 45 | McCabe, Thomas C |  | 134.64
PR | 998 | 07/03/25 | 47 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 07/03/25 | 48 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 07/03/25 | 52 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 07/03/25 | 55 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 07/03/25 | 57 | Ross, Kelli M |  | 124.85
PR | 998 | 07/03/25 | 58 | Silva Morales, Jair J |  | 83.23
PR | 998 | 07/03/25 | 59 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 07/03/25 | 61 | Taylor, Evan R |  | 95.47
PR | 998 | 07/03/25 | 63 | Waites, Thaddeus Z |  | 112
PR | 998 | 07/03/25 | 66 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 07/11/25 | 135 | Cruz Reyes, Jose |  | 97.23
PR | 998 | 07/11/25 | 139 | Amaya Gonzalez, Edilberto A |  | 120.95
PR | 998 | 07/11/25 | 143 | Balderas Ortiz, Ricardo I |  | 104.35
PR | 998 | 07/11/25 | 144 | Barnhart, Joseph N |  | 15.61
PR | 998 | 07/11/25 | 145 | Bautista Quintero, Isidoro |  | 56.92
PR | 998 | 07/11/25 | 146 | Carmona, Raul O |  | 125.69
PR | 998 | 07/11/25 | 147 | Castro Hernandez, Jose A |  | 128.06
PR | 998 | 07/11/25 | 148 | Cornejo Orellana, Carlos E |  | 61.58
PR | 998 | 07/11/25 | 149 | Cortes Mendiola, Victor H |  | 122.4
PR | 998 | 07/11/25 | 149 | Cortes Mendiola, Victor H |  | 29.38
PR | 998 | 07/11/25 | 152 | Cruz Guzman, Joel A |  | 120.95
PR | 998 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 07/11/25 | 157 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/11/25 | 158 | Gerard, Jordan E |  | 4.59
PR | 998 | 07/11/25 | 159 | Gerard, Mitchell J |  | 140
PR | 998 | 07/11/25 | 164 | Jimenez Alvarenga, Gerson M |  | 92.49
PR | 998 | 07/11/25 | 165 | Lima Romero, Melvin A |  | 77.42
PR | 998 | 07/11/25 | 169 | McCabe, Thomas C |  | 104.35
PR | 998 | 07/11/25 | 171 | Mendoza Morales, Jesus A |  | 97.23
PR | 998 | 07/11/25 | 172 | Merino Martinez, Humberto |  | 66.4
PR | 998 | 07/11/25 | 176 | Portillo Soriano, Walter A |  | 83
PR | 998 | 07/11/25 | 179 | Rodriguez Arevalos, Christian |  | 89.73
PR | 998 | 07/11/25 | 180 | Romero Garza, Jesus I |  | 5.05
PR | 998 | 07/11/25 | 181 | Ross, Kelli M |  | 89.73
PR | 998 | 07/11/25 | 182 | Silva Morales, Jair J |  | 80.63
PR | 998 | 07/11/25 | 183 | Suniga Aviles, Kelvin A |  | 56.92
PR | 998 | 07/11/25 | 185 | Taylor, Evan R |  | 59.67
PR | 998 | 07/11/25 | 187 | Waites, Thaddeus Z |  | 37.33
PR | 998 | 07/11/25 | 190 | Zuniga Avilez, Eduar A |  | 56.92
PR | 998 | 07/18/25 | 303 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 07/18/25 | 306 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 07/18/25 | 310 | Balderas Ortiz, Ricardo I |  | 134.64
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 26.01
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 5.2
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 2.6
PR | 998 | 07/18/25 | 311 | Barnhart, Joseph N |  | 13.01
PR | 998 | 07/18/25 | 312 | Bautista Quintero, Isidoro |  | 58.75
PR | 998 | 07/18/25 | 313 | Carmona, Raul O |  | 162.18
PR | 998 | 07/18/25 | 314 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 07/18/25 | 315 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 07/18/25 | 316 | Cortes Mendiola, Victor H |  | 176.26
PR | 998 | 07/18/25 | 316 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 07/18/25 | 319 | Cruz Guzman, Joel A |  | 93.64
PR | 998 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/18/25 | 325 | Gerard, Jordan E |  | 9.18
PR | 998 | 07/18/25 | 326 | Gerard, Mitchell J |  | 177.33
PR | 998 | 07/18/25 | 331 | Jimenez Alvarenga, Gerson M |  | 119.34
PR | 998 | 07/18/25 | 332 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 07/18/25 | 336 | McCabe, Thomas C |  | 134.64
PR | 998 | 07/18/25 | 338 | Mendoza Morales, Jesus A |  | 125.46
PR | 998 | 07/18/25 | 339 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 07/18/25 | 343 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 07/18/25 | 346 | Rodriguez Arevalos, Christian |  | 156.06
PR | 998 | 07/18/25 | 347 | Romero Garza, Jesus I |  | 22.72
PR | 998 | 07/18/25 | 348 | Ross, Kelli M |  | 93.64
PR | 998 | 07/18/25 | 349 | Silva Morales, Jair J |  | 104.04
PR | 998 | 07/18/25 | 350 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 07/18/25 | 352 | Taylor, Evan R |  | 95.47
PR | 998 | 07/18/25 | 354 | Waites, Thaddeus Z |  | 181.99
PR | 998 | 07/18/25 | 357 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 07/25/25 | 470 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 07/25/25 | 474 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 07/25/25 | 478 | Balderas Ortiz, Ricardo I |  | 26.93
PR | 998 | 07/25/25 | 480 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 07/25/25 | 481 | Carmona, Raul O |  | 129.74
PR | 998 | 07/25/25 | 482 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 07/25/25 | 483 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 07/25/25 | 484 | Cortes Mendiola, Victor H |  | 141.98
PR | 998 | 07/25/25 | 484 | Cortes Mendiola, Victor H |  | 53.86
PR | 998 | 07/25/25 | 487 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 07/25/25 | 492 | Gerard, Jeffrey S |  | 18.47
PR | 998 | 07/25/25 | 493 | Gerard, Jordan E |  | 27.54
PR | 998 | 07/25/25 | 494 | Gerard, Mitchell J |  | 186.66
PR | 998 | 07/25/25 | 499 | Jimenez Alvarenga, Gerson M |  | 47.74
PR | 998 | 07/25/25 | 500 | Lima Romero, Melvin A |  | 127.91
PR | 998 | 07/25/25 | 504 | McCabe, Thomas C |  | 134.64
PR | 998 | 07/25/25 | 506 | Mendoza Morales, Jesus A |  | 122.32
PR | 998 | 07/25/25 | 506 | Mendoza Morales, Jesus A |  | 3.14
PR | 998 | 07/25/25 | 507 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 07/25/25 | 511 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 07/25/25 | 514 | Rodriguez Arevalos, Christian |  | 31.21
PR | 998 | 07/25/25 | 516 | Ross, Kelli M |  | 93.64
PR | 998 | 07/25/25 | 517 | Silva Morales, Jair J |  | 104.04
PR | 998 | 07/25/25 | 518 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 07/25/25 | 520 | Waites, Thaddeus Z |  | 56
PR | 998 | 07/25/25 | 523 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 08/01/25 | 3 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 08/01/25 | 7 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 20.81
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/01/25 | 13 | Bautista Quintero, Isidoro |  | 44.06
PR | 998 | 08/01/25 | 13 | Bautista Quintero, Isidoro |  | 29.38
PR | 998 | 08/01/25 | 14 | Carmona, Raul O |  | 162.18
PR | 998 | 08/01/25 | 15 | Castro Hernandez, Jose A |  | 132.19
PR | 998 | 08/01/25 | 16 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 161.57
PR | 998 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 08/01/25 | 17 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 08/01/25 | 20 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 08/01/25 | 25 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 08/01/25 | 26 | Gerard, Jordan E |  | 13.77
PR | 998 | 08/01/25 | 27 | Gerard, Mitchell J |  | 186.66
PR | 998 | 08/01/25 | 33 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 08/01/25 | 37 | McCabe, Thomas C |  | 107.71
PR | 998 | 08/01/25 | 40 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 08/01/25 | 44 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 08/01/25 | 49 | Ross, Kelli M |  | 93.64
PR | 998 | 08/01/25 | 50 | Silva Morales, Jair J |  | 104.04
PR | 998 | 08/01/25 | 51 | Suniga Aviles, Kelvin A |  | 44.06
PR | 998 | 08/01/25 | 51 | Suniga Aviles, Kelvin A |  | 29.38
PR | 998 | 08/01/25 | 53 | Taylor, Evan R |  | 31.82
PR | 998 | 08/01/25 | 56 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 08/08/25 | 134 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 08/08/25 | 138 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 08/08/25 | 143 | Barnhart, Joseph N |  | 20.81
PR | 998 | 08/08/25 | 143 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/08/25 | 143 | Barnhart, Joseph N |  | 15.61
PR | 998 | 08/08/25 | 144 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 08/08/25 | 145 | Carmona, Raul O |  | 162.18
PR | 998 | 08/08/25 | 146 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 08/08/25 | 147 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 146.88
PR | 998 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 08/08/25 | 148 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 08/08/25 | 151 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 08/08/25 | 156 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/08/25 | 156 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/08/25 | 158 | Gerard, Mitchell J |  | 186.66
PR | 998 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 26.93
PR | 998 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/08/25 | 164 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 08/08/25 | 168 | McCabe, Thomas C |  | 134.64
PR | 998 | 08/08/25 | 171 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 08/08/25 | 175 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 08/08/25 | 180 | Ross, Kelli M |  | 93.64
PR | 998 | 08/08/25 | 181 | Silva Morales, Jair J |  | 104.04
PR | 998 | 08/08/25 | 182 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 08/08/25 | 184 | Taylor, Evan R |  | 63.65
PR | 998 | 08/08/25 | 187 | Zuniga Avilez, Eduar A |  | 44.06
PR | 998 | 08/08/25 | 187 | Zuniga Avilez, Eduar A |  | 29.38
PR | 998 | 08/15/25 | 260 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 08/15/25 | 263 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 08/15/25 | 268 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/15/25 | 269 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 08/15/25 | 270 | Carmona, Raul O |  | 162.18
PR | 998 | 08/15/25 | 271 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 08/15/25 | 272 | Cornejo Orellana, Carlos E |  | 85.68
PR | 998 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 146.88
PR | 998 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 08/15/25 | 273 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 08/15/25 | 276 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 08/15/25 | 281 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/15/25 | 281 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/15/25 | 282 | Gerard, Jordan E |  | 4.59
PR | 998 | 08/15/25 | 283 | Gerard, Mitchell J |  | 186.66
PR | 998 | 08/15/25 | 289 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 08/15/25 | 293 | McCabe, Thomas C |  | 80.78
PR | 998 | 08/15/25 | 293 | McCabe, Thomas C |  | 26.93
PR | 998 | 08/15/25 | 296 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 08/15/25 | 300 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 08/15/25 | 305 | Ross, Kelli M |  | 124.85
PR | 998 | 08/15/25 | 306 | Silva Morales, Jair J |  | 83.23
PR | 998 | 08/15/25 | 307 | Suniga Aviles, Kelvin A |  | 58.75
PR | 998 | 08/15/25 | 309 | Taylor, Evan R |  | 63.65
PR | 998 | 08/15/25 | 312 | Zuniga Avilez, Eduar A |  | 58.75
PR | 998 | 08/22/25 | 362 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 08/22/25 | 366 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 26.01
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/22/25 | 371 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/22/25 | 372 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 08/22/25 | 373 | Carmona, Raul O |  | 162.18
PR | 998 | 08/22/25 | 374 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 08/22/25 | 375 | Cornejo Orellana, Carlos E |  | 107.1
PR | 998 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 166.46
PR | 998 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 08/22/25 | 376 | Cortes Mendiola, Victor H |  | 4.9
PR | 998 | 08/22/25 | 379 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/22/25 | 385 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 08/22/25 | 386 | Gerard, Jordan E |  | 22.95
PR | 998 | 08/22/25 | 387 | Gerard, Mitchell J |  | 149.33
PR | 998 | 08/22/25 | 393 | Lima Romero, Melvin A |  | 107.71
PR | 998 | 08/22/25 | 397 | McCabe, Thomas C |  | 134.64
PR | 998 | 08/22/25 | 400 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 08/22/25 | 404 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 08/22/25 | 409 | Ross, Kelli M |  | 124.85
PR | 998 | 08/22/25 | 410 | Silva Morales, Jair J |  | 104.04
PR | 998 | 08/22/25 | 411 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 08/22/25 | 413 | Taylor, Evan R |  | 63.65
PR | 998 | 08/22/25 | 416 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 08/29/25 | 525 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 08/29/25 | 529 | Amaya Gonzalez, Edilberto A |  | 140.45
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/29/25 | 535 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 08/29/25 | 536 | Carmona, Raul O |  | 162.18
PR | 998 | 08/29/25 | 538 | Cornejo Orellana, Carlos E |  | 42.84
PR | 998 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 151.78
PR | 998 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 34.27
PR | 998 | 08/29/25 | 539 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 08/29/25 | 542 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 08/29/25 | 548 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 08/29/25 | 548 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/29/25 | 550 | Gerard, Mitchell J |  | 186.66
PR | 998 | 08/29/25 | 556 | Lima Romero, Melvin A |  | 134.64
PR | 998 | 08/29/25 | 560 | McCabe, Thomas C |  | 53.86
PR | 998 | 08/29/25 | 563 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 08/29/25 | 567 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 08/29/25 | 573 | Silva Morales, Jair J |  | 104.04
PR | 998 | 08/29/25 | 574 | Suniga Aviles, Kelvin A |  | 73.44
PR | 998 | 08/29/25 | 576 | Taylor, Evan R |  | 63.65
PR | 998 | 08/29/25 | 579 | Zuniga Avilez, Eduar A |  | 73.44
PR | 998 | 09/05/25 | 10 | Cruz Reyes, Jose |  | 100.37
PR | 998 | 09/05/25 | 14 | Amaya Gonzalez, Edilberto A |  | 124.85
PR | 998 | 09/05/25 | 19 | Barnhart, Joseph N |  | 20.81
PR | 998 | 09/05/25 | 19 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/05/25 | 19 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/05/25 | 20 | Bautista Quintero, Isidoro |  | 29.38
PR | 998 | 09/05/25 | 20 | Bautista Quintero, Isidoro |  | 29.38
PR | 998 | 09/05/25 | 21 | Carmona, Raul O |  | 129.74
PR | 998 | 09/05/25 | 22 | Castro Hernandez, Jose A |  | 99.14
PR | 998 | 09/05/25 | 24 | Cortes Mendiola, Victor H |  | 132.19
PR | 998 | 09/05/25 | 24 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 09/05/25 | 27 | Cruz Guzman, Joel A |  | 124.85
PR | 998 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/05/25 | 33 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/05/25 | 34 | Gerard, Jordan E |  | 32.13
PR | 998 | 09/05/25 | 35 | Gerard, Mitchell J |  | 140
PR | 998 | 09/05/25 | 41 | Lima Romero, Melvin A |  | 53.86
PR | 998 | 09/05/25 | 45 | McCabe, Thomas C |  | 80.78
PR | 998 | 09/05/25 | 48 | Merino Martinez, Humberto |  | 68.54
PR | 998 | 09/05/25 | 52 | Portillo Soriano, Walter A |  | 85.68
PR | 998 | 09/05/25 | 58 | Silva Morales, Jair J |  | 83.23
PR | 998 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 14.69
PR | 998 | 09/05/25 | 59 | Suniga Aviles, Kelvin A |  | 14.69
PR | 998 | 09/05/25 | 63 | Zuniga Avilez, Eduar A |  | 29.38
PR | 998 | 09/12/25 | 108 | Cruz Reyes, Jose |  | 125.46
PR | 998 | 09/12/25 | 111 | Amaya Gonzalez, Edilberto A |  | 156.06
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 52.02
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 31.21
PR | 998 | 09/12/25 | 117 | Bautista Quintero, Isidoro |  | 73.44
PR | 998 | 09/12/25 | 118 | Carmona, Raul O |  | 162.18
PR | 998 | 09/12/25 | 119 | Castro Hernandez, Jose A |  | 165.24
PR | 998 | 09/12/25 | 121 | Cortes Mendiola, Victor H |  | 117.5
PR | 998 | 09/12/25 | 124 | Cruz Guzman, Joel A |  | 156.06
PR | 998 | 09/12/25 | 130 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/12/25 | 131 | Gerard, Jordan E |  | 27.54
PR | 998 | 09/12/25 | 132 | Gerard, Mitchell J |  | 186.66
PR | 998 | 09/12/25 | 142 | McCabe, Thomas C |  | 134.64
PR | 998 | 09/12/25 | 145 | Merino Martinez, Humberto |  | 85.68
PR | 998 | 09/12/25 | 149 | Portillo Soriano, Walter A |  | 107.1
PR | 998 | 09/12/25 | 155 | Silva Morales, Jair J |  | 104.04
PR | 998 | 09/19/25 | 238 | Barnhart, Thomas L |  | 78.95
PR | 998 | 09/19/25 | 240 | Cruz Reyes, Jose |  | 116.05
PR | 998 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A |  | 93.64
PR | 998 | 09/19/25 | 243 | Amaya Gonzalez, Edilberto A |  | 11.7
PR | 998 | 09/19/25 | 248 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/19/25 | 248 | Barnhart, Joseph N |  | 10.4
PR | 998 | 09/19/25 | 248 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/19/25 | 249 | Bautista Quintero, Isidoro |  | 44.06
PR | 998 | 09/19/25 | 249 | Bautista Quintero, Isidoro |  | 23.87
PR | 998 | 09/19/25 | 250 | Carmona, Raul O |  | 150.02
PR | 998 | 09/19/25 | 251 | Castro Hernandez, Jose A |  | 152.85
PR | 998 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 156.67
PR | 998 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 19.58
PR | 998 | 09/19/25 | 253 | Cortes Mendiola, Victor H |  | 4.9
PR | 998 | 09/19/25 | 256 | Cruz Guzman, Joel A |  | 144.36
PR | 998 | 09/19/25 | 261 | Games, Jordan M |  | 20.27
PR | 998 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/19/25 | 262 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/19/25 | 263 | Gerard, Jordan E |  | 13.77
PR | 998 | 09/19/25 | 264 | Gerard, Mitchell J |  | 172.66
PR | 998 | 09/19/25 | 274 | McCabe, Thomas C |  | 107.71
PR | 998 | 09/19/25 | 277 | Merino Martinez, Humberto |  | 79.25
PR | 998 | 09/19/25 | 281 | Portillo Soriano, Walter A |  | 99.07
PR | 998 | 09/19/25 | 287 | Silva Morales, Jair J |  | 96.24
PR | 998 | 09/26/25 | 408 | Barnhart, Thomas L |  | 26.32
PR | 998 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/26/25 | 410 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 14.63
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 10.73
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 09/26/25 | 414 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 3.9
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 7.8
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 6.5
PR | 998 | 09/26/25 | 419 | Barnhart, Joseph N |  | 23.41
PR | 998 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 09/26/25 | 420 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 09/26/25 | 421 | Carmona, Raul O |  | 32.44
PR | 998 | 09/26/25 | 421 | Carmona, Raul O |  | 32.44
PR | 998 | 09/26/25 | 421 | Carmona, Raul O |  | 32.44
PR | 998 | 09/26/25 | 421 | Carmona, Raul O |  | 32.44
PR | 998 | 09/26/25 | 421 | Carmona, Raul O |  | 32.44
PR | 998 | 09/26/25 | 422 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 09/26/25 | 422 | Castro Hernandez, Jose A |  | 33.05
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 18.36
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 13.46
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 09/26/25 | 424 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 09/26/25 | 427 | Cruz Guzman, Joel A |  | 31.21
PR | 998 | 09/26/25 | 427 | Cruz Guzman, Joel A |  | 31.21
PR | 998 | 09/26/25 | 434 | Gerard, Jordan E |  | 9.18
PR | 998 | 09/26/25 | 435 | Gerard, Mitchell J |  | 37.33
PR | 998 | 09/26/25 | 435 | Gerard, Mitchell J |  | 37.33
PR | 998 | 09/26/25 | 435 | Gerard, Mitchell J |  | 37.33
PR | 998 | 09/26/25 | 435 | Gerard, Mitchell J |  | 37.33
PR | 998 | 09/26/25 | 435 | Gerard, Mitchell J |  | 37.33
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 26.93
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 6.73
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 8.42
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 5.05
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 6.73
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 4.21
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 11.78
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 4.21
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 5.89
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 2.52
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 18.51
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 9.26
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 6.73
PR | 998 | 09/26/25 | 445 | McCabe, Thomas C |  | 5.89
PR | 998 | 09/26/25 | 448 | Merino Martinez, Humberto |  | 17.14
PR | 998 | 09/26/25 | 448 | Merino Martinez, Humberto |  | 17.14
PR | 998 | 09/26/25 | 452 | Portillo Soriano, Walter A |  | 21.42
PR | 998 | 09/26/25 | 452 | Portillo Soriano, Walter A |  | 21.42
PR | 998 | 09/26/25 | 458 | Silva Morales, Jair J |  | 20.81
PR | 998 | 09/26/25 | 458 | Silva Morales, Jair J |  | 20.81
PR | 998 | 09/26/25 | 458 | Silva Morales, Jair J |  | 20.81
PR | 998 | 09/26/25 | 458 | Silva Morales, Jair J |  | 20.81
PR | 998 | 09/26/25 | 458 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/03/25 | 4 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/03/25 | 4 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/03/25 | 4 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/03/25 | 4 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/03/25 | 6 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 18.53
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 12.68
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/03/25 | 10 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 6.5
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 6.5
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 7.8
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 24.71
PR | 998 | 10/03/25 | 15 | Barnhart, Joseph N |  | 1.3
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 8.26
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 6.43
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 4.13
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 7.8
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/03/25 | 16 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/03/25 | 17 | Carmona, Raul O |  | 32.44
PR | 998 | 10/03/25 | 17 | Carmona, Raul O |  | 32.44
PR | 998 | 10/03/25 | 17 | Carmona, Raul O |  | 32.44
PR | 998 | 10/03/25 | 17 | Carmona, Raul O |  | 32.44
PR | 998 | 10/03/25 | 17 | Carmona, Raul O |  | 32.44
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 23.26
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 3.67
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 8.57
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 37.94
PR | 998 | 10/03/25 | 20 | Cortes Mendiola, Victor H |  | 1.84
PR | 998 | 10/03/25 | 27 | Eliassen, Cory H |  | 21.08
PR | 998 | 10/03/25 | 27 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/03/25 | 27 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/03/25 | 27 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/03/25 | 27 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 8.11
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/03/25 | 31 | Gerard, Jordan E |  | 3.44
PR | 998 | 10/03/25 | 32 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/03/25 | 32 | Gerard, Mitchell J |  | 30.33
PR | 998 | 10/03/25 | 32 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/03/25 | 32 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 26.93
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 10.1
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 1.68
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 5.05
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 4.21
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 10.1
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 9.26
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 8.42
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 19.35
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 5.05
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 7.57
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 14.31
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 2.52
PR | 998 | 10/03/25 | 42 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/03/25 | 55 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/03/25 | 55 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/03/25 | 55 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/03/25 | 55 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/03/25 | 55 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/10/25 | 156 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/10/25 | 156 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/10/25 | 156 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/10/25 | 156 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/10/25 | 156 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/10/25 | 158 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/10/25 | 162 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 16.91
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 31.21
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 7.8
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 2.6
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 2.6
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 2.6
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 14.31
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 6.5
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 4.13
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 5.51
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/10/25 | 168 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/10/25 | 169 | Carmona, Raul O |  | 32.44
PR | 998 | 10/10/25 | 169 | Carmona, Raul O |  | 32.44
PR | 998 | 10/10/25 | 169 | Carmona, Raul O |  | 32.44
PR | 998 | 10/10/25 | 169 | Carmona, Raul O |  | 32.44
PR | 998 | 10/10/25 | 169 | Carmona, Raul O |  | 32.44
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 11.02
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 14.69
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 30.6
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 3.67
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/10/25 | 172 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/10/25 | 179 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/10/25 | 179 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/10/25 | 179 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/10/25 | 179 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/10/25 | 179 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/10/25 | 182 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 1.17
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 35
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 38.5
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/10/25 | 184 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 17.14
PR | 998 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 17.14
PR | 998 | 10/10/25 | 185 | Gochez Molina, Douglas O |  | 17.14
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 13.46
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 1.68
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 11.78
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 12.62
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 0.84
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 13.46
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 15.15
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 17.67
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 0.84
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 0.84
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 7.57
PR | 998 | 10/10/25 | 195 | McCabe, Thomas C |  | 26.93
PR | 998 | 10/10/25 | 200 | Paco Leyva, Orlando |  | 2.33
PR | 998 | 10/10/25 | 208 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/10/25 | 208 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/10/25 | 208 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/10/25 | 208 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/17/25 | 360 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/17/25 | 360 | Barnhart, Thomas L |  | 23.03
PR | 998 | 10/17/25 | 360 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/17/25 | 360 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/17/25 | 360 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/17/25 | 362 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/17/25 | 363 | Da Cruz, Eduardo E |  | 14.08
PR | 998 | 10/17/25 | 363 | Da Cruz, Eduardo E |  | 4.84
PR | 998 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 7.8
PR | 998 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 17.56
PR | 998 | 10/17/25 | 367 | Amaya Gonzalez, Edilberto A |  | 17.56
PR | 998 | 10/17/25 | 369 | Araque, Mario W |  | 14.69
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 14.31
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 6.5
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 9.1
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 3.67
PR | 998 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 10.1
PR | 998 | 10/17/25 | 373 | Bautista Quintero, Isidoro |  | 5.05
PR | 998 | 10/17/25 | 374 | Carmona, Raul O |  | 32.44
PR | 998 | 10/17/25 | 374 | Carmona, Raul O |  | 32.44
PR | 998 | 10/17/25 | 374 | Carmona, Raul O |  | 32.44
PR | 998 | 10/17/25 | 374 | Carmona, Raul O |  | 32.44
PR | 998 | 10/17/25 | 374 | Carmona, Raul O |  | 32.44
PR | 998 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 22.03
PR | 998 | 10/17/25 | 377 | Cortes Mendiola, Victor H |  | 8.57
PR | 998 | 10/17/25 | 384 | Eliassen, Cory H |  | 11.63
PR | 998 | 10/17/25 | 384 | Eliassen, Cory H |  | 23.98
PR | 998 | 10/17/25 | 384 | Eliassen, Cory H |  | 23.98
PR | 998 | 10/17/25 | 384 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/17/25 | 384 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/17/25 | 386 | Games, Jordan M |  | 32.44
PR | 998 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/17/25 | 387 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/17/25 | 388 | Gerard, Jordan E |  | 4.59
PR | 998 | 10/17/25 | 388 | Gerard, Jordan E |  | 9.18
PR | 998 | 10/17/25 | 389 | Gerard, Mitchell J |  | 36.17
PR | 998 | 10/17/25 | 389 | Gerard, Mitchell J |  | 19.83
PR | 998 | 10/17/25 | 389 | Gerard, Mitchell J |  | 16.33
PR | 998 | 10/17/25 | 389 | Gerard, Mitchell J |  | 35
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 9.26
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 16.83
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 20.2
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 6.73
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 8.42
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 5.05
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 13.46
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 11.78
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 5.89
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 9.26
PR | 998 | 10/17/25 | 400 | McCabe, Thomas C |  | 26.93
PR | 998 | 10/17/25 | 413 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/17/25 | 413 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/17/25 | 413 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/17/25 | 413 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/17/25 | 413 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/24/25 | 493 | Barnhart, Thomas L |  | 24.67
PR | 998 | 10/24/25 | 493 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/24/25 | 493 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/24/25 | 493 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/24/25 | 493 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/24/25 | 495 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/24/25 | 496 | Da Cruz, Eduardo E |  | 8.36
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 20.81
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 11.7
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 10.4
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 13.01
PR | 998 | 10/24/25 | 505 | Barnhart, Joseph N |  | 28.61
PR | 998 | 10/24/25 | 506 | Bautista Quintero, Isidoro |  | 7.8
PR | 998 | 10/24/25 | 507 | Carmona, Raul O |  | 32.44
PR | 998 | 10/24/25 | 507 | Carmona, Raul O |  | 25.34
PR | 998 | 10/24/25 | 507 | Carmona, Raul O |  | 32.44
PR | 998 | 10/24/25 | 507 | Carmona, Raul O |  | 32.44
PR | 998 | 10/24/25 | 511 | Cortes Mendiola, Victor H |  | 26.93
PR | 998 | 10/24/25 | 516 | Draves, Steven W |  | 33.66
PR | 998 | 10/24/25 | 516 | Draves, Steven W |  | 33.66
PR | 998 | 10/24/25 | 516 | Draves, Steven W |  | 33.66
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 23.98
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 22.53
PR | 998 | 10/24/25 | 518 | Eliassen, Cory H |  | 1.09
PR | 998 | 10/24/25 | 520 | Games, Jordan M |  | 32.44
PR | 998 | 10/24/25 | 520 | Games, Jordan M |  | 25.34
PR | 998 | 10/24/25 | 520 | Games, Jordan M |  | 32.44
PR | 998 | 10/24/25 | 520 | Games, Jordan M |  | 32.44
PR | 998 | 10/24/25 | 522 | Gerard, Jordan E |  | 10.33
PR | 998 | 10/24/25 | 522 | Gerard, Jordan E |  | 9.18
PR | 998 | 10/24/25 | 522 | Gerard, Jordan E |  | 5.74
PR | 998 | 10/24/25 | 523 | Gerard, Mitchell J |  | 11.67
PR | 998 | 10/24/25 | 523 | Gerard, Mitchell J |  | 9.33
PR | 998 | 10/24/25 | 523 | Gerard, Mitchell J |  | 17.5
PR | 998 | 10/24/25 | 523 | Gerard, Mitchell J |  | 36.17
PR | 998 | 10/24/25 | 523 | Gerard, Mitchell J |  | 36.17
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 4.21
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 15.99
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 5.05
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 6.73
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 16.83
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 4.21
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 17.67
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 4.21
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 0.84
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 21.88
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 2.52
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 6.73
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 1.68
PR | 998 | 10/24/25 | 534 | McCabe, Thomas C |  | 12.62
PR | 998 | 10/24/25 | 548 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/24/25 | 548 | Silva Morales, Jair J |  | 12.35
PR | 998 | 10/31/25 | 660 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/31/25 | 660 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/31/25 | 660 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/31/25 | 660 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/31/25 | 660 | Barnhart, Thomas L |  | 26.32
PR | 998 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 10/31/25 | 662 | Cruz Reyes, Jose |  | 21.96
PR | 998 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 25.36
PR | 998 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 31.21
PR | 998 | 10/31/25 | 665 | Amaya Gonzalez, Edilberto A |  | 7.8
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 5.2
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 11.7
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 15.61
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 6.5
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 11.7
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 3.9
PR | 998 | 10/31/25 | 670 | Barnhart, Joseph N |  | 9.1
PR | 998 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 5.05
PR | 998 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 14.69
PR | 998 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 3.67
PR | 998 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 9.64
PR | 998 | 10/31/25 | 671 | Bautista Quintero, Isidoro |  | 3.67
PR | 998 | 10/31/25 | 672 | Carmona, Raul O |  | 32.44
PR | 998 | 10/31/25 | 672 | Carmona, Raul O |  | 33.45
PR | 998 | 10/31/25 | 672 | Carmona, Raul O |  | 32.44
PR | 998 | 10/31/25 | 672 | Carmona, Raul O |  | 31.42
PR | 998 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 11.02
PR | 998 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 39.17
PR | 998 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 9.79
PR | 998 | 10/31/25 | 676 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 10/31/25 | 680 | Da Cruz, Eduardo E |  | 3.08
PR | 998 | 10/31/25 | 680 | Da Cruz, Eduardo E |  | 14.52
PR | 998 | 10/31/25 | 682 | Draves, Steven W |  | 33.66
PR | 998 | 10/31/25 | 682 | Draves, Steven W |  | 28.4
PR | 998 | 10/31/25 | 682 | Draves, Steven W |  | 33.66
PR | 998 | 10/31/25 | 682 | Draves, Steven W |  | 33.66
PR | 998 | 10/31/25 | 682 | Draves, Steven W |  | 33.66
PR | 998 | 10/31/25 | 684 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/31/25 | 684 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/31/25 | 684 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/31/25 | 684 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/31/25 | 684 | Eliassen, Cory H |  | 23.26
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 32.44
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 31.42
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 24.33
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 9.12
PR | 998 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 16.07
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 5.74
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 6.89
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 3.44
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 3.44
PR | 998 | 10/31/25 | 688 | Gerard, Jordan E |  | 3.44
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 19.83
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 16.33
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 28
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 37.33
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 35
PR | 998 | 10/31/25 | 689 | Gerard, Mitchell J |  | 35
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 26.09
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 24.4
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 11.78
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 1.68
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 14.31
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 8.42
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 3.37
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 12.62
PR | 998 | 10/31/25 | 702 | McCabe, Thomas C |  | 2.52
PR | 998 | 10/31/25 | 715 | Silva Morales, Jair J |  | 6.5
PR | 998 | 10/31/25 | 715 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/31/25 | 715 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/31/25 | 715 | Silva Morales, Jair J |  | 20.81
PR | 998 | 10/31/25 | 715 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/07/25 | 49 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/07/25 | 49 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/07/25 | 49 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/07/25 | 49 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/07/25 | 49 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/07/25 | 51 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 7.8
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 2.6
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 7.8
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 2.6
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 9.1
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/07/25 | 61 | Carmona, Raul O |  | 5.07
PR | 998 | 11/07/25 | 61 | Carmona, Raul O |  | 32.44
PR | 998 | 11/07/25 | 71 | Draves, Steven W |  | 33.66
PR | 998 | 11/07/25 | 71 | Draves, Steven W |  | 31.56
PR | 998 | 11/07/25 | 71 | Draves, Steven W |  | 33.66
PR | 998 | 11/07/25 | 71 | Draves, Steven W |  | 33.66
PR | 998 | 11/07/25 | 71 | Draves, Steven W |  | 33.66
PR | 998 | 11/07/25 | 73 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/07/25 | 73 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/07/25 | 73 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/07/25 | 73 | Eliassen, Cory H |  | 12.35
PR | 998 | 11/07/25 | 73 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/07/25 | 75 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/07/25 | 75 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/07/25 | 76 | Gerard, Jordan E |  | 4.59
PR | 998 | 11/07/25 | 76 | Gerard, Jordan E |  | 8.03
PR | 998 | 11/07/25 | 76 | Gerard, Jordan E |  | 16.07
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 19.83
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 3.5
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 3.5
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 28
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 1.17
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 29.17
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 3.5
PR | 998 | 11/07/25 | 77 | Gerard, Mitchell J |  | 25.67
PR | 998 | 11/07/25 | 103 | Silva Morales, Jair J |  | 3.25
PR | 998 | 11/14/25 | 209 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/14/25 | 209 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/14/25 | 209 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/14/25 | 209 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/14/25 | 209 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/14/25 | 211 | Cruz Reyes, Jose |  | 24.31
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 19.51
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 22.11
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 3.9
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 1.3
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 1.3
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 14.31
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 2.6
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 6.5
PR | 998 | 11/14/25 | 221 | Carmona, Raul O |  | 32.44
PR | 998 | 11/14/25 | 221 | Carmona, Raul O |  | 32.44
PR | 998 | 11/14/25 | 221 | Carmona, Raul O |  | 32.44
PR | 998 | 11/14/25 | 221 | Carmona, Raul O |  | 32.44
PR | 998 | 11/14/25 | 221 | Carmona, Raul O |  | 32.44
PR | 998 | 11/14/25 | 231 | Draves, Steven W |  | 33.66
PR | 998 | 11/14/25 | 231 | Draves, Steven W |  | 33.66
PR | 998 | 11/14/25 | 231 | Draves, Steven W |  | 33.66
PR | 998 | 11/14/25 | 231 | Draves, Steven W |  | 33.66
PR | 998 | 11/14/25 | 231 | Draves, Steven W |  | 33.66
PR | 998 | 11/14/25 | 233 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/14/25 | 233 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/14/25 | 233 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/14/25 | 233 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/14/25 | 233 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/14/25 | 236 | Gerard, Jordan E |  | 5.74
PR | 998 | 11/14/25 | 236 | Gerard, Jordan E |  | 13.77
PR | 998 | 11/14/25 | 236 | Gerard, Jordan E |  | 29.84
PR | 998 | 11/14/25 | 236 | Gerard, Jordan E |  | 10.33
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 9.33
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 11.67
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 3.5
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 19.83
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 11.67
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 8.17
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 18.67
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 10.5
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 5.83
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 9.33
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 3.5
PR | 998 | 11/14/25 | 237 | Gerard, Mitchell J |  | 36.17
PR | 998 | 11/14/25 | 263 | Silva Morales, Jair J |  | 14.31
PR | 998 | 11/21/25 | 325 | Barnhart, Thomas L |  | 24.67
PR | 998 | 11/21/25 | 325 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/21/25 | 325 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/21/25 | 325 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/21/25 | 325 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/21/25 | 327 | Cruz Reyes, Jose |  | 21.96
PR | 998 | 11/21/25 | 338 | Carmona, Raul O |  | 32.44
PR | 998 | 11/21/25 | 338 | Carmona, Raul O |  | 32.44
PR | 998 | 11/21/25 | 338 | Carmona, Raul O |  | 32.44
PR | 998 | 11/21/25 | 338 | Carmona, Raul O |  | 32.44
PR | 998 | 11/21/25 | 338 | Carmona, Raul O |  | 32.44
PR | 998 | 11/21/25 | 342 | Cortes Mendiola, Victor H |  | 24.48
PR | 998 | 11/21/25 | 348 | Draves, Steven W |  | 33.66
PR | 998 | 11/21/25 | 348 | Draves, Steven W |  | 33.66
PR | 998 | 11/21/25 | 348 | Draves, Steven W |  | 33.66
PR | 998 | 11/21/25 | 350 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/21/25 | 350 | Eliassen, Cory H |  | 23.98
PR | 998 | 11/21/25 | 350 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/21/25 | 350 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 11/21/25 | 352 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 12.62
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 10.33
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 14.92
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 10.5
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 5.83
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 9.33
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 5.83
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 19.83
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 22.17
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 4.67
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 1.17
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 10.5
PR | 998 | 11/21/25 | 354 | Gerard, Mitchell J |  | 37.33
PR | 998 | 11/21/25 | 379 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/21/25 | 379 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/21/25 | 379 | Silva Morales, Jair J |  | 20.81
PR | 998 | 11/21/25 | 379 | Silva Morales, Jair J |  | 9.1
PR | 998 | 11/28/25 | 509 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/28/25 | 509 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/28/25 | 509 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/28/25 | 509 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/28/25 | 509 | Barnhart, Thomas L |  | 26.32
PR | 998 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/28/25 | 511 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 9.1
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 1.3
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 2.6
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 19.51
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 1.3
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 5.2
PR | 998 | 11/28/25 | 521 | Carmona, Raul O |  | 32.44
PR | 998 | 11/28/25 | 521 | Carmona, Raul O |  | 32.44
PR | 998 | 11/28/25 | 521 | Carmona, Raul O |  | 32.44
PR | 998 | 11/28/25 | 521 | Carmona, Raul O |  | 32.44
PR | 998 | 11/28/25 | 521 | Carmona, Raul O |  | 32.44
PR | 998 | 11/28/25 | 531 | Draves, Steven W |  | 34.71
PR | 998 | 11/28/25 | 531 | Draves, Steven W |  | 31.56
PR | 998 | 11/28/25 | 531 | Draves, Steven W |  | 33.66
PR | 998 | 11/28/25 | 531 | Draves, Steven W |  | 33.66
PR | 998 | 11/28/25 | 531 | Draves, Steven W |  | 23.14
PR | 998 | 11/28/25 | 533 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/28/25 | 533 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/28/25 | 533 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/28/25 | 533 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/28/25 | 533 | Eliassen, Cory H |  | 23.26
PR | 998 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/28/25 | 537 | Gerard, Jordan E |  | 3.44
PR | 998 | 11/28/25 | 537 | Gerard, Jordan E |  | 17.21
PR | 998 | 11/28/25 | 537 | Gerard, Jordan E |  | 6.89
PR | 998 | 11/28/25 | 537 | Gerard, Jordan E |  | 8.03
PR | 998 | 11/28/25 | 537 | Gerard, Jordan E |  | 5.74
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 28
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 2.33
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 10.5
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 1.17
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 14
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 12.83
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 15.17
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 9.33
PR | 998 | 11/28/25 | 538 | Gerard, Mitchell J |  | 25.67
PR | 998 | 11/28/25 | 563 | Silva Morales, Jair J |  | 6.5
PR | 998 | 12/05/25 | 35 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/05/25 | 35 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/05/25 | 35 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/05/25 | 37 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/05/25 | 45 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/05/25 | 45 | Barnhart, Joseph N |  | 26.01
PR | 998 | 12/05/25 | 46 | Bautista Quintero, Isidoro |  | 1.84
PR | 998 | 12/05/25 | 47 | Carmona, Raul O |  | 32.44
PR | 998 | 12/05/25 | 47 | Carmona, Raul O |  | 32.44
PR | 998 | 12/05/25 | 47 | Carmona, Raul O |  | 32.44
PR | 998 | 12/05/25 | 57 | Draves, Steven W |  | 33.66
PR | 998 | 12/05/25 | 57 | Draves, Steven W |  | 35.76
PR | 998 | 12/05/25 | 57 | Draves, Steven W |  | 33.66
PR | 998 | 12/05/25 | 59 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/05/25 | 59 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/05/25 | 59 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/05/25 | 63 | Gerard, Jordan E |  | 5.74
PR | 998 | 12/05/25 | 63 | Gerard, Jordan E |  | 11.48
PR | 998 | 12/05/25 | 63 | Gerard, Jordan E |  | 9.18
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 10.5
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 3.5
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 15.17
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 1.17
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 7
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 4.67
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 4.67
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 5.83
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 8.17
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 2.33
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 22.17
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 9.33
PR | 998 | 12/05/25 | 64 | Gerard, Mitchell J |  | 3.5
PR | 998 | 12/12/25 | 172 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/12/25 | 172 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/12/25 | 172 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/12/25 | 172 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/12/25 | 172 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 15.68
PR | 998 | 12/12/25 | 174 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 9.1
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 6.5
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 28.61
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 3.9
PR | 998 | 12/12/25 | 184 | Carmona, Raul O |  | 32.44
PR | 998 | 12/12/25 | 184 | Carmona, Raul O |  | 32.44
PR | 998 | 12/12/25 | 184 | Carmona, Raul O |  | 32.44
PR | 998 | 12/12/25 | 184 | Carmona, Raul O |  | 32.44
PR | 998 | 12/12/25 | 184 | Carmona, Raul O |  | 32.44
PR | 998 | 12/12/25 | 194 | Draves, Steven W |  | 33.66
PR | 998 | 12/12/25 | 194 | Draves, Steven W |  | 33.66
PR | 998 | 12/12/25 | 194 | Draves, Steven W |  | 33.66
PR | 998 | 12/12/25 | 194 | Draves, Steven W |  | 33.66
PR | 998 | 12/12/25 | 194 | Draves, Steven W |  | 33.66
PR | 998 | 12/12/25 | 196 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/12/25 | 196 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/12/25 | 196 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/12/25 | 196 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/12/25 | 196 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/12/25 | 200 | Gerard, Jordan E |  | 9.18
PR | 998 | 12/12/25 | 200 | Gerard, Jordan E |  | 12.62
PR | 998 | 12/12/25 | 200 | Gerard, Jordan E |  | 21.8
PR | 998 | 12/12/25 | 200 | Gerard, Jordan E |  | 24.1
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 9.33
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 2.33
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 1.17
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 17.5
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 24.5
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 12.83
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 16.33
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 10.5
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 10.5
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 4.67
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 15.17
PR | 998 | 12/12/25 | 201 | Gerard, Mitchell J |  | 17.5
PR | 998 | 12/19/25 | 313 | Barnhart, Thomas L |  | 24.67
PR | 998 | 12/19/25 | 313 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/19/25 | 313 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/19/25 | 313 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/19/25 | 313 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/19/25 | 315 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 6.5
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 7.8
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/19/25 | 325 | Carmona, Raul O |  | 32.44
PR | 998 | 12/19/25 | 325 | Carmona, Raul O |  | 32.44
PR | 998 | 12/19/25 | 325 | Carmona, Raul O |  | 32.44
PR | 998 | 12/19/25 | 335 | Draves, Steven W |  | 23.14
PR | 998 | 12/19/25 | 335 | Draves, Steven W |  | 33.66
PR | 998 | 12/19/25 | 335 | Draves, Steven W |  | 33.66
PR | 998 | 12/19/25 | 335 | Draves, Steven W |  | 33.66
PR | 998 | 12/19/25 | 335 | Draves, Steven W |  | 33.66
PR | 998 | 12/19/25 | 337 | Eliassen, Cory H |  | 22.53
PR | 998 | 12/19/25 | 337 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/19/25 | 337 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/19/25 | 337 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/19/25 | 340 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 12/19/25 | 341 | Gerard, Jordan E |  | 8.03
PR | 998 | 12/19/25 | 341 | Gerard, Jordan E |  | 11.48
PR | 998 | 12/19/25 | 341 | Gerard, Jordan E |  | 11.48
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 7
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 5.83
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 7
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 14
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 2.33
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 21
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 8.17
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 29.17
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 33.83
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 9.33
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 2.33
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 15.17
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 3.5
PR | 998 | 12/19/25 | 342 | Gerard, Mitchell J |  | 7
PR | 998 | 12/26/25 | 501 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/26/25 | 501 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/26/25 | 501 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/26/25 | 501 | Barnhart, Thomas L |  | 26.32
PR | 998 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/26/25 | 503 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 11.7
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 16.91
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 1.3
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/26/25 | 523 | Draves, Steven W |  | 31.56
PR | 998 | 12/26/25 | 523 | Draves, Steven W |  | 33.66
PR | 998 | 12/26/25 | 523 | Draves, Steven W |  | 22.09
PR | 998 | 12/26/25 | 525 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/26/25 | 525 | Eliassen, Cory H |  | 22.53
PR | 998 | 12/26/25 | 525 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/26/25 | 525 | Eliassen, Cory H |  | 23.26
PR | 998 | 12/26/25 | 528 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 12/26/25 | 529 | Gerard, Jordan E |  | 12.62
PR | 998 | 12/26/25 | 529 | Gerard, Jordan E |  | 13.77
PR | 998 | 12/26/25 | 529 | Gerard, Jordan E |  | 9.18
PR | 998 | 12/26/25 | 530 | Gerard, Mitchell J |  | 30.33
PR | 998 | 12/26/25 | 530 | Gerard, Mitchell J |  | 33.83
PR | 998 | 12/26/25 | 530 | Gerard, Mitchell J |  | 36.17
PR | 998 | 01/02/26 | 5 | Barnhart, Thomas L |  | 26.32
PR | 998 | 01/02/26 | 5 | Barnhart, Thomas L |  | 26.32
PR | 998 | 01/02/26 | 5 | Barnhart, Thomas L |  | 18.09
PR | 998 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 01/02/26 | 7 | Cruz Reyes, Jose |  | 25.09
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 1.3
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 2.6
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 11.7
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 2.6
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 3.9
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 5.2
PR | 998 | 01/02/26 | 15 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/02/26 | 21 | Cortes Mendiola, Victor H |  | 6.12
PR | 998 | 01/02/26 | 27 | Draves, Steven W |  | 35.76
PR | 998 | 01/02/26 | 27 | Draves, Steven W |  | 33.66
PR | 998 | 01/02/26 | 27 | Draves, Steven W |  | 21.04
PR | 998 | 01/02/26 | 29 | Eliassen, Cory H |  | 23.26
PR | 998 | 01/02/26 | 29 | Eliassen, Cory H |  | 13.08
PR | 998 | 01/02/26 | 29 | Eliassen, Cory H |  | 23.26
PR | 998 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/02/26 | 33 | Gerard, Jordan E |  | 10.33
PR | 998 | 01/02/26 | 33 | Gerard, Jordan E |  | 16.07
PR | 998 | 01/02/26 | 33 | Gerard, Jordan E |  | 5.74
PR | 998 | 01/02/26 | 34 | Gerard, Mitchell J |  | 17.5
PR | 998 | 01/02/26 | 34 | Gerard, Mitchell J |  | 3.5
PR | 998 | 01/02/26 | 34 | Gerard, Mitchell J |  | 32.67
PR | 998 | 01/02/26 | 34 | Gerard, Mitchell J |  | 23.33
PR | 998 | 01/09/26 | 120 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/09/26 | 120 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/09/26 | 120 | Barnhart, Thomas L |  | 25.82
PR | 998 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/09/26 | 122 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 14.73
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 8.03
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 9.37
PR | 998 | 01/09/26 | 142 | Draves, Steven W |  | 34.88
PR | 998 | 01/09/26 | 142 | Draves, Steven W |  | 34.88
PR | 998 | 01/09/26 | 142 | Draves, Steven W |  | 34.88
PR | 998 | 01/09/26 | 144 | Eliassen, Cory H |  | 24.61
PR | 998 | 01/09/26 | 144 | Eliassen, Cory H |  | 16.41
PR | 998 | 01/09/26 | 144 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/09/26 | 147 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/09/26 | 148 | Gerard, Jordan E |  | 5.64
PR | 998 | 01/09/26 | 148 | Gerard, Jordan E |  | 6.77
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 8.43
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 27.71
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 3.61
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/09/26 | 149 | Gerard, Mitchell J |  | 15.66
PR | 998 | 01/09/26 | 176 | Swails, Melanie L |  | 35.5
PR | 998 | 01/09/26 | 176 | Swails, Melanie L |  | 35.5
PR | 998 | 01/09/26 | 176 | Swails, Melanie L |  | 35.5
PR | 998 | 01/09/26 | 188 | Swails, Melanie L |  | -106.49
PR | 998 | 01/16/26 | 266 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/16/26 | 266 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/16/26 | 268 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 5.36
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 29.45
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 2.68
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 4.02
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 17.4
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 4.02
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 38.82
PR | 998 | 01/16/26 | 288 | Draves, Steven W |  | 26.16
PR | 998 | 01/16/26 | 288 | Draves, Steven W |  | 35.97
PR | 998 | 01/16/26 | 288 | Draves, Steven W |  | 34.88
PR | 998 | 01/16/26 | 288 | Draves, Steven W |  | 34.88
PR | 998 | 01/16/26 | 288 | Draves, Steven W |  | 34.88
PR | 998 | 01/16/26 | 290 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/16/26 | 290 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/16/26 | 290 | Eliassen, Cory H |  | 17.9
PR | 998 | 01/16/26 | 290 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/16/26 | 290 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/16/26 | 294 | Gerard, Jordan E |  | 5.64
PR | 998 | 01/16/26 | 294 | Gerard, Jordan E |  | 5.64
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 38.56
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 20.48
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 8.43
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 24.1
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 10.84
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 30.12
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 15.66
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 8.43
PR | 998 | 01/16/26 | 295 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/23/26 | 458 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 26.78
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 9.37
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 12.05
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 4.02
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 17.4
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 1.34
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 2.68
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 8.03
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 42.84
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 4.02
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 9.37
PR | 998 | 01/23/26 | 473 | Cortes Mendiola, Victor H |  | 40.39
PR | 998 | 01/23/26 | 479 | Draves, Steven W |  | 34.88
PR | 998 | 01/23/26 | 479 | Draves, Steven W |  | 31.61
PR | 998 | 01/23/26 | 479 | Draves, Steven W |  | 34.88
PR | 998 | 01/23/26 | 479 | Draves, Steven W |  | 34.88
PR | 998 | 01/23/26 | 479 | Draves, Steven W |  | 34.88
PR | 998 | 01/23/26 | 481 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/23/26 | 481 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/23/26 | 481 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/23/26 | 481 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/23/26 | 481 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/23/26 | 485 | Gerard, Jordan E |  | 4.51
PR | 998 | 01/23/26 | 485 | Gerard, Jordan E |  | 7.9
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 22.89
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 15.66
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 12.05
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 21.69
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 30.12
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 2.41
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 6.02
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 38.56
PR | 998 | 01/23/26 | 486 | Gerard, Mitchell J |  | 38.56
PR | 998 | 01/30/26 | 569 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/30/26 | 569 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/30/26 | 569 | Barnhart, Thomas L |  | 27.54
PR | 998 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/30/26 | 571 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 13.39
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 8.03
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 6.69
PR | 998 | 01/30/26 | 586 | Cortes Mendiola, Victor H |  | 40.39
PR | 998 | 01/30/26 | 586 | Cortes Mendiola, Victor H |  | 25.25
PR | 998 | 01/30/26 | 592 | Draves, Steven W |  | 34.88
PR | 998 | 01/30/26 | 592 | Draves, Steven W |  | 34.88
PR | 998 | 01/30/26 | 592 | Draves, Steven W |  | 34.88
PR | 998 | 01/30/26 | 592 | Draves, Steven W |  | 34.88
PR | 998 | 01/30/26 | 592 | Draves, Steven W |  | 34.88
PR | 998 | 01/30/26 | 594 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/30/26 | 594 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/30/26 | 594 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/30/26 | 594 | Eliassen, Cory H |  | 23.12
PR | 998 | 01/30/26 | 594 | Eliassen, Cory H |  | 23.87
PR | 998 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/30/26 | 598 | Gerard, Jordan E |  | 6.77
PR | 998 | 01/30/26 | 598 | Gerard, Jordan E |  | 6.77
PR | 998 | 01/30/26 | 598 | Gerard, Jordan E |  | 1.13
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 10.84
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 3.61
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 7.23
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 16.87
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 38.56
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 7.23
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 22.89
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 3.61
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 4.82
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 32.53
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 18.07
PR | 998 | 01/30/26 | 599 | Gerard, Mitchell J |  | 20.48
PR | 998 | 02/06/26 | 45 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/06/26 | 45 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/06/26 | 45 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/06/26 | 45 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/06/26 | 45 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/06/26 | 47 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/06/26 | 56 | Barnhart, Joseph N |  | 2.68
PR | 998 | 02/06/26 | 56 | Barnhart, Joseph N |  | 6.69
PR | 998 | 02/06/26 | 68 | Draves, Steven W |  | 34.88
PR | 998 | 02/06/26 | 68 | Draves, Steven W |  | 34.88
PR | 998 | 02/06/26 | 68 | Draves, Steven W |  | 34.88
PR | 998 | 02/06/26 | 68 | Draves, Steven W |  | 34.88
PR | 998 | 02/06/26 | 68 | Draves, Steven W |  | 34.88
PR | 998 | 02/06/26 | 69 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/06/26 | 69 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/06/26 | 69 | Eliassen, Cory H |  | 23.12
PR | 998 | 02/06/26 | 69 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/06/26 | 69 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 02/06/26 | 73 | Gerard, Jordan E |  | 10.16
PR | 998 | 02/06/26 | 73 | Gerard, Jordan E |  | 13.54
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 27.71
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 10.84
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 12.05
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 38.56
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 4.82
PR | 998 | 02/06/26 | 74 | Gerard, Mitchell J |  | 30.12
PR | 998 | 02/13/26 | 177 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/13/26 | 177 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/13/26 | 177 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/13/26 | 177 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/13/26 | 177 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/13/26 | 179 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A |  | 25.34
PR | 998 | 02/13/26 | 182 | Amaya Gonzalez, Edilberto A |  | 32.44
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 25.44
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 20.08
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 52.21
PR | 998 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 14.42
PR | 998 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 15.91
PR | 998 | 02/13/26 | 189 | Bautista Quintero, Isidoro |  | 13.43
PR | 998 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 15.15
PR | 998 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 41.65
PR | 998 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 25.25
PR | 998 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 15.15
PR | 998 | 02/13/26 | 194 | Cortes Mendiola, Victor H |  | 1.89
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 34.88
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 34.88
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 34.88
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 34.88
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 34.88
PR | 998 | 02/13/26 | 200 | Draves, Steven W |  | 16.35
PR | 998 | 02/13/26 | 201 | Eliassen, Cory H |  | 16.41
PR | 998 | 02/13/26 | 201 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/13/26 | 201 | Eliassen, Cory H |  | 23.87
PR | 998 | 02/13/26 | 201 | Eliassen, Cory H |  | 23.12
PR | 998 | 02/13/26 | 201 | Eliassen, Cory H |  | 24.61
PR | 998 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 02/13/26 | 205 | Gerard, Jordan E |  | 10.16
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 4.82
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 6.02
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 7.23
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 13.25
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 8.43
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 24.1
PR | 998 | 02/13/26 | 206 | Gerard, Mitchell J |  | 31.33
PR | 998 | 02/20/26 | 293 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/20/26 | 293 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/20/26 | 293 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/20/26 | 293 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/20/26 | 293 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/20/26 | 295 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/20/26 | 298 | Amaya Gonzalez, Edilberto A |  | 32.44
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 29.45
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 2.68
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 6.69
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 2.68
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 4.02
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 10.71
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 14.73
PR | 998 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 15.91
PR | 998 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 8.45
PR | 998 | 02/20/26 | 305 | Bautista Quintero, Isidoro |  | 15.91
PR | 998 | 02/20/26 | 310 | Cortes Mendiola, Victor H |  | 21.46
PR | 998 | 02/20/26 | 310 | Cortes Mendiola, Victor H |  | 40.39
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 9.81
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 15.26
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 28.34
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 34.88
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 32.7
PR | 998 | 02/20/26 | 316 | Draves, Steven W |  | 34.88
PR | 998 | 02/20/26 | 320 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 6.77
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 5.64
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 12.41
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 12.05
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 39.76
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 7.23
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 3.61
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 13.25
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 12.05
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 4.82
PR | 998 | 02/20/26 | 322 | Gerard, Mitchell J |  | 24.1
PR | 998 | 02/27/26 | 442 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/27/26 | 442 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/27/26 | 442 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/27/26 | 442 | Barnhart, Thomas L |  | 27.54
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 24.1
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 9.64
PR | 998 | 02/27/26 | 444 | Cruz Reyes, Jose |  | 16.07
PR | 998 | 02/27/26 | 446 | Amaya Gonzalez, Edilberto A |  | 30.41
PR | 998 | 02/27/26 | 448 | Aquino, Juan |  | 26.39
PR | 998 | 02/27/26 | 450 | Ascencio, Jose L |  | 24.67
PR | 998 | 02/27/26 | 451 | Balderas Ortiz, Ricardo I |  | 16.83
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 28.11
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 10.71
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 40.16
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 16.07
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 2.68
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 18.74
PR | 998 | 02/27/26 | 453 | Bautista Quintero, Isidoro |  | 15.91
PR | 998 | 02/27/26 | 454 | Carmona, Raul O |  | 30.98
PR | 998 | 02/27/26 | 456 | Chevez, Herson G |  | 21.8
PR | 998 | 02/27/26 | 458 | Cortes Mendiola, Victor H |  | 40.39
PR | 998 | 02/27/26 | 458 | Cortes Mendiola, Victor H |  | 37.87
PR | 998 | 02/27/26 | 459 | Countryman, Matthew K |  | 19.39
PR | 998 | 02/27/26 | 459 | Countryman, Matthew K |  | 6.96
PR | 998 | 02/27/26 | 462 | Da Cruz, Eduardo E |  | 13.2
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 34.88
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 34.88
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 13.08
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 32.7
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 34.88
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 34.88
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 4.36
PR | 998 | 02/27/26 | 464 | Draves, Steven W |  | 30.52
PR | 998 | 02/27/26 | 465 | Fox, Tamron P |  | 17.21
PR | 998 | 02/27/26 | 468 | Gerard, Jordan E |  | 12.41
PR | 998 | 02/27/26 | 468 | Gerard, Jordan E |  | 6.77
PR | 998 | 02/27/26 | 468 | Gerard, Jordan E |  | 11.28
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 38.56
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 38.56
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 14.46
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 38.56
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 32.53
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 10.84
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 3.61
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 1.2
PR | 998 | 02/27/26 | 469 | Gerard, Mitchell J |  | 9.64
PR | 998 | 02/27/26 | 473 | Gorman, Nathan W |  | 14.92
PR | 998 | 02/27/26 | 478 | Mackey, Cole J |  | 29.84
PR | 998 | 02/27/26 | 480 | Melgar Moz, Brandon |  | 14.92
PR | 998 | 02/27/26 | 481 | Mendoza Morales, Jesus A |  | 24.67
PR | 998 | 02/27/26 | 484 | Nunez Bravo, Jose L |  | 13.77
PR | 998 | 02/27/26 | 485 | Paco Leyva, Orlando |  | 36.15
PR | 998 | 02/27/26 | 486 | Perez Araque, Manuel A |  | 11.48
PR | 998 | 02/27/26 | 488 | Ramos Herrera, Franklin J |  | 24.67
PR | 998 | 02/27/26 | 490 | Rodriguez Arevalos, Christian |  | 25.36
PR | 998 | 02/27/26 | 492 | Silva Morales, Jair J |  | 20.08
PR | 998 | 02/27/26 | 493 | Suniga Aviles, Kelvin A |  | 14.92
PR | 998 | 02/27/26 | 498 | Young, Joshua S |  | 29.84
PR | 998 | 02/27/26 | 499 | Zuniga Avilez, Eduar A |  | 14.92
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 17.21
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/06/26 | 38 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/06/26 | 40 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 8.03
PR | 998 | 03/06/26 | 60 | Draves, Steven W |  | 34.88
PR | 998 | 03/06/26 | 60 | Draves, Steven W |  | 34.88
PR | 998 | 03/06/26 | 60 | Draves, Steven W |  | 34.88
PR | 998 | 03/06/26 | 60 | Draves, Steven W |  | 34.88
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 3.39
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 38.56
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 8.43
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 30.12
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 38.56
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 38.56
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 10.84
PR | 998 | 03/06/26 | 65 | Gerard, Mitchell J |  | 27.71
PR | 998 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 16.64
PR | 998 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 18.36
PR | 998 | 03/06/26 | 82 | Perez Araque, Manuel A |  | 18.36
PR | 998 | 03/13/26 | 183 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/13/26 | 183 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/13/26 | 183 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/13/26 | 183 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/13/26 | 183 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/13/26 | 185 | Cruz Reyes, Jose |  | 25.7
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 12.05
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 20.48
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 13.25
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 4.82
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 13.25
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 6.02
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 24.1
PR | 998 | 03/13/26 | 210 | Gerard, Mitchell J |  | 27.71
PR | 998 | 03/13/26 | 227 | Perez Araque, Manuel A |  | 18.36
PR | 998 | 03/13/26 | 227 | Perez Araque, Manuel A |  | 18.36
PR | 998 | 03/20/26 | 301 | Barnhart, Thomas L |  | 25.82
PR | 998 | 03/20/26 | 301 | Barnhart, Thomas L |  | 24.1
PR | 998 | 03/20/26 | 301 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/20/26 | 301 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/20/26 | 301 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 8.03
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 14.73
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 10.71
PR | 998 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 16.87
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 4.82
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 8.43
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 7.23
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 3.61
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 28.92
PR | 998 | 03/20/26 | 328 | Gerard, Mitchell J |  | 30.12
PR | 998 | 03/27/26 | 469 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/27/26 | 469 | Barnhart, Thomas L |  | 27.54
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 5.36
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 5.36
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 1.34
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 14.73
PR | 998 | 03/27/26 | 491 | Draves, Steven W |  | 34.88
PR | 998 | 03/27/26 | 491 | Draves, Steven W |  | 34.88
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 38.56
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 8.43
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 27.71
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 3.61
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 2.41
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 2.41
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 4.82
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 3.61
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 10.84
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 3.61
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 4.82
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 27.71
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 2.41
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 13.25
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 7.23
PR | 998 | 03/27/26 | 496 | Gerard, Mitchell J |  | 13.25
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 2.68
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 17.4
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 5.36
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 12.05
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 4.02
PR | 998 | 04/03/26 | 12 | Barnhart, Joseph N |  | 1.34
PR | 998 | 04/03/26 | 24 | Draves, Steven W |  | 34.88
PR | 998 | 04/03/26 | 24 | Draves, Steven W |  | 34.88
PR | 998 | 04/03/26 | 28 | Gerard, Jordan E |  | 10.16
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 38.56
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 2.41
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 7.23
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 4.82
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 8.43
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 1.2
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 38.56
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 38.56
PR | 998 | 04/03/26 | 29 | Gerard, Mitchell J |  | 32.53
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -84100 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -135900 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -9795 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -13650 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -80000 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -88000 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -2167 | 038354
AR | 999 | 10/18/24 | 511 | Compass General Construction I, LLC $M2 |  | -18205 | 038354
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 84100 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 135900 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 9795 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 13650 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 80000 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 88000 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 2167 | 038362
AR | 999 | 11/01/24 | 85 | Compass General Construction I, LLC $M2 |  | 18205 | 038362
AR | 999 | 10/17/25 | 433 | Compass General Construction I, LLC $M2 |  | 0 | 038489
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -19140 | 038502
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -3845 | 038502
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -15820 | 038502
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -15820 | 038502
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -24790 | 038502
AR | 999 | 11/20/25 | 392 | Compass General Construction I, LLC $M2 |  | -22343 | 038502
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 19140 | 038522
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 3845 | 038522
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 15820 | 038522
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 15820 | 038522
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 24790 | 038522
AR | 999 | 01/01/26 | 375 | Compass General Construction I, LLC $M2 |  | 22343 | 038522