## 01 Overview
OWP #2104 · Big 1410 Apartments
BMDC Services, LLC · 24 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 1196549
Revised budget (expenses) | 870823.24
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 1193734
Retention held | 59686.7
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 10415.16
AP | 435131.49
PR | 310992.63
AR | -1193734

## 02 Job Info
Job Information
Job ID | 2104
Project name | Big 1410 Apartments
General contractor | BMDC Services, LLC
Owner | BMDC Services, LLC
Units | 24
Insurance | Standard (COI)
Job start | Jun 2024
Expected completion | TBD (active — in trim)
Architect | N/A
MEP Engineer | N/A
RI Foreman | Tommy/Ben
Status | ACTIVE · in-progress · in trim
JDR report date | Apr 3, 2026
Location | 1410 E Howell St, Seattle, WA 98122
GC Subcontract # | 22-0500-01

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 1143800 | 1196549
Executed change orders (net) | 0 | 52749
Total contract value
Executed Change Orders
CO # | Description | Amount
CO#1 | Storm Overflow Drains (CR1053) | 7164
CO#1.2 | Add Irrigation POC (CR1109) | 2573
CO#4 | Core Drill for Other Subs (CR1080) | 3812
CO#6 | Add Booster Pump (CR1137) | 39200

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status
COR#01 | COR | Add Condensate Piping | 0 | NOT EXECUTED
COR#02 | COR | Core Drilling | 3812 | EXECUTED as CO#4
COR#03 | COR | Adding Overflows | 7164 | EXECUTED as CO#1
COR#04 | COR | Added Irrigation | 2573 | EXECUTED as CO#1.2
COR#05 | COR | Add Booster Pump | 39200 | EXECUTED as CO#6

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 2400 | 2400 | 4363.5 |  | 0
101 | Takeoff & Purchase Labor | 4800 | 4800 | 9215 |  | 0
110 | Underground Labor | 7125 | 7125 | 8973.5 |  | 0
111 | Garage Labor | 5000 | 5000 | 2268 |  | 0
112 | Canout Labor | 4100 | 4100 | 3928 |  | 0
120 | Roughin Labor | 86380 | 91880 | 132816 |  | 0
130 | Finish Labor | 12080 | 12080 | 10320.5 |  | 0
140 | Gas Labor | 4000 | 4000 | 3848 |  | 0
141 | Water Main/Insulation Lab | 22570 | 23420 | 17012.5 |  | 0
142 | Mech Room Labor | 39600 | 42600 | 9336 |  | 0
210 | Underground Material | 8500 | 8500 | 4029.94 |  | 0
211 | Garage Material | 4000 | 4000 | 2904.28 |  | 0
212 | Canout Material | 4018 | 4018 | 1262.92 |  | 0
220 | Roughin Material | 53635 | 53835 | 18939.04 |  | -17.06
230 | Finish Material | 384025 | 411659 | 343464.97 |  | 93.43
240 | Gas Material | 7500 | 7500 | 2063.38 |  | 0
241 | Water Main/Insulation Mat | 24065 | 25015 | 31392.49 |  | 137.53
242 | Mech Room Material | 44400 | 44400 | 28522.36 |  | 4462.42
603 | Permits & Licenses | 8675 | 8675 | 2505 |  | 0
607 | Other Expenses | 10000 | 10000 | 10462.27 |  | 0
995 | Payroll Burden | 76820.47 | 80714.75 | 93452.29 |  | 0
998 | Payroll Taxes | 14386.21 | 15101.49 | 15459.34 |  | 0
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 10 | 197405 | 202081
Material | 8 | 558927 | 432579.38
Overhead | 2 | 18675 | 12967.27
Burden | 2 | 95816.24 | 108911.63
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 2400 | 4363.5
101 | Takeoff & Purchase Labor | 4800 | 9215
110 | Underground Labor | 7125 | 8973.5
111 | Garage Labor | 5000 | 2268
112 | Canout Labor | 4100 | 3928
120 | Roughin Labor | 91880 | 132816
130 | Finish Labor | 12080 | 10320.5
140 | Gas Labor | 4000 | 3848
141 | Water Main/Insulation Lab | 23420 | 17012.5
142 | Mech Room Labor | 42600 | 9336
210 | Underground Material | 8500 | 4029.94
211 | Garage Material | 4000 | 2904.28
212 | Canout Material | 4018 | 1262.92
220 | Roughin Material | 53835 | 18939.04
230 | Finish Material | 411659 | 343464.97
240 | Gas Material | 7500 | 2063.38
241 | Water Main/Insulation Mat | 25015 | 31392.49
242 | Mech Room Material | 44400 | 28522.36
603 | Permits & Licenses | 8675 | 2505
607 | Other Expenses | 10000 | 10462.27
995 | Payroll Burden | 80714.75 | 93452.29
998 | Payroll Taxes | 15101.49 | 15459.34

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
California Hydronics Corp | 286931 | 6
Consolidated Supply Co. | 48240.58 | 81
Bank of America CC | 26613.41 | 51
Pacific Plumbing Supply Co., LLC | 23158.46 | 30
Ferguson Enterprises, Inc. #3007 | 20208.49 | 7
Keller Supply Company | 16443.42 | 16
MacArthur Co. NW 6276 | 6281.88 | 3
Rosen Supply Kirkland | 6183.32 | 22
Kele, Inc $ MI Controls | 466 | 1
Mechanical Sales, Inc. | 335.78 | 1
Capital One Credit Card | 225.15 | 7
Pac West Sales | 44 | 1
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gomez Aguirre, Exequiel | 1627.5 | 40122 |  | JOURNEYMAN
Eisenhauer, Tommy J | 1608.8 | 91699 |  | LEAD/SUPERVISOR
Martinez Reyes, Juan C | 387 | 17028 |  | LEAD/SUPERVISOR
Barnhart, Joseph N | 260 | 17297 |  | LEAD/SUPERVISOR
Mackey, Cole J | 158.5 | 8242 |  | LEAD/SUPERVISOR
Gerard, Jeffrey S | 119 | 8211 |  | LEAD/SUPERVISOR
Games, Jordan M | 90.8 | 4810 |  | LEAD/SUPERVISOR
Araque, Mario W | 68.2 | 1638 |  | JOURNEYMAN
Johnson, Jake E | 66 | 3432 |  | LEAD/SUPERVISOR
Anderson, Richard P | 45 | 2927 |  | LEAD/SUPERVISOR
Boss, Benjamin T | 36 | 1836 |  | LEAD/SUPERVISOR
Nunez Bravo, Jose L | 31.2 | 750 |  | JOURNEYMAN
Gerard, Jordan E | 29.5 | 1766 |  | LEAD/SUPERVISOR
Suniga Aviles, Kelvin A | 15.8 | 394 |  | JOURNEYMAN
Del Villar, Flabio | 15 | 375 |  | JOURNEYMAN
Melgar Moz, Brandon | 8 | 176 |  | JOURNEYMAN
Zuniga Avilez, Eduar A | 8 | 192 |  | JOURNEYMAN
Yohannes Jr., Samson | 8 | 264 |  | JOURNEYMAN
Silva Morales, Jair J | 8 | 272 |  | JOURNEYMAN
Calderon M, Roberto H | 7 | 154 |  | JOURNEYMAN
Cruz, Azael S | 7 | 224 |  | JOURNEYMAN
Jimenez Alvarenga, Gerson M | 7 | 273 |  | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 11 | 2807.5 | 157520
JOURNEYMAN | 11 | 1803.8 | 44561
APPRENTICE/HELPER | 0 | 0 | 0
OT-ONLY | 0 | 0 | 0

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 4611
Active workers | 22
Hours per unit (to date) | 192.1
Revenue per labor hour (billed) | 258.87
Percent complete | 99.76%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 27.22% | 34%
Roughin labor share (code 120) | 46.54% | 45%
Top vendor concentration | 65.94% | 38%
Hours per unit | 192.1354 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Supervision (100) CRITICAL overrun | ⚠ WATCH | Actual $4,364 vs revised $2,400 (+82%) — needs immediate attention
Takeoff & Purchase Labor (101) CRITICAL overrun | ⚠ WATCH | Actual $9,215 vs revised $4,800 (+92%) — needs immediate attention
Underground Labor (110) over revised | ⚠ WATCH | Actual $8,974 vs revised $7,125 (+26%) — monitor
Roughin Labor (120) over revised | ⚠ WATCH | Actual $132,816 vs revised $91,880 (+45%) — monitor
Water Main/Insulation Mat (241) over revised | ⚠ WATCH | Actual $31,392 vs revised $25,015 (+25%) — monitor
Payroll Burden (995) over revised | ⚠ WATCH | Actual $93,452 vs revised $80,715 (+16%) — monitor
Top vendor concentration (California Hydronics) | ⚠ WATCH | 66% of AP ($286,931) — high, monitor
Retention aging | ✓ OK | $59,687 held · 5.0% of billed · standard range
Forecast margin | ✓ OK | 27.2% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 756539.28 | 756539.28
Revenue billed (AR ·-1) | -1193734 | 1193734
AP source total |  | 435131.49
PR source total |  | 310992.63
GL source total |  | 10415.16

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-23 | v1.0 · live | Initial build for #2104 live project. 17-tab JCR schema on revised budget basis.