## Summary
#2104 · Big 1410 Apartments
BMDC Services, LLC · 24 units · ACTIVE · 99.8% billed · COI
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
1196549 | 27.22% | 1193734 | 2815
Key facts
Original contract |  | 1143800
Revised contract (CO impact) |  | 1196549
Executed COs (net) |  | 52749
Retention held |  | 59686.7
Revised expense budget |  | 870823.24
Forecast net profit |  | 325725.76
Percent complete |  | 99.76%
Live signals
Supervision (100) CRITICAL | ⚠ WATCH | Actual $4,364 vs revised $2,400 (+82%) — needs attention
Takeoff & Purchase Labor (101) CRITICAL | ⚠ WATCH | Actual $9,215 vs revised $4,800 (+92%) — needs attention
Underground Labor (110) over | ⚠ WATCH | Actual $8,974 vs revised $7,125 (+26%) — monitor
Roughin Labor (120) over | ⚠ WATCH | Actual $132,816 vs revised $91,880 (+45%) — monitor
Water Main/Insulation Mat (241) over | ⚠ WATCH | Actual $31,392 vs revised $25,015 (+25%) — monitor
Payroll Burden (995) over | ⚠ WATCH | Actual $93,452 vs revised $80,715 (+16%) — monitor
Top vendor (California Hydronics) | ⚠ WATCH | 66% of AP — high
Retention | ✓ OK | $59,687 held · 5% standard
Forecast margin | ✓ OK | 27.2% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
California Hydronics Corp | 6 | 286931 | 65.94%
Consolidated Supply Co. | 81 | 48240.58 | 11.09%
Bank of America CC | 51 | 26613.41 | 6.116%
Pacific Plumbing Supply Co., LLC | 30 | 23158.46 | 5.322%
Ferguson Enterprises, Inc. #3007 | 7 | 20208.49 | 4.644%
Keller Supply Company | 16 | 16443.42 | 3.779%

## Transactions
Transactions Detail
JDR source transactions for job #2104 · 1831 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 100 | 06/14/24 | 352 | Gerard, Jeffrey S | 1 | 69 | 92971
PR | 100 | 06/21/24 | 524 | Gerard, Jeffrey S | 2 | 138 | 92987
PR | 100 | 07/05/24 | 45 | Gerard, Jeffrey S | 1 | 69 | 93017
PR | 100 | 07/12/24 | 207 | Gerard, Jeffrey S | 1.5 | 103.5 | 93031
PR | 100 | 07/19/24 | 413 | Gerard, Jeffrey S | 2 | 138 | 93043
PR | 100 | 07/26/24 | 600 | Gerard, Jeffrey S | 5.5 | 379.5 | 93052
PR | 100 | 08/02/24 | 40 | Gerard, Jeffrey S | 1 | 69 | 93063
PR | 100 | 08/09/24 | 274 | Gerard, Jeffrey S | 2.5 | 172.5 | 23074
PR | 100 | 08/16/24 | 463 | Gerard, Jeffrey S | 2.5 | 172.5 | 33083
PR | 100 | 08/23/24 | 725 | Gerard, Jeffrey S | 1 | 69 | 43094
PR | 100 | 08/30/24 | 867 | Gerard, Jeffrey S | 1 | 69 | 53112
PR | 100 | 09/06/24 | 44 | Gerard, Jeffrey S | 2 | 138 | 13124
PR | 100 | 09/13/24 | 252 | Gerard, Jeffrey S | 4 | 276 | 23135
PR | 100 | 09/20/24 | 423 | Gerard, Jeffrey S | 1 | 69 | 33147
PR | 100 | 10/04/24 | 43 | Gerard, Jeffrey S | 1 | 69 | 13172
PR | 100 | 10/11/24 | 250 | Gerard, Jeffrey S | 1.5 | 103.5 | 23184
PR | 100 | 10/18/24 | 462 | Gerard, Jeffrey S | 1.5 | 103.5 | 33195
PR | 100 | 10/25/24 | 609 | Gerard, Jeffrey S | 1.5 | 103.5 | 43206
PR | 100 | 10/25/24 | 609 | Gerard, Jeffrey S | 1 | 69 | 43206
PR | 100 | 11/01/24 | 38 | Gerard, Jeffrey S | 2 | 138 | 13218
PR | 100 | 11/15/24 | 378 | Gerard, Jeffrey S | 2 | 138 | 33242
PR | 100 | 11/22/24 | 533 | Gerard, Jeffrey S | 1 | 69 | 43255
PR | 100 | 11/29/24 | 681 | Gerard, Jeffrey S | 2.5 | 172.5 | 53267
PR | 100 | 12/13/24 | 265 | Gerard, Jeffrey S | 1 | 69 | 23300
PR | 100 | 12/20/24 | 451 | Gerard, Jeffrey S | 1 | 69 | 33309
PR | 100 | 12/27/24 | 570 | Gerard, Jeffrey S | 1 | 69 | 43320
PR | 100 | 01/10/25 | 204 | Gerard, Jeffrey S | 2 | 138 | 23342
PR | 100 | 01/31/25 | 726 | Gerard, Jeffrey S | 1.5 | 103.5 | 53374
PR | 100 | 02/21/25 | 340 | Gerard, Jeffrey S | 1.5 | 103.5 | 33402
PR | 100 | 02/28/25 | 530 | Gerard, Jeffrey S | 1 | 69 | 43413
PR | 100 | 03/21/25 | 436 | Gerard, Jeffrey S | 1 | 69 | 93444
PR | 100 | 04/11/25 | 214 | Gerard, Jeffrey S | 1 | 69 | 93486
PR | 100 | 04/25/25 | 577 | Gerard, Jeffrey S | 1 | 69 | 43506
PR | 100 | 06/13/25 | 207 | Gerard, Jeffrey S | 1 | 69 | 23566
PR | 100 | 06/20/25 | 334 | Gerard, Jeffrey S | 1 | 69 | 33573
PR | 100 | 07/18/25 | 324 | Gerard, Jeffrey S | 1 | 69 | 33603
PR | 100 | 10/03/25 | 30 | Gerard, Jeffrey S | 1 | 69 | 13673
PR | 100 | 10/10/25 | 183 | Gerard, Jordan E | 2 | 120 | 23681
PR | 100 | 10/31/25 | 687 | Gerard, Jeffrey S | 1.5 | 103.5 | 53704
PR | 100 | 11/14/25 | 235 | Gerard, Jeffrey S | 1 | 69 | 23715
PR | 100 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 101 | 06/07/24 | 139 | Johnson, Jake E | 4 | 208 | 92961
PR | 101 | 06/14/24 | 352 | Gerard, Jeffrey S | 3 | 207 | 92971
PR | 101 | 06/14/24 | 362 | Johnson, Jake E | 1 | 52 | 92981
PR | 101 | 06/21/24 | 524 | Gerard, Jeffrey S | 4 | 276 | 92987
PR | 101 | 06/21/24 | 533 | Johnson, Jake E | 5 | 260 | 92996
PR | 101 | 06/28/24 | 731 | Gerard, Jeffrey S | 2 | 138 | 93003
PR | 101 | 06/28/24 | 740 | Johnson, Jake E | 4 | 208 | 93012
PR | 101 | 07/05/24 | 45 | Gerard, Jeffrey S | 5 | 345 | 93017
PR | 101 | 07/05/24 | 53 | Johnson, Jake E | 2 | 104 | 93025
PR | 101 | 07/12/24 | 207 | Gerard, Jeffrey S | 2 | 138 | 93031
PR | 101 | 07/12/24 | 216 | Johnson, Jake E | 2 | 104 | 93040
PR | 101 | 07/19/24 | 413 | Gerard, Jeffrey S | 6.5 | 448.5 | 93043
PR | 101 | 07/19/24 | 422 | Johnson, Jake E | 4 | 208 | 93052
PR | 101 | 07/26/24 | 600 | Gerard, Jeffrey S | 6 | 414 | 93052
PR | 101 | 07/26/24 | 609 | Johnson, Jake E | 1 | 52 | 93061
PR | 101 | 08/02/24 | 40 | Gerard, Jeffrey S | 3 | 207 | 93063
PR | 101 | 08/09/24 | 274 | Gerard, Jeffrey S | 3 | 207 | 23074
PR | 101 | 08/09/24 | 283 | Johnson, Jake E | 1 | 52 | 23083
PR | 101 | 08/16/24 | 463 | Gerard, Jeffrey S | 4 | 276 | 33083
PR | 101 | 08/16/24 | 472 | Johnson, Jake E | 2 | 104 | 33092
PR | 101 | 08/23/24 | 725 | Gerard, Jeffrey S | 1 | 69 | 43094
PR | 101 | 08/23/24 | 734 | Johnson, Jake E | 9 | 468 | 43103
PR | 101 | 08/30/24 | 867 | Gerard, Jeffrey S | 2 | 138 | 53112
PR | 101 | 08/30/24 | 876 | Johnson, Jake E | 1 | 52 | 53121
PR | 101 | 09/06/24 | 44 | Gerard, Jeffrey S | 1 | 69 | 13124
PR | 101 | 09/06/24 | 53 | Johnson, Jake E | 3 | 156 | 13133
PR | 101 | 09/13/24 | 252 | Gerard, Jeffrey S | 2 | 138 | 23135
PR | 101 | 09/13/24 | 261 | Johnson, Jake E | 4 | 208 | 23144
PR | 101 | 09/20/24 | 432 | Johnson, Jake E | 2 | 104 | 33156
PR | 101 | 09/27/24 | 568 | Johnson, Jake E | 3 | 156 | 43167
PR | 101 | 10/04/24 | 43 | Gerard, Jeffrey S | 1 | 69 | 13172
PR | 101 | 10/04/24 | 52 | Johnson, Jake E | 4 | 208 | 13181
PR | 101 | 10/11/24 | 250 | Gerard, Jeffrey S | 1 | 69 | 23184
PR | 101 | 10/11/24 | 259 | Johnson, Jake E | 1 | 52 | 23193
PR | 101 | 10/18/24 | 471 | Johnson, Jake E | 1 | 52 | 33204
PR | 101 | 10/25/24 | 609 | Gerard, Jeffrey S | 1 | 69 | 43206
PR | 101 | 11/01/24 | 38 | Gerard, Jeffrey S | 1 | 69 | 13218
PR | 101 | 11/01/24 | 47 | Johnson, Jake E | 1 | 52 | 13227
PR | 101 | 11/08/24 | 158 | Gerard, Jeffrey S | 2 | 138 | 23230
PR | 101 | 11/08/24 | 167 | Johnson, Jake E | 2 | 104 | 23239
PR | 101 | 11/15/24 | 387 | Johnson, Jake E | 1 | 52 | 33251
PR | 101 | 12/20/24 | 460 | Johnson, Jake E | 2 | 104 | 33318
PR | 101 | 01/10/25 | 204 | Gerard, Jeffrey S | 1 | 69 | 23342
PR | 101 | 02/14/25 | 230 | Johnson, Jake E | 1 | 52 | 23400
PR | 101 | 02/21/25 | 340 | Gerard, Jeffrey S | 1 | 69 | 33402
PR | 101 | 02/28/25 | 530 | Gerard, Jeffrey S | 1 | 69 | 43413
PR | 101 | 03/07/25 | 51 | Johnson, Jake E | 1 | 52 | 13431
PR | 101 | 03/14/25 | 251 | Johnson, Jake E | 2 | 104 | 23442
PR | 101 | 04/04/25 | 43 | Johnson, Jake E | 2 | 104 | 13485
PR | 101 | 05/09/25 | 174 | Gerard, Jeffrey S | 1 | 69 | 23523
PR | 101 | 05/09/25 | 174 | Gerard, Jeffrey S | 2 | 138 | 23523
PR | 101 | 06/13/25 | 208 | Gerard, Jordan E | 2 | 120 | 23567
PR | 101 | 07/25/25 | 493 | Gerard, Jordan E | 3 | 180 | 43611
PR | 101 | 08/01/25 | 26 | Gerard, Jordan E | 2 | 120 | 13617
PR | 101 | 08/22/25 | 386 | Gerard, Jordan E | 1 | 60 | 43636
PR | 101 | 09/05/25 | 34 | Gerard, Jordan E | 1 | 60 | 13648
PR | 101 | 09/12/25 | 131 | Gerard, Jordan E | 1 | 60 | 23653
PR | 101 | 09/19/25 | 263 | Gerard, Jordan E | 1 | 60 | 33659
PR | 101 | 10/03/25 | 31 | Gerard, Jordan E | 1 | 60 | 13674
PR | 101 | 10/10/25 | 167 | Barnhart, Joseph N | 2.5 | 170 | 23665
PR | 101 | 10/10/25 | 183 | Gerard, Jordan E | 2 | 120 | 23681
PR | 101 | 11/07/25 | 76 | Gerard, Jordan E | 2 | 120 | 13710
PR | 101 | 11/14/25 | 235 | Gerard, Jeffrey S | 1 | 69 | 23715
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 2 | 120 | 33722
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 1.25 | 75 | 33722
PR | 101 | 11/21/25 | 353 | Gerard, Jordan E | 1.5 | 90 | 33722
PR | 101 | 12/19/25 | 341 | Gerard, Jordan E | 0.75 | 45 | 33739
PR | 101 | 12/19/25 | 341 | Gerard, Jordan E | 1.5 | 90 | 33739
PR | 101 | 01/16/26 | 294 | Gerard, Jordan E | 2.5 | 147.5 | 33759
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 2 | 118 | 33785
PR | 110 | 07/19/24 | 390 | Barnhart, Joseph N | 3 | 204 | 93020
PR | 110 | 07/26/24 | 595 | Eisenhauer, Tommy J | 4 | 228 | 93047
PR | 110 | 08/09/24 | 237 | Anderson, Richard P | 14 | 910 | 3037
PR | 110 | 08/09/24 | 256 | Boss, Benjamin T | 8 | 408 | 23056
PR | 110 | 08/09/24 | 270 | Eisenhauer, Tommy J | 24 | 1368 | 23070
PR | 110 | 08/09/24 | 303 | Silva Morales, Jair J | 8 | 272 | 23103
PR | 110 | 08/09/24 | 312 | Yohannes Jr., Samson | 8 | 264 | 23112
PR | 110 | 08/16/24 | 428 | Anderson, Richard P | 5.5 | 357.5 | 3048
PR | 110 | 08/16/24 | 447 | Boss, Benjamin T | 24 | 1224 | 33067
PR | 110 | 08/16/24 | 459 | Eisenhauer, Tommy J | 30 | 1710 | 33079
PR | 110 | 08/23/24 | 721 | Eisenhauer, Tommy J | 19 | 1083 | 43090
PR | 110 | 08/30/24 | 852 | Boss, Benjamin T | 4 | 204 | 53097
PR | 110 | 08/30/24 | 863 | Eisenhauer, Tommy J | 8 | 456 | 53108
PR | 110 | 06/27/25 | 486 | Eisenhauer, Tommy J | 5 | 285 | 43579
PR | 111 | 10/25/24 | 606 | Eisenhauer, Tommy J | 28 | 1596 | 43203
PR | 111 | 10/25/24 | 613 | Gomez Aguirre, Exequiel | 28 | 672 | 43210
PR | 112 | 08/16/24 | 428 | Anderson, Richard P | 6 | 390 | 3048
PR | 112 | 09/13/24 | 217 | Anderson, Richard P | 5 | 325 | 3100
PR | 112 | 09/13/24 | 222 | Del Villar, Flabio | 8 | 200 | 3105
PR | 112 | 09/13/24 | 233 | Barnhart, Joseph N | 3 | 204 | 23116
PR | 112 | 09/13/24 | 247 | Eisenhauer, Tommy J | 14 | 798 | 23130
PR | 112 | 09/20/24 | 389 | Anderson, Richard P | 5 | 325 | 3113
PR | 112 | 09/20/24 | 419 | Eisenhauer, Tommy J | 10 | 570 | 33143
PR | 112 | 09/27/24 | 542 | Barnhart, Joseph N | 3 | 204 | 43141
PR | 112 | 09/27/24 | 555 | Eisenhauer, Tommy J | 16 | 912 | 43154
PR | 120 | 09/27/24 | 555 | Eisenhauer, Tommy J | 8 | 456 | 43154
PR | 120 | 10/04/24 | 39 | Eisenhauer, Tommy J | 8 | 456 | 13168
PR | 120 | 10/18/24 | 429 | Anderson, Richard P | 1.5 | 97.5 | 3162
PR | 120 | 10/18/24 | 459 | Eisenhauer, Tommy J | 12 | 684 | 33192
PR | 120 | 10/25/24 | 606 | Eisenhauer, Tommy J | 12 | 684 | 43203
PR | 120 | 10/25/24 | 613 | Gomez Aguirre, Exequiel | 12 | 288 | 43210
PR | 120 | 11/01/24 | 6 | Anderson, Richard P | 1 | 65 | 3186
PR | 120 | 11/01/24 | 35 | Eisenhauer, Tommy J | 24 | 1368 | 13215
PR | 120 | 11/01/24 | 42 | Gomez Aguirre, Exequiel | 24 | 576 | 13222
PR | 120 | 11/08/24 | 155 | Eisenhauer, Tommy J | 40 | 2280 | 23227
PR | 120 | 11/08/24 | 162 | Gomez Aguirre, Exequiel | 40 | 960 | 23234
PR | 120 | 11/15/24 | 346 | Anderson, Richard P | 1 | 65 | 3210
PR | 120 | 11/15/24 | 375 | Eisenhauer, Tommy J | 32 | 1824 | 33239
PR | 120 | 11/15/24 | 382 | Gomez Aguirre, Exequiel | 32 | 768 | 33246
PR | 120 | 11/22/24 | 530 | Eisenhauer, Tommy J | 32 | 1824 | 43252
PR | 120 | 11/22/24 | 537 | Gomez Aguirre, Exequiel | 40 | 960 | 43259
PR | 120 | 11/29/24 | 678 | Eisenhauer, Tommy J | 28 | 1596 | 53264
PR | 120 | 11/29/24 | 685 | Gomez Aguirre, Exequiel | 32 | 768 | 53271
PR | 120 | 12/06/24 | 80 | Eisenhauer, Tommy J | 12 | 684 | 13276
PR | 120 | 12/06/24 | 87 | Gomez Aguirre, Exequiel | 24 | 576 | 13283
PR | 120 | 12/06/24 | 96 | Martinez Reyes, Juan C | 8 | 352 | 13292
PR | 120 | 12/13/24 | 250 | Barnhart, Joseph N | 3 | 204 | 23285
PR | 120 | 12/13/24 | 262 | Eisenhauer, Tommy J | 24 | 1368 | 23297
PR | 120 | 12/13/24 | 269 | Gomez Aguirre, Exequiel | 40 | 960 | 23304
PR | 120 | 12/13/24 | 278 | Martinez Reyes, Juan C | 32 | 1408 | 23313
PR | 120 | 12/20/24 | 437 | Barnhart, Joseph N | 4 | 272 | 33295
PR | 120 | 12/20/24 | 448 | Eisenhauer, Tommy J | 32 | 1824 | 33306
PR | 120 | 12/20/24 | 455 | Gomez Aguirre, Exequiel | 40 | 960 | 33313
PR | 120 | 12/20/24 | 464 | Martinez Reyes, Juan C | 40 | 1760 | 33322
PR | 120 | 12/27/24 | 544 | Del Villar, Flabio | 7 | 175 | 3295
PR | 120 | 12/27/24 | 558 | Calderon M, Roberto H | 7 | 154 | 43308
PR | 120 | 12/27/24 | 564 | Cruz, Azael S | 7 | 224 | 43314
PR | 120 | 12/27/24 | 567 | Eisenhauer, Tommy J | 16 | 912 | 43317
PR | 120 | 12/27/24 | 574 | Gomez Aguirre, Exequiel | 23 | 552 | 43324
PR | 120 | 12/27/24 | 578 | Jimenez Alvarenga, Gerson M | 7 | 273 | 43328
PR | 120 | 12/27/24 | 583 | Martinez Reyes, Juan C | 16 | 704 | 43333
PR | 120 | 12/27/24 | 585 | Melgar Moz, Brandon | 8 | 176 | 43335
PR | 120 | 01/03/25 | 12 | Anderson, Richard P | 1 | 65 | 3301
PR | 120 | 01/03/25 | 44 | Gomez Aguirre, Exequiel | 16 | 384 | 13333
PR | 120 | 01/03/25 | 53 | Martinez Reyes, Juan C | 16 | 704 | 13342
PR | 120 | 01/10/25 | 207 | Gomez Aguirre, Exequiel | 32 | 768 | 23345
PR | 120 | 01/10/25 | 216 | Martinez Reyes, Juan C | 16 | 704 | 23354
PR | 120 | 01/17/25 | 364 | Eisenhauer, Tommy J | 20 | 1140 | 33350
PR | 120 | 01/17/25 | 370 | Gomez Aguirre, Exequiel | 40 | 960 | 33356
PR | 120 | 01/17/25 | 379 | Martinez Reyes, Juan C | 30 | 1320 | 33365
PR | 120 | 01/24/25 | 531 | Eisenhauer, Tommy J | 32 | 1824 | 43361
PR | 120 | 01/24/25 | 537 | Gomez Aguirre, Exequiel | 32 | 768 | 43367
PR | 120 | 01/24/25 | 546 | Martinez Reyes, Juan C | 28 | 1232 | 43376
PR | 120 | 01/31/25 | 712 | Barnhart, Joseph N | 2 | 136 | 53360
PR | 120 | 01/31/25 | 723 | Eisenhauer, Tommy J | 35 | 1995 | 53371
PR | 120 | 01/31/25 | 729 | Gomez Aguirre, Exequiel | 24 | 576 | 53377
PR | 120 | 01/31/25 | 738 | Martinez Reyes, Juan C | 34 | 1496 | 53386
PR | 120 | 02/07/25 | 42 | Barnhart, Joseph N | 1 | 68 | 13369
PR | 120 | 02/07/25 | 53 | Eisenhauer, Tommy J | 6 | 342 | 13380
PR | 120 | 02/07/25 | 59 | Gomez Aguirre, Exequiel | 11 | 264 | 13386
PR | 120 | 02/07/25 | 68 | Martinez Reyes, Juan C | 27 | 1188 | 13395
PR | 120 | 02/14/25 | 208 | Barnhart, Joseph N | 3 | 204 | 23378
PR | 120 | 02/14/25 | 219 | Eisenhauer, Tommy J | 38 | 2166 | 23389
PR | 120 | 02/14/25 | 225 | Gomez Aguirre, Exequiel | 40 | 960 | 23395
PR | 120 | 02/14/25 | 234 | Martinez Reyes, Juan C | 24 | 1056 | 23404
PR | 120 | 02/21/25 | 337 | Eisenhauer, Tommy J | 40 | 2280 | 33399
PR | 120 | 02/21/25 | 343 | Gomez Aguirre, Exequiel | 16 | 384 | 33405
PR | 120 | 02/21/25 | 352 | Martinez Reyes, Juan C | 40 | 1760 | 33414
PR | 120 | 02/28/25 | 516 | Barnhart, Joseph N | 0.5 | 34 | 43399
PR | 120 | 02/28/25 | 527 | Eisenhauer, Tommy J | 32 | 1824 | 43410
PR | 120 | 02/28/25 | 542 | Martinez Reyes, Juan C | 24 | 1056 | 43425
PR | 120 | 03/07/25 | 40 | Eisenhauer, Tommy J | 16 | 912 | 13420
PR | 120 | 03/07/25 | 46 | Gomez Aguirre, Exequiel | 8 | 192 | 13426
PR | 120 | 03/14/25 | 240 | Eisenhauer, Tommy J | 8 | 456 | 23431
PR | 120 | 03/14/25 | 246 | Gomez Aguirre, Exequiel | 8 | 192 | 23437
PR | 120 | 03/21/25 | 433 | Eisenhauer, Tommy J | 32 | 1824 | 93441
PR | 120 | 03/21/25 | 439 | Gomez Aguirre, Exequiel | 32 | 768 | 93447
PR | 120 | 03/28/25 | 588 | Eisenhauer, Tommy J | 32 | 1824 | 93462
PR | 120 | 03/28/25 | 595 | Gomez Aguirre, Exequiel | 32 | 768 | 93469
PR | 120 | 04/04/25 | 31 | Eisenhauer, Tommy J | 40 | 2280 | 13473
PR | 120 | 04/04/25 | 38 | Gomez Aguirre, Exequiel | 40 | 960 | 13480
PR | 120 | 04/11/25 | 211 | Eisenhauer, Tommy J | 32 | 1824 | 93483
PR | 120 | 04/11/25 | 218 | Gomez Aguirre, Exequiel | 32 | 768 | 93490
PR | 120 | 04/11/25 | 227 | Martinez Reyes, Juan C | 4 | 176 | 93499
PR | 120 | 04/18/25 | 435 | Eisenhauer, Tommy J | 30 | 1710 | 33493
PR | 120 | 04/18/25 | 442 | Gomez Aguirre, Exequiel | 40 | 960 | 33500
PR | 120 | 04/25/25 | 548 | Anderson, Richard P | 4 | 260 | 3477
PR | 120 | 04/25/25 | 574 | Eisenhauer, Tommy J | 22 | 1254 | 43503
PR | 120 | 04/25/25 | 581 | Gomez Aguirre, Exequiel | 40 | 960 | 43510
PR | 120 | 04/25/25 | 590 | Martinez Reyes, Juan C | 16 | 704 | 43519
PR | 120 | 05/02/25 | 17 | Barnhart, Joseph N | 0.5 | 34 | 13502
PR | 120 | 05/02/25 | 28 | Eisenhauer, Tommy J | 40 | 2280 | 13513
PR | 120 | 05/02/25 | 35 | Gomez Aguirre, Exequiel | 24 | 576 | 13520
PR | 120 | 05/09/25 | 162 | Barnhart, Joseph N | 5 | 340 | 23511
PR | 120 | 05/09/25 | 172 | Eisenhauer, Tommy J | 24 | 1368 | 23521
PR | 120 | 05/16/25 | 371 | Eisenhauer, Tommy J | 28 | 1596 | 33530
PR | 120 | 05/16/25 | 377 | Gomez Aguirre, Exequiel | 40 | 960 | 33536
PR | 120 | 05/23/25 | 457 | Barnhart, Joseph N | 0.5 | 34 | 43529
PR | 120 | 05/23/25 | 467 | Eisenhauer, Tommy J | 24 | 1368 | 43539
PR | 120 | 05/23/25 | 473 | Gomez Aguirre, Exequiel | 24 | 576 | 43545
PR | 120 | 05/30/25 | 555 | Eisenhauer, Tommy J | 20 | 1140 | 53547
PR | 120 | 05/30/25 | 562 | Gomez Aguirre, Exequiel | 24 | 576 | 53554
PR | 120 | 06/06/25 | 33 | Barnhart, Joseph N | 2 | 136 | 13545
PR | 120 | 06/06/25 | 43 | Eisenhauer, Tommy J | 24 | 1368 | 13555
PR | 120 | 06/06/25 | 50 | Gomez Aguirre, Exequiel | 40 | 1040 | 13562
PR | 120 | 06/13/25 | 204 | Eisenhauer, Tommy J | 39 | 2223 | 23563
PR | 120 | 06/13/25 | 211 | Gomez Aguirre, Exequiel | 39 | 1014 | 23570
PR | 120 | 06/20/25 | 331 | Eisenhauer, Tommy J | 32 | 1824 | 33570
PR | 120 | 06/20/25 | 338 | Gomez Aguirre, Exequiel | 32 | 832 | 33577
PR | 120 | 06/27/25 | 486 | Eisenhauer, Tommy J | 8 | 456 | 43579
PR | 120 | 06/27/25 | 493 | Gomez Aguirre, Exequiel | 13 | 338 | 43586
PR | 120 | 07/03/25 | 29 | Eisenhauer, Tommy J | 40 | 2280 | 13586
PR | 120 | 07/03/25 | 36 | Gomez Aguirre, Exequiel | 40 | 1040 | 13593
PR | 120 | 07/11/25 | 154 | Eisenhauer, Tommy J | 18 | 1026 | 23593
PR | 120 | 07/11/25 | 160 | Gomez Aguirre, Exequiel | 22 | 572 | 23599
PR | 120 | 07/18/25 | 327 | Gomez Aguirre, Exequiel | 8 | 208 | 33606
PR | 120 | 07/25/25 | 479 | Barnhart, Joseph N | 2 | 136 | 43597
PR | 120 | 07/25/25 | 489 | Eisenhauer, Tommy J | 4 | 228 | 43607
PR | 120 | 07/25/25 | 495 | Gomez Aguirre, Exequiel | 4 | 104 | 43613
PR | 120 | 08/01/25 | 22 | Eisenhauer, Tommy J | 40 | 2280 | 13613
PR | 120 | 08/01/25 | 28 | Gomez Aguirre, Exequiel | 36 | 936 | 13619
PR | 120 | 08/08/25 | 153 | Eisenhauer, Tommy J | 32 | 1824 | 23620
PR | 120 | 08/08/25 | 159 | Gomez Aguirre, Exequiel | 32 | 832 | 23626
PR | 120 | 08/15/25 | 278 | Eisenhauer, Tommy J | 35 | 1995 | 33625
PR | 120 | 08/15/25 | 284 | Gomez Aguirre, Exequiel | 36 | 936 | 33631
PR | 120 | 08/22/25 | 388 | Gomez Aguirre, Exequiel | 24 | 624 | 43638
PR | 120 | 08/22/25 | 388 | Gomez Aguirre, Exequiel | 8 | 208 | 43638
PR | 120 | 08/29/25 | 534 | Barnhart, Joseph N | 1 | 68 | 53627
PR | 120 | 08/29/25 | 545 | Eisenhauer, Tommy J | 37 | 2109 | 53638
PR | 120 | 08/29/25 | 551 | Gomez Aguirre, Exequiel | 40 | 1040 | 53644
PR | 120 | 09/05/25 | 30 | Eisenhauer, Tommy J | 30 | 1710 | 13644
PR | 120 | 09/05/25 | 36 | Gomez Aguirre, Exequiel | 30 | 780 | 13650
PR | 120 | 09/12/25 | 127 | Eisenhauer, Tommy J | 24 | 1368 | 23649
PR | 120 | 09/12/25 | 133 | Gomez Aguirre, Exequiel | 32 | 832 | 23655
PR | 120 | 09/19/25 | 259 | Eisenhauer, Tommy J | 18 | 1026 | 33655
PR | 120 | 09/19/25 | 265 | Gomez Aguirre, Exequiel | 13 | 338 | 33661
PR | 120 | 09/26/25 | 430 | Eisenhauer, Tommy J | 1.5 | 85.5 | 43662
PR | 120 | 09/26/25 | 436 | Gomez Aguirre, Exequiel | 0.25 | 6.5 | 43668
PR | 120 | 10/03/25 | 26 | Eisenhauer, Tommy J | 2.75 | 156.75 | 13669
PR | 120 | 10/03/25 | 56 | Suniga Aviles, Kelvin A | 8 | 192 | 13699
PR | 120 | 10/03/25 | 62 | Zuniga Avilez, Eduar A | 8 | 192 | 13705
PR | 120 | 10/10/25 | 178 | Eisenhauer, Tommy J | 5.75 | 327.75 | 23676
PR | 120 | 10/10/25 | 178 | Eisenhauer, Tommy J | 4.75 | 270.75 | 23676
PR | 120 | 10/10/25 | 186 | Gomez Aguirre, Exequiel | 8 | 208 | 23684
PR | 120 | 10/24/25 | 517 | Eisenhauer, Tommy J | 3 | 171 | 43693
PR | 120 | 10/31/25 | 683 | Eisenhauer, Tommy J | 0.25 | 14.25 | 53700
PR | 120 | 10/31/25 | 683 | Eisenhauer, Tommy J | 3.75 | 213.75 | 53700
PR | 120 | 11/07/25 | 59 | Barnhart, Joseph N | 0.75 | 51 | 13693
PR | 120 | 11/07/25 | 72 | Eisenhauer, Tommy J | 5 | 285 | 13706
PR | 120 | 11/07/25 | 79 | Gomez Aguirre, Exequiel | 0.75 | 19.5 | 13713
PR | 120 | 11/14/25 | 232 | Eisenhauer, Tommy J | 8 | 456 | 23712
PR | 120 | 11/14/25 | 239 | Gomez Aguirre, Exequiel | 7.5 | 195 | 23719
PR | 120 | 11/21/25 | 349 | Eisenhauer, Tommy J | 7.75 | 441.75 | 33718
PR | 120 | 11/21/25 | 356 | Gomez Aguirre, Exequiel | 8 | 208 | 33725
PR | 120 | 11/21/25 | 356 | Gomez Aguirre, Exequiel | 2.75 | 71.5 | 33725
PR | 120 | 11/28/25 | 532 | Eisenhauer, Tommy J | 8 | 456 | 43722
PR | 120 | 11/28/25 | 540 | Gomez Aguirre, Exequiel | 8 | 208 | 43730
PR | 120 | 12/05/25 | 58 | Eisenhauer, Tommy J | 8 | 456 | 13726
PR | 120 | 12/05/25 | 66 | Gomez Aguirre, Exequiel | 0.75 | 19.5 | 13734
PR | 120 | 12/05/25 | 66 | Gomez Aguirre, Exequiel | 2.25 | 58.5 | 13734
PR | 120 | 12/12/25 | 195 | Eisenhauer, Tommy J | 8 | 456 | 23730
PR | 120 | 12/12/25 | 195 | Eisenhauer, Tommy J | 8 | 456 | 23730
PR | 120 | 12/12/25 | 203 | Gomez Aguirre, Exequiel | 0.75 | 19.5 | 23738
PR | 120 | 12/19/25 | 336 | Eisenhauer, Tommy J | 8.5 | 484.5 | 33734
PR | 120 | 12/19/25 | 344 | Gomez Aguirre, Exequiel | 8 | 208 | 33742
PR | 120 | 01/23/26 | 487 | Gomez Aguirre, Exequiel | 3 | 84 | 43766
PR | 120 | 01/30/26 | 600 | Gomez Aguirre, Exequiel | 3 | 84 | 53771
PR | 120 | 01/30/26 | 600 | Gomez Aguirre, Exequiel | 2.75 | 77 | 53771
PR | 120 | 02/06/26 | 56 | Barnhart, Joseph N | 2.5 | 175 | 13756
PR | 120 | 02/13/26 | 188 | Barnhart, Joseph N | 4.25 | 297.5 | 23761
PR | 120 | 02/13/26 | 188 | Barnhart, Joseph N | 2 | 140 | 23761
PR | 120 | 02/13/26 | 207 | Gomez Aguirre, Exequiel | 1 | 28 | 23780
PR | 120 | 02/13/26 | 214 | Mackey, Cole J | 8 | 416 | 23787
PR | 120 | 02/13/26 | 214 | Mackey, Cole J | 8 | 416 | 23787
PR | 120 | 02/13/26 | 214 | Mackey, Cole J | 7.5 | 390 | 23787
PR | 120 | 02/13/26 | 214 | Mackey, Cole J | 8 | 416 | 23787
PR | 120 | 02/13/26 | 220 | Nunez Bravo, Jose L | 3.25 | 78 | 23793
PR | 120 | 02/13/26 | 229 | Suniga Aviles, Kelvin A | 7.75 | 201.5 | 23802
PR | 120 | 02/20/26 | 304 | Barnhart, Joseph N | 3.25 | 227.5 | 33768
PR | 120 | 02/20/26 | 304 | Barnhart, Joseph N | 0.75 | 52.5 | 33768
PR | 120 | 02/20/26 | 304 | Barnhart, Joseph N | 1 | 70 | 33768
PR | 120 | 02/20/26 | 330 | Mackey, Cole J | 8 | 416 | 33794
PR | 120 | 02/20/26 | 330 | Mackey, Cole J | 4.75 | 247 | 33794
PR | 120 | 02/20/26 | 330 | Mackey, Cole J | 7 | 364 | 33794
PR | 120 | 02/20/26 | 330 | Mackey, Cole J | 8 | 416 | 33794
PR | 120 | 02/20/26 | 330 | Mackey, Cole J | 8 | 416 | 33794
PR | 120 | 02/27/26 | 478 | Mackey, Cole J | 3 | 156 | 43798
PR | 120 | 02/27/26 | 478 | Mackey, Cole J | 5 | 260 | 43798
PR | 120 | 03/06/26 | 48 | Barnhart, Joseph N | 1.25 | 87.5 | 13776
PR | 120 | 03/06/26 | 74 | Mackey, Cole J | 8 | 416 | 13802
PR | 120 | 03/27/26 | 479 | Barnhart, Joseph N | 1 | 70 | 43788
PR | 120 | 03/27/26 | 479 | Barnhart, Joseph N | 2 | 140 | 43788
PR | 130 | 08/29/25 | 547 | Games, Jordan M | 4 | 212 | 53640
PR | 130 | 09/12/25 | 116 | Barnhart, Joseph N | 1 | 68 | 23638
PR | 130 | 09/19/25 | 261 | Games, Jordan M | 4 | 212 | 33657
PR | 130 | 10/03/25 | 26 | Eisenhauer, Tommy J | 7 | 399 | 13669
PR | 130 | 10/03/25 | 29 | Games, Jordan M | 1.25 | 66.25 | 13672
PR | 130 | 10/03/25 | 29 | Games, Jordan M | 8.75 | 463.75 | 13672
PR | 130 | 10/03/25 | 29 | Games, Jordan M | 4.75 | 251.75 | 13672
PR | 130 | 10/03/25 | 29 | Games, Jordan M | 4.5 | 238.5 | 13672
PR | 130 | 10/03/25 | 33 | Gomez Aguirre, Exequiel | 7.75 | 201.5 | 13676
PR | 130 | 10/10/25 | 164 | Araque, Mario W | 8 | 192 | 23662
PR | 130 | 10/10/25 | 164 | Araque, Mario W | 8 | 192 | 23662
PR | 130 | 10/10/25 | 164 | Araque, Mario W | 8 | 192 | 23662
PR | 130 | 10/10/25 | 164 | Araque, Mario W | 8 | 192 | 23662
PR | 130 | 10/10/25 | 164 | Araque, Mario W | 8 | 192 | 23662
PR | 130 | 10/10/25 | 181 | Games, Jordan M | 8 | 424 | 23679
PR | 130 | 10/10/25 | 181 | Games, Jordan M | 4 | 212 | 23679
PR | 130 | 10/10/25 | 181 | Games, Jordan M | 8 | 424 | 23679
PR | 130 | 10/10/25 | 181 | Games, Jordan M | 4.5 | 238.5 | 23679
PR | 130 | 10/10/25 | 181 | Games, Jordan M | 2.75 | 145.75 | 23679
PR | 130 | 10/17/25 | 369 | Araque, Mario W | 8 | 192 | 33670
PR | 130 | 10/17/25 | 369 | Araque, Mario W | 7.5 | 180 | 33670
PR | 130 | 10/17/25 | 369 | Araque, Mario W | 8.5 | 204 | 33670
PR | 130 | 10/17/25 | 369 | Araque, Mario W | 4.25 | 102 | 33670
PR | 130 | 10/17/25 | 372 | Barnhart, Joseph N | 0.25 | 17 | 33673
PR | 130 | 10/17/25 | 386 | Games, Jordan M | 8 | 424 | 33687
PR | 130 | 10/17/25 | 386 | Games, Jordan M | 5.75 | 304.75 | 33687
PR | 130 | 10/17/25 | 386 | Games, Jordan M | 8 | 424 | 33687
PR | 130 | 10/17/25 | 386 | Games, Jordan M | 4.5 | 238.5 | 33687
PR | 130 | 10/31/25 | 686 | Games, Jordan M | 2 | 106 | 53703
PR | 130 | 10/31/25 | 686 | Games, Jordan M | 8 | 424 | 53703
PR | 130 | 11/07/25 | 59 | Barnhart, Joseph N | 1.25 | 85 | 13693
PR | 130 | 11/14/25 | 219 | Barnhart, Joseph N | 2.5 | 170 | 23699
PR | 130 | 11/21/25 | 336 | Barnhart, Joseph N | 8.25 | 561 | 33705
PR | 130 | 11/21/25 | 336 | Barnhart, Joseph N | 2.75 | 187 | 33705
PR | 130 | 11/21/25 | 336 | Barnhart, Joseph N | 5.75 | 391 | 33705
PR | 130 | 11/21/25 | 336 | Barnhart, Joseph N | 5.5 | 374 | 33705
PR | 130 | 11/21/25 | 349 | Eisenhauer, Tommy J | 3.75 | 213.75 | 33718
PR | 130 | 12/19/25 | 323 | Barnhart, Joseph N | 2 | 136 | 33721
PR | 130 | 12/26/25 | 511 | Barnhart, Joseph N | 2 | 136 | 43729
PR | 130 | 12/26/25 | 511 | Barnhart, Joseph N | 5.75 | 391 | 43729
PR | 130 | 01/16/26 | 276 | Barnhart, Joseph N | 3.25 | 227.5 | 33741
PR | 130 | 01/30/26 | 580 | Barnhart, Joseph N | 2.5 | 175 | 53751
PR | 130 | 03/06/26 | 48 | Barnhart, Joseph N | 2 | 140 | 13776
PR | 140 | 01/03/25 | 38 | Eisenhauer, Tommy J | 8 | 456 | 13327
PR | 140 | 01/10/25 | 201 | Eisenhauer, Tommy J | 24 | 1368 | 23339
PR | 140 | 01/24/25 | 531 | Eisenhauer, Tommy J | 4 | 228 | 43361
PR | 140 | 01/24/25 | 546 | Martinez Reyes, Juan C | 4 | 176 | 43376
PR | 140 | 01/31/25 | 729 | Gomez Aguirre, Exequiel | 16 | 384 | 53377
PR | 140 | 01/31/25 | 738 | Martinez Reyes, Juan C | 4 | 176 | 53386
PR | 140 | 02/07/25 | 59 | Gomez Aguirre, Exequiel | 8 | 192 | 13386
PR | 140 | 08/22/25 | 382 | Eisenhauer, Tommy J | 8 | 456 | 43632
PR | 140 | 09/12/25 | 116 | Barnhart, Joseph N | 1 | 68 | 23638
PR | 140 | 12/05/25 | 45 | Barnhart, Joseph N | 2.5 | 170 | 13713
PR | 140 | 12/19/25 | 323 | Barnhart, Joseph N | 0.25 | 17 | 33721
PR | 140 | 01/30/26 | 580 | Barnhart, Joseph N | 0.5 | 35 | 53751
PR | 140 | 02/20/26 | 304 | Barnhart, Joseph N | 1 | 70 | 33768
PR | 140 | 02/20/26 | 330 | Mackey, Cole J | 1 | 52 | 33794
PR | 141 | 11/15/24 | 363 | Barnhart, Joseph N | 4 | 272 | 33227
PR | 141 | 11/15/24 | 448 | Barnhart, Joseph N | 4 | -272 | 93223
PR | 141 | 01/31/25 | 712 | Barnhart, Joseph N | 2 | 136 | 53360
PR | 141 | 02/07/25 | 53 | Eisenhauer, Tommy J | 8 | 456 | 13380
PR | 141 | 02/14/25 | 234 | Martinez Reyes, Juan C | 16 | 704 | 23404
PR | 141 | 02/21/25 | 343 | Gomez Aguirre, Exequiel | 24 | 576 | 33405
PR | 141 | 02/28/25 | 516 | Barnhart, Joseph N | 1.5 | 102 | 43399
PR | 141 | 02/28/25 | 533 | Gomez Aguirre, Exequiel | 40 | 960 | 43416
PR | 141 | 03/07/25 | 29 | Barnhart, Joseph N | 1 | 68 | 13409
PR | 141 | 03/07/25 | 40 | Eisenhauer, Tommy J | 16 | 912 | 13420
PR | 141 | 03/07/25 | 46 | Gomez Aguirre, Exequiel | 24 | 576 | 13426
PR | 141 | 03/14/25 | 240 | Eisenhauer, Tommy J | 32 | 1824 | 23431
PR | 141 | 03/14/25 | 246 | Gomez Aguirre, Exequiel | 32 | 768 | 23437
PR | 141 | 03/21/25 | 433 | Eisenhauer, Tommy J | 8 | 456 | 93441
PR | 141 | 03/21/25 | 439 | Gomez Aguirre, Exequiel | 8 | 192 | 93447
PR | 141 | 03/28/25 | 595 | Gomez Aguirre, Exequiel | 8 | 192 | 93469
PR | 141 | 04/18/25 | 435 | Eisenhauer, Tommy J | 2 | 114 | 33493
PR | 141 | 04/18/25 | 451 | Martinez Reyes, Juan C | 8 | 352 | 33509
PR | 141 | 05/02/25 | 35 | Gomez Aguirre, Exequiel | 8 | 192 | 13520
PR | 141 | 05/09/25 | 172 | Eisenhauer, Tommy J | 8 | 456 | 23521
PR | 141 | 05/09/25 | 178 | Gomez Aguirre, Exequiel | 32 | 768 | 23527
PR | 141 | 05/23/25 | 467 | Eisenhauer, Tommy J | 16 | 912 | 43539
PR | 141 | 05/23/25 | 473 | Gomez Aguirre, Exequiel | 16 | 384 | 43545
PR | 141 | 06/27/25 | 476 | Barnhart, Joseph N | 1 | 68 | 43569
PR | 141 | 08/22/25 | 382 | Eisenhauer, Tommy J | 8 | 456 | 43632
PR | 141 | 08/22/25 | 388 | Gomez Aguirre, Exequiel | 8 | 208 | 43638
PR | 141 | 02/06/26 | 56 | Barnhart, Joseph N | 0.5 | 52.5 | 13756
PR | 141 | 02/13/26 | 188 | Barnhart, Joseph N | 7.75 | 542.5 | 23761
PR | 141 | 02/13/26 | 220 | Nunez Bravo, Jose L | 4.5 | 108 | 23793
PR | 141 | 02/13/26 | 220 | Nunez Bravo, Jose L | 7.5 | 180 | 23793
PR | 141 | 02/13/26 | 220 | Nunez Bravo, Jose L | 8 | 192 | 23793
PR | 141 | 02/13/26 | 220 | Nunez Bravo, Jose L | 8 | 192 | 23793
PR | 141 | 03/06/26 | 74 | Mackey, Cole J | 6 | 312 | 13802
PR | 141 | 03/06/26 | 74 | Mackey, Cole J | 8 | 416 | 13802
PR | 141 | 03/13/26 | 193 | Barnhart, Joseph N | 0.5 | 35 | 23780
PR | 141 | 03/13/26 | 219 | Mackey, Cole J | 8 | 416 | 23806
PR | 141 | 03/13/26 | 219 | Mackey, Cole J | 3.75 | 195 | 23806
PR | 141 | 03/13/26 | 219 | Mackey, Cole J | 8 | 416 | 23806
PR | 141 | 03/13/26 | 219 | Mackey, Cole J | 8 | 416 | 23806
PR | 141 | 03/20/26 | 337 | Mackey, Cole J | 4.5 | 234 | 33810
PR | 141 | 03/20/26 | 337 | Mackey, Cole J | 8 | 416 | 33810
PR | 141 | 03/20/26 | 337 | Mackey, Cole J | 4 | 208 | 33810
PR | 141 | 03/20/26 | 337 | Mackey, Cole J | 8 | 416 | 33810
PR | 141 | 03/27/26 | 479 | Barnhart, Joseph N | 0.25 | 17.5 | 43788
PR | 141 | 03/27/26 | 505 | Mackey, Cole J | 8 | 416 | 43814
PR | 142 | 01/31/25 | 712 | Barnhart, Joseph N | 2 | 136 | 53360
PR | 142 | 06/27/25 | 476 | Barnhart, Joseph N | 2 | 136 | 43569
PR | 142 | 08/01/25 | 12 | Barnhart, Joseph N | 1 | 68 | 13603
PR | 142 | 08/29/25 | 534 | Barnhart, Joseph N | 2 | 136 | 53627
PR | 142 | 09/12/25 | 116 | Barnhart, Joseph N | 1 | 68 | 23638
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 1.75 | 119 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 5 | 340 | 23665
PR | 142 | 10/10/25 | 167 | Barnhart, Joseph N | 1.5 | 102 | 23665
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 1.75 | 119 | 13693
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 2 | 136 | 13693
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 2 | 136 | 13693
PR | 142 | 11/07/25 | 59 | Barnhart, Joseph N | 1.5 | 102 | 13693
PR | 142 | 11/07/25 | 72 | Eisenhauer, Tommy J | 1 | 57 | 13706
PR | 142 | 11/14/25 | 219 | Barnhart, Joseph N | 0.75 | 51 | 23699
PR | 142 | 11/21/25 | 336 | Barnhart, Joseph N | 8 | 544 | 33705
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 1.25 | 85 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 2.25 | 153 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 2.75 | 187 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 2.25 | 153 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 2.75 | 187 | 43709
PR | 142 | 11/28/25 | 519 | Barnhart, Joseph N | 8 | 544 | 43709
PR | 142 | 12/05/25 | 45 | Barnhart, Joseph N | 8.5 | 578 | 13713
PR | 142 | 12/05/25 | 45 | Barnhart, Joseph N | 1 | 68 | 13713
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 4 | 272 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 4.25 | 289 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 1 | 68 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 3.25 | 221 | 23717
PR | 142 | 12/12/25 | 182 | Barnhart, Joseph N | 0.5 | 34 | 23717
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 8 | 544 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 3 | 204 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 1.75 | 119 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 1 | 68 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 2 | 136 | 33721
PR | 142 | 12/19/25 | 323 | Barnhart, Joseph N | 2 | 136 | 33721
PR | 142 | 12/19/25 | 336 | Eisenhauer, Tommy J | 2 | 114 | 33734
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 2.25 | 153 | 43729
PR | 142 | 12/26/25 | 511 | Barnhart, Joseph N | 3.25 | 221 | 43729
PR | 142 | 01/09/26 | 130 | Barnhart, Joseph N | 1.75 | 122.5 | 23737
PR | 142 | 01/09/26 | 130 | Barnhart, Joseph N | 2.25 | 157.5 | 23737
PR | 142 | 01/09/26 | 130 | Barnhart, Joseph N | 2 | 140 | 23737
PR | 142 | 01/16/26 | 276 | Barnhart, Joseph N | 2.25 | 157.5 | 33741
PR | 142 | 01/23/26 | 467 | Barnhart, Joseph N | 3 | 210 | 43746
PR | 142 | 01/30/26 | 580 | Barnhart, Joseph N | 2.25 | 157.5 | 53751
PR | 142 | 02/27/26 | 452 | Barnhart, Joseph N | 0.5 | 35 | 43772
PR | 142 | 02/27/26 | 452 | Barnhart, Joseph N | 1 | 70 | 43772
PR | 142 | 02/27/26 | 452 | Barnhart, Joseph N | 6.75 | 472.5 | 43772
PR | 142 | 03/06/26 | 48 | Barnhart, Joseph N | 2.5 | 175 | 13776
PR | 142 | 03/06/26 | 48 | Barnhart, Joseph N | 1 | 70 | 13776
PR | 142 | 03/06/26 | 48 | Barnhart, Joseph N | 0.75 | 52.5 | 13776
PR | 142 | 03/06/26 | 48 | Barnhart, Joseph N | 1.5 | 105 | 13776
PR | 142 | 03/06/26 | 48 | Barnhart, Joseph N | 0.75 | 52.5 | 13776
PR | 142 | 03/13/26 | 193 | Barnhart, Joseph N | 1.5 | 105 | 23780
PR | 142 | 03/13/26 | 193 | Barnhart, Joseph N | 0.5 | 35 | 23780
PR | 142 | 03/13/26 | 193 | Barnhart, Joseph N | 1.5 | 105 | 23780
PR | 142 | 03/13/26 | 193 | Barnhart, Joseph N | 0.75 | 52.5 | 23780
PR | 142 | 03/20/26 | 306 | Anderson, Richard P | 0.5 | 33.5 | 33779
PR | 142 | 03/20/26 | 306 | Anderson, Richard P | 0.5 | 33.5 | 33779
PR | 142 | 03/20/26 | 311 | Barnhart, Joseph N | 1 | 70 | 33784
PR | 142 | 03/20/26 | 311 | Barnhart, Joseph N | 2 | 140 | 33784
GL | 210 | 07/09/24 | 113 | 06/30/2024 to 07/06/2024 |  | 83.54
AP | 210 | 07/24/24 | 553 | Consolidated Supply Co. |  | 97.07 | S012007916.001
AP | 210 | 08/01/24 | 137 | Consolidated Supply Co. |  | 2002.14 | S011975702.001
AP | 210 | 08/12/24 | 366 | Pacific Plumbing Supply Co., LLC |  | 339.71 | 51632302
GL | 210 | 08/12/24 | 372 |  |  | 272.04
AP | 210 | 08/13/24 | 384 | Rosen Supply Kirkland |  | 429.14 | 25472.01
AP | 210 | 08/16/24 | 529 | Rosen Supply Kirkland |  | 290.12 | 25604.01
AP | 210 | 08/20/24 | 590 | Consolidated Supply Co. |  | 2249.43 | S012037408.001
AP | 210 | 08/21/24 | 666 | Consolidated Supply Co. |  | 235.44 | S012047601.001
AP | 210 | 08/23/24 | 787 | Consolidated Supply Co. |  | 31.31 | S012049098.001
AP | 210 | 09/01/24 | 96 | Consolidated Supply Co. |  | -2249.43 | S012037408.001A
AP | 210 | 09/01/24 | 97 | Consolidated Supply Co. |  | 249.43 | S012037408.001B
GL | 211 | 07/09/24 | 113 | 06/30/2024 to 07/06/2024 |  | 65.85
GL | 211 | 07/23/24 | 528 | Req 558 |  | 1009.81
GL | 211 | 08/12/24 | 372 |  |  | 24.7
GL | 211 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 69.67
GL | 211 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 200
AP | 211 | 09/17/24 | 353 | Rosen Supply Kirkland |  | 74.43 | 25631.01
AP | 211 | 10/25/24 | 669 | Consolidated Supply Co. |  | 1215.36 | S012033487.001
GL | 211 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 33.16
AP | 211 | 11/12/24 | 270 | Consolidated Supply Co. |  | 55.4 | S012156416.001
GL | 211 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 12.9
GL | 211 | 04/22/25 | 528 | 04/13/2025 to 4/19/2025 |  | 31.92
GL | 211 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 5.2
GL | 211 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 24.41
GL | 211 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 42
GL | 211 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 6.05
GL | 211 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 51.75
GL | 211 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | -18.33
GL | 212 | 09/16/24 | 309 | 2024-09-08 to 2024-09-14 |  | 1187.16
GL | 212 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 44.54
GL | 212 | 10/03/24 | 86 | Richard Anderson |  | 31.22
GL | 220 | 07/31/24 | 662 | Transfer 2024-07-21 to 2024-07-27 |  | 59.94
GL | 220 | 08/12/24 | 372 |  |  | 43.32
GL | 220 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 27.17
AP | 220 | 10/22/24 | 562 | Consolidated Supply Co. |  | 3053.87 | S012035741.001
GL | 220 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 35.45
GL | 220 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 59.38
GL | 220 | 11/11/24 | 246 | 2024-11-03 to 2024-11-09 |  | 297.86
AP | 220 | 11/12/24 | 271 | Consolidated Supply Co. |  | 450.14 | S012158613.001
AP | 220 | 11/12/24 | 272 | Consolidated Supply Co. |  | 89.87 | S012162811.001
AP | 220 | 11/13/24 | 331 | Consolidated Supply Co. |  | 66.92 | S012168696.001
AP | 220 | 11/15/24 | 435 | Consolidated Supply Co. |  | 227.08 | S012170764.001
AP | 220 | 11/18/24 | 476 | Consolidated Supply Co. |  | 16.23 | S012182722.001
AP | 220 | 11/18/24 | 477 | Consolidated Supply Co. |  | 158.24 | S012182722.002
GL | 220 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 20.27
GL | 220 | 11/27/24 | 723 | 2024-11-17 to 2024-11-23 |  | 52.11
GL | 220 | 12/03/24 | 16 | 2024-11-24 to 2024-11-30 |  | 8
AP | 220 | 12/04/24 | 39 | Consolidated Supply Co. |  | 239.13 | S012197644.001
AP | 220 | 12/17/24 | 341 | Consolidated Supply Co. |  | 71.29 | S012204904.001
AP | 220 | 12/17/24 | 342 | Consolidated Supply Co. |  | 3558.13 | S012043912.001
GL | 220 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 44.53
GL | 220 | 12/30/24 | 679 | 2024-12-22 to 2024-12-28 |  | 41.95
AP | 220 | 01/02/25 | 144 | Rosen Supply Kirkland |  | 25.73 | 28608.01
AP | 220 | 01/08/25 | 156 | Pacific Plumbing Supply Co., LLC |  | 368.82 | 51737607
AP | 220 | 01/08/25 | 161 | Rosen Supply Kirkland |  | 596.92 | 28584.01
GL | 220 | 01/14/25 | 314 | 2025-01-05 to 2025-01-11 |  | 104.13
AP | 220 | 01/15/25 | 316 | Consolidated Supply Co. |  | 212.11 | S012236047.001
GL | 220 | 01/20/25 | 425 | 2025-01-12 to 2025-01-18 |  | 96.54
AP | 220 | 01/22/25 | 467 | Consolidated Supply Co. |  | 123.1 | S012244858.001
AP | 220 | 01/22/25 | 468 | Consolidated Supply Co. |  | 50.44 | S012248855.001
AP | 220 | 01/22/25 | 469 | Consolidated Supply Co. |  | 114.8 | S012250463.001
AP | 220 | 01/22/25 | 493 | Consolidated Supply Co. |  | 754.67 | S012255630.001
GL | 220 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 304.02
GL | 220 | 02/05/25 | 21 | 2025-01-26 to 2025-02-01 |  | 34.84
AP | 220 | 02/05/25 | 23 | Consolidated Supply Co. |  | 148.54 | S012274156.001
GL | 220 | 02/10/25 | 139 | 2025-02-02 to 2025-02-08 |  | 103.43
AP | 220 | 02/13/25 | 611 | Pacific Plumbing Supply Co., LLC |  | 336.62 | 51793712
AP | 220 | 02/14/25 | 267 | Consolidated Supply Co. |  | 628.63 | S012290475.001
AP | 220 | 02/14/25 | 268 | Consolidated Supply Co. |  | 101.47 | S012291083.001
GL | 220 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 214.87
AP | 220 | 02/17/25 | 296 | Rosen Supply Kirkland |  | 193.03 | 29814.01
GL | 220 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 326.14
GL | 220 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 124.03
AP | 220 | 02/28/25 | 597 | Pacific Plumbing Supply Co., LLC |  | 405.33 | 51792871
GL | 220 | 03/18/25 | 348 | 2025-03-09 to 2025-03-15 |  | 245.94
AP | 220 | 03/19/25 | 362 | Consolidated Supply Co. |  | 306.38 | S012335980.001
GL | 220 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 27.77
GL | 220 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 136.75
GL | 220 | 04/08/25 | 123 | 2025-03-30 to 2025-04-05 |  | 113.71
GL | 220 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 84.26
AP | 220 | 04/11/25 | 312 | Pacific Plumbing Supply Co., LLC |  | 34.04 | 51825083
AP | 220 | 04/16/25 | 382 | Capital One Credit Card |  | 24.96 | 040325-1
AP | 220 | 04/21/25 | 513 | Pacific Plumbing Supply Co., LLC |  | 40.3 | 51833496
GL | 220 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 4.94
AP | 220 | 05/02/25 | 93 | Consolidated Supply Co. |  | 12.98 | S012403721.001
AP | 220 | 05/02/25 | 102 | Pacific Plumbing Supply Co., LLC |  | 4.7 | 51843722
GL | 220 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 103.87
AP | 220 | 05/07/25 | 141 | Rosen Supply Kirkland |  | 86.94 | 31446.01
AP | 220 | 05/09/25 | 243 | Pacific Plumbing Supply Co., LLC |  | 15 | 51851527
GL | 220 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 49.23
GL | 220 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 38.93
GL | 220 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 10.89
AP | 220 | 05/31/25 | 680 | Rosen Supply Kirkland |  | 135.11 | 31834.01
GL | 220 | 05/31/25 | 681 | 2025-05-26 to 2025-05-30 |  | 11.24
AP | 220 | 06/04/25 | 13 | Pacific Plumbing Supply Co., LLC |  | 251.8 | 51851525
GL | 220 | 06/10/25 | 150 | 2025-06-01 to 2025-06-07 |  | 50.75
GL | 220 | 06/16/25 | 282 | 2025-06-09 to 2025-06-13 |  | 36.53
GL | 220 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 34.85
GL | 220 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 34.51
AP | 220 | 07/09/25 | 92 | Consolidated Supply Co. |  | 532.98 | S012488060.001
AP | 220 | 07/09/25 | 93 | Consolidated Supply Co. |  | 116.5 | S012490543.001
AP | 220 | 07/30/25 | 597 | Consolidated Supply Co. |  | 79.8 | S012527584.001
AP | 220 | 08/01/25 | 99 | Pacific Plumbing Supply Co., LLC |  | 440.6 | 51923577
AP | 220 | 08/07/25 | 192 | Consolidated Supply Co. |  | 101.37 | S012542103.001
GL | 220 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 39.16
AP | 220 | 08/20/25 | 355 | Consolidated Supply Co. |  | 57.4 | S012559773.001
AP | 220 | 08/26/25 | 456 | Capital One Credit Card |  | 29.76 | 071425J2
AP | 220 | 08/26/25 | 506 | Consolidated Supply Co. |  | 171.8 | S012566355.001
GL | 220 | 08/28/25 | 581 | Tommy Eisenhauer |  | 15.06
GL | 220 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 139.76
GL | 220 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 190.06
GL | 220 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 54.15
AP | 220 | 09/16/25 | 173 | Rosen Supply Kirkland |  | 28.5 | 33061.01
GL | 220 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 4.47
GL | 220 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 28.77
GL | 220 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 25.5
AP | 220 | 11/21/25 | 415 | Rosen Supply Kirkland |  | 329.35 | 35094.01
AP | 220 | 12/22/25 | 462 | Capital One Credit Card |  | 57.62 | 111725J
AP | 220 | 01/12/26 | 244 | Rosen Supply Kirkland |  | 178.77 | 35714.01
GL | 220 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 6.1
GL | 220 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 164.45
AP | 220 | 02/20/26 | 381 | Pacific Plumbing Supply Co., LLC |  | 36.8 | 52092867
GL | 220 | 02/23/26 | 414 | 2026-02-15 to 02-21 |  | 41.45
GL | 220 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | -104.83
AP | 220 | 03/10/26 | 171 | Rosen Supply Kirkland |  | 124.37 | 36296.03
AP | 220 | 03/10/26 | 172 | Rosen Supply Kirkland |  | -124.37 | 36296.04
AP | 220 | 03/10/26 | 173 | Rosen Supply Kirkland |  | 109.5 | 36296.05
AP | 220 | 03/11/26 | 176 | Rosen Supply Kirkland |  | 15.54 | 36296.01
AP | 230 | 08/14/24 | 413 | Keller Supply Company |  | 184.02 | S023242307.001
GL | 230 | 08/28/24 | 830 | Transfer 2024-08-18 to 2024-08-24 |  | 321.59
GL | 230 | 09/24/24 | 497 | 2024-09-15 to 2024-09-21 |  | 115.13
AP | 230 | 10/21/24 | 520 | California Hydronics Corp |  | 4990 | SIN195612
GL | 230 | 11/05/24 | 96 | 2024-10-27 to 2024-11-02 |  | 58.2
AP | 230 | 11/05/24 | 113 | California Hydronics Corp |  | 223572 | SIN197109
AP | 230 | 11/11/24 | 230 | California Hydronics Corp |  | 31525 | SIN197327
AP | 230 | 11/18/24 | 480 | Keller Supply Company |  | 253.14 | S023544909.001
GL | 230 | 11/19/24 | 500 | 2024-11-10 to 2024-11-16 |  | 11.85
GL | 230 | 12/09/24 | 207 | 2024-12-02 to 2024-12-06 |  | 71.37
AP | 230 | 12/17/24 | 338 | Keller Supply Company |  | -179.27 | S023622280.001
GL | 230 | 12/19/24 | 498 | 2024-12-08 to 2024-12-14 |  | 1426.33
GL | 230 | 12/21/24 | 617 | 2024-12-15 to 2024-12-21 |  | 640.82
AP | 230 | 12/25/24 | 649 | California Hydronics Corp |  | 585 | SIN201196
AP | 230 | 01/02/25 | 127 | Keller Supply Company |  | 1139.18 | S023419987.001
AP | 230 | 01/08/25 | 169 | Ferguson Enterprises, Inc. #3007 |  | 17258.16 | 3032311
AP | 230 | 02/14/25 | 284 | Rosen Supply Kirkland |  | 30 | 29755.02
GL | 230 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 125.27
AP | 230 | 02/26/25 | 497 | Rosen Supply Kirkland |  | 240 | 29919.01
GL | 230 | 02/28/25 | 594 | 2025-02-23 to 2025-02-28 |  | 876.89
GL | 230 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 317.88
AP | 230 | 03/19/25 | 357 | Pacific Plumbing Supply Co., LLC |  | 1227.84 | 51803840
GL | 230 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 53.74
GL | 230 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 603.68
AP | 230 | 04/28/25 | 636 | Consolidated Supply Co. |  | 696.1 | S012377815.001
GL | 230 | 04/29/25 | 667 | 2025-04-20 to 2025-04-26 |  | 330
GL | 230 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 262.08
GL | 230 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 27.56
GL | 230 | 05/30/25 | 607 | 2025-05-19 to 2025-05-23 |  | 3.64
AP | 230 | 06/16/25 | 284 | Pacific Plumbing Supply Co., LLC |  | 1227.84 | 51882697
AP | 230 | 06/27/25 | 563 | Rosen Supply Kirkland |  | 1612.06 | 31914.02
GL | 230 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 7.71
GL | 230 | 07/14/25 | 249 | 2025-07-07 to 2025-07-11 |  | 63.18
GL | 230 | 07/21/25 | 397 | 2025-07-13 to 2025-07-19 |  | 59.23
AP | 230 | 08/06/25 | 123 | Rosen Supply Kirkland |  | 997.08 | 31098.01
AP | 230 | 08/12/25 | 240 | Rosen Supply Kirkland |  | 360 | 32712.02
GL | 230 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 679.68
GL | 230 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 289.04
GL | 230 | 09/16/25 | 170 | 2025-09-07 to 09-13 |  | 10.79
AP | 230 | 09/16/25 | 222 | Keller Supply Company |  | 612.46 | S023406800.001
AP | 230 | 09/16/25 | 223 | Keller Supply Company |  | 612.46 | S023406834.001
AP | 230 | 09/17/25 | 226 | Consolidated Supply Co. |  | 646.4 | S012119225.001
AP | 230 | 09/17/25 | 227 | Consolidated Supply Co. |  | 646.4 | S012119231.001
GL | 230 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 37.99
AP | 230 | 09/23/25 | 358 | Consolidated Supply Co. |  | 646.4 | S012119236.001
AP | 230 | 09/23/25 | 359 | Consolidated Supply Co. |  | 617.14 | S012119241.001
AP | 230 | 09/24/25 | 405 | Keller Supply Company |  | 612.46 | S023407039.001
GL | 230 | 10/06/25 | 107 | 2025-09-28 to 10-04 |  | 104.8
AP | 230 | 10/07/25 | 126 | Keller Supply Company |  | 288.52 | S023983081.001
AP | 230 | 10/07/25 | 143 | Rosen Supply Kirkland |  | 343.48 | 33514.02
AP | 230 | 10/10/25 | 251 | Keller Supply Company |  | 2966.28 | S022360358.001
AP | 230 | 10/10/25 | 252 | Keller Supply Company |  | 2966.28 | S023419371.001
AP | 230 | 10/10/25 | 253 | Keller Supply Company |  | 2966.28 | S023419671.001
AP | 230 | 10/10/25 | 256 | Consolidated Supply Co. |  | 1006.2 | S012119568.001
AP | 230 | 10/10/25 | 257 | Consolidated Supply Co. |  | 1006.2 | S012119584.001
AP | 230 | 10/10/25 | 258 | Consolidated Supply Co. |  | 1006.2 | S012119594.001
GL | 230 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 831.98
AP | 230 | 10/13/25 | 281 | California Hydronics Corp |  | 125 | SIN224990
AP | 230 | 10/14/25 | 337 | Keller Supply Company |  | 608.19 | S023407111.001
AP | 230 | 10/14/25 | 338 | Keller Supply Company |  | -56.29 | S024638128.001
AP | 230 | 10/16/25 | 426 | Rosen Supply Kirkland |  | 107.62 | 34307.01
AP | 230 | 10/17/25 | 457 | Keller Supply Company |  | -229.03 | S024641840.001
GL | 230 | 10/21/25 | 459 | 2025-10-12 to 10-18 |  | 54.13
GL | 230 | 10/31/25 | 770 | 2025-10-26 to 11-01 |  | 3.46
GL | 230 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 57.95
AP | 230 | 11/14/25 | 283 | Keller Supply Company |  | 2897.13 | S023419913.001
GL | 230 | 11/17/25 | 292 | 2025-11-09 to 11-15 |  | 180.79
AP | 230 | 11/18/25 | 315 | Consolidated Supply Co. |  | 1006.2 | S012119605.001
AP | 230 | 11/18/25 | 318 | Keller Supply Company |  | 801.61 | S024641840.002
GL | 230 | 11/24/25 | 475 | 2025-11-16 to 11-22 |  | 623.46
AP | 230 | 12/02/25 | 16 | Ferguson Enterprises, Inc. #3007 |  | 268.93 | 4191024
AP | 230 | 12/02/25 | 19 | Pacific Plumbing Supply Co., LLC |  | 178.6 | 52024720
AP | 230 | 12/04/25 | 117 | Ferguson Enterprises, Inc. #3007 |  | 269 | 4207722
GL | 230 | 12/08/25 | 126 | 2025-11-30 to 12-06 |  | 116.22
GL | 230 | 12/15/25 | 260 | 2025-12-07 to 12/13 |  | 2.24
AP | 230 | 12/15/25 | 267 | Mechanical Sales, Inc. |  | 335.78 | INV-0816353
GL | 230 | 12/22/25 | 500 | 2025-12-14 to 12-20 |  | 175.66
GL | 230 | 01/12/26 | 238 | 2026-01-04 to 01-10 |  | 157.63
AP | 230 | 01/12/26 | 245 | Ferguson Enterprises, Inc. #3007 |  | 269 | 4243048
AP | 230 | 01/15/26 | 333 | Ferguson Enterprises, Inc. #3007 |  | -269 | CM623098
GL | 230 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 226.3
GL | 230 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 61.86
AP | 230 | 02/26/26 | 516 | California Hydronics Corp |  | 26134 | SIN236502
GL | 230 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 52.35
GL | 230 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | -780.9
AP | 230 | 03/18/26 | 293 | Pacific Plumbing Supply Co., LLC |  | 95.34 | 52116198
AP | 240 | 01/22/25 | 467 | Consolidated Supply Co. |  | 101.58 | S012244858.001
AP | 240 | 01/28/25 | 659 | Pacific Plumbing Supply Co., LLC |  | 595.35 | 51765137
GL | 240 | 01/29/25 | 679 | 2025-01-19 to 2025-01-25 |  | 289.33
AP | 240 | 02/11/25 | 161 | Consolidated Supply Co. |  | 60.69 | S012274154.001
GL | 240 | 04/11/25 | 308 | 2025-04-06 to 2025-04-12 |  | 56.02
GL | 240 | 08/11/25 | 235 | 2025-08-03 to 08-09 |  | 104.77
AP | 240 | 08/19/25 | 336 | Consolidated Supply Co. |  | 197.38 | S012554176.001
GL | 240 | 09/03/25 | 4 | 2025-08-24 to 08-30 |  | 105.23
AP | 240 | 12/22/25 | 492 | Kele, Inc $ MI Controls |  | 466 | MIS0807039351
GL | 240 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 65.52
AP | 240 | 01/28/26 | 564 | Pacific Plumbing Supply Co., LLC |  | 21.51 | 52071227
GL | 241 | 08/12/24 | 372 |  |  | 82.2
GL | 241 | 08/16/24 | 557 | 2024-08-11 to 2024-08-17 |  | 468.55
AP | 241 | 10/22/24 | 563 | Consolidated Supply Co. |  | 6379.73 | S012043872.001
GL | 241 | 10/29/24 | 714 | 2024-10-20 to 2024-10-26 |  | 31.2
AP | 241 | 02/05/25 | 12 | Consolidated Supply Co. |  | 296.18 | S012279295.001
AP | 241 | 02/11/25 | 142 | Consolidated Supply Co. |  | -296.18 | S012279295.002
AP | 241 | 02/11/25 | 143 | Consolidated Supply Co. |  | 296.18 | S012279295.003
AP | 241 | 02/14/25 | 276 | Consolidated Supply Co. |  | 108.24 | S012294329.001
GL | 241 | 02/17/25 | 288 | 2025-02-09 to 2025-02-15 |  | 356.49
AP | 241 | 02/18/25 | 302 | Consolidated Supply Co. |  | 41.08 | S012296222.001
GL | 241 | 02/25/25 | 473 | 2025-02-16 to 2025-02-22 |  | 704.05
AP | 241 | 03/05/25 | 137 | Consolidated Supply Co. |  | 978.42 | S012318071.001
AP | 241 | 03/06/25 | 90 | Consolidated Supply Co. |  | 138.6 | S012314496.001
GL | 241 | 03/11/25 | 145 | 2025-03-02 to 2025-03-08 |  | 121.58
AP | 241 | 03/11/25 | 169 | Consolidated Supply Co. |  | 424.1 | S012320066.001
AP | 241 | 03/11/25 | 170 | Consolidated Supply Co. |  | 1385.8 | S012322147.001
AP | 241 | 03/17/25 | 293 | Consolidated Supply Co. |  | 2361.62 | S012329170.001
GL | 241 | 03/18/25 | 348 | 2025-03-09 to 2025-03-15 |  | 116.44
AP | 241 | 03/19/25 | 386 | Pacific Plumbing Supply Co., LLC |  | 30.19 | 51808967
AP | 241 | 03/21/25 | 490 | Consolidated Supply Co. |  | 1130.94 | S012340825.001
AP | 241 | 03/21/25 | 498 | Consolidated Supply Co. |  | 126.69 | S012340825.002
GL | 241 | 03/24/25 | 528 | 2025-03-16 to 2025-03-22 |  | 157.2
AP | 241 | 04/01/25 | 115 | Consolidated Supply Co. |  | -2361.62 | S012329170.001A
AP | 241 | 04/01/25 | 116 | Consolidated Supply Co. |  | 2361.82 | S012329170.001B
GL | 241 | 04/04/25 | 84 | 2025-03-23 to 2025-03-29 |  | 203.55
AP | 241 | 04/08/25 | 137 | MacArthur Co. NW 6276 |  | 365.4 | 252125088
AP | 241 | 04/08/25 | 138 | MacArthur Co. NW 6276 |  | 5578.32 | 252125089
AP | 241 | 05/02/25 | 92 | Consolidated Supply Co. |  | 75.2 | S012399671.001
GL | 241 | 05/05/25 | 118 | 2025-04-27 to 2025-05-03 |  | 94.2
GL | 241 | 05/12/25 | 273 | 2025-05-05 to 2025-05-09 |  | 340.13
GL | 241 | 05/19/25 | 416 | 2025-05-11 to 2025-05-17 |  | 129.6
AP | 241 | 05/22/25 | 518 | Consolidated Supply Co. |  | 353.42 | S012424389.001
AP | 241 | 05/22/25 | 519 | Consolidated Supply Co. |  | 706.84 | S012426515.001
AP | 241 | 06/16/25 | 285 | Pacific Plumbing Supply Co., LLC |  | 31.2 | 51883163
GL | 241 | 06/24/25 | 390 | 2025-06-15 to 2025-06-21 |  | 209.31
AP | 241 | 06/24/25 | 400 | Consolidated Supply Co. |  | 1033.62 | S012472855.001
AP | 241 | 06/27/25 | 545 | MacArthur Co. NW 6276 |  | 338.16 | 252183359
GL | 241 | 06/30/25 | 568 | 2025-06-22 to 2025-06-28 |  | 355.73
AP | 241 | 06/30/25 | 576 | Consolidated Supply Co. |  | 484.62 | S012473688.001
GL | 241 | 07/07/25 | 81 | 2025-06-30 to 2025-07-04 |  | 153.54
AP | 241 | 07/09/25 | 94 | Consolidated Supply Co. |  | 612.38 | S012491515.001
AP | 241 | 07/09/25 | 95 | Consolidated Supply Co. |  | 426.4 | S012493269.001
AP | 241 | 07/09/25 | 96 | Consolidated Supply Co. |  | 48.38 | S012493269.002
AP | 241 | 08/25/25 | 451 | Ferguson Enterprises, Inc. #3007 |  | 1507.15 | 3949264
AP | 241 | 09/08/25 | 80 | Consolidated Supply Co. |  | 549.4 | S012570351.001
GL | 241 | 09/12/25 | 165 | 2025-08-31 to 09-06 |  | 415.47
AP | 241 | 09/16/25 | 177 | Consolidated Supply Co. |  | 100.2 | S012570351.002
AP | 241 | 09/16/25 | 212 | Consolidated Supply Co. |  | 380.57 | S012576425.001
AP | 241 | 09/16/25 | 215 | Consolidated Supply Co. |  | 123.82 | S012580564.001
GL | 241 | 09/22/25 | 308 | 2025-09-14 to 09-20 |  | 47.15
GL | 241 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 130.99
AP | 241 | 11/12/25 | 197 | Consolidated Supply Co. |  | 144.52 | S012676717.001
GL | 241 | 12/08/25 | 126 | 2025-11-30 to 12-06 |  | 94.52
AP | 241 | 12/15/25 | 268 | Pac West Sales |  | 44 | I-2513039
AP | 241 | 12/15/25 | 288 | Consolidated Supply Co. |  | 79.99 | S012721266.001
GL | 241 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 130.51
GL | 241 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 157.51
GL | 241 | 02/28/26 | 549 | 2026-02-22 to 02-28 |  | 385.18
GL | 241 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 41.92
GL | 241 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | -258.76
AP | 241 | 03/11/26 | 177 | Consolidated Supply Co. |  | 140.34 | S012830848.001
GL | 241 | 03/16/26 | 278 | 2026-03-09 to 03-13 |  | 30.26
GL | 241 | 03/16/26 | 278 | 2026-03-09 to 03-13 |  | 93.45
GL | 241 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | 74.8
GL | 242 | 10/13/25 | 278 | 2025-10-05 to 10-11 |  | 2083.23
AP | 242 | 10/17/25 | 442 | Consolidated Supply Co. |  | 1505.15 | S012636019.001
AP | 242 | 10/17/25 | 443 | Consolidated Supply Co. |  | 795.44 | S012636814.001
AP | 242 | 10/22/25 | 471 | Consolidated Supply Co. |  | 3464.68 | S012636019.002
AP | 242 | 10/31/25 | 764 | Consolidated Supply Co. |  | 877.1 | S012636814.002
AP | 242 | 11/05/25 | 32 | Pacific Plumbing Supply Co., LLC |  | 7778.61 | 52000776
AP | 242 | 11/05/25 | 37 | Pacific Plumbing Supply Co., LLC |  | 52.44 | 52000778
AP | 242 | 11/05/25 | 38 | Pacific Plumbing Supply Co., LLC |  | 405 | 52000779
GL | 242 | 11/10/25 | 170 | 2025-11-02 to 11-08 |  | 256.2
AP | 242 | 11/10/25 | 173 | Pacific Plumbing Supply Co., LLC |  | 222.98 | 52006600
AP | 242 | 11/24/25 | 480 | Ferguson Enterprises, Inc. #3007 |  | 905.25 | 4191626
GL | 242 | 11/30/25 | 586 | 2025-11-23 to 11-29 |  | 66.34
AP | 242 | 12/02/25 | 18 | Pacific Plumbing Supply Co., LLC |  | 3008.98 | 52024718
GL | 242 | 12/08/25 | 126 | 2025-11-30 to 12-06 |  | 426.43
GL | 242 | 12/15/25 | 260 | 2025-12-07 to 12/13 |  | 48.88
AP | 242 | 12/15/25 | 273 | Pacific Plumbing Supply Co., LLC |  | 831.11 | 52035909
GL | 242 | 01/12/26 | 238 | 2026-01-04 to 01-10 |  | 42.82
GL | 242 | 01/26/26 | 552 | 2026-01-18 to 01-24 |  | 133.41
AP | 242 | 01/28/26 | 565 | Pacific Plumbing Supply Co., LLC |  | 624.26 | 52071229
GL | 242 | 02/16/26 | 251 | 2026-02-09 to 02-13 |  | 123.52
GL | 242 | 02/23/26 | 414 | 2026-02-15 to 02-21 |  | 7.49
AP | 242 | 03/04/26 | 34 | Pacific Plumbing Supply Co., LLC |  | 3866.27 | 52103667
AP | 242 | 03/06/26 | 116 | Pacific Plumbing Supply Co., LLC |  | 179.72 | 52105634
GL | 242 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | 163.65
GL | 242 | 03/09/26 | 144 | 2026-03-02 - 03-07 |  | -10.59
AP | 242 | 03/13/26 | 260 | Pacific Plumbing Supply Co., LLC |  | 317.87 | 52111703
AP | 242 | 03/16/26 | 275 | Pacific Plumbing Supply Co., LLC |  | 189.63 | 52114693
GL | 242 | 03/16/26 | 278 | 2026-03-09 to 03-13 |  | 54.54
GL | 242 | 03/23/26 | 414 | 2026-03-15 to 03-21 |  | 9.12
AP | 242 | 03/26/26 | 546 | Capital One Credit Card |  | 39.48 | 030226J4
AP | 242 | 03/26/26 | 550 | Capital One Credit Card |  | 46.24 | 030426J1
AP | 242 | 03/26/26 | 555 | Capital One Credit Card |  | 7.11 | 030526J
AP | 603 | 06/30/24 | 847 | Bank of America CC |  | 2045 | 053024J
AP | 603 | 02/12/25 | 181 | Bank of America CC |  | 13677 | 012025B
AP | 603 | 03/18/25 | 322 | Bank of America CC |  | 210 | 022425J1
AP | 603 | 03/18/25 | 323 | Bank of America CC |  | 184 | 022425J2
AP | 603 | 10/24/25 | 598 | Bank of America CC |  | 66 | 091725J
AP | 607 | 08/20/24 | 602 | Bank of America CC |  | 488.96 | 071924R
GL | 607 | 08/22/24 | 771 | Richard Anderson |  | 10.88
AP | 607 | 09/30/24 | 625 | Bank of America CC |  | 478.96 | 081624R5
AP | 607 | 09/30/24 | 634 | Bank of America CC |  | 5.89 | 090324J
AP | 607 | 10/15/24 | 362 | Bank of America CC |  | 478.96 | 091624R5
AP | 607 | 10/15/24 | 370 | Bank of America CC |  | 5.89 | 091124J1
AP | 607 | 10/15/24 | 377 | Bank of America CC |  | 5.89 | 092624J1
AP | 607 | 10/15/24 | 383 | Bank of America CC |  | 5.99 | 100324J
AP | 607 | 10/15/24 | 385 | Bank of America CC |  | 5.99 | 100924J
AP | 607 | 11/30/24 | 749 | Bank of America CC |  | 478.96 | 101624R3
AP | 607 | 11/30/24 | 755 | Bank of America CC |  | 5.99 | 102224J
AP | 607 | 11/30/24 | 757 | Bank of America CC |  | 25.97 | 102424J
AP | 607 | 11/30/24 | 760 | Bank of America CC |  | 5.99 | 103024J
AP | 607 | 11/30/24 | 765 | Bank of America CC |  | 5.99 | 110724J
AP | 607 | 12/25/24 | 619 | Capital One Credit Card |  | 19.98 | 120424J
AP | 607 | 12/25/24 | 640 | Bank of America CC |  | 478.96 | 111524R3
AP | 607 | 12/30/24 | 652 | Bank of America CC |  | 5.99 | 111324J
AP | 607 | 12/30/24 | 658 | Bank of America CC |  | 5.99 | 120224J1
AP | 607 | 01/24/25 | 588 | Bank of America CC |  | 478.96 | 121624R2
AP | 607 | 01/24/25 | 591 | Bank of America CC |  | 11.98 | 121224J
AP | 607 | 01/24/25 | 593 | Bank of America CC |  | 3.5 | 121624J
AP | 607 | 02/12/25 | 167 | Bank of America CC |  | 478.96 | 011525R2
AP | 607 | 02/12/25 | 171 | Bank of America CC |  | 17.56 | 020625J
AP | 607 | 03/18/25 | 313 | Bank of America CC |  | 478.96 | 021625R1
AP | 607 | 03/18/25 | 320 | Bank of America CC |  | 10.94 | 021825J
AP | 607 | 04/16/25 | 338 | Bank of America CC |  | 478.96 | 031625R2
AP | 607 | 04/16/25 | 345 | Bank of America CC |  | 7.24 | 031325J
AP | 607 | 04/16/25 | 349 | Bank of America CC |  | 7.44 | 032725J2
AP | 607 | 04/16/25 | 352 | Bank of America CC |  | 3 | 040825J
AP | 607 | 05/27/25 | 304 | Bank of America CC |  | 478.96 | 041625R2
AP | 607 | 05/27/25 | 312 | Bank of America CC |  | 3 | 042225J
AP | 607 | 06/25/25 | 433 | Bank of America CC |  | 478.96 | 051625R2
AP | 607 | 06/25/25 | 437 | Bank of America CC |  | 3 | 051525J
AP | 607 | 06/25/25 | 439 | Bank of America CC |  | 8.69 | 052725J
AP | 607 | 07/22/25 | 399 | Bank of America CC |  | 478.96 | 061625R2
AP | 607 | 08/26/25 | 472 | Bank of America CC |  | 478.96 | 071625R2
AP | 607 | 09/23/25 | 333 | Bank of America CC |  | 578.84 | 081625R2
AP | 607 | 09/23/25 | 342 | Bank of America CC |  | 5.49 | 082125J
AP | 607 | 10/24/25 | 586 | Bank of America CC |  | 578.84 | 091625R2
AP | 607 | 10/24/25 | 593 | Bank of America CC |  | 250.72 | 100125R
AP | 607 | 10/24/25 | 594 | Bank of America CC |  | 294.42 | 100325R
AP | 607 | 10/29/25 | 657 | Bank of America CC |  | 7.99 | 100125J
AP | 607 | 11/24/25 | 439 | Bank of America CC |  | 578.84 | 101625R1
AP | 607 | 11/24/25 | 445 | Bank of America CC |  | 289.42 | 101625R7
AP | 607 | 12/22/25 | 471 | Bank of America CC |  | 578.84 | 111625R1
AP | 607 | 01/20/26 | 379 | Bank of America CC |  | 579.74 | 121625R
AP | 607 | 02/23/26 | 388 | Bank of America CC |  | -289.87 | 012026R
AP | 607 | 02/23/26 | 390 | Bank of America CC |  | 579.74 | 011626R1
PR | 995 | 06/07/24 | 139 | Johnson, Jake E |  | 86.63
PR | 995 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 06/14/24 | 362 | Johnson, Jake E |  | 21.66
PR | 995 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 06/21/24 | 533 | Johnson, Jake E |  | 108.29
PR | 995 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 06/28/24 | 740 | Johnson, Jake E |  | 86.63
PR | 995 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 143.69
PR | 995 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 07/05/24 | 53 | Johnson, Jake E |  | 43.32
PR | 995 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 07/12/24 | 216 | Johnson, Jake E |  | 43.32
PR | 995 | 07/19/24 | 390 | Barnhart, Joseph N |  | 84.97
PR | 995 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 186.8
PR | 995 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 07/19/24 | 422 | Johnson, Jake E |  | 86.63
PR | 995 | 07/26/24 | 595 | Eisenhauer, Tommy J |  | 94.96
PR | 995 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 172.43
PR | 995 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 158.06
PR | 995 | 07/26/24 | 609 | Johnson, Jake E |  | 21.66
PR | 995 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/09/24 | 237 | Anderson, Richard P |  | 379.02
PR | 995 | 08/09/24 | 256 | Boss, Benjamin T |  | 169.93
PR | 995 | 08/09/24 | 270 | Eisenhauer, Tommy J |  | 569.77
PR | 995 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 86.22
PR | 995 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 08/09/24 | 283 | Johnson, Jake E |  | 21.66
PR | 995 | 08/09/24 | 303 | Silva Morales, Jair J |  | 113.29
PR | 995 | 08/09/24 | 312 | Yohannes Jr., Samson |  | 109.96
PR | 995 | 08/16/24 | 428 | Anderson, Richard P |  | 162.44
PR | 995 | 08/16/24 | 428 | Anderson, Richard P |  | 148.9
PR | 995 | 08/16/24 | 447 | Boss, Benjamin T |  | 509.8
PR | 995 | 08/16/24 | 459 | Eisenhauer, Tommy J |  | 712.22
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 08/16/24 | 472 | Johnson, Jake E |  | 43.32
PR | 995 | 08/23/24 | 721 | Eisenhauer, Tommy J |  | 451.07
PR | 995 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/23/24 | 734 | Johnson, Jake E |  | 194.92
PR | 995 | 08/30/24 | 852 | Boss, Benjamin T |  | 84.97
PR | 995 | 08/30/24 | 863 | Eisenhauer, Tommy J |  | 189.92
PR | 995 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 08/30/24 | 876 | Johnson, Jake E |  | 21.66
PR | 995 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 09/06/24 | 53 | Johnson, Jake E |  | 64.97
PR | 995 | 09/13/24 | 217 | Anderson, Richard P |  | 135.36
PR | 995 | 09/13/24 | 222 | Del Villar, Flabio |  | 83.3
PR | 995 | 09/13/24 | 233 | Barnhart, Joseph N |  | 84.97
PR | 995 | 09/13/24 | 247 | Eisenhauer, Tommy J |  | 332.37
PR | 995 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 114.95
PR | 995 | 09/13/24 | 261 | Johnson, Jake E |  | 86.63
PR | 995 | 09/20/24 | 389 | Anderson, Richard P |  | 135.36
PR | 995 | 09/20/24 | 419 | Eisenhauer, Tommy J |  | 237.41
PR | 995 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 09/20/24 | 432 | Johnson, Jake E |  | 43.32
PR | 995 | 09/27/24 | 542 | Barnhart, Joseph N |  | 84.97
PR | 995 | 09/27/24 | 555 | Eisenhauer, Tommy J |  | 379.85
PR | 995 | 09/27/24 | 555 | Eisenhauer, Tommy J |  | 189.92
PR | 995 | 09/27/24 | 568 | Johnson, Jake E |  | 64.97
PR | 995 | 10/04/24 | 39 | Eisenhauer, Tommy J |  | 189.92
PR | 995 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/04/24 | 52 | Johnson, Jake E |  | 86.63
PR | 995 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 10/11/24 | 259 | Johnson, Jake E |  | 21.66
PR | 995 | 10/18/24 | 429 | Anderson, Richard P |  | 40.61
PR | 995 | 10/18/24 | 459 | Eisenhauer, Tommy J |  | 284.89
PR | 995 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 10/18/24 | 471 | Johnson, Jake E |  | 21.66
PR | 995 | 10/25/24 | 606 | Eisenhauer, Tommy J |  | 664.73
PR | 995 | 10/25/24 | 606 | Eisenhauer, Tommy J |  | 284.89
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 10/25/24 | 613 | Gomez Aguirre, Exequiel |  | 279.89
PR | 995 | 10/25/24 | 613 | Gomez Aguirre, Exequiel |  | 119.95
PR | 995 | 11/01/24 | 6 | Anderson, Richard P |  | 27.07
PR | 995 | 11/01/24 | 35 | Eisenhauer, Tommy J |  | 569.77
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/01/24 | 42 | Gomez Aguirre, Exequiel |  | 239.9
PR | 995 | 11/01/24 | 47 | Johnson, Jake E |  | 21.66
PR | 995 | 11/08/24 | 155 | Eisenhauer, Tommy J |  | 949.62
PR | 995 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/08/24 | 162 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 11/08/24 | 167 | Johnson, Jake E |  | 43.32
PR | 995 | 11/15/24 | 346 | Anderson, Richard P |  | 27.07
PR | 995 | 11/15/24 | 363 | Barnhart, Joseph N |  | 113.29
PR | 995 | 11/15/24 | 375 | Eisenhauer, Tommy J |  | 759.7
PR | 995 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 11/15/24 | 382 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 11/15/24 | 387 | Johnson, Jake E |  | 21.66
PR | 995 | 11/15/24 | 448 | Barnhart, Joseph N |  | -113.29
PR | 995 | 11/22/24 | 530 | Eisenhauer, Tommy J |  | 759.7
PR | 995 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 11/22/24 | 537 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 11/29/24 | 678 | Eisenhauer, Tommy J |  | 664.73
PR | 995 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 71.85
PR | 995 | 11/29/24 | 685 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 12/06/24 | 80 | Eisenhauer, Tommy J |  | 284.89
PR | 995 | 12/06/24 | 87 | Gomez Aguirre, Exequiel |  | 239.9
PR | 995 | 12/06/24 | 96 | Martinez Reyes, Juan C |  | 146.61
PR | 995 | 12/13/24 | 250 | Barnhart, Joseph N |  | 84.97
PR | 995 | 12/13/24 | 262 | Eisenhauer, Tommy J |  | 569.77
PR | 995 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/13/24 | 269 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 12/13/24 | 278 | Martinez Reyes, Juan C |  | 586.43
PR | 995 | 12/20/24 | 437 | Barnhart, Joseph N |  | 113.29
PR | 995 | 12/20/24 | 448 | Eisenhauer, Tommy J |  | 759.7
PR | 995 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/20/24 | 455 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 12/20/24 | 460 | Johnson, Jake E |  | 43.32
PR | 995 | 12/20/24 | 464 | Martinez Reyes, Juan C |  | 733.04
PR | 995 | 12/27/24 | 544 | Del Villar, Flabio |  | 72.89
PR | 995 | 12/27/24 | 558 | Calderon M, Roberto H |  | 64.14
PR | 995 | 12/27/24 | 564 | Cruz, Azael S |  | 93.3
PR | 995 | 12/27/24 | 567 | Eisenhauer, Tommy J |  | 379.85
PR | 995 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 12/27/24 | 574 | Gomez Aguirre, Exequiel |  | 229.91
PR | 995 | 12/27/24 | 578 | Jimenez Alvarenga, Gerson M |  | 113.7
PR | 995 | 12/27/24 | 583 | Martinez Reyes, Juan C |  | 293.22
PR | 995 | 12/27/24 | 585 | Melgar Moz, Brandon |  | 73.3
PR | 995 | 01/03/25 | 12 | Anderson, Richard P |  | 27.07
PR | 995 | 01/03/25 | 38 | Eisenhauer, Tommy J |  | 189.92
PR | 995 | 01/03/25 | 44 | Gomez Aguirre, Exequiel |  | 159.94
PR | 995 | 01/03/25 | 53 | Martinez Reyes, Juan C |  | 293.22
PR | 995 | 01/10/25 | 201 | Eisenhauer, Tommy J |  | 569.77
PR | 995 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 28.74
PR | 995 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 57.48
PR | 995 | 01/10/25 | 207 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 01/10/25 | 216 | Martinez Reyes, Juan C |  | 293.22
PR | 995 | 01/17/25 | 364 | Eisenhauer, Tommy J |  | 474.81
PR | 995 | 01/17/25 | 370 | Gomez Aguirre, Exequiel |  | 399.84
PR | 995 | 01/17/25 | 379 | Martinez Reyes, Juan C |  | 549.78
PR | 995 | 01/24/25 | 531 | Eisenhauer, Tommy J |  | 759.7
PR | 995 | 01/24/25 | 531 | Eisenhauer, Tommy J |  | 94.96
PR | 995 | 01/24/25 | 537 | Gomez Aguirre, Exequiel |  | 319.87
PR | 995 | 01/24/25 | 546 | Martinez Reyes, Juan C |  | 513.13
PR | 995 | 01/24/25 | 546 | Martinez Reyes, Juan C |  | 73.3
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/31/25 | 712 | Barnhart, Joseph N |  | 56.64
PR | 995 | 01/31/25 | 723 | Eisenhauer, Tommy J |  | 830.92
PR | 995 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 43.11
PR | 995 | 01/31/25 | 729 | Gomez Aguirre, Exequiel |  | 159.94
PR | 995 | 01/31/25 | 729 | Gomez Aguirre, Exequiel |  | 239.9
PR | 995 | 01/31/25 | 738 | Martinez Reyes, Juan C |  | 73.3
PR | 995 | 01/31/25 | 738 | Martinez Reyes, Juan C |  | 623.08
PR | 995 | 02/07/25 | 42 | Barnhart, Joseph N |  | 28.32
PR | 995 | 02/07/25 | 53 | Eisenhauer, Tommy J |  | 142.44
PR | 995 | 02/07/25 | 53 | Eisenhauer, Tommy J |  | 189.92
PR | 995 | 02/07/25 | 59 | Gomez Aguirre, Exequiel |  | 109.96
PR | 995 | 02/07/25 | 59 | Gomez Aguirre, Exequiel |  | 79.97
PR | 995 | 02/07/25 | 68 | Martinez Reyes, Juan C |  | 494.8
PR | 995 | 02/14/25 | 208 | Barnhart, Joseph N |  | 100.57
PR | 995 | 02/14/25 | 219 | Eisenhauer, Tommy J |  | 1067.84
PR | 995 | 02/14/25 | 225 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 02/14/25 | 230 | Johnson, Jake E |  | 21.66
PR | 995 | 02/14/25 | 234 | Martinez Reyes, Juan C |  | 520.61
PR | 995 | 02/14/25 | 234 | Martinez Reyes, Juan C |  | 347.07
PR | 995 | 02/21/25 | 337 | Eisenhauer, Tommy J |  | 1124.04
PR | 995 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 51.03
PR | 995 | 02/21/25 | 343 | Gomez Aguirre, Exequiel |  | 283.97
PR | 995 | 02/21/25 | 343 | Gomez Aguirre, Exequiel |  | 189.31
PR | 995 | 02/21/25 | 352 | Martinez Reyes, Juan C |  | 867.68
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 50.29
PR | 995 | 02/28/25 | 516 | Barnhart, Joseph N |  | 16.76
PR | 995 | 02/28/25 | 527 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 02/28/25 | 533 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 02/28/25 | 542 | Martinez Reyes, Juan C |  | 520.61
PR | 995 | 03/07/25 | 29 | Barnhart, Joseph N |  | 33.52
PR | 995 | 03/07/25 | 40 | Eisenhauer, Tommy J |  | 449.62
PR | 995 | 03/07/25 | 40 | Eisenhauer, Tommy J |  | 449.62
PR | 995 | 03/07/25 | 46 | Gomez Aguirre, Exequiel |  | 283.97
PR | 995 | 03/07/25 | 46 | Gomez Aguirre, Exequiel |  | 94.66
PR | 995 | 03/07/25 | 51 | Johnson, Jake E |  | 21.66
PR | 995 | 03/14/25 | 240 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 03/14/25 | 240 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 03/14/25 | 246 | Gomez Aguirre, Exequiel |  | 378.62
PR | 995 | 03/14/25 | 246 | Gomez Aguirre, Exequiel |  | 94.66
PR | 995 | 03/14/25 | 251 | Johnson, Jake E |  | 43.32
PR | 995 | 03/21/25 | 433 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 03/21/25 | 433 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 03/21/25 | 439 | Gomez Aguirre, Exequiel |  | 378.62
PR | 995 | 03/21/25 | 439 | Gomez Aguirre, Exequiel |  | 94.66
PR | 995 | 03/28/25 | 588 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 03/28/25 | 595 | Gomez Aguirre, Exequiel |  | 94.66
PR | 995 | 03/28/25 | 595 | Gomez Aguirre, Exequiel |  | 378.62
PR | 995 | 04/04/25 | 31 | Eisenhauer, Tommy J |  | 1124.04
PR | 995 | 04/04/25 | 38 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 04/04/25 | 43 | Johnson, Jake E |  | 43.32
PR | 995 | 04/11/25 | 211 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 04/11/25 | 218 | Gomez Aguirre, Exequiel |  | 378.62
PR | 995 | 04/11/25 | 227 | Martinez Reyes, Juan C |  | 86.77
PR | 995 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 843.03
PR | 995 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 56.2
PR | 995 | 04/18/25 | 442 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 04/18/25 | 451 | Martinez Reyes, Juan C |  | 173.54
PR | 995 | 04/25/25 | 548 | Anderson, Richard P |  | 128.18
PR | 995 | 04/25/25 | 574 | Eisenhauer, Tommy J |  | 618.22
PR | 995 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 04/25/25 | 581 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 04/25/25 | 590 | Martinez Reyes, Juan C |  | 347.07
PR | 995 | 05/02/25 | 17 | Barnhart, Joseph N |  | 16.76
PR | 995 | 05/02/25 | 28 | Eisenhauer, Tommy J |  | 1124.04
PR | 995 | 05/02/25 | 35 | Gomez Aguirre, Exequiel |  | 94.66
PR | 995 | 05/02/25 | 35 | Gomez Aguirre, Exequiel |  | 283.97
PR | 995 | 05/09/25 | 162 | Barnhart, Joseph N |  | 167.62
PR | 995 | 05/09/25 | 172 | Eisenhauer, Tommy J |  | 674.42
PR | 995 | 05/09/25 | 172 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 68.03
PR | 995 | 05/09/25 | 178 | Gomez Aguirre, Exequiel |  | 378.62
PR | 995 | 05/16/25 | 371 | Eisenhauer, Tommy J |  | 786.83
PR | 995 | 05/16/25 | 377 | Gomez Aguirre, Exequiel |  | 473.28
PR | 995 | 05/23/25 | 457 | Barnhart, Joseph N |  | 16.76
PR | 995 | 05/23/25 | 467 | Eisenhauer, Tommy J |  | 674.42
PR | 995 | 05/23/25 | 467 | Eisenhauer, Tommy J |  | 449.62
PR | 995 | 05/23/25 | 473 | Gomez Aguirre, Exequiel |  | 283.97
PR | 995 | 05/23/25 | 473 | Gomez Aguirre, Exequiel |  | 189.31
PR | 995 | 05/30/25 | 555 | Eisenhauer, Tommy J |  | 562.02
PR | 995 | 05/30/25 | 562 | Gomez Aguirre, Exequiel |  | 283.97
PR | 995 | 06/06/25 | 33 | Barnhart, Joseph N |  | 67.05
PR | 995 | 06/06/25 | 43 | Eisenhauer, Tommy J |  | 674.42
PR | 995 | 06/06/25 | 50 | Gomez Aguirre, Exequiel |  | 512.72
PR | 995 | 06/13/25 | 204 | Eisenhauer, Tommy J |  | 1095.94
PR | 995 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 06/13/25 | 208 | Gerard, Jordan E |  | 59.16
PR | 995 | 06/13/25 | 211 | Gomez Aguirre, Exequiel |  | 499.9
PR | 995 | 06/20/25 | 331 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 06/20/25 | 338 | Gomez Aguirre, Exequiel |  | 410.18
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 67.05
PR | 995 | 06/27/25 | 476 | Barnhart, Joseph N |  | 33.52
PR | 995 | 06/27/25 | 486 | Eisenhauer, Tommy J |  | 140.51
PR | 995 | 06/27/25 | 486 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 06/27/25 | 493 | Gomez Aguirre, Exequiel |  | 166.63
PR | 995 | 07/03/25 | 29 | Eisenhauer, Tommy J |  | 1124.04
PR | 995 | 07/03/25 | 36 | Gomez Aguirre, Exequiel |  | 512.72
PR | 995 | 07/11/25 | 154 | Eisenhauer, Tommy J |  | 505.82
PR | 995 | 07/11/25 | 160 | Gomez Aguirre, Exequiel |  | 282
PR | 995 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 07/18/25 | 327 | Gomez Aguirre, Exequiel |  | 102.54
PR | 995 | 07/25/25 | 479 | Barnhart, Joseph N |  | 67.05
PR | 995 | 07/25/25 | 489 | Eisenhauer, Tommy J |  | 112.4
PR | 995 | 07/25/25 | 493 | Gerard, Jordan E |  | 88.74
PR | 995 | 07/25/25 | 495 | Gomez Aguirre, Exequiel |  | 51.27
PR | 995 | 08/01/25 | 12 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/01/25 | 22 | Eisenhauer, Tommy J |  | 1124.04
PR | 995 | 08/01/25 | 26 | Gerard, Jordan E |  | 59.16
PR | 995 | 08/01/25 | 28 | Gomez Aguirre, Exequiel |  | 461.45
PR | 995 | 08/08/25 | 153 | Eisenhauer, Tommy J |  | 899.23
PR | 995 | 08/08/25 | 159 | Gomez Aguirre, Exequiel |  | 410.18
PR | 995 | 08/15/25 | 278 | Eisenhauer, Tommy J |  | 983.54
PR | 995 | 08/15/25 | 284 | Gomez Aguirre, Exequiel |  | 461.45
PR | 995 | 08/22/25 | 382 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 08/22/25 | 382 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 08/22/25 | 386 | Gerard, Jordan E |  | 29.58
PR | 995 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 307.63
PR | 995 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 102.54
PR | 995 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 102.54
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 67.05
PR | 995 | 08/29/25 | 534 | Barnhart, Joseph N |  | 33.52
PR | 995 | 08/29/25 | 545 | Eisenhauer, Tommy J |  | 1039.74
PR | 995 | 08/29/25 | 547 | Games, Jordan M |  | 104.52
PR | 995 | 08/29/25 | 551 | Gomez Aguirre, Exequiel |  | 512.72
PR | 995 | 09/05/25 | 30 | Eisenhauer, Tommy J |  | 843.03
PR | 995 | 09/05/25 | 34 | Gerard, Jordan E |  | 29.58
PR | 995 | 09/05/25 | 36 | Gomez Aguirre, Exequiel |  | 384.54
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 33.52
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 33.52
PR | 995 | 09/12/25 | 116 | Barnhart, Joseph N |  | 33.52
PR | 995 | 09/12/25 | 127 | Eisenhauer, Tommy J |  | 674.42
PR | 995 | 09/12/25 | 131 | Gerard, Jordan E |  | 29.58
PR | 995 | 09/12/25 | 133 | Gomez Aguirre, Exequiel |  | 410.18
PR | 995 | 09/19/25 | 259 | Eisenhauer, Tommy J |  | 505.82
PR | 995 | 09/19/25 | 261 | Games, Jordan M |  | 104.52
PR | 995 | 09/19/25 | 263 | Gerard, Jordan E |  | 29.58
PR | 995 | 09/19/25 | 265 | Gomez Aguirre, Exequiel |  | 166.63
PR | 995 | 09/26/25 | 430 | Eisenhauer, Tommy J |  | 42.15
PR | 995 | 09/26/25 | 436 | Gomez Aguirre, Exequiel |  | 3.2
PR | 995 | 10/03/25 | 26 | Eisenhauer, Tommy J |  | 196.71
PR | 995 | 10/03/25 | 26 | Eisenhauer, Tommy J |  | 77.28
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 32.66
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 228.63
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 124.11
PR | 995 | 10/03/25 | 29 | Games, Jordan M |  | 117.58
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 10/03/25 | 31 | Gerard, Jordan E |  | 29.58
PR | 995 | 10/03/25 | 33 | Gomez Aguirre, Exequiel |  | 99.34
PR | 995 | 10/03/25 | 56 | Suniga Aviles, Kelvin A |  | 94.66
PR | 995 | 10/03/25 | 62 | Zuniga Avilez, Eduar A |  | 94.66
PR | 995 | 10/10/25 | 164 | Araque, Mario W |  | 94.66
PR | 995 | 10/10/25 | 164 | Araque, Mario W |  | 94.66
PR | 995 | 10/10/25 | 164 | Araque, Mario W |  | 94.66
PR | 995 | 10/10/25 | 164 | Araque, Mario W |  | 94.66
PR | 995 | 10/10/25 | 164 | Araque, Mario W |  | 94.66
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 58.67
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 167.62
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 50.29
PR | 995 | 10/10/25 | 167 | Barnhart, Joseph N |  | 83.81
PR | 995 | 10/10/25 | 178 | Eisenhauer, Tommy J |  | 161.58
PR | 995 | 10/10/25 | 178 | Eisenhauer, Tommy J |  | 133.48
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 209.03
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 104.52
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 209.03
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 117.58
PR | 995 | 10/10/25 | 181 | Games, Jordan M |  | 71.85
PR | 995 | 10/10/25 | 183 | Gerard, Jordan E |  | 59.16
PR | 995 | 10/10/25 | 183 | Gerard, Jordan E |  | 59.16
PR | 995 | 10/10/25 | 186 | Gomez Aguirre, Exequiel |  | 102.54
PR | 995 | 10/17/25 | 369 | Araque, Mario W |  | 94.66
PR | 995 | 10/17/25 | 369 | Araque, Mario W |  | 88.74
PR | 995 | 10/17/25 | 369 | Araque, Mario W |  | 100.57
PR | 995 | 10/17/25 | 369 | Araque, Mario W |  | 50.29
PR | 995 | 10/17/25 | 372 | Barnhart, Joseph N |  | 8.38
PR | 995 | 10/17/25 | 386 | Games, Jordan M |  | 209.03
PR | 995 | 10/17/25 | 386 | Games, Jordan M |  | 150.24
PR | 995 | 10/17/25 | 386 | Games, Jordan M |  | 209.03
PR | 995 | 10/17/25 | 386 | Games, Jordan M |  | 117.58
PR | 995 | 10/24/25 | 517 | Eisenhauer, Tommy J |  | 84.3
PR | 995 | 10/31/25 | 683 | Eisenhauer, Tommy J |  | 7.03
PR | 995 | 10/31/25 | 683 | Eisenhauer, Tommy J |  | 105.38
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 52.26
PR | 995 | 10/31/25 | 686 | Games, Jordan M |  | 209.03
PR | 995 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 51.03
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 58.67
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 41.91
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 67.05
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 67.05
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 50.29
PR | 995 | 11/07/25 | 59 | Barnhart, Joseph N |  | 25.14
PR | 995 | 11/07/25 | 72 | Eisenhauer, Tommy J |  | 28.1
PR | 995 | 11/07/25 | 72 | Eisenhauer, Tommy J |  | 140.51
PR | 995 | 11/07/25 | 76 | Gerard, Jordan E |  | 59.16
PR | 995 | 11/07/25 | 79 | Gomez Aguirre, Exequiel |  | 9.61
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 25.14
PR | 995 | 11/14/25 | 219 | Barnhart, Joseph N |  | 83.81
PR | 995 | 11/14/25 | 232 | Eisenhauer, Tommy J |  | 224.81
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 34.02
PR | 995 | 11/14/25 | 239 | Gomez Aguirre, Exequiel |  | 96.14
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 265.91
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 88.64
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 185.33
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 177.28
PR | 995 | 11/21/25 | 336 | Barnhart, Joseph N |  | 257.86
PR | 995 | 11/21/25 | 349 | Eisenhauer, Tommy J |  | 209.39
PR | 995 | 11/21/25 | 349 | Eisenhauer, Tommy J |  | 101.32
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 56.88
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 35.55
PR | 995 | 11/21/25 | 353 | Gerard, Jordan E |  | 42.66
PR | 995 | 11/21/25 | 356 | Gomez Aguirre, Exequiel |  | 98.59
PR | 995 | 11/21/25 | 356 | Gomez Aguirre, Exequiel |  | 33.89
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 40.29
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 72.52
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 88.64
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 72.52
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 88.64
PR | 995 | 11/28/25 | 519 | Barnhart, Joseph N |  | 257.86
PR | 995 | 11/28/25 | 532 | Eisenhauer, Tommy J |  | 216.14
PR | 995 | 11/28/25 | 540 | Gomez Aguirre, Exequiel |  | 98.59
PR | 995 | 12/05/25 | 45 | Barnhart, Joseph N |  | 273.97
PR | 995 | 12/05/25 | 45 | Barnhart, Joseph N |  | 80.58
PR | 995 | 12/05/25 | 45 | Barnhart, Joseph N |  | 32.23
PR | 995 | 12/05/25 | 58 | Eisenhauer, Tommy J |  | 216.14
PR | 995 | 12/05/25 | 66 | Gomez Aguirre, Exequiel |  | 9.24
PR | 995 | 12/05/25 | 66 | Gomez Aguirre, Exequiel |  | 27.73
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 128.93
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 136.99
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 32.23
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 104.75
PR | 995 | 12/12/25 | 182 | Barnhart, Joseph N |  | 16.12
PR | 995 | 12/12/25 | 195 | Eisenhauer, Tommy J |  | 216.14
PR | 995 | 12/12/25 | 195 | Eisenhauer, Tommy J |  | 216.14
PR | 995 | 12/12/25 | 203 | Gomez Aguirre, Exequiel |  | 9.24
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 257.86
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 96.7
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 64.46
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 56.41
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 32.23
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 64.46
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 64.46
PR | 995 | 12/19/25 | 323 | Barnhart, Joseph N |  | 8.06
PR | 995 | 12/19/25 | 336 | Eisenhauer, Tommy J |  | 229.65
PR | 995 | 12/19/25 | 336 | Eisenhauer, Tommy J |  | 54.04
PR | 995 | 12/19/25 | 341 | Gerard, Jordan E |  | 21.33
PR | 995 | 12/19/25 | 341 | Gerard, Jordan E |  | 42.66
PR | 995 | 12/19/25 | 344 | Gomez Aguirre, Exequiel |  | 98.59
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 64.46
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 185.33
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 72.52
PR | 995 | 12/26/25 | 511 | Barnhart, Joseph N |  | 104.75
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 58.07
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 74.66
PR | 995 | 01/09/26 | 130 | Barnhart, Joseph N |  | 66.36
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 107.84
PR | 995 | 01/16/26 | 276 | Barnhart, Joseph N |  | 74.66
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/16/26 | 294 | Gerard, Jordan E |  | 69.92
PR | 995 | 01/23/26 | 467 | Barnhart, Joseph N |  | 99.54
PR | 995 | 01/23/26 | 487 | Gomez Aguirre, Exequiel |  | 39.82
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 74.66
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 16.59
PR | 995 | 01/30/26 | 580 | Barnhart, Joseph N |  | 82.95
PR | 995 | 01/30/26 | 600 | Gomez Aguirre, Exequiel |  | 39.82
PR | 995 | 01/30/26 | 600 | Gomez Aguirre, Exequiel |  | 36.5
PR | 995 | 02/06/26 | 56 | Barnhart, Joseph N |  | 82.95
PR | 995 | 02/06/26 | 56 | Barnhart, Joseph N |  | 24.89
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 257.15
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 141.02
PR | 995 | 02/13/26 | 188 | Barnhart, Joseph N |  | 66.36
PR | 995 | 02/13/26 | 207 | Gomez Aguirre, Exequiel |  | 13.27
PR | 995 | 02/13/26 | 214 | Mackey, Cole J |  | 197.18
PR | 995 | 02/13/26 | 214 | Mackey, Cole J |  | 197.18
PR | 995 | 02/13/26 | 214 | Mackey, Cole J |  | 184.86
PR | 995 | 02/13/26 | 214 | Mackey, Cole J |  | 197.18
PR | 995 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 36.97
PR | 995 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 51.19
PR | 995 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 85.32
PR | 995 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 91.01
PR | 995 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 91.01
PR | 995 | 02/13/26 | 229 | Suniga Aviles, Kelvin A |  | 95.51
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 107.84
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 24.89
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 33.18
PR | 995 | 02/20/26 | 304 | Barnhart, Joseph N |  | 33.18
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 55.93
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 197.18
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 117.08
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 172.54
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 24.65
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 197.18
PR | 995 | 02/20/26 | 330 | Mackey, Cole J |  | 197.18
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 16.59
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 33.18
PR | 995 | 02/27/26 | 452 | Barnhart, Joseph N |  | 223.97
PR | 995 | 02/27/26 | 478 | Mackey, Cole J |  | 73.94
PR | 995 | 02/27/26 | 478 | Mackey, Cole J |  | 123.24
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 66.36
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 82.95
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 41.48
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 33.18
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 24.89
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 49.77
PR | 995 | 03/06/26 | 48 | Barnhart, Joseph N |  | 24.89
PR | 995 | 03/06/26 | 74 | Mackey, Cole J |  | 197.18
PR | 995 | 03/06/26 | 74 | Mackey, Cole J |  | 147.89
PR | 995 | 03/06/26 | 74 | Mackey, Cole J |  | 197.18
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 49.77
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 16.59
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 49.77
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 16.59
PR | 995 | 03/13/26 | 193 | Barnhart, Joseph N |  | 24.89
PR | 995 | 03/13/26 | 219 | Mackey, Cole J |  | 197.18
PR | 995 | 03/13/26 | 219 | Mackey, Cole J |  | 92.43
PR | 995 | 03/13/26 | 219 | Mackey, Cole J |  | 197.18
PR | 995 | 03/13/26 | 219 | Mackey, Cole J |  | 197.18
PR | 995 | 03/20/26 | 306 | Anderson, Richard P |  | 15.88
PR | 995 | 03/20/26 | 306 | Anderson, Richard P |  | 15.88
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 33.18
PR | 995 | 03/20/26 | 311 | Barnhart, Joseph N |  | 66.36
PR | 995 | 03/20/26 | 337 | Mackey, Cole J |  | 110.92
PR | 995 | 03/20/26 | 337 | Mackey, Cole J |  | 197.18
PR | 995 | 03/20/26 | 337 | Mackey, Cole J |  | 98.59
PR | 995 | 03/20/26 | 337 | Mackey, Cole J |  | 197.18
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 8.3
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 33.18
PR | 995 | 03/27/26 | 479 | Barnhart, Joseph N |  | 66.36
PR | 995 | 03/27/26 | 505 | Mackey, Cole J |  | 197.18
PR | 998 | 06/07/24 | 139 | Johnson, Jake E |  | 15.91
PR | 998 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 06/14/24 | 352 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/14/24 | 362 | Johnson, Jake E |  | 3.98
PR | 998 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 06/21/24 | 524 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 06/21/24 | 533 | Johnson, Jake E |  | 19.89
PR | 998 | 06/28/24 | 731 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 06/28/24 | 740 | Johnson, Jake E |  | 15.91
PR | 998 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 26.39
PR | 998 | 07/05/24 | 45 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/05/24 | 53 | Johnson, Jake E |  | 7.96
PR | 998 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/12/24 | 207 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 07/12/24 | 216 | Johnson, Jake E |  | 7.96
PR | 998 | 07/19/24 | 390 | Barnhart, Joseph N |  | 15.61
PR | 998 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 34.31
PR | 998 | 07/19/24 | 413 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 07/19/24 | 422 | Johnson, Jake E |  | 15.91
PR | 998 | 07/26/24 | 595 | Eisenhauer, Tommy J |  | 17.44
PR | 998 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 31.67
PR | 998 | 07/26/24 | 600 | Gerard, Jeffrey S |  | 29.03
PR | 998 | 07/26/24 | 609 | Johnson, Jake E |  | 3.98
PR | 998 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/02/24 | 40 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/09/24 | 237 | Anderson, Richard P |  | 69.62
PR | 998 | 08/09/24 | 256 | Boss, Benjamin T |  | 31.21
PR | 998 | 08/09/24 | 270 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 15.84
PR | 998 | 08/09/24 | 274 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 08/09/24 | 283 | Johnson, Jake E |  | 3.98
PR | 998 | 08/09/24 | 303 | Silva Morales, Jair J |  | 20.81
PR | 998 | 08/09/24 | 312 | Yohannes Jr., Samson |  | 20.2
PR | 998 | 08/16/24 | 428 | Anderson, Richard P |  | 29.84
PR | 998 | 08/16/24 | 428 | Anderson, Richard P |  | 27.35
PR | 998 | 08/16/24 | 447 | Boss, Benjamin T |  | 93.64
PR | 998 | 08/16/24 | 459 | Eisenhauer, Tommy J |  | 130.82
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 08/16/24 | 463 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 08/16/24 | 472 | Johnson, Jake E |  | 7.96
PR | 998 | 08/23/24 | 721 | Eisenhauer, Tommy J |  | 82.85
PR | 998 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/23/24 | 725 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/23/24 | 734 | Johnson, Jake E |  | 35.8
PR | 998 | 08/30/24 | 852 | Boss, Benjamin T |  | 15.61
PR | 998 | 08/30/24 | 863 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 08/30/24 | 867 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 08/30/24 | 876 | Johnson, Jake E |  | 3.98
PR | 998 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/06/24 | 44 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/06/24 | 53 | Johnson, Jake E |  | 11.93
PR | 998 | 09/13/24 | 217 | Anderson, Richard P |  | 24.86
PR | 998 | 09/13/24 | 222 | Del Villar, Flabio |  | 15.3
PR | 998 | 09/13/24 | 233 | Barnhart, Joseph N |  | 15.61
PR | 998 | 09/13/24 | 247 | Eisenhauer, Tommy J |  | 61.05
PR | 998 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 09/13/24 | 252 | Gerard, Jeffrey S |  | 21.11
PR | 998 | 09/13/24 | 261 | Johnson, Jake E |  | 15.91
PR | 998 | 09/20/24 | 389 | Anderson, Richard P |  | 24.86
PR | 998 | 09/20/24 | 419 | Eisenhauer, Tommy J |  | 43.61
PR | 998 | 09/20/24 | 423 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 09/20/24 | 432 | Johnson, Jake E |  | 7.96
PR | 998 | 09/27/24 | 542 | Barnhart, Joseph N |  | 15.61
PR | 998 | 09/27/24 | 555 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 09/27/24 | 555 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 09/27/24 | 568 | Johnson, Jake E |  | 11.93
PR | 998 | 10/04/24 | 39 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/04/24 | 43 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/04/24 | 52 | Johnson, Jake E |  | 15.91
PR | 998 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/11/24 | 250 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/11/24 | 259 | Johnson, Jake E |  | 3.98
PR | 998 | 10/18/24 | 429 | Anderson, Richard P |  | 7.46
PR | 998 | 10/18/24 | 459 | Eisenhauer, Tommy J |  | 52.33
PR | 998 | 10/18/24 | 462 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/18/24 | 471 | Johnson, Jake E |  | 3.98
PR | 998 | 10/25/24 | 606 | Eisenhauer, Tommy J |  | 122.09
PR | 998 | 10/25/24 | 606 | Eisenhauer, Tommy J |  | 52.33
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/25/24 | 609 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/25/24 | 613 | Gomez Aguirre, Exequiel |  | 51.41
PR | 998 | 10/25/24 | 613 | Gomez Aguirre, Exequiel |  | 22.03
PR | 998 | 11/01/24 | 6 | Anderson, Richard P |  | 4.97
PR | 998 | 11/01/24 | 35 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/01/24 | 38 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/01/24 | 42 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 11/01/24 | 47 | Johnson, Jake E |  | 3.98
PR | 998 | 11/08/24 | 155 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 11/08/24 | 158 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/08/24 | 162 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 11/08/24 | 167 | Johnson, Jake E |  | 7.96
PR | 998 | 11/15/24 | 346 | Anderson, Richard P |  | 4.97
PR | 998 | 11/15/24 | 363 | Barnhart, Joseph N |  | 20.81
PR | 998 | 11/15/24 | 375 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 11/15/24 | 378 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 11/15/24 | 382 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 11/15/24 | 387 | Johnson, Jake E |  | 3.98
PR | 998 | 11/15/24 | 448 | Barnhart, Joseph N |  | -20.81
PR | 998 | 11/22/24 | 530 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 11/22/24 | 533 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/22/24 | 537 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 11/29/24 | 678 | Eisenhauer, Tommy J |  | 122.09
PR | 998 | 11/29/24 | 681 | Gerard, Jeffrey S |  | 13.2
PR | 998 | 11/29/24 | 685 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 12/06/24 | 80 | Eisenhauer, Tommy J |  | 52.33
PR | 998 | 12/06/24 | 87 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 12/06/24 | 96 | Martinez Reyes, Juan C |  | 26.93
PR | 998 | 12/13/24 | 250 | Barnhart, Joseph N |  | 15.61
PR | 998 | 12/13/24 | 262 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 12/13/24 | 265 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/13/24 | 269 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 12/13/24 | 278 | Martinez Reyes, Juan C |  | 107.71
PR | 998 | 12/20/24 | 437 | Barnhart, Joseph N |  | 20.81
PR | 998 | 12/20/24 | 448 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 12/20/24 | 451 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/20/24 | 455 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 12/20/24 | 460 | Johnson, Jake E |  | 7.96
PR | 998 | 12/20/24 | 464 | Martinez Reyes, Juan C |  | 134.64
PR | 998 | 12/27/24 | 544 | Del Villar, Flabio |  | 13.39
PR | 998 | 12/27/24 | 558 | Calderon M, Roberto H |  | 11.78
PR | 998 | 12/27/24 | 564 | Cruz, Azael S |  | 17.14
PR | 998 | 12/27/24 | 567 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 12/27/24 | 570 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/27/24 | 574 | Gomez Aguirre, Exequiel |  | 42.23
PR | 998 | 12/27/24 | 578 | Jimenez Alvarenga, Gerson M |  | 20.88
PR | 998 | 12/27/24 | 583 | Martinez Reyes, Juan C |  | 53.86
PR | 998 | 12/27/24 | 585 | Melgar Moz, Brandon |  | 13.46
PR | 998 | 01/03/25 | 12 | Anderson, Richard P |  | 4.97
PR | 998 | 01/03/25 | 38 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 01/03/25 | 44 | Gomez Aguirre, Exequiel |  | 29.38
PR | 998 | 01/03/25 | 53 | Martinez Reyes, Juan C |  | 53.86
PR | 998 | 01/10/25 | 201 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/10/25 | 204 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 01/10/25 | 207 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 01/10/25 | 216 | Martinez Reyes, Juan C |  | 53.86
PR | 998 | 01/17/25 | 364 | Eisenhauer, Tommy J |  | 87.21
PR | 998 | 01/17/25 | 370 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 01/17/25 | 379 | Martinez Reyes, Juan C |  | 100.98
PR | 998 | 01/24/25 | 531 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 01/24/25 | 531 | Eisenhauer, Tommy J |  | 17.44
PR | 998 | 01/24/25 | 537 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 01/24/25 | 546 | Martinez Reyes, Juan C |  | 94.25
PR | 998 | 01/24/25 | 546 | Martinez Reyes, Juan C |  | 13.46
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/31/25 | 712 | Barnhart, Joseph N |  | 10.4
PR | 998 | 01/31/25 | 723 | Eisenhauer, Tommy J |  | 152.62
PR | 998 | 01/31/25 | 726 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 01/31/25 | 729 | Gomez Aguirre, Exequiel |  | 29.38
PR | 998 | 01/31/25 | 729 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 01/31/25 | 738 | Martinez Reyes, Juan C |  | 13.46
PR | 998 | 01/31/25 | 738 | Martinez Reyes, Juan C |  | 114.44
PR | 998 | 02/07/25 | 42 | Barnhart, Joseph N |  | 5.2
PR | 998 | 02/07/25 | 53 | Eisenhauer, Tommy J |  | 26.16
PR | 998 | 02/07/25 | 53 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 02/07/25 | 59 | Gomez Aguirre, Exequiel |  | 20.2
PR | 998 | 02/07/25 | 59 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 02/07/25 | 68 | Martinez Reyes, Juan C |  | 90.88
PR | 998 | 02/14/25 | 208 | Barnhart, Joseph N |  | 15.61
PR | 998 | 02/14/25 | 219 | Eisenhauer, Tommy J |  | 165.7
PR | 998 | 02/14/25 | 225 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 02/14/25 | 230 | Johnson, Jake E |  | 3.98
PR | 998 | 02/14/25 | 234 | Martinez Reyes, Juan C |  | 80.78
PR | 998 | 02/14/25 | 234 | Martinez Reyes, Juan C |  | 53.86
PR | 998 | 02/21/25 | 337 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/21/25 | 340 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 02/21/25 | 343 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 02/21/25 | 343 | Gomez Aguirre, Exequiel |  | 29.38
PR | 998 | 02/21/25 | 352 | Martinez Reyes, Juan C |  | 134.64
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 7.8
PR | 998 | 02/28/25 | 516 | Barnhart, Joseph N |  | 2.6
PR | 998 | 02/28/25 | 527 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/28/25 | 530 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/28/25 | 533 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 02/28/25 | 542 | Martinez Reyes, Juan C |  | 80.78
PR | 998 | 03/07/25 | 29 | Barnhart, Joseph N |  | 5.2
PR | 998 | 03/07/25 | 40 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 03/07/25 | 40 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 03/07/25 | 46 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 03/07/25 | 46 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 03/07/25 | 51 | Johnson, Jake E |  | 3.98
PR | 998 | 03/14/25 | 240 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 03/14/25 | 240 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 03/14/25 | 246 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 03/14/25 | 246 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 03/14/25 | 251 | Johnson, Jake E |  | 7.96
PR | 998 | 03/21/25 | 433 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 03/21/25 | 433 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 03/21/25 | 436 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/21/25 | 439 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 03/21/25 | 439 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 03/28/25 | 588 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 03/28/25 | 595 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 03/28/25 | 595 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 04/04/25 | 31 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 04/04/25 | 38 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 04/04/25 | 43 | Johnson, Jake E |  | 7.96
PR | 998 | 04/11/25 | 211 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 04/11/25 | 214 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/11/25 | 218 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 04/11/25 | 227 | Martinez Reyes, Juan C |  | 13.46
PR | 998 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 130.82
PR | 998 | 04/18/25 | 435 | Eisenhauer, Tommy J |  | 8.72
PR | 998 | 04/18/25 | 442 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 04/18/25 | 451 | Martinez Reyes, Juan C |  | 26.93
PR | 998 | 04/25/25 | 548 | Anderson, Richard P |  | 19.89
PR | 998 | 04/25/25 | 574 | Eisenhauer, Tommy J |  | 95.93
PR | 998 | 04/25/25 | 577 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/25/25 | 581 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 04/25/25 | 590 | Martinez Reyes, Juan C |  | 53.86
PR | 998 | 05/02/25 | 17 | Barnhart, Joseph N |  | 2.6
PR | 998 | 05/02/25 | 28 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 05/02/25 | 35 | Gomez Aguirre, Exequiel |  | 14.69
PR | 998 | 05/02/25 | 35 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 05/09/25 | 162 | Barnhart, Joseph N |  | 26.01
PR | 998 | 05/09/25 | 172 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 05/09/25 | 172 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 05/09/25 | 174 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 05/09/25 | 178 | Gomez Aguirre, Exequiel |  | 58.75
PR | 998 | 05/16/25 | 371 | Eisenhauer, Tommy J |  | 122.09
PR | 998 | 05/16/25 | 377 | Gomez Aguirre, Exequiel |  | 73.44
PR | 998 | 05/23/25 | 457 | Barnhart, Joseph N |  | 2.6
PR | 998 | 05/23/25 | 467 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 05/23/25 | 467 | Eisenhauer, Tommy J |  | 69.77
PR | 998 | 05/23/25 | 473 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 05/23/25 | 473 | Gomez Aguirre, Exequiel |  | 29.38
PR | 998 | 05/30/25 | 555 | Eisenhauer, Tommy J |  | 87.21
PR | 998 | 05/30/25 | 562 | Gomez Aguirre, Exequiel |  | 44.06
PR | 998 | 06/06/25 | 33 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/06/25 | 43 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 06/06/25 | 50 | Gomez Aguirre, Exequiel |  | 79.56
PR | 998 | 06/13/25 | 204 | Eisenhauer, Tommy J |  | 170.06
PR | 998 | 06/13/25 | 207 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/13/25 | 208 | Gerard, Jordan E |  | 9.18
PR | 998 | 06/13/25 | 211 | Gomez Aguirre, Exequiel |  | 77.57
PR | 998 | 06/20/25 | 331 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 06/20/25 | 334 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 06/20/25 | 338 | Gomez Aguirre, Exequiel |  | 63.65
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 10.4
PR | 998 | 06/27/25 | 476 | Barnhart, Joseph N |  | 5.2
PR | 998 | 06/27/25 | 486 | Eisenhauer, Tommy J |  | 21.8
PR | 998 | 06/27/25 | 486 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 06/27/25 | 493 | Gomez Aguirre, Exequiel |  | 25.86
PR | 998 | 07/03/25 | 29 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 07/03/25 | 36 | Gomez Aguirre, Exequiel |  | 79.56
PR | 998 | 07/11/25 | 154 | Eisenhauer, Tommy J |  | 78.49
PR | 998 | 07/11/25 | 160 | Gomez Aguirre, Exequiel |  | 43.76
PR | 998 | 07/18/25 | 324 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 07/18/25 | 327 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 07/25/25 | 479 | Barnhart, Joseph N |  | 10.4
PR | 998 | 07/25/25 | 489 | Eisenhauer, Tommy J |  | 17.44
PR | 998 | 07/25/25 | 493 | Gerard, Jordan E |  | 13.77
PR | 998 | 07/25/25 | 495 | Gomez Aguirre, Exequiel |  | 7.96
PR | 998 | 08/01/25 | 12 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/01/25 | 22 | Eisenhauer, Tommy J |  | 174.42
PR | 998 | 08/01/25 | 26 | Gerard, Jordan E |  | 9.18
PR | 998 | 08/01/25 | 28 | Gomez Aguirre, Exequiel |  | 71.6
PR | 998 | 08/08/25 | 153 | Eisenhauer, Tommy J |  | 139.54
PR | 998 | 08/08/25 | 159 | Gomez Aguirre, Exequiel |  | 63.65
PR | 998 | 08/15/25 | 278 | Eisenhauer, Tommy J |  | 152.62
PR | 998 | 08/15/25 | 284 | Gomez Aguirre, Exequiel |  | 71.6
PR | 998 | 08/22/25 | 382 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 08/22/25 | 382 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 08/22/25 | 386 | Gerard, Jordan E |  | 4.59
PR | 998 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 47.74
PR | 998 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 08/22/25 | 388 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 10.4
PR | 998 | 08/29/25 | 534 | Barnhart, Joseph N |  | 5.2
PR | 998 | 08/29/25 | 545 | Eisenhauer, Tommy J |  | 161.34
PR | 998 | 08/29/25 | 547 | Games, Jordan M |  | 16.22
PR | 998 | 08/29/25 | 551 | Gomez Aguirre, Exequiel |  | 79.56
PR | 998 | 09/05/25 | 30 | Eisenhauer, Tommy J |  | 130.82
PR | 998 | 09/05/25 | 34 | Gerard, Jordan E |  | 4.59
PR | 998 | 09/05/25 | 36 | Gomez Aguirre, Exequiel |  | 59.67
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/12/25 | 116 | Barnhart, Joseph N |  | 5.2
PR | 998 | 09/12/25 | 127 | Eisenhauer, Tommy J |  | 104.65
PR | 998 | 09/12/25 | 131 | Gerard, Jordan E |  | 4.59
PR | 998 | 09/12/25 | 133 | Gomez Aguirre, Exequiel |  | 63.65
PR | 998 | 09/19/25 | 259 | Eisenhauer, Tommy J |  | 78.49
PR | 998 | 09/19/25 | 261 | Games, Jordan M |  | 16.22
PR | 998 | 09/19/25 | 263 | Gerard, Jordan E |  | 4.59
PR | 998 | 09/19/25 | 265 | Gomez Aguirre, Exequiel |  | 25.86
PR | 998 | 09/26/25 | 430 | Eisenhauer, Tommy J |  | 6.54
PR | 998 | 09/26/25 | 436 | Gomez Aguirre, Exequiel |  | 0.5
PR | 998 | 10/03/25 | 26 | Eisenhauer, Tommy J |  | 30.52
PR | 998 | 10/03/25 | 26 | Eisenhauer, Tommy J |  | 11.99
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 5.07
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 35.48
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 19.26
PR | 998 | 10/03/25 | 29 | Games, Jordan M |  | 18.25
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 10/03/25 | 31 | Gerard, Jordan E |  | 4.59
PR | 998 | 10/03/25 | 33 | Gomez Aguirre, Exequiel |  | 15.41
PR | 998 | 10/03/25 | 56 | Suniga Aviles, Kelvin A |  | 14.69
PR | 998 | 10/03/25 | 62 | Zuniga Avilez, Eduar A |  | 14.69
PR | 998 | 10/10/25 | 164 | Araque, Mario W |  | 14.69
PR | 998 | 10/10/25 | 164 | Araque, Mario W |  | 14.69
PR | 998 | 10/10/25 | 164 | Araque, Mario W |  | 14.69
PR | 998 | 10/10/25 | 164 | Araque, Mario W |  | 14.69
PR | 998 | 10/10/25 | 164 | Araque, Mario W |  | 14.69
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 9.1
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 26.01
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 7.8
PR | 998 | 10/10/25 | 167 | Barnhart, Joseph N |  | 13.01
PR | 998 | 10/10/25 | 178 | Eisenhauer, Tommy J |  | 25.07
PR | 998 | 10/10/25 | 178 | Eisenhauer, Tommy J |  | 20.71
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 32.44
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 16.22
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 32.44
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 18.25
PR | 998 | 10/10/25 | 181 | Games, Jordan M |  | 11.15
PR | 998 | 10/10/25 | 183 | Gerard, Jordan E |  | 9.18
PR | 998 | 10/10/25 | 183 | Gerard, Jordan E |  | 9.18
PR | 998 | 10/10/25 | 186 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 10/17/25 | 369 | Araque, Mario W |  | 14.69
PR | 998 | 10/17/25 | 369 | Araque, Mario W |  | 13.77
PR | 998 | 10/17/25 | 369 | Araque, Mario W |  | 15.61
PR | 998 | 10/17/25 | 369 | Araque, Mario W |  | 7.8
PR | 998 | 10/17/25 | 372 | Barnhart, Joseph N |  | 1.3
PR | 998 | 10/17/25 | 386 | Games, Jordan M |  | 32.44
PR | 998 | 10/17/25 | 386 | Games, Jordan M |  | 23.31
PR | 998 | 10/17/25 | 386 | Games, Jordan M |  | 32.44
PR | 998 | 10/17/25 | 386 | Games, Jordan M |  | 18.25
PR | 998 | 10/24/25 | 517 | Eisenhauer, Tommy J |  | 13.08
PR | 998 | 10/31/25 | 683 | Eisenhauer, Tommy J |  | 1.09
PR | 998 | 10/31/25 | 683 | Eisenhauer, Tommy J |  | 16.35
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 8.11
PR | 998 | 10/31/25 | 686 | Games, Jordan M |  | 32.44
PR | 998 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 9.1
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 6.5
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 10.4
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 7.8
PR | 998 | 11/07/25 | 59 | Barnhart, Joseph N |  | 3.9
PR | 998 | 11/07/25 | 72 | Eisenhauer, Tommy J |  | 4.36
PR | 998 | 11/07/25 | 72 | Eisenhauer, Tommy J |  | 21.8
PR | 998 | 11/07/25 | 76 | Gerard, Jordan E |  | 9.18
PR | 998 | 11/07/25 | 79 | Gomez Aguirre, Exequiel |  | 1.49
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 3.9
PR | 998 | 11/14/25 | 219 | Barnhart, Joseph N |  | 13.01
PR | 998 | 11/14/25 | 232 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/14/25 | 235 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/14/25 | 239 | Gomez Aguirre, Exequiel |  | 14.92
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 42.92
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 14.31
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 29.91
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 28.61
PR | 998 | 11/21/25 | 336 | Barnhart, Joseph N |  | 41.62
PR | 998 | 11/21/25 | 349 | Eisenhauer, Tommy J |  | 33.79
PR | 998 | 11/21/25 | 349 | Eisenhauer, Tommy J |  | 16.35
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 9.18
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 5.74
PR | 998 | 11/21/25 | 353 | Gerard, Jordan E |  | 6.89
PR | 998 | 11/21/25 | 356 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 11/21/25 | 356 | Gomez Aguirre, Exequiel |  | 5.47
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 6.5
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 11.7
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 14.31
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 11.7
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 14.31
PR | 998 | 11/28/25 | 519 | Barnhart, Joseph N |  | 41.62
PR | 998 | 11/28/25 | 532 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 11/28/25 | 540 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 12/05/25 | 45 | Barnhart, Joseph N |  | 44.22
PR | 998 | 12/05/25 | 45 | Barnhart, Joseph N |  | 13.01
PR | 998 | 12/05/25 | 45 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/05/25 | 58 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 12/05/25 | 66 | Gomez Aguirre, Exequiel |  | 1.49
PR | 998 | 12/05/25 | 66 | Gomez Aguirre, Exequiel |  | 4.48
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 20.81
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 22.11
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 16.91
PR | 998 | 12/12/25 | 182 | Barnhart, Joseph N |  | 2.6
PR | 998 | 12/12/25 | 195 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 12/12/25 | 195 | Eisenhauer, Tommy J |  | 34.88
PR | 998 | 12/12/25 | 203 | Gomez Aguirre, Exequiel |  | 1.49
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 41.62
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 15.61
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 9.1
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 5.2
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/19/25 | 323 | Barnhart, Joseph N |  | 1.3
PR | 998 | 12/19/25 | 336 | Eisenhauer, Tommy J |  | 37.06
PR | 998 | 12/19/25 | 336 | Eisenhauer, Tommy J |  | 8.72
PR | 998 | 12/19/25 | 341 | Gerard, Jordan E |  | 3.44
PR | 998 | 12/19/25 | 341 | Gerard, Jordan E |  | 6.89
PR | 998 | 12/19/25 | 344 | Gomez Aguirre, Exequiel |  | 15.91
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 10.4
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 29.91
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 11.7
PR | 998 | 12/26/25 | 511 | Barnhart, Joseph N |  | 16.91
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 9.37
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 12.05
PR | 998 | 01/09/26 | 130 | Barnhart, Joseph N |  | 10.71
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 17.4
PR | 998 | 01/16/26 | 276 | Barnhart, Joseph N |  | 12.05
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/16/26 | 294 | Gerard, Jordan E |  | 11.28
PR | 998 | 01/23/26 | 467 | Barnhart, Joseph N |  | 16.07
PR | 998 | 01/23/26 | 487 | Gomez Aguirre, Exequiel |  | 6.43
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 12.05
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 2.68
PR | 998 | 01/30/26 | 580 | Barnhart, Joseph N |  | 13.39
PR | 998 | 01/30/26 | 600 | Gomez Aguirre, Exequiel |  | 6.43
PR | 998 | 01/30/26 | 600 | Gomez Aguirre, Exequiel |  | 5.89
PR | 998 | 02/06/26 | 56 | Barnhart, Joseph N |  | 13.39
PR | 998 | 02/06/26 | 56 | Barnhart, Joseph N |  | 4.02
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 41.5
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 22.76
PR | 998 | 02/13/26 | 188 | Barnhart, Joseph N |  | 10.71
PR | 998 | 02/13/26 | 207 | Gomez Aguirre, Exequiel |  | 2.14
PR | 998 | 02/13/26 | 214 | Mackey, Cole J |  | 31.82
PR | 998 | 02/13/26 | 214 | Mackey, Cole J |  | 31.82
PR | 998 | 02/13/26 | 214 | Mackey, Cole J |  | 29.84
PR | 998 | 02/13/26 | 214 | Mackey, Cole J |  | 31.82
PR | 998 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 5.97
PR | 998 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 8.26
PR | 998 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 13.77
PR | 998 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 14.69
PR | 998 | 02/13/26 | 220 | Nunez Bravo, Jose L |  | 14.69
PR | 998 | 02/13/26 | 229 | Suniga Aviles, Kelvin A |  | 15.41
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 17.4
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 4.02
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 5.36
PR | 998 | 02/20/26 | 304 | Barnhart, Joseph N |  | 5.36
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 9.03
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 31.82
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 18.9
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 27.85
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 3.98
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 31.82
PR | 998 | 02/20/26 | 330 | Mackey, Cole J |  | 31.82
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 2.68
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 5.36
PR | 998 | 02/27/26 | 452 | Barnhart, Joseph N |  | 36.15
PR | 998 | 02/27/26 | 478 | Mackey, Cole J |  | 11.93
PR | 998 | 02/27/26 | 478 | Mackey, Cole J |  | 19.89
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 10.71
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 13.39
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 6.69
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 5.36
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 8.03
PR | 998 | 03/06/26 | 48 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/06/26 | 74 | Mackey, Cole J |  | 31.82
PR | 998 | 03/06/26 | 74 | Mackey, Cole J |  | 23.87
PR | 998 | 03/06/26 | 74 | Mackey, Cole J |  | 31.82
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 8.03
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 2.68
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 8.03
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 2.68
PR | 998 | 03/13/26 | 193 | Barnhart, Joseph N |  | 4.02
PR | 998 | 03/13/26 | 219 | Mackey, Cole J |  | 31.82
PR | 998 | 03/13/26 | 219 | Mackey, Cole J |  | 14.92
PR | 998 | 03/13/26 | 219 | Mackey, Cole J |  | 31.82
PR | 998 | 03/13/26 | 219 | Mackey, Cole J |  | 31.82
PR | 998 | 03/20/26 | 306 | Anderson, Richard P |  | 2.56
PR | 998 | 03/20/26 | 306 | Anderson, Richard P |  | 2.56
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 5.36
PR | 998 | 03/20/26 | 311 | Barnhart, Joseph N |  | 10.71
PR | 998 | 03/20/26 | 337 | Mackey, Cole J |  | 17.9
PR | 998 | 03/20/26 | 337 | Mackey, Cole J |  | 31.82
PR | 998 | 03/20/26 | 337 | Mackey, Cole J |  | 15.91
PR | 998 | 03/20/26 | 337 | Mackey, Cole J |  | 31.82
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 1.34
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 5.36
PR | 998 | 03/27/26 | 479 | Barnhart, Joseph N |  | 10.71
PR | 998 | 03/27/26 | 505 | Mackey, Cole J |  | 31.82
AR | 999 | 07/18/24 | 463 | BMDC Services, LLC $Big 1410 |  | -2045 | 038291
AR | 999 | 07/18/24 | 463 | BMDC Services, LLC $Big 1410 |  | -49250 | 038291
AR | 999 | 07/18/24 | 470 | BMDC Services, LLC $Big 1410 |  | 2045 | 038298
AR | 999 | 07/18/24 | 470 | BMDC Services, LLC $Big 1410 |  | 49250 | 038298