## 01 Overview
OWP #2112 · Big 3 Apartments
BMDC Services, LLC · 20 units · Live / in-progress · OCIP
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 518063
Retention held | 25903.15
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 0
PR | 0
AR | 0

## 02 Job Info
Job Information
Job ID | 2112
Project name | Big 3 Apartments
General contractor | BMDC Services, LLC
Owner | BMDC Big 3 LLC
Units | 20
Insurance | Not Wrap
Job start | May 2025
Expected completion | Jul 2026
Architect | Robison Engineering
MEP Engineer | Robison Engineering
Status | ACTIVE · in-progress
JDR report date | Mar 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0
Executed change orders (net) | 0 | 0
Total contract value
Executed Change Orders
CO # | Description | Amount
CO#01 | Condensate drain additions | 11500
CO#02 | Matte black flush lever upgrade | 1120
CO#03 | Water metering additions | 20100
CO#04 | Temporary water service | 1362
CO#05 | Minor re-routes + small adds | -1737

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 0 | 0 | 0
Material | 0 | 0 | 0
Overhead | 0 | 0 | 0
Burden | 0 | 0 | 0
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 0 | 0 | 0
JOURNEYMAN | 0 | 0 | 0
APPRENTICE/HELPER | 0 | 0 | 0
OT-ONLY | 0 | 0 | 0

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 0
Active workers | 0
Hours per unit (to date) | 0
Revenue per labor hour (billed) | 0
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34%
Roughin labor share (code 120) | 0% | 45%
Top vendor concentration | 0% | 38%
Hours per unit | 0 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Retention aging | ✓ OK | $25,903 held · 5.0% of billed · standard range
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 0 | 0
Revenue billed (AR ·-1) | 0 | 0
AP source total |  | 0
PR source total |  | 0
GL source total |  | 0

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · live | Initial build for #2112 live project. 17-tab JCR schema on revised budget basis.