## 01 Overview
OWP #2114 · Ballard Blossom Apartments
Holland Construction · 239 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 80000
Retention held | 0
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 55000
PR | 11355.58
AR | -80000

## 02 Job Info
Job Information
Job ID | 2114
Project name | Ballard Blossom Apartments
General contractor | Holland Construction
Owner
Units | 239
Insurance | OCIP (WRAP) — assumed by Owner
Job start | Sep 2025
Expected completion | Apr 2028 TCO (22-month field schedule from Jul 2026 foundations)
Architect
MEP Engineer | Robison Engineering
Status | ACTIVE · in-progress
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0
Executed change orders (net) | 0 | 0
Total contract value
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
101 | Takeoff & Purchase Labor | 0 | 0 | 7372.25 |  | 0
601 | Engineering/Plans | 0 | 0 | 55000 |  | 0
995 | Payroll Burden | 0 | 0 | 3419.25 |  | 0
998 | Payroll Taxes | 0 | 0 | 564.08 |  | 0
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 1 | 0 | 7372.25
Material | 0 | 0 | 0
Overhead | 1 | 0 | 55000
Burden | 2 | 0 | 3983.33
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
101 | Takeoff & Purchase Labor | 0 | 7372.25
601 | Engineering/Plans | 0 | 55000
995 | Payroll Burden | 0 | 3419.25
998 | Payroll Taxes | 0 | 564.08

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Robison Engineering, Inc. | 55000 | 1
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Jeffrey S | 62 | 4278 |  | LEAD/SUPERVISOR
Gerard, Jordan E | 52.2 | 3094 |  | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 2 | 114.2 | 7372
JOURNEYMAN | 0 | 0 | 0
APPRENTICE/HELPER | 0 | 0 | 0
OT-ONLY | 0 | 0 | 0

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 114
Active workers | 2
Hours per unit (to date) | 0.5
Revenue per labor hour (billed) | 700.22
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34%
Roughin labor share (code 120) | 0% | 45%
Top vendor concentration | 100% | 38%
Hours per unit | 0.47803 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $55,000 actual spend — needs CO or budget transfer
Top vendor concentration (Robison Engineering,) | ⚠ WATCH | 100% of AP ($55,000) — high, monitor
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 66355.58 | 66355.58
Revenue billed (AR ·-1) | -80000 | 80000
AP source total |  | 55000
PR source total |  | 11355.58
GL source total |  | 0

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · live | Initial build for #2114 live project. 17-tab JCR schema on revised budget basis.