## Summary
#2114 · Ballard Blossom
Holland Construction · 239 units · ACTIVE · 0.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
0 | 0% | 80000 | -80000
Key facts
Original contract |  | 0
Revised contract (CO impact) |  | 0
Executed COs (net) |  | 0
Retention held |  | 0
Revised expense budget |  | 0
Forecast net profit |  | 0
Percent complete |  | 0%
Live signals
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $55,000 actual — needs CO or budget transfer
Top vendor (Robison Engineering,) | ⚠ WATCH | 100% of AP — high
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ⚠ WATCH | 0.0% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Robison Engineering, Inc. | 1 | 55000 | 100%

## Transactions
Transactions Detail
JDR source transactions for job #2114 · 237 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 101 | 09/12/25 | 131 | Gerard, Jordan E | 3 | 180 | 23653
PR | 101 | 09/26/25 | 434 | Gerard, Jordan E | 1.75 | 105 | 43666
PR | 101 | 10/03/25 | 30 | Gerard, Jeffrey S | 0.5 | 34.5 | 13673
PR | 101 | 10/24/25 | 522 | Gerard, Jordan E | 1 | 60 | 43698
PR | 101 | 10/24/25 | 522 | Gerard, Jordan E | 1 | 60 | 43698
PR | 101 | 10/31/25 | 687 | Gerard, Jeffrey S | 1 | 69 | 53704
PR | 101 | 11/28/25 | 536 | Gerard, Jeffrey S | 1 | 69 | 43726
PR | 101 | 11/28/25 | 536 | Gerard, Jeffrey S | 1 | 69 | 43726
PR | 101 | 12/12/25 | 199 | Gerard, Jeffrey S | 1 | 69 | 23734
PR | 101 | 12/12/25 | 199 | Gerard, Jeffrey S | 0.5 | 34.5 | 23734
PR | 101 | 12/26/25 | 528 | Gerard, Jeffrey S | 2 | 138 | 43746
PR | 101 | 12/26/25 | 529 | Gerard, Jordan E | 2.25 | 135 | 43747
PR | 101 | 12/26/25 | 529 | Gerard, Jordan E | 0.75 | 45 | 43747
PR | 101 | 01/02/26 | 32 | Gerard, Jeffrey S | 1 | 69 | 13750
PR | 101 | 01/02/26 | 32 | Gerard, Jeffrey S | 1.5 | 103.5 | 13750
PR | 101 | 01/02/26 | 33 | Gerard, Jordan E | 1.75 | 105 | 13751
PR | 101 | 01/09/26 | 147 | Gerard, Jeffrey S | 1 | 69 | 23754
PR | 101 | 01/09/26 | 148 | Gerard, Jordan E | 3.25 | 191.75 | 23755
PR | 101 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 101 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 101 | 01/16/26 | 293 | Gerard, Jeffrey S | 1 | 69 | 33758
PR | 101 | 01/23/26 | 484 | Gerard, Jeffrey S | 1 | 69 | 43763
PR | 101 | 01/23/26 | 484 | Gerard, Jeffrey S | 2 | 138 | 43763
PR | 101 | 01/23/26 | 484 | Gerard, Jeffrey S | 1 | 69 | 43763
PR | 101 | 01/23/26 | 485 | Gerard, Jordan E | 2.5 | 147.5 | 43764
PR | 101 | 01/30/26 | 597 | Gerard, Jeffrey S | 1 | 69 | 53768
PR | 101 | 01/30/26 | 597 | Gerard, Jeffrey S | 2 | 138 | 53768
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 1 | 69 | 13772
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 0.5 | 34.5 | 13772
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 1 | 69 | 13772
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 2 | 138 | 13772
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 2 | 138 | 13772
PR | 101 | 02/06/26 | 72 | Gerard, Jeffrey S | 2 | 138 | 13772
PR | 101 | 02/06/26 | 73 | Gerard, Jordan E | 4 | 236 | 13773
PR | 101 | 02/06/26 | 73 | Gerard, Jordan E | 2.25 | 132.75 | 13773
PR | 101 | 02/06/26 | 73 | Gerard, Jordan E | 1.5 | 88.5 | 13773
PR | 101 | 02/13/26 | 204 | Gerard, Jeffrey S | 2 | 138 | 23777
PR | 101 | 02/13/26 | 204 | Gerard, Jeffrey S | 1 | 69 | 23777
PR | 101 | 02/13/26 | 204 | Gerard, Jeffrey S | 2 | 138 | 23777
PR | 101 | 02/13/26 | 204 | Gerard, Jeffrey S | 2 | 138 | 23777
PR | 101 | 02/13/26 | 205 | Gerard, Jordan E | 3.5 | 206.5 | 23778
PR | 101 | 02/20/26 | 320 | Gerard, Jeffrey S | 1 | 69 | 33784
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 0.75 | 44.25 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 2 | 118 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 2 | 118 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 0.75 | 44.25 | 33785
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 1 | 69 | 43787
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 1 | 69 | 43787
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 2 | 138 | 43787
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 2 | 138 | 43787
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 1 | 69 | 43787
PR | 101 | 03/06/26 | 63 | Gerard, Jeffrey S | 0.5 | 34.5 | 13791
PR | 101 | 03/06/26 | 63 | Gerard, Jeffrey S | 0.5 | 34.5 | 13791
PR | 101 | 03/06/26 | 63 | Gerard, Jeffrey S | 1 | 69 | 13791
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 1 | 59 | 13792
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 1.75 | 103.25 | 13792
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 1 | 69 | 23795
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 2 | 138 | 23795
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 1 | 69 | 23795
PR | 101 | 03/13/26 | 209 | Gerard, Jordan E | 3 | 177 | 23796
PR | 101 | 03/20/26 | 326 | Gerard, Jeffrey S | 1 | 69 | 33799
PR | 101 | 03/20/26 | 326 | Gerard, Jeffrey S | 1 | 69 | 33799
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 2 | 138 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 0.5 | 34.5 | 43803
PR | 101 | 03/27/26 | 495 | Gerard, Jordan E | 2.75 | 162.25 | 43804
PR | 101 | 03/27/26 | 495 | Gerard, Jordan E | 1.75 | 103.25 | 43804
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 0.5 | 34.5 | 13807
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 1 | 69 | 13807
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 0.5 | 34.5 | 13807
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 0.5 | 34.5 | 13807
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 1 | 69 | 13807
PR | 101 | 04/03/26 | 28 | Gerard, Jordan E | 1.25 | 73.75 | 13808
PR | 101 | 04/03/26 | 28 | Gerard, Jordan E | 2 | 118 | 13808
PR | 101 | 04/03/26 | 28 | Gerard, Jordan E | 4.75 | 280.25 | 13808
AP | 601 | 10/30/25 | 750 | Robison Engineering, Inc. |  | 55000 | 1448-001-1
PR | 995 | 09/12/25 | 131 | Gerard, Jordan E |  | 81.54
PR | 995 | 09/26/25 | 434 | Gerard, Jordan E |  | 47.57
PR | 995 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 15.63
PR | 995 | 10/24/25 | 522 | Gerard, Jordan E |  | 27.18
PR | 995 | 10/24/25 | 522 | Gerard, Jordan E |  | 27.18
PR | 995 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 31.26
PR | 995 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 12/26/25 | 528 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 12/26/25 | 529 | Gerard, Jordan E |  | 63.99
PR | 995 | 12/26/25 | 529 | Gerard, Jordan E |  | 21.33
PR | 995 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 49.06
PR | 995 | 01/02/26 | 33 | Gerard, Jordan E |  | 49.77
PR | 995 | 01/09/26 | 147 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/09/26 | 148 | Gerard, Jordan E |  | 90.89
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/23/26 | 485 | Gerard, Jordan E |  | 69.92
PR | 995 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/06/26 | 73 | Gerard, Jordan E |  | 111.86
PR | 995 | 02/06/26 | 73 | Gerard, Jordan E |  | 62.92
PR | 995 | 02/06/26 | 73 | Gerard, Jordan E |  | 41.95
PR | 995 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/13/26 | 205 | Gerard, Jordan E |  | 97.88
PR | 995 | 02/20/26 | 320 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 20.97
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 55.93
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 55.93
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 20.97
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 65.41
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 27.97
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 48.94
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 61
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/13/26 | 209 | Gerard, Jordan E |  | 78.23
PR | 995 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 61
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 15.25
PR | 995 | 03/27/26 | 495 | Gerard, Jordan E |  | 71.71
PR | 995 | 03/27/26 | 495 | Gerard, Jordan E |  | 45.64
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 15.25
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 15.25
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 15.25
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 30.5
PR | 995 | 04/03/26 | 28 | Gerard, Jordan E |  | 32.6
PR | 995 | 04/03/26 | 28 | Gerard, Jordan E |  | 52.16
PR | 995 | 04/03/26 | 28 | Gerard, Jordan E |  | 123.87
PR | 998 | 09/12/25 | 131 | Gerard, Jordan E |  | 13.77
PR | 998 | 09/26/25 | 434 | Gerard, Jordan E |  | 8.03
PR | 998 | 10/03/25 | 30 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 10/24/25 | 522 | Gerard, Jordan E |  | 4.59
PR | 998 | 10/24/25 | 522 | Gerard, Jordan E |  | 4.59
PR | 998 | 10/31/25 | 687 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 11/28/25 | 536 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 12/12/25 | 199 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 12/26/25 | 528 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 12/26/25 | 529 | Gerard, Jordan E |  | 10.33
PR | 998 | 12/26/25 | 529 | Gerard, Jordan E |  | 3.44
PR | 998 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/02/26 | 32 | Gerard, Jeffrey S |  | 7.92
PR | 998 | 01/02/26 | 33 | Gerard, Jordan E |  | 8.03
PR | 998 | 01/09/26 | 147 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/09/26 | 148 | Gerard, Jordan E |  | 14.67
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/16/26 | 293 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 01/23/26 | 484 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/23/26 | 485 | Gerard, Jordan E |  | 11.28
PR | 998 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 01/30/26 | 597 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/06/26 | 72 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/06/26 | 73 | Gerard, Jordan E |  | 18.05
PR | 998 | 02/06/26 | 73 | Gerard, Jordan E |  | 10.16
PR | 998 | 02/06/26 | 73 | Gerard, Jordan E |  | 6.77
PR | 998 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/13/26 | 204 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/13/26 | 205 | Gerard, Jordan E |  | 15.8
PR | 998 | 02/20/26 | 320 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 3.39
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 9.03
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 9.03
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 3.39
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 4.51
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 7.9
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/13/26 | 209 | Gerard, Jordan E |  | 13.54
PR | 998 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 03/27/26 | 495 | Gerard, Jordan E |  | 12.41
PR | 998 | 03/27/26 | 495 | Gerard, Jordan E |  | 7.9
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 04/03/26 | 28 | Gerard, Jordan E |  | 5.64
PR | 998 | 04/03/26 | 28 | Gerard, Jordan E |  | 9.03
PR | 998 | 04/03/26 | 28 | Gerard, Jordan E |  | 21.44
AR | 999 | 10/17/25 | 437 | Holland Acquisiton Co., LLC |  | -40000 | 038493
AR | 999 | 01/20/26 | 405 | Holland Acquisiton Co., LLC |  | -40000 | 038530