## 01 Overview
OWP #2115 · Elowen Apartments
Chinn Construction, LLC · None units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit
Forecast margin
Progress to Date
Work complete (billed) | 0
Retention held | 0
Earned less retention
Balance to finish
Percent complete
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 10407.5
PR | 2569.42
AR | 0

## 02 Job Info
Job Information
Job ID | 2115
Project name | Elowen Apartments
General contractor | Chinn Construction, LLC
Owner | North Cove Investors, LLC (Seattle, WA)
Units
Insurance | Standard (COI)
Job start | Feb 2026
Expected completion | TBD — schedule not published in budget proposal
Architect
MEP Engineer | One Way Plumbing (design-build, 2-D CAD)
Status | ACTIVE · in-progress
JDR report date | Apr 3, 2026

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0
Executed change orders (net) | 0 | 0
Total contract value
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
101 | Takeoff & Purchase Labor | 0 | 0 | 1653.75 |  | 0
601 | Engineering/Plans | 0 | 0 | 10407.5 |  | 10407.5
995 | Payroll Burden | 0 | 0 | 789.15 |  | 0
998 | Payroll Taxes | 0 | 0 | 126.52 |  | 0
TOTAL

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 1 | 0 | 1653.75
Material | 0 | 0 | 0
Overhead | 1 | 0 | 10407.5
Burden | 2 | 0 | 915.67
TOTAL

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
101 | Takeoff & Purchase Labor | 0 | 1653.75
601 | Engineering/Plans | 0 | 10407.5
995 | Payroll Burden | 0 | 789.15
998 | Payroll Taxes | 0 | 126.52

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Franklin Engineering | 10407.5 | 1
TOTAL AP

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Jordan E | 15.8 | 929 |  | LEAD/SUPERVISOR
Gerard, Jeffrey S | 10.5 | 724 |  | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 2 | 26.2 | 1654
JOURNEYMAN | 0 | 0 | 0
APPRENTICE/HELPER | 0 | 0 | 0
OT-ONLY | 0 | 0 | 0

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 26
Active workers | 2
Hours per unit (to date) | 26.2
Revenue per labor hour (billed) | 0
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34%
Roughin labor share (code 120) | 0% | 45%
Top vendor concentration | 100% | 38%
Hours per unit | 26.25 | 95

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $10,408 actual spend — needs CO or budget transfer
Top vendor concentration (Franklin Engineering) | ⚠ WATCH | 100% of AP ($10,408) — high, monitor
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 12976.92 | 12976.92
Revenue billed (AR ·-1) | 0 | 0
AP source total |  | 10407.5
PR source total |  | 2569.42
GL source total |  | 0

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · live | Initial build for #2115 live project. 17-tab JCR schema on revised budget basis.