## Summary
#2115 · Elowen Apartments
Chinn Construction, LLC · 1 units · ACTIVE · 0.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
0 | 0% | 0 | 0
Key facts
Original contract |  | 0
Revised contract (CO impact) |  | 0
Executed COs (net) |  | 0
Retention held |  | 0
Revised expense budget |  | 0
Forecast net profit |  | 0
Percent complete |  | 0%
Live signals
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $10,408 actual — needs CO or budget transfer
Top vendor (Franklin Engineering) | ⚠ WATCH | 100% of AP — high
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ⚠ WATCH | 0.0% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Franklin Engineering | 1 | 10407.5 | 100%

## Transactions
Transactions Detail
JDR source transactions for job #2115 · 55 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 101 | 02/13/26 | 205 | Gerard, Jordan E | 4 | 236 | 23778
PR | 101 | 02/13/26 | 205 | Gerard, Jordan E | 1 | 59 | 23778
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 0.75 | 44.25 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 0.5 | 29.5 | 33785
PR | 101 | 02/20/26 | 321 | Gerard, Jordan E | 1.25 | 73.75 | 33785
PR | 101 | 02/27/26 | 468 | Gerard, Jordan E | 1.25 | 73.75 | 43788
PR | 101 | 03/06/26 | 63 | Gerard, Jeffrey S | 1 | 69 | 13791
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 2.75 | 162.25 | 13792
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 1.75 | 103.25 | 13792
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 2.5 | 147.5 | 13792
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 2 | 138 | 23795
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 1 | 69 | 23795
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 1 | 69 | 23795
PR | 101 | 03/20/26 | 326 | Gerard, Jeffrey S | 1 | 69 | 33799
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 0.5 | 34.5 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 2 | 138 | 43803
PR | 101 | 03/27/26 | 494 | Gerard, Jeffrey S | 1 | 69 | 43803
AP | 601 | 03/23/26 | 399 | Franklin Engineering |  | 10407.5 | 1827
PR | 995 | 02/13/26 | 205 | Gerard, Jordan E |  | 111.86
PR | 995 | 02/13/26 | 205 | Gerard, Jordan E |  | 27.97
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 20.97
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 13.98
PR | 995 | 02/20/26 | 321 | Gerard, Jordan E |  | 34.96
PR | 995 | 02/27/26 | 468 | Gerard, Jordan E |  | 34.96
PR | 995 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 32.71
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 76.91
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 48.94
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 69.92
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 66.52
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 33.26
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 33.26
PR | 995 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 33.26
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 33.26
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 16.63
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 66.52
PR | 995 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 33.26
PR | 998 | 02/13/26 | 205 | Gerard, Jordan E |  | 18.05
PR | 998 | 02/13/26 | 205 | Gerard, Jordan E |  | 4.51
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 3.39
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 2.26
PR | 998 | 02/20/26 | 321 | Gerard, Jordan E |  | 5.64
PR | 998 | 02/27/26 | 468 | Gerard, Jordan E |  | 5.64
PR | 998 | 03/06/26 | 63 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 12.41
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 7.9
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 11.28
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/20/26 | 326 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 10.56
PR | 998 | 03/27/26 | 494 | Gerard, Jeffrey S |  | 5.28