## Summary
#2117 · Lachlan Apartments
Ravenna Partners · 104 units · ACTIVE · 0.0% billed
REV. CONTRACT | FORECAST MARGIN | BILLED TO DATE | BALANCE TO FINISH
0 | 0% | 0 | 0
Key facts
Original contract |  | 0
Revised contract (CO impact) |  | 0
Executed COs (net) |  | 0
Retention held |  | 0
Revised expense budget |  | 0
Forecast net profit |  | 0
Percent complete |  | 0%
Live signals
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $10,701 actual — needs CO or budget transfer
Top vendor (Franklin Engineering) | ⚠ WATCH | 100% of AP — high
Retention | ✓ OK | $344,993 held · 5% standard
Forecast margin | ⚠ WATCH | 0.0% forecast — monitor
Top vendors (AP)
Vendor | Invoices | Spend | % of AP
Franklin Engineering | 2 | 10701.25 | 100%

## Transactions
Transactions Detail
JDR source transactions for job #2117 · 17 rows
Src | Code | Post Date | Ref | Party | Hours | Amount | Check#
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 0.5 | 34.5 | 43787
PR | 101 | 02/27/26 | 467 | Gerard, Jeffrey S | 0.5 | 34.5 | 43787
PR | 101 | 03/06/26 | 64 | Gerard, Jordan E | 1 | 59 | 13792
PR | 101 | 03/13/26 | 208 | Gerard, Jeffrey S | 0.5 | 34.5 | 23795
PR | 101 | 04/03/26 | 27 | Gerard, Jeffrey S | 0.5 | 34.5 | 13807
AP | 601 | 02/20/26 | 367 | Franklin Engineering |  | 2768.75 | 1811
AP | 601 | 03/23/26 | 400 | Franklin Engineering |  | 7932.5 | 1826
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 16.35
PR | 995 | 03/06/26 | 64 | Gerard, Jordan E |  | 27.97
PR | 995 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 16.63
PR | 995 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 16.63
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 02/27/26 | 467 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 03/06/26 | 64 | Gerard, Jordan E |  | 4.51
PR | 998 | 03/13/26 | 208 | Gerard, Jeffrey S |  | 2.64
PR | 998 | 04/03/26 | 27 | Gerard, Jeffrey S |  | 2.64