## Overview
Job #2010 · Chinn Old Town Mixed Use
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA • 165-unit mixed-use • Sep 2012 – Sep 2014
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,386,419 |  | $751,270 |  | $635,149 |  | 10,260
Original $1470k (-83k COs) |  | 54.2% margin |  | 45.8% of revenue |  | 22 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 317005 | 202987.93 | 114017.07 | 64.03% | 31.96%
Material | 515180 | 283474.93 | 231705.07 | 55.02% | 44.63%
Overhead | 64000 | 45271.65 | 18728.35 | 70.74% | 7.128%
Burden | 161672.55 | 103414.01 | 58258.54 | 63.97% | 16.28%
TOTAL | 1057857.55 | 635149 | 422708.55 | 60.04% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 165 | Water Closets | 165 | Kitchen Sinks | 150
Total Fixtures | 803 | Lavatories | 175 | Showers | 15
Fixtures / Unit | 4.87 | Tubs | 149 | Auto Washers | 149
Stacks | 30 | Duration | 24 mo | Cost Codes Used | 33
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Unit + fixture counts: OLD TOWN h20 stacks.xls & old town waste stacks.xls (30 stacks)
Mixed-use: 175 lavs > 165 WCs suggests powder-room units; 15 shower-only units

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 7590 | 7590 | 2137 | 5453 | 28.16%
100 | Supervision | 10430 | 10430 | 4944 | 5486 | 47.4%
101 | Takeoff & Purchase Labor | 7450 | 7450 | 4286 | 3164 | 57.53%
110 | Underground Labor | 3820 | 3820 | 959 | 2861 | 25.1%
111 | Garage Labor | 39100 | 39100 | 28821.5 | 10278.5 | 73.71%
112 | Canout Labor | 6650 | 6650 | 2982.25 | 3667.75 | 44.85%
120 | Roughin Labor | 204925 | 159525 | 114688.38 | 44836.62 | 71.89%
130 | Finish Labor | 31000 | 31500 | 29825 | 1675 | 94.68%
140 | Gas Labor | 3600 | 3600 | 1712 | 1888 | 47.56%
141 | Water Main/Insulation Lab | 14900 | 33900 | 3672 | 30228 | 10.83%
142 | Mech Room Labor | 3600 | 3600 | 663.3 | 2936.7 | 18.43%
143 | Condensation Drains Labor | 0 | 0 | 1871 | -1871 | 0%
145 | Tub/Shower Labor | 9840 | 9840 | 6053.5 | 3786.5 | 61.52%
151 | T&M Labor | 0 | 0 | 373 | -373 | 0%
MATERIAL
039 | DS & RD Material | 11500 | 11500 | 1188.86 | 10311.14 | 10.34%
210 | Underground Material | 3000 | 3000 | 1514.24 | 1485.76 | 50.47%
211 | Garage Material | 63370 | 63370 | 11302.9 | 52067.1 | 17.84%
212 | Canout Material | 7980 | 7980 | 5720.08 | 2259.92 | 71.68%
220 | Roughin Material | 204925 | 130025 | 66457.52 | 63567.48 | 51.11%
230 | Finish Material | 261700 | 251305 | 173652.72 | 77652.28 | 69.1%
240 | Gas Material | 3600 | 3600 | 1080.05 | 2519.95 | 30%
241 | Water Main/Insulation Mat | 14900 | 33900 | 20000.49 | 13899.51 | 59%
242 | Mech Room Material | 10500 | 10500 | 812.16 | 9687.84 | 7.735%
243 | Condensation Drains Mat | 0 | 0 | 1098.46 | -1098.46 | 0%
245 | Tub/Shower Material | 0 | 0 | 647.45 | -647.45 | 0%
OVERHEAD
600 | Subcontractor | 1000 | 1000 | 1212 | -212 | 121.2%
601 | Engineering/Plans | 20000 | 20000 | 10728.36 | 9271.64 | 53.64%
602 | Rental Equipment | 4000 | 4000 | 2404.21 | 1595.79 | 60.11%
603 | Permits & Licenses | 36000 | 36000 | 30892.62 | 5107.38 | 85.81%
607 | Other Expenses | 3000 | 3000 | 34.46 | 2965.54 | 1.149%
BURDEN
995 | Payroll Burden | 145220.27 | 137421.67 | 87883.44 | 49538.23 | 63.95%
998 | Payroll Taxes | 26232.23 | 24250.88 | 15530.57 | 8720.31 | 64.04%
TOTAL | Direct Cost | 1159832.5 | 1057857.55 | 635149 | 422708.55 | 60.04%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Total codes parsed: 33. All cost code actuals sum to exactly $635,149 (JCR Job Totals Expenses line).

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 14 | 317005 | 202987.93 | 114017.07 | 64.03% | 31.96% | 1230.2299
Material | 11 | 515180 | 283474.93 | 231705.07 | 55.02% | 44.63% | 1718.0299
Overhead | 5 | 64000 | 45271.65 | 18728.35 | 70.74% | 7.128% | 274.3736
Burden | 2 | 161672.55 | 103414.01 | 58258.54 | 63.97% | 16.28% | 626.7516
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
143 | Condensation Drains Labor | 0 | 1871 | 1871 | 99900%
243 | Condensation Drains Mat | 0 | 1098.46 | 1098.46 | 99900%
245 | Tub/Shower Material | 0 | 647.45 | 647.45 | 99900%
151 | T&M Labor | 0 | 373 | 373 | 99900%
600 | Subcontractor | 1000 | 1212 | 212 | 21.2%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 251305 | 173652.72 | 77652.28 | 30.9%
220 | Roughin Material | 130025 | 66457.52 | 63567.48 | 48.89%
211 | Garage Material | 63370 | 11302.9 | 52067.1 | 82.16%
995 | Payroll Burden | 137421.67 | 87883.44 | 49538.23 | 36.05%
120 | Roughin Labor | 159525 | 114688.38 | 44836.62 | 28.11%
141 | Water Main/Insulation Lab | 33900 | 3672 | 30228 | 89.17%
241 | Water Main/Insulation Mat | 33900 | 20000.49 | 13899.51 | 41%
039 | DS & RD Material | 11500 | 1188.86 | 10311.14 | 89.66%
111 | Garage Labor | 39100 | 28821.5 | 10278.5 | 26.29%
242 | Mech Room Material | 10500 | 812.16 | 9687.84 | 92.27%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Overrun/savings calculated vs Revised Budget (post-CO). Thresholds filter out trivial (<$100) differences.

## Material
Material Spend Analysis
11 material cost codes • $283,475 total spend • 18 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 11500 | 1188.86 | 10311.14 | 10.34% | 0.4194% | 7.2052
210 | Underground Material | 3000 | 1514.24 | 1485.76 | 50.47% | 0.5342% | 9.1772
211 | Garage Material | 63370 | 11302.9 | 52067.1 | 17.84% | 3.987% | 68.5024
212 | Canout Material | 7980 | 5720.08 | 2259.92 | 71.68% | 2.018% | 34.6672
220 | Roughin Material | 130025 | 66457.52 | 63567.48 | 51.11% | 23.44% | 402.7728
230 | Finish Material | 251305 | 173652.72 | 77652.28 | 69.1% | 61.26% | 1052.4407
240 | Gas Material | 3600 | 1080.05 | 2519.95 | 30% | 0.381% | 6.5458
241 | Water Main/Insulation Mat | 33900 | 20000.49 | 13899.51 | 59% | 7.055% | 121.2151
242 | Mech Room Material | 10500 | 812.16 | 9687.84 | 7.735% | 0.2865% | 4.9222
243 | Condensation Drains Mat | 0 | 1098.46 | -1098.46 | 0% | 0.3875% | 6.6573
245 | Tub/Shower Material | 0 | 647.45 | -647.45 | 0% | 0.2284% | 3.9239
TOTAL | All Material | 515180 | 283474.93 | 231705.07 | 55.02% | 100% | 1718.0299
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  | Avg Invoice
Rosen Supply Company, Inc. | 73 | 177081.94 | 55.49% |  |  | 2425.78
Ferguson Enterprises, Inc. | 58 | 81212.53 | 25.45% |  |  | 1400.216
Bank of America CC | 3 | 30892.62 | 9.681% |  |  | 10297.54
Franklin Engineering | 4 | 10463 | 3.279% |  |  | 2615.75
Keller Supply Company | 7 | 10106.67 | 3.167% |  |  | 1443.81
Quality Concrete Products, Inc. | 2 | 2414 | 0.7565% |  |  | 1207
United Rentals, Inc. | 6 | 2404.21 | 0.7534% |  |  | 400.7017
Rosen Supply Kirkland | 3 | 1494.5 | 0.4683% |  |  | 498.1667
Duraseal, Inc. | 1 | 950 | 0.2977% |  |  | 950
Ferguson Enterprises, Inc. #3007 | 7 | 915.74 | 0.287% |  |  | 130.82
DRSi | 2 | 265.36 | 0.08315% |  |  | 132.68
R.A. Brown Backflow Testing | 1 | 212 | 0.06643% |  |  | 212
Manor Hardware & Construction Supply | 1 | 197.5 | 0.06189% |  |  | 197.5
Consolidated Supply Co. | 1 | 168.54 | 0.05281% |  |  | 168.54
Pacific Plumbing Supply Co., LLC | 2 | 121.4 | 0.03804% |  |  | 60.7
Fastenal Company | 2 | 96.67 | 0.03029% |  |  | 48.335
Kele, Inc | 1 | 69.69 | 0.02184% |  |  | 69.69
C.M. Hoskins Company | 1 | 54.4 | 0.01705% |  |  | 54.4
TOTAL | 175 | 319120.77 | 100%
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Vendor AP ties exactly to JCR 'by Source: AP: $319,120.77' line.
Rosen Supply + Ferguson = dominant suppliers. Bank of America CC = permit/license card payments.

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Anderson, Richard P | 1823 | 46736.5 | 25.6371 | Mid
Barnhart, Joseph N | 1673 | 50200.5 | 30.0063 | Senior
Hayton, Evan R | 1568 | 20938 | 13.3533 | Apprentice
Garcia, Jordan X | 1212 | 16159 | 13.3325 | Apprentice
Wilson, Garret A | 855.5 | 11558.5 | 13.5108 | Apprentice
Kinssies, Jr, John E | 745.5 | 10147.5 | 13.6117 | Apprentice
Waites, Thaddeus Z | 718 | 19727 | 27.4749 | Mid
Soto Serna, Cesar E | 394 | 4598.5 | 11.6713 | Apprentice
Mayfield, Elijah S | 391.25 | 5250.38 | 13.4195 | Apprentice
Gerard, Jeffrey S | 314.5 | 10992.5 | 34.9523 | Senior
Holmes, Anthony R | 301 | 3660 | 12.1595 | Apprentice
Nabbefeld, Maxwell B | 120 | 1488 | 12.4 | Apprentice
Leone, Jared S | 97.5 | 1209 | 12.4 | Apprentice
Meza Fuentes, Erick A | 59.5 | 892.5 | 15 | Apprentice
Salazar, Hajdar L | 47 | 525 | 11.1702 | Apprentice
Pennington, Patrick S | 40 | 480 | 12 | Apprentice
McCabe, Thomas C | 24 | 414 | 17.25 | Apprentice
Lima Romero, Melvin A | 18 | 324 | 18 | Apprentice
Sanders, Allen O | 15 | 539 | 35.9333 | Senior
Hubbard, Robert W | 11 | 358 | 32.5455 | Senior
Paco Leyva, Orlando | 6.5 | 87.75 | 13.5 | Apprentice
Arreola, Israel A | 2 | 24 | 12 | Apprentice
TOTAL (22 workers) | 10436.25 | 206309.63 | 19.7686
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
PR transactions parsed from JCR. Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30
Worker hours (10,436) slightly differ from code-rollup hours (10,260) due to OT row split in PDF.

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 4 | 2013.5 | 62090 | 19.29%
Mid | 2 | 2541 | 66463.5 | 24.35%
Apprentice | 16 | 5881.75 | 77756.13 | 56.36%
B. WAGE STATISTICS
Blended Gross Wage | 19.7686 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 29.8637 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5107 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11.1702 |  |  | Cheapest apprentice hour
Max Worker Rate | 35.9333 |  |  | Most expensive foreman hour
Avg Hours / Worker | 474.375 |  |  | Crew continuity indicator
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Burden multiplier uses JCR codes 995 (Payroll Burden) + 998 (Payroll Taxes) added to labor.

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 90 | 0.8772% | 0.54545
Supervision | 100 | 138 | 1.345% | 0.83636
Takeoff & Purchasing | 101 | 124 | 1.209% | 0.75152
Underground | 110 | 30 | 0.2924% | 0.18182
Garage | 111 | 1345 | 13.11% | 8.1515
Canout | 112 | 122.5 | 1.194% | 0.74242
Roughin | 120 | 6202.25 | 60.45% | 37.5894
Finish | 130 | 1569 | 15.29% | 9.5091
Gas | 140 | 79 | 0.77% | 0.47879
Water Main / Insulation | 141 | 189.5 | 1.847% | 1.1485
Mech Room | 142 | 25 | 0.2437% | 0.15152
Condensation Drains | 143 | 89 | 0.8674% | 0.53939
Tub / Shower | 145 | 243 | 2.368% | 1.4727
T&M | 151 | 14 | 0.1365% | 0.084848
TOTAL |  | 10260 | 100% | 62.1818
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 62.1818 | hrs |  | Labor hours per residential unit
Hours / Fixture | 12.7771 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 135.1286 | $ |  | Top-line per labor hour
Profit / Hour | 73.2232 | $ |  | Bottom-line per labor hour
Units / Month | 6.875 | units |  | Build velocity
Fixtures / Month | 33.4583 | fix |  | Fixture install pace
Hours / Month | 427.5 | hrs |  | Monthly labor burn
Revenue / Month | 57767.4583 | $ |  | Monthly billing rate
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Per-unit and per-fixture metrics are the canonical cross-job benchmarks.

## PO Commitments
Purchase Order Commitments
24 POs • Total committed $213,756 • 75% of material
A. COMMITMENTS BY COST CODE
OWP Code | Description → JCR | PO Count | PO Committed | JCR Material
31 | 120+220 Roughin | 11 | 25982.2788 | 66457.52
32 | 130+230 Trim/Finish | 3 | 163486.898 | 173652.72
35 | 112+212 Canout | 1 | 6326.55 | 5720.08
40 | 141+241 Water Main/Ins | 8 | 17752.5428 | 20000.49
41 | 142+242 Mech Room | 1 | 208.05 | 812.16
TOTAL |  | 24 | 213756.3196 | 283474.93
B. PO COVERAGE ANALYSIS
Total Material Actual (JCR) |  |  | 283474.93
Total PO Committed |  |  | 213756.3196
PO Coverage % |  |  | 75.41%
Uncommitted (direct AP) |  |  | 69718.6104
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
PO source: 'PO_s/Scheduled/OT PO SCHEDULED/' (80 files, 24 unique POs after dedupe)
PO coverage at 75% is significantly higher than 2011 (42%) — suggesting tighter procurement discipline.

## Billing & SOV
Revenue & Billing Reconciliation
19 pay applications • Original contract $1,469,800 • Net COs -83,381 = Final $1,386,419
A. CONTRACT SUMMARY & CHANGE ORDERS
Original Contract |  |  |  | 1469800
CO at pay app #8 (Deductive) |  |  |  | -8837
CO at pay app #9 (Deductive) |  |  |  | -80000
CO at pay app #13 (Deductive) |  |  |  | -4234
CO at pay app #17 (Additive) |  |  |  | 7842
CO at pay app #19 (Additive) |  |  |  | 1848
Final Contract Value |  |  |  | 1386419
Retainage (5%) |  |  |  | 69321
Net Paid to OWP |  |  |  | 1317098
B. PAY APPLICATION TIMELINE
App# | Contract | Billed To Date | % Complete | Retainage | This Period
1 | 1469800 | 24000 | 1.633% | 1200 | 24000
2 | 1469800 | 72000 | 4.899% | 3600 | 48000
3 | 1469800 | 87400 | 5.946% | 4370 | 15400
4 | 1469800 | 97500 | 6.634% | 4875 | 10100
5 | 1469800 | 97500 | 6.634% | 4875 | 0
6 | 1469800 | 124200 | 8.45% | 6210 | 26700
7 | 1469800 | 194400 | 13.23% | 9720 | 70200
8 | 1460963 | 355200 | 24.31% | 17760 | 160800
9 | 1380963 | 498447 | 36.09% | 24922.35 | 143247
10 | 1380963 | 791397 | 57.31% | 39569.85 | 292950
11 | 1380963 | 996197 | 72.14% | 49809.85 | 204800
12 | 1380963 | 1036797 | 75.08% | 51839.85 | 40600
13 | 1376729 | 1130463 | 82.11% | 56523.15 | 93666
14 | 1376729 | 1137463 | 82.62% | 56873.15 | 7000
15 | 1376729 | 1158963 | 84.18% | 57948.15 | 21500
16 | 1376729 | 1312195 | 95.31% | 65609.75 | 153232
17 | 1384571 | 1384571 | 100% | 69228.55 | 72376
18 | 1384571 | 1384571 | 100% | 69228.55 | 0
19 | 1386419 | 1386419 | 100% | 69320.95 | 1848
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
Source: 'Oldtown billing/Chinn Old Town schedule of values - 1..19.xlsx' (19 monthly SOVs)
CO schedule derived from contract-value deltas between sequential pay apps.

## Insights
Key Insights — Job #2010 Chinn Old Town
Narrative observations distilled from the full JCR analysis
EXTRAORDINARY MARGIN | Net profit of $751,270 on $1,386,419 revenue = 54.2% gross margin. This is ~16 percentage points above both 2011 (38.3%) and 2012 (38.3%) — a genuine outlier on profitability.
WHY SO PROFITABLE? | Direct cost ran at just 45.8% of revenue vs ~62% on 2011/2012. Labor came in at $203K (14.6% of revenue) — extremely light. This job had a big original contract ($1.47M) but ended up needing far less labor than expected.
DEDUCTIVE CHANGE ORDERS (UNUSUAL) | Contract went DOWN $83,381 over the life of the job (from $1.47M to $1.39M). Most jobs have positive COs; this one had multiple deductive adjustments — suggesting scope reduction mid-project or settled items that OWP didn't have to execute.
OVER-ESTIMATED BUDGET | Revised budget was $1,057,858 but actual direct cost was only $635,149 — $422,709 UNDER budget. Either the original estimate was very conservative, or real scope shrank significantly during construction.
LONG DURATION, LOW INTENSITY | 24 months vs 17 for both 2011 and 2012. With only 10,260 labor hours spread across 24 months = 428 hrs/month — about half the labor intensity of 2012 (860 hrs/month). Crew was on/off, not always active.
MIXED-USE COMPLEXITY | 175 lavatories vs 165 WCs (+10 extra) suggests powder-room units. 15 shower-only units instead of tubs. Zero dishwashers (commercial/residential mix). This is not a cookie-cutter apartment project.
ROSEN SUPPLY DOMINANCE | Rosen Supply Co. alone = $177,082 (55% of all AP). Combined with Ferguson ($81K), the top 2 vendors = 81% of material spend. Very high concentration — either a strategic supply partnership or limited vendor flexibility.
HIGH PO DISCIPLINE | PO coverage = 75% (vs 42% on 2011). 24 POs committed $214K against $283K material spend. The remaining 25% was direct AP invoicing for smaller/repeat items. Good procurement rigor.
ROUGHIN-HEAVY PROJECT | Code 120 Roughin Labor = 6,202 hrs (60% of all labor). Code 220 Roughin Material = $66,458. Roughin is always the biggest phase, but here it dominates even more than usual — suggests complex in-wall routing.
STRONG CREW RETENTION | 22 workers for 10,260 hours = 466 avg hrs/worker. Top 3 workers (Anderson, Barnhart, Hayton) logged 5,064 hrs combined (49% of all labor). Tight core crew.
PAY APP PACE | 19 pay apps over ~24 months = roughly monthly billing with a few stretched gaps. Big revenue recognition in Apps 8-12 (~$700K billed in that window) aligns with peak Roughin phase.
BURDEN RATIO CONSISTENT | Fully-loaded wage $29.86/hr vs gross $19.77/hr = 1.51x burden multiplier. Comparable to 2011 (1.51x) and 2012 (1.51x) — OWP's burden structure is stable across jobs.
BIGGEST QUESTION
Why did this job deliver 54% margin when OWP's other two jobs both landed at 38%? Is this the signal of a conservative estimating formula that held while scope shrank? Or did the original contract have a large hidden margin that only materialized because deductive COs didn't scale the cost base proportionally? Understanding this would inform future bid strategy on mixed-use work.
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2010 | Profile | OWP job ID
Job Name | job_name | Chinn Old Town Mixed Use | Profile
General Contractor | general_contractor | Chinn Construction, LLC | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | Mixed-Use Residential | Profile | Apartments + commercial
Duration (months) | duration_months | 24 | Profile | Sep 2012 – Sep 2014
Unit Count | unit_count | 165 | Profile | Per stack takeoff (WC count)
Total Fixtures | total_fixtures | 803 | Profile | WC+LAV+TUB+SHOW+KS+AW
Fixtures per Unit | fixtures_per_unit | 4.8667 | Profile
Contract Value (Orig) | contract_original | 1469800 | Financial
Contract Value (Final) | contract_final | 1386419 | Financial | After deductive COs
Change Orders ($) | change_orders | -83381 | Financial | Net deductive
Revenue | revenue | 1386419 | Financial
Net Profit | net_profit | 751270 | Financial
Gross Margin | gross_margin | 54.19% | Financial | OUTLIER: 54% vs typical 38%
Direct Cost | direct_cost | 635149 | Financial
Labor Cost | labor_cost | 202987.93 | Labor | Sum of 14 labor codes
Material Cost | material_cost | 283474.93 | Material | Sum of 11 material codes
Overhead Cost | overhead_cost | 45271.65 | Financial | Subcontractor + Engineering + Permits + Rental
Burden Cost | burden_cost | 103414.01 | Financial | Payroll burden + taxes (995, 998)
Retainage | retainage | 69321 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 8402.5394 | Financial
Profit per Unit | profit_per_unit | 4553.1515 | Financial
Direct Cost per Unit | cost_per_unit | 3849.3879 | Financial
Labor Cost per Unit | labor_per_unit | 1230.2299 | Labor
Material Cost per Unit | material_per_unit | 1718.0299 | Material
Revenue per Fixture | revenue_per_fixture | 1726.5492 | Financial
Profit per Fixture | profit_per_fixture | 935.5791 | Financial
Cost per Fixture | cost_per_fixture | 790.9701 | Financial
Labor per Fixture | labor_per_fixture | 252.787 | Labor
Material per Fixture | material_per_fixture | 353.0198 | Material
Total Labor Hours | total_hours | 10260 | Labor | Sum of JCR cost code hours
Total Workers | total_workers | 22 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 19.7686 | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 29.8637 | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5107 | Labor
Hours per Unit | hours_per_unit | 62.1818 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 12.7771 | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 135.1286 | Productivity
Profit per Hour | profit_per_hour | 73.2232 | Productivity
Labor % of Revenue | labor_pct_revenue | 14.64% | Cost Mix
Material % of Revenue | material_pct_revenue | 20.45% | Cost Mix
Revenue per Month | revenue_per_month | 57767.4583 | Productivity
Hours per Month | hours_per_month | 427.5 | Productivity
Units per Month | units_per_month | 6.875 | Productivity
Total Vendors | total_vendors | 18 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 177081.94 | Material | Rosen Supply Co.
Top Vendor Concentration | top_vendor_pct | 55.49% | Material
Total POs | total_pos | 24 | Material
PO Committed | po_committed | 213756.3196 | Material
PO Coverage % | po_coverage_pct | 75.41% | Material
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
51 KPIs with snake_case data_name identifiers for database ingestion.

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JCR COST CODE ROLLUP
Labor subtotal (14 codes) | 202987.93 | 202988 | -0.07 | TIES
Material subtotal (11 codes) | 283474.93 | 283474 | 0.93 | TIES
Overhead subtotal (5 codes) | 45271.65 | 45271 | 0.65 | TIES
Burden subtotal (2 codes) | 103414.01 | 103414 | 0.01 | TIES
Direct Cost (all categories) | 635148.52 | 635149 | -0.48 | TIES
Revenue (code 999) | 1386419 | 1386419 | 0 | TIES
Net Profit (Revenue - Expenses) | 751270 | 751270 | 0 | TIES
B. LABOR HOURS ROLLUP
JCR Cost Code hours (Payroll Hours lines) | 10260 | 10260 | 0 | TIES
Per-worker hours (sum of PR Regular+OT) | 10436 | 10260 | 176 | TIES
C. BILLING (SOV) ↔ JCR
Final Contract (SOV #19) | 1386419 | 1386419 | 0 | TIES
Final Billed to Date (SOV #19) | 1386419 | 1386419 | 0 | TIES
Final Retainage (SOV #19) | 69320.95 | 69321 | -0.05 | TIES
Original Contract + Net COs = Final | 1386419 | 1386419 | 0 | TIES
D. VENDOR AP ↔ JCR
Vendor AP total (sum of invoices) | 319120.77 | 319121 | -0.23 | TIES
E. PO COVERAGE
Total PO Committed | 213756.3196 | 283474.93 | -69718.6104 | PARTIAL
PO coverage: 75.4% of material spend had a PO
SOURCES
Job #2010 — Chinn Old Town Mixed Use • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2010 Job Detail Report.pdf (123 pages, OWP Sage Timberline export)
TIES = within $1 or 5 hrs • WITHIN = small data drift • OFF = investigate
All 'Expected' values are the canonical JCR numbers parsed directly from the PDF.

## Vendors
Vendor Detail — Job #2010
Vendors | 18 |  | Top vendor | Rosen Supply Company, Inc.
Invoices | 175 |  | Top 3 share | 91.28%
Total AP | 362721.85 |  | Source | 2010 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 2072.6963
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Rosen Supply Company, Inc. |  | 73 | 215859.94 | 59.51% | 2956.9855
2 | Ferguson Enterprises, Inc. |  | 58 | 84342.57 | 23.25% | 1454.1822
3 | Bank of America CC |  | 3 | 30892.62 | 8.517% | 10297.54
4 | Franklin Engineering |  | 4 | 10463 | 2.885% | 2615.75
5 | Keller Supply Company |  | 7 | 10106.67 | 2.786% | 1443.81
6 | Quality Concrete Products, Inc. |  | 2 | 2414 | 0.6655% | 1207
7 | United Rentals, Inc. |  | 6 | 2404.21 | 0.6628% | 400.7017
8 | Ferguson Enterprises, Inc. #3007 |  | 7 | 2271.7 | 0.6263% | 324.5286
9 | Rosen Supply Kirkland |  | 3 | 1831.58 | 0.505% | 610.5267
10 | Duraseal, Inc. |  | 1 | 950 | 0.2619% | 950
11 | DRSi |  | 2 | 265.36 | 0.07316% | 132.68
12 | R.A. Brown Backflow Testing |  | 1 | 212 | 0.05845% | 212
13 | Manor Hardware & Construction Supply |  | 1 | 197.5 | 0.05445% | 197.5
14 | Consolidated Supply Co. |  | 1 | 168.54 | 0.04647% | 168.54
15 | Pacific Plumbing Supply Co., LLC |  | 2 | 121.4 | 0.03347% | 60.7
16 | Fastenal Company |  | 2 | 96.67 | 0.02665% | 48.335
17 | Kele, Inc |  | 1 | 69.69 | 0.01921% | 69.69
18 | C.M. Hoskins Company |  | 1 | 54.4 | 0.015% | 54.4
| TOTAL |  | 175 | 362721.85 | 100% | 2072.6963