## Overview
Job #2117 · Lachlan Apartments
Cortex JCR Summary • Ravenna Partners (Owner: Ravenna Partners (owner-GC · self-developing))
PROJECT OVERVIEW
Project Job # | 2117
Project Name: | Lachlan Apartments
General Contractor | Ravenna Partners (Owner: Ravenna Partners (owner-GC · self-developing))
Location | 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford)
Project Duration | TBD · pending Ravenna acceptance of Nov 19 2025 BID – TBD (Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025)
Status | ACTIVE · pre-construction · final BID submitted
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,948,000 |  | $1,936,993 |  | $11,007 |  | 3
$2,610,000 orig + $-662,000 COs |  | 99.4% margin |  | 0.6% of revenue |  | 2 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 0 | 197 | -197 | 0 | 0.017897
Material | 0 | 0 | 0 | 0 | 0
Overhead | 0 | 10701.25 | -10701.25 | 0 | 0.9722
Burden | 0 | 109 | -109 | 0 | 0.0099026
TOTAL | 0 | 11007.25 | -11007.25 | 0 | 1
PROJECT PROFILE
Plumbing Units | 104 | Total Fixtures | 425 trim fixtures (verified Nov 19 2025 bid sheet ESTIMATE tab + proposal RESIDENT UNIT TRIM block) | Fixtures / Unit | 4.09
GC | Ravenna Partners | Owner | Ravenna Partners (owner-GC · self-developing) | Insurance | Standard COI
Status | ACTIVE · pre-construction · final BID submitted | Duration | Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025 | Permit | Pre-permit · plumbing permit submittal pending Ravenna acceptance
NARRATIVE
Pre-construction project — Ravenna Partners' FIRST OWP engagement, owner-GC pattern. OWP has pursued the Lachlan Apartments site at 3421 Woodland Park Ave N (Lower Woodland / Wallingford) for 23 months across 3 budget rounds: 1st Budget Dec 15 2023 ($2,610,000 / 122 units, submitted under Blueprint as GC); 2nd Budget Oct 17 2024 ($2,100,000 / 100 units, -19.5%, also Blueprint era); 3rd Budget FINAL Nov 19 2025 ($1,948,000 / 104 units / 425 trim, Ravenna Partners as new owner-GC, -7.2% from 2nd). Net -$662k (-25.4%) and -18 units across the 3-bid arc — owner repeatedly tightened scope to hit pro-forma. Owner contact Andrew Withnell. OWP design-build MEP is Franklin Engineering ($10,701 / 97% of $11k AP = standard pre-permit design fees). $0 billed against $11,007 sunk cost = -$11,007 carrying loss (tiny relative to $1.95M bid · standard 23-month pursuit posture). 2 OWP estimators (Jeffrey + Jordan Gerard) logged 3.0 hours YTD. Verified fixture profile from Nov 19 2025 bid sheet + proposal: 425 trim across 104 toilets (Gerber Maxwell GWS20912/20918) + 104 lavs (Kohler K-2035-1 + matte black Peerless trim) + 53 tubs (Sterling 71121110 Vikrell) + 51 showers (Sterling 95077) + 104 kitchen sinks (Peerless P7946LF-BL) + amenity/common/specialty (1 drinking fountain + 1 mop sink + 1 coffee maker connection + 2 Toto common WCs + 2 Kohler common lavs + 2 Kohler amenity sinks). Plus 535 RI total (106 DW + 104 icemaker + 104 washer + 104 condensate drains + 208 water spacer tubes/meters). Heat source: 3 gas boilers (199mbh × 100-gal AO Smith/Rinnai/Bock vertical) + B&G recirc + Heat Timer mixing valve. Owner-GC pattern means lean PM teams, price-sensitive negotiation, schedule-focused — expect tight CO scrutiny once subcontract executes. Forecast 24% margin once mobilized.
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
101 | Takeoff & Purchase Labor | 0 | 0 | 197 | -197 | 0
OVERHEAD
601 | Engineering/Plans | 0 | 0 | 10701 | -10701 | 0
BURDEN
995 | Payroll Burden | 0 | 0 | 94 | -94 | 0
998 | Payroll Taxes | 0 | 0 | 15 | -15 | 0
TOTAL Direct Cost |  | 11007.25 | 11007.25 | 11007.25
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 1 | 0 | 197 | -197 | 0 | 0.017898
Material | 0 | 0 | 0 | 0 | 0 | 0
Overhead | 1 | 0 | 10701 | -10701 | 0 | 0.9722
Burden | 2 | 0 | 109 | -109 | 0 | 0.0099028
Revenue | 0 | 0 | 0 | 0 | 0 | 0
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
601 | Engineering/Plans | 0 | 10701 | 10701 | 0
101 | Takeoff & Purchase Labor | 0 | 197 | 197 | 0
995 | Payroll Burden | 0 | 94 | 94 | 0
998 | Payroll Taxes | 0 | 15 | 15 | 0
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Material
Material Spend Analysis
0 material cost codes • $0 JDR material • 1 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Franklin Engineering | 2 | 10701 | 1
TOTAL | 2 | 10701 | 1
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gerard, Jeffrey S | 2 | 138 | 69 | Tier 1 (Estimator/Mgr)
Gerard, Jordan E | 1 | 59 | 59 | Tier 1 (Sr Estimator)
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Tier 1 (Estimator) | 2 | 3 | 100 | Senior estimating leadership · takeoff phase%
B. WAGE STATISTICS
Blended labor rate ($/hr) | —
Foreman labor rate ($/hr) | —
Burden multiplier | —
Min wage ($/hr) | —
Max wage ($/hr) | —
Avg hours per worker | —
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
TOTAL |  | 11007
PRODUCTIVITY RATIOS
Revenue per unit | $18,731
Direct cost per unit | $106
Hours per unit | 105.84
Revenue per hour | $177
Profit per hour | $176
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Franklin Engineering | 2 | 10701 | 100.0% | Top 5
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $1,948,000
Net Change Orders | $0
Final Contract | $1,948,000
Retainage Held | $0
Net Paid to OWP | $0
PAY APPLICATION HISTORY
No pay-app history in dashboard. Source: Sage AR module aggregate only.
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Pre-construction · $0 billed against $11,007 sunk design cost = -$11,007 carrying loss. Forecast 24% margin once Ravenna accepts Nov 19 2025 BID and field work mobilizes (industry benchmark for new owner-GC relationship).
2 | VENDOR CONCENTRATION | Franklin Engineering (OWP design-build MEP) = $10,701 (100% of $11,007 AP) across 2 design invoices. Only 1 AP vendor active — design-only phase has not yet engaged supply houses.
3 | CREW PROFILE | 2 OWP estimators logged 3.0 hours YTD: Jeffrey Gerard 2.0 hrs + Jordan Gerard 1.0 hr (takeoff). $197 labor base — virtually all takeoff/refinement work in design phase.
4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = 0 hrs / $0 actual (pre-mobilization). Code 101 Takeoff & Purchase Labor = 3.0 hrs / $197 — the only OWP labor activity to date.
5 | BUDGET DELIVERY | Final BID Nov 19 2025 = $1,948,000 (104 units · $18,731/unit · $4,584/trim fixture). 23-month bid pursuit since Dec 2023: 122u/$2.61M → 100u/$2.10M → 104u/$1.95M (-25% net).
6 | CONTRACT GROWTH | Bid trajectory: $2,610,000 (Dec 15 2023 1st Budget · Blueprint GC) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna Partners · -7.2%). Net -$662k (-25.4%) and -18 units across 3 bids.
7 | BURDEN RATIO | Burden codes 995 + 998 = $109 on $197 labor base = 55.3%. Slightly above OWP's typical 48-50% — design-phase labor with no field crew yet skews ratio.
8 | PROJECT SCALE | 104 units · 425 trim fixtures (verified Nov 19 2025 bid sheet) = 4.09 fixtures/unit. 535 RI fixtures · 705 permit fixtures. Revenue/unit $0 (pre-billing), hours/unit 0.03 takeoff. Ravenna Partners' 1st OWP engagement.
9 | PRODUCTIVITY | Blended labor rate $65.67/hr in design phase. Revenue/hour $0 (pre-billing). Profit/hour $-3,669 (carrying loss on tiny labor base). Field productivity benchmarks pending Ravenna acceptance.
10 | CO PROFILE | 0 executed COs (pre-construction). Bid revisions across 3 budget rounds (Dec 2023 → Nov 2025) not classified as COs. CO pipeline opens upon Ravenna acceptance.
11 | FIXTURE DENSITY | 425 trim fixtures ÷ 104 units = 4.09 fixtures/unit (verified Ravenna bid sheet 3rd Budget Nov 19 2025 + proposal RESIDENT UNIT TRIM): 104 toilets (98+6 ADA Gerber) + 104 lavs (Kohler K-2035-1 + matte black Peerless) + 53 tubs (47+6 ADA Sterling Vikrell) + 51 showers (Sterling 95077) + 104 kitchen sinks (Peerless P7946LF-BL) + 4 common (2 Toto WC + 2 Kohler lav) + 2 amenity sinks + 1 mop + 1 drinking fountain + 1 coffee. Plus 106 dishwasher RI + 104 icemaker RI + 104 washer RI + 104 condensate drains + 208 water spacer tubes.
12 | NEW GC SIGNAL · OWNER-GC | First OWP engagement with Ravenna Partners (owner-GC pattern · self-developing). Initial budget rounds Dec 2023 + Oct 2024 listed Blueprint as GC; Ravenna took over for Nov 2025 final bid. Owner-GC posture (lean PM, price-sensitive, schedule-focused) is unfamiliar territory for OWP — no closed-job baseline.
13 | DESIGN-TEAM POSTURE | Architect TBD per Master Project List (drawings published as 'Building Permit Plans' Nov 2025). MEP Franklin Engineering is OWP design-build partner ($10,701 design fees, ~0.55% of bid value · standard pre-permit ratio). Heat source: 3 gas boilers (199mbh × 100-gal AO Smith/Rinnai/Bock) — gas water heating with electric fallback alternate.
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | 99.4% | 32-38% | 30-40% | INFO
Revenue per unit | $18,731 | $10-15k | $8-20k | INFO
Direct cost per unit | $106 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 55% | 48-50% | 40-55% | WATCH
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $1,948,000 | $1,948,000 | — | OK
Billed: hero block vs JDR | $0 | $0 | — | INFO
Direct cost: meta vs costCats | $11,007 | $11,007 | — | OK
Worker count: dashboard vs meta | 2 | 2 | — | OK
AP vendor count vs JDR | Source aggregate | 1 | — | INFO
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Franklin Engineering | 2 | 10701 | 100.0% | Concentration flag
SOURCES
Job #2117 — Lachlan Apartments • GC: Ravenna Partners • Status: ACTIVE · pre-construction · final BID submitted
Canonical source: 2117_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2117_dashboard_arrays.json (mirrors index.html PROJECTS['2117'])
Project profile: 104 units · 3421 Woodland Park Ave N, Seattle WA (Lower Woodland / Wallingford) · Pre-construction · 23-month bid pursuit since Dec 2023 · final BID Nov 19 2025
Design team: Architect TBD (per Master Project List · drawings published as Building Permit Plans Nov 2025), Franklin Engineering (OWP design-build MEP · $10.7k design fees booked)
Contract: FINAL BID submitted Nov 19 2025 by OWP for $1,948,000 / 104u / 425 trim. 23-month, 3-bid pursuit: $2,610,000 (Dec 15 2023 1st Budget Blueprint era / 122u / 667 RI) → $2,100,000 (Oct 17 2024 2nd Budget Blueprint era / 100u / 539 RI · -19.5%) → $1,948,000 (Nov 19 2025 FINAL Ravenna era / 104u / 425 trim · -7.2%). Net -25.4% / -$662k / -18 units across 3 bids.
Billing: $0 billed across no progress billings yet — pre-acceptance phase. $0 retention.
Permit: Pre-permit · plumbing permit submittal pending Ravenna acceptance