## Overview
Job #2008 · Exxel Pacific Vivo Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA • 163-unit multifamily apartments • Jun 2013 – Aug 2014 (~15 months)
PROJECT OVERVIEW
Project Job # | 2008
Project Name: | Exxel Pacific Vivo Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA
Project Duration | Jun 2013 – Aug 2014 (~15 months)
Total Unique Documents | 2008 folder: JDR source document, 163 plumbing units
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,327,698 |  | $518,795 |  | $1,808,903 |  | 29,344
Original $2,256,200 + $71,498 COs |  | 22.3% margin |  | 77.7% of revenue |  | 49 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 551450 | 593780.08 | -42330.08 | 107.7% | 32.83%
Material | 1043740 | 816046.33 | 227693.67 | 78.18% | 45.11%
Overhead | 46570 | 80217.45 | -33647.45 | 172.3% | 4.435%
Burden | 299645.41 | 318858.96 | -19213.55 | 106.4% | 17.63%
TOTAL | 1941405.41 | 1808902.82 | 132502.59 | 93.17% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 163 | Total Fixtures | 1786 | Fixtures / Unit | 10.96
Duration | 15 mo
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 46715 | 46715 | 11671.12 | 35043.88 | 24.98%
100 | Supervision | 11600 | 11915 | 8811.5 | 3103.5 | 73.95%
101 | Takeoff & Purchase Labor | 10300 | 11560 | 15093.5 | -3533.5 | 130.6%
110 | Underground Labor | 5440 | 5440 | 7757.5 | -2317.5 | 142.6%
111 | Garage Labor | 44625 | 44625 | 38324.13 | 6300.87 | 85.88%
112 | Canout Labor | 42255 | 42255 | 29831.5 | 12423.5 | 70.6%
113 | Foundation Drain Labor | 3400 | 3400 | 2454 | 946 | 72.18%
120 | Roughin Labor | 261585 | 269760 | 303122.05 | -33362.05 | 112.4%
130 | Finish Labor | 43650 | 49430 | 76368.5 | -26938.5 | 154.5%
140 | Gas Labor | 18000 | 18200 | 21795.5 | -3595.5 | 119.8%
141 | Water Main/Insulation Lab | 40050 | 40050 | 64816.03 | -24766.03 | 161.8%
142 | Mech Room Labor | 8100 | 8100 | 13633.25 | -5533.25 | 168.3%
145 | Tub/Shower Labor | 0 | 0 | 101.5 | -101.5 | 0%
MATERIAL
039 | DS & RD Material | 60420 | 60420 | 26220.27 | 34199.73 | 43.4%
210 | Underground Material | 3000 | 3000 | 10852.76 | -7852.76 | 361.8%
211 | Garage Material | 33750 | 33750 | 15831.2 | 17918.8 | 46.91%
212 | Canout Material | 70425 | 70425 | 58265.64 | 12159.36 | 82.73%
213 | Foundation Material | 10550 | 10550 | 2839.07 | 7710.93 | 26.91%
220 | Roughin Material | 247610 | 250830 | 178543.02 | 72286.98 | 71.18%
230 | Finish Material | 498050 | 521715 | 428881.3 | 92833.7 | 82.21%
240 | Gas Material | 18000 | 18300 | 11391.29 | 6908.71 | 62.25%
241 | Water Main/Insulation Mat | 66750 | 66750 | 80448.24 | -13698.24 | 120.5%
242 | Mech Room Material | 5400 | 5400 | 2236.93 | 3163.07 | 41.42%
245 | Tub/Shower Material | 2600 | 2600 | 536.61 | 2063.39 | 20.64%
OVERHEAD
600 | Subcontractor | 7870 | 9070 | 16900.64 | -7830.64 | 186.3%
601 | Engineering/Plans | 35000 | 35500 | 57119.45 | -21619.45 | 160.9%
603 | Permits & Licenses | 2000 | 2000 | 6197.36 | -4197.36 | 309.9%
BURDEN
995 | Payroll Burden | 228724 | 254698.59 | 270898.22 | -16199.63 | 106.4%
998 | Payroll Taxes | 43743.47 | 44946.82 | 47960.74 | -3013.92 | 106.7%
TOTAL | Direct Cost | 1869612.47 | 1941405.41 | 1808902.82 | 132502.59 | 93.17%
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 13 | 551450 | 593780.08 | -42330.08 | 107.7% | 32.83% | 3642.8226
Material | 11 | 1043740 | 816046.33 | 227693.67 | 78.18% | 45.11% | 5006.4192
Overhead | 3 | 46570 | 80217.45 | -33647.45 | 172.3% | 4.435% | 492.1316
Burden | 2 | 299645.41 | 318858.96 | -19213.55 | 106.4% | 17.63% | 1956.1899
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 269760 | 303122.05 | 33362.05 | 12.37%
130 | Finish Labor | 49430 | 76368.5 | 26938.5 | 54.5%
141 | Water Main/Insulation Lab | 40050 | 64816.03 | 24766.03 | 61.84%
601 | Engineering/Plans | 35500 | 57119.45 | 21619.45 | 60.9%
995 | Payroll Burden | 254698.59 | 270898.22 | 16199.63 | 6.36%
241 | Water Main/Insulation Mat | 66750 | 80448.24 | 13698.24 | 20.52%
210 | Underground Material | 3000 | 10852.76 | 7852.76 | 261.8%
600 | Subcontractor | 9070 | 16900.64 | 7830.64 | 86.34%
142 | Mech Room Labor | 8100 | 13633.25 | 5533.25 | 68.31%
603 | Permits & Licenses | 2000 | 6197.36 | 4197.36 | 209.9%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 521715 | 428881.3 | 92833.7 | 17.79%
220 | Roughin Material | 250830 | 178543.02 | 72286.98 | 28.82%
011 | DS & RD Labor | 46715 | 11671.12 | 35043.88 | 75.02%
039 | DS & RD Material | 60420 | 26220.27 | 34199.73 | 56.6%
211 | Garage Material | 33750 | 15831.2 | 17918.8 | 53.09%
112 | Canout Labor | 42255 | 29831.5 | 12423.5 | 29.4%
212 | Canout Material | 70425 | 58265.64 | 12159.36 | 17.27%
213 | Foundation Material | 10550 | 2839.07 | 7710.93 | 73.09%
240 | Gas Material | 18300 | 11391.29 | 6908.71 | 37.75%
111 | Garage Labor | 44625 | 38324.13 | 6300.87 | 14.12%
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Material
Material Spend Analysis
11 material cost codes • $816,046 JDR material • 20 AP vendors • $974,278 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 60420 | 26220.27 | 34199.73 | 43.4% | 3.213% | 160.8606
210 | Underground Material | 3000 | 10852.76 | -7852.76 | 361.8% | 1.33% | 66.5813
211 | Garage Material | 33750 | 15831.2 | 17918.8 | 46.91% | 1.94% | 97.1239
212 | Canout Material | 70425 | 58265.64 | 12159.36 | 82.73% | 7.14% | 357.4579
213 | Foundation Material | 10550 | 2839.07 | 7710.93 | 26.91% | 0.3479% | 17.4176
220 | Roughin Material | 250830 | 178543.02 | 72286.98 | 71.18% | 21.88% | 1095.356
230 | Finish Material | 521715 | 428881.3 | 92833.7 | 82.21% | 52.56% | 2631.1736
240 | Gas Material | 18300 | 11391.29 | 6908.71 | 62.25% | 1.396% | 69.8852
241 | Water Main/Insulation Mat | 66750 | 80448.24 | -13698.24 | 120.5% | 9.858% | 493.5475
242 | Mech Room Material | 5400 | 2236.93 | 3163.07 | 41.42% | 0.2741% | 13.7235
245 | Tub/Shower Material | 2600 | 536.61 | 2063.39 | 20.64% | 0.06576% | 3.2921
TOTAL | All Material | 1043740 | 816046.33 | 227693.67 | 78.18% | 100% | 5006.4192
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 204 | 597586.16 | 61.34% |  |  |  | 2929.3439
Rosen Supply Company, Inc. | 118 | 91819.63 | 9.424% |  |  |  | 778.1325
Mechanical Sales, Inc. | 5 | 78442.97 | 8.051% |  |  |  | 15688.594
Keller Supply Company | 83 | 71760.48 | 7.366% |  |  |  | 864.5841
Franklin Engineering | 9 | 56505.5 | 5.8% |  |  |  | 6278.3889
Bank of America CC | 19 | 20102 | 2.063% |  |  |  | 1058
Quality Concrete Products, Inc. | 7 | 19615 | 2.013% |  |  |  | 2802.1429
Duraseal, Inc. | 3 | 15300 | 1.57% |  |  |  | 5100
Fastenal Company | 11 | 14267.27 | 1.464% |  |  |  | 1297.0245
Kele, Inc | 7 | 2272.16 | 0.2332% |  |  |  | 324.5943
C.M. Hoskins Company | 5 | 1597.08 | 0.1639% |  |  |  | 319.416
Ferguson Enterprises, Inc. #3007 | 5 | 1061.65 | 0.109% |  |  |  | 212.33
Capital One Credit Card | 92 | 936.66 | 0.09614% |  |  |  | 10.1811
Consolidated Supply Co. | 5 | 782.55 | 0.08032% |  |  |  | 156.51
DRSi | 5 | 613.95 | 0.06302% |  |  |  | 122.79
Structural Imaging, LLC | 1 | 500 | 0.05132% |  |  |  | 500
Evergreen Concrete Cutting, Inc. | 1 | 375 | 0.03849% |  |  |  | 375
American Express 3-41000 | 2 | 335 | 0.03438% |  |  |  | 167.5
R.A. Brown Backflow Testing | 1 | 257.64 | 0.02644% |  |  |  | 257.64
Platt | 2 | 147.74 | 0.01516% |  |  |  | 73.87
TOTAL | 585 | 974278.44 | 100%
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
Vendor AP ties to JDR 'by Source: AP' line (974,278.44)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Salazar, Hajdar L | 1950 | 25346 | 12.9979 | Apprentice
Reed, Reuben H | 1839 | 50190 | 27.292 | Mid
Hubbard, Robert W | 1771 | 59000.5 | 33.3148 | Senior
Sepulveda Gonzalez, Alfredo | 1755.5 | 42871.5 | 24.4212 | Mid
Arreola, Israel A | 1278 | 19601 | 15.3372 | Apprentice
Velasquez Cruz, Denis M | 1236 | 16740 | 13.5437 | Apprentice
Spears, Gregory M | 1186 | 16134 | 13.6037 | Apprentice
Ross, Kelli M | 1185 | 33066 | 27.9038 | Mid
Cortes Mendiola, Victor H | 1180 | 28772 | 24.3831 | Mid
Ramirez, Lorenzo A | 1101.75 | 17628 | 16 | Apprentice
Castro Hernandez, Carlos E | 1057 | 26832 | 25.3851 | Mid
McCabe, Thomas C | 985.5 | 17406.3 | 17.6624 | Apprentice
Castaneda Juarez, Gustavo | 892 | 12019 | 13.4742 | Apprentice
Gerard, Jeffrey S | 806.5 | 27755.8 | 34.4151 | Senior
Balderas Ortiz, Ricardo I | 784 | 10192 | 13 | Apprentice
Lopez Martinez, Abimael | 762 | 9144 | 12 | Apprentice
Castaneda Martinez, Gustavo | 738 | 20470 | 27.7371 | Mid
Vega Arriaga, Jorge | 734.5 | 9233.5 | 12.5711 | Apprentice
Monico Brambila, Jesus S | 659 | 9185.5 | 13.9385 | Apprentice
Sanders, Allen O | 635 | 18427.5 | 29.0197 | Mid
Veley, Nathaniel S | 541 | 13895 | 25.6839 | Mid
Paco Leyva, Orlando | 518.5 | 6543 | 12.6191 | Apprentice
Soto Cruz, Jovani | 498.75 | 7964 | 15.9679 | Apprentice
Alba Martinez, Santiago | 480 | 7200 | 15 | Apprentice
Rivera, Jorge A | 461 | 8298 | 18 | Mid
Palma Vides, Hugo | 400 | 11200 | 28 | Mid
Waites, Thaddeus Z | 396 | 10770 | 27.197 | Mid
Sanchez Garcia, Adelaido | 368 | 4784 | 13 | Apprentice
Kinssies, Jr, John E | 331 | 4801 | 14.5045 | Apprentice
Soto Serna, Cesar E | 321.25 | 4176.25 | 13 | Apprentice
Bateman, Rohan O | 318 | 3816 | 12 | Apprentice
Anderson, Richard P | 312 | 8320 | 26.6667 | Mid
Castro Hernandez, Jose A | 288 | 4896 | 17 | Apprentice
Agustin Rodriguez, Ezequiel | 287 | 3444 | 12 | Apprentice
Ramos Banegas, Noel O | 231 | 3003 | 13 | Apprentice
Rivera, Eli P | 224 | 2912 | 13 | Apprentice
Meza Fuentes, Erick A | 188 | 3597 | 19.133 | Mid
Vaughan, Tyler J | 157 | 2512 | 16 | Apprentice
Castaneda Juarez, Edgar D | 136 | 1972 | 14.5 | Apprentice
Perez, David B | 121 | 1694 | 14 | Apprentice
Ramos Garcia, Jose M | 120 | 1560 | 13 | Apprentice
Hubbard, Dustin R | 116 | 1388 | 11.9655 | Apprentice
Hayton, Evan R | 112 | 1536 | 13.7143 | Apprentice
Lima Romero, Melvin A | 60.5 | 1140.5 | 18.8512 | Mid
Garcia, Jordan X | 48 | 672 | 14 | Apprentice
Wilson, Garret A | 32 | 456 | 14.25 | Apprentice
Donelson, Richard T | 11 | 495 | 45 | Senior
Reyes, Robert J | 6 | 78 | 13 | Apprentice
Barnhart, Joseph N | 5.5 | 164.5 | 29.9091 | Mid
TOTAL (49 workers) | 29624.25 | 593301.85 | 20.0276
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 2588.5 | 87251.3 | 8.738%
Mid | 15 | 10753.5 | 278014 | 36.3%
Apprentice | 31 | 16282.25 | 228036.55 | 54.96%
B. WAGE STATISTICS
Blended Gross Wage | 20.0276 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.8072 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5382 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11.9655 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 604.5765 |  |  | Crew continuity indicator
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 532.75 | 1.816% | 3.2684
Supervision | 100 | 246.5 | 0.84% | 1.5123
Takeoff & Purchasing | 101 | 443 | 1.51% | 2.7178
Underground | 110 | 392.5 | 1.338% | 2.408
Garage | 111 | 1728 | 5.889% | 10.6012
Canout | 112 | 1126.5 | 3.839% | 6.911
Foundation Drain | 113 | 120 | 0.4089% | 0.7362
Roughin | 120 | 15344.5 | 52.29% | 94.138
Finish | 130 | 4236.75 | 14.44% | 25.9923
Gas | 140 | 910 | 3.101% | 5.5828
Water Main / Insulation | 141 | 3421.5 | 11.66% | 20.9908
Mech Room | 142 | 838 | 2.856% | 5.1411
Tub / Shower | 145 | 3.5 | 0.01193% | 0.021472
TOTAL |  | 29343.5 | 100% | 180.0215
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 180.0215 | hrs |  | Labor hours per residential unit
Hours / Fixture | 16.4297 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 79.3258 | $ |  | Top-line per labor hour
Profit / Hour | 17.6801 | $ |  | Bottom-line per labor hour
Units / Month | 10.8667 | units |  | Build velocity
Fixtures / Month | 119.0667 | fix |  | Fixture install pace
Hours / Month | 1956.2333 | hrs |  | Monthly labor burn
Revenue / Month | 155179.8667 | $ |  | Monthly billing rate
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## PO Commitments
Purchase Order Commitments
0 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $816,046
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
TOTAL |  | 0 | 0% | 816046.33
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 816046.33
Unique PO Count |  |  | 0
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
Jun 2013 – Aug 2014 • $2,327,698 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 2256200
Change Orders (net) |  |  |  |  | 71498
Final Contract Value |  |  |  |  | 2327698
Retainage (5%) |  |  |  |  | 116385
Net Paid to OWP |  |  |  |  | 2211313
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2327698 | 2327698 | 0 | TIES
Retainage | 116385 | 116385 | 0 | TIES
Direct Cost | 1808903 | 1808903 | 0 | TIES
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Insights
Key Insights — Job #2008 Exxel Pacific Vivo Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $518,795 on $2,327,698 revenue = 22.3% gross margin. Direct cost $1,808,903 absorbs 77.7% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $597,586 (61% of all AP) across 204 invoices. Total 20 AP vendors, $974,278 total AP spend.
CREW PROFILE | 49 workers for 29,344 hours = 599 avg hrs/worker. Top 3 workers logged 5,560 hrs combined (19% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 15,344 hrs (52% of all labor) and $303,122 actual. Code 230 Finish Material = $428,881 — 24% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,941,405; actual direct cost $1,808,903 → $132,503 variance (6.8% under revised budget).
CONTRACT GROWTH | Contract grew from $2,256,200 to $2,327,698 — net +$71,498 (3.2%). Retainage of $116,385 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $318,859 on $593,780 labor base = 53.7%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 163 units · 1786 fixtures · 15 months. Revenue/unit $14,280, hours/unit 180.0, profit/unit $3,183.
PRODUCTIVITY | Blended labor rate $20.24/hr. Revenue/hour $79. Profit/hour $18. 1,956 hrs/month burn rate.
FIXTURE DENSITY | 1786 fixtures ÷ 163 units = 10.96 fixtures/unit. Material/fixture $457, labor/fixture $332.
BIGGEST QUESTION
How does this job's 22.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2008 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific Vivo Apartments | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | 163-unit multifamily apartments | Profile
Duration (months) | duration_months | 15 | Profile | Jun 2013 – Aug 2014 (~15 months)
Unit Count | unit_count | 163 | Profile
Total Fixtures | total_fixtures | 1786 | Profile
Fixtures per Unit | fixtures_per_unit | 1096% | Profile
Contract Value (Orig) | contract_original | 2256200 | Financial
Contract Value (Final) | contract_final | 2327698 | Financial | After change orders
Change Orders ($) | change_orders | 71498 | Financial
Revenue | revenue | 2327698 | Financial
Net Profit | net_profit | 518795.18 | Financial
Gross Margin | gross_margin | 0.22288 | Financial
Direct Cost | direct_cost | 1808902.82 | Financial
Labor Cost | labor_cost | 593780.08 | Labor | Sum of 13 labor codes
Material Cost | material_cost | 816046.33 | Material | Sum of 11 material codes
Overhead Cost | overhead_cost | 80217.45 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 318858.96 | Financial | Codes 995+998
Retainage | retainage | 116385 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 14280.3558 | Financial
Profit per Unit | profit_per_unit | 3182.7925 | Financial
Direct Cost per Unit | cost_per_unit | 11097.5633 | Financial
Labor Cost per Unit | labor_per_unit | 3642.8226 | Labor
Material Cost per Unit | material_per_unit | 5006.4192 | Material
Revenue per Fixture | revenue_per_fixture | 1303.3024 | Financial
Profit per Fixture | profit_per_fixture | 290.4788 | Financial
Cost per Fixture | cost_per_fixture | 1012.8235 | Financial
Labor per Fixture | labor_per_fixture | 332.4637 | Labor
Material per Fixture | material_per_fixture | 456.9128 | Material
Total Labor Hours | total_hours | 29343.5 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 49 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 2022% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3110% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5382 | Labor
Hours per Unit | hours_per_unit | 180.0215 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 1643% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 7933% | Productivity
Profit per Hour | profit_per_hour | 1768% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.25509 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.35058 | Cost Mix
Revenue per Month | revenue_per_month | 155179.8667 | Productivity
Hours per Month | hours_per_month | 1956.2333 | Productivity
Units per Month | units_per_month | 1087% | Productivity
Total Vendors | total_vendors | 20 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 597586.16 | Material | Ferguson Enterprises, Inc.
Top Vendor Concentration | top_vendor_pct | 0.61336 | Material
Total POs | total_pos | 0 | Material | Unique POs by filename
Change Order % | co_pct | 0.03169 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 7933% | Productivity
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (13 codes) | 593780.08 | 593780.08 | 0 | TIES
Material subtotal (11 codes) | 816046.33 | 816046.33 | 0 | TIES
Overhead subtotal (3 codes) | 80217.45 | 80217.45 | 0 | TIES
Burden subtotal (2 codes) | 318858.96 | 318858.96 | 0 | TIES
Direct Cost (all categories) | 1808902.82 | 1808902.82 | 0 | TIES
Revenue (code 999) | 2327698 | 2327698 | 0 | TIES
Net Profit (Revenue - Expenses) | 518795.18 | 518795.18 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 29343.5 | 29343.5 | 0 | TIES
Per-worker hours (sum of PR Regular) | 29624.25 | 29343.5 | 280.75 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2327698 | 2327698 | 0 | TIES
Retainage | 116385 | 116385 | 0 | TIES
Direct Cost | 1808903 | 1808903 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 974278.44 | 974278 | 0.44 | TIES
SOURCES
Job #2008 — Exxel Pacific Vivo Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2008 Job Detail Report.pdf (282 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count: 163 (from project specifications)
Fixture count: 1,786 (estimated at ~11 fixtures per unit for mid-rise apartments)
Final contract $2,327,698 (original $2,256,200 + $71,498 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2008
Vendors | 20 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 585 |  | Top 3 share | 78.81%
Total AP | 974278.44 |  | Source | 2008 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1665.4332
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 204 | 597586.16 | 61.34% | 2929.3439
2 | Rosen Supply Company, Inc. |  | 118 | 91819.63 | 9.424% | 778.1325
3 | Mechanical Sales, Inc. |  | 5 | 78442.97 | 8.051% | 15688.594
4 | Keller Supply Company |  | 83 | 71760.48 | 7.366% | 864.5841
5 | Franklin Engineering |  | 9 | 56505.5 | 5.8% | 6278.3889
6 | Bank of America CC |  | 19 | 20102 | 2.063% | 1058
7 | Quality Concrete Products, Inc. |  | 7 | 19615 | 2.013% | 2802.1429
8 | Duraseal, Inc. |  | 3 | 15300 | 1.57% | 5100
9 | Fastenal Company |  | 11 | 14267.27 | 1.464% | 1297.0245
10 | Kele, Inc |  | 7 | 2272.16 | 0.2332% | 324.5943
11 | C.M. Hoskins Company |  | 5 | 1597.08 | 0.1639% | 319.416
12 | Ferguson Enterprises, Inc. #3007 |  | 5 | 1061.65 | 0.109% | 212.33
13 | Capital One Credit Card |  | 92 | 936.66 | 0.09614% | 10.1811
14 | Consolidated Supply Co. |  | 5 | 782.55 | 0.08032% | 156.51
15 | DRSi |  | 5 | 613.95 | 0.06302% | 122.79
16 | Structural Imaging, LLC |  | 1 | 500 | 0.05132% | 500
17 | Evergreen Concrete Cutting, Inc. |  | 1 | 375 | 0.03849% | 375
18 | American Express 3-41000 |  | 2 | 335 | 0.03438% | 167.5
19 | R.A. Brown Backflow Testing |  | 1 | 257.64 | 0.02644% | 257.64
20 | Platt |  | 2 | 147.74 | 0.01516% | 73.87
| TOTAL |  | 585 | 974278.44 | 100% | 1665.4332