## Overview
Job #2011 · Chinn Barrett Park Apartments
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA (Capitol Hill) • 117-unit 4-story multifamily apartments • Nov 2012 – Mar 2014 (~17 months)
PROJECT OVERVIEW
Project Job # | 2011
Project Name: | Chinn Barrett Park Apartments
General Contractor | Chinn Construction, LLC
Location | Seattle, WA (Capitol Hill)
Project Duration | Nov 2012 – Mar 2014 (~17 months)
Total Unique Documents | Barrett Park folder: Contract, Billing (aggregate + 13 SOVs), PO_s, Progress Payments, Change Orders
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$869,824 |  | $332,960 |  | $536,863 |  | 6,944
Original $813,050 + $56,774 COs |  | 38.3% margin |  | 61.7% of revenue |  | 31 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 174655 | 142882.75 | 31772.25 | 81.81% | 26.61%
Material | 393359 | 295005.88 | 98353.12 | 75% | 54.95%
Overhead | 45725 | 26210.1 | 19514.9 | 57.32% | 4.882%
Burden | 89051.11 | 72764.72 | 16286.39 | 81.71% | 13.55%
TOTAL | 702790.11 | 536863.45 | 165926.66 | 76.39% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 117 | Water Closets | 117 | Kitchen Sinks | 119
Total Fixtures | 841 | Lavatories | 117 | Dishwashers | 3
Fixtures / Unit | 7.18 | Tubs/Showers | 117 | Auto Washers | 117
Stacks | 30 | Floors | 4 | Duration | 17 mo
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 3250 | 3250 | 1008 | 2242 | 31.02%
100 | Supervision | 8190 | 8190 | 4164 | 4026 | 50.84%
101 | Takeoff & Purchase Labor | 5850 | 5850 | 3513 | 2337 | 60.05%
110 | Underground Labor | 13150 | 13150 | 6703 | 6447 | 50.97%
111 | Garage Labor | 16200 | 16200 | 10199 | 6001 | 62.96%
112 | Canout Labor | 3640 | 3640 | 2062 | 1578 | 56.65%
113 | Foundation Drain Labor | 0 | 5650 | 2115 | 3535 | 37.43%
120 | Roughin Labor | 82535 | 82835 | 81010.75 | 1824.25 | 97.8%
130 | Finish Labor | 24770 | 24770 | 21869 | 2901 | 88.29%
141 | Water Main/Insulation Lab | 0 | 0 | 208 | -208 | 0%
142 | Mech Room Labor | 1760 | 1760 | 1007 | 753 | 57.22%
145 | Tub/Shower Labor | 9360 | 9360 | 9024 | 336 | 96.41%
MATERIAL
039 | DS & RD Material | 4725 | 4725 | 1134.76 | 3590.24 | 24.02%
210 | Underground Material | 10300 | 10300 | 5311 | 4989 | 51.56%
211 | Garage Material | 14000 | 14000 | 6465.89 | 7534.11 | 46.18%
212 | Canout Material | 5460 | 5460 | 5222.75 | 237.25 | 95.65%
213 | Foundation Material | 0 | 6000 | 3664.54 | 2335.46 | 61.08%
220 | Roughin Material | 82540 | 82840 | 48840.52 | 33999.48 | 58.96%
230 | Finish Material | 231620 | 259734 | 207101.2 | 52632.8 | 79.74%
241 | Water Main/Insulation Mat | 7800 | 7800 | 15147.02 | -7347.02 | 194.2%
242 | Mech Room Material | 2500 | 2500 | 1233.58 | 1266.42 | 49.34%
244 | Fire Caulking Material | 0 | 0 | 0 | 0 | 0%
245 | Tub/Shower Material | 0 | 0 | 884.62 | -884.62 | 0%
OVERHEAD
600 | Subcontractor | 10000 | 13085 | 6346.07 | 6738.93 | 48.5%
601 | Engineering/Plans | 25000 | 25000 | 12573.03 | 12426.97 | 50.29%
603 | Permits & Licenses | 7630 | 7640 | 7291 | 349 | 95.43%
BURDEN
995 | Payroll Burden | 73133.62 | 75712.95 | 61834.11 | 13878.84 | 81.67%
998 | Payroll Taxes | 12905.93 | 13338.16 | 10930.61 | 2407.55 | 81.95%
TOTAL | Direct Cost | 656319.55 | 702790.11 | 536863.45 | 165926.66 | 76.39%
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 12 | 174655 | 142882.75 | 31772.25 | 81.81% | 26.61% | 1221.2201
Material | 11 | 393359 | 295005.88 | 98353.12 | 75% | 54.95% | 2521.4178
Overhead | 3 | 45725 | 26210.1 | 19514.9 | 57.32% | 4.882% | 224.0179
Burden | 2 | 89051.11 | 72764.72 | 16286.39 | 81.71% | 13.55% | 621.9207
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
241 | Water Main/Insulation Mat | 7800 | 15147.02 | 7347.02 | 94.19%
245 | Tub/Shower Material | 0 | 884.62 | 884.62 | 0%
141 | Water Main/Insulation Lab | 0 | 208 | 208 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 259734 | 207101.2 | 52632.8 | 20.26%
220 | Roughin Material | 82840 | 48840.52 | 33999.48 | 41.04%
995 | Payroll Burden | 75712.95 | 61834.11 | 13878.84 | 18.33%
601 | Engineering/Plans | 25000 | 12573.03 | 12426.97 | 49.71%
211 | Garage Material | 14000 | 6465.89 | 7534.11 | 53.82%
600 | Subcontractor | 13085 | 6346.07 | 6738.93 | 51.5%
110 | Underground Labor | 13150 | 6703 | 6447 | 49.03%
111 | Garage Labor | 16200 | 10199 | 6001 | 37.04%
210 | Underground Material | 10300 | 5311 | 4989 | 48.44%
100 | Supervision | 8190 | 4164 | 4026 | 49.16%
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Material
Material Spend Analysis
11 material cost codes • $295,006 JDR material • 14 AP vendors • $387,379 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 4725 | 1134.76 | 3590.24 | 24.02% | 0.3847% | 9.6988
210 | Underground Material | 10300 | 5311 | 4989 | 51.56% | 1.8% | 45.3932
211 | Garage Material | 14000 | 6465.89 | 7534.11 | 46.18% | 2.192% | 55.264
212 | Canout Material | 5460 | 5222.75 | 237.25 | 95.65% | 1.77% | 44.6389
213 | Foundation Material | 6000 | 3664.54 | 2335.46 | 61.08% | 1.242% | 31.3209
220 | Roughin Material | 82840 | 48840.52 | 33999.48 | 58.96% | 16.56% | 417.4403
230 | Finish Material | 259734 | 207101.2 | 52632.8 | 79.74% | 70.2% | 1770.0957
241 | Water Main/Insulation Mat | 7800 | 15147.02 | -7347.02 | 194.2% | 5.134% | 129.4617
242 | Mech Room Material | 2500 | 1233.58 | 1266.42 | 49.34% | 0.4182% | 10.5434
244 | Fire Caulking Material | 0 | 0 | 0 | 0% | 0% | 0
245 | Tub/Shower Material | 0 | 884.62 | -884.62 | 0% | 0.2999% | 7.5609
TOTAL | All Material | 393359 | 295005.88 | 98353.12 | 75% | 100% | 2521.4178
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 56 | 302211.38 | 78.01% |  |  |  | 5396.6318
Rosen Supply Company, Inc. | 30 | 35755.01 | 9.23% |  |  |  | 1191.8337
Franklin Engineering | 5 | 12487 | 3.223% |  |  |  | 2497.4
Keller Supply Company | 13 | 10651.28 | 2.75% |  |  |  | 819.3292
Fastenal Company | 4 | 8107.96 | 2.093% |  |  |  | 2026.99
Bank of America CC | 3 | 7291 | 1.882% |  |  |  | 2430.3333
Mickelo Construction LLC | 2 | 6217.07 | 1.605% |  |  |  | 3108.535
Quality Concrete Products, Inc. | 2 | 2598 | 0.6707% |  |  |  | 1299
Manor Hardware & Construction Supply | 2 | 870 | 0.2246% |  |  |  | 435
Core & Main LP | 1 | 810 | 0.2091% |  |  |  | 810
R.A. Brown Backflow Testing | 1 | 129 | 0.0333% |  |  |  | 129
C.M. Hoskins Company | 1 | 102 | 0.02633% |  |  |  | 102
DRSi | 1 | 86.03 | 0.02221% |  |  |  | 86.03
Capital One Credit Card | 2 | 63.21 | 0.01632% |  |  |  | 31.605
TOTAL | 123 | 387378.94 | 100%
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
Vendor AP ties to JDR 'by Source: AP' line (387,378.94)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 804.5 | 24669 | 30.6638 | Senior
Castro Hernandez, Jose A | 785.5 | 11541 | 14.6926 | Apprentice
Monico Brambila, Jesus S | 640 | 7792 | 12.175 | Apprentice
Garcia, Jordan X | 607 | 7748 | 12.7644 | Apprentice
Lima Romero, Melvin A | 523.5 | 9941.5 | 18.9904 | Mid
Castaneda Martinez, Gustavo | 449 | 11691 | 26.0379 | Mid
Palma Vides, Hugo | 384 | 9984 | 26 | Mid
Anderson, Richard P | 341 | 8866 | 26 | Mid
Wilson, Garret A | 320 | 4296 | 13.425 | Apprentice
Gerard, Jeffrey S | 254 | 8779 | 34.563 | Senior
McCabe, Thomas C | 196 | 3504 | 17.8776 | Apprentice
Ross, Kelli M | 189 | 5292 | 28 | Mid
Reed, Reuben H | 157 | 4082 | 26 | Mid
Sepulveda Gonzalez, Alfredo | 157 | 3547 | 22.5924 | Mid
Holmes, Anthony R | 136 | 1616 | 11.8824 | Apprentice
Kinssies, Jr, John E | 128 | 1696 | 13.25 | Apprentice
Meza Fuentes, Erick A | 126 | 2402 | 19.0635 | Mid
Barnhart, Joseph N | 122 | 3782 | 31 | Senior
Hayton, Evan R | 118 | 1652 | 14 | Apprentice
Ramirez, Lorenzo A | 108 | 1728 | 16 | Apprentice
Gonzalez Hernandez, Josue | 80 | 960 | 12 | Apprentice
Paco Leyva, Orlando | 37 | 444 | 12 | Apprentice
Veley, Nathaniel S | 34 | 850 | 25 | Mid
Hubbard, Dustin R | 33.5 | 402 | 12 | Apprentice
Cortes Mendiola, Victor H | 24 | 552 | 23 | Mid
Sanders, Allen O | 9 | 261 | 29 | Mid
Arreola, Israel A | 8 | 96 | 12 | Apprentice
Castro Hernandez, Carlos E | 8 | 184 | 23 | Mid
Soto Cruz, Jovani | 8 | 128 | 16 | Apprentice
Soto Serna, Cesar E | 8 | 104 | 13 | Apprentice
Vaughan, Tyler J | 8 | 104 | 13 | Apprentice
TOTAL (31 workers) | 6803 | 138693.5 | 20.3871
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 1180.5 | 37230 | 17.35%
Mid | 12 | 2401.5 | 57652.5 | 35.3%
Apprentice | 16 | 3221 | 43811 | 47.35%
B. WAGE STATISTICS
Blended Gross Wage | 20.3871 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 31.6989 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5548 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 11.8824 |  |  | Cheapest apprentice hour
Max Worker Rate | 34.563 |  |  | Most expensive foreman hour
Avg Hours / Worker | 219.4516 |  |  | Crew continuity indicator
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 56 | 0.8065% | 0.47863
Supervision | 100 | 117 | 1.685% | 1
Takeoff & Purchasing | 101 | 104 | 1.498% | 0.88889
Underground | 110 | 298.5 | 4.299% | 2.5513
Garage | 111 | 553 | 7.964% | 4.7265
Canout | 112 | 96 | 1.383% | 0.82051
Foundation Drain | 113 | 96.5 | 1.39% | 0.82479
Roughin | 120 | 3984 | 57.38% | 34.0513
Finish | 130 | 1173 | 16.89% | 10.0256
Water Main / Insulation | 141 | 16 | 0.2304% | 0.13675
Mech Room | 142 | 44 | 0.6337% | 0.37607
Tub / Shower | 145 | 405.5 | 5.84% | 3.4658
TOTAL |  | 6943.5 | 100% | 59.3462
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 59.3462 | hrs |  | Labor hours per residential unit
Hours / Fixture | 8.2562 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 125.2716 | $ |  | Top-line per labor hour
Profit / Hour | 47.9528 | $ |  | Bottom-line per labor hour
Units / Month | 6.8824 | units |  | Build velocity
Fixtures / Month | 49.4706 | fix |  | Fixture install pace
Hours / Month | 408.4412 | hrs |  | Monthly labor burn
Revenue / Month | 51166.0882 | $ |  | Monthly billing rate
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## PO Commitments
Purchase Order Commitments
0 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $295,006
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
TOTAL |  | #VALUE! | 100% | 295005.88
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 295005.88
Unique PO Count |  |  | 0
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
13 pay applications • Nov 2012 – Mar 2014 • $869,824 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 813050
Change Orders (net) |  |  |  |  | 56774
Final Contract Value |  |  |  |  | 869824
Retainage (5%) |  |  |  |  | 43491
Net Paid to OWP |  |  |  |  | 826333
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2012-11-15 | 9500 | 475 | 9025 | 9025 | 1.038%
2 | 2013-01-15 | 32700 | 1635 | 31065 | 40090 | 4.609%
3 | 2013-02-15 | 33000 | 1650 | 31350 | 71440 | 8.213%
4 | 2013-03-15 | 38800 | 1940 | 36860 | 108300 | 12.45%
5 | 2013-04-09 | 18700 | 935 | 17765 | 126065 | 14.49%
6 | 2013-05-09 | 63000 | 3150 | 59850 | 185915 | 21.37%
7 | 2013-06-11 | 235300 | 11765 | 223535 | 409450 | 47.07%
8 | 2013-07-11 | 183000 | 9150 | 173850 | 583300 | 67.06%
9 | 2013-08-09 | 41009 | 2050.45 | 38958.55 | 622258.55 | 71.54%
10 | 2013-09-10 | 5400 | 270 | 5130 | 627388.55 | 72.13%
11 | 2013-10-10 | 5100 | 255 | 4845 | 632233.55 | 72.69%
12 | 2014-02-10 | 103997 | 5199.85 | 98797.15 | 731030.7 | 84.04%
13 | 2014-03-10 | 100317.5 | 5015.875 | 95301.625 | 826332.32 | 95%
14 | 2014-11-13 | 43491.18 | 0 | 43491.18 | 869823.5 | 100%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 869824 | 869824 | 0 | TIES
Retainage | 43491 | 43491 | 0 | TIES
Direct Cost | 536863.45 | 536863.45 | 0 | TIES
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Insights
Key Insights — Job #2011 Chinn Barrett Park Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $332,960 on $869,824 revenue = 38.3% gross margin. Direct cost $536,863 absorbs 61.7% of revenue.
VENDOR CONCENTRATION | Ferguson Enterprises, Inc. alone = $302,211 (78% of all AP) across 56 invoices. Total 14 AP vendors, $387,379 total AP spend.
CREW PROFILE | 31 workers for 6,944 hours = 224 avg hrs/worker. Top 3 workers logged 2,230 hrs combined (32% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 3,984 hrs (57% of all labor) and $81,011 actual. Code 230 Finish Material = $207,101 — 39% of total direct cost.
BUDGET DELIVERY | Revised budget was $702,790; actual direct cost $536,863 → $165,927 variance (23.6% under revised budget).
CONTRACT GROWTH | Contract grew from $813,050 to $869,824 — net +$56,774 (7.0%). Retainage of $43,491 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $72,765 on $142,883 labor base = 50.9%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 117 units · 841 fixtures · 17 months. Revenue/unit $7,434, hours/unit 59.3, profit/unit $2,846.
PRODUCTIVITY | Blended labor rate $20.58/hr. Revenue/hour $125. Profit/hour $48. 408 hrs/month burn rate.
FIXTURE DENSITY | 841 fixtures ÷ 117 units = 7.19 fixtures/unit. Material/fixture $351, labor/fixture $170.
BIGGEST QUESTION
How does this job's 38.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2011 | Profile | OWP job ID
Job Name | job_name | Chinn Barrett Park Apartments | Profile
General Contractor | general_contractor | Chinn Construction, LLC | Profile
Location | location | Seattle, WA (Capitol Hill) | Profile
Project Type | project_type | 117-unit 4-story multifamily apartments | Profile
Duration (months) | duration_months | 17 | Profile | Nov 2012 – Mar 2014 (~17 months)
Unit Count | unit_count | 117 | Profile
Total Fixtures | total_fixtures | 841 | Profile
Fixtures per Unit | fixtures_per_unit | 7.188 | Profile
Contract Value (Orig) | contract_original | 813050 | Financial
Contract Value (Final) | contract_final | 869823.5 | Financial | After change orders
Change Orders ($) | change_orders | 56773.5 | Financial
Revenue | revenue | 869823.5 | Financial
Net Profit | net_profit | 332960.05 | Financial
Gross Margin | gross_margin | 0.38279 | Financial
Direct Cost | direct_cost | 536863.45 | Financial
Labor Cost | labor_cost | 142882.75 | Labor | Sum of 12 labor codes
Material Cost | material_cost | 295005.88 | Material | Sum of 11 material codes
Overhead Cost | overhead_cost | 26210.1 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 72764.72 | Financial | Codes 995+998
Retainage | retainage | 43491 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 7434.3889 | Financial
Profit per Unit | profit_per_unit | 2845.8124 | Financial
Direct Cost per Unit | cost_per_unit | 4588.5765 | Financial
Labor Cost per Unit | labor_per_unit | 1221.2201 | Labor
Material Cost per Unit | material_per_unit | 2521.4178 | Material
Revenue per Fixture | revenue_per_fixture | 1034.2729 | Financial
Profit per Fixture | profit_per_fixture | 395.9097 | Financial
Cost per Fixture | cost_per_fixture | 638.3632 | Financial
Labor per Fixture | labor_per_fixture | 169.8963 | Labor
Material per Fixture | material_per_fixture | 350.7799 | Material
Total Labor Hours | total_hours | 6943.5 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 31 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1997% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3106% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5548 | Labor
Hours per Unit | hours_per_unit | 5935% | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 8.2562 | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 125.2716 | Productivity
Profit per Hour | profit_per_hour | 4795% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.16427 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.33916 | Cost Mix
Revenue per Month | revenue_per_month | 51166.0882 | Productivity
Hours per Month | hours_per_month | 408.4412 | Productivity
Units per Month | units_per_month | 6.8824 | Productivity
Total Vendors | total_vendors | 14 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 302211.38 | Material | Ferguson Enterprises, Inc.
Top Vendor Concentration | top_vendor_pct | 0.78014 | Material
Total POs | total_pos | 0 | Material | Unique POs by filename
Change Order % | co_pct | 0.069828 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 125.2716 | Productivity
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (12 codes) | 142882.75 | 142882.75 | 0 | TIES
Material subtotal (11 codes) | 295005.88 | 295005.88 | 0 | TIES
Overhead subtotal (3 codes) | 26210.1 | 26210.1 | 0 | TIES
Burden subtotal (2 codes) | 72764.72 | 72764.72 | 0 | TIES
Direct Cost (all categories) | 536863.45 | 536863.45 | 0 | TIES
Revenue (code 999) | 869823.5 | 869823.5 | 0 | TIES
Net Profit (Revenue - Expenses) | 332960.05 | 332960.05 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 6943.5 | 6943.5 | 0 | TIES
Per-worker hours (sum of PR Regular) | 6803 | 6943.5 | -140.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 869824 | 869824 | 0 | TIES
Retainage | 43491 | 43491 | 0 | TIES
Direct Cost | 536863.45 | 536863.45 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 387378.94 | 387379 | -0.06 | TIES
SOURCES
Job #2011 — Chinn Barrett Park Apartments • GC: Chinn Construction, LLC • Seattle, WA (Capitol Hill)
Canonical source: 2011 Job Detail Report.pdf (69 pages, OWP Sage Timberline export)
Cost codes parsed: 29
Unit count: 117 units confirmed
Fixture count: 841 from permit SR1224327
Billing: BARRETT AGGREGATE BILLING.xlsx (13 pay apps Nov 2012 – Mar 2014)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2011
Vendors | 14 |  | Top vendor | Ferguson Enterprises, Inc.
Invoices | 123 |  | Top 3 share | 90.47%
Total AP | 387378.94 |  | Source | 2011 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 3149.4223
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Ferguson Enterprises, Inc. |  | 56 | 302211.38 | 78.01% | 5396.6318
2 | Rosen Supply Company, Inc. |  | 30 | 35755.01 | 9.23% | 1191.8337
3 | Franklin Engineering |  | 5 | 12487 | 3.223% | 2497.4
4 | Keller Supply Company |  | 13 | 10651.28 | 2.75% | 819.3292
5 | Fastenal Company |  | 4 | 8107.96 | 2.093% | 2026.99
6 | Bank of America CC |  | 3 | 7291 | 1.882% | 2430.3333
7 | Mickelo Construction LLC |  | 2 | 6217.07 | 1.605% | 3108.535
8 | Quality Concrete Products, Inc. |  | 2 | 2598 | 0.6707% | 1299
9 | Manor Hardware & Construction Supply |  | 2 | 870 | 0.2246% | 435
10 | Core & Main LP |  | 1 | 810 | 0.2091% | 810
11 | R.A. Brown Backflow Testing |  | 1 | 129 | 0.0333% | 129
12 | C.M. Hoskins Company |  | 1 | 102 | 0.02633% | 102
13 | DRSi |  | 1 | 86.03 | 0.02221% | 86.03
14 | Capital One Credit Card |  | 2 | 63.21 | 0.01632% | 31.605
| TOTAL |  | 123 | 387378.94 | 100% | 3149.4223