## Overview
Job #2012 · Exxel Pacific 8th Ave Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (4545 8th Ave NE) • 163-unit 9-story multifamily apartments + ground-floor retail • Mar 2013 – Jul 2014 (~17 months)
PROJECT OVERVIEW
Project Job # | 2012
Project Name: | Exxel Pacific 8th Ave Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (4545 8th Ave NE)
Project Duration | Mar 2013 – Jul 2014 (~17 months)
Total Unique Documents | 8th Ave folder: Contract (Exxel Pacific + One Way Plumbing), Billing (aggregate + 15 SOVs), PO_s (68 scheduled), Permits (plumbing, gas, boiler, backflow), Change Orders
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,391,455 |  | $544,854 |  | $846,601 |  | 14,607
Original $1,394,655 + $-3,200 COs |  | 39.2% margin |  | 60.8% of revenue |  | 40 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 305975 | 291321.88 | 14653.12 | 95.21% | 34.41%
Material | 561666 | 390750.86 | 170915.14 | 69.57% | 46.16%
Overhead | 33000 | 15938.74 | 17061.26 | 48.3% | 1.883%
Burden | 147117.15 | 148589.84 | -1472.69 | 101% | 17.55%
TOTAL | 1047758.15 | 846601.32 | 201156.83 | 80.8% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 163 | Water Closets | 163 | Lavatories | 163
Kitchen Sinks | 163 | Dishwashers | 163 | Laundry Washers | 163
Bathtub/Shower | 163 | Floor Drains | 5 | Roof Drains | 18
Total Fixtures | 1004 | Fixtures / Unit | 6.16 | Floors | 9 stories + retail
Duration | 17 mo
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 12500 | 12500 | 3752.5 | 8747.5 | 30.02%
100 | Supervision | 8100 | 8100 | 6023 | 2077 | 74.36%
101 | Takeoff & Purchase Labor | 12150 | 12150 | 6161.5 | 5988.5 | 50.71%
110 | Underground Labor | 5800 | 5800 | 3184.25 | 2615.75 | 54.9%
111 | Garage Labor | 14600 | 14600 | 19353.5 | -4753.5 | 132.6%
112 | Canout Labor | 11700 | 11700 | 5424 | 6276 | 46.36%
113 | Foundation Drain Labor | 2700 | 2700 | 984 | 1716 | 36.44%
120 | Roughin Labor | 139800 | 139800 | 177291.75 | -37491.75 | 126.8%
130 | Finish Labor | 31000 | 31000 | 34658.38 | -3658.38 | 111.8%
140 | Gas Labor | 3300 | 3300 | 2168 | 1132 | 65.7%
141 | Water Main/Insulation Lab | 41000 | 41000 | 15756 | 25244 | 38.43%
142 | Mech Room Labor | 3525 | 3525 | 9784 | -6259 | 277.6%
145 | Tub/Shower Labor | 19800 | 19800 | 6781 | 13019 | 34.25%
MATERIAL
039 | DS & RD Material | 17900 | 17900 | 5066.8 | 12833.2 | 28.31%
210 | Underground Material | 4300 | 4300 | 1635.51 | 2664.49 | 38.04%
211 | Garage Material | 11970 | 11970 | 6599.03 | 5370.97 | 55.13%
212 | Canout Material | 13130 | 13130 | 8579.19 | 4550.81 | 65.34%
213 | Foundation Material | 2700 | 2700 | 1789.12 | 910.88 | 66.26%
220 | Roughin Material | 161200 | 161200 | 94000.7 | 67199.3 | 58.31%
230 | Finish Material | 261600 | 269866 | 210145.22 | 59720.78 | 77.87%
240 | Gas Material | 3000 | 3000 | 996.32 | 2003.68 | 33.21%
241 | Water Main/Insulation Mat | 65600 | 65600 | 36964.67 | 28635.33 | 56.35%
242 | Mech Room Material | 12000 | 12000 | 22695.31 | -10695.31 | 189.1%
245 | Tub/Shower Material | 0 | 0 | 2278.99 | -2278.99 | 0%
OVERHEAD
600 | Subcontractor | 1000 | 1000 | 186 | 814 | 18.6%
601 | Engineering/Plans | 22000 | 22000 | 15682.03 | 6317.97 | 71.28%
603 | Permits & Licenses | 25600 | 10000 | 70.71 | 9929.29 | 0.7071%
BURDEN
995 | Payroll Burden | 125049.58 | 125049.58 | 126300.46 | -1250.88 | 101%
998 | Payroll Taxes | 22067.57 | 22067.57 | 22289.38 | -221.81 | 101%
TOTAL | Direct Cost | 1055092.15 | 1047758.15 | 846601.32 | 201156.83 | 80.8%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 13 | 305975 | 291321.88 | 14653.12 | 95.21% | 34.41% | 1787.2508
Material | 11 | 561666 | 390750.86 | 170915.14 | 69.57% | 46.16% | 2397.2445
Overhead | 3 | 33000 | 15938.74 | 17061.26 | 48.3% | 1.883% | 97.7837
Burden | 2 | 147117.15 | 148589.84 | -1472.69 | 101% | 17.55% | 911.5941
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 139800 | 177291.75 | 37491.75 | 26.82%
242 | Mech Room Material | 12000 | 22695.31 | 10695.31 | 89.13%
142 | Mech Room Labor | 3525 | 9784 | 6259 | 177.6%
111 | Garage Labor | 14600 | 19353.5 | 4753.5 | 32.56%
130 | Finish Labor | 31000 | 34658.38 | 3658.38 | 11.8%
245 | Tub/Shower Material | 0 | 2278.99 | 2278.99 | 0%
995 | Payroll Burden | 125049.58 | 126300.46 | 1250.88 | 1%
998 | Payroll Taxes | 22067.57 | 22289.38 | 221.81 | 1.005%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
220 | Roughin Material | 161200 | 94000.7 | 67199.3 | 41.69%
230 | Finish Material | 269866 | 210145.22 | 59720.78 | 22.13%
241 | Water Main/Insulation Mat | 65600 | 36964.67 | 28635.33 | 43.65%
141 | Water Main/Insulation Lab | 41000 | 15756 | 25244 | 61.57%
145 | Tub/Shower Labor | 19800 | 6781 | 13019 | 65.75%
039 | DS & RD Material | 17900 | 5066.8 | 12833.2 | 71.69%
603 | Permits & Licenses | 10000 | 70.71 | 9929.29 | 99.29%
011 | DS & RD Labor | 12500 | 3752.5 | 8747.5 | 69.98%
601 | Engineering/Plans | 22000 | 15682.03 | 6317.97 | 28.72%
112 | Canout Labor | 11700 | 5424 | 6276 | 53.64%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Material
Material Spend Analysis
11 material cost codes • $390,751 JDR material • 16 AP vendors • $409,755 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 17900 | 5066.8 | 12833.2 | 28.31% | 1.297% | 31.0847
210 | Underground Material | 4300 | 1635.51 | 2664.49 | 38.04% | 0.4186% | 10.0338
211 | Garage Material | 11970 | 6599.03 | 5370.97 | 55.13% | 1.689% | 40.4848
212 | Canout Material | 13130 | 8579.19 | 4550.81 | 65.34% | 2.196% | 52.6331
213 | Foundation Material | 2700 | 1789.12 | 910.88 | 66.26% | 0.4579% | 10.9762
220 | Roughin Material | 161200 | 94000.7 | 67199.3 | 58.31% | 24.06% | 576.6914
230 | Finish Material | 269866 | 210145.22 | 59720.78 | 77.87% | 53.78% | 1289.2345
240 | Gas Material | 3000 | 996.32 | 2003.68 | 33.21% | 0.255% | 6.1124
241 | Water Main/Insulation Mat | 65600 | 36964.67 | 28635.33 | 56.35% | 9.46% | 226.7771
242 | Mech Room Material | 12000 | 22695.31 | -10695.31 | 189.1% | 5.808% | 139.235
245 | Tub/Shower Material | 0 | 2278.99 | -2278.99 | 0% | 0.5832% | 13.9815
TOTAL | All Material | 561666 | 390750.86 | 170915.14 | 69.57% | 100% | 2397.2445
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Keller Supply Company | 45 | 154464.12 | 37.7% |  |  |  | 3432.536
Ferguson Enterprises, Inc. | 41 | 119072.08 | 29.06% |  |  |  | 2904.1971
Mechanical Sales, Inc. | 7 | 58896.52 | 14.37% |  |  |  | 8413.7886
Rosen Supply Company, Inc. | 54 | 39751.74 | 9.701% |  |  |  | 736.1433
Franklin Engineering | 4 | 15612.75 | 3.81% |  |  |  | 3903.1875
Bank of America CC | 6 | 9741.88 | 2.377% |  |  |  | 1623.6467
Quality Concrete Products, Inc. | 3 | 5806 | 1.417% |  |  |  | 1935.3333
Manor Hardware & Construction Supply | 7 | 1963.11 | 0.4791% |  |  |  | 280.4443
Patchworks, Inc. | 2 | 1837.5 | 0.4484% |  |  |  | 918.75
Capital One Credit Card | 8 | 1038.11 | 0.2533% |  |  |  | 129.7637
Rosen Supply Kirkland | 1 | 973.75 | 0.2376% |  |  |  | 973.75
Ferguson Enterprises, Inc. #3007 | 2 | 309.58 | 0.07555% |  |  |  | 154.79
R.A. Brown Backflow Testing | 1 | 186 | 0.04539% |  |  |  | 186
DRSi | 1 | 69.28 | 0.01691% |  |  |  | 69.28
American Express 3-41000 | 3 | 18.33 | 0.004473% |  |  |  | 6.11
C.M. Hoskins Company | 1 | 13.84 | 0.003378% |  |  |  | 13.84
TOTAL | 186 | 409754.59 | 100%
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
Vendor AP ties to JDR 'by Source: AP' line (409,754.59)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 1111 | 34877 | 31.3924 | Senior
Gonzalez Hernandez, Josue | 1001 | 12924 | 12.9111 | Apprentice
Lima Romero, Melvin A | 932 | 18140 | 19.4635 | Mid
Palma Vides, Hugo | 790 | 21434 | 27.1316 | Mid
Castro Hernandez, Jose A | 763 | 11903 | 15.6003 | Apprentice
Rivera, Eli P | 746 | 9192 | 12.3217 | Apprentice
Chavarria Lopez, Omar A | 738 | 9104 | 12.336 | Apprentice
Monico Brambila, Jesus S | 660 | 8620 | 13.0606 | Apprentice
Meza Fuentes, Erick A | 575.5 | 11510 | 20 | Mid
Rivera, Jorge A | 501 | 9018 | 18 | Mid
Paco Leyva, Orlando | 450.5 | 6319.25 | 14.0272 | Apprentice
Gerard, Jeffrey S | 406 | 14595 | 35.9483 | Senior
Veley, Nathaniel S | 381 | 10432 | 27.3806 | Mid
Ramos Garcia, Jose M | 363 | 4719 | 13 | Apprentice
Sanders, Allen O | 337.5 | 9751.5 | 28.8933 | Mid
Waites, Thaddeus Z | 319 | 8932 | 28 | Mid
Vega Arriaga, Jorge | 316 | 3803 | 12.0348 | Apprentice
Soto Cruz, Jovani | 280 | 4480 | 16 | Apprentice
Spears, Gregory M | 262 | 3406 | 13 | Apprentice
Soto Serna, Cesar E | 249 | 3237 | 13 | Apprentice
Castaneda Martinez, Gustavo | 248 | 6696 | 27 | Mid
Lopez Martinez, Abimael | 201 | 2412 | 12 | Apprentice
Castaneda Juarez, Edgar D | 197.25 | 2742.88 | 13.9056 | Apprentice
Cortes Mendiola, Victor H | 193 | 4619 | 23.9326 | Mid
Sepulveda Gonzalez, Alfredo | 176 | 4224 | 24 | Mid
Castro Hernandez, Carlos E | 171 | 4705 | 27.5146 | Mid
Vaughan, Tyler J | 168.5 | 2696 | 16 | Apprentice
Holmes, Anthony R | 162 | 2106 | 13 | Apprentice
Sanchez Garcia, Adelaido | 155 | 2015 | 13 | Apprentice
Velasquez Cruz, Denis M | 94 | 1222 | 13 | Apprentice
Agustin Rodriguez, Ezequiel | 83 | 996 | 12 | Apprentice
Arreola, Israel A | 42 | 609 | 14.5 | Apprentice
Rendon Villasenor, Ismael | 36 | 432 | 12 | Apprentice
Garcia, Jordan X | 32 | 448 | 14 | Apprentice
Wilson, Garret A | 32 | 416 | 13 | Apprentice
Barnhart, Joseph N | 11 | 323 | 29.3636 | Mid
McCabe, Thomas C | 8 | 144 | 18 | Mid
Castaneda Juarez, Gustavo | 7 | 91 | 13 | Apprentice
Hubbard, Dustin R | 5 | 60 | 12 | Apprentice
Hubbard, Robert W | 3.5 | 115.5 | 33 | Senior
TOTAL (40 workers) | 13206.75 | 253469.13 | 19.1924
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 1520.5 | 49587.5 | 11.51%
Mid | 13 | 4643 | 109928.5 | 35.16%
Apprentice | 24 | 7043.25 | 93953.13 | 53.33%
B. WAGE STATISTICS
Blended Gross Wage | 19.1924 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 33.3096 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.7356 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12 |  |  | Cheapest apprentice hour
Max Worker Rate | 35.9483 |  |  | Most expensive foreman hour
Avg Hours / Worker | 330.1687 |  |  | Crew continuity indicator
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 183 | 1.253% | 1.1227
Supervision | 100 | 165 | 1.13% | 1.0123
Takeoff & Purchasing | 101 | 172.5 | 1.181% | 1.0583
Underground | 110 | 145.5 | 0.9961% | 0.89264
Garage | 111 | 872 | 5.97% | 5.3497
Canout | 112 | 238 | 1.629% | 1.4601
Foundation Drain | 113 | 50 | 0.3423% | 0.30675
Roughin | 120 | 9319.5 | 63.8% | 57.1748
Finish | 130 | 1840.75 | 12.6% | 11.2929
Gas | 140 | 104 | 0.712% | 0.63804
Water Main / Insulation | 141 | 800 | 5.477% | 4.908
Mech Room | 142 | 379 | 2.595% | 2.3252
Tub / Shower | 145 | 338 | 2.314% | 2.0736
TOTAL |  | 14607.25 | 100% | 89.615
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 89.615 | hrs |  | Labor hours per residential unit
Hours / Fixture | 14.5491 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 95.2578 | $ |  | Top-line per labor hour
Profit / Hour | 37.3002 | $ |  | Bottom-line per labor hour
Units / Month | 9.5882 | units |  | Build velocity
Fixtures / Month | 59.0588 | fix |  | Fixture install pace
Hours / Month | 859.25 | hrs |  | Monthly labor burn
Revenue / Month | 81850.2941 | $ |  | Monthly billing rate
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## PO Commitments
Purchase Order Commitments
68 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $390,751
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 13 | 19.12%
31 | 120+220 Roughin | 14 | 20.59%
32 | 130+230 Trim/Finish | 7 | 10.29%
34 | 111+211 Garage | 1 | 1.471%
40 | 141+241 Water Main/Ins | 4 | 5.882%
41 | 140+240 Gas | 1 | 1.471%
OTHER | Unclassified | 28 | 41.18%
TOTAL |  | 68 | 100% | 390750.86
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
OTHER | 54 | 79.41%
ROSEN | 8 | 11.76%
MANOR | 2 | 2.941%
MECH SALES | 2 | 2.941%
KELLER | 1 | 1.471%
SIOUX CHIEF | 1 | 1.471%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 390750.86
Unique PO Count |  |  | 68
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
15 pay applications • Mar 2013 – Jul 2014 • $1,391,455 final
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1394655
Change Orders (net) |  |  |  |  | -3200
Final Contract Value |  |  |  |  | 1391455
Retainage (5%) |  |  |  |  | 69573
Net Paid to OWP |  |  |  |  | 1321882
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2013-03-19 | 48000 | 2400 | 45600 | 45600 | 3.277%
2 | 2013-04-18 | 41000 | 2050 | 38950 | 84550 | 6.076%
3 | 2013-05-20 | 16200 | 810 | 15390 | 99940 | 7.182%
4 | 2013-06-20 | 15900 | 795 | 15105 | 115045 | 8.268%
5 | 2013-07-20 | 25900 | 1295 | 24605 | 139650 | 10.04%
6 | 2013-08-20 | 92000 | 4600 | 87400 | 227050 | 16.32%
7 | 2013-09-20 | 213605 | 10680.25 | 202924.75 | 429974.75 | 30.9%
8 | 2013-10-17 | 440000 | 22000 | 418000 | 847974.75 | 60.94%
9 | 2013-11-19 | 228490 | 11424.5 | 217065.5 | 1065040.25 | 76.54%
10 | 2013-12-12 | 60560 | 3028 | 57532 | 1122572.25 | 80.68%
11 | 2014-01-20 | 106583 | 5329.15 | 101253.85 | 1223826.1 | 87.95%
12 | 2014-02-20 | 48805 | 2440.25 | 46364.75 | 1270190.85 | 91.29%
13 | 2014-03-20 | 49800 | 2490 | 47310 | 1317500.85 | 94.69%
14 | 2014-04-20 | 4612 | 230.6 | 4381.4 | 1321882.25 | 95%
15 | 2014-07-17 | 1861 | 0 | 1861 | 1323743.25 | 95.13%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1391455 | 1391455 | 0 | TIES
Retainage | 69573 | 69573 | 0 | TIES
Direct Cost | 846601 | 846601 | 0 | TIES
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Insights
Key Insights — Job #2012 Exxel Pacific 8th Ave Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $544,854 on $1,391,455 revenue = 39.2% gross margin. Direct cost $846,601 absorbs 60.8% of revenue.
VENDOR CONCENTRATION | Keller Supply Company alone = $154,464 (38% of all AP) across 45 invoices. Total 16 AP vendors, $409,755 total AP spend.
CREW PROFILE | 40 workers for 14,607 hours = 365 avg hrs/worker. Top 3 workers logged 3,044 hrs combined (21% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 9,320 hrs (64% of all labor) and $177,292 actual. Code 230 Finish Material = $210,145 — 25% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,047,758; actual direct cost $846,601 → $201,157 variance (19.2% under revised budget).
CONTRACT GROWTH | Contract grew from $1,394,655 to $1,391,455 — net +$-3,200 (-0.2%). Retainage of $69,573 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $148,590 on $291,322 labor base = 51.0%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 163 units · 1004 fixtures · 17 months. Revenue/unit $8,537, hours/unit 89.6, profit/unit $3,343.
PRODUCTIVITY | Blended labor rate $19.94/hr. Revenue/hour $95. Profit/hour $37. 859 hrs/month burn rate.
FIXTURE DENSITY | 1004 fixtures ÷ 163 units = 6.16 fixtures/unit. Material/fixture $389, labor/fixture $290.
BIGGEST QUESTION
How does this job's 39.2% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2012 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific 8th Ave Apartments | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile
Location | location | Seattle, WA (4545 8th Ave NE) | Profile
Project Type | project_type | 163-unit 9-story multifamily apartments + ground-floor retail | Profile
Duration (months) | duration_months | 17 | Profile | Mar 2013 – Jul 2014 (~17 months)
Unit Count | unit_count | 163 | Profile
Total Fixtures | total_fixtures | 1004 | Profile
Fixtures per Unit | fixtures_per_unit | 6.1595 | Profile
Contract Value (Orig) | contract_original | 1394655 | Financial
Contract Value (Final) | contract_final | 1391455 | Financial | After change orders
Change Orders ($) | change_orders | -3200 | Financial
Revenue | revenue | 1391455 | Financial
Net Profit | net_profit | 544853.68 | Financial
Gross Margin | gross_margin | 0.39157 | Financial
Direct Cost | direct_cost | 846601.32 | Financial
Labor Cost | labor_cost | 291321.88 | Labor | Sum of 13 labor codes
Material Cost | material_cost | 390750.86 | Material | Sum of 11 material codes
Overhead Cost | overhead_cost | 15938.74 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 148589.84 | Financial | Codes 995+998
Retainage | retainage | 69572.75 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 8536.5337 | Financial
Profit per Unit | profit_per_unit | 3342.6606 | Financial
Direct Cost per Unit | cost_per_unit | 5193.8731 | Financial
Labor Cost per Unit | labor_per_unit | 1787.2508 | Labor
Material Cost per Unit | material_per_unit | 2397.2445 | Material
Revenue per Fixture | revenue_per_fixture | 1385.9114 | Financial
Profit per Fixture | profit_per_fixture | 542.6829 | Financial
Cost per Fixture | cost_per_fixture | 843.2284 | Financial
Labor per Fixture | labor_per_fixture | 290.1612 | Labor
Material per Fixture | material_per_fixture | 389.1941 | Material
Total Labor Hours | total_hours | 14607.25 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 40 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1735% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3012% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.7356 | Labor
Hours per Unit | hours_per_unit | 8962% | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 1455% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 9526% | Productivity
Profit per Hour | profit_per_hour | 3730% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.20936 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.28082 | Cost Mix
Revenue per Month | revenue_per_month | 81850.2941 | Productivity
Hours per Month | hours_per_month | 859.25 | Productivity
Units per Month | units_per_month | 9.5882 | Productivity
Total Vendors | total_vendors | 16 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 154464.12 | Material | Keller Supply Company
Top Vendor Concentration | top_vendor_pct | 0.37697 | Material
Total POs | total_pos | 68 | Material | Unique POs by filename
Change Order % | co_pct | -0.0022945 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 9526% | Productivity
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (13 codes) | 291321.88 | 291321.88 | 0 | TIES
Material subtotal (11 codes) | 390750.86 | 390750.86 | 0 | TIES
Overhead subtotal (3 codes) | 15938.74 | 15938.74 | 0 | TIES
Burden subtotal (2 codes) | 148589.84 | 148589.84 | 0 | TIES
Direct Cost (all categories) | 846601.32 | 846601.32 | 0 | TIES
Revenue (code 999) | 1391455 | 1391455 | 0 | TIES
Net Profit (Revenue - Expenses) | 544853.68 | 544853.68 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 14607.25 | 14607.25 | 0 | TIES
Per-worker hours (sum of PR Regular) | 13206.75 | 14607.25 | -1400.5 | OFF
C. BILLING (SOV) ↔ JDR
Final Contract Value | 1391455 | 1391455 | 0 | TIES
Retainage | 69573 | 69573 | 0 | TIES
Direct Cost | 846601 | 846601 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 409754.59 | 409755 | -0.41 | TIES
SOURCES
Job #2012 — Exxel Pacific 8th Ave Apartments • GC: Exxel Pacific, Inc. • 4545 8th Ave NE, Seattle
Canonical source: 2012 Job Detail Report.pdf (135 pages, OWP Sage Timberline export)
Cost codes parsed: 30
Unit count (163) confirmed by plumbing permit SR1335240
Fixture count (1004) from permit detail: 163 WC + 163 lav + 163 shower + 163 sink + 163 DW + 163 washer + 5 floor drains + 18 roof drains + 1 indirect + 2 sump/ejector
Contract: One Way Plumbing contract executed (Exxel Pacific GC) with OWP markup
Billing: 8th AGGREGATE BILLING.xlsx (15 pay apps Mar 2013 – Jul 2014) + 15 SOV files
Final contract $1,391,455 (original $1,394,655 + $-3,200 COs)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2012
Vendors | 16 |  | Top vendor | Keller Supply Company
Invoices | 186 |  | Top 3 share | 81.13%
Total AP | 409754.59 |  | Source | 2012 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 2202.9817
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Keller Supply Company |  | 45 | 154464.12 | 37.7% | 3432.536
2 | Ferguson Enterprises, Inc. |  | 41 | 119072.08 | 29.06% | 2904.1971
3 | Mechanical Sales, Inc. |  | 7 | 58896.52 | 14.37% | 8413.7886
4 | Rosen Supply Company, Inc. |  | 54 | 39751.74 | 9.701% | 736.1433
5 | Franklin Engineering |  | 4 | 15612.75 | 3.81% | 3903.1875
6 | Bank of America CC |  | 6 | 9741.88 | 2.377% | 1623.6467
7 | Quality Concrete Products, Inc. |  | 3 | 5806 | 1.417% | 1935.3333
8 | Manor Hardware & Construction Supply |  | 7 | 1963.11 | 0.4791% | 280.4443
9 | Patchworks, Inc. |  | 2 | 1837.5 | 0.4484% | 918.75
10 | Capital One Credit Card |  | 8 | 1038.11 | 0.2533% | 129.7637
11 | Rosen Supply Kirkland |  | 1 | 973.75 | 0.2376% | 973.75
12 | Ferguson Enterprises, Inc. #3007 |  | 2 | 309.58 | 0.07555% | 154.79
13 | R.A. Brown Backflow Testing |  | 1 | 186 | 0.04539% | 186
14 | DRSi |  | 1 | 69.28 | 0.01691% | 69.28
15 | American Express 3-41000 |  | 3 | 18.33 | 0.004473% | 6.11
16 | C.M. Hoskins Company |  | 1 | 13.84 | 0.003378% | 13.84
| TOTAL |  | 186 | 409754.59 | 100% | 2202.9817