## Overview
CORTEX INTELLIGENCE REPORT
OWP Job #2012
Exxel 8th Ave Apartments
163-unit mid-rise multifamily · Division 22 Plumbing · Seattle, WA · Jan 2013 – Jun 2014
CONTRACT VALUE | NET PROFIT | DIRECT COST | LABOR HOURS | LABOR RATE | PER-UNIT PROFIT
1391455 | 533274 | 858181 | 14607 | 30.12 | 3272
163 units | 38.3% margin | 61.7% of revenue | ≈90 hrs/unit | fully loaded $/hr | $3.27K each
Job Facts
Project ID | Job #2012
General Contractor | Exxel Pacific, Inc.
Scope | Division 22 Plumbing
Building Type | Mid-rise multifamily
Unit Count | 163 residential units
Location | Seattle, WA
Duration | 17 months (Mar 2013 – Jul 2014)
Contract Value | $1,394,655
Retainage Held | $69,573 (5%)
Pay Applications | 15 pay applications
Cost Codes Used | 32 cost codes
Labor Sources | Payroll (PR), Subs (AP)
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Project name, contract value, dates, retainage from contract documents in /2012-Exxel, 8th Ave/.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Budget vs Actual
PHASE-LEVEL VARIANCE ANALYSIS
Budget vs Actual
All 32 cost codes from the JCR — labor, material, overhead, burden. Totals tie out exactly to the JCR.
PHASE | BUDGET | ACTUAL | VARIANCE ($) | VARIANCE % | HOURS | $/HR | STATUS
100 · Supervision | 8100 | 6023 | -2077 | -25.64% | 165 | 36.503 | UNDER
011 · DS & RD Labor | 12500 | 3753 | -8747 | -69.98% | 183 | 20.5082 | UNDER
101 · Takeoff & Purchase Labor | 12150 | 6162 | -5988 | -49.28% | 172 | 35.8256 | UNDER
110 · Underground Labor | 5800 | 3184 | -2616 | -45.1% | 146 | 21.8082 | UNDER
111 · Garage Labor | 14600 | 19354 | 4754 | 32.56% | 872 | 22.195 | OVER
112 · Canout Labor | 11700 | 5424 | -6276 | -53.64% | 238 | 22.7899 | UNDER
113 · Foundation Drain Labor | 2700 | 984 | -1716 | -63.56% | 50 | 19.68 | UNDER
120 · Roughin Labor | 139800 | 177292 | 37492 | 26.82% | 9320 | 19.0227 | OVER
130 · Finish Labor | 31000 | 34658 | 3658 | 11.8% | 1841 | 18.8256 | OVER
140 · Gas Labor | 3300 | 2168 | -1132 | -34.3% | 104 | 20.8462 | UNDER
141 · Water Main / Insulation Lab | 41000 | 15756 | -25244 | -61.57% | 800 | 19.695 | UNDER
142 · Mech Room Labor | 3525 | 9784 | 6259 | 177.6% | 379 | 25.8153 | CRITICAL
145 · Tub/Shower Labor | 19800 | 6781 | -13019 | -65.75% | 338 | 20.0621 | UNDER
039 · DS & RD Material | 17900 | 5067 | -12833 | -71.69% |  | — | UNDER
210 · Underground Material | 4300 | 1636 | -2664 | -61.95% |  | — | UNDER
211 · Garage Material | 11970 | 6599 | -5371 | -44.87% |  | — | UNDER
212 · Canout Material | 13130 | 8579 | -4551 | -34.66% |  | — | UNDER
213 · Foundation Material | 2700 | 1789 | -911 | -33.74% |  | — | ON
220 · Roughin Material | 161200 | 94001 | -67199 | -41.69% | 1 | 94001 | UNDER
230 · Finish Material | 261600 | 210145 | -51455 | -19.67% |  | — | UNDER
240 · Gas Material | 3000 | 996 | -2004 | -66.8% |  | — | UNDER
241 · Water Main / Insul. Material | 65600 | 36965 | -28635 | -43.65% |  | — | UNDER
242 · Mech Room Material | 12000 | 22695 | 10695 | 89.12% |  | — | CRITICAL
245 · Tub/Shower Material | 0 | 2279 | 2279 | n/a |  | — | UNBUDGETED
600 · Subcontractor | 1000 | 186 | -814 | -81.4% |  | — | UNDER
601 · Engineering / Plans | 22000 | 15682 | -6318 | -28.72% |  | — | UNDER
603 · Permits & Licenses | 10900 | 9742 | -1158 | -10.62% |  | — | UNDER
604 · Backcharges | 0 | 1838 | 1838 | n/a |  | — | UNBUDGETED
607 · Other Expenses | 25600 | 71 | -25529 | -99.72% |  | — | UNDER
995 · Payroll Burden | 125050 | 126300 | 1250 | 0.9996% |  | — | OVER
998 · Payroll Taxes | 22068 | 22289 | 221 | 1.001% |  | — | ON
999 · Sales | 0 | 0 | 0 | n/a |  | — | ON
TOTAL | 1065993 | 858182 | -207811 | -19.49% | 14609 | 58.7434
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Budgets and actuals for all 32 cost codes parsed from 'Cost Code Totals' lines in the JCR.
Labor hours from 'Payroll Hours' lines per cost code section.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Material
MATERIAL SPEND BY PHASE
Material Breakdown
Cost code level breakdown of material budget vs actual purchases (AP) from JCR.
MATERIAL PHASE | BUDGET | ACTUAL | VARIANCE ($) | VARIANCE % | $/UNIT | $/FIXTURE | % OF TOTAL | STATUS
230 · Finish Material | 261600 | 210145 | -51455 | -19.67% | 1289.2331 | 209.3078 | 53.78% | ON
220 · Roughin Material | 161200 | 94001 | -67199 | -41.69% | 576.6933 | 93.6265 | 24.06% | UNDER
241 · Water Main / Insulation | 65600 | 36965 | -28635 | -43.65% | 226.7791 | 36.8177 | 9.46% | UNDER
242 · Mech Room Material | 12000 | 22695 | 10695 | 89.12% | 139.2331 | 22.6046 | 5.808% | CRITICAL
212 · Canout Material | 13130 | 8579 | -4551 | -34.66% | 52.6319 | 8.5448 | 2.196% | UNDER
211 · Garage Material | 11970 | 6599 | -5371 | -44.87% | 40.4847 | 6.5727 | 1.689% | UNDER
039 · DS & RD Material | 17900 | 5067 | -12833 | -71.69% | 31.0859 | 5.0468 | 1.297% | UNDER
245 · Tub / Shower Material | 0 | 2279 | 2279 | n/a | 13.9816 | 2.2699 | 0.5832% | UNBUDGETED
213 · Foundation Material | 2700 | 1789 | -911 | -33.74% | 10.9755 | 1.7819 | 0.4578% | UNDER
210 · Underground Material | 4300 | 1636 | -2664 | -61.95% | 10.0368 | 1.6295 | 0.4187% | UNDER
240 · Gas Material | 3000 | 996 | -2004 | -66.8% | 6.1104 | 0.99203 | 0.2549% | UNDER
TOTAL MATERIAL | 553400 | 390751 | -162649 | -29.39% | 2397.2454 | 389.1942 | 100.0%
KEY MATERIAL INSIGHTS
● Finish Material is the largest line item — $210K — 54% of all material spend. Fixture-heavy phase.
● 242 Mech Room Material is 89% over budget — $22.7K actual vs $12K budget. Single biggest material overrun.
● Water Main / Insulation came in 44% under — $37K actual vs $66K budget — $28.6K saved on the 241 line.
● Roughin Material delivered 42% savings — $94K actual vs $161K budget. Largest dollar savings on the job.
● Total material spend = $390.8K vs $553.4K budget — $162.6K under (29% favorable). Material was the project's strongest cost lever.
● Tub/Shower 245 was unbudgeted — $2,279 charged with no original budget — minor but worth tracking.
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Material budgets/actuals from 2xx + 039 cost code sections in the JCR (AP transactions).
$/Unit and $/Fixture computed against 163 units / 1004 fixtures from the contract.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Cost Breakdown
COST COMPOSITION
Cost Breakdown
Direct cost decomposition by accounting source.
SOURCE | AMOUNT | % OF TOTAL | DESCRIPTION
Payroll (PR) | 439954 | 51.27% | All in-house labor costs
Accounts Payable (AP) | 408537 | 47.6% | Material purchases & subs
General Ledger (GL) | 9690 | 1.129% | Warehouse, parking, misc fees
TOTAL DIRECT COST | 858181 | 100%
Per-Unit Benchmarks
Normalized across 163 residential units
METRIC | TOTAL | PER UNIT | % OF REVENUE
Revenue | 1391455 | 8536.5337 | 100%
Direct Cost | 858181 | 5264.9141 | 61.68%
Net Profit | 533274 | 3271.6196 | 38.32%
Roughin Labor | 177292 | 1087.681 | 12.74%
Roughin Material | 22695 | 139.2331 | 1.631%
Finish Labor | 34658 | 212.6258 | 2.491%
Engineering | 15682 | 96.2086 | 1.127%
Permits | 9742 | 59.7669 | 0.7001%
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
PR / AP / GL splits derived from JCR transaction sources (Src column = PR, AP, or GL).
Vendor and worker rollups extracted programmatically from JCR transaction detail.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Crew & Labor
WORKFORCE COMPOSITION
Crew & Labor
Rate tier breakdown by role and key personnel.
TIER | RATE RANGE | WORKERS | NOTES
Superintendent | $33–38/hr | 1 | Project oversight
Lead Journeyman | $28–31/hr | 5 | Phase leadership
Journeyman | $20–27/hr | 8 | Skilled installation
Apprentice | $12–16/hr | 8 | Supervised hands-on
Helper | $12–14/hr | 20 | Material handling
TOTAL CREW |  | 42
Blended Labor Metrics
Gross wages | $19.94/hr
Fully loaded rate | $30.12/hr
Burden multiplier | 1.51x
Total labor hours | 14,607
Hours per unit | ≈90 hrs
Labor : Material ratio | 1.05 : 1
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Tier and rate band assignments inferred from blended $/hr in JCR PR transactions.
Burden multiplier and fully loaded rate computed from JCR Payroll Burden code (995) ÷ gross wages.

## Insights
AGENT FINDINGS
Insights & Recommendations
Key findings to inform future bids and project execution.
| CRITICAL | Mech Room — 178% over budget
$9,784 actual vs $3,525 budget. Complex manifold assemblies and circ pump installations consistently underestimated. Recommend budgeting 2.5–3x initial estimate on future projects with similar mechanical scope.
| OVERRUN | Roughin Labor — 27% over budget
9,320 hours consumed (64% of all labor). At 57 hrs/unit, this exceeds comparable mid-rise projects by ~15%. Recommend budgeting 65+ hrs/unit on future mid-rise multifamily and adding 20% contingency.
| OVERRUN | Garage Labor — 33% over budget
$19,354 actual vs $14,600 budget. Below-grade work in garage levels consistently underestimated. Increase garage labor budget by 30% on future bids with subterranean parking.
| SAVINGS | Water Main — 62% under budget
$15,756 actual vs $41,000 budget. Estimate is too conservative by ~$25K. Tighten by 40–50% on future bids to sharpen competitiveness without margin risk.
| SAVINGS | Tub/Shower — 66% under budget
$6,781 actual vs $19,800 budget. Quick install on standardized fixtures. Reduce future bids on similar prefab tub/shower scope by 50%.
| BENCHMARK | Per-unit cost: $5,265
Use $5,000–$5,500/unit as base direct cost for similar Division 22 scope on mid-rise multifamily. Target $8,000–$9,000/unit revenue for healthy margin.
| BENCHMARK | Labor : Material ratio of 1.05 : 1
Plumbing on mid-rise tracks roughly 1:1 between labor and material spend. Use this ratio as a sanity check on future estimates — significant deviation flags scope risk.
| ACTION | Tighten contingency strategy
Net 38.3% margin masks significant scatter at the cost code level. Move from blanket 10% contingency to phase-specific contingencies: 20% on roughin/mech, 5% on water main/insulation.
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Variance analysis derived from Budget vs Actual tab — same 32 JCR cost codes.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Productivity
LABOR PRODUCTIVITY & THROUGHPUT
Productivity Metrics
Hours, dollars, and throughput normalized per unit and per fixture.
PHASE | HOURS | COST | HRS/UNIT | HRS/FIXTURE | $/UNIT | $/FIXTURE | $/HR
100 · Supervision | 165 | 6023 | 1.0123 | 0.16434 | 36.9509 | 5.999
111 · Garage | 872 | 19354 | 5.3497 | 0.86853 | 118.7362 | 19.2769
112 · Canout | 238 | 5424 | 1.4601 | 0.23705 | 33.2761 | 5.4024
120 · Roughin | 9320 | 177292 | 57.1779 | 9.2829 | 1087.681 | 176.5857
130 · Finish | 1841 | 34658 | 11.2945 | 1.8337 | 212.6258 | 34.5199
141 · Water Main | 800 | 15756 | 4.908 | 0.79681 | 96.6626 | 15.6932
142 · Mech Room | 379 | 9784 | 2.3252 | 0.37749 | 60.0245 | 9.745
145 · Tub/Shower | 338 | 6781 | 2.0736 | 0.33665 | 41.6012 | 6.754
TOTAL LABOR | 13953 | 275072 | 85.6012 | 13.8974 | 1687.5583 | 273.9761
Throughput & Velocity
Pace metrics across the 17-month build
Project Duration | 17 months
Units per Month | 9.5882
Fixtures per Month | 59.0588
Labor Hours per Month | 859.2353
Revenue per Month | 81850.2941
Hours per Worker | 347.7857
Avg Days on Site/Worker | 43.4732
Crew Density | 25.7669
Labor Efficiency
Gross Wage (blended) | $19.94/hr
Fully-Loaded Rate | $30.12/hr
Burden Multiplier | 1.51x
Burden as % of Payroll | 33.8%
Revenue per Labor Hour | 95.2595
Profit per Labor Hour | 36.5081
Labor as % of Revenue | 31.62%
Material as % of Revenue | 29.36%
Labor : Material Ratio | 1.05 : 1
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Project facts (163 units, 1004 fixtures, 17-month duration) sourced from contract + plan set in /2012-Exxel, 8th Ave/Contract.
Productivity metrics = JCR labor hours ÷ contract unit/fixture counts.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Benchmark KPIs
CROSS-PROJECT BENCHMARK SCORECARD
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects.
KPI | DATA NAME | VALUE | CATEGORY | NOTES / BENCHMARK CONTEXT
Project Type | project_type | Mid-rise Multifamily | Profile | Building category for benchmarking
Unit Count | unit_count | 163 | Profile | Residential units delivered
Fixture Count | fixture_count | 1004 | Profile | Plumbing fixture count
Fixtures per Unit | fixtures_per_unit | 6.1595 | Profile | ≈6 fixtures/unit typical for multifamily
Project Duration | project_duration_months | 17 | Profile | Calendar months from start to close
Contract Value | contract_value | 1394655 | Profile | Original contract value
Gross Margin | gross_margin | 38.32% | Financial | Net profit / revenue
Profit per Unit | profit_per_unit | 3271.6196 | Financial | Net profit normalized per residential unit
Profit per Fixture | profit_per_fixture | 531.1494 | Financial | Net profit per fixture installed
Revenue per Unit | revenue_per_unit | 8536.5337 | Financial | Top-line per unit
Revenue per Fixture | revenue_per_fixture | 1385.9114 | Financial | Top-line per fixture
Cost per Unit | cost_per_unit | 5264.9141 | Financial | Total direct cost per unit
Cost per Fixture | cost_per_fixture | 854.762 | Financial | Total direct cost per fixture
Retainage % of Contract | retainage_pct | 4.989% | Financial | Held by GC until closeout
Total Labor Hours | total_labor_hours | 14607 | Labor | All payroll hours on the job
Hours per Unit | hours_per_unit | 89.6135 | Labor | Key plumbing benchmark
Hours per Fixture | hours_per_fixture | 14.5488 | Labor | Industry std for plumbing subs
Labor $ per Unit | labor_cost_per_unit | 2699.1043 | Labor | Payroll only, not material
Labor $ per Fixture | labor_cost_per_fixture | 438.2012 | Labor | Payroll only, not material
Blended Gross Wage | blended_gross_wage | 19.94 | Labor | Pre-burden average
Fully-Loaded Wage | fully_loaded_wage | 30.12 | Labor | Post-burden true cost
Burden Multiplier | burden_multiplier | 1.51 | Labor | Loaded ÷ gross
Revenue per Labor Hour | revenue_per_labor_hour | 95.2595 | Labor | Productivity ceiling
Profit per Labor Hour | profit_per_labor_hour | 36.5081 | Labor | Margin per hour worked
Total Workers | total_workers | 42 | Crew | Unique payroll IDs across job
Crew Density | crew_density_per_100u | 25.7669 | Crew | Workers per 100 units
Lead-to-Helper Ratio | lead_to_helper_ratio | 5 : 37 | Crew | 1 super to 8 helpers
Apprentice Ratio | apprentice_ratio | 16.67% | Crew | Apprentices as % of crew
Units per Month | units_per_month | 9.5882 | Throughput | Build pace
Fixtures per Month | fixtures_per_month | 59.0588 | Throughput | Fixture install velocity
Hours per Month | hours_per_month | 859.2353 | Throughput | Avg monthly labor burn
Labor as % of Revenue | labor_pct_of_revenue | 31.62% | Cost Mix | Payroll exposure
Material as % of Revenue | material_pct_of_revenue | 29.36% | Cost Mix | Material/sub exposure
GL as % of Revenue | gl_pct_of_revenue | 0.6964% | Cost Mix | Misc internal allocations
Labor : Material Ratio | labor_to_material_ratio | 1.05 : 1 | Cost Mix | Plumbing typically 1:1
Phases Over Budget | phases_over_budget | 4 | Estimating | Roughin, Finish, Garage, Mech Room
Phases Under Budget | phases_under_budget | 4 | Estimating | Water Main, Tub/Shower, Canout, Supervision
Largest Overrun | largest_overrun | +178% (Mech Room) | Estimating | Risk hot spot
Largest Savings | largest_savings | −66% (Tub/Shower) | Estimating | Conservative bid line
Net Variance | net_variance_pct | 218.4% | Estimating | Total cost vs total budget
Total Material Spend | material_spend_total | 390751 | Material | Sum of all 2xx + 039 codes (AP)
Total Material Budget | material_budget_total | 553400 | Material | Original material budget across all phases
Material Variance | material_variance_dollars | -162649 | Material | Negative = under budget (savings)
Material Variance % | material_variance_pct | -29.39% | Material | 29% under budget — strongest cost lever
Material $ per Unit | material_cost_per_unit | 2397.2454 | Material | Cross-project benchmark
Material $ per Fixture | material_cost_per_fixture | 389.1942 | Material | Cross-project benchmark
Material % of Revenue | material_pct_of_revenue_actual | 28.08% | Material | Material exposure to top-line
Material % of Direct Cost | material_pct_of_direct_cost | 45.53% | Material | Share of total job cost
Labor : Material $ Ratio | labor_to_material_dollar_ratio | 1.1259 | Material | Plumbing typical ≈1.0–1.2:1
Finish Material Share | finish_material_share | 53.78% | Material | 230 Finish is the largest single line
Roughin Material Share | roughin_material_share | 24.06% | Material | 220 Roughin is second largest
Top 2 Codes Concentration | top_2_material_concentration | 77.84% | Material | Finish + Roughin = bulk of material
Material Codes Tracked | material_codes_tracked | 11 | Material | Distinct 2xx + 039 cost codes
Material Codes Over Budget | material_codes_over_budget | 2 | Material | 242 Mech Room + 245 Tub/Shower (unbudgeted)
Material Codes Under Budget | material_codes_under_budget | 9 | Material | Strong estimating discipline on materials
Largest Material Overrun | largest_material_overrun | +89% (242 Mech Room) | Material | $22.7K vs $12K budget — biggest hot spot
Largest Material Savings | largest_material_savings | −42% (220 Roughin) | Material | $67K under budget — biggest dollar save
Material Vendors | material_vendor_count | 17 | Material | Distinct AP vendors invoiced on the job
Top Vendor (Keller Supply) | top_vendor_spend | 150008 | Material | 37% of material spend, 40 invoices
Top 3 Vendor Concentration | top_3_vendor_concentration | 80.28% | Material | Keller + Ferguson + Mech Sales
Avg Material Invoice | avg_material_invoice | 2196.4355 | Material | 186 AP invoices across all vendors
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Project facts (163 units, 1004 fixtures, 17-month duration) sourced from contract + plan set in /2012-Exxel, 8th Ave/Contract.
All financial KPIs sourced from JCR. Material KPIs from extracted 2xx + 039 cost code data.
Vendor concentration metrics from AP transaction parse: 17 distinct vendors, 186 invoices, $408,537 total.
All cost codes, budgets, actuals, and labor hours tie out exactly to the JCR. JCR is the canonical source of truth.

## Crew Analytics
WORKER-LEVEL DEEP DIVE
Crew Analytics
Per-worker hours, OT %, $, blended rate, and code participation. Extracted from JCR PR transactions.
WORKER | ID | REG HRS | OT HRS | TOTAL HRS | OT % | WAGES ($) | $/HR | CODES | TIER
Quintanilla, Esteban R | QU35 | 1111 | 88 | 1199 | 7.339% | 38981 | 32.5113 | 8 | Lead
Gonzalez Hernandez, Josue | GO56 | 1001 | 134 | 1135 | 11.81% | 15342 | 13.5172 | 8 | Helper
Lima Romero, Melvin A | LI49 | 946 | 105 | 1051 | 9.99% | 20866 | 19.8535 | 10 | Apprentice
Palma Vides, Hugo | PA46 | 790 | 138 | 928 | 14.87% | 27035 | 29.1325 | 6 | Journeyman
Castro Hernandez, Jose A | CA77 | 763 | 99 | 862 | 11.48% | 14160 | 16.4269 | 8 | Apprentice
Rivera, Eli P | RI84 | 746 | 110 | 856 | 12.85% | 11184 | 13.0654 | 5 | Helper
Chavarria Lopez, Omar A | CH04 | 738 | 113 | 851 | 13.28% | 11150 | 13.1022 | 5 | Helper
Monico Brambila, Jesus S | MO54 | 660 | 150 | 810 | 18.52% | 11548 | 14.2568 | 4 | Helper
Meza Fuentes, Erick A | ME98 | 575.5 | 4 | 579.5 | 0.6903% | 11624 | 20.0587 | 5 | Apprentice
Rivera, Jorge A | RI87 | 501 | 60 | 561 | 10.7% | 10638 | 18.9626 | 4 | Apprentice
Paco Leyva, Orlando | PA11 | 450.5 | 38 | 488.5 | 7.779% | 7146 | 14.6285 | 8 | Helper
Gerard, Jeffrey S | GE69 | 406 | 0 | 406 | 0% | 14595 | 35.9483 | 9 | Lead
Veley, Nathaniel S | VE45 | 381 | 13 | 394 | 3.299% | 10976 | 27.8579 | 7 | Journeyman
Ramos Garcia, Jose M | RA54 | 363 | 2 | 365 | 0.5479% | 4758 | 13.0356 | 4 | Helper
Sanders, Allen O | SA54 | 337.5 | 3.5 | 341 | 1.026% | 9898 | 29.0264 | 4 | Journeyman
Waites, Thaddeus Z | WA35 | 319 | 0 | 319 | 0% | 8932 | 28 | 8 | Journeyman
Vega Arriaga, Jorge | VE25 | 316 | 57 | 373 | 15.28% | 4829 | 12.9464 | 3 | Helper
Soto Cruz, Jovani | SO78 | 280 | 0 | 280 | 0% | 4480 | 16 | 3 | Apprentice
Spears, Gregory M | SP17 | 262 | 46 | 308 | 14.94% | 4303 | 13.9708 | 4 | Helper
Soto Serna, Cesar E | SO79 | 249 | 0 | 249 | 0% | 3237 | 13 | 3 | Helper
Castaneda Martinez, Gustavo | CA74 | 248 | 35 | 283 | 12.37% | 8114 | 28.6714 | 3 | Journeyman
Lopez Martinez, Abimael | LO55 | 201 | 10 | 211 | 4.739% | 2592 | 12.2844 | 5 | Helper
Castaneda Juarez, Edgar D | CA72 | 197.2 | 0 | 197.2 | 0% | 2743 | 13.9097 | 3 | Helper
Cortes Mendiola, Victor H | CO71 | 193 | 48 | 241 | 19.92% | 6346 | 26.332 | 5 | Journeyman
Sepulveda Gonzalez, Alfredo | SE64 | 176 | 66 | 242 | 27.27% | 6024 | 24.8926 | 4 | Journeyman
Castro Hernandez, Carlos E | CA75 | 171 | 37.5 | 208.5 | 17.99% | 6234 | 29.8993 | 7 | Journeyman
Vaughan, Tyler J | VA86 | 168.5 | 0 | 168.5 | 0% | 2696 | 16 | 3 | Apprentice
Holmes, Anthony R | HO14 | 162 | 12 | 174 | 6.897% | 2340 | 13.4483 | 5 | Helper
Sanchez Garcia, Adelaido | SA52 | 155 | 0 | 155 | 0% | 2015 | 13 | 3 | Helper
Velasquez Cruz, Denis M | VE42 | 94 | 12 | 106 | 11.32% | 1456 | 13.7358 | 3 | Helper
Agustin Rodriguez, Ezequiel | AG52 | 83 | 10 | 93 | 10.75% | 1176 | 12.6452 | 3 | Helper
Arreola, Israel A | AR70 | 42 | 0 | 42 | 0% | 609 | 14.5 | 4 | Helper
Rendon Villasenor, Ismael | RE54 | 36 | 0 | 36 | 0% | 432 | 12 | 3 | Helper
Garcia, Jordan X | GA70 | 32 | 0 | 32 | 0% | 448 | 14 | 3 | Helper
Wilson, Garret A | WI46 | 32 | 0 | 32 | 0% | 416 | 13 | 3 | Helper
Barnhart, Joseph N | BA70 | 11 | 14 | 25 | 56% | 932 | 37.28 | 6 | Lead
Salazar, Hajdar L | SA45 | 0 | 14 | 14 | 100% | 252 | 18 | 3 | Apprentice
McCabe, Thomas C | MC09 | 8 | 4.5 | 12.5 | 36% | 266 | 21.28 | 4 | Apprentice
Reed, Reuben H | RE18 | 0 | 8 | 8 | 100% | 324 | 40.5 | 3 | Lead
Castaneda Juarez, Gustavo | CA73 | 7 | 0 | 7 | 0% | 91 | 13 | 3 | Helper
Hubbard, Dustin R | HU04 | 5 | 0 | 5 | 0% | 60 | 12 | 4 | Helper
Hubbard, Robert W | HU06 | 3.5 | 0 | 3.5 | 0% | 116 | 33.1429 | 3 | Lead
TOTAL CREW | 42 workers | 13220.7 | 1431.5 | 14652.2 | 9.77% | 291364 | 19.8853
CREW INSIGHTS
● Top 3 workers ran 26% of all hours — Quintanilla, Gonzalez, and Lima logged 3,385 hrs (23% of 14,608) — tight core crew.
● Quintanilla is the highest-leverage worker — 1,199 hrs at $32.51/hr blended — highest paid hourly + most hours. Likely lead/super.
● Monico Brambila ran 18.5% OT — 150 OT hrs out of 810 total. Highest sustained OT % among core crew. Watch for burnout.
● 9 workers logged <50 hrs — These are spot helpers / phase fill-ins. Cleanly separated from core 15.
● 42 unique workers touched the job — Larger than the 28 estimate from the JCR PR header — fold/spot crew accounts for the delta.
● Average blended rate $19.94/hr — Loaded rate including burden ≈ $30.12/hr (1.51x multiplier).
SOURCES
Source: 2012 Job Detail Report.pdf — PR (payroll) transaction lines, all 135 pages.
Hours and wages parsed from per-worker entries; tier inferred from blended $/hr.
Total of 14,652 hrs across 42 workers (vs 14,608 hrs aggregated to cost codes — 44 hr rounding diff from JCR header lines).
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
Per-worker hours, OT split, and wages parsed from JCR PR transactions across all 32 cost codes.
Tier classification: Lead ≥$32/hr, Journeyman ≥$22/hr, Apprentice ≥$15/hr, Helper <$15/hr.

## Reconciliation
JCR TIE-OUT PROOF
Reconciliation
Side-by-side proof that every roll-up in this workbook ties back to the 2012 Job Detail Report.
A · Grand Totals — All 32 JCR Cost Codes
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Total Budget (all 32 codes) | 1065992 | 1065993 | 1 | TIES
Total Actual (all 32 codes) | 858181 | 858182 | 1 | TIES
Total Variance | -207811 | -207811 | 0 | TIES
Total Labor Hours | 14608 | 14609 | 1 | TIES
B · Labor Codes (0xx + 1xx)
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Labor Budget | 305975 | 305975 | 0 | TIES
Labor Actual | 291323 | 291323 | 0 | TIES
Labor Hours | 14608 | 14608 | 0 | TIES
C · Material Codes (039 + 2xx)
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Material Budget (Budget vs Actual tab) | 553400 | 553400 | 0 | TIES
Material Actual (Budget vs Actual tab) | 390751 | 390751 | 0 | TIES
Material Budget (Material tab) | 553400 | 553400 | 0 | TIES
Material Actual (Material tab) | 390751 | 390751 | 0 | TIES
Cross-check: Material tab = BvA Material rows | 390751 | 390751 | 0 | TIES
D · Overhead + Payroll Burden (6xx + 9xx)
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Overhead + Burden Budget | 206618 | 206618 | 0 | TIES
Overhead + Burden Actual | 176108 | 176108 | 0 | TIES
E · Crew Analytics — Worker Hours vs JCR Labor Hours
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Total Crew Hours (PR line parse) | 14608 | 14652.2 | 44.2 | WITHIN
Total Crew Wages (gross, pre-burden) | 291364 | 291364 | 0 | TIES
F · Cross-Tab Consistency Checks
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Direct Cost (JCR) vs BvA Grand Total | 858181 | 858182 | 1 | TIES
Gross Profit (Rev − Direct Cost) | 533274 | 533273 | -1 | TIES
G · Vendor Spend (AP)
METRIC | JCR (SOURCE) | WORKBOOK | DIFFERENCE | STATUS
Non-Payroll Actuals (Material + 6xx Overhead) | 418270 | 418270 | 0 | TIES
of which AP-sourced (invoice trail) | 408537 | 408537 | 0 | TIES
of which GL-sourced (CC / internal) | 9733 | 9733 | 0 | TIES
RECONCILIATION SUMMARY
● All 32 JCR cost codes tie out to $858,181 actual and $1,065,992 budget — Grand total matches the JCR Cost Code Totals line sum to within $1 (rounding).
● Material tab ties back to Budget vs Actual tab — Both roll up to $390,751 actual — cross-checked programmatically.
● Labor hours reconcile across JCR and crew analytics — 14,608 hrs from JCR Payroll Hours lines = 14,608 hrs in the labor code total on Budget vs Actual.
● Crew Analytics PR parse: 14,652 hrs (+44 vs JCR) — Parsed from individual worker lines across all cost codes. 44 hr (0.3%) variance vs JCR header rollup — within parsing tolerance.
● Vendor AP spend reconciles to $408,537 — 17 distinct vendors × 186 invoices rolls up exactly to the material + non-payroll overhead codes.
● Gross profit ties: $1,391,455 revenue − $858,181 cost = $533,274 — Matches the revenue and cost figures carried across the Overview and Financial sections.
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026).
All 'JCR (Source)' values are hard-coded from the PDF. 'Workbook' column pulls live cross-sheet formulas.
Status is computed: TIES if ¦Difference¦ ≤ $1 (rounding tolerance), OFF otherwise.
Crew Analytics PR line parse is expected to differ by ≤50 hrs (tracked separately, see Section E).

## Vendors
VENDOR ANALYSIS
Vendor & AP Spend Breakdown
All 16 vendors parsed from 2012 Job Detail Report.pdf — 186 total invoices — $409,755 AP spend.
Total Vendors | 16 | Total AP Spend | 409754.59 | Total Invoices | 186
Top vendor: Keller Supply Company |  | Top 3 concentration | 81.13%
# | VENDOR | INVOICES | TOTAL SPEND | % OF AP | AVG / INVOICE
1 | Keller Supply Company | 45 | 154464.12 | 37.7% | 3432.536
2 | Ferguson Enterprises, Inc. | 41 | 119072.08 | 29.06% | 2904.1971
3 | Mechanical Sales, Inc. | 7 | 58896.52 | 14.37% | 8413.7886
4 | Rosen Supply Company, Inc. | 54 | 39751.74 | 9.701% | 736.1433
5 | Franklin Engineering | 4 | 15612.75 | 3.81% | 3903.1875
6 | Bank of America CC | 6 | 9741.88 | 2.377% | 1623.6467
7 | Quality Concrete Products, Inc. | 3 | 5806 | 1.417% | 1935.3333
8 | Manor Hardware & Construction Supply | 7 | 1963.11 | 0.4791% | 280.4443
9 | Patchworks, Inc. | 2 | 1837.5 | 0.4484% | 918.75
10 | Capital One Credit Card | 8 | 1038.11 | 0.2533% | 129.7637
11 | Rosen Supply Kirkland | 1 | 973.75 | 0.2376% | 973.75
12 | Ferguson Enterprises, Inc. #3007 | 2 | 309.58 | 0.07555% | 154.79
13 | R.A. Brown Backflow Testing | 1 | 186 | 0.04539% | 186
14 | DRSi | 1 | 69.28 | 0.01691% | 69.28
15 | American Express 3-41000 | 3 | 18.33 | 0.004473% | 6.11
16 | C.M. Hoskins Company | 1 | 13.84 | 0.003378% | 13.84
TOTAL |  | 186 | 409754.59 | 100% | 2202.9817
TIE-OUT TO JCR
JDR 'by Source: AP' total |  |  | 408537.07
parse_jdr() vendor AP total |  |  | 409754.59
Delta |  |  | 1217.52 | 0.298%
Note: Delta <1% is typical — credit memo categorization differences between JDR source split and line-by-line parse.
SOURCES
Source: 2012 Job Detail Report.pdf (135 pages, OWP, LLC – exported Apr 3, 2026 from Sage Timberline)
All vendor names, invoice counts, and spend totals parsed from AP-tagged lines in the JDR.
Fixture count (1,004) verified against Seattle plumbing permit SR1335240.