## Overview
Job #2015 · Exxel Pacific Rooster Apts + Portage Bay Cafe
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA • Mixed-use 6-story apartments + ground-floor restaurant TI • Apr 2014 – Nov 2015 (~25 months)
PROJECT OVERVIEW
Project Job # | 2015
Project Name: | Exxel Pacific Rooster Apts + Portage Bay Cafe
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA
Project Duration | Apr 2014 – Nov 2015 (~25 months)
Total Unique Documents | Multiple folders across Rooster + PBC
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$2,146,708 |  | $563,703 |  | $1,583,005 |  | 28,661
Original $2,002,285 + $144,423 COs |  | 26.3% margin |  | 73.7% of revenue |  | 53 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 479050 | 583482.62 | -104432.62 | 121.8% | 36.86%
Material | 866894 | 661468.33 | 205425.67 | 76.3% | 41.79%
Overhead | 34425 | 43335.38 | -8910.38 | 125.9% | 2.738%
Burden | 242802.91 | 294718.23 | -51915.32 | 121.4% | 18.62%
TOTAL | 1623171.91 | 1583004.56 | 40167.35 | 97.53% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 197 | Water Closets | 197 | Kitchen Sinks | 190
Total Fixtures | 1,349 | Lavatories | 197 | Dishwashers | 188
Fixtures / Unit | 6.85 | Tubs | 197 | Auto Washers | 188
Floors | 6 | Stacks | 46 | Duration | 25 mo
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 11820 | 12360 | 7355 | 5005 | 59.51%
101 | Takeoff & Purchase Labor | 13790 | 15790 | 16582.5 | -792.5 | 105%
110 | Underground Labor | 6080 | 7830 | 7731 | 99 | 98.74%
111 | Garage Labor | 55870 | 67410 | 50128.5 | 17281.5 | 74.36%
112 | Canout Labor | 12300 | 12860 | 10087.5 | 2772.5 | 78.44%
113 | Foundation Drain Labor | 520 | 520 | 520.5 | -0.5 | 100.1%
120 | Roughin Labor | 244060 | 261060 | 387658.09 | -126598.09 | 148.5%
130 | Finish Labor | 41255 | 45665 | 45395.28 | 269.72 | 99.41%
140 | Gas Labor | 7250 | 11400 | 11582.5 | -182.5 | 101.6%
141 | Water Main/Insulation Lab | 29805 | 35505 | 37466.75 | -1961.75 | 105.5%
142 | Mech Room Labor | 5280 | 8650 | 8975 | -325 | 103.8%
MATERIAL
210 | Underground Material | 9825 | 9385 | 7557.66 | 1827.34 | 80.53%
211 | Garage Material | 59640 | 63870 | 41623.99 | 22246.01 | 65.17%
212 | Canout Material | 17220 | 17700 | 13825.36 | 3874.64 | 78.11%
213 | Foundation Material | 1275 | 1275 | 1275.6 | -0.6 | 100%
220 | Roughin Material | 210065 | 212365 | 176561.56 | 35803.44 | 83.14%
230 | Finish Material | 466740 | 483149 | 337546.71 | 145602.29 | 69.86%
240 | Gas Material | 3350 | 6250 | 6984.66 | -734.66 | 111.8%
241 | Water Main/Insulation Mat | 60900 | 60900 | 46749.33 | 14150.67 | 76.76%
242 | Mech Room Material | 12000 | 12000 | 29343.46 | -17343.46 | 244.5%
OVERHEAD
600 | Subcontractor | 25125 | 27425 | 36287 | -8862 | 132.3%
601 | Engineering/Plans | 2000 | 2000 | 7038.38 | -5038.38 | 351.9%
603 | Permits & Licenses | 5000 | 5000 | 10 | 4990 | 0.2%
BURDEN
995 | Payroll Burden | 183990.41 | 206430.98 | 249836.89 | -43405.91 | 121%
998 | Payroll Taxes | 32468.9 | 36371.93 | 44881.34 | -8509.41 | 123.4%
TOTAL | Direct Cost | 1517629.31 | 1623171.91 | 1583004.56 | 40167.35 | 97.53%
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 479050 | 583482.62 | -104432.62 | 121.8% | 36.86% | 2961.8407
Material | 9 | 866894 | 661468.33 | 205425.67 | 76.3% | 41.79% | 3357.7073
Overhead | 3 | 34425 | 43335.38 | -8910.38 | 125.9% | 2.738% | 219.9765
Burden | 2 | 242802.91 | 294718.23 | -51915.32 | 121.4% | 18.62% | 1496.0316
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 261060 | 387658.09 | 126598.09 | 48.49%
995 | Payroll Burden | 206430.98 | 249836.89 | 43405.91 | 21.03%
242 | Mech Room Material | 12000 | 29343.46 | 17343.46 | 144.5%
600 | Subcontractor | 27425 | 36287 | 8862 | 32.31%
998 | Payroll Taxes | 36371.93 | 44881.34 | 8509.41 | 23.4%
601 | Engineering/Plans | 2000 | 7038.38 | 5038.38 | 251.9%
141 | Water Main/Insulation Lab | 35505 | 37466.75 | 1961.75 | 5.525%
101 | Takeoff & Purchase Labor | 15790 | 16582.5 | 792.5 | 5.019%
240 | Gas Material | 6250 | 6984.66 | 734.66 | 11.75%
142 | Mech Room Labor | 8650 | 8975 | 325 | 3.757%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 483149 | 337546.71 | 145602.29 | 30.14%
220 | Roughin Material | 212365 | 176561.56 | 35803.44 | 16.86%
211 | Garage Material | 63870 | 41623.99 | 22246.01 | 34.83%
111 | Garage Labor | 67410 | 50128.5 | 17281.5 | 25.64%
241 | Water Main/Insulation Mat | 60900 | 46749.33 | 14150.67 | 23.24%
100 | Supervision | 12360 | 7355 | 5005 | 40.49%
603 | Permits & Licenses | 5000 | 10 | 4990 | 99.8%
212 | Canout Material | 17700 | 13825.36 | 3874.64 | 21.89%
112 | Canout Labor | 12860 | 10087.5 | 2772.5 | 21.56%
210 | Underground Material | 9385 | 7557.66 | 1827.34 | 19.47%
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Material
Material Spend Analysis
9 material cost codes • $661,468 JDR material • 24 AP vendors • $741,273 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 9385 | 7557.66 | 1827.34 | 80.53% | 1.143% | 38.3638
211 | Garage Material | 63870 | 41623.99 | 22246.01 | 65.17% | 6.293% | 211.2893
212 | Canout Material | 17700 | 13825.36 | 3874.64 | 78.11% | 2.09% | 70.1795
213 | Foundation Material | 1275 | 1275.6 | -0.6 | 100% | 0.1928% | 6.4751
220 | Roughin Material | 212365 | 176561.56 | 35803.44 | 83.14% | 26.69% | 896.2516
230 | Finish Material | 483149 | 337546.71 | 145602.29 | 69.86% | 51.03% | 1713.4351
240 | Gas Material | 6250 | 6984.66 | -734.66 | 111.8% | 1.056% | 35.4551
241 | Water Main/Insulation Mat | 60900 | 46749.33 | 14150.67 | 76.76% | 7.068% | 237.3062
242 | Mech Room Material | 12000 | 29343.46 | -17343.46 | 244.5% | 4.436% | 148.9516
TOTAL | All Material | 866894 | 661468.33 | 205425.67 | 76.3% | 100% | 3357.7073
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Rosen Supply Company, Inc. | 89 | 192671.23 | 25.99% |  |  |  | 2164.8453
Ferguson Enterprises, Inc. | 80 | 153391.68 | 20.69% |  |  |  | 1917.396
Keller Supply Company | 82 | 127204.94 | 17.16% |  |  |  | 1551.2798
Mechanical Sales, Inc. | 3 | 67768.3 | 9.142% |  |  |  | 22589.4333
Franklin Engineering | 11 | 44962.5 | 6.066% |  |  |  | 4087.5
Lotus United, LLC | 5 | 31310 | 4.224% |  |  |  | 6262
Duraseal, Inc. | 4 | 30250 | 4.081% |  |  |  | 7562.5
Consolidated Supply Co. | 22 | 26432.13 | 3.566% |  |  |  | 1201.4605
American Express 3-41000 | 6 | 23106 | 3.117% |  |  |  | 3851
Bank of America CC | 7 | 12653 | 1.707% |  |  |  | 1807.5714
Quality Concrete Products, Inc. | 6 | 8279 | 1.117% |  |  |  | 1379.8333
United Rentals, Inc. | 10 | 5848.82 | 0.789% |  |  |  | 584.882
Manor Hardware & Construction Supply | 6 | 3895 | 0.5254% |  |  |  | 649.1667
Scan2Core, Inc. | 3 | 3080 | 0.4155% |  |  |  | 1026.6667
MAD Concrete Cutting & Coring, Inc. | 3 | 2700 | 0.3642% |  |  |  | 900
Ferguson Enterprises, Inc. #3007 | 5 | 2674.97 | 0.3609% |  |  |  | 534.994
Capital One Credit Card | 7 | 2315.27 | 0.3123% |  |  |  | 330.7529
Kele, Inc | 5 | 715.13 | 0.09647% |  |  |  | 143.026
C.M. Hoskins Company | 1 | 606.32 | 0.08179% |  |  |  | 606.32
Core & Main LP | 4 | 432.88 | 0.0584% |  |  |  | 108.22
Fastenal Company | 5 | 352.83 | 0.0476% |  |  |  | 70.566
Rosen Supply Kirkland | 1 | 257.4 | 0.03472% |  |  |  | 257.4
A.R. Brown Backflow Testing | 2 | 257 | 0.03467% |  |  |  | 128.5
Seton Identification Products | 1 | 108.97 | 0.0147% |  |  |  | 108.97
TOTAL | 368 | 741273.37 | 100%
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
Vendor AP ties to JDR 'by Source: AP' line (741,273.37)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Palma Vides, Hugo | 1772 | 52380 | 29.5598 | Mid
Velasquez Cruz, Denis M | 1400 | 22434 | 16.0243 | Apprentice
Lima Romero, Melvin A | 1318.5 | 28491.5 | 21.609 | Mid
Hubbard, Robert W | 1202.5 | 42720.5 | 35.5264 | Senior
Galdamez, Dagoberto A | 1179 | 15914 | 13.4979 | Apprentice
Cruz Reyes, Jose | 1115 | 14866 | 13.3327 | Apprentice
Amaya Gonzalez, Edilberto A | 1113 | 14840 | 13.3333 | Apprentice
Castro Hernandez, Jose A | 1077 | 20560 | 19.0901 | Mid
Esparza Jimenez, Jose D | 979.5 | 19581.5 | 19.9913 | Mid
Chavarria Lopez, Omar A | 957.5 | 14410 | 15.0496 | Apprentice
Benites Portillo, Marvin E | 927 | 12051 | 13 | Apprentice
Lovo, German G | 863 | 11471.5 | 13.2926 | Apprentice
Palma Vides, Jorge A | 788 | 10427 | 13.2322 | Apprentice
Sepulveda Gonzalez, Alfredo | 679.5 | 17707 | 26.0589 | Mid
McCabe, Thomas C | 674.5 | 13982 | 20.7294 | Mid
Gonzalez Hernandez, Josue | 664.5 | 11227.5 | 16.8962 | Apprentice
Rodriguez Rodriguez, Aminadab N | 663 | 8660 | 13.0618 | Apprentice
Sanders, Allen O | 614.5 | 20278.5 | 33 | Senior
Rivera, Jorge A | 598.5 | 12145 | 20.2924 | Mid
Rodriguez Bonilla, Lisandro | 566 | 7370 | 13.0212 | Apprentice
Quintanilla, Esteban R | 543 | 17960 | 33.0755 | Senior
Vaughan, Tyler J | 531 | 9091 | 17.1205 | Apprentice
Anzora, William | 491 | 7074 | 14.4073 | Apprentice
Castaneda Martinez, Gustavo | 474.5 | 14162.5 | 29.8472 | Mid
Gerard, Jeffrey S | 459.5 | 18221 | 39.654 | Senior
Eliassen, Cory H | 428 | 5564 | 13 | Apprentice
Holmes, Anthony R | 315.5 | 4969.5 | 15.7512 | Apprentice
Walker, Craig M | 278 | 4170 | 15 | Apprentice
Reyes Cruz, Denis A | 276.5 | 3895 | 14.0868 | Apprentice
Ascencio, Jose L | 268 | 3484 | 13 | Apprentice
Cruz Guzman, Joel A | 267 | 3471 | 13 | Apprentice
Meza Fuentes, Erick A | 238 | 5410 | 22.7311 | Mid
Reyes, Robert J | 200 | 3000 | 15 | Apprentice
Soto Cruz, Jovani | 184 | 3304 | 17.9565 | Apprentice
Donelson, Richard T | 148.5 | 6682.5 | 45 | Senior
Barnhart, Joseph N | 143.5 | 4466.5 | 31.1254 | Senior
Cortes Mendiola, Victor H | 136 | 3808 | 28 | Mid
Kinssies, Jr, John E | 135 | 2112 | 15.6444 | Apprentice
Wilson, Garret A | 133.5 | 1889.5 | 14.1536 | Apprentice
Hubbard, Dustin R | 133.5 | 1778.5 | 13.3221 | Apprentice
Salazar, Hajdar L | 130 | 2080 | 16 | Apprentice
Ayers, Jordan L | 128 | 1912 | 14.9375 | Apprentice
Montenegro, Carlos E | 122 | 1952 | 16 | Apprentice
Monico Brambila, Jesus S | 104 | 1768 | 17 | Apprentice
Castaneda Juarez, Edgar D | 98 | 1568 | 16 | Apprentice
Taylor, Evan R | 96 | 1248 | 13 | Apprentice
Castaneda Juarez, Gustavo | 82.5 | 1320 | 16 | Apprentice
Gerard, Mitchell J | 66 | 885 | 13.4091 | Apprentice
Whitaker, Daniel J | 55.5 | 721.5 | 13 | Apprentice
Veley, Nathaniel S | 52 | 1508 | 29 | Mid
Aguilar, Tony A | 48 | 624 | 13 | Apprentice
Paco Leyva, Orlando | 25 | 425 | 17 | Apprentice
Gerard, Jordan E | 12 | 156 | 13 | Apprentice
TOTAL (53 workers) | 25955.5 | 512197.5 | 19.7337
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 6 | 3111.5 | 110329 | 11.99%
Mid | 11 | 8000 | 189735.5 | 30.82%
Apprentice | 36 | 14844 | 212133 | 57.19%
B. WAGE STATISTICS
Blended Gross Wage | 19.7337 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 33.8349 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.7146 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 13 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 489.7264 |  |  | Crew continuity indicator
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 181.5 | 0.6333% | 0.92132
Takeoff & Purchasing | 101 | 401.5 | 1.401% | 2.0381
Underground | 110 | 338 | 1.179% | 1.7157
Garage | 111 | 2333.5 | 8.142% | 11.8452
Canout | 112 | 407 | 1.42% | 2.066
Foundation Drain | 113 | 21 | 0.07327% | 0.1066
Roughin | 120 | 19733.75 | 68.85% | 100.1713
Finish | 130 | 2328.5 | 8.124% | 11.8198
Gas | 140 | 529 | 1.846% | 2.6853
Water Main / Insulation | 141 | 2007 | 7.003% | 10.1878
Mech Room | 142 | 380 | 1.326% | 1.9289
TOTAL |  | 28660.75 | 100% | 145.486
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 145.486 | hrs |  | Labor hours per residential unit
Hours / Fixture | 21.2459 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 74.9006 | $ |  | Top-line per labor hour
Profit / Hour | 19.6681 | $ |  | Bottom-line per labor hour
Units / Month | 7.88 | units |  | Build velocity
Fixtures / Month | 53.96 | fix |  | Fixture install pace
Hours / Month | 1146.43 | hrs |  | Monthly labor burn
Revenue / Month | 85868.32 | $ |  | Monthly billing rate
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## PO Commitments
Purchase Order Commitments
198 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $661,468
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 30 | 15.15%
31 | 120+220 Roughin | 42 | 21.21%
32 | 130+230 Trim/Finish | 30 | 15.15%
40 | 141+241 Water Main/Ins | 3 | 1.515%
41 | 140+240 Gas | 23 | 11.62%
OTHER | Unclassified | 70 | 35.35%
TOTAL |  | 198 | 100% | 661468.33
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 66 | 33.33%
KELLER | 49 | 24.75%
FEI | 42 | 21.21%
OTHER | 21 | 10.61%
CONSOLIDATED | 7 | 3.535%
MANOR | 6 | 3.03%
MECH SALES | 3 | 1.515%
FASTENAL | 3 | 1.515%
PIKE | 1 | 0.5051%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 661468.33
Unique PO Count |  |  | 198
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
20 pay apps (18 Rooster + 2 Portage Bay) • Original $2,002,285 + $144,423 COs = $2,146,708
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 2002285
Change Orders (net) |  |  |  |  | 144423
Final Contract Value |  |  |  |  | 2146708
Retainage (5%) |  |  |  |  | 103985
Net Paid to OWP |  |  |  |  | 2042723
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2014-04-20 | 44400 | 2220 | 42180 | 42180 | 1.965%
2 | 2014-05-20 | 22600 | 1130 | 21470 | 63650 | 2.965%
3 | 2014-07-17 | 33600 | 1680 | 31920 | 95570 | 4.452%
4 | 2014-08-19 | 23701 | 1185.05 | 22515.95 | 118085.95 | 5.501%
5 | 2014-09-18 | 79600 | 3980 | 75620 | 193705.95 | 9.023%
6 | 2014-10-20 | 73100 | 3655 | 69445 | 263150.95 | 12.26%
7 | 2014-11-17 | 73185 | 3659.25 | 69525.75 | 332676.7 | 15.5%
8 | 2014-12-15 | 142120 | 7106 | 135014 | 467690.7 | 21.79%
9 | 2015-01-20 | 545668 | 27283.4 | 518384.6 | 986075.3 | 45.93%
10 | 2015-02-19 | 188377 | 9418.85 | 178958.15 | 1165033.45 | 54.27%
11 | 2015-03-19 | 306651 | 15332.55 | 291318.45 | 1456351.9 | 67.84%
12 | 2015-04-20 | 160471 | 8023.55 | 152447.45 | 1608799.35 | 74.94%
13 | 2015-05-19 | 137507 | 6875.35 | 130631.65 | 1739431 | 81.03%
14 | 2015-06-18 | 91158 | 4557.9 | 86600.1 | 1826031.1 | 85.06%
15 | 2015-07-20 | 48802 | 2440.1 | 46361.9 | 1872393 | 87.22%
16 | 2015-08-20 | 50566 | 2528.3 | 48037.7 | 1920430.7 | 89.46%
17 | 2015-09-18 | 23479 | 1173.95 | 22305.05 | 1942735.75 | 90.5%
18 | 2015-11-16 | 2958 | 147.9 | 2810.1 | 1945545.85 | 90.63%
PB1 | 2015-08-20 | 28590 | 0 | 28590 | 28590 | 1.332%
PB2 | 2015-09-18 | 3175 | 0 | 3175 | 31765 | 1.48%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 2079708 | 2146708 | -67000 | WITHIN
Retainage | 103985 | 103985 | 0 | TIES
Direct Cost | 1583004.56 | 1641584 | -58579.44 | WITHIN
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Insights
Key Insights — Job #2015 Exxel Pacific Rooster Apts + Portage Bay Cafe
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $563,703 on $2,146,708 revenue = 26.3% gross margin. Direct cost $1,583,005 absorbs 73.7% of revenue.
VENDOR CONCENTRATION | Rosen Supply Company, Inc. alone = $192,671 (26% of all AP) across 89 invoices. Total 24 AP vendors, $741,273 total AP spend.
CREW PROFILE | 53 workers for 28,661 hours = 541 avg hrs/worker. Top 3 workers logged 4,490 hrs combined (16% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 19,734 hrs (69% of all labor) and $387,658 actual. Code 230 Finish Material = $337,547 — 21% of total direct cost.
BUDGET DELIVERY | Revised budget was $1,623,172; actual direct cost $1,583,005 → $40,167 variance (2.5% under revised budget).
CONTRACT GROWTH | Contract grew from $2,002,285 to $2,146,708 — net +$144,423 (7.2%). Retainage of $103,985 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $294,718 on $583,483 labor base = 50.5%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 197 units · 1349 fixtures · 25 months. Revenue/unit $10,897, hours/unit 145.5, profit/unit $2,861.
PRODUCTIVITY | Blended labor rate $20.36/hr. Revenue/hour $75. Profit/hour $20. 1,146 hrs/month burn rate.
FIXTURE DENSITY | 1349 fixtures ÷ 197 units = 6.85 fixtures/unit. Material/fixture $490, labor/fixture $433.
BIGGEST QUESTION
How does this job's 26.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2015 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific Rooster Apts + Portage Bay Cafe | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | Mixed-use 6-story apartments + ground-floor restaurant TI | Profile
Duration (months) | duration_months | 25 | Profile | Apr 2014 – Nov 2015 (~25 months)
Unit Count | unit_count | 197 | Profile
Total Fixtures | total_fixtures | 1349 | Profile
Fixtures per Unit | fixtures_per_unit | 6.8477 | Profile
Contract Value (Orig) | contract_original | 2002285 | Financial
Contract Value (Final) | contract_final | 2146708 | Financial | After change orders
Change Orders ($) | change_orders | 144423 | Financial
Revenue | revenue | 2146708 | Financial
Net Profit | net_profit | 563703.44 | Financial
Gross Margin | gross_margin | 0.26259 | Financial
Direct Cost | direct_cost | 1583004.56 | Financial
Labor Cost | labor_cost | 583482.62 | Labor | Sum of 11 labor codes
Material Cost | material_cost | 661468.33 | Material | Sum of 9 material codes
Overhead Cost | overhead_cost | 43335.38 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 294718.23 | Financial | Codes 995+998
Retainage | retainage | 103985 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 10896.9949 | Financial
Profit per Unit | profit_per_unit | 2861.4388 | Financial
Direct Cost per Unit | cost_per_unit | 8035.5561 | Financial
Labor Cost per Unit | labor_per_unit | 2961.8407 | Labor
Material Cost per Unit | material_per_unit | 3357.7073 | Material
Revenue per Fixture | revenue_per_fixture | 1591.3328 | Financial
Profit per Fixture | profit_per_fixture | 417.8676 | Financial
Cost per Fixture | cost_per_fixture | 1173.4652 | Financial
Labor per Fixture | labor_per_fixture | 432.5297 | Labor
Material per Fixture | material_per_fixture | 490.3398 | Material
Total Labor Hours | total_hours | 28660.75 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 53 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1787% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3064% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.7146 | Labor
Hours per Unit | hours_per_unit | 145.486 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 2125% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 7490% | Productivity
Profit per Hour | profit_per_hour | 1967% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.2718 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.30813 | Cost Mix
Revenue per Month | revenue_per_month | 85868.32 | Productivity
Hours per Month | hours_per_month | 1146.43 | Productivity
Units per Month | units_per_month | 7.88 | Productivity
Total Vendors | total_vendors | 24 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 192671.23 | Material | Rosen Supply Company, Inc.
Top Vendor Concentration | top_vendor_pct | 0.25992 | Material
Total POs | total_pos | 198 | Material | Unique POs by filename
Change Order % | co_pct | 0.072129 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 7490% | Productivity
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (11 codes) | 583482.62 | 583482.62 | 0 | TIES
Material subtotal (9 codes) | 661468.33 | 661468.33 | 0 | TIES
Overhead subtotal (3 codes) | 43335.38 | 43335.38 | 0 | TIES
Burden subtotal (2 codes) | 294718.23 | 294718.23 | 0 | TIES
Direct Cost (all categories) | 1583004.56 | 1583004.56 | 0 | TIES
Revenue (code 999) | 2146708 | 2146708 | 0 | TIES
Net Profit (Revenue - Expenses) | 563703.44 | 563703.44 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 28660.75 | 28660.75 | 0 | TIES
Per-worker hours (sum of PR Regular) | 25955.5 | 28660.75 | -2705.25 | OFF
C. BILLING (SOV) ↔ JDR
Final Contract Value | 2079708 | 2146708 | -67000 | WITHIN
Retainage | 103985 | 103985 | 0 | TIES
Direct Cost | 1583004.56 | 1641584 | -58579.44 | WITHIN
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 741273.37 | 690359 | 50914.37 | OFF
SOURCES
Job #2015 — Exxel Pacific Rooster Apartments + Portage Bay Cafe • GC: Exxel Pacific, Inc.
Canonical source: 2015 Job Detail Report.pdf (255 pages, OWP Sage Timberline export)
Cost codes parsed: 26 (Labor+Material+Overhead+Burden+Revenue)
Billing: ROOSTER AGGREGATE BILLING.xlsx (18 apps) + PORTAGE BAY AGGREGATE BILLING.xlsx (2 apps)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2015
Vendors | 24 |  | Top vendor | Rosen Supply Company, Inc.
Invoices | 368 |  | Top 3 share | 63.85%
Total AP | 741273.37 |  | Source | 2015 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 2014.3298
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Rosen Supply Company, Inc. |  | 89 | 192671.23 | 25.99% | 2164.8453
2 | Ferguson Enterprises, Inc. |  | 80 | 153391.68 | 20.69% | 1917.396
3 | Keller Supply Company |  | 82 | 127204.94 | 17.16% | 1551.2798
4 | Mechanical Sales, Inc. |  | 3 | 67768.3 | 9.142% | 22589.4333
5 | Franklin Engineering |  | 11 | 44962.5 | 6.066% | 4087.5
6 | Lotus United, LLC |  | 5 | 31310 | 4.224% | 6262
7 | Duraseal, Inc. |  | 4 | 30250 | 4.081% | 7562.5
8 | Consolidated Supply Co. |  | 22 | 26432.13 | 3.566% | 1201.4605
9 | American Express 3-41000 |  | 6 | 23106 | 3.117% | 3851
10 | Bank of America CC |  | 7 | 12653 | 1.707% | 1807.5714
11 | Quality Concrete Products, Inc. |  | 6 | 8279 | 1.117% | 1379.8333
12 | United Rentals, Inc. |  | 10 | 5848.82 | 0.789% | 584.882
13 | Manor Hardware & Construction Supply |  | 6 | 3895 | 0.5254% | 649.1667
14 | Scan2Core, Inc. |  | 3 | 3080 | 0.4155% | 1026.6667
15 | MAD Concrete Cutting & Coring, Inc. |  | 3 | 2700 | 0.3642% | 900
16 | Ferguson Enterprises, Inc. #3007 |  | 5 | 2674.97 | 0.3609% | 534.994
17 | Capital One Credit Card |  | 7 | 2315.27 | 0.3123% | 330.7529
18 | Kele, Inc |  | 5 | 715.13 | 0.09647% | 143.026
19 | C.M. Hoskins Company |  | 1 | 606.32 | 0.08179% | 606.32
20 | Core & Main LP |  | 4 | 432.88 | 0.0584% | 108.22
21 | Fastenal Company |  | 5 | 352.83 | 0.0476% | 70.566
22 | Rosen Supply Kirkland |  | 1 | 257.4 | 0.03472% | 257.4
23 | A.R. Brown Backflow Testing |  | 2 | 257 | 0.03467% | 128.5
24 | Seton Identification Products |  | 1 | 108.97 | 0.0147% | 108.97
| TOTAL |  | 368 | 741273.37 | 100% | 2014.3298